## Installation Procedures
NMDC DOC. No.: MDR-001
LOWER ZAKUM LONG TERM DEVELOPMENT PHASE-1 (LZ LTDP-1) NEW MAIN GAS LINE (NMGL) PROJECT
|  | NMDC PROJECT NO. 2369 | [11 empty] | REVISION :
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2025-08-11
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | MethodS TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| MIDLINE TIE-IN INSTALLATION PROCEDURE | 2369-PP-OF-003 | AD-27-G-80020 | A1 |  |  | T-389/23 | 2023-12-27
|  |  |  | 1 |  |  | T-364/24 | 2024-08-14
|  |  |  | 2 |  |  | T-546/24 | 2024-11-07
|  |  |  | 3 |  |  | T-067/25 | 2025-02-06 | 11-Feb-2025 | 2369-NPCC-ADNOC-T-01294 | 2025-02-13 | 11689-E-O-T-EPC-IFC-000059 | 1 - Approved | 2025-02-18 | SAF190-MCE-NPCC-T-075 | 2025-02-18 | SAF190-MCE-NPCC-T-075 | 1-Approved
| ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | 2369-PP-OF-016 | AD-27-G-80046 | A1 |  |  | T-255/23 | 2023-08-30
|  |  |  | 1 |  |  | T-357/23 | 2023-11-28
|  |  |  | 2 |  |  | T-511/24 | 2024-10-17 | 2024-10-18 | 2369-NPCC-ADNOC-T-01111 | 2024-11-04 | 11689-E-O-T-EPC-IFC-000047 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-366/25 | 2025-07-21
| ANCHOR HANDLING AND MOORING PROCEDURE FOR JACK UP BARGES | 2369-PP-OF-017 | AD-27-G-80047 | A1 |  |  | T-263/23 | 2023-09-04
|  |  |  | 1 |  |  | T-358/23 | 2023-11-28 | 2023-12-26 | 2369-NPCC-ADNOC-T-00535 | 2024-01-24 | 11689-E-O-T-EPC-IFR-000061 | 1 - Approved | 2024-01-13 | 2369-NPCC-MCE-T-0003
| ANCHOR HANDLING PROCEDURE FOR WORK BOATS | 2369-PP-OF-018 | AD-27-G-80048 | A1 |  |  | T-267/23 | 2023-09-08
| GROUT BAGS INSTALLATION AND FREE SPAN CORRECTION PROCEDURE | 2369-PP-OF-022 | AD-27-G-80052 | A1 |  |  | T-373/23 | 2023-12-12
|  |  |  | 1 |  |  | T-121/24 | 2024-03-14 | 2024-03-26 | 2369-NPCC-ADNOC-T-00727 | 2024-06-21 | 11689-E-O-T-EPC-IFR-000144 | 2 - Approved with Comments | 2024-05-12 | 2369-NPCC-MCE-T-0015 | 2024-07-10 | SAF190-MCE-NPCC-T-018 | 1-Approved
|  |  |  | 2 |  |  | T-361/25 | 2025-07-14
| METHOD STATEMENT FOR 34" OFFSHORE & ONSHORE PIPELINE PRE-COMMISSIONING WORK | 2369-PP-OF-023 | AD-27-G-80053 | A1 |  |  | T-385/23 | 2023-12-22
|  |  |  | 1 |  |  | T-004/24 | 2024-01-05
|  |  |  | 2 |  |  | T-005/25 | 2025-01-08 | 2025-01-09 | 2369-NPCC-ADNOC-T-01243 | 2025-01-30 | 11689-E-O-T-EPC-IFR-000332 | 3 - Reviewed with comments
|  |  |  | 3 |  |  | T-068/25 | 2025-02-08 | 2025-02-07 | 2369-NPCC-ADNOC-T-01288 | 2025-02-25 | 11689-E-O-T-EPC-IFA-000061 | 3 - Reviewed with comments
|  |  |  | 4 |  |  | T-095/25 | 2025-03-06 | 04-Mar-2025 | 2369-NPCC-ADNOC-T-01315 | 2025-03-11 | 11689-E-O-T-EPC-IFA-000063 | 2 - Approved with Comments
|  |  |  | 5 |  |  | T-125/25 | 2025-03-28 | 2025-03-28 | 2369-NPCC-ADNOC-T-01341 | 2025-04-18 | 11689-E-O-T-EPC-IFA-000064 | 2 - Approved with Comments
|  |  |  | 6 |  |  | T-194/25 | 2025-05-16
| RISER AND TIE IN SPOOLS INSTALLATION PROCEDURE | 2369-PP-OF-024 | AD-27-G-80054 | A1 |  |  | T-005/24 | 2024-01-05
|  |  |  | 1 |  |  | T-472/24 | 2024-09-26
|  |  |  | 2 |  |  | T-548/24 | 2024-11-09 | 2024-11-11 | 2369-NPCC-ADNOC-T-01150 | 2024-12-23 | 11689-E-O-T-EPC-IFR-000310 | 2 - Approved with Comments | 13-Nov-2024 | 2369-NPCC-MCE-T-0056 | 2024-11-27 | SAF190-MCE-NPCC-T-065 | 1-Approved
|  |  |  | 3 |  |  | T-124/25 | 2025-03-28 |  |  | 2025-04-07 | 11689-E-O-T-EPC-IFC-000061 | 1 - Approved | 2025-04-01 | 2369-NPCC-MCE-T-0065
| RP-2 JACKET INSTALLATION PROCEDURE | 2369-PP-OF-025 | AD-27-G-80055 | A1 |  |  | T-370/23 | 2023-12-11
|  |  |  | 1 |  |  | T-330/24 | 2024-07-19 | 2024-07-19 | 2369-NPCC-ADNOC-T-00929 | 2024-07-30 | 11689-E-O-T-EPC-IFR-000176 | 1 - Approved | 2024-07-29 | 2369-NPCC-MCE-T-0028 | 2024-08-01 | SAF190-MCE-NPCC-T-023
| RP-2 DECK INSTALLATION PROCEDURE | 2369-PP-OF-026 | AD-27-G-80056 | A1 |  |  | T-375/23 | 2023-12-13
|  |  |  | 1 |  |  | T-352/24 | 2024-08-07
|  |  |  | 2 |  |  | T-507/24 | 2024-10-15 | 2024-10-18 | 2369-NPCC-ADNOC-T-01115 | 2024-10-21 | 11689-E-O-T-EPC-IFC-000041 | 1 - Approved
| NEW BRIDGE (B15) FROM GPF TO RP-2 INSTALLATION PROCEDURE | 2369-PP-OF-027 | AD-27-G-80057 | A1 |  |  | T-377/23 | 2023-12-18
|  |  |  | 1 |  |  | T-380/24 | 2024-08-21
|  |  |  | 2 |  |  | T-461/24 | 2024-09-24 | 2024-09-25 | 2369-NPCC-ADNOC-T-01067 | 2024-10-11 | 11689-E-O-T-EPC-IFR-000258 | 1 - Approved
| SHORE PULL PROCEDURE | 2369-PP-OF-028 | AD-27-G-80079 | A1 |  |  | T-365/23 | 2023-12-06
|  |  |  | 1 |  |  | T-392/23 | 2023-12-28
|  |  |  | 2 |  |  | T-162/24 | 2024-04-18 | 2024-04-19 | 2369-NPCC-ADNOC-T-00759 | 2024-04-23 | 11689-E-O-T-EPC-IFC-000009 | 1 - Approved | 2024-05-12 | 2369-NPCC-MCE-T-0015 | 2024-05-16 | SAF190-MCE-NPCC-T-011 | 1-Approved
| PIPELINE INSTALLATION MANUAL | 2369-PP-OF-029 | AD-27-G-80080 | A1 |  |  | T-369/23 | 2023-12-11
|  |  |  | 1 |  |  | T-382/23 | 2023-12-20
|  |  |  | 2 |  |  | T-163/24 | 2024-04-18
|  |  |  | 3 |  |  | T-230/24 | 2024-05-30
|  |  |  | 4 |  |  | T-291/24 | 2024-07-01
|  |  |  | 5 |  |  | T-423/24 | 2024-09-12 | 2024-09-19 | 2369-NPCC-ADNOC-T-01057 | 2024-09-19 | 11689-E-O-T-EPC-IFC-000029 | 2 - Approved with Comments
|  |  |  | 6 |  |  | T-584/24 | 2024-12-06
| SLEEPERS INSTALLATION PROCEDURE | 2369-PP-OF-030 | AD-27-G-80081 | A1 |  |  | T-350/23 | 2023-11-16
|  |  |  | 1 |  |  | T-388/23 | 2023-12-27
|  |  |  | 2 |  |  | T-115/24 | 2024-03-12 | 2024-03-12 | 2369-NPCC-ADNOC-T-00689 | 2024-03-21 | 11689-E-O-T-EPC-IFC-000006 | 1 - Approved
| NEW BRIDGE SUPPORT TOWER INSTALLATION PROCEDURE | 2369-PP-OF-031 | AD-27-G-80082 | A1 |  |  | T-372/23 | 2023-12-12
|  |  |  | 1 |  |  | T-166/24 | 2024-04-19
|  |  |  | 2 |  |  | T-289/24 | 2024-07-01
|  |  |  | 3 |  |  | T-438/24 | 2024-09-17
|  |  |  | 4 |  |  | T-449/24 | 2024-09-20 | 2024-10-15 | 2369-NPCC-ADNOC-T-01106 | 2024-10-17 | 11689-E-O-T-EPC-IFC-000038 | 1 - Approved
| METHOD STATEMENT FOR HANDLING OF ANCHORS BY HAMMER HEAD CRANE VESSEL | 2369-PP-OF-036 | AD-27-G-80134 | A1 |  |  | T-265/23 | 2023-09-07
|  |  |  | 1 |  |  | T-359/23 | 2023-11-28 | 2023-12-26 | 2369-NPCC-ADNOC-T-00536 | 2024-01-24 | 11689-E-O-T-EPC-IFR-000058 | 1 - Approved
| FOC TRANSPOOLING PROCEDURE | 2369-PP-OF-046 | AD-27-G-80221 | A1 |  |  | T-270/24 | 2024-06-20
|  |  |  | 1 |  |  | T-333/24 | 2024-07-24 | 2024-07-26 | 2369-NPCC-ADNOC-T-00938 | 2024-07-30 | 11689-E-O-T-EPC-IFR-000174 | 1 - Approved | 2024-07-26 | 2369-NPCC-MCE-T-0027 | 2024-07-29 | SAF190-MCE-NPCC-T-022 | 1-Approved
| METHOD STATEMENT FOR TEMPORARY FOC REEL DRIVING | 2369-PP-OF-049 | AD-27-G-80242 | A1 |  |  | T-272/24 | 2024-06-25
| METHOD STATEMENT FOR CONNECTING GROMMET | 2369-PP-OF-050 | AD-27-G-80243
| METHOD STATEMENT FOR 34” PIPELINE REMEDIAL WORKS | 2369-PP-OF-052 | AD-27-G-80263 | A1 |  |  | T-494/24 | 2024-10-08
|  |  |  | 1 |  |  | T-496/24 | 2024-10-08
|  |  |  | 2 |  |  | T-499/24 | 2024-10-10 | 2024-10-11 | 2369-NPCC-ADNOC-T-01097 | 2024-10-21 | 11689-E-O-T-EPC-IFR-000270 | 1 - Approved | 2024-10-11 | 2369-NPCC-MCE-T-0050 | 2024-10-18 | SAF190-MCE-NPCC-T-055 | 1-Approved
| DEWATERING, DRYING AND NITROGEN PURGING PROCEDURE | 2369-PP-OF-054 | AD-27-G-80275 | A1 |  |  | T-564/24 | 2024-11-26
|  |  |  | A |  |  | T-570/24 | 2024-11-29
| CHEMICAL HANDLING & HYDROTEST WATER DISPOSAL PROCEDURE | 2369-PP-OF-058 | AD-27-G-80286 | 1 |  |  | T-604/24 | 2024-12-31 | 2025-01-09 | 2369-NPCC-ADNOC-T-01244

## Setup Plans & Anchor Patterns
NMDC DOC. No.:
LOWER ZAKUM LONG TERM DEVELOPMENT PHASE-1 (LZ LTDP-1) NEW MAIN GAS LINE (NMGL) PROJECT
|  | NMDC PROJECT NO. 2369 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2025-08-11
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE : | REF | DATE | REF | CODE
| DLB-750 ANCHOR PATTERN DURING SHORE PULL @ DAS ISLAND | 2369-AP-0001 | AD-27-G-80087 | 1 |  |  | T-384/23 | 2023-12-22 | 2024-01-30 | 2369-NPCC-ADNOC-T-00537 | 05-Feb-2024 | 11689-E-O-T-EPC-IFR-000066 | 1 - Approved
| DLB-750 ANCHOR PATTERN DURING LAYING OF 34'' NMGL FROM DAS ISLAND TO MIDLINE TIE-IN @KP 57.000 (OPTION-1) | 2369-AP-0002 | AD-27-G-80088 | 1 |  |  | T-031/24 | 2024-01-25 | 2024-01-25 | 2369-NPCC-ADNOC-T-00596 | 2024-05-29 | 11689-E-O-T-EPC-IFR-000135 | 3 - Reviewed with comments
| DLB-1000 ANCHOR PATTERN DURING MIDLINE TIE-IN @ KP 33.800 | 2369-AP-0003 | AD-27-G-80089 | 1 |  |  | T-597/24 | 2024-12-20
|  |  |  | 2 |  |  | T-060/25 | 2025-02-04 | 2025-02-04 | 2369-NPCC-ADNOC-T-01279 | 2025-02-05 | 11689-E-O-T-EPC-IFR-000343 | 1 - Approved | 2025-02-04 | 2369-NPCC-MCE-T-0061 | 2025-02-18 | SAF190-MCE-NPCC-T-075 | 1-Approved
| DLB-750 ANCHOR PATTERN DURING LAYING OF 34" NMGL FROM ZWSC RP-2 TO MIDLINE TIE-IN @ KP 57.000 (OPTION-1) | 2369-AP-0004 | AD-27-G-80090 | 1 |  |  | T-062/23 | 2024-02-09
|  |  |  | 2 |  |  | T-389-24 | 2024-08-30 | 2024-09-03 | 2369-NPCC-ADNOC-T-01017 | 2024-09-09 | 11689-E-O-T-EPC-IFR-000210 | 1 - Approved
| DLB-1000 ANCHOR PATTERN DURING RISER AND TIE-IN SPOOL INSTALLATION AT ZWSC RP-2 | 2369-AP-0005 | AD-27-G-80091 | 1 |  |  | T-419/24 | 2024-09-12
|  |  |  | 2 |  |  | T-447/24 | 2024-09-20
|  |  |  | 3 |  |  | T-474/24 | 2024-09-27
|  |  |  | 4 |  |  | T-530/24 | 2024-10-28 | 2024-10-29 | 2369-NPCC-ADNOC-T-01131 | 2024-10-30 | 11689-E-O-T-EPC-IFR-000277 | 1 - Approved
| DLS-4200 ANCHOR PATTERN DURING RP-2 DECK INSTALLATION | 2369-AP-0006 | AD-27-G-80092 | 1 |  |  | T-392-24 | 2024-08-30
|  |  |  | 2 |  |  | T-400/24 | 2024-09-03 | 2024-09-03 | 2369-NPCC-ADNOC-T-01016 | 2024-09-24 | 11689-E-O-T-EPC-IFR-000224 | 1 - Approved
| DLS-4200 ANCHOR PATTERN DURING BRIDGE INSTALLATION BETWEEN GPF AND ZWSC RP-2 | 2369-AP-0007 | AD-27-G-80093 | 1 |  |  | T-464/24 | 2024-09-25
|  |  |  | 2 |  |  | T-484/24 | 2024-10-02
|  |  |  | 3 |  |  | T-495/24 | 2024-10-08 | 2024-10-09 | 2369-NPCC-ADNOC-T-01093 | 2024-10-11 | 11689-E-O-T-EPC-IFR-000260 | 1 - Approved
| DLB-750 ANCHOR PATTERN DURING LAYING OF 34'' NMGL FROM DAS ISLAND TO MIDLINE TIE-IN @KP 33.800 (OPTION-2) | 2369-AP-0008 | AD-27-G-80094 | 1 |  |  | T-051/24 | 2024-02-08 | 2024-02-08 | 2369-NPCC-ADNOC-T-00625 | 2024-05-29 | 11689-E-O-T-EPC-IFR-000136 | 3 - Reviewed with comments
| DLB-750 ANCHOR PATTERN DURING MIDLINE TIE-IN @ KP 33.800 (OPTION-2) | 2369-AP-0009 | AD-27-G-80095
| DLB-750 ANCHOR PATTERN DURING LAYING OF 34'' NMGL FROM ZWSC RP-2 TO MIDLINE TIE-IN @ KP 33.800 (OPTION-2) | 2369-AP-0010 | AD-27-G-80096 | 1 |  |  | T-070-24 | 2024-02-13 | 2024-02-15 | 2369-NPCC-ADNOC-T-00634 | 2024-08-19 | 11689-E-O-T-EPC-IFR-000187 | 3 - Reviewed with comments
| SAFEEN-3000 ANCHOR PATTERN DURING LAYING OF 34" NMGL FROM KP 75.931 TO MIDLINE TIE-IN @ KP 33.800 | 2369-AP-0011 | AD-27-G-80097 | 1 |  |  | T-416/24 | 2024-09-12 | 2024-09-05 | 2369-NPCC-ADNOC-T-01020 | 19-Sep-2024 | 11689-E-O-T-EPC-IFR-000219 | 4
| DLS-4200 ANCHOR PATTERN DURING BST DECK INSTALLATION | 2369-AP-0012 | AD-27-G-80098 | 1 |  |  | T-412/24 | 2024-09-10 | 2024-09-10 | 2369-NPCC-ADNOC-T-01025 | 2024-09-23 | 11689-E-O-T-EPC-IFR-000222 | 1 - Approved
| DLB-750 ANCHOR PATTERN DURING START-UP POSITION AT ZWSC RP-2 | 2369-AP-0013 | AD-27-G-80131 | 1 |  |  | T-389-24 | 2024-08-30 | 2024-09-03 | 2369-NPCC-ADNOC-T-01018 | 2024-09-09 | 11689-E-O-T-EPC-IFR-000211 | 1 - Approved
| DLB-1000 ANCHOR PATTERN DURING OTHER ACTIVITIES AT ZWSC RP-2 | 2369-AP-0014 | AD-27-G-80276 | 1 |  |  | T-551/24 | 2024-11-18 | 2024-11-20 | 2369-NPCC-ADNOC-T-01180 | 2024-11-21 | 11689-E-O-T-EPC-IFR-000290 | 3 - Reviewed with comments
| DLB-1000 ANCHOR PATTERN DURING RISER AND TIE-IN SPOOL INSTALLATION AT ZWSC RP-2 | 2369-AP-0015 | AD-27-G-80277 | 1 |  |  | T-552/24 | 2024-11-18
|  |  |  | 2 |  |  | T-032/25 | 2025-01-21 | 2024-11-20 | 2369-NPCC-ADNOC-T-01261 | 2025-01-23 | 11689-E-O-T-EPC-IFR-000330 | 1 - Approved | 2025-01-23 | 2369-NPCC-MCE-T-0060 | 2025-01-23 | SAF190-MCE-NPCC-T-074 | 1-Approved
| SEP-750 ANCHOR PATTERN DURING HOOK-UP WORKS AT GPF | 2369-AP-0101 | AD-27-G-80099
| SEAFOX TRIDENT-1 ANCHOR PATTERN DURING HOOK-UP ACTIVITIES AT RP-2 | 2369-AP-0102 | AD-27-G-80100 | 1 |  |  | T-105/25 | 2025-03-18 | 2025-03-27 | 2369-NPCC-ADNOC-T-01338 | 2025-03-28 | 11689-E-O-T-EPC-IFR-000358 | 1 - Approved
| SEAFOX TRIDENT -1 ANCHOR PATTERN AT RP-1 | 2369-AP-0103 | AD-27-G-80101 | 1 |  |  | T-588/24 | 2024-12-11
| SEAFOX TRIDENT-1 ANCHOR PATTERN AT WIP OPTION 1 , OPTION 2 & OPTION 3 | 2369-AP-0104 | AD-27-G-80102 | 1 |  |  | T-592/24 | 2024-12-13
| SPARE | 2369-AP-0105 | AD-27-G-80103
| SPARE | 2369-AP-0106 | AD-27-G-80104
| SPARE | 2369-AP-0107 | AD-27-G-80105
| SUPPLY VESSEL ANCHOR PATTERN FOR SEP-750 AT GPF PLATFORM | 2369-AP-0201 | AD-27-G-80106 | 1 |  |  | T-016/24 | 2024-01-12 | 2024-01-30 | 2369-NPCC-ADNOC-T-00604 | 2024-02-05 | 11689-E-O-T-EPC-IFR-000068 | 3 - Reviewed with comments
|  | 2369-AP-0202 | AD-27-G-80107
|  | 2369-AP-0203 | AD-27-G-80108
|  | 2369-AP-0204 | AD-27-G-80109
|  | 2369-AP-0205 | AD-27-G-80110
|  | 2369-AP-0206 | AD-27-G-80111
|  | 2369-AP-0207 | AD-27-G-80112
|  | 2369-AP-0208 | AD-27-G-80113
|  | 2369-AP-0209 | AD-27-G-80114
|  | 2369-AP-0210 | AD-27-G-80115
| SAFEEN-3000 SETUP PLAN DURING ZWSC RP-2 JACKET INSTALLATION | 2369-DP-0001 | AD-27-G-80116 | 1 |  |  | T-305/24 | 2024-07-05 | 2024-07-08 | 2369-NPCC-ADNOC-T-00911 | 2024-07-18 | 11689-E-O-T-EPC-IFR-000158 | 1 - Approved |  |  | 2024-08-09 | SAF190-MCE-NPCC-T-024 | 1-Approved
| SAFEEN-3000 SETUP PLAN DURING BST INSTALLATION | 2369-DP-0002 | AD-27-G-80117 | 1 |  |  | T-281/24 | 2024-06-28 | 2024-07-06 | 2369-NPCC-ADNOC-T-00910 | 2024-07-18 | 11689-E-O-T-EPC-IFR-000157 | 1 - Approved |  |  | 2024-08-09 | SAF190-MCE-NPCC-T-024 | 1-Approved
|  | 2369-DP-0003 | AD-27-G-80118
| SAFEEN-3000 SETUP PLAN DURING SHORE PULL @ DAS ISLAND | 2369-DP-0004 | AD-27-G-80119 | 1 |  |  | T-126/24 | 2024-03-18 | 2024-03-18 | 2369-NPCC-ADNOC-T-00705 | 2024-03-21 | 11689-E-O-T-EPC-IFR-000102 | 1 - Approved
| SAFEEN-3000 SETUP PLAN DURING LAYING OF 34" NMGL FROM DAS ISLAND TO MIDLINE TIE-IN @ KP 33.800 | 2369-DP-0005 | AD-27-G-80120 | 1 |  |  | T-133/24 | 2024-03-21 | 2024-03-26 | 2369-NPCC-ADNOC-T-00726 | 2024-04-02 | 11689-E-O-T-EPC-IFR-000110 | 1 - Approved
| SAFEEN-3000 SETUP PLAN DURING LAYING OF 34'' NMGL FROM ZWSC RP-2 (@ KP 12.737 ) TO MIDLINE TIE-IN (@KP 33.800) | 2369-DP-0006 | AD-27-G-80121 | 1 |  |  | T-591/24 | 2024-12-12
|  | 2369-DP-0007 | AD-27-G-80122
| SEP-550 DP SET-UP PLAN DURING HOOK-UP ACTIVITIES @ RP-2 | 2369-DP-0008 | AD-27-G-80123 | 1 |  |  | T-480/24 | 2024-09-30
|  |  |  | 2 |  |  | T-492/24 | 2024-10-07 | 2024-10-25 | 2369-NPCC-ADNOC-T-01126 | 28-Oct-2024 | 11689-E-O-T-EPC-IFR-000274 | 1 - Approved
| SEP-450 DP SET-UP PLAN DURING HOOK-UP ACTIVITIES @ B15 BRIDGE | 2369-DP-0009 | AD-27-G-80124 | 1 |  |  | T-492/24 | 2024-10-07 | 2024-10-22 | 2369-NPCC-ADNOC-T-01120 | 2024-10-23 | 11689-E-O-T-EPC-IFR-000272 | 1 - Approved
|  |  |  | 2 |  |  | T-504/24 | 2024-10-11
| SAFEEN-3000 SET-UP PLAN DURING RISER FENDER INSTALLATION AT ZWSC RP-2 | 2369-DP-0010 | AD-27-G-80125 | 1 |  |  | T-082/25 | 2025-02-27 | 2025-02-27 | 2369-NPCC-ADNOC-T-01313 | 2025-03-04 | 11689-E-O-T-EPC-IFR-000352 | 2 - Approved with Comments | 2025-02-28 | 2369-NPCC-MCE-T-0064
|  | 2369-DP-0011 | AD-27-G-80126

## Sketches
NMDC DOC. No.:
LOWER ZAKUM LONG TERM DEVELOPMENT PHASE-1 (LZ LTDP-1) NEW MAIN GAS LINE (NMGL) PROJECT
|  | NMDC PROJECT NO. 2369 | [6 empty] | REVISION : |  | 0
|  | OFFSHORE Sketches | [6 empty] | DATE : | 2025-08-11
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| DLB-750 ANCHOR PATTERN DURING LAYING OF 34" NMGL FROM ZWSC RP-2 TO MIDLING TIE-IN @ KP 57.000 (OPTION-2) | 2369-AP-0004 |  | 2 |  |  | 2024-08-27 | VSK/AAA
| DLS-4200 ANCHOR PATTERN DURING BRIDGE INSTALLATION BETWEEN GPF AND ZWSC RP-2 | 2369-AP-0007 |  | 1 |  |  | 2024-08-27 | VSK/AAA
| DLS-4200 ANCHOR PATTERN DURING BST DECK INSTALLATION | 2369-AP-0012 |  | 1 |  |  | 2024-08-27 | VSK/AAA
| SAFEEN-3000 ANCHOR PATTERN DURING LAYING OF 34" NMGL FROM KP 75.931 TO MIDLINE TIE-IN @ KP 33.800 | 2369-AP-011 |  | 1 |  |  | 2024-08-28 | DRH/AAA
| DLB-750 ANCHOR PATTERN DURING LAYING OF 34" NMGL FROM ZWSC RP-2 TO MIDLING TIE-IN @ KP 57.000 (OPTION-1) | 2369-AP-0004 |  | 2 |  |  | 2024-08-28 | VKS/AAA
| DLS-4200 ANCHOR PATTERN DURING RP-2 DECK INSTALLATION | 2369-AP-0006 |  | 2 |  |  | 2024-09-02 | VKS/AAA
| DLB-750 ANCHOR PATTERN DURING START-UP POSITION AT ZWSC RP-2 | 2369-AP-0013 |  | 1 |  |  | 2024-08-28 | VKS/AAA
| DLB-750 ANCHOR PATTERN DURING LAYING OF 34'' NMGL FROM ZWSC RP-2 TO MIDLINE TIE-IN @ KP 57.0000 | 2369-AP-0004 |  | 2 |  |  | 2024-08-28 | VKS/AAA
| DLB-750 ANCHOR PATTERN DURING START-UP POSITION AT ZWSC RP-2 | 2369-AP-0004 |  | 1 |  |  | 2024-08-28 | VKS/AAA
| DLB-750 SETUP AT RP-2 | 2369-A3-031 |  | A |  |  | 2024-08-28 | VKS/AAA
| VESSEL POSITIONS AT ZWSC | 2369-A1-022 |  | A |  |  | 2024-09-03 | VKS/AAA
| SAFEEN-3000 POSITIONS DURING PRE-SETTING OF ANCHORS | 2369-A1-023 |  | A |  |  | 2024-09-03 | VKS/KM
| SAFEEN-3000 POSITIONS DURING PRE-SETTING OF ANCHORS | 2369-A1-024 |  | A |  |  | 2024-09-05 | VKS/KM
| PLB-648 POSITIONS DURING PRE-SETTING OF ANCHORS | 2369-A1-025 |  | A |  |  | 2024-09-05 | VKS/KM
| DLB-1000 ANCHOR PATTERN DURING RISER AND TIE-IN SPOOL INSTALLATION AT ZWSC RP-2 | 2369-AP-0015 |  | 1 |  |  | 2024-09-09 | VSK/AAA
| DLS-4200 ANCHOR PATTERN DURING BST DECK INSTALLATION | 2369-AP-0012 |  | 1 |  |  | 2024-09-09 | VSK/AAA
| SEP-550 DP SET-UP PLAN DURING HOOK-UP ACTIVITIES @ RP-2 | 2369-DP-0008 |  | 1 |  |  | 2024-09-13 | VSK/AAA
| DLB-750 ANCHOR PATTERN DURING LAYING OF 34'' NMGL FROM ZWSC RP-2 TO MIDLINE TIE-IN AND DLS-4200 ANCHOR PATTERN DURING RP-2 DECK INSTALLATION | 2369-A1-026 |  | 0 |  |  | 2024-09-17 | VSK/KM
| SEP-450 DP SET-UP PLAN DURING HOOK-UP ACTIVITIES @ B15 BRIDGE | 2369-DP-0009 |  | 1 |  |  | 2024-09-17 | VKS/AAA
| PRE-LAY SEABED RECTIFICATION BY SAND CEMENT BAGS | 2369-A3-032 |  | A |  |  | 2024-09-18 | VKS/KM
| DLB-1000 ANCHOR PATTERN DURING RISER AND TIE-IN SPOOL INSTALLATION AT ZWSC RP-2 | 2369-AP-0005 |  | 2 |  |  | 2024-09-20 | VKS/AAA
| (DLS-4200 Aviation dwgs at RP-2) | 2369-A3-030 |  | A |  |  | 2024-09-19 | NRH/AAA
| (SEP-550 Aviation dwgs at RP-2) | 2369-A3-033 |  | A |  |  | 2024-09-19 | ENH/AAA
| (SEP-550 setup at RP-2) | 2369-DP-0008 |  | 1 |  |  | 2024-09-19 | ENH/AAA
| (SEP-550 Aviation sketches @ ZK 14) | 2722-A3-009 |  | A |  |  | 2024-09-19 | ENH/AAA
| (DLB-1000 ANCHOR PATTERN DURING RISER AND TIE-IN INSTALLATION @ ZWSC RP-2) | 2369-AP-0005 |  | 3 |  |  | 2024-09-26 | VKS/AAA
| SEP-450 AVIATION CLEARANCE AT B15 | 2369-A3-36 |  | A |  |  | 2024-09-26 | ENH/AAA
| (SEP-550 setup at RP-2) | 2369-DP-0008 |  | 2 |  |  | 2024-10-01 | VKS/AAA
| 2369-AP-0015_R1(DLS-4200 AP during Standby Position) | 2369-AP-0015 |  | 1 |  |  | 2024-10-03 | VKS/KM
| (SEP-450 setup at B15 Bridge) | 2369-DP-0009 |  | 2 |  |  | 2024-10-04 | VKS/KM
| DEWATERING FOR 34'' PIPELINE REMEDIAL WORKS | 2369-A3-038 |  | A |  |  | 2024-10-05 | VKS/AT
| (CUT END with Catcher pin & Recovery pin on 34Inch PL) | 2369-A3-037 |  | A |  |  | 2024-10-05 | VKS/KM
| (CUT END with Catcher pin & Recovery pin on 34Inch PL) | 2369-A3-037 |  | 0 |  |  | 2024-10-07 | VKS/RAH
| (Recovery sequence for 34Inch NMGL with Piggybacked Cables) | 2369-A3-039 |  | 0 |  |  | 2024-10-07 | VKS/RAH
| (Investigation sketch for 34Inch NMGL Damage) | 2369-A3-040 |  | 0 |  |  | 2024-10-09 | VKS/KM
| (Schematic arrangement for Dewatering) | 2369-A3-038 |  | B |  |  | 2024-10-09 | VKS/AT
| (SEQUENCE FOR CABLE REEL RECOVERY DURING LAYDOWN) | 2369-A3-041 |  | A |  |  | 2024-10-10 | VKS/KM
| 2369-SAFEEN-3000 position during Temp. laydown of 34" NMGL | 2369-A3-042 |  | A |  |  | 2024-10-14 | VKS/KM
| (DLB-1000 ANCHOR PATTERN DURING RISER AND TIE-IN INSTALLATION @ ZWSC RP-2)-study-2 | 2369-AP-0005 |  | 4 |  |  | 2024-10-15 | VKS/KM
| (DLB-1000 ANCHOR PATTERN DURING OTHER ACTIVITIES @ ZWSC RP-2) | 2369-AP-0016 |  | 1 |  |  | 2024-10-15 | VKS/KM
| (Investigation sketch for 34Inch NMGL | 2369-A3-043 |  | 0 |  |  | 2024-10-18 | VKS/KM
| (DLB-1000 ANCHOR PATTERN DURING RISER FENDER REMOVAL AND INTALLATION @ ZWSC RP-2)_STUDY | 2369-AP-0015 |  | 1 |  |  | 2024-11-04 | EJJ/AAA
| 2369 Safeen-3000 Setup Plan During Laying 34'' NMGL From RP-2 To Midline | 2369-DP-0006 |  | 1 |  |  | 2024-11-06 | VKS/AAA
| (SEAFOX TRIDENT-1 AP at RP-2) | 2369-AP-0102 |  | 1 |  |  | 2024-11-25 | VKS/AAA
| (SEAFOC TRIDENT-1 Aviation Clearance at BST) | 2369-A3-044 |  | A |  |  | 2024-11-25 | VKS/KM
| (SEAFOC TRIDENT-1 Aviation Clearance at RP-1) | 2369-A3-045 |  | A |  |  | 2024-12-06 | VKS/KM
| (SEAFOX TRIDENT-1 AP at RP-1) | 2369-AP-0103 |  | 1 |  |  | 2024-12-06 | VKS/KM
| 2369-AP-0104_R1 (SEAFOX TRIDENT-1 AP at WIP) - Option-1 | 2369-AP-0104 |  | 0 |  |  | 2024-12-12 | VKS/AAA
| (SEAFOC TRIDENT-1 Aviation Clearance at WIP) | 2369-A3-046 |  | A |  |  | 2024-12-12 | VKS/AAA
| (SEAFOX TRIDENT-1 AP at WIP) - Option-1 | 2369-AP-0104 |  | 1 |  |  | 2024-12-12 | VKS/AAA
| (DLB-1000 AP DURING MIDLINE TIE-IN @ KP 33.800M) | 2369-AP-0003 |  | 1 |  |  | 2024-12-18 | EJJ/AAA
| (DLB-1000 AP DURING MIDLINE TIE-IN @ KP 33.800M) | 2369-AP-0003 |  | 1 |  |  | 2024-12-20 | EJJ/AAA
| Sequence for FOC Puling through J-Tube at ZWSC RP-2 location | 2369-A3-034 |  | B |  |  | 2024-12-27 | VKS/AAA
| ANCHOR PATTERN DURING RISER AND TIE-IN INSTALLATION @ ZWSC RP-2) | 2369-AP-0005 |  | 5 |  |  | 2025-01-07 | VKS/AAA
| (DLB-1000 ANCHOR PATTERN DURING WEATHER STANDBY POSITION AT ZWSC RP-2) | 2369-AP-0009 |  | 1 |  |  | 2025-01-15 | VKS/KM
| (DLB-1000 AP DURING MIDLINE TIE-IN @ KP 33.800M) | 2369-AP-0003 |  | 2 |  |  | 4/25/25 | EJJ/AAA
| (SAFEEN-3000 DP setup at RP-2) | 2369-DP-0010 |  | 1 |  |  | 2025-02-17 | VKS/KM
| (SAFEEN-3000 DP SETUP AT RP-2) | 2369-A3-048 |  | A |  |  | 2025-02-17 | VKS/KM
| (SAFEEN-3000 DP setup at RP-2) | 2369-DP-0010 |  | 1 |  |  | 2025-02-17 | VKS/KM
| (SEAFOX TRIDENT-1 AP at RP-2) | 2369-AP-0102 |  | 1 |  |  | 2025-02-20 | VKS/KM
| (SAFEEN-3000-Sequence for FOC Puling through J-Tube) | 2369-A3-050 |  | A |  |  | 2025-03-14 | EJJ/AAA
| (SEAFOX TRIDENT-1 AP at RP-2)_study | 2369-AP-0102 |  | 1 |  |  | 2025-03-17 | EJJ/AAA
| (MP-01 set-up sequence for FOC Puling through J-Tube) | 2369-A3-051 |  | A |  |  | 2025-03-21 | EJJ/AAA