## Installation Procedures
NMDC DOC. No.: MDR-001
EPC WORKS FOR BU HASEER ESP SURFACE FACILITY-PACKAGE - 4
|  | NMDC PROJECT NO. 2891 | [11 empty] | REVISION :
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2025-10-23
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM GLOBAL Maritime
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| METHOD STATEMENT FOR WHT-BH1 AND WHT-BH2 MODULES INSTALLATION | 2891-PP-OF-001 | AD-725-G-00133 | A1 |  |  | IFIR | 2025-01-29
|  |  |  | 1 |  |  | T-073/25 | 2025-02-18 | 2025-02-19 | ALS-17284-TR-1782 | 2025-03-21 | AYP-ALS-17284-TR-1578 | 3. COMMENTED |  |  | 2025-04-10 | GM-PRJ116419-COR-EM-0026 | B. Accepted subject to Comments
|  |  |  | 2 |  |  | T-234/25 | 2025-06-04 |  |  | 2025-06-12 | GM-PRJ116419-DR-CS-0013 R | 3. COMMENTED
|  |  |  | 3 |  |  | T-298/25 | 2025-06-26 |  |  |  | E-mail | Approved
|  |  |  | 4 |  |  | T-349/25 | 2025-07-11 | 2025-07-11 | ALS-17284-TR-2043 | 2025-08-04 | AYP-ALS-17284-TR-1812 | Approved |  |  | 2025-08-04
|  |  |  | 5 |  |  | T-390/25 | 2025-08-05 |  |  |  | AYP-ALS-17284-TR-1822 | Approved
| SPARE | 2891-PP-OF-002
| LIFTING AND INSTALLATION FOR MODULE AT WHT-BH1 BY SAFEEN-3000 MAIN HOIST OF MAIN CRANE (1) | 2891-LOP-0001 | AD-726-G-00131 | 2 |  |  | T-118/25 | 2025-03-27 |  |  | 2025-07-08 | E-mail | Approved
|  |  |  | 3 |  |  |  | 2025-07-12 | 12-07-2025
| LIFTING AND INSTALLATION FOR MODULE AT WHT-BH2 BY SAFEEN-3000 AUXILIARY HOIST OF MAIN CRANE (1) | 2891-LOP-0002 | AD-726-G-00132 | 2 |  |  | T-119/25 | 2025-03-27 |  |  | 2025-07-08 | E-mail | Approved
|  |  |  | 3 |  |  |  | 2025-07-12 | 12-07-2025

## Setup Plans & Anchor Patterns
NMDC DOC. No.:
EPC WORKS FOR BU HASEER ESP SURFACE FACILITY-PACKAGE - 4
|  | NMDC PROJECT NO. 2891 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2025-10-23
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE : | REF | DATE | REF | CODE
| DLS-4200 DP SETUP DURING WHT BH -1 MODULE INSTALLATION | 2891-DP-0001 | AD-726-C-330044 | 1 |  |  | 2025-05-21 | T-206/25
|  |  |  | 2 |  |  | 2025-06-26 | T-300/25 | 2025-07-22 | code-2
|  |  |  | 3 |  |  | 2025-07-04 | T-329/25 | 2025-08-06 | code-1
| DLS-4200 DP SETUP DURING WHT BH -2 MODULE INSTALLATION | 2891-DP-0002 | AD-727-C-330042 | 1 |  |  | 2025-05-21 | T-206/25
|  |  |  | 2 |  |  | 2025-06-26 | T-300/25 | 2025-07-22 | code-2
|  |  |  | 3 |  |  | 2025-07-04 | T-329/25 | 2025-08-06 | code-1
| DLS-4200 SETUP PLAN DURING BH-01 MODULES INSTALLATION | 2891-DP-0003
| DLS-4200 SETUP PLAN DURING BH-02 MODULES INSTALLATION | 2891-DP-0004

## Sketches
NMDC DOC. No.:
EPC WORKS FOR BU HASEER ESP SURFACE FACILITY-PACKAGE - 4
|  | NMDC PROJECT NO. 2891 | [6 empty] | REVISION : |  | 0
|  | OFFSHORE Sketches | [6 empty] | DATE : | 2025-10-23
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| (DLS-4200 Setup at WHT BH-1) | 2891-DP-0001 |  | 3 |  |  | 2025-07-04 | SKV
| (DLS-4200 Setup at WHT BH-2) | 2891-DP-0002 |  | 3 |  |  | 2025-07-04 | SKV

## Incomming DOC and DRG
NMDC DOC. No.:
EPC WORKS FOR BU HASEER ESP SURFACE FACILITY-PACKAGE - 4
|  | NMDC PROJECT NO. 2891 | [5 empty] | REVISION : |  | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [5 empty] | DATE : | 2025-10-23
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV.
Received From BUHASeer
DRAWINGS
| BU HASEER WELLHEAD TOWER NORTH - AREA 727 BH2 ESP MODULE LIFTING AND INSTALLATION |  | AD-727-C-330040 | 1 | 2024-11-04 | drg | @
| WHT-BH1 - BU HASEER WELLHEAD TOWER NORTH - AREA 726 ESP MODULE - BUMPER & GUIDE DETAILS |  | AD-726-C-330041 | 2 | 2024-11-04 | drg
| WHT1 - BU HASEER WELLHEAD TOWER NORTH - AREA 726 ESP MODULE - BUMPER & GUIDE DETAILS (CELLAR DECK) |  | AD-726-C-330041 | 3 | 2024-12-13
| WHT2 - BU HASEER WELLHEAD TOWER NORTH - AREA 727 ESP MODULE - BUMPER & GUIDE DETAILS (CELLAR DECK) |  | AD-727-C-330039 | 2 | 2024-12-13
| STRENGTH ANALYSIS REPORT FOR WHT-BH2 (FOR ESP INSTALLATION IMPACT LOADS) |  | AD-727-G-00127 | 4 | 2025-01-22
| SEAFASTENING ARRANGEMENT_Rev.2 |  | AD-725-C-330008 | 2 | 2025-02-28 | ENG DRAWING FOLDER
| SEAFASTENING STR DRAWINGS_Rev.2 |  | AD-725-C-330009-2 | 2 | 2025-02-28 | ENG DRAWING FOLDER
| SPREADER BAR SEAFASTING ARRANGEMENTS |  | AD-725-C-330017 | 1 | 2025-03-26 | ENG DRAWING FOLDER
| BU HASSER WELLHEAD TOWER NORTH - AREA 726 BH1-ESP MODULE LIFTING AND INSTALLATION |  | AD-726-C-330042 | 2 | 2025-06-04
| DLS 4200 DP SETUP DURING WHT - BH1 MODULE INSTALLATION |  | AD-726-C-330044 | 1 | 2025-06-04
| DLS 4200 DP SETUP DURING WHT - BH2 MODULE INSTALLATION |  | AD-727-C-330042 | 1 | 2025-06-04
| BU HASEER WELLHEAD TOWER NORTH - AREA 725 -ESP MODULE BH1 & BH2 - SLING LAYING ARRANGEMENT |  | AD-725-C-330058 | 2 | 2025-06-04
DOCUMENTS
| STRENGTH ANALYSIS REPORT FOR WHT-BH1 (FOR ESP INSTALLATION IMPACT LOADS) |  | AD-726-C-33003 | 2 | 2024-11-04 | doc
| STRENGTH ANALYSIS REPORT FOR WHT-BH1 (FOR ESP INSTALLATION IMPACT LOADS) |  | AD-726-C-33003 | 3 | 2024-12-13
| STRENGTH ANALYSIS REPORT FOR WHT-BH2 (FOR ESP INSTALLATION IMPACT LOADS) |  | AD-727-C-33003 | 2 | 2024-12-13
| WHT2 - BU HASEER WELLHEAD TOWER NORTH - AREA 727 ESP MODULE - BUMPER & GUIDE DETAILS (CELLAR DECK) |  | AD-727-C-330039 | 3 | 2025-01-22
| SEAFASTNING CALCULATION FOR SPRERADER BAR |  | AD-725-G-00017 | 1 | 2025-03-26