## Installation Procedures
NMDC DOC. No.: MDR-001
EPC WORK FOR UMM SHAIF LONG TERM DEVELOPMENT PHASE-1 (US-LTD-1)
|  | NMDC PROJECT NO. 2035 | [11 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| PRE-ENGINEERING JACKET FACE DIVING SURVEY PROCEDURE | 2035-PP-OF-0004 | AD-26-G-80074 | 1 | 2 |  | T-092/22 | 2022-03-15 | 17-Mar-2022 | 2035-NPCC-ADNOC-T-00039 | 2022-04-01 | E1372-AO-NPCC-T-00039 | 3-Reviewed with Comments
|  |  |  | 2 | 2 |  | T-139/22 | 2022-04-13 | 2022-04-14 | 2035-NPCC-ADNOC-T-00090 | 2022-06-03 | E1372-AO-NPCC-T-00090 | 2-Approved with Comments
|  |  |  | 3 | 2 |  | T-281/22 | 2022-07-07 | 2022-07-12 | 2035-NPCC-ADNOC-T-00225 | 2022-09-01 | E1372-AO-NPCC-T-00225 | 1-Approved
| ANCHOR HANDLING PROCEDURE FOR GRAVITY ANCHORS BY HAMMER HEAD CRANE VESSEL | 2035-PP-OF-0018 | AD-26-G-80088 | 1 | 2 |  | T-096/22 | 2022-03-16 | 2022-03-17 | 2035-NPCC-ADNOC-T-00041 | 2022-03-23 | E1372-AO-NPCC-T-00041 | 1-Approved
|  |  |  | 2 | 2 |  | T-113/22 | 2022-03-29 | 2022-03-31 | 2035-NPCC-ADNOC-T-00063 | 2022-05-25 | E1372-AO-NPCC-T-00063 | 1-Approved | 01-May-2023 | 2035-NPCC-MWS-T-0018 | 2023-05-21 | SAF185-MCE-NPCC-T-012 | 3-Not Accepted. Revise and re-submit
| ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | 2035-PP-OF-0019 | AD-26-G-80089 | A1 |  |  | T-244/23 | 2023-08-15
|  |  |  | 1 | 2 |  | T-245/23 | 2023-08-17 | 2023-08-30 | 2035-NPCC-ADNOC-T-01227 |  |  |  | 2023-08-30 | 2035-NPCC-MWS-T-0050
|  |  |  | 2 | 2 |  | T-532/24 | 2024-11-01 | 2024-11-02 | 2035-NMDC-ADNOC-T-03076 | 2025-11-19 | E1372-E-O-T-EPC-IFR-002613 | 2-Approved with Comments | 2024-11-05 | 2035-NMDC-MWS-T-0220 | 2024-11-19 | SAF185-MCE-NPCC-T-125 | 1-Approved
|  |  |  | 3 | 2 |  | T-559/24 | 2024-11-22 | 2024-11-26 | 2035-NMDC-ADNOC-T-03191 | 2024-12-05 | E1372-E-O-T-EPC-IFA-002538 | 1-Approved | 2024-11-26 | 2035-NMDC-MWS-T-0232 | 2024-11-30 | SAF185-MCE-NPCC-T-131 | -
|  |  |  | 4 | 2 |  | T-351/25 | 2025-07-16 | 2025-04-14 | 2035-NMDC-ADNOC-T-04009 | 2025-08-25 | E1372-E-O-T-EPC-IFA-002689 | 3-Reviewed with Comments | 2025-07-14 | 2035-NMDC-MWS-T-0314 | 2025-07-28 | SAF185-MCE-NPCC-T-178 | 1-Approved
|  |  |  | 5 | 2 |  | T-480/25 | 2025-09-17 | 2025-09-18 | 2035-NMDC-ADNOC-T-04247 | 2025-09-22 | E1372-E-O-T-EPC-IFA-002707 | 2-Approved with Comments | 2025-09-18 | 2035-NMDC-MWS-T-0351
|  |  |  | 6 | 2 |  | T-511/25 |  | 2025-10-16 | 2035-NMDC-ADNOC-T-04313 | 2025-10-13 | E1372-E-O-T-EPC-IFA-002723 | 1-Approved | 2025-10-06 | 2035-NMDC-MWS-T-0359 | 2025-10-09 | SAF185-MCE-NPCC-T-199 | 1-Approved
|  |  |  | 7 | 2 |  | T-606/25 |  | 2025-12-03 | 2035-NMDC-ADNOC-T-04590 | 2005-12-08 | E1372-E-O-T-EPC-IFC-003221 | 1-Approved | 2025-12-03 | 2035-NMDC-MWS-T-0399 | 2025-12-12 | SAF185-MCE-NPCC-T-211 | 1-Approved
|  |  |  | 8 | 2 |  | T-105/26 |  | 2026-03-13 | 2035-NMDC-ADNOC-T-05085 | 2026-03-18 | E1372-E-O-T-EPC-IFA-002839 | 3-Reviewed with Comments | 2026-03-13 | 2035-NMDC-MWS-T-0487 | 2026-03-25 | SAF185-MCE-NPCC-T-223 | 1-Approved
|  |  |  | 9 | 2 |  | T-110/26 | 2026-03-16 | 2026-03-24 | 2035-NMDC-ADNOC-T-05132 | 2026-04-07 | E1372-E-O-T-EPC-IFA-002851 | 1-Approved | 2026-03-24 | 2035-NMDC-MWS-T-0500 | 2026-03-26 | SAF185-MCE-NPCC-T-224 | 1-Approved
|  |  |  | 10 | 2 |  | T-395/26 | 2026-09-08 | 2026-09-08 | 2035-NMDC-ADNOC-T-05673 |  |  |  | 2026-09-08 | 2035-NMDC-MWS-T-0660
| ANCHOR HANDLING AND MOORING PROCEDURE FOR JACK UP BARGES | 2035-PP-OF-0020 | AD-26-G-80090 | A1
|  |  |  | 1 | 2 |  | T-186/23 | 2023-06-19 | 2023-07-01 | 2035-NPCC-ADNOC-T-01070 | 2023-11-15 | E1372-E-O-T-EPC-IFR-001788 | 5-Rejected | 2023-07-01 | 2035-NPCC-MWS-T-0037 | 2024-03-15 | SAF185-MCE-NPCC-T-066 | 1-Approved
|  |  |  | 2 | 2 |  | T-535/24 | 2024-11-02 | 2024-11-08 | 2035-NMDC-ADNOC-T-03102 | 2024-12-12 | E1372-E-O-T-EPC-IFR-002640 | 1-Approved | 2024-11-08 | 2035-NMDC-MWS-T-0224 | 2024-11-25 | SAF185-MCE-NPCC-T-128 | -
| GROUT BAGS INSTALLATION AND FREE SPANS CORRECTION PROCEDURE | 2035-PP-OF-0021 | AD-26-G-80091 | A1 | 2 |  | T-213/24 | 2024-05-21
|  |  |  | 1 | 2 |  | T-275/24 | 2024-06-26 | 2024-07-01 | 2035-NMDC-ADNOC-T-02406 | 2024-07-30 | E1372-E-O-T-EPC-IFR-002367 | 2-Approved with Comments | 2024-07-01 | 2035-NMDC-MWS-T-0166
|  |  |  | 2 | 2 |  | T-366/24 | 2024-08-14 | 2024-08-19 | 2035-NMDC-ADNOC-T-02669 | 2024-09-17 | E1372-E-O-T-EPC-IFR-002465 | 2-Approved with Comments | 2024-08-19 | 2035-NMDC-MWS-T-0184 | 2025-12-11 | SAF185-MCE-NPCC-T-211 | 1-Approved
|  |  |  | 3 | 2 |  | T-589/24 | 2024-12-11 | 2024-12-13 | 2035-NMDC-ADNOC-T-03248 | 2024-12-19 | E1372-E-O-T-EPC-IFA-002551 | 1-Approved | 13-Dec-2024 | 2035-NMDC-MWS-T-0240
|  |  |  | 4 | 2 |  | T-593/25 | 2025-11-25 | 2025-12-25 | 2035-NMDC-ADNOC-T-04714 | 2026-01-06 | E1372-E-O-T-EPC-IFC-003251 | 1-Approved | 2025-12-24 | 2035-NMDC-MWS-T-0427
| SLEEPERS AND FLEXIBLE MATTRESSES INSTALLATION PROCEDURE | 2035-PP-OF-0022 | AD-26-G-80092 | 1 | 2 |  | T-180/23 | 2023-06-09 | 2023-05-17 | 2035-NPCC-ADNOC-T-01025 | 2023-09-11 | E1372-E-O-T-EPC-IFR-001612 | 1-Approved | 2023-06-15 | 2035-NPCC-MWS-T-0030 | 2023-08-31 | SAF185-MCE-NPCC-T-032 | 1-Approved
|  |  |  | 2 | 2 |  | T-312/23 | 2023-10-20 | 2023-10-06 | 2035-NPCC-ADNOC-T-01323 | 2023-12-27 | E1372-E-O-T-EPC-IFA-001997 | 2-Approved with Comments | 2023-10-10 | 2035-NPCC-MWS-T-0066 | 2023-11-21 | AF185-MCE-NPCC-T-044 | 1-Approved
|  |  |  | 3 | 2 |  | T-391/23 | 2023-12-28 | 2024-01-02 | 2035-NPCC-ADNOC-T-01591 | 2024-01-16 | E1372-E-O-T-EPC-IFA-002014 | 1-Approved | 2024-01-03 | 2035-NPCC-MWS-T-0100
|  |  |  | 4 | 2 |  | T-027/24 | 2024-01-19 | 2024-01-23 | 2035-NPCC-ADNOC-T-01665 | 2024-03-26 | E1372-E-O-T-EPC-IFC-001584 | 1-Approved | 2024-01-23 | 2035-NPCC-MWS-T-0105 |  | SAF185-MCE-NPCC-T-055 | 1-Approved
|  |  |  | 5 | 2 |  | T-134/24 | 2024-03-22 | 2024-03-22 | 2035-NPCC-ADNOC-T-01874 | 2024-05-14 | E1372-E-O-T-EPC-IFC-001828 | 1-Approved | 2024-03-22 | 2035-NPCC-MWS-T-0126 | 2024-04-06 | SAF185-MCE-NPCC-T-069 | 1-Approved
|  |  |  | 6 | 2 |  | T-625/25 | 2026-01-02 | 2026-01-03 | 2035-NMDC-ADNOC-T-04737 | 2026-01-06 | E1372-E-O-T-EPC-IFC-003253 | 3-Reviewed with Comments | 2026-01-03 | 2035-NMDC-MWS-T-0434
|  |  |  | 7 | 2 |  | T-015/26 |  | 2026-01-12 | 2035-NMDC-ADNOC-T-04774 | 2026-01-21 | E1372-E-O-T-EPC-IFC-003266 | 2-Approved with Comments | 2026-01-12 | 2035-NMDC-MWS-T-0442 | 2026-01-30 | SAF185-MCE-NPCC-T-218 | 2-Approved with Comments
|  |  |  | 8 | 2 |  | T-060/26 | 2026-02-07 | 2026-02-13 | 2035-NMDC-ADNOC-T-04967 | 2026-03-04 | E1372-E-O-T-EPC-IFC-003317 | 1-Approved | 2026-02-13 | 2035-NMDC-MWS-T-0466 | 2026-01-17 | SAF185-MCE-NPCC-T-220 | 1-Approved
|  |  |  | 9 | 2 |  | T-389/26 | 2026-09-02 | 2026-09-02 | 2035-NMDC-ADNOC-T-05660 |  |  |  | 2026-09-02 | 2035-NMDC-MWS-T-0655
| PIPELINES INSTALLATION MANUAL | 2035-PP-OF-0025 | AD-26-G-80095 | A1 |  |  | T-324/23 | 2023-10-30
|  |  |  | 1 | 2 |  | T-003/24 | 2024-01-05 | 2024-01-08 | 2035-NPCC-ADNOC-T-01627 | 2024-04-15 | E1372-E-O-T-EPC-IFR-002089 | 3-Reviewed with Comments | 2024-01-08 | 2035-NPCC-MWS-T-0102 | 2024-02-13 | SAF185-MCE-NPCC-T-057 | 1-Approved
|  |  |  | 2 | 2 |  | T-220/24 | 2024-05-24 | 2024-05-27 | 2035-NMDC-ADNOC-T-02173 | 2024-07-02 | E1372-E-O-T-EPC-IFA-002259 | 2-Approved with Comments | 2024-05-27 | 2035-NMDC-MWS-T-0149 | 2024-07-23 | SAF185-MCE-NPCC-T-084 | 1-Approved
|  |  |  | 3 | 2 |  | T-372/24 | 2024-08-16 | 2024-08-26 | 2035-NMDC-ADNOC-T-02715 | 2024-10-03 | E1372-E-O-T-EPC-IFA-002437 | 2-Approved with Comments | 2024-08-26 | 2035-NMDC-MWS-T-0188 | 2024-08-29 | SAF185-MCE-NPCC-T-093 | 1-Approved
|  |  |  | 4 | 2 |  | T-541/24 | 2024-11-06 | 2024-11-11 | 2035-NMDC-ADNOC-T-03113 | 2024-12-05 | E1372-E-O-T-EPC-IFA-002534 | 2-Approved with Comments | 2024-11-11 | 2035-NMDC-MWS-T-0225 | 2024-11-19 | SAF185-MCE-NPCC-T-125 | 1-Approved
|  |  |  | 5 | 2 |  | T-086/25 | 2025-03-04 | 2025-03-04 | 2035-NMDC-ADNOC-T-03569 | 2025-03-07 | E1372-E-O-T-EPC-IFA-002607 | 2-Approved with Comments | 2025-03-04 | 2035-NMDC-MWS-T-0258 | 2025-03-18 | SAF185-MCE-NPCC-T-153 | 1-Approved
|  |  |  | 6 | 2 |  | T-174/25 | 2025-05-08 | 2025-06-10 | 2035-NMDC-ADNOC-T-03863 | 2025-07-03 | E1372-E-O-T-EPC-IFA-002662 | 2-Approved with Comments | 2025-05-27 | 2035-NMDC-MWS-T-0295 | 2025-08-11 | SAF185-MCE-NPCC-T-185 | 2-Approved with Comments
|  |  |  | 7 | 2 |  | T-415/25 | 2025-08-20 | 2025-08-20 | 2035-NMDC-ADNOC-T-04146 | 2025-08-29 | E1372-E-O-T-EPC-IFA-002693 | 2-Approved with Comments | 2025-08-20 | 2035-NMDC-MWS-T-0340 | 2025-08-29 | SAF185-MCE-NPCC-T-189 | 2-Approved with Comments
|  |  |  | 8 | 2 |  | T-489/25 | 2025-09-30 | 2025-09-30 | 2035-NMDC-ADNOC-T-04287 | 2025-10-06 | E1372-E-O-T-EPC-IFA-002717 | 2-Approved with Comments | 2025-09-30 | 2035-NMDC-MWS-T-0356 | 2025-10-09 | SAF185-MCE-NPCC-T-199 | 1-Approved
|  |  |  | 9 | 2 |  | T-617/25 |  | 2025-12-11 | 2035-NMDC-ADNOC-T-04651 | 2026-01-06 | E1372-E-O-T-EPC-IFA-002785 | 1-Approved | 2025-12-11 | 2035-NMDC-MWS-T-0412
|  |  |  | 10 | 2 |  | T-158/26 |  | 2026-04-16 | 2035-NMDC-ADNOC-T-05194 | 2026-05-01 | E1372-E-O-T-EPC-IFA-002860 | 1-Approved | 2026-04-16 | 2035-NMDC-MWS-T-0525 | 2026-04-27 | SAF185-MCE-NPCC-T-229 | 1-Approved
| JACKETS INSTALLATION MANUAL | 2035-PP-OF-0026 | AD-26-G-80096 | A1 |  |  | T-107/23 | 2023-03-16
|  |  |  | 1 | 2 |  | T-116/23 | 2023-04-06 | 2023-04-07 | 2035-NPCC-ADNOC-T-00839 | 2023-05-15 | E1372-E-O-T-EPC-IFR-001357 | 2-Approved with Comments | 2023-04-07 | 2035-NPCC-MWS-T-0009 | 2023-04-20 | SAF185-MCE-NPCC-T-009 | 3-Not Accepted. Revise and re-submit
|  |  |  | 2 | 2 |  | T-165/23 | 2023-05-31 | 2023-05-31 | 2035-NPCC-ADNOC-T-00967 | 2023-06-19 | E1372-E-O-T-EPC-IFA-001628 | 2-Approved with Comments | 2023-04-07 | 2035-NPCC-MWS-T-0026 | 2023-06-10 | SAF185-MCE-NPCC-T-016 | 3-Not Accepted. Revise and re-submit
|  |  |  | 3 | 2 |  | T-188/23 | 2023-06-20 | 2023-06-26 | 2035-NPCC-ADNOC-T-01066 | 2023-07-07 | E1372-E-O-T-EPC-IFA-001698 | 2-Approved with Comments | 26-Jun-2023 | 2035-NPCC-MWS-T-0036 | 2023-07-13 | SAF185-MCE-NPCC-T-022 | 1-Approved
|  |  |  | 4 | 2 |  | T-210/23 | 2023-07-13 | 2023-07-14 | 2035-NPCC-ADNOC-T-01100 | 2023-07-17 | E1372-E-O-T-EPC-IFA-001743 | 1-Approved | 2023-07-14 | 2035-NPCC-MWS-T-0038
|  |  |  | 5 | 2 |  | T-216/23 | 2023-07-17 | 2023-07-24 | 2035-NPCC-ADNOC-T-01132 | 2023-07-28 | E1372-E-O-T-EPC-IFC-000411 | 1-Approved | 2023-07-24 | 2035-NPCC-MWS-T-0045
| RISER (STALK-IN) INSTALLATION PROCEDURE | 2035-PP-OF-0027 | AD-26-G-80097 | 1 | 2 |  | T-450/24 | 2024-09-21 | 2024-09-26 | 2035-NMDC-ADNOC-T-02902 | 2024-10-23 | E1372-E-O-T-EPC-IFR-002549 | 2-Approved with Comments | 2024-09-26 | 2035-NMDC-MWS-T-0203 | 2024-10-08 | SAF185-MCE-NPCC-T-107 | 1-Approved
|  |  |  | 2 | 2 |  | T-570/25 | 2025-11-10 | 2025-11-10 | 2035-NMDC-ADNOC-T-04470 | 2025-11-13 | E1372-E-O-T-EPC-IFA-002742 | 3-Reviewed with Comments | 2025-11-10 | 2035-NMDC-MWS-T-0369 | 2025-11-19 | SAF185-MCE-NPCC-T-204 | 1-Approved
|  |  |  | 3 | 2 |  | T-582/25 | 2025-11-20 | 2025-11-20 | 2035-NMDC-ADNOC-T-04533 | 2025-11-24 | E1372-E-O-T-EPC-IFA-002758 | 2-Approved with Comments | 2025-11-20 | 2035-NMDC-MWS-T-0384 | 2025-11-26 | SAF185-MCE-NPCC-T-206 | 1-Approved
|  |  |  | 4 | 2 |  | T-300/26 | 2026-07-15 | 2026-07-16 | 2035-NMDC-ADNOC-T-05479 |  |  |  | 2026-07-16 | 2035-NMDC-MWS-T-0616
| J-TUBE AND ASSOCIATED CLAMPS INSTALLATION PROCEDURE | 2035-PP-OF-0028 | AD-26-G-80098 | 1 | 2 |  | T-256/23 | 2023-08-30 | 2023-08-31 | 2035-NPCC-ADNOC-T-01230 | 2023-10-11 | E1372-E-O-T-EPC-IFR-001694 | 2-Approved with Comments | 2023-08-31 | 2035-NPCC-MWS-T-0051 | 2023-11-09 | SAF185-MCE-NPCC-T-040 | 1-Approved
|  |  |  | 2 | 2 |  | T-305/23 | 2023-10-13 | 2023-10-17 | 2035-NPCC-ADNOC-T-01352 | 2023-11-02 | E1372-E-O-T-EPC-IFA-001927 | 2-Approved with Comments | 2023-10-17 | 2035-NPCC-MWS-T-0068
|  |  |  | 3 | 2 |  | T-332/23 | 2023-11-07 | 2023-11-07 | 2035-NPCC-ADNOC-T-01427 | 2023-11-20 | E1372-E-O-T-EPC-IFA-001958 | 1-Approved | 2023-11-08 | 2035-NPCC-MWS-T-0079
|  |  |  | 4 | 2 |  | T-353/23 | 2023-11-21 | 2023-11-23 | 2035-NPCC-ADNOC-T-01488 | 2023-12-12 | E1372-E-O-T-EPC-IFC-001079 | 1-Approved | 23-Nov-2023 | 2035-NPCC-MWS-T-0084
|  |  |  | 5 | 2 |  | T-365/23 | 2023-12-06 | 2023-12-08 | 2035-NPCC-ADNOC-T-01528 | 2023-12-18 | E1372-E-O-T-EPC-IFC-001117 | 1-Approved | 2023-12-08 | 2035-NPCC-MWS-T-0092 |  | SAF185-MCE-NPCC-T-054 | 1-Approved
|  |  |  | 6 | 2 |  | T-002/24 | 2024-01-04 | 2024-01-08 | 2035-NPCC-ADNOC-T-01628 | 2024-01-11 | E1372-E-O-T-EPC-IFC-001248 | 1-Approved | 08-Dec-2023 | 2035-NPCC-MWS-T-0101 | 2024-02-23 | SAF185-MCE-NPCC-T-062 | 1-Approved
| NEW DECK INSTALLATION PROCEDURE | 2035-PP-OF-0029 | AD-26-G-80099 | A1 |  |  | T-156/24 | 2024-04-05
|  |  |  | 1 | 2 |  | T-407/24 | 2024-09-06 | 2024-09-11 | 2035-NMDC-ADNOC-T-02817 | 2024-09-30 | E1372-E-O-T-EPC-IFR-002506 | 5-Rejected | 06-Sep-2024 | 2035-NMDC-MWS-T-0192 | 25-Oct-2024 | SAF185-MCE-NPCC-T-114 | 1-Approved
|  |  |  | 2 | 2 |  | T-527/24 | 2024-10-25 | 2024-10-30 | 2035-NMDC-ADNOC-T-03061 | 2024-11-01 | E1372-E-O-T-EPC-IFR-002563 | 2-Approved with Comments | 2024-10-30 | 2035-NMDC-MWS-T-0219 | 2024-11-07 | SAF185-MCE-NPCC-T-119 | 1-Approved
|  |  |  | 3 | 2 |  | T-542/24 | 2024-11-11 | 2024-11-14 | 2035-NMDC-ADNOC-T-03153 | 2024-11-20 | E1372-E-O-T-EPC-IFA-002501 | 1-Approved | 2024-11-14 | 2035-NMDC-MWS-T-0229 | 2024-11-19 | SAF185-MCE-NPCC-T-125 | 1-Approved
|  |  |  | 4 | 2 |  | T-078/25 | 2025-03-05 | 2025-03-05 | 2035-NMDC-ADNOC-T-03573 | 2025-03-24 | E1372-E-O-T-EPC-IFA-002618 | 1-Approved | 2025-03-05 | 2035-NMDC-MWS-T-0259 | 2025-03-18 | SAF185-MCE-NPCC-T-153 | 1-Approved
|  |  |  | 5 | 2 |  | T-151/25 | 2025-04-18 | 2025-04-18 | 2035-NMDC-ADNOC-T-03736 | 2025-05-20 | E1372-E-O-T-EPC-IFA-002645 | 1-Approved | 2025-04-18 | 2035-NMDC-MWS-T-0282 | 2025-04-21 | SAF185-MCE-NPCC-T-159 | 1-Approved
|  |  |  | 6 | 2 |  | T-343/25 | 2025-07-11 | 2025-07-09 | 2035-NMDC-ADNOC-T-03992 | 2025-07-28 | E1372-E-O-T-EPC-IFA-002677 | 1-Approved | 2025-07-09 | 2035-NMDC-MWS-T-0309 | 2025-07-28 | SAF185-MCE-NPCC-T-178 | 1-Approved
| RP1 DECK FLOAT OVER INSTALLATION PROCEDURE | 2035-PP-OF-0030 | AD-26-G-80100 | A1 |  |  | T-200/24 | 2024-05-11
|  |  |  | 1 | 2 |  | T-038/25 | 2025-01-23 | 2025-01-27 | 2035-NMDC-ADNOC-T-03436 | 2025-02-25 | E1372-E-O-T-EPC-IFA-002593 | 3-Reviewed with Comments | 2025-01-27 | 2035-NMDC-MWS-T-0254 | 2025-02-05 | SAF185-MCE-NPCC-T-145 | 1-Approved
|  |  |  | 2 | 2 |  | T-139/25 | 2025-04-10 | 2025-04-11 | 2035-NMDC-ADNOC-T-03696 | 2025-06-30 | E1372-E-O-T-EPC-IFR-002946 | 2-Approved with Comments | 2025-04-11 | 2035-NMDC-MWS-T-0272 | 2025-04-16 | SAF185-MCE-NPCC-T-158 | 3-Not Accepted. Revise and re-submit
|  |  |  | 3 | 2 |  | T-357/25 | 2025-07-21 | 2025-07-16 | 2035-NMDC-ADNOC-T-04024 | 2025-07-28 | E1372-E-O-T-EPC-IFA-002679 | 1-Approved | 2025-07-16 | 2035-NMDC-MWS-T-0317 | 2025-07-30 | SAF185-MCE-NPCC-T-179 | 1-Approved
| PIPELINES FLOODING, GAUGING, CLEANING AND HYDROTESTING PROCEDURE | 2035-PP-OF-0031 | AD-26-G-80101 | A1 |  |  | T-175/24 | 2024-04-25
|  |  |  | 1 | 2 |  | T-243/24 | 2024-06-06 | 2024-06-10 | 2035-NMDC-ADNOC-T-02287 | 2024-07-23 | E1372-E-O-T-EPC-IFR-002354 | 3-Reviewed with Comments | 2024-06-10 | 2035-NMDC-MWS-T-0161 | 2024-07-23 | SAF185-MCE-NPCC-T-084 | 1-Approved
|  |  |  | 2 | 2 |  | T-619/25 | 2025-12-11 | 2025-12-17 | 2035-NMDC-ADNOC-T-04661 | 2025-01-12 | E1372-E-O-T-EPC-IFA-002797 | 1-Approved | 2025-12-17 | 2035-NMDC-MWS-T-0413 | 2026-01-02 | SAF185-MCE-NPCC-T-215 | 1-Approved
|  |  |  | 3 | 2 |  | T-221/26 | 2026-05-19 | 2026-05-19 | 2035-NMDC-ADNOC-T-05315 | 2026-05-22 | E1372-E-O-T-EPC-IFC-003356 | 2-Approved with Comments
|  |  |  | 4 | 2 |  | T-237/26 | 2026-06-08 | 2026-06-10 | 2035-NMDC-ADNOC-T-05376 | 2026-06-19 | E1372-E-O-T-EPC-IFC-003372 | 2-Approved with Comments | 2026-06-10 | 2035-NMDC-MWS-T-0582 | 2026-06-15 | SAF185-MCE-NPCC-T-239 | 1-Approved
|  |  |  | 5 |  |  | T-375/26 | 2026-08-26 | 2026-08-26 | 2035-NMDC-ADNOC-T-05644 |  |  |  | 2026-08-26 | 2035-NMDC-MWS-T-0648
| COMPOSITE CABLE INSTALLATION & PULL IN THROUGH J-TUBE PROCEDURE | 2035-PP-OF-0032 | AD-26-G-80102 | A1 |  |  | T-441/25 | 2025-09-18
|  |  |  | 1 | 2 |  | T-076/25 | 2025-02-27 | 2025-03-04 | 2035-NMDC-ADNOC-T-03565 | 2025-03-21 | E1372-E-O-T-EPC-IFR-002798 | 3-Reviewed with Comments | 2025-03-04 | 2035-NMDC-MWS-T-0257 | 2025-04-02 | SAF185-MCE-NPCC-T-157 | 3-Not Accepted. Revise and re-submit
|  |  |  | 2 | 2 |  | T-197/25 |  | 2025-05-18 | 2035-NMDC-ADNOC-T-03833 | 2025-06-19 | E1372-E-O-T-EPC-IFR-002939 | 2-Approved with Comments | 2025-05-19 | 2035-NMDC-MWS-T-0289
|  |  |  | 3 | 2 |  | T-348/25 | 2025-07-11 | 2025-07-17 | 2035-NMDC-ADNOC-T-04030 | 2025-08-25 | E1372-E-O-T-EPC-IFA-002690 | 1-Approved | 2025-07-17 | 2035-NMDC-MWS-T-0322 | 2025-07-30 | SAF185-MCE-NPCC-T-179 | 1-Approved
| OFFSHORE HOOK-UP PROCEDURE | 2035-PP-OF-0033 | AD-26-G-80103
| PIPELINES CALIPER PIGGING PROCEDURE | 2035-PP-OF-0034 | AD-26-G-80104
| PIPELINES INTELLIGANT PIGGING PROCEDURE | 2035-PP-OF-0035 | AD-26-G-80105
| SUBSEA SPOOL INSTALLATION MANUAL | 2035-PP-OF-0038 | AD-26-G-80108 | 1 | 2 |  | T-229/25 | 2025-06-02 | 2025-06-02 | 2035-NMDC-ADNOC-T-03887 | 2025-07-03 | E1372-E-O-T-EPC-IFR-002955 | 3-Reviewed with Comments | 2025-06-02 | 2035-NPCC-MWS-T-0272
|  |  |  | 2 | 2 |  | T-575/25 | 2025-11-14 | 2025-11-17 | 2035-NMDC-ADNOC-T-04499 | 2025-11-20 | E1372-E-O-T-EPC-IFA-002751 | 3-Reviewed with Comments | 2025-11-17 | 2035-NMDC-MWS-T-0378 | 2025-11-20 | SAF185-MCE-NPCC-T-205 | 1-Approved
|  |  |  | 3 | 2 |  | T-591/25 | 2025-11-24 | 2025-11-24 | 2035-NMDC-ADNOC-T-04556 | 2025-11-26 | E1372-E-O-T-EPC-IFA-002760 | 1-Approved | 2025-11-25 | 2035-NMDC-MWS-T-0388 | 2025-12-12 | SAF185-MCE-NPCC-T-211 | 1-Approved
| SURVEY PROCEDURE FOR EXISTING J-TUBE AT PDP | 2035-PP-OF-0042 | AD-26-G-80112 | A1 |  |  | T-156/23 | 2023-05-15
|  |  |  | 1 | 2 |  | T-157/23 | 2023-05-17 | 2023-05-17 | 2035-NPCC-ADNOC-T-00939 | 2023-06-08 | E1372-E-O-T-EPC-IFR-001415 | 2-Approved with Comments | 2023-05-22 | 2035-NPCC-MWS-T-0022
|  |  |  | 2 | 2 |  | T-200/23 | 2023-07-03 | 2023-07-17 | 2035-NPCC-ADNOC-T-01105 | 2023-08-22 | E1372-E-O-T-EPC-IFA-001829 | 2-Approved with Comments | 2023-07-17 | 2035-NPCC-MWS-T-0039
|  |  |  | 3 | 2 |  | T-279/23 | 2023-09-20 | 2023-09-21 | 2035-NPCC-ADNOC-T-01272 |  |  | 1-Approved
|  |  |  | 4 | 2 |  | T-294/23 | 2023-10-05 | 2023-10-06 | 2035-NPCC-ADNOC-T-01324 | 2023-10-24 | E1372-E-O-T-EPC-IFC-000841 | 1-Approved
|  |  |  | 5 | 2 |  | T-013/24 | 2024-01-11 | 2024-01-16 | 2035-NPCC-ADNOC-T-01648 | 2024-01-22 | E1372-E-O-T-EPC-IFC-001310 | 1-Approved | 16-Jan-2024 | 2035-NPCC-MWS-T-0104
| FLANGE MANAGEMENT PROCEDURE FOR SUBSEA FLANGES | 2035-PP-OF-0044 | AD-26-G-80114 | 1 | 2 |  | T-323/23 | 2023-10-31 | 2023-11-01 | 2035-NPCC-ADNOC-T-01396 | 2023-11-23 | E1372-E-O-T-EPC-IFR-001807 | 2-Approved with Comments | 2023-11-01 | 2035-NPCC-MWS-T-0076
|  |  |  | 2 | 2 |  | T-579/25 | 2025-11-17 | 2025-11-17 | 2035-NMDC-ADNOC-T-04505 | 2025-12-05 | E1372-E-O-T-EPC-IFA-002761 | 2-Approved with Comments | 2025-11-17 | 2035-NMDC-MWS-T-0382
|  |  |  | 3 | 2 |  | T-611/25 | 2025-12-05 | 2025-12-08 | 2035-NMDC-ADNOC-T-04621 | 2026-01-06 | E1372-E-O-T-EPC-IFA-002784 | 1-Approved | 2025-12-08 | 2035-NMDC-MWS-T-0403 | 2025-12-11 | SAF185-MCE-NPCC-T-210 | 1-Approved
| MOORING OF CARGO BARGE ALONGSIDE SAFEEN-3000 PROCEDURE | 2035-PP-OF-0045 | AD-26-G-80115 | A1 |  |  | T-211/23 | 2023-07-13
|  |  |  | 1 | 2 |  | T-214/23 | 2023-07-14 | 2023-07-20 | 2035-NPCC-ADNOC-T-01121 | 2023-07-24 | E1372-E-O-T-EPC-IFI-000130 | 2-Approved with Comments
|  |  |  | 2 | 2 |  | T-222/23 | 2023-07-19
|  |  |  | 2 | 2 |  | T-225/23 | 2023-07-27 | 2023-07-26 | 2035-NPCC-ADNOC-T-01142 | 2023-07-27 | E1372-E-O-T-EPC-IFI-000135 | 2-Approved with Comments | 2023-07-20 | 2035-NPCC-MWS-T-0044 | 2023-08-09 | SAF185-MCE-NPCC-T-024 | 1-Approved
| NEW DECK INSTALLATION PROCEDURE (SAFEEN 3000 & DLS 4200) | 2035-PP-OF-0053 | AD-26-G-80123 | A1 |  |  | T-194/24 | 2024-05-08
|  |  |  | 1 | 2 |  | T-112/25 | 2025-03-19 | 2025-03-20 | 2035-NMDC-ADNOC-T-03617 | 2025-03-28 | E1372-E-O-T-EPC-IFR-002823 | 2-Approved with Comments | 2025-03-20 | 2035-NMDC-MWS-T-0268 | 2025-03-26 | SAF185-MCE-NPCC-T-156 | 3-Not Accepted
|  |  |  | 2 | 2 |  | T-296/25 | 2025-06-25 | 2025-07-02 | 2035-NMDC-ADNOC-T-03972 | 2025-07-11 | E1372-E-O-T-EPC-IFA-002664 | 2-Approved with Comments | 02-Jul-2025 | 2035-NMDC-MWS-T-0306
|  |  |  | 3 | 2 |  | T-346/25 | 2025-07-10 | 2025-07-11 | 2035-NMDC-ADNOC-T-04007 | 2025-07-28 | E1372-E-O-T-EPC-IFA-002678 | 1-Approved | 2025-07-11 | 2035-NMDC-MWS-T-0312 | 2025-07-30 | SAF185-MCE-NPCC-T-179 | 1-Approved
| MOORING OF CARGO BARGE ALONGSIDE TELFORD-31 PROCEDURE | 2035-PP-OF-0054 | AD-26-G-80124 | A1 |  |  | T-196/24 | 2024-05-09
|  |  |  | 1 | 2 |  | T-208/24 | 2024-05-17 | 2024-05-17 | 2035-NMDC-ADNOC-T-02132 | 2024-05-29 | E1372-E-O-T-EPC-IFR-002235 | 2-Approved with Comments
|  |  |  | 2 | 2 |  | T-235/24 | 2024-06-04 | 2024-06-05 | 2035-NMDC-ADNOC-T-02249 | 2024-07-09 | E1372-E-O-T-EPC-IFA-002271 | 2-Approved with Comments
|  |  |  | 3 | 2 |  | PMT DIRECT |  | 2026-02-18 | 2035-NMDC-ADNOC-T-05003 | 2026-02-27 | E1372-E-O-T-EPC-IFI-000500 | 4-Information Only
| METHOD OF STATEMENT FOR SEABED SURVEY FOR JACK-UP BARGE SETUP LOCATION | 2035-PP-OF-0062 | AD-26-G-80132 | 1 | 2 |  | T-368/24 | 2024-08-15 | 2024-08-16 | 2035-NMDC-ADNOC-T-02664 | 2024-09-03 | E1372-E-O-T-EPC-IFR-002438 | 2-Approved with Comments
|  |  |  | 2 | 2 |  | T-401/24 | 2024-09-04 | 2024-09-09 | 2035-NMDC-ADNOC-T-02789 | 2024-09-25 | E1372-E-O-T-EPC-IFA-002422 | 1-Approved
| METHOD STATEMENT FOR PREPARATORY WORKS ON RP-1 JACKET PRIOR TOPSIDE FLOAT-OVER | 2035-PP-OF-0077 | AD-26-G-80807 | 1 | 2 |  | T-097/25 | 2025-03-17 | 2025-03-17 | 2035-NMDC-ADNOC-T-03609 | 2025-03-26 | E1372-E-O-T-EPC-IFR-002804 | 2-Approved with Comments | 2025-03-17 | 2035-NMDC-MWS-T-0267 | 2025-03-20 | SAF185-MCE-NPCC-T-154 | 1-Approved
|  |  |  | 2 | 2 |  | T-158/25 | 2025-04-24 | 2025-04-25 | 2035-NMDC-ADNOC-T-03752 | 2025-07-28 | E1372-E-O-T-EPC-IFA-002676 | 1-Approved | 2025-04-24 | 2035-NMDC-MWS-T-0285 | 2025-05-05 | SAF185-MCE-NPCC-T-161 | 1-Approved
|  |  |  | 3 | 2 |  | T-178/25 | 2025-05-01 | Not issued to Client
| METHOD STATEMENT FOR RETRIEVAL, REPAIR AND REINSTATEMENT OF 2" PIGGYBACK CORRIDOR SPOOL | 2035-PP-OF-0095 | AD-26-G-80825 | 1 | 2 |  | T-384/26 | 2026-08-31
| BASELINE SURVEY PROCEDURE (CALIPER AND INTELLIGENT PIGGING FOR USLTDP-1 PIPELINES) | 2035-PP-OF-0096 | SUBCONTARCT DOC | 1 |  |  | SERVER

## Setup Plans & Anchor Patterns
NMDC DOC. No.: MDR-001
EPC WORK FOR UMM SHAIF LONG TERM DEVELOPMENT PHASE-1 (US-LTD-1)
|  | NMDC PROJECT NO. 2035 | [11 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC ENERGY NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE : | REF | DATE | REF | CODE
| ANCHOR PATTERN FOR SAFEEN-3000 DURING PL-3 RISER INSTALLATION AT USSC- RP1 | 2035-AP-0001 | AD-552-C-380018 | 1 |  |  | T-553/25 | 2025-10-30 | 2025-11-01 | 2035-NMDC-ADNOC-T-04444 | 2025-11-21 | E1372-E-O-T-EPC-IFA-002753 | 2-Approved with Comments | 2025-11-01 | 2035-NMDC-MWS-T-0367 | 2025-11-07 | SAF185-MCE-NPCC-T-202 | 1-Approved
|  |  |  | 2 |  |  | T-592/25 | 2025-11-25 | 2025-11-27 | 2035-NMDC-ADNOC-T-04568 | 2025-12-04 | E1372-E-O-T-EPC-IFR-003137 | 1-Approved | 2025-11-27 | 2035-NMDC-MWS-T-0391 | 2025-12-04 | SAF185-MCE-NPCC-T-208 | 1-Approved
| SAFEEN-3000 ANCHOR PATTERN DURING PL-5 RISER INSTALLATION AT USSC-RP1 | 2035-AP-0002 | AD-552-C-380019 | 1 |  |  | T-571/25 | 2025-11-11 | 2025-11-12 | 2035-NMDC-ADNOC-T-04476 | 2025-11-19 | E1372-E-O-T-EPC-IFR-003115 | 2-Approved with Comments | 2025-11-12 | 2035-NMDC-MWS-T-0371 | 20-Nov-2025 | SAF185-MCE-NPCC-T-205 | 1-Approved
|  |  |  | 2 |  |  | T-585/25 | 2025-11-21 | 2025-11-24 | 2035-NMDC-ADNOC-T-04548 | 2025-12-04 | E1372-E-O-T-EPC-IFR-003133 | 1-Approved | 2025-11-24 | 2035-NMDC-MWS-T-0385 | 2025-11-26 | SAF185-MCE-NPCC-T-206 | 1-Approved
| ANCHOR PATTERN FOR SAFEEN-3000 DURING PL-7 RISER INSTALLATION AT USSC- RP1 | 2035-AP-0003 | AD-552-C-380020 | 1 |  |  | T-628/25 | 2025-12-19 | 2025-12-23 | 2035-NMDC-ADNOC-T-04698 | 2026-01-07 | E1372-E-O-T-EPC-IFR-003182 | 2-Approved with Comments | 2025-12-23 | 2035-NMDC-MWS-T-0422 | 2025-12-23 | SAF185-MCE-NPCC-T-214 | 1-Approved
|  |  |  | 2 |  |  | T-102/26 | 2026-03-10 | 2026-03-17 | 2035-NMDC-ADNOC-T-05099 | 2026-03-18 | E1372-E-O-T-EPC-IFA-002840 | 1-Approved | 2026-03-17 | 2035-NMDC-MWS-T-0492
| ANCHOR PATTERN FOR SAFEEN-3000 DURING PL-2 RISER INSTALLATION AT USSC- RP1 | 2035-AP-0004 | AD-552-C-380021 | 1
| ANCHOR PATTERN FOR SAFEEN-3000 DURING PL-8 RISER INSTALLATION AT USSC- RP1 | 2035-AP-0005 | AD-552-C-380022 | 1
| DLB-1000 ANCHOR PATTERN DURING US-159A DECK INSTALLATION | 2035-AP-0007 | AD-768-C-380001 | 1 |  |  | T-550/24 | 2024-11-18 | 2024-11-19 | 2035-NMDC-ADNOC-T-03179 | 2025-01-09 | E1372-E-O-T-EPC-IFR-002674 | 1-Approved | 2024-11-20 | 2035-NMDC-MWS-T-0231 | 21-Nov-2024 | SAF185-MCE-NPCC-T-126 | 1-Approved
|  |  |  | 2 |  |  | T-177/25 | 2025-05-01 | 2025-05-01 | 2035-NMDC-ADNOC-T-03778 | 2025-05-09 | E1372-E-O-T-EPC-IFA-002633 | 1-Approved | 2025-05-01 | 2035-NMDC-MWS-T-0286
| DLB-1000 ANCHOR PATTERN DURING US-142A DECK INSTALLATION | 2035-AP-0009 | AD-769-C-380003 | 1 |  |  | T-550/24 | 2024-11-18 | 2024-11-19 | 2035-NMDC-ADNOC-T-03179 | 2025-01-09 | E1372-E-O-T-EPC-IFR-002674 | 1-Approved | 2024-11-20 | 2035-NMDC-MWS-T-0231 | 2024-11-21 | SAF185-MCE-NPCC-T-126 | 1-Approved
|  |  |  | 2 |  |  | T-156/25 | 2025-04-23 | 2025-04-25 | 2035-NMDC-ADNOC-T-03750 | 2025-05-26 | E1372-E-O-T-EPC-IFR-002902 | 1-Approved | 2025-04-24 | 2035-NMDC-MWS-T-0284 | 2025-05-05 | SAF185-MCE-NPCC-T-161 | 1-Approved
|  |  |  | 3 |  |  | T-359/25 | 2025-07-17 | 2025-07-17 | 2035-NMDC-ADNOC-T-04029 | 2025-07-22 | E1372-E-O-T-EPC-IFR-002981 | 2-Approved with Comments | 2025-07-17 | 2035-NMDC-MWS-T-0321 | 2025-07-28 | SAF185-MCE-NPCC-T-178 | 1-Approved
|  |  |  | 4 |  |  | PMT DIRECT |  | 2026-01-29 | 2035-NMDC-ADNOC-T-04845 | 2026-02-02 | E1372-E-O-T-EPC-IFI-000453 | 4-Information Only
| DLB-1000 ANCHOR PATTERN DURING US-153A DECK INSTALLATION | 2035-AP-0010 | AD-770-C-380002 | 1 |  |  | T-044/25 | 2025-02-24 | 2025-01-27 | 2035-NMDC-ADNOC-T-03437 | 2025-03-27 | E1372-E-O-T-EPC-IFR-002811 | 1-Approved | 2025-01-27 | 2035-NMDC-MWS-T-0255 | 2025-01-28 | SAF185-MCE-NPCC-T-144 | 1-Approved
|  |  |  | 2 |  |  | T-177/25 | 2025-05-01 | 2025-05-01 | 2035-NMDC-ADNOC-T-03779 | 2025-05-26 | E1372-E-O-T-EPC-IFA-002650 | 1-Approved | 2025-05-01 | 2035-NMDC-MWS-T-0287 | 2025-05-05 | SAF185-MCE-NPCC-T-161 | 1-Approved
| DLB-1000 ANCHOR PATTERN DURING BST -S13 DECK INSTALLATION | 2035-AP-0012 | AD-555-C-380001 | 1 |  |  | T-505/24 | 2024-10-15 | 2024-10-15 | 2035-NMDC-ADNOC-T-03002 | 2024-10-21 | E1372-E-O-T-EPC-IFR-002541 | 3-Reviewed with Comments | 2024-10-15 | 2035-NMDC-MWS-T-0215 | 2024-10-18 | SAF185-MCE-NPCC-T-111 | 1-Approved
|  |  |  | 2 |  |  | T-537/24 | 2024-11-04 | 2024-11-05 | 2035-NMDC-ADNOC-T-03077 | 2024-11-18 | E1372-E-O-T-EPC-IFR-002598 | 1-Approved | 2024-11-05 | 2035-NMDC-MWS-T-0221 | 2024-11-07 | SAF185-MCE-NPCC-T-118 | 1-Approved
| CONSTRUCTION BARGE ANCHOR PATTERN DURING INSTALLATION OF B26 & B27 BRIDGES | 2035-AP-0013 | AD-553/554-C-380000
| CONSTRUCTION BARGE ANCHOR PATTERN DURING TIE-IN SPOOL INSTALLATION AT US 159A | 2035-AP-0021 | AD-768-C-380002
| CONSTRUCTION BARGE ANCHOR PATTERN DURING TIE-IN SPOOL INSTALLATION AT US 12B WEST | 2035-AP-0022 | AD-767-C-380003
| CONSTRUCTION BARGE ANCHOR PATTERN DURING TIE-IN SPOOL INSTALLATION AT US 12B EAST | 2035-AP-0023 | AD-767-C-380004
| CONSTRUCTION BARGE ANCHOR PATTERN DURING TIE-IN SPOOL INSTALLATION AT US 142A | 2035-AP-0024 | AD-769-C-380004
| CONSTRUCTION BARGE ANCHOR PATTERN DURING TIE-IN SPOOL INSTALLATION AT US 153A WEST | 2035-AP-0025 | AD-770-C-380003
| CONSTRUCTION BARGE ANCHOR PATTERN DURING TIE-IN SPOOL INSTALLATION AT US 153A EAST | 2035-AP-0026 | AD-770-C-380004
| CONSTRUCTION BARGE ANCHOR PATTERN DURING TIE-IN SPOOL INSTALLATION AT US 19B | 2035-AP-0027 | AD-774-C-380003
| CONSTRUCTION BARGE ANCHOR PATTERN DURING RISER AND TIE-IN SPOOL INSTALLATION AT USSC RP-1 SOUTH | 2035-AP-0028 | AD-552-C-380001
| CONSTRUCTION BARGE (SAFEEN-3000) SETUP DURING PL-3 RISER (STALK-ON) INSTALLATION & MISCELLANEOUS ACTIVITIES AT USSC-RP1 EAST | 2035-AP-0029 | AD-552-C-380002 | 1 | 2 |  | T-577/25 | 2025-11-14
| CONSTRUCTION BARGE ANCHOR PATTERN DURING TIE-IN SPOOL INSTALLATION AT HP-1 | 2035-AP-0030 | AD-771-C-380001
| CONSTRUCTION BARGE ANCHOR PATTERN DURING TIE-IN SPOOL INSTALLATION AT HP-2 EAST | 2035-AP-0031 | AD-772-C-380001
| CONSTRUCTION BARGE ANCHOR PATTERN DURING TIE-IN SPOOL INSTALLATION AT HP-2 WEST | 2035-AP-0032 | AD-772-C-380002
| CONSTRUCTION BARGE ANCHOR PATTERN DURING TIE-IN SPOOL INSTALLATION AT HP-3 | 2035-AP-0033 | AD-773-C-380001
| ANCHOR PATTERN FOR SAFEEN-3000 DURING DAVIT LIFTING AND LATERAL SHIFTING OF PL-3 AT US-142A | 2035-AP-0034 | AD-769-C-380008 | 1 | 2 |  | T-574/25 | 2025-11-13 | 2025-11-14 | 2035-NMDC-ADNOC-T-04487 | 2025-11-19 | E1372-E-O-T-EPC-IFR-003115 | 2-Approved with Comments | 2025-11-14 | 2035-NMDC-MWS-T-0375 | 2025-11-19 | SAF185-MCE-NPCC-T-206 | 1-Approved
|  |  |  | 2 | 2 |  | T-586/25 | 2025-11-21 | 2025-11-24 | 2035-NMDC-ADNOC-T-04550 | 2025-12-10 | E1372-E-O-T-EPC-IFR-003148 | 2-Approved with Comments | 2025-11-24 | 2035-NMDC-MWS-T-0387 | 2025-11-26 | SAF185-MCE-NPCC-T-206 | 1-Approved
|  |  |  | 3 | 2 |  | T-633/25 | 2025-12-23 | 2026-01-07 | 2035-NMDC-ADNOC-T-04757 | 2026-01-15 | E1372-E-O-T-EPC-IFA-002803 | 1-Approved | 2026-01-07 | 2035-NMDC-MWS-T-0436 | 2026-01-19 | SAF185-MCE-NPCC-T-217 | 1-Approved
| CONSTRUCTION BARGE ANCHOR PATTERN DURING LAYING OF 16" WELL FLUID PIPELINE FROM USSC RP-1 TO US 12B INCLUDING 2" PIGGYBACK PIPELINE | 2035-AP-0042 | AD-552/767-C-380000
| CONSTRUCTION BARGE ANCHOR PATTERN DURING LAYING OF 16" WELL FLUID PIPELINE FROM US 19B TO US 153A INCLUDING 2" PIGGYBACK PIPELINE | 2035-AP-0045 | AD-774/770-C-380000
| CONSTRUCTION BARGE ANCHOR PATTERN DURING LAYING OF 16" WELL FLUID PIPELINE FROM USSC RP-1 TO HP-3 | 2035-AP-0046 | AD-552/773-C-380000
| CONSTRUCTION BARGE ANCHOR PATTERN DURING LAYING OF 16" WELL FLUID PIPELINE FROM USSC RP-1 TO HP-3 INCLUDING 2" PIGGYBACK PIPELINES | 2035-AP-0047 | AD-552/773-C-380001
| CONSTRUCTION BARGE ANCHOR PATTERN DURING LAYING OF 16" WELL FLUID PIPELINE FROM HP-3 TO HP-2 INCLUDING 2" PIGGYBACK PIPELINES | 2035-AP-0048 | AD-773/772-C-380000
| CONSTRUCTION BARGE ANCHOR PATTERN DURING LAYING OF 16" WELL FLUID PIPELINE FROM HP-2 TO HP-1 INCLUDING 2" PIGGYBACK PIPELINES | 2035-AP-0049 | AD-772/771-C-380000
| CONSTRUCTION BARGE ANCHOR PATTERN DURING LAYING OF 18" WELL FLUID PIPELINE FROM HP-1 TO HP-2 | 2035-AP-0050 | AD-771/772-C-380000
| CONSTRUCTION BARGE ANCHOR PATTERN DURING LAYING OF 16" WELL FLUID PIPELINE FROM USSC RP-1 TO HP-2 | 2035-AP-0051 | AD-552/772-C-380000
| DLS-4200 ANCHOR PATTERN DURING US-HP3 DECK INSTALLATION | 2035-AP-0083 | AD-773-C-380003 | 1 |  |  | T-335/25 | 2025-07-11 | 2025-07-11 | 2035-NMDC-ADNOC-T-04002 | 2025-08-20 | E1372-E-O-T-EPC-IFR-003017 | 1-Approved | 2025-07-11 | 2035-NMDC-MWS-T-0311 | 2025-07-14 | SAF185-MCE-NPCC-T-173 | 1-Approved
| LB-II ANCHOR PATTREN DURING FLOAT-OVER INSTALLATION OF RP-1 DECK | 2035-AP-0091 | AD-552-C-380004 | 1 |  |  | 2025-01-14 | T-016/25 | 2025-01-14 | 2035-NMDC-ADNOC-T-03393 | 2025-02-26 | E1372-E-O-T-EPC-IFR-002771 | 3-Reviewed with Comments | 2025-01-14 | 2035-NMDC-MWS-T-0248 | 2025-01-24 | SAF185-MCE-NPCC-T-143 | 1-Approved
|  |  |  | 2 |  |  | T-148/25 | 2025-04-17 | 2025-04-17 | 2035-NMDC-ADNOC-T-03724 | 2025-08-01 | E1372-E-O-T-EPC-IFA-002682 | 3-Reviewed with Comments | 2025-04-17 | 2035-NMDC-MWS-T-0281 | 2025-07-21 | SAF185-MCE-NPCC-T-159 | 1-Approved
|  |  |  | 3 |  |  | T-386/25 | 2025-08-05 | 2025-08-05 | 2035-NMDC-ADNOC-T-04088 | 2025-08-13 | E1372-E-O-T-EPC-IFR-003010 | 1-Approved | 2025-08-05 | 2035-NMDC-MWS-T-0328 | 2025-08-06 | SAF185-MCE-NPCC-T-182 | 1-Approved
| ANCHOR PATTERN FOR BARGE SEP-750 DURING HOOK-UP WORKS AT CSP-1 | 2035-AP-0101 | AD-502-C-380000 | 2 |  |  | T-478/24 | 2024-09-30 | 2024-09-30 | 2035-NMDC-ADNOC-T-02922 | 2024-10-14 | E1372-E-O-T-EPC-IFA-002451 | 1-Approved | 2024-09-30 | 2035-NMDC-MWS-T-0204 | 2024-10-01 | SAF185-MCE-NPCC-T-104 | 1-Approved
| JACK-UP BARGE ANCHOR PATTERN DURING HOOK-UP WORKS AT WIP-2 | 2035-AP-0102 | AD-186-C-380000 | 1 |  |  | T-071/25 | 2025-02-14 | 2025-02-14 | 2035-NMDC-ADNOC-T-03509 | 2025-02-19 | E1372-E-O-T-EPC-IFR-002763 | 3-Reviewed with Comments
|  |  |  | 2 |  |  | T-104/25 | 2025-03-19 | 2025-03-19 | 2035-NMDC-ADNOC-T-03616 | 2025-03-28 | E1372-E-O-T-EPC-IFR-002822 | 3-Reviewed with Comments
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-02-11 | 2035-NMDC-ADNOC-T-04942 | 2026-02-12 | E1372-E-O-T-EPC-IFI-000490 | 4-Information Only
| JACK-UP BARGE SETUP PLAN DURING HOOK-UP WORKS AT US-159 | 2035-AP-0112 | AD-290-C-380002 | 3 |  |  | T-502/24 | 2024-10-11 | 2024-11-15 | 2035-NMDC-ADNOC-T-02982 | 2024-11-15 | E1372-E-O-T-EPC-IFR-002597 | 1-Approved | 2025-09-11 | 2035-NMDC-MWS-T-0212 | 21-Oct-2024 | SAF185-MCE-NPCC-T-109 | 1-Approved
| JACK-UP BARGE SETUP PLAN DURING PREPARATORY & HOOK-UP WORKS AT US-153 | 2035-AP-0121 | AD-288-C-380002 | 3 |  |  | T-513/24 | 2024-10-18 | 2024-10-23 | 2035-NMDC-ADNOC-T-02964 | 2024-11-04 | E1372-E-O-T-EPC-IFR-002564 | 1-Approved | 2024-10-09 | 2035-NMDC-MWS-T-0210
|  |  |  | 4 |  |  | T-063/26 | 2026-02-10 | 2026-02-11 | 2035-NMDC-ADNOC-T-04941 | 2026-03-04 | E1372-E-O-T-EPC-IFR-003230 | 3-Reviewed with Comments
| JACK-UP BARGE ANCHOR PATTERN DURING HOOK-UP WORKS AT US-19/19A | 2035-AP-0122 | AD-334-C-380000 | 1 |  |  | T-007/25 | 2025-01-08 | 2025-01-10 | 2035-NMDC-ADNOC-T-03381 | 2025-01-20 | E1372-E-O-T-EPC-IFR-002714 | 3-Reviewed with Comments | 2025-01-10 | 2035-NMDC-MWS-T-0244 | 2025-01-23 | SAF185-MCE-NPCC-T-142 | 1-Approved
|  |  |  | 2 |  |  | T-094/25 | 2025-03-05 | 2025-03-05 | 2035-NMDC-ADNOC-T-03574 | 2025-03-28 | E1372-E-O-T-EPC-IFR-002819 | 3-Reviewed with Comments | 2025-03-05 | 2035-NMDC-MWS-T-0260 | 2025-03-18 | SAF185-MCE-NPCC-T-153 | 1-Approved
|  |  |  | 3 |  |  | T-142/25 | 2025-04-14 | 2025-04-14 | 2035-NMDC-ADNOC-T-03688 | 2025-07-21 | E1372-E-O-T-EPC-IFR-002850 | 1-Approved | 2025-04-11 | 2035-NMDC-MWS-T-0271 | 2025-04-16 | SAF185-MCE-NPCC-T-158 | 1-Approved
| JACK-UP BARGE ANCHOR PATTERN DURING HOOK-UP WORKS AT US-142 | 2035-AP-0123 | AD-289-C-380000 | 3 |  |  | T-497/24 | 2024-10-08 | 2024-11-18 | 2035-NMDC-ADNOC-T-02965 | 2024-12-05 | E1372-E-O-T-EPC-IFR-002633 | 1-Approved | 2024-10-09 | 2035-NMDC-MWS-T-0211 | 2024-12-05 | SAF185-MCE-NPCC-T-109 | 1-Approved
| JACK-UP BARGE SETUP PLAN DURING HOOK-UP WORKS AT US-12 | 2035-AP-0124 | AD-160-C-380001 | 1 |  |  | T-013/25 | 2025-01-10 | 2025-01-10 | 2035-NMDC-ADNOC-T-03383 | 2025-01-20 | E1372-E-O-T-EPC-IFR-002715 | 3-Reviewed with Comments | 2025-01-10 | 2035-NMDC-MWS-T-0246 | 23-Jan-2025 | SAF185-MCE-NPCC-T-142 | 1-Approved
| JACK-UP BARGE SETUP PLAN DURING PREPARATORY ACTIVITIES AT US-142 | 2035-AP-0126 | AD-288-C-380003 | 3 |  |  | T-553/24 | 2024-11-19 | 2024-11-19 | 2035-NMDC-ADNOC-T-03177 | 2024-12-05 | E1372-E-O-T-EPC-IFR-002635 | 1-Approved | 2025-11-19 | 2035-NMDC-MWS-T-0230 | 21-Nov-2024 | SAF185-MCE-NPCC-T-126 | 1-Approved
| JACK-UP BARGE SETUP PLAN DURING PREPARATORY ACTIVITIES AT US-159 | 2035-AP-0127 | AD-288-C-380004 | 1 |  |  | T-383/24 | 2024-08-23 | 2024-09-06 | 2035-NMDC-ADNOC-T-02780 | 24-Sep-2024 | E1372-E-O-T-EPC-IFR-002491 | 3-Reviewed with Comments | 2024-09-12 | 2035-NMDC-MWS-T-0193
|  |  |  | 2 |  |  | T-425/24 | 2024-09-13 | 2024-09-16 | 2035-NMDC-ADNOC-T-02840 | 2024-10-15 | E1372-E-O-T-EPC-IFR-002524 | 2-Approved with Comments | 2024-09-16 | 2035-NMDC-MWS-T-0200 | 2024-09-25 | SAF185-MCE-NPCC-T-101 | 1-Approved
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-02-11 | 2035-NMDC-ADNOC-T-04943 | 2026-02-12 | E1372-E-O-T-EPC-IFI-000488 | 4-Information Only
| DLB-1000 ANCHOR PATTERN DURING B-26 BRIDGE INSTALLATION | 2035-AP-0128 | AD-502-C-380005 | 1 |  |  | T-505/24 | 2024-10-15 | 2024-10-15 | 2035-NMDC-ADNOC-T-03003 | 2024-10-21 | E1372-E-O-T-EPC-IFR-002540 | 3-Reviewed with Comments | 2024-10-15 | 2035-NMDC-MWS-T-0216 | 2024-10-18 | SAF185-MCE-NPCC-T-111 | 1-Approved
|  |  |  | 2 |  |  | T-538/24 | 2024-11-04 | 2024-11-05 | 2035-NMDC-ADNOC-T-03078 | 2024-11-18 | E1372-E-O-T-EPC-IFR-002599 | 1-Approved | 2024-11-05 | 2035-NMDC-MWS-T-0222 | 07-Nov-2024 | SAF185-MCE-NPCC-T-118 | 1-Approved
| DLB-1000 ANCHOR PATTERN DURING BRIDGE B27 (RP-1 TO BST S-13) INSTALLATION | 2035-AP-0129 | AD-552-C-380006
| HEA KRAKEN SET UP AT RP-1 | 2035-AP-0130 | AD-552-C-380014
| HEA KRAKEN SET UP AT West side of RP-1 | 2035-AP-0131 | AD-552-C-380015 | 1 |  |  | T-394/25 | 2025-08-06 | 2025-08-07 | 2035-NMDC-ADNOC-T-04098 |  |  |  | 2025-08-07 | 2035-NMDC-MWS-T-0329 | 2025-08-08 | SAF185-MCE-NPCC-T-184 | 1-Approved
|  |  |  | 2 |  |  | T-450/25 | 2025-09-03 | 2025-09-03 | 2035-NMDC-ADNOC-T-04199 | 2025-10-01 | E1372-E-O-T-EPC-IFR-003070 | 3-Reviewed with Comments | 2025-09-03 | 2035-NMDC-MWS-T-0345 | 2025-09-08 | SAF185-MCE-NPCC-T-193 | 1-Approved
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-02-11 | 2035-NMDC-ADNOC-T-04944 | 2026-02-12 | E1372-E-O-T-EPC-IFI-000490 | 4-Information Only
| HEA KRAKEN SET UP AT BST-S13 | 2035-AP-0132 | AD-555-C-380007
| MUTAWA-401 SETUP AT USSC-B16 | 2035-AP-0136 | AD-186-C-380003 | 1 |  |  | T-563/25 | 2025-11-04 | 2025-11-04 | 2035-NMDC-ADNOC-T-04454 | 2025-11-26 | E1372-E-O-T-EPC-IFI-003129 | 1-Approved
| DIXIE PATRIOT SET-UP PLAN DURING HOOK-UP WORKS AT US-12 | 2035-AP-0137 | AD-377-C-380004 | 1
| DIXIE PATRIOT SET-UP PLAN DURING HOOK-UP WORKS AT US-19 | 2035-AP-0138 | AD-379-C-380003 | 1
| SAFEEN-3000 ANCHOR PATTERN DURING PL-8 AND PL-2 STALK- ON RISER INSTALLATIONS AT USSC- RP1 | 2035-AP-0139 | AD-552-C-380028 | 1
| SEP-650 ANCHOR PATTERN AT RP-1 WEST SIDE | 2035-AP-0140 | AD-552-C-380029 | 1 |  |  | T-135/26 | 2026-04-01 | 2026-04-03 | 2035-NMDC-ADNOC-T-05162 | 2026-04-07 | E1372-E-O-T-EPC-IFR-003272 | 2-Approved with Comments | 2026-04-03 | 2035-NMDC-MWS-T-0516 | 2026-06-23 | SAF185-MCE-NPCC-T-240 | 2-Approved with Comments
| ANCHOR PATTERN FOR DLB-750 DURING LAYING OF PL-1, 16" WELL FLUID PIPELINE FROM US 159A TO US 12B INCLUDING 2" PIGGYBACK PIPELINE | 2035-AP-0141 | AD-768/767-C-380002 | 1 |  |  | T-232/26 | 2026-06-01 | 2026-06-02 | 2035-NMDC-ADNOC-T-05348 | 2026-07-31 | E1372-E-O-T-EPC-IFR-003373 | 4-Information Only | 2026-06-02 | 2035-NMDC-MWS-T-0574
| ANCHOR PATTERN FOR DLB-750 DURING LAYING OF PL-4, 16" WELL FLUID PIPELINE FROM US 19B TO US 153A INCLUDING 2" PIGGYBACK PIPELINE | 2035-AP-0142 | AD-774/770-C-380002 | 1 |  |  | T-232/26 | 2026-06-01 | 2026-06-02 | 2035-NMDC-ADNOC-T-05349 | 2026-06-12 | E1372-E-O-T-EPC-IFR-003330 | 3-Reviewed with Comments | 2026-06-02 | 2035-NMDC-MWS-T-0575
| SEP-750 SET-UP PLAN DURING HOOK-UP WORKS AT US -19A | 2035-AP-0143 | AD-334-C-380001 | 1 |  |  | T-200/26 | 2026-05-11
| SEP-650 SET UP DURING HOOK UP WORKS AT HP-3 | 2035-AP-0144 | AD-773-C-380012 | 1 | 2
| MUTAWA-11 SETUP ALONGSIDE AT RP-1 | 2035-AP-0145 | AD-552-C-380030 | 1 | 2 |  | T-396/26 | 2026-09-07
| WORK ANCHOR PATTERN DURING TOPSIDE SURVEY AT US -159 | 2035-AP-0201 | AD-290-C-380000 | 1 |  |  | T-100/22 | 2022-03-18 | 18-Mar-2022 | 2035-NPCC-ADNOC-T-00044 | 2022-03-23 | E1372-AO-NPCC-T-00044 | 2-Approved with Comments
|  |  |  | 2 |  |  | T-114/22 | 2022-03-29 | 2022-03-30 | 2035-NPCC-ADNOC-T-00057 | 2022-04-05 | E1372-AO-NPCC-T-00057 | 2-Approved with Comments
|  |  |  | 3 |  |  | T-130/22 | 2022-04-08 | 2022-04-08 | 2035-NPCC-ADNOC-T-00078 | 2022-04-13 | E1372-AO-NPCC-T-00078 | 1-Approved
|  |  |  | 4 |  |  | T-166/22 | 2022-04-28 | 29-Apr-2022 | 2035-NPCC-ADNOC-T-00120 | 2022-05-12 | E1372-AO-NPCC-T-00120 | 1-Approved | 2023-03-27 | 2035-NPCC-MWS-T-0006
| WORKBOAT ANCHOR PATTERN DURING TOPSIDE SURVEY AT US -153 | 2035-AP-0202 | AD-288-C-380001 | 1 |  |  | T-102/22 | 2022-03-21 | 2022-03-21 | 2035-NPCC-ADNOC-T-00048 | 2022-04-05 | E1372-AO-NPCC-T-00048 | 2-Approved with Comments
|  |  |  | 2 |  |  | T-131/22 | 2022-04-08 | 2022-04-11 | 2035-NPCC-ADNOC-T-00080 | 2022-04-18 | E1372-AO-NPCC-T-00080 | 1-Approved
|  |  |  | 3 |  |  | T-166/22 | 2022-04-28 | 2022-04-29 | 2035-NPCC-ADNOC-T-00120 | 2022-05-12 | E1372-AO-NPCC-T-00120 | 1-Approved | 2023-03-27 | 2035-NPCC-MWS-T-0006
| WORKBOAT ANCHOR PATTERN DURING TOPSIDE SURVEY AT US -142 | 2035-AP-0203 | AD-289-C-380002 | 1 |  |  | T-102/22 | 2022-03-21 | 2022-03-21 | 2035-NPCC-ADNOC-T-00048 | 2022-04-05 | E1372-AO-NPCC-T-00048 | 2-Approved with Comments
|  |  |  | 2 |  |  | T-131/22 | 2022-04-08 | 2022-04-11 | 035-NPCC-ADNOC-T-00080 | 2022-04-18 | E1372-AO-NPCC-T-00080 | 1-Approved
|  |  |  | 3 |  |  | T-166/22 | 2022-04-28 | 2022-04-29 | 2035-NPCC-ADNOC-T-00120 | 2022-05-12 | E1372-AO-NPCC-T-00120 | 1-Approved | 2023-03-27 | 2035-NPCC-MWS-T-0006
| WORK ANCHOR PATTERN DURING TOPSIDE SURVEY AT US -12 AND US-12A | 2035-AP-0204 | AD-377-C-380003 | 1 |  |  | T-100/22 | 2022-03-18 | 2022-03-18 | 2035-NPCC-ADNOC-T-00045 | 2022-03-23 | E1372-AO-NPCC-T-00045 | 2-Approved with Comments
|  |  |  | 2 |  |  | T-114/22 | 2022-03-29 | 2022-03-30 | 2035-NPCC-ADNOC-T-00058 | 2022-04-05 | E1372-AO-NPCC-T-00058 | 2-Approved with Comments
|  |  |  | 3 |  |  | T-130/22 | 2022-04-08 | 2022-04-08 | 2035-NPCC-ADNOC-T-00079 | 2022-04-13 | E1372-AO-NPCC-T-00079 | 2-Approved with Comments
|  |  |  | 4 |  |  | T-168/22 | 2022-04-29 | 2022-04-29 | 2035-NPCC-ADNOC-T-00119 | 12-May-2022 | E1372-AO-NPCC-T-00119 | 2-Approved with Comments
|  |  |  | 5 |  |  | T-187/22 | 2022-05-13 | 2022-05-17 | 2035-NPCC-ADNOC-T-00134 | 2022-05-24 | E1372-AO-NPCC-T-00134 | 2-Approved with Comments | 2023-03-27 | 2035-NPCC-MWS-T-0006
| WORKBOAT ANCHOR PATTERN DURING TOPSIDE SURVEY AT US -19 AND US-19A | 2035-AP-0205 | AD-379/334-C-380004 | 1 |  |  | T-102/22 | 2022-03-21 | 2022-03-21 | 2035-NPCC-ADNOC-T-00048 | 2022-04-05 | E1372-AO-NPCC-T-00048 | 2-Approved with Comments
|  |  |  | 2 |  |  | T-131/22 | 2022-04-08 | 2022-04-11 | 2035-NPCC-ADNOC-T-00080 | 2022-04-18 | E1372-AO-NPCC-T-00080 | 1-Approved
|  |  |  | 3 |  |  | T-166/22 | 2022-04-28 | 2022-04-29 | 2035-NPCC-ADNOC-T-00120 | 2022-05-12 | E1372-AO-NPCC-T-00120 | 1-Approved | 2023-03-27 | 2035-NPCC-MWS-T-0006
| WORKBOAT ANCHOR PATTERN DURING PRE ENGINEERING SURVEY AT US-88 | 2035-AP-0206 | AD-284-C-380005 | 1 |  |  | T-111/22 | 2022-03-29 | 2022-03-29 | 2035-NPCC-ADNOC-T-00056 | 28-Apr-2022 | E1372-AO-NPCC-T-00056 | 1-Approved
|  |  |  | 2 |  |  | T-188/22 | 2022-05-17 | 2022-05-17 | 2035-NPCC-ADNOC-T-00135 | 2022-05-24 | E1372-AO-NPCC-T-00135 | 2-Approved with Comments | 2022-03-27 | 2035-NPCC-MWS-T-0006
| WORKBOAT ANCHOR PATTERN DURING PRE ENGINEERING SURVEY AT US-216 | 2035-AP-0207 | AD-424-C-380006 | 1 |  |  | T-111/22 | 2022-03-29 | 2022-03-29 | 2035-NPCC-ADNOC-T-00056 | 2022-04-28 | E1372-AO-NPCC-T-00056 | 1-Approved
|  |  |  | 2 |  |  | T-188/22 | 2022-05-17 | 2022-05-17 | 2035-NPCC-ADNOC-T-00135 | 2022-05-24 | E1372-AO-NPCC-T-00135 | 2-Approved with Comments | 2022-03-27 | 2035-NPCC-MWS-T-0006
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-02-18 | 2035-NMDC-ADNOC-T-04997 | 2026-02-24 | E1372-E-O-T-EPC-IFI-000496 | 4-Information Only
| WORKBOAT ANCHOR PATTERN DURING PRE ENGINEERING SURVEY AT US-218 | 2035-AP-0208 | AD-426-C-380007 | 1 |  |  | T-111/22 | 2022-03-29 | 2022-03-29 | 2035-NPCC-ADNOC-T-00056 | 2022-04-28 | E1372-AO-NPCC-T-00056 | 1-Approved
|  |  |  | 2 |  |  | T-188/22 | 2022-05-17 | 2022-05-17 | 2035-NPCC-ADNOC-T-00135 | 2022-05-24 | E1372-AO-NPCC-T-00135 | 2-Approved with Comments | 2022-03-27 | 2035-NPCC-MWS-T-0006
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-02-18 | 2035-NMDC-ADNOC-T-04998 | 2026-02-24 | E1372-E-O-T-EPC-IFI-000496 | 4-Information Only
| MUTAWA-401 SET-UP AT RP-1/B27 FOR INSTALLING DROP OUT SPOOL(RISER SIDE) | 2035-AP-0209 | AD-552/554-C-380001
| MUTAWA-401 SET-UP AT RP-1 / BRIDGE B27/ BST-13 AT EAST SIDE FOR INSTALLING HOOK-UP SPOOL | 2035-AP-0210 | AD-552/555-C-380001
| ANCHOR PATTERN FOR SEAFOX TRIDENT-1 AT BST-S13 | 2035-AP-0237 | AD-555-C-380006 | 1 |  |  | T-026/25 | 2025-01-17 | 2025-01-20 | 2035-NMDC-ADNOC-T-03413 | 2025-02-06 | E1372-E-O-T-EPC-IFR-002739 | 1-Approved | 2025-01-20 | 2035-NMDC-MWS-T-0252 | 23-Jan-2025 | SAF185-MCE-NPCC-T-142 | 1-Approved
| ANCHOR PATTERN FOR US-218 WITH SEAFOX TRIDENT-1 | 2035-AP-0239 | AD-426-C-380008 | 1 |  |  | T-200/25 | 2025-05-19 | 2025-05-19 | 2035-NMDC-ADNOC-T-03835 | 2025-05-29 | E1372-E-O-T-EPC-IFR-002908 | 2-Approved with Comments
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-02-11 | 2035-NMDC-ADNOC-T-04945 | 2026-02-12 | E1372-E-O-T-EPC-IFI-000488 | 4-Information Only
| ANCHOR PATTERN FOR US-216 WITH SEAFOX TRIDENT-1 | 2035-AP-0240 | AD-424-C-380007 | 1 |  |  | T-200/25 | 2025-05-19 | 2025-05-19 | 2035-NMDC-ADNOC-T-03836 | 2025-05-29 | E1372-E-O-T-EPC-IFR-002908 | 2-Approved with Comments
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-02-11 | 2035-NMDC-ADNOC-T-04946 | 2026-02-12 | E1372-E-O-T-EPC-IFI-000488 | 4-Information Only
| ANCHOR PATTERN FOR US-88 WITH SEAFOX TRIDENT-1 | 2035-AP-0241 | AD-284-C-380006 | 1 |  |  | T-200/25 | 2025-05-19 | 2025-05-19 | 2035-NMDC-ADNOC-T-03837 | 2025-05-29 | E1372-E-O-T-EPC-IFR-002908 | 2-Approved with Comments
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-02-11 | 2035-NMDC-ADNOC-T-04947 | 2026-02-12 | E1372-E-O-T-EPC-IFI-000488 | 4-Information Only
| ANCHOR PATTERN FOR SAPURA-1200 DURING LAYING OF PL-3, 16'' WELL FLUID PIPELINE FROM USSC RP-1 TO US 142A INCLUDING 2'' PIGGYBACK PIPELINE | 2035-AP-0244 | AD-552/769-C-380000 | 1 |  |  | T-266/25 | 2025-06-17 | 2025-06-18 | 2035-NMDC-ADNOC-T-03928 | 2025-07-17 | E1372-E-O-T-EPC-IFR-002978 | 3-Reviewed with Comments | 2025-06-18 | 2035-NMDC-MWS-T-0298 | 2025-06-30 | SAF185-MCE-NPCC-T-170 | 1-Approved
|  |  |  | 2 |  |  | T-353/25 | 2025-07-15 | 2025-07-16 | 2035-NMDC-ADNOC-T-04021 | 2025-09-01 | E1372-E-O-T-EPC-IFR-003032 | 3-Reviewed with Comments | 2025-07-16 | 2035-NMDC-MWS-T-0315 | 2025-08-02 | SAF185-MCE-NPCC-T-181 | 1-Approved
|  |  |  | 3 |  |  | T-496/25 | 2025-09-22 | 2025-09-24 | 2035-NMDC-ADNOC-T-04266 | 2025-09-29 | E1372-E-O-T-EPC-IFR-003065 | 1-Approved | 2025-09-24 | 2035-NMDC-MWS-T-0355
| ANCHOR PATTERN FOR SAPURA-1200 DURING LAYING OF PL-1,16'' WELL FLUID PIPELINE FROM US 19B TO US 153A INCLUDING 2'' PIGGYBACK PIPELINE | 2035-AP-0245 | AD-774/770-C-380001 | 1 |  |  | T-615/25 | 2025-12-10 | 2025-12-17 | 2035-NMDC-ADNOC-T-04671 | 2026-03-30 | E1372-E-O-T-EPC-IFR-003255 | 4-Information Only | 2025-12-17 | 2035-NMDC-MWS-T-0418 | 2026-03-03 | SAF185-MCE-NPCC-T-418 | 1-Approved
| ANCHOR PATTERN FOR SAPURA-1200 DURING LAYING OF PL-5, 16'' WELL FLUID PIPELINE FROM USSC RP-1 TO US-153A INCLUDING 2'' PIGGYBACK PIPELINE | 2035-AP-0246 | AD-552/770-C-380000 | 1 |  |  | T-376/25 | 2025-07-29 | 2025-07-30 | 2035-NMDC-ADNOC-T-04072 | 2025-09-01 | E1372-E-O-T-EPC-IFR-003032 | 3-Reviewed with Comments | 2025-07-30 | 2035-NMDC-MWS-T-0326 | 2025-08-01 | SAF185-MCE-NPCC-T-180 | 1-Approved
|  |  |  | 2 |  |  | T-505/25 | 2025-09-30 | 2025-10-01 | 2035-NMDC-ADNOC-T-04288 | 2025-10-27 | E1372-E-O-T-EPC-IFR-003089 | 2-Approved with Comments | 2025-10-01 | 2035-NMDC-MWS-T-0357 | 2025-10-09 | SAF185-MCE-NPCC-T-199 | 1-Approved
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-02-18 | 2035-NMDC-ADNOC-T-04999 | 2026-02-24 | E1372-E-O-T-EPC-IFI-000496 | 4-Information Only
| ANCHOR PATTERN FOR SAPURA-1200 DURING LAYING OF PL-7 18'' WELL FLUID PIPELINE FROM USSC RP-1 TO HP-2 | 2035-AP-0248 | AD-552/772-C-380001 | 1 |  |  | T-292/25 | 2025-06-25 | 2025-06-25 | 2035-NMDC-ADNOC-T-03955 | 2025-09-01 | E1372-E-O-T-EPC-IFR-003032 | 3-Reviewed with Comments | 2025-06-25 | 2035-NMDC-MWS-T-0304 | 2025-07-07 | SAF185-MCE-NPCC-T-171 | 1-Approved
|  |  |  | 2 |  |  | T-505/25 | 2025-09-30 | 2025-10-01 | 2035-NMDC-ADNOC-T-04289 | 2025-12-24 | E1372-E-O-T-EPC-IFR-003088 | 2-Approved with Comments | 2025-10-01 | 2035-NMDC-MWS-T-0358 | 2025-10-09 | SAF185-MCE-NPCC-T-199 | 1-Approved
|  |  |  | 3 |  |  | T-588/25 | 2025-11-21 | 2025-11-24 | 2035-NMDC-ADNOC-T-04549 | 2025-12-15 | E1372-E-O-T-EPC-IFR-003154 | 3-Reviewed with Comments | 2025-11-24 | 2035-NMDC-MWS-T-0386 | 26-Nov-2025 | SAF185-MCE-NPCC-T-206 | 1-Approved
|  |  |  | 4 |  |  | T-016/26 | 2026-01-12 | 2026-01-14 | 2035-NMDC-ADNOC-T-04795 | 2026-01-16 | E1372-E-O-T-EPC-IFR-003187 | 1-Approved | 2026-01-14 | 2035-NMDC-MWS-T-0444 | 2026-01-30 | SAF185-MCE-NPCC-T-218 | 1-Approved
| ANCHOR PATTERN FOR SAPURA-1200 DURING LAYING OF PL-9, 16'' WELL FLUID PIPELINE FROM USSC RP-1 TO US HP-3 INCLUDING 2'' PIGGYBACK PIPELINE | 2035-AP-0250 | AD-552/773-C-380002 | 1 |  |  | T-594/25 | 2025-11-25 | 2025-11-27 | 2035-NMDC-ADNOC-T-04569 | 2025-12-15 | E1372-E-O-T-EPC-IFR-003154 | 3-Reviewed with Comments | 2025-11-27 | 2035-NMDC-MWS-T-0392 | 2025-12-11 | SAF185-MCE-NPCC-T-209 | 1-Approved
|  |  |  | 2 |  |  | T-097/26 | 2026-03-05 |  |  | 2026-03-30 | E1372-E-O-T-EPC-IFR-003255 | 4-Information Only | 2026-03-05 | 2035-NMDC-MWS-T-0478 | 2026-03-09 | SAF185-MCE-NPCC-T-221 | 1-Approved
| ANCHOR PATTERN FOR SAPURA-1200 DURING LAYING OF PL-10 16'' WATER INJECTION PIPELINE (WITH DUAL 2'' PIGGYBACK) FROM HP-3 TO HP-2 | 2035-AP-0251 | AD-773/772-C-380001 | 1 |  |  | T-568/25 | 2025-11-07 | 2025-11-10 | 2035-NMDC-ADNOC-T-04472 | 2025-11-13 | E1372-E-O-T-EPC-IFR-003108 | 3-Reviewed with Comments | 2025-11-10 | 2035-NMDC-MWS-T-0370
|  |  |  | 2 |  |  | T-045/26 | 2026-01-30 | 2026-02-13 | 2035-NMDC-ADNOC-T-04965 | 2026-02-23 | E1372-E-O-T-EPC-IFA-002821 | 3-Reviewed with Comments | 2026-02-13 | 2035-NMDC-MWS-T-0463 | 2026-01-17 | SAF185-MCE-NPCC-T-220 | 1-Approved
|  |  |  | 3 |  |  | T-088/26 | 2026-02-26 | 2026-02-26 | 2035-NMDC-ADNOC-T-05031 | 2026-03-31 | E1372-E-O-T-EPC-IFA-002843 | 4-Information Only | 2026-02-26 | 2035-NMDC-MWS-T-0476 | 2026-03-09 | sAF185-MCE-NPCC-T-221 | 1-Approved
| ANCHOR PATTERN FOR SAPURA-1200 DURING LAYING OF PL-11, 16" WELL FLUID PIPELINE FROM US-HP-2 TO US-HP1 INCLUDING 2" PIGGYBACK PIPELINE | 2035-AP-0252 | AD-772/771-C-380001 | 1 |  |  | T-098/26 | 2026-03-05 |  |  | 2026-03-13 | E1372-E-O-T-EPC-IFR-003242 | 3-Reviewed with Comments | 2026-03-05 | 2035-NMDC-MWS-T-0479 | 2026-04-03 | SAF185-MCE-NPCC-T-225 | 1-Approved
| HEA TITAN ANCHOR PATTERN DURING HOOK-UP WORKS AT WIP-2/BST-S-06 | 2035-AP-0253 | AD-186-C-380002 | 1 |  |  | T-250/25 | 2025-06-17 | 2025-06-18 | 2035-NMDC-ADNOC-T-03929 | 2025-06-23 | E1372-E-O-T-EPC-IFR-002942 | 3-Reviewed with Comments | 2025-06-18 | 2035-NMDC-MWS-T-0299 | 2025-06-30 | SAF185-MCE-NPCC-T-170 | 1-Approved
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-02-11 | 2035-NMDC-ADNOC-T-04948 | 2026-02-12 | E1372-E-O-T-EPC-IFI-000490 | 4-Information Only
| HEA TITAN ANCHOR PATTERN DURING HOOK-UP WORKS AT WIP-2 & WIP-5 | 2035-AP-0254 | AD-185/186-C-380000 | 1 |  |  | T-250/25 | 2025-06-17 | 2025-06-18 | 2035-NMDC-ADNOC-T-03930 | 2025-06-23 | E1372-E-O-T-EPC-IFR-002942 | 3-Reviewed with Comments | 2025-06-18 | 2035-NMDC-MWS-T-0301 | 2025-06-30 | SAF185-MCE-NPCC-T-170 | 1-Approved
|  |  |  | 2 |  |  | T-401/25 | 2025-08-11 | 2025-08-11 | 2035-NMDC-ADNOC-T-04104 | 2025-08-29 | E1372-E-O-T-EPC-IFR-003029 | 3-Reviewed with Comments | 2025-08-14 | 2035-NMDC-MWS-T-0338 | 2025-08-19 | SAF185-MCE-NPCC-T-187 | 1-Approved
|  |  |  | 3 |  |  | T-638/25 | 2025-12-27 | 2026-01-07 | 2035-NMDC-ADNOC-T-04758 | 2026-01-15 | E1372-E-O-T-EPC-IFA-002804 | 2-Approved with Comments | 2026-01-07 | 2035-NMDC-MWS-T-0437 | 2026-01-19 | SAF185-MCE-NPCC-T-217 | 1-Approved
| JACK-UP BARGE SETUP PLAN DURING HOOK-UP WORKS AT US-142 | 2035-AP-0255 | AD-289-C-380001 | 1 |  |  | T-297/25 | 2025-07-01 | 2025-07-01 | 2035-NMDC-ADNOC-T-03964 | 2025-07-04 | E1372-E-O-T-EPC-IFR-002954 | 1-Approved | 2025-07-01 | 2035-NMDC-MWS-T-0305 |  | SAF185-MCE-NPCC-T-305 | 1-Approved
| DLB-1000 ANCHOR PATTERN DURING PL-3 RISER (STALK-ON) INSTALLATION AT USSC-RP1 | 2035-AP-0257 | AD-552-C-380010 | 1 |  |  | T-333/25 | 2025-07-07 | 2025-07-09 | 2035-NMDC-ADNOC-T-03991 | 2025-09-22 | E1372-E-O-T-EPC-IFR-003059 | 3-Reviewed with Comments | 2025-07-07 | 2035-NMDC-MWS-T-0308 | 2025-07-16 | SAF185-MCE-NPCC-T-174 | 1-Approved
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-01-29 | 2035-NMDC-ADNOC-T-04846 | 2026-02-03 | E1372-E-O-T-EPC-IFI-000455 | 4-Information Only
| GMS ENTERPRISE JACK-UP BARGE SETUP PLAN DURING HOOK-UP WORKS AT USSC BRIDGE - 17 | 2035-AP-0261 | AD-511-C-380001 | 1 |  |  | T-317/25 | 2025-07-03 | 2025-07-01 | 2035-NMDC-ADNOC-T-03986 | 2025-08-06 | E1372-E-O-T-EPC-IFR-003005 | 3-Reviewed with Comments | 2025-07-07 | 2035-NMDC-MWS-T-0307 | 2025-08-02 | SAF185-MCE-NPCC-T-181 | 1-Approved
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-02-11 | 2035-NMDC-ADNOC-T-04949 | 2026-02-12 | E1372-E-O-T-EPC-IFI-000490 | 4-Information Only
| SEP-750 ANCHOR PATTERN AT RP-1 WEST SIDE | 2035-AP-0262 | AD-552-C-380016 | 1 |  |  | T-389/25 | 2025-08-04 | 2025-08-11 | 2035-NMDC-ADNOC-T-04103 | 2025-08-29 | E1372-E-O-T-EPC-IFR-003029 | 3-Reviewed with Comments | 2025-08-12 | 2035-NMDC-MWS-T-0331 | 2025-08-14 | SAF185-MCE-NPCC-T-186 | 1-Approved
|  |  |  | 2 |  |  | T-455/25 | 2025-09-04 | 2025-09-08 | 2035-NMDC-ADNOC-T-04208 | 2025-09-10 | SAF185-MCE-NPCC-T-194 | 1-Approved | 2025-09-08 | 2035-NMDC-MWS-T-0346 | 2025-09-09 | SAF185-MCE-NPCC-T-194 | 1-Approved
|  |  |  | 3 |  |  | T-495/25 | 2025-09-22 | 2026-02-11 | 2035-NMDC-ADNOC-T-04950 | 2026-02-12 | E1372-E-O-T-EPC-IFI-000488 | 4-Information Only
| QMS SUBHIYA SET-UP AT US-159 WELLHEAD TOWER | 2035-AP-0263 | AD-290-C-380003 | 1 | 2 |  | T-064/26 | 2026-02-10 | 2026-02-11 | 2035-NMDC-ADNOC-T-04940 | 2026-03-04 | E1372-E-O-T-EPC-IFR-003231 | 1-Approved | 2026-02-11 | 2035-NMDC-MWS-T-0462
| MUTAWA-401 SET-UP AT RP-1 SOUTH SIDE FOR THE LIFTING & INSTALLATION OF EMERGENCY EXTENSION DECK. | 2035-AP-0264 | AD-552-C-380023 | 1 | 2
| SEP-750 SET-UP AT US-153 FOR THE HOOK-UP & COMMISSIONING SCOPE | 2035-AP-0265 | AD-288-C-380005 | 1 | 2
| DIXIE PATRIOT SET-UP AT RP-1 WEST SIDE FOR THE HOOK-UP & COMMISSIONING SCOPE – RP-1 | 2035-AP-0266 | AD-552-C-380024 | 1 | 2
| SEP-650 SET-UP AT US-142 WELLHEAD TOWER | 2035-AP-0267 | AD-289-C-380007 | 1 | 2
| SEP-750 ANCHOR PATTERN DURING HOOK-UP WORKS AT US-19/19A | 2035-AP-0268 | AD-379/334-C-380005 | 1 | 2 |  | T-210/26 | 2026-05-13 | 2026-05-15 | 2035-NMDC-ADNOC-T-05294 | 2026-06-19 | E1372-E-O-T-EPC-IFR-003337 | 1-Approved | 2026-05-15 | 2035-NMDC-MWS-T-0565
| SEAFOX TRIDENT-1 ANCHOR PATTERN AT RP-1 WEST SIDE | 2035-AP-0269 | AD-552-C-380025 | 1 | 2
| DIXIE ANCHOR PATTERN AT RP-1 WEST SIDE | 2035-AP-0270 | AD-552-C-380026
| ANCHOR PATTERN FOR DLB-1000 DURING PL-2, PL-8, AND PL-7 STALK-ON RISERS,PL-9 SPOOLS, WALKWAY AND SOUTH RISER FENDER INSTALLATION AT RP-1 | 2035-AP-0271 | AD-552-C-380027 | 1 | 2 |  | T-136/26 | 2026-04-02 | 2026-04-02 | 2035-NMDC-ADNOC-T-05150 | 2026-04-15 | E1372-E-O-T-EPC-IFR-003280 | 2-Approved with Comments | 2026-04-02 | 2035-NMDC-MWS-T-0506
|  |  |  | 2 | 2 |  | T-183/26 | 2026-04-28 | 2026-04-30 | 2035-NMDC-ADNOC-T-05247 | 2026-06-18 | E1372-E-O-T-EPC-IFA-002884 | 2-Approved with Comments | 2026-04-30 | 2035-NMDC-MWS-T-0548 | 2026-05-06 | SAF185-MCE-NPCC-T-230 | 1-Approved
|  |  |  | 3 | 2 |  | T-304/26 | 2026-07-15 | 2026-08-05 | 2035-NMDC-ADNOC-T-05567 | 2026-08-11 | E1372-E-O-T-EPC-IFA-002913 | 1-Approved | 2026-08-05 | 2035-NMDC-MWS-T-0633
| ANCHOR PATTERN FOR DLB-1000 DURING PL-6 AND PL-11 CORRIDOR SPOOLS’ INSTALLATION AT HP-1 | 2035-AP-0272 | AD-771-C-380005 | 1 | 2 |  | T-136/26 | 2026-04-02 | 2026-04-02 | 2035-NMDC-ADNOC-T-05151 | 2026-04-15 | E1372-E-O-T-EPC-IFR-003279 | 2-Approved with Comments | 2026-04-02 | 2035-NMDC-MWS-T-0507 | 2026-05-29 | SAF185-MCE-NPCC-T-232 | 1-Approved
| ANCHOR PATTERN FOR DLB-1000 DURING PL-6 AND PL-11 CORRIDOR SPOOLS’ INSTALLATION AT HP-2 (2ND END) | 2035-AP-0273 | AD-772-C-380006 | 1 | 2 |  | T-136/26 | 2026-04-02 | 2026-04-02 | 2035-NMDC-ADNOC-T-05152 | 2026-04-15 | E1372-E-O-T-EPC-IFR-003279 | 2-Approved with Comments | 2026-04-02 | 2035-NMDC-MWS-T-0508 | 2026-04-08 | SAF185-MCE-NPCC-T-226 | 1-Approved
| ANCHOR PATTERN FOR DLB-1000 DURING PL-7 AND PL-10 CORRIDOR SPOOLS’ INSTALLATION AT HP-2 (2ND END) | 2035-AP-0274 | AD-772-C-380007 | 1 | 2 |  | T-136/26 | 2026-04-02 | 2026-04-02 | 2035-NMDC-ADNOC-T-05153 | 2026-04-15 | E1372-E-O-T-EPC-IFR-003282 | 2-Approved with Comments | 2026-04-02 | 2035-NMDC-MWS-T-0509 | 2026-04-08 | SAF185-MCE-NPCC-T-226 | 1-Approved
| ANCHOR PATTERN FOR DLB-1000 DURING PL-8 AND PL-9 LATERAL SHIFTING, PL-8 AND PL-9 CORRIDOR SPOOLS’ INSTALLATION, AND PL-10 CORRIDOR SPOOL INSTALLATION AT HP-3 | 2035-AP-0275 | AD-773-C-380007 | 1 | 2 |  | T-136/26 | 2026-04-02 | 2026-04-02 | 2035-NMDC-ADNOC-T-05154 | 2026-04-15 | E1372-E-O-T-EPC-IFR-003283 | 2-Approved with Comments | 2026-04-02 | 2035-NMDC-MWS-T-0510 | 2026-04-08 | SAF185-MCE-NPCC-T-226 | 1-Approved
| ANCHOR PATTERN FOR DLB-1000 DURING PL-1 CORRIDOR SPOOL INSTALLATION AT US-159A | 2035-AP-0276 | AD-768-C-380006 | 1 | 2 |  | T-136/26 | 2026-04-02 | 2026-04-02 | 2035-NMDC-ADNOC-T-05155 | 2026-04-15 | E1372-E-O-T-EPC-IFR-003284 | 1-Approved | 2026-04-02 | 2035-NMDC-MWS-T-0511 | 2026-04-08 | SAF185-MCE-NPCC-T-226 | 1-Approved
| ANCHOR PATTERN FOR DLB-1000 DURING PL-2 LATERAL SHIFTING AND PL-1 AND PL-2 CORRIDOR SPOOLS INSTALLATION AT US-12B | 2035-AP-0277 | AD-767-C-380007 | 1 | 2 |  | T-136/26 | 2026-04-02 | 2026-04-02 | 2035-NMDC-ADNOC-T-05156 | 2026-04-15 | E1372-E-O-T-EPC-IFR-003281 | 2-Approved with Comments | 2026-04-02 | 2035-NMDC-MWS-T-0512 | 2026-05-13 | SAF185-MCE-NPCC-T-231 | 1-Approved
| ANCHOR PATTERN FOR DLB-1000 DURING PL-4 CORRIDOR SPOOL INSTALLATION AT US-19B | 2035-AP-0278 | AD-774-C-380006 | 1 | 2 |  | T-136/26 | 2026-04-02 | 2026-04-02 | 2035-NMDC-ADNOC-T-05157 | 2026-04-15 | E1372-E-O-T-EPC-IFR-003285 | 1-Approved | 2026-04-02 | 2035-NMDC-MWS-T-0513 | 2026-04-08 | SAF185-MCE-NPCC-T-226 | 1-Approved
| ANCHOR PATTERN FOR DLB-1000 DURING PL-4 AND PL-5 CORRIDOR SPOOLS INSTALLATION AT US-153A | 2035-AP-0279 | AD-770-C-380008 | 1 | 2 |  | T-136/26 | 2026-04-02 | 2026-04-02 | 2035-NMDC-ADNOC-T-05158 | 2026-04-15 | E1372-E-O-T-EPC-IFR-003286 | 1-Approved | 2026-04-02 | 2035-NMDC-MWS-T-0514 | 2026-05-13 | SAF185-MCE-NPCC-T-231 | 1-Approved
| ANCHOR PATTERN FOR SAFEEN 3000 AT HP-1 CARRYING OUT THE INSTALLATION OF PL-6 CORRIDOR AND CLOSE OUT SPOOL | 2035-AP-0280 | AD-771-C-380006 | 1 | 2 |  | T-111/26 | 2026-03-16 | 2026-03-17 | 2035-NMDC-ADNOC-T-05100 | 2026-03-18 | E1372-E-O-T-EPC-IFR-003250 | 1-Approved | 2026-03-17 | 2035-NMDC-MWS-T-0493 | 2026-03-25 | SAF185-MCE-NPCC-T-223 | 1-Approved
| ANCHOR PATTERN FOR DLB-1000 DURING PL-1 CORRIDOR SPOOL INSTALLATION AT US-12B | 2035-AP-0281 | AD-767-C-380008 | 1 | 2 |  | T-136/26 | 2026-04-02 | 2026-04-02 | 2035-NMDC-ADNOC-T-05159 | 2026-04-15 | E1372-E-O-T-EPC-IFR-003281 | 2-Approved with Comments | 2026-04-02 | 2035-NMDC-MWS-T-0515 | 2026-05-13 | SAF185-MCE-NPCC-T-231 | 1-Approved
| ANCHOR PATTERN FOR DLB-1000 DURING PL-5 CORRIDOR SPOOL INSTALLATION AT US-153A | 2035-AP-0282 | AD-770-C-380009
| ANCHOR PATTERN FOR SAFEEN-3000 DURING LAYING OF PL-8, 16" WELL FLUID PIPELINE FROM KP: 4.152 TO HP-3 | 2035-AP-0283 | AD-773-C-380008 | 1 | 2 |  | T-148/26 | 2026-04-10 | 2026-04-16 | 2035-NMDC-ADNOC-T-05192 | 2026-05-04 | E1372-E-O-T-EPC-IFR-003302 | 1-Approved | 2026-04-15 | 2035-NMDC-MWS-T-0523 | 2026-05-29 | SAF185-MCE-NPCC-T-232 | 1-Approved
| QMS SUBHIYA SETUP DURING HOOK-UP WORKS AT HP-3 | 2035-AP-0284 | AD-773-C-380009 | 1 | 2 |  | T-211/26 | 2026-05-14 | 2026-05-15 | 2035-NMDC-ADNOC-T-05295 | 2026-06-16 | E1372-E-O-T-EPC-IFR-003334 | 1-Approved | 2026-05-15 | 2035-NMDC-MWS-T-0566
| SEP-650 SETUP PLAN DURING HOOK-UP WORKS AT HP-1 | 2035-AP-0285 | AD-771-C-380007 | 1 | 2 |  | T-230/26 | 2026-05-25 | 2026-06-30 | 2035-NMDC-ADNOC-T-05427 | 2026-08-06 | E1372-E-O-T-EPC-IFR-003377 | 4-Information Only | 2026-06-30 | 2035-NMDC-MWS-T-0597 | 2026-07-02 | SAF185-MCE-NPCC-T-243 | 1-Approved
| ANCHOR PATTERN FOR MUTAWA-17 SETUP AT US-142A | 2035-AP-0286 | AD-769-C-380010 | 1 | 2
| QMS SUBHIYA DURING HOOK UP WORKS AT HP-1 | 2035-AP-0287 | AD-771-C-380008 | 1 | 2
| SEAFOX TRIDENT-1 SET UP DURING HOOK UP WORKS AT HP-3 | 2035-AP-0288 | AD-773-C-380010 | 1 | 2 |  | T-334/26 | 2026-08-05 | 2026-08-06 | 2035-NMDC-ADNOC-T-05568 |  |  |  | 2026-08-06 | 2035-NMDC-MWS-T-0634
| DIXIE PATRIOT SET UP DURING HOOK UP WORKS AT HP-3 | 2035-AP-0289 | AD-773-C-380011 | 1 | 2
| SEAFOX TRIDENT-1 SET UP DURING HOOK UP WORKS AT HP-2 | 2035-AP-0290 | AD-772-C-380009 | 1 | 2
| SAFEEN - 3000 SETUP DRAWING DURING INSTALLATION OF US-159-A JACKET | 2035-DP-0001 | AD-768-C-380000 | 1 |  |  | T-137/23 | 2023-04-24 | 2023-04-26 | 2035-NPCC-ADNOC-T-00874 | 2023-06-09 | E1372-E-O-T-EPC-IFR-001418 | 2-Approved with Comments | 2023-04-26 | 2035-NPCC-MWS-T-0013
|  |  |  | 2 |  |  | T-220/23 | 2023-07-19 | 2023-07-20 | 2035-NPCC-ADNOC-T-01119 | 2023-08-01 | E1372-E-O-T-EPC-IFR-001595 | 1-Approved | 2023-07-20 | 2035-NPCC-MWS-T-0041
| SAFEEN - 3000 SETUP DRAWING DURING INSTALLATION OF US-12-B JACKET | 2035-DP-0002 | AD-767-C-380001 | 1 |  |  | T-137/23 | 2023-04-24 | 2023-04-26 | 2035-NPCC-ADNOC-T-00874 | 2023-06-09 | E1372-E-O-T-EPC-IFR-001418 | 2-Approved with Comments | 2023-04-26 | 2035-NPCC-MWS-T-0013
|  |  |  | 2 |  |  | T-220/23 | 2023-07-19 | 2023-07-20 | 2035-NPCC-ADNOC-T-01119 | 2023-08-01 | E1372-E-O-T-EPC-IFR-001595 | 1-Approved | 2023-07-20 | 2035-NPCC-MWS-T-0041
| SAFEEN - 3000 SETUP DRAWING DURING INSTALLATION OF BST S-13 JACKET | 2035-DP-0003 | AD-555-C-380000 | 1 |  |  | T-175/23 | 2023-06-07 | 2023-04-26 | 2035-NPCC-ADNOC-T-00874 | 2023-06-09 | E1372-E-O-T-EPC-IFR-001418 | 2-Approved with Comments | 26-Apr-2023 | 2035-NPCC-MWS-T-0013
|  |  |  | 2 |  |  | T-363/23 | 2023-12-05 | 2023-06-08 | 2035-NPCC-ADNOC-T-00992 | 2023-08-01 | E1372-E-O-T-EPC-IFR-001595 | 1-Approved
| SAFEEN - 3000 SETUP DRAWING DURING INSTALLATION OF US 142-A JACKET | 2035-DP-0004 | AD-769-C-380002 | 1 |  |  | T-137/23 | 2023-04-24 | 2023-04-26 | 2035-NPCC-ADNOC-T-00874 | 2023-06-09 | E1372-E-O-T-EPC-IFR-001418 | 2-Approved with Comments | 2023-04-26 | 2035-NPCC-MWS-T-0013
|  |  |  | 2 |  |  | T-220/23 | 2023-07-19 | 2023-07-20 | 2035-NPCC-ADNOC-T-01119 | 2023-08-01 | E1372-E-O-T-EPC-IFR-001595 | 1-Approved | 2023-07-20 | 2035-NPCC-MWS-T-0041
| SAFEEN - 3000 SETUP DRAWING DURING INSTALLATION OF US 153-A JACKET | 2035-DP-0005 | AD-770-C-380001 | 1 |  |  | T-137/23 | 2023-04-24 | 2023-04-26 | 2035-NPCC-ADNOC-T-00874 | 2023-06-09 | E1372-E-O-T-EPC-IFR-001418 | 2-Approved with Comments | 2023-04-26 | 2035-NPCC-MWS-T-0013
|  |  |  | 2 |  |  | T-220/23 | 2023-07-19 | 2023-07-20 | 2035-NPCC-ADNOC-T-01119 | 2023-08-01 | E1372-E-O-T-EPC-IFR-001595 | 1-Approved | 2023-07-20 | 2035-NPCC-MWS-T-0041
| SAFEEN - 3000 SETUP DRAWING DURING INSTALLATION OF US 19-B JACKET | 2035-DP-0006 | AD-774-C-380001 | 1 |  |  | T-137/23 | 2023-04-24 | 2023-04-26 | 2035-NPCC-ADNOC-T-00875 | 2023-06-12 | E1372-E-O-T-EPC-IFR-001419 | 2-Approved with Comments | 2023-04-26 | 2035-NPCC-MWS-T-0014
|  |  |  | 2 |  |  | T-220/23 | 2023-07-19 | 2023-07-20 | 2035-NPCC-ADNOC-T-01119 | 2023-08-01 | E1372-E-O-T-EPC-IFR-001595 | 1-Approved | 2023-07-20 | 2035-NPCC-MWS-T-0041
|  |  |  | 3 |  |  | T-260/23 | 2023-09-01 | 2023-09-01 | 2035-NPCC-ADNOC-T-01238 | 2023-10-19 | E1372-E-O-T-EPC-IFR-001716 | 1-Approved | 2023-09-01 | 2035-NPCC-MWS-T-0054
| UMM SHAIF DP SETUP PLAN DURING HOOK-UP ACTIVITIES AT USSC CSP-1 | 2035-DP-0014 | AD-502-C-380001 | 1 |  |  | T-128/24 | 2024-03-20 | 2024-03-21 | 2035-NPCC-ADNOC-T-01865 | 2024-04-04 | E1372-E-O-T-EPC-IFR-002082 | 3-Reviewed with Comments
|  |  |  | 2 |  |  | T-190/24 | 2024-05-07 | 2024-05-08 | 2035-NMDC-ADNOC-T-02058 | 2024-05-28 | E1372-E-O-T-EPC-IFA-002185 | 3-Reviewed with Comments
|  |  |  | 3 |  |  | T-225/24 | 2024-05-29 | 2024-05-30 | 2035-NMDC-ADNOC-T-02204 | 2024-09-24 | E1372-E-O-T-EPC-IFA-002419 | 1-Approved
|  |  |  | 4 |  |  | T-529/24 | 2024-10-28 | 2024-10-30 | 2035-NMDC-ADNOC-T-03064 | 2024-12-11 | E1372-E-O-T-EPC-IFA-002543 | 1-Approved
| UMM SHAIF DP SETUP PLAN DURING HOOK-UP ACTIVITIES AT USSC WIP-2 | 2035-DP-0015 | AD-186-C-380001 | 1 |  |  | T-128/24 | 2024-03-20 | 2024-03-21 | 2035-NPCC-ADNOC-T-01866 | 2024-04-04 | E1372-E-O-T-EPC-IFR-002083 | 3-Reviewed with Comments
|  |  |  | 2 |  |  | T-258/24 | 2024-06-13 | 2024-06-13 | 2035-NMDC-ADNOC-T-02318 | 2024-09-27 | E1372-E-O-T-EPC-IFA-002425 | 2-Approved with Comments
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-02-11 | 2035-NMDC-ADNOC-T-04951 | 2026-02-12 | E1372-E-O-T-EPC-IFI-000488 | 4-Information Only
| MUTAWA-401 SETUP DURING HOOK-UP WORKS AT US-88 | 2035-DP-0018 | AD-284-C-380007 | 1 |  |  | T-616/25 | 2025-12-10 | 2025-12-16 | 2035-NMDC-ADNOC-T-04665 | 2026-01-06 | E1372-E-O-T-EPC-IFR-003173 | 1-Approved
| MUTAWA-401 SETUP DURING HOOK-UP WORKS AT US-218 | 2035-DP-0019 | AD-426-C-380009 | 1 |  |  | T-616/25 | 2025-12-10 | 2025-12-16 | 2035-NMDC-ADNOC-T-04666 | 2025-01-06 | E1372-E-O-T-EPC-IFR-003174 | 1-Approved
| CONSTRUCTION BARGE SETUP DRAWING DURING TIE-IN SPOOL INSTALLATION AT US 142A | 2035-DP-0024 | AD-769-C-38004 | 1 |  |  | T-574/25 | 2025-11-13 | 2025-11-14 | 2035-NMDC-ADNOC-T-04485 | 2025-12-05 | E1372-E-O-T-EPC-IFR-003140 | 2-Approved with Comments | 2025-11-14 | 2035-NMDC-MWS-T-0373 | 2025-11-20 | SAF185-MCE-NPCC-T-205 | 1-Approved
|  |  |  | 2 |  |  | T-021/26 | 2026-01-16 | 2026-01-21 | 2035-NMDC-ADNOC-T-04807 | 2026-01-27 | E1372-E-O-T-EPC-IFA-002809 | 1-Approved | 2026-01-21 | 2035-NMDC-MWS-T-0449 | 2026-01-30 | SAF185-MCE-NPCC-T-218 | 1-Approved
| CONSTRUCTION BARGE SETUP DRAWING DURING SPOOL INSTALLATION AT US 153A EAST | 2035-DP-0026 | AD-770-C-380004 | 1 |  |  | T-574/25 | 2025-11-13 | 2025-11-14 | 2035-NMDC-ADNOC-T-04486 | 2025-12-12 | E1372-E-O-T-EPC-IFR-003153 | 1-Approved | 2025-11-14 | 2035-NMDC-MWS-T-0374 | 2025-11-26 | SAF185-MCE-NPCC-T-206 | 1-Approved
| CONSTRUCTION BARGE (SAFEEN-3000) SETUP DURING PL-3 RISER (STALK-ON) INSTALLATION & MISCELLANEOUS ACTIVITIES AT USSC-RP1 EAST | 2035-DP-0029 | AD-552-C-380002 | 1 |  |  | T-577/25 | 2025-11-14 | 2025-11-01 | 2035-NMDC-ADNOC-T-04497 | 2025-12-09 | E1372-E-O-T-EPC-IFR-003147 | 1-Approved | 2025-11-17 | 2035-NMDC-MWS-T-0377 | 2025-11-20 | SAF185-MCE-NPCC-T-205 | 1-Approved
| SAFEEN - 3000 SETUP DRAWING DURING LAYING OF 16'' WELL FLUID PIPELINE FROM US 159A TO US 12B INCLUDING 2'' PIGGYBACK PIPELINE | 2035-DP-0041 | AD-768-767-C-380000 | 1 |  |  | T-299/23 | 2023-10-10 | 2023-10-10 | 2035-NPCC-ADNOC-T-01333 | 2023-11-07 | E1372-E-O-T-EPC-IFR-001761 | 2-Approved with Comments | 11-Oct-2023 | 2035-NPCC-MWS-T-0067
|  |  |  | 2 |  |  | T-181/24 | 2024-05-01 | 2024-05-01 | 2035-NMDC-ADNOC-T-02019 | 2024-09-10 | E1372-E-O-T-EPC-IFA-002392 | 2-Approved with Comments | 2024-05-01 | 2035-NPCC-MWS-T-0135
|  |  |  | 3 |  |  | T-018/25 | 2025-01-15 | 2025-01-16 | 2035-NMDC-ADNOC-T-03404 | 07-Mar-2025 | E1372-E-O-T-EPC-IFA-002606 | 1-Approved | 2025-01-16 | 2035-NMDC-MWS-T-0250
|  |  |  | 4 |  |  | T-299/26 | 2026-07-10 | 2026-07-13 | 2035-NMDC-ADNOC-T-05465 | 2026-08-11 | E1372-E-O-T-EPC-IFA-002914 | 1-Approved | 2026-07-13 | 2035-NMDC-MWS-T-0613
| SAFEEN - 3000 SETUP DRAWING DURING LAYING OF PL-2 16'' WELL FLUID PIPELINE USSC RP--1 TO US 12B INCLUDING 2'' PIGGYBACK PIPELINE | 2035-DP-0042 | AD-552-767-C-380000 | 1 |  |  | T-356/23 | 2023-11-25 | 27-Nov-2023 | 2035-NPCC-ADNOC-T-01498 | 2024-02-29 | E1372-E-O-T-EPC-IFR-001985 | 2-Approved with Comments | 2023-11-27 | 2035-NPCC-MWS-T-0086
|  |  |  | 2 |  |  | T-181/24 | 2024-05-01 | 2024-05-01 | 2035-NMDC-ADNOC-T-02020 | 2024-09-10 | E1372-E-O-T-EPC-IFA-002391 | 2-Approved with Comments | 2024-05-01 | 2035-NPCC-MWS-T-0136
|  |  |  | 3 |  |  | T-099/26 | 2026-03-09 | 2026-03-12 | 2035-NMDC-ADNOC-T-05081 | 2026-04-06 | E1372-E-O-T-EPC-IFA-002849 | 3-Reviewed with Comments | 2026-04-30 | 2035-NMDC-MWS-T-0547
|  |  |  | 4 |  |  | T-185/26 | 2026-04-30 | 2026-04-30 | 2035-NMDC-ADNOC-T-05246 | 2026-05-07 | E1372-E-O-T-EPC-IFR-003306 | 1-Approved | 2026-04-30 | 2035-NMDC-MWS-T-0547 | 2026-05-29 | SAF185-MCE-NPCC-T-232 | 1-Approved
| SAFEEN-3000 SETUP DRAWING DURING LAYING OF 16'' WELL FLUID PIPELINE FROM USSC RP-1 TO US 142A INCLUDING 2'' PIGGYBACK PIELINE | 2035-DP-0043 | AD-552-769-C-380000 | 1 |  |  | T-259/23 | 2023-09-01 | 2023-09-01 | 2035-NPCC-ADNOC-T-01237 | 2023-11-07 | E1372-E-O-T-EPC-IFR-001765 | 2-Approved with Comments | 2023-09-01 | 2035-NPCC-MWS-T-0053
|  |  |  | 2 |  |  | T-181/24 | 2024-05-01 | 2024-05-01 | 2035-NMDC-ADNOC-T-02021 | 2024-09-10 | E1372-E-O-T-EPC-IFA-002391 | 2-Approved with Comments | 2024-05-01 | 2035-NPCC-MWS-T-0137
|  |  |  | 3 |  |  | T-018/25 | 2025-01-15 | 2025-01-16 | 2035-NMDC-ADNOC-T-03405 | 2025-03-07 | E1372-E-O-T-EPC-IFA-002606 | 1-Approved | 2025-01-16 | 2035-NMDC-MWS-T-0251
| SAFEEN-3000 SETUP DRAWING DURING LAYING OF 16'' WELL FLUID PIPELINE FROM USSC RP-1 TO US 153A INCLUDING 2'' PIGGYBACK PIELINE | 2035-DP-0044 | AD-552-770-C-380000 | 1 |  |  | T-296/23 | 2023-10-06 | 2023-10-06 | 2035-NPCC-ADNOC-T-01325 | 2023-11-07 | E1372-E-O-T-EPC-IFR-001766 | 2-Approved with Comments | 2023-10-06 | 2035-NPCC-MWS-T-0065
|  |  |  | 2 |  |  | T-181/24 | 2024-05-01 | 2024-05-01 | 2035-NMDC-ADNOC-T-02022 | 2024-09-10 | E1372-E-O-T-EPC-IFA-002391 | 2-Approved with Comments | 2024-05-01 | 2035-NPCC-MWS-T-0138
| SAFEEN - 3000 SETUP DRAWING DURING LAYING OF PL-4 16'' WELL FLUID PIPELINE FROM US 19B TO US 153A INCLUDING 2'' PIGGYBACK PIPELINE | 2035-DP-0045 | AD-774-770-C-380000 | 1 |  |  | T-356/23 | 2023-11-25 | 2023-11-27 | 2035-NPCC-ADNOC-T-01499 | 2024-02-29 | E1372-E-O-T-EPC-IFR-001986 | 2-Approved with Comments | 27-Nov-2023 | 2035-NPCC-MWS-T-0087
|  |  |  | 2 |  |  | T-181/24 | 2024-05-01 | 2024-05-01 | 2035-NMDC-ADNOC-T-02023 | 2024-09-10 | E1372-E-O-T-EPC-IFA-002392 | 2-Approved with Comments | 2024-05-01 | 2035-NPCC-MWS-T-0139
|  |  |  | 3 |  |  | T-363/26 | 2026-08-24 | 2026-08-25 | 2035-NMDC-ADNOC-T-05640 |  |  |  | 2026-08-25 | 2035-NMDC-MWS-T-0647
| SAFEEN-3000 SETUP DRAWING DURING LAYING OF PL-8 16'' WELL FLUID PIPELINE FROM USSC RP-1 TO HP-3 | 2035-DP-0046 | AD-552-773-C-380000 | 1 |  |  | T-043/26 | 2026-01-29 | 2026-02-04 | 2035-NMDC-ADNOC-T-04896 | 2026-02-12 | E1372-E-O-T-EPC-IFR-003219 | 3-Reviewed with Comments | 2026-02-04 | 2035-NMDC-MWS-T-0455 | 2026-01-17 | SAF185-MCE-NPCC-T-220 | 1-Approved
|  |  |  | 2 |  |  | T-071/26 | 2026-02-13 | 2026-02-20 | 2035-NMDC-ADNOC-T-05004 | 2026-03-10 | E1372-E-O-T-EPC-IFR-003237 | 1-Approved | 2026-02-20 | 2035-NMDC-MWS-T-0470
| SAFEEN-3000 SET-UP DRAWING DURING LAYING OF PL-9, 16" WATER INJECTION SUBSEA PIPELINE (WITH DUAL 2" PIGGYBACK) FROM USSC-RP1 TO HP3 | 2035-DP-0047 | AD-552/773-C-380003 | 1 | 2 |  | T-303/26 | 2026-07-14 | 2026-07-16 | 2035-NMDC-ADNOC-T-05478 | 2026-08-06 | E1372-E-O-T-EPC-IFR-003376 | 4-Information Only | 2026-07-16 | 2035-NMDC-MWS-T-0615 | 2026-07-23 | SAF185-MCE-NPCC-T-248 | 1-Approved
| SAFEEN - 3000 SETUP DRAWING DURING LAYING OF PL-10, 16'' WELL FLUID PIPELINE FROM HP-3 TO HP-2 INCLUDING 2'' PIGGYBACK | 2035-DP-0048 | AD-773-772-C-380000 | 1 |  |  | T-009/24 | 2024-01-09 | 2024-01-10 | 2035-NPCC-ADNOC-T-01629 | 2024-02-29 | E1372-E-O-T-EPC-IFR-001986 | 2-Approved with Comments | 2024-01-10 | 2035-NPCC-MWS-T-0103
|  |  |  | 2 |  |  | T-181/24 | 2024-05-01 | 2024-05-01 | 2035-NMDC-ADNOC-T-02024 | 2024-09-10 | E1372-E-O-T-EPC-IFA-002392 | 2-Approved with Comments | 2024-05-01 | 2035-NPCC-MWS-T-0140
|  |  |  | 3 |  |  | T-213/26 | 2026-05-14 | 2026-05-15 | 2035-NMDC-ADNOC-T-05293 | 2026-07-01 | E1372-E-O-T-EPC-IFA-002890 | 3-Reviewed with Comments | 15-May-2026 | 2035-NMDC-MWS-T-0564
|  |  |  | 4 |  |  | T-278/26 | 2026-07-02 | 2026-07-03 | 2035-NMDC-ADNOC-T-05443 | 2026-07-07 | E1372-E-O-T-EPC-IFR-003347 | 1-Approved | 2026-07-03 | 2035-NMDC-MWS-T-0601
| SAFEEN-3000 SET-UP DRAWING DURING LAYING OF PL-11 16'' WATER INJECTION SUBSEA PIPELINE (WITH DUAL 2'' PIGGYBACK) FROM HP-2 TO HP-1 | 2035-DP-0049 | AD-772/771-C-380000 | 1 |  |  | T-203/26 | 2026-05-12 | 2026-05-12 | 2035-NMDC-ADNOC-T-05273 | 2026-08-11 | E1372-E-O-T-EPC-IFR-003380 | 3-Reviewed with Comments | 2026-05-12 | 2035-NMDC-MWS-T-0557
|  |  |  | 2 |  |  | T-346/26 | 2026-08-12 | 2026-08-14 | 2035-NMDC-ADNOC-T-05591 | 2026-08-20 | E1372-E-O-T-EPC-IFR-003392 | 2-Approved with Comments | 2026-08-14 | 2035-NMDC-MWS-T-0637
|  |  |  | 3 |  |  | T-354/26 | 2026-08-18 | 2026-08-20 | 2035-NMDC-ADNOC-T-05618 |  |  |  | 2026-08-20 | 2035-NMDC-MWS-T-0643
| SAFEEN-3000 SETUP DRAWING DURING LAYING OF PL-6 FOR 18" WELL FLUID PIPELINE FROM HP-1 TO HP-2 | 2035-DP-0050 | AD-771-772-C-380000 | 1 |  |  | T-383/23 | 2023-12-21 | 2023-11-27 | 2035-NPCC-ADNOC-T-01581 | 2024-02-29 | E1372-E-O-T-EPC-IFR-001986 | 2-Approved with Comments | 2023-12-22 | 2035-NPCC-MWS-T-0095
|  |  |  | 2 |  |  | T-181/24 | 2024-05-01 | 2024-05-01 | 2035-NMDC-ADNOC-T-02025 | 2024-09-10 | E1372-E-O-T-EPC-IFA-002392 | 2-Approved with Comments | 2024-05-01 | 2035-NPCC-MWS-T-0141
| SAFEEN - 3000 SETUP DRAWING DURING LAYING OF PL-7 16'' WELL FLUID PIPELINE FROM USSC RP-1 TO HP-2 | 2035-DP-0051 | AD-552-772-C-380000 | 1 |  |  | T-356/23 | 2023-11-25 | 2023-11-27 | 2035-NPCC-ADNOC-T-01500 | 2024-02-29 | E1372-E-O-T-EPC-IFR-001985 | 2-Approved with Comments | 2023-11-27 | 2035-NPCC-MWS-T-0088
|  |  |  | 2 |  |  | T-181/24 | 2024-05-01 | 2024-05-01 | 2035-NMDC-ADNOC-T-02026 | 1'0-Sep-2024 | E1372-E-O-T-EPC-IFA-002391 | 2-Approved with Comments | 2024-05-01 | 2035-NPCC-MWS-T-0142
| SAFEEN - 3000 SETUP DRAWING DURING INSTALLATION OF HP-1 JACKET | 2035-DP-0071 | AD-771-C-380002 | 1 |  |  | T-137/23 | 2023-04-24 | 26-Apr-2023 | 2035-NPCC-ADNOC-T-00875 | 2023-06-12 | E1372-E-O-T-EPC-IFR-001419 | 2-Approved with Comments | 2023-04-26 | 2035-NPCC-MWS-T-0014
|  |  |  | 2 |  |  | T-282/23 | 2023-09-26 | 2023-10-02 | 2035-NPCC-ADNOC-T-01297 | 2023-10-11 | E1372-E-O-T-EPC-IFR-001696 | 1-Approved | 02-Oct-2023 | 2035-NPCC-MWS-T-0063
| SAFEEN - 3000 SETUP DRAWING DURING INSTALLATION OF HP-2 JACKET | 2035-DP-0072 | AD-772-C-380003 | 1 |  |  | T-137/23 | 2023-04-24 | 2023-04-26 | 2035-NPCC-ADNOC-T-00875 | 2023-06-12 | E1372-E-O-T-EPC-IFR-001419 | 2-Approved with Comments | 2023-04-26 | 2035-NPCC-MWS-T-0014
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-01-29 | 2035-NMDC-ADNOC-T-04855 | 2026-02-02 | E1372-E-O-T-EPC-IFI-000454 | 4-Information Only
| SAFEEN - 3000 SETUP DRAWING DURING INSTALLATION OF HP-3 JACKET | 2035-DP-0073 | AD-773-C-380002 | 1 |  |  | T-137/23 | 2023-04-24 | 2023-04-26 | 2035-NPCC-ADNOC-T-00875 | 2023-06-12 | E1372-E-O-T-EPC-IFR-001419 | 2-Approved with Comments | 2023-04-26 | 2035-NPCC-MWS-T-0014
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-01-29 | 2035-NMDC-ADNOC-T-04854 | 2026-02-05 | E1372-E-O-T-EPC-IFI-000474 | 4-Information Only
| SAFEEN - 3000 SETUP DRAWING DURING INSTALLATION OF RP-1 JACKET | 2035-DP-0074 | AD-552-C-380003 | 1 |  |  | T-137/23 | 2023-04-24 | 2023-04-26 | 2035-NPCC-ADNOC-T-00875 | 2023-06-12 | E1372-E-O-T-EPC-IFR-001419 | 2-Approved with Comments | 2023-04-26 | 2035-NPCC-MWS-T-0014
|  |  |  | 2 |  |  | T-364/23 | 2023-12-06 | 2023-12-07 | 2035-NPCC-ADNOC-T-01527 | 2024-03-12 | E1372-E-O-T-EPC-IFR-002011 | 2-Approved with Comments | 2023-12-07 | 2035-NPCC-MWS-T-0091 | 2024-03-15 | SAF185-MCE-NPCC-T-066 | 1-Approved
|  |  |  | 3 |  |  | T-125/24 | 2024-03-17 | 19-Mar-2024 | 2035-NPCC-ADNOC-T-01855 | 2024-05-09 | E1372-E-O-T-EPC-IFR-002171 | 1-Approved | 2024-03-19 | 2035-NPCC-MWS-T-0125 | 22-Mar-2024 | SAF185-MCE-NPCC-T-068 | 1-Approved
| SAFEEN PEARL SETUP FOR PREPARATORY WORKS AT RP-1 | 2035-DP-0075 | AD-552-C-380008 | 1 |  |  | T-134/25 | 2025-04-08 | 2025-04-15 | 2035-NMDC-ADNOC-T-03708 | 2025-04-30 | E1372-E-O-T-EPC-IFR-002863 | 1-Approved | 2025-04-15 | 2035-NMDC-MWS-T-0278
| SAFEEN PEARL SETUP FOR PREPARATORY WORKS AT US 142A | 2035-DP-0076 | AD-769-C-380006 | 1 |  |  | T-134/25 | 2025-04-09 | 2025-04-15 | 2035-NMDC-ADNOC-T-03708 | 2025-04-30 | E1372-E-O-T-EPC-IFR-002864 | 1-Approved | 2025-04-15 | 2035-NMDC-MWS-T-0279
| SAPURA-1200 DP SET-UP DURING US-142A DECK INSTALLATION | 2035-DP-0077 | AD-769-C-380007 | 1
| SAPURA-1200 DP SET-UP DURING US-159A DECK INSTALLATION | 2035-DP-0078 | AD-768-C-380003 | 1
| SAFEEN PEARL SET UP PLAN AT RP-1 | 2035-DP-0079 | AD-552-C-380017 | 1
| DLS-4200 DP SETUP DURING US-153A DECK INSTALLATION | 2035-DP-0080 | AD-770-C-380006 | 1 |  |  | T-429/25 | 2025-08-26 | 2025-08-27 | 2035-NMDC-ADNOC-T-04175 | 2025-08-29 | E1372-E-O-T-EPC-IFR-003033 | 1-Approved | 2025-08-27 | 2035-NMDC-MWS-T-0344 | 2025-09-08 | SAF185-MCE-NPCC-T-191 | 1-Approved
| DLS-4200 SETUP DURING US-HP1 DECK INSTALLATION | 2035-DP-0081 | AD-771-C-380003 | 1 |  |  | T-288/25 | 2025-06-24 | 2025-06-24 | 2035-NMDC-ADNOC-T-03945 | 2025-06-30 | E1372-E-O-T-EPC-IFR-002949 | 3-Reviewed with Comments | 2025-06-24 | 2035-NMDC-MWS-T-0300 | 2025-07-07 | SAF185-MCE-NPCC-T-171 | 1-Approved
|  |  |  | 2 |  |  | T-324/25 | 2025-07-11 | 2025-07-17 | 2035-NMDC-ADNOC-T-04028 | 2025-07-31 | E1372-E-O-T-EPC-IFR-002996 | 1-Approved | 2025-07-17 | 2035-NMDC-MWS-T-0320 | 2025-07-28 | SAF185-MCE-NPCC-T-178 | 1-Approved
| DLS-4200 SETUP DURING US-HP2 DECK INSTALLATION | 2035-DP-0082 | AD-772-C-380004 | 1 |  |  | T-288/25 | 2025-06-24 | 2025-06-24 | 2035-NMDC-ADNOC-T-03946 | 2025-06-30 | E1372-E-O-T-EPC-IFR-002949 | 3-Reviewed with Comments | 2025-06-24 | 2035-NMDC-MWS-T-0302 | 2025-07-07 | SAF185-MCE-NPCC-T-171 | 1-Approved
|  |  |  | 2 |  |  | T-324/25 | 2025-07-11 | 2025-07-17 | 2035-NMDC-ADNOC-T-04027 | 2025-07-31 | E1372-E-O-T-EPC-IFR-002997 | 1-Approved | 2025-07-17 | 2035-NMDC-MWS-T-0319 | 2025-07-28 | SAF185-MCE-NPCC-T-178 | 1-Approved
| DLS-4200 SET-UP AT US-12B During DECK Installation | 2035-DP-0083 | AD-767-C-380006 | 1 |  |  | T-407/25 | 2025-08-12 | 2025-08-13 | 2035-NMDC-ADNOC-T-04113 | 2025-09-10 | E1372-E-O-T-EPC-IFR-003045 | 1-Approved | 2025-08-13 | 2035-NMDC-MWS-T-0335 | 2025-08-14 | SAF185-MCE-NPCC-T-186 | 1-Approved
| DLS-4200 SET-UP AT US-19B During DECK Installation | 2035-DP-0084 | AD-774-C-380004 | 1 |  |  | T-407/25 | 2025-08-12 | 2025-08-13 | 2035-NMDC-ADNOC-T-04114 | 2025-09-02 | E1372-E-O-T-EPC-IFR-003035 | 1-Approved | 2025-08-13 | 2035-NMDC-MWS-T-0336 | 2025-08-14 | SAF185-MCE-NPCC-T-186 | 1-Approved
| DLS-4200 SET-UP During B-27 Bridge Installation | 2035-DP-0085 | AD-554-C-380001 | 1 |  |  | T-463/25 | 2025-09-08 | 2025-09-09 | 2035-NMDC-ADNOC-T-04220 | 2025-09-15 | E1372-E-O-T-EPC-IFR-003054 | 1-Approved | 2025-09-09 | 2035-NMDC-MWS-T-0349 | 2025-09-15 | SAF185-MCE-NPCC-T-196 | 1-Approved
| DLS-4200 DP SETUP DURING HP-3 DECK INSTALLATION | 2035-DP-0086 | AD-773-C-380005 | 1
| HEA OCEANIC SET-UP PLAN AT US-142 DURING PL-3 SUBSEA WORKS | 2035-DP-0087 | AD-289-C-380008 | 1
| HEA-OCEANIC DP SETUP PLAN AT CC3-CX-01 INSIDE 500M OF US-216 | 2035-DP-0088 | AD-424-C-380008 | 1 |  |  | T-058/26 | 2026-02-06 | 2026-02-10 | 2035-NMDC-ADNOC-T-04926 | 2026-02-12 | E1372-E-O-T-EPC-IFR-003218 | 1-Approved
| HEA-OCEANIC DP SETUP PLAN AT CC8-CX-07 INSIDE 500M OF US-218 | 2035-DP-0089 | AD-426-C-380010 | 1 |  |  | T-058/26 | 2026-02-06 | 2026-02-10 | 2035-NMDC-ADNOC-T-04927 | 2026-02-12 | E1372-E-O-T-EPC-IFR-003218 | 1-Approved
| HEA-OCEANIC DP SETUP PLAN AT CC9-CX-25 INSIDE 500M OF US-218 | 2035-DP-0090 | AD-426-C-380011 | 1 |  |  | T-058/26 | 2026-02-06 | 2026-02-10 | 2035-NMDC-ADNOC-T-04928 | 2026-02-12 | E1372-E-O-T-EPC-IFR-003218 | 1-Approved
| HEA OCEANIC SETUP DURING PL-5 CLOSE OUT SPOOL INSTALLATION AT US-153A | 2035-DP-0091 | AD-770-C-380007 | 1 |  |  | T-093/26 | 2026-03-05 |  | 2035-NMDC-ADNOC-T-05033 | 2026-03-23 | E1372-E-O-T-EPC-IFR-003218 | 2-Approved with Comments
| MUTAWA 401 SETUP AT US-159A WHT | 2035-DP-0092 | AD-768-C-380007 | 1
| MUTAWA-17 SETUP AT US-142A | 2035-DP-0093 | AD-769-C-380009
| SAFEEN-3000 DP SET-UP DURING PL-11 CORRIDOR SPOOLS INSTALLATION AT HP-1 | 2035-DP-0094 | AD-771-C-380009 | 1 |  |  | T-348/26 | 2026-08-13 | 2026-08-14 | 2035-NMDC-ADNOC-T-05594 |  |  |  | 2026-08-14 | 2035-NMDC-MWS-T-0638
| SAFEEN-3000 DP SET-UP DURING PL-11 CORRIDOR SPOOLS INSTALLATION AT HP-2 | 2035-DP-0095 | AD-772-C-380008 | 1 |  |  | T-348/26 | 2026-08-13 | 2026-08-14 | 2035-NMDC-ADNOC-T-05595 |  |  |  | 2026-08-14 | 2035-NMDC-MWS-T-0639
| SAFEEN-3000 DP SET-UP DURING PL-4 CORRIDOR SPOOLS INSTALLATION AT US153A | 2035-DP-0096 | AD-770-C-380009 | 1 |  |  | T-377/26 | 2026-08-31 | 2026-08-31 | 2035-NMDC-ADNOC-T-05651 |  |  |  | 2026-08-31 | 2035-NMDC-MWS-T-0651
| SAFEEN-3000 DP SET-UP DURING PL-4 CORRIDOR SPOOLS INSTALLATION AT US19B | 2035-DP-0097 | AD-774-C-380005 | 1 |  |  | T-377/26 | 2026-08-31 | 2026-08-31 | 2035-NMDC-ADNOC-T-05652 |  |  |  | 2026-08-31 | 2035-NMDC-MWS-T-0652

## Sketches
NMDC DOC. No.: MDR-001
EPC WORK FOR UMM SHAIF LONG TERM DEVELOPMENT PHASE-1 (US-LTD-1)
|  | NMDC PROJECT NO. 2035 | [5 empty] | REVISION : | 0
|  | OFFSHORE Sketches | [5 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC ENERGY SKETCH NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | REMARKS
SUBMISSION STATUS
[6 empty] | DATE | REF
| (SAFEEN 3000 Setup during PL-1 Laydown at US-12B) | 2035-A1-016 | 3 |  |  |  | SKV
| (SAFEEN 3000 Setup during PL-4 Start-up at US-19B) | 2035-A1-019 | 2 |  |  |  | SKV
| (Safeen Pearl Setup at US 142A) | 2035-DP-0000 | 1 |  |  |  | SKV
| (Safeen Pearl Setup at RP-1) | 2035-DP-0000 | 1 |  |  |  | SKV
| ( DLB-1000 AP during Riser installation at US-RP1)_OPTION-2 | 2035-AP-0002 | 2 |  |  |  | EJJ
| (SAPURA-1200 AP during pipelaying of PL-7 from USSC RP-1 to HP-2) | 2035-AP-0248 | 1 |  |  |  | EJJ
| (SAPURA-1200 AP during pipelaying of PL-3 from USSC RP-1 to US-142A)_For Mooring | 2035-AP-0244 | 1 |  |  |  | EJJ
| (DLS-4200 SET-UP AT US-HP-3 during DECK Installation) | 2035-AP-083 | 1 |  |  |  | SKV
| (SAPURA-1200 AP during pipelaying of PL-3 from USSC RP-1 to US-142A) | 2035-AP-0244 | 1 |  |  |  | SKV
| (SAFEEN PEARL SETUP DURING CABLE (CC-7 & CC-8) Startup at US-142A) | 2035-A3-133 | A |  |  |  | SKV
| (SAPURA-1200 AP during pipelaying of PL-7 from USSC RP-1 to HP-2) | 2035-AP-0248 | 1 |  |  |  | EJJ
| (SAFEEN PEARL set-up during cable laying of CC-7_START-UP @ US-142A) | 2035-A3-133 | A |  |  |  | EJJ
| (SAFEEN PEARL set-up during cable laying of CC-6_START-UP @ US-HP1) | 2035-A3-134 | A |  |  |  | EJJ
| (SAFEEN PEARL set-up during cable laying of CC-5_START-UP @ US-19B) | 2035-A3-135 | A |  |  |  | EJJ
| (DLB 1000 AP during PL-3 Riser & Spool installation at RP1) | 2035-AP-0257 | 1 |  |  | 2025-06-26 | EJJ
| 2035-AP-0091-1 to 5_R3( LB-II AP during RP-1 FLOATOVER) | 2035-AP-0091 | 3 |  |  | 2025-06-26 | SKV
| (DLB 1000 AP during PL-3 Riser & Spool installation at RP1) | 2035-AP-0257 | 1 |  |  | 2025-06-30 | EJJ
| (SAFEEN PEARL set-up during cable laying of CC-7 @ US-HP2_LAY-DOWN) | 2035-A3-133 | B |  |  | 2025-06-30 | EJJ
| 2035-A1-048_R0(LB-II passage plan from outside FIELD to RP1)_OPTION-1 | 2035-A1-048 | 0 |  |  | 2025-07-07 | EJJ
| 2035-A4-006_R0(Temporary supports AS BUILT positions w.r.t. SAPURA-1200 AP during PL-3 laydown @ US-142A) | 2035-A4-006 | 0 |  |  | 2025-07-08 | EJJ
| 2035-AP-0091-1 TO 5_R3( LB-II AP during RP-1 FLOATOVER) | 2035-AP-0091 | 3 |  |  | 2025-07-10 | EJJ
| PL-4 SAFEEN-3000 LAY-DOWN STUDY @ 153 | - | - |  |  | 2025-07-11 | EJJ
| 2035-AP-0251-1 TO 3_R1(SAPURA-1200 AP during pipelaying of PL-10 from HP-3 to HP-2) | 2035-AP-0251 | 1 |  |  | 2025-08-07 | SKV
| 2035-A1-0049_R0 (SAPURA-1200 Vs SAFEEN PEARL Vs SEP-750 Clash study at HP-1) | 2035-A1-0049 | 0 |  |  | 2025-08-20 | SKV
| 2035-DP-0080_R1( DLS-4200 DP Setup during US 153-A DECK Installation) | 2035-DP-0080 | 1 |  |  | 2025-08-26 | SKV
| 2035-DP-0085-1 TO 2_R1(DLS-4200 SET-UP DURING B-27 BRIDGE INSTALLATION) | 2035-DP-0085 | 1 |  |  | 2025-09-01 | SKV
| 2035-AP-0244-1 TO 3_R3(SAPURA-1200 AP during pipelaying of PL-3 from USSC RP-1 to US-142A) | 2035-AP-0244 | 2 |  |  | 2025-09-02 | EJJ
| 2035-DP-0083_R2(DLS-4200 SET-UP AT US-12B During DECK Installation) | 2035-DP-0083 | 2 |  |  | 2025-09-04 | EJJ
| 2035-AP-0246-1 TO 5_R2(SAPURA-1200 AP during pipelaying of PL-5 from USSC RP-1 to US-153A) | 2035-AP-0246 | 2 |  |  | 2025-09-08 | EJJ
| 2035-AP-0248-1 TO 6_R2(SAPURA-1200 AP during pipelaying of PL-7 from USSC RP-1 to HP-2) | 2035-AP-0248 | 2 |  |  | 2025-09-08 | EJJ
| 2035-A1-052-1 & 2_R0(SAPURA-1200 SET-UP for (PL-3) during START-UP & LAY-DOWN) | 2035-A1-052 | 0 |  |  | 2025-09-12 | EJJ
| 2035-A3-178-1 TO 3_R0(DLS-4200 AVIATION SKETCHES DURING B-27 BRIDGE INSTALLATION) | 2035-A3-178 | 0 |  |  | 2025-09-15 | SKV
| 2035-AP-0248-1 TO 6_R3(SAPURA-1200 AP during pipelaying of PL-7 from USSC RP-1 to HP-2) | 2035-AP-0248 | 3 |  |  | 2025-09-15 | EJJ
| 2035-AP-0251-1 TO 3_R2(SAPURA-1200 AP during pipelaying of PL-10 from HP-3 to HP-2) | 2035-AP-0251 | 2 |  |  | 2025-09-15 | EJJ
| 2035-A3-134-1 TO 2_Rev-B(SAFEEN PEARL set-up during cable laying of CC-6_START-UP @ US-HP1) | 2035-A3-134 | B |  |  | 2025-09-19 | EJJ
| 2035-A3-133-1 OF 2-Rev-C(SAFEEN PEARL set-up during cable laying of CC-7_START-UP @ US-HP2) | 2035-A3-133 | C |  |  | 2025-09-22 | EJJ
| 2035-AP-0242-1 OF 2_R2(SAPURA-1200 AP during pipelaying 16 inch WF PL-1 from US 159A to US 12B) | 2035-AP-0242 | 2 |  |  | 2025-09-29 | EJJ
| 2035-A3-182-(1 TO 3)_R0(SAPURA-1200 AP during pipelaying of PL-3 from USSC RP-1 to US-142A_Aviation Sketches) | 2035-A3-182 | 0 |  |  | 2025-10-06 | EJJ
| 2035-AP-0251-1 TO 3_R2(SAPURA-1200 AP during pipelaying of PL-10 from HP-3 to HP-2) | 2035-AP-0251 | 2 |  |  | 2025-10-16 | EJJ
| 2035-AP-0001_R1(SAFEEN-3000 AP during PL-3 Riser & Spool installation at RP1) | 2035-AP-0001 | 1 |  |  | 2025-10-24 | SKV
| (SAPURA-1200 AP during pipelaying of PL-3 from USSC RP-1 to US-142A)_TOTAL_WITH BUOY | 2035-AP-0244 | 3 |  |  | 2025-10-28 | EJJ
| (SAPURA-1200 AP during pipelaying 16 inch WF PL-4 from US 19B to US 153A) | 2035-AP-0245 | 1 |  |  | 2025-10-29 | EJJ
| (SAPURA-1200 AP during pipelaying of PL-5 from USSC RP-1 to US-153A)_with RIG | 2035-AP-0246 | 2 |  |  | 2025-10-31 | EJJ
| 2035-AP-0002_R1(SAFEEN-3000 AP during PL-5 Riser & Spool installation at RP1) | 2035-AP-0002 | 1 |  |  | 2025-11-10 | SKV
| 2035-DP-0046-1 TO 5_R1( SAFEEN-3000 DP Setup during PL-8 Pipelay from USSC RP-1 TO HP-3) | 2035-DP-0046 | 1 |  |  | 2025-11-11 | SKV
| 2035-AP-0000_R1(SAFEEN-3000 AP during PL-3 Shifting at US-142A) | 2035-AP-0000 | 1 |  |  | 2025-11-12 | SKV
| 2035-A1-023-2 OF 2_R6(SAFEEN 3000 SET-UP for (PL-8) PROP. 16 inch WF PL.FROM USSC-RP1 TO HP-3) | 2035-A1-023 | 6 |  |  | 2025-11-12 | SKV
| 2035-DP-0046-1 TO 5_R1( SAFEEN-3000 DP Setup during PL-8 Pipelay from USSC RP-1 TO HP-3) | 2035-DP-0046 | 1 |  |  | 2025-11-12 | SKV
| 2035-AP-0001_R2(SAFEEN-3000 AP during PL-3 Riser & Spool installation at RP1) | 2035-AP-0001 | 2 |  |  | 2025-11-13 | SKV
| 2035-AP-0002_R2(SAFEEN-3000 AP during PL-5 Riser & Spool installation at RP1) | 2035-AP-0002 | 2 |  |  | 2025-11-13 | SKV
| 2035-A1-023-2 OF 2_R7(SAFEEN 3000 SET-UP for (PL-8) PROP. 16 inch WF PL.FROM USSC-RP1 TO HP-3) | 2035-A1-023 | 7 |  |  | 2025-11-18 | SKV
| 2035-AP-0248-1 TO 6_R3(SAPURA-1200 AP during pipelaying of PL-7 from USSC RP-1 to HP-2) | 2035-AP-0248 | 3 |  |  | 2025-11-21 | EJJ
| 2035-AP-0250_R1(SAPURA-1200 AP during pipelaying 16 inch WF PL-4 from USSC RP1 to HP-3)_TOTAL | 2035-AP-0250 | 1 |  |  | 2025-11-24 | EJJ
| 2035-A1-041_R0(INTERFACE Between SAPURA-1200 Vs SAFEEN-3000 Vs SEP-750 @ RP-1) | 2035-A1-041 | 0 |  |  | 2025-11-25 | SKV
| 2035-AP-0250-1 TO 4_R1(SAPURA-1200 AP during pipelaying 16 inch WF PL-9 from USSC RP1 to HP-3) | 2035-AP-0250 | 1 |  |  | 2025-11-25 | EJJ
| 2035-A1-041_R0(INTERFACE Between SAPURA-1200 Vs SAFEEN-3000 Vs SEP-750 @ RP-1) | 2035-A1-041 | 0 |  |  | 2025-11-26 | SKV
| 2035-A1-041-1_R1(INTERFACE Between SAPURA-1200 Vs SAFEEN-3000 Vs SEP-650 Vs SEP-750 @ RP-1) | 2035-A1-041 | 1 |  |  | 2025-11-26 | SKV
| 2035-A1-041-2_R1(INTERFACE Between SAPURA-1200 Vs SAFEEN-3000 Vs SEP-650 Vs SEP-750 @ RP-1) | 2035-A1-041 | 1 |  |  | 2025-11-26 | SKV
| 2035-DP-0041-1 TO 4_R4( SAFEEN-3000 DP Setup during PL-1 Pipelay from US 159A TO US 12B) | 2035-DP-0041 | 4 |  |  | 2025-12-03 | EJJ
| 2035-DP-0042-1 TO 6_R3( SAFEEN-3000 DP Setup during PL-2 Pipelay from USSC RP-1 TO US 12B) | 2035-DP-0042 | 3 |  |  | 2025-12-03 | EJJ
| 2035-DP-0050-1 TO 4_R3( SAFEEN-3000 DP Setup during PL-6 Pipelay from HP1 TO HP2) | 2035-DP-0050 | 3 |  |  | 2025-12-03 | EJJ
| 2035-16 inch WF PL-9 from USSC RP1 to HP-3_possible route |  |  |  |  | 2025-12-03 | EJJ
| 2035-A1-021-1 OF 2_R2(SAFEEN 3000 SET-UP for (PL-6) PROP. 18 inch WF PL.FROM HP1 TO HP-2) | 2035-A1-021 | 2 |  |  | 2025-12-09 | SKV
| 2035-A1-021-2 OF 2_R2(SAFEEN 3000 SET-UP for (PL-6) PROP. 18 inch WF PL.FROM HP1 TO HP-2) | 2035-A1-021 | 2 |  |  | 2025-12-09 | SKV
| 2035-AP-0003_R1(SAFEEN-3000 AP during PL-7 Riser & Spool installation at RP1) | 2035-AP-0003 | 1 |  |  | 2025-12-19 | SKV
| 2035-DP-0046-1 TO 6_R1( SAFEEN-3000 DP Setup during PL-8 Pipelay from RP-1 TO HP-3) | 2035-DP-0046 | 1 |  |  | 2025-12-23 | EJJ
| 2035-DP-0024_R2 (CB(SAFEEN-3000) SETUP DURING PL LATERAL SHIFTING & SPOOL INSTALLATION AT 142A) | 2035-DP-0024 | 2 |  |  | 2025-12-26 | SKV
| 2035-AP-0248-2 OF 6_R4(SAPURA-1200 AP during pipelaying of PL-7 from USSC RP-1 to HP-2) | 2035-AP-0248 | 4 |  |  | 2026-01-11 | EJJ
| 2035-AP-0251-1 TO 3_R2(SAPURA-1200 AP during pipelaying of PL-10 from HP-3 to HP-2) | 2035-AP-0251 | 2 |  |  | 2026-01-13 | EJJ
| 2035-AP-0245-2 OF 2_R1(SAPURA-1200 AP during pipelaying 16 inch WF PL-4 from US 19B to US 153A) with SEP-650 @ US-153 | 2035-AP-0245 | 1 |  |  | 2025-01-15 | EJJ
| 2035-DP-0087_R1(SAFEEN-3000 DP SET-UP DURING SOUTH RISER FENDER AND WALK-WAY INSTALLATION @ RP-1) | 2035-DP-0087 | 1 |  |  | 2026-01-23 | EJJ
| 2035-DP-0046-1 TO 6_R1( SAFEEN-3000 DP Setup during PL-8 Pipelay from RP-1 TO HP-3) | 2035-DP-0046 | 1 |  |  | 2026-01-26 | EJJ
| 2035-DP-0046-1 TO 6_R2( SAFEEN-3000 DP Setup during PL-8 Pipelay from RP-1 TO HP-3) | 2035-DP-0046 | 2 |  |  | 2026-02-11 | EJJ
| 2035-AP-0248-5 OF 6_R5(SAPURA-1200 AP during pipelaying of PL-7 from USSC RP-1 to HP-2) | 2035-AP-0248 | 5 |  |  | 2026-02-11 | EJJ
| 2035-A3-199 - TEMPORARY SUPPORT FOR A&R CABLE CROSSING LOCATION AT US-HP2 (18"WF P/L-7) FROM US-HP-2 TO USSC-RP1 | 2035-A3-199 | 0 |  |  | 2026-02-13 | EJJ
| 2035-A3-200_R0(TEMP. SUPPORT for A&R Cable crossing location at US-HP2 (16 inch WI PL (PL-10) FROM US-HP-3 TO US-HP2) | 2035-A3-200 | 0 |  |  | 2026-02-13 | EJJ
| 2035-AP-0252-1 TO 3_R1(SAPURA-1200 AP during pipelaying 16 inch WF PL-11 from HP-2 to HP-1) | 2035-AP-0252 | 1 |  |  | 2026-02-13 | EJJ
| 2035-AP-0248-1 TO 6_R5(SAPURA-1200 AP during pipelaying of PL-7 from USSC RP-1 to HP-2) | 2035-AP-0248 | 5 |  |  | 2026-02-16 | VSK
| QMS SUBHIYA ESCAPE ROUTE FROM US-159 TO ANCHORAGE | 2035-A-065 | 0 |  |  | 2026-03-04 | VSK
| 2035-AP-0274_R1(DLB 1000 AP PL-7 & PL-10 Corridor spools installation at HP-2) | 2035-AP-0274 | 1 |  |  | 2026-03-10 | EJJ
| 2035-AP-0275_R1(DLB 1000 AP PL-8 & PL-9 lateral shifting, PL-8, PL-9 & PL-10 Corridor spools installation @ HP-3) | 2035-AP-0275 | 1 |  |  | 2026-03-10 | EJJ
| 2035-AP-0003_R2(SAFEEN-3000 AP during PL-7 Riser & Spool installation at RP1) | 2035-AP-0003 | 2 |  |  | 2026-03-10 | EJJ
| 2035-AP-0139_R1(SAFEEN-3000 DP SET-UP during PL-8 & PL-2 Riser and spools installation at RP-1) | 2035-AP-0139 | 1 |  |  | 2026-03-11 | EJJ
| 2035-AP-0280_R1(SAFEEN 3000 AP SET-UP AT HP-1 for Corridor spools installation of PL-6) | 2035-AP-0280 | 1 |  |  | 2026-03-13 | EJJ
| 2035-AP-0276_R1(DLB 1000 AP PL-1 Corridor spools installation at US-159A) | 2035-AP-0276 | 1 |  |  | 2026-03-23 | EJJ
| 2035-AP-0277-1 & 2_R1(DLB 1000 AP PL-2 Lateral shifting and corridor spools installation at US-12B) | 2035-AP-0277 | 1 |  |  | 2026-03-23 | EJJ
| 2035-AP-0278_R1(DLB 1000 AP PL-4 Corridor spools installation at US-19B) | 2035-AP-0278 | 1 |  |  | 2026-03-23 | EJJ
| 2035-AP-0279-1 & 2_R1(DLB 1000 AP PL-4 Lateral shifting and corridor spools installation at US-153A) | 2035-AP-0279 | 1 |  |  | 2026-03-23 | EJJ
| 2035-AP-0281_R1(DLB 1000 AP during PL- 1 Corridor spools installation at US-12B) | 2035-AP-0281 | 1 |  |  | 2026-03-23 | EJJ
| 2035-AP-0282_R1(DLB 1000 AP during PL-5 Corridor spools installation at US-153A) | 2035-AP-0282 | 1 |  |  | 2026-03-23 | EJJ
| 2035-A4-007_R0(DLS-4200 DP Setup during PL-1 Pipelay_laydown@US-12B) | 2035-A4-007 | 0 |  |  | 2026-03-25 | EJJ
| 2035-A4-008_R0(DLS-4200 DP Setup during PL-11 Pipelay_laydown@US-HP2) | 2035-A4-008 | 0 |  |  | 2026-03-25 | EJJ
| 2035-AP-0271_R1(DLB 1000 AP PL-2, PL-7, PL-8 & PL-9 Riser and spools installation at RP-1) | 2035-AP-0271 | 1 |  |  | 2026-03-30 | EJJ
| 2035-AP-0272_R1(DLB 1000 AP PL-6 & PL-11 Corridor spools installation at HP-1) | 2035-AP-0272 | 1 |  |  | 2026-03-30 | EJJ
| 2035-AP-0273_R1(DLB 1000 AP PL-6 & PL-11 Corridor spools installation at HP-2) | 2035-AP-0273 | 1 |  |  | 2026-03-30 | EJJ
| 2035-AP-0274_R1(DLB 1000 AP PL-7 & PL-10 Corridor spools installation at HP-2) | 2035-AP-0274 | 1 |  |  | 2026-03-30 | EJJ
| 2035-AP-0275-1 & 2_R1(DLB 1000 AP PL-8 & PL-9 lateral shifting, PL-8, PL-9 & PL-10 corridor spools installation @ HP-3) | 2035-AP-0275 | 1 |  |  | 2026-03-30 | EJJ
| 2035-AP-0276_R1(DLB 1000 AP PL-1 Corridor spools installation at US-159A) | 2035-AP-0276 | 1 |  |  | 2026-03-30 | EJJ
| 2035-AP-0277-1 & 2_R1(DLB 1000 AP PL-2 Lateral shifting and corridor spools installation at US-12B) | 2035-AP-0277 | 1 |  |  | 2026-03-30 | EJJ
| 2035-AP-0278_R1(DLB 1000 AP PL-4 Corridor spools installation at US-19B) | 2035-AP-0278 | 1 |  |  | 2026-03-30 | EJJ
| 2035-AP-0279-1 & 2_R1(DLB 1000 AP PL-4 Lateral shifting and corridor spools installation at US-153A) | 2035-AP-0279 | 1 |  |  | 2026-03-30 | EJJ
| 2035-AP-0281_R1(DLB 1000 AP during PL- 1 Corridor spools installation at US-12B) | 2035-AP-0281 | 1 |  |  | 2026-03-30 | EJJ
| 2035-AP-0282_R1(DLB 1000 AP during PL-5 Corridor spools installation at US-153A) | 2035-AP-0282 | 1 |  |  | 2026-03-30 | EJJ
| 2035-DP-0048-1 TO 6_R2( SAFEEN-3000 DP Setup during PL-10 Pipelay from HP2 TO HP3) | 2035-DP-0048 | 2 |  |  | 2026-04-03 | EJJ
| 2035-A1-025-1 TO 2_R2(SAFEEN 3000 DP SET-UP for pipelaying of PL-10) _START-UP & LAY-DOWN) | 2035-A1-025 | 2 |  |  | 2026-04-04 | EJJ
| 2035-DP-0048-1 TO 6_R2( SAFEEN-3000 DP Setup during PL-10 Pipelay from HP2 TO HP3) | 2035-DP-0048 | 2 |  |  | 2026-04-04 | EJJ
| 2035-A1-025-1 TO 2_R2(SAFEEN 3000 SET-UP for (PL-10) PROP. 16 inch WI PL.FROM HP-3 TO HP-2) | 2035-A1-025 | 2 |  |  | 2026-04-06 | EJJ
| 2035-DP-0048-1 TO 6_R2( SAFEEN-3000 DP Setup during PL-10 Pipelay from HP2 TO HP3) | 2035-DP-0048 | 2 |  |  | 2026-04-06 | EJJ
| 2035-A1-025-1 TO 2_R2(SAFEEN 3000 SET-UP for (PL-10) PROP. 16 inch WI PL.FROM HP-3 TO HP-2) | 2035-A1-025 | 4 |  |  | 2026-04-09 | EJJ
| 2035-DP-0048-1 TO 6_R2( SAFEEN-3000 DP Setup during PL-10 Pipelay from HP2 TO HP3) | 2035-DP-0048 | 3 |  |  | 2026-04-09 | EJJ
| 2035-AP-0283-1 TO 3_R1( SAFEEN-3000 AP Setup during PL-8 Pipelay from KP 4.152 TO HP-3) | 2035-AP-0283 | 1 |  |  | 2026-04-10 | EJJ
| 2035-A1-067-1 & 2_R0(DLB 750 AP SET-UP during pipelaying of PL-1) _START-UP & LAY-DOWN) | 2035-A1-067 | 0 |  |  | 2025-04-15 | EJJ
| 2035-A1-068-1 & 2_R0(DLB 750 AP SET-UP during pipelaying of PL-4) _START-UP & LAY-DOWN) | 2035-A1-068 | 0 |  |  | 2025-04-15 | EJJ
| 2035-AP-0141-1 & 2_R1(DLB-750 AP during pipelaying 16 inch WF PL-1 from US 159A to US 12B) | 2035-AP-0141 | 1 |  |  | 2026-04-16 | EJJ
| 2035-AP-0142-1 & 2_R1(DLB-750 AP during pipelaying 16 inch WF PL-4 from US 19B to US 153A) | 2035-AP-0142 | 1 |  |  | 2026-04-16 | EJJ
| 2035-A1-067-1 & 2_R1(DLB 750 AP SET-UP during pipelaying of PL-1) _START-UP & LAY-DOWN) | 2035-A1-067 | 1 |  |  | 2026-04-27 | EJJ
| 2035-AP-0141-1 & 2_R1(DLB-750 AP during pipelaying 16 inch WF PL-1 from US 159A to US 12B) | 2035-AP-0141 | 1 |  |  | 2026-04-27 | EJJ
| 2035-A1-068-1 & 2_R1(DLB 750 AP SET-UP during pipelaying of PL-4) _START-UP & LAY-DOWN) | 2035-A1-068 | 1 |  |  | 2026-04-27 | EJJ
| 2035-AP-0142-1 & 2_R1(DLB-750 AP during pipelaying 16 inch WF PL-4 from US 19B to US 153A) | 2035-AP-0142 | 1 |  |  | 2026-04-27 | EJJ
| 2035-AP-0271_R2(DLB 1000 AP PL-2, PL-7, PL-8 & PL-9 Riser stalk-on and corridor spools installation at RP-1) | 2035-AP-0271 | 2 |  |  | 2026-04-27 | EJJ
| 2035-A1-067-1 & 2_R2(DLB 750 AP SET-UP during pipelaying of PL-1) _START-UP & LAY-DOWN) | 2035-A1-067 | 2 |  |  | 2026-05-04 | EJJ
| 2035-AP-0141-1 & 2_R1(DLB-750 AP during pipelaying 16 inch WF PL-1 from US 159A to US 12B) | 2035-AP-0141 | 1 |  |  | 2026-05-05 | EJJ
| 2035-AP-0142-1 & 2_R1(DLB-750 AP during pipelaying 16 inch WF PL-4 from US 19B to US 153A) | 2035-AP-0142 | 1 |  |  | 2026-05-05 | EJJ
| 2035-A3-0214_R0(SAFEEN-3000 DP SET-UP for pipelaying 0f PL-11 @ HP-2)_LAY-DOWN STUDY | 2035-A3-0214 | 0 |  |  | 2026-05-06 | EJJ
| 2035-DP-0049-1 TO 4_R1( SAFEEN-3000 DP Set-up during PL-11 Pipelay from HP1 TO HP2) | 2035-DP-0049 | 1 |  |  | 2026-05-11 | EJJ
| 2035-A3-0215-1 TO 3_R0(DLB 1000 Aviation clearance during Stalk-on Riser and Spools Installation at RP-1) | 2035-A3-0215 | 0 |  |  | 2026-05-12 | EJJ
| 2035-AP-XXXX_R1(SEP-650 SET-UP during HOOK-UP works at HP-1) |  | 1 |  |  | 2026-05-20 | EJJ
| 2035-A3-0217-1 TO 3_Rev-B( QMS SUBHIYAN AVIATION CLEARANCE AT HP-3) | 2035-A3-0217 | B |  |  | 2026-05-23 | EJJ
| 2035-AP-0284_R1( QMS SUBHIYAN SETUP AT HP-3) | 2035-AP-0284 | 1 |  |  | 2026-05-23 | EJJ
| 2035-AP-0285_R1(SEP-650 SET-UP during HOOK-UP works at HP-1) | 2035-AP-0285 | 1 |  |  | 2026-05-23 | EJJ
| 2035-AP-0140_R2-SEP-650 ANCHOR PATTERN AT RP-1 WEST SIDE | 2035-AP-0140 | 2 |  |  | 2026-05-25 | EJJ
| 2035-AP-0275-1 & 2_R2(DLB 1000 AP PL-8 & PL-9 lateral shifting, PL-8, PL-9 & PL-10 corridor spools installation @ HP-3) | 2035-AP-0275 | 2 |  |  | 2026-06-01 | EJJ
| 2035-A3-0205_Rev-B(SEP-650 AVIATION CLEARANCE AT RP-1) | 2035-A3-0205 | B |  |  | 2026-06-02 | EJJ
| 2035-A1-069_R0(DLB-1000 SETUP SEQUENCE DURING CORRIDOR SPOOL INSTALLATION AT HP-1) | 2035-A1-069 | 0 |  |  | 2026-06-04 | SKV
| 2035-A1-070_R0(SAFEEN PEARL CLASH CHECK AT US-142) | 2035-A1-070 | 0 |  |  | 2026-06-09 | EJJ
| 2035-A1-071-1 TO 6_R0(INTERFACE STUDY AT US-HP1) | 2035-A1-071 | 0 |  |  | 2026-06-12 | EJJ
| 2035-A1-072-1 TO 9_R0(INTERFACE STUDY AT US-HP2) | 2035-A1-072 | 0 |  |  | 2026-06-16 | EJJ
| 2035-A1-073-1 TO 9_R0(INTERFACE STUDY AT US-HP3) | 2035-A1-073 | 0 |  |  | 2026-06-16 | EJJ
| 2035-AP-0271_R3(DLB 1000 AP PL-2, PL-7, PL-8 Stalk-on Riser and PL-9 Spools Installation at RP-1) | 2035-AP-0271 | 3 |  |  | 2026-07-01 | EJJ
| 2035-DP-0041-1 TO 4_R5( SAFEEN-3000 DP Setup during PL-1 Pipelay from US 159A TO US 12B) | 2035-DP-0041 | 5 |  |  | 2026-07-09 | EJJ
| 2035-AP-0271_R3(DLB 1000 AP PL-2, PL-7, PL-8 Stalk-on Riser and PL-9 Spools Installation at RP-1) | 2035-AP-0271 | 3 |  |  | 2026-07-09 | EJJ
| 2035-AP-0271-1 & 2_R3(DLB 1000 AP during stalk-on riser, spool, walkway and fender installation at RP-1) | 2035-AP-0271 | 3 |  |  | 2026-07-15 | EJJ
| 2035-DP-0045-1 TO 3_R3( SAFEEN-3000 DP Setup during PL-4 Pipelay from 19-B TO 153-A) | 2035-DP-0045 | 3 |  |  | 2026-07-24 | EJJ
| 2035-DP-0049-1 TO 4_R2( SAFEEN-3000 DP Setup during PL-11 Pipelay from HP1 TO HP2) | 2035-DP-0049 | 2 |  |  | 2026-07-24 | EJJ