## 2171-2172
CRPO -69 (Project 2171/2172) Offshore Support Deliverable List
# | Document No. | Title | Rev. | Issue Date (Planned) | Outgoing Ref No. | Issue Date (Actual) | Remarks
- | Construction and Installation Procedure
1 | 2171-2172-PP-OF-012 | ANCHOR HANDLING PROCEDURE FOR FLOATING BARGE | A1 | 2021-08-30 | T-553/21 | 2021-12-23
|  |  | A | 2022-01-19 | T-007/22 | 2022-01-19
|  |  | 00 |  | T-108/22 | 2022-03-28
2 | 2171-2172-PP-OF-013 | PROCEDURE FOR SURVEY OF PIPELINE CONDITION AT TIE-IN LOCATION | A1 |  | T-304/21 | 2021-07-13
|  |  | A |  | T-337/21 | 2021-08-08
|  |  | B |  | T-432/21 | 2021-10-12
|  |  | 00 | 2021-12-28 | T-561/21 | 2021-12-28
|  |  | 00A |  | T-131/23 | 2023-04-17
3 | 2171-2172-PP-OF-015 | PROCEDURE FOR SUBSEA EXCAVATION WORK AT TIE-IN LOCATION | A1 |  | T-342/21 | 2021-08-11
|  |  | A |  | T-346/21 | 2021-08-15
|  |  | 00 |  | T-433/21 | 2021-10-13
|  |  | 00A | 2021-12-27 | T-560/21 | 2021-12-27
4 | 2171-2172-PP-OF-016 | PROCEDURE FOR REMOVAL OF PIPELINE COATING AT TIE-IN LOCATION | A1 |  | T-352/21 | 2021-08-19
|  |  | A |  | T-356/21 | 2021-08-23
|  |  | B |  | T-431/21 | 2021-10-12
|  |  | 00 | 2021-11-04 | T-466/21 | 2021-11-04
|  |  | 00A | 2022-01-05 | T-003/22 | 2022-01-05
5 | 2171-2172-PP-OF-017 | PROCEDURE FOR INSTALLATION OF CONCRETE SLEEPERS | A1 | 2021-10-10 | T-006/22 | 2022-01-18
|  |  | A | 2022-02-24 | T-067/22 | 2022-02-24
|  |  | 00A |  | T-008/23 | 2023-01-09
6 | 2171-2172-PP-OF-018 | PROCEDURE FOR INSTALLATION OF CONCRETE MATTRESSES |  | 2021-10-15
7 | 2171-2172-PP-OF-019 | PIPELINES INSTALLATION MANUAL | A1 |  | T-399/21 | 2021-09-22
|  |  | A |  | T-408/21 | 2021-09-26
|  |  | B |  | T-014/22 | 2022-01-20 | PMT ISSUED TO CLIENT
8 | 2171-2172-PP-OF-020 | PIPELINE EXTERNAL FIELD JOINT COATING PROCEDURE | A1 | 2021-11-15 | T-010/22 | 2022-01-19
|  |  | A |  | T-022/22 | 2022-01-26 | PMT ISSUED TO CLIENT
|  |  | B |  | T-135/22 | 2022-04-12
|  |  | 00 |  | T-177/22 | 2022-05-10
|  |  | 00A |  | T-344/24 | 2024-07-30
9 | 2171-2172-PP-OF-021 | PIPELINE INTERNAL FIELD JOINT COATING PROCEDURE |  | 2021-11-05
10 | 2171-2172-PP-OF-022 | PIPELINE FREESPAN CORRECTION AND GROUT BAGS INSTALLATION PROCEDURE | A1 | 2021-11-01 | T-184/22 | 2022-05-12
|  |  | A |  | T-233/22 | 2022-06-10
|  |  | B |  | T-331/22 | 2022-08-12
|  |  | 00 |  | T-368/22 | 2022-09-14
11 | 2171-2172-PP-OF-023 | PROCEDURE FOR INSTALLATION OF SUBSEA VALVE SKIDS AND ASSOCIATED TIE-IN SPOOLS WITH EXISTING PIPELINES | A | 2021-11-10 | T-279/22 | 2022-07-06
|  |  | 00 |  | T-406/22 | 2022-10-14
|  |  | 00B |  | T-126/23 | 2023-04-13
|  |  | 00C |  | T-149/23 | 2023-05-06
12 | 2171-2172-PP-OF-024 | PROCEDURE FOR INSTALLATION OF SUBSEA SPOOLS FOR BYPASS PIPELINES | A | 2021-11-25 | T-275/22 | 2022-07-05
|  |  | 00 |  | T-407/22 | 2022-10-14
|  |  | 00A |  | T-009/23 | 2023-01-09
|  |  | 00B |  | T-192/24 | 2024-05-08
13 | 2171-2172-PP-OF-025 | FLANGE MANAGEMENT PROCEDURE FOR SUBSEA FLANGE | A1 | 2021-11-20 | T-531/21 | 2021-12-13
|  |  | A |  | T-020/22 | 2022-01-25 | PMT ISSUED TO CLIENT
|  |  | B |  | T-112/22 | 2022-03-29
|  |  | 00A |  | T-441/22 | 2022-11-16
14 | 2171-2172-PP-OF-026 | SUBSEA SPOOL SCRAPING AND HYDROTESTING PROCEDURE | A | 2021-12-20 | T-084/22 | 2022-03-09
|  |  | B |  | T-268/22 | 2022-06-30
|  |  | 00 |  | T-298/22 | 2022-07-25
|  |  | 00A |  | T-206/24 | 2024-05-16
|  |  | 00B |  | T-238/24 | 2024-06-05
15 | 2171-2172-PP-OF-027 | PIPELINE SCRAPING AND HYDROTESTING PROCEDURE |  | 2021-12-01
16 | 2171-2172-PP-OF-028 | PIPELINE TIGHTNESS TEST AND LAY UP PROCEDURE |  | 2021-12-15
17 | 2171-2172-PP-OF-029 | PROCEDURE FOR HOT TAPPING |  | 2021-09-01
18 | 2171-2172-PP-OF-030 | PROCEDURE FOR INSTALLATION OF MECHANICAL CONNECTORS | A1 | 2021-11-15 | T-253/22 | 2022-06-20
|  |  | A |  | T-274/22 | 2022-07-05
|  |  | 00 |  | T-386/22 | 2022-09-28
|  |  | 00A |  | T-442/22 | 2022-11-16
|  |  | 00B |  | T-003/23 | 2023-01-03
|  |  | 00C |  | T-072/23 | 2023-02-21
|  |  | 00D |  | T-119/23 | 2023-04-11
19 | 2171-2172-PP-OF-031 | PROCEDURE FOR INSTALLATION OF HOT TAP CLAMPS AND HANDLING OF HOT TAP STACK UP | A1 | 2022-06-17 | T-248/22 | 2022-06-17
|  |  | A |  | T-278/22 | 2022-07-06
|  |  | 00 |  | T-390/22 | 2022-10-03
|  |  | 00A |  | T-462/22 | 2022-12-05
|  |  | 00B |  | T-088/23 | 2023-03-01
20 | 2171-2172-PP-OF-032 | PIPELINE EXTERNAL INFILL FIELD JOINT COATING PROCEDURE | A1 | 2021-12-06 | T-514/21 | 2021-12-06
|  |  | A | 2021-12-15 | T-537/21 | 2021-12-15
|  |  | 00. | 2021-12-15 | T-012/22 | 2022-01-20
21 | 2171-2172-PP-OF-033 | FBE COATING REPAIR PROCEDURE | A1 | 2022-01-26 | T-023/22 | 2022-01-26
|  |  | A | 2022-02-02 | T-029/22 | 2022-02-02
|  |  | B | 2022-03-16 | T-093/22 | 2022-03-16
|  |  | 00 |  | T-103/22 | 2022-03-24
|  |  | 00A |  | T-199/22 | 2022-05-23
22 | 2171-2172-PP-OF-034 | HOT TAP SIT MANUAL | A1 | 2022-02-21 | T-064/22 | 2022-02-21
|  |  | A | 2022-05-06 | T-171/22
23 | 2171-2172-PP-OF-035 | MID LINE SPOOLS INSTALLATION PROCEDURE FOR BYPASS LINE-1 AND BYPASS LINE-2 | A1 |  | T-209/22 | 2022-05-26
|  |  | A |  | T-218/22 | 2022-06-01
|  |  | 00 |  | T-303/22 | 2022-07-29
|  |  | 00A |  | T-308/23 | 2023-10-17
24 | 2171-2172-PP-OF-036 | METHOD STATEMENT FOR REPLACEMENT OF MECHANICAL CONNECTORS ON 48” CFL-34 | A1 |  | T-042/23 | 2023-01-30
|  |  | A |  | T-044/23 | 2023-01-31
B
|  |  | C |  | T-093/23 | 2023-03-07 | CANCELLED
|  |  | C |  | T-102/23 | 2023-03-13
|  |  | 00 |  | T-121/23 | 2023-04-11
25 | 2171-2172-PP-OF-037 | METHOD STATEMENT TO CONTAIN THE CRUDE SEEPAGE FROM MECHANICAL CONNECTORS AT CFL-34 | A1 |  | T-076/23 | 2023-02-22
|  |  | A |  | T-080/23 | 2023-02-23
|  |  | B |  | T-089/23 | 2023-03-02
26 | 2171-2172-PP-OF-038 | METHOD STATEMENT FOR DEPLOYING GRAVITY ANCHOR USING SAFEEN PRINCE AND AHT | A |  | T-300/22 | 2022-07-27
27 | 2171-2172-PP-OF-039 | METHOD STATEMENT FOR INSPECTION OF HOT TAP CLAMPS AT CFL-32 | A1 |  | T-435/22 | 2022-11-10
|  |  | A |  | T-444/22 | 2022-11-16
|  |  | B |  | T-094/23 | 2023-03-08
|  |  | 00 |  | T-108/23 | 2023-03-16
|  |  | 00A |  | T-140/23 | 2023-04-27
28 | 2171-2172-PP-OF-040 | SUBSEA ANTI CORROSION COATING PROCEDURE | A1 |  | T-436/22 | 2022-11-11
|  |  | A |  | T-438/22 | 2022-11-14
|  |  | B |  | T-111/23 | 2023-03-17
C
29 | 2171-2172-PP-OF-043 | PROCEDURE FOR REMEDIAL WORKS FOR INSTALLATION OF NEW HOT TAP CLAMPS AND NEW MECHANICAL CONNECTORS ON 48” CFL 34 REMEDIAL | A |  | T-218/23 | 2023-07-18
30 | 2171-2172-PP-OF-044 | PROCEDURE FOR THE PREPARATORY WORKS PRIOR TO REMEDIATION BY FLUSHING AT CFL-34 | A |  | PMT ISSUED
31 | 2171-2172-PP-OF-047 | PROCEDURE FOR REMEDIAL WORKS AND INSTALLATION OF NEW MECHANICAL CONNECTORS ON 48” CFL 34 REMEDIAL | A |  | T-343/23 | 2023-11-10
|  |  | B |  | T-114/24 | 2024-03-13

## Sketches
NMDC DOC. No.: MDR-001
CRPO -69 (Project 2171/2172) Offshore Support Deliverable List
|  | NMDC PROJECT NO. 2171-2172 | [6 empty] | REVISION : | 0
|  | OFFSHORE sketches | [6 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| 2171-2172-DP-0086-1 TO 2_Rev-A (MILLENNIUM-3 Setup plan during preconstruction survey activities for CFL-34) | 2171-2172-DP-0086 |  | A |  |  | 2026-09-01 | SKV
| 2171-A0-053_R0(MILLENIUM-3 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2171-A0-053 |  | 0 |  |  | 2026-09-01 | SKV
| 2171-A0-054_R0(MILLENNIUM-3 Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2171-A0-054 |  | 0 |  |  | 2026-09-01 | SKV
| 2171-2172-DP-0089-1 TO 2_Rev-A (SWORDFISH Setup plan during Spool demolition at CFL-34) | 2171-2172-DP-0089 |  | A |  |  | 2026-09-03 | SKV
| 2171-2172-DP-0090-1 TO 2_Rev-A (SWORDFISH Setup plan during Spool installation at CFL-34) | 2171-2172-DP-0090 |  | A |  |  | 2026-09-03 | SKV