## Installation Procedures
NMDC DOC. No.: MDR-001
SAUDI ARABIAN OIL COMPANY ZULF AH EAST & WEST OIL FACILITIES UNDER BI-10-07868
|  | NMDC PROJECT NO. 2300-2302 | [10 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [10 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ARAMCO OFFSHORE | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | Method TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[6 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| Rigid Pipelines Installation Manual | 2300-2302-PP-OF-002 | A1 |  | 2022-12-01 | T-115/23 | 2023-03-30
|  |  | A |  |  | T-167/23 | 2023-06-01 | 2023-07-07 | COM-2300-2302-NPCC-T-01288 | 2023-08-15 | ZOOPD-T-3806-23 | 2 - Reviewed with Comments
|  |  | B |  |  | T-246/23 | 2023-08-16 | 2023-10-09 | COM-2300-2302-NPCC-T-01471 | 2023-10-26 | ZOOPD-T-4515-23 | 4 - Reviewed with no comments
|  |  | 00 |  |  | T-025/24 | 2024-01-17 | 2024-01-19 | COM-2300-2302-NPCC-T-01779
|  |  | 00A |  |  | T-517/24 | 2024-10-21 | 2024-12-24 | COM-2300-2302-NMDC-E-T-02418 | 2025-01-02 | ZOOPD-T-6766-25 | 1- approved
|  |  | 00B |  |  | T-065/26 | 2026-02-10 | 2026-03-18 | COM-2300-2302-NMDC-E-T-03026 | 2026-06-08 | ZOOPD-T-7934-26 | 4 - Reviewed with no comments
| Crossings Supports Installation Procedure (Sleepers and Bridges Supports) | 2300-2302-PP-OF-003 | A1 |  | 2022-12-09 | T-164/23 | 2023-05-24
|  |  | A |  |  | T-185/23 | 2023-06-16 | 2023-06-23 | COM-2300-2302-NPCC-T-01268 | 2023-08-23 | ZOOPD-T-3877-23 | 2 - Reviewed with Comments
|  |  | B |  |  | T-257/23 | 2023-08-30 | 2023-09-04 | COM-2300-2302-NPCC-T-01432 | 26-Sep-2023 | ZOOPD-T-4264-23 | 4 - Reviewed with no comments
|  |  | 00 |  |  | T-292/23 | 2023-10-05 | 2023-10-10 | COM-2300-2302-NPCC-T-01525
|  |  | 00A |  |  | T-371/23 | 2023-12-11 | 2023-12-20 | COM-2300-2302-NPCC-T-01723 | 2023-12-25 | ZOOPD-T-4928-23 | 1- approved
| Retrofit Risers and Clamps Installation Procedure | 2300-2302-PP-OF-004 | A1 |  | 2024-02-26 | T-326/24 | 2024-07-18
|  |  | A |  |  | T-451/24 | 2024-09-21 | 2024-10-09 | COM-2300-2302-NMDC-E-T-02288 | 2024-11-11 | ZOOPD-T-6566-24 | 4 -No comments
| Mattresses Installation Procedures | 2300-2302-PP-OF-005 | A1 |  | 2024-01-30 | T-116/24 | 2024-03-11
|  |  | A |  |  | T-260/24 | 2024-06-14 | 2024-06-26 | COM-2300-2302-NMDC-E-T-02111 | 2024-06-26 | ZOOPD-T-6035-24 | 2 - Reviewed with Comments
| Flange Management Procedure- Subsea Flanges | 2300-2302-PP-OF-006 | A |  | 2023-01-30 | T-075/23 | 2023-02-22 | 2023-06-23 | COM-2300-2302-NPCC-T-01269 | 2023-07-14 | ZOOPD-T-3560-23 | 2 - Reviewed with Comments
|  |  | B |  |  | T-281/23 | 2023-09-22 | 2023-09-26 | COM-2300-2302-NPCC-T-01488 | 2023-11-03 | ZOOPD-T-4537-23 | 1- approved
|  |  | 00 |  |  | T-339/23 | 2023-11-09 | 09-Nov-2023 | COM-2300-2302-NPCC-T-01630
| PIPELINE FREESPAN CORRECTION AND GROUT BAGS INSTALLATION PROCEDURE | 2300-2302-PP-OF-007 | A1 |  | 2024-04-30 | T-168/24 | 2024-04-19
|  |  | A |  |  | T-226/24 | 2024-05-29 | 2024-05-30 | COM-2300-2302-NMDC-E-T-02058 | 2024-06-06 | ZOOPD-T-5780-22 | 2 - Reviewed with Comments
|  |  | B |  |  | T-290/24 | 2024-07-01 | 2024-07-03 | COM-2300-2302-NMDC-E-T-02130 | 2024-08-07 | ZOOPD-T-6124-24 | 3 - Not Approved/Rejected
|  |  | C |  |  | T-370/24 | 2024-08-16 | 2024-08-21 | COM-2300-2302-NMDC-E-T-02215 | 2024-08-22 | ZOOPD-T-6212-24 | 1 - Approved
|  |  | 00 |  |  | T-185-25 | 2025-05-19 | 2025-05-20 | COM-2300-2302-NMDC-E-T-02629
|  |  | 00A |  |  | T-288/26 | 2026-07-08
| Subsea Pipelines Flooding, Scrapping, Hydroesting and Lay up Procedure | 2300-2302-PP-OF-008 |  |  | 2024-12-20
| Subsea Spools and SSVSs Installation procedure | 2300-2302-PP-OF-009 | A1 |  | 2023-08-17 | T-376/23 | 2023-12-13
|  |  | A |  |  | T-231/24 | 2024-05-30 | 2024-06-03 | COM-2300-2302-NMDC-E-T-02062 | 06-Jun-2024 | ZOOPD-T-5779-22 | 1 - Approved
|  |  | B |  |  | T-453/25 | 2025-09-04 | 2025-09-05 | COM-2300-2302-NMDC-E-T-02780 | 2026-02-02 | ZOOPD-T-5779-26 | 1 - Approved
| 15 kV Cables Laying Procedure | 2300-2302-PP-OF-010 | A1 |  | 2024-06-08 | T-431/24 | 2024-09-14
|  |  | A |  |  | T-565/24 | 2024-11-27 | 2024-12-16 | COM-2300-2302-NMDC-E-T-02388 | 2024-12-16 | ZOOPD-T-6663-24 | 2 - Reviewed with Comments
|  |  | B |  |  | T-164/25 | 2025-04-30 | 2025-05-16 | COM-2300-2302-NMDC-E-T-02611 | 2025-05-20 | ZOOPD-T-7156-25 | 1 - Approved
|  |  | 00 |  |  | T-382/25 | 2025-08-01 | 2025-08-01 | COM-2300-2302-NMDC-E-T-02732 | 2025-08-04 | ZOOPD-T-7345-25 | 4 - Reviewed with no comments
| 230 kV Cables Transpooling Procedure | 2300-2302-PP-OF-011 |  |  | 2024-01-25
| Infield 230 kV Cables Installation Procedure | 2300-2302-PP-OF-012 |  |  | 2024-04-25
| 15 kV Cables Transpooling Procedure | 2300-2302-PP-OF-013 |  |  | 2024-04-08
| 230 kV Cable Installation Procedure from Onshore to ZTPS-2 | 2300-2302-PP-OF-014 |  |  | 2024-04-25
| Anchor Handling and Mooring procedure for Floating Barges | 2300-2302-PP-OF-015 |  |  | 2023-12-25
| JACKET INSTALLATION MANUAL | 2300-2302-PP-OF-016 | A |  | 2024-05-25 | T-336/24 | 2024-07-27 | 2024-07-29 | COM-2300-2302-NMDC-E-T-02176 | 2024-09-30 | ZOOPD-T-6371-24 | 4 - Reviewed with no comments
|  |  | 00 |  |  | T-092/25 | 2025-03-04 | 2025-03-05 | COM-2300-2302-NMDC-E-T-02534 | 2025-03-11 | ZOOPD-T-6976-25 | 1 - Approved
| ZTPS-2 Jacket Installation Procedure | 2300-2302-PP-OF-017 |  |  | 2024-06-17
| ZTPS-3 Jacket Installation Procedure | 2300-2302-PP-OF-018 |  |  | 2024-07-02
| ZTPS-4 Jacket Installation Procedure | 2300-2302-PP-OF-019 |  |  | 2024-06-09
| ZEDP-2 Jacket Installation Procedure | 2300-2302-PP-OF-020 |  |  | 2024-06-10
| ZEDP-2 Deck Installation Procedure | 2300-2302-PP-OF-021 | A |  | 2024-09-16 | T-613/25 | 2025-12-11 | 2025-12-11 | COM-2300-2302-NMDC-E-T-02883 | 2026-02-27 | ZOOPD-T-7777-26 | 2 - Reviewed with Comments
| PDMs Installation Procedure | 2300-2302-PP-OF-022 | A |  | 2024-05-13 | T-216/24 | 2024-05-22 | 2024-05-31 | COM-2300-2302-NMDC-E-T-02060 | 2024-08-02 | ZOOPD-T-6040-24 | 2 - Reviewed with Comments
|  |  | B |  |  | T-444/24 | 2024-09-18 | 2024-09-24 | COM-2300-2302-NMDC-E-T-02265 | 12-Nov-2024 | ZOOPD-T-6572-24 | 4 - Reviewed with no comments
| Float over Manual for ZTPS-1 Deck | 2300-2302-PP-OF-023 |  |  | 2024-12-02
| Float over Manual for ZTPS-2 Deck | 2300-2302-PP-OF-024 |  |  | 2024-09-06
| Flexible Pipelines Installation Procedure | 2300-2302-PP-OF-025 |  |  | 2024-03-30
| Float over Manual for ZTPS-3 Deck | 2300-2302-PP-OF-026 |  |  | 2025-03-14
| FLOATOVER INSTALLATION MANUAL FOR ZTPS-4 DECK | 2300-2302-PP-OF-027 | A |  | 2024-06-20 | T-575/24 | 2024-11-05 | 2024-12-11 | COM-2300-2302-NMDC-E-T-02394 | 2025-04-02 | ZOOPD-T-7016-25 | 4 - Reviewed with no comments
|  |  | 00 |  |  | T-152/25 | 2025-04-23 | 2025-04-24 | COM-2300-2302-NMDC-E-T-02608 |  |  | 5 - For Information
|  |  | 00A |  |  | T-440/25 | 2025-08-29 | 2025-09-17 | COM-2300-2302-NMDC-E-T-02795 | 2025-10-20 | ZOOPD-T-7541-25 | 4 - Reviewed with no comments
| Umbilicals Installation Procedure | 2300-2302-PP-OF-028 | A |  | 2024-07-08 | T-090/26 | 2026-02-27 | 2026-02-27 | COM-2300-2302-NMDC-E-T-02985 | 2026-04-29 | ZOOPD-T-7870-263 | 2 - Reviewed with Comments
|  |  | B |  |  | T-217/26 | 2026-05-19 | 2026-05-18 | COM-2300-2302-NMDC-E-T-03129 | 2026-06-01 | ZOOPD-T-7927-26 | 4 - Reviewed with no comments
| ICCPs Cable and Anode Sleds Installation Procedure | 2300-2302-PP-OF-029 | A |  | 2025-06-15 | T-001/26 | 2026-01-02 | 2026-01-06 | COM-2300-2302-NMDC-E-T-02915 | 2026-02-27 | ZOOPD-T-7776-26 | 4 - Reviewed with no comments
|  |  | B |  |  | T-106/26 | 2026-03-12 | 1899-12-31 | COM-2300-2302-NMDC-E-T-03027 | 2026-03-23 | ZOOPD-T-7813-26 | 4 - Reviewed with no comments
|  |  | 00 |  |  | T-130/26 | 2026-04-01 | 2026-04-03 | COM-2300-2302-NMDC-E-T-03054
| External FBE Coating Repair Procedure | 2300-2302-PP-OF-030 |  |  | 2023-01-30
| Pipelines Internal FBE Field joint Coating and Repair Procedure | 2300-2302-PP-OF-031 |  |  | 2023-01-30
| Subsea Spools Internal FBE Field joint Coating and Repair Procedure | 2300-2302-PP-OF-032 |  |  | 2023-01-30
| PIPELINE ANTI-CORROSION FIELD JOINT COATING AND FBE COATING REPAIR PROCEDURE | 2300-2302-PP-OF-033 | A |  | 2023-01-30 | T-166/23 | 2023-05-31 | 2023-06-02 | COM-2300-2302-NPCC-T-01223 | 2023-07-11 | ZOOPD-T-3982-23 | 2 - Reviewed with Comments
|  |  | B |  |  | T-233/23 | 2023-08-07 | 2023-08-29 | COM-2300-2302-NPCC-T-01416 | 21-Nov-2023 | ZOOPD-T-4661-23 | 1 - Approved
|  |  | 00 |  |  | T-188/24 | 2024-05-07 | 2024-05-11 | COM-2300-2302-NMDC-E-T-02025
| Pipeline External Infill Field Joint Coating Procedure | 2300-2302-PP-OF-034 |  |  | 2023-01-30
| METHOD STATEMENT FOR REMEDIAL WORKS ON 10” PIPELINE (ZTPS-4 TO Z1530/1539) | 2300-2302-PP-OF-062 | A |  |  | T-357/24 | 2024-08-08 | Not issued to COMPANY by Transmittal, issued by email to COMPANY by Amjad.
|  |  | 00 |  |  | T-360/24 | 2024-08-09
| METHOD STATEMENT FOR LATERAL SHIFTING OF 10” PIPELINE (ZTPS-4 TO Z1530/1539) TO ITS PROPOSED ROUTE BY LATERAL SHIFTING OF 12” PIPELINE (HDR#18 Z1330/1339 TO ZTPS-4) | 2300-2302-PP-OF-064 | A |  |  | T-427/24 | 2024-09-13
| SUBSEA FLOODING PROCEDURE FOR INFIELD PIPELINE AND TIE IN PIPELINE | 2300-2302-PP-OF-130 | A1 |  |  | T-083/25 | 2025-03-06
|  |  | A |  |  | T-122/25 | 2025-03-27 | 2025-04-17 | COM-2300-2302-NMDC-E-T-02601 | 2025-08-14 | ZOOPD-T-7376-25 | 1 - Approved
|  |  | B |  |  | T-534/25 | 2025-10-20
|  |  | 00 |  |  | T-290/26 | 2026-07-09 | 2026-07-10 | COM-2300-2302-NMDC-E-T-03187 | 2026-07-21 | ZOOPD-T-7973-26 | 1 - Approved
| MS FOR 230 kV SUBMARINE COMPOSITE CABLES STRAIGHTENING AND PULLING AT ZULF TPS AND EDP PLATFORMS | 2300-2302-PP-OF-133 | A |  |  | T-175/25 | 2025-05-02
|  |  | B |  |  | T-216/25 | 2025-06-02 | 2025-06-02 | COM-2300-2302-NMDC-E-T-02660 | 2025-06-09 | ZOOPD-T-7206-25 | 1 - Approved
|  |  | C |  |  | T-246/26 | 2028-06-12 | 17-Jun-2026 | COM-2300-2302-NMDC-E-T-03163 | 2026-07-06 | ZOOPD-T-7960-26 | 1 - Approved
| WORK PLAN FOR CCC MARITIME 2 | 2300-2302-PP-OF-137 | A |  |  | T-140/25 | 2025-04-11 | 2025-04-10 | COM-2300-2302-NMDC-E-T-02587 | 2025-04-22 | ZOOPD-T-7076-25 | 1 - Approved
| WORK PLAN FOR LIFTING AND SHIFTING OF FLEXIBLE REELS BETWEEN SHUJAA-2000/ , CARGO BARGES, AND MILLENNIUM-3 | 2300-2302-PP-OF-160 | A |  | CANCELLED | T-624/25 | 2025-12-16 | 2025-12-25 | COM-2300-2302-NMDC-E-T-02889 | 2026-01-02 | MDDXB-6053-MD-156-1406-01 | 5 - For Information | 2025-12-26 | 2300-2302-NMDC-E-MWS-T-0114
|  |  | B |  |  | T-631/25 | 2025-12-26 | 2026-04-16 | COM-2300-2302-NMDC-E-T-03077 | 2026-02-20 | MDDXB-6053-MD-156-1406-02 | 2 - Reviewed with Comments | 2026-02-10 | 2300-2302-NMDC-E-MWS-T-0115
|  |  | C |  |  | T-162/26 | 2026-04-18 | 2026-04-16 | COM-2300-2302-NMDC-E-T-03078 | 2026-04-20 | ZOOPD-T-7845/26 | 4 - Reviewed with No comments

## Setup Plans & Anchor Patterns
NMDC DOC. No.: MDR-001
SAUDI ARABIAN OIL COMPANY ZULF AH EAST & WEST OIL FACILITIES UNDER BI-10-07868
|  | NMDC PROJECT NO. 2300-2302 | [10 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [10 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ARAMCO OFFSHORE | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | Methods TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[6 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE : | REF | DATE : | REF | CODE
| DELMA-2000 PASSAGE PLAN FROM ANCHORAGE TO RBYN 10/19 | 2300-A0-010 | 0 |  | 2023-11-03 | T-325/23 | 2023-11-03
| DELMA-2000 PASSAGE PLAN FROM ANCHORAGE TO ZULF TPS-4 | 2300-A0-011 | 0 |  | 2023-11-03 | T-325/23 | 2023-11-03
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF 1230/1239 | 2300-A0-014 |  |  | 2024-03-22
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF 1280/1289 | 2300-A0-015 |  |  | 2024-03-22
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF 1410/1419 | 2302-A0-010 |  |  | 2024-04-15
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF EDP-1 | 2300-A0-017 | 0 |  | 2024-01-03 | T-127/24 | 2024-03-19
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF 1240/1249 | 2300-A0-018 |  |  | 2024-01-03
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF 1490/1499 | 2300-A0-019 |  |  | 2024-01-03
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF 1380/1389 | 2300-A0-020 |  |  | 2024-01-14
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF 1340/1349 | 2300-A0-021 |  |  | 2024-01-14
| DELMA 2000 Passage plan from ANCHORAGE to PL Crossing Locations | 2300-A0-013 |  |  | 2023-10-10
| DLS-4200 PASSAGE PLAN FROM ANCHORAGE TO ZULF TPS-3 | 2300-A0-026 |  |  |  | T-433/24 | 2024-09-16
| DLS-4200 PASSAGE PLAN FROM ANCHORAGE TO ZULF TPS-1 | 2300-A0-027 |  |  |  | T-433/24 | 2024-09-16
| SEP-450 Set- up @ ZULF TP-4 | 2302-A3-013 |  |  | 2023-07-15
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF 1200/1209 | 2300-A0-012 | 0 |  | 2023-11-03 | T-325/23 | 2023-11-03
| DLS-4200 PASSAGE PLAN FROM ANCHORAAGE TO ZULF TPS-3 | 2300-A0-026 | 0 |  |  | T-420/24 | 2024-09-12
| DLS-4200 PASSAGE PLAN FROM ANCHORAAGE TO ZULF TPS-1 | 2300-A0-027 | 0 |  |  | T-420/24 | 2024-09-12
| SHUJAA-2000 PASSAGE PLAN FROM ANCHORAAGE TO ZULF TPS-3 | 2300-A0-028 | 1 |  |  | T-445/24 | 2024-09-19
| SHUJAA-2000 PASSAGE PLAN FROM ANCHORAAGE TO ZULF TPS-1 | 2300-A0-029 | 0 |  |  | T-420/24 | 2024-09-12
| DLS-4200 PASSAGE PLAN FROM ANCHORAGE TO ZULF EDP-2 | 2300-A0-030 | 0 |  |  | T-445/24 | 2024-09-19
| DELMA-2000 PASSAGE PLAN FROM ANCHORAGE TO ZULF 1250-1259 | 2300-A0-031 | 1 |  |  | T-487/24 | 2024-10-03
| DELMA-2000 PASSAGE PLAN FROM ANCHORAGE TO ZULF 1220-1229 | 2300-A0-032 | 1 |  |  | T-487/24 | 2024-10-03
| OML INTERVENTION-2 PASSAGE PLAN FROM ANCHORAGE TO ZULF 1220-1229 | 2300-A0-033 | 1 |  |  | T-487/24 | 2024-10-03
| DELMA-2000 SETUP PLAN DURING 10" PIPELINE LAYING FROM RBYN 10/19 TO ZULF TPS-1 | 2300-DP-0006 | B |  | 2023-11-03 | T-325/23 | 2023-11-03
| DELMA-2000 SETUP PLAN DURING 12" PIPELINE LAYING FROM ZULF 1200/1209 TO ZULF TPS-1 | 2300-DP-0007 | B |  | 2023-11-03 | T-325/23 | 2023-11-03
| DELMA-2000 SETUP PLAN DURING 10" PIPELINE LAYING FROM ZULF 1530/1539 TO ZULF TPS-4 | 2302-DP-0003 | B |  | 2023-11-03 | T-325/23 | 2023-11-03
| DELMA-2000 SETUP PLAN DURING 12" PIPELINE LAYING FROM ZULF 1330/1339 TO ZULF TPS-4 | 2302-DP-0004 | B |  | 2023-11-03 | T-325/23 | 2023-11-03
| DELMA-2000 SET-UP during sleeper installation | 2302-DP-0005 |  |  | 2023-10-10
| DELMA-2000 SETUP PLAN DURING 16" PIPELINE LAYING FROM ZULF 1230/1239 TO ZULF TPS-1 (HDR#1) | 2300-DP-0006 |  |  | 2024-03-22
| DELMA-2000 SETUP PLAN DURING 16" PIPELINE LAYING FROM ZULF 1280/1289 TO ZULF TPS-3 (HDR#12) | 2300-DP-0007 |  |  | 2024-03-22
| DELMA-2000 SETUP PLAN DURING 16" PIPELINE LAYING FROM ZULF 1410/1419 TO ZULF TPS-2 (HDR#8) | 2302-DP-0008 |  |  | 2024-04-15
| DELMA-2000 SET-UP during sleeper installation | 2300-DP-0009 |  |  | 2023-08-01
| DELMA-2000 SETUP PLAN DURING 16" PIPELINE LAYING FROM ZULF TPS-4 TO ZULF 1290/1299 (HDR#17) | 2302-DP-0010 |  |  | 2024-04-15
| DELMA-2000 SETUP PLAN DURING 12" PIPELINE LAYING FROM ZULF 1390/1399 TO ZULF TPS-1 (HDR#3) | 2300-DP-0011 |  |  | 2024-01-03
| DELMA-2000 SETUP PLAN DURING 12" PIPELINE LAYING FROM ZULF 1240/1249 TO ZULF TPS-3 (HDR#11) | 2300-DP-0012 |  |  | 2024-01-03
| DELMA-2000 SETUP PLAN DURING 12" PIPELINE LAYING FROM ZULF 1490/1499 TO ZULF TPS-1 | 2300-DP-0013 |  |  | 2024-01-03
| DELMA-2000 SETUP PLAN DURING 12" PIPELINE LAYING FROM ZULF TPS-2 TO ZULF 1380/1389 (HDR#6) | 2302-DP-0014 |  |  | 2024-01-14
| DELMA-2000 SETUP PLAN DURING MATTRESS INSTALLATION AT CROSSING LOCATION | 2302-DP-0015 | 0 |  | 2024-01-14 | T-127/24 | 2024-03-19
| DELMA-2000 SETUP PLAN DURING 30" PIPELINE LAYING FROM ZULF TPS-2 TO ZULF TPS-4 | 2302-DP-0016 | D |  | 2024-05-19 | T-422/24 | 2024-09-12
| DELMA-2000 SETUP PLAN DURING 30" PIPELINE LAYING FROM ZULF TPS-3 TO ZULF TPS-1 | 2300-DP-0017 |  |  | 2024-06-09
| OML INTERVENTION-2 SETUP AT ZULP EDP-1 | 2300-DP-0027 | D |  |  | T-422/24 | 2024-09-12
| OML JACOB INTERVENTION-2 SETUP PLAN AT ZULF 1220/1229 | 2300-DP-0028 | B |  |  | T-487/24 | 2024-10-03
| SEP-450 SET UP PLAN AT ZULF 1250/1259 | 2300-DP-0029 | A
| SEP-650 SET UP PLAN AT ZULF 1230/1239 | 2300-DP-0030 | A
| OML JACOB INTERVENTION-2 SETUP PLAN AT ZULF 1400/1409 | 2300-DP-0031 | A
| SHUJAA-2000 SET-UP AT ZULP EDP-1 | 2300-DP-0032 | A
| DLS-4200 SETUP PLAN DURING ZTPS-1 JACKET AND PILE INSTALLATION | 2300-DP-0033 | A |  |  | T-420/24 | 2024-09-12
| SHUJAA 2000 SETUP PLAN FOR POST PILING , BOAT LANDING & BALANCE WORK AT ZTPS-1 | 2300-DP-0034 | B |  |  | T-433/24 | 2024-09-16
| DLS-4200 SETUP PLAN DURING ZTPS-3 JACKET AND PILE INSTALLATION | 2300-DP-0035 | B |  |  | T-433/24 | 2024-09-16
| SHUJAA-2000 SETUP PLAN FOR POST PILING BOAT LANDING & BALANCE WORK AT ZTPS-3 | 2300-DP-0036 | B |  |  | T-445/24 | 2024-09-19
| DLS-4200 SETUP PLAN DURING ZEDP-2 JACKET AND PILE INSTALLATION | 2300-DP-0037 | A |  |  | T-445/24
| DELMA-2000 SET-UP PLAN DURING ZULF 1220-1229 PDM INSTALLATION | 2300-DP-0038 | B |  |  | T-487/24 | 2024-10-03
| DELMA-2000 SET-UP PLAN DURING ZULF 1250-1259 PDM INSTALLATION | 2300-DP-0039 | B |  |  | T-487/24 | 2024-10-03
| Pre-Installed Soft Mooring Ropes on ZTPS-1 Jacket legs for Flaotover | 2300-A3-010
| Pre-Installed Soft Mooring Ropes on ZTPS-2 Jacket legs for Flaotover | 2300-A3-020
| Pre-Installed Soft Mooring Ropes on ZTPS-3 Jacket legs for Flaotover | 2300-A3-010
| Pre-Installed Soft Mooring Ropes on ZTPS-3 Jacket legs for Flaotover | 2300-A3-010
| PRE-INSTALLED SOFT MOORING ROPES ON ZTPS-4, ZTPS-3 AND ZTPS-1 FLOATOVER | 2300-A3-036 | C |  |  | T-403/24 | 2024-09-05
| Vessel Anchor Pattern for ZTPS-1 Jacket Installation | 2300-AP-0003 |  |  | 2024-05-25
| Vessel Anchor Pattern for ZTPS-2 Jacket Installation | 2300-AP-0004 |  |  | 2024-06-17
| Vessel Anchor Pattern for ZTPS-3 Jacket Installation | 2300-AP-0005 |  |  | 2024-07-02
| Vessel Anchor Pattern for ZTPS-4 Jacket Installation | 2300-AP-0006 |  |  | 2024-06-09
| Vessel Anchor Pattern for ZEDP-2 Jacket Installation | 2300-AP-007 |  |  | 2024-06-10
| Vessel Anchor Pattern for ZEDP-2 Deck Installation | 2300-AP-008 |  |  | 2024-09-16
| LB-II Anchor Pattern during ZTPS-1 Flaotover | 2300-AP-0001 |  |  | 2024-12-02
| ZTPS-1 Topside Floatover Installation Clearance - Entranace Phase | Sketch |  |  | 2024-12-02
| ZTPS-1 Topside Floatover Installation Clearance - Zero Load Transfer | Sketch |  |  | 2024-12-02
| ZTPS-1 Topside Floatover Installation Clearance - Partial (50%) Load Transfer | Sketch |  |  | 2024-12-02
| ZTPS-1 Topside Floatover Installation Clearance - Partial (90%) Load Transfer | Sketch |  |  | 2024-12-02
| ZTPS-1 Topside Floatover Installation Clearance - Full Load Transfer | Sketch |  |  | 2024-12-02
| ZTPS-1 Topside Floatover Installation Clearance - Barge Retrieval | Sketch |  |  | 2024-12-02
| LB-II Anchor Pattern during ZTPS-2 Flaotover | 2300-AP-0002 |  |  | 2024-09-06
| ZTPS-2 Topside Floatover Installation Clearance - Entranace Phase | Sketch |  |  | 2024-09-06
| ZTPS-2 Topside Floatover Installation Clearance - Zero Load Transfer | Sketch |  |  | 2024-09-06
| ZTPS-2 Topside Floatover Installation Clearance - Partial (50%) Load Transfer | Sketch |  |  | 2024-09-06
| ZTPS-2 Topside Floatover Installation Clearance - Partial (90%) Load Transfer | Sketch |  |  | 2024-09-06
| ZTPS-2 Topside Floatover Installation Clearance - Full Load Transfer | Sketch |  |  | 2024-09-06
| ZTPS-2 Topside Floatover Installation Clearance - Barge Retrieval | Sketch |  |  | 2024-09-06
| LB-II Anchor Pattern during ZTPS-3 Flaotover | 2300-AP-0003 |  |  | 2024-03-14
| ZTPS-3 Topside Floatover Installation Clearance - Entranace Phase | Sketch |  |  | 2024-03-14
| ZTPS-3 Topside Floatover Installation Clearance - Zero Load Transfer | Sketch |  |  | 2024-03-14
| ZTPS-3 Topside Floatover Installation Clearance - Partial (50%) Load Transfer | Sketch |  |  | 2024-03-14
| ZTPS-3 Topside Floatover Installation Clearance - Partial (90%) Load Transfer | Sketch |  |  | 2024-03-14
| ZTPS-3 Topside Floatover Installation Clearance - Full Load Transfer | Sketch |  |  | 2024-03-14
| ZTPS-3 Topside Floatover Installation Clearance - Barge Retrieval | Sketch |  |  | 2024-03-14
| LB-II Anchor Pattern during ZTPS-4 Flaotover | 2300-AP-0004 |  |  | 2024-06-20
| ZTPS-4 Topside Floatover Installation Clearance - Entranace Phase | Sketch |  |  | 2024-06-20
| ZTPS-4 Topside Floatover Installation Clearance - Zero Load Transfer | Sketch |  |  | 2024-06-20
| ZTPS-4 Topside Floatover Installation Clearance - Partial (50%) Load Transfer | Sketch |  |  | 2024-06-20
| ZTPS-4 Topside Floatover Installation Clearance - Partial (90%) Load Transfer | Sketch |  |  | 2024-06-20
| ZTPS-4 Topside Floatover Installation Clearance - Full Load Transfer | Sketch |  |  | 20.06.2024
| ZTPS-4 Topside Floatover Installation Clearance - Barge Retrieval | Sketch |  |  | 20.06.2024
| Vessel Anchor Pattern for ZULF 1210/1219 PDM Installation | 2300-AP-009 |  |  | 16.09.2024
| Vessel Anchor Pattern for ZULF 1200/1209 PDM Installation | 2300-AP-0010 |  |  | 04.12.2024
| Vessel Anchor Pattern for ZULF 1400/1409 PDM Installation | 2300-AP-0011 |  |  | 06.07.2024
| Vessel Anchor Pattern for ZULF 630, 1390/1399 PDM Installation | 2300-AP-0012 |  |  | 02.02.2025
| Vessel Anchor Pattern for RBYN 10/19 PDM Installation | 2300-AP-0013 |  |  | 30.10.2024
| Vessel Anchor Pattern for ZULF 1230/1239 PDM Installation | 2300-AP-0014 |  |  | 13.05.2024
| Vessel Anchor Pattern for ZULF 1220/1229 PDM Installation | 2300-AP-0015 |  |  | 16.05.2024
| Vessel Anchor Pattern for ZULF 1250/1259 PDM Installation | 2300-AP-0016 |  |  | 06.08.2024
| Vessel Anchor Pattern for ZULF 1240/1249 PDM Installation | 2300-AP-0017 |  |  | 18.01.2024
| Vessel Anchor Pattern for ZULF 1260/1269 PDM Installation | 2300-AP-0018 |  |  | 18.10.2024
| Vessel Anchor Pattern for ZULF 1270/1279 PDM Installation | 2300-AP-0019 |  |  | 22.01.2025
| Vessel Anchor Pattern for ZULF 1280/1289 PDM Installation | 2300-AP-0020 |  |  | 26.01.2025
| Vessel Anchor Pattern for ZULF 1490/1499 PDM Installation | 2300-AP-0021 |  |  | 30.01.2025
| Vessel Anchor Pattern for ZULF 1330 PDM Installation | 2300-AP-0022 |  |  | 10.07.2024
| Vessel Anchor Pattern for ZULF 1360 PDM Installation | 2300-AP-0023 |  |  | 09.08.2024
| Vessel Anchor Pattern for ZULF 1370 PDM Installation | 2300-AP-0024 |  |  | 13.08.2024
| Vessel Anchor Pattern for ZULF 1290 PDM Installation | 2300-AP-0025 |  |  | 22.10.2024
| Vessel Anchor Pattern for ZULF 1530 PDM Installation | 2300-AP-0026 |  |  | 26.10.2024
| Vessel Anchor Pattern for ZULF 1340 PDM Installation | 2300-AP-0027 |  |  | 07.11.2024
| Vessel Anchor Pattern for ZULF 1380 PDM Installation | 2300-AP-0028 |  |  | 11.11.2024
| Vessel Anchor Pattern for ZULF 1410 PDM Installation | 2300-AP-0029 |  |  | 15.11.2024
| Vessel Anchor Pattern for ZULF 1310 PDM Installation | 2300-AP-0030 |  |  | 05.02.2025
| Vessel Anchor Pattern for ZULF 1300 PDM Installation | 2300-AP-0031 |  |  | 09.02.2025
| Vessel Anchor Pattern for ZULF 1320 PDM Installation | 2300-AP-0032 |  |  | 02.03.2025
| Passage plan for ZTPS-1 Jacket Installation | 2300-AP-0033 |  |  | 25.05.2024
| Passage plan for ZTPS-2 Jacket Installation | 2300-AP-0034 |  |  | 17.06.2024
| Passage plan for ZTPS-3 Jacket Installation | 2300-AP-0035 |  |  | 02.07.2024
| Passage plan for ZTPS-4 Jacket Installation | 2300-AP-0036 |  |  | 09.06.2024
| Passage plan for ZEDP-2 Jacket Installation | 2300-AP-0037 |  |  | 10.06.2024
| Passage plan for ZEDP-2 Deck Installation | 2300-AP-0038 |  |  | 16.09.2024
| Passage plan for Zulf 1210/1219 Deck Installation | 2300-AP-0039 |  |  | 16.09.2024
| Passage plan for Zulf 1200/1209 Deck Installation | 2300-AP-0040 |  |  | 04.12.2024
| Passage plan for Zulf 1400/1409 Deck Installation | 2300-AP-0041 |  |  | 06.07.2024
| Passage plan for ZULF 630, 1390/1399 Deck Installation | 2300-AP-0042 |  |  | 02.02.2025
| Passage plan for RBYN 10/19 PDM Installation | 2300-AP-0043 |  |  | 30.10.2024
| Passage plan for ZULF 1230/1239 PDM Installation | 2300-AP-0044 |  |  | 13.05.2024
| Passage plan for ZULF 1220/1229 PDM Installation | 2300-AP-0045 |  |  | 16.05.2024
| Passage plan for ZULF 1250/1259 PDM Installation | 2300-AP-0046 |  |  | 06.08.2024
| Passage plan for ZULF 1240/1249 PDM Installation | 2300-AP-0047 |  |  | 18.01.2024
| Passage plan for ZULF 1260/1269 PDM Installation | 2300-AP-0048 |  |  | 18.10.2024
| Passage plan for ZULF 1270/1279 PDM Installation | 2300-AP-0049 |  |  | 22.01.2025
| Passage plan for ZULF 1280/1289 PDM Installation | 2300-AP-0050 |  |  | 26.01.2025
| Passage plan for ZULF 1490/1499 PDM Installation | 2300-AP-0051 |  |  | 30.01.2025
| Passage plan for ZULF 1330 PDM Installation | 2300-AP-0052 |  |  | 10.07.2024
| Passage plan for ZULF 1360 PDM Installation | 2300-AP-0053 |  |  | 09.08.2024
| Passage plan for ZULF 1370 PDM Installation | 2300-AP-0054 |  |  | 13.08.2024
| Passage plan for ZULF 1290 PDM Installation | 2300-AP-0055 |  |  | 22.10.2024
| Passage plan for ZULF 1530 PDM Installation | 2300-AP-0056 |  |  | 26.10.2024
| Passage plan for ZULF 1340 PDM Installation | 2300-AP-0057 |  |  | 07.11.2024
| Passage plan for ZULF 1380 PDM Installation | 2300-AP-0058 |  |  | 11.11.2024
| Passage plan for ZULF 1410 PDM Installation | 2300-AP-0059 |  |  | 15.11.2024
| Passage plan for ZULF 1310 PDM Installation | 2300-AP-0060 |  |  | 05.02.2025
| Passage plan for ZULF 1300 PDM Installation | 2300-AP-0061 |  |  | 09.02.2025
| Passage plan for ZULF 1320 PDM Installation | 2300-AP-0062 |  |  | 02.03.2025
| VESSEL PASSAGE PLAN FROM ZULUF ANCHORAGE TO ZULF TPS-4 | 2302-A0-023 | 0 |  |  | T-421/24 | 2024-09-12
| VESSEL PASSAGE PLAN FROM ZULUF ANCHORAGE TO ZULF TPS-2 | 2302-A0-024 | 1 |  |  | T-433/24 | 2024-09-16
| DLS-4200 SETUP PLAN DURING ZTPS-4 JACKET AND PILE INSTALLATION | 2302-DP-0017 | A |  |  | T-421/24 | 2024-09-12
| SHUJAA 2000 SETUP PLAN FOR POST PILING , BOAT LANDING & BALANCE WORK AT ZTPS-4 | 2302-DP-0018 | A |  |  | T-421/24 | 2024-09-12
| DLS-4200 SETUP PLAN DURING ZTPS-2 JACKET AND PILE INSTALLATION | 2302-DP-0019 | A |  |  | T-421/24 | 2024-09-12
| SHUJAA-2000 SETUP PLAN FOR POST PILING BOAT LANDING & BALANCE WORK AT ZTPS-2 | 2302-DP-0020 | B |  |  | T-433/24 | 2024-09-16

## Sketches
NMDC DOC. No.: MDR-001
SAUDI ARABIAN OIL COMPANY ZULF AH EAST & WEST OIL FACILITIES UNDER BI-10-07868
|  | NMDC PROJECT NO. 2300-2302 | [5 empty] | REVISION : | 0
|  | OFFSHORE SKETCHES | [5 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | REMARKS
SUBMISSION STATUS
[6 empty] | DATE | REF
| 15 KV PC LAYDOWN AT ZEDP-2 | 2300-A1-011 | A |  |  | 2024-08-23 | VSK/KM
| 15 KV PC LAYDOWN AT ZTPS-1 | 2300-A1-012 | A |  |  | 2024-08-23 | VSK/KM
| 15 KV PC LAYDOWN AT ZTPS-3 | 2300-A1-013 | A |  |  | 2024-08-23 | VSK/KM
| VESSEL PASSAGE PLAN FROM ZULUF ANCHORAGE TO ZULF TPS-4 | 2302-A0-023 | 0 |  |  | 2024-08-25 | EJJ/KM
| VESSEL PASSAGE PLAN FROM ZULUF ANCHORAGE TO ZULF TPS-2 | 2302-A0-024 | 0 |  |  | 2024-08-25 | EJJ/KM
| VESSEL PASSAGE PLAN FROM ZULUF ANCHORAGE TO ZULF TPS-2 | 2302-A0-024 | 0 |  |  | 2024-08-25 | EJJ/KM
| DLS-4200 SETUP PLAN DURING ZTPS-2 JACKET AND PILE INSTALLATION | 2302-DP-0019 | A |  |  | 2024-08-22 | EJJ/SJD
| SHUJAA2000 SETUP PLAN DURING ZTPS-2 BOATLANDING INSTALLATION AND BALANCE WORK | 2302-DP-0020 | A |  |  | 2024-08-23 | EJJ/SJD
| PRE-INSTALLED SOFT MOORING ROPES ON ZTPS-4,ZTPS-3 AND ZTPS-1 FLOATOVER | 2300-A3-036 | A |  |  | 2024-08-27 | SS/SJD
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF1230/1239 | 2300-A0-023 | 1 |  |  | 2024-08-27 | DRH/KM
| DELMA-2000 SETUP DURING 16'' PIPELINE LAYING FROM ZULF 1230/1239 TO ZULF TPS-1 | 2300-A0-021 | B |  |  | 2024-08-27 | DRH/KM
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF 1230/1239 | 2300-AO-023 | 1 |  |  | 2024-08-27 | DRH/KM
| DELMA-2000 SETUP PLAN DURING 16" PIPELINE LAYING FROM ZULF 1230/1239 TO ZULF TPS-1 | 2300-DP-0021 | B |  |  | 2024-08-27 | DRH/KM
| OML INTERVENTION-2 PASSAGE PLAAN FROM ANCHORAGE TO ZULF EDP-1 | 2300-A0-025 | 2 |  |  | 2024-09-02 | DRH/SSM
| PRE-INSTALLED SOFT MOORING ROPES ON ZTPS-4,ZTPS-3 AND ZTPS-1 FLOATOVER | 2300-A3-036 | C |  |  | 2024-09-05 | SS/SJD
| DLS-4200 SETUP PLAN DURING ZTPS-1 JACKET AND PILE INSTALLATION | 2300-DP-0033 | A |  |  | 2024-09-05 | EJJ/SJD
| SHUJAA-2000 SETUP PLAN FOR POST PILLING, BOAT LANDING & BALANCE WORK AT ZTPS-1 | 2300-DP-0034 | A |  |  | 2024-09-05 | EJJ/SJD
| SHUJAA-2000 PASSAGE PLAN FROM ANCHORAGE TO ZULF TPS-4 | 2302-A0-025 | 0 |  |  | 2024-09-07 | VKS/KM
| SHUJAA-2000 DP SETUP DURING LATERAL SHIFTING OF 10'' & 12'' P/L | 2302-DP-0017 | A |  |  | 2024-09-10 | VKS/KM
| DLS-4200 SET UP PLAN DURING ZTPS-3 JACKET AND PILE INSTALLATION | 2300-DP-0035 | A |  |  | 2024-09-10 | EJJ/SJD
| SHUJAA-2000 SETUP PLAN FOR POST PILLING, BOAT LANDING & BALANCE WORK AT ZTPS-3 | 2300-DP-0036 | A |  |  | 2024-09-10 | EJJ/SJD
| DLS-4200 PASSAGE PLAN FROM ANCHORAGE TO ZULF TPS-3 | 2300-A0-026 | 0 |  |  | 2024-09-11 | EJJ/SJD
| DLS-4200 PASSAGE PLAN FROM ANCHORAGE TO ZULF TPS-1 | 2300-A0-027 | 0 |  |  | 2024-09-11 | EJJ/SJD
| DLS-4200 PASSAGE PLAN FROM ANCHORAGE TO ZULF TPS-3 | 2300-A0-028 | 0 |  |  | 2024-09-11 | EJJ/SJD
| DLS-4200 PASSAGE PLAN FROM ANCHORAGE TO ZULF TPS-1 | 2300-A0-029 | 0 |  |  | 2024-09-11 | EJJ/SJD
| 203KV PC LAYDOWN AT ZEPD-2 | 2300-A1-014 | A |  |  | 2024-09-16 | VSK/KM
| 203KV PC LAYDOWN AT ZTPS-1-2 | 2300-A1-015 | A |  |  | 2024-09-16 | VSK/KM
| 203KV PC LAYDOWN AT ZTPS-3 | 2300-A1-016 | A |  |  | 2024-09-16 | VSK/KM
| (DELMA-2000 Passage plan from ANCHORAGE to ZULF 1250-1259) | 2300-A0-031 | 0 |  |  | 2024-09-24 | VKS/SJD
| (DELMA-2000 Passage plan from ANCHORAGE to ZULF 1220-1229) | 2300-A0-032 | 0 |  |  | 2024-09-24 | VKS/SJD
| (OML INTERVENTION-2 Passage plan from ANCHORAGE to ZULF 1220-1229) | 2300-A0-033 | 0 |  |  | 2024-09-24 | VKS/SJD
| (OML INTERVENTION-II SET-UP AT ZULF 1220-1229) | 2300-DP-0028 | A |  |  | 2024-09-25 | EJJ/SJD
| (DELMA-2000 set-up plan during ZULF 1220-1229 PDM Installation) | 2300-DP-0038 | A |  |  | 2024-09-25 | EJJ/SJD
| (DELMA-2000 set-up plan during ZULF 1250-1259 PDM Installation) | 2300-DP-0039 | A |  |  | 2024-09-25 | EJJ/SJD
| (DELMA-2000 Passage plan from ANCHORAGE to ZULF 1250-1259) | 2300-A0-031 | 1 |  |  | 2024-09-28 | VKS/SSB
| (DELMA-2000 Passage plan from ANCHORAGE to ZULF 1220-1229) | 2300-A0-032 | 1 |  |  | 2024-09-28 | VKS/SSB
| (OML INTERVENTION-2 Passage plan from ANCHORAGE to ZULF 1220-1229) | 2300-A0-033 | 1 |  |  | 2024-09-28 | VKS/SSB
| ( DELMA -2000 set-up during 30 inch PL from ZTPS-3 to ZTPS-1_Start-up & Lay-down)_option-1 | 2300-A1-009 | 2 |  |  | 2024-10-03 | EJJ/RAH
| ( DELMA -2000 set-up during 30 inch PL from ZTPS-3 to ZTPS-1_Start-up & Lay-down)_option-2 | 2300-A1-009 | 2 |  |  | 2024-10-03 | EJJ/RAH
| ( DELMA -2000 set-up during 30 inch Tie-Line from ZULF TPS-4 TO ZULF TPS-2_Start-up & Lay-down)_option-1 | 2302-A1-007 | 2 |  |  | 2024-10-03 | EJJ/RAH
| (SHUJAA-2000 Passage plan from ANCHORAGE to ZULF TPS-1) | 2300-A0-029 | 1 |  |  | 2024-10-14 | EJJ/SSB
| (SHUJAA-2000 Passage plan from ANCHORAGE to ZEDP-2) | 2300-A0-034 | 0 |  |  | 2024-10-14 | EJJ/SSB
| (OML INTERVENTION-II SET-UP AT ZULF 1220-1229 DURING PREPARATORY WORKS) | 2300-DP-0041 | A |  |  | 2024-10-24 | VKS/SSB
| (DLS-4200 Passage plan from ANCHORAGE to ZULF 1220-1229) | 2300-A0-036 | 0 |  |  | 2024-10-29 | EJJ/SSB
| (DLS-4200 Passage plan from ANCHORAGE to ZULF 1250-1259) | 2300-A0-037 | 0 |  |  | 2024-10-29 | EJJ/SSB
| (DLS-4200 set-up plan during ZULF 1220-1229 PDM Installation) | 2300-DP-0043 | A |  |  | 2024-10-29 | EJJ/SSB
| (DLS-4200 set-up plan during ZULF 1250-1259 PDM Installation) | 2300-DP-0044 | A |  |  | 2024-10-29 | EJJ/SSB
| (OML INTERVENTION-2 Passage plan from ANCHORAGE to ZULF 1250-1259) | 2300-A0-035 | 0 |  |  | 2024-10-29 | EJJ/SSB
| (OML INTERVENTION-II SET-UP AT ZULF 1250-1259) | 2300-DP-0042 | A |  |  | 2024-10-29 | EJJ/SSB
| (DELMA-2000 Passage plan from ANCHORAGE to ZTPS-2) | 2302-A0-026 | 0 |  |  | 2024-10-29 | EJJ/SSB
| (DELMA-2000 Passage plan from ANCHORAGE to ZTPS-4) | 2302-A0-027 | 0 |  |  | 2024-10-29 | EJJ/SSB
| (DELMA-2000 Setup plan during ZTPS-2 Boat Landing installation and jacket balance work) | 2302-DP-0021 | A |  |  | 2024-10-31 | EJJ/SSB
| (DELMA-2000 Setup plan during ZTPS-4 Boat Landing installation and jacket balance work) | 2302-DP-0022 | A |  |  | 2024-10-31 | EJJ/SSB
| ( DELMA -2000 set-up during 30 inch PL from ZTPS-3 to ZTPS-1_Start-up & Lay-down)-DLS-4200 | 2300-A1-009 | 3 |  |  | 2024-11-04 | EJJ/RAH
| ( DELMA -2000 set-up during 30 inch Tie-Line from ZULF TPS-4 TO ZULF TPS-2_Start-up & Lay-down)-SHUJAA-2000 | 2302-A1-007 | 3 |  |  | 2024-11-04 | EJJ/RAH
| (DELMA-2000 Setup plan during ZTPS-2 Boat Landing installation and jacket balance work) | 2302-DP-0021 | B |  |  | 2024-11-06 | EJJ/SSB
| (DELMA-2000 Setup plan during ZTPS-4 Boat Landing installation and jacket balance work) | 2302-DP-0022 | B |  |  | 2024-11-06 | EJJ/SSB
| 2300-A0-038_R0(DLS-4200 Passage plan from ANCHORAGE to ZULF GOSP-2 GGP) | 2300-A0-038 | 0 |  |  | 2024-11-06 | VKS/KM
| 2300-A0-039_R0(DLS-4200 Passage plan from ANCHORAGE to ZULF GOSP-2 GGP) | 2300-A0-039 | 0 |  |  | 2024-11-06 | VKS/KM
| 2300-DP-0049_Rev-A( DLS-4200 SETUP PLAN AT ZULF GOSP-2 GGP) | 2300-DP-0049 | A |  |  | 2024-11-06 | VKS/KM
| (CCC MARITIME-II Passage plan from ANCHORAGE to ZULF 1220-1229) | 2300-A0-040 | 0 |  |  | 2024-11-07 | EJJ/SSB
| (CCC MARITIME-II Passage plan from ANCHORAGE to ZULF 1250-1259) | 2300-A0-041 | 0 |  |  | 2024-11-07 | EJJ/SSB
| (CCC MARITIME-II SET-UP AT ZULF 1220-1229 DURING PREPARATORY WORKS) | 2300-DP-0050 | A |  |  | 2024-11-07 | EJJ/SSB
| (CCC MARITIME-II SET-UP AT ZULF 1250-1259 DURING PREPARATORY WORKS) | 2300-DP-0051 | A |  |  | 2024-11-07 | EJJ/SSB
| (DELMA -2000 set-up during 30 inch PL from ZTPS-3 to ZTPS-1_Start-up & Lay-down)-DLS-4200 & SUJAAH_option-1 & 2 | 2300-A1-009 | 4 |  |  | 2024-11-08 | EJJ/RAH
| ( DELMA -2000 set-up during 30 inch Tie-Line from ZULF TPS-4 TO ZULF TPS-2_Start-up & Lay-down)-DLS-4200 & SUJAAH_option-1 & 2 | 2302-A1-007 | 4 |  |  | 2024-11-08 | EJJ/RAH
| (DELMA-2000 SET-UP during remaining sleeper installation)- Commented by Constr. | 2300-DP-0052 | A |  |  | 2024-11-12 | EJJ/RAH
| (Passage plan from ANCHORAGE to ZULF 1230-1239) | 2300-A0-044 | 0 |  |  | 2024-11-14 | EJJ/SSB
| (SHUJAA-2000 set-up plan during ZULF 1230-1239 PDM Installation) | 2300-DP-0045 | B |  |  | 2024-11-19 | EJJ/SSB
| (OML INTERVENTION-II PASSAGE PLAN FROM ANCHORAGE TO ZULF EDP-1) | 2300-A0-025 | 3 |  |  | 2024-11-19 | EJJ/SSB
| (OML INTERVENTION-II SET-UP AT ZULF EDP-1) | 2300-DP-0027 | E |  |  | 2024-11-19 | EJJ/SSB
| (SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1400-1409) | 2300-A0-047 | 0 |  |  | 2024-11-19 | EJJ/SSB
| (SHUJAA-2000 set-up plan during ZULF 1400-1409 PDM Installation) | 2300-DP-0046 | A |  |  | 2024-11-19 | EJJ/SSB
| 2300-A0-049_R0(CCC MARITIME-II Passage plan from ANCHORAGE to ZULF 1230-1239) | 2300-A0-049 | 0 |  |  | 2024-11-19 | EJJ/SSB
| 2300-DP-0056-1 & 2_Rev-A (CCC MARITIME-II SET-UP AT ZULF 1230-1239 ROV & DIVE SEABED SURVEY) | 2300-DP-0056 | A |  |  | 2024-11-19 | EJJ/SSB
| 2300-DP-0057-1 & 2_Rev-A (CCC MARITIME-II SET-UP AT ZULF 1230-1239 DURING DEBRIS REMOVAL) | 2300-DP-0057 | A |  |  | 2024-11-19 | EJJ/SSB
| 2300-A0-048_R0(CCC MARITIME-II Passage plan from ANCHORAGE to ZULF 1400-1409) | 2300-A0-048 | 0 |  |  | 2024-11-19 | EJJ/SSB
| 2300-DP-0054-1 & 2_Rev-A (CCC MARITIME-II SET-UP AT ZULF 1400-1409 ROV & DIVE SEABED SURVEY) | 2300-DP-0054 | A |  |  | 2024-11-19 | EJJ/SSB
| 2300-DP-0055-1 & 2_Rev-A (CCC MARITIME-II SET-UP AT ZULF 1400-1409 DURING DEBRIS REMOVAL) | 2300-DP-0055 | A |  |  | 2024-11-19 | EJJ/SSB
| (OML INTERVENTION-II PASSAGE PLAN FROM ANCHORAGE TO ZULF EDP-1) | 2300-A0-025 | 4 |  |  | 2024-11-25 | EJJ/SSB
| (OML JACOB INTERVENSION-II SET-UP AT ZULF EDP-1) | 2300-DP-0027 | F |  |  | 2024-11-25 | EJJ/SSB
| ( DELMA -2000 set-up during 30 inch Tie-Line from ZULF TPS-4 TO ZULF TPS-2_Start-up & Lay-down)-DLS-4200 & SUJAAH_option-1 | 2302-A1-007 | 5 |  |  | 2024-11-25 | VKS/RAH
| (DELMA-2000 SET-UP during sleeper installation) | 2300-DP-0060 | A |  |  | 2024-11-26 | EJJ/RAH
| (OML INTERVENTION-II Setup plan during preparatory works @ ZTPS-4) | 2302-DP-0026 | A |  |  | 2024-11-27 | EJJ/SSB
| 2300-A0-036_R1(DLS-4200 Passage plan from ANCHORAGE to ZULF 1220-1229) | 2300-A0-036 | 1 |  |  | 2024-11-27 | EJJ/SSB
| 2300-A0-037_R1(DLS-4200 Passage plan from ANCHORAGE to ZULF 1250-1259) | 2300-A0-037 | 1 |  |  | 2024-11-27 | EJJ/SSB
| 2300-DP-0043_Rev-A(DLS-4200 set-up plan during ZULF 1220-1229 PDM Installation) | 2300-DP-0043 | A |  |  | 2024-11-27 | EJJ/SSB
| 2300-DP-0044_Rev-A(DLS-4200 set-up plan during ZULF 1250-1259 PDM Installation) | 2300-DP-0044 | A |  |  | 2024-11-27 | EJJ/SSB
| 2300-DP-0059-1 & 2_Rev-A (OML INTERVENTION-II Setup plan during preparatory works @ ZTPS-3) | 2300-DP-0059 | A |  |  | 2024-11-28 | EJJ/SSB
| (DELMA-2000 Passage plan from ANCHORAGE to Crossing Location(P14-CR-12) | 2300-A0-050 | 0 |  |  | 2024-12-09 | VKS/RAH
| (DELMA-2000 Setup during 30Inch Tie-Line Laying from ZULF TPS-1 to ZULF TPS-3) | 2300-DP-0047 | B |  |  | 2024-12-09 | VKS/RAH
| 2300-DP-0062-1 & 2_Rev-A(DLS-4200 set-up plan during ZULF 1230-1239 PDM Installation) | 2300-DP-0062 | A |  |  | 2024-12-12 | EJJ/SSB
| 2300-DP-0063-1 & 2_Rev-A(DLS-4200 set-up plan during ZULF 1400-1409 PDM Installation) | 2300-DP-0063 | A |  |  | 2024-12-12 | EJJ/SSB
| (DELMA- 2000 SET-UP PLAN FOR POST PILING, BOAT LANDING & BALANCE WORK AT ZTPS-3) | 2300-DP-0064 | B |  |  | 2024-12-17 | EJJ/SJD
| (OML INTERVENTION-II Setup plan during preparatory works @ ZTPS-2) | 2302-DP-0025 | A |  |  | 2024-12-18 | EJJ/SSB
| LB-II SETUP PLAN DURING ZULF TPS-4 TOPSIDE (FLOAT-OVER) INSTALLATION | 2302-DP-0027 | A |  |  | 2024-12-30 | VKS/SKJ
| Passage plan from ANCHORAGE to ZULF 1230-1239) | 2300-A0-053 | 0 |  |  | 2024-12-31 | EJJ/SSB
| Passage plan from ANCHORAGE to ZULF 1400-1409) | 2300-A0-054 | 0 |  |  | 2024-12-31 | EJJ/SSB
| DELMA 2000 set-up plan during ZULF 1230-1239 PDM Installation) | 2300-DP-0066 | A |  |  | 2025-01-02 | EJJ/SSB
| DELMA-2000 set-up plan during ZULF 1400-1409 PDM Installation) | 2300-DP-0067 | 1 |  |  | 2025-01-02 | EJJ/SSB
| 2300-A0-059_R0(DLS-4200 Passage plan from ANCHORAGE to ZULF GOSP-2 GGP) | 2300-A0-059 | 0 |  |  | 2025-01-04 | VKS/SSB
| 2300-A0-060_R0(DLS-4200 Passage plan from ANCHORAGE to ZULF GOSP-1 PP) | 2300-A0-060 | 0 |  |  | 2025-01-04 | VKS/SSB
| 2300-A0-061_R0(DLS-4200 Passage plan from ANCHORAGE to ARBI TP-01 FLARE) | 2300-A0-061 | 0 |  |  | 2025-01-04 | VKS/SSB
| DLS-4200 SETUP PLAN AT ZULF GOSP-2 GGP | 2300-DP-0068 | 0 |  |  | 2025-01-04 | VKS/SSB
| DLS-4200 SETUP PLAN AT ZULF GOSP-2 AP | 2300-DP-0069 | 0 |  |  | 2025-01-04 | VKS/SSB
| DLS-4200 SETUP PLAN AT ZULF GOSP-2 ACP | 2300-DP-0070 | 0 |  |  | 2025-01-04 | VKS/SSB
| DLS-4200 SETUP PLAN AT ZULF GOSP-1 PP | 2300-DP-0071 | 0 |  |  | 2025-01-04 | VKS/SSB
| DLS-4200 SETUP PLAN AT ZULF GOSP-1 AP | 2300-DP-0072 | 0 |  |  | 2025-01-04 | VKS/SSB
| DLS-4200 SETUP PLAN AT ZULF ARBI TP-01 FLARE | 2300-DP-0073 | 0 |  |  | 2025-01-04 | VKS/SSB
| SEP-450 SET-UP AT ZULF 1250-1259 DURING HOOK-UP WORKS | 2300-DP-0029 | A |  |  | 2025-01-09 | EJJ/SSB
| OML INTERVENTION-II SET-UP AT ZULF 1220-1229 DURING HOOK-UP WORKS | 2300-DP-0074 | A |  |  | 2025-01-09 | EJJ/SSB
| OML INTERVENTION-II Passage plan from ANCHORAGE to ZULF 1220-1229 | 2300-A0-062 | A |  |  | 2025-01-09 | EJJ/SSB
| Passage plan from ANCHORAGE to ZULF 1250-1259 | 2300-A0-063 | A |  |  | 2025-01-09 | EJJ/SSB
| (LB-II Setup plan during ZULF TPS-4 TOPSIDE Installation (FLOATOVER ) | 2302-DP-0027 | B |  |  | 2025-01-17 | VKS/SJD
| (LB-II Setup plan during ZULF TPS-4 TOPSIDE Installation (FLOATOVER ) | 2302-DP-0027 | B |  |  | 2025-01-20 | VKS/SJD
| (DELMA-2000 Setup during 30Inch Tie-Line Laying from ZULF TPS-2 to ZULF TPS-4) | 2302-DP-0023 | B |  |  | 2025-01-21 | VKS/RAH
| (DELMA-2000 Passage plan from ANCHORAGE to ZULF TPS-1) | 2300-A0-042 | 2 |  |  | 2025-01-27 | VKS/RAH
| (DELMA-2000 Passage plan from ANCHORAGE to ZTPS-2) | 2302-A0-028 | 2 |  |  | 2025-01-27 | VKS/RAH
| (VESSEL Passage plan to Tanajib port) | 2300-A0-064 | 0 |  |  | 2025-01-28 | VKS/SSB
| (Unrecovered Debris details at ZULF 1230-1239 | 2300-A3-081 | 0 |  |  | 2025-01-29 | VKS/SSB
| (VESSEL Passage plan to Tanajib port) | 2300-A0-064 | 1 |  |  | 2025-02-04 | VKS/SSB
| (230kV Cable Protection at 30 Inch PL Start-up location)_Option-1 | 2302-A3-019 | 1 |  |  | 2025-02-08 | VKS/SSB
| (230kV Cable Protection at 30 Inch PL Laydown location)_Option-1 | 2302-A3-020 | 1 |  |  | 2025-02-08 | VKS/SSB
| (VESSEL Passage plan to Tanajib port) | 2300-A0-064 | 2 |  |  | 2025-02-10 | VKS/SSB
| (VESSEL Passage plan from ANCHORAGE to ZULF 1280-1289) | 2300-A0-065 | 0 |  |  | 2025-02-12 | VKS/RB
| (SWORDFISH SETUP PLAN DURING PREPARATORY WORKS AT ZULF PLATFORMS) | 2300-DP-0076 | A |  |  | 2025-02-12 | VKS/RB
| (DELMA-2000 Passage plan from ANCHORAGE to ZTPS-4) | 2302-A0-027 | 3 |  |  | 2025-02-14 | EJJ/SJD
| (DELMA-2000 SETUP PLAN DURING ZULF 1360-1369 PDM INSTALLATION) | 2302-DP-0029 | A |  |  | 2025-02-15 | VKS/SSB
| (DELMA-2000 SETUP PLAN DURING ZULF 1370-1379 PDM INSTALLATION) | 2302-DP-0030 | A |  |  | 2025-02-15 | VKS/SSB
| (VESSEL Passage plan from ANCHORAGE to ZULF 1360-1369) | 2302-A0-032 | 0 |  |  | 2025-02-15 | VKS/SSB
| (VESSEL Passage plan from ANCHORAGE to ZULF 1370-1379) | 2302-A0-033 | 0 |  |  | 2025-02-15 | VKS/SSB
| (DELMA-2000 Passage plan from ANCHORAGE to ZTPS-4) | 2302-A0-027 | 3 |  |  | 2025-02-15 | EJJ/SSB
| (DELMA-2000 Setup plan during ZTPS-4 Boat Landing installation and jacket balance work) | 2302-DP-0022 | C |  |  | 2025-02-15 | EJJ/SSB
| (VESSEL Passage plan from ANCHORAGE to ZULF PLATFORMS) | 2300-A0-065 | 1 |  |  | 2025-02-17 | SKV
| (SWORDFISH SETUP PLAN DURING PREPARATORY WORKS AT ZULF PLATFORMS) | 2300-DP-0076 | B |  |  | 2025-02-17 | SKV
| (LB-II Setup plan during ZULF TPS-4 TOPSIDE Installation (FLOATOVER )-OPTION-2 | 2302-DP-0028 | A |  |  | 2025-02-18 | SKV
| (cable laydown at platform) | 2300-A4-003 | 0 |  |  | 2025-02-19 | SKV
| 2300-A0-067_R0(UMM SHAIF BERTH PLAN)-OPTION-1 | 2300-A0-067 | 0 |  |  | 2025-02-24 | SKV
| 2300-A0-068_R0(UMM SHAIF BERTH PLAN)-OPTION-2 | 2300-A0-068 | 0 |  |  | 2025-02-24 | SKV
| (Ras Tanura to Tanajib J Power Location) | 2300-A0-069 | 0 |  |  | 2025-02-24 | SKV
| (LB-II Passage plan from ANCHORAGE to ZTPS-4) | 2302-A0-031 | 2 |  |  | 2025-02-25 | SKV
| (LB-II Setup plan during ZULF TPS-4 TOPSIDE Installation (FLOATOVER )-OPTION-2 | 2302-DP-0028 | A |  |  | 2025-02-25 | SKV
| (OML INTERVENTION-II Setup plan during Hook-up works @ ZTPS-4) | 2302-DP-0026 | B |  |  | 2025-02-27 | EJJ
| (VESSEL Passage plan from ANCHORAGE to ZULF Platform Locations) | 2300-A0-070 | 0 |  |  | 2025-03-03 | SKV
| (SWORDFISH SETUP PLAN DURING PREPARATORY WORKS AT ZULF PLATFORMS) | 2300-DP-0078 | A |  |  | 2025-03-03 | SKV
| (OML INTERVENTION-II Passage plan from ANCHORAGE to ZULF 1400-1409) | 2300-A0-071 | 0 |  |  | 2025-03-04 | EJJ
| (OML INTERVENTION-II SET-UP AT ZULF 1400-1409 DURING PREPARATORY WORKS) | 2300-DP-0079 | A |  |  | 2025-03-04 | EJJ
| (SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1360-1369) | 2302-A0-034 | 0 |  |  | 2025-03-04 | EJJ
| (SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1370-1379) | 2302-A0-035 | 0 |  |  | 2025-03-04 | EJJ
| (SHUJAA-2000 SETUP PLAN DURING ZULF 1360-1369 PDM INSTALLATION) | 2302-DP-0035 | A |  |  | 2025-03-04 | EJJ
| (SHUJAA-2000 SETUP PLAN DURING ZULF 1370-1379 PDM INSTALLATION) | 2302-DP-0036 | A |  |  | 2025-03-04 | EJJ
| (Recovered Debris details at ZULF 1400-1409) | 2300-A3-090 | 0 |  |  | 2025-03-06 | EJJ
| (SEP-450 SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1360-1369) | 2302-DP-0037 | A |  |  | 2025-03-07 | EJJ
| (SEP-450 SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1360-1369) | 2302-DP-0037 | A |  |  | 2025-03-11 | EJJ
| (SEP-450 Passage plan from ANCHORAGE to ZULF 1360-1369) | 2302-A0-037 | 0 |  |  | 2025-03-08 | EJJ
| (SWORDFISH VESSEL SET-UP PLAN DURING FOR C29-230 KV PC @ ZTPS-4) | 2302-DP-0038 | A |  |  | 2025-03-16 | EJJ
| (SWORDFISH VESSEL SET-UP PLAN DURING FOR C33-230 KV PC @ ZTPS-4) | 2302-DP-0039 | A |  |  | 2025-03-16 | EJJ
| (UMM SHAIF SET-UP DURING CABLE LAYING FROM ZULF TPS-4 TO 1330-1339) | 2302-DP-0031 | B |  |  | 2025-03-18 | EJJ
| (UMM SHAIF SET-UP DURING CABLE LAYING FROM ZULF TPS-4 TO 1530-1539) | 2302-DP-0032 | B |  |  | 2025-03-18 | EJJ
| (SWORDFISH Passage plan from ANCHORAGE to ZULF Platform Locations) | 2300-A0-070 | 1 |  |  | 2025-03-18 | EJJ
| (VESSEL Passage plan from ANCHORAGE to ZULF Platform Locations for INITIAL FLOODING) | 2300-A0-073 | 0 |  |  | 2025-03-19 | SKV
| (SWORDFISH SET-UP during Additional Mattress installation) | 2300-DP-0080 | A |  |  | 2025-03-19 | SKV
| (SWORDFISH SET-UP during Freespan Correction & Crossing Supports Installation & Initial Flooding) | 2300-DP-0081 | A |  |  | 2025-03-19 | SKV
| (SWORDFISH Passage plan from ANCHORAGE to ZULF TPS-4) | 2302-A0-038 | 0 |  |  | 2025-03-19 | EJJ
| (SHUJAA-2000 Passage plan from ANCHORAGE to ZTPS-4) | 2302-A0-025 | 1 |  |  | 2025-03-24 | EJJ
| (SHUJAA-2000 Setup plan during ZTPS-4 Boat Landing installation and jacket balance wok) | 2302-DP-0018 | B |  |  | 2025-03-24 | EJJ
| (SWORDFISH Passage plan from ANCHORAGE to ZULF TPS-4) | 2302-A0-038 | 1 |  |  | 2025-03-25 | EJJ
| (SWORDFISH VESSEL SET-UP PLAN DURING CABLE SHIFTING OF C29-230 KV PC @ ZTPS-4) | 2302-DP-0038 | B |  |  | 2025-03-25 | EJJ
| (SWORDFISH VESSEL SET-UP PLAN DURING CABLE SHIFTING OF C33-230 KV PC @ ZTPS-4) | 2302-DP-0039 | B |  |  | 2025-03-25 | EJJ
| (SHUJAA-2000 Setup plan during ZTPS-4 Boat Landing installation and jacket balance wok) | 2302-DP-0018 | C |  |  | 2025-03-29 | SKV
| (VESSEL Passage plan from ANCHORAGE to ZULF Platform Locations for INITIAL FLOODING) | 2300-A0-073 | 1 |  |  | 2025-03-29 | SKV
| (SWORDFISH SET-UP during Freespan Correction & Crossing Supports Installation & Initial Flooding) | 2300-DP-0081 | B |  |  | 2025-03-29 | SKV
| (SHUJAA-2000 Passage plan from ANCHORAGE to ZTPS-2)-SUR 1819 | 2302-A0-039 | 0 |  |  | 2025-04-02 | EJJ
| (SHUJAA-2000 Setup plan during ZTPS-2 Boat Landing installation and jacket balance work) | 2302-DP-0040 | A |  |  | 2025-04-02 | EJJ
| (OML INTERVENTION-II Passage plan from ANCHORAGE to ZTPS-4)-SUR 9192 | 2302-A0-030 | 1 |  |  | 2025-04-03 | EJJ
| (SHUJAA-2000 Passage plan from ANCHORAGE to ZTPS-2)-SUR 1819 | 2302-A0-039 | 0 |  |  | 2025-04-03 | EJJ
| (SHUJAA-2000 Setup plan during ZTPS-2 Boat Landing installation and jacket balance work) | 2302-DP-0040 | B |  |  | 2025-04-03 | EJJ
| (SEP-450 SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1370-1379) | 2302-DP-0043 | A |  |  | 2025-04-07 | EJJ
| Rev-B(SHUJAA-2000 Setup plan during ZTPS-2 Boat Landing installation and jacket balance work) | 2302-DP-0040 | B |  |  | 2025-04-07 | EJJ
| 2300-A0-075_R0 (VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF PLATFORMS) | 2300-A0-075 | 0 |  |  | 2025-04-10 | SKV
| 2300-DP-0084-1 TO 5_Rev-A(CCC-MARITIME-2 SET-UP during RISER CLAMP Installation at ZULF PLATFORMS) | 2300-DP-0084 | A |  |  | 2025-04-10 | SKV
| 2302-A0-040_R0(ORIENTAL DRAGON Passage plan from ANCHORAGE to ZULF TPS-4) | 2302-A0-040 | 0 |  |  | 2025-04-10 | SKV
| 2302-DP-0044-1 TO 2_Rev-A(ORIENTAL DRAGON SET-UP PLAN DURING CABLE SHIFTING OF C33-230 KV PC @ ZTPS-4) | 2302-DP-0044 | A |  |  | 2025-04-10 | SKV
| 2302-DP-0045-1 TO 2_Rev-A(ORIENTAL DRAGON SET-UP PLAN DURING CABLE SHIFTING OF C29-230 KV PC @ ZTPS-4) | 2302-DP-0045 | A |  |  | 2025-04-10 | SKV
| (OML INTERVENTION-II Passage plan from ANCHORAGE to ZULF 1250-1259) | 2300-A0-035 | 3 |  |  | 2025-04-12 | EJJ
| (VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF PLATFORMS) | 2300-A0-075 | 0 |  |  | 2025-04-14 | EJJ
| (CCC MARITIME-II Passage plan from ANCHORAGE to ZULF 1250-1259) | 2300-A0-076 | 0 |  |  | 2025-04-14 | EJJ
| (ORIENTAL DRAGON Passage plan from ANCHORAGE to ZULF TPS-4) | 2302-A0-040 | 1 |  |  | 2025-04-14 | EJJ
| (ORIENTAL DRAGON SET-UP PLAN DURING CABLE SHIFTING OF C33-230 KV PC @ ZTPS-4) | 2302-DP-0044 | A |  |  | 2025-04-22 | SKV
| (ORIENTAL DRAGON SET-UP PLAN DURING CABLE SHIFTING OF C29-230 KV PC @ ZTPS-4) | 2302-DP-0045 | A |  |  | 2025-04-22 | SKV
| (SHUJAA-2000 PASSAGE PLAN FROM ANCHORAGE TO ZULF 1210-1219 )-SUR-1819 | 2300-A0-079 | 0 |  |  | 2025-04-23 | EJJ
| (SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1330-1339)-SUR-9192 | 2302-A0-041 | 0 |  |  | 2025-04-23 | EJJ
| (SHUJAA-2000 SETUP PLAN DURING ZULF 1210-1219 PDM INSTALLATION) | 2300-DP-0086 | A |  |  | 2025-04-24 | EJJ
| (SHUJAA-2000 SETUP PLAN DURING ZULF 1330-1339 PDM INSTALLATION) | 2302-DP-0041 | A |  |  | 2025-04-24 | EJJ
| (OML INTERVENTION-II SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1360-1369) | 2302-DP-0042 | A |  |  | 2025-04-25 | EJJ
| (OML INTERVENTION-II Passage plan from ANCHORAGE to ZULF 1360-1369) | 2302-A0-037 | 0 |  |  | 2025-04-28 | EJJ
| (SEP-450 Passage plan from ANCHORAGE to ZULF 1370-1379) | 2302-A0-042 | 0 |  |  | 2025-04-28 | EJJ
| 2300-A0-043_R3(DELMA-2000 Passage plan from ANCHORAGE to ZULF TPS-3) | 2300-A0-043 | 3 |  |  | 2025-04-29 | SKV
| 2302-A0-030_R2(OML INTERVENTION-II Passage plan from ANCHORAGE to ZTPS-4) | 2302-A0-030 | 3 |  |  | 2025-04-29 | SKV
| (LB-II Passage plan from ANCHORAGE to ZTPS-4) | 2302-A0-031 | 3 |  |  | 2025-05-27 | EJJ
| (SHUJAA-2000 Passage plan from ANCHORAGE to ZTPS-3) | 2300-A0-028 | 2 |  |  | 2025-05-28 | EJJ
| (SHUJAA-2000 Setup plan during ZTPS-3 Boat Landing installation and jacket balance wok) | 2300-DP-0036 | C |  |  | 2025-05-28 | EJJ
| 2302-A0-030_R3(OML INTERVENTION-II Passage plan from ANCHORAGE to ZTPS-4) | 2302-A0-030 | 3 |  |  | 2025-05-29 | EJJ
| 2302-DP-0026-1 to 2_Rev-C(OML INTERVENTION-II Setup plan during Hook-up works @ ZTPS-4) | 2302-DP-0026 | C |  |  | 2025-05-29 | EJJ
| (SHUJAA-2000 Setup plan during ZTPS-3 Boat Landing installation and jacket balance wok) | 2300-DP-0036 | D |  |  | 2025-06-02 | EJJ
| (OML INTERVENTION-II SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1370-1379) | 2302-DP-0052 | A |  |  | 2025-06-05 | EJJ
| 2300-A0-025_R5(OML INTERVENTION-II PASSAGE PLAN FROM ANCHORAGE TO ZULF EDP-1) | 2300-A0-025 | 5 |  |  | 2025-06-11 | EJJ
| 2300-A0-034_R1(SHUJAA-2000 Passage plan from ANCHORAGE to ZEDP-2) | 2300-A0-034 | 1 |  |  | 2025-06-11 | EJJ
| 2300-A0-082_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1260-1269) | 2300-A0-082 | 0 |  |  | 2025-06-11 | EJJ
| 2302-A0-045_R0(OML INTERVENTION-II Passage plan from ANCHORAGE to ZULF 1370-1379) | 2302-A0-045 | 0 |  |  | 2025-06-11 | EJJ
| 2302-A0-046_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1290-1299) | 2302-A0-046 | 0 |  |  | 2025-06-11 | EJJ
| 2300-DP-0089-1 & 2_Rev-A(SHUJAA-2000 SETUP PLAN DURING ZULF 1260-1269 PDM INSTALLATION) | 2300-DP-0089 | A |  |  | 2025-06-11 | EJJ
| 2302-DP-0052-1 & 2_Rev-A(OML INTERVENTION-II SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1370-1379) | 2302-DP-0052 | A |  |  | 2025-06-11 | EJJ
| 2302-DP-0053-1 & 2_Rev-A(SHUJAA-2000 SETUP PLAN DURING ZULF 1290-1299 PDM INSTALLATION) | 2302-DP-0053 | A |  |  | 2025-06-11 | EJJ
| 2300-DP-0040_Rev-C(SHUJAA-2000 Setup plan during EDP-2 Boat Landing installation and jacket balance wok) | 2300-DP-0040 | C |  |  | 2025-06-12 | EJJ
| 2300-DP-0089-1 & 2_Rev-A(SHUJAA-2000 SETUP PLAN DURING ZULF 1260-1269 PDM INSTALLATION) | 2300-DP-0089 | A |  |  | 2025-06-12 | EJJ
| 2300-DP-0090-1 & 2_Rev-A(OML INTERVENSION-II SET-UP AT ZULF EDP-1 DURING HOOK-UP WORKS) | 2300-DP-0090 | A |  |  | 2025-06-12 | EJJ
| 2300-A0-082_R1(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1260-1269) | 2300-A0-082 | 1 |  |  | 2025-06-14 | EJJ
| 2300-DP-0040_Rev-D(SHUJAA-2000 Setup plan during EDP-2 Boat Landing installation and jacket balance wok) | 2300-DP-0040 | D |  |  | 2025-06-14 | EJJ
| 2300-DP-0089-1 & 2_Rev-B(SHUJAA-2000 SETUP PLAN DURING ZULF 1260-1269 PDM INSTALLATION) | 2300-DP-0089 | B |  |  | 2025-06-14 | EJJ
| 2302-DP-0053-1 & 2_Rev-B(SHUJAA-2000 SETUP PLAN DURING ZULF 1290-1299 PDM INSTALLATION) | 2302-DP-0053 | B |  |  | 2025-06-14 | EJJ
| (SHUJAA-2000 Setup plan during EDP-2 Boat Landing installation and jacket balance wok) Model | 2300-DP-0040 | E |  |  | 2025-06-18 | EJJ
| (OML INTERVENSION-II SET-UP AT ZULF EDP-1 DURING HOOK-UP WORKS) | 2300-DP-0090 | B |  |  | 2025-06-18 | EJJ
| (SHUJAA-2000 SETUP PLAN DURING ZULF 1290-1299 PDM INSTALLATION) | 2302-DP-0053 | C |  |  | 2025-06-19 | EJJ
| (SEP-550 SET-UP AT ZULF 1220-1229) | 2300-A3-091 | 0 |  |  | 2025-06-24 | EJJ
| (SEP-550 SET-UP AT ZULF 1220-1229) | 2300-A3-091 | 1 |  |  | 2025-06-25 | EJJ
| 2302-A0-038_R2(SWORDFISH Passage plan from ANCHORAGE to ZULF TPS-4) | 2302-A0-038 | 2 |  |  | 2025-07-01 | VSK
| (OML INTERVENTION-II PASSAGE PLAN FROM ANCHORAGE to ZULF EDP-1) | 2300-A0-025 | 6 |  |  | 2025-07-01 | EJJ
| 3(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF EDP-2) | 2300-A0-034 | 2 |  |  | 2025-07-01 | EJJ
| 2300-A0-025_R6(OML INTERVENTION-II PASSAGE PLAN FROM ANCHORAGE to ZULF EDP-1) | 2300-A0-025 | 6 |  |  | 2025-07-01 | EJJ
| 2300-A0-034_R2(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF EDP-2) | 2300-A0-034 | 2 |  |  | 2025-07-01 | EJJ
| 2300-A0-083_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF GOSP-2 GGP) | 2300-A0-083 | 0 |  |  | 2025-07-01 | EJJ
| 2300-A0-084_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF GOSP-1 PP) | 2300-A0-084 | 0 |  |  | 2025-07-01 | EJJ
| (SHUJAA-2000 plan during Lifting Activities at ZULF GOSP-2 AP) | 2300-DP-0092 | A |  |  | 2025-07-02 | EJJ
| (SHUJAA-2000 SET-UP plan during Lifting Activities at ZULF GOSP-1 AP) | 2300-DP-0093 | A |  |  | 2025-07-02 | EJJ
| (SHUJAA-2000 SET-UP plan during Lifting Activities at ZULF GOSP-2 GGP) | 2300-DP-0091 | A |  |  | 2025-07-02 | EJJ
| (SHUJAA-2000 Setup plan during EDP-2 Boat Landing installation and jacket balance wok) | 2300-DP-0040 | F |  |  | 2025-07-04 | EJJ
| (SEP-550 SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1330-1339) | 2302-DP-0054 | A |  |  | 2025-07-10 | EJJ
| (SHUJAA-2000 SET-UP PLAN DURING ZULF 1530-1539 PDM INSTALLATION) | 2302-DP-0055 | A |  |  | 2025-07-10 | EJJ
| (SEP-550 Passage plan from ANCHORAGE to ZULF 1330-1339) | 2302-A0-047 | 0 |  |  | 2025-07-15 | EJJ
| (SHUJAA-2000 Passage plan from Anchorage to ZULF 1530-1539) | 2302-A0-048 | 0 |  |  | 2025-07-15 | EJJ
| 2300-A0-079_R1(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1210-1219 )_SUR 1819 | 2300-A0-079 | 1 |  |  | 2025-07-15 | EJJ
| 2302-A0-041_R1(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1330-1339)_SUR 9192 | 2302-A0-041 | 1 |  |  | 2025-07-15 | EJJ
| (SHUJAA-2000 SET-UP PLAN DURING ZULF 1530-1539 PDM INSTALLATION) | 2302-DP-0055 | B |  |  | 2025-07-17 | EJJ
| 2302-DP-0038-1 & 2_Rev-C(SWORDFISH VESSEL SET-UP PLAN DURING CABLE SHIFTING OF C29-230 KV PC @ ZTPS-4) | 2302-DP-0038 | C |  |  | 2025-07-23 | EJJ
| 2300-A0-088_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF Platform Locations) | 2300-A0-088 | 0 |  |  | 2025-08-25 | EJJ
| (SWORDFISH SETUP PLAN DURING PREPARATORY WORKS AT TPs and PDMs for Flexible) | 2300-DP-0097 | A |  |  | 2025-08-27 | EJJ
| 2300-A3-092_Rev-A (Pre-Installed soft mooring ropes @ ZTPS-2) | 2300-A3-092 | A |  |  | 2025-08-29 | SKV
| 2300-A0-082_R2(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1260-1269) | 2300-A0-082 | 2 |  |  | 2025-09-10 | EJJ
| 2300-A0-089_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1200-1209) | 2300-A0-089 | 0 |  |  | 2025-09-10 | EJJ
| 2302-A0-046_R1(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1290-1299) | 2302-A0-046 | 1 |  |  | 2025-09-10 | EJJ
| 2302-A0-054_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1340-1349) | 2302-A0-054 | 0 |  |  | 2025-09-10 | EJJ
| 2300-A0-082_R2(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1260-1269) | 2300-A0-082 | 2 |  |  | 2025-09-12 | EJJ
| 2300-A0-086_R2(SHUJAA-2000 Passage plan from ANCHORAGE to RBYN 10-19) | 2300-A0-086 | 2 |  |  | 2025-09-12 | EJJ
| 2300-A0-087_R2(OML INTERVENTION-II Passage plan from ANCHORAGE to ZULF 1210-1219) | 2300-A0-087 | 2 |  |  | 2025-09-12 | EJJ
| 2300-A0-089_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1200-1209) | 2300-A0-089 | 0 |  |  | 2025-09-12 | EJJ
| 2300-DP-0098-1 & 2_Rev-A(SHUJAA-2000 SETUP PLAN DURING ZULF 1200-1209 PDM INSTALLATION) | 2300-DP-0098 | A |  |  | 2025-09-12 | EJJ
| 2302-A0-046_R1(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1290-1299) | 2302-A0-046 | 1 |  |  | 2025-09-12 | EJJ
| 2302-A0-054_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1340-1349) | 2302-A0-054 | 0 |  |  | 2025-09-12 | EJJ
| 2302-DP-0066-1 & 2_Rev-A(SHUJAA-2000 SETUP PLAN DURING ZULF 1340-1349 PDM INSTALLATION) | 2302-DP-0066 | A |  |  | 2025-09-12 | EJJ
| 2302-A0-055_R0(HEA AL SARAB Passage plan from ANCHORAGE to ZULF 1290-1299) | 2302-A0-055 | 0 |  |  | 2025-09-16 | EJJ
| 2302-DP-0067-1 & 2_Rev-A(HEA AL SARAB SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1290-1299) | 2302-DP-0067 | A |  |  | 2025-09-18 | EJJ
| 2302-DP-0068-1 TO 8_Rev-A(LB-II Setup plan during ZULF TPS-2 TOPSIDE Installation (FLOATOVER)) | 2302-DP-0068 | A |  |  | 2025-09-19 | SKV
| 2302-A0-044_R2(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF TPS-4) | 2302-A0-044 | 2 |  |  | 2025-09-22 | SKV
| 2302-DP-0071_Rev-A(SHUJAA-2000 Setup plan during Subsea Spool wet store at ZULF TPS-4) | 2302-DP-0071 | A |  |  | 2025-09-22 | SKV
| 2302-A0-056_R0(LB-II Passage plan from ANCHORAGE to ZULF TPS-2) | 2302-A0-056 | 0 |  |  | 2025-09-22 | SKV
| 2302-DP-0068-1 TO 8_Rev-A(LB-II Setup plan during ZULF TPS-2 TOPSIDE Installation (FLOATOVER)) | 2302-DP-0068 | A |  |  | 2025-09-22 | SKV
| 2302-DP-0025-1 & 2_Rev-B(OML INTERVENTION-II Setup plan during preparatory works @ ZTPS-2) | 2302-DP-0025 | B |  |  | 2025-09-23 | EJJ
| 2302-DP-0069-1 TO 3_REV-B(UMM SHAIF SET-UP DURING CABLE LAYING FROM FROM ZTPS-2 TO ZULF1380-1389) | 2302-DP-0069 | B |  |  | 2025-09-23 | SKV
| 2302-A0-055_R1(HEA AL SARAB Passage plan from ANCHORAGE to ZULF 1290-1299) | 2302-A0-055 | 1 |  |  | 2025-09-25 | EJJ
| 2302-DP-0067-1 & 2_Rev-B(HEA AL SARAB SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1290-1299) | 2302-DP-0067 | B |  |  | 2025-09-25 | EJJ
| 2302-DP-0071_Rev-B(SHUJAA-2000 Setup plan during subsea spool wet store at ZULF TPS-4) | 2302-DP-0071 | B |  |  | 2025-09-25 | EJJ
| 2302-A0-057_R0(SWORDFISH Passage plan from ANCHORAGE to ZTPS-2)-SUR 1819 | 2302-A0-057 | 0 |  |  | 2025-09-26 | EJJ
| 2302-DP-0072-1 & 2_Rev-A(SWORDFISH VESSEL SET-UP PLAN DURING CABLE SHIFTING OF C30-230 KV PC @ ZTPS-2) | 2302-DP-0072 | A |  |  | 2025-09-26 | EJJ
| 2302-DP-0073-1 & 2_Rev-A(SWORDFISH VESSEL SET-UP PLAN DURING CABLE SHIFTING OF C33-230 KV PC @ ZTPS-2) | 2302-DP-0073 | A |  |  | 2025-09-26 | EJJ
| 2302-A0-039_R1(SHUJAA-2000 Passage plan from ANCHORAGE to ZTPS-2) | 2302-A0-039 | 1 |  |  | 2025-09-26 | SKV
| 2302-A0-040_R3(ORIENTAL DRAGON Passage plan from ANCHORAGE to ZULF TPS-4) | 2302-A0-040 | 3 |  |  | 2025-09-26 | SKV
| 2302-DP-0074_Rev-A(ORIENTAL DRAGON Setup plan during subsea spool wet store at ZULF TPS-4) | 2302-DP-0074 | A |  |  | 2025-09-26 | SKV
| 2302-DP-0075_Rev-A(SHUJAA-2000 Setup plan during subsea spool wet store at ZULF TPS-2) | 2302-DP-0075 | A |  |  | 2025-09-26 | SKV
| 2300-A0-028_R3(SHUJAA-2000 Passage plan from ANCHORAGE to ZTPS-3)_SUR 1819 | 2300-A0-028 | 3 |  |  | 2025-09-30 | EJJ
| 2300-A0-087_R3(OML INTERVENTION-II Passage plan from ANCHORAGE to ZULF 1210-1219)_SUR 1819 | 2300-A0-087 | 3 |  |  | 2025-09-30 | EJJ
| 2302-A0-058_R0(QMS AL SHAHAMA-II Passage plan from ANCHORAGE to ZULF 1330-1339) | 2302-A0-058 | 0 |  |  | 2025-10-01 | EJJ
| 2302-DP-0076-1 & 2_Rev-A(QMS AL SHAHAMA II DP SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1330-1339) | 2302-DP-0076 | A |  |  | 2025-10-01 | EJJ
| 2302-A0-059_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1380-1389) | 2302-A0-059 | 0 |  |  | 2025-10-02 | EJJ
| 2302-DP-0077-1 & 2_Rev-A(SHUJAA-2000 SETUP PLAN DURING ZULF 1380-1389 PDM INSTALLATION) | 2302-DP-0077 | A |  |  | 2025-10-02 | EJJ
| 2302-DP-0072-1 & 2_Rev-B(SWORDFISH VESSEL SET-UP PLAN DURING CABLE SHIFTING OF C30-230 KV PC @ ZTPS-2) | 2302-DP-0072 | B |  |  | 2025-10-02 | EJJ
| 2302-DP-0073-1 & 2_Rev-B(SWORDFISH VESSEL SET-UP PLAN DURING CABLE SHIFTING OF C33-230 KV PC @ ZTPS-2) | 2302-DP-0073 | B |  |  | 2025-10-02 | EJJ
| 2302-A0-060_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1410-1419) | 2302-A0-060 | 0 |  |  | 2025-10-03 | EJJ
| 2302-DP-0078-1 & 2_Rev-A(SHUJAA-2000 SET-UP PLAN DURING ZULF 1410-1419 PDM INSTALLATION) | 2302-DP-0078 | A |  |  | 2025-10-03 | EJJ
| 2302-DP-0074_Rev-B(ORIENTAL DRAGON Setup plan during subsea spool wet store at ZULF TPS-4) | 2302-DP-0074 | B |  |  | 2025-10-07 | EJJ
| 2302-DP-0075_Rev-B(SHUJAA-2000 Setup plan during subsea spool wet store at ZULF TPS-2) | 2302-DP-0075 | B |  |  | 2025-10-07 | EJJ
| 2302-DP-0076-1 OF 2_Rev-B(QMS AL SHAHAMA II DP SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1330-1339) | 2302-DP-0076 | B |  |  | 2025-10-07 | EJJ
| 2302-A0-062_R0(QMS AL SHAHAMA-II Passage plan from ANCHORAGE to ZULF 1290-1299) | 2302-A0-062 | 0 |  |  | 2025-10-14 | EJJ
| 2302-DP-0081-1 & 2_Rev-A(QMS AL SHAHAMA II SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1290-1299) | 2302-DP-0084 | A |  |  | 2025-10-14 | EJJ
| 2302-A0-063_R0(HEA AL SARAB Passage plan from Anchorage to ZULF 1530-1539) | 2302-A0-063 | 0 |  |  | 2025-10-16 | EJJ
| 2302-A0-064_R0(OML INTERVENTION-II Passage plan from ANCHORAGE to ZULF 1330-1339) | 2302-A0-064 | 0 |  |  | 2025-10-16 | EJJ
| 2302-DP-0082-1 & 2_Rev-A(HEA AL SARAB SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1530-1539) | 2302-DP-0082 | A |  |  | 2025-10-16 | EJJ
| 2302-DP-0083-1 & 2_Rev-A(OML INTERVENTION-II DP SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1330-1339) | 2302-DP-0083 | A |  |  | 2025-10-16 | EJJ
| 2302-A0-064_R0(QMS AL SHAHAMA-II Passage plan from ANCHORAGE to ZULF 1290-1299) | 2302-A0-064 | 0 |  |  | 2025-10-16 | EJJ
| 2302-A0-065_R0(HEA AL SARAB Passage plan from Anchorage to ZULF 1530-1539) | 2302-A0-065 | 0 |  |  | 2025-10-16 | EJJ
| (OML INTERVENTION-II Passage plan from ANCHORAGE to ZULF 1330-1339) | 2302-A0-066 | 0 |  |  | 2025-10-16 | EJJ
| (CCC WADAD ALETHIEA DP SET-UP PLAN DURING SUBSEA SPOOLS INSTALLATION AT ZTPS-4) | 2302-DP-0079 | B |  |  | 2025-10-20 | SKV
| (SHUJAA-2000 Passage plan from Anchorage to ZULF 1530-1539) | 2302-A0-048 | 1 |  |  | 2025-10-20 | SKV
| ORIENTAL DRAGON SET-UP PLAN DURING CABLE SHIFTING OF C30-230 KV PC @ ZTPS-2) | 2302-DP-0086 | A |  |  | 2025-10-21 | SKV
| ORIENTAL DRAGON SET-UP PLAN DURING CABLE SHIFTING OF C33-230 KV PC @ ZTPS-2) | 2302-DP-0087 | A |  |  | 2025-10-21 | SKV
| (ORIENTAL DRAGON Passage plan from ANCHORAGE to ZULF TPS-2) | 2302-A0-061 | 1 |  |  | 2025-10-22 | SKV
| (ORIENTAL DRAGON SET-UP PLAN DURING CABLE SHIFTING OF C30-230 KV PC @ ZTPS-2) | 2302-DP-0086 | A |  |  | 2025-10-22 | SKV
| (ORIENTAL DRAGON SET-UP PLAN DURING CABLE SHIFTING OF C33-230 KV PC @ ZTPS-2) | 2302-DP-0087 | A |  |  | 2025-10-22 | SKV
| (SHUJAA-2000 SET-UP PLAN DURING ZULF 1530-1539 PDM INSTALLATION) | 2302-DP-0055 | B |  |  | 2025-10-22 | SKV
| 2302-A0-028_R1(DELMA-2000 Passage plan from ANCHORAGE to ZTPS-2)-SUR 1819 | 2302-A0-028 | 1 |  |  | 2025-10-22 | SKV
| 2302-DP-0070-1 TO 4_Rev-A(DELMA-2000 SET-UP during 30Inch T.I Laying from ZTPS-2 to ZTPS-4) | 2302-DP-0070 | A |  |  | 2025-10-22 | SKV
| (Ras Tanura to Tanajib J Power Location) | 2302-A0-069 | 0 |  |  | 2025-10-22 | SKV
| (UMM SHAIF BERTH PLAN) | 2302-A0-070 | 0 |  |  | 2025-10-22 | SKV
| (SHUJAA-2000 SETUP PLAN DURING ZULF 1530-1539 PDM INSTALLATION) | 2302-DP-0055 | B |  |  | 2025-10-24 | SKV
| (Ras Tanura to Tanajib J Power Location) | 2302-A0-069 | 0 |  |  | 2025-10-30 | SKV
| (UMM SHAIF BERTH PLAN) | 2302-A0-070 | 0 |  |  | 2025-10-30 | SKV
| (SWORDFISH Passage plan from ANCHORAGE to ZULF 1260-1269) | 2300-A0-095 | 0 |  |  | 2025-11-02 | SKV
| (SWORDFISH SETUP PLAN DURING SEABED SURVEY AND DEBRIS REMOVAL AT ZULF 1290-1299) | 2300-DP-0095 | A |  |  | 2025-11-02 | SKV
| (SWORDFISH SETUP PLAN DURING SEABED SURVEY AND DEBRIS REMOVAL AT ZULF 1260-1269) | 2300-DP-0102 | A |  |  | 2025-11-02 | SKV
| (SWORDFISH Passage plan from ANCHORAGE to ZULF 1290-1299) | 2302-A0-075 | 0 |  |  | 2025-11-02 | SKV
| (CHUANG LI Passage plan from ANCHORAGE to ZULF TPS-3) | 2300-A0-097 | 0 |  |  | 2025-11-03 | EJJ
| (CHUANG LI SET-UP PLAN FOR POST PILING, BOAT LANDING & BALANCE WORK AT ZTPS-3) | 2300-DP-0104 | A |  |  | 2025-11-03 | EJJ
| (SHUJAA-2000 SET-UP PLAN DURING ZULF 1530-1539 PDM INSTALLATION) | 2302-DP-0055 | C |  |  | 2025-11-03 | EJJ
| (SWORDFISH SETUP PLAN DURING SEABED SURVEY AND DEBRIS REMOVAL AT ZULF 1330-1339) | 2300-DP-0098 | A |  |  | 2025-11-04 | DH
| (SWORDFISH Passage plan from ANCHORAGE to ZULF 1330-1339) | 2302-A0-080 | 0 |  |  | 2025-11-04 | DH
| (ORIENTAL DRAGON PASSAGE PLAN FROM ANCHORAGE TO OBD-11(SEA ISLAND 3) | 2300-A0-081 | 1 |  |  | 2025-11-04 | SKV
| (ORIENTAL DRAGON SET-UP PLAN DURING OBD #11 INSTALLATION AT SEA ISLAND 3) | 2300-DP-0105 | A |  |  | 2025-11-04 | SKV
| (HEA AL SARAB SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1290-1299) | 2302-DP-0067 | B |  |  | 2025-11-04 | EJJ
| (SWORDFISH PASSAGE PLAN FROM ANCHORAGE TO CROSSING LOCATION (P15-CR-01 & P14-CR-12)) | 2300-A0-096 | 0 |  |  | 2025-11-04 | DH
| (SWORDFISH Setup during Sleeper installation at Crossing location( P15-CR-01 & P14-CR-12 )) | 2300-DP-0103 | A |  |  | 2025-11-05 | SKV
| (HEA AL SARAB Passage plan from ANCHORAGE to ZULF 1330-1339) | 2302-A0-078 | 0 |  |  | 2025-11-05 | EJJ
| (HEA AL SARAB DP SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1330-1339) | 2302-DP-0096 | A |  |  | 2025-11-05 | EJJ
| (RAWABI-608 Passage plan from Anchorage to ZULF 1530-1539) | 2302-A0-079 | 0 |  |  | 2025-11-06 | EJJ
| (RAWABI-608 SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1530-1539) | 2302-DP-0097 | A |  |  | 2025-11-06 | EJJ
| (ORIENTAL DRAGON SET-UP PLAN DURING OBD #11 INSTALLATION AT SEA ISLAND 3) | 2300-DP-0105 | B |  |  | 2025-11-06 | SKV
| 2300-A0-095_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF 1260-1269) | 2300-A0-095 | 0 |  |  | 2025-11-06 | SKV
| 2300-DP-0095-1 TO 2_Rev-A(SWORDFISH SETUP PLAN DURING SEABED SURVEY AND DEBRIS REMOVAL AT ZULF 1290-1299) | 2300-DP-0095 | A |  |  | 2025-11-06 | SKV
| 2300-DP-0102-1 TO 2_Rev-A(SWORDFISH SETUP PLAN DURING SEABED SURVEY AND DEBRIS REMOVAL AT ZULF 1260-1269) | 2300-DP-0102 | A |  |  | 2025-11-06 | SKV
| 2302-A0-075_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF 1290-1299) | 2302-A0-075 | 0 |  |  | 2025-11-06 | SKV
| 2300-A0-098_R0(SHUJAA-2000 PASSAGE PLAN FROM ANCHORAGE TO ZULF 1240-1249)-SUR 1819 | 2300-A0-098 | 0 |  |  | 2025-11-09 | EJJ
| 2300-A0-099_R0(SHUJAA-2000 PASSAGE PLAN FROM ANCHORAGE TO ZULF ZULF 1270-1279)-SUR-9192 | 2300-A0-099 | 0 |  |  | 2025-11-09 | EJJ
| 2300-DP-0106-1 & 2_Rev-A(SHUJAA-2000 SETUP PLAN DURING ZULF 1240-1249 PDM INSTALLATION) | 2300-DP-0106 | A |  |  | 2025-11-09 | EJJ
| 2300-DP-0107-1 & 2_Rev-A(SHUJAA-2000 SETUP PLAN DURING ZULF 1270-1279 PDM INSTALLATION) | 2300-DP-0107 | A |  |  | 2025-11-09 | EJJ
| 2302-A0-049_R1(CHUANG LI Passage plan from ANCHORAGE to ZTPS-2) | 2302-A0-049 | 1 |  |  | 2025-11-11 | SKV
| 2300-A0-100_R0(SWORDFISH Passage plan from ANCHORAGE to RBYN 10-19) | 2300-A0-100 | 0 |  |  | 2025-11-13 | DH
| 2300-DP-0108-1 TO 2_Rev-A(SWORDFISH SETUP PLAN DURING SEABED SURVEY AND DEBRIS REMOVAL AT RBYN 10-19) | 2300-DP-0108 | A |  |  | 2025-11-13 | DH
| 2302-A0-081_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF 1530-1539) | 2302-A0-081 | 0 |  |  | 2025-11-13 | DH
| 2302-DP-0100-1 TO 2_Rev-A(SWORDFISH SETUP PLAN DURING SEABED SURVEY AND DEBRIS REMOVAL AT ZULF 1530-1539) | 2302-DP-0100 | A |  |  | 2025-11-13 | DH
| 2302-A0-080_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF 1330-1339) | 2302-A0-080 | 0 |  |  | 2025-11-16 | SKV
| 2302-DP-0109-1 TO 2_Rev-A(SWORDFISH SETUP PLAN DURING SUBSEA SPOOL INSTALLATION AT ZULF 1330-1339) | 2302-DP-0109 | A |  |  | 2025-11-16 | SKV
| 2302-DP-0092-1 TO 3_Rev-C(SWORDFISH Setup plan during subsea spool installation at ZULF TPS-4) | 2302-DP-0092 | C |  |  | 2025-11-18 | SKV
| 2302-DP-0110-1 TO 4_Rev-A(SWORDFISH Setup plan during subsea spool installation at ZULF TPS-4) | 2302-DP-0110 | A |  |  | 2025-11-18 | SKV
| 2302-DP-0111-1 TO 3_Rev-A(SWORDFISH Setup plan during subsea spool installation at ZULF TPS-4) | 2302-DP-0111 | A |  |  | 2025-11-18 | SKV
| 2302-DP-0112-1 TO 3_Rev-A(SWORDFISH Setup plan during subsea spool installation at ZULF TPS-4) | 2302-DP-0112 | A |  |  | 2025-11-18 | SKV
| 2302-DP-0113-1 TO 4_Rev-A(SWORDFISH Setup plan during subsea spool installation at ZULF TPS-2) | 2302-DP-0113 | A |  |  | 2025-11-24 | DH
| 2302-DP-0114-1 TO 4_Rev-A(SWORDFISH Setup plan during subsea spool installation at ZULF TPS-2) | 2302-DP-0114 | A |  |  | 2025-11-24 | DH
| 2302-DP-0115-1 TO 3_Rev-A(SWORDFISH Setup plan during subsea spool installation at ZULF TPS-2) | 2302-DP-0115 | A |  |  | 2025-11-24 | DH
| 2302-DP-0116-1 TO 4_Rev-A(SWORDFISH Setup plan during subsea spool installation at ZULF TPS-2) | 2302-DP-0116 | A |  |  | 2025-11-24 | DH
| 2302-A0-083_R0((SWORDFISH Passage plan from ANCHORAGE to ZULF TPS-2) | 2302-A0-083 | 0 |  |  | 2025-11-25 | DH
| 2302-A0-084_R0((SWORDFISH Passage plan from ANCHORAGE to ZULF 1380-1389) | 2302-A0-084 | 0 |  |  | 2025-11-25 | DH
| 2302-DP-0118-1 TO 2_Rev-A(SWORDFISH Setup plan during subsea spool and ssvs installation at ZULF 1380-1389) | 2302-DP-0118 | A |  |  | 2025-11-25 | DH
| 2300-A0-034_R3(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF EDP-2) | 2300-A0-034 | 3 |  |  | 2025-11-28 | EJJ
| 2300-DP-0040_Rev-F(SHUJAA-2000 Setup plan during EDP-2 Boat Landing installation and jacket balance wok) | 2300-DP-0040 | F |  |  | 2025-11-28 | EJJ
| 2302-A0-085_R0(HEA AL SARAB Passage plan from ANCHORAGE to ZULF 1340-1349) | 2302-A0-085 | 0 |  |  | 2025-11-28 | SKV
| 2302-DP-0121-1 TO 2_Rev-A(HEA AL SARAB SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1340-1349) | 2302-DP-0121 | A |  |  | 2025-11-28 | SKV
| 2300-A0-101_R0(SWORDFISH Passage plan from ANCHORAGE to EDP-2) | 2300-A0-101 | 0 |  |  | 2025-12-04 | SKV
| 2300-DP-0109-1 TO 2_Rev-A(SWORDFISH SET-UP PLAN DURING C30-230KV CABLE SHIFTING AT ZULF EDP-2) | 2300-DP-0109 | A |  |  | 2025-12-04 | SKV
| 2300-DP-0110-1 TO 2_Rev-A(SWORDFISH SET-UP PLAN DURING C31-230KV CABLE SHIFTING AT ZULF EDP-2) | 2300-DP-0110 | A |  |  | 2025-12-04 | SKV
| 2300-DP-0111-1 TO 2_Rev-A(SWORDFISH SET-UP PLAN DURING C27-230KV CABLE SHIFTING AT ZULF EDP-2) | 2300-DP-0111 | A |  |  | 2025-12-04 | SKV
| 2302-A0-079_R0(RAWABI-608 Passage plan from Anchorage to ZULF 1530-1539) | 2302-A0-079 | 0 |  |  | 2025-12-04 | EJJ
| 2300-A0-101_R0(SWORDFISH Passage plan from ANCHORAGE to EDP-2) | 2300-A0-101 | 0 |  |  | 2025-12-05 | SKV
| 2300-DP-0109-1 TO 2_Rev-A(SWORDFISH SET-UP PLAN DURING C30-230KV CABLE SHIFTING AT ZULF EDP-2) | 2300-DP-0109 | A |  |  | 2025-12-05 | SKV
| 2300-DP-0110-1 TO 2_Rev-A(SWORDFISH SET-UP PLAN DURING C31-230KV CABLE SHIFTING AT ZULF EDP-2) | 2300-DP-0110 | A |  |  | 2025-12-05 | SKV
| 2300-DP-0111-1 TO 2_Rev-A(SWORDFISH SET-UP PLAN DURING C27-230KV CABLE SHIFTING AT ZULF EDP-2) | 2300-DP-0111 | A |  |  | 2025-12-05 | SKV
| 2300-A0-089_R1(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1200-1209) | 2300-A0-089 | 1 |  |  | 2025-12-08 | SKV
| 2302-A0-054_R1(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1340-1349) | 2302-A0-054 | 1 |  |  | 2025-12-08 | SKV
| 2300-A0-102_R0(VESSEL Passage plan from ANCHORAGE to ZULF 1280-1289) | 2300-A0-102 | 0 |  |  | 2025-12-09 | EJJ
| 2300-DP-0112-1 & 2_Rev-A(SHUJAA-2000 SETUP PLAN DURING ZULF 1280-1289 PDM INSTALLATION) | 2300-DP-011 | A |  |  | 2025-12-09 | EJJ
| 2300-A0-103_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1490-1499) | 2300-A0-103 | 0 |  |  | 2025-12-09 | EJJ
| 2300-DP-0113-1 & 2_Rev-A(SHUJAA-2000 SETUP PLAN DURING ZULF 1490-1499 PDM INSTALLATION) | 2300-DP-0113 | A |  |  | 2025-12-09 | EJJ
| 2302-A0-069-1 OF 5_R1(Ras Tanura to Tanajib J Power Location) | 2302-A0-069 | 1 |  |  | 2025-12-09 | SKV
| 2302-A0-073-1 OF 5_R1(Ras Tanura to Tanajib J Power Location)-option | 2302-A0-073 | 1 |  |  | 2025-12-09 | SKV
| 2302-DP-0124-1 TO 2_Rev-A(RAWABI-608 SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1380-1389) | 2302-DP-0124 | A |  |  | 2025-12-10 | SKV
| 2300-A0-105_R0(SEP-450 Passage plan from ANCHORAGE to ZULF 1210-1219) | 2300-A0-105 | 0 |  |  | 2025-12-11 | EJJ
| 2300-DP-0115-1 & 2_Rev-A(SEP-450 SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1210-1219) | 2300-DP-0115 | A |  |  | 2025-12-11 | EJJ
| 2302-A0-089_R0 (QMS AL SHAHAMA II Passage plan from ANCHORAGE to ZULF 1410-1419) | 2302-A0-089 | 0 |  |  | 2025-12-11 | EJJ
| 2302-DP-0125-1 & 2_Rev-A(QMS AL SHAHAMA-II DP SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1410-1419) | 2302-DP-0125 | A |  |  | 2025-12-11 | EJJ
| 2300-A0-107_R0(CHUANG LI Passage plan from ANCHORAGE to EDP-2) | 2300-A0-107 | 0 |  |  | 2025-12-16 | SKV
| 2300-DP-0114-1 TO 2_Rev-A(CHUANG LI SET-UP PLAN DURING ZULF EDP-2 DECK INSTALLATION) | 2300-DP-0114 | A |  |  | 2025-12-16 | SKV
| 2300-A0-083_R1(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF GOSP-2 GGP) | 2300-A0-083 | 1 |  |  | 2025-12-16 | SKV
| 2300-A0-084_R1(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF GOSP-1 PP) | 2300-A0-084 | 1 |  |  | 2025-12-16 | SKV
| 2302-A0-093_R0(OML INTERVENTION-II Passage plan from Anchorage to ZULF 1380-1389) | 2302-A0-093 | 0 |  |  | 2025-12-17 | EJJ
| 2302-DP-0132-1 & 2_Rev-A(OML INTERVENTION-II SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1380-1389) | 2302-DP-0132 | A |  |  | 2025-12-17 | EJJ
| 2300-DP-0091_Rev-B(SHUJAA-2000 SET-UP plan during Lifting Activities at ZULF GOSP-2 GGP) | 2300-DP-0091 | B |  |  | 2025-12-22 | SKV
| 2300-DP-0092_Rev-B(SHUJAA-2000 SET-UP plan during Lifting Activities at ZULF GOSP-2 AP) | 2300-DP-0092 | B |  |  | 2025-12-22 | SKV
| 2300-DP-0114-1 to 2_Rev-B(CHUANG LI SET-UP PLAN DURING ZULF EDP-2 DECK INSTALLATION) | 2300-DP-0114 | B |  |  | 2025-12-22 | SKV
| 2300-DP-0110-1 TO 2_Rev-B(SWORDFISH SET-UP PLAN DURING C31-230KV CABLE SHIFTING AT ZULF EDP-2) | 2300-DP-0110 | B |  |  | 2025-12-22 | SKV
| 2302-A0-069-1 OF 5_R1(Ras Tanura to Tanajib J Power Location) | 2302-A0-069 | 1 |  |  | 2025-12-24 | SKV
| 2300-A3-076-1 TO 2_REV-C(JUMBO BAG INSTALLATION FOR 15 Kv CABLE)-1300-1309 | 2300-A3-076 | C |  |  | 2025-12-26 | SKV
| 2302-DP-0119-1 TO 2_REV-B(UMM SHAIF SET-UP DURING CABLE LAYING FROM FROM ZTPS-4 TO ZULF1300-1309) | 2302-DP-0119 | B |  |  | 2025-12-26 | SKV
| 2300-DP-0118-1 & 2_Rev-A (OML INTERVENTION-II Setup plan during Hook-up works @ ZTPS-1) | 2300-DP-0118 | A |  |  | 2025-12-02 | EJJ
| 2300-A0-110_R0(LB-II Passage plan from ANCHORAGE to ZULF TPS-1) | 2300-A0-110 | 0 |  |  | 2026-01-05 | SKV
| 2300-DP-0117-1 TO 9_REV-A(LB-II SETUP PLAN DURING TPS-1 TOPSIDE INSTALLATION (FLOATOVER)) | 2300-DP-0117 | A |  |  | 2026-01-05 | SKV
| 2300-DP-0118-1 & 2_Rev-B(OML INTERVENTION-II Setup plan during Hook-up works @ ZTPS-1) | 2300-DP-0118 | B |  |  | 2026-01-05 | EJJ
| 2300-A0-051_R1(OML INTERVENTION-II Passage plan from ANCHORAGE to ZULF TPS-1) | 2300-A0-051 | 1 |  |  | 2026-01-06 | EJJ
| 2300-DP-0118-1 & 2_Rev-A(OML INTERVENTION-II Setup plan during Hook-up works @ ZTPS-1) | 2300-DP-0118 | A |  |  | 2026-01-06 | EJJ
| 2300-A0-0114_R0(RAWABI-608 Passage plan from ANCHORAGE to ZULF 1410-1419) | 2300-A0-0114 | 0 |  |  | 2026-01-07 | AAE
| 2300-DP-0127_Rev-A(RAWABI-608 SETUP PLAN DURING HOOK-UP WORKS AT RBYN 10-19) | 2300-DP-0127 | A |  |  | 2026-01-07 | AAE
| 2302-DP-0128_Rev-A(RAWABI-608 SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1410-1419) | 2302-DP-0128 | A |  |  | 2026-01-07 | AAE
| 2300-A0-114_R0(HEA AL SARAB Passage plan from ANCHORAGE to EDP-2) | 2300-A0-114 | 0 |  |  | 2026-01-07 | EJJ
| 2300-DP-0124-1 & 2_Rev-A(HEA AL SARAB SET-UP AT ZULF EDP-2 DURING HOOK-UP WORKS) | 2300-DP-0124 | A |  |  | 2026-01-07 | EJJ
| 2300-DP-0117-1 TO 8_REV-B(LB-II SETUP PLAN DURING TPS-1 TOPSIDE INSTALLATION (FLOATOVER)) | 2300-DP-0117 | B |  |  | 2026-01-12 | SKV
| 2300-DP-0118-1 & 2_Rev-B(OML INTERVENTION-II Setup plan during Hook-up works @ ZTPS-1) | 2300-DP-0118 | B |  |  | 2025-01-12 | EJJ
| 2300-DP-0124-1 & 2_Rev-B(HEA AL SARAB SET-UP AT ZULF EDP-2 DURING HOOK-UP WORKS) | 2300-DP-0124 | B |  |  | 2026-01-13 | EJJ
| SEP-450 SETUP PLAN DURING HOOK-UP WORKS AT ZULF EDP-2 | 2300-DP-0132 | A |  |  | 2026-01-20 | EJJ
| SEP-450 PASSAGE PLAN FROM ANCHORAGE TO ZULF EDP-2 | 2300-A0-120 | 0 |  |  | 2026-01-20 | EJJ
| UMM SHAIF BERTH PLAN AT TANAJIB PIER FOR 15KV TRANSPOOLING | 2300-2302-A0-074 | A |  |  | 2026-01-21 | SKV
| 2300-A0-069_R0(CHUANG LI Passage plan from ANCHORAGE to ZULF 228-233) | 2300-A0-069 | 0 |  |  | 2026-02-04 | SKV
| 2790-2792-DP-0092-1 TO 2_Rev-A(CHUANG LI SET-UP PLAN DURING Demolition and Installation of upgrade platform at ZULF 228-233) | 2790-2792-DP-0092 | A |  |  | 2026-02-04 | SKV
| 2302-A0-0107_R0(RAWABI-608 Passage plan from NORTH ANCHORAGE to ZULF 1330-1339) | 2302-A0-0107 | 0 |  |  | 2026-02-09 | EJJ
| 2302-DP-0149-1 & 2_Rev-A(RAWABI-608 DP SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1330-1339) | 2302-DP-0149 | A |  |  | 2026-02-09 | EJJ
| 2302-DP-0143-1 TO 2_REV-B(CCC-MARITIME-2 SET-UP PLAN DURING PRE COMMISSIONING ACTIVITIES FOR 12 PL AT ZULF 1380-1389 TO TPS-2 | 2302-DP-0143 | B |  |  | 2026-02-09 | DH
| 2300-A0-126_R0(HEA AL SARAB PASSAGE PLAN FROM NORTH ANCHORAGE TO ZULF ZULF 1270-1279)_SUR-9192 | 2300-A0-126 | 0 |  |  | 2026-02-10 | EJJ
| 2300-DP-0137-1 & 2_Rev-A(HEA AL SARAB SETUP PLAN DURING HOOK-UP AND PRE-COMMISSIONING WORKS AT ZULF 1270-1279) | 2300-DP-0137 | A |  |  | 2026-02-10 | EJJ
| 2300-A0-127_R0(RAWABI-608 PASSAGE PLAN FROM ANCHORAGE TO ZULF 1240-1249)_SUR-1819 | 2300-A0-127 | 0 |  |  | 2026-02-11 | EJJ
| 2300-DP-0138-1 & 2_Rev-A(RAWABI-608 SETUP PLAN DURING HOOK-UP AND PRE-COMMISSIONING WORKS AT ZULF 1240-1249) | 2300-DP-0138 | A |  |  | 2026-02-11 | EJJ
| 2302-A0-113_R0 (RAWABI-608 passage plan from anchorage to ZULF 1370-1379) | 2302-A0-113 | 0 |  |  | 2026-02-16 | VSK
| 2302-DP-0152-1 TO 2_Rev-A(RAWABI-608 SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1370-1379) | 2302-DP-0152 | 0 |  |  | 2026-02-16 | VSK
| 2302-A0-029_R3(OML INTERVENTION-II Passage plan from ANCHORAGE to ZTPS-2) | 2302-A0-029 | 3 |  |  | 2026-02-19 | DRH
| 2302-DP-0025-1 & 2_Rev-C(OML INTERVENTION-II Setup plan during preparatory works @ ZTPS-2) | 2302-DP-0025 | C |  |  | 22-02-2026 | EJJ
| 2300-A3-096-1 TO 6_Rev-A (Typical Umbilical pull through j-tube(start-up) at ZULF Platforms by WADAD ALETHEIA) | 2300-A3-096 | A |  |  | 25-02-2026 | VSK
| 2300-A3-097-1 TO 6_Rev-A (Typical Umbilical Laying and Laydown at SSVS by WADAD ALETHEIA) | 2300-A3-097 | A |  |  | 25-02-2026 | VSK
| ORIENTAL DRAGON DECK LAYOUT FOR ICCP CABLE LAYING AND ANODE INSTALLATION | 2302-A3-025 | 0 |  |  | 2026-03-04 | VSK
| 2302-DP-0164-1 TO 2_REV-B(ORIENTAL DRAGON setup plan during ICCP Cable installation at ZULF 1340-1349) | 2302-DP-0164 | B |  |  | 2026-03-10 | VSK
| 2302-DP-0173-1 TO 2_Rev-A (SWORDFISH SETUP PLAN DURING TEMPORARY SUPPORTS INSTALLATION NEAR ZULF TPS-2 & TPS-4) | 2302-DP-0173 | A |  |  | 2026-03-13 | VSK
| 2302-DP-0173-1 TO 2_Rev-B (SWORDFISH SETUP PLAN DURING TEMPORARY SUPPORTS INSTALLATION NEAR ZULF TPS-2 & TPS-4) | 2302-DP-0173 | B |  |  | 2026-03-16 | VSK
| 2300-DP-0154_Rev-C(SHUJAA-2000 SETUP PLAN DURING SUBSEA SPOOL AND SSVS INSTALLATION AT ZULF-1240-1249) | 2300-DP-0154 | 3 |  |  | 2026-03-18 | EJJ
| 2302-DP-0162_Rev-03(ORIENTAL DRAGON SET-UP DURING ICCP CABLE INSTALLATION AT ZULF 1380-1389) | 2302-DP-0162 | 3 |  |  | 2026-03-18 | EJJ
| 2302-DP-0163_Rev-03(ORIENTAL DRAGON SET-UP DURING ICCP CABLE INSTALLATION AT ZULF 1410-1419) | 2302-DP-0163 | 3 |  |  | 2026-03-18 | EJJ
| 2302-DP-0164-1 TO 2_REV-D(ORIENTAL DRAGON setup plan during ICCP Cable installation at ZULF 1340-1349) | 2302-DP-0164 | D |  |  | 2026-03-18 | EJJ
| 2302-DP-0174-1 TO 2_REV-C(ORIENTAL DRAGON setup plan during ICCP Cable installation at ZULF 1360-1369) | 2302-DP-0174 | C |  |  | 2026-03-18 | EJJ
| 2302-DP-0175-1 TO 2_REV-C(ORIENTAL DRAGON setup plan during ICCP Cable installation at ZULF 1370-1379) | 2302-DP-0175 | C |  |  | 2026-03-18 | EJJ
| 2300-A0-132_R2(SWORDFISH Passage plan from ANCHORAGE to ZULF 1200-1209 and TIE-IN SPOOL LOCATION) | 2300-A0-132 | 2 |  |  | 2026-03-23 | EJJ
| 2300-DP-0150_Rev-B(SWORDFISH SETUP PLAN DURING RISER,CLAMP,SSVS,SUBSEA SPOOL INSTALLATIONS AT ZULF 1200-1209) | 2300-DP-0150 | B |  |  | 2026-03-23 | EJJ
| 2300-DP-0147_Rev-A(SWORDFISH SETUP PLAN DURING SSVS AND SUBSEA SPOOL INSTALLATION AT ZULF 630, 1390-1399) | 2300-DP-0147 | A |  |  | 2026-03-24 | EJJ
| 2302-DP-0173-1 TO 2_Rev-B (SWORDFISH SETUP PLAN DURING TEMPORARY SUPPORTS INSTALLATION NEAR ZULF TPS-2 & TPS-4) | 2302-DP-0173 | B |  |  | 2026-03-26 | SKV
| 2300-A0-137_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF 1230-1239) | 2300-A0-137 | 0 |  |  | 2026-03-31 | SKV
| 2300-DP-0159_Rev-A(SWORDFISH SET-UP PLAN DURING SUBSEA SPOOLS AND SSVS INSTALLATION AT ZULF 1230-1239) | 2300-DP-0159 | A |  |  | 2026-03-31 | SKV
| 2302-A0-109_R1(SWORDFISH) Passage plan from ANCHORAGE to ZULF 1300-1320) | 2302-A0-109 | 1 |  |  | 2026-03-31 | SKV
| 2302-DP-0151_1 TO 2_Rev-A(SWORDFISH DP SET-UP DURING LATERAL SPOOL INSTALLATION AND FLEXIBLE TIE-IN TO ZTPS 2(ZULF 1300-1320) | 2302-DP-0151 | A |  |  | 2026-03-31 | SKV
| 2300-A0-110_R1(LB-II Passage plan from ANCHORAGE to ZULF TPS-1) | 2300-A0-110 | 1 |  |  | 2026-03-31 | EJJ
| 2300-A0-111_R1(SWORDFISH Passage plan from ANCHORAGE to ZULF TPS-1) | 2300-A0-111 | 1 |  |  | 2026-04-01 | EJJ
| 2302-A0-137_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1300-1309) | 2302-A0-137 | 0 |  |  | 2026-04-01 | EJJ
| 2302-DP-0184_Rev-A (SHUJAA-2000 SET-UP PLAN DURING UMBILICAL INSTALLATION FROM ZULF 1300-1309 TO SSVS) | 2302-DP-0184 | A |  |  | 2026-04-01 | EJJ
| 2302-A0-138_R0(OML INTERVENTION II Passage plan from ANCHORAGE to ZULF 1290-1299) | 2302-A0-138 | 0 |  |  | 2026-04-02 | SKV
| 2302-DP-0185-1 TO 2_Rev-A(OML INTERVENTION-II SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1290-1299) | 2302-DP-0185 | A |  |  | 2026-04-02 | SKV
| 2302-A0-139_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1380-1389) | 2302-A0-139 | 0 |  |  | 2026-04-04 | SKV
| 2302-A0-140_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1410-1419) | 2302-A0-140 | 0 |  |  | 2026-04-04 | SKV
| 2302-DP-0186_Rev-A(SHUJAA-2000 SET-UP PLAN DURING UMBILCAL LAYING AT ZULF 1380-1389) | 2302-DP-0186 | A |  |  | 2026-04-04 | SKV
| 2302-DP-0187_Rev-A(SHUJAA-2000 SET-UP PLAN DURING UMBILCAL LAYING AT ZULF 1410-1419) | 2302-DP-0187 | A |  |  | 2026-04-04 | SKV
| 2302-A0-147_R0 (SHUJAA-2000 passage plan from anchorage to ZULF TPS-2) | 2302-A0-147 | 0 |  |  | 2026-04-09 | SKV
| 2302-DP-0192-1 TO 2_Rev-A (SHUJAA-2000 SETUP PLAN DURING FLEXIBLE PL INSTALLATION FROM ZULF TPS-2 TO ZULF 1360-1369) | 2302-DP-0192 | A |  |  | 2026-04-09 | SKV
| 2302-A0-147_R0 (SHUJAA-2000 passage plan from anchorage to ZULF TPS-2) | 2302-A0-147 | 0 |  |  | 2026-04-10 | SKV
| 2302-DP-0192-1 TO 2_Rev-A (SHUJAA-2000 SETUP PLAN DURING FLEXIBLE PL INSTALLATION FROM ZULF TPS-2 TO ZULF 1360-1369) | 2302-DP-0192 | A |  |  | 2026-04-10 | SKV
| 2302-DP-0194_Rev-A(SHUJAA-2000 SET-UP PLAN DURING FLEXIBLE PL INSTALLATION AT ZULF 1370-1379) | 2302-DP-0194 | A |  |  | 2026-04-10 | SKV
| 2302-A0-137_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1300-1309) | 2302-A0-137 | 0 |  |  | 2026-04-12 | SKV
| 2302-DP-0195_Rev-A (SHUJAA-2000 SET-UP PLAN DURING FLEXIBLE PL INSTALLATION FROM ZULF 1300-1309 TO SSVS) | 2302-DP-0195 | A |  |  | 2026-04-12 | SKV
| 2302-A0-137_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1300-1309) | 2302-A0-137 | 0 |  |  | 2026-04-13 | SKV
| 2302-DP-0195_Rev-A (SHUJAA-2000 SET-UP PLAN DURING FLEXIBLE PL INSTALLATION FROM ZULF 1300-1309 TO SSVS) | 2302-DP-0195 | A |  |  | 2026-04-13 | SKV
| 2302-A0-148_R0(ORIENTAL DRAGON Passage plan from ANCHORAGE to ZULF 1300-1320) | 2302-A0-148 | 0 |  |  | 2026-04-15 | SKV
| 2302-DP-0197_1 TO 2-Rev-A(ORIENTAL DRAGON SET-UP DURING LATERAL SPOOL INSTALLATION AND FLEXIBLE TIE-IN TO ZTPS 2(ZULF 1300-1320) | 2302-DP-0197 | A |  |  | 2026-04-15 | SKV
| 2300-A0-145_R0(ORIENTAL DRAGON Passage plan FROM ANCHORAGE TO ZULF 1240-1249) | 2300-A0-145 | 0 |  |  | 2026-04-16 | SKV
| 2300-DP-0172_Rev-A(ORIENTAL DRAGON SETUP PLAN DURING SUBSEA SPOOL AND SSVS INSTALLATION AT ZULF-1240-1249) | 2300-DP-0172 | A |  |  | 2026-04-16 | SKV
| 2302-A0-153_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF TPS-2 & TPS-4 & TPS-3) | 2302-A0-153 | 0 |  |  | 2026-04-30 | SKV
| 2302-DP-0200-1 TO 3_Rev-A (SWORDFISH SETUP PLAN DURING FLEXIBLE PL TIE-IN WITH RISER FOR ZULF TPS-2 & TPS-4 & TPS-3 LINES) | 2302-DP-0200 | A |  |  | 2026-04-30 | SKV
| 2302-DP-0200-1 TO 3_Rev-B (SWORDFISH SETUP PLAN DURING FLEXIBLE PL TIE-IN WITH RISER FOR ZULF TPS-2 & TPS-4 & TPS-3 LINES) | 2302-DP-0200 | B |  |  | 2026-05-04 | SKV
| 2302-DP-0200-1 TO 3_Rev-B (SWORDFISH SETUP PLAN DURING FLEXIBLE PL TIE-IN WITH RISER FOR ZULF TPS-2 & TPS-4 & TPS-3 LINES) | 2302-DP-0200 | B |  |  | 2026-05-05 | SKV
| 2300-A0-158_R0(QMS AL SHAHAMA-II PASSAGE PLAN FROM ANCHORAGE to ZULF EDP-2) | 2300-A0-158 | 0 |  |  | 2026-05-07 | EJJ
| 2300-DP-0185-1 & 2_Rev-A(QMS AL SHAHAMA-II SET-UP AT ZULF EDP-2 DURING HOOK-UP WORKS) | 2300-DP-0185 | A |  |  | 2026-05-07 | EJJ
| 2302-A0-149_R0(SHUJAA-2000 Passage plan During Umbilical laying AT ZULF 1330-1339)_SUR 9192 | 2302-A0-149 | 0 |  |  | 2026-05-11 | SKV
| 2302-A0-154_R0(SHUJAA-2000 Passage plan During Umbilical laying AT ZULF 1290-1299)_SUR 9192 | 2302-A0-154 | 0 |  |  | 2026-05-11 | SKV
| 2302-DP-0199_Rev-A(SHUJAA-2000 SET-UP PLAN DURING UMBILICAL LAYING AT ZULF 1330-1339) | 2302-DP-0199 | A |  |  | 2026-05-11 | SKV
| 2302-DP-0202_Rev-A(SHUJAA-2000 SET-UP PLAN DURING UMBILICAL LAYING AT ZULF 1290-1299) | 2302-DP-0202 | A |  |  | 2026-05-11 | SKV
| 2300-DP-0185-1 & 2_Rev-B(QMS AL SHAHAMA-II SET-UP AT ZULF EDP-2 DURING HOOK-UP WORKS) | 2300-DP-0185 | B |  |  | 2026-05-13 | EJJ
| 2300-A0-141_R1(UMM SHAIF PASSAGE PLAN FROM ANCHORAGE to ZULF EDP-2 TO ZULF 1200-1209) | 2300-A0-141 | 1 |  |  | 2026-05-14 | SKV
| 2300-DP-0119-1 TO 3_REV-B(UMM SHAIF DP SET-UP DURING CABLE LAYING FROM ZEDP-2 TO ZULF 1200-1209) | 2300-DP-0119 | B |  |  | 2026-05-14 | SKV
| 2300-DP-0160-1 TO 4_REV-C(UMM SHAIF SET-UP DURING MATTRESS & JUMBO BAG INSTALLATION AT ZULF 1200-1209) | 2300-DP-0160 | C |  |  | 2026-05-14 | SKV
| 2300-DP-0191_Rev-A(SHUJAA-2000 SET-UP PLAN DURING UMBILICAL LAYING AT ZULF 1210-1219) | 2300-DP-0191 | A |  |  | 2026-05-19 | SKV
| 2300-DP-0192_Rev-A(SHUJAA-2000 SET-UP PLAN DURING UMBILICAL INSTALLATION AT ZULF 1230-1239) | 2300-DP-0192 | A |  |  | 2026-05-19 | SKV
| 2300-DP-0197-1 & 2_Rev-A(RAWABI-608 SETUP PLAN DURING HOOK-UP AND PRE-COMMISSIONING WORKS AT ZULF 630, 1390-1399) | 2300-DP-0197 | A |  |  | 2026-06-03 | EJJ
| 2300-DP-0205-1 & 2_Rev-A(HEA AL SARAB SETUP PLAN DURING HOOK-UP AND PRE-COMMISSIONING WORKS AT ZULF 1260-1269) | 2300-DP-0205 | A |  |  | 2026-06-03 | EJJ
| 2300-DP-0206-1 & 2_Rev-A(QMS AL SHAHAMA-II SETUP PLAN DURING HOOK-UP AND PRE-COMMISSIONING WORKS AT ZULF 1270-1279) | 2300-DP-0206 | A |  |  | 2026-06-03 | EJJ
| 2300-A0-170_R0(RAWABI-608 Passage plan from ANCHORAGE to ZULF 630, 1390-1399)-SUR 1819 | 2300-A0-170 | 0 |  |  | 2026-06-01 | EJJ
| 2300-A0-171_R0(HEA AL SARAB PASSAGE PLAN FROM NORTH ANCHORAGE TO ZULF ZULF 1260-1269)-SUR 9192 | 2300-A0-171 | 0 |  |  | 2026-06-01 | EJJ
| 2300-A0-172_R0(QMS AL SHAHAMA-II Passage plan from NORTH ANCHORAGE to ZULF 1270-1279)-SUR 9192 | 2300-A0-172 | 0 |  |  | 2026-06-01 | EJJ
| 2300-A0-0173_R0(SWORDFISH Passage plan from NORTH ANCHORAGE to ZULF 1270-1279)-SUR-9192 | 2300-A0-0173 | 0 |  |  | 2026-06-01 | SKV
| 2300-A0-0174_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF 1250-1259)-SUR 1819 | 2300-A0-0174 | 0 |  |  | 2026-06-01 | SKV
| 2300-DP-0203-1 TO 2_Rev-A (SWORDFISH SETUP PLAN DURING FLEXIBLE PL TIE-IN AT ZULF 1250-1259 & ZULF 1270-1279) | 2300-DP-0203 | A |  |  | 2026-06-01 | SKV
| CONSTRUCTION VESSEL-VESSEL SETUP AT INSTALLATION POSITION (RMM) | 2300-A0-178 | 0 |  |  | 2026-06-09 | EJJ
| 2300-A0-171_R0(HEA AL SARAB PASSAGE PLAN FROM NORTH ANCHORAGE TO ZULF ZULF 1260-1269)-SUR 9192 | 2300-A0-171 | 0 |  |  | 2026-06-09 | EJJ
| 2300-DP-0205-1 & 2_Rev-A(HEA AL SARAB SETUP PLAN DURING HOOK-UP AND PRE-COMMISSIONING WORKS AT ZULF 1260-1269) | 2300-DP-0205 | A |  |  | 2026-06-09 | EJJ
| 2300-A0-171_R0(HEA AL SARAB PASSAGE PLAN FROM ANCHORAGE TO ZULF 1260-1269)-SUR-1819 | 2300-A0-171 | 0 |  |  | 2026-06-10 | EJJ
| 2300-A0-172_R0(QMS AL SHAHAMA-II Passage plan from ANCHORAGE to ZULF 1270-1279)-SUR-1819 | 2300-A0-172 | 0 |  |  | 2026-06-10 | EJJ
| 2300-A0-178_R1(MILLENNIUM-3) | 2300-A0-178 | 1 |  |  | 2026-06-11 | EJJ
| 2300-DP-0206-1 & 2_Rev-B(QMS AL SHAHAMA-II SETUP PLAN DURING HOOK-UP AND PRE-COMMISSIONING WORKS AT ZULF 1270-1279) | 2300-DP-0206 | B |  |  | 2026-06-12 | EJJ
| 2300-A0-171_R0(HEA AL SARAB PASSAGE PLAN FROM ANCHORAGE TO ZULF 1260-1269)-SUR-1819 | 2300-A0-171 | 0 |  |  | 2026-06-12 | EJJ
| 2300-A0-172_R0(QMS AL SHAHAMA-II Passage plan from ANCHORAGE to ZULF 1270-1279)-SUR-1819 | 2300-A0-172 | 0 |  |  | 2026-06-12 | EJJ
| 2302-A0-091_Rev-2(CCC MARITIME-2 passage plan from anchorage to ZULF 1330-1339) | 2302-A0-091 | 2 |  |  | 2026-06-14 | EJJ
| 2302-A0-161_R0(CCC MARITIME-2 Passage plan from ANCHORAGE to Z1270-1279 ) | 2302-A0-161 | 0 |  |  | 2026-06-14 | EJJ
| 2300-DP-0208_Rev-B(CCC MARITIME-2 SET-UP DURING ICCP CABLE INSTALLATION AT ZULF 1270-1279) | 2300-DP-0208 | B |  |  | 2026-06-14 | EJJ
| 2302-DP-0128_Rev-C(CCC MARITIME-2 DP SET-UP DURING ICCP CABLE INSTALLATION AT ZULF 1330-1339) | 2302-DP-0128 | B |  |  | 2026-06-14 | EJJ
| 2300-DP-0213_Rev-A(SHUJAA-2000 SET-UP PLAN DURING UMBILICAL INSTALLATION FROM ZULF 1240-1249 TO SSVS) | 2300-DP-0213 | A |  |  | 2026-06-16 | SKV
| 2300-DP-0214_Rev-A(SHUJAA-2000 SET-UP PLAN DURING UMBILICAL INSTALLATION FROM ZULF 1280-1289 TO SSVS) | 2300-DP-0214 | A |  |  | 2026-06-16 | SKV
| 2300-DP-0219_REV-A(SWORDFISH SET-UP PLAN DURING 15kV CABLE SHIFTING AT ZEDP-2) | 2300-DP-0219 | A |  |  | 2026-06-17 | SKV
| 2300-DP-0205-1 TO 4_Rev-A(SHUJAA-2000 SET-UP during Freespan Correction & Flooding & Mattress Installation on 30Inch Tie-line from ZTPS-4 to ZTPS-2) | 2300-DP-0205 | A |  |  | 2026-06-30 | SKV
| 2302-A0-163_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF TPS-4 & TPS-2)-SUR9192 | 2302-A0-163 | 0 |  |  | 2026-06-30 | SKV
| 2302-A0-165_R0( SEP-450 Passage plan from ANCHORAGE to ZULF TPS-2) | 2302-A0-165 | 0 |  |  | 2026-07-03 | SKV
| 2302-DP-0233-1 TO 2_Rev-A(SEP-450 SETUP PLAN DURING HOOK-UP WORKS AT ZULF TPS-2) | 2302-DP-0233 | A |  |  | 2026-07-03 | SKV
| 2302-A0-116_R0(RAWABI-608 Passage plan from ANCHORAGE to ZULF 1300-1309) | 2302-A0-116 | 0 |  |  | 2026-07-07 | EJJ
| 2302-A0-136_R0( HEA AL SARAB Passage plan from ANCHORAGE to ZULF 1320-1329) | 2302-A0-136 | 0 |  |  | 2026-07-07 | EJJ
| 2300-A0-194_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 1400-1409 & 1210-1219 & 1220-1229)-SUR1819 | 2300-A0-194 | 0 |  |  | 2026-07-07 | SKV
| 2300-DP-0231-1 TO 3_Rev-A(SHUJAA-2000 SET-UP PLAN DURING LATERAL SPOOL, SSVS INSTALLATION, AND FLEXIBLE TIE-IN FOR THE PIPELINES CONNECTED TO ZTPS 1) | 2300-DP-0231 | A |  |  | 2026-07-07 | SKV
| 2302-DP-0211-1 TO 4_Rev-A(SWORDFISH SET-UP during Freespan Correction & Flooding & Mattress Installation on 30Inch Tie-line from ZTPS-4 to ZTPS-2) | 2302-DP-0211 | A |  |  | 2026-07-07 | SKV
| 2300-A0-211_R0(HEA AL MAQAM Passage plan FROM ANCHORAGE TO ZULF 1270-1279)-SUR 1819 | 2300-A0-211 | 0 |  |  | 2026-08-11 | SKV
| 2300-DP-0249-1 TO 2_Rev-A(HEA AL MAQAM SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1270-1279) | 2300-DP-0249 | A |  |  | 2026-08-11 | SKV
| 2300-A0-212_R0(RAWABI-608 Passage plan from ANCHORAGE to ZULF 1230-1239)-SUR 1819 | 2300-A0-212 | 0 |  |  | 2026-08-11 | SKV
| 2300-DP-0250-1 TO 2_Rev-A(RAWABI-608 SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1230-1239) | 2300-DP-0250 | A |  |  | 2026-08-11 | SKV
| 2300-A0-213_R0(SEP-450 Passage plan from ANCHORAGE to ZULF 1230-1239)-SUR-1819 | 2300-A0-213 | 0 |  |  | 2026-08-15 | SKV
| 2300-DP-0252-1 TO 2_Rev-A(SEP-450 SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1230-1239) | 2300-DP-0252 | A |  |  | 2026-08-15 | SKV
| 2300-DP-0245-1 TO 3_Rev-B(SWORDFISH SET-UP PLAN DURING LATERAL SPOOL, SSVS INSTALLATION, AND FLEXIBLE TIE-IN at Z1250 & 1270) (2) | 2300-DP-0245 | B |  |  | 2026-08-18 | DRH
| 2300-A0-0214_R0(CCC MARITIME-II Passage plan from ANCHORAGE to ZULF TPS-3) | 2300-A0-0214 | 0 |  |  | 2026-08-18 | SKV
| 2300-DP-0253-1 TO 2_Rev-A(CCC MARITIME-II SET-UP PLAN DURING FLOODING FOR 30Inch TIE-LINE FROM ZTPS-3 TO ZTPS-1) | 2300-DP-0253 | A |  |  | 2026-08-18 | SKV
| 2302-A0-159_R1(OML INTERVENTION-II passage plan from anchorage to ZULF TPS-3) | 2302-A0-159 | 1 |  |  | 2026-08-27 | EJJ
| 2302-DP-0204-1 TO 2_Rev-C(OML INTERVENTION-II SET-UP PLAN DURING HOOK-UP WORKS AT ZULF TPS-3) | 2302-DP-0204 | C |  |  | 2026-08-27 | EJJ
| 2300-A0-216_R0(QMS AL SHAHAMA-II Passage plan from ANCHORAGE to ZULF 1200-1209) | 2300-A0-216 | 0 |  |  | 2026-08-30 | EJJ
| 2300-DP-0261-1 & 2_Rev-A(QMS AL SHAHAMA- II SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 1200-1209) | 2300-DP-0261 | A |  |  | 2026-08-30 | EJJ
| 2300-A0-157_R1(QMS SHAHAMA II Passage plan from ANCHORAGE to RBYN 10-19) | 2300-A0-157 | 1 |  |  | 2026-08-31 | EJJ
| 2300-A0-157_R1(QMS SHAHAMA II Passage plan from ANCHORAGE to RBYN 10-19) | 2300-A0-157 | 1 |  |  | 2026-09-01 | EJJ
| 2300-DP-0183-1 & 2_Rev-B(QMS AL SHAHAMA II SET-UP PLAN DURING HOOK-UP WORKS AT RBYN 10-19) | 2300-DP-0183 | B |  |  | 2026-09-01 | EJJ
| 2300-A0-113_R2(RAWABI-608 Passage plan from ANCHORAGE to RBYN 10-19) | 2300-A0-113 | 2 |  |  | 2026-09-01 | EJJ
| 2300-DP-0127-1 & 2_Rev-C(RAWABI-608 SET-UP PLAN DURING HOOK-UP WORKS AT RBYN 10-19) | 2300-DP-0127 | C |  |  | 2026-09-01 | EJJ
| 2300-DP-0254-1 & 2_Rev-A(HEA AL SARAB SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1400-1409) | 2300-DP-0254 | A |  |  | 2026-09-02 | EJJ
| 2302-DP-0204-1 TO 2_Rev-D(OML INTERVENTION-II SET-UP PLAN DURING HOOK-UP WORKS AT ZULF TPS-3) | 2302-DP-0204 | D |  |  | 2026-09-04 | EJJ
| 2300-A0-171_R1(HEA AL SARAB PASSAGE PLAN FROM ANCHORAGE TO ZULF 1260-1269)-SUR-1819 | 2300-A0-171 | 1 |  |  | 2026-09-08 | EJJ
| 2300-DP-0266-1 & 2_Rev-A(HEA AL MAQAM SETUP PLAN DURING HOOK-UP WORKS AT ZULF 1210-1219) | 2300-DP-0266 | A |  |  | 2026-09-08 | EJJ