## Installation Procedures
NMDC DOC. No.: MDR-001
CRPO #86 FOR JAFURAH DEVELOPMENT PROGRAM
|  | NMDC PROJECT NO. 2412-2413 | [11 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ARAMCO OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Method TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| SPM ANCHOR PILE & CHAIN INSTALLATION PROCEDURE | 2412-2413-PP-OF-004 |  | A1 |  |  | T-233/24 | 2024-06-01
|  |  |  | A |  |  | T-276/24 | 2024-06-27 | 2024-07-16 | 2412-2413-NPCC-T-06240 | 2024-07-19 | CPD-14244-SA-T-1760-24 | 04 - Action-Process
|  |  |  | 00 |  |  | T-334/24 | 2024-07-25 | 2024-07-29 | 2412-2413-NPCC-T-06376 | 2024-08-13 | CPD-14244-SA-T-1957-24 | 02 - Review & Comments
|  |  |  | 00A |  |  | T-387/24 | 2024-08-27 | 2024-09-04 | 2412-2413-NPCC-T-06817 | 2024-09-11 | CPD-14244-SA-T-2193-24 | 06 - No Objection
|  |  |  | 00B |  |  | T-465/24 | 2024-09-25 | 2024-10-07 | 2412-2413-NPCC-T-07143 | 2024-10-07 | CPD-14244-SA-T-2406-24 | 06 - No Objection
|  |  |  | 00C |  |  | T-558/24 | 2024-11-22 | 2024-11-22 | 2412-2413-NPCC-T-07623
| SUBSEA CABLE INSTALLATION PROCEDURE | 2412-2413-PP-OF-014 |  | A |  |  | T-065/25 | 2025-02-05 | 2025-02-13 | 2412-2413-NPCC-T-08200 | 2025-02-21 | CPD-14244-SA-T-0351-25 | 02 - Review & Comments
|  |  |  | B |  |  | T-085/25 | 2025-03-18 | 2025-03-18 | 2412-2413-NPCC-T-08447 | 2025-04-29 | CPD-14244-SA-T-1005-25 | 06 - No Objection
|  |  |  | 00 |  |  | T-233/25 | 2025-05-30 | 2025-05-31 | 2412-2413-NPCC-T-09050
| JOP DECK INSTALLATION PROCEDURE | 2412-2413-PP-OF-015 |  | A1 |  |  | T-610/25
|  |  |  | A |  |  | T-636/25 | 2025-12-23 | 2025-12-24 | 2412-2413-NPCC-T-10272 | 2026-01-23 | CPD-14244-SA-T-0127-26 | 02 - Review & Comments
| JACKET INSTALLATION MANUAL | 2412-2413-PP-OF-017 |  | A1 |  |  | T-117/24 | 2024-03-11
|  |  |  | A |  |  | T-219/24 | 2024-05-23 | 2024-05-29 | 2412-2413-NPCC-T-05653 | 2024-06-10 | CPD-14244-SA-T-1452-24 | 04 - Action-Process
|  |  |  | B |  |  | T-314/24 | 2024-07-08 | 2024-07-17 | 2412-2413-NPCC-T-06255 | 2024-07-22 | CPD-14244-SA-T-1774-24 | 04 - Action-Process
|  |  |  | 00 |  |  | T-411/24 | 2024-09-10 | 11-Sep-24 | 2412-2413-NPCC-T-06880 | 2024-09-26 | CPD-14244-SA-T-2323-24 | 06 - No Objection
|  |  |  | 00A |  |  | T-462/24 | 2024-09-24 | 2024-10-22 | 2412-2413-NPCC-T-07308
|  |  |  | 00B |  |  | T-513/25 | 2025-10-08 | 2025-10-09 | 2412-2413-NPCC-T-09932
| SUBSEA SPOOLS INSTALLATION PROCEDURE | 2412-2413-PP-OF-020 |  | A |  |  | T-585/24 | 2024-12-09 | 2024-12-16 | 2412-2413-NPCC-T-07815 | 2024-12-24 | CPD-14244-SA-T-3077-24 | 04 - Action-Process
|  |  |  | 00 |  |  | T-025/25 | 2025-01-17 | 2025-01-19 | 2412-2413-NPCC-T-08031 | 2024-12-24 | CPD-14244-SA-T-3077-24
|  |  |  | 00A |  |  | T-017/26 | 2026-01-12 | 2026-01-13 | 2412-2413-NPCC-T-10343
| EXISTING BOAT LANDING DEMOLITION PROCEDURE | 2412-2413-PP-OF-023
| PIPELINE FREESPAN CORRECTION PROCEDURE | 2412-2413-PP-OF-024 |  | A |  |  | T-012/25 | 2025-01-10 | 2025-01-19 | 2412-2413-NPCC-T-08032 | 2025-01-27 | CPD-14244-SA-T-0178-25 | 02 - Review & Comments
|  |  |  | B |  |  | T-133/25 | 2025-04-09 | 2025-04-09 | 2412-2413-NPCC-T-08619 | 2025-05-12 | CPD-14244-SA-T-1163-25 | 04 - Action-Process
|  |  |  | C |  |  | T-219/25 | 2025-05-28 | 2025-05-29 | 2412-2413-NPCC-T-09040
|  |  |  | 00 |  |  | T-258/25 | 2025-06-11 | 2025-06-12 | 2412-2413-NPCC-T-09142
| SHALLOW WATER MARKERS AND DANGER BUOY INSTALLATION PROCEDURE | 2412-2413-PP-OF-025 |  | A1 |  |  | T-461/25
|  |  |  | A |  |  | T-523/25 | 2025-11-10 | 2025-11-11 | CPD-14244-SA-T-2505-25 | 2025-11-11 | CPD-14244-SA-T-2505-25 | 01 - Information
|  |  |  | B |  |  | T-573/25 | 2025-11-12 | 2025-11-13 | 2412-2413-NPCC-T-10088 | 2025-11-24 | CPD-14244-SA-T-2536-25 | 06 - No Objection
|  |  |  | C |  |  | T-308/26 | 2026-07-17 | 2026-07-18 | 2412-2413-NPCC-T-10768 | 2026-07-22 | CPD-14244-SA-T-0592-26 | 04 - Action-Process
| CROSSING SUPPORTS INSTALLATION PROCEDURE | 2412-2413-PP-OF-027 |  | A1 |  |  | T-203/24 | 2024-05-15
|  |  |  | A |  |  | T-227/24 | 2024-05-29 | 2024-05-31 | 2412-2413-NPCC-T-05680 | 2024-06-11 | CPD-14244-SA-T-1457-24 | 04 - Action-Process
|  |  |  | B |  |  | T-292/24 | 2024-07-01 | 2024-07-16 | 2412-2413-NPCC-T-06245 | 2024-07-23 | CPD-14244-SA-T-1788-24 | 01 - Information
|  |  |  | 00 |  |  | T-345/24 | 2024-07-30 | 01-Aug-2024 | 2412-2413-NPCC-T-06427 | 2024-08-12 | CPD-14244-SA-T-1921-24 | 04 - Action-Process
|  |  |  | 00A |  |  | T-399/24 | 2024-09-03 | 2024-09-04 | 2412-2413-NPCC-T-06818 | 2024-09-11 | CPD-14244-SA-T-2194-24 | 06 - No Objection
| FLANGE MANAGEMENT PROCEDURE – SUBSEA FLANGES - IFR | 2412-2413-PP-OF-028 |  | A |  |  | T-208/23 | 2023-07-12 | 2023-11-15 | 2412-2413-NPCC-T-03692 | 2023-11-23 | CPD-14244-SA-T-2729-23 | 05 - Rejected/Resubmit
|  |  |  | B |  |  | T-239/24 | 2024-06-05 | 2024-06-11 | 2412-2413-NPCC-T-05805 | 2024-08-20 | EPM-2412-2413-PP-OF-028-Rev-B-T-05805 | 01 - Information
|  |  |  | 00 |  |  | T-386/24 | 2024-08-27 | 2024-09-06 | 2412-2413-NPCC-T-06833 | 2024-09-15 | EPM-2412-2413-PP-OF-028-Rev-00-T-06833 | 06 - No Objection
|  |  |  | 00A |  |  | T-425/25 | 2025-08-26 | 2025-08-26 | 2412-2413-NPCC-T-09677
| PIPELINE INTERNAL FIELD JOINT COATING | 2412-2413-PP-OF-030
| PLEM (PIPELINE END MANIFOLD) INSTALLATION PROCEDURE | 2412-2413-PP-OF-033 |  | A |  |  | T-459/24 | 2024-09-24 | 2024-09-24 | 2412-2413-NPCC-T-06990 | 2024-11-13 | CPD-14244-SA-T-2730-24 | 04 - Action-Process
|  |  |  | B |  |  | T-557/24 | 2024-11-21 | 2024-11-22 | 2412-2413-NPCC-T-07614 | 09-Dec-2024 | CPD-14244-SA-T-2940-24 | 06 - No Objection
|  |  |  | 00 |  |  | T-034/25 | 2025-01-22 | 2025-01-24 | 2412-2413-NPCC-T-08078
| RIGID PIPELINE INSTALLATION PROCEDURE FOR 56” PIPELINE SHOREPULL | 2412-2413-PP-OF-034 |  | A1 |  |  | T-342/24 | 2024-07-29
|  |  |  | A |  |  | T-379/24 | 2024-08-21 | 06-Dec-2024 | 2412-2413-NPCC-T-07720 | 2025-02-03 | CPD-14244-SA-T-0215-25 | 02 - Review & Comments
|  |  |  | B |  |  | T-569/24 | 2024-11-29 | 2024-12-06 | 2412-2413-NPCC-T-07720 | 2025-02-03 | CPD-14244-SA-T-0215-25 | 02 - Review & Comments
|  |  |  | 00 |  |  | T-024/25 | 2025-01-16 | 14-Feb-2025 | 2412-2413-NPCC-T-08222
| PIPELINE FLOODING, GAUGING, HYDROTESTING AND WET LAY-UP PROCEDURE | 2412-2413-PP-OF-040
| GROUTING PROCEDURE | 2412-2413-PP-OF-043
| RIGID PIPELINE INSTALLATION MANUAL – 48” PIPELINE | 2412-2413-PP-OF-064 |  | A |  |  | T-320/24 | 2024-07-11 | 2024-08-07 | 2412-2413-NPCC-T-06495 | 2024-08-19 | CPD-14244-SA-T-1991-24 | 04 - Action-Process
|  |  |  | B |  |  | T-384/24 | 2024-08-26 | 2024-08-29 | 2412-2413-NPCC-T-06736 | 2024-09-10 | CPD-14244-SA-T-2186-24 | 02 - Review & Comments
|  |  |  | 00 |  |  | T-426/24 | 2024-09-13 | 2024-09-17 | 2412-2413-NPCC-T-06925 | 2024-09-18 | CPD-14244-SA-T-2257-24 | 06 - No Objection
|  |  |  | 00A |  |  | T-500/24 | 2024-10-10 | 10-Oct-2024 | 2412-2413-NPCC-T-07184
|  |  |  | 00B |  |  | T-582/24 | 2024-11-05
| ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | 2412-2413-PP-OF-065 |  | A |  |  | T-248/23 | 2023-08-21 | 2023-11-15 | 2412-2413-NPCC-T-03693 | 2023-12-26 | CPD-14244-SA-T-3079-23 | 06 - No Objection
|  |  |  | 00 |  |  | T-574/24 | 2024-12-04 | 2024-12-07 | 2412-2413-NPCC-T-07732
|  |  |  | 00A |  |  | T-084/25 | 2025-03-01 | 2025-03-06 | 2412-2413-NPCC-T-08358 | 2025-03-19 | CPD-14244-SA-T-0651-25 | 06 - No Objection
| SPM PILES AND CHAIN INSTALLATION PROCEDURE | 2412-2413-PP-OF-XXX
| SPM HOSES INSTALALTION PROCEDURE | 2412-2413-PP-OF-XXX
| RIGID PIPELINE INSTALLATION PROCEDURE – 56” PIPELINE | 2412-2413-PP-OF-087 |  | A1 |  |  | T-428/24 | 2024-09-13
|  |  |  | A |  |  | T-489/24 | 2024-10-03 | 2024-10-11 | 2412-2413-NPCC-T-07201 | 2024-10-21 | CPD-14244-SA-T-2548-24 | 04 - Action-Process
|  |  |  | B |  |  | T-547/24 | 2024-11-09 | 11-Nov-2024 | 2412-2413-NPCC-T-07494 | 2024-11-18 | CPD-14244-SA-T-2782-24 | 06 - No Objection
|  |  |  | 00 |  |  | T-572/24 | 2024-12-01 | 04-Dec-2024 | 2412-2413-NPCC-T-07693
|  |  |  | 00A |  |  | T-144/25 | 2025-04-14 | 2025-04-29 | 2412-2413-NPCC-T-08797 | 2025-05-01 | CPD-14244-SA-T-1119-25 | 04 - Action-Process
| CRANE DEMOLITION PROCEDURE | 2412-2413-PP-OF-089 |  | A1 |  |  | T-481/24 | 2024-09-30
|  |  |  | A |  |  | T-518/24 | 2024-10-22 | 2024-10-23 | 2412-2413-NPCC-T-07313 | 2024-10-29 | CPD-14244-SA-T-2622-24 | 04 - Action-Process
|  |  |  | B |  |  | T-549/24 | 2024-11-14 | 2024-11-17 | 2412-2413-NPCC-T-07560 | 2024-12-09 | CPD-14244-SA-T-2958-24 | 06 - No Objection
| METHOD STATEMENT FOR RETRIEVAL OF SPM ANCHOR PILE AP#6 | 2412-2413-PP-OF-091 |  | A |  |  | T-041/25 | 2025-01-24 | 07-Feb-2025 | 2412-2413-NPCC-T-08173
|  |  |  | B |  |  | T-182/25 | 2025-05-20 | 2025-05-21 | 2412-2413-NPCC-T-08993 | 2025-05-26 | CPD-14244-SA-T-1296-25 | 02 - Review & Comments
|  |  |  | C |  |  | T-221/25 | 2025-05-28 | 2025-05-29 | 2412-2413-NPCC-T-09039 | 2025-06-16 | CPD-14244-SA-T-1498-25 | 04 - Action-Process
| METHOD STATEMENT FOR RETRIEVAL OF SPM ANCHOR PILE AP#6 | 2412-2413-PP-OF-096 |  | A |  |  | T-101/25 | 2025-03-10 | 2025-03-12 | 2412-2413-NPCC-T-08401 | 2025-03-12 | 2412-2413-NPCC-T-08401 | 04 - Action-Process
|  |  |  | 00 |  |  | T-508/25 | 2025-10-03 | 2025-10-03 | 2412-2413-NPCC-T-09890 | 2025-10-08 | CPD-14244-SA-T-2330-25 | 06 - No Objection
| METHOD STATEMENT FOR SPM BUOY HOOK-UP | 2412-2413-PP-OF-098 |  | A |  |  | T-169/25 | 2025-06-12 | 2025-06-13 | 2412-2413-NPCC-T-09126 | 2025-07-23 | CPD-14244-SA-T-1800-25 | 04 - Action-Process | 2025-06-13 | 2412-2413-PMT-MWS-T-0019
|  |  |  | B |  |  | T-510/25 | 2025-10-05 | 2025-10-06 | 2412-2413-NPCC-T-09899
| ANCHOR HANDLING PROCEDURE FOR UMM SHAIF | 2412-2413-PP-OF-100 |  | A |  |  | T-204/25 | NOT ISSUED
|  |  |  | B |  |  | T-230/25 | NOT ISSUED
|  |  |  | C |  |  | T-251/25 | NOT ISSUED
| WINCHES LOAD TEST PROCEDURE FOR GOGAS-255 BARGE | 2412-2413-PP-OF-101 |  | 0 |  |  | T-355/24 | 2024-08-08 |  | NOT ISSUED TO CLIENT
| METHOD STATEMENT FOR SPM SUBMARINE AND FLOATING HOSES INSTALLATION | 2412-2413-PP-OF-106 |  | A1
|  |  |  | A |  |  | T-467/25 | 2025-09-11 | 2025-09-11 | 2412-2413-NPCC-T-09773 | 2025-10-31 | CPD-14244-SA-T-2443-25 | 01 - Information
|  |  |  | 00 |  |  | T-555/25 | 2025-10-31 | 2025-11-04 | 2412-2413-NPCC-T-10057
| ANCHOR HANDLING AND MOORING PROCEDURE FOR CHUANG LI | 2412-2413-PP-OF-116 |  | A |  |  | T-046/26 | CANCELLED
|  |  |  | A |  |  | T-075/26 | NOT ISSUED

## Setup Plans & Anchor Patterns
NMDC DOC. No.: MDR-001
CRPO #86 FOR JAFURAH DEVELOPMENT PROGRAM
|  | NMDC PROJECT NO. 2412-2413 | [11 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ARAMCO OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | REF | DATE | REF | DATE | CODE
| DELMA-2000 DP SETUP DURING NEW JOP EXTENSION JACKET INSTALLATION | 2412-2413-AP-0001
| DELMA-2000 DP SETUP DURING DURING 48" PIPELAY (SPM-37A) FROM JOP TO SSVS | 2412-2413-AP-0002
| DLS-4200 DURING 56IN PL START UP AT JOP | 2412-2413-AP-0003 |  | B |  |  | T-456/24 | 2024-09-23
| DELMA-2000 DP SETUP DURING DURING 48" PIPELAY (SPM-37A) FROM SSVS TO SPM-37 | 2412-2413-AP-0004
| DLS-4200 AP DURING 56INCH SECTION-1 FROM SHORE TO JOP | 2412-2413-AP-0005 |  | A |  |  | T-456/24 | 2024-09-23
| ANCHOR PATTERN FOR BARGE DLS-4200 DURING SHORE PULL AND PIPELAY OF NEW 56" CLS26 PIPELINE FROM NEW JUAYMAH ONSHORE TANK FARM TO SSVS LOCATION | 2412-2413-AP-0006
| ANCHOR PATTERN FOR BARGE DLS-4200 DURING SHORE PULL AND PIPELAY OF NEW 56" CLS26 PIPELINE FROM NEW JOP PLATFORM LOCATION TO SSVS LOCATION | 2412-2413-AP-0007
| ANCHOR PATTERN FOR BARGE DLS-4200 DURING NEW JOP EXTENSION TOPSIDE INSTALLATION | 2412-2413-AP-0008
| CCC-MARITIME-2 DP SET-UP PLAN DURING TEMP SUPPORT AND MATTRESS INST 56IN SECTTION-1 | 2412-2413-AP-0034 |  | A |  |  | T-456/24 | 2024-09-23
| SAFEEN PRINCE SET-UP PLAN DURING SEABED SURVEY AT JOP | 2412-2413-DP-0001 |  | A |  |  | T-308/22 | 2022-08-02
| AQUA JACK -1 SETUP PLAN DURING SEABED SURVEY AT JOP | 2412-2413-DP-0002 |  | A |  |  | T-309/22 | 2022-08-03
|  |  |  | B |  |  | T-319/22 | 2022-08-08
| HUDHUD SET-UP PLAN DURING GEO-PHYSICAL SURVEY AT JUAYMAH FIELD | 2412-2413-DP-0003
| OSPREY SET-UP PLAN DURING GEO-PHYSICAL SURVEY AT JUAYMAH FIELD | 2412-2413-DP-0004
| MUTAWA-401 SET-UP PLAN DURING GEO-TECHNICAL SURVEY AT JUAYMAH FIELD | 2412-2413-DP-0005
| QMS POSEIDON SET-UP PLAN DURING ROV SURVEY AT CROSSING LOCATION | 2412-2413-DP-0006
| AQUA JACK SETUP PLAN AT BH LOCATIONS (SMT-BH-06 TO SMT-BH-11) | 2412-2413-DP-0007
| DELMA-2000 SETUP DURING NEW JOP EXTENSION JACKET INSTALLATION | 2412-2413-DP-0008
| MEO GALAXY SETUP AT JOP PLATFORM | 2412-2413-DP-0009
| DYNAMICALLY POSITIONED VESSEL SET-UP FOR 48" SPOOLS (SPM-37A) INSTALLATION (5 nos) AT SSVS LOCATION | 2412-2413-DP-0010
| DYNAMICALLY POSITIONED VESSEL SET-UP FOR 48" SPOOLS (SPM-37B) INSTALLATION (4 nos) AT SSVS LOCATION | 2412-2413-DP-0011
| DYNAMICALLY POSITIONED VESSEL SET-UP FOR 56" SPOOLS (8 nos) INSTALLATION AT SSVS LOCATION | 2412-2413-DP-0012
| DYNAMICALLY POSITIONED VESSEL SET-UP FOR 48" SPOOLS (SPM-37A) INSTALLATION (5 nos) AT SPM-37 LOCATION | 2412-2413-DP-0013
| SHUJAA-2000 SET-UP DURING SPM AP#1 INSTALLATION (SPMA-01) | 2412-2413-DP-0014 |  | A |  |  | T-277/24 | 2024-06-27
|  |  |  | B |  |  | T-287/24 | 2024-07-01
| DYNAMICALLY POSITIONED VESSEL SET-UP FOR ANCHOR PILE INSTALLATION (6 nso) AT SPM-37 LOCATION | 2412-2413-DP-0015
| SHUJAA-2000 SET-UP DURING SPM AP#2 INSTALLATION (SPMA-02) | 2412-2413-DP-0016 |  | A |  |  | T-277/24 | 2024-06-27
|  |  |  | B |  |  | T-287/24 | 2024-07-01
| SHUJAA-2000 SET-UP DURING SPM AP#3 INSTALLATION (SPMA-03) | 2412-2413-DP-0017 |  | A |  |  | T-277/24 | 2024-06-27
|  |  |  | B |  |  | T-287/24 | 2024-07-01
| SHUJAA-2000 SET-UP DURING SPM AP#4 INSTALLATION (SPMA-04) | 2412-2413-DP-0018 |  | A |  |  | T-277/24 | 2024-06-27
|  |  |  | B |  |  | T-287/24 | 2024-07-01
| SHUJAA-2000 SET-UP DURING SPM AP#5 INSTALLATION (SPMA-05) | 2412-2413-DP-0019 |  | A |  |  | T-277/24 | 2024-06-27
|  |  |  | B |  |  | T-287/24 | 2024-07-01
| SHUJAA-2000 SET-UP DURING SPM AP#6 INSTALLATION (SPMA-06) | 2412-2413-DP-0020 |  | A |  |  | T-277/24 | 2024-06-27
|  |  |  | B |  |  | T-287/24 | 2024-07-01
| SHUJA-2000 DP SETUP DURING NEW JOP EXTENSION JACKET INSTALLATION | 2412-2413-DP-0021 |  | A |  |  | T-280/24 | 2024-06-28
| SHUJA-2000 DP SETUP AT EXISTING JOP DURING BOAT LANDING DEMOLITION | 2412-2413-DP-0022 |  | A |  |  | T-280/24 | 2024-06-28
| SHUJA-2000 DP SET-UP DURING SLEEPER AND MATTRESS INSTAALLATION | 2412-2413-DP-0023 |  | A |  |  | T-264/24 | 2024-06-14
|  |  |  | B |  |  | T-279/24 | 2024-06-28
|  |  |  | C |  |  | T-288/24 | 2024-07-01
| SHUJAA-2000 DP SET-UP DURING PLEM INSTALLATION | 2412-2413-DP-0024 |  | A |  |  | T-278/24 | 2024-06-28
|  |  |  | B |  |  | T-287/24 | 2024-07-01
| SHUJAA-2000 DP SET-UP DURING SSVS INSTALLATION | 2412-2413-DP-0025 |  | A |  |  | T-278/24 | 2024-06-28
| DYNAMICALLY POSITIONED VESSEL SET-UP FOR CROSSING CR-04 INSTALLATION AT 48"-SPM-37B PIPELINE | 2412-2413-DP-0026
| DYNAMICALLY POSITIONED VESSEL SET-UP FOR CROSSING CR-01 INSTALLATION AT 56"-CLS-26 PIPELINE | 2412-2413-DP-0027
| DYNAMICALLY POSITIONED VESSEL SET-UP FOR CROSSING CR-02 INSTALLATION AT 56"-CLS-26 PIPELINE | 2412-2413-DP-0028
| DYNAMICALLY POSITIONED VESSEL SET-UP FOR CROSSING CR-01 INSTALLATION AT 15kV PC FROM SHORE TO NEW JOP | 2412-2413-DP-0029
| DYNAMICALLY POSITIONED VESSEL SET-UP FOR CROSSING CR-02 INSTALLATION AT 15kV PC FROM SHORE TO NEW JOP | 2412-2413-DP-0030
| CCC-MARITIME-2 DP SET-UP PLAN DURING TEMP SUPPORT AND MATTRESS INST SBM 37-A-SECTION-1 | 2412-2413-DP-0032 |  | A |  |  | T-456/24 | 2024-09-23
| CCC-MARITIME-2 DP SET-UP PLAN DURING TEMP SUPPORT AND MATTRESS INST SBM 37-B-SECTION-1 | 2412-2413-DP-0033 |  | A |  |  | T-456/24 | 2024-09-23
| AQUA JACK-1 PASSAGE PLAN FROM RAS TANURA ANCHORAGE TO JOP EXTENSION | 2412-A0-001 |  | 3 |  |  | T-313/22 | 2022-08-04
| VESSEL PASSAGE PLAN FROM RAS TANURA ANCHORAGE TO JOP EXTENSION | 2412-A0-021 |  | 2
| VESSEL PASSAGE PLAN FROM QATIF ANCHORAGE TO JOP EXTENSION | 2412-A0-028 |  | 1
| VESSEL PASSAGE PLAN FROM QATIF ANCHORAGE TO SHALLOW WATER AREA | 2412-A0-030 |  | 1 |  |  | T-456/24 | 2024-09-23
| PILOT BOAT APPROACH | 2412-A0-035 |  | 1 |  |  | T-456/24 | 2024-09-23

## Sketches
NMDC DOC. No.: MDR-001
CRPO #86 FOR JAFURAH DEVELOPMENT PROGRAM
|  | NMDC PROJECT NO. 2412-2413 | [6 empty] | REVISION : | 0
|  | OFFSHORE sketches | [6 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| DELMA-2000 DP SET-UP DURING TEMPORARY SUPPORT AND MATTRESS INSTALLATION | 2412-2413-DP-0030 |  | C |  |  | 2024-08-27 | DRH/SSB
| DELMA-2000 DP SET-UP DURING TEMPORARY SUPPORT AND MATTRESS INSTALLATION | 2412-2413-DP-0031 |  | C |  |  | 2024-08-27 | DRH/SSB
| DELMA-2000 DP SET-UP DURING TEMPORARY SUPPORT AND MATTRESS INSTALLATION | 2412-2413-DP-0030 |  | D |  |  | 2024-08-31 | DAR/SSB
| DELMA-2000 DP SET-UP DURING TEMPORARY SUPPORT AND MATTRESS INSTALLATION | 2412-2413-DP-0031 |  | D |  |  | 2024-08-31 | DAR/SSB
| NAVIGATION BUOY AROUND SPM L0CATION | 2412-A3-015 |  | A |  |  | 2024-08-28 | SS/SJD
| DLS-4200 ANCHOR PATTERN DURING 56'' PIPELINE START-UP AT JOP | 2412-2413-AP-0003 |  | B |  |  | 2024-09-11 | SS/KM
| 56'' PIPELINE SECTION-1 DLS-4200 ANCHOR NO GO ZONE AREA ON SUR CHART | 2412-A0-033 |  | 0 |  |  | 2024-09-12 | EJJ/SJD
| 56'' PIPELINE SECTION-2 DLS-4200 ANCHOR NO GO ZONE AREA ON SUR CHART | 2412-A0-034 |  | 0 |  |  | 2024-09-12 | EJJ/SJD
| PILOT BOAT APPROACH | 2412-A0-035 |  | 0 |  |  | 2024-09-18 | EJJ/SJD
| (DELMA-2000 DP SET-UP PLAN during Sleepers Installation) | 2412-2413-DP-0035 |  | A |  |  | 2024-09-30 | VKS/SJD
| (DELMA-2000 Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-039 |  | 0 |  |  | 2024-10-01 | VKS/SJD
| 2412-A0-040_R0 (DELMA-2000 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-040 |  | 0 |  |  | 2024-10-01 | VKS/SJD
| (SHUJAA-2000 Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-041 |  | 0 |  |  | 2024-10-03 | EJJ/SSB
| (SHUJAA-2000 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-042 |  | 0 |  |  | 2024-10-03 | EJJ/SSB
| (Navigation Buoy around SPM location) | 2412-A0-043 |  | 1 |  |  | 2024-10-07 | VKS/SSB
| (DSV PICASSO Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-044 |  | 0 |  |  | 2024-11-06 | EJJ/SJD
| (DSV PICASSO Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-045 |  | 0 |  |  | 2024-11-06 | EJJ/SJD
| (Anchor AP3 installation sequence) | 2412-A3-021 |  | 0 |  |  | 2024-11-12 | EJJ/SSB
| (DSV PICASSO Passage Plan from Ras Tanura Anchorage to PLEM) | 2412-A0-047 |  | 0 |  |  | 2024-11-19 | EJJ/SJD
| (DSV PICASSO Passage Plan from QATIF ANCHORAGE to PLEM) | 2412-A0-048 |  | 0 |  |  | 2024-11-19 | EJJ/SJD
| ( Shujaa 2000 Set Up for Spool Installation ) | 2412-2413-DP-0044 |  | B |  |  | 2024-12-19 | VKS/SJD
| ( Shujaa 2000 Set Up for Spool Installation at SSVS ) | 2412-2413-DP-0045 |  | B |  |  | 2024-12-19 | VKS/SJD
| (SHUJAA 2000 SET-UP for SPOOL INSTALLATION AT PLEM ) | 2412-2413-DP-0047 |  | B |  |  | 2024-12-19 | VKS/SJD
| DP SET-UP PLAN DURING SSVS INSTALLATION | 2412-2413-DP-0025 |  | C |  |  | 2024-12-31 | EJJ/SSB
| (VESSEL Passage Plan from Ras Tanura Anchorage to JUAYMAH FIELD) | 2412-A0-012 |  | 5 |  |  | 2025-01-15 | VKS/KM
| 2412-2413-AP-0007_Rev-A (DLS-4200 DURING Spool Installation at JOP) | 2412-2413-AP-0007 |  | A |  |  | 2025-01-15 | EJJ/SJD
| 2412-2413-DP-0041-1 & 2_Rev-A( Oriental Dragon Set Up for Spool Installation) | 2412-2413-DP-0041 |  | A |  |  | 2025-01-15 | EJJ/SJD
| 2412-2413-DP-0042-1 TO 3_Rev-A(Oriental Dragon Set Up for Spool Installation at SSVS) | 2412-2413-DP-0042 |  | A |  |  | 2025-01-15 | EJJ/SJD
| 2412-2413-DP-0043_Rev-A(Oriental Dragon Set Up for Spool Installation at PLEM) | 2412-2413-DP-0043 |  | A |  |  | 2025-01-16 | EJJ/SJD
| (ORIENTAL DRAGON SET-UP for Hydrotesting) | 2412-2413-DP-0050 |  | B |  |  | 2025-01-21 | EJJ/SJD
| 2412-2413-DP-0049-1 TO 5_Rev-B (ORIENTAL DRAGON SET-UP for Freespan correction-Flooding, Cleaning, Gauging) | 2412-2413-DP-0049 |  | B |  |  | 2025-01-21 | EJJ/SJD
| 2412-2413-DP-0028-01 TO 03_Rev-F (DELMA-2000 DP SET-UP PLAN during 48 INCH PIPELAYING SBM 37-B-SECTION-1) | 2412-2413-DP-0028 |  | F |  |  | 2025-01-22 | EJJ/SJD
| 2412-2413-DP-0029-01 TO 03_Rev-F (DELMA-2000 DP SET-UP PLAN during 48 INCH PIPELAYING SBM 37-A-SECTION-1) | 2412-2413-DP-0029 |  | F |  |  | 2025-01-22 | EJJ/SJD
| 2412-A0-069_R1(SHUJAA Set up during DMA installation) | 2412-A0-069 |  | 1 |  |  | 2025-01-22 | EJJ/SJD
| (Vessel position during Anchor Chain pre-tension operation) | 2412-A3-025 |  |  |  |  | 2025-01-22 | VKS/SSB
| ( Oriental Dragon Set Up for Spool Installation @ JOP) | 2412-2413-DP-0041 |  | B |  |  | 2025-01-23 | EJJ/SJD
| (DLS-4200 DURING Spool Installation at JOP) | 2412-2413-AP-0007 |  | B |  |  | 2025-01-28 | EJJ/SJD
| (Oriental Dragon Set Up for Spool Installation at PLEM) | 2412-2413-DP-0043 |  | B |  |  | 2025-01-29 | EJJ/SJD
| 2412-A0-021_R7 (VESSEL Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-021 |  | 7 |  |  | 2024-01-30 | EJJ/SJD
| 2412-A0-028_R6 (VESSEL Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-028 |  | 6 |  |  | 2024-01-30 | EJJ/SJD
| 2412-A0-049_R2(DSV ORIENTAL DRAGON Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-049 |  | 2 |  |  | 2024-01-30 | EJJ/SJD
| 2412-A0-050_R3(DSV ORIENTAL DRAGON Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-050 |  | 3 |  |  | 2024-01-30 | EJJ/SJD
| 2412-A0-051_R2(DSV ORIENTAL DRAGON Passage Plan from Ras Tanura Anchorage to PLEM) | 2412-A0-051 |  | 2 |  |  | 2024-01-30 | EJJ/SJD
| 2412-A0-052_R2(DSV ORIENTAL DRAGON Passage Plan from QATIF ANCHORAGE to PLEM) | 2412-A0-052 |  | 2 |  |  | 2024-01-30 | EJJ/SJD
| 2412-A0-058_R2(SHUJAA-2000 Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-058 |  | 2 |  |  | 2024-01-30 | EJJ/SJD
| 2412-A0-059_R2(SHUJAA-2000 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-059 |  | 2 |  |  | 2024-01-30 | EJJ/SJD
| 2412-A0-060_R1(SHUJAA-2000 Passage Plan from Ras Tanura Anchorage to PLEM) | 2412-A0-060 |  | 1 |  |  | 2024-01-30 | EJJ/SJD
| 2412-A0-061_R1(SHUJAA-2000 Passage Plan from QATIF ANCHORAGE to PLEM) | 2412-A0-061 |  | 1 |  |  | 2024-01-30 | EJJ/SJD
| (DLS-4200 DURING Spool Installation at JOP) | 2412-2413-AP-0007 |  | B |  |  | 2025-01-31 | EJJ/SJD
| (DLS-4200 DURING Spool Installation at JOP) | 2412-2413-AP-0008 |  | B |  |  | 2025-01-31 | EJJ/SJD
| (DLS-4200 DURING Spool Installation at JOP) | 2412-2413 |  | C |  |  | 2025-02-04 | EJJ/SJD
| (Anchor pile AP6 Diamond wire cutting and recovery) | 2412-A3-031 |  | 0 |  |  | 2025-03-08 | EJJ
| (VESSEL Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-028 |  | 7 |  |  | 2025-03-13 | EJJ
| (CCC-MARITIME-2 Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-037 |  | 2 |  |  | 2025-03-13 | EJJ
| (CCC-MARITIME-2 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-038 |  | 3 |  |  | 2025-03-13 | EJJ
| (SHUJAA-2000 Passage Plan from QATIF ANCHORAGE to PLEM) | 2412-A0-061 |  | 2 |  |  | 2025-03-13 | EJJ
| (DSV ORIENTAL DRAGON Passage Plan from Ras Tanura Anchorage to PLEM) | 2412-A0-051 |  | 3 |  |  | 2025-04-09 | EJJ
| (DSV ORIENTAL DRAGON Passage Plan from QATIF ANCHORAGE to PLEM) | 2412-A0-052 |  | 3 |  |  | 2025-04-09 | EJJ
| (ORIENTAL DRAGON set-up during cutiing of anchor pile & plem pile @ SPM-37) | 2412-2413-DP-0056 |  | A |  |  | 2025-04-10 | EJJ
| (DSV ORIENTAL DRAGON Passage Plan from Ras Tanura Anchorage to PLEM) | 2412-A0-051 |  | 3 |  |  | 2025-04-10 | EJJ
| (DSV ORIENTAL DRAGON Passage Plan from QATIF ANCHORAGE to PLEM) | 2412-A0-052 |  | 3 |  |  | 2025-04-10 | EJJ
| (ORIENTAL DRAGON set-up during cutiing of anchor pile & plem pile @ SPM-37) | 2412-2413-DP-0056 |  | B |  |  | 2025-04-14 | EJJ
| DLS-4200 DURING Spool Installation at JOP 7 SSVS_1 TO10 | - |  |  |  |  | 2025-04-21 | EJJ
| (DLS-4200 DURING Spool Installation at JOP & SSVS) | 2412-2413-AP-0009 |  | B |  |  | 2025-05-20 | EJJ
| 2412-2413-AP-0006-1 TO 3 _Rev-E (UMM SHAIF AP DURING CABLE LAYING From Shore to JOP) | 2412-2413-AP-0006- |  | E |  |  | 2025-05-28 | SKV
| 2412-A0-062-1 TO 9_R3(UMM SHAIF SET-UP SEQUENCE CABLE LAYING START UP) | 2412-A0-062 |  | 3 |  |  | 2025-05-28 | SKV
| (CCC-MARITIME-2 Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-037 |  | 4 |  |  | 2025-06-03 | EJJ
| (CCC-MARITIME-2 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-038 |  | 5 |  |  | 2025-06-03 | EJJ
| 2412-2413-AP-0006-1 TO 3 _Rev-F (UMM SHAIF AP DURING CABLE LAYING From Shore to JOP) | 2412-2413-AP-000 |  | F |  |  | 2025-06-10 | SKV
| 2412-2413-DP-0058 _Rev-A (UMM SHAIF DP DURING WET STORAGE OF ANCHORS) | 2412-2413-DP-0058 |  | A |  |  | 2025-06-10 | SKV
| 2412-A0-053_R3(15 kV CABLE LAYING UMM SHAIF Anchor No Go Zone Area on SUR Chart) | 2412-A0-053 |  | 3 |  |  | 2025-06-10 | SKV
| 2412-A0-057_R5 (UMM SHAIF Passage Plan from QATIF ANCHORAGE to Shallow water area) | 2412-A0-057 |  | 5 |  |  | 2025-06-10 | SKV
| 2412-A0-062-1 TO 9_R4(UMM SHAIF SET-UP SEQUENCE CABLE LAYING START UP) | 2412-A0-062 |  | 4 |  |  | 2025-06-10 | SKV
| (CCC-MARITIME-2 SETUP DURING PREPARATORY WORKS AT JOP) | 2412-2413-DP-0059 |  | A |  |  | 2025-06-11 | SKV
| 2412-2413-AP-0006-1 TO 3 _Rev-G (UMM SHAIF AP DURING CABLE LAYING From Shore to JOP) | 2412-2413-AP-0006 |  | G |  |  | 2025-06-12 | SKV
| 2412-2413-DP-0059 _Rev-B(CCC-MARITIME-2 SETUP DURING PREPARATORY WORKS AT JOP) | 2412-2413-DP-0059 |  | B |  |  | 2025-06-12 | SKV
| 2412-A0-062-1 TO 9_R5(UMM SHAIF SET-UP SEQUENCE CABLE LAYING START UP) | 2412-A0-062 |  | 5 |  |  | 2025-06-12 | SKV
| 2412-2413-DP-0060_Rev-A (SHUJAA-2000 SETUP DURING GRID-C SEADECK WALKWAY INSTALLATION AT JOP) | 2412-2413-DP-0060 |  | A |  |  | 2025-06-25 | SKV
| 2412-A0-058_R3(SHUJAA-2000 Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-058 |  | 3 |  |  | 2025-06-25 | SKV
| 2412-A0-059_R4(SHUJAA-2000 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-059 |  | 4 |  |  | 2025-06-25 | SKV
| (UMM SHAIF DP DURING JB INSTALLATION) | 2412-2413-DP-006 |  | A |  |  | 2025-07-01 | SKV
| ( Shujaa 2000 Set Up for Spool Installation at JOP) | 2412-2413-DP-0044 |  | E |  |  | 2025-07-11 | EJJ
| ( Shujaa 2000 Set Up for Spool Installation at SSVS ) | 2412-2413-DP-0045 |  | D |  |  | 2025-07-11 | EJJ
| (SHUJAA-2000 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-059 |  | 5 |  |  | 2025-07-15 | EJJ
| (UMM SHAIF Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-055 |  | 6 |  |  | 2025-07-16 | EJJ
| (UMM SHAIF Passage Plan from QATIF ANCHORAGE to Shallow water area) | 2412-A0-057 |  | 6 |  |  | 2025-07-16 | EJJ
| 2412-2413-DP-0044-1 TO 2_Rev-F( Shujaa 2000 Set Up for Spool Installation at JOP) | 2412-2413-DP-0044 |  | F |  |  | 2025-07-19 | EJJ
| 2412-2413-DP-0045-1 TO 3_Rev-E( Shujaa 2000 Set Up for Spool Installation at SSVS ) | 2412-2413-DP-0045 |  | E |  |  | 2025-07-19 | EJJ
| 2412-2413-DP-0074-1 TO 3 _Rev-A (CCC MARITIME-2 Setup during Shallow water marker installation) | 2412-2413-DP-0074 |  | A |  |  | 2025-09-10 | SKV
| 2412-A0-078_R0(CCC MARITIME-2 Passage Plan from QATIF ANCHORAGE to Shallow water area) | 2412-A0-078 |  | 0 |  |  | 2025-09-10 | SKV
| 2412-A0-079_R0 (CCC MARITIME-2 Passage Plan from RAS TANURA ANCHORAGE to Shallow water area) | 2412-A0-079 |  | 0 |  |  | 2025-09-10 | SKV
| 2412-2413-DP-0065_Rev-B (CCC Wedad Aletheia Set-up Plan during Seadeck Walkway Installation) | 2412-2413-DP-0065 |  | B |  |  | 2025-09-10 | SKV
| 2412-2413-DP-0065_Rev-C( CCC Wedad Aletheia Set-up Plan during Seadeck Walkway Installation) | 2412-2413-DP-0065 |  | C |  |  | 2025-09-13 | SKV
| (Oriental Dragon Setup during SPM-37 Installation) | 2412-2413-DP-0062 |  | D |  |  | 2025-09-13 | SKV
| CONNECTION OF PULL THROUGH WIRE TO END LINK OF THE CHAIN BY DIVER | 2412-A3-036 |  | A |  |  | 2025-09-13 | SKV
| (VESSEL Passage Plan from Ras Tanura Anchorage to JUAYMAH FIELD) | 2412-A0-012 |  | 6 |  |  | 2025-09-30 | EJJ
| (VESSEL Passage Plan from QATIF Anchorage to Trench location) | 2412-A0-024 |  | 1 |  |  | 2025-10-01 | EJJ
| (Chaung Li SET-UP DECK INSTALLATION AT JOP EXTENSION) | 2412-2413-AP-0011 |  | A |  |  | 2025-10-16 | SKV
| ( CCC-MARITIME-2 Setup during Shroud Installation) | 2412-2413-DP-0079 |  | A |  |  | 2025-10-21 | SKV
| (WADAD ALETHEIA ILI for the newly installed pipelines of 56”and 48” from JOP to PLEM) | 2412-2413-DP-0080 |  | A |  |  | 2025-10-21 | EJJ
| (CCC WADAD ALETHEIA Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-076 |  | 1 |  |  | 2025-10-21 | EJJ
| ( CCC-MARITIME-2 Setup during Shroud Installation) | 2412-2413-DP-0079 |  | B |  |  | 2025-10-27 | SKV
| (CCC MARITIME-2 Passage Plan from QATIF ANCHORAGE to PLEM) | 2412-A0-081 |  | 1 |  |  | 2025-10-27 | SKV
| (WADAD ALETHEIA ILI for the newly installed pipelines of 56”and 48” from JOP to PLEM) | 2412-2413-DP-0080 |  | B |  |  | 2025-10-27 | EJJ
| ( CCC WADAD ALETHEIA Setup during Danger Buoy Installation at SSVS) | 2412-2413-DP-0081 |  | A |  |  | 2025-10-28 | SKV
| (CCC WADAD ALETHEIA SET-UP PLAN DURING 48 INCH SPOOL INSTALLATION AT JOP) | 2412-2413-DP-0070 |  | C |  |  | 2025-10-30 | SKV
| (CCC WADAD ALETHEIA SET-UP PLAN DURING 56 INCH SPOOL INSTALLATION AT JOP) | 2412-2413-DP-0071 |  | C |  |  | 2025-10-30 | SKV
| (CCC WADAD ALETHEIA SET-UP PLAN DURING CONCRETE SLAB INSTALLATION ON 48 INCH SPOOL AT JOP) | 2412-2413-DP-0082 |  | B |  |  | 2025-11-03 | SKV
| (CCC WADAD ALETHEIA SET-UP PLAN DURING CONCRETE SLAB INSTALLATION ON 56 INCH SPOOL AT JOP) | 2412-2413-DP-0083 |  | B |  |  | 2025-11-03 | SKV
| 2412-2413-DP-0084_Rev-A( CCC Wadad Aletheia Set-up Plan during EDG Module Installation) | 2412-2413-DP-0084 |  | A |  |  | 2025-11-11 | SKV
| 2412-2413-DP-0085_Rev-A (CCC MARITIME-II SET-UP PLAN DURING MATTRESS INSTALLATION DURING WALKWAY INSTALLATION AT JOP) | 2412-2413-DP-0085 |  | A |  |  | 2025-11-18 | EJJ
| 2412-2413-DP-0065_Rev-D( CCC Wedad Aletheia Set-up Plan during Seadeck Walkway Installation) | 2412-2413-DP-0065 |  | D |  |  | 2025-11-20 | EJJ
| 2412-2413-AP-0011_Rev-B(ChuangLi SET-UP DECK INSTALLATION AT JOP EXTENSION) | 2412-2413-AP-0011 |  | B |  |  | 2025-11-21 | SKV
| 2412-A0-084-1 TO 8_R0(ChuangLi Setup sequence during JOP DECK EXTNESION Installation) | 2412-A0-084 |  | 0 |  |  | 2025-11-21 | SKV
| 2412-A0-085_R0(ChuangLi Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-085 |  | 0 |  |  | 2025-11-21 | SKV
| 2412-A0-086_R0(ChuangLi Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-086 |  | 0 |  |  | 2025-11-21 | SKV
| 2412-2413-DP-0065_Rev-E( CCC Wedad Aletheia Set-up Plan during Seadeck Walkway Installation) | 2412-2413-DP-0065 |  | E |  |  | 2025-12-03 | SKV
| 2412-2413-DP-0086_Rev-A( CCC Wedad Aletheia Set-up Plan during Seadeck Walkway Installation) | 2412-2413-DP-0086 |  | A |  |  | 2025-12-03 | SKV
| 2412-A0-038_R9(CCC-MARITIME-2 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-038 |  | 9 |  |  | 2025-12-03 | SKV
| 2412-A0-076_R3(CCC WADAD ALETHEIA Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-076 |  | 3 |  |  | 2025-12-03 | SKV
| 2412-2413-AP-0011_Rev-C(Chuang Li SET-UP DECK INSTALLATION AT JOP EXTENSION) | 2412-2413-AP-0011 |  | C |  |  | 2025-12-04 | SKV
| 2412-2413-DP-0065_Rev-E( CCC Wedad Aletheia Set-up Plan during East Seadeck Walkway Installation) | 2412-2413-DP-0065 |  | E |  |  | 2025-12-10 | SKV
| 2412-2413-DP-0086_Rev-A( CCC Wedad Aletheia Set-up Plan during West Seadeck Walkway Installation) | 2412-2413-DP-0086 |  | A |  |  | 2025-12-10 | SKV
| 2412-A0-038_R9(CCC-MARITIME-2 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-038 |  | 9 |  |  | 2025-12-10 | SKV
| 2412-A0-076_R3(CCC WADAD ALETHEIA Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-076 |  | 3 |  |  | 2025-12-10 | SKV
| 2412-2413-DP-0065_Rev-F( CCC Wedad Aletheia Set-up Plan during East Seadeck Walkway Installation) | 2412-2413-DP-0065 |  | F |  |  | 2025-12-18 | EJJ
| 2412-2413-AP-0012_Rev-A (SEP-450 SET-UP AT JOP for EDG Module Installation) | 2412-2413-AP-0012 |  | A |  |  | 2025-12-18 | EJJ
| 2412-2413-DP-0060_Rev-B (SEP-450 SETUP AT JOP) | 2412-2413-DP-0060 |  | B |  |  | 2025-12-19 | EJJ
| 2412-2413-AP-0011_Rev-C(Chuang Li SET-UP DECK INSTALLATION AT JOP EXTENSION) | 2412-2413-AP-0011 |  | C |  |  | 2025-12-19 | SKV
| 2412-2413-DP-0087-1 TO 2 _Rev-A (CCC WADAD ALETHEIA Setup during Concrete Sinker installation) | 2412-2413-DP-0087 |  | A |  |  | 2025-12-23 | SKV
| 2412-A0-087_R0(CCC WADAD ALETHEIA Passage Plan from QATIF ANCHORAGE to Shallow water area) | 2412-A0-087 |  | A |  |  | 2025-12-23 | SKV
| 2412-A0-088_R0(CCC WADAD ALETHEIA Passage Plan from Ras Tanura Anchorage to Shallow water area) | 2412-A0-088 |  | A |  |  | 2025-12-23 | SKV
| WET STORAGE OF SHALLOW WATER CONCRETE SINKER | 2412-A0-093 |  | 0 |  |  | 2026-01-15 | EJJ
| 2412-A0-084-01 TO 10_R0(ChuangLi Setup sequence during JOP DECK EXTNESION Installation) | 2412-A0-084 |  | 0 |  |  | 2026-01-20 | EJJ
| 2412-2413-AP-0011_Rev-C(Chuang Li SET-UP DECK INSTALLATION AT JOP EXTENSION) | 2412-2413-AP-0011 |  | C |  |  | 2026-01-20 | EJJ
| 2412-A0-081_R2(CCC MARITIME-2 Passage Plan from QATIF ANCHORAGE to PLEM) | 2412-A0-081 |  | 2 |  |  | 2026-02-11 | EJJ
| 2412-2413-DP-0089_Rev-A(CCC MARITIME-II Set-up at SPM-37 & PLEM-37 for Miscellaneous Activities) | 2412-2413-DP-0089 |  | A |  |  | 2026-02-12 | EJJ
| 2412-2413-DP-0060-1 TO 3_Rev-D (SEP-450 SETUP EDG MODULE INSTALLATION AND HOOK UP WORKS AT JOP) | 2412-2413-DP-0060 |  | D |  |  | 2026-03-31 | EJJ
| 2412-A0-082_R1(SEP-450 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-082 |  | 1 |  |  | 2026-03-31 | EJJ
| 2412-A0-083_R1(SEP-450 Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-083 |  | 1 |  |  | 2026-03-31 | EJJ
| 2412-A0-095_R0(SEP-450 SETUP DURING EDG MODULE INSTALLATION)_study | 2412-A0-095 |  | 0 |  |  | 2026-05-14 | EJJ
| 2412-2413-DP-0094_Rev-A (HEA AL MAQAM SETUP DURING HOOK UP WORKS AT JYMH CONTROL ROOM PLATFORM) | 2412-2413-DP-0094 |  | A |  |  | 2026-05-14 | SKV
| 2412-2413-DP-0093_Rev-A (HEA AL MAQAM SETUP DURING HOOK UP WORKS AT JYMH METERING PLATFORM) | 2412-2413-DP-0093 |  | A |  |  | 2026-05-14 | SKV
| 2412-2413-DP-0095_Rev-A(Zakher Pioneer Set-up during EDG support installation and Hook-up works) | 2412-2413-DP-0095 |  | A |  |  | 2026-05-18 | EJJ
| 2412-2413-DP-0095_Rev-A (AL SILA SETUP DURING HOOK UP WORKS AT JYMH METERING PLATFORM) | 2412-2413-DP-0095 |  | A |  |  | 2026-05-18 | SKV
| 2412-2413-DP-0096_Rev-A (AL SILA SETUP DURING HOOK UP WORKS AT JYMH CONTROL ROOM PLATFORM) | 2412-2413-DP-0096 |  | A |  |  | 2026-05-18 | SKV
| 2412-2413-DP-0107_Rev-A (RAWABI-608 SETUP DURING HOOK UP WORKS AT JYMH CONTROL ROOM PLATFORM) | 2412-2413-DP-0107 |  | A |  |  | 2026-08-17 | SKV
| 2412-A0-0102_R0(RAWABI-608 Passage Plan from QATIF ANCHORAGE to JOP EXTENSION) | 2412-A0-0102 |  | 0 |  |  | 2026-08-17 | SKV
| 2412-A0-0103_R0(RAWABI-608 Passage Plan from Ras Tanura Anchorage to JOP EXTENSION) | 2412-A0-0103 |  | 0 |  |  | 2026-08-17 | SKV
| 2412-2413-DP-0093-1 TO 2_Rev-A (SEP-450 SETUP DURING CONCRETE SLAB INSTALLATION AT JOP) | 2412-2413-DP-0093 |  | A |  |  | 2026-09-08 | SKV