## Installation Procedures
NMDC DOC. No.: MDR-001
EPC FOR REPLACEMENT OF TB-3 MOORING SYSTEM
|  | NMDC PROJECT NO. 2462 | [11 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2026-08-28
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| ANCHOR PILE INSTALLATION PROCEDURE | 2462-PP-OF-002 |  | A |  |  | T-306/23 | 2023-10-13
|  |  |  | 1 |  |  | T-307/23 | 2023-10-16 | 23-Oct-2023 | 2462-NPCC-AO-T-0015 | 2023-10-25 | PE-ZR&DAS-E0261-0004-23 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-344/23 | 2023-11-13 | 2023-11-06 | 2462-NPCC-AO-T-0032 | 2024-01-09 | PE-ZR&DAS-E0261-0018-24 | 1 - Approved | 2023-11-17 | 2462-NPCC-BW-T-0006
|  |  |  | 3 |  |  | T-205/24 | 2024-05-15 | 2024-05-20 | 2462-NPCC-AO-T-0069 | 2024-06-04 | PE-ZR&DAS-E0261-0027-24 | 3 - Reviewed with Comments
|  |  |  | 4 |  |  | T-274/24 | 2024-06-26 | 2024-07-12 | 2462-NPCC-AO-T-0088
|  |  |  | 5 |  |  | T-340/24 | 2024-07-26 | 2024-07-31 | 2462-NPCC-AO-T-0092
|  |  |  | 6 |  |  | T-358/24 | 2024-08-08 | 2024-08-14 | 2462-NPCC-AO-T-0098 | 2024-08-28 | PE-ZR&DAS-E0261-0036-24 | 1 - Approved
|  |  |  | 7 |  |  | T-213/25 | PMT | 2025-04-30 | 2462-NPCC-AO-T-0141 | 2025-05-30 | PE-ZR&DAS-E0261-0050-25 | 1 - Approved
|  |  |  | 8 |  |  | T-379/26 | 2026-08-28
| CHAIN LAYING PROCEDURE | 2462-PP-OF-003 | AD268-25-3-G-00204 | A |  |  | T-335/24 | 2024-07-25
|  |  |  | 1 |  |  | T-349/24 | 2024-08-02 | 2024-08-06 | 2462-NPCC-AO-T-0095
|  |  |  | 2 |  |  | T-362/24 | 2024-08-12 | 2024-08-14 | 2462-NPCC-AO-T-0099
|  |  |  | 3 |  |  | T-424/24 | 2024-09-12 | 13-Sep-2024 | 2462-NPCC-AO-T-0107 | 2024-10-03 | PE-ZR&DAS-E0261-0040-24 | 2 - Approved with Comments
|  |  |  | 4 |  |  | T-482/24 | 2024-10-01 | 03-Oct-2024 | 2462-NPCC-AO-T-0115 | 11-Oct-2024 | PE-ZR&DAS-E0261-0041-24 | 1 - Approved
|  |  |  | 5 |  |  | T-541/25 | 2025-10-22 | 2025-10-29 | 2462-NPCC-AO-T-0178 | 2025-11-17 | PE-ZR&DAS-E0261-0042-28 | 1 - Approved
|  |  |  | 6 |  |  | T-584/25 | 2025-11-20 | 2025-11-21 | 2462-NPCC-AO-T-0184
|  |  |  | 7 |  |  | T-380/26 | 2026-08-28
| METHOD STATEMENT FOR REMOVAL OF EXISTING CHAINS | 2462-PP-OF-005 | AD268-25-3-G-00205 | A |  |  | T-338/24 | 2024-07-26
|  |  |  | 1 |  |  | T-373/24 | 2024-08-17 | 2024-08-21 | 2462-NPCC-AO-T-0102 | 2024-09-10 | PE-ZR&DAS-E0261-0038-24 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-543/25 | 2025-10-22 | 2025-10-23 | 2462-NPCC-AO-T-0177 | 2025-11-17 | PE-ZR&DAS-E0261-0042-29 | 1 - Approved
|  |  |  | 5 |  |  | T-381/26 | 2026-08-28
| ANCHOR HANDLING PROCEDURE FOR GRAVITY ANCHORS BY HAMMER HEAD CRANE VESSEL & SEABED SURVEY FOR JACK-UP BARGE SET-UP | 2462-PP-OF-012 | Canelled | 1 |  |  | T-181/25
| RECOVERY PROCEDURE FOR CASING PILES AND DRILLING UNIT FROM SEABED | 2462-PP-OF-022 | AD268-25-3-G-00205 | 1 |  |  | T-443/24 | 2024-09-18 | 2024-09-19 | 2462-NPCC-AO-T-0110 | 2024-09-19 | 2462-NPCC-AO-T-0110 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-469/24 | 2024-09-25 | 2024-09-26 | 2462-NPCC-AO-T-0112
|  |  |  | 3 |  |  | T-382/26 | 2026-08-28

## Setup Plans & Anchor Patterns
NMDC DOC. No.: MDR-001
EPC FOR REPLACEMENT OF TB-3 MOORING SYSTEM
|  | NMDC PROJECT NO. 2462 | [11 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-08-28
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | REF | DATE | REF | DATE | CODE
| SEP-650 SET-UP PLAN AT TB-3, AP-6 LOCATION | 2462-AP-0101 |  | 1 |  |  | T-352/23 | 2023-11-17 | 2023-10-20 | 2462-NPCC-AO-T-0013
| SEP-650 SET-UP PLAN AT TB-3, AP-5 LOCATION | 2462-AP-0102 |  | 1 |  |  | T-367/23 | 2023-12-08 | 2023-11-10 | 2462-NPCC-AO-T-0043
| SEP-650 SET-UP PLAN AT TB-3, AP-4 LOCATION | 2462-AP-0103 |  | 1 |  |  | T-367/23 | 2023-12-08 | 2023-11-22 | 2462-NPCC-AO-T-0044
| SEP-650 SET-UP PLAN AT TB-3, AP-3 LOCATION | 2462-AP-0104 |  | 1 |  |  | T-367/23 | 2023-12-08 | 2023-12-10 | 2462-NPCC-AO-T-0045
| SEP-650 SET-UP PLAN AT TB-3, AP-2 LOCATION | 2462-AP-0105 |  | 1 |  |  | T-390/23 | 2023-12-27
| SEP-650 SET-UP PLAN AT TB-3, AP-1 LOCATION | 2462-AP-0106 |  | 1 |  |  | T-390/23 | 2023-12-27
| TELEFORD-31 SET-UP PLAN AT TB-3, AP-3 LOCATION | 2462-AP-0107 |  | 1 |  |  | T-236/24 | 2024-06-05 | 05-Jun-2024 | 2462-NPCC-AO-T-0075 | 13-Aug-2024 | PE-ZR&DAS-E0261-0035 | 1 - Approved
| TELEFORD-31 SET-UP PLAN AT TB-3, AP-4 LOCATION | 2462-AP-0108 |  | 1 |  |  | T-236/24 | 2024-06-05 | 2024-06-05 | 2462-NPCC-AO-T-0075 | 2024-08-13 | PE-ZR&DAS-E0261-0035 | 1 - Approved
| TELEFORD-31 SET-UP PLAN AT TB-3, AP-5 LOCATION | 2462-AP-0109 |  | 1 |  |  | T-236/24 | 2024-06-05 | 2024-06-05 | 2462-NPCC-AO-T-0075 | 13-Aug-2024 | PE-ZR&DAS-E0261-0035 | 1 - Approved
| DP VESSEL SET-UP FOR CHAIN LAYING AT AP1 LOCATION | 2462-AP-0110
| DP VESSEL SET-UP FOR DEMOLITION AT AP6 LOCATION | 2462-AP-0111
| DP VESSEL SET-UP FOR DEMOLITION AT AP5 LOCATION | 2462-AP-0112
| GMS PEPPER SET-UP PLAN AT TB-3 AP#3 LOCATION | 2462-AP-0113 |  | 1 |  |  | T-167/25 | 2025-04-28 | 2025-04-25 | 2462-NPCC-AO-T-0140
| GMS PEPPER SET-UP PLAN AT TB-3 AP#4 LOCATION | 2462-AP-0114 |  | 1 |  |  | T-167/25 | 2025-04-28 | 2025-04-25 | 2462-NPCC-AO-T-0140
| DP VESSEL SET-UP FOR DEMOLITION AT AP2 LOCATION | 2462-AP-0115
| DP VESSEL SET-UP FOR DEMOLITION AT AP1 LOCATION | 2462-AP-0116
| AVIATION DRAWING FOR SEP-650 AT AP6 LOCATION | 2462-AP-0117
| AVIATION DRAWING FOR SEP-650 AT AP5 LOCATION | 2462-AP-0118
| AVIATION DRAWING FOR SEP-650 AT AP4 LOCATION | 2462-AP-0119
| AVIATION DRAWING FOR SEP-650 AT AP3 LOCATION | 2462-AP-0120
| AVIATION DRAWING FOR SEP-650 AT AP2 LOCATION | 2462-AP-0121
| AVIATION DRAWING FOR SEP-650 AT AP1 LOCATION | 2462-AP-0122
| WORKBOAT (MUTAWA-101) ANCHOR PATTERN AT TB3 - A6 | 2462-AP-0201 |  | 1 |  |  | T-390/23 | 2023-12-27
| WORKBOAT (MUTAWA-101) ANCHOR PATTERN AT TB3 - A5 | 2462-AP-0202 |  | 1 |  |  | T-390/23 | 2023-12-27
| WORKBOAT (MUTAWA-101) ANCHOR PATTERN AT TB3 - A4 | 2462-AP-0203 |  | 1 |  |  | T-147/25 | 2025-04-17 | 2025-04-25 | 2462-NPCC-AO-T-0140
| WORKBOAT (MUTAWA-101) ANCHOR PATTERN AT TB3 - A3 | 2462-AP-0204 |  | 1 |  |  | T-147/25 | 2025-04-17 | 2025-04-25 | 2462-NPCC-AO-T-0140
| WORKBOAT (MUTAWA-101) ANCHOR PATTERN AT TB3 - A2 | 2462-AP-0205 |  | 1 |  |  | T-390/23 | 2023-12-27
| WORKBOAT (MUTAWA-101) ANCHOR PATTERN AT TB3-A1 | 2462-AP-0206 |  | 1 |  |  | T-374/23 | 2023-12-13 | 2023-12-13 | 2462-NPCC-AO-T-0049
| TELEFORD-31 AVIATION SKETCH AT PB3-A3 LOCATION | OFO-P2462-SK-M-009 |  | 1 |  |  | T-237/24
| TELEFORD-31 AVIATION SKETCH AT PB3-A4 LOCATION | OFO-P2462-SK-M-010 |  | 1 |  |  | T-237/24
| TELEFORD-31 AVIATION SKETCH AT PB3-A5 LOCATION | OFO-P2462-SK-M-011 |  | 1 |  |  | T-237/24

## Sketches
NMDC DOC. No.: MDR-001
EPC FOR REPLACEMENT OF TB-3 MOORING SYSTEM
|  | NMDC PROJECT NO. 2462 | [8 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [8 empty] | DATE : | 2026-08-28
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC | [5 empty] | REMARKS
SUBMISSION STATUS
[7 empty] | REF | DATE | Date | Ref
| GMS PEPPER AVIATION CLEARANCE DRAWING AT TB3-AP3 | 2462-SKETCH-001 |  | 1 |  |  | T-176/25 | 2025-04-30 | 2025-04-30 | 2462-NPCC-AO-T-0142
| GMS PEPPER AVIATION CLEARANCE DRAWING AT TB3-AP4 | 2462-SKETCH-002 |  | 1 |  |  | T-176/25 | 2025-04-30 | 2025-04-30 | 2462-NPCC-AO-T-0142