## Installation Procedures
NMDC DOC. No.: MDR-001
EPC for Seven Jackets Installation Project (Five Jackets for US LTDP-2 and Two Jackets for LZ EPS-2)
|  | NMDC PROJECT NO. 2631 | [11 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2026-09-03
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | 2631-PP-OF-0003 | AD-26-Z-80019 | A1 |  | 2024-10-22 | T-323/24 | 2024-07-13
|  |  |  | 1 |  |  | T-432/24 | 2024-09-16 | 2024-09-19 | 2631-NMDC-ADNOC-T-00234 | 2024-11-06 | 10477-E-O-T-US-IFR-000263 | 3-Reviewed with Comments
|  |  |  | 2 |  |  | T-571/24 | 2024-11-29 | 11-Dec-2024 | 2631-NMDC-ADNOC-T-00311 | 2025-01-03 | 10477-E-O-T-US-IFA-000219 | 1-Approved | 2024-12-18 | 2631-NMDC-MWS-T-0006 | 2025-01-06 | SAF194-MCE-NMDC-T-0011 | 1-Approved
| WHT 3-1 To WHT 3-5 Jackets Installation Procedure | 2631-PP-OF-0005 | AD-26-Z-80022 | A1 |  | 2025-02-24 | T-545/24 | 2024-11-07
|  |  |  | 1 |  |  | T-067/25 | 2025-02-07 | 2025-02-10 | 2631-NMDC-ADNOC-T-00371 | 2025-03-21 | 10477-E-O-T-US-IFR-000287 | 2-Approved with Comments | 2025-02-10 | 2631-NMDC-MWS-T-0021 | 2025-02-18 | SAF194-MCE-NMDC-T-0024 | 1-Approved
|  |  |  | 2 |  |  | T-123/25 | 2025-03-28 | 2025-03-28 | 2631-NMDC-ADNOC-T-00425 | 2025-04-02 | 10477-E-O-T-US-IFA-000241 | 1-Approved | 2025-03-28 | 2631-NMDC-MWS-T-0034 | 2025-04-02 | SAF194-MCE-NMDC-T-0030 | 1-Approved
|  |  |  | 3 |  |  | T-211/25 | 2025-05-27 | 2025-05-27 | 2631-NMDC-ADNOC-T-00531 | 2025-06-03 | 10477-E-O-T-US-IFA-000246 | 1-Approved | 27-May-2025 | 2631-NMDC-MWS-T-0046
| WHT-2 & WHT-3 Jackets Installation Procedure | 2631-PP-OF-0008 | AD-26-Z-80012 | A1 |  | 2025-01-24
|  |  |  | 1 |  |  | T-561/24 | 2024-11-26 | 2024-12-10 | 2631-NMDC-ADNOC-T-00309 | 2024-12-23 | 10477-E-O-T-US-IFR-000270 | 2-Approved with Comments | 2024-12-18 | 2631-NMDC-MWS-T-0003
|  |  |  | 2 |  |  | T-598/24 | 2024-12-23 | 2024-12-24 | 2631-NMDC-ADNOC-T-00331 | 2025-01-08 | 10477-E-O-T-US-IFA-000221 | 2-Approved with Comments | 2024-12-24 | 2631-NMDC-MWS-T-0009 | 2025-01-06 | SAF194-MCE-NMDC-T-0012 | 2-Commented
|  |  |  | 3 |  |  | T-010/25 | 2025-01-09 | 2025-01-10 | 2631-NMDC-ADNOC-T-00344 | 2025-02-05 | 10477-E-O-T-US-IFA-000231 | 1-Approved | 2025-02-05 | 2631-NMDC-MWS-T-0016 | 2025-02-07 | SAF194-MCE-NMDC-T-0020 | 2-Commented
|  |  |  | 4 |  |  | T-114/25 | 2025-03-19 | 2025-03-20 | 2631-NMDC-ADNOC-T-00419 | 2025-04-18 | 10477-E-O-T-US-IFA-000239 | 1-Approved | 2025-03-20 | 2631-NMDC-MWS-T-0032 | 2025-03-26 | SAF194-MCE-NMDC-T-0028 | 1-Approved
| METHOD STATEMENT FOR JACKET COMPLETION AND PUNCH LIST CLEARANCE ACTIVITIES | 2631-PP-OF-0010 | AD-26-Z-80342 | 1 |  |  | T-209/25 | 2025-05-20 | 2025-05-23 | 2631-NMDC-ADNOC-T-00520 | 2025-06-04 | 10477-E-O-T-US-IFR-000317 | 2-Approved with Comments | 2025-05-23 | 2631-NMDC-MWS-T-0044
|  |  |  | 2 |  |  | T-265/25 | 2025-06-23 | 2025-06-23 | 2631-NMDC-ADNOC-T-00622 | 2025-06-25 | 10477-E-O-T-US-IFA-000248 | 1-Approved | 2025-06-23 | 2631-NMDC-MWS-T-0062

## Setup Plans & Anchor Patterns
NMDC DOC. No.: MDR-001
EPC for Seven Jackets Installation Project (Five Jackets for US LTDP-2 and Two Jackets for LZ EPS-2)
|  | NMDC PROJECT NO. 2631 | [11 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-09-03
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | REF | DATE | REF | DATE | CODE
| DLB-1000 ANCHOR PATTERN DURING WHT-2 JACKET INSTALLATION | 2631-AP-0001 | AD-27-Z-80030 | 1 |  |  | T-595/24 | 2024-12-17 | 2024-12-18 | 2631-NMDC-ADNOC-T-00321 | 2024-12-31 | 10477-E-O-T-US-IFR-000274 | 3-Reviewed with Comments | 2631-NMDC-MWS-T-0004 | 2024-12-18 | SAF194-MCE-NMDC-T-0011 | 2025-01-06 | 1-Approved
|  |  |  | 2 |  |  | T-001/25 | 2025-01-02 | 2025-01-02 | 2631-NMDC-ADNOC-T-00340 | 2025-01-06 | 10477-E-O-T-US-IFR-000278 | 1-Approved | 2631-NMDC-MWS-T-0010 | 2025-01-02 | SAF194-MCE-NMDC-T-0015 | 2025-01-14 | 1-Approved
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-08-17 | 2631-NMDC-ADNOC-T-00786 | 2026-08-20 | 10477-E-O-T-US-IFN-000020 | 4-Information Only
| DLB-1000 ANCHOR PATTERN DURING WHT-3 JACKET INSTALLATION | 2631-AP-0002 | AD-27-Z-80031 | 1 |  |  | T-595/24 | 2024-12-17 | 2024-12-18 | 2631-NMDC-ADNOC-T-00322 | 2024-12-31 | 10477-E-O-T-US-IFR-000275 |  | 2631-NMDC-MWS-T-0005 | 2024-12-18 | SAF194-MCE-NMDC-T-0011 | 2025-01-06 | 1-Approved
|  |  |  | 2 |  |  | T-003/25 | 2025-01-05 | 2025-01-06 | 2631-NMDC-ADNOC-T-00342 | 2025-01-20 | 10477-E-O-T-US-IFR-000280 | 3-Reviewed with Comments | 2631-NMDC-MWS-T-0012 | 2025-01-06 | SAF194-MCE-NMDC-T-0015 | 2025-01-14 | 1-Approved
|  |  |  | 3 |  |  | T-043/25 | 2025-01-24 | 2025-01-27 | 2631-NMDC-ADNOC-T-00353 | 2025-01-29 | 10477-E-O-T-US-IFR-000282 | 1-Approved | 2631-NMDC-MWS-T-0015 | 2025-01-27 | SAF194-MCE-NMDC-T-0020 | 2025-02-07 | 1-Approved
|  |  |  | 4 |  |  | PMT DIRECT |  | 2026-08-17 | 2631-NMDC-ADNOC-T-00787 | 2026-08-20 | 10477-E-O-T-US-IFN-000020 | 4-Information Only
| DLB-1000 ANCHOR PATTERN DURING WHT-3-1 JACKET PILES AND JACKET APPURTENANCES INSTALLATION | 2631-AP-0003 | AD-26-Z-80198 | 1 |  |  | T-089/25 | 2025-03-03 | 2025-03-06 | 2631-NMDC-ADNOC-T-00400 | 2025-04-02 | 10477-E-O-T-US-IFR-000292 | 2-Approved with Comments | 2631-NMDC-MWS-T-0028 | 2025-03-06 | SAF194-MCE-NMDC-T-0027 | 2025-03-19 | 1-Approved
|  |  |  | 2 |  |  | T-129/25 | 2025-04-03 | 2025-04-03 | 2631-NMDC-ADNOC-T-00430 | 2025-05-21 | 10477-E-O-T-US-IFR-000308 | 5-Rejected | 2631-NMDC-MWS-T-0035 | 2025-04-03 | SAF194-MCE-NMDC-T-0031 | 2025-04-09 | 1-Approved
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-08-10 | 2631-NMDC-ADNOC-T-00775 | 2026-08-11 | 10477-E-O-T-US-IFI-000075 | 4-Information Only
| DLB-1000 ANCHOR PATTERN DURING WHT-3-2 JACKET PILES AND JACKET APPURTENANCES INSTALLATION | 2631-AP-0004 | AD-26-Z-80199 | 1 |  |  | T-325/25 | 2025-07-03 | 2025-07-07 | 2631-NMDC-ADNOC-T-00642 | 2025-08-15 | 10477-E-O-T-US-IFR-000334 | 1-Approved | 2631-NMDC-MWS-T-0063 | 2025-07-07 | SAF194-MCE-NMDC-T-0053 |  | 1-Approved
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-08-17 | 2631-NMDC-ADNOC-T-00788 | 2026-08-20 | 10477-E-O-T-US-IFN-000020 | 4-Information Only
| DLB-1000 ANCHOR PATTERN DURING WHT-3-3 JACKET PILES AND JACKET APPURTENANCES INSTALLATION | 2631-AP-0005 | AD-26-Z-80200 | 1 |  |  | T-090/25 | 2025-03-03 | 2025-03-06 | 2631-NMDC-ADNOC-T-00398 | 2025-04-02 | 10477-E-O-T-US-IFR-000290 | 2-Approved with Comments | 2631-NMDC-MWS-T-0027 | 2025-03-06 | SAF194-MCE-NMDC-T-0027 | 2025-03-19 | 1-Approved
|  |  |  | 2 |  |  | T-130/25 | 2025-04-03 | 2025-04-03 | 2631-NMDC-ADNOC-T-00433 | 2025-05-21 | 10477-E-O-T-US-IFR-000308 | 5-Rejected | 2631-NMDC-MWS-T-0036 | 2025-04-03 | SAF194-MCE-NMDC-T-0031 | 2025-04-09 | 1-Approved
|  |  |  | 3 |  |  | T-212/25 | 2025-05-27 | 2025-05-27 | 2631-NMDC-ADNOC-T-00533 | 2025-06-04 | 10477-E-O-T-US-IFR-000316 | 1-Approved | 2631-NMDC-MWS-T-0047 | 2025-05-27 | SAF194-MCE-NMDC-T-0044 | 2025-06-10 | 1-Approved
|  |  |  | 4 |  |  | T-249/25 | 2025-06-10 | 2025-06-10 | 2631-NMDC-ADNOC-T-00580 | 2025-06-12 | 10477-E-O-T-US-IFR-000318 | 1-Approved | 2631-NMDC-MWS-T-0058 | 2025-06-10 | SAF194-MCE-NMDC-T-0046 | 2025-06-16 | 1-Approved
|  |  |  | 5 |  |  | T-249/25 | 2025-06-17 |  | NOT ISSUED
|  |  |  | 5 |  |  | PMT DIRECT | 2026-08-17 | 2026-08-17 | 2631-NMDC-ADNOC-T-00789 | 2026-08-20 | 10477-E-O-T-US-IFN-000020 | 4-Information Only
| DLB-1000 ANCHOR PATTERN DURING WHT-3-4 JACKET PILES AND JACKET APPURTENANCES INSTALLATION | 2631-AP-0006 | AD-26-Z-80201 | 1 |  |  | T-350/25 | 2025-07-14 | 2025-07-18 | 2631-NMDC-ADNOC-T-00659 | 2025-07-25 | 10477-E-O-T-US-IFR-000329 | 1-Approved | 2631-NMDC-MWS-T-0068 | 2025-07-18 | SAF194-MCE-NMDC-T-0057 | 2025-07-23 | 1-Approved
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-08-18 | 2631-NMDC-ADNOC-T-00790 | 2026-08-20 | 10477-E-O-T-US-IFN-000020 | 4-Information Only
| DLB-1000 ANCHOR PATTERN DURING WHT-3-5 JACKET PILES AND JACKET APPURTENANCES INSTALLATION | 2631-AP-0007 | AD-26-Z-80202 | 1 |  |  | T-356/25 | 2025-07-16 | 2025-07-16 | 2631-NMDC-ADNOC-T-00652 | 2025-08-11 | 10477-E-O-T-US-IFR-000333 | 4-Information Only | 2631-NMDC-MWS-T-0065 | 2025-07-16 | SAF194-MCE-NMDC-T-0056 | 2025-07-21 | 1-Approved
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-08-18 | 2631-NMDC-ADNOC-T-00791 | 2026-08-20 | 10477-E-O-T-US-IFN-000020 | 4-Information Only
| SAFEEN-3000 SETUP PLAN DURING WHT 3-1 JACKET INSTALLATION | 2631-DP-0001 | AD-26-Z-80023 | 1 |  |  | T-089/25 | 2025-03-03 | 2025-03-06 | 2631-NMDC-ADNOC-T-00401 | 2025-04-02 | 10477-E-O-T-US-IFR-000293 | 1-Approved | 2631-NMDC-MWS-T-0029 | 2025-03-06 | SAF194-MCE-NMDC-T-0027 | 2025-03-19 | 1-Approved
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-08-18 | 2631-NMDC-ADNOC-T-00792 | 2026-08-20 | 10477-E-O-T-US-IFN-000020 | 4-Information Only
| UMM SHAIF - EPC FOR SEVEN JACKETS INSTALLATION - SAFEEN-3000 SETUP PLAN DURING WHT 3-2 JACKET INSTALLATION | 2631-DP-0002 | AD-26-Z-80024
| SAFEEN-3000 SETUP PLAN DURING WHT-3-3 JACKET INSTALLATION | 2631-DP-0003 | AD-26-Z-80025 | 1 |  |  | T-090/25 | 2025-03-03 | 2025-03-06 | 2631-NMDC-ADNOC-T-00399 | 2025-04-02 | 10477-E-O-T-US-IFR-000291 | 1-Approved | 2631-NMDC-MWS-T-0030 | 2025-03-06 | SAF194-MCE-NMDC-T-0027 | 2025-03-19 | 1-Approved
|  |  |  | 2 |  |  | T-191/25 | 2025-05-12 | 2025-05-13 | 2631-NMDC-ADNOC-T-00497 | 2025-05-21 | 10477-E-O-T-US-IFR-000307 | 1-Approved | 2631-NMDC-MWS-T-0042 | 2025-05-13 | SAF194-MCE-NMDC-T-0039 | 2025-05-22 | 1-Approved
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-08-24 | 2631-NMDC-ADNOC-T-00796 | 2026-09-03 | 10477-E-O-T-US-IFN-000023 | 4-Information Only
| UMM SHAIF - EPC FOR SEVEN JACKETS INSTALLATION - SAFEEN-3000 SETUP PLAN DURING WHT 3-4 JACKET INSTALLATION | 2631-DP-0004 | AD-26-Z-80026
| UMM SHAIF - EPC FOR SEVEN JACKETS INSTALLATION - SAFEEN-3000 SETUP PLAN DURING WHT 3-5 JACKET INSTALLATION | 2631-DP-0005 | AD-26-Z-80027
| SAPURA-1200 SETUP PLAN DURING WHT-3-3 JACKET INSTALLATION | 2631-DP-0006 | AD-26-Z-80316 | 1 |  |  | T-150/25 | 2025-04-23 | 2025-04-26 | 2631-NMDC-ADNOC-T-00466 | 2025-05-21 | 10477-E-O-T-LZ-IFR-000057 | 5-Rejected | 2631-NMDC-MWS-T-0040 | 2025-04-28 | SAF194-MCE-NMDC-T-0036 | 2025-05-08 | 1-Approved
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-08-10 | 2631-NMDC-ADNOC-T-00776 | 2026-08-11 | 10477-E-O-T-LZ-IFI-000021 | 4-Information Only
| SAPURA-1200 SETUP PLAN DURING WHT-3-5 JACKET INSTALLATION | 2631-DP-0007 | AD-26-Z-80343 | 1 |  |  | T-214/25 | 2025-05-26 | 2025-05-26 | 2631-NMDC-ADNOC-T-00526 | 2025-06-04 | 10477-E-O-T-US-IFR-000314 | 2-Approved with Comments | 2631-NMDC-MWS-T-0045 | 2025-05-26 | SAF194-MCE-NMDC-T-0053 | 2025-07-11 | 1-Approved
|  |  |  | 2 |  |  | T-273/25 | 2025-06-19 | 2025-06-19 | 2631-NMDC-ADNOC-T-00607 | 2025-06-23 | 10477-E-O-T-US-IFR-000323 | 1-Approved | 2631-NMDC-MWS-T-0061 | 2025-06-19 | SAF194-MCE-NMDC-T-0048 | 2025-06-25 | 1-Approved
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-09-03 | 2631-NMDC-ADNOC-T-00797 | 2026-09-03 | 10477-E-O-T-US-IFN-000023
| DLS-4200 SETUP PLAN DURING WHT 3-4 JACKET INSTALLATION | 2631-DP-0008 | AD-26-Z-80344 | 1 |  |  | T-227/25 | 2025-05-29 | 2025-05-30 | 2631-NMDC-ADNOC-T-00538 | 2025-06-19 | 2631-NMDC-ADNOC-T-00606 | 2-Approved with Comments | 2631-NMDC-MWS-T-0048 | 2025-05-30 | SAF194-MCE-NMDC-T-0046 | 2025-06-16 | 2-Approved with Comments
|  |  |  | 2 |  |  | T-274/25 | 2025-06-19 | 2025-06-19 | 2631-NMDC-ADNOC-T-00606 | 2025-06-23 | 10477-E-O-T-LZ-IFR-000088 | 1-Approved | 2631-NMDC-MWS-T-0060 | 2025-06-19 | SAF194-MCE-NMDC-T-0048 | 2025-06-25 | 1-Approved
| DLS-4200 SETUP PLAN DURING WHT 3-2 JACKET INSTALLATION | 2631-DP-0009 | AD-26-Z-80345 | 1 |  |  | T-267/25 | 2025-06-17 | 2025-06-18 | 2631-NMDC-ADNOC-T-00602 | 2025-06-23 | 10477-E-O-T-LZ-IFR-000088 | 1-Approved | 2631-NMDC-MWS-T-0059 | 2025-06-18 | SAF194-MCE-NMDC-T-0048 | 2025-06-25 | 1-Approved
|  |  |  | 2 |  |  | T-370/25 | 2025-07-22 | 2025-07-22 | 2631-NMDC-ADNOC-T-00668 | 2025-07-25 | 10477-E-O-T-LZ-IFR-000102 | 1-Approved | 2631-NMDC-MWS-T-0069 | 2025-07-22 | SAF194-MCE-NMDC-T-0058 | 2025-07-25 | 1-Approved
| MUTAWA-401 SETUP PLAN DURING WHT 3-1 PUNCH LIST CLEARANCE ACTIVITIES | 2631-DP-0010 | AD-26-Z-80361 | 1 |  |  | T-235/25 | 2025-05-31 | 2025-06-02 | 2631-NMDC-ADNOC-T-00558 | 2025-06-30 | 10477-E-O-T-LZ-IFR-000096 | 3-Reviewed with Comments | 2631-NMDC-MWS-T-0056 | 2025-06-02
|  |  |  | 2 |  |  | T-536/25 | 2025-10-20 | 2025-10-21 | 2631-NMDC-ADNOC-T-00756 | 2025-11-14 | 10477-E-O-T-LZ-IFR-000113 | 2-Approved with Comments | 2631-NMDC-MWS-T-0071 | 2025-10-21
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-08-10 | 2631-NMDC-ADNOC-T-00777 | 2026-08-11 | 10477-E-O-T-LZ-IFI-000020 | 4-Information Only
| MUTAWA-401 SETUP PLAN DURING WHT 3-3 PUNCH LIST CLEARANCE ACTIVITIES | 2631-DP-0011 | AD-26-Z-80362 | 1 |  |  | T-235/25 | 2025-05-31 | 2025-06-02 | 2631-NMDC-ADNOC-T-00557 | 2025-06-30 | 10477-E-O-T-LZ-IFR-000096 | 3-Reviewed with Comments | 2631-NMDC-MWS-T-0055 | 2025-06-02
|  |  |  | 2 |  |  | T-536/25 | 2025-10-20 | 2025-10-21 | 2631-NMDC-ADNOC-T-00757 | 2025-11-14 | 10477-E-O-T-LZ-IFR-000113 | 2-Approved with Comments | 2631-NMDC-MWS-T-0072 | 2025-10-21
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-08-10 | 2631-NMDC-ADNOC-T-00778 | 2026-08-11 | 10477-E-O-T-LZ-IFI-000020 | 4-Information Only
| MUTAWA-401 SETUP PLAN DURING WHT 2 PUNCH LIST CLEARANCE ACTIVITIES | 2631-DP-0012 | AD-26-Z-80363 | 1 |  |  | T-235/25 | 2025-05-31 | 2025-06-02 | 2631-NMDC-ADNOC-T-00556 | 2025-06-30 | 10477-E-O-T-LZ-IFR-000096 | 3-Reviewed with Comments | 2631-NMDC-MWS-T-0054 | 2025-06-02
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-08-10 | 2631-NMDC-ADNOC-T-00779 | 2026-08-11 | 10477-E-O-T-LZ-IFI-000021 | 4-Information Only
| MUTAWA-401 SETUP PLAN DURING WHT 3 PUNCH LIST CLEARANCE ACTIVITIES | 2631-DP-0013 | AD-26-Z-80364 | 1 |  |  | T-235/25 | 2025-05-31 | 2025-06-02 | 2631-NMDC-ADNOC-T-00555 | 2025-06-30 | 10477-E-O-T-LZ-IFR-000096 | 3-Reviewed with Comments | 2631-NMDC-MWS-T-0053 | 2025-06-02
|  |  |  | 2 |  |  | PMT DIRECT |  | 2026-08-10 | 2631-NMDC-ADNOC-T-00780 | 2026-08-11 | 10477-E-O-T-LZ-IFI-000021 | 4-Information Only
| MUTAWA-401 SETUP PLAN DURING WHT 3-2 PUNCH LIST CLEARANCE ACTIVITIES | 2631-DP-0014 | AD-26-Z-80365 | 1 |  |  | T-235/25 | 2025-05-31 | 2025-06-02 | 2631-NMDC-ADNOC-T-00554 | 2025-06-30 | 10477-E-O-T-LZ-IFR-000096 | 3-Reviewed with Comments | 2631-NMDC-MWS-T-0052 | 2025-06-02
|  |  |  | 2 |  |  | T-536/25 | 2025-10-20 | 2025-10-21 | 2631-NMDC-ADNOC-T-00758 | 2025-11-14 | 10477-E-O-T-LZ-IFR-000113 | 2-Approved with Comments | 2631-NMDC-MWS-T-0073 | 2025-10-21
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-08-10 | 2631-NMDC-ADNOC-T-00781 | 2026-08-11 | 10477-E-O-T-LZ-IFI-000020 | 4-Information Only
| MUTAWA-401 SETUP PLAN DURING WHT 3-4 PUNCH LIST CLEARANCE ACTIVITIES | 2631-DP-0015 | AD-26-Z-80366 | 1 |  |  | T-235/25 | 2025-05-31 | 2025-06-02 | 2631-NMDC-ADNOC-T-00553 | 2025-06-30 | 10477-E-O-T-LZ-IFR-000096 | 3-Reviewed with Comments | 2631-NMDC-MWS-T-0051 | 2025-06-02
|  |  |  | 2 |  |  | T-536/25 | 2025-10-20 | 2025-10-21 | 2631-NMDC-ADNOC-T-00759 | 2025-11-14 | 10477-E-O-T-LZ-IFR-000113 | 2-Approved with Comments | 2631-NMDC-MWS-T-0074 | 2025-10-21
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-08-10 | 2631-NMDC-ADNOC-T-00782 | 2026-08-11 | 10477-E-O-T-LZ-IFI-000020 | 4-Information Only
| MUTAWA-401 SETUP PLAN DURING WHT 3-5 PUNCH LIST CLEARANCE ACTIVITIES | 2631-DP-0016 | AD-26-Z-80367 | 1 |  |  | T-235/25 | 2025-05-31 | 2025-06-02 | 2631-NMDC-ADNOC-T-00552 | 2025-06-30 | 10477-E-O-T-LZ-IFR-000096 | 3-Reviewed with Comments | 2631-NMDC-MWS-T-0050 | 2025-06-02
|  |  |  | 2 |  |  | T-536/25 | 2025-10-20 | 2025-10-21 | 2631-NMDC-ADNOC-T-00760 | 2025-11-14 | 10477-E-O-T-LZ-IFR-000113 | 2-Approved with Comments | 2631-NMDC-MWS-T-0075 | 2025-10-20
|  |  |  | 3 |  |  | PMT DIRECT |  | 2026-08-10 | 2631-NMDC-ADNOC-T-00783 | 2026-08-11 | 10477-E-O-T-LZ-IFI-000020 | 4-Information Only

## Sketches
NMDC DOC. No.: MDR-001
EPC for Seven Jackets Installation Project (Five Jackets for US LTDP-2 and Two Jackets for LZ EPS-2)
|  | NMDC PROJECT NO. 2631 | [6 empty] | REVISION : | 0
|  | OFFSHORE Sketches | [6 empty] | DATE : | 2026-09-03
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| (DLB-1000 AP during WHT-2 JKT Installation) | 2631-AP-0001 |  | 1 |  |  | 2024-10-31 | SKV
| (DLB-1000 AP during WHT-3 JKT Installation) | 2631-AP-0002 |  | 1 |  |  | 2024-10-31 | SKV
| (Scaffolding Frame @ WHT-3) | 2631-A3-001 |  | A |  |  | 2024-12-18 | SKV
| AP during WHT-2 JKT Installation | 2631-AP-0001 |  | 2 |  |  | 2025-01-02 | SKV
| AP during WHT-3 JKT Installation | 2631-AP-0002 |  | 2 |  |  | 2025-01-02 | SKV
| (Anchor line shfting sequence) | 2631-A1-002 |  | A |  |  | 2025-01-24 | SKV
| (VESSEL PASSAGE PLAN TO WHT-2 & 3 Location) | 2631-A1-003 |  | A |  |  | 2025-01-24 | SKV
| (DLB-1000 AP during WHT-3 JKT Installation) | 2631-AP-0002 |  | 3 |  |  | 2025-01-24 | SKV
| (DLB-1000 AP during WHT 3-1 JKT PILE & DRILL DECK Installation) | 2631-AP-0003 |  | 1 |  |  | 2025-02-18 | SKV
| (DLB-1000 AP during WHT 3-3 JKT PILE & DRILL DECK Installation) | 2631-AP-0004 |  | 1 |  |  | 2025-02-18 | SKV
| (SAFEEN-3000 DP Setup during WHT 3-1 JKT Installation) | 2631-DP-0001 |  | 1 |  |  | 2025-02-18 | SKV
| (SAFEEN-3000 DP Setup during WHT 3-3 JKT Installation) | 2631-DP-0003 |  | 1 |  |  | 2025-02-18 | SKV
| (DLB-1000 AP during WHT 3-1 JKT PILES AND JACKET APPURTENANCES INSTALLATION) | 2631-AP-0003 |  | 2 |  |  | 2025-04-02 | SKV
| (DLB-1000 AP during WHT 3-3 JKT PILES AND JACKET APPURTENANCES INSTALLATION) | 2631-AP-0005 |  | 2 |  |  | 2025-04-02 | SKV
| (SAPURA-1200 DP Setup during WHT 3-3 JKT Installation) | 2631-DP-0006 |  | 1 |  |  | 2025-04-11 | EJJ
| (SAPURA 1200 setup during WHT3-5 JKT installation) | 2631-DP-0007 |  | 1 |  |  | 2025-05-01 | SKV
| (SAPURA 1200 setup during WHT3-4 JKT installation) | 2631-DP-0008 |  | 1 |  |  | 2025-05-01 | SKV
| (SAPURA 1200 setup during WHT3-2 JKT installation) | 2631-DP-0009 |  | 1 |  |  | 2025-05-01 | SKV
| (DLS-4200 PASSAGE PLAN TO WHT 3-4 Location) | 2631-A1-005 |  | A |  |  | 2025-06-03 | SKV
| (DLS-4200 DP Setup during WHT 3-3 JKT PILES AND JACKET APPURTENANCES INSTALLATION) | 2631-DP-0017 |  | 1 |  |  | 2025-06-04 | SKV
| (SAPURA 1200 setup during WHT3-5 JKT installation) | 2631-DP-0007 |  | 3 |  |  | 2025-06-20 | SKV