## Installation Procedures
NMDC DOC. No.: MDR-001
HAIL & GHASHA DEVELOPMENT PROJECT
|  | NMDC PROJECT NO. 2642 | [11 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | SAIPEM OFFSHORE | [8 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO COMPANY |  | FROM ABL-MWS |  |  | FROM COMPANY |  |  | STATUS FROM RINA
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | CODE | DATE | REF | CODE
| ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | CF0000-4002400 | 1-CF0000-31-PRO-2400-00 | A |  |  | T-556/24 | 2024-11-20
|  |  |  | A1 |  |  | T-567/24 | 2024-11-27 | 2024-12-20 | E-mail Reference
|  |  |  | 00 |  |  | T-171/25 | 2025-04-30 | 2025-05-01 | E-mail Reference | 2025-05-20 | 1-CF0000-31-PRO-2400-00_CS-0481 | N NOTED
|  |  |  | X100 |  |  | T-205/25 | 2025-05-30 | 2025-05-30 | E-mail Reference
|  |  |  | 01 |  |  | T-241/25 | 2025-06-09 | 2025-06-09 | E-mail Reference | 2025-06-17 | AD-G-30 44988-ABL-DRS-DRS-0626 | 2. Comments as noted
|  |  |  | 02 |  |  | T-173/26 | 2026-04-22 |  |  | 2026-05-07 | AD-G-30 44988-ABL-DRS-APP-3625 | Y |  |  |  | 2026-05-05 | 1-CF0000-31-PRO-2400-00_CS-0481 | H – ON HOLD
| JACKETS INSTALLATION MANUAL FOR DC6 AND CLQ | CF0000-4002401 | 1-CF0000-31-MAN-2401-00 | A |  |  | T-063/25 | 2025-02-05
|  |  |  | A1 |  |  | T-091/25 | 2025-03-12 | 2025-03-12 | E-mail Reference | 2025-04-11 | AD-G-30 44988-ABL-DRS-DRS-0130 | 2. Comments as noted | [6 empty] | rev. issued for oo
|  |  |  | 00 |  |  | T-199/25 | 2025-05-16 |  |  | 2025-05-29 | AD_G30_44988-ABL-DRS-DRS-0517 | 2. Comments as noted |  |  |  |  | 1-CF0000-31-MAN-2401-00_CS-0480 | NC – NOTED WITH COMMENTS
|  |  |  | X100 |  |  | T-237/25 | 2025-06-02
|  |  |  | X101 |  |  | T-239/25 | 2025-06-09 |  |  | 2025-06-11 | AD_G30_44988-ABL-DRS-APP-0575 | 2. Comments as noted
|  |  |  | 01 |  |  | T-255/25 | 2025-06-13 | 2025-06-17 | E-mail Reference
| TOPSIDE INSTALLATION PROCEDURE (GOP-SRP) | CF0000-4002402 | 1-CF0000-31-PRO-2402-00 | A1 |  |  | T-084/26 | 2026-02-25 | [5 empty] | 2026-02-26 | 1-CF0000-31-PRO-2402-00_A1_CPY2 | 2. Comments as noted
|  |  |  | X100 |  |  | T-212/26 | 2026-05-14 | 2026-05-15 | E-mail Reference | 2026-05-25 | AD_G30_44988-ABL-DRS-APP-3965 | Y
|  |  |  | 00 |  |  | T-220/26 | 2026-05-18 | [5 empty] | 2026-06-08 | 1-CF0000-31-PRO-2402-00_00_CPY1 | CODE 1-NO COMMENTS | 2026-05-27 | 1-CF0000-31-PRO-2402-00_CS-0482 | CLOSED
| BRIDGES & FLARE BOOM INSTALLATION PROCEDURE BRIDGES INSTALLATION PROCEDURE (GOP-SRP) | CF0000-4002404 | 1-CF0000-31-PRO-2404-00 | A1 |  |  | T-080/26 | 2026-03-09 | 2026-03-11 | E-mail Reference
|  |  |  | X100 |  |  | T-248/26 | 2026-06-17 | 2026-06-17 | E-mail Reference
| STALK ON RISERS INSTALLATION PROCEDURE | CF0000-4002405 | 1-CF0000-31-PRO-2405-00 | A1 |  |  | T-040/26 | 2026-01-28 | 2026-01-28 | E-mail Reference | [6 empty] | 2026-03-18 | 1-CF0000-31-PRO-2404-00_CS-0484 | CLOSED
|  |  |  | X100 |  |  | T-128/26 | 2026-03-28 | 2026-03-30 | E-mail Reference | 2026-04-08 | AD_G30_44988-ABL-DRS-DRS-3178 | Y/N
| SURFACE MID LINES INSTALLATION PROCEDURE | CF0000-4002407 | 1-CF0000-31-PRO-2407-00 | A1 |  |  | T-482/25 | 2025-09-19 | 2025-09-19 | E-mail Reference | 2025-09-29 | AD_G30_44988-ABL-DRS-DRS-1379 | N | 2025-09-29 | mail
|  |  |  | X100 |  |  | 2025-10-06 | T-514/25 | 2025-10-06 | E-mail Reference | 2025-10-22 | AD_G30_44988-ABL-DRS-1576 | Y/N
|  |  |  | 00 |  |  | T-551/25 | 2025-10-29 | 2025-10-29 | E-mail Reference | 2025-11-03 | AD_G30_44988-ABL-DRS-1634
| METHOD STATEMENT FOR FRAME REMOVAL AT GOP BY SAFEEN 3000 | CF0000-4002553 | 1-CF0000-31-MES-2553-00 | A |  |  | T-138/25 | 2025-04-21
|  |  |  | A1 |  |  | T-179/25 | 2025-05-01 | 2025-05-22 | E-mail Reference | 2025-09-16 | 1-CF0000-31-MES-2553-00_02_CPY1
|  |  |  | 00 |  |  | T-284/25 | 2025-06-23
|  |  |  | 01 |  |  | T-462/25 | 2025-09-09 | 2025-09-09 | E-mail Reference
|  |  |  | 02 |  |  | T-471/25 | 2025-09-12 | 2025-09-16 | E-mail Reference |  |  |  | 2025-09-28
| JACKETS INSTALLATION MANUAL FOR DC4 | CF0000-4002565 | 1-CF0000-31-MAN-2565-00 | A1 |  |  | T-248/25 | 2025-06-10 | 2025-06-10 | E-mail Reference | 2025-06-27 |  | 2. Comments as noted
|  |  |  | X1A1 |  |  | T-304/25 | 2025-06-27
|  |  |  | X1A1 |  |  | T-332/25 | 2025-07-07 | 2025-07-07 | E-mail Reference
|  |  |  | X200 |  |  | T-362/25 | 2025-07-18 | 2025-07-18 | E-mail Reference
|  |  |  | 00 |  |  | T-396/25 | 2025-08-07 |  |  | 2025-08-15 | [5 empty] | 2025-08-26 | mail
| CARGO BARGE TOWING PLAN | CF0000-4002567 | 1-CF0000-31-PRO-2567-00 | E1 |  |  | T-245/25 | 2025-06-10 | 2025-06-10 | E-mail Reference | 2025-06-12 | AD_G30_44988-ABL-DRS-DRS-0577 | 2. Comments as noted
[11 empty] | 2025-06-20 | AD_G30_44988-ABL-DRS-APP-0633 | 2. Comments as noted
|  |  |  | E2 |  |  | T-275/25 | 2025-06-23 | 2025-06-24 | E-mail Reference | 2025-07-21 | AD_G30_44988-ABL-DRS-APP-0766
| JACKET INSTALLATION MANUAL FOR DC1 | CF0000-4002574 | 1-CF0000-31-MAN-2574-00 | A1 |  |  | T-416/25 | 2025-08-18 |  |  | 2025-08-22 | AD_G30_44988-ABL-DRS-APP-0983 |  | 2025-08-22 |  | CODE-2
|  |  |  | 00 |  |  | T-438/25 | 2025-08-28 | 2025-08-28 | E-mail Reference | 2025-09-01 | AD_G30_44988-ABL-DRS-APP-1042
| JACKET INSTALLATION MANUAL FOR GOP-FLARE | CF0000-4002575 | 1-CF0000-31-MAN-2575-00 | A1 |  |  | T-435/25 | 2025-08-28 | 2025-08-28 | E-mail Reference | 2025-09-10 | AD_G30_44988-ABL-DRS-APP-1134
|  |  |  | 00 |  |  | T-470/25 | 2025-09-12 | 2025-09-12 | E-mail Reference | 2025-09-18 | AD_G30_44988-ABL-DRS-APP-1220 |  |  |  |  | 2025-09-19 | 1-CF0000-31-MAN-2575-00_CS-0524
| JACKET INSTALLATION MANUAL FOR GOP-SRP | GH5100-4002573 | 1-GH5100-31-MAN-2573-00 | A1 |  |  | T-369/25 | 2025-07-22 |  |  | 2025-07-24
|  |  |  | 00 |  |  | T-378/25 | 2025-07-25 |  |  | 2025-08-13 | [5 empty] | 26/8/25 | mail
| JACKET INSTALLATION MANUAL FOR GOP-SWI | GH5100-4002576 | 1-GH5100-31-MAN-2576-00 | A1 |  |  | T-436/25 | 2025-08-28 | 2025-08-28 | E-mail Reference
|  |  |  | X100 |  |  | T-517/25 | 2025-10-10 | 2025-10-10 | E-mail Reference | 2025-10-13 | AD_G30_44988-ABL-DRS-APP-1503
|  |  |  | 00 |  |  | T-526/25 | 2025-10-15 | 2025-10-16 | E-mail Reference | 2025-10-20 | AD_G30_44988-ABL-DRS-APP-1555
| JACKET INSTALLATION MANUAL FOR GOP-NRP | GH5100-4002577 | 1-GH5100-31-MAN-2577-00 | A1 |  |  | T-454/25 | 2025-09-08 | 2025-09-08 | E-mail Reference | [6 empty] | 2025-09-19 | 1-GH5100-31-MAN-2577-00_CS-0526
|  |  |  | 00 |  |  | T-491/25 | 2025-09-23 | 2025-09-23 | E-mail Reference | 2025-09-25 | AD_G30_44988-ABL-DRS-APP-1337
| STALK ON RISERS INSTALLATION PROCEDURE (DLS4200) | CF0000-4002625 | 1-CF0000-31-PRO-2625-00 | A1 |  |  | T-145/26 | 2026-04-09 |  | E-mail Reference | 2026-04-29 | AD_G30_44988-ABL-DRS-DRS-3526 | N
|  |  |  | X100 |  |  | T-197/26 | 2026-05-08 | 2026-05-11 | E-mail Reference | 2026-05-19 | AD_G30_44988-ABL-DRS-APP-3919 | Y
|  |  |  | 00 |  |  | T-216/26 | 2026-05-15
| TOPSIDES INSTALLATION PROCEDURE (DLS4200) (DC6) | CF0000-4002643 | 1-CF0000-31-PRO-2643-00 | A1 |  |  | T-186/26 | 2026-05-01
|  |  |  | A1 |  |  | T-224/26 | 2026-05-20 | 2026-05-21 | E-mail Reference | 2026-06-03 | AD_G30_44988-ABL-DRS-DRS-4077 | Y/N | 2026-06-18 | 1-CF0000-31-PRO-2643-00_A1_CPY2 | CODE 2-COMMENTS AS NOTED | 2026-05-27 | 1-CF0000-31-PRO-2643-00_CS-0533 | CLOSED
|  |  |  | X100 |  |  | T-272/26 | 2026-07-01 | 2026-07-02 | E-mail Reference | 2026-07-06 | AD_G30_44988-ABL-DRS-APP-4534 | Y
|  |  |  | 00 |  |  | T-285/26 | 2026-07-07 |  | E-mail Reference | 2026-07-14 | AD_G30_44988-ABL-DRS-APP-4604 | Y | 2026-07-15
| SURFACE MIDLINE INSTALLATION & REPAIR PROCEDURE | CF0000-4002649 | 1-CF0000-31-PRO-2649-00 | A1 |  |  | T-388/26 | 2026-09-02 |  |  | 2026-09-04 | AD_G30_44988-ABL-DRS-DRS-5304
| STALK ON RISERS INSTALLATION PROCEDURE (DLS4200) AT DC4 | GH0400-4002674 | 1-GH0400-31-PRO-2674-00 | A1 |  |  | T-364/26 | 2026-08-25 |  |  | 2026-09-01 | AD_G30_44988-ABL-DRS-DRS-5237
| TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT GOP-NRP | GH5100-4002659 | 1-GH5100-31-PRO-2659-00 | A1 |  |  | T-339/26 | 2026-08-10 |  |  | 2026-08-19 | AD_G30_44988-ABL-DRS-APP-5091 | Y
|  |  |  | 00 |  |  | T-390/26 | 2026-09-02
| TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT DC4 | GH0400-4002660 | 1-GH0400-31-PRO-2660-00
| TOPSIDE INSTALLATION PROCEDURE (SAFEEN3000) AT DC1 | GH0100-4002661 | 1-GH0100-31-PRO-2661-00
| TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT CLQ | GH6000-4002662 | 1-GH6000-31-PRO-2662-00
| TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT GOP FLARE | GH5100-4002663 | 1-GH5100-31-PRO-2663-00
| TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT GOP SWI | GH5100-4002664 | 1-GH5100-31-PRO-2664-00
| BRIDGES INSTALLATION PROCEDURE (DLS4200) AT DC6 | GH0600-4002665 | 1-GH0600-31-PRO-2665-00 | A1 |  |  | T-284/26 | 2026-07-07 |  |  | 2026-07-15 | AD_G30_44988-ABL-DRS-APP-4633 | Y | 2026-07-16 | 1-GH0600-31-PRO-2665-00_A1_CPY2 | CODE 1-NO COMMENTS | 2026-07-30 | 1-GH0600-31-PRO-2665-00_CS-0540 | CLOSED
|  |  |  | 00 |  |  | T-324/26 | 2026-07-29 |  |  | 2026-08-03 | AD_G30_44988-ABL-DRS-APP-4904 | Y | 2026-08-03 |  | CODE 1-NO COMMENTS
| BRIDGES INSTALLATION PROCEDURE (DLS4200) AT GOP-NRP | GH5100-4002666 | 1-GH5100-31-PRO-2666-00 | A1 |  |  | T-372/26 | 2026-08-26
| BRIDGES INSTALLATION PROCEDURE (DLS4200) AT DC4 | GH0400-4002667 | 1-GH0400-31-PRO-2667-00
| BRIDGE INSTALLATION PROCEDURE (SAFEEN3000) AT DC1 | GH0100-4002668 | 1-GH0100-31-PRO-2668-00
| BRIDGE INSTALLATION PROCEDURE (DLS4200) AT CLQ | GH6000-4002669 | 1-GH6000-31-PRO-2669-00
| BRIDGE & FLARE BOOM INSTALLATION PROCEDURE (DLS4200) AT GOP FLARE | GH5100-4002670 | 1-GH5100-31-PRO-2670-00
| BRIDGE INSTALLATION PROCEDURE (DLS4200) AT GOP SWI | GH5100-4002671 | 1-GH5100-31-PRO-2671-00
| STALK ON RISERS INSTALLATION PROCEDURE (DLS4200) AT DC6 AND GOP-NRP | GH0600-4002672 | 1-GH0600-31-PRO-2672-00 | A1 | 2 |  | T-259/26 | 2026-06-23 | 2026-06-24 | E-mail Reference | 2026-07-07 | AD_G30_44988-ABL-DRS-DRS-4559 |  | 2026-07-03 | 1-GH0600-31-PRO-2672-00_A1_CPY2 | CODE 2-COMMENTS AS NOTED
|  |  |  | X100 | 2 |  | T-292/26 | 2026-07-09 |  |  | 2026-07-16 | AD_G30_44988-ABL-DRS-APP-4651
|  |  |  | 00 |  |  | T-318/26 | 2026-07-23 | 2026-07-24 | E-mail Reference |  |  |  | 2026-08-03 |  | CODE 1-NO COMMENTS
| STALK ON RISERS INSTALLATION PROCEDURE (DLS4200) AT GOP-NRP | GH5100-4002673 | 1-GH5100-31-PRO-2673-00 | A1 | 2 |  | T-281/26 | 2026-07-06 | 2026-07-06 | E-mail Reference
| STALK ON RISERS INSTALLATION PROCEDURE (SAFEEN3000) AT DC1 | GH0100-4002675 | 1-GH0100-31-PRO-2675-00 | A1 |  |  | T-368/26 | 2026-08-25 |  |  | 2026-09-01 | AD_G30_44988-ABL-DRS-DRS-5240
| TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT GOP-NRP | GH5100-4002659 | 1-GH5100-31-PRO-2659-00 | A1 | [12 empty] | 2026-08-24 | P0043931-RIN-OFCR-TRN-00120 | CODE 2-COMMENTS AS NOTED
| TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT GOP-SRP | GH5100-4002677 | 1-GH5100-31-PRO-2677-00 | A1 | 2 |  | T-276/26 | 2026-07-02 |  |  | 2026-07-06 | AD_G30_44988-ABL-DRS-APP-4541 | Y |  |  |  | 2026-07-20 | 1-GH5100-31-PRO-2677-00_CS-0536 | CLOSED
|  |  |  | 00 |  |  | T-311/26 | 2026-07-19 | [5 empty] | 2026-08-11 |  | CODE 1-NO COMMENTS
| BRIDGES INSTALLATION PROCEDURE (DLS4200) AT GOP-SRP | GH5100-4002678 | 1-GH5100-31-PRO-2678-00 | A1 | 2 |  | T-283/26 | 2026-07-06 |  |  | 2026-07-15 | AD_G30_44988-ABL-DRS-APP-4632 | Y | 2026-07-16 | 1-GH5100-31-PRO-2678-00_A1_CPY2 | CODE 2-COMMENTS AS NOTED | 2026-07-20 | 1-GH5100-31-PRO-2678-00_CS-0537 | CLOSED
|  |  |  | 00 |  |  | T-316/26 | 2026-07-22 | [5 empty] | 2026-08-11 |  | CODE 1-NO COMMENTS | 2026-08-10 | 1-GH5100-31-PRO-2678-00_CS-0537 | CLOSED

## Setup Plans & Anchor Patterns
NMDC DOC. No.: MDR-001
HAIL & GHASHA DEVELOPMENT PROJECT
|  | NMDC PROJECT NO. 2642 | [11 empty] | REVISION : | 0 |  |  |  | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [8 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM ABL-MWS |  |  | FROM COMPANY |  |  | STATUS FROM RINA
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | REF | DATE | CODE | REF | DATE | CODE
| SAFEEN3000 ANCHOR PATTERN FOR MIDLINE TIEIN 34'' GOP-SRP TO OOP (HG-SP-28) | CF0000-4002524 | 1-CF0000-31-DWG-2524 | A1 |  |  | T-286/26 | 2026-07-07 |  |  | 2026-08-10 | AD-G30-44988-DRS-APP-5012 | Y
| SAFEEN3000 ANCHOR PATTERN FOR MIDLINE TIEIN 16'' GOP-SRP TO OOP (GH-SP-30) | CF0000-4002525 | 1-CF0000-31-DWG-2525 | A1 |  |  | T-494/25 | 2025-09-24 | 2025-09-24 | e-mail | 2025-10-08 | AD-G30-44988-DRS-APP-1479 | Y | HGDP-OFCR-00-TRN-007210 | 2025-10-06 | Code-2
|  |  |  | 00 |  |  | T-547/25 | 2025-10-25 | 2025-10-25 | e-mail | 2025-11-03 | AD-G30-44988-DRS-APP-1637 | Y
|  |  |  | 01 |  |  | T-564/25 | 2025-11-06 | 2025-11-07 | e-mail | 2025-11-13 | AD-G30-44988-DRS-APP-1705 | Y
| SAFEEN3000 ANCHOR PATTERN FOR MIDLINE TIEIN 12'' GOP-SRP TO OOP (HG-SP-31) | CF0000-4002526 | 1-CF0000-31-DWG-2526 | A1 |  |  | T-494/25 | 2025-09-24 | 2025-09-24 | e-mail | 2025-10-08 | AD-G30-44988-DRS-APP-1480 | Y | HGDP-OFCR-00-TRN-007210 | 2025-10-06 | Code-2
|  |  |  | 00 |  |  | T-547/25 | 2025-10-25 | 2025-10-25 | e-mail | 2025-11-03 | AD-G30-44988-DRS-APP-1638 | Y
|  |  |  | 01 |  |  | T-564/25 | 2025-11-06 | 2025-11-07 | e-mail
|  |  |  | 02 |  |  | T-286/26 | 2026-07-07 |  |  | 2026-07-09 | AD-G30-44988-DRS-APP-4591 | Y
| SAFEEN3000 ANCHOR PATTERN FOR MIDLINE TIEIN 16'' GOP-SRP TO OOP (HG-SP-32) | CF0000-4002527 | 1-CF0000-31-DWG-2527 | A1 |  |  | T-494/25 | 2025-09-24 | 2025-09-24 | e-mail | 2025-10-08 | AD-G30-44988-DRS-APP-1481 | Y | HGDP-OFCR-00-TRN-007210 | 2025-10-06 | Code-2
|  |  |  | 00 |  |  | T-547/25 | 2025-10-25 | 2025-10-25 | e-mail | 2025-11-03 | AD-G30-44988-DRS-APP-1639 | Y
|  |  |  | 01 |  |  | T-564/25 | 2025-11-06 | 2025-11-06 | e-mail | 2025-11-12 | AD-G30-44988-DRS-APP-1690 | Y
| SAFEEN-3000 PASSAGE PLAN TO GHASHA FIELD | CF0000-4002571 | 1-CF0000-31-GAS-2571 | A1 |  |  | T-278/25 | 2025-06-19 | 2025-06-19
| SAFEEN3000 ANCHOR PATTERN-DC/1 JACKET, TOP SIDE & BRIDGE INSTALLATION | GH0100-4002499 | 1-GH0100-31-DWG-2499 | E1 |  |  | T-523/24 | 2024-10-24
|  |  |  | A1 |  |  | T-290/25 | 2025-06-25 | 2025-06-25 | e-mail | 2025-07-22 | [6 empty] | 2025-07-23 | CODE 1-NO COMMENTS
|  |  |  | 00 |  |  | T-411/25 | 2025-08-15 | [6 empty] | 2025-08-20
|  |  |  | 01 |  |  | T-089/26 | 2026-02-27 |  |  | 2026-03-12 | AD-G30-44988-DRS-APP-2844
|  |  |  | 01 |  |  | T-132/26 | 2026-03-31 |  |  | 2026-04-22 | AD-G30-44988-ABL-DRS-APP-3413 | Y
| SAFEEN3000 ANCHOR PATTERN-DC1 RISER/SPOOL INSTALLATION | GH0100-4002500 | 1-GH0100-31-DWG-2500 | A1 |  |  | T-089/26 | 2026-02-27
| SAFEEN-3000 ANCHOR PATTERN-DC1 RISER/SPOOL INSTALLATION | GH0100-4002581 | 1-GH0100-31-DWG-2581-00 | A1 |  |  | T-096/26 | 2026-03-04 |  |  | 2026-03-12 | AD-G30-44988-DRS-DRS-2849 | CODE 2-COMMENTS AS NOTED
|  |  |  | 00 |  |  | T-266/26 | 2026-06-25 |  | e-mail | 2026-07-08 | AD-G30-44988-ABL-DRS-APP-4563 | Y
[11 empty] | 2026-08-11 | AD-G30-44988-ABL-DRS-APP-4707 | Y
| SAFEEN3000 ANCHOR PATTERN-DC/1 JACKET, TOP SIDE & BRIDGE INSTALLATION | GH5100-4002461 |  | E1 |  |  | T-523/24 | 2024-10-24 | 2024-10-28
| SAFEEN3000 ANCHOR PATTERN-DC/4 JACKET INSTALLATION | GH0400-4002481 | 1-GH0400-31-DWG-2481 | E1 |  |  | T-524/24 | 2024-10-25 | 2024-10-25
|  |  |  | A1 |  |  | T-157/25 | 2025-05-07 |  |  | 2025-05-27 |  | CODE 2-COMMENTS AS NOTED |  |  |  | AD_G30_44988-ABL-DRS-DRS-0598 | 2025-06-12 | 2. Action Required
|  |  |  | 00 |  |  | T-276/25 | 2025-06-21
|  |  |  | 01 |  |  | T-365/25 | 2025-07-21
|  |  |  | 00 |  |  | T-392/25 | 2025-08-06
| SAFEEN300 ANCHOR PATTERN-DC/4 TOP-SIDE & BRIDGE INSTALLATION | GH0400-4002482 | 1-GH0400-31-DWG-2482 | A1 |  |  | T-073/26 | 2026-02-23 | [5 empty] | 1-GH0400-31-DWG-2482-00_A1_CPY2 | 2026-02-23 | CODE 2-COMMENTS AS NOTED
| SAFEEN3000 ANCHOR PATTERN-DC/4 BRIDGE INSTALLATION | GH0400-4002497 | 1-GH0400-31-DWG-2497 | A1 |  |  | T-073/26 | 2026-02-23 | [5 empty] | 1-GH0400-31-DWG-2497-00_A1_CPY2 | 2026-02-23 | CODE 2-COMMENTS AS NOTED
| SAFEEN3000 ANCHOR PATTERN DURING RISER/SPOOL INSTALLATION AT DC/4 | GH0400-4002498 | 1-GH0400-31-DWG-2498 | A1 |  |  | T-073/26 | 2026-02-23 | [5 empty] | 1-GH0400-31-DWG-2498-00_A1_CPY2 | 2026-02-23 | CODE 2-COMMENTS AS NOTED
| DLS4200 ANCHOR PATTERN FOR RISER-SPOOL INSTALLATION AT DC4 | GH0400-4002605 | 1-GH0400-31-DWG-2605 | A1 |  |  | T-254/26 | 2026-06-20 |  |  | 2026-07-03 | AD-G30-44988-DRS-DRS-4481 | CODE 2-COMMENTS AS NOTED | 1-GH0400-31-DWG-2605-00_A1_CPY2 | 2026-07-08 | CODE 2-COMMENTS AS NOTED
[11 empty] | 2026-07-14 | AD-G30-44988-DRS-DRS-4608
[11 empty] | 2026-08-19 | AD-G30-44988-DRS-APP-5086
|  |  |  | 00 |  |  | T-293/26 | 2026-07-09
|  |  |  | 00 |  |  | T-359/26 | 2026-08-21 |  |  | 2026-09-01 | AD-G30-44988-DRS-APP-5226
| DLS4200 ANCHOR PATTERN FOR TOPSIDE INSTALLATION AT DC4 | GH0400-4002606 | 1-GH0400-31-DWG-2606 | A1 |  |  | T-254/26 | 2026-06-20 |  |  | 2026-07-03 | AD-G30-44988-DRS-DRS-4482 | CODE 2-COMMENTS AS NOTED | 1-GH0400-31-DWG-2606-00_A1_CPY | 2026-07-08 | CODE 2-COMMENTS AS NOTED
[11 empty] | 2026-07-14 | AD-G30-44988-DRS-DRS-4609
|  |  |  | A1 | [6 empty] | 2026-08-19 | AD-G30-44988-DRS-APP-5087
|  |  |  | 00 |  |  | T-293/26 | 2026-07-09
|  |  |  | 00 |  |  | T-359/26 | 2026-08-21
|  |  |  | 00 |  |  | T-367/26 | 2026-08-25
| DLS4200 ANCHOR PATTERN FOR BRIDGE INSTALLATION AT DC4 | GH0400-4002607 | 1-GH0400-31-DWG-2607 | A1 |  |  | T-254/26 | 2026-06-20 |  |  | 2026-07-03 | AD-G30-44988-DRS-DRS-4483 | CODE 2-COMMENTS AS NOTED | 1-GH0400-31-DWG-2607-00_A1_CPY2 | 2026-07-08 | CODE 2-COMMENTS AS NOTED
[11 empty] | 2026-07-14 | AD-G30-44988-DRS-DRS-4610
[11 empty] | 2026-08-19 | AD-G30-44988-DRS-APP-5088
|  |  |  | 00 |  |  | T-293/26 | 2026-07-09
|  |  |  | 00 |  |  | T-359/26 | 2026-08-21
|  |  |  | 00 |  |  | T-367/26 | 2026-08-25
| SAFEEN3000 ANCHOR PATTERN-GOP-SWI TOP SIDE INSTALLATION | GH5100-4002462 | 1-GH5100-31-DWG-2462-00 | A1 |  |  | T-089/26 | 2026-02-27 |  |  | 2026-03-13 | AD-G30-44988-DRS-APP-2845 | CODE 2-COMMENTS AS NOTED | 1-GH5100-31-DWG-2462-00_A1_CPY2 | 2026-02-23 | CODE 2-COMMENTS AS NOTED
| SAFEEN3000 ANCHOR PATTERN-GOP-SWI BRIDGE INSTALLATION | GH5100-4002463 | 1-GH5100-31-DWG-2463-00 | A1 |  |  | T-089/26 | 2026-02-27 |  |  | 2026-03-13 | AD-G30-44988-DRS-APP-2846 | CODE 2-COMMENTS AS NOTED | 1-GH5100-31-DWG-2463-00_A1_CPY2 | 2026-02-23 | CODE 2-COMMENTS AS NOTED
| SAFEEN3000 ANCHOR PATTERN-GOP-NRP TOP-SIDE INSTALLATION | GH5100-4002471 | 1-GH5100-31-DWG-2471-00 | A1 |  |  | T-073/26 | 2026-02-23 | [5 empty] | 1-GH5100-31-DWG-2471-00_A1_CPY2. | 2026-02-23 | CODE 2-COMMENTS AS NOTED
| SAFEEN3000 ANCHOR PATTERN-GOP-NRP EAST BRIDGE INSTALLATION | GH5100-4002472 | 1-GH5100-31-DWG-2472-00 | A1 |  |  | T-073/26 | 2026-02-23 | [5 empty] | 1-GH5100-31-DWG-2472-00_A1_CPY2 | 2026-02-23 | CODE 2-COMMENTS AS NOTED
| SAFEEN3000 ANCHOR PATTERN-GOP-NRP WEST BRIDGE INSTALLATION | GH5100-4002473 | 1-GH5100-31-DWG-2473-00 | A1 |  |  | T-073/26 | 2026-02-23
| SAFEEN3000 ANCHOR PATTERN-GOP-NRP RISER/SPOOL INSTALLATION | GH5100-4002474 | 1-GH5100-31-DWG-2474-00 | A1 |  |  | T-073/26 | 2026-02-23 | [5 empty] | 1-GH5100-31-DWG-2474-00_A1_CPY2 | 2026-02-23 | CODE 2-COMMENTS AS NOTED
| SAFEEN3000 ANCHOR PATTERN-FLARE TOP SIDE INSTALLATION | GH5100-4002476 | 1-GH5100-31-DWG-2476-00 | A1 |  |  | T-073/26 | 2026-02-23 |  |  | 2026-03-13 | AD-G30-44988-DRS-DRS-2850 | CODE 2-COMMENTS AS NOTED
| SAFEEN3000 ANCHOR PATTERN-FLARE BRIDGE INSTALLATION | GH5100-4002477 | 1-GH5100-31-DWG-2477-00 | A1 |  |  | T-073/26 | 2026-02-23 |  |  | 2026-03-13 | AD-G30-44988-DRS-DRS-2851 | CODE 2-COMMENTS AS NOTED | 1-GH5100-31-DWG-2477-00_A1_CPY2 | 2026-02-23 | CODE 2-COMMENTS AS NOTED
| SAFEEN3000 ANCHOR PATTERN - FLARE BOOM INSTALLATION | GH5100-4002580 | 1-GH5100-31-DWG-2580-00 | A1 |  |  | T-073/26 | 2026-02-23 |  |  | 2026-03-13 | AD-G30-44988-DRS-DRS-2852 | CODE 2-COMMENTS AS NOTED
| DLS4200 ANCHOR PATTERN FOR RISER-SPOOL INSTALLATION FROM DC6 AT GOP-SRP | GH5100-4002593 | 1-GH5100-31-DWG-2593-00 | A1 |  |  | T-149/26 | 2026-04-10 |  |  | 2026-05-07 | AD-G30-44988-DRS-APP-3646 | Y | 1-GH5100-31-DWG-2593-00_A1_CPY2 | 2026-04-27 | CODE 2-COMMENTS AS NOTED
|  |  |  | 00 |  |  | T-198/26 | 2026-05-08
|  |  |  | 00 |  |  | T-226/26 | 2026-05-22 |  |  | 2026-06-03 | AD-G30-44988-DRS-APP-4067 | Y
|  |  |  | 01 |  |  | T-229/26 | 2026-05-25 |  |  | 2026-06-19 | AD-G30-44988-DRS-APP-4308 | Y
| DLS4200 ANCHOR PATERN FOR RISER-SPOOL INSTALLATION FROM OPP AT GOP-SRP | GH5100-4002594 | 1-GH5100-31-DWG-2594-00 | A1 |  |  | T-149/26 | 2026-04-10 |  |  | 2026-05-07 | AD-G30-44988-ABL-DRS-APP-3647 | Y | 1-GH5100-31-DWG-2594-00_A1_CPY2 | 2026-04-27 | CODE 2-COMMENTS AS NOTED
|  |  |  | 00 |  |  | T-198/26 | 2026-05-08 | 2026-05-12 | e-mail | 2026-05-14 | AD-G30-44988-ABL-DRS-APP-3831 | Y
| DLS4200 ANCHOR PATTERN FOR TOPSIDE INSTALLATION AT GOP-SRP | GH5100-4002595 | 1-GH5100-31-DWG-2595-00 | A1 |  |  | T-265/26 | 2026-06-24 |  | e-mail | 2026-07-08 | AD-G30-44988-ABL-DRS-APP-4566 | Y | 1-GH5100-31-DWG-2595-00_A1_CPY | 2026-07-09 | CODE 1-NO COMMENTS
|  |  |  | 00 |  |  | T-298/26 | 2026-07-10 | [6 empty] | 2026-08-11 | CODE 1-NO COMMENTS
| DLS4200 ANCHOR PATTERN FOR NORTH BRIDGE INSTALLATION AT GOP-SRP | GH5100-4002596 | 1-GH5100-31-DWG-2596-00 | A1 |  |  | T-273/26 | 2026-07-01 |  |  | 2026-07-06 | AD-G30-44988-ABL-DRS-DRS-4524 | CODE 2-COMMENTS AS NOTED | 1-GH5100-31-DWG-2596-00_A1_CPY1 | 2026-07-16 | CODE 1-NO COMMENTS
[11 empty] | 2026-07-07 | AD-G30-44988-ABL-DRS-DRS-4560
[11 empty] | 2026-07-15 | AD-G30-44988-ABL-DRS-DRS-4630
|  |  |  | 00 |  |  | T-297/26 | 2026-07-10 | 2026-07-13 | e-mail |  |  |  |  | 2026-08-11 | CODE 1-NO COMMENTS
|  |  |  | X100 |  |  | T-307/26 | 2026-07-16 | 2026-07-16 | e-mail | 2026-07-20 | AD-G30-44988-ABL-DRS-APP-4679 | Y
|  |  |  | 01 |  |  | T-321/26 | 2026-07-27
| DLS4200 ANCHOR PATTERN FOR SOUTH BRIDGE INSTALLATION AT GOP-SRP | GH5100-4002597 | 1-GH5100-31-DWG-2597-00 | A1 |  |  | T-273/26 | 2026-07-01 |  | e-mail | 2026-07-08 | AD-G30-44988-ABL-DRS-APP-4571 | Y | 1-GH5100-31-DWG-2597-00_A1 | 2026-07-14 | CODE 1-NO COMMENTS
|  |  |  | 00 |  |  | T-297/26 | 2026-07-10 | [6 empty] | 2026-08-11 | CODE 1-NO COMMENTS
| DLS4200 ANCHOR PATTERN FOR RISER-SPOOL INSTALLATION AT GOP-NRP | GH5100-4002601 | 1-GH5100-31-DWG-2601-00 | A1 |  |  | T-174/26 | 2026-04-22 |  | e-mail | 2026-05-13 | AD-G30-44988-ABL-DRS-APP-3808 | Y
|  |  |  | 00 |  |  | T-263/26 | 2026-06-24 | [5 empty] | 1-GH5100-31-DWG-2601-00_00_CPY1 | 2026-07-09 | CODE 1-NO COMMENTS
|  |  |  | 01 |  |  | T-342/26 | 2026-08-11 |  |  | 2026-08-21 | AD-G30-44988-ABL-DRS-APP-5146
| DLS4200 ANCHOR PATTERN FOR TOPSIDE INSTALLATION AT GOP-NRP | GH5100-4002602 | 1-GH5100-31-DWG-2602-00 | A1 |  |  | T-174/26 | 2026-04-22 |  | e-mail | 2026-05-13 | AD-G30-44988-ABL-DRS-APP-3809 | Y | 1-GH5100-31-DWG-2602-00_A1 | 2026-08-11 | CODE 2-COMMENTS AS NOTED
|  |  |  | 00 |  |  | T-342/26 | 2026-08-11
|  |  |  | 00 |  |  | T-351/26 | 2026-08-14 |  |  | 2026-08-21 | AD-G30-44988-ABL-DRS-APP-5147 | Y
|  |  |  | 00 |  |  | T-369/26 | 2026-08-25 |  |  | 2026-08-27 | AD-G30-44988-ABL-DRS-APP-5211 | Y
| DLS4200 ANCHOR PATTERN FOR EAST BRIDGE INSTALLATION AT GOP-NRP | GH5100-4002603 | 1-GH5100-31-DWG-2603-00 | A1 |  |  | T-174/26 | 2026-04-22 |  | e-mail | 2026-05-13 | AD-G30-44988-ABL-DRS-APP-3810 | Y | 1-GH5100-31-DWG-2603-00_A1_CPY2 | 2026-08-11 | CODE 2-COMMENTS AS NOTED
|  |  |  | 00 |  |  | T-369/26 | 2026-08-25 |  |  | 2026-08-27 | AD-G30-44988-ABL-DRS-APP-5210 | Y
| DLS4200 ANCHOR PATTERN FOR WEST BRIDGE INSTALLATION AT GOP-NRP | GH5100-4002604 | 1-GH5100-31-DWG-2604-00 | A1 |  |  | T-174/26 | 2026-04-22 |  | e-mail | 2026-05-13 | AD-G30-44988-ABL-DRS-APP-3811 | Y | 1-GH5100-31-DWG-2604-00_A1_CPY2 | 2026-08-11 | CODE 2-COMMENTS AS NOTED
|  |  |  | 00 |  |  | T-369/26 | 2026-08-25 |  |  | 2026-08-27 | AD-G30-44988-ABL-DRS-APP-5212 | Y
| DLS4200 ANCHOR PATTERN FOR MSF INSTALLATION AT GOP-FLARE | GH5100-4002611 | 1-GH5100-31-DWG-2611-00 | A1 |  |  | T-256/26 | 2026-06-22 |  | e-mail | 2026-07-07 | AD-G30-44988-ABL-DRS-DRS-4556 |  | 1-GH5100-31-DWG-2611-00_A1_CPY1 | 2026-07-08 | CODE 1-NO COMMENTS
|  |  |  | 00 |  |  | T-391/26 | 2026-09-03
| DLS4200 ANCHOR PATTERN FOR BRIDGE INSTALLATION AT GOP-FLARE | GH5100-4002612 | 1-GH5100-31-DWG-2612-00 | A1 |  |  | T-256/26 | 2026-06-22 |  | e-mail | 2026-07-07 | AD-G30-44988-ABL-DRS-DRS-4557
|  |  |  | 00 |  |  | T-391/26 | 2026-09-03
| DLS4200 ANCHOR PATTERN FOR FLARE BOOM INSTALLATION AT GOP-FLARE | GH5100-4002613 | 1-GH5100-31-DWG-2613-00 | A1 |  |  | T-256/26 | 2026-06-22 |  | e-mail | 2026-07-07 | AD-G30-44988-ABL-DRS-DRS-4558 |  | 1-GH5100-31-DWG-2613-00_A1_CPY1 | 2026-07-08 | CODE 1-NO COMMENTS
|  |  |  | 00 |  |  | T-391/26 | 2026-09-03
| DLS4200 ANCHOR PATTERN FOR TOPSIDE INSTALLATION AT GOP-SWI | GH5100-4002614 | 1-GH5100-31-DWG-2614-00 | A1 |  |  | T-253/26 | 2026-06-22 |  | e-mail | 2026-07-07 | AD-G30-44988-ABL-DRS-DRS-4552 |  | 1-GH5100-31-DWG-2614-00_A1_cpy2 | 2026-08-11 | CODE 2-COMMENTS AS NOTED
[11 empty] | 2026-08-21 | AD-G30-44988-ABL-DRS-DRS-5162
|  |  |  | 00 |  |  | T-294/26 | 2026-07-09
| DLS4200 ANCHOR PATTERN FOR BRIDGE INSTALLATION AT GOP-SWI | GH5100-4002615 | 1-GH5100-31-DWG-2615-00 | A1 |  |  | T-253/26 | 2026-06-22 |  | e-mail | 2026-07-07 | AD-G30-44988-ABL-DRS-DRS-4553 |  | 1-GH5100-31-DWG-2615-00_A1_cpy2 | 2026-08-11 | CODE 2-COMMENTS AS NOTED
[11 empty] | 2026-08-21 | AD_G30_44988-ABL-DRS-APP-5161
| DLS4200 ANCHOR PATTERN FOR SEAWATER OUTFALL SPOOLS INSTALLATION AT GOP-SWI | GH5100-4002616 | 1-GH5100-31-DWG-2616-00 | A1 |  |  | T-253/26 | 2026-06-22 |  | e-mail | 2026-07-07 | AD-G30-44988-ABL-DRS-DRS-4554 |  | 1-GH5100-31-DWG-2616-00_A1_CPY2 | 2026-08-11 | CODE 2-COMMENTS AS NOTED
[11 empty] | 2026-08-21 | AD_G30_44988-ABL-DRS-APP-5160
| DLS4200 ANCHOR PATTERN FOR MIDLINE TIEIN 34" GOP-SRP TO OOP (HG-SP-28) | GH5100-4002617 | 1-GH5100-31-DWG-2617-00 | A1 |  |  | T-152/26 | 2026-04-15
|  |  |  | A1 |  |  | T-376/26 | 2026-08-26 |  |  | 2026-09-04 | AD_G30_44988-ABL-DRS-APP-5298
|  |  |  | 00 |  |  | T-397/26 | 2026-09-08
| DLS4200 ANCHOR PATTERN FOR MIDLINE TIEIN 12" GOP-SRP TO OOP (HG-SP-31) | GH5100-4002618 | 1-GH5100-31-DWG-2618-00 | A1 |  |  | T-152/26 | 2026-04-15
|  |  |  | A1 |  |  | T-376/26 | 2026-08-26 |  |  | 2026-09-04 | AD_G30_44988-ABL-DRS-APP-5299
|  |  |  | 00 |  |  | T-397/26 | 2026-09-08
| SAFEEN3000 SET-UP PLAN AT GOP-SRP TOP SIDE INSTALLATION | GH5100-4002619 | 1-GH5100-31-DWG-2619-00 | A1 |  |  | T-143/26 | 2026-04-07 |  | e-mail | 2026-05-07 | AD_G30_44988-ABL-DRS-APP-3637 | Y | 1-GH5100-31-DWG-2619-00_A1_CPY1 | 2026-04-21 | CODE 1-NO COMMENTS
|  |  |  | 00 |  |  | T-198/26 | 2026-05-08 | 2026-05-12 | e-mail | 2026-05-14 | AD_G30_44988-ABL-DRS-APP-3840 | Y
| SAFEEN3000 SET-UP PLAN AT GOP-SRP NORTH BRIDGE INSTALLATION | GH5100-4002620 | 1-GH5100-31-DWG-2620-00 | A1 |  |  | T-143/26 | 2026-04-07 |  |  | 2026-05-07 | AD_G30_44988-ABL-DRS-APP-3638 | Y | 1-GH5100-31-DWG-2620-00_A1_CPY2 | 2026-04-07 | CODE 2-COMMENTS AS NOTED
|  |  |  | 00 |  |  | T-198/26 | 2026-05-08 | 2026-05-12 | e-mail | 2026-05-14 | AD_G30_44988-ABL-DRS-APP-3841 | Y
| SAFEEN3000 SET-UP PLAN AT GOP-SRP SOUTH BRIDGE INSTALLATION | GH5100-4002621 | 1-GH5100-31-DWG-2621-00 | A1 |  |  | T-143/26 | 2026-04-07 |  |  | 2026-05-07 | AD_G30_44988-ABL-DRS-APP-3639 | Y | 1-GH5100-31-DWG-2621-00_A1_CPY1 | 2026-04-21 | CODE 1-NO COMMENTS
|  |  |  | 00 |  |  | T-198/26 | 2026-05-08 | 2026-05-12 | e-mail | 2026-05-14 | AD_G30_44988-ABL-DRS-APP-3842 | Y
| SAFEEN3000 ANCHOR PATTERN-DC/6 JACKET INSTALLATION | GH0600-4002478 | 1-GH0600-31-DWG-2478 | E1 |  |  | T-525/24 | 2024-10-25 | 2024-10-29
|  |  |  | A1 |  |  | T-157/25 | 2025-05-07 |  |  | 2025-05-25 |  | CODE 2-COMMENTS AS NOTED |  |  |  | AD_G30_44988-ABL-DRS-APP-0515 | 2025-05-28 | 3. An observation which requires no action
|  |  |  | 00 |  |  | T-232/25 | 2025-06-02 |  |  |  |  | CODE 2-COMMENTS AS NOTED |  |  |  | AD_G30_44988-ABL-DRS-APP-0567 | 2025-06-10 | 3. Approved
|  |  |  | 01 |  |  | T-281/25 | 2025-06-21
|  |  |  | 01 |  |  | T-295/25 | 2025-06-25 | 2025-06-25 | e-mail
| JACKUP SETUP ON GOP-SRP FOR HOOK-UP ACTIVITIES | GH5100-4002531 | 1-GH5100-31-DWG-2531 | A1 |  |  | T-114/26 | 2026-03-16 |  |  | 2026-04-06 | AD_G30_44988-ABL-DRS-DRS-3108 | N | 1-GH5100-31-DWG-2531-00_A1_CPY2 | 2026-03-26 | CODE 2-COMMENTS AS NOTED
| SAFEEN3000 ANCHOR PATTERN-DC/6 TOP-SIDE & BRIDGE INSTALLATION | GH0600-4002479 | 1-GH0600-31-DWG-2479 | A1 |  |  | T-035/26 | 2026-01-25 |  |  | 2026-03-30 | AD_G30_44988-ABL-DRS-APP-3071 | Y
|  |  |  | 00 |  |  | T-119/26 | 2026-03-18
| SAFEEN3000 ANCHOR PATTERN-DC/6 RISER/SPOOL INSTALLATION | GH0600-4002480 | 1-GH0600-31-DWG-2480 | A1 |  |  | T-035/26 | 2026-01-25 |  |  | 2026-03-30 | AD_G30_44988-ABL-DRS-APP-3072 | Y
|  |  |  | 00 |  |  | T-119/26 | 2026-03-18
| JACKUP SETUP ON DC6 FOR HOOK-UP ACTIVITIES | GH0600-4002537 | 1-GH0600-31-DWG-2537 | A1 |  |  | T-114/26 | 2026-03-16 |  |  | 2026-04-06 | AD_G30_44988-ABL-DRS-DRS-3107 | N | 1-GH0600-31-DWG-2537-00_A1_CPY2 | 2026-03-26 | CODE 2-COMMENTS AS NOTED
| DLS4200 ANCHOR PATTERN FOR RISER-SPOOL INSTALLATION AT DC6 | GH0600-4002598 | 1-GH0600-31-DWG-2598 | A1 |  |  | T-174/26 | 2026-04-22 |  |  | 2026-05-01 | AD_G30_44988-ABL-DRS-APP-3685 | Y
|  |  |  | 00 |  |  | T-233/26 | 2026-06-03 |  |  | 2026-06-12 | AD_G30_44988-ABL-DRS-APP-4252 | Y |  | 2026-08-11 | CODE 1-NO COMMENTS
| DLS4200 ANCHOR PATTERN FOR TOPSIDE & BRIDGE INSTALLATION AT DC6 | GH0600-4002600 | 1-GH0600-31-DWG-2600 | A1 |  |  | T-174/26 | 2026-04-22 |  |  | 2026-05-08 | AD_G30_44988-ABL-DRS-APP-3686 | Y
|  |  |  | 00 |  |  | T-262/26 | 2026-06-24 | 2026-06-24 | e-mail | 2026-07-06 | AD_G30_44988-ABL-DRS-APP-4506 | Y | 1-GH0600-31-DWG-2600-00_00_CPY1 | 2026-07-08 | CODE 1-NO COMMENTS
| SAFEEN3000 ANCHOR PATTERN-GOP-SW1 JACKET INSTALLATION | GH5100-4002461 | 1-GH5100-31-DWG-2461 | E1 |  |  | T-523/24 | 2024-10-24 | 2024-10-25 |  |  |  | Rejected
|  |  |  | A1 |  |  | T-293/25 | 2025-06-25
|  |  |  | 00 |  |  | T-422/25 | 2025-05-22 |  |  | 2026-09-29 | AD_G30_44988-ABL-DRS-APP-1378 | Y
|  |  |  | 01 |  | cancelled | T-520/25 | 2025-10-10
|  |  |  | 01 |  |  | T-525/25 | 2025-10-16 |  |  | 2025-10-16 | AD-G30-44988-DRS-APP-1509
| SAFEEN3000 ANCHOR PATTERN -GOP-SRP JACKET INSTALLATION | GH5100-4002464 | 1-GH5100-31-DWG-2464 | A1 |  |  | T-488/24 | 2024-10-03 | 2024-10-04 |  | 2024-11-21 |  | CODE 2-COMMENTS AS NOTED
|  |  |  | A2 |  |  | T-159/25 | 2025-04-28 |  |  | 2025-05-23
|  |  |  | 00 |  |  | T-322/25 | 2025-07-03
|  |  |  | 00 |  |  | T-393/25 | 2025-08-06
| SAFEEN3000 ANCHOR PATTERN -GOP-SRP TOP SIDE INSTALLATION | GH5100-4002465 | 1-GH5100-31-DWG-2465 | E1 |  |  | T-488/24 | 2024-10-03 | 2024-10-04 |  | 2024-11-21
| SAFEEN3000 ANCHOR PATTERN-GOP-SRP TOP SIDE INSTALLATION | GH5100-4002465 | 1-GH5100-31-DWG-2465 | A1 |  |  | T-035/26 | 2026-01-25 |  |  | 2026-02-10 | AD-G30-44988-DRS-APP-2479 | Y
|  |  |  | 00 |  |  | T-113/26 | 2026-03-18 |  |  | 2026-03-30 | AD-G30-44988-DRS-APP-3073 | Y
|  |  |  | CN |  |  | T-139/26 | 2026-04-02
| SAFEEN3000 ANCHOR PATTERN-GOP-SRP NORTH BRIDGE INSTALLATION | GH5100-4002466 | 1-GH5100-31-DWG-2466 | A1 |  |  | T-035/26 | 2026-01-25 |  |  | 2026-02-10 | AD-G30-44988-DRS-APP-2475
|  |  |  | 00 |  |  | T-113/26 | 2026-03-18 |  |  | 2026-03-30 | AD-G30-44988-DRS-DRS-3058
|  |  |  | CN |  |  | T-139/26 | 2026-04-02
| SAFEEN3000 ANCHOR PATTERN-GOP-SRP SOUTH BRIDGE INSTALLATION | GH5100-4002467 | 1-GH5100-31-DWG-2467 | A1 |  |  | T-035/26 | 2026-01-25 |  |  | 2026-02-10 | AD-G30-44988-DRS-APP-2476 | Y | 1-GH5100-31-DWG-2476-00_A1_CPY2 | 2026-02-23 | CODE 2-COMMENTS AS NOTED
|  |  |  | 00 |  |  | T-113/26 | 2026-03-18 |  |  | 2026-03-30 | AD-G30-44988-DRS-DRS-3059
|  |  |  | CN |  |  | T-139/26 | 2026-04-02
| SAFEEN3000 ANCHOR PATTERN-GOP-SRP RISER/ SPOOL INSTALLATION FROM DC6 | GH5100-4002468 | 1-GH5100-31-DWG-2468 | A1 |  |  | T-035/26 | 2026-01-25 |  |  | 2026-02-10 | AD-G30-44988-DRS-APP-2477 | Y | 1-GH5100-31-DWG-2468-00_00_CPY1 | 2026-03-24 | CODE 1-NO COMMENTS
|  |  |  | 00 |  |  | T-113/26 | 2026-03-18 |  |  | 2026-03-30 | AD-G30-44988-DRS-APP-3067 | Y
| SAFEEN3000 ANCHOR PATTERN-GOP-SRP RISER/ SPOOL INSTALLATION FROM OPP | GH5100-4002469 | 1-GH5100-31-DWG-2469 | A1 |  |  | T-035/26 | 2026-01-25 |  |  | 2026-02-10 | AD-G30-44988-DRS-APP-2478 | Y | 1-GH5100-31-DWG-2469-00_00_CPY1 | 2026-04-09 | CODE 1-NO COMMENTS
|  |  |  | 00 |  |  | T-113/26 | 2026-03-18 |  |  | 2026-03-30 | AD-G30-44988-DRS-APP-3068 | Y
| SAFEEN3000 ANCHOR PATTERN-GOP-NRP JACKET INSTALLATION | GH5100-4002470 | 1-GH5100-31-DWG-2470 | A1 |  |  | T-170/25 | 2025-04-30 |  |  | 2025-05-23 | AD_G30_44988-ABL-DRS-app-1087 | Y
|  |  |  | 00 |  |  | T-414/25 | 2025-08-18
|  |  |  | 01 |  |  | T-464/25 | 2025-09-10
|  |  |  | 01 |  |  | T-472/25 | 2025-09-18 |  |  | 2025-09-25 | AD_G30_44988-ABL-DRS-app-1338 | Y
|  |  |  | 02 |  |  | T-504/25 | 2025-09-30 | 2025-09-30 | e-mail | 2025-10-03 | AD_G30_44988-ABL-DRS-app-1393 | Y
|  |  |  | 03 |  |  | T-537/25 | 2025-10-21
| SAFEEN3000 ANCHOR PATTERN-GOP-NRP WEST BRIDGE INSTALLATION | GH5100-4002473 | 1-GH5100-31-DWG-2473 | A1 |  |  | T-073/26 | 2026-02-23 | [5 empty] | 1-GH5100-31-DWG-2473-00_A1_CPY2 | 2026-02-23 | CODE 2-COMMENTS AS NOTED
| SAFEEN3000 ANCHOR PATTERN - FLARE JACKET INSTALLATION | GH5100-4002475 | 1-GH5100-31-DWG-2475 | A1 |  |  | T-291/25 | 2025-06-25 | 2025-06-25 | e-mail | 2025-08-22 | AD_G30_44988-ABL-DRS-DRS-0985 | 2
|  |  |  | 00 |  |  | T-408/25 | 2025-08-13
|  |  |  | 00 |  |  | T-445/25 | 2025-09-02 | 2025-09-03 | e-mail | 2025-09-10 | AD_G30_44988-ABL-DRS-APP-1135 | Y |  | 2025-09-17 | 1. No comments
| SAFEEN-3000 SETUP FOR FRAME REMOVAL AT GOP SRP | GH5100-4002554 | 1-GH5100-31-DWG-2554 | A1 |  |  | T-137/25 | 2025-05-01
|  |  |  | 00 |  |  | T-446/25 | 2025-09-02 | 2025-09-03 | e-mail
|  |  |  | 01 |  |  | T-468/25 | 2025-09-11
| LIFTING DRAWING FOR FRAME REMOVAL AT GOP-SRP | GH5100-4002556 |  | A1
| SAFEEN-3000 ANCHOR PATTERN DURING CLQ JACKET & TOPSIDE INSTALLATION | GH6000-4002500 | 1-GH6000-31-DWG-2500 | A1 |  |  | T-155/25 | 2025-04-28 |  |  | 2025-05-23 |  | CODE 2-COMMENTS AS NOTED |  |  |  | AD_G30_44988-ABL-DRS-DRS-0516 | 2025-05-28 | 2-The comment require action
[14 empty] | 1-GH6000-31-DWG-2500-00_02_CPY2 | 2026-03-11 | CODE 2-COMMENTS AS NOTED | AD_G30_44988-ABL-DRS-APP-0576 | 2025-06-11 | 2-The comment require action
|  |  |  | 00 |  |  | T-256/25 | 2025-06-13 | [8 empty] | AD_G30_44988-ABL-DRS-APP-0627 | 2025-06-17 | 2-The comment require action
|  |  |  | 01 |  |  | T-315/25 | 2025-07-03 | 2025-07-04 | e-mail | 2025-07-16 |  | CODE 2-COMMENTS AS NOTED |  |  |  |  | 2025-07-23
|  |  |  | 2 |  |  | T-073/26 | 2026-02-23
| DLS4200 ANCHOR PATTERN FOR TOPSIDE INSTALLATION AT CLQ | GH6000-4002610 | 1-GH6000-31-DWG-2610-00 | A1 |  |  | T-255/26 | 2026-06-20 |  | e-mail | 2026-07-07 | AD_G30_44988-ABL-DRS-DRS-4556 |  | 1-GH6000-31-DWG-2610-00_A1_CPY1 | 2026-08-12 | 1. No comments
|  |  |  | 00 |  |  | T-391/26 | 2026-09-03

## Sketches
NPCC DOC. No.:
HAIL & GHASHA DEVELOPMENT PROJECT
|  | NMDC PROJECT NO. 2642 | [6 empty] | REVISION : |  | 0
|  | OFFSHORE Sketches | [6 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| (SAFEEN-3000 AP during Frame Removal at GOP) | 2642-A1-0091 |  | A |  |  | 2025-03-22 | SKV
| SAFEEN-3000 ANCHOR PATTERN DURING CLQ JACKET & TOPSIDE INSTALLATION | 1-GH6000-31-DWG-2500-01_A |  | A |  |  | 2025-04-22 | SKV
| safeen 3000 ANCHOR PATTERN DURING DC4 JACKET INSTALLATION | 1-GH0400-31-DWG-2481-00_A2 |  | A2 |  |  | 2025-04-23 | SKV
| safeen 3000 ANCHOR PATTERN DURING DC6 JACKET INSTALLATION | 1-GH0600-31-DWG-2478-00_A2 |  | A2 |  |  | 2025-04-23 | SKV
| safeen 3000 ANCHOR PATTERN -GOP-SRP JACKET INSTALLATION | 1-GH5100-31-DWG-2464-00_A2 |  | A2 |  |  | 2025-04-23 | SKV
| safeen 3000 ANCHOR PATTERN -GOP-NRP JACKET INSTALLATION | 1-GH5100-31-DWG-2470-00_A1 |  | A1 |  |  | 2025-04-28 | SKV
| SAFEEN-3000 ANCHOR PATTERN DURING CLQ JACKET & TOPSIDE INSTALLATION | 1-GH6000-31-DWG-2500-00_00 |  | 00 |  |  | 2025-05-28 | SKV
| SAFEEN-3000 ANCHOR PATTERN DURING CLQ JACKET & TOPSIDE INSTALLATION | 1-GH6000-31-DWG-2500-00_00 |  | 00 |  |  | 2025-05-30 | SKV
| safeen 3000 ANCHOR PATTERN DURING DC4 JACKET INSTALLATION | 1-GH0400-31-DWG-2481-00_00 |  | 00 |  |  | 2025-06-18 | SKV
| (SAFEEN-3000 AP during GOP-NRP JKT installation) | 1-GH5100-31-DWG-2470-00 |  | 00 |  |  | 2025-07-01 | SKV
| 1-GH5100-31-DWG-2464-00_00_study-1 | 1-GH5100-31-DWG-2464-00_00_study-1 |  | 00 |  |  | 2025-07-21 | EJJ
| SAFEEN-3000 ANCHOR PATTERN FOR FRAME REMOVAL AT GOP SRP | 1-GH5100-31-DWG-2554-01_00-STUDY |  | 00 |  |  | 2025-09-01 | SKV
|  | 1-GH5100-31-DWG-2554-01_00 |  | 0 |  |  | 2025-09-02 | SKV
|  | 1-GH0600-31-DWG-2480-01_A1 |  | A1 |  |  | 2026-01-19 | SKV
|  | 1-GH0600-31-DWG-2479-01_A1 |  | A1 |  |  | 2026-01-19 | SKV
|  | 1-GH5100-31-DWG-2468-01_A1 |  | A1 |  |  | 2026-01-19 | SKV
|  | 1-GH5100-31-DWG-2466-01_A1 |  | A1 |  |  | 2026-01-19 | SKV
|  | 1-GH5100-31-DWG-2469-01_A1 |  | A1 |  |  | 2026-01-19 | SKV
|  | 1-GH5100-31-DWG-2467-01_A1 |  | A1 |  |  | 2026-01-19 | SKV
|  | 1-GH5100-31-DWG-2465-01_A1 |  | A1 |  |  | 2026-01-19 | SKV
|  | 1-GH6000-31-DWG-2500-02_A1 |  | A1 |  |  | 2026-01-27 | SKV
|  | 1-GH5100-31-DWG-2477-01_A1 |  | A1 |  |  | 2026-01-27 | SKV
|  | 1-GH5100-31-DWG-XXXX-01_A1 |  | A1 |  |  | 2026-01-27 | SKV
|  | 1-GH5100-31-DWG-2476-01_A1 |  | A1 |  |  | 2026-01-27 | SKV
| SAFEEN3000 ANCHOR PATTERN-GOP-NRP TOP-SIDE INSTALLATION | 1-GH5100-31-DWG-2472-01_A1 |  | A1 |  |  | 2026-01-30 | SKV
| SAFEEN3000 ANCHOR PATTERN-GOP-NRP EAST BRIDGE INSTALLATION | 1-GH5100-31-DWG-2474-01 TO 04_A1 |  | A1 |  |  | 2026-01-30 | SKV
| SAFEEN3000 ANCHOR PATTERN-GOP-NRP WEST BRIDGE INSTALLATION | 1-GH5100-31-DWG-2471-01 TO 03_A1 |  | A1 |  |  | 2026-01-30 | SKV
| SAFEEN3000 ANCHOR PATTERN-GOP-NRP RISER/SPOOL INSTALLATION | 1-GH5100-31-DWG-2473-01 TO 02_A1 |  | A1 |  |  | 2026-01-30 | SKV
| SAFEEN300 ANCHOR PATTERN-DC/4 TOP-SIDE & BRIDGE INSTALLATION | GH0400-4002482 |  | A1 |  |  | 2026-02-06 | SKV
| SAFEEN3000 ANCHOR PATTERN-DC/4 BRIDGE INSTALLATION | GH0400-4002497 |  | A1 |  |  | 2026-02-06 | SKV
| SAFEEN3000 ANCHOR PATTERN DURING RISER/SPOOL INSTALLATION AT DC/4 | GH0400-4002498 |  | A1 |  |  | 2026-02-06 | SKV
| SAFEEN3000 ANCHOR PATTERN-GOP-SRP TOPSIDE INSTALLATION | 1-GH5100-31-DWG-2465-00_00 |  | 0 |  |  | 2026-03-25 | SKV
| 2642-A1-0094_Rev-B (Counter Weight skid location - GOP ISLAND) | 2642-A1-0094 |  | B |  |  | 2026-04-24 | SKV
| 2642-A1-0095_Rev-A (Counter Weight skid location - DC6 ISLAND) | 2642-A1-0095 |  | A |  |  | 2026-04-24 | SKV
| 210 OBSTACLE FREE SECTOR FOR HELICOPTER APPROACH | 2642-A1-0096-00_A |  | A |  |  | 2026-05-20 | SKV
| DLS4200 GANGWAY 20m LIFTING AND INSTALLATION AT DC6 PLATFORM | OFO-P2642-SK-T-107 |  | A1 |  |  | 2026-06-01 | REY