## Installation Procedures
NMDC DOC. No.: MDR-001
EPC WORKS FOR 20” MOL FROM UMM LULU TO ZIRKU ISLAND
|  | NMDC PROJECT NO. 2683 | [11 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2026-08-21
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | 2683-PP-OF-001 | AD-473-G-01051 | A1 |  | 2024-02-09 | T-063/24 | 2024-02-09
|  |  |  | 1 |  |  | T-082/24 | 2024-02-16 | 2024-02-19 | 2683-NPCC-AO-PMT-T-00202 | 2024-03-13 | E1941-AOF-NPCC-PMT-TR-00130 | 5 - Rejected
|  |  |  | 2 |  |  | T-129/24 | 2024-03-22 | 2024-03-22 | 2683-NPCC-AO-PMT-T-00241 | 2024-03-26 | E1941-AOF-NPCC-PMT-TR-00143 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-153/24 | 2024-04-05 | 2024-04-16 | 2683-NPCC-AO-PMT-T-00264 | 2024-04-23 | E1941-AOF-NPCC-PMT-TR-00155 | 1 - Approved
|  |  |  | 4 |  |  | T-177/24 | 2024-04-29 | 2024-05-09 | 2683-NMDC-E-AO-PMT-T-00288 |  |  | 1 - Approved | 2025-02-24 | 2683-NMDC-E-ABL-MWS-T-00011 | 2025-03-04 | DRS 0018 | 1 Approved
|  |  |  | 5 |  |  | T-242/25 | 2025-06-05 | 2025-06-09 | 2683-NMDC-E-AO-PMT-T-00772 |  |  | 1 - Approved | 2025-06-04 | 2683-NMDC-E-ABL-MWS-T-00026 | 2025-06-13 | DRS 0040 | 1 Approved
|  |  |  | 6 |  |  | T-252/25 | 2025-06-16 | 2025-06-16 | 2683-NMDC-E-AO-PMT-T-00782 | 2025-07-21 | E1941-AOF-NPCC-PMT-TR-00501 | 2. Approved with comments | 2025-06-17 | 2683-NMDC-E-ABL-MWS-T-00028 | 2025-06-26 | DRS 0043 | 1 Approved
|  |  |  | 7 |  |  | T-368/25 | 2025-07-21 | 2025-07-23 | 2683-NMDC-E-AO-PMT-T-00838 | 2025-09-10 | E1941-AOF-NPCC-PMT-TR-00560 | 1 - Approved | 2025-07-23 | 2683-NMDC-E-ABL-MWS-T-0039 | 2025-08-04 | DRS 0054 | 1 Approved
|  |  |  | 8 |  |  | T-104/26 | 2026-03-12 | 2026-03-13 | 2683-NMDC-E-AO-PMT-T-01176 | 2026-03-16 | E1941-AOF-NPCC-PMT-TR-00724 | 2. Approved with comments
|  |  |  | 9 |  |  | T-109/26 | 2026-03-16
|  |  |  | 10 |  |  | T-112/26 | 2026-03-16 | 2026-04-10 | 2683-NMDC-E-AO-PMT-T-01218 | 2026-04-20 | E1941-AOF-NPCC-PMT-TR-00755 | 1 - Approved | 2026-06-07 | 2683-NMDC-E-ABL-MWS-T-0102 | 2026-04-10 | ABL-DRS-0140 | 1 Approved
| ANCHOR HANDLING AND MOORING PROCEDURE FOR JACK UP BARGES | 2683-PP-OF-002 | AD-473-G-01052 | A1 |  | 2024-02-09 | T-066/24 | 2024-02-09
|  |  |  | 1 |  |  | T-083/24 | 2024-02-16 | 19-Feb-2024 | 2683-NPCC-AO-PMT-T-00198 | 2024-03-04 | E1941-AOF-NPCC-PMT-TR-00124 | 5 - Rejected
|  |  |  | 2 |  |  | T-111/24 | 2024-03-07 | 2024-03-08 | 2683-NPCC-AO-PMT-T-00228 | 2024-03-14 | E1941-AOF-NPCC-PMT-TR-00132 | 1 - Approved
|  |  |  | 3 |  |  | T-131/24 | 2024-03-22 | 2024-03-22 | 2683-NPCC-AO-PMT-T-00240 | 25-Mar-2024 | E1941-AOF-NPCC-PMT-TR-00142 | 1 - Approved
|  |  |  | 4 |  |  | T-197/24 | 2024-05-09 | 2024-05-13 | 2683-NMDC-E-AO-PMT-T-00292 |  |  | 1 - Approved | 2025-02-24 | 2683-NMDC-E-ABL-MWS-T-00011 | 2025-03-04 | DRS-0019 | 1 Approved
| ANCHOR HANDLING AND MOORING PROCEDURE FOR WORKBOATS | 2683-PP-OF-003 | AD-473-G-01053 | A1 |  | 2024-02-09 | T-067/24 | 2024-02-09
|  |  |  | 1 |  |  | T-071-24 | 2024-02-13 |  | 2683-NPCC-AO-PMT-T-00193 | 2024-02-13 | E1941-AOF-NPCC-PMT-TR-00136 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-155/24 | 2024-04-05 | 2024-04-16 | 2683-NPCC-AO-PMT-T-00263 | 2024-07-08 | E1941-AOF-NPCC-PMT-TR-00209 | 1 - Approved
|  |  |  | 3 |  |  | T-315/24 | 2024-07-09 | 2024-07-10 | 2683-NMDC-E-AO-PMT-T-00366 |  |  | 1 - Approved | 2025-02-24 | 2683-NMDC-E-ABL-MWS-T-00011 | 2025-03-04 | DRS 0020 | 1 Approved
| ANCHOR HANDLING AND MOORING PROCEDURE FOR HAMMERHEAD CRANE VESSELS | 2683-PP-OF-004 | AD-473-G-01054 | A1 |  | 2024-02-09 | T-065/24 | 2024-02-09
|  |  |  | 1 |  |  | T-084/24 | 2024-02-16 |  | 2683-NPCC-AO-PMT-T-00199 | 2024-02-19 | E1941-AOF-NPCC-PMT-TR-00129 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-130/24 | 2024-03-22 | 2024-03-22 | 2683-NPCC-AO-PMT-T-00242 | 2024-04-23 | E1941-AOF-NPCC-PMT-TR-00154 | 1 - Approved
|  |  |  | 3 |  |  | T-178/24 | 2024-04-29 | 2024-05-03 | 2683-NMDC-E-AO-PMT-T-00284 |  |  | 1 - Approved | 2025-02-24 | 2683-NMDC-E-ABL-MWS-T-00011 | 2025-03-04 | DRS 0021 | 1 Approved
| EXISTING PIPELINE DEMOLITION PROCEDURE | 2683-PP-OF-005 | AD-473-G-01055
| GROUT BAGS INSTALLATION AND FREE SPAN CORRECTION PROCEDURE | 2683-PP-OF-006 | AD-473-G-01056 | A1 |  | 2025-09-19 | T-488/25
|  |  |  | 1 |  |  | T-490/25 | 2025-09-23 | 2025-09-23 | 2683-NMDC-E-AO-PMT-T-00940 | 2025-09-26 | E1941-AOF-NPCC-PMT-TR-00581 | 1 - Approved
|  |  |  | 2 |  |  | T-026/26 | 2026-01-21 | 2026-01-26 | 2683-NMDC-E-AO-PMT-T-01092 | 2026-04-30 | E1941-AOF-NPCC-PMT-TR-00780 | 2 - Approved with Comments
| PIPELINE FLOODING GAUGING AND HYDROTESTING PROCEDURE | 2683-PP-OF-007 | AD-473-G-01057
| STALK-ON RISER INSTALLATION PROCEDURE | 2683-PP-OF-008 | AD-473-G-01058 | A1 |  | 2025-09-16 | T-475/25
|  |  |  | 1 |  |  | T-481/25 | 2025-09-18 | 2025-09-19 | 2683-NMDC-E-AO-PMT-T-00937 | 2025-10-22 | E1941-AOF-NPCC-PMT-TR-00604 | 2 - Approved with Comments | 2026-04-09 | 2683-NMDC-E-ABL-MWS-T-0112
|  |  |  | 2 |  |  | T-100/26 | 2026-03-10 | 2026-03-11 | 2683-NMDC-E-AO-PMT-T-01168 | 2026-04-13 | E1941-AOF-NPCC-PMT-TR-00761 | 1 - Approved |  |  | 2026-04-10 | ABL-DRS-0139 | 1 - Approved
| SHORE PULL PROCEDURE | 2683-PP-OF-009 | AD-473-G-01059 | A1 |  | 2025-03-10 | T-265/24 | 2024-06-14
|  |  |  | 1 |  |  | T-054/25 | 2025-02-14
|  |  |  | 1 |  |  | T-081/25 | 2025-03-10 | 2025-02-17 | 2683-NMDC-E-AO-PMT-T-00648 | 2025-04-07 | E1941-AOF-NPCC-PMT-TR-00409 | 2 - Approved with Comments | 2025-03-17 | 2683-NMDC-E-ABL-MWS-T-00011 | 2025-03-14 | DRS 0024 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-168/25 | 2025-04-30 | 2025-04-30 | 2683-NMDC-E-AO-PMT-T-00715 | 2025-05-19 | E1941-AOF-NPCC-PMT-TR-00440 | 2 - Approved with Comments | 2025-04-30 | 2683-NMDC-E-ABL-MWS-T-0018 | 2025-05-19 | ABL-DRS-0032 | 1 - Approved
|  |  |  | 3 |  |  | T-314/25 | 2025-07-02 | 2025-07-02 | 2683-NMDC-E-AO-PMT-T-00806 | 2025-07-05 | E1941-AOF-NPCC-PMT-TR-00488 | 2 - Approved with Comments | 2025-07-02 | 2683-NMDC-E-ABL-MWS-T-0032 | 2025-07-06 | ABL-DRS-0047 | 1 - Approved
|  |  |  | 4 |  |  | T-360/25 | 2025-07-17 | 2025-07-17 | 2683-NMDC-E-ABL-MWS-T-0037 | 2025-08-01 | E1941-AOF-NPCC-PMT-TR-00522 | 2 - Approved with Comments | 2025-07-22 | 2683-NMDC-E-ABL-MWS-T-0037 | 2025-08-04 | ABL-DRS-0052 | 1 - Approved
|  |  |  | 5 |  |  | T-391/25 | 2025-08-05 | 2025-08-07 | 2683-NMDC-E-AO-PMT-T-00848 | 2025-08-08 | E1941-AOF-NPCC-PMT-TR-00528 | 2 - Approved with Comments | 2025-08-06 | 2683-NMDC-E-ABL-MWS-T-0049
|  |  |  | 6 |  |  | T-404/25 | 2025-08-11 | 2025-08-13 | 2683-NMDC-E-AO-PMT-T-00874 | 2025-08-12 | E1941-AOF-NPCC-PMT-TR-00543 | 2 - Approved with Comments | 2025-08-13 | 2683-NMDC-E-ABL-MWS-T-0054 | 2025-08-15 | ABL-DRS-0062 | 1 - Approved
|  |  |  | 7 |  |  | T-025/26 | 2026-01-20 | 2026-01-21 | 2683-NMDC-E-AO-PMT-T-01090 | 2026-01-02 | E1941-AOF-NPCC-PMT-TR-00677 | 1 - Approved
| PIPELINE INSTALLATION MANUAL | 2683-PP-OF-010 | AD-473-G-01060 | A1 |  | 2024-06-09 | T-053/25 | 2025-02-01
|  |  |  | 1 |  |  | T-069/25 | 2025-02-11 | 2025-02-11 | 2683-NMDC-E-AO-PMT-T-00636 | 2025-02-28 | E1941-AOF-NPCC-PMT-TR-00397 | 5 - Rejected | 2025-02-24 | 2683-NMDC-E-ABL-MWS-T-00011 | 2025-03-17 | DRS 0025 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-306/25 | 2025-07-01 | 2025-07-01 | 2683-NMDC-E-AO-PMT-T-00804 | 2025-07-12 | E1941-AOF-NPCC-PMT-TR-00493 | 1 - Approved | 2025-07-01 | 2683-NMDC-E-ABL-MWS-T-00031 | 2025-07-07 | DRS 0046 | 1 - Approved
|  |  |  | 3 |  |  | T-358/25 | 2025-07-14 | 2025-07-18 | 2683-NMDC-E-AO-PMT-T-00833 | 2025-07-30 | E1941-AOF-NPCC-PMT-TR-00521 | 1 - Approved | 2025-07-17 | 2683-NMDC-E-ABL-MWS-T-00036 | 2025-08-08 | ABL-DRS-0058 | 1 - Approved
|  |  |  | 4 |  |  | T-383/25 | 2025-08-01 | 2025-08-01 | 2683-NMDC-E-AO-PMT-T-00857 | 2025-08-06 | E1941-AOF-NPCC-PMT-TR-00523 | 1 - Approved | 2025-08-06 | 2683-NMDC-E-ABL-MWS-T-00047 | 2025-08-01 | DRS 0066 | 1 - Approved
|  |  |  | 5 |  |  | T-449/25 | 2025-09-03 | 2025-09-03 | 2683-NMDC-E-AO-PMT-T-00910 | 2025-09-03 | 2683-NMDC-E-ABL-MWS-T-0061 | 1 - Approved | 2025-09-02 | 2683-NMDC-E-ABL-MWS-T-00061 | 2025-09-22 | DRS 0078 | 1 - Approved
| SLEEPERS AND MATTRESSES INSTALLATION PROCEDURE | 2683-PP-OF-011 | AD-473-G-01061 | A1 |  | 2024-09-26 | T-246/24 | 2024-06-07
|  |  |  | 1 |  |  | T-473/24 | 2024-09-26 | 2024-10-01 | 2683-NMDC-E-AO-PMT-T-00463 | 2024-10-10 | E1941-AOF-NPCC-PMT-TR-00289 | 2 - Approved with Comments | 2024-10-10 | 2683-NMDC-E-ABL-MWS-T-0001 | 2024-10-29 | ABL-DRS-0001 | 1 - Approved
|  |  |  | 2 |  |  | T-555/24 | 2024-11-19 | 21-Nov-2024 | 2683-NMDC-E-AO-PMT-T-00535 | 2024-12-05 | E1941-AOF-NPCC-PMT-TR-00330 | 1 - Approved | 2024-11-21 | 2683-NMDC-E-ABL-MWS-T-0002 | 2024-12-05 | ABL-DRS-0002 | 1 - Approved
|  |  |  | 3 |  |  | T-583/24 | 2024-12-06 | 2024-12-10 | 2683-NMDC-E-ABL-MWS-T-0006 | 2024-12-30 | E1941-AOF-NPCC-PMT-TR-00349 | 1 - Approved | 2024-12-10 | 2683-NMDC-E-ABL-MWS-T-0006 | 2024-12-12 | ABL-DRS-0006 | 1 - Approved
| RISER CLAMPS INSTALLATION PROCEDURE | 2683-PP-OF-040 | AD-473-G-01090 | 1 |  | 2025-05-09 | T-187/25 | 2025-05-09 | 2025-05-09 | 2683-NMDC-E-AO-PMT-T-00735 | 2025-05-09 | 2683-NMDC-E-AO-PMT-T-00735 | 2 - Approved with Comments | 2025-05-09 | 2683-NMDC-E-ABL-MWS-T-0021 | 2025-05-13 | ABL-DRS-0033 | 1 - Approved
|  |  |  | 2 |  |  | T-363/25 | 2025-07-18 | 2025-07-18 | 2683-NMDC-E-AO-PMT-T-00836 | 2025-07-26 | E1941-AOF-NPCC-PMT-TR-00509 | 1 - Approved | 2025-07-18 | 2683-NMDC-E-ABL-MWS-T-0034 | 2025-07-22 | ABL-DRS-0049 | 1 - Approved
|  |  |  | 3 |  |  | T-377/25 | 2025-07-29 | 2025-07-31 | 2683-NMDC-E-AO-PMT-T-00847 |  |  |  | 2025-07-31 | 2683-NMDC-E-ABL-MWS-T-0044
|  |  |  | 4 |  |  | T-612/25 |  | 2025-12-08 | 2683-NMDC-E-AO-PMT-T-01031 |  |  | 1 - Approved | 2025-12-08 | 2683-NMDC-E-ABL-MWS-T-0078 | 2025-12-09 | ABL-DRS-0102 | 1 - Approved
|  |  |  | 5 |  |  | T-042/26 | 2026-01-29 | 2026-02-03 | 2683-NMDC-E-AO-PMT-T-01110 | 2026-02-17 | E1941-AOF-NPCC-PMT-TR-00699 | 1 - Approved | 2026-02-03 | 2683-NMDC-E-ABL-MWS-T-0090 | 2026-02-13 | ABL-DRS-0113 | 1 - Approved
|  |  |  | 6 |  |  | pmt |  | 2026-03-05 | 2683-NMDC-E-AO-PMT-T-01159 | 2026-03-06 | E1941-AOF-NPCC-PMT-TR-00718 | 4 - For Information
|  |  |  | 7 |  |  | T-124/26 | 2026-04-02 | 2026-04-03 | 2683-NMDC-E-AO-PMT-T-01201 | 2026-04-15 | E1941-AOF-NPCC-PMT-TR-00763 | 2 - Approved with Comments | 2026-04-03 | 2683-NMDC-E-ABL-MWS-T-0107 | 2026-04-02 | ABL-DRS-0134 | 1 - Approved
|  |  |  | 8 |  |  | T-360/26 | 2026-08-21 | 2026-08-21 | 2683-NMDC-E-AO-PMT-T-01360 |  |  |  | 2026-08-21 | 2683-NMDC-E-ABL-MWS-T-0134
| METHOD STATEMENT FOR ADDITIONAL MITIGATION DURING ANCHOR HANDLING WHILE CROSSING GAS LINES AND MAIN OIL LINES BY GRAVITY ANCHOR | 2683-PP-OF-041 | AD-473-G-01091 | 1 |  | 2025-05-20 | T-203/25 | 2025-05-20 | 2025-05-21 | 2683-NMDC-E-AO-PMT-T-00752 | 2025-06-04 | E1941-AOF-NPCC-PMT-TR-00466 | 2 - Approved with Comments | 2025-05-20 | 2683-NMDC-E-ABL-MWS-T-0023
|  |  |  | 2 |  |  | T-240/25 | 2025-06-05 | 2025-06-09 | 2683-NMDC-E-AO-PMT-T-00773 | 2025-06-17 | E1941-AOF-NPCC-PMT-TR-00473 | 2 - Approved with Comments | 2025-06-07 | 2683-NMDC-E-ABL-MWS-T-0027 |  | ABL-DRS-0041 | 1 - Approved
|  |  |  | 3 |  |  | T-299/25 | 2025-06-26 | 2025-06-27 | 2683-NMDC-E-AO-PMT-T-00800 | 2025-07-26 | E1941-AOF-NPCC-PMT-TR-00500 | 1 - Approved | 2025-06-27 | 2683-NMDC-E-ABL-MWS-T-0030 |  | ABL-DRS-0045 | 1 - Approved
|  |  |  | 4 |  |  | T-378/25 | 2025-07-29 | 2025-07-29 | 2683-NMDC-E-AO-PMT-T-00845 |  |  | 1 - Approved | 2025-07-28 | 2683-NMDC-E-ABL-MWS-T-0043 | 2025-08-06 | ABL-DRS-0057 | 1 - Approved
| MIDLINE TIE-IN INSTALLATION PROCEDURE | 2683-PP-OF-054 | AD-473-G-01212 | A1 |  | 2025-10-09 | T-516/25
|  |  |  | 1 |  |  | T-519/25 | 2025-10-09 | 2025-10-13 | 2683-NMDC-E-AO-PMT-T-00963 | 2025-10-31 | E1941-AOF-NPCC-PMT-TR-00613 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-627/25 | 2025-12-18 | 2025-12-20 | 2683-NMDC-E-AO-PMT-T-01053 | 2025-12-22 | E1941-AOF-NPCC-PMT-TR-00659 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-146/26 | 2026-04-09 | 2026-04-13 | 2683-NMDC-E-AO-PMT-T-01215 | 2026-04-15 | E1941-AOF-NPCC-PMT-TR-00765 | 1 - Approved | 2026-05-15 | 2683-NMDC-E-ABL-MWS-T-0122 | 2026-05-15 | ABL-DRS-0149 | 1 - Approved

## Setup Plans & Anchor Patterns
NMDC DOC. No.: MDR-001
EPC WORKS FOR 20” MOL FROM UMM LULU TO ZIRKU ISLAND
|  | NMDC PROJECT NO. 2683 | [11 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-08-21
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| DLB 750 ANCHOR PATTERN DURING 20" MOL PIPELAYING FROM KP 0.00 TO 64.500 | 2683-AP-0001
| DLS-4200 ANCHOR PATTERN DURING 20'' MOL PIPELAYING FROM KP 0.00 TO 64.500 | 2683-AP-0002 | AD-473-PL-627041 | 1 |  |  | T-337/25 | 2025-07-09 | 2025-07-09 | 2683-NMDC-E-AO-PMT-T-00818 | 2025-07-29 | E1941-AOF-NPCC-PMT-TR-00517 | 2 - Approved with Comments | 2025-07-09 | 2683-NMDC-E-ABL-MWS-T-0033 | 2025-07-22 | DRS-0048 | 3 - Reviewed with Comments
[9 empty] | 2025-08-01 | 2683-NMDC-E-AO-PMT-T-00853 | 2025-10-10 | E1941-AOF-NPCC-PMT-TR-00563 | 1 - Approved
| DLS-4200 ANCHOR PATTERN DURING 20'' MOL PIPELAYING FROM SHORE TO KP 64.500 | 2683-AP-0003 | AD-473-PL-627042 | 1 |  |  | T-439/25 | 2025-08-29 | 2025-09-01 | 2683-NMDC-E-AO-PMT-T-00900 | 2025-09-22 | E1941-AOF-NPCC-PMT-TR-00575 | 1 - Approved | 2025-09-01 | 2683-NMDC-E-ABL-MWS-T-0060 |  | DRS-0077 | 1 - Approved
| DLS-4200 ANCHOR PATTERN DURING 20'' MOL PIPELAYING FROM KP 64.500 TO 109.700 | 2683-AP-0005 | AD-473-PL-627044 | 1 |  |  | T-621/25 | 2025-12-25 | 2025-12-17 | 2683-NMDC-E-AO-PMT-T-01045 | 2025-12-23 | E1941-AOF-NPCC-PMT-TR-00657 | 1 - Approved | 2025-12-18 | 2683-NMDC-E-ABL-MWS-T-0082 |  | DRS-0108 | 1 - Approved
| DLB-750 ANCHOR PATTERN DURING 20'' MOL RISER INSTALLATION AT ULRP | 2683-AP-0006 | AD-473-PL-627045 | 1 |  |  | T-031/26 | 2026-01-22 | 2026-01-26 | 2683-NMDC-E-AO-PMT-T-01091 | 2026-03-26 | E1941-AOF-NPCC-PMT-TR-00736 | 5 - Rejected
|  |  |  | 2 |  |  | T-164/26 | 2026-04-16 | 2026-04-20 | 2683-NMDC-E-AO-PMT-T-01228 | 2026-07-07 | E1941-AOF-NPCC-PMT-TR-00827 | 1 - Approved
| DLB-750 ANCHOR PATTERN DURING 20'' MOL MIDLINE TIE-IN AT KP 109.7 | 2683-AP-0007 | AD-473-PL-627046 | 1 |  |  | T-036/26 | 2026-01-26 | 2026-01-28 | 2683-NMDC-E-AO-PMT-T-01097 | 2026-03-25 | E1941-AOF-NPCC-PMT-TR-00732 | 1 - Approved
| DLB-750 ANCHOR PATTERN DURING 20'' MOL PIPELAYING FROM KP 60.000 TO 109.700 | 2683-AP-0008 | AD-473-PL-627047 | 1 |  |  | T-072/26 | 2026-02-13 | 2026-02-17 | 2683-NMDC-E-AO-PMT-T-01138 | 2026-02-20 | E1941-AOF-NPCC-PMT-TR-00700 | 3 - Reviewed with Comments
| DLB-750 ANCHOR PATTERN DURING STANDBY POSITION AT ULRP | 2683-AP-0009 | AD-473-PL-627048 | 1 |  |  | T-164/26 | 2026-04-16 | 2024-03-20 | 2683-NMDC-E-AO-PMT-T-01224 | 2026-07-07 | E1941-AOF-NPCC-PMT-TR-00827 | 1 - Approved
| DLS-4200 ANCHOR PATTERN DURING 20'' MOL MIDLINE TIE-IN AT KP 109.7 | 2683-AP-0010 | AD-473-PL-627049 | 1 |  |  | T-140/26 | 2026-04-03 | 2026-04-06 | 2683-NMDC-E-AO-PMT-T-01208 | 2026-04-17 | E1941-AOF-NPCC-PMT-TR-00766 | 2 - Approved with Comments

## Sketches
NMDC DOC. No.: MDR-001
EPC WORKS FOR 20” MOL FROM UMM LULU TO ZIRKU ISLAND
|  | NMDC PROJECT NO. 2683 | [11 empty] | REVISION : | 0
|  | OFFSHORE sketches | [11 empty] | DATE : | 2026-08-21
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC | [11 empty] | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| (DLB-750 AP during 20Inch MOL shore pull at zirku island) | 2683-A1-002 |  | 1 |  |  | 2024-11-25 | SKV
| (DLB-750 AP during 20Inch MOL shore pull at zirku island) | 2683-A1-004 |  | A |  |  | 2025-02-07 | SKV
| (DLS-4200 AP during 20Inch MOL shore pull at zirku island) | 2683-A1-005 |  | A |  |  | 2025-06-16 | SKV
| (DLB-750 AP during 20Inch MOL shore pull at zirku island) | 2683-A1-004 |  | B |  |  | 2025-06-17 | SKV
| (DLB-750 AP during 20Inch MOL shore pull at zirku island) | 2683-A1-004 |  | C |  |  | 2025-06-18 | SKV
| (DLB-750 AP during 20Inch MOL Riser installation at ULRP) | 2683-A1-007 |  | A |  |  | 2025-11-14 | SKV
| 2683-AP-0007_R1(DLB-750 AP during 20Inch MOL MIDLINE TIE-IN @ KP 109.7) | 2683-AP-0007 |  | 1 |  |  | 2026-01-26 | EJJ
| 2683-AP-0006-1 TO 3_R2(DLB-750 AP during 20Inch MOL Riser installation at ULRP) | 2683-AP-0006 |  | 2 |  |  | 2026-01-26 | SKV
| 2683-AP-0010_R1(DLS-4200 AP during 20Inch MOL MIDLINE TIE-IN @ KP 109.7) | 2683-AP-0010 |  | 1 |  |  | 2026-04-03 | SKV
| WORKBOAT ANCHOR PATTERN AT ULRP | 2683-AP-0000 |  | 1 |  |  | 2026-06-01 | SKV