## Installation Procedures
|  | ARAMCO | [10 empty] | NMDC DOC. No.: MDR-001
LONG TERM AGREEMENT (LTA) FOR OFFSHORE FACILITIES CRPO 128 – BI-10-16966 – REPLACE 48-INCH ZULUF TRUNKLINE (ZS-1)
|  | NPCC PROJECT NO. 2734-2735 | [10 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [10 empty] | DATE : | 2026-09-07
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ARAMCO OFFSHORE | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | Method TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[6 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| ZULF GOSP-2 EXISTING RISER PRE-ENGINEERING DIVE SURVEY PROCEDURE | 2734-2735-PP-OF-011 | A1 |  |  | T-021/24 | 2024-01-17
|  |  | A |  |  | T-024/24 | 2024-01-17 | 2024-01-23 | 2734-2735-NPCC-T-00182 | 2024-02-04 | CPD-ROZF-T-0182-24 | 4 - Retained for Information
|  |  | B |  |  | T-073-24 | 2024-02-13 | 15-Feb-2024 | 2734-2735-NPCC-T-00236 | 2024-04-01 | CPD-ROZF-T-0477-24 | 1 - Approved
| PIPELINES FLOODING, GAUGING, CLEANING AND HYDROTESTING PROCEDURE (BY OTHERS?) | 2734-2735-PP-OF-004
| Pipelines Internal FBE Field joint Coating and Repair Procedure | 2734-2735-PP-OF-007
| Pipeline External Anti-Corrosion Field Joint Coating Procedure | 2734-2735-PP-OF-008
| Pipeline External Infill Field Joint Coating Procedure | 2734-2735-PP-OF-009
| ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | 2734-2735-PP-OF-016 | A1 |  | 2024-07-19 | T-329/24 | 2024-07-19
|  |  | A |  |  | T-331/24 | 2024-07-25 | 2024-07-25 | 2734-2735-NMDC-T-00739 |  | OP&CPD-ROZF-T-1488-24 | 4 - Retained for Information
|  |  | 00 |  |  | T-121/25 | 2025-03-26
| FLANGE MANAGEMENT PROCEDURE – SUBSEA FLANGES | 2734-2735-PP-OF-017 | A1 |  |  | T-437/24 | 2024-09-17
|  |  | A |  |  | T-512/24 | 2024-10-17 | 2024-10-21 | 2734-2735-NMDC-T-01229 | 2024-11-27 | OP&CPD-ROZF-T-1917-24 | 1 - Approved
|  |  | 00 |  |  | T-143/25 | 2025-04-15 | 2025-07-24 | 2734-2735-NMDC-T-02866
| CROSSING SUPPORTS INSTALLATION PROCEDURE | 2734-2735-PP-OF-018 | A1 |  | 2024-07-18 | T-328/24 | 2024-07-18
|  |  | A |  |  | T-332/24 | 2024-07-25 | 2024-07-26 | 2734-2735-NMDC-T-00746 | 2024-09-05 | OP&CPD-ROZF-T-1187-24 | 6 - Approved with Comments
|  |  | 00 |  |  | T-113/25 | 2025-03-20 | 2025-03-22 | 2734-2735-NMDC-T-02073 | 2025-06-30 | OP&CPD-ROZF-T-1292-25 | 4 - Retained for Information
|  |  | 01 |  |  | T-527/25 | 2025-10-14 | 2025-10-15 | 2734-2735-NMDC-T-03314
| 48'' PIPELINE SHORE PULL PROCEDURE | 2734-2735-PP-OF-019 | A1 |  |  | T-359/24 | 2024-08-08
|  |  | A |  |  | T-498/24 | 2024-10-09 | 15-Oct-2024 | 2734-2735-NMDC-T-01199 | 2024-11-11 | OP&CPD-ROZF-T-1767-24 | 2 - Reviewed with Comments
|  |  | B |  |  | T-050/25 | 2025-01-31 | 2025-02-03 | 2734-2735-NMDC-T-01801 | 2025-04-23 | OP&CPD-ROZF-T-0749-25 | 6 - Approved with Comments
|  |  | 00 |  |  | T-327/25 | 2025-07-07 | 2025-11-21 | 2734-2735-NMDC-T-03512
| PIPELINE INSTALLATION MANUAL | 2734-2735-PP-OF-020 | A1 |  | 2024-08-27 | T-385/24 | 2024-08-27
|  |  | A |  |  | T-477/24 | 2024-09-28 | 2024-10-03 | 2734-2735-NMDC-T-01135 | 2024-11-20 | OP&CPD-ROZF-T-1886-24 | 1 - Approved
|  |  | 00 |  |  | T-127/25 | 2025-04-03 | 2025-04-03 | 2734-2735-NMDC-T-02151 | 2026-03-25 | OP&CPD-ROZF-T-0542-26 | 1 - Approved
| SUBSEA SPOOLS INSTALLATION PROCEDURE | 2734-2735-PP-OF-021 | A |  |  | T-029/26 | 2026-01-22 | 2026-01-23 | 2734-2735-NMDC-T-03795 | 19-Feb-2026 | OP&CPD-ROZF-T-0326-26 | 1 - Approved
| FREE SPAN RECTIFICATION PROCEDURE | 2734-2735-PP-OF-070 | A1 |  | 2024-09-17 | T-019/25 | 2025-01-16
|  |  | A |  |  | T-021/25 | 2025-01-16 | 2025-02-05 | 2734-2735-NMDC-T-01817 | 2025-02-12 | OP&CPD-ROZF-T-0287-25 | 2 - Reviewed with Comments
|  |  | B |  |  | T-077/25 | 2025-02-25 | 2025-02-25 | 2734-2735-NMDC-T-01939 | 2025-04-15 | OP&CPD-ROZF-T-0694-25 | 2 - Reviewed with Comments
|  |  | C |  |  | T-285/25 | 2025-07-03 | 2025-07-03 | 2734-2735-NMDC-T-02731 | 2025-10-22 | OP&CPD-ROZF-T-2249-25 | 1 - Approved
| PIPELINE ABANDON AND RECOVERY PROCEDURE FOR DELMA-2000 | 2734-2735-PP-OF-078. | A |  |  | T-310/25 | 2025-07-01
|  |  | 00 |  |  | T-326/25 | 2025-07-04
| DIMENSIONAL SURVEY FOR 48'' CRUDE OIL TO SAFANYIA RISER AT ZULF GOSP-2 | 2734-2735-PP-OF-079 | A |  |  | T-338/25 | 2025-07-11 | 2025-07-30 | 2734-2735-NMDC-T-02901 | 2025-08-25 | OP&CPD-ROZF-T-1640-25 | 1 - Approved
| SUBSEA SURVEY FOR 48'' RISER AT ZULF GOSP-2 | 2734-2735-PP-OF-080 | A |  |  | T-405/25 | 2025-08-12 | 2025-08-12 | 2734-2735-NMDC-T-02977 | 2025-10-27 | OP&CPD-ROZF-T-2306-25 | 1 - Approved
| EXISTING PIPELINE DEMOLISHING PROCEDURE | 2734-2735-PP-OF-082 | A1 |  |  | T-006/26 | 2026-01-06
|  |  | A |  |  | T-011/26 | 2026-01-09 | 2026-01-20 | 2734-2735-NMDC-T-03778 | 2026-01-29 | OP&CPD-ROZF-T-0151-26 | 2 - Reviewed with Comments
|  |  | B |  |  | T-267/26 | 2026-06-29
| RISER DEMOLITION AND INSTALLATION PROCEDURE | 2734-2735-PP-OF-083. | A1 |  |  | T-327/26
|  |  | A |  |  | T-356/26 | 2026-08-21
| AUXILIARY PUMPING SETUP & LPPT CONNECTION POINTS TO EVAPORATION POND NO.6 | 2734-2735-PP-OF-092 | 00 |  |  | T-347/26 | 2026-08-12

## Setup Plans & Anchor Patterns
|  | ARAMCO | [10 empty] | NMDC DOC. No.: MDR-001
LONG TERM AGREEMENT (LTA) FOR OFFSHORE FACILITIES CRPO 128 – BI-10-16966 – REPLACE 48-INCH ZULUF TRUNKLINE (ZS-1)
|  | NPCC PROJECT NO. 2734-2735 | [10 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [10 empty] | DATE : | 2026-09-07
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ARAMCO OFFSHORE | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[6 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF GOSP-2 & CROSSING LOACTION | 2734-A0-008 | A |  | 2024-02-07
|  |  | B |  |  | T-045/24 | 2024-02-07
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF GOSP-2 & CROSSING LOCATION | 2734-A0-009 | B |  | 2024-02-07 | T-045/24 | 2024-02-07
| SURVEY VESSEL PASSAGE PLAN FROM ZULF ANCHORAGE TO VESSEL STANDBY LOCATION | 2734-A0-011 | 0 |  | 2024-02-19 | T-089/24 | 2024-02-19
|  |  | 2 |  |  | T-092/24 | 2024-02-23
| SURVEY VESSEL PASSAGE PLAN FROM ZULF ANCHORAGE TO VESSEL STANDBY LOCATION | 2734-A0-012 | 0 |  | 2024-02-19 | T-088/24 | 2024-02-19
|  |  | 2 |  |  | T-092/24 | 2024-02-23
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF GOSP-2 & CROSSING LOCATION | 2734-A0-032 | A |  |  | T-520/24 | 2024-10-22
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF GOSP-2 & CROSSING LOCATION | 2734-A0-033 | A |  |  | T-520/24 | 2024-10-22
| CCC MARITIME-2 SETUP PLAN DURING DIVE/ROV PRE-ENGINEERING SURVEY AT CROSSING AND ZULF GOSP-2 LOCATION | 2734-DP-0006 | A |  | 2024-02-07
|  |  | B |  |  | T-045/24 | 2024-02-07
| SURVEY VESSEL / SHALLOW WATER SURVEY BOAT SETUP PLAN DURING PRE-CONSTRUCTION SURVEY FOR PROPOSED 48'' TL FROM 37.00 TO KP 63.44 | 2734-DP-0007 | A |  | 2024-02-19 | T-087/24 | 2024-02-19
|  |  | C |  |  | T-092/24 | 2024-02-23
| DELMA-2000 SETUP PLAN DURING SLEEPER INSTALLATION AT CROSSING LOCATION | 2734-DP-0008 | A |  |  | T-520/24 | 2024-10-22

## Sketches
|  | ARAMCO | [6 empty] | NMDC DOC. No.: MDR-001
LONG TERM AGREEMENT (LTA) FOR OFFSHORE FACILITIES CRPO 128 – BI-10-16966 – REPLACE 48-INCH ZULUF TRUNKLINE (ZS-1)
|  | NPCC PROJECT NO. 2734-2735 | [6 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [6 empty] | DATE : | 2026-09-07
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| DLB-750 ANCHOR PATTERN DURING 48" TL PIPELAY FROM KP 57.863 TO KP 57.000 | 2734-AO-025 |  | A |  |  | 2024-05-30
| DLB-750 POSITION DURING 48" TL LAYING FROM KP-58.00 TO KP 56.00 (100M TDP) | 2734-A3-005 |  | A |  |  | 2024-08-28
| DLB-750 POSITION DURING 48" TL LAYING FROM KP-58.00 TO KP 56.00 (150M TDP) | 2734-A3-006 |  | A |  |  | 2024-08-28
| DLB-750 ANCHOR PATTERN DURING 48'' TL SHOREPULL START-UP | 2734-A0-026 |  | A |  |  | 2024-09-12
| DLB-750 SET-UP SEQUENCE DURING SHOREPULL START-UP | 2734-A0-027 |  | A |  |  | 2024-09-12
| (PROPOSED CHANNEL DURING PIPELAY) | 2734-A3-007 |  | 0 |  |  | 2024-10-04
| (FLOATING CHANNEL & TRENCH -1 & 2) | 2734-A0-031 |  | A |  |  | 2024-10-08
| (DELMA-2000 Position during 48Inch TL start-up ZULF GOSP-2) | 2734-A1-001 |  | A |  |  | 2024-10-09
| (FLOATING CHANNEL & TRENCH -1 & 2) rev2 | 2734-A0-031 |  | B |  |  | 2024-10-11
| (VESSEL PASSAGE PLAN FROM ANCHORAGE TO CROSSING LOCATION) | 2734-A0-032 |  | A |  |  | 2024-10-14
| (VESSEL PASSAGE PLAN FROM ANCHORAGE TO CROSSING LOCATION) | 2734-A0-033 |  | A |  |  | 2024-10-14
| (DELMA-2000 Set-up at Crossing Locations) | 2734-DP-0008 |  | A |  |  | 2024-10-14
| (DELMA-2000 Position during 48Inch TL lay near FLARE location) | 2734-A1-002 |  | A |  |  | 2024-10-22
| (DELMA-2000 Position during Sleeper installation near FLARE location) | 2734-A1-003 |  | A |  |  | 2024-10-22
| (GREEN FIELD DECLARATION DURING OFFSHORE CONSTRUCTION) | 2734-A0-034 |  | A |  |  | 2024-11-05
| DELMA-2000 Set-up during pipelay from GOSP-2 to Mid line tie-in KP 35.5) | 2734-DP-0009 |  | A |  |  | 2024-12-05
| (DELMA-2000 Set-up during pipelay from KP 35.5 to KP 01.754 ) | 2734-DP-0010 |  | A |  |  | 2024-12-05
| 2734-A0-036_R0 (VESSEL PASSAGE PLAN FROM SAFANIA ANCHORAGE TO SHOREPULL LOCATION) | 2734-A0-036 |  | 0 |  |  | 2024-12-10
| 2734-A1-001_Rev-C(DELMA-2000 Position during 48Inch TL start-up ZULF GOSP-2) | 2734-A1-001 |  | C |  |  | 2024-12-19
| (DELMA-2000 Set-up during pipelay from GOSP-2 to Mid line tie-in KP 35.5) | 2734-DP-0009 |  | A |  |  | 2024-12-20
| (DELMA-2000 Set-up during pipelay from KP 35.5 to KP 01.754 ) | 2734-DP-0010 |  | A |  |  | 2024-12-20
| (DELMA-2000 Set-up during pipelay from GOSP-2 to KP 01.717) | 2734-DP-0011 |  | A |  |  | 2024-12-20
| (VESSEL PASSAGE PLAN FROM ZULF ANCHORAGE TO GOSP-2 LOCATION) | 2734-A0-037 |  | A |  |  | 2024-12-24
| (VESSEL PASSAGE PLAN FROM ZULF ANCHORAGE TO MIDLINE TIE-IN LOCATION) | 2734-A0-038 |  | A |  |  | 2024-12-24
| (VESSEL PASSAGE PLAN FROM SAFANIYA ANCHORAGE TO MIDLINE TIE-IN LOCATION) | 2734-A0-039 |  | A |  |  | 2024-12-24
| (DELMA-2000 Set-up during pipelay from GOSP-2 to Mid line tie-in) | 2734-DP-0009 |  | A |  |  | 2024-12-24
| (DELMA-2000 Set-up during pipelay from Midline to KP 01.754 ) | 2734-DP-0010 |  | A |  |  | 2024-12-24
| (DELMA-2000 Set-up during pipelay from GOSP-2 to KP 01.717) | 2734-DP-0011 |  | A |  |  | 2024-12-24
| (DELMA-2000 Set-up during TEMP. SUPPORT & PIPELINE PROTECTOR Installation for HBC at GOSP-2) | 2734-DP-0012 |  | A |  |  | 2024-12-26
| (DLB-750 AP during 48Inch TL Pipelay from shore to Midline tie-in) | 2734-AP-0002 |  | B |  |  | 2025-01-20
| (DLB-750 PASSAGE PLAN FROM SAFANIA ANCHORAGE TO SHOREPULL LOCATION) | 2734-A0-036 |  | B |  |  | 2025-01-20
| (CB PASSAGE PLAN FROM SAFANIA ANCHORAGE TO DLB-750 LOCATION) | 2734-A0-041 |  | B |  |  | 2025-01-20
| (DLB-750 PASSAGE PLAN FROM SAFANIA ANCHORAGE TO SHOREPULL LOCATION) | 2734-A0-042 |  | B |  |  | 2025-01-20
| (DLB-750 PASSAGE PLAN FROM SAFANIA ANCHORAGE TO SHOREPULL LOCATION)-OPTION | 2734-A0-043 |  | B |  |  | 2025-01-20
| (DLB-750 PASSAGE PLAN FROM SAFANIA ANCHORAGE TO SHOREPULL LOCATION)-OPTION | 2734-A0-044 |  | B |  |  | 2025-01-20
| (DLB-750 AP during 48Inch PL shore pull at KP 58.754) | 2734-AP-0003 |  | B |  |  | 2024-01-30
| (DLB-750 AP during Weather standby position) | 2734-AP-0004 |  | A |  |  | 2025-02-18 | SKV
| (DLB-750 AP during weather standby position at 20-30M water depth) | BRG-D750-021 |  | 0 |  |  | 2025-02-18 | SKV
| (DLB-750 AP during weather standby position at 5M water depth) | BRG-D750-020 |  | 0 |  |  | 2025-02-18 | SKV
| (DELMA-2000 Set-up at Crossing Locations) | 2734-DP-0013 |  | A |  |  | 2025-03-04 | SKV
| (DELMA-2000 Set-up during pipelay from Midline to KP 01.200 ) | 2734-DP-0014 |  | A |  |  | 2025-03-05 | SKV
| 2734-A0-032_Rev-B (VESSEL PASSAGE PLAN FROM ANCHORAGE TO CROSSING LOCATION) | 2734-A0-032 |  | B |  |  | 2025-03-05 | SKV
| 2734-A0-033_Rev-B (VESSEL PASSAGE PLAN FROM ANCHORAGE TO CROSSING LOCATION) | 2734-A0-033 |  | B |  |  | 2025-03-05 | SKV
| 2734-A0-038_Rev-B (VESSEL PASSAGE PLAN FROM ZULF ANCHORAGE TO MIDLINE TIE-IN LOCATION) | 2734-A0-038 |  | B |  |  | 2025-03-05 | SKV
| 2734-A0-039_Rev-B (VESSEL PASSAGE PLAN FROM SAFANIYA ANCHORAGE TO MIDLINE TIE-IN LOCATION) | 2734-A0-039 |  | B |  |  | 2025-03-05 | SKV
| (DELMA-2000 Set-up during pipelay from Midline to KP 01.200) | 2734-DP-0014 |  | C |  |  | 2025-03-10 | SKV
| (DELMA-2000 Set-up at Crossing Locations) | 2734-DP-0013 |  | B |  |  | 2025-03-21 | SKV
| (SHUJAA-2000 Set-up at Crossing Locations) | 2734-DP-0015 |  | A |  |  | 2025-03-21 | SKV
| (VESSEL PASSAGE PLAN FROM ANCHORAGE TO CROSSING LOCATION) | 2734-A0-032 |  | C |  |  | 2025-03-21 | SKV
| (VESSEL PASSAGE PLAN FROM ANCHORAGE TO CROSSING LOCATION) | 2734-A0-033 |  | C |  |  | 2025-03-21 | SKV
| (VESSEL PASSAGE PLAN FROM ZULF ANCHORAGE TO MIDLINE TIE-IN LOCATION) | 2734-A0-038 |  | C |  |  | 2025-03-21 | SKV
| (VESSEL PASSAGE PLAN FROM SAFANIYA ANCHORAGE TO MIDLINE TIE-IN LOCATION | 2734-A0-039 |  | C |  |  | 2025-03-21 | SKV
| (VESSEL PASSAGE PLAN FROM ANCHORAGE TO CROSSING LOCATION) | 2734-A0-032 |  | D |  |  | 2025-04-09 | SKV
| (VESSEL PASSAGE PLAN FROM ANCHORAGE TO CROSSING LOCATION) | 2734-A0-033 |  | D |  |  | 2025-04-09 | SKV
| (VESSEL PASSAGE PLAN FROM ANCHORAGE TO CROSSING LOCATION) | 2734-A0-032 |  | D |  |  | 2025-04-09 | SKV
| (VESSEL PASSAGE PLAN FROM ANCHORAGE TO CROSSING LOCATION) | 2734-A0-033 |  | D |  |  | 2025-04-09 | SKV
| (DELMA-2000 Set-up at Crossing Locations) | 2734-DP-0008 |  | B |  |  | 2025-04-09 | SKV
| (VESSEL PASSAGE PLAN FROM ZULF ANCHORAGE TO GOSP-2 LOCATION) | 2734-A0-037 |  | B |  |  | 2025-04-15 | SKV
| (VESSEL PASSAGE PLAN FROM ZULF ANCHORAGE TO MIDLINE TIE-IN LOCATION) | 2734-A0-038 |  | D |  |  | 2025-04-15 | SKV
| (VESSEL PASSAGE PLAN FROM SAFANIYA ANCHORAGE TO MIDLINE TIE-IN LOCATION) | 2734-A0-039 |  | D |  |  | 2025-04-15 | SKV
| (DELMA-2000 Set-up during pipelay from Midline to KP 01.709) | 2734-DP-0010 |  | B |  |  | 2025-04-15 | SKV
| (DELMA-2000 Set-up during pipelay from GOSP-2 to KP 01.671) | 2734-DP-0011 |  | B |  |  | 2025-04-15 | SKV
| (DLB-750 AP during 48Inch PL shore pull at KP 58.754) | 2734-AP-0003 |  | C |  |  | 2025-06-11 | SKV
| !2734-A0-041_REV-D (CB PASSAGE PLAN FROM SAFANIA ANCHORAGE TO DLB-750 LOCATION) | 2734-A0-041 |  | D |  |  | 2025-07-03 | SKV
| !2734-A0-043_REV-D (DLB-750 PASSAGE PLAN FROM SAFANIA ANCHORAGE TO SHOREPULL LOCATION)-OPTION | 2734-A0-043 |  | D |  |  | 2025-07-03 | SKV
| 2734-A0-002_Rev-F_(Vessel passage plan to ZULF GOSP-2) | 2734-A0-002 |  | F |  |  | 2025-07-03 | SKV
| 2734-A0-041_REV-D (CB PASSAGE PLAN FROM SAFANIA ANCHORAGE TO DLB-750 LOCATION) | 2734-A0-041 |  | D |  |  | 2025-07-03 | SKV
| 2734-A0-042_REV-D (DLB-750 PASSAGE PLAN FROM SAFANIA ANCHORAGE TO SHOREPULL LOCATION) | 2734-A0-042 |  | D |  |  | 2025-07-03 | SKV
| 2734-A0-043_REV-D (DLB-750 PASSAGE PLAN FROM SAFANIA ANCHORAGE TO SHOREPULL LOCATION)-OPTION | 2734-A0-043 |  | D |  |  | 2025-07-03 | SKV
| 2734-A0-046_R0(CCC MARITIME-2 Passage plan to ZULF GOSP-2)_SUR 1819 | 2734-A0-046 |  | 0 |  |  | 2025-07-18 | EJJ
| 2734-DP-0016_Rev-B(CCC MARITIME-2 Setup plan during ROV DIVING WORKS) | 2734-DP-0016 |  | B |  |  | 2025-07-18 | EJJ
| 2734-AP-0002-1 TO 8_Rev-D (DLB-750 AP during 48Inch TL Pipelay from shore to Midline tie-in) | 2734-AP-0002 |  | D |  |  | 2025-08-21 | SKV
| 2734-A0-048_REV-A (ESCORT TUG PASSAGE PLAN FROM CURRENT LOCATION TO SHOREPULL LOCATION) | 2734-A0-048 |  | A |  |  | 2025-09-01 | EJJ
| 2734-AP-0006_Rev-A (DLB-750 AP during 48Inch TL Pipelay verification survey for post trenching and cast material) | 2734-AP-0006 |  | A |  |  | 2025-09-01 | EJJ
| 2734-AP-0006_Rev-B (DLB-750 AP during 48Inch TL Pipelay verification survey for post trenching and cast material) | 2734-AP-0006 |  | B |  |  | 2025-09-01 | EJJ
| 2734-A0-049_Rev-A(SURVEY AREA FROM KP60 TO KP57) | 2734-A0-049 |  | A |  |  | 2025-09-01 | EJJ
| (DLB-750 AP during 48Inch TL Pipelay verification survey for post trenching and cast material) | 2734-AP-0006 |  | B |  |  | 2025-09-01 | EJJ
| (PCS of DLB-750 shore pull location during 48Inch TL Pipelay) | 2734-A0-049 |  | B |  |  | 2025-09-02 | EJJ
| (DLB-750 AP during 48Inch TL Pipelay verification survey for post trenching and cast material) | 2734-AP-0006 |  | C |  |  | 2025-09-02 | EJJ
| (DELMA-2000 Set-up during pipelay from KP +3.788 TO GOSP-2) | 2734-DP-0020 |  | A |  |  | 2025-10-09 | EJJ
| (DELMA-2000 PASSAGE PLAN FROM ZULF ANCHORAGE TO TEMPORARY LAY-DOWN POINT) | 2734-A0-051 |  | 0 |  |  | 2025-10-09 | EJJ
| (DELMA-2000 Set-up during SLEEPER INSTALLATION AT CROSSINGS) | 2734-DP-0021 |  | A |  |  | 2025-10-09 | EJJ
| (DELMA-2000 PASSAGE PLAN FROM ZULF ANCHORAGE TO CR #05A CROSSING LOCATION)_SUR 1819 | 2734-A0-051 |  | 1 |  |  | 2025-10-13 | EJJ
| (DELMA-2000 PASSAGE PLAN FROM ZULF ANCHORAGE TO TEMPORARY LAY-DOWN POINT)_SUR 1819 | 2734-A0-052 |  | 0 |  |  | 2025-10-13 | EJJ
| (DELMA-2000 Set-up during pipelay from KP +3.689 TO GOSP-2) | 2734-DP-0020 |  | B |  |  | 2025-10-13 | EJJ
| (DELMA-2000 Set-up during SLEEPER INSTALLATION AT CROSSINGS) | 2734-DP-0021 |  | B |  |  | 2025-10-13 | EJJ
| (ORIENTAL DRAGON PASSAGE PLAN FROM ZULF ANCHORAGE TO CR #05 CROSSING LOCATION)_SUR 1819 | 2734-A0-053 |  | 0 |  |  | 2025-10-21 | EJJ
| (ORIENTAL DRAGON PASSAGE PLAN FROM ZULF ANCHORAGE TO CR #05A CROSSING LOCATION)_SUR 1819 | 2734-A0-054 |  | 0 |  |  | 2025-10-21 | EJJ
| (ORIENTAL DRAGON Set-up during SLEEPER INSTALLATION AT CROSSINGS) | 2734-DP-0022 |  | A |  |  | 2025-10-21 | EJJ
| (ORIENTAL DRAGON Set-up during reovery of sleepers from KP 3.5 to KP 0.3) | 2734-DP-0023 |  | A |  |  | 2025-10-21 | EJJ
| (DELMA-2000 Set-up during pipelay from KP +3.689 TO GOSP-2) | 2734-DP-0020 |  | C |  |  | 2025-10-28 | EJJ
| (DELMA-2000 Set-up during SLEEPER INSTALLATION AT CROSSINGS) | 2734-DP-0021 |  | C |  |  | 2025-10-28 | EJJ
| (DELMA-2000 Set-up during pipelay from KP +3.689 TO GOSP-2) | 2734-DP-0020 |  | B |  |  | 2025-10-29 | EJJ
| (DELMA-2000 Set-up during SLEEPER INSTALLATION AT CROSSINGS) | 2734-DP-0021 |  | B |  |  | 2025-10-29 | EJJ
| (ORIENTAL DRAGON Set-up during SLEEPER INSTALLATION AT CROSSINGS) | 2734-DP-0022 |  | A |  |  | 2025-10-29 | EJJ
| 2734-A0-055_Rev-A_(DELMA-2000 Passage plan to ZULF GOSP-2)-SUR 9192 | 2734-A0-055 |  | A |  |  | 2025-11-24 | SKV
| 2734-A0-056_R0(DELMA-2000 Passage plan to ZULF GOSP-2)_SUR 1819 | 2734-A0-056 |  | 0 |  |  | 2025-11-24 | SKV
| 2734-DP-0024_Rev-A(DELMA-2000 Set-up during Survey at ZULF GOSP-2) | 2734-DP-0024 |  | A |  |  | 2025-11-24 | SKV
| 2734-AP-0007_Rev-A(DLB-750 AP during Weather standby position at KP 43.0) | 2734-AP-0007 |  | A |  |  | 2025-12-16 | SKV
| 2734-A0-002_Rev-H_(CCC MARITIME-2 Passage plan to ZULF GOSP-2) | 2734-A0-002 |  | H |  |  | 2025-12-25 | EJJ
| 2734-DP-0028-1 & 2_Rev-A(CCC MARITIME-II DP Set-up during FLOODING operation) | 2734-DP-0028 |  | A |  |  | 2025-12-25 | EJJ
| 2734-A0-057_R0(WADAD ALETHEIA Passage plan to ZULF GOSP-2)-SUR 9192 | 2734-A0-057 |  | 0 |  |  | 2025-12-25 | SKV
| 2734-A0-058_R0(WADAD ALETHEIA Passage plan to ZULF GOSP-2)_SUR 1819 | 2734-A0-058 |  | 0 |  |  | 2025-12-25 | SKV
| 2734-DP-0025-1 TO 2_Rev-A(WADAD ALETHEIA DP Set-up during Spool Installation at ZULF GOSP-2) | 2734-DP-0025 |  | A |  |  | 2025-12-25 | SKV
| 2734-DP-0026_Rev-A(WADAD ALETHEIA DP Set-up during Demolish Existing 48Inch PL at ZULF GOSP-2) | 2734-DP-0026 |  | A |  |  | 2025-12-25 | SKV
| 2734-A0-057_R0(WADAD ALETHEIA Passage plan to ZULF GOSP-2)-SUR 9192 | 2734-A0-057 |  | 0 |  |  | 2025-12-29 | SKV
| 2734-A0-058_R0(WADAD ALETHEIA Passage plan to ZULF GOSP-2)_SUR 1819 | 2734-A0-058 |  | 0 |  |  | 2025-12-29 | SKV
| 2734-DP-0025-1 TO 2_Rev-A(WADAD ALETHEIA DP Set-up during Spool Installation at ZULF GOSP-2) | 2734-DP-0025 |  | A |  |  | 2025-12-29 | SKV
| 2734-DP-0026_Rev-A(WADAD ALETHEIA DP Set-up during Demolish Existing 48Inch PL at ZULF GOSP-2) | 2734-DP-0026 |  | A |  |  | 2025-12-29 | SKV
| 2734-A0-057_R0_(WADAD ALETHEIA Passage plan to ZULF GOSP-2)-SUR 9192 | 2734-A0-057 |  | 0 |  |  | 2025-12-30 | EJJ
| 2734-A0-058_R0(WADAD ALETHEIA Passage plan to ZULF GOSP-2)_SUR 1819 | 2734-A0-058 |  | 0 |  |  | 2025-12-30 | EJJ
| 2734-DP-0027_Rev-A(CCC MARITIME-II DP Set-up during GB Installation at CR #05B) | 2734-DP-0027 |  | A |  |  | 2025-12-30 | EJJ
| 2734-A0-064_Rev-A_(CCC MARITIME-2 Passage plan to ZULF GOSP-2)_SUR 1819 | 2734-A0-064 |  | A |  |  | 2026-01-05 | EJJ
| 2734-DP-0028-1 & 2_Rev-B(CCC MARITIME-II DP Set-up during FLOODING operation) | 2734-DP-0028 |  | B |  |  | 2026-01-05 | EJJ
| 2734-DP-0025-1 TO 3_Rev-B(WADAD ALETHEIA DP Set-up during Spool Installation at ZULF GOSP-2) | 2734-DP-0025 |  | B |  |  | 2026-01-06 | SKV
| 2734-DP-0029_Rev-B(CCC WADAD ALETHEIA FOR MIDLINE TIE-IN SPOOL INSTALLATION) | 2734-DP-0029 |  | B |  |  | 2026-01-12 | SKV
| 2734-DP-0025-1 TO 3_Rev-C(WADAD ALETHEIA DP Set-up during Spool Installation at ZULF GOSP-2) | 2734-DP-0025 |  | C |  |  | 2026-01-15 | SKV
| 2734-A0-065_Rev-B(ORIANTAL DRAGON Passage plan to ZULF GOSP-2)_SUR 1819 | 2734-A0-065 |  | B |  |  | 2026-05-04 | SKV
| 2734-A0-067_Rev-B ( ORIANTAL DRAGON PASSAGE PLAN FROM ZULF ANCHORAGE TO MIDLINE TIE-IN LOCATION) Model | 2734-A0-067 |  | B |  |  | 2026-05-04 | SKV