## Installation Procedures
NMDC DOC. No.: MDR-001
EPC WORKS FOR EPS-2 AND PDP PROJECT
|  | NMDC PROJECT NO. 2745 | [11 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2026-09-07
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| ANCHOR HANDLING PROCEDURE BY HAMMER HEAD CRANE VESSEL | 2745-PP-OF-023 | AD-27-G-01044 | A1 |  |  | T-064/25 | 2025-02-05
| ANCHOR HANDLING AND MOORING PROCEDURE FOR WORK BOATS | 2745-PP-OF-024 | AD-27-G-01045
| ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | 2745-PP-OF-025 | AD-27-G-01046 | A1 |  |  | T-002/25 | 2025-01-03
|  |  |  | 1 | 2 |  | T-487/25 | 2025-09-18 | 2025-10-08 | 2745-NMDC-E-AO-T-00599 | 2026-02-17 | 11688-NMDC-TR-04071 | 2 - Approved with Comments | 2025-10-09 | 2745-NMDC-E-MWS-T-00001 | 2025-10-30 | SAF-220-MCE-NMDC-T-0001 | 1. Approved
|  |  |  | 2 | 2 |  | T-245/26 | 2028-06-12 | 2026-06-16 | 2745-NMDC-E-AO-T-01452 | 2026-06-17 | 11688-NMDC-TR-04848 | 2 - Approved with Comments | 2026-06-12 | 2745-NMDC-E-MWS-T-00097 | 2026-06-19 | SAF-220-MCE-NMDC-T-0026 | 2 - Approved with Comments
|  |  |  | 3 | 2 |  | T-252/26 | 2026-06-22 | 2026-06-23 | 2745-NMDC-E-AO-T-01490 | 2026-07-01 | 11688-NMDC-TR-04925 | 2 - Approved with Comments | 2026-06-22 | 2745-NMDC-E-MWS-T-00102
| ANCHOR HANDLING PROCEDURE FOR JACK UP BARGES | 2745-PP-OF-026 | AD-27-G-01047 | A1 |  |  | T-031/25 | 2025-01-21
|  |  |  | 1 |  |  | T-493/25 | 2025-09-22 | 2025-10-08 | 2745-NMDC-E-AO-T-00600 | 2026-02-17 | 11688-NMDC-TR-04071 | 2 - Approved with Comments | 2025-10-09 | 2745-NMDC-E-MWS-T-00002 | 2025-10-30 | SAF-220-MCE-NMDC-T-0001 | 1. Approved
| FREE SPANS CORRECTION & GROUT BAG INSTALLATION PROCEURE | 2745-PP-OF-027 | AD-27-G-01048 | A1 |  |  | T-349/26
|  |  |  | 1 |  |  | T-357/26 | 2026-08-21 | 2026-08-21 | 2745-NMDC-E-AO-T-01742 |  |  |  | 2026-08-21 | 2745-NMDC-E-MWS-T-00183
| SLEEPERS INSTALLATION PROCEDURE | 2745-PP-OF-028 | AD-27-G-01049 | A1 |  |  | T-367/25 | 2025-07-21
|  |  |  | 1 |  |  | T-385/25 | 2025-09-29 | 2025-09-29 | 2745-NMDC-E-AO-T-00566 | 2025-10-11 | 11688-NMDC-TR-03070 | 2 - Approved with Comments |  |  | 2026-05-13 | SAF-220-MCE-NMDC-T-0003 | 1. Approved
|  |  |  | 2 |  |  | T-189/26 | 2026-05-07 | 2026-05-11 | 2745-NMDC-E-AO-T-01321 | 2026-07-01 | 11688-NMDC-TR-04925 | 2 - Approved with Comments | 2026-05-11 | 2745-NMDC-E-MWS-T-00074
|  |  |  | 3 |  |  | T-288/26 | 2026-07-08 | 2026-07-09 | 2745-NMDC-E-AO-T-01573 | 2026-07-30 | 11688-NMDC-TR-05124 | 2 - Approved with Comments | 2026-07-09 | 2745-NMDC-E-MWS-T-00126 | 2026-07-14 | SAF-220-MCE-NMDC-T-0033 | 1. Approved
|  |  |  | 4 |  |  | T-335/26 |  | 2026-08-07 | 2745-NMDC-E-AO-T-01675 |  |  |  | 2026-08-06 | 2745-NMDC-E-MWS-T-00159 | 2026-08-25 | SAF-220-MCE-NMDC-T-0041 | 1. Approved
| PIPELINE INFILL MATERIAL FIELD JOINT COATING PROCEDURE | 2745-PP-OF-029 | AD-27-G-01050
| PIPELINE ANTI-CORROSION FIELD JOINT COATING PROCEDURE | 2745-PP-OF-030 | AD-27-G-01051
| PIPELINES INSTALLATION MANUAL | 2745-PP-OF-031 | AD-27-G-01052 | 1 |  |  | T-019/26 |  | 2026-02-10 | 2745-NMDC-E-AO-T-00954 | 2026-04-15 | 11688-NMDC-TR-04451 | 2 - Approved with Comments | 2026-01-24 | 2745-NMDC-E-MWS-T-00024 | 2026-02-27 | SAF-220-MCE-NMDC-T-0009 | 1. Approved
|  |  |  | 2 |  |  | T-175/26 | 2026-04-23 | 2026-04-30 | 2745-NMDC-E-AO-T-01277 | 2026-06-16 | 11688-NMDC-TR-04844 | 2 - Approved with Comments | 2026-04-30 | 2745-NMDC-E-MWS-T-00063 | 2026-05-15 | SAF-220-MCE-NMDC-T-0018 | 1. Approved
|  |  |  | 3 |  |  | T-268/26 |  | 2026-07-01 | 2745-NMDC-E-AO-T-01525 | 2026-07-30 | 11688-NMDC-TR-05124 | 2 - Approved with Comments | 2026-06-29 | 2745-NMDC-E-MWS-T-00112
|  |  |  | 4 |  |  | T-365/26 | 2026-08-25 | 2026-08-31 | 2745-NMDC-E-AO-T-01769 |  |  |  | 2026-08-27 | 2745-NMDC-E-MWS-T-00187
| COMPOSITE CABLE INSTALLATION PROCEDURE | 2745-PP-OF-032 | AD-27-G-01053
| RISER INSTALLATION PROCEDURE | 2745-PP-OF-033 | AD-27-G-01054
| J-TUBE AND RISER CLAMPS INSTALLATION PROCEDURE | 2745-PP-OF-034 | AD-27-G-01055 | A1 |  |  | T-116/26
|  |  |  | 1 |  |  | T-131/26 |  | 2026-04-06 | 2745-NMDC-E-AO-T-00954 | 2026-05-13 | 11688-NMDC-TR-04662 | 3 - Reviewed with Comments | 2026-04-01 | 2745-NMDC-E-MWS-T-00042
|  |  |  | 2 |  |  | T-274/26 | 2026-07-01 | 2026-07-03 | 2745-NMDC-E-AO-T-01544 | 2026-07-28 | 11688-NMDC-TR-05110 | 2 - Approved with Comments | 2026-07-02 | 2745-NMDC-E-MWS-T-00118
|  |  |  | 3 |  |  | T-366/26 | 2026-08-25 | 2026-08-31 | 2745-NMDC-E-AO-T-01770
| J-TUBE INSTALLATION PROCEDURE | 2745-PP-OF-035 | AD-27-G-01056 | 1 |  |  | T-515/25 | 2025-10-09 | 2025-10-14 | 2745-NMDC-E-AO-T-00613 | 2025-10-24 | 11688-NMDC-TR-03200 | 2 - Approved with Comments | 2025-10-28 | 2745-NMDC-E-MWS-T-00007 | 2025-12-15 | SAF-220-MCE-NMDC-T-0006 | 1. Approved
|  |  |  | 2 |  |  | T-589/25 | 2025-11-21 | 2025-11-21 | 2745-NMDC-E-AO-T-00770 | 2025-12-26 | 11688-NMDC-TR-03200 | 2 - Approved with Comments |  |  | 2025-12-22 | SAF-220-MCE-NMDC-T-0006 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-024/26 | PMT | 2026-01-22 | 2745-NMDC-E-AO-T-00942 | 2026-04-15 | 11688-NMDC-TR-04451 | 3 - Reviewed with Comments | 2026-01-22 | 2745--NMDC-E-MWS-T-00022
|  |  |  | 4 |  |  | T-199/26 | PMT | 2026-05-11 | 2745-NMDC-E-AO-T-01325 | 2026-07-01 | 11688-NMDC-TR-04925 | 2 - Approved with Comments | 2026-05-11 | 2745-NMDC-E-MWS-T-00075
|  |  |  | 5 |  |  | T-279/26 | 2026-07-03 | 2026-07-07 | 2745-NMDC-E-AO-T-01554 | 2026-07-30 | 11688-NMDC-TR-05124 | 2 - Approved with Comments | 2026-07-06 | 2745-NMDC-E-MWS-T-00119 | 2026-07-14 | SAF-220-MCE-NMDC-T-0033 | 1. Approved
|  |  |  | 6 |  |  | T-355/26 | 2026-08-19 | 2026-07-21 | 2745-NMDC-E-AO-T-01734 |  |  |  | 2026-08-19 | 2745-NMDC-E-MWS-T-001175
| TOPSIDE INSTALLATION PROCEDURE | 2745-PP-OF-036 | AD-27-G-01057
| TOPSIDE INSTALLATION BY FLOATOVER METHOD PROCEDURE | 2745-PP-OF-037 | AD-27-G-01058
| TOPSIDE INSTALLATION BY LIFTING METHOD PROCEDURE | 2745-PP-OF-038 | AD-27-G-01059
| JACKET INSTALLATION PROCEDURE | 2745-PP-OF-039 | AD-27-G-01060
| BRIDGE INSTALLATION PROCEDURE | 2745-PP-OF-040 | AD-27-G-01061
| PIPELINES FLOODING, GAUGING, CLEANING AND HYDROTESTING PROCEDURE | 2745-PP-OF-041 | AD-27-G-01062
| OFFSHORE HOOK-UP PROCEDURE | 2745-PP-OF-042 | AD-27-G-01063
| PIPELINES CALIPER PIGGING PROCEDURE | 2745-PP-OF-043 | AD-27-G-01064
| PIPELINES Intelligent PIGGING & Preservation PROCEDURE | 2745-PP-OF-044 | AD-27-G-01065
| PIPELINES DEWATERING, DRYING AND NITROGEN PURGING PROCEDURE | 2745-PP-OF-045 | AD-27-G-01066
| COMPOSITE CABLE TRANSPOOLING PROCEDURE | 2745-PP-OF-046 | AD-27-G-01067
| 6.6KV COMPOSITE CABLE INSTALLATION & PULL IN THROUGH J-TUBE PROCEDURE | 2745-PP-OF-058 | AD-27-G-01460 | A1 |  |  | T-223/25 | 2025-06-02
|  |  |  | 1 |  |  | T-316/25 | 2025-07-07 | 2025-07-09 | 2745-NMDC-E-AO-T-00367 | 2025-07-28 | 11688-NMDC-TR-02489 | 3. Reviewed with comments
|  |  |  | 2 |  |  | T-010/26 | 2026-01-08 | 2026-01-08 | 2745-NMDC-E-AO-T-00894
|  |  |  | 3 |  |  | T-271/26 | 2026-07-01 | 2026-07-02 | 2745-NMDC-E-AO-T-01543 |  |  |  | 2026-07-02 | 2745-NMDC-E-MWS-T-00117
| CABLE CROSSING SUPPORT INSTALLATION PROCEDURE (FLEXIBLE MATTRESS) | 2745-PP-OF-064 | AD-27-G-03213 | 1 |  |  | T-409/25 | 2025-08-13 | 2025-10-03 | 2745-NMDC-E-AO-T-00507 | 2025-10-14 | 11688-NMDC-TR-03093 | 2 - Approved with Comments | 2025-10-09 | 2745-NMDC-E-MWS-T-00004 | 2025-11-13 | SAF-220-MCE-NMDC-T-0003 | 1. Approved
| FREE SPAN CORRECTION PROCEDURE | 2745-PP-OF-104 | AD-27-G-75091
| WHT-2 TOPSIDE INSTALLATION PROCEDURE | 2745-PP-OF-128 | AD-27-G-75258 | A1 |  |  | T-319/26
|  |  |  | 1 |  |  | T-322/26 | 2026-07-28 | 2026-08-20 | 2745-NMDC-E-AO-T-01678
| METHOD STATEMENT FOR DLS-4200 SETUP SEQUENCE DURING WHT-3 TOPSIDE INSTALLATION ACTIVTIES | 2745-PP-OF-130 | AD-849-PL-62512 | A1 |  |  | T-250/26
| ZWSC-PDP AND ZWSC PDP-BST JACKETS INSTALLATION PROCEDURE | 2745-PP-OF-134 | AD-816-G-40108 | A1 |  |  | T-305/26
|  |  |  | 1 |  |  | T-338/26 | 2026-08-26 | 2026-08-31 | 2745-NMDC-E-AO-T-01785 |  |  |  | 2026-08-31 | 2745-NMDC-E-MWS-T-00189
| ZCSC-PDP AND ZCSC PDP-BST JACKETS INSTALLATION PROCEDURE | 2745-PP-OF-135 | AD-814-G-40116 |  |  |  | T-378/26
| GPF-II JACKET INSTALLATION MANUAL | 2745-PP-OF-136 | AD-845-G-00230 | A1 |  |  | T-345/26
| WHT-3 TOPSIDE INSTALLATION PROCEDURE | 2745-PP-OF-142 | requested | A1 |  |  | T-383/26
|  |  |  | 1 |  |  | T-392/26 | 2026-09-03
| ZWSC-PDP TOPSIDES INSTALLATION PROCEDURE | 2745-PP-OF-143 | requested
| BRIDGE 18 INSTALLATION PROCEDURE AT ZWSC-PDP | 2745-PP-OF-144 | requested | A1 |  |  | T-352/26
| BRIDGE 19 INSTALLATION PROCEDURE AT ZCSC-PDP | 2745-PP-OF-147 | requested | A1 |  |  | T-385/26

## Setup Plans & Anchor Patterns
NMDC DOC. No.: MDR-001
EPC WORKS FOR EPS-2 AND PDP PROJECT
|  | NMDC PROJECT NO. 2745 | [11 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-09-07
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE : | REF | date | ref | CODE
| ANCHORE PATTERN FOR BARGE DLB-750 DURING PIPELAY OF 16" WI (WPL-2) FROM WHT-2 TO WHT-3 | 2745-AP-0007 | AD-27-PL-625103 | 1 |  |  | T-074/26 | 2026-02-16 | 2026-02-24 | 2745-NMDC-E-AO-T-01048 | 2026-04-20 | 11688-NMDC-TR-04503 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-180/26 | 2026-04-28 | 2026-05-01 | 2745-NMDC-E-AO-T-01280 | 2026-05-13 | 11688-NMDC-TR-04662 | 3 - Reviewed with Comments | 2026-05-01 | 2745-NMDC-E-MWS-T-00065
|  |  |  | 3 |  |  | T-204/26 | 2026-05-13 | 2026-05-18 | 2745-NMDC-E-AO-T-01352 | 2026-07-01 | 11688-NMDC-TR-04925 | 1 - Approved | 2026-05-18 | 2745-NMDC-E-MWS-T-00081
|  |  |  | 4 |  |  | T-261/26 | 2026-06-24 | 2026-07-10 | 2745-NMDC-E-AO-T-01576 | 2026-07-14 | 11688-NMDC-TR-05005 | 1 - Approved |  |  | 2026-08-12 | SAF-220-MCE-NMDC-T-0039 | 1. Approved
| ANCHORE PATTERN FOR BARGE DLB-750 DURING PIPELAY OF 16" WF (OPL-2) FROM WHT-3 TO WHT-2 | 2745-AP-0008 | AD-27-PL-625104 | 1 |  |  | T-074/26 | 2026-02-16 | 2026-02-24 | 2745-NMDC-E-AO-T-01048 | 2026-04-20 | 11688-NMDC-TR-04503 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-180/26 | 2026-04-28 | 2026-05-01 | 2745-NMDC-E-AO-T-01280 | 2026-05-13 | 11688-NMDC-TR-04662 | 3 - Reviewed with Comments | 2026-05-01 | 2745-NMDC-E-MWS-T-00065
|  |  |  | 3 |  |  | T-204/26 | 2026-05-13 | 2026-05-18 | 2745-NMDC-E-AO-T-01352 | 2026-07-01 | 11688-NMDC-TR-04925 | 1 - Approved | 2026-05-18 | 2745-NMDC-E-MWS-T-00081
|  |  |  | 4 |  |  | T-261/26 | 2026-06-24 | 2026-07-10 | 2745-NMDC-E-AO-T-01576 | 2026-07-14 | 11688-NMDC-TR-05005 | 1 - Approved |  |  | 2026-08-12 | SAF-220-MCE-NMDC-T-0039 | 1. Approved
| ANCHORE PATTERN FOR BARGE DLB-750 DURING PIPELAY OF 18" WI FROM ZWSC (RP-1) TO WHT-2 | 2745-AP-0009 | AD-27-PL-625105 | 1 |  |  | T-007/26 | 2026-01-06 | 2026-02-25 | 2745-NMDC-E-AO-T-01054 | 2026-06-17 | 11688-NMDC-TR-04844 | 3 - Reviewed with Comments | 24-Feb-2026 | 2745-NMDC-E-MWS-T-00032 | 2026-04-09 | SAF-220-MCE-NMDC-T-0013 | 1. Approved
|  |  |  | 2 |  |  | T-358/26 | 2026-08-20 | 2026-08-13 | 2745-NMDC-E-AO-T-01710 |  |  |  | 2026-08-12 | 2745-NMDC-E-MWS-T-00168 | 2026-08-25 | SAF-220-MCE-NMDC-T-0041 | 1. Approved
| ANCHORE PATTERN FOR BARGE DLB-750 DURING PIPELAY OF 20" WF FROM WHT-2 TO ZWSC (RP-1) | 2745-AP-0010 | AD-27-PL-625106 | 1 |  |  | T-007/26 | 2026-01-06 | 2026-02-25 | 2745-NMDC-E-AO-T-01054 | 2026-06-17 | 11688-NMDC-TR-04844 | 3 - Reviewed with Comments | 2026-02-24 | 2745-NMDC-E-MWS-T-00032 | 2026-04-09 | SAF-220-MCE-NMDC-T-0013 | 1. Approved
|  |  |  | 2 |  |  | T-358/26 | 2026-08-20 | 2026-08-12 | 2745-NMDC-E-AO-T-01710 |  |  |  | 2026-08-12 | 2745-NMDC-E-MWS-T-00168 | 2026-08-25 | SAF-220-MCE-NMDC-T-0041 | 1. Approved
| ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY OF 24'' WF(OPL-4) FROM ZCSC-CRP TO ZWSC-RP-1 | 2745-AP-0011 | AD-27-PL-625107 | 1 |  |  | T-137/26 | 2026-04-07 | 2026-04-07 | 2745-NMDC-E-AO-T-01180 | 2026-06-17 | 11688-NMDC-TR-04844 | 3 - Reviewed with Comments | 2026-04-07 | 2745-NMDC-E-MWS-T-00048
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING RISER GUARD REMOVAL AND 18'' & 20'' RISER INSTALLATION AT WHT-2 PLATFORM (WEST FACE) | 2745-AP-0012 | AD-27-PL-625108-SHT-001 | 1 |  |  | T-121/26 | 2026-03-27 | 2026-03-30 | 2745-NMDC-E-AO-T-01140 | 2026-04-20 | 11688-NMDC-TR-04503 | 3 - Reviewed with Comments | 2026-03-30 | 2745-NMDC-E-MWS-T-00041
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING RISER GUARD REMOVAL AND 16'' & 16'' RISER INSTALLATION AT WHT-3 PLATFORM | 2745-AP-0013 | AD-27-PL-625109-SHT-001 | 1 |  |  | T-121/26 | 2026-03-27 | 2026-03-30 | 2745-NMDC-E-AO-T-01140 | 2026-04-20 | 11688-NMDC-TR-04503 | 3 - Reviewed with Comments | 2026-03-30 | 2745-NMDC-E-MWS-T-00041
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING RISER GUARD REMOVAL AND 16'' & 16'' RISER INSTALLATION AT WHT-2 PLATFORM (EAST FACE) | 2745-AP-0014 | AD-27-PL-625110-SHT-001 | 1 |  |  | T-121/26 | 2026-03-27 | 2026-03-30 | 2745-NMDC-E-AO-T-01140 | 2026-04-20 | 11688-NMDC-TR-04503 | 3 - Reviewed with Comments | 2026-03-30 | 2745-NMDC-E-MWS-T-00041
| ANCHOR PATTERN FOR BARGE DLB-750 DURING 18'' , 20'' AND 24'' WI RISERS INSTALLATION AND RISER GUARD REMOVAL AND AT ZWSC (RP-1) | 2745-AP-0015 | AD-27-PL-625111-SHT-001 | 1 |  |  | T-312/26 | 2026-07-21 | 2026-07-24 | 2745-NMDC-E-AO-T-01626 | 2026-07-29 | 11688-NMDC-TR-05115 | 3 - Reviewed with Comments | 2026-07-24 | 2745-NMDC-E-MWS-T-00141
| ANCHOR PATTERN FOR BARGE DLB-750 DURING 24" WF RISER INSTALLATION AND GUARD REMOVAL @CRP AT ZCSC PDP (OPL-4) | 2745-AP-0016 | AD-27-PL-625112-SHT-001
| ANCHOR PATTERN FOR BARGE DLS-4200 DURING WHT-3 TOPSIDE INSTALLATION | 2745-AP-0017 | AD-27-PL-625117-SHT-001 | 1 |  |  | T-393/26 | 2026-09-04
| SET- UP DRAWING FOR WHT-2 TOPSIDE INSTALLATION | 2745-AP-0018 | AD-27-PL-625118-SHT-001
| DLS-4200 ANCHOR PATTERN DURING ZWSC PDP TOPSIDE INSTALLATION | 2745-AP-0019 | AD-27-PL-625119-SHT-001
| DLB-1000 ANCHOR PATTERN During ZCSC-PDP Installation | 2745-AP-0020 | AD-27-PL-625120
| SET- UP DRAWING FOR ZWSC PDP JACKET INSTALLATION | 2745-AP-0021 | AD-27-PL-625121-SHT-001
| DLS-4200 ANCHOR PATTERN During ZWSC-GPF-II Jacket Installation | 2745-AP-0022 | AD-27-PL-625122
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING ZWSC BST-1 INSTALLATION | 2745-AP-0023 | AD-27-PL-625113-SHT-001
| DLB-1000 ANCHOR PATTERN During ZCSC PDP-BST Installation | 2745-AP-0024 | AD-27-PL-625114
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING GPF-II BST INSTALLATION | 2745-AP-0025 | AD-27-PL-625115-SHT-001
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING ZWSC PDP JACKET INSTALLATION | 2745-AP-0026 | AD-27-PL-625116-SHT-001
| SET- UP DRAWING FOR WHT-3 TOPSIDE INSTALLATION | 2745-AP-0027 | AD-27-PL-625123-SHT-001
| SET- UP DRAWING FOR WHT-2 TOPSIDE INSTALLATION | 2745-AP-0028 | AD-27-PL-625124-SHT-001
| SET- UP DRAWING FOR ZWSC PDP TOPSIDE INSTALLATION | 2745-AP-0029 | AD-27-PL-625125-SHT-001
| SET- UP DRAWING FOR ZSCSC PDP TOPSIDE INSTALLATION | 2745-AP-0030 | AD-27-PL-625126-SHT-001
| SET- UP DRAWING FOR GPF-II JACKET INSTALLATION | 2745-AP-0031 | AD-27-PL-625127-SHT-001
| SET- UP DRAWING FOR ZWSC PDP JACKET INSTALLATION | 2745-AP-0032 | AD-27-PL-625128-SHT-001
| SET- UP DRAWING FOR ZWSC PDP BRIDGE INSTALLATION | 2745-AP-0033 | AD-27-PL-625129-SHT-001
| DLB-1000 ANCHOR PATTERN During Bridge-19 Installation at ZCSC PDP | 2745-AP-0034 | AD-27-PL-625130-SHT-001
| SET- UP DRAWING FOR GPF-II BRIDGES INSTALLATION | 2745-AP-0035 | AD-27-PL-625131-SHT-001
| SET- UP DRAWING FOR FLARE SUPPORT INSTALLATION | 2745-AP-0036 | AD-27-PL-625132-SHT-001
| ANCHOR PATTERN OF B-42 DURING GPF-II FLOATOVER | 2745-AP-0037 | AD-27-PL-625133-SHT-001
| ANCHORE PATTERN FOR BARGE DLB-750 DURING SLEEPER INSTALLATION AT CROSSING LOCATION FOR 20" WF FROM WHT-2 TO ZWSC (RP-1) | 2745-AP-0038 | AD-27-PL-625134-SHT-001 | 1 |  |  | T-074/26 | 2026-02-16 | 2026-02-24 | 2745-NMDC-E-AO-T-01048 | 2026-04-08 | 11688-NMDC-TR-04399 | 3 - Reviewed with Comments | 2026-03-23 | 2745-NMDC-E-MWS-T-00038 | 2026-04-09 | SAF-220-MCE-NMDC-T-0013 | 1. Approved
|  |  |  | 2 |  |  | T-167/26 | 2026-04-17 | 2026-04-22 | 2745-NMDC-E-AO-T-01224 | 2026-05-05 | 11688-NMDC-TR-04601 | 2 - Approved with Comments | 2026-04-21 | 2745-NMDC-E-MWS-T-00053
|  |  |  | 3 |  |  | T-191/26 | 2026-05-06 | 2026-05-11 | 2745-NMDC-E-AO-T-01313 | 2026-07-01 | 11688-NMDC-TR-04925 | 1 - Approved | 2026-05-11 | 2745-NMDC-E-MWS-T-00072 | 2026-06-01 | SAF-220-MCE-NMDC-T-0021 | 1. Approved
|  |  |  | 4 |  |  | T-258/26 | 2026-06-22 | 2026-07-20 | 2745-NMDC-E-AO-T-01604 |  |  |  | 2026-04-17 | 2745-NMDC-E-MWS-T-00136
| DLB-750 AP DURING RISER GUARD REMOVAL AND RISER INSTALLATION WHT-2 (EAST FACE) | 2745-AP-0039 | AD-848-PL-625044-SHT-001 | 1 |  |  | T-215/26 | 2026-05-15 | 2026-05-22 | 2745-NMDC-E-AO-T-01355 | 2026-07-01 | 11688-NMDC-TR-04925 | 3 - Reviewed with Comments | 2026-05-18 | 2745-NMDC-E-MWS-T-00083
|  |  |  | 2 |  |  | T-315/26 | 2026-07-21 | 2026-07-28 | 2745-NMDC-E-AO-T-01639 | 2026-07-31 | 11688-NMDC-TR-05137 | 1 - Approved | 2026-07-27 | 2745-NMDC-E-MWS-T-00145
| DLB-750 AP DURING RISER GUARD REMOVAL AND RISER INSTALLATION WHT-2 (WEST FACE) | 2745-AP-0040 | AD-848-PL-625045-SHT-001 | 1 |  |  | T-215/26 | 2026-05-15 | 2026-05-22 | 2745-NMDC-E-AO-T-01355 | 2026-07-01 | 11688-NMDC-TR-04925 | 3 - Reviewed with Comments | 2026-05-18 | 2745-NMDC-E-MWS-T-00083
|  |  |  | 2 |  |  | T-315/26 | 2026-07-21 | 2026-07-28 | 2745-NMDC-E-AO-T-01639 | 2026-07-31 | 11688-NMDC-TR-05137 | 1 - Approved | 2026-07-27 | 2745-NMDC-E-MWS-T-00145
| DLB-750 AP DURING RISER GUARD REMOVAL AND RISER INSTALLATION WHT-3 | 2745-AP-0041 | AD-849-PL-625027-SHT-001 | 1 |  |  | T-215/26 | 2026-05-15 | 2026-05-22 | 2745-NMDC-E-AO-T-01355 | 2026-07-01 | 11688-NMDC-TR-04925 | 3 - Reviewed with Comments | 2026-05-18 | 2745-NMDC-E-MWS-T-00083
|  |  |  | 2 |  |  | T-315/26 | 2026-07-21 | 2026-07-28 | 2745-NMDC-E-AO-T-01639 | 2026-07-31 | 11688-NMDC-TR-05137 | 2 - Approved with Comments | 2026-07-27 | 2745-NMDC-E-MWS-T-00145
| ANCHOR PATTERN FOR BARGE DLB-750 DURING SLEEPER INSTALLATION AT CROSSING LOCATIONS OPL2-CR04 & OPL2-CR05 FOR 16'' WF(OPL-2) FROM WHT-3 TO WHT-2 | 2745-AP-0042 | AD-849-PL-625028-SHT-001 | 1 | 1 |  | T-257/26 | 2026-06-20 | 2026-06-26 | 2745-NMDC-E-AO-T-01510 | 2026-07-21 | 11688-NMDC-TR-05059 | 3 - Reviewed with Comments | 2026-06-25 | 2745-NMDC-E-MWS-T-00108
|  |  |  | 2 | 1 |  | T-329/26 | 2026-07-31 | 2026-08-03 | 2745-NMDC-E-AO-T-01660 | 2026-08-05 | 11688-NMDC-TR-05158 | 1 - Approved | 2026-08-03 | 2745-NMDC-E-MWS-T-00151
| DLB-750 STANDBY ANCHOR PATTERN DURING RISERS INSTALLATION AT ZWSC-RP1 | 2745-AP-0043 | AD-557-PL-625043-SHT-001 | 1 | 1 |  | T-323/26 | pmt | 2026-07-28 | 2745-NMDC-E-AO-T-01590 |  |  |  | 2026-07-28 | 2745-NMDC-E-MWS-T-00130
| DLS-4200 ANCHOR PATTERN DURING WHT-2 TOPSIDE INSTALLATION | 2745-AP-0044 | AD-848-PL-625046-SHT-001 | 1 | 1 |  | T-320/26 | 2026-07-24 | 2026-08-06 | 2745-NMDC-E-AO-T-01672 |  |  |  | 2026-08-05 | 2745-NMDC-E-MWS-T-00158
| LB-II ANCHOR PATTERN DURING FLOATOVER INSTTALLATION OF ZCSC-PDP DECK | 2745-AP-0045
| DLB-1000 ANCHOR PATTERN During ZCSC-PDP Boatlanding Installation | 2745-AP-0046
| DLB-750 STANDBY ANCHOR PATTERN DURING RISER INSTALLATION AT WHT-3 | 2745-AP-0047 | requested | 1 | 1 |  | T-386/26 | 2026-08-31 | 2026-09-02 | 2745-NMDC-E-AO-T-01790 |  |  |  | 2026-09-01 | 2745-NMDC-E-MWS-T-00190
| MUTAWA-17 SET-UP PLAN AT ZWSC-RP1 BOATLANDING-OPTION-1 | 2745-AP-0201 |  | 1 |  |  | T-176/26 | 2026-04-24
| MUTAWA-17 SET-UP PLAN AT ZWSC-RP1 BOATLANDING-OPTION-2 | 2745-AP-0202 |  | 1 |  |  | T-176/26 | 2026-04-24
| HUAXIA HONGHU01 SETUP PLAN DURING HOOK-UP WORKS AT ZWSC RP1 | 2745-DP-0001 | AD-557-G-00102 | 1 |  |  | T-038/26 | 2026-01-27 | 2026-02-20 | 2745-NMDC-E-AO-T-01049
| BLUE TITANIUM SETUP PLAN DURING HOOK-UP WORKS AT ZWSC RP1 | 2745-DP-0002 | AD-557-G-00103 | 1 |  |  | T-008/26 | 2026-01-07
| HUAXIA HONGHU01 SETUP PLAN DURING HOOK-UP WORKS AT ZWSC RP | 2745-DP-0003 | AD-201-PL-625000-SHT-001 | 1 |  |  | T-018/26 | 2026-01-14
| HEA VANTAGE SET-UP PLAN AT ZWSC-RP1 | 2745-DP-0004 | AD-557-PL-625011-SHT-001 | 1 |  |  | T-038/26 | 2026-01-27 | 2026-02-24 | 2745-NMDC-E-AO-T-01049 | 2026-04-03 | 11688-NMDC-TR-04372 | 5. rejected
|  |  |  | 2 |  |  | T-177/26 | 2026-04-24 | 2026-04-25 | 2745-NMDC-E-AO-T-01255 | 2026-04-30 | 11688-NMDC-TR-04587 | 1 - Approved
|  |  |  | 3 |  |  | T-317/26 | 2026-07-22 | 2026-07-28 | 2745-NMDC-E-AO-T-01643 | 2026-07-30 | 11688-NMDC-TR-05124 | 5 - Rejected
|  |  |  | 4 |  |  | T-373/26 | 2026-08-26
| HEA VANTAGE SETUP PLAN AT ZCSC CRP | 2745-DP-0005 | AD-496-PL-625019-SHT-001 | 1 |  |  | T-077/26 | 2026-02-23 | 2026-02-24 | 2745-NMDC-E-AO-T-01052 | 2026-04-09 | 11688-NMDC-TR-04399 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-235/26 | 2026-06-08 | 2026-06-10 | 2745-NMDC-E-AO-T-01421
|  |  |  | 3 |  |  | T-260/26 | 2026-06-23 | 2026-06-23 | 2745-NMDC-E-AO-T-01496 | 2026-07-21 | 11688-NMDC-TR-05059 | 3 - Reviewed with Comments
|  |  |  | 4 |  |  | T-394/26 | 2026-09-04 | 2026-09-07 | 2745-NMDC-E-AO-T-01807
| HEA VANTAGE SET-UP PLAN AT ZWSC-RP | 2745-DP-0006 | AD-557-PL-625013-SHT-001 | 1 |  |  | T-117/26 | 2026-03-18 | 2026-03-24 | 2745-NMDC-E-AO-T-01118 | 2026-04-03 | 11688-NMDC-TR-04372 | 5. rejected
|  |  |  | 2 |  |  | T-195/26 | 2026-05-07 | 2026-05-08 | 2745-NMDC-E-AO-T-01311 | 2026-04-03 | 11688-NMDC-TR-04662 | 3 - Reviewed with Comments
|  |  |  | 3 |  |  | T-222/26 | 2026-05-19 | 2026-05-19 | 2745-NMDC-E-AO-T-01363 | 2026-05-22 | 11688-NMDC-TR-04768 | 2 - Approved with Comments
|  |  |  | 4 |  |  | T-240/26 | 2026-06-09 | 2026-06-10 | 2745-NMDC-E-AO-T-01433 | 2026-07-21 | 11688-NMDC-TR-05059 | 3 - Reviewed with Comments
| HEA VANTAGE SET-UP PLAN AT ZWSC-S9 | 2745-DP-0007 | AD-557-PL-625014-SHT-001 | 1 |  |  | T-117/26 | 2026-03-18 | 2026-03-24 | 2745-NMDC-E-AO-T-01118 | 2026-04-17 | 11688-NMDC-TR-04372 | 5. rejected
| HEA VANTAGE SET-UP PLAN AT ZWSC-RP1 WITH SUPPLY VESSEL MOORING ARRANGEMENT | 2745-DP-0008 | AD-557-PL-625037-SHT-001 | 1 |  | AAA cancelled 23/7/26 | T-188/26 | 2026-05-04 | 2026-05-01 | 2745-NMDC-E-AO-T-01292 | 2026-05-13 | 11688-NMDC-TR-04673 | 5. rejected
| SEAFOX TRIDENT-1 SET-UP AT ZK-288 | 2745-DP-0009 | AD-311-PL-625005-SHT-001 | 1 | 1 |  | T-236/26 | 2026-06-08 | 2026-06-10 | 2745-NMDC-E-AO-T-01422 | 2026-06-18 | 11688-NMDC-TR-04848 | 2 - Approved with Comments
|  |  |  | 2 | 1 |  | T-270/26 | 2026-06-29 | 2026-07-07 | 2745-NMDC-E-AO-T-01555
| SEAFOX TRIDENT-1 SET-UP AT ZK-235 | 2745-DP-0010 | AD-27-PL-625576-SHT-001 | 1 | 1 |  | T-280/26 | 2026-07-06 | 2026-07-07 | 2745-NMDC-E-AO-T-01553 | 2026-07-17 | 11688-NMDC-TR-05032 | 1 - Approved
| SEAFOX TRIDENT-1 SET-UP AT ZK-35 | 2745-DP-0011 | AD-27-PL-625577-SHT-001 | 1 | 1 |  | T-280/26 | 2026-07-06 | 2026-07-07 | 2745-NMDC-E-AO-T-01553 | 2026-07-17 | 11688-NMDC-TR-05032 | 2 - Approved with Comments
| SEAFOX TRIDENT-1 SET-UP AT ZK-11 | 2745-DP-0012 | AD-27-PL-625578-SHT-001 | 1 | 1 |  | T-280/26 | 2026-07-06 | 2026-07-07 | 2745-NMDC-E-AO-T-01553 | 2026-07-17 | 11688-NMDC-TR-05032 | 2 - Approved with Comments
| LOWER ZAKUM - HEA KRAKEN SET-UP PLAN AT ZWSC RP1 | 2745-DP-0013 | AD-557-PL-625038-SHT-001 | 1 | 1 |  | T-302/26 | 2026-07-14 | 2026-07-22 | 2745-NMDC-E-AO-T-01609 | 2026-07-24 | 11688-NMDC-TR-05094 | 3 - Reviewed with Comments
| LOWER ZAKUM - HEA KRAKEN SET-UP PLAN AT ZWSC RP | 2745-DP-0014 | AD-201-PL-625001-SHT-001 | 1 | 1 |  | T-302/26 | 2026-07-14 | 2026-07-22 | 2745-NMDC-E-AO-T-01609 | 2026-07-24 | 11688-NMDC-TR-05094 | 3 - Reviewed with Comments
|  |  |  | 2 | 1 |  | T-330/26 | 2026-07-31 | 2026-08-03 | 2745-NMDC-E-AO-T-01661 | 2026-08-05 | 11688-NMDC-TR-05158 | 3 - Reviewed with Comments
|  |  |  | 3 |  |  | T-350/26 | 2026-08-14 | 2026-09-02 | 2745-NMDC-E-AO-T-01788
| SAFEEN-3000 SETUP PLAN DURING ZWSC-PDP JACKET INSTALLATION | 2745-DP-0015 | AD-816-PL-625005-SHT-001 | 1 | 1 |  | T-326/26 | 2026-07-30 | 2026-08-10 | 2745-NMDC-E-AO-T-01687
| SAFEEN-3000 SETUP PLAN DURING ZWSC PDP-BST JACKET INSTALLATION | 2745-DP-0016 | AD-816-PL-625006-SHT-001 | 1 | 1 |  | T-326/26 | 2026-07-30 | 2026-08-10 | 2745-NMDC-E-AO-T-01687

## Sketches
NMDC DOC. No.: MDR-001
EPC WORKS FOR EPS-2 AND PDP PROJECT
|  | NMDC PROJECT NO. 2745 | [6 empty] | REVISION : | 0
|  | OFFSHORE Sketches | [6 empty] | DATE : | 2026-09-07
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| SEP-550 Setup Plans at ZWSC-GPF-II-RP-2_option | 2745-A3-002 |  | 0 |  |  | 2025-02-24 | EJJ
| (UMM SHAIF AP during Cable (CL-3011) startup at AGI) | 2745-A1-001 |  | A |  |  | 2025-04-02 | SKV
| (UMM SHAIF AP during Cable (CL-3141) startup at AGI) | 2745-A1-002 |  | A |  |  | 2025-04-02 | SKV
| (PESTO Setup Plans at ZCSC-PDP) | 2745-A3-007 |  | 0 |  |  | 2025-06-11 | SKV
| (PILIPILI Setup Plans at ZCSC-PDP) | 2745-A3-008 |  | 0 |  |  | 2025-06-11 | SKV
| 2745-A3-009 to 010_Rev-A (AL MARYAH Setup during mattress installation at Cable (CL2&CL3 & CL4) Crossing Location) | 2745-A3-009 |  | A |  |  | 2025-06-17 | SKV
| 2745-A3-015 to 016_Rev-A (SAFEEN PEARL Setup during mattress installation at Cable (CL2&CL3&CL4) Crossing Location) | 2745-A3-015 |  | A |  |  | 2025-06-24 | SKV
| 2745-AP-0037_Rev-A(B-42 AP during GPF-II Float over) | 2745-AP-0037 |  | A |  |  | 2025-07-09 | EJJ
| 2745-A1-005_REV-A(DLB-1000 AP during OPL-4 Riser installation at ZWSC-RP1) | 2745-A1-005 |  | A |  |  | 2025-08-14 | SKV
| 2745-A1-004 _REV-A(DLB-1000 AP during OPL-4 Riser installation at ZCSC CRP) | 2745-A1-004 |  | A |  |  | 2025-08-14 | SKV
| 2745-A1-005_REV-A(DLB-1000 AP during OPL-4 Riser installation at ZWSC-RP1) | 2745-A1-005 |  | A |  |  | 2025-08-14 | SKV
| 2745-A1-006_REV-A(DLB-750 AP during OPL-4 Start-up at ZCSC CRP) | 2745-A1-006 |  | A |  |  | 2025-08-14 | SKV
| 2745-A1-007_REV-A(DLB-750 AP during OPL-4 Start-up at ZWSC-RP1) | 2745-A1-007 |  | A |  |  | 2025-08-14 | SKV
| 2745-A1-009_REV-A(DLB-750 AP during OPL-3 Start-up at ZWSC-RP1) | 2745-A1-009 |  | A |  |  | 2025-09-02 | SKV
| 2745-A1-010_REV-A(DLB-750 AP during OPL-3 Laydown at WHT-2) | 2745-A1-010 |  | A |  |  | 2025-09-02 | SKV
| 2745-A1-011_REV-A(DLB-750 AP during WPL-3 Start-up at ZWSC-RP1) | 2745-A1-011 |  | A |  |  | 2025-09-02 | SKV
| 2745-A1-012_REV-A(DLB-750 AP during WPL-3 Laydown at WHT-2) | 2745-A1-012 |  | A |  |  | 2025-09-02 | SKV
| 2745-A1-013-1 TO 4_REV-A(SHEERLEG AP during ZCSC PDP DECK INSTALLATION) | 2745-A1-013 |  | A |  |  | 2025-09-03 | SKV
| 2745-A1-014_REV-A(DLS-4200 AP during ZWSC-GPF-2 Jacket Installation) | 2745-A1-014 |  | A |  |  | 2025-09-04 | SKV
| 2745-A1-009_REV-A(DLB-750 AP during OPL-3 Start-up at ZWSC-RP1) | 2745-A1-009 |  | A |  |  | 2025-09-15 | SKV
| 2745-A1-011_REV-A(DLB-750 AP during WPL-3 Start-up at ZWSC-RP1) | 2745-A1-011 |  | A |  |  | 2025-09-15 | SKV
| 2745-A1-015_REV-A(DLB-750 AP during OPL-4 Start-up at ZWSC-RP1) | 2745-A1-015 |  | A |  |  | 2025-09-15 | SKV
| 2745-A1-013-1 TO 4_REV-A(SHEERLEG AP during ZCSC PDP DECK INSTALLATION) | 2745-A1-013 |  | A |  |  | 2025-09-16 | SKV
| 2745-AP-0037-1 TO 3_Rev-A(B-42 AP during GPF-II Float over) | 2745-AP-0037 |  | A |  |  | 2025-09-18 | EJJ
| 2745-A1-020_REV-A(DLS-4200 AP during ZCSC PDP DECK INSTALLATION)-STUDY-1 | 2745-A1-020 |  | A |  |  | 2025-10-14 | SKV
| 2745-A1-020-1 TO 3_REV-A(DLS-4200 AP during ZCSC PDP DECK INSTALLATION)-STUDY-2 | 2745-A1-020 |  | A |  |  | 2025-10-14 | SKV
| 2745-A1-006_REV-A(DLB-750 AP during OPL-4 Start-up at ZCSC CRP) | 2745-A1-006 |  | A |  |  | 2025-10-17 | SKV
| (SHEERLEG AP during ZCSC PDP DECK INSTALLATION) | 2745-A1-021 |  | A |  |  | 2025-11-03 | SKV
| 2745-A1-022-1 TO 4_REV-A(SHEERLEG AP during ZCSC PDP DECK INSTALLATION)-option | 2745-A1-022 |  | A |  |  | 2025-11-04 | SKV
| 2745-A1-015_REV-B(DLB-750 AP during OPL-4 Start-up at ZWSC-RP1) | 2745-A1-015 |  | B |  |  | 2025-11-02 | SKV
| 2745-A1-009_REV-B(DLB-750 AP during OPL-3 Start-up at ZWSC-RP1) | 2745-A1-009 |  | B |  |  | 2025-11-02 | SKV
| 2745-A1-011_REV-B(DLB-750 AP during WPL-3 Start-up at ZWSC-RP1) | 2745-A1-011 |  | B |  |  | 2025-11-02 | SKV
| 2745-A3-020_R1 (PILIPILI Setup Plan at ZCSC-CSP) | 2745-A3-020 |  | 1 |  |  | 2025-11-26 | SKV
| 2745-A3-047_R0 (PILIPILI Setup Plan at ZCSC-PDP) | 2745-A3-047 |  | 0 |  |  | 2025-11-26 | SKV
| 2745-A1-023_REV-B(PL-OPL-3 & WPL-3 Laydown at WHT-2) | 2745-A1-023 |  | B |  |  | 2025-12-12 | SKV
| 2745-A3-029_RevB(HUAXIA HONGHU01 Setup at ZWSC RP1) | 2745-A3-029 |  | B |  |  | 2025-12-16 | SKV
| 2745-A3-045_RevA(BLUE TITANIUM Setup at ZWSC RP1)OPTION-2 | 2745-A3-045 |  | A |  |  | 2025-12-16 | SKV
| 2745-A1-024_REV-A(PLB-648 AP during Riser guard removal at ZCSC CRP) | 2745-A1-024 |  | A |  |  | 2025-12-18 | EJJ
| 2745-A1-025_REV-A(PLB-648 AP during Riser guard removal at ZWSC-RP1) | 2745-A1-025 |  | A |  |  | 2025-12-18 | EJJ
| 2745-A3-029_RevB HUAXIA HONGHU01 Setup at ZWSC RP1) | 2745-A3-029 |  | B |  |  | 2025-12-18 | SKV
| 2745-A3-045_RevA(BLUE TITANIUM Setup at ZWSC RP1)OPTION-1 | 2745-A3-045 |  | A |  |  | 2025-12-18 | SKV
| 2745-AP-0010-1 TO 3_R1(DLB-750 AP during OPL-3 pipelay) | 2745-AP-0010 |  | 1 |  |  | 2025-12-21 | SKV
| 2745-DP-0001_R1(HUAXIA HONGHU01 Setup at ZWSC RP-1) | 2745-DP-0001 |  | 1 |  |  | 2025-12-27 | SKV
| 2745-DP-0002_R1(BLUE TITANIUM Setup at ZWSC RP-1) | 2745-DP-0002 |  | 1 |  |  | 2025-12-27 | SKV
| 2745-A1-026_Rev-A(HUAXIA HONGHU01 Setup at ZWSC GIP) | 2745-A1-026 |  | A |  |  | 2026-01-13 | SKV
| 2745-AP-0007-1 & 2_R1(DLB-750 AP during WPL-2 pipelay) | 2745-AP-0007 |  | 1 |  |  | 2026-01-18 | EJJ
| 2745-AP-0008-1 & 2_R1(DLB-750 AP during OPL-2 pipelay) | 2745-AP-0008 |  | 1 |  |  | 2026-01-21 | EJJ
| 2745-DP-0004_R1(HEA VANTAGE SET-UP @ ZWSC RP-1) | 2745-DP-0004 |  | 1 |  |  | 2026-01-23 | EJJ
| 2745-DP-0005_R1(HEA VANTAGE SET-UP @ ZCSC-CRP) | 2745-DP-0005 |  | 1 |  |  | 2026-01-23 | EJJ
| 2745-AP-0009-1 TO 3_R2(DLB-750 AP during WPL-3 pipelay) | 2745-AP-0009 |  | 2 |  |  | 2026-01-26 | SKV
| 2745-AP-0010-1 TO 3_R2(DLB-750 AP during OPL-3 pipelay) | 2745-AP-0010 |  | 2 |  |  | 2026-01-26 | SKV
| 2745-A1-030_Rev-A(SAFEEN-3000 AP during PDP JKT installation) | 2745-A1-030 |  | A |  |  | 2026-01-27 | SKV
| 2745-A1-029-1 TO 4_Rev-A(LB-11 Setup during PDP Deck installation_Floatover) | 2745-A1-029 |  | A |  |  | 2026-01-27 | SKV
| 2745-AP-XXXX-1 TO 5_R1(DLB-750 AP during Sleeper installation at crossing for OPL-3 PL) | 2745-AP-XXXX |  | 1 |  |  | 2026-02-04 | SKV
| 2745-AP-0000-1 OF 4_R1(DLB-750 AP during Riser Guard Removal and Riser installation at RP-1) | 2745-AP-0000 |  | 1 |  |  | 2026-02-06 | SKV
| 2745-SEATECH 61MFSIV (SUPPLY VESSEL) SETUP AT ZWSC-RP2 | -- |  | - |  |  | 2026-02-16 | SKV
| 2745-A1-029-1 TO 6_Rev-A(LB-11 Setup during PDP Deck installation_Floatover) | 2745-A1-029 |  | A |  |  | 2026-02-17 | SKV
| 2745-AP-0019_R1(DLS-4200 AP during ZWSC PDP Topside Instllation) | 2745-AP-0019 |  | 1 |  |  | 2026-02-24 | SKV
| 2745-A1-031_Rev-A(Details for DLB-750 Mooring line connection to jkt leg during WPL-3 Pipelay) | 2745-A1-031 |  | 1 |  |  | 2026-02-24 | SKV
| 2745-AP-0038-1 TO 5_R2(DLB-750 AP during Sleeper installation at crossing for OPL-3 PL) | 2745-AP-0038 |  | 2 |  |  | 2026-04-03 | SKV
| 2745-A1-034_Rev-A(DLB-1000 AP during ZCSC PDP JKT Installation) | 2745-A1-034 |  | A |  |  | 2026-04-13 | SKV
| 2745-A1-034_Rev-A(DLB-1000 AP during ZCSC PDP JKT Installation)-option | 2745-A1-034 |  | A |  |  | 2026-04-13 | SKV
| 2745-A1-034-1 TO 2_Rev-A(DLB-1000 AP during ZCSC PDP JKT Installation) | 2745-A1-034 |  | A |  |  | 2026-04-13 | SKV
| 2745-AP-0000_R1(DLB-750 AP during13A & 13B Spool installation at RP-1) | 2745-AP-0000 |  | 1 |  |  | 2026-04-16 | SKV
| 2745-AP-XXXX-1 TO 3_R1(DLB-750 AP during Riser Guard Removal and Riser installation AT WHT-2 (EAST FACE) |  |  | 1 |  |  | 2026-04-21 | EJJ
| 2745-AP-XXXX-1 TO 3_R1(DLB-750 AP during Riser Guard Removal and Riser installation AT WHT-2 (WEST FACE) |  |  | 1 |  |  | 2026-04-21 | EJJ
| 2745-AP-XXXX-1 TO 3_R1(DLB-750 AP during Riser Guard Removal and Riser installation AT WHT-3) |  |  | 1 |  |  | 2026-04-21 | EJJ
| 2745-A1-035_Rev-A (Sequence for WHT-2 Topside Installation) | 2745-A1-035 |  | A |  |  | 2026-04-22 | SKV
| 2745-A3-053_Rev-A(CB&SPACER BARGE Mooring arrangemetn with SHEERLEG during Topside Installation) | 2745-A3-053 |  | A |  |  | 2026-04-22 | SKV
| 2745-AP-0028_R1(SHEERLEG AP during WHT-2 Topside Installation) | 2745-AP-0028 |  | A |  |  | 2026-04-22 | SKV
| 2745-A3-017_Rev-B(SAFEEN PEARL SETUP DURING (CL-4) 6.6kV CABLE LAYDOWN AT WHT-3) | 2745-A3-017 |  | B |  |  | 2026-04-23 | SKV
| 2745-A3-018_Rev-B(SAFEEN PEARL SETUP DURING (CL-3) 6.6kV CABLE LAYDOWN AT WHT-3) | 2745-A3-018 |  | B |  |  | 2026-04-23 | SKV
| 2745-A3-055_Rev-A(SAFEEN PEARL SETUP DURING (CL-2) 6.6kV CABLE LAYDOWN AT WHT-2) | 2745-A3-055 |  | A |  |  | 2026-04-23 | SKV
| 2745-AP-0007-1 & 2_R2(DLB-750 AP during WPL-2 pipelay) | 2745-AP-0007 |  | 2 |  |  | 2026-04-27 | EJJ
| 2745-AP-0008-1 & 2_R2(DLB-750 AP during OPL-2 pipelay) | 2745-AP-0008 |  | 2 |  |  | 2026-04-27 | EJJ
| 2745-A1-036_Rev-A (DLS-4200 PASSAGE PLAN TO WHT-2 & 3 Location) | 2745-A1-036 |  | A |  |  | 2026-04-28 | SKV
| 2745-A1-0037_Rev-A(DLS-4200 AP during WHT-3 Topside Installation) | 2745-A1-0037 |  | A |  |  | 2026-05-01 | SKV
| 2745-A3-056 _Rev-A(UMM SHAIF SETUP DURING (CL-5 & 6) 132kV CABLE LAYDOWN AT GPF-2) | 2745-A3-056 |  | A |  |  | 2026-05-04 | SKV
| 2745-A3- 057_Rev-A(UMM SHAIF SETUP DURING (CL-5 & 6) 132kV CABLE LAYDOWN AT GPF-2) | 2745-A3- 057 |  | A |  |  | 2026-05-04 | SKV
| 2745-AP-0038-1 TO 5_R3(DLB-750 AP during Sleeper installation at crossing for OPL-3 PL) | 2745-AP-0038 |  | 3 |  |  | 2026-05-05 | SKV
| 2745-AP-0007-1 & 2_R3(DLB-750 AP during WPL-2 pipelay) | 2745-AP-0007 |  | 3 |  |  | 2026-05-11 | EJJ
| 2745-AP-0008-1 & 2_R3(DLB-750 AP during OPL-2 pipelay) | 2745-AP-0008 |  | 3 |  |  | 2026-05-11 | EJJ
| 2745-A3-018_Rev-B(SAFEEN PEARL SETUP DURING (CL-3) 6.6kV CABLE LAYDOWN AT WHT-3) | 2745-A3-018 |  | B |  |  | 2026-05-14 | SKV
| 2745-A3-059_Rev-A(SAFEEN PEARL SETUP DURING (CL-3) 6.6kV CABLE START-UP AT ZK-11) | 2745-A3-059 |  | A |  |  | 2026-05-14 | SKV
| 2745-AP-0000_R1(SAFEEN-3000 DP during13A & 13B Spool installation at RP-1) | 2745-AP-0000 |  | 1 |  |  | 2026-05-20 | SKV
| 2745-AP-0039-1 TO 3_R1(DLB-750 AP during Riser Guard Removal and Riser installation AT WHT-2 (EAST FACE) | 2745-AP-0039 |  | 1 |  |  | 2026-05-21 | EJJ
| 2745-AP-0040-1 TO 3_R1(DLB-750 AP during Riser Guard Removal and Riser installation AT WHT-2 (WEST FACE) | 2745-AP-0040 |  | 1 |  |  | 2026-05-21 | EJJ
| 2745-AP-0041-1 TO 3_R1(DLB-750 AP during Riser Guard Removal and Riser installation AT WHT-3) | 2745-AP-0041 |  | 1 |  |  | 2026-05-21 | EJJ
| 2745-A1-039_Rev-A(DLS-4200 AP during WHT-2 Topside Installation) | 2745-A1-039 |  | A |  |  | 2026-05-22 | SKV
| 2745-AP-0011_R1(DLB-750 AP during OPL-4 pipelay)_SEGMENT-1 | 2745-AP-0011 |  | 1 |  |  | 2026-06-05 | EJJ
| 2745-DP-0005_R2(HEA VANTAGE SET-UP @ ZCSC-CRP) | 2745-DP-0005 |  | 2 |  |  | 2026-06-08 | EJJ
| 2745-A3-066-1 TO 3_Rev-A (SEAFOX TRIDENT-1 AVIATION CLEARANCE AT ZK-288) Model | 2745-A3-066 |  | A |  |  | 2026-06-10 | SKV
| 2745-AP-0011-5 & 6_R1(DLB-750 AP during OPL-4 pipelay)_SEGMENT-2 | 2745-AP-0011 |  | 1 |  |  | 2026-06-10 | EJJ
| 2745-DP-0010_R1(SEAFOX TRIDENT-1 SET-UP @ ZK-235) | 2745-DP-0010 |  | 1 |  |  | 2026-06-11 | SKV
| 2745-DP-0011_R1(SEAFOX TRIDENT-1 SET-UP @ ZK-35) | 2745-DP-0011 |  | 1 |  |  | 2026-06-11 | SKV
| 2745-DP-0012_R1(SEAFOX TRIDENT-1 SET-UP @ ZK-11) | 2745-DP-0012 |  | 1 |  |  | 2026-06-11 | SKV
| 2745-AP-0026_R1(DLB-1000 AP during ZWSC PDP Jacket Installation) | 2745-AP-0026 |  | 1 |  |  | 2026-06-17 | EJJ
| 2745-AP-0011-1 TO 4_R1(DLB-750 AP during OPL-4 pipelay)_SEGMENT-1 | 2745-AP-0011 |  | 1 |  |  | 2026-06-17 | EJJ
| 2745-AP-0023_R1(DLB-1000 AP during ZWSC BST-1 Jacket Instllation) | 2745-AP-0023 |  | 1 |  |  | 2026-06-17 | EJJ
| 2745-AP-0038_R4(DLB-750 AP during Sleeper installation at crossing for OPL-2 PL) | 2745-AP-0038 |  | 4 |  |  | 2026-06-22 | EJJ
| 2745-AP-0042_R1(DLB-750 AP during SLEEPER INSTALLATION for OPL-2 PL.) | 2745-AP-0042 |  | 1 |  |  | 2026-06-22 | EJJ
| 2745-A1-029_Rev-A(LB-11 Setup during PDP Deck installation_Floatover)_OPTION WITH TUGS | 2745-A1-029 |  | A |  |  | 2026-06-25 | EJJ
| 2745-DP-0014_R1(SAFEEN-3000 Setup during ZWSC BST-1 Jacket Instllation) | 2745-DP-0014 |  | 1 |  |  | 2026-07-03 | SKV
| 2745-DP-0015_R1(SAFEEN-3000 Setup during ZWSC PDP Jacket Instllation) | 2745-DP-0015 |  | 1 |  |  | 2026-07-03 | SKV
| 2745-AP-0043_R1(DLB-750 Standby AP during Risers installation at ZWSC RP-1) | 2745-AP-0043 |  | 1 |  |  | 2026-07-08 | SKV
| 2745-AP-0033_R1(DLS-4200 AP during ZWSC PDP Bridge Instllation) | 2745-AP-0033 |  | 1 |  |  | 2026-07-08 | SKV
| 2745-A1-034-1 to 4_Rev-C(DLB-1000 AP during ZCSC PDP JKT Installation)-option | 2745-A1-034 |  | C |  |  | 2026-07-13 | EJJ
| 2745-AP-0039-1 TO 3_R2(DLB-750 AP during Riser Guard Removal and Riser installation AT WHT-2 (EAST FACE) | 2745-AP-0039 |  | 2 |  |  | 2026-07-21 | EJJ
| 2745-AP-0040-1 TO 3_R2(DLB-750 AP during Riser Guard Removal and Riser installation AT WHT-2 (WEST FACE) | 2745-AP-0040 |  | 2 |  |  | 2026-07-21 | EJJ
| 2745-AP-0041-1 TO 3_R2(DLB-750 AP during Riser Guard Removal and Riser installation AT WHT-3) | 2745-AP-0041 |  | 2 |  |  | 2026-07-21 | EJJ
| 2745-AP-0044_R1(DLS-4200 AP during WHT-2 Topside Installation) | 2745-AP-0044 |  | 1 |  |  | 2026-07-24 | DH
| 2745-A3-056_Rev-A(UMM SHAIF SETUP DURING (CL-5) 132kV CABLE LAYDOWN AT GPF-2)-option-3 | 2745-A3-056 |  | A |  |  | 2026-08-21 | SKV
| 2745-A3-057_Rev-A(UMM SHAIF SETUP DURING (CL-6) 132kV CABLE LAYDOWN AT GPF-2)-option-3 | 2745-A3-057 |  | A |  |  | 2026-08-21 | SKV
| 2745-A3-076_Rev-A(UMM SHAIF SETUP DURING (CL-3011) 132kV CABLE LAYDOWN AT ZWSC PDP) | 2745-A3-076 |  | A |  |  | 2026-08-21 | SKV
| 2745-A3-077_Rev-A(UMM SHAIF SETUP DURING (CL-3012) 132kV CABLE LAYDOWN AT ZWSC PDP) | 2745-A3-077 |  | A |  |  | 2026-08-21 | SKV
| 2745-A3-078_Rev-A(CABLE ROUTE CL-5 & 6 & 3011 & 3012 at ZWSC PDP & GPF-2) | 2745-A3-078 |  | A |  |  | 2026-08-21 | SKV
| 2745-A1-047_Rev-A (Under Keel Clearance during cable laying) | 2745-A1-047 |  | A |  |  | 2026-08-24 | SKV