## Installation Procedures
NMDC DOC. No.: MDR-001
UPGRADE ZULUF AM CRUDE PLATFORMS – ZULUF PACKAGE 3 ZTP-3 & ZULUF PACKAGE 4 SUBSEA CABLES & FLOWLINES
|  | NPCC PROJECT NO. 2790-2792 | [11 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2026-08-14
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ARAMCO OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Method TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| RIGID PIPELINE INSTALLATION PROCEDURE | 2790-2792-PP-OF-010 |  | A1 |  |  | T-103/25 | 2025-03-26
|  |  |  | A |  |  | T-126/25 | 2025-04-04 | 2025-04-03 | COM-2790-2792-NMDC-E-T-01378 | 2025-07-02 | ZAMUD-12741-136-137-T-1716-25 | 2 - Reviewed with comments
|  |  |  | 00 |  |  | T-333/26 | PMT | 2026-08-05 | COM-2790-2792-NMDC-E-T-05405
| Crossing Support Installation Procedure | 2790-2792-PP-OF-011
| RETROFIT RISERS, J-TUBES AND RISER GUARD INSTALLATION PROCEDURE | 2790-2792-PP-OF-012 |  | A |  |  | T-207/25 | 2025-05-22 | 2025-05-27 | COM-2790-2792-NMDC-E-T-01799 | 2025-06-30 | ZAMUD-12741-136-137-T-1682-25 | 2 - Reviewed with comments
|  |  |  | B |  |  | T-066/26 | 17-02-20262 | 2026-02-20 | COM-2790-2792-NMDC-E-T-04023 | 2026-03-16 | ZAMUD-12741-136-137-T-0531-26 | 4 - Reviewed with no comments
|  |  |  | 00 |  |  | T-125/26 | 2026-03-26 | 2026-03-26 | COM-2790-2792-NMDC-E-T-04340
| MATTRESS INSTALLATION PROCEDURE | 2790-2792-PP-OF-013 |  | A1 |  |  | T-348/24 | 2024-08-01
|  |  |  | A |  |  | T-503/24 | 2024-10-11 | 2024-10-21 | COM-2790-2792-NMDC-E-T-00636 | 12-Jan-2025 | ZAMUD-12741-136-137-T-0079-25 | 7 - See remarks
|  |  |  | B |  |  | T-039/25 | 2025-01-24 | 2025-01-27 | COM-2790-2792-NMDC-E-T-00963 | 2025-02-21 | ZAMUD-12741-136-137-T-0262-25 | 2 - Reviewed with comments
|  |  |  | 00 |  |  | T-098/25 | 2025-03-10 | 2025-03-11 | COM-2790-2792-NMDC-E-T-01253
| FLANGE MANAGEMENT PROCEDURE- SUBSEA FLANGES | 2790-2792-PP-OF-014 |  | A | CANCELLED AND APPROVED |  | T-189/25 | 2025-05-12 | 2025-05-12 | COM-2790-2792-NMDC-E-T-01680 | 2025-06-19 | ZAMUD-12741-136-137-T-1603-25 | 2 - Reviewed with comments
|  |  |  | B | CANCELLED AND APPROVED |  | T-133/26 | 2026-03-31 | 2026-04-01 | COM-2790-2792-NMDC-E-T-04416 | 2026-04-09 | ZAMUD-12741-136-137-T-0635-26 | 2 - Reviewed with comments
|  |  |  | A1 |  |  | T-170/26 | 2026-05-07
|  |  |  | C |  |  | T-238/26 | 2026-06-10 | 2026-06-09 | COM-2790-2792-NMDC-E-T-05049 | 2026-07-06 | ZAMUD-12741-136-137-T-1289-26 | 2 - Reviewed with comments
|  |  |  | D |  |  | T-283/26 | 2026-07-13 | 2026-07-13 | OM-2790-2792-NMDC-E-T-05249
| Free Span Rectification Procedure | 2790-2792-PP-OF-015
| Subsea Pipelines Flooding, Scrapping, Hydroesting and Lay up Procedure | 2790-2792-PP-OF-016
| SUBSEA SPOOLS AND SSVS(S) INSTALLATION PROCEDURE | 2790-2792-PP-OF-017 |  | A1 |  |  | T-192/25 | 2025-05-19
|  |  |  | A |  |  | T-218/25 | 2025-06-02 | 03-Jun-2025 | COM-2790-2792-NMDC-E-T-01850 | 2025-07-13 | ZAMUD-12741-136-137-T-1824-25 | 5 - For Information
|  |  |  | B |  |  | T-127/26 | 2026-03-31 | 2026-03-28 | COM-2790-2792-NMDC-E-T-04341 | 20-Apr-2026 | ZAMUD-12741-136-137-T-0683-26 | 2 - Reviewed with comments
|  |  |  | C |  |  | T-201/26 | 2026-05-13 | 12-May-2026 | COM-2790-2792-NMDC-E-T-04858 | 2026-06-30 | ZAMUD-12741-136-137-T-1228-26 | 4 - Reviewed with no comments
|  |  |  | 00 |  |  | T-301/26 | 2026-07-17 | 2026-07-01 | COM-2790-2792-NMDC-E-T-05291
| 15 KV SUBSEA CABLES INSTALLATION PROCEDURE | 2790-2792-PP-OF-018 |  | A1 |  |  | T-353/24 | 2024-08-08
|  |  |  | A |  |  | T-521/24 | 2024-10-23 | 2024-10-25 | COM-2790-2792-NMDC-E-T-00644 | 2024-12-24 | ZAMUD-12741-136-137-T-3191-24 | 5 - Reviewed with comments
|  |  |  | B |  |  | T-055/25 | 2025-02-03 | 06-Feb-25 | COM-2790-2792-NMDC-E-T-01006 | 2025-03-03 | ZAMUD-12741-136-137-T-0542-25 | 1 - Approved
|  |  |  | 00 |  |  | T-141/25 | 2025-04-14 | 2025-04-22 | COM-2790-2792-NMDC-E-T-01459
|  |  |  | 00A |  |  | T-247/25 | 2025-06-10 | 2025-06-11 | COM-2790-2792-NMDC-E-T-01904
|  |  |  | 00B |  |  | T-426/25 | 2025-08-28 | 2025-08-26 | COM-2790-2792-NMDC-E-T-02338
|  |  |  | 00C |  |  | T-529/25 | 2025-10-20 | 2025-10-30 | COM-2790-2792-NMDC-E-T-02715
| 15kV cable Transpooling Porcedure | 2790-2792-PP-OF-019
| FLEXIBLE PIPELINES INSTALLATION PROCEDURE | 2790-2792-PP-OF-022 |  | A1 |  |  | T-047/26 | 2026-02-02
|  |  |  | A |  |  | T-187/26 | 2026-05-01 | 2026-05-12 | COM-2790-2792-NMDC-E-T-04839 |  | ZAMUD-12741-136-137-T-1109-26 | 2 - Reviewed with comments
| ICCP AND ANODE SLEDS INSTALLATION PROCEDURE | 2790-2792-PP-OF-024 |  | A1 |  |  | T-479/24 | 2024-09-30
|  |  |  | A |  |  | T-066/25 | 2025-02-10 | 2025-02-10 | COM-2790-2792-NMDC-E-T-01051 | 2025-03-12 | ZAMUD-12741-136-137-T-0662-25 | 2 - Reviewed with comments
|  |  |  | B |  |  | T-210/25 | 2025-05-27 | 2025-05-28 | COM-2790-2792-NMDC-E-T-01802 | 2025-06-12 | ZAMUD-12741-136-137-T-1535-25 | 2 - Reviewed with comments
|  |  |  | 00 |  |  | T-443/25 | 2025-09-24 | 2025-09-02 | COM-2790-2792-NMDC-E-T-02370
|  |  |  | 00A |  |  | T-181/26 | 2026-04-28 | 2026-05-05 | COM-2790-2792-NMDC-E-T-04794
| Pipelines Internal FBE Field joint Coating and Repair Procedure | 2790-2792-PP-OF-025
| Pipelinex External Anti-Corrosion Field Joint Coating Procedure | 2790-2792-PP-OF-027
| Pipelines External Infill Field Joint Coating Procedure | 2790-2792-PP-OF-0xxx
| EXISTING PIPELINES AND SPOOL DEMOLITION PROCEDURE | 2790-2792-PP-OF-071 |  | A1 |  |  | T-614/25 | 2025-12-09
|  |  |  | A |  |  | T-059/26 | 2026-02-06 | 2026-02-09 | COM-2790-2792-NMDC-E-T-03861 | 2026-03-17 | ZAMUD-12741-136-137-T-0540-26 | 2 - Reviewed with comments
|  |  |  | B |  |  | T-126/26 |  | 2026-03-26 | COM-2790-2792-NMDC-E-T-04339 | 2026-06-30 | ZAMUD-12741-136-137-T-1230-26 | 2 - Reviewed with comments
|  |  |  | 00 |  |  | T-306/26 | 2026-07-17 | 2026-07-17 | COM-2790-2792-NMDC-E-T-05292
| Existing barge bumper demolition and New Riser guard installation procedure | 2790-2792-PP-OF-072
| 15kV Cable Testing Procedure | 2790-2792-PP-OF-0xxx
| ZULF 590/599 & ZULF 282/293 TOPSIDE UPGRADE PROCEDURE | 2790-2791-PP-OF-001 |  | A1 |  |  | T-433/25
|  |  |  | A |  |  | T-503/25 | 2025-10-08 | Project Number changed
|  |  |  | B |  |  | T-166/26 | 2026-04-23 | 2026-04-23 | COM-2790-2792-NMDC-E-T-04190
|  |  |  | C |  |  | T-337/26 | 2026-08-11
| ZULF 282/293 Topside Upgrade Procedure | 2790-2791-PP-OF-002
| ZULF 25/30, 180,1001 Jacket and Topside Slipover Procedure | 2790-2791-PP-OF-003
| ZULF 240/245, 347/348 Jacket and Topside Slipover Procedure | 2790-2791-PP-OF-004
| ZULF 228/233 & ZULF 240/245 JACKET AND TOPSIDE SLIPOVER PROCEDURE | 2790-2791-PP-OF-005 |  | A1 |  |  | T-150/26 | 2026-04-13
|  |  |  | A |  |  | T-228/26 | 2026-05-25 | 2026-05-25 | 2790-2791-NMDC-E-T-06405
| ZULF 140/145, 951/952 Jacket and Topside Slipover Procedure | 2790-2791-PP-OF-006
| ZULF 216/221, 346/349 Jacket and Topside Slipover Procedure | 2790-2791-PP-OF-007
| ZULF 122/127 Jacket and Topside Slipover Procedure | 2790-2791-PP-OF-008
| ZULF 146/151, 961/962 Jacket and Topside Slipover Procedure | 2790-2791-PP-OF-009
| ZULF 110/121 Existing Topside Demolition and New Topside Installation | 2790-2791-PP-OF-010
| ZULF 152/163 Existing Topside Demolition and New Topside Installation | 2790-2791-PP-OF-011
| ZULF 110/121 AUX Jacket and Topside bridge Installation Procedures | 2790-2791-PP-OF-012
| ZULF 152/163 AUX Jacket and Topside bridge Installation Procedures | 2790-2791-PP-OF-013
| ZULF TPS-3 New Scrapper Deck Installation Procedure | 2790-2791-PP-OF-014

## Setup Plans & Anchor Patterns
NMDC DOC. No.: MDR-001
UPGRADE ZULUF AM CRUDE PLATFORMS – ZULUF PACKAGE 3 ZTP-3 & ZULUF PACKAGE 4 SUBSEA CABLES & FLOWLINES
|  | NPCC PROJECT NO. 2790-2792 | [11 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-08-14
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ARAMCO OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| VESSEL PASSAGE PLAN FROM ANCHORAGE TO ZULF GOSP-3 & GOSP-4 PLATFORMS | 2790-A0-001 |  | 1 |  | 2024-02-07 | T-048/24 | 2024-02-07 | 2024-02-07
|  |  |  | 2 |  |  | T-100/24 | 2024-03-01 | 2024-03-01
| SCOPE OF WORK FOR CAMPAIGN-1 | 2790-2792-A0-005 |  | 0 |  |  | T-455/24 | 2024-09-23 | 2024-09-23
| UMM SHAIF PASSAGE PLAN FROM ANCHORAGE TO ZULF TPS-4 | 2790-2792-A0-006 |  | 0 |  |  | T-455/24 | 2024-09-23 | 2024-09-23
| PASSAGE PLAN FROM RAS TANURA TO TANAJIB J POWER LOCATION | 2790-2792-A0-007 |  | 0 |  |  | T-455/24 | 2024-09-23 | 2024-09-23
| UMM SHAIF PASSAGE PLAN FROM ANCHORAGE TO ZULF TPS-2 | 2790-2792-A0-008 |  | 0 |  |  | T-455/24 | 2024-09-23 | 2024-09-23
| DISCOVERY SETUP PLAN DURING PRE-ENGINEERING GEO-PHYSICAL SURVEY AT ZULF FILED | 2790-2792-DP-001 |  | B |  | 2024-02-07 | T-048/24 | 2024-02-07 | 2024-02-07
| CCC MARITIME-2 SETUP PLAN DURING PRE-ENGINEERING SURVEY AT ZULF FIELD PLATFORM LOCATIONS | 2790-2792-DP-002 |  | A |  | 2024-03-01 | T-100/24 | 2024-03-01 | 2024-03-01
|  |  |  | B |  |  | T-119/24 | 2024-03-13 | 2024-03-13

## Sketches
NMDC DOC. No.: MDR-001
UPGRADE ZULUF AM CRUDE PLATFORMS – ZULUF PACKAGE 3 ZTP-3 & ZULUF PACKAGE 4 SUBSEA CABLES & FLOWLINES
|  | NPCC PROJECT NO. 2790-2792 | [11 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-08-14
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | [12 empty] | REMARKS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | REF | DATE | CODE
| SCOPE OF WORK FOR CAMPAIGN-1 | 2790-2792-A0-005 |  | 0 |  |  | 2024-09-13
| UMM SHAIF PASSAGE PLAN FROM ANCHORAGE TO ZULF TPS-4 | 2790-2792-A0-006 |  | 0 |  |  | 2024-09-13
| PASSAGE PLAN FROM RAS TANURA TO TANAJIB J POWER LOCATION | 2790-2792-A0-007 |  | 0 |  |  | 2024-09-20
| (UMM SHAIF SET-UP during cable laying from ZTPS-4 TO ZULF 510-519)_START-UP & LAY-DOWN | 2790-2792-A3-004 |  | 0 |  |  | 2024-10-11
| (UMM SHAIF SET-UP during cable laying from ZTPS-4 TO ZULF 480-489)_START-UP & LAY-DOWN | 2790-2792-A3-005 |  | 0 |  |  | 2024-10-11
| (DELMA-2000 SET-UP during Startup of 8”rigid pipeline ZTPS-7 to ZTP-4) | 2790-2792-A3-013 |  | 0 |  |  | 2024-12-06
| (NAUTICA-2 set-up during preparatory works @ ZTPS-4) | 2790-2792-DP-0008 |  | A |  |  | 2024-12-20
| (NAUTICA-2 set-up during preparatory works @ ZTPS-2) | 2790-2792-DP-0009 |  | A |  |  | 2024-12-20
| (NAUTICA-2 set-up during preparatory works @ ZTPS-4) | 2790-2792-DP-0008 |  | A |  |  | 2024-12-23
| (NAUTICA-2 set-up during preparatory works @ ZTPS-2) | 2790-2792-DP-0009 |  | A |  |  | 2024-12-23
| (NAUTICA-2 set-up during preparatory works @ ZULF 510-519) | 2790-2792-DP-0010 |  | A |  |  | 2024-12-23
| (NAUTICA-2 set-up during preparatory works @ ZTPS-4) | 2790-2792-DP-0008 |  | B |  |  | 2025-02-03
| (NAUTICA-2 set-up during preparatory works @ ZTPS-4) | 2790-2792-DP-0008 |  | A |  |  | 2025-02-10 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZTPS-2) | 2790-2792-DP-0009 |  | A |  |  | 2025-02-10 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZULF 510-519) | 2790-2792-DP-0010 |  | A |  |  | 2025-02-10 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZULF 480-489) | 2790-2792-DP-0011 |  | A |  |  | 2025-02-10 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZULF 500-509) | 2790-2792-DP-0012 |  | A |  |  | 2025-02-10 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZULF 680-689) | 2790-2792-DP-0013 |  | A |  |  | 2025-02-10 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZTPS-7) | 2790-2792-DP-0014 |  | A |  |  | 2025-02-10 | EJJ
| (UMM SHAIF passage plan from ZULF anchorage to ZTPS-4) | 2790-2792-A0-006 |  | 1 |  |  | 2025-02-10 | SKV
| (Ras Tanura to Tanajib J Power Location) | 2790-2792-A0-007 |  | 1 |  |  | 2025-02-10 | SKV
| (UMM SHAIF passage plan from ZULF anchorage to ZULF 510-519) | 2790-2792-A0-012 |  | 0 |  |  | 2025-02-10 | SKV
| (UMM SHAIF passage plan from ZULF anchorage to ZULF 480-489) | 2790-2792-A0-013 |  | 0 |  |  | 2025-02-10 | SKV
34 | LOWER ZAKUM - CLV SETUP PLANS DURING LAYING OF HU-CL4 FROM ZK 329 TO ZK-307 | 2800-DP-0304 | AD-314-PL-625015-SHT-001 |  |  |  | 2025-04-01
35 | LOWER ZAKUM - CLV SETUP PLANS DURING LAYING OF HU-CL5 FROM ZK-307 TO ZK-88 | 2800-DP-0305 | AD-299-PL-625008-SHT-001 |  |  |  | 2025-04-01
36 | 2790-2792-DP-0021-1 TO 3_Rev-A(UMM SHAIF SET-UP DURING CABLE LAYING FROM ZULF 510-519 TO ZTPS-4) | 2790-2792-DP-0021 |  |  |  |  | 2025-02-11 | SKV
| 2790-2792-DP-0022-1 TO 2_Rev-A(UMM SHAIF SET-UP DURING CABLE LAYING FROM ZULF 480-489 TO ZTPS-4) | 2790-2792-DP-0022 |  |  |  |  | 2025-02-11 | SKV
| 2790-2792-A0-014_R0(NAUTICA-2 passage plan from ZULF anchorage to ZTPS-4) | 2790-2792-A0-014 |  | 0 |  |  | 2025-02-12 | EJJ
| 2790-2792-A0-015_R0(NAUTICA-2 passage plan from ZULF anchorage to ZTPS-2) | 2790-2792-A0-015 |  | 0 |  |  | 2025-02-12 | EJJ
| 2790-2792-A0-016_R0(NAUTICA-2 passage plan from ZULF anchorage to ZULF 510-519) | 2790-2792-A0-016 |  | 0 |  |  | 2025-02-12 | EJJ
| 2790-2792-A0-017_R0(NAUTICA-2 passage plan from ZULF anchorage to ZULF 480-489) | 2790-2792-A0-017 |  | 0 |  |  | 2025-02-12 | EJJ
| 2790-2792-A0-018_R0(NAUTICA-2 passage plan from ZULF anchorage to ZULF 500-509) | 2790-2792-A0-018 |  | 0 |  |  | 2025-02-12 | EJJ
| 2790-2792-A0-019_R0(NAUTICA-2 passage plan from ZULF anchorage to ZULF 680-689) | 2790-2792-A0-019 |  | 0 |  |  | 2025-02-12 | EJJ
| 2790-2792-A0-020_R0(NAUTICA-2 passage plan from ZULF anchorage to ZTPS-7) | 2790-2792-A0-020 |  | 0 |  |  | 2025-02-12 | EJJ
| (UMM SHAIF SET-UP DURING CABLE LAYING FROM ZULF 510-519 TO ZTPS-4) | 2790-2792-DP-0021 |  | A |  |  | 2025-02-12 | DH
| (UMM SHAIF SET-UP DURING CABLE LAYING FROM ZULF 480-489 TO ZTPS-4) | 2790-2792-DP-0022 |  | A |  |  | 2025-02-12 | DH
| (NAUTICA-2 set-up during preparatory works @ ZTPS-4) | 2790-2792-DP-000 |  | A |  |  | 2025-02-13 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZTPS-2) | 2790-2792-DP-0009 |  | A |  |  | 2025-02-13 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZULF 510-519) | 2790-2792-DP-0010 |  | A |  |  | 2025-02-13 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZULF 480-489) | 2790-2792-DP-0011 |  | A |  |  | 2025-02-13 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZULF 500-509) | 2790-2792-DP-0012 |  | A |  |  | 2025-02-13 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZULF 680-689) | 2790-2792-DP-0013 |  | A |  |  | 2025-02-13 | EJJ
| (NAUTICA-2 set-up during preparatory works @ ZULF TP-7) | 2790-2792-DP-0014 |  | A |  |  | 2025-02-13 | EJJ
| (SHUJAA-2000 & DELMA-2000 & AL SAFILIYA(JUB) at ZULF GOSP-4 TP) | 2790-2792-A3-041 |  | A |  |  | 2025-05-01 | SKV
| (15kV Cable Laydown at ZPTS-1 EAST) | 2790-2792-A3-042 |  | A |  |  | 2025-05-20 | SKV
| (15kV Cable Laydown at ZPTS-1 WEST) | 2790-2792-A3-043 |  | A |  |  | 2025-05-20 | SKV
| (15kV Cable Laydown at ZPTS-3) | 2790-2792-A3-044 |  | A
| (15kV Cable Laydown at ZPTS-2) | 2790-2792-A3-045 |  | A |  |  | 2025-05-20 | SKV
| (UMM SHAIF SET-UP DURING CROSSING MATTRESS INSTALATION AT 15KV ZULF 680-689) | 2790-2792-DP-0028 |  | B |  |  | 2025-06-02 | SKV
| (UMM SHAIF SET-UP DURING 15KV CABLE LAYING ZULF TPS-2 TO ZULF 680-689) | 2790-2792-DP-0029 |  | B |  |  | 2025-06-02 | SKV
| 2790-2792-DP-0027-1 TO 2_Rev-B(DELMA-2000 Setup during 8Inch PL Laying from ZULF TP-7 to GOSP 4 TP) | 2790-2792-DP-0027 |  | B |  |  | 2025-06-02 | EJJ
| 2790-2792-DP-0036-1 TO 2_Rev-A(CCC MAITIME-2 SET-UP DURING ICCP INSTALATION AT ZULF 680-689) | 2790-2792-DP-0036 |  | A |  |  | 2025-08-07 | SKV
| 2790-2792-DP-0037-1 TO 3_Rev-A(UMM SHAIF SET-UP DURING CROSSING MATTRESS INSTALLATION FOR CABLE ZTPS-4 TO ZTPS-7) | 2790-2792-DP-0037 |  | A |  |  | 2025-08-08 | SKV
| 2790-2792-DP-0038-1 TO 3_Rev-A(UMM SHAIF SET-UP DURING 15kV CABLE LAYING ZTPS-4 TO ZTPS-7) | 2790-2792-DP-0038 |  | A |  |  | 2025-08-08 | SKV
| 2790-2792-A0-006_R2(UMM SHAIF passage plan from ZULF anchorage to ZTPS-4) | 2790-2792-A0-006 |  | 2 |  |  | 2025-08-11 | SKV
| 2790-2792-DP-0037-1 TO 3_Rev-A(UMM SHAIF SET-UP DURING CROSSING MATTRESS INSTALLATION FOR CABLE ZTPS-4 TO ZTPS-7) | 2790-2792-DP-0037 |  | A |  |  | 2025-08-11 | SKV
| 2790-2792-DP-0038-1 TO 3_Rev-A(UMM SHAIF SET-UP DURING 15kV CABLE LAYING ZTPS-4 TO ZTPS-7) | 2790-2792-DP-0038 |  | A |  |  | 2025-08-11 | SKV
| 2790-2792-A0-025_R0(CCC MARITIME-2 passage plan from anchorage to ZULF 680-689) | 2790-2792-A0-025 |  | 0 |  |  | 2025-08-11 | SKV
| 2790-2792-DP-0036-1 TO 2_Rev-A(CCC MAITIME-2 SET-UP DURING ICCP INSTALATION AT ZULF 680-689) | 2790-2792-DP-0036 |  | A |  |  | 2025-08-11 | SKV
| (Proposed cable routes at ZTPS-1) | 2790-2792-A3-047 |  | A |  |  | 2025-08-12 | SKV
| (Proposed cable routes at ZTPS-3) | 2790-2792-A3-048 |  | A |  |  | 2025-08-12 | SKV
| (Proposed route for cable wet storage at Laydown location) | 2790-2792-A3-050 |  | A |  |  | 2025-08-18 | SKV
| (CCC-MARITIME-2 passage plan from ZULF anchorage to ZULF TP-7)-SUR-1819 | 2790-2792-A0-027 |  | 0 |  |  | 2025-08-18 | SKV
| (CCC-MARITIME-2 passage plan from ZULF NORTH anchorage to ZULF TP-7)-SUR-9192 | 2790-2792-A0-028 |  | 0 |  |  | 2025-08-18 | SKV
| (CCC MAITIME-2 SET-UP DURING ICCP INSTALATION AT ZULF TP-7) | 2790-2792-DP-0040 |  | A |  |  | 2025-08-18 | SKV
| (UMM SHAIF passage plan from ZULF anchorage to ZTPS-4) | 2790-2792-A0-006 |  | 2 |  |  | 2025-08-21 | SKV
| (UMM SHAIF SET-UP DURING CROSSING MATTRESS INSTALLATION FOR CABLE ZTPS-4 TO ZTP-7) | 2790-2792-DP-0037 |  | A |  |  | 2025-08-21 | SKV
| (UMM SHAIF SET-UP DURING 15kV CABLE LAYING ZTPS-4 TO ZTP-7) | 2790-2792-DP-0038 |  | A |  |  | 2025-08-21 | SKV
| 2790-2792-DP-0026-1 TO 3_Rev-C(UMM SHAIF SET-UP DURING ICCP INSTALATION AT ZULF TP-7) | 2790-2792-DP-0026 |  | C |  |  | 2025-08-21 | SKV
| 2790-2792-DP-0026-1 TO 3_Rev-D(UMM SHAIF SET-UP DURING ICCP INSTALATION AT ZULF TP-7) | 2790-2792-DP-0026 |  | D |  |  | 2025-08-26 | SKV
| 2790-2792-DP-0036-1 TO 2_Rev-B(CCC MAITIME-2 SET-UP DURING ICCP INSTALATION AT ZULF 680-689) | 2790-2792-DP-0036 |  | B |  |  | 2025-08-26 | SKV
| 2790-2792-DP-0037-1 TO 3_Rev-B(UMM SHAIF SET-UP DURING CROSSING MATTRESS INSTALLATION FOR CABLE ZTPS-4 TO ZTP-7) | 2790-2792-DP-0037 |  | B |  |  | 2025-08-26 | SKV
| 2790-2792-DP-0038-1 TO 3_Rev-B(UMM SHAIF SET-UP DURING 15kV CABLE LAYING ZTPS-4 TO ZTP-7) | 2790-2792-DP-0038 |  | B |  |  | 2025-08-26 | SKV
| 2790-2792-DP-0041_Rev-A(SHUJAA-2000 SET-UP DURING RISER INSTALLATION AT ZULF TP-7) | 2790-2792-DP-0041 |  | A |  |  | 2025-08-29 | SKV
| 2790-2792-DP-0043_Rev-A(SHUJAA-2000 SET-UP DURING RISER INSTALLATION AT ZULF TP-4) | 2790-2792-DP-0043 |  | A |  |  | 2025-08-29 | SKV
| 2790-2792-DP-0039-1 TO 2_Rev-B(CCC MAITIME-2 SET-UP DURING ICCP INSTALATION AT ZULF 500-509) | 2790-2792-DP-0039 |  | B |  |  | 2025-09-01 | EJJ
| 2790-2792-A0-030_R0(SHUJAA-2000 passage plan from ZULF anchorage to ZULF TP-7)-SUR-1819 | 2790-2792-A0-030 |  | 0 |  |  | 2025-09-01 | SKV
| 2790-2792-DP-0041_Rev-A(SHUJAA-2000 SET-UP DURING RISER INSTALLATION AT ZULF TP-7) | 2790-2792-DP-0041 |  | A |  |  | 2025-09-01 | SKV
| 2790-2792-DP-0043_Rev-A(SHUJAA-2000 SET-UP DURING RISER INSTALLATION AT ZULF TP-4) | 2790-2792-DP-0043 |  | A |  |  | 2025-09-01 | SKV
| 2790-2792-DP-0043_Rev-C(SHUJAA-2000 SET-UP DURING RISER INSTALLATION AT ZULF TP-4) Model | 2790-2792-DP-0043 |  | C |  |  | 2025-09-03 | SKV
| 2790-2792-A0-027_R1(CCC-MARITIME-2 passage plan from ZULF anchorage to ZULF TP-7)-SUR-1819 | 2790-2792-A0-027 |  | 1 |  |  | 2025-09-24 | SKV
| 2790-2792-A0-028_R0(CCC-MARITIME-2 passage plan from ZULF NORTH anchorage to ZULF TP-7)-SUR-9192 | 2790-2792-A0-028 |  | 0 |  |  | 2025-09-24 | SKV
| 2790-2792-A0-033_R0(CCC MARITIME-2 Passage plan from ANCHORAGE to ZULF GOSP-4) | 2790-2792-A0-033 |  | 0 |  |  | 2025-09-24 | SKV
| 2790-2792-DP-0046-1 TO 2_Rev-A(CCC MARITIME-2 SET-UP DURING 8Inch PL Pre-commissioning and Hydrotesting from ZTPS-7 to ZULF GOSP-4) | 2790-2792-DP-0046 |  | A |  |  | 2025-09-24 | SKV
| (CCC WADAD ALETHEIA SET-UP DURING RISER INSTALLATION AT ZULF TP-4) | 2790-2792-DP-0048 |  | A |  |  | 2025-10-15 | SKV
| (CCC WADAD ALETHEIA SET-UP DURING RISER INSTALLATION AT ZULF TP-7) | 2790-2792-DP-0049 |  | A |  |  | 2025-10-15 | SKV
| 2790-2792-DP-0050-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-4) | 2790-2792-DP-0050 |  | A |  |  | 2025-10-27 | SKV
| 2790-2792-DP-0051-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-7) | 2790-2792-DP-0051 |  | A |  |  | 2025-10-28 | SKV
| 2790-2792-DP-0052-1 TO 2_Rev-A(SWORDFISH Straightening of 15KV cables AT ZULF 500-509) | 2790-2792-DP-0052 |  | A |  |  | 2025-10-28 | SKV
| 2790-2792-A0-037_R1(CCC WADAD ALETHEIA passage plan from ANCHORAGE to ZULF TP-7) | 2790-2792-A0-037 |  | 1 |  |  | 2025-11-03 | SKV
| 2790-2792-A0-038_R1(CCC WADAD ALETHEIA passage plan from ANCHORAGE to ZULF GOSP-4) | 2790-2792-A0-038 |  | 1 |  |  | 2025-11-03 | SKV
| 2790-2792-DP-0048_Rev-A (CCC WADAD ALETHEIA SET-UP DURING RISER INSTALLATION AT ZULF TP-4) | 2790-2792-DP-0048 |  | A |  |  | 2025-11-03 | SKV
| 2790-2792-DP-0049_Rev-A (CCC WADAD ALETHEIA SET-UP DURING RISER INSTALLATION AT ZULF TP-7) | 2790-2792-DP-0049 |  | A |  |  | 2025-11-03 | SKV
| 2790-2792-DP-0050-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-4) | 2790-2792-DP-0050 |  | A |  |  | 2025-11-03 | SKV
| 2790-2792-DP-0051-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-7) | 2790-2792-DP-0051 |  | A |  |  | 2025-11-03 | SKV
| (SWORDFISH Straightening of 15KV cables AT ZULF 500-509) | 2790-2792-DP-0052 |  | B |  |  | 2025-11-03 | SKV
| 2790-2792-DP-0053-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-4)-OPTION | 2790-2792-DP-0053 |  | A |  |  | 2025-11-04 | SKV
| 2790-2792-DP-0054-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-7)-OPTION | 2790-2792-DP-0054 |  | A |  |  | 2025-11-05 | SKV
| 2790-2792-A0-040_R0(CCC WADAD ALETHEIA Passage plan from ANCHORAGE to ZULF 282-293) | 2790-2792-A0-040 |  | 0 |  |  | 2025-11-10 | SKV
| 2790-2792-A0-041_R0(CCC WADAD ALETHEIA Passage plan from ANCHORAGE to ZULF 294-301) | 2790-2792-A0-041 |  | 0 |  |  | 2025-11-10 | SKV
| 2790-2792-A0-042_R0(CCC WADAD ALETHEIA Passage plan from ANCHORAGE to ZULF TP-5) | 2790-2792-A0-042 |  | 0 |  |  | 2025-11-10 | SKV
| 2790-2792-A0-043_R0(CCC WADAD ALETHEIA Passage plan from ANCHORAGE to ZULF 330-339) | 2790-2792-A0-043 |  | 0 |  |  | 2025-11-10 | SKV
| 2790-2792-DP-0055-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP J-TUBE INSTALLATION AT ZULF 282-293 AND 330-339 AND 294-301 AND TP-5) | 2790-2792-DP-0055 |  | A |  |  | 2025-11-10 | SKV
| 2790-2792-DP-0053-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-4)-OPTION | 2790-2792-DP-0053 |  | A |  |  | 2025-11-11 | SKV
| 2790-2792-DP-0054-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-7)-OPTION | 2790-2792-DP-0054 |  | A |  |  | 2025-11-11 | SKV
| 2790-2792-DP-0053-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-4)-OPTION | 2790-2792-DP-0053 |  | A |  |  | 2025-11-11 | SKV
| 2790-2792-DP-0054-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-7)-OPTION | 2790-2792-DP-0054 |  | A |  |  | 2025-11-11 | SKV
| 2790-2792-A0-040_R0(CCC WADAD ALETHEIA Passage plan from ANCHORAGE to ZULF 282-293) | 2790-2792-A0-040 |  | 0 |  |  | 2025-11-11 | SKV
| 2790-2792-A0-041_R0(CCC WADAD ALETHEIA Passage plan from ANCHORAGE to ZULF 294-301) | 2790-2792-A0-041 |  | 0 |  |  | 2025-11-11 | SKV
| 2790-2792-A0-042_R0(CCC WADAD ALETHEIA Passage plan from ANCHORAGE to ZULF TP-5) | 2790-2792-A0-042 |  | 0 |  |  | 2025-11-11 | SKV
| 2790-2792-A0-043_R0(CCC WADAD ALETHEIA Passage plan from ANCHORAGE to ZULF 330-339) | 2790-2792-A0-043 |  | 0 |  |  | 2025-11-11 | SKV
| 2790-2792-DP-0055-1 TO 3_Rev-A (CCC WADAD ALETHEIA SET-UP J-TUBE INSTALLATION AT ZULF 282-293 AND 330-339 AND 294-301 AND TP-5) | 2790-2792-DP-0055 |  | A |  |  | 2025-11-11 | SKV
| 2790-2792-A0-044_R0(RAWABI-608 Passage plan from ANCHORAGE to ZULF 590-599) | 2790-2792-A0-044 |  | 0 |  |  | 2025-11-13 | SKV
| 2790-2792-A0-045_R0(RAWABI-608 Passage plan from ANCHORAGE to ZULF 282-293) | 2790-2792-A0-045 |  | 0 |  |  | 2025-11-13 | SKV
| 2790-2792-DP-0056-1 TO 3_Rev-A(RAWABI-608 SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 282-293) | 2790-2792-DP-0056 |  | A |  |  | 2025-11-13 | SKV
| 2790-2792-DP-0057-1 TO 3_Rev-A(RAWABI-608 SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 590-599) | 2790-2792-DP-0057 |  | A |  |  | 2025-11-13 | SKV
| 2790-2792-A0-046_R0(ChuangLi Passage plan from ANCHORAGE to ZULF 282-293) | 2790-2792-A0-046 |  | 0 |  |  | 2025-11-20 | SKV
| 2790-2792-A0-047_R0(ChuangLi Passage plan from ANCHORAGE to ZULF 590-599) | 2790-2792-A0-047 |  | 0 |  |  | 2025-11-20 | SKV
| 2790-2792-DP-0058_Rev-A(CHUANG LI SET-UP PLAN DURING Demolition and Installation of upgrade platform at ZULF 282-293) | 2790-2792-DP-0058 |  | A |  |  | 2025-11-20 | SKV
| 2790-2792-DP-0059_Rev-A(CHUANG LI SET-UP PLAN DURING Demolition and Installation of upgrade platform at ZULF 590-599) | 2790-2792-DP-0059 |  | A |  |  | 2025-11-20 | SKV
| 2790-2792-A0-046_R0(ChuangLi Passage plan from ANCHORAGE to ZULF 282-293) | 2790-2792-A0-046 |  | 0 |  |  | 2025-11-20 | SKV
| 2790-2792-A0-047_R0(ChuangLi Passage plan from ANCHORAGE to ZULF 590-599) | 2790-2792-A0-047 |  | 0 |  |  | 2025-11-20 | SKV
| 2790-2792-DP-0058_Rev-A(CHUANG LI SET-UP PLAN DURING Demolition and Installation of upgrade platform at ZULF 282-293) | 2790-2792-DP-0058 |  | A |  |  | 2025-11-20 | SKV
| 2790-2792-DP-0059_Rev-A(CHUANG LI SET-UP PLAN DURING Demolition and Installation of upgrade platform at ZULF 590-599) | 2790-2792-DP-0059 |  | A |  |  | 2025-11-20 | SKV
| 2790-2792-DP-0058_Rev-B(CHUANG LI SET-UP PLAN DURING Demolition and Installation of upgrade platform at ZULF 282-293) | 2790-2792-DP-0058 |  | B |  |  | 2025-11-24 | SKV
| 2790-2792-DP-0059_Rev-B(CHUANG LI SET-UP PLAN DURING Demolition and Installation of upgrade platform at ZULF 590-599) | 2790-2792-DP-0059 |  | B |  |  | 2025-11-24 | SKV
| 2790-2792-DP-0056-1 TO 3_Rev-B(RAWABI-608 SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 282-293) | 2790-2792-DP-0056 |  | B |  |  | 2025-11-24 | SKV
| 2790-2792-DP-0057-1 TO 3_Rev-B(RAWABI-608 SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 590-599) | 2790-2792-DP-0057 |  | B |  |  | 2025-11-24 | SKV
| 2790-2792-A0-048_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF 294-301) | 2790-2792-A0-048 |  | 0 |  |  | 2025-12-05 | SKV
| 2790-2792-A0-049_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 294-301) | 2790-2792-A0-049 |  | 0 |  |  | 2025-12-05 | SKV
| 2790-2792-A0-050_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF TP-5) | 2790-2792-A0-050 |  | 0 |  |  | 2025-12-05 | SKV
| 2790-2792-A0-051_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF 330-339) | 2790-2792-A0-051 |  | 0 |  |  | 2025-12-05 | SKV
| 2790-2792-A0-052_R0(SWORDFISH Passage plan from ANCHORAGE to ZULF 282-293) | 2790-2792-A0-052 |  | 0 |  |  | 2025-12-05 | SKV
| 2790-2792-DP-0062_Rev-A (SWORDFISH SET-UP J-TUBE INSTALLATION AT ZULF 294-301) | 2790-2792-DP-0062 |  | A |  |  | 2025-12-05 | SKV
| 2790-2792-DP-0063_Rev-A (SWORDFISH SET-UP J-TUBE INSTALLATION AT ZULF TP-5) | 2790-2792-DP-0063 |  | A |  |  | 2025-12-05 | SKV
| 2790-2792-DP-0064_Rev-A (SWORDFISH SET-UP J-TUBE INSTALLATION AT ZULF 330-339) | 2790-2792-DP-0064 |  | A |  |  | 2025-12-05 | SKV
| 2790-2792-DP-0065_Rev-A (SWORDFISH SET-UP J-TUBE INSTALLATION AT ZULF 282-293) | 2790-2792-DP-0065 |  | A |  |  | 2025-12-05 | SKV
| 2790-2792-DP-0066_Rev-A (SHUJAA-2000 SET-UP J-TUBE INSTALLATION AT ZULF 294-301) | 2790-2792-DP-0066 |  | A |  |  | 2025-12-05 | SKV
| 2790-2792-A0-027_R2(CCC-MARITIME-2 passage plan from ZULF anchorage to ZULF TP-7) | 2790-2792-A0-027 |  | 2 |  |  | 2025-12-24 | SKV
| 2790-2792-A0-033_R0(CCC MARITIME-2 Passage plan from ANCHORAGE to ZULF GOSP-4) | 2790-2792-A0-033 |  | 0 |  |  | 2025-12-24 | SKV
| 2790-2792-A0-037_R1(CCC WADAD ALETHEIA passage plan from Anchorage to ZULF TP-7) | 2790-2792-A0-037 |  | 1 |  |  | 2025-12-24 | SKV
| 2790-2792-A0-038_R2(CCC WADAD ALETHEIA passage plan from ANCHORAGE to ZULF GOSP-4) | 2790-2792-A0-038 |  | 2 |  |  | 2025-12-24 | SKV
| 2790-2792-DP-0048_Rev-B (CCC WADAD ALETHEIA SET-UP DURING RISER INSTALLATION AT ZULF TP-4) | 2790-2792-DP-0048 |  | B |  |  | 2025-12-25 | SKV
| 2790-2792-DP-0049_Rev-B (CCC WADAD ALETHEIA SET-UP DURING RISER INSTALLATION AT ZULF TP-7) | 2790-2792-DP-0049 |  | B |  |  | 2025-12-25 | SKV
| 2790-2792-DP-0053-1 TO 3_Rev-B (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-4) | 2790-2792-DP-0053 |  | B |  |  | 2025-12-25 | SKV
| 2790-2792-DP-0054-1 TO 3_Rev-B (CCC WADAD ALETHEIA SET-UP DURING CORRIDOR SPOOL INSTALLATION AT ZULF TP-7) | 2790-2792-DP-0054 |  | B |  |  | 2025-12-25 | SKV
| 2790-2792-DP-0080-1 TO 2_Rev-B(HEA AL SILA SET-UP PLAN DURING HOOK-UP WORKS AT ZULF 590-599) | 2790-2792-DP-0080 |  | B |  |  | 2026-02-09 | SKV
| 2790-2792-DP-0081-1 TO 2_Rev-B(HEA AL SILA SET-UP PLAN DURING PREPARATORY WORKS AT ZULF 590-599) | 2790-2792-DP-0081 |  | B |  |  | 2026-02-09 | SKV
| 2790-2792-A0-046_R1(ChuangLi Passage plan from ANCHORAGE to ZULF 282-293) | 2790-2792-A0-046 |  | 1 |  |  | 2026-02-20 | SKV
| 2790-2792-A0-047_R1(ChuangLi Passage plan from ANCHORAGE to ZULF 590-599) | 2790-2792-A0-047 |  | 1 |  |  | 2026-02-20 | SKV
| 2790-2792-DP-0027-1 TO 3_Rev-E(DELMA-2000 Setup during 8Inch PL Laying from ZULF TP-7 to GOSP 4 TP) | 2790-2792-DP-0027 |  | E |  |  | 2026-03-13 | SKV
| MAG CAPELLA SET UP AT ZTP-3 | 2790-2792-A3-064 |  | A |  |  | 2026-04-01 | SIVA
| MAG CAPELLA SET UP AT Z-590 option-1 & 2 | 2790-2792-A3-065 |  | A |  |  | 2026-04-01 | SIVA
| MAG CAPELLA SET UP AT Z-282 option-1 & 2 | 2790-2792-A3-066 |  | A |  |  | 2026-04-01 | SIVA
| MAG CAPELLA SET UP AT ZULF TPS-4 option-1 & 2 | 2790-2792-A3-067 |  | A |  |  | 2026-04-01 | SIVA
| MAG CAPELLA SET UP AT ZULF TPS-2 ooption-1 & 2 | 2790-2792-A3-068 |  | A |  |  | 2026-04-01 | SIVA
| MAG CAPELLA SET UP AT ZULF 510/519 option-1 & 2 | 2790-2792-A3-069 |  | A |  |  | 2026-04-01 | SIVA
| MAG CAPELLA SET UP AT ZULF 480/489 option-1 & 2 | 2790-2792-A3-070 |  | A |  |  | 2026-04-01 | SIVA
| MAG CAPELLA SET UP AT ZULF 680/689 option-1 & 2 | 2790-2792-A3-071 |  | A |  |  | 2026-04-01 | SIVA
| MAG CAPELLA SET UP AT ZULF 500-509 option-1 & 2 | 2790-2792-A3-073 |  | A |  |  | 2026-04-01 | SIVA
| 2790-2792-A0-069_R2(CHUANG LI Passage plan from ANCHORAGE to ZULF 228-233) | 2790-2792-A0-069 |  | 2 |  |  | 2026-04-27 | SKV
| 2790-2792-DP-0092-1 TO 2_Rev-B(CHUANG LI SET-UP PLAN DURING Demolition and Installation of upgrade platform at ZULF 228-233) | 2790-2792-DP-0092 |  | B |  |  | 2026-04-27 | SKV
| 2790-2792-DP-0110-1 to 4_Rev-A(UMM SHAIF SET-UP DURING CROSSING MATTRESS INSTALLATION FOR CABLE ZTPS-1 TO ZULF 330-339) | 2790-2792-DP-0110 |  | A |  |  | 2026-05-11 | DH
| 2790-2792-DP-0111-1 to 4_Rev-A (UMM SHAIF SET-UP DURING 15KV CABLE LAYING ZULF TPS-1 TO ZULF 330-339) | 2790-2792-DP-0111 |  | A |  |  | 2026-05-11 | DH
| 2790-2792-DP-0112-1 to 2_Rev-A(UMM SHAIF SET-UP DURING ICCP CABLE INSTALLATION AT ZULF 330-339) | 2790-2792-DP-0112 |  | A |  |  | 2026-05-11 | DH
| 2790-2792-A0-085_R0(SHUJAA-2000 Passage plan from ANCHORAGE to ZULF 204-209) | 2790-2792-A0-085 |  | 0 |  |  | 2026-05-13 | SKV
| 2790-2792-DP-0113_Rev-A(SHUJAA-2000 SET-UP DURING SPOOL INSTALLATION AT ZULF 204-209) | 2790-2792-DP-0113 |  | A |  |  | 2026-05-13 | SKV
| 2790-2792-DP-0110-1 to 4_Rev-A(UMM SHAIF SET-UP DURING CROSSING MATTRESS INSTALLATION FOR CABLE ZTPS-1 TO ZULF 330-339) | 2790-2792-DP-0110 |  | A |  |  | 2026-05-13 | DH
| 2790-2792-DP-0111-1 to 4_Rev-A (UMM SHAIF SET-UP DURING 15KV CABLE LAYING ZULF TPS-1 TO ZULF 330-339) | 2790-2792-DP-0111 |  | A |  |  | 2026-05-13 | DH
| 2790-2792-DP-0112-1 to 2_Rev-A(UMM SHAIF SET-UP DURING ICCP CABLE INSTALLATION AT ZULF 330-339) | 2790-2792-DP-0112 |  | A |  |  | 2026-05-13 | DH
| 2790-2792-DP-0114-1 to 3_Rev-A(UMM SHAIF SET-UP DURING CROSSING MATTRESS INSTALLATION FOR CABLE ZTPS-3 TO ZULF 360-369) | 2790-2792-DP-0114 |  | A |  |  | 2026-05-13 | DH
| 2790-2792-DP-0115-1 TO 3_Rev-A (UMM SHAIF SET-UP DURING 15KV CABLE LAYING ZULF TPS-3 TO ZULF 360-369) | 2790-2792-DP-0115 |  | A |  |  | 2026-05-13 | DH
| 2790-2792-DP-0116_Rev-A(UMM SHAIF SET-UP DURING ICCP CABLE INSTALLATION AT ZULF 360-369) | 2790-2792-DP-0116 |  | A |  |  | 2026-05-13 | DH
| 2790-2792-DP-0110-1 to 4_Rev-A(UMM SHAIF SET-UP DURING CROSSING MATTRESS INSTALLATION FOR CABLE ZTPS-1 TO ZULF 330-339) | 2790-2792-DP-0110 |  | A |  |  | 2026-05-14 | DH
| 2790-2792-DP-0111-1 to 4_Rev-A (UMM SHAIF SET-UP DURING 15KV CABLE LAYING ZULF TPS-1 TO ZULF 330-339) | 2790-2792-DP-0111 |  | A |  |  | 2026-05-14 | DH
| 2790-2792-A3-074-1 TO 2_REV-A(UMM SHAIF TOWING ARRANGEMENT) | 2790-2792-A3-074 |  | A |  |  | 2026-07-03 | SKV
| 2790-2792-A0-108_R0(DELMA-2000 Passage plan from ANCHORAGE to ZULF 590-599) | 2790-2792-A0-108 |  | 0 |  |  | 2026-08-10 | SKV
| 2790-2792-A0-109_R0(DELMA-2000 Passage plan from ANCHORAGE to ZULF 282-293) | 2790-2792-A0-109 |  | 0 |  |  | 2026-08-10 | SKV
| 2790-2792-DP-0150-1 TO 2_Rev-A(DELMA-2000 SET-UP PLAN DURING Demolition and Installation of upgrade platform at ZULF 590-599) | 2790-2792-DP-0150 |  | A |  |  | 2026-08-14 | SKV
| 2790-2792-DP-0151-1 TO 2_Rev-A(DELMA-2000 SET-UP PLAN DURING Demolition and Installation of upgrade platform at ZULF 282-293) | 2790-2792-DP-0151 |  | A |  |  | 2026-08-14 | SKV