## Installation Procedures
|  | ADNOC OFFSHORE | [11 empty] | NMDC DOC. No.: MDR-001
ADNOC EPC for LZ HABSHAN UPPER RECOVERY LEKHWAIR+20 MPB PROJECT
|  | NPCC PROJECT NO. 2800 | [11 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | REF | DATE | CODE
| Anchor Handling and Mooring Procedure for Floating Barges | 2800-PP-OF-001 | AD-27-PL-62574 | A1 |  |  | T-414/24 | 2024-09-11
|  |  |  | 1 |  | 2024-12-30 | T-434/24 | 2024-09-17 | 2024-09-23 | 2800-NMDC-E-AO-PMT-T-00285 | 2024-10-11 | 11681-NMDC-T-0981 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-593/24 | 2024-12-15 | 2024-12-17 | 2800-NMDC-E-AO-PMT-T-00550 | 2025-01-09 | 11681-NMDC-T-1462 | 1 - Approved
|  |  |  | 3 |  |  | T-103/26 | 2026-03-12 | 2026-03-13 | 2800-NMDC-E-AO-PMT-T-02515
|  |  |  | 4 |  |  | T-108/26 | 2026-03-16 | 2026-03-16 | 2800-NMDC-E-AO-PMT-T-02526 | 2026-05-06 | 11681-NMDC-T-3551 | 2 - Approved with Comments
| Anchor Handling and Mooring Procedure for Jackup Barges | 2800-PP-OF-002 | AD-27-PL-62575 | A1 |  |  | T-415/24 | 2024-09-11
|  |  |  | 1 |  | 2024-12-30 | T-435/24 | 2024-09-17 | 2024-09-23 | 2800-NMDC-E-AO-PMT-T-00286 | 2024-10-28 | 11681-NMDC-T-1083 | 5 - Rejected
| ANCHOR HANDLING AND MOORING PROCEDURE FOR HAMMER HEAD CRANE VESSEL | 2800-PP-OF-003 | AD-27-PL-62576 | A1 |  |  | T-417/24 | 2024-09-12
|  |  |  | 1 |  | 2024-12-30 | T-436/24 | 2024-09-17 | 2026-09-23 | 2800-NMDC-E-AO-PMT-T-00287 | 2026-10-18 | 11681-NMDC-T-1025 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-519/24 | 2024-10-22 | 2024-10-28 | 2800-NMDC-E-AO-PMT-T-00389 | 18-Nov-2024 | 11681-NMDC-T-1166 | 1 - Approved
|  |  |  | 3 |  |  | T-254/25 | 2025-06-13
| Risers and Tie In Spools Installation Procedure | 2800-PP-OF-004 | AD-27-PL-62577 | A1 |  |  | T-303/25 | 2025-05-01
|  |  |  | 1 |  | 2025-05-15 | T-312/25 | 2025-07-02 | 2025-07-03 | 2800-NMDC-E-AO-PMT-T-01419 | 2025-08-12 | 11681-NMDC-T-2701 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-432/25 | 2025-08-27 | 2026-08-28 | 2800-NMDC-E-AO-PMT-T-01691 | 2026-09-18 | 11681-NMDC-T-2896 | 1 - Approved
|  |  |  | 3 |  |  | T-538/25 | 2025-10-21 | 2025-10-22 | 2800-NMDC-E-AO-PMT-T-02006 | 2026-01-20 | 11681-NMDC-T-3301 | 1 - Approved
| PIPELINES INSTALLATION MANUAL | 2800-PP-OF-005 | AD-27-PL-62578 | A1 |  |  | T-008/25 | 2025-01-08
|  |  |  | 1 |  | 2025-02-15 | T-080/25 | 2025-03-05 | 2025-03-12 | 2800-NMDC-E-AO-PMT-T-00893 | 2025-04-09 | 11681-NMDC-T-1961 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-196/25 | 2025-05-16 | 2025-05-19 | 2800-NMDC-E-AO-PMT-T-01197 | 2025-06-03 | 11681-NMDC-T-2297 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-344/25 | 2025-07-10 | 2025-07-10 | 2800-NMDC-E-AO-PMT-T-01457 | 2025-07-23 | 11681-NMDC-T-2572 | 2 - Approved with Comments
|  |  |  | 4 |  |  | T-595/25 | 2025-12-03 | 2025-12-05 | 2800-NMDC-E-AO-PMT-T-02176 | 2025-12-19 | 11681-NMDC-T-3204 | 2 - Approved with Comments
| Pipelines Crossing Supports Installation Procedure (Concrete Sleepers) | 2800-PP-OF-006 | AD-27-PL-62579 | A1 |  |  | T-440/24 | 2024-09-17
|  |  |  | 1 |  | 2024-11-15 | T-457/24 | 2024-09-24 | 2024-09-25 | 2800-NMDC-E-AO-PMT-T-00298 | 25-Dec-2024 | 11681-NMDC-T-1380 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-096/25 | 2025-03-10 | 2025-03-12 | 2800-NMDC-E-AO-PMT-T-00896
|  |  |  | 3 |  |  | T-244/25 | 2025-06-17 | 2025-06-18 | 2800-NMDC-E-AO-PMT-T-01352 | 2025-07-02 | 11681-NMDC-T-2462 | 2 - Approved with Comments
|  |  |  | 4 |  |  | T-364/25 | 2025-06-24 | 2025-07-18 | 2800-NMDC-E-AO-PMT-T-01518 | 2025-07-24 | 11681-NMDC-T-2896 | 2 - Approved with Comments
|  |  |  | 5 |  |  | T-502/25 | 2025-09-26 | 2025-09-29 | 2800-NMDC-E-AO-PMT-T-01882 | 2025-12-10 | 11681-NMDC-T-3198 | 1 - Approved
|  |  |  | 6 |  |  | T-242/26 | 2026-06-16 | 2026-06-24 | 2800-NMDC-E-AO-PMT-T-02773
| Cables Crossing Supports Installation Procedure (Concrete Mattresses) | 2800-PP-OF-007 | AD-27-PL-62580 | A1 |  |  | T-560/24 | 2024-11-26
|  |  |  | 1 |  | 2024-11-15 | T-586/24 | 2024-12-09 | 2024-12-13 | 2800-NMDC-E-AO-PMT-T-00543 | 2025-02-07 | 11681-NMDC-T-1703 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-120/25 | 2025-03-28 | 2025-04-02 | 2800-NMDC-E-AO-PMT-T-00952 | 2025-05-28 | 11681-NMDC-T-2257 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-380/25 | 2025-08-01 | 2025-08-01 | 2800-NMDC-E-AO-PMT-T-01550 | 2025-09-18 | 11681-NMDC-T-2896 | 1 - Approved
|  |  |  | 4 |  |  | T-559/25 | 2025-11-03 | 2025-11-06 | 2800-NMDC-E-AO-PMT-T-02066 | 2025-11-10 | 11681-NMDC-T-3113 | 1 - Approved
| J-Tubes Installation Procedure | 2800-PP-OF-008 | AD-27-PL-62581 | A1 |  |  | T-602/24 | 2025-01-02
|  |  |  | 1 |  | 2024-12-25 | T-004/25 | 2025-01-08 | 2025-01-09 | 2800-NMDC-E-AO-PMT-T-00584 | 2025-01-28 | 11681-NMDC-T-1606 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-264/25 |  | 2025-06-19 | 2800-NMDC-E-AO-PMT-T-01350 | 2025-07-02 | 11681-NMDC-T-2467 | 1 - Approved
|  |  |  | 3 |  |  | T-434/25 | 2025-08-28 | 2025-08-29 | 2800-NMDC-E-AO-PMT-T-01696 | 2025-09-18 | 11681-NMDC-T-2896 | 2 - Approved with Comments
|  |  |  | 4 |  |  | T-499/25 | 2025-09-25 | 2025-09-29 | 2800-NMDC-E-AO-PMT-T-01879 | 2025-12-10 | 11681-NMDC-T-3198 | 1 - Approved
| Risers and-Tubes Clamps Installation Procedure | 2800-PP-OF-009 | AD-27-PL-62582 | A1 |  |  | T-599/24 | 2024-12-25
|  |  |  | 1 |  | 2024-12-25 | T-009/25 | 2025-01-08 | 2025-01-13 | 2800-NMDC-E-AO-PMT-T-00625 | 2025-01-28 | 11681-NMDC-T-1606 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-201/25 |  | 2025-05-30 | 2800-NMDC-E-AO-PMT-T-01237 | 2025-06-19 | 11681-NMDC-T-2397 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-443/25 | 2025-09-02 | 2025-09-03 | 2800-NMDC-E-AO-PMT-T-01740
|  |  |  | 4 |  |  | T-501/25 | 2025-09-26 | 2025-09-29 | 2800-NMDC-E-AO-PMT-T-01881
|  |  |  | 5 |  |  | T-623/25 | 2025-12-16 | 2025-12-31 | 2800-NMDC-E-AO-PMT-T-02271 | 2026-01-08 | 11681-NMDC-T-3273 | 1 - Approved
| Subsea Cables Installation Procedures | 2800-PP-OF-010 | AD-27-PL-62583 | A1 |  |  | T-280/25 | 2025-07-02
|  |  |  | 1 |  | 2025-04-01 | T-328/25 | 2025-07-07 | 2025-07-08 | 2800-NMDC-E-AO-PMT-T-01440 | 2025-08-12 | 11681-NMDC-T-2701 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-423/25 | 2025-08-22
|  |  |  | 3 |  |  | T-529/25 | 2025-10-16 | 2025-10-17 | 2800-NMDC-E-AO-PMT-T-01975 | 2025-12-19 | 11681-NMDC-T-3204 | 1 - Approved
|  |  |  | 4 |  |  | T-172/26 | 2026-04-28 | 2026-04-29 | 2800-NMDC-E-AO-PMT-T-02644
| FREE SPANS CORRECTION AND GROUT BAG INSTALLATION PROCEDURE | 2800-PP-OF-011 | AD-27-PL-62584 | A1 |  |  | T-479/25 | 2025-09-17
|  |  |  | 1 |  | 2025-09-30 | T-483/25 | 2025-09-18 | 2025-09-23 | 2800-NMDC-E-AO-PMT-T-01838
|  |  |  | 2 |  |  | T-530/25 | 2025-10-15 | 2025-10-17 | 2800-NMDC-E-AO-PMT-T-01985 | 2026-03-25 | 11681-NMDC-T-3448 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-589/25 | 2025-11-21 | 2025-11-24 | 2800-NMDC-E-AO-PMT-T-02153 | 2026-01-15 | 11681-NMDC-T-3296 | 1 - Approved
| Pipeline External Anti-Corrosion Field Joint Coating Procedure | 2800-PP-OF-012 | AD-27-PL-62585 |  |  | NA
| Pipeline External Infill Field Joint Coating Procedure | 2800-PP-OF-013 | AD-27-PL-62586 |  |  | NA
| Pipeline Flooding Gauging and Hydrotesting Procedure | 2800-PP-OF-014 | AD-27-PL-62587
| PIPELINE INSTALLATION AND LAYING ANALYSIS - OVERVIEW | 2800-PP-OF-017 | AD-27-PL-62590 | 1 |  | 2024-12-25 | T-601/24 | 2024-12-26 | 2024-12-28 | 2800-NMDC-E-AO-PMT-T-00574 | 2025-02-05 | 11681-NMDC-T-1685 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-561/25 | 2025-11-03 | 2025-11-10 | 2800-NMDC-E-AO-PMT-T-02084 | 2025-12-19 | 11681-NMDC-T-3204 | 1 - Approved
| DAVIT LIFTING ANALYSIS OVERVIEW DURING RISERS AND SPOOLS INSTALLATION | 2800-PP-OF-019 | AD-27-PL-62592 | 1 |  | 2024-12-25 | T-600/24 | 2024-12-26 | 2024-12-28 | 2800-NMDC-E-AO-PMT-T-00575 | 29-Jan-2025 | 11681-NMDC-T-1625 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-562/25 | 2025-11-04 | 2025-11-10 | 2800-NMDC-E-AO-PMT-T-02086 | 2025-12-19 | 11681-NMDC-T-3204 | 1 - Approved
| ANCHOR HANDLING AND MOORING PROCEDURE FOR WORKBOATS AD-27-PL-62722 | 2800-PP-OF-032 | AD-27-PL-62722 | 1 |  | 2024-12-30 | T-442/24 | 2024-09-18
|  |  |  | 2 |  |  | T-594/24 | 2024-12-16 | 2024-12-20 | 2800-NMDC-E-AO-PMT-T-00555 | 2025-01-06 | 11681-NMDC-T-1440 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-161/25 | 2025-04-25 | 2025-04-28 | 2800-NMDC-E-AO-PMT-T-01059 | 2025-05-28 | 11681-NMDC-T-2257 | 2 - Approved with Comments
|  |  |  | 4 |  |  | T-257/25 | 2025-06-13 | 2025-06-18 | 2800-NMDC-E-AO-PMT-T-01333 | 2025-07-05 | 11681-NMDC-T-2473 | 2 - Approved with Comments
| LOWER ZAKUM - SUBSEA FLANGE MANAGEMENT PROCEDURE | 2800-PP-OF-033 | AD-27-PL-63104 | A1 |  |  | T-208/25
|  |  |  | 1 |  | 2025-02-15 | T-228/25 | 2025-06-02 | 2025-06-04 | 2800-NMDC-E-AO-PMT-T-01269 | 2025-07-02 | 11681-NMDC-T-2455 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-352/25 | 2025-07-15 | 2025-07-15 | 2800-NMDC-E-AO-PMT-T-01477 | 2025-09-25 | 11681-NMDC-T-2936 | 2 - Approved with Comments
| LOWER ZAKUM - LIFTING PLAN AND PROCEDURE FOR SHALLOW DRAFT BOAT UNIQUE 2761 | 2800-PP-OF-034 | AD-27-PL-63312
| LOWER ZAKUM-MOBILIZATION & CALIBRATION REPORT FOR PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY BY M.V.MUTAWA-17 | 2800-PP-OF-035 | AD-27-PL-63401
| LOWER ZAKUM- MOBILIZATION & CALIBRATION REPORT FOR PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY BY UNIQUE-2761 | 2800-PP-OF-036 | AD-27-PL-63402
| LOWER ZAKUM- MOBILIZATION & CALIBRATION REPORT FOR PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY BY SAFEEN GAMMA | 2800-PP-OF-037 | AD-27-PL-63403
| LOWER ZAKUM - METHOD STATEMENT FOR ADDITIONAL MITIGATION DURING ANCHOR HANDLING WHILE CROSSING GAS LINES AND MAIN OIL LINES BY GRAVITY ANCHOR | 2800-PP-OF-039 | AD-27-PL-80050 | 1 |  | 2025-06-25 | T-253/25 | 2025-06-13 | 2025-06-16 | 2800-NMDC-E-AO-PMT-T-01341
| LOWER ZAKUM – STALK-ON RISER INSTALLATION PROCEDURE | 2800-PP-OF-040 | AD-27-PL- 63470 | A1 |  |  | T-342/25
|  |  |  | 1 |  | 2025-06-15 | T-347/25 | 2025-07-15 | 2025-07-15 | 2800-NMDC-E-AO-PMT-T-01478 | 2025-08-11 | 11681-NMDC-T-2701 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-458/25 | 2025-09-06 | 2025-09-08 | 2800-NMDC-E-AO-PMT-T-01785 | 2025-10-02 | 11681-NMDC-T-2976 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-553/25 | 2025-10-30 | 2025-11-06 | 2800-NMDC-E-AO-PMT-T-02067 | 2025-11-10 | 11681-NMDC-T-3113 | 1 - Approved
| LOWER ZAKUM – SUBSEA SPOOLS INSTALLATION PROCEDURE | 2800-PP-OF-041 | AD-27-PL-63471 | A1 |  |  | T-330/25
|  |  |  | 1 |  | 2025-06-15 | T-334/25 | 2025-07-15 | 2025-07-15 | 2800-NMDC-E-AO-PMT-T-01479 | 2025-10-15 | 11681-NMDC-T-3029 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-548/25 | 2025-10-24 | 2025-10-27 | 2800-NMDC-E-AO-PMT-T-02028 | 2025-12-10 | 11681-NMDC-T-3198 | 1 - Approved
| METHOD STATEMENT FOR FLOODING, CLEANING, GAUGING, HYDROTESTING AND LEAK TESTING | 2800-PP-OF-044 | AD-27-PL-63472 | A1 |  | 2025-08-15 | T-400/25 | 2025-08-08
|  |  |  | 1 |  |  | T-402/25 | 2025-08-11 | 2025-08-14 | 2800-NMDC-E-AO-PMT-T-01613 | 2026-08-11 | 11681-NMDC-T-2896 | 1 - Approved
|  |  |  | 2 |  |  | T-340/26 | 2026-08-12 | 2026-08-27 | 2800-NMDC-E-AO-PMT-T-02904
| LOWER ZAKUM - METHOD STATEMENT FOR CALIPER PIGGING AND INTELLIGENT PIGGING | 2800-PP-OF-045 |  | Subcontract Doc
| METHOD STATEMENT FOR DEWATERING DRYING AND NITROGEN PURGING. | 2800-PP-OF-046 | AD-27-PL-63474 | 1 |  | 2025-11-30 | T-597/25 | 2025-12-03 | 2025-12-05 | 2800-NMDC-E-AO-PMT-T-02177 | 2025-12-19 | 11681-NMDC-T-3204 | 1 - Approved
| METHOD STATEMENT FOR PIPELINE MULTIPLE STALK-ON | 2800-PP-OF-073 | AD-27-PL-63534 | A1 |  |  | T-506/25
|  |  |  | 1 |  | 2025-09-30 | T-512/25 | 2025-10-08 | 2025-10-10 | 2800-NMDC-E-AO-PMT-T-01944 | 2026-09-03 | 11681-NMDC-T-3204 | 1 - Approved

## Setup Plans & Anchor Patterns
|  | ADNOC OFFSHORE | [11 empty] | NMDC DOC. No.: MDR-001
ADNOC EPC for LZ HABSHAN UPPER RECOVERY LEKHWAIR+20 MPB PROJECT
|  | NPCC PROJECT NO. 2800 | [11 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| LOWER ZAKUM - PIPE LAYING BARGE ANCHOR PATTERN DURING LAYING OF 10" WI PIPELINE FROM ZK-47 TO ZK-372 | 2800-AP-0001 | AD-164-PL-625010-SHT-001 | 1 |  | 2025-04-01 | T-215/25 | 2025-05-27 | 2025-05-27 | 2800-NMDC-E-AO-PMT-T-01229 | 03-Jun-2025 | 11681-NMDC-T-2297 | 1 - Approved
|  |  |  | 2 |  |  | T-259/25 | 2025-06-15 | 2025-06-18 | 2800-NMDC-E-AO-PMT-T-01334 | 2026-04-03 | 11681-NMDC-T-3467 | 1 - Approved
|  |  |  | 3 |  |  | T-272/25 | 2025-06-19 | 2025-06-25 | 2800-NMDC-E-AO-PMT-T-01367 | 2025-07-05 | 11681-NMDC-T-2478 | 1 - Approved
|  |  |  | 4 |  |  | T-341/25 | 2025-07-09 | 2025-07-08 | 2800-NMDC-E-AO-PMT-T-01449
| PLB-648 ANCHOR PATTERN DURING LAYING OF 10'' WI PIPELINE FROM ZK-372 TO ZK-126.5/65 | 2800-AP-0002 | AD-313-PL-625021-SHT-001 | 1 |  | 2025-04-01 | T-262/25 | 2025-06-17 | 2025-06-18 | 2800-NMDC-E-AO-PMT-T-01302 | 2026-04-03 | 11681-NMDC-T-3467 | 1 - Approved
|  |  |  | 2 |  |  | T-272/25 | 2025-06-19 | 2025-06-25 | 2800-NMDC-E-AO-PMT-T-01368 | 2002-07-02 | 11681-NMDC-T-2461 | 1 - Approved
|  |  |  | 3 |  |  | T-336/25 | 2025-07-09 | 2025-07-09 | 2800-NMDC-E-AO-PMT-T-01448
|  |  |  | 4 |  |  | T-379/25 | 2025-07-29 | 2025-07-29 | 2800-NMDC-E-AO-PMT-T-01538 | 2026-04-03 | 11681-NMDC-T-3467 | 1 - Approved
| PLB-648 ANCHOR PATTERN DURING LAYING OF 6'' GAS LIFT (GL-1) PIPELINE FROM ZWSC GIP TO ZK-50 | 2800-AP-0003 | AD-166-PL-625029-SHT-001 | 1 |  | 2025-04-01 | T-302/25 | 2025-06-25 | 2025-06-30 | 2800-NMDC-E-AO-PMT-T-01396 | 2025-07-10 | 11681-NMDC-T-2500 | 1 - Approved
|  |  |  | 2 |  |  | T-437/25 | 2025-08-28 | 2025-08-28 | 2800-NMDC-E-AO-PMT-T-01689 | 03-Apr-2026 | 11681-NMDC-T-3467 | 1 - Approved
| PLB-648 ANCHOR PATTERN DURING LAYING OF 6'' GAS LIFT (GL-2) PIPELINE FROM ZK-50 TO ZK-43A | 2800-AP-0004 | AD-166-PL-625030-SHT-001 | 1 |  | 2025-04-01 | T-305/25 | 2025-06-30 | 2025-07-01 | 2800-NMDC-E-AO-PMT-T-01405 | 2025-08-12 | 11681-NMDC-T-2701 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-418/25 | 2025-08-28 | 2025-08-30 | 2800-NMDC-E-AO-PMT-T-01697 | 2025-08-21 | 11681-NMDC-T-2754 | 3 - Reviewed with Comments
|  |  |  | 3 |  |  | T-444/25 | 2025-09-02 | 2025-09-03 | 2800-NMDC-E-AO-PMT-T-01741 | 2026-04-03 | 11681-NMDC-T-3467 | 1 - Approved
| LOWER ZAKUM - PIPE LAYING BARGE ANCHOR PATTERN DURING LAYING OF 6" GL-3 PIPELINE FROM ZK-43A TO ZK-45 | 2800-AP-0005 | AD-165-PL-625027-SHT-001 | 1 |  | 2025-02-01 | T-321/25 | 2025-07-03 | 2025-07-04 | 2800-NMDC-E-AO-PMT-T-01423 | 2025-08-12 | 11681-NMDC-T-2698 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-460/25 | 2025-09-08 | 2025-09-09 | 2800-NMDC-E-AO-PMT-T-01784 | 2025-09-09 | 11681-NMDC-T-2847 | 3 - Reviewed with Comments
| PLB-648 ANCHOR PATTERN DURING LAYING OF 6'' (GL-4) PIPELINE FROM ZK-45 TO ZK-56 | 2800-AP-0006 | AD-162-PL-625021-SHT-001 | 1 |  | 2025-02-01 | T-427/25 | 2025-08-26 | 2025-08-28 | 2800-NMDC-E-AO-PMT-T-01683 | 2025-09-08 | 11681-NMDC-T-2841 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-522/25 | 2025-10-13 | 2025-08-28 | 2800-NMDC-E-AO-PMT-T-01961 | 2026-02-17 | 11681-NMDC-T-3377 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-343/26 | 2026-08-17 | 2026-08-14 | 2800-NMDC-E-AO-PMT-T-02903
| PLB-648 ANCHOR PATTERN DURING SLEEPER INSTALLATION AT GL-3 CROSSING LOCATION | 2800-AP-0007 | AD-27-PL-625197-SHT-001 | 1 |  | 2025-03-15 | T-153/25 | 2025-04-21 | 2025-04-24 | 2800-NMDC-E-AO-PMT-T-01042 | 2025-05-06 | 11681-NMDC-T-2113 | 2 - Approved with Comments
|  |  |  | 2 |  |  | T-217/25 | 2025-05-27 | 2025-05-27 | 2800-NMDC-E-AO-PMT-T-01230 | 2025-05-29 | 11681-NMDC-T-2264 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-246/25 | 2025-06-09 | 2025-06-11 | 2800-NMDC-E-AO-PMT-T-01291 | 2025-07-05 | 11681-NMDC-T-2264 | 1 - Approved
| PLB-648 ANCHOR PATTERN DURING SLEEPER INSTALLATION AT GL-4 CROSSING LOCATION- Option 1&2 | 2800-AP-0008 | AD-27-PL-625198-SHT-001 | 1 |  | 2025-04-15 | T-190/25 | 2025-05-13 | 2025-05-14 | 2800-NMDC-E-AO-PMT-T-01176 | 2025-06-27 | 11681-NMDC-T-2441 | 1 - Approved
|  |  |  | 2 |  |  | T-294/25 | 2025-06-25 | 2025-07-01 | 2800-NMDC-E-AO-PMT-T-01414 | 2025-07-11 | 11681-NMDC-T-2521 | 3 - Reviewed with Comments
| PLB-648 ANCHOR PATTERN DURING SLEEPER INSTALLATION AT GL-2 CROSSING LOCATION (CR # 11 & 18) | 2800-AP-0009 | AD-27-PL-625202-SHT-001 | Tittle cancelled
| PLB-648 ANCHOR PATTERN DURING RISER / J-TUBE CLAMPS INSTALLATION AT ZK-43A LOCATION | 2800-AP-0010 | AD-165-PL-625037-SHT-001 | Tittle cancelled
| PLB-648 ANCHOR PATTERN DURING RISER / J-TUBE CLAMPS INSTALLATION AT ZK-45 LOCATION | 2800-AP-0011 | AD-162-PL-625027-SHT-001 | Tittle cancelled
| PLB-648 ANCHOR PATTERN DURING RISER / J-TUBE CLAMPS INSTALLATION AT ZK-56 LOCATION | 2800-AP-0012 | AD-168-PL-625004-SHT-001 | Tittle cancelled
| PLB-648 ANCHOR PATTERN DURING GL-3 & 4 RISER INSTALLATION AT ZK-45 LOCATION | 2800-AP-0013 | AD-162-PL-625028-SHT-001 | 1 |  | 2025-06-15 | T-451/25 | 2025-09-03 | 2025-09-04 | 2800-NMDC-E-AO-PMT-T-01763 | 2025-09-09 | 11681-NMDC-T-2841 | 1 - Approved
| PLB-648 ANCHOR PATTERN DURING 10'' (WI-3) PIPELINE SHIFTING AT ZK-47 | 2800-AP-0014 | AD-164-PL-625012-SHT-001 | 1 |  | 2025-08-15 | T-531/25 | 2025-10-16 | 2025-10-17 | 2800-NMDC-E-AO-PMT-T-01984 | 2025-10-21 | 11681-NMDC-T-3047 | 1 - Approved
|  |  |  | 2 |  |  | T-578/25 | 2025-11-14 | 2025-11-14 | 2800-NMDC-E-AO-PMT-T-02123 | 2025-11-18 | 11681-NMDC-T-3137 | 1 - Approved
| PLB-648 ANCHOR PATTERN DURING 10'' (WI-4) PIPELINE SHIFTING AT ZK-372 | 2800-AP-0015 | AD-313-PL-625027-SHT-001 | 1 |  | 2025-08-15 | T-497/25 | 2025-09-24 | 2025-09-24 | 2800-NMDC-E-AO-PMT-T-01867 | 2025-09-25 | 11681-NMDC-T-2933 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-535/25 | 2025-10-20 | 2025-10-22 | 2800-NMDC-E-AO-PMT-T-02001 | 2025-10-27 | 11681-NMDC-T-3066 | 1 - Approved
| LOWER ZAKUM - PIPE LAYING BARGE ANCHOR PATTERN DURING LAYING OF 10" WI PIPELINE FROM ZK-372 TO ZK-126.5/65(START UP ZK-372) | 2800-AP-0016 | AD-313-PL-625028-SHT-001 | Tittle cancelled
| PLB-648 ANCHOR PATTERN DURING GL-3 RISER INSTALLATION AT ZK-43A | 2800-AP-0017 | AD-165-PL-625038-SHT-001 | 1 |  | 2025-08-15 | T-451/25 | 2025-09-03 | 2025-09-04 | 2800-NMDC-E-AO-PMT-T-01764 | 2025-09-03 | 11681-NMDC-T-2841 | 1 - Approved
|  |  |  | 2 |  |  | T-087/26 | 2026-03-04
| PLB-648 ANCHOR PATTERN DURING GL-1 RISER INSTALLATION AT ZK-50 | 2800-AP-0018 | AD-166-PL-625047-SHT-001 | 1 |  | 2025-12-15 | T-027/26 | 2026-01-21 | 2026-01-22 | 2800-NMDC-E-AO-PMT-T-02325 | 2025-01-23 | 11681-NMDC-T-3309 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-087/26 | 2026-03-04 |  |  | 2026-03-10 | 11681-NMDC-T-3418 | 1 - Approved
|  |  |  | 3 |  | 2025-12-15 | T-243/26 | 2028-06-12 | 2026-06-17 | 2800-NMDC-E-AO-PMT-T-02765 | 2026-06-19 | 11681-NMDC-T-3624 | 1 - Approved
| PLB-648 ANCHOR PATTERN DURING GL-2 RISER INSTALLATION AT ZK-50 | 2800-AP-0019 | AD-166-PL-625048-SHT-001 | 1 |  |  | T-027/26 | 2026-01-21 | 2026-01-22 | 2800-NMDC-E-AO-PMT-T-02325 | 2025-01-23 | 11681-NMDC-T-3309 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-087/26 | 2026-02-25 | 2026-03-05 | 2800-NMDC-E-AO-PMT-T-02487 | 2026-03-10 | 11681-NMDC-T-3418 | 1 - Approved
|  |  |  | 3 |  |  | T-243/26 | 2028-06-12 | 2026-06-17 | 2800-NMDC-E-AO-PMT-T-02765 | 2026-06-19 | 11681-NMDC-T-3624 | 1 - Approved
| PLB-648 ANCHOR PATTERN DURING GL-4 RISER INSTALLATION AT ZK-56 | 2800-AP-0020 | AD-168-PL-625005-SHT-001 | 1 |  |  | T-362/26 | 2026-08-24 | 2026-08-24 | 2800-NMDC-E-AO-PMT-T-02925 |  |  | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-387/26 | 2026-09-01 | 2026-09-02 | 2800-NMDC-E-AO-PMT-T-02933
| PLB-648 ANCHOR PATTERN DURING GL-2 RISER INSTALLATION AT ZK-43A LOCATION | 2800-AP-0021 | AD-165-PL-625040-SHT-001 | 1 |  | 2025-12-15 | T-492/25 | 2025-09-22 | 2025-09-23 | 2800-NMDC-E-AO-PMT-T-01839 | 2026-09-25 | 11681-NMDC-T-34292418 | 1 - Approved
| PLB-648 ANCHOR PATTERN DURING GL-1 RISER INSTALLATION AT ZWSC-GIP | 2800-AP-0022 | AD-447-PL-625035-SHT-001 | 1 |  | 2025-07-30 | T-430/25 | 2025-08-27 | 2025-08-28 | 2800-NMDC-E-AO-PMT-T-01690
|  |  |  | 2 |  |  | T-456/25 | 2025-09-04 | 2025-09-08 | 2800-NMDC-E-AO-PMT-T-01774 | 2026-02-20 | 11681-NMDC-T-3377 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-022/26 | 2026-01-19 | 2026-01-20 | 2800-NMDC-E-AO-PMT-T-02318 | 2026-01-21 | 11681-NMDC-T-3305 | 2 - Approved with Comments
| PLB-648 ANCHOR PATTERN DURING WEATHER STANDBY POSITION | 2800-AP-0023 | AD-27-PL-625226-SHT-001
| QMS CONQUEST SET UP AT ZK-43A | 2800-AP-0024 | AD-165-Z-800022-SHT-001 | 1 |  | 2026-04-15 | T-134/26 | 2026-04-01 | 2026-04-01 | 2800-NMDC-E-AO-PMT-T-02555 | 2026-04-10 | 11681-NMDC-T-3478 | 1 - Approved
|  |  |  | 2 |  |  | T-331/26 | 2026-07-31 | 2026-08-04 | 2800-NMDC-E-AO-PMT-T-02883
| PLB-648 ANCHOR PATTERN DURING MODULE INSTALLATION AT ZK-47 | 2800-AP-0025 | AD-164-PL-625017-SHT-001 | 1 |  | 2025-12-25 | T-618/25 | 2025-12-11 | 2025-12-15 | 2800-NMDC-E-AO-PMT-T-02198 | 2025-12-15 | 11681-NMDC-T-3210 | 1 - Approved
|  |  |  | 2 |  |  | T-640/25 | 2025-12-29 | 2025-12-31 | 2800-NMDC-E-AO-PMT-T-02272 | 21-Jan-2026 | 11681-NMDC-T-3305 | 2 - Approved with Comments
|  |  |  | 3 |  |  | T-101/26 | 2026-03-10 | 2026-03-11 | 2800-NMDC-E-AO-PMT-T-02511 | 2026-03-18 | 11681-NMDC-T-3430 | 3 - Reviewed with Comments
|  |  |  | 4 | PMT DIRECT
| PLB-648 ANCHOR PATTERN DURING AIRBAG INSTALLATION AT ZK-43A | 2800-AP-0026 | AD-165-Z-800021-SHT-001
| PLB-648 ANCHOR PATTERN DURING MODULE INSTALLATION AT ZK-50 | 2800-AP-0027 | AD-166-Z-800022-SHT-001 | 1 |  |  | T-243/26 | 2028-06-12 | 2026-06-17 | 2800-NMDC-E-AO-PMT-T-02766 | 2026-06-19 | 11681-NMDC-T-3624 | 1 - Approved
|  |  |  | 2 |  |  | T-341/26 | 2026-08-11 | 2026-08-14 | 2800-NMDC-E-AO-PMT-T-02903
| JOPETWIL-215 SET-UP AT ZK-126.5 | 2800-AP-0028 |  | 1 |  |  | T-295/26 | 2026-07-09 | 2026-07-10 | 2800-NMDC-E-AO-PMT-T-02828 | 2026-07-14 | 11681-NMDC-T-3674 | 1 - Approved
|  |  |  | 2 |  |  | T-314/26 | 2026-07-21 | 2026-07-23 | 2800-NMDC-E-AO-PMT-T-02859
| JOPETWIL-215 SET-UP DURING HOOK-UP WORKS AT ZK-329 | 2800-AP-0029 | AD-314-Z-000001-SHT-001
| SEP-550 SET UP DURING HOOK-UP WORKS AT ZK-50 | 2800-AP-0030 | AD-166-Z-800019-SHT-001
| PLB-648 ANCHOR PATTERN DURING DOG HOUSES INSTALLATION FOR GL-4 PIPELAY FROM ZK-45 TO ZK-56 | 2800-AP-0031 | AD-162-Z-800022-SHT-001
| LOWER ZAKUM - WORK BOAT ANHCOR PATTERN AT ZK-372 | 2800-AP-0101 | AD-313-PL-625022-SHT-001 |  |  | 2025-07-01
| LOWER ZAKUM - WORK BOAT ANHCOR AT ZK-126.5/65 | 2800-AP-0102 | AD-312-PL-625032-SHT-001 |  |  | 2025-07-01
| LOWER ZAKUM - WORK BOAT ANHCOR PATTERN AT ZK-50 | 2800-AP-0103 | AD-166-PL-625031-SHT-001 |  |  | 2025-07-01
| LOWER ZAKUM - WORK BOAT ANHCOR UPATTERN AT ZK-43A | 2800-AP-0104 | AD-165-PL-625028-SHT-001 |  |  | 2025-07-01
| LOWER ZAKUM - WORK BOAT ANHCOR PATTERN AT ZK-45 | 2800-AP-0105 | AD-162-PL-625022-SHT-001 |  |  | 2025-07-01
| LOWER ZAKUM - WORK BOAT ANHCOR PATTERN AT ZK-56 | 2800-AP-0106 | AD-168-PL-625001-SHT-001 |  |  | 2025-07-01
| LOWER ZAKUM - WORK BOAT ANHCOR PATTERN AT ZK-44 | 2800-AP-0107 | AD-410-PL-625020-SHT-001 |  |  | 2025-07-01
| LOWER ZAKUM - WORK BOAT ANHCOR PATTERN AT ZK-88 | 2800-AP-0108 | AD-174-PL-625000-SHT-001 |  |  | 2025-07-01
| LOWER ZAKUM - WORK BOAT ANHCOR PATTERN AT ZK-307 | 2800-AP-0109 | AD-299-PL-625006-SHT-001 |  |  | 2025-07-01
| LOWER ZAKUM - WORK BOAT ANHCOR PATTERN AT WHT-2 | 2800-AP-0110 | AD-332-PL-625000-SHT-001 |  |  | 2025-07-01
| LOWER ZAKUM - WORK BOAT ANHCOR PATTERN AT ZK-329 | 2800-AP-0111 | AD-314-PL-625013-SHT-001 |  |  | 2025-07-01
| LOWER ZAKUM - WORK BOAT ANHCOR PATTERN AT ZWSC GIP | 2800-AP-0112 | AD-447-PL-625031-SHT-001 |  |  | 2025-07-01
| MP-02 SET-UP AT ZK-280 | 2800-AP-0113 |  |  |  |  | T-296/26 | 2026-07-09 | 2026-07-10 | 2800-NMDC-E-AO-PMT-T-02829 | 2026-07-14 | 11681-NMDC-T-3674 | 1 - Approved
| QMS CONQUEST SET UP AT ZK-44 | 2800-AP-0114 |  |  |  |  | T-310/26 | 2026-07-20 | 2026-07-21 | 2800-NMDC-E-AO-PMT-T-02852
| JOPETWIL-215 SET UP AT ZCSC-NWIP | 2800-AP-0115
| JOPETWIL-215 SET UP AT ZK-40 | 2800-AP-0116
| spare | 2800-AP-0117
| PLB-648 ANCHOR PATTERN DURING GL-1 RISER INSTALLATION AT ZK-50 | 2800-AP-0118 | AD-166-Z-800020-SHT-001
| PLB-648 ANCHOR PATTERN DURING GL-2 RISER INSTALLATION AT ZK-50 | 2800-AP-0119 | AD-166-Z-800021-SHT-001
| WORK BOAT BES SOLAR SET UP PLAN AT ZK-47 | 2800-AP-0120 | AD-164-Z-800014-SHT-001 | 1 |  | NA | T-371/26 | 2026-08-25 | PMT Rejected
| WORK BOAT BES SOLAR SET UP PLAN AT ZK-372 | 2800-AP-0121 | AD-313-Z-000001-SHT-001 | 1 |  | NA | T-371/26 | 2026-08-25 | PMT Rejected
| WORK BOAT BES SOLAR SET UP PLAN AT ZK-126.5 | 2800-AP-0122 | AD-312-Z-800019-SHT-001 |  |  | NA
| WORK BOAT BES SOLAR SET UP PLAN AT GIP | 2800-AP-0123 | AD-447-Z-800025-SHT-001 |  |  | NA
| WORK BOAT BES SOLAR SET UP PLAN AT ZK-50 | 2800-AP-0124 | AD-166-Z-800017-SHT-001 |  |  | NA
| WORK BOAT BES SOLAR SET UP PLAN AT ZK-43A | 2800-AP-0125 | AD-165-Z-800023-SHT-001 |  |  | NA
| WORK BOAT BES SOLAR SET UP PLAN AT ZK-45 | 2800-AP-0126 | AD-162-Z-800020-SHT-001 |  |  | NA
| WORK BOAT BES SOLAR SET UP PLAN AT ZK-56 | 2800-AP-0127 | AD-168-Z-800016-SHT-001 |  |  | NA
| LOWER ZAKUM - JACKUP BARGE SETUP PLAN AND ANHCOR PATTERN AT ZK-372 | 2800-AP-0201 | AD-313-PL-625023-SHT-001
| LOWER ZAKUM - JACKUP BARGE SETUP PLAN AND ANHCOR PATTERN AT ZK-126.5/65 | 2800-AP-0202 | AD-312-PL-625033-SHT-001
| SEP-550 ANCHOR PATTERN DURING HOOK-UP WORKS AT ZK-50 | 2800-AP-0203 | AD-166-PL-625032-SHT-001 | 1 |  | 2025-05-01 | T-231/26 | 2026-06-01 | 2026-06-30 | 2800-NMDC-E-AO-PMT-T-02807
|  |  |  | 2 |  |  | T-275/26 | 2026-07-01 | 2026-07-03 | 2800-NMDC-E-AO-PMT-T-02811
|  |  |  | 3 |  |  | T-341/26 | 2026-08-11 | 2026-08-14 | 2800-NMDC-E-AO-PMT-T-02903
| HEA TITAN SET UP AT ZK-43A | 2800-AP-0204 | AD-165-PL-625029-SHT-001 | 1 |  | 2025-08-15 | T-417/25 | 2025-08-18 | 2026-01-23 | 2800-NMDC-E-AO-PMT-T-01637 | 2026-07-15 | 11681-NMDC-T-3306 | 1 - Approved
| LOWER ZAKUM - JACKUP BARGE SETUP PLAN AND ANHCOR PATTERN AT ZK-45 | 2800-AP-0205 | AD-162-PL-625023-SHT-001
| LOWER ZAKUM - JACKUP BARGE SETUP PLAN AND ANHCOR PATTERN AT ZK-56 | 2800-AP-0206 | AD-168-PL-625002-SHT-001
| LOWER ZAKUM - JACKUP BARGE SETUP PLAN AND ANHCOR PATTERN AT ZK-44 | 2800-AP-0207 | AD-410-PL-625021-SHT-001
| QMS CONQUEST SET-UP DURING HOOK-UP WORKS AT ZK-88 | 2800-AP-0208 | AD-174-PL-625001-SHT-001 | 1 |  | 2026-01-30 | T-041/26 | 2026-01-28 | 2026-01-29 | 2800-NMDC-E-AO-PMT-T-02360 | 2026-02-04 | 11681-NMDC-T-3481 | 2 - Approved with Comments
| LOWER ZAKUM - JACKUP BARGE SETUP PLAN AND ANHCOR PATTERN AT ZK-307 | 2800-AP-0209 | AD-299-PL-625007-SHT-001
| LOWER ZAKUM - JACKUP BARGE SETUP PLAN AND ANHCOR PATTERN AT WHT-2 | 2800-AP-0210 | AD-332-PL-625001-SHT-001
| LOWER ZAKUM - JACKUP BARGE SETUP PLAN AND ANHCOR PATTERN AT ZK-329 | 2800-AP-0211 | AD-314-PL-625014-SHT-001
| LOWER ZAKUM - JACKUP BARGE SETUP PLAN AND ANHCOR PATTERN AT ZWSC GIP | 2800-AP-0212 | AD-447-PL-625032-SHT-001 | 1 |  | 2026-03-15 | T-138/26 | 2026-04-02 | 2026-04-07 | 2800-NMDC-E-AO-PMT-T-02563 | 2026-04-10 | 11681-NMDC-T-3481 | 2 - Approved with Comments
|  |  |  | 2 | 2 |  | T-249/26 | 2026-06-17 | 2026-06-18 | 2800-NMDC-E-AO-PMT-T-02777 | 2026-06-24 | 11681-NMDC-T-3631 | 3 - Reviewed with Comments
| JOPETWIL-215 SET UP AT ZK-277 | 2800-AP-0213 | AD-302-PL-625003-SHT-001 | 1 |  | 2025-08-15 | T-417/25 | 2025-08-18 | 2025-08-22 | 2800-NMDC-E-AO-PMT-T-01638
| HEA KRAKEN SET UP AT ZK-280 | 2800-AP-0214 | AD-306-PL-625000-SHT-001 | 1 |  | 2025-08-15 | T-417/25 | 2025-08-18 | 2025-08-22 | 2800-NMDC-E-AO-PMT-T-01639 | 2025-08-15 | 11681-NMDC-T-3481 | 1 - Approved
|  |  |  | 2 |  |  | T-578/25 | 2025-11-14
| HEA TITAN SET UP AT ZK-280 | 2800-AP-0215 | AD-306-PL-625001-SHT-001 | 1 |  | 2025-08-15 | T-417/25 | 2025-08-18 | 2025-08-22 | 2800-NMDC-E-AO-PMT-T-01640 | 2025-08-15 | 11681-NMDC-T-2903 | 1 - Approved
| JOPETWIL-215 SET UP AT ZK-43A | 2800-AP-0216 | AD-165-PL-625039-SHT-001 | 1 |  | 2025-08-15 | T-417/25 | 2025-08-18 | 2025-08-22 | 2800-NMDC-E-AO-PMT-T-01641 | 2025-12-10 | 11681-NMDC-T-3198 | 2 - Approved with Comments
| QMS AL SHAHAMA SET UP AT ZK-280 | 2800-AP-0217 | AD-306-PL-625002-SHT-001
| HEA TITAN SET UP AT ZK-56 | 2800-AP-0218 | AD-168-PL-625006-SHT-001
| SEP-550 SET UP AT ZK-280 | 2800-AP-0219 | AD-306-PL-625003-SHT-001 | 1 |  | 2025-08-15 | T-477/25 | 2025-09-16 | 2025-10-16 | 2800-NMDC-E-AO-PMT-T-01813 | 2025-09-14 | 11681-NMDC-T-2912 | 1 - Approved
| QMS CONQUEST SET UP AT ZK-277 | 2800-AP-0220 | AD-302-PL-625004-SHT-001
| SEP-550 SET UP AT ZK-277 | 2800-AP-0221 | AD-302-PL-625005-SHT-001 | 1 |  | 2025-08-15 | T-507/25 | 2025-10-01 | 2025-10-01 | 2800-NMDC-E-AO-PMT-T-01911 | 2025-09-29 | 11681-NMDC-T-2978 | 2 - Approved with Comments
| SEP-550 SET-UP AT ZK-293 | 2800-AP-0222 | AD-315-PL-625004-SHT-001 | 1 |  | 2025-08-15 | T-565/25 | 2025-11-06 | 2025-11-06 | 2800-NMDC-E-AO-PMT-T-02081 | 2026-02-09 | 11681-NMDC-T-3354 | 1 - Approved
| HEA KRAKEN SET UP AT ZK-47 | 2800-AP-0223 | AD-164-PL-625016-SHT-001 | 1 |  |  | T-596/25 | 2025-11-27 | 2025-12-04 | 2800-NMDC-E-AO-PMT-T-02170
|  |  |  | 1 |  |  | T-609/25 | 2025-12-05 | 2025-12-04 | 2800-NMDC-E-AO-PMT-T-02170 | 2025-12-10 | 11681-NMDC-T-3193 | 1 - Approved
| LOWER ZAKUM - JACKUP BARGE SETUP PLAN AND ANHCOR PATTERN AT ZK-14 | 2800-AP-0224 | AD-213-PL-625003-SHT-001
| SEP-550 SET-UP AT ZK-47 | 2800-AP-0225 | AD-164-PL-625018-SHT-001 | 1 |  | 2025-12-15 | T-607/25 | 2025-12-04 | 2025-12-10 | 2800-NMDC-E-AO-PMT-T-02184 | 2025-12-10 | 11681-NMDC-T-3193 | 1 - Approved
| QMS CONQUEST SET-UP DURING HOOK-UP WORKS AT ZK-3 | 2800-AP-0226 | AD-393-PL-625000-SHT-001 | 1 |  | 2025-12-15 | T-634/25 | 2025-12-23 | 2025-12-25 | 2800-NMDC-E-AO-PMT-T-02256
| HEA KRAKEN SET-UP @ ZK-307 FOR HOOK-UP WORKS | 2800-AP-0227 | AD-299-PL-625015-SHT-001 | 1 |  | 2026-01-20 | T-013/26 | 2026-01-09 | 2026-01-10 | 2800-NMDC-E-AO-PMT-T-02299 | 2026-01-16 | 11681-NMDC-T-3299 | 3 - Reviewed with Comments
|  |  |  | 2 |  |  | T-033/26 | 2026-01-23 | 2026-01-24 | 2800-NMDC-E-AO-PMT-T-02332 | 2026-02-09 | 11681-NMDC-T-3354 | 5 - Rejected
| HEA KRAKEN SET-UP @ ZK-44 FOR HOOK-UP WORKS | 2800-AP-0228 | AD-410-PL-625024-SHT-001 | 1 |  | 2026-01-20 | T-049/26 | 2026-02-04 | 2026-02-06 | 2800-NMDC-E-AO-PMT-T-02408 | 2026-02-06 | 11681-NMDC-T-3351 | 2 - Approved with Comments
| JOPETWIL-215 SET-UP DURING HOOK-UP WORKS AT ZK-329 | 2800-AP-0229 | AD-314-PL-625018-SHT-001 | 1 |  | 2026-01-20 | T-083/26 | 2026-02-23 | 2026-02-23 | 2800-NMDC-E-AO-PMT-T-02464 |  | 11681-NMDC-T-3415 | 1 - Approved
|  |  |  | 2 |  |  | T-153/26 | 2026-04-15 | 2026-04-16 | 2800-NMDC-E-AO-PMT-T-02599 | 2026-05-21 | 11681-NMDC-T-3576 | 1 - Approved
| HEA TITAN SETUP AT ZK-44 DURING HOOK-UP WORKS | 2800-AP-0230 | AD-410-PL-625025-SHT-001
| HEA KRAKEN SETUP AT ZK-14 DURING HOOK-UP WORKS | 2800-AP-0231 | AD-213-PL-625004-SHT-001
| HEA TITAN SET UP AT ZK-43A DURING HOOK UP WORKS | 2800-AP-0232 | AD-165-PL-625059-SHT-001 | 1 |  | 2026-01-20 | T-012/26 | 2026-01-09 | 2026-01-01 | 2800-NMDC-E-AO-PMT-T-02299 | 2026-01-16 | 11681-NMDC-T-3299 | 2 - Approved with Comments
| JOPETWIL-215 SET UP DURING HOOK UP WORKS AT ZK-3 | 2800-AP-0233 | AD-393-Z-000001-SHT-001 | 1 |  | 2026-01-20 | T-034/26 | 2026-01-25 | 2026-01-27 | 2800-NMDC-E-AO-PMT-T-02335 | 2026-02-04 | 11681-NMDC-T-3331 | 2 - Approved with Comments
| HEA TITAN SET-UP AT ZK-47 | 2800-AP-0234 | AD-164-Z-800012-SHT-001
| JOPETWIL-215 SET-UP AT ZK-280 | 2800-AP-0235 | AD-306-Z-800008-SHT-001
| JOPETWIL-215 SET-UP DURING HOOK-UP WORKS AT ZK-88 | 2800-AP-0236 | AD-174-Z-000001-SHT-001 | 1 |  | 2026-02-15 | T-095/26 | 2026-03-03 | 2026-03-04 | 2800-NMDC-E-AO-PMT-T-02486 | 2026-03-09 | 11681-NMDC-T-3413 | 1 - Approved
| QMS CONQUEST SET UP AT ZK-40 | 2800-AP-0237 | AD-407-Z-000001-SHT-001
| HEA TITAN SET UP AT ZCSC-NWIP | 2800-AP-0238 | AD-463-Z-800015-SHT-001 | 1 |  | 2026-04-30 | T-202/26 | 2026-05-11 | 2026-05-13 | 2800-NMDC-E-AO-PMT-T-02683 | 2026-06-10 | 11681-NMDC-T-3615 | 2 - Approved with Comments
|  |  |  | 2 |  | 2026-05-30 | T-227/26 | 2026-05-22 | 2026-05-22 | 2800-NMDC-E-AO-PMT-T-02719
|  |  |  | 3 |  |  | T-361/26 | 2026-08-21
| JOPETWIL-215 SETUP DURING HOOK-UP WORKS AT ZK-307 | 2800-AP-0239 | AD-299-Z-000002-SHT-001 | 1 |  | 2026-04-30 | T-169/26 | 2026-04-20 | 2026-04-21 | 2800-NMDC-E-AO-PMT-T-02612 | 2026-04-22 | 11681-NMDC-T-3525 | 1 - Approved
| QMS CONQUEST SET UP AT ZK-372 | 2800-AP-0240 | AD-313-Z-000002-SHT-001 | 1 |  | 2026-04-30 | T-184/26 | 2026-04-29 | 2026-04-30 | 2800-NMDC-E-AO-PMT-T-02651
| LOWER ZAKUM - CLV SETUP PLANS DURING LAYING OF HU-CL1 FROM ZK-44 TO ZK-126.5 | 2800-DP-0301 | AD-410-PL-625022-SHT-001 |  |  | 2025-04-01
| LOWER ZAKUM - CLV SETUP PLANS DURING LAYING OF HU-CL2 FROM ZK-126.5 TO ZK-43A | 2800-DP-0302 | AD-312-PL-625034-SHT-001 |  |  | 2025-04-01
| LOWER ZAKUM - CLV SETUP PLANS DURING LAYING OF HU-CL3 FROM ZK-43A TO WHT-2 | 2800-DP-0303 | AD-165-PL-625030-SHT-001 |  |  | 2025-04-01
| LOWER ZAKUM - CLV SETUP PLANS DURING LAYING OF HU-CL4 FROM ZK 329 TO ZK-307 | 2800-DP-0304 | AD-314-PL-625015-SHT-001 |  |  | 2025-04-01
| LOWER ZAKUM - CLV SETUP PLANS DURING LAYING OF HU-CL5 FROM ZK-307 TO ZK-88 | 2800-DP-0305 | AD-299-PL-625008-SHT-001 |  |  | 2025-04-01
| MP02 SETUP DURING SLEEPER INSTALLATION AT GL-1 CROSSING LOCATION | 2800-DP-0306
| MP02 SETUP DURING SLEEPER INSTALLATION AT GL-2 CROSSING LOCATION | 2800-DP-0307
| MP02 SETUP DURING SLEEPER INSTALLATION AT WI-3 CROSSING LOCATION | 2800-DP-0308
| MP02 SETUP DURING SLEEPER INSTALLATION AT WI-4 CROSSING LOCATION | 2800-DP-0309
| MP-01 SETUP AT ZK-372 | 2800-A3-036 |  |  |  | 2025-06-16
| MP-01 SETUP AT ZK-307 | 2800-A3-037 |  |  |  | 2025-06-16
| MP-01 SETUP AT ZK-88 | 2800-A3-042 |  |  |  | 2025-06-16
| MP-01 SETUP AT ZK-329 | 2800-A3-043 |  |  |  | 2025-06-16
| MP-01 SETUP AT ZK-47 | 2800-A3-044 |  |  |  | 2025-06-16
| MP-01 SETUP AT ZK-44 | 2800-A3-045 |  |  |  | 2025-06-16
| MP-01 SETUP AT ZK-126.5-65 | 2800-A3-046 |  |  |  | 2025-06-16
| MP-01 SETUP AT ZK-50 | 2800-A3-047 |  |  |  | 2025-06-16
| MP-01 SETUP AT ZWSC-GIP | 2800-A3-048 |  |  |  | 2025-06-16

## Sketches
|  | ADNOC OFFSHORE | [11 empty] | NMDC DOC. No.: MDR-001
ADNOC EPC for LZ HABSHAN UPPER RECOVERY LEKHWAIR+20 MPB PROJECT
|  | NPCC PROJECT NO. 2800 | [11 empty] | REVISION : | 0
|  | OFFSHORE sketches | [11 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC | [11 empty] | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| WORK BOAT (MUTAWA -101) ANCHOR PATTERN DURING FREE SPAN CORRECTION FOR GL-4 P/L | 2801-A1-010 |  | 0 |  |  | 2024-08-29
| SKETCH FOR PLB-648 ANCHOR PATTERN DURING RISER INSTALLATION AT ZWSC - GIP | 2800-A1-011 |  | 0 |  |  | 2024-09-06
| (SEP-450 at ZCSC-NWIP) | 2800-A3-006 |  | A |  |  | 2024-10-22
| (SEP-750 at ZK-280) | 2800-A3-007 |  | A |  |  | 2024-10-22
| (SEP-750 at ZK-47) | 2800-A3-008 |  | A |  |  | 2024-10-23
| 2800-A3-009_Rev-A (OML INTERVENTION-II at ZK126.5-65) | 2800-A3-009 |  | A |  |  | 2024-10-24
| ((SAFEEN PEARL POSITIONS DURING CL-2 CABLE LAYING) | 2800-A1-023 |  | 0 |  |  | 2024-12-04
| ((SAFEEN PEARL POSITIONS DURING CL- 3 CABLE LAYING) | 2800-A1-024 |  | 0 |  |  | 2024-12-04
| 2800-A1-0025_R0(DLB-750 AP during GL-4 Startup at ZK-45 with RIG ) | 2734-A0-036 |  | 0 |  |  | 2024-12-11
| 2800-A1-0026_R0(DLB-750 Setup during GL-3 Laydown at ZK-45 with RIG ) | 2800-A1-0026 |  | 0 |  |  | 2024-12-11
| OML INTERVENTION-II POSITION AT ZK-45 | 2800-A3-017 |  | A |  |  | 2025-01-06
| QMS GLADIATOR POSITION AT SK-45 | 2800-A3-018 |  | A |  |  | 2025-01-06
| QMS GLADIATOR POSITION AT ZK-43A | 2800-A3-016 |  | A |  |  | 2025-01-08
| QMS GLADIATOR POSITION AT ZCSC-NWIP | 2800-A3-019 |  | A |  |  | 2025-01-08
| QMS GLADIATOR at ZK-45 | 2800-A3-018 |  | A |  |  | 2025-01-08
| QMS GLADIATOR at ZK-45)-option. | 2800-A3-018 |  | A |  |  | 2025-01-08
| QMS GLADIATOR at ZK-56 | 2800-A3-020 |  | A |  |  | 2025-01-08
| SKETCHFOR DLB-1000 ANCHOR PATTERN AT NWIP | 2800-A1-027 |  | 0 |  |  | 2025-01-10
| (ZMI KRAKEN at ZK-47) | 2800-A3-021 |  | A |  |  | 2025-01-16
| (MUTAWA-11 at ZK-3) | 2800-A3-022 |  | A |  |  | 2025-01-17
| (ZMI KRAKEN at ZK-280)-Option-1 | 2800-A3-023 |  | A |  |  | 2025-01-17
| (ZMI KRAKEN at ZK-47)-Option-4 | 2800-A3-021 |  | A |  |  | 2025-01-17
| (ZMI KRAKEN at ZK-280)-Option-3 | 2800-A3-023 |  | A |  |  | 2025-01-17
| (ZMI KRAKEN at ZK-280)-Option-4 | 2800-A3-023 |  | A |  |  | 2025-01-20
| (MUTAWA-11 at ZK-40) | 2800-A3-024 |  | A |  |  | 2025-01-20
| (MUTAWA-11 at ZK-42).pdf | 2800-A3-025 |  | A |  |  | 2025-01-21
| 2800-A3-026-1 OF 2_Rev-A (MUTAWA-11 at ZK-44) | 2800-A3-026 |  | A |  |  | 2025-01-22
| (MUTAWA-11 at ZK-88) | 2800-A3-027 |  | A |  |  | 2025-01-23
| (HEA TITAN at ZK-56) | 2800-A3-029 |  | A |  |  | 2025-01-27
| (HEA TITAN at NWIP) | 2800-A3-030 |  | A |  |  | 2025-01-27
| (HEA TITAN at ZK-56) | 2800-A3-029 |  | B |  |  | 2024-01-30
| (HEA TITAN at NWIP) | 2800-A3-030 |  | B |  |  | 2024-01-30
| (HEA TITAN @ GIP) | 2800-A3-031 |  | A |  |  | 2024-01-30
| (HEA TITAN with CB at ZK-56) | 2800-A3-032 |  | A |  |  | 2024-01-30
| LOWER ZAKUM - CLV SETUP PLANS DURING LAYING OF HU-CL5 FROM ZK-307 TO ZK-88 | 2800-DP-0305 |  |  |  |  | 2025-04-01
| (PLB-648 AP during sleeper installation for GL-4) | 2800-A1-032 |  | 0 |  |  | 2025-02-03
| MP-01 Setup during sleeper installation for GL-4) | 2800-A1-033 |  | 0 |  |  | 2025-02-03
| (MP-01 Setup during sleeper installation at crossing location for WI-3 PL) | 2800-A3-033 |  | A |  |  | 2025-02-03
| (PLB-648 AP during 6 Inch GL(GL-1) start-up at ZWSC GIP) | 2800-A1-033 |  | 0 |  |  | 2025-02-05
| (PLB-648 AP during 6 Inch GL(GL-2) Start-up at ZK 50) | 2800-A1-0034 |  | 0 |  |  | 2025-05-06 | SKV
| (PLB-648 AP during 6 Inch GL(GL-3) startup at ZK 43A) | 2800-A1-0035 |  | 0 |  |  | 2025-02-10 | SKV
| (PLB-648 AP during Mattress installation at GL-4 crossing location) | 2800-A1-037 |  | 0 |  |  | 2025-02-13 | SKV
| (PLB-648 AP during 6 Inch GL(GL-4) startup at ZK 45) DMA OPTION | 2800-A1-0036 |  | 0 |  |  | 2025-02-13 | SKV
| (PLB-648 AP during Sleeper installation at GL-3 crossing location) | 2800-A1-038 |  | 0 |  |  | 2025-02-19 | SKV
| (MP-02 Setup during sleeper installation at crossing location for WI-3 PL) | 2800-A3-034 |  | A |  |  | 2025-02-19 | SKV
| (PLB-648 AP during sleeper installation for GL-4)-OPTION | 2800-A1-032 |  | 0 |  |  | 2025-02-19 | SKV
| (PLB-648 AP during 10 Inch WI PL (WI-3) startup at ZK 372) | 2800-A1-0039 |  | 0 |  |  | 2025-02-22 | SKV
| (PLB-648 AP during 10 Inch WI PL (WI-4) startup at ZK 126) | 2800-A1-0040 |  | 0 |  |  | 2025-02-22 | SKV
| (HEA TITAN at ZK-43A) As per Engg | 2800-A3-035 |  | A |  |  | 2025-02-25 | SKV
| (PLB-648 AP during riser installation at ZWSC GIP) | 2800-A1-011 |  | 1 |  |  | 2025-02-25 | SKV
| (MP-01 setup at ZK-372) | 2800-A3-036 |  | A |  |  | 2025-03-19 | SKV
| (MP-01 setup at ZK-307) | 2800-A3-037 |  | A |  |  | 2025-03-19 | SKV
| (HEA TITAN setup at ZK-45) | 2800-A3-038 |  | A |  |  | 2025-03-21 | SKV
| (HEA KRAKEN setup at ZK-126.5) | 2800-A3-039 |  | A |  |  | 2025-03-21 | SKV
| (CARGO BARGE MOORING BOUY LOCATIONS) | 2800-A1-044 |  | 0 |  |  | 2025-04-10 | EJJ
| (PLB-648 AP during sleeper installation at crossing location) | 2800-AP-0007 |  | 2 |  |  | 2025-04-26 | SKV
| (PLB-648 Aviation sketch during GL-3 sleeper installation) | 2800-A3-041 |  | A |  |  | 2025-05-01 | SKV
| (HEA TITAN at ZK-43A) | 2800-A3-035 |  | B |  |  | 2025-05-26 | SKV
| (PLB-648 AP during sleeper installation at GL-4 crossing location)_Total (Option-1) | 2800-AP-0008 |  | 1 |  |  | 2025-05-27 | SKV
| (PLB-648 AP during sleeper installation at GL-3 crossing location) | 2800-AP-0007 |  | 3 |  |  | 2025-05-28 | SKV
| PLB-648 ANCHOR PATTERN DURING RISER CLAMP INSTALLATION AT ZK-43A LOCATION | 2800-AP-0010 |  | 1 |  |  | 2025-05-30 | SKV
| PLB-648 ANCHOR PATTERN DURING RISER CLAMP INSTALLATION AT ZK-45 LOCATION | 2800-AP-0011 |  | 1 |  |  | 2025-05-30 | SKV
| PLB-648 ANCHOR PATTERN DURING RISER CLAMP INSTALLATION AT ZK-56 LOCATION | 2800-AP-0012 |  | 1 |  |  | 2025-05-30 | SKV
| (DLB-1000 AP during US-12B DECK Installation) | 2800-AP-0008 |  | A |  |  | 2025-06-02 | SKV
| (DLB-1000 AP during US-19B DECK Installation) | 2800-AP-0011 |  | A |  |  | 2025-06-02 | SKV
| 2800-A3-036_Rev-A (MP-01 setup at ZK-372) | 2800-A3-036 |  | A |  |  | 2025-06-05 | SKV
| 2800-A3-037_Rev-A (MP-01 setup at ZK-307) | 2800-A3-037 |  | A |  |  | 2025-06-05 | SKV
| 2800-A3-042_Rev-A (MP-01 Setup at ZK-88) | 2800-A3-042 |  | A |  |  | 2025-06-05 | SKV
| 2800-A3-043_Rev-A (MP-01 Setup at ZK-329) | 2800-A3-043 |  | A |  |  | 2025-06-05 | SKV
| 2800-A3-044_Rev-A (MP-01 Setup at ZK-47) | 2800-A3-044 |  | A |  |  | 2025-06-05 | SKV
| 2800-A3-045_Rev-A (MP-01 Setup at ZK-44) | 2800-A3-045 |  | A |  |  | 2025-06-05 | SKV
| 2800-A3-046_Rev-A (MP-01 Setup at ZK-126.5-65) | 2800-A3-046 |  | A |  |  | 2025-06-05 | SKV
| 2800-A3-047_Rev-A (MP-01 Setup at ZK-50) | 2800-A3-047 |  | A |  |  | 2025-06-05 | SKV
| 2800-A3-048_Rev-A (MP-01 Setup at ZWSC-GIP) | 2800-A3-048 |  | A |  |  | 2025-06-05 | SKV
| 2800-A3-049_Rev-A (JOPETWEL Setup at ZK-277) | 2800-A3-049 |  | A |  |  | 2025-06-09 | SKV
| 2800-A3-050_Rev-A (JOPETWEL Setup at ZK-307)-OPTION-2 | 2800-A3-050 |  | A |  |  | 2025-06-09 | SKV
| 2800-A3-051_Rev-A (JOPETWEL Setup at ZK-88) | 2800-A3-051 |  | A |  |  | 2025-06-09 | SKV
| 2800-A3-052_Rev-A (JOPETWEL Setup at ZK-329) | 2800-A3-052 |  | A |  |  | 2025-06-09 | SKV
| (PLB-648 AP during Riser Installation at ZK-45) | 2800-AP-0013 |  | A |  |  | 2025-06-11 | SKV
| (PLB-648 AP during Riser Clamp Installation at ZK-43A) - Option-3 | 2800-AP-0010 |  | 1 |  |  | 2025-06-11 | SKV
| (PLB-648 AP during WI-3 Pipelay from ZK-372 to ZK-47) | 2800-AP-0001 |  | 2 |  |  | 2025-06-12 | SKV
| (SWORDFISH SET-UP during Additional Mattress installation) | 2300-DP-0080 |  | C |  |  | 2025-06-17 | SKV
| (SWORDFISH SET-UP during Freespan Correction & Crossing Supports Installation & Initial Flooding) | 2300-DP-0081 |  | D |  |  | 2025-06-17 | SKV
| 2800-AP-0001-1 TO 2_R3 (PLB-648 AP during WI-3 Pipelay from ZK-372 to ZK-47) | 2800-AP-0001 |  | 3 |  |  | 2025-06-18 | SKV
| 2800-AP-0002-1 TO 2_R2 (PLB-648 AP during WI-4 Pipelay from ZK-126.5-65 to ZK-372) | 2800-AP-0002 |  | 2 |  |  | 2025-06-18 | SKV
| 2800-AP-0008-1 TO 5_R2(PLB-648 AP during sleeper installation at GL-4 crossing location)_Option-1 | 2800-AP-0008 |  | 2 |  |  | 2025-06-24 | SKV
| (PLB-648 AP during GL-1 Pipelay from ZWSC GIP to ZK-50) | 2800-AP-0003 |  | A |  |  | 2025-06-25 | SKV
| 2800-AP-0004-1 TO 3_R1 (PLB-648 AP during GL-2 Pipelay from ZK-50 to ZK-43A) | 2800-AP-0004 |  | 1 |  |  | 2025-06-28 | SKV
| 2800-AP-0005-1 TO 4_R1 (PLB-648 AP during GL-3 Pipelay from ZK-43A to ZK-45) | 2800-AP-0005 |  | 1 |  |  | 2025-07-03 | SKV
| 2800-A3-061_Rev-A (MP-01 Setup at ZK-43A) | 2800-A3-061 |  | A |  |  | 2025-08-06 | SKV
| 2800-A3-062_Rev-A (MP-02 Setup at ZK-329) | 2800-A3-062 |  | A |  |  | 2025-08-07 | SKV
| 2800-A3-046_Rev-A (MP-01 Setup at ZK-126.5-65) | 2800-A3-046 |  | A |  |  | 2025-08-07 | SKV
| 2800-A3-063_Rev-A (MP-02 Setup at ZK-126.5-65) | 2800-A3-063 |  | A |  |  | 2025-08-07 | SKV
| 2800-AP-0018_R1 (PLB-648 AP during GL-1 Riser installation at ZK-50) | 2800-AP-0018 |  | 1 |  |  | 2025-08-13 | SKV
| 2800-AP-0019_R1 (PLB-648 AP during GL-2 Riser installation at ZK-50) | 2800-AP-0019 |  | 1 |  |  | 2025-08-13 | SKV
| 2800-AP-0020_R1 (PLB-648 AP during GL-4 Riser installation at ZK-56) STB LIFTING | 2800-AP-0020 |  | 1 |  |  | 2025-08-13 | SKV
| 2800-AP-0003-1 TO 2_R1 (PLB-648 AP during GL-1 Pipelay from ZWSC GIP to ZK-50) | 2800-AP-0003 |  | 1 |  |  | 2025-08-18 | SKV
| 2800-AP-0004-1 TO 3_R4 (PLB-648 AP during GL-2 Pipelay from ZK-50 to ZK-43A) | 2800-AP-0004 |  | 4 |  |  | 2025-09-01 | SKV
| 2800-A3-067-1 TO 2_Rev-A (SAFEEN PEARL POSTION DURING CL-3 CABLE LAYDOWN AT ZK-43A) | 2800-A3-067 |  | A |  |  | 2025-09-02 | SKV
| 2800-A3-066-1 TO 2_Rev-A (SAFEEN PEARL POSTION DURING CL-2 CABLE LAYDOWN AT ZK-43A) | 2800-A3-066 |  | A |  |  | 2025-09-02 | SKV
| 2800-AP-0005-1 TO 4_R3 (PLB-648 AP during GL-3 Pipelay from ZK-43A to ZK-45) | 2800-AP-0005 |  | 3 |  |  | 2025-09-16 | SKV
| 2800-AP-0005-1 TO 4_R2 (PLB-648 AP during GL-3 Pipelay from ZK-43A to ZK-45) | 2800-AP-0005 |  | 2 |  |  | 2025-09-16 | SKV
| 2800-A3-070 & 071_Rev-A (SAFEEN PEARL POSTION DURING CL-2 CABLE START-UP AT ZK-43A AND LAYDOWN AT ZK-126.5-65) | 2800-A3-070 & 071 |  | A |  |  | 2025-09-19 | SKV
| 2800-A3-072& 073_Rev-A (SAFEEN PEARL POSTION DURING CL-3 CABLE START-UP AT ZK-43A AND LAYDOWN AT WHT-2) | 2800-A3-072 & 073 |  | A |  |  | 2025-09-19 | SKV
| 2800-A3-075_Rev-A (CL-3 CABLE LAYDOWN AT WHT-2) | 2800-A3-075 |  | A |  |  | 2025-09-24 | SKV
| 2800-AP-0024_R1 (PLB-648 AP during Stalk-on pipe joints at ZK-372) | 2800-AP-0024 |  | 1 |  |  | 2025-09-24 | SKV
| (SAFEEN PEARL POSTION DURING CL-2 CABLE LAYDOWN AT ZK-43A) | 2800-A3-066 |  | A |  |  | 2025-10-23 | SKV
| 2800-A3-087_Rev-A (SAFEEN PEARL POSTION DURING CL-2 CABLE START-UP AT ZK-126-5-65) | 2800-A3-087 |  | A |  |  | 2025-10-23 | SKV
| 2800-AP-0014_R2 (PLB-648 AP during WI-3 Pipeline shifting at ZK-47)-STUDY-2 | 2800-AP-0014 |  | 2 |  |  | 2025-11-26 | SKV
| 2800-A3-090-1 TO 3-Rev-B (HEA KRAKEN AVIATION CLEARANCE AT ZK-47) | 2800-A3-090 |  | B |  |  | 2025-12-16 | SKV
| 2800-A3-095-1 TO 3-Rev-A (SEP-550 AVIATION CLEARANCE AT ZK-47) | 2800-A3-095 |  | A |  |  | 2025-12-16 | SKV
| 2800-AP-0022_R3 (PLB-648 AP during GL-1 Riser installation at ZWSC-GIP) | 2800-AP-0022 |  | 3 |  |  | 2025-12-22 | SKV
| 2800-A3-097-1 TO 3-Rev-A (QMS CONQUEST AVIATION CLEARANCE AT ZK-3) | 2800-A3-097 |  | A |  |  | 2025-12-22 | EJJ
| 2800-AP-0210_R1(QMS CONQUEST SET-UP @ ZK-3 FOR HOOK-UP WORKS) | 2800-AP-0210 |  | 1 |  |  | 2025-12-22 | EJJ
| 2800-AP-0209_R1(HEA KRAKEN SET-UP @ ZK-307 FOR HOOK-UP WORKS) | 2800-AP-0209 |  | 1 |  |  | 2025-12-22 | EJJ
| 2800-A3-098-1 TO 3_Rev-A (SEP-550 AVIATION CLEARANCE AT ZK-307) | 2800-A3-098 |  | A |  |  | 2025-12-25 | SKV
| 2800-AP-0209_R1(SEP 550 DP SET-UP @ ZK-307 FOR HOOK-UP WORKS) | 2800-AP-0209 |  | 1 |  |  | 2025-12-25 | SKV
| 2800-AP-0025_R3 (PLB-648 AP during Module installation at ZK-47) | 2800-AP-0025 |  | 3 |  |  | 2025-12-26 | SKV
| 2800-A3-098-1 TO 3_Rev-A (SEP-550 AVIATION CLEARANCE AT ZK-307) | 2800-A3-098 |  | A |  |  | 2025-12-26 | SKV
| 2800-A3-100-1 TO 3_Rev-A (HEA KRAKEN AVIATION CLEARANCE AT ZK-307) | 2800-A3-100 |  | A |  |  | 2025-12-26 | SKV
| 2800-AP-0227_R1(HEA KRAKEN SET-UP @ ZK-307 FOR HOOK-UP WORKS) | 2800-AP-0227 |  | 1 |  |  | 2025-12-29 | EJJ
| 2800-A3-066-1 OF 2_Rev-B (SAFEEN PEARL POSTION DURING CL-2 CABLE LAYDOWN AT ZK-43A) | 2800-A3-066 |  | B |  |  | 2025-12-30 | SKV
| 2800-A3-087_Rev-A (SAFEEN PEARL POSTION DURING CL-2 CABLE START-UP AT ZK-126.5-65) | 2800-A3-087 |  | A |  |  | 2025-12-30 | SKV
| 2800-AP-0017_R1 (PLB-648 AP during GL-3 Riser Installation at ZK-43A)-With HEA TITAN & as Laid cable-Dt-10-02-26 | 2800-AP-0017 |  | 1 |  |  | 2026-02-10 | SKV
| PLB-648 AP during GL-1 Riser installation at ZWSC-GIP | 2800-AP-0022 |  | 4 |  |  | 2026-02-19 | VKS
| PLB-648 AP during GL-1 Riser installation at ZWSC-GIP | 2800-AP-0022 |  | 5 |  |  | 2026-02-20 | VKS
| 2800-A1-046_R0(HEA-TITAN ESCAPE ROUTE FROM ZK-43 TO ANCHORAGE) STUDY | 2800-A1-046 |  |  |  |  | 2026-03-03 | VKS
| (ORIENTAL DRAGON Passage plan from ANCHORAGE to ZULF 1340-1349) | 2302-A0-121 |  | 0 |  |  | 2026-03-03 | VKS
| ORIENTAL DRAGON setup plan during ICCP Cable installation at ZULF 1340-1349) | 2302-DP-0164 |  | A |  |  | 2026-03-03 | VKS
| 2800-AP-0025_R4 (PLB-648 AP during Module installation at ZK-47)-Dated on 13-4-26 | 2800-AP-0025 |  | 4 |  |  | 2026-04-13 | SKV
| 2800-AP-0203_R0 (SEP 550 AP during Hook-up works at ZK-50) | 2800-AP-0203 |  | 0 |  |  | 2026-05-14 | EJJ
| 2800-A3-118-1 TO 3_R0 (SEP 550 AP during Hook-up works at ZK-50)_Aviation sketches | 2800-A3-118 |  | 0 |  |  | 2026-05-14 | EJJ
| 2800-AP-0238_R2(HEA TITAN SETUP AT ZCSC-NWIP) | 2800-AP-0238 |  | 2 |  |  | 2026-05-20 | EJJ
| 2800-AP-0203_R0 (SEP 550 AP during Hook-up works at ZK-50) | 2800-AP-0203 |  | 0 |  |  | 2026-05-25 | EJJ
| 2800-AP-0212_R2 (HEA TITAN SETUP AT GIP) | 2800-AP-0212 |  | 2 |  |  | 2026-06-01 | EJJ
| 2800-AP-0018_R3 (PLB-648 AP during GL-1 Riser installation at ZK-50) | 2800-AP-0018 |  | 3 |  |  | 2026-06-11 | SKV
| 2800-AP-0019_R3 (PLB-648 AP during GL-2 Riser installation at ZK-50) | 2800-AP-0019 |  | 3 |  |  | 2026-06-11 | SKV
| 2800-AP-0027_R1 (PLB-648 AP during Module installation at ZK-50) | 2800-AP-0027 |  | 1 |  |  | 2026-06-11 | SKV
| 2800-AP-0018_R3 (PLB-648 AP during GL-1 Riser installation at ZK-50) | 2800-AP-0018 |  | 3 |  |  | 2026-06-12 | SKV
| 2800-AP-0019_R3 (PLB-648 AP during GL-2 Riser installation at ZK-50) | 2800-AP-0019 |  | 3 |  |  | 2026-06-12 | SKV
| 2800-AP-0027_R1 (PLB-648 AP during Module installation at ZK-50) | 2800-AP-0027 |  | 1 |  |  | 2026-06-12 | SKV
| 2800-A3-109_RevB (HEA TITAN AVIATION CLEARANCE AT GIP) | 2800-A3-109 |  | 1 |  |  | 2026-06-12 | EJJ
| 2800-AP-0212_R2 (HEA TITAN SETUP AT GIP) | 2800-AP-0212 |  | 2 |  |  | 2006-06-12 | EJJ
| 2800-A3-109_RevB (HEA TITAN AVIATION CLEARANCE AT GIP) | 2800-A3-109 |  | B |  |  | 2006-06-12 | EJJ
| 2800-AP-0031-1 TO 2_R1 (PLB-648 AP during Dog houses installation for GL-4 Pipelay from ZK-45 TO ZK-56) | 2800-AP-0031 |  | 1 |  |  | 2026-08-13 | SKV
| 2800-AP-0238_R3 (HEA TITAN SETUP AT ZCSC-NWIP) | 2800-AP-0238 |  | 3 |  |  | 2026-08-20 | EJJ
| 2800-AP-0013-1 OF 2_R2 (PLB-648 AP during GL-3 & 4 Riser Installation at ZK-45)-DRAFT | 2800-AP-0013 |  | 2 |  |  | 2026-08-31 | SKV