## Installation Procedures
NMDC DOC. No.: MDR-001
NMDC PROJECT NO. 2820 EPC FOR LOWER ZAKUM LTDP PHASE-1 (LZ LTDP-1)PACKAGE-4 OFFSHORE FACILITIES
[15 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [12 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | OFFSHORE INST PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[8 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[8 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[8 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| LOWER ZAKUM LDTP1 PACKAGE 4 - FREE SPANS CORRECTION & GROUT BAG INSTALLATION PROCEURE | 2820-PP-OF-018 | AD-27-G-03123 |  | 2 | 2026-09-02 | 2026-11-01
| LOWER ZAKUM LDTP1 PACKAGE 4 - SLEEPERS/MATTRESS/BLOCKS INSTALLATION PROCEDURES | 2820-PP-OF-019 | AD-27-G-03124 | A1 | subcontract Document |  |  | T-014/26
| LOWER ZAKUM LDTP1 PACKAGE 4 - PIPELINES INSTALLATION MANUAL | 2820-PP-OF-021 | AD-27-G-03126 | A1 |  | 2026-07-21 | 2026-09-19 | T-142/26
|  |  |  | 1 | 2 |  |  | T-244/26 | 2026-06-16 | 2026-06-17 | 2820-NMDC-E-AO-PMT-T-00803 | 2026-06-17 | LZ-LTDP-1-10222-PKG4-TN-06089 | 2 - Approved with Comments | 2026-06-16 | 2820-NMDC-E-PMT-MWS-T-00006 | 2026-06-22 | SAF234-MCE-NMDC-T-0002 | 1. Approved
|  |  |  | 2 |  |  |  | T-344/26 |  | 2026-08-18 | 2820-NMDC-E-AO-PMT-T-00987 |  |  |  | 2026-08-12 | 2820-NMDC-E-PMT-MWS-T-00033
| LOWER ZAKUM LDTP1 PACKAGE 4 - 11 KV COMPOSITE CABLE INSTALLATION PROCEDURE | 2820-PP-OF-022 | AD-27-G-03127 |  | 2 | 2027-02-11 | 2027-04-12
| LOWER ZAKUM LDTP1 PACKAGE 4 - FLANGED RISER INSTALLATION PROCEDURE | 2820-PP-OF-023 | AD-27-G-03128 |  | 2 | 2027-02-22 | 2027-04-23
| LOWER ZAKUM LDTP1 PACKAGE 4 - J-TUBE AND ASSOCIATED CLAMPS INSTALLATION PROCEDURE | 2820-PP-OF-024 | AD-27-G-03129 | A1 | 2 | 2026-08-24 | 2026-10-23 | T-277/26
| LOWER ZAKUM LDTP1 PACKAGE 4 - TOPSIDE INSTALLATION PROCEDURE FOR WELL HEAD PLATFORM | 2820-PP-OF-025 | AD-27-G-03130 |  | 2 | 2027-05-14 | 2027-07-13
| LOWER ZAKUM LDTP1 PACKAGE 4 - JACKET INSTALLATION PROCEDURE FOR WHT, BST AND FST | 2820-PP-OF-026 | AD-27-G-03131 | A1 | 2
|  |  |  | 1 | 2 |  |  | T-325/26 | 2026-07-30 | 2026-07-31 | 2820-NMDC-E-AO-PMT-T-00949 | 2026-08-21 | LZ-LTDP-1-10222-PKG4-TN-06436 | 2 - Approved with Comments | 2026-07-31 | 2820-NMDC-E-PMT-MWS-T-00026 |  | SAF234-MCE-NMDC-T-0015 | 3. Not Accepted
| LOWER ZAKUM LDTP1 PACKAGE 4 - BRIDGE, FLARE STACK MSF, FLARE TOWERS AND BRIDGE SUPPORT TOWER INSTALLATION PROCEDURE | 2820-PP-OF-027 | AD-27-G-03132 |  | 2 | 2028-05-20 | 2028-07-19
| LOWER ZAKUM LDTP1 PACKAGE 4 - PIPELINE PRECOMMISSIONING PROCEDURE - FLOODING, CLEANING, GAUGING AND HYDROTESTING PROCEDURE | 2820-PP-OF-028 | AD-27-G-03133 |  | 2 | 2027-05-07 | 2027-07-06
| LOWER ZAKUM LDTP1 PACKAGE 4 - PIPELINE PRECOMMISSIONING PROCEDURE - PIPELINE CALIPER AND INTELLIGENT PROCEDURE | 2820-PP-OF-034 | AD-27-G-03166 |  | 2 | 2027-06-07 | 2027-08-06
| LOWER ZAKUM LDTP1 PACKAGE 4 - PIPELINE PRECOMMISSIONING PROCEDURE - DEWATERING, DRYING AND NITROGEN PURGING PROCEDURE | 2820-PP-OF-035 | AD-27-G-03167 |  | 2 | 2027-06-07 | 2027-08-06
| LOWER ZAKUM LDTP1 PACKAGE 4 - ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | 2820-PP-OF-036 | AD-27-G-03168 | A1 |  | 2026-07-03 | 2026-09-01 | T-560/25
|  |  |  | 1 | 2 |  |  | T-241/26 | 2026-06-12 | 2026-06-16 | 2820-NMDC-E-AO-PMT-T-00800 |  |  |  | 2026-06-12 | 2820-NMDC-E-PMT-MWS-T-00003 | 2026-07-08 | SAF234-MCE-NMDC-T-0004 | 1. Approved
| LOWER ZAKUM LDTP1 PACKAGE 4 - ANCHOR HANDLING AND MOORING PROCEDURE FOR JACKUP BARGES | 2820-PP-OF-037 | AD-27-G-03169 | A1 | 2 | 2027-02-24 | 2027-04-25 | T-550/25
|  |  |  | 1 | 2 |  |  | T-247/26 | 2026-06-16 | 2026-06-17 | 2820-NMDC-E-AO-PMT-T-00804 | 2026-07-06 | LZ-LTDP-1-10222-PKG4-TN-05833 | 2 - Approved with Comments | 2026-06-16 | 2820-NMDC-E-PMT-MWS-T-00007 | 2026-06-22 | SAF234-MCE-NMDC-T-0002 | 1. Approved
| LOWER ZAKUM LDTP1 PACKAGE 4 - ANCHOR HANDLING PROCEDURE BY HAMMER HEAD CRANE VESSEL | 2820-PP-OF-038 | AD-27-G-03170 |  | 2 | 2027-02-24 | 2027-04-25
| LOWER ZAKUM LTDP-1 – SUBSEA FLANGE MANAGEMENT PROCEDURE | 2820-PP-OF-039 | AD-27-G-03171 | A1 | 2 | 2026-07-03 | 2026-09-01 | T-115/26
|  |  |  | 1 | 2 |  |  | T-239/26 | 2026-06-10 | 2026-06-12 | 2820-NMDC-E-AO-PMT-T-00794 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06248 | 1 - Approved | 2026-06-12 | 2820-NMDC-E-PMT-MWS-T-00004
| LOWER ZAKUM LDTP1 PACKAGE 4 - 132 KV COMPOSITE CABLE INSTALLATION PROCEDURE | 2820-PP-OF-040 | AD-27-G-03172 |  | 2 | 2027-06-16 | 2027-08-15
| LOWER ZAKUM LDTP1 PACKAGE 4 - J-TUBE INSTALLATION PROCEDURE | 2820-PP-OF-041 | AD-27-G-03173 |  | 2 | 2026-08-24 | 2026-10-23
| LOWER ZAKUM LDTP1 PACKAGE 4 - RISERS (STALK-ON) AND TIE IN SPOOL INSTALLATION PROCEDURE | 2820-PP-OF-042 | AD-27-G-03174 | A1 | 2 | 2027-02-22 | 2027-04-23
| LOWER ZAKUM LDTP1 PACKAGE 4 - MIDLINE TIE-IN INSTALLATION PROCEDURE | 2820-PP-OF-043 | AD-27-G-03175 |  | 2 | 2027-02-22 | 2027-04-23
| LOWER ZAKUM LDTP1 PACKAGE 4 - SUBSEA SPOOL INSTALLATION PROCEDURE | 2820-PP-OF-044 | AD-27-G-03176 |  | 2 | 2027-02-22 | 2027-04-23
| LOWER ZAKUM LDTP1 PACKAGE 4 - TOPSIDE AND BRIDGE INSTALLATION PROCEDURE FOR EAST RISER PLATFORM (ERP) | 2820-PP-OF-045 | AD-27-G-03177 |  | 2 | 2027-06-03 | 2027-08-02
| LOWER ZAKUM LDTP1 PACKAGE 4 - JACKET INSTALLATION PROCEDURE FOR EAST RISER PLATFORM | 2820-PP-OF-046 | AD-27-G-03178 |  | 2 | 2026-09-03 | 2026-11-02
| LOWER ZAKUM LDTP1 PACKAGE 4 - SUBSEA DIVE SURVEY PROCEDURE BY WORKBOAT | 2820-PP-OF-055 | AD-27-G-75142 | A1 | 2 | 2026-09-02 | 2026-11-01 | T-168/26
|  |  |  | 1 | 2 |  |  | T-309/26 | PMT D | 2026-07-24 | 2820-NMDC-E-AO-PMT-T-00936 | 2026-07-30 | LZ-LTDP-1-10222-PKG4-TN-06154 | 2 - Approved with Comments | 2026-07-24 | 2820-NMDC-E-PMT-MWS-T-00022
|  |  |  | 2 |  |  |  | T-375/26
| METHOD STATEMENT FOR INSTALLATION OF ANCHOR FRAMES AT THE AL OMAIRAH ISLAND (AOI) | 2820-PP-OF-065 |  | 1 |  | PMT CONSTRUCTION TEAM
Formulas:
SUBMISSION PLAN = [OFFSHORE INST PLAN]-60

## Setup Plans & Anchor Patterns
NMDC DOC. No.: MDR-001
NMDC PROJECT NO. 2820 EPC FOR LOWER ZAKUM LTDP PHASE-1 (LZ LTDP-1)PACKAGE-4 OFFSHORE FACILITIES
[15 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [12 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DRAWING NUMBER | REV. | CLASS | SUBMISSION PLAN | OFFSHORE INST PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[8 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[8 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[8 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE : | REF | DATE | REF | CODE
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL301 - 22" WF WHT EA-1 TO WHT EA-5 | 2820-AP-1001 | AD-27-Z-000126-SHT-001 | 1 | 2 | 2026-08-28 | 2026-09-27
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL302 - 14" WI WHT EA-5 TO WHT EA-1 | 2820-AP-1002 | AD-27-Z-000127-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL303 - 6" GL WHT EA-5 TO WHT EA-1 | 2820-AP-1003 | AD-27-Z-000128-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL305 - 22" WF WHT EA-5 TO WHT EA-2B | 2820-AP-1004 | AD-27-Z-000129-SHT-001 | 1 | 2 | 2026-08-21 | 2026-09-20
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL306 - 14" WI WHT EA-2B TO WHT EA-5 | 2820-AP-1005 | AD-27-Z-000130-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL307 - 6" GL WHT EA-2A TO WHT EA-5 | 2820-AP-1006 | AD-27-Z-000131-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL309 - 22" WF WHT EA-2A TO ERP AOI-ISLAND | 2820-AP-1007 | AD-27-Z-000132-SHT-001 | 1 | 2 | 2026-09-10 | 2026-10-10
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL310 - 14" WI ERP AOI-ISLAND TO WHT EA-2A | 2820-AP-1008 | AD-27-Z-000133-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL311 - 6" GL ERP AOI-ISLAND TO WHT EA-2A | 2820-AP-1009 | AD-27-Z-000134-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL317 - 20" WF WHT EA-6 TO WHT EA-4 | 2820-AP-1010 | AD-27-Z-000135-SHT-001 | 1 | 2 | 2026-08-16 | 2026-09-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL318 - 14" WI WHT EA-4 TO WHT EA-6 | 2820-AP-1011 | AD-27-Z-000136-SHT-001 | 1 | 2 | 2026-10-01 | 2026-10-31
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL319 - 6" GL WHT EA-4 TO WHT EA-6 | 2820-AP-1012 | AD-27-Z-000137-SHT-001 | 1 | 2 | 2026-10-06 | 2026-11-05
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL321 - 20" WF WHT EA-4 TO ERP AOI-ISLAND | 2820-AP-1013 | AD-27-Z-000138-SHT-001 | 1 | 2 | 2026-08-10 | 2026-09-09 | T-353/26 | 2026-08-18 | 2026-08-19 | 2820-NMDC-E-AO-PMT-01004 | 2026-08-26 | LZ-LTDP-1-10222-PKG4-TN-06478 | 3 - Reviewed with comments | 2026-08-19 | 2820-NMDC-E-PMT-MWS-T-00035
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL322 - 14" WI ERP AOI-ISLAND TO WHT EA-4 | 2820-AP-1014 | AD-27-Z-000139-SHT-001 | 1 | 2 | 2026-09-20 | 2026-10-20
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL323 - 6" GL ERP AOI-ISLAND TO WHT EA-4 | 2820-AP-1015 | AD-27-Z-000140-SHT-001 | 1 | 2 | 2026-09-25 | 2026-10-25
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL325 - 36" WG ERP AOI-ISLAND TO ZWSC-RP2 - SECTION-1 | 2820-AP-1016 | AD-27-Z-000141-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL325 - 36" WG ERP AOI-ISLAND TO ZWSC-RP2 - SECTION-2 | 2820-AP-1017 | AD-27-Z-000142-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL326 - 18" GE ERP AOI-ISLAND TO ZWSC-RP2 - SECTION-1 | 2820-AP-1018 | AD-27-Z-000143-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL326 - 18" GE ERP AOI-ISLAND TO ZWSC-RP2 - SECTION-2 | 2820-AP-1019 | AD-27-Z-000144-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL329 - 30" OE ERP AOI-ISLAND TO ZWSC-NRP - SECTION-1 | 2820-AP-1020 | AD-27-Z-000145-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL329 - 30" OE ERP AOI-ISLAND TO ZWSC-NRP - SECTION-2 | 2820-AP-1021 | AD-27-Z-000146-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL330 - 18" WF AGI WHT-1 TO ERP AOI-ISLAND | 2820-AP-1022 | AD-27-Z-000147-SHT-001 | 1 | 2 | 2026-08-03 | 2026-09-02 | T-353/26 | 2026-08-18 | 2026-08-19 | 2820-NMDC-E-AO-PMT-01004 | 2026-08-26 | LZ-LTDP-1-10222-PKG4-TN-06478 | 3 - Reviewed with comments | 2026-08-19 | 2820-NMDC-E-PMT-MWS-T-00035
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL331 - 6" GL ERP AOI-ISLAND TO AGI WHT-1 | 2820-AP-1023 | AD-27-Z-000148-SHT-001 | 1 | 2 | 2026-10-11 | 2026-11-10
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL334 - 6" GI WHT ZK-182 TO ERP AOI-ISLAND | 2820-AP-1024 | AD-27-Z-000149-SHT-001 | 1 | 2 | 2026-10-16 | 2026-11-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL335 - SECTION-1 38" WF ZCSC-CRP TO ERP AOI ISLAND - SECTION-1 | 2820-AP-1025 | AD-27-Z-000150-SHT-001 | 1 | 2 | 2026-09-15 | 2026-10-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL335 - SECTION-1 38" WF ZCSC-CRP TO ERP AOI ISLAND - SECTION-2 | 2820-AP-1026 | AD-27-Z-000151-SHT-001 | 1 | 2 | 2026-09-15 | 2026-10-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL337 - 6" GL AGI WHT-1 TO EPS-2 WHT-2 | 2820-AP-1027 | AD-27-Z-000152-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-750 DURING PIPELAY OF PL338 - 6" GL EPS-2 WHT-2 TO EPS-2 WHT-3 | 2820-AP-1028 | AD-27-Z-000153-SHT-001 | 1 | 2 | 2027-02-21 | 2027-03-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT EA-1 (PL301, PL302, PL303) | 2820-AP-1201 | AD-817-Z-000018-SHT-001 | 1 | 2 | 2027-05-22 | 2027-06-21
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT EA-5 (PL301, PL302, PL303) | 2820-AP-1202 | AD-821-Z-000018-SHT-001 | 1 | 2 | 2027-05-16 | 2027-06-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT EA-5 (PL305, PL306, PL307) | 2820-AP-1203 | AD-821-Z-000019-SHT-001 | 1 | 2 | 2027-05-16 | 2027-06-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT EA-2B (PL305, PL306, PL307) | 2820-AP-1204 | AD-874-Z-000019-SHT-001 | 1 | 2 | 2027-04-30 | 2027-05-30
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT EA-2A (PL309, PL310, PL311) | 2820-AP-1205 | AD-818-Z-000018-SHT-001 | 1 | 2 | 2027-04-30 | 2027-05-30
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT ERP (PL309, PL310, PL311, PL335) | 2820-AP-1206 | AD-3022-Z-000030-SHT-001 | 1 | 2 | 2027-03-24 | 2027-04-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT EA-6 (PL317, PL318, PL319) | 2820-AP-1207 | AD-822-Z-000018-SHT-001 | 1 | 2 | 2027-04-21 | 2027-05-21
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT EA-4 (PL317, PL318, PL319) | 2820-AP-1208 | AD-820-Z-000018-SHT-001 | 1 | 2 | 2027-04-15 | 2027-05-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT EA-4 (PL321, PL322, PL323) | 2820-AP-1209 | AD-820-Z-000019-SHT-001 | 1 | 2 | 2027-04-15 | 2027-05-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT ERP (PL321, PL322, PL323) | 2820-AP-1210 | AD-3022-Z-000031-SHT-001 | 1 | 2 | 2027-03-24 | 2027-04-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT ERP (PL325, PL326, PL329, PL330, PL331) | 2820-AP-1211 | AD-3022-Z-000032-SHT-001 | 1 | 2 | 2027-03-24 | 2027-04-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING RISER AND SPOOL INSTALLATION AT ZWSC-RP-2 (PL325, PL326) | 2820-AP-1212 | AD-812-Z-000010-SHT-001 | 1 | 2 | 2027-06-30 | 2027-07-30
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING RISER AND SPOOL INSTALLATION AT ZWSC-NRP (PL329) | 2820-AP-1213 | AD-417-Z-000005-SHT-001 | 1 | 2 | 2027-07-16 | 2027-08-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT AGI WHT-1 (PL330, PL331) | 2820-AP-1214 | AD-811-Z-000018-SHT-001 | 1 | 2 | 2027-03-31 | 2027-04-30
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT ERP (PL334) | 2820-AP-1215 | AD-3022-Z-000033-SHT-001 | 1 | 2 | 2027-03-24 | 2027-04-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING RISER AND SPOOL INSTALLATION AT ZK-182 (PL334) | 2820-AP-1216 | AD-324-Z-000009-SHT-001 | 1 | 2 | 2027-05-31 | 2027-06-30
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING RISER AND SPOOL INSTALLATION AT ZCSC-CRP (PL335) | 2820-AP-1217 | AD-496-Z-000029-SHT-001 | 1 | 2 | 2027-06-15 | 2027-07-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING SPOOL INSTALLATION AT AGI-WHT-1 (PL337) | 2820-AP-1218 | AD-811-Z-000019-SHT-001 | 1 | 2 | 2027-03-31 | 2027-04-30
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING RISER AND SPOOL INSTALLATION AT EPS-2 WHT-2 (PL337, PL338) | 2820-AP-1219 | AD-848-Z-000011-SHT-001 | 1 | 2 | 2027-07-21 | 2027-08-20
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING RISER AND SPOOL INSTALLATION AT EPS-2 WHT-3 (PL338) | 2820-AP-1220 | AD-849-Z-000011-SHT-001 | 1 | 2 | 2027-07-31 | 2027-08-30
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING MID TI-IN INSTALLATION FOR PL325 | 2820-AP-1221 | AD-27-Z-000154-SHT-001 | 1 | 2 | 2027-08-16 | 2027-09-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING MID TI-IN INSTALLATION FOR PL326 | 2820-AP-1222 | AD-27-Z-000155-SHT-001 | 1 | 2 | 2027-08-31 | 2027-09-30
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING MID TI-IN INSTALLATION FOR PL329 | 2820-AP-1223 | AD-27-Z-000156-SHT-001 | 1 | 2 | 2027-09-15 | 2027-10-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING MID TI-IN INSTALLATION FOR PL335 | 2820-AP-1224 | AD-27-Z-000157-SHT-001 | 1 | 2 | 2027-06-15 | 2027-07-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING JACKET INSTALLATION AT AGI WHT-1 | 2820-AP-1501 | AD-811-Z-000016-SHT-001 | 1 | 2 | 2026-10-03 | 2026-11-02
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING JACKET INSTALLATION AT WHT EA-4 | 2820-AP-1502 | AD-820-Z-000016-SHT-001 | 1 | 2 | 2026-10-18 | 2026-11-17
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING JACKET INSTALLATION AT WHT EA-5 | 2820-AP-1503 | AD-821-Z-000016-SHT-001 | 1 | 2 | 2026-11-16 | 2026-12-16
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING JACKET INSTALLATION AT WHT EA-6 | 2820-AP-1504 | AD-822-Z-000016-SHT-001 | 1 | 2 | 2026-11-01 | 2026-12-01
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING JACKET INSTALLATION AT ERP AOI ISLAND | 2820-AP-1505 | AD-3022-Z-000026-SHT-001 | 1 | 2 | 2027-02-07 | 2027-03-09
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING JACKET INSTALLATION AT WHT EA-1 | 2820-AP-1506 | AD-817-Z-000016-SHT-001 | 1 | 2 | 2027-03-05 | 2027-04-04
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING JACKET INSTALLATION AT WHT EA-2A | 2820-AP-1507 | AD-818-Z-000016-SHT-001 | 1 | 2 | 2027-01-31 | 2027-03-02
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING JACKET INSTALLATION AT WHT EA-2B | 2820-AP-1508 | AD-874-Z-000016-SHT-001 | 1 | 2 | 2027-02-17 | 2027-03-19
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING JACKET INSTALLATION AT BST-1 | 2820-AP-1509 | AD-3023-Z-000103-SHT-001 | 1 | 2 | 2027-10-31 | 2027-11-30
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING JACKET INSTALLATION AT BST-2 | 2820-AP-1510 | AD-3023-Z-000104-SHT-001 | 1 | 2 | 2027-11-08 | 2027-12-08
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING JACKET INSTALLATION AT BST-3 | 2820-AP-1511 | AD-3023-Z-000105-SHT-001 | 1 | 2 | 2027-11-16 | 2027-12-16
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING JACKET INSTALLATION AT BST-4 | 2820-AP-1512 | AD-3023-Z-000106-SHT-001 | 1 | 2 | 2027-11-24 | 2027-12-24
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING JACKET INSTALLATION AT FST-1 | 2820-AP-1513 | AD-3023-Z-000107-SHT-001 | 1 | 2 | 2027-12-02 | 2028-01-01
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR DLB-1000 DURING JACKET INSTALLATION AT FST-2 | 2820-AP-1514 | AD-3023-Z-000108-SHT-001 | 1 | 2 | 2027-12-10 | 2028-01-09
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR DLS-4200 DURING DECK INSTALLATION AT AGI WHT-1 | 2820-AP-1515 | AD-811-Z-000017-SHT-001 | 1 | 2 | 2027-06-13 | 2027-07-13
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR DLS-4200 DURING DECK INSTALLATION AT WHT EA-4 | 2820-AP-1516 | AD-820-Z-000017-SHT-001 | 1 | 2 | 2027-06-20 | 2027-07-20
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR DLS-4200 DURING DECK INSTALLATION AT WHT EA-5 | 2820-AP-1517 | AD-821-Z-000017-SHT-001 | 1 | 2 | 2027-07-13 | 2027-08-12
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR DLS-4200 DURING DECK INSTALLATION AT WHT EA-6 | 2820-AP-1518 | AD-822-Z-000017-SHT-001 | 1 | 2 | 2027-06-27 | 2027-07-27
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR DLS-4200 DURING DECK INSTALLATION AT ERP AOI ISLAND | 2820-AP-1519 | AD-3022-Z-000027-SHT-001 | 1 | 2 | 2027-07-03 | 2027-08-02
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR DLS-4200 DURING MODULE INSTALLATION AT ZWSC-RP-2 | 2820-AP-1520 | AD-812-Z-000009-SHT-001 | 1 | 2 | 2027-07-19 | 2027-08-18
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR SHEERLEG BARGE DURING DECK INSTALLATION AT WHT EA-1 | 2820-AP-1521 | AD-817-Z-000017-SHT-001 | 1 | 2 | 2027-08-27 | 2027-09-26
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR SHEERLEG BARGE DURING DECK INSTALLATION AT WHT EA-2A | 2820-AP-1522 | AD-818-Z-000017-SHT-001 | 1 | 2 | 2027-08-03 | 2027-09-02
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR SHEERLEG BARGE DURING DECK INSTALLATION AT WHT EA-2B | 2820-AP-1523 | AD-874-Z-000017-SHT-001 | 1 | 2 | 2027-08-14 | 2027-09-13
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING DECK INSTALLATION AT BST-1 | 2820-AP-1524 | AD-3023-Z-000109-SHT-001 | 1 | 2 | 2028-06-19 | 2028-07-19
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING DECK INSTALLATION AT BST-2 | 2820-AP-1525 | AD-3023-Z-000110-SHT-001 | 1 | 2 | 2028-06-22 | 2028-07-22
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING DECK INSTALLATION AT BST-3 | 2820-AP-1526 | AD-3023-Z-000111-SHT-001 | 1 | 2 | 2028-06-20 | 2028-07-20
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING DECK INSTALLATION AT BST-4 | 2820-AP-1527 | AD-3023-Z-000112-SHT-001 | 1 | 2 | 2028-06-23 | 2028-07-23
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING DECK INSTALLATION AT FST-1 | 2820-AP-1528 | AD-3023-Z-000113-SHT-001 | 1 | 2 | 2028-06-21 | 2028-07-21
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING DECK INSTALLATION AT FST-2 | 2820-AP-1529 | AD-3023-Z-000114-SHT-001 | 1 | 2 | 2028-06-24 | 2028-07-24
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR DLS-4200 DURING RB-01 BRIDGE INSTALLATION AT ERP AOI ISLAND | 2820-AP-1530 | AD-3022-Z-000028-SHT-001 | 1 | 2 | 2027-07-03 | 2027-08-02
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR DLS-4200 DURING RB-02 BRIDGE INSTALLATION AT ERP AOI ISLAND | 2820-AP-1531 | AD-3022-Z-000029-SHT-001 | 1 | 2 | 2027-07-03 | 2027-08-02
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR SHEERLEG BARGE DURING BRIDGE INSTALLATION AT WHT EA-2A EA-2B | 2820-AP-1532 | AD-874-Z-000018-SHT-001 | 1 | 2 | 2028-06-27 | 2028-07-27
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING FB-01 BRIDGE INSTALLATION AT BST-4-AOI ISLAND | 2820-AP-1533 | AD-3023-Z-000115-SHT-001 | 1 | 2 | 2028-06-30 | 2028-07-30
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING FB-02 BRIDGE INSTALLATION AT BST-2 -BST-4 | 2820-AP-1534 | AD-3023-Z-000116-SHT-001 | 1 | 2 | 2028-07-03 | 2028-08-02
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING FB-03 BRIDGE INSTALLATION AT BST-2 -FST-1 | 2820-AP-1535 | AD-3023-Z-000117-SHT-001 | 1 | 2 | 2028-07-06 | 2028-08-05
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET UP PLAN FOR SAFEEN-3000 DURING FB-04 BRIDGE INSTALLATION AT BST-2 -FST-2 | 2820-AP-1536 | AD-3023-Z-000118-SHT-001 | 1 | 2 | 2028-07-09 | 2028-08-08
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET-UP PLAN FOR UMM SHAIF DURING CABLE LAY OF CL-304 11KV ZK-50 TO AGI WHT-1 | 2820-AP-1701 | AD-27-Z-000158-SHT-001 |  | 2 | 2027-03-13 | 2027-04-12
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET-UP PLAN FOR UMM SHAIF DURING CABLE LAY OF CL-305 11KV AGI WHT-1 TO ZK-44 | 2820-AP-1702 | AD-27-Z-000159-SHT-001 |  | 2 | 2027-03-20 | 2027-04-19
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET-UP PLAN FOR UMM SHAIF DURING CABLE LAY OF CL-306 11KV ZK-24 TO WHT EA-4 | 2820-AP-1703 | AD-27-Z-000160-SHT-001 |  | 2 | 2027-03-27 | 2027-04-26
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET-UP PLAN FOR UMM SHAIF DURING CABLE LAY OF CL-307 11KV WHT EA-4 TO WHT EA-6 | 2820-AP-1704 | AD-27-Z-000161-SHT-001 |  | 2 | 2027-04-03 | 2027-05-03
| LOWER ZAKUM LTDP1 PACKAGE 4 - SET-UP PLAN FOR UMM SHAIF DURING CABLE LAY OF CL-308 11KV WHT EA-6 TO ZK26A | 2820-AP-1705 | AD-27-Z-000162-SHT-001 |  | 2 | 2027-04-10 | 2027-05-10
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR UMM SHAIF DURING CABLE LAY OF CL-309 11KV ZK-62 TO WHT EA-5 | 2820-AP-1706 | AD-27-Z-000163-SHT-001 |  | 2 | 2027-04-17 | 2027-05-17
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR UMM SHAIF DURING CABLE LAY OF CL-311 11KV WHT EA-5 TO WHT EA-1 | 2820-AP-1707 | AD-27-Z-000164-SHT-001 |  | 2 | 2027-04-24 | 2027-05-24
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR UMM SHAIF DURING CABLE LAY OF CL-312 11KV WHT EA-1 TO WHT EA-2B | 2820-AP-1708 | AD-27-Z-000165-SHT-001 |  | 2 | 2027-05-01 | 2027-05-31
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR UMM SHAIF DURING CABLE LAY OF CL-313 11KV WHT EA-2B TO ZK-33 | 2820-AP-1709 | AD-27-Z-000166-SHT-001 |  | 2 | 2027-05-08 | 2027-06-07
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR UMM SHAIF DURING CABLE LAY OF CL-3021 132KV AGI ISLAND TO ERP AOI ISLAND | 2820-AP-1710 | AD-27-Z-000167-SHT-001 |  | 2 | 2027-07-16 | 2027-08-15
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR UMM SHAIF DURING CABLE LAY OF CL-3022 132KV AGI ISLAND TO ERP AOI ISLAND | 2820-AP-1711 | AD-27-Z-000168-SHT-001 |  | 2 | 2027-07-31 | 2027-08-30
| LOWER ZAKUM LTDP1 PACKAGE 4 - ANCHOR PATTERN FOR UMM SHAIF DURING CABLE LAY OF CL-3033 132KV ERP AOI ISLAND TO ZCSC PDP | 2820-AP-1712 | AD-27-Z-000169-SHT-001 |  | 2 | 2027-08-15 | 2027-09-14
| LOWER ZAKUM LTDP1 PACKAGE 4 -SAFEEN-3000 AP DURING PIPELAYING OF 20 INCH WF PL321 | 2820-AP-1713 | Requested
| LOWER ZAKUM LTDP1 PACKAGE 4 -SAFEEN-3000 AP DURING PIPELAYING OF 20 INCH WF PL317 | 2820-AP-1714 | Requested
| JACKUP BARGES NEW DRAWWINGS | 2820-AP-1801
| WORK BOATS NEW DRAWINGS | 2820-AP-2001
Formulas:
SUBMISSION PLAN = [OFFSHORE INST PLAN]-30
OFFSHORE INST PLAN = [OFFSHORE INST PLAN, row above]+8

## Sketches
NMDC DOC. No.: MDR-001
EPC FOR LOWER ZAKUM LTDP PHASE-1 (LZ LTDP-1)PACKAGE-4 OFFSHORE FACILITIES
|  | NMDC PROJECT NO. 2820 | [6 empty] | REVISION : | 0
|  | OFFSHORE Sketches | [6 empty] | DATE : | 2026-09-08
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| (Das Island_working area for DLB-1000 & SAFEEN 3000) | 2820-A1-001 |  | 0 |  |  | 2025-04-15 | EJJ
| (DLB 750 AP PL-321)_START-UP AT G-ISLAND | 2820-A1-002 |  | 0 |  |  | 2025-08-21 | EJJ
| (DLB 750 AP PL-317)_START-UP @ WHT EA-4 | 2820-A1-003 |  | 0 |  |  | 2025-08-21 | EJJ
| (DLB 750 AP PL-320)_START-UP @ WHT EA-6 | 2820-A1-004 |  | 0 |  |  | 2025-08-21 | EJJ
| (DLB 750 AP PL-313)_START-UP @ WHT EA-6 | 2820-A1-005 |  | 0 |  |  | 2025-08-21 | EJJ
| 2820-A1-012_R5 - DLB-750 LAYDOWN PL-335 (38'') NEAR CRP | 2820-A1-012 |  | 5 |  |  | 2025-12-17 | SKV
| 2820-A1-015_R3 - DLB-750 START-UP PL-335 (38'') NEAR CRP-Option | 2820-A1-015 |  | 3 |  |  | 2025-12-17 | SKV
| 2820-A1-026-1 TO 2_R0(HEA KRAKEN setup @ ZCSC CRP) - Option 1 (Origianl PDP) | 2820-A1-026 |  | 0 |  |  | 2025-12-18 | SKV
| 2820-A1-027-1 TO 2_R0(HEA KRAKEN setup @ ZCSC CRP) | 2820-A1-027 |  | 0 |  |  | 2025-12-18 | SKV
| 2820-A1-028-1 TO 2_R0(HEA KRAKEN setup @ ZCSC CSP) | 2820-A1-028 |  | 0 |  |  | 2025-12-18 | SKV
| AL OMAIRAH ISLAND ANCHOR ATUDY STRUCTURE AND PIPELINE INSTALLATION (CAMPAIGN-1) | 2820-A1-038 |  | 0 |  |  | 2026-02-03 | SKV
| 2820-A1-006_R1 (DLS4200 AP study for ERP platform installation) | 2820-A1-006 |  | 1 |  |  | 2026-02-10 | SKV
| 2820-A1-019_R1 (DLB-1000 AP DURING EA-2B JKT INSTALLATION) | 2820-A1-019 |  | 1 |  |  | 2026-02-10 | SKV
| 2820-A1-020_R1 (DLB-1000 AP DURING EA-2A JKT INSTALLATION) | 2820-A1-020 |  | 1 |  |  | 2026-02-10 | SKV
| 2820-A1-024_R1 (DLB-1000 AP DURING EA-1 JKT INSTALLATION) | 2820-A1-024 |  | 1 |  |  | 2026-02-10 | SKV
| 2820-A1-039_R0 (HLV AP DURING AGI WHT-1 JKT INSTALLATION) | 2820-A1-039 |  | 0 |  |  | 2026-02-10 | SKV
| 2820-A1-040_R0 (HLV AP DURING EA-4 JKT INSTALLATION) | 2820-A1-040 |  | 0 |  |  | 2026-02-10 | SKV
| 2820-A1-041_R0 (HLV AP DURING EA-6 JKT INSTALLATION) | 2820-A1-041 |  | 0 |  |  | 2026-02-10 | SKV
| 2820-A1-042_R0 (HLV AP DURING EA-5 JKT INSTALLATION) | 2820-A1-042 |  | 0 |  |  | 2026-02-10 | SKV
| 2820-A1-043_R0 (SAFEEN-3000 AP DURING EA-5 JKT INSTALLATION) | 2820-A1-043 |  | 0 |  |  | 2026-02-10 | SKV
| 2820-A3-021-RevA (DLB-750 UKC at PL335-CR27) | 2820-A3-021 |  | A |  |  | 2026-02-10 | SKV
| 2820-A3-022-RevA (DLS-4200 UKC at PL335-CR27) | 2820-A3-022 |  | A |  |  | 2026-02-10 | SKV
| 2820-A1-044_R0 (DLS-4200 AP DURING ERP JKT INSTALLATION - SIDE LIFT) | 2820-A1-044 |  | 0 |  |  | 2026-02-12 | SKV
| 2820-A1-033-1 OF 2_R1(DLB 750 AP During PL-331 START-UP @ AOI-ERP) | 2820-A1-033 |  | 1 |  |  | 2026-03-25 | SKV
| 2820-A1-044_R2 (DLS-4200 AP DURING ERP JKT INSTALLATION - SIDE LIFT) | 2820-A1-044 |  | 2 |  |  | 2026-03-25 | SKV
| 2820-A1-045-1 TO 3_R1(ANCHOR POSITIONS AT AL OMAIRAH ISLAND) | 2820-A1-045 |  | 1 |  |  | 2026-03-25 | SKV
| 2820-A1-047_R0(DLB 750 AP During PL-330 START-UP @ AOI-ERP) | 2820-A1-047 |  | 0 |  |  | 2026-03-25 | SKV
| 2820-A1-002_R1(DLB 750 AP PL-321) 20 inch WF PL from EA4 TO AOI_START-UP | 2820-A1-002 |  | 1 |  |  | 2026-04-11 | EJJ
| 2820-A1-043_R1(SAFEEN-3000 AP DURING EA-5 JKT INSTALLATION) | 2820-A1-043 |  | 1 |  |  | 2026-05-14 | EJJ
| 2820-A1-051_R0(SAFEEN 3000 AP DURING AGI WHT-1 JKT INSTALLATION) | 2820-A1-051 |  | 0 |  |  | 2026-05-14 | EJJ
| 2820-A1-052_R0(SAFEEN-3000 SET-UP DURING EA-4 JKT INSTALLATION) | 2820-A1-052 |  | 0 |  |  | 2026-05-21 | EJJ
| 2820-A1-053_R0(SAFEEN-3000 SET-UP DURING EA-6 JKT INSTALLATION) | 2820-A1-053 |  | 0 |  |  | 2026-05-21 | EJJ
| 2820-A1-056_R0(DLS-4200 AP During RB-02 Bridge Installaion @ AOI-ERP) | 2820-A1-056 |  | 0 |  |  | 2026-06-12 | SKV
| 2820-A1-057_R0(DLS-4200 AP During RB-01 Bridge Installaion @ AOI-ERP) | 2820-A1-057 |  | 0 |  |  | 2026-06-12 | SKV
| 2820-AP-1022-1 TO 4_R1(DLB 750 AP during pipelaying of 18 inch WF PL330) | 2820-AP-1022 |  | 1 |  |  | 2026-07-07 | EJJ
| 2820-AP-1013-1 TO 4_R1(DLB 750 AP during pipelaying of 20 inch WF PL321) | 2820-AP-1013 |  | 1 |  |  | 2026-07-11 | EJJ
| 2820-AP-1010-1 TO 2_R1(DLB 750 AP during pipelaying of 20 inch WF PL317) | 2820-AP-1010 |  | 1 |  |  | 2026-07-20 | EJJ
| 2820-AP-1501_R1(SAFEEN-3000 AP DURING AGI WHT-1 JKT INSTALLATION) | 2820-AP-1501 |  | 1 |  |  | 2026-08-19 | EJJ