## Installation Procedures
|  | TAIWAN POWER COMPANY | [11 empty] | NMDC DOC. No.: MDR-001
TUNG-HSIAO POWER PLANT 2ND STAGE RENEWAL PROJECT TURN-KEY CONTRACT OF SUBSEA GAS PIPELINE
|  | NMDC PROJECT NO. 2913 | [11 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2026-05-20
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | TAIWAN POWER COMPANY OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO TAIWAN POWER COMPANY |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| PIPELINE INSTALLATION MANUAL | 2913-PP-OF-001 |  | A1 |  |  | T-608/25 | 2025-12-04
| OFFSHORE PIPELINE MIDLINE TIE-IN INSTALLATION | 2913-PP-OF-008 |  | A |  |  | T-118/26 | 2026-03-18
| ANCHOR HANDLING PROCEDURE | 2913-PP-OF-009 |  | A1 |  |  | T-583/25 | 2025-11-20
|  |  |  | B |  |  | T-626/25 | 2025-12-17
|  |  |  | C |  |  | T-067/26 | 2026-02-11
| OFFSHORE PIPELAY PROCEDURE | 2913-PP-OF-013 |  | A |  |  | T-048/26 | 2026-03-03

## Setup Plans & Anchor Patterns
|  | TAIWAN POWER COMPANY | [11 empty] | NMDC DOC. No.: MDR-001
TUNG-HSIAO POWER PLANT 2ND STAGE RENEWAL PROJECT TURN-KEY CONTRACT OF SUBSEA GAS PIPELINE
|  | NMDC PROJECT NO. 2913 | [11 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-05-20
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | TAIWAN POWER COMPANY OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO TAIWAN POWER COMPANY |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE : | REF | DATE | REF | CODE
| DLS 4200 ANCHOR PATTERN DURING LAYING OF PL-A (DURING PIPE-LAY AT TAICHUNG) | 2913-AP-0001 |  | B |  |  | T-061/26 | 2026-02-11
|  |  |  | c |  |  | T-120/26 | 2026-03-26

## Sketches
|  | TAIWAN POWER COMPANY | [6 empty] | NMDC DOC. No.: MDR-001
TUNG-HSIAO POWER PLANT 2ND STAGE RENEWAL PROJECT TURN-KEY CONTRACT OF SUBSEA GAS PIPELINE
|  | NMDC PROJECT NO. 2913 | [6 empty] | REVISION : | 0
|  | OFFSHORE Sketches | [6 empty] | DATE : | 2026-05-20
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| (DLS-4200 FLOATATION CHANNEL) | 2913-A1-002 |  |  |  |  | 2025-05-22 | SKV
| 2913-AP-0001-1 TO 3_R1( DLS 4200 setup plans and anchor Pattern during Laying of PL-A) | 2913-AP-0001 |  |  |  |  | 2026-01-08 | SKV
| 2913-A1-006_Rev-A (Additional overlength PIPE at Tung Hsiao) | 2913-A1-006 |  |  |  |  | 2026-01-22 | SKV
| 2913-AP-0001_1 TO 6_Rev-B (DLS 4200 AP during Laying of PL-A) | 2913-AP-0001 |  |  |  |  | 2026-01-22 | SKV