## Installation Procedures
NMDC DOC. No.: MDR-001
EPC FOR DALMA GAS DEVELOPMENT PROJECT
|  | NMDC PROJECT NO. 8405 | [11 empty] | REVISION : | 0
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2026-06-11
SR. NO. | DESCRIPTION | NMDC Energy DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
| PRE-ENGINEERING JACKET FACE DIVING SURVEY PROCEDURE | 8405-PP-OF-004 | CA0000-51-PRO-0019 | 1A |  | 2021-12-22 | T-547/21
|  |  |  | A01 |  |  | T-558/21 | 2021-12-27 | 2022-01-10 | 8405-ADNOC-UDR-TRL-0068 | 2022-01-25 | AD-NPCC-P4331432-00074 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-126/22 | 2022-04-05 | 2022-04-23 | 8405-ADNOC-UDR-TRL-0976 | 2022-05-11 | 8405-ADNOC-NPCC-TRL-00233 | 3 - No Comments
|  |  |  | 02 |  |  | T-144/23 | 2023-05-05 | 2023-05-09 | 8405-ADNOC-UDR-TRL-6244 | 2023-06-02 | 8405-ADNOC-NPCC-TRL-02094 | 3 - No Comments
| ANCHOR HANDLING PROCEDURE FOR GRAVITY ANCHORS BY HAMMER HEAD CRANE VESSEL | 8405-PP-OF-018 | CA0000-51-PRO-0026 | A |  |  | T-15522 | 2022-04-27 | 27-Apr-2022 | 8405-ADNOC-UDR-TRL-1019 | 2022-05-13 | 8405-ADNOC-NPCC-TRL-00241 | 3 - No Comments
|  |  |  | 01 |  |  | T-193/22 | 2022-05-19 | 2022-04-20 | 8405-ADNOC-UDR-TRL-1895 | 2022-07-05 | 8405-ADNOC-NPCC-TRL-00452 | 2 - Comments as noted
|  |  |  | 02 |  |  | T-285/22 | 2022-07-14 | 2022-07-21 | 8405-ADNOC-UDR-TRL-2311 | 2022-08-02 | 8405-ADNOC-NPCC-TRL-00561 | 3 - No Comments
| ANCHOR HANDLING AND MOORING PROCEDURE FOR WORK BOATS | 8405-PP-OF-019 | CA0000-51-PRO-0027 | A |  | 2022-05-23 | T-200/22
|  |  |  | A01 |  |  | T-202/22 | 2022-05-24 | 2022-05-25 | 8405-ADNOC-UDR-TRL-1404 | 2022-06-06 | 8405-ADNOC-NPCC-TRL-00334 | 3 - No Comments
|  |  |  | 01 |  |  | T-257/22 | 2022-02-23 | 2022-06-28 | 8405-ADNOC-UDR-TRL-2023 | 2022-07-07 | 8405-ADNOC-NPCC-TRL-00466 | 3 - No Comments
| ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | 8405-PP-OF-020 | CA0000-51-PRO-0028 | A |  | 2022-05-25 | T-207/22
|  |  |  | A01 |  |  | T-213/22 | 2022-05-27 | 2022-06-20 | 8405-ADNOC-UDR-TRL-1897 | 2022-07-05 | 8405-ADNOC-NPCC-TRL-00452 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-284/22 | 2022-07-13 | 2022-07-14 | 8405-ADNOC-UDR-TRL-2293 | 2022-07-28 | 8405-ADNOC-NPCC-TRL-00548 | 3 - No Comments
|  |  |  | 02 |  |  | T-290/23 | 2023-09-28 | 2023-10-02 | 8405-ADNOC-UDR-TRL-7547 | 2023-10-27 | 8405-ADNOC-NPCC-TRL-02874 | 3 - No Comments
| ANCHOR HANDLING AND MOORING PROCEDURE FOR JACK UP BARGES | 8405-PP-OF-021 | CA0000-51-PRO-0029 | A |  | 2022-06-03 | T-221/22
|  |  |  | A01 |  |  | T-240/22 | 2022-06-14 | 2022-06-16 | 8405-ADNOC-UDR-TRL-1858 | 2022-06-30 | 8405-ADNOC-NPCC-TRL-00440 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-280/22 | 2022-07-06 | 2022-07-14 | 8405-ADNOC-UDR-TRL-2294 | 2022-07-28 | 8405-ADNOC-NPCC-TRL-00548 | 3 - No Comments
| FREE SPANS CORRECTION PROCEURE | 8405-PP-OF-022 | CA0000-51-PRO-0030 | A |  | 2023-06-07 | T-176/23
|  |  |  | A01 |  |  | T-198/23 | 2023-07-03 | 2023-07-04 | 8405-ADNOC-UDR-TRL-6835 | 2023-10-06 | 8405-ADNOC-NPCC-TRL-02753 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-302/23 | 2023-10-10 | 2023-10-11 | 8405-ADNOC-UDR-TRL-7632 | 2023-10-20 | 8405-ADNOC-NPCC-TRL-02831 | 2 - Comments as noted | 2023-10-10 | 8405-NPCC-MWS-T-00007
|  |  |  | 01 |  |  | T-053/24 | 2024-02-08 | 2024-02-08 | 8405-ADNOC-UDR-TRL-8544 | 2024-02-28 | 8405-ADNOC-NPCC-TRL-03378 | 1 - Rejected | 2024-02-08 | 8405-NPCC-MWS-T-00079
|  |  |  | 02 |  |  | T-099/24 | 2024-03-01 | 2024-10-29 | 8405-ADNOC-UDR-TRL-9594 | 2024-11-15 | 8405-ADNOC-NPCC-TRL-04069 | 3 - No Comments
|  |  |  | 03 |  |  | T-446/24 | 2024-09-19 | 2024-10-29 | 8405-ADNOC-UDR-TRL-9594 | 2024-11-15 | 8405-ADNOC-NPCC-TRL-04069 | 3 - No Comments
| SLEEPERS AND MATTRESSES INSTALLATION PROCEDURE | 8405-PP-OF-023 | CA0000-51-PRO-0031 | A |  | 2022-12-06 | T-465/22
|  |  |  | A01 |  |  | T-489/22 | 2022-12-21 | 2022-12-22 | 8405-ADNOC-UDR-TRL-4766 | 2023-01-10 | 8405-ADNOC-NPCC-TRL-01352 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-249/23 | 2023-08-21 | 2023-08-22 | 8405-ADNOC-UDR-TRL-7248 | 2023-08-29 | 8405-ADNOC-NPCC-TRL-02545 | 3 - No Comments
|  |  |  | 01 |  |  | T-046/23 | 2023-02-01 | 2023-02-06 | 8405-ADNOC-UDR-TRL-5134 | 2023-03-10 | 8405-ADNOC-NPCC-TRL-01637 | 1 - Rejected
|  |  |  | 02 |  |  | T-105/23 | 2023-03-14 | 2023-03-17 | 8405-ADNOC-UDR-TRL-5646 | 2023-04-06 | 8405-ADNOC-NPCC-TRL-01755 | 2 - Comments as noted
|  |  |  | 03 |  |  | T-193/23 | 2023-06-23 | 2023-06-23 | 8405-ADNOC-UDR-TRL-6754 | 26-Jul-2023 | 8405-ADNOC-NPCC-TRL-02377 | 1 - Rejected
|  |  |  | 04 |  |  | T-231/23 | 2023-08-03 | 2023-08-03 | 8405-ADNOC-UDR-TRL-7135 | 2023-08-17 | 8405-ADNOC-NPCC-TRL-02473 | 2 - Comments as noted
| PIPELINE INFILL MATERIAL FIELD JOINT COATING PROCEDURE | 8405-PP-OF-024 | CA0000-51-PRO-0032
| PIPELINE ANTI-CORROSION FIELD JOINT COATING PROCEDURE | 8405-PP-OF-025 | CA0000-51-PRO-0033
| PIPELINES INSTALLATION MANUAL | 8405-PP-OF-026 | CA0000-51-MAN-0001 | A01 |  |  | T-011/23 | 2023-01-10 | 2023-01-16 | 8405-ADNOC-UDR-TRL-5027 | 2023-02-14 | 8405-ADNOC-NPCC-TRL-01518 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-147/23 | 2023-05-05 | 2023-05-08 | 8405-ADNOC-UDR-TRL-6232 | 2023-06-02 | 8405-ADNOC-NPCC-TRL-02094 | 1 - Rejected
|  |  |  | B02 |  |  | T-177/23 | 2023-06-09 | 2023-06-09 | 8405-ADNOC-UDR-TRL-6581 | 2023-06-21 | 8405-ADNOC-NPCC-TRL-02192 | 1 - Rejected
|  |  |  | B03 |  |  | T-190/23 | 2023-06-21 | 2023-06-22 | 8405-ADNOC-UDR-TRL-6724 | 2023-06-26 | 8405-ADNOC-NPCC-TRL-02238 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-230/23 | 2023-08-02 | 2023-08-02 | 8405-ADNOC-UDR-TRL-7129 | 2023-08-18 | 8405-ADNOC-NPCC-TRL-02477 | 3 - No Comments
|  |  |  | 02 |  |  | T-268/23 | 2023-09-08 | 2023-09-08 | 8405-ADNOC-UDR-TRL-7413 | 2023-09-21 | 8405-ADNOC-NPCC-TRL-02673 | 3 - No Comments
|  |  |  | 03 |  |  | T-277/23 | 2023-09-19 | PMT REJECTED
| UMBILICALS INSTALLATION PROCEDURE | 8405-PP-OF-027 | CA0000-51-PRO-0034 | A |  | 2023-05-18 | T-158/23
|  |  |  | A01 |  |  | T-189/23 | 2023-06-21 | 2023-07-03 | 8405-ADNOC-UDR-TRL-6753 | 2023-08-23 | 8405-ADNOC-NPCC-TRL-02510 | 1 - Rejected
|  |  |  | A02 |  |  | T-262/23 | 2023-09-04 | 2023-09-05 | 8405-ADNOC-UDR-TRL-7380 | 2023-09-21 | 8405-ADNOC-NPCC-TRL-02673 | 1 - Rejected
|  |  |  | A03 |  |  | T-285/23 | 2023-09-26 | 2023-09-26 | 8405-ADNOC-UDR-TRL-7528 | 2023-10-03 | 8405-ADNOC-NPCC-TRL-02729 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-293/23 | 2023-10-05 | 2023-10-06 | 8405-ADNOC-UDR-TRL-7585 | 2023-10-11 | 8405-ADNOC-NPCC-TRL-02771 | 3 - No Comments | 2023-10-05 | 8405-NPCC-MWS-T-00001
|  |  |  | 01 |  |  | T-054-24 | 2024-02-09 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8577 | 2024-02-28 | 8405-ADNOC-NPCC-TRL-03378 | 3 - No Comments | 2024-02-13 | 8405-NPCC-MWS-T-00084
| FIBER OPTIC CABLES INSTALLATION PROCEDURE | 8405-PP-OF-028 | CA0000-51-PRO-0035
| ARZANAH ISLAND PIPELINES SHORE PULL PROCEDURE | 8405-PP-OF-029 | CA0000-51-PRO-0036 | A |  | 2022-12-29 | T-496/22
|  |  |  | A01 |  |  | T-040/23 | 2023-01-31 | 2023-02-01 | 8405-ADNOC-UDR-TRL-5186 | 2023-02-24 | 8405-ADNOC-NPCC-TRL-01566 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-192/23 | 2023-06-22 | 23-Jun-2023 | 8405-ADNOC-UDR-TRL-6743 | 2023-07-19 | 8405-ADNOC-NPCC-TRL-02340 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-113/23 | 2023-03-24 | 2023-03-28 | 8405-ADNOC-UDR-TRL-5780 | 14-Apr-2023 | 8405-ADNOC-NPCC-TRL-01794 | 1 - Rejected
|  |  |  | 02 |  |  | T-145/23 | 2023-05-05 | 2023-05-08 | 8405-ADNOC-UDR-TRL-6233 | 2023-06-12 | 8405-ADNOC-NPCC-TRL-02138 | 1 - Rejected
|  |  |  | 03 |  |  | T-229/23 | 2023-08-01 | 2023-08-02 | 8405-ADNOC-UDR-TRL-7124 | 2023-08-18 | 8405-ADNOC-NPCC-TRL-02477 | 3 - No Comments
| ZIRKU ISLAND PIPELINES SHORE PULL PROCEDURE | 8405-PP-OF-030 | CA0000-51-PRO-0037 | A |  | 2023-01-31 | T-047/23
|  |  |  | A01 |  |  | T-057/23 | 2023-02-09 | 2023-02-13 | 8405-ADNOC-UDR-TRL-5325 | 2023-02-27 | 8405-ADNOC-NPCC-TRL-01570 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-191/23 | 2023-06-22 | 2023-06-23 | 8405-ADNOC-UDR-TRL-6744 | 2023-07-26 | 8405-ADNOC-NPCC-TRL-02376 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-117/23 | 2023-04-07 | 2023-04-10 | 8405-ADNOC-UDR-TRL-5944 | 2023-04-28 | 8405-ADNOC-NPCC-TRL-01873 | 1 - Rejected
|  |  |  | 02 |  |  | T-146/23 | 2023-05-05 | 2023-05-08 | 8405-ADNOC-UDR-TRL-6234 | 2023-06-12 | 8405-ADNOC-NPCC-TRL-02138 | 1 - Rejected
|  |  |  | 03 |  |  | T-238/23 | 2023-08-09 | 2023-08-10 | 8405-ADNOC-UDR-TRL-7182 | 2023-08-29 | 8405-ADNOC-NPCC-TRL-02545 | 2 - Comments as noted
|  |  |  | 04 |  |  | T-310/23 | 2023-10-18 | 2023-10-19 | 8405-ADNOC-UDR-TRL-7697 | 2023-10-23 | 8405-ADNOC-NPCC-TRL-02832 | 2 - Comments as noted | 2023-10-19 | 8405-NPCC-MWS-T-00013
| RISER (STALK-IN) INSTALLATION PROCEDURE | 8405-PP-OF-031 | CA0000-51-PRO-0038 | A |  | 2023-09-27 | T-288/23
|  |  |  | A01 |  |  | T-291/23 | 2023-10-02 | 2023-10-04 | 8405-ADNOC-UDR-TRL-7577 | 2023-10-25 | 8405-ADNOC-NPCC-TRL-02852 | 1 - Rejected
|  |  |  | A02 |  |  | T-328/23 | 2023-11-02 | 2023-11-02 | 8405-ADNOC-UDR-TRL-7850 | 2023-11-07 | 8405-ADNOC-NPCC-TRL-02933 | 2 - Comments as noted | 2023-11-02 | 8405-NPCC-MWS-T-00026
|  |  |  | B01 |  |  | T-355/23 | 2023-11-22 | 2023-11-22 | 8405-ADNOC-UDR-TRL-8014 | 2023-11-28 | 8405-ADNOC-NPCC-TRL-03031 | 3 - No Comments | 2023-11-22 | 8405-NPCC-MWS-T-00042
|  |  |  | 01 |  |  | T-060/24 | 2024-02-09 | 2024-03-15 | 8405-ADNOC-UDR-TRL-8801 | 2024-03-19 | 8405-ADNOC-NPCC-TRL-03431 | 3 - No Comments
| MID LINE SURFCAE TIE IN(s) INSTALLATION PROCEDURE | 8405-PP-OF-032 | CA0000-51-PRO-0039 | A |  | 2023-09-18 | T-275/23
|  |  |  | A01 |  |  | T-280/23 | 2023-09-20 | 2023-09-20 | 8405-ADNOC-UDR-TRL-7482 | 2023-10-26 | 8405-ADNOC-NPCC-TRL-02868 | 1 - Rejected
|  |  |  | A02 |  |  | T-329/23 | 2023-11-02 | 2023-11-02 | 8405-ADNOC-UDR-TRL-7848 | 2023-11-07 | 8405-ADNOC-NPCC-TRL-02933 | 2 - Comments as noted | 2023-11-02 | 8405-NPCC-MWS-T-00025
|  |  |  | B01 |  |  | T-346/23 | 2023-11-15 | 2023-11-02 | 8405-ADNOC-UDR-TRL-7949 | 2024-03-19 | 8405-ADNOC-NPCC-TRL-03429 |  | 2023-11-15 | 8405-NPCC-MWS-T-00035
|  |  |  | 01 |  |  | T-132/24 | 2024-03-22 | 2024-03-22 | 8405-ADNOC-UDR-TRL-8838 | 2024-04-02 | 8405-ADNOC-NPCC-TRL-03483 | 3 - No Comments
| J-TUBE AND ASSOCIATED CLAMPS INSTALLATION PROCEDURE | 8405-PP-OF-033 | CA0000-51-PRO-0040 | A |  | 2022-12-09 | T-475/22
|  |  |  | A01 |  |  | T-490/22 | 2022-12-21 | 2022-12-23 | 8405-ADNOC-UDR-TRL-4797 | 2023-01-12 | 8405-ADNOC-NPCC-TRL-01366 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-041/23 | 2023-01-31 | 2023-02-01 | 8405-ADNOC-UDR-TRL-5188 | 2023-03-10 | 8405-ADNOC-NPCC-TRL-01637 | 1 - Rejected
|  |  |  | 02 |  |  | T-109/23 | 2023-03-16 | 2023-03-20 | 8405-ADNOC-UDR-TRL-5682 | 2023-04-13 | 8405-ADNOC-NPCC-TRL-01786 | 2 - Comments as noted
|  |  |  | 03 |  |  | T-170/23 | 2023-06-02 | 2023-06-14 | 8405-ADNOC-UDR-TRL-6645 | 2023-08-18 | 8405-ADNOC-NPCC-TRL-02477A | 3 - No Comments
|  |  |  | 04 |  |  | T-338/23 | 2023-11-09 | 2023-11-07 | 8405-ADNOC-UDR-TRL-7891 | 2023-11-09 | 8405-ADNOC-NPCC-TRL-02943 | 3 - No Comments | 2023-11-07 | 8405-NPCC-MWS-T-00031
|  |  |  | 05 |  |  | T-404/24 | 2024-09-05 | 2024-09-11 | 8405-ADNOC-UDR-TRL-9479 | 2024-10-14 | 8405-ADNOC-NPCC-TRL-03996 | 3 - No Comments
|  |  |  | 06 |  |  | T-534/24 | 2024-11-02 | 2024-11-24 | 8405-ADNOC-UDR-TRL-9663 | 2024-12-16 | 8405-ADNOC-NPCC-TRL-04128 | 3 - No Comments | 2024-11-24 | 8405-NPCC-MWS-T-00169
| INSTALLATION PROCEDURE FOR NEW DECKS BH-03, WHP-10, HD-T4 AND HD-03 | 8405-PP-OF-034 | CA0000-51-PRO-0041 | A |  | 2024-02-20 | T-091/24
|  |  |  | A01 |  |  | T-097/24 | 2024-02-29 | 2024-02-29 | 8405-ADNOC-UDR-TRL-8707 | 2024-03-22 | 8405-ADNOC-NPCC-TRL-03443 | 1 - Rejected | 2024-02-29 | 8405-NPCC-MWS-T-00089
|  |  |  | A02 |  |  | T-245/24 | 2024-06-07 | 11-Jun-2024 | 8405-ADNOC-UDR-TRL-9228 | 2024-06-26 | 8405-ADNOC-NPCC-TRL-03740 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-324/24 | 2024-07-18 | 2024-07-18 | 8405-ADNOC-UDR-TRL-9363 | 2024-08-06 | 8405-ADNOC-NPCC-TRL-03846 | 2 - Comments as noted | 2024-07-18 | 8405-NPCC-MWS-T-00143
|  |  |  | B02 |  |  | T-343/24 | 2024-07-29 | 06-Aug-2024 | 8405-ADNOC-UDR-TRL-9416 | 05-Sep-2024 | 8405-ADNOC-NPCC-TRL-03904 | 3 - No Comments | 01-Aug-2024 | 8405-NPCC-MWS-T-00145
|  |  |  | 01 |  |  | T-047/25 | 2025-01-28 | 2025-01-30 | 8405-ADNOC-UDR-TRL-9769 | 2025-02-18 | 8405-ADNOC-NPCC-TRL-04218 | 3 - No Comments | 2025-01-30 | 8405-NPCC-MWS-T-00179
| NEW BHY-03 DECK INSTALLATION PROCEDURE | 8405-PP-OF-035 | CA0000-51-PRO-0042
| DEMOLITION OF EXISTING DECK AND NEW DECK INSTALLATION PROCEDURE | 8405-PP-OF-036 | CA0000-51-PRO-0043 | A |  | 2023-07-27 | T-226/23
|  |  |  | A01 |  |  | T-239/23 | 2023-08-10 | 2023-08-15 | 8405-ADNOC-UDR-TRL-7215 | 2023-09-01 | 8405-ADNOC-NPCC-TRL-02567 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-272/23 | 2023-09-12 | 2023-09-12 | 8405-ADNOC-UDR-TRL-7434 | 2023-09-22 | 8405-ADNOC-NPCC-TRL-02681 | 2 - Comments as noted
|  |  |  | B02 |  |  | T-289/23 | 2023-09-28 | 2023-10-02 | 8405-ADNOC-UDR-TRL-7546 | 2023-10-16 | 8405-ADNOC-NPCC-TRL-02797 | 2 - Comments as noted
|  |  |  | B03 |  |  | T-319/23 | 2023-10-25 | 2023-10-25 | 8405-ADNOC-UDR-TRL-7750 | 27-Oct-2023 | 8405-ADNOC-NPCC-TRL-02874 | 2 - Comments as noted | 2023-10-25 | 8405-NPCC-MWS-T-00019
|  |  |  | B04 |  |  | T-330/23 | 2023-11-02 | 2023-11-02 | 8405-ADNOC-UDR-TRL-7846 | 06-Nov-2023 | 8405-ADNOC-NPCC-TRL-02925 | 3 - No Comments | 2023-11-02 | 8405-NPCC-MWS-T-00024
|  |  |  | 01 |  |  | T-348/23 | 2023-11-15 | 2023-11-16 | 8405-ADNOC-UDR-TRL-7956 | 2023-11-20 | 8405-ADNOC-NPCC-TRL-02979 | 3 - No Comments | 2023-11-02 | 8405-NPCC-MWS-T-00036
| NEW HD-03 DECK INSTALLATION PROCEDURE | 8405-PP-OF-037 | CA0000-51-PRO-0044
| PIPELINES FLOODING, GAUGING, CLEANING AND HYDROTESTING PROCEDURE | 8405-PP-OF-038 | CA0000-51-PRO-0045 | A |  | 2024-01-11 | T-014/24
|  |  |  | A01 |  |  | T-015/24 | 2024-01-12 | 2024-01-13 | 8405-ADNOC-UDR-TRL-8369 | 2024-02-20 | 8405-ADNOC-NPCC-TRL-03347 | 1 - Rejected | 2024-01-13 | 8405-NPCC-MWS-T-00064
|  |  |  | A02 |  |  | T-105/24 | 2024-04-04 | 06-Mar-2024 | 8405-ADNOC-UDR-TRL-8737 | 2024-03-19 | 8405-ADNOC-NPCC-TRL-03427 | 1 - Rejected | 2024-03-04 | 8405-NPCC-MWS-T-00093
|  |  |  | A03 |  |  | T-207/24 | 2024-05-16 | 2024-05-20 | 8405-ADNOC-UDR-TRL-9106 | 2024-07-11 | 8405-ADNOC-NPCC-TRL-03778 | 3 - No Comments | 2024-05-20 | 8405-NPCC-MWS-T-00119
|  |  |  | B01 |  |  | T-017/25 | 2025-01-15 | 2025-01-16 | 8405-ADNOC-UDR-TRL-9747 | 2025-01-20 | 8405-ADNOC-NPCC-TRL-04188 | 1 - Rejected | 2025-01-16 | 8405-NPCC-MWS-T-00172
|  |  |  | B02 |  |  | T-037/25 | 2025-01-23 | 2025-01-27 | 8405-ADNOC-UDR-TRL-9756 | 2025-01-29 | 8405-ADNOC-NPCC-TRL-04199 | 3 - No Comments | 2025-01-27 | 8405-NPCC-MWS-T-00175
|  |  |  | 01 |  |  | T-075/25 | 2025-02-19 | 2025-03-01 | 8405-ADNOC-UDR-TRL-9798 | 2025-05-02 | 8405-ADNOC-NPCC-TRL-04309 | 3 - No Comments
|  |  |  | 02 |  |  | T-428/25 | 2025-08-26 | 2025-09-02 | 8405-ADNOC-UDR-TRL-9926 | 2025-09-08 | 8405-ADNOC-NPCC-TRL-04396 | 1 - Rejected
|  |  |  | 03 |  |  | T-469/25 | 2025-09-11 | 2025-09-12 | 8405-ADNOC-UDR-TRL-9940 | 2025-09-25 | 8405-ADNOC-NPCC-TRL-04408 | 1 - Rejected
|  |  |  | 04 |  |  | T-509/25 | 2025-10-03 | 2025-10-04 | 8405-ADNOC-UDR-TRL-9958 | 2025-10-30 | 8405-ADNOC-NPCC-TRL-04430 | 1 - Rejected
|  |  |  | 05 |  |  | T-532/25 |  | 2025-10-28 | 8405-ADNOC-UDR-TRL-9976 | 2025-11-05 | 8405-ADNOC-NPCC-TRL-04433 | 2 - Comments as noted
|  |  |  | 06 |  |  | T-567/25 |  | 2025-11-07 | 8405-ADNOC-UDR-TRL-9982 | 2025-12-03 | 8405-ADNOC-NPCC-TRL-04453 | 3 - No Comments
| UMBILICAL SHOREPULL, INSTALLATION & PULL IN THROUGH J-TUBE PROCEDURE | 8405-PP-OF-039 | CA0000-51-PRO-0046
| COMPOSITE CABLE SHOREPULL, INSTALLATION & PULL IN THROUGH J-TUBE PROCEDURE | 8405-PP-OF-040 | CA0000-51-PRO-0047 | A |  | 2023-06-15 | T-184/23
|  |  |  | A1 |  |  | T-212/23 | 2023-07-14 | 2023-07-17 | 8405-ADNOC-UDR-TRL-6964 | 2023-10-20 | 8405-ADNOC-NPCC-TRL-02831 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-320/23 | 2023-10-25 | 2024-01-02 | 8405-ADNOC-UDR-TRL-8284 | 16-Jan-2024 | 8405-ADNOC-NPCC-TRL-03212 | 3 - No Comments
|  |  |  | 01 |  |  | T-406/24 | 2024-09-05 | 2024-09-16 | 8405-ADNOC-UDR-TRL-9488 | 2024-10-15 | 8405-ADNOC-NPCC-TRL-03997 | 3 - No Comments | 2024-09-16 | 8405-NPCC-MWS-T-00158
|  |  |  | 02 |  |  | T-531/24 | 2024-10-29 | 2024-10-30 | 8405-ADNOC-UDR-TRL-9595 | 2024-11-15 | 8405-ADNOC-NPCC-TRL-04069 | 3 - No Comments
| PIPELINES DEWATERING, DRYING AND NITROGEN PURGING PROCEDURE | 8405-PP-OF-045 | CA0000-51-PRO-0051 | A |  | 2024-11-06 | T-540/24
|  |  |  | A01 |  |  | T-596/24 | 2024-12-20 | 2024-12-25 | 8405-ADNOC-UDR-TRL-9725 | 2025-05-02 | 8405-ADNOC-NPCC-TRL-04310 | 1 - Rejected | 2024-12-25 | 8405-NPCC-MWS-T-00171
|  |  |  | A02 |  |  | T-474/25 | 2025-09-15 | 2025-09-16 | 8405-ADNOC-UDR-TRL-9943 | 2025-09-29 | 8405-ADNOC-NPCC-TRL-04410 | 1 - Rejected
|  |  |  | A03 |  |  | T-566/25 |  | 2025-11-07 | 8405-ADNOC-UDR-TRL-9983 | 2026-01-22 | 8405-ADNOC-NPCC-TRL-04482 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-069/26 | 2026-02-12 | 2026-02-12 | 8405-ADNOC-UDR-TRL-10044 | 2026-03-23 | 8405-ADNOC-NPCC-TRL-04507 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-171/26 | 2026-04-21 | 2026-04-21 | 8405-ADNOC-UDR-TRL-10081
| CABLE TRANSPOOLIING PROCEDURE | 8405-PP-OF-046 | CA0000-51-PRO-0052
| UMBILICAL TRANSPOOLIING PROCEDURE | 8405-PP-OF-047 | CA0000-51-PRO-0053 | A |  | 2023-05-01 | T-142/23
|  |  |  | A01 |  |  | T-143/23 | 2023-05-03 | 2023-05-05 | 8405-ADNOC-UDR-TRL-6211 | 2023-05-17 | 8405-ADNOC-NPCC-TRL-01979 | 1 - Rejected
|  |  |  | A02 |  |  | T-160/23 | 2023-05-22 | 2023-05-22 | 8405-ADNOC-UDR-TRL-6406 | 02-Jun-2023 | 8405-ADNOC-NPCC-TRL-02094 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-174/23 | 2023-06-07 | 2023-06-06 | 8405-ADNOC-UDR-TRL-6538 | 2023-06-14 | 8405-ADNOC-NPCC-TRL-02150 | 2 - Comments as noted
|  |  |  | B02 |  |  | T-183/23 | 2023-06-14 | 2023-06-15 | 8405-ADNOC-UDR-TRL-6659 | 2023-07-10 | 8405-ADNOC-NPCC-TRL-02286 | 3 - No Comments
|  |  |  | 01 |  |  | T-209/23 | 2023-07-12 | 2023-07-12 | 8405-ADNOC-UDR-TRL-6930 | 2023-07-31 | 8405-ADNOC-NPCC-TRL-02389 | 3 - No Comments
| EXISTING JACKET ADDITIONAL EXTENSION INSTALLATION PROCEDURE & ASSOCISTED APPARATUS FOR HD03 | 8405-PP-OF-131 | HD0301-51-PRO-0001 | A |  | 2023-08-18 | T-247/23
|  |  |  | A01 |  |  | T-287/23 | 2023-09-27 | 2023-09-28 | 8405-ADNOC-UDR-TRL-7535 | 2023-10-17 | 8405-ADNOC-NPCC-TRL-02805 | 1 - Rejected
|  |  |  | A02 |  |  | T-318/23 | 2023-10-25 | 2023-10-25 | 8405-ADNOC-UDR-TRL-7746 | 2023-11-01 | 8405-ADNOC-NPCC-TRL-02904 | 2 - Comments as noted | 2023-10-25 | 8405-NPCC-MWS-T-00018
|  |  |  | B01 |  |  | T-331/23 | 2023-11-03 | 2023-11-03 | 8405-ADNOC-UDR-TRL-7859 | 2023-11-07 | 8405-ADNOC-NPCC-TRL-02933 | 3 - No Comments | 2023-11-03 | 8405-NPCC-MWS-T-00027
|  |  |  | 01 |  |  | T-349/23 | 2023-11-15 | 2023-11-16 | 8405-ADNOC-UDR-TRL-7957 | 2023-11-17 | 8405-ADNOC-NPCC-TRL-02974 | 3 - No Comments | 2023-11-16 | 8405-NPCC-MWS-T-00037
| METHOD STATEMENT FOR TRENCHING AND BACKFILLING (ARZANAH ISLAND) | 8405-PP-OF-133 | AZ0091-51-MES-0001 | A01 |  |  |  |  | 2023-07-18 | 8405-ADNOC-UDR-TRL-6994 | 2023-07-19 | 8405-ADNOC-NPCC-TRL-02338 | 3 - No Comments
|  |  |  | 01 |  |  | T-221/23 | 2023-07-19 | 2023-07-19 | 8405-ADNOC-UDR-TRL-7000 | 2023-08-01 | 8405-ADNOC-NPCC-TRL-02396 | 3 - No Comments
| METHOD STATEMENT FOR PRESETTING OF ANCHORS AT SHALLOW WATER BY DLB-750 | 8405-PP-OF-138 | CF0000-51-MES-0002 | A |  | 2023-08-11 | T-240/23
|  |  |  | A01 |  |  | T-243/23 | 2023-08-15 | 2023-08-15 | 8405-ADNOC-UDR-TRL-7208 | 2023-08-22 | 8405-ADNOC-NPCC-TRL-02494 | 1 - Rejected
|  |  |  | A02 |  |  | T-250/23 | 2023-08-23 | 2023-08-23 | 8405-ADNOC-UDR-TRL-7272 | 2023-09-08 | 8405-ADNOC-NPCC-TRL-02596 | 1 - Rejected
|  |  |  | 01 |  |  | T-219/26 | 2026-05-19 | 2026-05-18 | 8405-ADNOC-UDR-TRL-10106
| COMPOSITE CABLE (CC1) TRANSPOOLING PROCEDURE | 8405-PP-OF-144 | CF0000-51-PRO-0001 | A |  | 2023-09-18 | T-276/23
|  |  |  | A01 |  |  | T-283/23 | 2023-09-26 | 2023-09-26 | 8405-ADNOC-UDR-TRL-7526 | 2023-10-06 | 8405-ADNOC-NPCC-TRL-02751 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-298/23 | 2023-10-09 | 09-Oct-2023 | 8405-ADNOC-UDR-TRL-7613 | 2023-10-12 | 8405-ADNOC-NPCC-TRL-02784 | 3 - No Comments | 2023-10-09 | 8405-NPCC-MWS-T-00004
|  |  |  | 01 |  |  | T-061-24 | 2024-02-09 | 2023-10-09 | 8405-ADNOC-UDR-TRL-8552 | 2024-02-14 | 8405-ADNOC-NPCC-TRL-03325 | 3 - No Comments | 2024-02-09 | 8405-NPCC-MWS-T-00081
| METHOD OF STATEMENT FOR SEABED SURVEY FOR JACK-UP BARGE SETUP LOCATION | 8405-PP-OF-165 | CF0000-51-MES-0008 | A01 |  |  | T-058-24 | 2024-02-09 | 2024-02-09 | 8405-ADNOC-UDR-TRL-8550 | 2024-02-16 | 8405-ADNOC-NPCC-TRL-03340 | 2 - Comments as noted | 2024-02-09 | 8405-NPCC-MWS-T-00080
|  |  |  | B01 |  |  | T-090/24 | 2024-02-19 | 2024-02-19 | 8405-ADNOC-UDR-TRL-8642 | 2024-02-29 | 8405-ADNOC-NPCC-TRL-03382 | 3 - No Comments | 20-Feb-2024 | 8405-NPCC-MWS-T-00087
|  |  |  | 01 |  |  | T-218/26 | 2026-05-19 | 2026-05-18 | 8405-ADNOC-UDR-TRL-10107
| METHOD STATEMENT FOR PL-6 TRENCH AIR LIFT ACTIVITIES AT ZIKRU ISLAND | 8405-PP-OF-167 | AZ0091-51-MES-0002 | A01 |  |  | T-120-24 | 2024-03-17 | 2024-03-12 | 8405-ADNOC-UDR-TRL-8783 | 2024-03-19 | 8405-ADNOC-NPCC-TRL-03427 | 2 - Comments as noted | 2024-03-12 | 8405-NPCC-MWS-T-00095
|  |  |  | B01 |  |  | T-191/24 | 2024-05-08
| IGD-E NEW DECK EXTENSION INSTALLATION PROCEDURE | 8405-PP-OF-170 | KP3801-51-PRO-0008 | A |  | 2024-05-22 | T-215/24
|  |  |  | A01 |  |  | T-458/24 | 2024-09-24 | 2024-09-26 | 8405-ADNOC-UDR-TRL-9505 | 2024-10-16 | 8405-ADNOC-NPCC-TRL-04002 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-526/24 | 2024-10-25 | 2024-10-30 | 8405-ADNOC-UDR-TRL-9596 | 2024-11-15 | 8405-ADNOC-NPCC-TRL-04069 | 3 - No Comments
|  |  |  | 01 |  |  | T-279/25 | 2025-06-23 | 2025-06-26 | 8405-ADNOC-UDR-TRL-9889 | 2025-07-31 | 8405-ADNOC-NPCC-TRL-04366 | 3 - No Comments
|  |  |  | 02 |  |  | T-311/25 | 2025-07-02
| METHOD STATEMENT FOR SHIFTING OF UMBILICAL CABLES, UC-1 AND UC-4, AT ARZANAH ISLAND- EAST | 8405-PP-OF-171 | AZ0091-51-MES-0003 | PMT issued
| METHOD STATEMENT FOR J-TUBE SEAL ENGAGEMENT OF UMBILICALS | 8405-PP-OF-178 | CF0000-51-MES-0178 | A01 |  |  | T-452/25 | 2025-09-03 | 2025-09-03 | 8405-ADNOC-UDR-TRL-9932 | 2025-09-08 | 8405-ADNOC-NPCC-TRL-04397 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-500/25 |  | 2025-09-25 | 8405-ADNOC-UDR-TRL-9951 | 2025-10-28 | 8405-ADNOC-NPCC-TRL-04422 | 3 - No Comments
|  |  |  | 01 |  |  | T-196/26 | 2026-05-12 | 2026-05-12 | 8405-ADNOC-UDR-TRL-10101
| HYDROTEST TREATED SEA WATER DISPOSAL PLAN | 8405-PP-OF-200 | CF0000-51-PLN-0200 | A01 |  |  | T-419/25 | 2025-08-19 | 2025-08-20 | 8405-ADNOC-UDR-TRL-9920 | 2025-09-02 | 8405-ADNOC-NPCC-TRL-04391 | 2 - Comments as noted
|  |  |  | A02 |  |  | T-466/25 | 2025-09-10 | 2025-09-10 | 8405-ADNOC-UDR-TRL-9937 | 2025-09-25 | 8405-ADNOC-NPCC-TRL-04408 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-498/25 | 2025-10-23 | 2025-10-23 | 8405-ADNOC-UDR-TRL-9972 | 2025-10-31 | 8405-ADNOC-NPCC-TRL-04431 | 3 - No Comments
| PRE-COMMISSIONING SITE SURVEY REPORT FOR ARZANAH AND ZIRKU | 8405-PP-OF-202 | CF0000-51-REP-0202 | A01 |  |  | T-485/25 |  | 2025-09-22 | 8405-ADNOC-UDR-TRL-9947 | 2025-10-03 | 8405-ADNOC-NPCC-TRL-04412 | 4 - Information only
| PL-6 PIPELINE STUCK PIG CONTIGENCY ACTION PLAN AND METHOD STATEMENT | 8405-PP-OF-209 | CF0000-51-PRO-0209 | A01 |  | CANCELLED | T-030/26
| PIPELINES CONTIGENCY PLAN FOR STUCK PIG | 8405-PP-OF-211 | CA0000-51-PLN-0005 | A01 |  |  | T-192/26 | 2026-05-07 | 2026-05-14 | 8405-ADNOC-UDR-TRL-10103 | 2026-06-09 | mail from PMT | Code-1 – Rejected.

## Setup Plans & Anchor Patterns
NMDC DOC. No.: MDR-001
EPC FOR DALMA GAS DEVELOPMENT PROJECT
|  | NMDC PROJECT NO. 8405 | [11 empty] | REVISION : | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2026-06-11
SR. NO. | DESCRIPTION | NMDC Energy DRAWING NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | DATE | REF | DATE | REF | CODE | DATE : | REF | DATE | REF | CODE
| ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY AND SHORE PULL OF PL-1 (14'' PIPELINE FROM SATAH WHP-10 TO ARZANAH ISLAND - EAST) | 8405-AP-0001 | ST0101-34-LAY-0011 | A01 |  |  | T-011/24 | 2024-01-11 | 2024-01-11 | 8405-ADNOC-UDR-TRL-8362 |  | 8405-ADNOC-NPCC-TRL-03378 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-193/26 | 2026-05-07 | 2026-05-09 | 8405-ADNOC-UDR-TRL-10090
| ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY OF PL-2 (12" PIPELINE FROM HAIR DALMA HD-03 TO HAIR DALMA HD WHP-T4) | 8405-AP-0002 | HD0101-34-LAY-0002 | A01 |  |  | T-326/23 | 2023-10-31 | 2023-10-31 | 8405-ADNOC-UDR-TRL-7816 | 2023-11-16 | 8405-ADNOC-NPCC-TRL-02971 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-193/26 | 2026-05-07 | 2026-05-09 | 8405-ADNOC-UDR-TRL-10091
| ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY AND SHORE PULL OF PL-3 (16'' PIPELINE FROM HAIR DALMA HD WHP-T-4 TO ARZANAH ISLAND - SOUTH) | 8405-AP-0003 | HD0201-34-LAY-0003 | A01 |  |  | T-155/23 | 2023-05-15 | 2023-05-15 | 8405-ADNOC-UDR-TRL-6338 | 2023-06-14 | 8405-ADNOC-NPCC-TRL-02150 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-193/26 | 2026-05-07 | 2026-05-09 | 8405-ADNOC-UDR-TRL-10092
| ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY AND SHOREPULL OF PL-4 (16'' PIPELINE FROM BU HASEER BH-03 TO ARZANAH ISLAND - EAST) | 8405-AP-0004 | BH0091-34-LAY-0004 | A01 |  |  | T-113/24 | 2024-03-18 | NOT ISSUED
| ANCHOR PATTERN FOR BARGE DLB-750 DURING SHORE PULL AND PIPELAY OF PL-5 (24'' PIPELINE FROM ARZANAH ISLAND - EAST TO IGD-E) | 8405-AP-0005 | KP0091-34-LAY-0005 | A01 |  |  | T-361/23 | 2023-12-05 | 2024-01-11 | 8405-ADNOC-UDR-TRL-8097 | 2023-12-19 | 8405-ADNOC-NPCC-TRL-03100 | 3 - No Comments
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8557 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY OF PL-6 (6'' PIPELINE FROM ARZANAH ISLAND - EAST TO ZIRKU ISLAND) | 8405-AP-0006 | CF0091-34-LAY-0006 | A01 |  |  | T-251/23 | 2023-08-23 | 2023-08-24 | 8405-ADNOC-UDR-TRL-7277 | 2023-09-01 | 8405-ADNOC-NPCC-TRL-02563 | 1 - Rejected
|  |  |  | A02 |  |  | T-254/23 | 2023-08-29 | 2023-09-01 | 8405-ADNOC-UDR-TRL-7356 | 08-Sep-2023 | 8405-ADNOC-NPCC-TRL-02598 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-270/23 | 2023-09-12 | 2023-09-12 | 8405-ADNOC-UDR-TRL-7427 | 2023-10-03 | 8405-ADNOC-NPCC-TRL-02726 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING RISER INSTALLATION AT SATAH WHP-10 (14" RISER FOR (PL-1) P/L FROM ARZANAH ISLAND TO SATAH WHP-10) | 8405-AP-0008 | ST0101-34-LAY-0008 | A01 |  |  | T-336/24 | 2024-07-25 | 2024-07-25 | 8405-ADNOC-UDR-TRL-9375 | 2024-08-23 | 8405-ADNOC-NPCC-TRL-03867 | 1 - Rejected
| ANCHOR PATTERN FOR BARGE DLB-750 DURING RISER INSTALLATION AT HD-03 (12'' RISER FOR (PL-2) PIPELINE FROM HD-03 TO HD WHP-T4) | 8405-AP-0009 | HD0101-34-LAY-0009 | A01 |  |  | T-151/24 | 2024-04-03 | 2024-04-04 | 8405-ADNOC-UDR-TRL-8918 | 2024-05-06 | 8405-ADNOC-NPCC-TRL-03586 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING RISER INSTALLATION AT HD WHP-T4 (12'' RISER FOR (PL-2) PIPELINE FROM HD-03 TO HD WHP-T4) | 8405-AP-0010 | HD0101-34-LAY-0010 | A01 |  |  | T-303/23 | 2023-10-11 | 2023-10-12 | 8405-ADNOC-UDR-TRL-7651 | 2023-10-27 | 8405-ADNOC-NPCC-TRL-02874 | 2 - Comments as noted
| ANCHOR PATTERN FOR BARGE DLB-750 DURING RISER INSTALLATION AT HD WHP-T4 (16'' RISER FOR (PL-3) PIPELINE FROM SOUTH ARZANAH TO HD WHP-T4) | 8405-AP-0011 | AZ0091-34-LAY-0011 | A01 |  |  | T-303/23 | 2023-10-11 | 2023-10-12 | 8405-ADNOC-UDR-TRL-7652 | 2023-10-27 | 8405-ADNOC-NPCC-TRL-02874 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-341/23 | 2023-11-12 | 2023-11-09 | 8405-ADNOC-UDR-TRL-7904 | 2023-11-27 | 8405-ADNOC-NPCC-TRL-03027 | 2 - Comments as noted
| ANCHOR PATTERN FOR BARGE DLB-750 DURING RISER INSTALLATION AT WHP BH-03 (16'' RISER FOR (PL-4) PIPELINE FROM EAST ARZANAH ISLAND TO WHP BH-03) | 8405-AP-0012 | BH0101-34-LAY-0012 | A01 |  |  | T-242/24 | 2024-06-06 | 2024-06-07 | 8405-ADNOC-UDR-TRL-9206 | 2024-06-26 | 8405-ADNOC-NPCC-TRL-03737 | 3 - No Comments | 2024-06-07 | 8405-NPCC-MWS-T-00129
| ANCHOR PATTERN FOR BARGE DLB-750 DURING INSTALLATION OF 24'' CONDUIT FOR UC-3 (UMBLICAL FROM ARZANAH ISLAND-SOUTH TO HD WHP-T4) | 8405-AP-0015 | HD0091-34-LAY-0015 | A01 |  |  | T-151/23 | 2023-05-08 | 2023-05-15 | 8405-ADNOC-UDR-TRL-6242 | 2023-06-14 | 8405-ADNOC-NPCC-TRL-02150 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-193/26 | 2026-05-07 | 2026-05-09 | 8405-ADNOC-UDR-TRL-10093
| ANCHOR PATTERN FOR BARGE DLB-750 DURING INSTALLATION OF 24'' CONDUIT FOR UC-1 (UMBLICAL FROM ARZANAH ISLAND-EAST TO SATAH WHP-10) | 8405-AP-0016 | AZ0091-34-LAY-0016 | A01 |  |  | T-228/23 | 2023-07-28 | 2023-07-31 | 8405-ADNOC-UDR-TRL-7099 | 2023-08-15 | 8405-ADNOC-NPCC-TRL-02457 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-232/23 | 2023-08-03 | NOT ISSUED
| ANCHOR PATTERN FOR BARGE DLB-750 DURING INSTALLATION OF 24'' CONDUIT FOR UC-4 (UMBLICAL FROM ARZANAH ISLAND-EAST TO BH-3) | 8405-AP-0017 | ST0101-34-LAY-0017 | A01 |  |  | T-227/23 | 2023-07-28 | 2023-07-31 | 8405-ADNOC-UDR-TRL-7100 | 2023-08-15 | 8405-ADNOC-NPCC-TRL-02457 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-232/23 | 2023-08-03 | NOT ISSUED
| ANCHOR PATTERN FOR BARGE DLB-750 DURING INSTALLATION OF 16'' CONDUIT FOR CC-1 (COMPOSITE CABLE FROM ARZANAH ISLAND-EAST TO IGD-E) | 8405-AP-0018 | AZ0091-34-LAY-0018 | A01 |  |  | T-232/23 | 2023-08-03 | 2023-08-03 | 8405-ADNOC-UDR-TRL-7133 | 2023-08-10 | 8405-ADNOC-NPCC-TRL-02434 | 3 - No Comments
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8558 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY OF PL-3 FROM KP 31.50 TO 2.00 (16" PIPELINE FROM HAIR DELMA HD WHP-T4 TO ARZANAH ISLAND - SOUTH) | 8405-AP-0019 | AZ0091-34-LAY-0019 | A01 |  |  | T-168/23 | 2023-06-02 | 2023-06-02 | 8405-ADNOC-UDR-TRL-6498 | 26-Jun-2023 | 8405-ADNOC-NPCC-TRL-02223 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-196/23 | 2023-06-26 | 2023-07-03 | 8405-ADNOC-UDR-TRL-6817 | 2023-07-05 | 8405-ADNOC-NPCC-TRL-02265 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-202/23 | 2023-07-06 | 2023-07-06 | 8405-ADNOC-UDR-TRL-6858 | 2023-07-28 | 8405-ADNOC-NPCC-TRL-02386 | 2 - Comments as noted
| ANCHOR PATTERN FOR DLB-750 DURING TEMP. SUPPORT INSTALLATION AT CROSSING LOCATION PL-3-C1 | 8405-AP-0020 | CF0000-34-LAY-0020 | A01 |  |  | T-169/23 | 2023-06-05 | 2023-06-05 | 8405-ADNOC-UDR-TRL-6521 | 2023-06-22 | 8405-ADNOC-NPCC-TRL-02208 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-195/23 | 2023-06-26 | 2023-07-04 | 8405-ADNOC-UDR-TRL-6632 | 2023-07-17 | 8405-ADNOC-NPCC-TRL-02324 | 3 - No Comments
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8559 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR DLB-750 DURING TEMP. SUPPORT INSTALLATION AT CROSSING LOCATION PL-3-C2 | 8405-AP-0021 | CF0000-34-LAY-0021 | A01 |  |  | T-169/23 | 2023-06-05 | 2023-06-05 | 8405-ADNOC-UDR-TRL-6521 | 2023-06-22 | 8405-ADNOC-NPCC-TRL-02208 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-195/23 | 2023-06-26 | 2023-07-04 | 8405-ADNOC-UDR-TRL-6632 | 2023-07-17 | 8405-ADNOC-NPCC-TRL-02324 | 2 - Comments as noted
| ANCHOR PATTERN FOR DLB-750 DURING TEMP. SUPPORT INSTALLATION FOR SEABED CORRECTION AT KP 7.237. KP 7.257 & KP 7.655 | 8405-AP-0022 | CF0000-34-LAY-0022 | A01 |  |  | T-169/23 | 2023-06-05 | 2023-06-05 | 8405-ADNOC-UDR-TRL-6521 | 2023-06-22 | 8405-ADNOC-NPCC-TRL-02208 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-195/23 | 2023-06-26 | 04-Jul-2023 | 8405-ADNOC-UDR-TRL-6632 | 2023-07-17 | 8405-ADNOC-NPCC-TRL-02324 | 3 - No Comments
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8560 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR DLB-750 DURING TEMP. SUPPORT INSTALLATION FOR SEABED CORRECTION AT KP 21.68 & KP 21.186 | 8405-AP-0023 | CF0000-34-LAY-0023 | A01 |  |  | T-169/23 | 2023-06-05 | 2023-06-05 | 8405-ADNOC-UDR-TRL-6521 | 22-Jun-2023 | 8405-ADNOC-NPCC-TRL-02208 | 2 - Comments as noted
|  |  |  | B01 |  |  | T-195/23 | 2023-06-26 | 2023-07-04 | 8405-ADNOC-UDR-TRL-6632 | 2023-07-17 | 8405-ADNOC-NPCC-TRL-02324 | 3 - No Comments
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8561 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY OF PL-3 FROM KP 31.00 TO 2.00 (16" PIPELINE FROM HAIR DELMA HD WHP-T4 TO ARZANAH ISLAND - SOUTH) | 8405-AP-0025 | AZ0091-34-LAY-0025 | A01 |  |  | T-207/23 | 2023-07-11 | 2023-07-12 | 8405-ADNOC-UDR-TRL-6927 | 2023-08-15 | 8405-ADNOC-NPCC-TRL-02456 | 1 - Rejected
|  |  |  | A02 |  |  | T-207/23 | 2023-07-11 | 2024-08-21 | 8405-ADNOC-UDR-TRL-9450 | 2024-09-19 | 8405-ADNOC-NPCC-TRL-03932 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING SHOREPULL OF PL-1(14'' PIPELINE FROM SATAH WHP-10 TO ARZANAH ISLAND-EAST) | 8405-AP-0026 | AZ0091-34-LAY-0026 | A01 |  |  | T-232/23 | 2023-08-03 | 2023-08-03 | 8405-ADNOC-UDR-TRL-7133 | 2023-08-10 | 8405-ADNOC-NPCC-TRL-02434 | 3 - No Comments
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8562 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING SHOREPULL OF PL-4 (16'' PIPELINE FROM BU HASEER BH-03 TO ARZANAH ISLAND-EAST) | 8405-AP-0028 | AZ0091-34-LAY-0028 | A01 |  |  | T-232/23 | 2023-08-03 | 2023-08-03 | 8405-ADNOC-UDR-TRL-7133 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8563 | 3 - No Comments
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8563 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING SHOREPULL OF PL-5 (24'' PIPELINE FROM ARZANAH ISLAND EAST TO IGD-E) | 8405-AP-0029 | KP0091-34-LAY-0029 | A01 |  |  | T-232/23 | 2023-08-03 | 03-Aug-2023 | 8405-ADNOC-UDR-TRL-7133 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8564 | 3 - No Comments
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8564 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 SHORE PULL AND PIPELAY OF PL-6 FROM ZIRKU ISLAND TO KP 48.600 (6'' PIPELINE FROM ARZANAH ISLAND - EAST TO ZIRKU ISLAND) | 8405-AP-0030 | AZ0091-34-LAY-0030 | A01 |  |  | T-026/24 | 2024-01-18 | 2024-01-18 | 8405-ADNOC-UDR-TRL-8403 | 24-Jan-2024 | 8405-ADNOC-NPCC-TRL-03246 | 3 - No Comments | 2024-01-18 | 8405-NPCC-MWS-T-00069
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8565 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAYING OF PL-1 (14'' PIPELINE FROM SATAH WHP-10 TO ARZANAH ISLAND-EAST ) POST SHORE PULL UPTO KP 15.618 (1.2 KM FROM LFP) | 8405-AP-0031 | AZ0091-34-LAY-0031 | A01 |  |  | T-237/23 | 2023-08-09 | 2023-08-09 | 8405-ADNOC-UDR-TRL-7180 | 2023-08-22 | 8405-ADNOC-NPCC-TRL-02504 | 3 - No Comments
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8566 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING SHOREPULL OF PL-4 (16'' PIPELINE FROM BU HASEER BH-03 TO ARZANAH ISLAND- EAST) POST SHORE PULL UPTO KP 47.630 (1.2 KM FROM LFP) | 8405-AP-0032 | AZ0091-34-LAY-0032 | A01 |  |  | T-235/23 | 2023-08-08 | 2023-08-09 | 8405-ADNOC-UDR-TRL-7172 | 2023-08-22 | 8405-ADNOC-NPCC-TRL-02504 | 3 - No Comments
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8567 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING SHOREPULL OF PL-5 (24'' PIPELINE FROM ARZANAH ISLAND EAST TO IGD-E) POST SHORE PULL UPTO KP 1.200 (1.2 KM FROM LFP) | 8405-AP-0033 | AZ0091-34-LAY-0032 | A01 |  |  | T-235/23 | 2023-08-08 | NOT ISSUED
| ANCHOR PATTERN FOR BARGE UMM SHAIF DURING LAYING OF UC-1 FROM ARZANAH ISLAND TO WHP-10 | 8405-AP-0034 | ST0101-34-LAY-0034 | A01 |  |  | T-022/24 | 2024-01-17 | 2024-01-17 | 8405-ADNOC-UDR-TRL-8400 | 2024-02-08 | 8405-ADNOC-NPCC-TRL-03309 | 3 - No Comments | 17-Jan-2024 | 8405-NPCC-MWS-T-00066
|  |  |  | B01 |  |  | T-029/24 | 2024-01-22 | NOT ISSUED
|  |  |  | 01 |  |  | T-110/24 | 2024-03-06 | 2024-03-07 | 8405-ADNOC-UDR-TRL-8756 | 2024-03-20 | 8405-ADNOC-NPCC-TRL-03432 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE UMM SHAIF DURING LAYING OF UC-3 FROM SOUTH ARZANAH ISLAND TO WHP T4 | 8405-AP-0036 | HD0201-34-LAY-0036 | A01 |  |  | T-314/23 | 2023-10-23 | 2023-10-24 | 8405-ADNOC-UDR-TRL-7736 | 2023-11-10 | 8405-ADNOC-NPCC-TRL-02948 | 3 - No Comments
|  |  |  | B01 |  |  | T-354/23 | 2023-11-22 | 2023-11-22 | 8405-ADNOC-UDR-TRL-8010 | 2023-12-07 | 8405-ADNOC-NPCC-TRL-03059 | 3 - No Comments
|  |  |  | 01 |  |  | T-069/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8569 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE UMM SHAIF DURING LAYING OF UC-4 FROM ARZANAH ISLAND TO BH-03 | 8405-AP-0037 | BH0301-34-LAY-0037 | A01 |  |  | T-264/23 | 2023-09-05 | 2023-09-05 | 8405-ADNOC-UDR-TRL-7388 | 2023-09-21 | 8405-ADNOC-NPCC-TRL-02679 | 3 - No Comments
|  |  |  | B01 |  |  | T-300/23 | 2023-10-10 | NOT ISSUED
|  |  |  | 01 |  |  | T-304/23 | 2023-10-11 | 2023-10-13 | 8405-ADNOC-UDR-TRL-7659 | 2023-10-19 | 8405-ADNOC-NPCC-TRL-02818 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE UMM SHAIF DURING LAYING OF CC-1 FROM ARZANAH ISLAND TO IGD-E | 8405-AP-0038 | KP3801-34-LAY-0038 | A01 |  |  | T-036/24 | 2024-02-02 | 2024-02-02 | 8405-ADNOC-UDR-TRL-8498 | 2024-02-14 | 8405-ADNOC-NPCC-TRL-03325 | 3 - No Comments
|  |  |  | B01 |  |  | T-094/24 | 2024-02-26 | NOT ISSUED |  |  |  |  | 2024-02-02 | 8405-NPCC-MWS-T-00077
| ANCHOR PATTERN FOR BARGE DLB-750 DURING SHORE PULL OF PL-3 AND CONTINUE LAYING UPTO KP 31.000 (16'' PIPELINE FROM HAIR DALMA HD WHP-T4 TO ARZANAH ISLAND - SOUTH) | 8405-AP-0039 | KP3801-34-LAY-0039 | A01 |  |  | T-286/23 | 2023-09-27 | 2023-09-27 | 8405-ADNOC-UDR-TRL-7529 | 2023-10-12 | 8405-ADNOC-NPCC-TRL-02785 | 3 - No Comments
|  |  |  | 01 |  |  | T-068/24 | 2024-02-10 | 2024-02-13 | 8405-ADNOC-UDR-TRL-8568 | 2024-04-18 | 8405-ADNOC-NPCC-TRL-03516 | 3 - No Comments
| ANCHORE PATTERN FOR BARGE DLB-750 DURING PIPELAY OF PL-3 FROM (KP 2.000 TO KP 0.000) AT HD WHP-T4 (16" PIPELINE FROM HAIR DALMA HD WHP-T4 TO ARZANAH ISLAND - SOUTH | 8405-AP-0040 | ST0101-34-LAY-0040 | A01 |  |  | T-326/23 | 2023-10-31 | 2023-10-31 | 8405-ADNOC-UDR-TRL-7816 | 2023-11-16 | 8405-ADNOC-NPCC-TRL-02971 | 2 - Comments as noted
| ANCHOR PATTERN FOR BARGE DLB-750 DURING PL-6 MIDLINE TIE-IN AT KP 48.600 ( 6'' PIPELINE FROM ARZAHAH ISLAND EAST TO ZIRKU ISLAND) | 8405-AP-0044 | KP3801-34-LAY-0044 | A01 |  |  | T-030/24 | 2024-01-24 | 2024-01-24 | 8405-ADNOC-UDR-TRL-8443 | 2024-02-14 | 8405-ADNOC-NPCC-TRL-03325 | 3 - No Comments
| SAFEEN 3000 ANCHOR PATTERN DURING LIFTING AND INSTALLATION OF WHP-10 DECK | 8405-AP-0045 | ST0101-34-LAY-0045 | A01 |  |  | T-098/24 | 2024-02-29 | 2024-03-01 | 8405-ADNOC-UDR-TRL-8709 | 2024-03-01 | 8405-ADNOC-UDR-TRL-8709 | 1 - Rejected
|  |  |  | A02 |  |  | T-247/24 | 2024-06-07 | 2024-06-07 | 8405-ADNOC-UDR-TRL-9208 | 2024-07-08 | 8405-NPCC-ADNOC-TRL-02032 | 1 - Rejected
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING PL-3 MID LINE TIE-IN AT KP 31.00 (16" P/L FROM HAIR DALMA HD WHP-T4 TO ARZANAH ISLAND -SOUTH) | 8405-AP-0046 | CF0000-34-LAY-0046 | A01 |  |  | T-136/24 | 2024-03-22 | 2024-03-23 | 8405-ADNOC-UDR-TRL-8847 | 2024-04-30 | 8405-ADNOC-NPCC-TRL-03552 | 1 - Rejected
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING PL-5 RISER & TIE-IN INSTALLATION AT IGD-E (24" RISER FOR (PL-5) PIPELINE FROM EAST ARZANAH ISLAND TO IGD-E (AT KP-38)) | 8405-AP-0047 | KP3801-34-LAY-0047 | A01 |  |  | T-136/24 | 2024-03-22 | 2024-03-23 | 8405-ADNOC-UDR-TRL-8847 | 2024-04-30 | 8405-ADNOC-NPCC-TRL-03552 | 2 - Comments as noted
|  |  |  | A02 |  |  | T-448/24 | 2024-09-20 | 2024-09-20 | 8405-ADNOC-UDR-TRL-9498 | 2024-10-15 | 8405-ADNOC-NPCC-TRL-03998 | 2 - Comments as noted
|  |  |  | A03 |  |  | T-323/25 | 2025-07-03 | 2025-07-04 | 8405-ADNOC-UDR-TRL-9895 | 2025-07-04 | 8405-ADNOC-UDR-TRL-9895 | 3 - No Comments
|  |  |  | A04 |  |  | T-409/25 | 2025-08-13 | 2025-09-02 | 8405-ADNOC-UDR-TRL-9929 | 2025-09-02 | 8405-ADNOC-UDR-TRL-9929 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING PL-4 RISER & TIE-IN INSTALLATION AT BH-03 (16" RISER FOR (PL-4) PIPELINE FROM EAST ARZANAH ISLAND TO WHP BH-03) | 8405-AP-0048 | BH0301-34-LAY-0048 | A01 |  |  | T-136/24 | 2024-03-22 | 2024-03-23 | 8405-ADNOC-UDR-TRL-8847 | 2024-04-30 | 8405-ADNOC-NPCC-TRL-03552 | 2 - Comments as noted
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING PL-2 RISER & TIE-IN INSTALLATION AT HD-3 (12" RISER FOR (PL-2) PIPELINE FROM HD-03 TO HD WHP-T4) | 8405-AP-0049 | HD0201-34-LAY-0049 | A01 |  |  | T-136/24 | 2024-03-22 | 2024-03-23 | 8405-ADNOC-UDR-TRL-8847 | 2024-04-30 | 8405-ADNOC-NPCC-TRL-03552 | 2 - Comments as noted
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING PL-1 RISER & TIE-IN INSTALLATION AT WHP-10 (14" RISER FOR (PL1) PIPELINE FROM ARZANAH ISLAND TO SATAH WHP-10) | 8405-AP-0050 | ST0101-34-LAY-0050 | A01 |  |  | T-136/24 | 2024-03-22 | 2024-03-23 | 8405-ADNOC-UDR-TRL-8847 | 2024-04-30 | 8405-ADNOC-NPCC-TRL-03553 | 2 - Comments as noted
| DLB-1000 ANCHOR PATTERN DURING NEW DECK EXTENSION INSTALLATION AT IGD-E | 8405-AP-0051 | KP3801-34-LAY-0051 | A01 |  |  | T-454/24 | 2024-09-23 | 2024-09-24 | 8405-ADNOC-UDR-TRL-9503 | 2024-10-15 | 8405-ADNOC-NPCC-TRL-03998 | 2 - Comments as noted
|  |  |  | A02 |  |  | T-516/24 | 2024-10-21 | 2024-10-21 | 8405-ADNOC-UDR-TRL-9564 | 2024-11-08 | 8405-ADNOC-NPCC-TRL-04054 | 3 - No Comments
| DLS-4200 ANCHOR PATTERN DURING LIFTING AND INSTALLATION OF WHP-10 DECK | 8405-AP-0052 | ST0101-34-LAY-0052 | A01 |  |  | T-347/24 | 2024-08-01 | 2024-08-02 | 8405-ADNOC-UDR-TRL-9400 | 2024-08-22 | 8405-ADNOC-NPCC-TRL-03865 | 1 - Rejected | 2024-08-02 | 8405-NPCC-MWS-T-00149
|  |  |  | A02 |  |  | T-374/24 | 2024-08-17 | NOT ISSUED
| DLS-4200 AP DURING HD-03 DECK INSTALLATION | 8405-AP-0053 | HD0101-34-LAY-0053
| DLS-4200 AP DURING HD-T4 DECK INSTALLATION | 8405-AP-0054 | HD0201-34-LAY-0054
| DLS-4200 ANCHOR PATTERN DURING LIFTING AND INSTALLATION OF WHP-10 DECK | 8405-AP-0055 | CF0000-34-LAY-0055
| DLB-1000 ANCHOR PATTERN DURING FOC SPLICING AT PL-6 MID LINE TIE-IN AT KP 48.600 | 8405-AP-0056 | KP3801-34-LAY-0056 | A01 |  |  | T-430/24 | 2024-09-13 | 2024-09-16 | 8405-ADNOC-UDR-TRL-9489 | 2024-10-15 | 8405-ADNOC-NPCC-TRL-03998 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE DLB-750 DURING PL-3 MID LINE TIE-IN AT KP 31.00 (16'' PIPELINE FROM HAIR DALMA HD WHP-T4 TO ARZANAH ISLAND - SOUTH) | 8405-AP-0109 | CF0000-34-LAY-0109 | A01 |  |  | T-149/24 | 2024-04-02 | 2024-04-03 | 8405-ADNOC-UDR-TRL-8911 | 2024-05-06 | 8405-ADNOC-NPCC-TRL-03586 | 3 - No Comments
| ANCHOR PATTERN FOR BARGE SEP-650 DURING DECK EXTENSION INSTALLATION AT IGD-E (EAST SIDE) | 8405-AP-0110 | KP3801-34-LAY-0110 | A01 |  |  | T-052/24 | 2024-02-08 | 2024-02-08 | 8405-ADNOC-UDR-TRL-8336 | 2024-03-22 | 8405-ADNOC-NPCC-TRL-03441 | 1 - Rejected
|  |  |  | A02 |  |  | T-135/24 | 2024-03-21 | 2024-03-22 | 8405-ADNOC-UDR-TRL-8839 | 2024-05-03 | 8405-ADNOC-NPCC-TRL-03576 | 1 - Rejected
| BARGE SEP-650 SET-UP AT IGD-E (EAST SIDE) | 8405-AP-0112 | KP3801-34-LAY-0112 | A01 |  |  | T-198/24 | 2024-05-09 | 2024-05-10 | 8405-ADNOC-UDR-TRL-9072 | 2024-06-07 | 8405-ADNOC-NPCC-TRL-03695 | 2 - Comments as noted
| SEP-450 SETUP DRAWING AT WHP-10 FOR HOOKUP ACTIVITIES | 8405-AP-0113 | ST0101-34-LAY-0113 | A01 |  |  | T-405/24 | 2024-09-05 | 2024-09-06 | 8405-ADNOC-UDR-TRL-9472 | 2024-09-24 | 8405-ADNOC-NPCC-TRL-03943 | 1 - Rejected
| SEP-650 DP SETUP DURING PRESERVATION ACTIVITIES AT WHP-10 | 8405-AP-0114 | ST0101-34-LAY-0114 | A01 |  |  | T-471/24 | 2024-09-26 | NOT ISSUED
|  |  |  | A02 |  |  | T-491/24 | 2024-10-04 | NOT ISSUED
| SEP-650 DP SET-UP DURING HOOK UP ACTIVITIES AT HD-T4 | 8405-AP-0116 | HD0201-34-LAY-0116 | A01 |  |  | T-088/25 | 2025-03-03 | 2025-03-05 | 8405-ADNOC-UDR-TRL-9801 |  |  |  | 2025-03-05 | 8405-NPCC-MWS-T-00182
| SEP-650 DP SETUP FOR HOOKUP ACTIVITIES ON HD-03 PF | 8405-AP-0117 | HD0301-34-LAY-0117 | A01 |  |  | T-132/25 | 2025-04-08 | 2025-04-08 | 8405-ADNOC-UDR-TRL-9819
|  |  |  | A02 |  |  | T-465/25 | 2025-09-09 | NOT ISSUED
| SEP-550 DP SET-UP DURING HOOK UP ACTIVITIES AT HD-T4 | 8405-AP-0118 | HD0201-34-LAY-0118 | A01
| SEAFOX TRIDENT SETUP DURING HOOKUP ACTIVITIES ON BH-03 PF | 8405-AP-0119 | HD0301-34-LAY-0119 | A01
| SEP-450 DP SET-UP DURING HOOK UP ACTIVITIES AT HD-T4 | 8405-AP-0120 | HD0201-34-LAY-0120 | A01 |  |  | T-163/25 | 2025-04-29 | 2025-09-16 | 8405-ADNOC-UDR-TRL-9944
|  |  |  | A02 |  |  | T-473/25 | 2025-09-13 | 2025-09-16 | 8405-ADNOC-UDR-TRL-9945
| SEP-450 SETUP for hookup activities @ BH-03 PF | 8405-AP-0121 | BH0301-34-LAY-0121 | A01
| SEP-450 SETUP PLAN ON IGD-E PF FOR DECK EXTENSION INSTALLATION | 8405-AP-0122 | KP3801-34-LAY-0122 | A01 |  |  | T-180/25 | 2025-05-01 | 2025-05-23 | 8405-ADNOC-UDR-TRL-9861 |  |  | 1 - Rejected
|  |  |  | A02 |  |  | T-222/25 | 2025-05-28 | 2025-06-24 | 8405-ADNOC-UDR-TRL-9875 | 2025-06-26 | 8405-ADNOC-NPCC-TRL-04346 | 2 - Comments as noted
|  |  |  | A03 |  |  | T-268/25 | 2025-06-18 | 2025-06-24 | 8405-ADNOC-UDR-TRL-9879 | 2025-06-26 | 8405-ADNOC-NPCC-TRL-04346 | 2 - Comments as noted
|  |  |  | A04 |  |  | T-309/25 | 2025-07-01 | 2025-07-01 | 8405-ADNOC-UDR-TRL-9892
| SEP-450 SETUP PLAN ON IGD-E PF FOR HOOKUP ACTIVITES | 8405-AP-0123 | KP3801-34-LAY-0123 | A01 |  |  | T-184/25 | 2025-05-03 | 2025-05-05 | 8405-ADNOC-UDR-TRL-9839 | 2025-05-15 | 8405-ADNOC-NPCC-TRL-04319 | 2 - Comments as noted
|  |  |  | A02 |  |  | T-222/25 | 2025-05-28 | 2025-06-24 | 8405-ADNOC-UDR-TRL-9878 | 2025-06-26 | 8405-ADNOC-NPCC-TRL-04346 | 1 - Rejected
|  |  |  | A03 |  |  | T-409/25 | 2025-08-13 | 2025-08-14 | 8405-ADNOC-UDR-TRL-9915 | 2025-08-26 | 8405-ADNOC-NPCC-TRL-04388 | 3 - No Comments
| SEP-650 SETUP for hookup activities @ BH-03 PF | 8405-AP-0124 | BH0301-34-LAY-0124 | A01 |  |  | T-261/25 | 2025-06-16 | 2025-06-19 | 8405-ADNOC-UDR-TRL-9873 | 2025-06-26 | 8405-ADNOC-NPCC-TRL-04346 | 3 - No Comments
| ELEVATION VIEW- SEP-650 SET UP AT BH-03 TOWER | 8405-AP-0125 | BH0301-34-LAY-0125 | A01 |  |  | T-269/25 | 2025-06-18 | 2025-07-04 | 8405-ADNOC-UDR-TRL-9896 | 04-Jul-2025 | 8405-ADNOC-UDR-TRL-9896 | 3 - No Comments
|  |  |  | A02 |  |  | T-395/25 | 2025-08-06 | 2025-08-06 | 8405-ADNOC-UDR-TRL-9911 | 2025-08-06 | 8405-ADNOC-UDR-TRL-9911 | 3 - No Comments
| WORKBOAT ANCHOR PATTERN DURING JACKET FACE SURVEY AT WHP-10 | 8405-AP-0201 | CF4901-34-LAY-0001 | A01 |  |  | T-128/22 | 2022-04-06 | 2022-04-27 | 8405-ADNOC-UDR-TRL-1008 | 2022-05-09 | 8405-ADNOC-NPCC-TRL-00224 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-193/26 | 2026-05-07 | 2026-05-09 | 8405-ADNOC-UDR-TRL-10094
| WORKBOAT ANCHOR PATTERN DURING JACKET FACE SURVEY AT WHP-BH-3 | 8405-AP-0202 | BH4900-34-LAY-0002 | A01 |  |  | T-128/22 | 2022-04-06 | 2022-04-27 | 8405-ADNOC-UDR-TRL-1008 | 2022-05-09 | 8405-ADNOC-NPCC-TRL-00224 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-193/26 | 2026-05-07 | 2026-05-09 | 8405-ADNOC-UDR-TRL-10095
| WORKBOAT ANCHOR PATTERN DURING JACKET FACE SURVEY AT HD-3 | 8405-AP-0203 | HD4900-34-LAY-0003 | A01 |  |  | T-128/22 | 2022-04-06 | 2022-04-27 | 8405-ADNOC-UDR-TRL-1008 | 2022-05-09 | 8405-ADNOC-NPCC-TRL-00224 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-193/26 | 2026-05-07 | 2026-05-09 | 8405-ADNOC-UDR-TRL-10096
| WORKBOAT ANCHOR PATTERN DURING JACKET FACE SURVEY AT HD-WHP-T4 (EAST SIDE) | 8405-AP-0204 | CF0000-34-LAY-0004 | A01 |  |  | T-128/22 | 2022-04-06 | 2022-04-27 | 8405-ADNOC-UDR-TRL-1008 | 2022-05-09 | 8405-ADNOC-NPCC-TRL-00224 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-193/26 | 2026-05-07 | 2026-05-09 | 8405-ADNOC-UDR-TRL-10097
| WORKBOAT ANCHOR PATTERN DURING JACKET FACE SURVEY AT HD-WHP-T4 (WEST SIDE) | 8405-AP-0205 | CF0000-34-LAY-0005 | A01 |  |  | T-128/22 | 2022-04-06 | 2022-04-27 | 8405-ADNOC-UDR-TRL-1008 | 2022-05-09 | 8405-ADNOC-NPCC-TRL-00224 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-193/26 | 2026-05-07 | 2026-05-09 | 8405-ADNOC-UDR-TRL-10098
| WORKBOAT ANCHOR PATTERN DURING JACKET FACE SURVEY AT IGD-E | 8405-AP-0206 | KP0000-34-LAY-0006 | A01 |  |  | T-128/22 | 2022-04-06 | 2022-04-27 | 8405-ADNOC-UDR-TRL-1008 | 2022-05-09 | 8405-ADNOC-NPCC-TRL-00224 | 2 - Comments as noted
|  |  |  | 01 |  |  | T-193/26 | 2026-05-07 | 2026-05-09 | 8405-ADNOC-UDR-TRL-10099
| WORK BOAT SWISSCO TOPAZ ANCHOR PATTERN AT HD-03 PLATFORM (SOUTH SIDE) | 8405-AP-0208 | HD0301-34-LAY-0208 | A01 |  |  | T-236/23 | 2023-08-09 | NOT ISSUED
| WORKBOAT MUTAWA -101 ANCHOR PATTERN DURING SEABED SURVEY AT IGD-E PLATFORM | 8405-AP-0209 | KP3801-34-LAY-0209 | A01 |  |  | T-059-24 | 2024-02-09 | 2024-02-09 | 8405-ADNOC-UDR-TRL-8554 | 2024-03-19 | 8405-ADNOC-NPCC-TRL-03431 | 2 - Comments as noted | 2024-02-09 | 8405-NPCC-MWS-T-00082
| ANCHOR PATTERN FOR MUTAWA-101 DURING PL-6 REMEDIAL WORKS NEAR ZIRKU ISLAND | 8405-AP-0210 | AZ0091-34-LAY-0210 | A01 |  |  | T-193/24 | 2024-05-08 | NOT ISSUED
| MUTAWA-101 ANCHOR PATTERN AT WHP-10 FOR RISER CLAMP INSTALLATION | 8405-AP-0211 | ST0101-34-LAY-0211 | A01 |  |  | T-356/24 | 2024-08-08 | 2024-05-09 | 8405-ADNOC-UDR-TRL-9426 | 2024-09-19 | 8405-ADNOC-NPCC-TRL-03934 | 1 - Rejected
| MUTAWA-101ANCHOR PATTERN AT BH-03 FOR RISER CLAMP INSTALLATION | 8405-AP-0212 | BH0301-34-LAY-0212 | A01 |  |  | T-356/24 | 2024-08-08 | 2024-05-09 | 8405-ADNOC-UDR-TRL-9426 | 2024-09-19 | 8405-ADNOC-NPCC-TRL-03934 | 1 - Rejected
| MUTAWA-101 ANCHOR PATTERN AT BH-03 FOR SEABED SURVEY | 8405-AP-0213 | BH0301-34-LAY-0213 | A01 |  |  | T-356/24 | 2024-08-08 | 2024-05-09 | 8405-ADNOC-UDR-TRL-9426 | 2024-09-19 | 8405-ADNOC-NPCC-TRL-03932 | 3 - No Comments
| MUTAWA-11 ANCHOR PATTERN AT HD-03 DURING FLOODING, CLEANING, GAUGING AND HYDROTESTING | 8405-AP-0214 | HD0301-34-LAY-0214 | A01 |  |  | T-011/25 | 2025-01-10 | 2025-01-10 | 8405-ADNOC-UDR-TRL-9739 | 2025-01-27 | 8405-ADNOC-NPCC-TRL-04194 | 1 - Rejected
|  |  |  | B01 |  |  | T-049/25 | 2025-01-29 | 2025-01-29 | 8405-ADNOC-UDR-TRL-9768 | 2025-02-20 | 8405-ADNOC-NPCC-TRL-04227 | 3 - No Comments
| MUTAWA-11 ANCHOR PATTERN AT WHP-T4 DURING FLOODING, CLEANING, GAUGING AND HYDROTESTING (POSITION-1) & (POSITION-2) SHEET 1 & 2 | 8405-AP-0215 | HD-0201-34-LAY-0215 | A01 |  |  | T-011/25 | 2025-01-10 | 2025-01-10 | 8405-ADNOC-UDR-TRL-9739 | 2025-01-27 | 8405-ADNOC-NPCC-TRL-04194 | 1 - Rejected
|  |  |  | B01 |  |  | T-049/25 | 2025-01-29 | 2025-01-29 | 8405-ADNOC-UDR-TRL-9768 | 2025-02-20 | 8405-ADNOC-NPCC-TRL-04227 | 3 - No Comments
| MUTAWA-11 ANCHOR PATTERN AT WHP-10 DURING FLOODING, CLEANING, GAUGING AND HYDROTESTING | 8405-AP-0216 | ST0101-34-LAY-0216 | A01 |  |  | T-011/25 | 2025-01-10 | 2025-01-10 | 8405-ADNOC-UDR-TRL-9741 | 2025-01-30 | 8405-ADNOC-NPCC-TRL-04202 | 1 - Rejected
|  |  |  | B01 |  |  | T-049/25 | 2025-01-29 | 2025-01-30 | 8405-ADNOC-UDR-TRL-9770 | 2025-02-20 | 8405-ADNOC-NPCC-TRL-04227 | 3 - No Comments
| MUTAWA-11 ANCHOR PATTERN AT IGD-E DURING FLOODING, CLEANING, GAUGING AND HYDROTESTING | 8405-AP-0217 | KP0091-34-LAY-0217 | A01 |  |  | T-011/25 | 2025-01-10 | 2025-01-10 | 8405-ADNOC-UDR-TRL-9739 | 2025-01-27 | 8405-ADNOC-NPCC-TRL-04194 | 1 - Rejected
|  |  |  | B01 |  |  | T-049/25 | 2025-01-29 | 2025-01-29 | 8405-ADNOC-UDR-TRL-9768 | 2025-02-20 | 8405-ADNOC-NPCC-TRL-04227 | 3 - No Comments
| MUTAWA-11 ANCHOR PATTERN AT BH-03 DURING FLOODING, CLEANING, GAUGING AND HYDROTESTING | 8405-AP-0218 | BH0301-34-LAY-0218 | A01 |  |  | T-011/25 | 2025-01-10 | 10-Jan-2025 | 8405-ADNOC-UDR-TRL-9739 | 2025-01-27 | 8405-ADNOC-NPCC-TRL-04194 | 1 - Rejected
|  |  |  | B01 |  |  | T-049/25 | 2025-01-29 | 2025-01-29 | 8405-ADNOC-UDR-TRL-9768 | 2025-02-20 | 8405-ADNOC-NPCC-TRL-04227 | 3 - No Comments
| SEAFOX TRIDENT-1 SETUP FOR HOOKUP ACTIVITIES AT WHP-10 PF | 8405-AP-0219 | ST0101-34-LAY-0220 | A01
| SEAFOX TRIDENT SETUP FOR HOOKUP ACTIVITIES ON IGD-E | 8405-AP-0220 | KP3801-34-LAY-0221 | A01 |  |  | T-313/25 | 2025-07-01 | 2025-07-01 | 8405-ADNOC-UDR-TRL-9893 |  |  |  | 2025-07-26 | 8405-NPCC-MWS-T-00185
| SEAFOX TRIDENT-1 AT IGD-E west side for hookup activities | 8405-AP-0221 | KP3801-34-LAY-0222 | A01 |  |  | T-412/25 | 2025-08-13 | 2025-08-14 | 8405-ADNOC-UDR-TRL-9914 | 2025-08-26 | 8405-ADNOC-NPCC-TRL-04388 | 1 - Rejected
|  |  |  | A02 |  |  | T-431/25 | 2025-08-27 | 2025-09-02 | 8405-ADNOC-UDR-TRL-9925 | 2025-09-16 | 8405-ADNOC-NPCC-TRL-04401 | 3 - No Comments
| SEP-650 SET-UP AT WHP-10 for hookup activities | 8405-AP-0222 | ST0101-34-LAY-0224 | A01
| SEAFOX TRIDENT-1 AND SEP-650 SET-UP AT BH-03 | 8405-AP-0223 | BH0301-34-LAY-0223 | A01
| DIXIE PATRIOT DP SET-UP AT HD-14 DURING HOOK UP ACTIVITIES | 8405-AP-0224 | HD0201-34-LAY-0224 | A01
| SEAFOX TRIDENT-1 SET UP DURING HOOK UP WORKS AT WHP-10 | 8405-AP-0225 | ST0101-34-LAY-0225 | A01
| UMM SHAIF BARGE DP SET-UP PLAN DURING UMBLICAL INSTALLATION OF UC-2 (FROM HD-03 TO HD WHP-T4) | 8405-DP-0202 | HD0101-34-LAY-0202 | A01 |  |  | T-010/24 | 2024-01-10 | 2024-01-10 | 8405-ADNOC-UDR-TRL-8353 | 2024-02-14 | 8405-ADNOC-NPCC-TRL-03325 | 3 - No Comments | 2024-01-10 | 8405-NPCC-MWS-T-00060
| SAFEEN-3000 DP SET-UP DURING REMOVAL OF EXISITNG TOPSIDE OF HAIR DALMA HD-3 | 8405-DP-0208 | HD0301-34-LAY-0208A | A01 |  |  | T-273/23 | 2023-09-15 | 2023-05-15 | 8405-ADNOC-UDR-TRL-7456 | 2023-09-27 | 8405-ADNOC-NPCC-TRL-02700 | 3 - No Comments
|  |  |  | B01 |  |  | T-313/23 | 2023-10-20 | NOT ISSUED
| SAFEEN-3000 DP SET-UP FOR HD-3 TRIPOD JACKET EXTENSION INSTALLATION | 8405-DP-0215 | HD0301-34-LAY-0215 | A01 |  |  | T-317/23 | 2023-10-24 | 2023-10-25 | 8405-ADNOC-UDR-TRL-7756 | 2023-11-10 | 8405-ADNOC-NPCC-TRL-02948 | 3 - No Comments | 2023-10-25 | 8405-NPCC-MWS-T-00020
|  |  |  | B01 |  |  | T-078-24 | 2024-02-15 | NOT ISSUED
| SAFEEN 3000 DP SETUP PLAN DURING LIFTING AND INSTALLATION OF BH-03 DECK | 8405-DP-0216 | BH0301-34-LAY-0216 | A01 |  |  | T-098/24 | 2024-02-29 | 2024-03-01 | 8405-ADNOC-UDR-TRL-8710 | 2024-04-30 | 8405-ADNOC-NPCC-TRL-03552 | 1 - Rejected | 2024-03-01 | 8405-NPCC-MWS-T-00090
|  |  |  | A02 |  |  | T-247/24 | 2024-06-07 | 2024-06-07 | 8405-ADNOC-UDR-TRL-9209 | 2024-07-08 | 8405-NPCC-ADNOC-TRL-02032 | 1 - Rejected
|  |  |  | A03 |  |  | T-318/24 | 2024-07-09 | 2024-07-10 | 8405-ADNOC-UDR-TRL-9333 | 2024-07-26 | 8405-ADNOC-NPCC-TRL-03815 | 3 - No Comments
| SAFEEN 3000 DP SETUP PLAN DURING LIFTING AND INSTALLATION OF HD-03 DECK | 8405-DP-0217 | HD0301-34-LAY-0217 | A01 |  |  | T-098/24 | 2024-02-29 | 01-Mar-2024 | 8405-ADNOC-UDR-TRL-8711 | 2024-04-30 | 8405-ADNOC-NPCC-TRL-03552 | 1 - Rejected | 2024-03-01 | 8405-NPCC-MWS-T-00090
|  |  |  | A02 |  |  | T-247/24 | 2024-06-07 | 07-Jun-2024 | 8405-ADNOC-UDR-TRL-9210 | 2024-07-08 | 8405-NPCC-ADNOC-TRL-02032 | 1 - Rejected
|  |  |  | A03 |  |  | T-027/25 | 2025-01-17 | 2025-01-20 | 8405-ADNOC-UDR-TRL-9750 | 2025-02-12 | 8405-ADNOC-NPCC-TRL-04215 | 3 - No Comments | 2025-01-17 | 8405-NPCC-MWS-T-00173
| SAFEEN 3000 DP SETUP PLAN DURING LIFTING AND INSTALLATION OF HD-T4 DECK | 8405-DP-0218 | ST0101-34-LAY-0218 | A01 |  |  | T-098/24 | 2024-02-29 | 2024-03-01 | 8405-ADNOC-UDR-TRL-8712 | 2024-04-30 | 8405-ADNOC-NPCC-TRL-03552 | 1 - Rejected | 2024-03-01 | 8405-NPCC-MWS-T-00090
|  |  |  | A02 |  |  | T-247/24 | 2024-06-07 | 2024-06-07 | 8405-ADNOC-UDR-TRL-9211 | 2024-07-08 | 8405-NPCC-ADNOC-TRL-02032 | 1 - Rejected
|  |  |  | A03 |  |  | T-027/25 | 2025-01-17 | 2025-01-20 | 8405-ADNOC-UDR-TRL-9751 | 2025-02-12 | 8405-ADNOC-NPCC-TRL-04215 | 3 - No Comments | 2025-01-17 | 8405-NPCC-MWS-T-00174
| DLS 4200 DP SETUP PLAN DURING LIFTING AND INSTALLATION OF BH-03 DECK | 8405-DP-0221 | BH0301-34-LAY-0221 | A01 |  |  | T-347/24 | 2024-08-01 | 2024-08-02 | 8405-ADNOC-UDR-TRL-9401 | 2024-08-22 | 8405-ADNOC-NPCC-TRL-03865 | 3 - No Comments | 2024-08-02 | 8405-NPCC-MWS-T-00149
| DLS 4200 DP SETUP PLAN DURING LIFTING AND INSTALLATION OF HD-03 DECK | 8405-DP-0222 | HD0301-34-LAY-0222 | A01 |  |  | T-347/24 | 2024-08-01 | 2024-08-02 | 8405-ADNOC-UDR-TRL-9402 | 2024-09-03 | 8405-ADNOC-NPCC-TRL-03895 | 3 - No Comments | 2024-08-02 | 8405-NPCC-MWS-T-00149
| DLS 4200 DP SETUP PLAN DURING LIFTING AND INSTALLATION OF WHP T-4 DECK | 8405-DP-0223 | ST0101-34-LAY-0223 | A01 |  |  | T-347/24 | 2024-08-01 | 2024-08-02 | 8405-ADNOC-UDR-TRL-9403 | 2024-09-03 | 8405-ADNOC-NPCC-TRL-03895 | 3 - No Comments | 2024-08-02 | 8405-NPCC-MWS-T-00149

## Sketches
NMDC DOC. No.: MDR-001
EPC FOR DALMA GAS DEVELOPMENT PROJECT
|  | NMDC PROJECT NO. 8405 | [6 empty] | REVISION : | 0
|  | OFFSHORE Sketches | [6 empty] | DATE : | 2026-06-11
SR. NO. | DESCRIPTION | NMDC Energy DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| DLS-4200 AP DURING WHP-10 POST DECK INSTALLATION WORKS | 8405-AP-0055 |  | A01 |  |  | 2024-08-26 | VSK/KM
| ANCHOR PATTERN FOR BARGE DLB-1000 DURING PL-5 RISER & TIE-IN INSTALLATION AT IGD-E | 8405-AP-0047 |  | A02 |  |  | 2024-09-03 | VKS/KM
| SEQUENCE FOR CABLE PULL THROUGH J-TUBE AT IGD-E | 8405-A3-109 |  | 0 |  |  | 2024-09-03 | VKS/KM
| SEP-450 SETUP AT WHP-10 | 8405-A3-110 |  | 0 |  |  | 2024-09-05 | VKS/MH
| SEP-450 SETUP DURING HOOK UP WORKS AT WHP-10 | 8405-AP-0113 |  | A01 |  |  | 2024-09-05 | VKS/MH
| SEQUENCE FOR FOC SPLICING BY DLB-1000 | P8405-A3-111 |  | A |  |  | 2024-09-10 | DRH/KM
| DLB-1000 ANCHOR PATTERN DURING NEW DECK EXTENSION INSTALLATION AT IGD-E | 8405-AP-0051 |  | A01 |  |  | 2024-09-12 | VSK/KM
| ANCHOR PATTEN FOR BARGE DLB-1000 DURING PL-5 RISER & TIE-IN INSTALLATION AT IGD-E | 8405-AP-0047 |  | A02 |  |  | 2024-09-13 | VSK/KM
| DLB-1000 ANCHOR PATTERN DURING FOC SPLICING AT PL-6 MID LINE TIE-IN AT KP 48.60 | 8405-AP-0056 |  | A01 |  |  | 2024-09-13 | VSK/KM
| CARGO BARGE APPROACH DURING IGD - E DECK EXTENSION INSTALLATION | 8405-A1-025 |  | 0 |  |  | 2024-09-23 | VSK/mh
| (CARGO BARGE Approach during IGD-E Deck Extension Installation) | 8405-A1-025 |  | 1 |  |  | 2024-10-20 | VKS/MHF
| ANCHOR PATTERN AT HD-03 DURING FLOODING, CLEANING, GOUGING, AND HYDROTESTING | 8405-AP-0214 |  | A01 |  |  | 2025-01-09 | VKS/RAH
| ANCHOR PATTERN AT WHP-T4 DURING FLOODING, CLEANING, GOUGING, AND HYDROTESTING (POSITION-1) | 8405-AP-0215 |  | A01 |  |  | 2025-01-09 | VKS/RAH
| ANCHOR PATTERN AT WHP-T4 DURING FLOODING, CLEANING, GOUGING, AND HYDROTESTING (POSITION-2) | 8405-AP-0215 |  | A01 |  |  | 2025-01-09 | VKS/RAH
| ANCHOR PATTERN AT WHP-10 DURING FLOODING, CLEANING, GOUGING, AND HYDROTESTING | 8405-AP-0216 |  | A01 |  |  | 2025-01-09 | VKS/RAH
| ANCHOR PATTERN AT IGD-E DURING FLOODING, CLEANING, GOUGING, AND HYDROTESTING | 8405-AP-0217 |  | A01 |  |  | 2025-01-09 | VKS/RAH
| ANCHOR PATTERN AT BH-3 DURING FLOODING, CLEANING, GOUGING, AND HYDROTESTING | 8405-AP-0218 |  | A01 |  |  | 2025-01-09 | VKS/RAH
| 8405-AP-0214_B01(MUTAWA-11 AP @ HD-3) | 8405-AP-0214 |  | B01 |  |  | 2025-01-15 | VKS/RAH
| 8405-AP-0215-1 OF 2_B01(MUTAWA-11 AP @ HD-WHP-T4) | 8405-AP-0215 |  | B01 |  |  | 2025-01-15 | VKS/RAH
| 8405-AP-0216_B01(MUTAWA-11 AP @ WHP-10) | 8405-AP-0216 |  | B01 |  |  | 2025-01-15 | VKS/RAH
| 8405-AP-0217_B01(MUTAWA-11 AP @ IGD-E) | 8405-AP-0217 |  | B01 |  |  | 2025-01-15 | VKS/RAH
| 8405-AP-0218_B01(MUTAWA-11 AP @ WHP-BH-3) | 8405-AP-0218 |  | B01 |  |  | 2025-01-15 | VKS/RAH
| (SAFEEN 3000 SET-UP during HD-03 DECK INSTALLATION) | 8405-DP-0217 |  | A03 |  |  | 2025-01-17 | VKS/MHF
| (SAFEEN 3000 SET-UP during HD-T4 DECK INSTALLATION) | 8405-DP-0218 |  | A03 |  |  | 2025-01-17 | VKS/MHF
| (SEP-650 SETUP @ HD-WHP-T4) | 8405-AP-0116 |  | A02 |  |  | 2025-03-11 | EJJ
| (SEP-550 SETUP @ HD-WHP-T4) | 8405-AP-0118 |  | A01 |  |  | 2025-03-18 | EJJ
| (SEP-650 DP SETUP HOOK-UP WORKS @ HD-03) | 8405-AP-0117 |  | A02 |  |  | 2025-04-02 | SKV
| (SEAFOX TRIDENT-1 AP @ HD-T4) | 8405-AP-0115 |  | A02 |  |  | 2005-04-02 | SKV
| (SEP-450 Aviation sketch at IGD-E platform) | 8405-A3-113 |  | B |  |  | 2025-06-07 | EJJ
| (SEP-450 at IGD-E) with OD co-ordinate | 8405-AP-0122 |  | A03 |  |  | 2025-06-09 | EJJ
| 8405-AP-0122_Rev-A04(SEP-450 at IGD-E) with OD co-ordinate | 8405-AP-0122 |  | A04 |  |  | 2025-06-30 | SKV
| 8405-AP-0047_A03(DLB 1000 ANCHOR PATTERN DURING PL-5 RISER & TIE-IN INSTALLATION AT IGD-E) | 8405-AP-0047 |  | A03 |  |  | 2025-07-02 | SKV
| 8405-A3-120-RevA SEP-650 LIFTING MATERIAL USING SEATRAX CRANE @ WHP-10 | 8405-A3-120 |  | A |  |  | 2025-10-31 | ENH
| 8405-A3-121-RevA SEP-650 LIFTING BILLY PUGH USING SEATRAX CRANE @ WHP-10 | 8405-A3-121 |  | A |  |  | 2025-10-31 | ENH
| SEP-650 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY-PUGH AT ZK-280 PLATFORM USING PELLEGRINI PEDESTAL CRANE | OFO-P8405-SK-134 |  | A |  |  | 2025-10-31 | MF
| SEP-650 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY-PUGH AT WHP BH-3 PLATFORM USING SEATRAX CRANE | OFO-P8405-SK-135 |  | A |  |  | 2025-10-31 | MF
| SEP-650 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY AT WHP BH-3 PLATFORM USING SEATRAX PEDESTAL CRANE | OFO-P8405-SK-133 |  | A |  |  | 2025-10-31 | MF
| SEP-650 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL AT WHP BH-3 PLATFORM USING PELLEGRINI PEDESTAL CRANE | OFO-P8405-SK-131 |  | A |  |  | 2025-10-31 | MF
| SEP-650 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL AT WHP BH-3 PLATFORM USING SEATRAX CRANE | OFO-P8405-SK-132 |  | A |  |  | 2025-10-31 | MF
| SEP-650 RECOVERY OF ZODIAC ARRANGEMENT AT WHP BH-3 PLATFORM USING PELLEGRINI PEDESTAL CRANE | OFO-P8405-SK-136 |  | A |  |  | 2025-10-31 | MF
| 8405-A3-122 - SEP-650 AVIATION CLEARANCE AT HD-03 | 8405-A3-122 |  | 0 |  |  | 2026-02-19 | VSK