## Pre -Req. Matrix
Deliverables Pre- Requisites Matrix
| Spec forExternal Pipeline Coating(3LPE) | Specifications For Pipeline Welding | Specifications For Linepipe (SMLS) | Spec forConcrete Wieght Coating and Anode Installation | Spec forField Joint Coating | Spec forOffshore Concrete Sleepers | Spec forFlexible Concrete Mattresses | Specification For Pipeline Flanges (Including Hanger Flanges), Gaskets, Bolts and Nuts | Spec forPipeline Crossings | Spec forPipeline Anodes | Specification For Neoprene Coating of Risers And Clamps | Spec forFree Span Correction | Spec for Painting and Coating | Pre-Construction Pipelines Routes and Anchor Clearance Survey Report | Pre-Engineering ROV Survey Report | Pre-Engineering Geophysical Survey Report | Pipeline On Bottom Roughness Report | Anchor Handling And Mooring Procedure For Floating Barges | Anchor Handling And Mooring Procedure For Jack Up Barges | Method Statement For Handling Of Anchors By Hammer Head Crane Vessel | Riser And Anode Clamps Installation Procedure | Risers Installation Procedure | Subsea Spools Installation Procedure | Existing Pipeline Demolition Procedure | Subsea Flanges Management Procedure | Data Sheet For Pipeline Flanges (Including Hanger Flanges), Gaskets, Bolts And Nuts | Sleepers Installation Procedure | Grout Bags Installation And Free Span Correction Procedure | Pipelines Overall Field Layout Drawing | Pipeline Alignment Sheet | Analysis & Design Of Offshore Concrete Sleepers | Pipeline Global Buckling and Walking Analysis Report
Spec forExternal Pipeline Coating(3LPE) | 1
Specifications For Pipeline Welding |  | 1
Specifications For Linepipe (SMLS) |  |  | 1
Spec forConcrete Wieght Coating and Anode Installation |  |  |  | 1
Spec forField Joint Coating |  |  |  |  | 1
Spec forOffshore Concrete Sleepers | [5 empty] | 1
Spec forFlexible Concrete Mattresses | [6 empty] | 1
Specification For Pipeline Flanges (Including Hanger Flanges), Gaskets, Bolts and Nuts | [7 empty] | 1
Spec forPipeline Crossings | [8 empty] | 1
Spec forPipeline Anodes | [9 empty] | 1
Specification For Neoprene Coating of Risers And Clamps | [10 empty] | 1
Spec forFree Span Correction | [11 empty] | 1
Spec for Painting and Coating | [12 empty] | 1
Pre-Construction Pipelines Routes and Anchor Clearance Survey Report | [13 empty] | 1
Pre-Engineering ROV Survey Report | [14 empty] | 1
Pre-Engineering Geophysical Survey Report | [15 empty] | 1
Pipeline On Bottom Roughness Report | [16 empty] | 1
Anchor Handling And Mooring Procedure For Floating Barges | [17 empty] | 1
Anchor Handling And Mooring Procedure For Jack Up Barges | [18 empty] | 1
Method Statement For Handling Of Anchors By Hammer Head Crane Vessel | [19 empty] | 1
Riser And Anode Clamps Installation Procedure | [20 empty] | 1
Risers Installation Procedure | [21 empty] | 1
Subsea Spools Installation Procedure | [22 empty] | 1
Existing Pipeline Demolition Procedure | [23 empty] | 1
Subsea Flanges Management Procedure | [24 empty] | 1
Data Sheet For Pipeline Flanges (Including Hanger Flanges), Gaskets, Bolts And Nuts | [25 empty] | 1
Sleepers Installation Procedure | [26 empty] | 1
Grout Bags Installation And Free Span Correction Procedure | [27 empty] | 1
Pipelines Overall Field Layout Drawing | [28 empty] | 1
Pipeline Alignment Sheet | [29 empty] | 1
Analysis & Design Of Offshore Concrete Sleepers | [30 empty] | 1
Pipeline Global Buckling and Walking Analysis Report | [31 empty] | 1