## Installation Procedures
NMDC DOC. No.: MDR-001
|  | NMDC PROJECT NO. E2964 | [11 empty] | REVISION :
|  | OFFSHORE INSTALLATION PROCEDURES | [11 empty] | DATE : | 2025-12-04
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | REF | DATE | REF | DATE | CODE | REF | DATE | REF | DATE | CODE

## Setup Plans & Anchor Patterns
NMDC DOC. No.:
|  | NMDC PROJECT NO. E2964 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE ANCHOR PATTERN AND DP DRAWINGS | [11 empty] | DATE : | 2025-12-04 |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | Methods TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | REF | DATE | REF | DATE | REF | DATE | CODE | REF | DATE | REF | DATE | CODE

## Sketches
NMDC DOC. No.:
|  | NMDC PROJECT NO. E2964 | [6 empty] | REVISION : |  | 0
|  | OFFSHORE Sketches | [6 empty] | DATE : | 2025-12-04 | 2023-08-02
SR. NO. | DESCRIPTION | NMDC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  |  | REMARKS
SUBMISSION STATUS
[7 empty] | DATE | REF
| E2964-A1-001_Rev-A (DLS-4200 AP during SPB Jacket Installation)-Option-2 | E2964-A1-001 |  | A |  |  | 2025-12-03 | SKV