## PROCEDURES
HAIL AND GHASHA DEVELOPMENT PROJECT
PROCEDURES STATUS
UPDATE | 2026-02-11 |  |  | CYCLE 01 |  |  |  |  | CYCLE 02 |  |  |  |  | CYCLE 03 |  |  |  |  | CYCLE 04
[6 empty] | CLT | ABL | RINA |  |  | CLT | ABL | RINA |  |  | CLT | ABL | RINA |  |  | CLT | ABL | RINA
DOC NO | SOW | PF | Title | CYL#01 REV | CYL#01 ISSUE DATA | CYL#01 CRS STK#01 | CYL#01 CRS STK#02 | CYL#01 CRS STK#03 | CYL#02 REV | CL#02 ISSUE DATE | CRS CYL#02 STK#01 | CRS CYL#02 STK#02 | CRS CYL#02 STK#03 | CYL#03 REV | CYL#03 ISSUE DATE | CYL#03 CRS STK#01 | CYL#03 CRS STK#02 | CYL#03 CRS STK#03 | CYL#04 REV | CL#04 ISSUE DATE | CRS CYL#04 STK#01 | CRS CYL#04 STK#02 | CRS CYL#04 STK#03 | NOTES
1-CF0000-31-PRO-2625-00 | RIS-SP | GOP-SRP | STALK ON RISERS INSTALLATION PROCEDURE (DLS4200) AT GOP-SRP | A1 | 2026-04-08 | 2026-04-29 | 2026-04-29 |  | X100 | 2026-05-07 |  | 2026-05-13 |  | 00 | 2026-05-15 | 2026-05-25 | 2026-05-19
1-CF0000-31-PRO-2402-00 | DECK | GOP-SRP | TOPSIDES INSTALLATION PROCEDURE (GOP-SRP) | A1 | 2026-02-20 | 2026-03-19 | 2026-03-17 | 2026-03-10 | X100 | 2026-04-28 |  | 2026-05-14 |  | 00 | 2026-05-18 | 2026-06-09 | 2026-05-25 | 2026-06-01
1-GH5100-31-PRO-2677-00 | DECK | GOP-SRP | TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT GOP-SRP | A1 | 2026-07-01 | 2026-07-16 | 2026-07-06 | 2026-07-20 | 00 | 2026-07-19
1-CF0000-31-PRO-2404-00 | BRD | GOP-SRP | BRIDGES INSTALLATION PROCEDURE (GOP-SRP) | A1 | 2026-02-18 | 2026-03-23 | 2026-03-25 | 2026-03-23 | X100 | 2026-06-16
1-GH5100-31-PRO-2678-00 | BRD | GOP-SRP | BRIDGES INSTALLATION PROCEDURE (DLS4200) AT GOP-SRP | A1 | 2026-07-03 | 2026-07-16 | 2026-07-15 | 2026-07-20 | 00 | 2026-07-22 |  |  | 2026-08-10
1-GH0600-31-PRO-2672-00 | RIS-SP | COMMON | STALK ON RISERS INSTALLATION PROCEDURE (DLS4200) AT DC6 AND GOP-NRP | A1 | 2026-06-22 | 2026-07-10 | 2026-07-07 |  | X100 | 2026-07-09 |  | 2026-07-16 |  | 00 | 2026-07-23 | 2026-08-03
1-CF0000-31-PRO-2643-00 | DECK | DC6 | TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT DC6 | A1 | 2026-05-20 | 2026-06-18 | 2026-06-03 | 2026-06-01 | X100 | 2026-06-30 |  | 2026-07-06 |  | 00 | 2026-07-06 | 2026-07-15 | 2026-07-14
1-GH0600-31-PRO-2665-00 | BRD | DC6 | BRIDGES INSTALLATION PROCEDURE (DLS4200) AT DC6 | A1 | 2026-07-06 | 2026-07-16 | 2026-07-15 | 2026-07-21 | 00 | 2026-07-29 | 2026-08-03 | 2026-08-03
1-GH5100-31-PRO-2673-00 | RIS-SP | GOP-NRP | STALK ON RISERS INSTALLATION PROCEDURE (DLS4200) AT GOP-NRP | A1 | 2026-07-03
1-GH5100-31-PRO-2659-00 | DECK | GOP-NRP | TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT GOP-NRP | A1 | waiting for lifting dwgs
1-GH5100-31-PRO-2666-00 | BRD | GOP-NRP | BRIDGES INSTALLATION PROCEDURE (DLS4200) AT GOP-NRP | A1 | waiting for lifting dwgs
1-GH0400-31-PRO-2674-00 | RIS-SP | DC4 | STALK ON RISERS INSTALLATION PROCEDURE (DLS4200) AT DC4
1-GH0400-31-PRO-2660-00 | DECK | DC4 | TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT DC4
1-GH0400-31-PRO-2667-00 | BRD | DC4 | BRIDGES INSTALLATION PROCEDURE (DLS4200) AT DC4
1-GH0100-31-PRO-2675-00 | RIS-SP | DC1 | STALK ON RISERS INSTALLATION PROCEDURE (SAFEEN3000) AT DC1
1-GH0100-31-PRO-2661-00 | DECK | DC1 | TOPSIDE INSTALLATION PROCEDURE (SAFEEN3000) AT DC1
1-GH0100-31-PRO-2668-00 | BRD | DC1 | BRIDGE INSTALLATION PROCEDURE (SAFEEN3000) AT DC1
1-GH6000-31-PRO-2662-00 | DECK | CLQ | TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT CLQ
1-GH6000-31-PRO-2669-00 | BRD | CLQ | BRIDGE INSTALLATION PROCEDURE (DLS4200) AT CLQ
1-GH5100-31-PRO-2663-00 | DECK | GOP-FLARE | TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT GOP FLARE
1-GH5100-31-PRO-2670-00 | BRD | GOP-FLARE | BRIDGE & FLARE BOOM INSTALLATION PROCEDURE (DLS4200) AT GOP FLARE
1-GH5100-31-PRO-2664-00 | DECK | GOP-SWI | TOPSIDE INSTALLATION PROCEDURE (DLS4200) AT GOP SWI
1-GH5100-31-PRO-2671-00 | BRD | GOP-SWI | BRIDGE INSTALLATION PROCEDURE (DLS4200) AT GOP SWI
1-CF0000-31-PRO-2649-00 | TIE-IN | COMMON | SURFACE MIDLINE INSTALLATION & REPAIR PROCEDURE
Total |  | 3 |  |  | 3 | [17 empty] | 0
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## APs SAFEEN3000
HAIL AND GHASHA DEVELOPMENT PROJECT
ANCHOR PATTERN STATUS
|  |  |  | CYCLE 01 |  |  |  | CYCLE 02 |  |  |  | CYCLE 03 |  |  |  | CYCLE 04
[6 empty] | CLT | ABL |  |  | CLT | ABL |  |  | CLT | ABL |  |  | CLT | ABL | 2025-08-13
anchor pattern NO | SOW | PF | Title | CYL#01 REV | CYL#01 ISSUE DATA | CYL#01 CRS STK#01 | CYL#01 CRS STK#02 | CYL#02 REV | CL#02 ISSUE DATE | CRS CYL#02 STK#01 | CRS CYL#02 STK#02 | CYL#03 REV | CYL#03 ISSUE DATE | CYL#03 CRS STK#01 | CYL#03 CRS STK#02 | CYL#04 REV | CL#04 ISSUE DATE | CRS CYL#04 STK#01 | CRS CYL#04 STK#02 | LATEST STATUS
1-GH5100-31-DWG-2465-00 | DECK | GOP-SRP | SAFEEN3000 ANCHOR PATTERN-GOP-SRP TOP SIDE INSTALLATION | A1 | 2026-01-23 | 2026-02-19 | 2026-02-10 | 00 | 2026-03-16 |  | 2026-03-30 | CN | 2026-04-06 | [6 empty] | 2026-04-06
1-GH5100-31-DWG-2466-00 | BRD | GOP-SRP | SAFEEN3000 ANCHOR PATTERN-GOP-SRP NORTH BRIDGE INSTALLATION | A1 | 2026-01-23 | 2026-02-11 | 2026-02-10 | 00 | 2026-03-16 |  | 2026-03-30 | CN | 2026-04-06 | [6 empty] | 2026-04-06
1-GH5100-31-DWG-2467-00 | BRD | GOP-SRP | SAFEEN3000 ANCHOR PATTERN-GOP-SRP SOUTH BRIDGE INSTALLATION | A1 | 2026-01-23 | 2026-02-11 | 2026-02-10 | 00 | 2026-03-16 |  | 2026-03-30 | CN | 2026-04-06 | [6 empty] | 2026-04-06
1-GH5100-31-DWG-2468-00 | RIS-SP | GOP-SRP | SAFEEN3000 ANCHOR PATTERN-GOP-SRP RISER/ SPOOL INSTALLATION FROM DC6 | A1 | 2026-01-23 | 2026-02-11 | 2026-02-10 | 00 | 2026-03-16 | 2026-04-13 | 2026-03-30 | [8 empty] | 2026-03-30
1-GH5100-31-DWG-2469-00 | RIS-SP | GOP-SRP | SAFEEN3000 ANCHOR PATTERN-GOP-SRP RISER/ SPOOL INSTALLATION FROM OPP | A1 | 2026-01-23 | 2026-02-11 | 2026-02-10 | 00 | 2026-03-16 | 2026-04-13 | 2026-03-30 | [8 empty] | 2026-03-30
1-GH5100-31-DWG-2619-00 | DECK | GOP-SRP | SAFEEN3000 SET-UP PLAN AT GOP-SRP TOP SIDE INSTALLATION | A1 | 2026-04-07 | 2026-05-04 | 2026-05-07 | 00 | 2026-05-08 | 2026-06-02 | 2026-05-14 | [8 empty] | 2026-05-14
1-GH5100-31-DWG-2620-00 | BRD | GOP-SRP | SAFEEN3000 SET-UP PLAN AT GOP-SRP NORTH BRIDGE INSTALLATION | A1 | 2026-04-07 | 2026-05-04 | 2026-05-07 | 00 | 2026-05-08 | 2026-06-02 | 2026-05-14 | [8 empty] | 2026-05-14
1-GH5100-31-DWG-2621-00 | BRD | GOP-SRP | SAFEEN3000 SET-UP PLAN AT GOP-SRP SOUTH BRIDGE INSTALLATION | A1 | 2026-04-07 | 2026-04-23 | 2026-05-07 | 00 | 2026-05-08 | 2026-06-02 | 2026-05-14 | [8 empty] | 2026-05-14
1-GH0600-31-DWG-2480-00 | RIS-SP | DC6 | SAFEEN3000 ANCHOR PATTERN-DC/6 RISER/SPOOL INSTALLATION | A1 | 2026-01-23 | 2026-02-11 | 2026-02-23 | 00 | 2026-03-18 |  | 2026-03-30 | [8 empty] | 2026-03-30
1-GH0600-31-DWG-2479-00 | DECK/BRG | DC6 | SAFEEN3000 ANCHOR PATTERN-DC/6 TOP-SIDE & BRIDGE INSTALLATION | A1 | 2026-01-23 | 2026-02-11 | 2026-02-23 | 00 | 2026-03-18 |  | 2026-03-30 | [8 empty] | 2026-03-30
1-GH5100-31-DWG-2474-00 | RIS-SP | GOP-NRP | SAFEEN3000 ANCHOR PATTERN-GOP-NRP RISER/SPOOL INSTALLATION | A1 | 2026-02-13 | 2026-03-19 | 2026-03-05 | [12 empty] | 2026-03-05
1-GH5100-31-DWG-2471-00 | DECK | GOP-NRP | SAFEEN3000 ANCHOR PATTERN-GOP-NRP TOP-SIDE INSTALLATION | A1 | 2026-02-13 | 2026-03-19 | 2026-03-05 | [12 empty] | 2026-03-05
1-GH5100-31-DWG-2472-00 | BRD | GOP-NRP | SAFEEN3000 ANCHOR PATTERN- GOP-NRP EAST BRIDGE INSTALLATION | A1 | 2026-02-13 | 2026-03-19 | 2026-03-05 | [12 empty] | 2026-03-05
1-GH5100-31-DWG-2473-00 | BRD | GOP-NRP | SAFEEN3000 ANCHOR PATTERN-GOP-NRP WEST BRIDGE INSTALLATION | A1 | 2026-02-13 | 2026-03-19 | 2026-03-05 | [12 empty] | 2026-03-05
1-GH0400-31-DWG-2498-00 | RIS-SP | DC4 | SAFEEN3000 ANCHOR PATTERN DURING RISER/SPOOL INSTALLATION AT DC/4 | A1 | 2026-02-13 | 2026-03-19 | 2026-03-05 | [12 empty] | 2026-03-05
1-GH0400-31-DWG-2482-00 | DECK | DC4 | SAFEEN3000 ANCHOR PATTERN-DC/4 TOP-SIDE & BRIDGE INSTALLATION | A1 | 2026-02-13 | 2026-03-19 | 2026-03-05 | [12 empty] | 2026-03-05
1-GH0400-31-DWG-2497-00 | BRD | DC4 | SAFEEN3000 ANCHOR PATTERN-DC/4 BRIDGE INSTALLATION | A1 | 2026-02-13 | 2026-03-19 | 2026-03-05 | [12 empty] | 2026-03-05
1-GH0100-31-DWG-2581-00 | RIS-SP | DC1 | SAFEEN3000 ANCHOR PATTERN-DC1 RISER/SPOOL INSTALLATION | A1 | 2026-03-05 | 2026-03-25 | 2026-07-08 | 00 | 2026-06-25 | davit clash needs to be checked | [9 empty] | davit clash needs to be checked
1-GH0100-31-DWG-2499-00 | DECK/BRG | DC1 | SAFEEN3000 ANCHOR PATTERN-DC/1 JACKET, TOP SIDE & BRIDGE INSTALLATION | 01 | 2026-02-27 |  | 2026-03-12 | 01 | 2026-03-31 |  | 2026-04-22 | waiting client CRS and installation drawings to issue REV02 | [7 empty] | waiting client CRS and installation drawings to issue REV02
1-GH6000-31-DWG-2500-00 | DECK | CLQ | SAFEEN-3000 ANCHOR PATTERN DURING CLQ JACKET & TOPSIDE INSTALLATION | 02 | 2026-02-13 | 2026-03-19 | 2026-03-04 | [12 empty] | 2026-03-04
1-GH5100-31-DWG-2476-00 | DECK | GOP-FLARE | SAFEEN3000 ANCHOR PATTERN- FLARE TOP SIDE INSTALLATION | A1 | 2026-02-13 | 2026-03-19 | 2026-03-12 | [12 empty] | 2026-03-12
1-GH5100-31-DWG-2477-00 | BRD | GOP-FLARE | SAFEEN3000 ANCHOR PATTERN- FLARE BRIDGE INSTALLATION | A1 | 2026-02-13 | 2026-03-19 | 2026-03-12 | [12 empty] | 2026-03-12
1-GH5100-31-DWG-2580-00 | FLR | GOP-FLARE | SAFEEN3000 ANCHOR PATTERN- FLARE BOOM INSTALLATION | A1 | 2026-02-13 | 2026-03-25 | 2026-03-12 | [12 empty] | 2026-03-12
1-GH5100-31-DWG-2647-00 | DECK | GOP-FLARE | SAFEEN3000 SET-UP PLAN AT GOP-FLARE MSF INSTALLATION | A1 | [15 empty] | A1
1-GH5100-31-DWG-2648-00 | BRD/FLR | GOP-FLARE | SAFEEN3000 SET-UP PLAN AT GOP-FLARE BRIDGE AND FLARE BOOM INSTALLATION | A1 | [15 empty] | A1
1-GH5100-31-DWG-2462-00 | DECK | GOP-SWI | SAFEEN3000 ANCHOR PATTERN-GOP-SWI TOP SIDE INSTALLATION | A1 | 2026-03-03 | 2026-03-19 | 2026-03-12 | [12 empty] | 2026-03-12
1-GH5100-31-DWG-2463-00 | BRD | GOP-SWI | SAFEEN3000 ANCHOR PATTERN-GOP-SWI BRIDGE INSTALLATION | A1 | 2026-03-03 | 2026-03-19 | 2026-03-12 | [12 empty] | 2026-03-12
1-GH5100-31-DWG-2646-00 | SP | GOP-SWI | SAFEEN3000 ANCHOR PATTERN-GOP-SWI SEAWATER OUTFALL SPOOLS INSTALLATION | A1 | [15 empty] | A1
1-CF0000-31-DWG-2524-00 | TIE-IN | HG-SP-28 | SAFEEN3000 ANCHOR PATTERN FOR MIDLINE TIEIN 34" GOP-SRP to OOP (HG-SP-28) | A1 | 2026-07-07 |  |  | sancheevi to modify working platform STBD side | [11 empty] | sancheevi to modify working platform STBD side
1-CF0000-31-DWG-2526-00 | TIE-IN | HG-SP-31 | SAFEEN3000 ANCHOR PATTERN FOR MIDLINE TIEIN 12" GOP-SRP to OOP (HG-SP-31) | 02 | 2026-07-07 |  | 2026-07-09 | sancheevi to modify working platform STBD side | [11 empty] | sancheevi to modify working platform STBD side
Total |  | 8 |  |  | 8 | [14 empty] | 8
Formulas:
LATEST STATUS = LOOKUP(2,1/([SOW]:INDEX(Table1[#This Row],COLUMN()-1)<>""),([SOW]:INDEX(Table1[#This Row],COLUMN()-1)))
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## APs DLS-4200
HAIL AND GHASHA DEVELOPMENT PROJECT
ANCHOR PATTERN STATUS
|  |  |  | CYCLE 01 |  |  |  | CYCLE 02 |  |  |  | CYCLE 03 |  |  |  | CYCLE 04
[6 empty] | CLT | ABL |  |  | CLT | ABL |  |  | CLT | ABL |  |  | CLT | ABL
anchor pattern NO | SOW | PF | Title | CYL#01 REV | CYL#01 ISSUE DATA | CYL#01 CRS STK#01 | CYL#01 CRS STK#02 | CYL#02 REV | CL#02 ISSUE DATE | CRS CYL#02 STK#01 | CRS CYL#02 STK#02 | CYL#03 REV | CYL#03 ISSUE DATE | CYL#03 CRS STK#01 | CYL#03 CRS STK#02 | CYL#04 REV | CL#04 ISSUE DATE | CRS CYL#04 STK#01 | CRS CYL#04 STK#02 | LATEST STATUS | NOTES
1-GH5100-31-DWG-2595-00 | DECK | GOP-SRP | DLS4200 ANCHOR PATTERN FOR TOPSIDE INSTALLATION AT GOP-SRP | A1 | 2026-06-24 | 2026-07-10 | 2026-07-08 | 00 | 2026-07-10 | [10 empty] | 2026-07-10
1-GH5100-31-DWG-2596-00 | BRD | GOP-SRP | DLS4200 ANCHOR PATTERN FOR NORTH BRIDGE INSTALLATION AT GOP-SRP | A1 | 2026-07-01 | 2026-07-16 | 2026-07-15 | 00 | 2026-07-09 | waiting for ABL reply to issue REV00 to client |  | X100 | 2026-07-16 |  | 2026-07-20 | 01 | 2026-07-28 |  |  | 2026-07-28
1-GH5100-31-DWG-2597-00 | BRD | GOP-SRP | DLS4200 ANCHOR PATTERN FOR SOUTH BRIDGE INSTALLATION AT GOP-SRP | A1 | 2026-07-01 | 2026-07-14 | 2026-07-08 | 00 | 2026-07-10 | [10 empty] | 2026-07-10
1-GH5100-31-DWG-2593-00 | RIS-SP | GOP-SRP | DLS4200 ANCHOR PATTERN FOR RISER-SPOOL INSTALLATION FROM DC6 AT GOP-SRP | A1 | 2026-04-10 | 2026-05-04 | 2026-05-07 | 00 | 2026-05-22 | 2026-06-04 | 2026-06-03 | 01 | 2026-06-11 |  | 2026-06-09 |  |  |  |  | 2026-06-09
1-GH5100-31-DWG-2594-00 | RIS-SP | GOP-SRP | DLS4200 ANCHOR PATTERN FOR RISER-SPOOL INSTALLATION FROM OPP AT GOP-SRP | A1 | 2026-04-10 | 2026-05-04 | 2026-05-07 | 00 | 2026-05-08 | 2026-05-25 | 2026-05-14 | [8 empty] | 2026-05-14
1-GH0600-31-DWG-2598-00 | RIS-SP | DC6 | DLS4200 ANCHOR PATTERN FOR RISER-SPOOL INSTALLATION AT DC6 | A1 | 2026-04-23 | 2026-05-07 | 2026-05-08 | 00 | 2026-06-04 |  | 2026-06-12 | waiting client CRS | [7 empty] | waiting client CRS
1-GH0600-31-DWG-2600-00 | DECK | DC6 | DLS4200 ANCHOR PATTERN FOR TOPSIDE & BRIDGE INSTALLATION AT DC6 | A1 | 2026-04-23 | 2026-05-07 | 2026-05-08 | 00 | 2026-06-23 | 2026-07-10 | 2026-07-06 | [8 empty] | 2026-07-06
1-GH5100-31-DWG-2601-00 | RIS-SP | GOP-NRP | DLS4200 ANCHOR PATTERN FOR RISER-SPOOL INSTALLATION AT GOP-NRP | A1 | 2026-04-23 | 2026-05-07 | 2026-05-14 | 00 | 2026-06-24 | 2026-07-10 |  | bagus to revise davit strops arrangement | [7 empty] | bagus to revise davit strops arrangement
1-GH5100-31-DWG-2602-00 | DECK | GOP-NRP | DLS4200 ANCHOR PATTERN FOR TOPSIDE INSTALLATION AT GOP-NRP | A1 | 2026-04-23 | 2026-05-15 | 2026-05-14 | 00 | waiting for lifting and installation drawings | [10 empty] | waiting for lifting and installation drawings
1-GH5100-31-DWG-2603-00 | BRD | GOP-NRP | DLS4200 ANCHOR PATTERN FOR EAST BRIDGE INSTALLATION AT GOP-NRP | A1 | 2026-04-23 | 2026-05-15 | 2026-05-14 | 00 | waiting for lifting and installation drawings | [10 empty] | waiting for lifting and installation drawings
1-GH5100-31-DWG-2604-00 | BRD | GOP-NRP | DLS4200 ANCHOR PATTERN FOR WEST BRIDGE INSTALLATION AT GOP-NRP | A1 | 2026-04-23 | 2026-05-15 | 2026-05-14 | 00 | waiting for lifting and installation drawings | [10 empty] | waiting for lifting and installation drawings
1-GH0400-31-DWG-2605-00 | RIS-SP | DC4 | DLS4200 ANCHOR PATTERN FOR RISER-SPOOL INSTALLATION AT DC4 | A1 | 2026-06-19 | 2026-07-10 | 2026-07-14 | 00 | 2026-07-09 | waiting ABL and client reply | [9 empty] | waiting ABL and client reply
1-GH0400-31-DWG-2606-00 | DECK | DC4 | DLS4200 ANCHOR PATTERN FOR TOPSIDE INSTALLATION AT DC4 | A1 | 2026-06-19 | 2026-07-10 | 2026-07-14 | 00 | 2026-07-09 | waiting ABL and client reply | [9 empty] | waiting ABL and client reply
1-GH0400-31-DWG-2607-00 | BRD | DC4 | DLS4200 ANCHOR PATTERN FOR BRIDGE INSTALLATION AT DC4 | A1 | 2026-06-19 | 2026-07-10 | 2026-07-14 | 00 | 2026-07-09 | waiting ABL and client reply | [9 empty] | waiting ABL and client reply
1-GH0100-31-DWG-2608-00 | RIS-SP | DC1 | DLS4200 ANCHOR PATTERN FOR RISER-SPOOL INSTALLATION AT DC1 | A1 | [15 empty] | A1
1-GH0100-31-DWG-2609-00 | DECK | DC1 | DLS4200 ANCHOR PATTERN FOR TOPSIDE & BRIDGE INSTALLATION AT DC1 | 01 | [15 empty] | 01
1-GH6000-31-DWG-2610-00 | DECK | CLQ | DLS4200 ANCHOR PATTERN FOR TOPSIDE INSTALLATION AT CLQ | A1 | 2026-06-19 |  | 2026-07-07 | waiting for ABL reply | [11 empty] | waiting for ABL reply
1-GH5100-31-DWG-2611-00 | DECK | GOP-FLARE | DLS4200 ANCHOR PATTERN FOR MSF INSTALLATION AT GOP-FLARE | A1 | 2026-06-19 | 2026-07-10 | 2026-07-07 | waiting for ABL reply | [11 empty] | waiting for ABL reply
1-GH5100-31-DWG-2612-00 | BRD | GOP-FLARE | DLS4200 ANCHOR PATTERN FOR BRIDGE INSTALLATION AT GOP-FLARE | A1 | 2026-06-19 |  | 2026-07-07 | waiting for ABL reply | [11 empty] | waiting for ABL reply
1-GH5100-31-DWG-2613-00 | FLR | GOP-FLARE | DLS4200 ANCHOR PATTERN FOR FLARE BOOM INSTALLATION AT GOP-FLARE | A1 | 2026-06-19 | 2026-07-10 | 2026-07-07 | waiting for ABL reply | [11 empty] | waiting for ABL reply
1-GH5100-31-DWG-2614-00 | DECK | GOP-SWI | DLS4200 ANCHOR PATTERN FOR TOPSIDE INSTALLATION AT GOP-SWI | A1 | 2026-06-19 |  | 2026-07-07 | 00 | issued for ABL only for review, waiting for lifting and installation drawing to modify REV00 | [10 empty] | issued for ABL only for review, waiting for lifting and installation drawing to modify REV00
1-GH5100-31-DWG-2615-00 | BRD | GOP-SWI | DLS4200 ANCHOR PATTERN FOR BRIDGE INSTALLATION AT GOP-SWI | A1 | 2026-06-19 |  | 2026-07-07 | 00 | issued for ABL only for review, waiting for lifting and installation drawing to modify REV00 | [10 empty] | issued for ABL only for review, waiting for lifting and installation drawing to modify REV00
1-GH5100-31-DWG-2616-00 | SP | GOP-SWI | DLS4200 ANCHOR PATTERN FOR SEAWATER OUTFALL SPOOLS INSTALLATION AT GOP-SWI | A1 | 2026-06-19 |  | 2026-07-07 | 00 | issued for ABL only for review, waiting for lifting and installation drawing to modify REV00 | [10 empty] | issued for ABL only for review, waiting for lifting and installation drawing to modify REV00
1-GH5100-31-DWG-2617-00 | TIE-IN | HG-SP-28 | DLS4200 ANCHOR PATTERN FOR MIDLINE TIEIN 34" GOP-SRP TO OOP (HG-SP-28) | A1 | under PMT reveiew | [14 empty] | under PMT reveiew
1-GH5100-31-DWG-2618-00 | TIE-IN | HG-SP-31 | DLS4200 ANCHOR PATTERN FOR MIDLINE TIEIN 12" GOP-SRP TO OOP (HG-SP-31) | A1 | under PMT reveiew | [14 empty] | under PMT reveiew
1-GH5100-31-DWG-2531-00 | HOOKUP | GOP-SRP | JACKUP SETUP ON GOP-SRP FOR HOOKUP ACTIVITIES | A1 | 2026-03-23 | 2026-04-07 | 2026-04-06 | 00 | 2026-06-29 | [10 empty] | 2026-06-29
1-GH0600-31-DWG-2537-00 | HOOKUP | DC6 | JACKUP SETUP ON DC6 FOR HOOKUP ACTIVITIES | A1 | 2026-03-23 | 2026-04-07 | 2026-04-06 | 00 | sancheevi to issue | [10 empty] | sancheevi to issue
1-GH5100-31-DWG-2532-00 | HOOKUP | GOP-NRP | JACKUP SETUP ON GOP-NRP FOR HOOKUP ACTIVITIES | A1 | sancheevi to issue | [14 empty] | sancheevi to issue
1-GH0400-31-DWG-2536-00 | HOOKUP | DC4 | JACKUP SETUP ON DC4 FOR HOOKUP ACTIVITIES | A1 | sancheevi to issue | [14 empty] | sancheevi to issue
1-GH0100-31-DWG-2535-00 | HOOKUP | DC1 | JACKUP SETUP ON DC1 FOR HOOKUP ACTIVITIES | A1 | sancheevi to issue | [14 empty] | sancheevi to issue
1-GH6000-31-DWG-2538-00 | HOOKUP | CLQ | JACKUP SETUP ON CLQ FOR HOOKUP ACTIVITIES | A1 | sancheevi to issue | [14 empty] | sancheevi to issue
1-GH5100-31-DWG-2534-00 | HOOKUP | GOP-FLARE | JACKUP SETUP ON GOP-FLARE FOR HOOKUP ACTIVITIES | A1 | sancheevi to issue | [14 empty] | sancheevi to issue
1-GH5100-31-DWG-2533-00 | HOOKUP | GOP-SWI | JACKUP SETUP ON GOP-SWI FOR HOOKUP ACTIVITIES | A1 | sancheevi to issue | [14 empty] | sancheevi to issue
Total |  | 6 |  |  | 6 | [14 empty] | 6
Formulas:
LATEST STATUS = LOOKUP(2,1/([SOW]:INDEX(Table14[#This Row],COLUMN()-1)<>""),([SOW]:INDEX(Table14[#This Row],COLUMN()-1)))
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## 1ST CAMPAIGN
HAIL AND GHASHA DEVELOPMENT PROJECT
ANCHOR PATTERN STATUS
[14 empty] | UPDATE | 2026-02-11 |  |  |  | 2025-08-13
anchor pattern NO | Activity | ISLAND | REV1 | REV1 ISSUE DATA | REV1 CLIENT CRS | REV1 ABL CRS | REV2 | REV2 ISSUE DATA | REV2 CLIENT CRS | REV2 ABL CRS | REV3 | REV3 ISSUE DATA | REV3 CLIENT CRS | REV3 ABL CRS | REV4 | REV4 ISSUE DATA | REV4 CLIENT CRS | REV4 ABL CRS | LATEST STATUS | REJECT
1-GH0600-31-DWG-2478-00 | JKT | DC6 | E1 | 2024-10-25 | 2025-01-23 |  | A1 | 2025-05-02 | 2025-05-27 | 2025-05-28 | 00 | 2025-05-30 | 2025-06-17 | 2025-06-10 | 01 | 2025-06-24 | 2025-07-04 | 2025-06-26 | 2025-06-26 | APPROVED
1-GH6000-31-DWG-2500-00 | JKT | CLQ | A1 | 2025-04-22 | 2025-05-19 | 2025-06-11 | 00 | 2025-06-11 | 2025-06-30 | 2025-06-17 | 01 | 03/07/2025 | 2025-07-23 | 2025-07-16 |  |  |  |  | 2025-07-16 | REQUIRE ACTION
1-GH5100-31-DWG-2464-00 | JKT | GOP-SRP | E1 | 2024-10-03 | 2025-01-23 |  | A1 | 23/04/2025 | 2025-05-20 | 2025-07-03 | 00 | 2025-07-04 | 00 (UNDER CLIENT REVIEW) | 2025-07-14 | 00 | 2025-07-22 | 2025-08-05 | 2025-08-05 | 2025-08-05
1-GH0400-31-DWG-2481-00 | JKT | DC4 | E1 | 2025-10-24 | 2025-01-23 |  | A1 | 2025-05-02 | 2025-05-27 | 2025-06-12 | 00 | 2025-06-19 | 00 (UNDER CLIENT REVIEW) | 2025-07-23 | 01 | 2025-07-21 | 2025-08-12 | 2025-08-12 | 2025-08-12
1-GH0100-31-DWG-2499-00 | JKT | DC1 | E1 | 2025-10-25 | 2025-01-23 |  | A1 | 2025-06-24 | 2025-07-23 | A1 (UNDER ABL REVIEW) | 00 | 2025-08-13 | 00 (UNDER CLIENT REVIEW) | 2025-08-19 | 2025-08-20 |  |  |  | 2025-08-20
1-GH5100-31-DWG-2475-00 | JKT | GOP-FLARE | A1 | 2025-06-24 | 2025-07-23 | 2025-08-22 | 00 | 12/08/2025 | 2025-09-18 | 2025-09-02 | [8 empty] | 2025-09-02
1-GH5100-31-DWG-2470-00 | JKT | GOP-NRP | A1 | 2025-11-28 | 2025-05-19 | 2025-08-14 | 00 | 15/08 | 2025-09-02 | 2025-09-04 | 01 | 2025-09-16 | 2025-09-29 | 2025-09-29 | 02 | 2025-09-30 | 00 (UNDER CLIENT REVIEW) | 2025-10-02 | 2025-10-02
1-GH5100-31-DWG-2461-00 | JKT | GOP-SWI | E1 | 2024-10-24 | 2025-01-23 |  | A1 | 2025-06-24 | 2025-07-23 | 2025-08-22 | 00 | 2025-08-22 | 2025-09-10 | 2025-09-29 | 01 | UNDER ISSUE |  |  | UNDER ISSUE
1-CF0000-31-DWG-2526-00 | AWTI | AWTI | A1 | 2025-09-23 | 2025-10-07 | 2025-10-08 | [12 empty] | 2025-10-08
Formulas:
LATEST STATUS = LOOKUP(2,1/([anchor pattern NO]:INDEX(Table13[#This Row],COLUMN()-1)<>""),([anchor pattern NO]:INDEX(Table13[#This Row],COLUMN()-1)))