## Sheet1
P2035 Umm Shaif - Installation Aids Register
Rev.19/12/2022
Ser. no. | Item Description | Qty. | Drawing Number | Drawing Issue Date | Material Delivery | Fabrication Start | Fabrication Completion | Fabrication Progress | Target Completion Date | Remarks
A | Rigid Pipelines
B | Subsea Spools and SSVSs
C | Concrete Sleepers
D | Concrete Mattresses
E | Flexible Pipelines
F | Umbilicals
G | P 2035 Cables 6.6 Kv & 11kV | QTY | Planned submission
1 | Top of J-Tube Pulling Quadrant | TBA
2 | Storage Quadrant | TBA
3 | Tugger Winch Securing detail | 1
4 | Temporary Hang Off Clamps (6.6kV & 11kV)) | TBA | 2024-09-20
5 | Cable Lay Tower (Safeen Pearl) (PETROKA) | 1 | 2024-09-20
6 | Deck Rollers | 1 | 2024-09-30
7 | Installation Chute | 1 | 2024-09-30
8 | Working Table | 1 | 2024-09-30
9 | Layout of cable on jacket | TBA
10 | A-frame | 0
11 | Half Moon | 0
12 | Compartments for the Carousel | 0
H | Pre-Commissioning
I | ICCPs