## PIPELINE & CABLE
|  | SAUDI ARABIAN OIL COMPANY - LONG TERM AGREEMENT (LTA) FOR OFFSHORE FACILITIES CRPO FOR JU'AYMAH OFFSHORE PLATFORM - BYPASS SYSTEM | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | NPCC PROJECT NO. 2171 (OOK)/ 2172 (IK) | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 2021-11-24
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPE STACKING ANALYSIS REPORT | 2171-2172-NN-RP-001 | A |  | 2022-01-02 | 2022-01-10 | CSE-2171-72-PMT-T-004 | 2022-01-14 | 2171-2172-NPCC-T-0878 | 2022-02-02 | CPD-JOPB-T-0156-22 | 2
|  |  | B |  |  | 2022-02-23 | CSE-2171-72-PMT-T-007 | 2022-03-02 | 2171-2172-NPCC-T-1034 | 2022-03-15 | CPD-JOPB-T-0387-22 | 1
2 | PIPELAY ANALYSIS REPORT FOR 48" BYPASS PIPELINES | 2171-2172-NN-RP-002 | A |  | 2022-01-03 | 2022-02-28 | CSE-2171-72-PMT-T-010 | 2022-03-04 | 2171-2172-NPCC-T-1048 | 2022-04-03 | CPD-JOPB-T-0494-22 | 2
|  |  | B |  |  | 2022-04-13 | CSE-2171-72-PMT-T-019 | 2022-04-14 | 2171-2172-NPCC-T-1171 | 2022-04-25 | CPD-JOPB-T-0629-22 | 1
|  |  | 00 |  |  | 2022-04-29 | CSE-2171-72-PMT-T-021 | 2022-04-29 | 2171-2172-NPCC-T-1227
3 | PIPELAY ANALYSIS REPORT FOR 48" BYPASS PIPELINE 2 FROM CLS 22 TIE-IN TO PLEM 31 / SPM 31 & PLEM 33 / SPM 33 | 2171-2172-NN-RP-003 |  |  | 2022-01-07
4 | PIPELAY ANALYSIS REPORT FOR 48" BYPASS PIPELINE 3 FROM CLS 23 TIE-IN TO PLEM 36 / SPM 36 | 2171-2172-NN-RP-004 |  |  | 2022-01-14
5 | PIPELAY ANALYSIS REPORT FOR 48" BYPASS PIPELINE 4 FROM CLS 24 TIE-IN TO PLEM 34 / SPM 34 & PLEM 35 / SPM 35 | 2171-2172-NN-RP-005 |  |  | 2022-01-21
6 | SPOOL LIFTING ANALYSIS REPORT FOR 48" BYPASS PIPELINE-1 | 2171-2172-NN-RP-006 | 1 | 2 | 2022-02-24 | 2023-01-06 | CSE-2171-72-PMT-T-052 | [10 empty] | govering by midline spool
7 | SPOOL LIFTING ANALYSIS REPORT FOR 48" BYPASS | 2171-2172-NN-RP-007 |  |  | 2022-02-27
8 | SPOOL LIFTING ANALYSIS REPORT FOR 48" BYPASS PIPELINE-2,3 & 4 BY TELFORD-25 | 2171-2172-NN-RP-008 | 1 | 2 | 2022-08-25 | 2023-01-25 | CSE-2171-72-PMT-T-060
9 | SPOOL LIFTING ANALYSIS REPORT FOR 48" BYPASS PIPELINE-4 | 2171-2172-NN-RP-009 |  |  | 2022-10-16
10 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF HTF, SSVS & SPOOLS ON CREST-287 | 2171-2172-NN-RP-010 | A | 3 | 2022-03-26 | 2022-08-03 | CSE-2171-72-PMT-T-030 | 2022-08-18 | 2171-2172-NPCC-T-1540 |  |  |  | 2022-08-18 | 2171-2172-NPCC-MWS-T-0016 | 2022-09-15 | BAS1178-TRN-018 | ACCEPTED WITH CONDITION
11 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF HTF, SSVS & SPOOLS ON MICLYN-259 | 2171-2172-NN-RP-011 | A | 3 | 2022-04-03 | 2022-08-03 | CSE-2171-72-PMT-T-029 | 2022-08-18 | 2171-2172-NPCC-T-1539 |  |  |  | 2022-08-18 | 2171-2172-NPCC-MWS-T-0015 | 2022-09-15 | BAS1178-TRN-019 | ACCEPTED WITH CONDITION
|  |  | B | 3 |  | 2022-10-07 | CSE-2171-72-PMT-T-035 | 2022-10-12 | 2171-2172-NPCC-T-1684 |  |  |  | 2022-10-12 | 2171-2172-NPCC-MWS-T-0018 | 2022-11-05 | BAS1178-TRN 019 | Approved
12 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CREST-287 | 2171-2172-NN-RP-012 | A | 3 | 2022-01-03 | 2022-03-16 | CSE-2171-72-PMT-T-012 | 2022-03-18 | 2171-2172-NPCC-T-1089 |  |  |  | 2022-03-18 | 2171-2172-NPCC-MWS-T-0003 | 2022-04-19 | BAS1178-TRN 004 | comments
13 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON MICLYN-259 | 2171-2172-NN-RP-013 | A | 3 | 2022-02-03 | 2022-03-24 | CSE-2171-72-PMT-T-016 | 2022-04-20 | 2171-2172-NPCC-T-1194 |  |  |  | 2022-04-20 | 2171-2172-NPCC-MWS-T-0007 | 2022-05-19 | BAS1178-TRN 011 | ACCEPTED WITH CONDITION
14 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CREST-287 | 2171-2172-NN-RP-014 | A | 3 | 2022-01-03 | 2022-03-23 | CSE-2171-72-PMT-T-015 | 2022-03-28 | 171-2172-NPCC-T-1099 |  |  |  | 2022-03-28 | 2171-2172-NPCC-MWS-T-0005 | 2022-04-19 | BAS1178-TRN 007 | comments
15 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF STINGER & MISC. ITEMS ON ALLIANZ CB-250 | 2171-2172-NN-RP-015 | A | 3 | 2022-01-03 | 2022-03-31 | CSE-2171-72-PMT-T-018 | 2022-04-03 | 2171-2172-NPCC-T-1137 |  |  |  | 2022-04-03 | 2171-2172-NPCC-MWS-T-0006 | 2022-04-19 | BAS1178-TRN 009 | comments
16 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON GOGAS-252. | 2171-2172-NN-RP-016 | A | 3 |  | 2022-05-18 | CSE-2171-72-PMT-T-022 | 2022-05-19 | 2171-2172-NPCC-T-1272 |  |  |  | 2022-05-19 | 2171-2172-NPCC-MWS-T-0009 | 2022-05-29 | BAS1178-TRN 013 | ACCEPTED WITH CONDITION
17 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON PFC-02 | 2171-2172-NN-RP-017 | A | 3 |  | 2022-05-18 | CSE-2171-72-PMT-T-023 | 2022-05-19 | 2171-2172-NPCC-T-1270 |  |  |  | 2022-05-19 | 2171-2172-NPCC-MWS-T-0008 | 2022-05-29 | BAS1178-TRN 015 | ACCEPTED WITH CONDITION
18 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF HTF & MISC. ITEMS ON MICLYN-258 | 2171-2172-NN-RP-018 | A | 3 |  | 2022-08-24 | CSE-2171-72-PMT-T-032 | [5 empty] | -- | -- | 2022-08-26 | BAS-1178-TRN-016 | Approved
19 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF FLUSHING EQP. & MISC. ITEMS ON MICLYN-258 | 2171-2172-NN-RP-019 | A | 3 |  | 2022-10-11 | CSE-2171-72-PMT-T-036
|  |  | B | 3 |  | 2023-06-08 | CSE-2171-72-PMT-T-066 | [5 empty] | -- | Email from Hisham Qazani | 2023-06-12 | BAS1178-TRN 030 | ACCEPTED WITH CONDITION
20 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF TANK, SSVS & SPOOLS ON GAC-81 | 2171-2172-NN-RP-020 | A | 3 |  | 2022-11-15 | CSE-2171-72-PMT-T-039 | 2022-11-18 | 2171-2172-NPCC-T-1731 |  |  |  | 2022-11-18 | 2171-2172-NPCC-MWS-T-0021 | 2022-11-21 | BAS1178-TRN 023 | ACCEPTED WITH CONDITION
21 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SSVS, SPOOLS & SHROUD ON CREST-287 | 2171-2172-NN-RP-021 | A | 3 |  | 2022-12-21 | CSE-2171-72-PMT-T-046 | 2022-12-21 | 2171-2172-NPCC-T-1767 |  |  |  | 2022-12-21 | 2171-2172-NPCC-MWS-T-0025
22 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS ON GOGAS-250 | 2171-2172-NN-RP-022 | A | 3 |  | 2022-12-27 | CSE-2171-72-PMT-T-049 | 2022-12-27 | 2171-2172-NPCC-T-1771 |  |  |  | 2022-12-27 | 2171-2172-NPCC-MWS-T-0028 | 2023-01-06 | BAS1178-TRN 026 | ACCEPTED WITH CONDITION
23 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SSVS, SPOOLS AND SLEEPERS ON EOS-283 | 2171-2172-NN-RP-023 | A | 3 |  | 2022-12-29 | CSE-2171-72-PMT-T-050 | 2022-12-29 | 2171-2172-NPCC-T-1774 |  |  |  | 2022-12-29 | 2171-2172-NPCC-MWS-T-0030 | 2023-01-06 | BAS1178-TRN 028 | ACCEPTED WITH CONDITION
24 | SEAFASTENING DESIGN REPORT FOR MATERIAL TEMPORARY STORAGE ON LB-II | 2171-2172-NN-RP-024 | A | 3 |  | 2023-05-25 | CSE-2171-72-PMT-T-065 | 2023-05-29 | 2171-2172-NPCC-T-1865 |  |  |  | 2023-05-29 | 2171-2172-NPCC-MWS-T-0031 | 2023-06-14 | BAS1178-TRN 032 | ACCEPTED WITH CONDITION
25 | SEAFASTENING DESIGN REPORT FOR HOT TAP FRAME TRANSPORTATION ON CB-6 | 2171-2172-NN-RP-025 | A | 3 |  | 2023-07-13 | CSE-2171-72-PMT-T-069
26 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SSVS AND SPOOLS ON EOS 283 | 2171-2172-NN-RP-026 | A | 3 |  | 2024-01-30 | CSE-2171-72-PMT-T-073 | 2024-01-31 | 2171-2172-NPCC-T-1971 |  |  |  | 2024-01-31 | 2171-2172-NPCC-MWS-T-0034 | 2024-02-07 | BAS1178-TRN 035 | ACCEPTED WITH CONDITION
27 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS AND SLEEPERS ON GAC -81 | 2171-2172-NN-RP-027 | A | 3 |  | 2024-02-06 | CSE-2171-72-PMT-T-075 | 2024-04-21 | 2171-2172-NPCC-T-2017 |  |  |  | 2024-04-19 | 2171-2172-NPCC-MWS-T-0036 | 2024-04-21 | BAS1178-TRN 038 | ACCEPTED WITH CONDITION
28 | SEAFASTENING DESIGN REPORT FOR GAC-81 WITH HOT TAP FRAMES & LAY DOWN HEADS ONBOARD | 2171-2172-NN-RP-028 | A |  |  | 2024-08-15 | CSE-2171-72-PMT-T-085 | [5 empty] | 2024-08-23 | 2171-2172-NPCC-MWS-T-0039 | 2024-09-07 | BAS1178-TRN 040 | ACCEPTED WITH CONDITION

## Documents - Naval & Marine
|  | SAUDI ARABIAN OIL COMPANY - LONG TERM AGREEMENT (LTA) FOR OFFSHORE FACILITIES CRPO FOR JU'AYMAH OFFSHORE PLATFORM - BYPASS SYSTEM | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | NPCC PROJECT NO. 2171 (OOK)/ 2172 (IK) | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (NAVAL & MARINE) | [10 empty] | DATE : |  |  |  | 2021-11-24
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | MOORING ANALYSIS FOR DLB-750 DURING LAYING OF PIPELINE #1 & 2 | 2171-2172-ZZ-CL-001 | A | 2 | 2022-01-03 | 2022-03-08 | CSE-2171-72-PMT-T-011 | 2022-03-10 | 2171-2172-NPCC-T-1061 | 2022-03-24 | CPD-JOPB-T-0438-22 | 5 | 2022-03-10 | 2171-2172-NPCC-MWS-T-0001 | 2022-04-19 | BAS1178-TRN 001 | comments | suby
2 | MOORING ANALYSIS FOR DLB-750 DURING LAYING OF PIPELINE # 3 | 2171-2172-ZZ-CL-002 | A | 2 | 2022-01-07 | 23/02/2022 10/03/2022 | CSE-2171-72-PMT-T-008 | 2022-03-15 | 2171-2172-NPCC-T-1070 | 2022-03-31 | CPD-JOPB-T-0476-22 | 5 | 2022-03-15 | 2171-2172-NPCC-MWS-T-0002 | 2022-04-19 | BAS1178-TRN 002 | comments | doc. modified on 10/03
3 | MOORING ANALYSIS DURING WEATHER STANDBY POSITION FOR PIPELINE - 1 & 2 | 2171-2172-ZZ-CL-003 | A | 2 | 2022-01-14 | 2022-03-17 | CSE-2171-72-PMT-T-014 | 2022-03-23 | 2171-2172-NPCC-T-1098 | 2022-04-05 | CPD-JOPB-T-0503-22 | 5 | 2022-03-23 | 2171-2172-NPCC-MWS-T-0004 | 2022-04-19 | BAS1178-TRN 005 | comments
4 | MOORING ANALYSIS DURING WEATHER STANDBY POISITION FOR PIPELINE - 3 & 4 | 2171-2172-ZZ-CL-004 | A | 2 | 2022-01-21 | 2022-03-29 | CSE-2171-72-PMT-T-017
5 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP1 AT CREST 287 | 2171-2172-ZZ-CL-005 | A | 3 | 2022-01-03 | 2022-03-16 | CSE-2171-72-PMT-T-012 | 2022-03-18 | 2171-2172-NPCC-T-1089 |  |  |  | 2022-03-23 | 2171-2172-NPCC-MWS-T-0003 | 2022-04-19 | BAS1178-TRN 003 | comments
6 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-2 @ MICLYIN 259 | 2171-2172-ZZ-CL-006 | A | 3 | 2022-02-03 | 2022-03-24 | CSE-2171-72-PMT-T-016 | 2022-04-20 | 2171-2172-NPCC-T-1194 |  |  |  | 2022-04-20 | 2171-2172-NPCC-MWS-T-0007 | 2022-05-19 | BAS1178-TRN 010 | ACCEPTED WITH CONDITION
7 | STABILITY ANALYSIS FOR TRANSPORTATION OF HOT TAP FRAME, VALVE SKID & SPOOLS FOR CFL-32 @ CREST 287 | 2171-2172-ZZ-CL-007 | A | 3 | 2022-03-26 | 2022-08-15 | CSE-2171-72-PMT-T-030 | 2022-08-18 | 2171-2172-NPCC-T-1540 |  |  |  | 2022-08-18 | 2171-2172-NPCC-MWS-T-0016 | 2022-09-15 | BAS1178-TRN-022 | ACCEPTED WITH CONDITION
8 | STABILITY ANALYSIS FOR TRANSPORTATION OF HOT TAP FRAME, VALVE SKID & SPOOLS FOR CLS-22 @ MICLYIN-259 | 2171-2172-ZZ-CL-008 | A | 3 | 2022-04-03 | 2022-08-15 | CSE-2171-72-PMT-T-029 | 2022-08-18 | 2171-2172-NPCC-T-1539 |  |  |  | 2022-08-18 | 2171-2172-NPCC-MWS-T-0015 | 2022-09-15 | BAS1178-TRN-021 | ACCEPTED WITH CONDITION
|  |  | B | 3 |  | 2022-10-07 | CSE-2171-72-PMT-T-035 | 2022-10-12 | 2171-2172-NPCC-T-1684 |  |  |  | 2022-10-12 | 2171-2172-NPCC-MWS-T-0018 | 2022-10-25 | BAS1178-TRN 021 | ACCEPTED WITH CONDITION
|  |  | C | 3 |  | 2023-05-18 | CSE-2171-72-PMT-T-064 | [5 empty] | 2023-05-18 | EMAIL | 2023-05-19 | BAS1178-TRN 029 | ACCEPTED WITH CONDITION
9 | STABILITY ANALYSIS FOR TRANSPORTATION OF CONCRETE SLEEPERS @ CREST 287 | 2171-2172-ZZ-CL-009 | A | 3 | 2022-01-03 | 2022-03-23 | CSE-2171-72-PMT-T-015 | 2022-03-28 | 2171-2172-NPCC-T-1099 |  |  |  | 2022-03-28 | 2171-2172-NPCC-MWS-T-0005 | 2022-04-19 | BAS1178-TRN 006 | comments
10 | MOORING ANALYSIS DURING SPOOL INSTALLATIONS FOR PIPELINE 1 & 2 | 2171-2172-ZZ-CL-010 |  |  | 2022-02-24
11 | MOORING ANALYSIS DURING SPOOL INSTALLATIONS FOR PIPELINE 3 & 4 | 2171-2172-ZZ-CL-011 |  |  | 2022-02-27
12 | STABILITY ANALYSIS DURING TRANSPORTATION OF VALVE SKIDS, SPOOLS & SHROUDS @ LB-II | 2171-2172-ZZ-CL-012 | A | 3 |  | 2023-05-25 | CSE-2171-72-PMT-T-065 | 2023-05-29 | 2171-2172-NPCC-T-1865 |  |  |  | 2023-05-29 | 2171-2172-NPCC-MWS-T-0031 | 2023-06-16 | BAS1178-TRN 033 | OPEN COMMENTS
13 | MOORING ANALYSIS DURING SUBSEA VALVE SKID & SPOOLS INSTALLATION AT CLS-21 INSTALLATION AT CLS-21 | 2171-2172-ZZ-CL-013 | A | 2 |  | 2022-12-13 | CSE-2171-72-PMT-T-043 | 2022-12-15 | 2171-2172-NPCC-T-1763 |  |  |  | 2022-12-15 | 2171-2172-NPCC-MWS-T-0024 |  |  |  | prashanth
14 | STABILITY ANALYSIS DURING TRANSPORTATION OF STINGER X SEC A AND MISC ITEMS @ ALLIANZ CB-250 | 2171-2172-ZZ-CL-014 | A | 3 |  | 2022-03-31 | CSE-2171-72-PMT-T-018 | 2022-04-03 | 2171-2172-NPCC-T-1137 |  |  |  | 2022-04-03 | 2171-2172-NPCC-MWS-T-0006 | 2022-04-19 | BAS1178-TRN 008 | comments
15 | STABILITY ANALYSIS FOR PFC-02 DURING TRANSPORTATION OF 48INCH PIPES FOR SPOOL | 2171-2172-ZZ-CL-015 | A | 3 |  | 2022-05-18 | CSE-2171-72-PMT-T-023 | 2022-05-19 | 2171-2172-NPCC-T-1270 |  |  |  | 2022-05-19 | 2171-2172-NPCC-MWS-T-0008 | 2022-05-29 | BAS1178-TRN 014 | ACCEPTED WITH CONDITION
16 | STABILITY ANALYSIS FOR TRANSPORTATION OF CC PIPES TRIP-3 @ GOGAS-252 | 2171-2172-ZZ-CL-016 | A | 3 |  | 2022-05-18 | CSE-2171-72-PMT-T-022 | 2022-05-19 | 2171-2172-NPCC-T-1272 |  |  |  | 2022-05-19 | 2171-2172-NPCC-MWS-T-0009 | 2022-05-29 | BAS1178-TRN 012 | ACCEPTED WITH CONDITION
17 | STABILITY ANALYSIS FOR CARGO BARGE MICLYN-258 | 2171-2172-ZZ-CL-017 | A | 3 |  | 2022-08-24 | CSE-2171-72-PMT-T-032 | [5 empty] | -- | -- | 2022-08-26 | BAS1178-TRN-017 | ACCEPTED WITH CONDITION
|  |  | B | 3 |  | 2022-10-11 | CSE-2171-72-PMT-T-036
|  |  | C | 3 |  | 2023-06-08 | CSE-2171-72-PMT-T-066 | [5 empty] | -- | Email from Hisham Qazani | 2023-06-12 | BAS1178-TRN 031 | ACCEPTED WITH CONDITION
18 | STABILITY ANALYSIS DURING TRANSPORTATION OF VALVE SKID, SPOOLS & CABLE TANK FOR CLS-21 @ GAC-81 | 2171-2172-ZZ-CL-018 | A | 3 |  | 2022-11-15 | CSE-2171-72-PMT-T-039 | 2022-11-18 | 2171-2172-NPCC-T-1731 |  |  |  | 2022-11-18 | 2171-2172-NPCC-MWS-T-0021 | 2022-11-21 | BAS1178-TRN 024 | ACCEPTED WITH CONDITION
19 | MOORING ANALYSIS DURING SUBSEA VALVE SKID & SPOOLS INSTALLATION AT CLS-24 | 2171-2172-ZZ-CL-019 | A | 2 |  | 2022-12-12 | CSE-2171-72-PMT-T-042 | 2022-12-15 | 2171-2172-NPCC-T-1762 |  |  |  | 2022-12-15 | 2171-2172-NPCC-MWS-T-0023
20 | STABILITY ANALYSIS FOR TRANSPORTATION OF VALVE SKID, SPOOLS, SHROUDS & SLEEPERS FOR CFL-33 & 35 @ EOS-283 | 2171-2172-ZZ-CL-020 | A | 3 |  | 2022-12-20 | CSE-2171-72-PMT-T-045 | 2022-12-21 | 2171-2172-NPCC-T-1768 |  |  |  | 2022-12-22 | 2171-2172-NPCC-MWS-T-0026 | 2023-01-06 | BAS1178-TRN 027 | ACCEPTED WITH CONDITION
21 | STABILITY ANALYSIS FOR TRANSPORTATION OF SPOOLS & SHROUDS @ GOGAS-250 | 2171-2172-ZZ-CL-021 | A | 3 |  | 2022-12-22 | CSE-2171-72-PMT-T-047 | 2022-12-23 | 2171-2172-NPCC-T-1770 |  |  |  | 2022-12-23 | 2171-2172-NPCC-MWS-T-0027 | 2023-01-06 | BAS1178-TRN 025 | ACCEPTED WITH CONDITION
22 | MOORING ANALYSIS DURING REMEDIAL WORK RECTIFICATION OF HOT TAPPING OPERATION AT CFL-34 | 2171-2172-ZZ-CL-022 | A | 2 |  | 2023-07-10 | CSE-2171-72-PMT-T-068 | [5 empty] | 2023-07-15 | 2171-2172-NPCC-MWS-T-0033 | 2023-07-20 | BAS1178-TRN 034 | comments
|  |  | B | 2 |  | 2023-07-28 | CSE-2171-72-PMT-T-070 | [5 empty] | 2023-07-28 | email | 2023-08-02 | BAS1178-TRN 034 | ACCEPTED WITH CONDITION
23 | STABILITY ANALYSIS FOR CARGO BARGE CB-6 | 2171-2172-ZZ-CL-023 | A | 3 |  | 2023-07-13 | CSE-2171-72-PMT-T-069
24 | STABILITY ANALYSIS FOR CARGO BARGE EOS-283 LOADED WITH VALVE SKIDS, SPOOLS AND SHROUDS | 2171-2172-ZZ-CL-024 | A | 3 |  | 2024-01-30 | CSE-2171-72-PMT-T-073 | 2024-01-31 | 2171-2172-NPCC-T-1971 |  |  |  | 2024-01-31 | 2171-2172-NPCC-MWS-T-0034 | 2024-02-14 | BAS1178-TRN 036 | ACCEPTED WITH CONDITION
25 | STABILITY ANALYSIS FOR CARGO BARGE GAC-81 LOADED WITH SLEEPERS AND SPOOLS | 2171-2172-ZZ-CL-025 | A | 3 |  | 2024-02-06 | CSE-2171-72-PMT-T-075 | 2024-04-21 | 2171-2172-NPCC-T-2017 |  |  |  | 2024-04-19 | 2171-2172-NPCC-MWS-T-0036 | 2024-04-21 | BAS1178-TRN 037 | ACCEPTED WITH CONDITION
26 | STABILITY ANALYSIS FOR CARGO BARGE GAC-81 WITH HOT TAP FRAMES & LAY DOWN HEADS ONBOARD | 2171-2172-ZZ-CL-026 | A | 3 |  | 2024-08-14 | CSE-2171-72-PMT-T-084 | [5 empty] | 2024-08-23 | 2171-2172-NPCC-MWS-T-0039 | 2024-09-07 | BAS1178-TRN 039 | ACCEPTED WITH CONDITION
|  |  | B | 3 |  | 2024-09-20 | CSE-2171-72-PMT-T-088
27

## DRAWINGS
|  | SAUDI ARABIAN OIL COMPANY - LONG TERM AGREEMENT (LTA) FOR OFFSHORE FACILITIES CRPO FOR JU'AYMAH OFFSHORE PLATFORM - BYPASS SYSTEM | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | NPCC PROJECT NO. 2171 (OOK)/ 2172 (IK) | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 2021-11-24
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | START UP HEAD (LAUNCHER) DETAILS FOR 48" BYPASS PIPELINE 3 & 4 (SUH-T1) | 2171-2172-NN-0001 | A | 3 | 2022-01-14 | 04/11/2021 12/01/2022 | CSE-2171-72-PMT-T-005 | 2022-01-14 | 2171-2172-NPCC-T-0879
|  |  | B | 3 |  | 2022-02-02 | CSE-2171-72-PMT-T-006 | 2022-02-02 | 2171-2172-NPCC-T-0942
|  |  | C | 3 |  | 2022-04-15 | CSE-2171-72-PMT-T-020 | 2022-04-15 | 2171-2172-NPCC-T-1175
2 | START UP HEAD (LAUNCHER) DETAILS FOR 48" BYPASS PIPELINE 1 & 2 SEG-A & B (SUH-T2) | 2171-2172-NN-0002 | A | 3 | 2022-01-03 | 04/11/2021 12/01/2022 | CSE-2171-72-PMT-T-005 | 2022-01-14 | 2171-2172-NPCC-T-0879
|  |  | B | 3 |  | 2022-02-02 | CSE-2171-72-PMT-T-006 | 2022-02-02 | 2171-2172-NPCC-T-0942
3 | LAYDOWN HEAD (RECEIVER) DETAILS FOR 48" BYPASS PIPELINE 3 & 4 (LDH-T1) | 2171-2172-NN-0003 | A | 3 | 2022-01-14 | 04/11/2021 12/01/2022 | CSE-2171-72-PMT-T-005 | 2022-01-14 | 2171-2172-NPCC-T-0879
|  |  | B | 3 |  | 2022-02-02 | CSE-2171-72-PMT-T-006 | 2022-02-02 | 2171-2172-NPCC-T-0942
|  |  | C | 3 |  | 2022-04-15 | CSE-2171-72-PMT-T-020 | 2022-04-15 | 2171-2172-NPCC-T-1175
4 | LAYDOWN HEAD (LAUNCHER) DETAILS FOR 48" BYPASS PIPELINE 1 & 2 SEG-A (LDH-T2) | 2171-2172-NN-0004 | A | 3 | 2022-01-03 | 04/11/2021 12/01/2022 | CSE-2171-72-PMT-T-005 | 2022-01-14 | 2171-2172-NPCC-T-0879
|  |  | B | 3 |  | 2022-02-02 | CSE-2171-72-PMT-T-006 | 2022-02-02 | 2171-2172-NPCC-T-0942
|  |  | C | 3 |  | 2022-04-15 | CSE-2171-72-PMT-T-020 | 2022-04-15 | 2171-2172-NPCC-T-1175
5 | LAYDOWN HEAD (RECEIVER) DETAILS FOR 48" BYPASS PIPELINE 1 & 2 @ SEG-B (LDH-T3) | 2171-2172-NN-0005 | A | 3 | 2022-01-03 | 04/11/2021 12/01/2022 | CSE-2171-72-PMT-T-005 | 2022-01-14 | 2171-2172-NPCC-T-0879
|  |  | B | 3 |  | 2022-02-02 | CSE-2171-72-PMT-T-006 | 2022-02-02 | 2171-2172-NPCC-T-0942
|  |  | C | 3 |  | 2022-04-15 | CSE-2171-72-PMT-T-020 | 2022-04-15 | 2171-2172-NPCC-T-1175
6 | EMERGENCY LAYDOWN HEAD FOR 48" BYPASS PIPELINES | 2171-2172-NN-0006 | A | 3 | 2022-01-03 | 04/11/2021 12/01/2022 | CSE-2171-72-PMT-T-005 | 2022-01-14 | 2171-2172-NPCC-T-0879
|  |  | B | 3 |  | 2022-02-02 | CSE-2171-72-PMT-T-006 | 2022-02-02 | 2171-2172-NPCC-T-0942
7 | LOADING ARRANGEMENT FOR TRANSPORTATION OF CONCRETE PIPE (CB-1) | 2171-2172-NN-0007 |  |  | 2022-01-03
8 | LOADING ARRANGEMENT FOR TRANSPORTATION OF CONCRETE PIPE (CB-2) | 2171-2172-NN-0008 |  |  | 2022-02-03
9 | LOADING ARRANGEMENT FOR TRANSPORTATION OF CONCRETE PIPE (CB-3) | 2171-2172-NN-0009 |  |  | 2022-03-03
10 | LOADING ARRANGEMENT FOR TRANSPORTATION OF SUBSEA SPOOLS AND VALVE SKIDS (TRIP-1) | 2171-2172-NN-0010 |  |  | 2022-03-26
11 | LOADING ARRANGEMENT FOR TRANSPORTATION OF SUBSEA SPOOLS AND VALVE SKIDS (TRIP-2) | 2171-2172-NN-0011 |  |  | 2022-04-03
12 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ CREST 287 | 2171-2172-NN-0012 | A | 3 | 2022-03-23 | 2022-03-23 | CSE-2171-72-PMT-T-015 | 2022-03-28 | 171-2172-NPCC-T-1099 |  |  |  | 2022-03-28 | 2171-2172-NPCC-MWS-T-0005 | 2022-04-19 | BAS1178-TRN 007 | comments
13 | LOADING ARRANGEMENT & SEAFASTENING, DETAILS OF VALVE SKID, SPOOLS, SHROUDS & CONCRETE SLEEPERS FOR CFL-33 & CFL-35 @ EOS-283 | 2171-2172-NN-0013 | A | 3 | 2022-12-12 | 2022-12-12 | CSE-2171-72-PMT-T-041 | 2022-12-13 | 2171-2172-NPCC-T-1761 |  |  |  | 2022-12-13 | 2171-2172-NPCC-MWS-T-0022
|  |  | B | 3 |  | 2022-12-29 | CSE-2171-72-PMT-T-050 | 2022-12-29 | 2171-2172-NPCC-T-1774 |  |  |  | 2022-12-29 | 2171-2172-NPCC-MWS-T-0030
|  |  | C | 3 |  | 2023-05-03 | CSE-2171-72-PMT-T-062
14 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE-4 SPOOL G.A-2 FOR BYPASS PIPELINE-4 FOR CROSSING CFL35 PIPELINE | 2171-2172-NN-0014 | A | 3 | 2023-01-13 | 2023-01-13 | CSE-2171-72-PMT-T-056
15 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE-4 SPOOL G.A AT CLS 24 (JOP) | 2171-2172-NN-0015 | A | 3 |  | 2023-01-16 | CSE-2171-72-PMT-T-057
16 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE-3 SPOOL G.A AT CFL36E (PLEM36 / SPM36) | 2171-2172-NN-0016 | A | 3 |  | 2023-01-18 | CSE-2171-72-PMT-T-059
17 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE-4 SPOOL G.A AT CFL35E (PLEM35 / SPM35) | 2171-2172-NN-0017 | A | 3 |  | 2023-01-18 | CSE-2171-72-PMT-T-058
18 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE SPOOL G.A FOR BYPASS P/L-2 AT CFL31W (PLEM31/SPM31) | 2171-2172-NN-0018 | A | 3 | 2023-01-13 | 2023-01-09 | CSE-2171-72-PMT-T-053 | 2023-01-15 | 2171-2172-NPCC-T-1786
19 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE FOR BYPASS P/L-2 FOR CROSSING CFL32 PIPELINE | 2171-2172-NN-0019 | A | 3 | 0 | 2023-01-09 | CSE-2171-72-PMT-T-053 | 2023-01-15 | 2171-2172-NPCC-T-1786
20 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE SPOOL G.A-2 FOR BYPASS P/L-2 NEAR CFL33W(PLEM33/SPM33) | 2171-2172-NN-0020 | A |  | 0 | 2023-01-05 | CSE-2171-72-PMT-T-051 | 2023-01-15 | 2171-2172-NPCC-T-1786
21 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE SPOOL G.A-3 FOR BYPASS P/L-2 NEAR CFL33W(PLEM33/SPM33) | 2171-2172-NN-0021 | A |  | 0 | 2023-01-05 | CSE-2171-72-PMT-T-051 | 2023-01-15 | 2171-2172-NPCC-T-1786
22 | TYPICAL LIFTING OF CONCRETE SLEEPERS FOR PIPELINE CROSSINGS | 2171-2172-NN-0022 | A | 3 | 2022-02-25 | 2022-02-25 | CSE-2171-72-PMT-T-009 | 2022-03-10 | 2171-2172-NPCC-T1068
23 | TYPICAL LIFTING OF CONCRETE MATTRESS | 2171-2172-NN-0023 |  |  | 2022-02-01
24 | LOADING ARRANGMENT FOR STINGER TRANSPORTATION | 2171-2172-NN-0024 |  |  | 2022-01-03
30 | FLANGE PROTECTOR DETAILS FOR 48” BYPASS PIPELINE | 2171-2172-NN-0030 | A | 3 |  | 2022-01-12 | CSE-2171-72-PMT-T-005 | 2022-01-14 | 2171-2172-NPCC-T-0879
31 | LOADING ARRANGEMENT & SEAFASTENING, DETAILS OF CC PIPES TRIP-1 @ CREST 287 | 2171-2172-NN-0031 | A | 3 |  | 2022-03-16 | CSE-2171-72-PMT-T-012 | 2022-03-18 | 2171-2172-NPCC-T-1089 |  |  |  | 2022-03-18 | 2171-2172-NPCC-MWS-T-0003 | 2022-04-19 | BAS1178-TRN 004 | comments
32 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES TRIP-2 @ MICLYN-259 | 2171-2172-NN-0032 | A | 3 |  | 2022-03-24 | CSE-2171-72-PMT-T-016 | 2022-04-20 | 2171-2172-NPCC-T-1194 |  |  |  | 2022-04-20 | 2171-2172-NPCC-MWS-T-0007 | 2022-05-19 | BAS1178-TRN 011 | ACCEPTED WITH CONDITION
33 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES TRIP-3 @ GOGAS-252 | 2171-2172-NN-0033 | A | 3 |  | 2022-05-18 | CSE-2171-72-PMT-T-022 | 2022-05-19 | 2171-2172-NPCC-T-1272 |  |  |  | 2022-05-19 | 2171-2172-NPCC-MWS-T-0009 | 2022-05-29 | BAS1178-TRN 013 | ACCEPTED WITH CONDITION
34 | LIFTING AND INSTALLATION OF 56" SUBSEA VALVE SKID (CLS-22) | 2171-2172-NN-0034 | A | 3 |  | 2022-03-16 | CSE-2171-72-PMT-T-013
35 | LIFTING AND INSTALLATION OF 56" SUBSEA VALVE SKID WITH SPOOLS (CLS-21) | 2171-2172-NN-0035
36 | LIFTING AND INSTALLATION OF 56" SUBSEA VALVE SKID WITH SPOOLS (CLS-23) | 2171-2172-NN-0036
37 | LIFTING AND INSTALLATION OF 56" SUBSEA VALVE SKID WITH SPOOLS (CLS-24) | 2171-2172-NN-0037
38 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF STINGER-X SEC (A) & MISC. ITEMS @ CARGO BARGE ALLIANZ - CB250 | 2171-2172-NN-0038 | A | 3 |  | 2022-03-31 | CSE-2171-72-PMT-T-018 | 2022-04-03 | 2171-2172-NPCC-T-1137 |  |  |  | 2022-04-03 | 2171-2172-NPCC-MWS-T-0006 | 2022-04-19 | BAS1178-TRN 009 | comments
39 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SPOOLS CC PIPES @ PFC-02 | 2171-2172-NN-0039 | A | 3 |  | 2022-05-18 | CSE-2171-72-PMT-T-023 | 2022-05-19 | 2171-2172-NPCC-T-1270 |  |  |  | 2022-05-19 | 2171-2172-NPCC-MWS-T-0008 | 2022-05-29 | BAS1178-TRN 015 | ACCEPTED WITH CONDITION
40 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE 1 & 2 AT MIDLINE TIE-IN | 2171-2172-NN-0040 | A | 3 |  | 29/06/2022 09/08/2022 | CSE-2171-72-PMT-T-031 | 2022-08-17 | 2171-2172-NPCC-T-1537
|  |  | B | 3 |  | 2023-01-06 | CSE-2171-72-PMT-T-052
41 | LOADING ARRANGEMENT & SEAFASTENING, DETAILS OF CC PIPES TRIP-4 @ CREST 287 | 2171-2172-NN-0041 | A | 3 |  | 2022-06-15 | CSE-2171-72-PMT-T-024 | 2022-06-16 | 2171-2172-NPCC-T-1391 |  |  |  | 2022-06-16 | 2171-2172-NPCC-MWS-T-0010
42 | LOADING ARRANGEMENT & SEAFASTENING, DETAILS OF CC PIPES TRIP-5 @ MICLYN-259 | 2171-2172-NN-0042 | A | 3 |  | 2022-06-17 | CSE-2171-72-PMT-T-025 | 2022-06-20 | 2171-2172-NPCC-T-1403 |  |  |  | 2022-06-20 | 2171-2172-NPCC-MWS-T-0011
43 | LOADING ARRANGEMENT & SEAFASTENING, DETAILS OF CC PIPES TRIP-6 @ GOGAS-252 | 2171-2172-NN-0043 | A | 3 |  | 2022-06-17 | CSE-2171-72-PMT-T-025 | 2022-06-20 | 2171-2172-NPCC-T-1407 |  |  |  | 2022-06-20 | 2171-2172-NPCC-MWS-T-0012
|  |  | B | 3 |  | 2022-07-05 | CSE-2171-72-PMT-T-027 | 2022-07-05 | 2171-2172-NPCC-T-1463 |  |  |  | 2022-07-05 | 2171-2172-NPCC-MWS-T-0014
44 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES TRIP-7 @ MICLYN-259 | 2171-2172-NN-0044 | A | 3 |  | 2022-08-12 | CSE-2171-72-PMT-T-028
45 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF HOT TAP FRAME, VALVE SKID & SPOOLS FOR CLS-22 @ MICLYB-259 | 2171-2172-NN-0045 | A | 3 |  | 2022-08-15 | CSE-2171-72-PMT-T-030 | 2022-08-18 | 2171-2172-NPCC-T-1539 |  |  |  | 2022-08-18 | 2171-2172-NPCC-MWS-T-0015
|  |  | B | 3 |  | 2022-10-07 | CSE-2171-72-PMT-T-035 | 2022-10-12 | 2171-2172-NPCC-T-1684 |  |  |  | 2022-10-12 | 2171-2172-NPCC-MWS-T-0018
|  |  | C |  |  | 2022-10-28 | CSE-2171-72-PMT-T-038 | 2022-11-02 | 2171-2172-NPCC-T-1712 |  |  |  | 2022-11-03 | 2171-2172-NPCC-MWS-T-0019
46 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF HOT TAP FRAME, VALVE SKID & SPOOLS FOR CFL-32 @ CREST-287 | 2171-2172-NN-0046 | A | 3 |  | 2022-08-15 | CSE-2171-72-PMT-T-029 | 2022-08-18 | 2171-2172-NPCC-T-1540 |  |  |  | 2022-08-18 | 2171-2172-NPCC-MWS-T-0016
|  |  | B |  |  | 2022-09-01 | CSE-2171-72-PMT-T-033
47 | LOADING ARRANGEMENT & SEAFASTENING DETAILS @ MICLYN-258 | 2171-2172-NN-0047 | A | 3 |  | 2022-08-24 | CSE-2171-72-PMT-T-032
48 | LIFTING AND INSTALLATION OF SPOOLS AT SUBSEA VALVE SKID ON PIPELINE TO SPM-32 | 2171-2172-NN-0048 | A | 3 |  | 2022-09-21 | CSE-2171-72-PMT-T-034 | 2023-10-03 | 2171-2172-NPCC-T-1673
|  |  | B | 3 |  | 2023-01-06 | CSE-2171-72-PMT-T-052
49 | LIFTING AND INSTALLATION OF 48" X 48" SUBSEA VALVE SKID ON PIPELINE TO SPM-32 | 2171-2172-NN-0049 | A | 3 |  | 2022-09-21 | CSE-2171-72-PMT-T-034 | 2023-10-03 | 2171-2172-NPCC-T-1673
50 | ARRANGEMENT & DETAILS OF PLATFORM FOR DIVING UNITS ON QMS POSEIDON | 2171-2172-NN-0050 | 1 | 3 | remarks | [12 empty] | Rev.1 sent to pmt on 28/09/2022 - CTL
51 | LOADING ARRANGEMENT & SEAFASTENING DETAILS FOR FLUSHING EQUIPMENT & MISC. ITEMS @ MICLYN-258 | 2171-2172-NN-0051 | A | 3 |  | 2022-10-11 | CSE-2171-72-PMT-T-036
|  |  | B | 3 |  | 2023-06-08 | CSE-2171-72-PMT-T-066
52 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF VALVE SKID, SPOOLS & CABLE TANK FOR CLS-21 @ GAC-81 | 2171-2172-NN-0052 | A | 3 |  | 2022-11-15 | CSE-2171-72-PMT-T-039 | 2022-11-15 | 2171-2172-NPCC-T-1728 |  |  |  | 2022-11-15 | 2171-2172-NPCC-MWS-T-0020
|  |  | B | 3 |  | 2023-03-03 | CSE-2171-72-PMT-T-061
53 | LOADING ARRANGEMENT & SEAFASTENING, DETAILS OF SPOOLS & SHROUDS @ GOGAS-250 | 2171-2172-NN-0053 | A | 3 |  | 2022-12-16 | CSE-2171-72-PMT-T-044 | 2022-12-23 | 2171-2172-NPCC-T-1770 |  |  |  | 2022-12-23 | 2171-2172-NPCC-MWS-T-0027
|  |  | B | 3 |  | 2022-12-27 | CSE-2171-72-PMT-T-049 | 2022-12-27 | 2171-2172-NPCC-T-1771 |  |  |  | 2022-12-27 | 2171-2172-NPCC-MWS-T-0028
54 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SPOOLS, VALVE SKIDS & SHROUDS @ CREST 287 | 2171-2172-NN-0054 | A | 3 |  | 2022-12-21 | CSE-2171-72-PMT-T-046 | 2022-12-21 | 2171-2172-NPCC-T-1767 |  |  |  | 2022-12-21 | 2171-2172-NPCC-MWS-T-0025
|  |  | B | 3 |  | 2022-12-26 | CSE-2171-72-PMT-T-048 | 2022-12-30 | 2171-2172-NPCC-T-1773 |  |  |  | 2022-12-30 | 2171-2172-NPCC-MWS-T-0029
|  |  | C | 3 |  | 2023-01-20 | CSE-2171-72-PMT-T-055
55 | LIFTING AND INSTALLATION OF SPOOL AT SUBSEA VALVE SKID ON PIPELINE-1 TO CLS-21 | 2171-2172-NN-0055 | A | 3 |  | 2023-01-06 | CSE-2171-72-PMT-T-052
56 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE FOR BYPASS P/L-2 AT MIDLINE TIE-IN-2 | 2171-2172-NN-0056 | A | 3 |  | 2023-01-09 | CSE-2171-72-PMT-T-053 | 2023-01-15 | 2171-2172-NPCC-T-1786
57 | LIFTING AND INSTALLATION OF 48" BYPASS P/L-2 SPOOL G.A-2 FOR BYPASS P/L-2 AT CROSSING CFL33 PIPELINE | 2171-2172-NN-0057 | A | 3 |  | 2023-01-09 | CSE-2171-72-PMT-T-053 | 2023-01-15 | 2171-2172-NPCC-T-1786
58 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE TIE-IN SPOOL GA AT CFL 33W (PLEM33/SPM33) | 2171-2172-NN-0058 | A | 3 |  | 2023-01-09 | CSE-2171-72-PMT-T-053 | 2023-01-15 | 2171-2172-NPCC-T-1786
59 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE SPOOL G.A FOR BYPASS P/L-2 AT CFL33W (PLEM33/SPM33) | 2171-2172-NN-0059 | A | 3 |  | 2023-01-10 | CSE-2171-72-PMT-T-054 | 2023-01-15 | 2171-2172-NPCC-T-1786
60 | TYPICAL CONCRETE SLEEPER LIFTING FOR BYPASS P/L-1, 2, 3 & 4 BY TELFORD-25 | 2171-2172-NN-0060 | A | 3 |  | 2023-03-09 | CSE-2171-72-PMT-T-056 | [10 empty] | re-sent
61 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE-4 SPOOL G.A-1 FOR BYPASS PIPELINE-4 AT CROSSING CFL36 PIPELINE | 2171-2172-NN-0061 | A | 3 | 2023-01-13 | 2023-01-13 | CSE-2171-72-PMT-T-056
62 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE-4 SPOOL G.A-2 AT CFL34E (PLEM34 / SPM34) | 2171-2172-NN-0062 | A | 3 | 2023-01-13 | 2023-01-13 | CSE-2171-72-PMT-T-056
63 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF VALVE SKID, SPOOLS, SHROUDS & CONCRETE SLEEPERS FOR CFL-33 & CFL-35 @ EOS-283 (NEW) | 2171-2172-NN-0063 | A | 3 |  | 2023-03-03 | CSE-2171-72-PMT-T-061
|  |  | B | 3 |  | 2024-04-25 | CSE-2171-72-PMT-T-081 | 2024-04-26 | 2171-2172-NPCC-T-2026 |  |  |  | 2024-04-26 | 2171-2172-NPCC-MWS-T-0038
64 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF HOT TAP FRAME, SPOOLS & FLUSHING EQUIPMENTS FOR CFL-32 @ GAC-81 | 2171-2172-NN-0064 | [16 empty] | haresh D
65 | MATERIAL STORAGE AT LB-II | 2171-2172-NN-0065 | A | 3 |  | 2023-05-25 | CSE-2171-72-PMT-T-065 | 2023-05-29 | 2171-2172-NPCC-T-1865 |  |  |  | 2023-05-29 | 2171-2172-NPCC-MWS-T-0031
|  |  | B | 3 |  | 2023-06-08 | CSE-2171-72-PMT-T-067 | 2023-06-09 | 2171-2172-NPCC-T-1873 |  |  |  | 2023-06-09 | 2171-2172-NPCC-MWS-T-0032
66 | LIFTING AND OFFLOADING (REMOVAL) OF SPOOLS AT SSVS CFL-32 BY DELMA-2000 | 2171-2172-NN-0066
67 | LIFTING AND INSTALLATION OF 48" SPOOL SPOOL G.A AT CFL34E (PLEM34 / SPM34)” | 2171-2172-NN-0067
68 | RECOVERY OF 48" BYPASS SPOOL AT CFL34E (PLEM34 / SPM34) JOP SIDE PIPELINE-4 | 2171-2172-NN-0068 | A | 3 |  | 2023-12-19 | CSE-2171-72-PMT-T-071
|  |  | B | 3 |  | 2024-01-25 | CSE-2171-72-PMT-T-074
|  |  | C | 3 |  | 2024-03-04 | CSE-2171-72-PMT-T-076
69 | RECOVERY OF 48" BYPASS SPOOL AT CFL34E (PLEM34 / SPM34) SPM34 SIDE PIPELINE-4 | 2171-2172-NN-0069 | A | 3 |  | 2023-12-19 | CSE-2171-72-PMT-T-071
|  |  | B | 3 |  | 2024-01-25 | CSE-2171-72-PMT-T-074
|  |  | C | 3 |  | 2024-03-04 | CSE-2171-72-PMT-T-076
70 | LIFTING AND INSTALLATION OF 48" BYPASS SPOOL AT CFL34E (PLEM34 / SPM34) PIPELINE-4 | 2171-2172-NN-0070 | A | 3 |  | 2023-12-19 | CSE-2171-72-PMT-T-072
|  |  | B | 3 |  | 2024-01-25 | CSE-2171-72-PMT-T-074
|  |  | C | 3 |  | 2024-06-04 | CSE-2171-72-PMT-T-082
71 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF VALVE SKID, SPOOLS & SHROUDS FOR CFL-31, CFL-33, CFL-34, CFL-35, AND CFL-36 | 2171-2172-NN-0071 | A | 3 |  | 2024-01-30 | CSE-2171-72-PMT-T-073 | 2024-01-31 | 2171-2172-NPCC-T-1971 |  |  |  | 2024-01-31 | 2171-2172-NPCC-MWS-T-0034
72 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SPOOLS & SLEEPERS @ GAC-81 | 2171-2172-NN-0072 | A | 3 |  | 2024-02-06 | CSE-2171-72-PMT-T-075
|  |  | B |  |  | 2024-04-22 | CSE-2171-72-PMT-T-078 | 2024-04-23 | 2171-2172-NPCC-T-2019 |  |  |  | 2024-04-23 | 2171-2172-NPCC-MWS-T-0037
73 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE SPOOL GA FOR BYPASS P/L-2 AT MIDLINE TIE-IN-2 | 2171-2172-NN-0073 | A | 3 |  | 2024-03-22 | CSE-2171-72-PMT-T-077
74 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE FOR BYPASS PIPELINE-2 FOR CROSSING CFL 32 PIPELINE | 2171-2172-NN-0074 | A | 3 |  | 2024-03-22 | CSE-2171-72-PMT-T-077
75 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE SPOOL G.A.-2 FOR BYPASS P/L-2 NEAR CFL 33W(PLEM33/SPM33) | 2171-2172-NN-0075 | A | 3 |  | 2024-03-22 | CSE-2171-72-PMT-T-077
76 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE SPOOL G.A.-3 FOR BYPASS P/L-2 NEAR CFL33W(PLEM33/SPM33) | 2171-2172-NN-0076 | A | 3 |  | 2024-03-22 | CSE-2171-72-PMT-T-077
77 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE-2 TIE-IN SPOOL GA AT CFL 33W(PLEM33/SPM33) BY SHUJAA-2000 | 2171-2172-NN-0077 | A | 3 |  | 2024-03-22 | CSE-2171-72-PMT-T-077
78 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE SPOOL G.A.-2 FOR BYPASS P/L-2 NEAR CFL 33W(PLEM33/SPM33) BY SHUJAA-2000 | 2171-2172-NN-0078 | A | 3 |  | 2024-03-22 | CSE-2171-72-PMT-T-077
79 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE-2 AT CFL 33W (PLEM 33 / SPM 33) BY SHUJAA-2000 | 2171-2172-NN-0079 | A | 3 |  | 2024-03-22 | CSE-2171-72-PMT-T-077
80 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE-2 SPOOL-1 GA AT CFL31W (PLEM31 / SPM31) BY SHUJAA-2000 | 2171-2172-NN-0080 | A | 3 |  | 2024-03-22 | CSE-2171-72-PMT-T-077
81 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE SPOOL-2 GA AT CFL31W (PLEM31 / SPM31) BY SHUJAA-2000 | 2171-2172-NN-0081 | A | 3 |  | 2024-03-22 | CSE-2171-72-PMT-T-077
82 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE FOR BYPASS PIPELINE-4 FOR CROSSING CFL36 PIPELINE (SPOOL-1) BY SHUJAA-2000 | 2171-2172-NN-0082
83 | LIFTING AND INSTALLATION OF 48" BYPASS PIPELINE AT CFL 35E (PLEM 35 / SPM 35) BY SHUJAA-2000 | 2171-2172-NN-0083
84 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SPOOLS (TRANSIT) @ GAC-81 | 2171-2172-NN-0084 | A | 3 |  | 2024-04-15 | CSE-2171-72-PMT-T-078 | 2024-04-21 | 2171-2172-NPCC-T-2017 |  |  |  | 2024-04-19 | 2171-2172-NPCC-MWS-T-0036
|  |  | B | 3 |  | 2024-04-22 | CSE-2171-72-PMT-T-079 | 2024-04-23 | 2171-2172-NPCC-T-2021
85 | TYPICAL CONCRETE SLEEPER LIFTING FOR BYPASS P/L-1 & 4 BY SHUJAA 2000 | 2171-2172-NN-0085 | A | 3 |  | 2024-04-22 | CSE-2171-72-PMT-T-079 | 2024-04-23 | 2171-2172-NPCC-T-2022
86 | LIFTING AND INSTALLATION OF 48" CORRDIOR SPOOLS FOR BYPASS PIPELINE-2 | 2171-2172-NN-0086 | A | 3 |  | 2024-04-24 | CSE-2171-72-PMT-T-080 | 2024-04-26 | 2171-2172-NPCC-T-2027
87 | LIFTING AND INSTALLATION OF 48" CORRDIOR SPOOLS FOR BYPASS PIPELINE-4 | 2171-2172-NN-0087 | B | 3 |  | 2024-08-19 | CSE-2171-72-PMT-T-086
|  |  | C | 3 |  | 2024-08-23 | CSE-2171-72-PMT-T-087
88 | LIFTING AND INSTALLATION OF FLOODED 48" CORRIDOR SPOOL FOR BYPASS PIPELINE-2 (FOR CROSSING CFL32) | 2171-2172-NN-0088
89 | LIFTING AND INSTALLATION OF 48" CORRDIOR SPOOLS PART-2 FOR BYPASS PIPELINE-4 AT CROSSING CFL35 | 2171-2172-NN-0089
90 | LIFTING AND INSTALLATION OF 48" CORRDIOR SPOOLS PART-1 FOR BYPASS PIPELINE-4 AT CROSSING CFL36 | 2171-2172-NN-0090
91 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF HOT TAP FRAMES & LAYDOWN HEADS @ GAC-81 | 2171-2172-NN-0091 | A | 3 |  | 2024-08-01 | CSE-2171-72-PMT-T-083 | [5 empty] | 2024-08-23 | 2171-2172-NPCC-MWS-T-0039
|  |  | B | 3 |  | 2024-09-20 | CSE-2171-72-PMT-T-089

## SKETCHES
Project 2171-2172
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2171-2172 | OFO-P2171-SK-001 | SEA CONQUEST DECK LAYOUT | 1 | A | √ | √ | 2021-09-28 | HZD | @
2 | 2171-2172 | OFO-P2171-SK-002 | TYPICAL PIG LAUNCHER & RECEIVER PLAN | 6 | B | √ | √ | 02/011/2021 | AKS | @
3 | 2171-2172 | OFO-P2171-SK-003 | PROTECTOR DETAILS FOR DIA42", DIA48" & DIA56" PIPELINES DURING EXCAVATION PLANS | 1 | D | √ | √ | 2021-10-16 | REY | @
4 | 2171-2172 | OFO-P2171-SK-004 | SUPPORT FRAME FOR HTM/BISEP INSTALLTION OPERATION-SIT | 2 + 48 | FA, G | √ | √ | 2022-06-06 | HZD | @
5 | 2171-2172 | OFO-P2171-SK-005 | MOCK-UPASSEMBLY | 11 | C | √ | √ | 2022-04-28 | HZD | @
6 | 2171-2172 | OFO-P2171-SK-006 | DETAILS OF 56'' TEST FIXTURE SUPPORT | 1 | B,BA,C | √ | √ | 2022-05-26 | HZD | @
7 | 2171-2172 | OFO-P2171-SK-007 | WET SIT ASSEMBLY | 10 | C | √ | √ | 2022-04-28 | HZD | @
8 | 2171-2172 | OFO-P2171-SK-008 | DETAILS OF 48'' TEST FIXTURE SUPPORT | 1 | A,AA | √ | √ | 2022-01-10 | CDG | @
9 | 2171-2172 | OFO-P2171-SK-009 | DETAILS OF 42'' TEST FIXTURE SUPPORT | 1 | A,AA | √ | √ | 2022-01-10 | CDG | @
10 | 2171-2172 | OFO-P2171-SK-010 | 56'' HOT CLAMP ASSEMBLY LIFTING ARRANGEMENT | 2 | A | √ | √ | 2022-01-13 | HZD | @
11 | 2171-2172 | OFO-P2171-SK-011 | START-UP ARRANGEMENT PROPOSED 48" BYPASS P/L-1 (SEG-B) FROM CLS21(JOP) TIE-IN TO CFL32W(PLEM 32/SPM32) @ KP 1.016 | 1 | B | √ | √ | 2022-04-18 | REY | @
12 | 2171-2172 | OFO-P2171-SK-012 | START-UP ARRANGEMENT PROPOSED 48" BYPASS P/L-2 (SEG-B) FROM CLS22(JOP) TIE-IN TO CFL33W(PLEM 33/SPM33) & CFL31W(PLEM31/SPM31) @ KP 0.959 | 1 | B | √ | √ | 2022-04-18 | REY | @
13 | 2171-2172 | OFO-P2171-SK-013 | START-UP ARRANGEMENT PROPOSED 48" BYPASS P/L-2 (SEG-A) FROM CLS22(JOP) TIE-IN TO CFL33W(PLEM 33/SPM33) & CFL31W(PLEM31/SPM31) @ KP 0.933 | 1 | B | √ | √ | 2022-04-18 | REY | @
14 | 2171-2172 | OFO-P2171-SK-014 | START-UP ARRANGEMENT PROPOSED 48" BYPASS P/L-1 (SEG-A) FROM CLS21(JOP) TIE-IN TO CFL32W(PLEM 32/SPM32) @ KP 0.990 | 1 | B | √ | √ | 2022-04-18 | REY | @
15 | 2171-2172 | OFO-P2171-SK-015 | START-UP ARRANGEMENT PROPOSED 48" BYPASS P/L-3 FROM CLS23(JOP) TIE-IN TO CFL36W(PLEM 36/SPM36) @ KP 0.000 | 1 | B | √ | √ | 2022-04-18 | REY | @
16 | 2171-2172 | OFO-P2171-SK-016 | START-UP ARRANGEMENT PROPOSED 48" BYPASS P/L-4 FROM CLS24(JOP) TIE-IN TO CFL34W(PLEM 34/SPM34) & CFL35W(PLEM35/SPM35) @ KP 0.000 | 1 | B | √ | √ | 2022-04-18 | REY | @
17 | 2171-2172 | OFO-P2171-SK-017 | SUPPORT FRAME TYPE-2 FOR HTM/BISEP INSTALLTION OPERATION | 2 | A | √ | √ | 2022-02-02 | HZD | @
18 | 2171-2172 | OFO-P2171-SK-018 | HANDRAILS DETAILS FOR SUPPORT FRAME | 2 + 19 | D,DA | √ | √ | 2022-03-01 | HZD | @
19 | 2171-2172 | OFO-P2171-SK-019 | DETAILS OF 56'' FIXTURE SUPPORT TEST HEAD | 1 + 3 | A,AA,B | √ | √ | 2022-02-25 | CDG/HZD | @
20 | 2171-2172 | OFO-P2171-SK-020 | PROTECTOR DETAILS FOR PIPELINES DURING LAYING OF PL-3 & PL-4 | 2 | A | √ | √ | 2022-02-14 | NAR
21 | 2171-2172 | OFO-P2171-SK-021 | DETAILS OF 56'' TEST FIXTURE SUPPORT - DRY SIT | [5 empty] | CDG
22 | 2171-2172 | OFO-P2171-SK-022 | SUPPORT FRAME FOR HTM/BISEP INSTALLTION OPERATION | 2 | A | √ | √ | 2022-02-02 | HZD | @
23 | 2171-2172 | OFO-P2171-SK-023 | FRAME FOOTPRINT ARRANGEMENT | 1 | A | √ | √ | 2022-02-03 | HZD | @
24 | 2171-2172 | OFO-P2171-SK-024 | PROTECTOR DETAILS FOR PIPELINES DURING LAYING OF PL-1 & PL-2 (SEGMENT-B) | 2 | A | √ | √ | 2022-02-14 | CDG |  | CANCELLED
25 | 2171-2172 | OFO-P2171-SK-025 | PROTECTOR DETAILS FOR PIPELINES DURING LAYING OF PL-1 & PL-2 (SEGMENT-A) | 2 | A | √ | √ | 2022-02-14 | CDG |  | CANCELLED
26 | 2171-2172 | OFO-P2171-SK-026 | PROTECTOR DETAILS FOR PIPELINES DURING LAYING DOWN OF PL-3 & PL-4 | 2 | A | √ | √ | 2022-02-14 | CDG |  | CANCELLED
27 | 2171-2172 | OFO-P2171-SK-027 | GENERAL PIPELAY PROFILE | 1 | A | √ | √ | 2022-02-11 | HZD | @
28 | 2171-2172 | OFO-P2171-SK-028 | ABANDONMENT & RECOVERY ARRANGEMENT AT FINAL STAGE | 1 | A | √ | √ | 2022-02-17 | AKS
29 | 2171-2172 | OFO-P2171-SK-029 | STINGER-10 SECTION-A 80" BUOYANCY TANK | 1 | A | √ | √ | 2022-02-17 | AKS
30 | 2171-2172 | OFO-P2171-SK-030 | STINGER-9 SECTION-A 80" BUOYANCY TANK | 1 | A | √ | √ | 2022-02-17 | AKS
31 | 2171-2172 | OFO-P2171-SK-031 | SPREADER BAR FRAME FOR BISEP | 1 + 4 | C,CA | √ | √ | 2022-05-10 | HZD | @
32 | 2171-2172 | OFO-P2171-SK-032 | ROV AND DIVING SPREAD FOOTPRINT ON DLS-750 | 1 | A | √ | √ | 2022-03-04 | HZD | @
33 | 2171-2172 | OFO-P2171-SK-033 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT | 1 | A | √ | √ | 2022-03-10 | CDG | @
34 | 2171-2172 | OFO-P2171-SK-034 | SUPPORT FRAME-2 TYPE-1 FOR HTM/BISEP INSTALLATION OPERATION | 2 + 48 | B, BA | √ | √ | 2022-06-07 | HZD | @
35 | 2171-2172 | OFO-P2171-SK-035 | OFFSHORE INSTALLATION STEPS ASSEMBLY | 7 | D | √ | √ | 2022-12-26 | HZD | @
36 | 2171-2172 | OFO-P2171-SK-036 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DLB-750 | 2 | A | √ | √ | 2022-03-30 | AKS | @
37 | 2171-2172 | OFO-P2171-SK-037 | FLOODING CONNECTION DETAILS ON CLOSURE PLATE | 1 | A | √ | √ | 2022-03-24 | NAR | @
38 | 2171-2172 | OFO-P2171-SK-038 | LIFTING & INSTALLATION OF HOT TAP CLAMP & TEST FIXTURE AT YARD | 2 | A | √ | √ | 2022-04-28 | HZD | @
39 | 2171-2172 | OFO-P2171-SK-039 | LIFTING & INSTALLATION OF INSTALLATION FRAME AT YARD | 1 | A | √ | √ | 2022-04-28 | HZD | @
40 | 2171-2172 | OFO-P2171-SK-040 | SPREADER BAR FRAME FOR HOT TAP MACHINE | 1 + 4 | B, BA | √ | √ | 2022-05-11 | HZD | @
41 | 2171-2172 | OFO-P2171-SK-041 | LIFTING & INSTALLATION OF HOT TAP MACHINE ON SLAB VALVE AT YARD | 2 | A, B | √ | √ | 2022-05-05 | HZD | @
42 | 2171-2172 | OFO-P2171-SK-042 | LIFTING & INSTALLATION OF BISEP ON SLAB VALVE AT YARD | 2 | A, B | √ | √ | 2022-05-05 | HZD | @
43 | 2171-2172 | OFO-P2171-SK-043 | LIFTING & INSTALLATION OF WET & DRY TEST ASSEMBLY | 3 | A | √ | √ | 2022-04-28 | HZD | @
44 | 2171-2172 | OFO-P2171-SK-044 | LIFTING & RECOVER HOT TAP MACHINE (WET SIT) | 2 | A | √ | √ | 2022-04-28 | HZD | @
45 | 2171-2172 | OFO-P2171-SK-045 | LIFTING & INSTALLATION OF BISEP ON SLAB VALVE (WET SIT) | 2 | B | √ | √ | 2022-08-22 | HZD | @
46 | 2171-2172 | OFO-P2171-SK-046 | FLANGE CLOSURE PLATE | 12 | CA | √ | √ | 2022-06-13 | NAR | @
47 | 2171-2172 | OFO-P2171-SK-047 | LOADING ARRANGEMENT OF MISC. ITEMS ON PLB-648 | 1 | A | √ | √ | 2022-04-20 | REY | @
48 | 2171-2172 | OFO-P2171-SK-048 | TRANSPORTATION OF HTM FRAME ON PLB-648 | 2 + 6 | AA, BA | √ | √ | 2022-05-13 | NAR | @
49 | 2171-2172 | OFO-P2171-SK-049 | TRANSPORTATION OF HTM FRAME ON DELMA 2000 | 2 + 12 | 0,1,A,B,C | √ | √ | 2022-08-15 | CDG | @
50 | 2171-2172 | OFO-P2171-SK-050 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT USING DLB-750 | 1 | A | √ | √ | 2022-05-17 | CDG | @
51 | 2171-2172 | OFO-P2171-SK-051 | TYPICAL STEVSHARK ANCHOR LIFTING ARRANGEMENT USING DLB-750 | 1 | A | √ | √ | 2022-05-17 | CDG | @
52 | 2171-2172 | OFO-P2171-SK-052 | DELAM-2000 LAYOUT | 1 | A | √ | √ | 2022-07-12 | CDG | @
53 | 2171-2172 | OFO-P2171-SK-053 | GRATING DETAIL FOR SPREADER BAR FRAME (BISEP) | 1+3 | A,0 | √ | √ | 2022-08-03 | HZD | @
54 | 2171-2172 | OFO-P2171-SK-054 | HANDRAILS DETAILS FOR SPREADER BAR FRAME (BISEP) | 1 | A | √ | √ | 2022-07-26 | HZD | @
55 | 2171-2172 | OFO-P2171-SK-055 | GRATING DETAIL FOR SPREADER BAR FRAME (HTM) | 1+2 | A,0 | √ | √ | 2022-08-03 | HZD | @
56 | 2171-2172 | OFO-P2171-SK-056 | HANDRAILS DETAILS FOR SPREADER BAR FRAME (HTM) | 1 | A | √ | √ | 2022-07-26 | HZD | @
57 | 2171-2172 | OFO-P2171-SK-057 | GRATING DETAIL FOR SUPPORT FRAME TYPE-1 FOR HTM/BISEP | 1+2 | A,0 | √ | √ | 2022-08-03 | HZD | @
58 | 2171-2172 | OFO-P2171-SK-058 | HT SEQUENCE OF ACTIVITION FOR DELMA-2000 | 14 | B | √ | √ | 2022-10-03 | CDG | @
59 | 2171-2172 | OFO-P2171-SK-059 | PROTECTOR DETAILS FOR PIPELINE-4 CLS-24 DURING PIPE LAYING | 1 | A,B | √ | √ | 2022-08-02 | REY | @
60 | 2171-2172 | OFO-P2171-SK-060 | TYPICAL LIFTING ARRANGEMENT FOR SMART FLANGES 42",48" & 56" | 1 | B | √ | √ | 2023-02-20 | REY | @
61 | 2171-2172 | OFO-P2171-SK-061 | HT SEQUENCE OF ACTIVITION FOR PLB-648 | 13 | A | √ | √ | 2022-08-31 | HZD | @
62 | 2171-2172 | OFO-P2171-SK-062 | LOADING ARRANGEMENT OF EQUIPMENTS ON DELMA-2000 | 1 | A | √ | √ | 2022-08-15 | SKS | @
63 | 2171-2172 | OFO-P2171-SK-063 | A - FRAME (6775x2480x5200) | 1 + 4 | A | √ | √ | 2022-08-18 | SKS | @
64 | 2171-2172 | OFO-P2171-SK-064 | A - FRAME (7690x3750x5000) | 1 + 6 | A | √ | √ | 2022-08-19 | SKS | @
65 | 2171-2172 | OFO-P2171-SK-065 | TYPICAL LIFTING FOR DEMOLISHED PIPE | 2 | A | √ | √ | 2022-09-19 | CDG | @
66 | 2171-2172 | OFO-P2171-SK-066 | AIRBAG LIFTING ARRANGEMENT FOR 48'' PIPELINE BYPASS PL-4 | 1 | A | √ | √ | 2022-11-16 | REY | @
67 | 2171-2172 | OFO-P2171-SK-067 | PIPELINE LIFTING ARRANGEMENT FOR 48'' PIPELINE BYPASS PL-4 BY CRANE | 1 | A | √ | √ | 2022-11-16 | REY | @
68 | 2171-2172 | OFO-P2171-SK-068 | AIRBAG LIFTING ARRANGEMENT FOR 48'' PIPELINE FOR FLOODED CASE | 1 | A | √ | √ | 2022-12-06 | CDG | @
69 | 2171-2172 | OFO-P2171-SK-069 | LIFTING & INSTALLATION OF BISEP & HTM (PLB-648) | 3 | B | √ | √ | 2022-12-20 | HZD | @
70 | 2171-2172 | OFO-P2171-SK-070 | LIFTING & INSTALLATION OF BISEP & HTM (DELMA-2000) | 3 | B | √ | √ | 2022-12-20 | HZD | @
71 | 2171-2172 | OFO-P2171-SK-071 | LIFTING AND OFFLOADING (REMOVAL) OF SPOOLS AT SSVS CFL-32 BY DELMA-2000 | [5 empty] | CDG
72 | 2171-2172 | OFO-P2171-SK-072 | LIFTING & OFFLOADING OF VALVE SKID-CLS-24 AT NPCC JETTY | 1 | A | √ | √ | 2023-05-22 | REY | @
73 | 2171-2172 | OFO-P2171-SK-073 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF HOT TAP FRAME @ CB-6 | 1 | A | √ | √ | 2023-07-12 | HZD | @
74 | 2171-2172 | OFO-P2171-SK-074 | LIFTING AND OFFLOADING OF FRAME | 1 | A | √ | √ | 2023-07-17 | HZD | @
75 | 2171-2172 | OFO-P2171-SK-075 | LIFTING AND OFFLOADING OF MISC. ITEM ON MICLYN-259 | 3 | A | √ | √ | 2023-07-15 | HZD | @
76 | 2171-2172 | OFO-P2171-SK-076 | SAT SYSTEM PLATFORM LAYOUT ON PLB-648 | 3 + 33 | B, 1 | √ | √ | 2023-07-31 | HZD | @ | sent to fabrication T-039 31/07/2023
77 | 2171-2172 | OFO-P2171-SK-077 | LIFTING & INSTALLATION OF SUPPORT FRAME, BISEP & HTM AT CFL-34 (PLB-648) | 1 | A | √ | √ | 2023-07-25 | HZD | @
78 | 2171-2172 | OFO-P2171-SK-078 | ENCAPSULATION BRACKETS ARRANGEMENT FOR 48" HTC ACTUATOR FLANGE | 1 | A | √ | √ | 2023-10-27 | CDG | @
79 | 2171-2172 | OFO-P2171-SK-079 | DETAILS OF ENCAPSULATION BRACKET - 1 FOR 48" HTC ACTUATOR FLANGE | 1 + 2 | A, 0 | √ | √ | 2023-10-27 | CDG | @ | sent to fabrication T-040 30/10/2023 resent on 06/11
80 | 2171-2172 | OFO-P2171-SK-080 | DETAILS OF ENCAPSULATION BRACKET - 2 FOR 48" HTC ACTUATOR | 1 + 4 | A, 0 | √ | √ | 2023-10-27 | CDG | @ | sent to fabrication T-040 30/10/2023 resent on 06/11
81 | 2171-2172 | OFO-P2171-SK-081 | DETAILS OF ENCAPSULATION BRACKET - 3 FOR 48" HTC ACTUATOR FLANGE | 1 + 4 | A, 0 | √ | √ | 2023-10-27 | CDG | @ | sent to fabrication T-040 30/10/2023 resent on 06/11
82 | 2171-2172 | OFO-P2171-SK-082 | ENCAPSULATION BRACKETS ARRANGEMENTFOR 48” MECH. CONNECTORS | 1 | A | √ | √ | 2023-11-02 | CDG | @
83 | 2171-2172 | OFO-P2171-SK-083 | DETAILS OF ENCAPSULATION BRACKET – 1 FOR 48” MECH. CONNECTORS | 1 + 2 | A, 0 | √ | √ | 2023-11-02 | CDG | @ | sent to fabrication T-041 07/11/2023
84 | 2171-2172 | OFO-P2171-SK-084 | DETAILS OF ENCAPSULATION BRACKET –2 FOR 48” MECH. CONNECTORS | 1 + 4 | A, 0 | √ | √ | 2023-11-02 | CDG | @ | sent to fabrication T-041 07/11/2023
85 | 2171-2172 | OFO-P2171-SK-085 | DETAILS OF ENCAPSULATION BRACKET –3 FOR 48” MECH. CONNECTORS | 1 + 4 | A, 0 | √ | √ | 2023-11-02 | CDG | @ | sent to fabrication T-041 07/11/2023
86 | 2171-2172 | OFO-P2171-SK-086 | SHUJAA 2000 SAT & FLUSHING EQUIPMENT LAYOUT | 1 | C | √ | √ | 2023-11-13 | REY | @
87 | 2171-2172 | OFO-P2171-SK-087 | DETAILS OF 48'' MECHANICAL CONNECTOR BLIND FLANGE & 48'' HOT TAP CLAMP BLIND FLANGE | 3 | A,0 | √ | √ | 2023-11-16 | CDG | @ | sent to fabrication T-042 17/11/2023
88 | 2171-2172 | OFO-P2171-SK-088 | LIFTING & RECOVERY OF BISEP ASSEMBLY (SHUJAA-2000) | 2 | B | √ | √ | 2024-01-19 | HZD | @
89 | 2171-2172 | OFO-P2171-SK-089 | LIFTING & RECOVERY OF HOT FRAME ASSEMBLY (SHUJAA-2000) | 2 | C | √ | √ | 2024-02-29 | HZD | @
90 | 2171-2172 | OFO-P2171-SK-090 | LIFTING AND OFFLOADING SPOOLS & SSVS BY DLB-1000 AT NPCC JETTY | 3 | A | √ | √ | 2024-01-18 | CDG | @
91 | 2171-2172 | OFO-P2171-SK-091 | CCC MARITIME-II DECK LAYOUT FOR STATS EQUIPMENTS DURING CFL 34 REMEDIAL WORK | 1 | A | √ | √ | 2024-01-15 | REY | @
92 | 2171-2172 | OFO-P2171-SK-092 | LIFTING AND OFFLOADING 500MT CABLE TANK BY DLB-1000 AT NPCC JETTY | 1 | A | √ | √ | 2024-01-19 | REY | @
93 | 2171-2172 | OFO-P2171-SK-093 | LIFTING AND OFFLOADING OF SSVS BY SAFEEN-3000 AT NPCC JETTY | 1 | A | √ | √ | 2024-01-23 | CDG | @
94 | 2171-2172 | OFO-P2171-SK-094 | LIFTING AND OFFLOADING 500MT CABLE TANK BY SAFEEN-3000 AT NPCC JETTY | 1 | A | √ | √ | 2024-01-24 | CDG | @
95 | 2171-2172 | OFO-P2171-SK-095 | LAYDOWN HEAD RECOVERY ARRANGEMENT BY CCC MARITIME-II | 2 | A | √ | √ | 2024-02-16 | CDG | @
96 | 2171-2172 | OFO-P2171-SK-096 | A-FRAMES REMOVAL ARRANGEMENT BY CCC MARITIME-II | 1 | A | √ | √ | 2024-01-26 | REY | @
97 | 2171-2172 | OFO-P2171-SK-097 | LIFTING & RECOVERY OF HOT TAP FRAME ASSEMBLY (SHUJAA-2000) (OPTION-1) | 8 | A | √ | √ | 2024-03-14 | AKS | @
98 | 2171-2172 | OFO-P2171-SK-098 | LIFTING & RECOVERY OF HOT TAP FRAME-1 ASSEMBLY NY (SHUJAA-2000) | 8 | A | √ | √ | 2024-03-29 | REY | @
99 | 2171-2172 | OFO-P2171-SK-099 | TYPICAL START-UP HEAD RECOVERY ARRANGEMENT BY CCC MARITIME-II | 1 | A | √ | √ | 2024-05-06 | AKS | @
100 | 2171-2172 | OFO-P2171-SK-100 | TYPICAL LIFTING ARRANGEMENT FOR B-CON MISALIGNMENT FLANGE 48 IN CLASS 300 | 1 | A | √ | √ | 2024-05-24 | AKS | @
101 | 2171-2172 | OFO-P2171-SK-101 | TYPICAL LAYDOWN HEAD RECOVERY ARRANGEMENT BY SHUJAA-2000 | 1 | A | √ | √ | 2024-06-14 | REY | @
102 | 2171-2172 | OFO-P2171-SK-102 | TYPICAL STEPS FOR SPOOLS LIFTING | 1 | A | √ | √ | 2024-06-14 | CDG | @
103 | 2171-2172 | OFO-P2171-SK-103 | ROTATION OF 48" CORRDIOR SPOOLS FOR BYPASS PIPELINE-2 AT CROSSING CFL33 | 1 | A | √ | √ | 2024-06-20 | AKS | @
104 | 2171-2172 | OFO-P2171-SK-104 | LIFTING OF 48" CORRDIOR SPOOLS FOR BYPASS PIPELINE-2 AT CROSSING CFL32 | 1 | A | √ | √ | 2024-06-20 | AKS | @
105 | 2171-2172 | OFO-P2171-SK-105 | ROTATION OF 48" CORRDIOR SPOOLS FOR BYPASS PIPELINE-2 AT CROSSING CFL32 | 1 | A | √ | √ | 2024-06-20 | AKS | @
106 | 2171-2172 | OFO-P2171-SK-106 | ROTATION OF 48" CORRIDOR SPOOLS FOR BYPASS PIPELINE-4 AT CROSSING CFL35 | 1 | A | √ | √ | 2024-07-02 | AKS | @
107 | 2171-2172 | OFO-P2171-SK-107 | ROTATION OF 48" CORRIDOR SPOOLS FOR BYPASS PIPELINE-4 AT CROSSING CFL36 PART-1 | 1 | B | √ | √ | 2024-07-17 | AKS | @
108 | 2171-2172 | OFO-P2171-SK-108 | AIR BAG ARRANGEMENT FOR 48" SPOOL | 1 | A | √ | √ | 2024-07-09 | AKS | @
109 | 2171-2172 | OFO-P2171-SK-109 | ROTATION OF FLOODED 48" CORRDIOR SPOOL FOR BYPASS PIPELINE-2 AT CROSSING CFL32 | 1 | A | √ | √ | 2024-06-20 | AKS | @
110 | 2171-2172 | OFO-P2171-SK-110 | PROJECT MATERIAL TRANSFER LAYOUT FROM EOS-283/LB-II TO B-42 USING DLB-1000 MAIN CRANE | 1 | B | √ | √ | 2024-07-27 | REY | @
111 | 2171-2172 | OFO-P2171-SK-111 | ROTATION 48" CORRDIOR SPOOL PART-2 FOR BYPASS PIPELINE-4 AT CROSSING CFL35 | 1 | A | √ | √ | 2024-07-17 | AKS | @
112 | 2171-2172 | OFO-P2171-SK-112 | ROTATION 48" CORRDIOR SPOOL PART-1 FOR BYPASS PIPELINE-4 AT CROSSING CFL36 | 1 | A | √ | √ | 2024-07-17 | AKS | @
113 | 2171-2172 | OFO-P2171-SK-113 | HORIZONTAL LIFTING OF 48" CORRDIOR SPOOL PART-2 FOR BYPASS PIPELINE-4 AT CROSSING CFL35 | 1 | A | √ | √ | 2024-07-19 | HZD | @
114 | 2171-2172 | OFO-P2171-SK-114 | PROJECT MATERIAL LAYOUT ARRANGEMENT ON B-42 AT NMDC JETTY | 1 | C | √ | √ | 2024-09-06 | REY | @
115 | 2171-2172 | OFO-P2171-SK-115 | PROPOSE SPOOLS (80M) LAYOUT AT CFL-34 |  |  |  |  | 2026-08-27 | CDG