## Documents - Pipeline & Cable
|  | ABU DHABI MARINE OPERATING COMPANY (ADMA-OPCO) | [14 empty] | NPCC DOC. No.: |  |  |  | 2207-NN-RP-060
|  | UMM LULU PACKAGE-1 FFD PROJECT | [14 empty] | ADMA DOC. No. : |  |  |  | AD162-562-G-06318
|  | NPCC PROJECT NO. 2207 | [14 empty] | REVISION : |  |  |  | B
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [14 empty] | DATE : |  |  |  | 2014-03-25
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | CHANGED DATE | Old DATES | REMAINING DAYS | NPCC |  |  |  | ADMA-OPCO |  |  | GMC |  |  |  |  | REMARKS |  |  | NPCC |  | ADMA-OPCO |  |  | GMC |  |  |  |  | REMARKS
[10 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS |  |  |  | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[10 empty] | CSE TO PMT |  | PMT TO ADMA-OPCO |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC |  |  |  | CSE TO PMT |  | PMT TO ADMA-OPCO |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[10 empty] | REF | DATE | REF | DATE | REF | DATE | CODE | REF | DATE | REF | DATE | CODE |  | REF | DATE | REF | DATE | REF | DATE | CODE | REF | DATE | REF | DATE | CODE
1 | PIPE STACKING ANALYSIS REPORT - Campaign-1 | 2207-NN-RP-001 | AD162-562-G-06200 | B | 2 | 2014-04-15 |  |  |  | CSE-OF-2207-001 | 2014-04-08 | 2207-NPCC-AO-T-00829 | 2014-04-09 | TR-UFFDP1-13-02476 | 2014-04-23 | 2 | 2207-NPCC-MWS-T-00079 | 2014-04-13 | GM/60295/099 | 2014-04-28 | ACCEPTED
|  |  |  | C | - |  |  |  |  | CSE-OF-2207-027 | 2014-07-21 | 2207-NPCC-AO-T-01271 | 2014-07-30 | TR-UFFDP1-13-03491 | 2014-08-04 | ACCEPTED | 2207-NPCC-MWS-T-00263 | 2014-07-31 | GM/60295/0345 | 2014-07-31 | ACCEPTED | -
2 | PIPE STACKING ANALYSIS REPORT -Campaign-2 | 2207-NN-RP-100 | AD197-473-G-06201 | B | 2 | 2015-03-07 |  |  | -16 | CSE-OF-2207-109 | 2015-03-23 | 2207-NPCC-AO-T-02388 | 2015-03-25 | TR-UFFDP1-13-05225 | 2015-04-12 | 2 | 2207-NPCC-MWS-T-00472 | 2015-03-25 | GM-60295-0643 | 2015-04-05 | A | -
|  |  |  | 0 | - | - |  |  |  | CSE-OF-2207-252 | 2015-12-13 | 2207-NPCC-AO-T-04058 | 2015-12-14 | TR-UFFDP1-13-06780 | 2015-12-29 | 1 | 2207-NPCC-MWS-T-00719 | 2015-12-15 | GM-60295-0922 | 2015-01-03 | A | -
3 | PIPELAY INSTALLATION REPORT FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 | 2207-NN-RP-002 | AD162-573/480-G-06202 | B | 2 | 2014-06-20 |  |  |  | CSE-OF-2207-031 | 2014-07-27 | 2207-NPCC-AO-T-01286 | 2014-07-31 | TR-UFFDP1-13-03499 | 2014-08-04 | ACCEPTED | 2207-NPCC-MWS-T-00266 | 2014-08-03 | GM/60295/0370 | 2014-08-18 | ACCEPTED | -
4 | PIPELAY INSTALLATION REPORT FOR 16" WELL FLUID P/L FROM WHT-5 TO WHT-2 | 2207-NN-RP-003 | AD162-480/475-G-06203 | B | 2 | 2014-07-29 |  |  |  | CSE-OF-2207-037 | 2014-08-07 | 2207-NPCC-AO-T-01331 | 2014-08-20 | TR-UFFDP1-13-03641 | 2014-08-20 | 2 | 2207-NPCC-MWS-T-00276 | 2014-08-11 | GM-60295-0376 | 2014-08-19 | ACCEPTED | -
|  |  |  | 0 | - | - |  |  |  | CSE-OF-2207-045 | 2014-09-07 | 2207-NPCC-AO-T-01425 | 2014-09-08 | TR-UFFDP1-13-03811 | 2014-09-11 | ACCEPTED | 2207-NPCC-MWS-T-00315 | 2014-09-09 | GM-60295-0439 | 2014-09-14 | ACCEPTED | -
5 | PIPELAY INSTALLATION REPORT FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP | 2207-NN-RP-004 | AD162-476/573-G-06204 | B | 2 | 2014-05-14 |  |  |  | CSE-OF-2207-004 | 2014-05-28 | 2207-NPCC-AO-T-01036 | 2014-05-28 | TR-UFFDP1-13-03254 | 2014-07-02 | 2 | 2207-NPCC-MWS-T-00130 | 2014-05-28 | GM/60295/0234 | 2014-06-07 | B (Accepted with comments) | -
|  |  |  | C | 2 |  |  |  |  | CSE-OF-2207-018 | 2014-07-07 | 2207-NPCC-AO-T-01207 | 2014-07-08 | TR-UFFDP1-13-03367 | 2014-07-14 | ACCEPTED | 2207-NPCC-MWS-T-00213 | 2014-07-09 | GM/60295/0301 | 2014-07-14 | ACCEPTED | -
6 | PIPELAY INSTALLATION REPORT FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 | 2207-NN-RP-005 | AD162-474/476-G-06205 | B | 2 | 2014-08-10 |  |  |  | CSE-OF-2207-002 | 2014-04-23 | 2207-NPCC-AO-T-00888 | 2014-04-30 | TR-UFFDP1-13-02698 | 2014-05-18 | 4 | 2207-NPCC-MWS-T-00137 | 2014-06-03 | GM/60295/0267 | 2014-06-23 | B (Accepted with comments) | -
|  |  |  | 0 | - | - |  |  |  | CSE-OF-2207-045 | 2014-09-07 | 2207-NPCC-AO-T-01426 | 2014-09-08 | TR-UFFDP1-13-03810 | 2014-09-11 | 2 | 2207-NPCC-MWS-T-00314 | 2014-09-09 | GM-60295-0440 | 2014-09-14 | ACCEPTED | -
|  |  |  | 1 | - | - |  |  |  | CSE-OF-2207-057 | 2014-09-14 | 2207-NPCC-AO-T-01465 | 2014-09-16 | TR-UFFDP1-13-03858 | 2014-09-17 | ACCEPTED | 2207-NPCC-MWS-T-00339 | 2014-09-18 | GM-60295-0467 | 2014-09-23 | ACCEPTED | CLIENT
7 | PIPELAY INSTALLATION REPORT FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 | 2207-NN-RP-006 | AD162-474/476-G-06206 | B | 2 | 2014-07-01 |  |  |  | CSE-OF-2207-040 | 2014-08-14 | 2207-NPCC-AO-T-01356 | 2014-08-18 | TR-UFFDP1-13-03712 | 2014-08-28 | 2 | 2207-NPCC-MWS-T-00291 | 2014-08-18 | GM-60295-0388 | 2014-08-24 | ACCEPTED | -
|  |  |  | 0 | - | - |  |  |  | CSE-OF-2207-042 | 2014-09-02 | 2207-NPCC-AO-T-01404 | 2014-09-02 | TR-UFFDP1-13-03751 | 2014-09-04 | ACCEPTED | 2207-NPCC-MWS-T-00312 | 2014-09-04 | GM-60295-0419 | 2014-09-07 | ACCEPTED | -
8 | PIPELAY INSTALLATION REPORT FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 | 2207-NN-RP-007 | AD162-474/476-G-06207 | B | 2 | 2014-07-07 |  |  |  | CSE-OF-2207-039 | 2014-08-13 | 2207-NPCC-AO-T-01351 | 2014-08-18 | TR-UFFDP1-13-03710 | 2014-08-28 | 2 | 2207-NPCC-MWS-T-00292 | 2014-08-18 | GM-60295-0394 | 2014-08-26 | B (Accepted with comments) | -
|  |  |  | 0 | - | - |  |  |  | CSE-OF-2207-050 | 2014-09-10 | 2207-NPCC-AO-T-01449 | 2014-09-12 | TR-UFFDP1-13-03853 | 2014-09-17 | ACCEPTED | 2207-NPCC-MWS-T-00329 | 2014-09-16 | GM-60295-0459 | 2014-09-17 | ACCEPTED | -
9 | PIPELAY INSTALLATION REPORT FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-RP-008 | AD162-476/573-G-06208 | B | 2 | 2014-06-03 |  |  |  | CSE-OF-2207-006 | 2014-06-03 | 2207-NPCC-AO-T-01069 | 2014-06-04 | TR-UFFDP1-13-03255 | 2014-07-02 | 2 | 2207-NPCC-MWS-T-00146 | 2014-06-04 | GM-60295-0278 | 2014-06-29 | B (Accepted with comments) | -
|  |  |  | C | 2 |  |  |  |  | CSE-OF-2207-019 | 2014-07-09 | 2207-NPCC-AO-T-01216 | 2014-07-10 | TR-UFFDP1-13-03798 | 2014-09-11 | ACCEPTED | 2207-NPCC-MWS-T-00216 | 2014-07-13 | GM-60295-0303 | 2014-07-14 | ACCEPTED | Client
10 | PIPELAY INSTALLATION REPORT FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-RP-009 | AD162-476/573-G-06209 | B | 2 | 2014-06-10 |  |  |  | CSE-OF-2207-010 | 2014-06-08 | 2207-NPCC-AO-T-01094 | 2014-06-10 | TR-UFFDP1-13-03256 | 2014-07-02 | 2 | 2207-NPCC-MWS-T-00160 | 2014-06-11 | GM-60295-0277 | 2014-06-29 | B (Accepted with comments) | -
|  |  |  | C | 2 |  |  |  |  | CSE-OF-2207-024 | 2014-07-15 | 2207-NPCC-AO-T-01241 | 2014-07-16 | TR-UFFDP1-13-03839 | 2014-09-17 | ACCEPTED | 2207-NPCC-MWS-T-00223 | 2014-07-20 | GM-60295-0317 | 2014-07-22 | ACCEPTED | -
11 | PIPELAY INSTALLATION REPORT FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP | 2207-NN-RP-010 | AD162-476/573-G-06210 | B | 2 | 2014-06-05 |  |  |  | CSE-OF-2207-022 | 2014-07-13 | 2207-NPCC-AO-T-01227 | 2014-07-14 | TR-UFFDP1-13-03506 | 2014-08-05 | 2 | 2207-NPCC-MWS-T-00221 | 2014-07-16 | GM-60295-0334 | 2014-07-24 | ACCEPTED | -
|  |  |  | 0 | - |  |  |  |  | CSE-OF-2207-036 | 2014-08-07 | 2207-NPCC-AO-T-01330 | 2014-08-10 | TR-UFFDP1-13-03566 | 2014-08-12 | ACCEPTED | 2207-NPCC-MWS-T-00275 | 2014-08-11 | GM/60295/0365 | 2014-08-14 | ACCEPTED | -
12 | PIPELAY INSTALLATION REPORT FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 | 2207-NN-RP-011 | AD162-573/480-G-06211 | B | 2 | 2014-06-15 |  |  |  | CSE-OF-2207-030 | 2014-07-24 | 2207-NPCC-AO-T-01280 | 2014-07-27 | TR-UFFDP1-13-03507 | 2014-08-05 | 2 | 2207-NPCC-MWS-T-00260 | 2014-07-31 |  |  |  | MWS
|  |  |  | 0 | - |  |  |  |  | CSE-OF-2207-038 | 2014-08-11 | 2207-NPCC-AO-T-01342 | 2014-08-12 | TR-UFFDP1-13-03580 | 2014-08-14 | ACCEPTED | 2207-NPCC-MWS-T-00282 | 2014-08-12 | GM-60295-0371 | 2014-08-18 | ACCEPTED | -
13 | PIPELAY INSTALLATION REPORT FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5 | 2207-NN-RP-012 | AD162-573/480-G-06212 | B | 2 | 2014-06-15 |  |  |  | CSE-OF-2207-024 | 2014-07-15 | 2207-NPCC-AO-T-01242 | 2014-07-16 | TR-UFFDP1-13-03465 | 2014-07-27 | 2 | 2207-NPCC-MWS-T-00224 | 2014-07-20 | GM/60295/0349 | 2014-08-04 | ACCEPTED | -
|  |  |  | 0 | - |  |  |  |  | CSE-OF-2207-032 | 2014-07-31 | 2207-NPCC-AO-T-01304 | 2014-08-06 | TR-UFFDP1-13-03537 | 2014-08-07 | ACCEPTED | 2207-NPCC-MWS-T-00269 | 2014-08-06 | GM-60295-0368 | 2014-08-18 | ACCEPTED | -
14 | PIPELAY INSTALLATION REPORT FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 | 2207-NN-RP-013 | AD162-480/475-G-06213 | B | 2 | 2014-07-22 |  |  |  | CSE-OF-2207-034 | 2014-08-05 | 2207-NPCC-AO-T-01321 | 2014-08-07 | TR-UFFDP1-13-03557 | 2014-08-12 | ACCEPTED | 2207-NPCC-MWS-T-00273 | 2014-08-08 | GM-60295-0387 | 2014-08-24 | ACCEPTED | -
15 | PIPELAY INSTALLATION REPORT FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 | 2207-NN-RP-014 | AD162-480/475-G-06214 | B | 2 | 2014-07-14 |  |  |  | CSE-OF-2207-033 | 2014-08-04 | 2207-NPCC-AO-T-01314 | 2014-08-06 | TR-UFFDP1-13-03684 | 2014-08-24 | 2 | 2207-NPCC-MWS-T-00270 | 2014-08-06 | GM/60295/0375 | 2014-08-19 | ACCEPTED | -
|  |  |  | 0 | - | - |  |  |  | CSE-OF-2207-041 | 2014-09-02 | 2207-NPCC-AO-T-01401 | 2014-09-02 | TR-UFFDP1-13-03752 | 2014-09-04 | ACCEPTED | 2207-NPCC-MWS-T-00311 | 2014-09-04 | GM/60295/0415 | 2014-09-04 | ACCEPTED | -
16 | PIPELAY NSTALLATION REPORT FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP | 2207-NN-RP-101 | AD197-481/477-G-06215 | B | 2 | 2015-06-17 |  | 2015-03-31 | 10 | CSE-OF-2207-122 | 2015-06-07 | 2207-NPCC-AO-T-02802 | 2015-06-09 | TR-UFFDP1-13-05692 | 2015-06-18 | 2 | 2207-NPCC-MWS-T-00499 | 2015-06-10 | GM-60295-0681 | 2015-06-21 | A | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-152 | 2015-07-15 | 2207-NPCC-AO-T-03050 | 2015-07-15 | TR-UFFDP1-13-05886 | 2015-07-23 | 1 | 2207-NPCC-MWS-T-00534 | 2015-07-19 | GM-60295-0869 | 2015-11-24 | A | -
17 | PIPELAY INSTALLATION REPORT FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 | 2207-NN-RP-102 | AD197-573/482-G-06216 | B | 2 | 2015-04-21 |  | 2015-04-21 | 15 | CSE-OF-2207-112 | 2015-04-07 | 2207-NPCC-AO-T-02489 | 2015-04-09 | TR-UFFDP1-13-05322 | 2015-04-23 | 3 | 2207-NPCC-MWS-T-00478 | 2015-04-13 | GM-60295-0656 | 2015-04-19 | A | -
|  |  |  | 0 | - | - | - |  | - | CSE-OF-2207-120 | 2015-05-24 | 2207-NPCC-AO-T-02719 | 2015-05-25 | TR-UFFDP1-13-05551 | 2015-05-28 | 1 | 2207-NPCC-MWS-T-00494 | 2015-05-26 | GM-60295-0678 | 2015-06-16 | A | -
18 | PIPELAY INSTALLATION REPORT FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 | 2207-NN-RP-103 | AD197-482/483-G-06217 | B | 2 | 2015-06-05 |  | 2015-05-12 | -24 | CSE-OF-2207-138 | 2015-06-30 | 2207-NPCC-AO-T-02973 | 2015-07-01 | TR-UFFDP1-13-05810 | 2015-07-06 | 2 | 2207-NPCC-MWS-T-00517 | 2015-07-02 | GM-60295-0702 | 2015-07-07 | A | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-148 | 2015-07-09 | 2207-NPCC-AO-T-03028 | 2015-07-12 | TR-UFFDP1-13-05854 | 2015-07-15 | 1 | 2207-NPCC-MWS-T-00531 | 2015-07-14 | GM-60295-0868 | 2015-11-24 | A | -
19 | PIPELAY INSTALLATION REPORT FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 | 2207-NN-RP-104 | AD197-483/482-G-06218 | B | 2 | 2015-06-09 |  | 2015-05-26 | -22 | CSE-OF-2207-141 | 2015-07-01 | 2207-NPCC-AO-T-02985 | 2015-07-05 | TR-UFFDP1-13-05835 | 2015-07-12 | 2 | 2207-NPCC-MWS-T-00524 | 2015-07-07 | GM-60295-0711 | 2015-07-12 | A | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-153 | 2015-07-15 | 2207-NPCC-AO-T-03053 | 2015-07-15 | TR-UFFDP1-13-05873 | 2015-07-22 | 1 | 2207-NPCC-MWS-T-00534 | 2015-07-19 | GM-60295-0867 | 2015-11-24 | A | -
20 | PIPELAY INSTALLATION REPORT FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 | 2207-NN-RP-105 | AD197-482/483-G-06219 | B | 2 | 2015-06-13 |  | 2015-05-19 | -16 | CSE-OF-2207-137 | 2015-06-29 | 2207-NPCC-AO-T-02971 | 2015-06-30 | TR-UFFDP1-13-05757 | 2015-07-02 | 2 | 2207-NPCC-MWS-T-00513 | 2015-07-01 | GM-60295-0706 | 2015-07-07 | A | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-144 | 2015-07-07 | 2207-NPCC-AO-T-03017 | 2015-07-08 | TR-UFFDP1-13-05842 | 2015-07-12 | 1 | 2207-NPCC-MWS-T-00526 | 2015-07-12 | GM-60295-0872 | 2015-11-24 | A | -
21 | PIPELAY INSTALLATION REPORT FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 | 2207-NN-RP-106 | AD197-573/482-G-06220 | B | 2 | 2015-06-01 |  | 2015-04-28 | -15 | CSE-OF-2207-129 | 2015-06-16 | 2207-NPCC-AO-T-02898 | 2015-06-17 | TR-UFFDP1-13-05713 | 2015-06-23 | 2 | 2207-NPCC-MWS-T-00508 | 2015-06-18 | - | - | - | MWS received on latest
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-139 | 2015-06-30 | 2207-NPCC-AO-T-02981 | 2015-07-01 | TR-UFFDP1-13-05774 | 2015-07-05 | 1 | 2207-NPCC-MWS-T-00518 | 2015-07-02 | GM-60295-0704 | 2015-07-07 | A | -
22 | PIPELAY INSTALLATION REPORT FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP | 2207-NN-RP-107 | AD197-482/573-G-06221 | B | 2 | 2015-06-01 |  | 2015-05-05 | -21 | CSE-OF-2207-133 | 2015-06-22 | 2207-NPCC-AO-T-02931 | 2015-06-24 | TR-UFFDP1-13-05735 | 2015-06-28 | 1 | 2207-NPCC-MWS-T-00512 | 2015-06-25 | GM-60295-0703 | 2015-07-07 | A | -
23 | PIPELAY INSTALLATION REPORT FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 | 2207-NN-RP-108 | AD197-573/481-G-06222 | B | 2 | 2015-06-21 |  | 2015-04-14 | -11 | CSE-OF-2207-142 | 2015-07-02 | 2207-NPCC-AO-T-02987 | 2015-07-05 | TR-UFFDP1-13-05841 | 2015-07-12 | 2 | 2207-NPCC-MWS-T-00523 | 2015-07-07 | GM-60295-0710 | 2015-07-12 | B | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-158 | 2015-07-26 | 2207-NPCC-AO-T-03085 | 2015-07-26 | TR-UFFDP1-13-05905 | 2015-07-29 | 1 | 2207-NPCC-MWS-T-00543 | 2015-07-26 | GM-60295-0871 | 2015-11-24 | A | -
24 | PIPELAY INSTALLATION REPORT FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP | 2207-NN-RP-109 | AD197-481/573-G-06223 | B | 2 | 2015-06-25 |  | 2015-04-07 | -13 | CSE-OF-2207-145 | 2015-07-08 | 2207-NPCC-AO-T-03023 | 2015-07-09 | TR-UFFDP1-13-05845 | 2015-07-13 | 2 | 2207-NPCC-MWS-T-00527 | 2015-07-12 | - | - | - | MWS received on latest
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-154 | 2015-07-20 | 2207-NPCC-AO-T-03068 | 2015-07-20 | TR-UFFDP1-13-05890 | 2015-07-27 | 1 | 2207-NPCC-MWS-T-00538 | 2015-07-21 | GM-60295-0870 | 2015-11-24 | A | -
25 | PIPELAY INSTALLATION REPORT FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP | 2207-NN-RP-110 | AD197-481/573-G-06224 | B | 2 | 2015-06-29 |  | 2015-03-24 | 15 | CSE-OF-2207-127 | 2015-06-14 | 2207-NPCC-AO-T-02870 | 2015-06-15 | TR-UFFDP1-13-05709 | 2015-06-23 | 2 | 2207-NPCC-MWS-T-00506 | 2015-06-16 | GM-60295-0705 | 2015-07-07 | B | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-157 | 2015-07-23 | 2207-NPCC-AO-T-03080 | 2015-07-26 | TR-UFFDP1-13-05904 | 2015-07-29 | 1 | 2207-NPCC-MWS-T-00542 | 2015-07-26 | GM-60295-0892 | 2015-11-30 | A | -
26 | PIPELAY INSTALLATION REPORT FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 | 2207-NN-RP-111 | AD197-481/477-G-06225 | B | 2 | 2015-03-17 |  | 2015-03-17 | -6 | CSE-OF-2207-108 | 2015-03-23 | 2207-NPCC-AO-T-02386 | 2015-03-25 | TR-UFFDP1-13-05218 | 2015-04-09 | 2 | 2207-NPCC-MWS-T-00473 | 2015-03-25 | GM-60295-0644 | 2015-04-05 | A | -
|  |  |  | 0 | - | - |  | - | - | CSE-OF-2207-119 | 2015-05-18 | 2207-NPCC-AO-T-02690 | 2015-05-19 | TR-UFFDP1-13-05537 | 2015-05-28 | 2 | 2207-NPCC-MWS-T-00492 | 2015-05-19 | - | - | - | MWS received on latest
|  |  |  | 1 | - | - |  |  | - | CSE-OF-2207-125 | 2015-06-07 | 2207-NPCC-AO-T-02823 | 2015-06-09 | TR-UFFDP1-13-05641 | 2015-06-14 | 1 | 2207-NPCC-MWS-T-00503 | 2015-06-11 | GM-60295-0893 | 2015-11-30 | A | -
27 | PIPELAY INSTALLATION REPORT FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 | 2207-NN-RP-112 | AD197-477/481-G-06226 | B | 2 | 2015-03-10 | 2015-05-16 | 2015-03-10 | -69 | CSE-OF-2207-119 | 2015-05-18 | 2207-NPCC-AO-T-02691 | 2015-05-19 | TR-UFFDP1-13-05545 | 2015-05-28 | 2 | 2207-NPCC-MWS-T-00493 | 2015-05-19 |  |  |  | MWS received on latest
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-123 | 2015-06-07 | 2207-NPCC-AO-T-02820 | 2015-06-09 | TR-UFFDP1-13-05651 | 2015-06-14 | 1 | 2207-NPCC-MWS-T-00501 | 2015-06-11 | GM-60295-0700 | 2015-07-06 | A | -
28 | PIPELAY INSTALLATION REPORT FOR 20" MOL AND 10.7 MM FOC FROM ULRP TO KP 89.056 | 2207-NN-RP-113 | AD197-573/602-G-06227 | B | 2 | 2015-08-01 |  | 2015-04-15 | -9 | CSE-OF-2207-163 | 2015-08-10 | 2207-NPCC-AO-T-03148 | 2015-08-10 | TR-UFFDP1-13-05977 | 2015-08-16 | 1 | 2207-NPCC-MWS-T-00560 | 2015-08-10 |  |  |  | Read Yahia email 18-08-15 for MWS
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-176 | 2015-08-16 | 2207-NPCC-AO-T-03230 | 2015-08-17 | TR-UFFDP1-13-06005 | 2015-08-23 | 1 | 2207-NPCC-MWS-T-00575 | 2015-08-17 | GM-60295-0744 GM-60295-0748 | 2015-08-18 | C | Only CRS sent for Rev 0 to MWS
|  |  |  | 1 | - | - |  |  | - | CSE-OF-2207-205 | 2015-08-27 | 2207-NPCC-AO-T-03341 | 2015-09-01 | TR-UFFDP1-13-06194 | 2015-09-16 | 1 | 2207-NPCC-MWS-T-00612 | 2015-09-02 | GM-60295-0776 | 2015-09-07 | B | -
| PIPELAY INSTALLATION REPORT FOR 20" MOL P/L AND 33mm FOC FROM ULRP TO KP 58.068 | 2207-NN-RP-114 | AD197-573/602-G-06228 | B | - | - |  | 2015-04-06 | - | CSE-OF-2207-220 | 2015-09-08 | 2207-NPCC-AO-T-03451 | 2015-09-09 | TR-UFFDP1-13-06158 | 2015-09-10 | 2 | 2207-NPCC-MWS-T-00627 | 2015-09-08 | GM-60295-0798 | 2015-09-09 | A | New Document with old number -
29 |  |  |  | 0 | [5 empty] | CSE-OF-2207-247 | 2015-11-23 | 2207-NPCC-AO-T-03985 | 2015-11-23 | TR-UFFDP1-13-06808 | 2016-01-06 | 4 | 2207-NPCC-MWS-T-00711 | 2015-11-24 |  |  |  | MWS DOCUMENT CANCELLED EMAIL YAHIA 09-12-15
30 | DAVIT LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 | 2207-NN-RP-015 | AD162-573/480-G-06229 | B | 2 | 2014-08-04 |  |  | -48 | CSE-OF-2207-071 | 2014-09-21 | 2207-NPCC-AO-T-01514 | 2014-09-22 | TR-UFFDP1-13-03941 | 2014-10-01 | 2 | ? | ? | ? | ? | ? | MWS
|  |  |  | 0 | - | - |  |  | - | V | - | 2207-NPCC-AO-T-01645 | 2014-10-14 | TR-UFFDP1-13-04046 | 2014-10-21 | ACCEPTED | 2207-NPCC-MWS-T-00399 | 2014-10-16 | GM-60295-0546 | 2014-10-30 | ACCEPTED | -
31 | DAVIT LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-5 TO WHT-2 | 2207-NN-RP-016 | AD162-480/475-G-06230 | B | 2 | 2014-08-08 |  |  | -47 | CSE-OF-2207-075 | 2014-09-24 | 2207-NPCC-AO-T-01549 | 2014-09-25 | TR-UFFDP1-13-03968 | 2014-10-06 | 2 | 2207-NPCC-MWS-T-00376 | 2014-09-27 | GM-60295-0508 | 2014-10-06 | ACCEPTED | -
|  |  |  | 0 | - | - |  |  | - | V | - | 2207-NPCC-AO-T-01645 | 2014-10-14 | TR-UFFDP1-13-04046 | 2014-10-21 | ACCEPTED | 2207-NPCC-MWS-T-00399 | 2014-10-16 | GM-60295-0541 | 2014-10-16 | ACCEPTED | -
32 | DAVIT LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP | 2207-NN-RP-017 | AD162-476/573-G-06231 | B | 2 | 2014-07-26 |  |  | -54 | CSE-OF-2207-046 | 2014-09-09 | 2207-NPCC-AO-T-01432 | 2014-09-10 | TR-UFFDP1-13-03843 | 2014-09-17 | 2 | 2207-NPCC-MWS-T-00318 | 2014-09-11 | GM-60295-0457 | 2014-09-17 | ACCEPTED | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-069 | 2014-09-21 | 2207-NPCC-AO-T-01507 | 2014-09-22 | TR-UFFDP1-13-03924 | 2014-09-30 | 2 | 2207-NPCC-MWS-T-00361 | 2014-09-24 | GM-60295-0491 | 2014-09-28 | ACCEPTED | -
|  |  |  | 1 | - | - |  |  | - | CSE-OF-2207-085 | 2014-10-02 | 2207-NPCC-AO-T-01612 | 2014-10-07 | TR-UFFDP1-13-03984 | 2014-10-13 | ACCEPTED | 2207-NPCC-MWS-T-00389 | 2014-10-08 | GM-60295-0533 | 2014-10-15 | ACCEPTED | -
33 | DAVIT LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 | 2207-NN-RP-018 | AD162-474/476-G-06232 | B | 2 | 2014-07-29 |  |  | -62 | CSE-OF-2207-080 | 2014-09-29 | 2207-NPCC-AO-T-01579 | 2014-09-30 | TR-UFFDP1-13-03973 | 2014-10-09 | 2 | 2207-NPCC-MWS-T-00385 | 2014-10-02 | GM-60295-0527 | 2014-10-14 | ACCEPTED | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-099 | 2014-11-17 | 2207-NPCC-AO-T-01833 | 2014-11-18 | TR-UFFDP1-13-04346 | 2014-11-29 | 2 | 2207-NPCC-MWS-T-00433 | 2014-11-19 | GM-60295-0587 | 2014-11-30 | ACCEPTED | -
34 | DAVIT LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 | 2207-NN-RP-019 | AD162-474/476-G-06233 | B | 2 | 2014-08-01 |  |  | -54 | CSE-OF-2207-075 | 2014-09-24 | 2207-NPCC-AO-T-01549 | 2014-09-25 | TR-UFFDP1-13-03968 | 2014-10-06 | 2 | 2207-NPCC-MWS-T-00376 | 2014-09-27 | GM-60295-0509 | 2014-10-06 | ACCEPTED | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-099 | 2014-11-17 | 2207-NPCC-AO-T-01833 | 2014-11-18 | TR-UFFDP1-13-04346 | 2014-11-29 | 2 | 2207-NPCC-MWS-T-00433 | 2014-11-19 | GM-60295-0588 | 2014-11-30 | ACCEPTED | -
35 | DAVIT LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 | 2207-NN-RP-020 | AD162-474/476-G-06234 | B | 2 | 2014-08-04 |  |  | -51 | CSE-OF-2207-077 | 2014-09-24 | 2207-NPCC-AO-T-01553 | 2014-09-27 | TR-UFFDP1-13-04229 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00380 | 2014-10-01 | GM-60295-0513 | 2014-10-06 | ACCEPTED | -
36 | DAVIT LIFT ANALYSIS REPORT FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-RP-021 | AD162-476/573-G-06235 | B | 2 | 2014-08-07 |  |  | -45 | CSE-OF-2207-069 | 2014-09-21 | 2207-NPCC-AO-T-01508 | 2014-09-22 | TR-UFFDP1-13-03927 | 2014-09-30 | 2 | 2207-NPCC-MWS-T-00360 | 2014-09-24 | GM-60295-0489 | 2014-09-28 | ACCEPTED | -
|  |  |  | 0 | [5 empty] | CSE-OF-2207-085 | 2014-10-02 | 2207-NPCC-AO-T-01612 | 2014-10-07 | TR-UFFDP1-13-03984 | 2014-10-13 | ACCEPTED | 2207-NPCC-MWS-T-00389 | 2014-10-08 | GM-60295-0534 | 2014-10-15 | ACCEPTED | -
37 | DAVIT LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-RP-022 | AD162-476/573-G-06236 | B | 2 | 2014-08-10 |  |  | -42 | CSE-OF-2207-069 | 2014-09-21 | 2207-NPCC-AO-T-01509 | 2014-09-22 | TR-UFFDP1-13-03926 | 2014-09-30 | 2 | 2207-NPCC-MWS-T-00359 | 2014-09-24 | GM-60295-0490 | 2014-09-28 | ACCEPTED | -
|  |  |  | 0 | [5 empty] | CSE-OF-2207-085 | 2014-10-02 | 2207-NPCC-AO-T-01612 | 2014-10-07 | TR-UFFDP1-13-03984 | 2014-10-13 | ACCEPTED | 2207-NPCC-MWS-T-00389 | 2014-10-08 | GM-60295-0535 | 2014-10-15 | ACCEPTED | -
38 | DAVIT LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP | 2207-NN-RP-023 | AD162-476/573-G-06237 | B | 2 | 2014-08-13 |  |  | -39 | CSE-OF-2207-069 | 2014-09-21 | 2207-NPCC-AO-T-01510 | 2014-09-22 | TR-UFFDP1-13-03928 | 2014-09-30 | 2 | 2207-NPCC-MWS-T-00358 | 2014-09-24 | GM-60295-0484 | 2014-09-25 | ACCEPTED | -
|  |  |  | 0 | [5 empty] | CSE-OF-2207-085 | 2014-10-02 | 2207-NPCC-AO-T-01612 | 2014-10-07 | TR-UFFDP1-13-03984 | 2014-10-13 | ACCEPTED | 2207-NPCC-MWS-T-00389 | 2014-10-08 | GM-60295-0536 | 2014-10-15 | ACCEPTED | -
39 | DAVIT LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 | 2207-NN-RP-024 | AD162-573/480-G-06238 | B | 2 | 2014-08-12 |  |  | -40 | CSE-OF-2207-071 | 2014-09-21 | 2207-NPCC-AO-T-01514 | 2014-09-22 | TR-UFFDP1-13-03941 | 2014-10-01 | 2 | ? | ? |  |  |  | MWS
|  |  |  | 0 | - | - |  |  | - | V | - | 2207-NPCC-AO-T-01646 | 2014-10-14 | TR-UFFDP1-13-04045 | 2014-10-21 | ACCEPTED | 2207-NPCC-MWS-T-00400 | 2014-10-16 | GM-60295-0547 | 2014-10-20 | ACCEPTED | -
40 | DAVIT LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5 | 2207-NN-RP-025 | AD162-573/480-G-06239 | B | 2 | 2014-08-16 |  |  | -36 | CSE-OF-2207-071 | 2014-09-21 | 2207-NPCC-AO-T-01514 | 2014-09-22 | TR-UFFDP1-13-03941 | 2014-10-01 | 2 | ? | ? |  |  |  | MWS
|  |  |  | 0 | - | - |  |  | - | V | - | 2207-NPCC-AO-T-01647 | 2014-10-14 | TR-UFFDP1-13-04047 | 2014-10-21 | ACCEPTED | 2207-NPCC-MWS-T-00401 | 2014-10-16 | GM-60295-0548 | 2014-10-20 | ACCEPTED | -
41 | DAVIT LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 | 2207-NN-RP-026 | AD162-480/475-G-06240 | B | 2 | 2014-08-20 |  |  | -35 | CSE-OF-2207-075 | 2014-09-24 | 2207-NPCC-AO-T-01549 | 2014-09-25 | TR-UFFDP1-13-03968 | 2014-10-06 | 2 | 2207-NPCC-MWS-T-00376 | 2014-09-27 | GM-60295-0510 | 2014-10-06 | ACCEPTED | -
|  |  |  | 0 | - | - |  |  | - | V | - | 2207-NPCC-AO-T-01647 | 2014-10-14 | TR-UFFDP1-13-04047 | 2014-10-21 | ACCEPTED | 2207-NPCC-MWS-T-00401 | 2014-10-16 | GM-60295-0543 | 2014-10-16 | ACCEPTED | -
42 | DAVIT LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 | 2207-NN-RP-027 | AD162-480/475-G-06241 | B | 2 | 2014-08-24 |  |  | -31 | CSE-OF-2207-075 | 2014-09-24 | 2207-NPCC-AO-T-01549 | 2014-09-25 | TR-UFFDP1-13-03968 | 2014-10-06 | 2 | 2207-NPCC-MWS-T-00376 | 2014-09-27 | GM-60295-0511 | 2014-10-06 | ACCEPTED | -
|  |  |  | 0 | - | - |  |  | - | V | - | 2207-NPCC-AO-T-01646 | 2014-10-14 | TR-UFFDP1-13-04045 | 2014-10-21 | ACCEPTED | 2207-NPCC-MWS-T-00400 | 2014-10-16 | GM-60295-0542 | 2014-10-16 | ACCEPTED | -
43 | DAVIT LIFT ANALYSIS REPORT FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP | 2207-NN-RP-115 | AD197-481/477-G-06242 | B | 2 | 2015-08-16 |  | 2015-06-23 | -9 | CSE-OF-2207-193 | 2015-08-25 | 2207-NPCC-AO-T-03305 | 2015-08-26 | TR-UFFDP1-13-06141 | 2015-09-08 | 3 | 2207-NPCC-MWS-T-00594 | 2015-08-26 | GM-60295-0783 | 2015-09-07 | A | -
|  |  |  | 0 | 1 |  |  |  | - | CSE-OF-2207-225 | 2015-09-13 | 2207-NPCC-AO-T-03487 | 2015-09-15 | TR-UFFDP1-13-06238 | 2015-09-20 | 1 | 2207-NPCC-MWS-T-00641 | 2015-09-17 | GM-60295-0862 | 2015-11-24 | A | -
|  |  |  | 1 | [5 empty] | CSE-OF-2207-267 | 2016-02-08 | 2207-NPCC-AO-T-04335 | 2016-02-11 | TR-UFFDP1-13-07043 | 2016-02-18 | 2 | 2207-NPCC-MWS-T-00757 | 2015-02-11 | GM-60295-0951 | 2016-02-22 | A | -
|  |  |  | 2 | [5 empty] | CSE-OF-2207-275 | 2016-02-24 | 2207-NPCC-AO-T-04427 | 2016-02-25 | TR-UFFDP1-13-07126 | 2016-03-09 | 2 | 2207-NPCC-MWS-T-00774 | 2016-03-01 |  |  |  | MWS`
44 | DAVIT LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 | 2207-NN-RP-116 | AD197-573/482-G-06243 | B | 2 | 2015-07-23 |  | 2015-07-14 | -25 | CSE-OF-2207-179 | 2015-08-17 | 2207-NPCC-AO-T-03236 | 2015-08-18 | TR-UFFDP1-13-06028 | 2015-08-23 | 2 | 2207-NPCC-MWS-T-00582 | 2015-08-18 |  |  |  | MWS received on latest
|  |  |  | 0 |  |  |  |  | - | CSE-OF-2207-191 | 2015-08-25 | 2207-NPCC-AO-T-03298 | 2015-08-25 | TR-UFFDP1-13-06068 | 2015-08-30 | 1 | 2207-NPCC-MWS-T-00596 | 2015-08-26 | GM-60295-0784 | 2015-09-07 | A | -
45 | DAVIT LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 | 2207-NN-RP-117 | AD197-482/483-G-06244 | B | 2 | 2015-08-04 |  | 2015-08-04 | -5 | CSE-OF-2207-162 | 2015-08-09 | 2207-NPCC-AO-T-03144 | 2015-08-12 | TR-UFFDP1-13-05978 | 2015-08-16 | 2 | 2207-NPCC-MWS-T-00559 | 2015-08-12 | GM-60295-0732 | 2015-08-15 | A | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-172 | 2015-08-13 | 2207-NPCC-AO-T-03210 | 2015-08-16 | TR-UFFDP1-13-05989 | 2015-08-18 | 1 | 2207-NPCC-MWS-T-00571 | 2015-08-16 | GM-60295-0785 | 2015-09-07 | A | -
|  |  |  | 1 | - | - |  |  | - | CSE-OF-2207-228 | 2015-09-14 | 2207-NPCC-AO-T-03499 | 2015-09-16 | Approved as per email from Yahia TR-UFFDP1-13-06240 | 2015-09-17 | 1 | 2207-NPCC-MWS-T-00642 | 2015-09-17 | GM-60295-0863 | 2015-11-24 | A | -
46 | DAVIT LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 | 2207-NN-RP-118 | AD197-483/482-G-06245 | B | 2 | 2015-08-08 |  | 2015-08-18 | -1 | CSE-OF-2207-162 | 2015-08-09 | 2207-NPCC-AO-T-03144 | 2015-08-12 | TR-UFFDP1-13-05978 | 2015-08-16 | 2 | 2207-NPCC-MWS-T-00559 | 2015-08-12 | GM-60295-0733 | 2015-08-15 | A | -
|  |  |  | 0 | - | - | - |  | - | CSE-OF-2207-172 | 2015-08-13 | 2207-NPCC-AO-T-03210 | 2015-08-16 | TR-UFFDP1-13-05989 | 2015-08-18 | 1 | 2207-NPCC-MWS-T-00571 | 2015-08-16 | GM-60295-0786 | 2015-09-07 | A | -
|  |  |  | 1 | - | - | - |  | - | CSE-OF-2207-228 | 2015-09-14 | 2207-NPCC-AO-T-03499 | 2015-09-16 | Approved as per email from Yahia TR-UFFDP1-13-06240 | 2015-09-17 | 1 | 2207-NPCC-MWS-T-00642 | 2015-09-17 | GM-60295-0864 | 2015-11-24 | A | -
47 | DAVIT LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 | 2207-NN-RP-119 | AD197-482/483-G-06246 | B | 2 | 2015-08-12 |  | 2015-08-11 | 3 | CSE-OF-2207-162 | 2015-08-09 | 2207-NPCC-AO-T-03144 | 2015-08-12 | TR-UFFDP1-13-05978 | 2015-08-16 | 2 | 2207-NPCC-MWS-T-00559 | 2015-08-12 | GM-60295-0734 | 2015-08-15 | A | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-172 | 2015-08-13 | 2207-NPCC-AO-T-03210 | 2015-08-16 | TR-UFFDP1-13-05989 | 2015-08-18 | 1 | 2207-NPCC-MWS-T-00571 | 2015-08-16 | GM-60295-0787 | 2015-09-07 | A | -
|  |  |  | 1 | - | - |  |  | - | CSE-OF-2207-228 | 2015-09-14 | 2207-NPCC-AO-T-03499 | 2015-09-16 | Approved as per email from Yahia TR-UFFDP1-13-06240 | 2015-09-17 | 1 | 2207-NPCC-MWS-T-00642 | 2015-09-17 | GM-60295-0865 | 2015-11-24 | A | -
48 | DAVIT LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 | 2207-NN-RP-120 | AD197-573/482-G-06247 | B | 2 | 2015-07-27 |  | 2015-07-21 | -21 | CSE-OF-2207-179 | 2015-08-17 | 2207-NPCC-AO-T-03236 | 2015-08-18 | TR-UFFDP1-13-06028 | 2015-08-23 | 2 | 2207-NPCC-MWS-T-00582 | 2015-08-18 |  |  |  | MWS received on latest
|  |  |  | 0 | [5 empty] | CSE-OF-2207-191 | 2015-08-25 | 2207-NPCC-AO-T-03298 | 2015-08-25 | TR-UFFDP1-13-06068 | 2015-08-30 | 1 | 2207-NPCC-MWS-T-00596 | 2015-08-26 | GM-60295-0788 | 2015-09-07 | A | -
49 | DAVIT LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP | 2207-NN-RP-121 | AD197-482/573-G-06248 | B | 2 | 2015-07-31 |  | 2015-07-28 | -17 | CSE-OF-2207-179 | 2015-08-17 | 2207-NPCC-AO-T-03236 | 2015-08-18 | TR-UFFDP1-13-06028 | 2015-08-23 | 2 | 2207-NPCC-MWS-T-00582 | 2015-08-18 |  |  |  | MWS received on latest
|  |  |  | 0 | [5 empty] | CSE-OF-2207-191 | 2015-08-25 | 2207-NPCC-AO-T-03298 | 2015-08-25 | TR-UFFDP1-13-06068 | 2015-08-30 | 1 | 2207-NPCC-MWS-T-00596 | 2015-08-26 | GM-60295-0823 | 2015-09-20 | A | -
50 | DAVIT LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 | 2207-NN-RP-122 | AD197-573/481-G-06249 | B | 2 | 2015-08-20 |  | 2015-07-07 | -5 | CSE-OF-2207-193 | 2015-08-25 | 2207-NPCC-AO-T-03305 | 2015-08-26 | TR-UFFDP1-13-06141 | 2015-09-08 | 3 | 2207-NPCC-MWS-T-00594 | 2015-08-26 | GM-60295-0793 | 2015-09-07 | A | -
|  |  |  | 0 | 1 |  |  |  |  | CSE-OF-2207-225 | 2015-09-13 | 2207-NPCC-AO-T-03487 | 2015-09-15 | TR-UFFDP1-13-06238 | 2015-09-20 | 1 | 2207-NPCC-MWS-T-00641 | 2015-09-17 | GM-60295-0866 | 2015-11-24 | A | -
|  |  |  | 1 | 1 | - |  |  |  | CSE-OF-2207-268 | 2016-02-09 | 2207-NPCC-AO-T-04344 | 2016-02-11 | TR-UFFDP1-13-07036 | 2016-02-23 | 2 | 2207-NPCC-MWS-T-00759 | 2015-02-11 | GM-60295-0949 | 2016-02-22 | A | -
|  |  |  | 2 | [5 empty] | CSE-OF-2207-275 | 2016-02-24 | 2207-NPCC-AO-T-04427 | 2016-02-25 | TR-UFFDP1-13-07126 | 2016-03-09 | 2 | 2207-NPCC-MWS-T-00774 | 2016-03-01 |  |  |  | MWS`
51 | DAVIT LIFT ANALYSIS REPORT FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP | 2207-NN-RP-123 | AD197-481/573-G-06250 | B | 2 | 2015-08-24 |  | 2015-06-30 | -1 | CSE-OF-2207-193 | 2015-08-25 | 2207-NPCC-AO-T-03305 | 2015-08-26 | TR-UFFDP1-13-06141 | 2015-09-08 | 3 | 2207-NPCC-MWS-T-00594 | 2015-08-26 | GM-60295-0792 | 2015-09-07 | A | -
|  |  |  | 0 | 1 |  |  |  |  | CSE-OF-2207-225 | 2015-09-13 | 2207-NPCC-AO-T-03487 | 2015-09-15 | TR-UFFDP1-13-06238 | 2015-09-20 | 1 | 2207-NPCC-MWS-T-00641 | 2015-09-17 | GM-60295-0856 | 2015-11-24 | A | -
|  |  |  | 1 | [5 empty] | CSE-OF-2207-267 | 2016-02-08 | 2207-NPCC-AO-T-04335 | 2016-02-11 | TR-UFFDP1-13-07043 | 2016-02-18 | 2 | 2207-NPCC-MWS-T-00757 | 2015-02-11 | GM-60295-0952 | 2016-02-22 | A | -
|  |  |  | 2 | [5 empty] | CSE-OF-2207-275 | 2016-02-24 | 2207-NPCC-AO-T-04427 | 2016-02-25 | TR-UFFDP1-13-07126 | 2016-03-09 | 2 | 2207-NPCC-MWS-T-00774 | 2016-03-01 |  |  |  | MWS`
52 | DAVIT LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP | 2207-NN-RP-124 | AD197-481/573-G-06251 | B | 2 | 2015-08-28 |  | 2015-06-16 | 3 | CSE-OF-2207-193 | 2015-08-25 | 2207-NPCC-AO-T-03305 | 2015-08-26 | TR-UFFDP1-13-06141 | 2015-09-08 | 3 | 2207-NPCC-MWS-T-00594 | 2015-08-26 | GM-60295-0791 | 2015-09-07 | A | -
|  |  |  | 0 | 1 |  |  |  |  | CSE-OF-2207-225 | 2015-09-13 | 2207-NPCC-AO-T-03487 | 2015-09-15 | TR-UFFDP1-13-06238 | 2015-09-20 | 1 | 2207-NPCC-MWS-T-00641 | 2015-09-17 | GM-60295-0857 | 2015-11-24 | A | -
|  |  |  | 1 | [5 empty] | CSE-OF-2207-267 | 2016-02-08 | 2207-NPCC-AO-T-04335 | 2016-02-11 | TR-UFFDP1-13-07128 | 2016-03-10 | 2 | 2207-NPCC-MWS-T-00757 | 2015-02-11 | GM-60295-0944 | 2016-02-22 | A | -
53 | DAVIT LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 | 2207-NN-RP-125 | AD197-481/477-G-06252 | B | 2 | 2015-07-15 |  | 2015-06-09 | -42 | CSE-OF-2207-195 | 2015-08-26 | 2207-NPCC-AO-T-03310 | 2015-08-27 | TR-UFFDP1-13-06174 | 2015-09-16 | 2 | 2207-NPCC-MWS-T-00602 | 2015-08-27 | GM-60295-0790 | 2015-09-07 | A | -
|  |  |  | 0 | 1 |  |  |  |  | CSE-OF-2207-247 | 2015-11-23 | 2207-NPCC-AO-T-03985 | 2015-11-23 | TR-UFFDP1-13-06807 | 2016-01-06 | 1 | 2207-NPCC-MWS-T-00711 | 2015-11-24 | GM-60295-0906 | 2015-12-13 | A | -
|  |  |  | 1 | 1 |  |  |  |  | CSE-OF-2207-262 | 2016-02-03 | 2207-NPCC-AO-T-04303 | 2016-02-08 | TR-UFFDP1-13-07054 | 2016-02-23 | 2 | 2207-NPCC-MWS-T-00749 | 2016-02-09 | GM-60295-0945 | 2016-02-22 | A | -
|  |  |  | 2 | [5 empty] | CSE-OF-2207-274 | 2016-02-24 | 2207-NPCC-AO-T-04426 | 2016-02-25 | TR-UFFDP1-13-07101 | 2016-03-02 | 2 | 2207-NPCC-MWS-T-00773 | 2016-03-01 |  |  |  | MWS
54 | DAVIT LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 | 2207-NN-RP-126 | AD197-477/481-G-06253 | B | 2 | 2015-07-19 |  | 2015-06-02 | -38 | CSE-OF-2207-195 | 2015-08-26 | 2207-NPCC-AO-T-03310 | 2015-08-27 | TR-UFFDP1-13-06175 | 2015-09-15 | 1 | 2207-NPCC-MWS-T-00602 | 2015-08-27 | GM-60295-0789 | 2015-09-07 | A | -
|  |  |  | 0 | 1 |  |  |  |  | CSE-OF-2207-262 | 2016-02-03 | 2207-NPCC-AO-T-04303 | 2016-02-08 | TR-UFFDP1-13-07054 | 2016-02-23 | 2 | 2207-NPCC-MWS-T-00749 | 2016-02-09 | GM-60295-0946 | 2016-02-22 | A | -
|  |  |  | 1 | [5 empty] | CSE-OF-2207-274 | 2016-02-24 | 2207-NPCC-AO-T-04426 | 2016-02-25 | TR-UFFDP1-13-07101 | 2016-03-02 | 2 | 2207-NPCC-MWS-T-00773 | 2016-03-01 |  |  |  | MWS
55 | DAVIT LIFT ANALYSIS REPORT FOR 20" MOL FROM ULRP TO KP89.256.83 | 2207-NN-RP-127 | AD197-573/602-G-06254 | B | 2 | 2015-08-30 |  | 2015-06-14 | -15 | CSE-OF-2207-228 | 2015-09-14 | 2207-NPCC-AO-T-03508 | 2015-09-17 | TR-UFFDP1-13-06299 | 2015-09-30 | 3 | 2207-NPCC-MWS-T-00643 | 2015-09-17 |  |  |  | MWS
|  |  |  | 0 | [5 empty] | CSE-OF-2207-240 | 2015-09-29 | 2207-NPCC-AO-T-03625 | 2015-09-30 | TR-UFFDP1-13-06316 | 2015-10-04 | 1 | 2207-NPCC-MWS-T-00663 | 2015-10-01 | GM-60295-0846 | 2015-10-21 | A | -
56 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 (@ULRP) | 2207-NN-RP-028 | AD162-573-G-06255 | B | 2 | 2014-09-06 |  |  | -51 | CSE-OF-2207-086 | 2014-10-27 | 2207-NPCC-AO-T-01721 | 2014-10-28 | TR-UFFDP1-13-04239 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00412 | 2014-10-29 | GM-60295-0566 | 2014-11-02 | ACCEPTED | -
57 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 (@WHT-5) | 2207-NN-RP-029 | AD162-480-G-06256 | B | 2 | 2014-08-04 |  |  | -51 | CSE-OF-2207-077 | 2014-09-24 | 2207-NPCC-AO-T-01553 | 2014-09-27 | TR-UFFDP1-13-04229 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00380 | 2014-10-01 | GM-60295-0525 | 2014-10-14 | ACCEPTED | -
58 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-5 TO WHT-2(@WHT-5) | 2207-NN-RP-030 | AD162-480-G-06257 | B | 2 | 2014-08-08 |  |  | -53 | CSE-OF-2207-081 | 2014-09-30 | 2207-NPCC-AO-T-01591 | 2014-10-02 | TR-UFFDP1-13-03978 | 2014-10-12 | ACCEPTED | 2207-NPCC-MWS-T-00382 | 2014-10-02 | GM-60295-0526 | 2014-10-14 | ACCEPTED | -
59 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-5 TO WHT-2(@WHT-2) | 2207-NN-RP-031 | AD162-475-G-06258 | B | 2 | 2014-08-26 |  |  | -85 | CSE-OF-2207-101 | 2014-11-20 | 2207-NPCC-AO-T-01850 | 2014-11-22 | TR-UFFDP1-13-04357 | 2014-11-29 | ACCEPTED | 2207-NPCC-MWS-T-00438 | 2014-11-24 | GM-60295-0605 | 2014-12-17 | ACCEPTED | -
60 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP (@WHT-3) | 2207-NN-RP-032 | AD162-476-G-06259 | B | 2 | 2014-09-26 |  |  | - | CSE-OF-2207-029 | 2014-07-22 | 2207-NPCC-AO-T-01277 | 2014-08-01 | TR-UFFDP1-13-03556 | 2014-08-12 | 2 | 2207-NPCC-MWS-T-00268 | 2014-08-03 |  | - | - | MWS
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-043 | 2014-09-04 | 2207-NPCC-AO-T-01417 | 2014-09-08 | TR-UFFDP1-13-03797 | 2014-09-11 | ACCEPTED | 2207-NPCC-MWS-T-00313 | 2014-09-09 | GM-60295-0424 | 2014-09-10 | B (Accepted with comments) | -
61 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP (@ULRP) | 2207-NN-RP-033 | AD162-573-G-06260 | B | 2 | 2014-09-09 |  |  | -22 | CSE-OF-2207-083 | 2014-10-01 | 2207-NPCC-AO-T-01600 | 2014-10-02 | TR-UFFDP1-13-03986 | 2014-10-13 | ACCEPTED | 2207-NPCC-MWS-T-00387 | 2014-10-08 | GM-60295-0530 | 2014-10-14 | ACCEPTED | -
62 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 (@WHT-1) | 2207-NN-RP-034 | AD162-474-G-06261 | B | 2 | 2014-10-21 |  |  | -19 | CSE-OF-2207-094 | 2014-11-09 | 2207-NPCC-AO-T-01788 | 2014-11-10 | TR-UFFDP1-13-04225 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00423 | 2014-11-11 | GM-60295-0582 | 2014-11-13 | ACCEPTED | -
63 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 (@WHT-3) | 2207-NN-RP-035 | AD162-476-G-06262 | B | 2 | 2014-09-29 |  |  | -1 | CSE-OF-2207-065 | 2014-09-17 | 2207-NPCC-AO-T-01493 | 2014-09-22 | TR-UFFDP1-13-03955 | 2014-10-08 | ACCEPTED | 2207-NPCC-MWS-T-00363 | 2014-09-24 | GM-60295-0501 | 2014-09-30 | ACCEPTED | -
64 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 (@WHT-1) | 2207-NN-RP-036 | AD162-474-G-06263 | B | 2 | 2014-10-25 |  |  | -18 | CSE-OF-2207-096 | 2014-11-12 | 2207-NPCC-AO-T-01812 | 2014-11-15 | TR-UFFDP1-13-04291 | 2014-11-22 | ACCEPTED | 2207-NPCC-MWS-T-00430 | 2014-11-17 | GM-60295-0595 | 2014-12-08 | ACCEPTED | -
65 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 (@WHT-3) | 2207-NN-RP-037 | AD162-476-G-06264 | B | 2 | 2014-10-03 |  |  | 17 | CSE-OF-2207-055 | 2014-09-14 | 2207-NPCC-AO-T-01459 | 2014-09-16 | TR-UFFDP1-13-04232 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00342 | 2014-09-18 | GM-60295-0496 | 2014-09-29 | B (Accepted with comments) | -
66 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 (@WHT-1) | 2207-NN-RP-038 | AD162-474-G-06265 | B | 2 | 2014-10-29 |  |  | -18 | CSE-OF-2207-097 | 2014-11-16 | 2207-NPCC-AO-T-01829 | 2014-11-18 | TR-UFFDP1-13-04331 | 2014-11-29 | ACCEPTED | 2207-NPCC-MWS-T-00432 | 2014-11-19 | GM-60295-0594 | 2014-12-08 | ACCEPTED | -
67 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 (@WHT-3) | 2207-NN-RP-039 | AD162-476-G-06266 | B | 2 | 2014-10-07 |  |  | 20 | CSE-OF-2207-063 | 2014-09-16 | 2207-NPCC-AO-T-01488 | 2014-09-22 | TR-UFFDP1-13-03922 | 2014-09-30 | ACCEPTED | 2207-NPCC-MWS-T-00364 | 2014-09-24 | GM-60295-0505 | 2014-10-12 | ACCEPTED | -
68 | RISER LIFT ANALYSIS REPORT FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP (@WHT-3) | 2207-NN-RP-040 | AD162-476-G-06267 | B | 2 | 2014-10-11 |  |  | 20 | CSE-OF-2207-051 | 2014-09-11 | 2207-NPCC-AO-T-01450 | 2014-09-12 | TR-UFFDP1-13-03846 | 2014-09-17 | 2 | 2207-NPCC-MWS-T-00330 | 2014-09-16 |  |  |  | MWS
|  |  |  | 0 | - | - |  |  |  | CSE-OF-2207-069 | 2014-09-21 | 2207-NPCC-AO-T-01505 | 2014-09-22 | TR-UFFDP1-13-03925 | 2014-09-30 | ACCEPTED | 2207-NPCC-MWS-T-00362 | 2014-09-24 | GM-60295-0487 | 2014-09-28 | ACCEPTED | -
69 | RISER LIFT ANALYSIS REPORT FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP (@ULRP) | 2207-NN-RP-041 | AD162-573-G-06268 | B | 2 | 2014-09-12 |  |  | -26 | V | - | 2207-NPCC-AO-T-01630 | 2014-10-09 | TR-UFFDP1-13-04020 | 2014-10-16 | ACCEPTED | 2207-NPCC-MWS-T-00394 | 2014-10-11 | GM-60295-0540 | 2014-10-15 | ACCEPTED | -
70 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP (@WHT-3) | 2207-NN-RP-042 | AD162-476-G-06269 | B | 2 | 2014-10-15 |  |  | 23 | CSE-OF-2207-047 | 2014-09-10 | 2207-NPCC-AO-T-01440 | 2014-09-11 | TR-UFFDP1-13-03838 | 2014-09-17 | 2 | 2207-NPCC-MWS-T-00319 | 2014-09-11 |  |  |  | MWS
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-072 | 2014-09-22 | 2207-NPCC-AO-T-01516 | 2014-09-22 |  | 2014-09-30 | ACCEPTED | 2207-NPCC-MWS-T-00370 | 2014-09-27 | GM-60295-0486 | 2014-09-28 | ACCEPTED | -
71 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP (@ULRP) | 2207-NN-RP-043 | AD162-573-G-06270 | B | 2 | 2014-09-15 |  |  | -23 | V | - | 2207-NPCC-AO-T-01631 | 2014-10-09 | TR-UFFDP1-13-04027 | 2014-10-16 | ACCEPTED | 2207-NPCC-MWS-T-00396 | 2014-10-11 | GM-60295-0558 | 2014-10-29 | ACCEPTED | -
72 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP (@WHT-3) | 2207-NN-RP-044 | AD162-476-G-06271 | B | 2 | 2014-10-19 |  |  | -9 | CSE-OF-2207-054 | 2014-09-11 | 2207-NPCC-AO-T-01460 | 2014-09-16 | TR-UFFDP1-13-03880 | 2014-09-23 | 2 | 2207-NPCC-MWS-T-00344 | 2014-09-18 | GM-60295-0480 | 2014-09-25 | ACCEPTED | -
|  |  |  | 0 | - | - |  |  | - | V | - | 2207-NPCC-AO-T-01629 | 2014-10-09 | TR-UFFDP1-13-04020 | 2014-10-16 | ACCEPTED | 2207-NPCC-MWS-T-00393 | 2014-10-11 | GM-60295-0518 | 2014-10-12 | ACCEPTED | -
73 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP (@ULRP) | 2207-NN-RP-045 | AD162-573-G-06272 | B | 2 | 2014-09-18 |  |  | -20 | V | - | 2207-NPCC-AO-T-01632 | 2014-10-09 | TR-UFFDP1-13-04027 | 2014-10-16 | ACCEPTED | 2207-NPCC-MWS-T-00395 | 2014-10-11 | GM-60295-0539 | 2014-10-15 | ACCEPTED | -
74 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 (@ULRP) | 2207-NN-RP-046 | AD162-573-G-06273 | B | 2 | 2014-09-21 |  |  | -42 | CSE-OF-2207-090 | 2014-11-02 | 2207-NPCC-AO-T-01752 | 2014-11-03 | TR-UFFDP1-13-04154 | 2014-11-08 | ACCEPTED | 2207-NPCC-MWS-T-00418 | 2014-11-05 | GM-60295-0574 | 2014-11-11 | ACCEPTED | -
75 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 (@WHT-5) | 2207-NN-RP-047 | AD162-480-G-06274 | B | 2 | 2014-08-12 |  |  | -44 | CSE-OF-2207-079 | 2014-09-28 | 2207-NPCC-AO-T-01571 | 2014-09-29 | TR-UFFDP1-13-03961 | 2014-10-06 | ACCEPTED | 2207-NPCC-MWS-T-00377 | 2014-10-01 | GM-60295-0506 | 2014-10-06 | B (Accepted with comments) | -
76 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5(@ULRP) | 2207-NN-RP-048 | AD162-573-G-06275 | B | 2 | 2014-09-24 |  |  | -33 | CSE-OF-2207-086 | 2014-10-27 | 2207-NPCC-AO-T-01721 | 2014-10-28 | TR-UFFDP1-13-04239 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00412 | 2014-10-29 | GM-60295-0567 | 2014-11-02 | ACCEPTED | -
77 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5 (@WHT-5) | 2207-NN-RP-049 | AD162-480-G-06276 | B | 2 | 2014-08-16 |  |  | -36 | CSE-OF-2207-069 | 2014-09-21 | 2207-NPCC-AO-T-01506 | 2014-09-24 | TR-UFFDP1-13-03956 | 2014-10-08 | ACCEPTED | 2207-NPCC-MWS-T-00371 | 2014-09-27 | GM-60295-0500 | 2014-09-30 | ACCEPTED | -
78 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 (@WHT-5) | 2207-NN-RP-050 | AD162-480-G-06277 | B | 2 | 2014-08-20 |  |  | -43 | CSE-OF-2207-084 | 2014-10-02 | 2207-NPCC-AO-T-01609 | 2014-10-07 | TR-UFFDP1-13-03985 | 2014-10-13 | ACCEPTED | 2207-NPCC-MWS-T-00388 | 2014-10-08 | GM-60295-0517 | 2014-10-12 | ACCEPTED | -
79 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 (@WHT-2) | 2207-NN-RP-051 | AD162-475-G-06278 | B | 2 | 2014-08-30 |  |  | -87 | CSE-OF-2207-102 | 2014-11-25 | 2207-NPCC-AO-T-01877 | 2014-11-26 | TR-UFFDP1-13-04387 | 2014-12-01 | ACCEPTED | 2207-NPCC-MWS-T-00439 | 2014-11-29 | GM-60295-0600 | 2014-12-17 | ACCEPTED | -
80 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 (@WHT-5) | 2207-NN-RP-052 | AD162-480-G-06279 | B | 2 | 2014-08-24 |  |  | -36 | CSE-OF-2207-080 | 2014-09-29 | 2207-NPCC-AO-T-01579 | 2014-09-30 | TR-UFFDP1-13-03974 | 2014-10-09 | ACCEPTED | 2207-NPCC-MWS-T-00385 | 2014-10-02 | GM-60295-0512 | 2014-10-06 | ACCEPTED | -
81 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 (@WHT-2) | 2207-NN-RP-053 | AD162-475-G-06280 | B | 2 | 2014-09-03 |  |  | -69 | CSE-OF-2207-096 | 2014-11-12 | 2207-NPCC-AO-T-01812 | 2014-11-15 | TR-UFFDP1-13-04291 | 2014-11-22 | ACCEPTED | 2207-NPCC-MWS-T-00430 | 2014-11-17 | GM-60295-0599 | 2014-12-17 | ACCEPTED | -
82 | RISER LIFT ANALYSIS REPORT FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP (@WHT-6) | 2207-NN-RP-128 | AD197-481-G-06281 | B | 2 | 2015-07-01 |  | 2015-04-01 | -1876 | CSE-OF-2207-263 | 2016-02-04 | 2207-NPCC-AO-T-04311 | 2016-02-08 | TR-UFFDP1-13-07067 | 2016-02-28 | 2 | 2207-NPCC-MWS-T-00750 | 2016-02-09 | GM-60295-0947 | 2016-02-22 | A | -
|  |  |  | C | 1 |  |  |  |  | CSE-OF-2207-282 | 2016-09-26 | 2207-NPCC-AO-T-05364 | 2016-09-28 | TR-UFFDP1-13-07895 | 2016-10-05 | 1 | 2207-NPCC-MWS-T-00856 | 2016-09-28
83 | RISER LIFT ANALYSIS REPORT FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP (@ULRP) | 2207-NN-RP-129 | AD197-573-G-06282 | B | 2 | 2015-07-05 |  | 2015-04-08 | -57 | CSE-OF-2207-210 | 2015-08-31 | 2207-NPCC-AO-T-03367 | 2015-09-02 | TR-UFFDP1-13-06189 | 2015-09-16 | 1 | 2207-NPCC-MWS-T-00615 | 2015-09-02 | GM-60295-0761 | 2015-09-06 | A | -
84 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 (@ULRP) | 2207-NN-RP-130 | AD197-573-G-06283 | B | 2 | 2015-07-09 |  | 2015-04-15 | -59 | CSE-OF-2207-124 | 2015-06-07 | 2207-NPCC-AO-T-02822 | 2015-06-09 | TR-UFFDP1-13-05652 | 2015-06-14 | 1 | 2207-NPCC-MWS-T-00502 | 2015-06-11 | GM-60295-0762 | 2015-09-06 | A | -
85 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 (@WHT-7) | 2207-NN-RP-131 | AD197-482-G-06284 | B | 2 | 2015-04-22 |  | 2015-04-22 | 2 | CSE-OF-2207-116 | 2015-04-20 | 2207-NPCC-AO-T-02546 | 2015-04-29 | TR-UFFDP1-13-05465 | 2015-05-17 | 2 | 2207-NPCC-MWS-T-00485 | 2015-05-13 | GM-60295-0669 | 2015-05-18 | A | -
|  |  |  | C | - | - |  |  | - | CSE-OF-2207-177 | 2015-08-16 | 2207-NPCC-AO-T-03232 | 2015-08-17 | TR-UFFDP1-13-06014 | 2015-08-23 | 1 | 2207-NPCC-MWS-T-00579 | 2015-08-18 | GM-60295-0764 | 2015-09-06 | A | -
86 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 (@WHT-7) | 2207-NN-RP-132 | AD197-482-G-06285 | B | 2 | 2015-04-29 |  | 2015-04-29 | 14 | CSE-OF-2207-115 | 2015-04-15 | 2207-NPCC-AO-T-02532 | 2015-04-29 | TR-UFFDP1-13-05454 | 2015-05-12 | 2 | 2207-NPCC-MWS-T-00486 | 2015-05-13 | GM-60295-0670 | 2015-05-18 | A | -
|  |  |  | C | - | - |  |  | - | CSE-OF-2207-173 | 2015-08-13 | 2207-NPCC-AO-T-03211 | 2015-08-16 | TR-UFFDP1-13-05990 | 2015-08-18 | 1 | 2207-NPCC-MWS-T-00572 | 2015-08-16 | GM-60295-0765 | 2015-09-06 | A | -
87 | RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 (@WHT-8) | 2207-NN-RP-133 | AD197-483-G-06286 | B | 2 | 2015-05-06 |  | 2015-05-06 | 21 | CSE-OF-2207-113 | 2015-04-15 | 2207-NPCC-AO-T-02526 | 2015-04-29 | TR-UFFDP1-13-05453 | 2015-05-12 | 2 | 2207-NPCC-MWS-T-00487 | 2015-05-13 | GM-60295-0671 | 2015-05-18 | A | -
|  |  |  | C | - | - |  |  | - | CSE-OF-2207-170 | 2015-08-12 | 2207-NPCC-AO-T-03173 | 2015-08-13 | TR-UFFDP1-13-05988 | 2015-08-18 | 1 | 2207-NPCC-MWS-T-00567 | 2015-08-13 | GM-60295-0766 | 2015-09-06 | A | -
88 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 (@WHT-8) | 2207-NN-RP-134 | AD197-483-G-06287 | B | 2 | 2015-05-13 |  | 2015-05-13 | 20 | CSE-OF-2207-117 | 2015-04-23 | 2207-NPCC-AO-T-02563 | 2015-04-29 | TR-UFFDP1-13-05488 | 2015-05-17 | 2 | 2207-NPCC-MWS-T-00484 | 2015-05-13 | GM-60295-0663 | 2015-05-17 | A | -
|  |  |  | C | [5 empty] | CSE-OF-2207-168 | 2015-08-11 | 2207-NPCC-AO-T-03160 | 2015-08-12 | TR-UFFDP1-13-05983 | 2015-08-16 | 1 | 2207-NPCC-MWS-T-00566 | 2015-08-12 | GM-60295-0767 | 2015-09-06 | A | -
89 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 (@WHT-7) | 2207-NN-RP-135 | AD197-482-G-06288 | B | 2 | 2015-07-13 |  | 2015-05-20 | -45 | CSE-OF-2207-203 | 2015-08-27 | 2207-NPCC-AO-T-03329 | 2015-08-30 | TR-UFFDP1-13-06116 | 2015-09-03 | 2 | 2207-NPCC-MWS-T-00610 | 2015-09-02 | GM-60295-0768 | 2015-09-06 | A | -
|  |  |  | CRS | - | - |  |  |  | CSE-OF-2207-255 | 2015-12-15 | 2207-NPCC-AO-T-04076 | 2015-12-17 | TR-UFFDP1-13-06797 | 2016-01-03 | 1 | 2207-NPCC-MWS-T-00723 | 2015-12-17 |  |  |  | -
90 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 (@ WHT-7) | 2207-NN-RP-136 | AD197-482-G-06289 | B | 2 | 2015-07-17 |  | 2015-05-27 | -33 | CSE-OF-2207-186 | 2015-08-19 | 2207-NPCC-AO-T-03251 | 2015-08-19 | TR-UFFDP1-13-06045 | 2015-08-27 | 2 | 2207-NPCC-MWS-T-00589 | 2015-08-20 | GM-60295-0769 | 2015-09-06 | A | -
|  |  |  | CRS | - | - |  |  |  | CSE-OF-2207-255 | 2015-12-15 | 2207-NPCC-AO-T-04076 | 2015-12-17 | TR-UFFDP1-13-06797 | 2016-01-03 | 1 | 2207-NPCC-MWS-T-00723 | 2015-12-17
91 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 (@ WHT-8) | 2207-NN-RP-137 | AD197-483-G-06290 | B | 2 | 2015-06-03 |  | 2015-06-03 | 44 | CSE-OF-2207-116 | 2015-04-20 | 2207-NPCC-AO-T-02546 | 2015-04-29 | TR-UFFDP1-13-05465 | 2015-05-17 | 2 | 2207-NPCC-MWS-T-00485 | 2015-05-13 | GM-60295-0672 | 2015-05-18 | A | -
|  |  |  | C | - | - |  |  |  | CSE-OF-2207-168 | 2015-08-11 | 2207-NPCC-AO-T-03160 | 2015-08-12 | TR-UFFDP1-13-05983 | 2015-08-16 | 1 | 2207-NPCC-MWS-T-00566 | 2015-08-12 | GM-60295-0770 | 2015-09-06 | A | -
92 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 (@ULRP) | 2207-NN-RP-138 | AD197-573-G-06291 | B | 2 | 2015-07-21 |  | 2015-06-10 | -37 | CSE-OF-2207-201 | 2015-08-27 | 2207-NPCC-AO-T-03325 | 2015-08-30 | TR-UFFDP1-13-06139 | 2015-09-08 | 1 | 2207-NPCC-MWS-T-00608 | 2015-09-02 | GM-60295-0771 | 2015-09-06 | A | -
93 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 (@WHT-7) | 2207-NN-RP-139 | AD197-482-G-06292 | B | 2 | 2015-07-25 |  | 2015-06-17 | -23 | CSE-OF-2207-180 | 2015-08-17 | 2207-NPCC-AO-T-03239 | 2015-08-18 | TR-UFFDP1-13-06017 | 2015-08-23 | 1 | 2207-NPCC-MWS-T-00578 | 2015-08-18 | GM-60295-0772 | 2015-09-06 | A | -
94 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP (@WHT-7) | 2207-NN-RP-140 | AD197-482-G-06293 | B | 2 | 2015-07-29 |  | 2015-06-24 | -22 | CSE-OF-2207-187 | 2015-08-20 | 2207-NPCC-AO-T-03261 | 2015-08-23 | TR-UFFDP1-13-06034 | 2015-08-26 | 2 | 2207-NPCC-MWS-T-00591 | 2015-08-23 | GM-60295-0773 | 2015-09-06 | A | -
|  |  |  | CRS | - | - |  |  |  | CSE-OF-2207-255 | 2015-12-15 | 2207-NPCC-AO-T-04076 | 2015-12-17 | TR-UFFDP1-13-06797 | 2016-01-03 | 1 | 2207-NPCC-MWS-T-00723 | 2015-12-17
95 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP (@ULRP) | 2207-NN-RP-141 | AD197-573-G-06294 | B | 2 | 2015-08-02 |  | 2015-07-01 | -24 | CSE-OF-2207-198 | 2015-08-26 | 2207-NPCC-AO-T-03313 | 2015-08-27 | TR-UFFDP1-13-06137 | 2015-09-08 | 1 | 2207-NPCC-MWS-T-00603 | 2015-08-27 | GM-60295-0774 | 2015-09-06 | A | -
96 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 (@ULRP) | 2207-NN-RP-142 | AD197-573-G-06295 | B | 2 | 2015-08-06 |  | 2015-07-08 | -28 | CSE-OF-2207-215 | 2015-09-03 | 2207-NPCC-AO-T-03404 | 2015-09-06 | TR-UFFDP1-13-06188 | 2015-09-16 | 1 | 2207-NPCC-MWS-T-00623 | 2015-09-07 | GM-60295-0809 | 2015-09-14 | A | -
97 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 (@WHT-6) | 2207-NN-RP-143 | AD197-481-G-06296 | B | 2 | 2015-08-10 |  | 2015-07-15 | -1836 | CSE-OF-2207-272 | 2016-02-15 | 2207-NPCC-AO-T-04366 | 2016-02-21 | TR-UFFDP1-13-07099 | 2016-03-02 | 2 | 2207-NPCC-MWS-T-00769 | 2016-02-21 | GM-60295-0943 | 2016-02-22 | A | -
|  |  |  | C | 1 |  |  |  |  | CSE-OF-2207-282 | 2016-09-26 | 2207-NPCC-AO-T-05364 | 2016-09-28 | TR-UFFDP1-13-07895 | 2016-10-05 | 1 | 2207-NPCC-MWS-T-00856 | 2016-09-28
98 | RISER LIFT ANALYSIS REPORT FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP (@WHT-6) | 2207-NN-RP-144 | AD197-481-G-06297 | B | 2 | 2015-08-14 |  | 2015-07-22 | -1832 | CSE-OF-2207-271 | 2016-02-11 | 2207-NPCC-AO-T-04357 | 2016-02-15 | TR-UFFDP1-13-07098 | 2016-03-02 | 2 | 2207-NPCC-MWS-T-00764 | 2016-02-17 | GM-60295-0941 | 2016-02-21 | A | -
|  |  |  | C | 1 |  |  |  |  | CSE-OF-2207-283 | 2016-09-27 | 2207-NPCC-AO-T-05368 | 2016-09-29 | TR-UFFDP1-13-07896 | 2016-10-05 | 1 | 2207-NPCC-MWS-T-00857 | 2016-10-03
99 | RISER LIFT ANALYSIS REPORT FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP (@ULRP) | 2207-NN-RP-145 | AD197-573-G-06298 | B | 2 | 2015-08-18 |  | 2015-07-29 | -13 | CSE-OF-2207-206 | 2015-08-31 | 2207-NPCC-AO-T-03358 | 2015-09-06 | TR-UFFDP1-13-06187 | 2015-09-16 | 1 | 2207-NPCC-MWS-T-00621 | 2015-09-07 | GM-60295-0810 | 2015-09-14 | A | -
100 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP (@WHT-6) | 2207-NN-RP-146 | AD197-481-G-06299 | B | 2 | 2015-08-22 |  | 2015-08-05 | -1824 | CSE-OF-2207-273 | 2016-02-15 | 2207-NPCC-AO-T-04371 | 2016-02-21 | TR-UFFDP1-13-07096 | 2016-03-02 | 2 | 2207-NPCC-MWS-T-00768 | 2016-02-21 | GM-60295-0942 | 2016-02-22 | A | -
|  |  |  | C | 1 |  |  |  |  | CSE-OF-2207-283 | 2016-09-27 | 2207-NPCC-AO-T-05368 | 2016-09-29 | TR-UFFDP1-13-07896 | 2016-10-05 | 1 | 2207-NPCC-MWS-T-00857 | 2016-10-03
101 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP (@ULRP) | 2207-NN-RP-147 | AD197-573-G-06300 | B | 2 | 2015-08-26 |  | 2015-08-12 | -7 | CSE-OF-2207-213 | 2015-09-02 | 2207-NPCC-AO-T-03377 | 2015-09-03 | TR-UFFDP1-13-06186 | 2015-09-16 | 1 | 2207-NPCC-MWS-T-00618 | 2015-09-06 | GM-60295-0811 | 2015-09-14 | A | -
102 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 (@WHT-6) | 2207-NN-RP-148 | AD197-481-G-06301 | B | 2 | 2015-08-30 |  | 2015-08-19 | -1816 | CSE-OF-2207-266 | 2016-02-08 | 2207-NPCC-AO-T-04327 | 2016-02-11 | TR-UFFDP1-13-07090 | 2016-03-05 | 2 | 2207-NPCC-MWS-T-00755 | 2015-02-11 | GM-60295-0948 | 2016-02-22 | A | -
|  |  |  | C | 1 |  |  |  |  | CSE-OF-2207-282 | 2016-09-26 | 2207-NPCC-AO-T-05364 | 2016-09-28 | TR-UFFDP1-13-07895 | 2016-10-05 | 1 | 2207-NPCC-MWS-T-00856 | 2016-09-28
103 | RISER LIFT ANALYSIS REPORT FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 (@WHT-4) | 2207-NN-RP-149 | AD197-477-G-06302 | B | 2 | 2015-09-03 |  | 2015-08-26 | -46 | CSE-OF-2207-238 | 2015-09-28 | 2207-NPCC-AO-T-03605 | 2015-09-30 | TR-UFFDP1-13-06315 | 2015-10-04 | 1 | 2207-NPCC-MWS-T-00660 | 2015-10-01 | GM-60295-0847 | 2015-10-21 | A | -
104 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 (@WHT-4) | 2207-NN-RP-150 | AD197-477-G-06303 | B | 2 | 2015-09-07 |  | 2015-09-02 | -42 | CSE-OF-2207-238 | 2015-09-28 | 2207-NPCC-AO-T-03605 | 2015-09-30 | TR-UFFDP1-13-06315 | 2015-10-04 | 1 | 2207-NPCC-MWS-T-00660 | 2015-10-01 | GM-60295-0848 | 2015-10-21 | A | -
105 | RISER LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 (@WHT-6) | 2207-NN-RP-151 | AD197-481-G-06304 | B | 2 | 2015-09-11 |  | 2015-09-09 | -1804 | CSE-OF-2207-269 | 2016-02-09 | 2207-NPCC-AO-T-04345 | 2016-02-11 | TR-UFFDP1-13-07093 | 2016-03-02 | 2 | 2207-NPCC-MWS-T-00760 | 2015-02-11 |  |  |  | MWS
|  |  |  | C | 1 |  |  |  |  | CSE-OF-2207-282 | 2016-09-26 | 2207-NPCC-AO-T-05364 | 2016-09-28 | TR-UFFDP1-13-07895 | 2016-10-05 | 1 | 2207-NPCC-MWS-T-00856 | 2016-09-28
106 | RISER LIFT ANALYSIS REPORT FOR 20" MOL FROM ULRP TO KP34.83 (@ULRP) | 2207-NN-RP-152 | AD197-573-G-06305 | B | 2 | 2015-09-15 |  | 2015-09-16 | -34 | CSE-OF-2207-237 | 2015-09-22 | 2207-NPCC-AO-T-03567 | 2015-09-23 | TR-UFFDP1-13-06294 | 2015-09-30 | 1 | 2207-NPCC-MWS-T-00656 | 2015-09-22 | GM-60295-0845 | 2015-10-21 | A | -
107 | SEAFASTENING DESIGN REPORT FOR CC PIPES FOR AWALCO-1 (TRIP-1) (Campaign-1) | 2207-NN-RP-054 | AD162-562-G-06306 | B | 2 | 2014-06-04 |  |  |  | CSE-OF-2207-009 | 2014-06-05 | 2207-NPCC-AO-T-01085 | 2014-06-08 | TR-UFFDP1-13-03257 | 2014-07-02 | 1 | 2207-NPCC-MWS-T-00147 | 2014-06-08 | GM/60295/0239 | 2014-06-12 | ACCEPTED | -
108 | SEAFASTENING DESIGN REPORT FOR CC PIPES FOR GOGAS-252 (TRIP-2) (Campaign-1) | 2207-NN-RP-055 | AD162-562-G-06307 | B | 2 | 2014-06-07 |  |  |  | CSE-OF-2207-011 | 2014-06-09 | 2207-NPCC-AO-T-01097 | 2014-06-11 | TR-UFFDP1-13-03664 | 2014-08-24 | ACCEPTED | 2207-NPCC-MWS-T-00167 | 2014-06-15 | GM/60295/0262 | 2014-06-18 | ACCEPTED | -
109 | SEAFASTENING DESIGN REPORT FOR CC PIPES FOR CB-7 (TRIP-6) (Campaign-1) | 2207-NN-RP-056 | AD162-562-G-06308 | B | 2 | 2014-06-15 |  |  | reused | CSE-OF-2207-074 | 2014-09-23 | 2207-NPCC-AO-T-01538 | 2014-09-25 | TR-UFFDP1-13-03949 | 2014-10-01 | ACCEPTED | 2207-NPCC-MWS-T-00374 | 2014-09-27 | GM-60295-0471 | 2014-09-24 | ACCEPTED | -
110 | SEAFASTENING DESIGN REPORT FOR CC PIPES -1 (Campaign-2) | 2207-NN-RP-153 | AD197-473-G-06309 | B | 2 | 2015-06-10 |  | 2015-04-01 | -8 | CSE-OF-2207-132 | 2015-06-18 | 2207-NPCC-AO-T-02913 | 2015-06-22 | TR-UFFDP1-13-05762 | 2015-07-02 | 2 | 2207-NPCC-MWS-T-00511 | 2015-06-22 | GM-60295-0684 | 2015-06-21 | A | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-147 | 2015-07-08 | 2207-NPCC-AO-T-03026 | 2015-07-12 | TR-UFFDP1-13-05856 | 2015-07-22 | 1 | 2207-NPCC-MWS-T-00530 | 2015-07-14 | GM-60295-0887 | 2015-11-25 | A | -
111 | SEAFASTENING DESIGN REPORT FOR CC PIPES -2 ON GOGAS-250 (Campaign-2) | 2207-NN-RP-154 | AD197-473-G-06310 | B | 2 | 2015-06-14 |  | 2015-04-08 | -15 | CSE-OF-2207-136 | 2015-06-29 | 2207-NPCC-AO-T-02968 | 2015-06-30 | TR-UFFDP1-13-05811 | 2015-07-06 | 2 | 2207-NPCC-MWS-T-00514 | 2015-07-01 | GM-60295-0691 | 2015-06-30 | A | -
|  |  |  | 0 | - | - |  |  | - | CSE-OF-2207-146 | 2015-07-08 | 2207-NPCC-AO-T-03025 | 2015-07-12 | TR-UFFDP1-13-05861 | 2015-07-22 | 1 | 2207-NPCC-MWS-T-00529 | 2015-07-14 | GM-60295-0888 | 2015-11-29 | A | -
112 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE COATED PIPES ON GAC-82 | 2207-NN-RP-155 | AD197-473-G-06311 | B | 2 | 2015-06-18 |  | 2015-04-15 | 23 | CSE-OF-2207-161 | 2015-08-05 | 2207-NPCC-AO-T-03137 | 2015-08-06 | TR-UFFDP1-13-06398 | 2015-10-21 | 1 | 2207-NPCC-MWS-T-00558 | 2015-08-06 | GM-60295-0730 | 2015-08-11 | A | -
113 | SEAFASTENING DESIGN REPORT FOR RISERS & SPOOLS -1 (Campaign-1) | 2207-NN-RP-057 | AD162-562-G-06312 |  | 2 | 2014-08-26 |  |  | -2185
114 | SEAFASTENING DESIGN REPORT FOR RISERS & SPOOLS -2 (Campaign-1) | 2207-NN-RP-058 | AD162-562-G-06313 |  | 2 | 2014-09-19 |  |  | -2161
115 | SEAFASTENING DESIGN REPORT FOR RISERS & SPOOLS -1 (Campaign-2) | 2207-NN-RP-156 | AD197-473-G-06314 | Not issued | 2 | 2015-07-30 |  | 2015-09-09 | -1847
116 | SEAFASTENING DESIGN REPORT FOR RISERS & SPOOLS -2 (Campaign-2) | 2207-NN-RP-157 | AD197-473-G-06315 | Not issued | 2 | 2015-08-03 |  | 2015-09-16 | -1843
117 | RISER LIFT ANALYSIS REPORT FOR 20" MOL FROM ULRP TO ZIRKU AT ULRP | 2207-NN-RP-158 | AD197-573/602-G-06316 | B | 2 | 2015-09-07 |  | 2015-10-01 | - | CSE-OF-2207-227 | 2015-09-13 | 2207-NPCC-AO-T-03495 | 2015-09-14 | TR-UFFDP1-13-06398 | 2015-10-21 | 1 | 2207-NPCC-MWS-T-00635 | 2015-09-15 | GM-60295-0825 | 2015-09-20 | A | -
118 | STACKING ANALYSIS FOR 20” MOL OF SARB-3 SECTION (Campaign-1) | 2207-NN-RP-059 | AD162-562-G-06317 | A | 2 | - |  |  |  | - | - | - | - | - | - | - | - | - |  | - | -
|  |  |  | B | 2 | - |  |  |  | Sent by DC through Del boy | 2014-02-06 | 2207-NPCC-AO-T-00574 | 2014-02-06 | TR-UFFDP1-13-01684 | 2014-02-10 | 2 | 2207-NPCC-MWS-T-00034 | 2014-02-06 | GM/60295/042 | 2014-02-09 | A (Accepted without comment) | -
119 | OFFSHORE CONSTRUCTION ENGINEERING REGISTER (PIPELINES & CABLES) | 2207-NN-RP-060 | AD162-562-G-06318 | B | 2 | [5 empty] | 2014-03-26
120 | SEAFASTENING DESIGN REPORT FOR CABLE BASKET ON CB-7 (Campaign-1) | 2207-NN-RP-061 | AD162-562-G-06319 | B | 2 | - |  |  | - | CSE-OF-2207-105 | 2015-01-06 | 2207-NPCC-AO-T-02020 | 2015-01-07 | TR-UFFDP1-13-04723 | 2015-01-22 | 2 | 2207-NPCC-MWS-T-00450 | 2014-01-08 | GM-60295-0611 | 2015-01-11 | ACCEPTED | CLIENT
121 | SEA FASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE COATED PIPES ON GAC-66(TRIP-6) | 2207-NN-RP-159 | AD197-473-G-06320 | B | - | - |  |  | - | CSE-OF-2207-183 | 2015-08-18 | 2207-NPCC-AO-T-03244 | 2015-08-18 | TR-UFFDP1-13-06029 | 2015-08-25 | 3 | 2207-NPCC-MWS-T-00583 | 2015-08-18 | GM-60295-0889 | 2015-11-29 | A | -
122 | SEA FASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE COATED PIPES ON GAC-67(TRIP-8) | 2207-NN-RP-160 | AD197-473-G-06321 | B | - | - |  |  | - | CSE-OF-2207-204 | 2015-08-27 | 2207-NPCC-AO-T-03330 | 2015-08-30 | TR-UFFDP1-13-06097 | 2015-09-03 | 1 | 2207-NPCC-MWS-T-00611 | 2015-09-02 | GM-60295-0890 | 2015-11-29 | A | -
123 | WELD REPAIR ANALYSIS FOR 20" MOL P/L FROM ULRP TO KP89.256 | 2207-NN-RP-161 | AD197-573/602-G-06322 | B | - | - |  |  |  | CSE-OF-2207-234 | 2015-09-21 | 2207-NPCC-AO-T-03555 | 2015-09-22 | TR-UFFDP1-13-06295 | 2015-09-30 | 1 | 2207-NPCC-MWS-T-00653 | 2015-09-22 |  |  |  | MWS
124 | AIRBAG LIFT ANALYSIS REPORT FOR 20” MOL | 2207-NN-RP-162 | AD197-473-G-06323 | B | - | - |  |  |  | CSE-OF-2207-249 | 2015-12-01 | 2207-NPCC-AO-T-04018 | 2015-12-06 | TR-UFFDP1-13-06710 | 2015-12-10 | 2 | 2207-NPCC-MWS-T-00716 | 2015-12-06 | GM-60295-0924 | 2016-01-03 | A | -
|  |  |  | 0 | - | - |  |  |  | CSE-OF-2207-254 | 2015-12-14 | 2207-NPCC-AO-T-04073 | 2015-12-16 | TR-UFFDP1-13-06753 | 2015-12-21 | 1 | 2207-NPCC-MWS-T-00722 | 2015-12-16 | GM-60295-0924 | 2016-01-03 | A | -
125 | AIRBAG LIFTING ANALYSIS REPORT OF 20” MOL FOR SLEEPER SHIFTING @ CR-10 | 2207-NN-RP-163 | AD197-473-G-06324 | B | - | - |  |  |  | CSE-OF-2207-256 | 2015-12-17 | 2207-NPCC-AO-T-04047 | 2015-12-27 | TR-UFFDP1-13-06792 | 2015-12-31 | 2 | - | - | GM-60295-0920 | 2016-01-03 | A | not applicable to MWS but still received the response
|  |  |  | 0 | - | - |  |  |  | CSE-OF-2207-259 | 2015-01-04 | 2207-NPCC-AO-T-04169 | 2015-01-04 | TR-UFFDP1-13-06826 | 2016-01-07 | 1 | 2207-NPCC-MWS-T-00734 | 2016-01-07 | GM-60295-928 | 2016-01-11 | B (Accepted with comments) | -
|  |  |  | 1 | - | - |  |  |  | CSE-OF-2207-260 | 2016-01-12 | 2207-NPCC-AO-T-04187 | 2016-01-13 | TR-UFFDP1-13-07249 | 2016-03-29 | 1 | 2207-NPCC-MWS-T-00740 | 2016-01-13 | GM-60295-0934 | 2016-01-19 | B (Accepted with comments) | -
|  |  |  | CRS to GM | [12 empty] | 2207-NPCC-MWS-T-00748 | 2016-02-04 | GM-60295-0939 | 2016-02-04 | A
126 | INSTALLATION ANALYSIS REPORT FOR SUBSEA FO CABLE REPAIR | 2207-NN-RP-164 | AD197-473-G-06325 | B | 2 |  |  |  |  | CSE-OF-2207-276 | 2016-04-24 | 2207-NPCC-AO-T-04680 | 2016-04-25 | TR-UFFDP1-13-07429 | 2016-04-28 | 2 | 2207-NPCC-MWS-T-00802 | 2016-04-25
|  |  |  | 0 | 1 |  |  |  |  | CSE-OF-2207-277 | 2016-05-09 | 2207-NPCC-AO-T-04748 | 2016-05-10 | TR-UFFDP1-13-07467 | 2016-05-17 | 1
127 | DAVIT LIFT ANALYSIS REPORT FOR RISER AT WHT-6 | 2207-NN-RP-165 | AD197-481-G-06326 | B | 2 |  |  |  |  | CSE-OF-2207-280 | 2016-09-25 | 2207-NPCC-AO-T-05361 | 2016-09-28 | TR-UFFDP1-13-07906 | 2016-10-10 | 2 | 2207-NPCC-MWS-T-00853 | 2016-09-28 | GM/60295/1032 | 2016-10-14 | B
|  |  |  | 0 | 1 |  |  |  |  | CSE-OF-2207-286 | 2016-10-13 | 2207-NPCC-AO-T-05443 | 2016-10-17 | TR-UFFDP1-13-07990 | 2016-11-03 | 1 | 2207-NPCC-MWS-T-00873 | 2016-10-17
128 | PIPELINE REPAIR REPORT FOR 10" WI P/L FROM ULRP TO WHT-6 AT WHT-6 | 2207-NN-RP-166 | AD197-481-G-06327 | B | 2 |  |  |  |  | CSE-OF-2207-292 | 2016-11-01 | 2207-NPCC-AO-T-05534 | 2016-11-03 | TR-UFFDP1-13-08156 | 2016-12-27 | 1 | 2207-NPCC-MWS-T-00897 | 2016-11-03
Formulas:
REMAINING DAYS = [SUBMISSION PLAN]-TODAY()
Old DATES = [Old DATES, row above]+15

## Documents - Naval Marine
|  | ABU DHABI MARINE OPERATING COMPANY (ADMA-OPCO) | [13 empty] | NPCC DOC. No.: |  |  |  | 2207-NN-RP-060
|  | UMM LULU PACKAGE-1 FFD PROJECT | [13 empty] | ADMA DOC. No. : |  |  |  | AD162-562-G-06318
|  | NPCC PROJECT NO. 2207 | [13 empty] | REVISION : |  |  |  | B
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (NAVEL MARINE) | [13 empty] | DATE : |  |  |  | 2014-03-25
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | OLD DATES | REMAINING DAYS | NPCC |  |  |  | ADMA-OPCO |  |  | GMC |  |  |  |  | REMARKS |  |  | NPCC |  | ADMA-OPCO |  |  | GMC |  |  |  |  | REMARKS
[9 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS | [5 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[9 empty] | CSE TO PMT |  | PMT TO ADMA-OPCO |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC |  |  |  | CSE TO PMT |  | PMT TO ADMA-OPCO |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[9 empty] | REF | DATE | REF | DATE | REF | DATE | CODE | REF | DATE | REF | DATE | CODE |  | REF | DATE | REF | DATE | REF | DATE | CODE | REF | DATE | REF | DATE | CODE
1 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 6", 10" AND 16" WELL FLUID P/L FROM ULRP TO WHT-5 | 2207-ZZ-CL-001 | AD162-573/480-G-03901 | B | 2 | 2014-06-20 |  | See Remarks | CSE-OF-2207-016 | 2014-07-01 | 2207-NPCC-AO-T-01193 | 2014-07-02 | TR-UFFDP1-13-03543 | 2014-08-10 | Accepted | 2207-NPCC-MWS-T-00205 | 2014-07-07 | GM/60295/0296 | 2014-07-09 | NOT ACCEPTED | Merged into single report with SR.NO 10,11, CLIENT
|  |  |  | C |  |  |  |  | CSE-OF-2207-023 | 2014-07-13 | 2207-NPCC-AO-T-01233 | 2014-07-15 | TR-UFFDP1-13-03393 | 2014-07-17 | ACCEPTED WITH COMMENTS | 2207-NPCC-MWS-T-00220 | 2014-07-15 | GM/60295/0315 | 2014-07-22 | ACCEPTED
2 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 16", 10" AND 6" WELL FLUID P/L FROM WHT-5 TO WHT-2 | 2207-ZZ-CL-002 | AD162-480/475-G-03902 | B | 2 | 2014-07-29 |  | See Remarks | CSE-OF-2207-028 | 2014-07-22 | 2207-NPCC-AO-T-01275 | 2014-07-30 | TR-UFFDP1-13-03492 | 2014-08-04 | Accepted | 2207-NPCC-MWS-T-00264 | 2014-07-31 | GM/60295/0373 | 2014-08-18 | ACCEPTED | Merged into single report with SR.NO 12,13, -
3 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 6", 8", 10" AND 16" WELL FLUID P/L FROM WHT-3 TO ULRP | 2207-ZZ-CL-003 | AD162-476/573-G-03903 | B | 2 | 2014-05-28 |  | See Remarks | CSE-OF-2207-015 | 2014-06-25 | 2207-NPCC-AO-T-01172 | 2014-06-26 | TR-UFFDP1-13-03337 | 2014-07-10 | ACCEPTED WITH COMMENTS | 2207-NPCC-MWS-T-00197 | 2014-06-30 | GM/60295/0286 | 2014-07-01 | ACCEPTED WITH COMMENTS | Merged into single report with SR.NO 7,8,9
|  |  |  | C | 1 | - |  |  | CSE-OF-2207-020 | 2014-07-10 | 2207-NPCC-AO-T-01217 | 2014-07-13 | TR-UFFDP1-13-03542 | 2014-08-10 | Accepted | 2207-NPCC-MWS-T-00219 | 2014-07-15 | GM/60295/0312 | 2014-07-17 | ACCEPTED | CLIENT
4 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 16", 10" AND 6" WELL FLUID P/L FROM WHT-1 TO WHT-3 | 2207-ZZ-CL-004 | AD162-474/476-G-03904 | B | 2 | 2014-06-25 |  | See Remarks | CSE-OF-2207-035 | 2014-08-06 | 2207-NPCC-AO-T-01326 | 2014-08-07 | TR-UFFDP1-13-03558 | 2014-08-12 | Accepted | 2207-NPCC-MWS-T-00274 | 2014-08-08 | GM/60295/0372 | 2014-08-18 | ACCEPTED | Merged into single report with SR.NO 5,6 -
5 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 | 2207-ZZ-CL-005 | AD162-474/476-G-03905 | Merged into 004 | 2 | 2014-07-01 |  | See Remarks | [12 empty] | Merged into 2207-ZZ-CL-004
6 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 | 2207-ZZ-CL-006 | AD162-474/476-G-03906 | Merged into 004 | 2 | 2014-07-07 |  | See Remarks | [12 empty] | Merged into 2207-ZZ-CL-004
7 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP | 2207-ZZ-CL-007 | AD162-476/573-G-03907 | Merged into 003 | 2 | 2014-06-03 |  | See Remarks | [12 empty] | Merged into 2207-ZZ-CL-003
8 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP | 2207-ZZ-CL-008 | AD162-476/573-G-03908 | Merged into 003 | 2 | 2014-06-10 |  | See Remarks | [12 empty] | Merged into 2207-ZZ-CL-003
9 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP | 2207-ZZ-CL-009 | AD162-476/573-G-03909 | Merged into 003 | 2 | 2014-06-05 |  | See Remarks | [12 empty] | Merged into 2207-ZZ-CL-003
10 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 | 2207-ZZ-CL-010 | AD162-573/480-G-03910 | Merged into 001 | 2 | 2014-06-15 |  | See Remarks | [12 empty] | Merged into 2207-ZZ-CL-001
11 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5 | 2207-ZZ-CL-011 | AD162-573/480-G-03911 | Merged into 001 | 2 | 2014-06-15 |  | See Remarks | [12 empty] | Merged into 2207-ZZ-CL-001
12 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 | 2207-ZZ-CL-012 | AD162-480/475-G-03912 | Merged into 002 | 2 | 2014-07-22 |  | See Remarks | [12 empty] | Merged into 2207-ZZ-CL-002
13 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 | 2207-ZZ-CL-013 | AD162-480/475-G-03913 | Merged into 002 | 2 | 2014-07-14 |  | See Remarks | [12 empty] | Merged into 2207-ZZ-CL-002
14 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP | 2207-ZZ-CL-100 | AD197-481/477-G-03914 | Not Issued | 2 | 2015-06-17 | 2015-03-31 | -1890
15 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7, 6" GAS LIFT P/L FROM ULRP TO WHT-7 & 10" WATER INJECTION P/L FROM WHT-7 TO ULRP | 2207-ZZ-CL-101 | AD197-573/482-G-03915 | B | 2 | 2015-06-29 | 2015-04-21 | 29 | CSE-OF-2207-121 | 2015-06-01 | 2207-NPCC-AO-T-02778 | 2015-06-02 | TR-UFFDP1-13-05576 | 2015-06-08 | 1 | 2207-NPCC-MWS-T-00498 | 2015-06-02 | GM-60295-0686 | 2015-06-22 | A | 3 reports merged 2207-ZZ-CL-101, 2207-ZZ-CL-105, 2207-ZZ-CL-106
16 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 16" WELL FLUID, 10" WATER INJECTION, 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 | 2207-ZZ-CL-102 | AD197-482/483-G-03916 | B | 2 | 2015-06-05 | 2015-05-12 | -31 | CSE-OF-2207-143 | 2015-07-06 | 2207-NPCC-AO-T-03004 | 2015-07-08 | TR-UFFDP1-13-06389 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00525 | 2015-07-12 | GM-60295-0886 | 2015-11-25 | A | '3 reports merged 2207-ZZ-CL-102, 2207-ZZ-CL-103, 2207-ZZ-CL-104
17 | MOORING ANALYSIS DURING INSTALLATIONS AT WHT-4 AND WHT-6 | 2207-ZZ-CL-103 | AD197-481/477-G-03917 | B | 2 | 2015-06-09 | 2015-05-26 | -27 | CSE-OF-2207-299 | 2020-05-20 | 2207-NPCC-AO-T-06469 | 2020-06-01 | TR-UFFDP1-13-09656 | 2020-06-14 | 2 | 2207-NPCC-MWS-T-01022 | 2020-05-28 | GM-60295-1174 | 2015-07-05 | B | Accepted subject to comments
|  |  |  | C | 1 |  |  |  | CSE-OF-2207-300 | 2020-07-08 | 2207-NPCC-AO-T-06550 | 2020-07-14 | TR-UFFDP1-13-09876 | 2020-07-27 | 2 | 2207-NPCC-MWS-T-01037 | 2020-07-09 | GM-60295-1194 | 2020-07-21 | A
18 | MOORING ANALYSIS DURING OLD BOAT LANDING REMOVAL AT WHT-6 | 2207-ZZ-CL-104 | AD197-481-G-03918 | B | 2 |  | 2015-05-19 |  | CSE-OF-2207-301 | 2020-07-28 | 2207-NPCC-AO-T-06605 | 2020-07-29 | TR-UFFDP1-13-09937 | 2020-08-09 | 2 | 2207-NPCC-MWS-T-01048 | 2020-07-29
19 | MOORING ANALYSIS DURING OLD BOAT LANDING REMOVAL AT WHT-4 | 2207-ZZ-CL-105 | AD197-477-G-03919 | B | 2 |  |  |  | CSE-OF-2207-302 | 2020-07-28 | 2207-NPCC-AO-T-06608 | 2020-07-29 | TR-UFFDP1-13-09936 | 2020-08-09 | 2 | 2207-NPCC-MWS-T-01049 | 2020-07-29
20 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP | 2207-ZZ-CL-106 | AD197-482/573-G-03920 | Merged into2207-ZZ-CL-101 | 2 | 2015-06-01 | 2015-05-05 | 0
21 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 | 2207-ZZ-CL-107 | AD197-573/481-G-03921 | Not Issued | 2 | 2015-06-21 | 2015-04-14 | -1886
22 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP | 2207-ZZ-CL-108 | AD197-481/573-G-03922 | Not Issued | 2 | 2015-06-25 | 2015-04-07 | -1882
23 | MOORING ANALYSIS DURING INSTALLATION OF 20” MOL P/L FROM K.P.0 TO K.P. 60 | 2207-ZZ-CL-109 | AD197-602-G-03923 | B | 2 | - | 2015-03-24 | -51 | CSE-OF-2207-221 | 2015-09-09 | 2207-NPCC-AO-T-03452 | 2015-09-12 | TR-UFFDP1-13-06197 | 2015-09-16 | 1 | 2207-NPCC-MWS-T-00628 | 2015-09-09 | GM-60295-0799 GM-60295-0800 | 2015-09-10 | A | New Document added on 07-09-15 -
24 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 & 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 | 2207-ZZ-CL-110 | AD197-481/477-G-03924 | B | 2 | 2015-03-17 | 2015-03-17 | -58 | CSE-OF-2207-118 | 2015-05-14 | 2207-NPCC-AO-T-02676 | 2015-05-17 | TR-UFFDP1-13-05560 | 2015-06-04 | 1 | 2207-NPCC-MWS-T-00492 | 2015-05-19 | GM-60295-0673 | 2015-05-25 | A | -
25 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 | 2207-ZZ-CL-111 | AD197-477/481-G-03925 | Not Issued | 2 | 2015-06-29 | 2015-03-10 | -1878
26 | MOORING ANALYSIS DURING STARTUP, PIPELAYING & LAYDOWN FOR 20" MAIN OIL LINE FROM ULRP TO KP 89.256 | 2207-ZZ-CL-112 | AD197-573/602-G-03926 | B | 2 | 2015-08-01 | 2015-04-15 | -9 | CSE-OF-2207-165 | 2015-08-10 | 2207-NPCC-AO-T-03154 | 2015-08-11 | TR-UFFDP1-13-05976 | 2015-08-16 | 2 | 2207-NPCC-MWS-T-00561 | 2015-08-11 | GM-60295-0739 GM-60295-0743 | 2015-08-16 | C | -
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-185 | 2015-08-19 | 2207-NPCC-AO-T-03248 | 2015-08-19 | TR-UFFDP1-13-06389 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00588 | 2015-08-20 | GM-60295-0746 | 2015-08-20 | B | -
|  |  |  | 1 | - | - |  | - | CSE-OF-2207-211 | 2015-08-31 | 2207-NPCC-AO-T-03368 | 2015-09-03 | TR-UFFDP1-13-06135 | 2015-09-09 | 4 | 2207-NPCC-MWS-T-00617 | 2015-09-06 | GM-60295-0794 | 2015-09-07 | B | -
27 | MOORING ANALYSIS DURING RISER INSTALLATION AT ULRP (SET-UP#1) | 2207-ZZ-CL-014 | AD162-573-G-03927 |  | 2 | 2014-09-06 |  | -2174
28 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-1 (SET-UP#1) | 2207-ZZ-CL-015 | AD162-474-G-03928 |  | 2 | 2014-10-21 |  | -2129
29 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-2 (SET-UP#1) | 2207-ZZ-CL-016 | AD162-475-G-03929 |  | 2 | 2014-08-26 |  | -2185
30 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-3 (SET-UP#1) | 2207-ZZ-CL-017 | AD162-476-G-03930 | B | 2 | 2014-09-26 |  | -2 | CSE-OF-2207-079 | 2014-09-28 | 2207-NPCC-AO-T-01572 | 2014-09-29 | TR-UFFDP1-13-04397 | 2014-12-07 | Information | 2207-NPCC-MWS-T-00379 | 2014-10-01 | GM-60295-0504 | 2014-10-02 | ACCEPTED | -
31 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-4 (SET-UP#1) | 2207-ZZ-CL-018 | AD197-477-G-03931 | Not Issued | 2 | 2015-09-03 | 2015-04-01 | -1812
32 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-5 (SET-UP#1) | 2207-ZZ-CL-019 | AD162-480-G-03932 |  | 2 | 2014-08-04 | 2014-08-04 | -2207
33 | MOORING ANALYSIS DURING RISER INSTALLATION OF 6", 8", 10", 18" AT WHT-6 (WEST FACE) | 2207-ZZ-CL-020 | AD197-481-G-03933 | B | 2 | 2015-08-30 | 2015-04-08 |  | CSE-OF-2207-284 | 2016-09-28 | 2207-NPCC-AO-T-05372 | 2016-10-03 | TR-UFFDP1-13-07897 | 2016-10-06 | 1 | 2207-NPCC-MWS-T-00860 | 2016-10-03 | GM-60295-1033 |  | B | GM-60295-1039-ACCEPTED FROM GMC
34 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-7 (SET-UP#1) | 2207-ZZ-CL-021 | AD197-482-G-03934 | B | 2 | 2015-07-25 | 2015-04-15 | -24 | CSE-OF-2207-185 | 2015-08-19 | 2207-NPCC-AO-T-03248 | 2015-08-19 | TR-UFFDP1-13-06389 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00588 | 2015-08-20 | GM-60295-0883 | 2015-11-25 | A | -
35 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-8 (SET-UP#1) | 2207-ZZ-CL-022 | AD197-483-G-03935 | B | 2 | 2015-08-07 | 2015-04-22 | -6 | CSE-OF-2207-175 | 2015-08-13 | 2207-NPCC-AO-T-03213 | 2015-08-16 | TR-UFFDP1-13-05991 | 2015-08-18 | 1 | 2207-NPCC-MWS-T-00570 | 2015-08-16 | GM-60295-0884 | 2015-11-25 | A | -
36 | MOORING ANALYSIS DURING RISER INSTALLATION AT ULRP (SET-UP#2) | 2207-ZZ-CL-113 | AD162-573-G-03936 |  | 2 | 2014-09-06 | 2014-09-06 | -2174
37 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-1 (SET-UP#2) | 2207-ZZ-CL-114 | AD162-474-G-03937 |  | 2 | 2014-10-21 | 2014-10-21 | -2129
38 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-2 (SET-UP#2) | 2207-ZZ-CL-115 | AD162-475-G-03938 |  | 2 | 2014-08-26 | 2014-08-26 | -2185
39 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-3 (SET-UP#2) | 2207-ZZ-CL-116 | AD197-476-G-03939 |  | 2 | 2014-09-26 | 2014-09-26 | -2154
40 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-4 (SET-UP#2) | 2207-ZZ-CL-117 | AD162-477-G-03940 | Not Issued | 2 | 2015-09-07 | 2015-04-29 | -1808
41 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-5 (SET-UP#2) | 2207-ZZ-CL-118 | AD197-480-G-03941 | Not Issued | 2 | 2014-08-04 | 2014-08-04 | -2207
42 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-6 (EAST FACE) (SET-UP#2) | 2207-ZZ-CL-119 | AD197-481-G-03942 | B | 2 | 2015-09-11 | 2015-05-06 | -152 | CSE-OF-2207-270 | 2016-02-10 | 2207-NPCC-AO-T-04350 | 2016-02-14 | TR-UFFDP1-13-07169 | 2016-03-15 | 2 | 2207-NPCC-MWS-T-00763 | 2016-02-16 | GM-60295-0950 | 2016-02-22 | A | -
|  |  |  | C | 2 |  |  |  | CSE-OF-2207-293 | 2016-11-14 | 2207-NPCC-AO-T-05580 | 2016-11-15 | TR-UFFDP1-13-08161 | 2016-12-27 | 1 | 2207-NPCC-MWS-T-00903 | 2016-11-15 | GM/60295/1063 | 2016-11-14 | A
43 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-7 (SET-UP#2) | 2207-ZZ-CL-120 | AD197-482-G-03943 | Not Issued | 2 | 2015-07-29 | 2015-05-13 | -1848
44 | MOORING ANALYSIS DURING RISER INSTALLATION AT WHT-8 (SET-UP#2) | 2207-ZZ-CL-121 | AD197-483-G-03944 | Not Issued | 2 | 2015-08-14 | 2015-05-20 | -1832
45 | MOORING ANALYSIS DURING MID LINE TIE-IN AT KP34.83 | 2207-ZZ-CL-122 | AD197-602-G-03945 | Not Issued | 2 | 2015-09-14 | 2015-10-01 | -1801
46 | MOORING ANALYSIS DURING INSTALLATION OF WHT-2 JACKET | 2207-ZZ-CL-023 | AD162-475-G-03946 | Not Issued | 2 | 2014-06-08 |  |  | CSE-OF-2207-003 | 2014-05-21 | 2207-NPCC-AO-T-01008 | 2014-05-26 | TR-UFFDP1-13-03221 | 2014-06-26 | Accepted | 2207-NPCC-MWS-T-00123 | 2014-05-27 | E/60295/152 | 2014-05-29 | ACCEPTED WITH COMMENTS | Rev C accepted by client
|  |  |  | Not Issued |  |  |  |  | CSE-OF-2207-005 | 2014-06-01 | 2207-NPCC-AO-T-01056 | 2014-06-02 | TR-UFFDP1-13-02987 | 2014-06-05 | Accepted | 2207-NPCC-MWS-T-00143 | 2014-06-04 | E/60295/160 | 2014-06-03 | ACCEPTED
47 | MOORING ANALYSIS DURING INSTALLATION OF WHT-5 JACKET | 2207-ZZ-CL-024 | AD162-480-G-03947 | Not Issued | 2 | 2014-06-21
48 | MOORING ANALYSIS DURING INSTALLATION OF WHT-3, WHT-1 & ULRP JACKET | 2207-ZZ-CL-025 | AD162-573-G-03948 | Not Issued | 2 | 2014-07-05 |  |  | CSE-OF-2207-025 | 2014-07-17 | 2207-NPCC-AO-T-01249 | 2014-07-20 | TR-UFFDP1-13-03449 | 2014-07-22 | Accepted | 2207-NPCC-MWS-T-00237 | 2014-07-21 | GM/60295/0327 | 2014-07-23 | ACCEPTED | -
49 | MOORING ANALYSIS DURING INSTALLATION OF WHT-3 JACKET | 2207-ZZ-CL-026 | AD162-476-G-03949 | Not Issued | 2 | 2014-07-25
50 | MOORING ANALYSIS DURING INSTALLATION OF WHT-1 JACKET | 2207-ZZ-CL-027 | AD162-474-G-03950 | Not Issued | 2 | 2014-08-08
51 | MOORING ANALYSIS DURING INSTALLATION OF WHT-7 & WHT-8 JACKETS | 2207-ZZ-CL-028 | AD162-482-G-03951 | Not Issued | 2 | 2014-08-21 |  | -25 | CSE-OF-2207-059 | 2014-09-15 | 2207-NPCC-AO-T-01472 | 2014-09-18 | TR-UFFDP1-13-03888 | 2014-09-25 | Accepted | 2207-NPCC-MWS-T-00349 | 2014-09-21 | GM/60295/0453 | 2014-09-16 | ACCEPTED | -
52 | MOORING ANALYSIS DURING INSTALLATION OF WHT-8 JACKET | 2207-ZZ-CL-029 | AD162-483-G-03952 | Not Issued | 2 | 2014-09-05 |  | -10 | [12 empty] | -
53 | MOORING ANALYSIS DURING LIFTING & INSTALLATION OF WHT-1 & WHT-3 TOPSIDES | 2207-ZZ-CL-123 | AD197-474-G-03953 | B | 2 | 2015-05-27 | 2015-05-27 | -259 | CSE-OF-2207-258 | 2015-01-04 | 2207-NPCC-AO-T-04168 | 2016-01-04 | TR-UFFDP1-13-07199 | 2016-03-21 | 4 | 2207-NPCC-MWS-T-00733 | 2016-01-05 | GM-60295-0953 | 2016-02-23 | C | CLIENT
|  |  |  | CRS MWS | - | - |  | - | [7 empty] | Email | 2016-02-28 | GM-60295-0958 | 2016-02-28 | A | -
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-278 | 2016-05-25 | 2207-NPCC-AO-T-04823 | 2016-05-26 | TR-UFFDP1-13-07492 | 2016-05-29 | 1 | 2207-NPCC-MWS-T-00810 | 2016-05-28
|  |  |  | 1 | 1 |  |  |  | CSE-OF-2207-279 | 2016-07-20 | 2207-NPCC-AO-T-05082 | 2016-07-21 | TR-UFFDP1-13-08162 | 2016-12-27 | 1
54 | MOORING ANALYSIS DURING LIFTING & INSTALLATION OF WHT-3 TOPSIDES | 2207-ZZ-CL-124 | AD197-476-G-03954 | Not Issued | 2 | 2015-06-03 | 2015-06-03 | -1904
55 | MOORING ANALYSIS DURING LIFTING & INSTALLATION OF WHT-2 TOPSIDES | 2207-ZZ-CL-125 | AD197-475-G-03955 | B | 2 | 2015-06-10 | 2015-06-10 | -1897 | CSE-OF-2207-289 | 2016-10-20 | 2207-NPCC-AO-T-05482 | 2016-10-25 | TR-UFFDP1-13-07974 | 2016-10-27 | 1 | 2207-NPCC-MWS-T-00884 | 2016-10-24 | GM/60295/1046 | 2016-10-24 | C
|  |  |  | C | 1 |  |  |  | CSE-OF-2207-291 | 2016-10-26 | 2207-NPCC-AO-T-05499 | 2016-10-30 | TR-UFFDP1-13-08163 | 2016-12-27 | 1 | 2207-NPCC-MWS-T-00891 | 2016-10-29 | GM/60295/1056 | 2016-11-06 | A
56 | MOORING ANALYSIS DURING LIFTING & INSTALLATION OF WHT-5 TOPSIDES | 2207-ZZ-CL-126 | AD197-480-G-03956 | B | 2 | 2015-06-17 | 2015-06-17 | -1890 | CSE-OF-2207-290 | 2016-10-24 | 2207-NPCC-AO-T-05487 | 2016-10-26 | TR-UFFDP1-13-08164 | 2016-12-27 | 1 | 2207-NPCC-MWS-T-00887 | 2016-10-25 | GM/60295/1050 | 2016-10-30 | A
57 | MOORING ANALYSIS DURING LIFTING & INSTALLATION OF WHT-8 TOPSIDES | 2207-ZZ-CL-127 | AD197-483-G-03957 | B | 2 | 2015-06-24 | 2015-06-24 | -1883 | CSE-OF-2207-295 | 2017-06-08 | 2207-NPCC-AO-T-05977 | 2017-06-12 |  |  |  | 2207-NPCC-MWS-T-00958 | 2017-06-13
|  |  |  | C | 2 |  |  |  | CSE-OF-2207-296 | 2017-06-22 | 2207-NPCC-AO-T-05997 | 2017-06-29 | TR-UFFDP1-13-08525 | 2017-07-02 | 2 | 2207-NPCC-MWS-T-00963 | 2017-06-24 | GM/60295/1124 | 2017-07-02 | A
58 | MOORING ANALYSIS DURING LIFTING & INSTALLATION OF WHT-7 TOPSIDES | 2207-ZZ-CL-128 | AD197-482-G-03958 | B | 2 | 2015-07-01 | 2015-07-01 | -1876 | CSE-OF-2207-294 | 2017-06-05 | 2207-NPCC-AO-T-05972 | 2017-06-06 | TR-UFFDP1-13-08842 | 2018-01-30 | 1 | 2207-NPCC-MWS-T-00952 | 2017-06-13
|  |  |  | B | 2 | 2014-06-04 |  |  | CSE-OF-2207-295 | 2014-06-04 | 2207-NPCC-AO-T-01070 | 2014-06-05 | TR-UFFDP1-13-03222 | 2014-06-26 | Accepted | 2207-NPCC-MWS-T-00155 | 2014-05-10 | GM/60295/0254 | 2014-06-16 | ACCEPTED WITH COMMENTS
|  |  |  | C | 2 | - |  |  | CSE-OF-2207-296 | 2014-06-18 | 2207-NPCC-AO-T-01148 | 2014-06-22 | TR-UFFDP1-13-03541 | 2014-08-10 | Accepted | 2207-NPCC-MWS-T-00191 | 2014-06-24 | GM-60295-0279 | 2014-06-29 | ACCEPTED | Client
|  |  |  | B | 2 | 2014-06-07 |  |  | CSE-OF-2207-297 | 2014-06-12 | 2207-NPCC-AO-T-01112 | 2014-06-12 | TR-UFFDP1-13-03223 | 2014-06-26 | Accepted | 2207-NPCC-MWS-T-00170 | 2014-06-16 | GM-60295-0280 | 2014-06-29 | ACCEPTED
|  |  |  | B | 2 | 2014-06-14 |  | reused | CSE-OF-2207-298 | 2014-09-23 | 2207-NPCC-AO-T-01537 | 2014-09-25 | TR-UFFDP1-13-03950 | 2014-10-01 | Accepted | 2207-NPCC-MWS-T-00373 | 2014-09-27 | GM-60295-0471 | 2014-09-24 | ACCEPTED | -
[5 empty] | 2 | 2014-06-20 |  | -2252 | CSE-OF-2207-299
[5 empty] | 2 | 2014-06-27 |  | -2245 | CSE-OF-2207-300
[5 empty] | 2 | 2014-07-05 |  | -2237 | CSE-OF-2207-301
[5 empty] | 2 | 2014-07-12 |  | Cancelled | CSE-OF-2207-302 | [11 empty] | Cancelled
[5 empty] | 2 | 2014-07-20 |  | Cancelled | CSE-OF-2207-303 | [11 empty] | Cancelled
[5 empty] | 2 | 2014-07-28 |  | Cancelled | CSE-OF-2207-304 | [11 empty] | Cancelled
|  |  |  | C | 2 |  |  |  | CSE-OF-2207-297 | 2017-06-29 | 2207-NPCC-AO-T-06004 | 2017-07-02 | TR-UFFDP1-13-08529 | 2017-07-05 | 2
1 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-1 (Campaign-2) | 2207-ZZ-CL-129 | AD197-473-G-03968 | B | 2 | 2015-06-10 | 2015-04-01 | -7 | CSE-OF-2207-130 | 2015-06-17 | 2207-NPCC-AO-T-02905 | 2015-06-21 | TR-UFFDP1-13-05711 | 2015-06-24 | 2 | 2207-NPCC-MWS-T-00510 | 2015-06-22 | GM-60295-0683 | 2015-06-21 | A | -
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-140 | 2015-06-30 | 2207-NPCC-AO-T-02982 | 2015-07-01 | TR-UFFDP1-13-05815 | 2015-07-07 | 1 | 2207-NPCC-MWS-T-00519 | 2015-07-02 | GM-60295-0858 | 2015-11-24 | A | -
2 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-2 (Campaign-2) | 2207-ZZ-CL-130 | AD197-473-G-03969 | B | 2 | 2015-06-14 | 2015-04-08 | -11 | CSE-OF-2207-134 | 2015-06-25 | 2207-NPCC-AO-T-02949 | 2015-06-30 | TR-UFFDP1-13-05814 | 2015-07-07 | 2 | 2207-NPCC-MWS-T-00515 | 2015-07-01 | GM-60295-0692 | 2015-06-30 | A | -
|  |  |  | 0 |  |  |  |  | CSE-OF-2207-248 | 2015-11-25 | 2207-NPCC-AO-T-04001 | 2015-11-26 | TR-UFFDP1-13-06669 | 2015-11-29 | 1 | 2207-NPCC-MWS-T-00714 | 2015-11-28 | GM-60295-0907 | 2015-12-13 | A | -
3 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-6 (Campaign-2) | 2207-ZZ-CL-131 | AD197-473-G-03970 | B | 2 | - | - | - | CSE-OF-2207-171 | 2015-08-13 | 2207-NPCC-AO-T-03207 | 2015-08-15 | TR-UFFDP1-13-05995 TR-UFFDP1-13-06021 | 2015-08-18 | 3 | 2207-NPCC-MWS-T-00569 | 2015-08-16 | GM-60295-0740 | 2015-08-17 | A | -
|  |  |  | C | - | - |  | - | CSE-OF-2207-189 | 2015-08-23 | 2207-NPCC-AO-T-03267 | 2015-08-24 | TR-UFFDP1-13-06043 | 2015-08-27 | 1 | 2207-NPCC-MWS-T-00595 | 2015-08-24 | GM-60295-0859 | 2015-11-24 | A | -
4 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-4 (Campaign-2) | 2207-ZZ-CL-132 | AD197-473-G-03971 | Not Issued | 2 | 2015-04-22 | 2015-04-22 | -1946
5 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-5 (Campaign-2) | 2207-ZZ-CL-133 | AD197-473-G-03972 | Not Issued | 2 | 2015-04-29 | 2015-04-29 | -1939
6 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-6 (Campaign-2) | 2207-ZZ-CL-134 | AD197-473-G-03973 | Not Issued | 2 | 2015-05-06 | 2015-05-06 | -1932
7 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-7 (Campaign-2) | 2207-ZZ-CL-135 | AD197-473-G-03974 | B | 2 | 2015-05-13 | 2015-05-13 | -105 | CSE-OF-2207-196 | 2015-08-26 | 2207-NPCC-AO-T-03311 | 2015-08-27 | TR-UFFDP1-13-06062 | 2015-08-31 | 1 | 2207-NPCC-MWS-T-00604 | 2015-08-27 | GM-60295-0752 | 2015-08-27 | A | -
8 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-8 (Campaign-2) | 2207-ZZ-CL-136 | AD197-473-G-03975 | B | 2 | 2015-05-20 | 2015-05-20 | -99 | CSE-OF-2207-209 | 2015-08-31 | 2207-NPCC-AO-T-03365 | 2015-09-02 | TR-UFFDP1-13-06133 | 2015-09-09 | 1 | 2207-NPCC-MWS-T-00614 | 2015-09-02 | GM-60295-0860 | 2015-11-24 | A | -
9 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-9 (Campaign-2) | 2207-ZZ-CL-137 | AD197-473-G-03976 | B | 2 | 2015-05-27 | 2015-05-27 | -105 | CSE-OF-2207-223 | 2015-09-09 | 2207-NPCC-AO-T-03454 | 2015-09-10 | TR-UFFDP1-13-06389 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00633 | 2015-09-10 | GM-60295-0861 | 2015-11-24 | A | -
10 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-10 (Campaign-2) | 2207-ZZ-CL-138 | AD197-473-G-03977 | Not Issued | 2 | 2015-06-03 | 2015-06-03 | -1904
11 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-11 (Campaign-2) | 2207-ZZ-CL-139 | AD197-473-G-03978 | Not Issued | 2 | 2015-06-10 | 2015-06-10 | -1897
12 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-12 (Campaign-2) | 2207-ZZ-CL-140 | AD197-473-G-03979 | Not Issued | 2 | 2015-06-17 | 2015-06-17 | -1890
13 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-13 (Campaign-2) | 2207-ZZ-CL-141 | AD197-473-G-03980 | Not Issued | 2 | 2015-06-24 | 2015-06-24 | -1883
14 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-14 (Campaign-2) | 2207-ZZ-CL-142 | AD197-473-G-03981 | Not Issued | 2 | 2015-07-01 | 2015-07-01 | -1876
15 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-15 (Campaign-2) | 2207-ZZ-CL-143 | AD197-473-G-03982 | Not Issued | 2 | 2015-07-08 | 2015-07-08 | -1869
16 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-16 (Campaign-2) | 2207-ZZ-CL-144 | AD197-473-G-03983 | Not Issued | 2 | 2015-07-15 | 2015-07-15 | -1862
17 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-17 (Campaign-2) | 2207-ZZ-CL-145 | AD197-473-G-03984 | Not Issued | 2 | 2015-07-22 | 2015-07-22 | -1855
18 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-18 (Campaign-2) | 2207-ZZ-CL-146 | AD197-473-G-03985 | Not Issued | 2 | 2015-07-29 | 2015-07-29 | -1848
19 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-19 (Campaign-2) | 2207-ZZ-CL-147 | AD197-473-G-03986 | Not Issued | 2 | 2015-08-05 | 2015-08-05 | -1841
20 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-20 (Campaign-2) | 2207-ZZ-CL-148 | AD197-473-G-03987 | Not Issued | 2 | 2015-08-12 | 2015-08-12 | -1834
21 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-21 (Campaign-2) | 2207-ZZ-CL-149 | AD197-473-G-03988 | Not Issued | 2 | 2015-08-19 | 2015-08-19 | -1827
22 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-22 (Campaign-2) | 2207-ZZ-CL-150 | AD197-473-G-03989 | Not Issued | 2 | 2015-08-26 | 2015-08-26 | -1820
23 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-23 (Campaign-2) | 2207-ZZ-CL-151 | AD197-473-G-03990 | Not Issued | 2 | 2015-09-02 | 2015-09-02 | -1813
24 | STABILITY ANALYSIS DURING TRANSPORTATION OF RISERS AND SPOOLS (TRIP-1) (Campaign-1) | 2207-ZZ-CL-039 | AD162-562-G-03991 | Not Issued | 2 | 2015-09-09 | 2015-09-09 | -1806
25 | STABILITY ANALYSIS DURING TRANSPORTATION OF RISERS AND SPOOLS (TRIP-2) (Campaign-1) | 2207-ZZ-CL-040 | AD162-562-G-03992 | Not Issued | 2 | 2015-09-16 | 2015-09-16 | -1799
26 | STABILITY ANALYSIS DURING TRANSPORTATION OF RISERS AND SPOOLS (TRIP-1) (Campaign-2) | 2207-ZZ-CL-152 | AD197-473-G-03993 | Not Issued | 2 | 2015-07-30 | 2015-09-09 | -1847
27 | STABILITY ANALYSIS DURING TRANSPORTATION OF RISERS AND SPOOLS (TRIP-2) (Campaign-2) | 2207-ZZ-CL-153 | AD197-473-G-03994 | Not Issued | 2 | 2015-08-03 | 2015-09-16 | -1843
28 | STABILITY ANALYSIS DURING TRANSPORTATION OF CABLE DRUMS (TRIP-1) (Campaign-2) | 2207-ZZ-CL-154 | AD197-473-G-03995 | Not Issued | 2 | 2015-09-23 | 2015-09-23 | -1792
29 | TOWAGE ANALYSIS DURING TRANSPORTATION OF CC PIPES (TRIP-1) | 2207-ZZ-CL-154 | AD162-562-G-03996 |  | 2 | 2014-07-07 |  |  | CSE-OF-2207-018 | 2014-07-07 | 2207-NPCC-AO-T-01209 | 2014-07-08 | TR-UFFDP1-13-03540 | 2014-08-07 | Accepted | 2207-NPCC-MWS-T-00214 | 2014-07-09 | GM/60295/0300 | 2014-07-13 | ACCEPTED | -
30 | TOWAGE ANALYSIS DURING TRANSPORTATION OF CC PIPES (TRIP-2) | 2207-ZZ-CL-155 | AD162-562-G-03997 |  | 2 | 2014-07-07 |  |  | CSE-OF-2207-018 | 2014-07-07 | 2207-NPCC-AO-T-01209 | 2014-07-08 | TR-UFFDP1-13-03540 | 2014-08-07 | Accepted | 2207-NPCC-MWS-T-00214 | 2014-07-09 | GM/60295/0300 | 2014-07-13 | ACCEPTED | -
31 | STABILITY ANALYSIS DURING TRANSPORTATION OF CABLE BASKET (CAMPAIGN-2) | 2207-ZZ-CL-156 | AD197-473-G-03998 | B | 2 | - |  | - | CSE-OF-2207-104 | 2014-12-25 | 2207-NPCC-AO-T-01996 | 2015-01-07 | TR-UFFDP1-13-04722 | 2015-01-22 | 2 | 2207-NPCC-MWS-T-00449 | 2014-01-08 | GM-60295-0611 | 2015-01-11 | A | -
|  |  |  | 0 | - | - |  |  | CSE-OF-2207-248 | 2015-11-25 | 2207-NPCC-AO-T-04001 | 2015-11-26 | TR-UFFDP1-13-06669 | 2015-11-29 | 1 | 2207-NPCC-MWS-T-00714 | 2015-11-28 | GM-60295-0908 | 2015-12-13 | A | -
99 | MOORING ANALYSIS DURING RISER INSTALLATION AT ULRP (EAST & WEST FACE) | 2207-ZZ-CL-157 | AD197-573-G-03999 | B | - | - |  | - | CSE-OF-2207-199 | 2015-08-27 | 2207-NPCC-AO-T-03322 | 2015-09-01 | TR-UFFDP1-13-06130 | 2015-09-09 | 1 | 2207-NPCC-MWS-T-00606 | 2015-09-02 | GM-60295-0885 | 2015-11-25 | A | -
Formulas:
REMAINING DAYS = [SUBMISSION PLAN]-TODAY()

## Drawings
|  | ABU DHABI MARINE OPERATING COMPANY (ADMA-OPCO) | [15 empty] | NPCC DOC. No.: |  | 2207-NN-RP-060
|  | UMM LULU PACKAGE-1 FFD PROJECT | [15 empty] | ADMA DOC. No. : |  | AD162-562-G-06318
|  | NPCC PROJECT NO. 2207 | [15 empty] | REVISION : |  | B
|  | OFFSHORE CONSTRUCTION ENGINEERING DRAWINGS | [15 empty] | DATE : |  | 2014-03-25
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | OLD DATES | REMAINING DAYS |  |  | NPCC |  | ADMA-OPCO |  |  | GMC |  |  |  |  | REMARKS |  |  | NPCC |  | ADMA-OPCO |  |  | GMC |  |  |  |  | REMARKS
[9 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS | [5 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[9 empty] | CSE TO PMT |  | PMT TO ADMA-OPCO |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC |  |  |  | CSE TO PMT |  | PMT TO ADMA-OPCO |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[9 empty] | REF | DATE | REF | DATE | REF | DATE | CODE | REF | DATE | REF | DATE | CODE |  | REF | DATE | REF | DATE | REF | DATE | CODE | REF | DATE | REF | DATE | CODE
1 | BUCKLE DETECTOR DETAILS FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 | 2207-NN-0001 | AD162-573/480-PL-62000 | A | 3 | 2014-06-06 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0203 | 2014-06-05 | ACCEPTED
2 | START UP HEAD DETAILS FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 | 2207-NN-0002 | AD162-573/480-PL-62001 | A | 3 | 2014-06-06 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0187 | 2014-06-05 | ACCEPTED
3 | EMERGENCY LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 | 2207-NN-0003 | AD162-573/480-PL-62002 | Cancelled | 3 | 2014-06-06 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
4 | LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 | 2207-NN-0004 | AD162-573/480-PL-62003 | A | 3 | 2014-06-06 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0216 | 2014-06-05 | ACCEPTED
5 | X-RAY STOPPER DETAILS FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 | 2207-NN-0005 | AD162-573/480-PL-62004 | Cancelled | 3 | 2014-06-06 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
6 | BUCKLE DETECTOR DETAILS FOR 16" WELL FLUID P/L FROM WHT-5 TO WHT-2 | 2207-NN-0006 | AD162-480/475-PL-62005 | A | 3 | 2014-05-06 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0204 | 2014-06-05 | ACCEPTED
7 | START UP HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-5 TO WHT-2 | 2207-NN-0007 | AD162-480/475-PL-62006 | A | 3 | 2014-05-06 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0188 | 2014-06-05 | ACCEPTED
8 | EMERGENCY LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-5 TO WHT-2 | 2207-NN-0008 | AD162-480/475-PL-62007 | Cancelled | 3 | 2014-05-06 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
9 | LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-5 TO WHT-2 | 2207-NN-0009 | AD162-480/475-PL-62008 | A | 3 | 2014-05-06 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0217 | 2014-06-05 | ACCEPTED
10 | X-RAY STOPPER DETAILS FOR 16" WELL FLUID P/L FROM WHT-5 TO WHT-2 | 2207-NN-0010 | AD162-480/475-PL-62009 | Cancelled | 3 | 2014-05-06 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
11 | BUCKLE DETECTOR DETAILS FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP | 2207-NN-0011 | AD162-476/573-PL-62010 | A | 3 | 2014-06-11 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0205 | 2014-06-05 | ACCEPTED
12 | START UP HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP | 2207-NN-0012 | AD162-476/573-PL-62011 | A | 3 | 2014-06-11 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0189 | 2014-06-05 | ACCEPTED
13 | EMERGENCY LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP | 2207-NN-0013 | AD162-476/573-PL-62012 | Cancelled | 3 | 2014-06-11 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
14 | LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP | 2207-NN-0014 | AD162-476/573-PL-62013 | A | 3 | 2014-06-11 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0218 | 2014-06-05 | ACCEPTED
15 | X-RAY STOPPER DETAILS FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP | 2207-NN-0015 | AD162-476/573-PL-62014 | Cancelled | 3 | 2014-06-11 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
16 | BUCKLE DETECTOR DETAILS FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 | 2207-NN-0016 | AD162-474/476-PL-62015 | A | 3 | 2014-04-17 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0193 | 2014-06-05 | ACCEPTED
17 | START UP HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 | 2207-NN-0017 | AD162-474/476-PL-62016 | A | 3 | 2014-04-17 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0190 | 2014-06-05 | ACCEPTED
18 | EMERGENCY LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 | 2207-NN-0018 | AD162-474/476-PL-62017 | Cancelled | 3 | 2014-04-17 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
19 | LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 | 2207-NN-0019 | AD162-474/476-PL-62018 | A | 3 | 2014-04-17 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0206 | 2014-06-05 | ACCEPTED
20 | X-RAY STOPPER DETAILS FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 | 2207-NN-0020 | AD162-474/476-PL-62019 | Cancelled | 3 | 2014-04-17 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
21 | BUCKLE DETECTOR DETAILS FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 | 2207-NN-0021 | AD162-474/476-PL-62020 | A | 3 | 2014-04-23 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0194 | 2014-06-05 | ACCEPTED
22 | START UP HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 | 2207-NN-0022 | AD162-474/476-PL-62021 | A | 3 | 2014-04-23 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0178 | 2014-06-05 | ACCEPTED
23 | EMERGENCY LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 | 2207-NN-0023 | AD162-474/476-PL-62022 | Cancelled | 3 | 2014-04-23 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
24 | LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 | 2207-NN-0024 | AD162-474/476-PL-62023 | A | 3 | 2014-04-23 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0207 | 2014-06-05 | ACCEPTED
25 | X-RAY STOPPER DETAILS FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 | 2207-NN-0025 | AD162-474/476-PL-62024 | Cancelled | 3 | 2014-04-23 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
26 | BUCKLE DETECTOR DETAILS FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 | 2207-NN-0026 | AD162-474/476-PL-62025 | A | 3 | 2014-04-29 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0195 | 2014-06-05 | ACCEPTED
27 | START UP HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 | 2207-NN-0027 | AD162-474/476-PL-62026 | A | 3 | 2014-04-29 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0179 | 2014-06-05 | ACCEPTED
28 | EMERGENCY LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 | 2207-NN-0028 | AD162-474/476-PL-62027 | Cancelled | 3 | 2014-04-29 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
29 | LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 | 2207-NN-0029 | AD162-474/476-PL-62028 | A | 3 | 2014-04-29 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0208 | 2014-06-05 | ACCEPTED
30 | X-RAY STOPPER DETAILS FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 | 2207-NN-0030 | AD162-474/476-PL-62029 | Cancelled | 3 | 2014-04-29 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
31 | BUCKLE DETECTOR DETAILS FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0031 | AD162-476/573-PL-62030 | A | 3 | 2014-07-01 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0196 | 2014-06-05 | ACCEPTED
32 | START UP HEAD DETAILS FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0032 | AD162-476/573-PL-62031 | A | 3 | 2014-07-01 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0180 | 2014-06-05 | ACCEPTED
33 | EMERGENCY LAYDOWN HEAD DETAILS FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0033 | AD162-476/573-PL-62032 | Cancelled | 3 | 2014-07-01 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
34 | LAYDOWN HEAD DETAILS FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0034 | AD162-476/573-PL-62033 | A | 3 | 2014-07-01 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0209 | 2014-06-05 | ACCEPTED
35 | X-RAY STOPPER DETAILS FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0035 | AD162-476/573-PL-62034 | Cancelled | 3 | 2014-07-01 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
36 | BUCKLE DETECTOR DETAILS FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0036 | AD162-476/573-PL-62035 | A | 3 | 2014-06-17 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0197 | 2014-06-05 | ACCEPTED
37 | START UP HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0037 | AD162-476/573-PL-62036 | A | 3 | 2014-06-17 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0181 | 2014-06-05 | ACCEPTED
38 | EMERGENCY LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0038 | AD162-476/573-PL-62037 | Cancelled | 3 | 2014-06-17 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
39 | LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0039 | AD162-476/573-PL-62038 | A | 3 | 2014-06-17 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0210 | 2014-06-05 | ACCEPTED
40 | X-RAY STOPPER DETAILS FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0040 | AD162-476/573-PL-62039 | Cancelled | 3 | 2014-06-17 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
41 | BUCKLE DETECTOR DETAILS FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP | 2207-NN-0041 | AD162-476/573-PL-62040 | A | 3 | 2014-06-24 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0198 | 2014-06-05 | ACCEPTED
42 | START UP HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP | 2207-NN-0042 | AD162-476/573-PL-62041 | A | 3 | 2014-06-24 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0182 | 2014-06-05 | ACCEPTED
43 | EMERGENCY LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP | 2207-NN-0043 | AD162-476/573-PL-62042 | Cancelled | 3 | 2014-06-24 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
44 | LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP | 2207-NN-0044 | AD162-476/573-PL-62043 | A | 3 | 2014-06-24 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0211 | 2014-06-05 | ACCEPTED
45 | X-RAY STOPPER DETAILS FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP | 2207-NN-0045 | AD162-476/573-PL-62044 | Cancelled | 3 | 2014-06-24 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
46 | BUCKLE DETECTOR DETAILS FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 | 2207-NN-0046 | AD162-573/480-PL-62045 | A | 3 | 2014-06-01 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0199 | 2014-06-05 | ACCEPTED
47 | START UP HEAD DETAILS FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 | 2207-NN-0047 | AD162-573/480-PL-62046 | A | 3 | 2014-06-01 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM60295/0183 | 2014-06-05 | ACCEPTED
48 | EMERGENCY LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 | 2207-NN-0048 | AD162-573/480-PL-62047 | Cancelled | 3 | 2014-06-01 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
49 | LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 | 2207-NN-0049 | AD162-573/480-PL-62048 | A | 3 | 2014-06-01 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0212 | 2014-06-05 | ACCEPTED
50 | X-RAY STOPPER DETAILS FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 | 2207-NN-0050 | AD162-573/480-PL-62049 | Cancelled | 3 | 2014-06-01 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
51 | BUCKLE DETECTOR DETAILS FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5 | 2207-NN-0051 | AD162-573/480-PL-62050 | A | 3 | 2014-05-27 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0200 | 2014-06-05 | ACCEPTED
52 | START UP HEAD DETAILS FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5 | 2207-NN-0052 | AD162-573/480-PL-62051 | A | 3 | 2014-05-27 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0184 | 2014-06-05 | ACCEPTED
53 | EMERGENCY LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5 | 2207-NN-0053 | AD162-573/480-PL-62052 | Cancelled | 3 | 2014-05-27 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
54 | LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5 | 2207-NN-0054 | AD162-573/480-PL-62053 | A | 3 | 2014-05-27 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0213 | 2014-06-05 | ACCEPTED
55 | X-RAY STOPPER DETAILS FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5 | 2207-NN-0055 | AD162-573/480-PL-62054 | Cancelled | 3 | 2014-05-27 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
56 | BUCKLE DETECTOR DETAILS FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 | 2207-NN-0056 | AD162-480/475-PL-62055 | A | 3 | 2014-05-12 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0201 | 2014-06-05 | ACCEPTED
57 | START UP HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 | 2207-NN-0057 | AD162-480/475-PL-62056 | A | 3 | 2014-05-12 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0185 | 2014-06-05 | ACCEPTED
58 | EMERGENCY LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 | 2207-NN-0058 | AD162-480/475-PL-62057 | Cancelled | 3 | 2014-05-12 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
59 | LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 | 2207-NN-0059 | AD162-480/475-PL-62058 | A | 3 | 2014-05-12 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0214 | 2014-06-05 | ACCEPTED
60 | X-RAY STOPPER DETAILS FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 | 2207-NN-0060 | AD162-480/475-PL-62059 | Cancelled | 3 | 2014-05-12 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
61 | BUCKLE DETECTOR DETAILS FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 | 2207-NN-0061 | AD162-480/475-PL-62060 | A | 3 | 2014-05-19 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0202 | 2014-06-05 | ACCEPTED
62 | START UP HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 | 2207-NN-0062 | AD162-480/475-PL-62061 | A | 3 | 2014-05-19 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0186 | 2014-06-05 | ACCEPTED
63 | EMERGENCY LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 | 2207-NN-0063 | AD162-480/475-PL-62062 | Cancelled | 3 | 2014-05-19 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
64 | LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 | 2207-NN-0064 | AD162-480/475-PL-62063 | A | 3 | 2014-05-19 |  |  | Sent by DC through Del boy | 2014-04-01 | 2207-NPCC-AO-T-00797 | 2014-04-09 |  |  |  | 2207-NPCC-MWS-T-00076 | 2014-04-13 | GM/60295/0215 | 2014-06-05 | ACCEPTED
65 | X-RAY STOPPER DETAILS FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 | 2207-NN-0065 | AD162-480/475-PL-62064 | Cancelled | 3 | 2014-05-19 |  |  | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled
66 | BUCKLE DETECTOR DETAILS FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP | 2207-NN-1000 | AD197-481/477-PL-62065 |  | 3 | 2015-03-17 |  | -1982
67 | START UP HEAD DETAILS FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP | 2207-NN-1001 | AD197-481/477-PL-62066 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
68 |  |  |  |  | 3 | 2015-03-17 |  | -1982
|  |  |  | B | - | - |  | - | CSE-OF-2207-128 | 2015-06-14 | 2207-NPCC-AO-T-02869 | 2015-06-16 | TR-UFFDP1-13-05718 | 2015-06-28 | 2 | 2207-NPCC-MWS-T-00507 | 2015-06-18 |  |  |  | MWS For Info only
|  |  |  | C | - | - |  | - | CSE-OF-2207-150 | 2015-07-12 | 2207-NPCC-AO-T-03037 | 2015-07-14 | TR-UFFDP1-13-05860 | 2015-07-22 | I | 2207-NPCC-MWS-T-00533 | 2015-07-14 |  |  | Approved in previous Rev | MWS For Info only
69 | LAYDOWN HEAD DETAILS FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP | 2207-NN-1003 | AD197-481/477-PL-62068 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
70 | X-RAY STOPPER DETAILS FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP | 2207-NN-1004 | AD197-481/477-PL-62069 |  | 3 | 2015-03-17 |  | -1982
71 | BUCKLE DETECTOR DETAILS FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 | 2207-NN-1005 | AD197-573/482-PL-62070 |  | 3 | 2015-03-17 |  | -1982
72 | START UP HEAD DETAILS FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 | 2207-NN-1006 | AD197-573/482-PL-62071 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
73 | EMERGENCY LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 | 2207-NN-1007 | AD197-573/482-PL-62072 |  | 3 | 2015-03-17 |  | -1982 | [11 empty] | A
74 | LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 | 2207-NN-1008 | AD197-573/482-PL-62073 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
75 | X-RAY STOPPER DETAILS FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 | 2207-NN-1009 | AD197-573/482-PL-62074 |  | 3 | 2015-03-17 |  | -1982
76 | BUCKLE DETECTOR DETAILS FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 | 2207-NN-1010 | AD197-482/483-PL-62075 |  | 3 | 2015-03-17 |  | -1982
77 | START UP HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 | 2207-NN-1011 | AD197-482/483-PL-62076 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
78 | EMERGENCY LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 | 2207-NN-1012 | AD197-482/483-PL-62077 |  | 3 | 2015-03-17 |  | -1982 | [11 empty] | A
79 | LAYDOWN HEAD DETAILS FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 | 2207-NN-1013 | AD197-482/483-PL-62078 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
80 | X-RAY STOPPER DETAILS FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 | 2207-NN-1014 | AD197-482/483-PL-62079 |  | 3 | 2015-03-17 |  | -1982
81 | BUCKLE DETECTOR DETAILS FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 | 2207-NN-1015 | AD197-483/482-PL-62080 |  | 3 | 2015-03-17 |  | -1982
82 | START UP HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 | 2207-NN-1016 | AD197-483/482-PL-62081 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
83 | EMERGENCY LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 | 2207-NN-1017 | AD197-483/482-PL-62082 |  | 3 | 2015-03-17 |  | -1982 | [11 empty] | A
84 | LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 | 2207-NN-1018 | AD197-483/482-PL-62083 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
85 | X-RAY STOPPER DETAILS FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 | 2207-NN-1019 | AD197-483/482-PL-62084 |  | 3 | 2015-03-17 |  | -1982
86 | BUCKLE DETECTOR DETAILS FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 | 2207-NN-1020 | AD197-482/483-PL-62085 |  | 3 | 2015-03-17 |  | -1982
87 | START UP HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 | 2207-NN-1021 | AD197-482/483-PL-62086 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
88 | EMERGENCY LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 | 2207-NN-1022 | AD197-482/483-PL-62087 |  | 3 | 2015-03-17 |  | -1982 | [11 empty] | A
89 | LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 | 2207-NN-1023 | AD197-482/483-PL-62088 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
90 | X-RAY STOPPER DETAILS FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 | 2207-NN-1024 | AD197-482/483-PL-62089 |  | 3 | 2015-03-17 |  | -1982
91 | BUCKLE DETECTOR DETAILS FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 | 2207-NN-1025 | AD197-573/482-PL-62090 |  | 3 | 2015-03-17 |  | -1982
92 | START UP HEAD DETAILS FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 | 2207-NN-1026 | AD197-573/482-PL-62091 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
93 | EMERGENCY LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 | 2207-NN-1027 | AD197-573/482-PL-62092 |  | 3 | 2015-03-17 |  | -1982 | [11 empty] | A
94 | LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 | 2207-NN-1028 | AD197-573/482-PL-62093 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
95 | X-RAY STOPPER DETAILS FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 | 2207-NN-1029 | AD197-573/482-PL-62094 |  | 3 | 2015-03-17 |  | -1982
96 | BUCKLE DETECTOR DETAILS FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP | 2207-NN-1030 | AD197-482/573-PL-62095 |  | 3 | 2015-03-17 |  | -1982
97 | START UP HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP | 2207-NN-1031 | AD197-482/573-PL-62096 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
98 | EMERGENCY LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP | 2207-NN-1032 | AD197-482/573-PL-62097 |  | 3 | 2015-03-17 |  | -1982 | [11 empty] | A
99 | LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP | 2207-NN-1033 | AD197-482/573-PL-62098 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
100 | X-RAY STOPPER DETAILS FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP | 2207-NN-1034 | AD197-482/573-PL-62099 |  | 3 | 2015-03-17 |  | -1982
101 | BUCKLE DETECTOR DETAILS FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 | 2207-NN-1035 | AD197-573/481-PL-62100 |  | 3 | 2015-03-17 |  | -1982
102 | START UP HEAD DETAILS FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 | 2207-NN-1036 | AD197-573/481-PL-62101 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
103 |  |  |  |  | 3 | 2015-03-17 |  | -1982
|  |  |  | B | - | - |  | - | CSE-OF-2207-128 | 2015-06-14 | 2207-NPCC-AO-T-02869 | 2015-06-16 | TR-UFFDP1-13-05718 | 2015-06-28 |  | 2207-NPCC-MWS-T-00507 | 2015-06-18 |  |  |  | -
|  |  |  | C | - | - |  | - | CSE-OF-2207-150 | 2015-07-12 | 2207-NPCC-AO-T-03037 | 2015-07-14 | TR-UFFDP1-13-05860 | 2015-07-22 | I | 2207-NPCC-MWS-T-00533 | 2015-07-14 |  |  | - | MWS For Info only
104 | LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 | 2207-NN-1038 | AD197-573/481-PL-62103 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
105 | X-RAY STOPPER DETAILS FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 | 2207-NN-1039 | AD197-573/481-PL-62104 |  | 3 | 2015-03-17 |  | -1982
106 | BUCKLE DETECTOR DETAILS FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP | 2207-NN-1040 | AD197-481/573-PL-62105 |  | 3 | 2015-03-17 |  | -1982
107 | START UP HEAD DETAILS FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP | 2207-NN-1041 | AD197-481/573-PL-62106 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
108 | EMERGENCY LAYDOWN HEAD DETAILS FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP | 2207-NN-1042 | AD197-481/573-PL-62107 |  | 3 | 2015-03-17 |  | -1982
|  |  |  | B | - | - |  | - | CSE-OF-2207-128 | 2015-06-14 | 2207-NPCC-AO-T-02869 | 2015-06-16 | TR-UFFDP1-13-05718 | 2015-06-28 |  | 2207-NPCC-MWS-T-00507 | 2015-06-18 |  |  |  | -
|  |  |  | C | - | - |  | - | CSE-OF-2207-150 | 2015-07-12 | 2207-NPCC-AO-T-03037 | 2015-07-14 | TR-UFFDP1-13-05860 | 2015-07-22 | I | 2207-NPCC-MWS-T-00533 | 2015-07-14 |  |  | - | MWS For Info only
109 | LAYDOWN HEAD DETAILS FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP | 2207-NN-1043 | AD197-481/573-PL-62108 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
110 | X-RAY STOPPER DETAILS FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP | 2207-NN-1044 | AD197-481/573-PL-62109 |  | 3 | 2015-03-17 |  | -1982
111 | BUCKLE DETECTOR DETAILS FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP | 2207-NN-1045 | AD197-481/573-PL-62110 |  | 3 | 2015-03-17 |  | -1982
112 | START UP HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP | 2207-NN-1046 | AD197-481/573-PL-62111 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
113 | EMERGENCY LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP | 2207-NN-1047 | AD197-481/573-PL-62112 |  | 3 | 2015-03-17 |  | -1982
|  |  |  | B | - | - |  | - | CSE-OF-2207-128 | 2015-06-14 | 2207-NPCC-AO-T-02869 | 2015-06-16 | TR-UFFDP1-13-05718 | 2015-06-28 |  | 2207-NPCC-MWS-T-00507 | 2015-06-18 |  |  |  | MWS
|  |  |  | C | - | - |  | - | CSE-OF-2207-150 | 2015-07-12 | 2207-NPCC-AO-T-03037 | 2015-07-14 | TR-UFFDP1-13-05860 | 2015-07-22 | I | 2207-NPCC-MWS-T-00533 | 2015-07-14 |  |  | - | MWS For Info only
114 | LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP | 2207-NN-1048 | AD197-481/573-PL-62113 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
115 | X-RAY STOPPER DETAILS FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP | 2207-NN-1049 | AD197-481/573-PL-62114 |  | 3 | 2015-03-17 |  | -1982
116 | BUCKLE DETECTOR DETAILS FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 | 2207-NN-1050 | AD197-481/477-PL-62115 |  | 3 | 2015-03-17 |  | -1982
117 | START UP HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 | 2207-NN-1051 | AD197-481/477-PL-62116 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
118 | EMERGENCY LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 | 2207-NN-1052 | AD197-481/477-PL-62117 |  | 3 | 2015-03-17 |  | -1982
119 | LAYDOWN HEAD DETAILS FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 | 2207-NN-1053 | AD197-481/477-PL-62118 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
120 | X-RAY STOPPER DETAILS FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 | 2207-NN-1054 | AD197-481/477-PL-62119 |  | 3 | 2015-03-17 |  | -1982
121 | BUCKLE DETECTOR DETAILS FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 | 2207-NN-1055 | AD197-477/481-PL-62120 |  | 3 | 2015-03-17 |  | -1982
122 | START UP HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 | 2207-NN-1056 | AD197-477/481-PL-62121 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0648 | 2015-04-07 | A | -
123 | EMERGENCY LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 | 2207-NN-1057 | AD197-477/481-PL-62122 |  | 3 | 2015-03-17 |  | -1982
124 | LAYDOWN HEAD DETAILS FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 | 2207-NN-1058 | AD197-477/481-PL-62123 | A | 3 | 2015-03-17 |  | -7 | CSE-OF-2207-110 | 2015-03-24 | 2207-NPCC-AO-T-02405 | 2015-03-29 | TR-UFFDP1-13-05247 | 2015-04-13 | 1 | 2207-NPCC-MWS-T-00474 | 2015-04-01 | GM-60295-0649 | 2015-04-07 | A | -
125 | X-RAY STOPPER DETAILS FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 | 2207-NN-1059 | AD197-477/481-PL-62124 |  | 3 | 2015-03-17 |  | -1982
126 | BUCKLE DETECTOR DETAILS FOR 20" MAIN OIL LINE FROM ULRP TO KP 34.38 | 2207-NN-1060 | AD197-573/602-PL-62125 | A | 3 | 2015-06-25 | 2015-03-17 | -100 | CSE-OF-2207-135 | 2015-06-25 | 2207-NPCC-AO-T-02950 | 2015-06-30 | TR-UFFDP1-13-05849 | 2015-07-14 | 2,I | 2207-NPCC-MWS-T-00516 | 2015-07-01 |  |  |  | MWS For Info only
127 | START UP HEAD DETAILS FOR 20" MAIN OIL LINE FROM ULRP TO KP 34.38 | 2207-NN-1061 | AD197-573/602-PL-62126 | A | 3 | 2015-06-25 | 2015-03-17 | -100 | CSE-OF-2207-135 | 2015-06-25 | 2207-NPCC-AO-T-02950 | 2015-06-30 | TR-UFFDP1-13-05849 | 2015-07-14 | 2,I | 2207-NPCC-MWS-T-00516 | 2015-07-01 |  |  |  | MWS For Info only
128 | EMERGENCY LAYDOWN HEAD DETAILS FOR 20" MAIN OIL LINE FROM ULRP TO KP 34.38 | 2207-NN-1062 | AD197-573/602-PL-62127 |  | 3 | 2015-03-17 | 2015-03-17 | -100 | [12 empty] | MWS For Info only
129 | LAYDOWN HEAD DETAILS FOR 20" MAIN OIL LINE FROM ULRP TO KP 34.38 | 2207-NN-1063 | AD197-573/602-PL-62128 | A | 3 | 2015-06-25 | 2015-03-17 | -100 | CSE-OF-2207-135 | 2015-06-25 | 2207-NPCC-AO-T-02950 | 2015-06-30 | TR-UFFDP1-13-05849 | 2015-07-14 | 2,I | 2207-NPCC-MWS-T-00516 | 2015-07-01 |  |  |  | MWS For Info only
130 | X-RAY STOPPER DETAILS FOR 20" MAIN OIL LINE FROM ULRP TO KP 34.38 | 2207-NN-1064 | AD197-573/602-PL-62129 |  | 3 | 2015-03-17 |  | -1982
131 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ AWALCO-I (TRIP-1) (Campaign-1) WITH BALLAST PLAN | 2207-NN-0066 | AD162-562-PL-62130 | A | 3 | 2014-06-04 |  |  | CSE-OF-2207-008 | 2014-06-04 | 2207-NPCC-AO-T-01075 | 2014-06-05 | TR-UFFDP1-13-03257 | 2014-07-02 | ACCEPTED | 2207-NPCC-MWS-T-00156 | 2014-06-10 | GM/60295/0254 | 2014-06-16 | ACCEPTED
|  |  |  | B | 3 |  |  |  | CSE-OF-2207-017 | 2014-07-03 | 2207-NPCC-AO-T-01200 | 2014-07-06 |  |  |  | 2207-NPCC-MWS-T-00207 | 2014-07-07 | GM-60295-0292 | 2014-07-09 | ACCEPTED | Client
|  |  |  | C | 3 |  |  |  | CSE-OF-2207-022 | 2014-07-13 | 2207-NPCC-AO-T-01226 | 2014-07-15 | TR-UFFDP1-13-03408 | 2014-07-17 | ACCEPTED | 2207-NPCC-MWS-T-00222 | 2014-07-16 | GM/60295/0313 | 2014-07-17 | ACCEPTED | Resent on 14-07-14
132 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ GOGAS-252 (TRIP-2) (Campaign-1) | 2207-NN-0067 | AD162-562-PL-62131 | A | 3 | 2014-06-07 |  |  | CSE-OF-2207-013 | 2014-06-15 | 2207-NPCC-AO-T-01122 | 2014-06-17 | TR-UFFDP1-13-03258 | 2014-07-02 | ACCEPTED | 2207-NPCC-MWS-T-00182 | 2014-06-18 | GM/60295/0341 | 2014-07-30 | ACCEPTED
|  |  |  | B | 3 |  |  |  | CSE-OF-2207-021 | 2014-07-10 | 2207-NPCC-AO-T-01222 | 2014-07-20 | TR-UFFDP1-13-03450 | 2014-07-22 | ACCEPTED | 2207-NPCC-MWS-T-00236 | 2014-07-21 | - | - | - | MWS Resent on 14-07-14
|  |  |  | C | 3 |  |  |  | CSE-OF-2207-026 | 2014-07-20 | 2207-NPCC-AO-T-01232 | 2014-07-21 | TR-UFFDP1-13-03455 | 2014-07-24 | ACCEPTED | 2207-NPCC-MWS-T-00236 | 2014-07-21 | GM/60295/0341 | 2014-07-30 | ACCEPTED
133 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ AWALCO-I (TRIP-3) (Campaign-1) | 2207-NN-0068 | AD162-562-PL-62132 | A | 3 | 2014-06-14 |  |  | CSE-OF-2207-021 | 2014-07-10 | 2207-NPCC-AO-T-01222 | 2014-07-20 | TR-UFFDP1-13-03450 | 2014-07-22 | ACCEPTED | [5 empty] | Client/MWS Resent on 14-07-14
|  |  |  | B | 3 |  |  |  | CSE-OF-2207-026 | 2014-07-20 | 2207-NPCC-AO-T-01232 | 2014-07-21 | TR-UFFDP1-13-03455 | 2014-07-24 | ACCEPTED | 2207-NPCC-MWS-T-00236 | 2014-07-21 | GM/60295/0366 GM/60295/0377 CRS | 2014-08-14 | B (Accepted with comments) | -
134 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-4) (Campaign-1) | 2207-NN-0069 | AD162-562-PL-62133 | A | 3 | 2014-06-20 |  |  | CSE-OF-2207-030 | 2014-07-24 | 2207-NPCC-AO-T-01281 | 2014-07-27 | TR-UFFDP1-13-03493 | 2014-08-04 | ACCEPTED | 2207-NPCC-MWS-T-00261 | 2014-07-31 | GM/60295/0353 | 2014-08-12 | ACCEPTED | -
135 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-5) (Campaign-1) | 2207-NN-0070 | AD162-562-PL-62134 | A | 3 | 2014-06-27 |  |  | CSE-OF-2207-030 | 2014-07-24 | 2207-NPCC-AO-T-01281 | 2014-07-27 | TR-UFFDP1-13-03493 | 2014-08-04 | ACCEPTED | 2207-NPCC-MWS-T-00261 | 2014-07-31 | GM/60295/0354 | 2014-08-12 | ACCEPTED | -
136 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-6) (Campaign-1) | 2207-NN-0071 | AD162-562-PL-62135 | A | 3 | 2014-07-05 |  |  | CSE-OF-2207-030 | 2014-07-24 | 2207-NPCC-AO-T-01281 | 2014-07-27 | TR-UFFDP1-13-03493 | 2014-08-04 | ACCEPTED | 2207-NPCC-MWS-T-00261 | 2014-07-31 | GM/60295/0355 | 2014-08-12 | ACCEPTED | -
|  |  |  | B | - | - |  | - | CSE-OF-2207-062 | 2014-09-16 | 2207-NPCC-AO-T-01487 | 2014-09-18 | TR-UFFDP1-13-03890 | 2014-09-23 | ACCEPTED | 2207-NPCC-MWS-T-00352 | 2014-09-22 | GM-60295-0471 | 2014-09-24 | ACCEPTED | -
137 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-7) (Campaign-1) | 2207-NN-0072 | AD162-562-PL-62136 |  | 3 | 2014-07-12 |  | Cancelled | [12 empty] | Cancelled
138 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-8) (Campaign-1) | 2207-NN-0073 | AD162-562-PL-62137 |  | 3 | 2014-07-20 |  | Cancelled | [12 empty] | Cancelled
139 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-9) (Campaign-1) | 2207-NN-0074 | AD162-562-PL-62138 |  | 3 | 2014-07-28 |  | Cancelled | [12 empty] | Cancelled
140 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-1) (Campaign-2) | 2207-NN-1065 | AD197-473-PL-62139 | A | 3 | 2015-06-10 | 2015-04-01 | -8 | CSE-OF-2207-131 | 2015-06-18 | 2207-NPCC-AO-T-02910 | 2015-06-21 | TR-UFFDP1-13-05712 | 2015-06-25 | 2 | 2207-NPCC-MWS-T-00509 | 2015-06-21 | GM-60295-0682 | 2015-06-21 | A | -
|  |  |  | CRS | - | - | - | - | CSE-OF-2207-250 | 2015-12-07 | 2207-NPCC-AO-T-04025 | 2015-12-09 | TR-UFFDP1-13-06800 | 2016-01-03 | 1 | 2207-NPCC-MWS-T-00724 | 2015-12-17 |  |  |  | -
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-149 | 2015-07-12 | 2207-NPCC-AO-T-03033 | 2015-07-13 | TR-UFFDP1-13-05872 | 2015-07-22 | 1 | 2207-NPCC-MWS-T-00532 | 2015-07-14 | GM-60295-0858 | 2015-11-24 | A | -
141 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-2) (Campaign-2) | 2207-NN-1066 | AD197-473-PL-62140 | A | 3 | 2015-06-14 | 2015-04-08 | -11 | CSE-OF-2207-135 | 2015-06-25 | 2207-NPCC-AO-T-02950 | 2015-06-30 | TR-UFFDP1-13-05849 | 2015-07-14 | 2 | 2207-NPCC-MWS-T-00516 | 2015-07-01 | GM-60295-0694 | 2015-07-01 | A | -
|  |  |  | CRS |  |  |  |  | CSE-OF-2207-251 | 2015-12-13 | 2207-NPCC-AO-T-04064 | 2015-12-14 | TR-UFFDP1-13-06941 | 2016-02-01 | 1 | 2207-NPCC-MWS-T-00718 | 2015-12-15 |  |  |  | -
142 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-3) (Campaign-2) | 2207-NN-1067 | AD197-473-PL-62141 | A | 3 | 2015-06-17 | 2015-04-15 | -25 | CSE-OF-2207-149 | 2015-07-12 | 2207-NPCC-AO-T-03033 | 2015-07-13 | TR-UFFDP1-13-05871 | 2015-07-22 | 2 | 2207-NPCC-MWS-T-00532 | 2015-07-14 |  |  |  | MWS
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-155 | 2015-07-22 | 2207-NPCC-AO-T-03076 | 2015-07-23 | TR-UFFDP1-13-05900 | 2015-07-28 | 1 | 2207-NPCC-MWS-T-00540 | 2015-07-23 | GM-60295-0718 | 2015-07-26 | A | -
143 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-4) (Campaign-2) | 2207-NN-1068 | AD197-473-PL-62142 | A | 3 | 2015-06-20 | 2015-04-22 | -22 | CSE-OF-2207-149 | 2015-07-12 | 2207-NPCC-AO-T-03033 | 2015-07-13 | TR-UFFDP1-13-05871 | 2015-07-22 | 2 | 2207-NPCC-MWS-T-00532 | 2015-07-14 |  |  |  | MWS
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-156 | 2015-07-22 | 2207-NPCC-AO-T-03077 | 2015-07-23 | TR-UFFDP1-13-05901 | 2015-07-28 | 1 | 2207-NPCC-MWS-T-00541 | 2015-07-23 | GM-60295-0725 | 2015-08-04 | A | -
144 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-1) (Campaign-2) | 2207-NN-1069 | AD197-473-PL-62143 | A | 3 | 2015-06-23 | 2015-04-29 | -48 | CSE-OF-2207-166 | 2015-08-10 | 2207-NPCC-AO-T-03156 | 2015-08-11 | TR-UFFDP1-13-05974 | 2015-08-16 | 1 | 2207-NPCC-MWS-T-00563 | 2015-08-11 | GM-60295-0891 | 2015-11-29 | A | -
145 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-6) (Campaign-2) | 2207-NN-1070 | AD197-473-PL-62144 | A | 3 | 2015-06-26 | 2015-05-06 | -52 | CSE-OF-2207-182 | 2015-08-17 | 2207-NPCC-AO-T-03241 | 2015-08-18 | TR-UFFDP1-13-06020 | 2015-08-23 | 3 | 2207-NPCC-MWS-T-00581 | 2015-08-18 | GM-60295-0859 | 2015-11-24 | A | -
|  |  |  | 0 |  |  |  | - | CSE-OF-2207-253 | 2015-12-13 | 2207-NPCC-AO-T-04060 | 2015-12-14 | TR-UFFDP1-13-06781 | 2015-12-29 | 1 | 2207-NPCC-MWS-T-00717 | 2015-12-15 | GM-60295-0919 | 2015-12-29 | A | -
146 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-7) (Campaign-2) | 2207-NN-1071 | AD197-473-PL-62145 | A | 3 | 2015-06-29 | 2015-05-13 | -55 | CSE-OF-2207-190 | 2015-08-23 | 2207-NPCC-AO-T-03274 | 2015-08-24 | TR-UFFDP1-13-06049 | 2015-08-27 | 2 | 2207-NPCC-MWS-T-00593 | 2015-08-23 | GM-60295-0873 | 2015-11-25 | A | -
|  |  |  | CRS |  |  |  |  | CSE-OF-2207-251 | 2015-12-13 | 2207-NPCC-AO-T-04064 | 2015-12-14 | TR-UFFDP1-13-06941 | 2016-02-01 | 1 | 2207-NPCC-MWS-T-00718 | 2015-12-15 |  |  |  | -
147 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-8) (Campaign-2) | 2207-NN-1072 | AD197-473-PL-62146 | A | 3 | 2015-07-02 | 2015-05-20 | -56 | CSE-OF-2207-208 | 2015-08-31 | 2207-NPCC-AO-T-03362 | 2015-09-02 | TR-UFFDP1-13-06134 | 2015-09-09 | 1 | 2207-NPCC-MWS-T-00613 | 2015-09-02 | GM-60295-0860 | 2015-11-24 | A | -
148 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-9) (Campaign-2) | 2207-NN-1073 | AD197-473-PL-62147 | A | 3 | 2015-07-05 | 2015-05-27 | -64 | CSE-OF-2207-218 | 2015-09-07 | 2207-NPCC-AO-T-03428 | 2015-09-09 | TR-UFFDP1-13-06400 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00626 | 2015-09-08 | GM-60295-0796 | 2015-09-09 | A | -
149 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-10) (Campaign-2) | 2207-NN-1074 | AD197-473-PL-62148 | A | 3 | 2015-07-08 | 2015-06-03 | -63 | CSE-OF-2207-222 | 2015-09-09 | 2207-NPCC-AO-T-03453 | 2015-09-10 | TR-UFFDP1-13-06400 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00632 | 2015-09-10 | GM-60295-0801 | 2015-09-13 | A | -
150 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES @ GAC-67 (TRIP-11) | 2207-NN-1075 | AD197-473-PL-62149 | A | 3 | 2015-07-11 | 2015-06-10 | -65 | CSE-OF-2207-226 | 2015-09-13 | 2207-NPCC-AO-T-03498 | 2015-09-14 | TR-UFFDP1-13-06400 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00638 | 2015-09-15 | GM-60295-0874 | 2015-11-25 | A | -
151 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ GAC-66 (TRIP-12) | 2207-NN-1076 | AD197-473-PL-62150 | A | 3 | 2015-07-14 | 2015-06-17 | -62 | CSE-OF-2207-226 | 2015-09-13 | 2207-NPCC-AO-T-03498 | 2015-09-14 | TR-UFFDP1-13-06400 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00638 | 2015-09-15 | GM-60295-0814 | 2015-09-20 | A | -
152 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-13) (Campaign-2) | 2207-NN-1077 | AD197-473-PL-62151 | A | 3 | 2015-07-17 | 2015-06-24 | -62 | CSE-OF-2207-232 | 2015-09-17 | 2207-NPCC-AO-T-03545 | 2015-09-20 | TR-UFFDP1-13-06270 | 2015-09-27 | 1 | 2207-NPCC-MWS-T-00647 | 2015-09-21 | GM-60295-0875 | 2015-11-25 | A | -
153 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-14) (Campaign-2) | 2207-NN-1078 | AD197-473-PL-62152 | A | 3 | 2015-07-20 | 2015-07-01 | -90 | CSE-OF-2207-233 | 2015-09-20 | 2207-NPCC-AO-T-03551 | 2015-09-22 | TR-UFFDP1-13-06400 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00651 | 2015-09-22 | GM-60295-0876 | 2015-11-25 | A | -
154 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-15) (Campaign-2) | 2207-NN-1079 | AD197-473-PL-62153 |  | 3 | 2015-07-23 | 2015-07-08 | -1854
155 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-16) (Campaign-2) | 2207-NN-1080 | AD197-473-PL-62154 |  | 3 | 2015-07-26 | 2015-07-15 | -1851
156 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-17) (Campaign-2) | 2207-NN-1081 | AD197-473-PL-62155 |  | 3 | 2015-07-29 | 2015-07-22 | -1848
157 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-18) (Campaign-2) | 2207-NN-1082 | AD197-473-PL-62156 |  | 3 | 2015-08-01 | 2015-07-29 | -1845
158 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-19) (Campaign-2) | 2207-NN-1083 | AD197-473-PL-62157 |  | 3 | 2015-08-04 | 2015-08-05 | -1842
159 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-20) (Campaign-2) | 2207-NN-1084 | AD197-473-PL-62158 |  | 3 | 2015-08-07 | 2015-08-12 | -1839
160 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-21) (Campaign-2) | 2207-NN-1085 | AD197-473-PL-62159 |  | 3 | 2015-08-10 | 2015-08-19 | -1836
161 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-22) (Campaign-2) | 2207-NN-1086 | AD197-473-PL-62160 |  | 3 | 2015-08-13 | 2015-08-26 | -1833
162 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-23) (Campaign-2) | 2207-NN-1087 | AD197-473-PL-62161 |  | 3 | 2015-08-16 | 2015-09-02 | -1830
163 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-1) (Campaign-1) | 2207-NN-0075 | AD162-562-PL-62162 | A | 3 | 2015-09-09 | 2015-09-09 | -27 | CSE-OF-2207-073 | 2014-09-22 | 2207-NPCC-AO-T-01517 | 2014-09-30 | TR-UFFDP1-13-03966 | 2014-10-06 | ACCEPTED | 2207-NPCC-MWS-T-00384 | 2014-10-02 | GM-60295-0479 | 2014-09-25 | ACCEPTED | -
164 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-2) (Campaign-1) | 2207-NN-0076 | AD162-562-PL-62163 | A | 3 | 2015-09-16 | 2015-09-16 | -19 | V | - | 2207-NPCC-AO-T-01635 | 2014-10-13 | TR-UFFDP1-13-04038 | 2014-10-21 | ACCEPTED | 2207-NPCC-MWS-T-00398 | 2014-10-13 | GM-60295-0515 | 2014-10-12 | ACCEPTED | -
165 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-1) (Campaign-2) | 2207-NN-1088 | AD197-473-PL-62164 | A | 3 | 2015-07-30 | 2015-09-09 | -11 | CSE-OF-2207-164 | 2015-08-10 | 2207-NPCC-AO-T-03153 | 2015-08-11 | TR-UFFDP1-13-05975 | 2015-08-16 | 1 | 2207-NPCC-MWS-T-00562 | 2015-08-11 | GM-60295-0731 | 2015-08-13 | A | -
166 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-2) (Campaign-2) | 2207-NN-1089 | AD197-473-PL-62165 | A | 3 | 2015-08-03 | 2015-09-16 | -31 | CSE-OF-2207-217 | 2015-09-03 | 2207-NPCC-AO-T-03409 | 2015-09-06 | TR-UFFDP1-13-06148 | 2015-09-09 | 1 | 2207-NPCC-MWS-T-00625 | 2015-09-07 | GM-60295-0877 | 2015-11-25 | A | -
167 | LOADING ARRANGEMENT AND SEAFASTENING OF CABLE DRUM (TRIP-1) (Campaign-2) | 2207-NN-1090 | AD197-473-PL-62166 |  | 3 | 2015-09-23 | 2015-09-23 | -1792
168 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID RISER FROM ULRP TO WHT-5 | 2207-NN-0077 | AD162-573/480-PL-62167 | A | 3 | 2014-08-04 | 2014-08-04 | -51 | CSE-OF-2207-075 | 2014-09-24 | 2207-NPCC-AO-T-01542 | 2014-09-25 | TR-UFFDP1-13-04232 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00375 | 2014-09-27 | GM/60295/0494 | 2014-09-29 | ACCEPTED | -
169 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID RISER FROM WHT-5 TO WHT-2 | 2207-NN-0078 | AD162-480/475-PL-62168 | A | 3 | 2014-08-08 | 2014-08-08 | -52 | CSE-OF-2207-080 | 2014-09-29 | 2207-NPCC-AO-T-01578 | 2014-09-30 | TR-UFFDP1-13-03967 | 2014-10-06 | ACCEPTED | 2207-NPCC-MWS-T-00386 | 2014-10-02 | GM-60295-0532 | 2014-10-15 | ACCEPTED | -
170 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID RISER FROM WHT-3 TO ULRP | 2207-NN-0079 | AD162-476/573-PL-62169 | A | 3 | 2014-07-26 | 2014-07-26 |  | CSE-OF-2207-027 | 2014-07-21 | 2207-NPCC-AO-T-01272 | 2014-07-30 | TR-UFFDP1-13-03653 | 2014-08-20 | ACCEPTED | 2207-NPCC-MWS-T-00265 | 2014-08-03 | GM-60295-0423 | 2014-09-10 | ACCEPTED | -
|  |  |  | B | - |  |  |  | CSE-OF-2207-082 | 2014-09-30 | 2207-NPCC-AO-T-01598 | 2014-10-02 | TR-UFFDP1-13-04233 | 2014-11-17 | ACCEPTED | 2207-NPCC-MWS-T-00383 | 2014-10-02 | GM-60295-0532 | 2014-10-15 | ACCEPTED | -
171 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID RISER FROM WHT-1 TO WHT-3 | 2207-NN-0080 | AD162-474/476-PL-62170 | A | 3 | 2014-07-29 | 2014-07-29 | -49 | CSE-OF-2207-064 | 2014-09-17 | 2207-NPCC-AO-T-01492 | 2014-09-18 | TR-UFFDP1-13-03891 | 2014-09-23 | ACCEPTED | 2207-NPCC-MWS-T-00353 | 2014-09-22 | GM/60295/0494 | 2014-09-29 | ACCEPTED | -
172 | TEMPORARY KNEE BRACE DETAILS FOR 10" WATER INJECTION RISER FROM WHT-1 TO WHT-3 | 2207-NN-0081 | AD162-474/476-PL-62171 | A | 3 | 2014-08-01 | 2014-08-01 | -45 | CSE-OF-2207-060 | 2014-09-15 | 2207-NPCC-AO-T-01475 | 2014-09-18 | TR-UFFDP1-13-04233 | 2014-11-17 | ACCEPTED | 2207-NPCC-MWS-T-00348 | 2014-09-21 | GM/60295/0494 | 2014-09-29 | ACCEPTED | -
173 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS LIFT RISER FROM WHT-1 TO WHT-3 | 2207-NN-0082 | AD162-474/476-PL-62172 | A | 3 | 2014-08-04 | 2014-08-04 | -42 | CSE-OF-2207-059 | 2014-09-15 | 2207-NPCC-AO-T-01473 | 2014-09-18 | TR-UFFDP1-13-03892 | 2014-09-23 | ACCEPTED | 2207-NPCC-MWS-T-00347 | 2014-09-21 | GM/60295/0494 | 2014-09-29 | ACCEPTED | -
174 | TEMPORARY KNEE BRACE DETAILS FOR 8" GAS INJECTION RISER FROM WHT-3 TO ULRP | 2207-NN-0083 | AD162-476/573-PL-62173 | A | 3 | 2014-08-07 | 2014-08-07 | -39 | CSE-OF-2207-052 | 2014-09-11 | 2207-NPCC-AO-T-01452 | 2014-09-12 | TR-UFFDP1-13-04234 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00331 | 2014-09-16 | GM/60295/0494 | 2014-09-29 | ACCEPTED | -
175 | TEMPORARY KNEE BRACE DETAILS FOR 10" WATER INJECTION RISER FROM WHT-3 TO ULRP | 2207-NN-0084 | AD162-476/573-PL-62174 | A | 3 | 2014-08-10 | 2014-08-10 | -36 | CSE-OF-2207-047 | 2014-09-10 | 2207-NPCC-AO-T-01438 | 2014-09-11 | TR-UFFDP1-13-04235 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00320 | 2014-09-11 | GM/60295/0494 | 2014-09-29 | ACCEPTED | -
176 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS LIFT RISER FROM WHT-3 TO ULRP | 2207-NN-0085 | AD162-476/573-PL-62175 | A | 3 | 2014-08-13 | 2014-08-13 | -33 | CSE-OF-2207-056 | 2014-09-14 | 2207-NPCC-AO-T-01461 | 2014-09-16 | TR-UFFDP1-13-03859 | 2014-09-17 | Information | 2207-NPCC-MWS-T-00341 | 2014-09-18 | GM/60295/0481 | 2014-09-25 | ACCEPTED | -
|  |  |  | B | - | - | - | - | V | - | 2207-NPCC-AO-T-01633 | 2014-10-09 | TR-UFFDP1-13-04028 | 2014-10-16 | ACCEPTED | 2207-NPCC-MWS-T-00397 | 2014-10-11 | GM-60295-0539 | 2014-10-15 | ACCEPTED | -
177 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS LIFT RISER FROM ULRP TO WHT-5 | 2207-NN-0086 | AD162-573/480-PL-62176 | A | 3 | 2014-08-12 | 2014-08-12 | -43 | CSE-OF-2207-076 | 2014-09-24 | 2207-NPCC-AO-T-01552 | 2014-09-27 |  |  |  | 2207-NPCC-MWS-T-00378 | 2014-10-01 | GM-60295-0532 | 2014-10-15 | ACCEPTED | Client
178 | TEMPORARY KNEE BRACE DETAILS FOR 10" WATER INJECTION RISER FROM ULRP TO WHT-5 | 2207-NN-0087 | AD162-573/480-PL-62177 | A | 3 | 2014-08-16 | 2014-08-16 | -33 | CSE-OF-2207-067 | 2014-09-18 | 2207-NPCC-AO-T-01497 | 2014-09-18 | TR-UFFDP1-13-03889 | 2014-09-23 | ACCEPTED | 2207-NPCC-MWS-T-00353 | 2014-09-22 | GM/60295/0494 | 2014-09-29 | ACCEPTED | -
179 | TEMPORARY KNEE BRACE DETAILS FOR 10" WATER INJECTION RISER FROM WHT-5 TO WHT-2 | 2207-NN-0088 | AD162-480/475-PL-62178 | A | 3 | 2014-08-20 | 2014-08-20 | -41 | CSE-OF-2207-082 | 2014-09-30 | 2207-NPCC-AO-T-01598 | 2014-10-02 | TR-UFFDP1-13-04233 | 2014-11-17 | ACCEPTED | 2207-NPCC-MWS-T-00383 | 2014-10-02 | GM-60295-0532 | 2014-10-15 | ACCEPTED | -
180 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS LIFT RISER FROM WHT-5 TO WHT-2 | 2207-NN-0089 | AD162-480/475-PL-62179 | A | 3 | 2014-08-24 | 2014-08-24 | -36 | CSE-OF-2207-080 | 2014-09-29 | 2207-NPCC-AO-T-01578 | 2014-09-30 | TR-UFFDP1-13-03967 | 2014-10-06 | ACCEPTED | 2207-NPCC-MWS-T-00386 | 2014-10-02 | GM-60295-0532 | 2014-10-15 | ACCEPTED | -
181 | TEMPORARY KNEE BRACE DETAILS FOR 18" WELL FLUID RISER FROM WHT-6 TO ULRP | 2207-NN-1091 | AD197-481/477-PL-62180 | A | 3 | 2015-04-01 | 2015-04-01 | -152 | CSE-OF-2207-212 | 2015-08-31 | 2207-NPCC-AO-T-03369 | 2015-09-02 | TR-UFFDP1-13-06132 TR-UFFDP1-13-06195 | 09-09-15 16-09-15 | 1 | 2207-NPCC-MWS-T-00616 | 2015-09-02 | GM-60295-0756 | 2015-09-06 | A | -
182 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID RISER FROM ULRP TO WHT-7 | 2207-NN-1092 | AD197-573/482-PL-62181 | A | 3 | 2015-04-15 | 2015-04-15 | -5 | CSE-OF-2207-116 | 2015-04-20 | 2207-NPCC-AO-T-02547 | 2015-04-29 | TR-UFFDP1-13-05475 | 2015-05-17 | 2 | 2207-NPCC-MWS-T-00485 | 2015-05-13 | GM-60295-0666 | 2015-05-18 | A | -
|  |  |  | B | - |  |  |  | CSE-OF-2207-192 | 2015-08-25 | 2207-NPCC-AO-T-03299 | 2015-08-25 | TR-UFFDP1-13-06052 | 2015-08-27 | 1 | 2207-NPCC-MWS-T-00597 | 2015-08-26 | GM-60295-0757 | 2015-09-06 | A | -
183 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID RISER FROM WHT-7 TO WHT-8 | 2207-NN-1093 | AD197-482/483-PL-62182 | A | 3 | 2015-04-29 | 2015-04-29 | 14 | CSE-OF-2207-114 | 2015-04-15 | 2207-NPCC-AO-T-02530 | 2015-04-29 | TR-UFFDP1-13-05473 | 2015-05-18 | 1 | 2207-NPCC-MWS-T-00488 | 2015-05-13 | GM-60295-0667 | 2015-05-18 | A | -
184 | TEMPORARY KNEE BRACE DETAILS FOR 10" WATER INJECTION RISER FROM WHT-8 TO WHT-7 | 2207-NN-1094 | AD197-483/482-PL-62183 | A | 3 | 2015-05-13 | 2015-05-13 | -89 | CSE-OF-2207-167 | 2015-08-11 | 2207-NPCC-AO-T-03159 | 2015-08-12 | TR-UFFDP1-13-06000 | 2015-08-18 | 1 | 2207-NPCC-MWS-T-00565 | 2015-08-12 | GM-60295-0736 | 2015-08-16 | A | -
185 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS LIFT RISER FROM WHT-7 TO WHT-8 | 2207-NN-1095 | AD197-482/483-PL-62184 | A | 3 | 2015-05-27 | 2015-05-27 | 37 | CSE-OF-2207-116 | 2015-04-20 | 2207-NPCC-AO-T-02547 | 2015-04-29 | TR-UFFDP1-13-05475 | 2015-05-17 | 2 | 2207-NPCC-MWS-T-00485 | 2015-05-13 | GM-60295-0665 | 2015-05-18 | A | For Info only
186 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS LIFT RISER FROM ULRP TO WHT-7 | 2207-NN-1096 | AD197-573/482-PL-62185 | A | 3 | 2015-06-10 | 2015-06-10 | -68 | CSE-OF-2207-181 | 2015-08-17 | 2207-NPCC-AO-T-03240 | 2015-08-18 | TR-UFFDP1-13-06018 | 2015-08-23 | 1 | 2207-NPCC-MWS-T-00580 | 2015-08-18 | GM-60295-0780 | 2015-09-07 | A | -
187 | TEMPORARY KNEE BRACE DETAILS FOR 10" WATER INJECTION RISER FROM WHT-7 TO ULRP | 2207-NN-1097 | AD197-482/573-PL-62186 | A | 3 | 2015-06-24 | 2015-06-24 | -57 | CSE-OF-2207-188 | 2015-08-20 | 2207-NPCC-AO-T-03262 | 2015-08-23 | TR-UFFDP1-13-06035 | 2015-08-26 | 2 | 2207-NPCC-MWS-T-00592 | 2015-08-23 | GM-60295-0781 | 2015-09-07 | A | For Info only
188 | TEMPORARY KNEE BRACE DETAILS FOR 10" WATER INJECTION RISER FROM ULRP TO WHT-6 | 2207-NN-1098 | AD197-573/481-PL-62187 | A | 3 | 2015-07-08 | 2015-07-08 | -57 | CSE-OF-2207-216 | 2015-09-03 | 2207-NPCC-AO-T-03406 | 2015-09-06 | TR-UFFDP1-13-06211 | 2015-09-17 | 1 | 2207-NPCC-MWS-T-00624 | 2015-09-07 | GM-60295-0806 | 2015-09-14 | A | -
189 | TEMPORARY KNEE BRACE DETAILS FOR 8" GAS INJECTION RISER FROM WHT-6 TO ULRP | 2207-NN-1099 | AD197-481/573-PL-62188 | A | 3 | 2015-07-22 | 2015-07-22 | -40 | CSE-OF-2207-207 | 2015-08-31 | 2207-NPCC-AO-T-03361 | 2015-09-06 | TR-UFFDP1-13-06208 | 2015-09-17 | 1 | 2207-NPCC-MWS-T-00622 | 2015-09-07 | GM-60295-0807 | 2015-09-14 | A | -
190 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS LIFT RISER FROM WHT-6 TO ULRP | 2207-NN-1100 | AD197-481/573-PL-62189 | A | 3 | 2015-08-05 | 2015-08-05 | -28 | CSE-OF-2207-214 | 2015-09-02 | 2207-NPCC-AO-T-03378 | 2015-09-03 | TR-UFFDP1-13-06206 | 2015-09-17 | 1 | 2207-NPCC-MWS-T-00619 | 2015-09-06 | GM-60295-0808 | 2015-09-14 | A | -
191 | TEMPORARY KNEE BRACE DETAILS FOR 10" WATER INJECTION RISER FROM WHT-6 TO WHT-4 | 2207-NN-1101 | AD197-481/477-PL-62190 | A | 3 | 2015-08-19 | 2015-08-19 | -61 | CSE-OF-2207-236 | 2015-09-22 | 2207-NPCC-AO-T-03565 | 2015-09-22 | TR-UFFDP1-13-06308 | 2015-10-04 | 1 | 2207-NPCC-MWS-T-00655 | 2015-09-22 | GM-60295-0878 | 2015-11-25 | A | -
|  |  |  | B |  |  |  |  | CSE-OF-2207-265 | 2016-02-07 | 2207-NPCC-AO-T-04321 | 2015-02-11 | TR-UFFDP1-13-07167 | 2016-03-15 | 1 | 2207-NPCC-MWS-T-00761 | 2016-02-14 |  |  |  | MWS
192 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS LIFT RISER FROM WHT-4 TO WHT-6 | 2207-NN-1102 | AD197-477/481-PL-62191 | A | 3 | 2015-09-02 | 2015-09-02 | -47 | CSE-OF-2207-236 | 2015-09-22 | 2207-NPCC-AO-T-03565 | 2015-09-22 | TR-UFFDP1-13-06308 | 2015-10-04 | 1 | 2207-NPCC-MWS-T-00655 | 2015-09-22 | GM-60295-0879 | 2015-11-25 | A | -
|  |  |  | B |  |  |  |  | CSE-OF-2207-265 | 2016-02-07 | 2207-NPCC-AO-T-04321 | 2015-02-11 | TR-UFFDP1-13-07167 | 2016-03-15 | 1 | 2207-NPCC-MWS-T-00761 | 2016-02-14 |  |  |  | MWS
193 | TEMPORARY KNEE BRACE DETAILS FOR 20" MAIN OIL LINE FROM ULRP TO ZIRKU | 2207-NN-1103 | AD197-573/602-PL-62192 | A | 3 | 2015-09-16 | 2015-09-16 | 2 | CSE-OF-2207-227 | 2015-09-13 | 2207-NPCC-AO-T-03497 | 2015-09-14 | TR-UFFDP1-13-06303 | 2015-09-30 | 1 | 2207-NPCC-MWS-T-00637 | 2015-09-15 | GM-60295-0815 | 2015-09-20 | A | -
194 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 (@ULRP) | 2207-NN-0090 | AD162-573-PL-62193 | A | 2 | 2014-09-06 |  | -39 | V | - | 2207-NPCC-AO-T-01649 | 2014-10-15 | TR-UFFDP1-13-04039 | 2014-10-21 | ACCEPTED | 2207-NPCC-MWS-T-00402 | 2014-10-16 | GM-60295-0559 | 2014-10-29 | ACCEPTED | -
|  |  |  | B | - | - |  | - | CSE-OF-2207-094 | 2014-11-09 | 2207-NPCC-AO-T-01789 | 2014-11-10 | TR-UFFDP1-13-04228 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00422 | 2014-11-11 | GM-60295-0577 | 2014-11-13 | ACCEPTED | -
195 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 (@WHT-5) | 2207-NN-0091 | AD162-480-PL-62194 | A | 2 | 2014-08-04 |  | -50 | CSE-OF-2207-075 | 2014-09-24 | 2207-NPCC-AO-T-01542 | 2014-09-25 | TR-UFFDP1-13-04232 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00375 | 2014-09-27 | GM-60295-0503 | 2014-10-01 | ACCEPTED | -
|  |  |  | B |  |  |  |  | CSE-OF-2207-087 | 2014-10-27 | 2207-NPCC-AO-T-01725 | 2014-10-29 | TR-UFFDP1-13-04123 | 2014-11-04 | ACCEPTED | 2207-NPCC-MWS-T-00413 | 2012-11-01 | GM-60295-0568 | 2014-11-02 | ACCEPTED | -
196 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID P/L FROM WHT-5 TO WHT-2(@WHT-5) | 2207-NN-0092 | AD162-480-PL-62195 | A | 2 | 2014-08-08 |  | -52 | CSE-OF-2207-080 | 2014-09-29 | 2207-NPCC-AO-T-01578 | 2014-09-30 | TR-UFFDP1-13-03967 | 2014-10-06 | ACCEPTED | 2207-NPCC-MWS-T-00386 | 2014-10-02 | GM-60295-0523 | 2014-10-13 | ACCEPTED | -
|  |  |  | B |  |  |  |  | CSE-OF-2207-086 | 2014-10-27 | 2207-NPCC-AO-T-01723 | 2014-10-28 | TR-UFFDP1-13-04124 | 2014-11-03 | ACCEPTED | 2207-NPCC-MWS-T-00411 | 2014-10-29 | GM-60295-0564 | 2014-11-02 | ACCEPTED | -
197 | ` | 2207-NN-0093 | AD162-475-PL-62196 | A | 2 | 2014-08-26 |  | -82 | CSE-OF-2207-098 | 2014-11-16 | 2207-NPCC-AO-T-01830 | 2014-11-18 | TR-UFFDP1-13-04402 | 2014-12-07 | ACCEPTED | 2207-NPCC-MWS-T-00434 | 2014-11-19 | GM-60295-0604 | 2014-12-17 | ACCEPTED | -
198 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP (@WHT-3) | 2207-NN-0094 | AD162-476-PL-62197 | A | 2 | 2014-09-26 |  |  | CSE-OF-2207-027 | 2014-07-21 | 2207-NPCC-AO-T-01272 | 2014-07-30 |  |  |  | 2207-NPCC-MWS-T-00265 | 2014-08-03 | GM-60295-0422 | 2014-09-10 | B (Accepted with comments) | Client
|  |  |  | B | - | - |  | - | CSE-OF-2207-044 'CSE-OF-2207-049 Revised | 2014-09-07 | 2207-NPCC-AO-T-01423 | 2014-09-16 | TR-UFFDP1-13-03864 | 2014-10-07 | ACCEPTED | 2207-NPCC-MWS-T-00343 | 2014-09-18 | GM-60295-0470 | 2014-09-24 | ACCEPTED | -
|  |  |  | C | - | - |  | - | CSE-OF-2207-047 Discarded | 2014-09-10
199 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP (@ULRP) | 2207-NN-0095 | AD162-573-PL-62198 | A | 2 | 2014-09-09 |  | -21 | CSE-OF-2207-082 | 2014-09-30 | 2207-NPCC-AO-T-01598 | 2014-10-02 | TR-UFFDP1-13-04233 | 2014-11-17 | ACCEPTED | 2207-NPCC-MWS-T-00383 | 2014-10-02 | GM-60295- 0528 | 2014-10-13 | ACCEPTED | -
200 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 (@WHT-1) | 2207-NN-0096 | AD162-474-PL-62199 | A | 2 | 2014-10-21 |  | -16 | CSE-OF-2207-093 | 2014-11-06 | 2207-NPCC-AO-T-01783 | 2014-11-10 | TR-UFFDP1-13-04401 | 2014-12-07 | ACCEPTED | 2207-NPCC-MWS-T-00424 | 2014-11-11 | GM-60295-0603 | 2014-12-17 | ACCEPTED | -
201 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 (@WHT-3) | 2207-NN-0097 | AD162-476-PL-62200 | A | 2 | 2014-09-29 |  | -1 | CSE-OF-2207-061 | 2014-09-16 | 2207-NPCC-AO-T-01484 | 2014-09-22 | TR-UFFDP1-13-04237 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00365 | 2014-09-24 | GM-60295-0502 | 2014-09-30 | ACCEPTED | -
202 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 (@WHT-1) | 2207-NN-0098 | AD162-474-PL-62201 | A | 2 | 2014-10-25 |  | -2125 | CSE-OF-2207-093 | 2014-11-06 | 2207-NPCC-AO-T-01783 | 2014-11-10 | TR-UFFDP1-13-04401 | 2014-12-07 | ACCEPTED | 2207-NPCC-MWS-T-00424 | 2014-11-11 | GM-60295-0592 | 2014-12-08 | ACCEPTED | -
|  |  |  | B | - | - |  | - | CSE-OF-2207-096 | 2014-11-12 | 2207-NPCC-AO-T-01811 | 2014-11-16 | TR-UFFDP1-13-04398 | 2014-12-07 | ACCEPTED | 2207-NPCC-MWS-T-00431 | 2014-11-17 | GM-60295-0592 | 2014-12-08 | ACCEPTED | -
203 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 (@WHT-3) | 2207-NN-0099 | AD162-476-PL-62202 | A | 2 | 2014-10-03 |  | 17 | CSE-OF-2207-057 | 2014-09-14 | 2207-NPCC-AO-T-01464 | 2014-09-16 | TR-UFFDP1-13-03858 | 2014-09-17 | ACCEPTED | 2207-NPCC-MWS-T-00340 | 2014-09-18 | GM-60295-0497 | 2014-09-29 | B (Accepted with comments) | -
204 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 (@WHT-1) | 2207-NN-0100 | AD162-474-PL-62203 | A | 2 | 2014-10-29 |  | 0 | CSE-OF-2207-089 | 2014-10-29 | 2207-NPCC-AO-T-01743 | 2014-10-30 | TR-UFFDP1-13-04122 | 2014-11-04 | ACCEPTED | 2207-NPCC-MWS-T-00415 | 2012-11-01 | GM-60295-0571 | 2014-11-02 | ACCEPTED | -
|  |  |  | B | - | - |  | - | CSE-OF-2207-095 | 2014-11-11 | 2207-NPCC-AO-T-01810 | 2014-11-13 | TR-UFFDP1-13-04399 | 2014-12-07 | ACCEPTED | 2207-NPCC-MWS-T-00429 | 2014-11-15 | GM-60295-0593 | 2014-12-08 | ACCEPTED | -
205 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 (@WHT-3) | 2207-NN-0101 | AD162-476-PL-62204 | A | 2 | 2014-10-07 |  |  | CSE-OF-2207-058 | 2014-09-15 | 2207-NPCC-AO-T-01469 | 2014-09-18 | TR-UFFDP1-13-04238 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00346 | 2014-09-21 | GM-60295-0498 | 2014-09-29 | ACCEPTED | -
206 | RISER/SPOOL LIFTING AND INSTALLATION FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP (@WHT-3) | 2207-NN-0102 | AD162-476-PL-62205 | A | 2 | 2014-10-11 |  | 29 | CSE-OF-2207-052 | 2014-09-11 | 2207-NPCC-AO-T-01452 | 2014-09-12 | TR-UFFDP1-13-04234 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00332 | 2014-09-16 | GM-60295-0482 | 2014-09-25 | B (Accepted with comments) | -
207 | RISER/SPOOL LIFTING AND INSTALLATION FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP (@ULRP) | 2207-NN-0103 | AD162-573-PL-62206 | A | 2 | 2014-09-12 |  | -46 | V | - | 2207-NPCC-AO-T-01624 | 2014-10-09 | TR-UFFDP1-13-04008 | 2014-10-15 | ACCEPTED | 2207-NPCC-MWS-T-00391 | 2014-10-11 | GM-60295-0537 | 2014-10-15 | ACCEPTED | -
208 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP (@WHT-3) | 2207-NN-0104 | AD162-476-PL-62207 | A | 2 | 2014-10-15 |  | 34 | CSE-OF-2207-047 | 2014-09-10 | 2207-NPCC-AO-T-01438 | 2014-09-11 | TR-UFFDP1-13-04235 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00320 | 2014-09-11 | GM-60295-0485 | 2014-09-25 | ACCEPTED | -
209 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP (@ULRP) | 2207-NN-0105 | AD162-573-PL-62208 | A | 2 | 2014-09-15 |  | -24 | V | - | 2207-NPCC-AO-T-01625 | 2014-10-09 | TR-UFFDP1-13-04009 | 2014-10-15 | ACCEPTED | 2207-NPCC-MWS-T-00392 | 2014-10-11 | GM-60295-0538 | 2014-10-15 | ACCEPTED | -
210 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP (@WHT-3) | 2207-NN-0106 | AD162-476-PL-62209 | A | 2 | 2014-10-19 |  | 37 | CSE-OF-2207-053 | 2014-09-11 | 2207-NPCC-AO-T-01458 | 2014-09-16 | TR-UFFDP1-13-03863 | 2014-09-17 | ACCEPTED | 2207-NPCC-MWS-T-00345 | 2014-09-18 | GM/60295/0483 | 2014-09-25 | ACCEPTED | -
211 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP (@ULRP) | 2207-NN-0107 | AD162-573-PL-62210 | A | 2 | 2014-09-18 |  | -42 | CSE-OF-2207-092 | 2014-11-05 | 2207-NPCC-AO-T-01777 | 2014-11-06 | TR-UFFDP1-13-04398 | 2014-12-07 | ACCEPTED | 2207-NPCC-MWS-T-00420 | 2014-11-08 | GM-60295-0539 | 2014-10-15 | ACCEPTED | -
212 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 (@ULRP) | 2207-NN-0108 | AD162-573-PL-62211 | A | 2 | 2014-09-21 |  | -36 | CSE-OF-2207-086 | 2014-10-27 | 2207-NPCC-AO-T-01723 | 2014-10-28 | TR-UFFDP1-13-04124 | 2014-11-03 | ACCEPTED | 2207-NPCC-MWS-T-00411 | 2014-10-29 | GM-60295-0565 | 2014-11-02 | ACCEPTED | -
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-094 | 2014-11-09 | 2207-NPCC-AO-T-01789 | 2014-11-10 | TR-UFFDP1-13-04228 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00422 | 2014-11-11 | GM-60295-0576 | 2014-11-13 | ACCEPTED | -
213 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 (@WHT-5) | 2207-NN-0109 | AD162-480-PL-62212 | A | 2 | 2014-08-12 |  | -43 | CSE-OF-2207-076 | 2014-09-24 | 2207-NPCC-AO-T-01552 | 2014-09-27 | TR-UFFDP1-13-04236 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00378 | 2014-10-01 | GM-60295-0519 | 2014-10-13 | ACCEPTED | -
|  |  |  | B | - | - |  | - | V | - | 2207-NPCC-AO-T-01681 | 2014-10-20 | TR-UFFDP1-13-04248 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00404 | 2014-10-20 | GM-60295-0544 | 2014-10-18 | ACCEPTED | -
|  |  |  | C | - | - |  | - | CSE-OF-2207-087 | 2014-10-27 | 2207-NPCC-AO-T-01725 | 2014-10-29 | TR-UFFDP1-13-04123 | 2014-11-04 | ACCEPTED | 2207-NPCC-MWS-T-00413 | 2012-11-01 | GM-60295-0569 | 2014-11-02 | ACCEPTED | -
214 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5(@ULRP) | 2207-NN-0110 | AD162-573-PL-62213 | A | 2 | 2014-09-24 |  | -42 | CSE-OF-2207-094 | 2014-11-09 | 2207-NPCC-AO-T-01650 | 2014-11-10 | TR-UFFDP1-13-04399 | 2014-12-07 | ACCEPTED | 2207-NPCC-MWS-T-00403 | 2014-11-11 | GM-60295-0578 | 2014-11-13 | ACCEPTED | -
|  |  |  | B | - | - |  | - | CSE-OF-2207-096 | 2014-11-12 | 2207-NPCC-AO-T-01811 | 2014-11-16 | TR-UFFDP1-13-04398 | 2014-12-07 | ACCEPTED | 2207-NPCC-MWS-T-00431 | 2014-11-17 | GM-60295-0586 | 2014-11-27 | ACCEPTED | -
215 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5 (@WHT-5) | 2207-NN-0111 | AD162-480-PL-62214 | A | 2 | 2014-08-16 |  | -32 | CSE-OF-2207-066 | 2014-09-17 | 2207-NPCC-AO-T-01494 | 2014-09-22 |  |  |  | 2207-NPCC-MWS-T-00355 | 2014-09-22 | GM-60295-0499 | 2014-09-30 | ACCEPTED | Client
|  |  |  | B | - | - |  | - | V | - | 2207-NPCC-AO-T-01682 | 2014-10-20 | TR-UFFDP1-13-04126 | 2014-11-03 | ACCEPTED | 2207-NPCC-MWS-T-00405 | 2014-10-20 | GM-60295-0545 | 2014-10-19 | ACCEPTED | -
|  |  |  | C | - | - |  | - | V | - | 2207-NPCC-AO-T-01694 | 2014-10-21 | TR-UFFDP1-13-04126 | 2014-11-03 | ACCEPTED | 2207-NPCC-MWS-T-00406 | 2014-10-21 | GM-60295-0553 | 2014-10-23 | ACCEPTED | -
|  |  |  | D | - | - |  | - | CSE-OF-2207-087 | 2014-10-27 | 2207-NPCC-AO-T-01725 | 2014-10-29 | TR-UFFDP1-13-04123 | 2014-11-04 | ACCEPTED | 2207-NPCC-MWS-T-00413 | 2012-11-01 | GM-60295-0570 | 2014-11-02 | ACCEPTED | -
216 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 (@WHT-5) | 2207-NN-0112 | AD162-480-PL-62215 | A | 2 | 2014-08-20 |  | -41 | CSE-OF-2207-082 | 2014-09-30 | 2207-NPCC-AO-T-01598 | 2014-10-02 | TR-UFFDP1-13-04233 | 2014-11-17 | ACCEPTED | 2207-NPCC-MWS-T-00383 | 2014-10-02 | GM-60295-0524 | 2014-10-13 | ACCEPTED | -
|  |  |  | B | ? | ? |  | ? | V | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ?
|  |  |  | C | - | - |  | - | V | - | 2207-NPCC-AO-T-01695 | 2014-10-21 | TR-UFFDP1-13-04125 | 2014-11-03 | ACCEPTED | 2207-NPCC-MWS-T-00407 | 2014-10-21 | GM-60295-0552 | 2014-10-23 | ACCEPTED | -
217 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 (@WHT-2) | 2207-NN-0113 | AD162-475-PL-62216 | A | 2 | 2014-08-30 |  | -81 | CSE-OF-2207-100 | 2014-11-19 | 2207-NPCC-AO-T-01846 | 2014-11-22 | TR-UFFDP1-13-04403 | 2014-12-07 | ACCEPTED | 2207-NPCC-MWS-T-00437 | 2014-11-24 | GM-60295-0602 | 2014-12-17 | ACCEPTED | -
218 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 (@WHT-5) | 2207-NN-0114 | AD162-480-PL-62217 | A | 2 | 2014-08-24 |  | -32 | CSE-OF-2207-078 | 2014-09-25 | 2207-NPCC-AO-T-01566 | 2014-10-07 | TR-UFFDP1-13-03983 | 2014-10-13 | ACCEPTED | 2207-NPCC-MWS-T-00390 | 2014-10-11 | GM-60295-0521 | 2014-10-13 | ACCEPTED | -
219 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 (@WHT-2) | 2207-NN-0115 | AD162-475-PL-62218 | A | 2 | 2014-09-03 |  | -64 | CSE-OF-2207-093 | 2014-11-06 | 2207-NPCC-AO-T-01783 | 2014-11-10 | TR-UFFDP1-13-04401 | 2014-12-07 | ACCEPTED | 2207-NPCC-MWS-T-00424 | 2014-11-11 | GM-60295-0601 | 2014-12-17 | ACCEPTED | -
|  |  |  | B | - | - |  | - | CSE-OF-2207-095 | 2014-11-11 | 2207-NPCC-AO-T-01810 | 2014-11-13 | TR-UFFDP1-13-04399 | 2014-12-07 | ACCEPTED | 2207-NPCC-MWS-T-00429 | 2014-11-15 | GM-60295-0601 | 2014-12-17 | ACCEPTED | -
220 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP (@WHT-6) | 2207-NN-1104 | AD197-481-PL-62219 | A | 2 | 2015-07-01 | 2015-04-01 | -218 | CSE-OF-2207-264 | 2016-02-04 | 2207-NPCC-AO-T-04313 | 2016-02-08 | TR-UFFDP1-13-07092 | 2016-03-02 | 2 | 2207-NPCC-MWS-T-00751 | 2016-02-09 |  |  |  | MWS
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-281 | 2016-09-26 | 2207-NPCC-AO-T-05362 | 2016-09-28 | TR-UFFDP1-13-08002 | 2016-11-07 | 1 | 2207-NPCC-MWS-T-00855 | 2016-09-28 | GM/60295/1023 | 2016-10-12 | B
|  |  |  | CRS TO MWS |  |  |  |  | SENT BY EMAIL | 2016-10-17 | [5 empty] | 2207-NPCC-MWS-T-00874 | 2016-10-18 | GM/60295/1041 | 2016-10-19 | A
|  |  |  | 1 | 1 |  |  |  | CSE-OF-2207-285 | 2016-10-12 | 2207-NPCC-AO-T-05436 | 2016-10-17 | TR-UFFDP1-13-07954 | 2016-10-23 | 1 | 2207-NPCC-MWS-T-00872 | 2016-10-18
221 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP (@ULRP) | 2207-NN-1105 | AD197-573-PL-62220 | A | 2 | 2015-07-05 | 2015-04-08 | -57 | CSE-OF-2207-212 | 2015-08-31 | 2207-NPCC-AO-T-03369 | 2015-09-02 | TR-UFFDP1-13-06132 TR-UFFDP1-13-06196 | 09-09-15 16-09-15 | 4 | 2207-NPCC-MWS-T-00616 | 2015-09-02 | GM-60295-0756 | 2015-09-06 | A | -
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-226 | 2015-09-13 | 2207-NPCC-AO-T-03500 | 2015-09-14 | TR-UFFDP1-13-06304 | 2015-09-30 | 1 | 2207-NPCC-MWS-T-00639 | 2015-09-15 | GM-60295-0816 | 2015-09-20 | A | -
222 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 (@ULRP) | 2207-NN-1106 | AD197-573-PL-62221 | A | 2 | 2015-07-09 | 2015-04-15 | -61 | CSE-OF-2207-126 | 2015-06-09 | 2207-NPCC-AO-T-02834 | 2015-06-10 | TR-UFFDP1-13-05660 | 2015-06-14 | 2 | 2207-NPCC-MWS-T-00504 | 2015-06-11 | GM-60295-0921 | 2016-01-03 | A | -
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-192 | 2015-08-25 | 2207-NPCC-AO-T-03299 | 2015-08-25 | TR-UFFDP1-13-06052 | 2015-08-27 | 1 | 2207-NPCC-MWS-T-00597 | 2015-08-26 | GM-60295-0757 | 2015-09-06 | A | -
|  |  |  | 1 | - | - |  | - | CSE-OF-2207-219 | 2015-09-08 | 2207-NPCC-AO-T-03442 | 2015-09-09 | TR-UFFDP1-13-06162 | 2015-09-15 | 1 | 2207-NPCC-MWS-T-00629 | 2015-09-10 | GM-60295-0812 | 2015-09-15 | A | -
223 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 (@WHT-7) | 2207-NN-1107 | AD197-482-PL-62222 | A | 2 | 2015-04-22 | 2015-04-22 | 2 | CSE-OF-2207-116 | 2015-04-20 | 2207-NPCC-AO-T-02547 | 2015-04-29 | TR-UFFDP1-13-05475 | 2015-05-17 | 2 | 2207-NPCC-MWS-T-00485 | 2015-05-13 | GM-60295-0666 | 2015-05-18 | A | -
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-178 | 2015-08-16 | 2207-NPCC-AO-T-03233 | 2015-08-17 | TR-UFFDP1-13-06013 | 2015-08-23 | 1 | 2207-NPCC-MWS-T-00576 | 2015-08-17 | GM-60295-0758 | 2015-09-06 | A | -
224 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 (@WHT-7) | 2207-NN-1108 | AD197-482-PL-62223 | A | 2 | 2015-04-29 | 2015-04-29 | 14 | CSE-OF-2207-114 | 2015-04-15 | 2207-NPCC-AO-T-02530 | 2015-04-29 | TR-UFFDP1-13-05474 | 2015-05-17 | 2 | 2207-NPCC-MWS-T-00488 | 2015-05-13 | GM-60295-0667 | 2015-05-18 | A | -
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-174 | 2015-08-13 | 2207-NPCC-AO-T-03212 | 2015-08-16 | TR-UFFDP1-13-06002 | 2015-08-18 | 1 | 2207-NPCC-MWS-T-00573 | 2015-08-16 | GM-60295-0759 | 2015-09-06 | A | -
|  |  |  | 1 |  |  |  |  | CSE-OF-2207-233 | 2015-09-20 | 2207-NPCC-AO-T-03552 | 2015-09-22 | TR-UFFDP1-13-06301 | 2015-09-30 | 1 | 2207-NPCC-MWS-T-00652 | 2015-09-22 | GM-60295-0880 | 2015-11-25 | A | -
225 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 (@WHT-8) | 2207-NN-1109 | AD197-483-PL-62224 | A | 2 | 2015-05-06 | 2015-05-06 | 21 | CSE-OF-2207-114 | 2015-04-15 | 2207-NPCC-AO-T-02530 | 2015-04-29 | TR-UFFDP1-13-05474 | 2015-05-17 | 2 | 2207-NPCC-MWS-T-00488 | 2015-05-13 | GM-60295-0668 | 2015-05-18 | A | -
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-169 | 2015-08-12 | 2207-NPCC-AO-T-03172 | 2015-08-13 | TR-UFFDP1-13-06001 | 2015-08-18 | 1 | 2207-NPCC-MWS-T-00568 | 2015-08-13 | GM-60295-0760 | 2015-09-06 | A | -
226 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 (@WHT-8) | 2207-NN-1110 | AD197-483-PL-62225 | A | 2 | 2015-05-13 | 2015-05-13 | 20 | CSE-OF-2207-117 | 2015-04-23 | 2207-NPCC-AO-T-02564 | 2015-04-29 | TR-UFFDP1-13-05489 | 2015-05-17 | 2 | 2207-NPCC-MWS-T-00484 | 2015-05-13 | GM-60295-0664 | 2015-05-17 | A | -
|  |  |  | 0 |  | - |  | - | CSE-OF-2207-167 | 2015-08-11 | 2207-NPCC-AO-T-03159 | 2015-08-12 | TR-UFFDP1-13-06000 | 2015-08-18 | 1 | 2207-NPCC-MWS-T-00565 | 2015-08-12 | GM-60295-0736 | 2015-08-16 | A | -
227 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 (@WHT-7) | 2207-NN-1111 | AD197-482-PL-62226 | A | 2 | 2015-07-13 | 2015-05-20 | -45 | CSE-OF-2207-202 | 2015-08-27 | 2207-NPCC-AO-T-03328 | 2015-09-01 | TR-UFFDP1-13-06131 | 2015-09-03 | 2 | 2207-NPCC-MWS-T-00609 | 2015-09-02 | GM-60295-0777 | 2015-09-07 | A | -
|  |  |  | 0 |  |  |  |  | CSE-OF-2207-233 | 2015-09-20 | 2207-NPCC-AO-T-03552 | 2015-09-22 | TR-UFFDP1-13-06301 | 2015-09-30 | 1 | 2207-NPCC-MWS-T-00652 | 2015-09-22 | GM-60295-0881 | 2015-11-25 | A | -
228 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 (@ WHT-7) | 2207-NN-1112 | AD197-482-PL-62227 | A | 2 | 2015-07-17 | 2015-05-27 | -32 | CSE-OF-2207-184 | 2015-08-18 | 2207-NPCC-AO-T-03247 | 2015-08-19 | TR-UFFDP1-13-06046 | 2015-09-30 | 2 | 2207-NPCC-MWS-T-00585 | 2015-08-19 | GM-60295-0778 | 2015-09-07 | A | -
|  |  |  | 0 |  |  |  |  | CSE-OF-2207-235 | 2015-09-21 | 2207-NPCC-AO-T-03556 | 2015-09-22 | TR-UFFDP1-13-06302 | 2015-09-30 | 1 | 2207-NPCC-MWS-T-00654 | 2015-09-22 | GM-60295-0882 | 2015-11-25 | A | -
229 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 (@ WHT-8) | 2207-NN-1113 | AD197-483-PL-62228 | A | 2 | 2015-06-03 | 2015-06-03 | 44 | CSE-OF-2207-116 | 2015-04-20 | 2207-NPCC-AO-T-02547 | 2015-04-29 | TR-UFFDP1-13-05475 | 2015-05-17 | 2 | 2207-NPCC-MWS-T-00485 | 2015-05-13 | GM-60295-0665 | 2015-05-18 | A | -
|  |  |  | 0 |  | - |  | - | CSE-OF-2207-167 | 2015-08-11 | 2207-NPCC-AO-T-03159 | 2015-08-12 | TR-UFFDP1-13-06000 | 2015-08-18 | 1 | 2207-NPCC-MWS-T-00565 | 2015-08-12 | GM-60295-0735 | 2015-08-15 | A | -
230 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 (@ULRP) | 2207-NN-1114 | AD197-573-PL-62229 | A | 2 | 2015-07-21 | 2015-06-10 | -203 | CSE-OF-2207-126 | 2015-06-09 | 2207-NPCC-AO-T-02834 | 2015-06-10 | TR-UFFDP1-13-05660 | 2015-06-14 | 2 | 2207-NPCC-MWS-T-00504 | 2015-06-11 |  |  |  | MWS
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-200 | 2015-08-27 | 2207-NPCC-AO-T-03324 | 2015-08-30 | TR-UFFDP1-13-06140 | 2015-09-08 | 1 | 2207-NPCC-MWS-T-00607 | 2015-09-02 | GM-60295-0779 | 2015-09-07 | A | -
231 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 (@WHT-7) | 2207-NN-1115 | AD197-482-PL-62230 | A | 2 | 2015-07-25 | 2015-06-17 | -23 | CSE-OF-2207-181 | 2015-08-17 | 2207-NPCC-AO-T-03240 | 2015-08-18 | TR-UFFDP1-13-06018 | 2015-08-23 | 1 | 2207-NPCC-MWS-T-00580 | 2015-08-18 | GM-60295-0780 | 2015-09-07 | A | -
232 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP (@WHT-7) | 2207-NN-1116 | AD197-482-PL-62231 | A | 2 | 2015-07-29 | 2015-06-24 | -22 | CSE-OF-2207-188 | 2015-08-20 | 2207-NPCC-AO-T-03262 | 2015-08-23 | TR-UFFDP1-13-06035 | 2015-08-26 | 2 | 2207-NPCC-MWS-T-00592 | 2015-08-23 | GM-60295-0781 | 2015-09-07 | A | -
|  |  |  | CRS |  |  |  |  | CSE-OF-2207-255 | 2015-12-15 | 2207-NPCC-AO-T-04076 | 2015-12-17 | TR-UFFDP1-13-06797 | 2016-01-03 | 1 | 2207-NPCC-MWS-T-00723 | 2015-12-17 | - | - | - | -
233 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP (@ULRP) | 2207-NN-1117 | AD197-573-PL-62232 | A | 2 | 2015-08-02 | 2015-07-01 | -24 | CSE-OF-2207-197 | 2015-08-26 | 2207-NPCC-AO-T-03312 | 2015-08-27 | TR-UFFDP1-13-06138 | 2015-09-08 | 1 | 2207-NPCC-MWS-T-00601 | 2015-08-27 | GM-60295-0782 | 2015-09-07 | A | -
|  |  |  | 0 | - | - |  | - | CSE-OF-2207-224 | 2015-09-09 | 2207-NPCC-AO-T-03457 | 2015-09-10 | TR-UFFDP1-13-06213 | 2015-09-17 | 1 | 2207-NPCC-MWS-T-00631 | 2015-09-10 | GM-60295-0805 | 2015-09-14 | A | -
234 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 (@ULRP) | 2207-NN-1118 | AD197-573-PL-62234 | A | 2 | 2015-08-06 | 2015-07-08 | -28 | CSE-OF-2207-216 | 2015-09-03 | 2207-NPCC-AO-T-03406 | 2015-09-06 | TR-UFFDP1-13-06212 | 2015-09-17 | 4 | 2207-NPCC-MWS-T-00624 | 2015-09-07 | GM-60295-0806 | 2015-09-14 | A | -
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-226 | 2015-09-13 | 2207-NPCC-AO-T-03500 | 2015-09-14 | TR-UFFDP1-13-06304 | 2015-09-30 | 1 | 2207-NPCC-MWS-T-00639 | 2015-09-15 | GM-60295-0818 | 2015-09-20 | A | -
235 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 (@WHT-6) | 2207-NN-1119 | AD197-481-PL-62235 | A | 2 | 2015-08-10 | 2015-07-15 | -183 | CSE-OF-2207-268 | 2016-02-09 | 2207-NPCC-AO-T-04343 | 2016-02-11 | TR-UFFDP1-13-07245 | 2016-03-29 | 2 | 2207-NPCC-MWS-T-00758 | 2015-02-11 |  |  |  | CLIENT/MWS
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-281 | 2016-09-26 | 2207-NPCC-AO-T-05362 | 2016-09-28 | TR-UFFDP1-13-08002 | 2016-11-07 | 1 | 2207-NPCC-MWS-T-00855 | 2016-09-28 | GM/60295/1025 | 2016-10-12 | B
|  |  |  | CRS TO MWS |  |  |  |  | SENT BY EMAIL | 2016-10-17 | [5 empty] | 2207-NPCC-MWS-T-00874 | 2016-10-18 | GM-60295-1040 | 2016-10-19 | A
236 | RISER/SPOOL LIFTING AND INSTALLATION FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP (@WHT-6) | 2207-NN-1120 | AD197-481-PL-62236 | A | 2 | 2015-08-14 | 2015-07-22 | -179 | CSE-OF-2207-267 | 2016-02-08 | 2207-NPCC-AO-T-04329 | 2016-02-11 | TR-UFFDP1-13-07162 | 2016-03-15 | 2 | 2207-NPCC-MWS-T-00756 | 2015-02-11 |  |  |  | CLIENT/MWS
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-281 | 2016-09-26 | 2207-NPCC-AO-T-05362 | 2016-09-28 | TR-UFFDP1-13-08002 | 2016-11-07 | 1 | 2207-NPCC-MWS-T-00855 | 2016-09-28 | GM/60295/1024 | 2016-10-12 | B
|  |  |  | CRS TO MWS |  |  |  |  | SENT BY EMAIL | 2016-10-17 | [5 empty] | 2207-NPCC-MWS-T-00874 | 2016-10-18 | GM/60295/1042 | 2016-10-19 | A
237 | RISER/SPOOL LIFTING AND INSTALLATION FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP (@ULRP) | 2207-NN-1121 | AD197-573-PL-62237 | A | 2 | 2015-08-18 | 2015-07-29 | -13 | CSE-OF-2207-207 | 2015-08-31 | 2207-NPCC-AO-T-03361 | 2015-09-06 | TR-UFFDP1-13-06209 | 2015-09-17 | 4 | 2207-NPCC-MWS-T-00622 | 2015-09-07 | GM-60295-0807 | 2015-09-14 | A | -
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-226 | 2015-09-13 | 2207-NPCC-AO-T-03500 | 2015-09-14 | TR-UFFDP1-13-06304 | 2015-09-30 | 1 | 2207-NPCC-MWS-T-00639 | 2015-09-15 | GM-60295-0820 | 2015-09-20 | A | -
238 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP (@WHT-6) | 2207-NN-1122 | AD197-481-PL-62238 | A | 2 | 2015-08-22 | 2015-08-05 | -171 | CSE-OF-2207-267 | 2016-02-08 | 2207-NPCC-AO-T-04329 | 2016-02-11 | TR-UFFDP1-13-07162 | 2016-03-15 | 2 | 2207-NPCC-MWS-T-00756 | 2015-02-11 |  |  |  | CLIENT/MWS
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-281 | 2016-09-26 | 2207-NPCC-AO-T-05362 | 2016-09-28 | TR-UFFDP1-13-08002 | 2016-11-07 | 1 | 2207-NPCC-MWS-T-00855 | 2016-09-28 | GM/60295/1026 | 2016-10-12 | B
|  |  |  | CRS TO MWS |  |  |  |  | SENT BY EMAIL | 2016-10-17 | [5 empty] | 2207-NPCC-MWS-T-00874 | 2016-10-18 | GM/60295/1043 | 2016-10-19 | A
239 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP (@ULRP) | 2207-NN-1123 | AD197-573-PL-62239 | A | 2 | 2015-08-26 | 2015-08-12 | -7 | CSE-OF-2207-214 | 2015-09-02 | 2207-NPCC-AO-T-03378 | 2015-09-03 | TR-UFFDP1-13-06207 | 2015-09-17 | 4 | 2207-NPCC-MWS-T-00619 | 2015-09-06 | GM-60295-0808 | 2015-09-14 | A | -
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-226 | 2015-09-13 | 2207-NPCC-AO-T-03500 | 2015-09-14 | TR-UFFDP1-13-06304 | 2015-09-30 | 1 | 2207-NPCC-MWS-T-00639 | 2015-09-15 | GM-60295-0821 | 2015-09-20 | A | -
|  |  |  | 1 | - | - |  | - | CSE-OF-2207-230 | 2015-09-15 | 2207-NPCC-AO-T-03520 | 2015-09-17 | TR-UFFDP1-13-06300 | 2015-09-30 | 1 | 2207-NPCC-MWS-T-00644 | 2015-09-17 | GM-60295-0909 | 2015-12-13 | A | -
240 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 (@WHT-6) | 2207-NN-1124 | AD197-481-PL-62240 | A | 2 | 2015-08-30 | 2015-08-19 | -163 | CSE-OF-2207-265 | 2016-02-07 | 2207-NPCC-AO-T-04320 | 2016-02-11 | TR-UFFDP1-13-07166 | 2016-03-15 | 2 | 2207-NPCC-MWS-T-00754 | 2015-02-11 |  |  |  | MWS
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-281 | 2016-09-26 | 2207-NPCC-AO-T-05362 | 2016-09-28 | TR-UFFDP1-13-08002 | 2016-11-07 | 1 | 2207-NPCC-MWS-T-00855 | 2016-09-28 | GM/60295/1027 | 2016-10-12 | A
|  |  |  | 1 | 1 |  |  |  | CSE-OF-2207-287 | 2016-10-17 | [5 empty] | 2207-NPCC-MWS-T-00875 | 2016-10-19
241 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 (@WHT-4) | 2207-NN-1125 | AD197-477-PL-62241 | A | 2 | 2015-09-03 | 2015-08-26 | -14 | CSE-OF-2207-231 | 2015-09-17 | 2207-NPCC-AO-T-03544 | 2015-09-20 | TR-UFFDP1-13-06310 | 2015-10-04 | 1 | 2207-NPCC-MWS-T-00646 | 2015-09-21 |  |  |  | MWS
|  |  |  | 0 |  |  |  |  | CSE-OF-2207-239 | 2015-09-29 | 2207-NPCC-AO-T-03623 | 2015-09-30 | TR-UFFDP1-13-06318 | 2015-10-04 | 1 | 2207-NPCC-MWS-T-00662 | 2015-10-01 |  |  |  | MWS
|  |  |  | 1 |  |  |  |  | CSE-OF-2207-245 | 2015-10-20 | 2207-NPCC-AO-T-03808 | 2015-10-21 | TR-UFFDP1-13-06424 | 2015-10-26 | 1 | Email | 2015-10-12 | GM-60295-0839 | 2015-10-13 | A | CLIENT
242 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 (@WHT-4) | 2207-NN-1126 | AD197-477-PL-62242 | A | 2 | 2015-09-07 | 2015-09-02 | -10 | CSE-OF-2207-231 | 2015-09-17 | 2207-NPCC-AO-T-03544 | 2015-09-20 | TR-UFFDP1-13-06310 | 2015-10-04 | 1 | 2207-NPCC-MWS-T-00646 | 2015-09-21 |  |  |  | MWS
|  |  |  | 0 |  |  |  |  | CSE-OF-2207-239 | 2015-09-29 | 2207-NPCC-AO-T-03623 | 2015-09-30 | TR-UFFDP1-13-06318 | 2015-10-04 | 1 | 2207-NPCC-MWS-T-00662 | 2015-10-01 |  |  |  | MWS
|  |  |  | 1 |  |  |  |  | CSE-OF-2207-245 | 2015-10-20 | 2207-NPCC-AO-T-03808 | 2015-10-21 | TR-UFFDP1-13-06424 | 2015-10-26 | 1 | Email | 2015-10-12 | GM-60295-0838 | 2015-10-13 | A | CLIENT
243 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 (@WHT-6) | 2207-NN-1127 | AD197-481-PL-62243 | A | 2 | 2015-09-11 | 2015-09-09 | -151 | CSE-OF-2207-265 | 2016-02-07 | 2207-NPCC-AO-T-04320 | 2016-02-11 | TR-UFFDP1-13-07166 | 2016-03-15 | 2 | 2207-NPCC-MWS-T-00754 | 2015-02-11 |  |  |  | MWS
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-281 | 2016-09-26 | 2207-NPCC-AO-T-05362 | 2016-09-28 | TR-UFFDP1-13-08002 | 2016-11-07 | 1 | 2207-NPCC-MWS-T-00855 | 2016-09-28 | GM/60295/1028 | 2016-10-12 | A
244 | RISER/SPOOL LIFTING AND INSTALLATION FOR 20" MAIN OIL LINE FROM ULRP TO ZIRKU (@ULRP) | 2207-NN-1128 | AD197-573-PL-62244 | A | 2 | 2015-09-15 | 2015-09-16 | 1 | CSE-OF-2207-227 | 2015-09-13 | 2207-NPCC-AO-T-03496 | 2015-09-14 | TR-UFFDP1-13-06401 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00636 | 2015-09-15 | GM-60295-0822 | 2015-09-20 | A | -
245 | INSTALLATION OF RISER PROTECTORS AT ULRP | 2207-NN-0116 | AD162-573-PL-62245 |  | 2 | 2014-09-06 |  | -2174
246 | INSTALLATION OF RISER PROTECTORS AT WHT-1 | 2207-NN-0117 | AD162-474-PL-62246 |  | 2 | 2014-10-21 |  | -2129
247 | INSTALLATION OF RISER PROTECTORS AT WHT-2 | 2207-NN-0118 | AD162-475-PL-62247 | A | 2 | 2014-08-26 |  | -119 | CSE-OF-2207-103 | 2014-12-23 | 2207-NPCC-AO-T-01983 | 2014-12-24 | TR-UFFDP1-13-04538 | 2014-12-25 | ACCEPTED | 2207-NPCC-MWS-T-00448 | 2014-12-25 | GM-60295-0609 | 2014-12-29 | ACCEPTED | -
248 | INSTALLATION OF RISER PROTECTORS AT WHT-3 | 2207-NN-0119 | AD162-476-PL-62248 | A | 2 | 2014-09-26 |  | 1 | CSE-OF-2207-078 | 2014-09-25 | 2207-NPCC-AO-T-01566 | 2014-10-07 | TR-UFFDP1-13-03983 | 2014-10-13 | ACCEPTED | 2207-NPCC-MWS-T-00390 | 2014-10-11 | GM-60295-0522 | 2014-10-13 | ACCEPTED | -
249 | REMOVAL OF EXISTING RISER PROTECTORS AT WHT-4 | 2207-NN-0120 | AD197-477-PL-62249 | A | 2 | 2015-06-17 | 2015-06-17 | -92 | CSE-OF-2207-231 | 2015-09-17 | 2207-NPCC-AO-T-03544 | 2015-09-20 | TR-UFFDP1-13-06309 | 2015-10-04 | 2 | 2207-NPCC-MWS-T-00646 | 2015-09-21 | - | - | - | MWS
|  |  |  | 0 |  |  |  |  | CSE-OF-2207-239 | 2015-09-29 | 2207-NPCC-AO-T-03623 | 2015-09-30 | TR-UFFDP1-13-06317 | 2015-10-04 | 2 | 2207-NPCC-MWS-T-00662 | 2015-10-01 | - | - | - | MWS
|  |  |  | 1 |  |  |  |  | CSE-OF-2207-243 | 2015-10-06 | 2207-NPCC-AO-T-03688 | 2015-10-08 | TR-UFFDP1-13-06365 | 2015-10-13 | 2 | 2207-NPCC-MWS-T-00672 | 2015-10-12 | GM-60295-0836 | 2015-10-13 | A | -
|  |  |  | 2 |  |  |  |  | CSE-OF-2207-246 | 2015-11-22 | 2207-NPCC-AO-T-03984 | 2015-11-23 | TR-UFFDP1-13-06643 | 2015-11-25 | 1 | 2207-NPCC-MWS-T-00710 | 2015-11-24 | GM-60295-0923 | 2016-01-03 | A | -
250 | INSTALLATION OF RISER PROTECTORS AT WHT-5 | 2207-NN-0121 | AD162-480-PL-62250 | A | 2 | 2014-08-04 | 2014-08-04 | -84 | CSE-OF-2207-086 | 2014-10-27 | 2207-NPCC-AO-T-01723 | 2014-10-28 | TR-UFFDP1-13-04124 | 2014-11-03 | 1 | 2207-NPCC-MWS-T-00411 | 2014-10-29 | GM-60295-0562 | 2014-11-02 | A | -
251 | REMOVAL & OFFLOADING OF EXISTING RISER PROTECTORS AT WHT-6 | 2207-NN-0122 | AD197-481-PL-62251 | A | 2 | 2015-06-25 | 2015-06-25 | -229 | CSE-OF-2207-265 | 2016-02-07 | 2207-NPCC-AO-T-04320 | 2016-02-11 | TR-UFFDP1-13-07166 | 2016-03-15 | 2 | 2207-NPCC-MWS-T-00754 | 2015-02-11 |  |  |  | MWS
|  |  |  | 0 | 1 |  |  |  | CSE-OF-2207-281 | 2016-09-26 | 2207-NPCC-AO-T-05362 | 2016-09-28 |  |  |  | 2207-NPCC-MWS-T-00855 | 2016-09-28 | GM/60295/1022 | 2016-10-12 | A
|  |  |  | 1 | 1 |  |  |  | CSE-OF-2207-285 | 2016-10-12 | 2207-NPCC-AO-T-05436 | 2016-10-17 |  |  |  | 2207-NPCC-MWS-T-00872 | 2016-10-18
|  |  |  | 2 | 1 |  |  |  | CSE-OF-2207-288 | 2016-10-18 | 2207-NPCC-AO-T-05467 | 2016-10-20 | TR-UFFDP1-13-07951 | 2016-10-25 | 1 | 2207-NPCC-MWS-T-00878 | 2016-10-20
252 | INSTALLATION OF RISER PROTECTORS AT WHT-7 | 2207-NN-0123 | AD197-482-PL-62252 | A | 2 | 2015-04-20 | 2015-04-20 | -127 | CSE-OF-2207-194 | 2015-08-25 | 2207-NPCC-AO-T-03307 | 2015-08-26 | TR-UFFDP1-13-06063 | 2015-08-31 | 1 | 2207-NPCC-MWS-T-00598 | 2015-08-26 | GM-60295-0911 | 2015-12-13 | A | -
253 | INSTALLATION OF RISER PROTECTORS AT WHT-8 | 2207-NN-0124 | AD197-483-PL-62253 | A | 2 | 2015-05-13 | 2015-05-13 | -104 | CSE-OF-2207-192 | 2015-08-25 | 2207-NPCC-AO-T-03299 | 2015-08-25 | TR-UFFDP1-13-06052 | 2015-08-27 | 1 | 2207-NPCC-MWS-T-00597 | 2015-08-26 | GM-60295-0757 | 2015-09-06 | A | -
254 | HYDROTEST DIAGRAM FOR 16" WELL FLUID P/L FROM ULRP TO WHT-5 | 2207-NN-0125 | AD162-573/480-PL-62254 | A | 3 | 2015-11-12 |  | 24 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
255 | HYDROTEST DIAGRAM FOR 16" WELL FLUID P/L FROM WHT-5 TO WHT-2 | 2207-NN-0126 | AD162-480/475-PL-62255 | A | 3 | 2015-09-20 |  | -29 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
256 | HYDROTEST DIAGRAM FOR 16" WELL FLUID P/L FROM WHT-3 TO ULRP | 2207-NN-0127 | AD162-476/573-PL-62256 | A | 3 | 2015-10-28 |  | 9 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
257 | HYDROTEST DIAGRAM FOR 16" WELL FLUID P/L FROM WHT-1 TO WHT-3 | 2207-NN-0128 | AD162-474/476-PL-62257 | A | 3 | 2015-09-05 |  | -44 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
258 | HYDROTEST DIAGRAM FOR 10" WATER INJECTION P/L FROM WHT-1 TO WHT-3 | 2207-NN-0129 | AD162-474/476-PL-62258 | A | 3 | 2015-09-07 |  | -42 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
259 | HYDROTEST DIAGRAM FOR 6" GAS LIFT P/L FROM WHT-1 TO WHT-3 | 2207-NN-0130 | AD162-474/476-PL-62259 | A | 3 | 2015-09-09 |  | -40 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
260 | HYDROTEST DIAGRAM FOR 8" GAS INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0131 | AD162-476/573-PL-62260 | A | 3 | 2015-10-31 |  | 12 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
261 | HYDROTEST DIAGRAM FOR 10" WATER INJECTION P/L FROM WHT-3 TO ULRP | 2207-NN-0132 | AD162-476/573-PL-62261 | A | 3 | 2015-11-02 |  | 14 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
262 | HYDROTEST DIAGRAM FOR 6" GAS LIFT P/L FROM WHT-3 TO ULRP | 2207-NN-0133 | AD162-476/573-PL-62262 | A | 3 | 2015-11-04 |  | 16 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
263 | HYDROTEST DIAGRAM FOR 6" GAS LIFT P/L FROM ULRP TO WHT-5 | 2207-NN-0134 | AD162-573/480-PL-62263 | A | 3 | 2015-11-07 |  | 19 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
264 | HYDROTEST DIAGRAM FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-5 | 2207-NN-0135 | AD162-573/480-PL-62264 | A | 3 | 2015-11-09 |  | 21 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
265 | HYDROTEST DIAGRAM FOR 10" WATER INJECTION P/L FROM WHT-5 TO WHT-2 | 2207-NN-0136 | AD162-480/475-PL-62265 | A | 3 | 2015-09-22 |  | -27 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
266 | HYDROTEST DIAGRAM FOR 6" GAS LIFT P/L FROM WHT-5 TO WHT-2 | 2207-NN-0137 | AD162-480/475-PL-62266 | A | 3 | 2015-09-24 |  | -25 | CSE-OF-2207-242 | 2015-10-06 | 2207-NPCC-AO-T-03687 | 2015-10-08 | TR-UFFDP1-13-06677 | 2015-11-30 | 1 | 2207-NPCC-MWS-T-00671 | 2015-10-08 |  |  | I | For Info only
267 | HYDROTEST DIAGRAM FOR 18" WELL FLUID P/L FROM WHT-6 TO ULRP | 2207-NN-1129 | AD197-481/477-PL-62267 | A | 3 | 2015-07-01 |  | -110 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
268 | HYDROTEST DIAGRAM FOR 16" WELL FLUID P/L FROM ULRP TO WHT-7 | 2207-NN-1130 | AD197-573/482-PL-62268 | A | 3 | 2015-07-04 |  | -107 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
269 | HYDROTEST DIAGRAM FOR 16" WELL FLUID P/L FROM WHT-7 TO WHT-8 | 2207-NN-1131 | AD197-482/483-PL-62269 | A | 3 | 2015-07-07 |  | -104 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
270 | HYDROTEST DIAGRAM FOR 10" WATER INJECTION P/L FROM WHT-8 TO WHT-7 | 2207-NN-1132 | AD197-483/482-PL-62270 | A | 3 | 2015-07-10 |  | -101 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
271 | HYDROTEST DIAGRAM FOR 6" GAS LIFT P/L FROM WHT-7 TO WHT-8 | 2207-NN-1133 | AD197-482/483-PL-62271 | A | 3 | 2015-07-13 |  | -98 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
272 | HYDROTEST DIAGRAM FOR 6" GAS LIFT P/L FROM ULRP TO WHT-7 | 2207-NN-1134 | AD197-573/482-PL-62272 | A | 3 | 2015-07-16 |  | -95 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
273 | HYDROTEST DIAGRAM FOR 10" WATER INJECTION P/L FROM WHT-7 TO ULRP | 2207-NN-1135 | AD197-482/573-PL-62273 | A | 3 | 2015-07-19 |  | -92 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
274 | HYDROTEST DIAGRAM FOR 10" WATER INJECTION P/L FROM ULRP TO WHT-6 | 2207-NN-1136 | AD197-573/481-PL-62274 | A | 3 | 2015-07-22 |  | -89 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
275 | HYDROTEST DIAGRAM FOR 8" GAS INJECTION P/L FROM WHT-6 TO ULRP | 2207-NN-1137 | AD197-481/573-PL-62275 | A | 3 | 2015-07-25 |  | -86 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
276 | HYDROTEST DIAGRAM FOR 6" GAS LIFT P/L FROM WHT-6 TO ULRP | 2207-NN-1138 | AD197-481/573-PL-62276 | A | 3 | 2015-07-28 |  | -83 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
277 | HYDROTEST DIAGRAM FOR 10" WATER INJECTION P/L FROM WHT-6 TO WHT-4 | 2207-NN-1139 | AD197-481/477-PL-62277 | A | 3 | 2015-07-31 |  | -80 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
278 | HYDROTEST DIAGRAM FOR 6" GAS LIFT P/L FROM WHT-4 TO WHT-6 | 2207-NN-1140 | AD197-477/481-PL-62278 | A | 3 | 2015-08-03 |  | -77 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06691 | 2015-12-06 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
279 | HYDROTEST DIAGRAM FOR 20" MAIN OIL LINE FROM ULRP TO KP 34.38 | 2207-NN-1141 | AD197-573/602-PL-62279 | A | 3 | 2015-08-06 |  | -74 | CSE-OF-2207-241 | 2015-10-06 | 2207-NPCC-AO-T-03636 | 2015-10-14 | TR-UFFDP1-13-06779 | 2015-12-29 | 1 | 2207-NPCC-MWS-T-00678 | 2015-10-13 |  |  | I | For Info only
280 | LIFTING AND INSTALLATION OF CONCRETE SLEEPERS AT CX-3, CX-4, CX-5 & CX-6 BY JAYA PEARL VESSEL | 2207-NN-0138 | AD162-562-PL-62280 | A | 2 | 2014-08-25 |  | -157 | CSE-OF-2207-106 | 2015-01-29 | 2207-NPCC-AO-T-02112 | 2015-02-01 | TR-UFFDP1-13-04788 | 2015-02-03 | 2 | 2207-NPCC-MWS-T-00451 | 2015-02-03 | GM-60295-0617 | 2015-02-16 | ACCEPTED | -
|  |  |  | B | - | - |  | - | CSE-OF-2207-107 | 2015-02-11 | 2207-NPCC-AO-T-02185 | 2014-02-14 |  |  |  | 2207-NPCC-MWS-T-00455 | 2015-02-16 |  |  |  | CLIENT/MWS
281 | LIFTING AND INSTALLATION OF MATTRESSES(TYPICAL) | 2207-NN-0139 | AD162-562-PL-62281 |  | 2 | 2014-08-30 |  | -2181
282 | DETAIL OF 16" TEMPORARY PIG LAUNCHER & RECEIVER 16" WELL FLUID PIPELINE FROM ULRP TO WHT-3 | 2207-NN-0140 | AD162-476/573-PL-62282 | A | 3 | - |  | - | CSE-OF-2207-047 | 2014-09-10 | 2207-NPCC-AO-T-01438 | 2014-09-11 | TR-UFFDP1-13-04235 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00320 | 2014-09-11 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
283 | DETAIL OF 10" TEMPORARY PIG LAUNCHER & RECEIVER 10" WATER INJECTION PIPELINE FROM ULRP TO WHT-3 | 2207-NN-0141 | AD162-476/573-PL-62283 | A | 3 | - |  | - | CSE-OF-2207-047 | 2014-09-10 | 2207-NPCC-AO-T-01438 | 2014-09-11 | TR-UFFDP1-13-04235 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00320 | 2014-09-11 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
284 | DETAIL OF 8" TEMPORARY PIG LAUNCHER & RECEIVER 8" GAS INJECTION PIPELINE FROM ULRP TO WHT-3 | 2207-NN-0142 | AD162-476/573-PL-62284 | A | 3 | - |  | - | CSE-OF-2207-048 | 2014-09-10 | 2207-NPCC-AO-T-01448 | 2014-09-12 | TR-UFFDP1-13-03834 | 2014-09-15 | Information | 2207-NPCC-MWS-T-00328 | 2014-09-16 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
285 | DETAIL OF 6" TEMPORARY PIG LAUNCHER & RECEIVER 6" GAS LIFT PIPELINE FROM ULRP TO WHT-3 | 2207-NN-0143 | AD162-476/573-PL-62285 | A | 3 | - |  | - | CSE-OF-2207-048 | 2014-09-10 | 2207-NPCC-AO-T-01448 | 2014-09-12 | TR-UFFDP1-13-03834 | 2014-09-15 | Information | 2207-NPCC-MWS-T-00328 | 2014-09-16 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
286 | DETAIL OF 6" TEMPORARY PIG LAUNCHER & RECEIVER 6" GAS LIFT PIPELINE FROM WHT-3 TO WHT-1 | 2207-NN-0144 | AD162-474/476-PL-62286 | A | 3 | - |  | - | CSE-OF-2207-051 | 2014-09-11 | 2207-NPCC-AO-T-01451 | 2014-09-12 | TR-UFFDP1-13-04240 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00333 | 2014-09-16 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
287 | DETAIL OF 10" TEMPORARY PIG LAUNCHER & RECEIVER 10" WATER INJECTION PIPELINE FROM WHT-3 TO WHT-1 | 2207-NN-0145 | AD162-474/476-PL-62287 | A | 3 | - |  | - | CSE-OF-2207-051 | 2014-09-11 | 2207-NPCC-AO-T-01451 | 2014-09-12 | TR-UFFDP1-13-04240 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00333 | 2014-09-16 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
288 | DETAIL OF 16" TEMPORARY PIG LAUNCHER & RECEIVER 16" WELL FLUID PIPELINE FROM WHT-3 TO WHT-1 | 2207-NN-0146 | AD162-474/476-PL-62288 | A | 3 | - |  | - | CSE-OF-2207-051 | 2014-09-11 | 2207-NPCC-AO-T-01451 | 2014-09-12 | TR-UFFDP1-13-04240 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00333 | 2014-09-16 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
289 | DETAIL OF 6" TEMPORARY PIG LAUNCHER & RECEIVER 6" GAS LIFT PIPELINE FROM ULRP TO WHT-5 | 2207-NN-0147 | AD162-573/480-PL-62289 | A | 3 | - |  | - | CSE-OF-2207-058 | 2014-09-15 | 2207-NPCC-AO-T-01469 | 2014-09-18 | TR-UFFDP1-13-04238 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00346 | 2014-09-21 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
290 | DETAIL OF 10" TEMPORARY PIG LAUNCHER & RECEIVER 10" WATER INJECTION PIPELINE FROM ULRP TO WHT-5 | 2207-NN-0148 | AD162-573/480-PL-62290 | A | 3 | - |  | - | CSE-OF-2207-058 | 2014-09-15 | 2207-NPCC-AO-T-01469 | 2014-09-18 | TR-UFFDP1-13-04238 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00346 | 2014-09-21 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
291 | DETAIL OF 16" TEMPORARY PIG LAUNCHER & RECEIVER 16" WELL FLUID PIPELINE FROM ULRP TO WHT-5 | 2207-NN-0149 | AD162-573/480-PL-62291 | A | 3 | - |  | - | CSE-OF-2207-058 | 2014-09-15 | 2207-NPCC-AO-T-01469 | 2014-09-18 | TR-UFFDP1-13-04238 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00346 | 2014-09-21 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
292 | DETAIL OF 6" TEMPORARY PIG LAUNCHER & RECEIVER 6" GAS LIFT PIPELINE FROM WHT-5 TO WHT-2 | 2207-NN-0150 | AD162-480/475-PL-62292 | A | 3 | - |  | - | CSE-OF-2207-058 | 2014-09-15 | 2207-NPCC-AO-T-01469 | 2014-09-18 | TR-UFFDP1-13-04238 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00346 | 2014-09-21 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
293 | DETAIL OF 10" TEMPORARY PIG LAUNCHER & RECEIVER 10" WATER INJECTION PIPELINE FROM WHT-5 TO WHT-2 | 2207-NN-0151 | AD162-480/475-PL-62293 | A | 3 | - |  | - | CSE-OF-2207-058 | 2014-09-15 | 2207-NPCC-AO-T-01469 | 2014-09-18 | TR-UFFDP1-13-04238 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00346 | 2014-09-21 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
294 | DETAIL OF 16" TEMPORARY PIG LAUNCHER & RECEIVER 16" WELL FLUID PIPELINE FROM WHT-5 TO WHT-2 | 2207-NN-0152 | AD162-480/475-PL-62294 | A | 3 | - |  | - | CSE-OF-2207-058 | 2014-09-15 | 2207-NPCC-AO-T-01469 | 2014-09-18 | TR-UFFDP1-13-04238 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00346 | 2014-09-21 | GM-60295-0495 | 2014-09-29 | ACCEPTED | -
295 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS @ MARCAP (TRIP-3) (Campaign-1) | 2207-NN-0153 | AD162-562-PL-62295 | A | 3 | - |  | - | CSE-OF-2207-088 | 2014-10-29 | 2207-NPCC-AO-T-01741 | 2014-10-30 | TR-UFFDP1-13-04122 | 2014-11-04 | ACCEPTED | 2207-NPCC-MWS-T-00414 | 2014-11-01 | GM-60295-0560 | 2014-10-30 | ACCEPTED | -
296 | LOADING ARRG'T & SEAFASTENING DETAILS OF RISERS, SPOOLS & FENDER @ GOGAS-252 (TRIP-4) | 2207-NN-0154 | AD162-562-PL-62296 | A | 3 |  |  |  | CSE-OF-2207-091 | 2014-11-03 | 2207-NPCC-AO-T-01760 | 2014-11-04 | TR-UFFDP1-13-04176 | 2014-11-10 | ACCEPTED | 2207-NPCC-MWS-T-00419 | 2014-11-05 | GM-60295-0575 | 2014-11-11 | ACCEPTED | -
|  |  |  | B | - | - |  | - | CSE-OF-2207-094 | 2014-11-09 | 2207-NPCC-AO-T-01789 | 2014-11-10 | TR-UFFDP1-13-04228 | 2014-11-16 | ACCEPTED | 2207-NPCC-MWS-T-00422 | 2014-11-11 | GM-60295-0575 | 2014-11-11 | ACCEPTED | -
297 | LIFTING AND INSTALLATION OF CORAL BREAKER BY JAYA PEARL | 2207-NN-1142 | AD197-473-PL-62280 | A | 3 | Chirag |  | - | CSE-OF-2207-111 | 2015-03-29 | 2207-NPCC-AO-T-02425 | 2015-04-09 | TR-UFFDP1-13-05237 | 2015-04-12 | 1 | 2207-NPCC-MWS-T-00479 | 2015-04-13 | GM-60295-0655 | 2015-04-19 | A | -
298 | DETAIL OF 16" TEMPORARY PIG LAUNCHER & RECEIVER 16" WELL FLUID PIPELINE FROM WHT-8 TO WHT-7 | 2207-NN-1143 | AD197-482/483-PL-62281 | A | 3 | Hiresh |  | - | CSE-OF-2207-114 | 2015-04-15 | 2207-NPCC-AO-T-02530 | 2015-04-29 | TR-UFFDP1-13-05474 | 2015-05-17 | 2 | 2207-NPCC-MWS-T-00488 | 2015-05-13 |  |  | I | MWS For Info only
299 | DETAIL OF 6" TEMPORARY PIG LAUNCHER & RECEIVER 6" GAS LIFT PIPELINE FROM WHT-8 TO WHT-7 | 2207-NN-1144 | AD197-482/483-PL-62282 | A | 3 | Hiresh |  | - | [11 empty] | I | CLIENT/MWS For Info only
300 | DETAIL OF 10" TEMPORARY PIG LAUNCHER & RECEIVER 10" WATER INJECTION PIPELINE FROM WHT-8 TO WHT-7 | 2207-NN-1145 | AD197-482/483-PL-62283 | A | 3 | Hiresh |  | - | [11 empty] | I | CLIENT/MWS For Info only
301 | DETAIL OF 16" TEMPORARY PIG LAUNCHER & RECEIVER 16" WELL FLUID PIPELINE FROM WHT-7 TO ULRP | 2207-NN-1146 | AD197-573/482-PL-62284 | A | 3 | Hiresh |  | - | [11 empty] | I | CLIENT/MWS For Info only
302 | DETAIL OF 6" TEMPORARY PIG LAUNCHER & RECEIVER 6" GAS LIFT PIPELINE FROM WHT-7 TO ULRP | 2207-NN-1147 | AD197-573/482-PL-62285 | A | 3 | Hiresh |  | - | [11 empty] | I | CLIENT/MWS For Info only
303 | DETAIL OF 10" TEMPORARY PIG LAUNCHER & RECEIVER 10" WATER INJECTION PIPELINE FROM WHT-7 TO ULRP | 2207-NN-1148 | AD197-573/482-PL-62286 | A | 3 | Hiresh |  | - | [11 empty] | I | CLIENT/MWS For Info only
304 | DETAIL OF 6" TEMPORARY PIG LAUNCHER & RECEIVER 6" GAS LIFT PIPELINE FROM WHT-6 TO ULRP | 2207-NN-1149 | AD197-481/573-PL-62287 | A | 3 | Hiresh |  | - | [11 empty] | I | CLIENT/MWS For Info only
305 | DETAIL OF 18" TEMPORARY PIG LAUNCHER & RECEIVER 18" WELL FLUDID PIPELINE FROM WHT-6 TO ULRP | 2207-NN-1150 | AD197-481/573-PL-62288 | A | 3 | Hiresh |  | - | [11 empty] | I | CLIENT/MWS For Info only
306 | DETAIL OF 8" TEMPORARY PIG LAUNCHER & RECEIVER 8" GAS INJECTION PIPELINE FROM WHT-6 TO ULRP | 2207-NN-1151 | AD197-481/573-PL-62289 | A | 3 | Hiresh |  | - | [11 empty] | I | CLIENT/MWS For Info only
307 | DETAIL OF 10" TEMPORARY PIG LAUNCHER & RECEIVER 10" WATER INJECTION PIPELINE FROM WHT-6 TO ULRP | 2207-NN-1152 | AD197-481/573-PL-62290 | A | 3 | Hiresh |  | - | [11 empty] | I | CLIENT/MWS For Info only
308 | DETAIL OF 6" TEMPORARY PIG LAUNCHER & RECEIVER 6" GAS LIFT PIPELINE FROM WHT-6 TO WHT-4 | 2207-NN-1153 | AD197-481/477-PL-62291 | A | 3 | Hiresh |  | - | [11 empty] | I | CLIENT/MWS For Info only
309 | DETAIL OF 10" TEMPORARY PIG LAUNCHER & RECEIVER 10" WATER INJECTION PIPELINE FROM WHT-6 TO WHT-4 | 2207-NN-1154 | AD197-481/477-PL-62292 | A | 3 | Hiresh |  | - | [11 empty] | I | CLIENT/MWS For Info only
310 | LOADING ARRANGEMENT OF CHEMICAL INJECTION PACKAGE @ KINGFISHER (TRIP-1) | 2207-NN-1155 | AD197-473-PL-62293 | A | 3 | Reyashi |  | - | CSE-OF-2207-131 | 2015-06-18 | 2207-NPCC-AO-T-02910 | 2015-06-21 | TR-UFFDP1-13-05712 | 2015-06-25 | 2 | 2207-NPCC-MWS-T-00509 | 2015-06-21 | GM-60295-0687 | 2015-06-22 | A | -
|  |  |  | CRS | - | - | - | - | CSE-OF-2207-250 | 07-15-15 | 2207-NPCC-AO-T-04025 | 2015-12-09 | TR-UFFDP1-13-06800 | 2016-01-03 | 1 | 2207-NPCC-MWS-T-00724 | 2015-12-17 |  |  |  | -
311 | 1600mm RADIUS THIMBLE 20" MOL PIPELINE | 2207-NN-1156 | AD197-473-PL-62294 | A | 3 | Chirag |  | - | CSE-OF-2207-115 | 2015-07-14 | 2207-NPCC-AO-T-03044 | 2015-07-15 | TR-UFFDP1-13-05930 | 2015-08-04 | 2 | 2207-NPCC-MWS-T-00534 | 2015-07-19 |  |  |  | For Info only
312 | CHEMICAL INJECTION PACKAGE LOADING ARRANGEMENT @ TRUE GRIT | 2207-NN-1157 | AD197-473-PL-62295 | A | 3 | Hiresh |  | - | CSE-OF-2207-159 | 2015-07-28 | 2207-NPCC-AO-T-03101 | 2015-07-29 |  |  |  | 2207-NPCC-MWS-T-00549 | 2015-07-29 |  |  |  | CLIENT/MWS For Info only
313 | CHEMICAL INJECTION PACKAGE LOADING ARRANGEMENT @ TRUE GRIT (TRIP-2) | 2207-NN-1158 | AD197-473-PL-62296 | A | 3 | Hiresh |  | - | CSE-OF-2207-160 | 2015-07-30 | 2207-NPCC-AO-T-03106 | 2015-07-30 |  |  |  | 2207-NPCC-MWS-T-00550 | 2015-07-30 |  |  |  | CLIENT/MWS For Info only
314 | INSTALLATION OF RISER PROTECTORS AT ULRP (ROW-1) | 2207-NN-0155 | AD197-573-PL-62297 | A | - | Hiresh |  | - | CSE-OF-2207-219 | 2015-09-08 | 2207-NPCC-AO-T-03442 | 2015-09-09 | TR-UFFDP1-13-06162 | 2015-09-15 | 1 | 2207-NPCC-MWS-T-00629 | 2015-09-10 | GM-60295-0812 | 2015-09-15 | A | -
315 | DETAIL OF 20” TEMPORARY PIG LAUNCHER & RECIEVER FROM ULRP TO ZIRKU ISLAND | 2207-NN-1159 | AD197-573/602-PL-62298 | A |  |  |  |  | CSE-OF-2207-227 | 2015-09-13 | 2207-NPCC-AO-T-03496 | 2015-09-14 |  |  |  | 2207-NPCC-MWS-T-00636 | 2015-09-15 | GM-60295-0822 | 2015-09-20 | A | CLIENT
|  |  |  | B |  |  |  |  | CSE-OF-2207-244 | 2015-10-08 | 2207-NPCC-AO-T-03700 | 2015-10-12 | TR-UFFDP1-13-06370 | 2015-10-13 | 1 | 2207-NPCC-MWS-T-00674 | 2015-10-08 |  |  | Approved in previous Rev | MWS
316 | INSTALLATION OF EXISTING RISER PROTECTOR AT WHT-4 (ROW-A) | 2207-NN-0156 | AD197-477-PL-62299 | A | - | - |  |  | CSE-OF-2207-231 | 2015-09-17 | 2207-NPCC-AO-T-03544 | 2015-09-20 | TR-UFFDP1-13-06309 | 2015-10-04 | 2 | 2207-NPCC-MWS-T-00646 | 2015-09-21 |  |  |  | MWS
|  |  |  | 0 |  |  |  |  | CSE-OF-2207-239 | 2015-09-29 | 2207-NPCC-AO-T-03623 | 2015-09-30 | TR-UFFDP1-13-06317 | 2015-10-04 | 2 | 2207-NPCC-MWS-T-00662 | 2015-10-01 |  |  |  | MWS
|  |  |  | 1 |  |  |  |  | CSE-OF-2207-243 | 2015-10-06 | 2207-NPCC-AO-T-03688 | 2015-10-08 | TR-UFFDP1-13-06365 | 2015-10-13 | 2 | 2207-NPCC-MWS-T-00672 | 2015-10-12 | GM-60295-0837 | 2015-10-13 | A | -
|  |  |  | 2 |  |  |  |  | CSE-OF-2207-246 | 2015-11-22 | 2207-NPCC-AO-T-03984 | 2015-11-23 | TR-UFFDP1-13-06643 | 2015-11-25 | 1 | 2207-NPCC-MWS-T-00710 | 2015-11-24 | GM-60295-0912 | 2015-12-13 | A | -
317 | REMOVAL OF EXISTING STAIRS AT WHT-4 (ROW-A) | 2207-NN-1161 | AD197-477-PL-62300 | A | Anjali added | Chirag |  |  | CSE-OF-2207-239 | 2015-09-29 | 2207-NPCC-AO-T-03622 | 2015-09-30 | TR-UFFDP1-13-06401 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00661 | 2015-10-01 |  |  |  | MWS For Info only
318 | INSTALLTION OF EXISTING STAIRS AT WHT-4 (ROW-A) | 2207-NN-1160 | AD197-477-PL-62301 | A | Anjali added | Chirag |  |  | CSE-OF-2207-239 | 2015-09-29 | 2207-NPCC-AO-T-03622 | 2015-09-30 | TR-UFFDP1-13-06401 | 2015-10-20 | 1 | 2207-NPCC-MWS-T-00661 | 2015-10-01 |  |  |  | MWS For Info only
319 | SHIFTING OF CS2 CONCRETE SLEEPER @ CROSSING NO. 10 BY SWIBER ATLANTIS | 2207-NN-1162 | AD197-477-PL-62302 | A |  |  |  |  | CSE-OF-2207-257 | 31-15-15 | 2207-NPCC-AO-T-04162 | 2016-01-06 | TR-UFFDP1-13-06833 | 2016-01-10 | 2 | 2207-NPCC-MWS-T-00736 | 2016-01-07 | GM-60295-929 | 2016-01-11 | B | For Info only
|  |  |  | B |  |  |  |  | CSE-OF-2207-261 | 2016-01-13 | 2207-NPCC-AO-T-04199 | 2016-01-14 | TR-UFFDP1-13-06886 | 2016-01-24 | 1 | 2207-NPCC-MWS-T-00742 | 2016-01-16 | GM-60295-0933 | 2016-01-17 | A | For Info only
320 | REMOVAL OF EXISTING STAIRS AT WHT-6 (ROW-2) | 2207-NN-1163 | AD197-477-PL-62303 | A |  |  |  |  | CSE-OF-2207-264 | 2016-02-04 | 2207-NPCC-AO-T-04313 | 2016-02-08 | TR-UFFDP1-13-07092 | 2016-03-02 | 2 | 2207-NPCC-MWS-T-00751 | 2016-02-09 |  |  |  | MWS
321 | REINSTLLATION OF EXISTING STAIRS AT WHT-6 (ROW-2) | 2207-NN-1164 | AD197-477-PL-62304 | A |  |  |  |  | CSE-OF-2207-264 | 2016-02-04 | 2207-NPCC-AO-T-04313 | 2016-02-08 | TR-UFFDP1-13-07092 | 2016-03-02 | 2 | 2207-NPCC-MWS-T-00751 | 2016-02-09 |  |  |  | MWS
322 | RE-INSTALLATION OF EXISTING RISER PROTECTOR AT WHT-6 | 2207-NN-1165 | AD197-481-PL-62305 | A |  |  |  |  | CSE-OF-2207-265 | 2016-02-07 | 2207-NPCC-AO-T-04320 | 2016-02-11 | TR-UFFDP1-13-07166 | 2016-03-15 | 2 | 2207-NPCC-MWS-T-00754 | 2015-02-11 |  |  |  | MWS
323 | PIPELINE REPAIR WORKS 10" WATER INJECTION PIPELINE FROM ULRP TO WHT-6 @ WHT-6 | 2207-NN-1172 | AD197-477-PL-62312 |  |  |  |  | REY
324 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR GANGWAY AT UL FIELD - WELLHEAD TOWER - 1, 3 & 5 | 2207-NN-1173 | AD162-562-PL-62282 | A |  | not under yahia |  | HZD | CSE-OF-2207-298 | 2017-09-18 | 2207-NPCC-AO-T-06069 | 2017-09-20 | TR-UFFDP1-13-08845 | 2018-01-30 | 1 | 2207-NPCC-MWS-T-00973 | 2017-09-19 |  |  |  | drg. # given by engg. On email dtd. 06/09/17 (stany)
325 | TYPICAL LIFTING AND INSTALLATION FOR TEMPORARY DG AT UL FIELD - WELLHEAD TOWER - 1, 3 & 5 | 2207-NN-1174 | AD162-562-PL-62283 |  |  | not under yahia |  | HZD
326 | LIFTING ARRANGEMENT OF MOV203 VALVE AT WHT-1 | 2207-NN-1175 | AD162-474-PL-62284 |  |  | REY
Formulas:
REMAINING DAYS = [SUBMISSION PLAN]-TODAY()
SUBMISSION PLAN = [SUBMISSION PLAN, row above]+3