## Documents - Pipeline & Cable
|  | SAUDI ARABIAN OIL COMPANY | [10 empty] | NPCC DOC. No.:
CRPO # 86 FOR JAFURAH DEVELOPMENT PROGRAM CONDENSATE TERMINAL BI-10-14244
|  | NPCC PROJECT NO. 2412-2413 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ARAMCO | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPELAY ANALYSIS REPORT FOR 48" PIPELINE BY DELMA-2000 | 2412-2413-NN-RP-001 | A | 2 |  | 2024-07-31 | CSE-2412-2413-PMT-T-010 | 2024-08-15 | 2412-2413-NPCC-T-06593 | 2024-08-28 | CPD-14244-SA-T-2073-24 | 4
|  |  | B |  |  | 2024-09-26 | CSE-2412-2413-PMT-T-034 | 2024-09-27 | 2412-2413-NPCC-T-07038 | 2024-10-15 | CPD-14244-SA-T-2499-24 | 6 | [5 empty] | CODE; 6-NO OBJECTION
|  |  | 00 | 3 |  | 2024-12-01 | CSE-2412-2413-PMT-T-054 | 2024-12-07 | 2412-2413-NPCC-T-07734
2 | PIPE STACKING ANALYSIS REPORT | 2412-2413-NN-RP-002 | A | 2 |  | 2024-08-05 | CSE-2412-2413-PMT-T-0011 | 2024-08-15 | 2412-2413-NPCC-T-06593 | 2024-08-22 | CPD-14244-SA-T-1998-24 | 4 | [5 empty] | Hold (email from PM 14/08)
3 | PIPELAY ANALYSIS REPORT FOR 56" PIPELINE FROM ONSHORE TANK FARM TO JOP | 2412-2413-NN-RP-003 | A | 2 |  | 2024-11-01 | CSE-2412-2413-PMT-T-041 | 2024-11-03 | 2412-2413-NPCC-T-07414 | 2024-11-12 | CPD-14244-SA-T-2725-24 | 4
|  |  | B | 2 |  | 2024-11-22 | CSE-2412-2413-PMT-T-052 | 2024-11-25 | 2412-2413-NPCC-T-07632 | 2024-11-27 | CPD-14244-SA-T-2887-24 | 4 |  |  |  | DRC_DU3914-2412-2413-NN-RP-003
|  |  | 00 | 2 |  | 2024-12-17 | CSE-2412-2413-PMT-T-061
4 | SPARE | 2412-2413-NN-RP-004
5 | PIPELAY ANALYSIS REPORT FOR 48" PIPELINE FROM JOP TO SSVS (SECTION A & B) | 2412-2413-NN-RP-005
6 | PIPELAY ANALYSIS REPORT FOR 48" PIPELINES FROM SSVS TO PLEM | 2412-2413-NN-RP-006
7 | SHOREPULL ANALYSIS REPORT FOR 56" PIPELINE AT ONSHORE TANK FARM | 2412-2413-NN-RP-007 | A | 2 |  | 2024-09-26 | CSE-2412-2413-PMT-T-033 | 2024-09-27 | 2412-2413-NPCC-T-07037 | 2024-10-11 | CRM-4045529805
|  |  | B | 2 |  | 2024-11-22 | CSE-2412-2413-PMT-T-053 | 2024-11-22 | 2412-2413-NPCC-T-07621 | 2024-11-25 | CPD-14244-SA-T-2859-24 | 4
8 | LIFTING ANALYSIS FOR SPOOLS AT JOP NEW EXTENSION | 2412-2413-NN-RP-008
9 | LIFTING ANALYSIS FOR SPOOLS AT SSVS | 2412-2413-NN-RP-009
10 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESS ON MICLYN-259 (TRIP-1) | 2412-2413-NN-RP-010 | A | 2 |  | 2024-06-26 | CSE-2412-2413-PMT-T-003 | [7 empty] | 2024-08-22 | MDDXB 6036-MD-11-1309-01
11 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS (Trip-2) | 2412-2413-NN-RP-011
12 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS (TRIP-1) | 2412-2413-NN-RP-012
13 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS ON EOS-281 | 2412-2413-NN-RP-013 | A | 2 |  | 2024-12-19 | CSE-2412-2413-PMT-T-060 | [5 empty] | 2025-01-02 | 2412-2413-PMT-MWS-T-0012 | 2025-01-14 | MDDXB 6036-MD-30-1332-01 | 1
14 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS (TRIP-3) | 2412-2413-NN-RP-014
15 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON GAC-82 (TRIP-1) | 2412-2413-NN-RP-015 | A | 2 |  | 2024-07-24 | CSE-2412-2413-PMT-T-007 | 2024-08-15 | 2412-2413-NPCC-T-06590 |  |  |  | 2024-08-15 | 2412-2413-PMT-MWS-T-0001 | 2024-08-22 | MDDXB 6036-MD-11-1304-01
16 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-2) | 2412-2413-NN-RP-016
17 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-3) | 2412-2413-NN-RP-017
18 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-4) | 2412-2413-NN-RP-018
19 | INSTALLATION ANALYSIS REPORT FOR 15KV CABLE | 2412-2413-NN-RP-019 | A | 2 |  | 2025-01-23 | CSE-2412-2413-PMT-T-071 | 2025-02-04 | 2412-2413-NPCC-T-08145 | 2025-03-05 | CPD-14244-SA-T-0505-25 | 2
|  |  | B | 2 |  | 2025-05-08 | CSE-2412-2413-PMT-T-094 | 2025-05-09 | 2412-2413-NPCC-T-08894 | 2025-05-13 | CPD-14244-SA-T-1213-25 | 4
20 | SEAFASTENING DESIGN REPORT FOR ASTRO-301 WITH CONSTRUCTION EQUIPMENT | 2412-2413-NN-RP-020 | A | 2 |  | 2024-08-12 | CSE-2412-2413-PMT-T-014 | 2024-08-15 | 2412-2413-NPCC-T-06590 |  |  |  | 2024-08-15 | 2412-2413-PMT-MWS-T-0001
21 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON MICLYN-258 (TRIP-2) | 2412-2413-NN-RP-021 | A | 2 |  | 2024-08-23 | CSE-2412-2413-PMT-T-019 | 2024-08-23 | 2412-2413-NPCC-T-06590 |  |  |  | 2024-08-23 | 2412-2413-PMT-MWS-T-0001
|  |  | B | 2 |  | 2024-08-30 | CSE-2412-2413-PMT-T-023
22 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON MICLYN-259 (TRIP-3) | 2412-2413-NN-RP-022 | A | 2 |  | 2024-08-27 | CSE-2412-2413-PMT-T-021
|  |  | B | 2 |  | 2024-09-02 | CSE-2412-2413-PMT-T-024 | [5 empty] | 2024-09-30 | 2412-2413-PMT-MWS-0002 | 17-10-2024 | MDDXB 6036-MD-21-1313-01 | approved
23 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON EOS-285 (TRIP-4) | 2412-2413-NN-RP-023 | A | 2 |  | 2024-09-10 | CSE-2412-2413-PMT-T-025
|  |  | B | 2 |  | 2024-10-21 | CSE-2412-2413-PMT-T-037 | [5 empty] | 2024-10-26 | 2412-2413-PMT-MWS-0005 | 2024-10-26 | MDDXB 6036-MD-23-1322-01 | approved
24 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF STINGER-9A & PROJECT MATERIALS OF DLS-4200 @ CB-8 | 2412-2413-NN-RP-024 | A | 2 |  | 2024-11-05 | CSE-2412-2413-PMT-T-042
25 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF 56 INCH CC PIPES ON MICLYN-288 (TRIP-1) | 2412-2413-NN-RP-025 | A | 2 |  | 2054-01-14 | CSE-2412-2413-PMT-T-068 | [5 empty] | 2025-01-15 | 2412-2413-PMT-MWS-T-0014 | 2025-01-19 | MDDXB 6036-MD-32-1336-01 | approved
26 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF 56 INCH CC PIPES ON GOGAS-252 (TRIP-2) | 2412-2413-NN-RP-026 | A | 2 |  | 2025-01-20 | CSE-2412-2413-PMT-T-069
27 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF 56 INCH CC PIPES ON AESEN-2803 (TRIP-3) | 2412-2413-NN-RP-027 | A | 2 |  | 2025-01-31 | CSE-2412-2413-PMT-T-072
28 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF 56 INCH CC PIPES ON CASPIAN-280 (TRIP-4) | 2412-2413-NN-RP-028 | A | 2 |  | 2025-02-20 | CSE-2412-2413-PMT-T-078
29 | Transpooling Analysis Report for 15kV Cable | 2412-2413-NN-RP-029 | A | 2 |  | 2025-02-14 | CSE-2412-2413-PMT-T-074 | 2025-05-14 | 2412-2413-NPCC-T-08932 |  |  |  | 2025-05-14 | 2412-2413-PMT-MWS-T-0018 | 2025-05-16 | MDDXB 6036-MD-49-1211-01 | approved
30 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF 56 INCH CC PIPES ON GOGAS-250 (TRIP-5) | 2412-2413-NN-RP-030 | A | 2 |  | 2025-02-20 | CSE-2412-2413-PMT-T-079
| SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS ON GOGAS-252 (TRIP-2) | 2412-2413-NN-RP-031 | A | 3 |  | 2025-05-30 | CSE-2412-2413-PMT-T-096

## Documents - Naval Marine
|  | SAUDI ARABIAN OIL COMPANY | [10 empty] | NPCC DOC. No.:
CRPO # 86 FOR JAFURAH DEVELOPMENT PROGRAM CONDENSATE TERMINAL BI-10-14244
|  | NPCC PROJECT NO. 2412-2413 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (Naval Marine) | [10 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ARAMCO | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | CHUANG LI MOORING ANALYSIS DURING INSTALLATION OF JOP NEW EXTENSION TOPSIDE | 2412-2413-ZZ-CL-001 | A | 2 |  | 2025-12-29 | CSE-2412-2413-PMT-T-106 | [5 empty] | 2025-12-29 | 2412-2413-PMT-MWS-T-0020 | 2025-01-02 | MDDXB 6036-MD-60-402-01 | comments
|  |  | B | 2 |  | 2026-01-13 | CSE-2412-2413-PMT-T-107 | [5 empty] | 2026-01-14 | 2412-2413-PMT-MWS-T-0021 | 2025-01-21 | MDDXB 6036-MD-60-402-02 | comments
|  |  | CRS | [9 empty] | 2026-01-23 | sent to pmt | 2025-02-10 | MDDXB 6036-MD-60-402-01 MDDXB 6036-MD-60-402-04 | Approved | M.ASH - sent to PMT on 23/01/26
2 | MOORING ANALYSIS DURING LAYING OF 56" PIPELINE FROM ONSHORE TANK FARM TO SSVS | 2412-2413-ZZ-CL-002
3 | MOORING ANALYSIS DURING LAYING OF 56" PIPELINE FROM JOP TO SSVS | 2412-2413-ZZ-CL-003
4 | MOORING ANALYSIS DURING LAYING OF 48" PIPELINE FROM JOP TO SSVS | 2412-2413-ZZ-CL-004
5 | STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS ON EOS-281 (Trip-1) | 2412-2413-ZZ-CL-005 | A | 2 |  | 2025-01-02 | CSE-2412-2413-PMT-T-064 | [5 empty] | 2025-01-02 | 2412-2413-PMT-MWS-T-0012 | 2025-01-16 | MDDXB 6036-MD-31-1334-01 | Approved
6 | STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS ON GOGAS-252 (TRIP-2) | 2412-2413-ZZ-CL-006 | A | 2 |  | 2025-05-30 | CSE-2412-2413-PMT-T-096
7 | STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS (Trip-3) | 2412-2413-ZZ-CL-007
8 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES ON MICLYN-259 (TRIP-1) | 2412-2413-ZZ-CL-008 | A | 2 |  | 2024-06-26 | CSE-2412-2413-PMT-T-003
9 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS (TRIP-2) | 2412-2413-ZZ-CL-009
10 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPE ON GAC-82 (TRIP-1) | 2412-2413-ZZ-CL-010 | A | 2 |  | 2024-07-24 | CSE-2412-2413-PMT-T-007 | 2024-08-15 | 2412-2413-NPCC-T-06590 |  |  |  | 2024-08-15 | 2412-2413-PMT-MWS-T-0001
11 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE COATED PIPES ON MICLYN-258 (TRIP-2) | 2412-2413-ZZ-CL-011 | A | 2 |  | 2024-08-22 | CSE-2412-2413-PMT-T-017
|  |  | B | 2 |  | 2024-08-30 | CSE-2412-2413-PMT-T-023
12 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE COATED PIPES ON MICLYN-259 (TRIP-3) | 2412-2413-ZZ-CL-012 | A | 2 |  | 2024-08-27 | CSE-2412-2413-PMT-T-021
|  |  | B | 2 |  | 2024-09-02 | CSE-2412-2413-PMT-T-024 | [5 empty] | 2024-09-30 | 2412-2413-PMT-MWS-0002 | 2024-10-17 | MDDXB 6036-MD-20-1314-01 - | Approved
13 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE COATED PIPES ON EOS-285 (TRIP-4) | 2412-2413-ZZ-CL-013 | A | 2 |  | 2024-09-10 | CSE-2412-2413-PMT-T-025
|  |  | B | 2 |  | 2024-10-21 | CSE-2412-2413-PMT-T-037 | [5 empty] | 2024-10-26 | 2412-2413-PMT-MWS-0005 | 2024-10-26 | MDDXB 6036-MD-22-1321-01 | Approved
14 | UMM SHAIF MOORING ANALYSIS AT CABLE STARTUP | 2412-2413-ZZ-CL-014 | A | 2 |  | 2024-07-04 | CSE-2412-2413-PMT-T-005
|  |  | B | 2 |  | 2024-11-21 | CSE-2412-2413-PMT-T-051 | [5 empty] | 2025-03-26 | 2412-2413-PMT-MWS-0016 | 2025-04-04 | MDDXB 6036-MD-48-1404-01 | comments
|  |  | CRS | [9 empty] | 2024-04-09 | mws's response sent to pmt (HZ) | 2024-04-11 | MDDXB 6036-MD-48-1404-02 | Approved
15 | STABILITY ANALYSIS REPORT FOR ASTRO-301 WITH CONSTRUCTION EQUIPMENTS ONBOARD | 2412-2413-ZZ-CL-015 | A | 2 |  | 2024-08-12 | CSE-2412-2413-PMT-T-013
16 | DLS 4200 MOORING ANALYSIS SHORE PULL AND LAYING 56IN PL | 2412-2413-ZZ-CL-016 | A | 2 |  | 2024-09-18 | CSE-2412-2413-PMT-T-031
|  |  | B | 2 |  | 2024-11-04 | CSE-2412-2413-PMT-T-043 | [5 empty] | 2025-03-25 | 2412-2413-PMT-MWS-0015 | 2025-03-26 | MDDXB 6036-MD-47-1403-01 | comments
|  |  | CRS | [9 empty] | 2025-03-27 | email from PMT - Rashed | 2025-03-27 | MDDXB 6036-MD-47-1403-02 | Approved
17 | DLS 4200 MOORING ANALYSIS SHORE STARTUP AT JOP 56IN PL | 2412-2413-ZZ-CL-017 | A | 2 |  | 2024-09-18 | CSE-2412-2413-PMT-T-032 | [5 empty] | 2024-10-01 | 2412-2413-PMT-MWS-0003 | 2024-10-15 | MDDXB 6036-MD-19-1401-01 | comments
|  |  | B | 2 |  | 2024-10-16 | CSE-2412-2413-PMT-T-038 | [5 empty] | 2024-10-17 | Email from PMT | 2024-10-18 | MDDXB 6036-MD-19-1401-02 | Approved
|  |  | C | 2 |  | 2024-11-11 | CSE-2412-2413-PMT-T-049 | [5 empty] | 2024-11-15 | 2412-2413-PMT-MWS-T-0007 | 2024-11-18 | MDDXB 6036-MD-19-1401-03 | Approved
18 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE COATED PIPES ON MICLYN-288 (TRIP-6) | 2412-2413-ZZ-CL-018
19 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF PROJECT MATERIALS ON CB-8 | 2412-2413-ZZ-CL-019 | A | 2 |  | 2024-11-05 | CSE-2412-2413-PMT-T-042
|  |  | B | 2 |  | 2024-12-25 | CSE-2412-2413-PMT-T-062 | [5 empty] | 2024-12-26 | 2412-2413-PMT-MWS-0010
20 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF 56" CONCRETE COATED PIPES (TRIP-1) | 2412-2413-ZZ-CL-020 | A | 2 |  | 2054-01-14 | CSE-2412-2413-PMT-T-068 | [5 empty] | 2025-01-15 | 2412-2413-PMT-MWS-T-0014 | 2025-01-19 | MDDXB 6036-MD-33-1337-01
21 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE COATED PIPES (TRIP-2) | 2412-2413-ZZ-CL-021 | A |  |  | 2025-01-20 | CSE-2412-2413-PMT-T-069
22 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF 56" CONCRETE COATED PIPES (TRIP-3) | 2412-2413-ZZ-CL-022 | A |  |  | 2025-01-20 | CSE-2412-2413-PMT-T-070 | [5 empty] | -- | -- | 2025-01-29 | MDDXB 6036-MD-38-1341-01 - | Approved
|  |  | B |  |  | 2025-01-31 | CSE-2412-2413-PMT-T-072
23 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF 56" CONCRETE COATED PIPES (TRIP-4) | 2412-2413-ZZ-CL-023 | A | 2 |  | 2025-02-20 | CSE-2412-2413-PMT-T-078
24 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF 56" CONCRETE COATED PIPES (TRIP-5) | 2412-2413-ZZ-CL-024 | A | 2 |  | 2025-02-20 | CSE-2412-2413-PMT-T-079
25 | STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF 56" CONCRETE COATED PIPES (TRIP-6) | 2412-2413-ZZ-CL-025

## Drawings
|  | SAUDI ARABIAN OIL COMPANY | [10 empty] | NPCC DOC. No.:
CRPO # 86 FOR JAFURAH DEVELOPMENT PROGRAM CONDENSATE TERMINAL BI-10-14244
|  | NPCC PROJECT NO. 2412-2413 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (DRAWINGS) | [10 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ARAMCO | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | SHOREPULL HEAD FOR 56" PIPELINE | 2412-2413-NN-0001 | A | 3 | remarks | 2024-07-29 | CSE-2412-2413-PMT-T-009 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-006- 29/07
|  |  | B | 3 |  | 2024-09-10 | CSE-2412-2413-PMT-T-026
|  |  | C |  |  | 2022-10-01 | CSE-2412-2413-PMT-T-036
2 | LAYDOWN HEAD FOR 56" PIPELINE | 2412-2413-NN-0002 | A | 3 | remarks | 2024-07-26 | CSE-2412-2413-PMT-T-008 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-005- 26/07
|  |  | B | 3 |  | 2024-09-16 | CSE-2412-2413-PMT-T-029
3 | START UP HEAD FOR 56" PIPELINE | 2412-2413-NN-0003 | A | 3 | remarks | 2024-07-26 | CSE-2412-2413-PMT-T-008 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-005- 26/07
|  |  | B | 3 |  | 2024-09-16 | CSE-2412-2413-PMT-T-029
4 | TYPICAL EMERGENCY LAYDOWN HEAD FOR 56" PIPELINE | 2412-2413-NN-0004 | A | 3 | remarks | 2024-07-26 | CSE-2412-2413-PMT-T-008 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-005- 26/07
|  |  | B | 3 |  | 2024-09-16 | CSE-2412-2413-PMT-T-029
|  |  | C | 3 |  | 2025-03-11 | CSE-2412-2413-PMT-T-082
5 | START UP HEAD FOR 48" PIPELINE | 2412-2413-NN-0005 | A | 3 | remarks | 2024-07-26 | CSE-2412-2413-PMT-T-008 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-005- 26/07
|  |  | B | 3 |  | 2024-08-08 | CSE-2412-2413-PMT-T-012 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-007- 08/08
|  |  | C | 3 |  | 2024-08-30 | CSE-2412-2413-PMT-T-022
6 | LAYDOWN HEAD FOR 48" PIPELINE | 2412-2413-NN-0006 | A | 3 | remarks | 2024-07-26 | CSE-2412-2413-PMT-T-008 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-005- 26/07
|  |  | B | 3 |  | 2024-08-23 | CSE-2412-2413-PMT-T-018
|  |  | C | 3 |  | 2024-08-26 | CSE-2412-2413-PMT-T-020
|  |  | D | 3 |  | 2024-08-30 | CSE-2412-2413-PMT-T-022
7 | TYPICAL EMERGENCY LAYDOWN HEAD FOR 48" PIPELINE | 2412-2413-NN-0007 | A | 3 | remarks | 2024-07-26 | CSE-2412-2413-PMT-T-008 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-005- 26/07
|  |  | B | 3 |  | 2024-08-23 | CSE-2412-2413-PMT-T-018
|  |  | C | 3 |  | 2024-08-30 | CSE-2412-2413-PMT-T-022
8 | TYPICAL BUCKLE DETECTOR DETAIL FOR 56" PIPELINE | 2412-2413-NN-0008 | A | 3 | remarks | 2024-07-26 | CSE-2412-2413-PMT-T-008 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-005- 26/07
|  |  | B | 3 |  | 2024-09-11 | CSE-2412-2413-PMT-T-027
|  |  | C | 3 |  | 2024-10-30 | CSE-2412-2413-PMT-T-040
9 | TYPICAL BUCKLE DETECTOR DETAIL FOR 48" PIPELINE | 2412-2413-NN-0009 | A | 3 | remarks | 2024-07-26 | CSE-2412-2413-PMT-T-008 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-005- 26/07
|  |  | B | 3 |  | 2024-09-11 | CSE-2412-2413-PMT-T-027
10 | TYPICAL LIFTING & INSTALLATION OF CONCRETE SLEEPERS | 2412-2413-NN-0010 | A | 3 |  | 2024-06-21 | CSE-2412-2413-PMT-T-002
|  |  | B | 3 |  | 2024-10-02 | CSE-2412-2413-PMT-T-030
11 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESS @ MICLYN-259 (TRIP-1) | 2412-2413-NN-0011 | A | 3 |  | 2024-06-26 | CSE-2412-2413-PMT-T-003
12 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS (TRIP-2) | 2412-2413-NN-0012
13 | LOADING ARRANGEMENT FOR TRANSPORTATION OF SUBSEA SPOOLS (TRIP-1) | 2412-2413-NN-0013
14 | LOADING ARRANGEMENT FOR TRANSPORTATION OF SUBSEA SPOOLS (TRIP-2) | 2412-2413-NN-0014
15 | SPOOL LIFTING AND INSTALLATION FOR 56" FROM SHORE TO SSVS AT SSVS | 2412-2413-NN-0015 | A | 3 |  | 2025-02-20 | CSE-2412-2413-PMT-T-077
|  |  | B | 3 |  | 2025-03-14 | CSE-2412-2413-PMT-T-083
16 | SPOOL LIFTING AND INSTALLATION FOR 56" FROM JOP TO SSVS AT JOP | 2412-2413-NN-0016 | A | 3 |  | 2025-04-04 | CSE-2412-2413-PMT-T-085 | [10 empty] | Reissuing
17 | SPOOL LIFTING AND INSTALLATION FOR 56" FROM JOP TO SSVS AT SSVS | 2412-2413-NN-0017 | A | 3 |  | 2025-02-20 | CSE-2412-2413-PMT-T-077
|  |  | B | 3 |  | 2025-03-14 | CSE-2412-2413-PMT-T-083
18 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM JOP TO SSVS (SECTION A) AT JOP | 2412-2413-NN-0018 | A | 3 |  | 2025-03-14 | CSE-2412-2413-PMT-T-084
|  |  | 00 | 3 |  | 2025-04-16 | CSE-2412-2413-PMT-T-090
19 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM JOP TO SSVS (SECTION A) AT SSVS | 2412-2413-NN-0019 | A | 3 |  | 2025-02-20 | CSE-2412-2413-PMT-T-077
20 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM JOP TO SSVS (SECTION B) AT JOP | 2412-2413-NN-0020 | A | 3 |  | 2025-03-14 | CSE-2412-2413-PMT-T-084
|  |  | 00 | 3 |  | 2025-04-16 | CSE-2412-2413-PMT-T-090
21 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM JOP TO SSVS (SECTION B) AT SSVS | 2412-2413-NN-0021 | A | 3 |  | 2025-02-20 | CSE-2412-2413-PMT-T-077
22 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM SSVS TO PLEM (SECTION A) AT SSVS | 2412-2413-NN-0022 | A | 3 |  | 2025-02-20 | CSE-2412-2413-PMT-T-077
23 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM SSVS TO PLEM (SECTION A) AT PLEM | 2412-2413-NN-0023 | A | 3 |  | 2025-01-08 | CSE-2412-2413-PMT-T-065
|  |  | 00 | 3 |  | 2025-04-16 | CSE-2412-2413-PMT-T-090
|  |  | '00A | 3 |  | 2025-08-12 | CSE-2412-2413-PMT-T-099
24 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM SSVS TO PLEM (SECTION B) AT SSVS | 2412-2413-NN-0024 | A | 3 |  | 2025-02-20 | CSE-2412-2413-PMT-T-077
|  |  | 00 | 3 |  | 2025-08-12 | CSE-2412-2413-PMT-T-099
25 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM SSVS TO PLEM (SECTION B) AT PLEM | 2412-2413-NN-0025 | A | 3 |  | 2025-01-08 | CSE-2412-2413-PMT-T-065
|  |  | 00 | 3 |  | 2025-04-16 | CSE-2412-2413-PMT-T-090
|  |  | 00A | 3 |  | 2025-08-12 | CSE-2412-2413-PMT-T-099
26 | TEMPORARY KNEE BRACE DETAILS FOR 56" FROM SHORE TO SSVS AT SSVS | 2412-2413-NN-0026
27 | TEMPORARY KNEE BRACE DETAILS FOR 56" FROM JOP TO SSVS AT JOP | 2412-2413-NN-0027
28 | TEMPORARY KNEE BRACE DETAILS FOR 56" FROM JOP TO SSVS AT SSVS | 2412-2413-NN-0028
29 | TEMPORARY KNEE BRACE DETAILS FOR 48" FROM JOP TO SSVS (SECTION A) AT JOP | 2412-2413-NN-0029
30 | TEMPORARY KNEE BRACE DETAILS FOR 48" FROM JOP TO SSVS (SECTION A) AT SSVS | 2412-2413-NN-0030
31 | TEMPORARY KNEE BRACE DETAILS FOR 48" FROM JOP TO SSVS (SECTION B) AT JOP | 2412-2413-NN-0031
32 | TEMPORARY KNEE BRACE DETAILS FOR 48" FROM JOP TO SSVS (SECTION B) AT SSVS | 2412-2413-NN-0032
33 | TEMPORARY KNEE BRACE DETAILS FOR 48" FROM SSVS TO PLEM (SECTION A) AT SSVS | 2412-2413-NN-0033
34 | TEMPORARY KNEE BRACE DETAILS FOR 48" FROM SSVS TO PLEM (SECTION A) AT PLEM | 2412-2413-NN-0034
35 | TEMPORARY KNEE BRACE DETAILS FOR 48" FROM SSVS TO PLEM (SECTION B) AT SSVS | 2412-2413-NN-0035
36 | TEMPORARY KNEE BRACE DETAILS FOR 48" FROM SSVS TO PLEM (SECTION B) AT PLEM | 2412-2413-NN-0036
37 | Temporary Scraper Launcher and Receiver Details for 56” Pipelines | 2412-2413-NN-0037
38 | Temporary Scraper Launcher and Receiver Details for 48” Pipelines | 2412-2413-NN-0038
39 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPE @ GAC-82 (TRIP-1) | 2412-2413-NN-0039 | A | 3 |  | 2024-07-24 | CSE-2412-2413-PMT-T-007 | 2024-08-15 | 2412-2413-NPCC-T-06590 |  |  |  | 2024-08-15 | 2412-2413-PMT-MWS-T-0001
40 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-2) | 2412-2413-NN-0040
41 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-3) | 2412-2413-NN-0041
42 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-4) | 2412-2413-NN-0042
43 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ GAC-82 (TRIP-5) | 2412-2413-NN-0043 | A | 3 |  | 2024-11-13 | CSE-2412-2413-PMT-T-039 | [5 empty] | 2024-11-15 | 2412-2413-PMT-MWS-T-0006
44 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-258 (TRIP-6) | 2412-2413-NN-0044 | A | 3 |  | 2024-11-07 | CSE-2412-2413-PMT-T-044
|  |  | B | 3 |  | 2024-11-20 | CSE-2412-2413-PMT-T-050 | [5 empty] | 2024-11-24 | 2412-2413-PMT-MWS-T-0008
45 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-258 (TRIP-7) | 2412-2413-NN-0045 | A | 3 |  | 2024-11-07 | CSE-2412-2413-PMT-T-045
|  |  | B | 3 |  | 2024-12-04 | CSE-2412-2413-PMT-T-055
46 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ EOS-285 (TRIP-8) | 2412-2413-NN-0046 | A | 3 |  | 2024-11-08 | CSE-2412-2413-PMT-T-046
|  |  | B | 3 |  | 2024-12-19 | CSE-2412-2413-PMT-T-057 | [7 empty] | 2024-12-23 | 2'412-2413-PMT-MWS-T-0009
47 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ GAC-82 (TRIP-9) | 2412-2413-NN-0047 | A | 3 |  | 2024-11-08 | CSE-2412-2413-PMT-T-047
|  |  | B |  |  | 2024-12-26 | CSE-2412-2413-PMT-T-059
48 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-259 (TRIP-10) | 2412-2413-NN-0048 | A | 3 |  | 2025-01-02 | CSE-2412-2413-PMT-T-063 | [7 empty] | 2025-01-02 | 2412-2413-PMT-MWS-T-0011
49 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 48” CC PIPES @ EOS-285 (TRIP-11) | 2412-2413-NN-0049 | A | 3 |  | 2025-01-10 | CSE-2412-2413-PMT-T-067
50 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 56” CC PIPES @ AESEN-2803 (TRIP-12) | 2412-2413-NN-0050 | A | 3 |  | 2025-05-31 | CSE-2412-2413-PMT-T-097
51 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-13) | 2412-2413-NN-0051
52 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-14) | 2412-2413-NN-0052
53 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-15) | 2412-2413-NN-0053
54 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-16) | 2412-2413-NN-0054
55 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-17) | 2412-2413-NN-0055
56 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-18) | 2412-2413-NN-0056
57 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-19) | 2412-2413-NN-0057
58 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-20) | 2412-2413-NN-0058
59 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-21) | 2412-2413-NN-0059
60 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-22) | 2412-2413-NN-0060
61 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-23) | 2412-2413-NN-0061
62 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-24) | 2412-2413-NN-0062
63 | TYPICAL LIFTING & INSTALLATION OF MATTRESS BY SHUJAA-2000 | 2412-2413-NN-0063 | A | 3 |  | 2024-07-06 | CSE-2412-2413-PMT-T-006
64 | FLANGE PROTECTOR DETAILS FOR 56" RIGID PIPELINES HEADS | 2412-2413-NN-0064 | A | 3 | remarks | 2024-07-26 | CSE-2412-2413-PMT-T-008 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-005- 26/07
|  |  | B |  |  | 2024-09-13 | CSE-2412-2413-PMT-T-028
65 | FLANGE PROTECTOR DETAILS FOR 48" RIGID PIPELINES HEADS | 2412-2413-NN-0065 | A | 3 | remarks | 2024-07-26 | CSE-2412-2413-PMT-T-008 | [10 empty] | sent to Fab. Ref.'CSE-OF-2412-T-005- 26/07
|  |  | B | 3 |  | 2024-09-13 | CSE-2412-2413-PMT-T-028
66 | CHAIN LAYING ARRANGEMENT @ GOGAS-255 | 2412-2413-NN-0066 | remarks | [14 empty] | sent to Fab. Ref.'CSE-OF-2412-T-002 - 03/07
67 | WINCH FOUNDATION DETAILS ON GOGAS-255 | 2412-2413-NN-0067
68 | LOADING ARRANGEMENT OF MISC. EQUIPMENTS ON ASTRO 301 | 2412-2413-NN-0068 | A | 3 |  | 2024-08-13 | CSE-2412-2413-PMT-T-015
69 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-258 (TRIP-2) | 2412-2413-NN-0069 | A | 3 |  | 2024-08-23 | CSE-2412-2413-PMT-T-016
|  |  | B | 3 |  | 2024-08-30 | CSE-2412-2413-PMT-T-023
70 | LOADING ARRANGEMENT OF CABLE TANK ON ASTRO-301 | 2412-2413-NN-0070
71 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-259 (TRIP-3) | 2412-2413-NN-0071 | A | 3 |  | 2024-08-27 | CSE-2412-2413-PMT-T-021
|  |  | B | 3 |  | 2024-09-02 | CSE-2412-2413-PMT-T-024 | [5 empty] | 2024-09-30 | 2412-2413-PMT-MWS-0002
72 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ EOS-285 (TRIP-4) | 2412-2413-NN-0072 | A | 3 |  | 2024-09-10 | CSE-2412-2413-PMT-T-025
|  |  | B | 3 |  | 2024-10-21 | CSE-2412-2413-PMT-T-037 | [5 empty] | 2024-10-26 | 2412-2413-PMT-MWS-0005
73 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF STINGER-9A & PROJECT MATERIALS OF DLS-4200 @ CB-8 | 2412-2413-NN-0073 | A | 3 |  | 2024-11-05 | CSE-2412-2413-PMT-T-042
|  |  | B | 3 |  | 2024-12-25 | CSE-2412-2413-PMT-T-062 | [5 empty] | 2024-12-26 | 2412-2413-PMT-MWS-0010
74 | HBC ARRANGEMENT FOR 56" PIPELINE SECTION-1 | 2412-2413-NN-0074 |  |  | SJD-25/09
75 | TYPICAL LIFTING & INSTALLATION OF MATTRESS & TEMP. SUPPORT AT JOP (SETUP-1) | 2412-2413-NN-0075 | A | 3 |  | 2024-09-26 | CSE-2412-2413-PMT-T-035
76 | TYPICAL LIFTING & INSTALLATION OF MATTRESS & TEMP. SUPPORT AT JOP (SETUP-2) | 2412-2413-NN-0076 | A | 3 |  | 2024-09-26 | CSE-2412-2413-PMT-T-035
77 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SPOOL @ EOS-281 | 2412-2413-NN-0077 | A | 3 |  | 2024-12-19 | CSE-2412-2413-PMT-T-058 | [5 empty] | 2025-01-02 | 2412-2413-PMT-MWS-T-0012
|  |  | B | 3 | IFC | 2025-01-08 | CSE-2412-2413-PMT-T-066 | [5 empty] | 2025-01-12 | 2412-2413-PMT-MWS-T-0013
|  |  | C | 3 | IFC | 24-03-2025 | CSE-2412-2413-PMT-T-086
78 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 56” CC PIPES @ MICLYN-288 (TRIP-1) | 2412-2413-NN-0078 | A | 3 |  | 2054-01-14 | CSE-2412-2413-PMT-T-068 | [5 empty] | 2025-01-15 | 2412-2413-PMT-MWS-T-0014
79 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 56" CC PIPES @ GOGAS-252 (Trip-2) | 2412-2413-NN-0079 | A |  |  | 2025-01-20 | CSE-2412-2413-PMT-T-069
80 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 56" CC PIPES @ AESEN-2803 (TRIP-3) | 2412-2413-NN-0080 | A | 3 |  | 2025-01-20 | CSE-2412-2413-PMT-T-070
|  |  | B | 3 |  | 2025-02-04 | CSE-2412-2413-PMT-T-072
81 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 56" CC PIPES @ CASPAN-280 (TRIP-4) | 2412-2413-NN-0081 | A | 3 |  | 2025-02-20 | CSE-2412-2413-PMT-T-078
82 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 56" CC PIPES @ GOGAS-250 (TRIP-5) | 2412-2413-NN-0082 | A | 3 |  | 19-02-2025 17-03-2025 | CSE-2412-2413-PMT-T-076
83 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 56" CC PIPES @ AESEN-2803 (TRIP-6) | 2412-2413-NN-0083 | A | 3 |  | 2025-04-07 | CSE-2412-2413-PMT-T-088
84 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ GAC-82- START UP TRIP | 2412-2413-NN-0084 | A | 3 |  | 2025-02-17 | CSE-2412-2413-PMT-T-075
85 | SPOOL LIFTING AND INSTALLATION FOR 56" FROM SHORE TO SSVS AT SSVS (ORIENTAL DRAGON) | 2412-2413-NN-0085 | A | 3 |  | 2025-03-03 | CSE-2412-2413-PMT-T-080
|  |  | 00 | 3 |  | 2025-04-28 | CSE-2412-2413-PMT-T-092
86 | SPOOL LIFTING AND INSTALLATION FOR 56" FROM JOP TO SSVS AT SSVS (ORIENTAL DRAGON) | 2412-2413-NN-0086 | A | 3 |  | 04-03-2025 12-03-2025 | CSE-2412-2413-PMT-T-081
|  |  | 00 | 3 |  | 2025-04-28 | CSE-2412-2413-PMT-T-092
87 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM JOP TO SSVS (SECTION A) AT SSVS (ORIENTAL DRAGON) | 2412-2413-NN-0087 | A | 3 |  | 2025-03-04 | CSE-2412-2413-PMT-T-081
|  |  | 00 | 3 |  | 2025-04-28 | CSE-2412-2413-PMT-T-092
88 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM JOP TO SSVS (SECTION B) AT SSVS (ORIENTAL DRAGON) | 2412-2413-NN-0088 | A | 3 |  | 2025-03-04 | CSE-2412-2413-PMT-T-081
|  |  | 00 | 3 |  | 2025-04-28 | CSE-2412-2413-PMT-T-092
89 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM SSVS TO PLEM (SECTION-A) AT SSVS (ORIENTAL DRAGON) | 2412-2413-NN-0089 | A | 3 |  | 2025-03-03 | CSE-2412-2413-PMT-T-080
|  |  | 00 | 3 |  | 2025-04-28 | CSE-2412-2413-PMT-T-092
90 | SPOOL LIFTING AND INSTALLATION FOR 48" FROM SSVS TO PLEM (SECTION-B) AT SSVS (ORIENTAL DRAGON) | 2412-2413-NN-0090 | A | 3 |  | 2025-03-03 | CSE-2412-2413-PMT-T-080
|  |  | 00 | 3 |  | 2025-04-28 | CSE-2412-2413-PMT-T-092
91 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 56"CC PIPES @ GOGAS-252 (TRIP-7) | 2412-2413-NN-0091 | A | 3 |  | 2025-04-07 | CSE-2412-2413-PMT-T-087
92 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON MICLYN-288 (TRIP-8) | 2412-2413-NN-0092 | A | 3 |  | 2025-04-21 | CSE-2412-2413-PMT-T-089
93 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 56” CC PIPES @ CASPIAN-280 (TRIP-9) | 2412-2413-NN-0093 | A | 3 |  | 2025-04-21 | CSE-2412-2413-PMT-T-091
94 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 56” CC PIPES @ GOGAS-250 (TRIP-10) | 2412-2413-NN-0094 | A | 3 |  | 2025-04-21 | CSE-2412-2413-PMT-T-091
95 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 56” CC PIPES @ GOGAS-252 (TRIP-11) | 2412-2413-NN-0095 | A | 3 |  | 2025-05-06 | CSE-2412-2413-PMT-T-093 | [5 empty] | 2025-05-09 | 2412-2413-PMT-MWS-T-0017
|  |  | B | 3 |  | 2025-05-16 | CSE-2412-2413-PMT-T-095 | [10 empty] | BARGE CHANGED
96 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SPOOL @ GOGAS-252 (TRIP-2) | 2412-2413-NN-0096 | A | 3 |  | 2025-05-30 | CSE-2412-2413-PMT-T-096
97 | LIFTING AND INSTALLATION FOR 56" SPOOLS FROM JOP TO SSVS AT JOP (CCC WADAD ALETHEIA) | 2412-2413-NN-0097 | A | 3 |  | 2025-09-11 | CSE-2412-2413-PMT-T-100
|  |  | B | 3 |  | 2025-10-03 | CSE-2412-2413-PMT-T-101
98 | LIFTING AND INSTALLATION FOR 48" SPOOL (SPM-37A) FROM JOP TO SSVS AT JOP (CCC WADAD ALETHEIA) | 2412-2413-NN-0098 | A | 3 |  | 2025-09-11 | CSE-2412-2413-PMT-T-100
|  |  | B | 3 |  | 2025-10-03 | CSE-2412-2413-PMT-T-101
99 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SPOOLS & MISC. ITEMS @ CB-8 | 2412-2413-NN-0099 | A | 3 |  | 2025-09-03 | CSE-2412-2413-PMT-T-099
100 | LIFTING AND INSTALLATION FOR 48" SPOOL (SPM-37B) FROM JOP TO SSVS AT JOP (CCC WADAD ALETHEIA) | 2412-2413-NN-0100 | A | 3 |  | 2025-09-11 | CSE-2412-2413-PMT-T-100
|  |  | B | 3 |  | 2025-10-03 | CSE-2412-2413-PMT-T-101
101 | LIFTING AND INSTALLATION FOR 56" SPOOL FROM JOP TO SSVS AT SSVS (CCC WADAD ALETHEIA) | 2412-2413-NN-0101 | A | 3 | NAR | 2025-10-06 | CSE-2412-2413-PMT-T-102
102 | LIFTING AND INSTALLATION FOR 48" SPOOL (SPM-37A) FROM JOP TO SSVS AT SSVS (CCC WADAD ALETHEIA) | 2412-2413-NN-0102 | A | 3 | NAR | 2025-10-21 | CSE-2412-2413-PMT-T-103
103 | LIFTING AND INSTALLATION FOR 48" SPOOL (SPM-37B) FROM JOP TO SSVS AT SSVS (CCC WADAD ALETHEIA) | 2412-2413-NN-0103 | A | 3 | NAR | 2025-11-19 | CSE-2412-2413-PMT-T-105
104 | SPARE | 2412-2413-NN-0104 | [15 empty] | EMAIL FROM REY CANCELLED DOC. # ON 18/11
105 | SPARE | 2412-2413-NN-0105
106 | SPARE | 2412-2413-NN-0106
107 | LIFTING AND INSTALLATION OF ILI TEMP LAUNCHER WITH WADAD ALTHEIA | 2412-2413-NN-0107 | A | 3 | MF | 2025-11-10 | CSE-2412-2413-PMT-T-104

## SKETCHES
Project 2412
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2412 | OFO-P2412-SK-T-001 | GENERAL PIPELAY PROFILE | 1 | D | √ | √ | 19/09/2024 | CDG | @
2 | 2412 | OFO-P2412-SK-T-002 | ABANDONMENT & RECOVERY ARRANGEMENT @ FINAL STAGE
3 | 2412 | OFO-P2412-SK-T-003 | START-UP ARRANGEMENT FOR 56” CLS-26 PL (SECTION-2) AT JOP | 1 | B | √ | √ | 2024-11-19 | NEH | @
4 | 2412 | OFO-P2412-SK-T-004 | SHORE PULL ARRANGEMENT AT JUAYMAH TERMINAL OFFSHORE | 2 | C | √ | √ | 2025-03-12 | CDG | @
5 | 2412 | OFO-P2412-SK-T-005 | TYPICAL AIR BAG ARRANGEMENTS FOR PIPELINE
6 | 2412 | OFO-P2412-SK-T-006 | TYPICAL ARRANGEMENT OF FLOATS ON PIPELINE
7 | 2412 | OFO-P2412-SK-T-007 | 42" ANCHOR PIPE | 1 + 8 | A, 0 | √ | √ | 23/07/2024 | HZD | @
8 | 2412 | OFO-P2412-SK-T-008 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY Delma 2000 | 2 | C | √ | √ | 26/08/2024 | HZD | @
9 | 2412 | OFO-P2412-SK-T-009 | LOADING ARRANGEMENT OF CONSTRUCTION EQUIPMENT ON ASTRO-301 | 1 | D | √ | √ | 26/07/2024 | JF | @
10 | 2412 | OFO-P2412-SK-T-010 | ADDITIONAL STANCHION DETAIL FOR ASTRO-301 | 1 + 4 | A, 0 | √ | √ | 25/06/2024 | HZD | @ | SENT TO FAB. REF. # T-001
11 | 2412 | OFO-P2412-SK-T-011 | DMA START UP ARRANGEMENT 48” P/L’S SPM 37A SECTION-2 FROM JOP TO SPM 37 | 2 | D | √ | √ | 08/10/2024 | SKT | @
12 | 2412 | OFO-P2412-SK-T-012 | DMA START UP ARRANGEMENT 48” P/L’S SPM 37B SECTION-2 FROM JOP TO SPM 37 | 2 | D | √ | √ | 08/10/2024 | SKT | @
13 | 2412 | OFO-P2412-SK-T-013 | TYPICAL BUCKLE DETECTOR INSTALLATION | 1 | A | √ | √ | 26/09/2024 | CDG | @
14 | 2412 | OFO-P2412-SK-T-014 | LAYOUT OF NEW STANCHIONS LOCATIONS ON ASTRO-301 | 1 | A | √ | √ | 03/07/2024 | JF | @
15 | 2412 | OFO-P2412-SK-T-015 | 24.9M STOPPER BEAM DETAILS ON ASTRO-301 | 1 + 3 | A, 0 | √ | √ | 03/07/2024 | JF | @ | SENT TO FAB. REF. # T-003 - 04-07
16 | 2412 | OFO-P2412-SK-T-016 | RETRACTABLE GANGWAY WITH TIE BACK TOWER FOR SHUJAA 2000 | 5, 3+12 | A, 0 | √ | √ | 17/07/2024 | SKS | @ | SENT TO FAB. REF. # T-004 - 17-07
17 | 2412 | OFO-P2412-SK-T-017 | RIGGING ARRANGEMENT BETWEEN HAMMER AND CHASER PILE | 1 | A | √ | √ | 17/07/2024 | AKS | @
18 | 2412 | OFO-P2412-SK-T-018 | RIGGING DETAILS FOR CHAIN LAYING ON GOGAS-255 | 1 | B | √ | √ | 17/07/2025 | AKS | @
19 | 2412 | OFO-P2412-SK-T-019 | WINCH FOUNDATION DETAILS ON GOGAS-255 | 1 | A, 0 | √ | √ | 2024-07-27 | AKS | @
20 | 2412 | OFO-P2412-SK-T-020 | DETAILS OF TEMPORARY SUPPORT H-2500 | 1 | C, 1 | √ | √ | 2024-09-23 | AKS | @
21 | 2412 | OFO-P2412-SK-T-021 | TRANSITION JOINTS FOR 48'' PIPELINE | 1 | A | √ | √ | 2024-08-05 | NAR | @
22 | 2412 | OFO-P2412-SK-T-022 | WATER TIGHT BUOYANT WITH 56" PIPE | 1 | A, 0 |  | √ | 2024-08-05 | AKS | @
23 | 2412 | OFO-P2412-SK-T-023 | AIR TUGGERS FOUNDATION ARRANGEMENT ON SHUJAA2000 MAIN DECK (FA5-24) | 1 | A | √ | √ | 2024-08-17 | HZD | @
24 | 2412 | OFO-P2412-SK-T-024 | AIR TUGGERS FOUNDATION ARRANGEMENT ON SHUJAA2000 MAIN DECK (FA10-40 | 1 | A | √ | √ | 2024-08-19 | HZD | @
25 | 2412 | OFO-P2412-SK-T-025 | STARTUP ARRANGEMENT FOR 48"-SPM-37A PL. (SECTION-1) & 48"-SPM-37B PL. (SECTION-1) | 1 | B | √ | √ | 08/10/2024 | SKT | @
26 | 2412 | OFO-P2412-SK-T-026 | ROV Base Frame on SHUJAA-2000 + CUTLIST | 1 + 14 | A, 0 | √ | √ | 13/09//2024 | Shajil | @
27 | 2412 | OFO-P2412-SK-T-027 | DETAILS OF BLIND FLANGE FOR 48" SSVM AND 56" SSVM | 1 + 1 | B, 1 | √ | √ | 2024-11-29 | AKS | @
28 | 2412 | OFO-P2412-SK-T-028 | BUCKLE DETECTOR BLOW DOWN ARRANGEMENT FOR 56” PIPE | 1 | A | √ | √ | 2024-10-01 | ENH | @
29 | 2412 | OFO-P2412-SK-T-029 | DETAILS OF CLOSURE PLATE FOR 48" SSVM & 48" PLEM | 1 + 2 | B, 1 | √ | √ | 2024-11-29 | AKS | @
30 | 2412 | OFO-P2412-SK-T-030 | DETAILS OF CLOSURE PLATE FOR 56" SSVM | 1 + 1 | B, 1 | √ | √ | 2024-11-29 | AKS | @
31 | 2412 | OFO-P2412-SK-T-031 | DETAILS OF CLOSURE PLATE FOR 56" SPOOL - SPECIAL OD | 1 + 1 | B, 1 | √ | √ | 2024-11-29 | AKS | @
32 | 2412 | OFO-P2412-SK-T-032 | DETAILS OF CLOSURE PLATE FOR 24" PLEM | 1 + 1 | B, 1 | √ | √ | 2024-11-29 | AKS | @
33 | 2412 | OFO-P2412-SK-T-033 | BUCKLE DETECTOR BLOW DOWN ARRANGEMENT FOR 48” PIPE | 1 | A | √ | √ | 2024-10-02 | ENH | @
34 | 2412 | OFO-P2412-SK-T-034 | PIPELAY PROFILE FOR 56’’ PIPELINE (DLS-4200) | 1 | A | √ | √ | 2024-10-31 | NAR | @
35 | 2412 | OFO-P2412-SK-T-035 | DETAILS OF CLOSURE PLATE FOR 48" SPOOL | 1 + 1 | B, 1 | √ | √ | 2024-11-29 | AKS | @
36 | 2412 | OFO-P2412-SK-T-036 | DETAILS OF CLOSURE PLATE FOR 56" SPOOL | 1 + 1 | B, 1 | √ | √ | 2024-11-29 | AKS | @
37 | 2412 | OFO-P2412-SK-T-037 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DLS-4200 | 1 | B | √ | √ | 2024-10-21 | NAR | @
38 | 2412 | OFO-P2412-SK-T-038 | 56’’ SHORE PULL HEAD SKID DETAILS | 1 + 10 | B, 1 | √ | √ | 2024-11-25 | SKT | @
39 | 2412 | OFO-P2412-SK-T-039 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES & STINGER HITCH @ MICLYN-288 | 1 | A | √ | √ | 2024-10-16 | CDG | @
40 | 2412 | OFO-P2412-SK-T-040 | START-UP HOLDBACK ARRANGEMENT @ JOP PLATFORM FOR 48” PIPELINE | 1 | A | √ | √ | 2024-10-29 | ENH | @
41 | 2412 | OFO-P2412-SK-T-041 | LIFTING & INSTALLATION OF STINGER-9A AT DLS-4200 | 1 | A | √ | √ | 2025-01-29 | REY | @
42 | 2412 | OFO-P2412-SK-T-042 | LIFTING RIGGING ARRANGEMENT FOR PILE RECOVERY | 1 | A | √ | √ | 2024-11-08 | CDG | @
43 | 2412 | OFO-P2412-SK-T-043 | CABLE SHOREPULL ARRANGEMENT | 1 | B | √ | √ | 2025-05-12 | CDG | @
44 | 2412 | OFO-P2412-SK-T-044 | 48" PIPELINE CATENARY | 1 | A | √ | √ | 2024-12-06 | AKS | @
45 | 2412 | OFO-P2412-SK-T-045 | STORAGE QUADRANT-1.2M RADIUS AT JOP | 1 | A | √ | √ | 2024-12-11 | SKT | @
46 | 2412 | OFO-P2412-SK-T-046 | A - FRAME FOR CABLE PULLING AT JOP | 1 | A | √ | √ | 2024-12-11 | SKT | @
47 | 2412 | OFO-P2412-SK-T-047 | 3M RADIUS HALF MOON BEND RESTRICTOR FOR CABLE LAYING AT JOP | 1 | A | √ | √ | 2024-12-11 | SKT | @
48 | 2412 | OFO-P2412-SK-T-048 | FLANGE CATCHER (FOR ALIGNMENT OF TIE-IN SPOOL) | 1 | A, 0 | √ | √ | 2024-12-30 | SKS | @
49 | 2412 | OFO-P2412-SK-T-049 | TIE-IN METROLOGY CLAMP (TYPE-1) | 1 | A, 0 | √ | √ | 2024-12-30 | SKS | @
50 | 2412 | OFO-P2412-SK-T-050 | RIGGING CONNECTION OF MESSENGER LINE AND PULLING WIRE | 1 | A | √ | √ | 2025-01-02 | CDG | @
51 | 2412 | OFO-P2412-SK-T-051 | TYPICAL CABLE PULLING ARRANGEMENT AT JOP | 1 | B | √ | √ | 2025-05-23 | SKT | @
52 | 2412 | OFO-P2412-SK-T-052 | EQUIPMENT LAYOUT ON CCC MARITIME-2 | 1 | A | √ | √ | 2025-04-14 | AMK | @
53 | 2412 | OFO-P2412-SK-T-053 | A-FRAME FOR DIVING TOOLS | 1 | A | √ | √ | 2025-04-28 | SKT | @
54 | 2412 | OFO-P2412-SK-T-054 | AP-6 ANCHOR PILE CUTTING WITH DIAMOND WIRE CUTTER AND RECOVERY |  |  |  |  | 2025-05-01 | SKT
55 | 2412 | OFO-P2412-SK-T-055 | CUTTING OF PLEM PILE HAMMER ALLOWANCE |  |  |  |  | 2025-05-01 | SKT
56 | 2412 | OFO-P2412-SK-T-056 | Cable 2nd end laydown and pulling arrangement at JOP platform |  |  |  |  | 2025-05-13 | SJD
57 | 2412 | OFO-P2412-SK-T-057 | SPREADER BAR LOWER SLING ARRANGEMENT | 1 | A | √ | √ | 2025-05-20 | CDG | @
58 | 2412 | OFO-P2412-SK-T-058 | DEPLOYMENT SEQUENCE FOR TYPICAL STEVSHARK MOORING SYSTEM | 3 | A | √ | √ | 2025-05-29 | SHIJU | @
59 | 2412 | OFO-P2412-SK-T-059 | RECOVERY SEQUENCE FOR TYPICAL STEVSHARK MOORING SYSTEM | 3 | A | √ | √ | 2025-05-29 | SHIJU | @
60 | 2412 | OFO-P2412-SK-T-060 | SPOOL FABRICATION SADDLE SUPPORT (SWL = 8MT) | 1 | A | √ | √ | 2025-07-04 | LEO | @
61 | 2412 | OFO-P2412-SK-T-061 | JET MIXING PUMP LIFTING ARRANGEMENT BY SHUJAA-2000 | 1 | B | √ | √ | 2025-08-14 | NAR | @
62 | 2412 | OFO-P2412-SK-T-062 | JET MIXING PUMP LIFTING ARRANGEMENT BY CCC MARITIME-2 | 1 | A | √ | √ | 2025-08-06 | NAR | @
63 | 2412 | OFO-P2412-SK-T-063 | FEASIBILTY CHECK TO LOADOUT 48'' SPM-37A, SPM-37B & 56'' CLS-26 SSVS SPOOLS AT SUPPLY BOAT PRIYA-2090 | 1 | B | √ | √ | 2025-09-02 | NAR | @
64 | 2412 | OFO-P2412-SK-T-064 | SHALLOW WATER CONCRETE BLOCK AND MARKER BUOY INSTALLATION SEQUENCES | 5 | B | √ | √ | 2025-11-06 | CDG | @
65 | 2412 | OFO-P2412-SK-T-065 | 48" SPM-37A PIPELINE PLATFORM SPOOL | 1 | A | √ | √ | 2025-09-19 | VDA | @
66 | 2412 | OFO-P2412-SK-T-066 | 48" SPM-37A PIPELINE SSVS SPOOLS |  |  |  |  | 2025-09-19 | VDA
67 | 2412 | OFO-P2412-SK-T-067 | 56" CLS-26 PIPELINE SSVS SPOOLS |  |  |  |  | 2025-09-19 | VDA
68 | 2412 | OFO-P2412-SK-T-068 | FEASIBILITY CHECK FOR LOADOUT OF SPOOLS ON SUPPLY BOAT PRIYA-2090 | 1 | A | √ | √ | 2025-09-22 | VDA | @
69 | 2412 | OFO-P2412-SK-T-069 | FEASIBILITY CHECK FOR LOADOUT OF SPOOLS ON SUPPLY BOAT PRIYA-2090 [FINAL TRIP ISA] | 1 | A | √ | √ | 2025-09-26 | SKS | @
70 | 2412 | OFO-P2412-SK-T-070 | TYPICAL LIFTING & INSTALLATION OF CONCRETE PROTECTION SLAB | 1 | B | √ | √ | 2025-11-24 | MF | @
71 | 2412 | OFO-P2412-SK-T-071 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND VESSEL AT ( JOP ) PLATFORM | 2 | A | √ | √ | 2026-03-30 | MF | @
72 | 2412 | OFO-P2412-SK-T-072 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT (JOP) PLATFORM | 2 | A | √ | √ | 2026-03-30 | MF | @
73 | 2412 | OFO-P2412-SK-T-073 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT (JOP) PLATFORM | 2 | A | √ | √ | 2026-03-30 | MF | @
74 | 2412 | OFO-P2412-SK-T-074 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT (JOP) PLATFORM | 2 | A | √ | √ | 2026-03-30 | MF | @
75 | 2412 | OFO-P2412-SK-T-075 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT (JOP) PLATFORM | 2 | A | √ | √ | 2026-03-30 | MF | @
76 | 2412 | OFO-P2412-SK-T-076 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT (JOP) PLATFORM | 2 | A | √ | √ | 2026-03-30 | MF | @
77 | 2412 | OFO-P2412-SK-T-077 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND VESSEL AT (JOP) PLATFORM | 2 | A | √ | √ | 2026-03-30 | MF | @
78 | 2412 | OFO-P2412-SK-T-078 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND PLATFORM AT (JOP) PLATFORM | 2 | A | √ | √ | 2026-03-30 | MF | @
79 | 2412 | OFO-P2412-SK-T-079 | 30” Tubular lifting feasibility check with Zakher Pioneer |  |  |  |  | 2026-05-21 | BINOY
80 | 2412 | OFO-P2412-SK-T-080 | ICCP CABLE SCOPE LAYOUT |  |  |  |  | 2026-07-04 | SKS
81 | 2412 | OFO-P2412-SK-T-081 | TYPICAL LIFTING & INSTALLATION OF CONCRETE PROTECTION SLAB | 1 | B | √ | √ | 2026-08-27 | CDG | @
82 | 2412 | OFO-P2412-SK-T-082 | SHALLOW WATER CONCRETE BLOCK AND MARKER BUOY LIFTING DRAWING - MILLENNIUM - 3 | 4 | A | √ | √ | 2026-07-16 | CDG | @
83 | 2412 | OFO-P2412-SK-T-083 | RECOVER ARRANGEMENT OF EXISTING DEAD MAN ANCHOR- MILLENNIUM - 3 | 1 | A | √ | √ | 2026-07-16 | CDG | @
84 | 2412 | OFO-P2412-SK-T-084 | TYPICAL LIFTING & INSTALLATION OF CONCRETE PROTECTION SLAB BY SEP-450 AT JOP |  |  |  |  | 2026-09-07 | CDG

## Cutlists
Project 2412
DETAILS OF CUT-LIST DRAWINGS TO FABRICATION
S.NO. | CUTLISTS DWG NO. | TITLE/DESCRIPTION | LATEST REV. | TRANS. REF. # | DATE | PREP. | REMARKS
1 | 2412-2413-NN-0001-CTL | SHOREPULL HEAD FOR 56" PIPELINE (WITH CUT-LIST 1+ 17) | 0 | CSE-OF-2412-T-006 | 2024-07-29 | NAR / AN
|  |  | 1 | CSE-OF-2412-T-011 | 2024-09-12 | NAR / AN
|  |  | 2 | CSE-OF-2412-T-015 | 2024-10-01 | NAR / AN
2 | 2412-2413-NN-0002-CTL | LAYDOWN HEAD FOR 56" PIPELINE (WITH CUT-LIST 1 + 29) | 0 | CSE-OF-2412-T-005 | 2024-07-26 | NAR /HAF
|  |  | 1 | CSE-OF-2412-T-013 | 2024-09-16 | NAR/AN
3 | 2412-2413-NN-0003-CTL | START UP HEAD FOR 56" PIPELINE (WITH CUT-LIST 1 + 28) | 0 | CSE-OF-2412-T-005 | 2024-07-26 | NAR /HAF
|  |  | 1 | CSE-OF-2412-T-013 | 2024-09-16 | NAR/AN
4 | 2412-2413-NN-0004-CTL | TYPICAL EMERGENCY LAYDOWN HEAD FOR 56" PIPELINE (WITH CUT-LIST 1 + 24) | 0 | CSE-OF-2412-T-005 | 2024-07-26 | NAR /HAF
|  |  | 1 | CSE-OF-2412-T-013 | 2024-09-16 | NAR/AN
5 | 2412-2413-NN-0005-CTL | START UP HEAD FOR 48" PIPELINE - WITH CUTLIST 1 + 25) | 0 | CSE-OF-2412-T-005 | 2024-07-26 | NAR /HAF
|  |  | 1 | CSE-OF-2412-T-007 | 2024-08-08 | NAR / AN
|  |  | 2 | CSE-OF-2412-T-010 | 2024-08-30 | NAR / AN
6 | 2412-2413-NN-0006-CTL | LAYDOWN HEAD FOR 48" PIPELINE (WITH CUTLIST 1 + 27) | 0 | CSE-OF-2412-T-005 | 2024-07-26 | NAR /HAF
|  |  | 1 | CSE-OF-2412-T-008 | 2024-08-23 | AKS/SM
|  |  | 2 | CSE-OF-2412-T-009 | 2024-08-26 | AKS/SM
|  |  | 3 | CSE-OF-2412-T-010 | 2024-08-30 | NAR / AN
7 | 2412-2413-NN-0007-CTL | TYPICAL EMERGENCY LAYDOWN HEAD FOR 48" PIPELINE (WITH CUTLIST 1 + 23) | 0 | CSE-OF-2412-T-005 | 2024-07-26 | NAR /HAF
|  |  | 1 | CSE-OF-2412-T-009 | 2024-08-26 | AKS/SM
|  |  | 2 | CSE-OF-2412-T-010 | 2024-08-30 | NAR / AN
8 | 2412-2413-NN-0008-CTL | TYPICAL BUCKLE DETECTOR DETAIL FOR 56" PIPELINE | 0 | CSE-OF-2412-T-005 | 2024-07-26 | NAR /AN
9 | 2412-2413-NN-0009-CTL | TYPICAL BUCKLE DETECTOR DETAIL FOR 48" PIPELINE | 0 | CSE-OF-2412-T-005 | 2024-07-26 | NAR /AN
10 | OFO-P2412-SK-T-015-CTL | 24.9M STOPPER BEAM DETAILS ON ASTRO-301 | 0 | CSE-OF-2412-T-005 | 2024-07-26 | JF/HAF
11 | OFO-P2412-SK-T-020-CTL | DETAILS OF TEMPORARY SUPPORT H-2500 (WITH CUT-LIST 1+ 9) | 0 | CSE-OF-2412-T-014 | 25/09/2024 | AKS/AN
12 | OFO-P2412-SK-T-026-CTL | ROV Base Frame on SHUJAA-2000 (WITH CUTLIST 1 + 14) | 0 | CSE-OF-2412-T-014 | 25/09/204 | SKT/DGU
13 | 2412-2413-NN-0064-CTL | TYPICAL LIFTING & INSTALLATION OF MATTRESS BY SHUJAA-2000 (WITH CUTLIST 1 + 8) | 0 | CSE-OF-2412-T-008 | 2024-07-26 | NAR /AN
|  |  | 1 | CSE-OF-2412-T-012 | 2024-09-13 | NAR /AN
14 | 2412-2413-NN-0065-CTL | FLANGE PROTECTOR DETAILS FOR 56" RIGID PIPELINES HEADS (WITH CUTLIST 1 + 8) | 0 | CSE-OF-2412-T-008 | 2024-07-26 | NAR /AN
|  |  | 1 | CSE-OF-2412-T-012 | 2024-09-13 | NAR /AN
15 | 2412-2413-NN-0066-CTL | CHAIN LAYING ARRANGEMENT @ GOGAS-255 | 0 | CSE-OF-2412-T-002 | 2024-07-03 | AKS/ASK
16 | OFO-P2412-SK-T-027 | DETAILS OF BLIND FLANGE FOR 48" SSVM AND 56" SSVM (WITH CUT-LIST 1 + 2 - REV-0) | 0 | CSE-OF-2412-T-016 | 2024-10-16 | SKT/AN
17 | OFO-P2412-SK-T-029 | DETAILS OF CLOSURE PLATE FOR 48" SSVM & 48" PLEM (WITH CUT-LIST 1 + 1 - REV-0) | 0 | CSE-OF-2412-T-016 | 2024-10-16 | SKT/AN
18 | OFO-P2412-SK-T-030 | DETAILS OF CLOSURE PLATE FOR 56" SSVM (WITH CUT-LIST 1 + 1 - REV-0) | 0 | CSE-OF-2412-T-016 | 2024-10-16 | SKT/AN
19 | OFO-P2412-SK-T-031 | DETAILS OF CLOSURE PLATE FOR 56" SPOOL - SPECIAL OD (WITH CUT-LIST 1 + 1 - REV-0) | 0 | CSE-OF-2412-T-016 | 2024-10-16 | SKT/AN
20 | OFO-P2412-SK-T-032 | DETAILS OF CLOSURE PLATE FOR 24" PLEM (WITH CUT-LIST 1 + 1 - REV-0) | 0 | CSE-OF-2412-T-016 | 2024-10-16 | SKT/AN
21 | OFO-P2412-SK-T-035 | DETAILS OF CLOSURE PLATE FOR 48" SPOOL (WITH CUT-LIST 1 + 1 - REV-0) | 0 | CSE-OF-2412-T-016 | 2024-10-16 | SKT/AN
22 | OFO-P2412-SK-T-036 | DETAILS OF CLOSURE PLATE FOR 56" SPOOL (WITH CUT-LIST 1 + 1 - REV-0) | 0 | CSE-OF-2412-T-016 | 2024-10-16 | SKT/AN
23 | OFO-P2412-SK-T-038 | 56’’ SHORE PULL HEAD SKID DETAILS (WITH CUT-LIST 1 + 10 - REV-1) | 0 | CSE-OF-2412-T-017 | 2024-10-31 | SKT/AN
|  |  | 1 | CSE-OF-2412-T-018 | 2024-11-26 | SKT/AN

## TN-PL
|  | SAUDI ARABIAN OIL COMPANY | [10 empty] | NPCC DOC. No.:
CRPO # 86 FOR JAFURAH DEVELOPMENT PROGRAM CONDENSATE TERMINAL BI-10-14244
|  | NPCC PROJECT NO. 2412-2413 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ARAMCO | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | Startup with Jacket Leg Holdback at JOP | 2412-TN-PL-001
2 | PIPELINE AND SPOOLS BREAKOVER ANALYSIS REPORT | 2412-TN-PL-002