## Documents - Pipeline & Cable
|  | SAUDI ARAMCO (LTA) FOR OFFSHORE FACILITIES | [10 empty] | NPCC DOC. No.:
CRPO # 87 FOR FOURTEEN (14) JACKETS IN MANIFA FIELD
|  | NPCC PROJECT NO. 2419-2420 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 2023-02-28
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 |  | 2419-2420-NN-RP-001
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Documents - Naval Marine
|  | SAUDI ARAMCO (LTA) FOR OFFSHORE FACILITIES | [10 empty] | NPCC DOC. No.:
CRPO # 87 FOR FOURTEEN (14) JACKETS IN MANIFA FIELD
|  | NPCC PROJECT NO. 2419-2420 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (Naval Marine) | [10 empty] | DATE : |  |  |  | 2023-02-28
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | MOORING ANALYSIS DURING INSTALLATION OF ABSF 250/259 JACKET | 2419-2420-ZZ-CL-001 | A | 2 |  | 2023-03-16 | CSE-2419-2420-PMT-T-001 | [5 empty] | 2023-03-17 | 2419-NPCC-MWS-T-0005 | 23/03/2023 28/03/2023 | MDDXB 6020-MD-05-401-01 MDDXB 6020-MD-05-401-02 | 1
|  |  | B | 2 |  | 2023-04-05 | CSE-2419-2420-PMT-T-004
2 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 500/509 JACKET | 2419-2420-ZZ-CL-002 | A | 2 |  | 2023-08-18 | CSE-2419-2420-PMT-T-017
|  |  | B | 2 |  | 2023-09-28 | CSE-2419-2420-PMT-T-028 | [5 empty] | 2023-09-28 | 2419-NPCC-MWS-T-0107
3 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 510/519 JACKET | 2419-2420-ZZ-CL-003 | A | 2 |  | 2023-03-29 | CSE-2419-2420-PMT-T-002 | [5 empty] | 2023-03-29 | 2419-NPCC-MWS-T-0013
|  |  | B | 2 |  | 2023-04-05 | CSE-2419-2420-PMT-T-003
4 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 520/529 JACKET | 2419-2420-ZZ-CL-004 | A | 2 |  | 2023-07-17 | CSE-2419-2420-PMT-T-011 | [5 empty] | 2023-07-17 | 2419-NPCC-MWS-T-0041 | 2023-07-20 | 6020-MD-27-406-01 | 1
5 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 550/559 JACKET | 2419-2420-ZZ-CL-005 | A | 2 |  | 2023-09-15 | CSE-2419-2420-PMT-T-024 | [5 empty] | 2023-09-15 | 2419-NPCC-MWS-T-0092
|  |  | B | 2 |  | 2023-10-02 | CSE-2419-2420-PMT-T-029
6 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 560/569 JACKET | 2419-2420-ZZ-CL-006 | A | 2 |  | 2023-05-25 | CSE-2419-2420-PMT-T-008 | [5 empty] | 2023-06-14 | 2419-NPCC-MWS-T-0032
|  |  | B | 2 |  | 2023-06-14 | CSE-2419-2420-PMT-T-009
7 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 570/579 JACKET | 2419-2420-ZZ-CL-007 | A | 2 |  | 2023-09-19 | CSE-2419-2420-PMT-T-025 | [5 empty] | 2023-09-19 | 2419-NPCC-MWS-T-0095
8 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 580/589 JACKET | 2419-2420-ZZ-CL-008 | A | 2 |  | 2023-06-22 | CSE-2419-2420-PMT-T-010
|  |  | B | 2 |  | 2023-08-08 | CSE-2419-2420-PMT-T-015 | [5 empty] | 2023-08-08 | 2419-NPCC-MWS-T-0065
|  |  | C | 2 |  | 2023-08-11 | CSE-2419-2420-PMT-T-016 | [5 empty] | 2023-08-11 | 2419-NPCC-MWS-T-0068
9 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 910/919 JACKET | 2419-2420-ZZ-CL-009 | A | 3 |  | 2023-07-19 | CSE-2419-2420-PMT-T-012 | [5 empty] | 2023-07-20 | 2419-NPCC-MWS-T-0042 | 2023-07-21 | MDDXB 6020-MD-31-407-01 | 1
10 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 920/929 JACKET | 2419-2420-ZZ-CL-010 | A | 2 |  | 2023-05-25 | CSE-2419-2420-PMT-T-007
11 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 930/939 JACKET | 2419-2420-ZZ-CL-011 | A | 2 |  | 2023-08-21 | CSE-2419-2420-PMT-T-018
|  |  | B | 2 |  | 2023-08-29 | CSE-2419-2420-PMT-T-021
12 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 940/949 JACKET | 2419-2420-ZZ-CL-012 | A | 2 |  | 2023-07-19 | CSE-2419-2420-PMT-T-012 | [5 empty] | 2023-07-20 | 2419-NPCC-MWS-T-0043 | 2023-07-21 | MDDXB 6020-MD-32-408-01 | 1
|  |  | B | 2 |  | 2023-09-15 | CSE-2419-2420-PMT-T-023 | [5 empty] | 2023-09-25 | 2419-NPCC-MWS-T-0099
|  |  | C | 2 |  | 2023-09-29 | CSE-2419-2420-PMT-T-027 | [5 empty] | 2023-09-29 | 2419-NPCC-MWS-T-0105
13 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 950/959 JACKET | 2419-2420-ZZ-CL-013 | A | 2 |  | 2023-09-19 | CSE-2419-2420-PMT-T-026 | [5 empty] | 2023-09-19 | 2419-NPCC-MWS-T-0096
|  |  | B | 2 |  | 2023-12-11 | CSE-2419-2420-PMT-T-030
14 | MOORING ANALYSIS DURING INSTALLATION OF MNIF 960/969 JACKET | 2419-2420-ZZ-CL-014 | A | 2 |  | 2023-08-22 | CSE-2419-2420-PMT-T-019 | [5 empty] | 2023-08-22 | 2419-NPCC-MWS-T-0077
|  |  | B | 2 |  | 2023-09-01 | CSE-2419-2420-PMT-T-022
15 | BERTHING ANALYSIS FOR WORKBOATS IN MNIF & ABSF FIELD | 2419-2420-ZZ-CL-015 | A | 2 |  | 2023-04-13 | CSE-2419-2420-PMT-T-005
|  |  | B | 2 |  | 2023-05-09 | CSE-2419-2420-PMT-T-006
|  |  | C | 2
|  |  | D | 2 |  | 2023-07-24 | CSE-2419-2420-PMT-T-013
16 | BERTHING ANALYSIS FOR WORKBOAT ASTRO AQUILA IN MNIF & ABSF FIELD | 2419-2420-ZZ-CL-016 | A | 2 |  | 2023-08-02 | CSE-2419-2420-PMT-T-014
17 | BERTHING ANALYSIS FOR WORKBOAT STANFORD HUDHUD IN MNIF & ABSF FIELD | 2419-2420-ZZ-CL-017 | A | 2 |  | 2023-08-28 | CSE-2419-2420-PMT-T-020
18
19
20
21
22
23
24
25
26
27
28
29
30

## Drawings
|  | SAUDI ARAMCO (LTA) FOR OFFSHORE FACILITIES | [10 empty] | NPCC DOC. No.:
CRPO # 87 FOR FOURTEEN (14) JACKETS IN MANIFA FIELD
|  | NPCC PROJECT NO. 2419-2420 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (Naval Marine) | [10 empty] | DATE : |  |  |  | 2023-02-28
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 |  | 2419-2420-NN-0001
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30