## Naval & Marine doc
NPCC DOC. No.:
CLIENT DOC. No. :
|  |  | NPCC PROJECT NO.2631 | [10 empty] | REVISION : |  |  |  | 0
|  |  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (Naval) | [10 empty] | DATE : |  |  |  | 2021-03-22
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO MCE |  | STATUS FROM MCE
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | MOORING ANALYSIS DURING INSTALLATION OF JACKET WHT-2 | 2631-ZZ-CL-0001 | AD-27-Z-80035 | 1 | 2 |  | 2024-12-19 | CSE-2631-PMT-T-001 | 2024-12-19 | 2631-NMDC-ADNOC-T-00324 | 2025-01-02 | 10477-E-O-T-US-IFR-000276 | 1 | 2024-12-19 | 2631-NMDC-MWS-T-0007 | 2024-12-27 | SAF194-MCE-NMDC-T-0006 | 1
|  |  |  | 2 | 2 |  | 2025-04-15 | CSE-2631-PMT-T-003 | 2025-04-15 | 2631-NMDC-ADNOC-T-00452 | 2025-04-28 | 10477-E-O-T-US-IFA-000243 | 1 | 2025-04-15 | 2631-NMDC-MWS-T-0039 | 2025-04-16 | SAF194-MCE-NMDC-T-0033 | 1
2 | MOORING ANALYSIS DURING INSTALLATION OF JACKET WHT-3 | 2631-ZZ-CL-0002 | AD-27-Z-80036 | 1 | 2 |  | 2024-12-19 | CSE-2631-PMT-T-001 | 2024-12-19 | 2631-NMDC-ADNOC-T-00325 | 2025-01-02 | 10477-E-O-T-US-IFR-000276 | 1 | 2024-12-19 | 2631-NMDC-MWS-T-0008 | 2024-12-27 | SAF194-MCE-NMDC-T-0006 | 1
|  |  |  | 2 | 2 |  | 2025-04-07 | CSE-2631-PMT-T-002 | 2025-04-08 | 2631-NMDC-ADNOC-T-00440 | 2025-04-16 | 10477-E-O-T-US-IFR-000302 | 1 | 2025-04-08 | 2631-NMDC-MWS-T-0038 | 2025-04-14 | SAF194-MCE-NMDC-T-0032 | 1
3 | MOORING ANALYSIS DURING INSTALLATION OF JACKET WHT-3-1 | 2631-ZZ-CL-0003 | TBA
4 | MOORING ANALYSIS DURING INSTALLATION OF JACKET WHT-3-2 PILES AND APPURTENANCES | 2631-ZZ-CL-0004 | TBA | 1 | 2 |  | 2025-07-07 | CSE-2631-PMT-T-005 | 2025-07-16 | 2631-NMDC-ADNOC-T-00644 | 2025-07-24 | 10477-E-O-T-US-IFR-000327 | 1 | 2025-07-16 | 2631-NMDC-MWS-T-0064 | 2025-07-11 | SAF194-MCE-NMDC-T-0053 | 1
5 | MOORING ANALYSIS DURING INSTALLATION OF WHT-3-3 PILES AND APPURTENANCES | 2631-ZZ-CL-0005 | TBA | 1 | 2 |  | 2025-05-30 | CSE-2631-PMT-T-004 | 2025-05-30 | 2631-NMDC-ADNOC-T-00543 | 2025-06-03 | 10477-E-O-T-LZ-IFR-000062 | 1 | 2025-05-30 | 2631-NMDC-MWS-T-0049 | 2025-06-09 | SAF194-MCE-NMDC-T-0044 | 1
6 | MOORING ANALYSIS DURING WHT-3-4 JACKET INSTALLATION | 2631-ZZ-CL-0006 | TBA | 1 | 2 |  | 2025-07-16 | CSE-2631-PMT-T-006 | 2025-07-16 | 2631-NMDC-ADNOC-T-00653 | 2025-07-24 | 10477-E-O-T-US-IFR-000330 | 1 | 2025-07-16 | 2631-NMDC-MWS-T-0066 | 2025-07-18 | SAF194-MCE-NMDC-T-0056 | 1
7 | MOORING ANALYSIS DURING WHT-3-5 JACKET PILES AND JACKET APPURTENANCES INSTALLATION | 2631-ZZ-CL-0007 | TBA | 1 | 2 |  | 2025-07-16 | CSE-2631-PMT-T-007 | 2025-07-16 | 2631-NMDC-ADNOC-T-00654 | 2025-07-24 | 10477-E-O-T-US-IFR-000330 | 1 | 2025-07-16 | 2631-NMDC-MWS-T-0067 | 2025-07-18 | SAF194-MCE-NMDC-T-0056 | 1

## DRAWINGS
NPCC DOC. No.:
CLIENT DOC. No. :
|  |  | NPCC PROJECT NO.2631 | [10 empty] | REVISION : |  |  |  | 0
|  |  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS | [10 empty] | DATE : |  |  |  | 2021-03-22
SR. NO. | DESCRIPTION | COMPANY DOCUMENT NUMBER | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO MCE |  | STATUS FROM MCE
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1
2
3 | [18 empty] | Rejected
4
5
6 | [18 empty] | Rejected
7 | [18 empty] | Rejected
8
9 | [18 empty] | Rejected
10
11
12
13
14
15
16
17 | [18 empty] | Rejected
18
19 | [18 empty] | Rejected
20
21
22
23
24
sent to Fabrication T-023 dtd.11/10/23
sent to Fabrication T-026 dtd.02/11/23
sent to Fabrication T-028 dtd.07/11/23
sent to Fabrication T-029 dtd.14/11/23
sent to Fabrication T-030 dtd.15/11/23

## Sketch
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2631 | OFO-P2631-SK-T-001 | LOADING ARRANGEMENT OF MISC EQUIPMENTS ON CB-6 | 2 | A | √ | √ | 2024-12-30 | HZD | @
2 | 2631 | OFO-P2631-SK-T-002 | LOADING ARRANGEMENT OF MISC EQUIPMENTS ON SABINA CB | 2 | A | √ | √ | 2025-04-08 | AMK | @
3 | 2631 | OFO-P2631-SK-T-003 | PERSONNEL TRANSFER USING STEEL BASKET (SAFEEN-3000) | 1 | A | √ | √ | 2025-04-23 | NAR | @
4 | 2631 | OFO-P2631-SK-T-004 | SAPURA 1200 DECK LAYOUT FOR JACKET INSTALLATION - SAPURA 1200 |  |  |  |  | 2025-05-01 | VICTOR
5 | 2631 | OFO-P2631-SK-T-005 | GANGWAY ARRANGEMENT FOR SAPURA-1200 | 2 | A | √ | √ | 2025-05-30 | SKS | @
6 | 2631 | OFO-P2631-SK-T-006 | PERSONNEL LIFTING & INSTALLATION FOR JACKETS - 7JKT CAMPAIGN BY MUTAWA - 401 |  |  |  |  | 2025-05-15 | HZD
7 | 2631 | OFO-P2631-SK-T-007 | GENERAL MATERIALS LIFTING & INSTALLATION FOR JACKETS - 7JKT CAMPAIGN BY MUTAWA - 401 |  |  |  |  | 2025-05-15 | HZD
8 | 2631 | OFO-P2631-SK-T-008 | PERSONNEL TRANSFER USING STEEL BASKET (SAPURA-1200) | 2 | A | √ | √ | 2025-05-21 | CDG | @
9 | 2631 | OFO-P2631-SK-T-009 | SAPURA 1200: GANGWAY LIFTING ARRANGEMENT | 1 | A | √ | √ | 2025-05-26 | SKS | @
10 | 2631 | OFO-P2631-SK-T-010 | SADDLE DETAILS FOR GANGWAY | 2 | B | √ | √ | 2025-06-11 | SKT | @
11 | 2631 | OFO-P2631-SK-T-011 | SAPURA 1200: GANGWAY LIFTING AND INSTALLATION | 1 | A | √ | √ | 2025-06-11 | SKS | @
12 | 2631 | OFO-P2631-SK-T-012 | PERSONNEL TRANSFER USING STEEL BASKET (DLS4200) | 2 | B | √ | √ | 2025-06-25 | MF | @
13 | 2631
14 | 2631
15 | 2631

## cut-list
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location