## Documents - Pipeline & Cable
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
HAIL & GHASHA DEVELOPMENT PROJECT PACKAGE 1 – OFFSHORE FACILITIES
|  | NMDC ENERGY PROJECT NO. 2642 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPE STACKING ANALYSIS AT YARD | CF0000-4002540 | 1-CF0000-31-REP-2540-00 | A1 | 2A |  | 2024-09-03 | CSE-2642-PMT-T-001 | -- | -- | 2024-09-24 | HGDP-OFCR-00-TRN-003383 | 2
|  |  |  | 00 | 2A |  | 2024-10-09 | CSE-2642-PMT-T-002 | -- | -- | 2024-10-23 | --
|  |  |  | 01 | 2A |  | 2025-01-15 | CSE-2642-PMT-T-005 | 2025-01-15 | OFCR-HGDP-00TRN-007850 | 2025-01-31 | 1-CF0000-32-REP-2540-00_01_CPY1 | approved
2 | RISER/SPOOL LIFT ANALYSIS REPORT AT GOP-SRP FROM DC6(CS PIPELINES) | GH5100-4002504 | 1-GH5100-31-REP-2504-00 | A1 | 2A |  | 2025-07-25 | CSE-2642-PMT-T-020 | 2025-07-28 | to ABL | 2025-08-19 | 1-GH5100-31-REP-2504-00_A1_CPY1_CRS | approved |  |  | 2025-08-13 | AD_G30_44988-ABL-DRS-APP-0881 | approved
|  |  |  | 00 | 2A |  | 2026-02-05 | CSE-2642-PMT-T-042 | 2026-02-05 | ABL/RINA | [5 empty] | 2026-02-17 | AD_G30_44988-ABL-DRS-APP-2562 | approved
3 | RISER/SPOOL LIFT ANALYSIS AT GOP | GH5100-4002418 | 1-GH5100-31-REP-2418-00 | A1 | 2A |  | 2025-08-01 | CSE-2642-PMT-T-021 | 2025-08-02 | ABL/RINA | 2025-08-19 | 1-GH5100-31-REP-2418-00_A1_CPY1 | approved |  |  | 2025-08-14 | 44988-ABL-DRS-APP-0894 | approved
|  |  |  | 00 |  |  | 2026-02-12 | CSE-2642-PMT-T-044 | 2026-02-13 | ABL/RINA | [5 empty] | 2026-02-18 | AD_G30_44988-ABL-DRS-APP-2565 | approved
4 | MIDLINE TIE-IN ANALYSIS REPORT FOR 12" | CF0000-4002424 | 1-CF0000-31-REP-2424-00 | A1 | 2A |  | 2025-08-11 | CSE-2642-PMT-T-023 | 2025-08-11 | ABL/RINA | 2025-08-27 | 1-CF0000-31-REP-2424-00_A1_cpy1_CRS | approved |  |  | 2025-09-18 | 44988-ABL-DRS-APP-1218 | approved
|  |  |  | 00 | 2A |  | 2025-10-08 | CSE-2642-PMT-T-032 | [7 empty] | 2025-10-13 | AD_G30_44988-ABL-DRS-APP-1501 | approved
5 | MIDLINE TIE-IN ANALYSIS REPORT FOR 16" | CF0000-4002423 | 1-CF0000-31-REP-2423-00 | A1 | 2A |  | 2025-10-01 | CSE-2642-PMT-T-031 | 2025-10-02 | ABL/RINA | 17-10-2025 | TRN-007329 | 2 |  |  | 2025-10-09 | AD_G30_44988-ABL-DRS-APP-1495 | approved
|  |  |  | 00 | 2A |  | 2025-10-25 | CSE-2642-PMT-T-034 | 2025-10-25 | ABL/RINA
6 | RISER/SPOOL LIFT ANALYSIS REPORT AT DC4 (CS PIPELINES) | GH0400-4002419 | 1-GH0400-31-REP-2419-00 | A1 | 2A |  | 2025-12-08 | CSE-2642-PMT-T-036 | 2025-12-10 | ABL/RINA | 2025-12-26 | HGDP-OFCR-00-TRN-007997 |  |  |  | 2026-01-22 | AD_G30_44988-ABL-DRS-APP-2259 | approved | reissued on 09/12
7 | RISER/SPOOL LIFT ANALYSIS REPORT AT GOP-SRP FROM DC6 (CRA PIPELINES) | GH5100-4002552 | 1-GH5100-31-REP-2552-00 | A1 | 2A |  | 2026-02-04 | CSE-2642-PMT-T-038 | 2026-02-04 | ABL/RINA | 2026-03-10 | 1-GH5100-31-REP-2552-00_A1_CPY1_CRS |  |  |  | 2026-02-09 | AD_G30_44988-ABL-DRS-APP-2469 | Approved
8 | DAVIT LIFT ANALYSIS AT GOP SRP | GH5100-4002411 | 1-GH5100-31-REP-2411-00 | A1 | 2A |  | 2026-02-03 | CSE-2642-PMT-T-039 | 2026-02-04 | ABL/RINA | 06-03-2026 30-03-2026 | P0043931-RIN-OFCR-TRN-00077 P0043931-RIN-OFCR-TRN-00084 | approved |  |  | 13-02-2026 27-303-26 | AD_G30_44988-ABL-DRS-DRS-2522 AD_G30_44988-ABL-DRS-APP-3045 | Approved
|  |  |  | B1 | 2A |  | 2026-03-22 | CSE-2642-PMT-T-051
9 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS AND RISERS ON CARGO BARGE – TRIP 1 | GH5100-4002623 | 1-GH5100-31-REP-2623-00 | A1 | 2A |  | 2026-04-10 | CSE-2642-PMT-T-054 | 2026-04-10 | ABL/RINA | 2026-05-04 | 1-GH5100-31-REP-2623-00_A1_CPY1_CRS |  |  |  | 2026-04-20 | AD_G30_44988-ABL-DRS-DRS-3381 | Approved
|  |  |  | 00 | 2A |  | 2026-05-15 | CSE-2642-PMT-T-063 | 2026-05-15 | CPY / MWS | [5 empty] | 2026-05-18 | AD_G30_44988-ABL-DRS-APP-3866 | Approved
|  |  |  | 01 | 2A |  | 2026-06-01 | CSE-2642-PMT-T-070 | 2026-06-02 | CPY / MWS | [5 empty] | 2026-06-03 | AD_G30_44988-ABL-DRS-APP-4066 | Approved
10 | RISER/SPOOL LIFT ANALYSIS AT DC6 (CRA PIPELINES) | GH0600-4002543 | 1-GH0600-31-REP-2543-00 | A1 | 2A |  | 2026-02-24 | CSE-2642-PMT-T-047 | 2026-02-24 | ABL/RINA | 2026-03-23 | 1-GH0600-31-REP-2543-00_A1_CPY1_CRS | approved |  |  | 2026-03-06 | AD_G30_44988-ABL-DRS-APP-2785 | Approved
11 | RISER/SPOOL LIFT ANALYSIS REPORT AT GOP-SRP (CS PIPELINES) BY DLS-4200 | GH5100-4002591 | 1-GH5100-31-REP-2591-00 | A1 | 2A |  | 2026-05-01 | CSE-2642-PMT-T-060 | 2026-05-01 | ABL/RINA | 2026-05-18 | 1-GH5100-31-REP-2591-00_A1_CPY1 | approved |  |  | 10-05-2026 19-05-2026 | AD_G30_44988-ABL-DRS-DRS-3725 AD_G30_44988-ABL-DRS-APP-3910 | Approved
12 | DAVIT LIFT ANALYSIS AT GOP SRP BY DLS-4200 | GH5100-4002592 | 1-GH5100-31-REP-2592-00 | A1 | 2A | BBP | 2026-05-04 | CSE-2642-PMT-T-061 | 2026-05-04 | ABL/RINA | 2026-05-18 | 1-GH5100-31-REP-2592-00_CS-0532 | approved |  |  | 10-05-2026 19-05-2026 | AD_G30_44988-ABL-DRS-DRS-3738 AD_G30_44988-ABL-DRS-APP-3908 | Approved
|  |  |  | 00 | 21 |  | 2026-05-20 | CSE-2642-PMT-T-064 | 2026-05-20 | ABL/RINA | [5 empty] | 2026-05-25 | AD_G30_44988-ABL-DRS-APP-3973 | Approved
13 | RISER/SPOOL LIFT ANALYSIS REPORT AT GOP-SRP (CRA PIPELINES) BY DLS-4200 | GH5100-4002590 | 1-GH5100-31-REP-2590-00 | A1 | 2A |  | 2026-05-06 | CSE-2642-PMT-T-062 | 2026-05-06 | ABL/RINA | 2026-05-18 | 1-GH5100-31-REP-2590-00_A1_CPY1 | approved |  |  | 10-05-2026 19-05-2026 | AD_G30_44988-ABL-DRS-DRS-3723 AD_G30_44988-ABL-DRS-APP-3909 | Approved
14 | DAVIT LIFT ANALYSIS AT DC6 | GH0600-4002417 | 1-GH0600-31-REP-2417-00 | A1 | 2A |  | 2026-05-25 | CSE-2642-PMT-T-068 | 2026-05-25 | ABL/RINA | 18-06-2026 29-07-2026 | 1-GH0600-31-REP-2417-00 P0043931-RIN-OFCR-TRN-00116 | approved |  |  | 2026-06-03 | AD_G30_44988-ABL-DRS-APP-4079 | Approved
|  |  |  | 00 | 2A |  | 2026-07-27 | CSE-2642-PMT-T-088 | 2026-07-27 | ABL/RINA | 2026-08-04 | 1-GH0600-31-REP-2417-00_00_CPY | approved |  |  | 2026-08-03 | AD_G30_44988-ABL-DRS-APP-4891 | Approved
15 | DLS 4200 RISER / SPOOL LIFT ANALYSIS AT DC6 | GH0600-4002654 | 1-GH0600-31-REP-2654-00 | A1 | 2A |  | 2026-06-02 | CSE-2642-PMT-T-071 | 2026-06-02 | ABL/RINA | 2026-06-18 | 1-GH0600-31-REP-2654-00 | approved |  |  | 2026-06-09 | AD_G30_44988-ABL-DRS-APP-4172 | Approved
|  |  |  | 00 | 2A |  | 2026-08-03 | CSE-2642-PMT-T-092 | 2026-08-03 | 2026-08-03 | 2026-08-19 | 1-GH0600-31-REP-2654-00_00 | CODE-1 |  |  | 2026-08-07 | AD_G30_44988-ABL-DRS-APP-4978 | Approved
16 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS AND RISERS ON CARGO BARGE – TRIP 2 | GH0000-4002656 | 1-GH0000-31-REP-2656-00 | A1 | 2A |  | 2026-06-21 | CSE-2642-PMT-T-072 | 2026-06-22 | CPY / MWS | 2026-07-08 | HGDP-OFCR-00-TRN-009407 | approved |  |  | 2026-07-01 | AD_G30_44988-ABL-DRS-APP-4451 | Approved
|  |  |  | 00 | 2A |  | 2026-07-24 | CSE-2642-PMT-T-084 | 2026-07-24 | CPY / MWS | 2026-08-05 | 1-GH0000-31-REP-2656-00_00 | approved | [5 empty] | REISSUED ON 24-07-2026
17 | MIDLINE TIE-IN ANALYSIS REPORT FOR 34" | CF0000-4002422 | 1-CF0000-31-REP-2422-00 | A1 | 2A |  | 2026-09-01 | CSE-2642-PMT-T-106 | 2026-09-01 | CPY / MWS | [5 empty] | 2026-09-04 | AD_G30_44988-ABL-DRS-DRS-5303 | COMMENTS
18 | DAVIT LIFT ANALYSIS AT GOP-NRP | GH5100-4002502 | 1-GH5100-31-REP-2502-00 | A1 | 2A |  | 2026-07-10 | CSE-2642-PMT-T-079 | 2026-07-10 | CPY / MWS / RINA | 2026-07-30 | 1-GH5100-31-REP-2502-00_A1_CPY1 | CODE-1 |  |  | 2026-07-20 | AD_G30_44988-ABL-DRS-APP-4684 | Approved
|  |  |  | 00 | 2A |  | 2026-08-07 | CSE-2642-PMT-T-095 | 2026-08-07 | CPY / MWS / RINA | 2026-08-19 | 1-GH5100-31-REP-2502-00_00 | CODE-1 |  |  | 2026-08-12 | AD_G30_44988-ABL-DRS-APP-5033 | Approved
19 | RISER/SPOOL LIFT ANALYSIS AT GOP-NRP | GH5100-4002503 | 1-GH5100-31-REP-2503-00 | A1 | 2A |  | 2026-07-23 | CSE-2642-PMT-T-086 | 2026-07-24 | CPY / MWS / RINA | 2026-08-11 | 1-GH5100-31-REP-2503-00_A1 | CODE-1
|  |  |  | 00 | 2A |  | 2026-08-31 | CSE-2642-PMT-T-104 | 2026-08-31 | CPY / MWS / RINA | 2026-09-04 | 1-GH5100-31-REP-2503-00_00 | CODE-1
20 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS/RISERS AND RISER PROTECTORS ON CARGO BARGE – TRIP 3 | GH0000-4002683 | 1-GH0000-31-REP-2683-00 | A1 | 2A |  | 2026-08-19 | CSE-2642-PMT-T-098 | 2026-08-19 | CPY / MWS / RINA | 2026-08-25 | 1-GH0000-31-REP-2683-00_A1 1 | code-2 comments |  |  | 2026-08-26 | AD_G30_44988-ABL-DRS-APP-5173 | Approved
|  |  |  | 00 | 2A |  | 2026-08-26 | CSE-2642-PMT-T-101 | 2026-08-26 | CPY / MWS / RINA | 2026-09-04 | 1-GH0000-31-REP-2683-00_00 | CODE-1
21 | DAVIT LIFT ANALYSIS AT DC4 |  | 1-GH0400-31-REP-2415-00
6 | 4" (HG-SP-33) FLEXIBLE PIPELINE INSTALLATION ANALYSIS
7 | 33Kv (HG-SC-3) COMPOSITE CABLE INSTALLATION ANALYSIS
8 | UMBILICALS INSTALLATION ANALYSIS
9 | DAVIT LIFT ANALYSIS AT DC1
10 | DAVIT LIFT ANALYSIS AT DC6
11 | DAVIT LIFT ANALYSIS AT GOP
12 | DAVIT LIFT ANALYSIS REPORT AT GOP-SRP FROM OPP
13 | DAVIT LIFT ANALYSIS REPORT AT GOP-NRP FROM DC4

## Documents - Naval Marine
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
HAIL & GHASHA DEVELOPMENT PROJECT PACKAGE 1 – OFFSHORE FACILITIES
|  | NMDC ENERGY PROJECT NO. 2642 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (Naval) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | MOORING ANALYSIS REPORT FOR JACKET INSTALLATION AT DC1 | GH0100-4002451 | 1-GH0100-31-REP-2451-00 | A1 | CLASS 2A | HZ | 2025-06-29 | CSE-2642-PMT-T-016 | 2025-06-30 | ABL/RINA | [5 empty] | 2025-08-12 | AD_G30_44988-ABL-DRS-DRS-0865 | 3 - comments | RESPONSE SENT TO 12/08/2025 (ABL)
|  |  |  | 00 | CLASS 2A | HZ | 2025-08-14 | CSE-2642-PMT-T-024 | 2025-08-15 | ABL/RINA | 21-08-2025 27-08-2025 | P0043931-RIN-OFCR-TRN-00038 1-GH0100-31-REP-2451-00_00_cpy1_CRS | approved |  |  | 2025-08-19 | AD_G30_44988-ABL-DRS-APP-0951 | approved
|  |  |  | A2 | CLASS 2A | HZ | 2025-09-02 | CSE-2642-PMT-T-028
2 | MOORING ANALYSIS REPORT FOR TOPSIDE/ BRIDGE/RISER INSTALLATION AT DC1 | GH0100-4002458 | 1-GH0100-31-REP-2458-00 | A1 | CLASS 2A | HZ | 2026-03-04 | CSE-2642-PMT-T-050 | 2026-03-04 | CPY, MWS AND RINA | 17-03-2026 27-03-2026 | 1-GH0100-31-REP-2458-00_CS-0487 P0043931-RIN-OFCR-TRN-00084 | approved |  |  | 12-03-2026 30-03-2026 20-04-2026 | AD_G30_44988-ABL-DRS-DRS-2848 AD_G30_44988-ABL-DRS-DRS-3057 AD_G30_44988-ABL-DRS-APP-3348 | approved | response sent on 24-03-2026 by HZ
|  |  |  | 00 | CLASS 2A |  | 2026-05-07 | CSE-2642-PMT-T-055 | 2026-05-09 | CPY, MWS AND RINA | [5 empty] | 2026-05-14 | AD_G30_44988-ABL-DRS-APP-3819 | approved
3 | SAFEEN-3000 MOORING ANALYSIS REPORT FOR JACKET INSTALLATION AT DC4 | GH0400-4002449 | 1-GH0400-31-REP-2449-00 | A1 | CLASS 2A | HZ | 2025-01-14 | CSE-2642-PMT-T-004 |  |  |  | 1-GH0400-31-REP-2449-00_A1_CPY2 | commented
|  |  |  | 00 | CLASS 2A | HZ | 2025-05-16 | CSE-2642-PMT-T-007 | 2025-05-16 | -- | 2025-05-22 | P0043931-RIN-OFCR-TRN-00018 | commented |  | response sent on 09/06/2025 | 12-06-2025 13-06-2025 | AD_G30_44988-ABL-DRS-DRS-0599 1-GH0400-31-REP-2449-00_CS-0490 Rev.2 | comments | RINA approved
|  |  |  | CRS | [9 empty] | 2025-06-19 | CRS 'response sent to mws | 2025-06-26 | aD_G30_44988-ABL-DRS-DRS-0663 | approved
|  |  |  | X101 | CLASS 2A | HZ | 2025-06-29 | CSE-2642-PMT-T-015 | 2025-06-30 | [6 empty] | 2025-07-14 | AD_G30_44988-ABL-DRS-APP-0688 | approved
|  |  |  | 01 | CLASS 2A | HZ | 2025-07-15 | CSE-2642-PMT-T-018 | 2025-07-15 | -- | 2025-07-24 | P0043931-RIN-OFCR-TRN-00034 | approved | 2025-07-24 | -- | 2025-08-04 | AD_G30_44988-ABL-DRS-APP-0827 | approved
4 | MOORING ANALYSIS REPORT FOR TOPSIDE/ BRIDGE/RISER INSTALLATION AT DC/4 | GH0400-4002457 | 1-GH0400-31-REP-2457-00 | A1 | CLASS 2A | HZ | 2026-02-20 | CSE-2642-PMT-T-046 | 2026-02-21 | ABL/RINA | 02-03-2026 09-03-2026 | P0043931-RIN-OFCR-TRN-00074 P0043931-RIN-OFCR-TRN-00078 | approved |  |  | 2026-02-25 | AD_G30_44988-ABL-DRS-APP-2683 | approved
|  |  |  | 00 |  | HZ | 2026-03-24 | CSE-2642-PMT-T-052 |  |  | 2026-03-30 | P0043931-RIN-OFCR-TRN-00085 | approved |  |  | 2026-03-26 | AD_G30_44988-ABL-DRS-APP-3031 | approved
5 | SAFEEN-3000 MOORING ANALYSIS REPORT FOR JACKET INSTALLATION AT DC6 | GH0600-4002450 | 1-GH0600-31-REP-2450-00 | A1 | CLASS 2A | HZ | 2024-12-25 | CSE-2642-PMT-T-003 |  | -- |  | 1-GH0600-31-REP-2450-00_A1_CPY2 | commented
|  |  |  | 00 | CLASS 2A | HZ | 2025-05-16 | CSE-2642-PMT-T-008 | 2025-05-16 | -- | 2025-05-22 | P0043931-RIN-OFCR-TRN-00018 | commented | 2025-06-04 | AD_G30_44988-ABL-DRS-DRS-0502 | 04-06-2025 09-06-2025 13-06-2025 | AD_G30_44988-ABL-DRS-DRS-0502 AD_G30_44988-ABL-DRS-APP-0562 1-GH0600-31-REP-2450-00_CS-0494 Rev.2 | approved
|  |  |  | 01 | CLASS 2A | HZ | 2025-06-16 | CSE-2642-PMT-T-012 | 2025-06-16 | -- | 2025-07-24 | P0043931-RIN-OFCR-TRN-00034 | approved |  |  | 19-06-2025 | AD_G30_44988-ABL-DRS-APP-0632 | comments
6 | MOORING ANALYSIS REPORT FOR TOPSIDE/ BRIDGE/RISER INSTALLATION AT DC/6 | GH0600-4002455 | 1-GH0600-31-REP-2455-00 | A1 | CLASS 2A | HZ | 2026-03-24 | CSE-2642-PMT-T-043 |  | ABL/RINA | 2026-03-30 | P0043931-RIN-OFCR-TRN-00085 | approved |  |  | 27-03-2026 22-04-2026 | AD_G30_44988-ABL-DRS-DRS-3035 AD_G30_44988-ABL-DRS-APP-3414 | Approved
|  |  |  | 00 | CLASS 2A | HZ | 2026-04-23 | CSE-2642-PMT-T-058 |  | ABL/RINA | 2026-05-04 | P0043931-RIN-OFCR-TRN-00091dated | hold |  |  | 2026-05-06 | AD_G30_44988-ABL-DRS-APP-3616 | Approved | Response to RINA sent on 07/05- HZ
7 | MOORING ANALYSIS REPORT FOR JACKET INSTALLATION AT GOP-SRP | GH5100-4002447 | 1-GH5100-31-REP-2447-00 | A1 | CLASS 2A
8 | MOORING ANALYSIS REPORT FOR JACKET INSTALLATION AT GOP-NRP | GH5100-4002448 | 1-GH5100-31-REP-2448-00 | A1 | CLASS 2A |  | 2025-07-07 | CSE-2642-PMT-T-017 | 2025-07-07 | 2025-07-17 | 2025-07-24 | P0043931-RIN-OFCR-TRN-00034 | approved |  |  | 12-08-2025 14-08-2025 | AD_G30_44988-ABL-DRS-DRS-0873 AD_G30_44988-ABL-DRS-APP-0903 | approved
|  |  |  | 00 | CLASS 2A |  | 2025-08-15 | CSE-2642-PMT-T-026 | 2025-08-15 | ABL/RINA | 2025-08-21 | P0043931-RIN-OFCR-TRN-00038 | approved |  |  | 2025-09-04 | AD_G30_44988-ABL-DRS-APP-1086 | approved
9 | MOORING ANALYSIS REPORT FOR JACKET INSTALLATION AT GOP-FLARE | GH5100-4002452 | 1-GH5100-31-REP-2452-00 | A1 | CLASS 2A
10 | MOORING ANALYSIS REPORT FOR JACKET INSTALLATION AT GOP-SWI | GH5100-4002453 | 1-GH5100-31-REP-2453-00 | A1 | CLASS 2A |  | 2025-07-17 | CSE-2642-PMT-T-019 | 2025-07-17 | 2025-07-17 | 24-07-2025 14-08-2025 | P0043931-RIN-OFCR-TRN-00034 & Company | approved |  |  | 2025-08-14 | 44988-ABL-DRS-APP-0890 | approved
|  |  |  | 00 | CLASS 2A | HZ | 2025-08-14 | CSE-2642-PMT-T-024 | 2025-08-15 | ABL/RINA | 21-08-2025 27-08-2025 | P0043931-RIN-OFCR-TRN-00038 1-GH5100-31-REP-2453-00_00_cpy1_CRS | approved |  |  | 2025-08-22 | AD_G30_44988-ABL-DRS-APP-0984 | approved
11 | MOORING ANALYSIS REPORT FOR TOPSIDE/ BRIDGE/RISER INSTALLATION AT GOP-SRP | GH5100-4002454 | 1-GH5100-31-REP-2454-00 | A1 | CLASS 2A |  | 2026-01-30 | CSE-2642-PMT-T-037 | 2026-01-30 | ABL/RINA | 09-02-2026 20-02-2026 | 1-GH5100-31-REP-2454-00_CS-0502 HGDP-OFCR-00-TRN-008507 | commented |  |  | 2026-02-09 | AD_G30_44988-ABL-DRS-APP-2488 | approved
|  |  |  | 00 |  |  | 2026-02-27 | CSE-2642-PMT-T-048 |  | ABL/RINA | 16-03-2026 27-03-2026 | P0043931-RIN-OFCR-TRN-00082 N 1-GH5100-31-REP-2454-00_00 | approved comments
12 | MOORING ANALYSIS REPORT FOR TOPSIDE/ BRIDGE/RISER INSTALLATION AT GOP-NRP | GH5100-4002456 | 1-GH5100-31-REP-2456-00 | A1 | CLASS 2A |  | 2016-02-18 | CSE-2642-PMT-T-045 | 2016-02-19 | ABL/RINA | 02-03-2026 09-03-2026 27-03-2026 | P0043931-RIN-OFCR-TRN-00074 P0043931-RIN-OFCR-TRN-00078 | approved |  |  | 2026-02-25 | AD_G30_44988-ABL-DRS-APP-2676 | approved
|  |  |  | 00 |  |  | 2026-03-25 | CSE-2642-PMT-T-053 |  | ABL/RINA | [5 empty] | 2026-04-08 | AD_G30_44988-ABL-DRS-APP-3184 | approved
13 | MOORING ANALYSIS REPORT FOR TOPSIDE INSTALLATION AT GOP-SWI | GH5100-4002459 | 1-GH5100-31-REP-2459-00 | A1 | CLASS 2A | remarks | 2026-03-04 | CSE-2642-PMT-T-049 | 2026-03-04 | CPY, MWS AND RINA | 2026-03-27 | 1-GH5100-31-REP-2459-00_CS-0504 | commented |  |  | 12-03-2026 27-03-2026 22-04-2026 | AD_G30_44988-ABL-DRS-DRS-2847 AD_G30_44988-ABL-DRS-DRS-3036 AD_G30_44988-ABL-DRS-APP-3416 | approved | Response to ABL / RINA on 24/03/26 - HZ
|  |  |  | 00 | CLASS 2A |  | 2026-04-23 | CSE-2642-PMT-T-059 | 2026-04-27 | CPY, MWS AND RINA | 2026-05-04 | P0043931-RIN-OFCR-TRN-00091dated | hold | [5 empty] | Response to RINA sent on 07/05- HZ
14 | MOORING ANALYSIS REPORT FOR TOPSIDE INSTALLATION AT GOP-FLARE | GH5100-4002460 | 1-GH5100-31-REP-2460-00 | A1 | CLASS 2A
15 | MOORING ANALYSIS REPORT FOR TOPSIDE INSTALLATION AT CLQ | GH6000-4002425 | 1-GH6000-31-REP-2425-00 | A1 | CLASS 2A
16 | MOORING ANALYSIS REPORT AT CLQ | GH6000-4002426 | 1-GH6000-31-REP-2426-00 | A1 | CLASS 2A |  | 2025-05-16 | CSE-2642-PMT-T-009 | 2025-05-16 | -- | 2025-05-22 | AD_G30_44988-ABL-DRS-DRS-0538 | commented |  | response sent on 09/06/2025 | 04-06-2025 13-06-2025 | AD_G30_44988-ABL-DRS-DRS-0538 1-GH6000-31-REP-2426-00_CS-0513 Rev.1 | RINA APPROVED
|  |  |  | 00 | CLASS 2A |  | 2025-06-16 | CSE-2642-PMT-T-012 | 2025-06-16 | -- | [5 empty] | 2025-06-19 | AD_G30_44988-ABL-DRS-DRS-0631 | comments
|  |  |  | CRS | [9 empty] | 19-06-2025 23-06-2025 | response sent to MWS on 19/06/2025 response sent to mws on 23/06 | 2025-06-23 | AD_G30_44988-ABL-DRS-DRS-0639 | -- | RESPONSE SENT TO 23/06/205
|  |  |  | X101 | CLASS 2A |  | 2025-06-24 | CSE-2642-PMT-T-013 | [7 empty] | 2025-06-26 | AD_G30_44988-ABL-DRS-APP-0660 | approved
|  |  |  | 01 | CLASS 2A |  | 27-06-2025 04-07-2025 | CSE-2642-PMT-T-014 |  |  | 2025-07-24 | P0043931-RIN-OFCR-TRN-00034 | approved
17 | MOORING ANALYSIS FOR FRAME REMOVAL AT GOP SRP | GH5100-4002555 | 1-GH5100-31-REP-2555-00 | A1 | CLASS 2A | HZ | 2025-04-22 | CSE-2642-PMT-T-006 |  | -- | 2025-05-05 | 1-GH5100-31-REP-2555-00_A1_CPY-1 | approved
|  |  |  | 00 | CLASS 2A |  | 2025-05-18 | CSE-2642-PMT-T-010 | 2025-05-16 | -- | 22-05-2025 18-06-2025 | P0043931-RIN-OFCR-TRN-00018 1-GH5100-31-REP-2555-00_00_CPY1 | approved |  | response sent on 09/06/2025 | 2025-06-13 | 1-GH5100-31-REP-2555-00_CS-0514 Rev.1 | approved
18 | MOORING ANALYSIS REPORT FOR PIPELINE MIDLINE TIE-IN (16" & 12" PIPELINES BETWEEN GOP SOUTH AND OPP | GH5100-4002578 | 1-GH5100-31-REP-2578-00 | A1 | CLASS 2A | HZ | 2025-09-25 | CSE-2642-PMT-T-030 | 2025-09-25 | ABL/RINA | 2025-10-06 | HGDP-OFCR-00-TRN-007210 | commented |  |  | 2025-10-09 | AD_G30_44988-ABL-DRS-APP-1482 | approved
|  |  |  | 00 | CLASS 2A | HZ | 2025-10-21 | CSE-2642-PMT-T-033 | 2025-10-21 | ABL/RINA | 2025-10-28 | P0043931-RIN-OFCR-TRN-00054 | approved |  |  | 2025-11-04 | AD_G30_44988-ABL-DRS-APP-1640 | approved
|  |  |  | 01 | CLASS 2A | HZ | 2025-11-06 | CSE-2642-PMT-T-035 | 2025-11-06 | ABL/RINA | 2025-11-12 | P0043931-RIN-OFCR-TRN-00058 | approved |  |  | 2025-11-12 | AD_G30_44988-ABL-DRS-APP-1691 | approved | Rev-02 (YH's email dated 18/11 It is not required)
19 | STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS/ RISER TRIP-1 | GH5100-4002624 | 1-GH5100-31-CNN-2624-00 | A1 | CLASS 2A | HZ | 2026-04-10 | CSE-2642-PMT-T-054 | 2026-04-10 | ABL/RINA | 2026-05-04 | 1-GH5100-31-CNN-2624-00_A1_CPY1_CRS |  |  |  | 20-04-2026 14-05-2026 | AD_G30_44988-ABL-DRS-DRS-3388 AD_G30_44988-ABL-DRS-APP-3830 | approved | response sent to ABL on 12/05 HZ
|  |  |  | 00 | CLASS 2A |  | 2026-05-15 | CSE-2642-PMT-T-063 | 2026-05-15 | CPY / MWS | [5 empty] | 2026-05-19 | AD_G30_44988-ABL-DRS-APP-3911 | approved
|  |  |  | 01 | CLASS 2A |  | 2026-06-01 | CSE-2642-PMT-T-070 | 2026-06-02 | CPY / MWS | 98-06-2026 | 1-GH5100-31-CNN-2624-00_01_CRS | approved |  |  | 2026-06-03 | AD_G30_44988-ABL-DRS-APP-4064 | approved
20 | DLS-4200 MOORING ANALYSIS REPORT AT DC1 | GH5100-4002630 | 1-GH0100-31-REP-2630-00 |  |  |  | 2026-08-18
21 | DLS-4200 MOORING ANALYSIS REPORT AT DC4 | GH0400-4002631 | 1-GH0400-31-REP-2631-00 | A1 | CLASS 2A |  | 2026-06-26 | CSE-2642-PMT-T-074 | 2026-06-26 | CPY / MWS / RINA | 03-07-2026 08-07-2026 | P0043931-RIN-OFCR-TRN-00104 H HGDP-OFCR-00-TRN-009407 | approved |  |  | 03-07-2026 14-07-2026 | AD_G30_44988-ABL-DRS-DRS-4484 AD_G30_44988-ABL-DRS-DRS-4613 | COMMENTS | response sent to ABL on 10/07 HZ
|  |  |  | X100 | CLASS 2A |  | 2026-07-16 | CSE-2642-PMT-T-080 | 2026-07-16 | ABL/RINA | 2026-07-22 | P0043931-RIN-OFCR-TRN-00112 | HOLD
|  |  |  | X200 | CLASS 2A |  | 2026-07-23 | CSE-2642-PMT-T-087 | 2026-07-24 | 2026-08-06 | 2026-07-27 | P0043931-RIN-OFCR-TRN-00115 H | approved |  |  | 2026-07-28 | AD_G30_44988-ABL-DRS-APP-4830 | APPROVED
|  |  |  | 00 | CLASS 2A |  | 2026-08-06 | CSE-2642-PMT-T-094 | 2026-08-06 | CPY / MWS / RINA | 2026-08-19 | P0043931-RIN-OFCR-TRN-00119 | approved |  |  | 2026-08-10 | AD_G30_44988-ABL-DRS-APP-4999 | APPROVED
|  |  |  | 01 | CLASS 2A |  | 2026-08-27 | CSE-2642-PMT-T-102
22 | DLS-4200 MOORING ANALYSIS REPORT AT DC6 | GH0600-4002632 | 1-GH0600-31-REP-2632-00 | A1 | CLASS 2A | HZ | 2026-04-23 | CSE-2642-PMT-T-057 | 2026-04-23 | ABL/RINA | 05-05-2026 11-05-2026 | P0043931-RIN-OFCR-TRN-00092 1-GH0600-31-REP-2632-00_A1_CPY3 | approved |  |  | 01-05-2026 08-05-2026 | AD_G30_44988-ABL-DRS-DRS-3584 AD_G30_44988-ABL-DRS-APP-3666 | APPROVED | crs sent to HZ RINA response sent on 07/05
|  |  |  | A2 | CLASS 2A |  | 2026-05-25 | CSE-2642-PMT-T-067 | 2026-05-25 | ABL/RINA | 2026-06-08 | P0043931-RIN-OFCR-TRN-00101 1-GH0600-31-REP-2632-00_A2_CRS | approved |  |  | 2026-06-03 | AD_G30_44988-ABL-DRS-APP-4072 | APPROVED
23 | DLS-4200 MOORING ANALYSIS REPORT AT GOP-SRP | GH5100-4002633 | 1-GH5100-31-REP-2633-00 | A1 | CLASS 2A | HZ | 2026-04-22 | CSE-2642-PMT-T-056 | 2026-04-23 | ABL/RINA | 05-05-2026 11-05-2026 01-06-2026 | P0043931-RIN-OFCR-TRN-00092 '1-GH5100-31-REP-2633-00_A1_CPY2 P0043931-RIN-OFCR-TRN-00099 N | approved |  |  | 01-05-2026 08-05-2026 | AD_G30_44988-ABL-DRS-DRS-3583 AD_G30_44988-ABL-DRS-APP-3665 | APPROVED | crs sent to HZ RINA response sent on 07/05
|  |  |  | A2 | CLASS 2A | remarks |  | CSE-2642-PMT-T-066 | 2026-05-22 | CPY / MWS | 08-06-2026 11-06-2026 | P0043931-RIN-OFCR-TRN-00102 P0043931-RIN-OFCR-TRN-00103 N | approved |  |  | 2026-06-03 | AD_G30_44988-ABL-DRS-APP-4071 | APPROVED | this report is cancelled
24 | DLS-4200 MOORING ANALYSIS REPORT AT GOP-NRP | GH5100-4002634 | 1-GH5100-31-REP-2634-00 | A1 | CLASS 2A |  | 2026-08-24 | CSE-2642-PMT-T-100 | 2026-08-26 | CPY / MWS / RINA | 02-09-2026 04-09-2026 | 1-GH5100-31-REP-2634-00_CS-0543 1-GH5100-31-REP-2634-00_A1 | Code 1 - No Comments |  |  | 2026-08-27 | AD_G30_44988-ABL-DRS-APP-5190 | APPROVED | REISSUED ON 26/08 | response sent to Rina on 03/09 - M.ASH
|  |  |  | 00 | CLASS 2A |  | 2026-09-07 | CSE-2642-PMT-T-107 | 2026-09-07 | CPY / MWS / RINA
25 | DLS-4200 MOORING ANALYSIS REPORT AT GOP-SWI | GH5100-4002635 | 1-GH5100-31-REP-2635-00 | A1 | CLASS 2A |  | 2026-08-13 | CSE-2642-PMT-T-096 | 2026-08-13 | CPY / MWS | 24-08-2026 31-08-2026 | P0043931-RIN-OFCR-TRN-00121 P0043931-RIN-OFCR-TRN-00122 | approved |  |  | 2026-08-19 | AD_G30_44988-ABL-DRS-APP-5094 | APPROVED | response sent to ARINA on 25/08 HZ
26 | DLS-4200 MOORING ANALYSIS REPORT AT GOP-FLARE | GH5100-4002636 | 1-GH5100-31-REP-2636-00 | A1 | CLASS 2A |  | 2026-07-02 | CSE-2642-PMT-T-076 | 2026-07-07 | CPY / MWS / RINA | 2026-07-13 | P0043931-RIN-OFCR-TRN-00108 | HOLD |  |  | 2026-07-09 | AD_G30_44988-ABL-DRS-DRS-4588 | COMMENTS | response sent to ABL on 10/07 HZ | response sent to Rina on 14/07 - HZ
|  |  |  | X1A2 | CLASS 2A |  | 2026-07-15 | CSE-2642-PMT-T-080 | 2026-07-16 | ABL/RINA | 2026-07-23 | 1-GH5100-31-REP-2636-00_CS-0538 | approved |  |  | 2026-07-20 | AD_G30_44988-ABL-DRS-APP-4694 | APPROVED
|  |  |  | 00 | CLASS 2A |  | 2026-07-30 | CSE-2642-PMT-T-090 | 2026-07-30 | CPY / MWS / RINA | 2026-08-19 | 1-GH5100-31-REP-2636-00_00 P0043931-RIN-OFCR-TRN-00119 | Code 1 - No Comments |  |  | 2026-08-03 | AD_G30_44988-ABL-DRS-APP-4906 | APPROVED
27 | DLS-4200 MOORING ANALYSIS REPORT AT CLQ | GH6000-4002637 | 1-GH6000-31-REP-2637-00 | A1 | CLASS 2A |  | 2026-07-06 | CSE-2642-PMT-T-078 | 2026-07-07 | CPY / MWS / RINA | 2026-07-13 | P0043931-RIN-OFCR-TRN-00108 | HOLD |  |  | 2026-07-09 | AD_G30_44988-ABL-DRS-DRS-4587 | COMMENTS | response sent to ABL on 10/07 HZ | response sent to Rina on 14/07 - HZ
|  |  |  | X1A2 | CLASS 2A |  | 2026-07-16 | CSE-2642-PMT-T-081 | 2026-07-16 | ABL/RINA | 2026-07-28 | P0043931-RIN-OFCR-TRN-00114 N | approved |  |  | 2026-07-20 | AD_G30_44988-ABL-DRS-APP-4693 | APPROVED
|  |  |  | 00 | CLASS 2A |  | 2026-07-30 | CSE-2642-PMT-T-090 | 2026-07-30 | CPY / MWS / RINA | 2026-08-19 | 1-GH6000-31-REP-2637-00_00 P0043931-RIN-OFCR-TRN-00119 | Code 1 - No Comments |  |  | 2026-08-03 | AD_G30_44988-ABL-DRS-APP-4903 | APPROVED
28 | SURFACE MIDLINE INSTALLATION PROCEDURE (DLS-4200) | CF0000-4002638 | 1-CF0000-31-PRO-2638-00 |  |  |  | 2026-04-25
29 | DLS-4200 MOORING ANALYSIS REPORT FOR MIDLINE TIEIN 34" & 12” (HG-SP-28 & HG-SP-31) | CF0000-4002639 | 1-GH5100-31-REP-2639-00 | A1 | CLASS 2A |  | 2026-08-17 | CSE-2642-PMT-T-097 | 2026-08-26 | CPY / MWS / RINA | 2026-09-01 | P0043931-RIN-OFCR-TRN-00124 H | HOLD |  |  | 2026-09-04 | AD_G30_44988-ABL-DRS-APP-5297 | APPROVED | response sent to RINA on 02-09-26 M.ASH
30 | MIDLINE TIE-IN ANALYSIS REPORT FOR HG-SP-28 (DLS-4200) | CF0000-4002640 | 1-CF0000-31-REP-2640-00 |  |  |  | 2026-04-25
31 | MIDLINE TIE-IN ANALYSIS REPORT FOR HG-SP-31 (DLS-4200) | CF0000-4002641 | 1-CF0000-31-REP-2641-00 |  |  |  | 2026-04-25
32 | STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS / RISER TRIP-2 | GH0000-4002657 | 1-GH0000-31-CNN-2657-00 | A1 | CLASS 2A |  | 2026-06-21 | CSE-2642-PMT-T-072 | 2026-06-22 | CPY / MWS | 2026-07-15 | 1-GH0000-31-CNN-2657-00_A1_CPY1 | approved |  |  | 2026-07-01 | AD_G30_44988-ABL-DRS-APP-4452 | APPROVED
|  |  |  | 00 | CLASS 2A |  | 2026-07-17 | CSE-2642-PMT-T-084 | 2026-07-22 | CPY / MWS | 2026-08-05 | 1-GH0000-31-CNN-2657-00_00_CPY | approved |  |  | 2026-07-27 | AD_G30_44988-ABL-DRS-APP-4809 | APPROVED
33 | SAFEEN 3000 MOORING ANALYSIS REPORT FOR MIDLINE TIEIN 34" & 12” (HG-SP-28 & HG-SP-31) | GH5100-4002639 | 1-GH5100-31-REP-2639-00
34 | DLS-4200 MOORING ANALYSIS REPORT AT GOP-SRP (TOPSIDE, BRIDGES & RISER PROTECTORS | GH5100-4002682 | 1-GH5100-31-REP-2682-00 | A1 | CLASS 2A |  | 2026-06-30 | CSE-2642-PMT-T-075 | 2026-06-30 | CPY / MWS / RINA | 2026-07-07 | P0043931-RIN-OFCR-TRN-00107 | approved |  |  | 07-07-2026 09-07-2026 | AD_G30_44988-ABL-DRS-DRS-4561 AD_G30_44988-ABL-DRS-DRS-4589 | COMMENTS | RESPONSE TO ABL's COMMENTS ON 08-07-2026 HZ
|  |  |  | X100 | CLASS 2A |  | 2026-07-16 | CSE-2642-PMT-T-083 | 2026-07-16 | ABL | [5 empty] | 2026-07-20 | AD_G30_44988-ABL-DRS-APP-4681 AD_G30_44988-ABL-DRS-APP-4751 | APPROVED
|  |  |  | 00 | CLASS 2A |  | 2026-07-21 | CSE-2642-PMT-T-085 | 2026-07-21 | CPY / MWS / RINA | 2026-07-28 | P0043931-RIN-OFCR-TRN-00114 N | approved
35 | STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS/ RISERS & RISER PROTECTORS TRIP-3 | GH0000-4002684 | 1-GH0000-31-CNN-2684-00 | A1 | CLASS 2A |  | 2026-08-19 | CSE-2642-PMT-T-098 | 2026-08-19 | CPY / MWS / RINA | 2026-08-25 | 1-GH0000-31-CNN-2684-00_A1 | code-2 comments |  |  | 2026-08-26 | AD_G30_44988-ABL-DRS-APP-5175 | APPROVED
|  |  |  | 00 | CLASS 2A |  | 2026-08-26 | CSE-2642-PMT-T-101 | 2026-08-26 | CPY / MWS / RINA | 2026-09-04 | 1-GH0000-31-CNN-2684-00_00 | CODE-1 APPROVED

## Drawings
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
HAIL & GHASHA DEVELOPMENT PROJECT PACKAGE 1 – OFFSHORE FACILITIES
|  | NMDC ENERGY PROJECT NO. 2642 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (Drawings) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | 16" RISER/SPOOL LIFTING DRAWINGS AT GOP FROM OPP (HG-SP-32) | GH5100-4002427 | 1-GH5100-31-DWG-2427-00 | E1 | 3 |  | 2025-06-02 | CSE-2642-PMT-T-011 | 2025-06-02 | -- | 2025-06-18 | HGDP-OFCR-00-TRN-006059 | 4 |  |  | 2025-08-13 | AD_G30_44988-ABL-DRS-DRS-0879
|  |  |  | E2 | 3 |  | 2026-02-12 | CSE-2642-PMT-T-044 | 2026-02-12 | to ABL / RINA | [5 empty] | 2026-03-05 | AD_G30_44988-ABL-DRS-APP-2760 | Approved
2 | 16" RISER/SPOOL LIFTING DRAWINGS AT GOP FROM OPP (HG-SP-30) | GH5100-4002428 | 1-GH5100-31-DWG-2428-00 | E1 | 3 |  | 2025-06-02 | CSE-2642-PMT-T-011 | 2025-06-02 | -- | 2025-06-18 | HGDP-OFCR-00-TRN-006059 | 4 |  |  | 2025-08-13 | AD_G30_44988-ABL-DRS-DRS-0879
|  |  |  | E2 | 3 |  | 2026-02-12 | CSE-2642-PMT-T-044 | 2026-02-24 | to ABL / RINA | [5 empty] | 2026-03-05 | AD_G30_44988-ABL-DRS-APP-2759 | Approved
3 | 12" RISER / SPOOL LIFTING DRAWING AT GOP FROM OPP (HG-SP-31) | GH500-4002429 | 1-GH5100-31-DWG-2429-00 | E1 | 3 |  | 2026-02-12 | CSE-2642-PMT-T-044 | 2026-02-13 | to ABL / RINA | 2026-03-26 | 1-GH5100-31-DWG-2429-00_E1_CPY4_CRS | comments |  |  | 2026-02-18 | AD_G30_44988-ABL-DRS-APP-2650 | Approved
4 | 6" RISER/SPOOL LIFTING DRAWING AT GOP FROM DC6 (HG-SP-24) | GH5100-4002433 | 1-GH5100-31-DWG-2433-00 | E1 | 3 |  | 2025-07-25 | CSE-2642-PMT-T-020 | 2025-07-28 | to ABL / RINA | 2025-08-19 | HGDP-OFCR-00-TRN-006681 | 4 |  |  | 2025-08-14 | 44988-ABL-DRS-APP-0891 | Approved
|  |  |  | E2 | 3 |  | 2026-02-04 | CSE-2642-PMT-T-041 | 2026-02-04 | to ABL / RINA | 2026-02-17 | HGDP-OFCR-00-TRN-008491 | 4 |  |  | 2026-02-18 | AD_G30_44988-ABL-DRS-APP-2563 | Approved
5 | 6" RISER/SPOOL LIFTING DRAWING AT GOP FROM DC6 (HG-SP-23) | GH5100-4002434 | 1-GH5100-31-DWG-2434-00 | E1 | 3 |  | 2025-07-25 | CSE-2642-PMT-T-020 | 2025-07-28 | to ABL / RINA | 2025-08-19 | HGDP-OFCR-00-TRN-006681 | 4 |  |  | 2025-08-14 | 44988-ABL-DRS-APP-0892 | Approved
|  |  |  | E2 | 3 |  | 2026-02-04 | CSE-2642-PMT-T-041 | 2026-02-04 | to ABL / RINA | 2026-02-17 | HGDP-OFCR-00-TRN-008491 | 4 |  |  | 2026-02-18 | AD_G30_44988-ABL-DRS-APP-2564 | Approved
6 | LIFTING DRAWING FOR FRAME REMOVAL AT GOP-SRP | GH5100-4002556 | 1-GH5100-31-DWG-2556-00 | A1 | 2 |  | 2025-08-08 | CSE-2642-PMT-T-022 | 2025-08-08 | to ABL / RINA | 2025-08-26 | 1-GH5100-31-DWG-2556-00_A1_CPY2 | comments
|  |  |  | 00 | 2 |  | 2025-09-06 | CSE-2642-PMT-T-027 | 2025-09-08 | to ABL / RINA
|  |  |  | 01 | 2 |  | 2025-09-24 | CSE-2642-PMT-T-029
7 | 8" RISER/SPOOL LIFTING DRAWING AT DC4 | GH0400-4002441 | 1-GH0400-31-DWG-2441-00 | E1 | 2 |  | 2025-12-08 | CSE-2642-PMT-T-036 | 2025-12-09 | to ABL / RINA | 2025-12-26 | HGDP-OFCR-00-TRN-008021 | 4 |  |  | 2026-01-22 | AD_G30_44988-ABL-DRS-APP-2256 | Approved
8 | 14" RISER/SPOOL LIFTING DRAWING AT DC4 | GH0400-4002442 | 1-GH0400-31-DWG-2442-00 | E1 | 2 |  | 2025-12-08 | CSE-2642-PMT-T-036 | 2025-12-09 | to ABL / RINA | 2025-12-26 | HGDP-OFCR-00-TRN-008021 | 4 |  |  | 2026-01-22 | AD_G30_44988-ABL-DRS-APP-2257 | Approved
9 | 10" RISER/SPOOL LIFTING DRAWING AT DC4 | GH0400-4002444 | 1-GH0400-31-DWG-2444-00 | E1 | 2 |  | 2025-12-08 | CSE-2642-PMT-T-036 | 2025-12-09 | to ABL / RINA | 2025-12-26 | HGDP-OFCR-00-TRN-008021 | 4 |  |  | 2026-01-22 | AD_G30_44988-ABL-DRS-APP-2258 | Approved
10 | 34" RISER/SPOOL LIFTING DRAWINGS AT GOP FROM OPP (HG-SP-28) | GH5100-4002430 | 1-GH5100-31-DWG-2430-00 | E1 | 2 |  | 2026-02-04 | CSE-2642-PMT-T-040 | 2026-02-04 | to ABL / RINA | 2026-02-20 | HGDP-OFCR-00-TRN-008470 | 4 |  |  | 2026-02-09 | AD_G30_44988-ABL-DRS-APP-2466 | Approved
11 | 12" RISER/SPOOL LIFTING DRAWING AT GOP FROM DC6 | GH5100-4002431 | 1-GH5100-31-DWG-2431-00 | E1 | 2 |  | 2026-02-04 | CSE-2642-PMT-T-040 | 2026-02-04 | to ABL / RINA | 2026-02-20 | HGDP-OFCR-00-TRN-008470 | 4 |  |  | 2026-02-09 | AD_G30_44988-ABL-DRS-APP-2467 | Approved
12 | 20" RISER/SPOOL LIFTING DRAWING AT GOP FROM DC6 | GH5100-4002432 | 1-GH5100-31-DWG-2432-00 | E1 | 2 |  | 2026-02-04 | CSE-2642-PMT-T-040 | 2026-02-04 | to ABL / RINA | 2026-02-20 | HGDP-OFCR-00-TRN-008476 | 4 |  |  | 2026-02-09 | AD_G30_44988-ABL-DRS-APP-2468 | Approved
13 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF RISERS/SPOOLS ON CARGO BARGE – TRIP 1 | GH5100-4002622 | 1-GH5100-31-DWG-2622-00 | A1 | 2 |  | 2026-04-10 | CSE-2642-PMT-T-054 | 2026-04-10 | to ABL / RINA | 2026-05-04 | 1-GH5100-31-DWG-2622-00_A1_CPY2_CRS |  |  |  | 2026-04-20 | AD_G30_44988-ABL-DRS-APP-3380 | Approved
|  |  |  | 00 | 2 |  | 2026-05-15 | CSE-2642-PMT-T-063 | 2026-05-15 | CPY / MWS | [5 empty] | 2026-05-19 | AD_G30_44988-ABL-DRS-APP-3912 | Approved
|  |  |  | 01 | 2 |  | 2026-06-01 | CSE-2642-PMT-T-069 | 2026-06-01 | CPY / MWS | 2026-06-09 | 1-GH5100-31-DWG-2622-00_01_CRS |  |  |  | 2026-06-03 | AD_G30_44988-ABL-DRS-APP-4065 | Approved
14 | 12” RISER/SPOOL LIFTING DRAWING AT DC6 | GH0600-4002435 | 1-GH0600-31-DWG-2435-00 | E1 | 2 |  | 2026-02-24 | CSE-2642-PMT-T-047 | 2026-02-27 | to ABL / RINA | [5 empty] | 2026-03-06 | AD_G30_44988-ABL-DRS-APP-2783 | Approved
15 | 20” RISER/SPOOL LIFTING DRAWING AT DC6 | GH0600-4002436 | 1-GH0600-31-DWG-2436-00 | E1 | 2 |  | 2026-02-24 | CSE-2642-PMT-T-047 | 2026-02-27 | to ABL / RINA | [5 empty] | 2026-03-06 | AD_G30_44988-ABL-DRS-APP-2784 | Approved
16 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF RISERS/SPOOLS ON CARGO BARGE (TRIP-1) | GH0600-4002481 | 1-GH0600-31-PLN-2481-00 | E1 | 2 |  | 2026-04-06 | CSE-2642-PMT-T-054
17 | 12" RISER/SPOOL LIFTING DRAWING AT GOP FROM OPP BY DLS-4200 (HG-SP-31) | GH5100-4002582 | 1-GH5100-31-DWG-2582-00 | E1 | 2 |  | 2026-05-01 | CSE-2642-PMT-T-060 | 2026-05-01 | to ABL / RINA | 2026-05-18 | 1-GH5100-31-DWG-2582-00_E1_CPY4 | COMMENTS |  |  | 06-05-2026 19-05-2026 | AD_G30_44988-ABL-DRS-DRS-3620 AD_G30_44988-ABL-DRS-APP-3903 | Approved
|  |  |  | E2 | 2 |  | 2026-05-20 | CSE-2642-PMT-T-064 | 2026-05-21 | to CPY, ABL & RINA |  | 1-GH5100-31-DWG-2582-00_E2 |  |  |  | 2026-06-02 | AD_G30_44988-ABL-DRS-APP-4023 | Approved
18 | 16" RISER/SPOOL LIFTING DRAWING AT GOP FROM OPP BY DLS-4200 (HG-SP-30) | GH5100-4002583 | 1-GH5100-31-DWG-2583-00 | E1 | 2 |  | 2026-05-01 | CSE-2642-PMT-T-060 | 2026-05-01 | to ABL / RINA | 2026-05-18 | 1-GH5100-31-DWG-2583-00_E1_CPY4 | COMMENTS |  |  | 06-05-2026 19-05-2026 | AD_G30_44988-ABL-DRS-DRS-3621 AD_G30_44988-ABL-DRS-APP-3904 | Approved
|  |  |  | E2 | 2 |  | 2026-05-20 | CSE-2642-PMT-T-064 | 2026-05-21 | to CPY, ABL & RINA |  | 1-GH5100-31-DWG-2583-00_E2 |  |  |  | 2026-06-02 | AD_G30_44988-ABL-DRS-APP-4024 | Approved
19 | 16" RISER/SPOOL LIFTING DRAWING AT GOP FROM OPP BY DLS-4200 (HG-SP-32) | GH5100-4002584 | 1-GH5100-31-DWG-2584-00 | E1 | 2 |  | 2026-05-01 | CSE-2642-PMT-T-060 | 2026-05-01 | to ABL / RINA | 2026-05-18 | 1-GH5100-31-DWG-2584-00_E1_CPY4 | COMMENTS |  |  | 06-05-2026 19-05-2026 | AD_G30_44988-ABL-DRS-DRS-3622 AD_G30_44988-ABL-DRS-APP-3905 | Approved
|  |  |  | E2 | 2 |  | 2026-05-20 | CSE-2642-PMT-T-064 | 2026-05-21 | to CPY, ABL & RINA |  | 1-GH5100-31-DWG-2584-00_E2 |  |  |  | 2026-06-02 | AD_G30_44988-ABL-DRS-APP-4025 | Approved
20 | 6" RISER/SPOOL LIFTING DRAWING AT GOP FROM DC6 BY DLS-4200 (HG-SP-23) | GH5100-4002585 | 1-GH5100-31-DWG-2585-00 | E1 | 2 |  | 2026-05-01 | CSE-2642-PMT-T-060 | 2026-05-01 | to ABL / RINA | 2026-05-18 | 1-GH5100-31-DWG-2585-00_E1_CPY4 | COMMENTS |  |  | 06-05-2026 19-05-2026 | AD_G30_44988-ABL-DRS-DRS-3623 AD_G30_44988-ABL-DRS-APP-3906 | Approved
|  |  |  | E2 | 2 |  | 2026-05-20 | CSE-2642-PMT-T-064 | 2026-05-21 | to CPY, ABL & RINA |  | 1-GH5100-31-DWG-2585-00_E2 |  |  |  | 2026-06-02 | AD_G30_44988-ABL-DRS-APP-4026 | Approved
|  |  |  | E3 | 2 |  | 2026-07-17 | CSE-2642-PMT-T-084 | 2026-07-22 | to CPY, ABL & RINA
|  |  |  | A1 | 2 |  | 2026-08-03 | CSE-2642-PMT-T-093 | [7 empty] | 2026-08-07 | AD_G30_44988-ABL-DRS-APP-4965 | Approved
21 | 6" RISER/SPOOL LIFTING DRAWING AT GOP FROM DC6 BY DLS-4200 (HG-SP-24) | GH5100-4002586 | 1-GH5100-31-DWG-2586-00 | E1 | 2 |  | 2026-05-01 | CSE-2642-PMT-T-060 | 2026-05-01 | to ABL / RINA | 2026-05-18 | 1-GH5100-31-DWG-2586-00_E1_CPY4 | COMMENTS |  |  | 06-05-2026 19-05-2026 | AD_G30_44988-ABL-DRS-DRS-3624 AD_G30_44988-ABL-DRS-APP-3907 | Approved
|  |  |  | E2 | 2 |  | 2026-05-20 | CSE-2642-PMT-T-064 | 2026-05-21 | to CPY, ABL & RINA | [5 empty] | 2026-06-02 | AD_G30_44988-ABL-DRS-APP-4027 | Approved
|  |  |  | E3 | 2 |  | 2026-06-06 | CSE-2642-PMT-T-077 | 2026-06-06 | to CPY, ABL & RINA |  | 1-GH5100-31-DWG-2586-00_E3 |  |  |  | 2026-06-08 | AD_G30_44988-ABL-DRS-APP-4564 | Approved
22 | 34" RISER/SPOOL LIFTING DRAWING AT GOP FROM OPP BY DLS-4200 (HG-SP-28) | GH5100-4002587 | 1-GH5100-31-DWG-2587-00 | E1 | 2 |  | 2026-05-06 | CSE-2642-PMT-T-062 | 2026-05-06 | to ABL / RINA | 2026-05-18 | 1-GH5100-31-DWG-2587-00_E1_CPY4 | COMMENTS |  |  | 2026-05-10 | AD_G30_44988-ABL-DRS-APP-3720 | Approved
|  |  |  | E2 | 2 |  | 2026-05-20 | CSE-2642-PMT-T-064 | 2026-05-21 | to CPY, ABL & RINA |  | 1-GH5100-31-DWG-2587-00_E2 |  |  |  | 2026-06-02 | AD_G30_44988-ABL-DRS-APP-4029 | Approved
23 | 12" RISER/SPOOL LIFTING DRAWING AT GOP FROM DC6 BY DLS-4200 (HG-SP-21) | GH5100-4002588 | 1-GH5100-31-DWG-2588-00 | E1 | 2 |  | 2026-05-06 | CSE-2642-PMT-T-062 | 2026-05-06 | to ABL / RINA | 2026-05-18 | 1-GH5100-31-DWG-2588-00_E1_CPY4 | COMMENTS |  |  | 2026-05-10 | AD_G30_44988-ABL-DRS-APP-3721 | Approved
|  |  |  | E2 | 2 |  | 2026-05-20 | CSE-2642-PMT-T-064 | 2026-05-21 | to CPY, ABL & RINA |  | 1-GH5100-31-DWG-2588-00_E2 |  |  |  | 2026-06-02 | AD_G30_44988-ABL-DRS-APP-4030 | Approved
|  |  |  | E3 | 2 |  | 2026-07-17 | CSE-2642-PMT-T-084 | 2026-07-22 | to CPY, ABL & RINA
|  |  |  | A1 | 2 |  | 2026-08-03 | CSE-2642-PMT-T-093 | 2026-08-03 | to CPY, ABL & RINA | [5 empty] | 2026-08-07 | AD_G30_44988-ABL-DRS-APP-4966 | Approved
24 | 20" RISER/SPOOL LIFTING DRAWING AT GOP FROM DC6 BY DLS-4200 (HG-SP-22) | GH5100-4002589 | 1-GH5100-31-DWG-2589-00 | E1 | 2 |  | 2026-05-06 | CSE-2642-PMT-T-062 | 2026-05-06 | to ABL / RINA | 2026-05-18 | 1-GH5100-31-DWG-2589-00_E1_CPY4 | COMMENTS |  |  | 2026-05-10 | AD_G30_44988-ABL-DRS-APP-3724 | Approved
|  |  |  | E2 | 2 |  | 2026-05-20 | CSE-2642-PMT-T-064 | 2026-05-21 | to CPY, ABL & RINA |  | 1-GH5100-31-DWG-2589-00_E2. |  |  |  | 2026-06-02 | AD_G30_44988-ABL-DRS-APP-4031 | Approved
|  |  |  | E3 | 2 |  | 2026-07-17 | CSE-2642-PMT-T-084 | 2026-07-22 | to CPY, ABL & RINA
|  |  |  | A1 | 2 |  | 2026-08-03 | CSE-2642-PMT-T-093 | 2026-08-03 | to CPY, ABL & RINA | [5 empty] | 2026-08-07 | AD_G30_44988-ABL-DRS-APP-4967 | Approved
25 | 12" RISER/SPOOL LIFTING DRAWING AT DC6 - DLS 4200 | GH0600-4002650 | 1-GH0600-31-DWG-2650-00 | E1 | 2 |  | 2026-06-02 | CSE-2642-PMT-T-071 | 2026-06-02 | to CPY, ABL & RINA | 2026-06-18 | 1-GH0600-31-DWG-2650-00_E1 | Code 4 - For Information |  |  | 2026-06-09 | AD_G30_44988-ABL-DRS-APP-4170 | APPROVED
|  |  |  | A1 | CLASS 2A |  | 2026-07-28 | CSE-2642-PMT-T-089 | 2026-07-29 | to CPY, ABL & RINA | 2026-08-05 | 1-GH0600-31-DWG-2650-00_A1 | Code 4 - For Information |  |  | 2026-08-04 | AD_G30_44988-ABL-DRS-APP-4937 | APPROVED
26 | 20" RISER/SPOOL LIFTING DRAWING AT DC6 - DLS 4200 | GH0600-4002651 | 1-GH0600-31-DWG-2651-00 | E1 | CLASS 2A |  | 2026-06-02 | CSE-2642-PMT-T-071 | 2026-06-02 | to CPY, ABL & RINA | 2026-06-18 | 1-GH0600-31-DWG-2651-00_E1_CRS | Code 4 - For Information |  |  | 2026-06-09 | AD_G30_44988-ABL-DRS-APP-4171 | APPROVED
|  |  |  | A1 | CLASS 2A |  | 2026-07-30 | CSE-2642-PMT-T-091 | 2026-07-30 | to CPY, ABL & RINA | 2026-08-05 | 1-GH0600-31-DWG-2651-00_A1 | Code 4 - For Information |  |  | 2026-08-04 | AD_G30_44988-ABL-DRS-APP-4938 | APPROVED
27 | 6" RISER/SPOOL LIFTING DRAWING AT DC6 (HG-SP-24) | GH0600-4002652 | 1-GH0600-31-DWG-2652-00 | E1 | CLASS 2A |  | 2026-06-02 | CSE-2642-PMT-T-071 | 2026-06-02 | to CPY, ABL & RINA | 2026-06-18 | 1-GH0600-31-DWG-2652-00 | Code 4 - For Information |  |  | 2026-06-09 | AD_G30_44988-ABL-DRS-APP-4173 | APPROVED
|  |  |  | A1 | CLASS 2A |  | 2026-07-28 | CSE-2642-PMT-T-089 | 2026-07-29 | to CPY, ABL & RINA | 2026-08-05 | 1-GH0600-31-DWG-2652-00_A1 | Code 4 - For Information |  |  | 2026-08-04 | AD_G30_44988-ABL-DRS-APP-4939 | APPROVED
28 | 6" RISER/SPOOL LIFTING DRAWING AT DC6 (HG-SP-23) | GH0600-4002653 | 1-GH0600-31-DWG-2653-00 | E1 | 2 |  | 2026-06-02 | CSE-2642-PMT-T-071 | 2026-06-02 | to CPY, ABL & RINA | 2026-06-18 | 1-GH0600-31-DWG-2653-00 | Code 4 - For Information |  |  | 2026-06-09 | AD_G30_44988-ABL-DRS-APP-4174 | APPROVED
|  |  |  | A1 | CLASS 2A |  | 2026-07-28 | CSE-2642-PMT-T-089 | 2026-07-29 | to CPY, ABL & RINA | 2026-08-05 | 1-GH0600-31-DWG-2653-00_A1 | Code 4 - For Information |  |  | 2026-08-04 | AD_G30_44988-ABL-DRS-APP-4940 | APPROVED
29 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF RISERS/SPOOLS ON CARGO BARGE - TRIP-2 | GH0000-4002658 | 1-GH0000-31-DWG-2658-00 | A1 | 2 |  | 2026-06-24 | CSE-2642-PMT-T-072 | 2026-06-24 | CPY / MWS | 2026-07-08 | HGDP-OFCR-00-TRN-009409 | CODE-2 COMMENTS |  |  | 2026-07-01 | AD_G30_44988-ABL-DRS-APP-4461 | APPROVED
|  |  |  | 00 | 2 |  | 2026-07-24 | CSE-2642-PMT-T-084 | 2026-07-24 | CPY / MWS | 2026-08-05 | 1-GH0000-31-DWG-2658-00_00 | CODE-1 APPROVED | [5 empty] | REISSUED ON 24-07-2026
30 | 22"(HG-SP-13) RISER/SPOOL LIFTING DRAWING AT GOP-NRP | GH5100-4002505 | 1-GH5100-31-DWG-2505-00 | E1 | 2 |  | 2026-07-10 | CSE-2642-PMT-T-079 | 2026-07-24 | CPY / MWS / RINA
|  |  |  | A1 | 2 |  | 2026-08-03 | CSE-2642-PMT-T-093 | 2026-08-03 | CPY / MWS / RINA | 2026-08-18 | 1-GH5100-31-DWG-2505-00_A1 |  |  |  | 2026-08-11 | AD_G30_44988-ABL-DRS-APP-5006 | APPROVED
|  |  |  | 00 | 2 |  | 2026-09-01 | CSE-2642-PMT-T-105 | 2026-09-01 | CPY / MWS / RINA | 2002-09-04 | 1-GH5100-31-DWG-2505-00_00 | CODE-1 APPROVED |  |  | 2026-09-07 | AD_G30_44988-ABL-DRS-APP-5326 | APPROVED
31 | 20"(HG-SP-14) RISER/SPOOL LIFTING DRAWING AT GOP-NRP | GH5100-4002508 | 1-GH5100-31-DWG-2508-00 | E1 | 2 |  | 2026-07-10 | CSE-2642-PMT-T-079 | 2026-07-24 | CPY / MWS / RINA
|  |  |  | A1 | 2 |  | 2026-08-03 | CSE-2642-PMT-T-093 | 2026-08-03 | CPY / MWS / RINA | 2026-08-18 | 1-GH5100-31-DWG-2508-00_A1 |  |  |  | 2026-08-11 | AD_G30_44988-ABL-DRS-APP-5007 | APPROVED
|  |  |  | 00 | 2 |  | 2026-08-27 | CSE-2642-PMT-T-103 | 2026-08-27 | CPY / MWS / RINA | 2026-09-04 | 1-GH5100-31-DWG-2508-00_00 | CODE-1 APPROVED
32 | 8"(HG-SP-16) RISER/SPOOL LIFTING DRAWING AT GOP-NRP | GH5100-4002509 | 1-GH5100-31-DWG-2509-00 | E1 | 2 |  | 2026-07-10 | CSE-2642-PMT-T-079 | 2026-07-24 | CPY / MWS / RINA
|  |  |  | A1 | 3 |  | 2026-08-03 | CSE-2642-PMT-T-093 | 2026-08-03 | CPY / MWS / RINA | 2026-08-18 | 1-GH5100-31-DWG-2509-00_A1 |  |  |  | 2026-08-11 | AD_G30_44988-ABL-DRS-APP-5008 | APPROVED
|  |  |  | 00 | 3 |  | 2026-08-20 | CSE-2642-PMT-T-099 | 2026-08-20 | CPY / MWS / RINA | [5 empty] | 2026-08-26 | AD_G30_44988-ABL-DRS-APP-5181 | APPROVED
33 | 14"(HG-SP-17) RISER/SPOOL LIFTING DRAWING AT GOP-NRP | GH5100-4002510 | 1-GH5100-31-DWG-2510-00 | E1 | 2 |  | 2026-07-10 | CSE-2642-PMT-T-079 | 2026-07-24 | CPY / MWS / RINA
|  |  |  | A1 | 2 |  | 2026-08-03 | CSE-2642-PMT-T-093 | 2026-08-03 | CPY / MWS / RINA | 2026-08-18 | 1-GH5100-31-DWG-2510-00_A1 |  |  |  | 2026-08-11 | AD_G30_44988-ABL-DRS-APP-5009 | APPROVED
|  |  |  | 00 | 3 |  | 2026-08-20 | CSE-2642-PMT-T-099 | 2026-08-20 | CPY / MWS / RINA | [5 empty] | 2026-08-26 | AD_G30_44988-ABL-DRS-APP-5180 | APPROVED
34 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF RISERS/SPOOLS/RISER PROTECTOS ON CARGO BARGE – TRIP 3 | GH0000-4002685 | 1-GH0000-31-DWG-2685-00 | A1 | 2 |  | 2026-08-19 | CSE-2642-PMT-T-098 | 2026-08-19 | CPY / MWS / RINA | 2026-08-25 | 1-GH0000-31-DWG-2685-00_A1 |  |  |  | 2026-08-26 | AD_G30_44988-ABL-DRS-APP-5174 | APPROVED
|  |  |  | 00 | 2 |  | 2026-08-26 | CSE-2642-PMT-T-101 | 2026-08-26 | CPY / MWS / RINA | 2026-09-04 | 1-GH0000-31-DWG-2685-00_00 | CODE-1 APPROVED
35 | 8" RISER/SPOOL LIFTING DRAWING @ DC4 (DLS 4200) | GH0400-4002690 | 1-GH0400-31-DWG-2690-00 | A1 | CLASS 2A
36 | 14" RISER/SPOOL LIFTING DRAWING @ DC4 (DLS 4200) | GH0400-4002691 | 1-GH0400-31-DWG-2691-00 | A1 | CLASS 2A
37 | 10" RISER/SPOOL LIFTING DRAWING @ DC4 (DLS 4200) | GH0400-4002692 | 1-GH0400-31-DWG-2692-00 | A1 | CLASS 2A

## Sketch
Project 2642
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2642 | OFO-P2642-SK-T-001 | GA AND DETAILS OF COUNTER WEIGHT SKID | 1 | A | √ | √ | 2024-05-08 | ENH | @
2 | 2642 | OFO-P2642-SK-T-002 | MIDLINE TIE-IN (HG-SP-30, HG-SP-31 & HG-SP-32)” | 3 | B | √ | √ | 2024-12-26 | CDG | @
3 | 2642 | OFO-P2642-SK-T-003 | FENDER FOR SAFEEN-3000 | 2 | A | √ | √ | 2024-12-17 | SKS | @
4 | 2642 | OFO-P2642-SK-T-004 | MIDLINE TIE-IN AT KP 11.000 OF 12" PIPELINE (HG-SP-31) FROM CHANIZ ISLAND TO MANAIF (LFP-OPP) | 2 | E | √ | √ | 2025-10-28 | LEO | @
5 | 2642 | OFO-P2642-SK-T-005 | MIDLINE TIE-IN AT KP 11.000 OF 16" PIPELINE (HG-SP-30) FROM CHANIZ ISLAND TO MANAIF (LFP-OPP) | 2 | E | √ | √ | 2025-10-28 | LEO | @
6 | 2642 | OFO-P2642-SK-T-006 | MIDLINE TIE-IN AT KP 31.409 OF 16" PIPELINE (HG-SP-32) FROM MANAIF (LFP-OPP) TO CHANIZ ISALND (GOP) | 2 | F | √ | √ | 2025-10-28 | LEO | @
7 | 2642 | OFO-P2642-SK-T-007 | CABLE PULLING ARRANGEMENT FOR 33KV SUBSEA CABLE | 2 | A | √ | √ | 2025-03-06 | Harfoush /HZD | @
8 | 2642 | OFO-P2642-SK-T-008 | CABLE PULLING ARRANGEMENT FOR 33KV SUBSEA CABLE AT CLQ PLATFORM | 2 | A | √ | √ | 2025-03-06 | HZD | @
9 | 2642 | OFO-P2642-SK-T-009 | LIFTING ARRANGEMENT DETAIL OF MOORING FRAME BY SAFEEN-3000 | 4 | A | √ | √ | 2025-04-08 | HZD | @
10 | 2642 | OFO-P2642-SK-T-010 | AWTI PLATFORM ARRANGEMENT | 1 | A | √ | √ | 2025-04-23 | CDG | @
11 | 2642 | OFO-P2642-SK-T-011 | PERSONNEL TRANSFER USING STEEL BASKET (SAFEEN-3000) | 2 | A | √ | √ | 2025-05-15 | CDG | @
12 | 2642 | OFO-P2642-SK-T-012 | H&G - SAFEEN 3000 DECK LAYOUT DURING JACKET INSTALLATION | 2 | A | √ | √ | 2025-05-10 | SKS | @
13 | 2642 | OFO-P2642-SK-T-013 | SCAFFOLDING WORKING FRAME AT DC-6 | 1 | A | √ | √ | 2025-05-14 | SHIJU | @
14 | 2642 | OFO-P2642-SK-T-014 | DETACHING CRANE OF SLEEVE PILE AT DC4 JACKET |  |  |  |  | 2025-05-14 | SHIJU
15 | 2642 | OFO-P2642-SK-T-015 | SCAFFOLDING WORKING FRAME AT CLQ | 1 | A | √ | √ | 2025-05-14 | SHIJU | @
16 | 2642 | OFO-P2642-SK-T-016 | DETACHING CRANE OF SLEEVE PILE AT DC4 JACKET | 3 | A | √ | √ | 2025-06-12 | SHIJU | @
17 | 2642 | OFO-P2642-SK-T-017 | DAVIT LIFT STROPS FOR STALK ON 16” PIPELENE (HG-SP-30) AT SRP GOP | 2 | C | √ | √ | 2026-01-23 | LEO | @
18 | 2642 | OFO-P2642-SK-T-018 | DAVIT LIFT STROPS FOR STALK ON 12” PIPELENE (HG-SP-31) AT SRP GOP | 2 | B | √ | √ | 2026-01-23 | LEO | @
19 | 2642 | OFO-P2642-SK-T-019 | DAVIT LIFT STROPS FOR STALK ON 16” PIPELENE (HG-SP-32) AT SRP GOP | 2 | B | √ | √ | 2026-01-23 | LEO | @
20 | 2642 | OFO-P2642-SK-T-020 | SAFEEN 3000 GANGWAY LIFTING AND INSTALLATION |  |  |  |  | 2025-05-19 | SHIJU
21 | 2642 | OFO-P2642-SK-T-021 | CB MOORING ARRANGEMNET TO SAFEEN3000 PORT AND STERN SIDE |  |  |  |  | 2025-05-28 | VDA
22 | 2642 | OFO-P2642-SK-T-022 | [5 empty] | 2025-05-28 | VDA
23 | 2642 | OFO-P2642-SK-T-023 | SAFEEN3000 GANGWAY 20m LIFTING AND INSTALLATION DRAWING | 3 | A | √ | √ | 2025-06-09 | SHIJU | @
24 | 2642 | OFO-P2642-SK-T-024 | S-280 HAMMER LIFT RIGGING ARRANGEMENT | 2 | B | √ | √ | 2025-07-23 | VDA | @ | T-002 - 23-07
25 | 2642 | OFO-P2642-SK-T-025 | S-600 HAMMER LIFT RIGGING ARRANGEMENT | 2 | A | √ | √ | 2025-07-15 | VDA | @ | T-001 - 16-07
26 | 2642 | OFO-P2642-SK-T-026 | SCAFFOLDING WORKING FRAME AT DC4 | 1 | A | √ | √ | 2025-06-13 | SHIJU | @
27 | 2642 | OFO-P2642-SK-T-027 | SCAFFOLDING WORKING FRAME AT GOP-SRP | 1 | A | √ | √ | 2025-06-13 | SHIJU | @
28 | 2642 | OFO-P2642-SK-T-028 | TANK LIFTING FRAME ARRANGEMENT AND DETAILS | 2 | A | √ | √ | 2025-06-20 | VDA | @
29 | 2642 | OFO-P2642-SK-T-029 | SEAFASTENING ARRANGEMENT OF HYDROHAMMERS ON SABINA | 3 + 23 | B, 0 | √ | √ | 2025-08-08 | SKT | @ | SM ACTIONED
30 | 2642 | OFO-P2642-SK-T-030 | DAVIT LIFT STROPS FOR STALK ON 6" PIPELINE (HG-SP-24) AT DC6 | 2 | A | √ | √ | 2025-09-02 | CDG | @
31 | 2642 | OFO-P2642-SK-T-031 | DAVIT LIFT STROPS FOR STALK ON 6" PIPELINE (HG-SP-24) AT GOP | 2 | B | √ | √ | 2026-01-22 | AMT | @
32 | 2642 | OFO-P2642-SK-T-032 | ABOVE WATER TIE-IN PLATFORM (AWTI) | 4 + 62 | B, 0 | √ | √ | 2025-10-02 | LEO | @ | HAF ACTIONED
33 | 2642 | OFO-P2642-SK-T-033 | DAVIT LIFT STROPS for 8in Pipeline (HG-SP-16) AT GOP and DC4 | 2 | A | √ | √ | 2025-09-09 | LEO | @
34 | 2642 | OFO-P2642-SK-T-034 | DAVIT LIFT STROPS for STALK ON 8in Pipeline (HG-SP-16) AT NRP GOP | 2 | A | √ | √ | 2025-09-10 | LEO | @
35 | 2642 | OFO-P2642-SK-T-035 | DAVIT LIFT STROPS FOR STALK ON 6" GAS LIFT PIPELINE (HG-SP-23) AT DC6 | 2 | A | √ | √ | 2025-09-10 | HZD | @
36 | 2642 | OFO-P2642-SK-T-036 | DAVIT LIFT STROPS FOR STALK ON 6" GAS LIFT PIPELINE (HG-SP-23) AT SRP GOP | 2 | B | √ | √ | 2026-01-22 | AMT | @
37 | 2642 | OFO-P2642-SK-T-037 | H&G - SAFEEN 3000 DECK LAYOUT DURING SURFACE MIDLINE TIE-IN | 2 | B | √ | √ | 2025-10-31 | CDG | @
38 | 2642 | OFO-P2642-SK-T-038 | DAVIT LIFT STROPS FOR STALK ON 14" WATER INJECTION PIPELINE (HG-SP-17) AT DC4 | 2 | A | √ | √ | 2025-09-12 | LEO | @
39 | 2642 | OFO-P2642-SK-T-039 | DAVIT LIFT STROPS FOR STALK ON 14" WATER INJECTION PIPELINE (HG-SP-17) AT NRP GOP | 2 | A | √ | √ | 2025-09-12 | LEO | @
40 | 2642 | OFO-P2642-SK-T-040 | DAVIT LIFT STROPS FOR STALK ON 10" WATER INJECTION PIPELINE (HG-SP-5) AT DC1 | 2 | B | √ | √ | 2025-09-17 | LEO | @
41 | 2642 | OFO-P2642-SK-T-041 | DAVIT LIFT STROPS FOR STALK ON 10" WATER INJECTION PIPELINE (HG-SP-5) AT DC4 | 2 | B | √ | √ | 2025-09-17 | LEO | @
42 | 2642 | OFO-P2642-SK-T-042 | MIDLINE TIE-IN ARRANGEMENT SKETCH AT KP 64 FOR 20" MOL PIPELINE FROM ULRP TO ZIRKU ISLAND | 2 | A | √ | √ | 2025-09-19 | HZD | @
43 | 2642 | OFO-P2642-SK-T-043 | SAFEEN3000 50MT DAVIT CRANE SEAFASTENING ON CB SAFEEN B-283 | 2 | A | √ | √ | 2025-09-23 | SKT | @
44 | 2642 | OFO-P2642-SK-T-044 | BEAR CAGE CLAMP LIFTIING & INSTALLATION ARRANGEMENT | 1 | B | √ | √ | 2025-10-28 | CDG | @
45 | 2642 | OFO-P2642-SK-T-045 | ROLLERS DETAILS FOR 220kV CABLE LADDER |  |  |  |  | 2025-11-03 | HZD
46 | 2642 | OFO-P2642-SK-T-046 | TYPICAL LIFTING AND RECOVERY ARRANGEMENT FOR DEMOLISHED CLUMP BLOCK | 1 | A | √ | √ | 2025-12-12 | MF | @
47 | 2642 | OFO-P2642-SK-T-047 | TYPICAL LIFTING AND RECOVERY ARRANGEMENT FOR DEMOLISHED PYRAMID ANODE |  |  |  |  | 2025-12-12 | MF
48 | 2642 | OFO-P2642-SK-T-048 | MIDLINE TIE-IN AT KP 9.650 OF 34" PIPELINE (HG-SP-28) FROM GOP-SOUTH TO LFP-OPP | 2 | C | √ | √ | 2025-12-19 | LEO | @
49 | 2642 | OFO-P2642-SK-T-049 | DAVIT LIFT STROPS FOR STALK ON 12" PIPELINE (HG-SP-21) AT DC6 | 2 | B | √ | √ | 2026-03-05 | LEO | @
50 | 2642 | OFO-P2642-SK-T-050 | DAVIT LIFT STROPS FOR STALK ON 12" PIPELINE (HG-SP-21) AT SRP GOP | 2 | B | √ | √ | 2026-01-27 | LEO | @
51 | 2642 | OFO-P2642-SK-T-051 | TYPICAL LIFTING AND SHIFTING ARRANGEMENT FOR 30MT CLUMP BLOCK | 1 | A | √ | √ | 2026-01-05 | NAR | @
52 | 2642 | OFO-P2642-SK-T-052 | DAVIT LIFT STROPS FOR STALK ON 34" PIPELINE (HG-SP-28) AT SRP GOP | 2 | B | √ | √ | 2026-02-03 | LEO | @
53 | 2642 | OFO-P2642-SK-T-053 | DAVIT LIFT STROPS FOR STALK ON 20" PIPELINE (HG-SP-22) AT SRP GOP | 2 | A | √ | √ | 2026-01-26 | LEO | @
54 | 2642 | OFO-P2642-SK-T-054 | DAVIT LIFT STROPS FOR STALK ON 22" PIPELINE (HG-SP-4) AT DC4 |  |  |  |  | 2026-01-28 | BBP
55 | 2642 | OFO-P2642-SK-T-055 | DAVIT LIFT STROPS FOR STALK ON 22" PIPELINE (HG-SP-4) AT DC1 |  |  |  |  | 2026-01-28 | BBP
56 | 2642 | OFO-P2642-SK-T-056 | DAVIT LIFT STROPS FOR STALK ON 22" PIPELINE (HG-SP-13) AT NRP GOP | 2 | A | √ | √ | 2026-03-18 | SSK | @
57 | 2642 | OFO-P2642-SK-T-057 | DAVIT LIFT STROPS FOR STALK ON 22" PIPELINE (HG-SP-13) AT DC4 | 2 | A | √ | √ | 2026-03-18 | SSK | @
58 | 2642 | OFO-P2642-SK-T-058 | DAVIT LIFT STROPS FOR STALK ON 20" PIPELINE (HG-SP-14) AT NRP GOP | 2 | A | √ | √ | 2026-03-17 | LEO | @
59 | 2642 | OFO-P2642-SK-T-059 | DAVIT LIFT STROPS FOR STALK ON 20" PIPELINE (HG-SP-14) AT DC4 | 2 | A | √ | √ | 2026-03-17 | LEO | @
60 | 2642 | OFO-P2642-SK-T-060 | DAVIT LIFT STROPS FOR STALK ON 20" PIPELINE (HG-SP-22) AT DC6 | 2 | A | √ | √ | 2026-02-04 | LEO | @
61 | 2642 | OFO-P2642-SK-T-061 | SAFEEN 3000 DECK LAYOUT FOR STALK ON RISER INSTALLATION |  |  |  |  | 2026-01-29 | BJ |  | SERVER ONLY NO FEEDBACK
62 | 2642 | OFO-P2642-SK-T-062 | METROLOGY SPOOL DIMENSION FOR 10" CS WATER INJECTION (HG-SP-5) CS PIPELINE FROM DC4 AT DC1 RISER PLATFORM | 1 | B | √ | √ | 2026-04-03 | BJ | @
63 | 2642 | OFO-P2642-SK-T-063 | SAFEEN 3000 GANGWAY A-FRAME SKID | 1 | A | √ | √ | 2026-03-02 | AMTIH | @
64 | 2642 | OFO-P2642-SK-T-064 | METROLOGY SPOOL DIMENSION FOR 16" LIFT GAS PIPELINE (HG-SP-32) FROM (LFP-OPP) MANAIF TO (GOP) CHANANIZ ISLAND |  |  |  |  | 2026-03-05 | BJ
65 | 2642 | OFO-P2642-SK-T-065 | METROLOGY SPOOL DIMENSION FOR 16" OIL PIPELINE (HG-SP-30) FROM (GOP) CHANANIZ ISLAND TO (LFP-OPP) MANAIF |  |  |  |  | 2026-03-05 | BJ
66 | 2642 | OFO-P2642-SK-T-066 | METROLOGY SPOOL DIMENSION FOR 12" CONDENSATE PIPELINE (HG-SP-31) FROM (GOP) CHANANIZ ISLAND TO (LFP-OPP) MANAIF |  |  |  |  | 2026-03-05 | BJ
67 | 2642 | OFO-P2642-SK-T-067 | METROLOGY SPOOL DIMENSION FOR 6" GAS LIFT PIPELINE (HG-SP-23) FROM (GOP) CHANANIZ ISLAND TO (DC6) SEEBEH ISLAND |  |  |  |  | 2026-03-05 | BJ
68 | 2642 | OFO-P2642-SK-T-068 | METROLOGY SPOOL DIMENSION FOR 6" WATER INJECTION PIPELINE (HG-SP-24) FROM (GOP) CHANANIZ ISLAND TO (DC6) SEEBEH ISLAND |  |  |  |  | 2026-03-05 | BJ
69 | 2642 | OFO-P2642-SK-T-069 | METROLOGY SPOOL DIMENSION FOR 34" WET SOUR GAS PIPELINE (HG-SP-28) FROM GOP TO (LFP-OPP) MANAIF |  |  |  |  | 2026-03-05 | BJ
70 | 2642 | OFO-P2642-SK-T-070 | SAFEEN 3000 BEAR CLAMP HANDLING BEAM (SWL=17 MT) | 1 | B | √ | √ | 2026-05-07 | AMTIH | @
71 | 2642 | OFO-P2642-SK-T-071 | DAVIT LIFT STROPS FOR STALK ON 20" PIPELINE (HG-SP-22) AT SRP GOP WITH DLS-4200 | 2 | B | √ | √ | 2026-05-19 | LEO | @
72 | 2642 | OFO-P2642-SK-T-072 | DAVIT LIFT STROPS FOR STALK ON 34" PIPELINE (HG-SP-28) AT SRP GOP WITH DLS-4200 | 2 | B | √ | √ | 2026-05-19 | LEO | @
73 | 2642 | OFO-P2642-SK-T-073 | DAVIT LIFT STROPS FOR STALK ON 12" PIPELINE (HG-SP-21) AT SRP GOP WITH DLS-4200 | 2 | B | √ | √ | 2026-05-19 | LEO | @
74 | 2642 | OFO-P2642-SK-T-074 | METROLOGY SPOOL DIMENSION FOR HG-SP-05 10” PIPELINE AT DC4 RISER PLATFORM JACKET | 1 | A | √ | √ | 2026-04-28 | BINOY | @
75 | 2642 | OFO-P2642-SK-T-075 | METROLOGY SPOOL DIMENSION FOR HG-SP-16 8” PIPELINE AT DC4 RISER PLATFORM JACKET | 1 | A | √ | √ | 2026-04-28 | BINOY | @ | REV-B SERVER ONLY
76 | 2642 | OFO-P2642-SK-T-076 | METROLOGY SPOOL DIMENSION FOR HG-SP-16 14” PIPELINE AT DC4 RISER PLATFORM JACKET | 1 | A | √ | √ | 2026-04-28 | BINOY | @
77 | 2642 | OFO-P2642-SK-T-077 | METROLOGY SPOOL DIMENSION FOR HG-SP-24 6” PIPELINE AT DC-6 RISER PLATFORM JACKET | 1 | A | √ | √ | 2026-04-28 | BINOY | @
78 | 2642 | OFO-P2642-SK-T-078 | METROLOGY SPOOL DIMENSION FOR HG-SP-23 6” PIPELINE AT DC-6 RISER PLATFORM JACKET | 1 | A | √ | √ | 2026-04-28 | BINOY | @
79 | 2642 | OFO-P2642-SK-T-079 | METROLOGY SPOOL DIMENSION FOR HG-SP-16 8” PIPELINE AT GOP NRP RISER PLATFORM JACKET | 1 | A | √ | √ | 2026-04-28 | BINOY | @ | REV-B SERVER ONLY
80 | 2642 | OFO-P2642-SK-T-080 | METROLOGY SPOOL DIMENSION FOR HG-SP-17 14” PIPELINE AT GOP NRP RISER PLATFORM JACKET | 1 | A | √ | √ | 2026-04-28 | BINOY | @
81 | 2642 | OFO-P2642-SK-T-081 | PIPELINE REPAIR SEQUENCE FOR HG-SP-31 (12" PIPELINE) AT MIDLINE TIE-IN LOCATION | 3 | B | √ | √ | 2026-09-04 | SIVA | @
82 | 2642 | OFO-P2642-SK-T-082 | DAVIT LIFT STROPS FOR STALK ON 16" PIPELINE (HG-SP-30) AT SRP GOP WITH DLS-4200 | 2 | C | √ | √ | 2026-05-19 | LEO | @
83 | 2642 | OFO-P2642-SK-T-083 | DAVIT LIFT STROPS FOR STALK ON 12" PIPELINE (HG-SP-31) AT SRP GOP WITH DLS-4200 | 2 | C | √ | √ | 2026-05-19 | LEO | @
84 | 2642 | OFO-P2642-SK-T-084 | DAVIT LIFT STROPS FOR STALK ON 16" PIPELINE (HG-SP-32) AT SRP GOP WITH DLS-4200 | 2 | C | √ | √ | 2026-05-19 | LEO | @
85 | 2642 | OFO-P2642-SK-T-085 | DAVIT LIFT STROPS FOR STALK ON 6” PIPELINE (HG-SP-24) AT SRP GOP WITH DLS-4200 | 2 | B | √ | √ | 2026-05-19 | LEO | @
86 | 2642 | OFO-P2642-SK-T-086 | DAVIT LIFT STROPS FOR STALK ON 6” PIPELINE (HG-SP-23) AT SRP GOP WITH DLS-4200 | 2 | C | √ | √ | 2026-05-19 | LEO | @
87 | 2642 | OFO-P2642-SK-T-087 | DAVIT LIFT STROPS FOR STALK ON 12" PIPELINE (HG-SP-21) AT DC6 WITH DLS-4200 | 2 | A | √ | √ | 2026-05-04 | LEO | @
88 | 2642 | OFO-P2642-SK-T-088 | DAVIT LIFT STROPS FOR STALK ON 20" PIPELINE (HG-SP-22) AT DC6 WITH DLS-4200 | 2 | B | √ | √ | 2026-07-01 | SKS | @
89 | 2642 | OFO-P2642-SK-T-089 | DAVIT LIFT STROPS FOR STALK ON 6” PIPELINE (HG-SP-23) AT DC6 WITH DLS-4200 | 2 | A | √ | √ | 2026-05-04 | LEO | @
90 | 2642 | OFO-P2642-SK-T-090 | DAVIT LIFT STROPS FOR STALK ON 6” PIPELINE (HG-SP-24) AT DC6 WITH DLS-4200 | 2 | A | √ | √ | 2026-05-04 | LEO | @
91 | 2642 | OFO-P2642-SK-T-091 | LIFTING AND INSTALLATION OF VALVE + ACTUATOR (XZV-9112) ASSEMBLY BY SEP-650 | 4 | A | √ | √ | 2026-05-11 | AMTITH | @
92 | 2642 | OFO-P2642-SK-T-092 | DLS-4200 DECK LAYOUT DURING DECK AND RISER INSTALLATION | 1 | A | √ | √ | 2026-06-05 | SKS
93 | 2642 | OFO-P2642-SK-T-093 | BEAR CAGE CLAMPS LIFTIING & INSTALLATION ARRANGEMENT BY DLS-4200 | 2 | A | √ | √ | 2026-04-29 | SSK | @
94 | 2642 | OFO-P2642-SK-T-094 | DAVIT LIFT STROPS FOR STALK ON 20" PIPELINE (HG-SP-14) AT DC4 WITH DLS-4200 | 2 | C | √ | √ | 2026-09-04 | LEO | @'
95 | 2642 | OFO-P2642-SK-T-095 | DAVIT LIFT STROPS FOR STALK ON 20" PIPELINE (HG-SP-14) AT NRP GOP WITH DLS-4200 | 2 | C | √ | √ | 2026-06-26 | LEO | @
96 | 2642 | OFO-P2642-SK-T-096 | METROLOGY SPOOL DIMENSION FOR HG-SP-21 12” PIPELINE AT DC-6 RISER PLATFORM | 1 | A | √ | √ | 2026-05-01 | BINOY | @
97 | 2642 | OFO-P2642-SK-T-097 | METROLOGY SPOOL DIMENSION FOR HG-SP-22 20” PIPELINE AT DC-6 RISER PLATFORM | 1 | A | √ | √ | 2026-05-01 | BINOY | @
98 | 2642 | OFO-P2642-SK-T-098 | METROLOGY SPOOL DIMENSION FOR HG-SP-21 12” PIPELINE AT GOP SRP RISER PLATFORM | 1 | B | √ | √ | 2026-05-08 | CDG | @
99 | 2642 | OFO-P2642-SK-T-099 | METROLOGY SPOOL DIMENSION FOR HG-SP-22 20” PIPELINE AT GOP SRP RISER PLATFORM | 1 | A | √ | √ | 2026-05-01 | BINOY | @
100 | 2642 | OFO-P2642-SK-T-100 | PIPELINE AS-LAID LATERAL PROFILE ON SEABED AFTER MIDLINE TIE-IN FOR HG-SP-28 (34IN PIPELINE) | 1 | A | √ | √ | 2026-04-30 | SIVA | @
101 | 2642 | OFO-P2642-SK-T-101 | DAVIT LIFT STROPS FOR STALK ON 22" PIPELINE (HG-SP-13) AT NRP GOP WITH DLS-4200 | 2 | A | √ | √ | 2026-05-04 | JF | @
102 | 2642 | OFO-P2642-SK-T-102 | DAVIT LIFT STROPS FOR STALK ON 22" PIPELINE (HG-SP-13) AT DC4 WITH DLS-4200 | 2 | B | √ | √ | 2026-06-26 | LEO | @
103 | 2642 | OFO-P2642-SK-T-103 | DAVIT LIFT STROPS FOR STALK ON 22" PIPELINE (HG-SP-4) AT DC4 WITH DLS-4200 | 2 | C | √ | √ | 2026-09-07 | LEO | @
104 | 2642 | OFO-P2642-SK-T-104 | DAVIT LIFT STROPS FOR STALK ON 22" PIPELINE (HG-SP-4) AT DC1 | 2 | A | √ | √ | 2026-05-05 | JF | @
105 | 2642 | OFO-P2642-SK-T-105 | DLS-4200 BEAR CLAMP HANDLING BEAM (SWL=30 MT) | 1 | A | √ | √ | 2026-05-05 | AAV | @
106 | 2642 | OFO-P2642-SK-T-106 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT BY DLS-4200 | 1 | A | √ | √ | 2026-05-06 | MF | @
107 | 2642 | OFO-P2642-SK-T-107 | DLS4200 GANGWAY 20m LIFTING AND INSTALLATION AT DC6 PLATFORM | 1 | A | √ | √ | 2026-05-13 | MF | @ | SERVER ONLY NO FEEDBACK
108 | 2642 | OFO-P2642-SK-T-108 | SAFEEN-3000 GANGWAY 20m LIFTING AND INSTALLATION AT GOP -SRP | 1 | A | √ | √ | 2026-05-13 | MF | @
109 | 2642 | OFO-P2642-SK-T-109 | DAVIT LIFT STROPS FOR STALK ON 8" PIPELINE (HG-SP-16) AT GOP-NRP WITH DLS-4200 | 2 | A | √ | √ | 2026-06-26 | MH (BBP) SKS | @
110 | 2642 | OFO-P2642-SK-T-110 | DAVIT LIFT STROPS FOR STALK ON 8" PIPELINE (HG-SP-16) AT DC4 WITH DLS-4200 |  |  |  |  | 2026-05-11 | MH (BBP)
111 | 2642 | OFO-P2642-SK-T-111 | DAVIT LIFT STROPS FOR STALK ON 10" WATER INJECTION PIPELINE (HG-SP-5) AT DC4 WITH DLS-4200 |  |  |  |  | 2026-05-11 | MH (BBP)
112 | 2642 | OFO-P2642-SK-T-112 | DAVIT LIFT STROPS FOR STALK ON 14" WATER INJECTION PIPELINE (HG-SP-17) AT GOP-NRP WITH DLS-4200 | 2 | A | √ | √ | 2026-06-26 | MH (BBP) SKS | @
113 | 2642 | OFO-P2642-SK-T-113 | DAVIT LIFT STROPS FOR STALK ON 14" WATER INJECTION PIPELINE (HG-SP-17) AT DC4 WITH DLS-4200 |  |  |  |  | 2026-05-11 | MH (BBP)
114 | 2642 | OFO-P2642-SK-T-114 | GENERAL ARRANGEMENT FOR AWTI PLATFORM ON DLS-4200 | 2 | B | √ | √ | 2026-06-05 | SKS | @
115 | 2642 | OFO-P2642-SK-T-115 | BEAR CAGE HANDLING FRAME ON DLS-4200 | 1 | A | √ | √ | 2026-05-13 | SKS | @ | SERVER ONLY NO FEEDBACK
116 | 2642 | OFO-P2642-SK-T-116 | DLS-4200 MOORING LINE CONNECTION DETAIL WITH ISLAND ANCHOR | 3 | B | √ | √ | 2026-08-25 | CDG | @
117 | 2642 | OFO-P2642-SK-T-117 | FLANGE COUPLING DETAIL FOR OUTFALL LINE SUBSEA SPOOLS AT GOP-SWI | 2 | A | √ | √ | 2026-05-19 | SKS | @
118 | 2642 | OFO-P2642-SK-T-118 | LIFTING AND INSTALLATION OF ZODIAC ACCESS LADDER AT GOP-SRP BY DLS-4200 |  |  |  |  | 2026-05-18 | SRV
119 | 2642 | OFO-P2642-SK-T-119 | COMPOSITE SPOOL DIMENSIONAL DETAIL PER METROLOGY REPORTS – GOP SRP | 1 | A | √ | √ | 2026-06-29 | BINOY | @ | SERVER ONLY NO FEEDBACK
120 | 2642 | OFO-P2642-SK-T-120 | LIFTING AND INSTALLATION OF MISCELLANEOUS HOOK UP SPOOLS BY SEP-650 AT DC6 | 5 | A | √ | √ | 2026-07-30 | AMK | @
121 | 2642 | OFO-P2642-SK-T-121 | DLS-4200 GANGWAY ARRANGEMENT AT GOP SRP PLATFORM | 2 | A | √ | √ | 2026-07-14 | SKS | @
122 | 2642 | OFO-P2642-SK-T-122 | DLS-4200 GANGWAY ARRANGEMENT AT GOP SRP PLATFORM – NORTH | 2 | A | √ | √ | 2026-07-14 | SKS | @
123 | 2642 | OFO-P2642-SK-T-123 | LIFTING AND INSTALLATION OF MISCELLANEOUS HOOK UP SPOOLS BY SEP-650 AT SRP | 8 | A | √ | √ | 2026-08-27 | AMITH | @
124 | 2642 | OFO-P2642-SK-T-124 | METROLOGY SPOOL DIMENSION FOR HG-SP-13 22” PIPELINE AT GOP NRP RISER PLATFORM |  |  |  |  | 2026-08-12 | BINOY
125 | 2642 | OFO-P2642-SK-T-125 | METROLOGY SPOOL DIMENSION FOR HG-SP-04 22” PIPELINE AT DC-1 RISER PLATFORM |  |  |  |  | 2026-08-12 | BINOY
126 | 2642 | OFO-P2642-SK-T-126 | METROLOGY SPOOL DIMENSION FOR HG-SP-14 20” PIPELINE AT GOP NRP RISER PLATFORM |  |  |  |  | 2026-08-12 | BINOY
127 | 2642 | OFO-P2642-SK-T-127 | COMPOSITE SPOOL DIMENSIONAL DETAIL PER METROLOGY REPORTS - GOP NRP RISER PLATFORM | 1 | A | √ | √ | 2026-08-13 | BINOY | @
128 | 2642 | OFO-P2642-SK-T-128 | COMPOSITE SPOOL DIMENSIONAL DETAIL PER METROLOGY REPORTS - DC-1 RISER PLATFORM |  |  |  |  | 2026-08-13 | BINOY
129 | 2642 | OFO-P2642-SK-T-129 | EMERGENCY RESCUE ARRANGEMENT TO THE SCAFFOLD STRETCHER | 1 | A | √ | √ | 2026-08-18 | CDG | @
130 | 2642 | OFO-P2642-SK-T-130 | METROLOGY SPOOL DIMENSION FOR HG-SP-14 20” PIPELINE AT DC-4 RISER PLATFORM |  |  |  |  | 2026-08-20 | BINOY
131 | 2642 | OFO-P2642-SK-T-131 | METROLOGY SPOOL DIMENSION FOR HG-SP-04 22” PIPELINE AT DC-4 RISER PLATFORM |  |  |  |  | 2026-08-20 | BINOY
132 | 2642 | OFO-P2642-SK-T-132 | METROLOGY SPOOL DIMENSION FOR HG-SP-13 22” PIPELINE AT DC-4 RISER PLATFORM |  |  |  |  | 2026-08-20 | BINOY
133 | 2642 | OFO-P2642-SK-T-133 | COMPOSITE SPOOL DIMENSIONAL DETAIL PER METROLOGY REPORTS - DC-4 |  |  |  |  | 2026-08-21 | BINOY
134 | 2642 | OFO-P2642-SK-T-134 | LIFTING AND INSTALLATION OF ZODIAC ACCESS LADDER AT DC1 BY SAFEEN-3000 | 1 | A | √ | √ | 2026-08-30 | SRV | @
135 | 2642 | OFO-P2642-SK-T-135 | GENERAL ARRANGEMENT FOR AWTI PLATFORM & BEAR CLAMP HANDLING FRAME ON SAFEEN 3000 |  |  |  |  | 2026-08-26 | SIVA
136 | 2642 | OFO-P2642-SK-T-136 | STORM CLAMP FOR 22'' PIPELINE | 1 | A | √ | √ | 2026-08-27 | NAR | @
137 | 2642 | OFO-P2642-SK-T-137 | MIDLINE TIE-IN AT KP 9.650 OF 34" PIPELINE (HG-SP-28) FROM GOP-SOUTH TO LFP-OPP WITH DLS-4200 | 2 | A | √ | √ | 2026-08-31 | SIVA | @
138 | 2642 | OFO-P2642-SK-T-138 | DAVIT LIFT STROPS FOR STALK ON 8" GAS LIFT PIPELINE (HG-SP-16) AT DC4 WITH DLS-4200 | 2 | B | √ | √ | 2026-09-04 | LEO | @
139 | 2642 | OFO-P2642-SK-T-139 | DAVIT LIFT STROPS FOR STALK ON 10" WATER INJECTION PIPELINE (HG-SP-5) AT DC4 WITH DLS-4200 | 2 | A | √ | √ | 2026-09-02 | LEO | @
140 | 2642 | OFO-P2642-SK-T-140 | DAVIT LIFT STROPS FOR STALK ON 14" WATER INJECTION PIPELINE (HG-SP-17) AT DC4 WITH DLS-4200 | 2 | B | √ | √ | 2026-09-04 | LEO | @
141 | 2642 | OFO-P2642-SK-T-141 | DAVIT LIFT STROPS FOR STALK ON 22" PIPELINE (HG-SP-13) AT DC4 WITH DLS-4200 | 2 | A | √ | √ | 2026-09-02 | LEO | @
142 | 2642 | OFO-P2642-SK-T-142 | BEAR CAGE CLAMP LIFTIING & INSTALLATION ARRANGEMENT BY DLS-4200 | 1 | A | √ | √ | 2026-09-02 | MF | @
143 | 2642 | OFO-P2642-SK-T-143 | MIDLINE TIE-IN AT KP 10.987 OF 12" PIPELINE (HG-SP-31) FROM GOP-SOUTH TO LFP-OPP WITH DLS-4200 | 3 | A | √ | √ | 2026-09-04 | LEO | @

## Cut-lists
Project 2642
CUT-LIST DRAWINGS
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2642 | OFO-P2642-SK-T-029-CTL | SEAFASTENING ARRANGEMENT OF HYDROHAMMERS ON SABINA | 3 + 23 | 0 | √ | √ | 2025-08-08 | SM ACTIONED ON 08/08 | @
2 | 2642 | OFO-P2642-SK-T-032CTL | ABOVE WATER TIE-IN PLATFORM (AWTI) | 4 + 62 | 0 | √ | √ | 2025-10-02 | HAF ACTIONED ON 02/10 | @
3 | 2642 | GH5100-4002427- CTL | TEMPORARY KNEE BRACE DETAILS FOR 16'' RISER/SPOOL AT GOP FROM OPP (GH-SP-32) CUTLIST | 1 + 9 | 0 | √ | √ | 2026-01-14 | HAF ACTIONED ON 02/10 | @
4 | 2642 | GH5100-4002428- CTL | TEMPORARY KNEE BRACE DETAILS FOR 16'' RISER/SPOOL AT GOP FROM OPP (GH-SP-30) CUTLIST | 1 + 9 | 0 | √ | √ | 2026-01-14 | HAF ACTIONED ON 02/10 | @
5 | 2642 | GH5100-4002429- CTL | 12" RISER / SPOOL LIFTING DRAWING AT GOP FROM OPP (HG-SP-31) - REV-E1 | 1 + 15 | 0 | √ | √ | 2026-02-15 | HAF ACTIONED ON 13/02 | @
6 | 2642 | GH5100-4002433- CTL | TEMPORARY KNEE BRACE DETAILS FOR 6'' RISER/SPOOL AT GOP FROM DC6 (HG-SP-24) CUTLIST | 1 + 14 | 0 | √ | √ | 2026-01-14 | HAF ACTIONED ON 02/10 | @
7 | 2642 | GH5100-4002434- CTL | TEMPORARY KNEE BRACE DETAILS FOR 6'' RISER/SPOOL AT GOP FROM DC6 (HG-SP-23) CUTLIST | 1 + 14 | 0 | √ | √ | 2026-01-14 | HAF ACTIONED ON 02/10 | @
8 | 2642 | GH5100-4002431- CTL | TEMPORARY KNEE BRACE DETAILS FOR 12" RISER / SPOOL AT GOP FROM DC6 (HG-SP-21) - CUTLIST | 1 + 10 | 0 | √ | √ | 2026-01-26 | HAF ACTIONED ON 28/01 | @
9 | 2642 | GH5100-4002432- CTL | TEMPORARY KNEE BRACE DETAILS FOR 20" RISER / SPOOL AT GOP FROM DC6 (HG-SP-22) - CUTLIST | 1 + 10 | 0 | √ | √ | 2026-01-26 | HAF ACTIONED ON 28/01 | @
10 | 2642 | GH0400-4002441-CTL | TEMPORARY KNEE BRACE DETAILS FOR 8'' RISER / SPOOL AT DC4 - CUTLIST | 1 + 14 | 0 | √ | √ | 2026-01-30 | HAF ACTIONED ON 30/01 | @
11 | 2642 | GH0400-4002442-CTL | TEMPORARY KNEE BRACE DETAILS FOR 14'' RISER / SPOOL AT DC4 - CUTLIST | 1 + 10 | 0 | √ | √ | 2026-01-29 | HAF ACTIONED ON 30/01 | @
12 | 2642 | GH0400-4002444-CTL | TEMPORARY KNEE BRACE DETAILS FOR 10'' RISER / SPOOL AT DC4 - CUTLIST | 1 + 13 | 0 | √ | √ | 2026-01-29 | HAF ACTIONED ON 30/01 | @
13 | 2642 | GH0600-4002436-CTL | 20” RISER/SPOOL LIFTING DRAWING AT DC6 | 1 + 10 | 0 | √ | √ | 2026-02-23 | HAF ACTIONED | '@
14 | 2642 | GH5100-4002622-CTL | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF RISERS/SPOOLS ON CARGO BARGE – TRIP 1 | 1 + 9 | 0 | √ | √ | 2026-05-13 | HAF ACTIONED | @
15 | 2642 | GH0600-4002652-CTL | 6" RISER/SPOOL LIFTING DRAWING AT DC6 (HG-SP-24) | 1 + 14 | 0 | √ | √ | 2026-06-03 | HAF ACTIONED | @
16 | 2642 | GH0600-4002653-CTL | 6" RISER/SPOOL LIFTING DRAWING AT DC6 (HG-SP-23) | 1 + 14 | 0 | √ | √ | 2026-06-03 | HAF ACTIONED | @
17 | 2642 | GH5100-4002505-CTL | TEMPORARY KNEE BRACE DETAILS FOR 14"( HG-SP-17) RISER/SPOOL @ GOP-NRP - CUTLIST | 1 + 11 | 0 | √ | √ | 2026-07-21 | HAF ACTIONED | @
18 | 2642 | GH5100-4002508-CTL | TEMPORARY KNEE BRACE DETAILS FOR 20"( HG-SP-14) RISER/SPOOL @ GOP-NRP - CUTLIST | 1 + 10 | 0 | √ | √ | 2026-07-21 | HAF ACTIONED | @
19 | 2642 | GH5100-4002509-CTL | TEMPORARY KNEE BRACE DETAILS FOR 8" RISER / SPOOL AT GOP-NRP ( HG-SP-16) - CUTLIST | 1 + 15 | 0 | √ | √ | 2026-07-20 | HAF ACTIONED | @
20 | 2642 | GH5100-4002510-CTL | TEMPORARY KNEE BRACE DETAILS FOR 22"( HG-SP-13) RISER/SPOOL @ GOP-NRP - CUTLIST | 1 + 13 | 0 | √ | √ | 2026-07-21 | HAF ACTIONED | @
21 | 2642 | OFO-P2642-SK-T-036CTL | STORM CLAMP FOR 22'' PIPELINE- CUTLIST | 1 + 5 | 0 | √ | √ | 2026-08-30 | KARTHICK | @