## Specification
|  |  | New 20’’ MOL from Umm Lulu to Zirku | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  |  | NPCC PROJECT NO.2683 | [10 empty] | REVISION : |  |  |  | 0
|  |  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS | [10 empty] | DATE : |  |  |  | 2023-11-08
SR. NO. | DESCRIPTION | COMPANY DOCUMENT NUMBER | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | MWS |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | SPECIFICATION FOR OFFSHORE PIPELINE AND RISER INSTALLATION |  | 2683-N-SP-0xxx
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
18
19
20
21
22
23
24
25
26
27

## PIPELINE & CABLE doc
|  |  | New 20’’ MOL from Umm Lulu to Zirku | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  |  | NPCC PROJECT NO.2683 | [10 empty] | REVISION : |  |  |  | 0
|  |  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS | [10 empty] | DATE : |  |  |  | 2023-11-08
SR. NO. | DESCRIPTION | COMPANY DOCUMENT NUMBER | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | MWS |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPE STACKING ANALYSIS REPORT | AD-473-G-63500 | 2683-NN-RP-001 | 1 | 2 | 2024-08-14 | 2024-09-09 | CSE-2683-PMT-T-001 | 2024-09-09 | 2683-NMDC-E-AO-PMT-T-00439 | 2024-09-26 | E1941-AOF-NPCC-PMT-TR-00280- | 2
|  |  |  | 2 | 2 |  | 2024-10-25 | CSE-2683-PMT-T-002 | 2024-10-25 | 2683-NMDC-E-AO-PMT-T-00501 | 2024-11-13 | E1941-AOF-NPCC-PMT-TR-00309 | 1 (Approved)
|  |  |  | 3 | 3 | IFI | 2024-11-17 | CSE-2683-PMT-T-003 | 2024-11-21 | 2683-NMDC-E-AO-PMT-T-00527 | 2024-11-21 | E1941-AOF-NPCC-PMT-TR-00317 | 1 (Approved)
2 | PIPELAY ANALYSIS REPORT FOR 20" MOL FROM ULRP TO ZIRKU ISLAND | AD-473-G-63501 | 2683-NN-RP-002 | 1 | 2 |  | 2025-05-30 | CSE-2683-PMT-T-017 | 2025-06-04 | 2683-NMDC-E-AO-PMT-T-00770 | 2025-06-13 | E1941-AOF-NPCC-PMT-TR-00469 | 2 - Approved with comments | 2025-06-04 | 2683-NMDC-E-ABL-MWS-T-0025 | 2025-06-16 | DRS-0042 | COMMENTS
|  |  |  | 2 | 2 |  | 2026-02-20 | CSE-2683-PMT-T-070 | 2026-02-26 | 2683-NMDC-E-AO-PMT-T-01142 | 2026-04-10 | E1941-AOF-NPCC-PMT-TR-00752 | 1 - Approved
3 | SHOREPULL ANALYSIS REPORT FOR 20" MOL AT ZIRKU ISLAND | AD-473-G-63502 | 2683-NN-RP-003 | 1 | 2 |  | 2025-07-25 | CSE-2683-PMT-T-022 | 2025-07-28 | 2683-NMDC-E-AO-PMT-T-00843 | 2025-08-15 | E1941-AOF-NPCC-PMT-TR-00540 | 2 - Approved with comments | 2025-07-28 | 2683-NMDC-E-ABL-MWS-T-0042 | 2025-08-08 | DRS-0059 | COMMENTS
|  |  |  | 2 | 2 |  | 2025-09-03 | CSE-2683-PMT-T-034 | 2025-09-08 | 2683-NMDC-E-AO-PMT-T-00913 | 2025-09-22 | E1941-AOF-NPCC-PMT-TR-00578 | 2 - Approved with comments | 2025-09-13 | 2683-NMDC-E-ABL-MWS-T-0064 | 2025-09-25 | DRS-0084 | COMMENTS
|  |  |  | 3 | 3 |  | 2025-09-26 | CSE-2683-PMT-T-040 | 2025-09-30 | 2683-NMDC-E-AO-PMT-T-00944 | 2025-09-30 | E1941-AOF-NPCC-PMT-TR-00588 | 1 (Approved)
4 | MIDLINE TIE-IN ANALYSIS REPORT FOR 20" MOL FROM ULRP TO ZIRKU ISLAND | AD-473-G-63503 | 2683-NN-RP-004 | 1 | 2 |  | 2025-10-02 | CSE-2683-PMT-T-041 | 2025-10-02 | 2683-NMDC-E-AO-PMT-T-00951 | 2025-10-09 | E1941-AOF-NPCC-PMT-TR-00596 | 2 - Approved with comments |  |  | 2025-10-09 | DRS-0088 | COMMENTS
|  |  |  | 2 | 2 |  | 2026-02-10 | CSE-2683-PMT-T-062 | 2026-02-19 | 2683-NMDC-E-AO-PMT-T-01126 | 2026-02-26 | E1941-AOF-NPCC-PMT-TR-00708 | 1 - Approved | 2026-02-22 | 2683-NMDC-E-ABL-MWS-T-0092 | 2026-02-26 | DRS-0118 | APPROVED
5 | LIFTING ANALYSIS FOR SPOOL OF 20" MOL FROM ULRP TO ZIRKU ISLAND AT ULRP | AD-473-G-63504 | 2683-NN-RP-005 | 1 | 2 |  | 2026-03-25 | CSE-2683-PMT-T-079 | 2026-03-25 | 2683-NMDC-E-AO-PMT-T-01190 | 2026-03-26 | E1941-AOF-NPCC-PMT-TR-00735 | 2 - Approved with comments | 2026-03-25 | 2683-NMDC-E-ABL-MWS-T-0105 | 2026-04-01 | DRS-0130 | APPROVED
|  |  |  | 2 | 2 |  | 2026-04-02 | CSE-2683-PMT-T-080 | 2026-04-03 | 2683-NMDC-E-AO-PMT-T-01203 | 2026-04-10 | E1941-AOF-NPCC-PMT-TR-00753 | 1 - Approved | 2026-04-03 | 2683-NMDC-E-ABL-MWS-T-0108 | 2026-04-02 | DRS-0135 | APPROVED
6 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS (TRIP-1) | AD-473-G-63505 | 2683-NN-RP-006
7 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AT GAC-68 (TRIP-1) | AD-473-G-63506 | 2683-NN-RP-007 | 1 | 3 |  | 2024-12-09 | CSE-2683-PMT-T-004 | 2024-12-09 | 2683-NMDC-E-AO-PMT-T-00554 |  |  |  | 2024-12-09 | 2683-NMDC-E-ABL-MWS-T-0003 | 2024-12-16 | DRS-0004 | APPROVED
|  |  |  | 2 | 3 |  | 2024-12-20 | CSE-2683-PMT-T-006 | 2024-12-31 | 2683-NMDC-E-AO-PMT-T-00586 | 2025-01-03 | E1941-AOF-NPCC-PMT-TR-00352 | 1 (Approved) | 2024-12-26 | 2683-NMDC-E-ABL-MWS-T-0010 | 2025-01-03 | DRS-0010 | APPROVED
8 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AT MARCAP SIBA (TRIP-2) | AD-473-G-63507 | 2683-NN-RP-008
9 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES @ PFC-01 (TRIP-1) | AD-473-G-63508 | 2683-NN-RP-009 | 1 | 2 |  | 2025-08-07 | CSE-2683-PMT-T-027 | 2025-08-11 | 2683-NMDC-E-AO-PMT-T-00866 | 2025-08-18 | E1941-AOF-NPCC-PMT-TR-00544 | 2 - Approved with comments | 2025-08-12 | 2683-NMDC-E-ABL-MWS-T-0050 | 2025-08-15 | DRS0064_ | APPROVED
|  |  |  | 2 | 3 |  | 2026-08-19 | CSE-2683-PMT-T-100 | 2026-08-19 | 2683-NMDC-E-AO-PMT-T-01355 | 2026-08-20 | E1941-AOF-NPCC-PMT-TR-00864 | 1 (Approved)
10 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES @ PRISM-7605 (TRIP-2) | AD-473-G-63509 | 2683-NN-RP-010 | 1 | 2 |  | 2025-08-09 | CSE-2683-PMT-T-028 | 2025-08-13 | 2683-NMDC-E-AO-PMT-T-00872 | 2025-08-18 | E1941-AOF-NPCC-PMT-TR-00542 | 2 - Approved with comments | 2025-07-31 | 2683-NMDC-E-ABL-MWS-T-0045 | 2025-08-15 | DRS0060_ | APPROVED
|  |  |  | 2 | 2 |  | 2025-08-28 | CSE-2683-PMT-T-031 | 2025-08-29 | 2683-NMDC-E-AO-PMT-T-00879 | 2025-09-16 | E1941-AOF-NPCC-PMT-TR-00568 | 1 (Approved) |  |  | 2025-09-04 | DRS0075 | APPROVED
11 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES @ PRESTIGE-283 (TRIP-3) | AD-473-G-63510 | 2683-NN-RP-011 | 1 | 2 |  | 2025-09-04 | CSE-2683-PMT-T-035 | 2025-09-11 | 2683-NMDC-E-AO-PMT-T-00918 | 2025-09-22 | E1941-AOF-NPCC-PMT-TR-00576 | 1 | 2025-09-11 | 2683-NMDC-E-ABL-MWS-T-0063
|  |  |  | 2 | 2 |  | 2025-10-01 | CSE-2683-PMT-T-039 | 2025-10-07 | 2683-NMDC-E-AO-PMT-T-00950 | 2025-10-09 | E1941-AOF-NPCC-PMT-TR-00595 | 1 | 2025-10-02 | 2683-NMDC-E-ABL-MWS-T-0068 | 2025-10-09 | DRS0089 | APPROVED
12 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES @ ASTRO-304 (TRIP-4) | AD-473-G-63511 | 2683-NN-RP-012 | 1 | 2 |  | 2025-10-09 | CSE-2683-PMT-T-042 | 2025-10-11 | 2683-NMDC-E-AO-PMT-T-00960 | 2025-10-30 | E1941-AOF-NPCC-PMT-TR-00609 | 1 | 2025-10-11 | 2683-NMDC-E-ABL-MWS-T-0070 | 2025-10-30 | DRS0093 | APPROVED
13 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AT ELISSA (TRIP-3) | AD-473-G-63512 | 2683-NN-RP-013 | 1 | 2 |  | 2025-02-24 | CSE-2683-PMT-T-011 | 2025-02-24 | 2683-NMDC-E-AO-PMT-T-00657 | 2025-02-25 | E1941-AOF-NPCC-PMT-TR-00393 | 2 - Approved with comments | 2025-02-26 | 2683-NMDC-E-ABL-MWS-T-0011 | 2025-03-04 | DRS0017 | APPROVED
14 | PIPELAY ANALYSIS REPORT FOR 20" MOL FROM ULRP TO ZIRKU ISLAND WITH DLS-4200 | AD-473-G-63513 | 2683-NN-RP-014 | 1 | 2 |  | 2025-08-01 | CSE-2683-PMT-T-026 | 2025-08-04 | 2683-NMDC-E-AO-PMT-T-00859 | 2025-08-11 | E1941-AOF-NPCC-PMT-TR-00533 | 2 - Approved with comments | 2025-08-02 | 2683-NMDC-E-ABL-MWS-T-0045 | 2025-08-22 | DRS0068 | COMMENTS
|  |  |  | 2 | 2 |  | 2025-09-17 | CSE-2683-PMT-T-037 | 2025-09-19 | 2683-NMDC-E-AO-PMT-T-00933 | 2025-09-26 | E1941-AOF-NPCC-PMT-TR-00585 | 1 (Approved) | 2025-09-19 | 2683-NMDC-E-ABL-MWS-T-0065 | 2025-09-26 | ABL-DRS-0085 | APPROVED
15 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES AT PFC-02 (TRIP-5) | AD-473-G-63514 | 2683-NN-RP-015 | 1 | 2 |  | 2025-10-22 | CSE-2683-PMT-T-044 | 2025-10-23 | 2683-NMDC-E-AO-PMT-T-00979 | 2025-10-23 | E1941-AOF-NPCC-PMT-TR-00607 | 1 | 2025-10-24 | 2683-NMDC-E-ABL-MWS-T-0072
|  |  |  | 2 | 3 | IFC | 2026-07-08 | CSE-2683-PMT-T-098 | 2026-07-14 | 2683-NMDC-E-AO-PMT-T-01324 | 2026-07-15 | E1941-AOF-NPCC-PMT-TR-00838 | 1
16 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES AT PFC-01 (TRIP-6) | AD-473-G-63515 | 2683-NN-RP-016 | 1 | 2 |  | 2025-12-08 | CSE-2683-PMT-T-049 | 2025-12-09 | 2683-NMDC-E-AO-PMT-T-01032 | 2025-12-17 | E1941-AOF-NPCC-PMT-TR-00652 | 1 | 2025-12-09 | 2683-NMDC-E-ABL-MWS-T-0079 | 2025-12-17 | DRS0103 | APPROVED
|  |  |  | 2 | 3 | IFC | 2026-07-08 | CSE-2683-PMT-T-098 | 2026-07-14 | 2683-NMDC-E-AO-PMT-T-01324 | 2026-07-15 | E1941-AOF-NPCC-PMT-TR-00838 | 1
17 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES AT PRISM-7605 (TRIP-7) | AD-473-G-63516 | 2683-NN-RP-017 | 1 | 2 |  | 2025-12-11 | CSE-2683-PMT-T-050 | 2025-12-11 | 2683-NMDC-E-AO-PMT-T-01039 | 2025-12-17 | E1941-AOF-NPCC-PMT-TR-00650 | 1 | 2025-12-11 | 2683-NMDC-E-ABL-MWS-T-0780 | 2025-12-17 | DRS-0104 | APPROVED
|  |  |  | 2 | 3 | IFC | 2026-07-08 | CSE-2683-PMT-T-098 | 2026-07-14 | 2683-NMDC-E-AO-PMT-T-01324 | 2026-07-15 | E1941-AOF-NPCC-PMT-TR-00838 | 1
18 | DAVIT LIFT ANALYSIS REPORT FOR 20” MOL AT ULRP | AD-473-G-63517 | 2683-NN-RP-018 | 1 | 2 |  | 2026-03-12 | CSE-2683-PMT-T-076 | 2026-03-12 | 2683-NMDC-E-ABL-MWS-T-0101 | 2026-03-16 | E1941-AOF-NPCC-PMT-TR-00723 | 2 | 2026-03-12 | 2683-NMDC-E-ABL-MWS-T-0101 | 2026-04-10 | DRS-0137 DRS-0129 | APPROVED
|  |  |  | 2 | 2 |  | 2026-04-09 | CSE-2683-PMT-T-085 | 2026-04-13 | 2683-NMDC-E-AO-PMT-T-01216 | 2026-04-27 | E1941-AOF-NPCC-PMT-TR-00777 | 1 | 2026-04-13 | 2683-NMDC-E-ABL-MWS-T-0113 | 2026-04-27 | DRS0142 | APPROVED
|  |  |  | 3 | 3 |  | 2026-05-19 | CSE-2683-PMT-T-093 | 2026-05-19 | 2683-NMDC-E-AO-PMT-T-01271 | 2026-05-20 | E1941-AOF-NPCC-PMT-TR-00801 | 1
18 | MIDLINE TIE-IN ANALYSIS REPORT FOR 20” MOL FROM ULRP TO ZIRKU ISLAND WITH DLS-4200 | AD-473-G-63518 | 2683-NN-RP-019 | 1 | 2 |  | 2026-04-22 | CSE-2683-PMT-T-086 | 2026-04-24 | 2683-NMDC-E-AO-PMT-T-01237 | 2026-05-04 | E1941-AOF-NPCC-PMT-TR-00783 | 1 | 2026-04-24 | 2683-NMDC-E-ABL-MWS-T-0115 | 2026-05-04 | DRS0143 | APPROVED
19 | SPARE | AD-473-G-63519 | 2683-NN-RP-020
20
21
22
23
24
25
26
27

## Naval & Marine doc
|  |  | New 20’’ MOL from Umm Lulu to Zirku | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  |  | NPCC PROJECT NO.2683 | [10 empty] | REVISION : |  |  |  | 0
|  |  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS | [10 empty] | DATE : |  |  |  | 2021-03-22
SR. NO. | DESCRIPTION | COMPANY DOCUMENT NUMBER | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES @ PFC-01 (TRIP-1) | AD-473-G-31500 | 2683-ZZ-CL-001 | 1 | 2 |  | 2025-08-07 | CSE-2683-PMT-T-027 | 2025-08-12 | 2683-NMDC-E-AO-PMT-T-00867 | 2025-08-12 | E1941-AOF-NPCC-PMT-TR-00534- | 2 | 2025-08-12 | 2683-NMDC-E-ABL-MWS-T-0050 | 2025-08-15 | DRS0063_ | APPROVED
|  |  |  | 2 | 3 |  | 2025-09-03 | CSE-2683-PMT-T-033 | 2025-09-08 | 2683-NMDC-E-AO-PMT-T-00911 | 2025-09-22 | E1941-AOF-NPCC-PMT-TR-00577 | 1 | 2025-09-08 | 2683-NMDC-E-ABL-MWS-T-0062 | 2025-09-22 | DRS0079 | APPROVED
2 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPE @ PRISM-7605 (TRIP-2) | AD-473-G-31501 | 2683-ZZ-CL-002 | 1 | 2 |  | 2025-08-09 | CSE-2683-PMT-T-028 | 2025-08-13 | 2683-NMDC-E-AO-PMT-T-00871 | 2025-08-14 | E1941-AOF-NPCC-PMT-TR-00537 | 2 | 2025-07-31 | 2683-NMDC-E-ABL-MWS-T-0045 | 2025-08-15 | DRS0061 | APPROVED
|  |  |  | 2 | 2 |  | 2025-08-28 | CSE-2683-PMT-T-031 | 2025-08-29 | 2683-NMDC-E-AO-PMT-T-00881 | 2025-09-16 | E1941-AOF-NPCC-PMT-TR-00568 | 1 |  |  | 2025-09-04 | DRS 0076 | APPROVED
3 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPE @ PRESTIGE-283 (TRIP-3) | AD-473-G-31502 | 2683-ZZ-CL-003 | 1 | 2 |  | 2025-09-04 | CSE-2683-PMT-T-035 | 2025-09-11 | 2683-NMDC-E-AO-PMT-T-00918 | 2025-09-22 | E1941-AOF-NPCC-PMT-TR-00576 | 1 | 2025-09-11 | 2683-NMDC-E-ABL-MWS-T-0063 | 2025-09-22 | DRS0083 | APPROVED
|  |  |  | 2 | 2 |  | 2025-10-01 | CSE-2683-PMT-T-039 | 2025-10-07 | 2683-NMDC-E-AO-PMT-T-00949 | 2025-10-09 | E1941-AOF-NPCC-PMT-TR-00595 | 1 | 2025-10-07 | 2683-NMDC-E-ABL-MWS-T-0068 | 2025-10-09 | DRS0090 | APPROVED
|  |  |  | 3 | 3 | IFC | 2026-06-19 | CSE-2683-PMT-T-094 | 2026-06-22 | 2683-NMDC-E-AO-PMT-T-01295 | 2026-06-22 | E1941-AOF-NPCC-PMT-TR-00817 | 1
4 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPE @ ASTRO-304 (TRIP-4) | AD-473-G-31503 | 2683-ZZ-CL-004 | 1 | 2 |  | 2025-10-09 | CSE-2683-PMT-T-042 | 2025-10-11 | 2683-NMDC-E-AO-PMT-T-00960 | 2025-10-30 | E1941-AOF-NPCC-PMT-TR-00608 | 1 | 2025-10-11 | 2683-NMDC-E-ABL-MWS-T-0070 | 2025-10-30 | DRS0090 | APPROVED
|  |  |  | 2 | 3 | IFC | 2026-06-30 | CSE-2683-PMT-T-095 | 2026-07-02 | 2683-NMDC-E-AO-PMT-T-01309
5 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS AT GAC-68 (TRIP-1) | AD-473-G-31504 | 2683-ZZ-CL-005 | 1 | 3 |  | 2024-12-09 | CSE-2683-PMT-T-004 | 2024-12-10 | 2683-NMDC-E-AO-PMT-T-00555 | 2024-12-30 | E1941-AOF-NPCC-PMT-TR-00348 | 1 | 2024-12-09 | 2683-NMDC-E-ABL-MWS-T-0004 | 2024-12-16 | DRS-003 | APPROVED
|  |  |  | 2 | 3 |  | 2024-12-20 | CSE-2683-PMT-T-006 | 2024-12-31 | 2683-NMDC-E-AO-PMT-T-00585 | 03/01/205 | E1941-AOF-NPCC-PMT-TR-00351 | 1 | 2024-12-26 | 2683-NMDC-E-ABL-MWS-T-0005 | 2025-01-03 | DRS-0009 | APPROVED
|  |  |  | 3 | 3 | IFC | 2026-06-30 | CSE-2683-PMT-T-095 | 2026-07-02 | 2683-NMDC-E-AO-PMT-T-01310
6 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS (TRIP-3) | AD-473-G-31505 | 2683-ZZ-CL-006 | 1 | 2 |  | 2025-02-24 | CSE-2683-PMT-T-011 | 2025-02-24 | 2683-NMDC-E-AO-PMT-T-00658 | 2025-02-25 | E1941-AOF-NPCC-PMT-TR-00394 | 2 | 2025-02-26 | 2683-NMDC-E-ABL-MWS-T-0011 | 2025-03-04 | DRS0022 | APPROVED | CLIENT COMMENTS ON MWS APPROVAL
|  |  |  | 2 | 3 | IFC | 2026-06-30 | CSE-2683-PMT-T-095 | 2026-07-02 | 2683-NMDC-E-AO-PMT-T-01308
7 | STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS | AD-473-G-31506 | 2683-ZZ-CL-007
8 | DLS-4200 MOORING ANALYSIS DURING 20” MOL FROM KP 0.00 TO 64.500 | AD-473-G-31507 | 2683-ZZ-CL-008 | 1 | 2 |  | 2025-07-14 | CSE-2683-PMT-T-020 | 2025-07-14 | 2683-NMDC-E-AO-PMT-T-00828 | 2025-07-24 | E1941-AOF-NPCC-PMT-TR-00512 | 2 | 2025-07-14 | 2683-NMDC-E-ABL-MWS-T-0035 | 14-07-2025 23-07-2025 | DRS0050 DRS0051 | APPROVED
|  |  |  | 2 | 3 |  | 2025-07-24 | CSE-2683-PMT-T-021 | 2025-07-30 | 2683-NMDC-E-AO-PMT-T-00842 | 2025-07-30 | E1941-AOF-NPCC-PMT-TR-00520- | 2
|  |  |  | 3 | 3 |  | 2025-07-31 | CSE-2683-PMT-T-024 | 2025-08-06 | 2683-NMDC-E-AO-PMT-T-00854 | 2025-08-12 | E1941-AOF-NPCC-PMT-TR-00536 | 1 | 2025-08-06 | 2683-NMDC-E-ABL-MWS-T-0041 | 2025-08-06 | DRS0056_ | APPROVED
9 | DLS-4200 MOORING ANALYSIS DURING 20" MOL FROM KP 64.500 TO KP 109.700 | AD-473-G-31508 | 2683-ZZ-CL-009 | 1 | 2 |  | 2025-12-16 | CSE-2683-PMT-T-051 | 2025-12-17 | 2683-NMDC-E-AO-PMT-T-01049 | 2025-12-22 | E1941-AOF-NPCC-PMT-TR-00657 | 1 | 2025-12-17 | 2683-NMDC-E-ABL-MWS-T-0084 | 2025-12-22 | DRS-0106 | APPROVED
|  |  |  | 2 | 3 | IFC | 2026-01-29 | CSE-2683-PMT-T-059 | 2026-01-29 | 2683-NMDC-E-AO-PMT-T-01100
10 | DLB-750 MOORING ANALYSIS DURING 20" MOL RISER INSTALLATION AT ULRP | AD-473-G-31509 | 2683-ZZ-CL-010 | 1 | 2 |  | 2025-12-05 | CSE-2683-PMT-T-047 | 2025-12-05 | 2683-NMDC-E-AO-PMT-T-01029 | 2025-12-10 | E1941-AOF-NPCC-PMT-TR-00642 | 1 | 2025-12-05 | 2683-NMDC-E-ABL-MWS-T-0076 | 2025-12-10 | DRS0100 | APPROVED
|  |  |  | 2 | 3 | IFC | 2026-01-29 | CSE-2683-PMT-T-060 | 2026-01-29 | 2683-NMDC-E-AO-PMT-T-01101 | 2026-01-30 | E1941-AOF-NPCC-PMT-TR-00686 | 2 | 2026-02-03 | 2683-NMDC-E-ABL-MWS-T-0084 | 2026-02-13 | ABL-DRS-0115 | APPROVED
|  |  |  | 3 | 3 |  | 2026-04-03 | CSE-2683-PMT-T-082 | 2026-04-03 | 2683-NMDC-E-AO-PMT-T-01206 | 2026-04-13 | E1941-AOF-NPCC-PMT-TR-00759 | 1 | 2026-04-03 | 2683-NMDC-E-ABL-MWS-T-0110 | 2026-04-03 | DRS-0136 | APPROVED
|  |  |  | 4 | 3 |  | 2026-04-09 | CSE-2683-PMT-T-084
11 | DLB-750 MOORING ANALYSIS DURING 20" MOL MIDLINE TIE-IN @ KP 109.7 | AD-473-G-31510 | 2683-ZZ-CL-011 | 1 | 2 |  | 2026-01-31 | CSE-2683-PMT-T-061 | 2026-02-02 | 2683-NMDC-E-AO-PMT-T-01107 | 2026-03-06 | E1941-AOF-NPCC-PMT-TR-00719- | 1 | 2026-02-02 | 2683-NMDC-E-ABL-MWS-T-0096 | 2026-03-06 | DRS0123 | APPROVED
|  |  |  | 2 | 3 | IFC | 2026-06-19 | CSE-2683-PMT-T-094 | 2026-06-19 | 2683-NMDC-E-AO-PMT-T-01296 | 2026-06-22 | E1941-AOF-NPCC-PMT-TR-00814 | 1
12 | DLS-4200 MOORING ANALYSIS DURING 20” MOL FROM KP 123 TO KP 64.5 | AD-473-G-31511 | 2683-ZZ-CL-012 | 1 | 2 |  | 2025-09-04 | CSE-2683-PMT-T-036 | 2025-09-10 | 2683-NMDC-E-AO-PMT-T-00917 | 2025-10-31 | E1941-AOF-NPCC-PMT-TR-00612 | 1 | 2025-09-10 | 2683-NMDC-E-ABL-MWS-T-0071 | 2025-10-31 | DRS0091 | APPROVED
|  |  |  | 2 | 3 | IFC | 2026-01-29 | CSE-2683-PMT-T-058 | 2026-01-29 | 2683-NMDC-E-AO-PMT-T-01099 | 2026-01-30 | E1941-AOF-NPCC-PMT-TR-00687 | 2 | 2026-02-03 | 2683-NMDC-E-ABL-MWS-T-0089 | 2026-02-13 | ABL-DRS-0114 | APPROVED
13 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPE @ PFC-02 (TRIP-5) | AD-473-G-31512 | 2683-ZZ-CL-013 | 1 | 3 |  | 2025-10-22 | CSE-2683-PMT-T-044 | 2025-10-23 | 2683-NMDC-E-AO-PMT-T-00978 | 2025-11-24 | E1941-AOF-NPCC-PMT-TR-00633 | 1 | 2025-10-23 | 2683-NMDC-E-ABL-MWS-T-0074 | 2025-11-24 | DRS0098 | APPROVED
|  |  |  | 2 | 3 | IFC | 2026-06-30 | CSE-2683-PMT-T-095 | 2026-07-02 | 2683-NMDC-E-AO-PMT-T-01306
14 | DLB-750 MOORING ANALYSIS DURING 20" MOL FROM KP 60.000 TO KP 109.700 | AD-473-G-31513 | 2683-ZZ-CL-014 | 1 | 2 |  | 2026-02-13 | CSE-2683-PMT-T-065 | 2026-02-16 | 2683-NMDC-E-AO-PMT-T-01129 | 2026-02-17 | E1941-AOF-NPCC-PMT-TR-00696 | 1 | 2026-02-17 | 2683-NMDC-E-ABL-MWS-T-0095 | 2026-02-27 | DRS0016 | APPROVED
|  |  |  | 2 | 3 | IFC | 2026-06-19 | CSE-2683-PMT-T-094 | 2026-06-19 | 2683-NMDC-E-AO-PMT-T-01297 | 2026-06-22 | E1941-AOF-NPCC-PMT-TR-00815 | 1
15 | DLS-4200 MOORING ANALYSIS DURING 20INCH MOL MIDLINE TIE-IN @ KP 109.7 | AD-473-G-31514 | 2683-ZZ-CL-015 | 1 | 2 |  | 2026-04-03 | CSE-2683-PMT-T-081 | 2026-04-03 | 2683-NMDC-E-AO-PMT-T-01205 | 2026-04-13 | E1941-AOF-NPCC-PMT-TR-00762 | 1 | 2026-04-03 | 2683-NMDC-E-ABL-MWS-T-0109 | 2026-04-10 | ABL-DRS-0141 | APPROVED
|  |  |  | 2 | 3 | IFC | 2026-06-19 | CSE-2683-PMT-T-094 | 2026-06-19 | 2683-NMDC-E-AO-PMT-T-01298 | 2026-06-22 | E1941-AOF-NPCC-PMT-TR-00816 | 1 | 2026-06-19 | 2683-NMDC-E-ABL-MWS-T-0124
16 | MOORING ANALYSIS OF WORK BOAT AT ULRP | AD-473-G-31515 | 2683-ZZ-CL-016 | 1 | 2 |  | 2026-07-10 | CSE-2683-PMT-T-099 | 2026-07-14 | 2683-NMDC-E-AO-PMT-T-01325 | 2026-07-14 | E1941-AOF-NPCC-PMT-TR-00842 | 3 | 2026-07-14 | 2683-NMDC-E-ABL-MWS-T-0131 | 2026-07-15 | DRS0157 | COMMENTS
|  |  |  | 2 | 2 |  | 2026-07-17 | CSE-2683-PMT-T-099 | 2026-07-20 | 2683-NMDC-E-AO-PMT-T-01330

## DRAWINGS
|  |  | New 20’’ MOL from Umm Lulu to Zirku | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  |  | NPCC PROJECT NO.2683 | [10 empty] | REVISION : |  |  |  | 0
|  |  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS | [10 empty] | DATE : |  |  |  | 2021-03-22
SR. NO. | DESCRIPTION | COMPANY DOCUMENT NUMBER | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | SHOREPULL HEAD FOR 20" MOL FROM ULRP TO ZIRKU ISLAND | AD-473-G-627000-SHT-001 | 2683-NN-0001 | 1 | 2 |  | 2025-02-11 | CSE-2683-PMT-T-008 | 2025-02-13 | 2683-NMDC-E-AO-PMT-T-00640 | 2025-03-04 | E1941-AOF-NPCC-PMT-TR-00399- | 2 | 2025-02-26 | 2683-NMDC-E-ABL-MWS-T-0011 | 2025-03-04 | DRS0012 | COMMENTS
|  |  |  | 2 | 2 |  | 2025-03-17 | CSE-2683-PMT-T-013 | 2025-03-19 | 2683-NMDC-E-AO-PMT-T-00687 | 2025-04-03 | E1941-AOF-NPCC-PMT-TR-00424 | 2 | 2025-03-22 | 2683-NMDC-E-ABL-MWS-T-0012 | 2025-04-08 | DRS-0026 | COMMENTS
|  |  |  | 3 | 3 | IFC | 2026-02-09 | CSE-2683-PMT-T-063 | 2026-02-16 | 2683-NMDC-E-AO-PMT-T-01118 | 2026-02-26 | E1941-AOF-NPCC-PMT-TR-00708 | 1 | 2026-02-14 | 2683-NMDC-E-ABL-MWS-T-0091 | 2026-02-26 | DRS-0122_ | APPROVED
2 | LAYDOWN HEAD FOR 20" MOL FROM ULRP TO ZIRKU ISLAND | AD-473-G-627001-SHT-001 | 2683-NN-0002 | 1 | 2 |  | 2025-02-11 | CSE-2683-PMT-T-008 | 2025-02-13 | 2683-NMDC-E-AO-PMT-T-00641 | 2025-03-04 | E1941-AOF-NPCC-PMT-TR-00399- | 2 | 2025-02-26 | 2683-NMDC-E-ABL-MWS-T-0011 | 2025-03-04 | DRS0013_ | COMMENTS
|  |  |  | 2 | 2 |  | 2025-05-01 | CSE-2683-PMT-T-015 | 2025-05-02 | 2683-NMDC-E-AO-PMT-T-00723 | 2025-05-20 | E1941-AOF-NPCC-PMT-TR-00453 | 2 | 2025-05-01 | 2683-NMDC-E-ABL-MWS-T-0019 | 2025-05-02 | DRS0038 | APPROVED
|  |  |  | 3 | 3 | IFC | 2026-02-09 | CSE-2683-PMT-T-063 | 2026-02-16 | 2683-NMDC-E-AO-PMT-T-01119 | 2026-02-26 | E1941-AOF-NPCC-PMT-TR-00708 | 1 | 2026-02-14 | 2683-NMDC-E-ABL-MWS-T-0091 | 2026-02-26 | DRS-01221 | APPROVED
3 | START UP HEAD FOR 20" MOL FROM ULRP TO ZIRKU ISLAND | AD-473-G-627002-SHT-001 | 2683-NN-0003 | 1 | 2 |  | 2025-02-11 | CSE-2683-PMT-T-008 | 2025-02-13 | 2683-NMDC-E-AO-PMT-T-00642 | 2025-03-04 | E1941-AOF-NPCC-PMT-TR-00399- | 2 | 2025-02-26 | 2683-NMDC-E-ABL-MWS-T-0011 | 2025-03-04 | DRS0014 | COMMENTS
|  |  |  | 2 | 2 |  | 2025-05-01 | CSE-2683-PMT-T-015 | 2025-05-02 | 2683-NMDC-E-AO-PMT-T-00724 | 2025-05-20 | E1941-AOF-NPCC-PMT-TR-00452 | 2 | 2025-05-02 | 2683-NMDC-E-ABL-MWS-T-0019 | 2025-05-02 | DRS0037 | APPROVED
|  |  |  | 3 | 3 | IFC | 2026-02-09 | CSE-2683-PMT-T-063 | 2026-02-11 | 2683-NMDC-E-AO-PMT-T-01120 | 2026-02-26 | E1941-AOF-NPCC-PMT-TR-00708 | 1 | 2026-02-14 | 2683-NMDC-E-ABL-MWS-T-0091 | 2026-02-26 | DRS-0120_ | APPROVED
4 | EMERGENCY LAYDOWN HEAD FOR 20" MOL FROM ULRP TO ZIRKU ISLAND | AD-473-G-627003-SHT-001 | 2683-NN-0004 | 1 | 2 |  | 2025-02-11 | CSE-2683-PMT-T-008 | 2025-02-13 | 2683-NMDC-E-AO-PMT-T-00643 | 2025-03-04 | E1941-AOF-NPCC-PMT-TR-00399- | 2 | 2025-02-26 | 2683-NMDC-E-ABL-MWS-T-0011 | 2025-03-04 | DRS0015 | COMMENTS
|  |  |  | 2 | 2 |  | 2025-05-01 | CSE-2683-PMT-T-015 | 2025-05-02 | 2683-NMDC-E-AO-PMT-T-00725 | 2025-05-20 | E1941-AOF-NPCC-PMT-TR-00452 | 2 | 2025-05-02 | 2683-NMDC-E-ABL-MWS-T-0019 | 2025-05-02 | DRS0036 | APPROVED
|  |  |  | 3 | 3 | IFC | 2026-02-09 | CSE-2683-PMT-T-063 | 2026-02-14 | 2683-NMDC-E-AO-PMT-T-01121 | 2026-02-26 | E1941-AOF-NPCC-PMT-TR-00708 | 1 | 2026-02-14 | 2683-NMDC-E-ABL-MWS-T-0091 | 2026-02-26 | DRS-0119_ | APPROVED
5 | TYPICAL BUCKLE DETECTOR DETAIL FOR 20" MOL FROM ULRP TO ZIRKU ISLAND | AD-473-G-627004-SHT-001 | 2683-NN-0005 | 1 | 2 |  | 2025-02-28 | CSE-2683-PMT-T-012 | 2025-03-06 | 2683-NMDC-E-AO-PMT-T-00671 | 2025-03-15 | E1941-AOF-NPCC-PMT-TR-00415 | 1
|  |  |  | 2 | 3 | IFC | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
6 | SPOOL LIFTING AND INSTALLATION FOR 20" MOL FROM ULRP TO ZIRKU ISLAND AT ULRP | AD-473-G-627005-SHT-001 | 2683-NN-0006 | 1 | 2 |  | 2026-03-10 | CSE-2683-PMT-T-073 | 2026-03-11 | 2683-NMDC-E-AO-PMT-T-01165 | 2026-03-16 | E1941-AOF-NPCC-PMT-TR-00727 | 2 | 2026-03-11 | 2683-NMDC-E-ABL-MWS-T-0099 | 2026-03-13 | DRS-0128 | COMMENTS
|  |  |  | 2 | 2 |  | 2026-04-07 | CSE-2683-PMT-T-083 | 2026-04-09 | 2683-NMDC-E-AO-PMT-T-01210 | 2026-04-13 | E1941-AOF-NPCC-PMT-TR-00760 | 1 | 2026-04-09 | 2683-NMDC-E-ABL-MWS-T-0111 | 2026-04-10 | ABL-DRS-0138 | APPROVED
|  |  |  | 3 | 2 |  | 2026-05-13 | CSE-2683-PMT-T-091 | 2026-05-14 | 2683-NMDC-E-AO-PMT-T-01262 |  |  |  | 2026-05-14 | 2683-NMDC-E-ABL-MWS-T-0121
|  |  |  | 4 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314
7 | DETAIL OF 20" TEMPORARY PIG LAUNCHER & RECEIVER FOR 20" MAIN OIL PIPELINE FROM ULRP TO ZIRKU ISLAND | AD-473-G-627006-SHT-001 | 2683-NN-0007 | 1 | 2 |  | 2025-10-17 | CSE-2683-PMT-T-043 | 2025-10-22 | 2683-NMDC-E-AO-PMT-T-00969 | 2026-01-09 | E1941-AOF-NPCC-PMT-TR-00670 | 2
|  |  |  | 2 | 2 |  | 2026-07-06 | CSE-2683-PMT-T-097 | 2026-07-06 | 2683-NMDC-E-AO-PMT-T-01315 | 2026-07-29 | E1941-AOF-NPCC-PMT-TR-00851 | 1
8 | TYPICAL LIFTING OF CONCRETE SLEEPERS | AD-473-G-627007-SHT-001 | 2683-NN-0008
9 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS AT GAC-68 (TRIP-1) | AD-473-G-627008-SHT-001 | 2683-NN-0009 | 1 | 3 |  | 2024-12-09 | CSE-2683-PMT-T-004 | 2024-12-09 | 2683-NMDC-E-AO-PMT-T-00556 | 2024-12-13 | E1941-AOF-NPCC-PMT-TR-00338 | 2 | 2024-12-09 | 2683-NMDC-E-ABL-MWS-T-0005 | 2024-12-16 | DRS-0005 | APPROVED
|  |  |  | 2 | 3 |  | 2024-12-20 | CSE-2683-PMT-T-006 | 2024-12-25 | 2683-NMDC-E-AO-PMT-T-00577 | 2025-01-03 | E1941-AOF-NPCC-PMT-TR-00355 | 2 | 2024-12-26 | 2683-NMDC-E-ABL-MWS-T-0008 | 2025-01-03 | DRS-008 | COMMENTS
|  |  |  | 3 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
10 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS (TRIP-2) | AD-473-G-627009-SHT-001 | 2683-NN-0010
11 | LOADING ARRANGEMENT FOR TRANSPORTATION OF SUBSEA SPOOLS (TRIP-1) | AD-473-G-627010-SHT-001 | 2683-NN-0011
12 | TEMPORARY KNEE BRACE DETAILS FOR 20" MOL-ULRP TO ZIRKU ISLAND AT ULRP | AD-473-G-627011-SHT-001 | 2683-NN-0012 | 1 | 2 |  | 12-02-20226 | CSE-2683-PMT-T-066 | 16-02-20226 | 2683-NMDC-E-AO-PMT-T-01128 | 17-02-20226 | E1941-AOF-NPCC-PMT-TR-00697 | 1
|  |  |  | 2 | 2 |  | 2026-03-09 | CSE-2683-PMT-T-072 | 2026-03-11 | 2683-NMDC-E-AO-PMT-T-01163 | 2026-03-12 | E1941-AOF-NPCC-PMT-TR-00721 | 1
|  |  |  | 3 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
13 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES @ @ PFC-01 (TRIP-1) | AD-473-G-627012-SHT-001 | 2683-NN-0013 | 1 | 2 |  | 2025-08-07 | CSE-2683-PMT-T-027 | 2025-08-11 | 2683-NMDC-E-AO-PMT-T-00868 |  |  |  | 2025-08-12 | 2683-NMDC-E-ABL-MWS-T-0050 | 2025-08-15 | DRS0065 DRS0067 | APPROVED | updated drg. Sent on 24/07
|  |  |  | 2 | 2 |  | 2025-09-03 | CSE-2683-PMT-T-032 | 2025-09-08 | 2683-NMDC-E-AO-PMT-T-00912 | 2025-09-22 | E1941-AOF-NPCC-PMT-TR-00577 | 1 | 2025-09-11 | 2683-NMDC-E-ABL-MWS-T-0063 | 2025-09-22 | DRS0080 | APPROVED
|  |  |  | 3 | 3 |  | 2025-09-17 | CSE-2683-PMT-T-038 | 2025-09-19 | 2683-NMDC-E-AO-PMT-T-00934 | 2025-10-07 | E1941-AOF-NPCC-PMT-TR-00591 | 1 | 2025-09-17 | 2683-NMDC-E-ABL-MWS-T-0066 | 2025-09-17 | DRS0086_ | APPROVED
|  |  |  | 4 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
14 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES @ PRISM-7605 (TRIP-2) | AD-473-G-627013-SHT-001 | 2683-NN-0014 | 1 | 2 |  | 2025-07-30 | CSE-2683-PMT-T-023 | 2025-08-04 | 2683-NMDC-E-AO-PMT-T-00850
|  |  |  | 2 | 2 |  | 2025-08-09 | CSE-2683-PMT-T-028 | 2025-08-15 | 2683-NMDC-E-AO-PMT-T-00873 | 2025-08-18 | E1941-AOF-NPCC-PMT-TR-00545 | 2 | 2025-08-09 | 2683-NMDC-E-ABL-MWS-T-0053
|  |  |  | 3 | 3 |  | 2025-08-28 | CSE-2683-PMT-T-031 | 2025-08-29 | 2683-NMDC-E-AO-PMT-T-00880 | [5 empty] | 2025-09-07 | DRS0074 | APPROVED
|  |  |  | 4 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
15 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES PRESTIGE-283 (TRIP-3) | AD-473-G-627014-SHT-001 | 2683-NN-0015 | 1 | 3 |  | 2025-09-04 | CSE-2683-PMT-T-035 | 2025-09-11 | 2683-NMDC-E-AO-PMT-T-00923 | 2025-09-22 | E1941-AOF-NPCC-PMT-TR-00576 | 1 | 2025-09-11 | 2683-NMDC-E-ABL-MWS-T-0063
|  |  |  | 2 | 3 |  | 2025-10-01 | CSE-2683-PMT-T-039 | 2025-10-29 | 2683-NMDC-E-AO-PMT-T-00984 | 2025-11-11 | E1941-AOF-NPCC-PMT-TR-00622 | 1 |  | 2683-NMDC-E-ABL-MWS-T-0072 | 2025-11-11 | DRS-0095 | APPROVED
16 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES AT ASTRO 304 (TRIP-4) | AD-473-G-627015-SHT-001 | 2683-NN-0016 | 1 | 3 |  | 2025-10-09 | CSE-2683-PMT-T-042 | 2025-10-11 | 2683-NMDC-E-AO-PMT-T-00961 | 2025-10-30 | E1941-AOF-NPCC-PMT-TR-00610 | 1 | 2025-10-11 | 2683-NMDC-E-ABL-MWS-T-0070 | 2025-10-30 | DRS0094 | APPROVED
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
17 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES AT PFC-02 (TRIP-5) | AD-473-G-627016-SHT-001 | 2683-NN-0017 | 1 | 2 |  | 2025-10-22 | CSE-2683-PMT-T-044 | 2025-10-23 | 2683-NMDC-E-AO-PMT-T-00977 | 2025-10-23 | E1941-AOF-NPCC-PMT-TR-00607 | 1 | 2025-10-24 | 2683-NMDC-E-ABL-MWS-T-0072
|  |  |  | 2 | 2 |  | 2025-10-27 | CSE-2683-PMT-T-045 | 2025-10-29 | 2683-NMDC-E-AO-PMT-T-00988 | 2025-11-11 | E1941-AOF-NPCC-PMT-TR-00622 | 1 | 2025-10-28 | 2683-NMDC-E-ABL-MWS-T-0073 | 2025-11-11 | DRS-0097 | APPROVED
|  |  |  | 3 | 2 |  | 2025-11-25 | CSE-2683-PMT-T-046 | 2025-12-03 | 2683-NMDC-E-AO-PMT-T-01019 | 2025-12-10 | E1941-AOF-NPCC-PMT-TR-00641 | 1 | 2025-12-03 | 2683-NMDC-E-ABL-MWS-T-0075 | 2025-12-10 | DRS-0099 | APPROVED
|  |  |  | 4 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
18 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON PFC-01 CB (TRIP-6) | AD-473-G-627017-SHT-001 | 2683-NN-0018 | 1 | 3 |  | 2025-12-05 | CSE-2683-PMT-T-048 | 2025-12-08 | 2683-NMDC-E-AO-PMT-T-01030 | 2025-12-08 | E1941-AOF-NPCC-PMT-TR-00638 E1941-AOF-NPCC-PMT-TR-00643 | 1 | 2025-12-08 | 2683-NMDC-E-ABL-MWS-T-0077 | 2025-12-10 | DRS-0101 | APPROVED
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
19 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES AT PRISM-7605 CB (TRIP-7) | AD-473-G-627018-SHT-001 | 2683-NN-0019 | 1 | 3 |  | 2025-12-11 | CSE-2683-PMT-T-050 | 2025-12-11 | 2683-NMDC-E-AO-PMT-T-01040 | 2025-12-17 | E1941-AOF-NPCC-PMT-TR-00650 | 1 | 2025-12-11 | 2683-NMDC-E-ABL-MWS-T-0081 | 2025-12-16 | DRS-0105 | APPROVED
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
20 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES AT PRESTIGE-283 (TRIP-8) | AD-473-G-627019-SHT-001 | 2683-NN-0020 | 1 | 3 |  | 2025-12-16 | CSE-2683-PMT-T-052 | 2025-12-17 | 2683-NMDC-E-AO-PMT-T-01048 | 2025-12-22 | E1941-AOF-NPCC-PMT-TR-00657 | 1 | 2025-12-17 | 2683-NMDC-E-ABL-MWS-T-0083 | 2025-12-22 | DRS-0107 | APPROVED
|  |  |  | 2 | 3 |  | 2025-12-24 | CSE-2683-PMT-T-054 | 2025-12-25 | 2683-NMDC-E-AO-PMT-T-01061 | 2025-12-29 | E1941-AOF-NPCC-PMT-TR-00662 | 1 | 2025-12-25 | email sent through PMT | 2025-12-29 | DRS-0110 | APPROVED
|  |  |  | 3 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
21 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON ASTRO-304 (TRIP-9) | AD-473-G-627020-SHT-001 | 2683-NN-0021 | 1 | 3 |  | 2025-12-22 | CSE-2683-PMT-T-053 | 2025-12-24 | 2683-NMDC-E-AO-PMT-T-01058 | 2026-01-22 | E1941-AOF-NPCC-PMT-TR-00679 | 1
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
22 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON PRISM-7605 (TRIP-10) | AD-473-G-627021-SHT-001 | 2683-NN-0022 | 1 | 3 |  | 2026-01-20 | CSE-2683-PMT-T-055 | 2026-01-23 | 2683-NMDC-E-AO-PMT-T-01088 | 2026-01-23 | E1941-AOF-NPCC-PMT-TR-00678 | 2 | 2026-01-23 | 2683-NMDC-E-ABL-MWS-T-0087 | 2026-01-20 | DRS0112 | APPROVED
|  |  |  | 2 | 3 |  | 2026-02-11 | CSE-2683-PMT-T-064 | 2026-02-16 | 2683-NMDC-E-AO-PMT-T-01127 | 2026-03-06 | E1941-AOF-NPCC-PMT-TR-00719- | 1 | 2026-02-16 | 2683-NMDC-E-ABL-MWS-T-0093 | 2026-03-06 | DRS0125 | APPROVED
|  |  |  | 3 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-07 | 2683-NMDC-E-AO-PMT-T-01314 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00834 | 1
23 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON PRESTIGE-283 (TRIP-11) | AD-473-G-627022-SHT-001 | 2683-NN-0023 | 1 | 2 |  | 2026-02-16 | CSE-2683-PMT-T-068 | 2026-02-17 | 2683-NMDC-E-AO-PMT-T-01134 | 2026-02-26 | E1941-AOF-NPCC-PMT-TR-00708 | 1 | 2026-02-14 | 2683-NMDC-E-ABL-MWS-T-0091 | 2026-02-27 | DRS-0117 | APPROVED
|  |  |  | 2 | 2 |  | 2026-04-21 | CSE-2683-PMT-T-087 | 2026-04-24 | 2683-NMDC-E-AO-PMT-T-01236 | 2026-05-04 | E1941-AOF-NPCC-PMT-TR-00784 | 1 | 2026-04-24 | 2683-NMDC-E-ABL-MWS-T-0114 | 2026-05-04 | DRS0144 | APPROVED
|  |  |  | 3 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01316 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00833 | 1
24 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES ON ASTRO-304 (TRIP-12) | AD-473-G-627023-SHT-001 | 2683-NN-0024 | 1 | 2 |  | 2026-03-10 | CSE-2683-PMT-T-074 | 2026-03-11 | 2683-NMDC-E-AO-PMT-T-01169 | 2026-03-16 | E1941-AOF-NPCC-PMT-TR-00727 | 2 | 2026-03-11 | 2683-NMDC-E-ABL-MWS-T-0100 | 2026-03-16 | DRS0126_ | COMMENTS
|  |  |  | 2 | 2 |  | 2026-03-25 | CSE-2683-PMT-T-078 | 2026-03-25 | 2683-NMDC-E-AO-PMT-T-01192 | 2026-03-26 | E1941-AOF-NPCC-PMT-TR-00733- | 2 | 2026-03-25 | 2683-NMDC-E-ABL-MWS-T-0104 | 2026-04-01 | DRS0131_ | APPROVED | client comment for mws approval - approved
|  |  |  | 3 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01316 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00833 | 1
25 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON PRISM-7605 (TRIP-13) | AD-473-G-627024-SHT-001 | 2683-NN-0025 | 1 | 2 |  | 2026-04-30 | CSE-2683-PMT-T-088 | 2026-05-01 | 2683-NMDC-E-AO-PMT-T-01243 | 2026-05-07 | E1941-AOF-NPCC-PMT-TR-00789 | 1 | 2026-05-01 | 2683-NMDC-E-ABL-MWS-T-0116 | 2026-05-07 | DRS0146 | APPROVED
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01316 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00833 | 1
26 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-14) | AD-473-G-627025-SHT-001 | 2683-NN-0026
27 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-15) | AD-473-G-627026-SHT-001 | 2683-NN-0027
28 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS CROSSING BY MP-01 | AD-473-G-627027-SHT-001 | 2683-NN-0028 | 1 | 2 |  | 2024-12-12 | CSE-2683-PMT-T-005 | 2024-12-12 | 2683-NMDC-E-AO-PMT-T-00568 | 2024-12-13 | E1941-AOF-NPCC-PMT-TR-00337 | 5 | 2024-12-12 | 2683-NMDC-E-ABL-MWS-T-0007 | 2024-12-20 | DRS0007 | APPROVED
|  |  |  | 2 | 2 |  | 2025-03-27 | CSE-2683-PMT-T-014 | 2025-03-29 | 2683-NMDC-E-AO-PMT-T-00697 | 2025-05-24 | E1941-AOF-NPCC-PMT-TR-00435 | 2 |  |  |  | DRS0027_ | APPROVED
|  |  |  | 3 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01316 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00833 | 1
29 | TYPICAL LIFTING AND INSTALLATION OF SANDBAGS BY CARGO NET USING MP-01 | AD-473-G-627028-SHT-001 | 2683-NN-0029 | 1 | 2 |  | 2025-05-16 | CSE-2683-PMT-T-016 | 2025-05-16 | 2683-NMDC-E-AO-PMT-T-00744 | 2025-05-16 | E1941-AOF-NPCC-PMT-TR-00450 | 2 | 2025-05-16 | 2683-NMDC-E-ABL-MWS-T-0022 |  |  | email from ASK 19/02/25 | email from JH-19/02
|  |  |  | 2 | 2 |  | 2026-07-06 | CSE-2683-PMT-T-097 | 2026-07-06 | 2683-NMDC-E-AO-PMT-T-01315 | 2026-07-29 | E1941-AOF-NPCC-PMT-TR-00851 | 1
30 | LIFTING AND INSTALLATION OF RISER CLAMP AT ULRP BY MP-01 | AD-473-G-627029-SHT-001 | 2683-NN-0030 | 1 | 3 |  | 2025-06-24 | CSE-2683-PMT-T-018 | 2025-06-27 | 2683-NMDC-E-AO-PMT-T-00799 | 2025-06-30 | E1941-AOF-NPCC-PMT-TR-00482- | 2 | 2025-06-27 | 2683-NMDC-E-ABL-MWS-T-0029 | 2025-07-06 | ABL-DRS-0044 | APPROVED | client comment for mws approval - approved
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01316 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00832 | 1
|  |  |  | 3 | 3 |  | 2026-08-21 | CSE-2683-PMT-T-101 | 2026-08-21 | 2683-NMDC-E-AO-PMT-T-01359
31 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS AT ELISSA CB (TRIP-3) | AD-473-G-627030-SHT-001 | 2683-NN-0031 | 1 | 3 |  | 2025-02-24 | CSE-2683-PMT-T-011 | 2025-02-24 | 2683-NMDC-E-AO-PMT-T-00656 | 2025-03-04 | E1941-AOF-NPCC-PMT-TR-00399 | 2 | 2025-02-26 | 2683-NMDC-E-ABL-MWS-T-0011 | 2025-03-04 | DRS0016 | APPROVED
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01316 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00833 | 1
32 | LIFTING AND INSTALLATION OF RISER CLAMP AT ULRP BY SAFEEN PEARL | AD-473-G-627031-SHT-001 | 2683-NN-0032 | 1 | 3 |  | 2025-08-12 | CSE-2683-PMT-T-029 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01316 | 2025-08-13 | E1941-AOF-NPCC-PMT-TR-00538 | 1 | 2025-08-12 | 2683-NMDC-E-ABL-MWS-T-0055 | 2025-08-22 | DRS-0070 | APPROVED
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01316 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00833 | 1
33 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DLS-4200 PIPE HANDLING CRANE | AD-473-G-627032-SHT-001 | 2683-NN-0033 | 1 | 2 |  | 2025-08-14 | CSE-2683-PMT-T-030 | 2025-08-18 | 2683-NMDC-E-AO-PMT-T-00882 | 2025-08-18 | E1941-AOF-NPCC-PMT-TR-00546 | 2
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01317 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00832 | 1
34 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT USING DLS-4200 | AD-473-G-627033-SHT-001 | 2683-NN-0034 | 1 | 2 |  | 2025-08-14 | CSE-2683-PMT-T-030 | 2025-08-18 | 2683-NMDC-E-AO-PMT-T-00883 | 2025-10-07 | E1941-AOF-NPCC-PMT-TR-00590 | 1 | 2025-08-18 | 2683-NMDC-E-ABL-MWS-T-0057
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01316 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00833 | 1
35 | PIPELINE HEADS RIGGING ARRANGEMENT | AD-473-G-627034-SHT-001 | 2683-NN-0035 |  |  | NAR - 15-08 Remarks | [12 empty] | This drg. Has been cancelled (ASK's email dtd. 21/08)
36 | LIFTING AND INSTALLATION OF RISER CLAMP AT ULRP BY MP-02 | AD-473-G-627035-SHT-001 | 2683-NN-0036 | 1 | 2 |  | 2026-01-22 | CSE-2683-PMT-T-056 | 2026-01-26 | 2683-NMDC-E-AO-PMT-T-01093 | 2026-01-26 | E1941-AOF-NPCC-PMT-TR-00681 | 2
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01317 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00832 | 1
37 | LIFTING AND INSTALLATION OF RISER CLAMP AT ULRP BY HEA OCEANIC | AD-473-G-627036-SHT-001 | 2683-NN-0037 | 1 | 2 |  | 2026-01-29 | CSE-2683-PMT-T-057 | 2026-01-30 | 2683-NMDC-E-AO-PMT-T-01102 | 2026-03-06 | E1941-AOF-NPCC-PMT-TR-00719- | 1 | 2026-01-30 | 2683-NMDC-E-ABL-MWS-T-0097 | 2026-03-06 | DRS0124 | APPROVED
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01316 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00833 | 1
38 | LIFTING AND INSTALLATION OF RISER CLAMP AT ULRP BY DLB-750 | AD-473-G-627037-SHT-001 | 2683-NN-0038 | 1 | 2 |  | 2026-02-16 | CSE-2683-PMT-T-069 | 2026-02-16 | 2683-NMDC-E-AO-PMT-T-01133 | 2026-02-20 | E1941-AOF-NPCC-PMT-TR-00706 | 2
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01317 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00832 | 1
39 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DLB-750 | AD-473-G-627038-SHT-001 | 2683-NN-0039 | 1 | 2 |  | 2026-02-13 | CSE-2683-PMT-T-067 | 2026-02-16 | 2683-NMDC-E-AO-PMT-T-01130 | 2026-02-18 | E1941-AOF-NPCC-PMT-TR-00698 | 2
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01317 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00832 | 1
40 | SPOOL LIFTING FOR 20" MOL | AD-473-G-627039-SHT-001 | 2683-NN-0040 | 1 | 2 |  | 2026-02-20 | CSE-2683-PMT-T-071 | 2026-02-21 | 2683-NMDC-E-AO-PMT-T-01143 | 2026-02-27 | E1941-AOF-NPCC-PMT-TR-00710 | 2
|  |  |  | 2 | 2 |  | 2026-03-11 | CSE-2683-PMT-T-075 | 2026-03-11 | 2683-NMDC-E-AO-PMT-T-01170 | 2026-04-10 | E1941-AOF-NPCC-PMT-TR-00751 | 2
|  |  |  | 3 | 2 |  | 2026-07-06 | CSE-2683-PMT-T-097 | 2026-07-06 | 2683-NMDC-E-AO-PMT-T-01315 | 2026-07-29 | E1941-AOF-NPCC-PMT-TR-00851 | 1
41 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DLB-750 (CRAWLER CRANE) | AD-473-G-627051-SHT-001 | 2683-NN-0041 |  |  | SRV
42 | TYPICAL LIFTING AND INSTALLATION OF SANDBAGS BY CARGO NET USING DLB-750 | AD-473-G-627052-SHT-001 | 2683-NN-0042 | 1 | 2 |  | 2026-03-22 | CSE-2683-PMT-T-077 | 2026-03-25 | 2683-NMDC-E-AO-PMT-T-01185 |  |  |  | 2026-03-25 | 2683-NMDC-E-ABL-MWS-T-0103 | 2026-04-01 | DRS-132 | APPROVED
|  |  |  | 2 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01316 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00833 | 1
43 | LIFTING AND INSTALLATION OF 20” SPOOLS FROM ULRP TO ZIRKU ISLAND AT ULRP (USING MUTAWA-401) | AD-473-G-627053-SHT-001 | 2683-NN-0043 | 1 | 2 |  | 2026-04-30 | CSE-2683-PMT-T-089 | 2026-05-01 | 2683-NMDC-E-AO-PMT-T-01244 | 2026-05-04 | E1941-AOF-NPCC-PMT-TR-00782- | 2
|  |  |  | 2 | 2 |  | 2026-05-06 | CSE-2683-PMT-T-090 | 2026-05-07 | 2683-NMDC-E-AO-PMT-T-01253 | 2026-05-08 | E1941-AOF-NPCC-PMT-TR-00790 | 2
|  |  |  | 3 | 2 |  | 2026-05-14 | CSE-2683-PMT-T-092 | 2026-05-15 | 2683-NMDC-E-AO-PMT-T-01264 | 2026-05-18 | E1941-AOF-NPCC-PMT-TR-00799 | 2
|  |  |  | 4 | 3 |  | 2026-07-03 | CSE-2683-PMT-T-096 | 2026-07-08 | 2683-NMDC-E-AO-PMT-T-01317 | 2026-07-09 | E1941-AOF-NPCC-PMT-TR-00832 | 1
44 | SPARE | AD-473-G-627054-SHT-001 | 2683-NN-0044
45 | SPARE | AD-473-G-627055-SHT-001 | 2683-NN-0045

## SKETCHES
Project 2683
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2683 | OFO-P2683-SK-T-001 | GENERAL PIPELAY PROFILE DLB-750
2 | 2683 | OFO-P2683-SK-T-002 | ABANDONMENT & RECOVERY ARRANGEMENT @ FINAL STAGE
3 | 2683 | OFO-P2683-SK-T-003 | DMA START-UP ARRANGEMENT FOR 16" WF PIPELINE FROM UAD TO SPUR
4 | 2683 | OFO-P2683-SK-T-004 | MARKER JOINTS FOR 20" PIPELINE
5 | 2683 | OFO-P2683-SK-T-005 | TRANSITION JOINTS FOR 20” PIPELINE
6 | 2683 | OFO-P2683-SK-T-006 | SHORE PULL ARRANGEMENT PROPOSED 20" MOL AT ZIRKU ISLAND | 1 | A | √ | √ | 26/12/2023 | HZD | @
7 | 2683 | OFO-P2683-SK-T-007 | TYPICAL AIR BAG ARRANGEMENTS FOR PIPELINE
8 | 2683 | OFO-P2683-SK-T-008 | TYPICAL ARRANGEMENT OF FLOATS ON PIPELINE
9 | 2683 | OFO-P2683-SK-T-009 | 42" ANCHOR PIPE
10 | 2683 | OFO-P2683-SK-T-010 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DLB-750 / MANITOWOC CRANE
11 | 2683 | OFO-P2683-SK-T-011 | LIFTING & OFFLOADING SMALL BOAT BY MUTAWA 401 | 1 | A | √ | √ | 16/12/2023 | AKS | @
12 | 2683 | OFO-P2683-SK-T-012 | SPARE |  |  |  |  | 04/06/2024 | HZD
13 | 2683 | OFO-P2683-SK-T-013 | PIPE LAYING WITHOUT FIELD JOINT ON DLB-750 | 3 | A | √ | √ | 04/06/2024 | HZD | @
14 | 2683 | OFO-P2683-SK-T-014 | PIPE LAYING WITHOUT FIELD JOINT ON SAFEEN-3000 | 5 | A | √ | √ | 04/06/2024 | HZD | @
15 | 2683 | OFO-P2683-SK-T-015 | ZIRKU LAYDOWN AREA |  |  |  |  | 10/07/2024 | REY
16 | 2683 | OFO-P2683-SK-T-016 | TRANSITION JOINTS FOR 48'' MOL PIPELINE | 1 | C | √ | √ | 07/11/2024 | NAR | @
17 | 2683 | OFO-P2683-SK-T-017 | MARKER JOINTS FOR 48'' MOL PIPELINE | 1 | B | √ | √ | 07/11/2024 | NAR | @
18 | 2683 | OFO-P2683-SK-T-018 | TYPICAL SLEEPER CROSS SECTION | 1 | A | √ | √ | 31/01/2025 | CDG | @
19 | 2683 | OFO-P2683-SK-T-019 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON MP-01 (Trip-1) | 1 | A | √ | √ | 2025-02-21 | JH | @
20 | 2683 | OFO-P2683-SK-T-020 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON MARCAB SIBA (Trip-2) | 1 | A | √ | √ | 2025-02-21 | JH | @
21 | 2683 | OFO-P2683-SK-T-021 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON MARCAB SIBA (Trip-4) | 1 | A | √ | √ | 2025-02-21 | JH | @
22 | 2683 | OFO-P2683-SK-T-022 | SHOREPULL ARRANGEMENT AT ZIRKU ISLAND | 1 | F | √ | √ | 2025-09-24 | LRA | @
23 | 2683 | OFO-P2683-SK-T-023 | HORIZONTAL HBC START-UP ARRANGEMENT OF 20" MOL ULRP TO ZIRKU ISLAND AT ULRP | 1 | E | √ | √ | 2025-09-26 | SKT | @
24 | 2683 | OFO-P2683-SK-T-024 | STINGER-9 SECTION –A 80” BUOYANCY TANK | 1 | C | √ | √ | 2025-08-28 | HZD | @
25 | 2683 | OFO-P2683-SK-T-025 | GRAVITY ANCHOR ARRANGEMENT ON AHT DECK | 1 | A | √ | √ | 2025-05-14 | ENH | @
26 | 2683 | OFO-P2683-SK-T-026 | TYPICAL ABADOMENT & RECOVERY / LAYDOWN ARRANGEMENT | 1 | B | √ | √ | 2026-02-05 | SHIJU | @
27 | 2683 | OFO-P2683-SK-T-027 | DLB-750 PIPELAY PROFILE | 1 | A | √ | √ | 2025-05-23 | NAR | @
28 | 2683 | OFO-P2683-SK-T-028 | SCHEMATIC LAYOUT AND CRANE CAPACITY - MP-01 | 1 | A | √ | √ | 2025-05-27 | CDG | @
29 | 2683 | OFO-P2683-SK-T-029 | 42" ANCHOR PIPE | 1 | B | √ | √ | 2025-07-23 | VDA | @
30 | 2683 | OFO-P2683-SK-T-030 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT USING DLS-4200 | 1 | B | √ | √ | 2025-10-17 | AMEER | @
31 | 2683 | OFO-P2683-SK-T-031 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT USING DLB-750 | 1 | B | √ | √ | 2025-08-08 | AMEER | @
32 | 2683 | OFO-P2683-SK-T-032 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DLS-4200 PIPE HENDLING CRANE | 4 | A | √ | √ | 2025-07-09 | MF | @
33 | 2683 | OFO-P2683-SK-T-033 | SCHEMATIC LAYOUT AND CRANE CAPACITY - DLB-4200 | 2 | A | √ | √ | 2025-07-22 | HZD | @ | T-007-23-07-2025
34 | 2683 | OFO-P2683-SK-T-034 | PIPELAY PROFILE FOR 20"MOL PIPELINE (DLS-4200) | 1 | B | √ | √ | 2025-08-27 | HZD | @
35 | 2683 | OFO-P2683-SK-T-035 | PROTECTOR DETAILS FOR 16'' PIPELINE | 1 | B | √ | √ | 2025-09-02 | SKS | @ | ABL-DRS-0071
36 | 2683 | OFO-P2683-SK-T-036 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 800MM) | 1 | A | √ | √ | 2025-06-26 | SKS | @ | ABL-DRS-0072
37 | 2683 | OFO-P2683-SK-T-037 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 1200MM) | 1 | A | √ | √ | 2025-06-26 | SKS | @ | ABL-DRS-0073
38 | 2683 | OFO-P2683-SK-T-038 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR TEMPORARY SUPPORT & PIPELINE PROTECTOR | 2 | B | √ | √ | 2025-07-22 | AMK | @ | T-007-23-07-2025
39 | 2683 | OFO-P2683-SK-T-039 | FLOATS DISCONNECTION BY DLB-750 | 2 | A | √ | √ | 2025-07-15 | ENH | @ | T-005 - 16-07-2025
40 | 2683 | OFO-P2683-SK-T-040 | FLOATS DISCONNECTION BY DLS-4200 | 2 | A | √ | √ | 2025-07-16 | ENH | @
41 | 2683 | OFO-P2683-SK-T-041 | FOAM FLOAT STRAPS FOR 20" PIPELINE | 1 | A | √ | √ | 2025-07-17 | SKS | @
42 | 2683 | OFO-P2683-SK-T-042 | TYPICAL ABANDONMENT & RECOVERY / LAYDOWN ARRANGEMENT WITH DLS-4200 | 1 | A | √ | √ | 2025-07-25 | VDA | @
43 | 2683 | OFO-P2683-SK-T-043 | 14’’ (355.6 Dia. )PIPE STANCHION | 1 + 5 | A,0 | √ | √ | 2025-07-25 | SKT | @
44 | 2683 | OFO-P2683-SK-T-044 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR TEMPORARY SUPPORT & PIPELINE PROTECTOR WITH MP-01 | 2 | A | √ | √ | 2025-07-29 | AMK | @ | 2683-NMDC-E-AO-PMT-T-00888 dtd. 20/08 DRS-0069 - 22-08-2025 - APPROVED
45 | 2683 | OFO-P2683-SK-T-045 | DAVIT LIFTING STROPS & AIRBAGS SPACING DETAILS FOR 20IN MOL AT ULRP WITH DLB-1000 [STBD SIDE] | 1 | A | √ | √ | 2025-08-07 | SKS | @
46 | 2683 | OFO-P2683-SK-T-046 | DLS-4200 MAIN DECK GENERAL ARRANGEMENT DURING PIPELAY | 1 | A | √ | √ | 2025-08-06 | HZD | @
47 | 2683 | OFO-P2683-SK-T-047 | ROLLER SUPPORT FOR PIPELINE PULLING | 1 | A | √ | √ | 2025-08-26 | NAR | @
48 | 2683 | OFO-P2683-SK-T-048 | LIFTING ARRANGEMENT FOR 18T POWER PACK | 1 | A | √ | √ | 2025-08-21 | AMK | @
49 | 2683 | OFO-P2683-SK-T-049 | LIFTING ARRANGEMENT FOR 42" ANCHOR PIPE | 1 | A | √ | √ | 2025-08-21 | AMK | @'
50 | 2683 | OFO-P2683-SK-T-050 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT | 1 | A | √ | √ | 2025-08-21 | AMK | @
51 | 2683 | OFO-P2683-SK-T-051 | LIFTING ARRANGEMENT FOR SPOOLING DEVICE | 1 | A | √ | √ | 2025-08-21 | AMK | @
52 | 2683 | OFO-P2683-SK-T-052 | STANCHION SUPPORT FOR SAFEEN PEARL | 1 | 0 | √ | √ | 2025-08-26 | HZD | @
53 | 2683 | OFO-P2683-SK-T-053 | DECK LAY OUT ARRANGEMENT FOR SHORE PULL EQUIPMENTS ON LCT – JAMEELAH | 1 | A | √ | √ | 2025-09-15 | CDG | @
54 | 2683 | OFO-P2683-SK-T-054 | DLS-4200 MAIN DECK GENERAL ARRANGEMENT DURING PIPE LAY | 1 | A | √ | √ | 2025-10-13 | AMK | @
55 | 2683 | OFO-P2683-SK-T-055 | MIDLINE TIE-IN ARRANGEMENT SKETCH AT KP 64 FOR 20" MOL PIPELINE FROM ULRP TO ZIRKU ISLAND | 2 | A | √ | √ | 2025-09-25 | HZD | @
56 | 2683 | OFO-P2683-SK-T-056 | LIFTING & INSTALLATION OF STINGER-9A TO STINGER 10A | 1 | A | √ | √ | 2025-10-29 | REY | @
57 | 2683 | OFO-P2683-SK-T-057 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF STINGER-10A ON CB EOS 4001 | 1 | A | √ | √ | 2025-10-22 | MF | @
58 | 2683 | OFO-P2683-SK-T-058 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 70MT GRAVITY ANCHORS ON CB EOS 4001 | 1 | A | √ | √ | 2025-10-27 | MF | @
59 | 2683 | OFO-P2683-SK-T-059 | ROV SEAFASTENING ON DLS4200 | 1 | A | √ | √ | 2025-11-13 | LEO | @
60 | 2683 | OFO-P2683-SK-T-060 | 90mm STEEL WIRE DRUM LIFTING FRAME | 2 | A | √ | √ | 2025-11-14 | LEO | @
61 | 2683 | OFO-P2683-SK-T-061 | SPOOLING DEVICE LIFTING ARRANGEMENT (N2/545/52F) | 1 | A | √ | √ | 2025-11-11 | HZD | @
62 | 2683 | OFO-P2683-SK-T-062 | 20" START-UP HEAD LIFTING & LOWRING WITH MP-01 | 1 | C | √ | √ | 2025-12-09 | LEO | @
63 | 2683 | OFO-P2683-SK-T-063 | MIDLINE TIE-IN ARRANGEMENT SKETCH AT KP 109.7 FOR 20" MOL PIPELINE FROM ULRP TO ZIRKU ISLAND | 2 | B | √ | √ | 2026-01-30 | LEO | @
64 | 2683 | OFO-P2683-SK-T-064 | RIGGING ARRANGEMENT FOR FOAM FLOAT DURING SHORE PULL | 2 | A | √ | √ | 2025-12-12 | SKS | @
65 | 2683 | OFO-P2683-SK-T-065 | TIE-IN METROLOGY CLAMP DETAILS | 1 | A | √ | √ | 2025-12-24 | SHIJU | @
66 | 2683 | OFO-P2683-SK-T-066 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR TEMPORARY SUPPORT & PIPELINE PROTECTOR BY HEA OCEANIC | 2 | A | √ | √ | 2026-01-05 | BAJ | @
67 | 2683 | OFO-P2683-SK-T-067 | 20” START-UP HEAD LIFTING & LOWERING WITH HEA OCEANIC | 3 | A | √ | √ | 2026-01-27 | SHM | @
68 | 2683 | OFO-P2683-SK-T-068 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR TEMPORARY SUPPORT & PIPELINE PROTECTOR WITH MP-02 | 2 | A | √ | √ | 2026-01-21 | CDG | @
69 | 2683 | OFO-P2683-SK-T-069 | 20" START-UP HEAD LIFTING & LOWERING WITH MP-02 | 3 | A | √ | √ | 2026-01-20 | CDG | @
70 | 2683 | OFO-P2683-SK-T-070 | STINGER-8 SECTION-A 80" BUOYANCY TANK | 1 | A | √ | √ | 2026-02-06 | SHIJU | @
71 | 2683 | OFO-P2683-SK-T-071 | PIPELAY PROFILE WITH STINGER-8A (DLB-750) | 1 | A | √ | √ | 2026-02-12 | LEO | @
72 | 2683 | OFO-P2683-SK-T-072 | DAVIT LIFTING STROPS & AIRBAGS SPACING DETAILS FOR 20IN MOL AT ULRP WITH DLB-750 [PORT SIDE] | 1 | B | √ | √ | 2026-03-18 | SSK | @
73 | 2683 | OFO-P2683-SK-T-073 | 20” START-UP HEAD LIFTING AND LOWERING WITH DLB-750 | 3 | B | √ | √ | 2026-04-01 | SRV | @
74 | 2683 | OFO-P2683-SK-T-074 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR TEMPORARY SUPPORT AND PIPELINE PROTECTOR WITH DLB-750 | 2 | A | √ | √ | 2026-03-18 | SRV | @
75 | 2683 | OFO-P2683-SK-T-075 | DLB-750 DECK LAYOUT DURING STALK ON RISER INSTALLATION | 1 | A | √ | √ | 2026-04-03 | JH | @ | SERVER ONLY
76 | 2683 | OFO-P2683-SK-T-076 | MIDLINE TIE-IN ARRANGEMENT SKETCH AT KP 109.7 FOR 20" MOL PIPELINE FROM ULRP TO ZIRKU ISLAND WITH DLS-4200 | 1 | A | √ | √ | 2026-04-10 | SSK | @
77 | 2683 | OFO-P2683-SK-T-077 | MUTAWA-401 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & PLATFORM (URLP) | 2 | A | √ | √ | 2026-05-15 | SSK | @
78 | 2683 | OFO-P2683-SK-T-078 | DLB-750 DECK LAYOUT DURING STALK ON RISER INSTALLATION |  |  |  |  | 2026-05-06 | LEO
79 | 2683 | OFO-P2683-SK-T-079 | LIFTING AND INSTALLATION OF PRESSURE PUMP AT ULRP BY MUTAWA-401 | 2 | A | √ | √ | 2026-06-08 | SRV | @
80 | 2683 | OFO-P2683-SK-T-080 | BASKET FOR IBS TANK | 1 | A | √ | √ | 2026-06-12 | SKS | @ | SERVER ONLY
81 | 2683 | OFO-P2683-SK-T-081 | DECK LAYOUT – FLOODING EQUIPMENT SET UP ON MUTAWA-11 | 1 | A | √ | √ | 2026-07-17 | SKS | @ | SERVER ONLY
82 | 2683 | OFO-P2683-SK-T-082 | MUTAWA-11 LIFTING & OFFLOADING ARRANGEMENT OF ZODIAC AT SUPPLY VESSEL & PLATFORM (URLP) | 1 | A | √ | √ | 2026-07-22 | MF | @
83 | 2683 | OFO-P2683-SK-T-083 | LIFTING & OFFLOADING ARRANGEMENT OF GRAVITY ANCHOR AT MUTAWA-101 | 1 | A | √ | √ | 2026-08-04 | SKS | @

## Cutlists
Project 2683
DETAILS OF CUT-LIST DRAWINGS TO FABRICATION
S.NO. | CUTLISTS DWG NO. | TITLE/DESCRIPTION | LATEST REV. | TRANS. REF. # | DATE | PREP. | REMARKS
1 | 2683-NN-0001-CTL | SHOREPULL HEAD FOR 20" MOL FROM ULRP TO ZIRKU ISLAND– (WITH CUTLIST 1 + 25 – REV-1) | 0 | CSE-OF-2683-T-001 | 2025-02-27 | SKT | @
|  |  | 1 | CSE-OF-2683-T-002 | 2025-03-17 | SKT | @
|  |  | 2 | CSE-OF-2683-T-003 | 2025-03-24 | SKT | @
2 | 2683-NN-0002-CTL | LAYDOWN HEAD FOR 20" MOL FROM ULRP TO ZIRKU ISLAND– (WITH CUTLIST 1 + 17– REV-1) | 0 | CSE-OF-2683-T-001 | 2025-02-27 | SKT | @
|  |  | 1 | CSE-OF-2683-T-004 | 2025-05-01 | SKT | @
3 | 2683-NN-0003-CTL | START UP HEAD FOR 20" MOL FROM ULRP TO ZIRKU ISLAND– (WITH CUTLIST 1 + 17– REV-1) | 0 | CSE-OF-2683-T-001 | 2025-02-27 | SKT | @
|  |  | 1 | CSE-OF-2683-T-004 | 2025-05-01 | SKT | @
4 | 2683-NN-0004-CTL | EMERGENCY LAYDOWN HEAD FOR 20" MOL FROM ULRP TO ZIRKU ISLAND– (WITH CUTLIST 1 + 17– REV-1) | 0 | CSE-OF-2683-T-001 | 2025-02-27 | SKT | @
|  |  | 1 | CSE-OF-2683-T-004 | 2025-05-01 | SKT | @
5 | OFO-P2683-SK-T-043-CTL | 14’’ (355.6 Dia. )PIPE STANCHION - (WITH CUTLIST 1+ 5 - REV--0) | 0 | CSE-OF-2683-T-008 | 2025-07-28 | SKT | @
6 | OFO-P2683-SK-T-029-CTL | 42" ANCHOR PIPE (WITH CUTLIST 1 + 7 - REV-0) | 0 | CSE-OF-2683-T-009 | 2025-08-12 | LEO | @
7 | 2683-NN-0014-CTL | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES @ PRISM-7605 (TRIP-2) | 0 | CSE-OF-2683-T-010 | 2025-08-26 | LEO | @
8 | 2683-NN-0007-CTL | DETAIL OF 20" TEMPORARY PIG LAUNCHER & RECEIVER FOR 20" MAIN OIL PIPELINE FROM ULRP TO ZIRKU ISLAND (WITH CUTLIST 1 + 23) | 0 | CSE-OF-2683-T-011 | 2025-12-08 | AMT | @
9 | 2683-NN-0012-CTL | TEMPORARY KNEE BRACE DETAILS FOR 20" MOL-ULRP TO ZIRKU ISLAND AT ULRP (1 + 9) | 0 | CANCELLED THE CUTLIST DGU EMAIL DTD 12-02-26' |  | NAR | @
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
DLB-750 MOORING ANALYSIS DURING MIDLINE OF 20" MOL