## Documents - Pipeline & Cable
|  | SAUDI ARAMCO (LTA) FOR OFFSHORE FACILITIES | [10 empty] | NPCC DOC. No.:
CRPO # 128 -REPLACEMENT OF OFFSHORE 48" ZULUF TRUNKLINE (ZS-1)
|  | NPCC PROJECT NO. 2734-2735 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 2023-12-26
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | Pipe Stacking Analysis Report | 2734-2735-NN-RP-001 | A | 2 |  | 2024-09-23 | CSE-2734-2735-PMT-T-002 | 2024-09-24 | 2734-2735-NMDC-T-01067 | 2024-10-15 | T-1509-24 - T-01067 | 2 | 2025-02-20 | 2734-2735-NMDC-MWS-T-0006
|  |  | B | 2 |  | 2025-03-25 | CSE-2734-2735-PMT-T-032 | 2025-04-01 | 2734-2735-NMDC-T-02146 | 2025-07-16 | OP&CPD-ROZF-T-1467-25 | 4
2 | Pipe lay Analysis Report for 48” Trunkline From Zuluf GOSP-2 to SFNY Onshore by DLB-750 | 2734-2735-NN-RP-002 | A | 2 |  | 2024-12-26 | CSE-2734-2735-PMT-T-010 | 2024-12-31 | 2734-2735-NMDC-T-01616 | 2025-03-24 | OP&CPD-ROZF-T-0480-25 | 2
|  |  | B | 2 |  | 2025-03-28 | CSE-2734-2735-PMT-T-036 | 2025-04-04 | 2734-2735-NMDC-T-02159
|  |  | 00 | 3 |  | 2025-07-31 | CSE-2734-2735-PMT-T-065 | 2025-07-31 | 2734-2735-NMDC-T-02906
3 | Shore pull Analysis Report for 48” Trunkline From Zuluf GOSP-2 to SFNY Onshore | 2734-2735-NN-RP-003 | A | 2 |  | 2024-12-26 | CSE-2734-2735-PMT-T-011 | 2025-01-08 | 2734-2735-NMDC-T-01659 | 2025-01-29 | INFO MAIL | APPROVED
|  |  | B | 2 |  | 2025-05-05 | CSE-2734-2735-PMT-T-45 | 2025-05-08 | 2734-2735-NMDC-T-02353
|  |  | 00 | 3 |  | 2025-07-15 | CSE-2734-2735-PMT-T-61 | 2025-07-17 | 2734-2735-NMDC-T-02816
4 | Midline tie-in Analysis Report for 48” Trunkline From Zuluf GOSP-2 to SFNY Onshore | 2734-2735-NN-RP-004
5 | LIFTING ANALYSIS FOR SPOOLS AT Zuluf GOSP-2 | 2734-2735-NN-RP-005
6 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-258 [with DLB-750] -TRIP-1 | 2734-2735-NN-RP-006 | A |  |  | 2025-02-07 | CSE-2734-2735-PMT-T-015 | 2025-02-23 | 2734-2735-NMDC-T-01920 |  |  |  | 2025-02-13 | 2734-2735-NMDC-MWS-T-0004 | 2025-02-17 | MDDXB 6145-MD-03-1308-01 | comments
|  |  | B |  |  | 2025-02-25 | CSE-2734-2735-PMT-T-025 | 2025-03-05 | 2734-2735-NMDC-T-01986 |  |  |  | 2025-02-26 | 2734-2735-NMDC-MWS-T-0007 | 2025-03-03 | MDDXB 6145-MD-03-1308-02 | comments
|  |  | 00 | 3 |  | 2025-06-20 | CSE-2734-2735-PMT-T-056 | 2025-06-23 | 2734-2735-NMDC-T-02637 |  |  |  | 2025-06-23 | 2734-2735-NMDC-MWS-T-0020
7 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-258 [with DELMA-2000] -TRIP-1 | 2734-2735-NN-RP-007 | A |  |  | 2025-02-12 | CSE-2734-2735-PMT-T-022 | 2024-02-22 | 2734-2735-NMDC-T-01921 |  |  |  | 2025-02-13 | 2734-2735-NMDC-MWS-T-0003 | 2025-02-18 | MDDXB 6145-MD-05-1306-01 | comments
|  |  | B |  |  | 2025-02-25 | CSE-2734-2735-PMT-T-025 | 2025-03-05 | 2734-2735-NMDC-T-01987 |  |  |  | 2025-02-26 | 2734-2735-NMDC-MWS-T-0007 | 2025-03-03 | MDDXB 6145-MD-05-1306-02 | Approved
|  |  | C |  |  | 2025-03-27 | CSE-2734-2735-PMT-T-034 | 2025-04-03 | 2734-2735-NMDC-T-02155 |  |  |  | 2025-04-03 | 2734-2735-NMDC-MWS-T-0015 | 2025-04-03 | MDDXB 6145-MD-05-1306-03 | Approved
8 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-259 [with DELMA-2000] -TRIP-2 | 2734-2735-NN-RP-008 | A |  |  | 2025-02-14 | CSE-2734-2735-PMT-T-023 | 2024-02-22 | 2734-2735-NMDC-T-01924 |  |  |  | 2025-02-17 | 2734-2735-NMDC-MWS-T-0005 | 2025-03-10 | MDDXB 6145-MD-07-1311-01 | comments
|  |  | B |  |  | 2025-03-18 | CSE-2734-2735-PMT-T-028 | 2025-03-20 | 2734-2735-NMDC-T-02063 |  |  |  | 2025-03-20 | 2734-2735-NMDC-MWS-T-0009
|  |  | C |  |  | 2025-03-24 | CSE-2734-2735-PMT-T-031 | 2025-06-03 | 2734-2735-NMDC-T-02543 |  |  |  | 2025-03-25 | 2734-2735-NMDC-MWS-T-0013
9 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-4) | 2734-2735-NN-RP-009
10 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON GAC-82 | 2734-2735-NN-RP-010 | A | 2 |  | 2025-01-27 | CSE-2734-2735-PMT-T-017 | 2025-02-03 | 2734-2735-NMDC-T-01802 | 2025-02-14 | OP&CPD-ROZF-T-0298-25 | APPROVED | 2025-02-04 | 2734-2735-NMDC-MWS-T-0001
|  |  | B | 2 |  | 2025-03-19 | CSE-2734-2735-PMT-T-030 | 2025-03-21 | 2734-2735-NMDC-T-02070 |  |  |  | 2025-03-21 | 2734-2735-NMDC-MWS-T-0010 | 13-02-25 26-03-25 | MDDXB 6145-MD-02-1303-02 MDDXB 6145-MD-02-1303-03 | Approved
11 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS (TRIP-2) | 2734-2735-NN-RP-011
12 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS (TRIP-3) | 2734-2735-NN-RP-012
13 | PIPELAY ANALYSIS REPORT FOR 48" TRUNKLINE BY DELMA-2000 | 2734-2735-NN-RP-013 | A | 2 |  | 2024-12-01 | CSE-2734-2735-PMT-T-008 | 2024-12-10 | 2734-2735-NMDC-T-01510 | 2025-01-28 | OP&CPD-ROZF-T-0158-25 | 2
|  |  | B | 2 |  | 2025-02-20 | CSE-2734-2735-PMT-T-024 | 2025-02-20 | 2734-2735-NMDC-T-01910
|  |  | 00 | 3 |  | 2025-03-26 | CSE-2734-2735-PMT-T-033 | 2025-03-27 | 2734-2735-NMDC-T-02115 | 2025-04-18 | OP&CPD-ROZF-T-0491-25 | 6
|  |  | 01 | 3 |  | 2025-04-25 | CSE-2734-2735-PMT-T-041 | 2025-04-27 | 2734-2735-NMDC-T-02286
|  |  | 02 | 3 |  | 2025-07-16 | CSE-2734-2735-PMT-T-062 | 2025-07-17 | 2734-2735-NMDC-T-02815 | 2026-04-10 | OP&CPD-ROZF-T-0175-2 | 2
14 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-259 [with DLB-750] -TRIP-2 | 2734-2735-NN-RP-014 | A | 2 |  | 2025-03-04 | CSE-2734-2735-PMT-T-026 | 2025-03-04 | 2734-2735-NMDC-T-01973 |  |  |  | 2025-03-05 | 2734-2735-NMDC-MWS-T-0008 | 2025-03-11 | MDDXB 6145-MD-09-1315-01 | Approved
|  |  | B | 3 |  | 2025-06-04 | CSE-2734-2735-PMT-T-054 | 2025-07-03 | 2734-2735-NMDC-T-02726 |  |  |  | 2025-07-03 | 2734-2735-NMDC-MWS-T-0022 | 2025-06-10 | MDDXB 6145-MD-09-1315-02 | Approved
15 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-259-TRIP-3 [WITH DLB-750] | 2734-2735-NN-RP-015 | A | 2 |  | 2025-03-19 | CSE-2734-2735-PMT-T-029 | 2025-04-01 | 2734-2735-NMDC-T-02143 |  |  |  | 2025-04-02 | 2734-2735-NMDC-MWS-T-0014 | 2025-04-11 | MDDXB 6145-MD-12-1318-01 | Approved
|  |  | B | 2 |  | 2025-06-09 | CSE-2734-2735-PMT-T-055 | 2025-06-15 | 2734-2735-NMDC-T-02567 |  |  |  | 2025-06-09 | email | 2025-06-11 | MDDXB 6145-MD-12-1318-02 | Approved
16 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON GOGAS-250-TRIP-4 [WITH DLB-750] | 2734-2735-NN-RP-016
17 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON GOGAS-255-TRIP-5 [WITH DLB-750] | 2734-2735-NN-RP-017
18 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON GAC-82-TRIP-3 [with DELMA-2000] | 2734-2735-NN-RP-018 | A | 2 |  | 2025-04-15 | CSE-2734-2735-PMT-T-038 | 2025-04-16 | 2734-2735-NMDC-T-02232 |  |  |  | 2025-04-24 | 2734-2735-NMDC-MWS-T-0017 | 2025-04-24 | MDDXB 6145-MD-13-1322-01 | Approved
19 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF MANITOWOC-999 CRANE ON ASTRO-3302 | 2734-2735-NN-RP-019 | A | 2 | HAF | 2025-04-25 | CSE-2734-2735-PMT-T-042 | 2025-07-15 | 2734-2735-NMDC-T-02789 |  |  |  | 2025-04-29 | email | 2025-04-30 | MDDXB 6145-MD-15-1324-02 | Approved
20 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-288-TRIP-4 [WITH DELMA-2000] | 2734-2735-NN-RP-020 | A | 3 |  | 2025-05-14 | CSE-2734-2735-PMT-T-046 | 2025-05-14 | 2734-2735-NMDC-T-02401 |  |  |  | 2025-05-14 | E-MAIL | 2025-05-14 | MDDXB 6145-MD-18-1328-01 - | Approved
21 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON CASPIAN-280-TRIP-5 [WITH DELMA-2000] | 2734-2735-NN-RP-021 | A | 3 |  | 2025-05-18 | CSE-2734-2735-PMT-T-047 | 2025-05-21 | 2734-2735-NMDC-T-02445 |  |  |  | 2025-05-19 | E-MAIL | 2025-05-19 | MDDXB 6145-MD-19-1329-01 - | Approved
22 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON AESEN-2803-TRIP-6 [WITH DELMA-2000] | 2734-2735-NN-RP-022 | A | 3 |  | 2025-05-30 | CSE-2734-2735-PMT-T-051 | 2025-05-30 | 2734-2735-NMDC-T-02520 |  |  |  | 2025-06-02 | 2734-2735-NMDC-MWS-T-0019 | 2025-06-03 | MDDXB 6145-MD-21-1332-01 | Approved
23 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON GOGAS-252 -TRIP-10-[with DLB-750] | 2734-2735-NN-RP-023 | A | 3 |  | 2025-11-25 | CSE-2734-2735-PMT-T-093 | 2025-11-25 | 2734-2735-NMDC-T-03538 |  |  |  | 2025-11-25 | 2734-2735-NMDC-MWS-T-0052 | 2025-11-26 | MDDXB 6145-MD-26-1354-01 | Approved
24 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-258 -TRIP-11-[with DLB-750] | 2734-2735-NN-RP-024 | A | 3 |  | 2025-11-27 | CSE-2734-2735-PMT-T-094 | 2025-11-27 | 2734-2735-NMDC-T-03548 |  |  |  | 2025-11-27 | 2734-2735-NMDC-MWS-T-0053
25 | SEAFASTENING DESIGN REPORT DURING TRANSPORTATION OF CC PIPES ON GOGAS-250 (TRIP-13) [with DLB-750] | 2734-2735-NN-RP-025 | A | 3 |  | 2025-11-28 | CSE-2734-2735-PMT-T-097 | 2025-12-03 | 2734-2735-NMDC-T-03561 |  |  |  | 2025-12-03 | 2734-2735-NMDC-MWS-T-0056
26 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF STINGER-9A & MISC ITEMS ON GAC-82 | 2734-2735-NN-RP-026 | A | 3 |  | 2016-02-05 | CSE-2734-2735-PMT-T-103
27 | SEA FASTENING DESIGN REPORT DURING TRANSPORTATION OF SPOOLS ON MICLYN-258 | 2734-2735-NN-RP-027 | A | 3 | PKR | 2016-03-25 | CSE-2734-2735-PMT-T-107 | 2026-04-06 | 2734-2735-NMDC-T-04138 | [5 empty] | 2026-04-14 | MDDXB 6145-MD-31-1369-01 | Approved
28
29
30

## Documents - Naval Marine
|  | SAUDI ARAMCO (LTA) FOR OFFSHORE FACILITIES | [10 empty] | NPCC DOC. No.:
CRPO # 128 -REPLACEMENT OF OFFSHORE 48" ZULUF TRUNKLINE (ZS-1)
|  | NPCC PROJECT NO. 2734-2735 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (Naval Marine) | [10 empty] | DATE : |  |  |  | 2023-12-26
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | BERTHING ANALYSIS FOR WORKBOATS | 2734-2735-ZZ-CL-001 | A | 2 |  | 2023-12-26 | CSE-2734-2735-PMT-T-001 | [10 empty] | do not submit company
2 | DLB750 MOORING ANALYSIS DURING SHOREPULL AND LAYING OF 48” TRUNKLINE FROM SHORE TO MIDLINE TIE IN | 2734-2735-ZZ-CL-002 | A | 2 |  | 2025-01-31 | CSE-2734-2735-PMT-T-020 | 2025-02-02 | 2734-2735-NMDC-T-01798 | 2025-02-17 | OP&CPD-ROZF-T-0260-25 | 4
|  |  | 00 | 2 |  | 2025-08-25 | CSE-2734-2735-PMT-T-069
3 | MOORING ANALYSIS DURING PIPELAYING OF 48” Trunkline From Zuluf GOSP-2 to SFNY Onshore | 2734-2735-ZZ-CL-003
4 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-258 -TRIP-1 [with DLB-750] | 2734-2735-ZZ-CL-004 | A |  |  | 2025-02-07 | CSE-2734-2735-PMT-T-015 | 2025-02-23 | 2734-2735-NMDC-T-01919 |  |  |  | 2025-02-13 | 2734-2735-NMDC-MWS-T-0004 | 2025-02-17 | MDDXB 6145-MD-04-1309-01 | Approved
|  |  | 00 | 3 |  | 2025-06-20 | CSE-2734-2735-PMT-T-056 | 2025-06-23 | 2734-2735-NMDC-T-02638 |  |  |  | 2025-06-23 | 2734-2735-NMDC-MWS-T-0020
5 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-258 [with DELMA-2000] -TRIP-1 | 2734-2735-ZZ-CL-005 | A |  |  | 2025-02-12 | CSE-2734-2735-PMT-T-022 | 2025-02-22 | 2734-2735-NMDC-T-01922 |  |  |  | 2025-02-13 | 2734-2735-NMDC-MWS-T-0003 | 2025-02-18 | MDDXB 6145-MD-06-1307-01 | Approved
|  |  | B |  |  | 2025-03-27 | CSE-2734-2735-PMT-T-034 | 2025-04-03 | 2734-2735-NMDC-T-02156 |  |  |  | 2025-04-03 | 2734-2735-NMDC-MWS-T-0015 | 2025-04-03 | MDDXB 6145-MD-06-1307-02 | Approved
6 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-259 -TRIP-2 [with DELMA-2000] | 2734-2735-ZZ-CL-006 | A |  |  | 2025-02-14 | CSE-2734-2735-PMT-T-023 | 2024-02-22 | 2734-2735-NMDC-T-01925 |  |  |  | 2025-02-17 | 2734-2735-NMDC-MWS-T-0005 | 2025-03-10 | MDDXB 6145-MD-08-1312-01 | Approved
|  |  | B |  |  | 2025-03-24 | CSE-2734-2735-PMT-T-031 | [5 empty] | 2025-03-25 | 2734-2735-NMDC-MWS-T-0013 | 2025-03-25 | MDDXB 6145-MD-08-1312-02 | Approved
7 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES TRIP-4 | 2734-2735-ZZ-CL-007
8 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CONCRETE SLEEPERS ON GAC-82 (TRIP-1) | 2734-2735-ZZ-CL-008 | A | 2 |  | 2025-01-27 | CSE-2734-2735-PMT-T-017 | 2025-02-03 | 2734-2735-NMDC-T-01803 | 2025-02-14 | OP&CPD-ROZF-T-0307-25 | 4 | 2025-02-04 | 2734-2735-NMDC-MWS-T-0001 | 2025-02-08 | MDDXB 6145-MD-01-1304-01 | Approved
|  |  | B | 2 |  | 2025-03-18 | CSE-2734-2735-PMT-T-027 | 2025-03-21 | 2734-2735-NMDC-T-02072 |  |  |  | 2025-03-21 | 2734-2735-NMDC-MWS-T-0012 | 2025-03-26 | MDDXB 6145-MD-01-1304-02 | Approved
9 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CONCRETE SLEEPERS (TRIP-2) | 2734-2735-ZZ-CL-009
10 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CONCRETE SLEEPERS (TRIP-3) | 2734-2735-ZZ-CL-010
11 | DLB750 STORM MOORING ANALYSIS AND CATENARIES | 2734-2735-ZZ-CL-011
12 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-259 -TRIP-2 [with DLB-750] | 2734-2735-ZZ-CL-012 | A | 2 |  | 2025-03-04 | CSE-2734-2735-PMT-T-026 | 2025-03-04 | 2734-2735-NMDC-T-01974 |  |  |  | 2025-03-05 | 2734-2735-NMDC-MWS-T-0008 | 2025-03-11 | MDDXB 6145-MD-10-1316-01 | Approved
|  |  | B | 3 |  | 2025-06-04 | CSE-2734-2735-PMT-T-054 | 2025-07-03 | 2734-2735-NMDC-T-02727 |  |  |  | 2025-07-03 | 2734-2735-NMDC-MWS-T-0022 | 2025-06-10 | MDDXB 6145-MD-09-1316-02 | Approved
13 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-259-TRIP-3 [WITH DLB-750] | 2734-2735-ZZ-CL-013 | A | 2 |  | 2025-03-19 | CSE-2734-2735-PMT-T-029 | 2025-04-11 | 2734-2735-NMDC-T-02144 |  |  |  | 2025-04-02 | 2734-2735-NMDC-MWS-T-0014 | 2025-04-11 | MDDXB 6145-MD-11-1317-01 | Approved
|  |  | B | 2 |  | 2025-06-09 | CSE-2734-2735-PMT-T-055 | 2025-06-11 | 2734-2735-NMDC-T-02568 |  |  |  | 2025-06-09 | email | 2025-06-11 | MDDXB 6145-MD-11-1317-02 | Approved
14 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON GOGAS-250-TRIP-4 [WITH DLB-750] | 2734-2735-ZZ-CL-014
15 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON GOGAS-255-TRIP-5 [WITH DLB-750] | 2734-2735-ZZ-CL-015
16 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON GAC-82-TRIP-3 [WITH DELMA-2000] | 2734-2735-ZZ-CL-016 | A | 2 |  | 2025-04-15 | CSE-2734-2735-PMT-T-038 | 2025-04-16 | 2734-2735-NMDC-T-02233 |  |  |  | 2025-04-24 | 2734-2735-NMDC-MWS-T-0017 | 2025-04-25 | MDDXB 6145-MD-14-1321-01 | Approved
|  |  | B | 3 |  | 2025-10-23 | CSE-2734-2735-PMT-T-082 | 2025-10-23 | 2734-2735-NMDC-T-03368 |  |  |  | 2025-10-23 | 2734-2735-NMDC-MWS-T-0041
17 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CRAWLER CRANE & MISC ITEMS ON ASTRO-3302 | 2734-2735-ZZ-CL-017 | A | 2 | PKR | 2025-04-25 | CSE-2734-2735-PMT-T-042 | 2025-07-15 | 2734-2735-NMDC-T-02788
18 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-288-TRIP-4 [WITH DELMA-2000] | 2734-2735-ZZ-CL-018 | A | 3 |  | 2025-05-14 | CSE-2734-2735-PMT-T-046 | 2025-05-14 | 2734-2735-NMDC-T-02402 |  |  |  | 2025-05-14 | email | 2025-05-18 | MDDXB 6145-MD-17-1327-01 | Approved
19 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON CASPIAN-280-TRIP-5 [WITH DELMA-2000] | 2734-2735-ZZ-CL-019 | A | 3 |  | 2025-05-18 | CSE-2734-2735-PMT-T-047 | 2025-05-21 | 2734-2735-NMDC-T-02446 |  |  |  | 2025-05-19 | E-MAIL | 2025-05-19 | MDDXB 6145-MD-19-1329-01 | Approved
20 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON AESEN-2803-TRIP-6 [WITH DELMA-2000] | 2734-2735-ZZ-CL-020 | A | 3 |  | 2025-05-30 | CSE-2734-2735-PMT-T-051 | 2025-05-30 | 2734-2735-NMDC-T-02521 |  |  |  | 2025-06-02 | 2734-2735-NMDC-MWS-T-0019 | 2025-06-03 | MDDXB 6145-MD-22-1333-01 | Approved
|  |  | B | 3 |  | 2025-10-20 | CSE-2734-2735-PMT-T-079 | 2025-10-21 | 2734-2735-NMDC-T-03335 |  |  |  | 2025-10-21 | 2734-2735-NMDC-MWS-T-0038 |  |  |  | reissued 20/10
21 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF MISC ITEMS ON GOGAS-255 [WITH DELMA-2000] | 2734-2735-ZZ-CL-021 | A | 3 |  | 2025-10-29 | CSE-2734-2735-PMT-T-085 | [5 empty] | 2025-10-31 | 2734-2735-NMDC-MWS-T-0043
22 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON GOGAS-252 -TRIP-10 [with DLB-750] | 2734-2735-ZZ-CL-022 | A | 3 |  | 2025-11-25 | CSE-2734-2735-PMT-T-093 | 2025-11-25 | 2734-2735-NMDC-T-03539 |  |  |  | 2025-11-25 | 2734-2735-NMDC-MWS-T-0052 | 2025-11-26 | MDDXB 6145-MD-27-1352-01 | Approved
23 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON MICLYN-258 -TRIP-11 [WITH DLB-750] | 2734-2735-ZZ-CL-023 | A | 3 |  | 2025-11-27 | CSE-2734-2735-PMT-T-094 | 2025-11-27 | 2734-2735-NMDC-T-03547 |  |  |  | 2025-11-27 | 2734-2735-NMDC-MWS-T-0053
24 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON GOGAS-250 (TRIP-13) [with DLB-750] | 2734-2735-ZZ-CL-024 | A | 3 | PKR | 2025-11-28 | CSE-2734-2735-PMT-T-097 | 2025-12-03 | 2734-2735-NMDC-T-03562 |  |  |  | 2025-12-03 | 2734-2735-NMDC-MWS-T-0056
25 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF STINGER-9A & MISC ITEMS ON GAC-82 | 2734-2735-ZZ-CL-025 | A | 3 |  | 2026-02-05 | CSE-2734-2735-PMT-T-103
26 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SPOOLS ON MICLYN-258 | 2734-2735-ZZ-CL-026 | A | 3 |  | 2026-03-22 | CSE-2734-2735-PMT-T-106 | 2026-04-06 | 2734-2735-NMDC-T-04145
27
28
29
30

## Drawings
|  | SAUDI ARAMCO (LTA) FOR OFFSHORE FACILITIES | [10 empty] | NPCC DOC. No.:
CRPO # 128 -REPLACEMENT OF OFFSHORE 48" ZULUF TRUNKLINE (ZS-1)
|  | NPCC PROJECT NO. 2734-2735 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (Drawings) | [10 empty] | DATE : |  |  |  | 2023-12-26
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ARAMCO OFFSHORE | [7 empty] | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO ARAMCO |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | SHORE PULL HEAD FOR 48" PIPELINE | 2734-2735-NN-0001 | A | 3 |  | 2024-10-17 | CSE-2734-2735-PMT-T-006 | 2025-02-05 | 2734-2735-NMDC-T-01833
|  |  | B | 3 |  | 2025-01-03 | CSE-2734-2735-PMT-T-013 | 2025-01-07 | 2734-2735-NMDC-T-01638
2 | START UP HEAD FOR 48" PIPELINE AT GOSP-2 | 2734-2735-NN-0002 | A | 3 |  | 2024-10-17 | CSE-2734-2735-PMT-T-006 | 2025-02-05 | 2734-2735-NMDC-T-01834
|  |  | B | 3 |  | 2025-04-17 | CSE-2734-2735-PMT-T-040 | 2025-05-30 | 2734-2735-NMDC-T-02514
|  |  | C | 3 |  | 2025-05-19 | CSE-2734-2735-PMT-T-048 | 2025-06-03 | 2734-2735-NMDC-T-02538
3 | LAYDOWN HEAD FOR 48" PIPELINE (SECTION 3) AT DUMMY SPOOL | 2734-2735-NN-0003 | A | 3 |  | 2024-10-17 | CSE-2734-2735-PMT-T-006 | 2025-02-05 | 2734-2735-NMDC-T-01818
|  |  | B | 3 |  | 2025-01-29 | CSE-2734-2735-PMT-T-018 | 2025-02-05 | 2734-2735-NMDC-T-01819
|  |  | C | 3 |  | 2025-04-17 | CSE-2734-2735-PMT-T-040 | 2025-05-30 | 2734-2735-NMDC-T-02515
|  |  | D | 3 |  | 2025-05-19 | CSE-2734-2735-PMT-T-048 | 2025-06-03 | 2734-2735-NMDC-T-02539
4 | EMERGENCY LAYDOWN HEAD FOR 48" PIPELINE | 2734-2735-NN-0004 | A | 3 |  | 2024-10-17 | CSE-2734-2735-PMT-T-006 | 2025-02-05 | 2734-2735-NMDC-T-01820
|  |  | B | 3 |  | 2025-01-25 | CSE-2734-2735-PMT-T-016 | 2025-01-25 | 2734-2735-NMDC-T-01751
|  |  | C | 3 |  | 2025-04-17 | CSE-2734-2735-PMT-T-040 | 2025-05-30 | 2734-2735-NMDC-T-02516
5 | START UP HEAD FOR 48" PIPELINE AT MIDLINE SPOOL | 2734-2735-NN-0005 | A | 3 |  | 2024-10-17 | CSE-2734-2735-PMT-T-006
|  |  | B | 3 |  | 2025-04-17 | CSE-2734-2735-PMT-T-040
6 | FLANGE PROTECTOR DETAILS FOR 48" PIPELINE HEADS 100mm THK CONCRETE | 2734-2735-NN-0006 | A | 3 |  | 2024-10-29 | CSE-2734-2735-PMT-T-007 | 2024-10-31 | 2734-2735-NMDC-T-01284 | 2024-11-20 | OP&CPD-ROZF-T-1852-24 | 2
|  |  | B | 3 |  | 2025-01-16 | CSE-2734-2735-PMT-T-014 | 2025-02-06 | 2734-2735-NMDC-T-01831
7 | FLANGE PROTECTOR DETAILS FOR 48" PIPELINE HEADS 75mm THK CONCRETE | 2734-2735-NN-0007 | A | 3 |  | 2024-10-29 | CSE-2734-2735-PMT-T-007 | 2024-10-31 | 2734-2735-NMDC-T-01284 | 2024-11-20 | OP&CPD-ROZF-T-1852-24 | 2
|  |  | B | 3 |  | 2025-01-16 | CSE-2734-2735-PMT-T-014 | 2025-02-05 | 2734-2735-NMDC-T-01830
8 | Flange Protector Details for 48" Dummy spool | 2734-2735-NN-0008
9 | Temporary Scraper Launcher and Receiver Details for 48” Pipelines | 2734-2735-NN-0009
10 | TYPICAL LIFTING OF CONCRETE SLEEPERS BY DELMA-2000 | 2734-2735-NN-0010 | A | 2 |  | 2024-09-18 | CSE-2734-2735-PMT-T-003 | 2024-09-23 | 2734-2735-NMDC-T-01066 | 2024-10-07 | OP&CPD-ROZF-T-1479-24 | 6 | [5 empty] | APPROVED WITH COMMENTS
|  |  | B |  |  | 2024-12-31 | CSE-2734-2735-PMT-T-012 | 2025-01-06 | 2734-2735-NMDC-T-01634
|  |  | C |  |  | 2025-03-29 | CSE-2734-2735-PMT-T-035 | 2025-04-07 | 2734-2735-NMDC-T-02170
11 | 48" SPOOL LIFTING AND INSTALLATION ARRANGEMENT FROM OIL TRUNKLINE ZULF GOSP-2 TO ONSHRE PLATFORM SPOOL USING SHUJAA-2000 | 2734-2735-NN-0011 |  | cdg
12 | TEMPORARY KNEE BRACE DETAILS FOR 48" AT ZULF GOSP-2 | 2734-2735-NN-0012
13 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN 258. (TRIP-1) (TRENCH#01 WITH DLB-750) | 2734-2735-NN-0013 | A | 2 |  | 2024-09-26 | CSE-2734-2735-PMT-T-005 | 2024-10-02 | 2734-2735-NMDC-T-01130
|  |  | B | 2 |  | 2025-01-21 | CSE-2734-2735-PMT-T-015 | 2025-02-05 | 2734-2735-NMDC-T-01832 |  |  |  | 2025-02-13 | 2734-2735-NMDC-MWS-T-0004
|  |  | 00 | 3 |  | 2025-06-04 | CSE-2734-2735-PMT-T-053
|  |  | 00A | 3 |  | 2025-06-20 | CSE-2734-2735-PMT-T-056 | 2025-06-23 | 2734-2735-NMDC-T-02639 |  |  |  | 2025-06-23 | 2734-2735-NMDC-MWS-T-0020
14 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-258 (TRIP-1) (with Delma-2000) | 2734-2735-NN-0014 | A |  |  | 2025-02-12 | CSE-2734-2735-PMT-T-022 | 2024-02-22 | 2734-2735-NMDC-T-01923 |  |  |  | 2025-02-13 | 2734-2735-NMDC-MWS-T-0003
|  |  | B |  |  | 2025-03-27 | CSE-2734-2735-PMT-T-034 | 2025-04-03 | 2734-2735-NMDC-T-02154 |  |  |  | 2025-04-03 | 2734-2735-NMDC-MWS-T-0015
|  |  | 00 |  |  | 2025-04-15 | CSE-2734-2735-PMT-T-039 | 2025-07-15 | 2734-2735-NMDC-T-02786
15 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-259 (TRIP-2) (with Delma-2000) | 2734-2735-NN-0015 | A | 3 |  | 2025-02-14 | CSE-2734-2735-PMT-T-023 | 2024-02-22 | 2734-2735-NMDC-T-01926 |  |  |  | 2025-02-17 | 2734-2735-NMDC-MWS-T-0005
|  |  | B | 3 |  | 2025-03-24 | CSE-2734-2735-PMT-T-031 | 2025-06-03 | 2734-2735-NMDC-T-02545 |  |  |  | 2025-03-25 | 2734-2735-NMDC-MWS-T-0013
16 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-258 (TRIP-4) (WITH DLB-750) | 2734-2735-NN-0016 | A | 3 | JH -06/3 MF-23-06 | 2025-06-29 | CSE-2734-2735-PMT-T-058 | 2025-06-30 | 2734-2735-NMDC-T-02708 |  |  |  | 2025-06-30 | 2734-2735-NMDC-MWS-T-0021
|  |  | B | 3 |  | 2025-07-29 | CSE-2734-2735-PMT-T-064 |  | MWS ONLY |  |  |  | 2025-07-30 | 2734-2735-NMDC-MWS-T-0026
|  |  | C | 3 |  | 2025-10-23 | CSE-2734-2735-PMT-T-083 | 2025-10-24 | 2734-2735-NMDC-T-03373 |  |  |  | 2025-10-24 | 2734-2735-NMDC-MWS-T-0042
17 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES @ GOGAS-250 (TRIP-5) (WITH DLB-750 | 2734-2735-NN-0017 | A | 3 |  | 2025-07-31 | CSE-2734-2735-PMT-T-066 | 2025-08-01 | 2734-2735-NMDC-T-02915 |  |  |  | 2025-08-07 | 2734-2735-NMDC-MWS-T-0027
|  |  | B | 3 |  | 2025-10-16 | CSE-2734-2735-PMT-T-077 | 2025-10-17 | 2734-2735-NMDC-T-03326 |  |  |  | 2025-10-17 | 2734-2735-NMDC-MWS-T-0036
|  |  | C | 3 |  | 2025-10-30 | CSE-2734-2735-PMT-T-086 | 2025-10-30 | 2734-2735-NMDC-T-03401 |  |  |  | 2025-10-31 | 2734-2735-NMDC-MWS-T-0044
18 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 48” CC PIPES @ AESEN-2803 (TRIP-6) (WITH DELMA-2000) | 2734-2735-NN-0018 | A | 3 |  | 2025-05-30 | CSE-2734-2735-PMT-T-051 | 2025-05-30 | 2734-2735-NMDC-T-02522 |  |  |  | 2025-06-02 | 2734-2735-NMDC-MWS-T-0019
19 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ GAC-82 CB (TRIP-7) [WITH DELMA-2000] | 2734-2735-NN-0019 | A | 3 | JH -01/7 | 2025-07-07 | CSE-2734-2735-PMT-T-060 | 2025-07-14 | 2734-2735-NMDC-T-02752 |  |  |  | 2025-07-07 | 2734-2735-NMDC-MWS-T-0023
|  |  | B | 3 |  | 2025-07-29 | CSE-2734-2735-PMT-T-063 | 2025-07-29 | 2734-2735-NMDC-T-02892 |  |  |  | 2025-07-29 | 734-2735-NMDC-MWS-T-0025
20 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-288 (TRIP-8) (WITH DELMA-2000) | 2734-2735-NN-0020 | A | 3 |  | 2025-07-31 | CSE-2734-2735-PMT-T-067 | 2025-08-01 | 2734-2735-NMDC-T-02914 |  |  |  | 2025-08-07 | 2734-2735-NMDC-MWS-T-0028
|  |  | B | 3 |  | 2025-09-01 | CSE-2734-2735-PMT-T-070 | 2025-09-01 | 2734-2735-NMDC-T-03094 |  |  |  | 2025-09-04 | 2734-2735-NMDC-MWS-T-0029
21 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES ON CASPIAN-280 CB (TRIP-9) | 2734-2735-NN-0021 | A | 3 |  | 2025-09-04 | CSE-2734-2735-PMT-T-071 | 2025-09-04 | 2734-2735-NMDC-T-03099 |  |  |  | 2025-09-04 | 2734-2735-NMDC-MWS-T-0030
22 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES @ AESEN-2803 (TRIP-10) WITH DELMA-2000 | 2734-2735-NN-0022 | A | 3 |  | 2025-09-12 | CSE-2734-2735-PMT-T-073 | 2025-09-15 | 2734-2735-NMDC-T-03137 |  |  |  | 2025-09-15 | 2734-2735-NMDC-MWS-T-0030
|  |  | 00 | 3 |  | 2025-10-13 | CSE-2734-2735-PMT-T-076 | 2025-10-17 | 2734-2735-NMDC-T-03317 |  |  |  | 2025-10-17 | 2734-2735-NMDC-MWS-T-0034
23 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES ON GAC-82 (TRIP-11) [WITH DELMA-2000] | 2734-2735-NN-0023 | A | 3 |  | 2025-09-09 | CSE-2734-2735-PMT-T-072 | 2025-09-10 | 2734-2735-NMDC-T-03122 |  |  |  | 2025-09-10 | 2734-2735-NMDC-MWS-T-0031
|  |  | B | 3 |  | 2025-10-21 | CSE-2734-2735-PMT-T-081 | 2025-10-22 | 2734-2735-NMDC-T-03360 |  |  |  | 2025-10-22 | 2734-2735-NMDC-MWS-T-0039
24 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE PIPES ON MICLYN-288 CB (TRIP-12) [WITH DELMA-2000] | 2734-2735-NN-0024 | A | 3 |  | 2025-10-08 | CSE-2734-2735-PMT-T-074 | 2025-10-08 | 2734-2735-NMDC-T-03259 |  |  |  | 2025-10-08 | 2734-2735-NMDC-MWS-T-0033
|  |  | B | 3 |  | 2025-10-21 | CSE-2734-2735-PMT-T-080 | 2025-10-23 | 2734-2735-NMDC-T-03364 |  |  |  | 2025-10-23 | 2734-2735-NMDC-MWS-T-0040
25 | LOADING ARRANGEMENT & SEAFASTENING OF 48” CC PIPES ON CASPIAN-280 CB (TRIP-13) [WITH DELMA-2000] | 2734-2735-NN-0025 | A | 3 |  | 2025-11-04 | CSE-2734-2735-PMT-T-087 | 2025-11-05 | 2734-2735-NMDC-T-03423 |  |  |  | 2025-11-06 | 2734-2735-NMDC-MWS-T-0046
|  |  | B | 3 |  | 2025-11-11 | CSE-2734-2735-PMT-T-089 | 2025-11-12 | 2734-2735-NMDC-T-03455 |  |  |  | 2025-11-12 | 2734-2735-NMDC-MWS-T-0048
26 | LOADING ARRANGEMENT OF CC PIPES ON GAC-82 CB (TRIP-14) [TRENCH #01 WITH DLB-750] | 2734-2735-NN-0026 | A | 3 |  | 2025-12-03 | CSE-2734-2735-PMT-T-098 | 2025-12-04 | 2734-2735-NMDC-T-03590 |  |  |  | 2025-12-04 | 2734-2735-NMDC-MWS-T-0057
27 | LOADING ARRANGEMENT OF CC PIPES ON GOGAS-252 CB (TRIP-15) [TRENCH #01 WITH DLB-750] | 2734-2735-NN-0027 | A | 3 |  | 2025-12-04 | CSE-2734-2735-PMT-T-099 | 2025-12-05 | 2734-2735-NMDC-T-03592 |  |  |  | 2025-12-05 | 2734-2735-NMDC-MWS-T-0058
28 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES ON MICLYN-258 CB (TRIP-16) | 2734-2735-NN-0028 | A | 3 |  | 2025-12-10 | CSE-2734-2735-PMT-T-100 | 2025-12-11 | 2734-2735-NMDC-T-03615 |  |  |  | 2025-12-10 | 2734-2735-NMDC-MWS-T-0059
29 | LOADING ARRANGEMENT OF CC PIPES ON AESEN-2803 CB (TRIP-17) [TRENCH #01 WITH DLB-750] | 2734-2735-NN-0029 | A | 3 |  | 2025-12-11 | CSE-2734-2735-PMT-T-101 | 2025-12-11 | 2734-2735-NMDC-T-03624 |  |  |  | 2025-12-11 | 2734-2735-NMDC-MWS-T-0060
30 | LOADING ARRANGEMENT OF CC PIPES ON GAC-82 CB (TRIP-18) [TRENCH #01 WITH DLB-750] | 2734-2735-NN-0030 | A | 3 |  | 2025-12-11 | CSE-2734-2735-PMT-T-101 | 2025-12-11 | 2734-2735-NMDC-T-03625 |  |  |  | 2025-12-11 | 2734-2735-NMDC-MWS-T-0060
|  |  | B | 3 |  | 2025-12-17 | CSE-2734-2735-PMT-T-102 | 2025-12-18 | 2734-2735-NMDC-T-03650 |  |  |  | 2025-12-18 | 2734-2735-NMDC-MWS-T-0061
31 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-19 WITH BALAST PLAN | 2734-2735-NN-0031
32 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-20 WITH BALAST PLAN | 2734-2735-NN-0032
33 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-21 WITH BALAST PLAN | 2734-2735-NN-0033
34 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-22 WITH BALAST PLAN | 2734-2735-NN-0034
35 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-23 WITH BALAST PLAN | 2734-2735-NN-0035
36 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-24 WITH BALAST PLAN | 2734-2735-NN-0036
37 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-25 WITH BALAST PLAN | 2734-2735-NN-0037
38 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-26 WITH BALAST PLAN | 2734-2735-NN-0038
39 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-27 WITH BALAST PLAN | 2734-2735-NN-0039
40 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-28 WITH BALAST PLAN | 2734-2735-NN-0040
41 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-29 WITH BALAST PLAN | 2734-2735-NN-0041
42 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-30 WITH BALAST PLAN | 2734-2735-NN-0042
43 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-31 WITH BALAST PLAN | 2734-2735-NN-0043
44 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-32 WITH BALAST PLAN | 2734-2735-NN-0044
45 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-33 WITH BALAST PLAN | 2734-2735-NN-0045
46 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-34 WITH BALAST PLAN | 2734-2735-NN-0046
47 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-35 WITH BALAST PLAN | 2734-2735-NN-0047
48 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-36 WITH BALAST PLAN | 2734-2735-NN-0048
49 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ GAC-82 (TRIP-1) | 2734-2735-NN-0049 | A | 2 |  | 2024-09-26 | CSE-2734-2735-PMT-T-004 | 2024-09-27 | 2734-2735-NMDC-T-01086 | 2024-11-11 | OP-CPD-ROZF-T-1697-24 | infor.
|  |  | B | 2 |  | 2024-12-26 | CSE-2734-2735-PMT-T-009 | 2024-12-31 | 2734-2735-NMDC-T-01617
|  |  | C | 2 |  | 2025-03-19 | CSE-2734-2735-PMT-T-030 | 2025-03-21 | 2734-2735-NMDC-T-02071 |  |  |  | 2025-03-21 | 2734-2735-NMDC-MWS-T-0011
|  |  | 00 | 3 |  | 2025-04-04 | CSE-2734-2735-PMT-T-037 | 2025-04-07 | 2734-2735-NMDC-T-02167 |  |  |  | 2025-04-10 | 2734-2735-NMDC-MWS-T-0016
50 | LOADING ARRANGEMENT AND SEAFASTENING OF CONCRETE SLEEPERS (TRIP-2) | 2734-2735-NN-0050
51 | LOADING ARRANGEMENT AND SEAFASTENING OF CONCRETE SLEEPERS (TRIP-3) | 2734-2735-NN-0051
52 | LAYDOWN HEAD FOR 48" PIPELINE (SECTION 1) AT MIDLINE SPOOL | 2734-2735-NN-0052 | A | 3 |  | 2024-10-17 | CSE-2734-2735-PMT-T-006 | 2025-02-05 | 2734-2735-NMDC-T-01821
|  |  | B | 3 |  | 2025-01-25 | CSE-2734-2735-PMT-T-016 | 2025-01-25 | 2734-2735-NMDC-T-01752
|  |  | C | 3 |  | 2025-04-17 | CSE-2734-2735-PMT-T-040 | 2025-05-30 | 2734-2735-NMDC-T-02517
53 | LAYDOWN HEAD FOR 48" PIPELINE AT DUMMY SPOOL | 2734-2735-NN-0053 | A | 3 |  | 2024-10-17 | CSE-2734-2735-PMT-T-006 | 2025-02-05 | 2734-2735-NMDC-T-01823
|  |  | B | 3 |  | 2025-01-29 | CSE-2734-2735-PMT-T-019 | 2025-02-05 | 2734-2735-NMDC-T-01824
|  |  | C | 3 |  | 2025-04-17 | CSE-2734-2735-PMT-T-040 | 2025-05-30 | 2734-2735-NMDC-T-02518
54 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CRAWLER CRANE & MISC. ITEMS ONBOARD CARGO BARGE ASTRO-3302 | 2734-2735-NN-0054 | A | 3 | NAR | 2025-04-25 | CSE-2734-2735-PMT-T-042 | 2025-07-15 | 2734-2735-NMDC-T-02787
55 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-259 (TRIP-2) (WITH DLB-750) | 2734-2735-NN-0055 | A | 2 |  | 2025-03-04 | CSE-2734-2735-PMT-T-026 | 2025-03-04 | 2734-2735-NMDC-T-01975 |  |  |  | 2025-03-05 | 2734-2735-NMDC-MWS-T-0008
|  |  | B | 3 |  | 2025-06-04 | CSE-2734-2735-PMT-T-054 | 2025-07-03 | 2734-2735-NMDC-T-02728 |  |  |  | 2025-07-03 | 2734-2735-NMDC-MWS-T-0022
56 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES AT MICLYN-259 (TRIP-3) (with DLB-750) | 2734-2735-NN-0056 | A | 2 |  | 2025-03-19 | CSE-2734-2735-PMT-T-029 | 2025-04-01 | 2734-2735-NMDC-T-02145 |  |  |  | 2025-04-02 | 2734-2735-NMDC-MWS-T-0014
|  |  | B | 2 |  | 2025-06-09 | CSE-2734-2735-PMT-T-055 | 2025-06-11 | 2734-2735-NMDC-T-02566
|  |  | 00 | 3 |  | 2025-06-23 | CSE-2734-2735-PMT-T-057 | 2025-07-15 | 2734-2735-NMDC-T-02793 |  |  |  | 15-76-2025 | 2734-2735-NMDC-MWS-T-0024
|  |  | 00A | 3 |  | 2025-08-05 | CSE-2734-2735-PMT-T-068
57 | TYPICAL LIFTING OF CONCRETE SLEEPERS BY SHUJAA 2000 | 2734-2735-NN-0057
58 | Sleeper loadout and seafastening details on CB-8 (with Delma-2000) | 2734-2735-NN-0058
59 | 48’’ PIPELINE ILI RECEIVER | 2734-2735-NN-0059 | A | 3 |  | 2025-04-17 | CSE-2734-2735-PMT-T-040 | 2025-05-30 | 2734-2735-NMDC-T-02519
60 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF F8" CC PIPES AT GAC-82 (TRIP-3 (WITH DELMA-2000) | 2734-2735-NN-0060 | A | 2 |  | 2025-04-15 | CSE-2734-2735-PMT-T-038 | 2025-04-16 | 2734-2735-NMDC-T-02234 |  |  |  | 2025-04-24 | 2734-2735-NMDC-MWS-T-0017 | 2025-04-28 | email | comments | Ajaykumar's email dtd. 28/04
|  |  | 00 | 3 | IFC | 2025-05-01 | CSE-2734-2735-PMT-T-044 | 2025-07-15 | 2734-2735-NMDC-T-02790
|  |  | 00A | 3 |  | 2025-05-30 | CSE-2734-2735-PMT-T-050
61 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-288 (TRIP-4) (WITH DELMA-2000) | 2734-2735-NN-0061 | A | 3 |  | 2025-04-29 | CSE-2734-2735-PMT-T-043 | 2025-04-30 | 2734-2735-NMDC-T-02310 |  |  |  | 2025-05-02 | 2734-2735-NMDC-MWS-T-0018
|  |  | B | 3 |  | 2025-05-14 | CSE-2734-2735-PMT-T-046 | 2025-05-14 | 2734-2735-NMDC-T-02403
|  |  | C | 3 |  | 2025-05-22 | CSE-2734-2735-PMT-T-049 | 2025-07-15 | 2734-2735-NMDC-T-02791
|  |  | 00 | 3 |  | 2025-07-04 | CSE-2734-2735-PMT-T-059
62 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ CASPIAN-280 (TRIP-5) [WITH DELMA-2000] | 2734-2735-NN-0062 | B | 3 | MF | 2025-05-18 | CSE-2734-2735-PMT-T-047 | 2025-05-21 | 2734-2735-NMDC-T-02447 |  |  |  | 2025-05-19 | E-MAIL
63 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-259(TRIP-4) [WITH DELMA-2000] | 2734-2735-NN-0063 |  |  | MF
64 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE PIPES @ CASPIAN-280 (TRIP-5) [WITH DELMA-2000] | 2734-2735-NN-0064 |  |  | MF
65 | EMERGENCY LAYDOWN HEAD FOR 48" PIPELINE (OPTION-2) | 2734-2735-NN-0065 | A | 3 |  | 2025-05-27 | CSE-2734-2735-PMT-T-052 | 2025-07-15 | 2734-2735-NMDC-T-02792
66 | TYPICAL RIGGING RECOVERY ARRANGEMENT FOR CONCRETE SLEEPERS BY DELMA-2000 | 2734-2735-NN-0066 | A | 3 |  | 2025-10-08 | CSE-2734-2735-PMT-T-074 | 2025-10-08 | 2734-2735-NMDC-T-03258 |  |  |  | 2025-10-08 | 2734-2735-NMDC-MWS-T-0033
67 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ AESEN-2803 (TRIP-2) | 2734-2735-NN-0067 | A | 3 |  | 2025-10-13 | CSE-2734-2735-PMT-T-075 | 2025-10-17 | 2734-2735-NMDC-T-03318 |  |  |  | 2025-10-17 | 2734-2735-NMDC-MWS-T-0035
68 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE PIPES @ GOGAS-252 (TRIP-6) (TRENCH# 1 WITH DLB-750] | 2734-2735-NN-0068 | A | 3 |  | 2025-11-01 | CSE-2734-2735-PMT-T-084 | 2025-11-04 | 2734-2735-NMDC-T-03420 |  |  |  | 2025-11-04 | 2734-2735-NMDC-MWS-T-0045 |  |  |  | 24-10-2025 reissued on 01/11
69 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE PIPES @ MICLYN-258 (TRIP-7) (TRENCH # 01 WITH DLB-750) | 2734-2735-NN-0069 | A | 3 |  | 2025-11-11 | CSE-2734-2735-PMT-T-088 | 2025-11-11 | 2734-2735-NMDC-T-03450 |  |  |  | 2025-11-11 | 2734-2735-NMDC-MWS-T-0047
70 | OPTION OF LOADING 27 NOS. RECOVERED SLEEPERS ON CASPIAN-280 | 2734-2735-NN-0070 | A | 3 |  | 2025-10-16 | CSE-2734-2735-PMT-T-078 | 2025-10-17 | 2734-2735-NMDC-T-03327 |  |  |  | 2025-10-17 | 2734-2735-NMDC-MWS-T-0037
71 | LOADING ARRANGEMENT FOR MESC. ITEMS @ GOGAS-255 | 2734-2735-NN-0071 | A | 3 |  | 2025-10-29 | CSE-2734-2735-PMT-T-085 | [5 empty] | 2025-10-31 | 2734-2735-NMDC-MWS-T-0043
72 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE PIPES @ GOGAS-250 (TRIP-8) [TRENCH # 01 WITH DLB-750] | 2734-2735-NN-0072 | A | 3 |  | 2025-11-12 | CSE-2734-2735-PMT-T-090 | 2025-11-12 | 2734-2735-NMDC-T-03459 |  |  |  | 2025-11-12 | 2734-2735-NMDC-MWS-T-0049
73 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES ON GAC-82 CB (TRIP-9) [TRENCH #01 WITH DLB-750] | 2734-2735-NN-0073 | A | 3 |  | 2025-11-17 | CSE-2734-2735-PMT-T-091 | 2025-11-18 | 2734-2735-NMDC-T-03481 |  |  |  | 2025-11-18 | 2734-2735-NMDC-MWS-T-0050
|  |  | B | 3 |  | 2025-11-21 | CSE-2734-2735-PMT-T-092 | 2025-11-21 | 2734-2735-NMDC-T-03510 |  |  |  | 2025-11-21 | 2734-2735-NMDC-MWS-T-0051
74 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES ON GOGAS-252 CB (TRIP-10) [TRENCH #01 WITH DLB-750] | 2734-2735-NN-0074 | A | 3 |  | 2025-11-25 | CSE-2734-2735-PMT-T-093 | 2025-11-25 | 2734-2735-NMDC-T-03540 |  |  |  | 2025-11-25 | 2734-2735-NMDC-MWS-T-0052
|  |  | B | 3 |  | 2025-11-28 | CSE-2734-2735-PMT-T-096 | 2025-11-28 | 2734-2735-NMDC-T-03560 |  |  |  | 2025-11-28 | 2734-2735-NMDC-MWS-T-0055
75 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES MICLYN-258 CB (TRIP-11) | 2734-2735-NN-0075 | A | 3 |  | 2025-11-27 | CSE-2734-2735-PMT-T-094 | 2025-11-27 | 2734-2735-NMDC-T-03546 |  |  |  | 2025-11-27 | 2734-2735-NMDC-MWS-T-0053
76 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON AESEN-2803 CB (TRIP-12) | 2734-2735-NN-0076 | A | 3 |  | 2025-11-27 | CSE-2734-2735-PMT-T-095 | 2025-11-28 | 2734-2735-NMDC-T-03556 |  |  |  | 2025-11-28 | 2734-2735-NMDC-MWS-T-0054
77 | LOADING ARRANGEMENT OF CC PIPES ON GOGAS-250 CB (TRIP-13) [TRENCH #01 WITH DLB-750] | 2734-2735-NN-0077 | A | 3 |  | 2025-11-28 | CSE-2734-2735-PMT-T-097 | 2025-12-03 | 2734-2735-NMDC-T-03563 |  |  |  | 2025-12-03 | 2734-2735-NMDC-MWS-T-0056
78 | 48" SPOOL LIFTING AND INSTALLATION ARRANGEMENT FROM OIL TRUNKLINE ZULF GOSP-2 TO ONSHORE PLATFORM SPOOL | 2734-2735-NN-0078 | A | 3 |  | 2026-04-28 | CSE-2734-2735-PMT-T-111 | [10 empty] | REVISED ON 28/04
|  |  | B | 3 |  | 2026-06-30 | CSE-2734-2735-PMT-T-112
|  |  | C | 3 |  | 2026-08-10 | CSE-2734-2735-PMT-T-113
79 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF STINGER-9A & MISCELLANEOUS ITEMS @ GAC-82 | 2734-2735-NN-0079 | A | 3 |  | 2026-02-05 | CSE-2734-2735-PMT-T-103
80 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SPOOL @ MICLYN-258 | 2734-2735-NN-0080 | A | 3 |  | 2026-04-01 | CSE-2734-2735-PMT-T-107 | 2026-04-06 | 2734-2735-NMDC-T-04144 | [8 empty] | reissued on 01/04
|  |  | B | 3 |  | 2026-04-09 | CSE-2734-2735-PMT-T-109 | 2026-04-10 | 2734-2735-NMDC-T-04201 |  |  |  | 2026-04-10 | 2734-2735-NMDC-MWS-T-0063
|  |  | C | 3 |  | 2026-04-20 | CSE-2734-2735-PMT-T-110
81 | LIFTING AND INSTALLATION OF CONCRETE SLEEPER (S2400) USING WADAD ALETHIEA | 2734-2735-NN-0081 | A | SRV |  | 2026-04-02 | CSE-2734-2735-PMT-T-108
82 | 48" SPOOL LIFTING AND INSTALLATION ARRANGEMENT FROM OIL TRUNKLINE ZULF GOSP-2 TO ONSHRE PLATFORM SPOOL BY USING ORIENTAL DRAGON | 2734-2735-NN-0082 |  | AMK
83 | 48" SPOOL LIFTING AND INSTALLATION ARRANGEMENT FROM OIL TRUNKLINE ZULF GOSP-2 TO ONSHRE PLATFORM SPOOL BY USING SHUJAA 200 | 2734-2735-NN-0083 |  | Binoy
84 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF RISERS, SPOOLS & MISC. ITEMS @ MICLYN-258 | 2734-2735-NN-0084 |  | Irfan

## SKETCHES
Project 2734
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2734 | OFO-P2734-SK-T-001 | PIPELAY PROFILE | 2 | A | √ | √ | 2024-07-10 | HZD | @
2 | 2734 | OFO-P2734-SK-T-002 | CONCRETE SLEEPER LIFTING & INSTALLATION BY DELMA-2000 | 1 | A | √ | √ | 2024-03-09 | CDG | @
3 | 2734 | OFO-P2734-SK-T-003 | DMA START-UP ARRANGEMENT FOR 48" PIPELINE
4 | 2734 | OFO-P2734-SK-T-004 | SHORE PULL ARRANGEMENT FOR 48" PIPELINE
5 | 2734 | OFO-P2734-SK-T-005 | TYPICAL AIR BAG ARRANGEMENTS FOR PIPELINE
6 | 2734 | OFO-P2734-SK-T-006 | TYPICAL ARRANGEMENT OF FLOATS ON PIPELINE
7 | 2734 | OFO-P2734-SK-T-007 | 42" ANCHOR PIPE
8 | 2734 | OFO-P2734-SK-T-008 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DLB-750 / MANITOWOC CRANE
9 | 2734 | OFO-P2734-SK-T-009 | 48" FLANGE - BOLT LENGTH | 4 | D | √ | √ | 2025-11-26 | SKS | @
10 | 2734 | OFO-P2734-SK-T-010 | STINGER 9A LIFTING AND INSTALLATION BY DLB-750 | 1 | B | √ | √ | 2024-09-30 | REY | @
11 | 2734 | OFO-P2734-SK-T-011 | SHOREPULL ARRANGEMENT AT SFNY ONSHORE | 1 | C | √ | √ | 2025-04-30 | CDG | @
12 | 2734 | OFO-P2734-SK-T-012 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DELMA-2000 |  |  |  |  | 2024-04-09 | NAR |  | HOLD
13 | 2734 | OFO-P2734-SK-T-013 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DLB-750 |  |  |  |  | 2024-04-09 | NAR |  | HOLD
14 | 2734 | OFO-P2734-SK-T-014 | TYPICAL PIPELINE PROTECTOR | 1 | A | √ | √ | 2025-04-16 | NAR | @
15 | 2734 | OFO-P2734-SK-T-015 | FLANGE ADAPTOR FOR AEGION COATING | 1 | B | √ | √ | 2025-01-30 | SKT | @
16 | 2734 | OFO-P2734-SK-T-016 | DLB-750 PIPELAY PROFILE | 1 | B | √ | √ | 2025-07-18 | MF | @
17 | 2734 | OFO-P2734-SK-T-017 | DLB-750 DECK LAYOUT AND PIPE STACKING ARRANGEMENT | 1 | A | √ | √ | 2024-10-30 | JH | @
18 | 2734 | OFO-P2734-SK-T-018 | STINGER-9 SECTION-A 80" BUOYANCY TANK | 1 | A | √ | √ | 2024-10-30 | CDG | @
19 | 2734 | OFO-P2734-SK-T-019 | DELMA-200 PIPELAY PROFILE FOR 48” PIPELINE | 1 | C | √ | √ | 2025-07-15 | ENH | @
20 | 2734 | OFO-P2734-SK-T-020 | DELAMA-2000 START-UP ARRANGEMENT FOR 48” TL AT GOSP-2 | 1 | C | √ | √ | 2025-05-29 | ENH | @
21 | 2734 | OFO-P2734-SK-T-021 | DELAMA-2000 START-UP ARRANGEMENT FOR 48” TL AT MIDLINE KP 35.5 | 1 | C | √ | √ | 2025-04-13 | ENH | @
22 | 2734 | OFO-P2734-SK-T-022 | 42" ANCHOR PIPE | 1 | A | √ | √ | 2024-12-11 | AKS | @
23 | 2734 | OFO-P2734-SK-T-023 | 48" FLANGE LUGS CLASH CHECK WITH BOLT TENSION JACK (AJ7) | 1 | C | √ | √ | 2025-08-26 | HZD | @
24 | 2734 | OFO-P2734-SK-T-024 | DLB-750 DECK LAYOUT FOR MISC. PROJECT MATERIAL & EQUIPMENT | 1 | E | √ | √ | 2025-07-15 | JF | @ | T-20 - 16-07-2025
25 | 2734 | OFO-P2734-SK-T-025 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR 48" PIPE JOINTS BY DELMA-2000 | 5 | B | √ | √ | 2025-04-02 | NAR | @
26 | 2734 | OFO-P2734-SK-T-026 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR 48" PIPE JOINTS BY DLB-750 | 5 | F | √ | √ | 2025-07-02 | MF | @
27 | 2734 | OFO-P2734-SK-T-027 | TYPICAL ONSHORE LIFTING CONCRETE SLEEPERS ARRANGEMENT | 2 | A | √ | √ | 2025-01-02 | CDG | @
28 | 2734 | OFO-P2734-SK-T-028 | 48" FLANGE LUGS CLASH CHECK WITH BOLT TENSION JACK (G4) | 1 | C | √ | √ | 2025-08-26 | HZD | @
29 | 2734 | OFO-P2734-SK-T-029 | USPS FRAME FOR 13.5M CONCRETE SLEEPER | 1 | B | √ | √ | 2025-01-28 | ENH | @
30 | 2734 | OFO-P2734-SK-T-030 | USPS FRAME FOR 14M CONCRETE SLEEPER | 1 | B | √ | √ | 2025-01-28 | ENH | @
31 | 2734 | OFO-P2734-SK-T-031 | USPS FRAME FOR 14.5M CONCRETE SLEEPER | 1 | B | √ | √ | 2025-01-28 | ENH | @
32 | 2734 | OFO-P2734-SK-T-032 | USPS FRAME FOR 15.5M CONCRETE SLEEPER | 1 | B | √ | √ | 2025-01-13 | ENH | @
33 | 2734 | OFO-P2734-SK-T-033 | DETAILS OF CLOSURE PLATE FOR 48" SPOOL | 1 | A | √ | √ | 2025-02-03 | AKS | @
34 | 2734 | OFO-P2734-SK-T-034 | MULTICAT ROSTAM DECK LAYOUT FOR AIR DIVING EQUIPMENT | 1 | A | √ | √ | 2025-02-06 | MF | @
35 | 2734 | OFO-P2734-SK-T-035 | CABLE PULLING ARRANGEMENT FOR 33KV SUBSEA CABLE |  |  |  |  | 2025-03-04 | HZD
36 | 2734 | OFO-P2734-SK-T-036 | CABLE PULLING ARRANGEMENT FOR 33KV SUBSEA CABLE AT CLQ PLATFORM |  |  |  |  | 2025-03-04 | HZD
37 | 2734 | OFO-P2734-SK-T-037 | DEPLOYMENT SEQUENCE FOR TYPICAL STEVSHARK MOORING SYSTEM. | 3 | A | √ | √ | 2025-03-19 | SKS | @
38 | 2734 | OFO-P2734-SK-T-038 | RECOVERY SEQUENCE FOR TYPICAL STEVSHARK MOORING SYSTEM | 3 | A | √ | √ | 2025-03-19 | SKS | @
39 | 2734 | OFO-P2734-SK-T-039 | CONNECTOR FOR SHORE PULL HEAD | 1 | B | √ | √ | 2025-04-14 | SKT | @
40 | 2734 | OFO-P2734-SK-T-040 | BASE PLATE FOR SHEAVE BLOCK | 1 | A | √ | √ | 2025-04-24 | SKT | @
41 | 2734 | OFO-P2734-SK-T-041 | BUSH FOR SHORE PULL HEAD | 1 | A | √ | √ | 2025-05-02 | SKT | @
42 | 2734 | OFO-P2734-SK-T-042 | TYPICAL PIPELINE PROTECTOR AT 15M LONG | 1 | A | √ | √ | 2025-05-09 | NAR | @
43 | 2734 | OFO-P2734-SK-T-043 | DETAILS OF TEMPORARY SUPPORT H-2500 | 1 + 9 | A, 0 | √ | √ | 2025-05-29 | NAR | @
44 | 2734 | OFO-P2734-SK-T-044 | DETAILS OF TEMPORARY SUPPORT H-1500 | 1 + 8 | A,0 | √ | √ | 2025-05-23 | NAR | @
45 | 2734 | OFO-P2734-SK-T-045 | 10 FT CONTAINER STACKING FRAME WITH ACCES PLATFPRM | 1 | B | √ | √ | 2025-06-03 | AMK | @
46 | 2734 | OFO-P2734-SK-T-046 | DELMA-2000 PIPELAY PROFILE FOR 48" DIA PIPELINE ADJUSTMENT | 1 | A | √ | √ | 2025-06-10 | HZD | @
47 | 2734 | OFO-P2734-SK-T-047 | STINGER TIPS SEPARATION OF DLB-750 | 1 | A | √ | √ | 2025-06-13 | HZD | @
48 | 2734 | OFO-P2734-SK-T-048 | RECOVERY OF 48"PIPELINE CWC 100mm WITH 60MT TENSION | 1 | A | √ | √ | 2025-06-16 | CDG | @
49 | 2734 | OFO-P2734-SK-T-049 | RECOVERY OF 48"PIPELINE CWC 100mm WITH 80MT TENSION | 7 | C | √ | √ | 2025-07-03 | HZD | @
50 | 2734 | OFO-P2734-SK-T-050 | RECOVERY OF 48"PIPELINE CWC 90/100mm WITH 60MT TENSION | 1 | A | √ | √ | 2025-06-18 | CDG | @
51 | 2734 | OFO-P2734-SK-T-051 | RIGGING CONNECTION BETWEEN SOFT ROPE AND PULLING WIRE |  |  |  |  | 2025-06-29 | SKS
52 | 2734 | OFO-P2734-SK-T-052 | RIGGING CONNECTION: SOFT ROPE TO SOFT ROPE |  |  |  |  | 2025-06-29 | SKS
53 | 2734 | OFO-P2734-SK-T-053 | RIGGING CONNECTION BETWEEN PULLING WIRE SECTIONS |  |  |  |  | 2025-06-30 | SKS
54 | 2734 | OFO-P2734-SK-T-054 | TYPICAL RIGGING ARRANGEMENT FOR LIFTEK FECB-5.0MT USING CARGO STRAP (ENDLESS STRAPS) | 2 | A | √ | √ | 2025-07-07 | MF | @
55 | 2734 | OFO-P2734-SK-T-055 | TYPICAL DLB-750 A&R RIGGING ARRANGEMENT | 1 | A | √ | √ | 2025-07-01 | JH | @
56 | 2734 | OFO-P2734-SK-T-056 | DELMA-2000 DECK LAYOUT MISC. PROJECT MATERIAL & EQUIPMENT | 1 | A | √ | √ | 2025-01-09 | NEH / JH | @
57 | 2734 | OFO-P2734-SK-T-057 | FLOATATION BUOY CONNECTION TO PULLING WIRE | 1 | A | √ | √ | 2025-07-02 | SKS | @
58 | 2734 | OFO-P2734-SK-T-058 | TYPICAL RIGGING ARRANGEMENT FOR LIFTEK FECB-2.5 MT USING CARGO STRAP (ENDLESS STRAPS) | 2 | A | √ | √ | 2025-07-07 | MF | @
59 | 2734 | OFO-P2734-SK-T-059 | TYPICAL RIGGING ARRANGEMENT FOR LIFTEK FECB-1.5 MT USING CARGO STRAP (ENDLESS STRAPS) | 2 | A | √ | √ | 2025-07-07 | MF | @
60 | 2734 | OFO-P2734-SK-T-060 | TYPICAL ARRANGEMENT OF FOAM FLOATS ON PIPELINE | 2 | A | √ | √ | 2025-07-07 | MF | @
61 | 2734 | OFO-P2734-SK-T-061 | INHOUSE FABRICATED RUNNING BLOCK | 1 | B | √ | √ | 2025-10-27 | AMEER | @
62 | 2734 | OFO-P2734-SK-T-062 | FLANGE CATCHER FOR 48" FLANGE | 1 | A | √ | √ | 2026-01-09 | SKS | @
63 | 2734 | OFO-P2734-SK-T-063 | CCC-M2 DECK LAYOUT DURING GROUTING AND FLOADING OPERATION | 1 | A | √ | √ | 2026-02-02 | MF | @ | SERVER ONLY
64 | 2734 | OFO-P2734-SK-T-064 | LIFTING & OFFLOADING ARRANGEMENT OF STINGER-9A AT DLB-750 | 1 | A | √ | √ | 2026-01-30 | NAR | @
65 | 2734 | OFO-P2734-SK-T-065 | 48" FLANGE - BOLT LENGTH | 1 | B | √ | √ | 2026-02-18 | SIVAKUMAR | @
66 | 2734 | OFO-P2734-SK-T-066 | 48”PIPELINE FOR ILI RECIEVER | 2 | A | √ | √ | 2026-03-16 | SC | @
67 | 2734 | OFO-P2734-SK-T-067 | CCCM2 for Pipeline Flooding and Grouting Installation | 1 | A | √ | √ | 2026-02-24 | LEO | @
68 | 2734 | OFO-P2734-SK-T-068 | ARRANGEMENT OF AIRBAGS ON SPOOLS DURING INSTALLATION | 1 | A | √ | √ | 2026-03-11 | SRV | @
69 | 2734 | OFO-P2734-SK-T-069 | DRIFT PIN FOR 48" FLANGE | 1 | A | √ | √ | 2026-04-04 | SK | @
70 | 2734 | OFO-P2734-SK-T-070 | 48" RISER FLANGE CONNECTION | 1 | A | √ | √ | 2026-04-08 | SK
71 | 2734 | OFO-P2734-SK-T-071 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF TIE-IN SPOOLS ON ORIENTAL DRAGON | 1 | A | √ | √ | 2026-05-04 | JF | @
72 | 2734 | OFO-P2734-SK-T-072 | Lifting arrangement for the 48" Blind Flange | 1 | A | √ | √ | 2026-05-15 | MF | @
73 | 2734 | OFO-P2734-SK-T-073 | DECK LAYOUT WITH TIE IN SPOOLS ONBOARD WADAD ALETHEIA | 1 | A | √ | √ | 2026-06-23 | JF | @
74 | 2734 | OFO-P2734-SK-T-074 | RISER CLAMPS INSTALLATION TORQUE TOOL CLEARANCE CHECK | 2 | A | √ | √ | 2026-07-01 | SKS | @
75 | 2734 | OFO-P2734-SK-T-075 | RISER CLAMP & RISER HANGER CLAMP LIFTING AND INSTALLATION | 1 | A | √ | √ | 2026-08-12 | AA | @
76 | 2734 | OFO-P2734-SK-T-076 | RISER CLAMP & RISER HANGER CLAMP LIFTING AND INSTALLATION | 1 | A | √ | √ | 2026-08-12 | AA | @
77 | 2734 | OFO-P2734-SK-T-077 | FLANGE CATCHER FOR 48’’ SWIVEL FLANGE |  |  |  |  | 2026-08-22 | NAR
78 | 2734 | OFO-P2734-SK-T-078 | DRIFT PIN FOR 48’’ SWIVEL FLANGE |  |  |  |  | 2026-08-22 | NAR

## Cutlists
Project 2734-2735
CUT-LIST DRAWINGS
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2734 | 2734-2735--NN-0001-CTL | SHORE PULL FOR 48” PIPELINE (WITH CUTLIST 1 + 18) | 1 + 18 | 1 | √ | √ | 2025-01-30 | CSE-OF-2734-35-001 | @ | SKT / AN
2 | 2734 | 2734-2735--NN-0002-CTL | START UP HEAD FOR 48" PIPELINE AT GOSP-2 (WITH CUTLIST 1 + 19) | 1 + 19 | 0 | √ | √ | 2024-11-04 | CSE-OF-2734-35-001 | @ | SKT / AN
3 | 2734 | 2734-2735--NN-0003-CTL | LAYDOWN HEAD FOR 48" PIPELINE (SECTION 3) AT DUMMY SPOOL (WITH CUTLIST 1 + 22) | 1 + 22 | 0 | √ | √ | 2025-01-29 | CSE-OF-2734-35-001 | @ | SKs / AN
4 | 2734 | 2734-2735--NN-0004-CTL | EMERGENCY LAYDOWN HEAD FOR 48” PIPELINE (WITH CUTLIST 1 + 22) | 1 + 22 | 0 | √ | √ | 2025-01-25 | CSE-OF-2734-35-004 | @ | SKS / AN
5 | 2734 | 2734-2735--NN-0005-CTL | START UP HEAD FOR 48" PIPELINE AT MIDLINE SPOOL (WITH CUTLIST 1 + 20) | 1 + 20 | 0 | √ | √ | 2024-11-04 | CSE-OF-2734-35-001 | @ | SKT / AN
6 | 2734 | 2734-2735--NN-0006-CTL | FLANGE PROTECTOR DETAILS FOR 48" PIPELINE HEADS 100mm THK CONCRETE (WITH CUTLIST 1 + 8) | 1 + 8 | 0 | √ | √ | 2024-11-04 | CSE-OF-2734-35-002 | @ | NAR AN
|  |  |  | 1 + 8 | 0 | √ | √ | 2024-01-16 | CSE-OF-2734-35-003 | @ | SKT AN
7 | 2734 | 2734-2735--NN-0007-CTL | FLANGE PROTECTOR DETAILS FOR 48" PIPELINE HEADS 75mm THK CONCRETE (WITH CUTLIST 1 + 8) | 1 + 8 | 0 | √ | √ | 2024-11-04 | CSE-OF-2734-35-002 | @ | NAR AN
|  |  |  | 1 + 8 | 0 | √ | √ | 2024-01-16 | CSE-OF-2734-35-003 | @ | SKT AN
| 2734 | OFO-P2734-SK-T-022-CTL | 42’’ Anchor Pipe – Cut List | 1 + 8 | 0 | √ | √ | 2025-02-12 | CSE-OF-2734-35-005 | @ | SKT AN
8 | 2734 | 2734-2735--NN-0052-CTL | LAYDOWN HEAD FOR 48" PIPELINE (SECTION 2) AT DUMMY SPOOL (WITH CUTLIST 1 + 22) | 1 + 22 | 0 | √ | √ | 2025-01-25 | CSE-OF-2734-35-004 | @ | SKs / AN
9 | 2734 | 2734-2735--NN-0053-CTL | LAYDOWN HEAD FOR 48" PIPELINE AT DUMMY SPOOL (WITH CUTLIST 1 + 26) | 1 + 26 | 0 | √ | √ | 2025-01-29 | CSE-OF-2734-35-001 | @ | SKs / AN
|  |  |  | 1 + 26 | 1 | √ | √ | 2025-04-15 | CSE-OF-2734-35-006 | @ | NAR/AN
10 | 2734 | OFO-P2734-SK-T-043-CTL | DETAILS OF TEMPORARY SUPPORT H-2500 | 1 + 9 | 0 | √ | √ | 2025-05-30 | CSE-OF-2734-35-007 | @ | NAR/PKR
11 | 2734 | OFO-P2734-SK-T-044-CTL | DETAILS OF TEMPORARY SUPPORT H-1500 | 1 + 8 | 0 | √ | √ | 2025-05-30 | CSE-OF-2734-35-007 | @ | NAR/PKR
12 | 2734
13 | 2734
14 | 2734
15 | 2734
16 | 2734
17 | 2734
18 | 2734
19 | 2734
20 | 2734
21 | 2734
22 | 2734