## Documents - Pipeline & Cable
|  | ADNOC OFFSHORE | [11 empty] | NMDC ENERGY DOC. No.:
ADNOC LZ LTDP-1 EPS-2 PDP PROJECT
|  | NMDC ENERGY PROJECT NO. 2745 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | LOWER ZAKUM – LTDP-1 PIPE STACKING ANALYSIS REPORT FOR ZWSC (PDP-GPF-II) ZCSC (PDP) | 2745-NN-RP-001 | AD-27-G-01692 | 1 | 2 |  | 21-10-2025 | CSE-2745-PMT-T-013 | 21-10-2025 | 2745-NMDC-E-AO-T-00635 | [8 empty] | reissued on 21/10
2 | LOWER ZAKUM – LTDP-1 PIPELAY ANALYSIS REPORT FOR OPL-2 16in WF FROM WHT-3 TO WHT-2 | 2745-NN-RP-006 | AD-27-G-01693
3 | LOWER ZAKUM – LTDP-1 PIPELAY ANALYSIS REPORT FOR OPL-3 20in WF FROM WHT-2 TO ZWSC (RP-1) | 2745-NN-RP-004 | AD-27-G-01694
4 | LOWER ZAKUM – LTDP-1 PIPELAY ANALYSIS REPORT FOR OPL-4 24in WF FROM ZCSC (CRP) TO ZWSC (RP-1) | 2745-NN-RP-005 | AD-27-G-01695
5 | LOWER ZAKUM – LTDP-1 PIPELAY ANALYSIS REPORT FOR WPL-2 16in WI FROM WHT-2 TO WHT-3 | 2745-NN-RP-002 | AD-27-G-01696
6 | LOWER ZAKUM – LTDP-1 PIPELAY ANALYSIS REPORT FOR WPL-3 18in WI FROM ZWSC (RP-1)TO WHT-2 | 2745-NN-RP-003 | AD-27-G-01697
7 | LOWER ZAKUM – LTDP-1 INSTALLATION ANALYSIS REPORT FOR 132KV CABLES AT AGI, ZWSC(PDP), ZWSC (GPF-ll) & ZCSC(PDP) | 2745-NN-RP-007 | AD-27-G-01698
8 | LOWER ZAKUM – LTDP-1 INSTALLATION ANALYSIS REPORT FOR 6.6KV CABLES | 2745-NN-RP-008 | AD-27-G-01699 | 1 | 2 |  | 12-11-2-25 | CSE-2745-PMT-T-019
9 | LOWER ZAKUM – LTDP-1 SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-1) | 2745-NN-RP-031
10 | LOWER ZAKUM – LTDP-1 SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-2) | 2745-NN-RP-032
11 | LOWER ZAKUM – LTDP-1 SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-3) | 2745-NN-RP-011
12 | LOWER ZAKUM – LTDP-1 SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-4) | 2745-NN-RP-012
13 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AT PRESTIGE-281 (TRIP-1) | 2745-NN-RP-016 | AD-27-G-01700 | 1 | 2 |  | 2025-10-14 | CSE-2745-PMT-T-007 | 2025-10-15 | 2745-NMDC-E-AO-T-00621 | 2025-10-24 | 11688-NMDC-TR-03200 | 4 | 2025-10-15 | 2745-NMDC-E-MWS-T-00005 | 2025-10-30 | SAF 220-MCE-NMDC-T-0001 | Accepted
14 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON PRESTIGE-282 (TRIP 2) | 2745-NN-RP-017 | AD-27-G-01701 | 1 | 2 |  | 2025-11-07 | CSE-2745-PMT-T-015 | 2025-11-09 | 2745-NMDC-E-AO-T-00718 |  |  |  | 2025-11-09 | 2745-NMDC-E-MWS-T-00013
15 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON PRESTIGE-281 (TRIP 3) | 2745-NN-RP-018 | AD-27-G-01087 | 1 | 2 | remarks | 2025-11-18 | CSE-2745-PMT-T-020 | 2025-11-19 | 2745-NMDC-E-AO-T-00758 |  |  |  | 2025-11-19 | 2745-NMDC-E-MWS-T-00016 |  |  |  | Client's # taken from NDMS
16 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 4 | 2745-NN-RP-019
17 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 5 | 2745-NN-RP-020
18 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 6 | 2745-NN-RP-021
19 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 7 | 2745-NN-RP-022
20 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 1 FOR WHT-2 & WHT-3 | 2745-NN-RP-007 | AD-27-G-01702
21 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 2 | 2745-NN-RP-008
22 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 3 | 2745-NN-RP-009
23 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 4 | 2745-NN-RP-010
24 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 5 | 2745-NN-RP-011
25 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 6 | 2745-NN-RP-012
26 | LOWER ZAKUM – LTDP-1 SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 7 | 2745-NN-RP-013
27 | LOWER ZAKUM – LTDP-1 DAVIT LIFT ANALYSIS REPORT FOR OPL-2 16in WF FROM WHT-3 TO WHT-2 | 2745-NN-RP-027
28 | LOWER ZAKUM – LTDP-1 DAVIT LIFT ANALYSIS REPORT FOR OPL-3 20in WF FROM WHT-2 TO ZWSC (RP-1) | 2745-NN-RP-028
29 | LOWER ZAKUM – LTDP-1 DAVIT LIFT ANALYSIS REPORT FOR OPL-4 24in WF FROM ZCSC (CRP) TO ZWSC (RP-1) | 2745-NN-RP-029
30 | LOWER ZAKUM – LTDP-1 DAVIT LIFT ANALYSIS REPORT FOR WPL-2 16in WI FROM WHT-2 TO WHT-3 | 2745-NN-RP-030
31 | LOWER ZAKUM – LTDP-1 DAVIT LIFT ANALYSIS REPORT FOR WPL-3 18in WI FROM ZWSC (RP-1)TO WHT-2 | 2745-NN-RP-031

## Documents - Naval Marine
|  | ADNOC OFFSHORE | [11 empty] | NMDC ENERGY DOC. No.:
ADNOC LZ LTDP-1 EPS-2 PDP PROJECT
|  | NMDC ENERGY PROJECT NO. 2745 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-1 FOR WHT-2 & WHT-3 | 2745-ZZ-CL-001 | AD-27-G-01703 | 1
2 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-2 | 2745-ZZ-CL-002
3 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-3 | 2745-ZZ-CL-003
4 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-4 | 2745-ZZ-CL-004
5 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-5 | 2745-ZZ-CL-005
6 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-6 | 2745-ZZ-CL-006
7 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-7 | 2745-ZZ-CL-007
8 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-8 | 2745-ZZ-CL-008
9 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 16" WI - WHT2 | 2745-ZZ-CL-026 | AD-818-G-00107
10 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 16" OIL - WHT2 | 2745-ZZ-CL-027 | AD-818-G-00108
11 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 18" - WHT2 | 2745-ZZ-CL-028 | AD-818-G-00109
12 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 20" - WHT2 | 2745-ZZ-CL-029 | AD-818-G-00110
13 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 24" - ZCSC CSP | 2745-ZZ-CL-030 | AD-814-G-00132
14 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS, J-TUBES AND RISERS - TRIP-1 | 2745-ZZ-CL-014
15 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS, J-TUBES AND RISERS - TRIP-2 | 2745-ZZ-CL-015
16 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS, J-TUBES AND RISERS - TRIP-3 | 2745-ZZ-CL-016
17 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS, J-TUBES AND RISERS - TRIP-4 | 2745-ZZ-CL-017
18 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LAYING OF 16" WI - WHT2 WHT3 | 2745-ZZ-CL-021 | AD-27-G-01704
19 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LAYING OF 16" OIL - WHT2 WHT3 | 2745-ZZ-CL-022 | AD-27-G-01705
20 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES PRESTIGE-281 (TRIP-1) | 2745-ZZ-CL-011 | AD-27-G-01706 | 1 | 2 |  | 2025-10-03 | CSE-2745-PMT-T-007 | 2025-10-04 | 2745-NMDC-E-AO-T-00587 | 2025-10-22 | 11688-NMDC-TR-03177 | 4
21 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES - TRIP-2 | 2745-ZZ-CL-012 | AD-27-G-01707 | 1 | 2 |  | 2025-11-07 | CSE-2745-PMT-T-015 | 2025-11-09 | 2745-NMDC-E-AO-T-00719 |  |  |  | 2025-11-09 | 2745-NMDC-E-MWS-T-00013
22 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS @ PRESTIGE-281 - TRIP-3 | 2745-ZZ-CL-013 |  | 1 | 2 |  | 2025-11-18 | CSE-2745-PMT-T-020 | 2025-11-19 | 2745-NMDC-E-AO-T-00759 |  |  |  | 2025-11-19 | 2745-NMDC-E-MWS-T-00017
23 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES - TRIP-4 | 2745-ZZ-CL-014
24 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES - TRIP-5 | 2745-ZZ-CL-015
25 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES - TRIP-6 | 2745-ZZ-CL-016
26 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LAYING OF 18" | 2745-ZZ-CL-023 | AD-27-G-01708
27 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LAYING OF 20" | 2745-ZZ-CL-024 | AD-27-G-01709
28 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LAYING OF 24" | 2745-ZZ-CL-025 | AD-27-G-01710
29 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING ZCSC PDP JACKET INSTALLATION | 2745-ZZ-CL-035 | AD-27-G-01711
30 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST JACKET INSTALLATION -1 | 2745-ZZ-CL-030 | AD-27-G-01712
31 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST JACKET INSTALLATION -2 | 2745-ZZ-CL-031 | AD-27-G-01713
32 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING ZCSC BST INSTALLATION– ZWSC (PDP-GPF-II) ZCSC (PDP) | 2745-ZZ-CL-033 | AD-27-G-01715
33 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING ZWSC GPF-II BST INSTALLATION– ZWSC (PDP-GPF-II) ZCSC (PDP) | 2745-ZZ-CL-034 | AD-27-G-01716
34 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING FLARE BST-3 INSTALLATION FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-034 | AD-27-G-01717
35 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING FLARE BST-4 INSTALLATION FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-035 | AD-27-G-01718
36 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING FLARE BST-5 INSTALLATION FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-036 | AD-27-G-01719
37 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS OF B-42 DURING FLOATOVER OF ZWSC GPF-II | 2745-ZZ-CL-036 | AD-845-G-00138
38 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST DECK INSTALLATION -1 FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-038 | AD-27-G-01720
39 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST DECK INSTALLATION -2 FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-039 | AD-27-G-01721
40 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST DECK INSTALLATION -3 FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-040 | AD-27-G-01722
41 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST DECK INSTALLATION -4 FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-041 | AD-27-G-01723
42 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST DECK INSTALLATION -5 FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-042 | AD-27-G-01724
43 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST BRIDGE INSTALLATION -1 FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-043 | AD-27-G-01725
44 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST BRIDGE INSTALLATION -2 FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-044 | AD-27-G-01726
45 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST BRIDGE INSTALLATION -3 FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-045 | AD-27-G-01727
46 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST BRIDGE INSTALLATION -4 FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-046 | AD-27-G-01728
47 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST BRIDGE INSTALLATION -5 FOR ZWSC (PDP-GPF-II) | 2745-ZZ-CL-047 | AD-27-G-01729
48 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 16" WI - WHT3 | 2745-ZZ-CL-048 | AD-819-G-00002
49 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 16" OIL - WHT3 | 2745-ZZ-CL-049 | AD-819-G-00003
50 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 18" - ZWSC RP1 | 2745-ZZ-CL-050 | AD-27-G-01730
51 | LOWER ZAKUM – LTDP-1 - MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 20" - ZWSC RP1 | 2745-ZZ-CL-051 | AD-27-G-01731
52 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 24" - ZWSC RP1 | 2745-ZZ-CL-052 | AD-27-G-01732

## Drawings
|  | ADNOC OFFSHORE | [11 empty] | NMDC ENERGY DOC. No.:
ADNOC LZ LTDP-1 EPS-2 PDP PROJECT
|  | NMDC ENERGY PROJECT NO. 2745 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | LOWER ZAKUM – LTDP-1 START UP HEAD DETAILS FOR 16'' PIPELINES FOR WHT-2 & WHT-3 | 2745-NN-0001 | AD-27-PL-625231-SHT-001
2 | LOWER ZAKUM – LTDP-1 START UP HEAD DETAILS FOR 18" PIPELINES FOR WHT-2 & ZWSC(RP1) | 2745-NN-0002 | AD-27-PL-625232-SHT-001
3 | LOWER ZAKUM – LTDP-1 START UP HEAD DETAILS FOR 20" PIPELINES FOR WHT-2 & ZWSC(RP1) | 2745-NN-0003 | AD-27-PL-625233-SHT-001
4 | LOWER ZAKUM – LTDP-1 START UP HEAD DETAILS FOR 24" PIPELINES FOR ZCSC CRP & RP1 | 2745-NN-0004 | AD-27-PL-625234-SHT-001
5 | LOWER ZAKUM – LTDP-1 LAYDOWN HEAD DETAILS FOR 16" PIPELINES FOR WHT-2 & WHT-3 | 2745-NN-0005 | AD-27-PL-625235-SHT-001
6 | LOWER ZAKUM – LTDP-1 LAYDOWN HEAD DETAILS FOR 18" PIPELINES FOR ZWSC(RP1) & WHT-2 | 2745-NN-0006 | AD-27-PL-625236-SHT-001
7 | LOWER ZAKUM – LTDP-1 LAYDOWN HEAD DETAILS FOR 20" PIPELINES FOR WHT-2 & ZWSC(RP1) | 2745-NN-0007 | AD-27-PL-625237-SHT-001
8 | LOWER ZAKUM – LTDP-1 LAYDOWN HEAD DETAILS FOR 24" PIPELINES FOR ZCSC CRP & ZWSC(RP1) | 2745-NN-0008 | AD-27-PL-625238-SHT-001
9 | LOWER ZAKUM – LTDP-1 EMERGENCY LAYDOWN HEAD DETAILS FOR 16" PIPELINES FOR WHT-2 & WHT-3 | 2745-NN-0009 | AD-27-PL-625239-SHT-001
10 | LOWER ZAKUM – LTDP-1 EMERGENCY LAYDOWN HEAD DETAILS FOR 18" PIPELINES FOR ZWSC(RP1) & WHT-2 | 2745-NN-0010 | AD-27-PL-625240-SHT-001
11 | LOWER ZAKUM – LTDP-1 EMERGENCY LAYDOWN HEAD DETAILS FOR 20" PIPELINES FOR WHT-2 & ZWSC(RP1) | 2745-NN-0011 | AD-27-PL-625241-SHT-001
12 | LOWER ZAKUM – LTDP-1 EMERGENCY LAYDOWN HEAD DETAILS FOR 24" PIPELINES FOR ZCSC CRP & ZWSC(RP1) | 2745-NN-0012 | AD-27-PL-625242-SHT-001
13 | LOWER ZAKUM – LTDP-1 BUCKLE DETECTOR FOR 16" PIPELINES FOR WHT-2 & WHT-3 | 2745-NN-0009 | AD-27-PL-625243-SHT-001
14 | LOWER ZAKUM – LTDP-1 BUCKLE DETECTOR FOR 18" PIPELINES FOR ZWSC(RP1) & WHT-2 | 2745-NN-0010 | AD-27-PL-625244-SHT-001
15 | LOWER ZAKUM – LTDP-1 BUCKLE DETECTOR FOR 20" PIPELINES FOR WHT-2 & ZWSC(RP1) | 2745-NN-0011 | AD-27-PL-625245-SHT-001
16 | LOWER ZAKUM – LTDP-1 BUCKLE DETECTOR FOR 24" PIPELINES FOR ZCSC CRP & ZWSC(RP1) | 2745-NN-0012 | AD-27-PL-625246-SHT-001
17 | LOWER ZAKUM – LTDP-1 TEMPORARY PIG LAUNCHER/ RECEVIER FOR 16" PIPELINES WHT-2 & WHT-3 | 2745-NN-0044 | AD-27-PL-625247-SHT-001
18 | LOWER ZAKUM – LTDP-1 TEMPORARY PIG LAUNCHER/ RECEVIER FOR 18" PIPELINES FOR ZWSC(RP1) & WHT-2 | 2745-NN-0045 | AD-27-PL-625248-SHT-001
19 | LOWER ZAKUM – LTDP-1 TEMPORARY PIG LAUNCHER/ RECEVIER FOR 20" PIPELINES FOR WHT-2 & ZWSC(RP1) | 2745-NN-0046 | AD-27-PL-625249-SHT-001
20 | LOWER ZAKUM – LTDP-1 TEMPORARY PIG LAUNCHER/ RECEVIER FOR 24" PIPELINES FOR ZCSC CRP & ZWSC(RP1) | 2745-NN-0047 | AD-27-PL-625250-SHT-001
21 | LOWER ZAKUM – LTDP-1 LIFTING & INSTALLATION OF J-TUBE BY SAFEEN PEARL AT WHT-ZK-11 | 2745-NN-0021 | AD-27-PL-625251-SHT-001 | 1 | 2 |  | 2025-10-24 | CSE-2745-PMT-T-016 | 2025-10-25 | 2745-NMDC-E-AO-T-00643 |  |  |  | 2025-10-25 | 2745-NMDC-E-MWS-T-00006
22 | LOWER ZAKUM – LTDP-1 LIFTING & INSTALLATION OF J-TUBE BY SAFEEN PEARL AT WHT-ZK-235 | 2745-NN-0022 | AD-27-PL-625252-SHT-001 | 1 | 2 |  | 2025-10-24 | CSE-2745-PMT-T-016 | 2025-10-25 | 2745-NMDC-E-AO-T-00643 |  |  |  | 2025-10-25 | 2745-NMDC-E-MWS-T-00006
23 | LOWER ZAKUM – LTDP-1 LIFTING & INSTALLATION OF J-TUBE CLAMPS BY SAFEEN PEARL AT WHT-ZK-235 | 2745-NN-0023 | AD-27-PL-625253-SHT-001 | 1 | 2 |  | 2025-10-24 | CSE-2745-PMT-T-016 | 2025-10-25 | 2745-NMDC-E-AO-T-00643 |  |  |  | 2025-10-25 | 2745-NMDC-E-MWS-T-00006
24 | LOWER ZAKUM – LTDP-1 LIFTING & INSTALLATION OF J-TUBE CLAMPS BY SAFEEN PEARL AT WHT-ZK-11 | 2745-NN-0024 | AD-27-PL-625254-SHT-001 | 1 | 2 |  | 2025-10-24 | CSE-2745-PMT-T-016 | 2025-10-25 | 2745-NMDC-E-AO-T-00643 |  |  |  | 2025-10-25 | 2745-NMDC-E-MWS-T-00006
25 | LOWER ZAKUM – LTDP-1 LIFTING & INSTALLATION OF J-TUBE AT ZK-288 | 2745-NN-0025 | AD-27-PL-625255-SHT-001
26 | LOWER ZAKUM – LTDP-1 LIFTING & INSTALLATION OF J-TUBE CLAMPS AT ZK-288 | 2745-NN-0026 | AD-27-PL-625256-SHT-001
27 | LOWER ZAKUM – LTDP-1 LIFTING & INSTALLATION OF RISER CLAMPS AT WHT-2 | 2745-NN-0048 | AD-27-PL-625257-SHT-001
28 | LOWER ZAKUM – LIFTING & INSTALLATION OF RISER CLAMPS AT WHT-3 | 2745-NN-0028 | AD-27-PL-625258-SHT-001
29 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPER FOR ZWSC (PDP-GPF-II) ZCSC (PDP) | 2745-NN-0013 | AD-27-PL-625259-SHT-001
30 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING OF CONCRETE MATTRESS FOR ZWSC (PDP-GPF-II) ZCSC (PDP) | 2745-NN-0014 | AD-27-PL-625260-SHT-001
31 | LOWER ZAKUM – LTDP-1 STALK ON RISER INSTALLATION FOR 16" WI PL - WHT2 | 2745-NN-0031 | AD-27-PL-625261-SHT-001
32 | LOWER ZAKUM – LTDP-1 STALK ON RISER INSTALLATION FOR 16" WI PL - WHT3 | 2745-NN-0032 | AD-27-PL-625262-SHT-001
33 | LOWER ZAKUM – LTDP-1 STALK ON RISER INSTALLATION FOR 16" OIL PL - WHT2 | 2745-NN-0033 | AD-27-PL-625263-SHT-001
34 | LOWER ZAKUM – LTDP-1 STALK ON RISER INSTALLATION FOR 16" OIL PL - WHT 3 | 2745-NN-0034 | AD-27-PL-625264-SHT-001
35 | LOWER ZAKUM – LTDP-1 TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 16" | 2745-NN-0019 | AD-27-PL-625265-SHT-001
36 | LOWER ZAKUM – LTDP-1 TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 18" | 2745-NN-0020 | AD-27-PL-625266-SHT-001
37 | LOWER ZAKUM – LTDP-1 TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 20" | 2745-NN-0021 | AD-27-PL-625267-SHT-001
38 | LOWER ZAKUM – LTDP-1 TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 24" | 2745-NN-0022 | AD-27-PL-625268-SHT-001
39 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-1) FOR WHT-2 & WHT-3 | 2745-NN-0023 | AD-27-PL-625269-SHT-001
40 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-2) | 2745-NN-0024
41 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-3) | 2745-NN-0025
42 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-4) | 2745-NN-0026
43 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-5) | 2745-NN-0027
44 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-6) | 2745-NN-0028
45 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-7) | 2745-NN-0029
46 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-2) FOR WHT-2, WHT-3, ZWSC(RP1) | 2745-NN-0033 | AD-27-PL-625270-SHT-001
47 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON PRESTIGE-282 CB (TRIP-2) | 2745-NN-0034 |  | 1 |  | remarks | 2025-11-07 | CSE-2745-PMT-T-015 | 2025-11-09 | 2745-NMDC-E-AO-T-00717 |  |  |  | 2025-11-09 | 2745-NMDC-E-MWS-T-00012 |  |  |  | JH - title changed mattresses removed
48 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON PRESTIGE-281 CB (TRIP-3) | 2745-NN-0035 |  | 1 |  |  | 2025-11-18 | CSE-2745-PMT-T-020 | 2025-11-19 | 2745-NMDC-E-AO-T-00757 |  |  |  | 2025-11-19 | 2745-NMDC-E-MWS-T-00015
49 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON PRESTIGE-282 CB (TRIP-4) | 2745-NN-0036 |  |  | JH
50 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-5) | 2745-NN-0037
51 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-6) | 2745-NN-0038
52 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-1) | 2745-NN-0052
53 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-2) | 2745-NN-0053
54 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-3) | 2745-NN-0054
55 | LOWER ZAKUM – LTDP-1 ANODE DEMOLITION AND OFFLODING ARRANGEMENT AT ZK-235 | 2745-NN-0055 | AD-27-PL-625271-SHT-001 | 1 | 2 |  | 2025-07-29 | CSE-2745-PMT-T-002
|  |  |  | 2 | 2 |  | 2025-10-13 | CSE-2745-PMT-T-011
56 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR CONCRETE SLEEPERS (USING MP-02) FOR ZWSC (PDP-GPF-II) ZCSC (PDP) | 2745-NN-0056 | AD-27-PL-625272-SHT-001 | 1 | 2 |  | 2025-08-04 | CSE-2745-PMT-T-005
57 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR MATTRESSES USING MP-02 FOR ZWSC (PDP-GPF-II) ZCSC (PDP) | 2745-NN-0057 | AD-27-PL-625273-SHT-001 | 1 | 2 |  | 2025-07-31 | CSE-2745-PMT-T-003
58 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON PRESTIGE-281 CB FOR WHT-2, WHT-3 | 2745-NN-0058 | AD-27-PL-625274-SHT-001 | 1 | 2 |  | 2025-10-03 | CSE-2745-PMT-T-007 | 2025-10-04 | 2745-NMDC-E-AO-T-00586 | 2025-10-22 | 11688-NMDC-TR-03177 | 4 | 2025-10-28 | 2745-NMDC-E-MWS-T-00007
59 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION OF CONCRETE MATTRESS (USING MP-01) FOR ZWSC (PDP-GPF-II) ZCSC (PDP) | 2745-NN-0059 | AD-27-PL-625275-SHT-001 | 1 | 2 |  | 17-09-2025 30-10-2025 | CSE-2745-PMT-T-006 | 2025-10-30 | 2745-NMDC-E-AO-T-00684 |  |  |  | 2025-10-30 | 2745-NMDC-E-MWS-T-00009 |  |  |  | again rev-1 sent to 30/10/2025
60 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS (USING MP-01) FOR ZWSC (PDP-GPF-II) ZCSC (PDP) | 2745-NN-0060 | AD-27-PL-625276-SHT-001 | 1 | 2 |  | 2025-10-06 | CSE-2745-PMT-T-008 | 2025-10-06 | 2745-NMDC-E-AO-T-00591 | 2025-10-09 | 11688-NMDC-TR-03071 | 3
|  |  |  | 2 | 2 |  | 2025-11-04 | CSE-2745-PMT-T-018 | 2025-11-05 | 2745-NMDC-E-AO-T-00700 |  |  |  | 2025-11-05 | 2745-NMDC-E-MWS-T-00011
61 | OWER ZAKUM – LTDP-1 STALK ON RISER INSTALLATION FOR 18" WI PL - WHT2 | 2745-NN-0061 | AD-27-PL-625277-SHT-001
62 | LOWER ZAKUM - WHT-ZK-288 LIFTING & INSTALLATION OF J-TUBE BY MP-01 (SHT. 1 TO 5) | 2745-NN-0062 | AD-27-PL-625278-SHT-001 | 1 | 2 |  | 2025-10-24 | CSE-2745-PMT-T-016 | 2025-10-28 | 2745-NMDC-E-AO-T-00643 |  |  |  | 2025-10-28 | 2745-NMDC-E-MWS-T-00006
63 | LOWER ZAKUM - WHT-ZK-288 LIFTING & INSTALLATION OF J-TUBE CLAMPS BY MP-01 (SHT. 1 TO 3) | 2745-NN-0063 | AD-27-PL-625279-SHT-001 | 1 | 2 |  | 2025-10-24 | CSE-2745-PMT-T-016 | 2025-10-28 | 2745-NMDC-E-AO-T-00643 |  |  |  | 2025-10-28 | 2745-NMDC-E-MWS-T-00007
64 | LOWER ZAKUM – LTDP-1 STALK ON RISER INSTALLATION FOR 18" WI PL - ZWSC RP1 | 2745-NN-0064 | AD-27-PL-625280-SHT-001 | 1 | 2 |  | 2025-11-03 | CSE-2745-PMT-T-017
| TYPICAL LIFTING AND INSTALLATION OF SANDBAGS USING MP-01 |  |  | REMARKS | [14 empty] | Title changed
65 | LOWER ZAKUM – LTDP-1 STALK ON RISER INSTALLATION FOR 20" OIL PL - WHT2 | 2745-NN-0065 | AD-27-PL-625281-SHT-001
66 | LOWER ZAKUM – LTDP-1 STALK ON RISER INSTALLATION FOR 20" OIL PL - ZWSC RP1 | 2745-NN-0066 | AD-27-PL-625282-SHT-001
67 | LOWER ZAKUM – LTDP-1 STALK ON RISER INSTALLATION FOR 24" OIL PL - ZCSC CSP | 2745-NN-0067 | AD-27-PL-625283-SHT-001
68 | LOWER ZAKUM – LTDP-1 STALK ON RISER INSTALLATION FOR 24" OIL PL - ZWSC RP1 | 2745-NN-0068 | AD-27-PL-625284-SHT-001

## Sketch
Project 2745
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2745 | OFO-P2745-SK-T-001 | TEMPORARY HANG OFF CLAMP FOR 89.9DIA CABLE |  |  |  |  | 06/05/2025 | CDG
2 | 2745 | OFO-P2745-SK-T-002 | TYPICAL CABLE PULLING ARRANGEMENT AT WHT ZK-235 |  |  |  |  | 21/05/2025 | SKT
3 | 2745 | OFO-P2745-SK-T-003 | TYPICAL CABLE PULLING ARRANGEMENT AT WHT ZK-288 |  |  |  |  | 21/05/2025 | SKT
4 | 2745 | OFO-P2745-SK-T-004 | TYPICAL CABLE PULLING ARRANGEMENT AT WHT-2 |  |  |  |  | 21/05/2025 | SKT
5 | 2745 | OFO-P2745-SK-T-005 | TYPICAL CABLE PULLING ARRANGEMENT AT WHT-3 |  |  |  |  | 21/05/2025 | SKT
6 | 2745 | OFO-P2745-SK-T-006 | TYPICAL CABLE PULLING ARRANGEMENT AT WHT ZK-11 |  |  |  |  | 26/05/2025 | SKT
7 | 2745 | OFO-P2745-SK-T-007 | TYPICAL LIFTING AND INSTALLATION OF FLEXIBLE MATTRESSES BY AL MARYAH FOR CABLE CROSSING LOCATIONS | 1 | C | √ | √ | 06/08/2025 | ENH | @
8 | 2745 | OFO-P2745-SK-T-008 | SAFEEN PEARL CABLE LAYOUT ARRANGEMENT | 1 | A | √ | √ | 30/06/2025 | SHIJU | @
9 | 2745 | OFO-P2745-SK-T-009 | STORAGE QUADRANT 1.5M RADIUS FOR 14’’ J-TUBE | 1 | A | √ | √ | 2025-07-27 | SKT | @
10 | 2745 | OFO-P2745-SK-T-010 | DETAILS OF STANCHION SUPPORT AND STOPPER BEAM ON PRESTIGE-282 CB | 1 + 7 | B, 3 | √ | √ | 2025-09-29 | JH / SKS | @ | CTL-Rev-3 Not issued -updating drawing
11 | 2745 | OFO-P2745-SK-T-011 | A-FRAME ARRANGEMENT FOR CABLE PULLING IN WHT-2 | 1 | A | √ | √ | 2025-10-13 | SKT | @
12 | 2745 | OFO-P2745-SK-T-012 | A-FRAME ARRANGEMENT FOR CABLE PULLING IN WHT-3 | 2 | A | √ | √ | 2025-10-13 | SKT | @
13 | 2745 | OFO-P2745-SK-T-013 | TYPICAL CABLE STORAGE ARRANGEMENT ON WALKWAY | 1 | A | √ | √ | 2025-10-13 | SKT | @
14 | 2745 | OFO-P2745-SK-T-014 | DECK LAYOUT OF MP-01 WITH CONCRETE MATTRESS, J-TUBE & CLAMPS |  |  |  |  | 2025-11-05 | AMITH

## Cut-lists
Project 2745
CUT-LIST DRAWINGS
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2745 | OFO-P2745-SK-T-010 | DETAILS OF STANCHION SUPPORTS AND STOPPER BEAM ON PRESTIGE-282 CB | 1 + 7 | 2 | √ | √ | 2025-09-30 | CSE-OF-2745-T-003 | @