## PIPELINE & CABLE
|  | Upgrade Zuluf AM Crude Platforms – Zuluf Package 3 ZTP-3 (CRPO 136) Upgrade Zuluf AM Crude Platforms – Zuluf Package 4 Subsea Cables & Flowlines (CRPO 137) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | CRPO#136 PACKAGE #4 -6511069591(OOK)/6511068664(IK)- ZULF AH WEST OIL FACILITIES BI-10-07868 CRPO#137 PACKAGE #5 6511069593(OOK)/6511068669(IK) - ZULF AH EAST OIL FACILITIES BI-10-07868 | [10 empty] | REVISION :
|  | OFFSHORE CONSTRUCTION ENGINEERING DELIVERABLES | [10 empty] | DATE :
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE# | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | 8" PIPE STACKING ANALYSIS REPORT | 2790-2792-NN-RP-001 | A | 2 | 2025-04-24 | 14/04/2025 | CSE-2790-2792-PMT-T-015 | 02-07-2025 | COM-2790-2792-NMDC-E-T-01989
2 | PIPELAY ANALYSIS REPORT FOR 12" PIPELINE FROM ZULF 110/121 TO ZTP-3 | 2790-2792-NN-RP-002 |  |  | 2026-04-13
3 | PIPELAY ANALYSIS REPORT FOR 12" PIPELINE FROM ZULF 146/151 TO ZTP-3 | 2790-2792-NN-RP-003 |  |  | 2026-12-09
4 | PIPELAY ANALYSIS REPORT FOR 8" PIPELINE FROM ZTP-7 TO ZTP-4 | 2790-2792-NN-RP-004 | A | 2 | 2025-05-05 | 25/04/2025 | CSE-2790-2792-PMT-T-019 | 25/04/2025 | COM-2790-2792-NMDC-E-T-01529 | 21/07/2025 | ZAMUD-12741-136-137-T-1878-25 | CODE-2 REVIEW COMMENTS
|  |  | B | 2 | 2025-09-19 | 09/09/2025 | CSE-2790-2792-PMT-T-025 | 09/09/2025 | COM-2790-2792-NMDC-E-T-02415 | 06/10/2025 | ZAMUD-12741-136-137-T-2464-25 | CODE-3 NOT APPROVED
|  |  | C | 2 | 2025-11-28 | 18-11-2025 | CSE-2790-2792-PMT-T-032 | 18-11-2025 | COM-2790-2792-NMDC-E-T-03060 | 11-12-2025 | ZAMUD-12741-136-137-T-2975-25 | CODE-3 NOT APPROVED
|  |  | D | 2 | 2026-06-14 | 04-06-2026 | CSE-2790-2792-PMT-T-056 | 04-06-2026 | COM-2790-2792-NMDC-E-T-05017 | 15-06-2026 | ZAMUD-12741-136-137- T-1175-26
|  |  | 00 | 3 |  | 17-07-2026 | CSE-2790-2792-PMT-T-067 | 05-08-2026 | COM-2790-2792-NMDC-E-T-05406
5 | INSTALLATION ANALYSIS REPORT FOR 10" FLEXIBLE PIPELINE FROM ZULF 25/30 TO ZTP-3 | 2790-2792-NN-RP-005 |  |  | 31-11-26
6 | INSTALLATION ANALYSIS REPORT FOR 10" FLEXIBLE PIPELINE FROM ZULF 122/127 TO ZTP-3 | 2790-2792-NN-RP-006 |  |  | 2027-03-07
7 | INSTALLATION ANALYSIS REPORT FOR 10" FLEXIBLE PIPELINE FROM ZULF 140/145 TO ZTP-3 | 2790-2792-NN-RP-007 |  |  | 2026-12-24
8 | INSTALLATION ANALYSIS REPORT FOR 12" FLEXIBLE PIPELINE FROM ZULF 216/221 TO ZTP-3 | 2790-2792-NN-RP-008 |  |  | 2026-11-21
9 | INSTALLATION ANALYSIS REPORT FOR 12" FLEXIBLE PIPELINE FROM ZULF 240/245 TO ZTP-3 | 2790-2792-NN-RP-0009 |  |  | 2026-11-09
10 | INSTALLATION ANALYSIS REPORT FOR 15KV SUBSEA CABLES CAMPAIGN-1 | 2790-2792-NN-RP-010 | A | 2 | 2024-10-26 | 16-10-2024 | CSE-2790-2792-PMT-T-001 | 28-10-2024 | COM-2790-2792-NMDC-E-T-00650 | 29/12/2024 | 12741-136-137- T-3231-24 T-00650 | CODE-2 REVIEW COMMENTS | 10/01/2025 | Email | 16/01/2025 | MDDXB 6152-MD-02-1402-01 | comments
|  |  | B | 2 | 2025-03-24 | 14/03/2025 | CSE-2790-2792-PMT-T-010 | 15/03/2025 | COM-2790-2792-NMDC-E-T-01283 | 19/03/2025 | ZAMUD-12741-136-137-T-0744-25 | 6 - Reviewed w/o comments | 19/03/2025 | 2790-2792-NMDC-E-MWS-T-00005 | 21/03/2025 | MDDXB 6152-MD-02-1402-02 | approved
|  |  | 00 | 3 | 2025-04-04 | 25/03/2025 | CSE-2790-2792-PMT-T-012 | 27/03/2025 | COM-2790-2792-NMDC-E-T-01359
|  |  | 01 | 3 | 2025-10-18 | 08/10/2025 | CSE-2790-2792-PMT-T-027 | 30/10/2025 | COM-2790-2792-NMDC-E-T-02716
11 | INSTALLATION ANALYSIS REPORT FOR ICCP CABLES CAMPAIGN-1 | 2790-2792-NN-RP-011 | A | 2 | 2024-12-06 | 26/11/2024 | CSE-2790-2792-PMT-T-003 | 29/11/2024 | COM-2790-2792-NMDC-E-T-00767 | 31/12/2024 | ZAMUD-12741-136-137-T-3253-24 | CODE-5 REVIEWED WITH COMMENTS | 09/01/2025 | Email | 14/01/2025 | MDDXB 6152-MD-01-1401-01 | comments
|  |  | B | 2 | 2025-04-12 | 02/04/2025 | CSE-2790-2792-PMT-T-012 | 04/04/2025 | COM-2790-2792-NMDC-E-T-01404 | 11/04/2025 | ZAMUD-12741-136-137-T-1041-25 | REVIEWED WITH NO COMMENTS
|  |  | 00 | 3 | 2025-05-05 | 25/04/2025 | CSE-2790-2792-PMT-T-020 | 25/04/2025 | COM-2790-2792-NMDC-E-T-01530
12 | LIFTING AND INSTALLATION ANALYSIS REPORT OF TIE IN SPOOL | 2790-2792-NN-RP-012 |  |  | cancelled
13 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES & MISC. ITEMS ON GAC-82 (TRIP-1) | 2790-2792-NN-RP-013 | A | 2 | 2026-06-20 | 2025-05-27 | CSE-2790-2792-PMT-T-021 | 2025-05-27 | COM-2790-2792-NMDC-E-T-01797 | 2025-06-30 | ZAMUD-12741-136-137-T-1683-25 | CODE-5 REVIEWED WITH COMMENTS | 2025-05-27 | 2790-2792-NMDC-E-MWS-T-00008 | 45820 | MDDXB 6152-MD-05-1301-01 | comments
|  |  | B | 2 |  | 2025-08-11 | CSE-2790-2792-PMT-T-022
14 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-2) | 2790-2792-NN-RP-014 |  |  | cancelled
15 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF FLEXIBLE PIPE REELS (TRIP-1) | 2790-2792-NN-RP-015 |  |  | 2026-10-01
16 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES, SLEEPERS & MATTRESSES ON ASTRO-250 (TRIP-1) | 2790-2792-NN-RP-016 | A | 2 | 2027-01-01 | 2026-06-25 | CSE-2790-2792-PMT-T-062 | 2026-06-25 | COM-2790-2792-NMDC-E-T-05152
|  |  | B | 2 |  | 2026-07-24 | CSE-2790-2792-PMT-T-068 | 2026-07-24 | COM-2790-2792-NMDC-E-T-05333 |  |  |  | 2026-07-24 | 2790-2792-NMDC-E-MWS-T-00023 | 2026-07-27 | MDDXB-6152-MD-27-1309-02 | approved
17 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES ON CARGO BARGE (TRIP-2) | 2790-2792-NN-RP-017 |  |  | 2027-01-01
18 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES ON CARGO BARGE (TRIP-3) | 2790-2792-NN-RP-018 |  |  | 2027-01-01
19 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF RISERS , J-TUBES, SPOOLS & MISC. ITEMS ON AESEN-2805 (TRIP-1) | 2790-2792-NN-RP-019 | A | 2 | 2026-03-15 | 2025-11-25 | CSE-2790-2792-PMT-T-033 | [5 empty] | 2025-11-25 | 2790-2792-NMDC-E-MWS-T-00011 | 2025-12-24 | MDDXB 6152-MD-08-1304-01 | comments
|  |  | CRS | [9 empty] | 2026-01-05 | email sent to PMT (SSM)
|  |  | B | 2 |  | 2026-03-22 | CSE-2790-2792-PMT-T-042 | 2026-03-24 | COM-2790-2792-NMDC-E-T-04300 | 2026-04-23 | ZAMUD-12741-136-137-T-0755-26 | 4 | 2026-03-24 | 2790-2792-NMDC-E-MWS-T-00017
20 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF RISERS & SPOOLS & J-TUBES (TRIP-2) | 2790-2792-NN-RP-020 |  |  | 2026-10-01
21 | TRANSPOOLING ANALYSIS REPORT FOR 15KV SUBSEA CABLE CAMPAIGN-1 | 2790-2792-NN-RP-021 | A | 2 | 2025-02-21 | 11/02/2025 | CSE-2790-2792-PMT-T-007 | 12/02/2025 | COM-2790-2792-NMDC-E-T-01062 |  |  |  | 12/02/2025 | 2790-2792-NMDC-E-MWS-T-00003 | 21/02/2025 | MDDXB 6152-MD-04-1201-01 | comments
|  |  | B | 2 | 2025-03-08 | 26/02/2025 | CSE-2790-2792-PMT-T-009 | [5 empty] | 27/02/2026 | 2790-2792-NMDC-E-MWS-T-00004 | 05/03/2025 | MDDXB-6152-MD-04-1201-02 | approved
22 | INSTALLATION ANALYSIS REPORT FOR ICCP CABLES CAMPAIGN-1 BY CCC MARITIME 2 | 2790-2792-NN-RP-022 | A | 2 | 2025-09-01 | 2025-08-22 | CSE-2790-2792-PMT-T-025 | 14-010-2025 | COM-2790-2792-NMDC-E-T-02681 |  |  |  | 14-010-2025 | 2790-2792-NMDC-E-MWS-T-00010
23 | PIPELAY ANALYSIS REPORT FOR 8” PIPELINE FROM ZTP-7 TO ZTP-4 WITH SAPURA 1200 | 2790-2792-NN-RP-023 | A | 2 | 2025-03-04 | 22/02/2025 | CSE-2790-2792-PMT-T-036
24 | INSTALLATION ANALYSIS REPORT FOR 15kV SUBSEA CABLES CAMPAIGN - 2 | 2790-2792-NN-RP-024 | A | 2 | 2026-03-09 | 27/02/2026 | CSE-2790-2792-PMT-T-040 | 28/02/2026 | COM-2790-2792-NMDC-E-T-04114 | 2026-06-01 | ZAMUD-12741-136-137-T-1022-26 | 2
|  |  | B | 2 | 2026-06-18 | 08-06-2026 | CSE-2790-2792-PMT-T-057 | 08-06-2026 | COM-2790-2792-NMDC-E-T-05034
|  |  | C | 2 |  | 12-06-2026 | CSE-2790-2792-PMT-T-060 | 12-06-2026 | COM-2790-2792-NMDC-E-T-05078 | 13-07-2026 | ZAMUD-12741-136-137- T-1350-26 | 2
|  |  | D | 2 |  | 16-07-2026 | CSE-2790-2792-PMT-T-066 | 16-07-2026 | COM-2790-2792-NMDC-E-T-05287 | 27-07-2026 | ZAMUD-12741-136-137- T-1453-26 | 2
25 | TRANSPOOLING ANALYSIS REPORT FOR 15KV SUBSEA CABLE CAMPAIGN-2 | 2790-2792-NN-RP-025 | A | 2 | 2026-05-02 | 22/04/2026 | CSE-2790-2792-PMT-T-046 | 22/04/2026 | COM-2790-2792-NMDC-E-T-04721
|  |  | B | 2 | 2026-06-11 | 01-06-2026 | CSE-2790-2792-PMT-T-053 | 02-06-2026 | COM-2790-2792-NMDC-E-T-04975 | 08-06-2026 | ZAMUD-12741-136-137-T-1068-26
26 | INSTALLATION ANALYSIS REPORT FOR ICCP CABLES CAMPAIGN-2 WITH UMM SHAIF | 2790-2792-NN-RP-026 | A | 2 | 2026-05-16 | 06-05-2026 | CSE-2790-2792-PMT-T-048 | 22-05-2026 | COM-2790-2792-NMDC-E-T-04952
27 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF TP-3 RISERS, SPOOLS & MISC. ITEMS ON CB-08 BARGE | 2790-2792-NN-RP-027 | A | 2 | 2026-10-01 | 01-06-2026 | CSE-2790-2792-PMT-T-054 | 10-06-2026 | 2790-2792-NMDC-E-MWS-T-00018
28 | SEAFASTENING DESIGN REPORT FOR DEMOLISHED LINEPIPES ON CB-8 BARGE | 2790-2792-NN-RP-028 | A | 2 | 2026-07-15 | 01-07-2026 | CSE-2790-2792-PMT-T-065
29 | TRANSPOOLING ANALYSIS REPORT FOR 15KV SUBSEA CABLES CAMPAIGN-2 (UMM SHAIF TO MILLENIUM-3) | 2790-2792-NN-RP-029 | A | 2 |  | 31-07-2026 | CSE-2790-2792-PMT-T-069 | [5 empty] | 31-07-2026 | 2790-2792-NMDC-E-MWS-T-00024

## Documents - Naval & Marine
|  | Upgrade Zuluf AM Crude Platforms – Zuluf Package 3 ZTP-3 (CRPO 136) Upgrade Zuluf AM Crude Platforms – Zuluf Package 4 Subsea Cables & Flowlines (CRPO 137) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | CRPO#136 PACKAGE #4 -6511069591(OOK)/6511068664(IK)- ZULF AH WEST OIL FACILITIES BI-10-07868 CRPO#137 PACKAGE #5 6511069593(OOK)/6511068669(IK) - ZULF AH EAST OIL FACILITIES BI-10-07868 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DELIVERABLES | [10 empty] | DATE : |  |  |  | 0
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE# | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | BERTHING ANALYSIS FOR BURGEON TIDE | 2790-2792-ZZ-CL-001 | A |  | 2024-01-17
B
2 | MOORING ANALYSIS DURING PIPELAYING OF 12" PIPELINE FROM ZULF 110/121 TO ZTP-3 | 2790-2792-ZZ-CL-002 |  |  | cancelled
3 | MOORING ANALYSIS DURING PIPELAYING OF 12" PIPELINE FROM ZULF 146/151 TO ZTP-3 | 2790-2792-ZZ-CL-003 |  |  | cancelled
4 | MOORING ANALYSIS DURING PIPELAYING OF 8" PIPELINE FROM ZTP-7 TO ZTP-4 | 2790-2792-ZZ-CL-004 |  |  | cancelled
5 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES & MISC. ITEMS ON GAC-82 (TRIP-1) | 2790-2792-ZZ-CL-005 | A | 2 | 2025-08-15 | 2025-05-27 | CSE-2790-2792-PMT-T-021 | 2025-05-27 | COM-2790-2792-NMDC-E-T-01798 | 21-07-2025 | ZAMUD-12741-136-137-T-1882-25 | CODE-1 Approved | 2025-05-27 | 2790-2792-NMDC-E-MWS-T-00009 | 16-06-205 | MDDXB-6152-MD-06-1302-01 | comments
|  |  | B | 2 |  | 2025-08-11 | CSE-2790-2792-PMT-T-022
6 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES (TRIP-2) | 2790-2792-ZZ-CL-006 |  |  | cancelled
7 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF FLEXIBLE PIPE REELS (TRIP-1) | 2790-2792-ZZ-CL-007 |  |  | 2026-10-01
8 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES, SLEEPERS & MATTRESSES ON ASTRO-250 (TRIP-1) | 2790-2792-ZZ-CL-008 | A | 2 | 2027-01-01 | 2026-06-25 | CSE-2790-2792-PMT-T-062 | 2026-06-25 | COM-2790-2792-NMDC-E-T-05153 | 2026-07-20 | ZAMUD-12741-136-137-T-1394-26 |  | 2026-06-25 | 2790-2792-NMDC-E-MWS-T-00021 | 2026-07-07 | MDDXB-6152-MD-29-1308-01 | Approved
|  |  | B | 2 |  | 2026-07-24 | CSE-2790-2792-PMT-T-068 | 2026-07-24 | COM-2790-2792-NMDC-E-T-05332 |  |  |  | 2026-07-24 | 2790-2792-NMDC-E-MWS-T-00022 | 2026-07-27 | MDDXB-6152-MD-29-1308-02 | Approved
9 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES ON CARGO BARGE (TRIP-2) | 2790-2792-ZZ-CL-009 |  |  | 2027-01-01
10 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES ON CARGO BARGE (TRIP-3) | 2790-2792-ZZ-CL-010 |  |  | 2027-01-01
11 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF RISERS & SPOOLS & J-TUBES (TRIP-1) | 2790-2792-ZZ-CL-011 | A | 2 | 2026-11-30 | 2025-11-25 | CSE-2790-2792-PMT-T-033 | [5 empty] | 2025-11-28 | 2790-2792-NMDC-E-MWS-T-00012 | 06-01-2026 | MDDXB-6152-MD-15-1305-01 | Approved
12 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF RISERS & SPOOLS & J-TUBES (TRIP-2) | 2790-2792-ZZ-CL-012 |  |  | 2026-10-01
13 | BERTHING ANALYSIS FOR STANFORD HUDHUD | 2790-2792-ZZ-CL-013 | A |  | 2026-01-05 | 2025-01-30 | CSE-2790-2792-PMT-T-005 | 2025-01-30 | COM-2790-2792-NMDC-E-T-00982 |  |  |  | 12/02/2025 | 2790-2792-NMDC-E-MWS-T-00003 | -- | MDDXB-6152-MD-03-401-01 | comments
|  |  | B |  |  | 2025-04-09 | CSE-2790-2792-PMT-T-014 | [5 empty] | 2025-04-10 | 2790-2792-NMDC-E-MWS-T-00007 | 2025-04-17 | MDDXB-6152-MD-03-401-02 | Approved
|  |  | 00 |  |  | 2025-04-18 | CSE-2790-2792-PMT-T-018 | 2025-05-23 | COM-2790-2792-NMDC-E-T-01776
|  |  | 00A |  |  | 2025-12-10 | CSE-2790-2792-PMT-T-034 | 2025-12-10 | COM-2790-2792-NMDC-E-T-03262 | [8 empty] | reissued on 10/12
|  |  | 00B |  |  | 2026-01-06 | CSE-2790-2792-PMT-T-039
14 | BERTHING ANALYSIS FOR MUTAWA-13 NEAR PLATFORMS | 2790-2792-ZZ-CL-014 | A | 2 | 2025-12-15 | 2025-10-17 | CSE-2790-2792-PMT-T-030 | 2025-10-23 | COM-2790-2792-NMDC-E-T-02811
|  |  | B | 2 |  | 2025-12-12 | CSE-2790-2792-PMT-T-035 | 2025-12-12 | COM-2790-2792-NMDC-E-T-03266 | 04-02-2026 | ZAMUD-12741-136-137-T-0288-26 | CODE-1 Approved
15 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES & MISC ITEMS ON CASPIAN-281(TRIP-1) | 2790-2792-ZZ-CL-015 |  |  | 2026-07-01
16 | BERTHING ANALYSIS FOR MAG CAPELLA | 2790-2792-ZZ-CL-016 | A | 2 | 2026-07-01 | 2026-03-24 | CSE-2790-2792-PMT-T-043
|  |  | B |  |  | 2026-04-02 | CSE-2790-2792-PMT-T-044
|  |  | C |  |  | 2026-05-20 | CSE-2790-2792-PMT-T-051
|  |  | D |  |  | 2026-05-25 | CSE-2790-2792-PMT-T-052
17 | BERTHING ANALYSIS FOR ZAKHER PIONEER & ZAKHER PELICAN | 2790-2792-ZZ-CL-017 | A | 2 | 2026-05-10 | 2026-05-08 | CSE-2790-2792-PMT-T-049
|  |  | B |  |  | 2026-08-04 | CSE-2790-2792-PMT-T-070
|  |  | C |  |  | 2026-08-20 | CSE-2790-2792-PMT-T-071
18 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF TP-3 RISER GUARDS, RISERS & CLAMPS ON CB-8 (TRIP-1) | 2790-2792-ZZ-CL-018 | A | 2 | 2026-06-05 | 01-06-2026 | CSE-2790-2792-PMT-T-054 | [5 empty] | 10-06-2026 | 2790-2792-NMDC-E-MWS-T-00019 | 18-06-2026 | MDDXB-6152-MD-30-1306-01 | Approved
19 | BERTHING ANALYSIS FOR MAG ARISTON | 2790-2792-ZZ-CL-019 | A | 2 | PKR | 2026-09-04 | CSE-2790-2792-PMT-T-072

## DRAWINGS
|  | Upgrade Zuluf AM Crude Platforms – Zuluf Package 3 ZTP-3 (CRPO 136) Upgrade Zuluf AM Crude Platforms – Zuluf Package 4 Subsea Cables & Flowlines (CRPO 137) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | CRPO#136 PACKAGE #4 -6511069591(OOK)/6511068664(IK)- ZULF AH WEST OIL FACILITIES BI-10-07868 CRPO#137 PACKAGE #5 6511069593(OOK)/6511068669(IK) - ZULF AH EAST OIL FACILITIES BI-10-07868 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DELIVERABLES | [10 empty] | DATE :
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE# | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | START UP HEAD FOR 10" PIPELINE | 2790-2792-NN-0001 |  |  | cancelled
2 | LAYDOWN HEAD FOR 10" PIPELINE | 2790-2792-NN-002 |  |  | cancelled
3 | TYPICAL EMERGENCY LAYDOWN HEAD FOR 10" PIPELINE | 2790-2792-NN-003 |  |  | cancelled
4 | TYPICAL BUCKLE DETECTOR DETAIL FOR 10" PIPELINE | 2790-2792-NN-004 |  |  | cancelled
5 | START UP HEAD FOR 12" PIPELINE | 2790-2792-NN-005 |  |  | cancelled
6 | LAYDOWN HEAD FOR 12" PIPELINE | 2790-2792-NN-006 |  |  | cancelled
7 | TYPICAL EMERGENCY LAYDOWN HEAD FOR 12" PIPELINE | 2790-2792-NN-007 |  |  | cancelled
8 | TYPICAL BUCKLE DETECTOR DETAIL FOR 12" PIPELINE | 2790-2792-NN-008 |  |  | cancelled
9 | START UP HEAD DETAILS FOR 8" PIPELINE | 2790-2792-NN-0009 | A | 3 | 2025-04-15 | 12-02-2025 | CSE-2790-2792-PMT-T-008
|  |  | B | 3 |  | 14-03-2025 | CSE-2790-2792-PMT-T-011
|  |  | C | 3 |  | 14-04-2025 | CSE-2790-2792-PMT-T-016
10 | LAYDOWN HEAD FOR 8" PIPELINE | 2790-2792-NN-0010 | A | 3 | 2025-04-15 | 12-02-2025 | CSE-2790-2792-PMT-T-008
|  |  | B | 3 |  | 14-04-2025 | CSE-2790-2792-PMT-T-016
11 | TYPICAL EMERGENCY LAYDOWN HEAD FOR 8" PIPELINE | 2790-2792-NN-0011 | A | 3 | 2025-04-15 | 12-02-2025 | CSE-2790-2792-PMT-T-008
|  |  | B | 3 |  | 14-04-2025 | CSE-2790-2792-PMT-T-016
12 | TYPICAL BUCKLE DETECTOR DETAIL FOR 8" PIPELINE | 2790-2792-NN-0012 |  |  | cancelled
13 | TYPICAL LIFTING OF CONCRETE SLEEPERS DELMA-2000 | 2790-2792-NN-0013 | A | 3 | 2025-08-10 | 04-08-2025 | CSE-2790-2792-PMT-T-023
14 | TYPICAL LIFTING OF CONCRETE MATRESSES BY UMM SHAIF | 2790-2792-NN-0014 | A | 3 | 2025-08-10 | 15-11-2024 | CSE-2790-2792-PMT-T-002
|  |  | B | 3 |  | 04-08-2025 | CSE-2790-2792-PMT-T-006
15 | LIFTING AND INSTALLATION ARRANGEMENT DRAWINGS FOR 10in RISER AT ZULUF ZTP-3 FROM ZULF 25/30 (ROW 2) | 2790-2792-NN-0015 |  | KTR 02-06 | 2026-10-01
16 | LIFTING AND INSTALLATION ARRANGEMENT DRAWINGS FOR 10in RISER AT ZULUF ZTP-3 FROM ZULF 122/127(ROW 2) | 2790-2792-NN-0016 |  | KTR 02-06 | 2026-10-01
17 | LIFTING AND INSTALLATION ARRANGEMENT DRAWINGS FOR 10in RISER AT ZULUF ZTP-3 FROM ZULF 140/145 (ROW 1) – TWO SECTIONS | 2790-2792-NN-0017 |  | KTR 02-06 | 2026-10-01
18 | LIFTING AND INSTALLATION ARRANGEMENT DRAWINGS FOR 12in RISER AT ZULUF ZTP-3 FROM ZULF 216/221 (ROW 2) – TWO SECTIONS | 2790-2792-NN-0018 |  | KTR 02-06 | 2026-10-01
19 | LIFTING AND INSTALLATION ARRANGEMENT DRAWINGS FOR 12in RISER AT ZULUF ZTP-3 FROM ZULF 240/245 (ROW 1) | 2790-2792-NN-0019 |  | KTR 02-06 | 2026-10-01
20 | LIFTING AND INSTALLATION ARRANGEMENT DRAWINGS FOR 12in RISER AT ZULUF ZTP-3 FROM ZULF 110/121 (ROW 1) | 2790-2792-NN-0020 |  | KTR 02-06 | 2026-10-01
21 | LIFTING AND INSTALLATION ARRANGEMENT DRAWINGS FOR 12in RISER AT ZULUF ZTP-3 FROM ZULF 146/151 (ROW 1) | 2790-2792-NN-0021 |  | KTR 02-06 | 2026-10-01
22 | LIFTING AND INSTALLATION OF 10" & 12" RISERS AT ZTP-3 | 2790-2792-NN-0022 |  |  | 2026-10-01
23 | LIFTING AND INSTALLATION OF 8" RISER AT ZTP-7 CCC WADED ALETHEIA | 2790-2792-NN-0023 | A | 3 | 2026-04-30 | 17-10-2025 | CSE-2790-2792-PMT-T-029
|  |  | B | 3 |  | 18-05-2026 | CSE-2790-2792-PMT-T-050
24 | LIFTING AND INSTALLATION OF 8" RISER AT ZTP-4 CCC WADAD ALETHEIA | 2790-2792-NN-0024 | A | 3 | 2026-04-30 | 23-04-2026 | CSE-2790-2792-PMT-T-047
25 | LIFTING AND INSTALLATION OF 16" RISER AT ZULF 228/233 | 2790-2792-NN-0025 |  |  | cancelled
26 | LIFTING AND INSTALLATION OF 10" & 16" RISERS AT ZULF 152/163 | 2790-2792-NN-0026 |  |  | cancelled
27 | LIFTING AND INSTALLATION ARRANGEMENT DRAWINGS FOR 16IN SPOOL AT ZULF 204/209 | 2790-2792-NN-0027 |  | KTR / CDG | 2026-06-30 | [12 empty] | SERVER ONLY - NO FEEDBACK - 06/08
28 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-146/151, 961/962 | 2790-2792-NN-0028 |  |  | cancelled
29 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-204/209, 289, 1000 | 2790-2792-NN-0029 |  |  | cancelled
30 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-240/245, 347/348 | 2790-2792-NN-0030 |  |  | cancelled
31 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-282/293 | 2790-2792-NN-0031 |  |  | cancelled
32 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-294/301 | 2790-2792-NN-0032 |  |  | cancelled
33 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-330/338 | 2790-2792-NN-0033 |  |  | cancelled
34 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-490/499 | 2790-2792-NN-0034 |  |  | cancelled
35 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF TP-5 | 2790-2792-NN-0035 |  |  | cancelled
36 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-500/509 | 2790-2792-NN-0036 |  |  | cancelled
37 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-680/689 | 2790-2792-NN-0037 |  |  | cancelled
38 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF TP-7 & ZULF-370/379 | 2790-2792-NN-0038 |  |  | cancelled
39 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-110/121 | 2790-2792-NN-0039 |  |  | cancelled
40 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-140/145, 951/952 | 2790-2792-NN-0040 |  |  | cancelled
41 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-590/599 | 2790-2792-NN-0041 |  |  | cancelled
42 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-25/30, 180, 1001 | 2790-2792-NN-0042 |  |  | cancelled
43 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-122/127 | 2790-2792-NN-0043 |  |  | cancelled
44 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-152/163 | 2790-2792-NN-0044 |  |  | cancelled
45 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-216/221, 346, 349 | 2790-2792-NN-0045 |  |  | cancelled
46 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-228/233, 308/309 | 2790-2792-NN-0046 |  |  | cancelled
47 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-360/369 | 2790-2792-NN-0047 |  |  | cancelled
48 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-480/489 | 2790-2792-NN-0048 |  |  | cancelled
49 | LIFTING AND INSTALLATION OF J-TUBES AT ZULF-510/519 | 2790-2792-NN-0049 |  |  | cancelled
50 | TYPICAL LIFTING FOR DEMOLISHED PIPES | 2790-2792-NN-0050 |  |  | 2026-07-15
51 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 8” CC PIPES @ GAC-82 (TRIP-1) | 2790-2792-NN-0051 | A | 3 | 2025-08-15 | 2025-05-27 | CSE-2790-2792-PMT-T-021
|  |  | B | 3 |  | 2025-08-11 | CSE-2790-2792-PMT-T-022
52 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 8" CC PIPES @ CASPIAN-281(TRIP-1) | 2790-2792-NN-0052 | A |  | SERVER ONLY REY 10-4-26 / 12/06
53 | LOADING ARRANGEMENT & SEAFASTENING OF FLEXIBLE PIPE REELS TRIP-1 WITH BALAST PLAN | 2790-2792-NN-0053 |  |  | 2026-10-01
54 | LOADING ARRANGEMENT & SEAFASTENING OF CONCRETE SLEEPERS & MATTRESSES TRIP-1 WITH BALAST PLAN | 2790-2792-NN-0054 |  |  | 2027-01-01
55 | LOADING ARRANGEMENT & SEAFASTENING OF CONCRETE SLEEPERS & MATTRESSES TRIP-2 WITH BALAST PLAN | 2790-2792-NN-0055 |  |  | 2027-01-01
56 | LOADING ARRANGEMENT & SEAFASTENING OF CONCRETE SLEEPERS & MATTRESSES TRIP-3 WITH BALAST PLAN | 2790-2792-NN-0056 |  |  | 2027-01-01 | `
57 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF DEMOLISHED PIPE ON CB-8 TRIP-1 | 2790-2792-NN-0057 | A | 3 | 2026-06-10 | 02-06-2026 | CSE-2790-2792-PMT-T-055
|  |  | B | 3 |  | 16-06-2026 | CSE-2790-2792-PMT-T-059
|  |  | 00 | 3 |  | 25-06-2026 | CSE-2790-2792-PMT-T-063
58 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SPOOLS AND TP-3 RISERS ON CB-8 | 2790-2792-NN-0058 | A | 2 | 2026-06-10 | 01-06-2026 | CSE-2790-2792-PMT-T-054
|  |  | B | 3 |  | 2026-06-08 | CSE-2790-2792-PMT-T-058
59 | FLANGE PROTECTOR DETAILS FOR 8" PIPELINE HEADS 25mm THK CONCRETE | 2790-2792-NN-0059 | A | 2 | 2025-04-30 | 2025-01-28 | CSE-2790-2792-PMT-T-004
|  |  | B | 2 |  | 2025-04-17 | CSE-2790-2792-PMT-T-017
60 | LOADING ARRANGEMENT & SEAFASTENING OF RISERS & SPOOLS & J-TUBES TRIP-1 WITH AESEN-2805 | 2790-2792-NN-0060 | A | 3 |  | 2025-10-20 | CSE-2790-2792-PMT-T-028
|  |  | B | 3 |  | 2025-11-25 | CSE-2790-2792-PMT-T-033
|  |  | C | 3 |  | 2026-03-13 | CSE-2790-2792-PMT-T-041 | [10 empty] | REV-D - SERVER ONLY 16/07/2026
61 | TYPICAL LIFTING OF CONCRETE MATRESSES BY DELMA-2000 | 2790-2792-NN-0061 |  |  | 2025-07-14
62 | TYPICAL LIFTING & INSTALLATION OF MATTRESSES DELMA-2000 | 2790-2792-NN-0062 | A | 3 | 2025-07-15 | 2025-07-14 | CSE-2790-2792-PMT-T-022
63 | TYPICAL RISER CLAMPS LIFTING AND INSTALLATION WADAD ALETHEIA | 2790-2792-NN-0063 |  |  | 2027-01-01
64 | TEMPORARY KNEE BRACE DETAIL FOR 8" SPOOL (S02) AT ZPT-4 | 2790-2792-NN-0064 | A | 3 | 2025-12-31 | 2025-12-29 | CSE-2790-2792-PMT-T-038
65 | TEMPORARY KNEE BRACE DETAIL FOR 8" SPOOL (S04) AT ZPT-7 | 2790-2792-NN-0065 | A | 3 | 2025-12-31 | 2025-12-29 | CSE-2790-2792-PMT-T-038
66 | TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING CCC WADAD ALETHEIA | 2790-2792-NN-0066 |  |  | 2026-07-15
67 | LIFTING AND INSTALLATION ARRANGEMENT DRAWING FOR 8IN F/L SPOOL AT ZTP-4 | 2790-2792-NN-0067 | A | 2 | 2026-07-15 | 2026-06-17 | CSE-2790-2792-PMT-T-061
68 | LIFTING AND INSTALLATION ARRANGEMENT DRAWING FOR 8IN F/L SPOOL AT ZTP-7 | 2790-2792-NN-0068 | A | 2 | 2026-07-15 | 2026-06-17 | CSE-2790-2792-PMT-T-061
69 | J-TUBE RIGGING ARRANGEMENT ZTP-5 (12’’ J-TUBE) | 2790-2792-NN-0069 | A | 2 | 2025-12-31 | 2025-12-24 | CSE-2790-2792-PMT-T-037
70 | J-TUBE RIGGING ARRANGEMENT ZULF 282/293 (12’’ J-TUBE) | 2790-2792-NN-0070 | A | 2 | 2025-12-31 | 2025-12-24 | CSE-2790-2792-PMT-T-037
71 | J-TUBE RIGGING ARRANGEMENT ZULF 294/301 (8’’ J-TUBE) | 2790-2792-NN-0071 | A | 2 | 2025-12-31 | 2025-12-24 | CSE-2790-2792-PMT-T-037
72 | J-TUBE RIGGING ARRANGEMENT ZULF 294/301 (12’’ J-TUBE) | 2790-2792-NN-0072 | A | 2 | 2025-12-31 | 2025-12-24 | CSE-2790-2792-PMT-T-037
73 | J-TUBE RIGGING ARRANGEMENT ZULF 330/339 (12’’ J-TUBE) | 2790-2792-NN-0073 | A | 2 | 2025-12-31 | 2025-12-24 | CSE-2790-2792-PMT-T-037
74 | J-TUBE INSTALLATION ARRANGEMENT DRAWING AT ZTP-5 (12’’ J-TUBE) | 2790-2792-NN-0074 |  |  | cancelled
75 | J-TUBE INSTALLATION ARRANGEMENT DRAWING AT ZULF 282/293 (12’’ J-TUBE | 2790-2792-NN-0075 |  |  | cancelled
76 | J-TUBE INSTALLATION ARRANGEMENT DRAWING AT ZULF 294/301 (8’’ J-TUBE) | 2790-2792-NN-0076 |  |  | cancelled
77 | J-TUBE INSTALLATION ARRANGEMENT DRAWING AT ZULF 294/301 (12’’ J-TUBE) | 2790-2792-NN-0077 |  |  | cancelled
78 | J-TUBE INSTALLATION ARRANGEMENT DRAWING AT ZULF 330/339 (12’’ J-TUBE) | 2790-2792-NN-0078 |  |  | cancelled
79 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES & MISC. ITEMS ON GAC-82 (TRIP-1) | 2790-2792-NN-0079 |  |  | 2027-01-01
80 | J-TUBE INSTALLATION ARRANGEMENT AT ZULF 330/339 (12’’ J-TUBE) BY SHUJAA-2000 | 2790-2792-NN-0080 | A |  | cancelled | [12 empty] | SERVER ONLY - NO FEEDBACK - 17/-06
81 | J-TUBE INSTALLATION ARRANGEMENT AT ZULF 294/301 (12’’ J-TUBE) BY SHUJAA-2000 | 2790-2792-NN-0081 |  |  | cancelled
82 | J-TUBE INSTALLATION ARRANGEMENT AT ZULF 294/301 (8’’ J-TUBE) BY SHUJAA-2000 | 2790-2792-NN-0082 | A |  | cancelled | [12 empty] | SERVER ONLY - NO FEEDBACK - 17/-06
83 | J-TUBE INSTALLATION ARRANGEMENT AT ZTP-5 (12’’ J-TUBE) BY SHUJAA-2000 | 2790-2792-NN-0083 | A |  | cancelled | [12 empty] | SERVER ONLY - NO FEEDBACK - 17/-06
84 | J-TUBE INSTALLATION ARRANGEMENT AT ZULF 282/293 (12’’ J-TUBE) BY SHUJAA-2000 | 2790-2792-NN-0084 | A |  | cancelled | REMARKS | [11 empty] | SERVER ONLY - NO FEEDBACK - 17/-06
85 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF DEMOLISHED PIPE ON CB-8 TRIP-2 | 2790-2792-NN-0085 | A | 3 | 2027-01-01 | 16-06-2026 | CSE-2790-2792-PMT-T-059
|  |  | 00 | 3 |  | 25-06-2026 | CSE-2790-2792-PMT-T-063
86 | LIFTING AND INSTALLATION ARRANGEMENT DRAWING FOR 8IN F/L SPOOL AT ZTP-4 USING ORIENTAL DRAGON | 2790-2792-NN-0086 |  |  | 2026-06-30 | REMARKS | [11 empty] | SERVER ONLY - NO FEEDBACK - 06/08
87 | LIFTING AND INSTALLATION ARRANGEMENT DRAWING FOR 8IN F/L SPOOL AT ZTP-7 USING ORIENTAL DRAGON | 2790-2792-NN-0087 |  |  | 2026-06-30 | REMARKS | [11 empty] | SERVER ONLY - NO FEEDBACK - 06/08
88 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 8" CC PIPES & MISC. ITEMS ON ASTRO-250 (TRIP-1) | 2790-2792-NN-0088 | A | 3 | 2026-06-30 | 2026-06-25 | CSE-2790-2792-PMT-T-062
|  |  | B | 3 |  | 2026-07-24 | CSE-2790-2792-PMT-T-068
89 | LIFTING AND INSTALLATION ARRANGEMENT DRAWING FOR 8IN F/L SPOOL AT ZTP-4 USING SWORDFISH | 2790-2792-NN-0089 |  |  | BINOY
90 | LIFTING AND INSTALLATION ARRANGEMENT DRAWING FOR 8IN F/L SPOOL AT ZTP-7 USING SWORDFISH | 2790-2792-NN-0090 |  |  | BINOY
91 | LIFTING AND INSTALLATION ARRANGEMENT DRAWING FOR 16IN F/L SPOOL AT ZTP-204/209 USING SWORDFISH | 2790-2792-NN-0091 |  |  | BINOY
92 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF HOOK UP SPOOLS ON SAFEEN B-283 | 2790-2792-NN-0092 | A | 3 | SSK | 2026-06-26 | CSE-2790-2792-PMT-T-064

## Sketches
Project 2790/2792(CRPO136 & 137)
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2792 | OFO-P2792-SK-T-001 | TEMPORARY QUADRANT ARRANGEMENT 0.8M RADIUS FOR 12-3/4" J-TUBE AT ZULF 510/519 | 2 + 34 | B, 0 | √ | √ | 2024-11-20 | SKS | @
2 | 2792 | OFO-P2792-SK-T-002 | TEMPORARY QUADRANT ARRANGEMENT 0.8M RADIUS FOR 10-3/4" ICCP J-TUBE AT ZULF TP-7 | 2 + 36 | B, 0 | √ | √ | 2024-11-20 | SKS | @
3 | 2792 | OFO-P2792-SK-T-003 | TEMPORARY QUADRANT ARRANGEMENT 0.8M RADIUS FOR 8-5/8" J-TUBE AT ZULF 510/519 | 2 + 36 | B, 0 | √ | √ | 2024-11-20 | SKS | @
4 | 2792 | OFO-P2792-SK-T-004 | TEMPORARY QUADRANT ARRANGEMENT 0.8M RADIUS FOR 8-5/8" J-TUBE AT ZULF 680/689 | 2 + 36 | B | √ | √ | 2024-11-20 | SKS | @
5 | 2792 | OFO-P2792-SK-T-005 | ICCP INSTALLATION AIDS - CABLE DRUM SUPPORT TRESTLE | 1 | B | √ | √ | 2024-11-20 | SKS | @
6 | 2792 | OFO-P2792-SK-T-006 | UMM SHAIF DECK LAYOUT DURING ICCP CABLE LAYING | 1 | B | √ | √ | 2024-10-03 | SHM | @
7 | 2792 | OFO-P2792-SK-T-007 | 15KV CABLE AND ICCP CABLE LOADING ARRANGEMENT | 1 | A | √ | √ | 2024-10-04 | CDG | @
8 | 2792 | OFO-P2792-SK-T-008 | ICCP INSTALLATION AIDS - ICCP ANODE CABLE TURNTABLE DETAILS | 1 | B | √ | √ | 2024-11-15 | SKS | @
9 | 2792 | OFO-P2792-SK-T-009 | ICCP INSTALLATION AIDS - PYRAMID ANODE LIFTING ARRANGEMENT (FOR CRPO-136) | 1 | B | √ | √ | 2024-11-15 | SKS | @
10 | 2792 | OFO-P2792-SK-T-010 | ICCP INSTALLATION AIDS - PYRAMID ANODE LIFTING ARRANGEMENT (17-SAMSS) | 1 | B | √ | √ | 2024-11-15 | SKS | @
11 | 2792 | OFO-P2792-SK-T-011 | ICCP INSTALLATION AIDS - PYRAMID ANODE LIFTING ARRANGEMENT | 1 | B | √ | √ | 2024-11-15 | SKS | @
12 | 2792 | OFO-P2792-SK-T-012 | ICCP INSTALLATION AIDS - ASSEMBLY HANDLING PALLET | 1 | C | √ | √ | 2025-02-03 | HZD | @
13 | 2792 | OFO-P2792-SK-T-013 | UMM SHAIF DECK LAYOUT DURING CABLE LAYING | 1 | A | √ | √ | 2024-10-15 | SKT | @
14 | 2792 | OFO-P2792-SK-T-014 | TYPICAL CABLE PULLING ARRANGEMENT AT PDM (TYPE-1) | 3 | C | √ | √ | 2025-03-07 | SKT | @
15 | 2792 | OFO-P2792-SK-T-015 | 3m RADIUS HALF MOON BEND RESTRICTOR FOR CABLE LAYING | 1 | A | √ | √ | 2024-11-25 | SKS | @
16 | 2792 | OFO-P2792-SK-T-016 | TEMPORARY QUADRANT ARRANGEMENT 1.3M RADIUS FOR J-TUBE (CABLE WITHOUT TENSION) | 2 | A | √ | √ | 2024-11-25 | SKS | @
17 | 2792 | OFO-P2792-SK-T-017 | TYPICAL BEACON SUPPORT ON MATTRESS FRAME | 1 | A | √ | √ | 2024-12-05 | CDG | @
18 | 2792 | OFO-P2792-SK-T-018 | BERGERON TIDE DECK LAYOUT FOR MATTRESS AND 20FT CONTAINER | 1 | A | √ | √ | 2024-01-29 | AKS | @
19 | 2792 | OFO-P2792-SK-T-019 | TYPICAL TUGGER SKID DETAILS FOR CABLE PULLING | 1 | B | √ | √ | 2025-03-17 | SKT | @
20 | 2792 | OFO-P2792-SK-T-020 | LIFTING ARRANGEMENT OF PALLET | 1 | A | √ | √ | 2025-02-03 | HZD | @
21 | 2792 | OFO-P2792-SK-T-021 | LIFTING ARRANGEMENT OF CABLE DRUM SUPPORT TRESTLE | 1 | A | √ | √ | 2025-01-31 | HZD | @
22 | 2792 | OFO-P2792-SK-T-022 | LIFTING ARRANGEMENT OF ICCP ANODE CABLE TURNTABLE | 1 | A | √ | √ | 2025-01-31 | HZD | @
23 | 2792 | OFO-P2792-SK-T-023 | TYPICAL LIFTING ARRANGEMENT FOR PYRAMID ANODE | 1 | A | √ | √ | 2025-01-31 | HZD | @
24 | 2792 | OFO-P2792-SK-T-024 | LIFTING ARRANGEMENT OF 1.3M RADIUS QUADRANT | 1 | A | √ | √ | 2025-01-31 | HZD | @
25 | 2792 | OFO-P2792-SK-T-025 | LIFTING ARRANGEMENT OF 0.8M RADIUS QUADRANT | 1 | A | √ | √ | 2025-01-31 | HZD | @
26 | 2792 | OFO-P2792-SK-T-026 | LIFTING ARRANGEMENT OF 3M RADIUS HALF MOON BEND RESTRICTOR | 1 | A | √ | √ | 2025-02-03 | HZD | @
27 | 2792 | OFO-P2792-SK-T-027 | TYPICAL CABLE PULLING ARRANGEMENTS AT ZTPS | 2 | A | √ | √ | 2025-10-10 | SKT | @
28 | 2792 | OFO-P2792-SK-T-028 | WELDMENT, OPEN BARGE THROUGH 8" | 1 | A | √ | √ | 2025-03-07 | CDG | @
29 | 2792 | OFO-P2792-SK-T-029 | SEAFASTENING ARRANGEMENT FOR DIVING EQUIPMENT ON UMM SHAIF | 2 | A | √ | √ | 2025-02-28 | SKS | @
30 | 2792 | OFO-P2792-SK-T-030 | INSTALLATION RIGGING FOR TURNING BOLLARD | 1 | A | √ | √ | 2025-04-08 | HZD | @
31 | 2792 | OFO-P2792-SK-T-031 | INSTALLATION RIGGING FOR SAND/CEMENT BAG | 1 | A | √ | √ | 2025-04-08 | HZD | @
32 | 2792 | OFO-P2792-SK-T-032 | LIFTING ARRANGEMENT DRAWING FOR PIPELINE TROUGH | 2 | A | √ | √ | 2025-04-08 | HZD | @
33 | 2792 | OFO-P2792-SK-T-033 | LIFTING ARRANGEMENT DRAWING FOR 8" PIPELINE START UP HEAD | 1 | A | √ | √ | 2025-04-10 | HZD | @
34 | 2792 | OFO-P2792-SK-T-034 | LIFTING ARRANGEMENT DRAWING FOR 8" PIPELINE LAYDOWN HEAD | 1 | C | √ | √ | 2025-09-29 | HZD | @
35 | 2792 | OFO-P2792-SK-T-035 | LIFTING ARRANGEMENT DRAWING FOR 8" PIPELINE EMERGENCY LAYDOWN HEAD | 1 | B | √ | √ | 2025-09-29 | HZD | @
36 | 2792 | OFO-P2792-SK-T-036 | GENERAL PIPELAY PROFILE | 1 | A | √ | √ | 2025-04-21 | HZD | @
37 | 2792 | OFO-P2792-SK-T-037 | DELAM-2000 START UP ARRANGEMENT FOR 8” F/L AT ZTP-7 | 1 | C | √ | √ | 2025-08-25 | LRA | @
38 | 2792 | OFO-P2792-SK-T-038 | LIFTING ARRANGEMENT DRAWING FOR 8" START-UP HEAD PIPELINE SECTION | 1 | B | √ | √ | 2025-09-29 | HZD | @
39 | 2792 | OFO-P2792-SK-T-039 | LIFTING ARRANGEMENT DRAWING FOR 8" LAYDOWN HEAD PIPELINE SECTION | 1 | B | √ | √ | 2025-09-29 | HZD | @
40 | 2792 | OFO-P2792-SK-T-040 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR 8" PIPE JOINTS BY DELMA-2000 (PORT SIDE) | 4 | B | √ | √ | 2025-07-16 | AMK | @ | T-005 - 16/07
41 | 2792 | OFO-P2792-SK-T-041 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR 8" PIPE JOINTS BY DELMA-2000 (STARBOARD SIDE) | 8 | B | √ | √ | 2025-07-16 | AMD | @ | T-005 - 16/07
42 | 2792 | OFO-P2792-SK-T-042 | DRIFT PIN FOR 8" 1500 FLANGE SIZE 1-5/8" | 1 | A | √ | √ | 2025-06-18 | VDA | @
43 | 2792 | OFO-P2792-SK-T-043 | FLANGE CATCHERS FOR 8" 3 1500 FLANGE SIZE 1-5/8" | 1 | A | √ | √ | 2025-06-18 | VDA | @
44 | 2792 | OFO-P2792-SK-T-044 | SPOOL FLANGE END PLATES WITH DIFFUSER ARRANGEMENT FOR 8" 1500 FLANGE | 1 | B | √ | √ | 2025-07-08 | VDA | @
45 | 2792 | OFO-P2792-SK-T-045 | DIFFUSER FOR FLOODING RISER & SPOOL | 1 | B | √ | √ | 2025-07-08 | VDA | @
46 | 2792 | OFO-P2792-SK-T-046 | LAYDOWN ARRANGEMENT FOR 8" F/L AT ZTP-4 | 1 | A | √ | √ | 2025-06-18 | HZD | @
47 | 2792 | OFO-P2792-SK-T-047 | CLAMP LIFTNG / RIGGING ARRANGEMET FOR CRPO TP-4 | 1 | A | √ | √ | 2025-07-01 | SKT | @
48 | 2792 | OFO-P2792-SK-T-048 | 8"PIPELINE-PIPE BUNK AND TRANSITION RING | 2 | A | √ | √ | 2025-05-23 | AMK | @
49 | 2792 | OFO-P2792-SK-T-049 | MATTRESS SEAFASTENING ON BURGERON TIDE | 1 + 2 | B, 0 | √ | √ | 2025-07-16 | AMK | @
50 | 2792 | OFO-P2792-SK-T-050 | PROTECTOR DETAILS FOR 30'' PIPELINE | 1 | A | √ | √ | 2025-06-25 | NAR | @
51 | 2792 | OFO-P2792-SK-T-051 | PROTECTOR DETAILS FOR 16'' PIPELINE | 1 | A | √ | √ | 2025-06-25 | NAR | @
52 | 2792 | OFO-P2792-SK-T-052 | PROTECTOR DETAILS FOR 10'' PIPELINE | 1 | A | √ | √ | 2025-06-25 | NAR | @
53 | 2792 | OFO-P2792-SK-T-053 | DETAILS OF TEMPORARY SUPPORT H-2500 | 1 | A | √ | √ | 2025-06-25 | NAR | @
54 | 2792 | OFO-P2792-SK-T-054 | CLAMP LIFTNG / RIGGING ARRANGEMET FOR CRPO TP-7 @ EL (-)34.400M | 1 | A | √ | √ | 2025-07-01 | SKT | @
55 | 2792 | OFO-P2792-SK-T-055 | INSTALLATION RIGGING FOR SAND/CEMENT BAG | 1 | A | √ | √ | 2025-07-07 | AMK | @ | T-005 - 16/07
56 | 2792 | OFO-P2792-SK-T-056 | TYPICAL RISER CLAMP LIFTNG / RIGGING ARRANGEMENT FOR TP3, TP-4 & TP-7 | 1 | A | √ | √ | 2025-07-28 | SKT | @
57 | 2792 | OFO-P2792-SK-T-057 | CLAMP LIFTING / RIGGING ARRANGEMENT FOR CRPO TP-7@EL(-)17.900M | 1 | A | √ | √ | 2025-07-01 | SKT | @
58 | 2792 | OFO-P2792-SK-T-058 | CLAMP LIFTNG / RIGGING ARRANGEMET FOR ZULF_294 CLAMP | 1 | C | √ | √ | 2025-08-14 | AMK | @
59 | 2792 | OFO-P2792-SK-T-059 | CLAMP LIFTNG / RIGGING ARRANGEMET FOR ZULF_TP5 CLAMP | 1 | A | √ | √ | 2025-07-02 | AMK | @
60 | 2792 | OFO-P2792-SK-T-060 | J-TUBE CLAMP LIFTNG / RIGGING ARRANGEMENT FOR ZULF_282 @ EL(-) 34.300M | 1 | A | √ | √ | 2025-07-01 | SKT | @
61 | 2792 | OFO-P2792-SK-T-061 | J-TUBE CLAMP LIFTNG / RIGGING ARRANGEMENT FOR ZULF_330 @ EL(-) 25.200M | 1 | A | √ | √ | 2025-07-01 | SKT | @
62 | 2792 | OFO-P2792-SK-T-062 | J-TUBE CLAMP LIFTNG / RIGGING ARRANGEMENT FOR ZULF_330 @ EL(-) 16.386M | 1 | B | √ | √ | 2025-07-27 | SKT | @
63 | 2792 | OFO-P2792-SK-T-063 | CLAMP LIFTNG / RIGGING ARRANGEMET FOR ZULF__294 CLAMP @ EL(-)16.900M | 1 | A | √ | √ | 2025-07-02 | AMK | @
64 | 2792 | OFO-P2792-SK-T-064 | DMA STEVSHARK ANCHOR SYSTEM | 1 | A | √ | √ | 2025-06-18 | SKT | @
65 | 2792 | OFO-P2792-SK-T-065 | SPARE
66 | 2792 | OFO-P2792-SK-T-066 | DRIFT PIN FOR 10" #1500 FLANGE SIZE 1-7/8" | 1 | A | √ | √ | 2025-09-19 | VDA | @
67 | 2792 | OFO-P2792-SK-T-067 | DRIFT PIN FOR 12" #1500 FLANGE SIZE 2" | 1 | A | √ | √ | 2025-09-19 | VDA | @
68 | 2792 | OFO-P2792-SK-T-068 | DRIFT PIN FOR 16" #1500 FLANGE SIZE 2 1/2" | 1 | A | √ | √ | 2025-09-19 | VDA | @
69 | 2792 | OFO-P2792-SK-T-069 | FLANGE CATCHERS FOR 10" #1500 FLANGE SIZE 1-7/8 | 1 | A | √ | √ | 2025-09-19 | VDA | @
70 | 2792 | OFO-P2792-SK-T-070 | FLANGE CATCHERS FOR 12" #1500 FLANGE SIZE 2" | 1 | A | √ | √ | 2025-09-19 | VDA | @
71 | 2792 | OFO-P2792-SK-T-071 | FLANGE CATCHERS FOR 16" #1500 FLANGE SIZE 2 1/2" | 1 | A | √ | √ | 2025-09-19 | VDA | @
72 | 2792 | OFO-P2792-SK-T-072 | SPOOL FLANGE END PLATES WITH DIFFUSER ARRANGEMENT FOR 10" #1500 FLANGE | 1 | A | √ | √ | 2025-09-19 | VDA | @
73 | 2792 | OFO-P2792-SK-T-073 | SPOOL FLANGE END PLATES WITH DIFFUSER ARRANGEMENT FOR 12" #1500 FLANGE | 1 | A | √ | √ | 2025-09-19 | VDA | @
74 | 2792 | OFO-P2792-SK-T-074 | SPOOL FLANGE END PLATES WITH DIFFUSER ARRANGEMENT FOR 16" #1500 FLANGE | 1 | A | √ | √ | 2025-09-19 | VDA | @
75 | 2792 | OFO-P2792-SK-T-075 | RISER CLAMP LIFTNG / RIGGING ARRANGEMENT FOR TP3 ON ROW-1 @ EL(-) 32.335M | 1 | A | √ | √ | 2025-07-08 | SKT | @
76 | 2792 | OFO-P2792-SK-T-076 | RISER CLAMP LIFTNG / RIGGING ARRANGEMENT FOR TP3 ON ROW-1 @ EL(-) 34.926M | 1 | A | √ | √ | 2025-07-08 | SKT | @
77 | 2792 | OFO-P2792-SK-T-077 | RISER CLAMP LIFTNG / RIGGING ARRANGEMENT FOR TP3 ON ROW-1 @ EL(-) 31.176M | 1 | A | √ | √ | 2025-07-08 | SKT | @
78 | 2792 | OFO-P2792-SK-T-078 | RISER CLAMP LIFTNG / RIGGING ARRANGEMENT FOR TP3 ON ROW-1 @ EL(-) 35.466M | 1 | A | √ | √ | 2025-07-08 | SKT | @
79 | 2792 | OFO-P2792-SK-T-079 | RISER CLAMP LIFTNG / RIGGING ARRANGEMENT FOR TP3 ON ROW-1 @ EL(-) 15.400M | 1 | A | √ | √ | 2025-07-07 | SKT | @
80 | 2792 | OFO-P2792-SK-T-080 | RISER CLAMP LIFTNG / RIGGING ARRANGEMENT FOR TP3 ON ROW-2 @ EL(-) 31.831M & EL(-)15.547M | 1 | A | √ | √ | 2025-07-28 | SKT | @
81 | 2792 | OFO-P2792-SK-T-081 | RISER CLAMP LIFTNG / RIGGING ARRANGEMENT FOR TP3 ON ROW-2 @ EL(-) 32.154M & EL(-)15.178M | 1 | A | √ | √ | 2025-07-28 | SKT | @
82 | 2792 | OFO-P2792-SK-T-082 | RISER CLAMP LIFTNG / RIGGING ARRANGEMENT FOR TP3 ON ROW-2 @ EL(-) 32.360M & EL(-) 14.900M | 1 | A | √ | √ | 2025-07-28 | SKT | @
83 | 2792 | OFO-P2792-SK-T-083 | LIFTING AND INSTALLATION TEMPORARY SUPPORT FOR 8”F/L PIPELINE AT GOSP-4 TP LAY-DOWN | 2 | B | √ | √ | 2025-07-04 | HZD | @
84 | 2792 | OFO-P2792-SK-T-084 | LIFTING AND INSTALLATION PIPELINE PROTECTOR FOR 8”F/L PIPELINE AT ZULF TP-7 START-UP | 2 | B | √ | √ | 2025-07-04 | HZD | @
85 | 2792 | OFO-P2792-SK-T-085 | SUPPORT FOR PIPE FACING MACHINE | 1 | A | √ | √ | 2025-07-31 | LEO | @
86 | 2792 | OFO-P2792-SK-T-086 | TYPICAL RISER CLAMP LIFTNG / RIGGING ARRANGEMENT FOR TP3 | 1 | A | √ | √ | 2025-07-28 | SKT | @
87 | 2792 | OFO-P2792-SK-T-087 | TYPICAL J-TUBE CLAMP LIFTNG / RIGGING ARRANGEMENT FOR ZULF_282 | 1 | A | √ | √ | 2025-08-05 | SKT | @
88 | 2792 | OFO-P2792-SK-T-088 | TYPICAL J-TUBE CLAMP LIFTNG / RIGGING ARRANGEMENT FOR ZULF_294, 330 & ZULF_TP5 | 1 | A | √ | √ | 2025-08-04 | SKT | @
89 | 2792 | OFO-P2792-SK-T-089 | CCC MARITIME-II DECK LAYOUT FOR ICCP CABLE LAYING AND ANODE INSTALLATION | 2 | A | √ | √ | 2025-08-21 | SHM | @
90 | 2792 | OFO-P2792-SK-T-090 | AIRBAGS DISTRIBUTION FOR PULL-IN OF 15kV FOR ZULF 500/509 & ZULF 680/689 AT ZTPS-2 | 1 | A | √ | √ | 2025-10-03 | CDG | @
91 | 2792 | OFO-P2792-SK-T-091 | 15kV CABLE STRAIGHTENING AT ZULF 500/509 PLATFORM | 1 | A | √ | √ | 2025-10-03 | SKS | @
92 | 2792 | OFO-P2792-SK-T-092 | TYPICAL HANGER CLAMP LIFTNG / RIGGING ARRANGEMENT FOR J-TUBES, TP4 & TP7 RISERS |  |  |  |  | 2025-10-07 | SKT
93 | 2792 | OFO-P2790-2792-SK-T-093 | DETAILS OF AIR BAG CONNECTION TO 15kV CABLE | 1 | A | √ | √ | 2025-10-23 | SKS | @
94 | 2792 | OFO-P2790-2792-SK-T-094 | TEMPORARY HANG OFF CLAMP FOR 8 INCH J-TUBE AT ZULF TPS2-500 | 1 | A | √ | √ | 2025-11-18 | Amith | @
95 | 2792 | OFO-P2790-2792-SK-T-095 | LOADING ARRANGEMENT OF CABLE REELS ON BARGE CB-V1 | 1 | A | √ | √ | 2025-11-21 | AMEER |  | SERVER ONLLY
96 | 2792 | OFO-P2790-2792-SK-T-096 | SHUJAA-2000 current deck layout for CRPO 136/137 Flex PL Laying | 14 | A | √ | √ | 2026-07-03 | LEO | @
97 | 2792 | OFO-P2790-2792-SK-T-097 | SAPURA 1200 – STINGER ROLLER SETTING | 1 | B |  | √ | 2025-12-12 | JH | @ | REV-A N/A
98 | 2792 | OFO-P2790-2792-SK-T-098 | SAPURA 1200 – VESSEL ROLLER SETTING | 1 | A | √ | √ | 2025-12-12 | JH
99 | 2792 | OFO-P2790-2792-SK-T-099 | SAPURA-1200 START UP ARRANGEMENT FOR 8" F/L AT ZTP-7 | 1 | A | √ | √ | 2025-12-16 | LEO | @
100 | 2792 | OFO-P2790-2792-SK-T-100 | PIPELAY PROFILE WITH STINGER - SAPURA 1200 | 1 | A | √ | √ | 2025-12-16 | LEO | @
101 | 2792 | OFO-P2790-2792-SK-T-101 | STANFORD HUDHUD CLASH CHECK AT ZULF-240//245 |  |  |  |  | 2025-12-16 | MF
102 | 2792 | OFO-P2790-2792-SK-T-102 | STANFORD HUDHUD CLASH CHECK AT ZULF -228/233 |  |  |  |  | 2025-12-16 | MF
103 | 2792 | OFO-P2790-2792-SK-T-103 | STANFORD HUDHUD CLASH CHECK AT ZULF -140/145 |  |  |  |  | 2025-12-16 | MF
104 | 2792 | OFO-P2790-2792-SK-T-104 | STANFORD HUDHUD CLASH CHECK AT ZULF -216/221 |  |  |  |  | 2025-12-16 | MF
105 | 2792 | OFO-P2790-2792-SK-T-105 | STANFORD HUDHUD CLASH CHECK AT ZULF -152/163 |  |  |  |  | 2025-12-16 | MF
106 | 2792 | OFO-P2790-2792-SK-T-106 | STINGER SECTION LAYOUT - SAPURA 1200 | 1 | A | √ | √ | 2025-12-17 | LEO | @
107 | 2792 | OFO-P2790-2792-SK-T-107 | FLUSHING EQUIPMENT LAYOUT O/B STANFORD HUDHUD | 1 | A | √ | √ | 2025-12-29 | AMT | @
108 | 2792 | OFO-P2790-2792-SK-T-108 | 15KV CABLE LOADING ARRANGEMENT FOR CRPO 136/137 2nd CAMPAIGN | 1 | G | √ | √ | 2026-05-15 | SSK | @ | REV-G - SERVER ONLY
109 | 2792 | OFO-P2790-2792-SK-T-109 | DIFFUSER (WITHOUT TANK) FOR FLOODING RISER | 1 | B | √ | √ | 2026-02-10 | SKS | @
110 | 2792 | OFO-P2790-2792-SK-T-110 | CHUANG LI DECK LAYOUT FOR JACKET INSTALLATION | 1 | A | √ | √ | 2026-02-13 | AMK |  | SERVER ONLLY
111 | 2792 | OFO-P2790-2792-SK-T-111 | DELMA-2000 DECK LAYOUT FOR JACKET INSTALLATION | 1 | A | √ | √ | 2026-02-10 | AMK |  | SERVER ONLLY
112 | 2792 | OFO-P2790-2792-SK-T-112 | BATTER GAUGE FOR J-TUBE & RISER CLAMP ALIGNMENT (1 : 8) | 1 | A | √ | √ | 2026-03-17 | AMITH | @
113 | 2792 | OFO-P2790-2792-SK-T-113 | BATTER GAUGE FOR J-TUBE & RISER CLAMP ALIGNMENT (1 : 8.5) | 1 | A | √ | √ | 2026-03-17 | AMITH | @
114 | 2792 | OFO-P2790-2792-SK-T-114 | BATTER GAUGE FOR J-TUBE & RISER CLAMP ALIGNMENT (1 : 16) | 1 | A | √ | √ | 2026-03-17 | AMITH | @
115 | 2792 | OFO-P2790-2792-SK-T-115 | ZAKHER PIONEER SET UP AT ZTP-3 | 2 | A | √ | √ | 2026-04-01 | SSK | @
116 | 2792 | OFO-P2790-2792-SK-T-116 | ZAKHER PIONEER SET UP AT Z-590 OPTION-1 & OPTION-2 | 2 | A | √ | √ | 2026-03-31 | SSK | @
117 | 2792 | OFO-P2790-2792-SK-T-117 | ZAKHER PIONEER SET UP AT Z-282 OPTION-1 & OPTION-2 | 4 | A | √ | √ | 2026-03-31 | SSK | @
118 | 2792 | OFO-P2790-2792-SK-T-118 | ZAKHER PIONEER SET UP AT ZULF TPS-4 OPTION-1 & OPTION-2 | 2 | A | √ | √ | 31/4/26 | SSK | @
119 | 2792 | OFO-P2790-2792-SK-T-119 | ZAKHER PIONEER SET UP AT ZULF TPS-2 OPTION-1 & OPTION-2 | 2 | A | √ | √ | 31/4/26 | SSK | @
120 | 2792 | OFO-P2790-2792-SK-T-120 | ZAKHER PIONEER SET UP AT ZULF 510/519 OPTION-1 & OPTION-2 | 2 | A | √ | √ | 31/4/26 | SSK | @
121 | 2792 | OFO-P2790-2792-SK-T-121 | ZAKHER PIONEER SET UP AT ZULF 480/489 OPTION-1 & OPTION-2 | 2 | A | √ | √ | 31/4/26 | SSK | @
122 | 2792 | OFO-P2790-2792-SK-T-122 | ZAKHER PIONEER SET UP AT ZULF 680/689 OPTION-1 & OPTION-2 | 2 | A | √ | √ | 31/4/26 | SSK | @
123 | 2792 | OFO-P2790-2792-SK-T-123 | ZAKHER PIONEER SET UP AT ZULF 500-509 OPTION-1 & OPTION-2 | 2 | A | √ | √ | 2026-03-30 | SSK | @
124 | 2792 | OFO-P2790-2792-SK-T-124 | CRPO 136-137 Spools and TP-3 risers Loading Arrangement & Sea fastening on CB-08 |  |  |  |  | 2026-04-20 | BINOY
125 | 2792 | OFO-P2790-2792-SK-T-125 | 8" PIPE FIELD JOINT - FLANGE AND STUD BOLT ARRANGEMENT | 2 | A | √ | √ | 2026-04-29 | SKS | @ | SERVER ONLLY
126 | 2792 | OFO-P2790-2792-SK-T-126 | 10" PIPE FIELD JOINT - FLANGE AND STUD BOLT ARRANGEMENT | 2 | A | √ | √ | 2026-04-29 | SKS | @ | SERVER ONLLY
127 | 2792 | OFO-P2790-2792-SK-T-127 | 12" PIPE FIELD JOINT - FLANGE AND STUD BOLT ARRANGEMENT | 2 | A | √ | √ | 2026-04-29 | SKS | @ | SERVER ONLLY
128 | 2792 | OFO-P2790-2792-SK-T-128 | 16" PIPE FIELD JOINT - FLANGE AND STUD BOLT ARRANGEMENT | 2 | A | √ | √ | 2026-04-29 | SKS | @ | SERVER ONLLY
129 | 2792 | OFO-P2790-2792-SK-T-129 | LOADOUT & SEA FASTENING OF CONCRETE MATTRESS ON AL MARJAN | 1 | A | √ | √ | 2026-05-19 | JF | @
130 | 2792 | OFO-P2790-2792-SK-T-130 | SPOOLS AND SHROUDS ON CB-08 |  |  |  |  | 2026-05-25 | BINOY
131 | 2792 | OFO-P2790-2792-SK-T-131 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR DEMOLISHED PIPE LINES BY SWORDFISH (PORT SIDE) |  |  |  |  | 2026-06-09 | BINOY
132 | 2792 | OFO-P2790-2792-SK-T-132 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR DEMOLISHED PIPE LINES BY SWORDFISH (STBD SIDE) |  |  |  |  | 2026-06-09 | BINOY
133 | 2792 | OFO-P2790-2792-SK-T-133 | ICCP INSTALLATION AIDS - PYRAMID ANODE LIFTING FRAME | 1 | A | √ | √ | 2026-07-04 | HZD | @
134 | 2792 | OFO-P2790-2792-SK-T-134 | 15kV TRANSPOOLING ARRANGEMENT AT JETTY (UMM SHAIF TO MILLENNIUM - 3) | 1 | A | √ | √ | 2026-07-02 | CDG | @ | SERVER ONLLY
135 | 2792 | OFO-P2790-2792-SK-T-135 | TYPICAL ARRANGEMENT FOR EXISTING PIPELINE TO BE DEMOLISHED AT CROSSING |  |  |  |  | 2026-07-07 | SRV
136 | 2792 | OFO-P2790-2792-SK-T-136 | SPOOL FABRICATION SADDEL SUPPORT FOR 16" SPOOL | 1 | A | √ | √ | 2026-08-06 | HZD | @ | SERVER ONLLY
137 | 2792 | OFO-P2790-2792-SK-T-137 | ZAKHER PIONEER SET UP AT ZULF Z-89/256 | 1 | A | √ | √ | 2026-07-29 | SSK | @ | SERVER ONLLY
138 | 2792 | OFO-P2790-2792-SK-T-138 | ZAKHER PIONEER SET UP AT ZULF Z-WELL-1 | 1 | A | √ | √ | 2026-07-29 | SSK | @ | SERVER ONLLY
139 | 2792 | OFO-P2790-2792-SK-T-139 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF TPS-1 | 1 | A | √ | √ | 2026-08-06 | SSK (SIVA) | @ | SERVER ONLLY
140 | 2792 | OFO-P2790-2792-SK-T-140 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF TPS-2 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
141 | 2792 | OFO-P2790-2792-SK-T-141 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF TPS-3 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
142 | 2792 | OFO-P2790-2792-SK-T-142 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF TP-3 (GOSP-3) | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
143 | 2792 | OFO-P2790-2792-SK-T-143 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF TP-4 (GOSP-4) | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
144 | 2792 | OFO-P2790-2792-SK-T-144 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF TP-7 | 3 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
145 | 2792 | OFO-P2790-2792-SK-T-145 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 25/30 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
146 | 2792 | OFO-P2790-2792-SK-T-146 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 110/121 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
147 | 2792 | OFO-P2790-2792-SK-T-147 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 122/127 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
148 | 2792 | OFO-P2790-2792-SK-T-148 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 140/145 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
149 | 2792 | OFO-P2790-2792-SK-T-149 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 146/151 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
150 | 2792 | OFO-P2790-2792-SK-T-150 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 152/163 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
151 | 2792 | OFO-P2790-2792-SK-T-151 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 216/221 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
152 | 2792 | OFO-P2790-2792-SK-T-152 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 228/233 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
153 | 2792 | OFO-P2790-2792-SK-T-153 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 240/245 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
154 | 2792 | OFO-P2790-2792-SK-T-154 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 282/293 | 2 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
155 | 2792 | OFO-P2790-2792-SK-T-155 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 294/301 | 2 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
156 | 2792 | OFO-P2790-2792-SK-T-156 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 330/338 | 2 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
157 | 2792 | OFO-P2790-2792-SK-T-157 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 360/369 | 2 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
158 | 2792 | OFO-P2790-2792-SK-T-158 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 480/489 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
159 | 2792 | OFO-P2790-2792-SK-T-159 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 490/499 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
160 | 2792 | OFO-P2790-2792-SK-T-160 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 500/509 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
161 | 2792 | OFO-P2790-2792-SK-T-161 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 510/519 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
162 | 2792 | OFO-P2790-2792-SK-T-162 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 590/599 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
163 | 2792 | OFO-P2790-2792-SK-T-163 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 680/689 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
164 | 2792 | OFO-P2790-2792-SK-T-164 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF 89/256 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
165 | 2792 | OFO-P2790-2792-SK-T-165 | ZAKHER PELICAN DURING BERTHING/MOORING AT ZULF Z-WELL-1 | 1 | A | √ | √ | 2026-08-06 | SSK | @ | SERVER ONLLY
166 | 2792 | OFO-P2790-2792-SK-T-166 | CRANE REACHABILITY AND CLASH STUDY FOR MAG CAPELLA AT ZTP-3 PLATFORM | 2 | A | √ | √ | 2026-08-19 | CDG | @
167 | 2792 | OFO-P2790-2792-SK-T-167 | CRANE REACHABILITY AND CLASH STUDY FOR MAG CAPELLA AT Z-590 PLATFORM | 1 | A | √ | √ | 2026-08-19 | CDG | @
168 | 2792 | OFO-P2790-2792-SK-T-168 | CRANE REACHABILITY AND CLASH STUDY FOR MAG CAPELLA AT Z-282 PLATFORM | 1 | A | √ | √ | 2026-08-19 | CDG | @
169 | 2792 | OFO-P2790-2792-SK-T-169 | LIFTING AND INSTALLATION OF ZTP-3 FLARE BRIDGE AND FLARE TOWER SPOOLS | 3 | A | √ | √ | 2026-08-26 | SSK | @
170 | 2792 | OFO-P2790-2792-SK-T-170 | 16" Z204/209 TIE IN SPOOL ON MAG CAPELLA |  |  |  |  | 2026-09-02 | SSK
171 | 2792 | OFO-P2790-2792-SK-T-171 | MAG ARISTON DURING BERTHING/MOORING AT ZTP-3 | 2 | A | √ | √ | 2026-09-09 | SSK | @
172 | 2792 | OFO-P2790-2792-SK-T-172 | MAG ARISTON DURING BERTHING/MOORING AT Z-590 | 2 | A | √ | √ | 2026-09-09 | SSK | @
173 | 2792 | OFO-P2790-2792-SK-T-173 | MAG ARISTON DURING BERTHING/MOORING AT Z-282 | 4 | A | √ | √ | 2026-09-09 | SSK | @
1 | 2790 | OFO-P2790--SK-T-001 | 25MT S.W.L. SPREADER BAR DETAILS | 1 + 4 | A, 0 | √ | √ | 2025-10-21 | SKT | @

## cutlists
Project 2790/2792(CRPO136 & 137)
CUT-LIST DRAWINGS
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2790-2792 | 2790-2792-NN-0009-CTL | START UP HEAD DETAILS FOR 8" PIPELINE (WITH CUTLIST 2 + 16 – REV-1) | 2 + 16 | 0 | √ | √ | 2025-03-14 | CSE-OF-2790-92-002 | @
|  |  |  | 2 + 16 | 1 | √ | √ | 2025-04-15 | CSE-OF-2790-92-003 | @
2 | 2790-2792 | 2790-2792-NN-0010-CTL | LAYDOWN HEAD DETAILS FOR 8" PIPELINE (WITH CUTLIST 2 + 20 – REV-0) | 2 + 20 | 0 | √ | √ | 2025-04-15 | CSE-OF-2790-92-003 | @
3 | 2790-2792 | 2790-2792-NN-0011-CTL | TYPICAL EMERGENCY LAYDOWN HEAD DETAILS FOR 8" PIPELINE (WITH CUTLIST 2 + 19 – REV-0) | 2 + 19 | 0 | √ | √ | 2025-04-15 | CSE-OF-2790-92-003 | @
4 | 2790-2792 | 2790-2792-NN-0059-CTL | FLANGE PROTECTOR DETAILS FOR 8" PIPELINE HEADS 25mm THK CONCRETE CUTLIST | 1 TO 9 | 0 | √ | √ | 2025-01-28 | CSE-OF-2790-92-001 | @
|  |  |  | 1 TO 8 | 1 | √ | √ | 2025-04-27 | CSE-OF-2790-92-004 | @
5 | 2790-2792 | 2790-2792-NN-0051-CTL | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 8” CC PIPES @ GAC-82 (TRIP-1) | 2 TO 8 | 0 | √ | √ | 2025-07-25 | DIRECT SENT | @ | Karthick
6 | 2790-2792 | 2790-2792-NN-0060-CTL | LOADING ARRANGEMENT & SEAFASTENING OF RISERS & SPOOLS & J-TUBES TRIP-1 WITH BALAST PLAN | 2 TO 20 | 0 | √ | √ | 2025-09-25 | DIRECT SENT | @ | Karthick
7 | 2790-2792 | OFO-P2792-SK-T-133-CTL | ICCP INSTALLATION AIDS - PYRAMID ANODE LIFTING FRAME | 1 + 15 | 0 | √ | √ | 2026-07-29 |  | @ | Karthick
8
9
10
11
12
13
14

## TN-PL
|  | Upgrade Zuluf AM Crude Platforms – Zuluf Package 3 ZTP-3 (CRPO 136) Upgrade Zuluf AM Crude Platforms – Zuluf Package 4 Subsea Cables & Flowlines (CRPO 137) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | CRPO#136 PACKAGE #4 -6511069591(OOK)/6511068664(IK)- ZULF AH WEST OIL FACILITIES BI-10-07868 CRPO#137 PACKAGE #5 6511069593(OOK)/6511068669(IK) - ZULF AH EAST OIL FACILITIES BI-10-07868 | [10 empty] | REVISION :
|  | OFFSHORE CONSTRUCTION ENGINEERING DELIVERABLES | [10 empty] | DATE :
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE# | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | 8IN PIPELINE START-UP ANALYSIS AT ZTP7 PLATFORM | 2790-TN-PL-001
2 | TN FOR 15 kV CABLE STRAIGHTENING ANALYSIS AT ZTPS-2 PLATFORM | 2790-TN-PL-002
3 | TN FOR 15 kV CABLE STRAIGHTENING ANALYSIS AT Z500-509 PLATFORM | 2790-TN-PL-003
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27

## TN-ST
|  | Upgrade Zuluf AM Crude Platforms – Zuluf Package 3 ZTP-3 (CRPO 136) Upgrade Zuluf AM Crude Platforms – Zuluf Package 4 Subsea Cables & Flowlines (CRPO 137) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | CRPO#136 PACKAGE #4 -6511069591(OOK)/6511068664(IK)- ZULF AH WEST OIL FACILITIES BI-10-07868 CRPO#137 PACKAGE #5 6511069593(OOK)/6511068669(IK) - ZULF AH EAST OIL FACILITIES BI-10-07868 | [10 empty] | REVISION :
|  | OFFSHORE CONSTRUCTION ENGINEERING DELIVERABLES | [10 empty] | DATE :
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE# | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 |  | 2790-TN-ST-001
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27

## TN-NA
|  | Upgrade Zuluf AM Crude Platforms – Zuluf Package 3 ZTP-3 (CRPO 136) Upgrade Zuluf AM Crude Platforms – Zuluf Package 4 Subsea Cables & Flowlines (CRPO 137) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | CRPO#136 PACKAGE #4 -6511069591(OOK)/6511068664(IK)- ZULF AH WEST OIL FACILITIES BI-10-07868 CRPO#137 PACKAGE #5 6511069593(OOK)/6511068669(IK) - ZULF AH EAST OIL FACILITIES BI-10-07868 | [10 empty] | REVISION :
|  | OFFSHORE CONSTRUCTION ENGINEERING DELIVERABLES | [10 empty] | DATE :
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE# | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 |  | 2790-TN-NA-001
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27