## Documents - Pipeline & Cable
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
ADNOC EPC for LZ HABSHAN UPPER RECOVERY LEKHWAIR+20 MPB PROJECT
|  | NPCC PROJECT NO. 2800 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPE STACKING ANALYSIS REPORT | 2800-NN-RP-001 | AD-27-PL-62839 | 1 |  | 2025-01-30 | 2025-01-20 | CSE-2800-PMT-T-001 | 2025-01-22 | 2800-NMDC-E-AO-PMT-T-00673 | 2025-03-27 | 11681-NMDC-T-1927 | 2
|  |  |  | 2 |  | 2025-05-24 | 2025-05-14 | CSE-2800-PMT-T-027 | 2025-05-16 | 2800-NMDC-E-AO-PMT-T-01174 | 2025-05-28 | 11681-NMDC-T-2267 | 2
2 | PIPELAY ANALYSIS REPORT FOR 10in WI-3 FROM ZK-47 TO ZK-372 | 2800-NN-RP-002 | AD-164-PL-62511 | 1 | 2 | 2025-06-23 | 2025-06-13 | CSE-2800-PMT-T-047 | 2025-06-16 | 2800-NMDC-E-AO-PMT-T-01332 | 2025-06-24 | 11681-NMDC-T-2427 | 2
|  |  |  | 2 | 2 | 2025-07-14 | 2025-07-04 | CSE-2800-PMT-T-059 | 2025-07-07 | 2800-NMDC-E-AO-PMT-T-01435 | 2025-07-14 | 11681-NMDC-T-2536 | 2
3 | PIPELAY ANALYSIS REPORT FOR 10in WI-4 FROM ZK-372 TO ZK-126.5/65 | 2800-NN-RP-003 | AD-313-PL-62514 | 1 | 2 | 2025-07-17 | 2025-07-07 | CSE-2800-PMT-T-060 | 2025-07-08 | 2800-NMDC-E-AO-PMT-T-01443 | 2025-07-23 | 11681-NMDC-T-2601 | 2
|  |  |  | 2 | 2 | 2025-08-08 | 2025-07-29 | CSE-2800-PMT-T-073 | 2025-07-29 | 2800-NMDC-E-AO-PMT-T-01536 | 2025-07-30 | 11681-NMDC-T-2649 | 2
|  |  |  | 3 | 2 | 2025-08-11 | 2025-08-01 | CSE-2800-PMT-T-078 | 2025-08-04 | 2800-NMDC-E-AO-PMT-T-01552
4 | PIPELAY ANALYSIS REPORT FOR 6in GL-1 FROM ZWSC GIP TO ZK-50 | 2800-NN-RP-004 | AD-447-PL-62518 | 1 | 2 | 2025-07-31 | 2025-07-21 | CSE-2800-PMT-T-069 | 2025-07-24 | 2800-NMDC-E-AO-PMT-T-01509 | 2025-07-31 | 11681-NMDC-T-2653 | 2
|  |  |  | 2 | 2 | 2025-09-01 | 2025-08-22 | CSE-2800-PMT-T-095 | 2025-08-25 | 2800-NMDC-E-AO-PMT-T-01667 | 2025-08-28 | 11681-NMDC-T-2789 | 2
5 | PIPELAY ANALYSIS REPORT FOR 6in GL-2 FROM ZK-50 TO ZK-43A | 2800-NN-RP-005 | AD-166-PL-62519 | 1 | 2 | 2025-08-25 | 2025-08-15 | CSE-2800-PMT-T-086 | 2025-08-25 | 2800-NMDC-E-AO-PMT-T-01674 | 2025-09-02 | 11681-NMDC-T-2813 | 2
6 | PIPELAY ANALYSIS REPORT FOR 6in GL-3 FROM ZK-43A TO ZK-45 | 2800-NN-RP-006 | AD-165-PL-62521 | 1 | 2 | 2025-09-16 | 2025-09-06 | CSE-2800-PMT-T-103 | 2025-09-08 | 2800-NMDC-E-AO-PMT-T-01775 | 2025-09-11 | 11681-NMDC-T-2853 | 3
|  |  |  | 2 | 2 | 2025-09-22 | 2025-09-12 | CSE-2800-PMT-T-110 | 2025-09-15 | 2800-NMDC-E-AO-PMT-T-01800 | 2025-09-17 | 11681-NMDC-T-2887 | 2
|  |  |  | 3 | 2 | 2025-09-28 | 2025-09-18 | CSE-2800-PMT-T-113 | 2025-09-19 | 2800-NMDC-E-AO-PMT-T-01827 | 2025-10-08 | 11681-NMDC-T-3001 | 2
7 | PIPELAY ANALYSIS REPORT FOR 6in GL-4 FROM ZK-45 TO ZK-56 | 2800-NN-RP-007 | AD-162-PL-62518 | 1 | 2 | 2026-02-23 | 2026-02-13 | CSE-2800-PMT-T-180 | 2026-02-16 | 2800-NMDC-E-AO-PMT-T-02434 | 2026-02-27 | 11681-NMDC-T-3394 | 3
|  |  |  | 2 | 2 | 2026-04-17 | 2026-04-07 | CSE-2800-PMT-T-203 | 2026-04-09 | 2800-NMDC-E-AO-PMT-T-02575 | 2026-04-27 | 11681-NMDC-T-3533 | 2
|  |  |  | 3 | 2 |  | 2026-08-08 | CSE-2800-PMT-T-247 | 2026-08-10 | 2800-NMDC-E-AO-PMT-T-02898
8 | WELD REPAIR ANALYSIS REPORT | 2800-NN-RP-008 | AD-27-PL-62840
9 | INSTALLATION ANALYSIS REPORT FOR 6.6KV CABLES | 2800-NN-RP-009 | AD-27-PL-62841 | 1 | 2 | 2025-09-22 | 2025-09-12 | CSE-2800-PMT-T-109 | 2025-09-15 | 2800-NMDC-E-AO-PMT-T-01804 | 2025-09-25 | 11681-NMDC-T-2938 | 2
|  |  |  | 2 | 2 | 2025-10-27 | 2025-10-17 | CSE-2800-PMT-T-125 | 2025-10-22 | 2800-NMDC-E-AO-PMT-T-01998 | 2025-11-12 | 11681-NMDC-T-3123 | 2
10 | RISER/SPOOL LIFTING ANALYSIS REPORT AT ZWSC-RP2 | 2800-NN-RP-010 | AD-447-PL-62519 |  |  | 2025-02-01
11 | RISER/SPOOL LIFTING ANALYSIS REPORT AT ZK-47 | 2800-NN-RP-011 | AD-164-PL-62512 | remarks |  | 2025-02-01 | [12 empty] | Hirash email dtd. 17/12/2025
12 | RISER/SPOOL LIFTING ANALYSIS REPORT AT ZK-372 | 2800-NN-RP-012 | AD-313-PL-62515 |  |  | 2025-02-01
13 | RISER AND SPOOL LIFTING ANALYSIS REPORT FOR GL-1 AT GIP | 2800-NN-RP-013 | AD-447-PL-62520 | 1 | 2 | 2026-02-20 | 2026-01-02 | CSE-2800-PMT-T-177 | 2026-01-04 | 2800-NMDC-E-AO-PMT-T-02398 | 2026-02-20 | 11681-NMDC-T-3385 | 1
|  |  |  | 2 | 2 |  | 2026-02-28 | CSE-2800-PMT-T-186 | 2026-03-06 | 2800-NMDC-E-AO-PMT-T-02484
14 | RISER AND SPOOL LIFTING ANALYSIS REPORT FOR GL-2 AT ZK-50 | 2800-NN-RP-014 | AD-166-PL-62520 | 1 | 2 | 2026-03-15 | 2026-03-13 | CSE-2800-PMT-T-192 | 2026-03-13 | 2800-NMDC-E-AO-PMT-T-02519 | 2026-03-25 | 11681-NMDC-T-3450 | 2
15 | RISER/SPOOL LIFTING ANALYSIS REPORT AT ZK-43A | 2800-NN-RP-015 | AD-165-PL-62522 |  |  | 2025-02-01
16 | RISER AND SPOOL LIFTING ANALYSIS FOR GL-3 AT ZK-45 | 2800-NN-RP-016 | AD-162-PL-62519 | 1 | 2 | 2026-05-05 | 2026-05-08 | CSE-2800-PMT-T-216 | 2026-05-11 | 2800-NMDC-E-AO-PMT-T-02673 | 2026-06-10 | 11681-NMDC-T-3615 | 4
17 | RISER/SPOOL LIFTING ANALYSIS REPORT AT ZK-372 | 2800-NN-RP-017 | AD-313-PL-62516 |  |  | 2025-02-01
18 | RISER/SPOOL LIFTING ANALYSIS REPORT AT ZK-126.5/65 | 2800-NN-RP-018 | AD-312-PL-62507 |  |  | 2025-02-01
19 | RISER AND SPOOL LIFTING ANALYSIS REPORT FOR GL-4 AT ZK-56 | 2800-NN-RP-019 | AD-168-PL-65001 |  | SM-02-09
20 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AT GAC-68 (TRIP-1) | 2800-NN-RP-020 | AD-27-PL-62842 | 1 |  | 2025-03-01 | 2025-02-11 | CSE-2800-PMT-T-002 | 2025-03-03 | 2800-NMDC-E-AO-PMT-T-00857 | 2025-05-19 | 11681-NMDC-T-2197 | 2
21 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES @ GAC-68 (TRIP-1) | 2800-NN-RP-021 | AD-27-PL-62843 | 1 | 2 | 2025-03-01 | 2025-06-23 | CSE-2800-PMT-T-050 | 2025-06-25 | 2800-NMDC-E-AO-PMT-T-01371 | 2025-07-11 | 11681-NMDC-T-2528 | 4
22 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF RISERS & SPOOLS (TRIP-1) | 2800-NN-RP-022 | AD-27-PL-62844 | 1 | 2 | 2025-05-01 | 2025-12-03 | CSE-2800-PMT-T-139 | 2025-12-04 | 2800-NMDC-E-AO-PMT-T-02173 | 2025-12-11 | 11681-NMDC-T-3204 | 4
23 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF RISERS & SPOOLS@ ELISSA (TRIP-2) | 2800-NN-RP-023 | AD-27-PL-62845 | 1 | 2 | 2025-05-01 |  | register updated SM 6/4/2026
24 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AT ES-281 (TRIP-1) | 2800-NN-RP-024 | AD-27-PL-62846 | 1 | 2 | 2025-01-15 | 2025-04-17 | CSE-2800-PMT-T-016 | 2025-04-19 | 2800-NMDC-E-AO-PMT-T-01039 | 2025-05-19 | 11681-NMDC-T-2197 | 2
25 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS - TRIP-2 | 2800-NN-RP-025 | AD-27-PL-62847 | 1 | 2 | 2025-01-15 | 2025-05-07 | CSE-2800-PMT-T-020 | 2025-05-14 | 2800-NMDC-E-AO-PMT-T-01146 | 2025-06-03 | 11681-NMDC-T-2291 | 2 | [5 empty] | No don’t submit to client Methods will revise it with after changing the cargo barge -Muhammed Hirash (DC)email dtd.09/04 | mail from Ahmos Elsaggan
|  |  |  | 2 | 2 |  | 2025-06-11 | CSE-2800-PMT-T-046 | 2025-06-16 | 2800-NMDC-E-AO-PMT-T-01340 | 2025-07-02 | 11681-NMDC-T-2467 | 2
|  |  |  | 3 | 2 |  | 2025-09-16 | CSE-2800-PMT-T-106 | 2025-09-17 | 2800-NMDC-E-AO-PMT-T-01811 | 2026-04-10 | 11681-NMDC-T-3478 | 4
26 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF MATTRESSES AND SPOOL ON AL JABER-34 | 2800-NN-RP-026 | AD-27-PL-62848 | 1 | 2 | 2025-01-15 | 2025-11-20 | CSE-2800-PMT-T-142 | 2025-11-20 | 2800-NMDC-E-AO-PMT-T-02137 | 2026-04-21 | 11681-NMDC-T-3523 | 4
|  |  |  | 2 | 2 |  | 2026-02-25 | CSE-2800-PMT-T-185 | 2026-02-26 | 2800-NMDC-E-AO-PMT-T-02473 | 2026-04-10 | 11681-NMDC-T-3478 | 4
27 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE MATTRESSES ON GAC-68 | 2800-NN-RP-027 | AD-27-PL-62849 | 1 | 2 |  | 2026-09-04 | CSE-2800-PMT-T-253 | 2026-09-07 | 2800-NMDC-E-AO-PMT-T-02945
28 | DAVIT LIFT ANALYSIS REPORT FOR 6in GL-1 FROM ZWSC GIP TO ZK-50 | 2800-NN-RP-028 | AD-447-PL-62524 | 1 | 2 | 2025-12-28 | 2025-12-18 | CSE-2800-PMT-T-155 | 2025-12-19 | 2800-NMDC-E-AO-PMT-T-02234 | 2026-01-13 | 11681-NMDC-T-3291 | 3
|  |  |  | 2 | 2 | 2026-02-13 | 2026-02-03 | CSE-2800-PMT-T-178 | 2026-02-04 | 2800-NMDC-E-AO-PMT-T-02401 | 2026-02-10 | 11681-NMDC-T-3362 | 2
|  |  |  | 3 | 2 | 2026-03-23 | 2026-03-13 | CSE-2800-PMT-T-194 | 2026-03-16 | 2800-NMDC-E-AO-PMT-T-02522 | 2026-03-26 | 11681-NMDC-T-3453 | 2
|  |  |  | 4 | 3 |  | 2026-07-06 | CSE-2800-PMT-T-233 | 2026-07-07 | 2800-NMDC-E-AO-PMT-T-02822
29 | DAVIT LIFT ANALYSIS REPORT FOR 6in GL-2 FROM ZK-50 TO ZK-43A | 2800-NN-RP-029 | AD-166-PL-62523 | 1 | 2 | 2025-10-27 | 2025-10-17 | CSE-2800-PMT-T-124 | 2025-10-18 | 2800-NMDC-E-AO-PMT-T-01988 | 2025-10-28 | 11681-NMDC-T-3075 | 2
|  |  |  | 2 | 2 | 2025-11-14 | 2025-11-04 | CSE-2800-PMT-T-134 | 2025-11-06 | 2800-NMDC-E-AO-PMT-T-02076 | 2025-11-26 | 11681-NMDC-T-3167 | 2
|  |  |  | 3 | 3 | 2026-01-05 | 2025-12-26 | CSE-2800-PMT-T-161 | 2025-12-30 | 2800-NMDC-E-AO-PMT-T-02246 | 2026-01-05 | 11681-NMDC-T-3263 | 2
|  |  |  | 4 | 3 | 2026-01-15 | 2026-01-05 | CSE-2800-PMT-T-166 | 2026-01-06 | 2800-NMDC-E-AO-PMT-T-02283 | 2026-01-07 | 11681-NMDC-T-3272 | 2
|  |  |  | 5 | 3 | 2026-03-17 | 2026-03-07 | CSE-2800-PMT-T-189 | 2026-03-11 | 2800-NMDC-E-AO-PMT-T-02499 | 2026-03-23 | 11681-NMDC-T-3443 | 2
|  |  |  | 6 | 3 |  | 2026-07-06 | CSE-2800-PMT-T-234 | 2026-07-07 | 2800-NMDC-E-AO-PMT-T-02823
30 | DAVIT LIFT ANALYSIS REPORT FOR 6in GL-3 FROM ZK-43A TO ZK-45 | 2800-NN-RP-030 | AD-165-PL-62525 | 1 | 2 | 2025-10-10 | 2025-09-30 | CSE-2800-PMT-T-116 | 2025-10-02 | 2800-NMDC-E-AO-PMT-T-01904 | 2025-10-14 | 11681-NMDC-T-3020 | 2
|  |  |  | 2 | 2 | 2025-12-07 | 2025-11-27 | CSE-2800-PMT-T-147 | 2025-11-28 | 2800-NMDC-E-AO-PMT-T-02167 | 2025-12-08 | 11681-NMDC-T-3192 | 2
|  |  |  | 3 | 3 | 2026-05-17 | 2026-05-07 | CSE-2800-PMT-T-214 | 2026-05-08 | 2800-NMDC-E-AO-PMT-T-02668 | 2026-05-01 | 11681-NMDC-T-3592 | 3 |  |  | 2026-06-01 | 11681-NMDC-T-3592 | CODE-3
|  |  |  | CRS |  |  | 2026-07-13 | CSE-2800-PMT-T-235 | [10 empty] | CRS SENT TO PMT
|  |  |  | 4 | 3 |  | 2026-07-31 | CSE-2800-PMT-T-244 | 2026-07-31 | 2800-NMDC-E-AO-PMT-T-02878 | 2026-08-19 | 11681-NMDC-T-3741 | 2
31 | DAVIT LIFT ANALYSIS REPORT FOR 6in GL-4 FROM ZK-45 TO ZK-56 | 2800-NN-RP-031 | AD-162-PL-62522 | 1 | 2 | 2026-08-10 | 2026-07-31 | CSE-2800-PMT-T-245 | 2026-07-31 | 2800-NMDC-E-AO-PMT-T-02880
32 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS - TRIP-3 | 2800-NN-RP-032 | AD-27-PL-63293 | 1 | 2 | 2025-04-24 | 2025-04-14 | CSE-2800-PMT-T-015 | 2025-04-15 | 2800-NMDC-E-AO-PMT-T-01030 | 2025-04-24 | 11681-NMDC-T-2054 | 2
33 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS @ES-281 TRIP-4 | 2800-NN-RP-033 | AD-27-PL-63294 | 1 | 2 | 2026-01-15 | 2025-06-20 | CSE-2800-PMT-T-052 | 2025-06-21 | 2800-NMDC-E-AO-PMT-T-01364 | 2025-07-11 | 11681-NMDC-T-2528 | 2
|  |  |  | 2 | 2 |  | 2026-01-15 | CSE-2800-PMT-T-167 | 2026-01-16 | 2800-NMDC-E-AO-PMT-T-02305 | 2026-01-21 | 11681-NMDC-T-3301 | 4
34 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF GL-4 CONCRETE SLEEPERS (TRIP 2) | 2800-NN-RP-034 | AD-27-PL-63295 | 1 | 2 | 2026-07-01 | 2026-07-24 | CSE-2800-PMT-T-242 | 2026-07-27 | 2800-NMDC-E-AO-PMT-T-02871
35 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS - TRIP-6 | 2800-NN-RP-035 | AD-27-PL-63296 | 1 | 2 | 2025-07-01 | 2025-07-03 | CSE-2800-PMT-T-057 | 2025-07-04 | 2800-NMDC-E-AO-PMT-T-01426 | 2025-07-24 | 11681-NMDC-T-2618 | 2
36 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS - TRIP-7 | 2800-NN-RP-036 | AD-27-PL-63297 |  |  | 2027-01-01
37 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS - TRIP-8 | 2800-NN-RP-037 | AD-27-PL-63298 |  |  | 2027-01-01
38 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES AND FOAM FLOATERS ON ES-282 | 2800-NN-RP-038 | AD-27-PL-63299 | 1 | 2 | 2026-09-01 | 2026-09-01 | CSE-2800-PMT-T-252 | 2026-09-02 | 2800-NMDC-E-AO-PMT-T-02927
39 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-4) | 2800-NN-RP-039 | AD-27-PL-63300 |  |  | 2026-07-10
40 | DAVIT LIFT ANALYSIS REPORT FOR 10in WI-3 FROM ZK-47 TO ZK-372 | 2800-NN-RP-040 | AD-164-PL-62516 | 1 | 2 | 2025-11-17 | 2025-11-07 | CSE-2800-PMT-T-136 | 2025-11-10 | 2800-NMDC-E-AO-PMT-T-02085 | 2025-11-26 | 11681-NMDC-T-3167 | 2
41 | DAVIT LIFT ANALYSIS REPORT FOR 10in WI-4 FROM ZK-372 TO ZK-126.5/65 | 2800-NN-RP-041 | AD-313-PL-62520 | 1 | 2 | 2025-11-03 | 2025-10-24 | CSE-2800-PMT-T-128 | 2025-10-25 | 2800-NMDC-E-AO-PMT-T-01972 | 2025-10-30 | 11681-NMDC-T-3087 | 2
|  |  |  | 2 | 2 | 2025-11-14 | 2025-11-04 | CSE-2800-PMT-T-133 | 2025-11-06 | 2800-NMDC-E-AO-PMT-T-02075 | 2025-11-26 | 11681-NMDC-T-3167 | 1
42 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF 6" CC PIPES @ ES-281 TRIP-1 | 2800-NN-RP-042 | AD-27-PL-63478 | 1 | 2 | 2026-07-30 | 2025-07-29 | CSE-2800-PMT-T-074 | 2025-07-31 | 2800-NMDC-E-AO-PMT-T-01541 | 2025-09-03 | 11681-NMDC-T-2825 | 2
|  |  |  | 2 | 2 |  | 2025-08-12 | CSE-2800-PMT-T-083 | 2025-08-14 | 2800-NMDC-E-AO-PMT-T-01609 | 2025-09-03 | 11681-NMDC-T-2825 | 2
43 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE BLOCKS | 2800-NN-RP-043 | AD-27-PL-63479 | 1 | 2 | 2025-08-25 | 2025-08-04 | CSE-2800-PMT-T-079 | 2025-08-08 | 2800-NMDC-E-AO-PMT-T-01593 | 2026-04-21 | 11681-NMDC-T-3523 | 4
44 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF 6" CC PIPES @ GAC-68 TRIP-2 | 2800-NN-RP-044 | AD-27-PL-63481 | 1 | 2 | 2025-08-25 | 2025-08-22 | CSE-2800-PMT-T-096 | 2025-08-25 | 2800-NMDC-E-AO-PMT-T-01671 | 2025-12-16 | 11681-NMDC-T-3219 | 4
45 | RISER/SPOOL LIFTING ANALYSIS AT ZK-43A | 2800-NN-RP-045 | AD-165-PL-62528
46 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF 6" CC PIPES (GL-4) AT ES-281 (TRIP-1) | 2800-NN-RP-046 | AD-27-PL-63510 | 1 | 2 | 2025-09-25 | 2025-09-16 | CSE-2800-PMT-T-111 | 2025-09-17 | 2800-NMDC-E-AO-PMT-T-01814 | 2026-01-14 | 11681-NMDC-T-3292 | 3
47 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SELEEPERS AT ES-281 (TRIP-3) | 2800-NN-RP-047 | AD-27-PL-63538 | 1 | 2 | 2026-02-05 | 2025-09-17 | CSE-2800-PMT-T-107 | 2025-09-19 | 2800-NMDC-E-AO-PMT-T-01825 | 2026-01-30 | 11681-NMDC-T-3333 | 4
|  |  |  | 2 | 2 |  | 2025-10-23 | CSE-2800-PMT-T-126 | 2025-10-24 | 2800-NMDC-E-AO-PMT-T-02011 | 2026-01-30 | 11681-NMDC-T-3333 | 4
|  |  |  | 3 | 2 |  | 2026-01-28 | CSE-2800-PMT-T-174 | 2026-01-29 | 2800-NMDC-E-AO-PMT-T-02361 | 2026-02-20 | 11681-NMDC-T-3385 | 4
48 | SEAFASTENING DESIGN REPORT FOR ZK-280 DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA 402 | 2800-NN-RP-048 | AD-306-PL-62504 | 1 | 2 | 2025-10-10 | 2025-10-10 | CSE-2800-PMT-T-119 | 2025-10-13 | 2800-NMDC-E-AO-PMT-T-01952 | 2025-12-11 | 11681-NMDC-T-3201 | 2
49 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF ZK-43A DECK EXTENSION ON MUTAWA 402 (TRIP-1) | 2800-NN-RP-049 | AD-165-PL-62530 |  |  | 2027-01-01
50 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF ZK-43A DECK EXTENSION ON GMS ARTEMIS (TRIP-1) | 2800-NN-RP-050 | AD-165-PL-62531 |  |  | 2027-01-01
51 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF ZK-43A DECK EXTENSION ON MUTAWA 402 (TRIP-2) | 2800-NN-RP-051 | AD-165-PL-62532 |  |  | 2027-01-01
52 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF ZK-43A DECK EXTENSION ON GMS ARTEMIS (TRIP-2) | 2800-NN-RP-052 | AD-165-PL-62533 |  |  | 2027-01-01
53 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF ZK-43A DECK EXTENSION ON MUTAWA 402 (TRIP-3) | 2800-NN-RP-053 | AD-165-PL-62534 |  |  | 2027-01-01
54 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF ZK-43A DECK EXTENSION ON GMS ARTEMIS (TRIP-3) | 2800-NN-RP-054 | AD-165-PL-62535 |  |  | 2027-01-01
55 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF ZK-43A DECK EXTENSION ON MUTAWA 402 (TRIP-5) | 2800-NN-RP-055 | AD-165-PL-62536 |  |  | 2027-01-01
56 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF ZK-43A DECK EXTENSION ON GMS ARTEMIS (TRIP-5) | 2800-NN-RP-056 | AD-165-PL-62537 |  |  | 2027-01-01
57 | AIR BAG LIFT ANALYSIS REPORT FOR 6in GL-2 FROM ZK-50 TO ZK-43A | 2800-NN-RP-057 | AD-166-PL-62532 | 1 | 2 | 2025-11-29 | 2025-11-19 | CSE-2800-PMT-T-140 | 2025-11-19 | 2800-NMDC-E-AO-PMT-T-02131 | 2025-11-28 | 11681-NMDC-T-3176 | 3
|  |  |  | 2 | 2 | 2025-12-29 | 2025-12-19 | CSE-2800-PMT-T-156 | 2025-12-22 | 2800-NMDC-E-AO-PMT-T-02235 | 2025-12-26 | 11681-NMDC-T-3247 | 3
|  |  |  | 3 | 2 | 2026-03-05 | 2026-02-23 | CSE-2800-PMT-T-184 | 2026-02-26 | 2800-NMDC-E-AO-PMT-T-02467 | 2026-03-16 | 11681-NMDC-T-3429 | 2
58 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF MATTRESSES ON ES-282 | 2800-NN-RP-058 | AD-27-PL-63611 | 1 | 2 | 2026-09-01 | 2026-08-25 | CSE-2800-PMT-T-251 | 2026-08-27 | 2800-NMDC-E-AO-PMT-T-02929
59 | RECTIFICATION ANALYSIS REPORT FOR 6.6KV CABLES | 2800-NN-RP-059 | AD-27-Z-80506 | 1 | 2 | 2026-01-16 | 2026-03-17 | CSE-2800-PMT-T-195 | 2026-03-18 | 2800-NMDC-E-AO-PMT-T-02532 | 2026-04-01 | 11681-NMDC-T-3461 | 2
60 | RISER AND SPOOL LIFTING ANALYSIS REPORT FOR GL-1 AT ZK-50 | 2800-NN-RP-060 | AD-166-Z-80005 | 1 | 2 | 2026-03-21 | 2026-03-24 | CSE-2800-PMT-T-198 | 2026-03-25 | 2800-NMDC-E-AO-PMT-T-02541 | 2026-04-10 | 11681-NMDC-T-3478 | 2
61 | AIR BAG LIFT ANALYSIS REPORT FOR 10in WI-4 FROM ZK-372 TO ZK-126.5/65 | 2800-NN-RP-061 | AD-313-Z-80004 | 1 | 2 | 2026-05-24 | 2026-05-14 | CSE-2800-PMT-T-218 | 2026-05-15 | 2800-NMDC-E-AO-PMT-T-02692 | 2026-06-05 | 11681-NMDC-T-3608 | 2
62 | SEAFASTENING DESIGN REPORT OF ZK-50 DECK EXTENSION MODULES ON GMS ARTEMIS (TRIP-2) | 2800-NN-RP-062 | AD-166-Z-80008
63 | SEAFASTENING DESIGN REPORT OF ZK-50 DECK EXTENSION MODULES ON MUTAWA-402 (TRIP-3) | 2800-NN-RP-063 | AD-166-Z-80009
64 | LOWER ZAKUM - RISER AND SPOOL LIFTING ANALYSIS REPORT FOR GL-4 AT ZK-45. | 2800-NN-RP-064 | AD-162-Z-80014 | 1 | 2 |  | 2026-07-22 | CSE-2800-PMT-T-239 | 2026-07-23 | 2800-NMDC-E-AO-PMT-T-02861
65 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOL AND GRAVITY ANCHOR AT ES-281 | 2800-NN-RP-065 | AD-27-Z-80718 | 1 | 2 |  | 2026-08-04 | CSE-2800-PMT-T-246 | 2026-08-04 | 2800-NMDC-E-AO-PMT-T-02888
66 | SEAFASTENING DESIGN REPORT OF ZCSC/NWIP DECK EXTENSION MODULES ON MUTAWA-402 (TRIP-1) | 2800-NN-RP-066 | AD-463-Z-80019 | SM
67 | SEAFASTENING DESIGN REPORT OF ZCSC/NWIP DECK EXTENSION MODULES ON GMS ARTEMIS (TRIP-1) | 2800-NN-RP-067 | TBA
68 | SEAFASTENING DESIGN REPORT OF ZCSC/NWIP DECK EXTENSION MODULES ON MUTAWA-402 (TRIP-5) | 2800-NN-RP-068 | AD-463-Z-80020 | SM
69 | SEAFASTENING DESIGN REPORT OF ZCSC/NWIP DECK EXTENSION MODULES ON GMS ARTEMIS (TRIP-5) | 2800-NN-RP-069 | TBA
70 | SEAFASTENING DESIGN REPORT OF ZCSC/NWIP DECK EXTENSION MODULES ON GMS ARTEMIS (TRIP-6) | 2800-NN-RP-070 | AD-165-Z-80015 | SM
71 | SEAFASTENING DESIGN REPORT OF ZCSC/NWIP DECK EXTENSION MODULES ON GMS ARTEMIS (TRIP-8) | 2800-NN-RP-071 | AD-165-Z-80016 | SM
72 | RISER AND SPOOL LIFTING ANALYSIS REPORT FOR GL-4 AT ZK-56 | 2800-NN-RP-072 | TBA | SM
73 | SEAFASTENING DESIGN REPORT OF ZK-50 DECK EXTENSION MODULES ON MUTAWA-402 (TRIP-2) | 2800-NN-RP-073 | TBA | SM

## Documents - Naval Marine
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
ADNOC EPC for LZ HABSHAN UPPER RECOVERY LEKHWAIR+20 MPB PROJECT
|  | NPCC PROJECT NO. 2800 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | BERTHING ANALYSIS FOR WORKBOATS | 2800-ZZ-CL-001 | AD-27-PL-62850 |  |  | 2027-01-01
2 | MOORING ANALYSIS DURING PIPELAYING OF 10in WI-3 FROM ZK-47 TO ZK-372 (PL-1) | 2800-ZZ-CL-002 | AD-164-PL-62513 | 1 | 2 | 2025-04-14 | 2025-05-27 | CSE-2800-PMT-T-035 | 2025-05-27 | 2800-NMDC-E-AO-PMT-T-01228 | 2025-05-28 | 11681-NMDC-T-2266 | 3
|  |  |  | 2 | 2 |  | 2025-06-04 | CSE-2800-PMT-T-040 | 2025-06-11 | 2800-NMDC-E-AO-PMT-T-01284 | 2025-06-11 | 11681-NMDC-T-2397 | 4
3 | MOORING ANALYSIS DURING PIPELAYING OF 10in WI-4 FROM ZK-126.5/65 TO ZK-372 | 2800-ZZ-CL-003 | AD-313-PL-62517 | 1 | 2 | 2025-04-18 | 2025-06-18 | CSE-2800-PMT-T-049 | 2025-06-19 | 2800-NMDC-E-AO-PMT-T-01355 | 2025-07-01 | 11681-NMDC-T-2462 | 4
|  |  |  | 2 | 2 |  | 2025-07-26 | CSE-2800-PMT-T-072 | 2025-07-29 | 2800-NMDC-E-AO-PMT-T-01531 | 2025-07-30 | 11681-NMDC-T-2645 | 4
4 | MOORING ANALYSIS DURING PIPELAYING OF 6in GL-1 FROM ZWSC GIP TO ZK-50 (PL-3) | 2800-ZZ-CL-004 | AD-447-PL-32521 | 1 | 2 | 2025-04-22 | 2025-07-01 | CSE-2800-PMT-T-055 | 2025-07-01 | 2800-NMDC-E-AO-PMT-T-01411 | 2025-08-25 | 11681-NMDC-T-2764 | 4
5 | MOORING ANALYSIS DURING PIPELAYING OF 6in GL-2 FROM ZK-50 TO ZK-43A (PL-4) | 2800-ZZ-CL-005 | AD-166-PL-62521 | 1 | 2 | 2025-05-01 | 2025-07-09 | CSE-2800-PMT-T-062 | 2025-07-09 | 2800-NMDC-E-AO-PMT-T-01452 | 2025-08-11 | 11681-NMDC-T-2701 | 3
|  |  |  | 2 | 2 |  | 2025-08-15 | CSE-2800-PMT-T-087 | 2025-08-19 | 2800-NMDC-E-AO-PMT-T-01634 | 2025-09-02 | 11681-NMDC-T-2809 | 4
6 | MOORING ANALYSIS DURING PIPELAYING OF 6in GL-3 FROM ZK-43A TO ZK-45 (PL-5) | 2800-ZZ-CL-006 | AD-165-PL-62523 | 1 | 2 | 2025-02-15 | 2025-07-09 | CSE-2800-PMT-T-062 | 2025-07-09 | 2800-NMDC-E-AO-PMT-T-01453 | 2025-08-11 | 11681-NMDC-T-2701 | 3
|  |  |  | 2 | 2 |  | 2025-08-15 | CSE-2800-PMT-T-088 | 2025-08-18 | 2800-NMDC-E-AO-PMT-T-01629 | 2025-09-15 | 11681-NMDC-T-2874 | 4
7 | MOORING ANALYSIS DURING PIPELAYING OF 6in GL-4 FROM ZK-45 TO ZK-56 (PL-6) | 2800-ZZ-CL-007 | AD-162-PL-62520 | 1 | 2 | 2025-02-15 | 2025-07-31 | CSE-2800-PMT-T-076 | 2025-08-01 | 2800-NMDC-E-AO-PMT-T-01549 | 2025-09-16 | 11681-NMDC-T-2885 | 4
|  |  |  | 2 | 2 |  | 2026-08-17 | CSE-2800-PMT-T-248 | 2026-08-18 | 2800-NMDC-E-AO-PMT-T-02912
8 | MOORING ANALYSIS DURING RISER/SPOOL INSTALLATION OF GL-1 AT ZWSC-GIP | 2800-ZZ-CL-008 | AD-447-PL-62522 | 1 | 2 | 2025-06-01 | 2025-08-28 | CSE-2800-PMT-T-098 | 2025-08-28 | 2800-NMDC-E-AO-PMT-T-01688 | 2025-09-16 | 11681-NMDC-T-2885 | 4
|  |  |  | 2 | 2 | 2025-09-06 | 2025-09-06 | CSE-2800-PMT-T-102 | 2025-09-17 | 2800-NMDC-E-AO-PMT-T-01821 | 2025-09-19 | 11681-NMDC-T-2899 | 4
|  |  |  | 3 | 2 | 2026-02-20 | 2026-02-19 | CSE-2800-PMT-T-182 | 2026-02-21 | 2800-NMDC-E-AO-PMT-T-02454 | 2026-03-25 | 11681-NMDC-T-3450 | 2
9 | MOORING ANALYSIS DURING WI-3 PIPELINE SHIFTING AT ZK-47 | 2800-ZZ-CL-009 | AD-164-PL-62514 | 1 | 2 | 2025-04-15 | 2025-07-10 | CSE-2800-PMT-T-065 | 2025-07-11 | 2800-NMDC-E-AO-PMT-T-01460 | 2025-09-16 | 11681-NMDC-T-2885 | 4
10 | MOORING ANALYSIS DURING WI-4 PIPELINE SHIFTING AT ZK-372 | 2800-ZZ-CL-010 | AD-313-PL-62518 | 1 | 2 | 2025-04-15 | 2025-07-10 | CSE-2800-PMT-T-067 | 2025-07-12 | 2800-NMDC-E-AO-PMT-T-01465 | 2025-09-16 | 11681-NMDC-T-2885 | 4
11 | MOORING ANALYSIS DURING RISER/SPOOL INSTALLATION AT ZWSC GIP | 2800-ZZ-CL-011 | AD-447-PL-62523 |  |  | 2025-05-14
12 | MOORING ANALYSIS DURING RISER INSTALLATION OF GL-1 AND GL-2 AT ZK-50 | 2800-ZZ-CL-012 | AD-166-PL-62522 | 1 | 2 | 2025-05-19 | 2025-08-19 | CSE-2800-PMT-T-089 | 2025-08-20 | 2800-NMDC-E-AO-PMT-T-01642 | 2025-09-16 | 11681-NMDC-T-2885 | 4
|  |  |  | 2 | 2 |  | 2026-06-12 | CSE-2800-PMT-T-228 | 2026-06-17 | 2800-NMDC-E-AO-PMT-T-02771
13 | MOORING ANALYSIS DURING RISER INSTALLATION OF GL-2 AND GL-3 AT ZK-43A | 2800-ZZ-CL-013 | AD-165-PL-62524 | 1 | 2 | 2025-05-24 | 2025-08-19 | CSE-2800-PMT-T-090 | 2025-08-20 | 2800-NMDC-E-AO-PMT-T-01643 | 2025-09-16 | 11681-NMDC-T-2885 | 4
14 | MOORING ANALYSIS DURING RISER INSTALLATION OF GL-3 AND GL-4 AT ZK-45 | 2800-ZZ-CL-014 | AD-162-PL-62521 | 1 | 2 | 2025-05-28 | 2025-08-19 | CSE-2800-PMT-T-091 | 2025-08-20 | 2800-NMDC-E-AO-PMT-T-01644 | 2025-09-16 | 11681-NMDC-T-2885 | 4
15 | LOWER ZAKUM - MOORING ANALYSIS DURING RISER/SPOOL INSTALLATION AT ZK-372 | 2800-ZZ-CL-015 | AD-313-PL-62519 |  |  | 2025-04-15
16 | MOORING ANALYSIS DURING RISER/SPOOL INSTALLATION AT ZK-126.5/65 | 2800-ZZ-CL-016 | AD-312-PL-62508 |  |  | 2025-04-15
17 | PLB-648 MOORING ANALYSIS DURING MODULE 1 INSTALLATION AT ZK-47 | 2800-ZZ-CL-017 | AD-164-PL-62515 | 1 |  | 2025-04-15 | 2025-12-23 | CSE-2800-PMT-T-152 | 2025-12-25 | 2800-NMDC-E-AO-PMT-T-02199 | 2025-12-31 | 11681-NMDC-T-3254 | 4 | [5 empty] | reissued on 23/12
18 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES @ GAC-68 (TRIP-1) | 2800-ZZ-CL-018 | AD-27-PL-62851 | 1 | 2 | 2025-03-27 | 2025-06-23 | CSE-2800-PMT-T-050 | 2025-06-25 | 2800-NMDC-E-AO-PMT-T-01369 | 2025-07-01 | 11681-NMDC-T-2462 | 4
19 | STABILITY ANALYSIS DURING TRANSPORTATION OF 6" CC PIPES TRIP-2 | 2800-ZZ-CL-019 | AD-27-PL-62852 | 1 | 2 | 2025-04-10 | 2025-08-22 | CSE-2800-PMT-T-096 | 2025-08-25 | 2800-NMDC-E-AO-PMT-T-01672 | 2025-12-16 | 11681-NMDC-T-3219 | 4
20 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF RISERS & SPOOLS @ ELISSA (TRIP-1) | 2800-ZZ-CL-020 | AD-27-PL-62853 | 1 | 2 | 2025-02-01 | 2025-12-03 | CSE-2800-PMT-T-139 | 2025-12-04 | 2800-NMDC-E-AO-PMT-T-02173 | 2025-12-11 | 11681-NMDC-T-3204 | 4
21 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF RISERS & SPOOLS (TRIP-2) | 2800-ZZ-CL-021 | AD-27-PL-62854 |  |  | 2025-05-01
22 | STABILITY ANALYSIS DURING TRANSPORTATION OF SLEEPERS TRIP-1 | 2800-ZZ-CL-022 | AD-27-PL-62855 | 1 |  | 2025-01-15 | 2025-02-27 | CSE-2800-PMT-T-004 | 2025-03-03 | 2800-NMDC-E-AO-PMT-T-00858 | 2025-05-19 | 11681-NMDC-T-2197 | 2
|  |  |  | 2 |  |  | 2025-04-03 | CSE-2800-PMT-T-012 | 2025-04-08 | 2800-NMDC-E-AO-PMT-T-00987 | 2025-05-19 | 11681-NMDC-T-2197 | 2
23 | STABILITY ANALYSIS DURING TRANSPORTATION OF SLEEPERS TRIP-2 (CANPAIGN-1) | 2800-ZZ-CL-023 | AD-27-PL-62856 | 1 | 2 | 2025-01-15 | 2025-05-07 | CSE-2800-PMT-T-020 | 2025-05-14 | 2800-NMDC-E-AO-PMT-T-01147 | 2025-06-04 | 11681-NMDC-T-2288 | 2 | [5 empty] | No don’t submit to client Methods will revise it with after changing the cargo barge -Muhammed Hirash (DC)email dtd.09/04 | mail from Ahmos Elsaggan
|  |  |  | 2 | 2 |  | 2025-09-16 | CSE-2800-PMT-T-106 | 2025-09-17 | 2800-NMDC-E-AO-PMT-T-01812 | 2025-12-31 | 11681-NMDC-T-3254 | 4
24 | STABILITY ANALYSIS DURING TRANSPORTATION OF MATTRESSES - TRIP-1 | 2800-ZZ-CL-024 | AD-27-PL-62857 | 1 | 2 | 2025-01-15 | 2025-07-03 | CSE-2800-PMT-T-058 | 2025-07-04 | 2800-NMDC-E-AO-PMT-T-01427 | 2025-12-31 | 11681-NMDC-T-3254 | 4
25 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC MATTRESSES | 2800-ZZ-CL-025 | AD-27-PL-62858 | 1 | 2 | 2025-01-15 | 2025-11-20 | CSE-2800-PMT-T-142 | 2025-11-20 | 2800-NMDC-E-AO-PMT-T-02138 | 2025-12-31 | 11681-NMDC-T-3254 | 4
|  |  |  | 2 | 2 |  | 2026-04-16 | CSE-2800-PMT-T-207 | 2026-04-17 | 2800-NMDC-E-AO-PMT-T-02602 | 2026-04-21 | 11681-NMDC-T-3523 | 4
26 | STABILITY ANALYSIS DURING TRANSPORTATION OF SLEEPERS TRIP-1 (CAMPAIGN 1) | 2800-ZZ-CL-026 | AD-27-PL-63301 | 1 | 2 | 2025-04-20 | 2025-04-17 | CSE-2800-PMT-T-016 | 2025-04-22 | 2800-NMDC-E-AO-PMT-T-01038 | 2025-05-19 | 11681-NMDC-T-2197 | 2
27 | STABILITY ANALYSIS DURING TRANSPORTATION OF SLEEPERS (TRIP-3) CAMPAIGN-2 | 2800-ZZ-CL-027 | AD-27-PL-63302 | 1 | 2 | 2025-04-20 | 2025-04-14 | CSE-2800-PMT-T-015 | 2025-04-15 | 2800-NMDC-E-AO-PMT-T-01031 | 2025-04-24 | 11681-NMDC-T-2054 | 4
28 | STABILITY ANALYSIS DURING TRANSPORTATION OF GL-4 SLEEPERS AT ES-281 (TRIP-3) | 2800-ZZ-CL-028 | AD-27-PL-63303 | 1 | 2 | 2025-09-01 | 2025-09-26 | CSE-2800-PMT-T-107 | 2025-09-30 | 2800-NMDC-E-AO-PMT-T-01880 | 2025-12-31 | 11681-NMDC-T-3254 | 4 | [5 empty] | REISSUED ON 26/09
|  |  |  | 2 | 2 |  | 2025-10-23 | CSE-2800-PMT-T-126 | 2025-10-24 | 2800-NMDC-E-AO-PMT-T-02010 | 2025-12-31 | 11681-NMDC-T-3254 | 4
29 | STABILITY ANALYSIS DURING TRANSPORTATION OF GL-4 SLEEPERS ON ES-282 (TRIP-2) | 2800-ZZ-CL-029 | AD-27-PL-63304 | 1 | 2 | 2026-08-01 | 2026-07-24 | CSE-2800-PMT-T-242 | 2026-07-27 | 2800-NMDC-E-AO-PMT-T-02872
30 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC MATTRESSES ONBOARD ES-282 | 2800-ZZ-CL-030 | AD-27-PL-63305 | 1 | 2 | 2026-08-01 | 2026-08-25 | CSE-2800-PMT-T-251 | 2026-08-27 | 2800-NMDC-E-AO-PMT-T-02930
31 | STABILITY ANALYSIS DURING TRANSPORTATION OF SLEEPERS TRIP-7 | 2800-ZZ-CL-031 | AD-27-PL-63306 |  |  | 2026-08-01
32 | PLB-648 MOTION ANALYSIS AND UKC CHECK IN SHALLOW WATER | 2800-ZZ-CL-032 | AD-27-PL-63307 | 1 | 2 | 2025-05-10 | 2025-05-08 | CSE-2800-PMT-T-025 | 2025-05-13 | 2800-NMDC-E-AO-PMT-T-01148 | 2025-06-03 | 11681-NMDC-T-2291 | 3 | [5 empty] | TITLE HAS BEEN CHANGED
|  |  |  | 2 | 2 |  | 2025-05-18 | CSE-2800-PMT-T-221 | 2027-05-19 | 2800-NMDC-E-AO-PMT-T-02703
33 | STABILITY ANALYSIS DURING TRANSPORTATION OF 6" CC PIPES @ ES-281 TRIP-1 | 2800-ZZ-CL-033 | AD-27-PL-63308 | 1 | 2 | 2025-08-15 | 2025-07-29 | CSE-2800-PMT-T-074 | 2025-07-31 | 2800-NMDC-E-AO-PMT-T-01539 | 2025-08-18 | 11681-NMDC-T-2735 | 4
|  |  |  | 2 | 2 |  | 2025-08-12 | CSE-2800-PMT-T-083 | 2025-08-14 | 2800-NMDC-E-AO-PMT-T-01609 | 2025-09-03 | 11681-NMDC-T-2825 | 2
34 | STABILITY ANALYSIS DURING TRANSPORTATION OF 6" CC PIPES (GL-4) TRIP-1 | 2800-ZZ-CL-034 | AD-27-PL-63309 | 1 | 2 | 2025-12-25 | 2025-09-16 | CSE-2800-PMT-T-111 | 2025-09-17 | 2800-NMDC-E-AO-PMT-T-01814 | 2025-12-31 | 11681-NMDC-T-3254 | 4
|  |  |  | 2 | 2 |  | 2025-12-24 | CSE-2800-PMT-T-159 | 2025-12-25 | 2800-NMDC-E-AO-PMT-T-02255
35 | MOORING ANALYSIS DURING SLEEPER INSTALLATION (GL-3) | 2800-ZZ-CL-035 | AD-27-PL-63310 | 1 | 2 | 2025-05-30 | 2025-04-10 | CSE-2800-PMT-T-013 | 2025-04-15 | 2800-NMDC-E-AO-PMT-T-01015 | 2025-05-21 | 11681-NMDC-T-2225 | 5
|  |  |  | 2 | 2 |  | 2025-05-22 | CSE-2800-PMT-T-031 | 2025-05-23 | 2800-NMDC-E-AO-PMT-T-01216 | 2025-05-27 | 11681-NMDC-T-2257 | 2
36 | MOORING ANALYSIS DURING SLEEPER INSTALLATION (GL-4) | 2800-ZZ-CL-036 | AD-27-PL-63311 | 1 | 2 | 2025-05-30 | 2025-04-10 | CSE-2800-PMT-T-014 | 2025-04-15 | 2800-NMDC-E-AO-PMT-T-01017 | 2025-05-26 | 11681-NMDC-T-2246 | 2
|  |  |  | 2 | 2 |  | 2025-05-29 | CSE-2800-PMT-T-036 | 2025-06-02 | 2800-NMDC-E-AO-PMT-T-01243 | 2025-06-23 | 11681-NMDC-T-2416 | 2
37 | MOORING ANALYSIS DURING SLEEPER INSTALLATION (GL-2) | 2800-ZZ-CL-037 | AD-27-PL-63405 | 1 | 2 | 2025-05-30 | 2025-05-14 | CSE-2800-PMT-T-028 | 2025-04-16 | 2800-NMDC-E-AO-PMT-T-01177 | 2025-06-03 | 11681-NMDC-T-2297 | 3
38 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE BLOCKS | 2800-ZZ-CL-038 | AD-27-PL-63480 | 1 | 2 | 2025-08-10 | 2025-08-04 | CSE-2800-PMT-T-079 | 2025-08-12 | 2800-NMDC-E-AO-PMT-T-01594 | 2025-12-31 | 11681-NMDC-T-3254 | 4
39 | MOORING ANALYSIS DURING RISER INSTALLATION OF GL-4 AT ZK-56 | 2800-ZZ-CL-039 | AD-168-PL-65002 | 1 | 2 | 2025-08-20 | 2025-08-19 | CSE-2800-PMT-T-092 | 2025-08-25 | 2800-NMDC-E-AO-PMT-T-01661 | 2025-09-16 | 11681-NMDC-T-2885 | 4
40 | MOORING ANALYSIS DURING STANDBY POSITION |  | AD-27-PL-63539 | 1 | 2 | 2025-09-30 | 2025-09-29 | CSE-2800-PMT-T-115 | 2025-09-30 | 2800-NMDC-E-AO-PMT-T-01889 | 2025-12-10 | 11681-NMDC-T-3198 | 2 | [5 empty] | Email from prince on 26/09.PMT
41 | HEA TITAN MOORING ANALYSIS AT GIP | 2800-ZZ-CL-041 | AD-447-Z-80030 | 1 | 2 | 2026-05-30 | 2026-05-22 | CSE-2800-PMT-T-223
42 | HEA TITAN MOORING ANALYSIS AT ZWSC-GIP | 2800-ZZ-CL-042 | AD-447-Z-80034 | 1 | 2 | 2026-06-10 | 2026-04-04 | CSE-2800-PMT-T-202 | 2026-04-06 | 2800-NMDC-E-AO-PMT-T-02566 | 2026-04-15 | 11681-NMDC-T-3495 | 4
|  |  |  | 2 | 3 |  | 2026-05-18 | CSE-2800-PMT-T-220 | 2027-05-19 | 2800-NMDC-E-AO-PMT-T-02701
|  |  |  | 3 | 3 |  | 2026-06-03 | CSE-2800-PMT-T-227 | 2026-06-03 | 2800-NMDC-E-AO-PMT-T-02742 | 2026-06-10 | 11681-NMDC-T-3615 | 2
43 | STABILITY ANALYSIS DURING TRANSPORTATION OF GRAVITY ANCHORS AND MISC ITEMS ON ES-281 | 2800-ZZ-CL-043 | AD-27-Z-80719 | 1 | 2 |  | 2026-08-04 | CSE-2800-PMT-T-246 | 2026-08-04 | 2800-NMDC-E-AO-PMT-T-02887
44 | HEA TITAN MOORING ANALYSIS AT ZCSC-NWIP | 2800-ZZ-CL-044 | AD-463-Z-80021 | 1 | 2 | reissued | 19-08-2026 21-08-2026 | CSE-2800-PMT-T-250 | 2026-08-24 | 2800-NMDC-E-AO-PMT-T-02915
45 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES AND FOAM FLOATERS ON ES-282 CB | 2800-ZZ-CL-045 | TBA | 1 | 2 |  | 2026-09-01 | CSE-2800-PMT-T-252 | 2026-09-02 | 2800-NMDC-E-AO-PMT-T-02935
46 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC MATTRESSES ONBOARD GAC-68 | 2800-ZZ-CL-046 |  | 1 | 2 |  | 2026-09-07 | CSE-2800-PMT-T-254 | 2026-09-07 | 2800-NMDC-E-AO-PMT-T-02948

## Drawings
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
ADNOC EPC for LZ HABSHAN UPPER RECOVERY LEKHWAIR+20 MPB PROJECT
|  | NPCC PROJECT NO. 2800 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | START UP HEAD DETAILS FOR 10’’ WATER INJECTION PIPELINE | 2800-NN-0001 | AD-27-PL-625137-SHT-001 | 1 | 2 | 2025-04-01 | 2025-02-28 | CSE-2800-PMT-T-005 | 2025-03-03 | 2800-NMDC-E-AO-PMT-T-00855 | 2025-05-20 | 11681-NMDC-T-2209 | 1
|  |  |  | 2 | 2 |  | 2025-04-21 | CSE-2800-PMT-T-017 | 2025-04-24 | 2800-NMDC-E-AO-PMT-T-01044 | 2025-06-04 | 11681-NMDC-T-2303 | 1
|  |  |  | 3 | 2 |  | 2025-05-20 | CSE-2800-PMT-T-030 | 2025-05-21 | 2800-NMDC-E-AO-PMT-T-01208 | 2025-06-04 | 11681-NMDC-T-2301 | 1
2 | START UP HEAD DETAILS FOR 6'' GL PIPELINES | 2800-NN-0002 | AD-27-PL-625138-SHT-001 | 1 | 2 | 2025-03-01 | 2025-05-29 | CSE-2800-PMT-T-037 | 2025-06-02 | 2800-NMDC-E-AO-PMT-T-01241 | 2025-06-03 | 11681-NMDC-T-2297 | 1
3 | LAYDOWN HEAD DETAILS FOR 10'' WATER INJECTION PIPELINE | 2800-NN-0003 | AD-27-PL-625139-SHT-001 | 1 | 2 | 2025-04-01 | 2025-03-12 | CSE-2800-PMT-T-007 | 2025-03-13 | 2800-NMDC-E-AO-PMT-T-00904 | 2025-05-20 | 11681-NMDC-T-2209 | 1
|  |  |  | 2 | 2 |  | 2025-04-21 | CSE-2800-PMT-T-017 | 2025-04-24 | 2800-NMDC-E-AO-PMT-T-01046 | 2025-06-04 | 11681-NMDC-T-2301 | 1
|  |  |  | 3 | 2 |  | 2025-05-20 | CSE-2800-PMT-T-030 | 2025-05-21 | 2800-NMDC-E-AO-PMT-T-01209 | 2025-06-04 | 11681-NMDC-T-2301 | 1
4 | LAYDOWN HEAD DETAILS FOR 6'' GL PIPELINES | 2800-NN-0004 | AD-27-PL-625140-SHT-001 | 1 | 2 | 2025-03-01 | 2025-06-09 | CSE-2800-PMT-T-043 | 2025-06-12 | 2800-NMDC-E-AO-PMT-T-01297 | 2025-06-17 | 11681-NMDC-T-2369 | 1
5 | EMERGENCY LAYDOWN HEAD DETAILS FOR 10" WI PIPELINES | 2800-NN-0005 | AD-27-PL-625141-SHT-001 | 1 | 2 | 2025-04-01 | 2025-03-25 | CSE-2800-PMT-T-010 | 2025-04-09 | 2800-NMDC-E-AO-PMT-T-01007 | 2025-04-17 | 11681-NMDC-T-2001 | 2
|  |  |  | 2 | 2 |  | 2025-05-08 | CSE-2800-PMT-T-026 | 2025-05-16 | 2800-NMDC-E-AO-PMT-T-01171 | 2025-05-19 | 11681-NMDC-T-2197 | 1
6 | EMERGENCY LAYDOWN HEAD DETAILS FOR 6'' GL PIPELINES | 2800-NN-0006 | AD-27-PL-625142-SHT-001 | 1 | 2 | 2025-03-01 | 2025-06-09 | CSE-2800-PMT-T-043 | 2025-06-12 | 2800-NMDC-E-AO-PMT-T-01298 | 2025-06-17 | 11681-NMDC-T-2369 | 1
7 | BUCKLE DETECTOR FOR 10" WI PIPELINES | 2800-NN-0007 | AD-27-PL-625143-SHT-001 | 1 | 2 | 2025-04-01 | 2025-04-28 | CSE-2800-PMT-T-019 | 2025-04-29 | 2800-NMDC-E-AO-PMT-T-01047 | 2025-05-22 | 11681-NMDC-T-2234 | 2
|  |  |  | 2 | 2 | 2025-06-01 | 2025-06-10 | CSE-2800-PMT-T-044 | 2025-06-10 | 2800-NMDC-E-AO-PMT-T-01299 | 2025-07-02 | 11681-NMDC-T-2467 | 2
|  |  |  | 3 | 3 | 2025-07-20 | 2025-07-18 | CSE-2800-PMT-T-068 | 2025-07-22 | 2800-NMDC-E-AO-PMT-T-01506 | 2025-09-18 | 11681-NMDC-T-2896 | 2
|  |  |  | 4 | 3 | 2026-03-10 | 2026-03-05 | CSE-2800-PMT-T-187 | 2026-03-06 | 2800-NMDC-E-AO-PMT-T-02491 | 2026-03-25 | 11681-NMDC-T-3450 | 2
8 | BUCKLE DETECTOR FOR 6" GL PIPELINES | 2800-NN-0008 | AD-27-PL-625144-SHT-001 | 1 | 2 | 2025-03-01 | 2025-04-28 | CSE-2800-PMT-T-019 | 2025-04-29 | 2800-NMDC-E-AO-PMT-T-01049 | 2025-05-22 | 11681-NMDC-T-2234 | 2
|  |  |  | 2 | 2 | 2025-06-20 | 2025-06-10 | CSE-2800-PMT-T-044 | 2025-06-10 | 2800-NMDC-E-AO-PMT-T-01300 | 2025-07-02 | 11681-NMDC-T-2467 | 2
|  |  |  | 3 | 3 | 2025-07-28 | 2025-07-18 | CSE-2800-PMT-T-068 | 2025-07-22 | 2800-NMDC-E-AO-PMT-T-01505 | 2025-07-23 | 11681-NMDC-T-2594 | 3
|  |  |  | 4 | 3 | 2026-03-15 | 2026-03-05 | CSE-2800-PMT-T-187 | 2026-03-06 | 2800-NMDC-E-AO-PMT-T-02491 | 2026-03-25 | 11681-NMDC-T-3450 | 2
9 | TEMPORARY PIG LAUNCHER & RECEIVER FOR 10" WI PIPELINES | 2800-NN-0009 | AD-27-PL-625145-SHT-001 | 1 | 3 | 2025-04-25 | 2025-10-28 | CSE-2800-PMT-T-129 | 2025-10-20 | 2800-NMDC-E-AO-PMT-T-02038
|  |  |  | 2 | 3 | 2026-03-21 | 2026-03-11 | CSE-2800-PMT-T-191 | 2026-03-13 | 2800-NMDC-E-AO-PMT-T-02518
|  |  |  | 3 | 3 | 2026-05-29 | 2026-05-19 | CSE-2800-PMT-T-217 | 2026-05-20 | 2800-NMDC-E-AO-PMT-T-02705
10 | TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL PIPELINES | 2800-NN-0010 | AD-27-PL-625146-SHT-001 | 1 | 3 | 2025-04-25 | 2025-10-28 | CSE-2800-PMT-T-129 | 2025-10-20 | 2800-NMDC-E-AO-PMT-T-02038
|  |  |  | 2 | 3 | 2026-03-21 | 2026-03-11 | CSE-2800-PMT-T-191 | 2026-03-13 | 2800-NMDC-E-AO-PMT-T-02518
|  |  |  | 3 | 3 | 2026-05-17 | 2026-05-07 | CSE-2800-PMT-T-215 | 2026-05-07 | 2800-NMDC-E-AO-PMT-T-02670
11 | TEMPORARY PIG LAUNCHER FOR 10" WI PIPELINES | 2800-NN-0011 | AD-27-PL-625147-SHT-001 |  |  | 2027-01-01
12 | TEMPORARY PIG RECEVIER FOR 6" GL PIPELINES | 2800-NN-0012 | AD-27-PL-625148-SHT-001 |  |  | 2027-01-01
13 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR (WI3) 10" WATER INJECTION PIPELINE FROM ZK-47 TO ZK-372 | 2800-NN-0013 | AD-27-PL-625149-SHT-001 | 1 | 3 | 2024-12-15 | 2025-03-28 | CSE-2800-PMT-T-011 | 2025-03-28 | 2800-NMDC-E-AO-PMT-T-00951 | 2025-05-19 | 11681-NMDC-T-2203 | 1
|  |  |  | 2 | 3 | 2025-04-30 | 2025-04-21 | CSE-2800-PMT-T-017
14 | 10” RISER LIFTING AND INSTALLATION DRAWING AT ZK-47 (MP-02) | 2800-NN-0014 | AD-164-PL-625011-SHT-001 | 1 | 2 | 2025-02-01 | 2025-08-22 | CSE-2800-PMT-T-094 | 2025-08-25 | 2800-NMDC-E-AO-PMT-T-01668 | 2025-09-17 | 11681-NMDC-T-2886 | 4
15 | 10” RISER (WI-3) LIFTING AND INSTALLATION AT ZK-372 (MP-01) | 2800-NN-0015 | AD-313-PL-625024-SHT-001 | 1 | 2 | 2025-02-01 | 2025-09-04 | CSE-2800-PMT-T-100 | 2025-09-08 | 2800-NMDC-E-AO-PMT-T-01773 | 2025-09-17 | 11681-NMDC-T-2886 | 4
16 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT PIPELINE FROM ZK-50 TO ZWSC-GIP (GL-1) AT ZWSC-GIP (GL-1) | 2800-NN-0016 | AD-447-PL-625033-SHT-001 | 1 | 2 | 2026-04-30 | 02-01-2026 21-01-2026 | CSE-2800-PMT-T-164 | 2026-01-22 | 2800-NMDC-E-AO-PMT-T-02324 | 2026-01-27 | 11681-NMDC-T-3321 | 1 | [5 empty] | HOLD - TAREK / AHMOS
|  |  |  | 2 | 2 |  | 2026-02-03 | CSE-2800-PMT-T-176 | 2026-02-04 | 2800-NMDC-E-AO-PMT-T-02397 | 2026-02-10 | 11681-NMDC-T-3360 | 2
|  |  |  | 3 | 3 |  | 2026-02-20 | CSE-2800-PMT-T-183 | 2026-02-23 | 2800-NMDC-E-AO-PMT-T-02461 | 2026-03-02 | 11681-NMDC-T-3393 | 2
|  |  |  | 4 | 3 |  | 2026-04-30 | CSE-2800-PMT-T-213 | 2026-05-04 | 2800-NMDC-E-AO-PMT-T-02654 | 2026-06-10 | 11681-NMDC-T-3615 | 2
17 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT PIPELINE FROM ZK-50 TO ZWSC-GIP (GL-1) AT ZK-50 (GL-1) | 2800-NN-0017 | AD-166-PL-625033-SHT-001 | 1 | 2 | 2026-03-30 | 2026-03-24 | CSE-2800-PMT-T-199 | 2026-03-25 | 2800-NMDC-E-AO-PMT-T-02544 | 2026-04-10 | 11681-NMDC-T-3478 | 2
18 | LOWER ZAKUM - RISER/SPOOL LIFTING AND INSTALLATION FOR (GL-2) 6” GL PL FROM ZK-50 TO ZK-43A AT ZK-43A (PLB-648) | 2800-NN-0018 | AD-165-PL-625031-SHT-001 | 1 | 2 | 2025-05-01 | 2025-10-13 | CSE-2800-PMT-T-120 | 2025-10-13 | 2800-NMDC-E-AO-PMT-T-01959 | 2025-10-27 | 11681-NMDC-T-3064 | 2
|  |  |  | 2 | 2 | 2025-11-10 | 2025-11-04 | CSE-2800-PMT-T-130 | 2025-11-06 | 2800-NMDC-E-AO-PMT-T-02069 | 2025-11-10 | 11681-NMDC-T-3113 | 2 | [5 empty] | reissued on 04/11
|  |  |  | 3 | 2 | 2026-01-20 | 2026-01-16 | CSE-2800-PMT-T-168 | 2026-01-16 | 2800-NMDC-E-AO-PMT-T-02308 | 2026-01-21 | 11681-NMDC-T-3301 | 1
19 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT PIPELINE FROM ZK-43A TO ZK-45 AT ZK-45 (GL-3) | 2800-NN-0019 | AD-162-PL-625024-SHT-001 | 1 | 2 | 2026-06-10 | 2026-04-27 | CSE-2800-PMT-T-211 | 2026-04-27 | 2800-NMDC-E-AO-PMT-T-02629
|  |  |  | 2 | 2 |  | 2026-06-04 | CSE-2800-PMT-T-225 | 2026-06-04 | 2800-NMDC-E-AO-PMT-T-02739 | 2026-06-10 | 11681-NMDC-T-3615 | 2 | [5 empty] | reissued on 04/06
|  |  |  | 3 | 2 |  | 2026-06-18 | CSE-2800-PMT-T-229 | 2026-06-19 | 2800-NMDC-E-AO-PMT-T-02779
20 | 10” RISER (WI-3) LIFTING AND INSTALLATION AT ZK-372 (MP-02) | 2800-NN-0020 | AD-313-PL-625025-SHT-001 | 1 | 2 | 2025-02-01 | 2025-09-04 | CSE-2800-PMT-T-100 | 2025-09-08 | 2800-NMDC-E-AO-PMT-T-01773 | 2025-09-17 | 11681-NMDC-T-2886 | 4
21 | RISER/SPOOL LIFTING DRAWING FOR 10 IN AT ZK-126.5/65 | 2800-NN-0021 | AD-312-PL-625036-SHT-001 | 1 | 2 | 2025-02-01 | 2025-09-01 | CSE-2800-PMT-T-099 | 2025-09-03 | 2800-NMDC-E-AO-PMT-T-01738 | 2025-09-17 | 11681-NMDC-T-2886 | 4
22 | LOWER ZAKUM – RISER / SPOOL LIFTING AND INSTALLATION FOR 6” GAS LIFT PIPELINE FROM ZK-50 TO ZK-43A (GL-2) AT ZK-50 | 2800-NN-0022 | AD-166-PL-625034-SHT-001 | 1 | 2 | 2025-05-01 | 2026-03-06 | CSE-2800-PMT-T-188 | 2027-03-06 | 2800-NMDC-E-AO-PMT-T-02498 | 2027-03-25 | 11681-NMDC-T-3450 | 2
|  |  |  | 2 | 2 |  | 2026-06-25 | CSE-2800-PMT-T-232 | 2026-06-25 | 2800-NMDC-E-AO-PMT-T-02801
23 | LOWER ZAKUM - RISER/SPOOL LIFTING DRAWING FOR 6 IN AT ZK-43A | 2800-NN-0023 | AD-165-PL-625032-SHT-001 |  |  | cancelled
24 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT PIPELINE FROM ZK-43A TO ZK-45 AT ZK-45 (GL-4) | 2800-NN-0024 | AD-162-PL-625025-SHT-001 | 1 | 2 |  | 2026-07-22 | CSE-2800-PMT-T-240 | 2026-07-23 | 2800-NMDC-E-AO-PMT-T-02862
25 | RISER/SPOOL LIFTING DRAWING FOR 6 IN AT ZK-56 | 2800-NN-0025 | AD-168-PL-625003-SHT-001 |  |  | cancelled
26 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE MATTRESSES | 2800-NN-0026 | AD-27-PL-625150-SHT-001 |  |  | cancelled
27 | TYPICAL LIFTING AND INSTALLATION OF J-TUBE CLAMPS | 2800-NN-0027 | AD-27-PL-625151-SHT-001 |  |  | cancelled
28 | TYPICAL LIFTING AND INSTALLATION OF RISER CLAMPS | 2800-NN-0028 | AD-27-PL-625152-SHT-001 |  |  | cancelled
29 | TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-44 | 2800-NN-0029 | AD-410-PL-625023-SHT-001 | 1 | 3 | 2025-02-01 | 2025-08-08 | CSE-2800-PMT-T-081 | 2025-08-16 | 2800-NMDC-E-AO-PMT-T-01619 | 2025-09-17 | 11681-NMDC-T-2886 | 4
30 | LOWER ZAKUM - TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-126.5/65 (MP-01) | 2800-NN-0030 | AD-312-PL-625037-SHT-001 | 1 | 2 | 2025-02-01 | 2025-08-14 | CSE-2800-PMT-T-085 | 2025-08-15 | 2800-NMDC-E-AO-PMT-T-01614 | 2025-08-21 | 11681-NMDC-T-2753 | 2
|  |  |  | 2 | 2 | 2025-09-30 | 2025-09-16 | CSE-2800-PMT-T-112 | 2025-09-18 | 2800-NMDC-E-AO-PMT-T-01817 | 2025-09-19 | 11681-NMDC-T-2899 | 4
31 | LOWER ZAKUM - TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-43A (MP-01) | 2800-NN-0031 | AD-165-PL-625033-SHT-001 | 1 | 2 | 2025-02-01 | 2025-08-21 | CSE-2800-PMT-T-093 | 2025-08-25 | 2800-NMDC-E-AO-PMT-T-01662 | 2025-09-17 | 11681-NMDC-T-2893 | 4
32 | TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-329 MP-01 | 2800-NN-0032 | AD-314-PL-625016-SHT-001 | 1 | 2 | 2025-02-01 | 2025-07-26 | CSE-2800-PMT-T-071 | 2025-07-29 | 2800-NMDC-E-AO-PMT-T-01530 | 2025-07-31 | 11681-NMDC-T-2651 | 2
|  |  |  | 2 | 2 | 2025-08-10 | 2025-08-08 | CSE-2800-PMT-T-080 | 2025-08-12 | 2800-NMDC-E-AO-PMT-T-01596 | 2025-09-17 | 11681-NMDC-T-2886 | 4
33 | J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-307 | 2800-NN-0033 | AD-299-PL-625012-SHT-001 |  |  | 2025-02-01
34 | LOWER ZAKUM TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-126.5/65 (MP-02) | 2800-NN-0034 | AD-312-PL-625038-SHT-001 | 1 | 2 | 2025-02-01 | 2025-08-14 | CSE-2800-PMT-T-085 | 2025-08-15 | 2800-NMDC-E-AO-PMT-T-01615 | 2025-08-21 | 11681-NMDC-T-2753 | 2
|  |  |  | 2 | 2 | 2025-09-20 | 2025-09-16 | CSE-2800-PMT-T-104 | 2025-09-17 | 2800-NMDC-E-AO-PMT-T-01820 | 2025-09-19 | 11681-NMDC-T-2899 | 4
35 | TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-43A (MP-02) | 2800-NN-0035 | AD-165-PL-625034-SHT-001 | 1 | 2 | 2025-02-01 | 2025-08-21 | CSE-2800-PMT-T-093 | 2025-08-25 | 2800-NMDC-E-AO-PMT-T-01663 | 2025-09-17 | 11681-NMDC-T-2893 | 4
36 | J-TUBE LIFTING AND INSTALLATION DRAWING AT WHT-2 | 2800-NN-0036 | AD-332-PL-625002-SHT-001 |  |  | 2025-02-01
37 | TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-307 | 2800-NN-0037 | AD-299-PL-625013-SHT-001 | 1 | 2 | 2025-02-01 | 2025-06-20 | CSE-2800-PMT-T-053 | 2025-06-20 | 2800-NMDC-E-AO-PMT-T-01363 | 2025-07-09 | 11681-NMDC-T-2503 | 1
38 | LOWER ZAKUM TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-88 | 2800-NN-0038 | AD-174-PL-625002-SHT-001 | 1 | 2 | 2025-02-01 | 2025-07-10 | CSE-2800-PMT-T-064 | 2025-07-11 | 2800-NMDC-E-AO-PMT-T-01459 | 2025-09-17 | 11681-NMDC-T-2886 | 4
39 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES @ GAC-68 (TRIP-1) | 2800-NN-0039 | AD-27-PL-625153-SHT-001 | 1 | 2 | 2025-03-01 | 2025-06-23 | CSE-2800-PMT-T-050 | 2025-06-25 | 2800-NMDC-E-AO-PMT-T-01370 | 2025-09-04 | 11681-NMDC-T-2835 | 4
40 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF 6 “ CC PIPES @ GAC-68 (TRIP-2) | 2800-NN-0040 | AD-27-PL-625154-SHT-001 | 1 | 2 | 2025-03-01 | 2025-08-22 | CSE-2800-PMT-T-096 | 2025-08-25 | 2800-NMDC-E-AO-PMT-T-01670 | 2025-09-04 | 11681-NMDC-T-2835 | 4
41 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF OF RISERS & SPOOLS @ ELISSA | 2800-NN-0041 | AD-27-PL-625155-SHT-001 | 1 | 2 | 2025-05-01 | 2025-12-03 | CSE-2800-PMT-T-139 | 2025-12-04 | 2800-NMDC-E-AO-PMT-T-02174 | 2025-12-11 | 11681-NMDC-T-3204 | 4
42 | LOADING ARRGT & SEAFASTENING DETAILS OF OF RISERS & SPOOLS TRIP-2 WITH BALAST PLAN | 2800-NN-0042 | AD-27-PL-625156-SHT-001 |  |  | 2025-05-01
43 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS AT GAC-68 (TRIP-2) | 2800-NN-0043 | AD-27-PL-625157-SHT-001 | 1 |  | 2025-01-01 | 2025-02-27 | CSE-2800-PMT-T-004 | 2025-03-03 | 2800-NMDC-E-AO-PMT-T-00856 | 2025-05-19 | 11681-NMDC-T-2197 | 2
|  |  |  | 2 |  | 2025-04-10 | 2025-04-03 | CSE-2800-PMT-T-012 | 2025-04-03 | 2800-NMDC-E-AO-PMT-T-00989 | 2025-05-19 | 11681-NMDC-T-2197 | 2
44 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ ASTRO (TRIP-3) | 2800-NN-0044 | AD-27-PL-625158-SHT-001 | 1 |  | 2025-01-01 | 2025-04-14 | CSE-2800-PMT-T-015 | 2025-04-15 | 2800-NMDC-E-AO-PMT-T-00985 | 2025-04-24 | 11681-NMDC-T-2053 | 4 | [5 empty] | reissued on 14/04/25 | mail from Ahmos Elsaggan
|  |  |  | 2 |  | 2025-04-10 | 2025-05-01 | ADVANCE COPY | 2025-05-02 | 2800-NMDC-E-AO-PMT-T-01094
45 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE MATTRASSES, SPOOLS, GA & MISC. ITEMS ON AL JABER-34 | 2800-NN-0045 | AD-27-PL-625159-SHT-001 | 1 |  | 2025-01-01 | 2025-11-20 | CSE-2800-PMT-T-142 | 2025-11-21 | 2800-NMDC-E-AO-PMT-T-02139 | 2026-04-21 | 11681-NMDC-T-3523 | 4
|  |  |  | 2 |  | 2026-03-20 | 2026-02-25 | CSE-2800-PMT-T-185 | 2026-02-25 | 2800-NMDC-E-AO-PMT-T-02474 | 2026-04-11 | 11681-NMDC-T-3478 | 4
|  |  |  | 3 |  | 2026-04-20 | 2026-04-20 | CSE-2800-PMT-T-208 | 2026-04-21 | 2800-NMDC-E-AO-PMT-T-02611 | 2026-06-03 | 11681-NMDC-T-3602 | 4
46 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ GAC-68 (TRIP-4) | 2800-NN-0046 | AD-27-PL-625160-SHT-001 | 1 | 2 | 2025-01-01 | 2025-05-08 | CSE-2800-PMT-T-024 | 2025-05-14 | 2800-NMDC-E-AO-PMT-T-01142 | 2025-06-03 | 11681-NMDC-T-2291 | 2
|  |  |  | 2 | 2 | 2026-06-30 | 2025-06-17 | CSE-2800-PMT-T-048 | 2025-06-17 | 2800-NMDC-E-AO-PMT-T-01301 | 2025-07-11 | 11681-NMDC-T-2528 | 2
47 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS AT ASTRO-250 (TRIP-5) | 2800-NN-0047 | AD-27-PL-625161-SHT-001 | 1 | 3 | 2025-07-25 | 2025-05-30 | CSE-2800-PMT-T-038 | 2025-06-02 | 2800-NMDC-E-AO-PMT-T-01263 | 2025-12-11 | 11681-NMDC-T-3204 | 4
|  |  |  | 2 | 3 |  | 2025-07-09 | CSE-2800-PMT-T-061 | 2025-07-09 | 2800-NMDC-E-AO-PMT-T-01450 | 2025-12-11 | 11681-NMDC-T-3204 | 4
48 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ ES-281 (TRIP-6)(CAMPAIGN-1) | 2800-NN-0048 | AD-27-PL-625162-SHT-001 | 1 | MF-26/06 | 2025-01-01 | 2025-06-30 | CSE-2800-PMT-T-054 | 2025-07-01 | 2800-NMDC-E-AO-PMT-T-01403 | 2025-09-04 | 11681-NMDC-T-2835 | 4
49 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS (GL-4) ON ES-282 CB | 2800-NN-0049 | AD-27-PL-625163-SHT-001 | 1 | 2 | 2027-01-01 | 17-08-2026 19-08-2026 | CSE-2800-PMT-T-249 | 2026-08-19 | 2800-NMDC-E-AO-PMT-T-02913
50 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE MATTRESSES ON ES-282 CB | 2800-NN-0050 | AD-27-PL-625164-SHT-001 | 1 | 2 | 2027-01-01 | 2026-08-25 | CSE-2800-PMT-T-251 | 2026-08-26 | 2800-NMDC-E-AO-PMT-T-02928
51 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE MATTRESSES ON GAC-68 CB | 2800-NN-0051 | AD-27-PL-625165-SHT-001 | 1 | 2 |  | 2026-09-04 | CSE-2800-PMT-T-253 | 2026-09-07 | 2800-NMDC-E-AO-PMT-T-02946
52 | LOADING ARRANGEMENT AND SEAFASTENING OF CONCRETE SLEEPERS & MATTRESSES (TRIP-10) | 2800-NN-0052 | AD-27-PL-625166-SHT-001 |  |  | 2027-01-01
53 | LOADING ARRANGEMENT AND SEAFASTENING OF CONCRETE SLEEPERS & MATTRESSES (TRIP-11) | 2800-NN-0053 | AD-27-PL-625167-SHT-001 |  |  | 2027-01-01
54 | LOADING ARRANGEMENT AND SEAFASTENING OF CONCRETE SLEEPERS & MATTRESSES (TRIP-12) | 2800-NN-0054 | AD-27-PL-625168-SHT-001 |  |  | 2027-01-01
55 | WET BUCKLE CONTENGENCY HEAD DETAILS FOR 6'' GL PIPELINES | 2800-NN-0055 | AD-27-PL-625173-SHT-001 |  |  | 2027-01-01
56 | WET BUCKLE CONTENGENCY HEAD DETAILS FOR 10'' WI PIPELINES | 2800-NN-0056 | AD-27-PL-625174-SHT-001 |  |  | 2027-01-01
57 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR (GL3) 6" GL PIPELINE FROM ZK-43A TO ZK-45 BY PLB-648 | 2800-NN-0057 | AD-165-PL-625035-SHT-001 | 1 | 3 | 2025-06-30 | 2025-03-04 | CSE-2800-PMT-T-006 | 2025-03-28 | 2800-NMDC-E-AO-PMT-T-00950 | 2025-06-04 | 11681-NMDC-T-2303 | 1
|  |  |  | 2 | 3 |  | 2025-04-24 | CSE-2800-PMT-T-018 | 2025-04-28 | 2800-NMDC-E-AO-PMT-T-01056 | 2025-05-05 | 11681-NMDC-T-2113 | 2
|  |  |  | 3 | 3 |  | 2025-06-04 | CSE-2800-PMT-T-042 | 2025-06-11 | 2800-NMDC-E-AO-PMT-T-01285 | 2025-06-17 | 11681-NMDC-T-2369 | 2
58 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ ES-281 (TRIP-1) (FOR PLB-648) | 2800-NN-0058 | AD-27-PL-625175-SHT-001 | 1 | 3 | 2025-04-30 | 2025-04-22 | CSE-2800-PMT-T-016 | 2025-04-24 | 2800-NMDC-E-AO-PMT-T-01037 | 2025-05-19 | 11681-NMDC-T-2197 | 2
59 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & CC PIPES @ ASTRO-251 (TRIP-2) CAMPAIGN-1 | 2800-NN-0059 | AD-27-PL-625176-SHT-001 | 1 | 3 | 2025-11-01 | 2025-05-01 | CSE-2800-PMT-T-020 | 2025-05-06 | 2800-NMDC-E-AO-PMT-T-01093
|  |  |  | 2 | 3 |  | 2025-07-10 | CSE-2800-PMT-T-066 | 2025-07-12 | 2800-NMDC-E-AO-PMT-T-01464
|  |  |  | 3 | 3 |  | 2025-08-01 | CSE-2800-PMT-T-077 | 2025-08-04 | 2800-NMDC-E-AO-PMT-T-01551 | 2025-09-03 | 11681-NMDC-T-2825 | 2
|  |  |  | 4 | 3 |  | 2025-09-16 | CSE-2800-PMT-T-106 | 2025-09-17 | 2800-NMDC-E-AO-PMT-T-01810 | 2025-12-11 | 11681-NMDC-T-3204 | 4
|  |  |  | 5 | 3 |  | 2025-11-04 | CSE-2800-PMT-T-132 | 2025-11-06 | 2800-NMDC-E-AO-PMT-T-02070 | 2025-11-10 | 11681-NMDC-T-3113 | 4
60 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR (GL4) 6" GL PIPELINE FROM ZK-45 TO ZK-56 BY PLB-648 | 2800-NN-0060 | AD-162-PL-625026-SHT-001 | 1 | 3 | 2025-05-30 | 24-03-2025 | CSE-2800-PMT-T-008 | 2025-03-26 | 2800-NMDC-E-AO-PMT-T-00937 | 2025-05-19 | 11681-NMDC-T-2203 | 1
|  |  |  | 2 | 3 |  | 2025-05-27 | CSE-2800-PMT-T-033 | 2025-05-27 | 2800-NMDC-E-AO-PMT-T-01226 | 2025-05-28 | 11681-NMDC-T-2269 | 2
|  |  |  | 3 | 3 |  | 2026-06-25 | CSE-2800-PMT-T-231 | 2026-06-25 | 2800-NMDC-E-AO-PMT-T-02799
61 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR (WI4) 10" WATER INJECTION PIPELINE FROM ZK-372 TO ZK-126.5/65 BY MP02 | 2800-NN-0061 | AD-313-PL-625026-SHT-001 | 1 | 2 | 2025-04-30 | 2025-03-28 | CSE-2800-PMT-T-011 | 2025-03-28 | 2800-NMDC-E-AO-PMT-T-00949 | 2025-05-19 | 11681-NMDC-T-2203 | 1
|  |  |  | 2 | 2 |  | 2025-04-21 | CSE-2800-PMT-T-017
62 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR (GL1) PIPELINE FROM ZWSC-GIP TO ZK-50 BY MP02 | 2800-NN-0062 | AD-447-PL-625034-SHT-001 | 1 | 2 | 2025-03-31 | 2025-03-28 | CSE-2800-PMT-T-011 | 2025-03-28 | 2800-NMDC-E-AO-PMT-T-00948 | 2025-05-19 | 11681-NMDC-T-2203 | 1
63 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR (GL2) PIPELINE FROM ZK-50 TO ZK-43A BY MP02 | 2800-NN-0063 | AD-166-PL-625035-SHT-001 | 1 | 2 | 2025-03-31 | 2025-03-28 | CSE-2800-PMT-T-011 | 2025-03-28 | 2800-NMDC-E-AO-PMT-T-00947 | 2025-05-19 | 11681-NMDC-T-2203 | 1
64 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE BLOCK FOR (GL3) 6" GL PIPELINE FROM ZK-43A TO ZK-45 BY PLB-648 | 2800-NN-0064 | AD-165-PL-625036-001 | 1 | 3 | 2025-05-31 | 2025-05-07 | CSE-2800-PMT-T-022 | 2025-05-09 | 2800-NMDC-E-AO-PMT-T-01139 | 2025-12-11 | 11681-NMDC-T-3204 | 4
65 | TYPICAL LIFTING AND INSTALLATION OF SANDBAGS BY CARGO NET USING MP-02 | 2800-NN-0065 | AD-27-PL-625200-001 | 1 | 2 | 2025-05-31 | 2025-05-08 | CSE-2800-PMT-T-023 | 2025-05-14 | 2800-NMDC-E-AO-PMT-T-01143 | 2025-05-14 | 11681-NMDC-T-2174 | 5
66 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ ES-281 (TRIP-3) (CAMPAIGN-1) | 2800-NN-0066 | AD-27-PL-625201-001 | 1 | 2 | 2025-05-31 | 2025-05-22 | CSE-2800-PMT-T-032 | 2025-05-26 | 2800-NMDC-E-AO-PMT-T-01222 | 2025-09-04 | 11681-NMDC-T-2835 | 4
67 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR (GL2) PIPELINE FROM ZK-50 TO ZK-43A BY PLB-648 | 2800-NN-0067 | AD-166-PL-625208 | 1 | 2 | 2025-05-31 | 2025-05-19 | CSE-2800-PMT-T-029 | 2025-05-21 | 2800-NMDC-E-AO-PMT-T-01206 | 2025-06-04 | 11681-NMDC-T-2301 | 1
|  |  |  | 2 | 2 | 2025-11-21 | 2025-11-25 | CSE-2800-PMT-T-144 | 2025-11-26 | 2800-NMDC-E-AO-PMT-T-02155 | 2025-12-10 | 11681-NMDC-T-3198 | 2
68 | TYPICAL LIFTING AND INSTALLATION OF SANDBAGS BY CARGO NET USING PLB-648 | 2800-NN-0068 | AD-27-PL-625203-SHT-001 | 1 | 2 | 2025-05-31 | 2025-05-27 | CSE-2800-PMT-T-034 | 2025-05-27 | 2800-NMDC-E-AO-PMT-T-01227 | 2025-06-04 | 11681-NMDC-T-2310 | 1
|  |  |  | 2 | 2 |  | 2026-07-17 | CSE-2800-PMT-T-238
69 | CABLE DRUM AND REEL SEAFASTENING DETAILS ON CB AL JABER 34 | 2800-NN-0069 | AD-27-PL-625204-SHT-001 | 1 | 2 | 2025-05-31 | 2025-06-03 | CSE-2800-PMT-T-039 | 2025-06-04 | 2800-NMDC-E-AO-PMT-T-01276 | 2026-03-25 | 11681-NMDC-T-3450 | 2
70 | TYPICAL LIFTING & INSTALLATION OF RISER / J-TUBE CLAMPS (VESSEL MP-01) | 2800-NN-0070 | AD-27-PL-625205-SHT-001 | 1 | 2 | 2025-05-31 | 2025-06-04 | CSE-2800-PMT-T-041 | 2025-06-12 | 2800-NMDC-E-AO-PMT-T-01286 | 2025-06-23 | 11681-NMDC-T-2416 | 2
71 | LOWER ZAKUM - TYPICAL LIFTING & INSTALLATION / DEMOLITION & REMOVAL OF RISER / J-TUBE CLAMPS BY PLB-648 WITH WHIP HOIST | 2800-NN-0071 | AD-27-PL-625206-SHT-001 | 1 | 2 | 2026-01-31 | 2025-06-04 | CSE-2800-PMT-T-041 | 2025-06-11 | 2800-NMDC-E-AO-PMT-T-01287 | 2025-06-17 | 11681-NMDC-T-2369 | 2
|  |  |  | 2 | 2 |  | 2025-11-21 | CSE-2800-PMT-T-143 | 2025-11-24 | 2800-NMDC-E-AO-PMT-T-02147 | 2025-12-10 | 11681-NMDC-T-3198 | 2
|  |  |  | 3 | 2 |  | 2026-01-19 | CSE-2800-PMT-T-170 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02312 | 2026-01-27 | 11681-NMDC-T-3321 | 1
|  |  |  | 4 | 3 |  | 2026-01-30 | CSE-2800-PMT-T-175 | 2026-02-02 | 2800-NMDC-E-AO-PMT-T-02393 | 2026-02-20 | 11681-NMDC-T-3385 | 2
72 | 10" FLANGE PROTECTOR FOR START-UP AND LAYDOWN HEAD – WI-3 | 2800-NN-0072 | AD-27-PL-625207-SHT-001 | 1 | 2 | 2025-06-09 | 2025-06-09 | CSE-2800-PMT-T-045
72 | 10" FLANGE PROTECTOR FOR START-UP AND LAYDOWN HEAD – WI-4 | 2800-NN-0073 | AD-27-PL-625208-SHT-001 | 1 | 2 | 2025-06-09 | 2025-06-09 | CSE-2800-PMT-T-045
74 | TYPICAL LIFTING & INSTALLATION OF ANODE BY PLB-648 (OPTION-1) | 2800-NN-0074 | AD-27-PL-625209-SHT-001 | 1 | 2 | 2026-01-31 | 2025-06-09 | CSE-2800-PMT-T-045 | 2025-06-14 | 2800-NMDC-E-AO-PMT-T-01303 | 2025-06-19 | 11681-NMDC-T-2386 | 2
|  |  |  | 2 | 2 |  | 2025-12-04 | CSE-2800-PMT-T-149 | 2025-12-05 | 2800-NMDC-E-AO-PMT-T-02179 | 2025-12-11 | 11681-NMDC-T-3204 | 4
|  |  |  | 3 | 2 |  | 2026-01-19 | CSE-2800-PMT-T-171 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02313 | 2026-01-27 | 11681-NMDC-T-3321 | 1
75 | TYPICAL LIFTING & INSTALLATION OF ANODE BY MP-01 | 2800-NN-0075 | AD-27-PL-625210-SHT-001 | 1 | 2 | 2025-06-30 | 2025-06-09 | CSE-2800-PMT-T-045 | 2025-06-14 | 2800-NMDC-E-AO-PMT-T-01304 | 2025-06-19 | 11681-NMDC-T-2386 | 2
76 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF GRAVITY ANCHOR, BARGE EXTENSION & BUOYS @ ELISSA | 2800-NN-0076 | AD-27-PL-625213-SHT-001 | 1 | 2 | 2025-06-30 | 2025-06-20 | CSE-2800-PMT-T-051 | 2025-06-20 | 2800-NMDC-E-AO-PMT-T-01362 | 2025-09-04 | 11681-NMDC-T-2835 | 4
77 | MODIFICATION OF START-UP HEAD FOR 10" WATER INJECTION PIPELINES | 2800-NN-0077 | AD-27-PL-625214-SHT-001 |  |  | 2027-01-01
78 | LOADING ARRANGEMENT & SEAFASTENING DETAILS FOR MATTRESSES @ ASTRO-250 (TRIP-1) | 2800-NN-0078 | AD-27-PL-625215-SHT-001 | 1 | 2 | 2025-07-15 | 2025-07-03 | CSE-2800-PMT-T-056 | 2025-07-04 | 2800-NMDC-E-AO-PMT-T-01424 | 2025-07-24 | 11681-NMDC-T-2618 | 2
79 | TYPICAL LIFTING AND INSTALLATION OF MATTRESS BY MP-02 | 2800-NN-0079 | AD-27-PL-625216-SHT-001 | 1 | 2 | 2025-07-31 | 2025-07-09 | CSE-2800-PMT-T-062 | 2025-07-09 | 2800-NMDC-E-AO-PMT-T-01451 | 2025-07-17 | 11681-NMDC-T-2517 | 2
|  |  |  | 2 | 2 |  | 2025-07-22 | CSE-2800-PMT-T-070 | 2025-07-24 | 2800-NMDC-E-AO-PMT-T-01511 | 2025-08-01 | 11681-NMDC-T-2658 | 2
80 | SEAFASTENING OF ZK-280 DECK EXTENSIONS MODULE 1, 4 & 5 ON MUTAWA-402 | 2800-NN-0080 | AD-27-PL-625217-SHT-001 |  |  | 2027-01-01
81 | LOADING ARRANGEMENT & SEAFASTENING DETAILS FOR 6” CC PIPES @ ES-281 (TRIP-1) | 2800-NN-0081 | AD-27-PL-625218-SHT-001 | 1 | 2 | 2025-08-25 | 2025-07-29 | CSE-2800-PMT-T-074 | 2025-07-31 | 2800-NMDC-E-AO-PMT-T-01540 | 2025-09-03 | 11681-NMDC-T-2825 | 2
|  |  |  | 2 | 3 |  | 2025-08-12 | CSE-2800-PMT-T-083 | 2025-08-14 | 2800-NMDC-E-AO-PMT-T-01609 | 2025-09-03 | 11681-NMDC-T-2825 | 2
82 | SEAFASTENING OF ZK-280 DECK EXTENSIONS MODULE 2 & 3 ON MUTAWA-402 | 2800-NN-0082 | AD-27-PL-625219-SHT-001 |  | SKS | 2027-01-01
83 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE BLOCKS @ ASTRO-250 | 2800-NN-0083 | AD-27-PL-625220-SHT-001 | 1 | 2 | 2025-08-30 | 2025-08-04 | CSE-2800-PMT-T-079 | 2025-08-12 | 2800-NMDC-E-AO-PMT-T-01595 | 2025-09-04 | 11681-NMDC-T-2835 | 4
84 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE BLOCK USING MP-02 | 2800-NN-0084 | AD-27-PL-625221-SHT-001 | 1 | 3 | 2025-09-10 | 2025-08-22 | CSE-2800-PMT-T-081 | 2025-08-23 | 2800-NMDC-E-AO-PMT-T-01620 | 2025-09-17 | 11681-NMDC-T-2886 | 4
|  |  |  | 2 | 3 |  | 2025-09-04 | CSE-2800-PMT-T-101 | 2025-09-04 | 2800-NMDC-E-AO-PMT-T-01772 | 2025-09-17 | 11681-NMDC-T-2886 | 4
85 | TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-44 (MP-02) | 2800-NN-0085 | AD-27-PL-625222-SHT-001 | 1 | 3 | 2025-09-10 | 2025-09-09 | CSE-2800-PMT-T-151 | 2025-09-10 | 2800-NMDC-E-AO-PMT-T-01789 | 2025-09-17 | 11681-NMDC-T-2886 | 4
86 | TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-329 (MP-02) | 2800-NN-0086 | AD-314-PL-625017-SHT-001 |  |  | 2027-01-01
87 | TYPICAL LIFTING AND INSTALLATION OF ANODE BY MP-02 | 2800-NN-0087 | AD-27-PL-625223-SHT-001 | 1 | 2 | 2025-09-25 | 2025-08-11 | CSE-2800-PMT-T-082 | 2025-08-13 | 2800-NMDC-E-AO-PMT-T-01606 | 2025-09-17 | 11681-NMDC-T-2893 | 4
|  |  |  | 2 | 2 |  | 2025-09-09 | CSE-2800-PMT-T-104 | 2025-09-10 | 2800-NMDC-E-AO-PMT-T-01791 | 2025-09-17 | 11681-NMDC-T-2893 | 4
88 | TYPICAL LIFTING AND INSTALLATION OF RISER/J-TUBES CLAMPS WITH MP-02 | 2800-NN-0088 | AD-27-PL-625224-SHT-001 | 1 | 2 | 2025-09-25 | 2025-08-12 | CSE-2800-PMT-T-084 | 2025-08-14 | 2800-NMDC-E-AO-PMT-T-01608 | 2025-10-01 | 11681-NMDC-T-2971 | 4
|  |  |  | 2 |  |  | 2025-09-09 | CSE-2800-PMT-T-104 | 2025-09-19 | 2800-NMDC-E-AO-PMT-T-01823 | 2025-09-19 | 11681-NMDC-T-2904 | 4
89 | SEAFASTENING OF ZK-280 DECK EXTENSION MODULES AND MISC. ITEMS ON HEA TITAN | 2800-NN-0089 | AD-27-PL-625225-SHT-001 |  |  | 2027-01-01
90 | 10” RISER LIFTING AND INSTALLATION DRAWING AT ZK-47 (MP-01) | 2800-NN-0090 | AD-164-PL-625013-SHT-001 | 1 | 2 | 2025-09-10 | 2025-08-22 | CSE-2800-PMT-T-094 | 2025-08-25 | 2800-NMDC-E-AO-PMT-T-01669 | 2025-09-17 | 11681-NMDC-T-2886 | 4
91 | 10" SPOOL LIFTING AND INSTALLATION DRAWING AT ZK-47 (MP-02) | 2800-NN-0091 | AD-164-PL-625014-SHT-001 | 1 | 2 | 2026-06-10 | 2025-08-26 | CSE-2800-PMT-T-097 | 2025-08-26 | 2800-NMDC-E-AO-PMT-T-01678 | 2025-09-17 | 11681-NMDC-T-2886 | 4
|  |  |  | 2 | 2 |  | 2026-04-07 | CSE-2800-PMT-T-204 | 2026-04-09 | 2800-NMDC-E-AO-PMT-T-02576 | 2026-04-15 | 11681-NMDC-T-3494 | 2
|  |  |  | 3 | 2 |  | 2026-06-02 | CSE-2800-PMT-T-226 | 2026-06-03 | 2800-NMDC-E-AO-PMT-T-02740 | 2026-06-10 | 11681-NMDC-T-3615 | 2
92 | 10" SPOOL LIFTING AND INSTALLATION DRAWING AT ZK-47 (MP-01) | 2800-NN-0092 | AD-164-PL-625015-SHT-001 | 1 | 2 | 2025-09-10 | 2025-08-26 | CSE-2800-PMT-T-097 | 2025-08-26 | 2800-NMDC-E-AO-PMT-T-01679 | 2025-09-17 | 11681-NMDC-T-2886 | 4
93 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZK-43A TO ZK-45 (GL-3) @ ZK-43A | 2800-NN-0093 | AD-165-PL-625041-SHT-001 | 1 | 2 | 2025-10-30 | 2025-10-14 | CSE-2800-PMT-T-121 | 2025-10-15 | 2800-NMDC-E-AO-PMT-T-01965 | 2026-01-21 | 11681-NMDC-T-3301 | 1
94 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" MOL AT ZK-43A (GL-3) | 2800-NN-0094 | AD-165-PL-625042-SHT-001 | 1 | 2 | 2026-03-31 | 2025-11-06 | CSE-2800-PMT-T-135 | 2025-11-06 | 2800-NMDC-E-AO-PMT-T-02079 | 2025-11-10 | 11681-NMDC-T-3113 | 2
|  |  |  | 2 | 2 |  | 02-01-2026 21-01-2026 | CSE-2800-PMT-T-163 | 2026-01-22 | 2800-NMDC-E-AO-PMT-T-02323 | 2026-01-26 | 11681-NMDC-T-3315 | 1
|  |  |  | 3 | 2 |  | 2026-03-25 | CSE-2800-PMT-T-200 | 2026-03-26 | 2800-NMDC-E-AO-PMT-T-02545 | 2026-04-10 | 11681-NMDC-T-3482 | 2
95 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZK-50 TO ZK-43A (GL-2) @ ZK-43A | 2800-NN-0095 | AD-166-PL-625049-SHT-001 | 1 | 2 | 2025-10-31 | 2025-10-14 | CSE-2800-PMT-T-121 | 2025-10-15 | 2800-NMDC-E-AO-PMT-T-01965 | 2026-01-21 | 11681-NMDC-T-3301 | 1
96 | 10" RISER LIFTING AND INSTALLATION AT ZK-126.5/65 (MP-02) | 2800-NN-0096 | AD-312-PL-625039-SHT-001 | 1 | 2 | 2025-09-10 | 2025-09-01 | CSE-2800-PMT-T-099 | 2025-09-03 | 2800-NMDC-E-AO-PMT-T-01739 | 2025-09-17 | 11681-NMDC-T-2886 | 4
97 | 10" SPOOL LIFTING AND INSTALLATION AT ZK-126.5/65 (MP-01) | 2800-NN-0097 | AD-312-PL-625040-SHT-001 | 1 | 2 | 2025-09-10 | 2025-09-04 | CSE-2800-PMT-T-100 | 2025-09-08 | 2800-NMDC-E-AO-PMT-T-01773 | 2025-09-17 | 11681-NMDC-T-2886 | 4
98 | 10" SPOOL LIFTING AND INSTALLATION AT ZK-126.5/65 (MP-02) | 2800-NN-0098 | AD-312-PL-625041-SHT-001 | 1 | 2 | 2026-05-20 | 2025-09-04 | CSE-2800-PMT-T-100 | 2025-09-08 | 2800-NMDC-E-AO-PMT-T-01773 | 2025-09-17 | 11681-NMDC-T-2886 | 4
|  |  |  | 2 | 2 |  | 15-12-2025 23-12-2025 | CSE-2800-PMT-T-153 | 2025-12-25 | 2800-NMDC-E-AO-PMT-T-02220 | 2026-01-15 | 11681-NMDC-T-3296 | 2 | [5 empty] | reissued on 23/12
|  |  |  | 3 | 2 |  | 2026-05-19 | CSE-2800-PMT-T-217 | 2026-05-20 | 2800-NMDC-E-AO-PMT-T-02706 | 2026-06-10 | 11681-NMDC-T-3615 | 2
99 | 10" RISER (WI-4) LIFTING AND INSTALLATION AT ZK-372 (MP-01) | 2800-NN-0099 | AD-313-PL-625029-SHT-001 | 1 | 2 | 2025-09-30 | 2025-09-12 | CSE-2800-PMT-T-108 | 2025-09-12 | 2800-NMDC-E-AO-PMT-T-01798 | 2025-09-17 | 11681-NMDC-T-2886 | 4
100 | 10" RISER (WI-4) LIFTING AND INSTALLATION AT ZK-372 (MP-02) | 2800-NN-0100 | AD-313-PL-625030-SHT-001 | 1 | 2 | 2025-09-30 | 2025-09-12 | CSE-2800-PMT-T-108 | 2025-09-12 | 2800-NMDC-E-AO-PMT-T-01798 | 2025-09-17 | 11681-NMDC-T-2886 | 4
|  |  |  | 2 | 2 | 2026-04-10 | 2026-04-09 | CSE-2800-PMT-T-206 | 2026-04-10 | 2800-NMDC-E-AO-PMT-T-02583 | 2026-04-15 | 11681-NMDC-T-3494 | 2
101 | 10" SPOOLS (WI-3) LIFTING AND INSTALLATION AT ZK-372 (MP-01) | 2800-NN-0101 | AD-313-PL-625031-SHT-001 | 1 | 2 | 2025-09-30 | 2025-09-16 | CSE-2800-PMT-T-112 | 2025-09-18 | 2800-NMDC-E-AO-PMT-T-01816 | 2025-09-19 | 11681-NMDC-T-2904 | 4
102 | 10" SPOOLS (WI-3) LIFTING AND INSTALLATION AT ZK-372 (MP-02) | 2800-NN-0102 | AD-313-PL-625032-SHT-001 | 1 | 2 | 2026-05-31 | 2025-09-16 | CSE-2800-PMT-T-112 | 2025-09-18 | 2800-NMDC-E-AO-PMT-T-01816 | 2025-09-19 | 11681-NMDC-T-2904 | 4
|  |  |  | 2 | 2 |  | 2026-05-22 | CSE-2800-PMT-T-222 | 2026-05-22 | 2800-NMDC-E-AO-PMT-T-02718 | 2026-06-03 | 11681-NMDC-T-3602 | 2
103 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS AT ES-281 (TRIP-3) | 2800-NN-0103 | AD-27-PL-625227-SHT-001 | 1 | 2 | 2026-01-25 | 2025-09-17 | CSE-2800-PMT-T-107 | 2025-09-19 | 2800-NMDC-E-AO-PMT-T-01828 | 2026-01-30 | 11681-NMDC-T-3333 | 4
|  |  |  | 2 | 2 |  | 2025-10-16 | CSE-2800-PMT-T-123 | 2025-10-17 | 2800-NMDC-E-AO-PMT-T-01980 | 2026-01-30 | 11681-NMDC-T-3333 | 4 | [5 empty] | BARGE CHANGED
|  |  |  | 3 | 2 |  | 2026-01-28 | CSE-2800-PMT-T-174 | 2026-01-29 | 2800-NMDC-E-AO-PMT-T-02362 | 2026-01-30 | 11681-NMDC-T-3333 | 4
104 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS FOR 6" CC PIPES (GL-4) @ ES-281 (TRIP-1) | 2800-NN-0104 | AD-27-PL-625228-SHT-001 | 1 | 2 | 2025-10-10 | 2025-09-16 | CSE-2800-PMT-T-111 | 2025-09-18 | 2800-NMDC-E-AO-PMT-T-01815 | 2026-04-20 | 11681-NMDC-T-3516 | 4
|  |  |  | 2 | 2 |  | 2025-10-08 | CSE-2800-PMT-T-118 | 2025-10-10 | 2800-NMDC-E-AO-PMT-T-01942 | 2025-10-30 | 11681-NMDC-T-3085 | 4
105 | 10" SPOOLS (WI-4) LIFTING AND INSTALLATION AT ZK-372 (MP-01) | 2800-NN-0105 | AD-313-PL-625033-SHT-001 | 1 | 2 | 2025-09-30 | 2025-09-16 | CSE-2800-PMT-T-112 | 2025-09-18 | 2800-NMDC-E-AO-PMT-T-01816 | 2025-09-19 | 11681-NMDC-T-2904 | 4
106 | 10" SPOOLS (WI-4) LIFTING AND INSTALLATION AT ZK-372 (MP-02) | 2800-NN-0106 | AD-313-PL-625034-SHT-001 | 1 | 2 | 2026-05-31 | 2025-09-16 | CSE-2800-PMT-T-112 | 2025-09-18 | 2800-NMDC-E-AO-PMT-T-01816 | 2025-09-19 | 11681-NMDC-T-2904 | 4
|  |  |  | 2 | 2 |  | 2026-05-22 | CSE-2800-PMT-T-222 | 2026-05-22 | 2800-NMDC-E-AO-PMT-T-02718 | 2026-06-03 | 11681-NMDC-T-3602 | 2
107 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON ES-281 (TRIP-4) | 2800-NN-0107 | AD-27-PL-625229-SHT-001 | 1 | 2 | 2026-01-20 | 2026-01-15 | CSE-2800-PMT-T-167 | 2026-01-16 | 2800-NMDC-E-AO-PMT-T-02304 | 2026-04-10 | 11681-NMDC-T-3478 | 4
108 | TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-43A (LEG-4) PLB-648 | 2800-NN-0108 | AD-165-PL-625043-SHT-001 | 1 | 2 | 2026-01-01 | 2025-09-25 | CSE-2800-PMT-T-114 | 2025-09-26 | 2800-NMDC-E-AO-PMT-T-01874 | 2025-10-01 | 11681-NMDC-T-2971 | 4
|  |  |  | 2 | 2 |  | 2025-11-04 | CSE-2800-PMT-T-131 | 2025-11-06 | 2800-NMDC-E-AO-PMT-T-02071 | 2025-11-10 | 11681-NMDC-T-3113 | 2
|  |  |  | 3 | 2 |  | 2025-12-04 | CSE-2800-PMT-T-149 | 2025-12-05 | 2800-NMDC-E-AO-PMT-T-02180 | 2025-12-11 | 11681-NMDC-T-3204 | 4
|  |  |  | 4 | 2 |  | 29-12-2025 02-01-2026 | CSE-2800-PMT-T-162 | 2026-01-05 | 2800-NMDC-E-AO-PMT-T-02267 | 2026-01-14 | 11681-NMDC-T-3292 | 2
109 | SINGLE PIECE J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-43A (PLB-648) | 2800-NN-0109 | AD-165-PL-625044-SHT-001 | 1 | 2 | 2026-01-01 | 2025-10-06 | CSE-2800-PMT-T-117 | 2025-10-22 | 2800-NMDC-E-AO-PMT-T-02004 | 2025-10-27 | 11681-NMDC-T-3064 | 2
|  |  |  | 2 | 2 |  | 2025-11-04 | CSE-2800-PMT-T-131 | 2025-11-06 | 2800-NMDC-E-AO-PMT-T-02072 | 2025-11-10 | 11681-NMDC-T-3113 | 2
|  |  |  | 3 | 2 |  | 2025-12-04 | CSE-2800-PMT-T-149 | 2025-12-05 | 2800-NMDC-E-AO-PMT-T-02181 | 2025-12-11 | 11681-NMDC-T-3204 | 4
|  |  |  | 4 | 2 |  | 29-12-2025 02-01-2026 | CSE-2800-PMT-T-162 | 2026-01-05 | 2800-NMDC-E-AO-PMT-T-02267 | 2026-01-14 | 11681-NMDC-T-3292 | 2
110 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-280 DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA 402 | 2800-NN-0110 | AD-306-PL-625004-SHT-001 | 1 | 2 | 2025-10-10 | 2025-10-10 | CSE-2800-PMT-T-110 | 2025-10-13 | 2800-NMDC-E-AO-PMT-T-01953 | 2025-12-11 | 11681-NMDC-T-3204 | 4
111 | SINGLE PIECE J-TUBE REMOVE AND RE-INSTALLATION DRAWING (CL-2) AT ZK-43A (PLB-648) | 2800-NN-0111 | AD-165-PL-625045-SHT-001 | 1 | 2 | 2026-01-01 | 2025-10-23 | CSE-2800-PMT-T-127 | 2025-10-23 | 2800-NMDC-E-AO-PMT-T-02007 | 2025-10-30 | 11681-NMDC-T-3092 | 2
|  |  |  | 2 | 2 |  | 2025-12-04 | CSE-2800-PMT-T-149 | 2025-12-05 | 2800-NMDC-E-AO-PMT-T-02182 | 2025-12-11 | 11681-NMDC-T-3204 | 4
|  |  |  | 3 | 2 |  | 29-12-2025 02-01-2026 | CSE-2800-PMT-T-162 | 2026-01-05 | 2800-NMDC-E-AO-PMT-T-02267 | 2026-01-14 | 11681-NMDC-T-3292 | 2
112 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (GL-4) MISC. EQUIMENT ON GAC-68 | 2800-NN-0112 | AD-27-PL-625332-SHT-001 | 1 | 2 | 2025-12-31 | 2025-10-15 | CSE-2800-PMT-T-122 | 2025-10-16 | 2800-NMDC-E-AO-PMT-T-01971 | [8 empty] | title modified rev-2
|  |  |  | 2 | 2 |  | 2025-12-24 | CSE-2800-PMT-T-159 | 2025-12-25 | 2800-NMDC-E-AO-PMT-T-02254 | 2026-04-21 | 11681-NMDC-T-3523 | 4
113 | J-TUBE/RISER CLAMPS REMOVAL AND RE-INSTALLATION DRAWING (CL-2) AT ZK-43A (PLB-648) (LEG-1) WITH WHIP HOIST | 2800-NN-0113 | AD-165-PL-625046-SHT-001 | 1 | 2 | 2026-01-31 | 2025-11-26 | CSE-2800-PMT-T-145 | 2025-11-27 | 2800-NMDC-E-AO-PMT-T-02163 | 2026-01-10 | 11681-NMDC-T-3296 | 1
|  |  |  | 2 | 2 |  | 2026-01-19 | CSE-2800-PMT-T-170 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02311 | 2026-01-27 | 11681-NMDC-T-3321 | 1
114 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON MUTAWA 402 (TRIP-1) | 2800-NN-0114 | AD-165-PL-625047-SHT-001 | 1 | 2 | 2025-11-16 | 2025-11-10 | CSE-2800-PMT-T-137 | 2025-11-10 | 2800-NMDC-E-AO-PMT-T-02095 | 2026-03-25 | 11681-NMDC-T-3450 | 2
115 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON GMS ARTEMIS (TRIP-1) | 2800-NN-0115 | AD-165-PL-625048-SHT-001 | 1 | 2 | 2025-11-16 | 2025-11-10 | CSE-2800-PMT-T-137 | 2025-11-10 | 2800-NMDC-E-AO-PMT-T-02096 | 2026-03-25 | 11681-NMDC-T-3450 | 2
116 | LOWER ZAKUM – SEAFASTENING OF ZK-43A DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA 402 (TRIP-2) | 2800-NN-0116 | AD-165-PL-625049-SHT-001 | 1 | 2 | 2025-11-18 | 2025-11-12 | CSE-2800-PMT-T-138 | 2025-11-13 | 2800-NMDC-E-AO-PMT-T-02112 | 2025-12-04 | 11681-NMDC-T-3184 | 2
117 | LOWER ZAKUM – SEAFASTENING OF ZK-43A DECK EXTENSION MODULES AND MISC. ITEMS ON GMS ARTEMIS (TRIP-2) | 2800-NN-0117 | AD-165-PL-625050-SHT-001 | 1 | 2 | 2025-11-18 | 2025-11-12 | CSE-2800-PMT-T-138 | 2025-11-13 | 2800-NMDC-E-AO-PMT-T-02113 | 2025-12-04 | 11681-NMDC-T-3184 | 2
118 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON MUTAWA 402 (TRIP-3) | 2800-NN-0118 | AD-165-PL-625051-SHT-001 | 1 | 2 | 2025-12-02 | 2025-11-26 | CSE-2800-PMT-T-146 | 2025-11-27 | 2800-NMDC-E-AO-PMT-T-02149 | 2026-04-10 | 11681-NMDC-T-3478 | 4
119 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON GMS ARTEMIS (TRIP-3) | 2800-NN-0119 | AD-165-PL-625052-SHT-001 | 1 | 2 | 2025-12-02 | 2025-11-26 | CSE-2800-PMT-T-146 | 2025-11-27 | 2800-NMDC-E-AO-PMT-T-02149 | 2026-04-10 | 11681-NMDC-T-3478 | 4
120 | LOWER ZAKUM – LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON MUTAWA 402 (TRIP-4) | 2800-NN-0120 | AD-165-PL-625053-SHT-001 | 1 | 2 | 2026-02-24 | 2026-02-18 | CSE-2800-PMT-T-181 | 2026-02-21 | 2800-NMDC-E-AO-PMT-T-02452 | 2026-04-10 | 11681-NMDC-T-3478 | 4
121 | LOWER ZAKUM – LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON GMS ARTEMIS (TRIP-4) | 2800-NN-0121 | AD-165-PL-625054-SHT-001 | 1 | 2 | 2026-02-24 | 2026-02-18 | CSE-2800-PMT-T-181 | 2026-02-21 | 2800-NMDC-E-AO-PMT-T-02452 | 2026-04-10 | 11681-NMDC-T-3478 | 4
122 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON MUTAWA 402 (TRIP-5) | 2800-NN-0122 | AD-165-PL-625055-SHT-001 |  |  | 2027-01-01
123 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON GMS ARTEMIS (TRIP-5) | 2800-NN-0123 | AD-165-PL-625056-SHT-001 |  |  | 2027-01-01
124 | ZK-43A GL-3 SMALL LADDER LIFTING ARRANGEMENT | 2800-NN-0124 | AD-165-PL-625057-SHT-001 | 1 | 2 | 2025-12-10 | 2025-11-19 | CSE-2800-PMT-T-141 | 2025-11-20 | 2800-NMDC-E-AO-PMT-T-02131 | 2025-11-25 | 11681-NMDC-T-3160 | 2
|  |  |  | 2 | 2 |  | 2025-12-04 | CSE-2800-PMT-T-150 | 2025-12-05 | 2800-NMDC-E-AO-PMT-T-02183 | 2025-12-11 | 11681-NMDC-T-3204 | 1
125 | TYPICAL LIFITNG AND INSTALLATION OF MATTRESS BY PLB-648 | 2800-NN-0125 | AD-27-PL-625344-SHT-001 | 1 | 2 | 2025-11-25 | 2025-11-27 | CSE-2800-PMT-T-148 | 2025-11-28 | 2800-NMDC-E-AO-PMT-T-02166 | 2025-12-11 | 11681-NMDC-T-3204 | 4
126 | J-TUBE/RISER CLAMPS REMOVAL AND RE-INSTALLATION DRAWING (CL-3) AT ZK-43A (PLB-648) (LEG-4) WITH WHIP HOIST | 2800-NN-0126 | AD-165-PL-625058-SHT-001 | 1 | 2 | 2026-01-20 | 2025-11-26 | CSE-2800-PMT-T-145 | 2025-11-27 | 2800-NMDC-E-AO-PMT-T-02163 | 2026-01-15 | 11681-NMDC-T-3296 | 1
|  |  |  | 2 | 2 |  | 2026-01-19 | CSE-2800-PMT-T-170 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02311 | 2026-01-27 | 11681-NMDC-T-3321 | 1
127 | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-1) | 2800-NN-0127 | AD-164-PL-625019-SHT-001 | 1 | 2 | 2025-12-08 | 2025-12-08 | CSE-2800-PMT-T-151 | 2025-12-10 | 2800-NMDC-E-AO-PMT-T-02188 | 2026-03-25 | 11681-NMDC-T-3450 | 2
128 | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-1) | 2800-NN-0128 | AD-164-PL-625020-SHT-001 |  |  | 2027-01-01
129 | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-2) | 2800-NN-0129 | AD-164-PL-625021-SHT-001 | 1 | 2 | 2025-12-31 | 2025-12-22 | CSE-2800-PMT-T-158 | 2025-12-22 | 2800-NMDC-E-AO-PMT-T-02244 | 2026-03-25 | 11681-NMDC-T-3450 | 2 | [5 empty] | CUTLIST DRG. SENT TO FAB. SHOP ON 11/12/25 REF. CSE-OF-2800-T-023
130 | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-2) | 2800-NN-0130 | AD-164-PL-625022-SHT-001 | 1 | 2 | 2025-12-31 | 2025-12-22 | CSE-2800-PMT-T-158 | 2025-12-22 | 2800-NMDC-E-AO-PMT-T-02245 | 2026-03-25 | 11681-NMDC-T-3450 | 2 | [5 empty] | CUTLIST DRG. SENT TO FAB. SHOP ON 16/12/25 REF. CSE-OF-2800-T-024
131 | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-3) | 2800-NN-0131 | AD-164-PL-625023-SHT-001 | 1 | 2 | 2026-01-09 | 2026-01-06 | CSE-2800-PMT-T-165 | 2026-01-07 | 2800-NMDC-E-AO-PMT-T-02287
|  |  |  | 2 | 2 | 2026-02-21 | 2026-02-18 | CSE-2800-PMT-T-181 | 2026-02-21 | 2800-NMDC-E-AO-PMT-T-02453 | 2026-03-25 | 11681-NMDC-T-3450 | 2
132 | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-3) | 2800-NN-0132 | AD-164-PL-625024-SHT-001 | 1 | 2 | 2026-01-09 | 2026-01-06 | CSE-2800-PMT-T-165 | 2026-01-07 | 2800-NMDC-E-AO-PMT-T-02287 | 2026-03-25 | 11681-NMDC-T-3450 | 2
133 | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-4) | 2800-NN-0133 | AD-164-PL-625025-SHT-001 |  |  | 2027-01-01
134 | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-4) | 2800-NN-0134 | AD-164-PL-625026-SHT-001 |  |  | 2027-01-01
135 | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-5) | 2800-NN-0135 | AD-164-PL-625027-SHT-001 |  |  | 2027-01-01
136 | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-5) | 2800-NN-0136 | AD-164-PL-625028-SHT-001 |  |  | 2027-01-01
137 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZWSC-GIP TO ZK-50 @ ZWSC-GIP (GL-1) | 2800-NN-0137 | AD-447-PL-625036-SHT-001 | 1 | 2 | 2025-12-24 | 2025-12-16 | CSE-2800-PMT-T-154 | 2025-12-17 | 2800-NMDC-E-AO-PMT-T-02223 | 2025-12-19 | 11681-NMDC-T-3251 | 4
138 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZK-43A TO ZK-45 @ ZK-45 (GL-3) | 2800-NN-0138 | AD-165-PL-625060-SHT-001 | 1 | 2 | 2025-12-26 | 2025-12-22 | CSE-2800-PMT-T-157 | 2025-12-22 | 2800-NMDC-E-AO-PMT-T-02242 | 2026-01-14 | 11681-NMDC-T-3292 | 1
139 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZWSC-GIP TO ZK-50 @ ZK-50 (GL-1) | 2800-NN-0139 | AD-447-PL-625037-SHT-001 | 1 | 2 | 2026-03-13 | 2026-01-19 | CSE-2800-PMT-T-172 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02314 | 2026-01-27 | 11681-NMDC-T-3321 | 1
|  |  |  | 2 | 2 |  | 2026-03-09 | CSE-2800-PMT-T-190 | 2026-03-11 | 2800-NMDC-E-AO-PMT-T-02507 | 2026-03-25 | 11681-NMDC-T-3450 | 1
140 | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZK-50 TO ZK-43A @ ZK-50 (GL-2) | 2800-NN-0140 | AD-166-PL-625050-SHT-001 | 1 | 2 | 2026-02-19 | 2026-02-11 | CSE-2800-PMT-T-179 | 2026-02-13 | 2800-NMDC-E-AO-PMT-T-02428 | 2026-02-20 | 11681-NMDC-T-3385 | 2
141 | ANODE INSTALLATION AT NWIP BY SAFEEN PEARL | 2800-NN-0141 | AD-27-PL-625349-SHT-001 | 1 | 2 | 2026-01-26 | 2026-01-22 | CSE-2800-PMT-T73 | 2026-01-22 | 2800-NMDC-E-AO-PMT-T-02326 | 2026-02-20 | 11681-NMDC-T-3385 | 2
142 | TYPICAL LIFTING & INSTALLATION OF ANODE BY PLB-648 (OPTION-2) | 2800-NN-0142 | AD-27-PL-625350-SHT-001 | 1 | 2 | 2026-01-27 | 2026-01-19 | CSE-2800-PMT-T-171 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02315 | 2026-01-27 | 11681-NMDC-T-3321 | 1
143 | TYPICAL J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-43A (LEG-4) (PLB-648 - WHIP HOIST) | 2800-NN-0143 | AD-165-PL-625061-SHT-001 | 1 | 2 | 2026-01-23 | 2026-01-19 | CSE-2800-PMT-T-169 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02309 | 2026-01-21 | 11681-NMDC-T-3301 | 1
144 | SINGLE PIECE J-TUBE LIFTING AND INSTALLATION DRAWING AT ZK-43A (LEG-4) (PLB-648 - WHIP HOIST) | 2800-NN-0144 | AD-165-PL-625062-SHT-001 | 1 | 2 | 2026-01-27 | 2026-01-19 | CSE-2800-PMT-T-169 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02309 | 2026-01-21 | 11681-NMDC-T-3301 | 1
145 | SINGLE PIECE J-TUBE REMOVAL AND RE-INSTALLATION DRAWING (CL-2) AT ZK-43A (PLB-648- WHIP HOIST) | 2800-NN-0145 | AD-165-PL-625063-SHT-001 | 1 | 2 | 2026-01-23 | 2026-01-19 | CSE-2800-PMT-T-169 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02309 | 2026-01-21 | 11681-NMDC-T-3301 | 1
146 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF MATTRESS, SPOOL & MISC. ITEMS @ ASTRO-251 | 2800-NN-0146 | AD-27-Z-000001-SHT-001 |  |  | 2027-01-01
147 | LOWER ZAKUM - J-TUBE/RISER CLAMPS REMOVAL AND RE-INSTALLATION DRAWING (CL-2) AT ZK-43A (PLB-648) (LEG-1) WITH MAIN HOIST | 2800-NN-0147 | AD-165-Z-800019-SHT-001 | 1 | 2 | 2026-01-22 | 2026-01-19 | CSE-2800-PMT-T-169 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02310 | 2026-01-27 | 11681-NMDC-T-3321 | 1
148 | LOWER ZAKUM - J-TUBE/RISER CLAMPS REMOVAL AND RE-INSTALLATION DRAWING (CL-3) AT ZK-43A (PLB-648) (LEG-4) WITH MAIN HOIST | 2800-NN-0148 | AD-165-Z-800020-SHT-001 | 1 | 2 | 2026-01-22 | 2026-01-19 | CSE-2800-PMT-T-169 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02310 | 2026-01-27 | 11681-NMDC-T-3321 | 1
149 | LOWER ZAKUM - TYPICAL LIFTING & INSTALLATION / DEMOLITION & REMOVAL OF RISER /J-TUBE CLAMPS BY PLB-648 WITH MAIN HOIST | 2800-NN-0149 | AD-27-Z-000002-SHT-001 | 1 | 2 | 2026-02-02 | 2026-01-19 | CSE-2800-PMT-T-169 | 2026-01-19 | 2800-NMDC-E-AO-PMT-T-02310 | 2026-01-27 | 11681-NMDC-T-3321 | 1
|  |  |  | 2 | 3 |  | 2026-01-30 | CSE-2800-PMT-T-175 | 2026-02-06 | 2800-NMDC-E-AO-PMT-T-02395 | 2026-04-20 | 11681-NMDC-T-3516 | 2
150 | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-1) | 2800-NN-0150 | AD-447-Z-800013-SHT-001 | 1 | 2 | 2026-04-02 | 2026-03-30 | CSE-2800-PMT-T-201 | 2026-04-01 | 2800-NMDC-E-AO-PMT-T-02547 | 2026-04-10 | 11681-NMDC-T-3478 | 4
151 | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-1) | 2800-NN-0151 | AD-447-Z-800014-SHT-001 | 1 | 2 | 2026-04-02 | 2026-03-30 | CSE-2800-PMT-T-201 | 2026-04-01 | 2800-NMDC-E-AO-PMT-T-02548 | 2026-04-10 | 11681-NMDC-T-3478 | 4
152 | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-2) | 2800-NN-0152 | AD-447-Z-800015-SHT-001 | 1 | 2 | 2026-04-12 | 2026-04-09 | CSE-2800-PMT-T-205 | 2026-04-10 | 2800-NMDC-E-AO-PMT-T-02582 | 2026-04-15 | 11681-NMDC-T-3495 | 4
153 | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-2) | 2800-NN-0153 | AD-447-Z-800016-SHT-001 | 1 | 2 | 2026-04-23 | 2026-04-20 | CSE-2800-PMT-T-209 | 2026-04-21 | 2800-NMDC-E-AO-PMT-T-02610 | 2026-06-03 | 11681-NMDC-T-3602 | 4
154 | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-3) | 2800-NN-0154 | AD-447-Z-800017-SHT-001 |  |  | 2027-01-01
155 | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-3) | 2800-NN-0155 | AD-447-Z-800018-SHT-001 | 1 | 2 | 2026-04-30 | 2026-04-29 | CSE-2800-PMT-T-212 | 2026-05-01 | 2800-NMDC-E-AO-PMT-T-02648 | 2026-06-03 | 11681-NMDC-T-3602 | 4
156 | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-4) | 2800-NN-0156 | AD-447-Z-800019-SHT-001 | 1 | 2 | 2026-05-31 | 2026-05-22 | CSE-2800-PMT-T-224 | 2026-05-25 | 2800-NMDC-E-AO-PMT-T-02720 | 2026-06-10 | 11681-NMDC-T-3615 | 4
157 | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-4) | 2800-NN-0157 | AD-447-Z-800020-SHT-001 |  |  | 2026-10-01
158 | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-5) | 2800-NN-0158 | AD-447-Z-800021-SHT-001 |  |  | 2026-10-15
159 | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-5) | 2800-NN-0159 | AD-447-Z-800022-SHT-001 |  |  | 2026-10-30
160 | LOWER ZAKUM – 6” BUCKLE DETECTOR FOR GL-4 GAS LIFT PIPELINE | 2800-NN-0160 | AD-27-Z-000125-SHT-001 | 1 | 2 | 2026-04-25 | 2026-03-05 | CSE-2800-PMT-T-187 | 2026-03-06 | 2800-NMDC-E-AO-PMT-T-02492 | 2026-03-25 | 11681-NMDC-T-3450 | 2
|  |  |  | 2 | 2 |  | 2026-04-23 | CSE-2800-PMT-T-210 | 2026-04-24 | 2800-NMDC-E-AO-PMT-T-02620 | 2026-06-10 | 11681-NMDC-T-3615 | 2
161 | MISC. ITEM LIFTING AT GIP WITH MP-02 | 2800-NN-0161 | AD-447-Z-800023-SHT-001 |  |  | 2026-03-11 | [12 empty] | DRG.SERVER ONLY SM EMAIL 11/03
162 | MISC. ITEM LIFTING AT GIP WITH PLB-648 | 2800-NN-0162 | AD-447-Z-800024-SHT-001 |  |  | 2026-03-11 | [12 empty] | DRG.SERVER ONLY SM EMAIL 11/03
163 | 10" SPOOL LIFTING AND INSTALLATION DRAWING AT ZK-47 (PLB-648) | 2800-NN-0163 | AD-164-Z-800013-SHT-001 | 1 | 2 | 2026-03-28 | 2026-03-23 | CSE-2800-PMT-T-197 | 2026-03-25 | 2800-NMDC-E-AO-PMT-T-02538 | 2026-04-10 | 11681-NMDC-T-3482 | 2
164 | LOWER ZAKUM – SEAFASTENING OF ZK- 126.5 DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-2) | 2800-NN-0164 | AD-312-Z-800013-SHT-001 | 1 | 2 | 2026-03-22 | 2026-03-17 | CSE-2800-PMT-T-193 | 2026-03-18 | 2800-NMDC-E-AO-PMT-T-02530 | 2026-03-24 | 11681-NMDC-T-3446 | 2
165 | LOWER ZAKUM – SEAFASTENING OF ZK- 126.5 DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-2) | 2800-NN-0165 | AD-312-Z-800014-SHT-001 | 1 | 2 | 2026-03-22 | 2026-03-17 | CSE-2800-PMT-T-193 | 2026-03-18 | 2800-NMDC-E-AO-PMT-T-02530 | 2026-03-24 | 11681-NMDC-T-3446 | 2
166 | LOWER ZAKUM – SEAFASTENING OF ZK 126.5 DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-1) | 2800-NN-0166 | AD-312-Z-800015-SHT-001 | 1 | 2 | 2026-03-22 | 2026-03-17 | CSE-2800-PMT-T-193 | 2026-03-18 | 2800-NMDC-E-AO-PMT-T-02530 | 2026-03-24 | 11681-NMDC-T-3446 | 2
167 | LOWER ZAKUM – SEAFASTENING OF ZK 126.5 DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-1) | 2800-NN-0167 | AD-312-Z-800016-SHT-001 | 1 | 2 | 2026-03-22 | 2026-03-17 | CSE-2800-PMT-T-193 | 2026-03-18 | 2800-NMDC-E-AO-PMT-T-02530 | 2026-03-24 | 11681-NMDC-T-3446 | 2
168 | LOWER ZAKUM – SEAFASTENING OF ZK- 126.5 DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-3) | 2800-NN-0168 | AD-312-Z-800017-SHT-001 | 1 | 2 | 2026-03-22 | 2026-03-17 | CSE-2800-PMT-T-196 | 2026-03-18 | 2800-NMDC-E-AO-PMT-T-02531 | 2026-04-10 | 11681-NMDC-T-3478 | 4
169 | LOWER ZAKUM – SEAFASTENING OF ZK- 126.5 DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-3) | 2800-NN-0169 | AD-312-Z-800018-SHT-001 | 1 | 2 | 2026-03-22 | 2026-03-17 | CSE-2800-PMT-T-196 | 2026-03-18 | 2800-NMDC-E-AO-PMT-T-02531 | 2026-04-10 | 11681-NMDC-T-3478 | 4
170 | REMOVAL & INSTALLATION OF STAIRCASE AT ZK-50 | 2800-NN-0170 | AD-166-Z-800018-SHT-001 | 1 | 2 | 2026-05-24 | 2026-05-19 | CSE-2800-PMT-T-219 | 2027-05-20 | 2800-NMDC-E-AO-PMT-T-02702
171 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & CC PIPES @ ES-281 | 2800-NN-0171 | AD-27-Z-000171-SHT-001 |  |  | 2026-08-01 | [12 empty] | REV-1 SERVER ONLY
172 | LOWER ZAKUM – SEAFASTENING OF ZK-50 DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA-402 - TRIP-2 | 2800-NN-0172 | AD-166-Z-800023-SHT-001 | 1 | 2 | 2026-08-01 | 2026-06-23 | CSE-2800-PMT-T-230 | 2026-06-23 | 2800-NMDC-E-AO-PMT-T-02792
173 | LOWER ZAKUM – SEAFASTENING OF ZK-50 DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA-402 - TRIP-3 | 2800-NN-0173 | AD-166-Z-800024-SHT-001 | 1 | 2 | 2026-08-01 | 2026-06-23 | CSE-2800-PMT-T-230 | 2026-06-23 | 2800-NMDC-E-AO-PMT-T-02793
174 | LOWER ZAKUM – SEAFASTENING ARRANGEMENT OF ZK-50 IN GMS ARTEMIS (TRIP-2) | 2800-NN-0174 | AD-166-Z-800025-SHT-001 | 1 | 2 | 2026-08-01 | 2026-06-23 | CSE-2800-PMT-T-230 | 2026-06-23 | 2800-NMDC-E-AO-PMT-T-02794
175 | LOWER ZAKUM – SEAFASTENING DETAILS OF ZK-50 DECK EXTENSION MODULES AND MISC. ITEMS ON ARTEMIS (TRIP-1) | 2800-NN-0175 | AD-166-Z-800026-SHT-001 | 1 | 2 | 2026-08-01 | 2026-06-23 | CSE-2800-PMT-T-230 | 2026-06-23 | 2800-NMDC-E-AO-PMT-T-02795
176 | LOWER ZAKUM – LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS (GL-4) ON ES-282 (TRIP-2) | 2800-NN-0176 | AD-27-Z-000172-SHT-001 | 1 | 2 |  | 2026-07-24 | CSE-2800-PMT-T-242 | 2026-07-24 | 2800-NMDC-E-AO-PMT-T-02870
177 | LOWER ZAKUM – LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SPOOLS, GA & MISC. ITEMS ON ES-281 | 2800-NN-0177 | AD-27-Z-000173-SHT-001 | 1 | 2 |  | 2026-08-04 | CSE-2800-PMT-T-246 | 2026-08-04 | 2800-NMDC-E-AO-PMT-T-02889
178 | LOWER ZAKUM – TEMPORARY KNEE BRACE DETAILS FOR RISER / SPOOL LIFITNG OF 6'' GAS LIFT PIPELINE FOR GL-4 AT ZK-45 | 2800-NN-0178 | AD-162-Z-800021-SHT-001 | 1 | 2 |  | 2026-07-17 | CSE-2800-PMT-T-237 | 2026-07-27 | 2800-NMDC-E-AO-PMT-T-02847
179 | LOWER ZAKUM – TYPICAL LIFTING & HANDLING ARRANGEMENT FOR 6" PIPE JOINTS BY PLB-648 | 2800-NN-0179 | AD-27-Z-000174-SHT-001 | 1 | 2 |  | 2026-07-14 | CSE-2800-PMT-T-236 | 2026-07-15 | 2800-NMDC-E-AO-PMT-T-02839 | 2026-07-16 | 11681-NMDC-T-3681 | 2
180 | LOWER ZAKUM – TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY PLB-648 | 2800-NN-0180 | AD-27-Z-000175-SHT-001 | 1 | 2 |  | 2026-07-14 | CSE-2800-PMT-T-236 | 2026-07-15 | 2800-NMDC-E-AO-PMT-T-02839 | 2026-07-16 | 11681-NMDC-T-3681 | 2
181 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (GL-4) & PLB 648 BARGE EXTENSION ON GAC-68 CB | 2800-NN-0181 | AD-27-Z-000176-SHT-001 | 1 | 2 |  | 2026-07-24 | CSE-2800-PMT-T-241 | 2026-07-27 | 2800-NMDC-E-AO-PMT-T-02870
182 | LOWER ZAKUM – SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA-402 (TRIP-1) (SHT. 1 TO 6) | 2800-NN-0182 | AD-463-Z-800017-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-255 | 08-09-2026 | 2800-NMDC-E-AO-PMT-T-02955
183 | LOWER ZAKUM – SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON GMS ARTEMIS (TRIP-1) (SHT. 1 TO 7) | 2800-NN-0183 | AD-463-Z-800018-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-255 | 08-09-2026 | 2800-NMDC-E-AO-PMT-T-02955
184 | LOWER ZAKUM – SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA-402 (TRIP-2) (SHT. 1 TO 3) | 2800-NN-0184 | AD-463-Z-800019-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-255
185 | ZAKUM – SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON GMS ARTEMIS (TRIP-2) (SHT. 1 TO 3) | 2800-NN-0185 | AD-463-Z-800020-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-255
186 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZCSC NWIP MODULES ON MUTAWA 402 (TRIP-3) | 2800-NN-0186 | AD-463-Z-800021-SHT-001 | SM | remarks | [13 empty] | server only
187 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZCSC NWIP MODULES ON GMS ARTEMIS (TRIP-3) | 2800-NN-0187 | AD-463-Z-800022-SHT-001 | SM | remarks | [13 empty] | server only
188 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZCSC NWIP MODULES ON MUTAWA 402 (TRIP-4) | 2800-NN-0188 | AD-463-Z-800023-SHT-001 | SM | remarks | [13 empty] | server only
189 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZCSC NWIP MODULES ON GMS ARTEMIS (TRIP-4) | 2800-NN-0189 | AD-463-Z-800024-SHT-001 | SM | remarks | [13 empty] | server only
190 | LOWER ZAKUM – SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA-402 (TRIP-5) | 2800-NN-0190 | AD-463-Z-800025-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-255 | 08-09-2026 | 2800-NMDC-E-AO-PMT-T-02955
191 | ZAKUM – SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON GMS ARTEMIS (TRIP-5) (SHT. 1 TO 6) | 2800-NN-0191 | AD-463-Z-800026-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-255 | 08-09-2026 | 2800-NMDC-E-AO-PMT-T-02955
192 | ZAKUM – SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON GMS ARTEMIS (TRIP-6) (SHT. 1 TO 3) | 2800-NN-0192 | AD-463-Z-800027-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-255 | 08-09-2026 | 2800-NMDC-E-AO-PMT-T-02954
193 | ZAKUM – SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA-402 (TRIP-7) (SHT. 1 TO 2) | 2800-NN-0193 | AD-463-Z-800028-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-255 | 08-09-2026 | 2800-NMDC-E-AO-PMT-T-02954
194 | ZAKUM – SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON GMS ARTEMIS (TRIP-7) (SHT. 1 TO 2) | 2800-NN-0194 | AD-463-Z-800029-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-255 | 08-09-2026 | 2800-NMDC-E-AO-PMT-T-02954
195 | SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON GMS ARTEMIS (TRIP-8) (SHT. 1 TO 7) | 2800-NN-0195 | AD-463-Z-800030-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-256 | 08-09-2026 | 2800-NMDC-E-AO-PMT-T-02954
196 | ZAKUM – SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA-402 (TRIP-9) (SHT. 1 TO 2) | 2800-NN-0196 | AD-463-Z-800031-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-256 | 08-09-2026 | 2800-NMDC-E-AO-PMT-T-02954
197 | SEAFASTENING OF ZCSC NWIP DECK EXTENSION MODULES AND MISC. ITEMS ON GMS ARTEMIS (TRIP-9) (SHT. 1 TO 2) | 2800-NN-0197 | AD-463-Z-800032-SHT-001 | 1 | 2 |  | 08-09-2026 | CSE-2800-PMT-T-256 | 08-09-2026 | 2800-NMDC-E-AO-PMT-T-02954
198 | TEMPORARY KNEE BRACE DETAILS FOR RISER / SPOOL LIFITNG OF 6'' GAS LIFT PIPELINE FOR GL-4 AT ZK-56 | 2800-NN-0198 | AD-168-Z-800017-SHT-001
199 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (GL-4) & FOAM FLOATERS ON ES-282 CB | 2800-NN-0199 | TBA | 1 |  |  | 2026-09-07 | CSE-2800-PMT-T-252 | 2026-09-07 | 2800-NMDC-E-AO-PMT-T-02947 | [8 empty] | reissued on 07-09

## Sketch
Project 2800
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2800 | OFO-P2800-SK-T-001 | SAFEEN OSV PEARL CABLE LAYOUT ARRANGEMENT | 1 | A | √ | √ | 29/07/2024 | AKS | @
2 | 2800 | OFO-P2800-SK-T-002 | GROUTING EQUIPMENT LOADOUT ON ZAKHER PIONEER DECK | 1 | A | √ | √ | 13/01/2025 | JH | @
3 | 2800 | OFO-P2800-SK-T-003 | GROUTING EQUIPMENT LOADOUT ON MUTAWA -13 DECK | 1 | A | √ | √ | 13/01/2025 | JH | @
4 | 2800 | OFO-P2800-SK-T-004 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON MP-02 (Trip-1) | 1 | A | √ | √ | 25/02/2025 | JH | @
5 | 2800 | OFO-P2800-SK-T-005 | LIFTING & OFFLOADING OF KOBELCO SKC 1350 FROM JETTY TO PLB-648 MAIN DECK | 1 | B | √ | √ | 18/04/2025 | REY | @
6 | 2800 | OFO-P2800-SK-T-006 | DETAILS OF TEMPORARY SUPPORT AT KP 4.548 (GL-2) 6” GAS LIFT SPOOL FROM ZK-50 TO ZK-43A(TS-01) |  |  |  |  | 12/04/2025 | REY
7 | 2800 | OFO-P2800-SK-T-007 | DETAILS OF TEMPORARY SUPPORT AT KP 4.548 (GL-2) 6” GAS LIFT SPOOL FROM ZK-50 TO ZK-43A(TS-02) |  |  |  |  | 12/04/2025 | REY
8 | 2800 | OFO-P2800-SK-T-008 | DETAILS OF TEMPORARY SUPPORT AT KP 4.548 (GL-2) 6” GAS LIFT SPOOL FROM ZK-50 TO ZK-43A(TS-03) |  |  |  |  | 12/04/2025 | REY
9 | 2800 | OFO-P2800-SK-T-009 | PIPELAY PROFILE WITH STINGER | 1 | C | √ | √ | 17/09/2025 | AMK | @
10 | 2800 | OFO-P2800-SK-T-010 | PIPELAY PROFILE WITH OUT STINGER FOR GL-04 | 1 | C | √ | √ | 26/01/2026 | LEO | @
11 | 2800 | OFO-P2800-SK-T-011 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF KOBELCO CKS 1350 ON PLB-648 MAIN DECK |  |  |  |  | 30/04/2025 | AMEER
12 | 2800 | OFO-P2800-SK-T-012 | Lashing details of Kobelco Crane on PLB-648 main deck | 1 | A | √ | √ | 03/05/2025 | NAR | @
13 | 2800 | OFO-P2800-SK-T-013 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY PLB-648 | 2 | D | √ | √ | 07/08/2025 | MF | @
14 | 2800 | OFO-P2800-SK-T-014 | Foam Float Straps for 6"Pipeline | 1 | A | √ | √ | 04/06/2025 | NHE / VDA | @
15 | 2800 | OFO-P2800-SK-T-015 | Foam Float Straps for 10” Pipeline | 1 | A | √ | √ | 04/06/2025 | NHE / VDA | @
16 | 2800 | OFO-P2800-SK-T-016 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT USING PLB-648 |  |  |  |  | 29/05/2025 | HZD
17 | 2800 | OFO-P2800-SK-T-017 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 800MM) | 1 | B, 0 | √ | √ | 13/06/2025 | CDG | @
18 | 2800 | OFO-P2800-SK-T-018 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 1100MM) | 1 | B, 0 | √ | √ | 13/06/2025 | CDG | @
19 | 2800 | OFO-P2800-SK-T-019 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 1300MM) | 1 | B, 0 | √ | √ | 13/06/2025 | CDG | @
20 | 2800 | OFO-P2800-SK-T-020 | PROTECTOR DETAILS FOR 4" PIPELINE DURING LAYDOWN | 1 | A | √ | √ | 10/06/2025 | CDG | @
21 | 2800 | OFO-P2800-SK-T-021 | START-UP ARRANGEMENT FOR 10'' WI-3 AT ZK-372 WITH PLB-648 | 1 | B | √ | √ | 07/07/2025 | NEH | @
22 | 2800 | OFO-P2800-SK-T-022 | TYPICAL ABANDONMENT & RECOVERY ARRANGEMENT AT FINAL STAGE | 1 | A | √ | √ | 11/06/2025 | HZD | @
23 | 2800 | OFO-P2800-SK-T-023 | TRANSITON JOINTS FOR 10" WI PIPELINES | 1 | A | √ | √ | 18/06/2025 | VDA | @
24 | 2800 | OFO-P2800-SK-T-024 | TEMPORARY SUPPORT DETAILS FOR 4"/6" PIPELINE DURING LAYDOWN | 1 | A,0 | √ | √ | 17/06/2025 | CDG | @
25 | 2800 | OFO-P2800-SK-T-025 | TYPICAL ABANDONMENT & RECOVERY ARRANGEMENT WITHOUT STINGER AT FINAL STAGE | 1 | A | √ | √ | 25/06/2025 | AMEER | @
26 | 2800 | OFO-P2800-SK-T-026 | CABLE TOWER DETAILS - SAFEEN PEARL | 4 | A | √ | √ | 19/06/2025 | SKT | @
27 | 2800 | OFO-P2800-SK-T-027 | SEAFASTENING GRILLAGE LAYOUT & DETAILS FOR SAFEEN PEARL | 2 | A | √ | √ | 19/06/2025 | SKT | @
28 | 2800 | OFO-P2800-SK-T-028 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR TEMPORARY SUPPORT | 1 | D | √ | √ | 11/07/2025 | MF | @
29 | 2800 | OFO-P2800-SK-T-029 | FLOATS DISCONNECTION | 2 | A | √ | √ | 20/06/2025 | NHE | @
30 | 2800 | OFO-P2800-SK-T-030 | LIFTING & INSTALLATION OF PLB-648 STERN EXTENSION PLATFORM | 2 | B | √ | √ | 29/10/2025 | CDG | @
31 | 2800 | OFO-P2800-SK-T-031 | DAVIT LIFTING STOPS & AIRBAGS SPACING DETAILS FOR WI-3 AT ZK-47 | 1 | B | √ | √ | 30/10/2025 | SKS | @
32 | 2800 | OFO-P2800-SK-T-032 | DAVIT LIFTING STOPS & AIRBAGS SPACING DETAILS FOR WI-4 AT ZK-372 | 1 | B | √ | √ | 27/10/2025 | SKS | @
33 | 2800 | OFO-P2800-SK-T-033 | DMA START-UP ARRANGEMENT FOR PROPOSED (WI-4) 10" W.I PIPELINE FROM ZK-372 TO ZK-126.5/65 | 2 | C | √ | √ | 28/07/2025 | SKS | @
34 | 2800 | OFO-P2800-SK-T-034 | HBC START-UP ARRANGEMENT FOR PROPOSED 6" PIPELINE (GL-1) FROM ZWSC-GIP TO ZK-50 | 1 | B | √ | √ | 22/08/2025 | ENH | @
35 | 2800 | OFO-P2800-SK-T-035 | TYPICAL CABLE PULLING ARRANGEMENT AT ZK43-A (WITH TOPSIDE) | 2 | C | √ | √ | 23/09/2025 | SKT | @
36 | 2800 | OFO-P2800-SK-T-036 | TYPICAL CABLE PULLING ARRANGEMENT AT WHT-2 (WITHOUT TOPSIDE) | 2 | B | √ | √ | 12/09/2025 | SKT | @
37 | 2800 | OFO-P2800-SK-T-037 | TYPICAL PIPELINE PROTECTOR / DOGHOUSE | 1 + 6 | B,0, C | √ | √ | 24/07/2025 | SKT | @
38 | 2800 | OFO-P2800-SK-T-038 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 1250MM) | 1 + 5 | A, 0 | √ | √ | 14/07/2025 | VDA | @ | CUTLIST ISSUED
39 | 2800 | OFO-P2800-SK-T-039 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 1150MM) | 1 + 5 | A, 0 | √ | √ | 04/08/2025 | VDA | @ | CUTLIST ISSUED
40 | 2800 | OFO-P2800-SK-T-040 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 750MM) | 1+ 3 | A, 0 | √ | √ | 14/07/2025 | VDA | @ | CUTLIST ISSUED
41 | 2800 | OFO-P2800-SK-T-041 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 350MM) | 1+ 3 | A, 0 | √ | √ | 14/07/2025 | VDA | @ | CUTLIST ISSUED
42 | 2800 | OFO-P2800-SK-T-042 | DETAILS OF TEMPORARY SUPPORT (H1250 mm X L8500 mm) | 1 + 5 | A, 0 | √ | √ | 21/07/2025 | VDA | @ | CUTLIST ISSUED
43 | 2800 | OFO-P2800-SK-T-043 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 300MM) |  |  |  |  | 27/06/2025 | VDA
44 | 2800 | OFO-P2800-SK-T-044 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 150MM) |  |  |  |  | 27/06/2025 | VDA
45 | 2800 | OFO-P2800-SK-T-045 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 900MM) | 1+ 5 | B,0 | √ | √ | 10/07/2025 | VDA | @ | CUTLIST ISSUED
46 | 2800 | OFO-P2800-SK-T-046 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 750MM) | 1+ 3 | B,0 | √ | √ | 04/08/2025 | VDA | @' | CUTLIST ISSUED
47 | 2800 | OFO-P2800-SK-T-047 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 200MM) | 1 | A | √ | √ | 01/07/2025 | VDA | @
48 | 2800 | OFO-P2800-SK-T-048 | STORAGE QUADRANT 1.5M RADIUS FOR 12’’ J-TUBE | 1 + 9 | A, 0 | √ | √ | 08/07/2025 | SKT | @
49 | 2800 | OFO-P2800-SK-T-049 | TYPICAL TUGGER SKID DETAILS FOR CABLE PULLING | 1 + 4 | A, 0 | √ | √ | 08/07/2025 | SKT | @
50 | 2800 | OFO-P2800-SK-T-050 | TEMPORARY HANG OFF CLAMP FOR 95 DIA CABLE | 1 | A | √ | √ | 27/07/2025 | SKT | @
51 | 2800 | OFO-P2800-SK-T-051 | A-FRAME ARRANGEMENT FOR CABLE PULLING | 1 + 8 | B, 0 | √ | √ | 15/12/2025 | LRA | @
52 | 2800 | OFO-P2800-SK-T-052 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE MATTRESSES @ MARCAP SIBA (TRIP-1) | 1 | A | √ | √ | 18/07/2025 | JH | @
53 | 2800 | OFO-P2800-SK-T-053 | FOAM FLOAT STRAPS FOR 20" PIPELINE | 1 | B | √ | √ | 16/07/2025 | SKS | @
54 | 2800 | OFO-P2800-SK-T-054 | TEMPORARY SUPPORT ARRANGEMENT FOR GL-2 CROSSING (CR-42) | 1 | A | √ | √ | 17/07/2025 | VDA | @
55 | 2800 | OFO-P2800-SK-T-055 | TEMPORARY SUPPORT ARRANGEMENT FOR GL-2 CROSSING (CR-44 & CR45) | 1 | B | √ | √ | 22/09/2025 | VDA | @
56 | 2800 | OFO-P2800-SK-T-056 | DMA START-UP ARRANGEMENT FOR PROPOSED (WI-4) 10" W.I PIPELINE AT ZK-372 | 2 | B | √ | √ | 28/07/2025 | SKS | @
57 | 2800 | OFO-P2800-SK-T-057 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR TEMPORARY SUPPORT USING MP-01 | 1 | A | √ | √ | 23/07/2025 | MF | @
58 | 2800 | OFO-P2800-SK-T-058 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR TEMPORARY SUPPORT USING MP-02 | 1 | A | √ | √ | 23/07/2025 | MF | @
59 | 2800 | OFO-P2800-SK-T-059 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR PIPELINE PROTECTOR USING MP-01 | 1 | A | √ | √ | 28/07/2025 | VDA | @
60 | 2800 | OFO-P2800-SK-T-060 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR PIPELINE PROTECTOR USING MP-02 | 1 | A | √ | √ | 28/07/2025 | VDA | @
61 | 2800 | OFO-P2800-SK-T-061 | 6" Marker Joint detail drawing | 1 | A | √ | √ | 30/07/2025 | SKS | @
62 | 2800 | OFO-P2800-SK-T-062 | SAFEEN PEARL CABLE LAYOUT ARRANGEMENT | 1 | B | √ | √ | 06/10/2025 | CDG | @
63 | 2800 | OFO-P2800-SK-T-063 | AIR BAG ARRANGEMENTS FOR 6" & 10” PIPELINE | 16 | A | √ | √ | 12/08/2025 | HZD | @
64 | 2800 | OFO-P2800-SK-T-064 | GALVANIZED SHEER ROLLER FRAME | 1 | A | √ | √ | 06/08/2025 | SKS | @
65 | 2800 | OFO-P2800-SK-T-065 | LIFTING & OFFLOADING OF STINGER-10A BY SAPURA-1200 | 1 | A | √ | √ | 06/08/2025 | CDG | @
66 | 2800 | OFO-P2800-SK-T-066 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR 6” PIPE JOINTS BY PLB-648 | 3 | B | √ | √ | 20/08/2025 | MF | @
67 | 2800 | OFO-P2800-SK-T-067 | PRE COMM-EQUIPMENT LAYOUT ON MUTAWA 11 | 1 | A | √ | √ | 08/08/2025 | SKT | @
68 | 2800 | OFO-P2800-SK-T-068 | DMA START-UP ARRANGEMENT FOR 6" GL-2 PIPELINE AT ZK-50 | 2 | B | √ | √ | 02/09/2025 | ENH | @
69 | 2800 | OFO-P2800-SK-T-069 | TYPICAL CABLE PULLING ARRANGEMENT AT ZK-88 (WITH TOPSIDE) | 2 | A | √ | √ | 13/08/2025 | SKT | @
70 | 2800 | OFO-P2800-SK-T-070 | TYPICAL CABLE PULLING ARRANGEMENT AT ZK-307 (WITHOUT TOPSIDE) |  |  |  |  | 13/08/2025 | SKT
71 | 2800 | OFO-P2800-SK-T-071 | TYPICAL CABLE PULLING ARRANGEMENT AT ZK-329 (WITH TOPSIDE) |  |  |  |  | 13/08/2025 | SKT
72 | 2800 | OFO-P2800-SK-T-072 | TYPICAL CABLE PULLING ARRANGEMENT AT ZK-44 (WITHOUT TOPSIDE) |  |  |  |  | 13/08/2025 | SKT
73 | 2800 | OFO-P2800-SK-T-073 | TYPICAL CABLE PULLING ARRANGEMENT AT ZK-126.5 (WITH TOPSIDE) |  |  |  |  | 13/08/2025 | SKT
74 | 2800 | OFO-P2800-SK-T-074 | DAVIT LIFTING STROPS & AIR BAGS SPACING DETAILS FOR 6 INCHES GL-1 AT ZK-50 | 1 | B | √ | √ | 27/11/2025 | LRA | @
75 | 2800 | OFO-P2800-SK-T-075 | DAVIT LIFTING STROPS & AIR BAGS SPACING DETAILS FOR 6 INCHES GL-1 AT ZWSC-GIP | 1 | B | √ | √ | 27/11/2025 | LRA | @
76 | 2800 | OFO-P2800-SK-T-076 | DAVIT LIFTING STROPS & AIR BAGS SPACING DETAILS FOR 6 INCHES GL-2 AT ZK-50 | 1 | B | √ | √ | 17/10/2025 | SKS | @
77 | 2800 | OFO-P2800-SK-T-077 | DAVIT LIFTING STROPS & AIR BAGS SPACING DETAILS FOR 6 INCHES GL-2 AT ZK-43A | 2 | E | √ | √ | 02/01/2026 | LRA | @
78 | 2800 | OFO-P2800-SK-T-078 | DAVIT LIFTING STROPS & AIR BAGS SPACING DETAILS FOR 6 INCHES GL-3 AT ZK-43A | 1 | B | √ | √ | 25/09/2025 | SKT | @
79 | 2800 | OFO-P2800-SK-T-079 | DAVIT LIFTING STROPS & AIR BAGS SPACING DETAILS FOR 6 INCHES GL-3 AT ZK-45 | 2 | E | √ | √ | 20/05/2026 | SKS | @
80 | 2800 | OFO-P2800-SK-T-080 | DAVIT LIFTING STROPS & AIR BAGS SPACING DETAILS FOR 6 INCHES GL-4 AT ZK-45 | 1 | C | √ | √ | 29/07/2026 | LEO | @
81 | 2800 | OFO-P2800-SK-T-081 | DAVIT LIFTING STROPS & AIR BAGS SPACING DETAILS FOR 6 INCHES GL-4 AT ZK-56 | 1 | D | √ | √ | 21/08/2026 | MF | @
82 | 2800 | OFO-P2800-SK-T-082 | HEA TITIAN LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT ( ZK 280) PLATFORM | 2 | B | √ | √ | 03/09/2025 | HZD | @
83 | 2800 | OFO-P2800-SK-T-083 | HEA TITIAN LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH AT ( ZK 280) PLATFORM | 2 | A | √ | √ | 22/08/2025 | MF | @
84 | 2800 | OFO-P2800-SK-T-084 | HEA TITIAN LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT ZK-280 PLATFORM | 2 | B | √ | √ | 29/08/2025 | MF | @
85 | 2800 | OFO-P2800-SK-T-085 | 10" GAUGE PLATE DETAIL |  |  |  |  | 18/08/2025 | SM
86 | 2800 | OFO-P2800-SK-T-086 | HEA TITIAN LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT (ZK-280) PLATFORM | 2 | A | √ | √ | 22/08/2025 | MF | @
87 | 2800 | OFO-P2800-SK-T-087 | HEA TITIAN LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT ZK-280 PLATFORM | 2 | B | √ | √ | 29/08/2025 | MF | @
88 | 2800 | OFO-P2800-SK-T-088 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT ( ZK 277 ) PLATFORM | 2 | A | √ | √ | 29/08/2025 | MF | @
89 | 2800 | OFO-P2800-SK-T-089 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT ( ZK 277 ) PLATFORM | 3 + 22 | A, 0 | √ | √ | 02/09/2025 | SKS | @ | SENT TO FAB. SM ON 03/09
90 | 2800 | OFO-P2800-SK-T-090 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT ( ZK 277 ) PLATFORM | 2 | A | √ | √ | 29/08/2025 | MF | @
91 | 2800 | OFO-P2800-SK-T-091 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT ( ZK 277 ) PLATFORM | 2 | A | √ | √ | 29/08/2025 | MF | @
92 | 2800 | OFO-P2800-SK-T-092 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT ( ZK 277 ) PLATFORM | 2 | A | √ | √ | 29/08/2025 | MF | @
93 | 2800 | OFO-P2800-SK-T-093 | ROV LARS LIFTING ARRANGEMENT BY PLB-648 | 1 | A | √ | √ | 29/08/2025 | SHM | @
94 | 2800 | OFO-P2800-SK-T-094 | 20FT CONTAINER LIFTING ARRANGEMENT BY PLB-648 | 1 | A | √ | √ | 29/08/2025 | SHM | @
95 | 2800 | OFO-P2800-SK-T-095 | HEA TITIAN LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT ( ZK 43A) PLATFORM | 2 | C | √ | √ | 20/01/2026 | NAR | @
96 | 2800 | OFO-P2800-SK-T-096 | HEA TITIAN LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT ( ZK 43A) PLATFORM | 2 | D | √ | √ | 22/01/2026 | NAR | @
97 | 2800 | OFO-P2800-SK-T-097 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-43A) | 2 | B | √ | √ | 05/11/2025 | NAR | @
98 | 2800 | OFO-P2800-SK-T-098 | HEA TITIAN LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT ( ZK 43A) PLATFORM | 2 | D | √ | √ | 21/01/2026 | NAR | @
99 | 2800 | OFO-P2800-SK-T-099 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-43A) | 2 | D | √ | √ | 21/01/2026 | NAR | @
100 | 2800 | OFO-P2800-SK-T-100 | DMA START-UP ARRANGEMENT FOR 6" PIPELINE (GL-2) AT ZK-50 | 1 | A | √ | √ | 27/08/2025 | NHE | @
101 | 2800 | OFO-P2800-SK-T-101 | DETAILS OF CABLE TOWER |  |  |  |  | 29/08/2025 | AMK
102 | 2800 | OFO-P2800-SK-T-102 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR PIPELINE PROTECTOR USING PLB-648 | 2 | A | √ | √ | 30/08/2025 | HZD | @
103 | 2800 | OFO-P2800-SK-T-103 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 900MM) | 1 + 5 | A, 0 | √ | √ | 02/09/2025 | VDA | @
104 | 2800 | OFO-P2800-SK-T-104 | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 600MM) | 1 + 5 | A, 0 | √ | √ | 02/09/2025 | VDA | @
105 | 2800 | OFO-P2800-SK-T-105 | DMA START-UP ARRANGEMENT FOR PROPOSED 6" PIPELINE (GL-3) FROM ZK-43A TO ZK-45 | 2 | A | √ | √ | 04/09/2025 | NHE | @
106 | 2800 | OFO-P2800-SK-T-106 | TYPICAL CABLE PULLING ARRANGEMENT WITH TUGGER ON PALTFORM (WITHOUT TOPSIDE) | 2 | B | √ | √ | 10/02/2026 | BAJ | @
107 | 2800 | OFO-P2800-SK-T-107 | TYPICAL CABLE PULLING ARRANGEMENT WITH TUGGER ON PALTFORM (WITH TOPSIDE) | 2 | B | √ | √ | 23/09/2025 | SKT | @
108 | 2800 | OFO-P2800-SK-T-108 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR TEMPORARY SUPPORT USING PLB-648 CRAWLER CRANE | 1 | C | √ | √ | 18/09/2025 | NAR | @
109 | 2800 | OFO-P2800-SK-T-109 | TYPICAL CABLE LAYOUT ARRANGEMENT ON JACKET WALKWAY | 1 | B | √ | √ | 10/12/2025 | LEO | @
110 | 2800 | OFO-P2800-SK-T-110 | INSTALLATION RIGGING FOR SAND/CEMENT BAG | 1 | A | √ | √ | 2025-09-13 | AK | @
111 | 2800 | OFO-P2800-SK-T-111 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-280) | 2 | A | √ | √ | 2025-09-16 | NAR | @
112 | 2800 | OFO-P2800-SK-T-112 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-280 PLATFORM | 2 | B | √ | √ | 2025-09-22 | NAR | @
113 | 2800 | OFO-P2800-SK-T-113 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-280) | 2 | A | √ | √ | 2025-09-16 | NAR | @
114 | 2800 | OFO-P2800-SK-T-114 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-280 PLATFORM | 2 | A | √ | √ | 2025-09-17 | NAR | @
115 | 2800 | OFO-P2800-SK-T-115 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 19.2M GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-280) | 2 | B | √ | √ | 2025-09-23 | NAR | @
116 | 2800 | OFO-P2800-SK-T-116 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 19.2M GANGWAY AT BARGE DECK & ZK-280 PLATFORM | 2 | A | √ | √ | 2025-09-17 | NAR | @
117 | 2800 | OFO-P2800-SK-T-117 | INSTALLATION RIGGING FOR SAND/CEMENT BAG BY USING MP-02 | 1 | C | √ | √ | 2026-01-23 | NAR | @
118 | 2800 | OFO-P2800-SK-T-118 | HURLK: Temporary Support Arrangement for GL-3 at Laydown Location | 1 | A | √ | √ | 2025-09-29 | LEO | @
119 | 2800 | OFO-P2800-SK-T-119 | HURLK: Davit Location for PLB-648 (GA) | C | A | √ | √ | 2025-09-25 | LEO | @
120 | 2800 | OFO-P2800-SK-T-120 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-280) | 2 | A | √ | √ | 2025-09-24 | NAR | @
121 | 2800 | OFO-P2800-SK-T-121 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-280 PLATFORM | 2 | A | √ | √ | 2025-09-24 | NAR | @
122 | 2800 | OFO-P2800-SK-T-122 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-280) | 2 | A | √ | √ | 2025-09-29 | NAR | @
123 | 2800 | OFO-P2800-SK-T-123 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-280 PLATFORM | 2 | A | √ | √ | 2025-09-29 | NAR | @
124 | 2800 | OFO-P2800-SK-T-124 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-280) | 2 | A | √ | √ | 2025-10-01 | NAR | @
125 | 2800 | OFO-P2800-SK-T-125 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-280 PLATFORM | 1 | A | √ | √ | 2025-10-02 | NAR | @
126 | 2800 | OFO-P2800-SK-T-126 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-280) | 2 | A | √ | √ | 2025-10-02 | NAR | @
127 | 2800 | OFO-P2800-SK-T-127 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-280 PLATFORM | 2 | A | √ | √ | 2025-10-03 | NAR | @
128 | 2800 | OFO-P2800-SK-T-128 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-280) | 2 | A | √ | √ | 2025-10-03 | NAR | @
129 | 2800 | OFO-P2800-SK-T-129 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-280 PLATFORM | 2 | A | √ | √ | 2025-10-07 | NAR | @
130 | 2800 | OFO-P2800-SK-T-130 | INSTALLATION OF DIVING BASKET WITH MP02 | 1 | B | √ | √ | 2026-01-20 | NAR | @
131 | 2800 | OFO-P2800-SK-T-131 | TYPICAL LIFTING ARRANGEMENT OF A-FRAME BY MP-02 | 1 | A | √ | √ | 2025-10-01 | CDG | @
132 | 2800 | OFO-P2800-SK-T-132 | DETAILS OF TEMPORARY SUPPORT FOR GL-2 SPOOLS AT ZK-43A (HEIGHT-1250MM) | 1 | B | √ | √ | 2025-10-17 | SKT | @
133 | 2800 | OFO-P2800-SK-T-133 | SPOOL FLANGE END PLATES ARRANGEMENT FOR 10" #1500 FLANGE | 1 | A | √ | √ | 2025-10-03 | HZD | @
134 | 2800 | OFO-P2800-SK-T-134 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT | 1 | A | √ | √ | 2025-10-03 | HZD | @
135 | 2800 | OFO-P2800-SK-T-135 | DRIFT PIN FOR 10” #1500 FLANGE | 1 | A | √ | √ | 2025-10-03 | HZD | @
136 | 2800 | OFO-P2800-SK-T-136 | FLANGE ACTCHERS FOR 10”#1500 | 1 | A | √ | √ | 2025-10-03 | HZD | @
137 | 2800 | OFO-P2800-SK-T-137 | TYPICAL LIFTING ARRANGEMENT OF 1.5M RADIUS QUADRANT | 1 | A | √ | √ | 2025-10-10 | SKT | @
138 | 2800 | OFO-P2800-SK-T-138 | TYPICAL LIFTING ARRANGEMENT OF A-FRAME | 1 | A | √ | √ | 2025-10-10 | SKT | @
139 | 2800 | OFO-P2800-SK-T-139 | RISER TOP PLATE & PADEYE DETAILS FOR 6"RISER AT ZK-43A - CUTLIST | 5 | 0 | √ | √ | 2025-10-03 | CDG | @
140 | 2800 | OFO-P2800-SK-T-140 | SEAFASTENING OF ZK-280 DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA 402 - CUTLSIT | 3 + 55 | 0 | √ | √ | 2025-10-08 | LEO | @ | KARTHICK
141 | 2800 | OFO-P2800-SK-T-141 | TYPICAL LIFTING ARRANGEMENT OF 2.5M RADIUS HALF MOON BEND RESTRICTOR | 1 | A | √ | √ | 2025-10-10 | SKT | @
142 | 2800 | OFO-P2800-SK-T-142 | TYPICAL PERSONNEL BASKET LIFITNG ARRANGEMENT BY MP-02 | 1 | A | √ | √ | 2025-10-06 | NAR | @
143 | 2800 | OFO-P2800-SK-T-143 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-277) | 2 | A | √ | √ | 2025-10-07 | NAR | @
144 | 2800 | OFO-P2800-SK-T-144 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-277 PLATFORM | 2 | A | √ | √ | 2025-10-08 | NAR | @
145 | 2800 | OFO-P2800-SK-T-145 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-277) | 2 | A | √ | √ | 2025-10-08 | NAR | @'
146 | 2800 | OFO-P2800-SK-T-146 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-277 PLATFORM | 2 | A | √ | √ | 2025-10-08 | NAR | @
147 | 2800 | OFO-P2800-SK-T-147 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-277) | 2 | A | √ | √ | 2025-10-09 | NAR | @
148 | 2800 | OFO-P2800-SK-T-148 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-277 PLATFORM | 2 | A | √ | √ | 2025-10-09 | NAR | @
149 | 2800 | OFO-P2800-SK-T-149 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-277) | 2 | A | √ | √ | 2025-10-09 | NAR | @
150 | 2800 | OFO-P2800-SK-T-150 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-277 PLATFORM | 2 | A | √ | √ | 2025-10-14 | NAR | @
151 | 2800 | OFO-P2800-SK-T-151 | SEA FASTENING OF ZK-280 DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA 402 - CUTLIST -TRIP-2 |  |  |  |  | 2025-10-08 | LEO
152 | 2800 | OFO-P2800-SK-T-152 | STALK ON OF PIPE JOINTS FOR 10" WI-4 PIPELINE FROM ZK-372 TO ZK-126.5/65 | 4 | A | √ | √ | 2025-10-23 | CDG | @
153 | 2800 | OFO-P2800-SK-T-153 | DISPOSITION FOR TEMPORARY SUPPORTS BELOW SPOOLS AT VARIOUS PLATFORMS | 2 | A | √ | √ | 2025-10-15 | SKT | @'
154 | 2800 | OFO-P2800-SK-T-154 | DETAILS OF TEMPORARY SUPPORT FOR GL-2 SPOOLS AT ZK-50 (HEIGHT - 1000MM) | 1 | B | √ | √ | 2025-10-17 | SKT | @'
155 | 2800 | OFO-P2800-SK-T-155 | DETAILS OF TEMPORARY SUPPORT WITH HEIGHT 1250MM (10" PIPE) | 2 | A | √ | √ | 2025-10-17 | SKT | @
156 | 2800 | OFO-P2800-SK-T-156 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-43A) | 2 | C | √ | √ | 2026-01-20 | NAR | @
157 | 2800 | OFO-P2800-SK-T-157 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-43A) | 2 | D | √ | √ | 2026-01-22 | NAR | @
158 | 2800 | OFO-P2800-SK-T-158 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-43A PLATFORM | 2 | D | √ | √ | 2026-01-22 | NAR | @
159 | 2800 | OFO-P2800-SK-T-159 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-88) | 2 | A | √ | √ | 2025-10-23 | NAR | @
160 | 2800 | OFO-P2800-SK-T-160 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-88 PLATFORM | 2 | A | √ | √ | 2025-10-24 | NAR | @
161 | 2800 | OFO-P2800-SK-T-161 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-88) | 2 | A | √ | √ | 2025-10-25 | NAR | @
162 | 2800 | OFO-P2800-SK-T-162 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-88 PLATFORM | 2 | A | √ | √ | 2025-10-27 | NAR | @
163 | 2800 | OFO-P2800-SK-T-163 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-88) | 2 | A | √ | √ | 2025-10-27 | NAR | @
164 | 2800 | OFO-P2800-SK-T-164 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-88 PLATFORM | 2 | A | √ | √ | 2025-10-27 | NAR | @
165 | 2800 | OFO-P2800-SK-T-165 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-88) | 2 | A | √ | √ | 2025-10-27 | NAR | @
166 | 2800 | OFO-P2800-SK-T-166 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-88 PLATFORM | 2 | A | √ | √ | 2025-10-28 | NAR | @
167 | 2800 | OFO-P2800-SK-T-167 | ZK-280 MODULES SEA FASTENING ON HEA KRAKEN - CUTLIST | 2 + 27 | 0 | √ | √ | 2025-10-30 | REY | @
168 | 2800 | OFO-P2800-SK-T-168 | GROUTING EQUIPMENT SET UP LAYOUT ON MP-02 | 2 | A | √ | √ | 2025-11-03 | MF | @
169 | 2800 | OFO-P2800-SK-T-169 | ZK-43A GL-3 SMALL LADDER LIFTING ARRANGEMENT | 1 | A | √ | √ | 2025-11-10 | HZD | @
170 | 2800 | OFO-P2800-SK-T-170 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-293) | 2 | A | √ | √ | 2025-11-07 | NAR | @
171 | 2800 | OFO-P2800-SK-T-171 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-293 PLATFORM | 2 | A | √ | √ | 2025-11-07 | NAR | @
172 | 2800 | OFO-P2800-SK-T-172 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-293) | 2 | A | √ | √ | 2025-11-07 | NAR | @
173 | 2800 | OFO-P2800-SK-T-173 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-293 PLATFORM |  |  |  |  | 2025-11-06 | NAR
174 | 2800 | OFO-P2800-SK-T-174 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-293) | 2 | A | √ | √ | 2025-11-08 | NAR | @
175 | 2800 | OFO-P2800-SK-T-175 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-293 PLATFORM | 2 | A | √ | √ | 2025-11-08 | NAR | @
176 | 2800 | OFO-P2800-SK-T-176 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-293) | 2 | A | √ | √ | 2025-11-10 | NAR | @
177 | 2800 | OFO-P2800-SK-T-177 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-293 PLATFORM | 2 | A | √ | √ | 2025-11-10 | NAR | @
178 | 2800 | OFO-P2800-SK-T-178 | 6" GUAGE PLATE DETAILS | 1 | A | √ | √ | 2025-11-12 | SM | @
179 | 2800 | OFO-P2800-SK-T-179 | 10" GUAGE PLATE DETAILS | 1 | A | √ | √ | 2025-11-12 | SM | @
180 | 2800 | OFO-P2800-SK-T-180 | MANUAL MONORAIL TO DEPLOY TIGER ROV (150 kg) |  |  |  |  | 2025-11-11 | LEO
181 | 2800 | OFO-P2800-SK-T-181 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | A | √ | √ | 2025-11-13 | NAR | @
182 | 2800 | OFO-P2800-SK-T-182 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-47 PLATFORM | 2 | A | √ | √ | 2025-11-13 | NAR | @
183 | 2800 | OFO-P2800-SK-T-183 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | A | √ | √ | 2025-11-13 | NAR | @
184 | 2800 | OFO-P2800-SK-T-184 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-47 PLATFORM | 2 | A | √ | √ | 2025-11-14 | NAR | @
185 | 2800 | OFO-P2800-SK-T-185 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | A | √ | √ | 2025-11-14 | NAR | @
186 | 2800 | OFO-P2800-SK-T-186 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-47 PLATFORM | 2 | A | √ | √ | 2025-11-16 | NAR | @
187 | 2800 | OFO-P2800-SK-T-187 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | A | √ | √ | 2025-11-16 | NAR | @
188 | 2800 | OFO-P2800-SK-T-188 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-47 PLATFORM | 2 | A | √ | √ | 2025-11-17 | NAR | @
189 | 2800 | OFO-P2800-SK-T-189 | TYPICAL LIFTING ARRANGEMENT OF HALF MOON | 1 | A | √ | √ | 2025-11-13 | CDG | @
190 | 2800 | OFO-P2800-SK-T-190 | LOADING ARRANGEMENT & SEAFASTENING OF SILO & MISC EQUIPMENTS @ MARCAP SIBA | 1 | A | √ | √ | 2025-11-18 | AMK | @
191 | 2800 | OFO-P2800-SK-T-191 | AIR BAG ARRANGEMENT FOR LIFTING OF 6IN GL-2 AT KP 1.044 | 1 | A | √ | √ | 2025-11-18 | Amith | @
192 | 2800 | OFO-P2800-SK-T-192 | GUAGE PLATE DETAIL FOR 6" AND 10" PIPE LINES | 1 | A | √ | √ | 2025-12-05 | LEO | @
193 | 2800 | OFO-P2800-SK-T-193 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | B | √ | √ | 2026-01-14 | NAR | @
194 | 2800 | OFO-P2800-SK-T-194 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-47 PLATFORM | 2 | A | √ | √ | 2026-01-14 | NAR | @
195 | 2800 | OFO-P2800-SK-T-195 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | B | √ | √ | 2026-01-15 | NAR | @
196 | 2800 | OFO-P2800-SK-T-196 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-47 PLATFORM | 2 | B | √ | √ | 2026-01-15 | NAR | @
197 | 2800 | OFO-P2800-SK-T-197 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | B | √ | √ | 2026-01-15 | NAR | @
198 | 2800 | OFO-P2800-SK-T-198 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-47 PLATFORM | 2 | A | √ | √ | 2025-12-10 | NAR | @
199 | 2800 | OFO-P2800-SK-T-199 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | B | √ | √ | 2026-01-16 | NAR | @
200 | 2800 | OFO-P2800-SK-T-200 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-47 PLATFORM | 2 | B | √ | √ | 2026-01-16 | NAR | @
201 | 2800 | OFO-P2800-SK-T-201 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR TEMPORARY SUPPORT | 1 | A | √ | √ | 2025-12-24 | SRV | @
202 | 2800 | OFO-P2800-SK-T-202 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-03) | 2 | A | √ | √ | 2025-12-27 | NAR | @
203 | 2800 | OFO-P2800-SK-T-203 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-03 PLATFORM | 2 | A | √ | √ | 2025-12-29 | NAR | @
204 | 2800 | OFO-P2800-SK-T-204 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-03) | 2 | A | √ | √ | 2025-12-29 | NAR | @
205 | 2800 | OFO-P2800-SK-T-205 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-03 PLATFORM | 2 | A | √ | √ | 2025-12-30 | NAR | @
206 | 2800 | OFO-P2800-SK-T-206 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-03) | 2 | A | √ | √ | 2025-12-31 | NAR | @
207 | 2800 | OFO-P2800-SK-T-207 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-03 PLATFORM | 2 | A | √ | √ | 2026-01-01 | NAR | @
208 | 2800 | OFO-P2800-SK-T-208 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-03) | 2 | A | √ | √ | 2026-01-05 | NAR | @
209 | 2800 | OFO-P2800-SK-T-209 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-03 PLATFORM | 2 | A | √ | √ | 2026-01-05 | NAR | @
210 | 2800 | OFO-P2800-SK-T-210 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2025-12-25 | SRV | @
211 | 2800 | OFO-P2800-SK-T-211 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2025-12-25 | SRV | @
212 | 2800 | OFO-P2800-SK-T-212 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2025-12-26 | SRV | @
213 | 2800 | OFO-P2800-SK-T-213 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2025-12-26 | SRV | @
214 | 2800 | OFO-P2800-SK-T-214 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2025-12-26 | SRV | @
215 | 2800 | OFO-P2800-SK-T-215 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2025-12-26 | SRV | @
216 | 2800 | OFO-P2800-SK-T-216 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2025-12-26 | SRV | @
217 | 2800 | OFO-P2800-SK-T-217 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF CONTAINER AT BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2025-12-26 | SRV | @
218 | 2800 | OFO-P2800-SK-T-218 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2025-12-29 | SRV | @
219 | 2800 | OFO-P2800-SK-T-219 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2025-12-29 | SRV | @
220 | 2800 | OFO-P2800-SK-T-220 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2025-12-30 | SRV | @
221 | 2800 | OFO-P2800-SK-T-221 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2025-12-30 | SRV | @
222 | 2800 | OFO-P2800-SK-T-222 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2025-12-30 | SRV | @
223 | 2800 | OFO-P2800-SK-T-223 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2025-12-30 | SRV | @
224 | 2800 | OFO-P2800-SK-T-224 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2025-12-30 | SRV | @
225 | 2800 | OFO-P2800-SK-T-225 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF CONTAINER AT BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2025-12-30 | SRV | @
226 | 2800 | OFO-P2800-SK-T-226 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT USING PLB-648 | 1 | A | √ | √ | 2026-02-02 | LEO | @
227 | 2800 | OFO-P2800-SK-T-227 | DMA START-UP ARRANGEMENT FOR PROPOSED 6" PIPELINE (GL-4) FROM ZK-45 TO ZK-56 | 2 | C | √ | √ | 2026-02-13 | LEO | @
228 | 2800 | OFO-P2800-SK-T-228 | TYPICAL ABANDONMENT & RECOVERY ARRANGEMENT WITHOUT STINGER | 3 | A | √ | √ | 2026-02-03 | LEO | @
229 | 2800 | OFO-P2800-SK-T-229 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | A | √ | √ | 2026-01-31 | NAR | @
230 | 2800 | OFO-P2800-SK-T-230 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-47 PLATFORM | 2 | A | √ | √ | 2026-01-31 | NAR | @
231 | 2800 | OFO-P2800-SK-T-231 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | A | √ | √ | 2026-01-31 | NAR | @
232 | 2800 | OFO-P2800-SK-T-232 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-47 PLATFORM | 2 | A | √ | √ | 2026-01-31 | NAR | @
233 | 2800 | OFO-P2800-SK-T-233 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | A | √ | √ | 2026-01-31 | NAR | @
234 | 2800 | OFO-P2800-SK-T-234 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-47 PLATFORM | 2 | A | √ | √ | 2026-01-31 | NAR | @
235 | 2800 | OFO-P2800-SK-T-235 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-47) | 2 | A | √ | √ | 2026-02-02 | NAR | @
236 | 2800 | OFO-P2800-SK-T-236 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-47 PLATFORM | 2 | A | √ | √ | 2026-02-02 | NAR | @
237 | 2800 | OFO-P2800-SK-T-237 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-44) | 2 | A | √ | √ | 2026-02-04 | NAR | @
238 | 2800 | OFO-P2800-SK-T-238 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-44 PLATFORM | 2 | B | √ | √ | 2026-02-07 | NAR | @
239 | 2800 | OFO-P2800-SK-T-239 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-44) | 2 | A | √ | √ | 2026-02-04 | NAR | @
240 | 2800 | OFO-P2800-SK-T-240 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-44 PLATFORM | 2 | A | √ | √ | 2026-02-05 | NAR | @
241 | 2800 | OFO-P2800-SK-T-241 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-44) | 2 | A | √ | √ | 2026-02-05 | NAR | @
242 | 2800 | OFO-P2800-SK-T-242 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-44 PLATFORM | 2 | A | √ | √ | 2026-02-05 | NAR | @
243 | 2800 | OFO-P2800-SK-T-243 | EXTRA KNEE BRACES FOR GL1 AT GIP | 1 | A | √ | √ | 2026-02-04 | CDG | @
244 | 2800 | OFO-P2800-SK-T-244 | MISC. ITEM LIFTING AT GIP WITH MP-02 | 3 | B | √ | √ | 2026-02-23 | CDG | @ | changed to drg.
245 | 2800 | OFO-P2800-SK-T-245 | MISC. ITEM LIFTING AT GIP WITH PLB-648 | 3 | B | √ | √ | 2026-02-23 | CDG | @
246 | 2800 | OFO-P2800-SK-T-246 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER FROM / TO DP VESSEL & BARGE DECK USING MAIN CRANE AT ZK-44 PLATFORM | 2 | A | √ | √ | 2026-02-20 | NAR | @
247 | 2800 | OFO-P2800-SK-T-247 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL FROM / TO DP VESSEL & BARGE DECK USING MAIN CRANE AT ZK-44 PLATFORM | 2 | A | √ | √ | 2026-02-20 | NAR | @
248 | 2800 | OFO-P2800-SK-T-248 | Typical Installation & Removal for Subsea Temporary Support & Knee Brace by PLB-648 Main Crane | 2 | A | √ | √ | 2026-03-03 | MF | @
249 | 2800 | OFO-P2800-SK-T-249 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-88) | 2 | A | √ | √ | 2026-03-02 | NAR | @
250 | 2800 | OFO-P2800-SK-T-250 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-88 PLATFORM | 2 | A | √ | √ | 2026-03-04 | NAR | @
251 | 2800 | OFO-P2800-SK-T-251 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-88) | 2 | A | √ | √ | 2026-03-03 | NAR | @
252 | 2800 | OFO-P2800-SK-T-252 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-88 PLATFORM | 2 | A | √ | √ | 2026-03-04 | NAR | @
253 | 2800 | OFO-P2800-SK-T-253 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-88) | 2 | A | √ | √ | 2026-03-04 | NAR | @
254 | 2800 | OFO-P2800-SK-T-254 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-88 PLATFORM | 2 | A | √ | √ | 2026-03-04 | NAR | @
255 | 2800 | OFO-P2800-SK-T-255 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-88) | 2 | A | √ | √ | 2026-03-04 | NAR | @
256 | 2800 | OFO-P2800-SK-T-256 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-88 PLATFORM | 2 | A | √ | √ | 2026-03-05 | NAR | @
257 | 2800 | OFO-P2800-SK-T-257 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-126.5/65) | 2 | A | √ | √ | 2026-03-04 | NAR | @
258 | 2800 | OFO-P2800-SK-T-258 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-126.5/65 PLATFORM | 2 | A | √ | √ | 2026-03-04 | NAR | @
259 | 2800 | OFO-P2800-SK-T-259 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-126.5/65) | 2 | A | √ | √ | 2026-03-04 | NAR | @
260 | 2800 | OFO-P2800-SK-T-260 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-126.5/65 PLATFORM | 2 | A | √ | √ | 2026-03-04 | NAR | @
261 | 2800 | OFO-P2800-SK-T-261 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-126.5/65) | 2 | A | √ | √ | 2026-03-04 | NAR | @
262 | 2800 | OFO-P2800-SK-T-262 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-126.5/65 PLATFORM | 2 | A | √ | √ | 2026-03-04 | NAR | @
263 | 2800 | OFO-P2800-SK-T-263 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-126.5/65) | 2 | A | √ | √ | 2026-03-04 | NAR | @
264 | 2800 | OFO-P2800-SK-T-264 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-126.5/65 PLATFORM | 2 | A | √ | √ | 2026-03-04 | NAR | @
265 | 2800 | OFO-P2800-SK-T-265 | Removal & installation of Staircase at ZK-50 | 2 | A | √ | √ | 2026-03-05 | CDG | @
266 | 2800 | OFO-P2800-SK-T-266 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT ( ZK-329 ) PLATFORM | 2 | A | √ | √ | 2026-03-17 | MF | @
267 | 2800 | OFO-P2800-SK-T-267 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND VESSEL AT ( ZK 329) PLATFORM | 2 | A | √ | √ | 2026-03-17 | MF | @
268 | 2800 | OFO-P2800-SK-T-268 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT ( ZK 329) PLATFORM | 2 | A | √ | √ | 2026-03-17 | MF | @
269 | 2800 | OFO-P2800-SK-T-269 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT ( ZK 329) PLATFORM | 2 | A | √ | √ | 2026-03-17 | MF | @
270 | 2800 | OFO-P2800-SK-T-270 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT ( ZK 329) PLATFORM | 2 | A | √ | √ | 2026-03-17 | MF | @
271 | 2800 | OFO-P2800-SK-T-271 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT ( ZK 329) PLATFORM | 2 | A | √ | √ | 2026-03-17 | MF | @
272 | 2800 | OFO-P2800-SK-T-272 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND VESSEL AT ( ZK 329) PLATFORM | 2 | A | √ | √ | 2026-03-23 | MF | @
273 | 2800 | OFO-P2800-SK-T-273 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND PLATFORM AT ( ZK 329) PLATFORM | 2 | A | √ | √ | 2026-03-17 | MF | @
274 | 2800 | OFO-P2800-SK-T-274 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT ( ZK-3 ) PLATFORM | 2 | A | √ | √ | 2026-03-23 | MF | @
275 | 2800 | OFO-P2800-SK-T-275 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND VESSEL AT ( ZK 3) PLATFORM | 2 | A | √ | √ | 2026-03-23 | MF | @
276 | 2800 | OFO-P2800-SK-T-276 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT ( ZK 3) PLATFORM | 2 | A | √ | √ | 2026-03-23 | MF | @
277 | 2800 | OFO-P2800-SK-T-277 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT ( ZK 3) PLATFORM | 2 | A | √ | √ | 2026-03-23 | MF | @
278 | 2800 | OFO-P2800-SK-T-278 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT ( ZK 3) PLATFORM | 2 | A | √ | √ | 2026-03-23 | MF | @
279 | 2800 | OFO-P2800-SK-T-279 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT ( ZK 3) PLATFORM | 2 | A | √ | √ | 2026-03-23 | MF | @
280 | 2800 | OFO-P2800-SK-T-280 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND VESSEL AT ( ZK 3) PLATFORM | 2 | A | √ | √ | 2026-03-23 | MF | @
281 | 2800 | OFO-P2800-SK-T-281 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND PLATFORM AT ( ZK 3) PLATFORM | 2 | A | √ | √ | 2026-03-23 | MF | @
282 | 2800 | OFO-P2800-SK-T-282 | TYPICAL LIFTING AND INSTALLATION OF FLANGE SHROUD BY MP-02 | 1 | A | √ | √ | 2026-04-09 | CDG | @
283 | 2800 | OFO-P2800-SK-T-283 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND VESSEL AT (ZWSC – GIP) PLATFORM | 2 | B | √ | √ | 2026-06-17 | MF | @
284 | 2800 | OFO-P2800-SK-T-284 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT (ZWSC – GIP) PLATFORM | 2 | B | √ | √ | 2026-06-17 | MF | @
285 | 2800 | OFO-P2800-SK-T-285 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT (ZWSC – GIP) PLATFORM | 2 | B | √ | √ | 2026-06-17 | MF | @
286 | 2800 | OFO-P2800-SK-T-286 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT (ZWSC – GIP) PLATFORM | 2 | B | √ | √ | 2026-06-17 | MF | @
287 | 2800 | OFO-P2800-SK-T-287 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT(ZWSC – GIP) PLATFORM | 2 | B | √ | √ | 2026-06-17 | MF | @
288 | 2800 | OFO-P2800-SK-T-288 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT(ZWSC – GIP) PLATFORM | 2 | B | √ | √ | 2026-06-17 | MF | @
289 | 2800 | OFO-P2800-SK-T-289 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND VESSEL AT (ZWSC – GIP) PLATFORM | 2 | A | √ | √ | 2026-06-17 | MF | @
290 | 2800 | OFO-P2800-SK-T-290 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND PLATFORM AT (ZWSC – GIP) PLATFORM | 2 | B | √ | √ | 2026-06-17 | MF | @
291 | 2800 | OFO-P2800-SK-T-291 | TYPICAL LIFTING AND INSTALLATION OF CABLE PROTECTOR BY MP-02 | 1 | A | √ | √ | 2026-04-21 | AMK | @
292 | 2800 | OFO-P2800-SK-T-292 | LIFTING OF 6.6KV CABLES FOR RECTIFICATION WORK | 1 | B | √ | √ | 2026-04-30 | SIVA | @
293 | 2800 | OFO-P2800-SK-T-293 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2026-04-22 | NAR | @
294 | 2800 | OFO-P2800-SK-T-294 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2026-04-22 | NAR | @
295 | 2800 | OFO-P2800-SK-T-295 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2026-04-23 | NAR | @
296 | 2800 | OFO-P2800-SK-T-296 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2026-04-23 | NAR | @
297 | 2800 | OFO-P2800-SK-T-297 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2026-04-23 | NAR | @
298 | 2800 | OFO-P2800-SK-T-298 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2026-04-23 | NAR | @
299 | 2800 | OFO-P2800-SK-T-299 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-307) | 2 | A | √ | √ | 2026-04-24 | NAR | @
300 | 2800 | OFO-P2800-SK-T-300 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-307 PLATFORM | 2 | A | √ | √ | 2026-04-24 | NAR | @
301 | 2800 | OFO-P2800-SK-T-301 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND VESSEL AT ( ZK 372 ) PLATFORM |  |  |  |  | 2026-04-30 | MF
302 | 2800 | OFO-P2800-SK-T-302 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT ( ZK 372 ) PLATFORM |  |  |  |  | 2026-04-30 | MF
303 | 2800 | OFO-P2800-SK-T-303 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT ( ZK 372 ) PLATFORM |  |  |  |  | 2026-04-30 | MF
304 | 2800 | OFO-P2800-SK-T-304 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT ( ZK 372 ) PLATFORM |  |  |  |  | 2026-04-30 | MF
305 | 2800 | OFO-P2800-SK-T-305 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT ( ZK 372 ) PLATFORM |  |  |  |  | 2026-04-30 | MF
306 | 2800 | OFO-P2800-SK-T-306 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT ( ZK 372 ) PLATFORM |  |  |  |  | 2026-04-30 | MF
307 | 2800 | OFO-P2800-SK-T-307 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND VESSEL AT ( ZK 372 ) PLATFORM |  |  |  |  | 2026-04-30 | MF
308 | 2800 | OFO-P2800-SK-T-308 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND PLATFORM AT ( ZK 372 ) PLATFORM |  |  |  |  | 2026-04-30 | MF
309 | 2800 | OFO-P2800-SK-T-309 | AIR BAG ARRANGEMENT FOR LIFTING OF 10IN WI-4 AT KP 1.911 AND KP 1.969 | 1 | A | √ | √ | 2026-05-08 | SIVA | @
310 | 2800 | OFO-P2800-SK-T-310 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND VESSEL AT (ZCSC – NWIP) PLATFORM | 2 | A | √ | √ | 2026-05-13 | CDG | @ | SERVER ONLY
311 | 2800 | OFO-P2800-SK-T-311 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT (ZCSC – NWIP) PLATFORM | 2 | A | √ | √ | 2026-05-13 | CDG | @ | SERVER ONLY
312 | 2800 | OFO-P2800-SK-T-312 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT (ZCSC – NWIP) PLATFORM | 2 | A | √ | √ | 2026-05-13 | CDG | @ | SERVER ONLY
313 | 2800 | OFO-P2800-SK-T-313 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT AT (ZCSC – NWIP) PLATFORM | 2 | A | √ | √ | 2026-05-13 | CDG | @ | SERVER ONLY
314 | 2800 | OFO-P2800-SK-T-314 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT (ZCSC – NWIP) PLATFORM | 2 | A | √ | √ | 2026-05-13 | CDG | @ | SERVER ONLY
315 | 2800 | OFO-P2800-SK-T-315 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT (ZCSC – NWIP) PLATFORM | 2 | A | √ | √ | 2026-05-13 | CDG | @ | SERVER ONLY
316 | 2800 | OFO-P2800-SK-T-316 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND VESSEL AT (ZCSC – NWIP) PLATFORM | 2 | A | √ | √ | 2026-05-13 | CDG | @ | SERVER ONLY
317 | 2800 | OFO-P2800-SK-T-317 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND PLATFORM AT (ZCSC – NWIP) PLATFORM | 2 | A | √ | √ | 2026-05-13 | CDG | @ | SERVER ONLY
318 | 2800 | OFO-P2800-SK-T-318 | FCG AND HT EQUIPMENT LAYOUT ON QMS CONQUEST JUB | 1 | A | √ | √ | 2026-05-15 | JF | @
319 | 2800 | OFO-P2800-SK-T-319 | FOAM FLOAT ARRANGEMENT ON 6" GL4 PIPELINE | 1 | C | √ | √ | 2026-08-04 | LEO | @
320 | 2800 | OFO-P2800-SK-T-320 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-50) | 2 | A | √ | √ | 2026-06-12 | CDG | @
321 | 2800 | OFO-P2800-SK-T-321 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-50 PLATFORM | 2 | A | √ | √ | 2026-06-12 | CDG | @
322 | 2800 | OFO-P2800-SK-T-322 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-50) | 2 | A | √ | √ | 2026-05-25 | CDG | @
323 | 2800 | OFO-P2800-SK-T-323 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-50 PLATFORM | 2 | A | √ | √ | 2026-05-25 | CDG | @
324 | 2800 | OFO-P2800-SK-T-324 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-50) | 2 | A | √ | √ | 2026-05-25 | CDG | @
325 | 2800 | OFO-P2800-SK-T-325 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-50 PLATFORM | 2 | A | √ | √ | 2026-05-25 | CDG | @
326 | 2800 | OFO-P2800-SK-T-326 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-50) | 2 | A | √ | √ | 2026-05-25 | CDG | @
327 | 2800 | OFO-P2800-SK-T-327 | SEP-550 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-50 PLATFORM | 2 | A | √ | √ | 2026-05-25 | CDG | @
328 | 2800 | OFO-P2800-SK-T-328 | HORIZONTAL BOW STRING (HBS) START-UP ARRANGEMENT FOR GL-4 AT ZK-45 | 1 | A | √ | √ | 2026-06-19 | CDG | @
329 | 2800 | OFO-P2800-SK-T-329 | TYPICAL RISER / SPOOL LIFTING ARRANGEMENT BY MP-01 | 3 | A | √ | √ | 2026-06-19 | CDG | @
330 | 2800 | OFO-P2800-SK-T-330 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT BARGE PORT SIDE AT (ZWSC – GIP) PLATFORM | 2 | A | √ | √ | 2026-07-15 | HZD | @
331 | 2800 | OFO-P2800-SK-T-331 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT BARGE PORT SIDE AT (ZWSC – GIP) PLATFORM | 2 | A | √ | √ | 2026-07-15 | HZD | @
332 | 2800 | OFO-P2800-SK-T-332 | (HEA TITAN ) LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND VESSEL AT BARGE PORT SIDE AT (ZWSC – GIP) PLATFORM | 2 | A | √ | √ | 2026-07-15 | HZD | @
333 | 2800 | OFO-P2800-SK-T-333 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-126.5/65) | 2 | A | √ | √ | 2026-07-06 | AJILESH | @ | REV-B - SERVER ONLY
334 | 2800 | OFO-P2800-SK-T-334 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-126.5/65 PLATFORM | 2 | A | √ | √ | 2026-07-06 | AJILESH | @ | REV-B - SERVER ONLY
335 | 2800 | OFO-P2800-SK-T-335 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT (ZK-126.5) PLATFORM | 2 | A | √ | √ | 2026-07-08 | MF | @ | REV-A - SERVER ONLY
336 | 2800 | OFO-P2800-SK-T-336 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGNGE BETWEEN BARGE AND PLATFORM AT (ZK-126.5) PLATFORM | 2 | A | √ | √ | 2026-07-08 | MF | @ | REV-A - SERVER ONLY
337 | 2800 | OFO-P2800-SK-T-337 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT (ZK-126.5) PLATFORM | 2 | A | √ | √ | 2026-07-08 | MF | @ | REV-A - SERVER ONLY
338 | 2800 | OFO-P2800-SK-T-338 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT (ZK-126.5) PLATFORM | 2 | A | √ | √ | 2026-07-08 | MF | @ | REV-A - SERVER ONLY
339 | 2800 | OFO-P2800-SK-T-339 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND VESSEL AT (ZK-126.5) PLATFORM | 2 | A | √ | √ | 2026-07-08 | MF | @ | REV-A - SERVER ONLY
340 | 2800 | OFO-P2800-SK-T-340 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND PLATFORM AT (ZK-126.5) PLATFORM | 2 | A | √ | √ | 2026-07-08 | MF | @ | REV-A - SERVER ONLY
341 | 2800 | OFO-P2800-SK-T-341 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-44) | 2 | A | √ | √ | 2026-07-21 | CDG | @
342 | 2800 | OFO-P2800-SK-T-342 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-44 PLATFORM | 2 | A | √ | √ | 2026-07-21 | CDG | @
343 | 2800 | OFO-P2800-SK-T-343 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-44) | 2 | A | √ | √ | 2026-07-21 | CDG | @
344 | 2800 | OFO-P2800-SK-T-344 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-44 PLATFORM | 2 | A | √ | √ | 2026-07-21 | CDG | @
345 | 2800 | OFO-P2800-SK-T-345 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-44) | 2 | A | √ | √ | 2026-07-21 | CDG | @
346 | 2800 | OFO-P2800-SK-T-346 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-44 PLATFORM | 2 | A | √ | √ | 2026-07-21 | CDG | @
347 | 2800 | OFO-P2800-SK-T-347 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-44) | 2 | A | √ | √ | 2026-07-21 | CDG | @
348 | 2800 | OFO-P2800-SK-T-348 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-44 PLATFORM | 2 | A | √ | √ | 2026-07-21 | CDG | @
349 | 2800 | OFO-P2800-SK-T-349 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZK-43A) | 2 | A | √ | √ | 2026-07-27 | CDG | @
350 | 2800 | OFO-P2800-SK-T-350 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZK-43A PLATFORM | 2 | A | √ | √ | 2026-07-27 | CDG | @
351 | 2800 | OFO-P2800-SK-T-351 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZK-43A) | 2 | A | √ | √ | 2026-07-27 | CDG | @
352 | 2800 | OFO-P2800-SK-T-352 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZK-43A PLATFORM | 2 | A | √ | √ | 2026-07-27 | CDG | @
353 | 2800 | OFO-P2800-SK-T-353 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZK-43A) | 2 | A | √ | √ | 2026-07-27 | CDG | @
354 | 2800 | OFO-P2800-SK-T-354 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZK-43A PLATFORM | 2 | A | √ | √ | 2026-07-27 | CDG | @
355 | 2800 | OFO-P2800-SK-T-355 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZK-43A) | 2 | A | √ | √ | 2026-07-27 | CDG | @
356 | 2800 | OFO-P2800-SK-T-356 | QMS CONQUEST LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZK-43A PLATFORM | 2 | A | √ | √ | 2026-07-27 | CDG | @
357 | 2800 | OFO-P2800-SK-T-357 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (ZCSC NWIP) | 2 | A | √ | √ | 2026-08-14 | NAR | @
358 | 2800 | OFO-P2800-SK-T-358 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & ZCSC NWIP PLATFORM | 2 | A | √ | √ | 2026-08-14 | NAR | @
359 | 2800 | OFO-P2800-SK-T-359 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (ZCSC NWIP) | 2 | A | √ | √ | 2026-08-14 | NAR | @
360 | 2800 | OFO-P2800-SK-T-360 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & ZCSC NWIP PLATFORM | 2 | A | √ | √ | 2026-08-14 | NAR | @
361 | 2800 | OFO-P2800-SK-T-361 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (ZCSC NWIP) | 2 | A | √ | √ | 2026-08-14 | NAR | @
362 | 2800 | OFO-P2800-SK-T-362 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & ZCSC NWIP PLATFORM | 2 | A | √ | √ | 2026-08-14 | NAR | @
363 | 2800 | OFO-P2800-SK-T-363 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (ZCSC NWIP) | 2 | A | √ | √ | 2026-08-14 | NAR | @
364 | 2800 | OFO-P2800-SK-T-364 | JOPETWIL-215 LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & ZCSC NWIP PLATFORM | 2 | A | √ | √ | 2026-08-14 | NAR | @
365 | 2800 | OFO-P2800-SK-T-365 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND VESSEL AT (ZK-43A) PLATFORM |  |  |  |  | 2026-09-07 | MF
366 | 2800 | OFO-P2800-SK-T-366 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT (ZK-43A) PLATFORM |  |  |  |  | 2026-09-07 | MF
367 | 2800 | OFO-P2800-SK-T-367 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT (ZK-43A) PLATFORM |  |  |  |  | 2026-09-07 | MF
368 | 2800 | OFO-P2800-SK-T-368 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT (ZK-43A) PLATFORM |  |  |  |  | 2026-09-07 | MF
369 | 2800 | OFO-P2800-SK-T-369 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT (ZK-43A) PLATFORM |  |  |  |  | 2026-09-07 | MF
370 | 2800 | OFO-P2800-SK-T-370 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT (ZK-43A) PLATFORM |  |  |  |  | 2026-09-07 | MF
371 | 2800 | OFO-P2800-SK-T-371 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND VESSEL AT (ZK-43A) PLATFORM |  |  |  |  | 2026-09-07 | MF
372 | 2800 | OFO-P2800-SK-T-372 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND PLATFORM AT (ZK-43A) PLATFORM |  |  |  |  | 2026-09-07 | MF

## Cut-lists
Project 2800
CUT-LIST DRAWINGS
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2800 | 2800-NN-0001-CTL | START UP HEAD DETAILS FOR 10’’ WATER INJECTION PIPELINE | 1 + 18 | 0 | √ | √ | 04-06-2025 | CSE-OF-2800-T-001 | @
2 | 2800 | 2800-NN-0003-CTL | LAYDOWN HEAD DETAILS FOR 10'' WATER INJECTION PIPELINE | 1 + 18 | 0 | √ | √ | 04-06-2025 | CSE-OF-2800-T-001 | @
3 | 2800 | 2800-NN-0005-CTL | EMERGENCY LAYDOWN HEAD DETAILS FOR 10" WI PIPELINES | 1 + 16 | 0 | √ | √ | 04-06-2025 | CSE-OF-2800-T-001 | @
4 | 2800 | OFO-P2800-SK-T-017-CTL | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 800MM) | 1 + 5 | 0 | √ | √ | 18-06-2025 | CSE-OF-2800-T-002 | @
5 | 2800 | OFO-P2800-SK-T-018-CTL | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 1100MM) | 1 + 5 | 0 | √ | √ | 18-06-2025 | CSE-OF-2800-T-002 | @
6 | 2800 | OFO-P2800-SK-T-019-CTL | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 1300MM) | 1 + 5 | 0 | √ | √ | 18-06-2025 | CSE-OF-2800-T-002 | @
7 | 2800 | OFO-P2800-SK-T-024-CTL | TEMPORARY SUPPORT DETAILS FOR 4"/6" PIPELINE DURING LAYDOWN | 1 + 6 | 0 | √ | √ | 18-06-2025 | CSE-OF-2800-T-003 | @
8 | 2800 | 2800-NN-0002-CTL | START UP HEAD DETAILS FOR 6'' GL PIPELINES | 1 + 21 | 0 | √ | √ | 18-06-2025 | CSE-OF-2800-T-004 | @
9 | 2800 | 2800-NN-0004-CTL | LAYDOWN HEAD DETAILS FOR 6'' GL PIPELINES | 1 + 21 | 0 | √ | √ | 18-06-2025 | CSE-OF-2800-T-004 | @
10 | 2800 | 2800-NN-0006-CTL | EMERGENCY LAYDOWN HEAD DETAILS FOR 6'' GL PIPELINES | 1 + 21 | 0 | √ | √ | 18-06-2025 | CSE-OF-2800-T-004 | @
11 | 2800 | 2800-NN-0072-CTL | 10" FLANGE PROTECTOR FOR START-UP AND LAYDOWN HEAD – WI-3 | 1 + 8 | 0 | √ | √ | 18-06-2025 | CSE-OF-2800-T-005 | @
12 | 2800 | 2800-NN-0073-CTL | 10" FLANGE PROTECTOR FOR START-UP AND LAYDOWN HEAD – WI-4 | 2 + 12 | 0 | √ | √ | 18-06-2025 | CSE-OF-2800-T-005 | @
13 | 2800 | OFO-P2800-SK-T-048 | STORAGE QUADRANT 1.5M RADIUS FOR 12’’ J-TUBE | 1 + 9 | 0 | √ | √ | 2025-07-08 | CSE-OF-2800-T-006 | @
14 | 2800 | OFO-P2800-SK-T-049 | TYPICAL TUGGER SKID DETAILS FOR CABLE PULLING | 1 + 4 | 0 | √ | √ | 2025-07-08 | CSE-OF-2800-T-006 | @
15 | 2800 | OFO-P2800-SK-T-051 | A-FRAME ARRANGEMENT FOR CABLE PULLING | 1 + 8 | 0 | √ | √ | 2025-07-08 | CSE-OF-2800-T-006 | @
16 | GEN. | OFO-GEN-SK-T-221-CTL | 2.5M RADIUS HALF MOON BEND RESTRICTOR FOR CABLE LAYING (WITH CUTLIST 2 + 27 – REV-0) | 2 + 27 | 0 | √ | √ | 2025-07-08 | CSE-OF-2800-T-006 | @ | GENERAL SKETCH
17 | 2800 | OFO-P2800-SK-T-037-CTL | TYPICAL PIPELINE PROTECTOR / DOGHOUSE | 1 + 6 | 0 | √ | √ | 2025-07-09 | CSE-OF-2800-T-007 | @
18 | 2800 | OFO-P2800-SK-T-038-CTL | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 1250MM) | 1 + 5 | 0 | √ | √ | 2025-07-14 | CSE-OF-2800-T-008 | @
19 | 2800 | OFO-P2800-SK-T-039-CTL | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 1150MM) | 1 + 5 | 0 | √ | √ | 2025-07-14 | CSE-OF-2800-T-008 | @
20 | 2800 | OFO-P2800-SK-T-040-CTL | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 750MM) | 1+ 3 | 0 | √ | √ | 2025-07-14 | CSE-OF-2800-T-008 | @
21 | 2800 | OFO-P2800-SK-T-041-CTL | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 350MM) | 1+ 3 | 0 | √ | √ | 2025-07-14 | CSE-OF-2800-T-008 | @
22 | 2800 | OFO-P2800-SK-T-042-CTL | DETAILS OF TEMPORARY SUPPORT (H1250 mm X L8500 mm) | 1+ 5 | 0 | √ | √ | 2025-07-21 | CSE-OF-2800-T-012 | @
23 | 2800 | OFO-P2800-SK-T-045-CTL | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 900MM) | 1+ 5 | 0 | √ | √ | 2025-07-14 | CSE-OF-2800-T-008 | @
24 | 2800 | OFO-P2800-SK-T-046-CTL | DETAILS OF TEMPORARY SUPPORT (HEIGHT - 600MM) | 1+ 3 | 0 | √ | √ | 2025-07-14 | CSE-OF-2800-T-008 | @
25 | 2800 | OFO-P2800-SK-T-089 | JOPETWIL 215 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT ( ZK 277 ) PLATFORM | 3 + 22 | 0 | √ | √ | 02/09//2025 | SM - DIRECT | @
26 | 2800 | OFO-P2800-SK-T-140-CTL | SEAFASTENING OF ZK-280 DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA 402 - CUTLSIT | 3 + 55 | 0 | √ | √ | 2025-10-08 | CSE-OF-2800-T-015 | @
27 | 2800 | 2800-NN-0093-CTL | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZK-43A TO ZK-45 (GL-3) @ ZK-43A | 1 + 11 | 0 | √ | √ | 2025-10-13 | CSE-OF-2800-T-016 | @
28 | 2800 | 2800-NN-0095-CTL | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZK-50 TO ZK-43A (GL-2) @ ZK-43A | 1 + 11 | 0 | √ | √ | 2025-10-13 | CSE-OF-2800-T-016 | @
29 | 2800 | OFO-P2800-SK-T-151 | SEA FASTENING OF ZK-280 DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA 402 - CUTLIST -TRIP-2 | 3 + 62 | 0 | √ | √ | 2025-10-15 | KTR - DIREST ON 15/10/2025 | @
30 | 2800 | 2800-NN-0114-CTL | FABRICATION DRAWING FOR SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION MODULES ON MUTAWA 402 (WITH CUTLIST 2 + 17 – REV-1) | 2 + 15 | 0 | √ | √ | 2025-11-10 | CSE-OF-2800-T-017 | @'
|  |  |  | 2 + 17 | 1 | √ | √ | 2025-12-09 | CSE-OF-2800-T-021 | @'
31 | 2800 | 2800-NN-0115-CTL | FABRICATION DRAWING FOR SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION MODULES ON GMS ARTEMIS (WITH CUTLIST 2 + 17 – REV-0) | 2 + 16 | 0 | √ | √ | 2025-11-10 | CSE-OF-2800-T-017 | @
|  |  |  | 2 + 17 | 1 | √ | √ | 2025-12-10 | CSE-OF-2800-T-022 | @
32 | 2800 | 2800-NN-0116-CTL | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON MUTAWA 402 (TRIP-2) | 1 + 5 | 0 | √ | √ | 2025-11-13 | CSE-OF-2800-T-018 | @ | reissued on 18/11/2025
33 | 2800 | 2800-NN-0117-CTL | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON GMS ARTEMIS (TRIP-2) | 2 + 28 | 0 | √ | √ | 2025-11-13 | CSE-OF-2800-T-018 | @
34 | 2800 | 2800-NN-0118-CTL | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON MUTAWA 402 (TRIP-3) | 4 + 67 | 0 | √ | √ | 2025-11-27 | CSE-OF-2800-T-019 | @
35 | 2800 | 2800-NN-0119-CTL | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION ON GMS ARTEMIS (TRIP-3) | 4 + 60 | 0 | √ | √ | 2025-11-27 | CSE-OF-2800-T-019 | @
36 | 2800 | 2800-NN-0127-CTL | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-1) | 3 + 20 | 0 | √ | √ | 2025-12-08 | CSE-OF-2800-T-020 | @
37 | 2800 | 2800-NN-0129-CTL | FABRICATION DRAWING FOR SEAFASTENING DETAILS OF ZK-47 DECK EXTENSION MODULES ON MUTAWA-402 (WITH CUTLIST | 2 + 6 | 0 | √ | √ | 2025-12-11 | CSE-OF-2800-T-023 | @
38 | 2800 | 2800-NN-0130-CTL | LOWER ZAKUM – SEAFASTENING OF ZK-47 DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-2) | 2 + 6 | 0 | √ | √ | 2025-12-16 | CSE-OF-2800-T-024 | @
39 | 2800 | 2800-NN-0137-CTL | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZWSC-GIP TO ZK-50 @ ZWSC-GIP (GL-1) | 1 + 11 | 0 | √ | √ | 2025-12-19 | CSE-OF-2800-T-025 | @
40 | 2800 | 2800-NN-0138-CTL | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZK-43A TO ZK-45 @ ZK-45 (GL-3) | 1 + 12 | 0 | √ | √ | 2025-12-22 | CSE-OF-2800-T-026 | @
41 | 2800 | 2800-NN-0132-CTL | FABRICATION DRAWING FOR SEAFASTENING DETAILS OF ZK-47 DECK EXTENSION MODULES ON GMS ARTEMIS (TRIP-3) | 5 + 34 | 0 | √ | √ | 29-12-2025 02-01-2026 | CSE-OF-2800-T-027 | @ | re-issued on 02/01-2026
42 | 2800 | 2800-NN-0131-CTL | FABRICATION DRAWING FOR SEAFASTENING DETAILS OF ZK-47 DECK EXTENSION MODULES ON MUTAWA-402 (TRIP-3) | 5 + 44 | 0 | √ | √ | 02-01-2026 | CSE-OF-2800-T-028 | @
43 | 2800 | 2800-NN-0139-CTL | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZWSC-GIP TO ZK-50 @ ZK-50 (GL-1) | 1 + 12 | 0 | √ | √ | 15-01-2026 | sent through email - SM | @
|  |  |  | 1 + 13 | 1 | √ | √ | 2026-03-03 | sent through email - SM | @
44 | 2800 | 2800-NN-0016-CTL | TEMPORARY RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GAS LIFT PIPELINE FROM AREA 447 TO ZWSC-GIP (GL-1) AT ZWSC-GIP (GL-1) | 1 + 5 | 0 | √ | √ | 20-01-2026 | sent through email - SM | @
|  |  |  | 1 + 5 | 1 | √ | √ | 29-01-2026 | sent through email - SM | @
45 | 2800 | 2800-NN-0120-CTL | FABRICATION DRAWING FOR SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION MODULES ON MUTAWA 402 (TRIP-4) (WITH CUTLIST 3 + 16 – REV-0) | 3 + 16 | 0 | √ | √ | 2026-02-05 | CSE-OF-2800-T-029 | @
46 | 2800 | 2800-NN-0121-CTL | FABRICATION DRAWING FOR SEAFASTENING DETAILS OF ZK-43A DECK EXTENSION MODULES GMS ARTEMIS (TRIP-4) | 3 + 14 | 0 | √ | √ | 2026-02-05 | CSE-OF-2800-T-029 | @
47 | 2800 | 2800-NN-0140-CTL | TEMPORARY KNEE BRACE DETAILS FOR 6" GAS PIPELINE FROM ZK-50 TO ZK-43A @ ZK-50 (GL-2)-CUTLIST - 1 + 13 | 1 + 13 | 0 | √ | √ | 2026-02-10 | sent through email - SM | @
48 | 2800 | OFO-P2800-SK-T-243-CTL | EXTRA KNEE BRACES FOR GL1 AT GIP | 1 + 3 | 0 | √ | √ | 2026-02-13 | sent through email - SM | @
49 | 2800 | 2800-NN-0150-CTL | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-1) | 2 + 10 | 0 | √ | √ | 2026-03-30 | SERVER ONLY - SM | @
50 | 2800 | 2800-NN-0151-CTL | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON GMS ARTEMIS (TRIP-1) | 3 + 14 | 0 | √ | √ | 2026-03-30 | SERVER ONLY - SM | @
51 | 2800 | 2800-NN-0154-CTL | LOWER ZAKUM – SEAFASTENING OF ZWSC-GIP DECK EXTENSION MODULES & MISC. ITEMS ON MUTAWA 402 (TRIP-3) | 6 + 46 | 0 | √ | √ | 2026-05-05 | SERVER ONLY - SM
52 | 2800 | 2800-NN-0172-CTL | LOWER ZAKUM – SEAFASTENING OF ZK-50 DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA-402 - TRIP-2 | 1 + 17 | 0 | √ | √ | 2026-06-22 | SERVER ONLY - SM
53 | 2800 | 2800-NN-0173-CTL | LOWER ZAKUM – SEAFASTENING OF ZK-50 DECK EXTENSION MODULES AND MISC. ITEMS ON MUTAWA-402 - TRIP-3 | 3 + 38 | 0 | √ | √ | 2026-06-22 | SERVER ONLY - SM
54 | 2800 | 2800-NN-0174-CTL | LOWER ZAKUM – SEAFASTENING ARRANGEMENT OF ZK-50 IN GMS ARTEMIS (TRIP-2) | 2 + 19 | 0 | √ | √ | 2026-06-22 | SERVER ONLY - SM
55 | 2800 | 2800-NN-0175-CTL | LOWER ZAKUM – SEAFASTENING DETAILS OF ZK-50 DECK EXTENSION MODULES AND MISC. ITEMS ON ARTEMIS (TRIP-1) | 3 + 15 | 0 | √ | √ | 2026-06-22 | SERVER ONLY - SM
56 |  | 2800-NN-0178-CTL | TEMPORARY KNEE BRACE DETAILS FOR RISER / SPOOL LIFITNG OF 6'' GAS LIFT PIPELINE FOR GL-4 AT ZK-45 - CUTLIST | 1 + 15 | 0 | √ | √ | 2026-07-15 | SERVER ONLY - SM

## TN-PL
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
ADNOC EPC for LZ HABSHAN UPPER RECOVERY LEKHWAIR+20 MPB PROJECT
|  | NPCC PROJECT NO. 2800 | [11 empty] | REVISION : |  |  |  | 0
|  | Technical Notes | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | SENSITIVITY ANALYSIS FOR BUOYANCY LOSS FOR 10in WI-3 FROM ZK-47 TO ZK-372 | 2800-TN-PL-001
2 | PIPELAY ANALYSIS WITHOUT BARGE ROLLER 11 IN PLB 648 | 2800-TN-PL-002
3 | Sensitivity on 3MTBuoy Instead of 2.2MTBuoy | 2800-TN-PL-003 |  | 2 | 2 |  | 2025-07-30 | CSE-2800-PMT-T-075 | 2025-07-31 | 2800-NMDC-E-AO-PMT-T-01548
4