## Documents - Pipeline & Cable
|  | ADNOC OFFSHORE | [11 empty] | NMDC ENERGY DOC. No.:
ADNOC LZ LTDP-1 PROJECT
|  | NMDC ENERGY PROJECT NO. 2820 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2025-11-10
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | LOWER ZAKUM LTDP-1 PACKAGE 4 - DESIGN BASIS FOR INSTALLATION ENGINEERING ANALYSIS | 2820-NN-RP-001 | AD-27-Z-80546 | 1 | 2 |  | 2026-06-04 | CSE-2820-PMT-T-004 | 2026-06-05 | 2820-NMDC-E-AO-PMT-T-00782 | 2026-06-26 | LZ-LTDP-1-10222-PKG4-TN-05741 | 2 | 2026-06-05 | 2820-NMDC-E-PMT-MWS-T-00002 | 2026-06-10 | SAF234-MCE-NMDC-T-0001 | HOLD
|  |  |  | 2 | 2 |  | 2026-08-18 | CSE-2820-PMT-T-019 | 2026-08-19 | 2820-NMDC-E-AO-PMT-T-01002 | [5 empty] | 2026-08-18 | SAF234-MCE-NMDC-T-0034
2 | LOWER ZAKUM LTDP-1 PACKAGE 4 - PIPE STACKING ANALYSIS REPORT - CAMPAIGN-1 | 2820-NN-RP-002 | AD-27-Z-80547 | 1 | 2 |  | 2026-05-01 | CSE-2820-PMT-T-002 | 2026-05-04 | 2820-NMDC-E-AO-PMT-T-00701 | 2026-05-25 | LZ-LTDP-1-10222-PKG4-TN-05374 | 2 | 2026-06-16 | 2820-NMDC-E-PMT-MWS-T-00005 | 2026-06-22 | SAF234-MCE-NMDC-T-0002 | HOLD
|  |  |  | 2 | 2 |  | 2026-08-11 | CSE-2820-PMT-T-018 | 2026-08-12 | 2820-NMDC-E-AO-PMT-T-00983 |  |  |  | 2026-08-12 | 2820-NMDC-E-PMT-MWS-T-00032 | 2026-08-19 | SAF234-MCE-NMDC-T-0014 | APPROVED
3 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-301) FROM FROM WHT EA-1 to WHT EA-5 | 2820-NN-RP-003 | AD-817-Z-00002
4 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-302) FROM FROM WHT EA-5 to WHT EA-1 | 2820-NN-RP-004 | AD-821-Z-00002
5 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-303) FROM WHT EA-5 to WHT EA-1 | 2820-NN-RP-005 | AD-821-Z-00003
6 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-305) FROM WHT EA-5 to WHT EA-2B | 2820-NN-RP-006 | AD-821-Z-00004
7 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-306) FROM WHT EA-2B to WHT EA-5 | 2820-NN-RP-007 | AD-818-Z-00002
8 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-307) FROM WHT EA-2A to WHT EA-5 | 2820-NN-RP-008 | AD-818-Z-00003
9 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-309) FROM WHT EA-2A to ERP G-Island | 2820-NN-RP-009 | AD-818-Z-00004
10 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-310) FROM ERP G-Island to WHT EA-2A | 2820-NN-RP-010 | AD-3002-Z-00001
11 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-311) FROM ERP G-Island to WHT EA-2A | 2820-NN-RP-011 | AD-3002-Z-00002
12 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 22" WF P/L (PL-317) FROM WHT EA-6 to WHT EA-4 | 2820-NN-RP-012 | AD-822-Z-00002
13 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 18" WI P/L (PL-318) FROM WHT EA-4 to WHT EA-6 | 2820-NN-RP-013 | AD-820-Z-00002
14 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-319) FROM WHT EA-4 to WHT EA-6 | 2820-NN-RP-014 | AD-820-Z-00003
15 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-321) FROM WHT EA-4 to ERP G-Island | 2820-NN-RP-015 | AD-820-Z-00004 | 1 | 2 |  | 2026-07-27 | CSE-2820-PMT-T-012 | 2026-07-27 | 2820-NMDC-E-AO-PMT-T-00940 | 2026-08-13 | LZ-LTDP-1-10222-PKG4-TN-06315 | 2 | 2026-07-27 | 2820-NMDC-E-PMT-MWS-T-00025 | 2026-08-05 | SAF234-MCE-NMDC-T-0011 | APPROVED
16 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 18" WI P/L (PL-322) FROM ERP G-Island to WHT EA-4 | 2820-NN-RP-016 | AD-3002-Z-00003
17 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-323) FROM ERP G-Island to WHT EA-4 | 2820-NN-RP-017 | AD-3002-Z-00004
18 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 30" WG P/L (PL-325) FROM ERP G-Island to ZWSC-RP2 | 2820-NN-RP-018 | AD-3002-Z-00005
19 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 20" GE P/L (PL-326) FROM ERP G-Island to ZWSC-RP2 | 2820-NN-RP-019 | AD-3002-Z-00006
20 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 30" OE P/L (PL-329) FROM ERP G-Island to ZWSC-NRP | 2820-NN-RP-020 | AD-3002-Z-00007
21 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 18" WF P/L (PL-330) FROM WHT-1 AGI ARES TO ERP AO-ISLAND | 2820-NN-RP-021 | AD-811-Z-00002 | 1 | 2 |  | 2026-07-13 | CSE-2820-PMT-T-002 | 2026-07-14 | 2820-NMDC-E-AO-PMT-T-00899 | 2026-08-13 | LZ-LTDP-1-10222-PKG4-TN-06324 | 2 | 2026-07-14 | 2820-NMDC-E-PMT-MWS-T-00014 | 2026-07-15 | SAF234-MCE-NMDC-T-0006 | APPROVED | TITLE CHANGED ON 10.06 - 14" & ERP G-ISALAND
22 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-331) FROM ERP G-Island to WHT-1 AGI Area | 2820-NN-RP-022 | AD-3002-Z-00008
23 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-334) FROM WHT ZK-182 to ERP G-Island | 2820-NN-RP-023 | AD-324-Z-00002
24 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 38" WF P/L (PL-335) FROM ZCSC-CRP to ERP G-Island | 2820-NN-RP-024 | AD-496-Z-00010
25 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-337) FROM WHT in AGI Area to EPS-2 WHT-2 | 2820-NN-RP-025 | AD-848-Z-00058
26 | LOWER ZAKUM LTDP1 PACKAGE 4 - PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-338) FROM EPS-2 WHT-2 to EPS-2 WHT-3 | 2820-NN-RP-026 | AD-848-Z-00059
27 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 20" WF P/L (PL-301) WHT EA-1 to WHT EA-5 | 2820-NN-RP-027 | AD-817-Z-00003
28 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 16" WI P/L (PL-302) WHT EA-5 to WHT EA-1 | 2820-NN-RP-028 | AD-821-Z-00005
29 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-303) WHT EA-5 to WHT EA-1 | 2820-NN-RP-029 | AD-821-Z-00006
30 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 20" WF P/L (PL-305) WHT EA-5 to WHT EA-2B | 2820-NN-RP-030 | AD-821-Z-00007
31 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 16" WI P/L (PL-306) WHT EA-2B to WHT EA-5 | 2820-NN-RP-031 | AD-818-Z-00005
32 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-307) WHT EA-2A to WHT EA-5 | 2820-NN-RP-032 | AD-818-Z-00006
33 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 20" WF P/L (PL-309) WHT EA-2A to ERP G-Island | 2820-NN-RP-033 | AD-27-Z-80548
34 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 16" WI P/L (PL-310) ERP G-Island to WHT EA-2A | 2820-NN-RP-034 | AD-3002-Z-00009
35 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-311) ERP G-Island to WHT EA-2A | 2820-NN-RP-035 | AD-3002-Z-00010
36 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 22" WF P/L (PL-317) WHT EA-6 to WHT EA-4 | 2820-NN-RP-036 | AD-822-Z-00003
37 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 18" WI P/L (PL-318) WHT EA-4 to WHT EA-6 | 2820-NN-RP-037 | AD-820-Z-00005
38 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-319) WHT EA-4 to WHT EA-6 | 2820-NN-RP-038 | AD-820-Z-00006
39 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 22" WF P/L (PL-321)WHT EA-4 to ERP G-Island | 2820-NN-RP-039 | AD-820-Z-00007
40 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 18" WI P/L (PL-322) ERP G-Island to WHT EA-4 | 2820-NN-RP-040 | AD-3002-Z-00011
41 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-323) ERP G-Island to WHT EA-4 | 2820-NN-RP-041 | AD-3002-Z-00012
42 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 30" WG P/L (PL-325) ERP G-Island to ZWSC-RP2 | 2820-NN-RP-042 | AD-3002-Z-00013
43 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 20" GE P/L (PL-326) ERP G-Island to ZWSC-RP2 | 2820-NN-RP-043 | AD-3002-Z-00014
44 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 30" OE P/L (PL-329) ERP G-Island to ZWSC-NRP | 2820-NN-RP-044 | AD-3002-Z-00015
45 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 14" WF P/L (PL-330 WHT-1 AGI Area to ERP G-Island | 2820-NN-RP-045 | AD-811-Z-00003
46 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-331)ERP G-Island to WHT-1 AGI Area | 2820-NN-RP-046 | AD-3002-Z-00016
47 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-334) WHT ZK-182 to ERP G-Island | 2820-NN-RP-047 | AD-324-Z-00003
48 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 38" WF P/L (PL-335) ZCSC-CRP to ERP G-Island | 2820-NN-RP-048 | AD-496-Z-00011
49 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-337) WHT in AGI Area to EPS-2 WHT-2 | 2820-NN-RP-049 | AD-811-Z-00004
50 | LOWER ZAKUM LTDP1 PACKAGE 4 - DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-338) EPS-2 WHT-2 to EPS-2 WHT-3 | 2820-NN-RP-050 | AD-848-Z-00060
51 | LOWER ZAKUM LTDP1 PACKAGE 4 - INSTALLATION ANALYSIS REPORT FOR 132KV CABLES | 2820-NN-RP-051 | AD-27-Z-80549
52 | LOWER ZAKUM LTDP1 PACKAGE 4 - INSTALLATION ANALYSIS REPORT FOR 6.6KV CABLES | 2820-NN-RP-052 | AD-27-Z-80550
53 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 1 | 2820-NN-RP-053 | AD-27-Z-80551
54 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 2 | 2820-NN-RP-054 | AD-27-Z-80552
55 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 3 | 2820-NN-RP-055 | AD-27-Z-80553
56 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 4 | 2820-NN-RP-056 | AD-27-Z-80554
57 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 5 | 2820-NN-RP-057 | AD-27-Z-80555
58 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 6 | 2820-NN-RP-058 | AD-27-Z-80556
59 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 7 | 2820-NN-RP-059 | AD-27-Z-80557
60 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 8 | 2820-NN-RP-060 | AD-27-Z-80558
61 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 9 | 2820-NN-RP-061 | AD-27-Z-80559
62 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 10 | 2820-NN-RP-062 | AD-27-Z-80560
63 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 11 | 2820-NN-RP-063 | AD-27-Z-80561
64 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 12 | 2820-NN-RP-064 | AD-27-Z-80562
65 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-1) | 2820-NN-RP-065 | AD-27-Z-80563
66 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-2) | 2820-NN-RP-066 | AD-27-Z-80564
67 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-3) | 2820-NN-RP-067 | AD-27-Z-80565
68 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-4) | 2820-NN-RP-068 | AD-27-Z-80566
69 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-5) | 2820-NN-RP-069 | AD-27-Z-80567
70 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-6) | 2820-NN-RP-070 | AD-27-Z-80568
71 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-7) | 2820-NN-RP-071 | AD-27-Z-80569
72 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-8) | 2820-NN-RP-072 | AD-27-Z-80570
73 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE MATTRESSES ON CB 1 | 2820-NN-RP-073 | AD-27-Z-80571
74 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE MATTRESSES ON CB 2 | 2820-NN-RP-074 | AD-27-Z-80572
75 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 1 | 2820-NN-RP-075 | AD-27-Z-80573 | 1 | REMARKS |  |  |  | 2026-06-29 | 2820-NMDC-E-AO-PMT-T-00854 |  |  |  | 2026-07-08 | 2820-NMDC-E-PMT-MWS-T-00013 2820-NMDC-E-PMT-MWS-T-00018 | 10-07-2026 22-07-2026 | SAF234-MCE-NMDC-T-0005 SAF234-MCE-NMDC-T-00057 | APPROVED | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
76 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 2 | 2820-NN-RP-076 | AD-27-Z-80574 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
77 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 3 | 2820-NN-RP-077 | AD-27-Z-80575 |  | REMARKS |  |  |  | 2026-09-02 | 2820-NMDC-E-AO-PMT-T-01037 | [8 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
78 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 4 | 2820-NN-RP-078 | AD-27-Z-80576 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
79 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 5 | 2820-NN-RP-079 | AD-27-Z-80577 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
80 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 6 | 2820-NN-RP-080 | AD-27-Z-80578 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
81 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 7 | 2820-NN-RP-081 | AD-27-Z-80579 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
82 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 8 | 2820-NN-RP-082 | AD-27-Z-80580 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
83 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 9 | 2820-NN-RP-083 | AD-27-Z-80581 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
84 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 10 | 2820-NN-RP-084 | AD-27-Z-80582 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
85 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 11 | 2820-NN-RP-085 | AD-27-Z-80583 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
86 | LOWER ZAKUM LTDP1 PACKAGE 4 - SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 12 | 2820-NN-RP-086 | AD-27-Z-80584 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)

## Documents - Naval Marine
|  | ADNOC OFFSHORE | [11 empty] | NMDC ENERGY DOC. No.:
ADNOC LZ LTDP-1 PROJECT
|  | NMDC ENERGY PROJECT NO. 2820 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (NAVAL MARINE) | [11 empty] | DATE : |  |  |  | 2025-11-10
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 1 | 2820-ZZ-CL-001 | AD-27-Z-80585
2 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 2 | 2820-ZZ-CL-002 | AD-27-Z-80586
3 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 3 | 2820-ZZ-CL-003 | AD-27-Z-80587
4 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 4 | 2820-ZZ-CL-004 | AD-27-Z-80588
5 | LOWER ZAKUM LTDP-1PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 5 | 2820-ZZ-CL-005 | AD-27-Z-80589
6 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 6 | 2820-ZZ-CL-006 | AD-27-Z-80590
7 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 7 | 2820-ZZ-CL-007 | AD-27-Z-80591
8 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 8 | 2820-ZZ-CL-008 | AD-27-Z-80592
9 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 9 | 2820-ZZ-CL-009 | AD-27-Z-80593
10 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 10 | 2820-ZZ-CL-010 | AD-27-Z-80594
11 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 11 | 2820-ZZ-CL-011 | AD-27-Z-80595
12 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 12 | 2820-ZZ-CL-012 | AD-27-Z-80596
13 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-1) | 2820-ZZ-CL-013 | AD-27-Z-80597
14 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-2) | 2820-ZZ-CL-014 | AD-27-Z-80598
15 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-3) | 2820-ZZ-CL-015 | AD-27-Z-80599
16 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-4) | 2820-ZZ-CL-016 | AD-27-Z-80600
17 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-5) | 2820-ZZ-CL-017 | AD-27-Z-80601
18 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-6) | 2820-ZZ-CL-018 | AD-27-Z-80602
19 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-7) | 2820-ZZ-CL-019 | AD-27-Z-80603
20 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-8) | 2820-ZZ-CL-020 | AD-27-Z-80604
21 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE MATTRESSES ON CB 1 | 2820-ZZ-CL-021 | AD-27-Z-80605
22 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE MATTRESSES ON CB 2 | 2820-ZZ-CL-022 | AD-27-Z-80606
23 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 1 | 2820-ZZ-CL-023 | AD-27-Z-80607 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
24 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 2 | 2820-ZZ-CL-024 | AD-27-Z-80608 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
25 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 3 | 2820-ZZ-CL-025 | AD-27-Z-80609 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
26 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 4 | 2820-ZZ-CL-026 | AD-27-Z-80610 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
27 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 5 | 2820-ZZ-CL-027 | AD-27-Z-80611 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
28 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 6 | 2820-ZZ-CL-028 | AD-27-Z-80612 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
29 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 7 | 2820-ZZ-CL-029 | AD-27-Z-80613 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
30 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 8 | 2820-ZZ-CL-030 | AD-27-Z-80614 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
31 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 9 | 2820-ZZ-CL-031 | AD-27-Z-80615 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
32 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 10 | 2820-ZZ-CL-032 | AD-27-Z-80616 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
33 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 11 | 2820-ZZ-CL-033 | AD-27-Z-80617 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
34 | LOWER ZAKUM LTDP-1 PACKAGE 4 - STABILITY ANALYSIS REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE 12 | 2820-ZZ-CL-034 | AD-27-Z-80618 |  | REMARKS | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
35 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 22" WF P/L (PL-301) FROM FROM WHT EA-1 TO WHT EA-5 | 2820-ZZ-CL-035 | AD-817-Z-00004 | 1 | 2 |  | 2026-07-22 | CSE-2820-PMT-T-009 | 2026-07-23 | 2820-NMDC-E-AO-PMT-T-00928 | 2026-07-30 | LZ-LTDP-1-10222-PKG4-TN-06150 | 2 | 2026-07-23 | 2820-NMDC-E-PMT-MWS-T-00020 | 2026-07-27 | SAF234-MCE-NMDC-T-0008 | HOLD | TITLE CHANGED
|  |  |  | 2 | 2 |  | 2026-08-03 | CSE-2820-PMT-T-014 | 2026-08-04 | 2820-NMDC-E-AO-PMT-T-00961 | 2026-08-12 | LZ-LTDP-1-10222-PKG4-TN-06301 | 2 | 2026-08-04 | 2820-NMDC-E-PMT-MWS-T-00028 | 2026-08-05 | SAF234-MCE-NMDC-T-0011 | APPROVED
36 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 16" WI P/L (PL-302) FROM WHT EA-5 to WHT EA-1 | 2820-ZZ-CL-036 | AD-817-Z-00005
37 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 6" GL P/L (PL-303) FROM WHT EA-5 to WHT EA-1 | 2820-ZZ-CL-037 | AD-821-Z-00008
38 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 22" WF P/L (PL-305) FROM WHT EA-5 to WHT EA-2B | 2820-ZZ-CL-038 | AD-821-Z-00009 | 1 | 2 |  | 2026-07-27 | CSE-2820-PMT-T-013 | 2026-07-27 | 2820-NMDC-E-AO-PMT-T-00939 | 2026-07-30 | LZ-LTDP-1-10222-PKG4-TN-06150 | 2 | 2026-07-27 | 2820-NMDC-E-PMT-MWS-T-00024 | 2026-07-30 | SAF234-MCE-NMDC-T-0010 | HOLD
|  |  |  | 2 | 2 |  | 2026-08-03 | CSE-2820-PMT-T-015 | 2026-08-04 | 2820-NMDC-E-AO-PMT-T-00961 | 2026-08-12 | LZ-LTDP-1-10222-PKG4-TN-06301 | 2
39 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 16" WI P/L (PL-306) FROM WHT EA-2B to WHT EA-5 | 2820-ZZ-CL-039 | AD-818-Z-00007
40 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 6" GL P/L (PL-307) FROM WHT EA-2A to WHT EA-5 | 2820-ZZ-CL-040 | AD-818-Z-00008
41 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 20" WF P/L (PL-309) FROM WHT EA-2A to ERP G-Island | 2820-ZZ-CL-041 | AD-818-Z-00009
42 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 16" WI P/L (PL-310) FROM ERP G-Island to WHT EA-2A | 2820-ZZ-CL-042 | AD-3002-Z-00017
43 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 6" GL P/L (PL-311) FROM ERP G-Island to WHT EA-2A | 2820-ZZ-CL-043 | AD-3002-Z-00018
44 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 20" WF P/L (PL-317) FROM WHT EA-6 TO WHT EA-4 | 2820-ZZ-CL-044 | AD-822-Z-00004 | 1 | 2 |  | 2026-07-22 | CSE-2820-PMT-T-009 | 2026-07-23 | 2820-NMDC-E-AO-PMT-T-00928 | 2026-07-30 | LZ-LTDP-1-10222-PKG4-TN-06150 | 2 | 2026-07-23 | 2820-NMDC-E-PMT-MWS-T-00020 | 2026-07-30 | SAF234-MCE-NMDC-T-0010 | HOLD
|  |  |  | 2 | 2 |  | 2026-08-03 | CSE-2820-PMT-T-016 | 2026-08-04 | 2820-NMDC-E-AO-PMT-T-00961 | 2026-08-12 | LZ-LTDP-1-10222-PKG4-TN-06301 | 2
45 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 18" WI P/L (PL-318) FROM WHT EA-4 to WHT EA-6 | 2820-ZZ-CL-045 | AD-820-Z-00008
46 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 6" GL P/L (PL-319) FROM WHT EA-4 to WHT EA-6 | 2820-ZZ-CL-046 | AD-820-Z-00009
47 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 20" WF P/L (PL-321) FROM WHT EA-4 TO ERP AOI­ ISLAND | 2820-ZZ-CL-047 | AD-820-Z-00010 | 1 | 2 | TITTLE CHANGED | 2026-07-13 | CSE-2820-PMT-T-008 | 2026-07-14 | 2820-NMDC-E-AO-PMT-T-00900 |  |  |  | 2026-07-14 | 2820-NMDC-E-PMT-MWS-T-00015 | 2026-07-15 | SAF234-MCE-NMDC-T-0006 | HOLD
|  |  |  | CRS | [9 empty] | 2026-07-23 | 2820-NMDC-E-PMT-MWS-T-00019 | 2026-07-27 | SAF234-MCE-NMDC-T-0008 | APPROVED
48 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 18" WI P/L (PL-322) FROM ERP G-Island to WHT EA-4 | 2820-ZZ-CL-048 | AD-820-Z-00011
49 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 6" GL P/L (PL-323) FROM ERP G-Island to WHT EA-4 | 2820-ZZ-CL-049 | AD-3002-Z-00019
50 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 30" WG P/L (PL-325) FROM ERP G-Island to ZWSC-RP2 | 2820-ZZ-CL-050 | AD-3002-Z-00020
51 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 20" GE P/L (PL-326) FROM ERP G-Island to ZWSC-RP2 | 2820-ZZ-CL-051 | AD-3002-Z-00021
52 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 30" OE P/L (PL-329) FROM ERP G-Island to ZWSC-NRP | 2820-ZZ-CL-052 | AD-3002-Z-00022
53 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 18" WF P/L (PL-330) FROM AOI­ ERP TO WHT­1 AGI AREA | 2820-ZZ-CL-053 | AD-811-Z-00005 | 1 | 2 | TITTLE CHANGED | 2026-07-13 | CSE-2820-PMT-T-007 | 2026-07-14 | 2820-NMDC-E-AO-PMT-T-00902 |  |  |  | 2026-07-14 | 2820-NMDC-E-PMT-MWS-T-00016 | 2026-07-15 | SAF234-MCE-NMDC-T-0006 | HOLD
|  |  |  | CRS | [9 empty] | 2026-07-23 | 2820-NMDC-E-PMT-MWS-T-00019 | 2026-07-27 | SAF234-MCE-NMDC-T-0008 | APPROVED
54 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 6" GL P/L (PL-331) FROM ERP G-Island to WHT-1 AGI Area | 2820-ZZ-CL-054 | AD-3002-Z-00023
55 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 6" GL P/L (PL-334) FROM WHT ZK-182 to ERP G-ISLAND | 2820-ZZ-CL-055 | AD-324-Z-00004
56 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 38" WF P/L (PL-335) FROM ZCSC-CRP TO ERP AOI ISLAND | 2820-ZZ-CL-056 | AD-496-Z-00012 | 1 | 2 | TITTLE CHANGED | 2026-07-22 | CSE-2820-PMT-T-009 | 2026-07-23 | 2820-NMDC-E-AO-PMT-T-00928 | 2026-07-30 | LZ-LTDP-1-10222-PKG4-TN-06150 | 2 | 2026-07-23 | 2820-NMDC-E-PMT-MWS-T-00020 | 2026-07-30 | SAF234-MCE-NMDC-T-0010 | HOLD
|  |  |  | 2 | 2 |  | 2026-08-03 | CSE-2820-PMT-T-017 | 2026-08-04 | 2820-NMDC-E-AO-PMT-T-00961 | 2026-08-12 | LZ-LTDP-1-10222-PKG4-TN-06301 | 2
57 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 6" GL P/L (PL-337) FROM WHT in AGI Area to EPS-2 WHT-2 | 2820-ZZ-CL-057 | AD-811-Z-00006
58 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR 6" GL P/L (PL-338) FROM EPS-2 WHT-2 to EPS-2 WHT-3 | 2820-ZZ-CL-058 | AD-814-Z-00076
59 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR BST JACKET INSTALLATION AT AL OMAIRAH ISLAND | 2820-ZZ-CL-059 | AD-27-Z-80619
60 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR BST DECK AND FLARE INSTALLATION AT AL OMAIRAH ISLAND | 2820-ZZ-CL-060 | AD-27-Z-80620
61 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR FST JACKET INSTALLATION AT AL OMAIRAH ISLAND | 2820-ZZ-CL-061 | AD-27-Z-80621
62 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR FST DECK AND FLARE INSTALLATION AT AL OMAIRAH ISLAND | 2820-ZZ-CL-062 | AD-27-Z-80622
63 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR WHT EA-2A JACKET INSTALLATION | 2820-ZZ-CL-063 | AD-818-Z-00010
64 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR WHT EA-2A DECK INSTALLATION | 2820-ZZ-CL-064 | AD-818-Z-00011
65 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR WHT EA-2B JACKET INSTALLATION | 2820-ZZ-CL-065 | AD-818-Z-00012
66 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR WHT EA-2B DECK INSTALLATION | 2820-ZZ-CL-066 | AD-818-Z-00013
67 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR WHT EA-1 JACKET INSTALLATION | 2820-ZZ-CL-067 | AD-817-Z-00006
68 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR WHT EA-1 DECK INSTALLATION | 2820-ZZ-CL-068 | AD-817-Z-00007
69 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR RISER INSTALLATION AT ZCSC-CRP | 2820-ZZ-CL-069 | AD-496-Z-00013
70 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR RISER INSTALLATION AT ZWSC-RP2 | 2820-ZZ-CL-070 | AD-812-Z-00006
71 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR RISER INSTALLATION AT ZWSC-NRP | 2820-ZZ-CL-071 | AD-417-Z-00002
72 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR RISER INSTALLATION AT ZK-182 | 2820-ZZ-CL-072 | AD-324-Z-00005
73 | LOWER ZAKUM LTDP1 PACKAGE 4 - MOORING ANALYSIS REPORT FOR RISER INSTALLATION AT ESP2-WHT 3 | 2820-ZZ-CL-073 | AD-849-Z-00048
74
75
76

## Drawings
|  | ADNOC OFFSHORE | [11 empty] | NMDC ENERGY DOC. No.:
ADNOC LZ LTDP-1 PROJECT
|  | NMDC ENERGY PROJECT NO. 2820 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (DRAWINGS) | [11 empty] | DATE : |  |  |  | 2025-11-10
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 20" PIPELINE FROM WHT EA-6 TO WHT EA-4 (PL-317) | 2820-NN-0001 | AD-27-PL-625429-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
2 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 16" PIPELINE | 2820-NN-0002 | AD-27-PL-625430-SHT-001 |  |  | remarks | [12 empty] | Cancelled (in this project there is no 16'' pipeline)
3 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 6" PIPELINE FROM ERP TO WHT EA-4 (PL-323) | 2820-NN-0003 | AD-27-PL-625431-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
4 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 22" PIPELINE FROM WHT EA-1 TO WHT EA-5 (PL-301) | 2820-NN-0004 | AD-27-PL-625432-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
5 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 18" PIPELINE FROM WHT-1 AGI TO ERP (PL-330) | 2820-NN-0005 | AD-27-PL-625433-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
6 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 30" PIPELINE FROM ERP ZWSC-NRP (PL-329) | 2820-NN-0006 | AD-27-PL-625434-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
7 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 14" PIPELINE FROM WHT EA-2B TO WHT EA-5 (PL-306) | 2820-NN-0007 | AD-27-PL-625435-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
8 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 38" PIPELINE FROM ZCSC TO ERP (PL-335) | 2820-NN-0008 | AD-27-PL-625436-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
9 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 20" PIPELINE FROM WHT EA-6 TO WHT EA-4 (PL-317) | 2820-NN-0009 | AD-27-PL-625437-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
10 | LOWER ZAKUM LTDP- PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 16" PIPELINE | 2820-NN-0010 | AD-27-PL-625438-SHT-001 |  |  | remarks | [12 empty] | Cancelled (in this project there is no 16'' pipeline)
11 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 6" PIPELINE FROM ERP TO WHT EA-4 (PL-323) | 2820-NN-0011 | AD-27-PL-625439-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
12 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 22" PIPELINE FROM WHT EA-1 TO WHT EA-5 (PL-301) | 2820-NN-0012 | AD-27-PL-625440-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
13 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 18" PIPELINE FROM WHT-1 AGI TO ERP (PL-330) | 2820-NN-0013 | AD-27-PL-625441-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
14 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 30" PIPELINE FROM ERP ZWSC-NRP (PL-329) | 2820-NN-0014 | AD-27-PL-625442-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
15 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 14" PIPELINE FROM WHT EA-2B TO WHT EA-5 (PL-306) | 2820-NN-0015 | AD-27-PL-625443-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
16 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 38" PIPELINE FROM ZCSC TO ERP (PL-335) | 2820-NN-0016 | AD-27-PL-625444-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
17 | LOWER ZAKUM LTDP- PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 20" PIPELINE FROM WHT EA-6 TO WHT EA-4 (PL-317) | 2820-NN-0017 | AD-27-PL-625445-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
18 | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 16" PIPELINE | 2820-NN-0018 | AD-27-PL-625446-SHT-001 |  |  | remarks | [12 empty] | Cancelled (in this project there is no 16'' pipeline)
19 | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 6" PIPELINE FROM ERP TO WHT EA-4 (PL-323) | 2820-NN-0019 | AD-27-PL-625447-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
20 | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 22" PIPELINE FROM WHT EA-1 TO WHT EA-5 (PL-301) | 2820-NN-0020 | AD-27-PL-625448-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
21 | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 18" PIPELINE FROM WHT-1 AGI TO ERP (PL-330) | 2820-NN-0021 | AD-27-PL-625449-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
22 | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 30" PIPELINE FROM ERP ZWSC-NRP (PL-329) | 2820-NN-0022 | AD-27-PL-625450-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
23 | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 14" PIPELINE FROM WHT EA-2B TO WHT EA-5 (PL-306) | 2820-NN-0023 | AD-27-PL-625451-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
24 | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 38" PIPELINE FROM ZCSC TO ERP (PL-335) | 2820-NN-0024 | AD-27-PL-625452-SHT-001 | [15 empty] | title changed email sent to pmt on 09/06
25 | LOWER ZAKUM LTDP-1 PACKAGE 4 - BUCKLE DETECTOR FOR 20" PIPELINE | 2820-NN-0025 | AD-27-PL-625453-SHT-001
26 | LOWER ZAKUM LTDP-1 PACKAGE 4 - BUCKLE DETECTOR FOR 16" PIPELINE | 2820-NN-0026 | AD-27-PL-625454-SHT-001
27 | LOWER ZAKUM LTDP-1 PACKAGE 4 - BUCKLE DETECTOR FOR 6" PIPELINE | 2820-NN-0027 | AD-27-PL-625455-SHT-001
28 | LOWER ZAKUM LTDP-1 PACKAGE 4 - BUCKLE DETECTOR FOR 22" PIPELINE | 2820-NN-0028 | AD-27-PL-625456-SHT-001
29 | LOWER ZAKUM LTDP-1 PACKAGE 4 - BUCKLE DETECTOR FOR 18" PIPELINE | 2820-NN-0029 | AD-27-PL-625457-SHT-001
30 | LOWER ZAKUM LTDP-1 PACKAGE 4 - BUCKLE DETECTOR FOR 30" PIPELINE | 2820-NN-0030 | AD-27-PL-625458-SHT-001
31 | LOWER ZAKUM LTDP-1 PACKAGE 4 - BUCKLE DETECTOR FOR 14" PIPELINE | 2820-NN-0031 | AD-27-PL-625459-SHT-001
32 | LOWER ZAKUM LTDP-1 PACKAGE 4 - BUCKLE DETECTOR FOR 38" PIPELINE | 2820-NN-0032 | AD-27-PL-625460-SHT-001
33 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TEMPORARY PIG LAUNCHER/ RECEVIER FOR 20" PIPELINE | 2820-NN-0033 | AD-27-PL-625461-SHT-001
34 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TEMPORARY PIG LAUNCHER/ RECEVIER FOR 16" PIPELINE | 2820-NN-0034 | AD-27-PL-625462-SHT-001
35 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TEMPORARY PIG LAUNCHER/ RECEVIER FOR 6" PIPELINE | 2820-NN-0035 | AD-27-PL-625463-SHT-001
36 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TEMPORARY PIG LAUNCHER/ RECEVIER FOR 22" PIPELINE | 2820-NN-0036 | AD-27-PL-625464-SHT-001
37 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TEMPORARY PIG LAUNCHER/ RECEVIER FOR 18" PIPELINE | 2820-NN-0037 | AD-27-PL-625465-SHT-001
38 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TEMPORARY PIG LAUNCHER/ RECEVIER FOR 30" PIPELINE | 2820-NN-0038 | AD-27-PL-625466-SHT-001
39 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TEMPORARY PIG LAUNCHER/ RECEVIER FOR 14" PIPELINE | 2820-NN-0039 | AD-27-PL-625467-SHT-001
40 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TEMPORARY PIG LAUNCHER/ RECEVIER FOR 38" PIPELINE | 2820-NN-0040 | AD-27-PL-625468-SHT-001
41 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS BY USING MP-01 | 2820-NN-0041 | AD-27-PL-625469-SHT-001 | 1 | remarks |  |  |  | 2026-07-31 | 2820-NMDC-E-AO-PMT-T-00954 |  |  |  | 2026-07-31 | 2820-NMDC-E-PMT-MWS-T-00013 | 2026-08-05 | SAF234-MCE-NMDC-T-0012 | approved | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
42 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE CLAMPS AT LOCATION 1 | 2820-NN-0042 | AD-27-PL-625470-SHT-001
43 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE CLAMPS AT LOCATION 2 | 2820-NN-0043 | AD-27-PL-625471-SHT-001
44 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE CLAMPS AT LOCATION 3 | 2820-NN-0044 | AD-27-PL-625472-SHT-001
45 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE CLAMPS AT LOCATION 4 | 2820-NN-0045 | AD-27-PL-625473-SHT-001
46 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE CLAMPS AT LOCATION 5 | 2820-NN-0046 | AD-27-PL-625474-SHT-001
47 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE CLAMPS AT LOCATION 6 | 2820-NN-0047 | AD-27-PL-625475-SHT-001
48 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE CLAMPS AT LOCATION 7 | 2820-NN-0048 | AD-27-PL-625476-SHT-001
49 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOWER ZAKUM – TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL317, PL318, PL319 & PL334 BY USING MP-01 | 2820-NN-0049 | AD-27-PL-625477-SHT-001 | 1 | 2 | remarks | 2026-03-11 | CSE-2820-PMT-T-001 | 2026-07-23 | 2820-NMDC-E-AO-PMT-T-00934 |  |  |  | 2026-07-08 | 2820-NMDC-E-PMT-MWS-T-00013 | 10-07-2027 30-07-2026 | SAF234-MCE-NMDC-T-0005 SAF234-MCE-NMDC-T-0010 | approved | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
50 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS AT PL335 (CR02) BY USING DLB-750 | 2820-NN-0050 | AD-27-PL-625478-SHT-001 |  | remarks | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
51 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE AT LOCATION 1 | 2820-NN-0051 | AD-27-PL-625479-SHT-001
52 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE AT LOCATION 2 | 2820-NN-0052 | AD-27-PL-625480-SHT-001
53 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE AT LOCATION 3 | 2820-NN-0053 | AD-27-PL-625481-SHT-001
54 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE AT LOCATION 4 | 2820-NN-0054 | AD-27-PL-625482-SHT-001
55 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE AT LOCATION 5 | 2820-NN-0055 | AD-27-PL-625483-SHT-001
56 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE AT LOCATION 6 | 2820-NN-0056 | AD-27-PL-625484-SHT-001
57 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LIFTING & INSTALLATION OF J-TUBE AT LOCATION 7 | 2820-NN-0057 | AD-27-PL-625485-SHT-001
58 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TYPICAL LIFTING AND INSTALLATION OF CONCRETE MATTRESS (USING MP-01) | 2820-NN-0058 | AD-27-PL-625486-SHT-001
59 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TYPICAL LIFTING AND INSTALLATION OF CONCRETE MATTRESS (USING MP-02) | 2820-NN-0059 | AD-27-PL-625487-SHT-001
60 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 1 | 2820-NN-0060 | AD-27-PL-625488-SHT-001
61 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 2 | 2820-NN-0061 | AD-27-PL-625489-SHT-001
62 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 3 | 2820-NN-0062 | AD-27-PL-625490-SHT-001
63 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 4 | 2820-NN-0063 | AD-27-PL-625491-SHT-001
64 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 5 | 2820-NN-0064 | AD-27-PL-625492-SHT-001
65 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 6 | 2820-NN-0065 | AD-27-PL-625493-SHT-001
66 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 7 | 2820-NN-0066 | AD-27-PL-625494-SHT-001
67 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 8 | 2820-NN-0067 | AD-27-PL-625495-SHT-001
68 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 9 | 2820-NN-0068 | AD-27-PL-625496-SHT-001
69 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 10 | 2820-NN-0069 | AD-27-PL-625497-SHT-001
70 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 11 | 2820-NN-0070 | AD-27-PL-625498-SHT-001
71 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 12 | 2820-NN-0071 | AD-27-PL-625499-SHT-001
72 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 13 | 2820-NN-0072 | AD-27-PL-625500-SHT-001
73 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON CARGO BARGE 14 | 2820-NN-0073 | AD-27-PL-625501-SHT-001
74 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-1) | 2820-NN-0074 | AD-27-PL-625502-SHT-001
75 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-2) | 2820-NN-0075 | AD-27-PL-625503-SHT-001
76 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-3) | 2820-NN-0076 | AD-27-PL-625504-SHT-001
77 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-4) | 2820-NN-0077 | AD-27-PL-625505-SHT-001
78 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-5) | 2820-NN-0078 | AD-27-PL-625506-SHT-001
79 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-6) | 2820-NN-0079 | AD-27-PL-625507-SHT-001
80 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-7) | 2820-NN-0080 | AD-27-PL-625508-SHT-001
81 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-8) | 2820-NN-0081 | AD-27-PL-625509-SHT-001
82 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-9) | 2820-NN-0082 | AD-27-PL-625510-SHT-001
83 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-10) | 2820-NN-0083 | AD-27-PL-625511-SHT-001
84 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE MATTRESSES ON CB 1 | 2820-NN-0084 | AD-27-PL-625512-SHT-001
85 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE MATTRESSES ON CB 2 | 2820-NN-0085 | AD-27-PL-625513-SHT-001
86 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS AT PL335 (CR06 TO CR16) BY USING MP-02 | 2820-NN-0086 | AD-27-PL-625514-SHT-001 |  | remarks | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
87 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 1 | 2820-NN-0087 | AD-27-PL-625515-SHT-001 | 1 | remarks |  |  |  | 2026-06-29 | 2820-NMDC-E-AO-PMT-T-00852 |  |  |  | 2026-07-08 | 2820-NMDC-E-PMT-MWS-T-00013 | 2027-07-10 | SAF234-MCE-NMDC-T-0005 SAF234-MCE-NMDC-T-0007 | APPROVED | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
88 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 2 | 2820-NN-0088 | AD-27-PL-625516-SHT-001 | 1 | remarks |  |  |  | 2026-07-21 | 2820-NMDC-E-AO-PMT-T-00916 | 03-09-206 | LZ-LTDP-1-10222-PKG4-TN-06538 | 2 | 2026-07-21 | 2820-NMDC-E-PMT-MWS-T-00018 | 2027-07-22 | SAF234-MCE-NMDC-T-0007 | APPROVED | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
89 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 3 | 2820-NN-0089 | AD-27-PL-625517-SHT-001 | 1 | remarks |  |  |  | 2026-07-21 | 2820-NMDC-E-AO-PMT-T-00916 | 03-09-206 | LZ-LTDP-1-10222-PKG4-TN-06538 | 2 | 2026-07-21 | 2820-NMDC-E-PMT-MWS-T-00018 | 2027-07-22 | SAF234-MCE-NMDC-T-0007 | APPROVED | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
90 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 4 | 2820-NN-0090 | AD-27-PL-625518-SHT-001 | 1 | remarks |  |  |  | 2026-07-21 | 2820-NMDC-E-AO-PMT-T-00916 | 03-09-206 | LZ-LTDP-1-10222-PKG4-TN-06538 | 2 | 2026-07-21 | 2820-NMDC-E-PMT-MWS-T-00018 | 2027-07-22 | SAF234-MCE-NMDC-T-0007 | APPROVED | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
91 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 5 | 2820-NN-0091 | AD-27-PL-625519-SHT-001 | 1 | remarks |  |  |  | 2026-07-21 | 2820-NMDC-E-AO-PMT-T-00916 | 03-09-206 | LZ-LTDP-1-10222-PKG4-TN-06538 | 2 | 2026-07-21 | 2820-NMDC-E-PMT-MWS-T-00018 | 2027-07-22 | SAF234-MCE-NMDC-T-0007 | APPROVED | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
92 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 6 | 2820-NN-0092 | AD-27-PL-625520-SHT-001 |  | remarks | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
93 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 7 | 2820-NN-0093 | AD-27-PL-625521-SHT-001 |  | remarks | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
94 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 8 | 2820-NN-0094 | AD-27-PL-625522-SHT-001 |  | remarks | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
95 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 9 | 2820-NN-0095 | AD-27-PL-625523-SHT-001 |  | remarks | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
96 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 10 | 2820-NN-0096 | AD-27-PL-625524-SHT-001 |  | remarks | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
97 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 11 | 2820-NN-0097 | AD-27-PL-625525-SHT-001 |  | remarks | [13 empty] | Safeen Subsea (Ahmed Ismail Mohamed's email dtd. 25-06-2026)
98 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON CARGO BARGE 12 | 2820-NN-0098 | AD-27-PL-625526-SHT-001 |  | remarks
99 | LOWER ZAKUM LTDP1 PACKAGE 4 - LIFTING & INSTALLATION OF 38in RISER AT ZCSC-CRP (PL-335) | 2820-NN-0099 | AD-27-PL-625527-SHT-001
100 | LOWER ZAKUM LTDP1 PACKAGE 4 - LIFTING & INSTALLATION OF 20in RISER AT ZWSC-RP2 (PL-326) | 2820-NN-0100 | AD-812-PL-000001-SHT-001
101 | LOWER ZAKUM LTDP1 PACKAGE 4 - LIFTING & INSTALLATION OF 30in RISER AT ZWSC-RP2 (PL-335) | 2820-NN-0101 | AD-812-PL-000002-SHT-001
102 | LOWER ZAKUM LTDP1 PACKAGE 4 - LIFTING & INSTALLATION OF 30in RISER AT ZWSC-NRP (PL-329) | 2820-NN-0102 | AD-417-PL-000003-SHT-001
103 | LOWER ZAKUM LTDP1 PACKAGE 4 - LIFTING & INSTALLATION OF 6in WELDED RISER AT ZK-182 (PL-334) | 2820-NN-0103 | AD-324-PL-625009-SHT-001
104 | LOWER ZAKUM LTDP1 PACKAGE 4 - LIFTING & INSTALLATION OF 6in RISER AT ESP2-WHT 3 (PL-338) | 2820-NN-0104 | AD-849-PL-625013-SHT-001
105 | LOWER ZAKUM LTDP1 PACKAGE 4 - LIFTING & INSTALLATION OF 6in RISER AT ESP2-WHT 2 (PL-338) | 2820-NN-0105 | AD-848-PL-625030-SHT-001
106 | LOWER ZAKUM LTDP1 PACKAGE 4 - LIFTING & INSTALLATION OF 30in RISER AT ZWSC-RP2 (PL-325) | 2820-NN-0106 | AD-812-PL-000003-SHT-001
107 | LOWER ZAKUM LTDP1 PACKAGE 4 - LIFTING & INSTALLATION OF 14in RISER AT AGI WHT-1 (PL-330) | 2820-NN-0107 | AD-27-PL-625527-SHT-001
108 | LOWER ZAKUM LTDP1 PACKAGE 4 - LIFTING & INSTALLATION OF 6in RISER AT AGI WHT-1 (PL-331) | 2820-NN-0108 | AD-27-PL-625528-SHT-001
109 | LOWER ZAKUM LTDP1 PACKAGE 4 - START-UP HEAD DETAILS FOR 20'' PIPELINE (PL-321) | 2820-NN-0109 | AD-27-PL-625529-SHT-001
110 | LOWER ZAKUM LTDP1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 20'' PIPELINE (PL-321) | 2820-NN-0110 | AD-27-PL-625530-SHT-001
111 | LOWER ZAKUM LTDP1 PACKAGE 4 - START-UP HEAD DETAILS FOR 18'' PIPELINE (PL-326) | 2820-NN-0111 | AD-27-PL-625531-SHT-001
112 | LOWER ZAKUM LTDP1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 18'' PIPELINE (PL-326) | 2820-NN-0112 | AD-27-PL-625532-SHT-001
113 | LOWER ZAKUM LTDP1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 18'' PIPELINE (PL-326) | 2820-NN-0113 | AD-27-PL-625533-SHT-001
114 | DETAILS OF BUCKLE DETECTOR FOR 18"x25.40W.T (PL-330) | 2820-NN-0114 | AD-27-PL-625535-SHT-001 | 1 | 2 |  | 2026-06-04 | CSE-2820-PMT-T-003 | 2026-06-04 | 2820-NMDC-E-AO-PMT-T-00779 | 2026-06-24 | LZ-LTDP-1-10222-PKG4-TN-05713 | 2 | 2026-06-25 | 2820-NMDC-E-PMT-MWS-T-00010
|  |  |  | 2 | 2 |  | 2026-09-08 | CSE-2820-PMT-T-020
115 | DETAILS OF BUCKLE DETECTOR FOR 18"x19.05W.T (PL-326) | 2820-NN-0115 | AD-27-PL-625536-SHT-001 | 1 | 2 |  | 2026-06-04 | CSE-2820-PMT-T-003 | 2026-06-04 | 2820-NMDC-E-AO-PMT-T-00779 | 2026-06-24 | LZ-LTDP-1-10222-PKG4-TN-05713 | 2 | 2026-06-25 | 2820-NMDC-E-PMT-MWS-T-00010
|  |  |  | 2 | 2 |  | 2026-09-08 | CSE-2820-PMT-T-020
116 | DETAILS OF BUCKLE DETECTOR FOR 20"x26.19W.T (PL-317 & PL-321) | 2820-NN-0116 | AD-27-PL-625537-SHT-001 | 1 | 2 |  | 2026-06-04 | CSE-2820-PMT-T-003 | 2026-06-04 | 2820-NMDC-E-AO-PMT-T-00779 | 2026-06-24 | LZ-LTDP-1-10222-PKG4-TN-05713 | 2 | 2026-06-25 | 2820-NMDC-E-PMT-MWS-T-00010
|  |  |  | 2 | 2 |  | 2026-09-08 | CSE-2820-PMT-T-020
117 | DETAILS OF BUCKLE DETECTOR FOR 22"x28.58W.T (PL-301 & PL-309) | 2820-NN-0117 | AD-27-PL-625538-SHT-001 | 1 | 2 |  | 2026-06-04 | CSE-2820-PMT-T-003 | 2026-06-04 | 2820-NMDC-E-AO-PMT-T-00779 | 2026-06-24 | LZ-LTDP-1-10222-PKG4-TN-05713 | 2 | 2026-06-25 | 2820-NMDC-E-PMT-MWS-T-00010
|  |  |  | 2 | 2 |  | 2026-09-08 | CSE-2820-PMT-T-020
118 | LOWER ZAKUM LTDP- PACKAGE 4 - START-UP HEAD DETAILS FOR 20'' PIPELINE FROM WHT EA-4 TO ERP (PL-321) | 2820-NN-0118 | AD-27-PL-625539-SHT-001 |  |  | NAR
119 | LOWER ZAKUM LTDP- PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 20'' PIPELINE FROM WHT EA-4 TO ERP (PL-321) | 2820-NN-0119 | AD-3022-PL-625201-SHT-001 |  |  | NAR
120 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 18" PIPELINE FROM ERP TO ZWSC RP2 (PL-326) | 2820-NN-0120 | AD-812-PL-0004-SHT-001 |  |  | NAR
121 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 18'' PIPELINE FROM ERP TO ZWSC RP2 (PL-326) | 2820-NN-0121 | AD-3022-PL-625202-SHT-001 |  |  | NAR
122 | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 18'' PIPELINE FROM ERP TO ZWSC RP2 (PL-326) | 2820-NN-0122 | AD-812-PL-0005-SHT-001 |  |  | NAR
123 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START-UP HEAD DETAILS FOR 22'' PIPELINE FROM WHT EA-5 TO WHT EA-2B (PL-305) | 2820-NN-0123 | AD-818-PL-625054-SHT-001 |  |  | NAR
124 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 22'' PIPELINE FROM WHT EA-5 TO WHT EA-2B (PL-305) | 2820-NN-0124 | AD-818-PL-625055-SHT-001 |  |  | NAR
125 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START-UP HEAD DETAILS FOR 22'' PIPELINE FROM WHT EA-2A TO ERP (PL-309) | 2820-NN-0125 | AD-3022-PL-625203-SHT-001 |  |  | NAR
126 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 22'' PIPELINE FROM WHT EA-2A TO ERP (PL-309) | 2820-NN-0126 | AD-3022-PL-625204-SHT-001 |  |  | NAR
127 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 6" PIPELINE FROM WHT EA-4 TO WHT EA-6 (PL-319) | 2820-NN-0127 | AD-822-PL-625013-SHT-001 |  |  | NAR
128 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 6" PIPELINE FROM WHT EA-4 TO WHT EA-6 (PL-319) | 2820-NN-0128 | AD-822-PL-625014-SHT-001 |  |  | NAR
129 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 6" PIPELINE FROM WHT EA-2B TO WHT EA-5 (PL-307) | 2820-NN-0129 | AD-821-PL-625037-SHT-001 |  |  | NAR
130 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 6" PIPELINE FROM WHT EA-2B TO WHT EA-5 (PL-307) | 2820-NN-0130 | AD-821-PL-625038-SHT-001 |  |  | NAR
131 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 6" PIPELINE FROM WHT EA-5 TO WHT EA-1 (PL-303) | 2820-NN-0131 | AD-817-PL-625021-SHT-001 |  |  | NAR
132 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 6" PIPELINE FROM WHT EA-5 TO WHT EA-1 (PL-303) | 2820-NN-0132 | AD-817-PL-625022-SHT-001 |  |  | NAR
133 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 6" PIPELINE FROM ERP TO WHT EA-2A (PL-311) | 2820-NN-0133 | AD-818-PL-625056-SHT-001 |  |  | NAR
134 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 6" PIPELINE FROM ERP TO WHT EA-2A (PL-311) | 2820-NN-0134 | AD-818-PL-625057-SHT-001 |  |  | NAR
135 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 6" PIPELINE FROM ERP TO WHT 1 AGI (PL-331) | 2820-NN-0135 | AD-811-PL-625145-SHT-001 |  |  | NAR
136 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 6" PIPELINE FROM ERP TO WHT 1 AGI (PL-331) | 2820-NN-0136 | AD-811-PL-625146-SHT-001 |  |  | NAR
137 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 6" PIPELINE FROM WHT-1 AGI TO EPS-2 WHT-2 (PL-337) | 2820-NN-0137 | AD-848-PL-625031-SHT-001 |  |  | NAR
138 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 6" PIPELINE FROM WHT-1 AGI TO EPS-2 WHT-2 (PL-337) | 2820-NN-0138 | AD-848-PL-625032-SHT-001 |  |  | NAR
139 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 6" PIPELINE FROM EPS-2 WHT-2 TO EPS-2 WHT-3 (PL-338) | 2820-NN-0139 | AD-849-PL-625014-SHT-001 |  |  | NAR
140 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 6" PIPELINE FROM EPS-2 WHT-2 TO EPS-2 WHT-3 (PL-338) | 2820-NN-0140 | AD-849-PL-625015-SHT-001 |  |  | NAR
141 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 6" PIPELINE FROM ZK-182 TO ERP (PL-334) | 2820-NN-0141 | AD-3022-PL-625205-SHT-001 |  |  | NAR
142 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 6" PIPELINE FROM ZK-182 TO ERP (PL-334) | 2820-NN-0142 | AD-3022-PL-625206-SHT-001 |  |  | NAR
143 | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 6" PIPELINE FROM ZK-182 TO ERP (PL-334) | 2820-NN-0143 | AD-3022-PL-625207-SHT-001 |  |  | NAR
144 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 14" PIPELINE FROM WHT EA-5 TO WHT EA-1 (PL-302) | 2820-NN-0144 | AD-817-PL-625023-SHT-001 |  |  | NAR
145 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 14" PIPELINE FROM WHT EA-5 TO WHT EA-1 (PL-302) | 2820-NN-0145 | AD-817-PL-625024-SHT-001 |  |  | NAR
146 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 14" PIPELINE FROM ERP TO WHT EA-2A (PL-310) | 2820-NN-0146 | AD-818-PL-625058-SHT-001 |  |  | NAR
147 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 14" PIPELINE FROM ERP TO WHT EA-2A (PL-310) | 2820-NN-0147 | AD-818-PL-625059-SHT-001 |  |  | NAR
148 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 14" PIPELINE FROM WHT EA-4 TO WHT EA-6 (PL-318) | 2820-NN-0148 | AD-822-PL-625015-SHT-001 |  |  | NAR
149 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 14" PIPELINE FROM WHT EA-4 TO WHT EA-6 (PL-318) | 2820-NN-0149 | AD-822-PL-625016-SHT-001 |  |  | NAR
150 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 14" PIPELINE FROM ERP TO WHT EA-4 (PL-322) | 2820-NN-0150 | AD-820-PL-625041-SHT-001 |  |  | NAR
151 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 14" PIPELINE FROM ERP TO WHT EA-4 (PL-322) | 2820-NN-0151 | AD-820-PL-625042-SHT-001 |  |  | NAR
152 | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 36" PIPELINE FROM ERP TO ZWSC-RP2 (PL-325) | 2820-NN-0152 | AD-812-PL-000006-SHT-001 |  |  | NAR
153 | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 36" PIPELINE FROM ERP TO ZWSC-RP2 (PL-325) | 2820-NN-0153 | AD-812-PL-000007-SHT-001 |  |  | NAR
154 | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 36" PIPELINE FROM ERP TO ZWSC-RP2 (PL-325) | 2820-NN-0154 | AD-812-PL-000008-SHT-001 |  |  | NAR
155 | LOWER ZAKUM LTDP-1 PACKAGE 4 – EMERGENCY LAYDOWN HEAD DETAILS FOR 22'' PIPELINE FROM WHT EA-5 TO WHT EA-2B (PL-305) | 2820-NN-0155 | AD-818-PL-625060-SHT-001 |  |  | NAR
156 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 18" PIPELINE HEAD 140MM CONCRETE (PL-330) | 2820-NN-0156 | AD-27-PL-625544-SHT-001 | 1 | 2 |  | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
157 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 18" PIPELINE HEAD 80MM CONCRETE (PL-330) | 2820-NN-0157 | AD-27-PL-625545-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
158 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 20" PIPELINE HEADS 125MM CONCRETE (PL-317) | 2820-NN-0158 | AD-27-PL-625546-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
159 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 20" PIPELINE HEAD 60MM CONCRETE (PL-321) | 2820-NN-0159 | AD-27-PL-625547-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
160 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 20" PIPELINE HEAD 80MM CONCRETE (PL-321) | 2820-NN-0160 | AD-27-PL-625548-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
161 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 22" PIPELINE HEAD 170MM CONCRETE (PL-301) | 2820-NN-0161 | AD-27-PL-625549-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
162 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 22" PIPELINE HEAD 150MM CONCRETE (PL-301) | 2820-NN-0162 | AD-27-PL-625550-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
163 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 22" PIPELINE HEADS 200MM CONCRETE (PL-305) | 2820-NN-0163 | AD-27-PL-625551-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
164 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 22" PIPELINE HEAD 200MM CONCRETE (PL-309) | 2820-NN-0164 | AD-27-PL-625552-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
165 | 2820-NN-0165 LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 22" PIPELINE HEAD 100MM CONCRETE (PL-309) | 2820-NN-0165 | AD-27-PL-625553-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
166 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 38" PIPELINE HEAD 170MM CONCRETE (PL-335) | 2820-NN-0166 | AD-27-PL-625559-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
167 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 38" PIPELINE HEAD 100MM CONCRETE (PL-335) | 2820-NN-0167 | AD-27-PL-625560-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
168 | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 38" PIPELINE HEAD 180MM CONCRETE (PL-335) | 2820-NN-0168 | AD-27-PL-625561-SHT-001 | 1 | 2 | NAR | 2026-07-03 | CSE-2820-PMT-T-005 | 2026-07-03 | 2820-NMDC-E-AO-PMT-T-00873 | 2026-08-10 | LZ-LTDP-1-10222-PKG4-TN-06247 | 2 | 2026-07-03 | 2820-NMDC-E-PMT-MWS-T-00012
169 | LOWER ZAKUM LTDP-1 PACKAGE 4 - DETAILS OF BUCKLE DETECTOR FOR 6"x15.88W.T (PL-319, PL-303, PL-307, PL-337, PL-338) | 2820-NN-0169 | AD-27-PL-625562-SHT-001 |  |  | remarks | [12 empty] | REV-1 DRG. SERVER ONLY - 27/07/2026
170 | LOWER ZAKUM LTDP-1 PACKAGE 4 - DETAILS OF BUCKLE DETECTOR FOR 6"x19.05W.T (PL-323, PL-331, PL-334, PL-311) | 2820-NN-0170 | AD-27-PL-625563-SHT-001 |  |  | remarks | [12 empty] | REV-1 DRG. SERVER ONLY - 27/07/2026
171 | LOWER ZAKUM LTDP-1 PACKAGE 4 - DETAILS OF BUCKLE DETECTOR FOR 14"x22.23W.T (PL-302, PL-306, PL-310, PL-318, PL-322) | 2820-NN-0171 | AD-27-PL-625564-SHT-001 |  |  | remarks | [12 empty] | REV-1 DRG. SERVER ONLY - 27/07/2026
172 | LOWER ZAKUM LTDP-1 PACKAGE 4 - DETAILS OF BUCKLE DETECTOR FOR 38"x41.28W.T (PL-335) | 2820-NN-0172 | AD-27-PL-625565-SHT-001 |  |  | remarks | [12 empty] | REV-1 DRG. SERVER ONLY - 27/07/2026
173 | LOWER ZAKUM LTDP-1 PACKAGE 4 - WHT-ZK-50 LIFTING & INSTALLATION OF J-TUBE BY SAFEEN PEARL | 2820-NN-0173 | AD-166-PL-625051-SHT-001 |  |  | remarks | [12 empty] | REV-1 DRG. SERVER ONLY - 31/08/2026
174 | LOWER ZAKUM LTDP-1 PACKAGE 4 - WHT-ZK-44 LIFTING & INSTALLATION OF J-TUBE BY SAFEEN PEARL | 2820-NN-0174 | AD-410-PL-625026-SHT-001 |  |  | remarks | [12 empty] | REV-1 DRG. SERVER ONLY - 31/08/2026
175 | LOWER ZAKUM LTDP-1 PACKAGE 4 - WHT-ZK-24 LIFTING & INSTALLATION OF J-TUBE BY SAFEEN PEARL | 2820-NN-0175 | AD-400-PL-625004-SHT-001 |  |  | remarks | [12 empty] | REV-1 DRG. SERVER ONLY - 31/08/2026
176 | LOWER ZAKUM LTDP-1 PACKAGE 4 - WHT-ZK-26A LIFTING & INSTALLATION OF J-TUBE BY SAFEEN PEARL | 2820-NN-0176 | AD-401-PL-000001-SHT-001 |  |  | remarks | [12 empty] | REV-1 DRG. SERVER ONLY - 31/08/2026
177 | LOWER ZAKUM LTDP-1 PACKAGE 4 - WHT-ZK-62 LIFTING & INSTALLATION OF J-TUBE BY SAFEEN PEARL | 2820-NN-0177 | AD-169-PL-625002-SHT-001 |  |  | remarks | [12 empty] | REV-1 DRG. SERVER ONLY - 31/08/2026
178 | LOWER ZAKUM LTDP-1 PACKAGE 4 - WHT-ZK-33 LIFTING & INSTALLATION OF J-TUBE BY SAFEEN PEARL | 2820-NN-0178 | AD-403-PL-000001-SHT-001 |  |  | remarks | [12 empty] | REV-1 DRG. SERVER ONLY - 31/08/2026

## Sketch
Project 2820
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2820 | OFO-P2820-SK-T-001 | DLB-1000: CRAWLER CRANE FEASIBILITY CHECK ON DECK | 1 | A | √ | √ | 27-11-2025 | SKS | @
2 | 2820 | OFO-P2820-SK-T-002 | DAVIT LIFT ARRANGEMENT DRAWING FOR 38” WF PIPELINE FROM ZCSC CRP TO AL OMAIRAH ISLAND (PL335) |  |  |  |  | 05-12-2025 | AMITH
3 | 2820 | OFO-P2820-SK-T-003 | Midline Tie-In Davit Lift Arrangement Drawing for 38” WF Pipeline from ZCSC CRP to Al Omairah Island (PL335) | 3 | A | √ | √ | 11-12-2025 | MF | @
4 | 2820 | OFO-P2820-SK-T-004 | START-UP ARRANGEMENT FOR 6"GL P/L FROM AOI-ERP TO ZK-182 AT AOI-ERP WITH DLB-750 | 1 | A | √ | √ | 11-02-2026 | CDG | @
5 | 2820 | OFO-P2820-SK-T-005 | MARKER JOINTS FOR 20’’ PIPELINE (PL317 & PL321) | 1 | A | √ | √ | 25-02-2026 | NAR | @
6 | 2820 | OFO-P2820-SK-T-006 | MARKER JOINTS FOR 14’’ PIPELINE (PL318, PL322, PL302, PL306 & PL310) | 1 | A | √ | √ | 25-02-2026 | NAR | @
7 | 2820 | OFO-P2820-SK-T-007 | MARKER JOINTS FOR 6’’ PIPELINE (PL319, PL323, PL331, PL303, PL307, PL311, PL337 & PL338)) | 1 | A | √ | √ | 25-02-2026 | NAR | @
8 | 2820 | OFO-P2820-SK-T-008 | MARKER JOINTS FOR 18’’ PIPELINE (PL330 & PL326) | 1 | A | √ | √ | 25-02-2026 | NAR | @
9 | 2820 | OFO-P2820-SK-T-009 | MARKER JOINTS FOR 38’’ PIPELINE (PL335) | 1 | A | √ | √ | 25-02-2026 | NAR | @
10 | 2820 | OFO-P2820-SK-T-010 | MARKER JOINTS FOR 22’’ PIPELINE (PL301, PL305 & PL309) | 1 | A | √ | √ | 25-02-2026 | NAR | @
11 | 2820 | OFO-P2820-SK-T-011 | MARKER JOINTS FOR 36’’ PIPELINE (PL325) | 1 | A | √ | √ | 25-02-2026 | NAR | @
12 | 2820 | OFO-P2820-SK-T-012 | MARKER JOINTS FOR 30’’ PIPELINE (PL329) | 1 | A | √ | √ | 25-02-2026 | NAR | @
13 | 2820 | OFO-P2820-SK-T-013 | TRANSITION JOINTS FOR 22’’ PIPELINE (PL301, PL305 & PL309) | 1 | A | √ | √ | 25-02-2026 | NAR | @
14 | 2820 | OFO-P2820-SK-T-014 | TRANSITION JOINTS FOR 6’’ PIPELINE (PL311 & PL331) | 1 | A | √ | √ | 25-02-2026 | NAR | @
15 | 2820 | OFO-P2820-SK-T-015 | TRANSITION JOINTS FOR 20’’ PIPELINE (PL317 & PL321) | 1 | A | √ | √ | 25-02-2026 | NAR | @
16 | 2820 | OFO-P2820-SK-T-016 | TRANSITION JOINTS FOR 18’’ PIPELINE (PL326 & PL330) | 1 | A | √ | √ | 25-02-2026 | NAR | @
17 | 2820 | OFO-P2820-SK-T-017 | TRANSITION JOINTS FOR 30’’ PIPELINE (PL329) | 1 | A | √ | √ | 25-02-2026 | NAR | @
18 | 2820 | OFO-P2820-SK-T-018 | TRANSITION JOINTS FOR 38’’ PIPELINE (PL335) | 1 | A | √ | √ | 25-02-2026 | NAR | @
19 | 2820 | OFO-P2820-SK-T-019 | CABLE PULLING ARRANGEMENT AT AGI ISLAND | 2 | A | √ | √ | 19-02-2026 | CDG | @
20 | 2820 | OFO-P2820-SK-T-020 | START-UP HEAD DETAILS FOR 20'' PIPELINE (PL-317) |  |  |  |  | 24-03-2026 | NAR
21 | 2820 | OFO-P2820-SK-T-021 | TYPICAL LIFTING AND HANDLING ARRANGEMENT FOR 38” PIPE JOINTS BY DLB-750 | 5 | D | √ | √ | 20-07-2026 | JF | @
22 | 2820 | OFO-P2820-SK-T-022 | TYPICAL PIGGYBACK GRAVITY ANCHOR LIFTING ARRANGEMENT WITH DLB-750 | 4 | A | √ | √ | 18-05-2026 | AMK | @
23 | 2820 | OFO-P2820-SK-T-023 | SCAFFOLDING WORKING FRAME AT WHT JACKET (4-LEGS) |  |  |  |  | 18-05-2026 | SRV
24 | 2820 | OFO-P2820-SK-T-024 | SCAFFOLDING WORKING FRAME AT ERP JACKET (8-LEGS) |  |  |  |  | 18-05-2026 | SRV
25 | 2820 | OFO-P2820-SK-T-025 | TYPICAL ABANDONMENT & RECOVERY / LAYDOWN ARRANGEMENT | 1 | A | √ | √ | 08-06-2026 | LEO | @
26 | 2820 | OFO-P2820-SK-T-026 | DLB-750 PIPELAY PROFILE-CAMPAIGN 1 - FOR 6", 14", 18", 20" & 22" PIPELINES | 1 | C | √ | √ | 07-07-2026 | LEO | @
27 | 2820 | OFO-P2820-SK-T-027 | DMA START UP ARRANGEMENT (PL 330) FOR PROPOSED 18" WF P/L FROM WHT-1 IN AGI TO AOI-ERP | 1 | B | √ | √ | 01-07-2026 | LEO | @
28 | 2820 | OFO-P2820-SK-T-028 | Airbag Arrangement Sketch for PL-330 Pipeline | 1 | A | √ | √ | 17-06-2026 | LEO | @
29 | 2820 | OFO-P2820-SK-T-029 | AIR BAG ARRANGEMENTS FOR 20" PL-321 PIPELINE | 1 | A | √ | √ | 14-07-2026 | LEO | @
30 | 2820 | OFO-P2820-SK-T-030 | DMA START-UP ARRANGEMENT FOR PROPOSED 20" WF PIPELINE FROM WHT EA-4 TO AOI ERP (PL 321) | 1 | B | √ | √ | 23-07-2026 | LEO | @
31 | 2820 | OFO-P2820-SK-T-031 | 46"(ID) x 54"(OD) DRILLING ADAPTOR AT ERP |  |  |  |  | 15-07-2026 | LEO
32 | 2820 | OFO-P2820-SK-T-032 | 46"(ID) x 54"(OD) DRILLING ADAPTOR AT WHT EA-2B |  |  |  |  | 15-07-2026 | LEO
33 | 2820 | OFO-P2820-SK-T-033 | 52"(ID) x 58"(OD) DRILLING ADAPTOR AT AGI, WHT EA-6, WHT EA-5 |  |  |  |  | 15-07-2026 | LEO
34 | 2820 | OFO-P2820-SK-T-034 | 52"(ID) x 58"(OD) DRILLING ADAPTOR AT WHT EA-4 |  |  |  |  | 15-07-2026 | LEO
35 | 2820 | OFO-P2820-SK-T-035 | 52"(ID) x 58"(OD) DRILLING ADAPTOR AT WHT EA-1, WHT EA-2A |  |  |  |  | 15-07-2026 | LEO
36 | 2820 | OFO-P2820-SK-T-036 | Typical Details of Protector at Cable Crossing | 1 | C | √ | √ | 03-08-2026 | SKS | @
37 | 2820 | OFO-P2820-SK-T-037 | LOWER ZAKUM LTDP-1 PACKAGE 4 - TYPICAL LIFTING & HANDLING ARRANGEMENT FOR 6" PIPE JOINTS BY DLB-750 | 3 | A | √ | √ | 11-08-2026 | JF | @
38 | 2820 | OFO-P2820-SK-T-038 | TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR PIPELINE PROTECTOR USING DLB750 | 1 | A | √ | √ | 06-08-2026 | CDG | @
39 | 2820 | OFO-P2820-SK-T-039 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DLB-750 | 9 | A | √ | √ | 18-08-2026 | MF | @
40 | 2820 | OFO-P2820-SK-T-040 | TYPICALTRANSITION JOINTS DETAILS | 1 | A | √ | √ | 17-08-2026 | NAR | @
41 | 2820 | OFO-P2820-SK-T-041 | DMA START UP ARRANGEMENT (PL 309) FOR PROPOSED 22" WF P/L FROM WHT-EA-2A TO AOI-ERP | 1 | A | √ | √ | 27-08-2026 | LEO | @
42 | 2820 | OFO-P2820-SK-T-042 | AIR BAG ARRANGEMENTS FOR PL-317 20” PIPELINE | 3 | A | √ | √ | 03-09-2026 | JF | @
43 | 2820 | OFO-P2820-SK-T-043 | DMA START UP ARRANGEMENT FOR PROPOSED 20" WF P/L FROM WHT-EA-6 TO WHT-EA-4 (PL317) | 1 | A | √ | √ | 04-09-2026 | LEO | @

## Cutlist
Project 2035-ADNOC
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2820 | 2820-NN-0001-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 20" PIPELINE FROM WHT EA-6 TO WHT EA-4 (PL-317) | 1 + 11 | 0 | √ | √ | 16-06-2026 | SATISH | @
2 | 2820 | 2820-NN-0004-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 22" PIPELINE FROM WHT EA-1 TO WHT EA-5 (PL-301) | 1 + 11 | 0 | √ | √ | 16-06-2026 | SATISH | @
3 | 2820 | 2820-NN-0005-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 18" PIPELINE FROM WHT-1 AGI TO ERP (PL-330) | 1 + 12 | 0 | √ | √ | 16-06-2026 | SATISH | @
4 | 2820 | 2820-NN-0009-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 20" PIPELINE FROM WHT EA-6 TO WHT EA-4 (PL-317) | 1 + 11 | 0 | √ | √ | 16-06-2026 | SATISH | @
5 | 2820 | 2820-NN-0012-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 22" PIPELINE FROM WHT EA-1 TO WHT EA-5 (PL-301) | 1 + 11 | 0 | √ | √ | 16-06-2026 | SATISH | @
6 | 2820 | 2820-NN-0013-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 18" PIPELINE FROM WHT-1 AGI TO ERP (PL-330) | 1 + 12 | 0 | √ | √ | 16-06-2026 | SATISH | @
7 | 2820 | 2820-NN-0017-CTL | LOWER ZAKUM LTDP- PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 20" PIPELINE FROM WHT EA-6 TO WHT EA-4 (PL-317) | 1 + 11 | 0 | √ | √ | 16-06-2026 | SATISH | @
8 | 2820 | 2820-NN-0020-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 22" PIPELINE FROM WHT EA-1 TO WHT EA-5 (PL-301) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
9 | 2820 | 2820-NN-0021-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 18" PIPELINE FROM WHT-1 AGI TO ERP (PL-330) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
10 | 2820 | 2820-NN-0118-CTL | LOWER ZAKUM LTDP- PACKAGE 4 - START-UP HEAD DETAILS FOR 20'' PIPELINE FROM WHT EA-4 TO ERP (PL-321) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
11 | 2820 | 2820-NN-0119-CTL | LOWER ZAKUM LTDP- PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 20'' PIPELINE FROM WHT EA-4 TO ERP (PL-321) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
12 | 2820 | 2820-NN-0120-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - START UP HEAD DETAILS FOR 18" PIPELINE FROM ERP TO ZWSC RP2 (PL-326) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
13 | 2820 | 2820-NN-0121-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 18'' PIPELINE FROM ERP TO ZWSC RP2 (PL-326) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
14 | 2820 | 2820-NN-0122-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - EMERGENCY LAYDOWN HEAD DETAILS FOR 18'' PIPELINE FROM ERP TO ZWSC RP2 (PL-326) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
15 | 2820 | 2820-NN-0123-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - START-UP HEAD DETAILS FOR 22'' PIPELINE FROM WHT EA-5 TO WHT EA-2B (PL-305) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
16 | 2820 | 2820-NN-0124-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 22'' PIPELINE FROM WHT EA-5 TO WHT EA-2B (PL-305) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
17 | 2820 | 2820-NN-0125-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - START-UP HEAD DETAILS FOR 22'' PIPELINE FROM WHT EA-2A TO ERP (PL-309) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
18 | 2820 | 2820-NN-0126-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - LAYDOWN HEAD DETAILS FOR 22'' PIPELINE FROM WHT EA-2A TO ERP (PL-309) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
19 | 2820 | 2820-NN-0155-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 – EMERGENCY LAYDOWN HEAD DETAILS FOR 22'' PIPELINE FROM WHT EA-5 TO WHT EA-2B (PL-305) |  | 0 | √ | √ | 16-06-2026 | SATISH | @
20 | 2820 | 2820-NN-0156-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 18" PIPELINE HEAD 140MM CONCRETE (PL-330)-CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
21 | 2820 | 2820-NN-0157-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 18" PIPELINE HEAD 80MM CONCRETE (PL-330) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
22 | 2820 | 2820-NN-0158-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 20" PIPELINE HEAD 125MM CONCRETE (PL-317) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
23 | 2820 | 2820-NN-0159-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 20" PIPELINE HEAD 60MM CONCRETE (PL-321) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
24 | 2820 | 2820-NN-0160-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 20" PIPELINE HEAD 80MM CONCRETE (PL-321) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
25 | 2820 | 2820-NN-0161-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 22" PIPELINE HEAD 170MM CONCRETE (PL-301) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
26 | 2820 | 2820-NN-0162-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 22" PIPELINE HEAD 150MM CONCRETE (PL-301) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
27 | 2820 | 2820-NN-0163-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 22" PIPELINE HEAD 200MM CONCRETE (PL-305) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
28 | 2820 | 2820-NN-0164-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 22" PIPELINE HEAD 200MM CONCRETE (PL-309) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
29 | 2820 | 2820-NN-0165-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 22" PIPELINE HEAD 100MM CONCRETE (PL-309) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
30 | 2820 | 2820-NN-0166-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 38" PIPELINE HEAD 170MM CONCRETE (PL-335) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
31 | 2820 | 2820-NN-0167-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 38" PIPELINE HEAD 100MM CONCRETE (PL-335) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.
32 | 2820 | 2820-NN-0168-CTL | LOWER ZAKUM LTDP-1 PACKAGE 4 - FLANGE PROTECTOR DETAILS FOR 38" PIPELINE HEAD 180MM CONCRETE (PL-335) -CUTLIST |  | 0 | √ | √ | 03-07-2026 | SATISH | @ | SUBMITTED TO FAB.

## TN-PL
|  | ADNOC OFFSHORE | [11 empty] | NMDC ENERGY DOC. No.:
ADNOC LZ LTDP-1 PROJECT
|  | NMDC ENERGY PROJECT NO. 2820 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (TECHNICAL NOTE) | [11 empty] | DATE : |  |  |  | 2025-11-10
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | LOWER ZAKUM LTDP-1 PACKAGE-4 - TEHCNICAL NOTE FOR MIDLINE TIE-IN OF PL-325 | 2820-TN-PL-001 | AM - 16-07-2026