## Documents - Pipeline & Cable
|  | ADNOC OFFSHORE | [11 empty] | NMDC ENERGY DOC. No.:
ADNOC LZ LTDP-1 PROJECT
|  | NMDC ENERGY PROJECT NO. 2820 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2025-11-10
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | DESIGN BASIS FOR INSTALLATION ENGINEERING ANALYSIS | 2820-NN-RP-001
| PIPE STACKING ANALYSIS REPORT | 2820-NN-RP-002
2 | PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-301) FROM FROM WHT EA-1 to WHT EA-5 | 2820-NN-RP-003
3 | PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-302) FROM FROM WHT EA-5 to WHT EA-1 | 2820-NN-RP-004
4 | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-303) FROM WHT EA-5 to WHT EA-1 | 2820-NN-RP-005
5 | PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-305) FROM WHT EA-5 to WHT EA-2B | 2820-NN-RP-006
6 | PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-306) FROM WHT EA-2B to WHT EA-5 | 2820-NN-RP-007
7 | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-307) FROM WHT EA-2A to WHT EA-5 | 2820-NN-RP-008
8 | PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-309) FROM WHT EA-2A to ERP G-Island | 2820-NN-RP-009
| PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-310) FROM ERP G-Island to WHT EA-2A | 2820-NN-RP-010
| PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-311) FROM ERP G-Island to WHT EA-2A | 2820-NN-RP-011
| PIPELAY ANALYSIS REPORT FOR 22" WF P/L (PL-317) FROM WHT EA-6 to WHT EA-4 | 2820-NN-RP-012
| PIPELAY ANALYSIS REPORT FOR 18" WI P/L (PL-318) FROM WHT EA-4 to WHT EA-6 | 2820-NN-RP-013
| PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-319) FROM WHT EA-4 to WHT EA-6 | 2820-NN-RP-014
| PIPELAY ANALYSIS REPORT FOR 22" WF P/L (PL-321) FROM WHT EA-4 to ERP G-Island | 2820-NN-RP-015
| PIPELAY ANALYSIS REPORT FOR 18" WI P/L (PL-322) FROM ERP G-Island to WHT EA-4 | 2820-NN-RP-016
| PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-323) FROM ERP G-Island to WHT EA-4 | 2820-NN-RP-017
| PIPELAY ANALYSIS REPORT FOR 30" WG P/L (PL-325) FROM ERP G-Island to ZWSC-RP2 | 2820-NN-RP-018
| PIPELAY ANALYSIS REPORT FOR 20" GE P/L (PL-326) FROM ERP G-Island to ZWSC-RP2 | 2820-NN-RP-019
| PIPELAY ANALYSIS REPORT FOR 30" OE P/L (PL-329) FROM ERP G-Island to ZWSC-NRP | 2820-NN-RP-020
| PIPELAY ANALYSIS REPORT FOR 14" WF P/L (PL-330) FROM WHT-1 AGI Area to ERP G-Island | 2820-NN-RP-021
| PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-331) FROM ERP G-Island to WHT-1 AGI Area | 2820-NN-RP-022
| PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-334) FROM WHT ZK-182 to ERP G-Island | 2820-NN-RP-023
| PIPELAY ANALYSIS REPORT FOR 38" WF P/L (PL-335) FROM ZCSC-CRP to ERP G-Island | 2820-NN-RP-024
| PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-337) FROM WHT in AGI Area to EPS-2 WHT-2 | 2820-NN-RP-025
| PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-338) FROM EPS-2 WHT-2 to EPS-2 WHT-3 | 2820-NN-RP-026
| DAVIT LIFT ANALYSIS REPORT FOR 20" WF P/L (PL-301) WHT EA-1 to WHT EA-5 | 2820-NN-RP-027
| DAVIT LIFT ANALYSIS REPORT FOR 16" WI P/L (PL-302) WHT EA-5 to WHT EA-1 | 2820-NN-RP-028
| DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-303) WHT EA-5 to WHT EA-1 | 2820-NN-RP-029
| DAVIT LIFT ANALYSIS REPORT FOR 20" WF P/L (PL-305) WHT EA-5 to WHT EA-2B | 2820-NN-RP-030
| DAVIT LIFT ANALYSIS REPORT FOR 16" WI P/L (PL-306) WHT EA-2B to WHT EA-5 | 2820-NN-RP-031
| DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-307) WHT EA-2A to WHT EA-5 | 2820-NN-RP-032
| DAVIT LIFT ANALYSIS REPORT FOR 20" WF P/L (PL-309) WHT EA-2A to ERP G-Island | 2820-NN-RP-033
| DAVIT LIFT ANALYSIS REPORT FOR 16" WI P/L (PL-310) ERP G-Island to WHT EA-2A | 2820-NN-RP-034
| DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-311) ERP G-Island to WHT EA-2A | 2820-NN-RP-035
| DAVIT LIFT ANALYSIS REPORT FOR 22" WF P/L (PL-317) WHT EA-6 to WHT EA-4 | 2820-NN-RP-036
| DAVIT LIFT ANALYSIS REPORT FOR 18" WI P/L (PL-318) WHT EA-4 to WHT EA-6 | 2820-NN-RP-037
| DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-319) WHT EA-4 to WHT EA-6 | 2820-NN-RP-038
| DAVIT LIFT ANALYSIS REPORT FOR 22" WF P/L (PL-321) WHT EA-4 to ERP G-Island | 2820-NN-RP-039
| DAVIT LIFT ANALYSIS REPORT FOR 18" WI P/L (PL-322) ERP G-Island to WHT EA-4 | 2820-NN-RP-040
| DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-323) ERP G-Island to WHT EA-4 | 2820-NN-RP-041
| DAVIT LIFT ANALYSIS REPORT FOR 30" WG P/L (PL-325) ERP G-Island to ZWSC-RP2 | 2820-NN-RP-042
| DAVIT LIFT ANALYSIS REPORT FOR 20" GE P/L (PL-326) ERP G-Island to ZWSC-RP2 | 2820-NN-RP-043
| DAVIT LIFT ANALYSIS REPORT FOR 30" OE P/L (PL-329) ERP G-Island to ZWSC-NRP | 2820-NN-RP-044
| DAVIT LIFT ANALYSIS REPORT FOR 14" WF P/L (PL-330) WHT-1 AGI Area to ERP G-Island | 2820-NN-RP-045
| DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-331) ERP G-Island to WHT-1 AGI Area | 2820-NN-RP-046
| DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-334) WHT ZK-182 to ERP G-Island | 2820-NN-RP-047
| DAVIT LIFT ANALYSIS REPORT FOR 38" WF P/L (PL-335) ZCSC-CRP to ERP G-Island | 2820-NN-RP-048
| DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-337) WHT in AGI Area to EPS-2 WHT-2 | 2820-NN-RP-049
| DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-338) EPS-2 WHT-2 to EPS-2 WHT-3 | 2820-NN-RP-050
| INSTALLATION ANALYSIS REPORT FOR 132KV CABLES | 2820-NN-RP-051
| INSTALLATION ANALYSIS REPORT FOR 6.6KV CABLES | 2820-NN-RP-052
9 | SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-1)
10 | SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-2)
11 | SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-3)
12 | SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-4)
13 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AT PRESTIGE-281 (TRIP-1)
14 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON PRESTIGE-282 (TRIP 2)
15 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 3
16 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 4
17 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 5
18 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 6
19 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 7
20 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 1
21 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 2
22 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 3
23 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 4
24 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 5
25 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 6
26 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 7

## Documents - Naval Marine
|  | ADNOC OFFSHORE | [11 empty] | NMDC ENERGY DOC. No.:
ADNOC LZ LTDP-1 PROJECT
|  | NMDC ENERGY PROJECT NO. 2820 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (NAVAL MARINE) | [11 empty] | DATE : |  |  |  | 2025-11-10
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-1 | 2745-ZZ-CL-001
2 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-2
3 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-3
4 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-4
5 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-5
6 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-6
7 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-7
8 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-8
9 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 16" WI
10 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 16" OIL
11 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 18"
12 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 20"
13 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 24"
14 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS, J-TUBES AND RISERS - TRIP-1
15 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS, J-TUBES AND RISERS - TRIP-2
16 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS, J-TUBES AND RISERS - TRIP-3
17 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF SUBSEA SPOOLS, J-TUBES AND RISERS - TRIP-4
18 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LAYING OF 16" WI
19 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LAYING OF 16" OIL
20 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES PRESTIGE-281 (TRIP-1)
21 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES - TRIP-2
22 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES - TRIP-3
23 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES - TRIP-4
24 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES - TRIP-5
25 | LOWER ZAKUM – LTDP-1 STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS & MATTRESSES - TRIP-6
26 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LAYING OF 18"
27 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LAYING OF 20"
28 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING LAYING OF 24"
29 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING ZCSC PDP JACKET INSTALLATION
30 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST JACKET INSTALLATION -1
31 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST JACKET INSTALLATION -2
32 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING ZWSC BST INSTALLATION
33 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING ZCSC BST INSTALLATION
34 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING GPF-II BST INSTALLATION
35 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING FLARE BST-3 INSTALLATION
36 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING FLARE BST-4 INSTALLATION
37 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING FLARE BST-5 INSTALLATION
38 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS OF B-42 DURING FLOATOVER OF GPF-II
39 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST DECK INSTALLATION -1
40 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST DECK INSTALLATION -2
41 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST DECK INSTALLATION -3
42 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST DECK INSTALLATION -4
43 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST DECK INSTALLATION -5
44 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST BRIDGE INSTALLATION -1
45 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST BRIDGE INSTALLATION -2
46 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST BRIDGE INSTALLATION -3
47 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST BRIDGE INSTALLATION -4
48 | LOWER ZAKUM – LTDP-1 MOORING ANALYSIS DURING BST BRIDGE INSTALLATION -5

## Drawings
|  | ADNOC OFFSHORE | [11 empty] | NMDC ENERGY DOC. No.:
ADNOC LZ LTDP-1 PROJECT
|  | NMDC ENERGY PROJECT NO. 2820 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (DRAWINGS) | [11 empty] | DATE : |  |  |  | 2025-11-10
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | START UP HEAD DETAILS FOR 20" PIPELINE | 2820-NN-0001
2 | START UP HEAD DETAILS FOR 16" PIPELINE | 2820-NN-0002
3 | START UP HEAD DETAILS FOR 6" PIPELINE | 2820-NN-0003
4 | START UP HEAD DETAILS FOR 22" PIPELINE | 2820-NN-0004
5 | START UP HEAD DETAILS FOR 18" PIPELINE | 2820-NN-0005
6 | START UP HEAD DETAILS FOR 30" PIPELINE | 2820-NN-0006
7 | START UP HEAD DETAILS FOR 14" PIPELINE | 2820-NN-0007
8 | START UP HEAD DETAILS FOR 38" PIPELINE | 2820-NN-0008
9 | LAYDOWN HEAD DETAILS FOR 20" PIPELINE | 2820-NN-0009
10 | LAYDOWN HEAD DETAILS FOR 16" PIPELINE | 2820-NN-0010
11 | LAYDOWN HEAD DETAILS FOR 6" PIPELINE | 2820-NN-0011
12 | LAYDOWN HEAD DETAILS FOR 22" PIPELINE | 2820-NN-0012
13 | LAYDOWN HEAD DETAILS FOR 18" PIPELINE | 2820-NN-0013
14 | LAYDOWN HEAD DETAILS FOR 30" PIPELINE | 2820-NN-0014
15 | LAYDOWN HEAD DETAILS FOR 14" PIPELINE | 2820-NN-0015
16 | LAYDOWN HEAD DETAILS FOR 38" PIPELINE | 2820-NN-0016
17 | EMERGENCY LAYDOWN HEAD DETAILS FOR 20" PIPELINE | 2820-NN-0017
18 | EMERGENCY LAYDOWN HEAD DETAILS FOR 16" PIPELINE | 2820-NN-0018
19 | EMERGENCY LAYDOWN HEAD DETAILS FOR 6" PIPELINE | 2820-NN-0019
20 | EMERGENCY LAYDOWN HEAD DETAILS FOR 22" PIPELINE | 2820-NN-0020
21 | EMERGENCY LAYDOWN HEAD DETAILS FOR 18" PIPELINE | 2820-NN-0021
22 | EMERGENCY LAYDOWN HEAD DETAILS FOR 30" PIPELINE | 2820-NN-0022
23 | EMERGENCY LAYDOWN HEAD DETAILS FOR 14" PIPELINE | 2820-NN-0023
24 | EMERGENCY LAYDOWN HEAD DETAILS FOR 38" PIPELINE | 2820-NN-0024
25 | BUCKLE DETECTOR FOR 20" PIPELINE | 2820-NN-0025
26 | BUCKLE DETECTOR FOR 16" PIPELINE | 2820-NN-0026
27 | BUCKLE DETECTOR FOR 6" PIPELINE | 2820-NN-0027
28 | BUCKLE DETECTOR FOR 22" PIPELINE | 2820-NN-0028
29 | BUCKLE DETECTOR FOR 18" PIPELINE | 2820-NN-0029
30 | BUCKLE DETECTOR FOR 30" PIPELINE | 2820-NN-0030
31 | BUCKLE DETECTOR FOR 14" PIPELINE | 2820-NN-0031
32 | BUCKLE DETECTOR FOR 38" PIPELINE | 2820-NN-0032
33 | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 20" PIPELINE | 2820-NN-0033
34 | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 16" PIPELINE | 2820-NN-0034
35 | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 6" PIPELINE | 2820-NN-0035
36 | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 22" PIPELINE | 2820-NN-0036
37 | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 18" PIPELINE | 2820-NN-0037
38 | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 30" PIPELINE | 2820-NN-0038
39 | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 14" PIPELINE | 2820-NN-0039
40 | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 38" PIPELINE | 2820-NN-0040
21 | LOWER ZAKUM - WHT-ZK-11 LIFTING & INSTALLATION OF J-TUBE BY MP-01 (SHT. 1 TO 3) | 2820-NN-0041
22 | LOWER ZAKUM - WHT-ZK-235 LIFTING & INSTALLATION OF J-TUBE BY MP-01 (SHT. 1 TO 5) | 2820-NN-0042
23 | LOWER ZAKUM - WHT-ZK-235 LIFTING & INSTALLATION OF J-TUBE CLAMPS BY MP-01 (SHT. 1 TO 3) | 2820-NN-0043
24 | LOWER ZAKUM - WHT-ZK-11 LIFTING & INSTALLATION OF J-TUBE CLAMPS BY MP-01 (SHT. 1 TO 3) | 2820-NN-0044
25 | LOWER ZAKUM – LTDP-1 LIFTING & INSTALLATION OF J-TUBE #3 | 2820-NN-0045
26 | LOWER ZAKUM – LTDP-1 LIFTING & INSTALLATION OF J-TUBE CLAMPS #3 | 2820-NN-0046
27 | LOWER ZAKUM – LTDP-1 LIFTING & INSTALLATION OF RISER CLAMPS #1 | 2820-NN-0047
28 | LIFTING & INSTALLATION OF RISER CLAMPS #2 | 2820-NN-0048
29 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS AT PL335 (CR02) BY USING MP-02 | 2820-NN-0049 | AMK-20/01/26
30 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS AT PL335 (CR02) BY USING DLB-750 | 2820-NN-0050 | REY-20/01/26
31 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING OF CONCRETE MATTRESS | 2820-NN-0051
32 | LOWER ZAKUM – LTDP-1 RISER/SPOOL LIFTING FOR 16" PL | 2820-NN-0052
33 | LOWER ZAKUM – LTDP-1 RISER/SPOOL LIFTING FOR 18" PL | 2820-NN-0053
34 | LOWER ZAKUM – LTDP-1 RISER/SPOOL LIFTING FOR 20" PL | 2820-NN-0054
35 | LOWER ZAKUM – LTDP-1 RISER/SPOOL LIFTING FOR 24" PL | 2820-NN-0055
36 | LOWER ZAKUM – LTDP-1 TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 16" | 2820-NN-0056
37 | LOWER ZAKUM – LTDP-1 TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 18" | 2820-NN-0057
38 | LOWER ZAKUM – LTDP-1 TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 20" | 2820-NN-0058
39 | LOWER ZAKUM – LTDP-1 TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 24" | 2820-NN-0059
40 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-1) | 2820-NN-0060
41 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-2) | 2820-NN-0061
42 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-3) | 2820-NN-0062
43 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-4) | 2820-NN-0063
44 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-5) | 2820-NN-0064
45 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-6) | 2820-NN-0065
46 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-7) | 2820-NN-0066
47 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-1) | 2820-NN-0067
48 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON PRESTIGE-282 CB (TRIP-2) | 2820-NN-0068
49 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON PRESTIGE-281 CB (TRIP-3) | 2820-NN-0069
50 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-4) | 2820-NN-0070
51 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-5) | 2820-NN-0071
52 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-6) | 2820-NN-0072
53 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-1) | 2820-NN-0073
54 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-2) | 2820-NN-0074
55 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-3) | 2820-NN-0075
56 | LOWER ZAKUM – LTDP-1 ANODE DEMOLITION AND OFFLODING ARRANGEMENT AT ZK-235 | 2820-NN-0076
57 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR CONCRETE SLEEPERS (USING MP-02) | 2820-NN-0077
58 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION ARRANGEMENT FOR MATTRESSES USING MP-02 | 2820-NN-0078
59 | LOWER ZAKUM – LTDP-1 LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CONCRETE SLEEPERS ON PRESTIGE-281 CB | 2820-NN-0079
60 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION OF CONCRETE MATTRESS (USING MP-01) | 2820-NN-0080
61 | LOWER ZAKUM – LTDP-1 TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS (USING MP-01) | 2820-NN-0081
62 | LOWER ZAKUM – LTDP-1 LOADING ARRANGMENT & SEAFASTENING DETAILS OF SUBSEA SPOOLS, JTUBES & RISERS (TRIP-4) | 2820-NN-0082
63 | LOWER ZAKUM - WHT-ZK-288 LIFTING & INSTALLATION OF J-TUBE BY MP-01 (SHT. 1 TO 5) | 2820-NN-0083
64 | LOWER ZAKUM - WHT-ZK-288 LIFTING & INSTALLATION OF J-TUBE CLAMPS BY MP-01 (SHT. 1 TO 3) | 2820-NN-0084
65 | TYPICAL LIFTING AND INSTALLATION OF SANDBAGS USING MP-01 | 2820-NN-0085
66 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS AT PL335 (CR06 TO CR16) BY USING MP-02 | 2820-NN-0086 | AMK-29/01/26

## Sketch
Project 2820
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2820 | OFO-P2820-SK-T-001 | DLB-1000: CRAWLER CRANE FEASIBILITY CHECK ON DECK | 1 | A | √ | √ | 27-11-2025 | SKS | @
2 | 2820 | OFO-P2820-SK-T-002 | DAVIT LIFT ARRANGEMENT DRAWING FOR 38” WF PIPELINE FROM ZCSC CRP TO AL OMAIRAH ISLAND (PL335) |  |  |  |  | 05-12-2025 | AMITH
3 | 2820 | OFO-P2820-SK-T-003 | Midline Tie-In Davit Lift Arrangement Drawing for 38” WF Pipeline from ZCSC CRP to Al Omairah Island (PL335) | 3 | A | √ | √ | 11-12-2025 | MF | @
4 | 2820 | OFO-P2820-SK-T-004 | START-UP ARRANGEMENT FOR 6"GL P/L FROM AOI-ERP TO ZK-182 AT AOI-ERP WITH DLB-750 | 1 | A | √ | √ | 11-02-2026 | CDG | @
5 | 2820 | OFO-P2820-SK-T-005 | MARKER JOINTS FOR 20’’ PIPELINE (PL317 & PL321) |  |  |  |  | 25-02-2026 | NAR
6 | 2820 | OFO-P2820-SK-T-006 | MARKER JOINTS FOR 14’’ PIPELINE (PL318, PL322, PL302, PL306 & PL310) |  |  |  |  | 25-02-2026 | NAR
7 | 2820 | OFO-P2820-SK-T-007 | MARKER JOINTS FOR 6’’ PIPELINE (PL319, PL323, PL331, PL303, PL307, PL311, PL337 & PL338)) |  |  |  |  | 25-02-2026 | NAR
8 | 2820 | OFO-P2820-SK-T-008 | MARKER JOINTS FOR 18’’ PIPELINE (PL330 & PL326) |  |  |  |  | 25-02-2026 | NAR
9 | 2820 | OFO-P2820-SK-T-009 | MARKER JOINTS FOR 38’’ PIPELINE (PL335) |  |  |  |  | 25-02-2026 | NAR
10 | 2820 | OFO-P2820-SK-T-010 | MARKER JOINTS FOR 22’’ PIPELINE (PL301, PL305 & PL309) |  |  |  |  | 25-02-2026 | NAR
11 | 2820 | OFO-P2820-SK-T-011 | MARKER JOINTS FOR 36’’ PIPELINE (PL325) |  |  |  |  | 25-02-2026 | NAR
12 | 2820 | OFO-P2820-SK-T-012 | MARKER JOINTS FOR 30’’ PIPELINE (PL329) |  |  |  |  | 25-02-2026 | NAR
13 | 2820 | OFO-P2820-SK-T-013 | TRANSITION JOINTS FOR 22’’ PIPELINE (PL301, PL305 & PL309) |  |  |  |  | 25-02-2026 | NAR
14 | 2820 | OFO-P2820-SK-T-014 | TRANSITION JOINTS FOR 6’’ PIPELINE (PL311 & PL331) |  |  |  |  | 25-02-2026 | NAR
15 | 2820 | OFO-P2820-SK-T-015 | TRANSITION JOINTS FOR 20’’ PIPELINE (PL317 & PL321) |  |  |  |  | 25-02-2026 | NAR
16 | 2820 | OFO-P2820-SK-T-016 | TRANSITION JOINTS FOR 18’’ PIPELINE (PL326 & PL330) |  |  |  |  | 25-02-2026 | NAR
17 | 2820 | OFO-P2820-SK-T-017 | TRANSITION JOINTS FOR 30’’ PIPELINE (PL329) |  |  |  |  | 25-02-2026 | NAR
18 | 2820 | OFO-P2820-SK-T-018 | TRANSITION JOINTS FOR 38’’ PIPELINE (PL335) |  |  |  |  | 25-02-2026 | NAR
19 | 2820 | OFO-P2820-SK-T-019 | CABLE PULLING ARRANGEMENT AT AGI ISLAND | 2 | A | √ | √ | 19-02-2026 | CDG | @
20 | 2820

## Cut-lists
Project 2820
CUT-LIST DRAWINGS
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location

## TN-PL
|  | ADNOC OFFSHORE | [11 empty] | NMDC ENERGY DOC. No.:
ADNOC LZ LTDP-1 PROJECT
|  | NMDC ENERGY PROJECT NO. 2820 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE TECHNICAL NOTES) | [11 empty] | DATE : |  |  |  | 2025-11-10
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 |  | 2820-TN-PL-001
2820-TN-PL-002
2 |  | 2820-TN-PL-003
3 |  | 2820-TN-PL-004
4 |  | 2820-TN-PL-005
5 |  | 2820-TN-PL-006
6 |  | 2820-TN-PL-007
7 |  | 2820-TN-PL-008
8 |  | 2820-TN-PL-009
9 |  | 2820-TN-PL-010
10 |  | 2820-TN-PL-011
11 |  | 2820-TN-PL-012
12 |  | 2820-TN-PL-013
13 |  | 2820-TN-PL-014
2820-TN-PL-015
2820-TN-PL-016
2820-TN-PL-017
2820-TN-PL-018
2820-TN-PL-019
2820-TN-PL-020
2820-TN-PL-021
2820-TN-PL-022
2820-TN-PL-023
2820-TN-PL-024
2820-TN-PL-025
2820-TN-PL-026
2820-TN-PL-027
2820-TN-PL-028
2820-TN-PL-029
2820-TN-PL-030
2820-TN-PL-031
2820-TN-PL-032
2820-TN-PL-033
2820-TN-PL-034
2820-TN-PL-035
2820-TN-PL-036
2820-TN-PL-037
2820-TN-PL-038
2820-TN-PL-039
2820-TN-PL-040
2820-TN-PL-041
2820-TN-PL-042
2820-TN-PL-043
2820-TN-PL-044
2820-TN-PL-045
2820-TN-PL-046
2820-TN-PL-047
2820-TN-PL-048
2820-TN-PL-049
2820-TN-PL-050
2820-TN-PL-051
2820-TN-PL-052
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26

## to be deleted
| 1 | 20 | WF P/L (PL-301) WHT EA-1 to WHT EA-5 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-301) WHT EA-1 to WHT EA-5 | DAVIT LIFT ANALYSIS REPORT FOR 20" WF P/L (PL-301) WHT EA-1 to WHT EA-5
| 2 | 16 | WI P/L (PL-302) WHT EA-5 to WHT EA-1 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-302) WHT EA-5 to WHT EA-1 | DAVIT LIFT ANALYSIS REPORT FOR 16" WI P/L (PL-302) WHT EA-5 to WHT EA-1
| 3 | 6 | GL P/L (PL-303) WHT EA-5 to WHT EA-1 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-303) WHT EA-5 to WHT EA-1 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-303) WHT EA-5 to WHT EA-1
| 4 | 20 | WF P/L (PL-305) WHT EA-5 to WHT EA-2B |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-305) WHT EA-5 to WHT EA-2B | DAVIT LIFT ANALYSIS REPORT FOR 20" WF P/L (PL-305) WHT EA-5 to WHT EA-2B
| 5 | 16 | WI P/L (PL-306) WHT EA-2B to WHT EA-5 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-306) WHT EA-2B to WHT EA-5 | DAVIT LIFT ANALYSIS REPORT FOR 16" WI P/L (PL-306) WHT EA-2B to WHT EA-5
| 6 | 6 | GL P/L (PL-307) WHT EA-2A to WHT EA-5 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-307) WHT EA-2A to WHT EA-5 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-307) WHT EA-2A to WHT EA-5
| 7 | 20 | WF P/L (PL-309) WHT EA-2A to ERP G-Island |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-309) WHT EA-2A to ERP G-Island | DAVIT LIFT ANALYSIS REPORT FOR 20" WF P/L (PL-309) WHT EA-2A to ERP G-Island
| 8 | 16 | WI P/L (PL-310) ERP G-Island to WHT EA-2A |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-310) ERP G-Island to WHT EA-2A | DAVIT LIFT ANALYSIS REPORT FOR 16" WI P/L (PL-310) ERP G-Island to WHT EA-2A
| 9 | 6 | GL P/L (PL-311) ERP G-Island to WHT EA-2A |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-311) ERP G-Island to WHT EA-2A | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-311) ERP G-Island to WHT EA-2A
| 10 | 22 | WF P/L (PL-317) WHT EA-6 to WHT EA-4 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 22" WF P/L (PL-317) WHT EA-6 to WHT EA-4 | DAVIT LIFT ANALYSIS REPORT FOR 22" WF P/L (PL-317) WHT EA-6 to WHT EA-4
| 11 | 18 | WI P/L (PL-318) WHT EA-4 to WHT EA-6 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 18" WI P/L (PL-318) WHT EA-4 to WHT EA-6 | DAVIT LIFT ANALYSIS REPORT FOR 18" WI P/L (PL-318) WHT EA-4 to WHT EA-6
| 12 | 6 | GL P/L (PL-319) WHT EA-4 to WHT EA-6 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-319) WHT EA-4 to WHT EA-6 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-319) WHT EA-4 to WHT EA-6
| 13 | 22 | WF P/L (PL-321) WHT EA-4 to ERP G-Island |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 22" WF P/L (PL-321) WHT EA-4 to ERP G-Island | DAVIT LIFT ANALYSIS REPORT FOR 22" WF P/L (PL-321) WHT EA-4 to ERP G-Island
| 14 | 18 | WI P/L (PL-322) ERP G-Island to WHT EA-4 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 18" WI P/L (PL-322) ERP G-Island to WHT EA-4 | DAVIT LIFT ANALYSIS REPORT FOR 18" WI P/L (PL-322) ERP G-Island to WHT EA-4
| 15 | 6 | GL P/L (PL-323) ERP G-Island to WHT EA-4 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-323) ERP G-Island to WHT EA-4 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-323) ERP G-Island to WHT EA-4
| 16 | 30 | WG P/L (PL-325) ERP G-Island to ZWSC-RP2 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 30" WG P/L (PL-325) ERP G-Island to ZWSC-RP2 | DAVIT LIFT ANALYSIS REPORT FOR 30" WG P/L (PL-325) ERP G-Island to ZWSC-RP2
| 17 | 20 | GE P/L (PL-326) ERP G-Island to ZWSC-RP2 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 20" GE P/L (PL-326) ERP G-Island to ZWSC-RP2 | DAVIT LIFT ANALYSIS REPORT FOR 20" GE P/L (PL-326) ERP G-Island to ZWSC-RP2
| 18 | 30 | OE P/L (PL-329) ERP G-Island to ZWSC-NRP |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 30" OE P/L (PL-329) ERP G-Island to ZWSC-NRP | DAVIT LIFT ANALYSIS REPORT FOR 30" OE P/L (PL-329) ERP G-Island to ZWSC-NRP
| 19 | 14 | WF P/L (PL-330) WHT-1 AGI Area to ERP G-Island |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 14" WF P/L (PL-330) WHT-1 AGI Area to ERP G-Island | DAVIT LIFT ANALYSIS REPORT FOR 14" WF P/L (PL-330) WHT-1 AGI Area to ERP G-Island
| 20 | 6 | GL P/L (PL-331) ERP G-Island to WHT-1 AGI Area |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-331) ERP G-Island to WHT-1 AGI Area | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-331) ERP G-Island to WHT-1 AGI Area
| 21 | 6 | GL P/L (PL-334) WHT ZK-182 to ERP G-Island |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-334) WHT ZK-182 to ERP G-Island | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-334) WHT ZK-182 to ERP G-Island
| 22 | 38 | WF P/L (PL-335) ZCSC-CRP to ERP G-Island |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 38" WF P/L (PL-335) ZCSC-CRP to ERP G-Island | DAVIT LIFT ANALYSIS REPORT FOR 38" WF P/L (PL-335) ZCSC-CRP to ERP G-Island
| 23 | 6 | GL P/L (PL-337) WHT in AGI Area to EPS-2 WHT-2 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-337) WHT in AGI Area to EPS-2 WHT-2 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-337) WHT in AGI Area to EPS-2 WHT-2
| 24 | 6 | GL P/L (PL-338) EPS-2 WHT-2 to EPS-2 WHT-3 |  | PIPELAY ANALYSIS REPORT FOR | DAVIT LIFT ANALYSIS REPORT FOR |  | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-338) EPS-2 WHT-2 to EPS-2 WHT-3 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L (PL-338) EPS-2 WHT-2 to EPS-2 WHT-3
20 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-301) FROM FROM WHT EA-1 to WHT EA-5
16 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-302) FROM FROM WHT EA-5 to WHT EA-1
6 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-303) FROM WHT EA-5 to WHT EA-1
20 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-305) FROM WHT EA-5 to WHT EA-2B
16 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-306) FROM WHT EA-2B to WHT EA-5
6 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-307) FROM WHT EA-2A to WHT EA-5
20 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 20" WF P/L (PL-309) FROM WHT EA-2A to ERP G-Island
16 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 16" WI P/L (PL-310) FROM ERP G-Island to WHT EA-2A
6 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-311) FROM ERP G-Island to WHT EA-2A
22 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 22" WF P/L (PL-317) FROM WHT EA-6 to WHT EA-4
18 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 18" WI P/L (PL-318) FROM WHT EA-4 to WHT EA-6
6 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-319) FROM WHT EA-4 to WHT EA-6
22 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 22" WF P/L (PL-321) FROM WHT EA-4 to ERP G-Island
18 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 18" WI P/L (PL-322) FROM ERP G-Island to WHT EA-4
6 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-323) FROM ERP G-Island to WHT EA-4
30 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 30" WG P/L (PL-325) FROM ERP G-Island to ZWSC-RP2
20 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 20" GE P/L (PL-326) FROM ERP G-Island to ZWSC-RP2
30 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 30" OE P/L (PL-329) FROM ERP G-Island to ZWSC-NRP
14 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 14" WF P/L (PL-330) FROM WHT-1 AGI Area to ERP G-Island
6 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-331) FROM ERP G-Island to WHT-1 AGI Area
6 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-334) FROM WHT ZK-182 to ERP G-Island
38 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 38" WF P/L (PL-335) FROM ZCSC-CRP to ERP G-Island
6 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-337) FROM WHT in AGI Area to EPS-2 WHT-2
6 | [6 empty] | PIPELAY ANALYSIS REPORT FOR 6" GL P/L (PL-338) FROM EPS-2 WHT-2 to EPS-2 WHT-3
20 |  |  | START UP HEAD DETAILS FOR | START UP HEAD DETAILS FOR 20" PIPELINE |  | START UP HEAD DETAILS FOR 20" PIPELINE
16 |  |  | START UP HEAD DETAILS FOR | START UP HEAD DETAILS FOR 16" PIPELINE |  | START UP HEAD DETAILS FOR 16" PIPELINE
6 |  |  | START UP HEAD DETAILS FOR | START UP HEAD DETAILS FOR 6" PIPELINE |  | START UP HEAD DETAILS FOR 6" PIPELINE
22 |  |  | START UP HEAD DETAILS FOR | START UP HEAD DETAILS FOR 22" PIPELINE |  | START UP HEAD DETAILS FOR 22" PIPELINE
18 |  |  | START UP HEAD DETAILS FOR | START UP HEAD DETAILS FOR 18" PIPELINE |  | START UP HEAD DETAILS FOR 18" PIPELINE
30 |  |  | START UP HEAD DETAILS FOR | START UP HEAD DETAILS FOR 30" PIPELINE |  | START UP HEAD DETAILS FOR 30" PIPELINE
14 |  |  | START UP HEAD DETAILS FOR | START UP HEAD DETAILS FOR 14" PIPELINE |  | START UP HEAD DETAILS FOR 14" PIPELINE
38 |  |  | START UP HEAD DETAILS FOR | START UP HEAD DETAILS FOR 38" PIPELINE |  | START UP HEAD DETAILS FOR 38" PIPELINE
LAYDOWN HEAD DETAILS FOR 20" PIPELINE
20 |  |  | LAYDOWN HEAD DETAILS FOR | LAYDOWN HEAD DETAILS FOR 20" PIPELINE |  | LAYDOWN HEAD DETAILS FOR 16" PIPELINE
16 |  |  | LAYDOWN HEAD DETAILS FOR | LAYDOWN HEAD DETAILS FOR 16" PIPELINE |  | LAYDOWN HEAD DETAILS FOR 6" PIPELINE
6 |  |  | LAYDOWN HEAD DETAILS FOR | LAYDOWN HEAD DETAILS FOR 6" PIPELINE |  | LAYDOWN HEAD DETAILS FOR 22" PIPELINE
22 |  |  | LAYDOWN HEAD DETAILS FOR | LAYDOWN HEAD DETAILS FOR 22" PIPELINE |  | LAYDOWN HEAD DETAILS FOR 18" PIPELINE
18 |  |  | LAYDOWN HEAD DETAILS FOR | LAYDOWN HEAD DETAILS FOR 18" PIPELINE |  | LAYDOWN HEAD DETAILS FOR 30" PIPELINE
30 |  |  | LAYDOWN HEAD DETAILS FOR | LAYDOWN HEAD DETAILS FOR 30" PIPELINE |  | LAYDOWN HEAD DETAILS FOR 14" PIPELINE
14 |  |  | LAYDOWN HEAD DETAILS FOR | LAYDOWN HEAD DETAILS FOR 14" PIPELINE |  | LAYDOWN HEAD DETAILS FOR 38" PIPELINE
38 |  |  | LAYDOWN HEAD DETAILS FOR | LAYDOWN HEAD DETAILS FOR 38" PIPELINE |  | EMERGENCY LAYDOWN HEAD DETAILS FOR 20" PIPELINE
EMERGENCY LAYDOWN HEAD DETAILS FOR 16" PIPELINE
EMERGENCY LAYDOWN HEAD DETAILS FOR 6" PIPELINE
20 |  |  | EMERGENCY LAYDOWN HEAD DETAILS FOR | EMERGENCY LAYDOWN HEAD DETAILS FOR 20" PIPELINE |  | EMERGENCY LAYDOWN HEAD DETAILS FOR 22" PIPELINE
16 |  |  | EMERGENCY LAYDOWN HEAD DETAILS FOR | EMERGENCY LAYDOWN HEAD DETAILS FOR 16" PIPELINE |  | EMERGENCY LAYDOWN HEAD DETAILS FOR 18" PIPELINE
6 |  |  | EMERGENCY LAYDOWN HEAD DETAILS FOR | EMERGENCY LAYDOWN HEAD DETAILS FOR 6" PIPELINE |  | EMERGENCY LAYDOWN HEAD DETAILS FOR 30" PIPELINE
22 |  |  | EMERGENCY LAYDOWN HEAD DETAILS FOR | EMERGENCY LAYDOWN HEAD DETAILS FOR 22" PIPELINE |  | EMERGENCY LAYDOWN HEAD DETAILS FOR 14" PIPELINE
18 |  |  | EMERGENCY LAYDOWN HEAD DETAILS FOR | EMERGENCY LAYDOWN HEAD DETAILS FOR 18" PIPELINE |  | EMERGENCY LAYDOWN HEAD DETAILS FOR 38" PIPELINE
30 |  |  | EMERGENCY LAYDOWN HEAD DETAILS FOR | EMERGENCY LAYDOWN HEAD DETAILS FOR 30" PIPELINE |  | BUCKLE DETECTOR FOR 20" PIPELINE
14 |  |  | EMERGENCY LAYDOWN HEAD DETAILS FOR | EMERGENCY LAYDOWN HEAD DETAILS FOR 14" PIPELINE |  | BUCKLE DETECTOR FOR 16" PIPELINE
38 |  |  | EMERGENCY LAYDOWN HEAD DETAILS FOR | EMERGENCY LAYDOWN HEAD DETAILS FOR 38" PIPELINE |  | BUCKLE DETECTOR FOR 6" PIPELINE
BUCKLE DETECTOR FOR 22" PIPELINE
BUCKLE DETECTOR FOR 18" PIPELINE
20 |  |  | BUCKLE DETECTOR FOR | BUCKLE DETECTOR FOR 20" PIPELINE |  | BUCKLE DETECTOR FOR 30" PIPELINE
16 |  |  | BUCKLE DETECTOR FOR | BUCKLE DETECTOR FOR 16" PIPELINE |  | BUCKLE DETECTOR FOR 14" PIPELINE
6 |  |  | BUCKLE DETECTOR FOR | BUCKLE DETECTOR FOR 6" PIPELINE |  | BUCKLE DETECTOR FOR 38" PIPELINE
22 |  |  | BUCKLE DETECTOR FOR | BUCKLE DETECTOR FOR 22" PIPELINE |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 20" PIPELINE
18 |  |  | BUCKLE DETECTOR FOR | BUCKLE DETECTOR FOR 18" PIPELINE |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 16" PIPELINE
30 |  |  | BUCKLE DETECTOR FOR | BUCKLE DETECTOR FOR 30" PIPELINE |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 6" PIPELINE
14 |  |  | BUCKLE DETECTOR FOR | BUCKLE DETECTOR FOR 14" PIPELINE |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 22" PIPELINE
38 |  |  | BUCKLE DETECTOR FOR | BUCKLE DETECTOR FOR 38" PIPELINE |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 18" PIPELINE
TEMPORARY PIG LAUNCHER/ RECEVIER FOR 30" PIPELINE
TEMPORARY PIG LAUNCHER/ RECEVIER FOR 14" PIPELINE
20 |  |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 20" PIPELINE |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 38" PIPELINE
16 |  |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 16" PIPELINE
6 |  |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 6" PIPELINE
22 |  |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 22" PIPELINE
18 |  |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 18" PIPELINE
30 |  |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 30" PIPELINE
14 |  |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 14" PIPELINE
38 |  |  | TEMPORARY PIG LAUNCHER/ RECEVIER FOR | TEMPORARY PIG LAUNCHER/ RECEVIER FOR 38" PIPELINE