## Documents - Pipeline & Cable
|  | TAI POWER COMPANY (TPC) | [11 empty] | NMDC ENERGY DOC. No.:
TUN-HSIAO POWER PLAN 2ND STAGE RENEWAL PROJECT TURN-KEY CONTRACT OF SUBSEA GAS PIPELINE
|  | NMDC ENERGYPROJECT NO. 2913 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | TAIPOWER OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO TAIPOWER |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | Pipelaying Installation Analysis Report | 2913-NN-RP-001 | TPSP-TK01-SD-REP-0001 | A | 2 |  | 05-12-2025 | CSE-2913-PMT-T-002 | 22-12-2025 | 2913-NMDC-E-TPC-L-0849 | 26-12-2025 | HK2501-PMT-DT-720 | A | 22-12-2025 | 2913-NMDC-MWS-MG-T-0005 | 2025-12-29 | GM-PRJ121987- |  | again sent to ftp on 09/12/2025
|  |  |  | B | 2 |  | 2026-03-05 | CSE-2913-PMT-T-010 | 2026-03-13 | 2913-NMDC-E-TPC-L-1080 | 2026-03-31 | HK2501-PMT-DT-995 | A - Returned for correction and additional information | 2026-03-17 | 2913-NMDC-MWS-MG-T-0028 | 2026-03-23 | GM-PRJ121987-DR-CS-0004 Rev.2 | A
|  |  |  | C | 2 |  | 2026-04-13 | CSE-2913-PMT-T-015 | 2026-04-14 | 2913-NMDC-E-TPC-L-1207 | 2026-04-30 | TPSP-TK01-REP-SEA-0001-C | A | 2026-04-14 | 2913-NMDC-MWS-MG-T-0036 | 2026-04-30 | GM-PRJ121987-DR-CS-0004 | A
|  |  |  | 0 |  |  | 2026-05-09 | CSE-2913-PMT-T-017 | 2026-05-11 | 2913-NMDC-E-TPC-L-1285 | 2026-05-22 | HK2501-PMT-DT-1167 |  | 2026-05-13 | 2913-NMDC-MWS-MG-T-0041
2 | Pipeline Stacking Analysis Report | 2913-NN-RP-002 | TPSP-TK01-REP-SEA-0004 | A | 2 |  | 26-11-2025 | CSE-2913-PMT-T-001 | 17-12-2025 | 2913-NMDC-E-TPC-L-0838 | 24-12-2025 | HK2501-PMT-DT-715 | A | 17-12-2025 | 2913-NMDC-MWS-MG-T-0003 | 24-12-2025 | GM-PRJ121987-DR-CS-0003 | B | A - Returned for correction and additional information
|  |  |  | B | 2 |  | 23-01-2026 28-01-2026 | CSE-2913-PMT-T-005 | 2026-01-29 | 2913-NMDC-E-TPC-L-0966 | 2026-02-13 | TPSP-TK01-REP-SEA-0004 | A | 2026-01-29 | 2913-NMDC-MWS-MG-T-0019 | 2026-02-13 | GM-PRJ121987-DR-CS-0003 | A
|  |  |  | C | 2 |  | 2026-02-25 | CSE-2913-PMT-T-009 | 2026-03-02 | 2913-NMDC-E-TPC-L-1064 | 2026-03-17 | CECI-1150011323 HK2501-PMT-DT-939 |  | 2026-03-05 | 2913-NMDC-MWS-MG-T-0025 | 2026-03-05 | GM-PRJ121987-COR-EM-0032 | A
|  |  |  | 0 | 3 |  | 2026-03-22 | CSE-2913-PMT-T-011 | 2026-03-26 | 2913-NMDC-E-TPC-L-1155 | 2026-03-26 | HK2501-PMT-DT-1043 |  | 2026-03-30 | 2913-NMDC-MWS-MG-T-0030
3 | Pipeline Midline Tie-in Installation Analysis Report | 2913-NN-RP-003 | TPSP-TK01-REP-SEA-0003 | A | 2 |  | 2026-04-13 | CSE-2913-PMT-T-014 | 2026-04-23 | 2913-NMDC-E-TPC-L-1221 | 2026-05-11 | CECI-1150020240 | A - Returned for correction and additional information | 2026-05-13 | 2913-NMDC-MWS-MG-T-0042 | 2026-06-01 | GM-PRJ121987-COR-EM-0052 | B
4 | MIDLINE TIE-IN ANALYSIS REPORT FOR PL-A | 2913-NN-RP-004
5 | Sea Fastening Design And Transportation Analysis Reports For Pipe Joints | 2913-NN-RP-005 | TPSP-TK01-SD-REP-0002
6 | WELD REPAIR ANALYSIS REPORT | 2913-NN-RP-006
7 | Sea Fastening Design Report for Pipes (Barge -1) | 2913-NN-RP-007
8 | Sea Fastening Design Report for Pipes (Barge -2) | 2913-NN-RP-008
9 | Sea Fastening Design Report for Pipes (Barge -3) | 2913-NN-RP-009
10 | Sea Fastening Design Report for Pipes (Barge -4) | 2913-NN-RP-010
11 | Sea Fastening Design Report for Pipes (Barge -5) | 2913-NN-RP-011
12 | Sea Fastening Design Report for Pipes (Barge -6) | 2913-NN-RP-012
13 | Sea Fastening Design Report for Pipes (Barge -7) | 2913-NN-RP-013
14 | Sea Fastening Design Report for Pipes (Barge -8) | 2913-NN-RP-014
15 | Spare | 2913-NN-RP-015
16
17
18
19
20
21
22
23
24
25
26
27

## Documents - Naval Marine
|  | TAI POWER COMPANY (TPC) | [11 empty] | NMDC ENERGY DOC. No.:
TUN-HSIAO POWER PLAN 2ND STAGE RENEWAL PROJECT TURN-KEY CONTRACT OF SUBSEA GAS PIPELINE
|  | NMDC ENERGYPROJECT NO. 2913 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC ENERGY |  |  |  | TAIPOWER OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO TAIPOWER |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | Mooring Analysis Report | 2913-ZZ-CL-001 | TPSP-TK01-REP-SEA-0005 | A | 2 |  | 17-02-2026 02-03-2026 | CSE-2913-PMT-T-007 | 2026-03-03 | 2913-NMDC-E-TPC-L-1069 | 2026-03-12 | CECI-1150011456 |  | 2026-04-04 | 2913-NMDC-MWS-MG-T-0026 |  | GM-PRJ121987-COR-EM-0036
|  |  |  | B | 2 |  | 2026-04-02 | CSE-2913-PMT-T-012 | 2026-04-04 | 2913-NMDC-E-TPC-L-1185 | 2026-04-17 | CECI-1150017164 |  | 2026-04-04 | 2913-NMDC-MWS-MG-T-0033 |  | GM-PRJ121987-COR-EM-0044
|  |  |  | 0 | 2 |  | 2026-04-27 | CSE-2913-PMT-T-016 | 2026-04-30 | 2913-NMDC-E-TPC-L-1251 |  | HK2501-PMT-DT-1138 |  | 2026-04-30 | 2913-NMDC-MWS-MG-T-0039
2 | DLS 4200 Mooring analysis report during PL-B Laying | 2913-ZZ-CL-002
3 | DLS 4200 Mooring analysis PL-A Mid line tie in Installation | 2913-ZZ-CL-003
4 | DLS 4200 Mooring analysis PL-B Mid line tie in Installation | 2913-ZZ-CL-004
5 | Stability Analysis Report for Pipes (Barge -1) | 2913-ZZ-CL-005
6 | Stability Analysis Report for Pipes (Barge -2) | 2913-ZZ-CL-006
7 | Stability Analysis Report for Pipes (Barge -3) | 2913-ZZ-CL-007
8 | Stability Analysis Report for Pipes (Barge -4) | 2913-ZZ-CL-008
9 | Stability Analysis Report for Pipes (Barge -5) | 2913-ZZ-CL-009
10 | Stability Analysis Report for Pipes (Barge -6) | 2913-ZZ-CL-010
11 | Stability Analysis Report for Pipes (Barge -7) | 2913-ZZ-CL-011
12 | Stability Analysis Report for Pipes (Barge -8) | 2913-ZZ-CL-012
13 | Spare | 2913-ZZ-CL-013
14 | Spare | 2913-ZZ-CL-014
15 | Spare | 2913-ZZ-CL-015
16
17
18
19
20
21
22
23
24
25

## Drawings
|  | TAI POWER COMPANY (TPC) | [11 empty] | NMDC ENERGY DOC. No.:
TUN-HSIAO POWER PLAN 2ND STAGE RENEWAL PROJECT TURN-KEY CONTRACT OF SUBSEA GAS PIPELINE
|  | NMDC ENERGYPROJECT NO. 2913 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DRAWINGS | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NMDC ENERGY DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | TAI POWER | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO TAIPOWER |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | Line Pipes Loading Arrangement - Offshore | 2913-NN-0001 | TPSP-TK01-SD-SEA-0001 | A |  | Not issued officially as per REY 3-4-26 | [12 empty] | Client # changed SM email 13/02
|  |  |  | B | Not issued (SERVER ONLY) REY 06-05-26
2 | START UP HEAD DETAILS FOR 36" PIPELINE LAUNCHER | 2913-NN-0002 |  | A | 2 |  | 2026-01-16 | CSE-2913-PMT-T-004
|  |  |  | B | 2 |  | 2026-02-03 | CSE-2913-PMT-T-006
|  |  |  | C | 2 |  | 2026-02-17 | CSE-2913-PMT-T-008
|  |  |  | 0 | 2 |  | 2026-04-06 | CSE-2913-PMT-T-013
3 | LAYDOWN HEAD DETAILS FOR 36" PIPELINE RECEIVER | 2913-NN-0003 |  | A | CANCELLED |  | 2025-12-12 | CSE-2913-PMT-T-003
|  |  |  | A | 2 |  | 2026-01-16 | CSE-2913-PMT-T-004
|  |  |  | B | 2 |  | 2026-02-03 | CSE-2913-PMT-T-006
|  |  |  | 0 | 2 |  | 2026-04-06 | CSE-2913-PMT-T-013
4 | LAYDOWN HEAD DETAILS FOR 36" PL-B | 2913-NN-0004
5 | EMERGENCY LAYDOWN HEAD FOR 36" PIPELINE RECEIVER | 2913-NN-0005 |  | A | CANCELLED |  | 2025-12-12 | CSE-2913-PMT-T-003
|  |  |  | A | 2 |  | 2026-01-16 | CSE-2913-PMT-T-004
|  |  |  | B | 2 |  | 2026-02-03 | CSE-2913-PMT-T-006
|  |  |  | 0 | 2 |  | 2026-04-06 | CSE-2913-PMT-T-013
6 | EMERGENCY LAYDOWN HEAD FOR 36" PL-B | 2913-NN-0006
7 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPER | 2913-NN-0007
8 | TYPICAL LIFTING AND INSTALLATION OF ROCK DAMPER | 2913-NN-0008
9 | LOADING ARRANGEMENT & SEAFASTENING OF PIPELAY EQUIPMENT WITH BALAST PLAN | 2913-NN-0009
10 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 1 | 2913-NN-0010
11 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 2 | 2913-NN-0011
12 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 3 | 2913-NN-0012
13 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 4 | 2913-NN-0013
14 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 5 | 2913-NN-0014
15 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 6 | 2913-NN-0015
16 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 7 | 2913-NN-0016
17 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 8 | 2913-NN-0017
18 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 9 | 2913-NN-0018
19 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 10 | 2913-NN-0019
20 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 11 | 2913-NN-0020
21 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 12 | 2913-NN-0021
22 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 13 | 2913-NN-0022
23 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 14 | 2913-NN-0023
24 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 15 | 2913-NN-0024
25 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 16 | 2913-NN-0025
26 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 17 | 2913-NN-0026
27 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 18 | 2913-NN-0027
28 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 19 | 2913-NN-0028
29 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 20 | 2913-NN-0029
30 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 21 | 2913-NN-0030
31 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 22 | 2913-NN-0031
32 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 23 | 2913-NN-0032
33 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 24 | 2913-NN-0033
34 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 25 | 2913-NN-0034
35 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 26 | 2913-NN-0035
36 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 27 | 2913-NN-0036
37 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 28 | 2913-NN-0037
38 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 29 | 2913-NN-0038
39 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 30 | 2913-NN-0039
40 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 31 | 2913-NN-0040
41 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 32 | 2913-NN-0041
42 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 33 | 2913-NN-0042
43 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 34 | 2913-NN-0043
44 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 35 | 2913-NN-0044
45 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 36 | 2913-NN-0045
46 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 37 | 2913-NN-0046
47 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 38 | 2913-NN-0047
48 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 39 | 2913-NN-0048
49 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 40 | 2913-NN-0049
50 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 41 | 2913-NN-0050
51 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 42 | 2913-NN-0051
52 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 43 | 2913-NN-0052
53 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 44 | 2913-NN-0053
54 | LOADING ARRANGEMENT & SEAFASTENING OF PIPES - TRIP 45 | 2913-NN-0054
55 | BUCKLE DETECTOR FOR 36” GAS LINE | 2913-NN-0055
56 | EMERGENCY LAYDOWN HEAD FOR 36” PIPELINE | 2913-NN-0056
57 | RECOVERY HEAD DETAILS FOR 36”PIPELINE | 2913-NN-0057 |  | A | 2 |  | 2026-07-20 | CSE-2913-PMT-T-019 | [10 empty] | REVISED DRG. ON 27/07 WITH SERVER ONLY
58 | BUCKLE RECOVERY HEAD FOR 36” PIPELINE | 2913-NN-0058 |  | A | 2 |  | 2026-05-09 | CSE-2913-PMT-T-018

## Sketch
Project 2913
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2913 | OFO-P2913-SK-T-001 | 36" PIPELINE - DAVIT LATERAL LOAD DURING MIDLINE | 1 | A | √ | √ | 17/03/2025 | CDG | @
2 | 2913 | OFO-P2913-SK-T-002 | NMDC PIPES STORAGE AREA | 1 | A | √ | √ | 19/04/2025 | REY | @
3 | 2913 | OFO-P2913-SK-T-003 | PIPELAY PROFILE FOR 36’’ PIPELINE (DLS-4200) | 1 | A | √ | √ | 03/06/2025 | CDG | @
4 | 2913 | OFO-P2913-SK-T-004 | DLS-4200 MAIN DECK GENERAL ARRANGEMENT DURING PIPE LAY | 1 | A | √ | √ | 20/09/2025 | LEO | @
5 | 2913 | OFO-P2913-SK-T-005 | TYPICAL 30" CC PIPE LIFTING | 1 | C | √ | √ | 04/06/2026 | HZD | @
6 | 2913 | OFO-P2913-SK-T-006 | 36" PIPES ONBOARD (EEMS-DUBLIN / DOVER) | 1 | A | √ | √ | 02/09/2025 | LEO | @
7 | 2913 | OFO-P2913-SK-T-007 | 36" PIPES ONBOARD (SYMPHONY PROVIDER) | 2 | B | √ | √ | 04/02/2026 | AMT | @
8 | 2913 | OFO-P2913-SK-T-008 | DLS 4200 DECK LAYOUT DURING TRANSIENT TO TAIWAN | 1 | B | √ | √ | 23/12/2025 | BAJ | @
9 | 2913 | OFO-P2913-SK-T-009 | TYPICAL ARRANGEMENT OF FLOATS AND SHELL SLEEVE BAGS DISTRIBUTION ON PIPE JOINT | 1 | C | √ | √ | 15/12/2025 | SKS | @
10 | 2913 | OFO-P2913-SK-T-010 | TYPICAL ABANDONMENT & RECOVERY / LAYDOWN ARRANGEMENT WITH DLS-4200 | 1 | B | √ | √ | 10/04/2026 | SSK | @
11 | 2913 | OFO-P2913-SK-T-011 | DLS-4200 – FIRE LINE STATION ARRANGEMENT | 1 | A | √ | √ | 46028 | SKS | @
12 | 2913 | OFO-P2913-SK-T-012 | DLS-4200 PIPELAY PROFILE FOR 36" SUBSEA GAS PIPELINE | 1 | B | √ | √ | 04/12/2025 | LEO | @
13 | 2913 | OFO-P2913-SK-T-013 | GENERAL ARRANGEMENT FOR AWTI PLATFORM ON DLS-4200 | 2 | A | √ | √ | 03/12/2025 | SKS | @
14 | 2913 | OFO-P2913-SK-T-014 | ABOVE WATER TIE-IN PLATFORM [AWTI] |  |  |  |  | 03/12/2025 | SKS
15 | 2913 | OFO-P2913-SK-T-015 | DLS-4200 DMA START-UP ARRANGEMENT FOR 36" SUBSEA PIPELINE | 2 | B | √ | √ | 05/03/2026 | SSK | @
16 | 2913 | OFO-P2913-SK-T-016 | MIDLINE TIE-IN ARRANGEMENT AT KP 3.149 FOR 36" PIPELINE "A" | 2 | D | √ | √ | 08/05/2026 | LEO | @
17 | 2913 | OFO-P2913-SK-T-017 | MIDLINE TIE-IN ARRANGEMENT AT KP 52.629 FOR 36" PIPELINE "B" | 2 | D | √ | √ | 08/05/2026 | LEO | @
18 | 2913 | OFO-P2913-SK-T-018 | TYPICAL FOR 20.6T STEVSHARK ®REX ANCHOR SYSTEM |  | A | √ | √ | 05/01/2026 | SKS |  | server only REY email dtd. 26/01
19 | 2913 | OFO-P2913-SK-T-019 | TYPICAL PRESET FOR 20.6T STEVSHARK ®REX ANCHOR SYSTEM |  | A | √ | √ | 05/01/2026 | SKS |  | server only REY email dtd. 26/01
20 | 2913 | OFO-P2913-SK-T-020 | TYPICAL 20.6T STEVSHARK ®REX PIGGYBACK ANCHOR SYSTEM | 1 | A | √ | √ | 11/01/2026 | SKS | @
21 | 2913 | OFO-P2913-SK-T-021 | 20.6T STEVSHARK ®REX ARRANGEMENT AHT (PRESET DEPLOYMENT USING SINGLE AHT) | 1 | A | √ | √ | 11/01/2026 | SKS | @
22 | 2913 | OFO-P2913-SK-T-022 | DEPLOYMENT SEQUENCE FOR TYPICAL 20.6T STEVSHARK ®REX TYPICAL PRESET MOORING SYSTEM USING SINGLE AHT | 3 | A | √ | √ | 11/01/2026 | SKS | @
23 | 2913 | OFO-P2913-SK-T-023 | RECOVERY SEQUENCE FOR TYPICAL 20.6T STEVSHARK ®REX MOORING SYSTEM | 1 | A | √ | √ | 11/01/2026 | SKS | @
24 | 2913 | OFO-P2913-SK-T-024 | DEPLOYMENT SEQUENCE OF 20.6T STEVSHARK ®REX ANCHOR (PIGGYBACK) OPTION-2 | 1 | A | √ | √ | 11/01/2026 | SKS | @
25 | 2913 | OFO-P2913-SK-T-025 | SEQUENCE OF MIDLINE TIE-IN INSTALLATION SKT BY DLS-4200 | 4 | A | √ | √ | 26/01/2026 | CDG | @
26 | 2913 | OFO-P2913-SK-T-026 | MIDLINE TIE-IN PLATFORM ON DLS-4200 | 4 + 63 | A, 0 | √ | √ | 31/01/2026 | LEO | @
27 | 2913 | OFO-P2913-SK-T-027 | LIFTING & OFFLOADING OF STINGER-10A AT JETTY BY DLS-4200 (OPTION-A) | 2 | A | √ | √ | 06/06/2026 | NAR | @
28 | 2913 | OFO-P2913-SK-T-028 | LIFTING & OFFLOADING OF STINGER-10A AT JETTY BY DLS-4200 (OPTION-2) |  |  |  |  | 21/01/2026 | NAR
29 | 2913 | OFO-P2913-SK-T-029 | PIPELINE LAYDOWN SEQUENCE | 4 | B | √ | √ | 08/05/2026 | LEO | @
30 | 2913 | OFO-P2913-SK-T-030 | DLS 4200 DECK LAYOUT DURING OPERATIONS IN TAIWAN | 1 | A | √ | √ | 28/01/2026 | SRV | SERVER ONLY
31 | 2913 | OFO-P2913-SK-T-031 | DLS 4200 DECK LAYOUT DURING WEATHER STANDBY IN TAIWAN | 1 | A | √ | √ | 02/02/2026 | SRV
32 | 2913 | OFO-P2913-SK-T-032 | DLS-4200 TYPICAL SETUP AT CROSSING POINTS | 1 | B | √ | √ | 08/05/2026 | LEO | @
33 | 2913 | OFO-P2913-SK-T-033 | STORM CLAMP FOR36" PIPELINE | 1 | A | √ | √ | 17/02/2026 | SC | @
34 | 2913 | OFO-P2913-SK-T-034 | PIPELINE HDD OVERLENGTH RECOVERY ARRANGEMENT | 1 | B | √ | √ | 02/04/2026 | MF | @
35 | 2913 | OFO-P2913-SK-T-035 | DEPLOYMENT SEQUENCE FOR TYPICAL 20.6T STEVSHARK ®REX MOORING SYSTEM | 3 | A | √ | √ | 11/01/2026 | SKS | @
36 | 2913 | OFO-P2913-SK-T-036 | 20.6T STEVSHARK ®REX TYPICAL MOORING SYSTEM ARRANGEMENT ON AHT DECK | 1 | A | √ | √ | 11/01/2026 | SKS | @
37 | 2913 | OFO-P2913-SK-T-037 | TYPICAL 20.6T STEVSHARK ®REX PIGGYBACK ANCHOR SYSTEM (OPTION-2) | 1 | A | √ | √ | 11/01/2026 | SKS | @
38 | 2913 | OFO-P2913-SK-T-038 | DEPLOYMENT SEQUENCE OF 20.6T STEVSHARK ®REX ANCHOR (PIGGYBACK) (OPTION-2) | 3 | A | √ | √ | 11/01/2026 | SKS | @
39 | 2913 | OFO-P2913-SK-T-039 | DLS 4200: DECK LAYOUT DURING TRANSIT TO TAIWAN | 1 | A | √ | √ | 16/02/2026 | SKS | @ | SERVER ONLY
40 | 2913 | OFO-P2913-SK-T-040 | DLS-4200: STINGER SEAFASTENING | 1 | A | √ | √ | 04/03/2026 | HZD | @
41 | 2913 | OFO-P2913-SK-T-041 | STORYBOARD FOR STARTUP DMA INSTALLATION UTILIZING LAYING VESSEL | 6 | A | √ | √ | 01/04/2026 | SKS | @ | SERVER ONLY
42 | 2913 | OFO-P2913-SK-T-042 | TYPICAL 36" CC PIPE LIFTING IN ANCHOR MODE BY DLS-4200 | 1 | B | √ | √ | 46177 | HZD | @
43 | 2913 | OFO-P2913-SK-T-043 | BOUYANCY UNIT RIGGING ARRANGEMENT | 1 | B | √ | √ | 17/03/2026 | LEO | @
44 | 2913 | OFO-P2913-SK-T-044 | DLS-4200 DMA START-UP ARRANGEMENT FOR 36" SUBSEA PIPELINE "A" AT KP 51.334 | 2 | A | √ | √ | 05/03/2026 | SSK | @
45 | 2913 | OFO-P2913-SK-T-045 | Pipe Fender on DLS-4200 | 5 | A | √ | √ | 04/04/2026 | LEO | @ | SERVER ONLY
46 | 2913 | OFO-P2913-SK-T-046 | DLS-4200: FOAM FLOATERS PLATFORM AT STERN | 4 | A | √ | √ | 16/03/2026 | SKS | @
47 | 2913 | OFO-P2913-SK-T-047 | DLS-4200 SETUP DURING FOAM FLOAT DISONNECTION SEQUENCE |  |  |  |  | 17/03/2026 | NEH
48 | 2913 | OFO-P2913-SK-T-048 | STORYBOARD FOR STARTUP DMA INSTALLATION UTILIZING AHT | 6 | A | √ | √ | 09-04-2026 | SKS | @ | SERVER ONLY
49 | 2913 | OFO-P2913-SK-T-049 | LIFTING AND REMOVAL OF EXISTING SHELL SLEEVE BY DLS-4200 | 1 | A | √ | √ | 17/04/2026 | SRV | @
50 | 2913 | OFO-P2913-SK-T-050 | BEAR CAGE CLAMP LIFTIING & INSTALLATION ARRANGEMENT BY DLS-4200 | 1 | A | √ | √ | 07/04/2026 | SRV | @
51 | 2913 | OFO-P2913-SK-T-051 | TYPICAL RIGGING ARRANGEMENT FOR 36” PIPELINE HEADS |  |  |  |  | 14/04/2026 | SIVA
52 | 2913 | OFO-P2913-SK-T-052 | HEAD RECOVEY CLAMP DETAIL & SECTIONS |  |  |  |  | 03/09/2026 | BINOY
53 | 2913 | OFO-P2913-SK-T-053 | HEAD RECOVEY CLAMP (OP-2) DETAIL & SECTIONS |  |  |  |  | 07/09/2026 | BINOY
36" PIPELINE - DAVIT LATERAL LOAD DURING MIDLINE

## Cut-lists
Project 2913
CUT-LIST DRAWINGS
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2913 | OFO-P2913-SK-T-026-CTL | MIDLINE TIE-IN PLATFORM ON DLS-4200 | 4 + 63 | 0 | √ | √ | 31-01-2026 | Irfan | @
2 | 2913 | 2913-NN-0002-CTL | START UP HEAD DETAILS FOR 36" PIPELINE LAUNCHER | 2 + 20 | 0 | √ | √ | 02-02-2026 | sent through email - SM | @
3 | 2913 | 2913-NN-0003-CTL | LAYDOWN HEAD DETAILS FOR 36" PIPELINE RECEIVER | 2 + 20 | 0 | √ | √ | 02-02-2026 | sent through email - SM | @
4 | 2913 | 2913-NN-0005-CTL | EMERGENCY LAYDOWN HEAD FOR 36" PIPELINE RECEIVER | 2 + 20 | 0 | √ | √ | 02-02-2026 | sent through email - SM | @
5 | 2913 | OFO-P2913-SK-T-033-CTL | STORM CLAMP FOR36" PIPELINE | 1 + 5 | 0 | √ | √ | 17-02-2026 | sent through email - SM | @
6 | 2913 | 2913-NN-0057-CTL | RECOVERY HEAD DETAILS FOR 36”PIPELINE | 1 + 9 | 0 | √ | √ | 2026-07-20 | sent through email - SM | @ | REVISED DRG. ON 27/07 WITH SERVER ONLY
7 | 2913
8 | 2913