## Documents - Pipeline & Cable
NPCC DOC. No.:
|  | LTHE - BASSEIN DEVELOPMENT PROJECT ( SUBCONTRACT FOR INSTALLATION WORKS) | [10 empty] | . No. :
|  | NPCC PROJECT NO. 3249 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DRAWINGS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 2016-10-19
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[6 empty] | DATE | REF | REF | DATE | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPELAY INSTALLATION REPORT FOR 8 " OIL PIPE LINE FROM BH to BCPA-2 | 3249-NN-RP-001 | 0 | 2 | 2016-10-15 | 2016-11-02 | CSE-OF-3249-003 | 3249-NPCC-LTHE-T-0151 | 2016-11-03 | 2016-12-08 | email |  |  |  | 2016-12-06 | Email 11-00032MI-95
|  |  | 1 | 2 |  | 2016-12-12 | CSE-OF-3249-024 | 3249-NPCC-LTHE-T-0240 | 2016-12-13
2 | PIPELAY INSTALLATION REPORT FOR 14 " OIL PIPE LINE FROM BH to BCPA-3 | 3249-NN-RP-002 | 0 | 2 | 2016-10-15 | 2016-11-02 | CSE-OF-3249-003 | 3249-NPCC-LTHE-T-0152 | 2016-11-03 | [5 empty] | 2016-12-05 | Email 11-00032MI-96
|  |  | 1 | 2 |  | 2016-12-08 | CSE-OF-3249-023 | 3249-NPCC-LTHE-T-0238 | 2016-12-13
3 | SPOOL LIFT ANALYSIS REPORT FOR 8" OIL PIPELINE FROM BH TO BCPA-2 AT BCPA-2 | 3249-NN-RP-003 | 0 | 2 | 2016-11-10
4 | RISER LIFT ANALYSIS REPORT FOR 8 " OIL PIPE LINE FROM BH to BCPA-2 (@BCPA-2) | 3249-NN-RP-004 | 0 | 2 | 2016-11-10 | 2016-12-05 | CSE-OF-3249-020 | 3249-NPCC-LTHE-T-0234 | 2016-12-08
5 | SPOOL LIFT ANALYSIS REPORT FOR 8 " OIL PIPE LINE FROM BH to BCPA-2 (@BH) | 3249-NN-RP-005 | 0 | 2 | 2016-11-10 | 2017-01-16 | CSE-OF-3249-031 | 3249-NPCC-LTHE-T-0306 | 2017-01-17
6 | SPOOL LIFT ANALYSIS REPORT FOR 14 " WF (GAS) PIPE LINE FROM BH to BCPA-3 (@BH) | 3249-NN-RP-006 | 0 | 2 | 2016-11-10 | 2017-01-18 | CSE-OF-3249-034 | 3249-NPCC-LTHE-T-0311 | 2017-01-19 | [8 empty] | title changed 14" oil P/l
7 | SPOOL LIFT ANALYSIS REPORT FOR 14 " WF (GAS) PIPE LINE FROM BH to BCPA-3 (@BCPA-3) | 3249-NN-RP-007 | 0 | 2 | 2016-11-10 | 2017-02-21 | CSE-OF-3249-039 | 3249-NPCC-LTHE-T-0344 | 2017-02-21
8 | Spare | 3249-NN-RP-008
9 | Spare | 3249-NN-RP-009
10 | Spare | 3249-NN-RP-010
11 | Spare | 3249-NN-RP-011
12
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION; (4) REJECTED
LTHE CODE : (1) REJECTED; (2) COMMENTED - WORK MAY PROCEED; (3) APPROVED; (4) FOR INFORMATION
MWS APPROVAL CODE : (A) ACCEPTED WITHOUT COMMENTS; (B) ACCEPTED SUBJECT TO COMMENTS; (C) NOT ACCEPTED; (D) INFORMATION ONLY

## Documents - Naval Marine
NPCC DOC. No.:
|  | LTHE - BASSEIN DEVELOPMENT PROJECT ( SUBCONTRACT FOR INSTALLATION WORKS) | [10 empty] | . No. :
|  | NPCC PROJECT NO. 3249 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DRAWINGS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 2016-10-19
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN |  |  | NPCC |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | MOORING ANALYSIS REPORT FOR 8" OIL PIPE LINE FROM BH TO BCPA-2 AND 14" GAS PIPELINE FROM BH TO BCPA-3 | 3249-ZZ-RP-001 | 0 | 2 | 2016-10-20 | 2016-11-01 | CSE-OF-3249-002 | 02/11/2016 | 3249-NPCC-LTHE-T-0148 | 2016-11-14 | EMAIL | 2
|  |  | 1 | 1 |  | 2016-11-15 | CSE-OF-3249-009 | 2016-11-15 | 3249-NPCC-LTHE-T-0172
|  |  | CRS | 2 |  | 2016-11-24 | CSE-OF-3249-015 | 2016-11-24 | 3249-NPCC-LTHE-T-0203 | 2016-11-28 | EMAIL
|  |  | CRS | 2 |  | 2016-12-07 | CSE-OF-3249-021 | 2016-12-08 | 3249-NPCC-LTHE-T-0228 | [5 empty] | 2016-12-27 | 11-00032MI-94
2 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 14 " OIL PIPE LINE FROM BH to BCPA-3 | 3249-ZZ-RP-002 | 0 | 1 | SPARE | remarks | [11 empty] | merged with 3249-zz-rp- 001
3 | MOORING ANALYSIS REPORT DURING RISER INSTALLATION AT BCPA-2 | 3249-ZZ-RP-003 | 0 | 2 | 2016-10-30 | 2016-11-17 | CSE-OF-3249-011 | 2016-11-20 | 3249-NPCC-LTHE-T-0197
|  |  | 1 | 2 |  | 2016-12-27 | CSE-OF-3249-027 | 2016-12-28 | 3249-NPCC-LTHE-T-0276 | [5 empty] | 2017-01-17 | 11-00032MI-127
|  |  | 2 | 2 |  |  |  |  | EMAIL SENT ON 06/01/2017
|  |  | 3 | 2 |  | 2017-01-19 | CSE-OF-3249-035 | 2017-01-19 | 3249-NPCC-LTHE-T-0315
|  |  | CRS |  |  | 2017-01-23 | EMAIL SENT | 2017-01-24 | 3249-NPCC-LTHE-T-0319
|  |  | 4 | 2 |  | 2017-01-29 | CSE-OF-3249-037 | 2017-01-29 | 3249-NPCC-LTHE-T-0328
4 | MOORING ANALYSIS REPORT FOR JACKET, DECK AND PILE INSTALLATION AT BH | 3249-ZZ-RP-004 | 0 | 2 | 2016-10-30 | 2016-11-16 | CSE-OF-3249-010 | 2016-11-17 | 3249-NPCC-LTHE-T-0183
|  |  | 1 | 2 |  | 2016-12-15 | CSE-OF-3249-025 | 2016-12-15 | 3249-NPCC-LTHE-T-0253 | [5 empty] | 2016-12-27 | 11-00032MI-115
|  |  | 2 | 2 |  | 2016-12-28 | CSE-OF-3249-028 | 2016-12-29 | 3249-NPCC-LTHE-T-0285 | [5 empty] | 2017-01-03 | 11-00032MI-115
|  |  | CRS | [11 empty] | 2017-01-04 | sent by mail
5 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION (BH WHP) TOPSIDE | 3249-ZZ-RP-005 | 0 | 1 | 2016-11-05
6 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF (BCPA-3) JACKET AND PILE | 3249-ZZ-RP-006 | 0 | 1 | 2016-11-11 | 2016-12-08 | CSE-OF-3249-022 | 2016-12-08 | 3249-NPCC-LTHE-T-0232
|  |  | 1 |  |  | 2016-12-27 | CSE-OF-3249-027 | 2016-12-28 | 3249-NPCC-LTHE-T-0277 | [5 empty] | 2017-01-19 | 11-00032MI-128
|  |  | 2 |  |  | 2017-01-31 | CSE-OF-3249-038 | 2017-02-01 | 3249-NPCC-LTHE-T-0330
7 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF BLQ-3 JACKET AND PILE | 3249-ZZ-RP-007 | 0 | 1 | 2016-11-15 | 2017-01-09 | CSE-OF-3249-029 | 2017-01-11 | 3249-NPCC-LTHE-T-0304 | [5 empty] | 2017-02-07 | CRS
|  |  | CRS |  |  |  | EMAIL SENT ON 09/02/2017 | 2017-02-21 | 3249-NPCC-LTHE-T-0343 | [5 empty] | 2017-02-21 | 11-00032MI-156
|  |  | 1 | 1 |  | 2017-02-23 | CSE-OF-3249-040 | 2017-02-23 | 3249-NPCC-LTHE-T-0349 | [5 empty] | 2017-02-26 | 11-00032MI-156 R1
|  |  | CRS |  |  |  | EMAIL SENT ON 26/02/2017
8 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF BLQ-3 TOPSIDE | 3249-ZZ-RP-008 | 0 | 1 | 2016-11-15 | 2017-01-15 | CSE-OF-3249-030 | 2017-01-15 | 3249-NPCC-LTHE-T-0305
9 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF (BCPA-2) - (BCPA-3) BRIDGE | 3249-ZZ-RP-009 | 0 | 1 | 2016-11-20 | 2017-01-16 | CSE-OF-3249-032 | 2017-01-17 | 3249-NPCC-LTHE-T-0307
10 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF (BCPA-3) TOPSIDES MODULES (5NOS) | 3249-ZZ-RP-010 | 0 | 1 | 2016-11-23
11 | SPARE | 3249-ZZ-RP-011
12 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF BLQ3 - BCPA3 BRIDGE | 3249-ZZ-RP-012 | 0 | 1 | 2016-11-25 | 2017-01-25 | CSE-OF-3249-036 | 2017-01-26 | 3249-NPCC-LTHE-T-0324
13 | SPARE | 3249-ZZ-RP-013
14 | SPARE | 3249-ZZ-RP-014
15 | SPARE | 3249-ZZ-RP-015
16 | SPARE | 3249-ZZ-RP-016
17
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION; (4) REJECTED
LTHE CODE : (1) REJECTED; (2) COMMENTED - WORK MAY PROCEED; (3) APPROVED; (4) FOR INFORMATION
MWS APPROVAL CODE : (A) ACCEPTED WITHOUT COMMENTS; (B) ACCEPTED SUBJECT TO COMMENTS; (C) NOT ACCEPTED; (D) INFORMATION ONLY

## Drawings
NPCC DOC. No.:
|  | LTHE - BASSEIN DEVELOPMENT PROJECT ( SUBCONTRACT FOR INSTALLATION WORKS) | [10 empty] | . No. :
|  | NPCC PROJECT NO. 3249 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DRAWINGS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 2016-10-19
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN |  |  | NPCC |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | REF | DATE | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | BUCKLE DETECTOR DETAILS FOR 8 " OIL PIPE LINE FROM BH to BCPA-2 | 3249-NN-001 | 0 | 2 | 2016-10-15 | 2016-10-30 | CSE-OF-3249-001 | 3249-NPCC-LTHE-T-0138 | 2016-10-31 | 2016-11-10 | 3249-NPCC-LTHE-T-0138 | 2 | [5 empty] | AKS
2 | START UP HEAD DETAILS FOR 8 " OIL PIPE LINE FROM BH to BCPA-2 | 3249-NN-002 | 0 | 2 | 2016-10-20 | 2016-10-30 | CSE-OF-3249-001 | 3249-NPCC-LTHE-T-0138 | 2016-10-31 | 2016-11-10 | 3249-NPCC-LTHE-T-0138 | 2 | [5 empty] | AKS
3 | LAYDOWN HEAD DETAILS FOR 8 " OIL PIPE LINE FROM BH to BCPA-2 | 3249-NN-003 | 0 | 2 | 2016-10-20 | 2016-10-30 | CSE-OF-3249-001 | 3249-NPCC-LTHE-T-0138 | 2016-10-31 | 2016-11-10 | 3249-NPCC-LTHE-T-0138 | 2 | [5 empty] | AKS
|  |  | 1 | 1 |  | 2016-11-07 | CSE-OF-3249-008 | 3249-NPCC-LTHE-T-0165 | 2016-11-10 | [8 empty] | CDG
4 | BUCKLE DETECTOR DETAILS FOR 14 " OIL PIPE LINE FROM BH to BCPA-3 | 3249-NN-004 | 0 | 2 | 2016-10-15 | 2016-10-30 | CSE-OF-3249-001 | 3249-NPCC-LTHE-T-0138 | 2016-10-31 | 2016-11-10 | 3249-NPCC-LTHE-T-0138 | 2 | [5 empty] | AKS
5 | START UP HEAD DETAILS FOR 14 " OIL PIPE LINE FROM BH to BCPA-3 | 3249-NN-005 | 0 | 2 | 2016-10-20 | 2016-11-07 | CSE-OF-3249-005 | 3249-NPCC-LTHE-T-0161 | 2016-11-17 | [8 empty] | HZD
6 | LAYDOWN HEAD DETAILS FOR 14 " OIL PIPE LINE FROM BH to BCPA-3 | 3249-NN-006 | 0 | 2 | 2016-10-20 | 2016-11-07 | CSE-OF-3249-005 | 3249-NPCC-LTHE-T-0161 | 2016-11-17 | [8 empty] | NAR
7 | TEMPORARY KNEE BRACE DETAILS FOR 8 " OIL PIPE LINE FROM BH to BCPA-2 (@BH) | 3249-NN-007 | 0 | 2 | 2016-11-05 | 2016-11-27 | CSE-OF-3249-016 | 3249-NPCC-LTHE-T-0214 | 2016-11-28
8 | TEMPORARY KNEE BRACE DETAILS FOR 8 " OIL PIPE LINE FROM BH to BCPA-2 (@BCPA-2) | 3249-NN-008 | 0 | 2 | 2016-11-05
9 | TEMPORARY KNEE BRACE DETAILS FOR 14 " OIL PIPE LINE FROM BH to BCPA-3 (@BH) | 3249-NN-009 | 0 | 2 | 2016-11-08 | 2016-11-27 | CSE-OF-3249-016 | 3249-NPCC-LTHE-T-0214 | 2016-11-28
10 | TEMPORARY KNEE BRACE DETAILS FOR 14" OIL PIPE LINE FROM BH to BCPA-3 (@BCPA-3) | 3249-NN-010 | 0 | 2 | 2016-11-05 | 2016-11-27 | CSE-OF-3249-016 | 3249-NPCC-LTHE-T-0214 | 2016-11-28
11 | HYDROTEST DIAGRAM FOR 8 " OIL PIPE LINE FROM BH to BCPA-2 | 3249-NN-011 | 0 | 2 | 2016-11-20
12 | HYDROTEST DIAGRAM FOR 14 " OIL PIPE LINE FROM BH to BCPA-3 | 3249-NN-012 | 0 | 2 | 2016-11-20
13 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 8 " OIL PIPE LINE FROM BH to BCPA-2 | 3249-NN-013 | 0 | 2 | 2016-11-20
14 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 14 " OIL PIPE LINE FROM BH to BCPA-3 | 3249-NN-014 | 0 | 2 | 2016-11-20
15 | SPOOL LIFTING AND INSTALLATION FOR 8 " OIL PIPE LINE FROM BH to BCPA-2(@BH) | 3249-NN-015 | 0 | 2 | 2016-11-05 | 2017-01-16 | CSE-OF-3249-031 | 3249-NPCC-LTHE-T-0306 | 2017-01-17
|  |  | 1 | 2 |  | 2017-01-18 | CSE-OF-3249-033 | 3249-NPCC-LTHE-T-0309 | 2017-01-19
16 | RISER/SPOOL LIFTING AND INSTALLATION FOR 8 " OIL PIPE LINE FROM BH to BCPA-2(@BCPA-2) | 3249-NN-016 | 0 | 2 | 2016-11-05 | 2016-12-05 | CSE-OF-3249-019 | 3249-NPCC-LTHE-T-0230 | 2016-12-08
|  |  | 1 | 2 |  | 2016-12-25 | CSE-OF-3249-026 | 3249-NPCC-LTHE-T-0268 | 2016-12-25
17 | SPOOL LIFTING AND INSTALLATION FOR 14 " WF (GAS) PIPELINE FROM BH to BCPA-3(@BH) | 3249-NN-017 | 0 | 2 | 2016-11-05 | 2017-01-18 | CSE-OF-3249-034 | 3249-NPCC-LTHE-T-0311 | 2017-01-19 | [8 empty] | title changed - 14" oil P/L
18 | SPOOL LIFTING AND INSTALLATION FOR 14 " WF (GAS) PIPE LINE FROM BH to BCPA-3(@BCPA-3) | 3249-NN-018 | 0 | 2 | 2016-11-05 | 2017-02-21 | CSE-OF-3249-039 | 3249-NPCC-LTHE-T-0345 | 2017-02-21
19 | FLANGE PROTECTOR FOR 8" SUH | 3249-NN-019 | 0 | 2 | 2016-10-20 | TAKEN BY CDG
20 | FLANGE PROTECTOR FOR 8" LDH | 3249-NN-020 | 0 | 2 | 2016-10-20 | 2016-11-06 | CSE-OF-3249-004 | 3249-NPCC-LTHE-T-0157 | 2016-11-06 | [8 empty] | AKS
21 | FLANGE PROTECTOR FOR 14" SUH | 3249-NN-021 | 0 | 2 | 2016-10-20 | 2016-11-06 | CSE-OF-3249-004 | 3249-NPCC-LTHE-T-0157 | 2016-11-06 | [8 empty] | AKS
22 | FLANGE PROTECTOR FOR 14" LDH | 3249-NN-022 | 0 | 2 | 2016-10-20 | 2016-11-06 | CSE-OF-3249-004 | 3249-NPCC-LTHE-T-0157 | 2016-11-06 | [8 empty] | AKS
23 | SHROUD FOR SSIV | 3249-NN-023 | 0 | 2 | 2016-10-25
24 | TEMPORARY SLEEPERS | 3249-NN-024 | 0 | 2 | 2016-10-25
25 | LOADING ARRANGEMENT & SEAFASTENING OF STINGER-9A @ GAC-66 | 3249-NN-025 | 0 | 2 |  | 2016-11-30 | CSE-OF-3249-017 | 3249-NPCC-LTHE-T-0233 | 2016-12-08
26 | VALVE PROTECTOR FOR 14" WF(GAS) PIPELINE FROM BH TO BCPA-3 | 3249-NN-026 | 0 | 2 |  | 2016-11-21 | CSE-OF-3249-013 | 3249-NPCC-LTHE-T-0201 | 2016-11-22 | [8 empty] | AKS
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION; (4) REJECTED
LTHE CODE : (1) REJECTED; (2) COMMENTED - WORK MAY PROCEED; (3) APPROVED; (4) FOR INFORMATION
MWS APPROVAL CODE : (A) ACCEPTED WITHOUT COMMENTS; (B) ACCEPTED SUBJECT TO COMMENTS; (C) NOT ACCEPTED; (D) INFORMATION ONLY