## Documents
|  |  | Client : ADMA-OPCO | [11 empty] | NPCC DOC. No.:
|  | ADDITIONAL GAS SUPPLY TO ONSHORE AND FLEXIBILITY ASSURANCE AT USSC. | [12 empty] | ADMA DOC. No. :
|  |  | Project 3278 | [11 empty] | REVISION :
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS | [12 empty] | DATE :
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADMA-OPCO |  |  | TPA (BV) |  |  | MWS (MD) |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADMA-OPCO
[7 empty] | REF | DATE | REF | DATE | REF | DATE | CODE | REF | DATE | CODE | REF | DATE | CODE
1 | SEP-250 MOORING ANALYSIS AT US-216 | 3278-PP-OF-040 | AD214-026-G-00900 | 1 | 1 | SUBMITTED | CSE-OF-3278-019 | 2017-04-02 | 3278-NPCC-AO-T-08506 | 2017-04-02 | AO-NPCC-TN-4645 | 2017-04-25 | A
2 | SEP-250 MOORING ANALYSIS AT ABK-TIP (FIRST SET-UP) | 3278-PP-OF-042 | AD214-026-G-00902 | 1 | 1 | SUBMITTED | SENT TO PMT | 2015-09-30 | 3278-NPCC-AO-T-05311 | 2015-09-30 | AO-NPCC-TN-3229 | 2015-10-06 | B |  |  |  | MDDXB 5092-MD-03-407-01 | 2015-10-01 | COMMENTED
3 | MOORING ANALYSIS DOCUMENTS FOR JACKET AND DECK INSTALLATION | 3278-PP-OF-061 | AD214-026-G-01814
4 | CABLE INSTALLATION ANALYSIS | 3278-PP-OF-062 | AD214-026-G-01815 | 1 | 1 | SUBMITTED | CSE-OF-3278-004 | 2016-03-30 | 3278-NPCC-AO-T-07280 | 2016-03-31 | AO-NPCC-TN-4219 | 2016-06-07 | B
|  |  |  | 2 | 1 | SUBMITTED | CSE-OF-3278-009 | 2016-07-12 | 3278-NPCC-AO-T-07906 | 2016-07-13 | AO-NPCC-TN-4296 | 2016-06-17 | B
5 | MOORING ANALYSIS DURING TAE JACKET INSTALLATION | 3278-PP-OF-064 | AD214-026-G-01817 | 1 | 1 | SUBMITTED | CSE-OF-3278-001 | 2016-03-03 | 3278-NPCC-AO-T-07054 | 2016-03-03 | AO-NPCC-TN-3864 | 2016-03-08 | B
|  |  |  | 2 | 1 | SUBMITTED | CSE-OF-3278-005 | 2016-05-11 | 3278-NPCC-AO-T-07675 | 2016-05-23
|  |  |  | 3 | 1 | SUBMITTED | CSE-OF-3278-006 | 2016-06-07 | 3278-NPCC-AO-T-07750 | 2016-06-07 | AO-NPCC-TN-4279 | 2016-06-28 | A
6 | MOORING ANALYSIS AT TA PLATFORM | 3278-PP-OF-065 | AD214-026-G-01818 | 1 | 1 | SUBMITTED | CSE-OF-3278-003 | 2016-03-28 | 3278-NPCC-AO-T-07246 | 2016-03-28 | AO-NPCC-TN-4107 | 2016-05-10 | B
|  |  |  | 2 | 1 | SUBMITTED | CSE-OF-3278-017 | 2016-12-07 | 3278-NPCC-AO-T-08321 | 2016-12-08
|  |  |  | 3 | 1 | SUBMITTED | CSE-OF-3278-018 | 2016-12-15 | 3278-NPCC-AO-T-08338 | 2016-12-18 | AO-NPCC-TN-4519 | 2016-12-19 | A
7 | MOORING ANALYSIS DURING TAE DECK INSTALLATION | 3278-PP-OF-068 | AD214-026-G-01821 | 1 | 1 | SUBMITTED | CSE-OF-3278-010 | 2016-08-21 | 3278-NPCC-AO-T-08049 | 2016-08-22 | AO-NPCC-TN-4381 | 2016-08-23 | B
8 | SEP-250 MOORING ANALYSIS AT S7 | 3278-PP-OF-075 | AD214-026-G-01828 | 1 | 1 | SUBMITTED | CSE-OF-3278-007 | 2016-06-09 | 3278-NPCC-AO-T-07769 | 2016-06-12 | AO-NPCC-TN-4279 | 2016-06-28 | A
9 | MOORING ANALYSIS ABK TABLE TOP INSTALLATION | 3278-PP-OF-089 | AD214-026-G-1842 | 1 | 1 | SUBMITTED | CSE-OF-3278-011 | 2016-08-28 | 3278-NPCC-AO-T-08074 | 2016-08-29
|  |  |  | 2 | 1 | SUBMITTED | CSE-OF-3278-012 | 2016-09-07 | 3278-NPCC-AO-T-08125 | 2016-09-07 | AO-NPCC-TN-4461 | 2016-10-23 | A
10 | MOORING ANALYSIS OF SEP-650 AT WIP | 3278-PP-OF-092 | AD214-026-G-01845 | 1 | 1 | SUBMITTED | CSE-OF-3278-013 | 2016-09-28 | 3278-NPCC-AO-T-08175 | 2016-09-28 | AO-NPCC-TN-4489 | 2016-11-10 | A
|  |  |  | 2 | 1 | SUBMITTED | CSE-OF-3278-016 | 2016-11-29 | 3278-NPCC-AO-T-08305 | 2016-11-29 | AO-NPCC-TN-4512 | 2016-12-14 | A
|  |  |  | 3 | 1 | SUBMITTED | CSE-OF-3278-022 | 2017-07-16 | 3278-NPCC-AO-T-08645 | 2017-07-17 | AO-NPCC-TN-4725 | 2017-07-23 | A
11 | MOORING ANALYSIS OF SEP-650 AT B14 | 3278-PP-OF-093 | AD214-026-G-01846 | 1 | 1 | SUBMITTED | CSE-OF-3278-014 | 2016-09-29 | 3278-NPCC-AO-T-08180 | 2016-09-29 | AO-NPCC-TN-4438 | 2016-10-04 | B
|  |  |  | 2 | 1 | SUBMITTED | CSE-OF-3278-015 | 2016-10-12 | 3278-NPCC-AO-T-08270 | 2016-10-17 | AO-NPCC-TN-4461 | 2016-10-23 | A
12 | MOORING ANALYSIS OF WORKBOAT AT B14/NGTP | 3278-PP-OF-115 | AD214-026-G-01868 | 1 | 1 | SUBMITTED | CSE-OF-3278-020 | 2017-05-18 | 3278-NPCC-AO-T-08569 | 2017-05-18 | [6 empty] | MDDXB 5092-MD-70-473-01 | 2017-05-22 | COMMENTED
|  |  |  | 2 | 1 | SUBMITTED | CSE-OF-3278-021 | 2017-05-25 | 3278-NPCC-AO-T-08583 | 2017-05-25 | AO-NPCC-TN-4683 | 2017-06-06 | A
|  |  |  | 3 | 1 | SUBMITTED | CSE-OF-3278-024 | 2017-09-28 | 3278-NPCC-AO-T-08724 | 2017-09-28 | AO-NPCC-TN-4772 | 2017-10-04 | A
13 | MOORING ANALYSIS OF SEP 650 AT US-58 | 3278-PP-OF-122 | AD214-026-G-01875 | 1 | 1 | SUBMITTED | CSE-OF-3278-023 | 2017-07-23 | 3278-NPCC-AO-T-08652 | 2017-07-23 | AO-NPCC-TN-4771 | 2017-09-26 | A
14 | MOORING ANALYSIS OF JB-118 AT HAP | 3278-PP-OF-131 | AD214-026-G-01884 | 1 | 1 | SUBMITTED | CSE-OF-3278-025 | 2017-10-11 | 3278-NPCC-AO-T-08747 | 2017-10-11 | AO-NPCC-TN-4776 | 2017-10-11 | C
|  |  |  | 2 | 1 | SUBMITTED | CSE-OF-3278-026 | 2017-10-12 | 3278-NPCC-AO-T-08750 | 2017-10-15 | AO-NPCC-TN-4802 | 2017-12-14 | A
15 | MOORING ANALYSIS FOR SEP-350 AT ABK | 3278-PP-OF-135 | AD214-026-G-01888 | 1 | 1 | SUBMITTED | CSE-OF-3278-027 | 2017-11-09 | 3278-NPCC-AO-T-08772 | 2017-11-13 | AO-NPCC-TN-4795 | 2017-11-23 | D
|  |  |  | 2 | 1 | SUBMITTED | CSE-OF-3278-029 | 2018-01-09 | 3278-NPCC-AO-T-08810 | 2018-01-10 | AO-NPCC-TN-4827 | 2018-02-04 | A
16 | MOORING ANALYSIS OF WORKBOAT AT B11 BRIDGE | 3278-PP-OF-139 | AD214-026-G-01892 | 1 | 1 | SUBMITTED | CSE-OF-3278-028 | 2017-12-31 | 3278-NPCC-AO-T-08802 | 2018-01-02 | AO-NPCC-TN-4811 | 2018-01-03 | A
17 | MOORING ANALYSIS FOR SEP-650 AT SOUTH OF US58 | 3278-PP-OF-141 | AD214-026-G-01894 | 1 | 1 | SUBMITTED | CSE-OF-3278-030 | 2018-01-10 | 3278-NPCC-AO-T-08816 | 2018-01-11
|  |  |  | 2 | 1 | SUBMITTED | CSE-OF-3278-031 | 2018-01-18 | 3278-NPCC-AO-T-08825 | 2018-01-18 | AO-NPCC-TN-4827 | 2018-02-04 | A
18 | MOORING ANALYSIS FOR SEP-650 AT ABK | 3278-PP-OF-148 | AD214-26-G-01600 | 1 | 1 | SUBMITTED | CSE-OF-3278-032 | 2018-04-22 | 3278-NPCC-AO-T-08929 | 2018-04-22
19 | MOORING ANALYSIS FOR SEP-150 AT US-58 | 3278-PP-OF-154 | AD214-26-G-01606 | 1 | 1 | SUBMITTED | CSE-OF-3278-033 | 2018-08-07 | 3278-NPCC-AO-T-09003 | 2018-08-08
20 | MOORING ANALYSIS FOR SEP-150 AT TAE DECK | 3278-PP-OF-155 | AD214-26-G-01607 | 1 | 1 | SUBMITTED | CSE-OF-3278-034 | 2018-08-14 | 3278-NPCC-AO-T-09012 | 2018-08-15
DOCUMENT CLASS : (1) ISSUED FOR COMMENTS & APPROVAL (2) ISSUED FOR CONSTRUCTION (3) ISSUED FOR INFORMATION
ADMA-OPCO APPROVAL CODE : (A)APPROVED; (B) GENERALLY ACCEPTABLE ,INCORPORATE COMMENTS & RE-SUBMIT; (C)NOT ACCEPTABLE; (D) FOR INFORMATION

## Drawings
Client : ADMA-OPCO
ADDITIONAL GAS SUPPLY TO ONSHORE AND FLEXIBILITY ASSURANCE AT USSC.
Project 3278
OFFSHORE CONSTRUCTION ENGINEERING DRAWINGS
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC | [5 empty] | ADMA-OPCO |  |  | TPA (BV) |  |  | MWS (GM) |  |  | REMARKS
[7 empty] | SUBMISSION STATUS | [5 empty] | APPROVAL STATUS |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | OFF TO PMT |  | PMT TO ADMA OPCO
[7 empty] | REF | DATE | REF | DATE | REF | DATE | REF | DATE | CODE | REF | DATE | CODE | REF | DATE | CODE
1 | UMM SHAIF BST-S7 JACKET MODIFICATION J-TUBE INSTALLATION DRAWING AT BST (S7) | 3278-OFF-9799 | AD214-521-C-79799 | 0 | 2 |  |  |  | CSE-OF-3278-002 | 2016-03-08
2 | UMM SHAIF US-88 JACKET MODIFICATION J-TUBE INSTALLATION DRAWING AT US-88 | 3278-OFF-9800 | AD214-521-C-79800 | 0 | 2 |  |  |  | CSE-OF-3278-002 | 2016-03-08
3 | UMM SHAIF US-216 JACKET MODIFICATION J-TUBE INSTALLATION DRAWING AT US-216 | 3278-OFF-9801 | AD214-521-C-79801 | 0 | 2 |  |  |  | CSE-OF-3278-002 | 2016-03-08
|  |  |  | 1 | 2 |  |  |  | CSE-OF-3278-008 | 2016-07-03
4 | UMM SHAIF US-218 JACKET MODIFICATION J-TUBE INSTALLATION DRAWING AT US-218 | 3278-OFF-9802 | AD214-521-C-79802 | 0 | 2 |  |  |  | CSE-OF-3278-002 | 2016-03-08
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADMA-OPCO APPROVAL CODE : (1) REJECTED; (2) COMMENTED - WORK MAY PROCEED; (3) APPROVED; (4) FOR INFORMATION
MWS APPROVAL CODE : (A) ACCEPTED WITHOUT COMMENTS; (B) ACCEPTED SUBJECT TO COMMENTS; (C) NOT ACCEPTED; (D) INFORMATION ONLY

## Available Numbers (hidden)
NPCC Numbers | Available numbers | All numbers are subject to changed as per document and its location
2272-NN-RP-0501 | AD178-201-G-09497 | AD178-27/216-G-09497 | AD178-27/216-G-09189
2272-NN-RP-0502 | AD178-201-G-09498 | AD178-27/216-G-09498
2272-NN-RP-0503 | AD178-201-G-09499 | AD178-27/216-G-09499
2272-NN-1144 | AD178-201-G-09500 | AD178-27/216-G-09500
2272-NN-1145 | AD178-201-G-09501 | AD178-27/216-G-09501
2272-NN-1146 | AD178-201-G-09502 | AD178-27/216-G-09502
2272-NN-1147 | AD178-201-G-09503 | AD178-27/216-G-09503
2272-NN-1148 | AD178-201-G-09504 | AD178-27/216-G-09504
2272-NN-1149 | AD178-201-G-09505 | AD178-27/216-G-09505
2272-NN-1150 | AD178-201-G-09506 | AD178-27/216-G-09506
2272-NN-1151 | AD178-201-G-09507 | AD178-27/216-G-09507
2272-NN-1152 | AD178-201-G-09508 | AD178-27/216-G-09508
2272-NN-1153 | AD178-201-G-09509 | AD178-27/216-G-09509
2272-NN-1154 | AD178-201-G-09510 | AD178-27/216-G-09510
2272-NN-1155 | AD178-201-G-09511 | AD178-27/216-G-09511
2272-NN-1156 | AD178-201-G-09512 | AD178-27/216-G-09512
2272-NN-1157 | AD178-201-G-09513 | AD178-27/216-G-09513
2272-NN-1158 | AD178-201-G-09514 | AD178-27/216-G-09514
2272-NN-1159 | AD178-201-G-09515 | AD178-27/216-G-09515
2272-NN-1160 | AD178-201-G-09516 | AD178-27/216-G-09516
2272-NN-1161 | AD178-201-G-09517 | AD178-27/216-G-09517
2272-NN-1162 | AD178-201-G-09518 | AD178-27/216-G-09518
2272-NN-1163 | AD178-201-G-09519 | AD178-27/216-G-09519
2272-NN-1164 | AD178-201-G-09520 | AD178-27/216-G-09520
2272-NN-1165 | AD178-201-G-09521 | AD178-27/216-G-09521
2272-NN-1166 | AD178-201-G-09522 | AD178-27/216-G-09522
2272-ZZ-RP-3504 | AD178-201-G-09523 | AD178-327-G-09523
2272-ZZ-RP-3505 | AD178-201-G-09524 | AD178-559/498-G-09524
2272-ZZ-RP-3506 | AD178-201-G-09525 | AD178-496-G-09525
2272-ZZ-RP-3507 | AD178-201-G-09526 | AD178-498-G-09526
2272-ZZ-RP-3508 | AD178-201-G-09527 | AD178-560-G-09527
2272-ZZ-RP-3509 | AD178-201-G-09528 | AD178-559-G-09528
2272-ZZ-RP-3510 | AD178-201-G-09529 | AD178-560-G-09529
2272-ZZ-RP-3511 | AD178-201-G-09530 | AD178-558-G-09530
2272-ZZ-RP-3512 | AD178-201-G-09531 | AD178-557-G-09531
2272-ZZ-RP-3513 | AD178-201-G-09532 | AD178-557-G-09532
2272-ZZ-RP-3514 | AD178-201-G-09533 | AD178-558-G-09533
2272-ZZ-RP-3515 | AD178-201-G-09534 | AD178-561-G-09534
2272-ZZ-RP-3516 | AD178-201-G-09535 | AD178-561-G-09535
2272-ZZ-RP-3517 | AD178-201-G-09536 | AD178-496-G-09536
2272-NN-0247 |  | AD178-27/216-G-09537
2272-NN-RP-0504 | AD178-201-G-09538 | AD178-27/216-G-09538
2272-NN-RP-0505 | AD178-201-G-09539 | AD178-27/216-G-09539
2272-NN-RP-0506 | AD178-201-G-09540 | AD178-27/216-G-09540
2272-NN-RP-0507 | AD178-201-G-09541 | AD178-27/216-G-09541
2272-NN-RP-0508 | AD178-201-G-09542 | AD178-27/216-G-09542
2272-NN-RP-0509 | AD178-201-G-09543 | AD178-27/216-G-09543
2272-ZZ-RP-1604 |  | AD178-27/216-G-09544
2272-ZZ-RP-3004 |  | AD178-27/216-G-09545
2272-NN-RP-0601 |  | AD178-27/216-G-09546
2272-NN-0214 |  | AD178-27/2161-G-09547
2272-NN-RP-0701 |  | AD178-27/2161-G-09548
2272-NN-0233 |  | AD178-27/2161-G-09549
2272-NN-RP-0304 |  | AD178-27/2161-G-09550
2272-NN-0234 |  | AD178-27/2161-G-09551
2272-NN-0235 |  | AD178-27/2161-G-09552
2272-NN-0236 |  | AD178-27/2161-G-09553
2272-NN-0237 |  | AD178-27/2161-G-09554
2272-NN-0238 |  | AD178-27/2161-G-09555
2272-NN-0239 |  | AD178-27/2161-G-09556
2272-NN-5049 |  | AD178-27/2161-G-09557
2272-NN-RP-0510 |  | AD178-27/2161-G-09558
2272-NN-RP-0511 |  | AD178-27/2161-G-09559
2272-NN-0246 |  | AD178-27/2161-G-09560
2272-NN-RP-0512 |  | AD178-27/2161-G-09561
2272-NN-0248 |  | AD178-27/2161-G-09562
2272-NN-0249 |  | AD178-27/216-G-09563
2272-NN-0250 |  | AD178-27/216-G-09564
2272-NN-RP-2005 |  | AD178-27/216-G-09565
2272-NN-0501 |  | AD178-27/216-G-09566
2272-NN-RP-2905 |  | AD178-27/216-G-09567
2272-NN-0502 |  | AD178-27/216-G-09568
2272-NN-RP-2305 |  | AD178-27/216-G-09569
2272-NN-3506 |  | AD178-27/216-G-09570
2272-NN-RP-2205 |  | AD178-27/216-G-09571
2272-NN-0503 |  | AD178-27/216-G-09572
2272-NN-0504 |  | AD178-27/216-G-09573
2272-NN-0240 |  | AD178-27/216-G-09574
2272-ZZ-RP-3519 |  | AD178-335-G-09575
AD178-201-G-09576
AD178-201-G-09577
AD178-201-G-09578
AD178-201-G-09579
AD178-201-G-09580
AD178-201-G-09581
AD178-201-G-09582
AD178-201-G-09583
AD178-201-G-09584
AD178-201-G-09585
AD178-201-G-09586
AD178-201-G-09587
AD178-201-G-09588
AD178-201-G-09589
AD178-201-G-09590
AD178-201-G-09591
AD178-201-G-09592
AD178-201-G-09593
AD178-201-G-09594
AD178-201-G-09595
AD178-201-G-09596
AD178-201-G-09597
AD178-201-G-09598
AD178-201-G-09599
AD178-201-G-09600
AD178-201-G-09601
AD178-201-G-09602
AD178-201-G-09603
AD178-201-G-09604
AD178-201-G-09605
AD178-201-G-09606
AD178-201-G-09607
AD178-201-G-09608
AD178-201-G-09609
AD178-201-G-09610
AD178-201-G-09611
AD178-201-G-09612
AD178-201-G-09613
AD178-201-G-09614
AD178-201-G-09615
AD178-201-G-09616
AD178-201-G-09617
AD178-201-G-09618
AD178-201-G-09619
AD178-201-G-09620
AD178-201-G-09621
AD178-201-G-09622
AD178-201-G-09623
AD178-201-G-09624
AD178-201-G-09625
AD178-201-G-09626
AD178-201-G-09627
AD178-201-G-09628
AD178-201-G-09629
AD178-201-G-09630
AD178-201-G-09631
AD178-201-G-09632
AD178-201-G-09633
AD178-201-G-09634
AD178-201-G-09635
AD178-201-G-09636
AD178-201-G-09637
AD178-201-G-09638
AD178-201-G-09639
AD178-201-G-09640
AD178-201-G-09641
AD178-201-G-09642
AD178-201-G-09643
AD178-201-G-09644
AD178-201-G-09645
AD178-201-G-09646
AD178-201-G-09647
AD178-201-G-09648
AD178-201-G-09649
AD178-201-G-09650
AD178-201-G-09651
AD178-201-G-09652
AD178-201-G-09653
AD178-201-G-09654
AD178-201-G-09655
AD178-201-G-09656
AD178-201-G-09657
AD178-201-G-09658
AD178-201-G-09659
AD178-201-G-09660
AD178-201-G-09661
AD178-201-G-09662
AD178-201-G-09663
AD178-201-G-09664
AD178-201-G-09665
AD178-201-G-09666
AD178-201-G-09667
AD178-201-G-09668
AD178-201-G-09669
AD178-201-G-09670
AD178-201-G-09671
AD178-201-G-09672
AD178-201-G-09673
AD178-201-G-09674
AD178-201-G-09675
AD178-201-G-09676
AD178-201-G-09677
AD178-201-G-09678
AD178-201-G-09679
AD178-201-G-09680
AD178-201-G-09681
AD178-201-G-09682
AD178-201-G-09683
AD178-201-G-09684
AD178-201-G-09685
AD178-201-G-09686
AD178-201-G-09687
AD178-201-G-09688
AD178-201-G-09689
AD178-201-G-09690
AD178-201-G-09691
AD178-201-G-09692
AD178-201-G-09693
AD178-201-G-09694
AD178-201-G-09695
AD178-201-G-09696
AD178-201-G-09697
AD178-201-G-09698
AD178-201-G-09699

## Deleted Documents (hidden)
#REF! | MOORING ANALYSIS FOR BARGE DLB-1000 DURING DEMOLITION OF ZCSC OAP JACKET, TOPSIDE AND BRIDGE | 2272-ZZ-RP-3504 | AD178-327-G-09497 | 0 | 2 | 2015-05-26 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLB-1000 DURING INSTALLATION OF ZCSC BST-Q | 2272-ZZ-RP-3505 | AD178-559/498-G-09498 | 0 | 2 | 2015-05-16 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLB-1000 DURING INSTALLATION OF ZCSC CRP JACKET AND TOPSIDE | 2272-ZZ-RP-3506 | AD178-496-G-09499 | 0 | 2 | 2015-07-02 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLS-1000 DURING INSTALLATION OF BRIDGE BR (CRP - ZCSC CSP) | 2272-ZZ-RP-3507 | AD178-328-G-09500 | 0 | 2 | 2015-08-20 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLB-1000 DURING DEMOLITION OF EXISTING BRIDGE BS (ZK01 - ZCSC CSP) | 2272-ZZ-RP-3508 | AD178-329/328-G-09501 | 0 | 2 | 2015-06-26 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLB-1000 DURING INSTALLATION OF ZCSC BST JACKET & DECK | 2272-ZZ-RP-3509 | AD178-559-G-09502 | 0 | 2 | 2015-06-30 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLB-1000 DURING INSTALLATION OF NEW BRIDGE BS (ZK01 - ZCSC CSP) | 2272-ZZ-RP-3510 | AD178-329/328-G-09503 | 0 | 2 | 2015-07-05 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLB-1000 DURING INSTALLATION OF ZWSC BST-S8 & BST-S9 | 2272-ZZ-RP-3511 | AD178-558/558-G-09504 | 0 | 2 | 2015-08-09 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLB-1000 DURING INSTALLATION OF ZWSC RP1 JACKET | 2272-ZZ-RP-3512 | AD178-557-G-09505 | 0 | 2 | 2015-09-09 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLS-4200 DURING INSTALLATION OF ZWSC RP1 TOPSIDE | 2272-ZZ-RP-3513 | AD178-557-G-09506 | 0 | 2 | 2015-11-21 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLS-4200 DURING INSTALLATION OF BRIDGE B13A & B13B (ZWSC RP1 - CSP) | 2272-ZZ-RP-3514 | AD178-557/202-G-09507 | 0 | 2 | 2015-11-27 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLB-1000 DURING INSTALLATION OF ZWSC BST-S10 AND BST-S11 | 2272-ZZ-RP-3515 | AD178-561/561-G-09508 | 0 | 2 | 2015-11-30 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)
#REF! | MOORING ANALYSIS FOR BARGE DLS-4200 DURING INSTALLATION OF BRIDGE B14 (ZWSC RP - CSP) | 2272-ZZ-RP-3516 | AD178-201/202-G-09509 | 0 | 2 | 2015-12-07 | Deleted as per email from Ayman Moh'd El Sherif (NPCC)

## Sheet1 (hidden)
SR. NO. | RADIAL | PIPELINE | PIPELINE | DESCRIPTION | OFFSHORE START DATE | SUBMISSION PLANNED DATE FOR DRW | SUBMISSION PLANNED DATE FOR DOC
1 |  |  | PL-35 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-35 AT ZK29 | 2015-04-01 | 2014-12-01 | 2015-03-01
2 |  |  | PL-35 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-35 AT ZK280 | 2015-04-06 | 2014-12-07 | 2015-03-06
3 |  |  | PL-42 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-42 AT ZK158/76 | 2015-04-11 | 2014-11-15 | 2015-03-11
4 | RADIAL 24 | PL-42 | PL-41 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-41 AT ZK158/76 | 2015-04-11 | 2014-11-12 | 2015-03-11
5 |  |  | PL-10 | RISER/SPOOL LIFTING AND INSTALLATION FOR 8" OIL PIPELINE (PL-10) AT ZK300 | 2015-04-20 | 2014-11-07 | 2015-03-20
6 |  |  | PL-23 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-23 AT ZK47 | 2015-04-25 | 2015-01-19 | 2015-03-25
7 |  |  | PL-22 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-22 AT ZK290 | 2015-04-30 | 2015-02-11 | 2015-03-30
8 |  |  | PL-23 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-23 AT ZK290 | 2015-04-30 | 2015-01-13 | 2015-03-30
9 |  |  | PL-22 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-22 AT ZK167 | 2015-05-09 | 2015-02-04 | 2015-04-09
10 | RADIAL 153 | PL-20 | PL-7 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-7 AT ZK38 | 2015-05-14 | 2015-02-21 | 2015-04-14
11 |  |  | PL-31 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-31 AT ZK38 | 2015-05-14 | 2015-02-10 | 2015-04-14
12 |  |  | PL-31 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-31 AT ZK42 | 2015-05-20 | 2015-02-17 | 2015-04-20
13 |  |  | PL-14 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-14 AT ZK237 | 2015-05-26 | 2015-04-09 | 2015-04-26
14 |  |  | PL-15 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-15 AT ZK237 | 2015-05-26 | 2015-03-28 | 2015-04-26
15 | RADIAL 24 | PL-42 | PL-41 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-41 AT ZK24 | 2015-06-04 | 2015-05-17 | 2015-05-04
16 | RADIAL 88 | PL-4 | PL-7 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-7 AT ZCSC BST | 2015-06-11 | 2015-02-14 | 2015-05-11
17 |  |  | PL-42 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-42 AT ZCSC CRP | 2015-08-04 | 2015-05-17 | 2015-03-04
18 |  |  | PL-15 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-15 AT ZCSC CRP | 2015-08-04 | 2015-03-21 | 2015-07-04
19 |  |  | PL-13 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-13 AT ZCSC CRP | 2015-08-04 | 2015-05-25 | 2015-07-04
20 |  |  | PL-19 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-19 AT ZCSC CRP | 2015-08-04 | 2015-06-08 | 2015-07-04
21 |  |  | PL-14 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-14 AT ZK235 | 2015-09-07 | 2015-04-02 | 2015-08-07
22 |  |  | PL-13 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-13 AT ZK304 | 2015-09-12 | 2015-03-22 | 2015-08-12
23 |  |  | PL-12 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-12 AT ZK304 | 2015-09-12 | 2015-06-02 | 2015-08-12
24 |  |  | PL-12 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-12 AT ZK13 | 2015-09-22 | 2015-05-26 | 2015-08-22
25 |  |  | PL-11 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-11 AT ZK13 | 2015-09-22 | 2015-06-25 | 2015-08-22
26 |  |  | PL-11 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-11 AT ZK14 | 2015-10-02 | 2015-06-18 | 2015-09-02
27 |  |  | PL-19 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-19 AT ZK22 | 2015-10-07 | 2015-06-15 | 2015-09-07
28 | RADIAL 153 | PL-43 | PL-9 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-9 AT ZK22 | 2015-10-07 | 2015-09-22 | 2015-09-07
29 | RADIAL 50 | PL-44 | PL-9 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-9 AT ZK39 | 2015-10-16 | 2015-09-29 | 2015-09-16
30 | RADIAL 153 | PL-2 | PL-8 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE-8 AT ZK39 | 2015-10-16 | 2015-09-23 | 2015-09-16
31 | RADIAL 153 | PL-2 | PL-8 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE-8 AT ZK129 | 2015-10-25 | 2015-09-30 | 2015-09-25
32 | RADIAL 88 | PL-21 | PL-6 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-6 AT ZK329 | 2015-10-30 | 2015-10-09 | 2015-09-30
33 |  |  | PL-20 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-20 AT ZK153 | 2015-10-30 | 2015-11-22 | 2015-09-30
34 | RADIAL 237 | PL-15 | PL-3 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-3 AT ZK153 | 2015-10-30 | 2015-11-27 | 2015-09-30
35 |  |  | PL-43 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-43 AT ZK153 | 2015-10-30 | 2015-03-07 | 2015-09-30
36 | RADIAL 88 | PL-21 | PL-6 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-6 AT ZWSC RP1 | 2015-11-04 | 2015-10-02 | 2015-10-04
37 |  |  | PL-21 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-21 AT ZWSC RP1 | 2015-11-04 | 2015-11-01 | 2015-10-04
38 |  |  | PL-21 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-21 AT ZK88 | 2015-11-04 | 2015-11-08 | 2015-10-04
39 | RADIAL 22 | PL-8 | PL-5 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-5 AT ZK88 | 2015-11-04 | 2015-11-15 | 2015-10-04
40 |  |  | PL-20 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-20 AT ZWSC RP1 | 2015-11-04 | 2015-11-15 | 2015-10-04
41 | RADIAL 304 | PL-13 | PL-3 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-3 AT ZK293 | 2015-11-12 | 2015-12-04 | 2015-10-12
42 | RADIAL 38 | PL-31 | PL-2 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-2 AT ZK293 | 2015-11-12 | 2016-01-07 | 2015-10-12
43 | RADIAL 47 | PL-22 | PL-1 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-1 AT ZK293 | 2015-11-12 | 2015-12-08 | 2015-10-12
44 | RADIAL 22 | PL-9 | PL-5 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-5 AT ZK110 | 2015-11-14 | 2015-11-08 | 2015-10-14
45 | RADIAL 304 | PL-11 | PL-4 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-4 AT ZK110 | 2015-11-14 | 2015-10-18 | 2015-10-14
46 | RADIAL 304 | PL-11 | PL-4 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-4 AT ZK288 | 2015-11-24 | 2015-10-25 | 2015-10-24
47 | RADIAL 38 | PL-31 | PL-2 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-2 AT ZK189 | 2015-11-26 | 2015-12-30 | 2015-10-26
48 |  |  | PL-10 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-10 AT ZK20 | 2015-11-29 | 2015-10-13 | 2015-10-29
49 | RADIAL 47 | PL-23 | PL-1 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-1 AT ZK277 | 2015-12-01 | 2015-12-15 | 2015-11-01
50 |  |  | PL-43 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-43 AT ZK162 | 2015-12-06 | 2015-03-14 | 2015-11-06
51 |  |  | PL-44 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-44 AT ZK50 | 2015-12-11 |  | 2015-11-11
52 |  |  | PL-44 | RISER/SPOOL LIFTING AND INSTALLATION FOR PIPELINE PL-44 AT ZK44 | 2015-12-16 |  | 2015-11-16