## Documents - Pipeline & Cable
|  | ABU DHABI MARINE OPERATING COMPANY (ADMA-OPCO) | [12 empty] | NPCC DOC. No.:
|  | UMM LULU PACKAGE-1 FFD PROJECT | [12 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 3291 | [12 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [12 empty] | DATE : |  |  |  | 2015-11-17
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | REMAINING DAYS | NPCC |  |  |  | ADMA-OPCO |  |  | MATTHEWS DANIEL |  |  |  |  | REMARKS
[8 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[8 empty] | CSE TO PMT |  | PMT TO ADMA-OPCO |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[8 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPE STACKING ANALYSIS REPORT | 3291-NN-RP-001 | AD219-705-G-00401 | B | 2 | 2016-02-28 |  | 2016-03-01 | CSE-OF-3291-008 | 2016-03-02 | 3291-NPCC-PMT-AO-T-00919 | 2016-03-15 | 38-22701-N-T-04607 | 2 | 2016-03-29 | 3291-NPCC-MWS-T-0047
|  |  |  | 0 | 1 |  |  | 2016-03-24 | CSE-OF-3291-025 | 2016-03-28 | 3291-NPCC-PMT-AO-T-01011 | 2016-04-04 | 38-22701-N-T-04927 | 1 | 2016-03-29 | 3291-NPCC-MWS-T-0055
2 | PIPELAY INSTALLATION REPORT FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-RP-002 | AD219-486/492-G-00402 | B | 2 | 2016-03-12 |  | 2016-05-02 | CSE-OF-3291-048 | 2016-05-03 | 3291-NPCC-PMT-AO-T-01208 | 2016-05-10 | 38-22701-N-T-05605 | 2A | 2016-05-09 | 3291-NPCC-MWS-T-0107 | 2016-05-11 | MDDXB-5171-MD- 098-1851-01 | commented
|  |  |  | CRS | [10 empty] | 2016-05-12 | SENT BY E-MAIL
|  |  |  | 0 | 1 |  |  | 2016-05-12 | CSE-OF-3291-064 | 2016-05-15 | 3291-NPCC-PMT-AO-T-01249 | 2016-05-18 | 38-22701-N-T-05725 | 1 | 2016-05-15 | 3291-NPCC-MWS-T-0129 | 2016-05-12 | MDDXB-5171-MD-098-1851-02 | Accepted
3 | PIPELAY INSTALLATION REPORT FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-RP-003 | AD219-486/492-G-00403 | B | 2 | 2016-03-19 |  | 2016-05-09 | CSE-OF-3291-057 | 2016-05-10 | 3291-NPCC-PMT-AO-T-01233 | 2016-05-15 | 38-22701-N-T-05659 | 3 | 2016-05-10 | 3291-NPCC-MWS-T-0118 | 2016-05-11 | MDDXB-5171-MD-099-1854-01 | commented
|  |  |  | CRS | [10 empty] | 2016-05-12 | SENT BY E-MAIL | 2016-05-17 | MDDXB-5171-MD-099-1854-02 | Accepted
|  |  |  | C | 2 |  |  | 2016-05-18 | CSE-OF-3291-068 | 2016-05-18 | 3291-NPCC-PMT-AO-T-01274 | 2016-05-18 | 38-22701-P1-ADMA-NPCC-T-05728 | 2A | 2016-05-18 | 3291-NPCC-MWS-T-0136
|  |  |  | 0 | 1 |  |  | 2016-05-19 | CSE-OF-3291-072 | 2016-05-19 | 3291-NPCC-PMT-AO-T-01286 | 2016-05-29 | 38-22701-N-T-05808 | 1 | 2016-05-19 | 3291-NPCC-MWS-T-0140 | 2016-05-23 | MDDXB-5171-MD-099-1854-03 | Accepted
4 | PIPELAY INSTALLATION REPORT FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-RP-004 | AD219-494/493-G-00404 | B |  | 2016-03-25 |  | 2016-03-31 | CSE-OF-3291-032 | 2016-04-03 | 3291-NPCC-PMT-AO-T-01039 | 2016-04-10 | 38-22701-N-T-05052 | 2 | 2016-03-31 | 3291-NPCC-MWS-T-0062 | 2016-04-05 | MDDXB-5171-MD-051-1825-01 | commented
|  |  |  | CRS |  |  |  | 2016-04-12 | CRS(MWS) SENT TO PMT | [7 empty] | 2016-04-13 | MDDXB-5171-MD- 051-1825-02 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-11-08 | CSE-OF-3291-291 | 2016-11-09 | 3291-NPCC-PMT-AO-T-02146 | 2016-11-20 | 38-22701-N-T-07758 | 1 | 2016-11-09 | 3291-NPCC-MWS-T-0424 | 2016-11-22 | MDDXB-5171-MD-051-1825-03 | Accepted
5 | PIPELAY INSTALLATION REPORT FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-RP-005 | AD219-494/493-G-00405 | B | 2 | 2016-03-31 |  | 2016-03-30 | CSE-OF-3291-029 | 2016-03-30 | 3291-NPCC-PMT-AO-T-01032 | 2016-04-10 | 38-22701-N-T-05054 | 2 | 2016-03-31 | 3291-NPCC-MWS-T-0086 | 2016-04-05 | MDDXB-5171-MD-052-1826-01 | commented
|  |  |  | CRS |  |  |  | 2016-04-12 | CRS(MWS) SENT TO PMT | [7 empty] | 2016-04-13 | MDDXB-5171-MD-052-1826-02 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-05-02 | CSE-OF-3291-049 | 2016-05-03 | 3291-NPCC-PMT-AO-T-01209 | 2016-05-15 | 38-22701-N-T-05597 | 1 | 2016-05-09 | 3291-NPCC-MWS-T-0108 | 2016-05-09 | MDDXB-5171-MD-052-1826-03 | Accepted
6 | PIPELAY INSTALLATION REPORT FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-RP-006 | AD219-493/494-G-00406 | B | 2 | 2016-04-06 |  | 2016-03-30 | CSE-OF-3291-030 | 2016-03-31 | 3291-NPCC-PMT-AO-T-01036 | 2016-04-10 | 38-22701-N-T-05053 | 2 | 2016-03-31 | 3291-NPCC-MWS-T-0058 | 2016-04-05 | MDDXB-5171-MD-053-1828-01 | commented
|  |  |  | CRS |  |  |  | 2016-04-12 | CRS(MWS) SENT TO PMT
|  |  |  | 0 | 1 |  |  | 2016-05-02 | CSE-OF-3291-049 | 2016-05-03 | 3291-NPCC-PMT-AO-T-01209 | 2016-05-15 | 38-22701-N-T-05597 | 1 | 2016-05-09 | 3291-NPCC-MWS-T-0108 | 2016-05-10 | MDDXB-5171-MD-053-1828-02 | Accepted
7 | INSTALLATION ANALYSIS REPORT FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-RP-007 | AD219-485/488-G-00407 | B | 2 | 2016-04-12 |  | 2016-06-15 | CSE-OF-3291-103 | 2016-06-19 | 3291-NPCC-PMT-AO-T-01462 | 2016-06-30 | 38-22701-N-T-06308 | 3 | 2016-06-19 | 3291-NPCC-MWS-T-0180 | 2016-06-26 | MDDXB-5171-MD- 150-1896-01 | commented
|  |  |  | CRS |  |  |  | 2016-06-28 | CRS(MWS) SENT TO PMT
|  |  |  | C | 2 |  |  | 2016-07-11 | CSE-OF-3291-154 | 2016-07-12 | 3291-NPCC-PMT-AO-T-01582 | 2016-07-27 | 38-22701-N-T-06656 | 3 | 2016-07-12 | 3291-NPCC-MWS-T-0230 | 2016-07-19 | MDDXB-5171-MD-150-1896-02 | commented
|  |  |  | CRS |  |  |  | 2016-07-24 | CRS(MWS) SENT TO PMT | [7 empty] | 2016-07-24 | MDDXB-5171-MD-150-1896-03 | Accepted
|  |  |  | D | 2 |  |  | 2016-08-11 | CSE-OF-3291-221 | 2016-08-14 | 3291-NPCC-PMT-AO-T-01780 | 2016-08-22 | 38-22701-N-T-06964 | 1 | 07/08/2016 14/08/2016 | 3291-NPCC-MWS-T-0285 3291-NPCC-MWS-T-0301 | 2016-08-11 | MDDXB-5171-MD-150-1896-04 | Accepted
8 | INSTALLATION ANALYSIS REPORT FOR 6" WI PIPELINE FROM WHT-2 TO WHT-3 | 3291-NN-RP-008 | AD219-485/488-G-00408 | B | 2 | 2016-04-19 |  | 2016-05-30 | CSE-OF-3291-080 | 2016-05-31 | 3291-NPCC-PMT-AO-T-01371 | 2016-06-14 | 38-22701-N-T-06058 | 1 | 2016-05-31 | 3291-NPCC-MWS-T-0155 | 2016-06-26 | MDDXB-5171-MD- 149-1897-01 | Accepted
9 | INSTALLATION ANALYSIS REPORT FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-RP-009 | AD219-485/488-G-00409 | B | 2 | 2016-04-25 |  | 2016-06-02 | CSE-OF-3291-087 | 2016-06-02 | 3291-NPCC-PMT-AO-T-01393 | 2016-06-15 | 38-22701-N-T-06087 | 2 | 2016-06-02 | 3291-NPCC-MWS-T-0162 | 2016-06-16 | MDDXB-5171-MD- 142-1876-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-06-21 | CSE-OF-3291-115 | 2016-06-22 | 3291-NPCC-PMT-AO-T-01485 | 2016-07-14 | 38-22701-N-T-06423 | 1 | 2016-06-23 | 3291-NPCC-MWS-T-0191 | 2016-06-26 | MDDXB-5171-MD-142-1876-02 | Accepted
10 | INSTALLATION ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-RP-010 | AD219-486/485-G-00410 | B | 2 | 2016-05-01 |  | 2016-05-25 | CSE-OF-3291-075 | 2016-05-26 | 3291-NPCC-PMT-AO-T-01332 | 2016-06-08 | 38-22701-N-T-05995 | 3 | 2016-05-26 | 3291-NPCC-MWS-T-0148 | 2016-06-09 | MDDXB-5171-MD- 124-1871-01 | commented
|  |  |  | CRS | [10 empty] | 2016-06-12 | SENT BY E-MAIL
|  |  |  | C | 2 |  |  | 2016-06-21 | CSE-OF-3291-112 | 2016-06-22 | 3291-NPCC-PMT-AO-T-01480 | 2016-07-14 | 38-22701-N-T-06427 | 3
|  |  |  | D | 2 |  |  | 2016-07-17 | CSE-OF-3291-167 | 2016-07-18 | 3291-NPCC-PMT-AO-T-01627 | 2016-07-21 | 38-22701-N-T-06583 | 2 | 2016-07-18 | 3291-NPCC-MWS-T-0242 | 2016-07-19 | MDDXB-5171-MD-124-1871-02 | accepted
|  |  |  | E | 2 |  |  | 2016-07-21 | CSE-OF-3291-177 | 2016-07-26 | 3291-NPCC-PMT-AO-T-01655 | 2016-08-09 | 38-22701-N-T-06844 | 1 | 2016-07-26 | 3291-NPCC-MWS-T-0255 | 2016-07-31 | MDDXB-5171-MD-124-1871-03 | Accepted
11 | INSTALLATION ANALYSIS REPORT FOR 6" GL PIPELINE FROM WHT-9 TO NSMFT | 3291-NN-RP-011 | AD219-486/494-G-00411 | B | 2 | 2016-05-07 |  | 2016-04-06 | CSE-OF-3291-033 | 2016-04-07 | 3291-NPCC-PMT-AO-T-01053 | 2016-04-14 | 38-22701-N-T-05194 | 2 | 2016-04-27 | 3291-NPCC-MWS-T-0095 | 2016-04-28 | MDDXB-5171-MD-075-1839-01 | accepted
|  |  |  | 0 | 1 |  |  | 2016-05-03 | CSE-OF-3291-053 | 2016-05-09 | 3291-NPCC-PMT-AO-T-01217 | 2016-05-12 | 38-22701-N-T-05645 | 3 | 2016-05-09 | 3291-NPCC-MWS-T-0110 | 2016-05-10 | MDDXB-5171-MD-075-1839-02 | accepted
|  |  |  | 1 | 1 |  |  | 2016-10-20 | CSE-OF-3291-281 | 2016-10-23 | 3291-NPCC-PMT-AO-T-02099 | 2016-11-03 | 38-22701-N-T-07609 | 2A | 2016-10-23 | 3291-NPCC-MWS-T-0408 | 2016-10-27 | MDDXB-5171-MD-075-1839-03 | Accepted
|  |  |  | 2 | 1 |  |  | 2016-11-08 | CSE-OF-3291-291 | 2016-11-09 | 3291-NPCC-PMT-AO-T-02147 | 2016-11-20 | 38-22701-N-T-07759 | 1 | 2016-11-09 | 3291-NPCC-MWS-T-0425 | 2016-11-22 | MDDXB-5171-MD-075-1839-04 | Accepted
12 | INSTALLATION ANALYSIS REPORT FOR 8" WI PIPELINE FROM NSMFT TO WHT-9 | 3291-NN-RP-012 | AD219-486/494-G-00412 | B | 2 | 2016-05-14 |  | 2016-04-06 | CSE-OF-3291-034 | 2016-04-07 | 3291-NPCC-PMT-AO-T-01066 | 2016-04-14 | 38-22701-N-T-05196 | 2 | 2016-04-27 | 3291-NPCC-MWS-T-0094 | 2016-05-03 | MDDXB-5171-MD-080- 1843-01 | commented
|  |  |  | CRS |  |  |  | 2016-05-04 | CRS(MWS) SENT TO PMT | 2016-05-04 | ACK BY SHAHEER |  |  |  |  | 3291-NPCC-MWS-T-0094 | 2016-05-08 | MDDXB-5171-MD-080-1843-02 | accepted
|  |  |  | 0 | 1 |  |  | 2016-05-03 | CSE-OF-3291-054 | 2016-05-04 | 3291-NPCC-PMT-AO-T-01221 | 2016-05-10 | 38-22701-P1-ADMA-NPCC-T-05606 | 1 | 2016-05-09 | 3291-NPCC-MWS-T-0112 | 2016-05-11 | MDDXB-5171-MD-080-1843-03 | accepted
13 | INSTALLATION ANALYSIS REPORT FOR 14" WF PIPELINE FROM WHT-9 TO NSMFTT | 3291-NN-RP-013 | AD219-494/486-G-00413 | B | 2 | 2016-05-20 |  | 2016-03-31 | CSE-OF-3291-032 | 2016-04-03 | 3291-NPCC-PMT-AO-T-01039 | 2016-04-10 | 38-22701-N-T-05052 | 2 | 2016-03-31 | 3291-NPCC-MWS-T-0062 | 2016-04-05 | MDDXB-5171-MD-054-1829-01 | commented
|  |  |  | CRS |  |  |  | 2016-04-12 | CRS(MWS) SENT TO PMT | [7 empty] | 2016-04-28 | MDDXB-5171-MD-054-1829-02 | accepted
|  |  |  | 0 | 1 |  |  | 2016-04-27 | CSE-OF-3291-047 | 2016-05-03 | 3291-NPCC-PMT-AO-T-01167 | 2016-05-11 | 38-22701-P1-ADMA-NPCC-T-05609 | 3 | 2016-05-09 | 3291-NPCC-MWS-T-0106 | 2016-05-10 | MDDXB-5171-MD-054-1829-03 | accepted
|  |  |  | 1 | 1 |  |  | 2016-10-20 | CSE-OF-3291-281 | 2016-10-23 | 3291-NPCC-PMT-AO-T-02098 | 2016-11-03 | 38-22701-N-T-07613 | 2A | 2016-10-23 | 3291-NPCC-MWS-T-0407 | 2016-10-27 | MDDXB-5171-MD-054-1829-04 | Accepted | REV.0,1 & 2 ALL WITH- DRAW ON 17/11/2016. (EMAIL DTD. 17/11)
|  |  |  | 2 | 1 | REMARKS |  | 2016-11-08 | CSE-OF-3291-291 | 2016-11-09 | 3291-NPCC-PMT-AO-T-02148 |  |  |  | 2016-11-09 | 3291-NPCC-MWS-T-0426 | 2016-11-22 | MDDXB-5171-MD-054-1829-05 | Accepted
14 | INSTALLATION ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-RP-014 | AD219-486/491-G-00414 | B |  | 2016-05-27 |  | 2016-05-03 | CSE-OF-3291-052 | 2016-05-03 | 3291-NPCC-PMT-AO-T-01213 | 2016-05-15 | 38-22701-N-T-05594 | 2 | 2016-05-09 | 3291-NPCC-MWS-T-0113 | 2016-05-11 | MDDXB-5171-MD-101-1852-01 | commented
|  |  |  | CRS | [10 empty] | 2016-05-12 | SENT BY E-MAIL
|  |  |  | 0 | 1 |  |  | 2016-05-22 | CSE-OF-3291-073 | 2016-05-23 | 3291-NPCC-PMT-AO-T-01294 | 2016-06-05 | 38-22701-N-T-05945 | 2 | 2016-05-23 | 3291-NPCC-MWS-T-0143 | 2016-05-25 | MDDXB-5171-MD-101-1852-02 | commented
|  |  |  | 1 | 1 |  |  | 2016-10-19 | CSE-OF-3291-280 | 2016-10-20 | 3291-NPCC-PMT-AO-T-02094 | 2016-11-01 | 38-22701-N-T-07611 | 1 | 2016-10-20 | 3291-NPCC-MWS-T-0403
15 | INSTALLATION ANALYSIS REPORT FOR 6" WI PIPELINE FROM NSMFT TO WHT-6 | 3291-NN-RP-015 | AD219-486/491-G-00415 | B | 2 | 2016-06-03 |  | 2016-04-14 | CSE-OF-3291-040 | 2016-04-17 | 3291-NPCC-PMT-AO-T-01110 | 2016-04-26 | 38-22701-N-T-05383 | 2 | 2016-04-27 | 3291-NPCC-MWS-T-0080 | 2016-05-03 | MDDXB-5171-MD- 078-1841-01 | accepted
|  |  |  | 0 | 1 |  |  | 2016-06-01 | CSE-OF-3291-086 | 2016-06-02 | 3291-NPCC-PMT-AO-T-01388 | 2016-06-14 | 38-22701-N-T-06060 | 1 | 2016-06-02 | 3291-NPCC-MWS-T-0160 | 2016-06-14 | MDDXB-5171-MD-078-1841-02 | accepted
16 | INSTALLATION ANALYSIS REPORT FOR 6" GL PIPELINE FROM NSMFT TO WHT-6 | 3291-NN-RP-016 | AD219-486/491-G-00416 | B | 2 | 2016-06-09 |  | 2016-04-07 | CSE-OF-3291-036 | 2016-04-10 | 3291-NPCC-PMT-AO-T-01076 | 2016-04-14 | 38-22701-N-T-05195 | 2 | 2016-04-27 | 3291-NPCC-MWS-T-0083 | 2016-05-03 | MDDXB-5171-MD-079- 1842-01 | commented
|  |  |  | CRS |  |  |  | 2016-05-04 | CRS(MWS) SENT TO PMT | 2016-05-04 | ACK BY SHAHEER |  |  |  |  | 3291-NPCC-MWS-T-0083 | 2016-05-04 | MDDXB-5171-MD-079-1842-02 | accepted
|  |  |  | 0 | 1 |  |  | 2016-05-03 | CSE-OF-3291-051 | 2016-05-04 | 3291-NPCC-PMT-AO-T-01211 | 2016-05-15 | 38-22701-N-T-05598 | 1 | 2016-05-09 | 3291-NPCC-MWS-T-0111 | 2016-05-10 | MDDXB-5171-MD-079-1842-03 | accepted
|  |  |  | 1 | 1 |  |  | 2016-06-01 | CSE-OF-3291-084 | 2016-06-02 | 3291-NPCC-PMT-AO-T-01383 | 2016-06-14 | 38-22701-N-T-06061 | 3 | 2016-06-02 | 3291-NPCC-MWS-T-0159 | 2016-06-14 | MDDXB-5171-MD-079-1842-04 | accepted
|  |  |  | 2 | 1 |  |  | 2016-06-21 | CSE-OF-3291-113 | 2016-06-22 | 3291-NPCC-PMT-AO-T-01483 | 2016-07-14 | 38-22701-N-T-06424 | 1 | 2016-06-23 | 3291-NPCC-MWS-T-0189 | 2016-06-28 | MDDXB-5171-MD-079-1842-05 | accepted
17 | INSTALLATION ANALYSIS REPORT FOR 6" GL P/L FROM WHT-5 TO NSMFT | 3291-NN-RP-017 | AD219-486/490-G-00417 | B | 2 | 2016-06-15 |  | 2016-05-18 | CSE-OF-3291-070 | 2016-05-18 | 3291-NPCC-PMT-AO-T-01277 | 2016-06-01 | 38-22701-N-T-05911 | 2 | 2016-05-18 | 3291-NPCC-MWS-T-0138 | 2016-05-25 | MDDXB-5171-MD- 110-1865-01 | accepted
|  |  |  | 0 | 1 |  |  | 2016-06-09 | CSE-OF-3291-093 | 2016-06-12 | 3291-NPCC-PMT-AO-T-01413 | 2016-06-26 | 38-22701-N-T-06230 | 1 | 2016-06-12 | 3291-NPCC-MWS-T-0168 | 2016-06-15 | MDDXB-5171-MD-110-1865-02 | accepted
18 | INSTALLATION ANALYSIS REPORT FOR 10" WI P/L FROM WHT-5 TO NSMFT | 3291-NN-RP-018 | AD219-486/490-G-00418 | B | 2 | 2016-06-22 |  | 2016-05-17 | CSE-OF-3291-067 | 2016-05-18 | 3291-NPCC-PMT-AO-T-01272 | 2016-06-01 | 38-22701-N-T-05910 | 2 | 2016-05-18 | 3291-NPCC-MWS-T-0135 | 2016-06-01 | MDDXB-5171-MD- 116-1864-01 | accepted
|  |  |  | 0 | 1 |  |  | 2016-06-09 | CSE-OF-3291-094 | 2016-06-13 | 3291-NPCC-PMT-AO-T-01416 | 2016-06-26 | 38-22701-N-T-06231 | 1 | 2016-06-13 | 3291-NPCC-MWS-T-0171 | 2016-06-19 | MDDXB-5171-MD-116-1864-02 | Accepted
19 | INSTALLATION ANALYSIS REPORT FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-RP-019 | AD219-490/486-G-00419 | B | 2 | 2016-06-29 |  | 2016-05-16 | CSE-OF-3291-065 | 2016-05-16 | 3291-NPCC-PMT-AO-T-01258 | 2016-05-30 | 38-22701-N-T-05887 | 3 | 2016-05-11 | 3291-NPCC-MWS-T-0133 | 2016-06-01 | MDDXB-5171-MD- 117-1862-01 | commented
|  |  |  | CRS | [10 empty] | 2016-06-02 | SENT BY E-MAIL
|  |  |  | 0 | 1 |  |  | 2016-06-01 | CSE-OF-3291-082 | 2016-06-02 | 3291-NPCC-PMT-AO-T-01381 | 2016-06-14 | 38-22701-N-T-06059 | 3 | 2016-06-02 | 3291-NPCC-MWS-T-0157 | 2016-06-09 | MDDXB-5171-MD- 117-1862-02 | Accepted
|  |  |  | 1 | 1 |  |  | 2016-06-21 | CSE-OF-3291-114 | 2016-06-22 | 3291-NPCC-PMT-AO-T-01484 | 2016-07-14 | 38-22701-N-T-06428 | 1 | 2016-06-23 | 3291-NPCC-MWS-T-0190 | 2016-06-27 | MDDXB-5171-MD-117-1862-03 | Accepted
20 | INSTALLATION ANALYSIS REPORT FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-RP-020 | AD219-489/490-G-00420 | B | 2 | 2016-07-07 |  | 2016-03-01 | CSE-OF-3291-010 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00928 | 2016-03-16 | 38-22701-N-T-04638 | 3 | 2016-03-29 | 3291-NPCC-MWS-T-0048
|  |  |  | C | 2 |  |  | 2016-03-23 | CSE-OF-3291-021 | 2016-03-23 | 3291-NPCC-PMT-AO-T-01007 | 2016-03-31 | 38-22701-N-T-04893 | 2 | 2016-03-29 | 3291-NPCC-MWS-T-0053 | 2016-04-03 | MDDXB-5171-MD-050-1833-01 | commented
|  |  |  | CRS |  |  |  | 2016-04-12 | CRS(MWS) SENT TO PMT
|  |  |  | 0 | 1 |  |  | 2016-05-09 | CSE-OF-3291-058 | 2016-05-10 | 3291-NPCC-PMT-AO-T-01234 | 2016-05-11 | 38-22701-N-T-05644 | 2 | 2016-05-10 | 3291-NPCC-MWS-T-0119 | 2016-05-16 | MDDXB-5171-MD-050-1833-02 | Accepted
|  |  |  | 1 | 1 |  |  | 2016-05-22 | CSE-OF-3291-074 | 2016-05-23 | 3291-NPCC-PMT-AO-T-01303 | 2016-05-29 | 38-22701-N-T-05809 | 2 | 2016-05-23 | 3291-NPCC-MWS-T-0144 | 2016-06-01 | MDDXB-5171-MD-050-1833-03 | commented
|  |  |  | CRS | [10 empty] | 2016-06-02 | SENT BY E-MAIL
|  |  |  | 2 | 1 |  |  | 2016-05-30 | CSE-OF-3291-081 | 2016-06-01 | 3291-NPCC-PMT-AO-T-01373 | 2016-06-13 | 38-22701-N-T-06057 | 1 | 2016-06-01 | 3291-NPCC-MWS-T-0156 | 2016-06-09 | MDDXB-5171-MD-050-1833-04 | accepted
21 | INSTALLATION ANALYSIS REPORT FOR 6" GL P/L FROM WHT-4 TO WHT-5 | 3291-NN-RP-021 | AD219-490/489-G-00421 | B | 2 | 2016-07-14 |  | 2016-05-08 | CSE-OF-3291-056 | 2016-05-09 | 3291-NPCC-PMT-AO-T-01228 | 2016-05-15 | 38-22701-N-T-05658 | 2A
|  |  |  | 0 | 1 |  |  | 2016-05-19 | CSE-OF-3291-071 | 2016-05-19 | 3291-NPCC-PMT-AO-T-01285 | 2016-05-29 | 38-22701-N-T-05807 | 1 | 2016-05-19 | 3291-NPCC-MWS-T-0139 | 2016-05-25 | MDDXB-5171-MD-112-1867-01 | Accepted
22 | INSTALLATION ANALYSIS REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-022 | AD219-490/489-G-00422 | B | 2 | 2016-07-20 |  | 2016-05-08 | CSE-OF-3291-056 | 2016-05-09 | 3291-NPCC-PMT-AO-T-01228 | 2016-05-15 | 38-22701-N-T-05658 | 2A
|  |  |  | 0 | 1 |  |  | 2016-05-19 | CSE-OF-3291-071 | 2016-05-19 | 3291-NPCC-PMT-AO-T-01285 | 2016-05-29 | 38-22701-N-T-05807 | 1 | 2016-05-19 | 3291-NPCC-MWS-T-0139 | 2016-05-25 | MDDXB-5171-MD-111-1866-01 | commented
|  |  |  | CRS | [10 empty] | 2016-05-25 | SENT BY E-MAIL
23 | INSTALLATION ANALYSIS REPORT FOR 16" MOL FROM DAS ISLAND TO NSMFT | 3291-NN-RP-023 | AD219-486-G-00423 | B | 2 | 2016-07-26 |  | 2016-08-01 | CSE-OF-3291-200 | 2016-08-02 | 3291-NPCC-PMT-AO-T-01719 | 2016-08-17 | 38-22701-N-T-06934 | 2 | 2016-08-02 | 3291-NPCC-MWS-T-0277 | 2016-08-18 | MDDXB-5171-MD- 233-1960-01 | commented
|  |  |  | CRS | [10 empty] | 2016-09-05 | SENT BY E-MAIL | 2016-09-05 | MDDXB-5171-MD-233-1960-02 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-08-29 | CSE-OF-3291-243 | 2016-08-30 | 3291-NPCC-PMT-AO-T-01870 | 2016-09-18 | 38-22701-N-T-07231 | 2 | 2016-08-30 | 3291-NPCC-MWS-T-0333
|  |  |  | 1 | 1 |  |  | 2016-09-22 | CSE-OF-3291-266 | 2016-09-25 | 3291-NPCC-PMT-AO-T-01978 | 2016-10-05 | 38-22701-N-T-07404 | 2 | 2016-09-25 | 3291-NPCC-MWS-T-0376 | 2016-09-26 | MDDXB-5171-MD-233-1960-03 | Aceepted
|  |  |  | 2 | 1 |  |  | 2016-10-06 | CSE-OF-3291-274 | 2016-10-06 | 3291-NPCC-PMT-AO-T-02037 | 2016-10-12 | 38-22701-N-T-07454 | 1 | 2016-10-06 | 3291-NPCC-MWS-T-0392 | 2016-10-09 | MDDXB-5171-MD-233-1960-04 | Aceepted
24 | INSTALLATION ANALYSIS REPORT FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-RP-024 | AD219-469/486-G-00424 | B | 2 | 2016-09-20 |  | 2016-06-28 | CSE-OF-3291-128 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01535 | 2016-07-24 | 38-22701-N-T-06536 | 2 | 2016-06-30 | 3291-NPCC-MWS-T-0204 | 2016-07-14 | MDDXB-5171-MD- 180-1917-01 | commented
|  |  |  | CRS | [10 empty] | 2016-07-17 | SENT BY E-MAIL
|  |  |  | 0 | 1 |  |  | 2016-07-26 | CSE-OF-3291-188 | 2016-07-27 | 3291-NPCC-PMT-AO-T-01681 | 2016-08-09 | 38-22701-N-T-06843 | 1 | 2016-07-27 | 3291-NPCC-MWS-T-0264 | 2016-08-07 | MDDXB-5171-MD-180-1917-02 | Accepted
25 | DAVIT LIFT ANALYSIS REPORTAT WHT-7 | 3291-NN-RP-025 | AD219-486/492-G-00425 | B | 2 | 2016-09-01 | See remarks | 2016-07-12 | CSE-OF-3291-155 | 2016-07-14 | 3291-NPCC-PMT-AO-T-01584 | 2016-07-28 | 38-22701-N-T-06678 | 1 | 2016-07-14 | 3291-NPCC-MWS-T-0231 | 2016-07-26 | MDDXB-5171-MD- 190-1937-01 | Accepted | previous title was 6in nsmft to wht-7
|  |  |  | 0 | 2 |  |  | 2017-03-26 | CSE-OF-3291-336 | 2017-03-27 | 3291-NPCC-PMT-AO-T-02620 | 2017-04-12 | 38-22701-N-T-09020 | 1 | 2017-03-27 | 3291-NPCC-MWS-T-0500 | 2017-03-27 | MDDXB-5171-MD-190-1937-02 | Accepted
26 | PIPELINE REPAIR REPORT FOR 6" GL P/L FROM NSMFT TO WHT-9 AT WHT-9 | 3291-NN-RP-026 | AD219-486/494-G-00426 | B | 2 | 2016-09-04 | yahia | 2016-10-03 | CSE-OF-3291-272 | 2016-10-04 | 3291-NPCC-PMT-AO-T-02022 | 2016-10-06 | 38-22701-N-T-07412 | 1 | 2016-10-04 | 3291-NPCC-MWS-T-0290 |  |  |  |  | DAVIT LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-7
27 | DAVIT LIFT ANALYSIS REPORT AT WHT-8 | 3291-NN-RP-027 | AD219-494/493-G-00427 | B | 2 | 2016-07-12 | See remarks | 2016-07-13 | CSE-OF-3291-157 | 2016-07-14 | 3291-NPCC-PMT-AO-T-01603 | 2016-07-28 | 38-22701-N-T-06677 | 1 | 2016-07-14 | 3291-NPCC-MWS-T-0233 | 2016-07-27 | MDDXB-5171-MD- 192-1938-01 | Accepted | previous title was 6in wht-8 to wht-9
|  |  |  | 0 | 1 |  |  | 2016-09-01 | CSE-OF-3291-246 | 2016-09-04 | 3291-NPCC-PMT-AO-T-01891 | 2016-09-21 | 38-22701-N-T-07286 | 1 | 2016-09-04 | 3291-NPCC-MWS-T-0337
|  |  |  | 1 | 1 |  |  | 2016-09-29 | CSE-OF-3291-271 | 2016-09-29 | 3291-NPCC-PMT-AO-T-02011 | 2016-10-06 | 38-22701-N-T-07413 | 1 | 2016-09-29 | 3291-NPCC-MWS-T-0385 | 2016-10-13 | MDDXB-5171-MD-192-1938-02 | Accepted
28 | DAVIT LIFT ANALYSIS REPORT AT WHT-9 | 3291-NN-RP-028 | AD219-494/493-G-00428 | B | 2 | 2016-07-15 |  | 2016-08-18 | CSE-OF-3291-230 | 2016-08-21 | 3291-NPCC-PMT-AO-T-01829 | 2016-09-01 | 38-22701-N-T-07106 | 2A | 2016-08-21 | 3291-NPCC-MWS-T-0319 | 2016-08-24 | MDDXB-5171-MD- 243-1974-01 | Accepted | previous title was 6in wi wht-8 to wht-9
|  |  |  | 0 | 1 |  |  | 2016-10-19 | CSE-OF-3291-280 | 2016-10-20 | 3291-NPCC-PMT-AO-T-02095 | 2016-11-01 | 38-22701-N-T-07610 | 1 | 2016-10-20 | 3291-NPCC-MWS-T-0404 | 2016-11-24 | MDDXB-5171-MD-243-1974-02 | Accepted
29 | PIPELINE LIFTING ANALYSIS FOR GROUTBAG INSTALLATION (16IN MOL DAS TO NSMFT) | 3291-NN-RP-029 | AD219-486-G-00429 | B | 2 | REZA |  | 2017-02-08 | CSE-OF-3291-313 | 2017-02-09 | 3291-NPCC-PMT-AO-T-02423 | 2017-02-22 | 38-22701-N-T-08538 | 2 | 2017-02-12 | 3291-NPCC-MWS-T-0464 | 2017-02-21 | MDDXB-5171-MD- 280-4421-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2017-06-19 | CSE-OF-3291-361 | 2017-06-20 | 3291-NPCC-PMT-AO-T-03022 | 2017-09-14 | 38-22701-N-T-10132 | 1 | 2017-06-20 | 3291-NPCC-MWS-T-0542 | 2017-07-20 | MDDXB-5171-MD-280-4421-02 | Accepted
30 | DAVIT LIFT ANALYSIS REPORT AT WHT-2 | 3291-NN-RP-030 | AD219-485-G-00430 | B | 2 | REZA | See remarks | 2017-01-22 | CSE-OF-3291-312 | 2017-01-22 | 3291-NPCC-PMT-AO-T-02372 | 2017-02-05 | 38-22701-N-T-08386 | 2A | 2017-01-22 | 3291-NPCC-MWS-T-0462 | 2017-02-20 | MDDXB-5171-MD- 278-4418-01 | Accepted | previous title was 12in wht-2 to wht-3
|  |  |  | 0 | 1 | REZA |  | 2017-03-22 | CSE-OF-3291-333 | 2017-03-23 | 3291-NPCC-PMT-AO-T-02605 | 2017-04-12 | 38-22701-N-T-09019 | 1 | 2017-03-23 | 3291-NPCC-MWS-T-0495
|  |  |  | 1 | 1 |  |  | 2017-03-26 | CSE-OF-3291-337 | 2017-03-27 | 3291-NPCC-PMT-AO-T-02625 | 2017-04-12 | 38-22701-N-T-09021 | 1 | 2017-03-27 | 3291-NPCC-MWS-T-0503 | 2017-03-29 | MDDXB-5171-MD-278-4418-02 | Accepted
31 | DAVIT LIFT ANALYSIS REPORT AT WHT-3 | 3291-NN-RP-031 | AD219-488-G-00431 | B | 2 | REZA | See remarks | 2017-05-17 | CSE-OF-3291-353 | 2017-05-17 | 3291-NPCC-PMT-AO-T-02848 | 2017-06-01 | 38-22701-N-T-09395 | 1 | 2017-05-18 | 3291-NPCC-MWS-T-0530 | 2017-05-31 | MDDXB-5171-MD-311-4447-01 | Accepted | previous title was 6in wht-2 to wht-3 all p/l
|  |  |  | 0 | 1 |  |  | 2017-11-07 | CSE-OF-3291-367 | 2017-11-08 | 3291-NPCC-PMT-AO-T-03449 | 2017-11-20 | 38-22701-N-T-10479 | 2 | 2017-11-07 | 3291-NPCC-MWS-T-0574 | 2017-11-13 | MDDXB-5171-MD-311-4447-02 | Accepted
|  |  |  | 1 | 1 |  |  | 2017-11-20 | CSE-OF-3291-372 | 2017-11-21 | 3291-NPCC-PMT-AO-T-03481 | 2017-12-06 | 38-22701-N-T-10537 | 2 | 2017-11-20 | 3291-NPCC-MWS-T-0580 | 2017-11-21 | MDDXB-5171-MD-311-4447-03 | Accepted
32 | PIPELINE LIFTING ANALYSIS FOR SLEEPER SHIFTING (WHT-2 TO WHT-3) | 3291-NN-RP-032 | AD219-485/488-G-00432 | B | 2 |  |  | 2016-11-24 | CSE-OF-3291-302 | 2016-11-27 | 3291-NPCC-PMT-AO-T-02208 | 2016-12-07 | 38-22701-N-T-07939 | 2A | 2016-11-27 | 3291-NPCC-MWS-T-0447 | 2016-12-14 | MDDXB-5171-MD- 274-4409-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-12-28 | CSE-OF-3291-309 | 2017-01-02 | 3291-NPCC-PMT-AO-T-02298 | 2017-01-12 | 38-22701-N-T-08200 | 1 | 2017-01-02 | 3291-NPCC-MWS-T-0458 | 2017-02-20 | MDDXB-5171-MD-274-4409-02 | Accepted
33 | 16" MOL SHIFTING TO ORIGINAL POSITION ANALYSIS | 3291-NN-RP-033 | AD219-705-G-00433 | B | 2 | REZA | 2016-11-21 | 2017-03-05 | CSE-OF-3291-321 | 2017-03-05 | 3291-NPCC-PMT-AO-T-02505 | 2017-03-19 | 38-22701-N-T-08732 | 1 | 2017-03-05 | 3291-NPCC-MWS-T-0478 | 2017-04-11 | MDDXB-5171-MD- 288-4430-01 | Accepted
34 | DAVIT LIFT ANALYSIS REPORT FOR AT NSMFT (EAST) | 3291-NN-RP-034 | AD219-486/494-G-00434 | B | 2 | 2016-09-10 | See remarks | 2016-07-13 | CSE-OF-3291-156 | 2016-07-14 | 3291-NPCC-PMT-AO-T-01598 | 2016-07-28 | 38-22701-N-T-06682 | 2 | 2016-07-14 | 3291-NPCC-MWS-T-0232 | 2016-07-26 | MDDXB-5171-MD- 191-1939-01 | Accepted | previous title was 6in NSMFT TO WHT-9
|  |  |  | 0 | 1 |  |  | 2016-08-08 | CSE-OF-3291-210 | 2016-08-09 | 3291-NPCC-PMT-AO-T-01758 | 2016-08-22 | 38-22701-N-T-06962 | 2 | 2016-08-09 | 3291-NPCC-MWS-T-0288 | 2016-08-14 | MDDXB-5171-MD-191-1939-02 | Accepted
|  |  |  | 1 | 1 |  |  | 2016-08-15 | CSE-OF-3291-225 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01800 | 2016-08-22 | 38-22701-N-T-06967 | 1 | 2016-08-16 | 3291-NPCC-MWS-T-0309 | 2016-08-22 | MDDXB-5171-MD-191-1939-03 | Accepted
35 | DAVIT LIFT ANALYSIS REPORT AT NSMFT (WEST) | 3291-NN-RP-035 | AD219-486/494-G-00435 | B | 2 | 2016-09-13 | See remarks | 2017-01-02 | CSE-OF-3291-310 | 2017-01-03 | 3291-NPCC-PMT-AO-T-02305 | 2017-01-18 | 38-22701-N-T-08237 | 2 | 2017-01-03 | 3291-NPCC-MWS-T-0459 | 2017-02-20 | MDDXB-5171-MD- 277-4415-01 | Accepted | previous title was 8in NSMFT TO WHT-9
|  |  |  | 0 | 1 |  |  | 2017-04-02 | CSE-OF-3291-346 | 2017-04-04 | 3291-NPCC-PMT-AO-T-02660 | 2017-04-12 | 38-22701-N-T-09023 | 2A | 2017-04-04 | 3291-NPCC-MWS-T-0514
36 | WELD REPAIR ANALYSIS | 3291-NN-RP-036 | AD219-705-G-00436 |  |  | 2016-10-26 | REZA
37 | DAVIT LIFT ANALYSIS REPORT FOR ALL PIPELINES AT WHT-6 | 3291-NN-RP-037 | AD219-486/491-G-00437 | B | 2 | 2016-09-08 | See remarks | 2016-06-28 | CSE-OF-3291-123 | 2016-06-29 | 3291-NPCC-PMT-AO-T-01526 | 2016-07-14 | 38-22701-N-T-06449 | 2 | 2016-06-29 | 3291-NPCC-MWS-T-0199 | 2016-07-17 | MDDXB-5171-MD- 186-1914-01 | Accepted | previous title was 10in nsmft to wht-6
|  |  |  | 0 | 1 |  |  | 2016-07-19 | CSE-OF-3291-174 | 21/07/2016 | 3291-NPCC-PMT-AO-T-01644 | 2016-07-31 | 38-22701-N-T-06702 | 1 | 2016-07-20 | 3291-NPCC-MWS-T-0250 | 2016-07-28 | MDDXB-5171-MD-186-1914-02 | Accepted
38 | SEA FASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON SEAWAYS-17 (TRIP-12) | 3291-NN-RP-038 | AD219-705-G-00438 | B | 2 | 2016-10-23 | SKM | 2016-10-24 | CSE-OF-3291-283 | 2016-10-24 | 3291-NPCC-PMT-AO-T-02106 | 2016-11-07 | 38-22701-N-T-07672 | 1 | 2016-10-24 | 3291-NPCC-MWS-T-0412
39 | PIPELINE REPAIR REPORT FOR 6" GL P/L FROM NSMFT TO WHT-6 AT WHT-6 | 3291-NN-RP-039 | AD219-486/491-G-00439 | B | 2 | Reza |  | 2016-08-11 | CSE-OF-3291-218 | 2016-08-11 | 3291-NPCC-PMT-AO-T-01777 | 2016-08-17 | 38-22701-N-T-06913 | 2 | 2016-08-11 | 3291-NPCC-MWS-T-0299 | 2016-08-17 | MDDXB-5171-MD- 232-1967-01 | Accepted | previous title was davit lift analysis 6" GL P/L NSMFT WHT-6
|  |  |  | 0 | 1 |  |  | 2016-10-19 | CSE-OF-3291-280 | 2016-10-20 | 3291-NPCC-PMT-AO-T-02096 | 2016-11-01 | 38-22701-N-T-07617 | 1 | 2016-10-20 | 3291-NPCC-MWS-T-0405 | 2016-11-24 | MDDXB-5171-MD-232-1967-02 | Accepted
40 | DAVIT LIFT ANALYSIS REPORT FOR AT WHT-5 | 3291-NN-RP-040 | AD219-486/490-G-00440 | B | 2 | 2016-08-25 | See remarks | 2016-06-28 | CSE-OF-3291-124 | 2016-06-29 | 3291-NPCC-PMT-AO-T-01528 | 2016-07-12 | 38-22701-N-T-06426 | 1 | 2016-06-29 | 3291-NPCC-MWS-T-0200 | 2016-07-14 | MDDXB-5171-MD- 181-1915-01 | Accepted | previous title was 6in nsmft to wht-5
41 | DAVIT LIFT ANALYSIS REPORT AT WHT-4 | 3291-NN-RP-041 | AD219-486/490-G-00441 | B | 2 | 2016-08-28 | See remarks | 2016-06-28 | CSE-OF-3291-125 | 2016-06-29 | 3291-NPCC-PMT-AO-T-01529 | 2016-07-12 | 38-22701-N-T-06422 | 1 | 2016-06-29 | 3291-NPCC-MWS-T-0201 | 2016-07-17 | MDDXB-5171-MD- 185-1913-01 | Accepted | previous title was 10in nsmft to wht-5
42 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON GAC-82 (TRIP-16) | 3291-NN-RP-042 | AD219-705-G-00442 | B | 2 | 2017-02-19 | SKM | 2017-02-20 | CSE-OF-3291-316 | 2017-02-21 | 3291-NPCC-PMT-AO-T-02462 | 2017-03-02 | 38-22701-N-T-08608 | 1 | 2017-02-21 | 3291-NPCC-MWS-T-0468
43 | DAVIT LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-043 | AD219-489/490-G-00443 | B | 2 | 2016-08-07 |  | 2016-06-09 | CSE-OF-3291-095 | 2016-06-13 | 3291-NPCC-PMT-AO-T-01422 | 2016-06-23 | 38-22701-N-T-06195 | 2 | [5 empty] | pls. see the documents nn-rp-040 & 041
44 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-044 | AD219-490/489-G-00444 | B | 2 | 2016-08-10 |  | 2016-06-08 | CSE-OF-3291-091 | 2016-06-09 | 3291-NPCC-PMT-AO-T-01407 | 2016-06-23 | 38-22701-N-T-06194 | 2 | 2016-06-12 | 3291-NPCC-MWS-T-0166 | 2016-06-16 | MDDXB-5171-MD- 143-1884-01 | Accepted | pls. see the documents nn-rp-040 & 041
45 | DAVIT LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-045 | AD219-490/489-G-00445 | B | 2 | 2016-08-13 |  | 2016-06-12 | CSE-OF-3291-096 | 2016-06-13 | 3291-NPCC-PMT-AO-T-01426 | 2016-06-26 | 38-22701-N-T-06196 | 2 | 2016-06-13 | 3291-NPCC-MWS-T-0174 |  |  |  | pls. see the documents nn-rp-040 & 041
46 | PIPELINE LIFTING ANALYSIS FOR SLEEPER SHIFTING (10" EGL NSMFT to USSC IGD-HAP) | 3291-NN-RP-046 | AD219-486/469-G-00446 | B | 2 | Reza |  | 2016-10-17 | CSE-OF-3291-277 | 2016-10-18 | 3291-NPCC-PMT-AO-T-02085 | 2016-11-06 | 38-22701-N-T-07657 | 2 | 2016-10-18 | 3291-NPCC-MWS-T-0400 | 2016-10-19 | MDDXB-5171-MD- 272-4404-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-11-09 | CSE-OF-3291-292 | 2016-11-09 | 3291-NPCC-PMT-AO-T-02150 | 2016-11-20 | 38-22701-N-T-07760 | 1 | 2016-11-09 | 3291-NPCC-MWS-T-0427 | 2016-11-24 | MDDXB-5171-MD-272-4404-02 | Accepted
|  |  |  | 1 | 1 |  |  | 2017-05-09 | CSE-OF-3291-351 | 2017-05-10 | 3291-NPCC-PMT-AO-T-02820 | 2017-05-25 | 38-22701-N-T-09342 | 1 | 2017-05-10 | 3291-NPCC-MWS-T-0528
|  |  |  | 2 | 1 |  |  | 2017-05-15 | CSE-OF-3291-352 | 2017-05-15 | 3291-NPCC-PMT-AO-T-02842 | 2017-05-25 | 38-22701-N-T-09341 | 1 | 2017-05-15 | 3291-NPCC-MWS-T-0529 | 2017-05-16 | MDDXB-5171-MD-272-4404-03 | Accepted
|  |  |  | 3 | 1 |  |  | 2017-07-24 | CSE-OF-3291-364 | 2017-07-25 | 3291-NPCC-PMT-AO-T-03215 | 2017-09-14 | 38-22701-N-T-10134 | 1 | 2017-07-25 | 3291-NPCC-MWS-T-0554 | 2017-07-26 | MDDXB-5171-MD-272-4404-04 | Accepted
47 | DAVIT LIFT ANALYSIS REPORT AT IGD-HAP | 3291-NN-RP-047 | AD219-469/486-G-00447 | B | 2 | 2016-10-16 | See remarks | 2016-09-08 | CSE-OF-3291-253 | 2016-09-14 | 3291-NPCC-PMT-AO-T-01919 |  |  |  | 2016-09-14 | 3291-NPCC-MWS-T-0353 |  |  |  | previous title was 10in export gas igd-hap to nsmft
|  |  |  | 0 | 1 |  |  | 2016-09-18 | CSE-OF-3291-259 | 2016-09-20 | 3291-NPCC-PMT-AO-T-01949 | 2016-10-03 | 38-22701-N-T-07372 | 2 | 2016-09-20 | 3291-NPCC-MWS-T-0363 | 2016-10-13 | MDDXB-5171-MD- 266-1985-01 | Accepted
|  |  |  | 1 | 1 |  |  | 2016-10-19 | CSE-OF-3291-280 | 2016-10-20 | 3291-NPCC-PMT-AO-T-02097 | 2016-11-01 | 38-22701-N-T-07614 | 1 | 2016-10-20 | 3291-NPCC-MWS-T-0406 | 2016-11-24 | MDDXB-5171-MD-266-1985-02 | Accepted
48 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-RP-048 | AD219-486/492-G-00448 | B | 2 | 2016-09-01 |  | 2016-06-16 | CSE-OF-3291-106 | 2016-06-21 | 3291-NPCC-PMT-AO-T-01468 | 2016-06-30 | 38-22701-N-T-06306 | 3 | 2016-06-21 | 3291-NPCC-MWS-T-0181 | 2016-06-27 | MDDXB-5171-MD-154-1898-01 | Accepted
|  |  |  | C | 2 |  |  | 2016-07-21 | CSE-OF-3291-176 | 2016-07-24 | 3291-NPCC-PMT-AO-T-01654 | 2016-08-04 | 38-22701-N-T-06759 | 2A | 2016-07-24 | 3291-NPCC-MWS-T-0254 | 2016-07-28 | MDDXB-5171-MD-154-1898-02 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-08-16 | CSE-OF-3291-226 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01808 | 2016-08-25 | 38-22701-N-T-07018 | 1 | 2016-08-16 | 3291-NPCC-MWS-T-0313 | 2016-08-22 | MDDXB-5171-MD-154-1898-03 | accepted
49 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-RP-049 | AD219-486/492-G-00449 | B | 2 | 2016-09-22 |  | 2016-08-10 | CSE-OF-3291-217 | 2016-08-11 | 3291-NPCC-PMT-AO-T-01775 | 2016-08-17 | 38-22701-N-T-06914 | 1 | 2016-08-11 | 3291-NPCC-MWS-T-0297 | 2016-08-21 | MDDXB-5171-MD- 236-1966-01 | Accepted
50 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-RP-050 | AD219-486/492-G-00450 | B | 2 | 2016-09-04 |  | 2016-06-13 | CSE-OF-3291-097 | 2016-06-15 | 3291-NPCC-PMT-AO-T-01433 | 2016-06-26 | 38-22701-N-T-06204 | 3 | 2016-06-15 | 3291-NPCC-MWS-T-0175
|  |  |  | C | 2 |  |  | 2016-06-28 | CSE-OF-3291-196 | 2016-06-28 | 3291-NPCC-PMT-AO-T-01701 | 2016-08-09 | 38-22701-N-T-06832 | 2A | 2016-07-28 | 3291-NPCC-MWS-T-0272 | 2016-08-04 | MDDXB-5171-MD- 210-1959-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-09-08 | CSE-OF-3291-254 | 2016-09-14 | 3291-NPCC-PMT-AO-T-01921 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-14 | 3291-NPCC-MWS-T-0355 | 2016-10-09 | MDDXB-5171-MD-210-1959-02 | Accepted
51 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-RP-051 | AD219-486/492-G-00451 | B | 2 | 2016-09-25 |  | 2016-08-09 | CSE-OF-3291-215 | 2016-08-10 | 3291-NPCC-PMT-AO-T-01770 | 2016-08-17 | 38-22701-N-T-06912 | 1 | 2016-08-10 | 3291-NPCC-MWS-T-0294 | 2016-08-14 | MDDXB-5171-MD- 230-1965-01 | Accepted
52 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-RP-052 | AD219-494/493-G-00452 | B | 2 | 2016-07-25 |  | 2016-08-21 | CSE-OF-3291-232 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01834 | 2016-09-04 | 38-22701-N-T-07108 | 1 | 2016-08-23 | 3291-NPCC-MWS-T-0322 | 2016-08-24 | MDDXB-5171-MD- 244-1976-01 | Accepted
53 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-RP-053 | AD219-494/493-G-00453 | B | 2 | 2016-07-12 |  | 2016-08-03 | CSE-OF-3291-204 | 2016-08-04 | 3291-NPCC-PMT-AO-T-01737 | 2016-08-11 | 38-22701-N-T-06871 | 2 | 2016-08-04 | 3291-NPCC-MWS-T-0281 | 2016-08-11 | MDDXB-5171-MD- 228-1961-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-10-20 | CSE-OF-3291-281 | 2016-10-23 | 3291-NPCC-PMT-AO-T-02100 | 2016-11-03 | 38-22701-N-T-07618 | 1 | 2016-10-23 | 3291-NPCC-MWS-T-0409 | 2016-10-27 | MDDXB-5171-MD-228-1961-02 | Accepted
54 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-RP-054 | AD219-494/493-G-00454 | B | 2 | 2016-07-28 |  | 2016-08-28 | CSE-OF-3291-240 | 2016-08-28 | 3291-NPCC-PMT-AO-T-01857 | 2016-09-04 | 38-22701-N-T-07104 | 1 | 2016-08-28 | 3291-NPCC-MWS-T-0330 | 2016-08-30 | MDDXB-5171-MD- 249-1979-01 | Accepted
55 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-RP-055 | AD219-494/493-G-00455 | B | 2 | 2016-07-15 |  | 2016-08-04 | CSE-OF-3291-205 | 2016-08-06 | 3291-NPCC-PMT-AO-T-01738 | 2016-08-17 | 38-22701-N-T-06911 | 1 | 2016-08-06 | 3291-NPCC-MWS-T-0282 | 2016-08-14 | MDDXB-5171-MD- 231-1962-01 | Accepted
56 | RISER LIFT ANALYSIS REPORT FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-8) | 3291-NN-RP-056 | AD219-493/494-G-00456 | B | 2 | 2016-07-18 |  | 2016-08-07 | CSE-OF-3291-209 | 2016-08-07 | 3291-NPCC-PMT-AO-T-01751 | 2016-08-17 | 38-22701-N-T-06915 | 1 | 2016-08-07 | 3291-NPCC-MWS-T-0287 | 2016-08-11 | MDDXB-5171-MD- 227-1963-01 | Accepted
57 | RISER LIFT ANALYSIS REPORT FOR 14" WF P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-RP-057 | AD219-493/494-G-00457 | B | 2 | 2016-08-01 |  | 2016-08-22 | CSE-OF-3291-234 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01839 | 2016-09-04 | 38-22701-N-T-07105 | 2A | 2016-08-23 | 3291-NPCC-MWS-T-0324 | 2016-08-24 | MDDXB-5171-MD- 245-1977-01 | commented | previous title was wht-8 to WHT-9 @ WHT-9
|  |  |  | CRS | [10 empty] | 2016-08-25 | SENT BY E-MAIL
|  |  |  | 0 | 1 |  |  | 2016-11-29 | CSE-OF-3291-303 | 2016-11-30 | 3291-NPCC-PMT-AO-T-02224 | 2016-12-08 | 38-22701-N-T-07941 | 1 | 2016-11-30 | 3291-NPCC-MWS-T-0449 | 2016-12-14 | MDDXB-5171-MD-245-1977-02 | Accepted
58 | RISER/SPOOL LIFT ANALYSIS REPORT FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-RP-058 | AD219-485/488-G-00458 | B | 2 | 2016-11-01 |  | 2017-03-28 | CSE-OF-3291-339 | 2017-03-29 | 3291-NPCC-PMT-AO-T-02637 | 2017-04-17 | 38-22701-N-T-09058 | 1 | 2017-03-29 | 3291-NPCC-MWS-T-0508 | 2017-04-11 | MDDXB-5171-MD- 296-4444-01 | Accepted
59 | RISER LIFT ANALYSIS REPORT FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-RP-059 | AD219-485/488-G-00459 | B | 2 | 2016-10-19 |  | 2017-06-13 | CSE-OF-3291-358 | 2017-06-18 | 3291-NPCC-PMT-AO-T-02992 | 2017-07-04 | 38-22701-N-T-09653 | 2 | 2017-06-18 | 3291-NPCC-MWS-T-0538 | 2017-06-28 | MDDXB-5171-MD-314-4450-01 | Accepted
60 | RISER /SPOOL LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-RP-060 | AD219-485/488-G-00460 | B | 2 | 2016-11-04 |  | 2017-03-30 | CSE-OF-3291-345 | 2017-04-03 | 3291-NPCC-PMT-AO-T-02655 | 2017-04-20 | 38-22701-N-T-09092 | 2A | 2017-04-03 | 3291-NPCC-MWS-T-0513 | 2017-04-11 | MDDXB-5171-MD- 295-4442-01 | Accepted
61 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-RP-061 | AD219-485/488-G-00461 | B | 2 | 2016-10-22 |  | 2017-06-13 | CSE-OF-3291-356 | 2017-06-14 | 3291-NPCC-PMT-AO-T-02989 | 2017-07-04 | 38-22701-N-T-09654 | 2 | 2017-06-13 | 3291-NPCC-MWS-T-0536 | 2017-06-28 | MDDXB-5171-MD-313-4449-01 | Accepted
62 | RISER / SPOOL LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-RP-062 | AD219-485/488-G-00462 | B | 2 | 2016-11-07 |  | 2017-02-04 | CSE-OF-3291-348 | 2017-04-06 | 3291-NPCC-PMT-AO-T-02683 | 2017-04-20 | 38-22701-N-T-09093 | 2 | 2017-04-06 | 3291-NPCC-MWS-T-0519 | 2017-04-18 | MDDXB-5171-MD- 297-4445-01 | Accepted
63 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-RP-063 | AD219-485/488-G-00463 | B | 2 | 2016-10-25 |  | 2017-06-15 | CSE-OF-3291-360 | 2017-06-18 | 3291-NPCC-PMT-AO-T-03007 | 2017-07-04 | 38-22701-N-T-09652 | 2 | 2017-06-18 | 3291-NPCC-MWS-T-0541 | 2017-06-28 | MDDXB-5171-MD-315-4451-01 | Accepted
64 | RISER /SPOOL LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-2 @ WHT-2 | 3291-NN-RP-064 | AD219-486/485-G-00464 | B | 2 | 2016-09-07 |  | 2017-03-23 | CSE-OF-3291-335 | 2017-03-27 | 3291-NPCC-PMT-AO-T-02615 | 2017-04-12 | 38-22701-N-T-09022 | 1 | 2017-03-23 | 3291-NPCC-MWS-T-0497 | 2017-04-11 | MDDXB-5171-MD- 294-4438-01 | Accepted
65 | RISER/ SPOOL LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-2 @ NSMFT | 3291-NN-RP-065 | AD219-486/485-G-00465 | B | 2 | 2016-11-10 |  | 2017-02-12 | CSE-OF-3291-315 | 2017-02-13 | 3291-NPCC-PMT-AO-T-02433 | 2017-02-26 | 38-22701-N-T-08564 | 2 | 2017-02-13 | 3291-NPCC-MWS-T-0465
|  |  |  | 0 | 1 |  |  | 2017-03-27 | CSE-OF-3291-338 | 2017-03-28 | 3291-NPCC-PMT-AO-T-02629 | 2017-04-17 | 38-22701-N-T-09061 | 1 | 2017-03-28 | 3291-NPCC-MWS-T-0505 | 2017-04-11 | MDDXB-5171-MD- 290-4423-01 | Accepted
66 | RISER/SPOOL LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-RP-066 | AD219-486/494-G-00466 | B | 2 | 2016-09-10 |  | 2017-03-05 | CSE-OF-3291-321 | 2017-03-05 | 3291-NPCC-PMT-AO-T-02506 | 2017-03-16 | 38-22701-N-T-08730 | 1 | 2017-03-05 | 3291-NPCC-MWS-T-0479 | 2017-04-11 | MDDXB-5171-MD- 292-4429-01 | Accepted
67 | RISER LIFT ANALYSIS REPORT FOR 6"GL P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-RP-067 | AD219-486/494-G-00467 | B | 2 | 2016-10-02 |  | 2016-08-31 | CSE-OF-3291-245 | 2016-09-01 | 3291-NPCC-PMT-AO-T-01884 | 2016-09-18 | 38-22701-N-T-07230 | 1 | 2016-09-01 | 3291-NPCC-MWS-T-0336 | 2016-10-13 | MDDXB-5171-MD- 264-1981-01 | Accepted
68 | RISER / SPOOL LIFT ANALYSIS REPORT FOR 8" WI P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-RP-068 | AD219-486/494-G-00468 | B |  | 2016-09-13 |  | 2017-02-23 | CSE-OF-3291-317 | 2017-02-26 | 3291-NPCC-PMT-AO-T-02478 | 2017-03-08 | 38-22701-N-T-08647 | 1 | 2017-02-26 | 3291-NPCC-MWS-T-0471 | 2017-04-11 | MDDXB-5171-MD- 291-4425-01 | Accepted
69 | RISER LIFT ANALYSIS REPORT FOR 8" WI P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-RP-069 | AD219-486/494-G-00469 | B | 2 | 2016-10-05 |  | 2016-08-28 | CSE-OF-3291-242 | 2016-08-29 | 3291-NPCC-PMT-AO-T-01866 | 2016-09-08 | 38-22701-N-T-07173 | 2 | 2016-08-29 | 3291-NPCC-MWS-T-0332 | 2016-10-13 | MDDXB-5171-MD- 263-1980-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-12-05 | CSE-OF-3291-306 | 2016-12-06 | 3291-NPCC-PMT-AO-T-02232 | 2016-12-13 | 38-22701-N-T-07988 | 1 | 2016-12-06 | 3291-NPCC-MWS-T-0453 | 2016-12-14 | MDDXB-5171-MD-263-1980-02 | Accepted
70 | RISER LIFT ANALYSIS REPORT FOR WF 14" P/L FROM WHT-9 TO NSMFT (@WHT-9) | 3291-NN-RP-070 | AD219-494/486-G-00470 | B | 2 | 2016-10-08 |  | 2016-08-24 | CSE-OF-3291-236 | 2016-08-25 | 3291-NPCC-PMT-AO-T-01847 | 2016-09-04 | 38-22701-N-T-07107 | 2A | 2016-08-25 | 3291-NPCC-MWS-T-0326 | 2016-08-28 | MDDXB-5171-MD- 248-1978-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-11-30 | CSE-OF-3291-304 | 2016-12-04 | 3291-NPCC-PMT-AO-T-02227 | 2016-12-13 | 38-22701-N-T-07987 | 1 | 2016-12-04 | 3291-NPCC-MWS-T-0450 | 2016-12-14 | MDDXB-5171-MD-248-1978-02 | Accepted
71 | RISER / SPOOL LIFT ANALYSIS REPORT FOR 14" WELL FLUID P/L FROM WHT-9 TO NSMFT (@NSMFT) | 3291-NN-RP-071 | AD219-494/486-G-00471 | B | 2 | 2016-09-16 |  | 2017-03-12 | CSE-OF-3291-327 | 2017-03-13 | 3291-NPCC-PMT-AO-T-02530 | 2017-03-26 | 38-22701-N-T-08801 | 1 | 2017-03-16 | 3291-NPCC-MWS-T-0487
72 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-RP-072 | AD219-486/491-G-00472 | B | 2 | 2016-09-19 |  | 2016-03-28 | CSE-OF-3291-028 | 2016-04-05 | 3291-NPCC-PMT-AO-T-01022 | 2016-04-18 | 38-22701-N-T-05230 | 3 | 2016-03-31 | 3291-NPCC-MWS-T-0085 | 11/04/2016 | MDDXB-5171-MD-062-1831-01 | Accepted
|  |  |  | CRS |  |  |  | 2016-06-02 | CSE-OF-3291-088 | 2016-06-06 | 3291-NPCC-PMT-AO-T-01394 | 2016-06-16 | 38-22701-N-T-06088 | 3
|  |  |  | C | 2 |  |  | 2016-07-28 | CSE-OF-3291-193 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01691 | 2016-08-09 | 38-22701-N-T-06831 | 1 | 2016-07-28 | 3291-NPCC-MWS-T-0269 | 07/08/2017 | MDDXB-5171-MD-062-1831-02 | Accepted
73 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-RP-073 | AD219-486/491-G-00473 | B | 2 | 2016-09-08 |  | 2016-07-14 | C'SE-OF-3291-160 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01607 | 2016-07-27 | 38-22701-N-T-06653 | 2A | 2016-07-17 | 3291-NPCC-MWS-T-0235 | 24/07/2016 | MDDXB-5171-MD- 187-1940-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-09-06 | C'SE-OF-3291-252 | 2016-09-07 | 3291-NPCC-PMT-AO-T-01911 | 2016-09-18 | 38-22701-N-T-07222 | 1 | 2016-09-07 | 3291-NPCC-MWS-T-0349 | 2016-10-09 | MDDXB-5171-MD-187-1940-02 | Accepted
74 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-RP-074 | AD219-486/491-G-00474 | B | 2 | 2016-09-22 |  | 2016-07-25 | CSE-OF-3291-181 | 2016-07-26 | 3291-NPCC-PMT-AO-T-01666 | 2016-08-04 | 38-22701-N-T-06758 | 1 | 2016-07-26 | 3291-NPCC-MWS-T-0258 | 02/08/2016 | MDDXB-5171-MD- 202-1954-01 | Accepted
75 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-RP-075 | AD219-486/491-G-00475 | B | 2 | 2016-09-11 |  | 2016-07-14 | CSE-OF-3291-166 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01616 | 2016-07-27 | 38-22701-N-T-06655 | 2A | 2016-07-17 | 3291-NPCC-MWS-T-0241 | 24/07/2016 | MDDXB-5171-MD- 189-1942-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-11-23 | CSE-OF-3291-301 | 2016-11-23 | 3291-NPCC-PMT-AO-T-02196 | 2016-12-04 | 38-22701-N-T-07891 | 1 | 2016-11-23 | 3291-NPCC-MWS-T-0443 | 2016-12-27 | MDDXB-5171-MD-189-1942-02 | Accepted
76 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-RP-076 | AD219-486/491-G-00476 | B | 2 | 2016-09-25 |  | 2016-07-25 | CSE-OF-3291-184 | 2016-07-27 | 3291-NPCC-PMT-AO-T-01669 | 2016-08-04 | 38-22701-N-T-06757 | 2A | 2016-07-27 | 3291-NPCC-MWS-T-0260 | 04/08/2016 | MDDXB-5171-MD- 207-1955-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-08-17 | CSE-OF-3291-228 | 2016-08-17 | 3291-NPCC-PMT-AO-T-01814 | 2016-08-25 | 38-22701-N-T-07017 | 1 | 2016-08-17 | 3291-NPCC-MWS-T-0315 | 21/08/2016 | MDDXB-5171-MD-207-1955-02 | Accepted
77 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-RP-077 | AD219-486/491-G-00477 | B | 2 | 2016-09-14 |  | 2016-07-14 | CSE-OF-3291-163 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01611 | 2016-07-27 | 38-22701-N-T-06654 | 2A | 2016-07-17 | 3291-NPCC-MWS-T-0237 | 24/07/2016 | MDDXB-5171-MD- 188-1941-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-09-05 | CSE-OF-3291-250 | 2016-09-06 | 3291-NPCC-PMT-AO-T-01904 | 2016-09-18 | 38-22701-N-T-07229 | 2A | 2016-09-06 | 3291-NPCC-MWS-T-0347 | 2016-10-09 | MDDXB-5171-MD-188-1941-02 | Accepted
|  |  |  | 1 | 1 |  |  | 2016-11-06 | CSE-OF-3291-290 | 2016-11-07 | 3291-NPCC-PMT-AO-T-02140 | 2016-11-16 | 38-22701-N-T-07716 | 1 | 2016-11-07 | 3291-NPCC-MWS-T-0421 | 2016-11-23 | MDDXB-5171-MD-188-1941-03 | Accepted
78 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-RP-078 | AD219-486/490-G-00478 | B | 2 | 2016-09-28 |  | 2016-07-26 | CSE-OF-3291-188 | 2016-07-27 | 3291-NPCC-PMT-AO-T-01682 | 2016-08-04 | 38-22701-N-T-06756 | 1 | 2016-07-27 | 3291-NPCC-MWS-T-0265 | 04/08/2016 | MDDXB-5171-MD- 208-1957-01 | Accepted
79 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-RP-079 | AD219-486/490-G-00479 | B | 2 | 2016-08-25 |  | 2016-07-05 | CSE-OF-3291-151 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01576 | 2016-07-20 | 38-22701-N-T-06544 | 2 | 2016-07-10 | 3291-NPCC-MWS-T-0225 | 2016-07-14 | MDDXB-5171-MD- 178-1928-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-09-04 | CSE-OF-3291-248 | 2016-09-05 | 3291-NPCC-PMT-AO-T-01900 | 2016-09-18 | 38-22701-N-T-07228 | 2A | 2016-09-05 | 3291-NPCC-MWS-T-0344 | 2016-10-09 | MDDXB-5171-MD-178-1928-02 | Accepted
|  |  |  | 1 | 1 |  |  | 2016-11-13 | CSE-OF-3291-293 | 2016-11-14 | 3291-NPCC-PMT-AO-T-02157 | 2016-11-24 | 38-22701-N-T-07802 | 1 | 2016-11-14 | 3291-NPCC-MWS-T-0428 | 2016-11-23 | MDDXB-5171-MD-178-1928-03 | Accepted
80 | RISER LIFT ANALYSIS REPORT FOR 10" WI P/L FROM WHT-5 TO NSMFT AT NSMFT | 3291-NN-RP-080 | AD219-486/490-G-00480 | B | 2 | 2016-10-01 |  | 2016-07-26 | CSE-OF-3291-192 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01685 | 2016-08-09 | 38-22701-N-T-06829 | 2A | 2016-07-28 | 3291-NPCC-MWS-T-0268 | 04/08/2016 | MDDXB-5171-MD- 209-1958-01 | Accepted | previous title was WHT-5 TO NSMFT @ WHT-5
|  |  |  | 0 | 1 |  |  | 2016-10-05 | CSE-OF-3291-273 | 2016-10-06 | 3291-NPCC-PMT-AO-T-02028 | 2016-10-12 | 38-22701-N-T-07452 | 1 | 2016-10-09 | 3291-NPCC-MWS-T-0391 | 2016-10-18 | MDDXB-5171-MD-209-1958-02 | Accepted
81 | RISER LIFT ANALYSIS REPORT FOR 10" WI P/L FROM WHT-5 TO NSMFT @ WHT-5 | 3291-NN-RP-081 | AD219-486/490-G-00481 | B | 2 | 2016-08-28 |  | 2016-07-05 | CSE-OF-3291-151 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01576 | 2016-07-20 | 38-22701-N-T-06544 | 2 | 2016-07-10 | 3291-NPCC-MWS-T-0225 | 2016-07-14 | MDDXB-5171-MD- 179-1929-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-10-25 | CSE-OF-3291-285 | 2016-10-26 | 3291-NPCC-PMT-AO-T-02112 | 2016-11-03 | 38-22701-N-T-07616 | 1 | 2016-10-26 | 3291-NPCC-MWS-T-0415 | 2016-10-30 | MDDXB-5171-MD-179-1929-02 | Accepted
82 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-5 TO NSMFT (@WHT-5) | 3291-NN-RP-082 | AD219-490/486-G-00482 | B | 2 | 2016-08-31 |  | 2016-07-04 | CSE-OF-3291-146 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01573 | 2016-07-20 | 38-22701-N-T-06546 | 2A | 2016-07-10 | 3291-NPCC-MWS-T-0222 | 2016-07-13 | MDDXB-5171-MD- 177-1927-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-10-18 | CSE-OF-3291-279 | 2016-10-19 | 3291-NPCC-PMT-AO-T-02088 | 2016-11-01 | 38-22701-N-T-07615 | 1 | 2016-10-19 | 3291-NPCC-MWS-T-0402 | 2016-10-23 | MDDXB-5171-MD-177-1927-02 | Accepted
83 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-RP-083 | AD219-490/486-G-00483 | B | 2 | 2016-10-04 |  | 2016-04-17 | CSE-OF-3291-041 | 2016-04-21 | 3291-NPCC-PMT-AO-T-01124 | 2016-04-26 | 38-22701-N-T-05380 | 3 | 2016-05-01 | 3291-NPCC-MWS-T-0079
|  |  |  | CRS |  |  |  | 2016-06-02 | CSE-OF-3291-088 | 2016-06-06 | 3291-NPCC-PMT-AO-T-01394 | 2016-06-16 | 38-22701-N-T-06088 | 3
|  |  |  | C | 2 |  |  | 2016-07-31 | CSE-OF-3291-198 | 2016-07-31 | 3291-NPCC-PMT-AO-T-01712 | 2016-08-11 | 38-22701-N-T-06862 | 2 | 2016-07-31 | 3291-NPCC-MWS-T-0274 | 2016-08-11 | MDDXB-5171-MD- 226-1844-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-09-19 | CSE-OF-3291-260 | 2016-09-20 | 3291-NPCC-PMT-AO-T-01952 | 2016-09-28 | 38-22701-N-T-07330 | 1 | 2016-09-20 | 3291-NPCC-MWS-T-0364 | 2016-10-18 | MDDXB-5171-MD-226-1844-02 | Accepted
84 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-4) | 3291-NN-RP-084 | AD219-489/490-G-00484 | B | 2 | 2016-08-07 |  | 2016-06-20 | CSE-OF-3291-109 | 2016-06-22 | 3291-NPCC-PMT-AO-T-01476 | 2016-06-30 | 38-22701-N-T-06311 | 2 | 2016-06-22 | 3291-NPCC-MWS-T-0186 | 2016-06-27 | MDDXB-5171-MD- 153-1902-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-11-20 | CSE-OF-3291-300 | 2016-11-21 | 3291-NPCC-PMT-AO-T-02178 | 2016-12-04 | 38-22701-N-T-07890 | 1 | 2016-11-21 | 3291-NPCC-MWS-T-0437 | 2016-11-24 | MDDXB-5171-MD-153-1902-02 | Accepted
85 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-5) | 3291-NN-RP-085 | AD219-489/490-G-00485 | B | 2 | 2016-08-20 |  | 2016-06-28 | CSE-OF-3291-129 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01536 | 2016-07-12 | 38-22701-N-T-06431 | 2A | 2016-06-30 | 3291-NPCC-MWS-T-0205 | 2016-07-13 | MDDXB-5171-MD- 174-1918-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-08-08 | CSE-OF-3291-212 | 2016-08-09 | 3291-NPCC-PMT-AO-T-01763 | 2016-08-22 | 38-22701-N-T-06965 | 1 | 2016-08-09 | 3291-NPCC-MWS-T-0290 | 2016-08-11 | MDDXB-5171-MD-174-1918-02 | Accepted
86 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-4 TO WHT-5 (@WHT-5) | 3291-NN-RP-086 | AD219-490/489-G-00486 | B | 2 | 2016-08-23 |  | 2016-07-04 | CSE-OF-3291-142 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01562 | 2016-07-20 | 38-22701-N-T-06545 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0219 | 2016-07-13 | MDDXB-5171-MD- 176-1926-01 | Accepted
87 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-4 TO WHT-5 (@WHT-4) | 3291-NN-RP-087 | AD219-490/489-G-00487 | B | 2 | 2016-08-10 |  | 2016-06-26 | CSE-OF-3291-122 | 2016-06-28 | 3291-NPCC-PMT-AO-T-01478 | 2016-07-12 | 38-22701-N-T-06429 | 2A | 2016-06-28 | 3291-NPCC-MWS-T-0198 | 2016-07-14 | MDDXB-5171-MD- 183-1904-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-11-16 | CSE-OF-3291-297 | 2016-11-17 | 3291-NPCC-PMT-AO-T-02169 | 2016-11-27 | 38-22701-N-T-07810 | 1 | 2016-11-17 | 3291-NPCC-MWS-T-0434 | 2016-11-24 | MDDXB-5171-MD-183-1904-02 | Accepted
88 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-RP-088 | AD219-490/489-G-00488 | B | 2 | 2016-08-26 |  | 2016-06-30 | CSE-OF-3291-136 | 2016-07-04 | 3291-NPCC-PMT-AO-T-01552 | 2016-07-20 | 38-22701-N-T-06547 | 2 | 2016-07-04 | 3291-NPCC-MWS-T-0214 | 2016-07-13 | MDDXB-5171-MD- 175-1923-01 | Accepted
|  |  |  | 0 | 1 |  |  | 2016-11-14 | CSE-OF-3291-295 | 2016-11-15 | 3291-NPCC-PMT-AO-T-02161 | 2016-11-24 | 38-22701-N-T-07801 | 1 | 2016-11-15 | 3291-NPCC-MWS-T-0431 | 2016-11-23 | MDDXB-5171-MD-175-1923-02 | Accepted
89 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-4) | 3291-NN-RP-089 | AD219-490/489-G-00489 | B | 2 | 2016-08-13 |  | 2016-06-23 | CSE-OF-3291-119 | 2016-06-26 | 3291-NPCC-PMT-AO-T-01499 | 2016-07-12 | 38-22701-N-T-06430 | 1 | 2016-06-27 | 3291-NPCC-MWS-T-0194 | 2016-07-14 | MDDXB-5171-MD- 182-1910-01 | Accepted
90 | RISER / SPOOL LIFT ANALYSIS REPORT FOR 16" MAIN OIL P/L FROM NSMFT TO DAS ISLAND AT NSMFT | 3291-NN-RP-090 | AD219-486-G-00490 | B | 2 | 2016-10-23 |  | 2017-03-07 | CSE-OF-3291-323 | 2017-03-08 | 3291-NPCC-PMT-AO-T-02514 | 2017-03-16 | 38-22701-N-T-08731 | 1 | 2017-03-08 | 3291-NPCC-MWS-T-0482 | 2017-04-11 | MDDXB-5171-MD- 293-4431-01 | Accepted
91 | RISER LIFT ANALYSIS REPORT FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@IGD-HAP) | 3291-NN-RP-091 | AD219-469/486-G-00491 | B | 2 | 2016-10-16 |  | 2016-10-06 | CSE-OF-3291-274 | 2016-10-06 | 3291-NPCC-PMT-AO-T-02038 | 2016-10-12 | 38-22701-N-T-07448 | 1 | 2016-10-09 | 3291-NPCC-MWS-T-0393 | 2016-10-18 | MDDXB-5171-MD- 269-4402-01 | Accepted
92 | RISER / SPOOL LIFT ANALYSIS REPORT FOR 10" EXCESS GAS EXPORT P/L FROM NSMFT TO USSC IGD-HAP (@NSMFT) | 3291-NN-RP-092 | AD219-469/486-G-00492 | B | 2 | 2016-10-26 |  | 2017-03-09 | CSE-OF-3291-325 | 2017-03-11 | 3291-NPCC-PMT-AO-T-02522 | 2017-03-26 | 38-22701-N-T-08802 | 1 | 2017-03-16 | 3291-NPCC-MWS-T-0485
93 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF RCC SLEEPERS ON MICLYN-285 (TRIP-1) | 3291-NN-RP-093 | AD219-705-G-00493 | B | 2 | 2016-04-01 |  | 2016-03-21 | CSE-OF-3291-017 | 2016-03-22 | 3291-NPCC-PMT-AO-T-00990 | 2016-04-04 | 38-22701-N-T-04926 | 2 | 2016-03-31 | 3291-NPCC-MWS-T-0078 | 2016-04-03 | MDDXB-5171-MD-048-1307-01 | Accepted
94 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON GAC-81 (TRIP-1) | 3291-NN-RP-094 | AD219-705-G-00494 | B | 2 | 2016-04-05 |  | 2016-03-23 | CSE-OF-3291-019 | 2016-03-23 | 3291-NPCC-PMT-AO-T-01003 | 2016-04-04 | 38-22701-N-T-04931 | 2 | 2016-03-29 | 3291-NPCC-MWS-T-0051 | 2016-03-30 | MDDXB-5171-MD-047-1303-01 | Accepted
|  |  |  | CRS |  |  |  | 2016-06-01 | CSE-OF-3291-085 | 2016-06-02 | 3291-NPCC-PMT-AO-T-01387 | 2016-06-16 | 38-22701-N-T-06089 | 2
95 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON ASTRO-302 (TRIP-2) | 3291-NN-RP-095 | AD219-705-G-00495 | B | 2 | 2016-04-09 |  | 2016-04-12 | CSE-OF-3291-039 | 2016-04-13 | 3291-NPCC-PMT-AO-T-01096 | 2016-04-24 | 38-22701-N-T-05274 | 2 | 2016-04-27 | 3291-NPCC-MWS-T-0081 | 2016-04-27 | MDDXB-5171-MD -070-1312-01 | Accepted
|  |  |  | CRS |  |  |  | 2016-06-01 | CSE-OF-3291-085 | 2016-06-02 | 3291-NPCC-PMT-AO-T-01387 | 2016-06-16 | 38-22701-N-T-06089 | 2
96 | INSTALLATION ANALYSIS REPORT SLEEPERS SHIFTING | 3291-NN-RP-096 | AD219-705-G-00496 |  |  | TAKEN BY YAHIA | NOT ISSUED OFFICIALLY | [7 empty] | 2016-05-31 | SENT BY E-MAIL | 2016-05-31 | MDDXB-5171-MD-115-1875-01 | Accepted
97 | SEAFASTENING FOR RISERS AND SPOOLS ON ZAKHER-101 | 3291-NN-RP-097 | AD219-705-G-00497 | B | 2 | SKM |  | 2017-03-21 | CSE-OF-3291-332 | 2017-03-22 | 3291-NPCC-PMT-AO-T-02592 | 2017-03-30 | 38-22701-N-T-08870 | 1 | 2017-03-23 | 3291-NPCC-MWS-T-0493 |  |  |  | title changed - s/f. design report for trans. Of piles on zakher-101
98 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CB-6 (TRIP-3) | 3291-NN-RP-098 | AD219-705-G-00498 | B | 2 | SUBMITTED |  | 2016-05-11 | CSE-OF-3291-062 | 2016-05-12 | 3291-NPCC-PMT-AO-T-01245 | 2016-05-15 | 38-22701-N-T-05668 | 1 | 2016-05-12 | 3291-NN-RP-097 | 2016-05-15 | MDDXB-5171-MD-105-1321-01 | Accepted | withdraw this trans. From ADMA (infor. Mr. Yahia)
99 | DAVIT LIFT ANALYSIS @ NSMFT EAST SIDE AFTER METROLOGY | 3291-NN-RP-099 | AD219-486-G-00499 | B | 2 |  | REMARKS | 2016-09-01 | CSE-OF-3291-246 | 2016-09-04 | 3291-NPCC-PMT-AO-T-01892 |  |  |  | 2016-09-04 | 3291-NPCC-MWS-T-0338 | 2016-10-13 | MDDXB-5171-MD- 265-1982-01 | Accepted
100 | INSTALLATION ANALYSIS REPORT FOR 26" CONDUIT PIPELINE | 3291-NN-RP-100 | AD219-705-G-00500 | B | 2 | SUBMITTED |  | 2016-09-06 | CSE-OF-3291-251 | 2016-09-07 | 3291-NPCC-PMT-AO-T-01910 | 2016-09-25 | 38-22701-N-T-07309 | 2 | 2016-09-07 | 3291-NPCC-MWS-T-0348
|  |  |  | 0 | 1 |  |  | 2016-09-29 | CSE-OF-3291-271 | 2016-09-29 | 3291-NPCC-PMT-AO-T-02014 | 2016-10-09 | 38-22701-N-T-07430 | 2 | 2016-09-29 | 3291-NPCC-MWS-T-0387
|  |  |  | 1 | 1 |  |  | 2016-10-13 | CSE-OF-3291-276 | 2016-10-16 | 3291-NPCC-PMT-AO-T-02063 | 2016-11-01 | 38-22701-N-T-07620 | 1 | 2016-10-16 | 3291-NPCC-MWS-T-0395
101 | 10" EGL SHIFTING TO ORIGINAL POSITION ANALYSIS | 3291-NN-RP-101 | AD219-486-G-00573 | B | 2 | SUBMITTED |  | 2016-09-21 | CSE-OF-3291-263 | 2016-09-22 | 3291-NPCC-PMT-AO-T-01973 | 2016-10-05 | 38-22701-N-T-07405 | 2 | 2016-09-22 | 3291-NPCC-MWS-T-0374
|  |  |  | 0 | 1 |  |  | 2016-10-13 | CSE-OF-3291-276 | 2016-10-16 | 3291-NPCC-PMT-AO-T-02063 | 2016-10-19 | 38-22701-N-T-07528 | 2A | 2016-10-16 | 3291-NPCC-MWS-T-0395 | 2016-10-18 | MDDXB-5171-MD- 271-1998-01 | Accepted
|  |  |  | 1 | 1 |  |  | 2016-10-27 | CSE-OF-3291-288 | 2016-10-27 | 3291-NPCC-PMT-AO-T-02120 | 2016-11-09 | 38-22701-N-T-07692 | 1 | 2016-10-27 | 3291-NPCC-MWS-T-0418 | 2016-12-27 | MDDXB-5171-MD-271-1998-02 | Accepted
102 | RECOVERY AND INSTALLATION ANALYSIS REPORT FOR 10” EGL PIPELINE FROM IGD-HAP TO NSMFT WITH DLB-1000 | 3291-NN-RP-102 | AD219-469/486-G-00575 | B | 2 | Reza | REMARKS | 2017-01-15 | CSE-OF-3291-311 | 2017-01-16 | 3291-NPCC-PMT-AO-T-02342 | 2017-01-26 | 38-22701-N-T-08319 | 2 | 2017-01-16 | 3291-NPCC-MWS-T-0460 | 2017-03-12 | MDDXB-5171-MD- 281-4416-01 | Accepted | This Document Not applicabe anymore (infor. from Mr. Yahia)
103 | RECOVERY AND INSTALLATION ANALYSIS REPORT FOR 16” MOL FROM DAS ISLAND TO NSMFT WITH DLB-1000 | 3291-NN-RP-103 | AD219-486-G-00576 | B | 2 | Reza | REMARKS | 2017-01-15 | CSE-OF-3291-311 | 2017-01-16 | 3291-NPCC-PMT-AO-T-02344 | 2017-01-26 | 38-22701-N-T-08318 | 2 | 2017-01-16 | 3291-NPCC-MWS-T-0461 | 2017-03-12 | MDDXB-5171-MD- 282-4417-01 | Accepted | This Document Not applicabe anymore (infor. from Mr. Yahia)
104 | PIPELINE LIFTING ANALYSIS FOR SLEEPER SHIFTING (10in EGL NSMFT to USSC IGD-HAP) | 3291-NN-RP-104 | AD219-486/469-G-00577 | B | 2 | SUBMITTED |  | 2017-06-11 | CSE-OF-3291-354 | 2017-06-12 | 3291-NPCC-PMT-AO-T-02978 | 2017-06-22 | 38-22701-N-T-09599 | 2 | 2017-06-13 | 3291-NPCC-MWS-T-0535 | 2017-06-28 | MDDXB-5171-MD-312-4448-01 | Accepted
105 | MIDLINE TIE IN ANALYSIS FOR 6” GAS LIFT PL FROM NSMFT TO WHT-9 @ KP3.479 | 3291-NN-RP-105 | AD219-486/494-G-00578 | B | 2 |  |  | 2021-05-25 | CSE-OF-3291-376 | 2021-05-25 | 3291-NPCC-PMT-AO-T-05061 | 2021-06-08 | 38-22701-N-L-01809 | 2
|  |  |  | C | 2 |  |  | 2021-06-16 | CSE-OF-3291-377 | 2021-06-16 | 3291-NPCC-PMT-AO-T-05062
|  |  |  | D | 2 |  |  | 2021-07-11 | CSE-OF-3291-378 | 2021-07-12 | 3291-NPCC-PMT-AO-T-05065
106 | MIDLINE TIE IN ANALYSIS USING FLANGE FOR 6” GAS LIFT PL FROM NSMFT TO WHT-9 @ KP 3.479 | 3291-NN-RP-106 | AD219-486/494-G-00579 | B | 2 |  |  | 2021-08-09 | CSE-OF-3291-379 | 2021-08-10 | 3291-NPCC-PMT-AO-T-05079
|  |  |  | C | 2 |  |  | 2021-09-01 | CSE-OF-3291-380 | 2021-09-02 | 3291-NPCC-PMT-AO-T-05091 | 2021-09-23 | 38-22701-N-T-13254 | 1
|  |  |  | D | 2 |  |  | 2022-03-03 | CSE-OF-3291-381 | 2022-03-04 | 3291-NPCC-PMT-AO-T-05140 | 2022-03-17 | 38-22701-N-T-13284 | 2
|  |  |  | 0 | 3 |  |  | 2022-11-08 | CSE-OF-3291-389 | 2022-11-11 | 3291-NPCC-PMT-AO-T-05221 | 2022-11-11 | 38-22701-N-T-13352 | 1
107 | PIPELINE DEMOLITION, SPOOL LIFTING & INSTALLATION FOR 6” GAS LIFT PL FROM NSMFT TO WHT-9 @ KP 3.479 | 3291-NN-RP-107 | AD219-486/494-G-00582 | B | 2 |  |  | 2022-09-28 | CSE-OF-3291-388 | 2022-09-28 | 3291-NPCC-PMT-AO-T-05205
|  |  |  | C | 2 |  |  | 2022-11-08 | CSE-OF-3291-389 | 2022-11-11 | 3291-NPCC-PMT-AO-T-05222 | 2022-11-11 | 38-22701-N-T-13353 | 1
|  |  |  | D | 2 |  |  | 2022-11-15 | CSE-OF-3291-391 | 2022-11-15 | 3291-NPCC-PMT-AO-T-05228 | 2022-11-21 | 38-22701-N-T-13355 | 1
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADMA-OPCO APPROVAL CODE : (1) ACCEPTED; (2) ACCEPTED WITH COMMENTS; (2A) ACCEPTED WITH MINOR COMMENTS;
(3) NOT ACCEPTED, REVISE & RESUBMIT; (4) FOR INFORMATION

## Documents - Naval Marine
|  | ABU DHABI MARINE OPERATING COMPANY (ADMA-OPCO) | [12 empty] | NPCC DOC. No.:
|  | UMM LULU PACKAGE-1 FFD PROJECT | [12 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 3291 | [12 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (NAVAL & MARINE) | [12 empty] | DATE : |  |  |  | 2015-11-17
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | REMAINING DAYS |  |  | NPCC |  | ADMA-OPCO |  |  | MATTHEWS DANIEL |  |  |  |  | REMARKS
[8 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[8 empty] | CSE TO PMT |  | PMT TO ADMA-OPCO |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[8 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6” WI P/L & 10” WF P/L FROM NSMFT TO WHT-7 | 3291-ZZ-RP-001 | AD219-486/492-G-00501 | B | 2 | 2016-03-12 | SUBMITTED | 2016-05-04 | CSE-OF-3291-055 | 2016-05-08 | 3291-NPCC-PMT-AO-T-01224 | 2016-06-20 | 38-22701-N-T-06153 | 1 | 2016-05-04 | 3291-NPCC-MWS-T-0146 | 2016-05-04 | MDDXB-5171-MD-088-1845-01 | COMMENTED | title changed, previous was 6in 4.9km
2 | MOORING ANALYSIS DURING INSTALLATION OF 6” & 10” RISERS, TIE-IN SPOOLS AND RISER FENDERS AT NSMFT (WEST FACE) | 3291-ZZ-RP-002 | AD219-486-G-00502 | B | 2 | 2027-03-14 | PKR | 2017-03-13 | CSE-OF-3291-328 | 2017-03-15 | 3291-NPCC-PMT-AO-T-02558 | 2016-04-02 | 38-22701-N-T-08906 | 1 | 2017-03-16 | 3291-NPCC-MWS-T-0488 | 2017-03-20 | MDDXB-5171- MD-283-4432-01 | COMMENTED
|  |  |  | CRS | [10 empty] | 2017-03-21 | SENT BY E-MAIL | 2017-03-22 | MDDXB-5171-MD-283-4432-02 | ACCEPTED
3 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.1 KM GAS LIFT P/L FROM WHT-9 TO WHT-8 | 3291-ZZ-RP-003 | AD219-494/493-G-00503 | B | 2 | 2016-03-25 |  | 2016-03-16 | CSE-OF-3291-015 | 2016-03-17 | 3291-NPCC-PMT-AO-T-00972 | 2016-03-28 | 38-22701-N-T-04848 | 2 | 2016-03-21 | 3291-NPCC-MWS-T-0041 | 2016-03-22 | MDDXB-5171-MD-025-1824-01 | COMMENTED
|  |  |  | 0 | 1 |  |  | 2016-03-24 | CSE-OF-3291-024 | 2016-03-28 | 3291-NPCC-PMT-AO-T-01009 | 2016-04-03 | 38-22701-N-T-04936 | 1 | 2016-03-31 | 3291-NPCC-MWS-T-0082 | 2016-04-06 | MDDXB-5171-MD-025-1824-02 | ACCEPTED
4 | MOORING ANALYSIS DURING 10" EXCESS GAS PIPELINE SHIFTING AT MFT | 3291-ZZ-RP-004 | AD219-486-G-00504 | B | 2 | 2016-03-31 | SUBY | 2017-04-03 | CSE-OF-3291-347 | 2017-04-05 | 3291-NPCC-PMT-AO-T-02677 | 2017-04-09 | 38-22701-N-T-08988 | 1 | 2017-04-05 | 3291-NPCC-MWS-T-0518 | 2017-04-04 | MDDXB-5171-MD- 287-4441-01 | ACCEPTED | title changed, previous was MERGED WITH 3291-ZZ-RP-003 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.1 KM WATER INJECTION P/L FROM WHT-9 TO WHT-8
5 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING REMOVAL OF WHT-3 JACKET | 3291-ZZ-RP-005 | AD219-488-G-00505 | B | 2 |  | PKR-13/04 | 2017-04-16 | CSE-OF-3291-349 | 2017-04-16 | 3291-NPCC-PMT-AO-T-02722 | 2017-05-02 | 38-22701-N-T-09196 | 1 | 2017-04-16 | 3291-NPCC-MWS-T-0523 | 2017-05-21 | MDDXB-5171- MD-307-790-01 | COMMENTED |  | title changed, previous was MERGED WITH 3291-ZZ-RP-003
|  |  |  | CRS | [10 empty] | 2017-05-22 | SENT BY E-MAIL | 2017-05-23 | MDDXB-5171-MD-307-790-02 | ACCEPTED
6 | MOORING ANALYSIS DURING PIPE LAYING OF 12" WF P/L 6" GL , 6" WI PL FROM WHT-2 TO WHT-3 | 3291-ZZ-RP-006 | AD219-485/488-G-00506 | B | 2 | 2016-04-12 |  | 2016-07-17 | CSE-OF-3291-168 | 2016-07-18 | 3291-NPCC-PMT-AO-T-01628 | 2016-08-21 | 38-22701-N-T-06953 | 1 | 2016-07-18 | 3291-NPCC-MWS-T-0243 | 2016-08-11 | MDDXB-5171-MD- 229-1946-01 | COMMENTED | title changed, previous was 12" x 4.6
7 | MOORING ANALYSIS DURING HOOK-UP WORKS & MECHANICAL COMPLETION AT IGD-HAP, B-25 & B-24 LOCATION | 3291-ZZ-RP-007 | AD219-469-G-00507 | B | 2 |  |  | 2017-09-27 | CSE-OF-3291-365 | 2017-09-27 | 3291-NPCC-PMT-AO-T-03385 | 2017-10-21 | 38-22701-N-T-10330 | 1 | 2017-09-27 | 3291-NPCC-MWS-T-0568 | 2017-10-02 | MDDXB-5171- MD-336-816-01 | ACCEPTED
8 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.6 KM GAS LIFT P/L FROM WHT-2 TO WHT-3 | 3291-ZZ-RP-008 | AD219-485/488-G-00508 | merged with zz-rp-006 | spare | 2016-04-25 | [13 empty] | merged with 3291-nn-rp-006
9 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 3.7 KM GAS LIFT P/L FROM NSMFT TO WHT-2 | 3291-ZZ-RP-009 | AD219-486/485-G-00509 | B | 2 | 2016-05-01 | PKR | 2016-06-05 | CSE-OF-3291-089 | 2016-06-06 | 3291-NPCC-PMT-AO-T-01397 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-06-06 | 3291-NPCC-MWS-T-0163 | 2016-06-20 | MDDXB-5171- MD-146-1878-01 | COMMENTED
10 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" GL P/L, 8” WI P/L AND 14” WF P/L FROM NSMFT TO WHT-9 (5.5KM) | 3291-ZZ-RP-010 | AD219-486/494-G-00510 | B | 2 | 2016-05-07 |  | 2016-04-06 | CSE-OF-3291-035 | 2016-04-07 | 3291-NPCC-PMT-AO-T-01072 | 2016-06-20 | 38-22701-N-T-06153 | 1 | 2016-04-27 | 3291-NPCC-MWS-T-0093 | 2016-04-28 | MDDXB-5171-MD-074-1840-01 | COMMENTED
11 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 8" X 5.5 KM WATER INJECTION P/L FROM NSMFT TO WHT-9 | 3291-ZZ-RP-011 | AD219-486/494-G-00511 | see remarks | spare | 2016-05-14 | [13 empty] | merged with 3291-nn-rp-010
12 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 14” WF P/L FROM NSMFT TO WHT-9 | 3291-ZZ-RP-012 | AD219-494/486-G-00512 |  |  | 2016-05-20 | PKR | [12 empty] | title changed, previous merged with 3291-nn-rp-010
13 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" GL P/L, 6” WI P/L AND 10” WF P/L FROM NSMFT TO WHT-6 (5.2KM) | 3291-ZZ-RP-013 | AD219-486/491-G-00513 | B | 2 | 2016-05-27 | SUBMITTED | 2016-05-10 | CSE-OF-3291-059 | 2016-05-11 | 3291-NPCC-PMT-AO-T-01242 | 2016-06-20 | 38-22701-N-T-06153 | 1 | 2016-05-11 | 3291-NPCC-MWS-T-0122 | 2016-05-11 | MDDXB-5171-MD- 100-1855-01 | ACCEPTED
14 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 5.2 KM WATER INJECTION P/L FROM NSMFT TO WHT-6 | 3291-ZZ-RP-014 | AD219-486/491-G-00514 | Merged with 3291-zz-rp-013 |  | 2016-06-03
15 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 5.2 KM GAS LIFT P/L FROM NSMFT TO WHT-6 | 3291-ZZ-RP-015 | AD219-486/491-G-00515 |  |  | 2016-06-09
16 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 6.0 KM GAS LIFT P/L FROM NSMFT TO WHT-5 | 3291-ZZ-RP-016 | AD219-486/490-G-00516 |  |  | 2016-06-15
17 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 10" X 6.0 KM WATER INJECTION P/L FROM NSMFT TO WHT-5 | 3291-ZZ-RP-017 | AD219-486/490-G-00517 |  |  | 2016-06-22
18 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" GL P/L, 10” WI P/L AND 18” WF P/L FROM NSMFT TO WHT-5 (6.075KM) | 3291-ZZ-RP-018 | AD219-490/486-G-00518 | B | 2 | 2016-06-29 | SUBMITTED | 2016-05-16 | CSE-OF-3291-066 | 2016-05-17 | 3291-NPCC-PMT-AO-T-01261 | 2016-06-20 | 38-22701-N-T-06153 | 1 | 2016-05-17 | 3291-NPCC-MWS-T-0134 | 2016-06-01 | MDDXB-5171-MD- 118-1863-01 | COMMENTED | title changed, previous was 18in 6.075KM
|  |  |  | CRS | [10 empty] | 2016-06-05 | SENT BY E-MAIL
19 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 18" X 4.7 KM WELL FLUID P/L FROM WHT-4 TO WHT-5 | 3291-ZZ-RP-019 | AD219-489/490-G-00519 | B | 2 | 2016-07-07 |  | 2016-03-31 | CSE-OF-3291-031 | 2016-03-31 | 3291-NPCC-PMT-AO-T-01038 | 2016-06-20 | 38-22701-N-T-06153 | 1 | 2016-03-31 | 3291-NPCC-MWS-T-0061 | 2016-05-17 | MDDXB-5171- MD-108-1830-01 | COMMENTED
|  |  |  | CRS | [10 empty] | 2016-05-19 | SENT BY E-MAIL | 2016-06-01 | MDDXB-5171-MD-108-1830-02 | ACCEPTED
20 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.7 KM GAS LIFT P/L FROM WHT-5 TO WHT-4 | 3291-ZZ-RP-020 | AD219-490/489-G-00520 | Merged with 3291-ZZ-RP-019 |  | 2016-07-14
21 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.7 KM WATER INJECTION P/L FROM WHT-5 TO WHT-4 | 3291-ZZ-RP-021 | AD219-490/489-G-00521 |  |  | 2016-07-20
22 | MOORING ANALYSIS FOR DURING LAYING OF 16" X 69 KM MAIN OIL LINE (MOL) FROM DAS ISLAND TO NSMFT | 3291-ZZ-RP-022 | AD219-486-G-00522 | B |  | 2016-07-26 |  | 2016-09-08 | CSE-OF-3291-255 | 2016-09-14 | 3291-NPCC-PMT-AO-T-01927 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-09-14 | 3291-NPCC-MWS-T-0356 | 2016-09-18 | MDDXB-5171-MD-251-1984-01 | COMMENTED
[17 empty] | 2016-09-25 | MDDXB-5171-MD-251-1984-02 | ACCEPTED
23 | MOORING ANALYSIS DURING LAYING OF 10" EXCESS GAS PIPE LINE FROM IGD-HAP TO NSMFT | 3291-ZZ-RP-023 | AD219-469/486-G-00523 | B | 2 | 2016-09-20 |  | 2016-08-08 | CSE-OF-3291-213 | 2016-08-10 | 3291-NPCC-PMT-AO-T-01764 | 2016-08-21 | 38-22701-N-T-06953 | 1 | 2016-08-10 | 3291-NPCC-MWS-T-0291 | 2016-08-21 | MDDXB-5171-MD- 235-1964-01 | COMMENTED | title changed, previous was 10" X 32 KM (MOL)
|  |  |  | CRS | [10 empty] | 2016-08-22 | SENT BY E-MAIL | 2016-08-22 | MDDXB-5171-MD-235-1964-02 | accepted
24 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-3 & WHT-6 JACKET | 3291-ZZ-RP-024 | AD219-488-G-00524 | B | 2 | 2016-03-05 |  | 2016-05-02 | CSE-OF-3291-050 | 2016-05-03 | 3291-NPCC-PMT-AO-T-01212 | 2016-06-20 | 38-22701-N-T-06153 | 1 | 2016-05-09 | 3291-NPCC-MWS-T-0109 | 2016-05-08 | MDDXB-5171-MD-090-753-01 | COMMENTED
|  |  |  | CRS |  |  |  | 2016-05-08 | SENT TO PMT | [5 empty] | 2016-05-09 | 3291-NPCC-MWS-T-0109 | 2016-05-08 | MDDXB-5171-MD-090-753-02 | accepted
25 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-4 & WHT-5 JACKET | 3291-ZZ-RP-025 | AD219-489-G-00525 | B | 2 | 2015-11-17 |  | 2015-11-17 | CSE-OF-3291-001 | 2015-11-17 | 3291-NPCC-PMT-AO-T-00624 | 2015-12-06 | 38-22701-N-T-03499 | 2 | 2016-03-29 | 3291-NPCC-MWS-T-0044 |  |  |  | ADMA comments - Approval of this document is sub. approval to by MWS
26 | MOORING ANALYSIS DURING HOOK UP WORK AT NSMFT | 3291-ZZ-RP-026 | AD219-486-G-00526 | B |  | PKR -31/01 |  | 2018-02-06 | CSE-OF-3291-373 | 2018-02-07 | 3291-NPCC-PMT-AO-T-03802 | 2018-08-05 | 38-22701-N-T-11404 | 1 | 2018-02-07 | 3291-NPCC-MWS-T-0590 | 2018-02-08 | MDDXB-5171- MD-347-5008-01 | COMMENTED
27 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-6 JACKET | 3291-ZZ-RP-027 | AD219-491-G-00527 | Merged with 3291-ZZ-RP-028 |  | 2016-04-27
28 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-7 JACKET | 3291-ZZ-RP-028 | AD219-492-G-00528 | B | 2 | 2016-06-23 |  | 2016-09-29 | CSE-OF-3291-271 | 2016-09-29 | 3291-NPCC-PMT-AO-T-02012 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-29 | 3291-NPCC-MWS-T-0386 | 2016-10-09 | MDDXB-5171- MD-257-777-01 | accepted
29 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-8 JACKET | 3291-ZZ-RP-029 | AD219-493-G-00529 | B | 2 | 2016-05-16 |  | 2016-08-15 | CSE-OF-3291-223 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01796 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-16 | 3291-NPCC-MWS-T-0305
|  |  |  | C | 2 |  |  | 2016-08-25 | CSE-OF-3291-238 | 2016-08-27 | 3291-NPCC-PMT-AO-T-01854 |  |  |  | 2016-08-27 | 3291-NPCC-MWS-T-0328 | 2016-08-29 | MDDXB-5171- MD-238-768-02 | accepted
30 | MOORING ANALYSIS DURING INSTALLATION OF WHT-9 JACKET | 3291-ZZ-RP-030 | AD219-494-G-00530 | B | 2 | 2015-05-06 |  | 2016-06-29 | CSE-OF-3291-132 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01541 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-06-30 | 3291-NPCC-MWS-T-0209 | 2016-07-03 | MDDXB-5171-MD-165-766-02 | accepted
31 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-3 TOPSIDES | 3291-ZZ-RP-031 | AD219-488-G-00531 |  |  | 2016-12-01
32 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-4 TOPSIDES | 3291-ZZ-RP-032 | AD219-489-G-00532 | B | 2 | 2016-12-06 |  | 2017-07-09 | CSE-OF-3291-362 | 2017-07-10 | 3291-NPCC-PMT-AO-T-03121 | 2017-07-17 | 38-22701-N-T-09768 | 1 | 2017-07-10 | 3291-NPCC-MWS-T-0545 | 2017-07-17 | MDDXB-5171- MD-323-795-01 | COMMENTED
33 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-5 TOPSIDES | 3291-ZZ-RP-033 | AD219-490-G-00533 | B | 2 | 2016-12-11 |  | 2017-07-12 | CSE-OF-3291-363 | 2017-07-12 | 3291-NPCC-PMT-AO-T-03155 | 2017-07-17 | 38-22701-N-T-09767 | 1 | 2017-07-12 | 3291-NPCC-MWS-T-0546 | 2017-07-17 | MDDXB-5171- MD-324-798-01 | COMMENTED
34 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-6 TOPSIDES | 3291-ZZ-RP-034 | AD219-491-G-00534 |  |  | 2016-12-16
35 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-7 TOPSIDES | 3291-ZZ-RP-035 | AD219-492-G-00535 |  |  | 2016-12-21
36 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-8 TOPSIDES | 3291-ZZ-RP-036 | AD219-493-G-00536 |  |  | 2016-12-26
37 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-9 TOPSIDES | 3291-ZZ-RP-037 | AD219-494-G-00537 |  |  | 2016-12-31
38 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-8 (WEST FACE) | 3291-ZZ-RP-038 | AD219-493-G-00538 | B | 2 | 2016-07-12 | SUBMITTED | 2016-09-18 | CSE-OF-3291-258 | 2016-08-19 | 3291-NPCC-PMT-AO-T-01943 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-19 | 3291-NPCC-MWS-T-0361 | 2016-10-11 | MDDXB-5171- MD-262-1992-01 | COMMENTED
39 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 8", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-9 (EAST FACE) | 3291-ZZ-RP-039 | AD219-494-G-00539 | B | 2 | 2016-07-25 | SUBMITTED | 2016-09-14 | CSE-OF-3291-256 | 2016-09-18 | 3291-NPCC-PMT-AO-T-01935 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-18 | 3291-NPCC-MWS-T-0358 | 2016-10-11 | MDDXB-5171- MD-261-1991-01 | ACCEPTED
40 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 18" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-4 (EAST FACE) | 3291-ZZ-RP-040 | AD219-489-G-00540 | B | 2 | 2016-08-07 | PKR | 2016-06-23 | CSE-OF-3291-116 | 2016-06-23 | 3291-NPCC-PMT-AO-T-01489 | 2016-06-29 | 38-22701-N-T-06288 | 1 | 2016-06-23 | 3291-NPCC-MWS-T-0192 | 2016-07-03 | MDDXB-5171-MD- 164-1903-01 | COMMENTED
|  |  |  | 0 | 1 |  | PKR | 2016-07-04 | CSE-OF-3291-139 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01559 | 31/07/2016 | 38-22701-N-T-06705 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0217 | 2016-07-11 | MDDXB-5171-MD-164-1903-02 | ACCEPTED
41 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 10", 18", 16" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-5 (EAST FACE) | 3291-ZZ-RP-041 | AD219-490-G-00541 | B | 2 | 2016-08-20 | PKR | 2016-07-04 | CSE-OF-3291-144 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01569 | 31/07/2016 | 38-22701-N-T-06705 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0220 | 2016-07-12 | MDDXB-5171- MD-171-1924-01 | ACCEPTED
42 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 12" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-3 (WEST FACE) | 3291-ZZ-RP-042 | AD219-488-G-00542 | B | 2 | 2016-10-19 | PKP | 2017-11-12 | CSE-OF-3291-369 | 2017-11-13 | 3291-NPCC-PMT-AO-T-03463 | 2020-08-12 | 38-22701-N-T-12023 | 4 | 2017-11-13 | 3291-NPCC-MWS-T-0577 | 2017-11-13 | MDDXB-5171- MD-346-4460-01 | ACCEPTED
43 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6" & 12" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-2 (EAST & WEST FACE) | 3291-ZZ-RP-043 | AD219-485-G-00543 | B | 2 | 2016-11-01 |  | 2017-03-16 | CSE-OF-3291-331 | 2017-03-19 | 3291-NPCC-PMT-AO-T-02567 | 2016-04-02 | 38-22701-N-T-08906 | 1 | 2017-03-19 | 3291-NPCC-MWS-T-0491 | 2017-03-21 | MDDXB-5171-MD- 286-4435-01 | COMMENTED
44 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT- 2 (EAST FACE) | 3291-ZZ-RP-044 | AD219-485-G-00544 | SPARE |  | 2016-11-10 | merged with ZZ-RP-043
45 | MOORING ANALYSIS DURING INSTALLATION OF 16" RISER, TIE-IN SPOOLS AND RISER FENDERS AT NSMFT (WEST FACE) | 3291-ZZ-RP-045 | AD219-486-G-00545 | B | 2 | 2016-09-07 | PKR | 2017-03-16 | CSE-OF-3291-330 | 2017-03-19 | 3291-NPCC-PMT-AO-T-02564 | 2016-04-02 | 38-22701-N-T-08906 | 1 | 2017-03-19 | 3291-NPCC-MWS-T-0490 | 2017-03-21 | MDDXB-5171-MD- 285-4434-01 | COMMENTED | title changed, previous was CONSTRUCTION BARGE 6"
|  |  |  | CRS | [10 empty] | 2017-03-22 | SENT BY E-MAIL
46 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 8", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (WEST FACE) | 3291-ZZ-RP-046 | AD219-486-G-00546 | B | 2 | 2016-09-10 |  | 2017-03-15 | CSE-OF-3291-329 | 2017-03-16 | 3291-NPCC-PMT-AO-T-02561 | 2016-04-02 | 38-22701-N-T-08906 | 1 | 2017-03-19 | 3291-NPCC-MWS-T-0489 | 2017-03-20 | MDDXB-5171-MD- 284-4433-01 | COMMENTED
|  |  |  | CRS | [10 empty] | 2017-03-21 | SENT BY E-MAIL | 2017-03-22 | MDDXB-5171-MD-284-4433-02 | ACCEPTED
47 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6",10",18" RISER , TIE-IN SPOOLS AND RISER FENDER AT NSMFT (EAST FACE) SETUP#1 | 3291-ZZ-RP-047 | AD219-486-G-00547 | B | 2 | 2016-09-28 |  | 2016-05-26 | CSE-OF-3291-077 | 2016-05-29 | 3291-NPCC-PMT-AO-T-01349 | 21/08/2016 24/08/2016 | 38-22701-N-T-06953 38-22701-N-T-06998 | 1 | 2016-05-29 | 3291-NPCC-MWS-T-0150 | 2016-06-09 | MDDXB-5171-MD- 125-1872-01 | Accepted
48 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (EAST FACE) SETUP #2 | 3291-ZZ-RP-048 | AD219-486-G-00548 | B | 2 | 2016-09-19 |  | 2016-05-30 | CSE-OF-3291-078 | 2016-05-31 | 3291-NPCC-PMT-AO-T-01362 | 21/08/2016 24/08/2016 | 38-22701-N-T-06953 '38-22701-N-T-06998 | 1 | 2016-05-31 | 3291-NPCC-MWS-T-0153 | 2016-06-14 | MDDXB-5171-MD- 131-1874-01 | Accepted
49 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (EAST FACE) SETUP #3 | 3291-ZZ-RP-049 | AD219-486-G-00549 | B | 2 | 2016-09-01 | PKR | 2016-06-06 | CSE-OF-3291-090 | 2016-06-08 | 3291-NPCC-PMT-AO-T-01401 | 31/07/2016 | 38-22701-N-T-06705 | 1 | 2016-06-08 | 3291-NPCC-MWS-T-0165 | 2016-06-14 | MDDXB-5171-MD- 130-1882-01 | Accepted
50 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 18" AND 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-5 (WEST FACE) | 3291-ZZ-RP-050 | AD219-490-G-00550 | B | 2 | 2016-08-20 | PKR | 2016-07-05 | CSE-OF-3291-147 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01574 | 31/07/2016 | 38-22701-N-T-06705 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0223 | 2016-07-05 | MDDXB-5171- MD-170-1921-01 | COMMENTED
|  |  |  | CRS | [10 empty] | 2016-07-10 | SENT BY E-MAIL | 2016-07-11 | MDDXB-5171-MD-170-1921-02 | Accepted
51 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-6 (WEST FACE) | 3291-ZZ-RP-051 | AD219-491-G-00551 | B | 2 | 2016-09-08 |  | 2016-07-05 | CSE-OF-3291-153 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01578 | 31/07/2016 | 38-22701-N-T-06705 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0227 | 2016-07-12 | MDDXB-5171- MD-172-1925-01 | COMMENTED
52 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-7 (WEST FACE) | 3291-ZZ-RP-052 | AD219-492-G-00552 | B | 2 | 2016-09-22 | SUBMITTED | 2016-09-20 | CSE-OF-3291-262 | 2016-09-21 | 3291-NPCC-PMT-AO-T-01962 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-22 | 3291-NPCC-MWS-T-0369 | 2016-12-28 | MDDXB-5171- MD-276-1996-01 | COMMENTED
53 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-9 (WEST FACE) | 3291-ZZ-RP-053 | AD219-494-G-00553 | B | 2 | 2016-07-25 | SUBMITTED | 2016-09-15 | CSE-OF-3291-257 | 2016-09-17 | 3291-NPCC-PMT-AO-T-01937 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-17 | 3291-NPCC-MWS-T-0359 | 2016-10-11 | MDDXB-5171- MD-260-1990-01 | ACCEPTED
54 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT IGD-HAP (WEST FACE) | 3291-ZZ-RP-054 | AD219-486-G-00554 | B | 2 | 2016-10-16 | SUBMITTED | 2016-09-20 | CSE-OF-3291-261 | 2016-09-21 | 3291-NPCC-PMT-AO-T-01961 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-21 | 3291-NPCC-MWS-T-0368 | 2016-10-19 | MDDXB-5171- MD-270-1995-01 | COMMENTED
|  |  |  | CRS | [10 empty] | 2016-10-23 | SENT BY E-MAIL | 2016-10-24 | MDDXB-5171-MD-270-1995-02 | ACCEPTED
|  |  |  | 0 | 1 |  |  | 2016-11-17 | CSE-OF-3291-298 | 2016-11-20 | 3291-NPCC-PMT-AO-T-02171 | 2016-12-25 | 38-22701-N-T-08083 | 1 | 2016-11-20 | 3291-NPCC-MWS-T-0435 | 2016-11-21 | MDDXB-5171-MD-270-1995-03 | ACCEPTED
55 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-1 (Campaign-1) | 3291-ZZ-RP-055 | AD219-469-G-00555 | B | 2 | 2016-04-01 |  | 2016-03-15 | CSE-OF-3291-013 | 2016-03-17 | 3291-NPCC-PMT-AO-T-00970 | 2016-03-28 | 38-22701-N-T-04849 | 2 | 2016-03-31 | 3291-NPCC-MWS-T-0076
|  |  |  | C | 2 |  |  | 2016-03-23 | CSE-OF-3291-018 | 2016-03-23 | 3291-NPCC-PMT-AO-T-01001 | 2016-03-27 | 38-22701-N-T-04829 | 1 | 2016-03-29 | 3291-NPCC-MWS-T-0050 | 2016-04-03 | MDDXB-5171-MD-049-1301-01 | accepted
56 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-2 (Campaign-1) | 3291-ZZ-RP-056 | AD219-705-G-00556 | B |  | 2016-04-05 |  | 2016-04-18 | CSE-OF-3291-045 | 2016-04-19 | 3291-NPCC-PMT-AO-T-01128 | 2016-05-08 | 38-22701-N-T-05533 | 1 | 2016-04-19 | 3291-NPCC-MWS-T-0074 | 2016-04-26 | MDDXB-5171-MD-069-1311-01 | accepted
57 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-3 (Campaign-1) | 3291-ZZ-RP-057 | AD219-705-G-00557 | B |  | 2016-04-09 |  | 2016-05-12 | CSE-OF-3291-060 | 2016-05-12 | 3291-NPCC-PMT-AO-T-01243 | 2016-05-15 | 38-22701-N-T-05672 | 1 | 2016-05-12 | 3291-NPCC-MWS-T-0124 | 2016-05-12 | MDDXB-5171- MD-104-1320-01 | accepted
58 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-4 (Campaign-1) | 3291-ZZ-RP-058 | AD219-705-G-00558 |  |  | 2016-04-13
59 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-5 (Campaign-1) | 3291-ZZ-RP-059 | AD219-705-G-00559 |  |  | 2016-04-17
60 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-6 (Campaign-1) | 3291-ZZ-RP-060 | AD219-705-G-00560 |  |  | 2016-04-21
61 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-7 (Campaign-1) | 3291-ZZ-RP-061 | AD219-705-G-00561 |  |  | 2016-04-25
62 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-8 (Campaign-1) | 3291-ZZ-RP-062 | AD219-705-G-00562 |  |  | 2016-04-29
63 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-9 (Campaign-1) | 3291-ZZ-RP-063 | AD219-705-G-00563 |  |  | 2016-05-03
64 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-10 (Campaign-1) | 3291-ZZ-RP-064 | AD219-705-G-00564 |  |  | 2016-05-07
65 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-11 (Campaign-1) | 3291-ZZ-RP-065 | AD219-705-G-00565 |  |  | 2016-05-11
66 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-12 (Campaign-1) | 3291-ZZ-RP-066 | AD219-705-G-00566 |  |  | 2016-05-15
67 | STABILITY ANALYSIS DURING TRANSPORTATION OF RCC SLEEPERS TRIP-1 (CAMPAIGN-1) | 3291-ZZ-RP-067 | AD219-705-G-00567 | B | 2 | SUBMITTED |  | 2016-03-27 | CSE-OF-3291-027 | 2016-03-28 | 3291-NPCC-PMT-AO-T-01020 | 2016-06-20 | 38-22701-N-T-06153 | 1 | 2016-03-28 | 3291-NPCC-MWS-T-0084 | 2016-03-28 | MDDXB-5171-MD-036-1302-01 | Accepted
68 | MOORING ANALYSIS DURING SHORE PULL AT DAS ISLAND | 3291-ZZ-RP-068 | AD219-705-G-00568 | B | 2 | SUBMITTED |  | 2016-06-14 | CSE-OF-3291-101 | 2016-06-15 | 3291-NPCC-PMT-AO-T-01442 | 2016-06-30 | 38-22701-N-T-06334 | 1 | 2016-06-15 | 3291-NPCC-MWS-T-0178 | 2016-07-13 | MDDXB-5171- MD-173-1888-01 | COMMENTED
|  |  |  | 0 | 1 |  |  | 2016-08-02 | CSE-OF-3291-201 | 2016-08-02 | 3291-NPCC-PMT-AO-T-01725 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-08-02 | 3291-NPCC-MWS-T-0278 | 2016-08-17 | MDDXB-5171-MD-173-1888-02 | ACCEPTED
69 | MOORING ANALYSIS DURING SLEEPER INSTALLATION FOR WHT-2 TO WHT-3 PIPELINES | 3291-ZZ-RP-069 | AD219-485/488-G-00569 | B | 2 |  | PKR | 19/07/2016 | CSE-OF-3291-171 | 20/07/2016 | 3291-NPCC-PMT-AO-T-01638 | 31/07/2016 | 38-22701-N-T-06705 | 1 | 20/07/2016 | 3291-NPCC-MWS-T-0247 | 2016-07-28 | MDDXB-5171-MD- 193-1948-01 | ACCEPTED
70 | MOORING ANALYSIS DURING SLEEPER INTALLATION FOR WHT-5 TO WHT-4 PIPELINES | 3291-ZZ-RP-070 | AD219-490/489-G-00570 | B | 2 |  | PKR | 20/07/2016 | CSE-OF-3291-175 | 21/07/2016 | 3291-NPCC-PMT-AO-T-01647 | 31/07/2016 | 38-22701-N-T-06705 | 1 | 20/07/2016 | 3291-NPCC-MWS-T-0252 | 2016-07-28 | MDDXB-5171-MD- 196-1952-01 | ACCEPTED
71 | MOORING ANALYSIS DURING SLEEPER INSTALLATION AT CX-01 FOR 10" EXCESS GAS PIPELINES FROM IGD-HAP TO NSMFT | 3291-ZZ-RP-071 | AD219-469/486-G-00571 | B | 2 |  | PKR | 19/07/2016 | CSE-OF-3291-172 | 21/07/2016 | 3291-NPCC-PMT-AO-T-01639 | 31/07/2016 | 38-22701-N-T-06705 | 1 | 20/07/2016 | 3291-NPCC-MWS-T-0248 | 2016-07-28 | MDDXB-5171-MD- 194-1950-01 | ACCEPTED
72 | MOORING ANALYSIS DURING SLEEPER INSTALLATION AT CX-01 FOR 16" MAIN OIL PIPELINE (MFT TO DAS ISLAND) | 3291-ZZ-RP-072 | AD219-486-G-00572 | B | 2 |  | PKR | 19/07/2016 | CSE-OF-3291-173 | 21/07/2016 | 3291-NPCC-PMT-AO-T-01640 | 31/07/2016 | 38-22701-N-T-06705 | 1 | 20/07/2016 | 3291-NPCC-MWS-T-0249 | 2016-07-28 | MDDXB-5171-MD- 195-1951-01 | ACCEPTED
73 | MOORING ANALYSIS DURING INSTALLATION OF RISER FENDER AT IGD-HAP (WEST FACE) | 3291-ZZ-RP-073 | AD219-469-G-00574 | B | 2 |  | PKR | 2016-11-14 | CSE-OF-3291-294 | 2016-11-15 | 3291-NPCC-PMT-AO-T-02159 | 2016-12-25 | 38-22701-N-T-08083 | 1 | 2016-11-15 | 3291-NPCC-MWS-T-0429 | 2016-11-22 | MDDXB-5171 -MD-273-4406-01 | COMMENTED
|  |  |  | CRS | [10 empty] | 2016-11-29 | SENT BY E-MAIL
74 | MOORING ANALYSIS DURING SUBSEA REPAIR 6INCH GL FROM WHT-9 | 3291-ZZ-RP-074 | AD219-494-G-00580 | B | 2 |  | PRR | 2022-04-11 | CSE-OF-3291-382 | 2022-04-12 | 3291-NPCC-PMT-AO-T-05150 |  |  |  | 2022-04-12 | 3291-NPCC-MWS-T-0651
75 | MOORING ANALYSIS DURING HOOK UP WORKS AT WHT-2 | 3291-ZZ-RP-075 | AD219-485-G-00581 AD303-485-G-00581 | B | 2 |  |  | 2022-06-20 | CSE-OF-3291-384 | 2022-06-20 | 3291-NPCC-PMT-AO-T-05180 | 2022-06-28 | NASR-ADNOC-NPCC-T-02097 | 2
|  |  | AD303-485-G-00581 | C | 2 |  |  | 2022-07-01 | CSE-OF-3291-385 | 2022-07-01 | 3291-NPCC-PMT-AO-T-85MBD-00389 | 2022-07-02 | NASR-ADNOC-NPCC-T-02109 | 2 | 2022-07-01 | 3291-NPCC-MWS-T-0656
|  |  |  | D | 2 |  |  | 2022-07-22 | CSE-OF-3291-386 | 2022-07-22 | 3291-NPCC-PMT-AO-T-85MBD-00393 | 2022-08-05 | NASR-ADNOC-NPCC-T-02174 | 2 | 2022-07-22 | 3291-NPCC-MWS-T-0658
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADMA-OPCO APPROVAL CODE : (1) ACCEPTED; (2) ACCEPTED WITH COMMENTS; (2A) ACCEPTED WITH MINOR COMMENTS;
(3) NOT ACCEPTED, REVISE & RESUBMIT; (4) FOR INFORMATION
Formulas:
SUBMISSION PLAN = 5+[SUBMISSION PLAN, row above]

## Drawings
|  | ABU DHABI MARINE OPERATING COMPANY (ADMA-OPCO) | [12 empty] | NPCC DOC. No.:
|  | UMM LULU PACKAGE-1 FFD PROJECT | [12 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 3291 | [12 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (DRAWINGS) | [12 empty] | DATE : |  |  |  | 2015-11-17
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | REMAINING DAYS |  |  | NPCC |  | ADMA-OPCO |  |  | MATTHEWS DANIEL |  |  |  |  | REMARKS
[8 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[8 empty] | CSE TO PMT |  | PMT TO ADMA-OPCO |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[8 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0001 | AD219-486/492-PL-00601 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
2 | START UP HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0002 | AD219-486/492-PL-00602 | A |  | 2016-02-28 | NAR | 2016-02-27 | CSE-OF-3291-006 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00910 |  |  |  | 2016-03-29 | 3291-NPCC-MWS-T-0046
3 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0003 | AD219-486/492-PL-00603 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
4 | BUCKLE DETECTOR DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0004 | AD219-486/492-PL-00604 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
5 | START UP HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0005 | AD219-486/492-PL-00605 | A |  | 2016-02-28 | NAR | 2016-02-24 | CSE-OF-3291-005 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00903 |  |  |  | 2016-03-29 | 3291-NPCC-MWS-T-0045
6 | LAYDOWN HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0006 | AD219-486/492-PL-00606 | A |  | 2016-02-28 | NAR | 2016-02-24 | CSE-OF-3291-005 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00903 |  |  |  | 2016-03-29 | 3291-NPCC-MWS-T-0045
7 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0007 | AD219-494/493-PL-00607 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
8 | START UP HEAD DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0008 | AD219-494/493-PL-00608 | B |  | 2016-02-28 | HZD | 2016-03-02 | CSE-OF-3291-009 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0065
9 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0009 | AD219-494/493-PL-00609 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
10 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0010 | AD219-494/493-PL-00610 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
11 | START UP HEAD DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0011 | AD219-494/493-PL-00611 | B |  | 2016-02-28 | NAR | 2016-03-02 | CSE-OF-3291-009 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0065
12 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0012 | AD219-494/493-PL-00612 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
13 | BUCKLE DETECTOR DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0013 | AD219-493/494-PL-00613 | A |  | 2016-02-28 | AVN | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
14 | START UP HEAD DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0014 | AD219-493/494-PL-00614 | A |  | 2016-02-28 | HZD | 2016-02-28 | CSE-OF-3291-007 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0064
15 | LAYDOWN HEAD DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0015 | AD219-493/494-PL-00615 | A |  | 2016-02-28 | HZD | 2016-02-28 | CSE-OF-3291-007 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0064
16 | BUCKLE DETECTOR DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0016 | AD219-485/488-PL-00616 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
17 | START UP HEAD DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0017 | AD219-485/488-PL-00617 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
18 | LAYDOWN HEAD DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0018 | AD219-485/488-PL-00618 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
19 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0019 | AD219-485/488-PL-00619 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
20 | START UP HEAD DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0020 | AD219-485/488-PL-00620 | B |  | 2016-02-28 | NAR | 2016-03-02 | CSE-OF-3291-009 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0065
21 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0021 | AD219-485/488-PL-00621 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
22 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0022 | AD219-485/488-PL-00622 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
23 | START UP HEAD DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0023 | AD219-485/488-PL-00623 | B |  | 2016-02-28 | HZD | 2016-03-02 | CSE-OF-3291-009 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0065
24 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0024 | AD219-485/488-PL-00624 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
25 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0025 | AD219-486/485-PL-00625 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
26 | START UP HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0026 | AD219-486/485-PL-00626 | B |  | 2016-02-28 | NAR | 2016-03-02 | CSE-OF-3291-009 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0065
27 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0027 | AD219-486/485-PL-00627 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
28 | BUCKLE DETECTOR DETAILS FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0028 | AD219-486/494-PL-00628 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
29 | START UP HEAD DETAILS FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0029 | AD219-486/494-PL-00629 | B |  | 2016-02-28 | NAR | 2016-03-02 | CSE-OF-3291-009 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0065
30 | LAYDOWN HEAD DETAILS FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0030 | AD219-486/494-PL-00630 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
31 | BUCKLE DETECTOR DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0031 | AD219-486/494-PL-00631 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
32 | START UP HEAD DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0032 | AD219-486/494-PL-00632 |  |  | 2016-02-28
33 | LAYDOWN HEAD DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0033 | AD219-486/494-PL-00633 |  |  | 2016-02-28
34 | BUCKLE DETECTOR DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0034 | AD219-494/486-PL-00634 | A |  | 2016-02-28 | AKS | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
35 | START UP HEAD DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0035 | AD219-494/486-PL-00635 | A |  | 2016-02-28 | AKS | 2016-02-24 | CSE-OF-3291-004 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00902
36 | LAYDOWN HEAD DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0036 | AD219-494/486-PL-00636 | A |  | 2016-02-28 | AKS | 2016-02-24 | CSE-OF-3291-004 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00902
37 | BUCKLE DETECTOR DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0037 | AD219-486/491-PL-00637 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
38 | START UP HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0038 | AD219-486/491-PL-00638 | A |  | 2016-02-28 | NAR | 2016-02-28 | CSE-OF-3291-007 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0064
39 | LAYDOWN HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0039 | AD219-486/491-PL-00639 | A |  | 2016-02-28 | NAR | 2016-02-28 | CSE-OF-3291-007 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0064
40 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0040 | AD219-486/491-PL-00640 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
41 | START UP HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0041 | AD219-486/491-PL-00641 | B |  | 2016-02-28 | NAR | 2016-03-02 | CSE-OF-3291-009 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0065
42 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0042 | AD219-486/491-PL-00642 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
43 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0043 | AD219-486/491-PL-00643 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
44 | START UP HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0044 | AD219-486/491-PL-00644 | B |  | 2016-02-28 | NAR | 2016-03-02 | CSE-OF-3291-009 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0065
45 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0045 | AD219-486/491-PL-00645 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
46 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0046 | AD219-486/490-PL-00646 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
47 | START UP HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0047 | AD219-486/490-PL-00647 | B |  | 2016-02-28 | NAR | 2016-03-02 | CSE-OF-3291-009 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0065
48 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0048 | AD219-486/490-PL-00648 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
49 | BUCKLE DETECTOR DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0049 | AD219-486/490-PL-00649 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
50 | START UP HEAD DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0050 | AD219-486/490-PL-00650 | A |  | 2016-02-28 | HZD | 2016-02-28 | CSE-OF-3291-007 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0064
51 | LAYDOWN HEAD DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0051 | AD219-486/490-PL-00651 | A |  | 2016-02-28 | HZD | 2016-02-28 | CSE-OF-3291-007 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0064
52 | BUCKLE DETECTOR DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0052 | AD219-490/486-PL-00652 | A |  | 2016-02-28 | AKS | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
53 | START UP HEAD DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0053 | AD219-490/486-PL-00653 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-003 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00900 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0060
54 | LAYDOWN HEAD DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0054 | AD219-490/486-PL-00654 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-003 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00900 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0060
55 | BUCKLE DETECTOR DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0055 | AD219-489/490-PL-00655 | A |  | 2016-02-28 | AVN | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
56 | START UP HEAD DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0056 | AD219-489/490-PL-00656 | A |  | 2016-02-28 | NAR | 2016-02-27 | CSE-OF-3291-006 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00910 |  |  |  | 2016-03-29 | 3291-NPCC-MWS-T-0046
57 | LAYDOWN HEAD DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0057 | AD219-489/490-PL-00657 | A |  | 2016-02-28 | NAR | 2016-02-27 | CSE-OF-3291-006 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00910 |  |  |  | 2016-03-29 | 3291-NPCC-MWS-T-0046
58 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0058 | AD219-490/489-PL-00658 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
59 | START UP HEAD DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0059 | AD219-490/489-PL-00659 | B |  | 2016-02-28 | HZD | 2016-03-02 | CSE-OF-3291-009 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0065
60 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0060 | AD219-490/489-PL-00660 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
61 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0061 | AD219-490/489-PL-00661 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
62 | START UP HEAD DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0062 | AD219-490/489-PL-00662 | B |  | 2016-02-28 | NAR | 2016-03-02 | CSE-OF-3291-009 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0065
63 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0063 | AD219-490/489-PL-00663 | B |  | 2016-02-28 | NAR | 2016-03-07 | CSE-OF-3291-011 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0066
64 | BUCKLE DETECTOR DETAILS FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0064 | AD219-486-PL-00664 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
65 | START UP HEAD DETAILS FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0065 | AD219-486-PL-00665 |  |  | 2016-02-28
66 | LAYDOWN HEAD DETAILS FOR 16" MAIN OIL P/L FROM NSMFT TO DAS ISLAND | 3291-NN-0066 | AD219-486-PL-00666 | B | 2 | 2016-02-28 | HZD | 2016-12-20 | CSE-OF-3291-308 | 2016-12-20 | 3291-NPCC-PMT-AO-T-02276 | 07/02/2017 30/03/2017 | 38-22701-N-T-08891 38-22701-N-T-08417 | 1 | 2016-12-20 | 3291-NPCC-MWS-T-0455
67 | BUCKLE DETECTOR DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0067 | AD219-469/486-PL-00667 | A |  | 2016-02-28 | NAR | 2016-02-23 | CSE-OF-3291-002 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0059
68 | START UP HEAD DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0068 | AD219-469/486-PL-00668 | A |  | 2016-02-28 | NAR | 2016-02-28 | CSE-OF-3291-007 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0064
69 | LAYDOWN HEAD DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0069 | AD219-469/486-PL-00669 | A |  | 2016-02-28 |  | 2016-02-28 | CSE-OF-3291-007 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914 |  |  |  | 2016-03-31 | 3291-NPCC-MWS-T-0064
|  |  |  | B | 2 |  | HZD | 2016-07-25 | CSE-OF-3291-185 | 2016-07-27 | 3291-NPCC-PMT-AO-T-01667 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-27 | 3291-NPCC-MWS-T-0259
|  |  |  | C | 2 |  | HZD | 2016-12-20 | CSE-OF-3291-308 | 2016-12-20 | 3291-NPCC-PMT-AO-T-02277 | 2017-01-22 | 38-22701-N-T-08243 | 1 | 2016-12-20 | 3291-NPCC-MWS-T-0456
70 | LOADING ARRGT & SEAFASTENING OF CC PIPES @ GAC-81 (TRIP-1) WITH BALAST PLAN | 3291-NN-0070 | AD219-705-PL-00670 | B | 2 | 2016-04-01 | NAR | 2016-03-23 | CSE-OF-3291-020 | 2016-03-28 | 3291-NPCC-PMT-AO-T-01006 | 2016-06-20 | 38-22701-N-T-06153 | 1 | 2016-03-29 | 3291-NPCC-MWS-T-0052
71 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-2) WITH BALAST PLAN | 3291-NN-0071 | AD219-705-PL-00671 | B | 2 | 2016-04-05 | REY | 2016-04-11 | CSE-OF-3291-037 | 2016-04-24 | 3291-NPCC-PMT-AO-T-01091 | 2016-05-10 | 38-22701-N-T-05581 | 1 | 2016-05-09 | 3291-NPCC-MWS-T-0116
72 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ CB-6 (TRIP-3) WITH BALAST PLAN | 3291-NN-0072 | AD219-705-PL-00672 | B |  | 2016-04-01 | REY | 2016-05-11 | CSE-OF-3291-061 | 2016-05-12 | 3291-NPCC-PMT-AO-T-01244 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-05-12 | 3291-NPCC-MWS-T-0123
73 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-4) WITH BALAST PLAN | 3291-NN-0073 | AD219-705-PL-00673 | B | 2 | 2016-04-05 | REY | 2016-05-18 | CSE-OF-3291-069 | 2016-05-18 | 3291-NPCC-PMT-AO-T-01126 | 2016-05-19 | 38-22701-N-T-05733 | 1 | 2016-05-18 | 3291-NPCC-MWS-T-0137
74 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-5) WITH BALAST PLAN | 3291-NN-0074 | AD219-705-PL-00674 | B | 2 | 2016-04-09 | REY | 2016-05-25 | CSE-OF-3291-076 | 2016-05-26 | 3291-NPCC-PMT-AO-T-01334 | 2016-06-20 | 38-22701-N-T-06153 | 1 | 2016-05-26 | 3291-NPCC-MWS-T-0149
75 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ SEAWAYS-17 (TRIP-6) WITH BALAST PLAN | 3291-NN-0075 | AD219-705-PL-00675 | B | 2 | 2016-04-13 | REY | 2016-06-08 | CSE-OF-3291-092 | 2016-06-09 | 3291-NPCC-PMT-AO-T-01410 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-06-09 | 3291-NPCC-MWS-T-0167
76 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ ASTRO-305 (TRIP-7) WITH BALAST PLAN | 3291-NN-0076 | AD219-705-PL-00676 | B | 2 | 2016-04-17 | REY | 2016-06-13 | CSE-OF-3291-100 | 2016-06-15 | 3291-NPCC-PMT-AO-T-01436 | 2016-06-30 | 38-22701-N-T-06333 | 1 | 2016-06-15 | 3291-NPCC-MWS-T-0177
77 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ SEAWAYS-17 (TRIP-8) WITH BALAST PLAN | 3291-NN-0077 | AD219-705-PL-00677 | B | 2 | 2016-04-21 |  | 2016-06-15 | CSE-OF-3291-102 | 2016-06-16 | 3291-NPCC-PMT-AO-T-01456 | 2016-06-29 | 38-22701-N-T-06291 | 1 | 2016-06-16 | 3291-NPCC-MWS-T-0179
|  |  |  | C | 2 |  | REY | 2016-06-28 | CSE-OF-3291-126 | 2016-06-29 | 3291-NPCC-PMT-AO-T-01530 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-06-29 | 3291-NPCC-MWS-T-0202
78 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ CB-6 (TRIP-9) WITH BALAST PLAN | 3291-NN-0078 | AD219-705-PL-00678 | B | 2 | 2016-04-25 | REY | 2016-07-05 | CSE-OF-3291-149 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01575 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0224
79 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-10) WITH BALAST PLAN | 3291-NN-0079 | AD219-705-PL-00679 | B | 2 | 2016-04-29 |  | 2016-08-04 | CSE-OF-3291-206 | 2016-08-07 | 3291-NPCC-PMT-AO-T-01741 |  |  |  | 2016-08-07 | 3291-NPCC-MWS-T-0284
|  |  |  | C | 2 |  | REY | 2016-08-16 | CSE-OF-3291-226 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01804 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-16 | 3291-NPCC-MWS-T-0312
80 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ CB-6 (TRIP-11) WITH BALAST PLAN | 3291-NN-0080 | AD219-705-PL-00680 | B | 2 | 2016-05-03 | REY | 2016-09-29 | CSE-OF-3291-271 | 2016-09-29 | 3291-NPCC-PMT-AO-T-02016 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-29 | 3291-NPCC-MWS-T-0388
81 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ SEAWAYS-17 (TRIP-12) WITH BALAST PLAN | 3291-NN-0081 | AD219-705-PL-00681 | B | 2 | 2016-05-07 | REY | 2016-09-29 | CSE-OF-3291-271 | 2016-09-29 | 3291-NPCC-PMT-AO-T-02016 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-29 | 3291-NPCC-MWS-T-0388
82 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-13) WITH BALAST PLAN | 3291-NN-0082 | AD219-705-PL-00682 | B | 2 | 2016-05-11 | REY | 2016-10-24 | CSE-OF-3291-283 | 2016-10-24 | 3291-NPCC-PMT-AO-T-02109 | 2016-11-06 | 38-22701-N-T-07649 | 1 | 2016-10-24 | 3291-NPCC-MWS-T-0413
83 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-14) WITH BALAST PLAN | 3291-NN-0083 | AD219-705-PL-00683 | B | 2 | 2016-05-15 | REY | 2016-10-24 | CSE-OF-3291-282 | 2016-10-24 | 3291-NPCC-PMT-AO-T-02105 | 2016-11-06 | 38-22701-N-T-07649 | 1 | 2016-10-24 | 3291-NPCC-MWS-T-0411
84 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ CB-6 (TRIP-15) WITH BALAST PLAN | 3291-NN-0084 | AD219-705-PL-00684 | B | 2 | 2016-05-19 | REY | 2016-10-25 | CSE-OF-3291-286 | 2016-10-26 | 3291-NPCC-PMT-AO-T-02113 | 2016-11-06 | 38-22701-N-T-07649 | 1 | 2016-10-26 | 3291-NPCC-MWS-T-0416
85 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ GAC-82 (TRIP-16) | 3291-NN-0085 | AD219-705-PL-00685 | B | 2 | 2016-05-23 |  | 2017-02-20 | CSE-OF-3291-316 | 2017-02-21 | 3291-NPCC-PMT-AO-T-02465 | 2017-02-22 | 38-22701-N-T-08542 | 1 | 2017-02-21 | 3291-NPCC-MWS-T-0469
86 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ GAC-81 (TRIP-17) | 3291-NN-0086 | AD219-705-PL-00686 | B | 2 | 2016-05-27 |  | 2017-02-20 | CSE-OF-3291-316 | 2017-02-21 | 3291-NPCC-PMT-AO-T-02465 | 2017-02-22 | 38-22701-N-T-08542 | 1 | 2017-02-21 | 3291-NPCC-MWS-T-0469
87 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-18) WITH BALAST PLAN | 3291-NN-0087 | AD219-705-PL-00687 |  |  | 2016-05-31
88 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-19) WITH BALAST PLAN | 3291-NN-0088 | AD219-705-PL-00688 |  |  | 2016-06-04
89 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-20) WITH BALAST PLAN | 3291-NN-0089 | AD219-705-PL-00689 |  |  | 2016-06-08
90 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-21) WITH BALAST PLAN | 3291-NN-0090 | AD219-705-PL-00690 |  |  | 2016-06-12
91 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-22) WITH BALAST PLAN | 3291-NN-0091 | AD219-705-PL-00691 |  |  | 2016-06-16
92 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-23) WITH BALAST PLAN | 3291-NN-0092 | AD219-705-PL-00692 |  |  | 2016-06-20
93 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-24) WITH BALAST PLAN | 3291-NN-0093 | AD219-705-PL-00693 |  |  | 2016-06-24
94 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-25) WITH BALAST PLAN | 3291-NN-0094 | AD219-705-PL-00694 |  |  | 2016-06-28
95 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-26) WITH BALAST PLAN | 3291-NN-0095 | AD219-705-PL-00695 |  |  | 2016-07-02
96 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-27) WITH BALAST PLAN | 3291-NN-0096 | AD219-705-PL-00696 |  |  | 2016-07-06
97 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-28) WITH BALAST PLAN | 3291-NN-0097 | AD219-705-PL-00697 |  |  | 2016-07-10
98 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-29) WITH BALAST PLAN | 3291-NN-0098 | AD219-705-PL-00698 |  |  | 2016-07-14
99 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-30) WITH BALAST PLAN | 3291-NN-0099 | AD219-705-PL-00699 |  |  | 2016-07-18
100 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS @ ZAKHER-101 (TRIP-1) WITH BALAST PLAN | 3291-NN-0100 | AD219-705-PL-00700 | B | 2 | 2016-07-22 | REY | 2016-07-03 | CSE-OF-3291-138 | 2016-07-04 | 3291-NPCC-PMT-AO-T-01554 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-07-04 | 3291-NPCC-MWS-T-0216
101 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS @ ZAKHER-101 (TRIP-2) WITH BALAST PLAN | 3291-NN-0101 | AD219-705-PL-00701 | B | 2 | 2016-07-26 | REY | 2017-03-21 | CSE-OF-3291-332 | 2017-03-22 | 3291-NPCC-PMT-AO-T-02593 | 2017-04-02 | 38-22701-N-T-08906 | 1 | 2017-03-23 | 3291-NPCC-MWS-T-0494
102 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-3) WITH BALAST PLAN | 3291-NN-0102 | AD219-705-PL-00702 |  |  | 2016-07-30
103 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-4) WITH BALAST PLAN | 3291-NN-0103 | AD219-705-PL-00703 |  |  | 2016-08-03
104 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-5) WITH BALAST PLAN | 3291-NN-0104 | AD219-705-PL-00704 |  |  | 2016-08-07
105 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-6) WITH BALAST PLAN | 3291-NN-0105 | AD219-705-PL-00705 |  |  | 2016-08-11
106 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-7) WITH BALAST PLAN | 3291-NN-0106 | AD219-705-PL-00706 |  |  | 2016-08-15
107 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-8) WITH BALAST PLAN | 3291-NN-0107 | AD219-705-PL-00707 |  |  | 2016-08-19
108 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-9) WITH BALAST PLAN | 3291-NN-0108 | AD219-705-PL-00708 |  |  | 2016-08-23
109 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-10) WITH BALAST PLAN | 3291-NN-0109 | AD219-705-PL-00709 |  |  | 2016-08-27
110 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-0110 | AD219-486/492-PL-00710 | B | 2 | 2016-09-01 | AKS | 2016-06-16 | CSE-OF-3291-105 | 2016-06-21 | 3291-NPCC-PMT-AO-T-01469 | 2016-08-09 | 38-22701-N-T-06840 | 3
111 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-0111 | AD219-486/492-PL-00711 | B | 2 | 2016-09-22 | AKS | 2016-08-10 | CSE-OF-3291-217 | 2016-08-11 | 3291-NPCC-PMT-AO-T-01773 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-11 | 3291-NPCC-MWS-T-0295
112 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-0112 | AD219-486/492-PL-00712 | B | 2 | 2016-09-04 |  | 2016-06-13 | CSE-OF-3291-098 | 2016-06-15 | 3291-NPCC-PMT-AO-T-01434 | 2016-06-29 | 38-22701-N-T-06293 | 3 | 2016-06-15 | 3291-NPCC-MWS-T-0176
|  |  |  | C |  |  | AVN | 2016-07-28 | CSE-OF-3291-195 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01699 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-28 | 3291-NPCC-MWS-T-0271
113 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-0113 | AD219-486/492-PL-00713 | B | 2 | 2016-09-25 | NAR | 2016-08-09 | CSE-OF-3291-215 | 2016-08-10 | 3291-NPCC-PMT-AO-T-01769 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-10 | 3291-NPCC-MWS-T-0293
114 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-0114 | AD219-494/493-PL-00714 | B | 2 | 2016-07-25 | AVN | 2016-08-21 | CSE-OF-3291-232 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01833 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-23 | 3291-NPCC-MWS-T-0321
115 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-0115 | AD219-494/493-PL-00715 | B | 2 | 2016-07-12 | AVN | 2016-08-03 | CSE-OF-3291-203 | 2016-08-04 | 3291-NPCC-PMT-AO-T-01735 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-04 | 3291-NPCC-MWS-T-0279
|  |  |  | C | 2 |  |  | 2016-09-19 | CSE-OF-3291-260 | 2016-09-20 | 3291-NPCC-PMT-AO-T-01955 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-20 | 3291-NPCC-MWS-T-0366
116 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-0116 | AD219-494/493-PL-00716 | B | 2 | 2016-07-28 | AKS | 2016-08-28 | CSE-OF-3291-240 | 2016-08-28 | 3291-NPCC-PMT-AO-T-01856 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-28 | 3291-NPCC-MWS-T-0329
117 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-0117 | AD219-494/493-PL-00717 | B | 2 | 2016-07-15 | AKS | 2016-08-03 | CSE-OF-3291-203 | 2016-08-04 | 3291-NPCC-PMT-AO-T-01736 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-04 | 3291-NPCC-MWS-T-0280
118 | TEMPORARY KNEE BRACE DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-8) | 3291-NN-0118 | AD219-493/494-PL-00718 | B |  | 2016-07-18 | AVN | 2016-08-04 | CSE-OF-3291-208 | 2016-08-07 | 3291-NPCC-PMT-AO-T-01745 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-07 | 3291-NPCC-MWS-T-0286
119 | TEMPORARY KNEE BRACE DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-9) | 3291-NN-0119 | AD219-493/494-PL-00719 | B | 2 | 2016-08-01 | AVN | 2016-08-22 | CSE-OF-3291-234 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01838 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-23 | 3291-NPCC-MWS-T-0323
120 | TEMPORARY KNEE BRACE DETAIL FOR 12" WF P/L FROM WHT-3 TO WHT-2 (@WHT-2) | 3291-NN-0120 | AD219-485/488-PL-00720 | B | 2 | 2016-11-01 | AVN | 2017-03-28 | CSE-OF-3291-339 | 2017-03-29 | 3291-NPCC-PMT-AO-T-02635 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-29 | 3291-NPCC-MWS-T-0506
121 | TEMPORARY KNEE BRACE DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0121 | AD219-485/488-PL-00721 | B | 2 | 2016-10-19 |  | 2017-06-13 | CSE-OF-3291-358 | 2017-06-18 | 3291-NPCC-PMT-AO-T-02993 | 2017-08-20 | 38-22701-N-T-09983 | 1 | 2017-06-18 | 3291-NPCC-MWS-T-0539
122 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-0122 | AD219-485/488-PL-00722 | B | 2 | 2016-11-04 |  | 2017-03-30 | CSE-OF-3291-344 | 2017-04-03 | 3291-NPCC-PMT-AO-T-02653 | 2017-05-02 | 38-22701-N-T-09199 | 4 | 2017-04-03 | 3291-NPCC-MWS-T-0512
123 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0123 | AD219-485/488-PL-00723 | B | 2 | 2016-10-22 |  | 2017-06-12 | CSE-OF-3291-356 | 2017-06-13 | 3291-NPCC-PMT-AO-T-02990 | 2017-08-20 | 38-22701-N-T-09983 | 1 | 2017-06-13 | 3291-NPCC-MWS-T-0537
124 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-2 ) | 3291-NN-0124 | AD219-485/488-PL-00724 | B | 2 | 2016-11-07 | AKS | 2017-03-29 | CSE-OF-3291-342 | 2017-03-30 | 3291-NPCC-PMT-AO-T-02650 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-30 | 3291-NPCC-MWS-T-0511
125 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-3 ) | 3291-NN-0125 | AD219-485/488-PL-00725 | B | 2 | 2016-10-25 |  | 2017-06-15 | CSE-OF-3291-360 | 2017-06-18 | 3291-NPCC-PMT-AO-T-03006 | 2017-08-20 | 38-22701-N-T-09983 | 1 | 2017-06-18 | 3291-NPCC-MWS-T-0540
126 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 (@NSMFT) | 3291-NN-0126 | AD219-486/485-PL-00726 | B | 2 | 2016-09-07 | AKS | 2017-02-12 | CSE-OF-3291-315 | 2017-02-13 | 3291-NPCC-PMT-AO-T-02434 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-02-13 | 3291-NPCC-MWS-T-0466
127 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 (@WHT-2) | 3291-NN-0127 | AD219-486/485-PL-00727 |  |  | 2016-11-10
128 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-0128 | AD219-486/494-PL-00728 | B | 2 | 2016-09-10 | AKS | 2017-03-05 | CSE-OF-3291-321 | 2017-03-05 | 3291-NPCC-PMT-AO-T-02507 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-03-05 | 3291-NPCC-MWS-T-0480
129 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-0129 | AD219-486/494-PL-00729 | B | 2 | 2016-10-02 | AVN | 2016-08-31 | CSE-OF-3291-245 | 2016-09-01 | 3291-NPCC-PMT-AO-T-01883 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-09-01 | 3291-NPCC-MWS-T-0335
130 | TEMPORARY KNEE BRACE DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-0130 | AD219-486/494-PL-00730 | B | 2 | 2016-09-13 | NAR | 2017-02-23 | CSE-OF-3291-317 | 2017-02-26 | 3291-NPCC-PMT-AO-T-02477 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-02-26 | 3291-NPCC-MWS-T-0470
131 | TEMPORARY KNEE BRACE DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-0131 | AD219-486/494-PL-00731 | B | 2 | 2016-10-05 | AVN | 2016-08-28 | CSE-OF-3291-242 | 2016-08-29 | 3291-NPCC-PMT-AO-T-01865 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-29 | 3291-NPCC-MWS-T-0331
132 | TEMPORARY KNEE BRACE DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT (@WHT-9) | 3291-NN-0132 | AD219-494/486-PL-00732 | B | 2 | 2016-10-08 | AVN | 2016-08-24 | CSE-OF-3291-236 | 2016-08-25 | 3291-NPCC-PMT-AO-T-01845 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-25 | 3291-NPCC-MWS-T-0325
133 | TEMPORARY KNEE BRACE DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT (@NSMFT) | 3291-NN-0133 | AD219-494/486-PL-00733 | B | 2 | 2016-09-16 |  | 2017-03-12 | CSE-OF-3291-327 | 2017-03-13 | 3291-NPCC-PMT-AO-T-02529 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-03-16 | 3291-NPCC-MWS-T-0486
134 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0134 | AD219-486/491-PL-00734 | B | 2 | 2016-09-19 | AVN | 2016-03-23 | CSE-OF-3291-022 | 2016-03-23 | 3291-NPCC-PMT-AO-T-01008 | 2016-04-18 | 38-22701-N-T-05223 | 3 | 2016-03-29 | 3291-NPCC-MWS-T-0054
|  |  |  | C | 2 |  |  | 2016-07-28 | CSE-OF-3291-195 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01693 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-28 | 3291-NPCC-MWS-T-0270
135 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0135 | AD219-486/491-PL-00735 | B | 2 | 2016-09-08 | AVN | 2016-07-14 | CSE-OF-3291-159 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01605 | 2016-07-31 | 38-22701-N-T-06705 | 1 | 2016-07-17 | 3291-NPCC-MWS-T-0234
136 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0136 | AD219-486/491-PL-00736 | B | 2 | 2016-09-22 | AVN | 2016-07-25 | CSE-OF-3291-180 | 2016-07-26 | 3291-NPCC-PMT-AO-T-01665 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-26 | 3291-NPCC-MWS-T-0257
137 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0137 | AD219-486/491-PL-00737 | B | 2 | 2016-09-11 | AVN | 2016-07-14 | CSE-OF-3291-165 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01614 | 2016-07-31 | 38-22701-N-T-06705 | 1 | 2016-07-17 | 3291-NPCC-MWS-T-0239
138 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0138 | AD219-486/491-PL-00738 | B | 2 | 2016-09-25 | AKS | 2016-07-25 | CSE-OF-3291-186 | 2016-07-27 | 3291-NPCC-PMT-AO-T-01670 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-27 | 3291-NPCC-MWS-T-0261
139 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0139 | AD219-486/491-PL-00739 | B | 2 | 2016-09-14 | AVN | 2016-07-14 | CSE-OF-3291-162 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01610 | 2016-07-31 | 38-22701-N-T-06705 | 1 | 2016-07-17 | 3291-NPCC-MWS-T-0236
140 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-0140 | AD219-486/490-PL-00740 | B | 2 | 2016-09-28 | AVN | 2016-07-26 | CSE-OF-3291-189 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01678 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-28 | 3291-NPCC-MWS-T-0263
141 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-0141 | AD219-486/490-PL-00741 | B | 2 | 2016-08-25 | AKS | 2016-07-05 | CSE-OF-3291-149 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01575 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0224
142 | TEMPORARY KNEE BRACE DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-0142 | AD219-486/490-PL-00742 | B |  | 2016-10-01 | AVN | 2016-07-26 | CSE-OF-3291-191 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01683 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-28 | 3291-NPCC-MWS-T-0266
143 | TEMPORARY KNEE BRACE DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-0143 | AD219-486/490-PL-00743 | B | 2 | 2016-08-28 | AVN | 2016-07-05 | CSE-OF-3291-152 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01577 | 2016-07-14 | 38-22701-N-T-06475 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0226
144 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT (@WHT-5) | 3291-NN-0144 | AD219-490/486-PL-00744 | B | 2 | 2016-08-31 | AVN | 2016-07-04 | CSE-OF-3291-145 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01572 | 2016-07-14 | 38-22701-N-T-06474 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0221
145 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT (@NSMFT) | 3291-NN-0145 | AD219-490/486-PL-00745 | B | 3 | 2016-10-04 | AVN | 2016-04-17 | CSE-OF-3291-043 | 2016-02-21 | 3291-NPCC-PMT-AO-T-01127 | 2016-05-08 | 38-22701-N-T-05559 | 2 | 2016-04-20 | 3291-NPCC-MWS-T-0075
|  |  |  | 0 | 3 |  |  | 2016-05-12 | CSE-OF-3291-063 | 2016-05-15 | 3291-NPCC-PMT-AO-T-01248 | 2016-05-16 | 38-22701-N-T-05707 | 1 | 2016-05-15 | 3291-NPCC-MWS-T-0128
|  |  |  | C | 3 |  | AVN | 2016-07-31 | CSE-OF-3291-199 | 2016-07-31 | 3291-NPCC-PMT-AO-T-01715 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-31 | 3291-NPCC-MWS-T-0276 |  |  |  | T-01715 - INFOR. ONLY
146 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-4) | 3291-NN-0146 | AD219-489/490-PL-00746 | B | 2 | 2016-08-07 | NAR | 2016-06-20 | CSE-OF-3291-110 | 2016-06-22 | 3291-NPCC-PMT-AO-T-01475 | 2016-06-30 | 38-22701-N-T-06347 | 1 | 2016-06-22 | 3291-NPCC-MWS-T-0185
[12 empty] | 2016-07-31 | 38-22701-N-T-06705 | 1
147 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-5) | 3291-NN-0147 | AD219-489/490-PL-00747 | B | 2 | 2016-08-20 | NAR | 2016-06-28 | CSE-OF-3291-130 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01537 | 2016-07-14 | 38-22701-N-T-06473 | 1 | 2016-06-30 | 3291-NPCC-MWS-T-0206
148 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-0148 | AD219-490/489-PL-00748 | B | 2 | 2016-08-23 | AVN | 2016-07-04 | CSE-OF-3291-140 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01561 | 2016-07-14 | 38-22701-N-T-06472 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0218
149 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-4) | 3291-NN-0149 | AD219-490/489-PL-00749 | B | 2 | 2016-08-10 | AVN | 2016-06-26 | CSE-OF-3291-120 | 2016-06-28 | 3291-NPCC-PMT-AO-T-01474 | 2016-06-30 | 38-22701-N-T-06348 | 1 | 2016-06-28 | 3291-NPCC-MWS-T-0187
[12 empty] | 2016-07-31 | 38-22701-N-T-06705 | 1
150 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-5 ) | 3291-NN-0150 | AD219-490/489-PL-00750 | B | 2 | 2016-08-26 | AVN | 2016-07-03 | CSE-OF-3291-137 | 2016-07-04 | 3291-NPCC-PMT-AO-T-01553 | 2016-07-14 | 38-22701-N-T-06471 | 1 | 2016-07-04 | 3291-NPCC-MWS-T-0215
151 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-4 ) | 3291-NN-0151 | AD219-490/489-PL-00751 | B | 2 | 2016-08-13 | AVN | 2016-06-23 | CSE-OF-3291-118 | 2016-06-26 | 3291-NPCC-PMT-AO-T-01500 | 2016-06-30 | 38-22701-N-T-06346 | 1 | 2016-06-27 | 3291-NPCC-MWS-T-0195
152 | TEMPORARY KNEE BRACE DETAILS FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT @ NSMFT | 3291-NN-0152 | AD219-486-PL-00752 | B | 2 | 2016-10-23 |  | 2017-03-07 | CSE-OF-3291-323 | 2017-03-08 | 3291-NPCC-PMT-AO-T-02513 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-03-08 | 3291-NPCC-MWS-T-0481
153 | TEMPORARY KNEE BRACE DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@ IGD-HAP) | 3291-NN-0153 | AD219-469/486-PL-00753 | B | 2 | 2016-10-16 | NAR | 2016-09-22 | CSE-OF-3291-265 | 2016-09-22 | 3291-NPCC-PMT-AO-T-01977 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-22 | 3291-NPCC-MWS-T-0375
154 | TEMPORARY KNEE BRACE DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@NSMFT) | 3291-NN-0154 | AD219-469/486-PL-00754 | B | 2 | 2016-10-26 |  | 2017-03-09 | CSE-OF-3291-325 | 2017-03-11 | 3291-NPCC-PMT-AO-T-02520 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-03-16 | 3291-NPCC-MWS-T-0484
155 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0155 | AD219-486/492-PL-00755 |  |  | 2016-10-26
156 | HYDROTEST DIAGRAM FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0156 | AD219-486/492-PL-00756 |  |  | 2016-10-26
157 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0157 | AD219-494/493-PL-00757 |  |  | 2016-10-26
158 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0158 | AD219-494/493-PL-00758 |  |  | 2016-10-26
159 | HYDROTEST DIAGRAM FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0159 | AD219-493/494-PL-00759 |  |  | 2016-10-26
160 | HYDROTEST DIAGRAM FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0160 | AD219-485/488-PL-00760 |  |  | 2016-10-26
161 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0161 | AD219-485/488-PL-00761 |  |  | 2016-10-26
162 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0162 | AD219-485/488-PL-00762 |  |  | 2016-10-26
163 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0163 | AD219-486/485-PL-00763 |  |  | 2016-10-26
164 | HYDROTEST DIAGRAM FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0164 | AD219-486/494-PL-00764 |  |  | 2016-10-26
165 | HYDROTEST DIAGRAM FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0165 | AD219-486/494-PL-00765 |  |  | 2016-10-26
166 | HYDROTEST DIAGRAM FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0166 | AD219-494/486-PL-00766 |  |  | 2016-10-26
167 | HYDROTEST DIAGRAM FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0167 | AD219-486/491-PL-00767 |  |  | 2016-10-26
168 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0168 | AD219-486/491-PL-00768 |  |  | 2016-10-26
169 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0169 | AD219-486/491-PL-00769 |  |  | 2016-10-26
170 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0170 | AD219-486/490-PL-00770 |  |  | 2016-10-26
171 | HYDROTEST DIAGRAM FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0171 | AD219-486/490-PL-00771 |  |  | 2016-10-26
172 | HYDROTEST DIAGRAM FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0172 | AD219-490/486-PL-00772 |  |  | 2016-10-26
173 | HYDROTEST DIAGRAM FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0173 | AD219-489/490-PL-00773 |  |  | 2016-10-26
174 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0174 | AD219-490/489-PL-00774 |  |  | 2016-10-26
175 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0175 | AD219-490/489-PL-00775 |  |  | 2016-10-26
176 | HYDROTEST DIAGRAM FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0176 | AD219-486-PL-00776 |  |  | 2016-10-26
177 | HYDROTEST DIAGRAM FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0177 | AD219-469/486-PL-00777 |  |  | 2016-10-26
178 | DETAIL OF 6" TEMPORARY PIG LAUNCHER 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0178 | AD219-486/492-PL-00778 | B | 2 | 2016-09-01 | NAR | 2018-08-14 | CSE-OF-3291-375 | 2020-04-02 | 3291-NPCC-PMT-AO-T-04345 | 2020-08-12 | 38-22701-N-T-12025 | 4 |  | 3291-NPCC-MWS-T-0608
179 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0179 | AD219-486/492-PL-00779 |  |  | 2016-09-04
180 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0180 | AD219-494/493-PL-00780 |  |  | 2016-07-12
181 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0181 | AD219-494/493-PL-00781 |  |  | 2016-07-15
182 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0182 | AD219-493/494-PL-00782 |  |  | 2016-07-18
183 | DETAIL OF 12" TEMPORARY PIG LAUNCHER 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0183 | AD219-485/488-PL-00783 | B | 2 | 2016-10-19 | AKS | 2018-08-14 | CSE-OF-3291-375 | 2020-04-02 | 3291-NPCC-PMT-AO-T-04345 | 2020-08-12 | 38-22701-N-T-12025 | 4 |  | 3291-NPCC-MWS-T-0608
184 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0184 | AD219-485/488-PL-00784 |  |  | 2016-10-22
185 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0185 | AD219-485/488-PL-00785 |  |  | 2016-10-25
186 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0186 | AD219-486/485-PL-00786 |  |  | 2016-09-07
187 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0187 | AD219-486/494-PL-00787 |  |  | 2016-09-10
188 | DETAIL OF 8" TEMPORARY PIG LAUNCHER 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0188 | AD219-486/494-PL-00788 | B | 2 | 2016-09-13 | NAR | 2018-08-14 | CSE-OF-3291-375 | 2020-04-02 | 3291-NPCC-PMT-AO-T-04345 | 2020-08-12 | 38-22701-N-T-12025 | 4 |  | 3291-NPCC-MWS-T-0608
189 | DETAIL OF 14" TEMPORARY PIG LAUNCHER14" WF P/L FROM WHT-9 TO NSMFT | 3291-NN-0189 | AD219-494/486-PL-00789 | B | 2 | 2016-09-16 | AKS | 2018-08-14 | CSE-OF-3291-375 | 2020-04-02 | 3291-NPCC-PMT-AO-T-04345 | 2020-08-12 | 38-22701-N-T-12025 | 4 |  | 3291-NPCC-MWS-T-0608
190 | DETAIL OF 10" TEMPORARY PIG LAUNCHER 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0190 | AD219-486/491-PL-00790 | B | 2 | 2016-09-08 | AKS | 2018-08-14 | CSE-OF-3291-375 | 2020-04-02 | 3291-NPCC-PMT-AO-T-04345 | 2020-08-12 | 38-22701-N-T-12025 | 4 |  | 3291-NPCC-MWS-T-0608
191 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0191 | AD219-486/491-PL-00791 |  |  | 2016-09-11
192 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0192 | AD219-486/491-PL-00792 |  |  | 2016-09-14
193 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0193 | AD219-486/490-PL-00793 |  |  | 2016-08-25
194 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0194 | AD219-486/490-PL-00794 |  |  | 2016-08-28
195 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0195 | AD219-490/486-PL-00795 |  |  | 2016-08-31
196 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0196 | AD219-489/490-PL-00796 |  |  | 2016-08-07
197 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0197 | AD219-490/489-PL-00797 |  |  | 2016-08-10
198 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0198 | AD219-490/489-PL-00798 |  |  | 2016-08-13
199 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0199 | AD219-486-PL-00799 |  |  | 2016-10-23
200 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0200 | AD219-469/486-PL-00800 |  |  | 2016-10-16
201 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-0201 | AD219-486/492-PL-00801 | B | 2 | 2016-09-01 | AKS | 2016-06-16 | CSE-OF-3291-105 | 2016-06-21 | 3291-NPCC-PMT-AO-T-01469 | 2016-08-09 | 38-22701-N-T-06840 | 3
|  |  |  | C | 2 |  |  | 2016-07-21 | CSE-OF-3291-178 | 2016-07-24 | 3291-NPCC-PMT-AO-T-01653 | 2016-08-09 | 38-22701-N-T-06842 | 1 | 2016-07-24 | 3291-NPCC-MWS-T-0253
|  |  |  | D | 2 |  | CDG | 2016-08-15 | CSE-OF-3291-222 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01795 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-16 | 3291-NPCC-MWS-T-0304
|  |  |  | 0 | 1 |  |  | 2016-09-01 | CSE-OF-3291-247 | 2016-09-04 | 3291-NPCC-PMT-AO-T-01893 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-04 | 3291-NPCC-MWS-T-0339
202 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-0202 | AD219-486/492-PL-00802 | B | 2 | 2016-09-22 | AKS | 2016-08-10 | CSE-OF-3291-217 | 2016-08-11 | 3291-NPCC-PMT-AO-T-01773 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-11 | 3291-NPCC-MWS-T-0295
|  |  |  | C | 2 |  | HZD | 2017-03-26 | CSE-OF-3291-337 | 2017-03-27 | 3291-NPCC-PMT-AO-T-02622 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-27 | 3291-NPCC-MWS-T-0501
203 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WF P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-0203 | AD219-486/492-PL-00803 | B | 2 | 2016-09-04 | AKS | 2016-06-13 | CSE-OF-3291-098 | 2016-06-15 | 3291-NPCC-PMT-AO-T-01434 | 2016-06-29 | 38-22701-N-T-06293 | 3 | 2016-06-15 | 3291-NPCC-MWS-T-0176
|  |  |  | C |  |  | CDG | 2016-07-28 | CSE-OF-3291-195 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01699 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-28 | 3291-NPCC-MWS-T-0271
|  |  |  | D | 2 |  |  | 2016-08-15 | CSE-OF-3291-222 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01795 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-16 | 3291-NPCC-MWS-T-0304
|  |  |  | 0 | 1 |  |  | 2016-09-01 | CSE-OF-3291-247 | 2016-09-04 | 3291-NPCC-PMT-AO-T-01893 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-04 | 3291-NPCC-MWS-T-0339
|  |  |  | 1 | 1 |  | ANN | 2016-09-08 | CSE-OF-3291-253 | 2016-09-14 | 3291-NPCC-PMT-AO-T-01920 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-14 | 3291-NPCC-MWS-T-0354
204 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WF P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-0204 | AD219-486/492-PL-00804 | B | 2 | 2016-09-25 | AKS | 2016-08-09 | CSE-OF-3291-215 | 2016-08-10 | 3291-NPCC-PMT-AO-T-01769 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-10 | 3291-NPCC-MWS-T-0293
|  |  |  | C |  |  | CDG | 2017-03-26 | CSE-OF-3291-337 | 2017-03-27 | 3291-NPCC-PMT-AO-T-02622 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-27 | 3291-NPCC-MWS-T-0501
205 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-0205 | AD219-494/493-PL-00805 | B | 2 | 2016-07-25 | CDG | 2016-08-21 | CSE-OF-3291-232 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01833 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-23 | 3291-NPCC-MWS-T-0321
206 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-0206 | AD219-494/493-PL-00806 | B | 2 | 2016-07-12 | NAR | 2016-08-03 | CSE-OF-3291-203 | 2016-08-04 | 3291-NPCC-PMT-AO-T-01735 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-04 | 3291-NPCC-MWS-T-0279
|  |  |  | C | 2 |  | AKS | 2016-09-04 | CSE-OF-3291-249 | 2016-09-06 | 3291-NPCC-PMT-AO-T-01901 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-09-06 | 3291-NPCC-MWS-T-0345
|  |  |  | D | 1 |  |  | 2016-09-28 | CSE-OF-3291-270 | 2016-09-29 | 3291-NPCC-PMT-AO-T-02007 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-29 | 3291-NPCC-MWS-T-0383
207 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-0207 | AD219-494/493-PL-00807 | B | 2 | 2016-07-28 | AKS | 2016-08-28 | CSE-OF-3291-240 | 2016-08-28 | 3291-NPCC-PMT-AO-T-01856 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-28 | 3291-NPCC-MWS-T-0329
208 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-0208 | AD219-494/493-PL-00808 | B | 2 | 2016-07-15 | AKS | 2016-08-03 | CSE-OF-3291-203 | 2016-08-04 | 3291-NPCC-PMT-AO-T-01736 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-04 | 3291-NPCC-MWS-T-0280
|  |  |  | C | 2 |  | HZD | 2016-09-04 | CSE-OF-3291-249 | 2016-09-06 | 3291-NPCC-PMT-AO-T-01901 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-09-06 | 3291-NPCC-MWS-T-0345
|  |  |  | D | 1 |  | HZD | 2016-09-28 | CSE-OF-3291-270 | 2016-09-29 | 3291-NPCC-PMT-AO-T-02007 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-29 | 3291-NPCC-MWS-T-0383
209 | RISER/SPOOL LIFTING AND INSTALLATION FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-8) | 3291-NN-0209 | AD219-493/494-PL-00809 | B | 2 | 2016-07-18 | AKS | 2016-08-04 | CSE-OF-3291-208 | 2016-08-07 | 3291-NPCC-PMT-AO-T-01745 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-07 | 3291-NPCC-MWS-T-0286
|  |  |  | C | 2 |  | HZD | 2016-09-04 | CSE-OF-3291-249 | 2016-09-06 | 3291-NPCC-PMT-AO-T-01901 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-09-06 | 3291-NPCC-MWS-T-0345
|  |  |  | D | 1 |  |  | 2016-09-28 | CSE-OF-3291-270 | 2016-09-29 | 3291-NPCC-PMT-AO-T-02007 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-29 | 3291-NPCC-MWS-T-0383
210 | RISER/SPOOL LIFTING AND INSTALLATION FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-9) | 3291-NN-0210 | AD219-493/494-PL-00810 | B | 2 | 2016-08-01 | AKS | 2016-08-22 | CSE-OF-3291-234 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01838 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-23 | 3291-NPCC-MWS-T-0323
211 | RISER/SPOOL LIFTING AND INSTALLATION FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-0211 | AD219-485/488-PL-00811 | B | 2 | 2016-11-01 |  | 2017-03-28 | CSE-OF-3291-339 | 2017-03-29 | 3291-NPCC-PMT-AO-T-02635 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-29 | 3291-NPCC-MWS-T-0506
212 | RISER/SPOOL LIFTING AND INSTALLATION FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0212 | AD219-485/488-PL-00812 | B | 2 | 2016-10-19 |  | 2017-06-13 | CSE-OF-3291-358 | 2017-06-18 | 3291-NPCC-PMT-AO-T-02993 | 2017-08-20 | 38-22701-N-T-09983 | 1 | 2017-06-18 | 3291-NPCC-MWS-T-0539
|  |  |  | C | 2 |  |  | 2017-11-06 | CSE-OF-3291-366 | 2017-11-08 | 3291-NPCC-PMT-AO-T-03448 |  |  |  | 2017-11-07 | 3291-NPCC-MWS-T-0573
|  |  |  | D | 2 |  |  | 2017-11-08 | CSE-OF-3291-368 | 2017-11-09 | 3291-NPCC-PMT-AO-T-03451 | 2018-08-05 | 38-22701-N-T-11401 | 1 | 2017-11-09 | 3291-NPCC-MWS-T-0575 | 2017-11-12 | MDDXB-5171-MD- 343-4456-01 | APPROVED
213 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-0213 | AD219-485/488-PL-00813 | B | 2 | 2016-11-04 | HZD | 2017-03-29 | CSE-OF-3291-340 | 2017-03-30 | 3291-NPCC-PMT-AO-T-02641 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-30 | 3291-NPCC-MWS-T-0509
214 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0214 | AD219-485/488-PL-00814 | B | 2 | 2016-10-22 |  | 2017-06-12 | CSE-OF-3291-356 | 2017-06-13 | 3291-NPCC-PMT-AO-T-02990 | 2017-08-20 | 38-22701-N-T-09983 | 1 | 2017-06-13 | 3291-NPCC-MWS-T-0537
|  |  |  | C | 2 |  |  | 2017-11-06 | CSE-OF-3291-366 | 2017-11-08 | 3291-NPCC-PMT-AO-T-03448 | 2018-08-05 | 38-22701-N-T-11401 | 1 | 2017-11-07 | 3291-NPCC-MWS-T-0573 | 2017-11-12 | MDDXB-5171-MD- 344-4457-01 | APPROVED
215 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-0215 | AD219-485/488-PL-00815 | B | 2 | 2016-11-07 | CDG | 2017-03-29 | CSE-OF-3291-342 | 2017-03-30 | 3291-NPCC-PMT-AO-T-02650 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-30 | 3291-NPCC-MWS-T-0511
216 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0216 | AD219-485/488-PL-00816 | B | 2 | 2016-10-25 |  | 2017-06-15 | CSE-OF-3291-360 | 2017-06-18 | 3291-NPCC-PMT-AO-T-03006 | 2017-08-20 | 38-22701-N-T-09983 | 1 | 2017-06-18 | 3291-NPCC-MWS-T-0540
|  |  |  | C | 2 |  |  | 2017-11-06 | CSE-OF-3291-366 | 2017-11-08 | 3291-NPCC-PMT-AO-T-03448 | 2018-08-05 | 38-22701-N-T-11401 | 1 | 2017-11-07 | 3291-NPCC-MWS-T-0573 | 2017-11-12 | MDDXB-5171-MD- 345-4458-01 | APPROVED
217 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-2 (@NSMFT) | 3291-NN-0217 | AD219-486/485-PL-00817 | B | 2 | 2016-09-07 | HZD | 2017-02-12 | CSE-OF-3291-315 | 2017-02-13 | 3291-NPCC-PMT-AO-T-02434 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-02-13 | 3291-NPCC-MWS-T-0466
|  |  |  | C | 2 |  | CDG | 2017-03-27 | CSE-OF-3291-338 | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-28 | 3291-NPCC-MWS-T-0504
218 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-2 (@WHT-2) | 3291-NN-0218 | AD219-486/485-PL-00818 | B | 2 | 2016-11-10 | AKS/CDG | 2017-03-23 | CSE-OF-3291-334 | 2017-03-24 | 3291-NPCC-PMT-AO-T-02608 |  |  |  | 2017-03-24 | 3291-NPCC-MWS-T-0496
|  |  |  | C | 2 |  | HZD | 2017-03-27 | CSE-OF-3291-338 | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-28 | 3291-NPCC-MWS-T-0504
219 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-0219 | AD219-486/494-PL-00819 | B | 2 | 2016-09-10 | AKS | 2017-03-05 | CSE-OF-3291-321 | 2017-03-05 | 3291-NPCC-PMT-AO-T-02507 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-03-05 | 3291-NPCC-MWS-T-0480
|  |  |  | C | 2 |  | AKS | 2017-03-27 | CSE-OF-3291-338 | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-28 | 3291-NPCC-MWS-T-0504
220 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-0220 | AD219-486/494-PL-00820 | B | 2 | 2016-10-02 | AKS | 2016-08-31 | CSE-OF-3291-245 | 2016-09-01 | 3291-NPCC-PMT-AO-T-01883 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-09-01 | 3291-NPCC-MWS-T-0335
|  |  |  | C | 1 |  |  | 2016-09-28 | CSE-OF-3291-269 | 2016-09-28 | 3291-NPCC-PMT-AO-T-02005 | 2016-12-25 | 38-22701-N-T-08083 | 1 | 2016-09-28 | 3291-NPCC-MWS-T-0382
221 | RISER/SPOOL LIFTING AND INSTALLATION FOR 8" WI P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-0221 | AD219-486/494-PL-00821 | B | 2 | 2016-09-13 | CDG | 2017-02-23 | CSE-OF-3291-317 | 2017-02-26 | 3291-NPCC-PMT-AO-T-02477 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-02-26 | 3291-NPCC-MWS-T-0470
|  |  |  | C | 2 |  | AKS | 2017-03-27 | CSE-OF-3291-338 | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-28 | 3291-NPCC-MWS-T-0504
222 | RISER/SPOOL LIFTING AND INSTALLATION FOR 8" WI P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-0222 | AD219-486/494-PL-00822 | B | 2 | 2016-10-05 | NAR | 2016-08-28 | CSE-OF-3291-242 | 2016-08-29 | 3291-NPCC-PMT-AO-T-01865 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-29 | 3291-NPCC-MWS-T-0331
|  |  |  | 0 | 1 |  | NAR | 2016-12-04 | CSE-OF-3291-305 | 2016-12-05 | 3291-NPCC-PMT-AO-T-02230 | 2016-12-25 | 38-22701-N-T-08083 | 1 | 2016-12-05 | 3291-NPCC-MWS-T-0452
223 | RISER/SPOOL LIFTING AND INSTALLATION FOR 14" WF P/L FROM WHT-9 TO NSMFT (@WHT-9) | 3291-NN-0223 | AD219-494/486-PL-00823 | B | 2 | 2016-10-08 | AKS | 2016-08-24 | CSE-OF-3291-236 | 2016-08-25 | 3291-NPCC-PMT-AO-T-01845 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-25 | 3291-NPCC-MWS-T-0325
224 | RISER/SPOOL LIFTING AND INSTALLATION FOR WF 14" P/L FROM WHT-9 TO NSMFT (@NSMFT) | 3291-NN-0224 | AD219-494/486-PL-00824 | B | 2 | 2016-09-16 |  | 2017-03-12 | CSE-OF-3291-327 | 2017-03-13 | 3291-NPCC-PMT-AO-T-02529 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-03-16 | 3291-NPCC-MWS-T-0486
|  |  |  | C | 2 |  | AKS | 2017-03-27 | CSE-OF-3291-338 | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-28 | 3291-NPCC-MWS-T-0504
225 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WF P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0225 | AD219-486/491-PL-00825 | B | 2 | 2016-09-19 | AKS | 2016-03-23 | CSE-OF-3291-022 | 2016-03-23 | 3291-NPCC-PMT-AO-T-01008 | 2016-04-18 | 38-22701-N-T-05223 | 3 | 2016-03-29 | 3291-NPCC-MWS-T-0054
|  |  |  | C | 2 |  |  | 2016-07-28 | CSE-OF-3291-195 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01693 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-28 | 3291-NPCC-MWS-T-0270
|  |  |  | D | 2 |  |  | 2016-08-15 | CSE-OF-3291-222 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01795 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-16 | 3291-NPCC-MWS-T-0304
|  |  |  | 0 | 1 |  | AKS | 2016-09-01 | CSE-OF-3291-247 | 2016-09-04 | 3291-NPCC-PMT-AO-T-01893 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-04 | 3291-NPCC-MWS-T-0339
226 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WF P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0226 | AD219-486/491-PL-00826 | B | 2 | 2016-09-08 | AKS | 2016-07-14 | CSE-OF-3291-159 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01605 | 2016-07-31 | 38-22701-N-T-06705 | 1 | 2016-07-17 | 3291-NPCC-MWS-T-0234
|  |  |  | 0 | 1 |  | AKS | 2016-09-04 | CSE-OF-3291-248 | 2016-09-05 | 3291-NPCC-PMT-AO-T-01899 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-05 | 3291-NPCC-MWS-T-0343
227 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0227 | AD219-486/491-PL-00827 | B | 2 | 2016-09-22 | NAR | 2016-07-25 | CSE-OF-3291-180 | 2016-07-26 | 3291-NPCC-PMT-AO-T-01665 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-26 | 3291-NPCC-MWS-T-0257
|  |  |  | C | 2 |  |  | 2016-08-15 | CSE-OF-3291-222 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01795 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-16 | 3291-NPCC-MWS-T-0304
228 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0228 | AD219-486/491-PL-00828 | B | 2 | 2016-09-11 | AKS | 2016-07-14 | CSE-OF-3291-165 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01614 | 2016-07-31 | 38-22701-N-T-06705 | 1 | 2016-07-17 | 3291-NPCC-MWS-T-0239
|  |  |  | 0 | 1 |  | NAR | 2016-11-23 | CSE-OF-3291-301 | 2016-11-23 | 3291-NPCC-PMT-AO-T-02195 | 2016-12-25 | 38-22701-N-T-08083 | 1 | 2016-11-23 | 3291-NPCC-MWS-T-0442
229 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0229 | AD219-486/491-PL-00829 | B | 2 | 2016-09-25 | AKS | 2016-07-25 | CSE-OF-3291-186 | 2016-07-27 | 3291-NPCC-PMT-AO-T-01670 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-27 | 3291-NPCC-MWS-T-0261
|  |  |  | C | 2 |  | CDG | 2016-08-15 | CSE-OF-3291-222 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01795 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-16 | 3291-NPCC-MWS-T-0304
|  |  |  | 0 | 1 |  | AKS | 2016-09-01 | CSE-OF-3291-247 | 2016-09-04 | 3291-NPCC-PMT-AO-T-01893 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-04 | 3291-NPCC-MWS-T-0339
230 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0230 | AD219-486/491-PL-00830 | B | 2 | 2016-09-14 | AKS | 2016-07-14 | CSE-OF-3291-162 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01610 | 2016-07-31 | 38-22701-N-T-06705 | 1 | 2016-07-17 | 3291-NPCC-MWS-T-0236
|  |  |  | 0 | 1 |  | AKS | 2016-09-04 | CSE-OF-3291-248 | 2016-09-05 | 3291-NPCC-PMT-AO-T-01899 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-05 | 3291-NPCC-MWS-T-0343
|  |  |  | 1 | 1 |  |  | 2016-11-06 | CSE-OF-3291-289 | 2016-11-07 | 3291-NPCC-PMT-AO-T-02139 | 2016-12-25 | 38-22701-N-T-08083 | 1 | 2016-11-07 | 3291-NPCC-MWS-T-0420
231 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-0231 | AD219-486/490-PL-00831 | B | 2 | 2016-09-28 | AVN | 2016-07-26 | CSE-OF-3291-189 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01678 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-28 | 3291-NPCC-MWS-T-0263
|  |  |  | C | 2 |  | CDG | 2016-08-15 | CSE-OF-3291-222 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01795 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-16 | 3291-NPCC-MWS-T-0304
|  |  |  | 0 | 1 |  | AKS | 2016-09-01 | CSE-OF-3291-247 | 2016-09-04 | 3291-NPCC-PMT-AO-T-01893 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-04 | 3291-NPCC-MWS-T-0339
232 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-0232 | AD219-486/490-PL-00832 | B | 2 | 2016-08-25 | HZD | 2016-07-05 | CSE-OF-3291-149 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01575 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0224
|  |  |  | 0 | 1 |  |  | 2016-09-04 | CSE-OF-3291-248 | 2016-09-05 | 3291-NPCC-PMT-AO-T-01899 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-05 | 3291-NPCC-MWS-T-0343
|  |  |  | 1 | 1 |  |  | 2016-11-06 | CSE-OF-3291-289 | 2016-11-07 | 3291-NPCC-PMT-AO-T-02139 | 2016-12-25 | 38-22701-N-T-08083 | 1 | 2016-11-07 | 3291-NPCC-MWS-T-0420
233 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WI P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-0233 | AD219-486/490-PL-00833 | B | 2 | 2016-10-01 | CDG | 2016-07-26 | CSE-OF-3291-191 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01683 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-07-28 | 3291-NPCC-MWS-T-0266
|  |  |  | C | 2 |  | CDG | 2016-08-15 | CSE-OF-3291-222 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01795 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-16 | 3291-NPCC-MWS-T-0304
|  |  |  | 0 | 1 |  |  | 2016-09-01 | CSE-OF-3291-247 | 2016-09-04 | 3291-NPCC-PMT-AO-T-01893 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-04 | 3291-NPCC-MWS-T-0339
|  |  |  | 1 | 1 |  | AKS | 2016-09-08 | CSE-OF-3291-253 | 2016-09-14 | 3291-NPCC-PMT-AO-T-01920 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-14 | 3291-NPCC-MWS-T-0354
234 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WI P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-0234 | AD219-486/490-PL-00834 | B | 2 | 2016-08-28 | CDG | 2016-07-05 | CSE-OF-3291-152 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01577 | 2016-07-14 | 38-22701-N-T-06475 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0226
|  |  |  | 0 | 1 |  | AVN | 2016-10-24 | CSE-OF-3291-284 | 2016-10-26 | 3291-NPCC-PMT-AO-T-02111 | 2016-11-06 | 38-22701-N-T-07648 | 1 | 2016-10-26 | 3291-NPCC-MWS-T-0414
235 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" WF P/L FROM WHT-5 TO NSMFT (@WHT-5) | 3291-NN-0235 | AD219-490/486-PL-00835 | B | 2 | 2016-08-31 | CDG | 2016-07-04 | CSE-OF-3291-145 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01572 | 2016-07-14 | 38-22701-N-T-06474 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0221
|  |  |  | 0 | 1 |  | CDG | 2016-10-18 | CSE-OF-3291-278 | 2016-10-19 | 3291-NPCC-PMT-AO-T-02087 | 2016-11-06 | 38-22701-N-T-07648 | 1 | 2016-10-19 | 3291-NPCC-MWS-T-0401
236 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" WF P/L FROM WHT-5 TO NSMFT (@NSMFT) | 3291-NN-0236 | AD219-490/486-PL-00836 | B | 2 | 2016-10-04 | NAR | 2016-04-17 | CSE-OF-3291-042 | 2016-06-07 | 3291-NPCC-PMT-AO-T-01398 | 2016-06-20 | 38-22701-N-T-06162 | 3 | 2016-04-21 | 3291-NPCC-MWS-T-0077
|  |  |  | C |  |  |  | 2016-07-31 | CSE-OF-3291-199 | 2016-07-31 | 3291-NPCC-PMT-AO-T-01713 |  |  |  | 2016-07-31 | 3291-NPCC-MWS-T-0275
|  |  |  | D | 2 |  | HZD | 2016-08-16 | CSE-OF-3291-224 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01798 |  |  |  | 2016-08-16 | 3291-NPCC-MWS-T-0307
|  |  |  | 0 | 1 |  |  | 2016-09-01 | CSE-OF-3291-247 | 2016-09-04 | 3291-NPCC-PMT-AO-T-01893 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-09-04 | 3291-NPCC-MWS-T-0339
|  |  |  | 1 | 1 |  | AKS | 2016-09-19 | CSE-OF-3291-260 | 2016-09-20 | 3291-NPCC-PMT-AO-T-01953 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-20 | 3291-NPCC-MWS-T-0365
237 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-4) | 3291-NN-0237 | AD219-489/490-PL-00837 | B | 2 | 2016-08-07 | HZD | 2016-06-20 | CSE-OF-3291-110 | 2016-06-22 | 3291-NPCC-PMT-AO-T-01475 | 2016-07-31 | 38-22701-N-T-06705 | 1 | 2016-06-22 | 3291-NPCC-MWS-T-0185
|  |  |  | 0 | 1 |  | AKS | 2016-11-20 | CSE-OF-3291-299 | 2016-11-21 | 3291-NPCC-PMT-AO-T-02175 | 2016-12-25 | 38-22701-N-T-08083 | 1 | 2016-11-21 | 3291-NPCC-MWS-T-0436
238 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-5) | 3291-NN-0238 | AD219-489/490-PL-00838 | B | 2 | 2016-08-20 | HZD | 2016-06-28 | CSE-OF-3291-130 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01537 | 2016-07-14 | 38-22701-N-T-06473 | 1 | 2016-06-30 | 3291-NPCC-MWS-T-0206
|  |  |  | 0 | 1 |  | HZD | 2016-08-08 | CSE-OF-3291-211 | 2016-08-09 | 3291-NPCC-PMT-AO-T-01762 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-09 | 3291-NPCC-MWS-T-0289
239 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-0239 | AD219-490/489-PL-00839 | B | 2 | 2016-08-23 | HZD | 2016-07-04 | CSE-OF-3291-140 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01561 | 2016-07-14 | 38-22701-N-T-06472 | 1 | 2016-07-10 | 3291-NPCC-MWS-T-0218
240 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-4) | 3291-NN-0240 | AD219-490/489-PL-00840 | B | 2 | 2016-08-10 | AKS | 2016-06-20 | CSE-OF-3291-120 | 2016-06-28 | 3291-NPCC-PMT-AO-T-01474 | 2016-07-31 | 38-22701-N-T-06705 | 1 | 2016-06-28 | 3291-NPCC-MWS-T-0187
|  |  |  | 0 | 1 |  | NAR | 2016-11-16 | CSE-OF-3291-296 | 2016-11-17 | 3291-NPCC-PMT-AO-T-02164 | 2016-11-17 | 38-22701-N-T-07750 | 1 | 2016-11-17 | 3291-NPCC-MWS-T-0432
241 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-0241 | AD219-490/489-PL-00841 | B | 2 | 2016-08-26 | AKS | 2016-07-03 | CSE-OF-3291-137 | 2016-07-04 | 3291-NPCC-PMT-AO-T-01553 | 2016-07-14 | 38-22701-N-T-06471 | 1 | 2016-07-04 | 3291-NPCC-MWS-T-0215
|  |  |  | 0 | 1 |  | NAR | 2016-11-14 | CSE-OF-3291-295 | 2016-11-15 | 3291-NPCC-PMT-AO-T-02160 | 2016-12-25 | 38-22701-N-T-08083 | 1 | 2016-11-15 | 3291-NPCC-MWS-T-0430
242 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-4) | 3291-NN-0242 | AD219-490/489-PL-00842 | B | 2 | 2016-08-13 | AKS | 2016-06-23 | CSE-OF-3291-118 | 2016-06-26 | 3291-NPCC-PMT-AO-T-01500 | 2016-06-30 | 38-22701-N-T-06346 | 1 | 2016-06-27 | 3291-NPCC-MWS-T-0195
243 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0243 | AD219-486-PL-00843 | B | 2 | 2016-10-23 |  | 2017-03-07 | CSE-OF-3291-323 | 2017-03-08 | 3291-NPCC-PMT-AO-T-02513 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-03-08 | 3291-NPCC-MWS-T-0481
|  |  |  | C | 2 |  | CDG | 2017-03-27 | CSE-OF-3291-338 | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-28 | 3291-NPCC-MWS-T-0504
244 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@IGD-HAP) | 3291-NN-0244 | AD219-469/486-PL-00844 | B | 2 | 2016-10-16 |  | 2016-09-22 | CSE-OF-3291-265 | 2016-09-22 | 3291-NPCC-PMT-AO-T-01977 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-22 | 3291-NPCC-MWS-T-0375
|  |  |  | C | 1 |  |  | 2016-10-10 | CSE-OF-3291-275 | 2016-10-12 | 3291-NPCC-PMT-AO-T-01992 |  |  |  | 2016-10-12 | 3291-NPCC-MWS-T-0378
|  |  |  | D | 2 |  | HZD | 2016-10-13 | CSE-OF-3291-276 | 2016-10-16 | 3291-NPCC-PMT-AO-T-02074 |  |  |  | 2016-10-16 | 3291-NPCC-MWS-T-0398
|  |  |  | 0 | 1 |  |  | 2016-10-26 | CSE-OF-3291-287 | 2016-10-30 | 3291-NPCC-PMT-AO-T-02117 | 2016-11-30 | 38-22701-N-T-07606 | 1 | 2016-10-30 | 3291-NPCC-MWS-T-0417
245 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@NSMFT) | 3291-NN-0245 | AD219-469/486-PL-00845 | B | 2 | 2016-10-26 |  | 2017-03-09 | CSE-OF-3291-325 | 2017-03-11 | 3291-NPCC-PMT-AO-T-02520 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-03-16 | 3291-NPCC-MWS-T-0484
|  |  |  | C | 2 |  | AKS | 2017-03-27 | CSE-OF-3291-338 | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-28 | 3291-NPCC-MWS-T-0504
246 | TYPICAL LIFITNG AND INSTALLATION OF RCC SLEEPER AT NEAR IGD-HAP PLATFORM USING SWIBER ATLANTIS | 3291-NN-0246 | AD219-469-PL-00846 | B | 2 | SUBMITTED | HZD | 2016-03-20 | CSE-OF-3291-016 | 2016-03-21 | 3291-NPCC-PMT-AO-T-00982 | 2016-08-24 | 38-22701-N-T-06997 | 4 | 2016-03-29 | 3291-NPCC-MWS-T-0049
|  |  |  | C | 2 |  |  | 2016-03-27 | CSE-OF-3291-026 | 2016-04-05 | 3291-NPCC-PMT-AO-T-01012 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-03-29 | 3291-NPCC-MWS-T-0056
|  |  |  | D | 2 | SUBMITTED | HZD | 2016-04-11 | CSE-OF-3291-038 | 2016-04-24 | 3291-NPCC-PMT-AO-T-01094 | 2016-05-02 | 38-22701-N-T-05390 | 1 | 2016-04-13 | 3291-NPCC-MWS-T-0097 | 2016-04-13 | MDDXB-5171- MD-063-1827-01 | Accepted
247 | LOADING ARRGT & SEAFASTENING DETAILS OF RCC SLEEPERS BY MICHLYN-285 (TRIP-1) | 3291-NN-0247 | AD219-705-PL-00847 | B | 2 | SUBMITTED | NAR | 2016-03-16 | CSE-OF-3291-014 | 2016-03-17 | 3291-NPCC-PMT-AO-T-00971 | 2016-03-27 | 38-22701-N-T-04773 | 2 | 2016-03-31 | 3291-NPCC-MWS-T-0067
|  |  |  | C | 2 |  |  | 2016-03-27 | CSE-OF-3291-026 | 2016-04-05 | 3291-NPCC-PMT-AO-T-01012 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-03-29 | 3291-NPCC-MWS-T-0056
|  |  |  | D | 2 | SUBMITTED | REY | 2016-04-11 | CSE-OF-3291-037 | 2016-04-24 | 3291-NPCC-PMT-AO-T-01088 | 2016-05-08 | 38-22701-N-T-05580 | 1 | 2016-05-09 | 3291-NPCC-MWS-T-0115
248 | LOADING ARRGT & SEAFASTENING DETAILS OF RCC SLEEPERS BY MICHLYN-285 (TRIP-2) | 3291-NN-0248 | AD219-705-PL-00848 | B | 2 | SUBMITTED | NAR | 2016-04-19 | CSE-OF-3291-046 | 2016-04-21 | 3291-NPCC-PMT-AO-T-01143 | 2016-05-08 | 38-22701-N-T-05535 | 1 | 2016-05-09 | 3291-NPCC-MWS-T-0114
249 | LOADING ARRANGEMENT & SEAFASTENING OF WHT-6 PILES | 3291-NN-0249 | AD219-491-PL-00849 |  |  | REY
250 | TYPICAL LIFTING AND INSTALLATION OF RCC SLEEPER 18" WELL FLUID PIPELINE (WHT-4 TO WHT-5) CX-01 | 3291-NN-0250 | AD219-489/490-PL-00850 | B | 2 | SUBMITTED |  | 2016-05-30 | CSE-OF-3291-079 | 2016-05-31 | 3291-NPCC-PMT-AO-T-01363 | 2016-06-20 | 38-22701-N-T-06153 | 1 | 2016-05-31 | 3291-NPCC-MWS-T-0154
|  |  |  | C | 2 |  |  | 2016-06-01 | CSE-OF-3291-083 | 2016-06-01 | 3291-NPCC-PMT-AO-T-01382
|  |  |  | D | 2 |  | HZD | 2016-07-21 | CSE-OF-3291-178 | 2016-07-24 | 3291-NPCC-PMT-AO-T-01653 | 2016-08-09 | 38-22701-N-T-06842 | 1 | 2016-07-24 | 3291-NPCC-MWS-T-0253
251 | REMOVAL & REINSTALLATION RISER PROTECTOR-2 AT NSMFT PLATFROM (ROW-2) | 3291-NN-0251 | AD219-486-PL-00851 | B | 2 |  | CDG | 2016-06-28 | CSE-OF-3291-127 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01532 | 2016-08-09 | 38-22701-N-T-06835 | 1 | 2016-06-30 | 3291-NPCC-MWS-T-0203
|  |  |  | 0 | 1 |  |  | 2016-08-10 | CSE-OF-3291-217 | 2016-08-11 | 3291-NPCC-PMT-AO-T-01774 |  |  |  | 2016-08-11 | 3291-NPCC-MWS-T-0296
|  |  |  | 1 | 1 |  | CDG | 2016-08-16 | CSE-OF-3291-227 | 2016-08-17 | 3291-NPCC-PMT-AO-T-01811 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-17 | 3291-NPCC-MWS-T-0314
252 | LIFTING & INSTALLATION RISER PROTECTOR AT WHT-4 PLATFROM (ROW-2) | 3291-NN-0252 | AD219-489-PL-00852 | B | 2 |  | CDG | 2016-06-29 | CSE-OF-3291-133 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01542 | 2016-07-13 | 38-22701-N-T-06452 | 2 | 2016-06-30 | 3291-NPCC-MWS-T-0210
|  |  |  | 0 |  |  |  | 19/07/2016 | CSE-OF-3291-170 | 20/07/2016 | 3291-NPCC-PMT-AO-T-01637 | 2016-07-31 | 38-22701-N-T-06705 | 1 | 20/07/2016 | 3291-NPCC-MWS-T-0246
253 | LIFTING & INSTALLATION RISER PROTECTOR AT WHT-5 PLATFROM | 3291-NN-0253 | AD219-486-PL-00853 | B | 2 |  | CDG | 2016-06-30 | CSE-OF-3291-134 | 2016-07-04 | 3291-NPCC-PMT-AO-T-01551 | 2016-08-24 | 38-22701-N-T-06998 | 1 | 2016-07-04 | 3291-NPCC-MWS-T-0212
254 | LIFTING & INSTALLATION RISER PROTECTOR AT WHT-6 PLATFROM | 3291-NN-0254 | AD219-491-PL-00854 | B | 2 |  | CDG | 19/07/2016 | CSE-OF-3291-169 | 20/07/2016 | 3291-NPCC-PMT-AO-T-01636 | 2016-07-31 | 38-22701-N-T-06705 | 1 | 20/07/2016 | 3291-NPCC-MWS-T-0245
255 | LIFTING & INSTALLATION RISER PROTECTOR AT IGD-HAP | 3291-NN-0255 | AD219-469-PL-00855 | B | 2 | SUBMITTED |  | 2016-09-22 | CSE-OF-3291-265 | 2016-09-22 | 3291-NPCC-PMT-AO-T-01977 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-22 | 3291-NPCC-MWS-T-0375
|  |  |  | C | 1 |  |  | 2016-09-26 | CSE-OF-3291-267 | [10 empty] | CANCELLED
|  |  |  | 1 | 1 |  | CDG | 2016-10-13 | CSE-OF-3291-276 | 2016-10-16 | 3291-NPCC-PMT-AO-T-02075 | 2016-11-06 | 38-22701-N-T-07648 | 1 | 2016-10-16 | 3291-NPCC-MWS-T-0399
256 | 16" MOL PIPELINE FROM NSMFT TO DAS ISLAND SHORE PULL HEAD DETAILS | 3291-NN-0256 | AD219-486-PL-00856 | B | 2 |  |  | 2016-08-11 | CSE-OF-3291-221 | 2016-08-14 | 3291-NPCC-PMT-AO-T-01781 | 2016-08-24 | 38-22701-N-T-06999 | 1 | 2016-08-14 | 3291-NPCC-MWS-T-0302
|  |  |  | C | 2 |  | HZD | 2016-08-24 | CSE-OF-3291-237 | 2016-08-25 | 3291-NPCC-PMT-AO-T-01849 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-25 | 3291-NPCC-MWS-T-0327
257 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L STACK ON DRAWING OF PIPE JOINT @ WHT-6 | 3291-NN-0257 | AD219-491-PL-00857 | B | 2 |  | HZD | 2016-08-11 | CSE-OF-3291-219 | 2016-08-11 | 3291-NPCC-PMT-AO-T-01779 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-11 | 3291-NPCC-MWS-T-0300
258 | 16" J-TUBE LIFTING AND INSTALLATION @ NSMFT | 3291-NN-0258 | AD219-486-PL-00858 | B | 2 | REY |  | 2016-08-16 | CSE-OF-3291-224 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01797 | 2016-09-21 | 38-22701-N-T-07287 | 4 | 2016-08-16 | 3291-NPCC-MWS-T-0306
259 | 26" PIPELINE SHORE PULL HEAD DETAILS - NSMFT TO DAS ISLAND | 3291-NN-0259 | AD219-486-PL-00859 | B | 2 | HD |  | 2016-08-18 | CSE-OF-3291-230 | 2016-08-21 | 3291-NPCC-PMT-AO-T-01828 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-21 | 3291-NPCC-MWS-T-0318
260 | LAY DOWN HEAD DETAILS FOR 26" PIPELINE FROM IGD-HAP TO NSMFT | 3291-NN-0260 | AD219-469/486-PL-00860 | B | 2 | HD |  | 2016-08-18 | CSE-OF-3291-230 | 2016-08-21 | 3291-NPCC-PMT-AO-T-01828 | 2016-09-21 | 38-22701-N-T-07285 | 1 | 2016-08-21 | 3291-NPCC-MWS-T-0318
261 | LIFTING & INSTALLATION RISER PROTECTOR AT WHT-9 PLATFORM | 3291-NN-0261 | AD219-494-PL-00861 | B | 2 | AKS |  | 2016-09-27 | CSE-OF-3291-268 | 2016-09-28 | 3291-NPCC-PMT-AO-T-01996 | 2016-10-20 | 38-22701-N-T-07554 | 1 | 2016-09-28 | 3291-NPCC-MWS-T-0379
262 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL PIPELINE STACK ON DRAWING OF PIPE JOINT @WHT-9 | 3291-NN-0262 | AD219-494-PL-00862 |  |  | AKS
263 | TYPICAL CONCRETE SLEEPER SHIFTING (PX-18) 10" EXCESS GAS P/L (NSMFT TO USSC IGD-HAP) | 3291-NN-0263 | AD219-486/469-PL-00863 |  |  | CDG 02/11/2016
264 | REMOVAL & REINSTALLATION RISER PROTECTOR-1 AT NSMFT PLATFORM (ROW-1) | 3291-NN-0264 | AD219-486-PL-00864 | B | 2 | CDG |  | 2017-02-28 | CSE-OF-3291-319 | 2017-02-28 | 3291-NPCC-PMT-AO-T-02489 | 2017-04-02 | 38-22701-N-T-08905 | 1 | 2017-02-28 | 3291-NPCC-MWS-T-0474
|  |  |  | C | 2 |  |  | 2017-03-23 | CSE-OF-3291-335 | 2017-03-27 | 3291-NPCC-PMT-AO-T-02616 |  |  |  | 2017-03-23 | 3291-NPCC-MWS-T-0498
|  |  |  | D | 2 |  |  | 2017-03-28 | CSE-OF-3291-339 | 2017-03-29 | 3291-NPCC-PMT-AO-T-02636 |  |  |  | 2017-03-29 | 3291-NPCC-MWS-T-0507
|  |  |  | 0 | 1 |  |  | 2017-04-04 | CSE-OF-3291-347 | 2017-04-05 | 3291-NPCC-PMT-AO-T-02676 | 2017-04-09 | 38-22701-N-T-08989 | 1 | 2017-04-05 | 3291-NPCC-MWS-T-0517
265 | REMOVAL & OFFLOADING RISER PROTECTOR-1 & 2 AT WHT-2 (ROW-1 & 2) | 3291-NN-0265 | AD219-485-PL-00865 | B | 2 | CDG |  | 2017-03-23 | CSE-OF-3291-335 | 2017-03-27 | 3291-NPCC-PMT-AO-T-02617 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-23 | 3291-NPCC-MWS-T-0499
|  |  |  | C | 2 |  |  | 2017-04-02 | CSE-OF-3291-347 | 2017-04-05 | 3291-NPCC-PMT-AO-T-02663 |  |  |  | 2017-04-05 | 3291-NPCC-MWS-T-0516
|  |  |  | 0 | 1 |  |  | 2017-05-03 | CSE-OF-3291-350 | 2017-05-04 | 3291-NPCC-PMT-AO-T-02789 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-05-04 | 3291-NPCC-MWS-T-0526
266 | LIFTING & INSTALLATION RISER PROTECTOR AT WHT-7 PLATFORM | 3291-NN-0266 | AD219-492-PL-00866 | B | 2 |  |  | 2017-03-26 | CSE-OF-3291-337 | 2017-03-27 | 3291-NPCC-PMT-AO-T-02623 | 2017-05-08 | 38-22701-N-T-09233 | 1 | 2017-03-27 | 3291-NPCC-MWS-T-0502
267 | LOADING ARRANGEMENT & SEAFASTENING OF RISERS AND SPOOLS @ AL-JABER-35 (TRIP-3) | 3291-NN-0267 | AD219-705-PL-00867 | B | 2 |  |  | 2017-11-16 | CSE-OF-3291-370 | 2017-11-19 | 3291-NPCC-PMT-AO-T-03472 | 2018-08-05 | 38-22701-N-T-11402 | 1 | 2017-11-16 | 3291-NPCC-MWS-T-0578
268 | LIFTING & INSTALLATION RISER PROTECTORS AT WHT-3 PLATFORM | 3291-NN-0268 | AD219-488-PL-00868 | B | 2 | AKS |  | 2017-11-19 | CSE-OF-3291-371 | 2017-11-20 | 3291-NPCC-PMT-AO-T-03476 | 2018-08-05 | 38-22701-N-T-11403 | 1 | 2017-11-19 | 3291-NPCC-MWS-T-0579
269 | 16" RISER/SPOOL REMOVAL AT NSMFT 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0269 | AD219-486-PL-00869 | CDG | [15 empty] | NOT SENT TO PMT
270 | DETAIL OF 6" TEMPORARY PIG LAUNCHER / RECEIVER 6" GL PIPELINE FROM NSMFT TO WHT-9 | 3291-NN-0270 | AD219-486-PL-00494 | CDG | [15 empty] | NOT SENT TO PMT
271 | SPOOL DEMOLITION, LIFTING AND INSTALLATION FOR 6" GAS LIFT PIPELINE (NSMFT TO WHT-9) AT KP 3.473 | 3291-NN-0271 | AD219-486-PL-00495 | B |  |  |  | 2022-06-13 | CSE-OF-3291-383 | 2022-06-13 | 3291-NPCC-PMT-AO-T-05177
|  |  |  | C |  |  |  | 2022-07-29 | CSE-OF-3291-387 | 2022-08-01 | 3291-NPCC-PMT-AO-T-05192
|  |  |  | D |  |  |  | 2022-09-28 | CSE-OF-3291-388 | 2022-09-29 | 3291-NPCC-PMT-AO-T-05205
272 | SPOOL DEMOLITION, LIFTING AND INSTALLATION FOR 6" GAS LIFT PIPELINE (NSMFT TO WHT-9) AT KP 3.473 USE CCC PIONEER | 3291-NN-0272 | AD219-486-PL-00496
273 | FLANGE SHROUD LIFTING AND INSTALLATION FOR 6" GAS LIFT PIPELINE (NSMFT TO WHT-9) AT KP 3.460 & KP3.485 | 3291-NN-0273 | AD219-486-PL-00497 | B | 2 |  |  | 2022-11-08 | CSE-OF-3291-389 | 2022-11-09 | 3291-NPCC-PMT-AO-T-05222 | 2022-11-11 | 38-22701-N-T-13353 | 1
274 | SPOOL DEMOLITION, LIFTING AND INSTALLATION FOR 6" GAS LIFT PIPELINE (NSMFT TO WHT-9) AT KP 3.473 BY DLB-1000 | 3291-NN-0274 | AD219-486-PL-00498 | B | 2 |  |  | 2022-11-15 | CSE-OF-3291-390 | 2022-11-15 | 3291-NPCC-PMT-AO-T-05227
|  |  |  | 0 |  |  |  | 2022-11-15 | CSE-OF-3291-392
275
276
277
278
279
280
281
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADMA-OPCO APPROVAL CODE : (1) ACCEPTED; (2) ACCEPTED WITH COMMENTS; (2A) ACCEPTED WITH MINOR COMMENTS;
(3) NOT ACCEPTED, REVISE & RESUBMIT; (4) FOR INFORMATION
Formulas:
SUBMISSION PLAN = 4+[SUBMISSION PLAN, row above]

## CLIENT
|  | ABU DHABI MARINE OPERATING COMPANY (ADMA-OPCO) | [17 empty] | NPCC DOC. No.:
|  | UMM LULU PACKAGE-1 FFD PROJECT | [17 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 3291 | [17 empty] | REVISION :
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [17 empty] | DATE :
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | Latest REV. | CLASS | CLIENT STATUS | GM Status | ISSUED FOR CLIENT'S REVIEW/COMMENTS (IFR) 60 % |  |  | CLIENT'S RESPONSE DATE ON (IFR) |  |  | INCORPORATION OF COMMENTS AND ISSUED FOR CLIENT APPROVAL (IFA) 80% |  |  | CLIENT'S RESPONSE DATE ON (IFA) |  |  | ISSUED FOR CONSTRUCTION (IFC) 100 % |  |  | CLIENT'S RESPONSE DATE ON (IFC) |  | REMARKS
CURRENT STATUS
[8 empty] | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | DATE | REF
1 | PIPE STACKING ANALYSIS REPORT | 3291-NN-RP-001 | AD219-705-G-00401 | 0 | 1 | 1 | - | 2016-02-28 | 2016-03-02 | 3291-NPCC-PMT-AO-T-00919 |  | 2016-03-15 | 38-22701-N-T-04607 | [7 empty] | 2016-03-28 | 3291-NPCC-PMT-AO-T-01011 | 2016-04-04 | 38-22701-N-T-04927 | APPROVED
2 | PIPELAY INSTALLATION REPORT FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-RP-002 | AD219-486/492-G-00402 | 0 | 1 | 1 | Accepted | 2016-03-12 | 2016-05-03 | 3291-NPCC-PMT-AO-T-01208 |  | 2016-05-18 | 38-22701-N-T-05725 | [7 empty] | 2016-05-15 | 3291-NPCC-PMT-AO-T-01249
3 | PIPELAY INSTALLATION REPORT FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-RP-003 | AD219-486/492-G-00403 | 0 | 1 | 1 | Accepted | 2016-03-19 | 2016-05-10 | 3291-NPCC-PMT-AO-T-01233 |  | 2016-05-15 | 38-22701-N-T-05659 |  | 2016-05-18 | 3291-NPCC-PMT-AO-T-01274 |  | 2016-05-18 | 38-22701-P1-ADMA-NPCC-T-05728 |  | 2016-05-19 | 3291-NPCC-PMT-AO-T-01286 | 2016-05-29 | 38-22701-N-T-05808 | APPROVED
4 | PIPELAY INSTALLATION REPORT FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-RP-004 | AD219-494/493-G-00404 | 0 | 1 | 1 | Accepted | 2016-03-25 | 2016-04-03 | 3291-NPCC-PMT-AO-T-01039 |  | 2016-04-10 | 38-22701-N-T-05052 |  | 2016-11-09 | 3291-NPCC-PMT-AO-T-02146 |  | 2016-11-20 | 38-22701-N-T-07758
5 | PIPELAY INSTALLATION REPORT FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-RP-005 | AD219-494/493-G-00405 | 0 | 1 | 1 | Accepted | 2016-03-31 | 2016-03-30 | 3291-NPCC-PMT-AO-T-01032 |  | 2016-04-10 | 38-22701-N-T-05054 | [7 empty] | 2016-05-03 | 3291-NPCC-PMT-AO-T-01209 | 2016-05-15 | 38-22701-N-T-05597
6 | PIPELAY INSTALLATION REPORT FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-RP-006 | AD219-493/494-G-00406 | 0 | 1 | 1 | Accepted | 2016-04-06 | 2016-03-31 | 3291-NPCC-PMT-AO-T-01036 |  | 2016-04-10 | 38-22701-N-T-05053 | [7 empty] | 2016-05-03 | 3291-NPCC-PMT-AO-T-01209 | 2016-05-15 | 38-22701-N-T-05597
7 | INSTALLATION ANALYSIS REPORT FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-RP-007 | AD219-485/488-G-00407 | D | 2 | 1 | Accepted | 2016-04-12 | 2016-06-19 | 3291-NPCC-PMT-AO-T-01462 |  | 2016-06-30 | 38-22701-N-T-06308 |  | 2016-07-12 | 3291-NPCC-PMT-AO-T-01582 |  | 2016-07-27 | 38-22701-N-T-06656 |  | 2016-08-14 | 3291-NPCC-PMT-AO-T-01780 | 2016-08-22 | 38-22701-N-T-06964
8 | INSTALLATION ANALYSIS REPORT FOR 6" WI PIPELINE FROM WHT-2 TO WHT-3 | 3291-NN-RP-008 | AD219-485/488-G-00408 | B | 2 | 1 | Accepted | 2016-04-19 | 2016-05-31 | 3291-NPCC-PMT-AO-T-01371 |  | 2016-06-14 | 38-22701-N-T-06058
9 | INSTALLATION ANALYSIS REPORT FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-RP-009 | AD219-485/488-G-00409 | 0 | 2 | 1 | Accepted | 2016-04-25 | 2016-06-02 | 3291-NPCC-PMT-AO-T-01393 |  | 2016-06-15 | 38-22701-N-T-06087 |  | 2016-06-22 | 3291-NPCC-PMT-AO-T-01485 |  | 2016-07-14 | 38-22701-N-T-06423
10 | INSTALLATION ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-RP-010 | AD219-486/485-G-00410 | E | 2 | 1 | Accepted | 2016-05-01 | 2016-05-26 | 3291-NPCC-PMT-AO-T-01332 |  | 2016-06-08 | 38-22701-N-T-05995 |  | 2016-06-22 | 3291-NPCC-PMT-AO-T-01480 |  | 2016-07-14 | 38-22701-N-T-06427 |  | 18/07/2016 26/07/2016 | 3291-NPCC-PMT-AO-T-01627 3291-NPCC-PMT-AO-T-01655 | 2016-08-09 | 38-22701-N-T-06844
11 | INSTALLATION ANALYSIS REPORT FOR 6" GL PIPELINE FROM WHT-9 TO NSMFT | 3291-NN-RP-011 | AD219-486/494-G-00411 | 2 | 1 | 1 | Accepted | 2016-05-07 | 2016-04-07 | 3291-NPCC-PMT-AO-T-01053 |  | 2016-04-14 | 38-22701-N-T-05194 |  | 2016-05-09 | 3291-NPCC-PMT-AO-T-01217 |  | 2016-05-12 | 38-22701-N-T-05645 |  | 23/10/2016 09/11/2016 | 3291-NPCC-PMT-AO-T-02099 3291-NPCC-PMT-AO-T-02147 | 2016-11-20 | 38-22701-N-T-07759
12 | NSTALLATION ANALYSIS REPORT FOR 8" WI PIPELINE FROM NSMFT TO WHT-9 | 3291-NN-RP-012 | AD219-486/494-G-00412 | 0 | 1 | 1 | Accepted | 2016-05-14 | 2016-04-07 | 3291-NPCC-PMT-AO-T-01066 |  | 2016-04-14 | 38-22701-N-T-05196 | [7 empty] | 2016-05-04 | 3291-NPCC-PMT-AO-T-01221 | 2016-05-10 | 38-22701-P1-ADMA-NPCC-T-05606
13 | INSTALLATION ANALYSIS REPORT FOR 14" WF PIPELINE FROM WHT-9 TO NSMFTT | 3291-NN-RP-013 | AD219-494/486-G-00413 | 2 | 1 | - | Accepted | 2016-05-20 | 2016-04-03 | 3291-NPCC-PMT-AO-T-01039 |  | 2016-04-10 | 38-22701-N-T-05052 |  | 2016-05-03 | 3291-NPCC-PMT-AO-T-01167 |  | 2016-05-11 | 38-22701-P1-ADMA-NPCC-T-05609 |  | 23/10/2016 09/11/2016 | 3291-NPCC-PMT-AO-T-02098 3291-NPCC-PMT-AO-T-02148 | 2016-11-03 | 38-22701-N-T-07613
14 | INSTALLATION ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-RP-014 | AD219-486/491-G-00414 | 1 | 1 | 1 | - | 2016-05-27 | 2016-05-03 | 3291-NPCC-PMT-AO-T-01213 |  | 2016-05-15 | 38-22701-N-T-05594 |  | 2016-05-23 | 3291-NPCC-PMT-AO-T-01294 |  | 2016-06-05 | 38-22701-N-T-05945 |  | 2016-10-20 | 3291-NPCC-PMT-AO-T-02094 | 2016-11-01 | 38-22701-N-T-07611
15 | INSTALLATION ANALYSIS REPORT FOR 6" WI PIPELINE FROM NSMFT TO WHT-6 | 3291-NN-RP-015 | AD219-486/491-G-00415 | 0 | 2 | 1 | Accepted | 2016-06-03 | 2016-04-17 | 3291-NPCC-PMT-AO-T-01110 |  | 2016-04-26 | 38-22701-N-T-05383 |  | 2016-06-02 | 3291-NPCC-PMT-AO-T-01388 |  | 2016-06-14 | 38-22701-N-T-06060
16 | INSTALLATION ANALYSIS REPORT FOR 6" GL PIPELINE FROM NSMFT TO WHT-6 | 3291-NN-RP-016 | AD219-486/491-G-00416 | 2 | 2 | 1 | Accepted | 2016-06-09 | 2016-04-10 | 3291-NPCC-PMT-AO-T-01076 |  | 2016-04-14 | 38-22701-N-T-05195 |  | 2016-06-02 | 3291-NPCC-PMT-AO-T-01383 |  | 2016-06-14 | 38-22701-N-T-06061 |  | 04/05/2016 22/06/2016 | 3291-NPCC-PMT-AO-T-01211 3291-NPCC-PMT-AO-T-01483 | 2016-07-14 | 38-22701-N-T-06424
17 | INSTALLATION ANALYSIS REPORT FOR 6" GL P/L FROM WHT-5 TO NSMFT | 3291-NN-RP-017 | AD219-486/490-G-00417 | 0 | 1 | 1 | Accepted | 2016-06-15 | 2016-05-18 | 3291-NPCC-PMT-AO-T-01277 |  | 2016-06-01 | 38-22701-N-T-05911 |  | 2016-06-12 | 3291-NPCC-PMT-AO-T-01413 |  | 2016-06-26 | 38-22701-N-T-06230
18 | INSTALLATION ANALYSIS REPORT FOR 10" WI P/L FROM WHT-5 TO NSMFT | 3291-NN-RP-018 | AD219-486/490-G-00418 | 0 | 1 | 1 | Accepted | 2016-06-22 | 2016-05-18 | 3291-NPCC-PMT-AO-T-01272 |  | 2016-06-01 | 38-22701-N-T-05910 |  | 2016-06-13 | 3291-NPCC-PMT-AO-T-01416 |  | 2016-06-26 | 38-22701-N-T-06231
19 | INSTALLATION ANALYSIS REPORT FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-RP-019 | AD219-490/486-G-00419 | 1 | 1 | 1 | Accepted | 2016-06-29 | 2016-05-16 | 3291-NPCC-PMT-AO-T-01258 |  | 2016-05-30 | 38-22701-N-T-05887 |  | 02/06/2016 | 3291-NPCC-PMT-AO-T-01381 |  | 2016-06-14 | 38-22701-N-T-06059 |  | 2016-06-22 | 3291-NPCC-PMT-AO-T-01484 | 2016-07-14 | 38-22701-N-T-06428
20 | INSTALLATION ANALYSIS REPORT FOR 18" WF P/L FROM WHT-4 TO WHT- | 3291-NN-RP-020 | AD219-489/490-G-00420 | 2 | 1 | 1 | Accepted | 2016-07-07 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00928 |  | 2016-03-16 | 38-22701-N-T-04638 |  | 23/03/2016 10/05/2016 | 3291-NPCC-PMT-AO-T-01007 3291-NPCC-PMT-AO-T-01234 |  | 31/03/2016 11/05/2016 | 38-22701-N-T-04893 38-22701-N-T-05644 |  | 23/05/2016 01/06/2016 | 3291-NPCC-PMT-AO-T-01303 3291-NPCC-PMT-AO-T-01373 | 2016-06-13 | 38-22701-N-T-06057
21 | INSTALLATION ANALYSIS REPORT FOR 6" GL P/L FROM WHT-4 TO WHT-5 | 3291-NN-RP-021 | AD219-490/489-G-00421 | 0 | 1 | 1 | Accepted | 2016-07-14 | 2016-05-09 | 3291-NPCC-PMT-AO-T-01228 |  | 2016-05-15 | 38-22701-N-T-05658 | [7 empty] | 2016-05-19 | 3291-NPCC-PMT-AO-T-01285 | 2016-05-29 | 38-22701-N-T-05807
22 | INSTALLATION ANALYSIS REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-022 | AD219-490/489-G-00422 | 0 | 1 | 1 | commented | 2016-07-20 | 2016-05-09 | 3291-NPCC-PMT-AO-T-01228 |  | 2016-05-15 | 38-22701-N-T-05658 | [7 empty] | 2016-05-19 | 3291-NPCC-PMT-AO-T-01285 | 2016-05-29 | 38-22701-N-T-05807
23 | INSTALLATION ANALYSIS REPORT FOR 16" MOL FROM DAS ISLAND TO NSMFT | 3291-NN-RP-023 | AD219-486-G-00423 | 2 | 1 | 1 | Accepted | 2016-07-26 | 2016-08-02 | 3291-NPCC-PMT-AO-T-01719 |  | 2016-08-17 | 38-22701-N-T-06934 |  | 30/08/2016 | 3291-NPCC-PMT-AO-T-01870 |  | 2016-09-18 | 38-22701-N-T-07231 |  | 25/9/2016 06/10/2016 | 3291-NPCC-PMT-AO-T-01978 3291-NPCC-PMT-AO-T-02037 | 2016-10-12 | 38-22701-N-T-07454
24 | PIPELAY INSTALLATION REPORT FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-RP-024 | AD219-469/486-G-00424 | 0 | 1 | - | Accepted | 2016-09-20 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01535 |  | 2016-07-24 | 38-22701-N-T-06536 | [7 empty] | 2016-07-27 | 3291-NPCC-PMT-AO-T-01681 | 2016-08-09 | 38-22701-N-T-06843
25 | DAVIT LIFT ANALYSIS REPORTAT WHT-7 | 3291-NN-RP-025 | AD219-486/492-G-00425 | 0 | 2 | 1 | Accepted | 2016-09-01 | 2016-07-14 | 3291-NPCC-PMT-AO-T-01584 |  | 2016-07-28 | 38-22701-N-T-06678 |  | 2017-03-27 | 3291-NPCC-PMT-AO-T-02620 |  | 2017-04-12 | 38-22701-N-T-09020
26 | PIPELINE REPAIR REPORT FOR 6" GL P/L FROM NSMFT TO WHT-9 AT WHT-9 | 3291-NN-RP-026 | AD219-486/494-G-00426 | B | 2 | 1 | - | 2016-09-04 | 2016-10-04 | 3291-NPCC-PMT-AO-T-02022 |  | 2016-10-06 | 38-22701-N-T-07412
27 | DAVIT LIFT ANALYSIS REPORT AT WHT-8 | 3291-NN-RP-027 | AD219-494/493-G-00427 | 1 | 1 | 1 | Accepted | 2016-07-12 | 2016-07-14 | 3291-NPCC-PMT-AO-T-01603 |  | 2016-07-28 | 38-22701-N-T-06677 | [7 empty] | 04/09/2016 29/09/2016 | 3291-NPCC-PMT-AO-T-01891 3291-NPCC-PMT-AO-T-02011 | 2016-10-06 | 38-22701-N-T-07413
28 | DAVIT LIFT ANALYSIS REPORT FOR AT WHT-9 | 3291-NN-RP-028 | AD219-494/493-G-00428 | 0 | 1 | 1 | Accepted | 2016-07-15 | 2016-08-21 | 3291-NPCC-PMT-AO-T-01829 |  | 2016-09-01 | 38-22701-N-T-07106 | [7 empty] | 2016-10-20 | 3291-NPCC-PMT-AO-T-02095 | 2016-11-01 | 38-22701-N-T-07610
29 | PIPELINE LIFTING ANALYSIS FOR GROUTBAG INSTALLATION (16IN MOL DAS TO NSMFT) | 3291-NN-RP-029 | AD219-486-G-00429 | 0 | 1 | 1 | Accepted | 2016-07-18 | 2017-02-09 | 3291-NPCC-PMT-AO-T-02423 |  | 2017-02-22 | 38-22701-N-T-08538 | [7 empty] | 2017-06-20 | 3291-NPCC-PMT-AO-T-03022 | 2017-09-14 | 38-22701-N-T-10132
30 | DAVIT LIFT ANALYSIS REPORT AT WHT-2 | 3291-NN-RP-030 | AD219-485-G-00430 | 1 | 1 | 1 | Accepted | 2016-10-19 | 2017-01-22 | 3291-NPCC-PMT-AO-T-02372 |  | 2017-02-05 | 38-22701-N-T-08386 |  | 2017-03-23 | 3291-NPCC-PMT-AO-T-02605 |  | 2017-04-12 | 38-22701-N-T-09019 |  | 2017-03-27 | 3291-NPCC-PMT-AO-T-02625 | 2017-04-12 | 38-22701-N-T-09021
31 | DAVIT LIFT ANALYSIS REPORT AT WHT-3 | 3291-NN-RP-031 | AD219-488-G-00431 | 1 | 1 | -- | Accepted | 2016-10-22 | 2017-05-17 | 3291-NPCC-PMT-AO-T-02848 |  | 2017-06-01 | 38-22701-N-T-09395 |  | 2017-11-08 | 3291-NPCC-PMT-AO-T-03449 |  | 2017-11-20 | 38-22701-N-T-10479 |  | 2017-11-21 | 3291-NPCC-PMT-AO-T-03481 | 2017-12-06 | 38-22701-N-T-10537
32 | PIPELINE LIFTING ANALYSIS FOR SLEEPER SHIFTING (WHT-2 TO WHT-3) | 3291-NN-RP-032 | AD219-485/488-G-00432 | 0 | 1 | 1 | Accepted |  | 2016-11-27 | 3291-NPCC-PMT-AO-T-02208 |  | 2016-12-07 | 38-22701-N-T-07939 | [7 empty] | 2017-01-02 | 3291-NPCC-PMT-AO-T-02298 | 2017-01-12 | 38-22701-N-T-08200
33 | 16" MOL SHIFTING TO ORIGINAL POSITION ANALYSIS | 3291-NN-RP-033 | AD219-705-G-00433 | B | 2 | 1 | Accepted |  | 2017-03-05 | 3291-NPCC-PMT-AO-T-02505 |  | 2017-03-19 | 38-22701-N-T-08732
34 | DAVIT LIFT ANALYSIS REPORT FOR AT NSMFT (EAST) | 3291-NN-RP-034 | AD219-486/494-G-00434 | 1 | 1 | 1 | Accepted | 2016-09-10 | 2016-07-14 | 3291-NPCC-PMT-AO-T-01598 |  | 2016-07-28 | 38-22701-N-T-06682 |  | 2016-08-09 | 3291-NPCC-PMT-AO-T-01758 |  | 2016-08-22 | 38-22701-N-T-06962 |  | 2016-08-16 | 3291-NPCC-PMT-AO-T-01800 | 2016-08-22 | 38-22701-N-T-06967
35 | DAVIT LIFT ANALYSIS REPORT AT NSMFT (WEST) | 3291-NN-RP-035 | AD219-486/494-G-00435 | 0 | 1 | 2A | - | 2016-09-13 | 2017-01-03 | 3291-NPCC-PMT-AO-T-02305 |  | 2017-01-18 | 38-22701-N-T-08237 |  | 2017-04-04 | 3291-NPCC-PMT-AO-T-02660 |  | 2017-04-12 | 38-22701-N-T-09023
36 | WELD REPAIR ANALYSIS | 3291-NN-RP-036 | AD219-705-G-00436 |  |  | - | - | 2016-10-26
37 | DAVIT LIFT ANALYSIS REPORT FOR ALL PIPELINES AT WHT-6 | 3291-NN-RP-037 | AD219-486/491-G-00437 | 0 | 1 | 1 | Accepted | 2016-09-08 | 2016-06-29 | 3291-NPCC-PMT-AO-T-01526 |  | 2016-07-14 | 38-22701-N-T-06449 | [7 empty] | 21/07/2016 | 3291-NPCC-PMT-AO-T-01644 | 2016-07-31 | 38-22701-N-T-06702
38 | SEA FASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON SEAWAYS-17 (TRIP-12) | 3291-NN-RP-038 | AD219-705-G-00438 | B | 2 | 1 | - | 2016-09-11 | 2016-10-24 | 3291-NPCC-PMT-AO-T-02106 |  | 2016-11-07 | 38-22701-N-T-07672
39 | PIPELINE REPAIR REPORT FOR 6" GL P/L FROM NSMFT TO WHT-6 AT WHT-6 | 3291-NN-RP-039 | AD219-486/491-G-00439 | 0 | 1 | 1 | Accepted | 2016-09-14 | 2016-08-11 | 3291-NPCC-PMT-AO-T-01777 |  | 2016-08-17 | 38-22701-N-T-06913 | [7 empty] | 2016-10-20 | 3291-NPCC-PMT-AO-T-02096 | 2016-11-01 | 38-22701-N-T-07617
40 | DAVIT LIFT ANALYSIS REPORT FOR AT WHT-5 | 3291-NN-RP-040 | AD219-486/490-G-00440 | B | 2 | 1 | Accepted | 2016-08-25 | 2016-06-29 | 3291-NPCC-PMT-AO-T-01528 |  | 2016-07-12 | 38-22701-N-T-06426
41 | DAVIT LIFT ANALYSIS REPORT AT WHT-4 | 3291-NN-RP-041 | AD219-486/490-G-00441 | B | 2 | 1 | Accepted | 2016-08-28 | 2016-06-29 | 3291-NPCC-PMT-AO-T-01529 |  | 2016-07-12 | 38-22701-N-T-06422
42 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON GAC-82 (TRIP-16) | 3291-NN-RP-042 | AD219-705-G-00442 | B | 2 | 1 | - | 2016-08-31 | 2017-02-21 | 3291-NPCC-PMT-AO-T-02462 |  | 2017-03-02 | 38-22701-N-T-08608
43 | DAVIT LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-043 | AD219-489/490-G-00443 | B | 2 | 2 | - | 2016-08-07 | 2016-06-13 | 3291-NPCC-PMT-AO-T-01422 |  | 2016-06-23 | 38-22701-N-T-06195 | [11 empty] | previous title was 18in wht-4 to wht-5
44 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-044 | AD219-490/489-G-00444 | B | 2 | 2 | Accepted | 2016-08-10 | 2016-06-09 | 3291-NPCC-PMT-AO-T-01407 |  | 2016-06-23 | 38-22701-N-T-06194
45 | DAVIT LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-045 | AD219-490/489-G-00445 | B | 2 | 2 | - | 2016-08-13 | 2016-06-13 | 3291-NPCC-PMT-AO-T-01426 |  | 2016-06-26 | 38-22701-N-T-06196
46 | PIPELINE LIFTING ANALYSIS FOR SLEEPER SHIFTING (10" EGL NSMFT to USSC IGD-HAP) | 3291-NN-RP-046 | AD219-486/469-G-00446 | 3 | 1 | 1 | Accepted |  | 2016-10-18 | 3291-NPCC-PMT-AO-T-02085 |  | 2016-11-06 | 38-22701-N-T-07657 |  | 2016-11-09 | 3291-NPCC-PMT-AO-T-02150 |  | 2016-11-20 | 38-22701-N-T-07760 |  | 10/05/2017 15/05/2017 | 3291-NPCC-PMT-AO-T-02820 3291-NPCC-PMT-AO-T-02842 | 25/05/2017 14/09/2017 | 38-22701-N-T-09341 '38-22701-N-T-10134 | ADMA Ref. T- 09341 & T-09342 - Accepted
47 | DAVIT LIFT ANALYSIS REPORT AT IGD-HAP | 3291-NN-RP-047 | AD219-469/486-G-00447 | 1 | 1 | 1 | Accepted | 2016-10-16 | 2016-09-14 | 3291-NPCC-PMT-AO-T-01919 |  |  |  |  | 2016-09-20 | 3291-NPCC-PMT-AO-T-01949 |  | 2016-10-03 | 38-22701-N-T-07372 |  | 2016-10-20 | 3291-NPCC-PMT-AO-T-02097 | 2016-11-01 | 38-22701-N-T-07614
48 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-RP-048 | AD219-486/492-G-00448 | 0 | 1 | 1 | Accepted | 2016-09-01 | 2016-06-21 | 3291-NPCC-PMT-AO-T-01468 |  | 2016-06-30 | 38-22701-N-T-06306 |  | 2016-07-24 | 3291-NPCC-PMT-AO-T-01654 |  | 2016-08-04 | 38-22701-N-T-06759 |  | 2016-08-16 | 3291-NPCC-PMT-AO-T-01808 | 2016-08-25 | 38-22701-N-T-07018
49 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-RP-049 | AD219-486/492-G-00449 | B | 2 | 1 | Accepted | 2016-09-22 | 2016-08-11 | 3291-NPCC-PMT-AO-T-01775 |  | 2016-08-17 | 38-22701-N-T-06914
50 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-RP-050 | AD219-486/492-G-00450 | 0 | 1 | 4 | Accepted | 2016-09-04 | 2016-06-15 | 3291-NPCC-PMT-AO-T-01433 |  | 2016-06-26 | 38-22701-N-T-06204 |  | 2016-06-28 | 3291-NPCC-PMT-AO-T-01701 |  | 2016-08-09 | 38-22701-N-T-06832 |  | 2016-09-14 | 3291-NPCC-PMT-AO-T-01921 | 2016-09-21 | 38-22701-N-T-07287
51 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-RP-051 | AD219-486/492-G-00451 | B | 2 | 1 | Accepted | 2016-09-25 | 2016-08-10 | 3291-NPCC-PMT-AO-T-01770 |  | 2016-08-17 | 38-22701-N-T-06912
52 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-RP-052 | AD219-494/493-G-00452 | B | 2 | 1 | Accepted | 2016-07-25 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01834 |  | 2016-09-04 | 38-22701-N-T-07108
53 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-RP-053 | AD219-494/493-G-00453 | 0 | 2 | 1 | Accepted | 2016-07-12 | 2016-08-04 | 3291-NPCC-PMT-AO-T-01737 |  | 2016-08-11 | 38-22701-N-T-06871 |  | 2016-10-23 | 3291-NPCC-PMT-AO-T-02100 |  | 2016-11-03 | 38-22701-N-T-07618
54 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-RP-054 | AD219-494/493-G-00454 | B | 2 | 1 | Accepted | 2016-07-28 | 2016-08-28 | 3291-NPCC-PMT-AO-T-01857 |  | 2016-09-04 | 38-22701-N-T-07104
55 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-RP-055 | AD219-494/493-G-00455 | B | 2 | 1 | Accepted | 2016-07-15 | 2016-08-06 | 3291-NPCC-PMT-AO-T-01738 |  | 2016-08-17 | 38-22701-N-T-06911
56 | RISER LIFT ANALYSIS REPORT FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-8) | 3291-NN-RP-056 | AD219-493/494-G-00456 | B | 2 | 1 | Accepted | 2016-07-18 | 2016-08-07 | 3291-NPCC-PMT-AO-T-01751 |  | 2016-08-17 | 38-22701-N-T-06915
57 | RISER LIFT ANALYSIS REPORT FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-9) | 3291-NN-RP-057 | AD219-493/494-G-00457 | 0 | 1 | 1 | Accepted | 2016-08-01 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01839 |  | 2016-09-04 | 38-22701-N-T-07105 |  | 2016-11-30 | 3291-NPCC-PMT-AO-T-02224 |  | 2016-12-08 | 38-22701-N-T-07941
58 | RISER/SPOOL LIFT ANALYSIS REPORT FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-RP-058 | AD219-485/488-G-00458 | B | 2 | 1 | Accepted | 2016-11-01 | 2017-03-29 | 3291-NPCC-PMT-AO-T-02637 |  | 2017-04-17 | 38-22701-N-T-09058
59 | RISER LIFT ANALYSIS REPORT FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-RP-059 | AD219-485/488-G-00459 | B | 2 | 2 | - | 2016-10-19 | 2017-06-18 | 3291-NPCC-PMT-AO-T-02992 |  | 2017-07-04 | 38-22701-N-T-09653
60 | RISER /SPOOL LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-RP-060 | AD219-485/488-G-00460 | B | 2 | 2A | Accepted | 2016-11-04 | 2017-04-03 | 3291-NPCC-PMT-AO-T-02655 |  | 2017-04-20 | 38-22701-N-T-09092
61 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-RP-061 | AD219-485/488-G-00461 | B | 2 | 2 | - | 2016-10-22 | 2017-06-14 | 3291-NPCC-PMT-AO-T-02989 |  | 2017-07-04 | 38-22701-N-T-09654
62 | RISER / SPOOL LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-RP-062 | AD219-485/488-G-00462 | B | 2 | 2 | Accepted | 2016-11-07 | 2017-02-06 | 3291-NPCC-PMT-AO-T-02683 |  | 2017-04-20 | 38-22701-N-T-09093
63 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-RP-063 | AD219-485/488-G-00463 | B | 2 | 2 | - | 2016-10-25 | 2017-06-18 | 3291-NPCC-PMT-AO-T-03007 |  | 2017-07-04 | 38-22701-N-T-09652
64 | RISER /SPOOL LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-2 @ WHT-2 | 3291-NN-RP-064 | AD219-486/485-G-00464 | B | 2 | 1 | Accepted | 2016-09-07 | 2017-03-27 | 3291-NPCC-PMT-AO-T-02615 |  | 2017-04-12 | 38-22701-N-T-09022
65 | RISER/ SPOOL LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-2 @ NSMFT | 3291-NN-RP-065 | AD219-486/485-G-00465 | 0 | 1 | 1 | Accepted | 2016-11-10 | 2017-02-13 | 3291-NPCC-PMT-AO-T-02433 |  | 2017-02-26 | 38-22701-N-T-08564 |  | 2017-03-28 | 3291-NPCC-PMT-AO-T-02629 |  | 2017-04-17 | 38-22701-N-T-09061
66 | RISER/SPOOL LIFT ANALYSIS REPORT FOR 6" GAS LIFT P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-RP-066 | AD219-486/494-G-00466 | B | 2 | 1 | Accepted | 2016-09-10 | 2017-03-05 | 3291-NPCC-PMT-AO-T-02506 |  | 2017-03-16 | 38-22701-N-T-08730
67 | RISER LIFT ANALYSIS REPORT FOR 6"GL P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-RP-067 | AD219-486/494-G-00467 | B | 2 | 1 | Accepted | 2016-10-02 | 2016-09-01 | 3291-NPCC-PMT-AO-T-01884 |  | 2016-09-18 | 38-22701-N-T-07230
68 | RISER / SPOOL LIFT ANALYSIS REPORT FOR 8" WI P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-RP-068 | AD219-486/494-G-00468 | B | 2 | 1 | Accepted | 2016-09-13 | 2017-02-26 | 3291-NPCC-PMT-AO-T-02478 |  | 2017-03-08 | 38-22701-N-T-08647
69 | RISER LIFT ANALYSIS REPORT FOR 8" WI P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-RP-069 | AD219-486/494-G-00469 | 0 | 1 | 1 | Accepted | 2016-10-05 | 2016-08-29 | 3291-NPCC-PMT-AO-T-01866 |  | 2016-09-08 | 38-22701-N-T-07173 | [7 empty] | 2016-12-06 | 3291-NPCC-PMT-AO-T-02232 | 2016-12-13 | 38-22701-N-T-07988
70 | RISER LIFT ANALYSIS REPORT FOR WF 14" P/L FROM WHT-9 TO NSMFT (@WHT-9) | 3291-NN-RP-070 | AD219-494/486-G-00470 | 0 | 1 | 1 | Accepted | 2016-10-08 | 2016-08-25 | 3291-NPCC-PMT-AO-T-01847 |  | 2016-09-04 | 38-22701-N-T-07107 | [7 empty] | 2016-12-04 | 3291-NPCC-PMT-AO-T-02227 | 2016-12-13 | 38-22701-N-T-07987
71 | RISER / SPOOL LIFT ANALYSIS REPORT FOR 14" WELL FLUID P/L FROM WHT-9 TO NSMFT (@NSMFT) | 3291-NN-RP-071 | AD219-494/486-G-00471 | B | 2 | 1 | - | 2016-09-16 | 2017-03-13 | 3291-NPCC-PMT-AO-T-02530 |  | 2017-03-26 | 38-22701-N-T-08801
72 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-RP-072 | AD219-486/491-G-00472 | C | 2 | 1 | Accepted | 2016-09-19 | 2016-04-05 | 3291-NPCC-PMT-AO-T-01022 |  | 2016-04-18 | 38-22701-N-T-05230 |  | 2016-06-06 | 3291-NPCC-PMT-AO-T-01394 |  | 2016-06-16 | 38-22701-N-T-06088 |  | 2016-07-28 | 3291-NPCC-PMT-AO-T-01691 | 2016-08-09 | 38-22701-N-T-06831
73 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-RP-073 | AD219-486/491-G-00473 | 0 | 1 | 1 | Accepted | 2016-09-08 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01607 |  | 2016-07-27 | 38-22701-N-T-06653 | [7 empty] | 2016-09-07 | 3291-NPCC-PMT-AO-T-01911 | 2016-09-18 | 38-22701-N-T-07222
74 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-RP-074 | AD219-486/491-G-00474 | B | 2 | 1 | Accepted | 2016-09-22 | 2016-07-26 | 3291-NPCC-PMT-AO-T-01666 |  | 2016-08-04 | 38-22701-N-T-06758
75 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-RP-075 | AD219-486/491-G-00475 | 0 | 1 | 1 | Accepted | 2016-09-11 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01616 |  | 2016-07-27 | 38-22701-N-T-06655 |  | 2016-11-23 | 3291-NPCC-PMT-AO-T-02196 |  | 2016-12-04 | 38-22701-N-T-07891
76 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-RP-076 | AD219-486/491-G-00476 | 0 | 1 | 1 | Accepted | 2016-09-25 | 2016-07-27 | 3291-NPCC-PMT-AO-T-01669 |  | 2016-08-04 | 38-22701-N-T-06757 |  | 2016-08-17 | 3291-NPCC-PMT-AO-T-01814 |  | 2016-08-25 | 38-22701-N-T-07017
77 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-RP-077 | AD219-486/491-G-00477 | 1 | 1 | 1 | Accepted | 2016-09-14 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01611 |  | 2016-07-27 | 38-22701-N-T-06654 |  | 2016-09-06 | 3291-NPCC-PMT-AO-T-01904 |  | 2016-09-18 | 38-22701-N-T-07229 |  | 2016-11-07 | 3291-NPCC-PMT-AO-T-02140 | 2016-11-16 | 38-22701-N-T-07716
78 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-RP-078 | AD219-486/490-G-00478 | B | 2 | 1 | Accepted | 2016-09-28 | 2016-07-27 | 3291-NPCC-PMT-AO-T-01682 |  | 2016-08-04 | 38-22701-N-T-06756
79 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-RP-079 | AD219-486/490-G-00479 | 1 | 1 | 1 | Accepted | 2016-08-25 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01576 |  | 2016-07-20 | 38-22701-N-T-06544 |  | 2016-09-05 | 3291-NPCC-PMT-AO-T-01900 |  | 2016-09-18 | 38-22701-N-T-07228 |  | 2016-11-14 | 3291-NPCC-PMT-AO-T-02157 | 2016-11-24 | 38-22701-N-T-07802
80 | RISER LIFT ANALYSIS REPORT FOR 10" WI P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-RP-080 | AD219-486/490-G-00480 | 0 | 1 | 1 | Accepted | 2016-10-01 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01685 |  | 2016-08-09 | 38-22701-N-T-06829 | [7 empty] | 2016-10-06 | 3291-NPCC-PMT-AO-T-02028 | 2016-10-12 | 38-22701-N-T-07452
81 | RISER LIFT ANALYSIS REPORT FOR 10" WI P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-RP-081 | AD219-486/490-G-00481 | 0 | 1 | 1 | Accepted | 2016-08-28 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01576 |  | 2016-07-20 | 38-22701-N-T-06544 |  | 2016-10-26 | 3291-NPCC-PMT-AO-T-02112 |  | 2016-11-03 | 38-22701-N-T-07616
82 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-5 TO NSMFT (@WHT-5) | 3291-NN-RP-082 | AD219-490/486-G-00482 | 0 | 1 | 1 | Accepted | 2016-08-31 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01573 |  | 2016-07-20 | 38-22701-N-T-06546 | [7 empty] | 2016-10-19 | 3291-NPCC-PMT-AO-T-02088 | 2016-11-01 | 38-22701-N-T-07615
83 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-RP-083 | AD219-490/486-G-00483 | 0 | 1 | 1 | Accepted | 2016-10-04 | 2016-04-21 | 3291-NPCC-PMT-AO-T-01124 |  | 2016-04-26 | 38-22701-N-T-05380 |  | 2016-06-06 | 3291-NPCC-PMT-AO-T-01394 |  | 2016-06-16 | 38-22701-N-T-06088 |  | 31/07/2016/ 20/9/2016 | 3291-NPCC-PMT-AO-T-01712/ 3291-NPCC-PMT-AO-T-01952 | 2016-09-28 | 38-22701-N-T-07330
84 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-4) | 3291-NN-RP-084 | AD219-489/490-G-00484 | 0 | 1 | 1 | Accepted | 2016-08-07 | 2016-06-22 | 3291-NPCC-PMT-AO-T-01476 |  | 2016-06-30 | 38-22701-N-T-06311 | [7 empty] | 2016-11-21 | 3291-NPCC-PMT-AO-T-02178 | 2016-12-04 | 38-22701-N-T-07890
85 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-5) | 3291-NN-RP-085 | AD219-489/490-G-00485 | 0 | 1 | 1 | Accepted | 2016-08-20 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01536 |  | 2016-07-12 | 38-22701-N-T-06431 | [7 empty] | 2016-08-09 | 3291-NPCC-PMT-AO-T-01763 | 2016-08-22 | 38-22701-N-T-06965
86 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-RP-086 | AD219-490/489-G-00486 | B | 2 | 1 | Accepted | 2016-08-23 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01562 |  | 2016-07-20 | 38-22701-N-T-06545
87 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-4 TO WHT-5 (@WHT-4) | 3291-NN-RP-087 | AD219-490/489-G-00487 | 0 | 1 | 1 | Accepted | 2016-08-10 | 2016-06-28 | 3291-NPCC-PMT-AO-T-01478 |  | 2016-07-12 | 38-22701-N-T-06429 | [7 empty] | 2016-11-17 | 3291-NPCC-PMT-AO-T-02169 | 2016-11-27 | 38-22701-N-T-07810 | previous title was wht-5 to wht-4
88 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-RP-088 | AD219-490/489-G-00488 | 0 | 1 | - | Accepted | 2016-08-26 | 2016-07-04 | 3291-NPCC-PMT-AO-T-01552 |  | 2016-07-20 | 38-22701-N-T-06547 |  | 2016-11-15 | 3291-NPCC-PMT-AO-T-02161 |  | 2016-11-24 | 38-22701-N-T-07801
89 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-4) | 3291-NN-RP-089 | AD219-490/489-G-00489 | B | 2 | 1 | Accepted | 2016-08-13 | 2016-06-26 | 3291-NPCC-PMT-AO-T-01499 |  | 2016-07-12 | 38-22701-N-T-06430
90 | RISER / SPOOL LIFT ANALYSIS REPORT FOR 16" MAIN OIL P/L FROM NSMFT TO DAS ISLAND AT NSMFT | 3291-NN-RP-090 | AD219-486-G-00490 | B | 2 | 1 | Accepted | 2016-10-23 | 2017-03-08 | 3291-NPCC-PMT-AO-T-02514 |  | 2017-03-16 | 38-22701-N-T-08731
91 | RISER LIFT ANALYSIS REPORT FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@IGD-HAP) | 3291-NN-RP-091 | AD219-469/486-G-00491 | B | 2 | 1 | Accepted | 2016-10-16 | 2016-10-06 | 3291-NPCC-PMT-AO-T-02038 |  | 2016-10-12 | 38-22701-N-T-07448
92 | RISER / SPOOL LIFT ANALYSIS REPORT FOR 10" EXCESS GAS EXPORT P/L FROM NSMFT TO USSC IGD-HAP (@NSMFT) | 3291-NN-RP-092 | AD219-469/486-G-00492 | B | 2 | 1 | - | 2016-10-26 | 2017-03-11 | 3291-NPCC-PMT-AO-T-02522 |  | 2017-03-26 | 38-22701-N-T-08802
93 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF RCC SLEEPERS ON MICLYN-285 (TRIP-1) | 3291-NN-RP-093 | AD219-705-G-00493 | B | 2 | - | Accepted | 2016-04-01 | 2016-03-22 | 3291-NPCC-PMT-AO-T-00990 |  | 2016-04-04 | 38-22701-N-T-04926
94 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON GAC-81 (TRIP-1) | 3291-NN-RP-094 | AD219-705-G-00494 | B | 2 | 2 | Accepted | 2016-04-05 | 2016-03-23 | 3291-NPCC-PMT-AO-T-01003 |  | 2016-04-04 | 38-22701-N-T-04931 |  | 2016-06-02 | 3291-NPCC-PMT-AO-T-01387 |  | 2016-06-16 | 38-22701-N-T-06089
95 | SEAFASTENING DESIGN REPORT FOR CC @ASTRO-302 (TRIP-2) | 3291-NN-RP-095 | AD219-705-G-00495 | B | 2 | 2 | Accepted | 2016-04-09 | 2016-04-13 | 3291-NPCC-PMT-AO-T-01096 |  | 2016-04-24 | 38-22701-N-T-05274 |  | 2016-06-02 | 3291-NPCC-PMT-AO-T-01387 |  | 2016-06-16 | 38-22701-N-T-06089
96 | TAKEN BY YAHIA (TITLE UNKNOWN) | 3291-NN-RP-096 | AD219-705-G-00496
97 | SEAFASTENING FOR RISERS AND SPOOLS ON ZAKHER-101 | 3291-NN-RP-097 | AD219-705-G-00497 | B | 2 | 1 |  |  | 2017-03-22 | 3291-NPCC-PMT-AO-T-02592 |  | 2017-03-30 | 38-22701-N-T-08870
98 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CB-6 (TRIP-3) | 3291-NN-RP-098 | AD219-705-G-00498 | B | 2 | 1 | Accepted | SUBMITTED | 2016-05-12 | 3291-NPCC-PMT-AO-T-01245 |  | 2016-05-15 | 38-22701-N-T-05668
99 | DAVIT LIFT ANALYSIS @ NSMFT EAST SIDE AFTER METROLOGY | 3291-NN-RP-099 | AD219-486-G-00499 | B | 2 |  | Accepted |  | 2016-09-04 | 3291-NPCC-PMT-AO-T-01892 | [7 empty] | 2016-10-19
100 | INSTALLATION ANALYSIS REPORT FOR 26" CONDUIT PIPELINE | 3291-NN-RP-100 | AD219-705-G-00500 | 1 | 1 | 1 |  |  | 2016-09-07 | 3291-NPCC-PMT-AO-T-01910 |  | 2016-09-25 | 38-22701-N-T-07309 |  | 2016-09-29 | 3291-NPCC-PMT-AO-T-02014 |  | 2016-10-09 | 38-22701-N-T-07430 |  | 2016-10-16 | 3291-NPCC-PMT-AO-T-02063 | 2016-11-01 | 38-22701-N-T-07620
101 | 10" EGL SHIFTING TO ORIGINAL POSITION ANALYSIS | 3291-NN-RP-101 | AD219-486-G-00573 | 1 | 1 | 1 | Accepted | SUBMITTED | 2016-09-22 | 3291-NPCC-PMT-AO-T-01973 |  | 2016-10-05 | 38-22701-N-T-07405 |  | 2016-10-16 | 3291-NPCC-PMT-AO-T-02063 |  | 2016-10-19 | 38-22701-N-T-07528 |  | 2016-10-27 | 3291-NPCC-PMT-AO-T-02120 | 2016-11-09 | 38-22701-N-T-07692
102 | RECOVERY AND INSTALLATION ANALYSIS REPORT FOR 10” EGL PIPELINE FROM IGD-HAP TO NSMFT WITH DLB-1000 | 3291-NN-RP-102 | AD219-469/486-G-00575 | B | 2 | 2 | Accepted | REMARKS | 2017-01-16 | 3291-NPCC-PMT-AO-T-02342 |  | 2017-01-26 | 38-22701-N-T-08319 | [11 empty] | withdraw this trans. From ADMA (infor. Mr. Yahia's email dtd. 22/03/2017)
103 | RECOVERY AND INSTALLATION ANALYSIS REPORT FOR 16” MOL FROM DAS ISLAND TO NSMFT WITH DLB-1000 | 3291-NN-RP-103 | AD219-486-G-00576 | B | 2 | 2 | Accepted | REMARKS | 2017-01-16 | 3291-NPCC-PMT-AO-T-02344 |  | 2017-01-26 | 38-22701-N-T-08318 | [11 empty] | withdraw this trans. From ADMA (infor. Mr. Yahia's email dtd. 22/03/2017)
104 | PIPELINE LIFTING ANALYSIS FOR SLEEPER SHIFTING (10in EGL NSMFT to USSC IGD-HAP) | 3291-NN-RP-104 | AD219-486/469-G-00577 | B | 2 | 2 |  | SUBMITTED | 2017-06-12 | 3291-NPCC-PMT-AO-T-02978 |  | 2017-06-22 | 38-22701-N-T-09599
| NAVAL & MARINE | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
96 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6” WI P/L & 10” WF P/L FROM NSMFT TO WHT-7 | 3291-ZZ-RP-001 | AD219-486/492-G-00501 | B | 2 | 1 | commented | 1916-03-12 | 2016-05-08 | 3291-NPCC-PMT-AO-T-01224 |  | 2016-06-20 | 38-22701-N-T-06153
97 | MOORING ANALYSIS DURING INSTALLATION OF 6” & 10” RISERS, TIE-IN SPOOLS AND RISER FENDERS AT NSMFT (WEST FACE) | 3291-ZZ-RP-002 | AD219-486-G-00502 | B | 2 | 1 | Accepted | 1916-03-19 | 2017-03-15 | 3291-NPCC-PMT-AO-T-02558 |  | 2016-04-02 | 38-22701-N-T-08906
98 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.1 KM GAS LIFT P/L FROM WHT-9 TO WHT-8 | 3291-ZZ-RP-003 | AD219-494/493-G-00503 | 0 | 1 | - | Accepted | 1916-03-25 | 2016-03-17 | 3291-NPCC-PMT-AO-T-00972 |  |  | mws comments received | [7 empty] | 2016-03-28 | 3291-NPCC-PMT-AO-T-01009 | 2016-04-03 | 38-22701-N-T-04936 | APPROVED
99 | MOORING ANALYSIS DURING 10" EXCESS GAS PIPELINE SHIFTING AT MFT | 3291-ZZ-RP-004 | AD219-486-G-00504 | B | 2 | - | Accepted | 1916-03-31 | 2017-04-05 | 3291-NPCC-PMT-AO-T-02677 |  | 2017-04-09 | 38-22701-N-T-08988
100 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING REMOVAL OF WHT-3 JACKET | 3291-ZZ-RP-005 | AD219-488-G-00505 | B | 2 | 1 | Accepted |  | 2017-04-16 | 3291-NPCC-PMT-AO-T-02722 |  | 2017-05-02 | 38-22701-N-T-09196
101 | MOORING ANALYSIS DURING PIPE LAYING OF 12" WF P/L 6" GL , 6" WI PL FROM WHT-2 TO WHT-3 | 3291-ZZ-RP-006 | AD219-485/488-G-00506 | B | 2 | 1 | commented | 1916-04-12 | 2016-07-18 | 3291-NPCC-PMT-AO-T-01628 |  | 2016-08-21 | 38-22701-N-T-06953
102 | MOORING ANALYSIS DURING HOOK-UP WORKS & MECHANICAL COMPLETION AT IGD-HAP, B-25 & B-24 LOCATION | 3291-ZZ-RP-007 | AD219-469-G-00507 | B | 2 | 1 | Accepted | 1916-04-19 | 2017-09-27 | 3291-NPCC-PMT-AO-T-03385 |  | 2017-10-21 | 38-22701-N-T-10330
103 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.6 KM GAS LIFT P/L FROM WHT-2 TO WHT-3 | 3291-ZZ-RP-008 | AD219-485/488-G-00508 |  |  | - | - | 1916-04-25
104 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 3.7 KM GAS LIFT P/L FROM NSMFT TO WHT-2 | 3291-ZZ-RP-009 | AD219-486/485-G-00509 | B | 2 | - | commented | 1916-05-01 | 2016-06-06 | 3291-NPCC-PMT-AO-T-01397
105 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" GL P/L, 8” WI P/L AND 14” WF P/L FROM NSMFT TO WHT-9 (5.5KM) | 3291-ZZ-RP-010 | AD219-486/494-G-00510 | B | 2 | 1 | commented | 1916-05-07 | 2016-04-07 | 3291-NPCC-PMT-AO-T-01072 |  | 2016-06-20 | 38-22701-N-T-06153
106 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 8" X 5.5 KM WATER INJECTION P/L FROM NSMFT TO WHT-9 | 3291-ZZ-RP-011 | AD219-486/494-G-00511 | Merged with 3291-ZZ-RP-010 |  | - | - | 1916-05-14
107 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 14" X 5.5 KM WELL FLUID P/L FROM WHT-9 TO NSMFT | 3291-ZZ-RP-012 | AD219-494/486-G-00512 |  |  | - | - | 1916-05-20
108 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" GL P/L, 6” WI P/L AND 10” WF P/L FROM NSMFT TO WHT-6 (5.2KM) | 3291-ZZ-RP-013 | AD219-486/491-G-00513 | B | 2 | 1 | Accepted | 1916-05-27 | 2016-05-11 | 3291-NPCC-PMT-AO-T-01242 |  | 2016-06-20 | 38-22701-N-T-06153
109 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 5.2 KM WATER INJECTION P/L FROM NSMFT TO WHT-6 | 3291-ZZ-RP-014 | AD219-486/491-G-00514 | Merged with 3291-ZZ-RP-013 |  | - | - | 1916-06-03
110 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 5.2 KM GAS LIFT P/L FROM NSMFT TO WHT-6 | 3291-ZZ-RP-015 | AD219-486/491-G-00515 |  |  | - | - | 1916-06-09
111 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 6.0 KM GAS LIFT P/L FROM NSMFT TO WHT-5 | 3291-ZZ-RP-016 | AD219-486/490-G-00516 |  |  | - | - | 1916-06-15
112 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 10" X 6.0 KM WATER INJECTION P/L FROM NSMFT TO WHT-5 | 3291-ZZ-RP-017 | AD219-486/490-G-00517 |  |  | - | - | 1916-06-22
113 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" GL P/L, 10” WI P/L AND 18” WF P/L FROM NSMFT TO WHT-5 (6.075KM) | 3291-ZZ-RP-018 | AD219-490/486-G-00518 | B | 2 | 1 | commented | 1916-06-29 | 2016-05-17 | 3291-NPCC-PMT-AO-T-01261 |  | 2016-06-20 | 38-22701-N-T-06153
114 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 18" X 4.7 KM WELL FLUID P/L FROM WHT-4 TO WHT-5 | 3291-ZZ-RP-019 | AD219-489/490-G-00519 | B | 2 | 1 | Accepted | 1916-07-07 | 2016-03-31 | 3291-NPCC-PMT-AO-T-01038 |  | 2016-06-20 | 38-22701-N-T-06153
115 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.7 KM GAS LIFT P/L FROM WHT-5 TO WHT-4 | 3291-ZZ-RP-020 | AD219-490/489-G-00520 | Merged with 3291-ZZ-RP-019 |  | - | - | 1916-07-14
116 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.7 KM WATER INJECTION P/L FROM WHT-5 TO WHT-4 | 3291-ZZ-RP-021 | AD219-490/489-G-00521 |  |  | - | - | 1916-07-20
117 | MOORING ANALYSIS FOR DURING LAYING OF 16" X 69 KM MAIN OIL LINE (MOL) FROM DAS ISLAND TO NSMFT | 3291-ZZ-RP-022 | AD219-486-G-00522 | B | 2 | 1 | - | 1916-07-26 | 2016-09-14 | 3291-NPCC-PMT-AO-T-01927 |  | 2016-09-21 | 38-22701-N-T-07285
118 | MOORING ANALYSIS DURING LAYING OF 10" EXCESS GAS PIPE LINE FROM IGD-HAP TO NSMFT | 3291-ZZ-RP-023 | AD219-469/486-G-00523 | B | 2 | 1 | Accepted | 1916-09-20 | 2016-08-10 | 3291-NPCC-PMT-AO-T-01764 |  | 2016-08-21 | 38-22701-N-T-06953
119 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-3 & WHT-6 JACKET | 3291-ZZ-RP-024 | AD219-488-G-00524 | B | 2 | 1 | Accepted | 2016-03-05 | 2016-05-03 | 3291-NPCC-PMT-AO-T-01212 |  | 2016-06-20 | 38-22701-N-T-06153
121 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-4 & WHT-5 JACKET | 3291-ZZ-RP-025 | AD219-489-G-00525 | B | 2 | 2 | - | 2015-11-17 | 2015-11-17 | '3291-NPCC-PMT-AO-T-00624 |  | 2015-12-06 | 38-22701-N-T-03499
122 | MOORING ANALYSIS DURING HOOK UP WORK AT NSMFT | 3291-ZZ-RP-026 | AD219-486-G-00526 | B | 2 | 1 | Accepted |  | 2018-02-07 | 3291-NPCC-PMT-AO-T-03802 |  | 2018-08-05 | 38-22701-N-T-11404
123 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-6 JACKET | 3291-ZZ-RP-027 | AD219-491-G-00527 | Merged with 3291-ZZ-RP-024 |  | - | - | 2016-04-27
124 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-7 JACKET | 3291-ZZ-RP-028 | AD219-492-G-00528 | B | 2 | 1 | Accepted | 2016-06-23 | 2016-09-29 | 3291-NPCC-PMT-AO-T-02012 |  | 2016-10-20 | 38-22701-N-T-07554
125 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-8 JACKET | 3291-ZZ-RP-029 | AD219-493-G-00529 | C | 2 | 4 | Accepted | 2016-05-16 | 2016-08-16 | 3291-NPCC-PMT-AO-T-01796 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-08-27 | 3291-NPCC-PMT-AO-T-01854 |  | 2016-09-21 | 38-22701-N-T-07287
126 | MOORING ANALYSIS DURING INSTALLATION OF WHT-9 JACKET | 3291-ZZ-RP-030 | AD219-494-G-00530 | B | 2 | - | Accepted | 2015-05-06 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01541
127 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-3 TOPSIDES | 3291-ZZ-RP-031 | AD219-488-G-00531 |  |  | - | - | 2016-12-01
128 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-4 TOPSIDES | 3291-ZZ-RP-032 | AD219-489-G-00532 | B | 2 | 1 | commented | 2016-12-06 | 2017-07-10 | 3291-NPCC-PMT-AO-T-03121 |  | 2017-07-17 | 38-22701-N-T-09768
129 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-5 TOPSIDES | 3291-ZZ-RP-033 | AD219-490-G-00533 | B | 2 | 1 | commented | 2016-12-11 | 2017-07-12 | 3291-NPCC-PMT-AO-T-03155 |  | 2017-07-17 | 38-22701-N-T-09767
130 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-6 TOPSIDES | 3291-ZZ-RP-034 | AD219-491-G-00534 |  |  | - | - | 2016-12-16
131 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-7 TOPSIDES | 3291-ZZ-RP-035 | AD219-492-G-00535 |  |  | - | - | 2016-12-21
132 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-8 TOPSIDES | 3291-ZZ-RP-036 | AD219-493-G-00536 |  |  | - | - | 2016-12-26
133 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-9 TOPSIDES | 3291-ZZ-RP-037 | AD219-494-G-00537 |  |  | - | - | 2016-12-31
134 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-8 (WEST FACE) | 3291-ZZ-RP-038 | AD219-493-G-00538 | B | 2 | 1 | commented | 2016-07-12 | 2016-08-19 | 3291-NPCC-PMT-AO-T-01943 |  | 2016-10-20 | 38-22701-N-T-07554
135 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 8", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-9 (WEST FACE) | 3291-ZZ-RP-039 | AD219-494-G-00539 | B | 2 | 1 | Accepted | 2016-07-25 | 2016-09-18 | 3291-NPCC-PMT-AO-T-01935 |  | 2016-10-20 | 38-22701-N-T-07554
136 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 18" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-4 (EAST FACE) | 3291-ZZ-RP-040 | AD219-489-G-00540 | 0 | 1 | 1 | Accepted | 2016-08-07 | 2016-06-23 | 3291-NPCC-PMT-AO-T-01489 |  | 2016-06-29 | 38-22701-N-T-06288 | [7 empty] | 2016-07-10 | 3291-NPCC-PMT-AO-T-01559 | 13/07/2016 | 38-22701-N-T-06705
137 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 10", 18", 16" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-5 (EAST FACE) | 3291-ZZ-RP-041 | AD219-490-G-00541 | B | 2 | 1 | Accepted | 2016-08-20 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01569 |  | 31/07/2016 | 38-22701-N-T-06705
138 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 12" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-3 (WEST FACE) | 3291-ZZ-RP-042 | AD219-488-G-00542 | B | 2 | - | - | 2016-10-19 | 2017-11-13 | 3291-NPCC-PMT-AO-T-03463
139 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6" & 12" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-2 (EAST & WEST FACE) | 3291-ZZ-RP-043 | AD219-485-G-00543 | B | 2 | 1 | commented | 2016-11-01 | 2017-03-19 | 3291-NPCC-PMT-AO-T-02567 |  | 2016-04-02 | 38-22701-N-T-08906
140 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT- 2 (EAST FACE) | 3291-ZZ-RP-044 | AD219-485-G-00544 | SPARE |  | - | - | 2016-11-10
141 | MOORING ANALYSIS DURING INSTALLATION OF 16" RISER, TIE-IN SPOOLS AND RISER FENDERS AT NSMFT (WEST FACE) | 3291-ZZ-RP-045 | AD219-486-G-00545 | B | 2 | 1 | commented | 2016-09-07 | 2017-03-19 | 3291-NPCC-PMT-AO-T-02564 |  | 2016-04-02 | 38-22701-N-T-08906
142 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 8", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (WEST FACE) | 3291-ZZ-RP-046 | AD219-486-G-00546 | B | 2 | - | Accepted | 2016-09-10 | 2017-03-16 | 3291-NPCC-PMT-AO-T-02561 |  | 2016-04-02 | 38-22701-N-T-08906
143 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 10", 18" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (EAST FACE) SETUP #1 | 3291-ZZ-RP-047 | AD219-486-G-00547 | B | 2 | 1 | Accepted | 2016-09-28 | 2016-05-29 | 3291-NPCC-PMT-AO-T-01349 |  | 21/08/2016 24/08/2016 | 38-22701-N-T-06953 38-22701-N-T-06998
144 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (EAST FACE) SETUP #2 | 3291-ZZ-RP-048 | AD219-486-G-00548 | B | 2 | 1 | Accepted | 2016-09-19 | 2016-05-31 | 3291-NPCC-PMT-AO-T-01362 |  | 21/08/2016 24/08/2016 | 38-22701-N-T-06953 '38-22701-N-T-06998
145 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (EAST FACE) SETUP #3 | 3291-ZZ-RP-049 | AD219-486-G-00549 | B | 2 | 1 | Accepted | 2016-09-01 | 2016-06-08 | 3291-NPCC-PMT-AO-T-01401 |  | 31/07/2016 | 38-22701-N-T-06705
146 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 18" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-5 (WEST FACE) | 3291-ZZ-RP-050 | AD219-490-G-00550 | B | 2 | 1 | Accepted | 2016-08-20 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01574 |  | 31/07/2016 | 38-22701-N-T-06705
147 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-6 (WEST FACE) | 3291-ZZ-RP-051 | AD219-491-G-00551 | B | 2 | 1 | commented | 2016-09-08 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01578 |  | 31/07/2016 | 38-22701-N-T-06705
148 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-7 (WEST FACE) | 3291-ZZ-RP-052 | AD219-492-G-00552 | B | 2 | 1 | commented | 2016-09-22 | 2016-09-21 | 3291-NPCC-PMT-AO-T-01962 |  | 2016-10-20 | 38-22701-N-T-07554
149 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-9 (EAST FACE) | 3291-ZZ-RP-053 | AD219-494-G-00553 | B | 2 | 1 | Accepted | 2016-07-25 | 2016-09-17 | 3291-NPCC-PMT-AO-T-01937 |  | 2016-10-20 | 38-22701-N-T-07554
150 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT IGD-HAP (WEST FACE) | 3291-ZZ-RP-054 | AD219-486-G-00554 | 0 | 1 | 1 | Accepted | 2016-10-16 | 2016-09-21 | 3291-NPCC-PMT-AO-T-01961 |  | 2016-10-20 | 38-22701-N-T-07554 | [7 empty] | 2016-11-20 | 3291-NPCC-PMT-AO-T-02171 | 2016-12-25 | 38-22701-N-T-08083
151 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-1 (Campaign-1) | 3291-ZZ-RP-055 | AD219-469-G-00555 | C | 2 | 1 | Accepted | 2016-04-01 | 2016-03-17 | 3291-NPCC-PMT-AO-T-00970 |  | 2016-03-27 | 38-22701-N-T-04829 |  | 2016-03-23 | 3291-NPCC-PMT-AO-T-01001
152 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-2 (Campaign-1) | 3291-ZZ-RP-056 | AD219-705-G-00556 | B | 2 | 1 | Accepted | 2016-04-05 | 2016-04-19 | 3291-NPCC-PMT-AO-T-01128 |  | 2016-05-08 | 38-22701-N-T-05533
153 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-3 (Campaign-1) | 3291-ZZ-RP-057 | AD219-705-G-00557 | B | 2 | 1 | Accepted | 2016-04-09 | 2016-05-12 | 3291-NPCC-PMT-AO-T-01243 |  | 2016-05-15 | 38-22701-N-T-05672
154 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-4 (Campaign-1) | 3291-ZZ-RP-058 | AD219-705-G-00558 |  |  | - | - | 2016-04-13
155 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-5 (Campaign-1) | 3291-ZZ-RP-059 | AD219-705-G-00559 |  |  | - | - | 2016-04-17
156 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-6 (Campaign-1) | 3291-ZZ-RP-060 | AD219-705-G-00560 |  |  | - | - | 2016-04-21
157 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-7 (Campaign-1) | 3291-ZZ-RP-061 | AD219-705-G-00561 |  |  | - | - | 2016-04-25
158 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-8 (Campaign-1) | 3291-ZZ-RP-062 | AD219-705-G-00562 |  |  | - | - | 2016-04-29
159 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-9 (Campaign-1) | 3291-ZZ-RP-063 | AD219-705-G-00563 |  |  | - | - | 2016-05-03
160 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-10 (Campaign-1) | 3291-ZZ-RP-064 | AD219-705-G-00564 |  |  | - | - | 2016-05-07
161 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-11 (Campaign-1) | 3291-ZZ-RP-065 | AD219-705-G-00565 |  |  | - | - | 2016-05-11
162 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-12 (Campaign-1) | 3291-ZZ-RP-066 | AD219-705-G-00566 |  |  | - | - | 2016-05-15
163 | STABILITY ANALYSIS DURING TRANSPORTATION OF RCC SLEEPERS TRIP-1 (CAMPAIGN-1) | 3291-ZZ-RP-067 | AD219-705-G-00567 | B | 2 | 1 | commented |  | 2016-03-28 | 3291-NPCC-PMT-AO-T-01020 |  | 2016-06-20 | 38-22701-N-T-06153
164 | MOORING ANALYSIS DURING SHORE PULL AT DAS ISLAND | 3291-ZZ-RP-068 | AD219-705-G-00568 | 0 | 1 | 1 | Accepted |  | 2016-06-15 | 3291-NPCC-PMT-AO-T-01442 |  | 2016-06-30 | 38-22701-N-T-06334 | [7 empty] | 2016-08-02 | 3291-NPCC-PMT-AO-T-01725 | 2016-10-20 | 38-22701-N-T-07554
165 | MOORING ANALYSIS DURING SLEEPER INSTALLATION FOR WHT-2 TO WHT-3 PIPELINES | 3291-ZZ-RP-069 | AD219-485/488-G-00569 | B | 2 | 1 | Accepted |  | 20/07/2016 | 3291-NPCC-PMT-AO-T-01638 |  | 31/07/2016 | 38-22701-N-T-06705
166 | MOORING ANALYSIS DURING SLEEPER INTALLATION FOR WHT-5 TO WHT-4 PIPELINES | 3291-ZZ-RP-070 | AD219-490/489-G-00570 | B | 2 | 1 | Accepted |  | 21/07/2016 | 3291-NPCC-PMT-AO-T-01647 |  | 31/07/2016 | 38-22701-N-T-06705
167 | MOORING ANALYSIS DURING SLEEPER INSTALLATION AT CX-01 FOR 10" EXCESS GAS PIPELINES FROM IGD-HAP TO NSMFT | 3291-ZZ-RP-071 | AD219-469/486-G-00571 | B | 2 | 1 | Accepted |  | 21/07/2016 | 3291-NPCC-PMT-AO-T-01639 |  | 31/07/2016 | 38-22701-N-T-06705
168 | MOORING ANALYSIS DURING SLEEPER INSTALLATION AT CX-01 FOR 16" MAIN OIL PIPELINE (MFT TO DAS ISLAND) | 3291-ZZ-RP-072 | AD219-486-G-00572 | B | 2 | 1 | Accepted |  | 21/07/2016 | 3291-NPCC-PMT-AO-T-01640 |  | 31/07/2016 | 38-22701-N-T-06705
169 | MOORING ANALYSIS DURING INSTALLATION OF RISER FENDER AT IGD-HAP (WEST FACE) | 3291-ZZ-RP-073 | AD219-469-G-00574 | B | 2 | 1 | Accepted |  | 2016-11-15 | 3291-NPCC-PMT-AO-T-02159 |  | 2016-12-25 | 38-22701-N-T-08083
| DRAWINGS | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
165 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0001 | AD219-486/492-PL-00601 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
166 | START UP HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0002 | AD219-486/492-PL-00602 | A |  | - | - | 2016-02-28 | 2016-02-27 | 3291-NPCC-PMT-AO-T-00910
167 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0003 | AD219-486/492-PL-00603 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
168 | BUCKLE DETECTOR DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0004 | AD219-486/492-PL-00604 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
169 | START UP HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0005 | AD219-486/492-PL-00605 | A |  | - | - | 2016-02-28 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00903
170 | LAYDOWN HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0006 | AD219-486/492-PL-00606 | A |  | - | - | 2016-02-28 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00903
171 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0007 | AD219-494/493-PL-00607 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
172 | START UP HEAD DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0008 | AD219-494/493-PL-00608 | B |  | - | - | 2016-02-28 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923
173 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0009 | AD219-494/493-PL-00609 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
174 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0010 | AD219-494/493-PL-00610 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
175 | START UP HEAD DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0011 | AD219-494/493-PL-00611 | B |  | - | - | 2016-02-28 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923
176 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0012 | AD219-494/493-PL-00612 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
177 | BUCKLE DETECTOR DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0013 | AD219-493/494-PL-00613 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
178 | START UP HEAD DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0014 | AD219-493/494-PL-00614 | A |  | - | - | 2016-02-28 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914
179 | LAYDOWN HEAD DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0015 | AD219-493/494-PL-00615 | A |  | - | - | 2016-02-28 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914
180 | BUCKLE DETECTOR DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0016 | AD219-485/488-PL-00616 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
181 | START UP HEAD DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0017 | AD219-485/488-PL-00617 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
182 | LAYDOWN HEAD DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0018 | AD219-485/488-PL-00618 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
183 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0019 | AD219-485/488-PL-00619 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
184 | START UP HEAD DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0020 | AD219-485/488-PL-00620 | B |  | - | - | 2016-02-28 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923
185 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0021 | AD219-485/488-PL-00621 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
186 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0022 | AD219-485/488-PL-00622 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
187 | START UP HEAD DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0023 | AD219-485/488-PL-00623 | B |  | - | - | 2016-02-28 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923
188 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0024 | AD219-485/488-PL-00624 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
189 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0025 | AD219-486/485-PL-00625 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
190 | START UP HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0026 | AD219-486/485-PL-00626 | B |  | - | - | 2016-02-28 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923
191 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0027 | AD219-486/485-PL-00627 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
192 | BUCKLE DETECTOR DETAILS FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0028 | AD219-486/494-PL-00628 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
193 | START UP HEAD DETAILS FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0029 | AD219-486/494-PL-00629 | B |  | - | - | 2016-02-28 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923
194 | LAYDOWN HEAD DETAILS FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0030 | AD219-486/494-PL-00630 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
195 | BUCKLE DETECTOR DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0031 | AD219-486/494-PL-00631 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
196 | START UP HEAD DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0032 | AD219-486/494-PL-00632 |  |  | - | - | 2016-02-28
197 | LAYDOWN HEAD DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0033 | AD219-486/494-PL-00633 |  |  | - | - | 2016-02-28
198 | BUCKLE DETECTOR DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0034 | AD219-494/486-PL-00634 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
199 | START UP HEAD DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0035 | AD219-494/486-PL-00635 | A |  | - | - | 2016-02-28 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00902
200 | LAYDOWN HEAD DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0036 | AD219-494/486-PL-00636 | A |  | - | - | 2016-02-28 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00902
201 | BUCKLE DETECTOR DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0037 | AD219-486/491-PL-00637 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
202 | START UP HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0038 | AD219-486/491-PL-00638 | A |  | - | - | 2016-02-28 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914
203 | LAYDOWN HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0039 | AD219-486/491-PL-00639 | A |  | - | - | 2016-02-28 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914
204 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0040 | AD219-486/491-PL-00640 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
205 | START UP HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0041 | AD219-486/491-PL-00641 | B |  | - | - | 2016-02-28 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923
206 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0042 | AD219-486/491-PL-00642 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
207 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0043 | AD219-486/491-PL-00643 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
208 | START UP HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0044 | AD219-486/491-PL-00644 | B |  | - | - | 2016-02-28 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923
209 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0045 | AD219-486/491-PL-00645 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
210 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0046 | AD219-486/490-PL-00646 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
211 | START UP HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0047 | AD219-486/490-PL-00647 | B |  | - | - | 2016-02-28 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923
212 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0048 | AD219-486/490-PL-00648 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
213 | BUCKLE DETECTOR DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0049 | AD219-486/490-PL-00649 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
214 | START UP HEAD DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0050 | AD219-486/490-PL-00650 | A |  | - | - | 2016-02-28 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914
215 | LAYDOWN HEAD DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0051 | AD219-486/490-PL-00651 | A |  | - | - | 2016-02-28 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914
216 | BUCKLE DETECTOR DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0052 | AD219-490/486-PL-00652 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
217 | START UP HEAD DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0053 | AD219-490/486-PL-00653 | A |  | - | - | 2016-02-28 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00900
218 | LAYDOWN HEAD DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0054 | AD219-490/486-PL-00654 | A |  | - | - | 2016-02-28 | 2016-02-25 | 3291-NPCC-PMT-AO-T-00900
219 | BUCKLE DETECTOR DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0055 | AD219-489/490-PL-00655 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
220 | START UP HEAD DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0056 | AD219-489/490-PL-00656 | A |  | - | - | 2016-02-28 | 2016-02-27 | 3291-NPCC-PMT-AO-T-00910
221 | LAYDOWN HEAD DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0057 | AD219-489/490-PL-00657 | A |  | - | - | 2016-02-28 | 2016-02-27 | 3291-NPCC-PMT-AO-T-00910
222 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0058 | AD219-490/489-PL-00658 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
223 | START UP HEAD DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0059 | AD219-490/489-PL-00659 | B |  | - | - | 2016-02-28 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923
224 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0060 | AD219-490/489-PL-00660 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
225 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0061 | AD219-490/489-PL-00661 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
226 | START UP HEAD DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0062 | AD219-490/489-PL-00662 | B |  | - | - | 2016-02-28 | 2016-03-03 | 3291-NPCC-PMT-AO-T-00923
227 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0063 | AD219-490/489-PL-00663 | B |  | - | - | 2016-02-28 | 2016-03-08 | 3291-NPCC-PMT-AO-T-00940
228 | BUCKLE DETECTOR DETAILS FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0064 | AD219-486-PL-00664 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
229 | START UP HEAD DETAILS FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0065 | AD219-486-PL-00665 |  |  | - | - | 2016-02-28
230 | LAYDOWN HEAD DETAILS FOR 16" MAIN OIL P/L FROM NSMFT TO DAS ISLAND | 3291-NN-0066 | AD219-486-PL-00666 | B | 2 | 1 | - | 2016-02-28 | 2016-12-20 | 3291-NPCC-PMT-AO-T-02276 |  | 2017-02-07 | 38-22701-N-T-08891 38-22701-N-T-08417
231 | BUCKLE DETECTOR DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0067 | AD219-469/486-PL-00667 | A |  | - | - | 2016-02-28 | 2016-02-24 | 3291-NPCC-PMT-AO-T-00898
232 | START UP HEAD DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0068 | AD219-469/486-PL-00668 | A |  | - | - | 2016-02-28 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914
233 | LAYDOWN HEAD DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0069 | AD219-469/486-PL-00669 | C | 2 | 1 | - | 2016-02-28 | 2016-03-01 | 3291-NPCC-PMT-AO-T-00914 |  |  |  |  | 2016-07-27 | 3291-NPCC-PMT-AO-T-01667 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-12-20 | 3291-NPCC-PMT-AO-T-02277 | 2017-01-22 | 38-22701-N-T-08243
234 | LOADING ARRGT & SEAFASTENING OF CC PIPES @ GAC-81 (TRIP-1) WITH BALAST PLAN | 3291-NN-0070 | AD219-705-PL-00670 | B | 2 | 1 | - | 2016-04-01 | 2016-03-28 | 3291-NPCC-PMT-AO-T-01006 |  | 2016-06-20 | 38-22701-N-T-06153
235 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-2) WITH BALAST PLAN | 3291-NN-0071 | AD219-705-PL-00671 | B | 2 | 1 | - | 2016-04-05 | 2016-04-24 | 3291-NPCC-PMT-AO-T-01091 |  | 2016-05-10 | 38-22701-N-T-05581
236 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ CB-6 (TRIP-3) WITH BALAST PLAN | 3291-NN-0072 | AD219-705-PL-00672 | B | 2 | 1 | - | 2016-04-01 | 2016-05-12 | 3291-NPCC-PMT-AO-T-01244 |  | 2016-08-24 | 38-22701-N-T-06998
237 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-4) WITH BALAST PLAN | 3291-NN-0073 | AD219-705-PL-00673 | B | 2 | 1 | - | 2016-04-05 | 2016-05-18 | 3291-NPCC-PMT-AO-T-01126 |  | 2016-05-19 | 38-22701-N-T-05733
238 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-5) WITH BALAST PLAN | 3291-NN-0074 | AD219-705-PL-00674 | B | 2 | 1 | - | 2016-04-09 | 2016-05-26 | 3291-NPCC-PMT-AO-T-01334 |  | 2016-06-20 | 38-22701-N-T-06153
239 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ SEAWAYS-17 (TRIP-6) WITH BALAST PLAN | 3291-NN-0075 | AD219-705-PL-00675 | B | 2 | 1 | - | 2016-04-13 | 2016-06-09 | 3291-NPCC-PMT-AO-T-01410 |  | 2016-08-24 | 38-22701-N-T-06998
240 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ ASTRO-305 (TRIP-7) WITH BALAST PLAN | 3291-NN-0076 | AD219-705-PL-00676 | B | 2 | 1 | - | 2016-04-17 | 2016-06-15 | 3291-NPCC-PMT-AO-T-01436 |  | 2016-06-30 | 38-22701-N-T-06333
241 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ SEAWAYS-17 (TRIP-8) WITH BALAST PLAN | 3291-NN-0077 | AD219-705-PL-00677 | C | 2 | 1 | - | 2016-04-21 | 2016-06-16 | 3291-NPCC-PMT-AO-T-01456 |  | 2016-06-29 | 38-22701-N-T-06291 |  | 2016-06-29 | 3291-NPCC-PMT-AO-T-01530 |  | 2016-08-24 | 38-22701-N-T-06998
242 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-9) WITH BALAST PLAN | 3291-NN-0078 | AD219-705-PL-00678 | B | 2 | 1 | - | 2016-04-25 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01575 |  | 2016-08-24 | 38-22701-N-T-06998
243 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-10) WITH BALAST PLAN | 3291-NN-0079 | AD219-705-PL-00679 | C | 2 | 4 | - | 2016-04-29 | 2016-08-07 | 3291-NPCC-PMT-AO-T-01741 |  |  |  |  | 2016-08-16 | 3291-NPCC-PMT-AO-T-01804 |  | 2016-09-21 | 38-22701-N-T-07287
244 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ CB-6 (TRIP-11) WITH BALAST PLAN | 3291-NN-0080 | AD219-705-PL-00680 | B | 2 | 1 | - | 2016-05-03 | 2016-09-29 | 3291-NPCC-PMT-AO-T-02016 |  | 2016-10-20 | 38-22701-N-T-07554
245 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ SEAWAYS-17 (TRIP-12) WITH BALAST PLAN | 3291-NN-0081 | AD219-705-PL-00681 | B | 2 | 1 | - | 2016-05-07 | 2016-09-29 | 3291-NPCC-PMT-AO-T-02016 |  | 2016-10-20 | 38-22701-N-T-07554
246 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-13) WITH BALAST PLAN | 3291-NN-0082 | AD219-705-PL-00682 | B | 2 | 1 | - | 2016-05-11 | 2016-10-24 | 3291-NPCC-PMT-AO-T-02109 |  | 2016-11-06 | 38-22701-N-T-07649
247 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-14) WITH BALAST PLAN | 3291-NN-0083 | AD219-705-PL-00683 | B | 2 | 1 | - | 2016-05-15 | 2016-10-24 | 3291-NPCC-PMT-AO-T-02105 |  | 2016-11-06 | 38-22701-N-T-07649
248 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ CB-6 (TRIP-15) WITH BALAST PLAN | 3291-NN-0084 | AD219-705-PL-00684 | B | 2 | 1 | - | 2016-05-19 | 2016-10-26 | 3291-NPCC-PMT-AO-T-02113 |  | 2016-11-06 | 38-22701-N-T-07649
249 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ GAC-82 (TRIP-16) | 3291-NN-0085 | AD219-705-PL-00685 | B | 2 | 1 | - | 2016-05-23 | 2017-02-21 | 3291-NPCC-PMT-AO-T-02465 |  | 2017-02-22 | 38-22701-N-T-08542
250 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ GAC-81 (TRIP-17) | 3291-NN-0086 | AD219-705-PL-00686 | B | 2 | 1 | - | 2016-05-27 | 2017-02-21 | 3291-NPCC-PMT-AO-T-02465 |  | 2017-02-22 | 38-22701-N-T-08542
251 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-18) WITH BALAST PLAN | 3291-NN-0087 | AD219-705-PL-00687 |  |  | - | - | 2016-05-31
252 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-19) WITH BALAST PLAN | 3291-NN-0088 | AD219-705-PL-00688 |  |  | - | - | 2016-06-04
253 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-20) WITH BALAST PLAN | 3291-NN-0089 | AD219-705-PL-00689 |  |  | - | - | 2016-06-08
254 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-21) WITH BALAST PLAN | 3291-NN-0090 | AD219-705-PL-00690 |  |  | - | - | 2016-06-12
255 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-22) WITH BALAST PLAN | 3291-NN-0091 | AD219-705-PL-00691 |  |  | - | - | 2016-06-16
256 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-23) WITH BALAST PLAN | 3291-NN-0092 | AD219-705-PL-00692 |  |  | - | - | 2016-06-20
257 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-24) WITH BALAST PLAN | 3291-NN-0093 | AD219-705-PL-00693 |  |  | - | - | 2016-06-24
258 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-25) WITH BALAST PLAN | 3291-NN-0094 | AD219-705-PL-00694 |  |  | - | - | 2016-06-28
259 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-26) WITH BALAST PLAN | 3291-NN-0095 | AD219-705-PL-00695 |  |  | - | - | 2016-07-02
260 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-27) WITH BALAST PLAN | 3291-NN-0096 | AD219-705-PL-00696 |  |  | - | - | 2016-07-06
261 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-28) WITH BALAST PLAN | 3291-NN-0097 | AD219-705-PL-00697 |  |  | - | - | 2016-07-10
262 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-29) WITH BALAST PLAN | 3291-NN-0098 | AD219-705-PL-00698 |  |  | - | - | 2016-07-14
263 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-30) WITH BALAST PLAN | 3291-NN-0099 | AD219-705-PL-00699 |  |  | - | - | 2016-07-18
264 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS @ ZAKHER-101 (TRIP-1) WITH BALAST PLAN | 3291-NN-0100 | AD219-705-PL-00700 | B | 2 | 1 | - | 2016-07-22 | 2016-07-04 | 3291-NPCC-PMT-AO-T-01554 |  | 2016-08-24 | 38-22701-N-T-06998
265 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS @ ZAKHER-101 (TRIP-2) WITH BALAST PLAN | 3291-NN-0101 | AD219-705-PL-00701 | B | 2 | 1 | - | 2016-07-26 | 2017-03-22 | 3291-NPCC-PMT-AO-T-02593 |  | 2017-04-02 | 38-22701-N-T-08906
266 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-3) WITH BALAST PLAN | 3291-NN-0102 | AD219-705-PL-00702 |  |  | - | - | 2016-07-30
267 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-4) WITH BALAST PLAN | 3291-NN-0103 | AD219-705-PL-00703 |  |  | - | - | 2016-08-03
268 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-5) WITH BALAST PLAN | 3291-NN-0104 | AD219-705-PL-00704 |  |  | - | - | 2016-08-07
269 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-6) WITH BALAST PLAN | 3291-NN-0105 | AD219-705-PL-00705 |  |  | - | - | 2016-08-11
270 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-7) WITH BALAST PLAN | 3291-NN-0106 | AD219-705-PL-00706 |  |  | - | - | 2016-08-15
271 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-8) WITH BALAST PLAN | 3291-NN-0107 | AD219-705-PL-00707 |  |  | - | - | 2016-08-19
272 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-9) WITH BALAST PLAN | 3291-NN-0108 | AD219-705-PL-00708 |  |  | - | - | 2016-08-23
273 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-10) WITH BALAST PLAN | 3291-NN-0109 | AD219-705-PL-00709 |  |  | - | - | 2016-08-27
274 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-0110 | AD219-486/492-PL-00710 | B | 2 | 3 | - | 2016-09-01 | 2016-06-21 | 3291-NPCC-PMT-AO-T-01469 |  | 2016-08-09 | 38-22701-N-T-06840
275 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-0111 | AD219-486/492-PL-00711 | B | 2 | 1 | - | 2016-09-22 | 2016-08-11 | 3291-NPCC-PMT-AO-T-01773 |  | 2016-09-21 | 38-22701-N-T-07285
276 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-0112 | AD219-486/492-PL-00712 | C | 2 | 4 | - | 2016-09-04 | 2016-06-15 | 3291-NPCC-PMT-AO-T-01434 |  | 2016-06-29 | 38-22701-N-T-06293 |  | 2016-07-28 | 3291-NPCC-PMT-AO-T-01699 |  | 2016-09-21 | 38-22701-N-T-07287
277 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-0113 | AD219-486/492-PL-00713 | B | 2 | 1 | - | 2016-09-25 | 2016-08-10 | 3291-NPCC-PMT-AO-T-01769 |  | 2016-09-21 | 38-22701-N-T-07285
278 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-0114 | AD219-494/493-PL-00714 | B | 2 | 1 | - | 2016-07-25 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01833 |  | 2016-09-21 | 38-22701-N-T-07285
279 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-0115 | AD219-494/493-PL-00715 | C | 2 | 1 | - | 2016-07-12 | 2016-08-04 | 3291-NPCC-PMT-AO-T-01735 |  | 2016-09-21 | 38-22701-N-T-07285 |  | 2016-09-20 | 3291-NPCC-PMT-AO-T-01955 |  | 2016-10-20 | 38-22701-N-T-07554
280 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-0116 | AD219-494/493-PL-00716 | B | 2 | 1 | - | 2016-07-28 | 2016-08-28 | 3291-NPCC-PMT-AO-T-01856 |  | 2016-09-21 | 38-22701-N-T-07285
281 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-0117 | AD219-494/493-PL-00717 | B | 2 | 1 | - | 2016-07-15 | 2016-08-04 | 3291-NPCC-PMT-AO-T-01736 |  | 2016-09-21 | 38-22701-N-T-07285
282 | TEMPORARY KNEE BRACE DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-8) | 3291-NN-0118 | AD219-493/494-PL-00718 | B | 2 | 1 | - | 2016-07-18 | 2016-08-07 | 3291-NPCC-PMT-AO-T-01745 |  | 2016-09-21 | 38-22701-N-T-07285
283 | TEMPORARY KNEE BRACE DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-9) | 3291-NN-0119 | AD219-493/494-PL-00719 | B | 2 | 1 | - | 2016-08-01 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01838 |  | 2016-09-21 | 38-22701-N-T-07285
284 | TEMPORARY KNEE BRACE DETAIL FOR 12" WF P/L FROM WHT-3 TO WHT-2 (@WHT-2) | 3291-NN-0120 | AD219-485/488-PL-00720 | B | 2 | 1 | - | 2016-11-01 | 2017-03-29 | 3291-NPCC-PMT-AO-T-02635 |  | 2017-05-08 | 38-22701-N-T-09233
285 | TEMPORARY KNEE BRACE DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0121 | AD219-485/488-PL-00721 | B | 2 | 1 | - | 2016-10-19 | 2017-06-18 | 3291-NPCC-PMT-AO-T-02993 |  | 2017-08-20 | 38-22701-N-T-09983
286 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-0122 | AD219-485/488-PL-00722 | B | 2 | 4 | - | 2016-11-04 | 2017-04-03 | 3291-NPCC-PMT-AO-T-02653 |  | 2017-05-02 | 38-22701-N-T-09199
287 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0123 | AD219-485/488-PL-00723 | B | 2 | 1 | - | 2016-10-22 | 2017-06-13 | 3291-NPCC-PMT-AO-T-02990 |  | 2017-08-20 | 38-22701-N-T-09983
288 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-2 ) | 3291-NN-0124 | AD219-485/488-PL-00724 | B | 2 | 1 | - | 2016-11-07 | 2017-03-30 | 3291-NPCC-PMT-AO-T-02650 |  | 2017-05-08 | 38-22701-N-T-09233
289 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-3 ) | 3291-NN-0125 | AD219-485/488-PL-00725 | B | 2 | 1 | - | 2016-10-25 | 2017-06-18 | 3291-NPCC-PMT-AO-T-03006 |  | 2017-08-20 | 38-22701-N-T-09983
290 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 (@NSMFT) | 3291-NN-0126 | AD219-486/485-PL-00726 | B | 2 | 1 | - | 2016-09-07 | 2017-02-13 | 3291-NPCC-PMT-AO-T-02434 |  | 2017-04-02 | 38-22701-N-T-08905
291 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 (@WHT-2) | 3291-NN-0127 | AD219-486/485-PL-00727 |  |  | - | - | 2016-11-10
292 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-0128 | AD219-486/494-PL-00728 | B | 2 | 1 | - | 2016-09-10 | 2017-03-05 | 3291-NPCC-PMT-AO-T-02507 |  | 2017-04-02 | 38-22701-N-T-08905
293 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-0129 | AD219-486/494-PL-00729 | B | 2 | 1 | - | 2016-10-02 | 2016-09-01 | 3291-NPCC-PMT-AO-T-01883 |  | 2016-09-21 | 38-22701-N-T-07285
294 | TEMPORARY KNEE BRACE DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-0130 | AD219-486/494-PL-00730 | B | 2 | 1 | - | 2016-09-13 | 2017-02-26 | 3291-NPCC-PMT-AO-T-02477 |  | 2017-04-02 | 38-22701-N-T-08905
295 | TEMPORARY KNEE BRACE DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-0131 | AD219-486/494-PL-00731 | B | 2 | 1 | - | 2016-10-05 | 2016-08-29 | 3291-NPCC-PMT-AO-T-01865 |  | 2016-09-21 | 38-22701-N-T-07285
296 | TEMPORARY KNEE BRACE DETAILS FOR 14" WF P/L FROM WHT-9 TO NSMFT (@WHT-9) | 3291-NN-0132 | AD219-494/486-PL-00732 | B | 2 | 1 | - | 2016-10-08 | 2016-08-25 | 3291-NPCC-PMT-AO-T-01845 |  | 2016-09-21 | 38-22701-N-T-07285
297 | TEMPORARY KNEE BRACE DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT (@NSMFT) | 3291-NN-0133 | AD219-494/486-PL-00733 | B | 2 | 1 | - | 2016-09-16 | 2017-03-13 | 3291-NPCC-PMT-AO-T-02529 |  | 2017-04-02 | 38-22701-N-T-08905
298 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0134 | AD219-486/491-PL-00734 | C | 2 | 4 | - | 2016-09-19 | 2016-03-23 | 3291-NPCC-PMT-AO-T-01008 |  | 2016-04-18 | 38-22701-N-T-05223 |  | 2016-07-28 | 3291-NPCC-PMT-AO-T-01693 |  | 2016-09-21 | 38-22701-N-T-07287
299 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0135 | AD219-486/491-PL-00735 | B | 2 | 1 | - | 2016-09-08 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01605 |  | 2016-07-31 | 38-22701-N-T-06705
300 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0136 | AD219-486/491-PL-00736 | B | 2 | 4 | - | 2016-09-22 | 2016-07-26 | 3291-NPCC-PMT-AO-T-01665 |  | 2016-09-21 | 38-22701-N-T-07287
301 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0137 | AD219-486/491-PL-00737 | B | 2 | 1 | - | 2016-09-11 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01614 |  | 2016-07-31 | 38-22701-N-T-06705
302 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0138 | AD219-486/491-PL-00738 | B | 2 | - | - | 2016-09-25 | 2016-07-27 | 3291-NPCC-PMT-AO-T-01670 |  | 2016-09-21 | 38-22701-N-T-07287
303 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0139 | AD219-486/491-PL-00739 | B | 2 | 1 | - | 2016-09-14 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01610 |  | 2016-07-31 | 38-22701-N-T-06705
304 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-0140 | AD219-486/490-PL-00740 | B | 2 | 4 | - | 2016-09-28 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01678 |  | 2016-09-21 | 38-22701-N-T-07287
305 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-0141 | AD219-486/490-PL-00741 | B | 2 | 1 | - | 2016-08-25 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01575 |  | 2016-08-24 | 38-22701-N-T-06998
306 | TEMPORARY KNEE BRACE DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-0142 | AD219-486/490-PL-00742 | B | 2 | - | - | 2016-10-01 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01683 |  | 2016-09-21 | 38-22701-N-T-07287
307 | TEMPORARY KNEE BRACE DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-0143 | AD219-486/490-PL-00743 | B | 2 | 1 | - | 2016-08-28 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01577 |  | 2016-07-14 | 38-22701-N-T-06475
308 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT (@WHT-5) | 3291-NN-0144 | AD219-490/486-PL-00744 | B | 2 | 1 | - | 2016-08-31 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01572 |  | 2016-07-14 | 38-22701-N-T-06474
309 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT (@NSMFT) | 3291-NN-0145 | AD219-490/486-PL-00745 | C | 3 | 1 | - | 2016-10-04 | 2016-02-21 | 3291-NPCC-PMT-AO-T-01127 |  | 2016-05-08 | 38-22701-N-T-05559 |  | 2016-07-31 | 3291-NPCC-PMT-AO-T-01715 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-05-15 | 3291-NPCC-PMT-AO-T-01248 | 2016-05-16 | 38-22701-N-T-05707
310 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-4) | 3291-NN-0146 | AD219-489/490-PL-00746 | B | 2 | 1 | - | 2016-08-07 | 2016-06-22 | 3291-NPCC-PMT-AO-T-01475 |  | 2016-06-30 | 38-22701-N-T-06347 |  |  |  |  | 2016-07-31 | 38-22701-N-T-06705
311 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-5) | 3291-NN-0147 | AD219-489/490-PL-00747 | B | 2 | 1 | - | 2016-08-20 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01537 |  | 2016-07-14 | 38-22701-N-T-06473
312 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-0148 | AD219-490/489-PL-00748 | B | 2 | 1 | - | 2016-08-23 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01561 |  | 2016-07-14 | 38-22701-N-T-06472
313 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-4) | 3291-NN-0149 | AD219-490/489-PL-00749 | B | 2 | 1 | - | 2016-08-10 | 2016-06-28 | 3291-NPCC-PMT-AO-T-01474 |  | 2016-06-30 | 38-22701-N-T-06348 |  |  |  |  | 2016-07-31 | 38-22701-N-T-06705
314 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-5 ) | 3291-NN-0150 | AD219-490/489-PL-00750 | B | 2 | 1 | - | 2016-08-26 | 2016-07-04 | 3291-NPCC-PMT-AO-T-01553 |  | 2016-07-14 | 38-22701-N-T-06471
315 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-4 ) | 3291-NN-0151 | AD219-490/489-PL-00751 | B | 2 | 1 | - | 2016-08-13 | 2016-06-26 | 3291-NPCC-PMT-AO-T-01500 |  | 2016-06-30 | 38-22701-N-T-06346
316 | TEMPORARY KNEE BRACE DETAILS FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT @ NSMFT | 3291-NN-0152 | AD219-486-PL-00752 | B | 2 | 1 | - | 2016-10-23 | 2017-03-08 | 3291-NPCC-PMT-AO-T-02513 |  | 2017-04-02 | 38-22701-N-T-08905
317 | TEMPORARY KNEE BRACE DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@ IGD-HAP) | 3291-NN-0153 | AD219-469/486-PL-00753 | B | 2 | 1 | - | 2016-10-16 | 2016-09-22 | 3291-NPCC-PMT-AO-T-01977 |  | 2016-10-20 | 38-22701-N-T-07554
318 | TEMPORARY KNEE BRACE DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@NSMFT) | 3291-NN-0154 | AD219-469/486-PL-00754 | B | 2 | 1 | - | 2016-10-26 | 2017-03-11 | 3291-NPCC-PMT-AO-T-02520 |  | 2017-04-02 | 38-22701-N-T-08905
319 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0155 | AD219-486/492-PL-00755 |  |  | - | - | 2016-10-26
320 | HYDROTEST DIAGRAM FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0156 | AD219-486/492-PL-00756 |  |  | - | - | 2016-10-26
321 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0157 | AD219-494/493-PL-00757 |  |  | - | - | 2016-10-26
322 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0158 | AD219-494/493-PL-00758 |  |  | - | - | 2016-10-26
323 | HYDROTEST DIAGRAM FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0159 | AD219-493/494-PL-00759 |  |  | - | - | 2016-10-26
324 | HYDROTEST DIAGRAM FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0160 | AD219-485/488-PL-00760 |  |  | - | - | 2016-10-26
325 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0161 | AD219-485/488-PL-00761 |  |  | - | - | 2016-10-26
326 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0162 | AD219-485/488-PL-00762 |  |  | - | - | 2016-10-26
327 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0163 | AD219-486/485-PL-00763 |  |  | - | - | 2016-10-26
328 | HYDROTEST DIAGRAM FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0164 | AD219-486/494-PL-00764 |  |  | - | - | 2016-10-26
329 | HYDROTEST DIAGRAM FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0165 | AD219-486/494-PL-00765 |  |  | - | - | 2016-10-26
330 | HYDROTEST DIAGRAM FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0166 | AD219-494/486-PL-00766 |  |  | - | - | 2016-10-26
331 | HYDROTEST DIAGRAM FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0167 | AD219-486/491-PL-00767 |  |  | - | - | 2016-10-26
332 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0168 | AD219-486/491-PL-00768 |  |  | - | - | 2016-10-26
333 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0169 | AD219-486/491-PL-00769 |  |  | - | - | 2016-10-26
334 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0170 | AD219-486/490-PL-00770 |  |  | - | - | 2016-10-26
335 | HYDROTEST DIAGRAM FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0171 | AD219-486/490-PL-00771 |  |  | - | - | 2016-10-26
336 | HYDROTEST DIAGRAM FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0172 | AD219-490/486-PL-00772 |  |  | - | - | 2016-10-26
337 | HYDROTEST DIAGRAM FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0173 | AD219-489/490-PL-00773 |  |  | - | - | 2016-10-26
338 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0174 | AD219-490/489-PL-00774 |  |  | - | - | 2016-10-26
339 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0175 | AD219-490/489-PL-00775 |  |  | - | - | 2016-10-26
340 | HYDROTEST DIAGRAM FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0176 | AD219-486-PL-00776 |  |  | - | - | 2016-10-26
341 | HYDROTEST DIAGRAM FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0177 | AD219-469/486-PL-00777 |  |  | - | - | 2016-10-26
342 | DETAIL OF 6" TEMPORARY PIG LAUNCHER 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0178 | AD219-486/492-PL-00778 | B | 2 | - | - | 2016-09-01
343 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0179 | AD219-486/492-PL-00779 |  |  | - | - | 2016-09-04
344 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0180 | AD219-494/493-PL-00780 |  |  | - | - | 2016-07-12
345 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0181 | AD219-494/493-PL-00781 |  |  | - | - | 2016-07-15
346 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0182 | AD219-493/494-PL-00782 |  |  | - | - | 2016-07-18
347 | DETAIL OF 12" TEMPORARY PIG LAUNCHER 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0183 | AD219-485/488-PL-00783 | B | 2 | - | - | 2016-10-19
348 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0184 | AD219-485/488-PL-00784 |  |  | - | - | 2016-10-22
349 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0185 | AD219-485/488-PL-00785 |  |  | - | - | 2016-10-25
350 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0186 | AD219-486/485-PL-00786 |  |  | - | - | 2016-09-07
351 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0187 | AD219-486/494-PL-00787 |  |  | - | - | 2016-09-10
352 | DETAIL OF 8" TEMPORARY PIG LAUNCHER 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0188 | AD219-486/494-PL-00788 | B | 2 | - | - | 2016-09-13
353 | DETAIL OF 14" TEMPORARY PIG LAUNCHER14" WF P/L FROM WHT-9 TO NSMFT | 3291-NN-0189 | AD219-494/486-PL-00789 | B | 2 | - | - | 2016-09-16
354 | DETAIL OF 10" TEMPORARY PIG LAUNCHER 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0190 | AD219-486/491-PL-00790 | B | 2 | - | - | 2016-09-08
355 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0191 | AD219-486/491-PL-00791 |  |  | - | - | 2016-09-11
356 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0192 | AD219-486/491-PL-00792 |  |  | - | - | 2016-09-14
357 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0193 | AD219-486/490-PL-00793 |  |  | - | - | 2016-08-25
358 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0194 | AD219-486/490-PL-00794 |  |  | - | - | 2016-08-28
359 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0195 | AD219-490/486-PL-00795 |  |  | - | - | 2016-08-31
360 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0196 | AD219-489/490-PL-00796 |  |  | - | - | 2016-08-07
361 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0197 | AD219-490/489-PL-00797 |  |  | - | - | 2016-08-10
362 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0198 | AD219-490/489-PL-00798 |  |  | - | - | 2016-08-13
363 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0199 | AD219-486-PL-00799 |  |  | - | - | 2016-10-23
364 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0200 | AD219-469/486-PL-00800 |  |  | - | - | 2016-10-16
365 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-0201 | AD219-486/492-PL-00801 | 0 | 1 | - | - | 2016-09-01 | 2016-06-21 | 3291-NPCC-PMT-AO-T-01469 |  | 2016-08-09 | 38-22701-N-T-06840 |  | 24/07/2016 16/08/2016 | 3291-NPCC-PMT-AO-T-01653 3291-NPCC-PMT-AO-T-01795 |  | 2016-08-09 | 38-22701-N-T-06842 |  | 2016-09-04 | 3291-NPCC-PMT-AO-T-01893 | 2016-09-21 | 38-22701-N-T-07287
366 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-0202 | AD219-486/492-PL-00802 | C | 2 | 1 | - | 2016-09-22 | 2016-08-11 | 3291-NPCC-PMT-AO-T-01773 |  | 2016-09-21 | 38-22701-N-T-07285 |  | 2017-03-27 | 3291-NPCC-PMT-AO-T-02622 |  | 2017-05-08 | 38-22701-N-T-09233
367 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WF P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-0203 | AD219-486/492-PL-00803 | 1 | 1 | 4 | - | 2016-09-04 | 2016-06-15 | 3291-NPCC-PMT-AO-T-01434 |  | 2016-06-29 | 38-22701-N-T-06293 |  | 28/07/2016 16/08/2016 | 3291-NPCC-PMT-AO-T-01699 3291-NPCC-PMT-AO-T-01795 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 04/09/2016 14/9/2016 | 3291-NPCC-PMT-AO-T-01893 3291-NPCC-PMT-AO-T-01920 | 2016-09-21 | 38-22701-N-T-07287
368 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WF P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-0204 | AD219-486/492-PL-00804 | C | 2 | 1 | - | 2016-09-25 | 2016-08-10 | 3291-NPCC-PMT-AO-T-01769 |  |  |  |  | 2017-03-27 | 3291-NPCC-PMT-AO-T-02622 |  | 2017-05-08 | 38-22701-N-T-09233
369 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-0205 | AD219-494/493-PL-00805 | B | 2 | - | - | 2016-07-25 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01833 |  | 2016-09-21 | 38-22701-N-T-07285
370 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-0206 | AD219-494/493-PL-00806 | D | 2 | 1 | - | 2016-07-12 | 2016-08-04 | 3291-NPCC-PMT-AO-T-01735 |  | 2016-09-21 | 38-22701-N-T-07285 |  | 2016-09-06 | 3291-NPCC-PMT-AO-T-01901 |  | 2016-09-21 | 38-22701-N-T-07285 |  | 2016-09-29 | 3291-NPCC-PMT-AO-T-02007 | 2016-10-20 | 38-22701-N-T-07554
371 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-0207 | AD219-494/493-PL-00807 | B | 2 | 1 | - | 2016-07-28 | 2016-08-28 | 3291-NPCC-PMT-AO-T-01856 |  | 2016-09-21 | 38-22701-N-T-07285
372 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-0208 | AD219-494/493-PL-00808 | D | 2 | 1 | - | 2016-07-15 | 2016-08-04 | 3291-NPCC-PMT-AO-T-01736 |  | 2016-09-21 | 38-22701-N-T-07285 |  | 2016-09-06 | 3291-NPCC-PMT-AO-T-01901 |  | 2016-09-21 | 38-22701-N-T-07285 |  | 2016-09-29 | 3291-NPCC-PMT-AO-T-02007 | 2016-10-20 | 38-22701-N-T-07554
373 | RISER/SPOOL LIFTING AND INSTALLATION FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-8) | 3291-NN-0209 | AD219-493/494-PL-00809 | D | 2 | 1 | - | 2016-07-18 | 2016-08-07 | 3291-NPCC-PMT-AO-T-01745 |  | 2016-09-21 | 38-22701-N-T-07285 |  | 2016-09-06 | 3291-NPCC-PMT-AO-T-01901 |  | 2016-09-21 | 38-22701-N-T-07285 |  | 2016-09-29 | 3291-NPCC-PMT-AO-T-02007 | 2016-10-20 | 38-22701-N-T-07554
374 | RISER/SPOOL LIFTING AND INSTALLATION FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-9) | 3291-NN-0210 | AD219-493/494-PL-00810 | B | 2 | 1 | - | 2016-08-01 | 2016-08-23 | 3291-NPCC-PMT-AO-T-01838 |  | 2016-09-21 | 38-22701-N-T-07285
375 | RISER/SPOOL LIFTING AND INSTALLATION FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-0211 | AD219-485/488-PL-00811 | B | 2 | - | - | 2016-11-01 | 2017-03-29 | 3291-NPCC-PMT-AO-T-02635 |  | 2017-05-08 | 38-22701-N-T-09233
376 | RISER/SPOOL LIFTING AND INSTALLATION FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0212 | AD219-485/488-PL-00812 | D | 2 | 1 | Accepted | 2016-10-19 | 2017-06-18 | 3291-NPCC-PMT-AO-T-02993 |  | 2017-08-20 | 38-22701-N-T-09983 |  | 2017-11-08 | 3291-NPCC-PMT-AO-T-03448 3291-NPCC-PMT-AO-T-03451 |  | 2018-08-05 | 38-22701-N-T-11401
377 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-0213 | AD219-485/488-PL-00813 | B | 2 | 1 | - | 2016-11-04 | 2017-03-30 | 3291-NPCC-PMT-AO-T-02641 |  | 2017-05-08 | 38-22701-N-T-09233
378 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0214 | AD219-485/488-PL-00814 | C | 2 | 1 | Accepted | 2016-10-22 | 2017-06-13 | 3291-NPCC-PMT-AO-T-02990 |  | 2017-08-20 | 38-22701-N-T-09983 |  | 2017-11-08 | 3291-NPCC-PMT-AO-T-03448 |  | 2018-08-05 | 38-22701-N-T-11401
379 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-0215 | AD219-485/488-PL-00815 | B | 2 | 1 | - | 2016-11-07 | 2017-03-30 | 3291-NPCC-PMT-AO-T-02650 |  | 2017-05-08 | 38-22701-N-T-09233
380 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0216 | AD219-485/488-PL-00816 | C | 2 | 1 | Accepted | 2016-10-25 | 2017-06-18 | 3291-NPCC-PMT-AO-T-03006 |  | 2017-08-20 | 38-22701-N-T-09983 |  | 2017-11-08 | 3291-NPCC-PMT-AO-T-03448 |  | 2018-08-05 | 38-22701-N-T-11401
381 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-2 (@NSMFT) | 3291-NN-0217 | AD219-486/485-PL-00817 | C | 2 | 1 | - | 2016-09-07 | 2017-02-13 | 3291-NPCC-PMT-AO-T-02434 |  | 2017-04-02 | 38-22701-N-T-08905 |  | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 |  | 2017-05-08 | 38-22701-N-T-09233
382 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-2 (@WHT-2) | 3291-NN-0218 | AD219-486/485-PL-00818 | C | 2 | 1 | - | 2016-11-10 | 2017-03-24 | 3291-NPCC-PMT-AO-T-02608 |  |  |  |  | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 |  | 2017-05-08 | 38-22701-N-T-09233
383 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-0219 | AD219-486/494-PL-00819 | C | 2 | 1 | - | 2016-09-10 | 2017-03-05 | 3291-NPCC-PMT-AO-T-02507 |  | 2017-04-02 | 38-22701-N-T-08905 |  | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 |  | 2017-05-08 | 38-22701-N-T-09233
384 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-0220 | AD219-486/494-PL-00820 | C | 2 | 1 | - | 2016-10-02 | 2016-09-01 | 3291-NPCC-PMT-AO-T-01883 |  | 2016-09-21 | 38-22701-N-T-07285 |  | 2016-09-28 | 3291-NPCC-PMT-AO-T-02005 |  | 2016-12-25 | 38-22701-N-T-08083
385 | RISER/SPOOL LIFTING AND INSTALLATION FOR 8" WI P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-0221 | AD219-486/494-PL-00821 | C | 2 | 1 | - | 2016-09-13 | 2017-02-26 | 3291-NPCC-PMT-AO-T-02477 |  | 2017-04-02 | 38-22701-N-T-08905 |  | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 |  | 2017-05-08 | 38-22701-N-T-09233
386 | RISER/SPOOL LIFTING AND INSTALLATION FOR 8" WI P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-0222 | AD219-486/494-PL-00822 | 0 | 1 | 1 | - | 2016-10-05 | 2016-08-29 | 3291-NPCC-PMT-AO-T-01865 |  | 2016-09-21 | 38-22701-N-T-07285 | [7 empty] | 2016-12-05 | 3291-NPCC-PMT-AO-T-02230 | 2016-12-25 | 38-22701-N-T-08083
387 | RISER/SPOOL LIFTING AND INSTALLATION FOR 14" WF P/L FROM WHT-9 TO NSMFT (@WHT-9) | 3291-NN-0223 | AD219-494/486-PL-00823 | B | 2 | 1 | - | 2016-10-08 | 2016-08-25 | 3291-NPCC-PMT-AO-T-01845 |  | 2016-09-21 | 38-22701-N-T-07285
388 | RISER/SPOOL LIFTING AND INSTALLATION FOR WF 14" P/L FROM WHT-9 TO NSMFT (@NSMFT) | 3291-NN-0224 | AD219-494/486-PL-00824 | C | 2 | 1 | - | 2016-09-16 | 2017-03-13 | 3291-NPCC-PMT-AO-T-02529 |  | 2017-04-02 | 38-22701-N-T-08905 |  | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 |  | 2017-05-08 | 38-22701-N-T-09233
389 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WF P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0225 | AD219-486/491-PL-00825 | 0 | 1 | 4 | - | 2016-09-19 | 2016-03-23 | 3291-NPCC-PMT-AO-T-01008 |  | 2016-04-18 | 38-22701-N-T-05223 |  | 28/07/2016 16/08/2016 | 3291-NPCC-PMT-AO-T-01693 3291-NPCC-PMT-AO-T-01795 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-09-04 | 3291-NPCC-PMT-AO-T-01893 | 2016-09-21 | 38-22701-N-T-07287
390 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WF P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0226 | AD219-486/491-PL-00826 | 0 | 1 | 4 | - | 2016-09-08 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01605 |  | 2016-07-31 | 38-22701-N-T-06705 | [7 empty] | 2016-09-05 | 3291-NPCC-PMT-AO-T-01899 | 2016-09-21 | 38-22701-N-T-07287
391 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0227 | AD219-486/491-PL-00827 | C | 2 | 4 | - | 2016-09-22 | 2016-07-26 | 3291-NPCC-PMT-AO-T-01665 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-08-16 | 3291-NPCC-PMT-AO-T-01795 |  | 2016-09-21 | 38-22701-N-T-07287
392 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0228 | AD219-486/491-PL-00828 | 0 | 1 | 1 | - | 2016-09-11 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01614 |  | 2016-07-31 | 38-22701-N-T-06705 |  | 2016-11-23 | 3291-NPCC-PMT-AO-T-02195 |  | 2016-12-25 | 38-22701-N-T-08083
393 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0229 | AD219-486/491-PL-00829 | 0 | 1 | 4 | - | 2016-09-25 | 2016-07-27 | 3291-NPCC-PMT-AO-T-01670 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-08-16 | 3291-NPCC-PMT-AO-T-01795 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-09-04 | 3291-NPCC-PMT-AO-T-01893 | 2016-09-21 | 38-22701-N-T-07287
394 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0230 | AD219-486/491-PL-00830 | 1 | 1 | 1 | - | 2016-09-14 | 2016-07-17 | 3291-NPCC-PMT-AO-T-01610 |  | 2016-07-31 | 38-22701-N-T-06705 |  | 2016-09-05 | 3291-NPCC-PMT-AO-T-01899 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-11-07 | 3291-NPCC-PMT-AO-T-02139 | 2016-12-25 | 38-22701-N-T-08083
395 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-0231 | AD219-486/490-PL-00831 | 0 | 1 | 4 | - | 2016-09-28 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01678 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-08-16 | 3291-NPCC-PMT-AO-T-01795 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-09-04 | 3291-NPCC-PMT-AO-T-01893 | 2016-09-21 | 38-22701-N-T-07287
396 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-0232 | AD219-486/490-PL-00832 | 1 | 1 | 1 | - | 2016-08-25 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01575 |  | 2016-08-24 | 38-22701-N-T-06998 |  | 2016-09-05 | 3291-NPCC-PMT-AO-T-01899 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-11-07 | 3291-NPCC-PMT-AO-T-02139 | 2016-12-25 | 38-22701-N-T-08083
397 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WI P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-0233 | AD219-486/490-PL-00833 | 1 | 1 | 4 | - | 2016-10-01 | 2016-07-28 | 3291-NPCC-PMT-AO-T-01683 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 2016-08-16 | 3291-NPCC-PMT-AO-T-01795 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 04/09/2016 14/9/2016 | 3291-NPCC-PMT-AO-T-01893 3291-NPCC-PMT-AO-T-01920 | 2016-09-21 | 38-22701-N-T-07287
398 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" WI P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-0234 | AD219-486/490-PL-00834 | 0 | 1 | 1 | - | 2016-08-28 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01577 |  | 2016-07-14 | 38-22701-N-T-06475 | [7 empty] | 2016-10-26 | 3291-NPCC-PMT-AO-T-02111 | 2016-11-06 | 38-22701-N-T-07648
399 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" WF P/L FROM WHT-5 TO NSMFT (@WHT-5) | 3291-NN-0235 | AD219-490/486-PL-00835 | 0 | 1 | 1 | - | 2016-08-31 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01572 |  | 2016-07-14 | 38-22701-N-T-06474 | [7 empty] | 2016-10-19 | 3291-NPCC-PMT-AO-T-02087 | 2016-11-06 | 38-22701-N-T-07648
400 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" WF P/L FROM WHT-5 TO NSMFT (@NSMFT) | 3291-NN-0236 | AD219-490/486-PL-00836 | 1 | 1 | 1 | - | 2016-10-04 | 2016-06-07 | 3291-NPCC-PMT-AO-T-01398 |  | 2016-06-20 | 38-22701-N-T-06162 |  | 31/07/2016 16/08/2016 | 3291-NPCC-PMT-AO-T-01713 3291-NPCC-PMT-AO-T-01798 |  | 2016-09-21 | 38-22701-N-T-07287 |  | 04/09/2016/ 20/9/2016 | 3291-NPCC-PMT-AO-T-01893/ '3291-NPCC-PMT-AO-T-01953 | 2016-10-20 | 38-22701-N-T-07554
401 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-4) | 3291-NN-0237 | AD219-489/490-PL-00837 | 0 | 1 | 1 | - | 2016-08-07 | 2016-06-22 | 3291-NPCC-PMT-AO-T-01475 |  | 2016-06-30 | 38-22701-N-T-06347 |  |  |  |  | 2016-07-31 | 38-22701-N-T-06705 |  | 2016-11-21 | 3291-NPCC-PMT-AO-T-02175 | 2016-12-25 | 38-22701-N-T-08083
402 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-5) | 3291-NN-0238 | AD219-489/490-PL-00837 | 0 | 1 | 4 | - | 2016-08-20 | 2016-06-30 | 3291-NPCC-PMT-AO-T-01537 |  | 2016-07-14 | 38-22701-N-T-06473 | [7 empty] | 2016-08-09 | 3291-NPCC-PMT-AO-T-01762 | 2016-09-21 | 38-22701-N-T-07287
403 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-0239 | AD219-490/489-PL-00839 | B | 2 | 1 | - | 2016-08-23 | 2016-07-10 | 3291-NPCC-PMT-AO-T-01561 |  | 2016-07-14 | 38-22701-N-T-06472
404 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-4) | 3291-NN-0240 | AD219-490/489-PL-00840 | 0 | 1 | 1 | - | 2016-08-10 | 2016-06-28 | 3291-NPCC-PMT-AO-T-01474 |  | 2016-06-30 | 38-22701-N-T-06348 |  |  |  |  | 2016-07-31 | 38-22701-N-T-06705 |  | 2016-11-17 | 3291-NPCC-PMT-AO-T-02164 | 2016-11-17 | 38-22701-N-T-07750
405 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-0241 | AD219-490/489-PL-00841 | 0 | 1 | 1 | - | 2016-08-26 | 2016-07-04 | 3291-NPCC-PMT-AO-T-01553 |  | 2016-07-14 | 38-22701-N-T-06471 |  | 2016-11-15 | 3291-NPCC-PMT-AO-T-02160 |  | 2016-12-25 | 38-22701-N-T-08083
406 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-4) | 3291-NN-0242 | AD219-490/489-PL-00842 | B | 2 | 1 | - | 2016-08-13 | 2016-06-26 | 3291-NPCC-PMT-AO-T-01500 |  | 2016-06-30 | 38-22701-N-T-06346
407 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0243 | AD219-486-PL-00843 | C | 2 | 1 | - | 2016-10-23 | 2017-03-08 | 3291-NPCC-PMT-AO-T-02513 |  | 2017-04-02 | 38-22701-N-T-08905 |  | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 |  | 2017-05-08 | 38-22701-N-T-09233
408 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@IGD-HAP) | 3291-NN-0244 | AD219-469/486-PL-00844 | 0 | 1 | 1 | - | 2016-10-16 | 2016-09-22 | 3291-NPCC-PMT-AO-T-01977 |  | 2016-10-20 | 38-22701-N-T-07554 |  | 12/10/2016 16/10/2016 | 3291-NPCC-PMT-AO-T-01992 3291-NPCC-PMT-AO-T-02074 |  |  |  |  | 2016-10-30 | 3291-NPCC-PMT-AO-T-02117 | 2016-11-30 | 38-22701-N-T-07606
409 | RISER/SPOOL LIFTING AND INSTALLATION FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@NSMFT) | 3291-NN-0245 | AD219-469/486-PL-00845 | C | 2 | 1 | - | 2016-10-26 | 2017-03-11 | 3291-NPCC-PMT-AO-T-02520 |  | 2017-04-02 | 38-22701-N-T-08905 |  | 2017-03-28 | 3291-NPCC-PMT-AO-T-02628 |  | 2017-05-08 | 38-22701-N-T-09233
410 | TYPICAL LIFITNG AND INSTALLATION OF RCC SLEEPER AT NEAR IGD-HAP PLATFORM USING SWIBER ATLANTIS | 3291-NN-0246 | AD219-469-PL-00846 | D | 2 | 1 | Accepted | - | 2016-03-21 | 3291-NPCC-PMT-AO-T-00982 |  | 2016-08-24 | 38-22701-N-T-06997 |  | 05/04/2016 24/04/2016 | 3291-NPCC-PMT-AO-T-01012 3291-NPCC-PMT-AO-T-01094 |  | 2016-05-02 | 38-22701-N-T-05390
411 | LOADING ARRGT & SEAFASTENING DETAILS OF RCC SLEEPERS BY MICHLYN-285 (TRIP-1) | 3291-NN-0247 | AD219-705-PL-00847 | D | 2 | 1 | - | - | 2016-03-17 | 3291-NPCC-PMT-AO-T-00971 |  | 2016-03-27 | 38-22701-N-T-04773 |  | 05/04/2016 24/04/2016 | 3291-NPCC-PMT-AO-T-01012 3291-NPCC-PMT-AO-T-01088 |  | 2016-05-08 | 38-22701-N-T-05580
412 | LOADING ARRGT & SEAFASTENING DETAILS OF RCC SLEEPERS BY MICHLYN-285 (TRIP-2) | 3291-NN-0248 | AD219-705-PL-00848 | B | 2 | 1 | - |  | 2016-04-21 | 3291-NPCC-PMT-AO-T-01143 |  | 2016-05-08 | 38-22701-N-T-05535
413 | LOADING ARRANGEMENT & SEAFASTENING OF WHT-6 PILES | 3291-NN-0249 | AD219-491-PL-00849 |  |  | - | -
414 | TYPICAL LIFTING AND INSTALLATION OF RCC SLEEPER 18" WELL FLUID PIPELINE (WHT-4 TO WHT-5) CX-01 | 3291-NN-0250 | AD219-489/490-PL-00850 | D | 2 | 1 | - |  | 2016-05-31 | 3291-NPCC-PMT-AO-T-01363 |  | 2016-06-20 | 38-22701-N-T-06153 |  | 2016-07-24 | 3291-NPCC-PMT-AO-T-01653 |  | 2016-08-09 | 38-22701-N-T-06842
415 | REMOVAL & REINSTALLATION RISER PROTECTOR-2 AT NSMFT PLATFROM (ROW-2) | 3291-NN-0251 | AD219-486-PL-00851 | 1 | 4 | - | - |  | 2016-06-30 | 3291-NPCC-PMT-AO-T-01532 |  | 2016-08-09 | 38-22701-N-T-06835 |  | 2016-08-11 | 3291-NPCC-PMT-AO-T-01774 |  |  |  |  | 2016-08-17 | 3291-NPCC-PMT-AO-T-01811 | 2016-09-21 | 38-22701-N-T-07287
416 | LIFTING & INSTALLATION RISER PROTECTOR AT WHT-4 PLATFROM (ROW-2) | 3291-NN-0252 | AD219-489-PL-00852 | 0 | 2 | 1 |  |  | 2016-06-30 | 3291-NPCC-PMT-AO-T-01542 |  | 2016-07-13 | 38-22701-N-T-06452 |  | 20/07/2016 | 3291-NPCC-PMT-AO-T-01637 |  | 2016-07-31 | 38-22701-N-T-06705
417 | LIFTING & INSTALLATION RISER PROTECTOR AT WHT-5 PLATFROM | 3291-NN-0253 | AD219-486-PL-00853 | B | 2 | 1 |  |  | 2016-07-04 | 3291-NPCC-PMT-AO-T-01551 |  | 2016-08-24 | 38-22701-N-T-06998
418 | LIFTING & INSTALLATION RISER PROTECTOR AT WHT-6 PLATFROM | 3291-NN-0254 | AD219-491-PL-00854 | B | 2 | 1899-12-31 |  |  | 20/07/2016 | 3291-NPCC-PMT-AO-T-01636 |  | 2016-07-31 | 38-22701-N-T-06705
419 | LIFTING & INSTALLATION RISER PROTECTOR AT IGD-HAP | 3291-NN-0255 | AD219-469-PL-00855 | 1 | 2 | 1 |  |  | 2016-09-22 | 3291-NPCC-PMT-AO-T-01977 |  | 2016-10-20 | 38-22701-N-T-07554 | [7 empty] | 2016-10-16 | 3291-NPCC-PMT-AO-T-02075 | 2016-11-06 | 38-22701-N-T-07648
420 | 16" MOL PIPELINE FROM NSMFT TO DAS ISLAND SHORE PULL HEAD DETAILS | 3291-NN-0256 | AD219-486-PL-00856 | C | 2 | 1 |  |  | 2016-08-14 | 3291-NPCC-PMT-AO-T-01781 |  | 2016-08-24 | 38-22701-N-T-06999 |  | 2016-08-25 | 3291-NPCC-PMT-AO-T-01849 |  | 2016-09-21 | 38-22701-N-T-07285
421 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL P/L STACK ON DRAWING OF PIPE JOINT @ WHT-6 | 3291-NN-0257 | AD219-491-PL-00857 | B | 2 | 1 |  |  | 2016-08-11 | 3291-NPCC-PMT-AO-T-01779 |  | 2016-09-21 | 38-22701-N-T-07285
422 | 16" J-TUBE LIFTING AND INSTALLATION @ NSMFT | 3291-NN-0258 | AD219-486-PL-00858 | B | 2 |  |  |  | 2016-08-16 | 3291-NPCC-PMT-AO-T-01797 |  | 2016-09-21 | 38-22701-N-T-07287
423 | 26" PIPELINE SHORE PULL HEAD DETAILS - NSMFT TO DAS ISLAND | 3291-NN-0259 | AD219-486-PL-00859 | B | 2 | 1 |  |  | 2016-08-21 | 3291-NPCC-PMT-AO-T-01828 |  | 2016-09-21 | 38-22701-N-T-07285
424 | LAY DOWN HEAD DETAILS FOR 26" PIPELINE FROM IGD-HAP TO NSMFT | 3291-NN-0260 | AD219-469/486-PL-00860 | B | 2 | 1 |  |  | 2016-08-21 | 3291-NPCC-PMT-AO-T-01828 |  | 2016-09-21 | 38-22701-N-T-07285
425 | LIFTING & INSTALLATION RISER PROTECTOR AT WHT-9 PLATFORM | 3291-NN-0261 | AD219-494-PL-00861 | B | 2 | 1 | - |  | 2016-09-28 | 3291-NPCC-PMT-AO-T-01996 |  | 2016-10-20 | 38-22701-N-T-07554
426 | RISER/SPOOL LIFTING AND INSTALLATION FOR 6" GL PIPELINE STACK ON DRAWING OF PIPE JOINT @WHT-9 | 3291-NN-0262 | AD219-494-PL-00862
427 | TYPICAL CONCRETE SLEEPER SHIFTING (PX-18) 10" EXCESS GAS P/L (NSMFT TO USSC IGD-HAP) | 3291-NN-0263 | AD219-486/469-PL-00863
428 | REMOVAL & REINSTALLATION RISER PROTECTOR-1 AT NSMFT PLATFORM (ROW-1) | 3291-NN-0264 | AD219-486-PL-00864 | 0 | 1 | 1 |  |  | 2017-02-28 | 3291-NPCC-PMT-AO-T-02489 |  | 2017-04-02 | 38-22701-N-T-08905 |  | 27/03/2017 29/03/2017 | 3291-NPCC-PMT-AO-T-02616 3291-NPCC-PMT-AO-T-02636 |  |  |  |  | 2017-04-05 | 3291-NPCC-PMT-AO-T-02676 | 2017-04-09 | 38-22701-N-T-08989
429 | REMOVAL & OFFLOADING RISER PROTECTOR-1 & 2 AT WHT-2 (ROW-1 & 2) | 3291-NN-0265 | AD219-485-PL-00865 | 0 | 1 | 1 |  |  | 2017-03-27 | 3291-NPCC-PMT-AO-T-02617 |  | 2017-05-08 | 38-22701-N-T-09233 |  | 2017-04-05 | 3291-NPCC-PMT-AO-T-02663 |  |  |  |  | 2017-05-04 | 3291-NPCC-PMT-AO-T-02789 | 2017-05-08 | 38-22701-N-T-09233
430 | LIFTING & INSTALLATION RISER PROTECTOR AT WHT-7 PLATFORM | 3291-NN-0266 | AD219-492-PL-00866 | B | 2 | 1 |  |  | 2017-03-27 | 3291-NPCC-PMT-AO-T-02623 |  | 2017-05-08 | 38-22701-N-T-09233
431 | LOADING ARRANGEMENT & SEAFASTENING OF RISERS AND SPOOLS @ AL-JABER-35 (TRIP-3) | 3291-NN-0267 | AD219-705-PL-00867 | B | 2 | 1 | Accepted |  | 2017-11-19 | 3291-NPCC-PMT-AO-T-03472 |  | 2018-08-05 | 38-22701-N-T-11402
432 | LIFTING & INSTALLATION RISER PROTECTORS AT WHT-3 PLATFORM | 3291-NN-0268 | AD219-488-PL-00868 | B | 2 | 1 | Accepted |  | 2017-11-20 | 3291-NPCC-PMT-AO-T-03476 |  | 2018-08-05 | 38-22701-N-T-11403
433 | 16" RISER/SPOOL REMOVAL AT NSMFT 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0269 | AD219-486-PL-00869
Formulas:
PLANNED = 4+[PLANNED, row above]