## Documents - Pipeline & Cable
|  | ABU DHABI MARINE OPERATING COMPANY (ADMA-OPCO) | [15 empty] | NPCC DOC. No.:
|  | UMM LULU PACKAGE-1 FFD PROJECT | [15 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 3291 | [15 empty] | REVISION :
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [15 empty] | DATE :
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | Latest REV. | CLASS | ISSUED FOR CLIENT'S REVIEW/COMMENTS (IFR) 60 % |  |  | CLIENT'S RESPONSE DATE ON (IFR) |  |  | INCORPORATION OF COMMENTS AND ISSUED FOR CLIENT APPROVAL (IFA) 80% |  |  | CLIENT'S RESPONSE DATE ON (IFA) |  |  | ISSUED FOR CONSTRUCTION (IFC) 100 % |  |  | CLIENT'S RESPONSE DATE ON (IFC) |  | REMARKS
[6 empty] | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | DATE | REF
1 | PIPE STACKING ANALYSIS REPORT | 3291-NN-RP-001 | AD219-705-G-00401
2 | PIPELAY INSTALLATION REPORT FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-RP-002 | AD219-486/492-G-00402
3 | PIPELAY INSTALLATION REPORT FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-RP-003 | AD219-486/492-G-00403
4 | PIPELAY INSTALLATION REPORT FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-RP-004 | AD219-494/493-G-00404
5 | PIPELAY INSTALLATION REPORT FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-RP-005 | AD219-494/493-G-00405
6 | PIPELAY INSTALLATION REPORT FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-RP-006 | AD219-493/494-G-00406
7 | PIPELAY INSTALLATION REPORT FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-RP-007 | AD219-485/488-G-00407
8 | PIPELAY INSTALLATION REPORT FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-RP-008 | AD219-485/488-G-00408
9 | PIPELAY INSTALLATION REPORT FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-RP-009 | AD219-485/488-G-00409
10 | PIPELAY INSTALLATION REPORT FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-RP-010 | AD219-486/485-G-00410
11 | PIPELAY INSTALLATION REPORT FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-RP-011 | AD219-486/494-G-00411
12 | PIPELAY INSTALLATION REPORT FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-RP-012 | AD219-486/494-G-00412
13 | PIPELAY INSTALLATION REPORT FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-RP-013 | AD219-494/486-G-00413
14 | PIPELAY INSTALLATION REPORT FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-RP-014 | AD219-486/491-G-00414
15 | PIPELAY INSTALLATION REPORT FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-RP-015 | AD219-486/491-G-00415
16 | PIPELAY INSTALLATION REPORT FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-RP-016 | AD219-486/491-G-00416
17 | PIPELAY INSTALLATION REPORT FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-RP-017 | AD219-486/490-G-00417
18 | PIPELAY INSTALLATION REPORT FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-RP-018 | AD219-486/490-G-00418
19 | PIPELAY INSTALLATION REPORT FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-RP-019 | AD219-490/486-G-00419
20 | PIPELAY INSTALLATION REPORT FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-RP-020 | AD219-489/490-G-00420
21 | PIPELAY INSTALLATION REPORT FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-021 | AD219-490/489-G-00421
22 | PIPELAY INSTALLATION REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-022 | AD219-490/489-G-00422
23 | PIPELAY INSTALLATION REPORT FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-RP-023 | AD219-486-G-00423
24 | PIPELAY INSTALLATION REPORT FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-RP-024 | AD219-469/486-G-00424
25 | DAVIT LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-RP-025 | AD219-486/492-G-00425
26 | DAVIT LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-RP-026 | AD219-486/492-G-00426
27 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-RP-027 | AD219-494/493-G-00427
28 | DAVIT LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-RP-028 | AD219-494/493-G-00428
29 | DAVIT LIFT ANALYSIS REPORT FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-RP-029 | AD219-493/494-G-00429
30 | DAVIT LIFT ANALYSIS REPORT FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-RP-030 | AD219-485/488-G-00430
31 | DAVIT LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-RP-031 | AD219-485/488-G-00431
32 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-RP-032 | AD219-485/488-G-00432
33 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-RP-033 | AD219-486/485-G-00433
34 | DAVIT LIFT ANALYSIS REPORT FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-RP-034 | AD219-486/494-G-00434
35 | DAVIT LIFT ANALYSIS REPORT FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-RP-035 | AD219-486/494-G-00435
36 | DAVIT LIFT ANALYSIS REPORT FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-RP-036 | AD219-494/486-G-00436
37 | DAVIT LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-RP-037 | AD219-486/491-G-00437
38 | DAVIT LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-RP-038 | AD219-486/491-G-00438
39 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-RP-039 | AD219-486/491-G-00439
40 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-RP-040 | AD219-486/490-G-00440
41 | DAVIT LIFT ANALYSIS REPORT FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-RP-041 | AD219-486/490-G-00441
42 | DAVIT LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-RP-042 | AD219-490/486-G-00442
43 | DAVIT LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-RP-043 | AD219-489/490-G-00443
44 | DAVIT LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-044 | AD219-490/489-G-00444
45 | DAVIT LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-RP-045 | AD219-490/489-G-00445
46 | DAVIT LIFT ANALYSIS REPORT FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-RP-046 | AD219-486-G-00446
47 | DAVIT LIFT ANALYSIS REPORT FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-RP-047 | AD219-469/486-G-00447
48 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-RP-048 | AD219-486/492-G-00448
49 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-RP-049 | AD219-486/492-G-00449
50 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-RP-050 | AD219-486/492-G-00450
51 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-RP-051 | AD219-486/492-G-00451
52 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-RP-052 | AD219-494/493-G-00452
53 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-RP-053 | AD219-494/493-G-00453
54 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-RP-054 | AD219-494/493-G-00454
55 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-RP-055 | AD219-494/493-G-00455
56 | RISER LIFT ANALYSIS REPORT FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-8) | 3291-NN-RP-056 | AD219-493/494-G-00456
57 | RISER LIFT ANALYSIS REPORT FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-9) | 3291-NN-RP-057 | AD219-493/494-G-00457
58 | RISER LIFT ANALYSIS REPORT FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-RP-058 | AD219-485/488-G-00458
59 | RISER LIFT ANALYSIS REPORT FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-RP-059 | AD219-485/488-G-00459
60 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-RP-060 | AD219-485/488-G-00460
61 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-RP-061 | AD219-485/488-G-00461
62 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-RP-062 | AD219-485/488-G-00462
63 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-RP-063 | AD219-485/488-G-00463
64 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-2 (@NSMFT) | 3291-NN-RP-064 | AD219-486/485-G-00464
65 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-2 (@WHT-2) | 3291-NN-RP-065 | AD219-486/485-G-00465
66 | RISER LIFT ANALYSIS REPORT FOR GL 6" P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-RP-066 | AD219-486/494-G-00466
67 | RISER LIFT ANALYSIS REPORT FOR GL 6" P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-RP-067 | AD219-486/494-G-00467
68 | RISER LIFT ANALYSIS REPORT FOR 8" WI P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-RP-068 | AD219-486/494-G-00468
69 | RISER LIFT ANALYSIS REPORT FOR 8" WI P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-RP-069 | AD219-486/494-G-00469
70 | RISER LIFT ANALYSIS REPORT FOR WF 14" P/L FROM WHT-9 TO NSMFT (@WHT-9) | 3291-NN-RP-070 | AD219-494/486-G-00470
71 | RISER LIFT ANALYSIS REPORT FOR WF 14" P/L FROM WHT-9 TO NSMFT (@NSMFT) | 3291-NN-RP-071 | AD219-494/486-G-00471
72 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-RP-072 | AD219-486/491-G-00472
73 | RISER LIFT ANALYSIS REPORT FOR 10" WF P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-RP-073 | AD219-486/491-G-00473
74 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-RP-074 | AD219-486/491-G-00474
75 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-RP-075 | AD219-486/491-G-00475
76 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-RP-076 | AD219-486/491-G-00476
77 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-RP-077 | AD219-486/491-G-00477
78 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-RP-078 | AD219-486/490-G-00478
79 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-RP-079 | AD219-486/490-G-00479
80 | RISER LIFT ANALYSIS REPORT FOR 10" WI P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-RP-080 | AD219-486/490-G-00480
81 | RISER LIFT ANALYSIS REPORT FOR 10" WI P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-RP-081 | AD219-486/490-G-00481
82 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-5 TO NSMFT (@WHT-5) | 3291-NN-RP-082 | AD219-490/486-G-00482
83 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-5 TO NSMFT (@NSMFT) | 3291-NN-RP-083 | AD219-490/486-G-00483
84 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-4) | 3291-NN-RP-084 | AD219-489/490-G-00484
85 | RISER LIFT ANALYSIS REPORT FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-5) | 3291-NN-RP-085 | AD219-489/490-G-00485
86 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-RP-086 | AD219-490/489-G-00486
87 | RISER LIFT ANALYSIS REPORT FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-4) | 3291-NN-RP-087 | AD219-490/489-G-00487
88 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-RP-088 | AD219-490/489-G-00488
89 | RISER LIFT ANALYSIS REPORT FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-4) | 3291-NN-RP-089 | AD219-490/489-G-00489
90 | RISER LIFT ANALYSIS REPORT FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-RP-090 | AD219-486-G-00490
91 | RISER LIFT ANALYSIS REPORT FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@IGD-HAP) | 3291-NN-RP-091 | AD219-469/486-G-00491
92 | RISER LIFT ANALYSIS REPORT FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@NSMFT) | 3291-NN-RP-092 | AD219-469/486-G-00492
93 | SEAFASTENING DESIGN REPORT FOR CC PIPES -1 | 3291-NN-RP-093 | AD219-705-G-00493
94 | SEAFASTENING DESIGN REPORT FOR CC PIPES -2 | 3291-NN-RP-094 | AD219-705-G-00494
95 | SEAFASTENING DESIGN REPORT FOR CC PIPES -3 | 3291-NN-RP-095 | AD219-705-G-00495
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
119
121
122
123

## Documents - Naval Marine
|  | ABU DHABI MARINE OPERATING COMPANY (ADMA-OPCO) | [15 empty] | NPCC DOC. No.:
|  | UMM LULU PACKAGE-1 FFD PROJECT | [15 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 3291 | [15 empty] | REVISION :
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (NAVEL MARINE) | [15 empty] | DATE :
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | Latest REV. | CLASS | ISSUED FOR CLIENT'S REVIEW/COMMENTS (IFR) 60 % |  |  | CLIENT'S RESPONSE DATE ON (IFR) |  |  | INCORPORATION OF COMMENTS AND ISSUED FOR CLIENT APPROVAL (IFA) 80% |  |  | CLIENT'S RESPONSE DATE ON (IFA) |  |  | ISSUED FOR CONSTRUCTION (IFC) 100 % |  |  | CLIENT'S RESPONSE DATE ON (IFC) |  | REMARKS
[6 empty] | PLANNED | DATE | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | Date | REF
1 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.9 KM WATER INJECTION P/L FROM NSMFT TO WHT-7 | 3291-ZZ-RP-001 | AD219-486/492-G-00501
2 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 10" X 4.9 KM WELL FLUID P/L FROM NSMFT TO WHT-7 | 3291-ZZ-RP-002 | AD219-486/492-G-00502
3 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.1 KM GAS LIFT P/L FROM WHT-9 TO WHT-8 | 3291-ZZ-RP-003 | AD219-494/493-G-00503
4 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.1 KM WATER INJECTION P/L FROM WHT-9 TO WHT-8 | 3291-ZZ-RP-004 | AD219-494/493-G-00504
5 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 14" X 4.1 KM WELL FLUID P/L FROM WHT-9 TO WHT-8 | 3291-ZZ-RP-005 | AD219-494/493-G-00505
6 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 12" X 4.6 KM WELL FLUID P/L FROM WHT-2 TO WHT-3 | 3291-ZZ-RP-006 | AD219-485/488-G-00506
7 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.5 KM WATER INJECTION P/L FROM WHT-2 TO WHT-3 | 3291-ZZ-RP-007 | AD219-485/488-G-00507
8 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.6 KM GAS LIFT P/L FROM WHT-2 TO WHT-3 | 3291-ZZ-RP-008 | AD219-485/488-G-00508
9 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 3.7 KM GAS LIFT P/L FROM NSMFT TO WHT-2 | 3291-ZZ-RP-009 | AD219-486/485-G-00509
10 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 5.5 KM GAS LIFT P/L FROM NSMFT TO WHT-9 | 3291-ZZ-RP-010 | AD219-486/494-G-00510
11 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 8" X 5.5 KM WATER INJECTION P/L FROM NSMFT TO WHT-9 | 3291-ZZ-RP-011 | AD219-486/494-G-00511
12 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 14" X 5.5 KM WELL FLUID P/L FROM WHT-9 TO NSMFT | 3291-ZZ-RP-012 | AD219-494/486-G-00512
13 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 10" X 5.2 KM WELL FLUID P/L FROM NSMFT TO WHT-6 | 3291-ZZ-RP-013 | AD219-486/491-G-00513
14 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 5.2 KM WATER INJECTION P/L FROM NSMFT TO WHT-6 | 3291-ZZ-RP-014 | AD219-486/491-G-00514
15 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 5.2 KM GAS LIFT P/L FROM NSMFT TO WHT-6 | 3291-ZZ-RP-015 | AD219-486/491-G-00515
16 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 6.0 KM GAS LIFT P/L FROM NSMFT TO WHT-5 | 3291-ZZ-RP-016 | AD219-486/490-G-00516
17 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 10" X 6.0 KM WATER INJECTION P/L FROM NSMFT TO WHT-5 | 3291-ZZ-RP-017 | AD219-486/490-G-00517
18 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 18" X 6.075 KM WELL FLUID P/L FROM WHT-5 TO NSMFT | 3291-ZZ-RP-018 | AD219-490/486-G-00518
19 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 18" X 4.7 KM WELL FLUID P/L FROM WHT-4 TO WHT-5 | 3291-ZZ-RP-019 | AD219-489/490-G-00519
20 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.7 KM GAS LIFT P/L FROM WHT-5 TO WHT-4 | 3291-ZZ-RP-020 | AD219-490/489-G-00520
21 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 6" X 4.7 KM WATER INJECTION P/L FROM WHT-5 TO WHT-4 | 3291-ZZ-RP-021 | AD219-490/489-G-00521
22 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 16" X 69 KM MAIN OIL LINE (MOL) FROM DAS ISLAND TO NSMFT | 3291-ZZ-RP-022 | AD219-486-G-00522
23 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LAYING OF 10" X 32 KM MAIN OIL LINE (MOL) FROM IGD-HAP TO NSMFT | 3291-ZZ-RP-023 | AD219-469/486-G-00523
24 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-3 JACKET | 3291-ZZ-RP-024 | AD219-488-G-00524
25 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-4 JACKET | 3291-ZZ-RP-025 | AD219-489-G-00525
26 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-5 JACKET | 3291-ZZ-RP-026 | AD219-490-G-00526
27 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-6 JACKET | 3291-ZZ-RP-027 | AD219-491-G-00527
28 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-7 JACKET | 3291-ZZ-RP-028 | AD219-492-G-00528
29 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-8 JACKET | 3291-ZZ-RP-029 | AD219-493-G-00529
30 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF WHT-9 JACKET | 3291-ZZ-RP-030 | AD219-494-G-00530
31 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-3 TOPSIDES | 3291-ZZ-RP-031 | AD219-488-G-00531
32 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-4 TOPSIDES | 3291-ZZ-RP-032 | AD219-489-G-00532
33 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-5 TOPSIDES | 3291-ZZ-RP-033 | AD219-490-G-00533
34 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-6 TOPSIDES | 3291-ZZ-RP-034 | AD219-491-G-00534
35 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-7 TOPSIDES | 3291-ZZ-RP-035 | AD219-492-G-00535
36 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-8 TOPSIDES | 3291-ZZ-RP-036 | AD219-493-G-00536
37 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING LIFTING & INSTALLATION OF WHT-9 TOPSIDES | 3291-ZZ-RP-037 | AD219-494-G-00537
38 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-8 (WEST FACE) | 3291-ZZ-RP-038 | AD219-493-G-00538
39 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 8", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-9 (WEST FACE) | 3291-ZZ-RP-039 | AD219-494-G-00539
40 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 18" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-4 (EAST FACE) | 3291-ZZ-RP-040 | AD219-489-G-00540
41 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 10", 18", 16" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-5 (EAST FACE) | 3291-ZZ-RP-041 | AD219-490-G-00541
42 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 12" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-3 (WEST FACE) | 3291-ZZ-RP-042 | AD219-488-G-00542
43 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 12" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-2 (WEST FACE) | 3291-ZZ-RP-043 | AD219-485-G-00543
44 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT- 2 (EAST FACE) | 3291-ZZ-RP-044 | AD219-485-G-00544
45 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (WEST FACE) | 3291-ZZ-RP-045 | AD219-486-G-00545
46 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 8", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (WEST FACE) | 3291-ZZ-RP-046 | AD219-486-G-00546
47 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 10", 18" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (SOUTH FACE) | 3291-ZZ-RP-047 | AD219-486-G-00547
48 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (SOUTH FACE) | 3291-ZZ-RP-048 | AD219-486-G-00548
49 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT NSMFT (SOUTH FACE) | 3291-ZZ-RP-049 | AD219-486-G-00549
50 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 18" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-5 (WEST FACE) | 3291-ZZ-RP-050 | AD219-490-G-00550
51 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-6 (WEST FACE) | 3291-ZZ-RP-051 | AD219-491-G-00551
52 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 6", 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-7 (WEST FACE) | 3291-ZZ-RP-052 | AD219-492-G-00552
53 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 x 6", 14" RISER, TIE-IN SPOOLS AND RISER FENDER AT WHT-9 (EAST FACE) | 3291-ZZ-RP-053 | AD219-494-G-00553
54 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 2 RISERS, TIE-IN SPOOLS AND RISER FENDER AT NSMFT | 3291-ZZ-RP-054 | AD219-486-G-00554
55 | MOORING ANALYSIS FOR CONSTRUCTION BARGE DURING INSTALLATION OF 10" RISER, TIE-IN SPOOLS AND RISER FENDER AT IGD-HAP (SOUTH FACE) | 3291-ZZ-RP-055 | AD219-469-G-00555
56 | MOORING ANALYSIS DURING LIFTING & INSTALLATION OF WHT-5 TOPSIDES | 3291-ZZ-RP-056 | AD219-490-G-00556
57 | STABILITY ANALYSIS REPORT FOR CB#1 | 3291-ZZ-RP-057 | AD219-705-G-00557
58 | STABILITY ANALYSIS REPORT FOR CB#2 | 3291-ZZ-RP-058 | AD219-705-G-00558
59 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-1 (Campaign-1) | 3291-ZZ-RP-059 | AD219-705-G-00559
60 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-2 (Campaign-1) | 3291-ZZ-RP-060 | AD219-705-G-00560
61 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-3 (Campaign-1) | 3291-ZZ-RP-061 | AD219-705-G-00561
62 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-4 (Campaign-1) | 3291-ZZ-RP-062 | AD219-705-G-00562
63 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-5 (Campaign-1) | 3291-ZZ-RP-063 | AD219-705-G-00563
64 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-6 (Campaign-1) | 3291-ZZ-RP-064 | AD219-705-G-00564
65 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-7 (Campaign-1) | 3291-ZZ-RP-065 | AD219-705-G-00565
66 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-8 (Campaign-1) | 3291-ZZ-RP-066 | AD219-705-G-00566
67 | BALLAST PLAN DURING TRANSPORTATION OF CC PIPES TRIP-9 (Campaign-1) | 3291-ZZ-RP-067 | AD219-705-G-00567
59 | STABILITY ANALYSIS REPORT FOR CB#3 | 3291-ZZ-RP-068 | AD219-705-G-00568

## Drawings
|  | ABU DHABI MARINE OPERATING COMPANY (ADMA-OPCO) | [15 empty] | NPCC DOC. No.:
|  | UMM LULU PACKAGE-1 FFD PROJECT | [15 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 3291 | [15 empty] | REVISION :
|  | OFFSHORE CONSTRUCTION ENGINEERING DRAWINGS | [15 empty] | DATE :
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADMA-OPCO DOCUMENT NUMBER | Latest REV. | CLASS | ISSUED FOR CLIENT'S REVIEW/COMMENTS (IFR) 60 % |  |  | CLIENT'S RESPONSE DATE ON (IFR) |  |  | INCORPORATION OF COMMENTS AND ISSUED FOR CLIENT APPROVAL (IFA) 80% |  |  | CLIENT'S RESPONSE DATE ON (IFA) |  |  | ISSUED FOR CONSTRUCTION (IFC) 100 % |  |  | CLIENT'S RESPONSE DATE ON (IFC) |  | REMARKS
[6 empty] | PLANNED | DATE | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | PLANNED | ACTUAL | REF | DATE | REF
1 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0001 | AD219-486/492-G-00601
2 | START UP HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0002 | AD219-486/492-G-00602
3 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0003 | AD219-486/492-G-00603
4 | BUCKLE DETECTOR DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0004 | AD219-486/492-G-00604
5 | START UP HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0005 | AD219-486/492-G-00605
6 | LAYDOWN HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0006 | AD219-486/492-G-00606
7 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0007 | AD219-494/493-G-00607
8 | START UP HEAD DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0008 | AD219-494/493-G-00608
9 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0009 | AD219-494/493-G-00609
10 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0010 | AD219-494/493-G-00610
11 | START UP HEAD DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0011 | AD219-494/493-G-00611
12 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0012 | AD219-494/493-G-00612
13 | BUCKLE DETECTOR DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0013 | AD219-493/494-G-00613
14 | START UP HEAD DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0014 | AD219-493/494-G-00614
15 | LAYDOWN HEAD DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0015 | AD219-493/494-G-00615
16 | BUCKLE DETECTOR DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0016 | AD219-485/488-G-00616
17 | START UP HEAD DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0017 | AD219-485/488-G-00617
18 | LAYDOWN HEAD DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0018 | AD219-485/488-G-00618
19 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0019 | AD219-485/488-G-00619
20 | START UP HEAD DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0020 | AD219-485/488-G-00620
21 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0021 | AD219-485/488-G-00621
22 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0022 | AD219-485/488-G-00622
23 | START UP HEAD DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0023 | AD219-485/488-G-00623
24 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0024 | AD219-485/488-G-00624
25 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0025 | AD219-486/485-G-00625
26 | START UP HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0026 | AD219-486/485-G-00626
27 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0027 | AD219-486/485-G-00627
28 | BUCKLE DETECTOR DETAILS FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0028 | AD219-486/494-G-00628
29 | START UP HEAD DETAILS FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0029 | AD219-486/494-G-00629
30 | LAYDOWN HEAD DETAILS FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0030 | AD219-486/494-G-00630
31 | BUCKLE DETECTOR DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0031 | AD219-486/494-G-00631
32 | START UP HEAD DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0032 | AD219-486/494-G-00632
33 | LAYDOWN HEAD DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0033 | AD219-486/494-G-00633
34 | BUCKLE DETECTOR DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0034 | AD219-494/486-G-00634
35 | START UP HEAD DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0035 | AD219-494/486-G-00635
36 | LAYDOWN HEAD DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0036 | AD219-494/486-G-00636
37 | BUCKLE DETECTOR DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0037 | AD219-486/491-G-00637
38 | START UP HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0038 | AD219-486/491-G-00638
39 | LAYDOWN HEAD DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0039 | AD219-486/491-G-00639
40 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0040 | AD219-486/491-G-00640
41 | START UP HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0041 | AD219-486/491-G-00641
42 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0042 | AD219-486/491-G-00642
43 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0043 | AD219-486/491-G-00643
44 | START UP HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0044 | AD219-486/491-G-00644
45 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0045 | AD219-486/491-G-00645
46 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0046 | AD219-486/490-G-00646
47 | START UP HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0047 | AD219-486/490-G-00647
48 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0048 | AD219-486/490-G-00648
49 | BUCKLE DETECTOR DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0049 | AD219-486/490-G-00649
50 | START UP HEAD DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0050 | AD219-486/490-G-00650
51 | LAYDOWN HEAD DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0051 | AD219-486/490-G-00651
52 | BUCKLE DETECTOR DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0052 | AD219-490/486-G-00652
53 | START UP HEAD DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0053 | AD219-490/486-G-00653
54 | LAYDOWN HEAD DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0054 | AD219-490/486-G-00654
55 | BUCKLE DETECTOR DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0055 | AD219-489/490-G-00655
56 | START UP HEAD DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0056 | AD219-489/490-G-00656
57 | LAYDOWN HEAD DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0057 | AD219-489/490-G-00657
58 | BUCKLE DETECTOR DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0058 | AD219-490/489-G-00658
59 | START UP HEAD DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0059 | AD219-490/489-G-00659
60 | LAYDOWN HEAD DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0060 | AD219-490/489-G-00660
61 | BUCKLE DETECTOR DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0061 | AD219-490/489-G-00661
62 | START UP HEAD DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0062 | AD219-490/489-G-00662
63 | LAYDOWN HEAD DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0063 | AD219-490/489-G-00663
64 | BUCKLE DETECTOR DETAILS FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0064 | AD219-486-G-00664
65 | START UP HEAD DETAILS FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0065 | AD219-486-G-00665
66 | LAYDOWN HEAD DETAILS FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0066 | AD219-486-G-00666
67 | BUCKLE DETECTOR DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0067 | AD219-469/486-G-00667
68 | START UP HEAD DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0068 | AD219-469/486-G-00668
69 | LAYDOWN HEAD DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0069 | AD219-469/486-G-00669
70 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-1) WITH BALAST PLAN | 3291-NN-0070 | AD219-705-G-00670
71 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-2) WITH BALAST PLAN | 3291-NN-0071 | AD219-705-G-00671
72 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-3) WITH BALAST PLAN | 3291-NN-0072 | AD219-705-G-00672
73 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-4) WITH BALAST PLAN | 3291-NN-0073 | AD219-705-G-00673
74 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-5) WITH BALAST PLAN | 3291-NN-0074 | AD219-705-G-00674
75 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-6) WITH BALAST PLAN | 3291-NN-0075 | AD219-705-G-00675
76 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-7) WITH BALAST PLAN | 3291-NN-0076 | AD219-705-G-00676
77 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-8) WITH BALAST PLAN | 3291-NN-0077 | AD219-705-G-00677
78 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-9) WITH BALAST PLAN | 3291-NN-0078 | AD219-705-G-00678
79 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-10) WITH BALAST PLAN | 3291-NN-0079 | AD219-705-G-00679
80 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-11) WITH BALAST PLAN | 3291-NN-0080 | AD219-705-G-00680
81 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-12) WITH BALAST PLAN | 3291-NN-0081 | AD219-705-G-00681
82 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-13) WITH BALAST PLAN | 3291-NN-0082 | AD219-705-G-00682
83 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-14) WITH BALAST PLAN | 3291-NN-0083 | AD219-705-G-00683
84 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-15) WITH BALAST PLAN | 3291-NN-0084 | AD219-705-G-00684
85 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-16) WITH BALAST PLAN | 3291-NN-0085 | AD219-705-G-00685
86 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-17) WITH BALAST PLAN | 3291-NN-0086 | AD219-705-G-00686
87 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-18) WITH BALAST PLAN | 3291-NN-0087 | AD219-705-G-00687
88 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-19) WITH BALAST PLAN | 3291-NN-0088 | AD219-705-G-00688
89 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-20) WITH BALAST PLAN | 3291-NN-0089 | AD219-705-G-00689
90 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-21) WITH BALAST PLAN | 3291-NN-0090 | AD219-705-G-00690
91 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-22) WITH BALAST PLAN | 3291-NN-0091 | AD219-705-G-00691
92 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-23) WITH BALAST PLAN | 3291-NN-0092 | AD219-705-G-00692
93 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-24) WITH BALAST PLAN | 3291-NN-0093 | AD219-705-G-00693
94 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-25) WITH BALAST PLAN | 3291-NN-0094 | AD219-705-G-00694
95 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-26) WITH BALAST PLAN | 3291-NN-0095 | AD219-705-G-00695
96 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-27) WITH BALAST PLAN | 3291-NN-0096 | AD219-705-G-00696
97 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-28) WITH BALAST PLAN | 3291-NN-0097 | AD219-705-G-00697
98 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-29) WITH BALAST PLAN | 3291-NN-0098 | AD219-705-G-00698
99 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES (TRIP-30) WITH BALAST PLAN | 3291-NN-0099 | AD219-705-G-00699
100 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-1) WITH BALAST PLAN | 3291-NN-0100 | AD219-705-G-00700
101 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-2) WITH BALAST PLAN | 3291-NN-0101 | AD219-705-G-00701
102 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-3) WITH BALAST PLAN | 3291-NN-0102 | AD219-705-G-00702
103 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-4) WITH BALAST PLAN | 3291-NN-0103 | AD219-705-G-00703
104 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-5) WITH BALAST PLAN | 3291-NN-0104 | AD219-705-G-00704
105 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-6) WITH BALAST PLAN | 3291-NN-0105 | AD219-705-G-00705
106 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-7) WITH BALAST PLAN | 3291-NN-0106 | AD219-705-G-00706
107 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-8) WITH BALAST PLAN | 3291-NN-0107 | AD219-705-G-00707
108 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-9) WITH BALAST PLAN | 3291-NN-0108 | AD219-705-G-00708
109 | LOADING ARRANGEMENT AND SEAFASTENING OF RISERS AND SPOOLS (TRIP-10) WITH BALAST PLAN | 3291-NN-0109 | AD219-705-G-00709
110 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-0110 | AD219-486/492-G-00710
111 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-0111 | AD219-486/492-G-00711
112 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 (@NSMFT) | 3291-NN-0112 | AD219-486/492-G-00712
113 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-7 (@WHT-7) | 3291-NN-0113 | AD219-486/492-G-00713
114 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-0114 | AD219-494/493-G-00714
115 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-0115 | AD219-494/493-G-00715
116 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-9) | 3291-NN-0116 | AD219-494/493-G-00716
117 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-9 TO WHT-8 (@WHT-8) | 3291-NN-0117 | AD219-494/493-G-00717
118 | TEMPORARY KNEE BRACE DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-8) | 3291-NN-0118 | AD219-493/494-G-00718
119 | TEMPORARY KNEE BRACE DETAILS FOR 14" WF P/L FROM WHT-8 TO WHT-9 (@WHT-9) | 3291-NN-0119 | AD219-493/494-G-00719
120 | TEMPORARY KNEE BRACE DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-0120 | AD219-485/488-G-00720
121 | TEMPORARY KNEE BRACE DETAILS FOR 12" WF P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0121 | AD219-485/488-G-00721
122 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-2) | 3291-NN-0122 | AD219-485/488-G-00722
123 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-2 TO WHT-3 (@WHT-3) | 3291-NN-0123 | AD219-485/488-G-00723
124 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-2 ) | 3291-NN-0124 | AD219-485/488-G-00724
125 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-2 TO WHT-3 (@WHT-3 ) | 3291-NN-0125 | AD219-485/488-G-00725
126 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 (@NSMFT) | 3291-NN-0126 | AD219-486/485-G-00726
127 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-2 (@WHT-2) | 3291-NN-0127 | AD219-486/485-G-00727
128 | TEMPORARY KNEE BRACE DETAILS FOR GL 6" P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-0128 | AD219-486/494-G-00728
129 | TEMPORARY KNEE BRACE DETAILS FOR GL 6" P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-0129 | AD219-486/494-G-00729
130 | TEMPORARY KNEE BRACE DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 (@NSMFT) | 3291-NN-0130 | AD219-486/494-G-00730
131 | TEMPORARY KNEE BRACE DETAILS FOR 8" WI P/L FROM NSMFT TO WHT-9 (@WHT-9) | 3291-NN-0131 | AD219-486/494-G-00731
132 | TEMPORARY KNEE BRACE DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT (@WHT-9) | 3291-NN-0132 | AD219-494/486-G-00732
133 | TEMPORARY KNEE BRACE DETAILS FOR WF 14" P/L FROM WHT-9 TO NSMFT (@NSMFT) | 3291-NN-0133 | AD219-494/486-G-00733
134 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0134 | AD219-486/491-G-00734
135 | TEMPORARY KNEE BRACE DETAILS FOR 10" WF P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0135 | AD219-486/491-G-00735
136 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0136 | AD219-486/491-G-00736
137 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0137 | AD219-486/491-G-00737
138 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 (@NSMFT) | 3291-NN-0138 | AD219-486/491-G-00738
139 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-6 (@WHT-6) | 3291-NN-0139 | AD219-486/491-G-00739
140 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-0140 | AD219-486/490-G-00740
141 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-0141 | AD219-486/490-G-00741
142 | TEMPORARY KNEE BRACE DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 (@NSMFT) | 3291-NN-0142 | AD219-486/490-G-00742
143 | TEMPORARY KNEE BRACE DETAILS FOR 10" WI P/L FROM NSMFT TO WHT-5 (@WHT-5) | 3291-NN-0143 | AD219-486/490-G-00743
144 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT (@WHT-5) | 3291-NN-0144 | AD219-490/486-G-00744
145 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-5 TO NSMFT (@NSMFT) | 3291-NN-0145 | AD219-490/486-G-00745
146 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-4) | 3291-NN-0146 | AD219-489/490-G-00746
147 | TEMPORARY KNEE BRACE DETAILS FOR 18" WF P/L FROM WHT-4 TO WHT-5 (@WHT-5) | 3291-NN-0147 | AD219-489/490-G-00747
148 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-5) | 3291-NN-0148 | AD219-490/489-G-00748
149 | TEMPORARY KNEE BRACE DETAILS FOR 6" GL P/L FROM WHT-5 TO WHT-4 (@WHT-4) | 3291-NN-0149 | AD219-490/489-G-00749
150 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-5 ) | 3291-NN-0150 | AD219-490/489-G-00750
151 | TEMPORARY KNEE BRACE DETAILS FOR 6" WI P/L FROM WHT-5 TO WHT-4 (@WHT-4 ) | 3291-NN-0151 | AD219-490/489-G-00751
152 | TEMPORARY KNEE BRACE DETAILS FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0152 | AD219-486-G-00752
153 | TEMPORARY KNEE BRACE DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@ IGD-HAP) | 3291-NN-0153 | AD219-469/486-G-00753
154 | TEMPORARY KNEE BRACE DETAILS FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT (@NSM) | 3291-NN-0154 | AD219-469/486-G-00754
155 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0155 | AD219-486/492-G-00755
156 | HYDROTEST DIAGRAM FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0156 | AD219-486/492-G-00756
157 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0157 | AD219-494/493-G-00757
158 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0158 | AD219-494/493-G-00758
159 | HYDROTEST DIAGRAM FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0159 | AD219-493/494-G-00759
160 | HYDROTEST DIAGRAM FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0160 | AD219-485/488-G-00760
161 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0161 | AD219-485/488-G-00761
162 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0162 | AD219-485/488-G-00762
163 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0163 | AD219-486/485-G-00763
164 | HYDROTEST DIAGRAM FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0164 | AD219-486/494-G-00764
165 | HYDROTEST DIAGRAM FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0165 | AD219-486/494-G-00765
166 | HYDROTEST DIAGRAM FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0166 | AD219-494/486-G-00766
167 | HYDROTEST DIAGRAM FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0167 | AD219-486/491-G-00767
168 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0168 | AD219-486/491-G-00768
169 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0169 | AD219-486/491-G-00769
170 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0170 | AD219-486/490-G-00770
171 | HYDROTEST DIAGRAM FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0171 | AD219-486/490-G-00771
172 | HYDROTEST DIAGRAM FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0172 | AD219-490/486-G-00772
173 | HYDROTEST DIAGRAM FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0173 | AD219-489/490-G-00773
174 | HYDROTEST DIAGRAM FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0174 | AD219-490/489-G-00774
175 | HYDROTEST DIAGRAM FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0175 | AD219-490/489-G-00775
176 | HYDROTEST DIAGRAM FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0176 | AD219-486-G-00776
177 | HYDROTEST DIAGRAM FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0177 | AD219-469/486-G-00777
178 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM NSMFT TO WHT-7 | 3291-NN-0178 | AD219-486/492-G-00778
179 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 10" WF P/L FROM NSMFT TO WHT-7 | 3291-NN-0179 | AD219-486/492-G-00779
180 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM WHT-9 TO WHT-8 | 3291-NN-0180 | AD219-494/493-G-00780
181 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM WHT-9 TO WHT-8 | 3291-NN-0181 | AD219-494/493-G-00781
182 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 14" WF P/L FROM WHT-8 TO WHT-9 | 3291-NN-0182 | AD219-493/494-G-00782
183 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 12" WF P/L FROM WHT-2 TO WHT-3 | 3291-NN-0183 | AD219-485/488-G-00783
184 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM WHT-2 TO WHT-3 | 3291-NN-0184 | AD219-485/488-G-00784
185 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM WHT-2 TO WHT-3 | 3291-NN-0185 | AD219-485/488-G-00785
186 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM NSMFT TO WHT-2 | 3291-NN-0186 | AD219-486/485-G-00786
187 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR GL 6" P/L FROM NSMFT TO WHT-9 | 3291-NN-0187 | AD219-486/494-G-00787
188 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 8" WI P/L FROM NSMFT TO WHT-9 | 3291-NN-0188 | AD219-486/494-G-00788
189 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR WF 14" P/L FROM WHT-9 TO NSMFT | 3291-NN-0189 | AD219-494/486-G-00789
190 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 10" WF P/L FROM NSMFT TO WHT-6 | 3291-NN-0190 | AD219-486/491-G-00790
191 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM NSMFT TO WHT-6 | 3291-NN-0191 | AD219-486/491-G-00791
192 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM NSMFT TO WHT-6 | 3291-NN-0192 | AD219-486/491-G-00792
193 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM NSMFT TO WHT-5 | 3291-NN-0193 | AD219-486/490-G-00793
194 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 10" WI P/L FROM NSMFT TO WHT-5 | 3291-NN-0194 | AD219-486/490-G-00794
195 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 18" WF P/L FROM WHT-5 TO NSMFT | 3291-NN-0195 | AD219-490/486-G-00795
196 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 18" WF P/L FROM WHT-4 TO WHT-5 | 3291-NN-0196 | AD219-489/490-G-00796
197 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" GL P/L FROM WHT-5 TO WHT-4 | 3291-NN-0197 | AD219-490/489-G-00797
198 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 6" WI P/L FROM WHT-5 TO WHT-4 | 3291-NN-0198 | AD219-490/489-G-00798
199 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 16" MAIN OIL P/L FROM DAS ISLAND TO NSMFT | 3291-NN-0199 | AD219-486-G-00799
200 | DETAIL OF TEMPORARY PIG LAUNCHER & RECEIVER FOR 10" EXCESS EXPORT GAS P/L FROM IGD-HAP TO NSMFT | 3291-NN-0200 | AD219-469/486-G-00800
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315