## Documents - Pipeline & Cable
|  | ABU DHABI GAS INDUSTRIES LTD (GASCO) | [11 empty] | NPCC DOC. No.: 4232-PP-GE-001
IGD-E (PHASE-1) – 42” OFFSHORE PIPELINE PROJECT
|  | GASCO AGREEMENT NO. 13527904 FOR EPC WORKS / GASCO PROJECT NO. 5279 | [11 empty] | REVISION : |  |  |  | 0
|  | NPCC PROJECT NO. 4232 | [11 empty] | DATE : |  |  |  | 2016-11-15
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | CLIENT DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN |  |  | NPCC |  | CLIENT |  |  | MWS (LOC) |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPE STACKING ANALYSIS REPORT FOR 42" PIPELINE | 4232-NN-RP-101 | GD-100-A4-Z-5-71140 | 0 | 2 | 2016-12-05 | 2016-12-05 | CSE-OF-4232-002 | 2016-12-06 | T-NPCC-GASCO-P5279-4232-1264 | 2016-12-22 | T-X(C)-5276-1187 | 2 | [5 empty] | CLIENT COMMENTED
|  |  |  | 0A | 2 |  | 2017-01-03 | CSE-OF-4232-004 | 2017-01-09 | T-NPCC-GASCO-P5279-4232-1410 | 2017-01-31 | T-X(C)-5279-1324 | 2 | [5 empty] | CLIENT COMMENTED
|  |  |  | 0B | 1 |  | 2017-02-06 | CSE-OF-4232-018 | 2017-02-12 | T-NPCC-GASCO-P5279-4232-1562 | 2017-03-01 | T-X(C)-5279-1462 | 3 | 2017-02-20 | T-NPCC-LOC-P5279-4232-0036 | 2017-02-27 | 1393_152615_DRS0046 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-22 | CSE-OF-4232-113 | 2018-03-01 | T-NPCC-GASCO-P5279-4232-3066 | 2018-03-14 | T-X(C)-5279-2559 | 3 | [5 empty] | CLOSED
2 | PIPELAY INSTALLATION REPORT FOR 42" PIPELINE | 4232-NN-RP-102 | GD-100-A4-Z-5-71141 | 0 | 2 | 2017-01-05 | 2017-01-09 | CSE-OF-4232-006 | 2017-01-10 | T-NPCC-GASCO-P5279-4232-1421 | 2017-01-29 | T-X(C)-5279-1316 | 2 | 2017-01-18 | T-NPCC-LOC-P5279-4232-0009 | 2017-01-26 | 1393_150097_DRS0033 | 3 | LOC 'APPROVED CLIENT COMMENTED
|  |  |  | 0A | 2 |  | 2017-02-23 | CSE-OF-4232-023 | 2017-02-26 | T-NPCC-GASCO-P5279-4232-1722 | 2017-03-21 | T-X(C)-5279-1602 | 2 | 2017-02-23 | T-NPCC-LOC-P5279-4232-0044 | 2017-03-01 | 1393_152813_DRS0055 | 3 | LOC APPROVED CLIENT COMMENTED
|  |  |  | 0B | 2 |  | 2017-03-22 | CSE-OF-4232-031 | 2017-03-25 | T-NPCC-GASCO-P5279-4232-1900 |  |  |  | 2017-03-25 | T-NPCC-LOC-P5279-4232-0066 | 2017-03-28 | 1393_155099_DRS0071 | 3 | LOC APPROVED
|  |  |  | 0C | 2 |  | 2017-04-13 | CSE-OF-4232-036 | 2017-04-13 | T-NPCC-GASCO-P5279-4232-1983 |  |  |  | 2017-04-13 | T-NPCC-LOC-P5279-4232-0078 | 2017-04-18 | 004965-LOC-DRS-0088 | 3 | LOC APPROVED
|  |  |  | 0D | 2 |  | 2017-04-20 | CSE-OF-4232-039 | 2017-05-01 | T-NPCC-GASCO-P5279-4232-2043 | 2017-05-09 | T-X-C-5279-1828 | 2 | 2017-05-01 | T-NPCC-LOC-P5279-4232-0086 |  |  |  | CLIENT COMMENTED
|  |  |  | 0E | 2 |  | 2017-06-01 | CSE-OF-4232-055 | 2017-06-06 | T-NPCC-GASCO-P5279-4232-2213 | 2017-06-28 | T-X-C-5279-1985 | 2 | 2017-06-06 | T-NPCC-LOC-P5279-4232-0107 | 2017-06-18 | 1393_160541_DRS011 | 3 | LOC APPROVED CLIENT COMMENTED
|  |  |  | 0F | 1 |  | 2018-04-18 | CSE-OF-4232-119 | 2018-04-22 | T-NPCC-GASCO-5279-4232-3146 | 2018-06-12 | T-X(C)-5279-2652 | 3 | 2018-04-22 | T-NPCC-LOC-5279-4232-0239
|  |  |  | 1 | 1 |  | 2018-06-20 | CSE-OF-4232-120 | 2018-06-20 | T-NPCC-GASCO-5279-4232-3198 | 2018-10-11 | T-X(C)-5279-2767 | 3
3 | PIPELINE MIDLINE TIE-IN ANALYSIS FOR 42” PIPELINE | 4232-NN-RP-103 | GD-100-A4-Z-5-71142 | 0 | 2 | 2017-03-05 | 2017-02-23 | CSE-OF-4232-023 | 2017-02-26 | T-NPCC-GASCO-P5279-4232-1723 | 2017-03-30 | T-X(C)-5279-1645 | 2 | 2017-02-26 | T-NPCC-LOC-P5279-4232-0045 | 2017-03-01 | 1393_152815_DRS0048 | 2 | CLIENT & 'LOC COMMENTED
|  |  |  | 0A | 2 |  | 2017-06-15 | CSE-OF-4232-057 | 2017-06-18 | T-NPCC-GASCO-P5279-4232-2276 | 2017-07-18 | T-X-C-5279-2056 | 2 | 2017-06-18 | T-NPCC-LOC-P5279-4232-0110 | 2017-06-20 | 1393_161515_DRS0116 | 3 | LOC APPROVED CLIENT COMMENTED
|  |  |  | 0B | 2 |  | 2017-08-23 | CSE-OF-4232-082 | 2017-09-05 | T-NPCC-GASCO-P5279-4232-2524 | 2017-09-19 | T-X(C)-5279-2210 | 2 | 2017-09-05 | T-NPCC-LOC-P5279-4232-0154 |  |  |  | CLIENT COMMENTED
|  |  |  | 0C | 2 |  | 2017-09-19 | CSE-OF-4232-093 | 2017-09-20 | T-NPCC-GASCO-P5279-4232-2620 | 2017-11-13 | T-X(C)-5279-2364 | 3 | 2017-09-20 | T-NPCC-LOC-P5279-4232-0177 | 2017-09-23 | 1393_167661_DRS0173 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-22 | CSE-OF-4232-113 | 2018-03-01 | T-NPCC-GASCO-P5279-4232-3068 | 2018-03-14 | T-X(C)-5279-2561 | 2 | [5 empty] | CLIENT COMMENTED
|  |  |  | 1A | 1 |  | 2018-04-18 | CSE-OF-4232-119 | 2018-04-23 | T-NPCC-GASCO-P5279-4232-3148 | 2018-06-12 | T-X(C)-5279-2653 | 3
4 | SHORE PULL ANALYSIS REPORT FOR 42" PIPELINE | 4232-NN-RP-104 | GD-100-A4-Z-5-71143 | 0 | 2 | 2016-08-02 | 2016-12-13 | CSE-OF-4232-003 | 2016-12-18 | T-NPCC-GASCO-P5279-4232-1302 | 2017-01-16 | T-X(C)-5279-1262 | 2 | 2016-12-18 | T-NPCC-LOC-P5279-4232-0009 | 2017-01-15 | 1393_149125_DRS0027 | 2 | LOC & CLIENT COMMENTED
|  |  |  | 0A | 2 |  | 2017-02-01 | CSE-OF-4232-016 | 2017-02-06 | T-NPCC-GASCO-P5279-4232-1524 | 2017-02-23 | T-X(C)-5279-1435 | 2 | 2017-02-20 | T-NPCC-LOC-P5279-4232-0034 | 2017-03-01 | 1393_152617_DRS0052 | 2 | LOC & 'CLIENT COMMENTED
|  |  |  | 0B | 2 |  | 2017-03-07 | CSE-OF-4232-025 | 2017-03-09 | T-NPCC-GASCO-P5279-4232-1790 | 2017-03-19 | T-X(C)-5279-1584 | 2 | 2017-03-09 | T-NPCC-LOC-P5279-4232-0052 |  |  |  | CLIENT COMMENTED
|  |  |  | 0C | 2 |  | 2017-03-20 | CSE-OF-4232-030 | 2017-03-21 | T-NPCC-GASCO-P5279-4232-1886 | 2017-04-20 | T-X-C-5279-1769 | 2 | 2017-03-21 | T-NPCC-LOC-P5279-4232-0065 | 2017-03-21 | 1393_154659_DRS0063 | 3 | LOC APPROVED CLIENT COMMENTED
|  |  |  | 0D | 2 |  | 2017-06-01 | CSE-OF-4232-055 | 2017-06-06 | T-NPCC-GASCO-P5279-4232-2215 | 2017-07-13 | T-X-C-5279-2041 | 3 | 2017-06-06 | T-NPCC-LOC-P5279-4232-0108 | 2017-06-18 | 1393_160543_DRS0112 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-22 | CSE-OF-4232-113 | 2018-03-01 | T-NPCC-GASCO-P5279-4232-3067 | 2018-03-14 | T-X(C)-5279-2564 | 3 | [5 empty] | CLOSED
5 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF 42” PIPE JOINT VALVE ON ZAKHER QUEEN | 4232-NN-RP-105 | GD-100-A4-Z-5-71144 | 0 | 2 |  | 2017-08-02 | CSE-OF-4232-074 | 2017-08-08 | T-NPCC-GASCO-P5279-4232-2451 | 2017-08-14 | T-X-C-5279-2120 | 3 | 2017-08-09 | T-NPCC-LOC-P5279-4232-0140 | 2017-08-20 | 1393_164830_DRS0148 | 3 | CLIENT & LOC APPROVED
|  |  |  | 1 | 1 |  | 2018-02-25 | CSE-OF-4232-115 | 2018-03-01 | T-NPCC-GASCO-P5279-4232-3078 | 2018-04-04 | T-X(C)-5279-2574 | 3 | [5 empty] | CLOSED
6 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON GAC-81 (TRIP-2) | 4232-NN-RP-106 | GD-100-A4-Z-5-71145 | 0 | 2 | 2017-01-20 | 2017-02-09 | CSE-OF-4232-019 | 2017-02-12 | T-NPCC-GASCO-P5279-4232-1595 | 2017-03-13 | T-X(C)-5279-1543 | 3 | 2017-02-20 | T-NPCC-LOC-P5279-4232-0035 | 2017-02-27 | 1393_152614_DRS0047 | 3 | LOC & CLIENT APPROVED
|  |  |  | 0A | 2 |  | 2017-04-03 | CSE-OF-4232-035 | 2017-04-10 | T-NPCC-GASCO-P5279-4232-1955 | 2017-04-30 | T-X-C-5279-1797 | 3 | 2017-04-11 | T-NPCC-LOC-P5279-4232-0075 | 2017-04-13 | 1393_154122_DRS0083 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-25 | CSE-OF-4232-115 | 2018-03-01 | T-NPCC-GASCO-P5279-4232-3080 | 2018-03-22 | T-X(C)-5279-2568 | 3 | [5 empty] | CLOSED
7 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON GAC-81 | 4232-NN-RP-107 | GD-100-A4-Z-5-71146 | 0 | 2 | 2017-02-20 | 2017-03-12 | CSE-OF-4232-027 | 2017-03-15 | T-NPCC-GASCO-P5279-4232-1814 | 2017-04-25 | T-X(C)-5279-1777 | 2 | 2017-03-15 | T-NPCC-LOC-P5279-4232-0055 | 2017-03-22 | 1393_154122_DRS0065 | 3 | LOC APPROVED CLIENT COMMENTED
|  |  |  | 0A | 2 |  | 2017-07-20 | CSE-OF-4232-069 | 2017-07-25 | T-NPCC-GASCO-P5279-4232-2411 | 2017-08-07 | T-X(C)-5279-2106 | 3 | 2017-07-25 | T-NPCC-LOC-P5279-4232-0135 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-27 | CSE-OF-4232-116 | 2018-03-08 | T-NPCC-GASCO-P5279-4232-3083
8 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON SEAWAYS-17 (TRIP-3) | 4232-NN-RP-108 | GD-100-A4-Z-5-71147 | 0 | 2 | 2017-03-20 | 2017-04-17 | CSE-OF-4232-037 | 2017-04-19 | T-NPCC-GASCO-P5279-4232-2012 | 2017-05-23 | T-X-C-5279-1862 | 3 | 2017-04-19 | T-NPCC-LOC-P5279-4232-0082 | 2017-04-19 | 004965-LOC-DRS-0093 | 3 | CLIENT & 'LOC APPROVED
|  |  |  | 1 | 1 |  | 2018-02-27 | CSE-OF-4232-116 | 2018-03-08 | T-NPCC-GASCO-P5279-4232-3084
9 | SEAFASTENING DESIGN REPORT FOR SLEEPERS AND MATTRESSES | 4232-NN-RP-109 | GD-100-A4-Z-5-71148 | 0 | 2 | 2017-01-10 | 2017-01-26 | CSE-OF-4232-015 | 2017-01-31 | T-NPCC-GASCO-P5279-4232-1509 | 2017-02-27 | T-X(C)-5279-1447 | 3 | 2017-01-31 | T-NPCC-LOC-P5279-4232-0028 | 2017-01-31 | 1393_150962_DRS0037 | 3 | LOC AND CLIENT APPROVED
|  |  |  | 0A | 1 |  | 2017-03-19 | CSE-OF-4232-029 | 2017-03-21 | T-NPCC-GASCO-P5279-4232-1873 | 2017-04-26 | T-X(C)-5279-1790 | 3 | 2017-03-21 | T-NPCC-LOC-P5279-4232-0062 | 2017-03-22 | 1393_154657_DRS0067 | 3 | LOC AND CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-27 | CSE-OF-4232-117 | 2018-03-05 | T-NPCC-GASCO-P5279-4232-3088
10 | PIPELINE LIFTING ANALYSIS FOR SLEEPER/SLEEVE INSTALLATION | 4232-NN-RP-110 | used in methods proc as per requested by Jishu
11 | PIPELINE LIFTING ANALYSIS FOR 42" PIPELINE | 4232-NN-RP-111 | GD-100-A4-Z-5-72354 | 0 | 2 |  | 2017-05-09 | CSE-OF-4232-048 | 2017-05-10 | T-NPCC-GASCO-P5279-4232-2101 | 2017-05-30 | T-X-C-5279-1897 | 2 | 2017-05-10 | T-NPCC-LOC-P5279-4232-0099 |  |  |  | CLIENT COMMENTED
|  |  |  | 0A | 2 |  | 2017-08-07 | CSE-OF-4232-077 | 2017-08-21 | T-NPCC-GASCO-P5279-4232-2470 | 2017-10-04 | T-X(C)-5279-2253 | 2 | 2017-08-23 | T-NPCC-LOC-P5279-4232-0145 | 2017-08-23 | 1393_165500_DRS0158 | 3 | LOC APPROVED CLIENT COMMENTED
|  |  |  | 0B | 2 |  | 2017-10-05 | CSE-OF-4232-100 | 2017-10-09 | T-NPCC-GASCO-P5279-4232-2696 | 2017-10-25 | T-X(C)-5279-2306 | 2 | 2017-10-09 | T-NPCC-LOC-P5279-4232-0197 |  |  |  | CLIENT COMMENTED
12 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON AL JABER-34 | 4232-NN-RP-112 | GD-100-A4-Z-5-72432 | 0 | 2 |  | 2017-07-17 | CSE-OF-4232-068 | 2017-07-23 | T-NPCC-GASCO-P5279-4232-2399 | 2017-07-25 | T-X-C-5279-2077 | 3 | 2017-07-23 | T-NPCC-LOC-P5279-4232-0132 | 2017-07-23 | 1393_163766_DRS0134 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-27 | CSE-OF-4232-117 | 2018-03-05 | T-NPCC-GASCO-P5279-4232-3089
13 | PIPELINE LIFTING ANALYSIS FOR SLEEPER SHIFTING | 4232-NN-RP-113 | GD-100-A4-Z-5-72435 | 0 | 2 |  | 2017-09-05 | CSE-OF-4232-085 | 2017-09-06 | T-NPCC-GASCO-P5279-4232-2568 | 2017-09-10 | T-X-C-5279-2184 | 2 | 2017-09-06 | T-NPCC-LOC-P5279-4232-0159 |  |  |  | CLIENT COMMENTED
|  |  |  | 0A | 1 |  | 2017-09-12 | CSE-OF-4232-088 | 2017-09-17 | T-NPCC-GASCO-P5279-4232-2590 | 2017-09-19 | T-X(C)-5279-2219 | 3 | 2017-09-17 | T-NPCC-LOC-P5279-4232-0167 | 2017-09-17 | 1393_167144_DRS0211 | 3 | CLIENT & LOC APPROVED
|  |  |  | 1 | 1 |  | 2018-02-22 | CSE-OF-4232-113 | 2018-03-01 | T-NPCC-GASCO-P5279-4232-3070 | 2018-03-22 | T-X(C)-5279-2566 | 3 | [5 empty] | CLOSED
14 | PIPELINE LIFTING ANALYSIS FOR GROUT BAGS INSTALLATION | 4232-NN-RP-114 | GD-100-A4-Z-5-72456 | 0 |  |  | 2017-09-12 | CSE-OF-4232-088 | 2017-09-14 | T-NPCC-GASCO-P5279-4232-2588 | 2017-09-25 | T-X(C)-5279-2232 | 2 | 2017-09-14 | T-NPCC-LOC-P5279-4232-0166 | 2017-09-14 | 1393_166942_DRS0212 | 3 | CLIENT COMMENTED LOC APPROVED
|  |  |  | 0A | 1 |  | 2017-10-01 | CSE-OF-4232-096 | 2017-10-04 | T-NPCC-GASCO-P5279-4232-2663 | 2017-10-09 | T-X(C)-5279-2265 | 3 | 2017-10-04 | T-NPCC-LOC-P5279-4232-0190 | 2017-10-09 | 1393_168177_DRS0226 | 3 | CLIENT & LOC APPROVED
|  |  |  | 0B | 1 |  | 2017-10-10 | CSE-OF-4232-102 | 2017-10-12 | T-NPCC-GASCO-P5279-4232-2715 | 2017-10-22 | T-X(C)-5279-2294 | 2 | 2017-10-12 | T-NPCC-LOC-P5279-4232-0200 |  |  |  | CLIENT COMMENTED
|  |  |  | 0C | 1 |  | 2017-01-08 | CSE-OF-4232-110 | 2017-01-08 | T-NPCC-GASCO-P5279-4232-2983 | 2018-01-21 | T-X(C)-5279-2499 | 3 | [5 empty] | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-22 | CSE-OF-4232-113 | 2018-03-01 | T-NPCC-GASCO-P5279-4232-3071 | 2018-03-22 | T-X(C)-5279-2567 | 3 | [5 empty] | CLOSED
15 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON AL JABER-35 | 4232-NN-RP-115 | GD-100-A4-Z-5-72458 | 0 | 2 |  | 2017-09-19 | CSE-OF-4232-092 | 2017-09-21 | T-NPCC-GASCO-P5279-4232-2609 | 2017-09-25 | T-X(C)-5279-2234 | 3 | 2017-09-21 | T-NPCC-LOC-P5279-4232-0174 | 2017-09-20 | 1393_167378_DRS0169 | 3 | CLIENT & 'LOC APPROVED
|  |  |  | 1 | 1 |  | 2018-03-01 | CSE-OF-4232-118 | 2018-03-05 | T-NPCC-GASCO-P5279-4232-3093
16 | LIFT ANALISYS OF 30”RISER AT KP-38 | 4232-NN-RP-116 | GD-100-A4-Z-5-72467 | 0 | 2 |  | 2017-10-26 | CSE-OF-4232-104 | 2017-10-31 | T-NPCC-GASCO-P5279-4232-2813 | 2017-11-19 | T-X(C)-5279-2387 | 3 | 2017-10-31 | T-NPCC-LOC-P5279-4232-0203 | 2017-10-31 | 1393_169442_DRS0250 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-03-01 | CSE-OF-4232-118 | 2018-03-08 | T-NPCC-GASCO-P5279-4232-3094
17 | PIPELINE LIFTING ANALYSIS FOR 3LPP COATING REPAIR AT JOINT NO: 192 | 4232-NN-RP-117 | GD-100-A4-Z-5-72468 | 0 | 2 |  | 2018-01-29 | CSE-OF-4232-111 | 2018-02-01 | T-NPCC-GASCO-P5279-4232-3007 | 2018-02-04 | T-X(C)-5279-2510 | 2 | 2018-02-01 | T-NPCC-LOC-P5279-4232-0235 |  |  |  | CLIENT COMMENTED
|  |  |  | 0A | 1 |  | 2018-02-07 | CSE-OF-4232-112 | 2018-02-09 | T-NPCC-GASCO-P5279-4232-3038 | 2018-06-12 | T-X(C)-5279-2651 | 3 | 2018-02-11 | T-NPCC-LOC-P5279-4232-0236
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION; (4) REJECTED
GASCO CODE : (1) REJECTED; (2) COMMENTS AS NOTED; (3) NO COMMENTS; (4) INFORMATION ONLY
LOC APPROVAL CODE : (1) THE COMMENT HAS BEEN SATISFACTORILY CLOSED; (2) THE COMMENT REQUIRES ACTION; (3) AN OBSERVATION THAT REQUIRES NO ACTION

## Documents - Naval Marine
|  | ABU DHABI GAS INDUSTRIES LTD (GASCO) | [11 empty] | NPCC DOC. No.: 4232-PP-GE-001
IGD-E (PHASE-1) – 42” OFFSHORE PIPELINE PROJECT
|  | GASCO AGREEMENT NO. 13527904 FOR EPC WORKS / GASCO PROJECT NO. 5279 | [11 empty] | REVISION : |  |  |  | 0
|  | NPCC PROJECT NO. 4232 | [11 empty] | DATE : |  |  |  | 2016-11-15
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | CLIENT DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN |  |  | NPCC |  | CLIENT |  |  | MWS |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | MOORING ANALYSIS DURING PIPELAYING OF 42" PIPELINE FROM RAS AL QILA TO MID LINE TIE-IN | 4232-ZZ-CL-101 | GD-100-A4-Z-5-71149 | 0 | 2 | 2017-01-10 | 2017-08-28 | CSE-OF-4232-084 | 2017-08-30 | T-NPCC-GASCO-P5279-4232-2546 | 2017-09-06 | T-X(C)-5279-2162 | 2 | 2017-08-30 | T-NPCC-LOC-P5279-4232-0157 | 2017-09-05 | 1393_165913_DRS0153 | 2 | CLIENT & 'LOC COMMENTED
|  |  |  | 0A | 1 |  | 2017-09-13 | CSE-OF-4232-090 | 2017-09-13 | T-NPCC-GASCO-P5279-4232-2600 | 2017-11-01 | T-X(C)-5279-2336 | 3 | 2017-09-17 | T-NPCC-LOC-P5279-4232-0169 | 2017-09-27 | 1393_167150_DRS0198 | 1 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2017-11-06 | CSE-OF-4232-107 | 2017-11-07 | T-NPCC-GASCO-P5279-4232-2836 | 2017-11-19 | T-X(C)-5279-2385 | 3 | 2017-11-07 | L-NPCC-LOC-P5279-4232-0215 |  |  |  | CLIENT APPROVED
2 | MOORING ANALYSIS DURING PIPELAYING OF 42" PIPELINE FROM DAS ISLAND TO MID LINE TIE-IN | 4232-ZZ-CL-102 | GD-100-A4-Z-5-71150 | 0 | 2 | 2017-01-10 | 2017-01-15 | CSE-OF-4232-010 | 2017-01-17 | T-NPCC-GASCO-P5279-4232-1464 | 2017-02-16 | T-X(C)-5279-1401 | 2 | 2017-01-17 | T-NPCC-LOC-P5279-4232-0021 | 2017-01-30 | 1393_150108_DRS0036 | 2 | CLIENT & LOC COMMENTED
|  |  |  | 0A | 2 |  | 2017-02-22 | CSE-OF-4232-022 | 2017-03-01 | T-NPCC-GASCO-P5279-4232-1699 | 2017-03-29 | T-X(C)-5279-1663 | 3 | 2017-03-01 | T-NPCC-LOC-P5279-4232-0042 | 2017-03-02 | 1393_153107_DRS0056 | 1 | CLIENT & 'LOC APPROVED
|  |  |  | 1 | 1 |  | 2017-11-08 | CSE-OF-4232-109 | 2017-11-13 | T-NPCC-GASCO-P5279-4232-2857 |  |  |  | 2017-11-13 | T-NPCC-LOC-P5279-4232-0218
3 | MOORING ANALYSIS DURING 42” PIPELINE MID LINE TIE-IN | 4232-ZZ-CL-103 | GD-100-A4-Z-5-71151 | 0 | 2 | 2017-03-10 | was included in 4232-zz-cl-111
4 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES TRIP-1 | 4232-ZZ-CL-104 | GD-100-A4-Z-5-71152 | 0 | 2 | 2017-01-20 | 2017-02-12 | CSE-OF-4232-021 | 2017-02-14 | T-NPCC-GASCO-P5279-4232-1625 | 2017-03-13 | T-X(C)-5279-1544 | 2 | [5 empty] | CLIENT COMMENTED
|  |  |  | 0A | 2 |  | 2017-03-30 | CSE-OF-4232-034 | 2017-04-03 | T-NPCC-GASCO-P5279-4232-1944 | 2017-04-05 | T-X-C-5279-1693 | 3 | 2017-04-03 | T-NPCC-LOC-P5279-4232-0071 | 2017-04-02 | 004965-LOC-DRS-0079 | 2 | CLIENT APPROVED LOC COMMENTED
|  |  |  | CRS TO LOC | [9 empty] | 2017-04-06 | LOC RESPONSE | 2017-04-10 | 1393_156072_DRS0081 | 1 | LOC COMMENTS CLOSED
|  |  |  | 1 | 1 |  | 2017-11-08 | CSE-OF-4232-109 | 2017-11-13 | T-NPCC-GASCO-P5279-4232-2864 | 2017-11-16 | T-X(C)-5279-2380 | 3 | 2017-11-13 | T-NPCC-LOC-P5279-4232-0219 |  |  |  | CLIENT APPROVED
5 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPES ON GAC-81 | 4232-ZZ-CL-105 | GD-100-A4-Z-5-71153 | 0 | 2 | 2017-02-20 | 2017-03-07 | CSE-OF-4232-026 | 2017-03-09 | T-NPCC-GASCO-P5279-4232-1791 |  |  |  | 2017-03-09 | T-NPCC-LOC-P5279-4232-0053 | 2017-03-23 | 1393_153917_DRS0070 | 2 | LOC COMMENTED
|  |  |  | 0A | 2 |  | 2017-03-30 | CSE-OF-4232-034 | 2017-04-03 | T-NPCC-GASCO-P5279-4232-1945 |  |  |  | 2017-04-03 | T-NPCC-LOC-P5279-4232-0072 | 2017-04-04 | 004965-LOC-DRS-0080 | 2 | LOC COMMENTED
[14 empty] | 2017-04-16 | email sent to loc | 2017-04-19 | 004965-LOC-DRS-0091 | 1 | LOC APPROVED
|  |  |  | 0B | 2 |  | 2017-04-17 | CSE-OF-4232-037 | 2017-04-19 | T-NPCC-GASCO-P5279-4232-2019 | 2017-04-26 | T-X(C)-5279-1788 | 2 | 2017-04-19 | T-NPCC-LOC-P5279-4232-0084 |  |  |  | CLIENT COMMENTED
|  |  |  | 0C | 1 |  | 2017-04-24 | CSE-OF-4232-040 | 2017-04-25 | T-NPCC-GASCO-P5279-4232-2046 | 2017-06-21 | T-X-C-5279-1972 | 3 | 2017-04-24 | T-NPCC-LOC-P5279-4232-0087 | 2017-04-25 | 004965-LOC-DRS-0096 | 1 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2017-11-08 | CSE-OF-4232-109 | 2017-11-13 | T-NPCC-GASCO-P5279-4232-2865 | 2017-12-06 | T-X(C)-5279-2416 | 1 | 2017-11-13 | T-NPCC-LOC-P5279-4232-0220 |  |  |  | CLIENT APPROVED
6 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES (TRIP-3) | 4232-ZZ-CL-106 | GD-100-A4-Z-5-71154 | 0 | 2 | 2017-03-20 | 2017-04-17 | CSE-OF-4232-037 | 2017-04-19 | T-NPCC-GASCO-P5279-4232-1998 | 2017-06-21 | T-X-C-5279-1971 | 3 | 2017-04-19 | T-NPCC-LOC-P5279-4232-0080 | 2017-04-19 | 004965-LOC-DRS-0092 | 1 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2017-11-08 | CSE-OF-4232-109 | 2017-11-13 | T-NPCC-GASCO-P5279-4232-2866 |  |  |  | 2017-11-13 | T-NPCC-LOC-P5279-4232-0221
7 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE MATTRESS & RCC SLEEPERS (TRIP-1) | 4232-ZZ-CL-107 | GD-100-A4-Z-5-71155 | 0 | 2 | 2017-01-10 | 2017-01-25 | CSE-OF-4232-014 | 2017-01-26 | T-NPCC-GASCO-P5279-4232-1490 | 2017-02-22 | T-X(C)-5279-1419 | 2 | 2017-01-26 | T-NPCC-LOC-P5279-4232-0025 | 2017-02-12 | 1393_151807_DRS0040 | 1 | LOC APPROVED CLIENT COMMENTED
|  |  |  | 0A | 1 |  | 2017-02-27 | CSE-OF-4232-022 | 2017-03-01 | T-NPCC-GASCO-P5279-4232-1700 |  |  |  | 2017-03-02 | T-NPCC-LOC-P5279-4232-0043 | 2017-03-07 | 1393_153369_DRS0059 | 1 | LOC APPROVED
|  |  |  | 0B | 1 |  | 2017-03-16 | CSE-OF-4232-028 | 2017-03-19 | T-NPCC-GASCO-P5279-4232-1849 | 2017-04-13 | T-X(C)-5279-1736 | 3 | 2017-03-19 | T-NPCC-LOC-P5279-4232-0059 | 2017-03-22 | 1393_154496_DRS0066 | 1 | CLIENT & 'LOC APPROVED
|  |  |  | 1 | 1 |  | 2017-11-08 | CSE-OF-4232-109 | 2017-11-13 | T-NPCC-GASCO-P5279-4232-2867 | 2017-12-06 | T-X(C)-5279-2417 | 1 | 2017-11-13 | T-NPCC-LOC-P5279-4232-0222 |  |  |  | CLIENT APPROVED
8 | MOORING ANALYSIS DURING TRIPOD INSTALLATION AT KP 88 | 4232-ZZ-CL-108 | GD-100-A4-Z-5-71156 | 0 | 2 |  | 2017-08-01 | CSE-OF-4232-073 | 2017-08-03 | T-NPCC-GASCO-P5279-4232-2450 | 2017-09-17 | T-X-C-5279-2203 | 2 | 2017-08-03 | T-NPCC-LOC-P5279-4232-0139
9 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES ON AL-JABER-34 | 4232-ZZ-CL-109 | GD-100-A4-Z-5-72431 | 0 | 2 |  | 2017-07-17 | CSE-OF-4232-068 | 2017-07-19 | T-NPCC-GASCO-P5279-4232-2400 | 2017-07-23 | T-X-C-5279-2068 | 3 | 2017-07-19 | T-NPCC-LOC-P5279-4232-0133 | 2017-07-20 | 1393_163657_DRS0135 | 3 | CLIENT & LOC APPROVED
|  |  |  | 1 | 1 |  | 2017-11-08 | CSE-OF-4232-109 | 2017-11-13 | T-NPCC-GASCO-P5279-4232-2868 | 2017-11-21 | T-X(C)-5279-2396 | 3 | 2017-11-13 | T-NPCC-LOC-P5279-4232-0223 |  |  |  | CLIENT APPROVED
10 | MOORING ANALYSIS DURING JACKET INSTALLATION AT KP 38 | 4232-ZZ-CL-110 | GD-100-A4-Z-5-72433 | 0 | 2 |  | 2017-08-03 | CSE-OF-4232-075 | 2017-08-03 | T-NPCC-GASCO-P5279-4232-2458 | 2017-09-12 | T-X-C-5279-2204 | 2 | 2017-08-03 | T-NPCC-LOC-P5279-4232-0143 | 2017-09-26 | 1393_168144_DRS0194 | 2 | LOC & CLIENT COMMENTED
|  |  |  | 0A | 1 |  | 2017-10-03 | CSE-OF-4232-098 | 2017-10-04 | T-NPCC-GASCO-P5279-4232-2690 |  |  |  | 2017-10-04 | T-NPCC-LOC-P5279-4232-0194 | 2017-10-03 | 1393_168144_DRS0217 | 2 | LOC COMMENTED
|  |  |  | 0B | 1 |  | 2017-10-04 | CSE-OF-4232-099 | 2017-10-08 | T-NPCC-GASCO-P5279-4232-2692 | 2017-10-25 | T-X(C)-5279-2304 | 2 | 2017-10-08 | T-NPCC-LOC-P5279-4232-0195 | 2017-10-04 | 1393_168144_DRS0218 | 3 | LOC APPROVED CLIENT COMMENTED
|  |  |  | 1 | 1 |  | 2017-11-06 | CSE-OF-4232-106 | 2017-11-07 | T-NPCC-GASCO-P5279-4232-2835 | 2017-11-19 | T-X(C)-5279-2384 | 3 | 2017-11-07 | L-NPCC-LOC-P5279-4232-0214 |  |  |  | CLIENT APPROVED
11 | MOORING ANALYSIS DURING MIDLINE TIE IN AT KP 102.35 | 4232-ZZ-CL-111 | GD-100-A4-Z-5-72434 | 0 | 2 |  | 2017-08-06 | CSE-OF-4232-076 | 2017-08-07 | T-NPCC-GASCO-P5279-4232-2468 | 2017-09-08 | T-X(C)-5279-2174 | 2 | 2017-08-07 | T-NPCC-LOC-P5279-4232-0144 | 2017-08-20 | 1393_164775_DRS0149 | 2 | CLIENT & 'LOC COMMENTED
|  |  |  | 0A | 1 |  | 2017-09-27 | CSE-OF-4232-094 | 2017-09-28 | T-NPCC-GASCO-P5279-4232-2645 | 2017-10-13 | T-X(C)-5279-2360 | 3 | 2017-09-27 | T-NPCC-LOC-P5279-4232-0186 | 2017-09-27 | 1393_167874_DRS0197 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-25 | CSE-OF-4232-114 | 2018-03-01 | T-NPCC-GASCO-P5279-4232-3072 | 2018-04-04 | T-X(C)-5279-2572 | 3 | [5 empty] | CLOSED
12 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES ON AL-JABER-35 | 4232-ZZ-CL-112 | GD-100-A4-Z-5-72473 | 0 | 2 |  | 2017-09-19 | CSE-OF-4232-092 | 2017-09-19 | T-NPCC-GASCO-P5279-4232-2612 | 2017-10-08 | T-X(C)-5279-2258 | 3 | 2017-09-23 | T-NPCC-LOC-P5279-4232-0176 | 2017-09-20 | 1393_167380_DRS0167 | 3 | LOC APPROVED CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2017-11-08 | CSE-OF-4232-109 | 2017-11-13 | T-NPCC-GASCO-P5279-4232-2869 | 2017-11-21 | T-X(C)-5279-2397 | 3 | 2017-11-13 | T-NPCC-LOC-P5279-4232-0224 |  |  |  | CLIENT APPROVED
13 | MOORING ANALYSIS DURING INSTALLATION OF DECK AT KP 38 | 4232-ZZ-CL-113 | GD-100-A4-Z-5-72466 | 0 | 2 |  | 2017-10-23 | CSE-OF-4232-103 | 2017-10-26 | T-NPCC-GASCO-P5279-4232-2792 | 2017-10-29 | T-X(C)-5279-2318 | 2 | 2017-10-26 | T-NPCC-LOC-P5279-4232-0201 | 2017-10-26 | 1393_169244_DRS0247 | 2 | CLIENT COMMENTED LOC APPROVED
|  |  |  | 0A | 1 |  | 2017-11-02 | CSE-OF-4232-105 | 2017-11-02 | T-NPCC-GASCO-P5279-4232-2831 | 2017-11-16 | T-X(C)-5279-2376 | 3 | 2017-11-02 | T-NPCC-LOC-P5279-4232-0212 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-25 | CSE-OF-4232-114 | 2018-03-01 | T-NPCC-GASCO-P5279-4232-3073 | 2018-04-04 | T-X(C)-5279-2573 | 3 | [5 empty] | CLOSED
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION; (4) REJECTED
GASCO CODE : (1) REJECTED; (2) COMMENTS AS NOTED; (3) NO COMMENTS; (4) INFORMATION ONLY
LOC APPROVAL CODE : (1) THE COMMENT HAS BEEN SATISFACTORILY CLOSED; (2) THE COMMENT REQUIRES ACTION; (3) AN OBSERVATION THAT REQUIRES NO ACTION

## Drawings
|  | ABU DHABI GAS INDUSTRIES LTD (GASCO) | [11 empty] | NPCC DOC. No.: 4232-PP-GE-001
IGD-E (PHASE-1) – 42” OFFSHORE PIPELINE PROJECT
|  | GASCO AGREEMENT NO. 13527904 FOR EPC WORKS / GASCO PROJECT NO. 5279 | [11 empty] | REVISION : |  |  |  | 0
|  | NPCC PROJECT NO. 4232 | [11 empty] | DATE : |  |  |  | 2016-11-15
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | CLIENT DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN |  |  | NPCC |  | CLIENT |  |  | MWS |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIGGING AND HYDROTEST DIAGRAM DAS ISLAND TO RAS AL QILA | 4232-NN-1001 | GD-100-A3-Z-5-71157 | 0 | 2 | 2017-07-10 | 2017-09-12 | CSE-OF-4232-087 | 2017-09-12 | T-NPCC-GASCO-P5279-4232-2587 | 2017-09-19 | T-X-C-5279-2216 | 2 | 2017-09-17 | T-NPCC-LOC-P5279-4232-0165 | 2017-09-26 | 1393_166941_DRS0181 | NA | CLIENT COMMENTED
2 | BUCKLE DETECTOR DETAILS FOR 42" IGD-E OFFSHORE GAS P/L FROM DAS ISLAND TO RAS AL QILA | 4232-NN-1002 | GD-100-A3-Z-5-71158 | 0 | 2 | 2017-01-15 | 2017-01-03 | CSE-OF-4232-005 | 2017-01-12 | T-NPCC-GASCO-P5279-4232-1412
|  |  |  | 0A | 2 |  | 2017-03-23 | CSE-OF-4232-032 | 2017-03-25 | T-NPCC-GASCO-P5279-4232-1909 | 2017-03-30 | T-X(C)-5279-1677 | 3 | 2017-03-26 | T-NPCC-LOC-P5279-4232-0067 | 2017-03-28 | 1393_155102_DRS0074 | 3 | CLIENT APPROVED 'LOC - INFORMATION
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
3 | SHORE PULL HEAD DETAILS FOR 42" IGD-E OFFSHORE GAS PIPELINE DAS ISLAND TO RAS AL QILA | 4232-NN-1003 | GD-100-A3-Z-5-71159 | 0 | 2 | 2017-03-15 | 2017-01-17 | CSE-OF-4232-012 | 2017-01-19 | T-NPCC-GASCO-P5279-4232-1430 |  |  |  | 2017-01-19 | T-NPCC-LOC-P5279-4232-0018 | 2017-01-26 | 1393_150507_DRS0034 | 3 | LOC - INFORMATION
4 | LOADING ARRG’T & SEAFASTENING DETAILS OF C.C PIPES @JABER-34 (TRIP-29) | 4232-NN-1004 | GD-100-A3-Z-5-71160 | 0 | 2 | 2017-01-15 | 2017-09-10 | CSE-OF-4232-086 | 2017-09-14 | T-NPCC-GASCO-P5279-4232-2579 | 2017-09-19 | T-X(C)-5279-2213 | 3 | 2017-09-14 | T-NPCC-LOC-P5279-4232-0163 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
5 | EMERGENCY / LAYDOWN HEAD DETAILS FOR 42"x30.18 THK. IGD-E OFFSHORE GAS PIPELINE DAS ISLAND TO RAS AL QILA | 4232-NN-1005 | GD-100-A3-Z-5-71161 | 0 | 2 | 2017-01-15 | 2017-01-17 | CSE-OF-4232-013 | 2017-01-19 | T-NPCC-GASCO-P5279-4232-1430 | 2017-10-02 | T-X(C)-5279-2243 | 3 | 2017-01-19 | T-NPCC-LOC-P5279-4232-0018 | 2017-01-26 | 1393_150508_DRS0035 | 3 | LOC - 'INFORMATION CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
6 | LAYDOWN HEAD DETAILS FOR 42" PIPELINE | 4232-NN-1006 | GD-100-A3-Z-5-71162 | 0 | 2 | 2017-03-15
7 | X-RAY STOPPER DETAILS FOR 42" PIPELINE FROM RAS AL QILA TO DAS ISLAND | 4232-NN-1008 | GD-100-A3-Z-5-71163 | 0 | 2 | 2016-09-15
8 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF C.C. PIPES @ GAC-82 (TRIP-1) | 4232-NN-1009 | GD-100-A3-Z-5-71164 | 0 | 2 | 2017-01-20 | 2017-02-13 | CSE-OF-4232-022 | 2017-02-14 | T-NPCC-GASCO-P5279-4232-1626 | 2017-03-13 | T-X(C)-5279-1545 | 3 | 2017-03-19 | T-NPCC-LOC-P5279-4232-0057 | 2017-03-22 | 1393_154498_DRS0069 | 2 | CLIENT APPROVED LOC COMMENTED
|  |  |  | 0A | 2 |  | 2017-03-29 | CSE-OF-4232-033 | 2017-04-02 | T-NPCC-GASCO-P5279-4232-1936 | 2017-04-03 | T-X(C)-5279-1685 | 3 | 2017-03-29 | T-NPCC-LOC-P5279-4232-0069 | 2017-04-02 | 004965-LOC-DRS-0077 | 2 | CLIENT APPROVED LOC COMMENTED
|  |  |  | CRS TO LOC | [9 empty] | 2017-04-06 | LOC RESPONSE | 2017-04-10 | 1393_156073_DRS0082 | 3 | LOC COMMENTS CLOSED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
9 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF C.C. PIPES @GAC-81 (TRIP-2) | 4232-NN-1010 | GD-100-A3-Z-5-71165 | 0 | 2 | 2017-02-20 | 2017-03-12 | CSE-OF-4232-027 | 2017-03-15 | T-NPCC-GASCO-P5279-4232-1813 |  |  |  | 2017-03-15 | T-NPCC-LOC-P5279-4232-0054 | 2017-03-22 | 1393_154121_DRS0068 | 2 | LOC COMMENTED
|  |  |  | 0A | 2 |  | 2017-03-29 | CSE-OF-4232-033 | 2017-04-02 | T-NPCC-GASCO-P5279-4232-1938 | 2017-04-03 | T-X(C)-5279-1686 | 3 | 2017-03-29 | T-NPCC-LOC-P5279-4232-0070 | 2017-04-02 | 004965-LOC-DRS-0078 | 2 | CLIENT APPROVED LOC COMMENTED (CRS SENT TO LOC 13/04)
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
10 | LOADING ARRGT & SEAFASTENING DETAILS OF CC PIPES @ SEAWAYS-17 (TRIP-3) | 4232-NN-1011 | GD-100-A3-Z-5-71166 | 0 | 2 | 2017-03-20 | 2017-04-17 | CSE-OF-4232-037 | 2017-04-19 | T-NPCC-GASCO-P5279-4232-2018 | 2017-04-25 | T-X-C-5279-1778 | 3 | 2017-04-19 | T-NPCC-LOC-P5279-4232-0083
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
11 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES @ GAC-82 (TRIP-4) | 4232-NN-1012 | GD-100-A3-Z-5-71167 | 0 | 2 | 2017-04-01 | 2017-04-20 | CSE-OF-4232-038 | 2017-04-25 | T-NPCC-GASCO-P5279-4232-2041 | 2017-04-27 | T-X-(C)-5279-1794 | 2 | 2017-04-25 | T-NPCC-LOC-P5279-4232-0085 | 2017-04-25 | 004965-LOC-DRS- 0095 | 2 | LOC AND CLIENT COMMENTED
|  |  |  | 0A | 1 |  | 2017-04-26 | CSE-OF-4232-041 | 2017-04-29 | T-NPCC-GASCO-P5279-4232-2051 | 2017-05-03 | T-X(C)-5279-1804 | 2 | 2017-04-29 | T-NPCC-LOC-P5279-4232-0088 |  |  |  | CLIENT COMMENTED
|  |  |  | 1 | 1 |  | 2018-06-20 | CSE-OF-4232-120 | 2018-06-20 | T-NPCC-GASCO-P5279-4232-3199
12 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES @ GAC-81 (TRIP-5) | 4232-NN-1013 | GD-100-A3-Z-5-71168 | 0 | 2 | 2017-04-15 | 2017-04-27 | CSE-OF-4232-042 | 2017-04-29 | T-NPCC-GASCO-P5279-4232-2060 | 2017-05-03 | T-X(C)-5279-1810 | 2 | 2017-04-29 | T-NPCC-LOC-P5279-4232-0089 | 2017-04-29 | 1393_157939_DRS0098 | 2 | CLIENT & LOC COMMENTED
[7 empty] | 2017-05-04 | CRS TO LOC SENT | [5 empty] | 2017-05-09 | T-NPCC-LOC-P5279-4232-0095
|  |  |  | 0A | 2 |  | 2017-05-09 | CSE-OF-4232-046 | 2017-05-10 | T-NPCC-GASCO-P5279-4232-2100 | 2017-05-25 | T-X-C-5279-1878 | 3 | 2017-05-10 | T-NPCC-LOC-P5279-4232-0098 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
13 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES @ SEAWAYS-17 (TRIP-6) | 4232-NN-1014 | GD-100-A3-Z-5-71169 | 0 | 2 | 2017-04-30 | 2017-04-27 | CSE-OF-4232-042 | 2017-04-29 | T-NPCC-GASCO-P5279-4232-2060 | 2017-05-03 | T-X(C)-5279-1810 | 2 | 2017-04-29 | T-NPCC-LOC-P5279-4232-0089 | 2017-04-29 | 1393_157940_DRS0099 | 2 | CLIENT & LOC COMMENTED
[7 empty] | 2017-05-08 | CRS TO LOC SENT | [5 empty] | 2017-05-09 | T-NPCC-LOC-P5279-4232-0095
14 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES @ GAC-82 (TRIP-7) | 4232-NN-1015 | GD-100-A3-Z-5-71170 | 0 | 2 | 2017-05-01 | 2017-04-27 | CSE-OF-4232-042 | 2017-04-29 | T-NPCC-GASCO-P5279-4232-2060 | 2017-05-03 | T-X(C)-5279-1810 | 2 | 2017-04-29 | T-NPCC-LOC-P5279-4232-0089 | 2017-05-11 | 1393_157941_DRS0103 | 3 | CLIENT COMMENTED LOC APPROVED
|  |  |  | 0A | 2 |  | 2017-05-10 | CSE-OF-4232-047 | 2017-05-11 | T-NPCC-GASCO-P5279-4232-2098 | 2017-05-25 | T-X-C-5279-1876 | 3 | 2017-05-15 | T-NPCC-LOC-P5279-4232-0096 | 2017-05-16 | 004965-LOC-DRS-0104 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055
15 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-81(TRIP-8) | 4232-NN-1016 | GD-100-A3-Z-5-71171 | 0 | 2 | 2017-05-15 | 2017-04-30 | CSE-OF-4232-044 | 2017-05-01 | T-NPCC-GASCO-P5279-4232-2067 | 2017-05-09 | T-X-C-5279-1823 | 2 | 2017-05-01 | T-NPCC-LOC-P5279-4232-0092 | 2017-05-11 | 1393_157981_DRS0102 | 3 | CLIENT COMMENTED LOC APPROVED
|  |  |  | 0A | 2 |  | 2017-05-09 | CSE-OF-4232-047 | 2017-05-10 | T-NPCC-GASCO-P5279-4232-2099 | 2017-05-25 | T-X-C-5279-1877 | 3 | 2017-05-10 | T-NPCC-LOC-P5279-4232-0097 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
16 | LOADING ARRGT AND SEAFASTENING DETAILS OF CC PIPES @ SEAWAYS-17 (TRIP-9) | 4232-NN-1017 | GD-100-A3-Z-5-71172 | 0 | 2 | 2017-05-30 | 2017-05-07 | CSE-OF-4232-045 | 2017-05-10 | T-NPCC-GASCO-P5279-4232-2089 | 2017-05-25 | T-X-C-5279-1882 | 3 | 2017-05-10 | T-NPCC-LOC-P5279-4232-0093 | 2017-05-11 | 1393_158667_DRS0101 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
17 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-82 (TRIP-10) | 4232-NN-1018 | GD-100-A3-Z-5-71173 | 0 | 2 | 2017-06-01 | 2017-05-11 | CSE-OF-4232-049 | 2017-05-15 | T-NPCC-GASCO-P5279-4232-2112 | 2017-05-25 | T-X(C )-5272-1883 | 3 | 2017-05-15 | T-NPCC-LOC-P5279-4232-0101 | 2017-05-21 | 1393_159428_DRS0107 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
18 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-81 (TRIP-11) | 4232-NN-1019 | GD-100-A3-Z-5-71174 | 0 | 2 | 2017-06-15 | 2017-05-16 | CSE-OF-4232-050 | 2017-05-21 | T-NPCC-GASCO-P5279-4232-2133 | 2017-06-21 | T-X-C-5279-1973 | 3 | 2017-05-21 | T-NPCC-LOC-P5279-4232-0102 | 2017-05-21 | 1393_159427_DRS0106 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
19 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ SEAWAYS-17 (TRIP-12) | 4232-NN-1020 | GD-100-A3-Z-5-71175 | 0 | 2 | 2017-06-30 | 2017-05-18 | CSE-OF-4232-051 | 2017-05-22 | T-NPCC-GASCO-P5279-4232-2139 | 2017-05-30 | T-X-C-5279-1895 | 3 | 2017-05-22 | T-NPCC-LOC-P5279-4232-0202 | 2017-05-23 | 1393_159535_DRS0108 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
20 | LOADING ARRANGEMENT AND SEAFASTENING OF CC PIPES @ GAC-82 (TRIP-13) | 4232-NN-1021 | GD-100-A3-Z-5-71176 | 0 | 2 | 2017-07-01 | 2017-05-18 | CSE-OF-4232-051 | 2017-05-22 | T-NPCC-GASCO-P5279-4232-2139 | 2017-05-30 | T-X-C-5279-1895 | 3 | 2017-05-22 | T-NPCC-LOC-P5279-4232-0202 | 2017-06-18 | 1393_159536_DRS0109 | 3 | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
21 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-81 (TRIP-14) | 4232-NN-1022 | GD-100-A3-Z-5-71177 | 0 | 2 | 2017-07-15 | 2017-05-24 | CSE-OF-4232-053 | 2017-05-28 | T-NPCC-GASCO-P5279-4232-2172 | 2017-06-01 | T-X(C)-5279-1910 | 3 | 2017-05-28 | T-NPCC-LOC-P5279-4232-0105 | 2017-06-18 | 1393_159877_DRS0115 | 3 | CLIENT & LOC APPROVED
|  |  |  | 1 | 2 |  | 2017-06-22 | CSE-OF-4232-059 | 2017-06-28 | T-NPCC-GASCO-P5279-4232-2291 | 2017-07-03 | T-X-C-5279-2001 | 3 | 2017-06-28 | T-NPCC-LOC-P5279-4232-0113 | 2017-07-04 | 1393_162199_DRS0120 | 3 | CLIENT & LOC APPROVED
22 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ SEAWAYS-17 (TRIP-15) | 4232-NN-1023 | GD-100-A3-Z-5-71178 | 0 | 2 | 2017-07-30 | 2017-06-01 | CSE-OF-4232-054 | 2017-06-06 | T-NPCC-GASCO-P5279-4232-2207 | 2017-06-12 | T-X-C-5279-1941 | 3 | 2017-06-06 | T-NPCC-LOC-P5279-4232-0106 | 2017-06-18 | 004965-LOC-DRS-0114 | 3 | CLIENT & LOC APPROVED
|  |  |  | 0A | 2 |  | 2017-06-28 | CSE-OF-4232-061 | 2017-07-04 | T-NPCC-GASCO-P5279-4232-2326 | 2017-07-10 | T-X-C-5279-2028 | 3 | 2017-07-05 | T-NPCC-LOC-P5279-4232-0115 | 2017-07-09 | 1393_162542_DRS0125 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
23 | LOADING ARRANGEMENT FOR SLEEPERS ON CARGO BARGES. | 4232-NN-1024 | GD-100-A3-Z-5-71179 | 0 | 2 | 2017-01-01
24 | LOADING ARRANGEMENT FOR MATTRESSES ON CARGO BARGES. | 4232-NN-1025 | GD-100-A3-Z-5-71180 | 0 | 2 | 2017-01-05
25 | SHORE PULL ARRANGEMENT FOR 42" GAS PIPELINE @ RAS AL QILAE | 4232-NN-1026 | GD-100-A3-Z-5-71181 | 0 | 2 | 2016-10-25 | 2017-02-28 | CSE-OF-4232-024 | 2017-03-01 | T-NPCC-GASCO-P5279-4232-1765 | 2017-03-21 | T-X(C)-5279-1592 | 2 | 2017-03-01 | T-NPCC-LOC-P5279-4232-0049 | 2017-03-02 | 1393_153109_DRS0058 | 3 | LOC APPROVED CLIENT COMMENTED
|  |  |  | 0A | 2 |  | 2017-06-07 | CSE-OF-4232-056 | 2017-06-08 | T-NPCC-GASCO-P5279-4232-2235 | 2017-06-28 | T-X-C-5279-1990 | 2 | 2017-06-08 | T-NPCC-LOC-P5279-4232-0109 | 2017-06-18 | 1393_160860_DRS0113 | 3 | LOC APPROVED CLIENT COMMENTED
|  |  |  | 0B | 2 |  |  | NOT ISSUED FROM OFFSHORE | 2017-09-12 | T-NPCC-GASCP-P5279-4232-2586 | 2017-09-17 | T-X-C-5279-2201 | 3 | 2017-09-11 | T-NPCC-LOC-P5279-4232-0164 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
26 | SHORE PULL ARRANGEMENT FOR 42" GAS PIPELINE @ DAS ISLAND | 4232-NN-1027 | GD-100-A3-Z-5-71182 | 0 | 2 | 2016-09-20 | 2017-02-28 | CSE-OF-4232-024 | 2017-03-01 | T-NPCC-GASCO-P5279-4232-1729 | 2017-03-21 | T-X(C)-5279-1591 | 3 | 2017-03-01 | T-NPCC-LOC-P5279-4232-0047 | 2017-03-02 | 1393_153108_DRS0057 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2017-05-22 | CSE-OF-4232-052 | 2017-05-25 | T-NPCC-GASCO-P5279-4232-2155 | 2017-05-30 | T-X-C-5279-1896 | 3 | 2017-05-25 | T-NPCC-LOC-P5279-4232-0104 | 2017-06-18 | 1393_159685_DRS0110 | 3 | CLIENT & LOC APPROVED
27 | DETAIL OF TEMPORARY PIG LAUNCHER / RECEIVER FOR 42" IGD-E OFFSHORE GAS P/L DAS ISLAND TO RAS AL QILA | 4232-NN-1028 | GD-100-A3-Z-5-71183 | 0 | 2 | 2017-09-15 | 2017-10-02 | CSE-OF-4232-097
28 | LIFTING ARRANGMENT FOR SLEEPERS INSTALLATION | 4232-NN-1029 | GD-100-A3-Z-5-71184 | 0 | 2 | 2016-12-15
29 | LIFTING ARRANGEMENT FOR MATTRESSES INSTALLATION | 4232-NN-1030 | GD-100-A3-Z-5-71185 | 0 | 2 | 2016-12-15
30 | EMERGENCY HEAD DETAILS FOR 42"x33 THK. IGD-E OFFSHORE GAS PIPELINE DAS ISLAND TO RAS AL QILA | 4232-NN-1031 | GD-100-A3-Z-5-71186 |  |  | 2016-11-24
31 | TYPICAL LIFTING AND INSTALLATION OF MATTRESS BY CRESTA ATHENA VESSEL | 4232-NN-1032 | GD-100-A3-Z-5-71187 | 0 | 2 | 2016-11-24 | 2016-11-28 | CSE-OF-4232-001 | 2016-12-07 | T-NPCC-GASCO-P5279-4232-1246 | 2016-12-26 | T-X(C)-5276-1193 | 2 | [5 empty] | CLIENT COMMENTED
|  |  |  | 0A | 1 |  | 2017-01-03 | CSE-OF-4232-005 | 2017-02-15 | T-NPCC-GASCO-P5279-4232-1411 | 2017-03-02 | T-X(C)-5279-1479 | 2 | 2017-02-20 | T-NPCC-LOC-P5279-4232-0014 | 2017-02-27 | 1393_152619_DRS0045 | 2 | CLIENT & 'LOC COMMENTED
|  |  |  | 0B | 1 |  | 2017-03-20 | CSE-OF-4232-020 | 2017-03-25 | T-NPCC-GASCO-P5279-4232-1691 | 2017-04-18 | T-X-C-5279-1758 | 3 | 2017-03-25 | T-NPCC-LOC-P5279-4232-0040 | 2017-03-28 | 1393_155100_DRS0072 | 2 | CLIENT APPROVED 'LOC COMMENTED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
32 | TYPICAL SHIFTING OF CONCRETE SLEEPER BY CRESTA ATHENA VESSEL | 4232-NN-1033 | GD-100-A3-Z-5-71188 | 0 | 2 | 2016-11-24 | 2016-11-28 | CSE-OF-4232-001 | 2016-12-07 | T-NPCC-GASCO-P5279-4232-1246 | 2016-12-26 | T-X(C)-5276-1193 | 2 | [5 empty] | CLIENT COMMENTED
|  |  |  | 0A | 1 |  | 2017-01-03 | CSE-OF-4232-005 | 2017-02-26 | T-NPCC-GASCO-P5279-4232-1689 | 2017-03-15 | T-X(C)-5279-1560 | 3 | 2017-02-26 | T-NPCC-LOC-P5279-4232-0039 | 2017-02-27 | 1393_152814_DRS0044 | 2 | LOC COMMENTED CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
33 | EMERGENCY HEAD DETAILS FOR 42"x 33.00 THK. IGD-E OFFSHORE GAS PIPELINE DAS ISLAND TO RAS AL QILA | 4232-NN-1034 | GD-100-A3-Z-5-71189 | 0 | 3 |  | 2017-04-30 | CSE-OF-4232-044 | 2017-05-30 | T-NPCC-GASCO-P5279-4232-2066 |  |  |  | 2017-05-30 | T-NPCC-LOC-P5279-4232-0091 | 2017-08-15 | 1393_164488_DRS0144 | INFO
34 | LOADING ARRG'T & SEAFASTENING DETAILS OF CONCRETE MATTRESS & R.C.C SLEEPERS @ SEAWAYS-17 (TRIP-1) | 4232-NN-1035 | GD-100-A3-Z-5-72059 | 0 | 2 |  | 2017-01-25 | CSE-OF-4232-014 | 2017-01-26 | T-NPCC-GASCO-P5279-4232-1489 | 2017-02-19 | T-X(C)-5279-1416 | 3 | 2017-01-26 | T-NPCC-LOC-P5279-4232-0024 | 2017-01-26 | 1393_151806_DRS0039 | 3 | LOC & CLIENT APPROVED
|  |  |  | 0A | 1 |  | 2017-02-20 | CSE-OF-4232-021 | 2017-02-26 | T-NPCC-GASCO-P5279-4232-1692 | 2017-03-15 | T-X(C)-5279-1561 | 3 | 2017-02-26 | T-NPCC-LOC-P5279-4232-0041 | 2017-02-27 | 1393_152818_DRS0043 | 3 | LOC & CLIENT APPROVED
|  |  |  | 0B | 1 |  | 2017-03-16 | CSE-OF-4232-028 | 2017-03-16 | T-NPCC-GASCO-P5279-4232-1858 |  |  |  | 2017-03-16 | T-NPCC-LOC-P5279-4232-0060
|  |  |  | 0C | 1 |  | 2017-03-20 | CSE-OF-4232-030 | 2017-03-21 | T-NPCC-GASCO-P5279-4232-1885 | 2017-04-25 | T-X-C-5279-1775 | 3 | 2017-03-21 | T-NPCC-LOC-P5279-4232-0064 | 2017-03-21 | 1393_154662_DRS0064 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
35 | EMERGENCY HEAD DETAILS FOR 42"x30.18 THK. IGD-E OFFSHORE GAS PIPELINE DAS ISLAND TO RAS AL QILA | 4232-NN-1036 | GD-100-A3-Z-5-72347 | 0 | 3 |  | 2017-04-30 | CSE-OF-4232-044 | 2017-05-30 | T-NPCC-GASCO-P5279-4232-2065 |  |  |  | 2017-05-30 | T-NPCC-LOC-P5279-4232-0090 | 2017-08-15 | 1393_164487_DRS0145 | INFO
36 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-82 (TRIP-16) | 4232-NN-1037 | GD-100-A3-Z-5-72224 | 0 | 2 |  | 2017-07-02 | CSE-OF-4232-062 | 2017-07-04 | T-NPCC-GASCO-P5279-4232-2338 | 2017-07-10 | T-X-C-5279-2029 | 3 | 2017-07-05 | T-NPCC-LOC-P5279-4232-0118 | 2017-07-05 | 1393_162543_DRS0127 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
37 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-81 (TRIP-17) | 4232-NN-1038 | GD-100-A3-Z-5-72225 | 0 | 2 |  | 2017-07-05 | CSE-OF-4232-063 | 2017-07-06 | T-NPCC-GASCO-P5279-4232-2345 | 2017-07-12 | T-X-C-5279-2042 | 3 | 2017-07-06 | T-NPCC-LOC-P5279-4232-0120 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
38 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ SEAWAYS-17 (TRIP-18) | 4232-NN-1039 | GD-100-A3-Z-5-72226 | 0 | 2 |  | 2017-07-09 | CSE-OF-4232-064 | 2017-07-11 | T-NPCC-GASCO-P5279-4232-2359 | 2017-07-12 | T-X-C-5279-2043 | 3 | 2017-07-11 | T-NPCC-LOC-P5279-4232-0124 | 2017-07-12 | 1393_163132_DRS0129 | 3 | LOC & CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
39 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-82 (TRIP-19) | 4232-NN-1040 | GD-100-A3-Z-5-72227 | 0 | 2 |  | 2017-07-11 | CSE-OF-4232-065 | 2017-07-13 | T-NPCC-GASCO-P5279-4232-2363 | 2017-07-20 | T-X-C-5279-2064 | 3 | 2017-07-13 | T-NPCC-LOC-P5279-4232-0125 | 2017-08-15 | 1393_163408_DRS0146 | 3 | CLIENT & LOC APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
40 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-81 (TRIP-20) | 4232-NN-1041 | GD-100-A3-Z-5-72228 | 0 | 2 |  | 2017-07-11 | CSE-OF-4232-066 | 2017-07-13 | T-NPCC-GASCO-P5279-4232-2369 | 2017-07-20 | T-X-C-5279-2065 | 3 | 2017-07-13 | T-NPCC-LOC-P5279-4232-0126 | 2017-08-15 | 1393_163404_DRS0147 | 3 | CLIENT & LOC APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
41 | TYPICAL LIFTING & INSTALLATION OF STEEL SLEEPERS BY NPCC CREST ATHENA VESSEL | 4232-NN-1042 | GD-100-A3-Z-5-72229 | 0 | 2 |  | 2017-09-27 | CSE-OF-4232-095 | 2017-09-28 | T-NPCC-GASCO-P5279-4232-2648 | 2017-10-25 | T-X(C)-5279-2305 | 2 | 2017-09-28 | T-NPCC-LOC-P5279-4232-0187 | 2017-09-28 | 1393_167995_DRS0208 | 2 | CLIENT & LOC COMMENTED
|  |  |  | 1 | 1 |  | 2018-06-20 | CSE-OF-4232-120 | 2018-06-20 | T-NPCC-GASCO-P5279-4232-3199
42 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C. PIPES @ AL-JABER-34 (TRIP-21) | 4232-NN-1043 | GD-100-A3-Z-5-72411 | 0 | 2 |  | 2017-07-16 | CSE-OF-4232-067 | 2017-07-18 | T-NPCC-GASCO-P5279-4232-2392 | 2017-07-23 | T-X-C-5279-2069 | 3 | 2017-07-18 | T-NPCC-LOC-P5279-4232--0130 | 2017-07-19 | 1393_163573_DRS0136 | 3 | CLIENT & LOC APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
43 | TYPICAL LIFTING & INSTALLATION OF 42" PIPE JOINT VALVE | 4232-NN-1044 | GD-100-A3-Z-5-72412 | 0 | 2 |  | TRSL CANCELLED
44 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-82 (TRIP-22) | 4232-NN-1045 | GD-100-A3-Z-5-72413 | 0 | 2 |  | 2017-07-24 | CSE-OF-4232-070 | 2017-07-26 | T-NPCC-GASCO-P5279-4232-2419 | 2017-07-31 | T-X-C-5279-2087 | 3 | 2017-07-26 | T-NPCC-LOC-P5279-4232-0136 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
45 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-81 (TRIP-23) | 4232-NN-1046 | GD-100-A3-Z-5-72414 | 0 | 2 |  | 2017-07-30 | CSE-OF-4232-071 | 2017-08-01 | T-NPCC-GASCO-P5279-4232-2447 | 2017-08-13 | T-X(C)-5279-2112 | 3 | 2017-07-31 | T-NPCC-LOC-P5279-4232-0137 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
46 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ JABER-34 (TRIP-24) | 4232-NN-1047 | GD-100-A3-Z-5-72415 | 0 | 2 |  | 2017-07-31 | CSE-OF-4232-072 | 2017-08-01 | T-NPCC-GASCO-P5279-4232-2448 | 2017-08-13 | T-X-C-5279-2113 | 3 | 2017-08-01 | T-NPCC-LOC-P5279-4232-0138 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
47 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-82 (TRIP-25) | 4232-NN-1048 | GD-100-A3-Z-5-72416 | 0 | 2 |  | 2017-08-08 | CSE-OF-4232-079 | 2017-08-21 | T-NPCC-GASCO-P8279-4232-2477 | 2017-08-27 | T-X(C)-5279-2141 | 3 | 2017-08-08 | T-NPCC-LOC-P5279-4232-0148 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
48 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ GAC-81 (TRIP-26) | 4232-NN-1049 | GD-100-A3-Z-5-72417 | 0 | 2 |  | 2017-08-10 | CSE-OF-4232-080 | 2017-08-21 | T-NPCC-GASCO-P8279-4232-2493 | 2017-08-27 | T-X(C)-5279-2142 | 3 | 2017-08-10 | T-NPCC-LOC-P5279-4232-0151 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
49 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @ JABER-34 (TRIP-27) | 4232-NN-1050 | GD-100-A3-Z-5-72418 | 0 | 2 |  | 2017-08-22 | CSE-OF-4232-081 | 2017-08-31 | T-NPCC-GASCO-P5279-4232-2518 | 2017-09-06 | T-X(C)-5279-2163 | 3 | 2017-08-31 | T-NPCC-LOC-P5279-4232-0152 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
50 | TYPICAL LIFTING & OFFLOADING OF STEEL SLEEPERS BY DEMAG-CC-1800-1 | 4232-NN-1051 | GD-100-A3-Z-5-72419 |  |  | REY
51 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @GAC-82 (TRIP-28) | 4232-NN-1052 | GD-100-A3-Z-5-72420 | 0 | 2 |  | 2017-08-27 | CSE-OF-4232-083 | 2017-09-05 | T-NPCC-GASCO-P5279-4232-2543 | 2017-09-14 | T-X(C)-5279-2194 | 3 | 2017-09-05 | T-NPCC-LOC-P5279-4232-0156 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
52 | LOADING ARRGT & SEAFASTENING DETAILS OF C.C PIPES @GAC-81 (TRIP-30) | 4232-NN-1053 | GD-100-A3-Z-5-72461 | 0 | 2 |  | 2017-09-13 | CSE-OF-4232-089 | 2017-09-14 | T-NPCC-GASCO-P5279-4232-2593 | 2017-09-19 | T-X(C)-5279-2215 | 3 | 2017-09-14 | T-NPCC-LOC-P5279-4232-0168 |  |  |  | CLIENT APPROVED
|  |  |  | 1 | 1 |  | 2018-02-13 | CSE-OF-4232-0108 | 2018-02-14 | T-NPCC-GASCO-P5279-4232-3055 |  |  |  | 2018-02-14 | T-NPCC-LOC-P5279-4232-0237
53 | LOADING ARRG’T & SEAFASTENING DETAILS OF C.C PIPES @ (TRIP-31) WITH BALLAST PLAN | 4232-NN-1054 | GD-100-A3-Z-5-72462 | 0 | 2 |  | 2017-09-17 | CSE-OF-4232-091 | [5 empty] | 2017-09-17 | T-NPCC-LOC-P5279-4232-0172 | 2017-09-17 | 1393_167140_DRS0162 | 3 | LOC APPROVED
54 | LOADING ARRG’T & SEAFASTENING DETAILS OF C.C PIPES @ AL-JABER-35 (TRIP-32) WITH BALLAST PLAN | 4232-NN-1055 | GD-100-A3-Z-5-72463 | 0 | 2 |  | 2017-09-19 | CSE-OF-4232-092 | 2017-09-21 | T-NPCC-GASCO-P5279-4232-2611 |  |  |  | 2017-09-21 | T-NPCC-LOC-P5279-4232-0175 | 2017-09-20 | 1393_167379_DRS0168 | 3 | LOC APPROVED
55 | LIFTING & INSTALLATION OF 30" RISER BY SEP-250 | 4232-NN-1056 | GD-100-A3-Z-5-72464 | 0 | 2 |  | 2017-10-09 | CSE-OF-4232-101 | 2017-10-11 | T-NPCC-GASCO-P5279-4232-2710 | 2017-10-19 | T-X(C)-5279-2289 | 2 | [5 empty] | CLIENT COMMENTED
|  |  |  | 0A | 1 |  | 2017-10-26 | CSE-OF-4232-104 | 2017-10-31 | T-NPCC-GASCO-P5279-4232-2815 | 2017-11-01 | T-X(C)-5279-2333 | 3 | 2017-10-31 | T-NPCC-LOC-P5279-4232-0204 | 2017-10-31 | 1393_169443_DRS0249 | 3 | CLIENT APPROVED LOC APPROVED
|  |  |  | 1 | 1 |  | 2017-11-07 | CSE-OF-4232-108 | 2017-11-08 | T-NPCC-GASCO-P5279-4232-2849 |  |  |  | 2017-11-08 | L-NPCC-LOC-P5279-4232-0216 | 2017-11-08 | 1393_169932_DRS0255 | 3 | LOC APPROVED
56 | TYPICAL LIFTING & INSTALLATION OF STEEL SLEEPER ON SUPPLY VESSEL BY NPCC CREST ATHENA VESSEL | 4232-NN-1057 | GD-100-A3-Z-5-72465 |  |  | CDG
57 |  | 4232-NN-1058 | USED IN DOC NAVAL
58 |  | 4232-NN-1059 | USED IN DOC PIPELINE
59 |  | 4232-NN-1060 | USED IN DOC PIPELINE
60 |  | 4232-NN-1061 | GD-100-A3-Z-5-72469
61 |  | 4232-NN-1062 | GD-100-A3-Z-5-72470
62 |  | 4232-NN-1063 | GD-100-A3-Z-5-72471
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION; (4) REJECTED
GASCO CODE : (1) REJECTED; (2) COMMENTS AS NOTED; (3) NO COMMENTS; (4) INFORMATION ONLY
LOC APPROVAL CODE : (1) THE COMMENT HAS BEEN SATISFACTORILY CLOSED; (2) THE COMMENT REQUIRES ACTION; (3) AN OBSERVATION THAT REQUIRES NO ACTION