## Pipeline
LIFE EXTENSION OF WELL PLATFORM PROJECT (TENDER-3) Contract No. : MR/ES/MM/LEWPP (TENDER-3)/01/P851C16001/2016
|  | Date : | #REF!
|  | Revision : | #REF! | NPCC Project No. 6214
|  | NPCC Doc No.: | #REF!
OFFSHORE DOCUMENTS
SR. NO. | NPCC PROJECT DOCUMENT NUMBER |  | DESCRIPTION |  | REV NO. | INCHARGE | SCHEDULE FOR SUBMISSION | OIL AND NATURAL GAS CORPORATION (ONGC) LIMITED | [5 empty] | MARINE WARRANTY SURVEYOR | [5 empty] | REMARKS
[8 empty] | DOC. CLASS | SUBMISSION STATUS |  | APPROVAL STATUS |  |  | MWS REVIEW REQ'D | SUBMISSION STATUS |  | APPROVAL STATUS
[9 empty] | REF | DATE | REF | DATE | STATUS |  | REF | DATE | REF | DATE | STATUS
A. | PIPELINE DOCUMENTS
1 | 6214-NN-RP-XXX |  |  |  | 0 |  |  | 2
2 |  |  |  |  | 0 |  |  | 2
3 |  |  |  |  | 0 |  |  | 2
4 |  |  |  |  | 0 |  |  | 2
5 |  |  |  |  | 0 |  |  | 2
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0

## Naval Marine
LIFE EXTENSION OF WELL PLATFORM PROJECT (TENDER-3) Contract No. : MR/ES/MM/LEWPP (TENDER-3)/01/P851C16001/2016
|  | Date : | #REF!
|  | Revision : | #REF! | NPCC Project No. 6214
|  | NPCC Doc No.: | #REF!
OFFSHORE DOCUMENTS
SR. NO. | NPCC PROJECT DOCUMENT NUMBER |  | DESCRIPTION |  | REV NO. | SCHEDULE FOR SUBMISSION |  | CSE TO PMT |  | OIL AND NATURAL GAS CORPORATION (ONGC) |  |  |  |  | MARINE WARRANTY SURVEYOR | [5 empty] | REMARKS
[7 empty] | DOC. CLASS | DATE | REF | PMT TO CLIENT |  | APPROVAL STATUS |  |  | MWS REVIEW REQ'D | SUBMISSION STATUS |  | APPROVAL STATUS
[10 empty] | REF | DATE | REF | DATE | STATUS |  | REF | DATE | REF | DATE | STATUS
B | NAVAL MARINE DOCUMENTS
1 | 6214-ZZ-CL-101 |  | MOORING ANALYSIS FOR HLS-2000 DURING REMOVAL OF EXISTING DECK AND INSTALLATION OF NEW DECK AT WI-8 LOCATION |  | 0 |  | 2 | 02-10-2017 | CSE-OF-015 | T-0451 | 03-10-2017 |  |  |  |  | T-0022 | 02-10-2017
[5 empty] | 1 |  | 2 | 17-10-2017 | CSE-OF-017 | T-0479 | 17-10-2017
[5 empty] | 2 |  | 2 | 03-11-2017 | CSE-OF-019 | T-0523 | 05-11-2017 | EMAIL | 2017-11-14 | INF.
2 | 6214-ZZ-CL-102 |  | MOORING ANALYSIS FOR HLS-2000 DURING REMOVAL OF EXISTING DECK AND INSTALLATION OF NEW DECK AT WI-9 LOCATION |  | 0 |  | 2 | 02-10-2017 | CSE-OF-016 | T-0453 | 2017-10-05 | ONGC---- | 2017-10-29 | COMMENTS
[5 empty] | 1 |  | 2 | 01-11-2017 | CSE-OF-018 | T-0516 | 05-11-2017
[5 empty] | 2 |  | 2 | 15-11-2017 | CSE-OF-020 | T-0540 | 2017-11-16
3 | 6214-ZZ-CL-103 |  | MOORING ANALYSIS FOR HLS-2000 DURING REMOVAL OF EXISTING DECK AND INSTALLATION OF NEW DECK AT EB LOCATION |  | 0 |  | 2 | 2017-12-03 | CSE-OF-021 | T-0566 | 2017-12-04
4 | 6214-ZZ-CL-104 |  | MOORING ANALYSIS FOR HLS-2000 DURING REMOVAL OF EXISTING DECK AND INSTALLATION OF NEW DECK AT IN LOCATION |  | 0 |  | 2 | 2017-12-05 | CSE-OF-022 | T-0568 | 2017-12-05
5 | 6214-ZZ-CL-105 |  | MOORING ANALYSIS FOR HLS-2000 DURING REMOVAL OF EXISTING DECK AND INSTALLATION OF NEW DECK AT WI-2 LOCATION | SPARE | 0 |  | 2 | 2018-01-28 | CSE-OF-026 | T-0677 | 2018-01-30 | E-MAIL | 2018-01-30 | NO COMMENTS
6 | 6214-ZZ-CL-106 |  | MOORING ANALYSIS FOR HLS-2000 DURING REMOVAL OF EXISTING DECK AND INSTALLATION OF NEW DECK AT NK LOCATION | SPARE | 0 |  | 2 | 29-01-2018 | CSE-OF-028 | T-0689 | 2018-02-04 | E-MAIL | 2018-02-20 | INFOR. | [6 empty] | BEFORE NI LOCATION
7 | 6214-ZZ-CL-107 |  | MOORING ANALYSIS FOR HLS-2000 DURING REMOVAL OF EXISTING DECK AND INSTALLATION OF NEW DECK AT NT LOCATION | SPARE | 0 |  | 2 | 25-03-2018 | CSE-OF-033 | T-0775 | 2018-03-26 | E-MAIL | 2018-03-28 | INFOR.
8 | 6214-ZZ-CL-108 |  | MOORING ANALYSIS FOR HLS-2000 DURING REMOVAL OF EXISTING DECK AND INSTALLATION OF NEW DECK AT NJ LOCATION | SPARE | 0 |  | 2 | 22-02-2018 | CSE-OF-029 | T-0729 | 25-02-2018 | E-MAIL | 2018-03-14 | Comments
9 | 6214-ZZ-CL-109 |  | MOORING ANALYSIS FOR HLS-2000 DURING REMOVAL OF EXISTING DECK AND INSTALLATION OF NEW DECK AT WI-7 LOCATION | SPARE | 0 |  | 2 | 22-02-2018 | CSE-OF-029 | T-0730 | 25-02-2018 | E-MAIL | 2018-03-21 | INFOR.
10 | 6214-ZZ-CL-110 |  | MOORING ANALYSIS FOR HLS-2000 DURING REMOVAL OF EXISTING DECK AND INSTALLATION OF NEW DECK AT EE LOCATION |  | 0 |  | 2 | 25-03-2018 | CSE-OF-033 | T-0776 | 2018-03-26 | E-MAIL | 2018-03-28 | INFOR.
11 | 6214-ZZ-CL-111 |  | SPARE |  | 0
12 | 6214-ZZ-CL-112 |  | SPARE |  | 0
13 | 6214-ZZ-CL-113 |  | SPARE |  | 0
14 | 6214-ZZ-CL-114 |  | SPARE |  | 0
15 | 6214-ZZ-CL-115 |  | SPARE |  | 0
16 | 6214-ZZ-CL-116 |  | SPARE |  | 0
17 | 6214-ZZ-CL-117 |  | SPARE |  | 0
18 | 6214-ZZ-CL-118 |  | SPARE |  | 0
19 | 6214-ZZ-CL-119 |  | SPARE |  | 0
20 | 6214-ZZ-CL-120 |  | SPARE |  | 0
21 | 6214-ZZ-CL-121 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PRE ENGINEERING SURVEY AT NJ |  | 0 |  | 2 | 16-02-2017 | CSE-OF-001 | T-0090 | 2017-02-19 | IRS | 03-03-2017 | comments
[5 empty] | 1 |  | 2 | 05-03-2017 | CSE-OF-003 | T-0106 | 2017-03-11
22 | 6214-ZZ-CL-122 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PRE ENGINEERING SURVEY AT WI-8 |  | 0 | Remarks | 2 | 30-03-2017 | CSE-OF-013 | [11 empty] | DOC. WITH PMT (HOLDING)
23 | 6214-ZZ-CL-123 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PRE ENGINEERING SURVEY AT WI-9 |  | 0 | Remarks | 2 | 23-03-2017 | CSE-OF-010 | [11 empty] | DOC. WITH PMT (HOLDING)
24 | 6214-ZZ-CL-124 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PRE ENGINEERING SURVEY AT IN |  | 0 | Remarks | 2 | 29-03-2017 | CSE-OF-012 | [11 empty] | DOC. WITH PMT (HOLDING)
25 | 6214-ZZ-CL-125 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PRE ENGINEERING SURVEY AT EE |  | 0 | Remarks | 2 | 06-04-2017 | CSE-OF-014 | [11 empty] | DOC. WITH PMT (HOLDING)
26 | 6214-ZZ-CL-126 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PRE ENGINEERING SURVEY AT EB |  | 0 |  | 2 | 26-03-2017 | CSE-OF-011 | T-0149 | 2017-03-26
27 | 6214-ZZ-CL-127 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PRE ENGINEERING SURVEY AT WI-7 |  | 0 | Remarks | 2 | 30-03-2017 | CSE-OF-013 | [11 empty] | DOC. WITH PMT (HOLDING)
28 | 6214-ZZ-CL-128 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PRE ENGINEERING SURVEY AT NK |  | 0 |  | 2 | 21-02-2017 | CSE-OF-002 | T-0093 | 2017-02-21
[5 empty] | 1 |  | 2 | 12-03-2017 | CSE-OF-004 | T-0111 | 13-03-2017
[5 empty] | 2 |  | 2 | 15-03-2017 | CSE-OF-005 | T-0123 | 15-03-2017
[5 empty] | 3 |  | 2 | 21-03-2017 | CSE-OF-008 | T-0140 | 21-03-2017
29 | 6214-ZZ-CL-129 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PRE ENGINEERING SURVEY AT NT |  | 0 |  | 2 | 05-03-2017 | CSE-OF-003 | T-0107 | 2017-03-11
[5 empty] | 1 |  | 2 | 19-03-2017 | CSE-OF-007 | T-0136 | 19-03-2017
[5 empty] | 2 |  | 2 | 21-03-2017 | CSE-OF-009 | T-0145 | 21-03-2017
30 | 6214-ZZ-CL-130 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PRE ENGINEERING SURVEY AT WI-2 |  | 0 |  | 2 | 16-03-2017 | CSE-OF-006 | T-0135 | 19-03-2017
31 | 6214-ZZ-CL-131 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PREPARATORY WORKS, DECOMMISSIONING, HOOK UP WORKS AND COMMISSIONING AT WI-8 |  | 0 |  | 2 | 20-12-2017 | CSE-OF-023 | T-0595 | 2017-12-21
32 | 6214-ZZ-CL-132 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PREPARATORY WORKS, DECOMMISSIONING, HOOK UP WORKS AND COMMISSIONING AT WI-9 |  | 0 |  | 2 | 21-12-2017 | CSE-OF-024 | T-0596 | 2017-12-21
33 | 6214-ZZ-CL-133 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PREPARATORY WORKS, DECOMMISSIONING, HOOK UP WORKS AND COMMISSIONING AT EB |  | 0 | Remarks | 2 | 10-01-2018 | CSE-OF-025 | [6 empty] | T-0304 | 2018-02-04 |  |  |  | DOC. SENT TO MCE ONLY
34 | 6214-ZZ-CL-134 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PREPARATORY WORKS, DECOMMISSIONING, HOOK UP WORKS AND COMMISSIONING AT IN |  | 0 | Remarks | 2 | 10-01-2018 | CSE-OF-025 | [6 empty] | T-0304 | 2018-02-04 |  |  |  | DOC. SENT TO MCE ONLY
35 | 6214-ZZ-CL-135 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PREPARATORY WORKS, DECOMMISSIONING, HOOK UP WORKS AND COMMISSIONING AT WI-2 |  | 0 |  | 2 | 29-01-2018 | CSE-OF-027 | T-0680 | 2018-01-30 | EMAIL | 2018-02-20 | INFOR
36 | 6214-ZZ-CL-136 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PREPARATORY WORKS, DECOMMISSIONING, HOOK UP WORKS AND COMMISSIONING AT NK |  | 0 |  | 2 | 29-01-2018 | CSE-OF-028 | T-0690 | 2018-02-04 | EMAIL | 2018-02-19 | INFOR.
37 | 6214-ZZ-CL-137 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PREPARATORY WORKS, DECOMMISSIONING, HOOK UP WORKS AND COMMISSIONING AT NJ |  | 0 |  | 2 | 2018-03-04 | CSE-OF-031 | T-0752 | 2018-03-08
38 | 6214-ZZ-CL-138 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PREPARATORY WORKS, DECOMMISSIONING, HOOK UP WORKS AND COMMISSIONING AT WI-7 |  | 0 |  | 2 | 22-02-2018 | CSE-OF-030 | T-0731 | 25-02-2018 | EMAIL | 2018-03-14 | Comments
[5 empty] | CRS |  |  | 2018-03-22 | CSE-OF-032 | T-0768 | 24-03-2018 | EMAIL | 2018-04-09 | INFOR.
39 | 6214-ZZ-CL-139 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PREPARATORY WORKS, DECOMMISSIONING, HOOK UP WORKS AND COMMISSIONING AT NT |  | 0 |  | 2 | 25-03-2018 | CSE-OF-033 | T-0777 | 2018-03-26 | E-MAIL | 28/03/2018 03/04/2018 | Comments
[5 empty] | CRS |  |  | 05-04-2018 | CSE-OF-035 | T-0813 | 2018-04-09 | E-MAIL | 2018-04-25 | INFOR.
40 | 6214-ZZ-CL-140 |  | MOORING ANALYSIS FOR HAL SUPPORTER DURING PREPARATORY WORKS, DECOMMISSIONING, HOOK UP WORKS AND COMMISSIONING AT EE |  | 0 |  | 2 | 25-03-2018 | CSE-OF-033 | T-0778 | 2018-03-26 | E-MAIL | 28/03/2018 03/04/2018 | Comments
[5 empty] | CRS |  |  | 03-04-2018 | CSE-OF-034 | T-0811 | 2018-04-05 | E-MAIL | 2018-04-25 | INFOR.
41

## Drawings
LIFE EXTENSION OF WELL PLATFORM PROJECT (TENDER-3) Contract No. : MR/ES/MM/LEWPP (TENDER-3)/01/P851C16001/2016
|  | Date : | #REF!
|  | Revision : | #REF! | NPCC Project No. 6214
|  | NPCC Doc No.: | #REF!
OFFSHORE DOCUMENTS
SR. NO. | NPCC PROJECT DOCUMENT NUMBER |  | DESCRIPTION |  | REV NO. | INCHARGE | SCHEDULE FOR SUBMISSION | OIL AND NATURAL GAS CORPORATION (ONGC) LIMITED | [5 empty] | MARINE WARRANTY SURVEYOR | [5 empty] | REMARKS
[8 empty] | DOC. CLASS | SUBMISSION STATUS |  | APPROVAL STATUS |  |  | MWS REVIEW REQ'D | SUBMISSION STATUS |  | APPROVAL STATUS
[9 empty] | REF | DATE | REF | DATE | STATUS |  | REF | DATE | REF | DATE | STATUS
C | NAVAL MARINE DOCUMENTS
1 | 6214-NN-XXX |  |  |  | 0 |  |  | 2
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20