## PIPELINE & CABLE
|  | LTA FOR OFFSHORE FACILITIES : CRPO FOR STP-21, SG3-AUX UPGRADE, ASSOCIATED PIPELINES & POWER CABLES (OOK) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | NPCC PROJECT NO. 7243 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 2018-07-15
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPELINE STACKING ANALYSIS REPORT | 7243-7244-NN-RP-001 | A | 2 |  | 2019-03-04 | CSE-OF-7243-007 | 2019-03-06 | 7243-7244-NPCC-T-3797 | 2019-03-11 | FD-T-3309-19 | CODE-3
|  |  | B | 1 |  | 2019-03-13 | CSE-OF-7243-011 | 2019-03-14 | 7243-7244-NPCC-T-3866 | 2019-03-19 | FD-T-3930-19 | CODE-2
|  |  | C | 1 |  | 2019-03-20 | CSE-OF-7243-012 | 2019-03-26 | 7243-7244-NPCC-T-3977 | 2019-03-31 | FD-T-4546-19 | CODE-1
|  |  | 00 | 1 |  | 2019-11-04 | CSE-OF-7243-053 | 2019-11-04 | 7243-7244-NPCC-T-5059
2 | INSTALLATION ANALYSIS REPORT FOR TL-14 30" FROM STP-21 TO LANDFALL | 7243-7244-NN-RP-002 | A | 2 |  | 2019-01-10 | CSE-OF-7243-004 | 2019-01-10 | 7243-7244-NPCC-T-3418 | 2019-02-07 | FD-T-1842-19 | CODE-2
|  |  | B | 1 |  | 2019-03-03 | CSE-OF-7243-006 | 2019-03-06 | 7243-7244-NPCC-T-3796 | 2019-04-01 | FD-T-4584-19 | CODE-1
|  |  | 00 | 1 |  | 2019-05-13 | CSE-OF-7243-019 | 2019-05-14 | 7243-7244-NPCC-T-4426
|  |  | 00A | 1 |  | 2019-08-28 | CSE-OF-7243-039 | 2019-08-28 | 7243-7244-NPCC-T-4897
|  |  | 00B | 1 |  | 2019-09-16 | CSE-OF-7243-045 | 2019-09-18 | 7243-7244-NPCC-T-4937
|  |  | 00C | 1 |  | 2019-09-24 | CSE-OF-7243-046 | 2019-10-06 | 7243-7244-NPCC-T-4960
3 | INSTALLATION ANALYSIS REPORT FOR 16" CRA CLADDED PIPELINE FROM SGOSP-3-AUX to STP-21 | 7243-7244-NN-RP-003 | A | 2 |  | 2019-05-23 | CSE-OF-7243-021 | 2019-05-23 | 7243-7244-NPCC-T-4479 | 2019-06-24 | FD-T-8566-19 | CODE-2
|  |  | B | 1 |  | 2019-07-09 | CSE-OF-7243-033 | 2019-07-10 | 7243-7244-NPCC-T-4747 | 2019-10-16 | FD-T-13862-19 | CODE-4
|  |  | 00 | 1 |  | 2020-03-01 | CSE-OF-7243-065 | 2020-03-02 | 7243-7244-NPCC-T-5253
4 | SUBSEA COMPOSITE POWER CABLE LAYING ANALYSIS REPORT | 7243-7244-NN-RP-004 | A | 2 |  | 2019-06-25 | CSE-OF-7243-028 | 2019-06-26 | 7243-7244-NPCC-T-4659 | 2019-07-10 | T-4597-19 | CODE-2
|  |  | B | 1 |  | 2019-07-22 | CSE-OF-7243-034 | 2019-07-22 | 7243-7244-NPCC-T-4793 | 2019-07-24 | T-4990-19 | CODE-1
|  |  | 00 | 1 |  | 2019-09-26 | CSE-OF-7243-044 | 2019-10-06 | 7243-7244-NPCC-T-4966
|  |  | 00A | 1 |  | 2019-10-10 | CSE-OF-7243-048 | 2019-10-10 | 7243-7244-NPCC-T-4996
5 | Subsea Composite Power Cable Laying Analysis Report from STP-21 to STP-18 | 7243-7244-NN-RP-005
6 | Shore pull package report for 30" from LANDFALL | 7243-7244-NN-RP-006
7 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON ALLIANZ CB-251 | 7243-7244-NN-RP-007 | A | 3 |  | 2019-04-11 | CSE-OF-7243-013 |  | NO SUBMISSION TO CLIENT
8 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES, RCC SLEEPERS & MATTRESSES ON GOGAS-255 | 7243-7244-NN-RP-008 | A | 3 |  | 2019-04-18 | CSE-OF-7243-014 |  | NO SUBMISSION TO CLIENT
9 | SEA FASTENING DESIGN REPORT FOR THE TRANSPORTATION OF CC PIPES ON ZAKHER-101.(TRIP-3) | 7243-7244-NN-RP-009 | A | 3 |  | 2019-09-09 | CSE-OF-7243-020 |  | NO SUBMISSION TO CLIENT
10 | Sea Fastening Design Report For Transportation Of RCC SLEEPERS ON (1st Cargo Barge) | 7243-7244-NN-RP-010
11 | Sea Fastening Design Report For Transportation Of RCC SLEEPERS ON (2nd Cargo Barge) | 7243-7244-NN-RP-011
12 | Sea Fastening Design Report For Transportation Of MATTRESSES ON (1ST Cargo Barge) | 7243-7244-NN-RP-012
13 | 16" Spool Lifting analysis at TP-21 | 7243-7244-NN-RP-013
14 | 12" Spool Lifting analysis at TP-21 | 7243-7244-NN-RP-014
15 | 30" Spool Lifting analysis at TP-21 | 7243-7244-NN-RP-015
16 | 16" Spool Lifting analysis at GOSP-3 | 7243-7244-NN-RP-016
17 | SEA FASTENING DESIGN REPORT FOR THE TRANSPORTATION OF CC PIPES CREST-287 (TRIP-2) | 7243-7244-NN-RP-017 | A | 3 |  | 2019-09-09 | CSE-OF-7243-023 |  | NO SUBMISSION TO CLIENT
18 | SPOOL LIFTING ANALYSIS REPORT FOR SPOOLS AT TP-21 AND GOSP-3 | 7243-7244-NN-RP-018 | A | 3 |  | 2019-07-09 | CSE-OF-7243-031 |  | NO SUBMISSION TO CLIENT
19 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS ON GOGAS-250 | 7243-7244-NN-RP-019 | 00 | 3 |  | 2019-08-07 | CSE-OF-7243-036 |  | NO SUBMISSION TO CLIENT
20 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS & MISC. ITEMS ON MICLYN-258 | 7243-7244-NN-RP-020 | 00 | 3 |  | 2019-09-03 | CSE-OF-7243-043 |  | NO SUBMISSION TO CLIENT
21 | ANALYSIS & DESIGN OF CABLE TOWER ON MILLENEUM-3 | 7243-7244-NN-RP-021 | A | 2 |  | 2019-10-09 | CSE-OF-7243-047 | 2019-10-10 | 7243-7244-NPCC-T-4995
22 | ICCP CABLE LAYING ANALYSIS REPROT | 7243-7244-NN-RP-022 | A | 2 |  | 2019-10-21 | CSE-OF-7243-050 | 2019-10-22 | 7243-7244-NPCC-T-5023 | 2019-10-29 | SMBAMPPD-T-7151-19 | REVIEWED WITH COMMENTS
|  |  | B | 1 |  | 2019-11-05 | CSE-OF-7243-052 | 2019-11-05 | 7243-7244-NPCC-T-5060 | 2019-11-14 | SMBAMPPD-T-7357-19 | APPROVED
23 | DAVIT LIFTING AND SHIFTING ANALYSIS REPORT FOR TL-14 30" PIPELINE | 7243-7244-NN-RP-023 | A | 2 |  | 2019-11-18 | CSE-OF-7243-055 | 2019-11-21 | 7243-7244-NPCC-T-5080 | 2019-12-22 | SMBAMPPD-T-8114-19 | APPROVED
24 | INSTALLATION ANALYSIS REPORT FOR TL-14 30" FROM KP12.500 TO KP 15.700 | 7243-7244-NN-RP-024 | A | 2 |  | 2020-02-13 | CSE-OF-7243-062 | 2020-03-01 | 7243-7244-NPCC-T-5254 | 2020-03-15 | SMBAMPPD-T-1556-20 | APPROVED
25 | INSTALLATION ANALYSIS REPORT FOR 16"MANIFA P/L | 7243-7244-NN-RP-025 | A | 2 |  | 2020-05-21 | CSE-OF-7243-076 |  | NO SUBMISSION TO CLIENT

## Documents - Naval & Marine
|  | LTA FOR OFFSHORE FACILITIES : CRPO FOR STP-21, SG3-AUX UPGRADE, ASSOCIATED PIPELINES & POWER CABLES (OOK) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | NPCC PROJECT NO. 7243 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (NAVAL & MARINE) | [10 empty] | DATE : |  |  |  | 2018-07-15
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | MOORING ANALYSIS DURING SHORE PULL AND PIPELAYING OF 30" TL FROM SFNY SHORE LINE TO SFNY TP-21 | 7243-7244--ZZ-CL-001 | A | 2 |  | 2019-01-30 | CSE-OF-7243-005 |  | NO SUBMISSION TO CLIENT
|  |  | 00 | 3 |  | 2019-06-12 | CSE-OF-7243-027 | 2019-06-17 | 7243-7244-NPCC-T-4604
2 | MOORING ANALYSIS DURING PIPELAYING OF 16" TIE-IN LINE FROM SFNY TP-21 TO SFNY GOSP-3 | 7243-7244-ZZ-CL-002 | 00 | 3 |  | 2019-06-10 | CSE-OF-7243-024 | 2019-06-11 | 7243-7244-NPCC-T-4557
|  |  | 01 | 3 |  | 2019-07-31 | SUBMITTED BY VENU |  | NO SUBMISSION TO CLIENT
3 | MOORING ANALYSIS DURING SFNY TP-21 JACKET INSTALLATION | 7243-7244-ZZ-CL-003 | A | 2 |  | 2018-10-25 | CSE-OF-7243-001 | 2018-11-01 | 7243-7244-NPCC-T-2958 '7243-7244-NPCC-T-3007 | 2018-11-29 | FD-T-15807-18 | 4
|  |  | 00 | 3 |  | 2019-06-10 | CSE-OF-7243-017 | 2019-06-11 | 7243-7244-NPCC-T-4556
4 | MOORING ANALYSIS DURING SFNY TP-21 DECK INSTALLATION | 7243-7244-ZZ-CL-004 | 00 | 3 |  | 2019-06-13 | CSE-OF-7243-027 | 2019-06-17 | 7243-7244-NPCC-T-4605
|  |  | 01 | 3 |  | 2019-06-26 | CSE-OF-7243-029 |  | NO SUBMISSION TO CLIENT
5 | STABILITY ANALYSIS DURING TRANSPORTATION OF C.C PIPES @ ALLIANZ CB-252 | 7243-7244-ZZ-CL-005 | A | 2 |  | 2019-05-21 | CSE-OF-7243-013 |  | NO SUBMISSION TO CLIENT
6 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES @ CREST 287 | 7243-7244-ZZ-CL-006 | 00 | 3 |  | 2019-09-09 | CSE-OF-7243-020 |  | NO SUBMISSION TO CLIENT
7 | STABILITY ANALYSIS DURING TRANSPORTATION OF CC PIPES @ ZAKHER-101 | 7243-7244-ZZ-CL-007 | 00 | 3 |  | 2019-09-09 | CSE-OF-7243-023 |  | NO SUBMISSION TO CLIENT
8 | STABILITY ANALYSIS DURING TRANSPORTATION OF RCC SLEEPERS & MATTRESSES @ GOGAS-255 | 7243-7244-ZZ-CL-008 | A | 2 |  | 2019-04-18 | CSE-OF-7243-014 |  | NO SUBMISSION TO CLIENT
9 | STABILITY ANALYSIS DURING TRANSPORTATION OF RCC SLEEPERS ON (2nd Cargo Barge) | 7243-7244-ZZ-CL-009
10 | STABILITY ANALYSIS DURING TRANSPORTATION OF MATTRESSES ON (1ST Cargo Barge) | 7243-7244-ZZ-CL-010
11 | STABILITY ANALYSIS DURING TRANSPORTATION OF SPOOLS ON GOGAS-250 | 7243-7244-ZZ-CL-011 | 0 | 3 |  | 2019-08-07 | CSE-OF-7243-036 |  | NO SUBMISSION TO CLIENT
12 | STABILITY ANALYSIS DURING TRANSPORTATION OF SPOOLS & MISC ITEMS @ MICLYN-258 | 7243-7244-ZZ-CL-012 | 00 | 3 |  | 2019-09-03 | CSE-OF-7243-043 |  | NO SUBMISSION TO CLIENT
13 | STABILITY ANALYSIS DURING TRANSPORTATION OF DECK EXTENSION AND HOOK-UP MATERIALS @ MICLYN-258 | 7243-7244-ZZ-CL-013 | 00 | 3 |  | 2020-04-22 | CSE-OF-7243-072 |  | NO SUBMISSION TO CLIENT
14 | MOORING ANALYSIS DURING PIPELAYING OF 16" PIPES FROM KP 0.760 TO KP 0.047 | 7243-7244-ZZ-CL-014 | A | 2 |  | 2020-05-16 | CSE-OF-7243-074 |  | NO SUBMISSION TO CLIENT
15 | MOORING ANALYSIS FOR 16IN SPOOL INSTALLATION AT MNIF 742/749 | 7243-7244-ZZ-CL-015 | A | 2 |  | 2020-05-18 | CSE-OF-7243-075 |  | PENDING WITH PMT
16 | MOORING ANALYSIS FOR 16IN SPOOL INSTALLATION AT SSVS | 7243-7244-ZZ-CL-016 | A | 2 |  | 2020-05-21 | CSE-OF-7243-077 |  | PENDING WITH PMT
17 | BERTHING ANALYSIS FOR QMS ADVENTURE AT SFNY TP-21 PLATFORM | 7243-7244-ZZ-CL-017 | A | 2 |  | 2020-09-09 | CSE-OF-7243-079 | 2020-09-09 | 7243-7244-NPCC-T-5443
18 | BERTHING ANALYSIS FOR MEO GALAXY AT SFNY TP-22 PLATFORM | 7243-7244-ZZ-CL-018 | A | 2 |  | 2022-12-13 | CSE-OF-7243-080
CLIENT CODE - CODE-1 - APPROVED, CODE-2 - REVIEWED WITH COMMENTS, CODE-3 - NOT APPRVOED/REJECTED, CODE-4 - FOR INFORMATION.

## DRAWINGS
|  | LTA FOR OFFSHORE FACILITIES : CRPO FOR STP-21, SG3-AUX UPGRADE, ASSOCIATED PIPELINES & POWER CABLES (OOK) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | NPCC PROJECT NO. 7243 | [10 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (DRAWINGS) | [10 empty] | DATE : |  |  |  | 2018-07-15
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | BUCKLE DETECTOR DETAILS FOR 30" FROM STP-21 TO LANDFALL (649.38/664.39) | 7243-7244-NN-0001 | A | 3 |  | 2018-12-11 | CSE-OF-7243-002 |  | NO SUBMISSION TO CLIENT
2 | SHOREPULL HEAD DETAILS FOR 30" FROM STP-21 TO LANDFALL (1st SECTIONAL) | 7243-7244-NN-0002 | A | 3 |  | 2019-03-10 | CSE-OF-7243-008 |  | NO SUBMISSION TO CLIENT
3 | LAYDOWN HEAD DETAILS FOR 30" FROM STP-21 TO LANDFALL | 7243-7244-NN-0003 | A | 3 |  | 2018-12-11 | CSE-OF-7243-002 |  | NO SUBMISSION TO CLIENT
4 | LAYDOWN HEAD DETAILS FOR 30" FROM STP-21 TO LANDFALL @STP-21 | 7243-7244-NN-0004 | A | 3 |  | 2018-12-11 | CSE-OF-7243-002 |  | NO SUBMISSION TO CLIENT
|  |  | B | 3 |  | 2019-03-11 | CSE-OF-7243-010 |  | NO SUBMISSION TO CLIENT
|  |  | C | 3 |  | 2019-09-22 | CSE-OF-7243-042 |  | NO SUBMISSION TO CLIENT
5 | Laydown Head Details for 30" from STP-21 to LANDFALL (2nd section) | 7243-7244-NN-0005
6 | Start-Up Head+Shore Pull Head details for 30"from from STP-21 to LANDFALL( 2nd section) | 7243-7244-NN-0006
7 | BUCKLE DETECTOR DETAILS FOR 16" CRA CLADDED PIPELINE FROM SGOSP-3 AUX TO STP-21 | 7243-7244-NN-0007 | A | 3 |  | 2018-12-11 | CSE-OF-7243-002 |  | NO SUBMISSION TO CLIENT
8 | START UP HEAD DETAILS FOR 16" CRA CLADDED PIPELINE FROM SGOSP-3-AUX TO STP-21 | 7243-7244-NN-0008 | A | 3 |  | 2019-03-10 | CSE-OF-7243-008 |  | NO SUBMISSION TO CLIENT
|  |  | B | 3 |  | 2019-09-01 | CSE-OF-7243-042 |  | NO SUBMISSION TO CLIENT
9 | LAYDOWN HEAD DETAILS FOR 16" CRA CLADDED PIPELINE FROM SGOSP-3-AUX TO STP-21 | 7243-7244-NN-0009 | A | 3 |  | 2019-03-10 | CSE-OF-7243-008 |  | NO SUBMISSION TO CLIENT
|  |  | B | 3 |  | 2019-09-01 | CSE-OF-7243-042 |  | NO SUBMISSION TO CLIENT
10 | SPOOL LIFTING AND INSTALLATION FOR 16" SPOOL AT SFNY TP-21 | 7243-7244-NN-0010 | A | 3 |  | 2019-07-09 | CSE-OF-7243-030 | 2019-08-28 | 7243-7244-NPCC-T-4895
|  |  | B | 3 |  | 2019-08-29 | CSE-OF-7243-041 |  | NO SUBMISSION TO CLIENT
11 | SPOOL LIFTING AND INSTALLATION FOR 12" SPOOL AT SFNY TP-21 | 7243-7244-NN-0011 | A | 3 |  | 2019-07-09 | CSE-OF-7243-030 | 2019-08-28 | 7243-7244-NPCC-T-4895
|  |  | B | 3 |  | 2019-08-29 | CSE-OF-7243-041 |  | NO SUBMISSION TO CLIENT
12 | SPOOL LIFTING AND INSTALLATION FOR 30" SPOOL AT SFNY TP-21 | 7243-7244-NN-0012 | A | 3 |  | 2019-07-09 | CSE-OF-7243-030 | 2019-08-28 | 7243-7244-NPCC-T-4895
|  |  | B | 3 |  | 2020-07-15 | CSE-OF-7243-067 |  | NO SUBMISSION TO CLIENT
13 | RISER LIFTING AND INSTALLATION FOR 16" RISER SFNY GOSP-3 AUX PLATFORM SFNY GOSP-3 TO SFNY TP-21 | 7243-7244-NN-0013 | A | 3 |  | 2019-05-26 | CSE-OF-7243-022 |  | NO SUBMISSION TO CLIENT
|  |  | B | 3 |  | 2019-08-15 | CSE-OF-7243-037 | 2019-08-28 | 7243-7244-NPCC-T-4895
14 | LOADING ARRANGEMENT & SEAFASTENING OF CC PIPES TRIP-1 @ ALLIANZ CB-252 | 7243-7244-NN-0014 | A | 3 |  | 2019-05-21 | CSE-OF-7243-013 |  | NO SUBMISSION TO CLIENT
15 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-2 @ CREST 287 | 7243-7244-NN-0015 | A | 3 |  | 2019-09-09 | CSE-OF-7243-020 |  | NO SUBMISSION TO CLIENT
16 | LOADING ARRANGEMENT & SEAFASTENING OF CC PIPES TRIP-3 @ ZAKHER 101 | 7243-7244-NN-0016 | A | 3 |  | 2019-09-09 | CSE-OF-7243-023 |  | NO SUBMISSION TO CLIENT
17 | LOADING ARRANGEMENT & SEAFASTENING OF RCC SLEEPERS AND MATTRESSES | 7243-7244-NN-0017 | A | 3 |  | 2019-04-18 | CSE-OF-7243-014 |  | NO SUBMISSION TO CLIENT
18 | Loading Arrangment & Seafastening of RCC Sleeprs on (2nd Cargo Barge) | 7243-7244-NN-0018
19 | Loading Arrangment & Seafastening OF MATTRESSES ON (1ST Cargo Barge) | 7243-7244-NN-0019
20 | LOADING ARRANGEMENT & SEAFASTENING DETAILS DURING TRANSPORTATION OF STINGER-IX SEC-A @ ZAKHER-101 | 7243-7244-NN-0020
21 | TYPICAL LIFTING AND INSTALLATION OF RCC SLEEPER | 7243-7244-NN-0021 | A | 3 |  | 2019-05-08 | CSE-OF-7243-016 |  | NO SUBMISSION TO CLIENT
22 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE MATTRESS | 7243-7244-NN-0022 | A | 3 |  | 2019-05-12 | CSE-OF-7243-018 |  | NO SUBMISSION TO CLIENT
23 | CLAMP LIFTING AND INSTALLATION FOR 16" RISER SFNY GOSP-3 TO SFNY TP-21 | 7243-7244-NN-0023 | A | 3 |  | 2019-08-15 | CSE-OF-7243-038 |  | NO SUBMISSION TO CLIENT
24 | TEMPORARY KNEE BRACE DETAILS FOR 16" SPOOL AT TP-21 | 7243-7244-NN-0024 | A | 3 |  | 2019-07-09 | CSE-OF-7243-030 |  | NO SUBMISSION TO CLIENT
25 | Temporary Knee Brace Details for 12" Spool at TP-21 | 7243-7244-NN-0025
26 | TEMPORARY KNEE BRACE DETAILS FOR 30" SPOOL AT TP-21 | 7243-7244-NN-0026 | A | 3 |  | 2019-07-09 | CSE-OF-7243-030 |  | NO SUBMISSION TO CLIENT
27 | TEMPORARY KNEE BRACE DETAILS FOR 16" SPOOL AT GOSP-3 | 7243-7244-NN-0027 | A | 3 |  | 2019-07-09 | CSE-OF-7243-030 |  | NO SUBMISSION TO CLIENT
28 | FLANGE PROTECTOR DETAILS FOR TL-14 30" FROM STP-21 TO LANDFALL | 7243-7244-NN-0028 | A | 3 |  | 2018-12-29 | CSE-OF-7243-003 |  | NO SUBMISSION TO CLIENT
29 | FLANGE PROTECTOR DETAILS FOR 16" CRA CLADDED PIPELINE FROM SGOSP-3-AUX TO STP-21 | 7243-7244-NN-0029 | A | 3 |  | 2018-12-29 | CSE-OF-7243-003 |  | NO SUBMISSION TO CLIENT
30 | EMERGENCY HEAD DETAILS FOR TL-14 30" FROM STP-21 TO LANDFALL | 7243-7244-NN-0030 | A | 3 |  | 2019-03-10 | CSE-OF-7243-008 |  | NO SUBMISSION TO CLIENT
31 | EMERGENCY HEAD DETAILS FOR 16" CRA CLADDED PIPELINE FROM SGOSP-3-AUX TO STP-21 | 7243-7244-NN-0031 | A | 3 |  | 2019-03-10 | CSE-OF-7243-008 |  | NO SUBMISSION TO CLIENT
32 | Typical Demolishing and lifting of P/L and Spools | 7243-7244-NN-0032
33 | TEMPORARY 30" SCRAPER RECEIVER / LAUNCHER | 7243-7244-NN-0033 | A | 3 |  | 2020-07-27 | CSE-OF-7243-078
34 | TEMPORARY 16" SCRAPER RECEIVER / LAUNCHER | 7243-7244-NN-0034 | A | 3 |  | 2020-02-18 | CSE-OF-7243-064 |  | NO SUBMISSION TO CLIENT
35 | SHORE PULL ARRANGEMENT AND MOBILIZATION FOR 30" PIPELINE @ SFNY TP-21 TO SFNY GOSP-1 | OFO-P7243-SK-015 | A | 3 |  | 2019-04-25 | CSE-OF-7243-015 | 2019-04-28 | 7243-7244-NPCC-T-4296
|  |  | B | 3 |  | 2019-06-02 | CSE-OF-7243-026 |  | NO SUBMISSION TO CLIENT
36 | SHORE PULL ARRANGEMENT AND DEMOBILIZATION FOR 30" PIPELINE @ SFNY TP-21 TO SFNY GOSP-1 | OFO-P7243-SK-018 | A | 3 |  | 2019-04-25 | CSE-OF-7243-015 | 2019-04-28 | 7243-7244-NPCC-T-4296
37 | 16" START UP JOINT ASSEMBLE AT STP-21 | OFO-P7243-SK-024-001 | 0 | FAB |  | 2019-08-05 | CSE-OF-7243-035 |  | NO SUBMISSION TO CLIENT
38 | 30" LAYDOWN JOINT ASSEMBLE AT STP-21 | OFO-P7243-SK-025-001 | 0 | FAB |  | 2019-08-05 | CSE-OF-7243-035 |  | NO SUBMISSION TO CLIENT
39 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-4 @ CREST 287 | 7243-7244-NN-0035 | A | 3 |  | 2019-11-26 | CSE-OF-7243-054 |  | NO SUBMISSION TO CLIENT
40 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-5 @ CREST-287 | 7243-7244-NN-0036 | A | 3 |  | 2020-02-04 | CSE-OF-7243-059 |  | NO SUBMISSION TO CLIENT
41 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-6 @ ZAKHER-101 | 7243-7244-NN-0037 | A | 3 |  | 2020-02-10 | CSE-OF-7243-061 |  | NO SUBMISSION TO CLIENT
42 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-7 @ ALLIANZ CB-252 | 7243-7244-NN-0038 | A | 3 |  | 2020-01-06 | CSE-OF-7243-058 |  | NO SUBMISSION TO CLIENT
43 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF TRANSPORTATION SPOOLS @ GOGAS-250 | 7243-7244-NN-0039 | A | 3 |  | 2019-08-07 | CSE-OF-7243-036 |  | NO SUBMISSION TO CLIENT
44 | SPOOL LIFTING AND INSTALLATION FOR 16" SPOOL SFNY GOSP-3 AUX PLATFORM (SFNY GOSP-3 TO SFNT TP-21) | 7243-7244-NN-0040 | A | 3 |  | 2019-07-09 | CSE-OF-7243-030 | 2019-08-28 | 7243-7244-NPCC-T-4895
|  |  | B | 3 |  | 2020-04-08 | CSE-OF-7243-070 |  | NO SUBMISSION TO CLIENT
45 | SPOOLS INSTALLATION METHODOLOGY BY SAID ALETHIA | 7243-7244-NN-0041 | A | 3 |  | 2019-08-29 | CSE-OF-7243-040 |  | NO SUBMISSION TO CLIENT
46 | LOADING ARRANGEMENT & SEAFASTENING OF SPOOLS & MISC ITEMS @ MICLYN-258 | 7243-7244-NN-0042 | A | 3 |  | 2019-09-03 | CSE-OF-7243-043 |  | NO SUBMISSION TO CLIENT
47 | TYPICAL LIFTING AND INSTALLATION CONCRETE MATTRESS @ CR-15 FOR CABLE LAYING FROM SFNY TP-21 TO SFNY TP-22 | 7243-7244-NN-0043 | A | 3 |  | 2019-10-14 | CSE-OF-7243-049 |  | NO SUBMISSION TO CLIENT
48 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-8 @ ZAKHER-101 | 7243-7244-NN-0044 | A | 3 |  | 2020-03-09 | CSE-OF-7243-066 |  | NO SUBMISSION TO CLIENT
49 | LOADING ARRANGEMENT & SEAFASTENING OF DECK EXTENSION & HOOK-UP MATERIALS @ MICLYN-258 | 7243-7244-NN-0045 | A | 3 |  | 2020-04-22 | CSE-OF-7243-072 |  | NO SUBMISSION TO CLIENT
50 | LOADING ARRANGEMENT & SEAFASTENING OF CC PIPES TRIP-9 @ EOS-283 | 7243-7244-NN-0046 | A | 3 |  | 2020-04-08 | CSE-OF-7243-071 |  | NO SUBMISSION TO CLIENT
51 | LOADING ARRANGEMENT & SEAFASTENING OF CC PIPES & SHALLOW WATER MARKERS TRIP-10 @ ZAKHER-101 | 7243-7244-NN-0047 | A | 3 |  | 2020-04-05 | CSE-OF-7243-069 |  | NO SUBMISSION TO CLIENT
52 | SPOOL LIFTING AND INSTALLATION FOR 30" SPOOL AT SFNY TP-21 (SPOOL-2, 3 & 4) | 7243-7244-NN-0048 | A | 3 |  | 2020-04-26 | CSE-OF-7243-073 |  | PENDING WITH PMT
53 | SPOOL LIFTING AND INSTALLATION FOR 30" SPOOL AT SFNY TP-21 (SPOOL-5) | 7243-7244-NN-0049 | A | 3 |  | 2020-04-26 | CSE-OF-7243-073 |  | PENDING WITH PMT
54 | SPOOL LIFTING AND INSTALLATION FOR 16" SPOOL AT MNIF 742/749, TIE-IN & SSVS MANIFA 742/749 16" FLOWLINE | 7243-7244-NN-0050
55 | LIFTING AND INSTALLATION ARRANGEMENT OF SHALLOW WATER MARKER | 7243-7244-NN-0051
56 | SPOOL LIFTING AND INSTALLATION FOR 30" SPOOL AT SFNY TP-21 SPOOL-3 & 4 | 7243-7244-NN-0052