## NAVAL MARINE
PROJECT 7279 - PROJECT DELIVERABLE REGISTER
[20 empty] | Date | : 06-05-2018
|  | PROCUREMENT, CONSTRUCTION AND INSTALLATION (PCI) of DALMA GAS DEVELOPMENT PROJECT - FOUR (4) WELL HEAD | [17 empty] | Revision | : 0
[20 empty] | Agreement No | : 409566
[20 empty] | NPCC Proj No. | : 7279
[20 empty] | CLIENT Doc. | : AD258-764-G-00130
|  | OFFSHORE CONSTRUCTION | [17 empty] | NPCC Doc No. | : 7279-PP-GE-001
SL. NO. | DESCRIPTION | NPCC DOC. No | IN CHARGE | DOC. CLASS | SCHEDULE DATE | COMPANY DOC. NO. | REV NO | OFFSHORE TO PMT |  | PMT TO CLIENT |  | STATUS (ADNOC OFFSHORE) |  |  | PMT TO MWS |  | STATUS (DNV-GL) |  |  | NPCC Reply Status"P" for Pending | PENDING (DAYS) | REMARKS
[8 empty] | REF | DATE | REF | DATE | REF | DATE | STATUS* | REF | DATE | REF | DATE | STATUS*
1 | MOORING ANALYSIS REPORT DURING INSTALLATION OF WHP-T4 JACKET | 7279-ZZ-RP-001 | OSD | 2 | 2018-12-05 | AD258-764-G-00211 | A | CSE-OF-7279-001 | 2018-10-29 | 7279-NPCC-AO-T-00188 | 2018-10-29 | AO-NPCC-409566-00246- | 2018-12-16 | CODE -2 | EMAIL | 2018-10-30 | BAS1033-TRN 001 | 2018-10-31 | OPEN COMMENTS
[7 empty] | B | CSE-OF-7279-002 | 2018-12-31 | 7279-NPCC-AO-T-00229 | 2019-01-02 | AO-NPCC-409566-00288 | 2019-01-24 | CODE -2 | 7279-NPCC-MWS- T-00004 | 02/01/2019 | BAS1033-TRN 001 | 11/01/19 | Accepted with condition
|  |  |  | 1 |  |  | 0 | CSE-OF-7279-004 | 2019-01-27 | 7279-NPCC-AO-T-00249 | 2019-01-28 | AO-NPCC-409566-00339 | 2019-02-24 | Accepted | 7279-NPCC-AO-T-00249 | 2019-01-28 | BAS1033-TRN 001 | 05/02/19 | Accepted with condition
2 | MOORING ANALYSIS REPORT DURING INSTALLATION OF WHP 10 JACKET | 7279-ZZ-RP-002 | OSD | 2 | 2019-02-14 | AD258-764-G-00212 | A | CSE-OF-7279-005 | 2019-01-28 | 7279-NPCC-AO-T-00252 | 2019-01-29 | AO-NPCC-409566-00337 | 2019-02-20 | CODE -2 | 7279-NPCC-AO-T-00252 | 2019-01-29 | BAS1033-TRN 017 | 21/02/19 | OPEN COMMENTS
|  |  |  | 1 |  |  | B | CSE-OF-7279-007 | 2019-03-21 | 7279-NPCC-AO-T-00274 | 2019-03-24 | AO-NPCC-409566-00390 | 2019-04-11 | Accepted | 7279-NPCC-AO-T-00274 | 2019-03-24 | BAS1033-TRN 017-01 | 2019-03-31 | Accepted with condition
3 | MOORING ANALYSIS REPORT FOR INSTALLATION OF WHP BH-3 JACKET | 7279-ZZ-RP-003 | OSD | 2 | 2019-02-25 | AD258-764-G-00213 | A | CSE-OF-7279-003 | 2019-01-21 | 7279-NPCC-AO-T-00242 | 23/01/2019 | AO-NPCC-409566-00338 | 2019-02-20 | CODE -2 | 7279-NPCC-MWS- T-00006 | 23/01/2019 | BAS1033-TRN 016 | 21/02/19 | OPEN COMMENTS
|  |  |  | 1 |  |  | B | CSE-OF-7279-007 | 2019-03-21 | 7279-NPCC-AO-T-00275 | 2019-03-24 | AO-NPCC-409566-00391 | 2019-04-11 | Accepted | 7279-NPCC-AO-T-00275 | 2019-03-24 | BAS1033-TRN 016-01 | 2019-03-31 | Accepted with condition
|  |  |  | 1 |  |  | 0 | BY EMAIL | 2019-05-01 | 7279-NPCC-AO-T-00300 | 2019-05-01 |  |  |  | 7279-NPCC-AO-T-00300 | 2019-05-01 | BAS1033-TRN 016-02 | 2019-05-10 | Accepted with condition
4 | MOORING ANALYSIS REPORT FOR INSTALLATION OF WHP NS-19 JACKET | 7279-ZZ-RP-004 | OSD | 2 | 2019-03-05 | AD258-764-G-00214 | A | CSE-OF-7279-006 | 2019-02-06 | 7279-NPCC-AO-T-00258 | 2019-02-06 |  |  |  | 7279-NPCC-AO-T-00258 | 2019-02-06 | BAS1033-TRN 018 | 21/02/19 | OPEN COMMENTS
|  |  |  | 1 |  |  | B | CSE-OF-7279-008 | 2019-04-29 | 7279-NPCC-AO-T-00295 | 2019-04-29 |  |  |  | 7279-NPCC-AO-T-00295 | 2019-04-29 | BAS1033-TRN-018 | 2019-05-05 | Accepted with condition