## Documents - Naval & Marine
|  | LONG TERM AGREEMENT (LTA) FOR OFFSHORE FACILITIES CRPO FOR NINE (9) STANDARDIZED SSS JACKETS IN ZULF FIELD UNDER BI-12-18000 | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  | NPCC PROJECT NO. 8241-8242 | [10 empty] | REVISION : |  |  |  | A
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (NAVAL & MARINE) | [10 empty] | DATE : |  |  |  | 2019-03-12
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | DNV-GL |  |  | GMC |  |  |  |  | REMARKS
[6 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[6 empty] | CSE TO PMT |  | PMT TO MWS |  | FROM MWS |  |  | PMT TO GMC |  | STATUS FROM GMC
[6 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | MOORING ANALYSIS DURING ZULF 2040/2049 JACKET INSTALLATION | 8241-8242-PP-OF-034 | A | 2 |  | 2019-07-18 | CSE-OF-8241/8242-001 | 2019-07-20 | SENT VIA FTP TO MWS
2 | MOORING ANALYSIS DURING ZULF 2090/2099 JACKET AND PILE INSTALLATION | 8241-8242-PP-OF-035 | A | 2 |  | 2019-07-23 | CSE-OF-8241/8242-002 | 2019-07-24 | SENT VIA EMAIL TO MWS | 2019-08-25 | BAS1073-TRN 042 | ACCEPTED
3 | MOORING ANALYSIS DURING ZULF 2060/2069 JACKET INSTALLATION | 8241-8242-PP-OF-039 | A | 2 |  | 2019-08-08 | CSE-OF-8241/8242-003 | 2019-08-10 | SENT VIA EMAIL TO MWS | 2019-08-25 | BAS1073-TRN 041 | ACCEPTED
4 | MOORING ANALYSIS DURING ZULF 1200/1209 JACKET RELATED INSTALLATION ACTIVITIES | 8241-8242-PP-OF-040 | A | 2 |  | 2019-08-26 | CSE-OF-8241/8242-005 | 2019-08-26 | 8241-NPCC-DNVGL-T-0069 | 2019-08-27 | BAS1073-TRN 017 | ACCEPTED
5 | MOORING ANALYSIS DURING ZULF 1250/1259 JACKET RELATED INSTALLATION ACTIVITIES | 8241-8242-PP-OF-041 | A | 2 |  | 2019-08-25 | CSE-OF-8241/8242-004 | 2019-08-25 | 8241-NPCC-DNVGL-T-0068
6 | MOORING ANALYSIS DURING ZULF 2000/2009 JACKET INSTALLATION | 8241-8242-PP-OF-042 | A | 2 |  | 2019-09-10 | CSE-OF-8241/8242-006 | 2019-09-12 | 8241-NPCC-DNVGL-T-0073
7 | MOORING ANALYSIS FOR HLS-2000 DURING ZULF 2000/2009 JACKET INSTALLATION | 8241-8242-PP-OF-043 | A | 2 |  | 2019-09-22 | CSE-OF-8241/8242-007 | 2019-09-23 | 8241-NPCC-DNVGL-T-0079
8 | MOORING ANALYSIS DURING ZULF 2021/2029 INSERT PILES AND CONDUCTORS INSTALLATION | 8241-8242-PP-OF-048 | A | 2 |  | 2020-09-10 | CSE-OF-8241/8242-008 | 2020-09-20 | sent to DNV-GL | 2020-09-20 | BAS1073-TRN 054 | ACCEPTED
9 | MOORING ANALYSIS DURING INSTALLATION OF PILE SECTION CONDUCTORS AND BOAT LANDING AT ZULF 2071/2079 | 8241-8242-PP-OF-049 | A | 2 |  | 2020-10-05 | CSE-OF-8241/8242-009 | 2020-10-08 | 8241-NPCC-DNVGL-T-0121 | 2020-10-08 | BAS1073-TRN 055 | ACCEPTED
10 | BERTHING ANALYSIS FOR KIRKCONNELL TIDE AT ZULF 2021/907/2071 PLATFORMS | 8241-8242-PP-OF-050 | A | 3 |  | ON HOLD | CSE-OF-8241/8242-010