## Specification (hidden)
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
|  | UMM AL DALKH EARLY PRODUCTION SCHEME EPC PROJECT | [11 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 2136 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2021-11-23
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADNOC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | SPECIFICATION FOR OFFSHORE PIPELINE AND RISER INSTALLATION – REV-A1 | 2136-N-SP-0314 | E1279-TS-PLW-L-0019 | B1 |  |  | 2022-02-15 | E-MAIL
2
3
4
5
6
7
8
9
10
11
12
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADNOC APPROVAL CODE : (1) ACCEPTED; (2) ACCEPTED WITH COMMENTS; (2A) ACCEPTED WITH MINOR COMMENTS;
(3) NOT ACCEPTED, REVISE & RESUBMIT; (4) FOR INFORMATION

## Documents - Pipeline & Cable
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
|  | EPC FOR UMM SHAIF LONG TERM DEVELOPMENT PHASE-1 (USLTDP1) PROJECT | [11 empty] | ADNOC DOC. No. :
|  | NPCC PROJECT NO. 2035 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2022-03-17
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADNOC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPE STACKING ANALYSIS REPORT | 2035-NN-RP-001
2 | PIPELAY INSTALLATION REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-159A TO US-12B (PL-1) | 2035-NN-RP-002
3 | PIPELAY INSTALLATION REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-12B TO USSC-RP1 (PL-2) | 2035-NN-RP-003
4 | PIPELAY INSTALLATION REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-142A TO USSC-RP1 (PL-3) | 2035-NN-RP-004
5 | PIPELAY INSTALLATION REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-19B TO US-153A (PL-4) | 2035-NN-RP-005
6 | PIPELAY INSTALLATION REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-153A TO USSC-RP1 (PL-5) | 2035-NN-RP-006
7 | PIPELAY INSTALLATION REPORT FOR 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) | 2035-NN-RP-007
8 | PIPELAY INSTALLATION REPORT FOR 18" HP OIL SUBSEA PIPELINE FROM HP2 TO USSC-RP1 (PL-7) | 2035-NN-RP-008
9 | PIPELAY INSTALLATION REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM HP3 TO USSC-RP1 (PL-8) | 2035-NN-RP-009
10 | PIPELAY INSTALLATION REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) | 2035-NN-RP-010
11 | PIPELAY INSTALLATION REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) | 2035-NN-RP-011
12 | PIPELAY INSTALLATION REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) | 2035-NN-RP-012
13 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM US-153A TO US-19B(CC-4) - CB-1 | 2035-NN-RP-013
14 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM US-1216 TO US153A(CC-3) - CB-2 | 2035-NN-RP-014
15 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM US-142A TO US218(CC-8) - CB-3 | 2035-NN-RP-015
16 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM US-159A TO US-12B(CC-11) - CB-7 | 2035-NN-RP-016
17 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM US-19B TO HP-1(CC-5) - CB-8 | 2035-NN-RP-017
18 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM HP1 TO HP2(CC-6) - CB-9 | 2035-NN-RP-018
19 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM HP-2 TO US-142A(CC-7) - CB-10 | 2035-NN-RP-019
20 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM USSC-RP1 TO HP3(CC-2) - CB-11 | 2035-NN-RP-020
21 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM USSC-RP1 TO HP3(CC-1) - CB-12 | 2035-NN-RP-021
22 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM USSC-PDP TO WHT- GI-1(CC-13) TO US-128 - CB-13 | 2035-NN-RP-022
23 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM USSC-PDP TO WHT- GP-1(CC-14) TO US-159A - CB-14 | 2035-NN-RP-023
24 | DAVIT LIFT ANALYSIS REPORT @ USSC-RP1 | 2035-NN-RP-024
25 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-159A TO US-12B (PL-1) | 2035-NN-RP-025
26 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-12B TO USSC-RP1 (PL-2) | 2035-NN-RP-026
27 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-142A TO USSC-RP1 (PL-3) | 2035-NN-RP-027
28 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-19B TO US-153A (PL-4) | 2035-NN-RP-028
29 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-153A TO USSC-RP1 (PL-5) | 2035-NN-RP-029
30 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) | 2035-NN-RP-030
31 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 18" HP OIL SUBSEA PIPELINE FROM HP2 TO USSC-RP1 (PL-7) | 2035-NN-RP-031
32 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM HP3 TO USSC-RP1 (PL-8) | 2035-NN-RP-032
33 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) | 2035-NN-RP-033
34 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) | 2035-NN-RP-034
35 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) | 2035-NN-RP-035
36 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-1) | 2035-NN-RP-036
37 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-2) | 2035-NN-RP-037
38 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-3) | 2035-NN-RP-038
39 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-4) | 2035-NN-RP-039
40 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-5) | 2035-NN-RP-040
41 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-6) | 2035-NN-RP-041
42 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF RISERS, SPOOLS & RISER PROTECTOR (TRIP-1) | 2035-NN-RP-042
43 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF RISERS, SPOOLS & RISER PROTECTOR (TRIP-2) | 2035-NN-RP-043
44 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF RISERS, SPOOLS & RISER PROTECTOR (TRIP-3) | 2035-NN-RP-044
45 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS - (TRIP-1) | 2035-NN-RP-045
46 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS - (TRIP-2) | 2035-NN-RP-046
47 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS - (TRIP-3) | 2035-NN-RP-047
48 | SPARE | 2035-NN-RP-048
49 | SPARE | 2035-NN-RP-049
50 | SPARE | 2035-NN-RP-050
51 | SPARE | 2035-NN-RP-051
52 | SPARE | 2035-NN-RP-052
53 | SPARE | 2035-NN-RP-053
54 | SPARE | 2035-NN-RP-054
55 | SPARE | 2035-NN-RP-055
56 | SPARE | 2035-NN-RP-056
57 | SPARE | 2035-NN-RP-057
58 | SPARE | 2035-NN-RP-058
59 | SPARE | 2035-NN-RP-059
60 | SPARE | 2035-NN-RP-060
61 | SPARE | 2035-NN-RP-061
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADNOC APPROVAL CODE : (1) ACCEPTED; (2) ACCEPTED WITH COMMENTS; (2A) ACCEPTED WITH MINOR COMMENTS;
(3) NOT ACCEPTED, REVISE & RESUBMIT; (4) FOR INFORMATION

## Documents - Naval Marine
|  | ADNOC OFFSHORE | [12 empty] | NPCC DOC. No.:
|  | EPC FOR UMM SHAIF LONG TERM DEVELOPMENT PHASE-1 (USLTDP1) PROJECT | [12 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 2035 | [12 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (NAVAL & MARINE) | [12 empty] | DATE : |  |  |  | 2022-03-17
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADNOC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | REMAINING DAYS | NPCC |  |  |  | ADNOC OFFSHORE |  |  | - |  |  |  |  | REMARKS
[8 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[8 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[8 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | MOORING ANALYSIS DURING PIPELAYING OF 16" HP OIL SUBSEA PIPELINE FROM US-159A TO US-12B (PL-1) | 2035-ZZ-CL-001
2 | MOORING ANALYSIS DURING PIPELAYING OF 16" HP OIL SUBSEA PIPELINE FROM US-12B TO USSC-RP1 (PL-2) | 2035-ZZ-CL-002
3 | MOORING ANALYSIS DURING PIPELAYING OF 16" HP OIL SUBSEA PIPELINE FROM US-142A TO USSC-RP1 (PL-3) | 2035-ZZ-CL-003
4 | MOORING ANALYSIS DURING PIPELAYING OF 16" HP OIL SUBSEA PIPELINE FROM US-19B TO US-153A (PL-4) | 2035-ZZ-CL-004
5 | MOORING ANALYSIS DURING PIPELAYING OF 16" HP OIL SUBSEA PIPELINE FROM US-153A TO USSC-RP1 (PL-5) | 2035-ZZ-CL-005
6 | MOORING ANALYSIS DURING PIPELAYING OF 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) | 2035-ZZ-CL-006
7 | MOORING ANALYSIS DURING PIPELAYING OF 18" HP OIL SUBSEA PIPELINE FROM HP2 TO USSC-RP1 (PL-7) | 2035-ZZ-CL-007
8 | MOORING ANALYSIS DURING PIPELAYING OF 16" HP OIL SUBSEA PIPELINE FROM HP3 TO USSC-RP1 (PL-8) | 2035-ZZ-CL-008
9 | MOORING ANALYSIS DURING PIPELAYING OF 16" WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) | 2035-ZZ-CL-009
10 | MOORING ANALYSIS DURING PIPELAYING OF 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) | 2035-ZZ-CL-010
11 | MOORING ANALYSIS DURING PIPELAYING OF 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) | 2035-ZZ-CL-011
12 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" HP OIL SUBSEA PIPELINE FROM US-159A TO US-12B (PL-1) | 2035-ZZ-CL-012
13 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" HP OIL SUBSEA PIPELINE FROM US-12B TO USSC-RP1 (PL-2) | 2035-ZZ-CL-013
14 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" HP OIL SUBSEA PIPELINE FROM US-142A TO USSC-RP1 (PL-3) | 2035-ZZ-CL-014
15 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" HP OIL SUBSEA PIPELINE FROM US-19B TO US-153A (PL-4) | 2035-ZZ-CL-015
16 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" HP OIL SUBSEA PIPELINE FROM US-153A TO USSC-RP1 (PL-5) | 2035-ZZ-CL-016
17 | MOORING ANALYSIS DURING RISER INSTALLATION OF 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) | 2035-ZZ-CL-017
18 | MOORING ANALYSIS DURING RISER INSTALLATION OF 18" HP OIL SUBSEA PIPELINE FROM HP2 TO USSC-RP1 (PL-7) | 2035-ZZ-CL-018
19 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" HP OIL SUBSEA PIPELINE FROM HP3 TO USSC-RP1 (PL-8) | 2035-ZZ-CL-019
20 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) | 2035-ZZ-CL-020
21 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) | 2035-ZZ-CL-021
22 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) | 2035-ZZ-CL-022
23 | MOORING ANALYSIS DURING CABLE LAYING FROM US-153A TO US-19B(CC-4) - CB-1 | 2035-ZZ-CL-023
24 | MOORING ANALYSIS DURING CABLE LAYING FROM US-1216 TO US153A(CC-3) - CB-2 | 2035-ZZ-CL-024
25 | MOORING ANALYSIS DURING CABLE LAYING FROM US-142A TO US218(CC-8) - CB-3 | 2035-ZZ-CL-025
26 | MOORING ANALYSIS DURING CABLE LAYING FROM US-159A TO US-12B(CC-11) - CB-7 | 2035-ZZ-CL-026 |  |  |  | \
27 | MOORING ANALYSIS DURING CABLE LAYING FROM US-19B TO HP-1(CC-5) - CB-8 | 2035-ZZ-CL-027
28 | MOORING ANALYSIS DURING CABLE LAYING FROM HP1 TO HP2(CC-6) - CB-9 | 2035-ZZ-CL-028
29 | MOORING ANALYSIS DURING CABLE LAYING FROM HP-2 TO US-142A(CC-7) - CB-10 | 2035-ZZ-CL-029
30 | MOORING ANALYSIS DURING CABLE LAYING FROM USSC-RP1 TO HP3(CC-2) - CB-11 | 2035-ZZ-CL-030
31 | MOORING ANALYSIS DURING CABLE LAYING FROM USSC-RP1 TO HP3(CC-1) - CB-12 | 2035-ZZ-CL-031
32 | MOORING ANALYSIS DURING CABLE LAYING FROM USSC-PDP TO WHT- GI-1(CC-13) TO US-128 - CB-13 | 2035-ZZ-CL-032
33 | MOORING ANALYSIS DURING CABLE LAYING FROM USSC-PDP TO WHT- GP-1(CC-14) TO US-159A - CB-14 | 2035-ZZ-CL-033
34 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES TRIP-1 | 2035-ZZ-CL-034
35 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES TRIP-2 | 2035-ZZ-CL-035
36 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES TRIP-3 | 2035-ZZ-CL-036
37 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES TRIP-4 | 2035-ZZ-CL-037
38 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES TRIP-5 | 2035-ZZ-CL-038
39 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES TRIP-6 | 2035-ZZ-CL-039
40 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF RISERS, SPOOLS & RISER PROTECTOR TRIP-1 | 2035-ZZ-CL-040
41 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF RISERS, SPOOLS & RISER PROTECTOR TRIP-2 | 2035-ZZ-CL-041
42 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF RISERS, SPOOLS & RISER PROTECTOR TRIP-3 | 2035-ZZ-CL-042
43 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS TRIP-1 | 2035-ZZ-CL-043
44 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS TRIP-2 | 2035-ZZ-CL-044
45 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS TRIP-3 | 2035-ZZ-CL-045
46 | SPARE | 2035-ZZ-CL-046
47 | SPARE | 2035-ZZ-CL-047
48 | SPARE | 2035-ZZ-CL-048
49 | SPARE | 2035-ZZ-CL-049
50 | SPARE | 2035-ZZ-CL-050
51 | SPARE | 2035-ZZ-CL-051
52 | SPARE | 2035-ZZ-CL-052
53 | SPARE | 2035-ZZ-CL-053
54 | SPARE | 2035-ZZ-CL-054
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADNOC APPROVAL CODE : (1) ACCEPTED; (2) ACCEPTED WITH COMMENTS; (2A) ACCEPTED WITH MINOR COMMENTS;
(3) NOT ACCEPTED, REVISE & RESUBMIT; (4) FOR INFORMATION

## Drawings
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
|  | EPC FOR UMM SHAIF LONG TERM DEVELOPMENT PHASE-1 (USLTDP1) PROJECT | [11 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 2035 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (DRAWINGS) | [11 empty] | DATE : |  |  |  | 2022-03-17
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADNOC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE |  |  | - |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | START UP HEAD DETAILS FOR 16” PL | 2035-NN-0001
2 | START UP HEAD DETAILS FOR 18” PL | 2035-NN-0002
3 | LAYDOWN HEAD DETAILS FOR 16" PL | 2035-NN-0003
4 | LAYDOWN HEAD DETAILS FOR 18" PL | 2035-NN-0004
5 | EMERGENCY LAYDOWN HEAD DETAILS FOR 16" PL | 2035-NN-0005
6 | EMERGENCY LAYDOWN HEAD DETAILS FOR 18" PL | 2035-NN-0006
7 | BUCKLE DETECTOR DETAILS FOR 16" PL | 2035-NN-0007
8 | BUCKLE DETECTOR DETAILS FOR 18" PL | 2035-NN-0008
9 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-159A TO US-12B (PL-1) @ US-159A | 2035-NN-0009
10 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-159A TO US-12B (PL-1) @ US-12B | 2035-NN-0010
11 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-12B TO USSC-RP1 (PL-2) @ US-12B | 2035-NN-0011
12 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-12B TO USSC-RP1 (PL-2) @ USSC-RP1 | 2035-NN-0012
13 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-142A TO USSC-RP1 (PL-3) @ US-142A | 2035-NN-0013
14 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-142A TO USSC-RP1 (PL-3) @ USSC-RP1 | 2035-NN-0014
15 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-19B TO US-153A (PL-4) @ US-19B | 2035-NN-0015
16 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-19B TO US-153A (PL-4) @ US-153A | 2035-NN-0016
17 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-153A TO USSC-RP1 (PL-5) @ US-153A | 2035-NN-0017
18 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-153A TO USSC-RP1 (PL-5) @ USSC-RP1 | 2035-NN-0018
19 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) @ HP1 | 2035-NN-0019
20 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) @ HP2 | 2035-NN-0020
21 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" HP OIL SUBSEA PIPELINE FROM HP2 TO USSC-RP1 (PL-7) @ HP2 | 2035-NN-0021
22 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" HP OIL SUBSEA PIPELINE FROM HP2 TO USSC-RP1 (PL-7) @ USSC-RP1 | 2035-NN-0022
23 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM HP3 TO USSC-RP1 (PL-8) @ HP3 | 2035-NN-0023
24 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM HP3 TO USSC-RP1 (PL-8) @ USSC-RP1 | 2035-NN-0024
25 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) @ USSC-RP1 | 2035-NN-0025
26 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) @ HP3 | 2035-NN-0026
27 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) @ HP3 | 2035-NN-0027
28 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) @ HP2 | 2035-NN-0028
29 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) @ HP2 | 2035-NN-0029
30 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) @ HP1 | 2035-NN-0030
31 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-1 WITH BALAST PLAN | 2035-NN-0031
32 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-2 WITH BALAST PLAN | 2035-NN-0032
33 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-3 WITH BALAST PLAN | 2035-NN-0033
34 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-4 WITH BALAST PLAN | 2035-NN-0034
35 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-5 WITH BALAST PLAN | 2035-NN-0035
36 | LOADING ARRANGEMENT & SEAFASTENING OF C.C PIPES TRIP-6 WITH BALAST PLAN | 2035-NN-0036
37 | LOADING ARRGT & SEAFASTENING DETAILS OF OF RISERS, SPOOLS & RISER PROTECTOR TRIP-1 WITH BALAST PLAN | 2035-NN-0037
38 | LOADING ARRGT & SEAFASTENING DETAILS OF OF RISERS, SPOOLS & RISER PROTECTOR TRIP-2 WITH BALAST PLAN | 2035-NN-0038
39 | LOADING ARRGT & SEAFASTENING DETAILS OF OF RISERS, SPOOLS & RISER PROTECTOR TRIP-3 WITH BALAST PLAN | 2035-NN-0039
40 | LOADING ARRANGEMENT AND SEAFASTENING OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS TRIP-1 WITH BALAST PLAN | 2035-NN-0040
41 | LOADING ARRANGEMENT AND SEAFASTENING OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS TRIP-2 WITH BALAST PLAN | 2035-NN-0041
42 | LOADING ARRANGEMENT AND SEAFASTENING OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS TRIP-3 WITH BALAST PLAN | 2035-NN-0042
43 | TYPICAL LIFTING AND INSTALLATION DRAWING FOR SLEEPERS | 2035-NN-0043
44 | TYPICAL LIFTING AND INSTALLATION DRAWING FOR MATTRESSES | 2035-NN-0044
45 | TYPICAL LIFTING AND INSTALLATION DRAWING FOR GROUTBAG | 2035-NN-0045
46 | TYPICAL LIFTING AND INSTALLATION DRAWING FOR TEMPORARY SUPPORT | 2035-NN-0046
47 | SPARE | 2035-NN-0047
48 | SPARE | 2035-NN-0048
49 | SPARE | 2035-NN-0049
50 | SPARE | 2035-NN-0050
51 | SPARE | 2035-NN-0051
52 | SPARE | 2035-NN-0052
53 | SPARE | 2035-NN-0053
54 | SPARE | 2035-NN-0054
55 | SPARE | 2035-NN-0055
56 | SPARE | 2035-NN-0056
57 | SPARE | 2035-NN-0057
58 | SPARE | 2035-NN-0058
59 | SPARE | 2035-NN-0059
60 | SPARE | 2035-NN-0060
61 | SPARE | 2035-NN-0061
62 | SPARE | 2035-NN-0062
63 | SPARE | 2035-NN-0063
64 | SPARE | 2035-NN-0064
65 | SPARE | 2035-NN-0065
66 | SPARE | 2035-NN-0066
67 | SPARE | 2035-NN-0067
68 | SPARE | 2035-NN-0068
69 | SPARE | 2035-NN-0069
70 | SPARE | 2035-NN-0070
71 | SPARE | 2035-NN-0071
72
73
74
75
76
77
78
79
80
81
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADMA-OPCO APPROVAL CODE : (1) ACCEPTED; (2) ACCEPTED WITH COMMENTS; (2A) ACCEPTED WITH MINOR COMMENTS;
(3) NOT ACCEPTED, REVISE & RESUBMIT; (4) FOR INFORMATION