## Specification (hidden)
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
|  | UMM AL DALKH EARLY PRODUCTION SCHEME EPC PROJECT | [11 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 2136 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2021-11-23
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADNOC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | SPECIFICATION FOR OFFSHORE PIPELINE AND RISER INSTALLATION – REV-A1 | 2136-N-SP-0314 | E1279-TS-PLW-L-0019 | B1 |  |  | 2022-02-15 | E-MAIL
2
3
4
5
6
7
8
9
10
11
12
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADNOC APPROVAL CODE : (1) ACCEPTED; (2) ACCEPTED WITH COMMENTS; (2A) ACCEPTED WITH MINOR COMMENTS;
(3) NOT ACCEPTED, REVISE & RESUBMIT; (4) FOR INFORMATION

## Documents - Pipeline & Cable
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
|  | EPC FOR UMM SHAIF LONG TERM DEVELOPMENT PHASE-1 (USLTDP1) PROJECT | [11 empty] | ADNOC DOC. No. :
|  | NPCC PROJECT NO. 2035 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2022-03-17
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADNOC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPE STACKING ANALYSIS REPORT | 2035-NN-RP-001 | AD-26-G-64000 | 1 | 2 | 2023-12-25 | 2023-03-17 | CSE-2035-PMT-T-007 | 2023-03-27 | 2035-NPCC-ADNOC-T-00748 | 2023-04-11 | E1372-E-O-T-EPC-IFR-001265 | 2 | 2023-03-27 | 2035-NPCC-MWS-T-0004
|  |  |  | 2 | 2 |  | 2023-08-16 | CSE-2035-PMT-T-013 | 2023-08-16 | 2035-NPCC-ADNOC-T-01192 | 2023-08-24 | E1372-E-O-T-EPC-IFA-001835 | 1 | 2023-08-18 | 2035-NPCC-MWS-T-0047 | 2023-11-09 | SAF185-MCE-NPCC-T-040 | Approved
|  |  |  | 3 | 2 |  | 2023-11-14 | CSE-2035-PMT-T-031 | 2023-11-14 | 2035-NPCC-ADNOC-T-01463 | 2023-11-30 | E1372-E-O-T-EPC-IFC-001039 | 1 | 2023-11-14 | 2035-NPCC-MWS-T-0080 | 2024-02-23 | SAF185-MCE-NPCC-T-062 | Approved
2 | PIPELAY INSTALLATION REPORT FOR 16" WF PIPELINE FROM US-159A TO US-12B (PL-1) | 2035-NN-RP-002 | AD-768/767-G-64000 | 1 | 2 | 2024-01-04 | 2023-12-08 | CSE-2035-PMT-T-036 | 2023-12-15 | 2035-NPCC-ADNOC-T-01530 | 2024-01-09 | E1372-E-O-T-EPC-IFR-001878 | 2 | 2023-12-15 | 2035-NPCC-MWS-T-0094 | 2024-02-09 | SAF185-MCE-NPCC-T-056 SAF185-MCE-NPCC-T-057 | accepted with comments
|  |  |  | 2 | 2 |  | 2024-03-25 | CSE-2035-PMT-T-055 | 2024-03-28 | 2035-NPCC-ADNOC-T-01897 | 2024-04-29 | E1372-E-O-T-EPC-IFA-002136 | 1 | 28/03/2024 | 2035-NPCC-MWS-T-0131 | 2024-05-29 | SAF185-MCE-NPCC-T-073 | HOLD | CRS SENT TO MWS ON 31.05 PK
|  |  |  | CRS | [9 empty] | 31/05/2024 | 2035-NMDC-MWS-T-0155 | 2024-07-20 | SAF185-MCE-NPCC-T-083 | HOLD
|  |  |  | 3 | 2 |  | 2025-10-22 | CSE-2035-PMT-T-189 | 2025-10-22 | 2035-NMDC-ADNOC-T-04388 | 2025-11-21 | E1372-E-O-T-EPC-IFA-002752 | 3 | 2025-10-22 | 2035-NMDC-MWS-T-0363 | 2025-11-06 | SAF185-MCE-NPCC-T-202 | Approved
|  |  |  | 4 | 2 |  | 2026-01-16 | CSE-2035-PMT-T-240 | 2026-01-19 | 2035-NMDC-ADNOC-T-04804 | 20-0122026 | E1372-E-O-T-EPC-IFA-002820 | 1 | 2026-01-19 | 2035-NMDC-MWS-T-0447 | 2026-01-29 | SAF185-MCE-NPCC-T-218 | 1 - Approved
3 | PIPELAY INSTALLATION REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-12B TO USSC-RP1 (PL-2) | 2035-NN-RP-003 | AD-767/552-G-64000 | 1 | 2 | 2024-01-12 | 2024-02-27 | CSE-2035-PMT-T-048 | 2024-02-27 | 2035-NPCC-ADNOC-T-01764 | 2024-03-14 | E1372-E-O-T-EPC-IFR-002027 | 2 | 2024-02-27 | 2035-NPCC-MWS-T-0116 | 2024-03-13 | SAF185-MCE-NPCC-T-065 | accepted with comments
|  |  |  | 2 | 2 |  | 2024-03-25 | CSE-2035-PMT-T-056 | 2024-03-28 | 2035-NPCC-ADNOC-T-01896 | 2024-04-29 | E1372-E-O-T-EPC-IFA-002136 | 1 | 28/03/2024 | 2035-NPCC-MWS-T-0130 | 2024-05-29 | SAF185-MCE-NPCC-T-073 | accepted with comments | CRS SENT TO MWS ON 31.05 PK
|  |  |  | CRS | [9 empty] | 31/05/2024 | 2035-NMDC-MWS-T-0154 | 2024-07-20 | SAF185-MCE-NPCC-T-083 | HOLD
|  |  |  | 3 | 2 |  | 2025-11-28 | CSE-2035-PMT-T-205 | 2025-12-03 | 2035-NMDC-ADNOC-T-04580 | 2025-12-24 | E1372-E-O-T-EPC-IFA-002774 | 1 | 2025-12-03 | 2035-NMDC-MWS-T-0396 | 2025-12-11 | SAF185-MCE-NPCC-T-210 | Approved
4 | PIPELAY INSTALLATION REPORT FOR 16" WF PIPELINE FROM US-142A TO USSC-RP1 (PL-3) | 2035-NN-RP-004 | AD-769/552-G-64000 | 1 | 2 | 2024-01-24 | 2024-06-24 | CSE-2035-PMT-T-078 | 2024-06-25 | 2035-NMDC-ADNOC-T-02363 | 2024-07-16 | E1372-E-O-T-EPC-IFR-002338 | 2 | 2024-06-25 | 2035-NPCC-MWS-T-0164 | 2024-10-08 | SAF185-MCE-NPCC-T-107 | HOLD
|  |  |  | 2 | 2 |  | 2025-02-01 | CSE-2035-PMT-T-137 | 2025-02-03 | 2035-NMDC-ADNOC-T-03459 | 2025-02-19 | E1372-E-O-T-EPC-IFR-002757 | 1 | 2025-02-03 | 2035-NMDC-MWS-T-0256 | 2025-02-07 | SAF185-MCE-NPCC-T-146 | Approved
5 | PIPELAY INSTALLATION REPORT FOR 16" WF SUBSEA PIPELINE FROM US-19B TO US-153A (PL-4) | 2035-NN-RP-005 | AD-774/770-G-64000 | 1 | 2 | 2024-02-16 | 2024-12-28 | CSE-2035-PMT-T-126 | 2024-12-30 | 2035-NMDC-ADNOC-T-03298 | 2025-01-17 | E1372-E-O-T-EPC-IFR-002713 | 1 | 2024-12-30 | 2035-NMDC-MWS-T-0243 | 2025-01-23 | SAF185-MCE-NPCC-T-142 | Approved
|  |  |  | 2 | 2 |  |  | CSE-2035-PMT-T-270 | 2026-03-18 | 2035-NMDC-ADNOC-T-05118 | 2026-04-20 | E1372-E-O-T-EPC-IFA-002854 | 1 | 2026-03-18 | 2035-NMDC-MWS-T-0498 | 2026-03-24 | SAF185-MCE-NPCC-T-223 | 1 - Approved
|  |  |  | 3 | 2 |  | 2026-08-24 | CSE-2035-PMT-T-358 | 2026-08-25 | 2035-NMDC-ADNOC-T-05634 | 2026-08-27 | E1372-E-O-T-EPC-IFA-002928 | 1 | 2026-08-25 | 2035-NMDC-MWS-T-0645 | 2026-08-27 | SAF185-MCE-NPCC-T-252 | 1 - Approved
|  |  |  | 4 | 3 |  | 2026-08-31 | CSE-2035-PMT-T-360 | 2026-08-31 | 2035-NMDC-ADNOC-T-05654 |  |  |  | 2026-08-31 | 2035-NMDC-MWS-T-0653
6 | PIPELAY INSTALLATION REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-153A TO USSC-RP1 (PL-5) | 2035-NN-RP-006 | AD-770/552-G-64000 | 1 | 2 | 2024-02-04 | 2023-09-22 | CSE-2035-PMT-T-021 | 2023-09-22 | 2035-NPCC-ADNOC-T-01268 | 2023-10-20 | E1372-E-O-T-EPC-IFR-001718 | 2 | 2023-09-22 | 2035-NPCC-MWS-T-0060 | 2023-11-09 | SAF185-MCE-NPCC-T-040 | Approved
|  |  |  | 2 | 2 |  | 2023-12-25 | CSE-2035-PMT-T-039 | 2023-12-26 | 2035-NPCC-ADNOC-T-01582 | 2024-01-29 | E1372-E-O-T-EPC-IFR-002013 | 2 | 2023-12-26 | 2035-NPCC-MWS-T-0096 | 2024-02-09 | SAF185-MCE-NPCC-T-057 | Approved
|  |  |  | 3 | 2 |  | 2024-03-26 | CSE-2035-PMT-T-054 | 2024-03-27 | 2035-NPCC-ADNOC-T-01585 | 2024-04-29 | E1372-E-O-T-EPC-IFA-002135 | 1 | 2024-03-27 | 2035-NPCC-MWS-T-0127 | 2024-05-29 | SAF185-MCE-NPCC-T-073 | Approved
|  |  |  | 4 | 3 | IFC | 2024-07-15 | CSE-2035-PMT-T-087 | 2024-07-16 | 2035-NMDC-ADNOC-T-02481 | 2024-08-01 | E1372-E-O-T-EPC-IFC-002232 | 1 | 2024-07-16 | 2035-NPCC-MWS-T-0174 | 2024-07-20 | SAF185-MCE-NPCC-T-083 | Approved
|  |  |  | 5 | 3 | IFC | 2025-03-11 | CSE-2035-PMT-T-144 | 2025-03-13 | 2035-NMDC-ADNOC-T-03602 | 2025-05-20 | E1372-E-O-T-EPC-IFC-003024 | 1 | 2025-03-13 | 2035-NMDC-MWS-T-0266 | 2025-03-19 | SAF185-MCE-NPCC-T-154 | Approved
7 | PIPELAY INSTALLATION REPORT FOR 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) | 2035-NN-RP-007 | AD-771/772-G-64000 | 1 | 2 | 2024-04-08 | 2025-09-08 | CSE-2035-PMT-T-178 | 2025-09-08 | 2035-NMDC-ADNOC-T-04214 | 2025-09-26 | E1372-E-O-T-EPC-IFR-003062 | 1 | 2025-09-08 | 2035-NMDC-MWS-T-0347 | 2025-09-16 | SAF185-MCE-NPCC-T-198 | Approved
8 | PIPELAY INSTALLATION REPORT FOR 18" WF PIPELINE FROM HP2 TO USSC-RP1 (PL-7) | 2035-NN-RP-008 | AD-772/552-G-64000 | 1 | 2 | 2024-04-20 | 2024-08-30 | CSE-2035-PMT-T-100 | 2024-08-30 | 2035-NMDC-ADNOC-T-02745 | 20/09/2024 | E1372-E-O-T-EPC-IFR-002476 | 2 | 2024-08-30 | 2035-NPCC-MWS-T-0190 | 2024-10-07 | SAF185-MCE-NPCC-T-106 | Approved
|  |  |  | 2 | 2 |  | 2025-04-16 | CSE-2035-PMT-T-150 | 2025-04-16 | 2035-NMDC-ADNOC-T-03720 | 2025-05-20 | E1372-E-O-T-EPC-IFA-002645 | 1 | 2025-04-16 | 2035-NMDC-MWS-T-0280 | 2025-04-21 | SAF185-MCE-NPCC-T-159 | Approved
9 | PIPELAY INSTALLATION REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM HP3 TO USSC-RP1 (PL-8) | 2035-NN-RP-009 | AD-773/552-G-64000 | 1 | 2 | 2024-02-23 | 2205-08-20 | CSE-2035-PMT-T-175 | 2205-08-20 | 2035-NMDC-ADNOC-T-04145 | 2025-11-21 | E1372-E-O-T-EPC-IFR-003118 | 3 | 2205-08-20 | 2035-NMDC-MWS-T-0341 | 2025-09-16 | SAF185-MCE-NPCC-T-198 | Approved
10 | PIPELAY INSTALLATION REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) | 2035-NN-RP-010 | AD-552/773-G-64000 | 1 | 2 | 2024-03-03 | 2025-12-06 | CSE-2035-PMT-T-213 | 2025-12-08 | 2035-NMDC-ADNOC-T-04627 | 2025-12-24 | E1372-E-O-T-EPC-IFR-003167 | 1 | 2025-12-08 | 2035-NMDC-MWS-T-0405 | 2025-12-10 | SAF185-MCE-NPCC-T-209 | Approved
11 | PIPELAY INSTALLATION REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) | 2035-NN-RP-011 | AD-773/772-G-64000 | 1 | 2 | 2024-03-12 | 2025-02-25 | CSE-2035-PMT-T-146 | 2025-03-26 | 2035-NMDC-ADNOC-T-03643 | 2025-05-20 | E1372-E-O-T-EPC-IFR-002891 | 1 | 2025-03-27 | 2035-NMDC-MWS-T-0269 | 2025-04-15 | SAF185-MCE-NPCC-T-158 | Approved
|  |  |  | 2 | 2 |  | 2026-04-13 | CSE-2035-PMT-T-279 | 2026-04-15 | 2035-NMDC-ADNOC-T-05187 | 2026-04-20 | E1372-E-O-T-EPC-IFA-002854 | 1 | 2026-04-15 | 2035-NMDC-MWS-T-0518 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
12 | PIPELAY INSTALLATION REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) | 2035-NN-RP-012 | AD-772/771-G-64000 | 1 | 2 | 2024-03-25 | 2026-02-12 | CSE-2035-PMT-T-251 | 2026-02-16 | 2035-NMDC-ADNOC-T-04975 | 2026-03-17 | E1372-E-O-T-EPC-IFR-003232 | 3 | 2026-02-16 | 2035-NMDC-MWS-T-0467
|  |  |  | 2 | 2 |  | 2026-03-05 | CSE-2035-PMT-T-260 | 2026-03-09 | 2035-NMDC-ADNOC-T-05057 | 2026-03-30 | E1372-E-O-T-EPC-IFA-002845 | 4 | 2026-03-09 | 2035-NMDC-MWS-T-0483 | 2026-03-09 | SAF185-MCE-NPCC-T-221 | 1 - Approved
13 | SUBSEA CABLE LAYING ANALYSIS REPORT BY SAFEEN PEARL | 2035-NN-RP-013 | AD-770/774-G-64000 | 1 | 2 | 2024-02-29 | 2025-01-15 | CSE-2035-PMT-T-131 | 2025-01-16 | 2035-NMDC-ADNOC-T-03403 | 2025-02-04 | E1372-E-O-T-EPC-IFR-002730 | 1 | 2025-01-16 | 2035-NMDC-MWS-T-0249 | 2025-02-13 | SAF185-MCE-NPCC-T-148 | Approved
14 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM US-1216 TO US153A(CC-3) - CB-2 | 2035-NN-RP-014 | AD-424/770-G-64000 | 1 | 2 | 2024-02-23
15 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM US-142A TO US218(CC-8) - CB-3 | 2035-NN-RP-015 | AD-769/426-G-64000 | 1 | 2 | 2024-03-26
16 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM US-159A TO US-12B(CC-11) - CB-7 | 2035-NN-RP-016 | AD-768/767-G-64001 | 1 | 2 | 2024-02-08
17 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM US-19B TO HP-1(CC-5) - CB-8 | 2035-NN-RP-017 | AD-774/771-G-64000 | 1 | 2 | 2024-03-06
18 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM HP1 TO HP2(CC-6) - CB-9 | 2035-NN-RP-018 | AD-771/772-G-64001 | 1 | 2 | 2024-03-13 | The highlighted documents are not required
19 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM HP-2 TO US-142A(CC-7) - CB-10 | 2035-NN-RP-019 | AD-772/769-G-64000 | 1 | 2 | 2024-03-20
20 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM USSC-RP1 TO HP3(CC-2) - CB-11 | 2035-NN-RP-020 | AD-552/773-G-64001 | 1 | 2 | 2024-04-17
21 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM USSC-RP1 TO HP3(CC-1) - CB-12 | 2035-NN-RP-021 | AD-552/773-G-64002 | 1 | 2 | 2024-04-09
22 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM USSC-PDP TO WHT- GI-1(CC-13) TO US-128 - CB-13 | 2035-NN-RP-022 | AD-775/274-G-64000 | 1 | 2 | 2024-04-01
23 | SUBSEA CABLE LAYING ANALYSIS REPORT FROM USSC-PDP TO WHT- GP-1(CC-14) TO US-159A - CB-14 | 2035-NN-RP-023 | AD-776/768-G-64000 | 1 | 2 | 2024-01-31
24 | Pipelay Installation Report for 16" HP Oil Subsea Pipeline from HP3 to USSC-RP1 (PL-8) by DLB 1000 | 2035-NN-RP-024 | AD-552-G-64000 | 1 | 2 | 2024-03-14
25 | SPOOL LIFT ANALYSIS REPORT FOR 16” WELL FLUID PIPELINE FROM US-159A TO US-12B (PL-1) | 2035-NN-RP-025 | AD-768/767-G-64002 | 1 | 2 | 2024-02-09 | 2026-06-11 | CSE-2035-PMT-T-326 | 2026-06-12 | 2035-NMDC-ADNOC-T-05381 | 2026-06-16 | E1372-E-O-T-EPC-IFR-003332 | 1 | 2026-06-12 | 2035-NMDC-MWS-T-0586 | 2026-06-15 | SAF185-MCE-NPCC-T-239 | Approved
26 | SPOOL LIFT ANALYSIS REPORT FOR 16" WELL FLUID PIPELINE FROM US-12B TO USSC-RP1 (PL-2) | 2035-NN-RP-026 | AD-767/552-G-64001 | 1 | 2 | 2024-02-20 | 2026-05-21 | CSE-2035-PMT-T-317 | 2026-05-22 | 2035-NMDC-ADNOC-T-05330 | 2026-06-10 | E1372-E-O-T-EPC-IFR-003327 | 1 | 2026-05-22 | 2035-NMDC-MWS-T-0568
|  |  |  | 2 | 2 |  | 2026-06-16 | CSE-2035-PMT-T-327 | 2026-06-16 | 2035-NMDC-ADNOC-T-05411 | 2026-06-30 | E1372-E-O-T-EPC-IFA-002891 | 1 | 2026-06-16 | 2035-NMDC-MWS-T-0589 | 2026-06-29 | SAF185-MCE-NPCC-T-241 | Approved
27 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-142A TO USSC-RP1 (PL-3) | 2035-NN-RP-027 | AD-769/552-G-64001 | 1 | 2 | 2024-02-26 | 2025-12-03 | CSE-2035-PMT-T-208 | 2025-12-03 | 2035-NMDC-ADNOC-T-04589 | 2025-12-12 | E1372-E-O-T-EPC-IFR-003152 | 2 | 2025-12-03 | 2035-NMDC-MWS-T-0398 | 2025-12-04 | SAF185-MCE-NPCC-T-207 | Approved
|  |  |  | 2 | 3 |  |  |  | 2026-02-18 | PMT SENT TO CLIENT DIRECT | 2026-02-26 | E1372-E-O-T-EPC-IFI-000498
28 | SPOOL LIFT ANALYSIS REPORT FOR 16” WELL FLUID PIPELINE FROM US-19B TO US-153A (PL-4) | 2035-NN-RP-028 | AD-774/770-G-64001 | 1 | 2 | 2024-03-15 | 2026-06-25 | CSE-2035-PMT-T-329 | 2026-06-25 | 2035-NMDC-ADNOC-T-05417 | 2026-07-06 | E1372-E-O-T-EPC-IFR-003350 | 1 | 2026-06-25 | 2035-NMDC-MWS-T-0591 | 2026-06-29 | SAF185-MCE-NPCC-T-241 | HOLD
|  |  |  | 2 | 2 |  | 2026-07-17 | CSE-2035-PMT-T-338 | 2026-07-20 | 2035-NMDC-ADNOC-T-05504 | 2026-09-03 | E1372-E-O-T-EPC-IFA-002932 | 1 | 2026-07-20 | 2035-NMDC-MWS-T-0622 | 2026-07-22 | SAF185-MCE-NPCC-T-248 | 1 - Approved
29 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM US-153A TO USSC-RP1 (PL-5) | 2035-NN-RP-029 | AD-770/552-G-64001 | 1 | 2 | 2024-03-08 | 2025-12-04 | CSE-2035-PMT-T-212 | 2025-12-05 | 2035-NMDC-ADNOC-T-04609 | 2025-12-12 | E1372-E-O-T-EPC-IFR-003150 | 3 | 2025-12-05 | 2035-NMDC-MWS-T-0402 | 2025-12-11 | SAF185-MCE-NPCC-T-210 | Approved
|  |  |  | 2 | 2 |  | 2025-12-16 | CSE-2035-PMT-T-221 | 2025-12-17 | 2035-NMDC-ADNOC-T-04669 | 2025-12-24 | E1372-E-O-T-EPC-IFA-002776 | 1 | 2025-12-17 | 2035-NMDC-MWS-T-0416 | 2025-12-18 | SAF185-MCE-NPCC-T-213 | 1 - Approved
30 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) | 2035-NN-RP-030 | AD-771/772-G-64002 | 1 | 2 | 2024-05-07
31 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 18" HP OIL SUBSEA PIPELINE FROM HP2 TO USSC-RP1 (PL-7) | 2035-NN-RP-031 | AD-772/552-G-64001 | 1 | 2 | 2024-05-24 | 2026-01-08 | CSE-2035-PMT-T-234 | 2026-01-09 | 2035-NMDC-ADNOC-T-04763 | 2026-01-16 | E1372-E-O-T-EPC-IFR-003193 | 1 | 2026-01-09 | 2035-NMDC-MWS-T-0439 | 2026-02-02 | SAF185-MCE-NPCC-T-219 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-02-03 | CSE-2035-PMT-T-245 | 2026-02-04 | 2035-NMDC-ADNOC-T-04905 | 2026-02-18 | E1372-E-O-T-EPC-IFA-002818 | 3 | 2026-02-04 | 2035-NMDC-MWS-T-0456 | 2026-02-16 | SAF185-MCE-NPCC-T-220 | 1 - Approved
|  |  |  | 3 | 2 |  | 2026-03-05 | CSE-2035-PMT-T-258 | 2026-03-06 | 2035-NMDC-ADNOC-T-05051 | 2026-03-11 | E1372-E-O-T-EPC-IFA-002833 | 1 | 2026-03-06 | 2035-NMDC-MWS-T-0481 | 2026-03-09 | SAF185-MCE-NPCC-T-221 | 1 - Approved
|  |  |  | 4 | 2 |  | 2026-07-30 | CSE-2035-PMT-T-345 | 2026-07-30 | 2035-NMDC-ADNOC-T-05539 | 2026-08-14 | E1372-E-O-T-EPC-IFA-002921 | 1 | 2026-07-30 | 2035-NMDC-MWS-T-0623 | 2026-08-03 | SAF185-MCE-NPCC-T-249 | 1 - Approved
32 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" HP OIL SUBSEA PIPELINE FROM HP3 TO USSC-RP1 (PL-8) | 2035-NN-RP-032 | AD-773/552-G-64001 | 1 | 2 | 2024-06-18 | 2026-05-25 | CSE-2035-PMT-T-318 | 2026-06-01 | 2035-NMDC-ADNOC-T-05333 | 2026-06-19 | E1372-E-O-T-EPC-IFR-003338 | 1 | 01-06-2026 01-07-2026 16-07-2026 | 2035-NMDC-MWS-T-0571 2035-NMDC-MWS-T-0600 2035-NMDC-MWS-T-0617 | 10-06-2026 02-07-2026 22-07-2026 | SAF185-MCE-NPCC-T-237 SAF185-MCE-NPCC-T-243 SAF185-MCE-NPCC-T-248 | 1 - Approved | MCE's Response sent to PMT on 30/06/2026 & 15-07-2026
|  |  |  | 2 | 2 |  | 2026-07-31 | CSE-2035-PMT-T-348 | 2026-08-04 | 2035-NMDC-ADNOC-T-05558 | 2026-08-14 | E1372-E-O-T-EPC-IFA-002920 | 1 | 2026-08-04 | 2035-NMDC-MWS-T-0629 | 2026-08-05 | SAF185-MCE-NPCC-T-250 | 1 - Approved
33 | SPOOL LIFT ANALYSIS REPORT FOR 16” WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) | 2035-NN-RP-033 | AD-552/773-G-64003 | 1 | 2 | 2024-04-07 | 2026-06-04 | CSE-2035-PMT-T-321 | 2026-06-08 | 2035-NMDC-ADNOC-T-05366 | 2026-06-16 | E1372-E-O-T-EPC-IFR-003332 | 1 | 2026-06-08 | 2035-NMDC-MWS-T-0579 | 2026-06-10 | SAF185-MCE-NPCC-T-238 | 1 - Approved
34 | SPOOL LIFT ANALYSIS REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) | 2035-NN-RP-034 | AD-773/772-G-64001 | 1 | 2 | 2024-06-11 | 2026-05-01 | CSE-2035-PMT-T-305 | 2026-05-04 | 2035-NMDC-ADNOC-T-05254 | 2026-05-18 | E1372-E-O-T-EPC-IFR-003311 | 3 | 2026-05-04 | 2035-NMDC-MWS-T-0553 | 2026-05-13 | SAF185-MCE-NPCC-T-231 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-06-08 | CSE-2035-PMT-T-324 | 2026-06-09 | 2035-NMDC-ADNOC-T-05368 | 2026-06-23 | E1372-E-O-T-EPC-IFA-002887 | 1 | 2026-06-09 | 2035-NMDC-MWS-T-0581 | 2026-06-22 | SAF185-MCE-NPCC-T-240 | approved
35 | SPOOL LIFT ANALYSIS REPORT FOR 16” WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) | 2035-NN-RP-035 | AD-772/771-G-64001 | 1 | 2 | 2024-06-05 | 02-07-26 | CSE-2035-PMT-T-332 | 03-07-26 | 2035-NMDC-ADNOC-T-05444 |  |  |  | 03-07-26 | 2035-NMDC-MWS-T-0602 | 06-07-26 | SAF185-MCE-NPCC-T-244 | 1 - Approved
36 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES & REELS ON CARGO BARGE (ASTRO-3302) (TRIP-1) | 2035-NN-RP-036 | AD-26-G-64001 | 1 | 2 | 2023-11-23 | 2024-07-10 | CSE-2035-PMT-T-085 | 2024-07-10 | 2035-NMDC-ADNOC-T-02471 | 2024-07-24 | E1372-E-O-T-EPC-IFR-002360 | 1 | 2024-07-10 | 2035-NPCC-MWS-T-0171 | 2024-07-15 | SAF185-MCE-NPCC-T-082 | 1 - Approved
37 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE (SAFEEN B - 281) (TRIP-2) | 2035-NN-RP-037 | AD-26-G-64002 | 1 | 2 | 2023-12-14 | 2025-04-10 | CSE-2035-PMT-T-149 | 2025-04-15 | 2035-NMDC-ADNOC-T-03702 | 2025-04-20 | E1372-E-O-T-EPC-IFR-002895 | 1 | 2025-04-15 | 2035-NPCC-MWS-T-0274 | 2025-04-15 | SAF185-MCE-NPCC-T-158 | 1 - Approved
38 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES & REELS ON CARGO BARGE SAFEEN B-283 (TRIP-3) | 2035-NN-RP-038 | AD-26-G-64003 | 1 | 2 | 2024-01-11 | 2025-05-20 | CSE-2035-PMT-T-155 | 2025-05-20 | 2035-NMDC-ADNOC-T-03842 | 2025-06-18 | E1372-E-O-T-EPC-IFR-002936 | 1 | 2025-05-20 | 2035-NPCC-MWS-T-0290 | 2025-05-29 | SAF185-MCE-NPCC-T-166 | 1 - Approved
39 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON PFC-02 - TRIP-3 | 2035-NN-RP-039 | AD-26-G-64004 | 1 | 2 | 2024-02-01 | 2026-03-18 | CSE-2035-PMT-T-269 | 2026-03-18 | 2035-NMDC-ADNOC-T-05115 | 2026-03-30 | E1372-E-O-T-EPC-IFR-003259 | 1 | 2026-03-18 | 2035-NMDC-MWS-T-0495 | 2026-03-24 | SAF185-MCE-NPCC-T-223 | 1 - Approved
40 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-5) | 2035-NN-RP-040 | AD-26-G-64005 | 1 | 2 | 2024-02-29
41 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (TRIP-6) | 2035-NN-RP-041 | AD-26-G-64006 | 1 | 2 | 2024-03-14
42 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS AND RISERS ON CARGO BARGE ES-282 | 2035-NN-RP-042 | AD-26-G-64007 | 1 | 2 | 2024-01-24 | 2025-10-14 | CSE-2035-PMT-T-185
43 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SPOOLS ON CARGO BARGE (AESEN-2812) | 2035-NN-RP-043 | AD-26-G-64008 | 1 | 2 | 2024-01-24 | 2026-04-29 | CSE-2035-PMT-T-297 | 2026-04-29 | 2035-NMDC-ADNOC-T-05241 | 2026-05-22 | E1372-E-O-T-EPC-IFR-003313 | 1 | 2026-04-29 | 2035-NMDC-MWS-T-0545 | 2026-05-06 | SAF185-MCE-NPCC-T-230 | approved
44 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF RISERS, SPOOLS & RISER PROTECTOR ON CARGO BAGE (AESEN-2811) | 2035-NN-RP-044 | AD-26-G-64009 | 1 | 2 |  | 2026-05-01 | CSE-2035-PMT-T-303 | 2026-05-04 | 2035-NMDC-ADNOC-T-05252 | 2026-05-22 | E1372-E-O-T-EPC-IFR-003315 | 1 | 2026-05-04 | 2035-NMDC-MWS-T-0551 | 2026-05-06 | SAF185-MCE-NPCC-T-230 | approved
45 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE (CB-7) | 2035-NN-RP-045 | AD-26-G-64010 | 1 | 2 | 2023-06-21 | 2023-09-05 | CSE-2035-PMT-T-018 | 2023-09-07 | 2035-NPCC-ADNOC-T-01245 | 2023-09-21 | E1372-E-O-T-EPC-IFR-001668 | 4 | 2023-09-07 | 2035-NPCC-MWS-T-0056 | 2023-10-16 | SAF185-MCE-NPCC-T-038 | 3 - HOLD
46 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE (CB-8) | 2035-NN-RP-046 | AD-26-G-64011 | 1 | 2 | 2023-07-11
47 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS - (TRIP-3) | 2035-NN-RP-047 | AD-26-G-64012 | 1 | 2 | 2023-08-15
48 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE (ES-282) | 2035-NN-RP-048 | AD-26-G-64113 | 1 | 2 |  | 2023-10-30 | CSE-2035-PMT-T-027 | 2023-10-30 | 2035-NPCC-ADNOC-T-01388 | 2023-11-11 | E1372-E-O-T-EPC-IFR-001799 | 1 | 2023-10-31 | 2035-NPCC-MWS-T-0074 | 2023-11-16 | SAF185-MCE-NPCC-T-043 | 3 - HOLD
|  |  |  | 2 | 3 |  | 2024-05-28 | CSE-2035-PMT-T-072 | 2024-05-28 | 2035-NMDC-ADNOC-T-02187 | 2024-05-31 | E1372-E-O-T-EPC-IFC-001924 | 1 | 2024-05-28 | 2035-NPCC-MWS-T-0150 | 2024-06-07 | SAF185-MCE-NPCC-T-075 | approved
49 | J-TUBE LIFTING ANALYSIS REPORT AT US-216 AND US-218 | 2035-NN-RP-049 | AD-26-G-64114 | 1 | 2 |  | 2023-11-02 | CSE-2035-PMT-T-029 | 2023-11-03 | 2035-NPCC-ADNOC-T-01408 | 2023-11-15 | E1372-E-O-T-EPC-IFR-001791 | 1
|  |  |  | 2 | IFC |  | 2023-11-23 | CSE-2035-PMT-T-034 | 2023-11-27 | 2035-NPCC-ADNOC-T-01490 | 2023-12-12 | E1372-E-O-T-EPC-IFC-001079 | 1 | 2023-11-27 | 2035-NPCC-MWS-T-0075 |  | SAF185-MCE-NPCC-T-054 | Approved
50 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE (ASTRO-250) | 2035-NN-RP-050 | AD-26-G-64115 | 1 | 2 |  | 2024-01-01 | CSE-2035-PMT-T-040 | 2024-01-02 | 2035-NPCC-ADNOC-T-01597 | 2024-03-12 | E1372-E-O-T-EPC-IFR-002016 | 1 | 2024-01-02 | 2035-NPCC-MWS-T-0098 |  | SAF185-MCE-NPCC-T-053 | Approved
51 | WELD REPAIR ANALYSIS REPORT | 2035-NN-RP-051
52 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE (ASTRO-304) | 2035-NN-RP-052 | AD-26-G-64117 | 1 | 2 |  | 2024-02-14 | CSE-2035-PMT-T-044 | 2024-02-15 | 2035-NPCC-ADNOC-T-01734 | 2024-02-29 | E1372-E-O-T-EPC-IFR-001989 | 1 | 2024-02-15 | 2035-NPCC-MWS-T-0114 | 2024-02-21 | SAF185-MCE-NPCC-T-060 | Approved
53 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE (GAC-68) | 2035-NN-RP-053 | AD-26-G-64118 | 1 | 2 |  | 2024-11-13 | CSE-2035-PMT-T-116 | 2024-11-14 | 2035-NMDC-ADNOC-T-03151 | 2024-11-18 | E1372-E-O-T-EPC-IFR-002604 | 1 | 2024-11-14 | 2035-NMDC-MWS-T-0227 | 2024-11-15 | SAF185-MCE-NPCC-T-123 | Approved
54 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS ON CARGO BARGE ASTRO-251 | 2035-NN-RP-054 | AD-26-G-64119 | 1 | 2 |  | 2024-12-12 | CSE-2035-PMT-T-121 | 2024-12-12 | 2035-NMDC-ADNOC-T-03240 | 2025-01-09 | E1372-E-O-T-EPC-IFR-002667 | 1 | 2024-12-12 | 2035-NMDC-MWS-T-0239 | 2024-12-13 | SAF185-MCE-NPCC-T-135 | Approved
55 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES & REELS ON CARGO BARGE (SAFEEN-B-282) | 2035-NN-RP-055 | AD-26-G-64120 | 1 | 2 |  | 2025-03-05 | CSE-2035-PMT-T-142 | 2025-03-06 | 2035-NMDC-ADNOC-T-03579 | 2025-03-28 | E1372-E-O-T-EPC-IFR-002821 | 1 | 2025-03-06 | 2035-NMDC-MWS-T-0261 | 2025-03-20 | SAF185-MCE-NPCC-T-155 | 3 - HOLD
56 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF MATTRESS ON CARGO BARGE (ASTRO-251) | 2035-NN-RP-056 | AD-26-G-64121 | 1 | 2 |  | 2025-03-06 | CSE-2035-PMT-T-143 | 2025-03-07 | 2035-NMDC-ADNOC-T-03586 | 2025-03-28 | E1372-E-O-T-EPC-IFR-002821 | 1 | 2025-03-07 | 2035-NMDC-MWS-T-0264 | 2025-03-18 | SAF185-MCE-NPCC-T-153 | 1 - Approved
57 | PIPELAY INSTALLATION REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) BY SAPURA 1200 | 2035-NN-RP-057 | AD-26-G-64122 | 1 | 2 |  | 2025-05-22 | CSE-2035-PMT-T-157 | 2025-05-23 | 2035-NMDC-ADNOC-T-03855 | 2025-07-14 | E1372-E-O-T-EPC-IFR-002966 | 1 | 2025-05-23 | 2035-NMDC-MWS-T-0293 | 2025-07-07 | SAF185-MCE-NPCC-T-171 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-02-18 | CSE-2035-PMT-T-254 | 2026-02-18 | 2035-NMDC-ADNOC-T-05006 | 2026-03-17 | E1372-E-O-T-EPC-IFA-002827 | 3 | 2026-02-18 | 2035-NMDC-MWS-T-0471
|  |  |  | 3 | 2 |  | 2026-03-05 | CSE-2035-PMT-T-259 | 2026-03-06 | 2035-NMDC-ADNOC-T-05050 | 2026-03-09 | E1372-E-O-T-EPC-IFA-002832 | 1 | 2026-03-06 | 2035-NMDC-MWS-T-0480 | 2026-03-09 | SAF185-MCE-NPCC-T-221 | 1 - Approved
58 | Pipelay Installation Report for 16" Well Fluid Subsea Pipeline from US-153A to USSC-RP1 (PL-5) by Sapura 1200 | 2035-NN-RP-058 | AD-26-G-64123 | 1 | 2 |  | 2025-06-17 | CSE-2035-PMT-T-160 | 2025-06-18 | 2035-NMDC-ADNOC-T-03927 | 2025-07-14 | E1372-E-O-T-EPC-IFR-002967 | 1 | 2025-06-18 | 2035-NMDC-MWS-T-0297 | 2025-07-11 | SAF185-MCE-NPCC-T-172 | 1 - Approved
|  |  |  | 2 | 2 |  | 2025-08-21 | CSE-2035-PMT-T-177 | 2025-08-22 | 2035-NMDC-ADNOC-T-04159 | 2025-11-21 | E1372-E-O-T-EPC-IFC-003213 | 1 | 2025-08-22 | 2035-NMDC-MWS-T-0343 | 2025-09-16 | SAF185-MCE-NPCC-T-198 | Approved
59 | PIPELAY INSTALLATION REPORT FOR 16" WF PIPELINE FROM US-142A TO USSC-RP1 (PL-3) BY SAPURA 1200. | 2035-NN-RP-059 | AD-26-G-64124 | 1 | 2 |  | 2025-05-28 | CSE-2035-PMT-T-158 | 2025-05-28 | 2035-NMDC-ADNOC-T-03876 | 2025-07-14 | E1372-E-O-T-EPC-IFR-002968 | 1 | 2025-05-28 | 2035-NMDC-MWS-T-0296 | 2025-07-07 | SAF185-MCE-NPCC-T-171 | 1 - Approved
60 | PIPELAY INSTALLATION REPORT FOR 18" WF PIPELINE FROM HP2 TO USSC-RP1 (PL-7) BY SAPURA 1200. | 2035-NN-RP-060 | AD-26-G-64125 | 1 | 2 |  | 2025-06-24 | CSE-2035-PMT-T-162 | 2025-06-25 | 2035-NMDC-ADNOC-T-03953 | 2025-07-14 | E1372-E-O-T-EPC-IFR-002969 | 1 | 2025-06-25 | 2035-NMDC-MWS-T-0303 | 2025-07-11 | SAF185-MCE-NPCC-T-172 | 1 - Approved
61 | Pipelay Installation Report for 16" Well Fluid Subsea Pipeline from US-19B to US-153A (PL-4) by Sapura 1200 | 2035-NN-RP-061 | AD-26-G-64126 | 1 | 2 |  | 2025-07-15 | CSE-2035-PMT-T-167 | 2025-07-16 | 2035-NMDC-ADNOC-T-04022 | 2025-12-10 | E1372-E-O-T-EPC-IFR-003149 | 1 | 2025-07-16 | 2035-NMDC-MWS-T-0316 | 2025-09-16 | SAF185-MCE-NPCC-T-198 | Approved
|  |  |  | 2 | 2 |  | 2026-02-12 | CSE-2035-PMT-T-252 | 2026-03-05 | 2035-NMDC-ADNOC-T-05044 | 2026-03-30 | E1372-E-O-T-EPC-IFA-002845 | 4 | 2026-03-05 | 2035-NMDC-MWS-T-0477 | 2026-03-09 | SAF185-MCE-NPCC-T-221 | 1 - Approved
62 | Pipelay Installation Report for 16" HP Oil Subsea Pipeline from US-12B to USSC-RP1 (PL-2) by Sapura 1200 | 2035-NN-RP-062 | AD-26-G-64127 | 1 | 2 |  | 2025-08-07 | CSE-2035-PMT-T-171 | 2025-08-07 | 2035-NMDC-ADNOC-T-04097 | 2025-11-21 | E1372-E-O-T-EPC-IFR-003118 | 3 | 2025-08-07 | 2035-NMDC-MWS-T-0330 | 2025-09-16 | SAF185-MCE-NPCC-T-198 | Approved
63 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES & REELS ON CARGO BARGE SAFEEN B-284 (TRIP-3) | 2035-NN-RP-063 | AD-26-G-64128 | 1 | 2 |  | 2025-07-07 | CSE-2035-PMT-T-163
64 | PIPELAY INSTALLATION REPORT FOR 16” WF PIPELINE FROM US-159A TO US-12B (PL-1) BY SAPURA 1200 | 2035-NN-RP-064 | AD-26-G-64129 | 1 | 2 |  | 2025-09-08 | CSE-2035-PMT-T-119 | 2025-09-08 | 2035-NMDC-ADNOC-T-04219 | 2025-09-26 | E1372-E-O-T-EPC-IFR-003062 | 1 | 2025-09-08 | 2035-NMDC-MWS-T-0348 | 2025-09-12 | SAF185-MCE-NPCC-T-195 | 1 - Approved
65 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES & REELS ON CARGO BARGE (CREST-2802) | 2035-NN-RP-065 | AD-26-G-64130 | 1 | 2 |  | 2025-08-20 | CSE-2035-PMT-T-176 | 2025-08-20 | 2035-NMDC-ADNOC-T-04155 | 2025-09-15 | E1372-E-O-T-EPC-IFR-003052 | 1 | 2025-08-20 | 2035-NMDC-MWS-T-0342 | 2025-09-16 | SAF185-MCE-NPCC-T-198 | Approved
66 | DAVIT LIFT ANALYSIS REPORT FOR 16” WF PIPELINE FROM US-142A TO USSC RP-1 (PL-3) | 2035-NN-RP-066 | AD-26-G-64131 | 1 | 2 |  | 2025-10-30 | CSE-2035-PMT-T-191 | 2025-11-01 | 2035-NMDC-ADNOC-T-04443 | 2025-11-12 | E1372-E-O-T-EPC-IFR-003107 | 1 | 2025-11-01 | 2035-NMDC-MWS-T-0366 | 2025-11-06 | SAF185-MCE-NPCC-T-202 | Approved
|  |  |  | 2 | 2 |  | 2025-12-08 | CSE-2035-PMT-T-215 | 2025-12-09 | 2035-NMDC-ADNOC-T-04631 | 2025-12-22 | E1372-E-O-T-EPC-IFA-002770 | 1 | 2025-12-09 | 2035-NMDC-MWS-T-0408 | 2025-12-11 | SAF185-MCE-NPCC-T-210 | Approved
|  |  |  | 3 | 2 |  | 2025-12-23 | CSE-2035-PMT-T-226 | 2025-12-24 | 2035-NMDC-ADNOC-T-04707 | 2026-01-06 | E1372-E-O-T-EPC-IFA-002786 | 1 | 2025-12-24 | 2035-NMDC-MWS-T-0424
67 | DAVIT LIFT ANALYSIS REPORT FOR 16” WF PIPELINE FROM US-153A TO USSC RP-1 (PL-5) | 2035-NN-RP-067 | AD-26-G-64132 | 1 | 2 |  | 2025-11-08 | CSE-2035-PMT-T-194 | 2025-11-10 | 2035-NMDC-ADNOC-T-04469 | 2025-11-26 | E1372-E-O-T-EPC-IFR-003130 | 1 | 2025-11-10 | 2035-NMDC-MWS-T-0368 | 2025-11-20 | SAF185-MCE-NPCC-T-205 | 1 - Approved
|  |  |  | 2 | 2 |  | 2025-12-24 | CSE-2035-PMT-T-228 | 2025-12-24 | 2035-NMDC-ADNOC-T-04708 | 2026-01-06 | E1372-E-O-T-EPC-IFA-002787 | 1 | 2025-12-24 | 2035-NMDC-MWS-T-0425
68 | Pipelay Installation Report for 18" HP Oil Subsea Pipeline from HP1 to HP2 (PL-6) by SAFEEN 3000 | 2035-NN-RP-068 | AD-26-G-64133 | 1 | 2 |  | 2025-11-03 | CSE-2035-PMT-T-188 | 2025-12-30 | 2035-NMDC-ADNOC-T-04725 | 2026-01-12 | E1372-E-O-T-EPC-IFR-003184 | 1 | 2025-12-30 | 2035-NMDC-MWS-T-0430 | 2026-01-06 | SAF185-MCE-NPCC-T-216 | 1 - Approved | Reminder sent to pmt on 30/12/25
|  |  |  | 2 | 2 |  | 2026-01-27 | CSE-2035-PMT-T-243 | 2026-01-28 | 2035-NMDC-ADNOC-T-04841 | 2026-02-02 | E1372-E-O-T-EPC-IFA-002811 | 1 | 2026-01-28 | 2035-NMDC-MWS-T-0453 | 2026-01-29 | SAF185-MCE-NPCC-T-218 | 1 - Approved
69 | Pipelay Installation Report for 16" HP Oil Subsea Pipeline from HP3 to USSC-RP1 (PL-8) by SAFEEN 3000 | 2035-NN-RP-069 | AD-26-G-64134 | 1 | 2 |  | 2025-11-20 | CSE-2035-PMT-T-203 | 2025-11-20 | 2035-NMDC-ADNOC-T-04523 | 2025-12-10 | E1372-E-O-T-EPC-IFR-003149 | 1 | 2025-11-20 | 2035-NMDC-MWS-T-0383 | 2025-11-26 | SAF185-MCE-NPCC-T-206 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-01-21 | CSE-2035-PMT-T-241 | 2026-01-21 | 2035-NMDC-ADNOC-T-04814 | 2026-02-20 | E1372-E-O-T-EPC-IFA-002820 | 1 | 2026-01-21 | 2035-NMDC-MWS-T-0450 | 2026-01-29 | SAF185-MCE-NPCC-T-218 | 1 - Approved
70 | DAVIT LIFT ANALYSIS REPORT FOR 18” WF PIPELINE FROM HP2 TO USSC RP-1 (PL-7) | 2035-NN-RP-070 | AD-26-G-64135 | 1 | 2 |  | 2025-12-04 | CSE-2035-PMT-T-211 | 2025-12-08 | 2035-NMDC-ADNOC-T-04626 | 2025-12-24 | E1372-E-O-T-EPC-IFR-003166 | 1 | 2025-12-08 | 2035-NMDC-MWS-T-0404 | 2025-12-10 | SAF185-MCE-NPCC-T-209 | Approved
71 | DAVIT LIFT ANALYSIS REPORT FOR 16” WF PIPELINE FROM HP3 TO USSC RP-1 (PL-8) | 2035-NN-RP-071 | AD-26-G-64136 | 1 | 2 |  | 2025-12-08 | CSE-2035-PMT-T-216 | 2025-12-09 | 2035-NMDC-ADNOC-T-04630 | 2025-12-22 | E1372-E-O-T-EPC-IFR-003164 | 1 | 2025-12-09 | 2035-NMDC-MWS-T-0407 | 2025-12-10 | SAF185-MCE-NPCC-T-209 | Approved
|  |  |  | 2 | 2 |  | 2026-03-30 | CSE-2035-PMT-T-276 | 2026-03-01 | 2035-NMDC-ADNOC-T-05149 | 2026-04-07 | E1372-E-O-T-EPC-IFA-002851 | 1 | 2026-04-01 | 2035-NMDC-MWS-T-0505 | 2026-04-03 | SAF185-MCE-NPCC-T-225 | accepted
72 | DAVIT LIFT ANALYSIS REPORT FOR 16” WF PIPELINE FROM US-12B TO USSC RP-1 (PL-2) | 2035-NN-RP-072 | AD-26-G-64137 | 1 | 2 |  | 2025-12-26 | CSE-2035-PMT-T-230 | 2025-12-26 | 2035-NMDC-ADNOC-T-04720 | 2026-03-18 | E1372-E-O-T-EPC-IFR-003252 | 1 | 2025-12-26 | 2035-NMDC-MWS-T-0429 | 2026-01-06 | SAF185-MCE-NPCC-T-216 | 1 - Approved
73 | SPOOL LIFT ANALYSIS REPORT FOR 16" HP OIL SUBSEA PIPELINE AT US 142A (PL-3) AND US 153A (PL-5) | 2035-NN-RP-073 | AD-26-G-64138 | 1 | 2 |  | 2025-12-18 | CSE-2035-PMT-T-222 | 2025-12-18 | 2035-NMDC-ADNOC-T-04675 | 2026-01-06 | E1372-E-O-T-EPC-IFR-003176 | 1 | 2025-12-18 | 2035-NMDC-MWS-T-0419 | 2025-12-23 | SAF185-MCE-NPCC-T-214 | 1 - Approved
74 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES & REELS ON CARGO BARGE SAFEEN B-281 (TRIP-7) | 2035-NN-RP-074 | AD-26-G-64139 | 1 | 2 |  | 2025-12-31 | CSE-2035-PMT-T-224 | 2026-01-02 | 2035-NMDC-ADNOC-T-04733 | 2026-01-27 | E1372-E-O-T-EPC-IFR-003206 | 1 | 2026-01-02 | 2035-NMDC-MWS-T-0432 | 2026-01-29 | SAF185-MCE-NPCC-T-218 | 1 - Approved
75 | Pipelay Installation Report for 16" Water Injection Subsea Pipeline from USSC-RP1 to HP3 (PL-9) by SAFEEN 3000 | 2035-NN-RP-075 | AD-26-G-64140 | 1 | 2 |  | 2026-01-16 | CSE-2035-PMT-T-239 | 2026-01-19 | 2035-NMDC-ADNOC-T-04805 | 2026-01-28 | E1372-E-O-T-EPC-IFR-003207 | 5 | 2026-01-19 | 2035-NMDC-MWS-T-0448 | 2026-01-29 | SAF185-MCE-NPCC-T-218 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-03-10 | CSE-2035-PMT-T-264 | 2026-03-10 | 2035-NMDC-ADNOC-T-05064 | 2026-04-20 | E1372-E-O-T-EPC-IFR-003288 | 1 | 2026-03-10 | 2035-NMDC-MWS-T-0486
76 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES (PL-6 & PL-8) ON ASTRO-251 | 2035-NN-RP-076 | AD-26-G-64141 | 1 | 2 |  | 2026-02-09 | CSE-2035-PMT-T-250 | 2026-02-11 | 2035-NMDC-ADNOC-T-04936 | 2026-02-20 | E1372-E-O-T-EPC-IFR-003223 | 1 | 2026-02-11 | 2035-NMDC-MWS-T-0459 | 2026-02-16 | SAF185-MCE-NPCC-T-220 | 1 - Approved
77 | DAVIT LIFT ANALYSIS REPORT FOR PL-8 AND PL-9 PIPELINE AT HP3 PLATFORM WITH DLB-1000 | 2035-NN-RP-077 | AD-26-G-64142 | 1 | 2 |  | 2026-02-24 | CSE-2035-PMT-T-257 | 2026-02-25 | 2035-NMDC-ADNOC-T-05023 | 2026-03-18 | E1372-E-O-T-EPC-IFR-003252 | 1 | 2026-02-25 | 2035-NMDC-MWS-T-0473
|  |  |  | 2 | 2 |  | 2026-05-13 | CSE-2035-PMT-T-309 | 2026-05-13 | 2035-NMDC-ADNOC-T-05281 | 2026-05-18 | E1372-E-O-T-EPC-IFA-002871 | 1 | 13-05-2026 06-07-2206 | 2035-NMDC-MWS-T-0559 2035-NMDC-MWS-T-0608 | 29-05-2026 06-07-2026 | SAF185-MCE-NPCC-T-232 SAF185-MCE-NPCC-T-244 | 1 - Approved
|  |  |  | 3 | 3 |  | 2026-09-07 | CSE-2035-PMT-T-362 | 2026-09-09 | 2035-NMDC-ADNOC-T-05672 |  |  |  | 2026-09-09 | 2035-NMDC-MWS-T-0659
78 | DAVIT LIFT ANALYSIS REPORT FOR 16” WF PIPELINE FROM HP3 TO USSC RP-1 (PL-8) AT USSC RP-1 BY DLB 1000 | 2035-NN-RP-078 | AD-552-G-64143 | 1 | 2 |  | 2026-03-09 | CSE-2035-PMT-T-262 | 2026-03-10 | 2035-NMDC-ADNOC-T-05059 | 2026-03-18 | E1372-E-O-T-EPC-IFR-003252 | 1 | 2026-03-10 | 2035-NMDC-MWS-T-0484
|  |  |  | 2 |  |  | 2026-04-22 | CSE-2035-PMT-T-285 | 2026-04-22 | 2035-NMDC-ADNOC-T-05216 | 2026-05-07 | E1372-E-O-T-EPC-IFA-002865 | 1 | 2026-04-22 | 2035-NMDC-MWS-T-0532 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
79 | DAVIT LIFT ANALYSIS REPORT FOR PL-2 PIPELINE AT US-12B PLATFORM WITH DLB-1000 | 2035-NN-RP-079 | AD-767-G-64144 | 1 | 2 |  | 2026-03-13 | CSE-2035-PMT-T-266 | 2026-03-17 | 2035-NMDC-ADNOC-T-05094 | 2026-04-07 | E1372-E-O-T-EPC-IFR-003269 | 1 | 2026-03-17 | 2035-NMDC-MWS-T-0491 | 2026-03-24 | SAF185-MCE-NPCC-T-223 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-05-13 | CSE-2035-PMT-T-310 | 2026-05-13 | 2035-NMDC-ADNOC-T-05282 | 2026-07-07 | E1372-E-O-T-EPC-IFA-002893 | 1 | 13-05-2026 06-07-2026 | 2035-NMDC-MWS-T-0560 2035-NMDC-MWS-T-0607 | 29-05-2026 06-07-2026 | SAF185-MCE-NPCC-T-232 SAF185-MCE-NPCC-T-244 | 1 - Approved
80 | PIPELAY INSTALLATION REPORT FOR 16" WATER INJECTION SUBSEA PIPELINE HP2 TO HP1 (PL-11) BY SAFEEN-3000 | 2035-NN-RP-080 | AD-772/771-G-64145 | 1 | 2 |  | 2026-03-23 | CSE-2035-PMT-T-272 | 2026-03-24 | 2035-NMDC-ADNOC-T-05134 | 2026-04-20 | E1372-E-O-T-EPC-IFR-003287 | 1 | 2026-03-24 | 2035-NMDC-MWS-T-0501 | 2026-03-26 | SAF185-MCE-NPCC-T-224 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-08-04 | CSE-2035-PMT-T-350 | 2026-08-05 | 2035-NMDC-ADNOC-T-05565 | 2026-09-03 | E1372-E-O-T-EPC-IFA-002932 | 1 | 2026-08-05 | 2035-NMDC-MWS-T-0632
81 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES & REELS ON ASTRO-251 | 2035-NN-RP-081 | AD-26-G-64146 | 1 | 2 |  | 2026-03-18 | CSE-2035-PMT-T-267 | 2026-03-25 | 2035-NMDC-ADNOC-T-05135 | 2026-04-06 | E1372-E-O-T-EPC-IFR-003265 | 1 | 2026-03-25 | 2035-NMDC-MWS-T-0502 | 2026-03-26 | SAF185-MCE-NPCC-T-224 | 1 - Approved
82 | Pipelay Installation Report for 16" Well Fluid Pipeline from US-159A to US-12B (PL-1) by DLS 4200 | 2035-NN-RP-082 | AD-768/767-G-64147
83 | Pipelay Installation Report for 16" Well Fluid Subsea Pipeline from US-19B to US-153A (PL-4) by DLS 4200 | 2035-NN-RP-083 | AD-774/770-G-64148
84 | Pipelay Installation Report for 16” Water Injection Subsea Pipeline from HP2 to HP1 (PL-11) by DLS 4200 | 2035-NN-RP-084 | AD-772/771-G-64149
85 | DAVIT LIFT ANALYSIS REPORT FOR PL-2 PIPELINE AT USSC RP-1 PLATFORM WITH DLB-1000 | 2035-NN-RP-085 | AD-552-G-64150 | 1 | 2 |  | 2026-05-14 | CSE-2035-PMT-T-312 | 2026-05-15 | 2035-NMDC-ADNOC-T-05290 | 2026-07-07 | E1372-E-O-T-EPC-IFR-003351 | 1 | 15-05-2026 06-07-2026 | 2035-NMDC-MWS-T-0561 2035-NMDC-MWS-T-0606 | 29-05-20206 06-07-2026 | SAF185-MCE-NPCC-T-232 SAF185-MCE-NPCC-T-244 | 1 - Approved
86 | SPOOL LIFT ANALYSIS REPORT FOR 18” HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) | 2035-NN-RP-086 | AD-771/772-G-64151 | 1 | 2 |  | 2026-04-17 | CSE-2035-PMT-T-286 | 2026-04-20 | 2035-NMDC-ADNOC-T-05202 | 2026-05-04 | E1372-E-O-T-EPC-IFR-003303 | 3 | 2026-04-20 | 2035-NMDC-MWS-T-0526 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-05-07 | CSE-2035-PMT-T-308 | 2026-05-07 | 2035-NMDC-ADNOC-T-05264 | 2026-05-18 | E1372-E-O-T-EPC-IFA-002871 | 1 | 2026-05-07 | 2035-NMDC-MWS-T-0556 | 2026-05-13 | SAF185-MCE-NPCC-T-231 | 1 - Approved
|  |  |  | 3 | 2 |  | 2026-07-28 | CSE-2035-PMT-T-342
87 | DAVIT LIFT ANALYSIS REPORT FOR PL-7 PIPELINE AT USSC RP-1 PLATFORM WITH DLB-1000 | 2035-NN-RP-087 | AD-552-G-64152 | 1 |  |  | 2026-04-22 | CSE-2035-PMT-T-284 | 2026-04-22 | 2035-NMDC-ADNOC-T-05217 | 2026-05-06 | E1372-E-O-T-EPC-IFR-003305 | 1 | 2026-04-22 | 2035-NMDC-MWS-T-0533 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
88 | SPOOL LIFT ANALYSIS REPORT FOR 18” WELL FLUID PIPELINE FROM HP2 TO USSC-RP1 (PL-7) | 2035-NN-RP-088 | AD-772/552-G-64153 | 1 | 2 |  | 2026-04-22 | CSE-2035-PMT-T-291 | 2026-04-23 | 2035-NMDC-ADNOC-T-05222 | 2026-04-30 | E1372-E-O-T-EPC-IFR-003301 | 1 | 2026-04-23 | 2035-NMDC-MWS-T-0534 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
89 | SPOOL LIFT ANALYSIS REPORT FOR 16” WELL FLUID PIPELINE FROM HP3 TO USSC-RP1 (PL-8) | 2035-NN-RP-089 | AD-773/552-G-64154 | 1 | 2 |  | 2026-04-28 | CSE-2035-PMT-T-295 | 2026-04-29 | 2035-NMDC-ADNOC-T-05232 | 2026-05-12 | E1372-E-O-T-EPC-IFR-003308 | 3 | 2026-04-30 | 2035-NMDC-MWS-T-0538 | 2026-05-13 | SAF185-MCE-NPCC-T-231 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-05-15 | CSE-2035-PMT-T-314 | 2026-05-15 | 2035-NMDC-ADNOC-T-05292 | 2026-06-03 | E1372-E-O-T-EPC-IFA-002875 | 1 | 2026-05-15 | 2035-NMDC-MWS-T-0563 | 2026-05-29 | SAF185-MCE-NPCC-T-234 | 1 - Approved
|  |  |  | 3 | 2 |  | 2026-06-05 | CSE-2035-PMT-T-322 | 2026-06-08 | 2035-NMDC-ADNOC-T-05364 | 2026-06-16 | E1372-E-O-T-EPC-IFA-002883 | 1 | 2026-06-08 | 2035-NMDC-MWS-T-0578 | 2026-06-10 | SAF185-MCE-NPCC-T-237 | 1 - Approved
90 | PIPELAY INSTALLATION REPORT FOR 16" WELL FLUID PIPELINE FROM US-159A TO US-12B (PL-1) BY DLB 750 | 2035-NN-RP-090 | AD-768/767-G-64155 | 1 | 2 |  | 2026-05-18 | CSE-2035-PMT-T-315 | 2026-05-22 | 2035-NMDC-ADNOC-T-05336 |  |  |  | 2026-05-22 | 2035-NMDC-MWS-T-0570 | 2026-05-29 | SAF185-MCE-NPCC-T-233 | HOLD
91 | Pipelay Installation Report for 16" Well Fluid Subsea Pipeline from US-19B to US-153A (PL-4) by DLB 750 | 2035-NN-RP-091 | AD-26-774/770-64156 | 1 | 2 |  | 2026-06-09 | CSE-2035-PMT-T-325 | 2026-06-11 | 2035-NMDC-ADNOC-T-05377 | 2026-06-23 | E1372-E-O-T-EPC-IFR-003339 | 1 | 2026-06-11 | 2035-NMDC-MWS-T-0583 | 2026-06-22 | SAF185-MCE-NPCC-T-240 | HOLD
92 | Air Bag Lift Analysis Report for 16” WF Pipeline from US-HP3 to USSC-RP1 (PL-8) | 2035-NN-RP-092 | AD-773/552-G-64157 | 1 | 2 |  | 2026-06-24 | CSE-2035-PMT-T-328 | 2026-06-30 | 2035-NMDC-ADNOC-T-05429 | 2026-08-19 | E1372-E-O-T-EPC-IFR-003395 | 1 | 2026-06-30 | 2035-NMDC-MWS-T-0598 | 020-07-2026 | SAF185-MCE-NPCC-T-243 | 1 - Approved
93 | SPOOL & RISER LIFT ANALYSIS REPORT FOR 16" WELL FLUID PIPELINE FROM US-12B TO USSC-RP1 (PL-2) @ USSC-RP1 | 2035-NN-RP-093 | AD-767-552-G-64158 | 1 | 2 |  | 2026-07-15 | CSE-2035-PMT-T-339 | 2026-07-16 | 2035-NMDC-ADNOC-T-05481 | 2026-07-30 | E1372-E-O-T-EPC-IFR-003372 | 1 | 2026-07-16 | 2035-NMDC-MWS-T-0618 | 2026-07-22 | SAF185-MCE-NPCC-T-248 | 1 - Approved
1 | ANALYSIS OF 9M SIMPLY SUPPORTED GANGWAY | OFO-GEN-X-RP-017-R-0
2 | Specification for Pipeline, Riser and Cable Installation | 2035-NN-SP-001 | [16 empty] | Email dtd 24/08/2022-YH
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADNOC APPROVAL CODE : (1) ACCEPTED; (2) ACCEPTED WITH COMMENTS; (2A) ACCEPTED WITH MINOR COMMENTS;
(3) NOT ACCEPTED, REVISE & RESUBMIT; (4) FOR INFORMATION

## Documents - Naval Marine
|  | ADNOC OFFSHORE | [12 empty] | NPCC DOC. No.:
|  | EPC FOR UMM SHAIF LONG TERM DEVELOPMENT PHASE-1 (USLTDP1) PROJECT | [12 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 2035 | [12 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (NAVAL & MARINE) | [12 empty] | DATE : |  |  |  | 2022-03-17
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADNOC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | REMAINING DAYS | NPCC |  |  |  | ADNOC OFFSHORE |  |  | - |  |  |  |  | REMARKS
[8 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[8 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[8 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | MOORING ANALYSIS DURING PIPELAYING OF 16" HP OIL SUBSEA PIPELINE FROM US-159A TO US-12B (PL-1) | 2035-ZZ-CL-001 | AD-768/767-G-64003 | 1 | 2 | 2024-01-04
2 | MOORING ANALYSIS DURING PIPELAYING OF 16" HP OIL SUBSEA PIPELINE FROM US-12B TO USSC-RP1 (PL-2) | 2035-ZZ-CL-002 | AD-767/552-G-64002 | 1 | 2 | 2024-01-12
3 | SAPURA 1200 MOORING ANALYSIS DURING PIPELAYING OF 16" HP PL FROM USSC-RP-1 TO US-142A (PL-3) | 2035-ZZ-CL-003 | AD-769/552-G-64003 | 1 | 2 | 2024-01-24 |  | 2025-06-17 | CSE-2035-PMT-T-161 | 2025-06-18 | 2035-NMDC-ADNOC-T-03926 | 2025-07-21 | E1372-E-O-T-EPC-IFR-002979 | 1 | 2025-07-14 | 2035-NPCC-MWS-T-0313 | 2025-07-15 | SAF185-MCE-NPCC-T-174 | 1 - Approved
|  |  |  | 2 | 2 |  |  | 2025-10-06 | CSE-2035-PMT-T-181 | 2025-10-06 | 2035-NMDC-ADNOC-T-04316 | 2025-11-12 | E1372-E-O-T-EPC-IFR-003107 | 1 | 2025-10-06 | 2035-NMDC-MWS-T-0360 | 2025-10-10 | SAF185-MCE-NPCC-T-200 | 1 - Approved
4 | MOORING ANALYSIS DURING PIPELAYING OF 16" HP OIL SUBSEA PIPELINE FROM US-19B TO US-153A (PL-4) | 2035-ZZ-CL-004 | AD-774/770-G-64002 | 1 | 2 | 2024-02-16
5 | SAPURA 1200 MOORING ANALYSIS DURING PIPELAYING OF 16" HP PL FROM USSC-RP-1 TO US-153A (PL-5) | 2035-ZZ-CL-005 | AD-770/552-G-64002 | 1 | 2 | 2024-02-04 |  | 2025-08-12 | CSE-2035-PMT-T-173 | 2025-08-14 | 2035-NMDC-ADNOC-T-04115 | 2025-11-12 | E1372-E-O-T-EPC-IFR-003107 | 1 | 2025-08-13 | 2035-NMDC-MWS-T-0337 | 2025-09-12 | SAF185-MCE-NPCC-T-195 | 1 - Approved
6 | MOORING ANALYSIS DURING PIPELAYING OF 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) | 2035-ZZ-CL-006 | AD-771/772-G-64003 | 1 | 2 | 2024-04-08
7 | SUPURA 1200 MOORING ANALYSIS DURING PIPELAYING OF 18" HP FROM USSC-RP1 TO HP2 (PL-7) | 2035-ZZ-CL-007 | AD-772/552-G-64002 | 1 | 2 | 2024-04-20 |  | 2025-05-21 | CSE-2035-PMT-T-156 | 2025-05-23 | 2035-NMDC-ADNOC-T-03856 | 2025-07-14 | E1372-E-O-T-EPC-IFR-002970 | 1 | 2025-05-23 | 2035-NPCC-MWS-T-0294 | 2025-07-07 | SAF185-MCE-NPCC-T-171 | 1 - Approved
8 | SAFEEN3000 MOORING ANALYSIS DURING PIPELAYING OF 16" HP OIL SUBSEA PIPELINE FROM HP3 TO USSC-RP1 (PL-8) | 2035-ZZ-CL-008 | AD-773/552-G-64002 | 1 | 2 | 2024-02-23 |  | 2026-04-10 | CSE-2035-PMT-T-278 | 2026-04-15 | 2035-NMDC-ADNOC-T-05191 | 2026-04-27 | E1372-E-O-T-EPC-IFR-003297 | 1 | 2026-04-15 | 2035-NMDC-MWS-T-0522 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
9 | SAPURA 1200 MOORING ANALYSIS DURING PIPELAYING OF 16" WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) | 2035-ZZ-CL-009 | AD-552/773-G-64004 | 1 | 2 | 2024-03-03 |  | 2025-12-06 | CSE-2035-PMT-T-214 | 2025-12-08 | 2035-NMDC-ADNOC-T-04628 | 2026-01-11 | E1372-E-O-T-EPC-IFR-003191 | 1 | 2025-12-08 | 2035-NMDC-MWS-T-0406 | 2025-12-10 | SAF185-MCE-NPCC-T-209 | Approved
10 | SAPURA-1200 MOORING ANALYSIS DURING PIPELAYING OF 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) | 2035-ZZ-CL-010 | AD-773/772-G-64002 | 1 | 2 | 2024-03-12 |  | 2025-10-27 | CSE-2035-PMT-T-190 | 2025-10-29 | 2035-NMDC-ADNOC-T-04417 | 2025-11-12 | E1372-E-O-T-EPC-IFR-003107 | 1 | 2025-10-29 | 2035-NMDC-MWS-T-0364 | 2025-11-07 | SAF185-MCE-NPCC-T-202 | 1 - Approved
11 | MOORING ANALYSIS DURING PIPELAYING OF 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) | 2035-ZZ-CL-011 | AD-772/771-G-64002 | 1 | 2 | 2024-03-25
12 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" HP OIL SUBSEA PIPELINE FROM US-159A TO US-12B (PL-1) | 2035-ZZ-CL-012 | AD-768/767-G-64004 | 1 | 2 | 2024-02-09
13 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" HP OIL SUBSEA PIPELINE FROM US-12B TO USSC-RP1 (PL-2) | 2035-ZZ-CL-013 | AD-767/552-G-64003 | 1 | 2 | 2024-02-20
14 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" HP OIL SUBSEA PIPELINE FROM US-142A TO USSC-RP1 (PL-3) | 2035-ZZ-CL-014 | AD-769/552-G-64004 | 1 | 2 | 2024-02-26
15 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" HP OIL SUBSEA PIPELINE FROM US-19B TO US-153A (PL-4) | 2035-ZZ-CL-015 | AD-774/770-G-64003 | 1 | 2 | 2024-03-15
16 | SAFEEN-3000 MOORING ANALYSIS DURING PL-5 RISER & SPOOL INSTALLATION RP1 | 2035-ZZ-CL-016 | AD-770/552-G-64003 | 1 | 2 | 2024-03-08 |  | 2025-11-11 | CSE-2035-PMT-T-195
17 | MOORING ANALYSIS DURING RISER INSTALLATION OF 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) | 2035-ZZ-CL-017 | AD-771/772-G-64004 | 1 | 2 | 2024-05-07
18 | SAFEEN-3000 MOORING ANALYSIS DURING PL-7 RISER & SPOOL INSTALLATION AT RP-1 | 2035-ZZ-CL-018 | AD-772/552-G-64003 | 1 | 2 | 2024-05-24 |  | 2025-12-22 | CSE-2035-PMT-T-223 | 2025-12-22 | 2035-NMDC-ADNOC-T-04689 | 2026-01-16 | E1372-E-O-T-EPC-IFR-003192 | 1 | 2025-12-22 | 2035-NMDC-MWS-T-0420 | 2025-12-23 | SAF185-MCE-NPCC-T-214 | 1 - Approved
19 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" HP OIL SUBSEA PIPELINE FROM HP3 TO USSC-RP1 (PL-8) | 2035-ZZ-CL-019 | AD-773/552-G-64003 | 1 | 2 | 2024-06-18
20 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) | 2035-ZZ-CL-020 | AD-552/773-G-64005 | 1 | 2 | 2024-04-07
21 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) | 2035-ZZ-CL-021 | AD-773/772-G-64003 | 1 | 2 | 2024-06-11
22 | MOORING ANALYSIS DURING RISER INSTALLATION OF 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) | 2035-ZZ-CL-022 | AD-772/771-G-64003 | 1 | 2 | 2024-06-05
23 | MOORING ANALYSIS DURING CABLE LAYING FROM US-153A TO US-19B(CC-4) - CB-1 | 2035-ZZ-CL-023 | AD-770/774-G-64001 | 1 | 2 | 2024-02-29
24 | MOORING ANALYSIS DURING CABLE LAYING FROM US-1216 TO US153A(CC-3) - CB-2 | 2035-ZZ-CL-024 | AD-424/770-G-64001 | 1 | 2 | 2024-02-23
25 | MOORING ANALYSIS DURING CABLE LAYING FROM US-142A TO US218(CC-8) - CB-3 | 2035-ZZ-CL-025 | AD-769/426-G-64001 | 1 | 2 | 2024-03-26
26 | MOORING ANALYSIS DURING CABLE LAYING FROM US-159A TO US-12B(CC-11) - CB-7 | 2035-ZZ-CL-026 | AD-768/767-G-64005 | 1 | 2 | 2024-02-08
27 | MOORING ANALYSIS DURING CABLE LAYING FROM US-19B TO HP-1(CC-5) - CB-8 | 2035-ZZ-CL-027 | AD-774/771-G-64001 | 1 | 2 | 2024-03-06
28 | MOORING ANALYSIS DURING CABLE LAYING FROM HP1 TO HP2(CC-6) - CB-9 | 2035-ZZ-CL-028 | AD-771/772-G-64005 | 1 | 2 | 2024-03-13
29 | MOORING ANALYSIS DURING CABLE LAYING FROM HP-2 TO US-142A(CC-7) - CB-10 | 2035-ZZ-CL-029 | AD-772/769-G-64001 | 1 | 2 | 2024-03-20
30 | MOORING ANALYSIS DURING CABLE LAYING FROM USSC-RP1 TO HP3(CC-2) - CB-11 | 2035-ZZ-CL-030 | AD-552/773-G-64006 | 1 | 2 | 2024-04-17
31 | MOORING ANALYSIS DURING CABLE LAYING FROM USSC-RP1 TO HP3(CC-1) - CB-12 | 2035-ZZ-CL-031 | AD-552/773-G-64007 | 1 | 2 | 2024-04-09
32 | MOORING ANALYSIS DURING CABLE LAYING FROM USSC-PDP TO WHT- GI-1(CC-13) TO US-128 - CB-13 | 2035-ZZ-CL-032 | AD-775/274-G-64001 | 1 | 2 | 2024-04-01
33 | MOORING ANALYSIS DURING CABLE LAYING FROM USSC-PDP TO WHT- GP-1(CC-14) TO US-159A - CB-14 | 2035-ZZ-CL-033 | AD-776/768-G-64001 | 1 | 2 | 2024-01-31
34 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON SAFEEN B-282 (PL-3) TRIP-1 | 2035-ZZ-CL-034 | AD-26-G-64013 | 1 | 2 | 2023-12-31 |  | 2024-07-10 | CSE-2035-PMT-T-085 | 2024-07-10 | 2035-NMDC-ADNOC-T-02472 | 2024-07-24 | E1372-E-O-T-EPC-IFR-002361 | 1 | 2024-07-10 | 2035-NPCC-MWS-T-0172 | 2024-07-15 | SAF185-MCE-NPCC-T-082 | 1 - Approved
|  |  |  | 2 | 2 |  |  | 2025-03-05 | CSE-2035-PMT-T-142 | 2025-03-06 | 2035-NMDC-ADNOC-T-03581 | 2025-03-28 | E1372-E-O-T-EPC-IFR-002820 | 1 | 2025-03-06 | 2035-NMDC-MWS-T-0262 | 2025-03-18 | SAF185-MCE-NPCC-T-153 | 1 - Approved
35 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON SAFEEN B281 (PL-3 & PL-5) TRIP-2 | 2035-ZZ-CL-035 | AD-26-G-64014 | 1 | 2 | 2024-01-16 |  | 2025-04-10 | CSE-2035-PMT-T-149 | 2025-04-15 | 2035-NMDC-ADNOC-T-03704 | 2025-04-20 | E1372-E-O-T-EPC-IFR-002895 | 1 | 2025-04-14 | 2035-NMDC-MWS-T-0276 | 2025-04-15 | SAF185-MCE-NPCC-T-158 | 1 - Approved
36 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON CREST-2802 (PL-5)-TRIP NO.3 | 2035-ZZ-CL-036 | AD-26-G-64015 | 1 | 2 | 2024-02-11 |  | 2025-05-20 | CSE-2035-PMT-T-155 | 2025-05-20 | 2035-NMDC-ADNOC-T-03843 | 2025-06-18 | E1372-E-O-T-EPC-IFR-002936 | 1 | 2025-05-20 | 2035-NMDC-MWS-T-0291 | 2025-05-29 | SAF185-MCE-NPCC-T-166 | 1 - Approved
|  |  |  | 2 | 2 |  |  | 2025-07-23 | CSE-2035-PMT-T-168 | 2025-07-25 | 2035-NMDC-ADNOC-T-04058 | 2025-11-12 | E1372-E-O-T-EPC-IFR-003107 | 1 | 2025-07-25 | 2035-NMDC-MWS-T-0325 | 2025-07-30 | SAF185-MCE-NPCC-T-179 | 1 - Approved
37 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON SAFEEN-B-284 (PL-5 & PL-7) - TRIP-4 | 2035-ZZ-CL-037 | AD-26-G-64016 | 1 | 2 | 2024-02-24 |  | 2025-09-18 | CSE-2035-PMT-T-180 | 2025-09-18 | 2035-NMDC-ADNOC-T-04250 | 2025-11-12 | E1372-E-O-T-EPC-IFR-003107 | 1 | 2025-09-18 | 2035-NMDC-MWS-T-0352 | 2025-10-09 | SAF185-MCE-NPCC-T-199 | 1 - Approved
38 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON CREST-2802 (PL-7) TRIP-6 | 2035-ZZ-CL-038 | AD-26-G-64017 | 1 | 2 | 2024-03-17 |  | 2025-11-25 | CSE-2035-PMT-T-204 | 2025-11-26 | 2035-NMDC-ADNOC-T-04564 | 2026-01-16 | E1372-E-O-T-EPC-IFR-003190 | 1 | 2025-11-26 | 2035-NMDC-MWS-T-0389 | 2025-12-11 | SAF185-MCE-NPCC-T-211 | 1 - Approved
39 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON ASTRO-252 (PL-6 & PL-8) TRIP-2 (SAFEEN 3000 SOW) | 2035-ZZ-CL-039 | AD-26-G-64018 | 1 | 2 | 2024-03-31 |  | 2026-02-09 | CSE-2035-PMT-T-250 | 2026-02-11 | 2035-NMDC-ADNOC-T-04937 | 2026-02-20 | E1372-E-O-T-EPC-IFR-003223 | 1 | 2026-02-11 | 2035-NMDC-MWS-T-0460 | 2026-02-16 | SAF185-MCE-NPCC-T-220 | 1 - Approved
40 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF RISERS & SPOOLS ONBOARD ES-282 | 2035-ZZ-CL-040 | AD-26-G-64019 | 1 | 2 | 2024-02-05 |  | 2025-10-08 | CSE-2035-PMT-T-184 | 2025-10-08 | 2035-NMDC-ADNOC-T-04334 |  |  |  | 2025-10-08 | 2035-NMDC-MWS-T-0362
41 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON PFC-02 (PL-2 & PL-8) - TRIP-3 (SAFEEN-3000 SOW) | 2035-ZZ-CL-041 | AD-26-G-64020 | 1 | 2 | 2024-02-05 |  | 2026-03-18 | CSE-2035-PMT-T-269 | 2026-03-18 | 2035-NMDC-ADNOC-T-05116 | 2026-03-18 | E1372-E-O-T-EPC-IFR-003260 | 1 | 2026-03-18 | 2035-NMDC-MWS-T-0496 | 2026-03-24 | SAF185-MCE-NPCC-T-223 | 1 - Approved
42 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SPOOLS ON AESEN-2812 | 2035-ZZ-CL-042 | AD-26-G-64021 | 1 | 2 |  |  | 2026-04-29 | CSE-2035-PMT-T-297 | 2026-04-29 | 2035-NMDC-ADNOC-T-05240 | 2026-05-22 | E1372-E-O-T-EPC-IFR-003313 | 1 | 2026-04-29 | 2035-NMDC-MWS-T-0544 | 2026-05-06 | SAF185-MCE-NPCC-T-230 | approved
43 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SLEEPERS ON CB-7 - TRIP-1 | 2035-ZZ-CL-043 | AD-26-G-64022 | 1 | 2 | 2023-06-28 |  | 2023-09-05 | CSE-2035-PMT-T-018 | 2023-09-07 | 2035-NPCC-ADNOC-T-01245 | 2023-09-21 | E1372-E-O-T-EPC-IFR-001668 | 4 | 2023-09-07 | 2035-NPCC-MWS-T-0056 | 2023-10-16 | SAF185-MCE-NPCC-T-038 | 1 - Approved
44 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CC PIPES ON SAFEEN B-282 (PL-9) TRIP-10 | 2035-ZZ-CL-044 | AD-26-G-64023 | 1 | 2 | 2023-07-18 |  | 2026-03-13 | CSE-2035-PMT-T-265 | 2026-03-16 | 2035-NMDC-ADNOC-T-05092 | 2026-04-06 | E1372-E-O-T-EPC-IFR-003266 | 1 | 2026-03-16 | 2035-NMDC-MWS-T-0490 | 2026-03-24 | SAF185-MCE-NPCC-T-223 | 1 - Approved
45 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SPOOLS ON AESEN-2811 | 2035-ZZ-CL-045 | AD-26-G-64024 | 1 | 2 |  |  | 2026-05-01 | CSE-2035-PMT-T-303 | 2026-05-04 | 2035-NMDC-ADNOC-T-05251 | 2026-05-22 | E1372-E-O-T-EPC-IFR-003315 | 1 | 2026-05-04 | 2035-NMDC-MWS-T-0550 | 2026-05-06 | SAF185-MCE-NPCC-T-230 | approved
46 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SLEEPERS ON ES-282 - TRIP-3 | 2035-ZZ-CL-046 | AD-26-G-64025 | 1 | 2 |  |  | 2023-10-30 | CSE-2035-PMT-T-027 | 2023-10-30 | 2035-NPCC-ADNOC-T-01389 | 2023-11-11 | E1372-E-O-T-EPC-IFR-001799 | 1 | 2023-10-31 | 2035-NPCC-MWS-T-0073 | 2023-11-16 | SAF185-MCE-NPCC-T-043 | 3 - HOLD
47 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SLEEPERS ON ASTRO-250 FOR PL-3 | 2035-ZZ-CL-047 | AD-26-G-64026 | 1 | 2 |  |  | 2024-01-01 | CSE-2035-PMT-T-040 | 2024-01-02 | 2035-NPCC-ADNOC-T-01596 | 2024-01-24 | E1372-E-O-T-EPC-IFR-001912 |  | 2024-01-02 | 2035-NPCC-MWS-T-0097 | 2024-01-06 | SAF185-MCE-NPCC-T-053 | approved
48 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF CONCRETE SLEEPERS (PL-3) @ ASTRO-304 | 2035-ZZ-CL-048 | AD-26-G-64027 | 1 | 2 |  |  | 2024-02-14 | CSE-2035-PMT-T-044 | 2024-02-15 | 2035-NPCC-ADNOC-T-01733 | 2024-02-29 | E1372-E-O-T-EPC-IFR-001988 | 1 | 2024-02-15 | 2035-NPCC-MWS-T-0113 | 2024-02-16 | SAF185-MCE-NPCC-T-059 | approved
|  |  |  | 2 | IFC |  |  | 2024-03-04 | CSE-2035-PMT-T-049 | 2024-03-05 | 2035-NPCC-ADNOC-T-01781 | 2024-03-12 | E1372-E-O-T-EPC-IFC-001504 | 1 | 2024-03-05 | 2035-NPCC-MWS-T-0119 | 2024-03-05 | SAF185-MCE-NPCC-T-064 | approved
49 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SLEEPERS (PL-3, PL-2 & PL-1) ON ES-282 | 2035-ZZ-CL-049 | AD-26-G-64028 | 1 | 2 |  |  | 2024-03-13 | CSE-2035-PMT-T-050 | 2024-03-14 | 2035-NPCC-ADNOC-T-01829 | 2024-03-25 | E1372-E-O-T-EPC-IFR-002053 | 1 | 2024-03-14 | 2035-NPCC-MWS-T-0120 | 2024-03-14 | SAF185-MCE-NPCC-T-067 | approved
50 | SEP-750 MOORING ANALYSIS AT CSP-01 | 2035-ZZ-CL-050 | AD-26-G-64029 | 1 | 2 |  |  | 2024-07-29 | CSE-2035-PMT-T-090 | 2025-09-24 | 2035-NMDC-ADNOC-T-02590 | 2025-09-24 | E1372-E-O-T-EPC-IFR-002487 | 1 |  | 2035-NMDC-MWS-T-0181 | 2024-09-12 | SAF185-MCE-NPCC-T-097 | 1 - Approved
|  |  |  | 2 | 2 |  |  | 2024-10-01 | CSE-2035-PMT-T-105 | 2024-10-01 | 2035-NMDC-ADNOC-T-02926 | 2024-10-11 | E1372-E-O-T-EPC-IFR-002522 | 1 | 2024-10-01 | 2035-NMDC-MWS-T-0205 | 2024-10-01 | SAF185-MCE-NPCC-T-104 | approved
51 | DLB-1000 MOORING ANALYSIS AT BST-S13 DECK AND B-26 | 2035-ZZ-CL-051 | AD-26-G-64030 | 1 | 2 |  |  | 2024-10-12 | CSE-2035-PMT-T-111 | 2024-10-14 | 2035-NMDC-ADNOC-T-02991 | 2024-10-29 | E1372-E-O-T-EPC-IFR-002552 | 3 | 2024-10-14 | 2035-NMDC-MWS-T-0214 | 2024-10-17 | SAF185-MCE-NPCC-T-110 | approved
|  |  |  | 2 | 2 |  |  | 2024-11-05 | CSE-2035-PMT-T-113 | 2024-11-06 | 2035-NMDC-ADNOC-T-03080 | 2024-11-27 | E1372-E-O-T-EPC-IFR-002629 | 1 | 2024-11-06 | 2035-NMDC-MWS-T-0223 | 2024-11-08 | SAF185-MCE-NPCC-T-120 | approved
52 | DLB-1000 MOORING ANALYSIS AT US 159-A & US 142-A | 2035-ZZ-CL-052 | AD-26-G-64031 | 1 | 2 |  |  | 2025-01-10 | CSE-2035-PMT-T-129 | 2025-01-13 | 2035-NMDC-ADNOC-T-03391 | 2025-02-03 | E1372-E-O-T-EPC-IFR-002728 | 1 | 2025-01-13 | 2035-NMDC-MWS-T-0247 | 2025-01-24 | SAF185-MCE-NPCC-T-143 | approved
53 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SLEEPERS ON GAC-68- TRIP-11 | 2035-ZZ-CL-053 | AD-26-G-64032 | 1 | 2 |  |  | 2024-11-13 | CSE-2035-PMT-T-116 | 2024-11-14 | 2035-NMDC-ADNOC-T-03150 | 2024-11-18 | E1372-E-O-T-EPC-IFR-002603 | 1 | 2024-11-14 | 2035-NMDC-MWS-T-0226 | 2024-11-15 | SAF185-MCE-NPCC-T-123 | Approved
54 | STABILITY ANALYSIS REPORT DURING TRANSPORTATION OF SLEEPERS ON ASTRO-251 | 2035-ZZ-CL-054 | AD-26-G-64033 | 1 | 2 |  |  | 2024-12-12 | CSE-2035-PMT-T-121 | 2024-12-12 | 2035-NMDC-ADNOC-T-03239 | 2025-01-08 | E1372-E-O-T-EPC-IFR-002666 | 1 | 2024-12-12 | 2035-NMDC-MWS-T-0238 | 2024-12-13 | SAF185-MCE-NPCC-T-135 | Approved
55 | DLB-1000 MOORING ANALYSIS DURING US-153A DECK INSTALLATION | 2035-ZZ-CL-055 | AD-26-G-64034 | 1 | 2 |  |  | 2025-01-24 | CSE-2035-PMT-T-134 | 2025-01-24 | 2035-NMDC-ADNOC-T-03431 | 2025-02-12 | E1372-E-O-T-EPC-IFR-002747 | 1 | 2025-01-24 | 2035-NMDC-MWS-T-0253 | 2025-01-28 | SAF185-MCE-NPCC-T-144 | Approved
56 | SEP-750 MOORING ANALYSIS AT WIP-2 | 2035-ZZ-CL-056 | AD-26-G-64035 | 1 | 2 |  |  | 2025-03-17 | CSE-2035-PMT-T-145 | 2025-03-19 | 2035-NMDC-ADNOC-T-03613 | 2025-04-17 | E1372-E-O-T-EPC-IFR-002845 | 1
57 | DLS-4200 MOORING ANALYSIS AT US-HP-3 DURING DECK INSTALLATION | 2035-ZZ-CL-057 | AD-26-G-64036 | 1 | 2 |  |  | 2025-07-09 | CSE-2035-PMT-T-164 | 2025-07-10 | 2035-NMDC-ADNOC-T-03998 | 2025-08-20 | E1372-E-O-T-EPC-IFR-003019 | 3 | 2025-07-10 | 2035-NMDC-MWS-T-0310 | 2025-07-17 | SAF185-MCE-NPCC-T-173 | comments
|  |  |  | 2 | 2 |  |  | 2025-08-19 | CSE-2035-PMT-T-174 | 2025-08-20 | 2035-NMDC-ADNOC-T-04142 | 2025-09-03 | E1372-E-O-T-EPC-IFR-003039 | 1 | 2025-08-20 | 2035-NMDC-MWS-T-0339 | 2025-08-29 | SAF185-MCE-NPCC-T-189 | Approved
58 | DLB 1000 MOORING ANALYSIS DURING PL-3 RISER & SPOOL INSTALLATION AT RP1 | 2035-ZZ-CL-058 | AD-26-G-64037 | 1 | 2 |  |  | 2025-07-11 | CSE-2035-PMT-T-165 | 2025-07-16 | 2035-NMDC-ADNOC-T-04026 | 2025-08-04 | E1372-E-O-T-EPC-IFR-003001 | 1 | 2025-07-16 | 2035-NMDC-MWS-T-0318 | 2025-07-26 | SAF185-MCE-NPCC-T-178 | Approved
59 | SAFEEN 3000 DURING PL-3 RISER & INSTALLATION AT RP-1 | 2035-ZZ-CL-059 | AD-26-G-64038 | 1 | 2 |  |  | 2025-10-30 | CSE-2035-PMT-T-192 | 2025-10-31 | 2035-NMDC-ADNOC-T-04440 | 2025-11-12 | E1372-E-O-T-EPC-IFR-003107 | 1 | 2025-10-31 | 2035-NMDC-MWS-T-0365 | 06-11-2025 05-12-2025 | SAF185-MCE-NPCC-T-202 SAF185-MCE-NPCC-T-208 | Approved
60 | SAFEEN-3000 MOORING ANALYSIS DURING PL-3 SHIFTING AT US-142A | 2035-ZZ-CL-060 | AD-769-G-64039 | 1 | 2 |  |  | 2025-11-13 | CSE-2035-PMT-T-198 | 2025-11-13 | 2035-NMDC-ADNOC-T-04484 | 2025-12-08 | E1372-E-O-T-EPC-IFR-003143 | 1 | 2025-11-13 | 2035-NMDC-MWS-T-0372 | 2025-12-12 | SAF185-MCE-NPCC-T-212 | Approved
|  |  |  | 2 | 2 |  |  | 2025-12-23 | CSE-2035-PMT-T-227 | 2025-12-24 | 2035-NMDC-ADNOC-T-04703 | 2026-01-16 | E1372-E-O-T-EPC-IFA-002806 | 1 | 2025-12-24 | 2035-NMDC-MWS-T-0423
61 | SAFEEN-3000 MOORING ANALYSIS DURINGCORRIDOR SPOOLS INSTALLATION PL-6 AT HP-1 | 2035-ZZ-CL-061 | AD-771-G-64040 | 1 | 2 |  |  | 2026-03-16 | CSE-2035-PMT-T-268 | 2026-03-18 | 2035-NMDC-ADNOC-T-05101 | 2026-04-07 | E1372-E-O-T-EPC-IFR-003271 | 1 | 2026-03-18 | 2035-NMDC-MWS-T-0494 | 2026-03-24 | SAF185-MCE-NPCC-T-223 | 1 - Approved
62 | DLB-1000 MOORING ANALYSIS DURING PL-6 AND PL-11 CORRIDOR SPOOLS INSTALLATION AT HP-1 | 2035-ZZ-CL-062 | AD-771-G-64041 | 1 | 2 |  |  | 2026-03-24 | CSE-2035-PMT-T-273 | 2026-04-06 | 2035-NMDC-ADNOC-T-05166 | 2026-04-22 | E1372-E-O-T-EPC-IFR-003292 | 1 | 2026-04-06 | 2035-NMDC-MWS-T-0517 | 2026-04-22 | SAF185-MCE-NPCC-T-227 | 1 - Approved
63 | DLB-1000 MOORING ANALYSIS DURING PL-6 and PL-11 corridor spools installation at HP-2 | 2035-ZZ-CL-063 | AD-772-G-64042 | 1 | 2 |  |  | 2026-04-21 | CSE-2035-PMT-T-289 | 2026-04-22 | 2035-NMDC-ADNOC-T-05210 | 2026-05-06 | E1372-E-O-T-EPC-IFR-003305 | 1 | 2026-04-22 | 2035-NMDC-MWS-T-0529 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
64 | DLB-1000 MOORING ANALYSIS DURING PL-7 and PL-10 corridor spools installation at HP-2 | 2035-ZZ-CL-064 | AD-772-G-64043 | 1 | 2 |  |  | 2026-04-21 | CSE-2035-PMT-T-290 | 2026-04-22 | 2035-NMDC-ADNOC-T-05209 | 2026-04-27 | E1372-E-O-T-EPC-IFR-003297 | 1 | 2026-04-22 | 2035-NMDC-MWS-T-0528 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
65 | DLB-1000 MOORING ANALYSIS DURING PL-8,PL-9 and PL-10 corridor spools installation at HP-3 and Lateral shifting PL-8 and PL-9 | 2035-ZZ-CL-065 | AD-773-G-64044 | 1 | 2 |  |  | 2026-04-23 | CSE-2035-PMT-T-292 | 2026-04-24 | 2035-NMDC-ADNOC-T-05224 | 2026-05-07 | E1372-E-O-T-EPC-IFR-003307 | 1 | 2026-04-24 | 2035-NMDC-MWS-T-0535 | 2026-05-06 | SAF185-MCE-NPCC-T-230 | approved
66 | DLB-1000 MOORING ANALYSIS DURING PL-2, PL-7, PL-8 STALK-ON RISER AND PL-9 SPOOLS INSTALLATION AT RP-1 | 2035-ZZ-CL-066 | AD-552-G-64045 | 1 | 2 |  |  | 2026-04-24 | CSE-2035-PMT-T-293 | 2026-04-24 | 2035-NMDC-ADNOC-T-05225 | 2026-05-07 | E1372-E-O-T-EPC-IFR-003307 | 1 | 2026-04-24 | 2035-NMDC-MWS-T-0536 | 2026-05-06 | SAF185-MCE-NPCC-T-230 | approved
|  |  |  | 2 | 2 |  |  | 2026-07-10 | CSE-2035-PMT-T-336 | 2026-07-10 | 2035-NMDC-ADNOC-T-05462 | 2026-07-29 | E1372-E-O-T-EPC-IFA-002906 | 1 | 2026-07-10 | 2035-NMDC-MWS-T-0612 | 2026-07-14 | SAF185-MCE-NPCC-T-246 | 1 - Approved
|  |  |  | 3 | 2 |  |  | 2026-08-24 | CSE-2035-PMT-T-357 | 2026-08-25 | 2035-NMDC-ADNOC-T-05637 | 2026-09-03 | E1372-E-O-T-EPC-IFA-002932 | 1 | 2026-08-25 | 2035-NMDC-MWS-T-0646 | 2026-08-27 | SAF185-MCE-NPCC-T-252 | 1 - Approved
67 | DLB-1000 Mooring Analysis During PL-1 Corridor spools installation at US-159A | 2035-ZZ-CL-067 | AD-768-G-64046 | 1 | 2 |  |  | 2026-04-28 | CSE-2035-PMT-T-294 | 2026-04-29 | 2035-NMDC-ADNOC-T-05231 | 2026-05-14 | E1372-E-O-T-EPC-IFR-003310 | 1 | 2026-04-30 | 2035-NMDC-MWS-T-0537 | 2026-05-13 | SAF185-MCE-NPCC-T-231 | 1 - Approved
68 | DLB-1000 Mooring Analysis During PL-2 Lateral shifting and corridor spools installation at US-12B | 2035-ZZ-CL-068 | AD-767-G-64047 | 1 | 2 |  |  | 2026-04-28 | CSE-2035-PMT-T-296 | 2026-04-29 | 2035-NMDC-ADNOC-T-05233 | 2026-05-14 | E1372-E-O-T-EPC-IFR-003310 | 1 | 2026-04-29 | 2035-NMDC-MWS-T-0539 | 2026-05-13 | SAF185-MCE-NPCC-T-231 | 1 - Approved
69 | DLB-1000 Mooring Analysis During PL-4 Corridor spools installation at US-19B | 2035-ZZ-CL-069 | AD-774-G-64048 | 1 | 2 |  |  | 2026-04-29 | CSE-2035-PMT-T300 | 2026-04-29 | 2035-NMDC-ADNOC-T-05238 | 2026-05-07 | E1372-E-O-T-EPC-IFR-003307 | 1 | 2026-04-29 | 2035-NMDC-MWS-T-0542
70 | DLB-1000 Mooring Analysis During PL-4 Lateral shifting and corridor spools installation at US-153A | 2035-ZZ-CL-070 | AD-770-G-64049 | 1 | 2 |  |  | 2026-04-29 | CSE-2035-PMT-T301 | 2026-04-29 | 2035-NMDC-ADNOC-T-05239 | 2026-05-07 | E1372-E-O-T-EPC-IFR-003307 | 1 | 2026-04-29 | 2035-NMDC-MWS-T-0543 | 06-05-2026 13-05-2026 | SAF185-MCE-NPCC-T-230 'SAF185-MCE-NPCC-T-231 | approved
71 | DLB-1000 Mooring Analysis During PL- 1 Corridor spools installation at US-12B | 2035-ZZ-CL-071 | AD-767-G-64050 | 1 | 2 |  |  | 2026-04-30 | CSE-2035-PMT-T302 | 2026-05-01 | 2035-NMDC-ADNOC-T-05249 | 2026-05-14 | E1372-E-O-T-EPC-IFR-003310 | 1 | 2026-05-01 | 2035-NMDC-MWS-T-0549
72 | DLB-1000 Mooring Analysis During PL-5 Corridor spools installation at US-153A | 2035-ZZ-CL-072 | AD-770-G-64051 | 1 | 2 |  |  | 2026-05-01 | CSE-2035-PMT-T304
73 | SEP-650 MOORING ANALYSIS AT RP-1 WEST SIDE | 2035-ZZ-CL-073 | AD-552-G-64052 | 1 | 2 |  |  | 2026-04-07 | CSE-2035-PMT-T-277
74 | SPOOLS DYNAMIC LIFTING ANALYSIS DAF BY DLB-1000 | 2035-ZZ-CL-074 | AD-26-G-64053 | 1 | 2 |  |  | 2026-04-14 | CSE-2035-PMT-T-282 | 2026-04-16 | 2035-NMDC-ADNOC-T-05193 | 2026-04-22 | E1372-E-O-T-EPC-IFR-003290 | 2 | 2026-04-16 | 2035-NMDC-MWS-T-0524 | 2026-04-23 | SAF185-MCE-NPCC-T-228 | 1
75 | DLB-750 Mooring Analysis during laying of 16" well fluid pipeline from US-159A to US-12B (PL-1) | 2035-ZZ-CL-075 | AD-768/767-G-64054 | 1 | 2 |  |  | 2026-05-04 | CSE-2035-PMT-T306 | 2026-05-04 | 2035-NMDC-ADNOC-T-05256 | 2026-05-22 | E1372-E-O-T-EPC-IFR-003316 | 1 | 2026-05-04 | 2035-NMDC-MWS-T-0554 | 2026-05-13 | SAF185-MCE-NPCC-T-231 | 1 - Approved
76 | DLB-750 Mooring Analysis during laying of 16" well fluid pipeline from US-19B to US-153A (PL-4) | 2035-ZZ-CL-076 | AD-774/770-G-64055 | 1 | 2 |  |  | 2026-05-05 | CSE-2035-PMT-T307 | 2026-05-05 | 2035-NMDC-ADNOC-T-05260 | 2026-05-14 | E1372-E-O-T-EPC-IFR-003310 | 1 | 2026-05-05 | 2035-NMDC-MWS-T-0555 | 2026-05-13 | SAF185-MCE-NPCC-T-231 | 1 - Approved
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADNOC APPROVAL CODE : (1) ACCEPTED; (2) ACCEPTED WITH COMMENTS; (2A) ACCEPTED WITH MINOR COMMENTS;
(3) NOT ACCEPTED, REVISE & RESUBMIT; (4) FOR INFORMATION

## Drawings
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
|  | EPC FOR UMM SHAIF LONG TERM DEVELOPMENT PHASE-1 (USLTDP1) PROJECT | [11 empty] | ADMA DOC. No. :
|  | NPCC PROJECT NO. 2035 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (DRAWINGS) | [11 empty] | DATE : |  |  |  | 2022-03-17
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | ADNOC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE |  |  | - |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MD |  | STATUS FROM MD
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | START UP HEAD DETAILS FOR 16” PIPE LINE (WELD TYPE) | 2035-NN-0001 | AD-26-PL-640000 | 1 | 3 | 2023-11-05 | 2023-05-25 | CSE-2035-PMT-T-009 | 2023-05-26 | 2035-NPCC-ADNOC-T-00950 | 2023-09-21 | E1372-E-O-T-EPC-IFI-000165 | 1 | 2023-05-26 | 2035-NPCC-MWS-T-0024
2 | START UP HEAD DETAILS FOR 18” PIPE LINE (FLANGE TYPE) | 2035-NN-0002 | AD-26-PL-640001 | 1 | 3 | 2024-02-08 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00671 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000068 | 2
|  |  |  | 2 | 3 |  | 2023-04-05 | CSE-2035-PMT-T-008 | 2023-04-13 | 2035-NPCC-ADNOC-T-00707 |  |  |  | 2023-04-13 | 2035-NPCC-MWS-T-0007
3 | LAYDOWN HEAD DETAILS FOR 16" PIPE LINE (WELD TYPE) | 2035-NN-0003 | AD-26-PL-640002 | 1 | 3 | 2023-11-05 | This drawing is no more use, Since all LD head are flanged Type (please refer 2035-NN-0050 Rev3)
4 | START UP HEAD DETAILS FOR 18” PIPE LINE (WELD TYPE) | 2035-NN-0004 | AD-26-PL-640003 | 1 | 3 | 2024-02-08 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00672 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000068 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-05-25 | CSE-2035-PMT-T-009 | 2023-05-26 | 2035-NPCC-ADNOC-T-00951 | 2023-09-21 | E1372-E-O-T-EPC-IFI-000163 | 1 | 2023-05-26 | 2035-NPCC-MWS-T-0025
5 | TYPICAL EMERGENCY HEAD FOR 16" PIPELINE | 2035-NN-0005 | AD-26-PL-640004 | 1 | 3 | 2023-11-05 | 2023-02-13 | CSE-2035-PMT-T-005 | 2023-02-14 | 2035-NPCC-ADNOC-T-00720 | 2023-02-21 | E1372-E-O-T-EPC-IFI-000074 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-05-25 | CSE-2035-PMT-T-009 | 2023-05-26 | 2035-NPCC-ADNOC-T-00951 | 2023-09-21 | E1372-E-O-T-EPC-IFI-000162 | 1 | 2023-05-26 | 2035-NPCC-MWS-T-0025
6 | TYPICAL EMERGENCY HEAD FOR 18" PIPE LINE | 2035-NN-0006 | AD-26-PL-640005 | 1 | 3 | 2024-02-08 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00673 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000068 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-04-05 | CSE-2035-PMT-T-008 | 2023-04-13 | 2035-NPCC-ADNOC-T-00709
|  |  |  | 3 | 3 |  | 2026-03-06 | CSE-2035-PMT-T-261 | 2026-03-09 | 2035-NMDC-ADNOC-T-05053 | 2026-03-10 | E1372-E-O-T-EPC-IFI-000507 | 4
7 | BUCKLE DETECTOR DETAILS FOR 16"x 26.19 W.T | 2035-NN-0007 | AD-26-PL-640006 | 1 | 3 | 2023-11-05 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00674 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000069 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-08-17 | CSE-2035-PMT-T-014 | 2023-08-18 | 2035-NPCC-ADNOC-T-01202 | 2023-09-04 | E1372-E-O-T-EPC-IFI-000156 | 4 | 2023-08-18 | 2035-NPCC-MWS-T-0048
8 | BUCKLE DETECTOR DETAILS FOR 18"x 28.58 W.T | 2035-NN-0008 | AD-26-PL-640007 | 1 | 3 | 2024-02-08 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00675 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000069 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-08-17 | CSE-2035-PMT-T-014 | 2023-08-18 | 2035-NPCC-ADNOC-T-01202 | 2023-09-04 | E1372-E-O-T-EPC-IFI-000156 | 4 | 2023-08-18 | 2035-NPCC-MWS-T-0048
9 | SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM US-159A TO US-12B (PL-1) @ US-159A | 2035-NN-0009 | AD-768/767-PL-640000 | 1 | 3 | 2024-02-09 | 2026-06-11 | CSE-2035-PMT-T-326 | 2026-06-12 | 2035-NMDC-ADNOC-T-05382 | 2026-06-23 | E1372-E-O-T-EPC-IFC-003374 | 1 | 2026-06-12 | 2035-NMDC-MWS-T-0587 | 2026-06-22 | SAF185-MCE-NPCC-T-240 | HOLD
|  |  |  | 2 | 3 |  | 0-7-07-2026 | CSE-2035-PMT-T-335 | 07-07-2026 | 2035-NMDC-ADNOC-T-05454 | 28-07-2026 | E1372-E-O-T-EPC-IFC-003389 | 1 | 07-07-2026 | 2035-NMDC-MWS-T-0610 | 09-07-2026 | SAF185-MCE-NPCC-T-245 | Approved
10 | SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-159A TO US-12B (PL-1) @ US-12B | 2035-NN-0010 | AD-768/767-PL-640001 | 1 | 3 | 2024-02-14 | 2026-06-11 | CSE-2035-PMT-T-326 | 2026-06-12 | 2035-NMDC-ADNOC-T-05383 | 2026-06-23 | E1372-E-O-T-EPC-IFC-003374 | 1 | 2026-06-12 | 2035-NMDC-MWS-T-0588 | 2026-06-15 | SAF185-MCE-NPCC-T-239 | Approved
11 | SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-12B TO USSC-RP1 (PL-2) @ US-12B | 2035-NN-0011 | AD-767/552-PL-640000 | 1 | 2 | 2024-02-20 | 2026-05-21 | CSE-2035-PMT-T-317 | 2026-05-22 | 2035-NMDC-ADNOC-T-05331 | 2026-06-10 | E1372-E-O-T-EPC-IFC-003364 | 1 | 2026-05-22 | 2035-NMDC-MWS-T-0569 | 2026-05-29 | SAF185-MCE-NPCC-T-233 | HOLD
|  |  |  | 2 | 3 |  | 2026-06-16 | CSE-2035-PMT-T-327 | 2026-06-24 | 2035-NMDC-ADNOC-T-05412 |  |  |  | 2026-06-24 | 2035-NMDC-MWS-T-0590 | 2026-06-29 | SAF185-MCE-NPCC-T-241 | Approved
12 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM US-12B TO USSC-RP1 (PL-2) @ USSC-RP1 | 2035-NN-0012 | AD-767/552-PL-640001 | 1 | 2 | 2024-03-29 | 2025-08-11 | CSE-2035-PMT-T-172 | 2025-08-14 | 2035-NMDC-ADNOC-T-04107 | 2025-11-11 | E1372-E-O-T-EPC-IFC-003205 | 3 | 2025-08-12 | 2035-NMDC-MWS-T-0332 | 2025-11-07 | SAF185-MCE-NPCC-T-202 | 1 - Approved
|  |  |  | 2 | 2 |  | 14-05-2025 01-06-2026 | CSE-2035-PMT-T-311 | 2026-06-01 | 2035-NMDC-ADNOC-T-05340 | 2026-06-02 | E1372-E-O-T-EPC-IFC-003366 | 2 | 2026-06-01 | 2035-NMDC-MWS-T-0572 | 2026-06-09 | SAF185-MCE-NPCC-T-236 | 1 - Approved
|  |  |  | 3 | 3 |  | 07-07-2026 | CSE-2035-PMT-T-335 | 07-07-2026 | 2035-NMDC-ADNOC-T-05455 | 22-07-2026 | E1372-E-O-T-EPC-IFC-003387 | 1 | 07-07-2026 | 2035-NMDC-MWS-T-0611 | 09-07-2026 | SAF185-MCE-NPCC-T-245 | Approved
13 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-142A TO USSC-RP1 (PL-3) @ US-142A | 2035-NN-0013 | AD-769/552-PL-640000 | 1 | 3 | 2024-02-26 | 2025-05-05 | CSE-2035-PMT-T-152 | 2025-05-05 | 2035-NMDC-ADNOC-T-03788 | 2025-11-11 | E1372-E-O-T-EPC-IFC-003205 | 3 | 2025-05-05 | 2035-NMDC-MWS-T-0288 | 2025-05-15 | SAF185-MCE-NPCC-T-163 | 1
|  |  |  | 2 | 3 |  | 2025-11-14 | CSE-2035-PMT-T-199 | 2025-11-17 | 2035-NMDC-ADNOC-T-04502 | 2025-11-20 | E1372-E-O-T-EPC-IFC-003211 | 3 | 2025-11-17 | 2035-NMDC-MWS-T-0379
|  |  |  | 3 | 3 |  | 2025-12-11 | CSE-2035-PMT-T-218 | 2025-12-11 | 2035-NMDC-ADNOC-T-04650 | 2025-12-31 | E1372-E-O-T-EPC-IFC-003247 | 3 | 2025-12-11 | 2035-NMDC-MWS-T-0411 | 2025-12-12 | SAF185-MCE-NPCC-T-212 | Approved
|  |  |  | 4 | 3 |  | 2026-01-06 | CSE-2035-PMT-T-232 | 2026-01-06 | 2035-NMDC-ADNOC-T-04750 | 2026-01-07 | E1372-E-O-T-EPC-IFC-003256 | 2 | 2026-01-06 | 2035-NMDC-MWS-T-0435
|  |  |  | 5 | 3 |  | 2026-01-11 | CSE-2035-PMT-T-236 | 2026-01-12 | 2035-NMDC-ADNOC-T-04775 | 2026-01-16 | E1372-E-O-T-EPC-IFC-003265 | 1 | 2026-01-12 | 2035-NMDC-MWS-T-0443
14 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM US-142A TO USSC-RP1 (PL-3) @ USSC-RP1 | 2035-NN-0014 | AD-769/552-PL-640001 | 1 | 2 | 2025-10-15 | 2025-11-14 | CSE-2035-PMT-T-200 | 2025-11-17 | 2035-NMDC-ADNOC-T-04504 | 2025-11-20 | E1372-E-O-T-EPC-IFR-003117 | 3 | 2025-11-17 | 2035-NMDC-MWS-T-0381 | 2025-11-20 | SAF185-MCE-NPCC-T-205 | 1 - Approved
|  |  |  | 2 | 2 |  | 2025-12-03 | CSE-2035-PMT-T-209 | 2025-12-03 | 2035-NMDC-ADNOC-T-04591 |  |  |  | 2025-12-03 | 2035-NMDC-MWS-T-0400 | 2025-12-05 | SAF185-MCE-NPCC-T-208 | 1 - Approved
|  |  |  | 2 | 2 |  | 2025-12-10 | reissued on 09/12 | 2025-12-10 | 2035-NMDC-ADNOC-T-04642 | 2025-12-17 | E1372-E-O-T-EPC-IFA-002765 | 1 | 2025-12-10 | 2035-NMDC-MWS-T-0409 | 2025-12-12 | SAF185-MCE-NPCC-T-212 | Approved
15 | SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM US-19B TO US-153A (PL-4) @ US-19B | 2035-NN-0015 | AD-774/770-PL-640000 | 1 | 3 | 2024-03-15 | 2026-06-25 | CSE-2035-PMT-T-329 | 2026-06-25 | 2035-NMDC-ADNOC-T-05418 | 2026-07-06 | E1372-E-O-T-EPC-IFR-003348 | 2 | 2026-06-25 | 2035-NMDC-MWS-T-0592 | 2026-06-29 | SAF185-MCE-NPCC-T-241 | HOLD
|  |  |  | 2 | 3 |  | 2026-07-17 | CSE-2035-PMT-T-338 | 2026-07-20 | 2035-NMDC-ADNOC-T-05502 | 2026-09-03 | E1372-E-O-T-EPC-IFC-003409 | 1 | 2026-07-20 | 2035-NMDC-MWS-T-0620 | 2026-07-22 | SAF185-MCE-NPCC-T-248 | 1 - Approved
16 | SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM US-19B TO US-153A (PL-4) @ US-153A | 2035-NN-0016 | AD-774/770-PL-640001 | 1 | 3 | 2024-03-03 | 2026-06-25 | CSE-2035-PMT-T-329 | 2026-06-25 | 2035-NMDC-ADNOC-T-05419 | 2026-07-06 | E1372-E-O-T-EPC-IFC-003381 | 3 | 2026-06-25 | 2035-NMDC-MWS-T-0593 | 2026-06-29 | SAF185-MCE-NPCC-T-241 | HOLD
|  |  |  | 2 | 3 |  | 2026-07-17 | CSE-2035-PMT-T-338 | 2026-07-20 | 2035-NMDC-ADNOC-T-05503 | 2026-09-03 | E1372-E-O-T-EPC-IFC-003409 | 1 | 2026-07-20 | 2035-NMDC-MWS-T-0621 | 2026-07-22 | SAF185-MCE-NPCC-T-248 | 1 - Approved
17 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-153A TO USSC-RP1 (PL-5) @ US-153A | 2035-NN-0017 | AD-770/552-PL-640000 | 1 | 2 | 2024-03-08 | 2025-12-10 | CSE-2035-PMT-T-217 | 2025-12-10 | 2035-NMDC-ADNOC-T-04643 | 2025-12-22 | E1372-E-O-T-EPC-IFC-003235 | 3 | 2025-12-10 | 2035-NMDC-MWS-T-0410 | 2025-12-12 | SAF185-MCE-NPCC-T-212 | Approved | REISSUED ON 10/12
|  |  |  | 2 | 2 |  | 2025-12-22 | CSE-2035-PMT-T-229 | 24-12-2025 31-12-2025 | 2035-NMDC-ADNOC-T-04710 |  |  |  | 24-12-2025 31-12-2025 | 2035-NMDC-MWS-T-0426 | 2026-01-06 | SAF185-MCE-NPCC-T-216 | 1 - Approved
18 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM US-153A TO USSC-RP1 (PL-5) @ USSC-RP1 | 2035-NN-0018 | AD-770/552-PL-640001 | 1 | 3 | 2024-04-07 | 2025-11-28 | CSE-2035-PMT-T-206 | 2025-12-03 | 2035-NMDC-ADNOC-T-04579 | 2025-12-11 | E1372-E-O-T-EPC-IFC-003224 | 2 | 2025-12-03 | 2035-NMDC-MWS-T-0395 | 2025-12-04 | SAF185-MCE-NPCC-T-207 | Approved
|  |  |  | 2 | 3 |  | 2025-12-17 | CSE-2035-PMT-T-220 | 2025-12-17 | 2035-NMDC-ADNOC-T-04670 | 2025-12-29 | E1372-E-O-T-EPC-IFC-003243 | 1 | 2025-12-17 | 2035-NMDC-MWS-T-0417 | 2025-12-18 | SAF185-MCE-NPCC-T-213 | 1 - Approved
19 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) @ HP1 | 2035-NN-0019 | AD-771/772-PL-640000 | 1 | 2 |  | 2026-03-22 | CSE-2035-PMT-T-272 | 2026-03-23 | 2035-NMDC-ADNOC-T-05128 | 2026-04-06 | E1372-E-O-T-EPC-IFR-003268 | 3 |  |  | 2026-04-03 | SAF185-MCE-NPCC-T-225 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-04-14 | CSE-2035-PMT-T-280 | 2026-04-15 | 2035-NMDC-ADNOC-T-05190 | 2026-04-22 | E1372-E-O-T-EPC-IFR-003291 | 1 | 2026-04-15 | 2035-NMDC-MWS-T-0521 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
|  |  |  | 3 | 3 |  | 2026-06-25 | CSE-2035-PMT-T-330 | 2026-06-26 | 2035-NMDC-ADNOC-T-05421 | 2026-07-06 | E1372-E-O-T-EPC-IFC-003382 | 2 | 2026-06-26 | 2035-NMDC-MWS-T-0594 | 2026-06-30 | SAF185-MCE-NPCC-T-242 | 1 - Approved
|  |  |  | 4 | 3 |  | 2026-07-28 | CSE-2035-PMT-T-342
20 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" HP OIL SUBSEA PIPELINE FROM HP1 TO HP2 (PL-6) @ HP2 | 2035-NN-0020 | AD-771/772-PL-640001 | 1 | 2 | 2024-05-30 | 2026-04-14 | CSE-2035-PMT-T-280 | 2026-04-15 | 2035-NMDC-ADNOC-T-05188 | 2026-04-20 | E1372-E-O-T-EPC-IFC-003342 | 1 | 2026-04-15 | 2035-NMDC-MWS-T-0519 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
|  |  |  | 2 | 3 |  | 2026-06-25 | CSE-2035-PMT-T-330 | 2026-06-26 | 2035-NMDC-ADNOC-T-05422 | 2026-07-01 | E1372-E-O-T-EPC-IFC-003378 | 1 | 2026-06-26 | 2035-NMDC-MWS-T-0595 | 2026-06-30 | SAF185-MCE-NPCC-T-242 | 1 - Approved
21 | SPOOL LIFTING AND INSTALLATION FOR 18" WELL FLUID PIPELINE FROM HP2 TO USSC-RP1 (PL-7) @ HP2 | 2035-NN-0021 | AD-772/552-PL-640000 | 1 | 2 | 2024-05-24 | 2026-04-20 | CSE-2035-PMT-T-283 | 2026-04-22 | 2035-NMDC-ADNOC-T-05212 | 2026-04-30 | E1372-E-O-T-EPC-IFR-003301 | 1 | 2026-04-22 | 2035-NMDC-MWS-T-0531 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
22 | RISER/SPOOL LIFTING AND INSTALLATION FOR 18" WELL FLUID PIPELINE FROM HP2 TO USSC-RP1 (PL-7) @ USSC-RP1 | 2035-NN-0022 | AD-772/552-PL-640001 | 1 | 2 | 2024-04-07 | 2026-01-08 | CSE-2035-PMT-T-235 | 2026-01-09 | 2035-NMDC-ADNOC-T-04764 | 2026-01-27 | E1372-E-O-T-EPC-IFC-003298 | 3 | 2026-01-09 | 2035-NMDC-MWS-T-0440 | 2026-02-02 | SAF185-MCE-NPCC-T-219 | 3-Reviewed with Comments
|  |  |  | 2 | 3 |  | 2026-02-09 | CSE-2035-PMT-T-249 | 2026-02-11 | 2035-NMDC-ADNOC-T-04935 | 2026-02-18 | E1372-E-O-T-EPC-IFC-003310 | 1 | 2026-02-11 | 2035-NMDC-MWS-T-0458 | 2026-02-16 | SAF185-MCE-NPCC-T-220 | 1 - Approved
|  |  |  | 3 | 3 |  | 2026-02-24 | CSE-2035-PMT-T-256 | 2026-02-25 | 2035-NMDC-ADNOC-T-05024 | 2026-03-18 | E1372-E-O-T-EPC-IFC-003323 | 1 | 2026-02-25 | 2035-NMDC-MWS-T-0474
|  |  |  | 4 | 3 |  | 2026-06-02 | CSE-2035-PMT-T-319 | 2026-06-03 | 2035-NMDC-ADNOC-T-05357 | 2026-06-19 | E1372-E-O-T-EPC-IFC-003371 | 3 | 2026-06-03 | 2035-NMDC-MWS-T-0576 | 2026-06-09 | SAF185-MCE-NPCC-T-236 | 1 - Approved
|  |  |  | 5 | 3 |  | 2026-07-01 | CSE-2035-PMT-T-331 | 2026-07-01 | 2035-NMDC-ADNOC-T-05435 | 2026-07-08 | E1372-E-O-T-EPC-IFC-003384 | 1 | 2026-07-01 | 2035-NMDC-MWS-T-0599 | 2026-07-02 | SAF185-MCE-NPCC-T-243 | 1 - Approved
|  |  |  | 6 | 3 |  | 2026-07-31 | CSE-2035-PMT-T-346 | 2026-07-31 | 2035-NMDC-ADNOC-T-05546 | 2026-08-14 | E1372-E-O-T-EPC-IFC-003397 | 1 | 2026-07-31 | 2035-NMDC-MWS-T-0627 | 2026-08-03 | SAF185-MCE-NPCC-T-249 | 1 - Approved
23 | SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM HP3 TO USSC-RP1 (PL-8) @ HP3 | 2035-NN-0023 | AD-773/552-PL-640000 | 1 | 2 |  | 2026-04-21 | CSE-2035-PMT-T-288 | 2026-04-21 | 2035-NMDC-ADNOC-T-05211 | 2026-04-27 | E1372-E-O-T-EPC-IFC-003345 | 3 | 2026-04-22 | 2035-NMDC-MWS-T-0530 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-05-14 | CSE-2035-PMT-T-313 | 2026-05-15 | 2035-NMDC-ADNOC-T-05291 | 2026-06-03 | E1372-E-O-T-EPC-IFC-003360 | 1 | 2026-05-15 | 2035-NMDC-MWS-T-0562 | 2026-05-29 | SAF185-MCE-NPCC-T-234 | 1 - Approved
24 | RISER/SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM HP3 TO USSC-RP1 (PL-8) @ USSC-RP1 | 2035-NN-0024 | AD-773/552-PL-640001 | 1 | 3 | 2024-04-07 | 2025-08-11 | CSE-2035-PMT-T-172 | 2025-08-14 | 2035-NMDC-ADNOC-T-04108 | 2025-11-11 | E1372-E-O-T-EPC-IFC-003205 | 3 | 2025-08-12 | 2035-NMDC-MWS-T-0333 | 2025-11-07 | SAF185-MCE-NPCC-T-202 | 1 - Approved
|  |  |  | 2 | 3 |  | 2026-04-29 | CSE-2035-PMT-T-299 | 2026-04-29 | 2035-NMDC-ADNOC-T-05235 | 2026-05-12 | E1372-E-O-T-EPC-IFC-003349 | 3 | 2026-04-29 | 2035-NMDC-MWS-T-0541 | 2026-05-06 | SAF185-MCE-NPCC-T-230 | approved
|  |  |  | 3 | 3 |  | 2026-05-18 | CSE-2035-PMT-T-316 | 2026-05-20 | 2035-NMDC-ADNOC-T-05319 | 2026-06-10 | E1372-E-O-T-EPC-IFC-003362 | 1 | 2026-05-20 | 2035-NMDC-MWS-T-0567 | 2026-06-02 | SAF185-MCE-NPCC-T-235 | 1 - Approved
|  |  |  | 4 | 3 |  | 2026-07-13 | CSE-2035-PMT-T-337 | 2026-07-15 | 2035-NMDC-ADNOC-T-05470 | 2026-07-23 | E1372-E-O-T-EPC-IFC-003386 | 3 | 2026-07-15 | 2035-NMDC-MWS-T-0614 | 2026-07-15 | SAF185-MCE-NPCC-T-247 | 1 - Approved
|  |  |  | 5 | 3 |  | 2026-07-31 | CSE-2035-PMT-T-347 | 2026-08-04 | 2035-NMDC-ADNOC-T-05559 | 2026-08-14 | E1372-E-O-T-EPC-IFC-003396 | 1 | 2026-08-04 | 2035-NMDC-MWS-T-0630 | 2026-08-05 | SAF185-MCE-NPCC-T-250 | 1 - Approved
25 | SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) @ USSC-RP1 | 2035-NN-0025 | AD-552/773-PL-640000 | 1 | 3 |  | 2026-03-03 | CSE-2035-PMT-T-320 | 2026-06-03 | 2035-NMDC-ADNOC-T-05358 | 2026-06-19 | E1372-E-O-T-EPC-IFC-003373 | 1 | 2026-06-03 | 2035-NMDC-MWS-T-0577 | 2026-06-09 | SAF185-MCE-NPCC-T-236 | 1 - Approved
26 | SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM USSC-RP1 TO HP3 (PL-9) | 2035-NN-0026 | AD-552/773-PL-640001 | 1 | 2 |  | 2026-06-04 | CSE-2035-PMT-T-321 | 2026-06-08 | 2035-NMDC-ADNOC-T-05367 | 2026-06-19 | E1372-E-O-T-EPC-IFC-003373 | 1 | 2026-06-08 | 2035-NMDC-MWS-T-0580 | 2026-06-10 | SAF185-MCE-NPCC-T-238 | 1 - Approved
27 | SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) @ HP3 | 2035-NN-0027 | AD-773/772-PL-640000 | 1 | 3 | 2024-06-11 | 2026-06-05 | CSE-2035-PMT-T-323 | 2026-06-11 | 2035-NMDC-ADNOC-T-05379 | 2026-06-23 | E1372-E-O-T-EPC-IFC-003374 | 1 | 2026-06-11 | 2035-NMDC-MWS-T-0585 | 2026-06-15 | SAF185-MCE-NPCC-T-239 | Approved
|  |  |  | 2 | 3 |  | 2026-07-06 | CSE-2035-PMT-T-334 | 2026-07-06 | 2035-NMDC-ADNOC-T-05451 | 2026-07-24 | E1372-E-O-T-EPC-IFC-003388 | 1 | 2026-07-06 | 2035-NMDC-MWS-T-0605 | 09-07-2026 | SAF185-MCE-NPCC-T-245 | Approved
|  |  |  | 3 | 3 |  | 2026-07-31 | CSE-2035-PMT-T-344 | 2026-07-31 | 2035-NMDC-ADNOC-T-05547 | 2026-09-03 | E1372-E-O-T-EPC-IFC-003409 | 1 | 2026-07-31 | 2035-NMDC-MWS-T-0628 | 2026-08-03 | SAF185-MCE-NPCC-T-249 | 1 - Approved
28 | SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP3 TO HP2 (PL-10) @ HP2 | 2035-NN-0028 | AD-773/772-PL-640001 | 1 | 2 | 2024-05-13 | 2026-04-29 | CSE-2035-PMT-T-298 | 2026-04-29 | 2035-NMDC-ADNOC-T-05234 | 2026-05-18 | E1372-E-O-T-EPC-IFC-003352 | 3 | 2026-04-29 | 2035-NMDC-MWS-T-0540 | 2026-05-06 | SAF185-MCE-NPCC-T-230 | approved
|  |  |  | 2 | 2 |  | 2026-06-05 | CSE-2035-PMT-T-323 | 2026-06-11 | 2035-NMDC-ADNOC-T-05378 | 2026-06-23 | E1372-E-O-T-EPC-IFC-003374 | 1 | 2026-06-11 | 2035-NMDC-MWS-T-0584 | 2026-06-22 | SAF185-MCE-NPCC-T-240 | approved
|  |  |  | 3 | 3 |  | 2026-06-25 | CSE-2035-PMT-T-330 | 2026-06-26 | 2035-NMDC-ADNOC-T-05423 | 2026-07-06 | E1372-E-O-T-EPC-IFC-003383 | 1 | 2026-06-26 | 2035-NMDC-MWS-T-0596 | 2026-06-30 | SAF185-MCE-NPCC-T-242 | 1 - Approved
|  |  |  | 4 | 3 |  | 2026-08-07 | CSE-2035-PMT-T-352
29 | SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) @ HP2 | 2035-NN-0029 | AD-772/771-PL-640000 | 1 | 2 | 2024-06-05 | 02-07-26 | CSE-2035-PMT-T-332 | 03-07-26 | 2035-NMDC-ADNOC-T-05445 | 10-07-26 | E1372-E-O-T-EPC-IFC-003385 | 1 | 03-07-26 | 2035-NMDC-MWS-T-0603 | 2026-07-06 | SAF185-MCE-NPCC-T-244 | 1 - Approved
30 | SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) @ HP1 | 2035-NN-0030 | AD-772/771-PL-640001 | 1 | 2 | 2024-05-01 | 02-07-26 | CSE-2035-PMT-T-332 | 03-07-26 | 2035-NMDC-ADNOC-T-05446 | 10-07-26 | E1372-E-O-T-EPC-IFC-003385 | 1 | 03-07-26 | 2035-NMDC-MWS-T-0604 | 2026-07-06 | SAF185-MCE-NPCC-T-244 | 1 - Approved
31 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (PL-3) AT SAFEEN B-282 (TRIP-1) | 2035-NN-0031 | AD-26-PL-640008 | 1 | 2 | 2023-11-23 | 2024-07-10 | CSE-2035-PMT-T-085 | 2024-07-10 | 2035-NMDC-ADNOC-T-02473 | 2024-07-24 | E1372-E-O-T-EPC-IFR-002362 | 1 | 2024-07-10 | 2035-NPCC-MWS-T-0173 | 2024-07-15 | SAF185-MCE-NPCC-T-082 | 1 - Approved
|  |  |  | 2 | 2 |  | 2024-07-26 | CSE-2035-PMT-T-089 | 2024-07-31 | 2035-NMDC-ADNOC-T-02566 | 2024-08-27 | E1372-E-O-T-EPC-IFR-002416 | 1 | 2024-07-31 | 2035-NPCC-MWS-T-0177 | 2024-08-01 | SAF185-MCE-NPCC-T-086 | HOLD
|  |  |  | CRS | [9 empty] | 2024-08-02 | CRS- sent throu. Email | 2024-08-02 | SAF185-MCE-NPCC-T-087 | 1 - Approved
|  |  |  | 3 | 2 |  | 2025-03-05 | CSE-2035-PMT-T-142 | 2025-03-06 | 2035-NMDC-ADNOC-T-03582 | 2025-03-28 | E1372-E-O-T-EPC-IFC-002981 | 1 | 2025-03-06 | 2035-NMDC-MWS-T-0263 | 2025-03-18 | SAF185-MCE-NPCC-T-153 | 1 - Approved
|  |  |  | 4 |  |  | 2025-04-08 | CSE-2035-PMT-T-148 | 2025-04-09 | 2035-NMDC-ADNOC-T-03679 | 2025-05-31 | E1372-E-O-T-EPC-IFC-003030 | 1 | 2025-04-09 | 2035-NMDC-MWS-T-0273 | 2025-04-15 | SAF185-MCE-NPCC-T-158 | 1 - Approved
32 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (PL-3 & PL-5) AT SAFEEN B-281 (TRIP-2) | 2035-NN-0032 | AD-26-PL-640009 | 1 | 2 | 2024-12-14 | 2025-04-10 | CSE-2035-PMT-T-149 | 2025-04-15 | 2035-NMDC-ADNOC-T-03705 | 2025-05-09 | E1372-E-O-T-EPC-IFR-002876 | 1 | 2025-04-15 | 035-NMDC-MWS-T-0277 | 2025-04-15 | SAF185-MCE-NPCC-T-158 | 1 - Approved
33 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (PL-5) @ CREST-2802 (TRIP-3) | 2035-NN-0033 | AD-26-PL-640010 | 1 | 2 | 2024-01-11 | 2025-05-20 | CSE-2035-PMT-T-155 | 2025-05-20 | 2035-NMDC-ADNOC-T-03844 | 2025-06-18 | E1372-E-O-T-EPC-IFR-002936 | 1 |  | 035-NMDC-MWS-T-0292 | 2025-05-29 | SAF185-MCE-NPCC-T-166 | 1 - Approved
|  |  |  | 2 | 2 |  | 2025-07-23 | CSE-2035-PMT-T-168 | 2025-07-25 | 2035-NMDC-ADNOC-T-04057 | 2025-11-12 | E1372-E-O-T-EPC-IFR-003107 | 1 | 2025-07-25 | 2035-NMDC-MWS-T-0324
34 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES (PL-5 & PL-7) AT SAFEEN-B-284 (TRIP-4) | 2035-NN-0034 | AD-26-PL-640011 | 1 | 3 | 2024-02-01 | 2025-09-18 | CSE-2035-PMT-T-180 | 2025-09-18 | 2035-NMDC-ADNOC-T-04251 | 2025-11-10 | E1372-E-O-T-EPC-IFI-000442 | 1 | 2025-09-18 | 2035-NMDC-MWS-T-0353 | 2025-10-09 | SAF185-MCE-NPCC-T-199 | 1 - Approved
|  |  |  | 2 | 3 |  | 2025-11-03 | CSE-2035-PMT-T-193 | 2025-11-07 | 2035-NMDC-ADNOC-T-04466 | 2025-11-24 | E1372-E-O-T-EPC-IFI-000447 | 1 | 2025-11-07 | 2035-NMDC-MWS-T-0361 | 2025-11-12 | SAF185-MCE-NPCC-T-203 | 1 - Approved | REISSUED
35 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES (PL-5 & PL-7) ON SAFEEN B-282 (TRIP-5) | 2035-NN-0035 | AD-26-PL-640012 | 1 | 2 | 2024-02-29 | 2025-11-12 | CSE-2035-PMT-T-196 | 2025-11-14 | 2035-NMDC-ADNOC-T-04488 | 2025-11-24 | E1372-E-O-T-EPC-IFR-003124 | 1 | 2025-11-14 | 2035-NMDC-MWS-T-0376 | 2025-11-20 | SAF185-MCE-NPCC-T-205 | 1 - Approved
36 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF 16” CC PIPES (PL-11) ON SAFEEN B-281 (TRIP-12) | 2035-NN-0036 | AD-26-PL-640013 | 1 | 2 |  | 2026-08-05 | CSE-2035-PMT-T-351 | 2026-08-06 | 2035-NMDC-ADNOC-T-05570 | 2026-09-03 | E1372-E-O-T-EPC-IFR-003399 | 1 | 2026-08-06 | 2035-NMDC-MWS-T-0635 | 2026-08-12 | SAF185-MCE-NPCC-T-251 | 1 - Approved
37 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF OF SPOOLS @ AESEN-2812 | 2035-NN-0037 | AD-26-PL-640014 | 1 | 2 | 2024-01-24 | 2026-04-14 | CSE-2035-PMT-T-281 | 2026-04-14 | 2035-NMDC-ADNOC-T-05189 | 2026-04-27 | E1372-E-O-T-EPC-IFR-003297 | 1 | 2026-04-15 | 2035-NMDC-MWS-T-0520 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-04-29 | CSE-2035-PMT-T-297 | 2026-04-29 | 2035-NMDC-ADNOC-T-05242 | 2026-05-07 | E1372-E-O-T-EPC-IFA-002866 | 1 | 2026-04-29 | 2035-NMDC-MWS-T-0546 | 2026-05-06 | SAF185-MCE-NPCC-T-230 | approved
38 | LOADING ARRGT & SEAFASTENING DETAILS OF OF RISERS, SPOOLS & RISER PROTECTOR TRIP-2 WITH BALAST PLAN | 2035-NN-0038 | AD-26-PL-640015 | 1 | 2 | 2024-01-24
39 | LOADING ARRGT & SEAFASTENING DETAILS OF OF RISERS, SPOOLS & RISER PROTECTOR TRIP-3 WITH BALAST PLAN | 2035-NN-0039 | AD-26-PL-640016 | 1 | 2 | 2024-05-16
40 | LOADING ARRANGEMENT AND SEAFASTENING OF CONCRETE SLEEPERS (PL-3) @ ASTRO-250 | 2035-NN-0040 | AD-26-PL-640017 | 1 | 2 | 2023-06-21 | 2024-01-01 | CSE-2035-PMT-T-040 | 2024-01-02 | 2035-NPCC-ADNOC-T-001598 | 2024-03-12 | E1372-E-O-T-EPC-IFR-002017 | 1 | 2024-01-02 | 2035-NPCC-MWS-T-0097 | 2024-01-06 | SAF185-MCE-NPCC-T-053 | approved
|  |  |  | 2 | IFC |  | 2024-03-14 | CSE-2035-PMT-T-051 | 2024-03-14 | 2035-NPCC-ADNOC-T-01834 | 2024-05-15 | E1372-E-O-T-EPC-IFC-001843 | 1 | 2024-03-14 | 2035-NPCC-MWS-T-0122 | 2024-03-14 | SAF185-MCE-NPCC-T-067 | approved
41 | LOADING ARRANGEMENT AND SEAFASTENING OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS TRIP-2 WITH BALAST PLAN | 2035-NN-0041 | AD-26-PL-640018 | 1 | 2 | 2023-07-11
42 | LOADING ARRANGEMENT AND SEAFASTENING OF SLEEPERS, MATTRESSES , GROUT BAG AND MISCELLANEOUS TRIP-3 WITH BALAST PLAN | 2035-NN-0042 | AD-26-PL-640019 | 1 | 2 | 2023-08-15
43 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-1 | 2035-NN-0043 | AD-26-PL-640020 | 1 | 2 | 2023-07-13 | 2023-08-23 | CSE-2035-PMT-T-015 | 2023-08-23 | 2035-NPCC-ADNOC-T-001213 | 2023-10-24 | E1372-E-O-T-EPC-IFR-00185 | 2 | 2023-08-23 | 2035-NPCC-MWS-T-0049
|  |  |  | 2 | IFC |  | 2026-02-03 | PMT SENT TO CLIENT DIRECT |  |  | 2026-02-27 | E1372-E-O-T-EPC-IFI-000499 | 4
44 | TYPICAL LIFTING AND INSTALLATION OF MATTRESS BY HEA OCEANIC | 2035-NN-0044 | AD-26-PL-640021 | 1 | 2 | 2023-07-13 | 2025-12-30 | CSE-2035-PMT-T-231 | 2025-12-31 | 2035-NMDC-ADNOC-T-04732 |  |  |  | 2025-12-31 | 2035-NPCC-MWS-T-0431 | 2026-01-06 | SAF185-MCE-NPCC-T-216 | 1 - Approved
|  |  |  | 1 | 3 | reissued | 2026-01-19 | CSE-2035-PMT-T-231 | 2026-01-23 | 2035-NMDC-ADNOC-T-04821 | 2026-01-26 | E1372-E-O-T-EPC-IFC-003297 | 3 | 2026-01-22 | 2035-NMDC-MWS-T-0451 | 2026-02-02 | SAF185-MCE-NPCC-T-219 | 3-Reviewed with Comments
|  |  |  | 2 | 3 |  | 2026-02-05 | CSE-2035-PMT-T-246 | 2026-02-13 | 2035-NMDC-ADNOC-T-04966 | 2026-02-20 | E1372-E-O-T-EPC-IFC-003311 | 2 | 2026-02-13 | 2035-NMDC-MWS-T-0464 | 2026-02-16 | SAF185-MCE-NPCC-T-220 | 1 - Approved
45 | TYPICAL LIFTING AND INSTALLATION DRAWING FOR GROUTBAG | 2035-NN-0045 | AD-26-PL-640022 | 1 | 2 | 2024-04-16
46 | TYPICAL LIFTING AND INSTALLATION DRAWING FOR TEMPORARY SUPPORT | 2035-NN-0046 | AD-26-PL-640023 | 1 | 2 | 2024-04-16
47 | TEMPORARY 18" PIG LAUNCHER & RECEIVER | 2035-NN-0047 | AD-26-PL-640024 | 1 | 3 | 2023-04-16 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00676 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000070 | 4 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 |  |  | 2023-06-19 | CSE-2035-PMT-T-010 | 2023-06-19 | 2035-NPCC-ADNOC-T-00712 | 2023-07-25 | E1372-E-O-T-EPC-IFI-000131 | 1
48 | TEMPORARY 16" PIG LAUNCHER & RECEIVER | 2035-NN-0048 | AD-26-PL-640025 | 1 | 3 | 2023-04-16 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00677 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000070 | 4 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 |  |  | 2023-06-19 | CSE-2035-PMT-T-010 | 2023-06-19 | 2035-NPCC-ADNOC-T-00713 | 2023-07-25 | E1372-E-O-T-EPC-IFI-000131 | 1
49 | START UP HEAD DETAILS FOR 16" PIPE LINE (FLANGE TYPE) | 2035-NN-0049 | AD-26-PL-640026 | 1 | 2 | 2023-11-05 | 2023-05-25 | CSE-2035-PMT-T-009 | 2023-05-26 | 2035-NPCC-ADNOC-T-00950 | 2023-09-21 | E1372-E-O-T-EPC-IFI-000165 | 1 | 2023-05-26 | 2035-NPCC-MWS-T-0024
50 | LAYDOWN HEAD DETAIL FOR 16" PIPE LINE (FLANGE TYPE) | 2035-NN-0050 | AD-26-PL-640027 | 1 | 3 | 2023-11-05 | 2023-02-07 | CSE-2035-PMT-T-003 | 2023-02-06 | 2035-NPCC-ADNOC-T-00694 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000072 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-05-25 | CSE-2035-PMT-T-009 | 2023-05-26 | 2035-NPCC-ADNOC-T-00951 | 2023-09-21 | E1372-E-O-T-EPC-IFI-000163 | 1 | 2023-05-26 | 2035-NPCC-MWS-T-0025
|  |  |  | 3 | 3 |  | 2026-02-24 | CSE-2035-PMT-T-256 | 2026-02-25 | 2035-NMDC-ADNOC-T-05025 | 2026-03-05 | E1372-E-O-T-EPC-IFI-000505 | 4 | 2026-02-25 | 2035-NMDC-MWS-T-0475
51 | LAYDOWN HEAD DETAILS FOR 18" PIPE LINE (FLANGE TYPE) | 2035-NN-0051 | AD-26-PL-640028 | 1 | 3 | 2023-11-05 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00678 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000069 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-04-05 | CSE-2035-PMT-T-008 | 2023-04-13 | 2035-NPCC-ADNOC-T-00714
52 | BUCKLE DETECTOR DETAILS FOR 16"x 28.58 W.T | 2035-NN-0052 | AD-26-PL-640029 | 1 | 3 | 2023-11-05 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00679 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000071 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-08-17 | CSE-2035-PMT-T-014 | 2023-08-18 | 2035-NPCC-ADNOC-T-01202 | 2023-09-04 | E1372-E-O-T-EPC-IFI-000156 | 4 | 2023-08-18 | 2035-NPCC-MWS-T-0048
53 | BUCKLE DETECTOR DETAILS FOR 16"x 22.23 W.T | 2035-NN-0053 | AD-26-PL-640030 | 1 | 3 | 2023-11-05 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00680 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000071 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-08-17 | CSE-2035-PMT-T-014 | 2023-08-18 | 2035-NPCC-ADNOC-T-01202 | 2023-09-04 | E1372-E-O-T-EPC-IFI-000156 | 4 | 2023-08-18 | 2035-NPCC-MWS-T-0048
54 | BUCKLE DETECTOR DETAILS FOR 16"x 21.44 W.T | 2035-NN-0054 | AD-26-PL-640031 | 1 | 3 | 2023-11-05 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00681 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000071 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-08-17 | CSE-2035-PMT-T-014 | 2023-08-18 | 2035-NPCC-ADNOC-T-01202 | 2023-09-04 | E1372-E-O-T-EPC-IFI-000156 | 4 | 2023-08-18 | 2035-NPCC-MWS-T-0048
55 | BUCKLE DETECTOR DETAILS FOR 18" X 26.97 W.T | 2035-NN-0055 | AD-26-PL-640032 | 1 | 3 | 2023-11-05 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00682 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000072 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-08-17 | CSE-2035-PMT-T-014 | 2023-08-18 | 2035-NPCC-ADNOC-T-01202 | 2023-09-04 | E1372-E-O-T-EPC-IFI-000156 | 4 | 2023-08-18 | 2035-NPCC-MWS-T-0048
56 | START UP HEAD, LAYDOWN, EMERGENCY HEAD & BLIND FLANGE DETAILS FOR 2" PIGGYBACK PIPELINE | 2035-NN-0056 | AD-26-PL-640033 | 1 | 3 | 2023-11-05 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00683 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000070 | 4 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-05-25 | CSE-2035-PMT-T-009 | 2023-05-26 | 2035-NPCC-ADNOC-T-00951 | 2023-09-21 | E1372-E-O-T-EPC-IFI-000163 | 4 | 2023-05-26 | 2035-NPCC-MWS-T-0025
|  |  |  | 3 | 3 |  | 2023-11-14 | CSE-2035-PMT-T-030 | 2023-11-16 | 2035-NPCC-ADNOC-T-01467 | 2023-11-30 | E1372-E-O-T-EPC-IFI-000216 | 4 | [5 empty] | CSE-OF-2035-T-014 dated 14/11/2023
57 | BUCKLE DETECTOR DETAILS FOR 18" X 30.18 W.T | 2035-NN-0057 | AD-26-PL-640034 | 1 | 3 | 2023-11-05 | 2023-02-06 | CSE-2035-PMT-T-002 | 2023-02-06 | 2035-NPCC-ADNOC-T-00684 | 2023-02-16 | E1372-E-O-T-EPC-IFI-000072 | 2 | 2023-03-28 | 2035-NPCC-MWS-T-0007
|  |  |  | 2 | 3 |  | 2023-08-17 | CSE-2035-PMT-T-014 | 2023-08-18 | 2035-NPCC-ADNOC-T-01202 | 2023-09-04 | E1372-E-O-T-EPC-IFI-000156 | 4 | 2023-08-18 | 2035-NPCC-MWS-T-0048
58 | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 50mm THK. CONCRETE COATING | 2035-NN-0058 | AD-26-PL-640035 | 1 | 3 | 2023-11-05 | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01064 | 2023-08-01 | E1372-E-O-T-EPC-IFI-000139 | 4 | 2023-07-01 | 2035-NPCC-MWS-T-0034
59 | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 80mm THK. CONCRETE COATING | 2035-NN-0059 | AD-26-PL-640036 | 1 | 3 | 2023-11-05 | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01064 | 2023-08-01 | E1372-E-O-T-EPC-IFI-000139 | 4 | 2023-07-01 | 2035-NPCC-MWS-T-0034
60 | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 95mm THK. CONCRETE COATING | 2035-NN-0060 | AD-26-PL-640037 | 1 | 3 | 2023-06-07 | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01064 | 2023-08-03 | E1372-E-O-T-EPC-IFI-000142 | 4 | 2023-07-01 | 2035-NPCC-MWS-T-0034
61 | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 70mm THK. CONCRETE COATING | 2035-NN-0061 | AD-26-PL-640038 | 1 | 3 |  | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01064 | 2023-08-03 | E1372-E-O-T-EPC-IFI-000142 | 4 | 2023-07-01 | 2035-NPCC-MWS-T-0034
62 | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 175mm THK. CONCRETE COATING | 2035-NN-0062 | AD-26-PL-640039 | 1 | 3 |  | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01064 | 2023-08-03 | E1372-E-O-T-EPC-IFI-000142 | 4 | 2023-07-01 | 2035-NPCC-MWS-T-0034
63 | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 85mm THK. CONCRETE COATING | 2035-NN-0063 | AD-26-PL-640040 | 1 | 3 |  | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01064 | 2023-08-03 | E1372-E-O-T-EPC-IFI-000142 | 4 | 2023-07-01 | 2035-NPCC-MWS-T-0034
64 | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 150mm THK. CONCRETE COATING | 2035-NN-0064 | AD-26-PL-640041 | 1 | 3 |  | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01064 | 2023-08-03 | E1372-E-O-T-EPC-IFI-000142 | 4 | 2023-07-01 | 2035-NPCC-MWS-T-0034
65 | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 120mm THK. CONCRETE COATING | 2035-NN-0065 | AD-26-PL-640042 | 1 | 3 |  | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01065 | 2023-07-30 | E1372-E-O-T-EPC-IFI-000216 | 4 | 2023-07-03 | 2035-NPCC-MWS-T-0035
66 | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 60mm THK. CONCRETE COATING | 2035-NN-0066 | AD-26-PL-640043 | 1 | 3 |  | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01065 | 2023-07-30 | E1372-E-O-T-EPC-IFI-000216 | 4 | 2023-07-03 | 2035-NPCC-MWS-T-0035
67 | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 100mm THK. CONCRETE COATING | 2035-NN-0067 | AD-26-PL-640044 | 1 | 3 |  | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01065 | 2023-07-30 | E1372-E-O-T-EPC-IFI-000216 | 4 | 2023-07-03 | 2035-NPCC-MWS-T-0035
68 | FLANGE PROTECTOR DETAILS FOR 18" PIPELINE WITH 150mm THK. CONCRETE COATING | 2035-NN-0068 | AD-26-PL-640045 | 1 | 3 |  | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01065 | 2023-07-30 | E1372-E-O-T-EPC-IFI-000216 | 4 | 2023-07-03 | 2035-NPCC-MWS-T-0035
69 | FLANGE PROTECTOR DETAILS FOR 18" PIPELINE WITH 40mm THK. CONCRETE COATING | 2035-NN-0069 | AD-26-PL-640046 | 1 | 3 |  | 2023-06-26 | CSE-2035-PMT-T-011 | 2023-07-01 | 2035-NPCC-ADNOC-T-01065 | 2023-07-30 | E1372-E-O-T-EPC-IFI-000216 | 4 | 2023-07-03 | 2035-NPCC-MWS-T-0035
70 | TYPICAL TEMP. SUPPORT LIFTING AND INSTALLATION FOR 16" & 18" PIPELINE | 2035-NN-0070 | AD-26-PL-640047 | 1 | 3 |  | 2024-01-31 | CSE-2035-PMT-T-042 | 2024-02-01 | 2035-NPCC-ADNOC-T-01686 | 2024-02-27 | E1372-E-O-T-EPC-IFR-001979 | 1 | 2024-02-01 | 2035-NPCC-MWS-T-0111 | 2024-02-16 | SAF185-MCE-NPCC-T-059 | approved
|  |  |  | 2 | IFC |  | 2024-02-29 | CSE-2035-PMT-T-047 | 2024-03-01 | 2035-NPCC-ADNOC-T-01774 | 2024-05-14 | E1372-E-O-T-EPC-IFC-001827 | 1 | 2024-03-01 | 2035-NPCC-MWS-T-0118 | 2024-03-04 | SAF185-MCE-NPCC-T-063 | approved
|  |  |  | 3 | IFC |  | 2024-04-05 | CSE-2035-PMT-T-058 | 2024-04-22 | 2035-NPCC-ADNOC-T-01970 |  |  |  | 2024-04-22 | 2035-NPCC-MWS-T-0132
71 | FLANGE PROTECTOR DETAILS FOR 18" PIPELINE WITH 800mm THK. CONCRETE COATING | 2035-NN-0071 | AD-26-PL-640048 | 1 | 3 |  | 2023-07-24 | CSE-2035-PMT-T-012 | 2023-07-24 | 2035-NPCC-ADNOC-T-01128 | 2023-08-03 | E1372-E-O-T-EPC-IFI-000142 | 4
72 | LIFTING & INSTALLATION OF J-TUBE AT US-218 | 2035-NN-0072 | AD-26-PL-640049 | 1 | 3 |  | 2023-08-31 | CSE-2035-PMT-T-016 | 2023-08-31 | 2035-NPCC-ADNOC-T-01231 | 2023-10-24 | E1372-E-O-T-EPC-IFR-001730 | 2 | 2023-08-31 | 2035-NPCC-MWS-T-0052
|  |  |  | 2 | 3 |  | 2023-12-02 | CSE-2035-PMT-T-035 | 2023-12-05 | 2035-NPCC-ADNOC-T-01517 | 2023-12-29 | E1372-E-O-T-EPC-IFC-001118 | 1 | 2023-12-06 | 2035-NPCC-MWS-T-0089
|  |  |  | 3 | 3 |  | 2024-01-31 | CSE-2035-PMT-T-042 | 2024-02-01 | 2035-NPCC-ADNOC-T-01681 | 2024-02-08 | E1372-E-O-T-EPC-IFC-001366 | 1 | 2024-02-01 | 2035-NPCC-MWS-T-0107 | 2024-02-09 | SAF185-MCE-NPCC-T-056 | Accepted
73 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ CB-7 (TRIP-1) | 2035-NN-0073 | AD-26-PL-640050 | 1 | 3 |  | 2023-09-05 | CSE-2035-PMT-T-018 | 2023-09-07 | 2035-NPCC-ADNOC-T-01245 | 2023-09-21 | E1372-E-O-T-EPC-IFR-001668 | 4 | 2023-09-07 | 2035-NPCC-MWS-T-0057
74 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ CB-8 (TRIP-2) | 2035-NN-0074 | AD-26-PL-640051
75 | LIFTING & INSTALLATION OF J-TUBE CLAMP AT US-218 | 2035-NN-0075 | AD-26-PL-640052 | 1 | 2 |  | 2023-09-04 | CSE-2035-PMT-T-017 | 2023-09-04 | 2035-NPCC-ADNOC-T-01241 | 2023-10-23 | E1372-E-O-T-EPC-IFR-001723 | 2 | 2023-09-04 | 2035-NPCC-MWS-T-0055
|  |  |  | 2 | 3 |  | 2023-12-02 | CSE-2035-PMT-T-035 | 2023-12-05 | 2035-NPCC-ADNOC-T-01518 | 2023-12-29 | E1372-E-O-T-EPC-IFC-001118 | 1 | 2023-12-06 | 2035-NPCC-MWS-T-0090
|  |  |  | 3 | 3 |  | 2024-01-31 | CSE-2035-PMT-T-042 | 2024-02-01 | 2035-NPCC-ADNOC-T-01684 | 2024-02-08 | E1372-E-O-T-EPC-IFC-001367 | 1 | 2024-02-01 | 2035-NPCC-MWS-T-0112 | 2024-02-09 | SAF185-MCE-NPCC-T-056 | Accepted
76 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-4 | 2035-NN-0076 | AD-26-PL-640053 | 1 | 2 |  | 2023-09-11 | CSE-2035-PMT-T-020 | 2023-09-11 | 2035-NPCC-ADNOC-T-01253 | 2023-10-24 | E1372-E-O-T-EPC-IFR-001724 | 2 | 2023-09-11 | 2035-NPCC-MWS-T-0059 | 2023-11-21 | SAF185-MCE-NPCC-T-044 | Accepted
|  |  |  | 2 | 3 |  | 2026-02-03 | PMT SENT TO CLIENT DIRECT |  |  | 2026-02-05 | E1372-E-O-T-EPC-IFI-000485 | 4
77 | LIFTING & INSTALLATION OF J-TUBE AT US-216 | 2035-NN-0077 | AD-26-PL-640054 | 1 | 2 |  | 2023-09-26 | CSE-2035-PMT-T-022 | 2023-09-28 | 2035-NPCC-ADNOC-T-01290 | 2023-10-24 | E1372-E-O-T-EPC-IFR-001729 | 2 | 2023-09-11 | 2035-NPCC-MWS-T-0062
|  |  |  | 2 | 3 |  | 2023-12-02 | CSE-2035-PMT-T-035 | 2023-12-05 | 2035-NPCC-ADNOC-T-01517 | 2023-12-29 | E1372-E-O-T-EPC-IFC-001118 | 1 | 2023-12-06 | 2035-NPCC-MWS-T-0089
|  |  |  | 3 | 3 |  | 2024-01-31 | CSE-2035-PMT-T-042 | 2024-02-01 | 2035-NPCC-ADNOC-T-01685 | 2024-02-08 | E1372-E-O-T-EPC-IFC-001367 | 1 | 2024-02-01 | 2035-NPCC-MWS-T-0109 | 2024-02-09 | SAF185-MCE-NPCC-T-056 | Accepted
78 | LIFTING & INSTALLATION OF J-TUBE CLAMP AT US-216 | 2035-NN-0078 | AD-26-PL-640055 | 1 | 2 |  | 2023-09-27 | CSE-2035-PMT-T-023 | 2023-09-28 | 2035-NPCC-ADNOC-T-01289 | 2023-10-24 | E1372-E-O-T-EPC-IFR-001727 | 2 | 2023-09-11 | 2035-NPCC-MWS-T-0061
|  |  |  | 2 | 3 |  | 2023-12-02 | CSE-2035-PMT-T-035 | 2023-12-05 | 2035-NPCC-ADNOC-T-01518 | 2023-12-29 | E1372-E-O-T-EPC-IFC-001118 | 1 | 2023-12-06 | 2035-NPCC-MWS-T-0090
|  |  |  | 3 | 3 |  | 2024-01-31 | CSE-2035-PMT-T-042 | 2024-02-01 | 2035-NPCC-ADNOC-T-01682 | 2024-02-08 | E1372-E-O-T-EPC-IFC-001366 | 1 | 2024-02-01 | 2035-NPCC-MWS-T-0108 | 2024-02-09 | SAF185-MCE-NPCC-T-056 | Approved
79 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS USING JAYA PEARL FOR PL-1 | 2035-NN-0079 | AD-26-PL-640056 | 1 | 2 |  | 2023-09-28 | CSE-2035-PMT-T-024 | 2023-10-02 | 2035-NPCC-ADNOC-T-01296 | 2023-10-24 | E1372-E-O-T-EPC-IFR-001728 | 2 | 2023-10-02 | 2035-NPCC-MWS-T-0064
|  |  |  | 2 |  | IFC | 2026-02-03 | PMT SENT TO CLIENT DIRECT |  |  | 2026-02-27 | E1372-E-O-T-EPC-IFI-000499 | 4
80 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-1 BY SAFEEN 3000 | 2035-NN-0080 | AD-26-PL-640057 | 1 | 2 |  | 2023-10-19 | CSE-2035-PMT-T-025 | 2023-10-19 | 2035-NPCC-ADNOC-T-01360 | 2024-01-25 | E1372-E-O-T-EPC-IFR-001913 | 1 | 2023-10-20 | 2035-NPCC-MWS-T-0069 | 15/02/2024 22/02/2024 | SAF185-MCE-NPCC-T-058 SAF185-MCE-NPCC-T-061 | Approved
|  |  |  | 2 |  | LOP
81 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-2 BY SAFEEN 3000 | 2035-NN-0081 | AD-26-PL-640058 | 1 | 2 |  | 2023-12-08 | CSE-2035-PMT-T-037 | 2023-12-13 | 2035-NPCC-ADNOC-T-01545 | 2024-01-25 | E1372-E-O-T-EPC-IFR-001914 | 1 | 2023-12-13 | 2035-NPCC-MWS-T-0093 | 15/02/2024 22/02/2024 | SAF185-MCE-NPCC-T-058 SAF185-MCE-NPCC-T-061 | Approved
|  |  |  | 2 |  | LOP
82 | LIFTING & INSTALLATION OF J-TUBE AT US-216 BY ASTRO AQUILA | 2035-NN-0082 | AD-424-PL-640059 | 1 | 2 |  | 2710/2023 | CSE-2035-PMT-T-026 | 2023-10-30 | 2035-NPCC-ADNOC-T-01384 | 2023-11-15 | E1372-E-O-T-EPC-IFR-001789 | 1 | 2023-10-30 | 2035-NPCC-MWS-T-0071
|  |  |  | 2 | 2 |  | 21/11/2023 | CSE-2035-PMT-T-031 | 21/11/2023 | 2035-NPCC-ADNOC-T-01479 |  |  |  | 21/11/2023 | 2035-NPCC-MWS-T-0081
|  |  |  | 3 | 2 |  | 21/11/2024 | CSE-2035-PMT-T-032 | 22/11/2024 | 2035-NPCC-ADNOC-T-01482 | 12/12/2024 | E1372-E-O-T-EPC-IFC-001078 | 2 | 22/11/2023 | 2035-NPCC-MWS-T-0083
|  |  |  | 4 |  | IFC | 2026-02-03 | PMT SENT TO CLIENT DIRECT |  |  | 2026-02-27 | E1372-E-O-T-EPC-IFI-000499 | 4
83 | LIFTING & INSTALLATION OF J-TUBE CLAMP US-216 BY ASTRO AQUILA | 2035-NN-0083 | AD-424-PL-640060 | 1 | 2 |  | 2710/2023 | CSE-2035-PMT-T-026 | 2023-10-30 | 2035-NPCC-ADNOC-T-01385 | 2023-11-15 | E1372-E-O-T-EPC-IFR-001789 | 1 | 2023-10-30 | 2035-NPCC-MWS-T-0072
|  |  |  | 2 | 2 |  | 21/11/2023 | CSE-2035-PMT-T-031 | 21/11/2023 | 2035-NPCC-ADNOC-T-01479 | 2024-04-25 | E1372-E-O-T-EPC-IFC-001641 | 5 | 21/11/2023 | 2035-NPCC-MWS-T-0081
|  |  |  | 3 |  | IFC | 2026-02-03 | PMT SENT TO CLIENT DIRECT |  |  | 2026-02-27 | E1372-E-O-T-EPC-IFI-000499 | 4
84 | LIFTING & INSTALLATION OF J-TUBE AT US-218 BY ASTRO AQUILA | 2035-NN-0084 | AD-26-PL-640061 | 1 | 2 |  | 02/11/2024 | CSE-2035-PMT-T-028 | 02/11/2024 | 2035-NPCC-ADNOC-T-01404 | 2023-11-15 | E1372-E-O-T-EPC-IFR-001790 | 1 | 02/11/2023 | 2035-NPCC-MWS-T-0077 | 21/11/2024 | SAF185-MCE-NPCC-T-045 | 3
|  |  |  | 2 | 2 |  | 21/11/2023 | CSE-2035-PMT-T-031 | 21/11/2023 | 2035-NPCC-ADNOC-T-01479 | 2026-02-27 | E1372-E-O-T-EPC-IFI-000499 | 4 | 21/11/2023 | 2035-NPCC-MWS-T-0081
|  |  |  | 3 | 2 |  | 21/11/2024 | CSE-2035-PMT-T-032 | 22/11/2024 | 2035-NPCC-ADNOC-T-01482 | 12/12/2024 | E1372-E-O-T-EPC-IFC-001078 | 2 | 22/11/2023 | 2035-NPCC-MWS-T-0083
|  |  |  | 4 |  | IFC | 2026-02-03 | PMT SENT TO CLIENT DIRECT |  |  | 2026-02-27 | E1372-E-O-T-EPC-IFI-000499 | 4
85 | LIFTING & INSTALLATION OF J-TUBE CLAMP AT US-218 BY ASTRO AQUILA | 2035-NN-0085 | AD-26-PL-640062 | 1 | 2 |  | 02/11/2024 | CSE-2035-PMT-T-028 | 02/11/2024 | 2035-NPCC-ADNOC-T-01405 | 2023-11-15 | E1372-E-O-T-EPC-IFR-001790 | 1 | 02/11/2024 | 2035-NPCC-MWS-T-0078
|  |  |  | 2 | 2 |  | 21/11/2023 | CSE-2035-PMT-T-031 | 21/11/2023 | 2035-NPCC-ADNOC-T-01479 | 2024-04-25 | E1372-E-O-T-EPC-IFC-001641 | 5 | 21/11/2023 | 2035-NPCC-MWS-T-0081
|  |  |  | 3 |  | IFC | 2026-02-05 | PMT SENT TO CLIENT DIRECT |  |  | 2026-02-27 | E1372-E-O-T-EPC-IFI-000499 | 4
86 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ ES-282 (TRIP-3) | 2035-NN-0086 | AD-26-PL-640063 | 1 | 2 |  | 2023-10-30 | CSE-2035-PMT-T-027 | 2023-10-30 | 2035-NPCC-ADNOC-T-01387 | 2023-11-22 | E1372-E-O-T-EPC-IFR-001803 | 1 | 2023-10-31 | 2035-NPCC-MWS-T-0075 | 22/11/2023 | SAF185-MCE-NPCC-T-046 | Approved
87 | TYPICAL PERSONNEL TRANSFER BASKET ARRANGEMENT FROM VESSEL | 2035-NN-0087 | AD-26-PL-640064 | 1 | 2 |  | 2023-12-02 | CSE-2035-PMT-T-035 | 2023-12-12 | 2035-NPCC-ADNOC-T-01519 | 2024-01-22 | E1372-E-O-T-EPC-IFR-001909 | 1
|  |  |  | 2 | 3 |  | 2024-01-31 | CSE-2035-PMT-T-042 | 2024-02-01 | 2035-NPCC-ADNOC-T-01685 | 2024-04-01 | E1372-E-O-T-EPC-IFC-001589 | 1
88 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-3 BY SAFEEN 3000 | 2035-NN-0088 | AD-26-PL-640065 | 1 | 2 |  | 2023-12-08 | CSE-2035-PMT-T-037 | 2023-12-13 | 2035-NPCC-ADNOC-T-01545 | 2024-01-25 | E1372-E-O-T-EPC-IFR-001914 | 1 | 2023-12-13 | 2035-NPCC-MWS-T-0093 | 15/02/2024 22/02/2024 | SAF185-MCE-NPCC-T-058 SAF185-MCE-NPCC-T-061 | Approved
|  |  |  | 2 |  | LOP
89 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-4 BY SAFEEN 3000 | 2035-NN-0089 | AD-26-PL-640066 | 1 | 2 |  | 2023-12-21 | CSE-2035-PMT-T-038 | 2023-12-22 | 2035-NPCC-ADNOC-T-01580 | 2024-01-25 | E1372-E-O-T-EPC-IFR-001915 | 1
|  |  |  | 2 |  | LOP
90 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-3 BY SAFEEN SURVEYOR | 2035-NN-0090 | AD-26-PL-640067
91 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-3 BY UMM SHAIF | 2035-NN-0091 | AD-26-PL-640068 | 1 | 2 |  | 2024-01-19 | CSE-2035-PMT-T-041 | 2024-01-19 | 2035-NPCC-ADNOC-T-01658 | 2024-02-29 | E1372-E-O-T-EPC-IFR-001987 | 1
92 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-3 BY TELFORD25 | 2035-NN-0092 | AD-26-PL-640069 | 1 | 2 |  | 2024-01-19 | CSE-2035-PMT-T-041 | 2024-01-19 | 2035-NPCC-ADNOC-T-01659 | 2024-04-15 | E1372-E-O-T-EPC-IFR-002090 | 5
|  |  |  | 2 |  | IFC | 2026-02-05 | PMT SENT TO CLIENT DIRECT |  |  | 2026-02-27 | E1372-E-O-T-EPC-IFI-000499 | 4
93 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS (PL-3) @ ASTRO-304 | 2035-NN-0093 | AD-26-PL-640070 | 1 | 2 |  | 2024-02-14 | CSE-2035-PMT-T-044 | 2024-02-15 | 2035-NPCC-ADNOC-T-01732 | 14/03/204 | E1372-E-O-T-EPC-IFR-002025 | 1 | 2024-03-12 | 2035-NPCC-MWS-T-0110 | 2024-03-13 | SAF185-MCE-NPCC-T-065 | Approved
|  |  |  | 2 | 3 |  | 2024-03-15 | CSE-2035-PMT-T-052 | 2024-03-18 | 2035-NPCC-ADNOC-T-01843 | 2024-05-15 | E1372-E-O-T-EPC-IFC-001840 | 1 | 2024-03-18 | 2035-NPCC-MWS-T-0123 | 2024-03-22 | SAF185-MCE-NPCC-T-068 | Approved
94 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-5 BY SAFEEN 3000 | 2035-NN-0094 | AD-26-PL-640071 | 1 | 2 |  | 2024-02-16 | CSE-2035-PMT-T-045 | 2024-02-16 | 2035-NPCC-ADNOC-T-01743 | 2024-02-29 | E1372-E-O-T-EPC-IFR-001987 | 1 | 2024-02-16 | 2035-NPCC-MWS-T-0106 | 2024-02-21 | SAF185-MCE-NPCC-T-060 | 3
95 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS (PL-3, PL-2 & PL-1) @ ES-282 | 2035-NN-0095 | AD-26-PL-640072 | 1 | 2 |  | 2024-03-13 | CSE-2035-PMT-T-050 | 2024-03-14 | 2035-NPCC-ADNOC-T-01828 | 2024-03-25 | E1372-E-O-T-EPC-IFR-002052 | 1 | 2024-03-14 | 2035-NPCC-MWS-T-0121 | 2024-03-14 | SAF185-MCE-NPCC-T-067 | approved
|  |  |  | 2 | 3 | IFC | 2024-05-21 | CSE-2035-PMT-T-068 | 2024-05-21 | 2035-NMDC-ADNOC-T-02143 | 2024-05-31 | E1372-E-O-T-EPC-IFC-001922 | 1 | 2024-05-21 | 2035-NPCC-MWS-T-0148 | 2024-06-07 | SAF185-MCE-NPCC-T-075 | approved
96 | TYPICAL LIFTING AND INSTALLATION OF BUCKLE TRIGGER FLEXIBLE MATTRESSES BY SAFEEN 3000 | 2035-NN-0096 | AD-26-PL-640073 | 1 | 2 |  | 2024-02-29 | CSE-2035-PMT-T-046 | 2024-02-29 | 2035-NPCC-ADNOC-T-01772 |  |  |  | 2024-02-29 | 2035-NPCC-MWS-T-0117
|  |  |  | 2 | 2 |  | 2024-04-25 | CSE-2035-PMT-T-060 | 2024-04-26 | 2035-NPCC-ADNOC-T-01989 | 2024-05-15 | E1372-E-O-T-EPC-IFC-001842 | 1 | 2024-04-26 | 2035-NPCC-MWS-T-0134 |  |  | Approved
|  |  |  | 3 |  | IFC | 2024-07-15 | CSE-2035-PMT-T-087 | 2024-07-16 | 2035-NMDC-ADNOC-T-02483 | 2024-07-30 | E1372-E-O-T-EPC-IFC-002216 | 1 | 2024-07-16 | 2035-NPCC-MWS-T-0175 | 2024-07-23 | SAF185-MCE-NPCC-T-084 | Approved
|  |  |  | 4 |  |  | 2024-08-14 | CSE-2035-PMT-T-095
97 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-3 BY TELFORD-31 | 2035-NN-0097 | AD-26-PL-640074 | 1 | 2 |  | 2024-03-15 | CSE-2035-PMT-T-052 | 2024-03-18 | 2035-NPCC-ADNOC-T-01844 | 2024-03-25 | E1372-E-O-T-EPC-IFR-002056 | 2 | 2024-03-18 | 2035-NPCC-MWS-T-0124 | 2024-05-04 | SAF185-MCE-NPCC-T-069 | Approved
|  |  |  | 2 | 2 |  | 2024-03-25 | CSE-2035-PMT-T-057 | 2024-03-28 | 2035-NPCC-ADNOC-T-01895 | 2024-04-19 | E1372-E-O-T-EPC-IFA-002131 | 1 | 2024-03-28 | 2035-NPCC-MWS-T-0129 | 2024-05-04 | SAF185-MCE-NPCC-T-069 | Approved
|  |  |  | 3 | 3 | IFC | 2024-04-25 | CSE-2035-PMT-T-059 | 2024-04-26 | 2035-NPCC-ADNOC-T-01988 | 2024-05-15 | E1372-E-O-T-EPC-IFC-001841 | 1 | 2024-04-26 | 2035-NPCC-MWS-T-0133
|  |  |  | 4 | 3 | IFC | 2024-05-16 | CSE-2035-PMT-T-066 | 2024-05-16 | 2035-NMDC-ADNOC-T-02120 | 2024-05-31 | E1372-E-O-T-EPC-IFC-001921 | 1 | 2024-05-16 | 2035-NPCC-MWS-T-0145
|  |  |  | 5 | 3 | IFC | 2024-05-27 | CSE-2035-PMT-T-071 | 2024-05-28 | 2035-NMDC-ADNOC-T-02189 | 2024-07-01 | E1372-E-O-T-EPC-IFC-002071 | 1 | 2024-05-28 | 2035-NPCC-MWS-T-0151 | 2024-07-04 | SAF185-MCE-NPCC-T-079 | Approved
98 | LIFTING AND INSTALLATION OF LINE CO-30" PIPING AT CSP-01 UTILIZING DP VESSEL UMM SHAIF | 2035-NN-0098 | AD-26-PL-640075 | 1 | 2 |  | 2024-03-21 | CSE-2035-PMT-T-053 | 2024-03-22 | 2035-NPCC-ADNOC-T-01875 | 2024-04-18 | E1372-E-O-T-EPC-IFR-002102 | 5
|  |  |  | 2 | 2 |  | 2024-05-10 | CSE-2035-PMT-T-063 | 2024-05-13 | 2035-NMDC-ADNOC-T-02073 | 2024-05-30 | E1372-E-O-T-EPC-IFR-002242 | 3
|  |  |  | 3 | 3 | IFC | 2024-07-06 | CSE-2035-PMT-T-083 | 2024-07-09 | 2035-NMDC-ADNOC-T-02457 | 2024-07-22 | E1372-E-O-T-EPC-IFC-002172 | 3
|  |  |  | 4 |  | IFC | 2024-12-01 | CSE-2035-PMT-T-119 | 2024-12-10 | 2035-NMDC-ADNOC-T-03226 | 2024-12-17 | E1372-E-O-T-EPC-IFC-002749 | 1
99 | LIFTING AND INSTALLATION OF LINE TW-24" PIPING AT CSP-01 UTILIZING DP VESSEL UMM SHAIF | 2035-NN-0099 | AD-26-PL-640076 | 1 | 2 |  | 2024-05-10 | CSE-2035-PMT-T-063 | 2024-05-13 | 2035-NMDC-ADNOC-T-02074 | 2024-06-05 | E1372-E-O-T-EPC-IFR-002258 | 3
|  |  |  | 2 | 3 | IFC | 2024-07-06 | CSE-2035-PMT-T-083 | 2024-07-09 | 2035-NMDC-ADNOC-T-02456 | 2024-07-22 | E1372-E-O-T-EPC-IFC-002172 | 3
|  |  |  | 3 |  |  | 2024-12-19 | CSE-2035-PMT-T-123 | 2024-12-20 | 2035-NMDC-ADNOC-T-03277 | 2024-12-25 | E1372-E-O-T-EPC-IFC-002757 | 1
100 | LIFTING AND INSTALLATION OF LINE CO-20" PIPING AT CSP-01 UTILIZING DP VESSEL UMM SHAIF | 2035-NN-0100 | AD-26-PL-640077 | 1 | 2 |  | 2024-05-10 | CSE-2035-PMT-T-063 | 2024-05-13 | 2035-NMDC-ADNOC-T-02075 | 2024-06-05 | E1372-E-O-T-EPC-IFR-002259 | 3
|  |  |  | 2 | 3 | IFC | 2024-07-06 | CSE-2035-PMT-T-083 | 2024-07-09 | 2035-NMDC-ADNOC-T-02455 | 2024-07-22 | E1372-E-O-T-EPC-IFC-002171 | 3
|  |  |  | 3 |  | IFC | 2024-12-01 | CSE-2035-PMT-T-119 | 2024-12-10 | 2035-NMDC-ADNOC-T-03227 | 2024-12-17 | E1372-E-O-T-EPC-IFC-002748 | 1
101 | TYPICAL TEMP. SUPPORT LIFTING AND INSTALLATION FOR 16" & 18" PIPELINE BY TELFORD-31 | 2035-NN-0101 | AD-26-PL-640078 | 1 | 3 |  | 2024-05-07 | CSE-2035-PMT-T-061 | 2024-05-07 | 2035-NMDC-ADNOC-T-02045 | 2024-05-31 | E1372-E-O-T-EPC-IFC-001919 | 1 | 2024-05-07 | 2035-NPCC-MWS-T-0143
102 | LIFTING AND INSTALLATION OF SPOOL AT BRIDGE B16, B17 & B18 UTILIZING DP VESSEL UMM SHAIF | 2035-NN-0102 | AD-26-PL-640079 | 1 | 3 |  | 2024-05-10 | CSE-2035-PMT-T-063 | 2024-05-13 | 2035-NMDC-ADNOC-T-02076 | 2024-06-05 | E1372-E-O-T-EPC-IFR-002260 | 3
|  |  |  | 2 | 3 | IFC | 2024-07-06 | CSE-2035-PMT-T-083 | 2024-07-09 | 2035-NMDC-ADNOC-T-02454 | 2024-07-22 | E1372-E-O-T-EPC-IFC-002171 | 3
|  |  |  | 3 |  |  | hold | CSE-2035-PMT-T-107 | 2026-02-05 | 2035-NMDC-ADNOC-T-04913 | 2026-02-19 | E1372-E-O-T-EPC-IFI-000494 | 1
103 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-2 BY TELFORD-31 | 2035-NN-0103 | AD-26-PL-640080 | 1 | 3 | IFC | 2024-05-14 | CSE-2035-PMT-T-063 | 2024-05-14 | 2035-NMDC-ADNOC-T-02077 | 2024-05-31 | E1372-E-O-T-EPC-IFR-002247 | 2
|  |  |  | 2 | 3 |  | 2024-05-29 | CSE-2035-PMT-T-073 | 2024-05-30 | 2035-NMDC-ADNOC-T-02202 | 2024-07-01 | E1372-E-O-T-EPC-IFC-002071 | 1 | 2024-07-02 | 2035-NPCC-MWS-T-0153 | 2024-07-09 | SAF185-MCE-NPCC-T-080 | Approved
104 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-1 BY TELFORD-31 | 2035-NN-0104 | AD-26-PL-640081 | 1 | 3 | IFC | 2024-05-14 | CSE-2035-PMT-T-065 | 2024-05-14 | 2035-NMDC-ADNOC-T-02110 | 2024-05-31 | E1372-E-O-T-EPC-IFC-001920 | 2 | 2024-05-15 | 2035-NPCC-MWS-T-0146
|  |  |  | 2 | 3 |  | 2024-05-29 | CSE-2035-PMT-T-073 | 2024-05-30 | 2035-NMDC-ADNOC-T-02203 | 2024-07-01 | E1372-E-O-T-EPC-IFC-002071 | 1 | 2024-07-02 | 2035-NPCC-MWS-T-0152 | 2024-07-09 | SAF185-MCE-NPCC-T-080 | Approved
105 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS (PL-1) @ ASTRO-250 | 2035-NN-0105 | AD-26-PL-640082 | 1 | 3 | IFC | 2024-05-16 | CSE-2035-PMT-T-067 | 2024-05-16 | 2035-NMDC-ADNOC-T-02126 | 2024-05-31 | E1372-E-O-T-EPC-IFR-002249 | 1 | 2024-05-16 | 2035-NPCC-MWS-T-0147 | 2024-05-31 | SAF185-MCE-NPCC-T-074 | Approved
|  |  |  | 2 | 3 | IFC | 2024-06-05 | CSE-2035-PMT-T-075 | 2024-06-05 | 2035-NMDC-ADNOC-T-02242 | 2024-07-01 | E1372-E-O-T-EPC-IFC-002071 | 1 | 2024-06-05 | 2035-NPCC-MWS-T-0159
|  |  |  | 3 | 3 | IFC | 2024-06-12 | CSE-2035-PMT-T-077 | 2024-06-12 | 2035-NMDC-ADNOC-T-02308 | 2024-07-23 | E1372-E-O-T-EPC-IFC-002176 | 1 | 2024-06-12 | 2035-NPCC-MWS-T-0160 | 2024-06-27 | SAF185-MCE-NPCC-T-078 | Approved
106 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS (PL-5) @ ASTRO-304 | 2035-NN-0106 | AD-26-PL-640083 | 1 | 2 |  | 21/05/2024 29/05/2024 | CSE-2035-PMT-T-069 | 2024-05-31 | 2035-NMDC-ADNOC-T-02213 | 2024-07-02 | E1372-E-O-T-EPC-IFR-002305 | 1 | 2024-05-31 | 2035-NPCC-MWS-T-0156 | 2024-06-15 | SAF185-MCE-NPCC-T-076 | Approved
107 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS (PL-5, PL-4, PL-6 & PL-11) AT ES-282 | 2035-NN-0107 | AD-26-PL-640084 | 1 | 2 |  | 2024-06-25 | CSE-2035-PMT-T-079 | 2024-06-25 | 2035-NMDC-ADNOC-T-02367 | 2024-07-09 | E1372-E-O-T-EPC-IFR-002317 | 1 | 2024-06-25 | 2035-NPCC-MWS-T-0165 | 2024-07-04 | SAF185-MCE-NPCC-T-079 | Approved
108 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS (PL-6, PL7, PL-11 & PL-10) @ ASTRO-250 | 2035-NN-0108 | AD-26-PL-640085 | 1 | 2 |  | 2024-07-03 | CSE-2035-PMT-T-081 | 2024-07-04 | 2035-NMDC-ADNOC-T-02442 | 2024-07-09 | E1372-E-O-T-EPC-IFR-002317 | 1 | 2024-07-04 | 2035-NPCC-MWS-T-0168 | 2024-07-04 | SAF185-MCE-NPCC-T-079 | Approved
109 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-4 BY TELFORD-31 | 2035-NN-0109 | AD-26-PL-640086 | 1 | 3 | IFC | 2024-06-03 | CSE-2035-PMT-T-074 | 2024-06-04 | 2035-NMDC-ADNOC-T-02225 | 2024-07-01 | E1372-E-O-T-EPC-IFC-002071 | 1 | 2024-06-04 | 2035-NPCC-MWS-T-0157 | 2024-07-04 | SAF185-MCE-NPCC-T-079 | Approved
110 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-5 BY TELFORD-31 | 2035-NN-0110 | AD-26-PL-640087 | 1 | 3 | IFC | 2024-06-03 | CSE-2035-PMT-T-074 | 2024-06-04 | 2035-NMDC-ADNOC-T-02226 | 2024-07-01 | E1372-E-O-T-EPC-IFC-002071 | 1 | 2024-06-04 | 2035-NPCC-MWS-T-0158 | 2024-07-04 | SAF185-MCE-NPCC-T-079 | Approved
111 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-6 & PL-11 BY TELFORD-31 | 2035-NN-0111 | AD-26-PL-640088 | 1 | 3 | IFC | 2024-06-08 | CSE-2035-PMT-T-076 | 2024-06-11 | 2035-NMDC-ADNOC-T-02294 | 2024-07-01 | E1372-E-O-T-EPC-IFC-002071 | 1 | 2024-06-11 | 2035-NPCC-MWS-T-0162 | 2024-07-09 | SAF185-MCE-NPCC-T-080 | Approved
112 | TYPICAL LIFTING AND INSTALLATION OF REELS BY SAFEEN 3000 | 2035-NN-0112 | AD-26-PL-640089 | 1 | 3 | IFC | 2024-06-08 | CSE-2035-PMT-T-076 | 2024-06-11 | 2035-NMDC-ADNOC-T-02295 | 2024-09-11 | E1372-E-O-T-EPC-IFC-002356 | 1 | 2024-06-11 | 2035-NPCC-MWS-T-0163 | 2024-07-11 | SAF185-MCE-NPCC-T-081 | HOLD
|  |  |  | 2 | 3 | IFC | 2025-07-14 | CSE-2035-PMT-T-166 | 2025-08-01 | 2035-NMDC-ADNOC-T-04079 | 2025-11-11 | E1372-E-O-T-EPC-IFC-003205 | 3 | 2025-08-01 | 2035-NMDC-MWS-T-0327 | 2025-08-11 | SAF185-MCE-NPCC-T-185 | Approved
|  |  |  | 3 | 3 | IFC | 2026-03-06 | CSE-2035-PMT-T-261 | 2026-03-09 | 2035-NMDC-ADNOC-T-05054 | 2026-03-12 | E1372-E-O-T-EPC-IFC-003322 | 2 | 2026-03-09 | 2035-NMDC-MWS-T-0482 | 2026-04-03 | SAF185-MCE-NPCC-T-225 | Accepted
113 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-7 & PL-10 BY TELFORD-31 | 2035-NN-0113 | AD-26-PL-640090 | 1 | 3 | IFC | 2024-06-27 | CSE-2035-PMT-T-080 | 2024-07-01 | 2035-NMDC-ADNOC-T-02419 | 2024-07-16 | E1372-E-O-T-EPC-IFC-002138 | 2 | 2024-07-01 | 2035-NPCC-MWS-T-0167 | 2024-07-09 | SAF185-MCE-NPCC-T-080 | HOLD
|  |  |  | 2 | 3 | IFC | 2024-07-17 | CSE-2035-PMT-T-082 | 2024-07-17 | 2035-NMDC-ADNOC-T-02451 | 2024-07-30 | E1372-E-O-T-EPC-IFC-002216 | 1 | 2024-07-08 | 2035-NPCC-MWS-T-0169 | 2024-07-11 | SAF185-MCE-NPCC-T-081 | Approved
114 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-8 & PL-9 BY TELFORD-31 | 2035-NN-0114 | AD-26-PL-640091 | 1 | 3 | IFC | 2024-07-09 | CSE-2035-PMT-T-084 | 2024-07-09 | 2035-NMDC-ADNOC-T-02460 | 2024-07-30 | E1372-E-O-T-EPC-IFC-002214 | 5 | 2024-07-09 | 2035-NPCC-MWS-T-0170 | 2024-07-15 | SAF185-MCE-NPCC-T-082 | 1 - Approved
|  |  |  | 2 |  | IFC | 2026-02-05 | PMT SENT TO CLIENT DIRECT |  |  | 2026-02-27 | E1372-E-O-T-EPC-IFI-000499 | 4
115 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES TRIP-8 (PL-7 & PL-10) AT ASTRO 304 | 2035-NN-0115 | AD-26-PL-640092 | 1 | 2 |  | 2024-07-23 | CSE-2035-PMT-T-088 | 2024-07-25 | 2035-NMDC-ADNOC-T-02526 | 2024-08-27 | E1372-E-O-T-EPC-IFR-002417 | 1 | 2024-07-25 | 2035-NMDC-MWS-T-0176 | 2024-07-29 | SAF185-MCE-NPCC-T-085 | 1 - Approved
116 | TYPICAL LIFTING AND INSTALLATION OF FLEXIBLE MATTRESSES BY SAFEEN PEARL FOR CABLE CROSSING LOCATIONS | 2035-NN-0116 | AD-26-PL-640093 | 1 |  |  | 2024-08-13 | CSE-2035-PMT-T-094 | 2024-08-20 | 2035-NMDC-ADNOC-T-02676 | 2024-09-09 | E1372-E-O-T-EPC-IFR-002451 | 1 | 2024-08-20 | 2035-NMDC-MWS-T-0186 | 2024-08-21 | SAF185-MCE-NPCC-T-091 | 3
|  |  |  | 2 |  |  | 2024-09-11 | CSE-2035-PMT-T-101 | 2024-09-11 | 2035-NMDC-ADNOC-T-02816 | 2024-09-19 | E1372-E-O-T-EPC-IFR-002471 | 5 | 2024-09-11 | 2035-NMDC-MWS-T-0191 | 2024-09-12 | SAF185-MCE-NPCC-T-097 | HOLD
|  |  |  | 3 |  |  | 2024-09-25 | CSE-2035-PMT-T-104 | 2024-09-26 | 2035-NMDC-ADNOC-T-02900 | 2024-10-03 | E1372-E-O-T-EPC-IFC-002461 | 1 | 2024-09-26 | 2035-NMDC-MWS-T-0201 |  | SAF185-MCE-NPCC-T-102 | 1 - Approved
|  |  |  | 4 |  |  | 2024-10-01 | CSE-2035-PMT-T-106 | 2024-10-01 | 2035-NMDC-ADNOC-T-02928 | 2024-10-11 | E1372-E-O-T-EPC-IFC-002523 | 1 | 2024-10-01 | 2035-NMDC-MWS-T-0206 |  |  | 1 - Approved
117 | TYPICAL LIFTING AND INSTALLATION OF FLEXIBLE MATTRESSES BY TELFORD-31 FOR CABLE CROSSING LOCATIONS | 2035-NN-0117 | AD-26-PL-640094 | 1 |  |  | 2024-08-13 | CSE-2035-PMT-T-094 | 2024-08-21 | 2035-NMDC-ADNOC-T-02687 | 2024-09-09 | E1372-E-O-T-EPC-IFR-002451 | 1 | 2024-08-21 | 2035-NMDC-MWS-T-0187 | 2024-08-21 | SAF185-MCE-NPCC-T-091 | 1 - Approved
118 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-6, PL-7, PL-8, PL-9, PL-10 & PL-11 BY SAFEEN OSV PEARL | 2035-NN-0118 | AD-26-PL-640095 | 1 | 3 |  | 2024-08-01 | CSE-2035-PMT-T-092 | 2024-08-01 | 2035-NMDC-ADNOC-T-02576 | 2024-08-27 | E1372-E-O-T-EPC-IFC-002284 | 2 | 2024-08-01 | 2035-NMDC-MWS-T-0180 | 2024-08-08 | SAF185-MCE-NPCC-T-088 | 1 - Approved
|  |  |  | 2 | 3 |  | 2024-08-26 | CSE-2035-PMT-T-098 | 2024-08-28 | 2035-NMDC-ADNOC-T-02718 | 2024-09-11 | E1372-E-O-T-EPC-IFC-002357 | 3 | 2024-08-26 | 2035-NMDC-MWS-T-0189 | 2024-08-29 | SAF185-MCE-NPCC-T-093 | 1 - Approved
|  |  |  | 3 |  |  | 2024-09-25 | CSE-2035-PMT-T-104 | 2024-09-26 | 2035-NMDC-ADNOC-T-02900 | 2024-10-11 | E1372-E-O-T-EPC-IFC-002523 | 1 | 2024-09-26 | 2035-NMDC-MWS-T-0201 | 2024-09-27 | SAF185-MCE-NPCC-T-102 | 1 - Approved
119 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS TRIP-9 (PL-7 & PL-10) AT ASTRO-304 | 2035-NN-0119 | AD-26-PL-640096 | 1 | 2 |  | 2024-08-01 | CSE-2035-PMT-T-091 | 2024-08-01 | 2035-NMDC-ADNOC-T-02574 | 2024-08-27 | E1372-E-O-T-EPC-IFR-002416 | 1 | 2024-08-01 | 2035-NMDC-MWS-T-079 | 2024-08-01 | SAF185-MCE-NPCC-T-086 | 1 - Approved
|  |  |  | 2 | 2 |  | 2024-09-12 | CSE-2035-PMT-T-103 | 2024-09-12 | 2035-NMDC-ADNOC-T-02827 | 2024-09-30 | E1372-E-O-T-EPC-IFR-002504 | 1 | 2024-09-12 | 2035-NMDC-MWS-T-194 | 2024-09-12 | SAF185-MCE-NPCC-T-097 | 1 - Approved
120 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE (WITH SINGLE 2" PIGGYBACK) FORM US-142A TO USSC-RP1 (PL-3) AT USSC-RP1 | 2035-NN-0120 | AD-26-PL-640097 | 1 | 2 |  | 2024-08-06 | CSE-2035-PMT-T-093 | [10 empty] | SENT TO FAB.
121 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE (WITH SINGLE 2" PIGGYBACK) FORM US-142A TO USSC-RP1 (PL-3) AT US-142A | 2035-NN-0121 | AD-26-PL-640098
122 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE (WITH SINGLE 2" PIGGYBACK) FROM US-153A TO USSC-RP1 (PL-5) AT USSC-RP1 | 2035-NN-0122 | AD-26-PL-640099 | 1 | 2 |  | 2024-08-06 | CSE-2035-PMT-T-093 | [10 empty] | SENT TO FAB.
123 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE (WITH SINGLE 2" PIGGYBACK) FROM US-153A TO USSC-RP1 (PL-5) AT US-153A | 2035-NN-0123 | AD-26-PL-640100
124 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE FROM US-12B TO USSC-RP1 (PL-2) @ USSC-RP-1 | 2035-NN-0124 | AD-26-PL-640101 | 1 | 2 |  | 2024-08-28 | CSE-2035-PMT-T-099
125 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE (WITH SINGLE 2" PIGGYBACK) FROM US-12B TO USSC-RP1 (PL-2) AT US-12B | 2035-NN-0125 | AD-26-PL-640102
126 | TEMPORARY KNEE BRACE DETAILS FOR 18" WELL FLUID PIPELINE FROM HP2 TO USSC-RP1 (PL-7) @ USSC-RP1 | 2035-NN-0126 | AD-26-PL-640103 | 1 | 2 |  | 2024-08-28 | CSE-2035-PMT-T-099
127 | TEMPORARY KNEE BRACE DETAILS FOR 18" WELL FLUID PIPELINE (WITH SINGLE 2" PIGGYBACK) FROM HP2 TO USSC-RP1 (PL-7) AT HP2 | 2035-NN-0127 | AD-26-PL-640104
128 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE FROM HP3 TO USSC-RP1 (PL-8) AT USSC-RP1 | 2035-NN-0128 | AD-26-PL-640105 | 1 | 2 |  | 2024-08-28 | CSE-2035-PMT-T-099
129 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE FROM HP3 TO USSC-RP1 (PL-8) HP3 | 2035-NN-0129 | AD-26-PL-640106
130 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS @ ASTRO-250 (TRIP-10) | 2035-NN-0130 | AD-26-PL-640107 | 1 |  |  | 2024-08-19 | CSE-2035-PMT-T-097 | 2024-08-20 | 2035-NMDC-ADNOC-T-02675 | 2024-09-11 | E1372-E-O-T-EPC-IFR-002454 | 5 |  |  | 2024-08-21 | SAF185-MCE-NPCC-T-091 | 1 - Approved
|  |  |  | 2 |  |  | 2024-10-02 | CSE-2035-PMT-T-108 | 3/1024 | 2035-NMDC-ADNOC-T-02939 | 2024-10-15 | E1372-E-O-T-EPC-IFA-002455 | 1 | 2024-10-03 | 2035-NMDC-MWS-T-0207 | 2024-10-03 | SAF185-MCE-NPCC-T-105 | 1 - Approved
|  |  |  | 3 |  |  | 2024-10-07 | CSE-2035-PMT-T-109 | 2024-10-08 | 2035-NMDC-ADNOC-T-02958 | 2024-10-20 | E1372-E-O-T-EPC-IFA-002481 | 1 | 2024-10-08 | 2035-NMDC-MWS-T-0209 | 2024-10-23 | SAF185-MCE-NPCC-T-112 | 2 - Approved
131 | TYPICAL TEMP. SUPPORT LIFTING AND INSTALLATION FOR 16" & 18" PIPELINE BY SAFEEN OSV PEARL | 2035-NN-0131 | AD-26-PL-640108 | 1 |  |  | 2024-08-15 | CSE-2035-PMT-T-096 | 2024-08-15 | 2035-NMDC-ADNOC-T-02646 | 1909/2024 | E1372-E-O-T-EPC-IFR-002468 | 5 | 2024-08-15 | 2035-NMDC-MWS-T-0183 | 2024-08-17 | SAF185-MCE-NPCC-T-090 | 1 - Approved
|  |  |  | 2 |  |  | 2024-09-25 | CSE-2035-PMT-T-104 | 2024-09-26 | 2035-NMDC-ADNOC-T-02900 | 2024-10-11 | E1372-E-O-T-EPC-IFC-002523 | 1 | 2024-09-26 | 2035-NMDC-MWS-T-0201 |  | SAF185-MCE-NPCC-T-102 | 1 - Approved
132 | TYPICAL LIFTING AND INSTALLATION OF BUCKLE TRIGGER FLEXIBLE MATTRESSES BY SAFEEN OSV PEARL | 2035-NN-0132 | AD-26-PL-640109 | 1 | 3 |  | 2024-09-11 | CSE-2035-PMT-T-102 | 1309/2024 | 2035-NMDC-ADNOC-T-02832 | 1909/2024 | E1372-E-O-T-EPC-IFC-002404 | 5 | 1309/2024 | 2035-NMDC-MWS-T-0195
|  |  |  | 2 |  |  | 2024-09-25 | CSE-2035-PMT-T-104 | 2024-09-26 | 2035-NMDC-ADNOC-T-02900 | 2024-10-11 | E1372-E-O-T-EPC-IFC-002523 | 1 | 2024-09-26 | 2035-NMDC-MWS-T-0201 |  | SAF185-MCE-NPCC-T-102 | 1 - Approved
133 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-7 & PL-8 BY SAFEEN PEARL | 2035-NN-0133 | AD-26-PL-640110 | 1 | 3 |  | 2024-09-25 | CSE-2035-PMT-T-104 | 2024-09-27 | 2035-NMDC-ADNOC-T-02901 | 2024-10-01 | E1372-E-O-T-EPC-IFC-002449 | 2 | 2024-09-27 | 2035-NMDC-MWS-T-0202 | 2024-10-01 | SAF185-MCE-NPCC-T-104 | 1 - Approved
|  |  |  | 2 | 3 | IFCT | 2026-02-05 | PMT has sent it directly to the client. |  |  | 2026-02-27 | E1372-E-O-T-EPC-IFI-000499 | 4
134 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS AT ASTRO-250 (TRIP-10) | 2035-NN-0134 | AD-26-PL-640111
135 | TYPICAL LIFTING AND INSTALLATION OF SANDBAGS BY CARGO NET USING SAFEEN PEARL | 2035-NN-0135 | AD-26-PL-640112 | 1 | 3 |  | 2024-10-10 | CSE-2035-PMT-T-110 | 2024-10-10 | 2035-NMDC-ADNOC-T-02978 | 2024-10-15 | E1372-E-O-T-EPC-IFC-002534 | 1
136 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS TRIP-11 (PL-7, PL-8 & PL-9) AT GAC-68 | 2035-NN-0136 | AD-26-PL-640113 | 1 | 3 |  | 2024-11-11 | CSE-2035-PMT-T-115 | 2024-11-12 | 2035-NMDC-ADNOC-T-03116 | 2024-11-13 | E1372-E-O-T-EPC-IFR-002577 | 1 | 2024-11-12 | 2035-NMDC-MWS-T-0228 | 2024-11-12 | SAF185-MCE-NPCC-T-122 | 1 - Approved
137 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS AT ASTRO-250 (TRIP-12) | 2035-NN-0137 | AD-26-PL-640114 | 1 | 3 |  | 2024-11-27 | CSE-2035-PMT-T-117 | 2024-11-27 | 2035-NMDC-ADNOC-T-03197 | 2024-12-12 | E1372-E-O-T-EPC-IFI-000367 | 1 | 2024-11-27 | 2035-NMDC-MWS-T-0233 | 2024-11-28 | SAF185-MCE-NPCC-T-130 | 2 - Approved
138 | LIFTING AND INSTALLATION OF LINE C-30” PIPING AT CSP-01 UTILIZING DLB-1000 | 2035-NN-0138 | AD-26-PL-640115 | 1 | 3 | IFC | 2024-12-01 | CSE-2035-PMT-T-118 | 2024-12-06 | 2035-NMDC-ADNOC-T-03221 | 2024-12-06 | E1372-E-O-T-EPC-IFC-002717 | 1 | 2024-12-06 | 2035-NMDC-MWS-T-0234 | 2024-12-10 | SAF185-MCE-NPCC-T-133 | 1 - Approved
139 | LIFTING AND INSTALLATION OF LINE CO-20" PIPING AT CSP-01 UTILIZING DLB-1000 | 2035-NN-0139 | AD-26-PL-640116 | 1 | 3 | IFC | 2024-12-01 | CSE-2035-PMT-T-118 | 2024-12-06 | 2035-NMDC-ADNOC-T-03222 | 2024-12-06 | E1372-E-O-T-EPC-IFC-002718 | 1 | 2024-12-06 | 2035-NMDC-MWS-T-0235 | 2024-12-10 | SAF185-MCE-NPCC-T-133 | 1 - Approved
140 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPERS FOR PL-7, PL-8 & PL-9 BY SAFEEN PEARL | 2035-NN-0140 | AD-26-PL-640117 | 1 | 3 | IFC | 2024-12-27 | CSE-2035-PMT-T-125 |  | PMT HOLD -EMAIL DTD. 03/01/25' WAEL
141 | LIFTING AND INSTALLATION OF MISCELLANEOUS HOOK UP SPOOLS AT BRIDGE B-26 BY DLB-1000 | 2035-NN-0141 | AD-26-PL-640118
142 | LIFTING AND INSTALLATION OF MONORAIL FRAME AT BRIDGE B-26 BY DLB-1000 | 2035-NN-0142 | AD-26-PL-640119 | 1 | 3 | IFC | 2024-12-19 | CSE-2035-PMT-T-122 | 2024-12-19 | 2035-NMDC-ADNOC-T-03274 | 2025-01-08 | E1372-E-O-T-EPC-IFC-002774 | 1 | 2024-12-20 | 2035-NMDC-MWS-T-0241
143 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS AT ASTRO-251 CB (TRIP-13) | 2035-NN-0143 | AD-26-PL-640120 | 1 | 3 |  | 2024-12-12 | CSE-2035-PMT-T-121 | 2024-12-12 | 2035-NMDC-ADNOC-T-03238 | 2025-01-08 | E1372-E-O-T-EPC-IFC-002774 | 1 | 2024-12-12 | 2035-NMDC-MWS-T-0237 | 2024-12-13 | SAF185-MCE-NPCC-T-135 | 1 - Approved
144 | LIFTING AND INSTALLATION OF 30" BRACE RIGGING ARRANGEMENT BELOW BRIDGE LANDING BY DLB-1000 | 2035-NN-0144 | AD-26-PL-640121 | 1 | 3 |  | 2024-12-10 | CSE-2035-PMT-T-120 | 2024-12-10 | 2035-NMDC-ADNOC-T-03231 | 2024-12-16 | E1372-E-O-T-EPC-IFC-002747 | 1 | 2024-12-10 | 2035-NMDC-MWS-T-0236 | 2024-12-12 | SAF185-MCE-NPCC-T-134
145 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS AT ASTRO-250 CB (TRIP-14) | 2035-NN-0145 | AD-26-PL-640122 | 1 | 3 |  | 2024-12-20 | CSE-2035-PMT-T-124 | 2024-12-24 | 2035-NMDC-ADNOC-T-03279 | 2024-12-27 | E1372-E-O-T-EPC-IFI-000370 | 1 | 2024-12-24 | 2035-NMDC-MWS-T-0242 | 2024-12-26 | SAF185-MCE-NPCC-T-137 | 1 - Approved
146 | LIFTING AND INSTALLATION OF MISCELLANEOUS HOOK UP SPOOLS AT BRIDGE B-26 BY UMM SHAIF | 2035-NN-0146 | AD-26-PL-640123 | 1 | 3 | IFC | 2024-12-30 | CSE-2035-PMT-T-127 | 2024-12-31 | 2035-NMDC-ADNOC-T-03299 | 2025-01-08 | E1372-E-O-T-EPC-IFC-002774 | 1
|  |  |  | 2 | 3 |  | 2025-01-16 | CSE-2035-PMT-T-130 | 2025-01-16 | 2035-NMDC-ADNOC-T-03400 | 2025-01-24 | E1372-E-O-T-EPC-IFC-002814 | 3
|  |  |  | 3 | 3 |  | PMT has sent it directly to the client. 18-02-2026 |  |  | 2035-NMDC-ADNOC-T-04989 | 2026-03-04 | E1372-E-O-T-EPC-IFI-000504 | 4
147 | LIFTING AND INSTALLATION OF 20’’ TIE-IN SPOOL BY SEP-750 | 2035-NN-0147 | AD-26-PL-640124 | 1 | 3 |  | 2025-02-08 | CSE-2035-PMT-T-139 | 2025-02-10 | 2035-NMDC-ADNOC-T-03487 | 2025-02-12 | E1372-E-O-T-EPC-IFC-002870 | 1
148 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CONCRETE MATTRESSES @ ASTRO-251 | 2035-NN-0148 | AD-26-PL-640125 | 1 | 3 |  | 09-01-2025 15/01/2025 | CSE-2035-PMT-T-128 | 2025-01-16 | 2035-NMDC-ADNOC-T-03395 | 2025-01-23 | E1372-E-O-T-EPC-IFI-000373 | 1 | 2025-01-16 | 2035-NMDC-MWS-T-0245 | 2025-01-21 | SAF185-MCE-NPCC-T-141 | 1 - Approved
|  |  |  | 2 | 3 | Cancelled | 2025-03-06 | CSE-2035-PMT-T-143 | 07-03-2025 | 2035-NMDC-ADNOC-T-03587 |  |  |  | 07-03-2025 | 2035-NMDC-MWS-T-0265 | 2025-03-18 | SAF185-MCE-NPCC-T-153 | 1 - Approved | This drg. Revised & issued same rev.
|  |  |  | 2 | 3 | latest | 2025-03-26 | CSE-2035-PMT-T-143 | 26-03-2025 | 2035-NMDC-ADNOC-T-03644 | 2025-05-20 | E1372-E-O-T-EPC-IFI-000401 | 1 | 27-03-2025 | 2035-NMDC-MWS-T-0270
149 | LIFTING AND INSTALLATION OF RV LINE / FLARE HEAD BY UMM SHAIF | 2035-NN-0149 | AD-26-PL-640126 | 1 | 3 | IFC | 2025-01-16 | CSE-2035-PMT-T-130 | 2025-01-16 | 2035-NMDC-ADNOC-T-03401 | 2025-01-22 | E1372-E-O-T-EPC-IFC-002806 | 1
150 | DEMOLITION AND INSTALLATION OF 36’’ TIE-IN SPOOL BY SEP-750 | 2035-NN-0150 | AD-26-PL-640127 | 1 | 3 | IFC | 2025-02-04 | CSE-2035-PMT-T-138 | 2025-02-05 | 2035-NMDC-ADNOC-T-03473 | 2025-02-12 | E1372-E-O-T-EPC-IFC-002867 | 1
151 | LIFTING AND INSTALLATION OF MISCELLANEOUS HOOK UP SPOOLS AT BRIDGE B-26 BY KRAKEN | 2035-NN-0151 | AD-26-PL-640128 | 1 | 3 | IFC | 2025-01-22 | CSE-2035-PMT-T-133 | 2025-01-27 | 2035-NMDC-ADNOC-T-03438 | 2025-01-30 | E1372-E-O-T-EPC-IFC-002834 | 1
152 | LIFTING AND INSTALLATION OF RV LINE / FLARE HEAD BY KRAKEN | 2035-NN-0152 | AD-26-PL-640129 | 1 | 3 | IFC | 2025-01-27 | CSE-2035-PMT-T-136 | 2025-01-28 | 2035-NMDC-ADNOC-T-03440 | 2025-02-06 | E1372-E-O-T-EPC-IFC-002846 | 2
|  |  |  | 2 | 3 |  | PMT has sent it directly to the client. |  |  |  | 2026-03-04 | E1372-E-O-T-EPC-IFI-000504 | 4
153 | LIFTING AND INSTALLATION OF MOV BY SEP-750 | 2035-NN-0153 | AD-26-PL-640130
154 | LIFTING AND INSTALLATION OF LINE TW-24’’ SPOOL AT CSP-01 & 24’’ SPOOL AT BRIDGE B16 BY SEP-750 | 2035-NN-0154 | AD-26-PL-640131 | 1 | 3 | IFC | 2025-03-03 | CSE-2035-PMT-T-141 | 2025-03-04 | 2035-NMDC-ADNOC-T-03567 | 2025-03-12 | E1372-E-O-T-EPC-IFC-002941 | 2
|  |  |  | 2 | 3 |  | 2025-03-26 | CSE-2035-PMT-T-147 | 2025-03-27 | 2035-NMDC-ADNOC-T-03648 | 2025-03-04 | E1372-E-O-T-EPC-IFC-002987 | 1
155 | UMM SHAIF - LIFTING AND INSTALLATION OF SPOOLS AT BRIDGE B16 & B17 UTILIZING JACK-UP BARGE SEP-750 | 2035-NN-0155 | AD-26-PL-640132 | 1 | 3 | IFC | 2025-05-01 | CSE-2035-PMT-T-151 | 2025-05-02 | 2035-NMDC-ADNOC-T-03780 | 2025-05-15 | E1372-E-O-T-EPC-IFC-003021 | 1
156 | Installation of 24" TW line spool at B16 (Spool EO) | 2035-NN-0156 | AD-26-PL-640133 | 1 | 3 | IFC | 2025-05-19 | CSE-2035-PMT-T-154 | 2025-05-19 | 2035-NMDC-ADNOC-T-03838 | 2025-05-23 | E1372-E-O-T-EPC-IFC-003031 | 1
157 | LIFTING AND INSTALLATION OF PIPE RACK SUPPORT AT BRIDGE B17 UTILIZING JACK-UP BARGE SEP-750 | 2035-NN-0157 | AD-26-PL-640134 | 1 | 3 |  | 2025-06-04 | CSE-2035-PMT-T-159 | 2025-06-09 | 2035-NMDC-ADNOC-T-03900 | 2025-06-10 | E1372-E-O-T-EPC-IFC-003041 | 1
158 | LIFTING AND INSTALLATION OF 24'' & 30" SPOOL AT B17 & B18 BY HEA TITAN | 2035-NN-0158 | AD-26-PL-640135 | 1 | 3 | IFC | 2025-07-29 | CSE-2035-PMT-T-169 | 2025-07-29 | 2035-NMDC-ADNOC-T-04071
|  |  |  | 2 | 3 | IFC | 2025-10-16 | CSE-2035-PMT-T-187
159 | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID SPOOL (WITH SINGLE 2" PIGGYBACK) FROM US-19B TO US-153A (PL-4) AT US-19B | 2035-NN-0159 | AD-26-PL-640136 | 1 | 2 |  | 2025-07-31 | CSE-2035-PMT-T-170
160 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF RISERS AND SPOOLS @ ES - 282 | 2035-NN-0160 | AD-26-PL-640137 | 1 | 2 |  | 2025-11-14 | CSE-2035-PMT-T-197 | 2025-11-17 | 2035-NMDC-ADNOC-T-04503 | 2025-11-24 | E1372-E-O-T-EPC-IFR-003127 | 1 | 2025-11-17 | 2035-NMDC-MWS-T-0380 | 2025-11-20 | SAF185-MCE-NPCC-T-205 | 1 - Approved
161 | UMM SHAIF - LIFTING AND INSTALLATION OF PIPE RACK SUPPORT AT BRIDGE B18 UTILIZING JACK-UP BARGE HEA TITAN | 2035-NN-0161 | AD-26-PL-640138 | 1 | 2 |  | 2025-11-14 | CSE-2035-PMT-T-201 | 2025-11-17 | 2035-NMDC-ADNOC-T-04498 | 2025-11-24 | E1372-E-O-T-EPC-IFR-003123 | 2
|  |  |  | 2 | 3 |  | PMT has sent it directly to the client. |  | 2026-02-18 | 2035-NMDC-ADNOC-T-04991 | 2026-03-04 | E1372-E-O-T-EPC-IFI-000504 | 4
162 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES (PL-7) AT CREST-2802 (TRIP-6) | 2035-NN-0162 | AD-26-PL-640139 | 1 | 2 |  | 2025-11-25 | CSE-2035-PMT-T-204 | 2025-11-26 | 2035-NMDC-ADNOC-T-04565 | 2025-12-15 | E1372-E-O-T-EPC-IFR-003157 | 1 | 2025-11-26 | 2035-NMDC-MWS-T-0390 | 2025-12-11 | SAF185-MCE-NPCC-T-211 | 1 - Approved
163 | INSTALLATION OF 24" TW LINE EO SPOOL IN TWO PIECES AT B16 BY MUTAWA 401 | 2035-NN-0163 | AD-510-PL-640140 | 1 | 2 |  | 2025-11-17 | CSE-2035-PMT-T-202 | 2025-11-19 | 2035-NMDC-ADNOC-T-04518 | 2025-11-24 | E1372-E-O-T-EPC-IFR-003122 | 2
164 | UMM SHAIF- LIFTING AND INSTALLATION OF 14’’ SPOOLS AT WIP-2 & WIP-5 BY HEA TITAN | 2035-NN-0164 | AD-26-PL-640141 | 1 | 2 |  | 2025-12-03 | CSE-2035-PMT-T-207 | 2025-12-04 | 2035-NMDC-ADNOC-T-04585 |  |  |  | 2025-12-04 | 2035-NMDC-MWS-T-0397
165 | RISER TOP PART LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM US-142A TO USSC-RP1 (PL-3) @ USSC-RP1 | 2035-NN-0165 | AD-769/552-PL-640142 | 1 | 2 |  | 2025-12-03 | CSE-2035-PMT-T-210 | 2025-12-04 | 2035-NMDC-ADNOC-T-04601 | 2025-12-12 | E1372-E-O-T-EPC-IFR-003151 | 1 | 2025-12-04 | 2035-NMDC-MWS-T-0401 | 2025-12-05 | SAF185-MCE-NPCC-T-208 | 1 - Approved
166 | RISER TOP PART LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM US-153A TO USSC-RP1 (PL-5) @ USSC-RP1 | 2035-NN-0166 | AD-770/552-PL-640143 | 1 | 3 |  | 2025-11-28 | CSE-2035-PMT-T-206 | 2025-12-03 | 2035-NMDC-ADNOC-T-04578 | 2025-12-12 | E1372-E-O-T-EPC-IFC-003225 | 3 | 2025-12-03 | 2035-NMDC-MWS-T-0394 | 2025-12-04 | SAF185-MCE-NPCC-T-207 | 1 - Approved
|  |  |  | 2 | 3 |  | 2025-12-22 | CSE-2035-PMT-T-225 | 2025-12-23 | 2035-NMDC-ADNOC-T-04696 | 2026-01-06 | E1372-E-O-T-EPC-IFC-003250 | 3 | 2025-12-23 | 2035-NMDC-MWS-T-0421 | 2025-12-23 | SAF185-MCE-NPCC-T-214 | 1 - Approved
|  |  |  | 3 | 3 | reissued | 07-01-2026 09-01-2026 | CSE-2035-PMT-T-233 | 2026-01-12 | 2035-NMDC-ADNOC-T-04769 | 2026-01-16 | E1372-E-O-T-EPC-IFC-003264 | 1 | 2026-01-12 | 2035-NMDC-MWS-T-0441 | 2026-02-22 | SAF185-MCE-NPCC-T-219 | 1 - Approved
167 | SOUTH RISER GUARD TEMPORARY INSTALLATION AID LIFTING USING MUTAWA 401 | 2035-NN-0167 | AD-26-PL-640144 | 1 | 2 |  | 2025-12-16 | CSE-2035-PMT-T-219 | 2025-12-17 | 2035-NMDC-ADNOC-T-04668 | 2026-01-06 | E1372-E-O-T-EPC-IFR-003175 | 2 | 2025-12-17 | 2035-NMDC-MWS-T-0415 | 2025-12-18 | SAF185-MCE-NPCC-T-213 | 1 - Approved
|  |  |  | 2 | 2 |  | 2025-01-13 | CSE-2035-PMT-T-237 | 2026-01-16 | 2035-NMDC-ADNOC-T-04801 | 2026-01-27 | E1372-E-O-T-EPC-IFA-002808 | 1 | 2026-01-16 | 2035-NMDC-MWS-T-0446 | 2026-01-29 | SAF185-MCE-NPCC-T-218 | 1 - Approved
168 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES ON (PL-7) AT SAFEEN B-281 (TRIP-7) | 2035-NN-0168 | AD-26-PL-640145 | 1 | 2 |  | 2025-12-31 | CSE-2035-PMT-T-224 | 2026-01-02 | 2035-NMDC-ADNOC-T-04734 | 2026-01-16 | E1372-E-O-T-EPC-IFR-003188 | 2 | 2026-01-02 | 2035-NMDC-MWS-T-0433
|  |  |  | 2 | 2 |  | 2026-01-14 | CSE-2035-PMT-T-238 | 2026-01-20 | 2035-NMDC-ADNOC-T-04797 | 2026-01-27 | E1372-E-O-T-EPC-IFR-003206 | 1 | 2026-01-16 | 2035-NMDC-MWS-T-0445 | 2026-01-19 | SAF185-MCE-NPCC-T-217 | 1 - Approved
169 | REMOVAL ARRANGEMENT OF BST-S13 BUMPERS BY SAFEEN-3000 | 2035-NN-0169 | AD-26-PL-640146
170 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (PL-6 & PL-7) AT SAFEEN B-284 (TRIP-1) | 2035-NN-0170 | AD-26-PL-640147 | 1 | 3 |  | 2026-01-22 | CSE-2035-PMT-T-242 | 2026-01-22 | 2035-NMDC-ADNOC-T-04825 | 2026-01-26 | E1372-E-O-T-EPC-IFI-000451 | 2 | 2026-01-22 | 2035-NMDC-MWS-T-0452 | 2026-01-29 | SAF185-MCE-NPCC-T-218 | 1 - Approved
|  |  |  | 2 | 3 |  | 2026-01-29 | CSE-2035-PMT-T-244 | 2026-01-30 | 2035-NMDC-ADNOC-T-04861 | 2026-02-05 | E1372-E-O-T-EPC-IFI-000473 | 4 | 2026-01-30 | 2035-NMDC-MWS-T-0454 | 2026-02-16 | SAF185-MCE-NPCC-T-220 | 1 - Approved
171 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (PL-6 & PL-8) ON ASTRO-251 (TRIP-2) | 2035-NN-0171 | AD-26-PL-640148 | 1 | 3 |  | 2026-02-09 | CSE-2035-PMT-T-250 | 2026-02-11 | 2035-NMDC-ADNOC-T-04938 | 2026-02-20 | E1372-E-O-T-EPC-IFR-003223 | 1 | 2026-02-11 | 2035-NMDC-MWS-T-0461 | 2026-02-16 | SAF185-MCE-NPCC-T-220 | 1 - Approved
172 | CLOSE OUT SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-153A TO USSC-RP1 (PL-5) @ US-153A | 2035-NN-0172 | AD-770/552-PL-640149 | 1 | 3 |  | 2026-02-05 | CSE-2035-PMT-T-247 | 2026-02-09 | 2035-NMDC-ADNOC-T-04925 | 2026-02-12 | E1372-E-O-T-EPC-IFC-003306 | 2 | 2026-02-05 | 2035-NPCC-MWS-T-0273 | 2026-02-16 | SAF185-MCE-NPCC-T-220 | 1 - Approved
|  |  |  | 2 | 3 |  | 2026-02-17 | CSE-2035-PMT-T-253 | 2026-02-17 | 2035-NMDC-ADNOC-T-04992 | 2026-02-20 | E1372-E-O-T-EPC-IFC-003312 | 1 | 2026-02-17 | 2035-NMDC-MWS-T-0468
172 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (PL-7 & PL-10, PL-8) ON SAFEEN B-284 (TRIP-8) | 2035-NN-0173 | AD-26-PL-640150 | 1 | 2 |  | 2026-02-20 | CSE-2035-PMT-T-255 | 2026-02-23 | 2035-NMDC-ADNOC-T-05015 | 2026-03-18 | E1372-E-O-T-EPC-IFR-003251 | 1 | 2026-02-23 | 2035-NMDC-MWS-T-0472
173 | CLOSE OUT SPOOL LIFTING AND INSTALLATION FOR 16" HP OIL SUBSEA PIPELINE FROM US-142A TO USSC-RP1 (PL-3) @ US-142A | 2035-NN-0174 | AD-769/552-PL-640151 | 1 | 3 |  | 2026-02-09 | CSE-2035-PMT-T-248 | 2026-02-11 | 2035-NMDC-ADNOC-T-04934 | 2026-02-12 | E1372-E-O-T-EPC-IFC-003306 | 2 | 2026-02-11 | 2035-NMDC-MWS-T-0457 | 2026-02-16 | SAF185-MCE-NPCC-T-220 | 1 - Approved
|  |  |  | 2 | 3 |  | 2026-02-17 | CSE-2035-PMT-T-253 | 2026-02-17 | 2035-NMDC-ADNOC-T-04993 | 2026-02-20 | E1372-E-O-T-EPC-IFC-003312 | 1 | 2026-02-17 | 2035-NMDC-MWS-T-0469
174 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES AT PFC-02 (TRIP-3) | 2035-NN-0175 | AD-26-PL-640152 | 1 | 2 |  | 2026-03-18 | CSE-2035-PMT-T-269 | 2026-03-18 | 2035-NMDC-ADNOC-T-05117 | 2026-03-30 | E1372-E-O-T-EPC-IFR-003256 | 1 | 2026-03-18 | 2035-NMDC-MWS-T-0497 | 2026-03-24 | SAF185-MCE-NPCC-T-223 | 1 - Approved
175 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (PL-10) ON SAFEEN B-281 (TRIP-9) | 2035-NN-0176 | AD-26-PL-640153 | 1 | 2 |  | 2026-02-09 | CSE-2035-PMT-T-262 | 2026-02-10 | 2035-NMDC-ADNOC-T-05063 | 2026-03-18 | E1372-E-O-T-EPC-IFR-003251 | 1 | 2026-02-10 | 2035-NMDC-MWS-T-0485
176 | LOADING ARRANGEMENT & SEAFASTENING OF REEL ON MUTAWA-401 | 2035-NN-0177 | AD-26-PL-640154
177 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES (PL-8 & PL-2) ON ASTRO-251 (TRIP-4) | 2035-NN-0178 | AD-26-PL-640155 | 1 | 2 |  | 2026-03-18 | CSE-2035-PMT-T-267 | 2026-03-25 | 2035-NMDC-ADNOC-T-05136 | 2026-03-30 | E1372-E-O-T-EPC-IFR-003256 | 1 | 2026-03-25 | 2035-NMDC-MWS-T-0503 | 2026-03-26 | SAF185-MCE-NPCC-T-224 | 1 - Approved
178 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES (PL-2 & PL-9) ON SAFEEN B-282 (TRIP-10) | 2035-NN-0179 | AD-26-PL-640156 | 1 | 2 |  | 2026-03-13 | CSE-2035-PMT-T-265 | 2026-03-16 | 2035-NMDC-ADNOC-T-05091 | 2026-04-06 | E1372-E-O-T-EPC-IFR-003264 | 1 | 2026-03-16 | 2035-NMDC-MWS-T-0489 | 2026-03-24 | SAF185-MCE-NPCC-T-223 | 1 - Approved
|  |  |  | 2 | 2 |  | 2026-04-20 | CSE-2035-PMT-T-287 | 2026-04-20 | 2035-NMDC-ADNOC-T-05205 | 2026-05-06 | E1372-E-O-T-EPC-IFA-002864 | 1 | 2026-04-20 | 2035-NMDC-MWS-T-0527 | 2026-04-25 | SAF185-MCE-NPCC-T-229 | 1 - Approved
180 | RISER TOP PART LIFTING AND INSTALLATION FOR 18" WELL FLUID PIPELINE FROM HP2 TO USSC-RP1 (PL-7) @ USSC-RP1 | 2035-NN-0180 | AD-772/552-PL-640157 | 1 | 2 |  | 2026-03-31 | CSE-2035-PMT-T-275 | 2026-03-31 | 2035-NMDC-ADNOC-T-05144 | 2026-04-07 | E1372-E-O-T-EPC-IFC-003338 | 1 | 2026-03-31 | 2035-NMDC-MWS-T-0504 | 2026-04-03 | SAF185-MCE-NPCC-T-225 | 1 - Approved
|  |  |  | 2 | 2 |  | 14-05-2025 01-06-2026 | CSE-2035-PMT-T-311 | 2026-06-01 | 2035-NMDC-ADNOC-T-05341 | 2026-06-17 | E1372-E-O-T-EPC-IFC-003370 | 1 | 2026-06-01 | 2035-NMDC-MWS-T-0573 | 2026-06-10 | SAF185-MCE-NPCC-T-238 | 1 - Approved
|  |  |  | 3 | 3 |  | 2026-07-31 | CSE-2035-PMT-T-346 | 2026-07-31 | 2035-NMDC-ADNOC-T-05545 | 2026-08-14 | E1372-E-O-T-EPC-IFC-003395 | 3 | 2026-07-31 | 2035-NMDC-MWS-T-0626 | 2026-08-03 | SAF185-MCE-NPCC-T-249 | 1 - Approved
|  |  |  | 4 | 3 |  | 2026-08-20 | CSE-2035-PMT-T-356 | 2026-08-21 | 2035-NMDC-ADNOC-T-05623 | 2026-09-03 | E1372-E-O-T-EPC-IFC-003409 | 1 | 2026-08-21 | 2035-NMDC-MWS-T-0644 | 2026-08-27 | SAF185-MCE-NPCC-T-252 | 1 - Approved
181 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF SPOOLS @AESEN-2811 | 2035-NN-0181 | AD-26-PL-640158 | 1 | 2 |  | 2026-05-01 | CSE-2035-PMT-T-303 | 2026-05-04 | 2035-NMDC-ADNOC-T-05253 | 2026-05-22 | E1372-E-O-T-EPC-IFR-003316 | 1 | 2026-05-04 | 2035-NMDC-MWS-T-0552
182 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES (PL-1) ON ASTRO-251 (TRIP-5) | 2035-NN-0182 | AD-26-PL-640159 | 1 | 2 |  | 2026-07-06 | CSE-2035-PMT-T-333 | 2026-07-07 | 2035-NMDC-ADNOC-T-05453 | 2026-08-06 | E1372-E-O-T-EPC-IFR-003378 | 4 | 2026-07-07 | 2035-NMDC-MWS-T-0609 | 09-07-2026 | SAF185-MCE-NPCC-T-245 | Approved
183 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (PL-9) ON ASTRO-251 (TRIP-5) | 2035-NN-0183 | AD-26-PL-640160 | 1 | 2 |  | 2026-07-24 | CSE-2035-PMT-T-341 | 2026-07-27 | 2035-NMDC-ADNOC-T-05501 | 18-08-2026 | E1372-E-O-T-EPC-IFR-003391 | 1 | 2026-07-27 | 2035-NMDC-MWS-T-0619 | 2026-08-12 | SAF185-MCE-NPCC-T-251 | 1 - Approved
184 | DETAIL OF 16" TEMPORARY PIG LAUNCHER & RECEIVER | 2035-NN-0184 | AD-26-PL-640161 | 1 | 2 |  | 2026-07-20 | CSE-2035-PMT-T-340 | 2026-07-31 | 2035-NMDC-ADNOC-T-05541 |  |  |  | 2026-07-31 | 2035-NMDC-MWS-T-0625
185 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CABLE REEL ON SAFEEN B-281 (TRIP-6) | 2035-NN-0185 | AD-26-PL-640162 | 1 | 2 |  | 2026-07-31 | CSE-2035-PMT-T-343 | 2026-07-31 | 2035-NMDC-ADNOC-T-05540 | 18-08-2026 | E1372-E-O-T-EPC-IFR-003388 | 1 | 2026-07-31 | 2035-NMDC-MWS-T-0624 | 2026-08-12 | SAF185-MCE-NPCC-T-251 | 1 - Approved
186 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF CC PIPES (PL-1) ON SAFEEN B-282 (TRIP-7) | 2035-NN-0186 | AD-26-PL-640163 | 1 | 2 |  | 2026-07-31 | CSE-2035-PMT-T-349 | 2026-08-04 | 2035-NMDC-ADNOC-T-05560 | 18-08-2026 | E1372-E-O-T-EPC-IFR-003390 | 1 | 2026-08-04 | 2035-NMDC-MWS-T-0631 | 2026-08-12 | SAF185-MCE-NPCC-T-251 | 1 - Approved
187 | LIFTING OF S-1400-A1 SLEEPERS AT CX-04 TO CX-05 AND TS-500A SLEEPERS AT BUCKLE TRIGGER - 1 BY HEA OCEANIC FOR 16" WELL FLUID PIPELINE FROM HP-3 TO USSC-RP1 (PL-8) | 2035-NN-0187 | AD-26-PL-640164 | 1 | 2 |  | 19-08-2026 | CSE-2035-PMT-T-355 | 19-08-2026 | 2035-NMDC-ADNOC-T-05614 |  |  |  | 19-08-2026 | 2035-NMDC-MWS-T-0642 | 2026-08-27 | SAF185-MCE-NPCC-T-252 | 1 - Approved
188 | LOADING ARRANGEMENT AND SEAFASTENING DETAILS OF 16” CC PIPES (PL-4) ON SAFEEN B-284 CB (TRIP-13) | 2035-NN-0188 | AD-26-PL-640165 | 1 | 2 |  | 10-08-2026 | CSE-2035-PMT-T-353 | 10-08-2026 | 2035-NMDC-ADNOC-T-05576 | 2026-09-03 | E1372-E-O-T-EPC-IFR-003399 | 1 | 10-08-2026 | 2035-NMDC-MWS-T-0636 | 2026-08-12 | SAF185-MCE-NPCC-T-251 | 1 - Approved
189 | SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) @ HP1 BY SAFEEN 3000 | 2035-NN-0189 | AD-26-PL-640166 | 1 | 3 |  | 17-08-2026 | CSE-2035-PMT-T-354 | 18-08-2026 | 2035-NMDC-ADNOC-T-05604 | 27-08-2026 | E1372-E-O-T-EPC-IFC-003407 | 2 | 18-08-2026 | 2035-NMDC-MWS-T-0640 | 2026-08-27 | SAF185-MCE-NPCC-T-252 | HOLD
|  |  |  | 2 | 3 |  | 04-09-2026 | CSE-2035-PMT-T-361 | 04-09-2026 | 2035-NMDC-ADNOC-T-05662 |  |  |  | 04-09-2026 | 2035-NMDC-MWS-T-0656
190 | SPOOL LIFTING AND INSTALLATION FOR 16" WATER INJECTION SUBSEA PIPELINE FROM HP2 TO HP1 (PL-11) @ HP2 BY SAFEEN 3000 | 2035-NN-0190 | AD-26-PL-640167 | 1 | 3 |  | 17-08-2026 | CSE-2035-PMT-T-354 | 18-08-2026 | 2035-NMDC-ADNOC-T-05605 | 27-08-2026 | E1372-E-O-T-EPC-IFC-003408 | 2 | 18-08-2026 | 2035-NMDC-MWS-T-0641 | 2026-08-27 | SAF185-MCE-NPCC-T-252 | 1 - Approved
|  |  |  | 2 | 3 |  | 04-09-2026 | CSE-2035-PMT-T-361 | 04-09-2026 | 2035-NMDC-ADNOC-T-05663 |  |  |  | 04-09-2026 | 2035-NMDC-MWS-T-0657
191 | SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM US-19B TO US-153A (PL-4) @US-19B BY SAFEEN 3000 | 2035-NN-0191 | AD-774/770-PL-640002 | 1 | 2 |  | 27-08-2026 | CSE-2035-PMT-T-359 | 27-08-2026 | 2035-NMDC-ADNOC-T-05648 |  |  |  | 27-08-2026 | 2035-NMDC-MWS-T-0650
192 | SPOOL LIFTING AND INSTALLATION FOR 16" WELL FLUID PIPELINE FROM US-19B TO US-153A (PL-4) @US-153A BY SAFEEN 3000 | 2035-NN-0192 | AD-774/770-PL-640003 | 1 | 2 |  | 27-08-2026 | CSE-2035-PMT-T-359 | 27-08-2026 | 2035-NMDC-ADNOC-T-05647 |  |  |  | 27-08-2026 | 2035-NMDC-MWS-T-0649
DOCUMENT CLASS : (1) ISSUED FOR APPROVAL; (2) ISSUED FOR REVIEW & COMMENTS; (3) ISSUED FOR INFORMATION
ADMA-OPCO APPROVAL CODE : (1) ACCEPTED; (2) ACCEPTED WITH COMMENTS; (2A) ACCEPTED WITH MINOR COMMENTS;
(3) NOT ACCEPTED, REVISE & RESUBMIT; (4) FOR INFORMATION

## Sketch
Project 2035-ADNOC
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2035 | OFO-P2035-SK-001 | 100 MT S.W.L SPREADER BAR DETAILS | 1 | D | √ | √ | 2023-03-24 | SKS | @
2 | 2035 | OFO-P2035-SK-002 | REEL LIFTING ARRANGEMENT |  |  |  |  | 2023-02-27 | SM
3 | 2035 | OFO-P2035-SK-003 | MARKER AND TRANSITION JOINTS (PL-1) | 1 | B | √ | √ | 2023-08-17 | AKS | @
4 | 2035 | OFO-P2035-SK-004 | MARKER AND TRANSITION JOINTS (PL-2) | 1 | B | √ | √ | 2023-08-17 | AKS | @
5 | 2035 | OFO-P2035-SK-005 | MARKER AND TRANSITION JOINTS (PL-3) | 1 | B | √ | √ | 2023-08-17 | AKS | @
6 | 2035 | OFO-P2035-SK-006 | MARKER AND TRANSITION JOINTS (PL-4) | 1 | B | √ | √ | 2023-08-17 | AKS | @
7 | 2035 | OFO-P2035-SK-007 | MARKER AND TRANSITION JOINTS (PL-5) | 1 | B | √ | √ | 2023-08-17 | AKS | @
8 | 2035 | OFO-P2035-SK-008 | MARKER AND TRANSITION JOINTS (PL-6) | 1 | B | √ | √ | 2023-08-17 | CDG | @
9 | 2035 | OFO-P2035-SK-009 | MARKER AND TRANSITION JOINTS (PL-7) | 1 | B | √ | √ | 2023-08-17 | AKS | @
10 | 2035 | OFO-P2035-SK-010 | MARKER AND TRANSITION JOINTS (PL-8) | 1 | B | √ | √ | 2023-08-17 | AKS | @
11 | 2035 | OFO-P2035-SK-011 | MARKER AND TRANSITION JOINTS (PL-9) | 1 | B | √ | √ | 2023-08-17 | AKS | @
12 | 2035 | OFO-P2035-SK-012 | MARKER AND TRANSITION JOINTS (PL-10) | 1 | B | √ | √ | 2023-08-17 | AKS | @
13 | 2035 | OFO-P2035-SK-013 | MARKER AND TRANSITION JOINTS (PL-11) | 1 | B | √ | √ | 2023-08-17 | AKS | @
14 | 2035 | OFO-P2035-SK-014 | HSS PEEL-OFF TEST REQUIREMENT | 1 | A | √ | √ | 2023-03-14 | CDG | @
15 | 2035 | OFO-P2035-SK-015 | TEMPORARY SUPPORT FOR HBC CROSSING LOCATION AT (PL-4) FROM US-19B TO US-153A @ US-19B | 1 | B | √ | √ | 2023-08-03 | REY | @
16 | 2035 | OFO-P2035-SK-016 | TEMPORARY SUPPORT FOR HBC CROSSING LOCATION AT (PL-10) FROM HP-3 TO HP-2 (PCKG-2) @ HP-3 | 1 | A | √ | √ | 2023-03-31 | REY | @
17 | 2035 | OFO-P2035-SK-017 | HAMMER HEAD CRANE VESSEL – GRAVITY ANCHORS ARRANGEMENT LAYOUT | 1 | A | √ | √ | 2023-04-26 | REY | @
18 | 2035 | OFO-P2035-SK-018 | DETAILS OF TEMPORARY SUPPORT H-900 (TS-01) | 1 + 5 | B, 1 | √ | √ | 2023-08-31 | CDG | @ | CSE-OF-2035-T-011 dated 01/09/2023
|  |  |  | 1 | C | √ | √ | 2024-05-28 | AKS | @
19 | 2035 | OFO-P2035-SK-019 | DETAILS OF TEMPORARY SUPPORT H-1050 (TS-02) | 1 + 4 | B, 1 | √ | √ | 2023-08-31 | AKS | @ | CSE-OF-2035-T-011 dated 01/09/2023
|  |  |  | 1 | C | √ | √ | 2024-05-28 | AKS | @
20 | 2035 | OFO-P2035-SK-020 | DETAILS OF TEMPORARY SUPPORT H-1250 (TS-03) | 1 + 4 | B, 1 | √ | √ | 2023-08-31 | AKS | @ | CSE-OF-2035-T-011 dated 01/09/2023
|  |  |  | 1 | C | √ | √ | 2024-05-28 | AKS | @
21 | 2035 | OFO-P2035-SK-021 | DETAILS OF TEMPORARY SUPPORT H-1600 (TS-04) | 1 + 4 | B, 1 | √ | √ | 2023-08-31 | AKS | @ | CSE-OF-2035-T-011 dated 01/09/2023
|  |  |  | 1 | C | √ | √ | 2024-05-28 | AKS | @
22 | 2035 | OFO-P2035-SK-022 | SAFEEN 3000 MISC. EQUIPMENT LAYOUT | 1 | A | √ | √ | 2023-06-09 | CDG | @
23 | 2035 | OFO-P2035-SK-023 | LIFTING ARRANGEMENT FOR DRILLING UNIT WIRTH 612/615 BY SAFEEN 3000 | 1 | B | √ | √ | 2023-07-28 | CDG | @
24 | 2035 | OFO-P2035-SK-024 | LIFTING ARRANGEMENT FOR DRILLING BHA WIRTH 612/615 BY SAFEEN 3000 | 1 | A | √ | √ | 2023-07-27 | CDG | @
25 | 2035 | OFO-P2035-SK-025 | DETAILS OF TEMPORARY SUPPORT AT (PL-10) 16" WI PIPELINE (WITH DUAL 2" PIGGYBACK) FROM HP3 TO HP2 | 1 + 3 | A, 0 | √ | √ | 2023-08-22 | AKS | @ | CSE-OF-2035-T-010 dated 23/08/2023
26 | 2035 | OFO-P2035-SK-026 | DETAILS OF TEMPORARY SUPPORT H-1100 (TS-06) | 1 + 5 | A, 0 | √ | √ | 2023-08-31 | AKS | @ | CSE-OF-2035-T-011 dated 01/09/2023
|  |  |  | 1 | B | √ | √ | 2024-05-28 | AKS | @
27 | 2035 | OFO-P2035-SK-027 | DETAILS OF TEMPORARY SUPPORT H-1200 (TS-07) | 1 + 5 | A, 0 | √ | √ | 2023-08-31 | AKS | @ | CSE-OF-2035-T-011 dated 01/09/2023
|  |  |  | 1 | B | √ | √ | 2024-05-28 | AKS | @
28 | 2035 | OFO-P2035-SK-028 | DETAILS OF TEMPORARY SUPPORT H-800 (TS-08) | 1 + 5 | A, 0 | √ | √ | 2023-08-31 | AKS | @ | CSE-OF-2035-T-011 dated 01/09/2023
|  |  |  | 1 | B | √ | √ | 2024-05-28 | AKS | @
29 | 2035 | OFO-P2035-SK-029 | DETAILS OF TEMPORARY SUPPORT H-800 (TS-09) | 1 + 5 | A, 0 | √ | √ | 2023-08-31 | AKS | @ | CSE-OF-2035-T-011 dated 01/09/2023
|  |  |  | 1 | B | √ | √ | 2024-05-28 | AKS | @
30 | 2035 | OFO-P2035-SK-030 | PIPELAY PROFILE WITH STINGER-SAFEEN-3000 | 1 | B | √ | √ | 2025-03-07 | HZD | @
31 | 2035 | OFO-P2035-SK-031 | FLANGE PROTECTOR DETAILS FOR 2" PIPE LINE (FLANGE TYPE) | 1 + 4 | A, 0 | √ | √ | 2023-09-13 | AKS | @ | CSE-OF-2035-T-012 dated 15/09/2023
32 | 2035 | OFO-P2035-SK-032 | PIGGING BACK PULLING HEAD FOR 2" PIPE LINE (FLANGE TYPE) | 1 + 5 | A, 0 | √ | √ | 2023-09-13 | AKS | @ | CSE-OF-2035-T-012 dated 15/09/2023
|  |  |  | 1 + 5 | B, 1 | √ | √ | 2023-11-14 | AKS | @ | CSE-OF-2035-T-014 dated 14/11/2023
33 | 2035 | OFO-P2035-SK-033 | STINGER SECTION-1 (SAFEEN-3000) | 1 | A | √ | √ | 2023-09-14 | AKS | @
34 | 2035 | OFO-P2035-SK-034 | TYPICAL ABANDONMENT & RECOVERY / LAYDOWN ARRANGEMENT | 1 | A | √ | √ | 2023-09-14 | AKS | @
35 | 2035 | OFO-P2035-SK-035 | HORIZONTAL (HBS) START-UP ARRANGEMENT 16" WELL FLUID PIPELINE FROM US-153A TO USSC-RP1 (PL-5) (WITH ∅2" SINGLE PIGGYBACK) | 1 | D | √ | √ | 2025-03-10 | ENH | @
36 | 2035 | OFO-P2035-SK-036 | SAFEEN-3000 PIGGYBACK CABLE LAYING ARRANGEMENT | 15 + 271 | A, 0 | √ | √ | 2023-10-10 | SC | @ | CSE-OF-2035-T-013 dated 24/10/2023
37 | 2035 | OFO-P2035-SK-037 | START-UP ARRANGEMENT 16" WELL FUID PIPELINE FROM US-159A TO US-12B (PL-1) | 1 | C | √ | √ | 2026-01-15 | LEO | @
38 | 2035 | OFO-P2035-SK-038 | STANCHIONS (W18x97) | 1 + 3 | A,0 | √ | √ | 2023-12-21 | SC | @
39 | 2035 | OFO-P2035-SK-039 | STANCHIONS (W24x131) | 1 + 3 | A,0 | √ | √ | 2023-12-22 | SC | @
40 | 2035 | OFO-P2035-SK-040 | STANCHIONS (W24x162) | 1 + 3 | A,0 | √ | √ | 2023-12-22 | SC | @
41 | 2035 | OFO-P2035-SK-041 | STANCHIONS (W27x94) | 1 + 3 | A,0 | √ | √ | 2023-12-21 | SC | @
42 | 2035 | OFO-P2035-SK-042 | STANCHIONS (W27x161) | 1 + 3 | A,0 | √ | √ | 2023-12-21 | SC | @
43 | 2035 | OFO-P2035-SK-043 | AIR TUGGER GUIDE ROLLER ON CCC MARITIME - 2 | 1 | B | √ | √ | 2023-12-26 | AKS | @
44 | 2035 | OFO-P2035-SK-044 | SAFEEN-3000 STERN EXTENSION LIFTING ARRANGEMENT | 2 | B | √ | √ | 2024-02-01 | REY | @
45 | 2035 | OFO-P2035-SK-045 | HORIZONTAL (HBS) START-UP ARRANGEMENT 16" WF PIPELINE FROM US-12B TO USSC-RP1 (PL-2) AT RP-1 | 1 | C | √ | √ | 2025-11-21 | LEO | @
46 | 2035 | OFO-P2035-SK-046 | DAVIT LIFTING STROPS DETAILS | 1 | A | √ | √ | 2024-03-06 | AKS | @
47 | 2035 | OFO-P2035-SK-047 | AIR BAG ARRANGEMENTS FOR 16 & 18” PIPELINE | 2 | B | √ | √ | 2024-08-20 | NAR | @
48 | 2035 | OFO-P2035-SK-048 | HORIZONTAL (HBS) START-UP ARRANGEMENT FOR 18" WELL FLUID PIPELINE FROM HP-2 TO USSC-RP1 (PL-7)” |  |  |  |  | 2024-07-22 | CDG
49 | 2035 | OFO-P2035-SK-049 | EQUIPMENT LAYOUT ON SAFEEN-3000 | 2 | B | √ | √ | 2024-04-16 | SKS | @
50 | 2035 | OFO-P2035-SK-050 | TYPICAL PERSONNEL TRANSFER BASKET ARRANGEMENT FROM VESSEL / CARGO BARGE | 2 | A | √ | √ | 2024-05-10 | HZD | @
51 | 2035 | OFO-P2035-SK-051 | CABLE TRANSFER BETWEEN UMM SHAIF AND CABLE TANK | 2 | A | √ | √ | 2024-05-09 | CDG | @
52 | 2035 | OFO-P2035-SK-052 | LIFTING & INSTALLATION OF 26m GANGWAY AT CSP-01 | 1 | A | √ | √ | 2024-05-23 | AKS | @
53 | 2035 | OFO-P2035-SK-053 | HORIZONTAL (HBS) START-UP ARRANGEMENT 16" WF PIPELINE FROM US-142A TO USSC-RP1 (PL-3) AT RP-1 | 1 | C | √ | √ | 2025-02-04 | ENH | @
54 | 2035 | OFO-P2035-SK-054 | GANGWAY ARRANGEMENT BETWEEN PLATFORM AND VESSEL AT LOCATION-2 | 2 | C | √ | √ | 2024-07-05 | HZD | @
55 | 2035 | OFO-P2035-SK-055 | GANGWAY ARRANGEMENT BETWEEN PLATFORM AND VESSEL POSITION-III |  |  |  |  | 2024-06-27 | SKS
56 | 2035 | OFO-P2035-SK-056 | ADDITIONAL PADEYE ARRANGEMENT AT LB-II | 1 | A,0 | √ | √ | 2024-10-09 | AKS | @
57 | 2035 | OFO-P2035-SK-057 | LB-II MOORING WINCH LOAD TEST ARRANGEMENT | 1 | A | √ | √ | 2024-07-27 | AKS | @
58 | 2035 | OFO-P2035-SK-058 | SAFEEN PEARL CABLE LAYOUT ARRANGEMENT | 1 | F | √ | √ | 2025-07-22 | LRA | @
59 | 2035 | OFO-P2035-SK-059 | DMA START-UP ARRANGEMENT PROPOSED (PL-4) 16" WELL FLUID PL. FROM US-19B TO US-153A (PACKAGE-1) | 1 | B | √ | √ | 2026-03-09 | SSK | @
60 | 2035 | OFO-P2035-SK-060 | DMA START-UP ARRAMGEMENT (PL-10) PROPOSED 16" WI PLATFORM HP-3 TO HP-2 | 1 | D | √ | √ | 2026-04-09 | SSK | @
61 | 2035 | OFO-P2035-SK-061 | TEMPORARY HANG OFF CLAMP for 87.2 DIA CABLE. | 1 + 3 | A,0 | √ | √ | 2024-09-18 | SKT | @
62 | 2035 | OFO-P2035-SK-062 | TEMPORARY HANG OFF CLAMP for 97.3 DIA CABLE. | 1 + 3 | A,0 | √ | √ | 20/09/2024 | SKT | @
63 | 2035 | OFO-P2035-SK-063 | CABLE LAYING QUADRANT | 1 | A | √ | √ | 2024-09-25 | SKT | @
64 | 2035 | OFO-P2035-SK-064 | SEP-750 LIFTING & OFFLODING ARRANGEMENT FOR 20 FT. CONTAINER | 1 | A | √ | √ | 2024-09-28 | HZD | @
65 | 2035 | OFO-P2035-SK-065 | SEP-750 LIFTING & OFFLODING ARRANGEMENT FOR SCAFFOLDING PIPE BUNDLE | 1 | A | √ | √ | 2024-09-28 | HZD | @
66 | 2035 | OFO-P2035-SK-066 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PERSONNEL TRANSFER BASKET | 2 | B | √ | √ | 2024-10-04 | HZD | @
67 | 2035 | OFO-P2035-SK-067 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER USING MAIN CRANE | 1 | A | √ | √ | 2024-10-01 | HZD | @
68 | 2035 | OFO-P2035-SK-068 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR SCAFFOLDING PIPE BUNDLE USING MAIN CRANE | 1 | A | √ | √ | 2024-10-02 | HZD | @
69 | 2035 | OFO-P2035-SK-069 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER AT US 142 | 2 | A | √ | √ | 2024-11-19 | AKS | @
70 | 2035 | OFO-P2035-SK-070 | SEP-450 TRIDENT LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM DECK TO US-142 PLATFORM | 2 | A | √ | √ | 2024-11-19 | AKS | @
71 | 2035 | OFO-P2035-SK-071 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH AT US 142 PLATFORM | 2 | A | √ | √ | 2024-11-19 | AKS | @
72 | 2035 | OFO-P2035-SK-072 | SEP-450 LIFTING & OFFLOADING BILLY PUGH FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US-142 | 2 | A | √ | √ | 2024-11-19 | AKS | @
73 | 2035 | OFO-P2035-SK-073 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY AT US 142 PLATFORM | 2 | A | √ | √ | 2024-11-19 | AKS | @
74 | 2035 | OFO-P2035-SK-074 | SEP-450 LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT US 142 | 1 | A | √ | √ | 2024-11-19 | AKS | @
75 | 2035 | OFO-P2035-SK-075 | SEAFOX TRIDENT LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH AT US 142 PLATFORM | 2 | D | √ | √ | 2024-11-24 | AKS | @
76 | 2035 | OFO-P2035-SK-076 | SEAFOX TRIDENT LIFTING & OFFLOADING BILL PUGH FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US 142 | 2 | D | √ | √ | 2024-11-24 | AKS | @
77 | 2035 | OFO-P2035-SK-077 | SEAFOX TRIDENT LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER AT US 142 | 2 | D | √ | √ | 2024-11-24 | AKS | @
78 | 2035 | OFO-P2035-SK-078 | SEAFOX TRIDENT LIFTING & OFFLOADING ARRANGEMENT FOR 10 FT. CONTAINER FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US 142 | 2 | D | √ | √ | 2024-11-24 | AKS | @
79 | 2035 | OFO-P2035-SK-079 | SEAFOX TRIDENT LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY AT US 142 PLATFORM | 2 | E | √ | √ | 2024-11-24 | AKS | @
80 | 2035 | OFO-P2035-SK-080 | SEAFOX TRIDENT LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT US 142 | 1 | E | √ | √ | 2024-11-25 | AKS | @
81 | 2035 | OFO-P2035-SK-081 | RECOVERY OF ZODIAC ARRANGEMENT FROM SEAFOX TRIDENT |  |  |  |  | 2024-10-11 | CDG
82 | 2035 | OFO-P2035-SK-082 | SEP-450 RECOVERY OF ZODIAC ARRANGEMENT AT US 142 | 2 | A | √ | √ | 2024-11-21 | AKS | @
83 | 2035 | OFO-P2035-SK-083 | SEP-450 REMOVAL ARRANGEMENT OF GANGWAY AT US 142 | 1 | A | √ | √ | 2024-11-25 | AKS | @
84 | 2035 | OFO-P2035-SK-084 | SEP-650 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH AT US 153 PLATFORM | 2 | B | √ | √ | 2024-10-24 | HZD | @
85 | 2035 | OFO-P2035-SK-085 | SEAFOX TRIDENT REMOVAL ARRANGEMENT OF GANGWAY AT US 142 | 1 | E | √ | √ | 2024-11-25 | AKS | @
86 | 2035 | OFO-P2035-SK-086 | SEP-650 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER AT US 153 | 2 | B | √ | √ | 2024-10-24 | HZD | @
87 | 2035 | OFO-P2035-SK-087 | SEP-650 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US 153 | 2 | B | √ | √ | 2024-10-24 | HZD | @
88 | 2035 | OFO-P2035-SK-088 | SEP-650 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY AT US 153 PLATFORM | 2 | B | √ | √ | 2024-10-24 | HZD | @
89 | 2035 | OFO-P2035-SK-089 | SEP-650 LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT US 153 | 1 | B | √ | √ | 2024-10-24 | HZD | @
90 | 2035 | OFO-P2035-SK-090 | SEP-650 REMOVAL ARRANGEMENT OF GANGWAY AT US 153 | 1 | B | √ | √ | 2024-10-24 | HZD | @
91 | 2035 | OFO-P2035-SK-091 | RECOVERY OF ZODIAC ARRANGEMENT SEAFOX TRIDENT DECK AT US 142 | 2 | D | √ | √ | 2024-11-24 | AKS | @
92 | 2035 | OFO-P2035-SK-092 | RECOVERY OF ZODIAC ARRANGEMENT FROM SEP-650 DECK AT US 153 |  |  |  |  | 2024-10-12 | AKS
93 | 2035 | OFO-P2035-SK-093 | SEP-650 RECOVERY OF ZODIAC ARRANGEMENT AT US 153 | 2 | B | √ | √ | 2024-10-24 | HZD | @
94 | 2035 | OFO-P2035-SK-094 | SEP-650 LIFTING & OFFLOADINGBILLY POGH FROM DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US 153 | 2 | B | √ | √ | 2024-10-24 | HZD | @
95 | 2035 | OFO-P2035-SK-095 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER AT US 159 | 2 | B | √ | √ | 2024-11-04 | AKS | @
96 | 2035 | OFO-P2035-SK-096 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US 159 | 2 | B | √ | √ | 2024-11-04 | AKS | @
97 | 2035 | OFO-P2035-SK-097 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY AT US 159 PLATFORM | 2 | B | √ | √ | 2024-11-04 | AKS | @
98 | 2035 | OFO-P2035-SK-098 | HEA KRAKEN LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT US 159 | 1 | B | √ | √ | 2024-11-04 | AKS | @
99 | 2035 | OFO-P2035-SK-099 | HEA KRAKEN REMOVAL ARRANGEMENT OF GANGWAY AT US 159 | 1 | B | √ | √ | 2024-11-04 | AKS | @
100 | 2035 | OFO-P2035-SK-100 | RECOVERY OF ZODIAC ARRANGEMENT FROM HEA KRAKEN DECK AT US 159 | 2 | B | √ | √ | 2024-11-04 | AKS | @
101 | 2035 | OFO-P2035-SK-101 | SEP-650 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL AT US 159 | 2 | B | √ | √ | 2024-10-24 | HZD | @
102 | 2035 | OFO-P2035-SK-102 | SEP-650 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US 159 | 2 | B | √ | √ | 2024-10-24 | HZD | @
103 | 2035 | OFO-P2035-SK-103 | SEAFOX TRIDENT LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL AT US 142 | 2 | D | √ | √ | 2024-11-24 | AKS | @
104 | 2035 | OFO-P2035-SK-104 | SEAFOX TRIDENT LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US 142 | 2 | D | √ | √ | 2024-11-24 | AKS | @
105 | 2035 | OFO-P2035-SK-105 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL AT US 142 | 2 | A | √ | √ | 2024-11-21 | AKS | @
106 | 2035 | OFO-P2035-SK-106 | SEP-450 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US 142 | 2 | A | √ | √ | 2024-11-21 | AKS | @
107 | 2035 | OFO-P2035-SK-107 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL AT US 159 | 2 | B | √ | √ | 2024-11-04 | AKS | @
108 | 2035 | OFO-P2035-SK-108 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US 159 | 2 | B | √ | √ | 2024-11-04 | AKS | @
109 | 2035 | OFO-P2035-SK-109 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH AT US 159 PLATFORM | 2 | B | √ | √ | 2024-11-04 | AKS | @
110 | 2035 | OFO-P2035-SK-110 | HEA KRAKEN LIFTING & OFFLOADING BILL PUGH FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US 159 | 2 | B | √ | √ | 2024-11-04 | AKS | @
111 | 2035 | OFO-P2035-SK-111 | TYPICAL LIFTING ARRANGEMENT OF 70MT GRAVITY ANCHOR BY DLB-1000 | 1 | B | √ | √ | 2024-10-30 | REY | @
112 | 2035 | OFO-P2035-SK-112 | PADEYE DETAIL ON SAFEEN OSV PEARL BOOM REST | 1 | A | √ | √ | 2024-11-07 | SKT | @
113 | 2035 | OFO-P2035-SK-113 | SEA FASTENING GRILLAGE LAYOUT & DETAILS | 2 + 41 | B, 0 | √ | √ | 2025-03-20 | SKT | @ | Rahul actioned on 21/03/25 (email)
114 | 2035 | OFO-P2035-SK-114 | CABLE TOWER DETAILS | 6 | C | √ | √ | 2025-04-10 | SKT | @ | Rahul actioned on 21/03/25 (email)
115 | 2035 | OFO-P2035-SK-115 | REMOVAL AND RE-INSTALLATION OF SAFEEN PEARL CRANE BOOM REST | 1 | A | √ | √ | 2024-11-12 | CDG | @
116 | 2035 | OFO-P2035-SK-116 | STORAGE QUADRANT-1.2M RADIUS FOR 16" J-TUBE | 1 + 9 | B,0 | √ | √ | 2025-04-30 | SKT | @
117 | 2035 | OFO-P2035-SK-117 | TYPICAL CABLE PULLING ARRANGEMENT AT US-142A | 1 | A | √ | √ | 2025-01-17 | CDG | @
118 | 2035 | OFO-P2035-SK-118 | RIGGING PLATFORM INSTALLATION ON BST-S13 JACKET BY DLB-1000 |  |  |  |  | 2024-11-18 | CDG
119 | 2035 | OFO-P2035-SK-119 | LIFTING AND INSTALLATION OF 30" BRACE RIGGING ARRANGEMENT BELOW BRIDGE LANDING BY DLB-1000 |  |  |  |  | 2024-12-06 | NAR
120 | 2035 | OFO-P2035-SK-120 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY SAFEEN-3000 | 2 | A | √ | √ | 2025-01-09 | AKS | @
121 | 2035 | OFO-P2035-SK-121 | UMM SHAIF PL-8 CX-01 TEMPORARY SUPPORT | 2 | A | √ | √ | 2025-01-10 | SKT | @
122 | 2035 | OFO-P2035-SK-122 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER AT US-19/19A | 2 | A | √ | √ | 2025-04-16 | NAR | @
123 | 2035 | OFO-P2035-SK-123 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US -19/19A | 2 | A | √ | √ | 2025-04-16 | NAR | @
124 | 2035 | OFO-P2035-SK-124 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY AT US-19/19A PLATFORM | 2 | B | √ | √ | 2025-04-16 | NAR | @
125 | 2035 | OFO-P2035-SK-125 | HEA KRAKEN LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT US-19/19A | 1 | B | √ | √ | 2025-04-16 | NAR | @
126 | 2035 | OFO-P2035-SK-126 | HEA KRAKEN REMOVAL ARRANGEMENT OF GANGWAY AT US-19/19A | 1 | B | √ | √ | 2025-04-16 | NAR | @
127 | 2035 | OFO-P2035-SK-127 | RECOVERY OF ZODIAC ARRANGEMENT FROM HEA KRAKEN DECK AT US-19/19A | 1 | A | √ | √ | 2025-01-14 | AKS | @
128 | 2035 | OFO-P2035-SK-128 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL AT US-19/19A | 2 | B | √ | √ | 2025-04-16 | NAR | @
129 | 2035 | OFO-P2035-SK-129 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US-19/19A | 2 | B | √ | √ | 2025-04-16 | NAR | @
130 | 2035 | OFO-P2035-SK-130 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH AT US-19/19A PLATFORM | 2 | B | √ | √ | 2025-04-16 | NAR | @
131 | 2035 | OFO-P2035-SK-131 | HEA KRAKEN LIFTING & OFFLOADING BILLY PUGH FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US-19/19A | 2 | B | √ | √ | 2025-04-16 | NAR | @
132 | 2035 | OFO-P2035-SK-132 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER AT US-12/12A | 1 | A | √ | √ | 2025-01-14 | AKS | @
133 | 2035 | OFO-P2035-SK-133 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US -12/12A | 1 | A | √ | √ | 2025-01-14 | AKS | @
134 | 2035 | OFO-P2035-SK-134 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY AT US-12/12A PLATFORM | 1 | A | √ | √ | 2025-01-14 | AKS | @
135 | 2035 | OFO-P2035-SK-135 | HEA KRAKEN LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT US-12/12A | 1 | A | √ | √ | 2025-01-14 | AKS | @
136 | 2035 | OFO-P2035-SK-136 | HEA KRAKEN REMOVAL ARRANGEMENT OF GANGWAY AT US-12/12A | 1 | A | √ | √ | 2025-01-14 | AKS | @
137 | 2035 | OFO-P2035-SK-137 | RECOVERY OF ZODIAC ARRANGEMENT FROM HEA KRAKEN DECK AT US-12/12A | 1 | A | √ | √ | 2025-01-14 | AKS | @
138 | 2035 | OFO-P2035-SK-138 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL AT US-12/12A | 1 | A | √ | √ | 2025-01-14 | AKS | @
139 | 2035 | OFO-P2035-SK-139 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US-12/12A | 1 | A | √ | √ | 2025-01-14 | AKS | @
140 | 2035 | OFO-P2035-SK-140 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH AT US-12/12A PLATFORM | 1 | A | √ | √ | 2025-01-14 | AKS | @
141 | 2035 | OFO-P2035-SK-141 | HEA KRAKEN LIFTING & OFFLOADING BILLY PUGH FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US-12/12A | 1 | A | √ | √ | 2025-01-14 | AKS | @
142 | 2035 | OFO-P2035-SK-142 | UMM SHAIF PL-9 CX-16 TEMPORARY SUPPORT | 2 | A | √ | √ | 2025-01-16 | SKT | @
143 | 2035 | OFO-P2035-SK-143 | LAYOUT FOR TEMPORARY SUPPORT IN UMM SHAIF PL-8 CX-16 | 1 | A | √ | √ | 2025-01-16 | SKT | @
144 | 2035 | OFO-P2035-SK-144 | HEA KRAKEN LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT BRIDGE B-26 | 1 | A | √ | √ | 2025-01-24 | NAR | @
145 | 2035 | OFO-P2035-SK-145 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL AT BRIDGE B-26 | 2 | A | √ | √ | 2025-01-27 | AKS | @
146 | 2035 | OFO-P2035-SK-146 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT BRIDGE B-26 | 2 | A | √ | √ | 2025-01-27 | AKS | @
147 | 2035 | OFO-P2035-SK-147 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH AT BRIDGE B-26 PLATFORM | 1 | A | √ | √ | 2025-01-28 | AKS | @
148 | 2035 | OFO-P2035-SK-148 | HEA KRAKEN LIFTING & OFFLOADING BILLY PUGH FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT BRIDGE B-26 | 1 | A | √ | √ | 2025-01-28 | AKS | @
149 | 2035 | OFO-P2035-SK-149 | RECOVERY OF ZODIAC ARRANGEMENT FROM HEA KRAKEN DECK AT BRIDGE B-26 | 1 | A | √ | √ | 2025-01-28 | AKS | @
150 | 2035 | OFO-P2035-SK-150 | HEA KRAKEN LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY AT BRIDGE B-26 PLATFORM | 1 | A | √ | √ | 2025-01-28 | AKS | @
151 | 2035 | OFO-P2035-SK-151 | START-UP ARRANGEMENT FOR 16" WELL FUID PIPELINE FROM US-159A TO US-12B (PKG.-1)” | 1 | A | √ | √ | 2025-02-06 | CDG | @
152 | 2035 | OFO-P2035-SK-152 | SAFEEN 3000 DECK LAYOUT FOR PIPELAY WITH PIGGYBACK REELS | 1 | A | √ | √ | 2025-03-07 | CDG | @ | REV-B SERVER ONLY
153 | 2035 | OFO-P2035-SK-153 | REELS CRADLE DETAILS |  |  |  |  | 2025-03-03 | CDG
154 | 2035 | OFO-P2035-SK-154 | PERSONNEL TRANSFER USING STEEL BASKET (DLB-1000) | 2 | B | √ | √ | 2025-04-02 | CDG | @
155 | 2035 | OFO-P2035-SK-155 | TYPICAL CABLE PULLING ARRANGEMENTS AT US159A | 3 | B | √ | √ | 2025-05-02 | SKT | @
156 | 2035 | OFO-P2035-SK-156 | TYPICAL CABLE PULLING ARRANGEMENTS AT HP-3 | 2 | B | √ | √ | 2025-05-02 | SKT | @
157 | 2035 | OFO-P2035-SK-157 | TYPICAL CABLE PULLING ARRANGEMENTS AT USSC-RP1 | 2 | B | √ | √ | 2025-05-02 | SKT | @
158 | 2035 | OFO-P2035-SK-158 | SAFEEN-3000 STINGER SECTION-1 ON CB-6 LOADING ARRANGEMENT & SEAFASTENING DETAILS |  |  |  |  | 2025-03-13 | SKS
159 | 2035 | OFO-P2035-SK-159 | TYPICAL LIFTING ARRANGEMENT OF 70MT GRAVITY ANCHOR BY SAFEEN-3000 |  |  |  |  | 2025-03-27 | MF
160 | 2035 | OFO-P2035-SK-160 | CABLE TOWER LADDER DETAIL |  |  |  |  | 2025-03-28 | HZD/AMK
161 | 2035 | OFO-P2035-SK-161 | DAVIT LIFT AT US-142A FOR PL-3 WITH DLB-1000 (STBD SIDE) | 1 | A | √ | √ | 2025-04-05 | ENH | @
162 | 2035 | OFO-P2035-SK-162 | STALK-ON AT RP1 FOR PL-3 WITH DLB-1000 (STBD SIDE) | 1 | A | √ | √ | 2025-04-05 | ENH | @
163 | 2035 | OFO-P2035-SK-163 | STALK-ON AT RP1 FOR PL-5 WITH DLB-1000 (STBD SIDE) | 1 | B | √ | √ | 2025-07-04 | ENH | @
164 | 2035 | OFO-P2035-SK-164 | Loading arrangement of misc. equipment on Safeen-3000 main deck | 1 | A | √ | √ | 2025-04-09 | AMEER | @
165 | 2035 | OFO-P2035-SK-165 | STALK-ON AT RP1 FOR PL-7 WITH DLB-1000 (STBD SIDE) | 1 | A | √ | √ | 2025-04-09 | ENH | @
166 | 2035 | OFO-P2035-SK-166 | SEAFASTENING DETAILS OF CABLE BASKET ON SAFEEN PEARL VESSEL | 1 | A | √ | √ | 2025-05-06 | VICTOR | @
167 | 2035 | OFO-P2035-SK-167 | SAFEEN PEARL LIFTING & OFFLOADING ARRANGEMENT FOR PERSONNEL TRANSFER BASKET AT RP-1 PLATFORM | 1 | A | √ | √ | 2025-04-22 | CDG | @
168 | 2035 | OFO-P2035-SK-168 | SAFEEN PEARL LIFTING & OFFLOADING ARRANGEMENT FOR PERSONNEL TRANSFER BASKET AT US142A PLATFORM | 1 | A | √ | √ | 2025-04-22 | CDG | @
169 | 2035 | OFO-P2035-SK-169 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY AT S06 PLATFORM | 2 | A | √ | √ | 2025-04-11 | SHM | @
170 | 2035 | OFO-P2035-SK-170 | SEP-750 LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT S06 PLATFORM | 1 | B | √ | √ | 2025-05-01 | SHM | @
171 | 2035 | OFO-P2035-SK-171 | SEP-750 REMOVAL ARRANGEMENT OF GANGWAY AT S06 PLATFORM | 1 | B | √ | √ | 2025-05-01 | SHM | @
172 | 2035 | OFO-P2035-SK-172 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH AT S06 PLATFORM | 2 | A | √ | √ | 2025-04-16 | SHM | @
173 | 2035 | OFO-P2035-SK-173 | SEP-750 LIFTING & OFFLOADING BILLY PUGH FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT S06 PLATFORM | 2 | A | √ | √ | 2025-04-16 | SHM | @
174 | 2035 | OFO-P2035-SK-174 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL AT S06 PLATFORM | 2 | B | √ | √ | 2025-05-01 | SHM | @
175 | 2035 | OFO-P2035-SK-175 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT S06 PLATFORM | 2 | B | √ | √ | 2025-05-01 | SHM | @
176 | 2035 | OFO-P2035-SK-176 | SEP-750 LIFTING FOR LAUNCHING AND RECOVERY OF ZODIAC AT S06 PLATFORM | 2 | B | √ | √ | 2025-05-01 | SHM | @
177 | 2035 | OFO-P2035-SK-177 | LIFTING PLAN FOR STABBING GUIDE | 2 | A | √ | √ | 2025-04-15 | HZD | @
178 | 2035 | OFO-P2035-SK-178 | A-FRAME ARRANGEMENTS FOR CABLE PULLING | 3 | B | √ | √ | 2025-05-30 | VDA | @
179 | 2035 | OFO-P2035-SK-179 | HORIZONTAL (HBS) START-UP ARRANGEMENT FOR 16" WELL FLUID PIPELINE FROM HP-3 TO USSC-RP1 (PL-8) | 1 | B | √ | √ | 2025-11-03 | SKS | @
180 | 2035 | OFO-P2035-SK-180 | HORIZONTAL (HBS) START-UP ARRANGEMENT FOR 16" WATER INJECTION PIPELINE FROM HP-3 TO USSC-RP1 (PL-9) | 1 | B | √ | √ | 2025-09-15 | CDG | @
181 | 2035 | OFO-P2035-SK-181 | TYPICAL CABLE PULLING ARRANGEMENT AT HP3 (WITH TOPSIDE) | 2 | B | √ | √ | 2025-08-11 | SKT | @
182 | 2035 | OFO-P2035-SK-182 | TYPICAL CABLE PULLING ARRANGEMENT AT RP1 (WITH TOPSIDE) | 2 | B | √ | √ | 2025-08-11 | SKT | @
183 | 2035 | OFO-P2035-SK-183 | GROUT BAG LIFTING ARRANGEMENT BY SAFEEN PEARL | 1 | A | √ | √ | 2025-04-24 | CDG | @
183 | 2035 | OFO-P2035-SK-184 | SAPURA-1200 LOADING ARRANGEMENT FOR PIGGYBACK PIPE LAYING | 1 | B | √ | √ | 2025-05-21 | CDG | @
184 | 2035 | OFO-P2035-SK-185 | TYPICAL CABLE PULLING ARRANGEMENT AT US159A (WITH TOPSIDE) | 2 | B | √ | √ | 2025-08-11 | SKT | @
185 | 2035 | OFO-P2035-SK-186 | ROLLER SUPPORTS FOR PIGGYBACK PIPE LAYING IN WAY OF HATCH OPENING | 1 | B | √ | √ | 2025-05-21 | CDG | @
186 | 2035 | OFO-P2035-SK-187 | SEAFOX TRIDENT LIFTING & OFFLOADING BILLY PUGH FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US-218 | 2 | A | √ | √ | 2025-05-12 | NAR | @
187 | 2035 | OFO-P2035-SK-188 | STINGER SECTION LAYOUT - SAPURA 1200 | 1 | A | √ | √ | 2025-05-12 | MF | @
188 | 2035 | OFO-P2035-SK-189 | TYPICAL CABLE PULLING ARRANGEMENT AT US-218 (WITH TOPSIDE) | 2 | B | √ | √ | 2025-08-11 | SKT | @
189 | 2035 | OFO-P2035-SK-190 | TYPICAL CABLE PULLING ARRANGEMENT AT US-216 (WITH TOPSIDE) | 2 | B | √ | √ | 2025-08-11 | SKT | @
191 | 2035 | OFO-P2035-SK-191 | SEAFOX TRIDENT LIFTING & OFFLOADING BILLY PUGH FROM VESSEL TO BARGE DECK AND FROM BARGE DECK TO VESSEL AT US-218 | 1 | A | √ | √ | 2025-05-13 | NAR | @
192 | 2035 | OFO-P2035-SK-192 | PL-9 AT CX16 TEMPORARY SUPPORT LIFTING ARRANGEMENT BY SAFEEN PEARL |  |  |  |  | 2025-05-13 | HZD
193 | 2035 | OFO-P2035-SK-193 | PIPELAY PROFILE WITH STINGER - SAPURA 1200 | 1 | A | √ | √ | 2025-05-14 | CDG | @
194 | 2035 | OFO-P2035-SK-194 | ABANDONMENT & RECOVERY / LAYDOWN ARRANGEMENT FOR PROPOSED 16" WI PIPELINE FROM HP3 TO HP2 (PL-10 WITH SAPURA 1200 (TYPICAL) | 1 | A | √ | √ | 2025-05-15 | CDG | @
195 | 2035 | OFO-P2035-SK-195 | DMA START UP ARRANGEMENT (PL-10) PROPOSED 16" WI PL.FROM HP-3 TO HP-2 WITH SAPURA 1200 | 1 | C | √ | √ | 2026-02-12 | LEO | @
196 | 2035 | OFO-P2035-SK-196 | HORIZONTAL (HBS) START-UP ARRANGEMENT 16" WF PIPELINE FROM US-142A TO USSC-RP1 (PL-3) AT RP-1 BY SAPURA 1200 | 1 | A | √ | √ | 2025-05-15 | CDG | @
197 | 2035 | OFO-P2035-SK-197 | TYPICAL CABLE PULLING ARRANGEMENT AT US-19B (WITHOUT TOPSIDE) | 2 | B | √ | √ | 2025-08-08 | SKT | @
198 | 2035 | OFO-P2035-SK-198 | TYPICAL CABLE PULLING ARRANGEMENT AT US-19B (WITH TOPSIDE) | 2 | A | √ | √ | 2025-07-18 | SKT | @
199 | 2035 | OFO-P2035-SK-199 | TYPICAL CABLE PULLING ARRANGEMENT AT PDP (WITH TOPSIDE) |  |  |  |  | 2025-05-15 | SKT
200 | 2035 | OFO-P2035-SK-200 | SAPURA 1200 - VESSEL ROLLER SETTING | 1 | A | √ | √ | 2025-05-16 | AMEER | @
201 | 2035 | OFO-P2035-SK-201 | SAPURA 1200 - STINGER ROLLER SETTING | 1 | B | √ | √ | 2025-07-15 | AMEER | @ | T-020 - 16-07-2025
202 | 2035 | OFO-P2035-SK-202 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY SAPURA 1200 | 4 | A | √ | √ | 2025-05-25 | NAR | @
203 | 2035 | OFO-P2035-SK-203 | SEAFOX TRIDENT LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH AT US-216 PLATFORM | 2 | A | √ | √ | 2025-05-26 | SHIJU | @
204 | 2035 | OFO-P2035-SK-204 | SEAFOX TRIDENT LIFTING & OFFLOADING BILLY PUGH FROM BARGE DECK TO PLATFORM AND FROM PLATFORM TO BARGE DECK AT US 216 | 2 | A | √ | √ | 2025-05-26 | SHIJU | @
205 | 2035 | OFO-P2035-SK-205 | HORIZONTAL (HBS) START-UP ARRANGEMENT FOR 18" WELL FLUID PIPELINE FROM HP-2 TO USSC-RP1 (PL-7) – SAPURA 1200 | 1 | B | √ | √ | 2025-06-23 | CDG | @
206 | 2035 | OFO-P2035-SK-206 | Horizontal (HBS) Start-Up Arrangement for Proposed 16” Well Fluid Pipeline from US-153A to USSC-RP1 (PL-5) with Sapura 1200 | 1 | A | √ | √ | 2025-06-22 | HZD | @
207 | 2035 | OFO-P2035-SK-207 | DMA START-UP ARRANGEMENT (PL-4) PROPOSED 16" WF PL. FROM US-19B TO US-153A WITH SAPURA 1200 | 1 | B | √ | √ | 2026-02-16 | LEO | @
208 | 2035 | OFO-P2035-SK-208 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY FROM VESSL TO BARGE AT US 142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
209 | 2035 | OFO-P2035-SK-209 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY FROM BARGE TO VESSEL AT US 142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
210 | 2035 | OFO-P2035-SK-210 | SEP-750 LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT US 142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
211 | 2035 | OFO-P2035-SK-211 | SEP-750 REMOVAL ARRANGEMENT OF GANGWAY AT US 142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
212 | 2035 | OFO-P2035-SK-212 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH FROM VESSEL TO BARGE AT US142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
213 | 2035 | OFO-P2035-SK-213 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH FROM BARGE TO VESSEL AT US142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
214 | 2035 | OFO-P2035-SK-214 | SEP-750 LIFTING & OFFLOADING BILLY PUGH FROM BARGE DECK TO PLATFORM AT US 142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
215 | 2035 | OFO-P2035-SK-215 | SEP-750 LIFTING & OFFLOADING BILLY PUGH FROM PLATFORM TO BARGE DECK AT US 142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
216 | 2035 | OFO-P2035-SK-216 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM VESSEL TO BARGE AT US142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
217 | 2035 | OFO-P2035-SK-217 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE TO VESSEL AT US142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
218 | 2035 | OFO-P2035-SK-218 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AT US142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
219 | 2035 | OFO-P2035-SK-219 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM PLAT FORM TO BARGE DECK AT US142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
220 | 2035 | OFO-P2035-SK-220 | TYPICAL LIFTING ARRANGEMENT OF 70 MT GRAVITY ANCHOR BY SAPURA 1200 | 1 | A | √ | √ | 2025-07-09 | JH | @
221 | 2035 | OFO-P2035-SK-221 | SAFEEN PEARL CABLE LAY CHUTE SHIFT TO STERN | 1 | A | √ | √ | 2025-07-31 | LE0 | @
222 | 2035 | OFO-P2035-SK-222 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM VESSEL TO BARGE AT US142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
223 | 2035 | OFO-P2035-SK-223 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM BARGE TO VESSEL AT US142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
224 | 2035 | OFO-P2035-SK-224 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM BARGE DECK TO PLATFORM AT US142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
225 | 2035 | OFO-P2035-SK-225 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM PLAT FORM TO BARGE DECK AT US142 PLATFORM | 1 | A | √ | √ | 2025-07-10 | MF | @
226 | 2035 | OFO-P2035-SK-226 | TYPICAL LIFTING ARRANGEMENT OF ANCHOR BUOY BY SAPURA 1200 | 1 | A | √ | √ | 2025-07-10 | JH | @
227 | 2035 | OFO-P2035-SK-227 | LBII Access Platform During RP-1 Floatover | 1 + 10 | A,0 | √ | √ | 2025-08-01 | LEO | @
228 | 2035 | OFO-P2035-SK-228 | TYPICAL CABLE PULLING ARRANGEMENT AT HP-1 (WITHOUT TOPSIDE) | 2 | B | √ | √ | 2025-08-08 | SKT | @
229 | 2035 | OFO-P2035-SK-229 | TYPICAL CABLE PULLING ARRANGEMENT AT HP-1 (WITH TOPSIDE) | 2 | A | √ | √ | 2025-07-27 | SKT | @
230 | 2035 | OFO-P2035-SK-230 | TYPICAL CABLE PULLING ARRANGEMENT AT HP-2 (WITHOUT TOPSIDE) | 2 | A | √ | √ | 2025-08-04 | SKT | @
231 | 2035 | OFO-P2035-SK-231 | TYPICAL CABLE PULLING ARRANGEMENT AT HP-2 (WITH TOPSIDE) | 2 | A | √ | √ | 2025-07-27 | SKT | @
232 | 2035 | OFO-P2035-SK-232 | TYPICAL CABLE PULLING ARRANGEMENT AT US-142A (WITHOUT TOPSIDE) | 2 | A | √ | √ | 2025-07-27 | SKT | @
233 | 2035 | OFO-P2035-SK-233 | TYPICAL CABLE PULLING ARRANGEMENT AT US-142A (WITH TOPSIDE) | 2 | A | √ | √ | 2025-07-27 | SKT | @
234 | 2035 | OFO-P2035-SK-234 | HORIZONTAL (HBS) START-UP ARRANGEMENT 16" WF PIPELINE FROM US-12B TO USSC-RP1 (PL-2) AT RP-1 WITH SAPURA 1200 | 1 | A | √ | √ | 2025-07-17 | VDA | @
235 | 2035 | OFO-P2035-SK-235 | START-UP ARRANGEMENT FOR 16" WELL FLUID PIPELINE FROM US-159A TO US-12B (PL-1) - SAPURA 1200 | 1 | A | √ | √ | 2025-08-20 | SKS | @
236 | 2035 | OFO-P2035-SK-236 | PADEYE FOR ROV CROSSHAUL - SAPURA 1200 | 1 | B | √ | √ | 2025-09-09 | SKS | @
237 | 2035 | OFO-P2035-SK-237 | HP-1 COUNTERWEIGHT PLATFORM LIFTING ARRANGEMENT & DETAILS | 2 | A | √ | √ | 2025-09-01 | VDA | @
238 | 2035 | OFO-P2035-SK-238 | HP-2 COUNTERWEIGHT PLATFORM LIFTING ARRANGEMENT & DETAILS |  |  |  |  | 2025-07-29 | VDA
239 | 2035 | OFO-P2035-SK-239 | START-UP ARRANGEMENT FOR 16" WELL FLUID PIPELINE FROM HP-3 TO USSC-RP1 (PL-8) - SAPURA 1200 | 1 | A | √ | √ | 2025-08-01 | SKS | @
240 | 2035 | OFO-P2035-SK-240 | HP-3 COUNTERWEIGHT PLATFORM LIFTING ARRANGEMENT & DETAILS | 4 | A | √ | √ | 2025-09-15 | VDA | @
241 | 2035 | OFO-P2035-SK-241 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT (HP1, HP2 AND HP3 COUNTER WEIGHT PLATFORM) USING DLS-4200 | 1 | A | √ | √ | 2025-08-11 | AMK | @
242 | 2035 | OFO-P2035-SK-242 | SEP-750 INSTALLATION ARRANGEMENT OF GANGWAY BETWEEN US 142 AND US 142A | 1 | A | √ | √ | 2025-08-01 | MF | @
243 | 2035 | OFO-P2035-SK-243 | INSTALLATION RIGGING FOR SAND/CEMENT BAG | 1 | A | √ | √ | 2025-08-22 | HZD | @
244 | 2035 | OFO-P2035-SK-244 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR HALF-MOON BY OSV SAFEEN PEARL | 1 | A | √ | √ | 2025-08-15 | MF | @
245 | 2035 | OFO-P2035-SK-245 | PIPELINE SHIFTING SEQUENCE DURING LAYDOWN SKETCH FOR PL-5 | 7 | A | √ | √ | 2025-08-19 | LEO | @
246 | 2035 | OFO-P2035-SK-246 | TEMPORARY BOLLARD DETAILS FOR ASTRO-304 | 1 | A | √ | √ | 2025-08-19 | VDA | @
247 | 2035 | OFO-P2035-SK-247 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY AT WIP |  |  |  |  | 2025-08-21 | SHM
248 | 2035 | OFO-P2035-SK-248 | HEA TITAN LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT WIP |  |  |  |  | 2025-08-21 | SHM
249 | 2035 | OFO-P2035-SK-249 | HEA TITAN REMOVAL ARRANGEMENT OF GANGWAY AT WIP |  |  |  |  | 2025-08-21 | SHM
250 | 2035 | OFO-P2035-SK-250 | PIPELINE SHIFTING DURING LAYDOWN AT US-12B (KP3.934) FOR PROPOSED 16" WELL FLUID PIPELINE FROM US-159A TO US-12B (PL-1) | 7 | B | √ | √ | 2025-10-17 | LEO | @
251 | 2035 | OFO-P2035-SK-251 | DMA START-UP ARRANGEMENT FOR PROPOSED 18" WELL FUID SUBSEA PIPELINE FROM (PL-6) FROM HP-1 TO HP2 | 4 | G | √ | √ | 2026-01-27 | LEO | @
252 | 2035 | OFO-P2035-SK-252 | TYPICAL LIFTING ARRANGEMENT FOR TEMPORARY SUPPORT | 1 | C | √ | √ | 2025-09-26 | HZD | @
253 | 2035 | OFO-P2035-SK-253 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY FROM BARGE DECK TO PLATFORM & PLATFORM TO BARGE DECK AT WIP | 2 | B | √ | √ | 2025-10-14 | NAR | @
254 | 2035 | OFO-P2035-SK-254 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK | 2 | B | √ | √ | 2025-10-14 | NAR | @
255 | 2035 | OFO-P2035-SK-255 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & WIP PLATFORM | 2 | B | √ | √ | 2025-10-14 | NAR | @
256 | 2035 | OFO-P2035-SK-256 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF 20 FT. CONTAINER AT SUPPLY VESSEL & BARGE DECK | 2 | B | √ | √ | 2025-10-23 | NAR | @
257 | 2035 | OFO-P2035-SK-257 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF 20 FT. CONTAINER AT BARGE DECK & WIP PLATFORM | 2 | A | √ | √ | 2025-09-10 | NAR | @
258 | 2035 | OFO-P2035-SK-258 | TYPICAL LIFTING & OFFLOADING ARRANGEMENT FOR BELL MOUTH PLATE BY SAFEEN PEARL | 1 | B | √ | √ | 2025-10-06 | HZD | @
259 | 2035 | OFO-P2035-SK-259 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF SCAFFOLDING BUNDLE AT SUPPLY VESSEL & BARGE DECK | 2 | B | √ | √ | 2025-10-23 | NAR | @
260 | 2035 | OFO-P2035-SK-260 | HEA TITAN LIFTING & OFFLOADING ARRANGEMENT OF SCAFFOLDING BUNDLE AT BARGE DECK & WIP PLATFORM | 2 | A | √ | √ | 2025-09-16 | NAR | @
261 | 2035 | OFO-P2035-SK-261 | PL-2 PIPELINE DAVIT LIFT AT US-12B WITH DLB-1000 (STBD SIDE) | 1 | A | √ | √ | 2025-09-23 | VDA | @
262 | 2035 | OFO-P2035-SK-262 | STALK-ON AT RP1 FOR PL-2 WITH DLB-1000 (STBD SIDE) | 1 | A | √ | √ | 2025-09-23 | VDA | @
263 | 2035 | OFO-P2035-SK-263 | A-FRAME DETAILS (AS-BUILT) | 1 | A | √ | √ | 2025-09-18 | CDG | @'
264 | 2035 | OFO-P2035-SK-264 | MONO RAIL SUPPORT DETAILS (AS-BUILT) | 1 | A | √ | √ | 2025-09-18 | CDG | @
265 | 2035 | OFO-P2035-SK-265 | ROLLER BOX SUPPORT DETAILS (AS-BUILT) | 1 | A | √ | √ | 2025-09-18 | CDG | @
266 | 2035 | OFO-P2035-SK-266 | SEP-750 LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT USSC-RP1WEST SIDE PLATFORM | 1 | A | √ | √ | 2025-09-26 | AMK | @
267 | 2035 | OFO-P2035-SK-267 | SEP-750 REMOVAL ARRANGEMENT OF GANGWAY AT USSC-RP1WEST SIDE PLATFORM | 1 | A | √ | √ | 2025-09-26 | AMK | @
268 | 2035 | OFO-P2035-SK-268 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH FROM VESSEL TO USSC-RP1WEST SIDE PLATFORM | 1 | A | √ | √ | 2025-09-26 | AMK | @
269 | 2035 | OFO-P2035-SK-269 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH FROM BARGE TO VESSEL AT USSC-RP1WEST SIDE PLATFORM | 1 | A | √ | √ | 2025-09-26 | AMK | @
270 | 2035 | OFO-P2035-SK-270 | SEP-750 LIFTING & OFFLOADING BILLY PUGH FROM BARGE DECK TO PLATFORM AT USSC-RP1 WEST SIDE PLATFORM | 1 | A | √ | √ | 2025-09-26 | AMK | @
271 | 2035 | OFO-P2035-SK-271 | SEP-750 LIFTING & OFFLOADING BILLY PUGH FROM PLATFORM TO BARGE DECK AT USSC-RP1 WEST SIDE PLATFORM | 1 | A | √ | √ | 2025-09-26 | AMK | @
272 | 2035 | OFO-P2035-SK-272 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM VESSEL TO BARGE AT USSC-RP1 WEST SIDE PLATFORM | 1 | A | √ | √ | 2025-09-26 | AMK | @
273 | 2035 | OFO-P2035-SK-273 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE TO VESSEL AT USSC-RP1 WEST SIDE PLATFORM | 1 | A | √ | √ | 2025-09-26 | AMK | @
274 | 2035 | OFO-P2035-SK-274 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AT USSC-RP1 WEST SIDE PLATFORM | 1 | A | √ | √ | 2025-09-26 | AMK | @
275 | 2035 | OFO-P2035-SK-275 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM PLATFORM TO BARGE DECK AT USSC-RP1 WEST SIDE PLATFORM | 1 | A | √ | √ | 2025-09-26 | AMK | @
276 | 2035 | OFO-P2035-SK-276 | DMA START-UP ARRANGEMENT FOR 16" WI PIPELINE (PL-11) FROM HP-2 TO HP-1 | 4 | F | √ | √ | 2026-03-06 | LEO | @
277 | 2035 | OFO-P2035-SK-277 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR 20FT CONTAINER FROM VESSEL TO BARGE AT USSC-RP1 PLATFORM |  |  |  |  | 2025-09-26 | AMK
278 | 2035 | OFO-P2035-SK-278 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR 20FT CONTAINER FROM BARGE TO VESSEL AT USSC-RP1 PLATFORM |  |  |  |  | 2025-09-26 | AMK
279 | 2035 | OFO-P2035-SK-279 | STALK-ON AT RP-1 FOR PL-3 WITH SAFEEN-3000 (PORT SIDE) | 1 | B | √ | √ | 2025-10-23 | LE0 | @
280 | 2035 | OFO-P2035-SK-280 | PL3 PIPELINE DAVIT LIFT AT US-142A WITH SAFEEN 3000 (PORT SIDE) | 1 | B | √ | √ | 2025-10-28 | SKS | @
281 | 2035 | OFO-P2035-SK-281 | STALK-ON AT RP-1 FOR PL-5 WITH SAFEEN-3000 (PORT SIDE) | 1 | A | √ | √ | 2025-10-21 | SKS | @
282 | 2035 | OFO-P2035-SK-282 | H&G - SAFEEN 3000 DECK LAYOUT DURING STALK ON RISER INSTALLATION | 2 | A | √ | √ | 2025-11-11 | CDG | @
283 | 2035 | OFO-P2035-SK-283 | STALK-ON AT RP-1 FOR PL-7 WITH SAFEEN-3000 (PORT SIDE) | 1 | A | √ | √ | 2025-11-04 | CDG | @
284 | 2035 | OFO-P2035-SK-284 | RISER TOP PLATE & PADEYE DETAILS FOR 16" RISER | 1 + 4 | B,1 | √ | √ | 2025-12-03 | HZD | @
285 | 2035 | OFO-P2035-SK-285 | RISER TOP PLATE & PADEYE DETAILS FOR 18" RISER | 1 + 4 | B,1 | √ | √ | 2025-12-03 | HZD | @
286 | 2035 | OFO-P2035-SK-286 | AWTI PLATFORM, ROV CONTROL SEAFASTENING AND MOORING GUARD DETAIL AT SAFEEN 3000 | 1 | A | √ | √ | 2025-11-11 | CDG | @
287 | 2035 | OFO-P2035-SK-287 | STALK-ON AT RP-1 FOR PL8 WITH SAFEEN-3000 (PORT SIDE) | 1 | C | √ | √ | 2026-03-17 | LEO | @
288 | 2035 | OFO-P2035-SK-288 | STALK-ON AT RP-1 FOR PL2 WITH SAFEEN-3000 (PORT SIDE) | 1 | B | √ | √ | 2025-12-22 | LEO | @
289 | 2035 | OFO-P2035-SK-289 | PL-2 PIPELINE DAVIT LIFT AT US-12B WITH SAFEEN-3000 (PORT SIDE) | 1 | B | √ | √ | 2025-12-22 | LEO | @
290 | 2035 | OFO-P2035-SK-290 | GAUGE PLATE DETAILS | 1 | C | √ | √ | 2026-05-21 | LEO | @
291 | 2035 | OFO-P2035-SK-291 | TYPICAL LIFTING AND INSTALLATION OF REELS BY SAFEEN 3000 | 1 | C | √ | √ | 2026-04-03 | MF | @
292 | 2035 | OFO-P2035-SK-292 | LIFTING ARRANGEMENT OF DIVING MATERIAL BASKET BY SAFEEN-3000 | 2 | B | √ | √ | 2025-11-27 | NAR | @
293 | 2035 | OFO-P2035-SK-293 | LIFTING ARRANGEMENT OF SAND / CEMENT BAGS USING JUMBO BAG BY SAFEEN-3000 | 1 | B | √ | √ | 2025-11-27 | NAR | @
294 | 2035 | OFO-P2035-SK-294 | LIFTING ARRANGEMENT OF SAND / CEMENT BAGS USING CARGO NET BAG BY SAFEEN-3000 | 2 | B | √ | √ | 2025-11-28 | NAR | @
295 | 2035 | OFO-P2035-SK-295 | 14 INCHES NON RATED SPADE | 1 | A | √ | √ | 2025-11-20 | LEO | @
296 | 2035 | OFO-P2035-SK-296 | LIFTING ARRANGEMENT OF DIVING BASKET FOR GOLDEN GATE DEPLOYMENT BY SAFEEN-3000 | 2 | C | √ | √ | 2025-12-30 | NAR | @
297 | 2035 | OFO-P2035-SK-297 | SEP-750 LIFTING & OFFLOADING BILLY PUGH BETWEEN BARGE DECK AT USSC-RP1 WEST SIDE AND SUPPLY VESSEL AT PORTSIDE USING SEA TRAX CRANE |  |  |  |  | 2025-11-24 | MF |  | NO FEED BACK
298 | 2035 | OFO-P2035-SK-298 | SEP-750 LIFTING & OFFLOADING PROJECT MATERIAL BETWEEN BARGE DECK AT USSC-RP1 WEST SIDE AND SUPPLY VESSEL AT STARBOARD SIDE USING SEA TRAX CRANE |  |  |  |  | 2025-11-24 | MF |  | NO FEED BACK
299 | 2035 | OFO-P2035-SK-299 | SEP-750 LIFTING & OFFLOADING BILLY PUGH BETWEEN BARGE DECK AT USSC-RP1 WEST SIDE AND SUPPLY VESSEL AT STARBOARD USING SEA TRAX CRANE |  |  |  |  | 2025-11-25 | MF |  | NO FEED BACK
300 | 2035 | OFO-P2035-SK-300 | SEP-750 LIFTING & OFFLOADING PROJECT MATERIAL BETWEEN BARGE DECK AT USSC-RP1 WEST SIDE AND SUPPLY VESSEL AT PORTSIDE USING SEA TRAX CRANE |  |  |  |  | 2025-11-25 | MF |  | NO FEED BACK
301 | 2035 | OFO-P2035-SK-301 | RECOVERY ARRANGEMENT OF START-UP / LAYDOWN HEAD BY SAFEEN-3000 | 2 | B | √ | √ | 2025-11-29 | NAR | @
302 | 2035 | OFO-P2035-SK-302 | RECOVERY ARRANGEMENT OF KNEE BARCE BY SAFEEN-3000 | 2 | A | √ | √ | 2025-11-27 | NAR | @
303 | 2035 | OFO-P2035-SK-303 | LIFTING ARRANGEMENT OF WIRE ROPE BY SAFEEN-3000 | 2 | A | √ | √ | 2025-12-05 | NAR | @
304 | 2035 | OFO-P2035-SK-304 | LIFTING ARRANGEMENT OF AIRLIFT PIPE BY SAFEEN-3000 | 1 | A | √ | √ | 2025-12-03 | NAR | @
305 | 2035 | OFO-P2035-SK-305 | PL-8 PIPELINE DAVIT LIFT AT HP-3 WITH SAFEEN-3000 (PORT SIDE) | 1 | A | √ | √ | 2025-11-26 | SKS | @
306 | 2035 | OFO-P2035-SK-306 | SEP-750 LIFTING & OFFLOADING CCU BETWEEN BARGE DECK AT USSC-RP1 WEST SIDE AND SUPPLY VESSEL AT STARBOARD SIDE USING SEA TRAX CRANE |  |  |  |  | 2025-11-26 | MF |  | NO FEED BACK
307 | 2035 | OFO-P2035-SK-307 | SEP-750 LIFTING & OFFLOADING CCU BETWEEN BARGE DECK AT USSC-RP1 WEST SIDE AND SUPPLY VESSEL AT PORTSIDE USING SEA TRAX CRANE |  |  |  |  | 2025-11-26 | MF |  | NO FEED BACK
308 | 2035 | OFO-P2035-SK-308 | SEP-750 LIFTING & OFFLOADING CCU BETWEEN SUPPLY VESSEL AND USSC-RP1 PLATFORM AT STARBOARD SIDE USING SEA TRAX CRANE |  |  |  |  | 2025-11-27 | MF |  | NO FEED BACK
309 | 2035 | OFO-P2035-SK-309 | SEP-750 LIFTING & OFFLOADING CCU BETWEEN SUPPLY VESSEL AND USSC-RP1 PLATFORM AT PORTSIDE USING SEA TRAX CRANE |  |  |  |  | 2025-11-27 | MF |  | NO FEED BACK
310 | 2035 | OFO-P2035-SK-310 | SEP-750 LIFTING & OFFLOADING PROJECT MATERIAL BETWEEN SUPPLY VESSEL AND USSC-RP1 PLATFORM AT STARBOARD SIDE USING SEA TRAX CRANE |  |  |  |  | 2025-11-27 | MF |  | NO FEED BACK
311 | 2035 | OFO-P2035-SK-311 | SEP-750 LIFTING & OFFLOADING PROJECT MATERIAL BETWEEN SUPPLY VESSEL AND USSC-RP1 PLATFORM AT PORTSIDE USING SEA TRAX CRANE |  |  |  |  | 2025-11-27 | MF |  | NO FEED BACK
312 | 2035 | OFO-P2035-SK-312 | RECOVERY ARRANGEMENT OF KNEE BRACE CLAMP BY SAFEEN-3000 | 2 | A | √ | √ | 2025-12-03 | NAR | @
313 | 2035 | OFO-P2035-SK-313 | RECOVERY ARRANGEMENT OF 16’’ BLIND FLANGE BY SAFEEN-3000 | 2 | A | √ | √ | 2025-12-04 | NAR | @
314 | 2035 | OFO-P2035-SK-314 | RECOVERY ARRANGEMENT OF 18’’ BLIND FLANGE BY SAFEEN-3000 | 2 | A | √ | √ | 2025-12-04 | NAR | @
315 | 2035 | OFO-P2035-SK-315 | LIFTING ARRANGEMENT OF SAND / CEMENT BAGS USING JUMBO BAG BY HEA OCEANIC | 1 | A | √ | √ | 2025-12-18 | MF | @
316 | 2035 | OFO-P2035-SK-316 | LIFTING ARRANGEMENT OF SAND / CEMENT BAGS USING CARGO NET BAG BY HEA OCEANIC | 1 | A | √ | √ | 2025-12-18 | MF | @
317 | 2035 | OFO-P2035-SK-317 | LIFTING ARRANGEMENT OF DIVING MATERIAL BASKET BY HEA OCEANIC | 1 | A | √ | √ | 2025-12-24 | MF | @
318 | 2035 | OFO-P2035-SK-318 | RECOVERY ARRANGEMENT OF START-UP / LAYDOWN HEAD BY HEA OCEANIC | 1 | A | √ | √ | 2025-12-24 | MF | @
319 | 2035 | OFO-P2035-SK-319 | LIFTING ARRANGEMENT OF DIVING BASKET FOR GOLDEN GATE DEPLOYMENT BY HEA OCEANIC | 1 | A | √ | √ | 2025-12-24 | MF | @
320 | 2035 | OFO-P2035-SK-320 | LIFTING ARRANGEMENT OF AIRLIFT PIPE BY HEA OCEANIC | 1 | B | √ | √ | 2026-01-31 | BAJ | @
321 | 2035 | OFO-P2035-SK-321 | RECOVERY ARRANGEMENT OF 16'' BLIND FLANGE BY HEA OCEANIC |  |  |  |  | 2025-12-17 | MF
322 | 2035 | OFO-P2035-SK-322 | LIFTING ARRANGEMENT OF 18'' BLIND FLANGE BY HEA OCEANIC | 1 | A | √ | √ | 2025-12-26 | MF | @
323 | 2035 | OFO-P2035-SK-323 | LIFTING ARRANGEMENT OF WIRE ROPE BY HEA OCEANIC | 1 | A | √ | √ | 2025-12-25 | MF | @
324 | 2035 | OFO-P2035-SK-324 | LIFTING ARRANGEMENT OF A FRAME (AF-04-14) (AF-04-15) BY HEA OCEANIC | 1 | A | √ | √ | 2025-12-26 | MF | @
325 | 2035 | OFO-P2035-SK-325 | LIFTING ARRANGEMENT OF A FRAME (AF-01) BY HEA OCEANIC | 1 | B | √ | √ | 2026-01-05 | NAR | @
326 | 2035 | OFO-P2035-SK-326 | LIFTING ARRANGEMENT OF A FRAME (AF-2004-15) BY HEA OCEANIC |  |  |  |  | 2025-12-17 | MF
327 | 2035 | OFO-P2035-SK-327 | MATTRESSES & GROUTING EQUIPMENT SET-UP LAYOUT ON HEA OCEAN | 1 | B | √ | √ | 2026-02-07 | MF | @
328 | 2035 | OFO-P2035-SK-328 | LIFTING ARRANGEMENT OF EMPTY GROUT BAGS BY HEA OCEANIC | C | A | √ | √ | 2025-12-23 | MF | @
329 | 2035 | OFO-P2035-SK-329 | LIFTING ARRANGEMENT OF FLANGE SHROUD BY HEA OCEANIC | 1 | B | √ | √ | 2026-01-05 | NAR | @
330 | 2035 | OFO-P2035-SK-330 | LIFTING ARRANGEMENT OF 2IN TIE IN SPOOL BY HEA OCEANIC | 1 | C | √ | √ | 2026-01-15 | MF | @
331 | 2035 | OFO-P2035-SK-331 | REMOVAL ARRANGEMENT OF BST-S13 BUMPERS BY SAFEEN-3000 | 2 | B | √ | √ | 2025-12-26 | AMT | @
332 | 2035 | OFO-P2035-SK-332 | RECOVERY ARRANGEMENT OF KNEE BARCE WITH CLAMP BY SAFEEN-3000 | 2 | A | √ | √ | 2026-01-01 | NAR | @
333 | 2035 | OFO-P2035-SK-333 | HORIZONTAL (HBS) START-UP ARRANGEMENT FOR 16" WATER INJECTION PIPELINE FROM HP-3 TO USSC-RP1 (PL-9) BY SAFEEN 3000 | 1 | A | √ | √ | 2026-01-02 | BJ | @
334 | 2035 | OFO-P2035-SK-334 | LIFTING ARRANGEMENT FOR TRANSFERRING RISER SPOOLS FROM WEST TO EAST SIDE OF RP-1 BY SAFEEN-3000 | 3 | A | √ | √ | 2026-01-07 | AMT | @
335 | 2035 | OFO-P2035-SK-335 | ROV CROSS HAULING -FROM BARGE STERN OPTION-2 |  |  |  |  | 2026-01-29 | AMT
336 | 2035 | OFO-P2035-SK-336 | TYPICAL LIFTING ARRANGEMENT FOR TEMPORARY SUPPORT DURING INSTALLATION AND REMOVAL | 4 | B | √ | √ | 2026-02-11 | HZD | @
337 | 2035 | OFO-P2035-SK-337 | PIPELINE SHIFTING DURING LAYDOWN AT US-153A (KP 3.540) FOR PROPOSED 16” WF SUBSEA PIPELINE FROM US-19B TO US-153A (PL-4) | 4 | B | √ | √ | 2026-02-23 | SSK | @
338 | 2035 | OFO-P2035-SK-338 | LAYDOWN HEAD DETAIL FOR 16” PIPELINE (FLANGE TYPE) | 1 | A | √ | √ | 2026-02-05 | AMT | @
339 | 2035 | OFO-P2035-SK-339 | PL-08 PIPELINE DAVIT LIFTING AT HP-03 PLATFORM WITH DLB-1000 (PORT SIDE) | 2 | B | √ | √ | 2026-02-23 | SSK | @
340 | 2035 | OFO-P2035-SK-340 | PL-09 PIPELINE DAVIT LIFTING AND SHIFTING AT HP-03 PLATFORM WITH DLB-1000 (PORT SIDE) | 2 | D | √ | √ | 2026-07-21 | LEO | @
341 | 2035 | OFO-P2035-SK-341 | PL-8 Pipeline Davit Lift Arrangement Sketch at USSC RP-1 | 1 | B | √ | √ | 2026-02-27 | LEO | @
342 | 2035 | OFO-P2035-SK-342 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT SUPPLY VESSEL & BARGE DECK (US-159) | 2 | A | √ | √ | 2026-02-16 | NAR | @
343 | 2035 | OFO-P2035-SK-343 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT OF BILLY PUGH AT BARGE DECK & US-159 PLATFORM | 2 | A | √ | √ | 2026-02-16 | NAR | @
344 | 2035 | OFO-P2035-SK-344 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT SUPPLY VESSEL & BARGE DECK (US-159) | 2 | A | √ | √ | 2026-02-18 | NAR | @
345 | 2035 | OFO-P2035-SK-345 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT OF GANGWAY AT BARGE DECK & US-159 PLATFORM | 2 | A | √ | √ | 2026-02-19 | NAR | @
346 | 2035 | OFO-P2035-SK-346 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & BARGE DECK (US-159) | 2 | A | √ | √ | 2026-02-17 | NAR | @
347 | 2035 | OFO-P2035-SK-347 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT BARGE DECK & US-159 PLATFORM | 2 | A | √ | √ | 2026-02-17 | NAR | @
348 | 2035 | OFO-P2035-SK-348 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT SUPPLY VESSEL & BARGE DECK (US-159) | 2 | A | √ | √ | 2026-02-17 | NAR | @
349 | 2035 | OFO-P2035-SK-349 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT OF 20FT CONTAINER AT BARGE DECK & US-159 PLATFORM | 2 | A | √ | √ | 2026-02-17 | NAR | @
350 | 2035 | OFO-P2035-SK-350 | RECOVERY ARRANGEMENT OF KNEE BRACE WITH CLAMP BY HEA OCEANIC | 1 | A | √ | √ | 2026-02-14 | HZD | @
351 | 2035 | OFO-P2035-SK-351 | RECOVERY ARRANGEMENT OF TEMPORARY SHROUD BY HEA OCEANIC | 1 | A | √ | √ | 2026-02-14 | HZD | @
352 | 2035 | OFO-P2035-SK-352 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY FROM VESSL TO BARGE AT US 153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
353 | 2035 | OFO-P2035-SK-353 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY FROM BARGE TO VESSEL AT US 153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
354 | 2035 | OFO-P2035-SK-354 | SEP-750 LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT US 153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
355 | 2035 | OFO-P2035-SK-355 | SEP-750 REMOVAL ARRANGEMENT OF GANGWAY AT US 153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
356 | 2035 | OFO-P2035-SK-356 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH FROM VESSEL TO BARGE AT US153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
357 | 2035 | OFO-P2035-SK-357 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH FROM BARGE TO VESSEL AT US153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
358 | 2035 | OFO-P2035-SK-358 | SEP-750 LIFTING & OFFLOADING BILLY PUGH FROM BARGE DECK TO PLATFORM AT US 153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
359 | 2035 | OFO-P2035-SK-359 | SEP-750 LIFTING & OFFLOADING BILLY PUGH FROM PLATFORM TO BARGE DECK AT US 153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
360 | 2035 | OFO-P2035-SK-360 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM VESSEL TO BARGE AT US153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
361 | 2035 | OFO-P2035-SK-361 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE TO VESSEL AT US153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @'
362 | 2035 | OFO-P2035-SK-362 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AT US153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
363 | 2035 | OFO-P2035-SK-363 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM PLAT FORM TO BARGE DECK AT US153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
364 | 2035 | OFO-P2035-SK-364 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM VESSEL TO BARGE AT US-153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
365 | 2035 | OFO-P2035-SK-365 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM BARGE TO VESSEL AT US-153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @'
366 | 2035 | OFO-P2035-SK-366 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM BARGE DECK TO PLATFORM AT US-153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
367 | 2035 | OFO-P2035-SK-367 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR 20 FT. CONTAINER FROM PLAT FORM TO BARGE DECK AT US-153 PLATFORM | 1 | A | √ | √ | 2026-02-24 | SRV | @
368 | 2035 | OFO-P2035-SK-368 | TYPICAL LIFTING AND INSTALLATION OF REELS BY SAFEEN-3000 FROM MUTAWA-401 | 1 | A | √ | √ | 2026-02-27 | BINOY | @
369 | 2035 | OFO-P2035-SK-369 | TYPICAL LIFTING AND INSTALLATION OF REELS BY SAPURA-1200 FROM MUTAWA-401 | 1 | A | √ | √ | 2026-02-27 | BINOY | @
370 | 2035 | OFO-P2035-SK-370 | STALK -ON AT RP-1 FOR PL-2 WITH DLB-1000 (PORT SIDE) | 1 | B | √ | √ | 2026-03-11 | SSK | @
371 | 2035 | OFO-P2035-SK-371 | PL-2 PIPELINE DAVIT LIFT AT US-12B WITH DLB-1000 (PORT SIDE) | 1 | A | √ | √ | 2026-03-04 | LEO | @
372 | 2035 | OFO-P2035-SK-372 | Deployment & Recovery Arrangement of 75MT Gravity Anchor by DLB-1000 | 1 | A | √ | √ | 2026-03-12 | Ameeer | @
373 | 2035 | OFO-P2035-SK-373 | Recovery Arrangement of Knee Brace by DLB-1000 | 1 | A | √ | √ | 2026-03-10 | Ameeer | @
374 | 2035 | OFO-P2035-SK-374 | Lifting Arrangement of Sand/ Cement Bags using Jumbo Bag by DLB-1000 | 1 | A | √ | √ | 2026-03-09 | Ameeer | @
375 | 2035 | OFO-P2035-SK-375 | Lifting Arrangement of Diving Material Basket by DLB-1000 | 1 | A | √ | √ | 2026-03-10 | Ameeer | @
376 | 2035 | OFO-P2035-SK-376 | Lifting Arrangement of Sand/ Cement Bags using Cargo Net Bag by DLB-1000 | 1 | A | √ | √ | 2026-03-10 | Ameeer | @
377 | 2035 | OFO-P2035-SK-377 | Recovery Arrangement of Start-up/Laydown Head by DLB-1000 | 1 | A | √ | √ | 2026-03-12 | Ameeer | @
378 | 2035 | OFO-P2035-SK-378 | Lifting Arrangement of Airlift Pipe by DLB-1000 | 1 | A | √ | √ | 2026-03-10 | Ameeer | @
379 | 2035 | OFO-P2035-SK-379 | Recovery Arrangement of Knee Brace Clamps by DLB-1000 | 1 | A | √ | √ | 2026-03-12 | Ameeer | @
380 | 2035 | OFO-P2035-SK-380 | Recovery Arrangement of 18in Blind Flange by DLB-1000 | 1 | A | √ | √ | 2026-03-12 | Ameeer | @
381 | 2035 | OFO-P2035-SK-381 | Lifting Arrangement of Wire Rope by DLB-1000 | 1 | A | √ | √ | 2026-03-12 | Ameeer | @
382 | 2035 | OFO-P2035-SK-382 | Lifting Arrangement of A-Frame (AF-01) | 1 | A | √ | √ | 2026-03-12 | Ameeer | @
383 | 2035 | OFO-P2035-SK-383 | Lifting Arrangement of A-Frame (AF-04-14) / (AF-2004-15) | 1 | A | √ | √ | 2026-03-12 | Ameeer | @
384 | 2035 | OFO-P2035-SK-384 | DIXIE PATRIOT LIFTING & INSTALLATION ARRANGEMENT OF GANGWAY AT USSC-RP1WEST SIDE PLATFORM |  |  |  |  | 2026-03-09 | SRV
385 | 2035 | OFO-P2035-SK-385 | DIXIE PATRIOT REMOVAL ARRANGEMENT OF GANGWAY AT USSC-RP1WEST SIDE PLATFORM |  |  |  |  | 2026-03-09 | SRV
386 | 2035 | OFO-P2035-SK-386 | DIXIE PATRIOT LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH FROM VESSEL TO USSC-RP1WEST SIDE PLATFORM |  |  |  |  | 2026-03-09 | SRV
387 | 2035 | OFO-P2035-SK-387 | DIXIE PATRIOT LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH FROM BARGE TO VESSEL AT USSC-RP1WEST SIDE PLATFORM |  |  |  |  | 2026-03-09 | SRV
388 | 2035 | OFO-P2035-SK-388 | DIXIE PATRIOT LIFTING & OFFLOADING BILLY PUGH FROM BARGE DECK TO PLATFORM AT USSC-RP1 WEST SIDE PLATFORM |  |  |  |  | 2026-03-09 | SRV
389 | 2035 | OFO-P2035-SK-389 | DIXIE PATRIOT LIFTING & OFFLOADING BILLY PUGH FROM PLATFORM TO BARGE DECK AT USSC-RP1 WEST SIDE PLATFORM |  |  |  |  | 2026-03-09 | SRV
390 | 2035 | OFO-P2035-SK-390 | DIXIE PATRIOT LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM VESSEL TO BARGE AT USSC-RP1 WEST SIDE PLATFORM |  |  |  |  | 2026-03-09 | SRV
391 | 2035 | OFO-P2035-SK-391 | DIXIE PATRIOT LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE TO VESSEL AT USSC-RP1 WEST SIDE PLATFORM |  |  |  |  | 2026-03-09 | SRV
392 | 2035 | OFO-P2035-SK-392 | DIXIE PATRIOT LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM BARGE DECK TO PLATFORM AT USSC-RP1 WEST SIDE PLATFORM |  |  |  |  | 2026-03-09 | SRV
393 | 2035 | OFO-P2035-SK-393 | DIXIE PATRIOT LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL FROM PLATFORM TO BARGE DECK AT USSC-RP1 WEST SIDE PLATFORM |  |  |  |  | 2026-03-09 | SRV
394 | 2035 | OFO-P2035-SK-394 | DIXIE PATRIOT LIFTING & OFFLOADING ARRANGEMENT FOR 20FT CONTAINER FROM VESSEL TO BARGE AT USSC-RP1 PLATFORM |  |  |  |  | 2026-03-09 | SRV
395 | 2035 | OFO-P2035-SK-395 | DIXIE PATRIOT LIFTING & OFFLOADING ARRANGEMENT FOR 20FT CONTAINER FROM BARGE TO VESSEL AT USSC-RP1 PLATFORM |  |  |  |  | 2026-03-09 | SRV
396 | 2035 | OFO-P2035-SK-396 | DMA Start-Up Arrangement Sketch for PL-11 by SAFEEN 3000 |  |  |  |  | 2026-03-13 | LEO
397 | 2035 | OFO-P2035-SK-397 | US LTDP-1 Project] Pipelay Profile with Stinger - DLS 4200 (for PL-1) | 1 | A | √ | √ | 2026-03-26 | LEO | @
398 | 2035 | OFO-P2035-SK-398 | A-FRAME | 1 | C | √ | √ | 2026-06-30 | SC | @
399 | 2035 | OFO-P2035-SK-399 | DLB-1000 DECK LAYOUT FOR STALK ON RISER AND SPOOLS INSTALLATION | 1 | A | √ | √ | 2026-05-14 | JF | @
400 | 2035 | OFO-P2035-SK-400 | TYPICAL ABANDONMENT AND RECOVERY / LAYDOWN ARRANGEMENT WITH DLS-4200 | 1 | A | √ | √ | 2026-04-03 | SSK | @
401 | 2035 | OFO-P2035-SK-401 | (SEP-650) LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND VESSEL AT (RP1) PLATFORM |  |  |  |  | 2026-04-06 | MF
402 | 2035 | OFO-P2035-SK-402 | (SEP-650) LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT (RP1) PLATFORM |  |  |  |  | 2026-04-06 | MF
403 | 2035 | OFO-P2035-SK-403 | (SEP-650) LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND VESSEL AT (RP1) PLATFORM | 2 | A | √ | √ | 2026-04-09 | MF | @
404 | 2035 | OFO-P2035-SK-404 | (SEP-650) LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT (RP1) PLATFORM | 2 | A | √ | √ | 2026-04-09 | MF | @
405 | 2035 | OFO-P2035-SK-405 | (SEP-650) LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND VESSEL AT (RP1) PLATFORM | 2 | A | √ | √ | 2026-04-09 | MF | @
406 | 2035 | OFO-P2035-SK-406 | (SEP-650) LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND PLATFORM AT (RP1) PLATFORM | 2 | A | √ | √ | 2026-04-09 | MF | @
407 | 2035 | OFO-P2035-SK-407 | (SEP-650) LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND VESSEL AT (RP1) PLATFORM | 2 | A | √ | √ | 2026-04-09 | MF | @
408 | 2035 | OFO-P2035-SK-408 | (SEP-650) LIFTING & OFFLOADING ARRANGEMENT FOR CCU CARGO CONTAINER BETWEEN BARGE AND PLATFORM AT (RP1) PLATFORM | 2 | A | √ | √ | 2026-04-09 | MF | @
409 | 2035 | OFO-P2035-SK-409 | STROP ARRANGEMENT FOR PL-7 DAVIT LIFT @ USSC RP-1 WITH DLB 1000 | 1 | A | √ | √ | 2026-04-06 | leo
410 | 2035 | OFO-P2035-SK-410 | DECK LAYOUT FOR MUTAWA-17 DURING PRE-COMMISSIONING SCOPE | 1 | A | √ | √ | 2026-04-24 | SKS | @
411 | 2035 | OFO-P2035-SK-411 | MUTAWA-401 LIFTING & OFFLOADING ARRANGEMENT OF PROJECT MATERIAL AT SUPPLY VESSEL & PLATFORM (US-159A) | 2 | A | √ | √ | 2026-04-21 | NAR | @
412 | 2035 | OFO-P2035-SK-412 | MUTAWA-401 LIFTING & OFFLOADING ARRANGEMENT OF E&I JUNCTION BOX AT SUPPLY VESSEL & PLATFORM (US-159A) | 2 | A | √ | √ | 2026-04-21 | NAR | @
413 | 2035 | OFO-P2035-SK-413 | TYPICAL ABANDONMENT AND RECOVERY / LAYDOWN ARRANGEMENT WITH DLB-750 | 1 | A | √ | √ | 2026-05-04 | JF | @
414 | 2035 | OFO-P2035-SK-414 | DLB-750 PIPELAY PROFILE | 1 | B | √ | √ | 2026-05-14 | LEO | @
415 | 2035 | OFO-P2035-SK-415 | 16” START-UP HEAD LIFTING AND LOWERING WITH HEA OCEANIC (PL-8) | 3 | B | √ | √ | 2026-05-06 | JF | @
416 | 2035 | OFO-P2035-SK-416 | START-UP ARRANGEMENT FOR 16” WELL FLUID PIPELINE FROM US-159A TO US-12B (PL-1) BY DLB-750 | 1 | A | √ | √ | 2026-05-05 | JF | @
417 | 2035 | OFO-P2035-SK-417 | Pipeline Shifting Sequence during Laydown Sketch for PL-1 with DLB-750 | 6 | B | √ | √ | 2026-05-14 | LEO | @
418 | 2035 | OFO-P2035-SK-418 | USLTDP-1 2035 - As-Laid Drawing Request – L-Frame Davit for ROV Deployment (DLB-1000) | 2 | A | √ | √ | 2026-05-15 | SC |  | SERVER ONLY
419 | 2035 | OFO-P2035-SK-419 | Lifting Temporary Pig Launcher & Receiver by MUTAWA 17 at US-159A WHT | 2 | A | √ | √ | 2026-05-21 | CDG | @
420 | 2035 | OFO-P2035-SK-420 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND VESSEL AT (US-19A) PLATFORM | 2 | A | √ | √ | 2026-05-18 | MF | @ | SERVER ONLY
421 | 2035 | OFO-P2035-SK-421 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY BETWEEN BARGE AND PLATFORM AT (US-19A ) PLATFORM | 2 | A | √ | √ | 2026-05-18 | MF | @ | SERVER ONLY
422 | 2035 | OFO-P2035-SK-422 | Lifting Temporary Pig Launcher & Receiver by MUTAWA 17 at HP1 | 2 | A | √ | √ | 2026-05-21 | CDG | @
423 | 2035 | OFO-P2035-SK-423 | Lifting Temporary Pig Launcher & Receiver by MUTAWA 17 at RP1 | 1 | A | √ | √ | 2026-05-21 | CDG | @
424 | 2035 | OFO-P2035-SK-424 | Lifting Arrangement of Flange Shroud by DLB-1000 | 1 | A | √ | √ | 2026-05-21 | SSK | @
425 | 2035 | OFO-P2035-SK-425 | Recovery Arrangement of Temporary Shroud by DLB-1000 | 1 | A | √ | √ | 2026-05-21 | SSK | @
426 | 2035 | OFO-P2035-SK-426 | PIPELINE SHIFTING DURING LAYDOWN AT US-153A (KP 3.540) FOR PROPOSED 16” WF SUBSEA PIPELINE FROM US-19B TO US-153A (PL-4) WITH DLB-750 | 6 | A | √ | √ | 2026-06-05 | LEO | @
427 | 2035 | OFO-P2035-SK-427 | SPARE |  |  |  |  | 2026-06-16 | MIM
428 | 2035 | OFO-P2035-SK-428 | DECK LAYOUT FOR DLB-750 DURING PIGGYBACK PIPELAY INSTALLATION | 1 | A | √ | √ | 2026-07-13 | MF | @
429 | 2035 | OFO-P2035-SK-429 | DMA Start-Up Arrangement for Proposed (PL-4) 16” Well Fluid PL. from US-19B to US-153A by DLB-750 | 1 | A | √ | √ | 2026-05-19 | SSK | @
430 | 2035 | OFO-P2035-SK-430 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY (19M LG.) BETWEEN BARGE AND VESSEL AT (US-19A) PLATFORM | 2 | A | √ | √ | 2026-05-26 | CDG | @
431 | 2035 | OFO-P2035-SK-431 | SEP-750 LIFTING & OFFLOADING ARRANGEMENT FOR GANGWAY (19M LG.) BETWEEN BARGE AND PLATFORM AT (US-19A ) PLATFORM | 2 | A | √ | √ | 2026-05-26 | CDG | @
432 | 2035 | OFO-P2035-SK-432 | AIR BAG ARRANGEMENT FOR LIFTING OF 16” WF PIPELINE FROM US-HP3 TO USSC-RP1 (PL-8) AT KP 0.908 | 1 | A | √ | √ | 2026-06-23 | SSK | @
433 | 2035 | OFO-P2035-SK-433 | AIR BAG ARRANGEMENT FOR LIFTING OF 16” WF PIPELINE FROM US-HP3 TO USSC-RP1 (PL-8) AT KP 1.583 | 1 | A | √ | √ | 2026-06-23 | SSK | @
434 | 2035 | OFO-P2035-SK-434 | DMA START-UP ARRANGEMENT FOR PL-11 AT US-HP2 BY SAFEEN 3000 | 1 | C | √ | √ | 2026-07-28 | SSK | @
435 | 2035 | OFO-P2035-SK-435 | Typical Lifting and Handling for Pipe Joints by DLB-750 | 1 | A | √ | √ | 2026-07-09 | MF | @
436 | 2035 | OFO-P2035-SK-436 | Typical Lifting and Installation of Reels by DLB-750 | 1 | A | √ | √ | 2026-07-10 | MF | @
437 | 2035 | OFO-P2035-SK-437 | Deployment & Recovery Arrangement of 75MT Gravity Anchor by DLB-750 | 1 | A | √ | √ | 2026-07-09 | MF | @
438 | 2035 | OFO-P2035-SK-438 | Recovery Arrangement of Temporary Shroud by DLB-750 | 1 | A | √ | √ | 2026-07-09 | MF | @
439 | 2035 | OFO-P2035-SK-439 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND STARBOARD SIDE VESSEL AT (HP-3) PLATFORM | 2 | A | √ | √ | 2026-06-25 | MF | ;@
440 | 2035 | OFO-P2035-SK-440 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT FOR BILLY PUGH BETWEEN BARGE AND PLATFORM AT (HP-3) PLATFORM | 2 | A | √ | √ | 2026-06-25 | MF | ;@
441 | 2035 | OFO-P2035-SK-441 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIAL BETWEEN BARGE AND STARBOARD SIDE VESSEL AT (HP-3) PLATFORM | 2 | A | √ | √ | 2026-06-25 | MF | ;@
442 | 2035 | OFO-P2035-SK-442 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT FOR PROJECT MATERIALBETWEEN BARGE AND PLATFORM AT (HP-3) PLATFORM | 2 | A | √ | √ | 2026-06-25 | MF | ;@
443 | 2035 | OFO-P2035-SK-443 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT FOR 20FT CONTAINER BETWEEN BARGE AND STARBOARD SIDE VESSEL AT (HP-3) PLATFORM | 2 | A | √ | √ | 2026-06-25 | MF | ;@
444 | 2035 | OFO-P2035-SK-444 | QMS SUBHIYA LIFTING & OFFLOADING ARRANGEMENT FOR 20FT CONTAINER BETWEEN BARGE AND PLATFORM AT (HP-3) PLATFORM | 2 | A | √ | √ | 2026-06-25 | MF | ;@
445 | 2035 | OFO-P2035-SK-445 | Lifting Temporary Pig Launcher & Receiver by DLB-1000 at USSC-RP1 | 2 | B | √ | √ | 2026-07-30 | HZD | @
446 | 2035 | OFO-P2035-SK-446 | TYPICAL LIFTING ARRANGMENT OF A - FRAME BY DELMA 1000 | 1 | B | √ | √ | 2026-09-04 | HZD | @
447 | 2035 | OFO-P2035-SK-447 | LIFTING THREE-PHASE TRANSFORMER BY SAFEEN-3000 AT HP-3 | 2 | A | √ | √ | 2026-07-06 | Ameeer | @
448 | 2035 | OFO-P2035-SK-448 | PIPELINE SHIFTING DURING LAYDOWN AT US-12B (KP 6.600) FOR PROPOSED 16” WATER INJECTION PIPELINE FROM US-HP2 TO US-HP1 (PL-11) WITH SAFEEN 3000 | 5 | A | √ | √ | 2026-08-03 | AAV | @
449 | 2035 | OFO-P2035-SK-449 | TYPICAL LIFTING ARRANGEMENT FOR TEMPORARY SUPPORT DURING INSTALLATION AND REMOVAL (USING DLB-1000) | 5 | A | √ | √ | 2026-07-16 | Ameeer | @
450 | 2035 | OFO-P2035-SK-450 | LIFTING ARRANGEMENT FOR ALUMINUM GANGWAY BY MUTAWA 17 AT US-159A WHT | 1 | A | √ | √ | 2026-07-21 | SIVA | @
451 | 2035 | OFO-P2035-SK-451 | LIFTING ARRANGEMENT FOR ALUMINUM GANGWAY BY MUTAWA 17 AT HP1 | 1 | A | √ | √ | 2026-07-21 | SIVA | @
452 | 2035 | OFO-P2035-SK-452 | LIFTING ARRANGEMENT FOR ALUMINUM GANGWAY BY MUTAWA 17 AT RP1 | 1 | A | √ | √ | 2026-07-21 | SIVA | @
453 | 2035 | OFO-P2035-SK-453 | LIFTING ARRANGEMENT FOR PROJECT MATERIAL BY MUTAWA 17 AT US-159A WHT | 1 | A | √ | √ | 2026-07-21 | SIVA | @
454 | 2035 | OFO-P2035-SK-454 | LIFTING ARRANGEMENT PROJECT MATERIAL BY MUTAWA 17 AT HP1 | 1 | A | √ | √ | 2026-07-21 | SIVA | @
455 | 2035 | OFO-P2035-SK-455 | LIFTING ARRANGEMENT FOR PROJECT MATERIAL BY MUTAWA 17 AT RP1 | 1 | A | √ | √ | 2026-07-21 | SIVA | @
456 | 2035 | OFO-P2035-SK-456 | SPOOL RECOVERY AND RE-INSTALLATION FOR 2" SINGLE PIGGYBACK OF CORRIDOR SPOOL PL-5 FROM US-153A TO USSC-RP1 (PL-5) @ US-153A | 4 | A | √ | √ | 2026-07-24 | HZD
458 | 2035 | OFO-P2035-SK-457 | HORIZONTAL (HBS) START-UP ARRANGEMENT 16" WF PIPELINE FROM US-19B TO US-153A (PL-4) AT US-19B | 1 | B | √ | √ | 2026-08-27 | SKS | @
459 | 2035 | OFO-P2035-SK-458 | PIPELINE SHIFTING SEQUENCE DURING LAYDOWN FOR PL-4 WITH SAFEEN 3000 | 5 | B | √ | √ | 2026-08-24 | BINOY | @
460 | 2035 | OFO-P2035-SK-459 | Recovery and Re-Installation for 2” Single Piggyback of Corridor Spool PL-5 from US-153A to USSC-RP1 (PL-5) @US-153A by SAFEEN-3000 | 4 | A | √ | √ | 2026-08-27 | CDG | @
461 | 2035 | OFO-P2035-SK-460 | TESTING FLANGE & HYDROTEST REFERENCE DIAGRAM | 1 | A | √ | √ | 2026-09-01 | HZD | @
462 | 2035 | OFO-P2035-SK-461 | Lifting Arrangement of Flange Shroud by SAFEEN-3000 | 2 | A | √ | √ | 2026-09-08 | MF | @
463 | 2035 | OFO-P2035-SK-462 | Recovery Arrangement of Temporary Shroud by SAFEEN-3000 | 2 | A | √ | √ | 2026-09-08 | MF | @
464 | 2035 | OFO-P2035-SK-463 | MUTAWA 401 LIFTING OF BILLY PUGH FOR TRANSFERRING OF PERSONNEL FROM SUPPLY VESSEL TO BARGE AT US 218 |  |  |  |  | 2026-09-01 | NHE
465 | 2035 | OFO-P2035-SK-464 | MUTAWA 401 LIFTING OF BILLY PUGH FOR TRANSFERRING OF PERSONNEL FROM BARGE TO PLATFORM AT US 218 |  |  |  |  | 2026-09-01 | NHE
466 | 2035 | OFO-P2035-SK-465 | MUTAWA 401 LIFTING OF PROJECT MATERIALS AND CCUS FROM SUPPLY VESSEL TO BARGE AT US 218 |  |  |  |  | 2026-09-01 | NHE
467 | 2035 | OFO-P2035-SK-466 | MUTAWA 401 LIFTING OF PROJECT MATERIALS AND CCUS FROM BARGE TO PLATFORM AT US 218 |  |  |  |  | 2026-09-01 | NHE
468 | 2035 | OFO-P2035-SK-467 | MUTAWA 401 LIFTING OF HARD BOTTOM WORK BOAT (ZODIAC) FROM BARGE TO SEA AT US 218 |  |  |  |  | 2026-09-01 | NHE
469 | 2035 | OFO-P2035-SK-468 | MUTAWA 401 LIFTING OF BILLY PUGH FOR TRANSFERRING OF PERSONNEL FROM SUPPLY VESSEL TO BARGE AT US 88 |  |  |  |  | 2026-09-02 | NHE
470 | 2035 | OFO-P2035-SK-469 | MUTAWA 401 LIFTING OF BILLY PUGH FOR TRANSFERRING OF PERSONNEL FROM BARGE TO PLATFORM AT US 88 |  |  |  |  | 2026-09-02 | NHE
471 | 2035 | OFO-P2035-SK-470 | MUTAWA 401 LIFTING OF PROJECT MATERIALS AND CCUS FROM SUPPLY VESSEL TO BARGE AT US 88 |  |  |  |  | 2026-09-02 | NHE
472 | 2035 | OFO-P2035-SK-471 | MUTAWA 401 LIFTING OF PROJECT MATERIALS AND CCUS FROM BARGE TO PLATFORM AT US 88 |  |  |  |  | 2026-09-02 | NHE
473 | 2035 | OFO-P2035-SK-472 | MUTAWA 401 LIFTING OF HARD BOTTOM WORK BOAT (ZODIAC) FROM BARGE TO SEA AT US 88 |  |  |  |  | 2026-09-02 | NHE

## Cut-list
Project 2035-ADNOC
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2035 | 2035-NN-0001 | START UP HEAD DETAILS FOR 16” PIPE LINE (WELD TYPE) | 4 | 1A |  | √ | 2023-05-25 | CSE-OF-2035-T-006 | @ | AKS
2 | 2035 | 2035-NN-0002-CTL | START UP HEAD DETAILS FOR 18" PIPLE LINE (FLANGE TYPE) WITH CUTLIST 1 + 11 | 1 + 11 | 0 | √ | √ | 2023-02-06 | CSE-OF-2035-T-001 | @ | CDG
|  |  |  | 1 + 11 | 1 | √ | √ | 2023-04-04 | CSE-OF-2035-T-005 | @ | AKS
|  |  |  | 1 + 11 | 2 | √ | √ | 2023-05-25 | CSE-OF-2035-T-006 | @ | AKS
3 | 2035 | 2035-NN-0004-CTL | START UP HEAD DETAILS FOR 18" PIPLE LINE (WELD TYPE) WITH CUTLIST 1 + 10 | 1 + 10 | 1 | √ | √ | 2023-02-13 | CSE-OF-2035-T-003 | @ | HZD
|  |  |  | 1 + 10 | 2 | √ | √ | 2023-04-04 | CSE-OF-2035-T-005 | @ | AKS
|  |  |  | 1 + 10 | 3 | √ | √ | 2023-05-25 | CSE-OF-2035-T-006 | @ | AKS
3 | 2035 | 2035-NN-0005-CTL | TYPICAL EMERGENCY HEAD FOR 16" PIPE LINE (WITH CUTLIST 1 + 14 | 1 + 14 | 0 | √ | √ | 2023-02-16 | CSE-OF-2035-T-004 | @ | CDG
|  |  |  | 1 + 14 | 1 | √ | √ | 2023-04-04 | CSE-OF-2035-T-005 | @ | AKS
|  |  |  | 1 + 14 | 2 | √ | √ | 2023-05-25 | CSE-OF-2035-T-006 | @ | AKS
4 | 2035 | 2035-NN-0006-CTL | TYPICAL EMERGENCY HEAD FOR 18" PIPE LINE (WITH CUTLIST 1 + 10 REV-1) | 1 + 10 | 1 | √ | √ | 2023-02-13 | CSE-OF-2035-T-003 | @ | CDG
|  |  |  | 1 + 10 | 2 | √ | √ | 2023-04-04 | CSE-OF-2035-T-005 | @ | AKS
5 | 2035 | 2035-NN-0047-CTL | TEMPORARY 18" PIG LAUNCHER & RECEIVER (WITH CUTLIST 1 + 11 REV-1) | 1 + 11 | 1 | √ | √ | 2023-02-09 | CSE-OF-2035-T-003 | @ | AKS
6 | 2035 | 2035-NN-0048-CTL | TEMPORARY 16" PIG LAUNCHER & RECEIVER (WITH CUTLIST 1 + 11 REV-1) | 1 + 11 | 1 | √ | √ | 2023-02-09 | CSE-OF-2035-T-003 | @ | AKS
| 2035 | 2035-NN-0049-CTL | START UP HEAD DETAILS FOR 16" PIPE LINE (FLANGE TYPE) | 3 | 1A |  | √ | 2023-05-25 | CSE-OF-2035-T-006 | @ | AKS
7 | 2035 | 2035-NN-0050-CTL | LAYDOWN HEAD DETAILS FOR 16" PIPE LINE (FLANGE TYPE) | 1 + 15 1 + 14 | 0 | √ | √ | 2023-02-07 | CSE-OF-2035-T-002 | @ | AKS
|  |  |  | 1 + 15 1 + 14 | 1 | √ | √ | 2023-04-04 | CSE-OF-2035-T-005 | @
|  |  |  | 1 + 15 | 2 | √ | √ | 2023-05-25 | CSE-OF-2035-T-006 | @ | AKS
8 | 2035 | 2035-NN-0051-CTL | LAYDOWN HEAD DETAILS FOR 18" PIPE LINE (FLANGE TYPE) | 1 + 11 | 0 | √ | √ | 2023-02-06 | CSE-OF-2035-T-001 | @ | CDG
|  |  |  | 1 + 11 | 1 | √ | √ | 2023-04-04 | CSE-OF-2035-T-005 | @
|  |  |  | 1 + 11 | 2 | √ | √ | 2023-05-25 | CSE-OF-2035-T-006 | @ | AKS
9 | 2035 | 2035-NN-0056-CTL | START UP HEAD, LAYDOWN, EMERGENCY HEAD & BLIND FLANGE DETAILS FOR 2" PIGGYBACK PIPELINE | 1 + 4 | 0 | √ | √ | 2023-02-06 | CSE-OF-2035-T-001 | @ | CDG
|  |  |  | 1 + 4 | 1 | √ | √ | 2023-05-25 | CSE-OF-2035-T-006 | @ | AKS
10 | 2035 | 2035-NN-0058-CTL | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 50mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 0 | √ | √ | 2023-06-26 | CSE-OF-2035-T-007 | @ | AKS
11 | 2035 | 2035-NN-0059-CTL | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 80mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 0 | √ | √ | 2023-06-26 | CSE-OF-2035-T-007 | @ | AKS
12 | 2035 | 2035-NN-0060-CTL | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 95mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 1 | √ | √ | 2023-07-20 | CSE-OF-2035-T-009 | @ | AKS
13 | 2035 | 2035-NN-0061-CTL | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 70mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 0 | √ | √ | 2023-06-26 | CSE-OF-2035-T-007 | @ | AKS
14 | 2035 | 2035-NN-0062-CTL | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 175mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 0 | √ | √ | 2023-06-26 | CSE-OF-2035-T-007 | @ | AKS
15 | 2035 | 2035-NN-0063-CTL | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 85mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 0 | √ | √ | 2023-06-26 | CSE-OF-2035-T-007 | @ | AKS
16 | 2035 | 2035-NN-0064-CTL | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 150mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 1 | √ | √ | 2023-07-20 | CSE-OF-2035-T-009 | @ | AKS
17 | 2035 | 2035-NN-0065-CTL | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 120mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 1 | √ | √ | 2023-07-20 | CSE-OF-2035-T-009 | @ | AKS
18 | 2035 | 2035-NN-0066-CTL | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 60mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 1 | √ | √ | 2023-07-20 | CSE-OF-2035-T-009 | @ | AKS
19 | 2035 | 2035-NN-0067-CTL | FLANGE PROTECTOR DETAILS FOR 16" PIPELINE WITH 100mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 1 | √ | √ | 2023-07-20 | CSE-OF-2035-T-009 | @ | AKS
20 | 2035 | 2035-NN-0068-CTL | FLANGE PROTECTOR DETAILS FOR 18" PIPELINE WITH 150mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 1 | √ | √ | 2023-07-20 | CSE-OF-2035-T-009 | @ | AKS
21 | 2035 | 2035-NN-0069-CTL | FLANGE PROTECTOR DETAILS FOR 18" PIPELINE WITH 40mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 1 | √ | √ | 2023-07-20 | CSE-OF-2035-T-009 | @ | AKS
22 | 2035 | 2035-NN-0071-CTL | FLANGE PROTECTOR DETAILS FOR 18" PIPELINE WITH 80mm THK. CONCRETE COATING - (WITH CUTLIST) | 1 + 6 | 1 | √ | √ | 2023-07-24 | CSE-OF-2035-T-009 | @ | CDG
23 | 2035 | OFO-P2035-SK-113 | SEAFASTENING GRILLAGE LAYOUT & DETAILS (WITH CUTLIST 2 + 41 – REV-0) | 1 + 12 | 0 | √ | √ | 2024-11-11 | CSE-OF-2035-T-018 | @ | SKT
24 | 2035 | OFO-P2035-SK-114 | CABLE TOWER DETAILS (WITH CUTLIST 4 + 222 - REV-0) | 4 + 222 | 0 | √ | √ | 2024-11-20 | CSE-OF-2035-T-017 | @ | SKT
25 | 2035 | 2035-NN-0120-CTL | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE (WITH SINGLE 2" PIGGYBACK) FORM US-142A TO USSC-RP1 (PL-3) AT USSC-RP1 | 1 + 12 | 0 | √ | √ | 2024-08-01 | CSE-OF-2035-T-015 | @ | AKS
26 | 2035 | 2035-NN-0122-CTL | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE (WITH SINGLE 2" PIGGYBACK) FROM US-153A TO USSC-RP1 (PL-5) AT USSC-RP1 | 1 + 12 | 0 | √ | √ | 2024-08-01 | CSE-OF-2035-T-015 | @ | AKS
27 | 2035 | 2035-NN-0124-CTL | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE FROM US-12B TO USSC-RP1 (PL-2) @ USSC-RP-1 | 1 + 14 | 0 | √ | √ | 2024-08-30 | CSE-OF-2035-T-016 | @ | NAR
28 | 2035 | 2035-NN-0126-CTL | TEMPORARY KNEE BRACE DETAILS FOR 18" WELL FLUID PIPELINE FROM HP2 TO USSC-RP1 (PL-7) @ USSC-RP1 | 1 + 12 | 0 | √ | √ | 2024-08-30 | CSE-OF-2035-T-016 | @ | NAR
29 | 2035 | 2035-NN-0128-CTL | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID PIPELINE FROM HP3 TO USSC-RP1 (PL-8) AT USSC-RP1 | 1 + 12 | 0 | √ | √ | 2024-08-30 | CSE-OF-2035-T-016 | @ | NAR
30 | 2035 | OFO-P2035-SK-116 | STORAGE QUADRANT-1.2M RADIUS FOR 16" J-TUBE | 1 + 9 | 0 | √ | √ | 2025-05-01 | CSE-OF-2035-T-019 | @ | NAR
31 | 2035 | 2035-NN-0159-CTL | TEMPORARY KNEE BRACE DETAILS FOR 16" WELL FLUID SPOOL (WITH SINGLE 2" PIGGYBACK) FROM US-19B TO US-153A (PL-4) AT US-19B | 1 + 8 | 0 | √ | √ | 2025-05-31 | CSE-OF-2035-T-024 | @ | AMK
32 | 2035 | 2035-NN-0014-CTL | CLAMP DETAILS FOR 16” RISER TOP PART AT PL-3 (USSC-RP-1) (WITH CUTLIST 1 + 3– REV-0) | 1 + 3 | 0 | √ | √ | 2025-12-08 | CSE-OF-2035-T-025 | @ | HZD
33 | 2035 | OFO-P2035-SK-284-CTL | RISER TOP PLATE & PADEYE FOR 16” RISER (WITH CUTLIST 1 + 4– REV-1) | 1 + 4 | 1 | √ | √ | 2025-12-08 | CSE-OF-2035-T-025 | @ | AMT
34 | 2035 | OFO-P2035-SK-285-CTL | RISER TOP PLATE & PADEYE FOR 18” RISER (WITH CUTLIST 1 + 4– REV-1 | 1 + 4 | 1 | √ | √ | 2025-12-08 | CSE-OF-2035-T-025 | @ | AMT
35 | 2035 | 2035-NN-0160-CTL | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF RISERS AND SPOOLS @ ES - 282 | 1 + 4 | 0 | √ | √ | 2025-12-08 | CSE-OF-2035-T-026 | @