## Documents - Pipeline & Cable
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
ADNOC GAS EPC WORKSMAXIMIZING ETHANE RECOVERY AND MONETIZATION (MERAM)
|  | NPCC PROJECT NO. 2705 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NMDC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPE STACKING ANALYSIS AT YARD | SDOC-1000482-GG-500-9500-F35-NMD-51-001 |  | A | 2 |  | 2024-09-01 | CSE-2824-29-PMT-T-001 | [5 empty] | -- | -- | 2024-10-23 | JV | comments
|  |  |  | B | 2 |  | 01-11-2024 16/01/2025 | CSE-2705-29-PMT-T-001

## Documents - Naval Marine
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
ADNOC GAS EPC WORKSMAXIMIZING ETHANE RECOVERY AND MONETIZATION (MERAM)
|  | NPCC PROJECT NO. 2824 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Drawings
|  | ADNOC OFFSHORE | [11 empty] | NPCC DOC. No.:
ADNOC GAS EPC WORKSMAXIMIZING ETHANE RECOVERY AND MONETIZATION (MERAM)
|  | NPCC PROJECT NO. 2824 | [11 empty] | REVISION : |  |  |  | 0
|  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (DRAWINGS) | [11 empty] | DATE : |  |  |  | 2023-08-02
SR. NO. | DESCRIPTION | NPCC DOCUMENT NUMBER | COMPANY DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLAN | NPCC |  |  |  | ADNOC OFFSHORE | [7 empty] | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO ADNOC |  | FROM CLIENT |  |  | PMT TO MWS |  | STATUS FROM MWS
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 |  | 2824-NN-0001

## Sketch
Project 2824
SKETCHES
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location
1 | 2824

## Cut-lists
Project 2824
CUT-LIST DRAWINGS
CATEGORY : | [5 empty] | FORMAT |  | Transmittal/Source |  |  | REMARKS
S.NO. | PROJECT | OFFSHORE DWG NO. | TITLE/DESCRIPTION | NO. OF SHEETS | REV | ACAD | PDF | Date | Reference | Location