## Data_List_Final_04
Lower Zakum LTDP­1, EPC Works for EPS­2 and PDP Project
PROJECT DELIVERABLES REGISTER
COMPANY Project No. |  |  |  |  | COMPANY DOC. No. AD-27-G-00915 |  |  | REV
14001-11688
CONTRACTOR Project No. |  |  |  |  | CONTRACTOR DOC. No. 2745-PP-GE-001 |  |  | 2
2745
S/NO | COMPANY DOCUMENT No. | ID2 | ID4 | ID5 | CONTRACTOR DOCUMENT No. | TITLE / DESCRIPTION | DOCUMENT CLASS | PLANNED ISSUANCE DATE | DOCUMENT CLASS
1 | PROJECT GENERAL
1.1 | AD-27-G-00915 |  |  |  | 2745-PP-GE-001 | PROJECT DELIVERABLES REGISTER
1.2 | AD-27-G-00916 |  |  |  | 2745-PP-GE-002 | PROJECT EXECUTION PLAN
1.3 | AD-27-G-00917 |  |  |  | 2745-PP-GE-003 | PROJECT COORDINATION PROCEDURE
1.4 | AD-27-G-00918 |  |  |  | 2745-PP-GE-004 | DOCUMENT CONTROL PROCEDURE
1.5 | AD-27-G-00919 |  |  |  | 2745-PP-GE-005 | PROJECT CONTROL PROCEDURE
1.6 | AD-27-G-00920 |  |  |  | 2745-PP-GE-006 | PROJECT PLANNING PACKAGE
1.7 | AD-27-G-00921 |  |  |  | 2745-PP-GE-007 | INVOICING PROCEDURE
1.8 | AD-27-G-00922 |  |  |  | 2745-PP-GE-008 | 90 DAYS SCHEDULE
1.9 | AD-27-G-00923 |  |  |  | 2745-PP-GE-009 | PROJECT CONTROLS CLOSE OUT REPORT
1.1 | AD-27-G-00924 |  |  |  | 2745-PP-GE-010 | SUB-CONTRACT PROCEDURE
1.11 | AD-27-G-00925 |  |  |  | 2745-PP-GE-011 | CHANGE MANAGEMENT PROCEDURE
1.12 | AD-27-G-00926 |  |  |  | 2745-PP-GE-012 | FINAL DOSSIER INDEX
1.13 | AD-27-G-00927 |  |  |  | 2745-PP-GE-013 | CLOSE OUT REPORT
1.14 | AD-27-G-00928 |  |  |  | 2745-PP-GE-014 | RISK MANGEMENT PROCEDURE
| AD-27-G-02951 |  |  |  | 2745-PP-GE-015 | PROJECT RISK MANAGEMENT PLAN
1.16 | AD-27-G-00929 |  |  |  | 2745-PP-GE-016 | PROJECT RISK REGISTER
1.17 | AD-27-G-00930 |  |  |  | 2745-PP-GE-017 | INTERFACE MANAGEMENT PROCEDURE
1.18 | AD-27-G-00931 |  |  |  | 2745-PP-GE-018 | INTERFACE REGISTER
1.19 | AD-27-G-00932 |  |  |  | 2745-PP-GE-019 | LONG LEAD AND CERITICAL ITEMS LIST
1.2 | AD-27-G-00933 |  |  |  | 2745-PP-GE-020 | SPARE PARTS DATA PACKAGE SUBMITTAL PLAN
1.21 | AD-27-G-00934 |  |  |  | 2745-PP-GE-021 | TERMS OF REFERENCE FOR RISK MANAGEMENT WORKSHOP
1.22 | AD-27-G-00935 |  |  |  | 2745-PP-GE-022 | TERMS OF REFERENCE FOR LESSON LEARNT WORKSHOP
| AD-27-G-02952 |  |  |  | 2745-PP-GE-023 | VENDOR DOCUMENTS MANAGMENT PROCEDURE
| AD-27-G-02953 |  |  |  | 2745-PP-GE-024 | SCOPE OF WORK FOR TRAINING COMPANY’S ENGINEERS
| AD-27-G-02954 |  |  |  | 2745-PP-GE-025 | POSITIVE MATERIAL IDENTIFICATION (PMI) SPECIFICATION
| AD-27-G-023004 |  |  |  | 2745-PP-GE-026 | PROJECT INTEGRITY PLAN
[5 empty] | 2745-PP-GE-027 | PROJECT LESSONS LEARNED - MASTER REGISTER
[5 empty] | 2745-PP-GE-028 | Fabrication Readiness Review Checklist for EPS-2 GO NO GO
[5 empty] | 2745-PP-GE-029 | PROJECT MATERIAL MANAGEMENT PROCEDURE
[5 empty] | 2745-PP-GE-030 | PROJECT SCHEDULE RISK ANALYSIS PROCEDURE
[5 empty] | 2745-PP-GE-031 | PROJECT TARGET PLANNING PACKAGE
[5 empty] | 2745-PP-GE-032 | METHOD STATEMENT FOR GROUT LINE HYDROTESTING
2 | PROCUREMENT
2.1 | AD-27-G-00936 |  |  |  | 2745-PP-PR-001 | PROJECT PROCUREMENT PROCEDURE
2.2 | AD-27-G-00937 |  |  |  | 2745-PP-PR-002 | VENDOR INSPECTION COORDINATION PROCEDURE
3 | HSE
3.1 | AD-27-G-00938 |  |  |  | 2745-PP-HS-001 | PROJECT HSE PLAN
3.2 | AD-27-G-00939 |  |  |  | 2745-PP-HS-002 | PROJECT CONSTRUCTION HSE PLAN
3.3 | AD-27-G-00940 |  |  |  | 2745-PP-HS-003 | EMERGENCY RESPONSE PLAN
3.4 | AD-27-G-00941 |  |  |  | 2745-PP-HS-004 | PROJECT WASTE MANAGEMENT PLAN
3.5 | AD-27-G-00942 |  |  |  | 2745-PP-HS-005 | PROJECT WELFARE MANAGEMENT PLAN
3.6 | AD-27-G-00943 |  |  |  | 2745-PP-HS-006 | EMERGENCY BRIDGING PLANS
3.7 | AD-27-G-02955 |  |  |  | 2745-PP-HS-007 | HEAT STRESS MANAGEMENT PLAN
| AD-27-G-02956 |  |  |  | 2745-PP-HS-008 | CONSTRUCTION ENVIORMENTAL MANAGEMENT PLAN
| AD-27-G-02957 |  |  |  | 2745-PP-HS-009 | HSE FOCUS PLAN
| AD-27-G-02958 |  |  |  | 2745-PP-HS-010 | SIMULTANEOUS OPERATIONS (SIMOPS) REPORT
| AD-27-G-02959 |  |  |  | 2745-PP-HS-011 | SOCIAL IMPACT SCREENING REPORT
| AD-27-G-02960 |  |  |  | 2745-PP-HS-012 | TERMS OF REFERENCE FOR SIMOPS STUDY
| AD-27-G-02961 |  |  |  | 2745-PP-HS-013 | TERMS OF REFERENCE FOR SOCIAL IMPACT SCREENING WORKSHOP
| AD-27-G-02962 |  |  |  | 2745-PP-HS-014 | TERMS OF REFERENCE FOR GHG/BAT
| AD-27-G-02963 |  |  |  | 2745-PP-HS-015 | GHG MANANAGENT PLAN
| AD-27-G-02964 |  |  |  | 2745-PP-HS-016 | EXTERNAL STAKEHOLDER ENGAGEMENT PLAN (ESEP)
| AD-27-G-02965 |  |  |  | 2745-PP-HS-017 | GHG/BAT ASSESSMENT REPORT
| AD-27-G-02966 |  |  |  | 2745-PP-HS-018 | TERMS OF REFERENCE FOR SOCIAL IMPACT SCREENING WORKSHOP
| AD-27-G-01315 |  |  |  | 2745-PP-HS-019 | PROJECT INCENTIVE PLAN
4 | QA&QC
4.1 | AD-27-G-00944 |  |  |  | 2745-PP-QA-001 | PROJECT QUALITY PLAN
4.2 | AD-27-G-00945 |  |  |  | 2745-PP-QA-002 | PROJECT MATERIAL CONTROL, INSPECTION, IDENTIFICATION & TRACEABILITY PROCEDURE
4.3 | AD-27-G-00946 |  |  |  | 2745-PP-QA-003 | NON-CONFORMANCE REPORTING PROCEDURE
4.4 | AD-27-G-00947 |  |  |  | 2745-PP-QA-004 | DIMENSIONAL CONTROL PROCEDURE
4.5 | AD-27-G-00948 |  |  |  | 2745-PP-QA-005 | HARDNESS TESTING PROCEDURE
4.6 | AD-27-G-00949 |  |  |  | 2745-PP-QA-006 | ULTRASONIC TESTING PROCEDURE
4.7 | AD-27-G-00950 |  |  |  | 2745-PP-QA-007 | MAGNETIC PARTICLE TESTING PROCEDURE
4.8 | AD-27-G-00951 |  |  |  | 2745-PP-QA-008 | RADIOGRAPHIC TESTING PROCEDURE
4.9 | AD-27-G-00952 |  |  |  | 2745-PP-QA-009 | LIQUID PENETRANT TESTING PROCEDURE
4.1 | AD-27-G-00953 |  |  |  | 2745-PP-QA-010 | QC PERSONNEL LIST
4.11 | AD-27-G-00954 |  |  |  | 2745-PP-QA-011 | PROJECT QUALITY AUDIT SCHEDULE
4.12 | AD-27-G-00955 |  |  |  | 2745-PP-QA-012 | PROJECT QUALITY AUDIT PROCEDURE
4.13 | AD-27-G-00956 |  |  |  | 2745-PP-QA-013 | PROJECT QAQC ORGANIZATION CHART
4.14 | AD-27-G-00957 |  |  |  | 2745-PP-QA-014 | PHASED ARRAY ULTRASONIC TESTING PROCEDURE
4.15 | AD-27-G-00958 |  |  |  | 2745-PP-QA-015 | AUTOMATIC ULTRASONIC TESTING PROCDEURE FOR PIPELINE
4.16 | AD-27-G-00959 |  |  |  | 2745-PP-QA-016 | AUTOMATIC ULTRASONIC TESTING VALIDATION PROCDEURE
4.17 | AD-27-G-00960 |  |  |  | 2745-PP-QA-017 | MAGNETIC PARTICLE TESTING PROCEDURE (PIPELINE)
4.18 | AD-27-G-00961 |  |  |  | 2745-PP-QA-018 | ULTRASONIC TESTING PROCEDURE (PIPELINE)
4.19 | AD-27-G-00962 |  |  |  | 2745-PP-QA-019 | LIST OF NDT OPERATORS (ONSHORE & OFFSHORE)
4.2 | AD-27-G-00963 |  |  |  | 2745-PP-QA-020 | LIST OF PAUT PERSONNEL - OFFSHORE
4.21 | AD-27-G-00964 |  |  |  | 2745-PP-QA-021 | WELDING CONSUMABLE CONTROL PROCEDURE
4.22 | AD-27-G-00965 |  |  |  | 2745-PP-QA-022 | WELDING PROCEDURES - STRUCTURAL
4.23 | AD-27-G-00966 |  |  |  | 2745-PP-QA-023 | WELDING PROCEDURES - PIPELINES, RISERS & PIPELINE SPOOLS
4.24 | AD-27-G-00967 |  |  |  | 2745-PP-QA-024 | WELDING PROCEDURES - PIPELINE CAD (THERMIT)
4.25 | AD-27-G-00968 |  |  |  | 2745-PP-QA-025 | WELDING PROCEDURES - PIPING
4.26 | AD-27-G-00969 |  |  |  | 2745-PP-QA-026 | MUSSFAH WELDERS LIST-STRUCTURAL
4.27 | AD-27-G-00970 |  |  |  | 2745-PP-QA-027 | MUSSFAH WELDERS LIST-RISER & PIPELINE SPOOLS
4.28 | AD-27-G-00971 |  |  |  | 2745-PP-QA-028 | MUSSFAH WELDERS - PIPING
4.29 | AD-27-G-00972 |  |  |  | 2745-PP-QA-029 | OFFSHORE WELDERS LIST-STRUCTURAL
4.3 | AD-27-G-00973 |  |  |  | 2745-PP-QA-030 | OFFSHORE WELDERS LIST - PIPING
4.31 | AD-27-G-00974 |  |  |  | 2745-PP-QA-031 | OFFSHORE WELDERS LIST (RISERS & TIE-IN)
4.32 | AD-27-G-00975 |  |  |  | 2745-PP-QA-032 | OFFSHORE WELDERS LIST (PIPELINE) - AUTOMATIC & REPAIR
4.33 | AD-27-G-00976 |  |  |  | 2745-PP-QA-033 | INSPECTION & TEST PLAN FOR FOR ONSHORE STRUCTURAL WORKS
4.34 | AD-27-G-00977 |  |  |  | 2745-PP-QA-034 | INSPECTION & TEST PLAN FOR PIPING FABRICATION, INSTALLATION & TESTING
4.35 | AD-27-G-00978 |  |  |  | 2745-PP-QA-035 | INSPECTION & TEST PLAN FOR RISER & PIPELINE SPOOL FABRICATION
4.36 | AD-27-G-00979 |  |  |  | 2745-PP-QA-036 | INSPECTION & TEST PLAN FOR OFFSHORE PIPELAYING & RISER INSTALLATION
4.37 | AD-27-G-00980 |  |  |  | 2745-PP-QA-037 | QC PERSONNEL LIST (OFFSHORE)
4.38 | AD-27-G-00981 |  |  |  | 2745-PP-QA-038 | INSPECTION & TEST PLAN FOR ELECTRICAL WORKS (ONSHORE)
4.39 | AD-27-G-00982 |  |  |  | 2745-PP-QA-039 | INSPECTION AND TEST PLAN FOR OFFSHORE INSTALLATION & HOOK-UP
4.4 | AD-27-G-00983 |  |  |  | 2745-PP-QA-040 | INSPECTION & TEST PLAN FOR INSTRUMENTATION WORKS (ONSHORE & OFFSHORE)
4.41 | AD-27-G-00984 |  |  |  | 2745-PP-QA-041 | CALIBRATION OF MEASURING AND TESTING EQUIPMENT PROCEDURE
4.42 | AD-27-G-00985 |  |  |  | 2745-PP-QA-042 | IECEx PERSONNEL LIST WITH QUALIFICATION RECORDS
4.43 | AD-27-G-00986 |  |  |  | 2745-PP-QA-043 | INSPECTION & TEST PLAN FOR SUBSEA CABLE INSTALLATION
4.44 | AD-27-G-00987 |  |  |  | 2745-PP-QA-044 | INSPECTION & TEST PLAN FOR TELECOMMUNICATION WORKS (ONSHORE & OFFSHORE)
4.45 | AD-27-G-00988 |  |  |  | 2745-PP-QA-045 | INSPECTION AND TEST PLAN FOR COATING WORK ( ONSHORE & OFFSHORE)
4.46 | AD-27-G-00989 |  |  |  | 2745-PP-QA-046 | STRUCTURAL NDT PLAN
4.47 | AD-27-G-00990 |  |  |  | 2745-PP-QA-047 | MUSAFFAH WELDERS LIST - GROUT PIPES
4.48 | AD-27-G-00991 |  |  |  | 2745-PP-QA-048 | INSPECTION & TEST PLAN FOR INSTALLATION OF SUBSEA UMBILICAL / SUBSEA COMPOSITE AND FIBRE OPTIC CABLE WORKS
4.49 | AD-27-G-00992 |  |  |  | 2745-PP-QA-049 | INSPECTION AND TEST PLAN (MATERIAL RECEIVING INSPECTION)
4.5 | AD-27-G-00993 |  |  |  | 2745-PP-QA-050 | INSPECTION AND TESTING PLAN FOR CONCRETE WEIGHT COATING AND ANODE INSTALLATION
4.51 | AD-27-G-00994 |  |  |  | 2745-PP-QA-051 | INSPECTION AND TESTING PLAN FOR EXTERNAL LINE PIPE THREE LAYER POLYETHYLENE COATING
4.52 | AD-27-G-00995 |  |  |  | 2745-PP-QA-052 | INSPECTION AND TESTING PLAN FOR EXTERNAL LINE PIPE THREE LAYER POLYPROPYLENE COATING
4.55 | AD-27-G-02974 |  |  |  | 2745-PP-QA-055 | SPARE
4.58 | AD-27-G-02977 |  |  |  | 2745-PP-QA-058 | PROJECT INSPECTION COORDINATION PROCEDURE (VENDORS)
4.59 | AD-27-G-02978 |  |  |  | 2745-PP-QA-059 | PROJECT INSPECTION COORDINATION PROCEDURE (INTERNAL, SUBCONTRACTORS, FABRICATION, CONSTRUCTION)
4.6 | AD-27-G-02979 |  |  |  | 2745-PP-QA-060 | WELD REPAIR PROCEDURES (INCLUDING ARC BURN REPAIR & ARC GOUGING)
4.61 | AD-27-G-02980 |  |  |  | 2745-PP-QA-061 | CORRECTIVE & PREVENTIVE ACTION PROCEDURE
4.62 | AD-27-G-02981 |  |  |  | 2745-PP-QA-062 | POSITIVE MATERIAL IDENTIFICATION (PMI) SPECIFICATION
4.63 | AD-27-G-02982 |  |  |  | 2745-PP-QA-063 | PROCEDURE FOR POSITIVE MATERIAL IDENTIFICATION
4.64 | AD-27-G-02983 |  |  |  | 2745-PP-QA-064 | FABRICATION QUALITY DOSSIER INDEX (TEMPLATE)
4.65 | AD-27-G-02984 |  |  |  | 2745-PP-QA-065 | CONSTRUCTION QUALITY DOSSIER INDEX (TEMPLATE)
4.66 | AD-27-G-02985 |  |  |  | 2745-PP-QA-066 | WELD NUMBERING PROCEDURE
4.67 | AD-27-G-02986 |  |  |  | 2745-PP-QA-067 | BASELINE SURVEY PROCEDURE
4.68 | AD-27-G-02987 |  |  |  | 2745-PP-QA-068 | PROJECT WELDING SPECIFICATION (PIPING)
4.69 | AD-27-G-02988 |  |  |  | 2745-PP-QA-069 | STRUCTURAL STEEL WELDING SPECIFICATION
| AD-27-G-02989 |  |  |  | 2745-PP-QA-070 | PROCEDURE FOR POST-WELD HEAT TREATMENT OF PIPING JOINTS BY ELECTRICAL RESISTANCE METHOD (LOCAL)
| AD-27-G-01433 |  |  |  | 2745-PP-QA-071 | RADIOGRAPHY FILM DIGITIZATION PROCEDURE (NMDC YARD & OFFSHORE
| AD-27-G-01434 |  |  |  | 2745-PP-QA-072 | DIGITAL RADIOGRAPHIC (DR) TESTING PROCEDURE (NMDC YARD & OFFSHORE)
5 | ONSHORE INSTALLATION
5.2 | AD-27-G-00996 |  |  |  | 2745-PP-ON-002 | STORES MANUAL
5.3 | AD-27-G-00997 |  |  |  | 2745-PP-ON-003 | STRUCTURAL FABRICATION and ERECTION PROCEDURE
5.4 | AD-27-G-00998 |  |  |  | 2745-PP-ON-004 | PIPING & PIPELINE SPEC. SPOOLS FABRICATION AND ERECTION PROCEDURE
5.5 | AD-27-G-00999 |  |  |  | 2745-PP-ON-005 | PIPING & RISER TESTING PROCEDURE
5.6 | AD-27-G-01000 |  |  |  | 2745-PP-ON-006 | PLATE GIRDER FABRICATION PROCEDURE
5.7 | AD-27-G-01001 |  |  |  | 2745-PP-ON-007 | PAINTING PROCEDURE
5.8 | AD-27-G-01002 |  |  |  | 2745-PP-ON-008 | PASSIVE FIRE PROOFING PROCEDURE
5.9 | AD-27-G-01003 |  |  |  | 2745-PP-ON-009 | HOT DIP GALVANIZING PROCEDURE
5.1 | AD-27-G-01004 |  |  |  | 2745-PP-ON-010 | DISTORTION ORRECTION PROCEDURE
5.11 | AD-27-G-01005 |  |  |  | 2745-PP-ON-011 | PWHT PROCEDURE FOR PIPING (FURNACE / LOCAL)
5.12 | AD-27-G-01006 |  |  |  | 2745-PP-ON-012 | FLANGE MANAGEMENT PROCEDURE
5.13 | AD-27-G-01007 |  |  |  | 2745-PP-ON-013 | VALVE TESTING PROCEDURE
5.14 | AD-27-G-01008 |  |  |  | 2745-PP-ON-014 | METHOD STATEMENT FOR COLD BENDING OF TUBULAR BENDS
5.15 | AD-27-G-01009 |  |  |  | 2745-PP-ON-015 | SHRINKAGE AND DISTORTION CONTROL PROCEDURE
5.16 | AD-27-G-01010 |  |  |  | 2745-PP-ON-016 | GAP CONTROL METHOD STATEMENT (SOCKET WELDS & THREADED ENGAGEMENT)
5.18 | AD-27-G-01011 |  |  |  | 2745-PP-ON-018 | PROCEDURE FOR CABLE GLANDING AND CONDUIT SEALING
5.19 | AD-27-G-01012 |  |  |  | 2745-PP-ON-019 | PROCEDURE FOR HIGH /MEDIUM VOLTAGE (HV/MV) CABLE SPLICING / TERMINATION
5.2 | AD-27-G-01013 |  |  |  | 2745-PP-ON-020 | PROCEDURE FOR FIBER OPTIC CABLE INSTALLATION, SPLICING AND TESTING
5.21 | AD-27-G-01014 |  |  |  | 2745-PP-ON-021 | PROCEDURE OF CONTROL & CALIBRATIOIN OF MEASURING, INSPECTION AND TESTING INSTRUMENTS
5.22 | AD-27-G-02967 |  |  |  | 2745-PP-ON-022 | METHOD STATEMENT FOR INSTALLATION OF TRANSFORMER AND OIL FILTRATION
5.23 | AD-27-G-02968 |  |  |  | 2745-PP-ON-023 | LOADOUT PROCEDURE
| AD-27-G-02969 |  |  |  | 2745-PP-ON-024 | GIS INSTALLATION PROCEDURE
5.24 | AD-27-G-02970 |  |  |  | 2745-PP-ON-025 | METHOD STATEMENT FOR COLD BENDING OF SHAPES
| AD-27-G-02971 |  |  |  | 2745-PP-ON-026 | SCOPE OF WORK FOR FABRICATION OF STRUCTURAL TERTIARY ITEMS
| AD-27-G-01314 |  |  |  | 2745-PP-ON-027 | SCOPE OF WORK FOR FABRICATION OF PLATE GIRDERS
| AD-27-G-02972 |  |  |  | 2745-PP-ON-028 | THREE LAYER POLYETHYLENE COATING PROCEDURE FOR LINE PIPE
| AD-27-G-02973 |  |  |  | 2745-PP-ON-029 | THREE LAYER POLYPROPYLENE COATING PROCEDURE FOR LINE PIPE
| AD-27-G-02975 |  |  |  | 2745-PP-ON-030 | CONCRETE WEIGHT COATING AND ANODE INSTALLATION PROCEDURE
| AD-27-G-02976 |  |  |  | 2745-PP-ON-031 | OLOR CODING SYSTEM FOR CONCRETE COATED PIPES
| AD-27-G-01312 |  |  |  | 2745-PP-ON-032 | PICKLING AND PASSIVATION PROCEDURE
| AD-27-G-01313 |  |  |  | 2745-PP-ON-033 | LOWER ZAKUM - SPECIFICATION FOR FABRICATION, ERECTION & TESTING OF METALLIC PIPEWORK (Addendum to AGES-SP-09-007, Rev.1)
| AD-27-G-023005 |  |  |  | 2745-PP-ON-034 | PROCEDURE FOR ELECTRICAL/ INSTRUMENTATION/ TELECOM INSTALLATION & PRE_COM WORKS
[5 empty] | 2745-PP-ON-035 | STOCKPILING & HANDLING PROCEDURE FOR BARE & 3-LAYER / CONCRETE COATED PIPES
6 | OFFSHORE INSTALLATION
| AD-27-G-01022 |  |  |  | 2745-PP-OF-001 | PRE-ENGINEERING GEOPHYSICAL SURVEY PROCEDURE(If Required)
6.2 | AD-27-G-01023 |  |  |  | 2745-PP-OF-002 | PRE-ENGINEERING GEOTECHNICAL SURVEY PROCEDURE(If Required)
6.3 | AD-27-G-01024 |  |  |  | 2745-PP-OF-003 | GEOTECHNICAL FACTUAL REPORT(If Required)
6.4 | AD-27-G-01025 |  |  |  | 2745-PP-OF-004 | PRE-ENGINEERING JACKET FACE DIVING SURVEY PROCEDURE
6.5 | AD-27-G-01026 |  |  |  | 2745-PP-OF-005 | PRE-ENGINEERING ACKET FACE & APPROACH ROV SURVEY PROCEDURE
6.6 | AD-27-G-01027 |  |  |  | 2745-PP-OF-006 | PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY PROCEDURE
6.7 | AD-27-G-01028 |  |  |  | 2745-PP-OF-007 | POST-CONSTRUCTION ANCHOR CLEARANCE SURVEY PROCEDURE
6.8 | AD-27-G-01029 |  |  |  | 2745-PP-OF-008 | POSITIONING AND INSTALLATION SURVEY PROCEDURE
6.9 | AD-27-G-01030 |  |  |  | 2745-PP-OF-009 | PIPELINE BASELINE SURVEY PROCEDURE
6.1 | AD-27-G-01031 |  |  |  | 2745-PP-OF-010 | PIPELINE BASELINE SURVEY REPORT
6.11 | AD-27-G-01032 |  |  |  | 2745-PP-OF-011 | PRE-ENGINEERING GEOPHYSICAL SURVEY REPORT(If Required)
6.12 | AD-27-G-01033 |  |  |  | 2745-PP-OF-012 | PRE-ENGINEERING GEOTECHNICAL SURVEY REPORT(If Required)
6.13 | AD-27-G-01034 |  |  |  | 2745-PP-OF-013 | PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY REPORT
6.14 | AD-27-G-01035 |  |  |  | 2745-PP-OF-014 | POST-CONSTRUCTION ANCHOR CLEARANCE SURVEY REPORT
6.15 | AD-27-G-01036 |  |  |  | 2745-PP-OF-015 | PRE-ENGINEERING ROV/CROSSING SURVEY REPORT
6.16 | AD-27-G-01037 |  |  |  | 2745-PP-OF-016 | PIPELINE/CABLE AS-BUILT SURVEY PROCEDURE
6.17 | AD-27-G-01038 |  |  |  | 2745-PP-OF-017 | PIPELINE AS LAID SURVEY PROCEDURE
6.18 | AD-27-G-01039 |  |  |  | 2745-PP-OF-018 | CABLE AS LAID SURVEY PROCEDURE
6.19 | AD-27-G-01040 |  |  |  | 2745-PP-OF-019 | PIPELINE AS-BUILT SURVEY REPORT
6.2 | AD-27-G-01041 |  |  |  | 2745-PP-OF-020 | CABLE AS-BUILT SURVEY REPORT
6.21 | AD-27-G-01042 |  |  |  | 2745-PP-OF-021 | PIPELINE AS LAID SURVEY REPORT
6.22 | AD-27-G-01043 |  |  |  | 2745-PP-OF-022 | CABLE AS LAID SURVEY REPORT
6.23 | AD-27-G-01044 |  |  |  | 2745-PP-OF-023 | ANCHOR HANDLING PROCEDURE FOR GRAVITY ANCHORS BY HAMMER HEAD CRANE VESSEL
6.24 | AD-27-G-01045 |  |  |  | 2745-PP-OF-024 | ANCHOR HANDLING AND MOORING PROCEDURE FOR WORK BOATS
6.25 | AD-27-G-01046 |  |  |  | 2745-PP-OF-025 | ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES
6.26 | AD-27-G-01047 |  |  |  | 2745-PP-OF-026 | ANCHOR HANDLING AND MOORING PROCEDURE FOR JACK UP BARGES
6.27 | AD-27-G-01048 |  |  |  | 2745-PP-OF-027 | FREE SPANS CORRECTION & GROUT BAG INSTALLATION PROCEURE
6.28 | AD-27-G-01049 |  |  |  | 2745-PP-OF-028 | SLEEPERS/MATTRESS/BLOCKS INSTALLATION PROCEDURES
6.29 | AD-27-G-01050 |  |  |  | 2745-PP-OF-029 | PIPELINE INFILL MATERIAL FIELD JOINT COATING PROCEDURE
6.3 | AD-27-G-01051 |  |  |  | 2745-PP-OF-030 | PIPELINE ANTI-CORROSION FIELD JOINT COATING PROCEDURE
6.31 | AD-27-G-01052 |  |  |  | 2745-PP-OF-031 | PIPELINES INSTALLATION MANUAL
6.32 | AD-27-G-01053 |  |  |  | 2745-PP-OF-032 | COMPOSITE CABLE INSTALLATION PROCEDURE
6.33 | AD-27-G-01054 |  |  |  | 2745-PP-OF-033 | RISER INSTALLATION PROCEDURE
6.34 | AD-27-G-01055 |  |  |  | 2745-PP-OF-034 | J-TUBE AND RISER CLAMPS INSTALLATION PROCEDURE
6.35 | AD-27-G-01056 |  |  |  | 2745-PP-OF-035 | J-TUBE INSTALLATION PROCEDURE
6.36 | AD-27-G-01057 |  |  |  | 2745-PP-OF-036 | TOPSIDE INSTALLATION PROCEDURE
6.37 | AD-27-G-01058 |  |  |  | 2745-PP-OF-037 | TOPSIDE INSTALLATION BY FLOATOVER METHOD PROCEDURE
6.38 | AD-27-G-01059 |  |  |  | 2745-PP-OF-038 | TOPSIDE INSTALLATION BY LIFTING METHOD PROCEDURE
6.39 | AD-27-G-01060 |  |  |  | 2745-PP-OF-039 | JACKET INSTALLATION PROCEDURE
6.4 | AD-27-G-01061 |  |  |  | 2745-PP-OF-040 | BRIDGE INSTALLATION PROCEDURE
6.41 | AD-27-G-01062 |  |  |  | 2745-PP-OF-041 | PIPELINES FLOODING, GAUGING, CLEANING AND HYDROTESTING PROCEDURE
6.42 | AD-27-G-01063 |  |  |  | 2745-PP-OF-042 | OFFSHORE HOOK-UP PROCEDURE
6.43 | AD-27-G-01064 |  |  |  | 2745-PP-OF-043 | PIPELINES CALIPER PIGGING PROCEDURE
6.44 | AD-27-G-01065 |  |  |  | 2745-PP-OF-044 | PIPELINES Intelligent PIGGING & Preservation PROCEDURE
6.45 | AD-27-G-01066 |  |  |  | 2745-PP-OF-045 | PIPELINES DEWATERING, DRYING AND NITROGEN PURGING PROCEDURE
6.46 | AD-27-G-01067 |  |  |  | 2745-PP-OF-046 | COMPOSITE CABLE TRANSPOOLING PROCEDURE
6.47 | AD-27-G-01068 |  |  |  | 2745-PP-OF-047 | 3D LASER SCAN SURVEY PROCEDURE
6.48 | AD-27-G-01069 |  |  |  | 2745-PP-OF-048 | PRE - ENGINEERING GEOTECHANICAL SURVEY AND PIPE SOIL INTERACTION REPORT SURVEY REPORT(If Required)
6.237 | AD-27-G-01070 |  |  |  | 2745-PP-OF-049 | BROWNFIELD AND HOOK-UP EXECUTION PLAN.
| AD-27-G-01071 |  |  |  | 2745-PP-OF-050 | OFFSHORE INSTALLATION EXECUTION PLAN
| AD-27-G-01072 |  |  |  | 2745-PP-OF-052 | MOBILIZATION AND CALIBRATION REPORT FOR PRE ENGINEERING ROV SURVEY-VESSEL DP2 – CREST ALPHA-1
| AD-27-G-01316 |  |  |  | 2745-PP-OF-053 | ECA METHOD STATEMENT FOR LOWER ZAKUM LTDP-1 EPS-2 PROJECT PIPELINES
| AD-27-G-01317 |  |  |  | 2745-PP-OF-054 | ECA REPORT FOR 16”- WPL-2 (WATER INJECTION PIPELINE
| AD-27-G-01318 |  |  |  | 2745-PP-OF-055 | ECA REPORT FOR 16” - OPL-2 (WELL FLUID PIPELINE)
| AD-27-G-01319 |  |  |  | 2745-PP-OF-056 | ECA REPORT FOR 18”- WPL-3 (WATER INJECTION PIPELINE)
| AD-27-G-01320 |  |  |  | 2745-PP-OF-057 | ECA REPORT FOR 20”- OPL-3 AND 24”- OPL-4 (WELL FLUID PIPELINES)
[5 empty] | 2745-PP-OF-058 | .6KV COMPOSITE CABLE LAYING PROCEDURE
[5 empty] | 2745-PP-OF-059 | OFFSHORE EXECUTION PLAN EPS-2 AND PDP PROJECT
6.49 | AD-27-G-01073 |  |  |  | 2745-NN-RP-001 | PIPE STACKING ANALYSIS REPORT
6.5 | AD-27-G-01074 |  |  |  | 2745-NN-RP-002 | PIPELAY ANALYSIS REPORT FOR 16" WI
6.51 | AD-27-G-01075 |  |  |  | 2745-NN-RP-003 | PIPELAY ANALYSIS REPORT FOR 18"
6.52 | AD-27-G-01076 |  |  |  | 2745-NN-RP-004 | PIPELAY ANALYSIS REPORT FOR 20
6.53 | AD-27-G-01077 |  |  |  | 2745-NN-RP-005 | PIPELAY ANALYSIS REPORT FOR 24
6.54 | AD-27-G-01078 |  |  |  | 2745-NN-RP-006 | PIPELAY ANALYSIS REPORT FOR 16" OIL
6.55 | AD-27-G-01079 |  |  |  | 2745-NN-RP-007 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 1
6.56 | AD-27-G-01080 |  |  |  | 2745-NN-RP-008 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 2
6.57 | AD-27-G-01081 |  |  |  | 2745-NN-RP-009 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 3
6.58 | AD-27-G-01082 |  |  |  | 2745-NN-RP-010 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 4
6.59 | AD-27-G-01083 |  |  |  | 2745-NN-RP-011 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 5
6.6 | AD-27-G-01084 |  |  |  | 2745-NN-RP-012 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 6
6.61 | AD-27-G-01085 |  |  |  | 2745-NN-RP-013 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 7
6.62 | AD-27-G-01086 |  |  |  | 2745-NN-RP-014 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 8
6.63 | AD-27-G-01087 |  |  |  | 2745-NN-RP-015 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE 9
6.64 | AD-27-G-01088 |  |  |  | 2745-NN-RP-016 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 1
6.65 | AD-27-G-01089 |  |  |  | 2745-NN-RP-017 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 2
6.66 | AD-27-G-01090 |  |  |  | 2745-NN-RP-018 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 3
6.67 | AD-27-G-01091 |  |  |  | 2745-NN-RP-019 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 4
6.68 | AD-27-G-01092 |  |  |  | 2745-NN-RP-020 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 5
6.69 | AD-27-G-01093 |  |  |  | 2745-NN-RP-021 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 6
6.7 | AD-27-G-01094 |  |  |  | 2745-NN-RP-022 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 7
6.71 | AD-27-G-01095 |  |  |  | 2745-NN-RP-023 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 8
6.72 | AD-27-G-01096 |  |  |  | 2745-NN-RP-024 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 9
6.73 | AD-27-G-01105 |  |  |  | 2745-NN-RP-025 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS AND MATTRESSES ON CB 10
6.74 | AD-27-G-01106 |  |  |  | 2745-NN-RP-026 | RISER/SPOOL LIFTING ANALYSIS REPORT for 16" WI
6.75 | AD-27-G-01107 |  |  |  | 2745-NN-RP-027 | RISER/SPOOL LIFTING ANALYSIS REPORT for 16" OIL
6.76 | AD-27-G-01108 |  |  |  | 2745-NN-RP-028 | RISER/SPOOL LIFTING ANALYSIS REPORT for 18" WI
6.77 | AD-27-G-01109 |  |  |  | 2745-NN-RP-029 | RISER/SPOOL LIFTING ANALYSIS REPORT for 20" OIL
6.78 | AD-27-G-01110 |  |  |  | 2745-NN-RP-030 | RISER/SPOOL LIFTING ANALYSIS REPORT for 24" OIL
6.79 | AD-27-G-01111 |  |  |  | 2745-NN-RP-031 | SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS (TRIP-1)
6.8 | AD-27-G-01112 |  |  |  | 2745-NN-RP-032 | SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS (TRIP-2)
| AD-27-G-02920 |  |  |  | 2745-NN-RP-033 | TOPSIDE PULL IN ANALYSIS
6.238 | AD-27-G-02921 |  |  |  | 2745-NN-RP-034 | CABLE SHORE PULL ANALYSIS
| AD-27-PL-62838 |  |  |  | 2745-NN-RP-035 | NSTALLATION ANALYSIS REPORT FOR CC1, CC2, CC3, CC4, CC5, CC6, CC7 & CC8
6.89 | AD-27-G-01115 |  |  |  | 2745-NN-0001 | START UP HEAD FOR 16" PL
6.9 | AD-27-G-01116 |  |  |  | 2745-NN-0002 | START UP HEAD FOR 18" PL
6.91 | AD-27-G-01117 |  |  |  | 2745-NN-0003 | START UP HEAD FOR 20" PL
6.92 | AD-27-G-01118 |  |  |  | 2745-NN-0004 | START UP HEAD FOR 24" PL
6.93 | AD-27-G-01119 |  |  |  | 2745-NN-0005 | LAYDOWN HEAD FOR 16" PL
6.94 | AD-27-G-01120 |  |  |  | 2745-NN-0006 | LAYDOWN HEAD FOR 18" PL
6.95 | AD-27-G-01121 |  |  |  | 2745-NN-0007 | LAYDOWN HEAD FOR 20" PL
6.96 | AD-27-G-01122 |  |  |  | 2745-NN-0008 | LAYDOWN HEAD FOR 24" PL
6.97 | AD-27-G-02947 |  |  |  | 2745-NN-0009 | TYPICAL BUCKLE DETECTOR DETAIL FOR 16"
6.98 | AD-27-G-02948 |  |  |  | 2745-NN-0010 | TYPICAL BUCKLE DETECTOR DETAIL FOR 18"
6.99 | AD-27-G-02949 |  |  |  | 2745-NN-0011 | TYPICAL BUCKLE DETECTOR DETAIL FOR 20"
6.1 | AD-27-G-02950 |  |  |  | 2745-NN-0012 | TYPICAL BUCKLE DETECTOR DETAIL FOR 24"
6.101 | AD-27-G-02846 |  |  |  | 2745-NN-0013 | TYPICAL LIFTING AND INSTALLATION OF CONCRETE SLEEPER
6.102 | AD-27-G-02847 |  |  |  | 2745-NN-0014 | TYPICAL LIFTING OF CONCRETE MATTRESS
6.103 | AD-27-G-02848 |  |  |  | 2745-NN-0015 | RISER/SPOOL LIFTING FOR 16" PL
6.104 | AD-27-G-02849 |  |  |  | 2745-NN-0016 | RISER/SPOOL LIFTING FOR 18" PL
6.105 | AD-27-G-02850 |  |  |  | 2745-NN-0017 | RISER/SPOOL LIFTING FOR 20" PL
6.106 | AD-27-G-02851 |  |  |  | 2745-NN-0018 | RISER/SPOOL LIFTING FOR 24" PL
6.107 | AD-27-G-02852 |  |  |  | 2745-NN-0019 | TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 16"
6.108 | AD-27-G-02853 |  |  |  | 2745-NN-0020 | TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 18"
6.109 | AD-27-G-02854 |  |  |  | 2745-NN-0021 | TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 20"
6.11 | AD-27-G-02855 |  |  |  | 2745-NN-0022 | TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING OF 24"
6.111 | AD-27-G-02856 |  |  |  | 2745-NN-0023 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-1)
6.112 | AD-27-G-02857 |  |  |  | 2745-NN-0024 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-2)
6.113 | AD-27-G-02858 |  |  |  | 2745-NN-0025 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-3)
6.114 | AD-27-G-02859 |  |  |  | 2745-NN-0026 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-4)
6.115 | AD-27-G-02860 |  |  |  | 2745-NN-0027 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-5)
6.116 | AD-27-G-02861 |  |  |  | 2745-NN-0028 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-6)
6.117 | AD-27-G-02862 |  |  |  | 2745-NN-0029 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-7)
6.118 | AD-27-G-02863 |  |  |  | 2745-NN-0030 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-8)
6.119 | AD-27-G-02864 |  |  |  | 2745-NN-0031 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-9)
6.12 | AD-27-G-02865 |  |  |  | 2745-NN-0032 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-10)
6.121 | AD-27-G-02866 |  |  |  | 2745-NN-0033 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-1)
6.122 | AD-27-G-02867 |  |  |  | 2745-NN-0034 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-2)
6.123 | AD-27-G-02868 |  |  |  | 2745-NN-0035 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-3)
6.124 | AD-27-G-02869 |  |  |  | 2745-NN-0036 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-4)
6.125 | AD-27-G-02870 |  |  |  | 2745-NN-0037 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-5)
6.126 | AD-27-G-02871 |  |  |  | 2745-NN-0038 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-6)
6.127 | AD-27-G-02872 |  |  |  | 2745-NN-0039 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-7)
6.128 | AD-27-G-02873 |  |  |  | 2745-NN-0040 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-8)
6.129 | AD-27-G-02874 |  |  |  | 2745-NN-0041 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-9)
6.13 | AD-27-G-02875 |  |  |  | 2745-NN-0042 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONCRETE SLEEPERS & MATTRESSES (TRIP-10)
6.131 | AD-27-G-02876 |  |  |  | 2745-NN-0043 | TYPICAL LIFITNG AND INSTALLATION OF A-FRAME & QUADRANT
6.132 | AD-27-G-02877 |  |  |  | 2745-NN-0044 | DETAIL OF 16" TEMPORARY PIG LAUNCHER & RECEIVER
6.133 | AD-27-G-02878 |  |  |  | 2745-NN-0045 | DETAIL OF 18" TEMPORARY PIG LAUNCHER & RECEIVER
6.134 | AD-27-G-02879 |  |  |  | 2745-NN-0046 | DETAIL OF 20" TEMPORARY PIG LAUNCHER & RECEIVER
6.135 | AD-27-G-02880 |  |  |  | 2745-NN-0047 | DETAIL OF 24" TEMPORARY PIG LAUNCHER & RECEIVER
6.136 | AD-27-G-02881 |  |  |  | 2745-NN-0048 | LIFTING & INSTALLATION OF RISER CLAMPS & J-TUBE CLAMPS
6.137 | AD-27-PL-625070-SHT-001 |  |  |  | OFO-P2745-SK-001 | PQT TEST PIPE REQUIREMENT
6.138 | AD-27-PL-625071-SHT-001 |  |  |  | OFO-P2745-SK-002 | MARKER AND TRANSITION JOINTS
6.139 | AD-27-PL-625072-SHT-001 |  |  |  | OFO-P2745-SK-003 | GENERAL PIPELAY PROFILE
6.14 | AD-27-PL-625073-SHT-001 |  |  |  | OFO-P2745-SK-004 | TYPICAL ABANDONMENT & RECOVERY / LAYDOWN ARRANGEMENT
6.141 | AD-27-PL-625074-SHT-001 |  |  |  | OFO-P2745-SK-005 | STINGER-9 SECTION-A 80" BUOYANCY TANK
6.142 | AD-27-PL-625075-SHT-001 |  |  |  | OFO-P2745-SK-006 | GENERAL PIPELAY PROFILE-II
6.143 | AD-27-PL-625076-SHT-001 |  |  |  | OFO-P2745-SK-007 | TRANSFER BETWEEN CABLE STORAGE AND CLV CABLE LAYING VESSEL
6.144 | AD-27-PL-625077-SHT-001 |  |  |  | OFO-P2745-SK-008 | HBS START-UP ARRANGEMENT FOR 16" WI
6.145 | AD-27-PL-625078-SHT-001 |  |  |  | OFO-P2745-SK-009 | HBS START-UP ARRANGEMENT FOR 16" OIL
6.146 | AD-27-PL-625079-SHT-001 |  |  |  | OFO-P2745-SK-010 | HBS START-UP ARRANGEMENT FOR 18" WI
6.147 | AD-27-PL-625080-SHT-001 |  |  |  | OFO-P2745-SK-011 | HBS START-UP ARRANGEMENT FOR 20"
6.148 | AD-27-PL-625081-SHT-001 |  |  |  | OFO-P2745-SK-012 | HBS START-UP ARRANGEMENT FOR 24"
6.149 | AD-27-PL-625082-SHT-001 |  |  |  | OFO-P2745-SK-013 | DMA START-UP ARRANGEMENT 16" WI
6.15 | AD-27-PL-625083-SHT-001 |  |  |  | OFO-P2745-SK-014 | DMA START-UP ARRANGEMENT 16" OIL
6.151 | AD-27-PL-625084-SHT-001 |  |  |  | OFO-P2745-SK-015 | DMA START-UP ARRANGEMENT 18"
6.152 | AD-27-PL-625085-SHT-001 |  |  |  | OFO-P2745-SK-016 | DMA START-UP ARRANGEMENT 20"
6.153 | AD-27-PL-625086-SHT-001 |  |  |  | OFO-P2745-SK-017 | DMA START-UP ARRANGEMENT 24"
6.154 | AD-27-PL-625087-SHT-001 |  |  |  | OFO-P2745-SK-018 | TYPICAL LIFTING & HANDLING ARRANGEMENT FOR PIPE JOINTS BY DLB-750 / MANITOWOC CRANE
6.155 | AD-27-PL-625088-SHT-001 |  |  |  | OFO-P2745-SK-019 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT USING DLB-750
6.156 | AD-27-PL-625089-SHT-001 |  |  |  | OFO-P2745-SK-020 | TYPICAL GRAVITY ANCHOR LIFTING ARRANGEMENT USING DLB-1000
6.157 | AD-27-PL-625090-SHT-001 |  |  |  | OFO-P2745-SK-021 | SPREADER BAR - AS-BUILT
6.158 | AD-27-PL-625091-SHT-001 |  |  |  | OFO-P2745-SK-022 | TYPICAL A-FRAME FOR CABLE PULLING
6.159 | AD-27-PL-625092-SHT-001 |  |  |  | OFO-P2745-SK-023 | TYPICAL LIFITNG AND INSTALLATION OF CONCRETE SADDLE
6.16 | AD-27-PL-625093-SHT-001 |  |  |  | OFO-P2745-SK-024 | TEMP. QUADRANT ARRANGMENT FOR J-TUBE
6.161 | AD-27-PL-625094-SHT-001 |  |  |  | OFO-P2745-SK-025 | JUMBO BAG LIFTING FRAME – 12 MT SWL
6.162 | AD-27-PL-625095-SHT-001 |  |  |  | OFO-P2745-SK-026 | TYPICAL LIFTING ARRANGEMENT FOR DRILLING UNIT
6.163 | AD-27-PL-625096-SHT-001 |  |  |  | OFO-P2745-SK-027 | DAVIT LIFTING STROPS DETAILS
6.164 | AD-27-G-02882 |  |  |  | 2745-ZZ-CL-001 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-1
6.165 | AD-27-G-02883 |  |  |  | 2745-ZZ-CL-002 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-2
6.166 | AD-27-G-02884 |  |  |  | 2745-ZZ-CL-003 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-3
6.167 | AD-27-G-02885 |  |  |  | 2745-ZZ-CL-004 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-4
6.168 | AD-27-G-02886 |  |  |  | 2745-ZZ-CL-005 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-5
6.169 | AD-27-G-02887 |  |  |  | 2745-ZZ-CL-006 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-6
6.17 | AD-27-G-02888 |  |  |  | 2745-ZZ-CL-007 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-7
6.171 | AD-27-G-02889 |  |  |  | 2745-ZZ-CL-008 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-8
6.172 | AD-27-G-02890 |  |  |  | 2745-ZZ-CL-009 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-9
6.173 | AD-27-G-02891 |  |  |  | 2745-ZZ-CL-010 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPE ON CARGO BARGE - TRIP-10
6.174 | AD-27-G-02892 |  |  |  | 2745-ZZ-CL-011 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS / MATTRESSES - TRIP-1
6.175 | AD-27-G-02893 |  |  |  | 2745-ZZ-CL-012 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS / MATTRESSES - TRIP-2
6.176 | AD-27-G-02894 |  |  |  | 2745-ZZ-CL-013 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS / MATTRESSES - TRIP-3
6.177 | AD-27-G-02895 |  |  |  | 2745-ZZ-CL-014 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS / MATTRESSES - TRIP-4
6.178 | AD-27-G-02896 |  |  |  | 2745-ZZ-CL-015 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS / MATTRESSES - TRIP-5
6.179 | AD-27-G-02897 |  |  |  | 2745-ZZ-CL-016 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS / MATTRESSES - TRIP-6
6.18 | AD-27-G-02898 |  |  |  | 2745-ZZ-CL-017 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS / MATTRESSES - TRIP-7
6.181 | AD-27-G-02899 |  |  |  | 2745-ZZ-CL-018 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS / MATTRESSES - TRIP-8
6.182 | AD-27-G-02900 |  |  |  | 2745-ZZ-CL-019 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS / MATTRESSES - TRIP-9
6.183 | AD-27-G-02901 |  |  |  | 2745-ZZ-CL-020 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS / MATTRESSES - TRIP-10
6.184 | AD-27-G-02902 |  |  |  | 2745-ZZ-CL-021 | MOORING ANALYSIS DURING LAYING OF 16" WI
6.185 | AD-27-G-02903 |  |  |  | 2745-ZZ-CL-022 | MOORING ANALYSIS DURING LAYING OF 16" OIL
6.186 | AD-27-G-02904 |  |  |  | 2745-ZZ-CL-023 | MOORING ANALYSIS DURING LAYING OF 18"
6.187 | AD-27-G-02905 |  |  |  | 2745-ZZ-CL-024 | MOORING ANALYSIS DURING LAYING OF 20"
6.188 | AD-27-G-02906 |  |  |  | 2745-ZZ-CL-025 | MOORING ANALYSIS DURING LAYING OF 24"
6.189 | AD-27-G-02907 |  |  |  | 2745-ZZ-CL-026 | MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 16" WI
6.19 | AD-27-G-02908 |  |  |  | 2745-ZZ-CL-027 | MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 16" OIL
6.191 | AD-27-G-02909 |  |  |  | 2745-ZZ-CL-028 | MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 18"
6.192 | AD-27-G-02910 |  |  |  | 2745-ZZ-CL-029 | MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 20"
6.193 | AD-27-G-02911 |  |  |  | 2745-ZZ-CL-030 | MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR 24"
6.194 | AD-27-G-02912 |  |  |  | 2745-ZZ-CL-031 | ANCHOR PATTERN OF DLB750 FOR LAYING OF 16" WI
6.195 | AD-27-G-02913 |  |  |  | 2745-ZZ-CL-032 | MOORING ANALYSIS DURING ZWSC BST INSTALLATION
6.196 | AD-27-G-02914 |  |  |  | 2745-ZZ-CL-033 | MOORING ANALYSIS DURING ZCSC BST INSTALLATION
6.197 | AD-27-G-02915 |  |  |  | 2745-ZZ-CL-034 | MOORING ANALYSIS DURING GPF-II BST INSTALLATION
6.198 | AD-27-G-02916 |  |  |  | 2745-ZZ-CL-035 | MOORING ANALYSIS DURING ZCSC PDP JACKET INSTALLATION
6.199 | AD-27-G-02917 |  |  |  | 2745-ZZ-CL-036 | MOORING ANALYSIS OF B-42 DURING FLOATOVER OF GPF-II
6.2 | AD-27-PL-625097-SHT-001 |  |  |  | 2745-AP-0001 | ANCHOR PATTERN DURING JACKET FACE SURVEY
6.201 | AD-27-PL-625098-SHT-001 |  |  |  | 2745-AP-0002 | ANCHOR PATTERN DURING JACKET FACE SURVEY
6.202 | AD-27-PL-625099-SHT-001 |  |  |  | 2745-AP-0003 | ANCHOR PATTERN DURING JACKET FACE SURVEY
6.203 | AD-27-PL-625100-SHT-001 |  |  |  | 2745-AP-0004 | ANCHOR PATTERN DURING JACKET FACE SURVEY
6.204 | AD-27-PL-625101-SHT-001 |  |  |  | 2745-AP-0005 | ANCHOR PATTERN DURING JACKET FACE SURVEY
6.205 | AD-27-PL-625102-SHT-001 |  |  |  | 2745-AP-0006 | ANCHOR PATTERN DURING JACKET FACE SURVEY
6.206 | AD-27-PL-625103-SHT-001 |  |  |  | 2745-AP-0007 | ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY OF 16" WI
6.207 | AD-27-PL-625104-SHT-001 |  |  |  | 2745-AP-0008 | ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY OF 16" OIL
6.208 | AD-27-PL-625105-SHT-001 |  |  |  | 2745-AP-0009 | ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY OF 18" WI
6.209 | AD-27-PL-625106-SHT-001 |  |  |  | 2745-AP-0010 | ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY OF 20"
6.21 | AD-27-PL-625107-SHT-001 |  |  |  | 2745-AP-0011 | ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY OF 24"
6.211 | AD-27-PL-625108-SHT-001 |  |  |  | 2745-AP-0012 | ANCHOR PATTERN FOR BARGE DLB-1000 DURING 16" WI RISER INSTALLATION
6.212 | AD-27-PL-625109-SHT-001 |  |  |  | 2745-AP-0013 | ANCHOR PATTERN FOR BARGE DLB-1000 DURING 16" OIL RISER INSTALLATION
6.213 | AD-27-PL-625110-SHT-001 |  |  |  | 2745-AP-0014 | ANCHOR PATTERN FOR BARGE DLB-1000 DURING 18" RISER INSTALLATION
6.214 | AD-27-PL-625111-SHT-001 |  |  |  | 2745-AP-0015 | ANCHOR PATTERN FOR BARGE DLB-1000 DURING 20" RISER INSTALLATION
6.215 | AD-27-PL-625112-SHT-001 |  |  |  | 2745-AP-0016 | ANCHOR PATTERN FOR BARGE DLB-1000 DURING 24" WI RISER INSTALLATION
6.22 | AD-27-PL-625117-SHT-001 |  |  |  | 2745-AP-0017 | SET- UP DRAWING FOR WHT-3 TOPSIDE INSTALLATION
6.221 | AD-27-PL-625118-SHT-001 |  |  |  | 2745-AP-0018 | SET- UP DRAWING FOR WHT-2 TOPSIDE INSTALLATION
6.222 | AD-27-PL-625119-SHT-001 |  |  |  | 2745-AP-0019 | SET- UP DRAWING FOR ZWSC PDP TOPSIDE INSTALLATION
6.223 | AD-27-PL-625120-SHT-001 |  |  |  | 2745-AP-0020 | SET- UP DRAWING FOR ZCSC PDP TOPSIDE INSTALLATION
6.224 | AD-27-PL-625121-SHT-001 |  |  |  | 2745-AP-0021 | SET- UP DRAWING FOR ZWSC PDP JACKET INSTALLATION
6.225 | AD-27-PL-625122-SHT-001 |  |  |  | 2745-AP-0022 | SET- UP DRAWING FOR GPF-II JACKET INSTALLATION
6.216 | AD-27-PL-625113-SHT-001 |  |  |  | 2745-AP-0023 | ANCHOR PATTERN FOR BARGE DLB-1000 DURING ZWSC BST INSTALLATION
6.217 | AD-27-PL-625114-SHT-001 |  |  |  | 2745-AP-0024 | ANCHOR PATTERN FOR BARGE DLB-1000 DURING ZCSC BST INSTALLATION
6.218 | AD-27-PL-625115-SHT-001 |  |  |  | 2745-AP-0025 | ANCHOR PATTERN FOR BARGE DLB-1000 DURING GPF-II BST INSTALLATION
6.219 | AD-27-PL-625116-SHT-001 |  |  |  | 2745-AP-0026 | ANCHOR PATTERN FOR ZCSC PDP JACKET INSTALLATION
6.226 | AD-27-PL-625123-SHT-001 |  |  |  | 2745-AP-0027 | SET- UP DRAWING FOR WHT-3 TOPSIDE INSTALLATION
6.227 | AD-27-PL-625124-SHT-001 |  |  |  | 2745-AP-0028 | SET- UP DRAWING FOR WHT-2 TOPSIDE INSTALLATION
6.228 | AD-27-PL-625125-SHT-001 |  |  |  | 2745-AP-0029 | SET- UP DRAWING FOR ZWSC PDP TOPSIDE INSTALLATION
6.229 | AD-27-PL-625126-SHT-001 |  |  |  | 2745-AP-0030 | SET- UP DRAWING FOR ZSCSC PDP TOPSIDE INSTALLATION
6.23 | AD-27-PL-625127-SHT-001 |  |  |  | 2745-AP-0031 | SET- UP DRAWING FOR GPF-II JACKET INSTALLATION
6.231 | AD-27-PL-625128-SHT-001 |  |  |  | 2745-AP-0032 | SET- UP DRAWING FOR ZWSC PDP JACKET INSTALLATION
6.232 | AD-27-PL-625129-SHT-001 |  |  |  | 2745-AP-0033 | SET- UP DRAWING FOR ZWSC PDP BRIDGE INSTALLATION
6.233 | AD-27-PL-625130-SHT-001 |  |  |  | 2745-AP-0034 | SET- UP DRAWING FOR ZCSC PDP BRIDGE INSTALLATION
6.234 | AD-27-PL-625131-SHT-001 |  |  |  | 2745-AP-0035 | SET- UP DRAWING FOR GPF-II BRIDGES INSTALLATION
6.235 | AD-27-PL-625132-SHT-001 |  |  |  | 2745-AP-0036 | SET- UP DRAWING FOR FLARE SUPPORT INSTALLATION
6.236 | AD-27-PL-625133-SHT-001 |  |  |  | 2745-AP-0037 | ANCHOR PATTERN OF B-42 DURING GPF-II FLOATOVER
7 | COMMISSIONING
7.1 | AD-27-G-02922 |  |  |  | 2745-PP-CM-001 | PRECOMMISSIONING AND COMMISSIONING PROCEDURE
7.2 | AD-27-G-02923 |  |  |  | 2745-PP-CM-002 | SYSTEM/SUBSYSTEM LIST
7.3 | AD-27-G-02924 |  |  |  | 2745-PP-CM-003 | PUNCHLIST PROCEDURE
7.4 | AD-27-G-02925 |  |  |  | 2745-PP-CM-004 | PERMIT TO WORK PROCEDURE
7.5 | AD-27-G-02926 |  |  |  | 2745-PP-CM-005 | LIST OF OPERATIONAL TEST PROCEDURES
7.6 | AD-27-G-02927 |  |  |  | 2745-PP-CM-006 | PRE-COMMISSIONING / COMMISSIONING TEST RECORDS AND RESPONSIBILITY MATRIX
7.7 | AD-27-G-02928 |  |  |  | 2745-PP-CM-007 | COMPLETION MANAGEMENT SYSTEM PROCEDURE
7.8 | AD-27-G-02929 |  |  |  | 2745-PP-CM-008 | FIRST FILL INVENTORY, CONSUMPTION AND TOP UP SCHEDULE (INCLUDING CHEMICALS, HYDRAULIC OIL)
7.9 | AD-27-G-02930 |  |  |  | 2745-PP-CM-009 | N2-HE LEAK TEST PROCEDURE
7.1 | AD-27-G-02931 |  |  |  | 2745-PP-CM-010 | HANDOVER PROCEDURE
7.11 | AD-27-G-02932 |  |  |  | 2745-PP-CM-011 | PROJECT PRESERVATION PROCEDURE
7.12 | AD-27-G-02933 |  |  |  | 2745-PP-CM-012 | PERFORMANCE TEST PROCEDURE
7.13 | AD-27-G-02934 |  |  |  | 2745-PP-CM-013 | START UP PROCEDURE
7.14 | AD-27-G-02935 |  |  |  | 2745-PP-CM-014 | VENDOR MOBILIZATION PROCEDURE
7.15 | AD-27-G-02936 |  |  |  | 2745-PP-CM-015 | TRAINING PROCEDURE AND SCHEDULE
| AD-27-G-02937 |  |  |  | 2745-PP-CM-016 | SYSTEM / SUB-SYSTEM LIST & MARK-UP FOR WHT-3 AREA 849
| AD-27-G-02938 |  |  |  | 2745-PP-CM-017 | SYSTEM / SUB-SYSTEM LIST & MARK-UP FOR GPF-II AREA-845
| AD-27-G-02939 |  |  |  | 2745-PP-CM-018 | SYSTEM / SUB-SYSTEM LIST & MARK-UP FOR PDP PLATFORM AREA ZWSC
| AD-27-G-02940 |  |  |  | 2745-PP-CM-019 | SYSTEM / SUB-SYSTEM LIST & MARK-UP FOR ZWSC MODIFICATIONS
| AD-27-G-02941 |  |  |  | 2745-PP-CM-020 | SYSTEM / SUB-SYSTEM LIST & MARK-UP FOR PDP PLATFORM AREA ZCSC
| AD-27-G-02942 |  |  |  | 2745-PP-CM-021 | SYSTEM / SUB-SYSTEM LIST & MARK-UP FOR ZCC MODIFICATIONS
| AD-27-G-02943 |  |  |  | 2745-PP-CM-022 | START UP & PERFORMANCE TEST PROCEDURE FOR ZWSC-PDP
| AD-27-G-02944 |  |  |  | 2745-PP-CM-023 | START UP & PERFORMANCE TEST PROCEDURE FOR ZCSC-PDP

## PIPELINE & CABLE doc (hidden)
|  |  | EPC FOR DALMA GAS DEVELOPMENT PROJECT PACKAGE-A (OFFSHORE FACILITIES) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  |  | NPCC PROJECT NO.8405 | [10 empty] | REVISION : |  |  |  | 0
|  |  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 44363
SR. NO. | DESCRIPTION | COMPANY DOCUMENT NUMBER | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | PIPE STACKING ANALYSIS REPORT | CF0000-32-REP-0001 | 8405-NN-RP-001 | A01 | 1 | 2023-05-02
2 | PIPELAY ANALYSIS REPORT FOR PL-1 ( 16" GAS-CONDENSTAE) FROM SATAH WHP-10 TO ARZANAH ISLAND | AZ0091-32-REP-0002 | 8405-NN-RP-002 | A01 | 1 | 2023-04-25
3 | PIPELAY ANALYSIS REPORT FOR PL-2 ( 14" GAS-CONDENSTAE) FROM HD-3 TO HD WHP-T4 | HD0201-32-REP-0003 | 8405-NN-RP-003 | A01 | 1 | 2023-04-28
4 | PIPELAY ANALYSIS REPORT FOR PL-3 ( 18" GAS-CONDENSTAE) FROM HD WHP-T4 TO ARZANAH ISLAND | AZ0091-32-REP-0004 | 8405-NN-RP-004 | A01 | 1 | 2023-05-04
5 | PIPELAY ANALYSIS REPORT FOR PL-4 ( 18" GAS-CONDENSTAE) FROM WHP BH-3 SATAH WHP-10 TO ARZANAH ISLAND | AZ0091-32-REP-0005 | 8405-NN-RP-005 | A01 | 1 | 2023-05-04
6 | PIPELAY ANALYSIS REPORT FOR PL-5 ( 24" EXPORT GAS ) FROM ARZANAH ISLAND TO IGD-E(AT KP-38) | KP3801-34-REP-0006 | 8405-NN-RP-006 | A01 | 1 | 2023-05-06
7 | PIPELAY ANALYSIS REPORT FOR PL-6 ( 6" EXPORT-CONDENSTAE & FOC PIGGY BACKED) FROM ARZANAH ISLAND TO ZIRKU ISLAND | AZ0091-32-REP-0007 | 8405-NN-RP-007 | A01 | 1 | 2023-05-07
8 | SHORE PULL ANALYSES REPORT AT ARZANAH EAST | AZ0091-32-REP-0008 | 8405-NN-RP-008 | A01 | 1 | 2023-04-12
9 | SHORE PULL ANALYSES REPORT AT ARZANAH SOUTH | AZ0091-32-REP-0009 | 8405-NN-RP-009 | A01 | 1 | 2023-04-13
10 | SHORE PULL ANALYSIS REPORT AT ZIRKU ISLAND | AZ0091-32-REP-0010 | 8405-NN-RP-010 | A01 | 1 | 2023-04-14
11 | MIDLINE TIE-IN ANALYSIS REPORT | CF0000-32-REP-0011 | 8405-NN-RP-011 | A01 | 1 | 2023-05-15
12 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE | CF0000-32-REP-0012 | 8405-NN-RP-012 | A01 | 1 | 2023-04-17
13 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE | Duplicate | 8405-NN-RP-013 | A01 | 1 | 2023-04-18
14 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE |  | 8405-NN-RP-014 | A01 | 1 | 2023-04-19
15 | SEAFASTENING DESIGN REPORT FOR TRANSPORTATION OF CC PIPES ON CARGO BARGE |  | 8405-NN-RP-015 | A01 | 1 | 2023-04-20
16 | SEAFASTENING DESGIN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS |  | 8405-NN-RP-016 | A01 | 1 | 2023-05-02
17 | SEAFASTENING DESGIN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS |  | 8405-NN-RP-017 | A01 | 1 | 2023-05-02
18 | SEAFASTENING DESGIN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS |  | 8405-NN-RP-018 | A01 | 1 | 2023-05-02
19 | SEAFASTENING DESGIN REPORT FOR TRANSPORTATION OF CONCRETE SLEEPERS |  | 8405-NN-RP-019 | A01 | 1 | 2023-05-02
20 | SEAFASTENING DESGIN REPORT FOR TRANSPORTATION OF CONCRETE MATTRESSES |  | 8405-NN-RP-020 | A01 | 1 | 2023-05-05
21 | SEAFASTENING DESGIN REPORT FOR TRANSPORTATION OF CONCRETE MATTRESSES |  | 8405-NN-RP-021 | A01 | 1 | 2023-05-05
22 | RISER/SPOOL LIFTING ANALYSIS REPORT AT WHP BH3 | BH0101-32-REP-0013 | 8405-NN-RP-022 | A01 | 1 | 2023-06-20
23 | RISER/SPOOL LIFTING ANALYSIS REPORT AT SATAH WHP-10 | ST0101-32-REP-0014 | 8405-NN-RP-023 | A01 | 1 | 2023-05-12
24 | RISER/SPOOL LIFTING ANALYSIS REPORT AT IGD-E | KP3801-32-REP-0015 | 8405-NN-RP-024 | A01 | 1 | 2023-05-20
25 | RISER/SPOOL LIFTING ANALYSIS REPORT AT WHP HD3 | BH0101-32-REP-0016 | 8405-NN-RP-025 | A01 | 1 | 2023-06-20
26 | RISER/SPOOL LIFTING ANALYSIS REPORT AT HD WHP-T4 | BH0201-32-REP-0017 | 8405-NN-RP-026 | A01 | 1 | 2023-06-20
27 | SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS (TRIP-1) | CF0000-32-REP-0018 | 8405-NN-RP-027 | A01 | 1 | 2023-06-20
28 | SEAFASTENING ANALYSIS REPORT FOR TRANSPORTATION OF SUBSEA SPOOLS (TRIP-2) | CF0000-32-REP-0019 | 8405-NN-RP-028 | A01 | 1 | 2023-06-12
29 | INSTALLATION ANALYSIS REPORT FOR CC-1( COMPOSITE CABLES FROM ARZANAH ISLAND TO IGD-E) | KP3801-32-REP-0020 | 8405-NN-RP-029 | A01 | 1 | 2023-05-22
30 | Composite Cable Installation analysis report | CF0000-32-REP-0021 | 8405-NN-RP-30 | A01 | 1 | 2023-06-20
31 | Umbilical Installation analysis report | CF0000-32-REP-0022 | 8405-NN-RP-31 | A01 | 1

## Naval & Marine doc (hidden)
|  |  | EPC FOR DALMA GAS DEVELOPMENT PROJECT PACKAGE-A (OFFSHORE FACILITIES) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  |  | NPCC PROJECT NO.8405 | [10 empty] | REVISION : |  |  |  | 0
|  |  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 44277
SR. NO. | DESCRIPTION | COMPANY DOCUMENT NUMBER | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPEPIPE AT CARGO BAGE | CF0000-32-REP-0021 | 8405-ZZ-CL-001 | A01 | 1 | 2023-05-03
2 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPEPIPE AT CARGO BAGE | Duplicate | 8405-ZZ-CL-002 | A01 | 1 | 2023-05-03
3 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPEPIPE AT CARGO BAGE |  | 8405-ZZ-CL-003 | A01 | 1 | 2023-05-03
4 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE COATED PIPEPIPE AT CARGO BAGE |  | 8405-ZZ-CL-004 | A01 | 1 | 2023-05-03
5 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS AT CARGO BAGE |  | 8405-ZZ-CL-005 | A01 | 1 | 2023-05-14
6 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE MATTRESS AT CARGO BAGE | CF0000-32-REP-0022 | 8405-ZZ-CL-006 | A01 | 1 | 2023-05-14
7 | STABILITY ANALYSIS DURING TRANSPORTATION OF CONCRETE SLEEPERS AT CARGO BAGE | Duplicate | 8405-ZZ-CL-007 | A01 | 1 | 2023-05-14
8 | MOORING ANALYSIS DURING LAYING PL-1 ( 16" GAS-CONDENSTAE) FROM SATAH WHP-10 TO ARZANAH ISLAND | AZ0091-32-REP-0023 | 8405-ZZ-CL-008 | A01 | 1 | 2023-05-15
9 | MOORING ANALYSIS DURING LAYING PL-2 ( 14" GAS-CONDENSTAE) FROM HD-3 TO HD WHP-T4 | HD0201-32-REP-0024 | 8405-ZZ-CL-009 | A01 | 1 | 2023-05-16
10 | MOORING ANALYSIS DURING LAYING PL-3 ( 18" GAS-CONDENSTAE) FROM HD WHP-T4 TO ARZANAH ISLAND | AZ0091-32-REP-0025 | 8405-ZZ-CL-010 | A01 | 1 | 2023-05-17
11 | MOORING ANALYSIS DURING LAYING PL-4 ( 18" GAS-CONDENSTAE) FROM WHP BH-3 SATAH WHP-10 TO ARZANAH ISLAND | AZ0091-32-REP-0026 | 8405-ZZ-CL-011 | A01 | 1 | 2023-05-18
12 | MOORING ANALYSIS DURING LAYING PL-5 ( 24" EXPORT GAS ) FROM ARZANAH ISLAND TO IGD-E(AT KP-38) | KP3801-32-REP-0027 | 8405-ZZ-CL-012 | A01 | 1 | 2023-05-19
13 | MOORING ANALYSIS DURING SHORE PULL AT ARZANAH EAST | AZ0091-32-REP-0028 | 8405-ZZ-CL-013 | A01 | 1 | 2023-05-14
14 | MOORING ANALYSIS DURING SHORE PULL AT ARZANAH SOUTH. | AZ0091-32-REP-0029 | 8405-ZZ-CL-014 | A01 | 1 | 2023-04-10
15 | MOORING ANALYSIS DURING SHORE PULL AT ZIRKU ISLAND | AZ0091-32-REP-0030 | 8405-ZZ-CL-015 | A01 | 1 | 2023-04-10
16 | MOORING ANALYSIS DURING MIDLINE TIE-IN | CF0000-32-REP-0031 | 8405-ZZ-CL-016 | A01 | 1 | 2023-04-10
| MOORING ANALYSIS DURING MIDLINE TIE-IN | CF0000-32-REP-0032 | 8405-ZZ-CL-017 | A01 | 1 | 2023-06-26
| MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR PL1 | CF0000-32-REP-0033 | 8405-ZZ-CL-018 | A01 | 1 | 2023-06-08
| MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR PL2 | CF0000-32-REP-0034 | 8405-ZZ-CL-019 | A01 | 1 | 2023-06-08
| MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR PL3 | CF0000-32-REP-0035 | 8405-ZZ-CL-020 | A01 | 1 | 2023-06-08
| MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR PL4 | CF0000-32-REP-0036 | 8405-ZZ-CL-021 | A01 | 1 | 2023-06-08
| MOORING ANALYSIS DURING LATERAL SHIFTING & STALK-ON RISER INSTALLATION FOR PL5 | CF0000-32-REP-0037 | 8405-ZZ-CL-022 | A01 | 1 | 2023-06-08

## DRAWINGS (hidden)
|  |  | EPC FOR DALMA GAS DEVELOPMENT PROJECT PACKAGE-A (OFFSHORE FACILITIES) | [10 empty] | NPCC DOC. No.:
CLIENT DOC. No. :
|  |  | NPCC PROJECT NO.8405 | [10 empty] | REVISION : |  |  |  | 0
|  |  | OFFSHORE CONSTRUCTION ENGINEERING DOCUMENTS (PIPELINE & CABLE) | [10 empty] | DATE : |  |  |  | 44277
SR. NO. | DESCRIPTION | COMPANY DOCUMENT NUMBER | NPCC DOCUMENT NUMBER | REV. | CLASS | SUBMISSION PLANNED DATE | NPCC |  |  |  | CLIENT |  |  | GMC |  |  |  |  | REMARKS
[7 empty] | SUBMISSION STATUS |  |  |  | APPROVAL STATUS |  |  | SUBMISSION STATUS |  | APPROVAL STATUS
[7 empty] | CSE TO PMT |  | PMT TO CLIENT |  | FROM CLIENT |  |  | PMT TO GMC |  | STATUS FROM GMC
[7 empty] | DATE | REF | DATE | REF | DATE | REF | CODE | DATE | REF | DATE | REF | CODE
1 | SHOREPULL HEAD FOR PL-1( 16" GAS-CONDENSTAE FROM SATAH WHP-10 TO ARZANAH ISLAND ) | AZ0091-32-LAY-0001 | 8405-NN-0001 | A01 | 2 | 2023-04-12
2 | SHOREPULL HEAD FOR PL-4 ( 18" GAS-CONDENSTAE) FROM WHP BH-3 SATAH WHP-10 TO ARZANAH ISLAND | AZ0091-32-LAY-0002 | 8405-NN-0002 | A01 | 2 | 2023-04-13
3 | SHOREPULL HEAD FOR PL-6 ( ( 6" EXPORT-CONDENSTAE & FOC PIGGY BACKED) | CF0000-32-LAY-0003 | 8405-NN-0003 | A01 | 2 | 2023-04-14
4 | SHOREPULL HEAD FOR PL-5 ( 24" EXPORT GAS ) FROM ARZANAH ISLAND TO IGD-E(AT KP-38) | KP3801-32-LAY-0004 | 8405-NN-0004 | A01 | 2 | 2023-04-15
5 | SHOREPULL HEAD FOR PL-3 ( 18" GAS-CONDENSTAE) FROM HD WHP-T4 TO ARZANAH ISLAND | AZ0091-32-LAY-0005 | 8405-NN-0005 | A01 | 2 | 2023-04-16
6 | SHORE PULL HEAD FOR 24" CONDUIT | CF0000-32-LAY-0006 | 8405-NN-0006 | A01 | 2 | 2023-04-17
7 | SHORE PULL HEAD FOR 16" CONDUIT | CF0000-32-LAY-0007 | 8405-NN-0007 | A01 | 2 | 2023-04-18
8 | LAYDOWN HEAD FOR PL-1 ( 16" GAS-CONDENSTAE) | CF0000-32-LAY-0008 | 8405-NN-0008 | A01 | 2 | 2023-04-12
9 | LAYDOWN HEAD FOR PL-2 ( 14" GAS-CONDENSTAE) FROM HD-3 TO HD WHP-T4 | HD0201-32-LAY-0009 | 8405-NN-0009 | A01 | 2 | 2023-04-13
10 | LAYDOWN HEAD FOR PL-3 ( 18" GAS-CONDENSTAE) FROM HD WHP-T4 TO ARZANAH ISLAND | AZ0091-32-LAY-0010 | 8405-NN-0010 | A01 | 2 | 2023-04-14
11 | LAYDOWN HEAD FOR PL-4 ( 18" GAS-CONDENSTAE) FROM WHP BH-3 SATAH WHP-10 TO ARZANAH ISLAND | AZ0091-32-LAY-0011 | 8405-NN-0011 | A01 | 2 | 2023-04-15
12 | LAYDOWN HEAD FOR PL-5 ( 24" EXPORT GAS ) FROM ARZANAH ISLAND TO IGD-E(AT KP-38) | KP3801-32-LAY-0012 | 8405-NN-0012 | A01 | 2 | 2023-04-16
13 | LAYDOWN HEAD FOR FOR PL-6 ( 6" EXPORT-CONDENSTAE & FOC PIGGY BACKED) FROM ARZANAH ISLAND TO ZIRKU ISLAND | AZ0091-32-LAY-0013 | 8405-NN-0013 | A01 | 2 | 2023-04-17
14 | LAYDOWN HEAD FOR 24" CONDUIT | CF0000-32-LAY-0014 | 8405-NN-0014 | A01 | 2 | 2023-04-18
15 | LAYDOWN HEAD FOR 16" CONDUIT | CF0000-32-LAY-0015 | 8405-NN-0015 | A01 | 2 | 2023-04-15
16 | TYPICAL BUCKLE DETECTOR DETAIL FOR PL-1( 16" GAS-CONDENSTAE FROM SATAH WHP-10 TO ARZANAH ISLAND ) | AZ0091-32-LAY-0016 | 8405-NN-0016 | A01 | 2 | 2023-04-30
17 | TYPICAL BUCKLE DETECTOR DETAIL FORPL-2 ( 14" GAS-CONDENSTAE) FROM HD-3 TO HD WHP-T4 | HD0201-32-LAY-0017 | 8405-NN-0017 | A01 | 2 | 2023-05-01
18 | TYPICAL BUCKLE DETECTOR DETAILPL-3 ( 18" GAS-CONDENSTAE) FROM HD WHP-T4 TO ARZANAH ISLAND | AZ0091-32-LAY-0018 | 8405-NN-0018 | A01 | 2 | 2023-05-02
19 | TYPICAL BUCKLE DETECTOR DETAIL FOR PL-4 ( 18" GAS-CONDENSTAE) FROM WHP BH-3 SATAH WHP-10 TO ARZANAH ISLAND | AZ0091-32-LAY-0019 | 8405-NN-0019 | A01 | 2 | 2023-05-03
20 | TYPICAL BUCKLE DETECTOR DETAIL FOR PL-5 ( 24" EXPORT GAS ) FROM ARZANAH ISLAND TO IGD-E(AT KP-38) | KP3801-32-LAY-0020 | 8405-NN-0020 | A01 | 2 | 2023-05-04
21 | TYPICAL BUCKLE DETECTOR DETAILPL-6 ( 6" EXPORT-CONDENSTAE & FOC PIGGY BACKED) FROM ARZANAH ISLAND TO ZIRKU ISLAND | AZ0091-32-LAY-0021 | 8405-NN-0021 | A01 | 2 | 2023-05-05
22 | TYPICAL LIFTING OF CONCRETE SLEEPERS | CF0000-32-LAY-0022 | 8405-NN-0022 | A01 | 2 | 2023-05-07
23 | TYPICAL LIFTING OF CONCRETE SLEEPERS | Duplicate | 8405-NN-0023 | A01 | 2 | 2023-05-08
24 | RISER/SPOOL LIFTING AT SATAH WHP-10 | ST0101-32-LAY-0023 | 8405-NN-0024 | A01 | 1 | 2023-05-28
25 | RISER/SPOOL LIFTING AT BU HASSER WHP BH3 | BH0101-32-LAY-0024 | 8405-NN-0025 | A01 | 1 | 2023-05-29
26 | RISER/SPOOL LIFTING AT IGD-E | KP3801-32-LAY-0025 | 8405-NN-0026 | A01 | 1 | 2023-06-02
27 | RISER/SPOOL LIFTING AT HD-3 | HD0101-32-LAY-0026 | 8405-NN-0027 | A01 | 1 | 2023-06-03
28 | RISER/SPOOL LIFITNG AT HD-WHP T4 | HD0201-32-LAY-0027 | 8405-NN-0028 | A01 | 1 | 2023-06-05
29 | TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING AT SATAH WHP-10 | ST0101-32-LAY-0028 | 8405-NN-0029 | A01 | 2 | 2023-06-07
30 | TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING AT BU HASSER WHP BH3 | BH0101-32-LAY-0029 | 8405-NN-0030 | A01 | 2 | 2023-06-08
31 | TEMPORARY KNEE BRACE DETAILS FORRISER/SPOOL LIFTING AT IGD-E | KP3801-32-LAY-0030 | 8405-NN-0031 | A01 | 2 | 2023-06-09
32 | TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFTING AT HD-3 | HD0101-32-LAY-0031 | 8405-NN-0032 | A01 | 2 | 2023-06-10
33 | TEMPORARY KNEE BRACE DETAILS FOR RISER/SPOOL LIFITNG AT HD-WHP T4 | HD0201-32-LAY-0032 | 8405-NN-0033 | A01 | 2 | 2023-06-11
34 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-1) | CF0000-32-LAY-0033 | 8405-NN-0034 | A01 | 1 | 2023-04-17
35 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-2) | CF0000-32-LAY-0034 | 8405-NN-0035 | A01 | 1 | 2023-04-18
36 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-3) | CF0000-32-LAY-0035 | 8405-NN-0036 | A01 | 1 | 2023-04-19
37 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-4) | CF0000-32-LAY-0036 | 8405-NN-0037 | A01 | 1 | 2023-04-20
38 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-5) | CF0000-32-LAY-0037 | 8405-NN-0038 | A01 | 1 | 2023-04-30
39 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-6) | CF0000-32-LAY-0038 | 8405-NN-0039 | A01 | 1 | 2023-05-03
40 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-7) | CF0000-32-LAY-0039 | 8405-NN-0040 | A01 | 1 | 2023-05-06
41 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-8) | CF0000-32-LAY-0040 | 8405-NN-0041 | A01 | 1 | 2023-05-09
42 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-9) | CF0000-32-LAY-0041 | 8405-NN-0042 | A01 | 1 | 2023-05-12
43 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-10) | CF0000-32-LAY-0042 | 8405-NN-0043 | A01 | 1 | 2023-05-15
44 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-11) | CF0000-32-LAY-0043 | 8405-NN-0044 | A01 | 1 | 2023-05-18
45 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-12) | CF0000-32-LAY-0044 | 8405-NN-0045 | A01 | 1 | 2023-05-21
46 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-13) | CF0000-32-LAY-0045 | 8405-NN-0046 | A01 | 1 | 2023-05-24
47 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-14) | CF0000-32-LAY-0046 | 8405-NN-0047 | A01 | 1 | 2023-05-27
48 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-15) | CF0000-32-LAY-0047 | 8405-NN-0048 | A01 | 1 | 2023-05-30
49 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-16) | CF0000-32-LAY-0048 | 8405-NN-0049 | A01 | 1 | 2023-06-02
50 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-17) | CF0000-32-LAY-0049 | 8405-NN-0050 | A01 | 1 | 2023-06-05
51 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-18) | CF0000-32-LAY-0050 | 8405-NN-0051 | A01 | 1 | 2023-06-08
52 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-19) | CF0000-32-LAY-0051 | 8405-NN-0052 | A01 | 1 | 2023-06-11
53 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-20) | CF0000-32-LAY-0052 | 8405-NN-0053 | A01 | 1 | 2023-06-14
54 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-21) | CF0000-32-LAY-0053 | 8405-NN-0054 | A01 | 1 | 2023-06-17
55 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-22) | CF0000-32-LAY-0054 | 8405-NN-0055 | A01 | 1 | 2023-06-20
56 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-23) | CF0000-32-LAY-0055 | 8405-NN-0056 | A01 | 1 | 2023-06-23
57 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-24) | CF0000-32-LAY-0056 | 8405-NN-0057 | A01 | 1 | 2023-06-26
58 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-25) | CF0000-32-LAY-0057 | 8405-NN-0058 | A01 | 1 | 2023-06-29
59 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-26) | CF0000-32-LAY-0058 | 8405-NN-0059 | A01 | 1 | 2023-07-02
60 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-27) | CF0000-32-LAY-0059 | 8405-NN-0060 | A01 | 1 | 2023-07-05
61 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-28) | CF0000-32-LAY-0060 | 8405-NN-0061 | A01 | 1 | 2023-07-08
62 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-29) | CF0000-32-LAY-0061 | 8405-NN-0062 | A01 | 1 | 2023-07-11
63 | LOADING ARRANGEMENT & SEAFASTENING DETAILS OF CC PIPES (TRIP-30) | CF0000-32-LAY-0062 | 8405-NN-0063 | A01 | 1 | 2023-07-14
64 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONSRETE SLEEPERS(TRIP-1) | CF0000-32-LAY-0063 | 8405-NN-0064 | A01 | 1 | 2023-05-02
65 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONSRETE SLEEPERS(TRIP-2) | CF0000-32-LAY-0064 | 8405-NN-0065 | A01 | 1 | 2023-05-05
66 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONSRETE SLEEPERS(TRIP-3) | CF0000-32-LAY-0065 | 8405-NN-0066 | A01 | 1 | 2023-05-08
67 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONSRETE SLEEPERS(TRIP-4) | CF0000-32-LAY-0066 | 8405-NN-0067 | A01 | 1 | 2023-05-11
68 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONSRETE SLEEPERS(TRIP-5) | CF0000-32-LAY-0067 | 8405-NN-0068 | A01 | 1 | 2023-05-14
69 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONSRETE SLEEPERS(TRIP-6) | CF0000-32-LAY-0068 | 8405-NN-0069 | A01 | 1 | 2023-05-17
70 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONSRETE SLEEPERS(TRIP-7) | CF0000-32-LAY-0069 | 8405-NN-0070 | A01 | 1 | 2023-05-20
71 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONSRETE SLEEPERS(TRIP-8) | CF0000-32-LAY-0070 | 8405-NN-0071 | A01 | 1 | 2023-05-23
72 | LOADING ARRANGMENT & SEAFASTENING DETAILS OF CONSRETE SLEEPERS(TRIP-9) | CF0000-32-LAY-0071 | 8405-NN-0072 | A01 | 1 | 2023-05-26
73 | FLANGE PROTECTOR DETAILS FOR 16" CONDUIT | CF0000-32-LAY-0072 | 8405-NN-0073 | A01 | 3 | 2023-05-20
74 | FLANGE PROTECTOR DETAILS FOR 24" CONDUIT (TYPE-1) | CF0000-32-LAY-0073 | 8405-NN-0074 | A01 | 3 | 2023-05-20
75 | FLANGE PROTECTOR DETAILS FOR 24" CONDUIT (TYPE-2) | CF0000-32-LAY-0074 | 8405-NN-0075 | A01 | 1 | 2023-06-10
76 | START UP HEAD DETAILS PL-2 (12" GAS-CONDENSATE) FROM HD-3 TO HD WHP-T4 | HD0201-32-LAY-0075 | 8405-NN-0076 | A01 | 1 | 2023-06-11

## Anchor Pattern (hidden)
ABU DHABI NATIONAL OIL COMPANY (ADNOC) EPC FOR DALMA GAS DEVELOPMENT PROJECT CONTRACT AGREEMENT NO: 6000001102(A)
COMPANY Project No. | P4331432 | ANCHOR PATTERNS REGISTER |  | Rev. 00
CONTRACTOR Project No. | 8405 |  |  | 2025-07-01 09:53
Sl. No. | Contractor Document No. | COMPANY Document No. | Title / Description | Vessel Name | Remarks | REV. | CLASS | SUBMISSION PLANNED DATE
1 | 8405-AP-0201 | CF4901-34-LAY-0001 | MUTAWA-101 ANCHOR PATTERN DURING JACKET FACE SURVEY AT WHP-10 | MUTAWA-101 | ISSUED | A01 | 1 | 2023-08-30
2 | 8405-AP-0202 | BH4900-34-LAY-0002 | MUTAWA-101 ANCHOR PATTERN DURING JACKET FACE SURVEY AT WHP-BH-3 | MUTAWA-101 | ISSUED | A01 | 1 | 2023-08-30
3 | 8405-AP-0203 | HD4900-34-LAY-0003 | MUTAWA-101 ANCHOR PATTERN DURING JACKET FACE SURVEY AT HD-3 | MUTAWA-101 | ISSUED | A01 | 1 | 2023-08-30
4 | 8405-AP-0204 | CF0000-34-LAY-0004 | MUTAWA-101 ANCHOR PATTERN DURING JACKET FACE SURVEY AT HD-WHP-T4 (EAST SIDE) | MUTAWA-101 | ISSUED | A01 | 1 | 2023-08-30
5 | 8405-AP-0205 | CF0000-34-LAY-0005 | MUTAWA-101 ANCHOR PATTERN DURING JACKET FACE SURVEY AT HD-WHP-T4 (WEST SIDE) | MUTAWA-101 | ISSUED | A01 | 1 | 2023-08-30
6 | 8405-AP-0206 | KP0000-34-LAY-0006 | MUTAWA-101 ANCHOR PATTERN DURING JACKET FACE SURVEY AT IGD-E | MUTAWA-101 | ISSUED | A01 | 1 | 2023-06-30
7 | 8405-AP-0001 | ST0101-34-LAY-0001 | ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY AND SHORE PULL OF PL-1 (14'' PIPELINE FROM SATAH WHP-10 TO ARZANAH ISLAND- EAST ) | DLB-750 |  | A01 | 1 | 2023-04-20
8 | 8405-AP-0002 | HD0101-34-LAY-0002 | ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY OF PL-2 (12'' PIPELINE FROM HAIR DALMA HD-03 TO HAIR DALMA HD WHP-T4) | DLB-750 |  | A01 | 1 | 2023-04-22
9 | 8405-AP-0003 | HD0201-34-LAY-0003 | ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY AND SHORE PULL OF PL-3 (16'' PIPELINE FROM HAIR DALMA HD WHP-T4 TO ARZANAH ISLAND- SOUTH) | DLB-750 |  | A01 | 1 | 2023-04-24
10 | 8405-AP-0004 | BH0091-34-LAY-0004 | ANCHOR PATTERN FOR BARGE DLB-750 DURING PIPELAY AND SHORE PULL OF PL-4 (16'' PIPELINE FROM BU HASEER BH-03 TO ARZANAH ISLAND- EAST) | DLB-750 |  | A01 | 1 | 2023-04-26
11 | 8405-AP-0005 | KP0091-34-LAY-0005 | ANCHOR PATTERN FOR BARGE DLB-750 DURING SHORE PULL AND PIPELAY OF PL-5 (24'' PIPELINE FROM ARZANAH ISLAND- EAST TO IGD-E) | DLB-750 |  | A01 | 1 | 2023-04-28
12 | 8405-AP-0006 | CF0091-34-LAY-0006 | ANCHOR PATTERN FOR BARGE DLB-750 DURING SHORE PULL AND PIPELAY OF PL-6 (6'' PIPELINE FROM ARZANAH ISLAND- EAST TO ZIRKU ISLAND) | DLB-750 |  | A01 | 1 | 2023-04-30
13 | 8405-AP-0007 | KP0091-34-LAY-0007 | ANCHOR PATTERN FOR BARGE DLB-750 DURING COMPOSITE CABLE SHORE PULL AND INSTALLATION OF CC-1 (FROM ARZANAH ISLAND- EAST TO IGD-E) | DLB-750 |  | A01 | 1 | 2023-05-02
14 | 8405-AP-0008 | ST0101-34-LAY-0008 | ANCHOR PATTERN FOR BARGE DLB-750 DURING RISER INSTALLATION AT SATAH WHP-10 (14" RISER FOR (PL-1) PIPELINE FROM ARZANAH ISLAND TO SATAH WHP-10) | DLB-750 |  | A01 | 1 | 2023-05-04
15 | 8405-AP-0009 | HD0101-34-LAY-0009 | ANCHOR PATTERN FOR BARGE SAFEEN-3000 DURING RISER INSTALLATION AT HD-03 (12" RISER FOR (PL-2) PIPELINE FROM HD-03 TO HD WHP-T4) | SAFEEN-3000 |  | A01 | 1 | 2023-05-06
16 | 8405-AP-0010 | HD0101-34-LAY-0010 | ANCHOR PATTERN FOR BARGE SAFEEN-3000 DURING RISER INSTALLATION AT HD WHP-T4 (12" RISER FOR (PL-2) PIPELINE FROM HD-03 TO HD WHP-T4) | SAFEEN-3000 |  | A01 | 1 | 2023-05-08
17 | 8405-AP-0011 | AZ0091-34-LAY-0011 | ANCHOR PATTERN FOR BARGE SAFEEN-3000 DURING RISER INSTALLATION AT HD WHP-T4 (16" RISER FOR (PL-3) PIPELINE FROM SOUTH ARZANAH ISLAND TO HD WHP-T4) | SAFEEN-3000 |  | A01 | 1 | 2023-05-10
18 | 8405-AP-0012 | BH0101-34-LAY-0012 | ANCHOR PATTERN FOR BARGE SAFEEN-3000 DURING RISER INSTALLATION AT WHP BH-03 (16" RISER FOR (PL-4) PIPELINE FROM EAST ARZANAH ISLAND TO WHP BH-03) | SAFEEN-3000 |  | A01 | 1
19 | 8405-AP-0013 | KP0091-34-LAY-0013 | ANCHOR PATTERN FOR BARGE SAFEEN-3000 DURING RISER INSTALLATION AT IGD-E (KP-38) (24" RISER FOR (PL-5) PIPELINE FROM EAST ARZANAH ISLAND TO IGD-E (KP-38)) | SAFEEN-3000 |  | A01 | 1
20 | 8405-AP-0014 | HD0091-34-LAY-0014 | ANCHOR PATTERN FOR BARGE SAFEEN- 3000 DURING HD-03 JACKET EXTENSION | SAFEEN-3000 |  | A01 | 1
21 | 8405-AP-0015 | HD0091-34-LAY-0015 | ANCHOR PATTERN FOR BARGE DLB-750 DURING INSTALLATION OF 24" CONDUIT FOR UC-3 (UMBILICAL FROM ARZANAH ISLAND-SOUTH TO HD WHP-T4), AT ARZANAH ISLAND-SOUTH | DLB-750 |  | A01 | 1
22 | 8405-AP-0016 | AZ0091-34-LAY-0016 | ANCHOR PATTERN FOR BARGE DLB-750 DURING INSTALLATION OF 24" CONDUIT FOR UC-1 (UMBILICAL FROM ARZANAH ISLAND-EAST TO SATAH WHP-10), AT ARZANAH ISLAND-EAST | DLB-750 |  | A01 | 1
23 | 8405-AP-0017 | ST0101-34-LAY-0017 | ANCHOR PATTERN FOR BARGE DLB-750 DURING INSTALLATION OF 24" CONDUIT FOR UC-4 (UMBILICAL FROM ARZANAH ISLAND-EAST TO BH-3), AT ARZANAH ISLAND-EAST | DLB-750 |  | A01 | 1 | 2023-05-17
24 | 8405-AP-0018 | AZ0091-34-LAY-0018 | ANCHOR PATTERN FOR BARGE DLB-750 DURING INSTALLATION OF 16" CONDUIT FOR CC-1 (COMPOSITE CABLE FROM ARZANAH ISLAND-EAST TO IGD-E), AT ARZANAH ISLAND-EAST | DLB-750 |  | A01 | 1 | 2023-05-17
25 | 8405-AP-0101 | HD0091-34-LAY-0101 | ANCHOR PATTERN FOR BARGE SEP-450 DURING REMOVAL OF EXISTING TOPSIDE OF HAIR DALMA HD-03 | SEP-450 |  | A01 | 1
26 | 8405-AP-0102 | HD0091-34-LAY-0102 | ANCHOR PATTERN FOR BARGE SEP-450 DURING INSTALLATION OF NEW TOPSIDE FOR HAIR DALMA HD-03 | SEP-450 |  | A01 | 1
27 | 8405-AP-0103 | HD0091-34-LAY-0103 | ANCHOR PATTERN FOR BARGE SEP-450 DURING INSTALLATION OF HD WHP-T4 TOPSIDE | SEP-450 |  | A01 | 1
28 | 8405-AP-0104 | BH0101-34-LAY-0104 | ANCHOR PATTERN FOR BARGE SEP-450 DURING INSTALLATION OF WHP BH-03 TOPSIDE | SEP-450 |  | A01 | 1
29 | 8405-AP-0105 | ST0101-34-LAY-0105 | ANCHOR PATTERN FOR BARGE SEP-450 DURING INSTALLATION OF SATAH WHP-10 TOPSIDE | SEP-450 |  | A01 | 1
30 | 8405-AP-0106 | KP0091-34-LAY-0106 | ANCHOR PATTERN FOR BARGE SEP-750 DURING DECK EXTENSION AT IGD-E | SEP-750 |  | A01 | 1

## DP (hidden)
ABU DHABI NATIONAL OIL COMPANY (ADNOC) EPC FOR DALMA GAS DEVELOPMENT PROJECT CONTRACT AGREEMENT NO: 6000001102(A)
COMPANY Project No. | P4331432 | DP SET- UP PLANS REGISTER |  | Rev. 00
CONTRACTOR Project No. | 8405 |  |  | 2023-04-10
Sl. No. | Contractor Document No. | COMPANY Document No. | Title / Description | Vessel Name | Remarks
1 | 8405-DP-0201 | ST0101-34-LAY-0201 | DP SET- UP PLAN FOR UMBILICAL & CABLE LAYING VESSEL DURING UMBILICAL SHORE PULL AND INSTALLATION OF UC-1 (UMBILICAL FROM ARZANAH ISLAND-EAST TO SATAH WHP-10) | UMBILICAL & CABLE LAYING VESSEL
2 | 8405-DP-0202 | HD0101-34-LAY-0202 | DP SET- UP PLAN FOR UMBILIUMBILICAL & CABLE LAYING VESSEL DURING UMBILICAL INSTALLATION OF UC-2 (UMBILICAL FROM HD-03 TO HD WHP-T4) | UMBILICAL & CABLE LAYING VESSEL
3 | 8405-DP-0203 | HD0101-34-LAY-0203 | DP SET- UP PLAN FOR UMBILICAL & CABLE LAYING VESSEL DURING UMBILICAL SHORE PULL AND INSTALLATION OF UC-3 (UMBILICAL FROM ARZANAH ISLAND-SOUTH TO HD WHP-T4) | UMBILICAL & CABLE LAYING VESSEL
4 | 8405-DP-0204 | BH0101-34-LAY-0204 | DP SET- UP PLAN FOR UMBILICAL & CABLE LAYING VESSEL DURING UMBILICAL SHORE PULL AND INSTALLATION OF UC-4 (UMBILICAL FROM ARZANAH ISLAND-EAST TO BH-03) | UMBILICAL & CABLE LAYING VESSEL
5 | 8405-DP-0205 | KP0091-34-LAY-0205 | DP SET- UP PLAN FOR VESSEL SAFEEN PRINCE DURING J-TUBE INSTALLATION AT IGD-E (KP-38) (16" J-TUBE FOR (CC-1) COMPOSITE CABLE FROM EAST ARZANAH ISLAND (SPLITTER BOX) TO IGD-E (KP-38)) | SAFEEN PRINCE
6 | 8405-DP-0206 | CF0000-34-LAY-0206 | DP SET- UP PLAN FOR UMBILICAL & CABLE LAYING VESSEL WHILE AT VESSEL ACCESS CHANNEL | UMBILICAL & CABLE LAYING VESSEL
7 | 8405-DP-0207 | ST0101-34-LAY-0207 | DP SET- UP PLAN FOR UMBILICAL & CABLE LAYING VESSEL DURING UMBILICAL INSTALLATION OF UC-1 (UMBILICAL FROM ARZANAH ISLAND-EAST TO SATAH WHP-10), AT SHALLOW WATER AREA | UMBILICAL & CABLE LAYING VESSEL
8 | 8405-DP-0101 | KP0091-34-LAY-0101 | DP SET- UP PLAN FOR BARGE SEP-450 DURING DECK EXTENSION AT IGD-E | SEP-450

## COMMISSION - List of OTP (hidden)
OPERATIONAL TEST PROCEDURES LIST
|  | ADNOC Document No.: CA0000-54-PRO-003 | [13 empty] | Rev.
|  | CONTRACTOR Document No.: 8405-PP-CM-006 | [13 empty] | A
OTPs / ALL PLATFORMS
OTPs - PLATFORM : BH-03
Project Document Number | ADNOC Document Number | System Number | Rev | Sub-Systems | [5 empty] | Title | OTP | Vendor Required | Commissioning Phase | Discipline Custodian | Location | Remarks
8405-BH0091-100-0001 | BH0091-54-PRO-100-0001 | BH0091-100 | A01 | 001 | [5 empty] | OTP for BH-03 to Arzanah 16" Gas Producer Sebsea Pipeline | X | No | Stage 5 | Process | Offshore
8405-HB0101-110-0001 | BH0101-54-PRO-110-0001 | BH0101-110 | A01 | 001 | 005 | 007 | 009 |  |  | OTP for Wellhead Control Panel (WHCP) & Wellheads | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
|  | BH0101-610 | A01 | 001 | 002
8405-BH0101-401-0001 | BH0101-54-PRO-401-0001 | BH0101-401 | A01 | 001 | 002 | 004 |  |  |  | OTP for Production Manifold & MPFM | X | Yes | Stage 4 | Process/Instrumentation | Onshore / Offshore
8405-BH0101-501-0001 | BH0101-54-PRO-501-0001 | BH0101-501 | A01 | 001 | [5 empty] | OTP for Nitrogen Distribution | X | No | Stage 3 | Mechanical | Onshore
8405-BH0101-502-0001 | BH0101-54-PRO-502-0001 | BH0101-502 | A01 | 001 | 002 | 003 | 004 | 005 | 006 | OTP for Chemical Injection | X | No | Stage 3 | Mechanical | Onshore / Offshore
8405-BH0101-511-0001 | BH0101-54-PRO-511-0001 | BH0101-511 | A01 | 001 | 002 |  |  |  |  | OTP for Hazardous Open Drains | X | No | Stage 3 | Mechanical | Onshore
8405-BH0101-512-0001 | BH0101-54-PRO-512-0001 | BH0101-512 | A01 | 001 | 002 |  |  |  |  | OTP for Closed Drains | X | No | Stage 3 | Mechanical | Onshore
8405-BH0101-601-0001 | BH0101-54-PRO-601-0001 | BH0101-601 | A01 | 001 | 002 |  |  |  |  | OTP for DCS System | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-BH0101-602-0001 | BH0101-54-PRO-602-0001 | BH0101-602 | A01 | 001 | 002 |  |  |  |  | OTP for ESD System and Cause & Effect | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-BH0101-603-0001 | BH0101-54-PRO-603-0001 | BH0101-603 | A01 | 001 | 002 | 003 |  |  |  | OTP for F&G System and Cause & Effect | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-BH0101-620-0001 | BH0101-54-PRO-620-0001 | BH0101-620 | A01 | 001 | [5 empty] | OTP for HIPPS System | X | Yes | Stage 2 | Instrumentation | Onshore
8405-BH0101-652-0001 | BH0101-54-PRO-652-0001 | BH0101-652 | A01 | 001 | [5 empty] | OTP for Telephone & Tetra System | X | Yes | Stage 4 | Telecom | Onshore / Offshore
8405-BH0101-653-0001 | BH0101-54-PRO-653-0001 | BH0101-653 | A01 | 001 | [5 empty] | OTP for CCTV System | X | Yes | Stage 4 | Telecom | Onshore / Offshore
8405-BH0101-701-0001 | BH0101-54-PRO-701-0001 | BH0101-701 | A01 | 001 | 002 |  |  |  |  | OTP for Firefighting System | X | No | Stage 3 | Mechanical | Onshore
8405-BH0091-800-0001 | BH0091-54-PRO-8000-0001 | BH0091-800 | A01 | 001 | [5 empty] | OTP for BH-03 to Arzanah Subsea Umbilical | X | Yes | Stage 5 | Electrical | Offshore
|  | BH0091-810 | A01 | 001
|  | BH0091-811 | A01 | 001
8405-BH0101-820-0001 | BH0101-54-PRO-820-0001 | BH0101-820 | A01 | 001 | [5 empty] | OTP for 6.6 KV Ring Main Unit | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-BH0101-821-0001 | BH0101-54-PRO-821-0001 | BH0101-821 | A01 | 001 | [5 empty] | OTP for 6.6 KV / 433 V Transformer | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-BH0101-830-0001 | BH0101-54-PRO-830-0001 | BH0101-830 | A01 | 001 | 002 | 003 | 004 | 005 | 006 | OTP for 415 V Switchboard & Small Power | X | Yes | Stage 1 | Electrical | Onshore
8405-BH0101-840-0001 | BH0101-54-PRO-840-0001 | BH0101-840 | A01 | 001 | 002 |  |  |  |  | OTP for 24 V DC UPS | X | Yes | Stage 1 | Electrical | Onshore
8405-BH0101-850-0001 | BH0101-54-PRO-850-0001 | BH0101-850 | A01 | 001 | [5 empty] | OTP for Electrical Control & Monitoring System (ECMS) | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-BH0101-860-0001 | BH0101-54-PRO-860-0001 | BH0101-860 | A01 | 001 | [5 empty] | OTP for Navaids System | X | No | Stage 4 | Electrical | Onshore
8405-BH0101-861-0001 | BH0101-54-PRO-861-0001 | BH0101-861 | A01 | 001 | [5 empty] | OTP for Bird Deterrent System | X | No | Stage 4 | Electrical | Onshore
OTPs - PLATFORM : HD-03
Project Document Number | ADNOC Document Number | System Number | Rev | Sub-Systems | [5 empty] | Title | OTP | Vendor Required | Commissioning Phase | Discipline Custodian |  | Remarks
8405-HD0091-100-0001 | HD0091-54-PRO-100-0001 | HD0091-100 | A01 | 001 | [5 empty] | OTP for HD-03 to HD-T4 12" Gas Producer Sebsea Pipeline | X | No | Stage 5 | Process | Offshore
8405-HD0101-110-0001 | HD0101-54-PRO-110-0001 | HD0101-110 | A01 | 001 | 009 |  |  |  |  | OTP for Wellhead Control Panel (WHCP) & Wellheads | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
|  | HD0101-610 | A01 | 001 | 002
8405-HD0101-401-0001 | HD0101-54-PRO-401-0001 | HD0101-401 | A01 | 001 | 002 | 004 |  |  |  | OTP for Production Manifold & MPFM | X | Yes | Stage 4 | Process/Instrumentation | Onshore / Offshore
8405-HD0101-501-0001 | HD0101-54-PRO-501-0001 | HD0101-501 | A01 | 001 | [5 empty] | OTP for Nitrogen Distribution | X | No | Stage 3 | Mechanical | Onshore
8405-HD0101-502-0001 | HD0101-54-PRO-502-0001 | HD0101-502 | A01 | 001 | 002 | 004 | 005 | 006 |  | OTP for Chemical Injection | X | No | Stage 3 | Mechanical | Onshore / Offshore
8405-HD0101-511-0001 | HD0101-54-PRO-511-0001 | HD0101-511 | A01 | 001 | 002 |  |  |  |  | OTP for Hazardous Open Drains | X | No | Stage 3 | Mechanical | Onshore
8405-HD0101-512-0001 | HD0101-54-PRO-512-0001 | HD0101-512 | A01 | 001 | 002 |  |  |  |  | OTP for Closed Drains | X | No | Stage 3 | Mechanical | Onshore
8405-HD0101-601-0001 | HD0101-54-PRO-601-0001 | HD0101-601 | A01 | 001 | 002 |  |  |  |  | OTP for DCS System | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-HD0101-602-0001 | HD0101-54-PRO-602-0001 | HD0101-602 | A01 | 001 | 002 |  |  |  |  | OTP for ESD System and Cause & Effect | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-HD0101-603-0001 | HD0101-54-PRO-603-0001 | HD0101-603 | A01 | 001 | 002 | 003 |  |  |  | OTP for F&G System and Cause & Effect | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-HD0101-620-0001 | HD0101-54-PRO-620-0001 | HD0101-620 | A01 | 001 | [5 empty] | OTP for HIPPS System | X | Yes | Stage 2 | Instrumentation | Onshore
8405-HD0101-652-0001 | HD0101-54-PRO-652-0001 | HD0101-652 | A01 | 001 | [5 empty] | OTP for Telephone & Tetra System | X | Yes | Stage 4 | Telecom | Onshore / Offshore
8405-HD0101-653-0001 | HD0101-54-PRO-653-0001 | HD0101-653 | A01 | 001 | [5 empty] | OTP for CCTV System | X | Yes | Stage 4 | Telecom | Onshore / Offshore
8405-HD0101-701-0001 | HD0101-54-PRO-701-0001 | HD0101-701 | A01 | 001 | 002 |  |  |  |  | OTP for Firefighting System | X | No | Stage 3 | Mechanical | Onshore
8405-HD0091-800-0001 | HD0091-54-PRO-800-0001 | HD0091-800 | A01 | 001 | [5 empty] | OTP for HD-03 to HD-T4 Subsea Umbilical | X | Yes | Stage 5 | Electrical | Offshore
|  | HD0091-810 | A01 | 001
|  | HD0091-811 | A01 | 001
8405-HD0101-820-0001 | HD0101-54-PRO-820-0001 | HD0101-820 | A01 | 001 | [5 empty] | OTP for 6.6 KV Ring Main Unit | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-HD0101-821-0001 | HD0101-54-PRO-821-0001 | HD0101-821 | A01 | 001 | [5 empty] | OTP for 6.6 KV / 433 V Transformer | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-HD0101-830-0001 | HD0101-54-PRO-830-0001 | HD0101-830 | A01 | 001 | 002 | 003 | 004 | 005 | 006 | OTP for 415 V Switchboard & Small Power | X | Yes | Stage 1 | Electrical | Onshore
8405-HD0101-840-0001 | HD0101-54-PRO-840-0001 | HD0101-840 | A01 | 001 | 002 |  |  |  |  | OTP for 24 V DC UPS | X | Yes | Stage 1 | Electrical | Onshore
8405-HD0101-850-0001 | HD0101-54-PRO-850-0001 | HD0101-850 | A01 | 001 | [5 empty] | OTP for Electrical Control & Monitoring System (ECMS) | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-HD0101-860-0001 | HD0101-54-PRO-860-0001 | HD0101-860 | A01 | 001 | [5 empty] | OTP for Navaids System | X | No | Stage 4 | Electrical | Onshore
8405-HD0101-861-0001 | HD0101-54-PRO-861-0001 | HD0101-861 | A01 | 001 | [5 empty] | OTP for Bird Deterrent System | X | No | Stage 4 | Electrical | Onshore
OTPs - PLATFORM : HD-T4
Project Document Number | ADNOC Document Number | System Number | Rev | Sub-Systems | [5 empty] | Title | OTP | Vendor Required | Commissioning Phase | Discipline Custodian |  | Remarks
8405-HD0091-101-0001 | HD0091-54-PRO-101-0001 | HD0091-101 | A01 | 001 | [5 empty] | OTP for HD-T4 to Arzanah 16" Gas Producer Sebsea Pipeline | X | No | Stage 5 | Process | Offshore
8405-HD0201-110-0001 | HD0201-54-PRO-110-0001 | HD0201-110 | A01 | 001 | 002 | 003 |  |  |  | OTP for Wellhead Control Panel (WHCP) & Wellheads | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
|  | HD0201-610 | A01 | 001 | 002
8405-HD0201-401-0001 | HD0201-54-PRO-401-0001 | HD0201-401 | A01 | 001 | 002 | 003 | 004 |  |  | OTP for Production Manifold & MPFM | X | Yes | Stage 4 | Process/Instrumentation | Onshore / Offshore
8405-HD0201-501-0001 | HD0201-54-PRO-501-0001 | HD0201-501 | A01 | 001 | [5 empty] | OTP for Nitrogen Distribution | X | No | Stage 3 | Mechanical | Onshore
8405-HD0201-502-0001 | HD0201-54-PRO-502-0001 | HD0201-502 | A01 | 001 | 002 | 004 | 005 | 006 |  | OTP for Chemical Injection | X | No | Stage 3 | Mechanical | Onshore / Offshore
8405-HD0201-511-0001 | HD0201-54-PRO-511-0001 | HD0201-511 | A01 | 001 | 002 |  |  |  |  | OTP for Hazardous Open Drains | X | No | Stage 3 | Mechanical | Onshore
8405-HD0201-512-0001 | HD0201-54-PRO-512-0001 | HD0201-512 | A01 | 001 | 002 |  |  |  |  | OTP for Closed Drains | X | No | Stage 3 | Mechanical | Onshore
8405-HD0201-601-0001 | HD0201-54-PRO-601-0001 | HD0201-601 | A01 | 001 | 002 |  |  |  |  | OTP for DCS System | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-HD0201-602-0001 | HD0201-54-PRO-602-0001 | HD0201-602 | A01 | 001 | 002 |  |  |  |  | OTP for ESD System and Cause & Effect | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-HD0201-603-0001 | HD0201-54-PRO-603-0001 | HD0201-603 | A01 | 001 | 002 | 003 |  |  |  | OTP for F&G System and Cause & Effect | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-HD0201-620-0001 | HD0201-54-PRO-620-0001 | HD0201-620 | A01 | 001 | [5 empty] | OTP for HIPPS System | X | Yes | Stage 2 | Instrumentation | Onshore
8405-HD0201-652-0001 | HD0201-54-PRO-652-0001 | HD0201-652 | A01 | 001 | [5 empty] | OTP for Telephone & Tetra System | X | Yes | Stage 4 | Telecom | Onshore / Offshore
8405-HD0201-653-0001 | HD0201-54-PRO-653-0001 | HD0201-653 | A01 | 001 | [5 empty] | OTP for CCTV System | X | Yes | Stage 4 | Telecom | Onshore / Offshore
8405-HD0201-701-0001 | HD0201-54-PRO-701-0001 | HD0201-701 | A01 | 001 | 002 |  |  |  |  | OTP for Firefighting System | X | No | Stage 3 | Mechanical | Onshore
8405-HD0091-801-0001 | HD0091-54-PRO-801-0001 | HD0091-801 | A01 | 001 | [5 empty] | OTP for HD-T4 to Arzanah Subsea Umbilical | X | Yes | Stage 5 | Electrical | Offshore
|  | HD0091-812 | A01 | 001
|  | HD0091-813 | A01 | 001
8405-HD0201-820-0001 | HD0201-54-PRO-820-0001 | HD0201-820 | A01 | 001 | [5 empty] | OTP for 6.6 KV Ring Main Unit | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-HD0201-821-0001 | HD0201-54-PRO-821-0001 | HD0201-821 | A01 | 001 | [5 empty] | OTP for 6.6 KV / 433 V Transformer | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-HD0201-830-0001 | HD0201-54-PRO-830-0001 | HD0201-830 | A01 | 001 | 002 | 003 | 004 | 005 | 006 | OTP for 415 V Switchboard & Small Power | X | Yes | Stage 1 | Electrical | Onshore
8405-HD0201-840-0001 | HD0201-54-PRO-840-0001 | HD0201-840 | A01 | 001 | 002 |  |  |  |  | OTP for 24 V DC UPS | X | Yes | Stage 1 | Electrical | Onshore
8405-HD0201-850-0001 | HD0201-54-PRO-850-0001 | HD0201-850 | A01 | 001 | [5 empty] | OTP for Electrical Control & Monitoring System (ECMS) | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-HD0201-860-0001 | HD0201-54-PRO-860-0001 | HD0201-860 | A01 | 001 | [5 empty] | OTP for Navaids System | X | No | Stage 4 | Electrical | Onshore
8405-HD0201-861-0001 | HD0201-54-PRO-861-0001 | HD0201-861 | A01 | 001 | [5 empty] | OTP for Bird Deterrent System | X | No | Stage 4 | Electrical | Onshore
OTPs - PLATFORM : SATAH WHP-10
Project Document Number | ADNOC Document Number | System Number | Rev | Sub-Systems | [5 empty] | Title | OTP | Vendor Required | Commissioning Phase | Discipline Custodian |  | Remarks
8405-ST0091-100-0001 | ST0091-54-PRO-100-0001 | ST0091-100 | A01 | 001 | [5 empty] | OTP for WHP10 to Arzanah 16" Gas Producer Sebsea Pipeline | X | No | Stage 5 | Process | Offshore
8405-ST0101-110-0001 | ST0101-54-PRO-110-0001 | ST0101-110 | A01 | 003 | 005 | 006 |  |  |  | OTP for Wellhead Control Panel (WHCP) & Wellheads | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
|  | ST0101-610 | A01 | 001 | 002
8405-ST0101-401-0001 | ST0101-54-PRO-401-0001 | ST0101-401 | A01 | 001 | 002 | 004 |  |  |  | OTP for Production Manifold & MPFM | X | Yes | Stage 4 | Process/Instrumentation | Onshore / Offshore
8405-ST0101-501-0001 | ST0101-54-PRO-501-0001 | ST0101-501 | A01 | 001 | [5 empty] | OTP for Nitrogen Distribution | X | No | Stage 3 | Mechanical | Onshore
8405-ST0101-502-0001 | ST0101-54-PRO-502-0001 | ST0101-502 | A01 | 001 | 002 | 004 | 005 | 006 |  | OTP for Chemical Injection | X | No | Stage 3 | Mechanical | Onshore / Offshore
8405-ST0101-511-0001 | ST0101-54-PRO-511-0001 | ST0101-511 | A01 | 001 | 002 |  |  |  |  | OTP for Hazardous Open Drains | X | No | Stage 3 | Mechanical | Onshore
8405-ST0101-512-0001 | ST0101-54-PRO-512-0001 | ST0101-512 | A01 | 001 | 002 |  |  |  |  | OTP for Closed Drains | X | No | Stage 3 | Mechanical | Onshore
8405-ST0101-601-0001 | ST0101-54-PRO-601-0001 | ST0101-601 | A01 | 001 | 002 |  |  |  |  | OTP for DCS System | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-ST0101-602-0001 | ST0101-54-PRO-602-0001 | ST0101-602 | A01 | 001 | 002 |  |  |  |  | OTP for ESD System and Cause & Effect | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-ST0101-603-0001 | ST0101-54-PRO-603-0001 | ST0101-603 | A01 | 001 | 002 | 003 |  |  |  | OTP for F&G System and Cause & Effect | X | Yes | Stage 2 | Instrumentation | Onshore / Offshore
8405-ST0101-620-0001 | ST0101-54-PRO-620-0001 | ST0101-620 | A01 | 001 | [5 empty] | OTP for HIPPS System | X | Yes | Stage 2 | Instrumentation | Onshore
8405-ST0101-652-0001 | ST0101-54-PRO-652-0001 | ST0101-652 | A01 | 001 | [5 empty] | OTP for Telephone & Tetra System | X | Yes | Stage 4 | Telecom | Onshore / Offshore
8405-ST0101-653-0001 | ST0101-54-PRO-653-0001 | ST0101-653 | A01 | 001 | [5 empty] | OTP for CCTV System | X | Yes | Stage 4 | Telecom | Onshore / Offshore
8405-ST0101-701-0001 | ST0101-54-PRO-701-0001 | ST0101-701 | A01 | 001 | 002 |  |  |  |  | OTP for Firefighting System | X | No | Stage 3 | Mechanical | Onshore
8405-ST0091-800-0001 | ST0091-54-PRO-800-0001 | ST0091-800 | A01 | 001 | [5 empty] | OTP for BH-03 to Arzanah Subsea Umbilical | X | Yes | Stage 5 | Electrical | Offshore
|  | ST0091-810 | A01 | 001
|  | ST0091-811 | A01 | 001
8405-ST0101-820-0001 | ST0101-54-PRO-820-0001 | ST0101-820 | A01 | 001 | [5 empty] | OTP for 6.6 KV Ring Main Unit | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-ST0101-821-0001 | ST0101-54-PRO-821-0001 | ST0101-821 | A01 | 001 | [5 empty] | OTP for 6.6 KV / 433 V Transformer | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-ST0101-830-0001 | ST0101-54-PRO-830-0001 | ST0101-830 | A01 | 001 | 002 | 003 | 004 | 005 | 006 | OTP for 415 V Switchboard & Small Power | X | Yes | Stage 1 | Electrical | Onshore
8405-ST0101-840-0001 | ST0101-54-PRO-840-0001 | ST0101-840 | A01 | 001 | 002 |  |  |  |  | OTP for 24 V DC UPS | X | Yes | Stage 1 | Electrical | Onshore
8405-ST0101-850-0001 | ST0101-54-PRO-850-0001 | ST0101-850 | A01 | 001 | [5 empty] | OTP for Electrical Control & Monitoring System (ECMS) | X | Yes | Stage 1 | Electrical | Onshore / Offshore
8405-ST0101-860-0001 | ST0101-54-PRO-860-0001 | ST0101-860 | A01 | 001 | [5 empty] | OTP for Navaids System | X | No | Stage 4 | Electrical | Onshore
8405-ST0101-861-0001 | ST0101-54-PRO-861-0001 | ST0101-861 | A01 | 001 | [5 empty] | OTP for Bird Deterrent System | X | No | Stage 4 | Electrical | Onshore
OTPs - PLATFORM : IGD-E
Project Document Number | ADNOC Document Number | System Number | Rev | Sub-Systems | [5 empty] | Title | OTP | Vendor Required | Commissioning Phase | Discipline Custodian |  | Remarks
8405-KP3891-101-0001 | KP3891-54-PRO-101-0001 | KP3891-101 | A01 | 001 | [5 empty] | OTP for Arzanah to IGD-E 24" Gas Export Sebsea Pipeline | X | No | Stage 5 | Process | Offshore
8405-KP3801-402-0001 | KP3801-54-PRO-402-0001 | KP3801-402 | A01 | 005 | [5 empty] | OTP for Export Gas Header & Receiver | X | No | Stage 5 | Process | Offshore
8405-KP3801-511-0001 | KP3801-54-PRO-511-0001 | KP3801-511 | A01 | 001 | [5 empty] | OTP for Hazardous Open Drains | X | No | Stage 3 | Mechanical | Offshore
8405-KP3801-512-0001 | KP3801-54-PRO-512-0001 | KP3801-512 | A01 | 001 | 002 |  |  |  |  | OTP for Closed Drains | X | No | Stage 3 | Mechanical | Offshore
8405-KP3801-601-0001 | KP3801-54-PRO-601-0001 | KP3801-601 | A01 | 001 | 002 |  |  |  |  | OTP for DCS System | X | Yes | Stage 2 | Instrumentation | Offshore
8405-KP3801-602-0001 | KP3801-54-PRO-602-0001 | KP3801-602 | A01 | 001 | 002 |  |  |  |  | OTP for ESD System and Cause & Effect | X | Yes | Stage 2 | Instrumentation | Offshore
8405-KP3801-603-0001 | KP3801-54-PRO-603-0001 | KP3801-603 | A01 | 001 | 002 | 003 |  |  |  | OTP for F&G System and Cause & Effect | X | Yes | Stage 2 | Instrumentation | Offshore
8405-KP3801-611-0001 | KP3801-54-PRO-611-0001 | KP3801-611 | A01 | 001 | 002 |  |  |  |  | OTP for Hydraulic Pump Unit | X | No | Stage 4 | Mechanical / Instrumentation | Offshore
8405-KP3801-652-0001 | KP3801-54-PRO-652-0001 | KP3801-652 | A01 | 001 | [5 empty] | OTP for Telephone & Tetra System | X | Yes | Stage 4 | Telecom | Offshore
8405-KP3801-653-0001 | KP3801-54-PRO-653-0001 | KP3801-653 | A01 | 001 | [5 empty] | OTP for CCTV System | X | Yes | Stage 4 | Telecom | Offshore
8405-KP3801-701-0001 | KP3801-54-PRO-701-0001 | KP3801-701 | A01 | 002 | [5 empty] | OTP for Firefighting System | X | No | Stage 3 | Mechanical | Offshore
8405-KP3891-800-0001 | KP3891-54-PRO-800-0001 | KP3891-800 | A01 | 001 | [5 empty] | OTP for Arzanah to IGD-E Subsea Composite Cable | X | No | Stage 5 | Electrical | Offshore
|  | KP3891-810 | A01 | 001 | [10 empty] | Offshore
|  | KP3891-811 | A01 | 001 | [10 empty] | Offshore
8405-KP3801-820-0001 | KP3801-54-PRO-820-0001 | KP3801-820 | A01 | 001 | [5 empty] | OTP for 6.6 KV Ring Main Unit | X | Yes | Stage 1 | Electrical | Offshore
8405-KP3801-821-0001 | KP3801-54-PRO-821-0001 | KP3801-821 | A01 | 001 | [5 empty] | OTP for 6.6 KV / 433 V Transformer | X | Yes | Stage 1 | Electrical | Offshore
8405-KP3801-830-0001 | KP3801-54-PRO-830-0001 | KP3801-830 | A01 | 001 | 002 | 003 | 004 | 005 | 006 | OTP for 415 V Switchboard & Small Power | X | Yes | Stage 1 | Electrical | Offshore
8405-KP3801-840-0001 | KP3801-54-PRO-840-0001 | KP3801-840 | A01 | 001 | 002 |  |  |  |  | OTP for 24 V DC UPS | X | Yes | Stage 1 | Electrical | Offshore
8405-KP3801-850-0001 | KP3801-54-PRO-850-0001 | KP3801-850 | A01 | 001 | [5 empty] | OTP for Electrical Control & Monitoring System (ECMS) | X | Yes | Stage 1 | Electrical | Offshore
8405-KP3801-860-0001 | KP3801-54-PRO-860-0001 | KP3801-860 | A01 | 001 | [5 empty] | OTP for Navaids System | X | No | Stage 4 | Electrical | Offshore
8405-KP3801-861-0001 | KP3801-54-PRO-861-0001 | KP3801-861 | A01 | 001 | [5 empty] | OTP for Bird Deterrent System | X | No | Stage 4 | Electrical | Offshore
OTPs - ZIRKU
Project Document Number | ADNOC Document Number | System Number | Rev | Sub-Systems | [5 empty] | Title | OTP | Vendor Required | Commissioning Phase | Discipline Custodian |  | Remarks
8405-CF0091-102-0001 | CF0091-54-PRO-102-0001 | CF0091-102 | A01 | 001 | [5 empty] | OTP for Arzanah to IGD-E 6" Condensate Export Sebsea Pipeline | X | No | Stage 5 | Process | Offshore

## P6_List_Final (hidden)
EPC FOR DALMA GAS DEVELOPMENT PROJECT PACKAGE-A (OFFSHORE FACILITIES)
PROJECT DELIVERABLES REGISTER
COMPANY Project No. |  |  |  |  | COMPANY DOC. No. CA0000-59-REG-0001 |  |  | REV
P4331432
CONTRACTOR Project No. |  |  |  |  | CONTRACTOR DOC. No. 8405-PP-GE-001 |  |  | 01
8405
SECTION | COMPANY DOCUMENT No. | ID2 | ID4 | ID5 | CONTRACTOR DOCUMENT No. | TITLE / DESCRIPTION | DOCUMENT CLASS | 1ST REVISION ISSUANCE PLANNED DATE | ACTUAL DATE | 2ND REVISION ISSUANCE PLANNED DATE | ACTUAL DATE | 3RD REVISION ISSUANCE PLANNED DATE | ACTUAL DATE | DOCUMENT CLASS
A | PROJECT MANAGEMENT
A.1 | PROJECT GENERAL
A.1.1 | CA0000-59-REG-0001 | GDVPJ1000 | GDVPJ1005 | GDVPJ1010 | 8405-PP-GE-001 | PROJECT DELIVERABLES REGISTER | 1 | 2021-12-30 | 2021-12-30 | 2022-03-04 |  | 2022-03-25 |  | 1
A.1.2 | CA0000-59-PLN-0001 | GDVPJ1015 | GDVPJ1020 | GDVPJ1025 | 8405-PP-GE-002 | PROJECT EXECUTION PLAN | 1 | 2022-01-12 | 2022-01-11 | 2022-02-09 | 2022-02-03 | 2022-03-23 |  | 1
A.1.3 | CA0000-59-PRO-0001 | GDVPJ1030 | GDVPJ1035 | GDVPJ1040 | 8405-PP-GE-003 | PROJECT COORDINATION & COMMUNICATION PROCEDURE | 1 | 2022-02-09 | 2022-02-07 | 2022-03-09 |  | 2022-04-04 |  | 1
A.1.4 | CA0000-59-PRO-0002 | GDVPJ1045 | GDVPJ1050 | GDVPJ1055 | 8405-PP-GE-004 | PROJECT DOCUMENT CONTROL PROCEDURE | 1 | 2022-01-21 | 2021-12-30 | 2022-02-25 | 2022-02-23 | 2022-03-22 |  | 1
A.1.5 | CA0000-59-PLN-0002 | GDVPJ1060 | GDVPJ1065 | GDVPJ1070 | 8405-PP-GE-005 | PROJECT INTERFACE MANAGEMENT PLAN | 2 | 2022-02-11 | 2022-01-11 | 2022-03-04 | 2022-02-16 | 2022-03-22 |  | 2
A.1.6 | CA0000-59-REG-0002 | GDVPJ1090 | GDVPJ1095 | GDVPJ1100 | 8405-PP-GE-006 | PROJECT RISK REGISTER | 2 | 2022-03-23 |  | 2022-03-29 |  | 2022-04-11 |  | 2
A.1.7 | CA0000-59-PRO-0011 | GDVPT1065 | GDVPT1075 | GDVPT1085 | 8405-PP-GE-007 | VENDOR DOCUMENT MANAGEMENT PROCEDURE | 1 | 2022-05-11 |  | 2022-06-15 |  | 2022-07-18 |  | 1
A.1.8 | CA0000-59-PRO-0004 | GDVPJ1075 | GDVPJ1080 | GDVPJ1085 | 8405-PP-GE-008 | PROJECT RISK MANAGEMENT PROCEDURE | 1 | 2022-01-28 | 2022-01-14 | 2022-02-22 | 2022-02-21 | 2022-03-15 |  | 1
A.1.9 | CA0000-50-REP-0002 | GDVPJ1240 | GDVPJ1245 | GDVPJ1310 | 8405-PP-GE-029 | PROJECT RISK CLOSE-OUT REPORT | 1 | 2024-08-28 |  | 2024-09-26 |  | 2025-02-20 |  | 1
A.1.10 | CA0000-50-PRO-0008 |  |  |  | 8405-PP-GE-037 | TOR / PROCEDURE FOR PROJECT RISK ASSESSMENT WORKSHOP | 1 | 2022-02-17 | [5 empty] | 1
A.1.11 | CA0000-59-PLN-0003 | GDVPJ1105 | GDVPJ1110 | GDVPJ1115 | 8405-PP-GE-009 | PROJECT SUBCONTRACT PLAN | 1 | 2022-01-14 | 2022-01-20 | 2022-02-28 |  | 2022-03-28 |  | 1
A.1.12 | CA0000-59-PLN-0004 | GDVPJ1120 | GDVPJ1125 | GDVPJ1130 | 8405-PP-GE-010 | ASSET INTEGRITY MANAGEMENT PLAN | 1 | 2022-03-11 |  | 2022-04-22 |  | 2022-05-25 |  | 1
A.1.13 | CA0000-59-PRO-0005 | GDVPJ1290 | GDVPJ1300 | GDVPJ1250 | 8405-PP-GE-011 | FINAL DOCUMENTATION HANDOVER PROCEDURE | 1 | 2023-09-18 |  | 2023-10-17 |  | 2023-11-14 |  | 1
A.1.14 | CA0000-59-PRO-0006 | GDVPJ1135 | GDVPJ1140 | GDVPJ1145 | 8405-PP-GE-012 | CONSTRUCTABILITY WORKSHOP PROCEDURE | 1 | 2022-06-20 |  | 2022-07-18 |  | 2022-08-18 |  | 1
A.1.15 | CA0000-59-REP-0002 |  |  |  | 8405-PP-GE-035 | CONSTRUCTABILITY WORKSHOP REPORT | 1 | 2022-06-27 | [5 empty] | 1
A.1.16 | CA0000-59-REP-0003 |  |  |  | 8405-PP-GE-036 | CONSTRUCTABILITY WORKSHOP CLOSE-OUT REPORT | 1 | 2022-07-15 | [5 empty] | 1
A.1.17 | CA0000-59-PRO-0007 | GDVPJ1150 | GDVPJ1155 | GDVPJ1160 | 8405-PP-GE-013 | PROJECT MATERIAL MANAGEMENT PROCEDURE | 1 | 2022-02-09 | 2022-01-31 | 2022-03-23 |  | 2022-04-20 |  | 1
A.1.18 | CA0000-59-REG-0003 | GDVPJ1165 | GDVPJ1170 | GDVPJ1175 | 8405-PP-GE-014 | PROJECT INTERFACE REGISTER | 2 | 2022-01-28 | 2022-01-21 | 2022-02-25 | 2022-03-16 | 2022-03-29 |  | 2
A.1.19 | CA0000-59-PRO-0008 | GDVPJ1180 | GDVPJ1185 | GDVPJ1190 | 8405-PP-GE-015 | DESIGN DEVIATION / CONCESSION REQUEST AUTHORIZATION (DCA) PROCEDURE | 1 | 2022-02-16 | 2022-02-04 | 2022-03-11 |  | 2022-04-01 |  | 1
A.1.20 | CA0000-59-GDD-0001 | GDVPJ1195 | GDVPJ1200 | GDVPJ1205 | 8405-PP-GE-016 | PROJECT PROCEDURE FOR NOTIFICATION TO SITE OF CHANGE (NSC) | 1 | 2022-02-16 | 2022-02-14 | 2022-03-09 |  | 2022-03-30 |  | 1
A.1.21 | CA0000-89-REP-0001 |  |  |  | 8405-PP-GE-017 | PROJECT CLOSE OUT REPORT | 2 | 2022-08-20 | [5 empty] | 2
A.1.22 | CA0000-59-COD-0001 |  |  |  | 8405-PP-GE-038 | PROJECT COMPLETION DOSSIER | 1 | 2022-08-20 | [5 empty] | 1
A.1.23 | CA0000-59-PRO-0009 |  |  |  | 8405-PP-GE-039 | AS-BUILT DOCUMENTATION PROCEDURE | 1 | 2024-02-25 | [5 empty] | 1
A.1.24 | CA0000-59-PLN-0005 | GDVPJ1260 | GDVPJ1270 | GDVPJ1280 | 8405-PP-GE-018 | LOGISTICS MANAGEMENT PLAN | 3 | 2022-06-27 |  | 2022-07-25 |  | 2022-08-15 |  | 3
A.1.25 | CA0000-50-PRO-0009 |  |  |  | 8405-PP-GE-033 | LESSON LEARNT PROCEDURE | 1 | 2022-02-01 | [5 empty] | 1
A.1.26 | CA0000-59-REG-0004 | GDVPJ1210 | GDVPJ1215 | GDVPJ1220 | 8405-PP-GE-019 | LESSON LEARNT REGISTER | 2 | 2022-02-18 |  | 2022-03-18 |  | 2022-04-15 |  | 2
A.1.27 | CA0000-89-REP-0002 | GDVPJ1225 | GDVPJ1230 | GDVPJ1235 | 8405-PP-GE-020 | LESSON LEARNT WORKSHOP REPORT | 2 | 2022-04-20 | 2022-02-25 | 2022-05-18 |  | 2022-06-15 |  | 2
A.1.28 | CA0000-54-MAN-001 |  |  |  | 8405-PP-CM-033 | Operating Manuals (Various documents) | 2 | 2024-08-20 | [5 empty] | 2
A.1.29 | CA0000-54-MAN-002 |  |  |  | 8405-PP-CM-034 | INSTALLATION AND MAINTENANCE MANUALS (VARIOUS DOCUMENTS) | 2 | 2024-08-20 | [5 empty] | 2
A.1.30 | CA0000-59-MAN-001 |  |  |  | 8405-PP-GE-040 | CERTIFICATION MANUAL (THIS DOCUMENT ALREADY SEND THRU LETTER NO. 8405-NPCC-A-L-0059 DATED 22-02-22 | 3 | 2022-02-22 | [5 empty] | 3
A.1.31 | CA0000-59-MAN-002 |  |  |  | 8405-PP-GE-041 | INDEXES FOR FINAL DOCUMENTATION MANUALS | 3 | 2024-06-15 | [5 empty] | 3
A.1.32 | CA0000-52-PLN-008 |  |  |  | 8405-PP-HS-023 | TRAINING PLAN | 3 | 2024-05-21 | [5 empty] | 3
A.1.33 | CA0000-58-GDD-0001 |  |  |  | 8405-PP-PR-012 | CONTRACT ORGANIZATION AND MANNING, ORGANIZATION CHARTS | 1 | 2022-01-17 | [5 empty] | 1
A.1.2 | PROJECT CONTROL
A.1.2.1 | CA0000-50-PRO-0001 | GDVPC1005 | GDVPC1010 | GDVPC1015 | 8405-PP-GE-021 | PLANNING & SCHEDULING PROCEDURE | 1 | 2022-01-13 | 2022-01-10 | 2022-02-10 | 2022-02-07 | 2022-03-03 | 2022-03-04 | 1
A.1.2.2 | CA0000-50-PRO-0002 | GDVPC1020 | GDVPC1025 | GDVPC1030 | 8405-PP-GE-022 | PROGRESS MEASUREMENT PROCEDURE | 1 | 2022-01-11 | 2022-01-07 | 2022-02-08 | 2022-02-21 | 2022-03-03 | 2022-03-04 | 1
A.1.2.3 | CA0000-50-GDD-0001 | GDVPC1050 | GDVPC1055 | GDVPC1060 | 8405-PP-GE-023 | PROJECT PLANNING PACKAGE | 1 | 2022-02-04 | 2022-02-07 | 2022-02-28 | 2022-02-26 | 2022-03-09 |  | 1
A.1.2.4 | CA0000-50-REP-0001 | GDVPC1085 | GDVPC1090 | GDVPC1095 | 8405-PP-GE-024 | QUARTERLY SCHEDULE RISK ANALYSIS REPORT | 1 | 2022-04-29 |  | 2022-06-01 |  | 2022-06-29 |  | 1
A.1.2.5 | CA0000-50-PRO-0003 | GDVPC1115 | GDVPC1120 | GDVPC1125 | 8405-PP-GE-025 | MANAGEMENT OF CHANGE PROCEDURE | 1 | 2022-02-10 | 2022-02-07 | 2022-04-01 |  | 2022-05-25 |  | 1
A.1.2.6 | CA0000-50-SCH-0001 | GDVPC1000 | GDVPC1000 | GDVPC1000 | 8405-PP-GE-030 | 30/90 DAYS FRONT END SCHEDULES | 3 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2022-02-05 | 2021-12-27 | 2022-02-05 | 3
A.1.2.7 | CA0000-50-PRO-0004 |  |  |  | 8405-PP-GE-027 | PROJECT CONTRACT TRENDING PROCEDURE | 1 | 2022-01-14 | [5 empty] | 1
A.1.2.8 | CA0000-50-PRO-0005 | GDVPC1065 | GDVPC1070 | GDVPC1075 | 8405-PP-GE-028 | INVOICING PROCEDURE | 2 | 2022-01-28 | 2022-01-10 | 2022-02-25 | 2022-02-15 | 2022-03-25 | 2022-02-23 | 2
A.1.2.9 | CA0000-50-PRO-0006 | GDVPC1035 | GDVPC1040 | GDVPC1045 | 8405-PP-GE-031 | PROGRESS REPORTING & PROGRESS REVIEW/CERTIFICATION PROCEDURE | 1 | 2022-01-07 | 2022-01-07 | 2022-02-04 | 2022-02-10 | 2022-03-04 | 2022-03-04 | 1
A.1.2.10 | CA0000-50-PRO-0007 | GDVPC1080 | GDVPC1080 | GDVPC1080 | 8405-PP-GE-032 | SCHEDULE RISK ANALYSIS PROCEDURE | 1 | 2022-02-04 | 2022-02-09 | 2022-03-24 | 2022-03-07 | 2022-03-24 |  | 1
A.1.2.11 | CA0000-54-SCH-0001 |  |  |  | 8405-PP-CM-035 | DETAILED PRE-COMMISSIONING / COMMISSIONING & START UP SCHEDULES | 1 | 2023-05-15 | [5 empty] | 1
A.1.2.12 | CA0000-58-SCH-0001 |  |  |  | 8405-PP-PR-013 | DETAILED CONSTRUCTION / MECHANICAL COMPLETION SCHEDULE | 2 | 2022-08-22 | [5 empty] | 2
A.1.2.13 | CA0000-50-REP-00XX |  |  |  | 8405-WPR-0XX | WEEKLY PROGRESS REPORTS | 3 | [6 empty] | 3
A.1.2.14 | CA0000-50-REP-3-00XX |  |  |  | 8405-MPR-0XX | MONTHLY PROGRESS REPORTS | 3 | [6 empty] | 3
A.1.2.15 | CA0000-58-PLN-0002 |  |  |  | 8405-PP-PR-014 | RECOVERY PLANS | 2 | [6 empty] | 2
A.1.2.16 | CA0000-59-PRO-0010 |  |  |  | 8405-PP-GE-042 | ASSET REGISTER PROCEDURE | 1 | 2022-04-22 | [5 empty] | 1
A.1.2.17 | CA0000-59-REG-0005 |  |  |  | 8405-PP-GE-043 | ASSET REGISTER | 2 | 2022-05-20 | [5 empty] | 2
CONTRACTS
A.1.2.20 | CA0000-58-GDD-0003 |  |  |  | 8405-PP-PR-015 | PERFORMANCE BANK GUARANTEE | 1 | [6 empty] | 1
A.1.2.21 | CA0000-58-GDD-0004 |  |  |  | 8405-PP-PR-016 | ADVANCE PAYMENT BOND | 1 | [6 empty] | 1
A.1.2.22 | CA0000-58-GDD-0005 |  |  |  | 8405-PP-PR-017 | INSURANCE POLICIES/CERTIFICATES (CONTRACTOR AND SUBCONTRACTOR) | 1 | [6 empty] | 1
A.1.2.23 | CA0000-59-REP-0004 |  |  |  | 8405-PP-GE-044 | SUBCONTRACTOR’S PERFORMANCE FEEDBACK REPORT | 3 | [6 empty] | 3
A.1.2.24 | CA0000-59-GDD-0006 |  |  |  | 8405-PP-GE-045 | UNPRICED COPY SUBCONTRACT AGREEMENTS (WILL BE DEVELOPED SEPARATELY FOR ALL S/C) | 3 | [6 empty] | 3
A.1.3 | PROCUREMENT
A.1.3.1 | CA0000-58-PLN-0001 | GDVPT1000 | GDVPT1005 | GDVPT1010 | 8405-PP-PR-001 | PROJECT PROCUREMENT PLAN | 2 | 2022-02-04 | 2022-01-17 | 2022-03-11 |  | 2022-04-01 |  | 2
A.1.3.2 | CA0000-58-PVL-0001 | GDVPT1015 | GDVPT1020 | GDVPT1025 | 8405-PP-PR-002 | PROJECT VENDOR LIST (PVL) | 1 | 2022-02-11 | 2022-01-12 | 2022-03-11 |  | 2022-04-04 |  | 1
A.1.3.3 | CA0000-58-PRO-0003 |  |  |  | 8405-PP-PR-007 | VENDOR PRE-QUALIFICATION PROCEDURES | 1 | [6 empty] | 1
A.1.3.4 | CA0000-58-LST-0001 | GDVPT1030 | GDVPT1035 | GDVPT1040 | 8405-PP-PR-003 | LIST OF LONG LEAD ITEM (LLIS) | 2 | 2022-03-11 |  | 2022-04-15 |  | 2022-05-18 |  | 2
A.1.3.5 | CA0000-58-GDD-0002 |  |  |  | 8405-PP-PR-008 | AWARD RECOMMENDATIONS | 1 | [6 empty] | 1
A.1.3.6 | CA0000-58-PAR-0001 |  |  |  | 8405-PP-PR-009 | UNPRICED PURCHASE ORDERS | 3 | [6 empty] | 3
A.1.3.7 | CA0000-58-PRO-0006 |  |  |  | 8405-PP-PR-018 | EXPEDITING PROCEDURE | 2 | 2022-04-15 | [5 empty] | 2
A.1.3.8 | CA0000-58-PRO-0001 | GDVPT1045 | GDVPT1050 | GDVPT1055 | 8405-PP-PR-004 | VENDOR INSPECTION COORDINATION PROCEDURE | 3 | 2022-04-08 | 2022-02-16 | 2022-05-18 |  | 2022-06-09 |  | 3
A.1.3.9 | CA0000-58-LST-0002 |  |  |  | 8405-PP-PR-005 | PROJECT SUBCONTRACTORS LIST (PSL) | 2 | 2022-01-10 | [5 empty] | 2
A.1.3.10 | CA0000-58-PRO-0002 |  |  |  | 8405-PP-PR-006 | VENDOR PREQUALIFICATION PROCEDURE | 2 | 2022-01-02 | [5 empty] | 2
A.1.3.11 | CA0000-58-TBE-0001 |  |  |  | 8405-PP-PR-010 | TECHNICAL BID EVALUATION REPORTS (MULTIPLE DOCUMENTS) | 2 | [6 empty] | 2
A.1.3.12 | CA0000-58-REP-0001 |  |  |  | 8405-PP-PR-011 | EXPEDITING REPORTS (MULTIPLE DOCUMENTS) | 2 | [6 empty] | 2
A.1.4 | HSE
A.1.4.1 | CA0000-52-MAN-0001 | GDVHS1000 | GDVHS1000 | GDVHS1000 | 8405-PP-HS-001 | HSE MANUAL SAF-002 - CORPORATE DOCUMENT | 3 | 2022-01-06 | 2022-01-04 | 2022-01-28 |  | 2022-01-28 |  | 3
A.1.4.2 | CA0000-52-MAN-0002 | GDVHS1010 | GDVHS1010 | GDVHS1010 | 8405-PP-HS-002 | NPCC ENVIRONMENT MANAGEMENT SYSTEM MANUAL | 3 | 2022-02-04 | 2022-01-04 | 2022-03-11 |  | 2022-03-11 |  | 3
A.1.4.3 | CA0000-52-GDD-0001 | GDVHS1025 | GDVHS1030 | GDVHS1035 | 8405-PP-HS-003 | COVID 19 & BUSINESS CONTINUITY GUIDELINES - NPCC OFFICES | 3 | 2022-03-11 | 2022-01-04 | 2022-04-08 |  | 2022-05-11 |  | 3
A.1.4.4 | CA0000-52-PLN-0001 |  |  |  | 8405-PP-HS-004 | RISK ASSESSMENT FOR PRE-ENGINEERING GEOPHYSICAL SURVEY | 2 | 2022-02-21 | [5 empty] | 2
A.1.4.5 | CA0000-52-PLN-0002 | GDVHS1045 | GDVHS1050 | GDVHS1055 | 8405-PP-HS-005 | CONSTRUCTION HSE PLAN - OFFSHORE | 1 | 2022-05-19 |  | 2022-06-16 |  | 2022-07-19 |  | 1
A.1.4.6 | CA0000-52-PLN-0003 |  |  |  | 8405-PP-HS-006 | EMERGENCY RESPONSE PLAN | 1 | 2022-05-10 | [5 empty] | 1
A.1.4.7 | CA0000-52-PLN-0004 | GDVHS1110 | GDVHS1120 | GDVHS1130 | 8405-PP-HS-007 | EMERGENCY RESPONSE PLAN - OFFSHORE | 1 | 2022-07-27 |  | 2022-08-24 |  | 2022-09-21 |  | 1
A.1.4.8 | CA0000-52-PLN-0006 |  |  |  | 8405-PP-HS-008 | WASTE MANAGEMENT PLAN - ISLAND |  | 2022-08-12
A.1.4.9 | CA0000-52-PLN-0007 | GDVHS1075 | GDVHS1080 | GDVHS1085 | 8405-PP-HS-009 | WASTE MANAGEMENT PLAN - OFFSHORE | 1 | 2022-07-01 |  | 2022-08-03 |  | 2022-08-31 |  | 1
A.1.4.10 | CA0000-52-PRO-0001 |  |  |  | 8405-PP-HS-010 | MEDICAL EVACUATION PROCEDURE (MEDEVAC) - ISLAND | 1 | 2022-08-12 | [5 empty] | 1
A.1.4.11 | CA0000-52-PRO-0002 | GDVHS1090 | GDVHS1095 | GDVHS1100 | 8405-PP-HS-011 | MEDICAL EVACUATION PROCEDURE (MEDEVAC) - OFFSHORE | 1 | 2022-07-20 |  | 2022-08-17 |  | 2022-09-14 |  | 1
A.1.4.12 | CA0000-52-PRO-0003 | GDVHS1060 | GDVHS1065 | GDVHS1070 | 8405-PP-HS-012 | CONSTRUCTION ENVIRONMENT MANAGEMENT PLAN - OFFSHORE | 1 | 2022-06-10 |  | 2022-07-13 |  | 2022-08-02 |  | 1
A.1.4.13 | CA0000-52-PLN-0008 | GDVHS1005 | GDVHS1015 | GDVHS1020 | 8405-PP-HS-013 | PROJECT HSE PLAN | 1 | 2022-02-04 | 2022-01-13 | 2022-03-04 | 2022-02-21 | 2022-04-01 |  | 1
A.1.4.14 | CA0000-52-SCH-0001 |  |  |  | 8405-PP-HS-014 | PLANNED INTERNAL & EXTERNAL AUDIT SCHEDULE FOR QHSE | 1 | [6 empty] | 1
A.1.4.15 | CA0000-52-HSE-0001 |  |  |  | 8405-PP-HS-015 | INTERFACE HSE REVIEW | 1 | [6 empty] | 1
A.1.4.16 | CA0000-52-REG-0001 |  |  |  | 8405-PP-HS-016 | HSE ACTION TRACKING REGISTER | 1 | [6 empty] | 1
A.1.4.17 | CA0000-52-PLN-0009 |  |  |  | 8405-PP-HS-017 | ENVIRONMENTAL MANAGEMENT PLAN (CONSTRUCTION & OPERATIONS) | 1 | 2022-07-02 | [5 empty] | 1
A.1.4.18 | CA0000-52-PRO-0004 |  |  |  | 8405-PP-HS-018 | WORK PERMIT PROCEDURE | 2 | 2022-07-07 | [5 empty] | 2
A.1.4.19 | CA0000-52-PLN-0010 |  |  |  | 8405-PP-HS-019 | CONTRACTOR CAMP HSE PLAN | 1 (Offshore Barges) | 2022-07-12 | [5 empty] | 1 (Offshore Barges)
A.1.4.20 | CA0000-52-REP-0001 |  |  |  | 8405-PP-HS-020 | CONSTRUCTION RISK ASSESSMENT | 2 | 2022-07-15 | [5 empty] | 2
A.1.4.21 | CA0000-52-PRO-0005 |  |  |  | 8405-PP-HS-021 | HEMS PROCEDURES & HEMS BRIDGING DOCUMENT | 1 | 2022-07-13 | [5 empty] | 1
A.1.4.22 | CA0000-52-PLN-0011 |  |  |  | 8405-PP-HS-022 | ERP BRIDGING DOCUMENT | 1 | [6 empty] | 1
A.1.4.23 | CA0000-52-PLN-0012 |  |  |  | 8405-PP-HS-025 | CONSTRUCTION HSE PLAN - YARD
A.1.5 | QA&QC
A.1.5.1 | CA0000-63-PLN-0001 | GDVQA1000 | GDVQA1005 | GDVQA1010 | 8405-PP-QA-001 | PROJECT QUALITY PLAN | 1 | 2022-01-28 | 2022-01-13 | 2022-03-04 |  | 2022-04-01 |  | 1
A.1.5.2 | CA0000-63-PRO-0020 |  |  |  | 8405-PP-QA-046 | PROJECT QUALITY AUDIT PROCEDURE | 1 | 2022-04-22 | [5 empty] | 1
A.1.5.3 | CA0000-63-SCH-0001 | GDVQA1015 | GDVQA1020 | GDVQA1025 | 8405-PP-QA-002 | PROJECT QUALITY AUDIT SCHEDULE | 1 | 2022-02-04 | 2022-01-17 | 2022-03-18 |  | 2022-04-15 |  | 1
A.1.5.4 | CA0000-63-PRO-0001 | GDVQA1030 | GDVQA1035 | GDVQA1040 | 8405-PP-QA-003 | NON-CONFORMANCE REPORTING SYSTEM PROCEDURE | 1 | 2022-04-15 |  | 2022-06-15 |  | 2022-08-22 |  | 1
A.1.5.5 | CA0000-63-PRO-0002 | GDVQA1045 | GDVQA1050 | GDVQA1055 | 8405-PP-QA-004 | PROJECT MATERIAL CONTROL INSPECTION IDENTIFICATION AND TRACEABILITY PROCEDURE | 1 | 2022-04-22 | 2022-03-12 | 2022-06-15 |  | 2022-09-08 |  | 1
A.1.5.6 | CA0000-63-PRO-0003 | GDVQA1060 | GDVQA1065 | GDVQA1070 | 8405-PP-QA-005 | DIMENSIONAL CONTROL PROCEDURE | 1 | 2022-05-25 |  | 2022-07-06 |  | 2022-09-08 |  | 1
A.1.5.7 | CA0000-63-PRO-0004 | GDVQA1075 | GDVQA1080 | GDVQA1085 | 8405-PP-QA-006 | POSITIVE MATERIAL IDENTIFICATION (PMI) PROCEDURE | 1 | 2022-05-30 |  | 2022-07-14 |  | 2022-09-01 |  | 1
A.1.5.8 | CA0000-63-PRO-0005 | GDVQA1090 | GDVQA1095 | GDVQA1100 | 8405-PP-QA-007 | WELDING CONSUMABLE CONTROL PROCEDURE | 2 | 2022-06-02 |  | 2022-07-19 |  | 2022-08-30 |  | 2
A.1.5.9 | CA0000-63-PRO-0006 | GDVQA1105 | GDVQA1110 | GDVQA1115 | 8405-PP-QA-008 | WELDING PROCEDURES - STRUCTURAL | 1 | 2022-06-09 |  | 2022-07-26 |  | 2022-09-06 |  | 1
A.1.5.10 | CA0000-63-PRO-0007 | GDVQA1120 | GDVQA1125 | GDVQA1130 | 8405-PP-QA-009 | WELDING PROCEDURES - PIPING | 1 | 2022-07-07 |  | 2022-08-23 |  | 2022-10-25 |  | 1
A.1.5.11 | CA0000-63-PRO-0008 | GDVQA1135 | GDVQA1140 | GDVQA1145 | 8405-PP-QA-010 | WELDING PROCEDURES - PIPELINE SPOOLS | 1 | 2022-08-23 |  | 2022-10-04 |  | 2022-12-08 |  | 1
A.1.5.12 | CA0000-63-PLN-0002 | GDVQA1150 | GDVQA1155 | GDVQA1160 | 8405-PP-QA-011 | INSPECTION AND TEST PLAN FOR E & I WORKS (ONSHORE) | 1 | 2022-08-09 |  | 2022-09-20 |  | 2022-11-22 |  | 1
A.1.5.13 | CA0000-63-PLN-0003 | GDVQA1180 | GDVQA1185 | GDVQA1190 | 8405-PP-QA-013 | INSPECTION AND TEST PLAN FOR PIPELAYING WORK | 1 | 2022-09-27 |  | 2022-11-08 |  | 2023-01-12 |  | 1
A.1.5.14 | CA0000-63-PLN-0004 | GDVQA1195 | GDVQA1200 | GDVQA1205 | 8405-PP-QA-014 | INSPECTION & TEST PLAN FOR SUBSEA UMBILICAL AND FIBRE OPTIC & CABLE INSTALLATION | 1 | 2022-08-08 |  | 2022-09-19 |  | 2022-10-31 |  | 1
A.1.5.15 | CA0000-63-LST-0011 | GDVQA1210 | GDVQA1215 | GDVQA1220 | 8405-PP-QA-015 | QC PERSONNEL LIST (ONSHORE) | 2 | 2022-04-29 |  | 2022-06-15 |  | 2022-08-01 |  | 2
A.1.5.16 | CA0000-63-LST-0002 | GDVQA1225 | GDVQA1230 | GDVQA1235 | 8405-PP-QA-016 | QC PERSONNEL LIST (OFFSHORE) | 2 | 2022-07-18 |  | 2022-08-29 |  | 2022-10-10 |  | 2
A.1.5.17 | CA0000-63-LST-0003 | GDVQA1240 | GDVQA1240 | GDVQA1240 | 8405-PP-QA-017 | MUSSAFAH WELDERS LIST (STRUCTURAL) | 1 | 2022-04-01 |  | 2022-05-18 |  | 2022-05-18 |  | 1
A.1.5.18 | CA0000-63-LST-0004 | GDVQA1245 | GDVQA1245 | GDVQA1245 | 8405-PP-QA-018 | MUSSAFAH WELDERS LIST (PIPING) | 1 | 2022-06-16 |  | 2022-07-26 |  | 2022-07-26 |  | 1
A.1.5.19 | CA0000-63-LST-0005 | GDVQA1250 | GDVQA1250 | GDVQA1250 | 8405-PP-QA-019 | OFFSHORE WELDERS LIST (STRUCTURAL) | 1 | 2022-10-17 |  | 2022-11-21 |  | 2022-11-21 |  | 1
A.1.5.20 | CA0000-63-LST-0006 | GDVQA1270 | GDVQA1270 | GDVQA1270 | 8405-PP-QA-020 | OFFSHORE WELDERS LIST (PIPING) | 1 | 2022-11-28 |  | 2023-01-04 |  | 2023-01-04 |  | 1
A.1.5.21 | CA0000-63-LST-0007 | GDVQA1255 | GDVQA1255 | GDVQA1255 | 8405-PP-QA-021 | OFFSHORE WELDERS LIST (RISERS & TIE-IN) | 1 | 2022-07-25 |  | 2022-08-29 |  | 2022-08-29 |  | 1
A.1.5.22 | CA0000-63-LST-0008 | GDVQA1260 | GDVQA1260 | GDVQA1260 | 8405-PP-QA-022 | OFFSHORE WELDERS LIST (PIPELINE) - AUTOMATIC & REPAIR | 1 | 2022-08-08 |  | 2022-09-12 |  | 2022-09-12 |  | 1
A.1.5.23 | CA0000-63-LST-0009 | GDVQA1265 | GDVQA1265 | GDVQA1265 | 8405-PP-QA-023 | OFFSHORE WELDERS LIST (PIPELINE) - MANUAL & REPAIR | 1 | 2022-08-23 |  | 2022-09-26 |  | 2022-09-26 |  | 1
A.1.5.24 | CA0000-63-PRO-0009 | GDVQA1275 | GDVQA1280 | GDVQA1285 | 8405-PP-QA-024 | RADIOGRAPHIC TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS | 1 | 2022-05-18 |  | 2022-06-15 |  | 2022-07-18 |  | 1
A.1.5.25 | CA0000-63-PRO-0010 | GDVQA1290 | GDVQA1295 | GDVQA1300 | 8405-PP-QA-025 | ULTRASONIC TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS | 1 | 2022-05-18 |  | 2022-06-29 |  | 2022-08-15 |  | 1
A.1.5.26 | CA0000-63-PRO-0011 | GDVQA1640 | GDVQA1650 | GDVQA1660 | 8405-PP-QA-026 | LIQUID PENETRANT PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS | 1 | 2022-07-06 |  | 2022-08-08 |  | 2022-09-05 |  | 1
A.1.5.27 | CA0000-63-PRO-0012 | GDVQA1305 | GDVQA1310 | GDVQA1315 | 8405-PP-QA-027 | MAGNETIC PARTICLE TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS | 1 | 2022-05-18 |  | 2022-06-29 |  | 2022-09-05 |  | 1
A.1.5.28 | CA0000-63-PRO-0013 | GDVQA1320 | GDVQA1325 | GDVQA1330 | 8405-PP-QA-028 | NDT PROCEDURES (PIPELINES) | 1 | 2022-06-20 |  | 2022-08-04 |  | 2022-09-08 |  | 1
A.1.5.29 | CA0000-63-LST-0010 | GDVQA1335 | GDVQA1340 | GDVQA1345 | 8405-PP-QA-029 | NDT OPERATORS LIST (ONSHORE / OFFSHORE) | 2 | 2022-06-20 |  | 2022-08-04 |  | 2022-10-06 |  | 2
A.1.5.30 | CA0000-63-PRO-0014 | GDVQA1350 | GDVQA1355 | GDVQA1360 | 8405-PP-QA-030 | PIPING WELDS PHASED ARRAY ULTRASONIC TESTING PROCEDURE | 1 | 2022-06-20 |  | 2022-08-04 |  | 2022-09-22 |  | 1
A.1.5.31 | CA0000-63-PRO-0015 | GDVQA1365 | GDVQA1370 | GDVQA1375 | 8405-PP-QA-031 | AUTOMATED ULTRASONIC TESTING PROCEDURE FOR PIPELINE WELDS | 1 | 2022-06-20 |  | 2022-08-04 |  | 2022-10-06 |  | 1
A.1.5.32 | CA0000-63-RPT-0001 | GDVQA1380 | GDVQA1385 | GDVQA1390 | 8405-PP-QA-032 | ENGINEERING CRITICALITY ASSESSMENT REPORT FOR PIPELINE WELDS | 1 | 2022-06-20 |  | 2022-08-04 |  | 2022-10-06 |  | 1
A.1.5.33 | CA0000-63-PRO-0016 | GDVQA1395 | GDVQA1400 | GDVQA1405 | 8405-PP-QA-033 | BASELINE SURVEY PROCEDURE | 1 | 2022-07-21 |  | 2022-08-18 |  | 2022-09-15 |  | 1
A.1.5.34 | CA0000-63-GDD-0001 | GDVQA1410 | GDVQA1415 | GDVQA1420 | 8405-PP-QA-034 | AUT / NDT PERSONNEL QUALIFICATIONS SUMMARY | 2 | 2022-07-21 |  | 2022-09-01 |  | 2022-10-13 |  | 2
A.1.5.35 | CA0000-63-PRO-0017 | GDVQA1520 | GDVQA1530 | GDVQA1540 | 8405-PP-QA-035 | INSTALLATION PROCEDURE FOR E&I WORKS | 1 | 2022-08-01 |  | 2022-08-29 |  | 2022-09-26 |  | 1
A.1.5.36 | CA0000-63-PLN-0005 | GDVQA1425 | GDVQA1430 | GDVQA1435 | 8405-PP-QA-036 | INSPECTION & TEST PLAN FOR ONSHORE CONSTRUCTION WORKS | 1 | 2022-05-18 |  | 2022-06-29 |  | 2022-08-15 |  | 1
A.1.5.37 | CA0000-63-PLN-0006 | GDVQA1440 | GDVQA1445 | GDVQA1450 | 8405-PP-QA-037 | INSPECTION & TEST PLAN FOR OFFSHORE CONSTRUCTION WORKS | 1 | 2022-08-18 |  | 2022-09-29 |  | 2022-11-10 |  | 1
A.1.5.38 | CA0000-63-PLN-0007 | GDVQA1550 | GDVQA1560 | GDVQA1570 | 8405-PP-QA-038 | INSPECTION AND TEST PLAN (MATERIAL RECEIVING INSPECTION) | 1 | 2022-07-18 |  | 2022-08-15 |  | 2022-09-12 |  | 1
A.1.5.39 | CA0000-63-PLN-0008 | GDVQA1455 | GDVQA1460 | GDVQA1465 | 8405-PP-QA-039 | STRUCTURAL NDT PLAN | 2 | 2022-05-25 |  | 2022-07-06 |  | 2022-08-15 |  | 2
A.1.5.40 | CA0000-63-GDD-0002 | GDVQA1470 | GDVQA1475 | GDVQA1480 | 8405-PP-QA-040 | PROCEDURE FOR DIGITIZATION OF RADIOGRAPHS (NPCC YARD & OFFSHORE WORKS) | 2 | 2022-06-08 |  | 2022-07-25 |  | 2022-09-05 |  | 2
A.1.5.41 | CA0000-63-PRO-0018 | GDVQA1485 | GDVQA1490 | GDVQA1495 | 8405-PP-QA-041 | HARDNESS TEST PROCEDURE | 2 | 2022-06-08 |  | 2022-07-25 |  | 2022-09-05 |  | 2
A.1.5.42 | CA0000-63-PRO-0019 | GDVQA1500 | GDVQA1505 | GDVQA1510 | 8405-PP-QA-042 | PIPELINE CAD (THERMIT) WELDING PROCEDURE | 1 | 2022-04-29 |  | 2022-06-15 |  | 2022-07-18 |  | 1
A.1.5.43 | CA0000-63-GDD-0003 | GDVQA1580 | GDVQA1590 | GDVQA1600 | 8405-PP-QA-043 | QC DOSSIER INDEX | 1 | 2022-08-15 |  | 2022-09-05 |  | 2022-09-26 |  | 1
A.1.5.44 | CA0000-63-SPE-0001 |  |  |  | 8405-PP-QA-044 | SPECIFICATION FOR POSITIVE MATERIAL IDENTIFICATION (PMI) | 1 | 2022-04-25 | [5 empty] | 1
A.1.5.45 | CA0000-63-SPE-0002 |  |  |  | 8405-PP-QA-045 | PROJECT WELDING SPECIFICATION | 1 | 2022-04-25 | [5 empty] | 1
A.1.5.46 | CA0000-63-PRO-0021 |  |  |  | 8405-PP-QA-047 | CA/PA PROCEDURE | 1 | [6 empty] | 1
A.1.5.47 | CA0000-63-LST-0001 |  |  |  | 8405-PP-QA-048 | LIST OF QUALITY OBJECTIVES AND KPIS | 2 | 2022-05-10 | [5 empty] | 2
A.1.5.48 | CA0000-63-PRO-0022 |  |  |  | 8405-PP-QA-049 | INSPECTION MANAGEMENT PROCEDURE | 1 | 2022-05-15 | [5 empty] | 1
A.1.5.49 | CA0000-63-GDD-0004 |  |  |  | 8405-PP-QA-050 | PROJECT QUALITY ORGANIZATION CHART | 2 | 2022-04-15 | [5 empty] | 2
A.1.5.50 | CA0000-63-PRO-0023 |  |  |  | 8405-PP-QA-051 | WELD NUMBERING PROCEDURES | 2 | 2022-06-10 | [5 empty] | 2
A.1.5.51 | CA0000-63-REP-0001 |  |  |  | 8405-PP-QA-052 | WELD MAP/S (REPORT) | 2 | [6 empty] | 2
A.1.5.52 | CA0000-63-REP-0002 |  |  |  | 8405-PP-QA-053 | PAINTING / COATING APPLICATOR QUALIFICATION RECORDS (REPORT) | 2 | [6 empty] | 2
A.1.5.53 | CA0000-63-PRO-024 |  |  |  | 8405-PP-QA-054 | CORRECTIVE & PREVENTIVE ACTION PROCEDURE | 2 | 2022-05-25 | [5 empty] | 2
A.1.6 | ONSHORE CONSTRUCTION
A.1.6.1 | CA0000-51-PRO-0001 |  |  |  | 8405-PP-ON-001 | HOT TAPPING PROCEDURE | 1 | 2023-08-10 | [5 empty] | 1
A.1.6.2 | CA0000-51-PRO-0002 | GDVYF1090 | GDVYF1095 | GDVYF1100 | 8405-PP-ON-002 | EQUIPMENT INSULATION PROCEDURE - HOT & COLD | 1 | 2022-06-15 |  | 2022-07-18 |  | 2022-08-19 |  | 1
A.1.6.3 | CA0000-51-PRO-0003 | GDVYF1105 | GDVYF1110 | GDVYF1115 | 8405-PP-ON-003 | HOT DIP GALVANIZING PROCEDURE | 1 | 2022-06-15 |  | 2022-07-18 |  | 2022-08-15 |  | 1
A.1.6.4 | CA0000-51-PRO-0004 | GDVYF1045 | GDVYF1050 | GDVYF1055 | 8405-PP-ON-004 | SURFACE PREPARATION AND PAINTING PROCEDURE | 1 | 2022-05-11 |  | 2022-06-08 |  | 2022-07-06 |  | 1
A.1.6.5 | CA0000-51-PRO-0005 | GDVYF1060 | GDVYF1065 | GDVYF1070 | 8405-PP-ON-005 | POST WELD HEAT TREATMENT (PWHT) PROCEDURE (PIPING) | 1 | 2022-05-18 |  | 2022-06-15 |  | 2022-07-18 |  | 1
A.1.6.6 | CA0000-51-PRO-0006 | GDVYF1120 | GDVYF1125 | GDVYF1130 | 8405-PP-ON-006 | PIPING FLUSHING, TESTING AND DRYING PROCEDURE | 1 | 2022-06-15 |  | 2022-07-18 |  | 2022-08-15 |  | 1
A.1.6.7 | CA0000-51-PRO-0007 | GDVYF1135 | GDVYF1140 | GDVYF1145 | 8405-PP-ON-007 | PASSIVE FIRE PROOFING PROCEDURE | 1 | 2022-06-15 |  | 2022-07-18 |  | 2022-08-15 |  | 1
A.1.6.8 | CA0000-51-GDD-0001 | GDVYF1150 | GDVYF1150 | GDVYF1150 | 8405-PP-ON-008 | COLOR CODING SYSTEM FOR PIPES | 2 | 2022-06-22 |  | 2022-07-18 |  | 2022-07-18 |  | 2
A.1.6.9 | CA0000-51-PRO-0008 | GDVYF1155 | GDVYF1155 | GDVYF1155 | 8405-PP-ON-009 | PIPING FLANGE MANAGEMENT PROCEDURE | 1 | 2022-06-29 |  | 2022-07-25 |  | 2022-07-25 |  | 1
A.1.6.10 | CA0000-51-MES-0001 | GDVYF1160 | GDVYF1160 | GDVYF1160 | 8405-PP-ON-010 | METHOD STATEMENT FOR RETESTING OF VALVES (VALVE SEAT / LEAK TESTING) | 1 | 2022-08-01 |  | 2022-08-22 |  | 2022-08-22 |  | 1
A.1.6.11 | CA0000-51-MES-0002 | GDVYF1165 | GDVYF1165 | GDVYF1165 | 8405-PP-ON-011 | METHOD STATEMENT FOR PIPE INSULATION AT ONSHORE AND OFFSHORE | 1 | 2022-08-15 |  | 2022-09-05 |  | 2022-09-05 |  | 1
A.1.6.12 | CA0000-51-PRO-0009 | GDVYF1000 | GDVYF1005 | GDVYF1010 | 8405-PP-ON-012 | STRUCTURAL FABRICATION AND ERECTION PROCEDURE | 1 | 2022-08-15 |  | 2022-05-18 |  | 2022-06-15 |  | 1
A.1.6.13 | CA0000-51-PRO-0010 | GDVYF1015 | GDVYF1020 | GDVYF1025 | 8405-PP-ON-013 | PIPING FABRICATION AND ERECTION PROCEDURE | 1 | 2022-04-22 |  | 2022-05-25 |  | 2022-07-18 |  | 1
A.1.6.14 | CA0000-51-PRO-0011 | GDVYF1215 | GDVYF1220 | GDVYF1225 | 8405-PP-ON-014 | WEIGHING PROCEDURE FOR JACKETS AND DECKS | 1 | 2022-06-15 |  | 2022-07-18 |  | 2022-08-15 |  | 1
A.1.6.15 | CA0000-51-PRO-0012 | GDVYF1230 | GDVYF1235 | GDVYF1240 | 8405-PP-ON-015 | LOAD OUT PROCEDURE FOR THE DECKS | 1 | 2022-08-29 |  | 2022-09-26 |  | 2022-10-24 |  | 1
A.1.6.16 | CA0000-51-PRO-0013 | GDVYF1030 | GDVYF1035 | GDVYF1040 | 8405-PP-ON-016 | DISTORTION (FREESPAN) CORRECTION PROCEDURE | 1 | 2022-04-29 |  | 2022-06-01 |  | 2022-06-29 |  | 1
A.1.6.17 | CA0000-51-PRO-0014 | GDVYF1200 | GDVYF1205 | GDVYF1210 | 8405-PP-ON-017 | FABRICATION PROCEDURE FOR PRESSURE VESSELS | 1 | 2022-06-15 |  | 2022-07-13 |  | 2022-08-05 |  | 1
A.1.6.18 | CA0000-51-MES-0003 | GDVYF1185 | GDVYF1190 | GDVYF1195 | 8405-PP-ON-018 | METHOD STATEMENT FOR COLD BENDING OF J-TUBE BENDS | 1 | 2022-06-15 |  | 2022-07-18 |  | 2022-08-01 |  | 1
A.1.6.19 | CA0000-51-PRO-0015 | GDVYF1170 | GDVYF1175 | GDVYF1180 | 8405-PP-ON-019 | PROCEDURE FOR PWHT OF STRUCTURAL WORKS AT SITE (FIELD JOINTS) | 1 | 2022-04-29 |  | 2022-06-01 |  | 2022-08-10 |  | 1
A.1.6.20 | CA0000-51-PRO-0016 | GDVYF1245 | GDVYF1250 | GDVYF1255 | 8405-PP-ON-020 | GROSS AIR LEAK TEST PROCEDURE | 1 | 2022-06-15 |  | 2022-07-18 |  | 2022-08-15 |  | 1
A.1.6.21 | CA0000-59-GDD-0002 |  |  |  | 8405-PP-GE-046 | TEMPORARY SITE FACILITIES LAYOUT WITH RELATED TEMPORARY SERVICES DETAILS (TO INCLUDE OFFICES, WORKSHOPS, WAREHOUSES, ETC. | 2 | 2022-06-13 | [5 empty] | 2
A.1.7 | OFFSHORE CONSTRUCTION
A.1.7.1 | CA0000-51-PRO-0017 | GDVOF1000 | GDVOF1005 | GDVOF1010 | 8405-PP-OF-001 | PRE-ENGINEERING GEOPHYSICAL SURVEY PROCEDURE | 1 | 2022-01-19 | 2022-01-13 | 2022-02-23 | 2022-03-07 | 2022-03-07 |  | 1
A.1.7.2 | CA0000-51-PRO-0018 | GDVOF1015 | GDVOF1020 | GDVOF1025 | 8405-PP-OF-002 | PRE-ENGINEERING GEOTECHNICAL SURVEY PROCEDURE | 1 | 2022-01-19 | 2022-01-14 | 2022-02-14 |  | 2022-02-24 |  | 1
A.1.7.3 | CA0000-51-RPT-0001 | GDVOF1030 | GDVOF1030 | GDVOF1030 | 8405-PP-OF-003 | GEOTECHNICAL FACTUAL REPORT | 3 | 2022-04-06 |  | 2022-04-27 |  | 2022-04-27 |  | 3
A.1.7.4 | CA0000-51-PRO-0019 | GDVOF1035 | GDVOF1040 | GDVOF1045 | 8405-PP-OF-004 | PRE-ENGINEERING JACKET FACE DIVING SURVEY PROCEDURE | 1 | 2022-02-02 | 2022-01-10 | 2022-03-02 |  | 2022-03-23 |  | 1
A.1.7.5 | CA0000-51-PRO-0020 | GDVOF1065 | GDVOF1070 | GDVOF1075 | 8405-PP-OF-005 | PRE-ENGINEERING ROV SURVEY PROCEDURE (JACKET FACE SURVEY, PLATFORM APPROACH & CROSSING) | 1 | 2022-02-16 | 2022-01-29 | 2022-03-03 | 2022-03-02 | 2022-03-17 |  | 1
A.1.7.6 | CA0000-51-PRO-0021 | GDVOF1645 | GDVOF1655 | GDVOF1665 | 8405-PP-OF-006 | PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY PROCEDURE | 1 | 2022-06-13 |  | 2022-07-15 |  | 2022-08-12 |  | 1
A.1.7.7 | CA0000-51-PRO-0022 | GDVOF1050 | GDVOF1055 | GDVOF1060 | 8405-PP-OF-007 | POSITIONING AND INSTALLATION SURVEY PROCEDURE | 1 | 2022-08-30 |  | 2022-09-20 |  | 2022-10-11 |  | 1
A.1.7.8 | CA0000-51-PRO-0023 | GDVOF1100 | GDVOF1105 | GDVOF1110 | 8405-PP-OF-008 | PIPELINE BASELINE SURVEY PROCEDURE | 1 | 2022-05-23 |  | 2022-06-20 |  | 2022-07-21 |  | 1
A.1.7.9 | CA0000-51-RPT-0002 | GDVOF1120 | GDVOF1125 | GDVOF1130 | 8405-PP-OF-009 | PIPELINE BASELINE SURVEY REPORT | 1 | 2024-01-31 |  | 2024-02-29 |  | 2024-03-28 |  | 1
A.1.7.10 | CA0000-51-RPT-0003 | GDVOF1085 | GDVOF1085 | GDVOF1085 | 8405-PP-OF-010 | PRE-ENGINEERING GEOPHYSICAL SURVEY REPORT | 1 | 106/04/22 |  | 2022-04-26 |  | 2022-04-26 |  | 1
A.1.7.11 | CA0000-51-RPT-0004 |  |  |  | 8405-PP-OF-011 | PRE-ENGINEERING GEOTECHNICAL SURVEY REPORT | 1 | [6 empty] | 1
A.1.7.12 | CA0000-51-RPT-0005 | GDVOF1095 | GDVOF1095 | GDVOF1095 | 8405-PP-OF-012 | PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY REPORT | 2 | 2022-12-08 |  | 2022-12-16 |  | 2022-12-16 |  | 2
A.1.7.13 | CA0000-51-RPT-0006 | GDVOF1090 | GDVOF1090 | GDVOF1090 | 8405-PP-OF-013 | PRE-ENGINEERING ROV/CROSSING SURVEY REPORT | 2 | 2022-04-29 |  | 2022-05-26 |  | 2022-05-26 |  | 2
A.1.7.14 | CA0000-51-PRO-0024 | GDVOF1140 | GDVOF1145 | GDVOF1150 | 8405-PP-OF-014 | PIPELINE/CABLE/UMBILICAL AS-BUILT SURVEY PROCEDURE | 1 | 2022-07-21 |  | 2022-08-18 |  | 2022-09-12 |  | 1
A.1.7.15 | CA0000-51-PRO-0025 | GDVOF1155 | GDVOF1160 | GDVOF1165 | 8405-PP-OF-015 | PIPELINE/CABLE/UMBILICAL AS LAID SURVEY PROCEDURE | 1 | 2022-07-21 |  | 2022-08-18 |  | 2022-09-12 |  | 1
A.1.7.16 | CA0000-51-RPT-0007 | GDVOF1135 | GDVOF1135 | GDVOF1135 | 8405-PP-OF-016 | PIPELINE/CABLE/UMBILICAL AS-BUILT SURVEY REPORT | 2 | 2022-04-05 |  | 2024-04-30 |  | 2024-04-30 |  | 2
A.1.7.17 | CA0000-51-RPT-0008 | GDVOF1115 | GDVOF1115 | GDVOF1115 | 8405-PP-OF-017 | PIPELINE/CABLE/UMBILICAL AS LAID SURVEY REPORT | 2 | 2022-04-08 |  | 2024-04-30 |  | 2024-04-30 |  | 2
A.1.7.18 | CA0000-51-PRO-0026 | GDVOF1170 | GDVOF1175 | GDVOF1180 | 8405-PP-OF-018 | ANCHOR HANDLING PROCEDURE FOR GRAVITY ANCHORS BY HAMMER HEAD CRANE VESSEL | 1 | 2022-07-21 |  | 2022-08-18 |  | 2022-09-12 |  | 1
A.1.7.19 | CA0000-51-PRO-0027 | GDVOF1185 | GDVOF1190 | GDVOF1195 | 8405-PP-OF-019 | ANCHOR HANDLING AND MOORING PROCEDURE FOR WORK BOATS | 1 | 2022-07-21 |  | 2022-08-18 |  | 2022-09-15 |  | 1
A.1.7.20 | CA0000-51-PRO-0028 | GDVOF1200 | GDVOF1205 | GDVOF1210 | 8405-PP-OF-020 | ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | 1 | 2022-08-24 |  | 2022-09-21 |  | 2022-10-14 |  | 1
A.1.7.21 | CA0000-51-PRO-0029 | GDVOF1215 | GDVOF1220 | GDVOF1225 | 8405-PP-OF-021 | ANCHOR HANDLING AND MOORING PROCEDURE FOR JACK UP BARGES | 1 | 2022-08-30 |  | 2022-09-27 |  | 2022-10-13 |  | 1
A.1.7.22 | CA0000-51-PRO-0030 | GDVOF1230 | GDVOF1235 | GDVOF1240 | 8405-PP-OF-022 | FREE SPANS CORRECTION PROCEURE | 1 | 2022-07-27 |  | 2022-08-24 |  | 2022-09-21 |  | 1
A.1.7.23 | CA0000-51-PRO-0031 | GDVOF1265 | GDVOF1270 | GDVOF1275 | 8405-PP-OF-023 | SLEEPERS/MATTRESS/GROUT BAG INSTALLATION PROCEDURES | 1 | 2022-07-27 |  | 2022-08-17 |  | 2022-09-28 |  | 1
A.1.7.24 | CA0000-51-PRO-0032 | GDVOF1245 | GDVOF1250 | GDVOF1255 | 8405-PP-OF-024 | PIPELINE INFILL MATERIAL FIELD JOINT COATING PROCEDURE | 1 | 2022-07-27 |  | 2022-08-24 |  | 2022-09-21 |  | 1
A.1.7.25 | CA0000-51-PRO-0033 | GDVOF1280 | GDVOF1285 | GDVOF1290 | 8405-PP-OF-025 | PIPELINE ANTI-CORROSION FIELD JOINT COATING PROCEDURE | 1 | 2022-08-24 |  | 2022-09-14 |  | 2022-09-30 |  | 1
A.1.7.26 | CA0000-51-MAN-0001 | GDVOF1295 | GDVOF1300 | GDVOF1305 | 8405-PP-OF-026 | PIPELINES INSTALLATION MANUAL | 2 | 2022-08-30 |  | 2022-09-27 |  | 2022-10-17 |  | 2
A.1.7.27 | CA0000-51-PRO-0034 |  |  |  | 8405-PP-OF-027 | UMBILICALS INSTALLATION MANUAL | 1 | 2023-08-12 | [5 empty] | 1
A.1.7.29 | CA0000-51-PRO-0036 | GDVOF1340 | GDVOF1345 | GDVOF1350 | 8405-PP-OF-029 | CABLE INSTALLATION MANUAL | 1 | 2022-08-30 |  | 2022-09-27 |  | 2022-11-08 |  | 1
A.1.7.30 | CA0000-51-PRO-0037 | GDVOF1355 | GDVOF1360 | GDVOF1365 | 8405-PP-OF-030 | ZIRKU ISLAND PIPELINES SHORE PULL PROCEDURE | 1 | 2022-08-30 |  | 2022-09-13 |  | 2022-09-27 |  | 1
A.1.7.31 | CA0000-51-PRO-0055 |  |  |  | 8405-PP-ON-021 | ARZANAH ISLAND (AT EAST SIDE) PIPELINES SHORE PULL PROCEDURE | 1 | 2023-01-06 | [5 empty] | 1
A.1.7.32 | CA0000-51-PRO-0056 |  |  |  | 8405-PP-ON-022 | ARZANAH ISLAND (AT SOUTH SIDE) PIPELINES SHORE PULL PROCEDURE | 1 | 2023-01-06 | [5 empty] | 1
A.1.7.31 | CA0000-51-PRO-0038 | GDVOF1370 | GDVOF1375 | GDVOF1380 | 8405-PP-OF-031 | RISER (STALK-IN) INSTALLATION PROCEDURE | 1 | 2022-08-30 |  | 2022-09-27 |  | 2022-10-13 |  | 1
A.1.7.32 | CA0000-51-PRO-0039 | GDVOF1385 | GDVOF1390 | GDVOF1395 | 8405-PP-OF-032 | MID LINE SURFCAE TIE IN(s) INSTALLATION PROCEDURE | 1 | 2022-08-30 |  | 2022-09-27 |  | 2022-10-13 |  | 1
A.1.7.33 | CA0000-51-PRO-0040 | GDVOF1400 | GDVOF1405 | GDVOF1410 | 8405-PP-OF-033 | J-TUBE AND ASSOCIATED CLAMPS INSTALLATION PROCEDURE | 1 | 2022-05-30 |  | 2022-06-27 |  | 2022-07-28 |  | 1
A.1.7.34 | CA0000-51-PRO-0041 | GDVOF1415 | GDVOF1420 | GDVOF1425 | 8405-PP-OF-034 | NEW WHP-10 DECK INSTALLATION PROCEDURE | 1 | 2022-05-30 |  | 2022-06-27 |  | 2022-07-28 |  | 1
A.1.7.36 | CA0000-51-PRO-0043 | GDVOF1445 | GDVOF1450 | GDVOF1455 | 8405-PP-OF-036 | DEMOLITION OF EXISTING DECK AND NEW DECK INSTALLATION PROCEDURE FOR HD-3 | 1 | 2022-05-30 |  | 2022-06-27 |  | 2022-07-28 |  | 1
A.1.7.38 | CA0000-51-PRO-0045 | GDVOF1475 | GDVOF1480 | GDVOF1485 | 8405-PP-OF-038 | PIPELINES FLOODING, GAUGING, CLEANING AND HYDROTESTING PROCEDURE | 1 | 2022-06-06 |  | 2022-07-04 |  | 2022-08-04 |  | 1
A.1.7.41 | CA0000-51-MES-0004 | GDVOF1520 | GDVOF1525 | GDVOF1530 | 8405-PP-OF-041 | METHOD STATEMENT FOR CIVIL WORKS FOR SHOREPULL | 1 | 2022-08-24 |  | 2022-09-21 |  | 2022-10-19 |  | 1
A.1.7.42 | CA0000-51-PRO-0048 | GDVOF1535 | GDVOF1540 | GDVOF1545 | 8405-PP-OF-042 | OFFSHORE HOOK-UP PROCEDURE | 1 | 2022-08-24 |  | 2022-09-21 |  | 2022-10-19 |  | 1
A.1.7.43 | CA0000-51-PRO-0049 | GDVOF1550 | GDVOF1555 | GDVOF1560 | 8405-PP-OF-043 | PIPELINES CALIPER PIGGING PROCEDURE | 1 | 2022-08-25 |  | 2022-09-22 |  | 2022-10-20 |  | 1
A.1.7.44 | CA0000-51-PRO-0050 | GDVOF1565 | GDVOF1570 | GDVOF1575 | 8405-PP-OF-044 | PIPELINES Intelligent PIGGING PROCEDURE | 1 | 2022-08-30 |  | 2022-09-27 |  | 2022-10-18 |  | 1
A.1.7.45 | CA0000-51-PRO-0051 | GDVOF1580 | GDVOF1585 | GDVOF1590 | 8405-PP-OF-045 | PIPELINES DEWATERING, DRYING AND NITROGEN PURGING PROCEDURE | 1 | 2022-08-30 |  | 2022-09-27 |  | 2022-10-18 |  | 1
A.1.7.46 | CA0000-51-PRO-0052 | GDVOF1595 | GDVOF1600 | GDVOF1605 | 8405-PP-OF-046 | CABLE TRANSPOOLIING PROCEDURE | 2 | 2022-09-06 |  | 2022-10-04 |  | 2022-11-01 |  | 2
A.1.7.47 | CA0000-51-PRO-0053 | GDVOF1610 | GDVOF1615 | GDVOF1620 | 8405-PP-OF-047 | UMBILICAL TRANSPOOLIING PROCEDURE | 1 | 2022-09-27 |  | 2022-10-25 |  | 2022-11-22 |  | 1
A.1.7.48 | CA0000-51-PRO-0054 | GDVOF1625 | GDVOF1630 | GDVOF1635 | 8405-PP-OF-048 | TRENCHING & BACKFILLING PROCEDURE | 1 | 2022-08-03 |  | 2022-08-31 |  | 2022-09-28 |  | 1
A.1.7.49 | CA0000-51-PRO-0057 |  |  |  | 8405-PP-OF-049 | 3D LASER SCAN SURVEY PROCEDURE | 2 | 2022-03-30 | [5 empty] | 2
A.1.7.50 | CA0000-51-PRO-0058 |  |  |  | 8405-PP-OF-050 | ROV AS-BUILT SURVEY PROCEDURE | 1 | 2022-03-02 | [5 empty] | 1
A.1.7.51 | CA0000-51-PRO-0059 |  |  |  | 8405-PP-OF-051 | UMBILICAL PROTECTION, PACKAGING, STORAGE AND TRANSPORTATION GUIDELINES / PROCEDURES. | 1 | 2022-05-02 | [5 empty] | 1
A.1.7.52 | CA0000-51-PRO-0060 |  |  |  | 8405-PP-OF-052 | UMBILICAL HANDLING, PULL-IN & HOOK-UP PROCEDURES / GUIDELINES. | 1 | 2023-08-12 | [5 empty] | 1
A.1.7.53 | CA0000-51-PRO-0061 |  |  |  | 8405-PP-OF-053 | PIPELINE PRESERVATION PROCEDURE | 1 | 2023-04-10 | [5 empty] | 1
A.1.7.54 | CA0000-52-REP-0002 |  |  |  | 8405-PP-HS-024 | CONSTRUCTION BARGE QRA/SAFETY CASE (REPORT) | 1 (Old Barges approval) | [6 empty] | 1 (Old Barges approval)
A.1.7.55 | CA0000-51-SOW-0001 |  |  |  | 8405-PP-OF-054 | SCOPE OF WORK FOR TRANSPORTATIONOF UMBILICALS FROM VENDOR
A.1.8 | COMMISSIONING
A.1.8.1 | CA0000-54-REG-0001 | GDVCG1000 | GDVCG1005 | GDVCG1010 | 8405-PP-CM-001 | COMMISSIONING DELIVERABLE REGISTER | 2 | 2022-06-15 |  | 2022-08-01 |  | 2022-09-12 |  | 2
A.1.8.2 | CA0000-54-PRO-0001 | GDVCG1015 | GDVCG1020 | GDVCG1025 | 8405-PP-CM-002 | PRECOMMISSIONING AND COMMISSIONING PROCEDURE | 1 | 2022-06-22 |  | 2022-08-08 |  | 2022-09-19 |  | 1
A.1.8.3 | CA0000-54-LST-0001 | GDVCG1030 | GDVCG1035 | GDVCG1040 | 8405-PP-CM-003 | SYSTEM / SUBSYSTEM LIST | 1 | 2022-07-06 |  | 2022-08-22 |  | 2022-10-03 |  | 1
A.1.8.4 | CA0000-54-PRO-0002 | GDVCG1045 | GDVCG1050 | GDVCG1055 | 8405-PP-CM-004 | PERMIT TO WORK (PTW) PROCEDURE | 1 | 2022-07-25 |  | 2022-09-05 |  | 2022-10-17 |  | 1
A.1.8.5 | CA0000-54-PLN-0002 | GDVCG1150 | GDVCG1150 | GDVCG1150 | 8405-PP-CM-005 | VENDOR MOBILIZATION PLAN | 3 | 2022-08-01 |  | 2022-09-05 |  | 2022-09-05 |  | 3
A.1.8.6 | CA0000-54-PRO-0003 | GDVCG1075 | GDVCG1080 | GDVCG1085 | 8405-PP-CM-006 | LIST OF OPERATIONAL TEST PROCEDURES | 1 | 2022-07-25 |  | 2022-09-05 |  | 2022-10-17 |  | 1
A.1.8.7 | CA0000-54-PRO-0004 | GDVCG1090 | GDVCG1095 | GDVCG1100 | 8405-PP-CM-007 | PUNCH LIST PROCEDURE | 1 | 2022-07-25 |  | 2022-09-05 |  | 2022-10-03 |  | 1
A.1.8.8 | CA0000-54-PRO-0005 | GDVCG1105 | GDVCG1110 | GDVCG1115 | 8405-PP-CM-008 | PRE-COMMISSIONING / COMMISSIONING TEST RECORDS AND RESPONSIBILITY MATRIX | 2 | 2022-07-25 |  | 2022-09-05 |  | 2022-10-17 |  | 2
A.1.8.9 | CA0000-54-PRO-0006 | GDVCG1120 | GDVCG1125 | GDVCG1130 | 8405-PP-CM-009 | CO-CONSOLE PROCEDURE | 2 | 2022-07-18 |  | 2022-08-29 |  | 2022-10-10 |  | 2
A.1.8.10 | CA0000-54-GDD-0001 | GDVCG1135 | GDVCG1140 | GDVCG1145 | 8405-PP-CM-010 | FIRST FILL INVENTORY, CONSUMPTION AND TOP UP SCHEDULE (INCLUDING CHEMICALS, HYDRAULIC OIL) | 1 | 2022-07-25 |  | 2022-09-05 |  | 2022-10-12 |  | 1
A.1.8.11 | CA0000-54-PLN-0001 | GDVCG1155 | GDVCG1160 | GDVCG1165 | 8405-PP-CM-011 | COMMISSIONING EXECUTION PLAN | 1 | 2022-07-25 |  | 2022-09-05 |  | 2022-10-17 |  | 1
A.1.8.12 | CA0000-54-PRO-0007 | GDVCG1170 | GDVCG1175 | GDVCG1180 | 8405-PP-CM-012 | N2-HE LEAK TEST & Inserting PROCEDURE | 1 | 2022-07-25 |  | 2022-09-05 |  | 2022-10-17 |  | 1
A.1.8.13 | CA0000-54-PRO-0008 | GDVCG1185 | GDVCG1190 | GDVCG1195 | 8405-PP-CM-013 | HANDOVER PROCEDURE | 1 | 2022-11-28 |  | 2023-01-11 |  | 2023-02-22 |  | 1
A.1.8.14 | CA0000-54-MES-0001 | GDVCG1200 | GDVCG1205 | GDVCG1210 | 8405-PP-CM-014 | METHOD STATEMENT FOR INSTRUMENT LOOP CHECKS & FUNCTION TESTS RELATED TO DCS, ESD AND F&G SYSTEMS | 1 | 2022-07-25 |  | 2022-08-31 |  | 2022-10-17 |  | 1
A.1.8.15 | CA0000-54-PRO-0009 | GDVCG1220 | GDVCG1220 | GDVCG1220 | 8405-PP-CM-015 | PROJECT PRESERVATION PROCEDURE | 1 | 2022-10-24 |  | 2022-11-14 |  | 2022-11-14 |  | 1
A.1.8.16 | CA0000-54-PRO-0010 | GDVCG1215 | GDVCG1225 | GDVCG1230 | 8405-PP-CM-016 | SYSTEM OPERATION TEST PROCEDURES | 1 | 2022-11-14 |  | 2022-12-28 |  | 2023-02-08 |  | 1
A.1.8.17 | CA0000-54-LST-0002 | GDVCG1235 | GDVCG1240 | GDVCG1245 | 8405-PP-CM-017 | LIST OF SPECIAL TOOLS AND CONSUMABLES | 2 | 2022-10-17 |  | 2022-11-28 |  | 2023-01-11 |  | 2
A.1.8.18 | CA0000-54-LST-0003 | GDVCG1250 | GDVCG1255 | GDVCG1260 | 8405-PP-CM-018 | LIST OF COMMISSIONING SPARE PARTS | 1 | 2022-11-14 |  | 2022-12-28 |  | 2023-02-22 |  | 1
A.1.8.19 | CA0000-54-GDD-0002 | GDVCG1265 | GDVCG1270 | GDVCG1275 | 8405-PP-CM-019 | PERFORMANCE TEST | 1 | 2022-12-14 |  | 2023-01-25 |  | 2023-03-08 |  | 1
A.1.8.20 | CA0000-54-PRO-0011 | GDVCG1280 | GDVCG1285 | GDVCG1290 | 8405-PP-CM-020 | START-UP PROCEDURE | 1 | 2023-01-11 |  | 2023-02-22 |  | 2023-04-05 |  | 1
A.1.8.21 | CA0000-54-PRO-0012 | GDVCG1060 | GDVCG1065 | GDVCG1070 | 8405-PP-CM-021 | COMMISSIONING PERMIT TO WORK (PTW) PROCEDURE | 1 | 2022-07-25 |  | 2022-09-05 |  | 2022-10-17 |  | 1
A.1.8.22 | CA0000-54-PRO-0013 |  |  |  | 8405-PP-CM-022 | PRE-START-UP ACTIVITIES PROCEDURE | 1 | [6 empty] | 1
A.1.8.23 | CA0000-54-PRO-0014 |  |  |  | 8405-PP-CM-023 | AS COMMISSIONED DOCUMENTATION PROCEDURE | 1 | [6 empty] | 1
A.1.8.24 | CA0000-54-PRO-0015 |  |  |  | 8405-PP-CM-024 | MODIFICATIONS PROCEDURE | 1 | [6 empty] | 1
A.1.8.25 | CA0000-54-COD-0001 |  |  |  | 8405-PP-CM-025 | RFC/RFSU & HAND OVER DOSSIER | 1 | [6 empty] | 1
A.1.8.26 | CA0000-54-PHL-0001 |  |  |  | 8405-PP-CM-026 | MANNING PHILOSOPHY | 1 | [6 empty] | 1
A.1.8.27 | CA0000-54-PRO-0016 |  |  |  | 8405-PP-CM-027 | SAT (SITE ACCEPTANCE TEST) PROCEDURE AND REPORT. | 1 | [6 empty] | 1
A.1.8.28 | CA0000-54-PRO-0017 |  |  |  | 8405-PP-CM-028 | ISOLATION PLAN / PROCEDURES | 1 | [6 empty] | 1
A.1.8.29 | CA0000-54-REP-0001 |  |  |  | 8405-PP-CM-029 | CMMS INCLUDING DATA ENTRY TO SAP SYSTEM | 1 | [6 empty] | 1
A.1.8.30 | CA0000-54-PRO-0018 |  |  |  | 8405-PP-CM-030 | LOCK-OUT / TAG-OUT PROCEDURE | 1 | [6 empty] | 1
A.1.8.31 | CA0000-54-PRO-0019 |  |  |  | 8405-PP-CM-031 | CONSTRUCTION & COMMISSIONING PTW BRIDGING DOCUMENT | 1 | [6 empty] | 1
A.1.8.32 | CA0000-54-DWG-0001 |  |  |  | 8405-PP-CM-032 | MARKED-UP CRITICAL DRAWINGS AND DOCUMENTS | 1 | [6 empty] | 1

## P6_Data (hidden)
Activity Step Count | Activity ID | Activity Name | Org Dur | Early Start | Early Finish | Late Start | Late Finish | Total Float
EPC FOR DALMA GAS DEVELOPMENT PROJECT |  |  | 1159 | 2021-12-19 | 2025-02-20 | 2021-12-19 | 2025-03-22 | 31
MILESTONE |  |  | 1159 | 2021-12-19 | 2025-02-20 | 2021-12-19 | 2025-03-22 | 31
PROJECT MILESTONES |  |  | 1159 | 2021-12-19 | 2025-02-20 | 2021-12-19 | 2025-03-22 | 31
0 | MS1010 | EFFECTIVE/COMMENCEMENT DATE | 0 | 2021-12-19 |  | 2021-12-19 |  | 0
0 | MSGENA02 | APPROVED PLANNING DOSSIER COVERING - BASELINE SCHEDULE, MILESTONE COMPLETION SCHEDULE, PROJECT CONTROL PROCEDURES ETC. | 0 |  | 2022-03-07 |  | 2022-03-07 | 0
0 | MSCONF14 | COMPLETION OF PRE- COMM & MC OF ALL PIPELINES INCL. COMPOSITE & FO CABLES | 0 |  | 2024-03-24 |  | 2024-04-21 | 28
0 | MSCONF15 | COMPLETION OF PRE- COMMISSIONING & MECHANICAL COMPLETION OF ALL UMBILICAL'S | 0 |  | 2024-04-01 |  | 2024-04-21 | 20
0 | MSCONF16 | COMPLETION OF PRE- COMM & MC OF ALL WHT'S (ST-10,HD-03, BH-03 & HD-T4) | 0 |  | 2024-04-07 |  | 2024-05-21 | 44
0 | MS1070 | M 1 - RFSU FOR OFFSHORE FACILITIES AT ST-10 | 0 |  | 2024-05-21 |  | 2024-05-21 | 0
0 | MS1100 | M 2 - RFSU FOR OFFSHORE FACILITIES AT BH-03 | 0 |  | 2024-05-21 |  | 2024-05-21 | 0
0 | MS1060 | M 3 - RFSU FOR OFFSHORE FACILITIES AT HD-03 | 0 |  | 2024-07-21 |  | 2024-07-21 | 0
0 | MS1130 | M 4 - RFSU FOR OFFSHORE FACILITIES AT HDT-04 | 0 |  | 2024-08-23 |  | 2024-09-20 | 28
0 | MS2030 | M 5 - COMPLETE TEST RUN & ACHIEVE PAC FOR ALL WHT'S PIPELINES & UMBILICAL | 0 |  | 2025-02-20 |  | 2025-03-22 | 31
CONTRACTUAL COMPLETION MILESTONE |  |  | 1119 | 2022-01-28 | 2025-02-20 | 2022-04-29 | 2025-03-22 | 31
GENERAL |  |  | 138 | 2022-04-04 | 2022-10-20 | 2022-07-20 | 2023-03-08 | 97
0 | MSGENA01 | ISSUE PROJECT EXECUTION PLAN, COORDINATION PROCEDURE, ENGG, PROCUREMENT PROCEDURES, HSE/QUALITY PLANS -FINAL ISSUE | 0 |  | 2022-04-04 |  | 2022-07-20 | 72
0 | MSGENA03 | ISSUE CONSTRUCTION EXECUTION PLAN/ PROCEDURES/ METHOD STATEMENTS ALONG WITH TIE-IN/ SHUTDOWN PHILOSOPHY, ETC | 0 |  | 2022-08-19 |  | 2022-12-21 | 87
0 | MSGENA04 | ISSUE HYDROTESTING, DRYING, PURGING, PRE-COMM, COMMISSIONING & DEMOLITION PROCEDURES - FINAL ISSUE | 0 |  | 2022-10-20 |  | 2023-03-08 | 97
DETAIL ENGINEERING |  |  | 246 | 2022-01-28 | 2023-01-19 | 2022-05-20 | 2023-04-27 | 69
0 | MSDEEB22 | ISSUE IST MTO AND MRS FOR STRUCTURAL STEEL BULK MATERIALS FOR ALL AREAS. | 0 |  | 2022-01-28 |  | 2022-07-22 | 120
0 | MSDEEB14 | ISSUE IST MTO AND MRS FOR LINE PIPES | 0 |  | 2022-02-17 |  | 2022-05-20 | 64
0 | MSDEEB15 | ISSUE FINAL MTO AND MRS FOR LINE PIPES | 0 |  | 2022-04-04 |  | 2022-06-02 | 41
0 | MSDEEB16 | ISSUE IST MTO AND MRS FOR ALL BALANCE PIPELINE MATERIALS | 0 |  | 2022-04-19 |  | 2022-09-20 | 105
0 | MSDEEB01 | PREPARE DESIGN BASIS FOR ALL ENGINEERING DISCIPLINES AND ISSUE TO COMPANY - FINAL ISSUE | 0 |  | 2022-04-20 |  | 2022-07-22 | 62
0 | MSDEEB18 | ISSUE IST MTO AND MRS FOR ALL PIPING BULK MATERIALS | 0 |  | 2022-04-26 |  | 2022-09-01 | 87
0 | MSDEEB05 | COMPLETE 30% MODELLING FOR OFFSHORE FACILITIES | 0 |  | 2022-05-19 |  | 2022-08-03 | 52
0 | MSDEEB02 | PRE-ENGG SURVEY (TOPO/BATH/SOIL INVESTIGATION) & SUBMIT FINAL REPORTS, P/L ROUTE ALIGNMENT SHEETS & ROUTE MAPS (IFC) | 0 |  | 2022-05-19 |  | 2022-08-17 | 61
0 | MSDEEB17 | ISSUE FINAL MTO AND MRS FOR ALL BALANCE PIPELINE MATERIALS | 0 |  | 2022-05-20 |  | 2022-09-05 | 74
0 | MSDEEB12 | ISSUE MRS FOR ALL MECHANICAL EQUIPMENT & PACKAGES - FINAL | 0 |  | 2022-06-14 |  | 2022-09-07 | 59
0 | MSDEEB04 | ISSUE PFDS, P&IDS, PLOT PLANS, EQUIPMENT LAYOUTS AND EQUIPMENT LIST, FOR ALL FACILITIES FOR HAZOP | 0 |  | 2022-06-15 |  | 2022-08-26 | 50
0 | MSDEEB13 | ISSUE MRS FOR ALL E&I EQUIPMENT & PACKAGES - FINAL | 0 |  | 2022-06-16 |  | 2022-09-07 | 57
0 | MSDEEB03. | OBTAIN FINAL ROUTE APPROVAL FROM AUTHORITIES | 0 |  | 2022-06-20 |  | 2022-09-15 | 61
0 | MSDEEB06 | COMPLETE P&IDS, PLOT PLANS REVIEW | 0 |  | 2022-06-20 |  | 2022-10-19 | 85
0 | MSDEEB20 | ISSUE IST MTO AND MRS FOR ALL E&I BULK MATERIALS | 0 |  | 2022-06-20 |  | 2023-01-19 | 149
0 | MSDEEB07 | COMPLETE HAZOP/ SIL REVIEW & SUBMIT FINAL REPORT AFTER INCORPORATING COMPANY COMMENTS (FINAL ISSUE) | 0 |  | 2022-08-04 |  | 2022-12-15 | 94
0 | MSDEEB23 | ISSUE FINAL MTO AND MRS FOR STRUCTURAL STEEL BULK MATERIALS FOR ALL AREAS. | 0 |  | 2022-08-04 |  | 2022-11-23 | 80
0 | MSDEEB09A | COMPLETE HSEIA & QRA, AFTER REVIEW / APPROVAL BY COMPANY AND SUBMIT FINAL REPORTS | 0 |  | 2022-08-19 |  | 2022-12-14 | 82
0 | MSDEEB10 | COMPLETE 60% MODELLING FOR OFFSHORE FACILITIES | 0 |  | 2022-08-22 |  | 2022-10-26 | 48
0 | MSDEEB19 | ISSUE FINAL MTO AND MRS FOR ALL PIPING BULK MATERIALS | 0 |  | 2022-08-31 |  | 2023-01-06 | 91
0 | MSDEEB08A | ISSUE PFDS/P&IDS/PLOT PLANS/EQT LAYOUTS/DATA SHEETS/EQT LIST FOR ALL FACILITIE AFTER INCORP. HAZOP COMMENTS-CRITICAL IFC | 0 |  | 2022-09-02 |  | 2023-01-18 | 97
0 | MSDEEB09 | COMPLETE HSEIA & QRA, AFTER REVIEW / APPROVAL BY COMPANY AND SUBMIT CRITICAL FINAL REPORTS | 0 |  | 2022-09-19 |  | 2023-01-04 | 76
0 | MSDEEB11 | ISSUE IFC TIE-IN SCHEDULE & DETAILS FOR ALL NEW FACILITIES. | 0 |  | 2022-09-19 |  | 2023-04-27 | 155
0 | MSDEEB21 | ISSUE FINAL MTO AND MRS FOR ALL E&I BULK MATERIALS | 0 |  | 2022-09-19 |  | 2023-02-02 | 97
0 | MSDEEB27 | ISSUE DRAWINGS FOR ALL PIPELINES & UMBILICAL'S CROSSINGS - IFC | 0 |  | 2022-10-19 |  | 2023-04-27 | 132
0 | MSDEEB25 | ISSUE SLD, HAZARDOUS AREA CLASSIFICATION DETAILS FOR ALL WHT'S - IFC | 0 |  | 2022-10-20 |  | 2023-04-27 | 132
0 | MSDEEB26A | ISSUE ELECTRICAL & INSTRUMENT CABLE SCHEDULES, CABLE LAYOUTS, EARTHING LAYOUTS, FOR WHT'S - CRITICAL IFC | 0 |  | 2022-10-20 |  | 2023-04-27 | 132
0 | MSDEEB26 | ISSUE ELECTRICAL & INSTRUMENT CABLE SCHEDULES, CABLE LAYOUTS, EARTHING LAYOUTS, FOR WHT'S - IFC | 0 |  | 2022-11-17 |  | 2023-04-27 | 112
0 | MSDEEB29 | COMPLETE 90% MODELLING FOR OFFSHORE FACILITIES | 0 |  | 2022-11-21 |  | 2023-02-06 | 54
0 | MSDEEB28 | ISSUE ALIGNMENT SHEETS FOR ALL PIPELINES & UMBILICAL'S - IFC | 0 |  | 2022-11-21 |  | 2023-04-27 | 109
0 | MSDEEB08 | ISSUE PFDS, P&IDS, PLOT PLANS, EQT LAYOUTS, DATA SHEETS, EQT LIST, FOR ALL FACILITIES AFTER INCORP. HAZOP COMMENTS - IFC | 0 |  | 2022-12-16 |  | 2023-04-27 | 93
0 | MSDEEB24 | ISSUE IFC ALL ISOMETRICS | 0 |  | 2022-12-19 |  | 2023-04-27 | 92
0 | MSDEEB30 | COMPLETE ALL THE DETAIL ENGINEERING ACTIVITIES FOR OFFSHORE FACILITIES | 0 |  | 2023-01-19 |  | 2023-04-27 | 69
PROCUREMENT |  |  | 114 | 2022-04-04 | 2022-09-19 | 2022-06-17 | 2023-01-25 | 91
0 | MSPROC01 | ISSUE PURCHASE ORDERS FOR LINE PIPES (COATED) | 0 |  | 2022-04-04 |  | 2022-06-17 | 52
0 | MSPROC17 | ISSUE PURCHASE ORDERS FOR ALL MAJOR CIVIL/ STRUCTURAL BULK MATERIALS - I MTO. | 0 |  | 2022-04-04 |  | 2022-08-02 | 81
0 | MSPROC02 | ISSUE PURCHASE ORDERS FOR LAUNCHERS AND RECEIVERS | 0 |  | 2022-05-20 |  | 2022-07-27 | 46
0 | MSPROC03 | ISSUE PURCHASE ORDER FOR PIPELINE HOT BENDS | 0 |  | 2022-05-20 |  | 2022-09-23 | 88
0 | MSPROC04 | ISSUE PURCHASE ORDERS FOR DRAIN DRUM & DRAIN PUMP | 0 |  | 2022-05-20 |  | 2022-07-22 | 43
0 | MSPROC05 | ISSUE PURCHASE ORDERS FOR PRESSURE VESSEL | 0 |  | 2022-05-20 |  | 2022-07-22 | 43
0 | MSPROC11 | ISSUE PURCHASE ORDERS FOR ICSS | 0 |  | 2022-05-20 |  | 2022-07-27 | 46
0 | MSPROC13 | ISSUE PURCHASE ORDERS FOR PIPING BULK MATERIALS AT SITE- I MTO. | 0 |  | 2022-05-20 |  | 2022-09-30 | 93
0 | MSPROC06 | ISSUE PURCHASE ORDERS FOR SUBSEA CABLES (COMPOSITE) | 0 |  | 2022-06-20 |  | 2022-08-17 | 40
0 | MSPROC07 | ISSUE PURCHASE ORDERS FOR HIPPS SYSTEM | 0 |  | 2022-06-20 |  | 2022-08-26 | 47
0 | MSPROC08 | ISSUE PURCHASE ORDERS FOR WELL HEAD CONTROL PANEL | 0 |  | 2022-06-20 |  | 2022-09-06 | 54
0 | MSPROC12 | ISSUE PURCHASE ORDERS FOR ALL BALANCE PIPELINE MATERIALS (BARRED TEE, ISOLATION JOINTS, ANCHOR FLANGES ETC.) | 0 |  | 2022-06-20 |  | 2022-10-07 | 76
0 | MSPROC15 | ISSUE PURCHASE ORDERS FOR ALL E&I BULK MATERIALS & TAGGED INSTRUMENTS - I MTO. | 0 |  | 2022-06-20 |  | 2022-10-07 | 77
0 | MSPROC19 | SUBMIT G-SPIRS TO CPY & PLACE ORDERS FOR OPERATIONAL SPARES FOR ALL ITEMS AFTER OBTAINING CPY APPROVALS (N/A) | 0 |  | 2022-06-20 |  | 2022-11-15 | 104
0 | MSPROC10 | ISSUE PURCHASE ORDERS FOR CHOKE VALVES,ON/OFF VALVE & MOV | 0 |  | 2022-07-06 |  | 2022-09-07 | 43
0 | MSPROC09 | ISSUE PURCHASE ORDERS FOR CONTROL VALVES, SELF REGULATING VALVES & PSV | 0 |  | 2022-07-20 |  | 2022-12-16 | 106
0 | MSPROC18 | ISSUE PURCHASE ORDERS FOR ALL MAJOR CIVIL/ STRUCTURAL BULK MATERIALS - FINAL MTO. | 0 |  | 2022-08-19 |  | 2023-01-04 | 97
0 | MSPROC14 | ISSUE PURCHASE ORDERS FOR PIPING BULK MATERIALS AT SITE - FINAL MTO. | 0 |  | 2022-09-16 |  | 2023-01-06 | 79
0 | MSPROC16 | ISSUE PURCHASE ORDERS FOR ALL E&I BULK MATERIALS & TAGGED INSTRUMENTS - FINAL MTO. | 0 |  | 2022-09-19 |  | 2023-01-25 | 91
SUBCONTRACTS |  |  | 204 | 2022-02-25 | 2022-12-20 | 2022-04-29 | 2023-06-09 | 122
0 | MSSUBD01 | AWARD SUBCONTRACTS FOR PRE-ENGINEERING SURVEY (TOPO/BATH/SOIL INVESTIGATION) (N/A) | 0 |  | 2022-02-25 |  | 2022-04-29 | 46
0 | MSSUBD02 | AWARD SUBCONTRACTS FOR LINEPIPE COATING WORKS (N/A) | 0 |  | 2022-06-20 |  | 2023-01-13 | 145
0 | MSSUBD03 | AWARD SUBCONTRACTS FOR DREDGING & BACKFILLING WORKS | 0 |  | 2022-09-02 |  | 2022-11-09 | 48
0 | MSSUBD04 | AWARD SUBCONTRACTS FOR HOOK UP & MODIFICATION WORKS (N/A) | 0 |  | 2022-12-20 |  | 2023-06-09 | 122
MANUFACTURING & DELIVERY |  |  | 366 | 2022-08-20 | 2023-08-21 | 2022-12-30 | 2023-12-20 | 121
0 | MSMNDE01 | READY FOR LOAD OUT OF UMBILICAL'S (FROM UMBILICAL VENDOR MANUFACTURING SHOP) | 0 |  | 2022-08-20 |  | 2023-06-10 | 294
0 | MSMNDE19 | RECEIVE ALL MAJOR CIVIL/ STRUCTURAL BULK MATERIALS - I MTO | 0 |  | 2022-09-04 |  | 2022-12-30 | 117
0 | MSMNDE15 | RECEIVE ALL PIPING BULK MATERIALS AT SITE- I MTO. | 0 |  | 2022-11-19 |  | 2023-04-18 | 150
0 | MSMNDE02 | RECEIVE ALL LINE PIPES (COATED) AT SITE - FIRST LOT | 0 |  | 2022-12-08 |  | 2023-05-03 | 146
0 | MSMNDE20 | RECEIVE ALL MAJOR CIVIL/ STRUCTURAL BULK MATERIALS - FINAL MTO | 0 |  | 2022-12-20 |  | 2023-03-30 | 100
0 | MSMNDE16 | RECEIVE ALL PIPING BULK MATERIALS AT SITE - FINAL MTO. | 0 |  | 2023-01-19 |  | 2023-04-28 | 99
0 | MSMNDE17 | RECEIVE ALL E&I BULK MATERIALS AT SITE & TAGGED INSTRUMENTS - I MTO. | 0 |  | 2023-02-19 |  | 2023-08-07 | 169
0 | MSMNDE05 | RECEIVE ALL PIPELINE HOT BENDS AT SITE | 0 |  | 2023-02-27 |  | 2023-07-11 | 134
0 | MSMNDE14 | RECEIVE ALL BALANCE PIPELINE MATERIALS (BARRED TEE, ISOLATION JOINTS, ANCHOR FLANGES ETC.) AT SITE | 0 |  | 2023-04-20 |  | 2023-09-01 | 134
0 | MSMNDE03 | RECEIVE ALL LINE PIPES (COATED) AT SITE - FINAL LOT | 0 |  | 2023-04-21 |  | 2023-06-28 | 68
0 | MSMNDE04 | RECEIVE ALL LAUNCHERS AND RECEIVERS AT SITE | 0 |  | 2023-05-03 |  | 2023-10-04 | 154
0 | MSMNDE11 | RECEIVE ALL CONTROL VALVES, SELF REGULATING VALVES & PSV AT SITE | 0 |  | 2023-05-03 |  | 2023-09-01 | 121
0 | MSMNDE18 | RECEIVE ALL E&I BULK MATERIALS AT SITE & TAGGED INSTRUMENTS - FINAL MTO. | 0 |  | 2023-06-05 |  | 2023-09-23 | 110
0 | MSMNDE10 | RECEIVE ALL WELL HEAD CONTROL PANEL AT SITE | 0 |  | 2023-06-20 |  | 2023-09-20 | 92
0 | MSMNDE21 | RECEIVE INSURANCE SPARES FOR ALL EQUIPMENT & PACKAGES AT SITE AND HANDOVER TO COMPANY (N/A) | 0 |  | 2023-06-20 |  | 2023-11-25 | 158
0 | MSMNDE22 | RECEIVE ALL OPERATING SPARES AT SITE AND HAND-OVER TO COMPANY (N/A) | 0 |  | 2023-06-20 |  | 2023-11-25 | 158
0 | MSMNDE09 | RECEIVE ALL HIPPS SYSTEM AT SITE | 0 |  | 2023-06-21 |  | 2023-11-18 | 150
0 | MSMNDE06 | RECEIVE ALL DRAIN DRUM & DRAIN PUMP AT SITE | 0 |  | 2023-06-21 |  | 2023-09-08 | 79
0 | MSMNDE12 | RECEIVE ALL CHOKE VALVES,ON/OFF VALVE & MOV AT SITE | 0 |  | 2023-07-03 |  | 2023-09-01 | 60
0 | MSMNDE13 | RECEIVE ALL ICSS AT SITE | 0 |  | 2023-07-20 |  | 2023-12-20 | 153
0 | MSMNDE07 | RECEIVE ALL PRESSURE VESSEL AT SITE | 0 |  | 2023-07-21 |  | 2023-09-14 | 55
0 | MSMNDE08 | RECEIVE ALL SUBSEA CABLES (COMPOSITE) AT SITE | 0 |  | 2023-08-21 |  | 2023-11-05 | 76
CONSTRUCTION, MECHANICAL COMPLETION & PRE-COMM |  |  | 466 | 2022-12-08 | 2024-03-18 | 2023-04-26 | 2024-05-21 | 64
0 | MSCONF01 | COMPLETE COATING OF ALL LINE PIPES - FIRST LOT | 0 |  | 2022-12-08 |  | 2023-04-26 | 120
0 | MSCONF02 | COMPLETE COATING OF ALL LINE PIPES - FINAL LOT | 0 |  | 2023-04-14 |  | 2023-06-21 | 59
0 | MSCONF03 | COMPLETE ALL FABRICATION OF BU HASEER (BH-03) WHT & READY FOR LOAD OUT | 0 |  | 2023-08-21 |  | 2023-11-25 | 84
0 | MSCONF04 | COMPLETE ALL FABRICATION OF SATAH (ST-10) WHT & READY FOR LOAD OUT | 0 |  | 2023-09-15 |  | 2023-11-16 | 54
0 | MSCONF06 | COMPLETE ALL FABRICATION OF HAIR DALMA (HD-03) WHT & READY FOR LOAD OUT | 0 |  | 2023-10-11 |  | 2024-03-04 | 125
0 | MSCONF05 | COMPLETE ALL FABRICATION OF HAIR DALMA (HD-T4) WHT & READY FOR LOAD OUT | 0 |  | 2023-10-12 |  | 2024-03-04 | 124
0 | MSCONF09 | COMPLETION OF WHT'S (BU HASEER - BH-03) TOPSIDE INSTALLATION WORKS | 0 |  | 2023-10-31 |  | 2023-11-29 | 26
0 | MSCONF08 | COMPLETION OF WHT'S ( SATAH - ST-10) TOPSIDE INSTALLATION WORKS | 0 |  | 2023-11-05 |  | 2023-12-05 | 30
0 | MSCONF07 | COMPLETE ALL PIPELINE LAYING WORKS INCLUDING FO & COMPOSITE CABLES | 0 |  | 2023-11-27 |  | 2024-04-12 | 137
0 | MSCONF13 | COMPLETION OF ALL TIE-IN TO ONSHORE FACILITIES & IGD-E PLATFORMS INCL. ALL HOOK UP'S | 0 |  | 2024-01-16 |  | 2024-05-21 | 126
0 | MSCONF11 | COMPLETION OF WHT (HAIR DALMA - HD-T4) TOPSIDE INSTALLATION WORKS | 0 |  | 2024-03-06 |  | 2024-03-26 | 20
0 | MSCONF10 | COMPLETION OF WHT (HAIR DALMA - HD-03) TOPSIDE INSTALLATION WORKS | 0 |  | 2024-03-11 |  | 2024-04-01 | 21
0 | MSCONF12 | COMPLETION OF ALL SUBSEA UMBILICAL LAYING WORKS | 0 |  | 2024-03-18 |  | 2024-05-06 | 49
COMMISSIONING & RFSU |  |  | 275 | 2024-05-21 | 2025-02-20 | 2024-05-21 | 2025-03-22 | 31
0 | MSCOMG01 | COMPLETE COMM. & ACHIEVEMENT OF RFSU FOR ST-10 WHT WITH NEW P/L SYSTEMS, UMBILICAL'S & ASSOCIATED FACILITIES | 0 |  | 2024-05-21 |  | 2024-05-21 | 0
0 | MSCOMG02 | COMPLETE COMM & ACHIEVEMENT OF RFSU FOR BH-03 WHT WITH ALL NEW P/L SYSTEMS, UMBILICAL'S & ASSOCIATED FACILITIES | 0 |  | 2024-05-21 |  | 2024-05-21 | 0
0 | MSCOMG03 | COMPLETE COMM & ACHIEVEMENT OF RFSU FOR HD-03 WHT WITH ALL NEW P/L SYSTEMS, UMBILICAL'S & ASSOCIATED FACILITIES | 0 |  | 2024-07-21 |  | 2024-07-21 | 0
0 | MSCOMG04 | COMPLETE COMM & ACHIEVEMENT OF RFSU FOR HD-T4 WHT WITH ALL NEW P/L SYSTEMS, UMBILICAL'S & ASSOCIATED FACILITIES | 0 |  | 2024-08-20 |  | 2024-09-20 | 31
0 | MSCOMG05 | COMPLETE TEST RUN & ACHIEVE PAC FOR ALL WHT'S, PIPELINES & UMBILICALS | 0 |  | 2025-02-20 |  | 2025-03-22 | 31
PROJECT INTERFACE ACTIVITIES INPUTS (DATES ARE TO BE AGREED WITH COMPANY/ PACKAGE "B" CONTRACTOR) |  |  | 832 | 2021-12-19 | 2024-03-30 | 2022-01-21 | 2024-05-02 | 33
0 | MS2040 | FEED NATIVE FILES FOR DOCUMENTS AND DRAWINGS FROM COMPANY | 14 | 2021-12-19 | 2022-01-06 | 2022-03-11 | 2022-03-30 | 60
0 | MS2090 | ONSHORE PIPELINE/ PIPING DETAILS, FLARE HEADER ROUTING , FLARE CAPACITY AT ARZANAH - BY PACKAGE "B" | 51 | 2021-12-19 | 2022-02-28 | 2022-03-04 | 2022-05-18 | 55
0 | MS2050 | FEED STAGE DATABASE FOR THE SMART PLANT TOOLS (SPI,SPPID, SPEL, SP3D & SFP) BY PACKAGE-B | 51 | 2021-12-19 | 2022-02-28 | 2022-08-08 | 2022-10-17 | 160
0 | MS2150 | CUSTOMIZED SMARTPLANT TOOLS SETUP (FOR SPI, SPPID, SPEL, SP3D & SPF) BY PACKAGE "B" | 51 | 2021-12-19 | 2022-02-28 | 2022-02-15 | 2022-04-26 | 42
0 | MS2190 | ONSHORE P/L,PIPING DETAILS (LENGTH/ROUTING/EXPORT GAS/CONDENSATE COMPOSITION/TEMPE )@ ARZANAH & ZIRKU BY PACKAGE "B" | 51 | 2021-12-19 | 2022-02-28 | 2022-03-04 | 2022-05-18 | 55
0 | MS2200 | SP3D MODELLING PROCEDURE BY PACKAGE "B" | 51 | 2021-12-19 | 2022-02-28 | 2022-02-25 | 2022-05-11 | 50
0 | MS2220 | SPI DATABASE SET UP BY PACKAGE "B" | 51 | 2021-12-19 | 2022-02-28 | 2022-03-10 | 2022-05-24 | 59
0 | MS2230 | SP3D DATABASE (CATALOGUE AND SPEC LIBRARY) SET UP TO MEET THE REQUIREMENTS OF PACKAGE-A CONTRACTOR’s SCOPE BY PKG "B" | 51 | 2021-12-19 | 2022-02-28 | 2022-03-10 | 2022-05-24 | 59
0 | MS2240 | SP3D SUPPORT CUSTOMIZATION TO MEET THE REQUIREMENTS OF PACKAGE-A CONTRACTOR’s SUPPORT STANDARD. BY PACKAGE "B" | 51 | 2021-12-19 | 2022-02-28 | 2022-03-10 | 2022-05-24 | 59
0 | MS2680 | IMPLEMENTATION PROCEDURE FOR SMART PLANT ELECTRICAL (SPEL) BY PACKAGE "B" | 51 | 2021-12-19 | 2022-02-28 | 2022-04-06 | 2022-06-20 | 78
0 | MS2550 | ICSS SPECIFICATION BY PACKAGE "B" | 52 | 2021-12-19 | 2022-03-01 | 2022-02-21 | 2022-05-06 | 46
0 | MS2560 | PACKAGE INTERFACE PHILOSOPHY BY PACKAGE "B" | 51 | 2021-12-19 | 2022-03-01 | 2022-02-22 | 2022-05-06 | 46
0 | MS2210 | SIZE OF SUBSEA CABLE & SPLITTER BOX BY PACKAGE "B" | 59 | 2021-12-19 | 2022-03-10 | 2022-02-17 | 2022-05-13 | 44
0 | MS2570 | ICSS SYSTEM ARCHITECTURAL DRAWINGS BY PACKAGE "B" | 51 | 2021-12-29 | 2022-03-11 | 2022-03-04 | 2022-05-18 | 46
0 | MS2110 | INTERFACE ELECTRICAL SIGNAL LIST - BY PACKAGE "B" | 69 | 2021-12-19 | 2022-03-24 | 2022-02-24 | 2022-06-03 | 49
0 | MS2130 | ELECT. PROTECTION CONTROL/METERING /INTERLOCKING/ECMS/PMS/LIGHTING/EARTHING/LIGHTNING/LOAD SHEDDING PHILOSOPHY BY PKG B | 69 | 2021-12-19 | 2022-03-24 | 2022-02-24 | 2022-06-03 | 49
0 | MS2260 | ECMS INTERFACE UNIT (EIU) MAKE&MODEL FOR ONSHORE & OFFSHORE (TO BE PROCURED FROM RMU VENDOR) BY PACKAGE "B" | 69 | 2021-12-19 | 2022-03-24 | 2022-02-24 | 2022-06-03 | 49
0 | MS2250 | SUBSEA CABLE LINE DIFFERENTIAL PROTECTION RELAY MAKE/MODELS&COMBINED SENSOR MAKE&MODELS FOR OFFSHORE 6.6KV RMU’s BY PKGB | 74 | 2021-12-19 | 2022-03-31 | 2022-02-17 | 2022-06-03 | 44
0 | MS2580 | FINAL HARDWARE PROTOTYPE DEVELOPMENT BY PACKAGE "B" | 50 | 2022-01-28 | 2022-04-08 | 2022-04-04 | 2022-06-15 | 46
0 | MS2590 | FINALIZATION OF HARDWARE/ SOFTWARE/ LICENSES FOR HEAD END EQUIPMENT BY PACKAGE "B" | 50 | 2022-01-28 | 2022-04-08 | 2022-04-04 | 2022-06-15 | 46
0 | MS2290 | TELECOM SYSTEM INTEGRATOR SELECTION AND TELECOM ITEMS MANUFACTURER AND MODEL NAME BY PACKAGE "B" | 81 | 2021-12-19 | 2022-04-11 | 2022-03-02 | 2022-06-27 | 53
0 | MS2300 | INLINE ULTRASONIC FLOW METER (UTFM), PT AND TT ALONG WITH LDS AND RTU DETAILS (FOR IGD-E). BY PACKAGE "B" | 81 | 2021-12-19 | 2022-04-11 | 2022-03-24 | 2022-07-22 | 69
0 | MS2600 | CYBER SECURITY SPECIFICATION BY PACKAGE "B" | 50 | 2022-02-11 | 2022-04-22 | 2022-04-18 | 2022-06-29 | 46
0 | MS2610 | HARDWARE FDS (BY MAC) APPROVED BY BY PACKAGE "A" & "B" | 50 | 2022-02-11 | 2022-04-22 | 2022-04-18 | 2022-06-29 | 46
0 | MS2620 | SOFTWARE FUNCTIONAL DESIGN SPECIFICATION (FDS) (BY MAC) APPROVED BY PACKAGE A & B | 50 | 2022-02-22 | 2022-05-06 | 2022-04-27 | 2022-07-13 | 46
0 | MS2630 | SYSTEM PHILODOPHY (ALARM/ CONTROL) BY PACKAGE "B" | 50 | 2022-02-22 | 2022-05-06 | 2022-04-27 | 2022-07-13 | 46
0 | MS2640 | GRAPHICS GUIDLINE DEVELOPMENT & TESTING BASED ON SP-1152 ( BY MAC) | 50 | 2022-02-22 | 2022-05-06 | 2022-04-27 | 2022-07-13 | 46
0 | MS2320 | RADIO COVERAGE STUDY REPORT BY PACKAGE "B" | 98 | 2021-12-19 | 2022-05-09 | 2022-04-06 | 2022-08-29 | 78
0 | MS2330 | CCTV COVERAGE STUDY REPORT BY PACKAGE "B" | 98 | 2021-12-19 | 2022-05-09 | 2022-04-06 | 2022-08-29 | 78
0 | MS2270 | CYBER SECURITY SYSTEM REQUIREMENT FOR ICSS AND OTHER SUB-SYSTEMS BY PACKAGE "B" | 99 | 2021-12-19 | 2022-05-10 | 2022-02-23 | 2022-07-19 | 48
0 | MS2310 | CABLE TRENCH DRAWING FROM SHORELINE TO TUTU / SPLITTER BOX FOR SUBSEA FO CABLE LAYING BY PACKAGE "B" | 128 | 2021-12-19 | 2022-06-20 | 2022-03-14 | 2022-09-15 | 61
0 | MS2280 | COMNPANY’S FREE ISSUE MATERIALS ENGINEERING DETAILS (HOP PANELS FOR SH-10 & BH-03/ DHMS & DAU FOR ALL 4 WHP) BY COMPANY | 143 | 2021-12-19 | 2022-07-14 | 2022-03-25 | 2022-10-19 | 70
0 | MS2650 | ICSS DEVELOPMNT OF TEMPLATES (BY PACKAGE "B" | 50 | 2022-04-28 | 2022-07-15 | 2022-10-18 | 2022-12-28 | 117
0 | MS2660 | ICSS DATEBASE SETUP AND TAGGING PHILOSOPHY BY PACKAGE "B" | 50 | 2022-04-28 | 2022-07-15 | 2022-10-18 | 2022-12-28 | 117
0 | MS2340 | PIPING ISOMETRICS / GAD EXTRACTION SETUP TO MEET THE REQUIREMENTS OF PACKAGE-A CONTRACTOR’s SCOPE BY PACKAGE "B" | 145 | 2021-12-19 | 2022-07-18 | 2022-03-23 | 2022-10-19 | 68
0 | MS2700 | ICSS HARDWARE FREEZ FOR MAC BY PACKAGE "A" | 0 |  | 2022-08-04 |  | 2022-12-28 | 103
0 | MS2350 | ALARM PHILOSOPHY DOCUMENT ISSUANCE BY PACKAGE "B" | 193 | 2021-12-19 | 2022-09-22 | 2022-04-13 | 2023-01-18 | 83
0 | MS2710 | ICSS SOFTWARE FREEZ FOR MAC BY PACKAGE "A" | 0 |  | 2022-10-21 |  | 2022-12-28 | 47
0 | MS2380 | READINESS OF ONSHORE TRENCHES AND FOUND'N FOR TUTU BOXES/SPLITTER BOX/FO PATCH PANEL @ ARZANAH SOUTH &EAST BY PKG "B" | 273 | 2021-12-19 | 2023-01-16 | 2022-03-07 | 2023-04-03 | 56
0 | MS2400 | READINESS OF ONSHORE TRENCH /FOUNDATION FOR FO PATCH PANEL @ ZIRKU FOR THE INST'N & TERMINATION OF FOC BY PACKAGE "B" | 273 | 2021-12-19 | 2023-01-16 | 2022-04-04 | 2023-05-03 | 76
0 | MS2360 | RECEIPT OF COMPANY FREE ISSUE MATERIALS (HOP PANELS FOR SH-10 & BH-03/ DHMS & DAU FOR ALL 4 WHP) BY COMPANY | 298 | 2021-12-19 | 2023-02-20 | 2022-03-28 | 2023-05-31 | 71
0 | MS2670 | TELECOM EQUIPMENT DELIVERY BY PACKAGE "B" | 333 | 2021-12-19 | 2023-04-10 | 2022-03-08 | 2023-07-04 | 57
0 | MS2410 | COMPL'N OF INST'N BY PKG-B OF ALL ONSHORE P/LS TESTING/CALIPER/DEWATERING/DRYING & TIE-INS@ARZANAH/ZIRKU BY PACKAGE "B" | 408 | 2021-12-19 | 2023-08-01 | 2022-06-16 | 2024-01-26 | 126
0 | MS2390 | START-UP PROCEDURE FOR OVERALL FACILITIES INCLUDING PKG-A SCOPE BY PACKAGE "B" | 427 | 2021-12-19 | 2023-08-28 | 2022-04-20 | 2023-12-29 | 88
0 | MS2520 | PIPE LINE TIE-IN READINESS AT ARZANAH ISLAND & ZIRKU ISLAND BY PACKAGE "B" | 432 | 2021-12-19 | 2023-09-04 | 2022-02-28 | 2023-11-14 | 51
0 | MS2690 | SUPPLY OF PLDS FOR IGD-E TOWER BY PACKAGE "B" | 486 | 2021-12-19 | 2023-11-20 | 2022-04-22 | 2024-03-27 | 90
0 | MS2420 | AVAILABILITY OF POWER TO OFFSHORE FOR FINAL COMM.(RFSU)/CONTRACTR TO PROVIDE DG DURING CONSTRUCTION PHASE. PACKAGE "B" | 505 | 2021-12-19 | 2023-12-18 | 2022-04-27 | 2024-05-01 | 93
0 | MS2430 | INTEGRATION OF ICSS/ECMS BETWEEN WHTS AND ONSHORE BY PACKAGE "B" | 505 | 2021-12-19 | 2023-12-18 | 2022-04-27 | 2024-05-01 | 93
0 | MS2440 | INTEGRATION OF TELECOM BETWEEN WHTS AND ONSHORE BY PACKAGE "B" | 505 | 2021-12-19 | 2023-12-18 | 2022-04-27 | 2024-05-01 | 93
0 | MS2450 | SUPPLYING CHEMICALS/NITROGEN/OTHER UTILITIES TO WHTS BY PKG-B BY PACKAGE "B" | 505 | 2021-12-19 | 2023-12-18 | 2022-04-27 | 2024-05-01 | 93
0 | MS2460 | 6.6 KV SUBSEA POWER READINESS AT ARZANAH ISLAND BY PACKAGE "B" | 505 | 2021-12-19 | 2023-12-18 | 2022-04-13 | 2024-04-17 | 83
0 | MS2470 | ECMS READINESS AT ARZANAH ISLAND BY PACKAGE "B" | 543 | 2021-12-19 | 2024-02-12 | 2022-03-04 | 2024-05-01 | 55
0 | MS2480 | ICSS READINESS AT ARZANAH ISLAND BY PACKAGE "B" | 543 | 2021-12-19 | 2024-02-12 | 2022-03-04 | 2024-05-01 | 55
0 | MS2490 | PLDS AT ARZANAH ISLAND BY PACKAGE "B" | 543 | 2021-12-19 | 2024-02-12 | 2022-03-04 | 2024-05-01 | 55
0 | MS2500 | FO SYSTEM READINESS AT ARZANAH ISLAND BY PACKAGE "B" | 543 | 2021-12-19 | 2024-02-12 | 2022-03-04 | 2024-05-01 | 55
0 | MS2510 | LAN, CCTV, TELEPHONE/BWA, RADIO SYSTEM READINESS AT ARZANAH ISLAND BY PACKAGE "B" | 543 | 2021-12-19 | 2024-02-12 | 2022-03-04 | 2024-05-01 | 55
0 | MS2530 | CHEMICALS/UTILITIES (MEG/DOWNHOLE GAS CORROS'N INHIBITOR/TOPSIDE GAS CORROS'N/NITROGEN) READINESS AT ARZANAH BY PKG "B | 543 | 2021-12-19 | 2024-02-12 | 2022-03-04 | 2024-05-01 | 55
0 | MS2540 | READINESS OF DOWNSTREAM FACILITIES AT ARZANAH AND ZIRKU ISLAND TO RECEIVE HYDROCARBON BY PACKAGE "B" | 832 | 2021-12-19 | 2024-03-30 | 2022-01-21 | 2024-05-02 | 33
HOME OFFICE SERVICES |  |  | 1159 | 2021-12-19 | 2025-02-20 | 2021-12-19 | 2025-03-22 | 31
GENERAL & PROJECT MANAGEMENT |  |  | 1159 | 2021-12-19 | 2025-02-20 | 2021-12-19 | 2025-03-22 | 31
PROJECT DELIVERABLES & PROCEDURE |  |  | 1159 | 2021-12-19 | 2025-02-20 | 2021-12-19 | 2025-03-22 | 31
PROJECT MANAGEMENT |  |  | 1159 | 2021-12-19 | 2025-02-20 | 2021-12-19 | 2025-03-22 | 31
0 | GDVPJ1000 | PROJECT DELIVERABLES REGISTER - ICR | 10 | 2021-12-19 | 2021-12-30 | 2021-12-19 | 2022-01-03 | 1
0 | GDVPJ1015 | PROJECT EXECUTION PLAN - ICR | 13 | 2021-12-23 | 2022-01-12 | 2022-01-25 | 2022-02-11 | 22
0 | GDVPJ1105 | PROJECT SUBCONTRACT PLAN & PROCEDURE- ICR | 21 | 2021-12-19 | 2022-01-17 | 2022-03-03 | 2022-03-31 | 54
0 | GDVPJ1045 | PROJECT DOCUMENT CONTROL PROCEDURE - ICR | 20 | 2021-12-23 | 2022-01-21 | 2021-12-26 | 2022-01-24 | 1
0 | GDVPJ1165 | PROJECT INTERFACE REGISTER- ICR | 20 | 2021-12-30 | 2022-01-28 | 2022-04-20 | 2022-05-20 | 78
0 | GDVPJ1075 | PROJECT RISK MANAGEMENT PROCEDURE- ICR | 20 | 2021-12-30 | 2022-01-28 | 2022-03-14 | 2022-04-08 | 51
0 | GDVPJ1020 | PROJECT EXECUTION PLAN - IFA | 10 | 2022-01-26 | 2022-02-09 | 2022-05-23 | 2022-06-03 | 80
0 | GDVPJ1150 | PROJECT MATERIAL MANAGEMENT PROCEDURE- ICR | 20 | 2022-01-12 | 2022-02-09 | 2022-03-23 | 2022-04-19 | 50
0 | GDVPJ1030 | PROJECT COORDINATION PROCEDURE - ICR | 20 | 2022-01-12 | 2022-02-09 | 2022-04-22 | 2022-05-24 | 72
0 | GDVPJ1060 | PROJECT INTERFACE MANAGEMENT PLAN - ICR | 15 | 2022-01-21 | 2022-02-11 | 2022-01-24 | 2022-02-14 | 1
0 | GDVPJ1195 | PROJECT PROCEDURE FOR NOTIFICATION TO SITE OF CHANGE (NSC) - ICR | 20 | 2022-01-19 | 2022-02-16 | 2022-05-09 | 2022-06-03 | 75
0 | GDVPJ1180 | DESIGN DEVIATION / CONCESSION REQUEST AUTHORIZATION (DCA) PROCEDURE- ICR | 18 | 2022-01-21 | 2022-02-16 | 2022-05-09 | 2022-06-01 | 73
0 | GDVPJ1210 | LESSON LEARNT REGISTER - ICR | 27 | 2022-01-12 | 2022-02-18 | 2022-04-20 | 2022-05-31 | 70
0 | GDVPJ1080 | PROJECT RISK MANAGEMENT PROCEDURE- IFA | 10 | 2022-02-08 | 2022-02-22 | 2022-08-08 | 2022-08-19 | 123
0 | GDVPJ1170 | PROJECT INTERFACE REGISTER- IFA | 10 | 2022-02-11 | 2022-02-25 | 2022-06-06 | 2022-06-17 | 78
0 | GDVPJ1050 | PROJECT DOCUMENT CONTROL PROCEDURE - IFA | 15 | 2022-02-04 | 2022-02-25 | 2022-05-26 | 2022-06-15 | 76
0 | GDVPJ1110 | PROJECT SUBCONTRACT PLAN & PROCEDURE-- IFA | 20 | 2022-01-31 | 2022-02-28 | 2022-04-15 | 2022-05-17 | 54
0 | GDVPJ1065 | PROJECT INTERFACE MANAGEMENT PLAN - IFA | 5 | 2022-02-25 | 2022-03-04 | 2022-02-28 | 2022-03-07 | 1
0 | GDVPJ1005 | PROJECT DELIVERABLES REGISTER - IFA | 35 | 2022-01-14 | 2022-03-04 | 2022-04-06 | 2022-05-27 | 58
0 | GDVPJ1200 | PROJECT PROCEDURE FOR NOTIFICATION TO SITE OF CHANGE (NSC) - IFA | 5 | 2022-03-02 | 2022-03-09 | 2022-06-20 | 2022-06-24 | 75
0 | GDVPJ1035 | PROJECT COORDINATION PROCEDURE - IFA | 10 | 2022-02-23 | 2022-03-09 | 2022-06-08 | 2022-06-21 | 72
0 | GDVPJ1185 | DESIGN DEVIATION / CONCESSION REQUEST AUTHORIZATION (DCA) PROCEDURE- IFA | 7 | 2022-03-02 | 2022-03-11 | 2022-06-16 | 2022-06-24 | 73
0 | GDVPJ1090 | PROJECT RISK REGISTER - ICR | 20 | 2022-02-11 | 2022-03-11 | 2022-06-20 | 2022-07-21 | 88
0 | GDVPJ1085 | PROJECT RISK MANAGEMENT PROCEDURE- FINAL | 10 | 2022-03-01 | 2022-03-15 | 2022-08-29 | 2022-09-09 | 123
0 | GDVPJ1215 | LESSON LEARNT REGISTER - IFA | 10 | 2022-03-04 | 2022-03-18 | 2022-06-15 | 2022-06-28 | 70
0 | GDVPJ1120 | ASSET INTEGRITY MANAGEMENT PLAN- ICR | 25 | 2022-02-11 | 2022-03-18 | 2022-07-26 | 2022-08-29 | 111
0 | GDVPJ1055 | PROJECT DOCUMENT CONTROL PROCEDURE - FINAL | 10 | 2022-03-08 | 2022-03-22 | 2022-06-27 | 2022-07-13 | 76
0 | GDVPJ1070 | PROJECT INTERFACE MANAGEMENT PLAN - FINAL | 5 | 2022-03-15 | 2022-03-22 | 2022-07-04 | 2022-07-13 | 76
0 | GDVPJ1155 | PROJECT MATERIAL MANAGEMENT PROCEDURE- IFA | 20 | 2022-02-23 | 2022-03-23 | 2022-05-09 | 2022-06-03 | 50
0 | GDVPJ1025 | PROJECT EXECUTION PLAN - FINAL | 20 | 2022-02-23 | 2022-03-23 | 2022-06-20 | 2022-07-20 | 80
0 | GDVPJ1010 | PROJECT DELIVERABLES REGISTER - FINAL | 5 | 2022-03-18 | 2022-03-25 | 2022-06-13 | 2022-06-17 | 58
0 | GDVPJ1115 | PROJECT SUBCONTRACT PLAN & PROCEDURE-- FINAL | 10 | 2022-03-14 | 2022-03-28 | 2022-06-01 | 2022-06-14 | 54
0 | GDVPJ1095 | PROJECT RISK REGISTER - IFA | 5 | 2022-03-22 | 2022-03-29 | 2022-08-23 | 2022-08-29 | 104
0 | GDVPJ1175 | PROJECT INTERFACE REGISTER - FINAL | 10 | 2022-03-15 | 2022-03-29 | 2022-07-04 | 2022-07-20 | 76
0 | GDVPJ1205 | PROJECT PROCEDURE FOR NOTIFICATION TO SITE OF CHANGE (NSC) - FINAL | 5 | 2022-03-23 | 2022-03-30 | 2022-07-14 | 2022-07-20 | 75
0 | GDVPJ1190 | DESIGN DEVIATION / CONCESSION REQUEST AUTHORIZATION (DCA) PROCEDURE- FINAL | 5 | 2022-03-25 | 2022-04-01 | 2022-07-14 | 2022-07-20 | 73
0 | GDVPJ1040 | PROJECT COORDINATION PROCEDURE - FINAL | 8 | 2022-03-23 | 2022-04-04 | 2022-07-06 | 2022-07-20 | 72
0 | GDVPJ1100 | PROJECT RISK REGISTER - FINAL | 3 | 2022-04-06 | 2022-04-11 | 2022-09-07 | 2022-09-09 | 104
0 | GDVPJ1220 | LESSON LEARNT REGISTER - FINAL | 10 | 2022-04-01 | 2022-04-15 | 2022-10-04 | 2022-10-17 | 126
0 | GDVPJ1225 | LESSON LEARNT WORKSHOP REPORT - ICR | 20 | 2022-03-18 | 2022-04-15 | 2022-06-29 | 2022-07-29 | 70
0 | GDVPJ1160 | PROJECT MATERIAL MANAGEMENT PROCEDURE - FINAL | 10 | 2022-04-06 | 2022-04-20 | 2022-06-20 | 2022-07-01 | 50
0 | GDVPJ1125 | ASSET INTEGRITY MANAGEMENT PLAN- IFA | 15 | 2022-04-01 | 2022-04-22 | 2022-09-13 | 2022-10-03 | 111
0 | GDVPJ1230 | LESSON LEARNT WORKSHOP REPORT - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-08-15 | 2022-08-26 | 70
0 | GDVPJ1130 | ASSET INTEGRITY MANAGEMENT PLAN- FINAL | 10 | 2022-05-11 | 2022-05-25 | 2022-10-18 | 2022-10-31 | 111
0 | GDVPJ1135 | CONSTRUCTABILITY WORKSHOP PROCEDURE- ICR | 15 | 2022-05-25 | 2022-06-15 | 2022-09-05 | 2022-09-23 | 70
0 | GDVPJ1235 | LESSON LEARNT WORKSHOP REPORT - FINAL | 10 | 2022-06-01 | 2022-06-15 | 2022-09-12 | 2022-09-23 | 70
0 | GDVPJ1260 | LOGISTICS MANAGEMENT PLAN - ICR | 10 | 2022-06-08 | 2022-06-22 | 2022-10-18 | 2022-10-31 | 91
0 | GDVPJ1140 | CONSTRUCTABILITY WORKSHOP PROCEDURE- IFA | 10 | 2022-06-29 | 2022-07-18 | 2022-10-10 | 2022-10-21 | 70
0 | GDVPJ1270 | LOGISTICS MANAGEMENT PLAN - IFA | 10 | 2022-07-06 | 2022-07-25 | 2022-11-15 | 2022-11-28 | 91
0 | GDVPJ1280 | LOGISTICS MANAGEMENT PLAN - IFC | 5 | 2022-08-08 | 2022-08-15 | 2022-12-15 | 2022-12-21 | 91
0 | GDVPJ1145 | CONSTRUCTABILITY WORKSHOP PROCEDURE- FINAL | 13 | 2022-08-01 | 2022-08-18 | 2022-11-07 | 2022-11-23 | 70
0 | GDVPJ1290 | FINAL DOCUMENTATION HANDOVER PROCEDURE - ICR | 20 | 2023-08-21 | 2023-09-18 | 2023-11-17 | 2023-12-15 | 63
0 | GDVPJ1300 | FINAL DOCUMENTATION HANDOVER PROCEDURE- IFA | 10 | 2023-10-03 | 2023-10-17 | 2024-01-02 | 2024-01-15 | 63
0 | GDVPJ1250 | FINAL DOCUMENTATION HANDOVER PROCEDURE - FINAL | 20 | 2023-10-17 | 2023-11-14 | 2024-01-16 | 2024-02-13 | 63
0 | GDVPJ1240 | PROJECT CLOSE-OUT REPORT - ICR | 20 | 2024-08-01 | 2024-08-28 | 2024-12-23 | 2025-01-17 | 101
0 | GDVPJ1245 | PROJECT CLOSE-OUT REPORT - IFA | 10 | 2024-09-12 | 2024-09-26 | 2025-02-03 | 2025-02-14 | 101
0 | GDVPJ1310 | PROJECT CLOSE-OUT REPORT - FINAL | 20 | 2025-01-31 | 2025-02-20 | 2025-03-02 | 2025-03-22 | 31
PROJECT CONTROL |  |  | 135 | 2021-12-19 | 2022-06-29 | 2021-12-19 | 2022-10-19 | 78
0 | GDVPC1000 | 30/90 DAYS FRONT END SCHEDULES - IFI | 7 | 2021-12-19 | 2021-12-27 | 2021-12-21 | 2021-12-30 | 3
0 | GDVPC1035 | PROGRESS REPORTING PROCEDURE - ICR | 15 | 2021-12-19 | 2022-01-07 | 2021-12-19 | 2022-01-10 | 1
0 | GDVPC1020 | PROGRESS MEASUREMENT PROCEDURE - ICR | 12 | 2021-12-23 | 2022-01-11 | 2021-12-27 | 2022-01-13 | 2
0 | GDVPC1005 | PLANNING & SCHEDULING PROCEDURE - ICR | 15 | 2021-12-23 | 2022-01-13 | 2021-12-26 | 2022-01-17 | 2
0 | GDVPC1065 | PROJECT INVOICING PROCEDURE - ICR | 20 | 2021-12-30 | 2022-01-28 | 2022-04-01 | 2022-04-29 | 65
0 | GDVPC1040 | PROGRESS REPORTING PROCEDURE - IFA | 10 | 2022-01-21 | 2022-02-04 | 2022-01-24 | 2022-02-07 | 1
0 | GDVPC1050 | PROJECT PLANNING PACKAGE - ICR | 30 | 2021-12-26 | 2022-02-04 | 2021-12-30 | 2022-02-11 | 5
0 | GDVPC1025 | PROGRESS MEASUREMENT PROCEDURE - IFA | 10 | 2022-01-25 | 2022-02-08 | 2022-01-27 | 2022-02-10 | 2
0 | GDVPC1010 | PLANNING & SCHEDULING PROCEDURE - IFA | 10 | 2022-01-28 | 2022-02-10 | 2022-01-31 | 2022-02-14 | 2
0 | GDVPC1070 | PROJECT INVOICING PROCEDURE - IFA | 10 | 2022-02-11 | 2022-02-25 | 2022-05-27 | 2022-06-09 | 72
0 | GDVPC1115 | MANAGEMENT OF CHANGE PROCEDURES - ICR | 20 | 2022-01-28 | 2022-02-25 | 2022-06-03 | 2022-06-30 | 87
0 | GDVPC1055 | PROJECT PLANNING PACKAGE - IFA | 8 | 2022-02-17 | 2022-02-28 | 2022-02-23 | 2022-03-07 | 5
0 | GDVPC1030 | PROGRESS MEASUREMENT PROCEDURE - FINAL | 7 | 2022-02-22 | 2022-03-03 | 2022-02-24 | 2022-03-07 | 2
0 | GDVPC1015 | PLANNING & SCHEDULING PROCEDURE - FINAL | 5 | 2022-02-25 | 2022-03-03 | 2022-02-28 | 2022-03-07 | 2
0 | GDVPC1045 | PROGRESS REPORTING PROCEDURE - FINAL | 10 | 2022-02-18 | 2022-03-04 | 2022-02-21 | 2022-03-07 | 1
0 | GDVPC1060 | PROJECT PLANNING PACKAGE - FINAL | 2 | 2022-03-08 | 2022-03-09 | 2022-08-19 | 2022-08-22 | 112
0 | GDVPC1100 | PROJECT VARIATION ORDER PROCEDURE - ICR | 20 | 2022-02-18 | 2022-03-18 | 2022-06-03 | 2022-06-30 | 72
0 | GDVPC1080 | SCHEDULE RISK ANALYSIS PROCEDURE - IFI | 40 | 2022-01-28 | 2022-03-24 | 2022-05-30 | 2022-07-27 | 83
0 | GDVPC1075 | PROJECT INVOICING PROCEDURE - FINAL | 10 | 2022-03-11 | 2022-03-25 | 2022-08-09 | 2022-08-22 | 101
0 | GDVPC1120 | MANAGEMENT OF CHANGE PROCEDURES - IFA | 15 | 2022-03-11 | 2022-04-01 | 2022-07-20 | 2022-08-09 | 87
0 | GDVPC1105 | PROJECT VARIATION ORDER PROCEDURE - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-07-20 | 2022-08-02 | 72
0 | GDVPC1085 | SCHEDULE RISK ANALYSIS REPORT - ICR | 20 | 2022-04-01 | 2022-04-29 | 2022-07-28 | 2022-08-24 | 78
0 | GDVPC1110 | PROJECT VARIATION ORDER PROCEDURE - FINAL | 10 | 2022-04-29 | 2022-05-18 | 2022-08-17 | 2022-08-30 | 72
0 | GDVPC1125 | MANAGEMENT OF CHANGE PROCEDURES - FINAL | 10 | 2022-05-11 | 2022-05-25 | 2022-08-24 | 2022-09-06 | 72
0 | GDVPC1090 | SCHEDULE RISK ANALYSIS REPORT - IFA | 10 | 2022-05-18 | 2022-06-01 | 2022-09-08 | 2022-09-21 | 78
0 | GDVPC1095 | SCHEDULE RISK ANALYSIS REPORT - FINAL | 10 | 2022-06-15 | 2022-06-29 | 2022-10-06 | 2022-10-19 | 78
HSE |  |  | 182 | 2021-12-30 | 2022-09-21 | 2022-03-01 | 2023-01-11 | 79
0 | GDVHS1000 | HSE MANUAL SAF-002 - CORPORATE DOCUMENT - IFI | 20 | 2021-12-30 | 2022-01-28 | 2022-03-01 | 2022-03-28 | 42
0 | GDVHS1005 | PROJECT HSE PLAN - ICR | 20 | 2022-01-07 | 2022-02-04 | 2022-04-20 | 2022-05-20 | 73
0 | GDVHS1040 | RISK ASSESSMENT FOR PRE-ENGINEERING GEOPHYSICAL SURVEY- IFI | 10 | 2022-01-28 | 2022-02-11 | 2022-03-29 | 2022-04-11 | 42
0 | GDVHS1015 | PROJECT HSE PLAN - IFA | 10 | 2022-02-18 | 2022-03-04 | 2022-06-06 | 2022-06-17 | 73
0 | GDVHS1025 | COVID 19 & BUSINESS CONTINUITY GUIDELINES - NPCC OFFICES - ICR | 30 | 2022-01-28 | 2022-03-11 | 2022-05-24 | 2022-07-04 | 79
0 | GDVHS1010 | NPCC ENVIRONMENT MANAGEMENT SYSTEM MANUAL - IFI | 30 | 2022-01-28 | 2022-03-11 | 2022-05-24 | 2022-07-04 | 79
0 | GDVHS1020 | PROJECT HSE PLAN - FINAL | 10 | 2022-03-18 | 2022-04-01 | 2022-07-04 | 2022-07-20 | 73
0 | GDVHS1030 | COVID 19 & BUSINESS CONTINUITY GUIDELINES - NPCC OFFICES - IFA | 10 | 2022-03-25 | 2022-04-08 | 2022-07-22 | 2022-08-04 | 79
0 | GDVHS1035 | COVID 19 & BUSINESS CONTINUITY GUIDELINES - NPCC OFFICES - FINAL | 10 | 2022-04-22 | 2022-05-11 | 2022-08-19 | 2022-09-01 | 79
0 | GDVHS1045 | CONSTRUCTION HSE PLAN - OFFSHORE - ICR | 16 | 2022-04-22 | 2022-05-19 | 2022-08-19 | 2022-09-09 | 79
0 | GDVHS1060 | CONSTRUCTION ENVIRONMENT MANAGEMENT PLAN - OFFSHORE - ICR | 16 | 2022-05-19 | 2022-06-10 | 2022-09-12 | 2022-10-03 | 79
0 | GDVHS1050 | CONSTRUCTION HSE PLAN - OFFSHORE - IFA | 10 | 2022-06-02 | 2022-06-16 | 2022-11-08 | 2022-11-21 | 110
0 | GDVHS1075 | WASTE MANAGEMENT PLAN - OFFSHORE - ICR | 20 | 2022-06-03 | 2022-07-01 | 2022-09-27 | 2022-10-24 | 79
0 | GDVHS1065 | CONSTRUCTION ENVIRONMENT MANAGEMENT PLAN - OFFSHORE - IFA | 10 | 2022-06-24 | 2022-07-13 | 2022-11-16 | 2022-11-29 | 100
0 | GDVHS1055 | CONSTRUCTION HSE PLAN - OFFSHORE - FINAL | 10 | 2022-06-30 | 2022-07-19 | 2022-12-08 | 2022-12-21 | 110
0 | GDVHS1090 | MEDICAL EVACUATION PROCEDURE (MEDEVAC) - OFFSHORE - ICR | 20 | 2022-06-17 | 2022-07-20 | 2022-10-11 | 2022-11-07 | 79
0 | GDVHS1110 | EMERGENCY RESPONSE PLAN - OFFSHORE - OFFSHORE - ICR | 20 | 2022-06-24 | 2022-07-27 | 2022-10-18 | 2022-11-14 | 79
0 | GDVHS1070 | CONSTRUCTION ENVIRONMENT MANAGEMENT PLAN - OFFSHORE - FINAL | 4 | 2022-07-27 | 2022-08-02 | 2022-12-16 | 2022-12-21 | 100
0 | GDVHS1080 | WASTE MANAGEMENT PLAN - OFFSHORE - IFA | 10 | 2022-07-20 | 2022-08-03 | 2022-11-29 | 2022-12-14 | 94
0 | GDVHS1095 | MEDICAL EVACUATION PROCEDURE (MEDEVAC) - OFFSHORE - IFA | 10 | 2022-08-03 | 2022-08-17 | 2022-11-29 | 2022-12-14 | 84
0 | GDVHS1120 | EMERGENCY RESPONSE PLAN - OFFSHORE - OFFSHORE - IFA | 10 | 2022-08-10 | 2022-08-24 | 2022-11-29 | 2022-12-14 | 79
0 | GDVHS1085 | WASTE MANAGEMENT PLAN - OFFSHORE- FINAL | 10 | 2022-08-17 | 2022-08-31 | 2022-12-29 | 2023-01-11 | 94
0 | GDVHS1100 | MEDICAL EVACUATION PROCEDURE (MEDEVAC) - OFFSHORE - FINAL | 10 | 2022-08-31 | 2022-09-14 | 2022-12-29 | 2023-01-11 | 84
0 | GDVHS1130 | EMERGENCY RESPONSE PLAN - OFFSHORE - OFFSHORE - FINAL | 10 | 2022-09-07 | 2022-09-21 | 2022-12-29 | 2023-01-11 | 79
QUALITY ASSURANCE / QUALITY CONTROL (QA/QC) |  |  | 261 | 2021-12-30 | 2023-01-12 | 2022-03-29 | 2023-06-06 | 102
0 | GDVQA1000 | PROJECT QUALITY PLAN - ICR | 20 | 2021-12-30 | 2022-01-28 | 2022-03-29 | 2022-04-25 | 62
0 | GDVQA1015 | PROJECT QUALITY AUDIT SCHEDULE - ICR | 20 | 2022-01-07 | 2022-02-04 | 2022-04-22 | 2022-05-24 | 75
0 | GDVQA1005 | PROJECT QUALITY PLAN - IFA | 15 | 2022-02-11 | 2022-03-04 | 2022-05-13 | 2022-06-02 | 62
0 | GDVQA1020 | PROJECT QUALITY AUDIT SCHEDULE - IFA | 20 | 2022-02-18 | 2022-03-18 | 2022-06-08 | 2022-07-05 | 75
0 | GDVQA1010 | PROJECT QUALITY PLAN - FINAL | 10 | 2022-03-18 | 2022-04-01 | 2022-06-21 | 2022-07-04 | 64
0 | GDVQA1030 | NON CONFIRMANCE REPORTING SYSTEM PROCEDURE - ICR | 20 | 2022-03-18 | 2022-04-15 | 2022-06-17 | 2022-07-19 | 62
0 | GDVQA1025 | PROJECT QUALITY AUDIT SCHEDULE - FINAL | 10 | 2022-04-01 | 2022-04-15 | 2022-07-25 | 2022-08-05 | 75
0 | GDVQA1045 | PROJECT MATERIAL CONTROL,INSPECTION AND TRACEABILITY PROCEDURE(CORPORATE PROCEDURE) - ICR | 20 | 2022-03-25 | 2022-04-22 | 2022-06-24 | 2022-07-26 | 62
0 | GDVQA1210 | QC PERSONNEL LIST (ONSHORE) - ICR | 20 | 2022-04-01 | 2022-04-29 | 2022-07-05 | 2022-08-04 | 64
0 | GDVQA1275 | RADIOGRAPHIC TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - ICR | 20 | 2022-04-15 | 2022-05-18 | 2022-07-22 | 2022-08-18 | 64
0 | GDVQA1500 | PIPELINE CAD (THERMIT) WELDING PROCEDURE - ICR | 20 | 2022-04-15 | 2022-05-18 | 2022-08-08 | 2022-09-02 | 75
0 | GDVQA1425 | INSPECTION & TEST PLAN FOR ONSHORE CONSTRUCTION WORKS - ICR | 20 | 2022-04-15 | 2022-05-18 | 2022-07-22 | 2022-08-18 | 64
0 | GDVQA1290 | ULTRASONIC TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - ICR | 20 | 2022-04-15 | 2022-05-18 | 2022-07-22 | 2022-08-18 | 64
0 | GDVQA1305 | MAGNETIC PARTICLE TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - ICR | 20 | 2022-04-15 | 2022-05-18 | 2022-07-22 | 2022-08-18 | 64
0 | GDVQA1240 | MUSSAFAH WELDERS LIST (STRUCTURAL) - IFI | 35 | 2022-03-25 | 2022-05-18 | 2022-06-28 | 2022-08-18 | 64
0 | GDVQA1455 | STRUCTURAL NDT PLAN - ICR | 20 | 2022-04-22 | 2022-05-25 | 2022-07-29 | 2022-08-25 | 64
0 | GDVQA1060 | DIMENSIONAL CONTROL PROCEDURE - ICR | 20 | 2022-04-22 | 2022-05-25 | 2022-07-27 | 2022-08-23 | 62
0 | GDVQA1075 | POSITIVE MATERIAL IDENTIFICATION (PMI) PROCEDURE - ICR | 20 | 2022-04-27 | 2022-05-30 | 2022-08-01 | 2022-08-26 | 62
0 | GDVQA1090 | WELDING CONSUMABLE CONTROL PROCEDURE - ICR | 20 | 2022-05-05 | 2022-06-02 | 2022-08-04 | 2022-08-31 | 62
0 | GDVQA1485 | HARDNESS TEST PROCEDURE - ICR | 20 | 2022-05-11 | 2022-06-08 | 2022-08-12 | 2022-09-08 | 64
0 | GDVQA1470 | PROCEDURE FOR DIGITIZATION OF RADIOGRAPHS (NPCC YARD & OFFSHORE WORKS) - ICR | 20 | 2022-05-11 | 2022-06-08 | 2022-08-12 | 2022-09-08 | 64
0 | GDVQA1105 | WELDING PROCEDURES - STRUCTURAL - ICR | 20 | 2022-05-12 | 2022-06-09 | 2022-08-11 | 2022-09-07 | 62
0 | GDVQA1280 | RADIOGRAPHIC TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - IFA | 20 | 2022-05-18 | 2022-06-15 | 2022-10-10 | 2022-11-04 | 100
0 | GDVQA1505 | PIPELINE CAD (THERMIT) WELDING PROCEDURE - IFA | 20 | 2022-05-18 | 2022-06-15 | 2022-09-05 | 2022-09-30 | 75
0 | GDVQA1050 | PROJECT MATERIAL CONTROL,INSPECTION AND TRACEABILITY PROCEDURE(CORPORATE PROCEDURE) - IFA | 25 | 2022-05-11 | 2022-06-15 | 2022-09-12 | 2022-10-14 | 85
0 | GDVQA1035 | NON CONFIRMANCE REPORTING SYSTEM PROCEDURE - IFA | 30 | 2022-04-29 | 2022-06-15 | 2022-08-22 | 2022-09-30 | 75
0 | GDVQA1215 | QC PERSONNEL LIST (ONSHORE) - IFA | 20 | 2022-05-18 | 2022-06-15 | 2022-09-16 | 2022-10-13 | 84
0 | GDVQA1335 | NDT OPERATORS LIST (ONSHORE / OFFSHORE) - ICR | 20 | 2022-05-23 | 2022-06-20 | 2022-10-28 | 2022-11-24 | 111
0 | GDVQA1365 | AUTOMATED ULTRASONIC TESTING PROCEDURE FOR PIPELINE WELDS - ICR | 20 | 2022-05-23 | 2022-06-20 | 2022-10-18 | 2022-11-14 | 103
0 | GDVQA1350 | PIPING WELDS PHASED ARRAY ULTRASONIC TESTING PROCEDURE - ICR | 20 | 2022-05-23 | 2022-06-20 | 2022-10-18 | 2022-11-14 | 103
0 | GDVQA1380 | ENGINEERING CRITICALITY ASSESSMENT REPORT FOR PIPELINE WELDS- ICR | 20 | 2022-05-23 | 2022-06-20 | 2022-10-18 | 2022-11-14 | 103
0 | GDVQA1320 | NDT PROCEDURES (PIPELINES) - ICR | 20 | 2022-05-23 | 2022-06-20 | 2022-08-22 | 2022-09-16 | 62
0 | GDVQA1295 | ULTRASONIC TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - IFA | 20 | 2022-06-01 | 2022-06-29 | 2022-09-26 | 2022-10-21 | 80
0 | GDVQA1430 | INSPECTION & TEST PLAN FOR ONSHORE CONSTRUCTION WORKS - IFA | 20 | 2022-06-01 | 2022-06-29 | 2022-09-05 | 2022-09-30 | 65
0 | GDVQA1310 | MAGNETIC PARTICLE TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - IFA | 20 | 2022-06-01 | 2022-06-29 | 2022-09-05 | 2022-09-30 | 65
0 | GDVQA1460 | STRUCTURAL NDT PLAN - IFA | 20 | 2022-06-08 | 2022-07-06 | 2022-09-26 | 2022-10-21 | 75
0 | GDVQA1065 | DIMENSIONAL CONTROL PROCEDURE - IFA | 20 | 2022-06-08 | 2022-07-06 | 2022-10-03 | 2022-10-28 | 80
0 | GDVQA1640 | LIQUID PENETRANT PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - ICR | 20 | 2022-06-08 | 2022-07-06 | 2022-09-16 | 2022-10-13 | 69
0 | GDVQA1120 | WELDING PROCEDURES - PIPING - ICR | 20 | 2022-06-09 | 2022-07-07 | 2022-09-30 | 2022-10-27 | 78
0 | GDVQA1080 | POSITIVE MATERIAL IDENTIFICATION (PMI) PROCEDURE - IFA | 20 | 2022-06-13 | 2022-07-14 | 2022-09-19 | 2022-10-14 | 67
0 | GDVQA1285 | RADIOGRAPHIC TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - FINAL | 20 | 2022-06-15 | 2022-07-18 | 2022-11-07 | 2022-12-06 | 100
0 | GDVQA1510 | PIPELINE CAD (THERMIT) WELDING PROCEDURE - FINAL | 20 | 2022-06-15 | 2022-07-18 | 2022-10-03 | 2022-10-28 | 75
0 | GDVQA1225 | QC PERSONNEL LIST (OFFSHORE) - ICR | 20 | 2022-06-15 | 2022-07-18 | 2022-10-14 | 2022-11-10 | 84
0 | GDVQA1550 | INSPECTION AND TEST PLAN (MATERIAL RECEIVING INSPECTION) - ICR | 10 | 2022-06-29 | 2022-07-18 | 2022-09-30 | 2022-10-13 | 64
0 | GDVQA1095 | WELDING CONSUMABLE CONTROL PROCEDURE - IFA | 20 | 2022-06-16 | 2022-07-19 | 2022-09-26 | 2022-10-21 | 69
0 | GDVQA1395 | BASELINE SURVEY PROCEDURE - ICR | 20 | 2022-06-20 | 2022-07-21 | 2022-11-15 | 2022-12-14 | 103
0 | GDVQA1410 | AUT / NDT PERSONNEL QUALIFICATIONS SUMMARY - ICR | 20 | 2022-06-20 | 2022-07-21 | 2022-11-15 | 2022-12-14 | 103
0 | GDVQA1490 | HARDNESS TEST PROCEDURE - IFA | 20 | 2022-06-22 | 2022-07-25 | 2022-09-23 | 2022-10-20 | 64
0 | GDVQA1475 | PROCEDURE FOR DIGITIZATION OF RADIOGRAPHS (NPCC YARD & OFFSHORE WORKS) - IFA | 20 | 2022-06-22 | 2022-07-25 | 2022-09-26 | 2022-10-21 | 65
0 | GDVQA1110 | WELDING PROCEDURES - STRUCTURAL - IFA | 20 | 2022-06-23 | 2022-07-26 | 2022-09-26 | 2022-10-21 | 64
0 | GDVQA1245 | MUSSAFAH WELDERS LIST (PIPING) - IFI | 30 | 2022-06-09 | 2022-07-26 | 2023-01-25 | 2023-03-07 | 159
0 | GDVQA1220 | QC PERSONNEL LIST (ONSHORE) - FINAL | 20 | 2022-06-29 | 2022-08-01 | 2022-11-07 | 2022-12-06 | 90
0 | GDVQA1520 | INSTALLATION PROCEDURE FOR E&I WORKS - ICR | 20 | 2022-06-29 | 2022-08-01 | 2022-09-30 | 2022-10-27 | 64
0 | GDVQA1340 | NDT OPERATORS LIST (ONSHORE / OFFSHORE) - IFA | 20 | 2022-07-04 | 2022-08-04 | 2022-12-13 | 2023-01-09 | 111
0 | GDVQA1355 | PIPING WELDS PHASED ARRAY ULTRASONIC TESTING PROCEDURE - IFA | 20 | 2022-07-04 | 2022-08-04 | 2022-12-27 | 2023-01-23 | 121
0 | GDVQA1385 | ENGINEERING CRITICALITY ASSESSMENT REPORT FOR PIPELINE WELDS - IFA | 20 | 2022-07-04 | 2022-08-04 | 2022-12-13 | 2023-01-09 | 111
0 | GDVQA1325 | NDT PROCEDURES (PIPELINES) - IFA | 20 | 2022-07-04 | 2022-08-04 | 2022-10-03 | 2022-10-28 | 62
0 | GDVQA1370 | AUTOMATED ULTRASONIC TESTING PROCEDURE FOR PIPELINE WELDS - IFA | 20 | 2022-07-04 | 2022-08-04 | 2022-12-13 | 2023-01-09 | 111
0 | GDVQA1195 | INSPECTION & TEST PLAN FOR SUBSEA UMBILICAL & CABLE INSTALLATION - ICR | 20 | 2022-07-06 | 2022-08-08 | 2022-12-08 | 2023-01-04 | 106
0 | GDVQA1650 | LIQUID PENETRANT PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - IFA | 20 | 2022-07-06 | 2022-08-08 | 2022-10-14 | 2022-11-10 | 69
0 | GDVQA1150 | INSPECTION AND TEST PLAN FOR E & I WORKS (ONSHORE) - ICR | 20 | 2022-07-07 | 2022-08-09 | 2022-10-28 | 2022-11-24 | 78
0 | GDVQA1465 | STRUCTURAL NDT PLAN - FINAL | 15 | 2022-07-25 | 2022-08-15 | 2022-11-07 | 2022-11-25 | 75
0 | GDVQA1435 | INSPECTION & TEST PLAN FOR ONSHORE CONSTRUCTION WORKS - FINAL | 20 | 2022-07-18 | 2022-08-15 | 2022-10-17 | 2022-11-11 | 65
0 | GDVQA1300 | ULTRASONIC TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - FINAL | 20 | 2022-07-18 | 2022-08-15 | 2022-11-07 | 2022-12-06 | 80
0 | GDVQA1560 | INSPECTION AND TEST PLAN (MATERIAL RECEIVING INSPECTION) - IFA | 10 | 2022-08-01 | 2022-08-15 | 2022-10-28 | 2022-11-10 | 64
0 | GDVQA1580 | QC DOSSIER INDEX - ICR | 20 | 2022-07-18 | 2022-08-15 | 2022-10-19 | 2022-11-15 | 67
0 | GDVQA1400 | BASELINE SURVEY PROCEDURE - IFA | 20 | 2022-07-21 | 2022-08-18 | 2023-01-12 | 2023-02-08 | 123
0 | GDVQA1440 | INSPECTION & TEST PLAN FOR OFFSHORE CONSTRUCTION WORKS - ICR | 20 | 2022-07-21 | 2022-08-18 | 2023-01-04 | 2023-01-31 | 117
0 | GDVQA1040 | NON CONFIRMANCE REPORTING SYSTEM PROCEDURE - FINAL | 35 | 2022-06-29 | 2022-08-22 | 2022-10-17 | 2022-12-06 | 75
0 | GDVQA1125 | WELDING PROCEDURES - PIPING - IFA | 20 | 2022-07-26 | 2022-08-23 | 2023-01-25 | 2023-02-21 | 129
0 | GDVQA1135 | WELDING PROCEDURES - PIPELINE SPOOLS - ICR | 20 | 2022-07-26 | 2022-08-23 | 2022-12-14 | 2023-01-10 | 99
0 | GDVQA1230 | QC PERSONNEL LIST (OFFSHORE) - IFA | 20 | 2022-08-01 | 2022-08-29 | 2022-11-25 | 2022-12-26 | 84
0 | GDVQA1255 | OFFSHORE WELDERS LIST (RISERS & TIE-IN) - IFI | 30 | 2022-07-18 | 2022-08-29 | 2023-01-19 | 2023-03-01 | 131
0 | GDVQA1530 | INSTALLATION PROCEDURE FOR E&I WORKS - IFA | 20 | 2022-08-01 | 2022-08-29 | 2022-12-13 | 2023-01-09 | 94
0 | GDVQA1100 | WELDING CONSUMABLE CONTROL PROCEDURE - FINAL | 20 | 2022-08-02 | 2022-08-30 | 2022-11-07 | 2022-12-06 | 69
0 | GDVQA1415 | AUT / NDT PERSONNEL QUALIFICATIONS SUMMARY - IFA | 20 | 2022-08-04 | 2022-09-01 | 2022-12-29 | 2023-01-25 | 103
0 | GDVQA1085 | POSITIVE MATERIAL IDENTIFICATION (PMI) PROCEDURE - FINAL | 25 | 2022-07-28 | 2022-09-01 | 2022-10-31 | 2022-12-06 | 67
0 | GDVQA1495 | HARDNESS TEST PROCEDURE - FINAL | 20 | 2022-08-08 | 2022-09-05 | 2022-11-07 | 2022-12-06 | 65
0 | GDVQA1315 | MAGNETIC PARTICLE TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - FINAL | 35 | 2022-07-18 | 2022-09-05 | 2022-10-17 | 2022-12-06 | 65
0 | GDVQA1480 | PROCEDURE FOR DIGITIZATION OF RADIOGRAPHS (NPCC YARD & OFFSHORE WORKS) - FINAL | 20 | 2022-08-08 | 2022-09-05 | 2022-11-07 | 2022-12-06 | 65
0 | GDVQA1590 | QC DOSSIER INDEX - IFA | 15 | 2022-08-15 | 2022-09-05 | 2022-11-16 | 2022-12-08 | 67
0 | GDVQA1660 | LIQUID PENETRANT PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS - FINAL | 20 | 2022-08-08 | 2022-09-05 | 2022-11-11 | 2022-12-12 | 69
0 | GDVQA1115 | WELDING PROCEDURES - STRUCTURAL - FINAL | 20 | 2022-08-09 | 2022-09-06 | 2022-11-07 | 2022-12-06 | 64
0 | GDVQA1330 | NDT PROCEDURES (PIPELINES) - FINAL | 15 | 2022-08-18 | 2022-09-08 | 2022-11-14 | 2022-12-06 | 62
0 | GDVQA1055 | PROJECT MATERIAL CONTROL,INSPECTION AND TRACEABILITY PROCEDURE(CORPORATE PROCEDURE) - FINAL | 25 | 2022-08-04 | 2022-09-08 | 2022-10-31 | 2022-12-06 | 62
0 | GDVQA1070 | DIMENSIONAL CONTROL PROCEDURE - FINAL | 15 | 2022-08-18 | 2022-09-08 | 2022-11-14 | 2022-12-06 | 62
0 | GDVQA1260 | OFFSHORE WELDERS LIST (PIPELINE) - AUTOMATIC & REPAIR - IFI | 30 | 2022-08-01 | 2022-09-12 | 2023-02-02 | 2023-03-15 | 131
0 | GDVQA1570 | INSPECTION AND TEST PLAN (MATERIAL RECEIVING INSPECTION) - FINAL | 10 | 2022-08-29 | 2022-09-12 | 2022-11-25 | 2022-12-12 | 64
0 | GDVQA1405 | BASELINE SURVEY PROCEDURE - FINAL | 20 | 2022-08-18 | 2022-09-15 | 2023-02-09 | 2023-03-08 | 123
0 | GDVQA1200 | INSPECTION & TEST PLAN FOR SUBSEA UMBILICAL & CABLE INSTALLATION - IFA | 20 | 2022-08-22 | 2022-09-19 | 2023-01-19 | 2023-02-15 | 106
0 | GDVQA1155 | INSPECTION AND TEST PLAN FOR E & I WORKS (ONSHORE) - IFA | 20 | 2022-08-23 | 2022-09-20 | 2022-12-13 | 2023-01-09 | 78
0 | GDVQA1360 | PIPING WELDS PHASED ARRAY ULTRASONIC TESTING PROCEDURE - FINAL | 35 | 2022-08-04 | 2022-09-22 | 2023-01-24 | 2023-03-13 | 121
0 | GDVQA1265 | OFFSHORE WELDERS LIST (PIPELINE) - MANUAL & REPAIR - IFI | 30 | 2022-08-15 | 2022-09-26 | 2023-02-16 | 2023-03-29 | 131
0 | GDVQA1540 | INSTALLATION PROCEDURE FOR E&I WORKS - FINAL | 20 | 2022-08-29 | 2022-09-26 | 2023-01-10 | 2023-02-06 | 94
0 | GDVQA1600 | QC DOSSIER INDEX - FINAL | 15 | 2022-09-05 | 2022-09-26 | 2022-12-09 | 2022-12-29 | 67
0 | GDVQA1180 | INSPECTION AND TEST PLAN FOR PIPELAYING WORK - ICR | 20 | 2022-08-30 | 2022-09-27 | 2022-12-20 | 2023-01-16 | 78
0 | GDVQA1445 | INSPECTION & TEST PLAN FOR OFFSHORE CONSTRUCTION WORKS - IFA | 20 | 2022-09-01 | 2022-09-29 | 2023-02-15 | 2023-03-14 | 117
0 | GDVQA1140 | WELDING PROCEDURES - PIPELINE SPOOLS - IFA | 20 | 2022-09-06 | 2022-10-04 | 2023-01-25 | 2023-02-21 | 99
0 | GDVQA1345 | NDT OPERATORS LIST (ONSHORE / OFFSHORE) - FINAL | 35 | 2022-08-18 | 2022-10-06 | 2023-01-24 | 2023-03-13 | 111
0 | GDVQA1375 | AUTOMATED ULTRASONIC TESTING PROCEDURE FOR PIPELINE WELDS - FINAL | 35 | 2022-08-18 | 2022-10-06 | 2023-01-24 | 2023-03-13 | 111
0 | GDVQA1390 | ENGINEERING CRITICALITY ASSESSMENT REPORT FOR PIPELINE WELDS - FINAL | 35 | 2022-08-18 | 2022-10-06 | 2023-01-24 | 2023-03-13 | 111
0 | GDVQA1235 | QC PERSONNEL LIST (OFFSHORE) - FINAL | 20 | 2022-09-12 | 2022-10-10 | 2023-01-10 | 2023-02-06 | 84
0 | GDVQA1420 | AUT / NDT PERSONNEL QUALIFICATIONS SUMMARY - FINAL | 20 | 2022-09-15 | 2022-10-13 | 2023-02-09 | 2023-03-08 | 103
0 | GDVQA1130 | WELDING PROCEDURES - PIPING - FINAL | 35 | 2022-09-06 | 2022-10-25 | 2023-03-08 | 2023-04-27 | 129
0 | GDVQA1205 | INSPECTION & TEST PLAN FOR SUBSEA UMBILICAL & CABLE INSTALLATION - FINAL | 20 | 2022-10-03 | 2022-10-31 | 2023-03-02 | 2023-03-29 | 106
0 | GDVQA1185 | INSPECTION AND TEST PLAN FOR PIPELAYING WORK - IFA | 20 | 2022-10-11 | 2022-11-08 | 2023-01-31 | 2023-02-27 | 78
0 | GDVQA1450 | INSPECTION & TEST PLAN FOR OFFSHORE CONSTRUCTION WORKS - FINAL | 20 | 2022-10-13 | 2022-11-10 | 2023-03-29 | 2023-04-27 | 117
0 | GDVQA1250 | OFFSHORE WELDERS LIST (STRUCTURAL) - IFI | 30 | 2022-10-10 | 2022-11-21 | 2023-02-07 | 2023-03-20 | 84
0 | GDVQA1160 | INSPECTION AND TEST PLAN FOR E & I WORKS (ONSHORE) - FINAL | 35 | 2022-10-04 | 2022-11-22 | 2023-04-17 | 2023-06-06 | 137
0 | GDVQA1145 | WELDING PROCEDURES - PIPELINE SPOOLS - FINAL | 35 | 2022-10-18 | 2022-12-08 | 2023-03-08 | 2023-04-27 | 99
0 | GDVQA1270 | OFFSHORE WELDERS LIST (PIPING) - IFI | 30 | 2022-11-21 | 2023-01-04 | 2023-03-21 | 2023-05-03 | 84
0 | GDVQA1190 | INSPECTION AND TEST PLAN FOR PIPELAYING WORK - FINAL | 35 | 2022-11-22 | 2023-01-12 | 2023-03-14 | 2023-05-03 | 78
WORKSHOP & STUDIES |  |  | 580 | 2022-02-02 | 2024-05-22 | 2022-05-09 | 2024-09-19 | 82
0 | GDVWS1005 | SCHEDULE REVIEW WORKSHOP-1 | 1 | 2022-02-02 | 2022-02-02 | 2022-05-09 | 2022-05-09 | 65
0 | GDVWS1010 | LESSEON LEARN WORKSHOP | 1 | 2022-02-21 | 2022-02-21 | 2022-07-27 | 2022-07-27 | 106
0 | GDVWS1020 | PROJECT RISK REVIEW WORKSHOP-1 | 1 | 2022-03-18 | 2022-03-18 | 2022-07-28 | 2022-07-28 | 88
0 | GDVWS1195 | SCHEDULE REVIEW WORKSHOP-2 | 1 | 2022-05-23 | 2022-05-23 | 2022-10-19 | 2022-10-19 | 104
0 | GDVWS1035 | QUALITY REVIEW WORKSHOP | 1 | 2022-06-01 | 2022-06-01 | 2022-11-28 | 2022-11-28 | 125
0 | GDVWS1095 | PROJECT RISK REVIEW WORKSHOP-2 | 1 | 2022-07-06 | 2022-07-06 | 2022-10-19 | 2022-10-19 | 72
0 | GDVWS1165 | FABRICATION READINESS REVIEW WORKSHOP | 1 | 2022-08-11 | 2022-08-11 | 2022-12-12 | 2022-12-12 | 85
0 | GDVWS1025 | CONSTRUCTIBILITY REVIEW WORKSHOP | 3 | 2022-08-23 | 2022-08-26 | 2022-11-29 | 2022-12-05 | 70
0 | GDVWS1085 | TIE-IN REVIEW WORKSHOP | 1 | 2022-10-03 | 2022-10-03 | 2023-01-18 | 2023-01-18 | 75
0 | GDVWS1115 | PROJECT RISK REVIEW WORKSHOP-3 | 1 | 2022-10-19 | 2022-10-19 | 2023-04-17 | 2023-04-17 | 126
0 | GDVWS1205 | SCHEDULE REVIEW WORKSHOP-3 | 1 | 2022-11-30 | 2022-11-30 | 2023-04-27 | 2023-04-27 | 102
0 | GDVWS1045 | SIMOP WORKSHOP -1 REVIEW WORKSHOP | 2 | 2023-01-10 | 2023-01-11 | 2023-04-26 | 2023-04-27 | 74
0 | GDVWS1185 | PIPELINE INSTALLATION READINESS REVIEW WORKSHOP | 1 | 2023-01-12 | 2023-01-12 | 2023-04-07 | 2023-04-07 | 62
0 | GDVWS1125 | PROJECT RISK REVIEW WORKSHOP-4 | 1 | 2023-01-25 | 2023-01-25 | 2023-08-31 | 2023-09-01 | 151
0 | GDVWS1065 | SIMOP WORKSHOP -2 REVIEW WORKSHOP | 2 | 2023-02-23 | 2023-02-24 | 2023-11-15 | 2023-11-16 | 182
0 | GDVWS1215 | SCHEDULE REVIEW WORKSHOP-4 | 1 | 2023-04-20 | 2023-04-20 | 2023-09-08 | 2023-09-08 | 95
0 | GDVWS1135 | PROJECT RISK REVIEW WORKSHOP-5 | 1 | 2023-04-26 | 2023-04-26 | 2024-03-04 | 2024-03-04 | 215
0 | GDVWS1145 | PROJECT RISK REVIEW WORKSHOP-6 | 1 | 2023-07-05 | 2023-07-05 | 2024-04-25 | 2024-04-25 | 203
0 | GDVWS1175 | DECK INSTALLATION & HOOK-UP WORKS READINESS REVIEW WORKSHOP | 1 | 2023-09-14 | 2023-09-15 | 2023-11-21 | 2023-11-21 | 47
0 | GDVWS1155 | PROJECT RISK REVIEW WORKSHOP-7 | 1 | 2023-10-11 | 2023-10-11 | 2024-07-17 | 2024-07-17 | 192
0 | GDVWS1075 | PSSR REVIEW WORKSHOP | 4 | 2023-12-18 | 2023-12-21 | 2024-04-29 | 2024-05-02 | 90
0 | GDVWS1225 | SCHEDULE RISK REVIEW WORKSHOP-5 | 1 | 2023-12-28 | 2023-12-28 | 2024-05-09 | 2024-05-09 | 90
0 | GDVWS1245 | OPERATION READINESS PEER REVIEW WORKSHOP | 1 | 2024-01-09 | 2024-01-09 | 2024-05-20 | 2024-05-20 | 90
0 | GDVWS1255 | PROJECT RISK REVIEW WORKSHOP-8 | 1 | 2024-01-24 | 2024-01-24 | 2024-07-18 | 2024-07-18 | 119
0 | GDVWS1265 | PROJECT RISK REVIEW WORKSHOP-9 | 1 | 2024-04-24 | 2024-04-24 | 2024-07-19 | 2024-07-19 | 59
0 | GDVWS1235 | SCHEDULE RISK REVIEW WORKSHOP-6 | 1 | 2024-05-22 | 2024-05-22 | 2024-09-19 | 2024-09-19 | 82
PROCUREMENT |  |  | 130 | 2022-01-07 | 2022-07-18 | 2022-03-15 | 2022-09-28 | 53
0 | GDVPT1000 | PROJECT PROCUREMENT PLAN - ICR | 20 | 2022-01-07 | 2022-02-04 | 2022-03-15 | 2022-04-11 | 47
0 | GDVPT1015 | PROJECT VENDOR LIST (PVL) - ICR | 15 | 2022-01-21 | 2022-02-11 | 2022-05-06 | 2022-05-26 | 72
0 | GDVPT1020 | PROJECT VENDOR LIST (PVL) - IFA | 10 | 2022-02-25 | 2022-03-11 | 2022-06-10 | 2022-06-23 | 72
0 | GDVPT1005 | PROJECT PROCUREMENT PLAN - IFA | 15 | 2022-02-18 | 2022-03-11 | 2022-04-26 | 2022-05-19 | 47
0 | GDVPT1030 | LIST OF LONG LEAD ITEM (LLIS) - ICR | 10 | 2022-03-04 | 2022-03-18 | 2022-05-13 | 2022-05-26 | 47
0 | GDVPT1010 | PROJECT PROCUREMENT PLAN - FINAL | 5 | 2022-03-25 | 2022-04-01 | 2022-07-14 | 2022-07-20 | 73
0 | GDVPT1025 | PROJECT VENDOR LIST (PVL)- FINAL | 6 | 2022-03-25 | 2022-04-04 | 2022-07-13 | 2022-07-20 | 72
0 | GDVPT1035 | LIST OF LONG LEAD ITEM (LLIS) - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-06-13 | 2022-06-24 | 48
0 | GDVPT1045 | VENDOR INSPECTION COORDINATION PROCEDURE - ICR | 20 | 2022-03-18 | 2022-04-15 | 2022-05-27 | 2022-06-23 | 47
0 | GDVPT1050 | VENDOR INSPECTION COORDINATION PROCEDURE - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-07-13 | 2022-07-26 | 47
0 | GDVPT1040 | LIST OF LONG LEAD ITEM (LLIS) FINAL | 10 | 2022-04-29 | 2022-05-18 | 2022-07-14 | 2022-07-27 | 48
0 | GDVPT1065 | VENDOR DOCUMENT MANAGEMENT PROCEDURE - ICR | 20 | 2022-04-15 | 2022-05-18 | 2022-07-04 | 2022-08-03 | 53
0 | GDVPT1055 | VENDOR INSPECTION COORDINATION PROCEDURE - FINAL | 6 | 2022-06-01 | 2022-06-09 | 2022-08-10 | 2022-08-17 | 47
0 | GDVPT1075 | VENDOR DOCUMENT MANAGEMENT PROCEDURE- IFA | 10 | 2022-06-01 | 2022-06-15 | 2022-08-18 | 2022-08-31 | 53
0 | GDVPT1085 | VENDOR DOCUMENT MANAGEMENT PROCEDURE - IFC | 10 | 2022-06-29 | 2022-07-18 | 2022-09-15 | 2022-09-28 | 53
ONSHORE YARD FABRICATION |  |  | 150 | 2022-03-18 | 2022-10-24 | 2022-08-02 | 2023-06-21 | 169
0 | GDVYF1000 | STRUCTURAL FABRICATION AND ERECTION PROCEDURE - ICR | 20 | 2022-03-18 | 2022-04-15 | 2022-08-02 | 2022-08-29 | 91
0 | GDVYF1015 | PIPING FABRICATION AND ERECTION PROCEDURE - ICR | 20 | 2022-03-25 | 2022-04-22 | 2022-09-27 | 2022-10-24 | 126
0 | GDVYF1170 | PROCEDURE FOR PWHT OF STRUCTURAL WORKS AT SITE (FIELD JOINTS)- ICR | 20 | 2022-04-01 | 2022-04-29 | 2022-09-02 | 2022-09-29 | 104
0 | GDVYF1030 | DISTORTION (FREESPAN) CORRECTION PROCEDURE - ICR | 10 | 2022-04-15 | 2022-04-29 | 2022-08-30 | 2022-09-12 | 91
0 | GDVYF1045 | SURFACE PREPARATION AND PAINTING PROCEDURE - ICR | 20 | 2022-04-08 | 2022-05-11 | 2022-08-23 | 2022-09-19 | 91
0 | GDVYF1060 | POST WELD HEAT TREATMENT (PWHT) PROCEDURE (PIPING) - ONSHORE - ICR | 20 | 2022-04-15 | 2022-05-18 | 2022-08-30 | 2022-09-26 | 91
0 | GDVYF1005 | STRUCTURAL FABRICATION AND ERECTION PROCEDURE - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-09-21 | 2022-10-04 | 97
0 | GDVYF1020 | PIPING FABRICATION AND ERECTION PROCEDURE - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-11-08 | 2022-11-21 | 126
0 | GDVYF1175 | PROCEDURE FOR PWHT OF STRUCTURAL WORKS AT SITE (FIELD JOINTS) - IFA | 10 | 2022-05-18 | 2022-06-01 | 2022-11-08 | 2022-11-21 | 121
0 | GDVYF1035 | DISTORTION (FREESPAN) CORRECTION PROCEDURE- IFA | 10 | 2022-05-18 | 2022-06-01 | 2022-11-08 | 2022-11-21 | 121
0 | GDVYF1050 | SURFACE PREPARATION AND PAINTING PROCEDURE - IFA | 10 | 2022-05-25 | 2022-06-08 | 2022-11-08 | 2022-11-21 | 116
0 | GDVYF1010 | STRUCTURAL FABRICATION AND ERECTION PROCEDURE - FINAL | 10 | 2022-06-01 | 2022-06-15 | 2022-11-08 | 2022-11-21 | 111
0 | GDVYF1065 | POST WELD HEAT TREATMENT (PWHT) PROCEDURE (PIPING) - ONSHORE - IFA | 10 | 2022-06-01 | 2022-06-15 | 2022-11-08 | 2022-11-21 | 111
0 | GDVYF1105 | HOT DIP GALVANIZING PROCEDURE- ICR | 20 | 2022-05-18 | 2022-06-15 | 2022-09-27 | 2022-10-24 | 91
0 | GDVYF1135 | PASSIVE FIRE PROOFING PROCEDURE - ICR | 20 | 2022-05-18 | 2022-06-15 | 2022-09-27 | 2022-10-24 | 91
0 | GDVYF1090 | EQUIPMENT INSULATION PROCEDURE - HOT & COLD - ONSHORE - ICR | 20 | 2022-05-18 | 2022-06-15 | 2022-09-27 | 2022-10-24 | 91
0 | GDVYF1200 | FABRICATION PROCEDURE FOR PRESSURE VESSELS - ICR | 20 | 2022-05-18 | 2022-06-15 | 2022-10-05 | 2022-11-01 | 97
0 | GDVYF1215 | WEIGHING PROCEDURE FOR DECKS - ICR | 20 | 2022-05-18 | 2022-06-15 | 2022-11-21 | 2022-12-20 | 130
0 | GDVYF1120 | PIPING FLUSHING, TESTING AND DRYING PROCEDURE- ICR | 20 | 2022-05-18 | 2022-06-15 | 2022-09-27 | 2022-10-24 | 91
0 | GDVYF1185 | METHOD STATEMENT FOR COLD BENDING OF J-TUBE BENDS - ICR | 20 | 2022-05-18 | 2022-06-15 | 2022-09-30 | 2022-10-27 | 94
0 | GDVYF1245 | GROSS AIR LEAK TEST PROCEDURE - ICR | 20 | 2022-05-18 | 2022-06-15 | 2022-10-11 | 2022-11-07 | 101
0 | GDVYF1275 | SOW TERTIARY STEEL WORKS - IFI | 10 | 2022-06-13 | 2022-06-27 | 2022-12-22 | 2023-01-04 | 133
0 | GDVYF1040 | DISTORTION (FREESPAN) CORRECTION PROCEDURE - FINAL | 10 | 2022-06-15 | 2022-06-29 | 2022-12-08 | 2022-12-21 | 121
0 | GDVYF1055 | SURFACE PREPARATION AND PAINTING PROCEDURE - FINAL | 10 | 2022-06-22 | 2022-07-06 | 2022-12-08 | 2022-12-21 | 116
0 | GDVYF1205 | FABRICATION PROCEDURE FOR PRESSURE VESSELS- IFA | 10 | 2022-06-24 | 2022-07-13 | 2022-11-11 | 2022-11-24 | 97
0 | GDVYF1285 | SOW FOR FABRICATION OF GRATING AND GALVANIZATION -IFI | 10 | 2022-06-27 | 2022-07-14 | 2023-02-17 | 2023-03-02 | 164
0 | GDVYF1110 | HOT DIP GALVANIZING PROCEDURE- IFA | 10 | 2022-06-29 | 2022-07-18 | 2022-11-08 | 2022-11-21 | 91
0 | GDVYF1250 | GROSS AIR LEAK TEST PROCEDURE - IFA | 10 | 2022-06-29 | 2022-07-18 | 2023-01-26 | 2023-02-08 | 146
0 | GDVYF1190 | METHOD STATEMENT FOR COLD BENDING OF J-TUBE BENDS - IFA | 10 | 2022-06-29 | 2022-07-18 | 2022-11-11 | 2022-11-24 | 94
0 | GDVYF1125 | PIPING FLUSHING, TESTING AND DRYING PROCEDURE- IFA | 10 | 2022-06-29 | 2022-07-18 | 2022-11-08 | 2022-11-21 | 91
0 | GDVYF1095 | EQUIPMENT INSULATION PROCEDURE - HOT & COLD - ONSHORE - IFA | 10 | 2022-06-29 | 2022-07-18 | 2022-11-08 | 2022-11-21 | 91
0 | GDVYF1140 | PASSIVE FIRE PROOFING PROCEDURE - IFA | 10 | 2022-06-29 | 2022-07-18 | 2022-11-08 | 2022-11-21 | 91
0 | GDVYF1025 | PIPING FABRICATION AND ERECTION PROCEDURE - FINAL | 10 | 2022-06-29 | 2022-07-18 | 2022-12-08 | 2022-12-21 | 111
0 | GDVYF1070 | POST WELD HEAT TREATMENT (PWHT) PROCEDURE (PIPING) - ONSHORE - FINAL | 10 | 2022-06-29 | 2022-07-18 | 2022-12-08 | 2022-12-21 | 111
0 | GDVYF1220 | WEIGHING PROCEDURE FOR DECKS - IFA | 10 | 2022-06-29 | 2022-07-18 | 2023-01-04 | 2023-01-17 | 130
0 | GDVYF1150 | COLOR CODING SYSTEM FOR PIPES - IFI | 20 | 2022-06-15 | 2022-07-18 | 2022-11-08 | 2022-12-07 | 101
0 | GDVYF1155 | PIPING FLANGE MANAGEMENT PROCEDURE - IFI | 20 | 2022-06-22 | 2022-07-25 | 2023-04-11 | 2023-05-10 | 204
0 | GDVYF1195 | METHOD STATEMENT FOR COLD BENDING OF J-TUBE BENDS- FINAL | 10 | 2022-07-18 | 2022-08-01 | 2022-12-08 | 2022-12-21 | 101
0 | GDVYF1210 | FABRICATION PROCEDURE FOR PRESSURE VESSELS - FINAL | 10 | 2022-07-22 | 2022-08-05 | 2022-12-08 | 2022-12-21 | 97
0 | GDVYF1265 | SOW PIPING INSULAION - IFI | 20 | 2022-07-06 | 2022-08-08 | 2023-02-13 | 2023-03-10 | 153
0 | GDVYF1180 | PROCEDURE FOR PWHT OF STRUCTURAL WORKS AT SITE (FIELD JOINTS) - FINAL | 10 | 2022-07-27 | 2022-08-10 | 2022-12-08 | 2022-12-21 | 94
0 | GDVYF1115 | HOT DIP GALVANIZING PROCEDURE- FINAL | 10 | 2022-08-01 | 2022-08-15 | 2022-12-08 | 2022-12-21 | 91
0 | GDVYF1145 | PASSIVE FIRE PROOFING PROCEDURE - FINAL | 10 | 2022-08-01 | 2022-08-15 | 2022-12-08 | 2022-12-21 | 91
0 | GDVYF1130 | PIPING FLUSHING, TESTING AND DRYING PROCEDURE - FINAL | 10 | 2022-08-01 | 2022-08-15 | 2022-12-08 | 2022-12-21 | 91
0 | GDVYF1225 | WEIGHING PROCEDURE FOR DECKS - FINAL | 10 | 2022-08-01 | 2022-08-15 | 2023-02-01 | 2023-02-14 | 130
0 | GDVYF1255 | GROSS AIR LEAK TEST PROCEDURE - FINAL | 10 | 2022-08-01 | 2022-08-15 | 2023-02-23 | 2023-03-08 | 146
0 | GDVYF1100 | EQUIPMENT INSULATION PROCEDURE - HOT & COLD - ONSHORE - FINAL | 10 | 2022-08-05 | 2022-08-19 | 2022-12-08 | 2022-12-21 | 87
0 | GDVYF1160 | METHOD STATEMENT FOR RETESTING OF VALVES (VALVE SEAT / LEAK TESTING) - IFI | 20 | 2022-07-25 | 2022-08-22 | 2023-05-11 | 2023-06-07 | 204
0 | GDVYF1230 | LOAD OUT PROCEDURE FOR THE DECKS - ICR | 20 | 2022-08-01 | 2022-08-29 | 2023-02-01 | 2023-02-28 | 130
0 | GDVYF1165 | METHOD STATEMENT FOR PIPE INSULATION AT ONSHORE AND OFFSHORE - IFI | 20 | 2022-08-08 | 2022-09-05 | 2023-05-25 | 2023-06-21 | 204
0 | GDVYF1235 | LOAD OUT PROCEDURE FOR THE DECKS - IFA | 10 | 2022-09-12 | 2022-09-26 | 2023-03-15 | 2023-03-28 | 130
0 | GDVYF1240 | LOAD OUT PROCEDURE FOR THE DECKS - FINAL | 10 | 2022-10-10 | 2022-10-24 | 2023-04-12 | 2023-04-27 | 130
OFFSHORE DELIVERABLES |  |  | 594 | 2021-12-21 | 2024-04-30 | 2022-02-18 | 2024-07-19 | 55
0 | GDVOF1015 | PRE - ENGINEERING GEOTECHANICAL SURVEY AND PIPE SOIL INTERACTION SURVEY PROCEDURE - ICR | 20 | 2021-12-21 | 2022-01-19 | 2022-03-01 | 2022-03-28 | 49
0 | GDVOF1000 | PRE-ENGINEERING GEOPHYSICAL SURVEY PROCEDURE - ICR | 20 | 2021-12-21 | 2022-01-19 | 2022-02-18 | 2022-03-17 | 42
0 | GDVOF1035 | PRE-ENGINEERING JACKET FACE DIVING SURVEY PROCEDURE - ICR | 10 | 2022-01-19 | 2022-02-02 | 2022-03-31 | 2022-04-13 | 51
0 | GDVOF1020 | PRE - ENGINEERING GEOTECHANICAL SURVEY AND PIPE SOIL INTERACTION SURVEY PROCEDURE - IFA | 8 | 2022-02-02 | 2022-02-14 | 2022-04-12 | 2022-04-21 | 49
0 | GDVOF1065 | PRE-ENGINEERING ROV SURVEY PROCEDURE (JACKET FACE SURVEY, PLATFORM APPROACH & CROSSING) - ICR | 20 | 2022-01-19 | 2022-02-16 | 2022-04-01 | 2022-04-28 | 52
0 | GDVOF1005 | PRE-ENGINEERING GEOPHYSICAL SURVEY PROCEDURE - IFA | 15 | 2022-02-02 | 2022-02-23 | 2022-04-01 | 2022-04-21 | 42
0 | GDVOF1025 | PRE - ENGINEERING GEOTECHANICAL SURVEY AND PIPE SOIL INTERACTION SURVEY PROCEDURE - FINAL | 3 | 2022-02-21 | 2022-02-24 | 2022-04-29 | 2022-05-06 | 49
0 | GDVOF1040 | PRE-ENGINEERING JACKET FACE DIVING SURVEY PROCEDURE- IFA | 10 | 2022-02-16 | 2022-03-02 | 2022-04-28 | 2022-05-16 | 51
0 | GDVOF1070 | PRE-ENGINEERING ROV SURVEY PROCEDURE (JACKET FACE SURVEY, PLATFORM APPROACH & CROSSING) - IFA | 5 | 2022-02-24 | 2022-03-03 | 2022-05-12 | 2022-05-18 | 52
0 | GDVOF1010 | PRE-ENGINEERING GEOPHYSICAL SURVEY PROCEDURE - FINAL | 3 | 2022-03-02 | 2022-03-07 | 2022-04-29 | 2022-05-06 | 42
0 | GDVOF1715 | SCOPE OF WORK FOR TRANSPORTATION OF UMBILICALS FROM VENDOR - ICR | 25 | 2022-02-09 | 2022-03-16 | 2022-12-09 | 2023-01-12 | 209
0 | GDVOF1075 | PRE-ENGINEERING ROV SURVEY PROCEDURE (JACKET FACE SURVEY, PLATFORM APPROACH & CROSSING) - FINAL | 5 | 2022-03-10 | 2022-03-17 | 2022-05-26 | 2022-06-01 | 52
0 | GDVOF1045 | PRE-ENGINEERING JACKET FACE DIVING SURVEY PROCEDURE- FINAL | 5 | 2022-03-16 | 2022-03-23 | 2022-05-31 | 2022-06-06 | 51
0 | GDVOF1725 | SCOPE OF WORK FOR TRANSPORTATION OF UMBILICALS FROM VENDOR - IFC | 10 | 2022-03-30 | 2022-04-13 | 2023-02-22 | 2023-03-07 | 227
0 | GDVOF1085 | PRE-ENGINEERING GEOPHYSICAL SURVEY REPORT - IFI | 17 | 2022-04-04 | 2022-04-26 | 2022-05-31 | 2022-06-22 | 38
0 | GDVOF1080 | PRE - ENGINEERING GEOTECHANICAL SURVEY AND PIPE SOIL INTERACTION REPORT SURVEY REPORT - IFI | 17 | 2022-04-04 | 2022-04-26 | 2022-05-31 | 2022-06-22 | 38
0 | GDVOF1030 | GEOTECHNICAL FACTUAL REPORT - IFI | 18 | 2022-04-04 | 2022-04-27 | 2022-05-30 | 2022-06-22 | 37
0 | GDVOF1100 | PIPELINE BASELINE SURVEY PROCEDURE - ICR | 15 | 2022-04-28 | 2022-05-23 | 2022-07-05 | 2022-07-28 | 45
0 | GDVOF1090 | PRE-ENGINEERING ROV/CROSSING SURVEY REPORT - IFI | 20 | 2022-04-25 | 2022-05-26 | 2022-09-26 | 2022-10-21 | 104
0 | GDVOF1415 | NEW WHP-10 DECK INSTALLATION PROCEDURE - ICR | 20 | 2022-04-28 | 2022-05-30 | 2022-11-25 | 2022-12-26 | 145
0 | GDVOF1445 | DEMOLITION OF HD-03 EXISTING DECK AND NEW DECK INSTALLATION PROCEDURE - ICR | 20 | 2022-04-28 | 2022-05-30 | 2022-11-25 | 2022-12-26 | 145
0 | GDVOF1430 | NEW BHY-03 DECK INSTALLATION PROCEDURE - ICR | 20 | 2022-04-28 | 2022-05-30 | 2022-11-25 | 2022-12-26 | 145
0 | GDVOF1400 | J-TUBE AND ASSOCIATED CLAMPS INSTALLATION PROCEDURE - ICR | 20 | 2022-04-28 | 2022-05-30 | 2022-11-25 | 2022-12-26 | 145
0 | GDVOF1460 | NEW HD-T4 DECK INSTALLATION PROCEDURE - ICR | 20 | 2022-05-10 | 2022-06-06 | 2022-12-06 | 2023-01-02 | 145
0 | GDVOF1475 | PIPELINES FLOODING, GAUGING, CLEANING AND HYDROTESTING PROCEDURE - ICR | 20 | 2022-05-10 | 2022-06-06 | 2022-12-06 | 2023-01-02 | 145
0 | GDVOF1490 | UMBILICAL SHOREPULL, INSTALLATION & PULL IN THROUGH J-TUBE PROCEDURE - ICR | 20 | 2022-05-10 | 2022-06-06 | 2022-12-06 | 2023-01-02 | 145
0 | GDVOF1505 | CABLE SHOREPULL, INSTALLATION & PULL IN THROUGH J-TUBE PROCEDURE - ICR | 20 | 2022-05-10 | 2022-06-06 | 2022-12-06 | 2023-01-02 | 145
0 | GDVOF1645 | PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY PROCEDURE - ICR | 10 | 2022-05-31 | 2022-06-14 | 2022-10-27 | 2022-11-09 | 104
0 | GDVOF1105 | PIPELINE BASELINE SURVEY PROCEDURE - IFA | 10 | 2022-06-07 | 2022-06-20 | 2022-08-12 | 2022-08-25 | 45
0 | GDVOF1675 | SCOPE OF WORK TRENCHING & BACKFILLING - IRC | 15 | 2022-06-03 | 2022-06-23 | 2022-08-10 | 2022-08-30 | 45
0 | GDVOF1420 | NEW WHP-10 DECK INSTALLATION PROCEDURE - IFA | 10 | 2022-06-14 | 2022-06-27 | 2023-01-26 | 2023-02-08 | 157
0 | GDVOF1450 | DEMOLITION OF HD-03 EXISTING DECK AND NEW DECK INSTALLATION PROCEDURE - IFA | 10 | 2022-06-14 | 2022-06-27 | 2023-01-26 | 2023-02-08 | 157
0 | GDVOF1405 | J-TUBE AND ASSOCIATED CLAMPS INSTALLATION PROCEDURE - IFA | 10 | 2022-06-14 | 2022-06-27 | 2023-01-26 | 2023-02-08 | 157
0 | GDVOF1435 | NEW BHY-03 DECK INSTALLATION PROCEDURE - IFA | 10 | 2022-06-14 | 2022-06-27 | 2023-01-26 | 2023-02-08 | 157
0 | GDVOF1465 | NEW HD-T4 DECK INSTALLATION PROCEDURE - IFA | 10 | 2022-06-21 | 2022-07-04 | 2023-01-26 | 2023-02-08 | 152
0 | GDVOF1480 | PIPELINES FLOODING, GAUGING, CLEANING AND HYDROTESTING PROCEDURE - IFA | 10 | 2022-06-21 | 2022-07-04 | 2023-01-26 | 2023-02-08 | 152
0 | GDVOF1495 | UMBILICAL SHOREPULL, INSTALLATION & PULL IN THROUGH J-TUBE PROCEDURE - IFA | 10 | 2022-06-21 | 2022-07-04 | 2023-01-26 | 2023-02-08 | 152
0 | GDVOF1510 | CABLE SHOREPULL, INSTALLATION & PULL IN THROUGH J-TUBE PROCEDURE - IFA | 10 | 2022-06-21 | 2022-07-04 | 2023-01-17 | 2023-01-30 | 145
0 | GDVOF1655 | PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY PROCEDURE- IFA | 10 | 2022-06-28 | 2022-07-15 | 2022-11-24 | 2022-12-09 | 104
0 | GDVOF1695 | SCOPE OF WORK FOR ONSHORE WORKS & ASSISTANCE - IRC | 15 | 2022-06-24 | 2022-07-19 | 2022-08-31 | 2022-09-20 | 45
0 | GDVOF1185 | ANCHOR HANDLING AND MOORING PROCEDURE FOR WORK BOATS - ICR | 20 | 2022-06-21 | 2022-07-21 | 2022-09-30 | 2022-10-27 | 70
0 | GDVOF1155 | PIPELINE/CABLE/UMBILICAL AS LAID SURVEY PROCEDURE - ICR | 20 | 2022-06-21 | 2022-07-21 | 2022-12-20 | 2023-01-16 | 125
0 | GDVOF1170 | ANCHOR HANDLING PROCEDURE FOR GRAVITY ANCHORS BY HAMMER HEAD CRANE VESSEL - ICR | 20 | 2022-06-21 | 2022-07-21 | 2022-09-30 | 2022-10-27 | 70
0 | GDVOF1140 | PIPELINE/CABLE/UMBILICAL AS-BUILT SURVEY PROCEDURE - ICR | 20 | 2022-06-21 | 2022-07-21 | 2022-09-30 | 2022-10-27 | 70
0 | GDVOF1110 | PIPELINE BASELINE SURVEY PROCEDURE - FINAL | 10 | 2022-07-05 | 2022-07-21 | 2022-10-14 | 2022-10-27 | 70
0 | GDVOF1245 | PIPELINE INFILL MATERIAL FIELD JOINT COATING PROCEDURE - ICR | 10 | 2022-07-14 | 2022-07-27 | 2022-10-20 | 2022-11-02 | 70
0 | GDVOF1230 | FREE SPANS CORRECTION PROCEURE - ICR | 10 | 2022-07-14 | 2022-07-27 | 2022-10-20 | 2022-11-02 | 70
0 | GDVOF1265 | SLEEPERS INSTALLATION PROCEDURES - ICR | 15 | 2022-07-04 | 2022-07-27 | 2022-10-13 | 2022-11-02 | 70
0 | GDVOF1425 | NEW WHP-10 DECK INSTALLATION PROCEDURE - FINAL | 10 | 2022-07-15 | 2022-07-28 | 2023-02-23 | 2023-03-08 | 157
0 | GDVOF1455 | DEMOLITION OF HD-03 EXISTING DECK AND NEW DECK INSTALLATION PROCEDURE - FINAL | 10 | 2022-07-15 | 2022-07-28 | 2023-02-23 | 2023-03-08 | 157
0 | GDVOF1440 | NEW BHY-03 DECK INSTALLATION PROCEDURE - FINAL | 10 | 2022-07-15 | 2022-07-28 | 2023-02-23 | 2023-03-08 | 157
0 | GDVOF1410 | J-TUBE AND ASSOCIATED CLAMPS INSTALLATION PROCEDURE - FINAL | 10 | 2022-07-15 | 2022-07-28 | 2023-02-23 | 2023-03-08 | 157
0 | GDVOF1685 | SCOPE OF WORK TRENCHING & BACKFILLING - IFC | 15 | 2022-07-13 | 2022-08-02 | 2022-10-20 | 2022-11-09 | 71
0 | GDVOF1625 | TRENCHING & BACKFILLING PROCEDURE - ICR | 15 | 2022-07-14 | 2022-08-03 | 2022-10-20 | 2022-11-09 | 70
0 | GDVOF1470 | NEW HD-T4 DECK INSTALLATION PROCEDURE - FINAL | 10 | 2022-07-22 | 2022-08-04 | 2023-02-23 | 2023-03-08 | 152
0 | GDVOF1485 | PIPELINES FLOODING, GAUGING, CLEANING AND HYDROTESTING PROCEDURE - FINAL | 10 | 2022-07-22 | 2022-08-04 | 2023-02-23 | 2023-03-08 | 152
0 | GDVOF1500 | UMBILICAL SHOREPULL, INSTALLATION & PULL IN THROUGH J-TUBE PROCEDURE - FINAL | 10 | 2022-07-22 | 2022-08-04 | 2023-02-23 | 2023-03-08 | 152
0 | GDVOF1665 | PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY PROCEDURE- FINAL | 10 | 2022-07-29 | 2022-08-12 | 2022-12-26 | 2023-01-06 | 104
0 | GDVOF1515 | CABLE SHOREPULL, INSTALLATION & PULL IN THROUGH J-TUBE PROCEDURE - FINAL | 20 | 2022-07-19 | 2022-08-15 | 2023-02-09 | 2023-03-08 | 145
0 | GDVOF1270 | SLEEPERS INSTALLATION PROCEDURES - IFA | 15 | 2022-07-28 | 2022-08-17 | 2022-11-10 | 2022-11-30 | 75
0 | GDVOF1160 | PIPELINE/CABLE/UMBILICAL AS LAID SURVEY PROCEDURE- IFA | 10 | 2022-08-05 | 2022-08-18 | 2023-01-31 | 2023-02-13 | 125
0 | GDVOF1175 | ANCHOR HANDLING PROCEDURE FOR GRAVITY ANCHORS BY HAMMER HEAD CRANE VESSEL - IFA | 10 | 2022-08-05 | 2022-08-18 | 2023-01-31 | 2023-02-13 | 125
0 | GDVOF1190 | ANCHOR HANDLING AND MOORING PROCEDURE FOR WORK BOATS - IFA | 10 | 2022-08-05 | 2022-08-18 | 2023-01-26 | 2023-02-08 | 122
0 | GDVOF1145 | PIPELINE/CABLE/UMBILICAL AS-BUILT SURVEY PROCEDURE - IFA | 10 | 2022-08-05 | 2022-08-18 | 2023-01-31 | 2023-02-13 | 125
0 | GDVOF1705 | SCOPE OF WORK FOR ONSHORE WORKS & ASSISTANCE E - IFC | 15 | 2022-08-03 | 2022-08-23 | 2022-12-05 | 2022-12-23 | 86
0 | GDVOF1235 | FREE SPANS CORRECTION PROCEURE - IFA | 10 | 2022-08-11 | 2022-08-24 | 2023-02-27 | 2023-03-10 | 140
0 | GDVOF1250 | PIPELINE INFILL MATERIAL FIELD JOINT COATING PROCEDURE - IFA | 10 | 2022-08-11 | 2022-08-24 | 2022-11-17 | 2022-11-30 | 70
0 | GDVOF1280 | PIPELINE ANTI-CORROSION FIELD JOINT COATING PROCEDURE - ICR | 20 | 2022-07-28 | 2022-08-24 | 2023-01-03 | 2023-01-30 | 111
0 | GDVOF1200 | ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES- ICR | 20 | 2022-07-28 | 2022-08-24 | 2022-12-16 | 2023-01-12 | 99
0 | GDVOF1520 | METHOD STATEMENT FOR CIVIL WORKS FOR SHOREPULL - ICR | 20 | 2022-07-28 | 2022-08-24 | 2022-11-03 | 2022-11-30 | 70
0 | GDVOF1535 | OFFSHORE HOOK-UP PROCEDURE - ICR | 20 | 2022-07-28 | 2022-08-24 | 2022-11-03 | 2022-11-30 | 70
0 | GDVOF1550 | PIPELINES CALIPER PIGGING PROCEDURE - ICR | 20 | 2022-07-29 | 2022-08-25 | 2022-11-04 | 2022-12-05 | 70
0 | GDVOF1355 | ZIRKU ISLAND PIPELINES SHORE PULL PROCEDURE- ICR | 20 | 2022-08-03 | 2022-08-30 | 2022-12-27 | 2023-01-23 | 102
0 | GDVOF1050 | BARGE POSITING AND INSTALLATION SURVEY PROCEDURE - ICR | 5 | 2022-08-24 | 2022-08-30 | 2022-11-30 | 2022-12-08 | 70
0 | GDVOF1370 | RISER (STALK-IN) INSTALLATION PROCEDURE- ICR | 20 | 2022-08-03 | 2022-08-30 | 2022-12-27 | 2023-01-23 | 102
0 | GDVOF1310 | UMBILICALS INSTALLATION PROCEURE - ICR | 15 | 2022-08-10 | 2022-08-30 | 2022-12-29 | 2023-01-18 | 99
0 | GDVOF1385 | MID LINE SURFCAE TIE IN(s) INSTALLATION PROCEDURE - ICR | 20 | 2022-08-03 | 2022-08-30 | 2022-12-27 | 2023-01-23 | 102
0 | GDVOF1340 | ARZANAH ISLAND PIPELINES SHORE PULL PROCEDURE - ICR | 20 | 2022-08-03 | 2022-08-30 | 2022-12-27 | 2023-01-23 | 102
0 | GDVOF1295 | PIPELINES INSTALLATION MANUAL - ICR | 20 | 2022-08-03 | 2022-08-30 | 2022-12-22 | 2023-01-18 | 99
0 | GDVOF1215 | ANCHOR HANDLING AND MOORING PROCEDURE FOR JACK UP BARGES - ICR | 20 | 2022-08-03 | 2022-08-30 | 2022-12-22 | 2023-01-18 | 99
0 | GDVOF1325 | FIBER OPTIC CABLES INSTALLATION PROCEDURE - ICR | 20 | 2022-08-03 | 2022-08-30 | 2022-12-27 | 2023-01-23 | 102
0 | GDVOF1565 | PIPELINES INTLIGANT PIGGING PROCEDURE - ICR | 10 | 2022-08-17 | 2022-08-30 | 2022-11-23 | 2022-12-08 | 70
0 | GDVOF1580 | PIPELINES DEWATERING, DRYING AND NITROGEN PURGING PROCEDURE - ICR | 15 | 2022-08-10 | 2022-08-30 | 2022-12-29 | 2023-01-18 | 99
0 | GDVOF1630 | TRENCHING & BACKFILLING PROCEDURE - IFA | 10 | 2022-08-18 | 2022-08-31 | 2022-11-24 | 2022-12-09 | 70
0 | GDVOF1595 | CABLE TRANSPOOLIING PROCEDURE - ICR | 20 | 2022-08-10 | 2022-09-06 | 2023-01-17 | 2023-02-13 | 112
0 | GDVOF1165 | PIPELINE/CABLE/UMBILICAL AS LAID SURVEY PROCEDURE - FINAL | 10 | 2022-08-30 | 2022-09-12 | 2023-02-23 | 2023-03-08 | 125
0 | GDVOF1180 | ANCHOR HANDLING PROCEDURE FOR GRAVITY ANCHORS BY HAMMER HEAD CRANE VESSEL - FINAL | 10 | 2022-08-30 | 2022-09-12 | 2023-02-23 | 2023-03-08 | 125
0 | GDVOF1150 | PIPELINE/CABLE/UMBILICAL AS-BUILT SURVEY PROCEDURE - FINAL | 10 | 2022-08-30 | 2022-09-12 | 2023-02-23 | 2023-03-08 | 125
0 | GDVOF1360 | ZIRKU ISLAND PIPELINES SHORE PULL PROCEDURE- IFA | 10 | 2022-08-31 | 2022-09-13 | 2023-02-09 | 2023-02-22 | 114
0 | GDVOF1285 | PIPELINE ANTI-CORROSION FIELD JOINT COATING PROCEDURE - IFA | 10 | 2022-09-01 | 2022-09-14 | 2023-02-07 | 2023-02-20 | 111
0 | GDVOF1195 | ANCHOR HANDLING AND MOORING PROCEDURE FOR WORK BOATS - FINAL | 10 | 2022-09-02 | 2022-09-15 | 2023-02-23 | 2023-03-08 | 122
0 | GDVOF1055 | BARGE POSITING AND INSTALLATION SURVEY PROCEDURE - IFA | 5 | 2022-09-14 | 2022-09-20 | 2022-12-23 | 2022-12-29 | 70
0 | GDVOF1205 | ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES- IFA | 10 | 2022-09-08 | 2022-09-21 | 2023-01-31 | 2023-02-13 | 101
0 | GDVOF1240 | FREE SPANS CORRECTION PROCEURE - FINAL | 10 | 2022-09-08 | 2022-09-21 | 2023-03-27 | 2023-04-07 | 140
0 | GDVOF1260 | PIPELINE INFILL MATERIAL FIELD JOINT COATING PROCEDURE - FINAL | 10 | 2022-09-08 | 2022-09-21 | 2023-02-23 | 2023-03-08 | 118
0 | GDVOF1525 | METHOD STATEMENT FOR CIVIL WORKS FOR SHOREPULL - IFA | 10 | 2022-09-08 | 2022-09-21 | 2023-01-26 | 2023-02-08 | 98
0 | GDVOF1540 | OFFSHORE HOOK-UP PROCEDURE - IFA | 10 | 2022-09-08 | 2022-09-21 | 2023-01-26 | 2023-02-08 | 98
0 | GDVOF1255 | PIPELINE INFILL MATERIAL FIELD JOINT COATING PROCEDURE - IFC | 10 | 2022-09-08 | 2022-09-21 | 2023-04-26 | 2023-05-09 | 160
0 | GDVOF1555 | PIPELINES CALIPER PIGGING PROCEDURE - IFA | 10 | 2022-09-09 | 2022-09-22 | 2023-01-26 | 2023-02-08 | 97
0 | GDVOF1375 | RISER (STALK-IN) INSTALLATION PROCEDURE - IFA | 10 | 2022-09-14 | 2022-09-27 | 2023-02-07 | 2023-02-20 | 102
0 | GDVOF1345 | ARZANAH ISLAND PIPELINES SHORE PULL PROCEDURE - IFA | 10 | 2022-09-14 | 2022-09-27 | 2023-03-14 | 2023-03-27 | 127
0 | GDVOF1315 | UMBILICALS INSTALLATION PROCEURE - IFA | 10 | 2022-09-14 | 2022-09-27 | 2023-02-02 | 2023-02-15 | 99
0 | GDVOF1390 | MID LINE SURFCAE TIE IN(s) INSTALLATION PROCEDURE - IFA | 10 | 2022-09-14 | 2022-09-27 | 2023-02-07 | 2023-02-20 | 102
0 | GDVOF1300 | PIPELINES INSTALLATION MANUAL - IFA | 10 | 2022-09-14 | 2022-09-27 | 2023-02-03 | 2023-02-16 | 100
0 | GDVOF1220 | ANCHOR HANDLING AND MOORING PROCEDURE FOR JACK UP BARGES- IFA | 10 | 2022-09-14 | 2022-09-27 | 2023-02-07 | 2023-02-20 | 102
0 | GDVOF1330 | FIBER OPTIC CABLES INSTALLATION PROCEDURE - IFA | 10 | 2022-09-14 | 2022-09-27 | 2023-02-07 | 2023-02-20 | 102
0 | GDVOF1365 | ZIRKU ISLAND PIPELINES SHORE PULL PROCEDURE - FINAL | 10 | 2022-09-14 | 2022-09-27 | 2023-02-23 | 2023-03-08 | 114
0 | GDVOF1570 | PIPELINES INTLIGANT PIGGING PROCEDURE - IFA | 10 | 2022-09-14 | 2022-09-27 | 2023-02-02 | 2023-02-15 | 99
0 | GDVOF1585 | PIPELINES DEWATERING, DRYING AND NITROGEN PURGING PROCEDURE - IFA | 10 | 2022-09-14 | 2022-09-27 | 2023-02-02 | 2023-02-15 | 99
0 | GDVOF1610 | UMBILICAL TRANSPOOLIING PROCEDURE - ICR | 20 | 2022-08-31 | 2022-09-27 | 2023-01-24 | 2023-02-20 | 102
0 | GDVOF1275 | SLEEPER INSTALLATION PROCEDURES - FINAL | 20 | 2022-09-01 | 2022-09-28 | 2023-03-13 | 2023-04-07 | 135
0 | GDVOF1635 | TRENCHING & BACKFILLING PROCEDURE - FINAL | 10 | 2022-09-15 | 2022-09-28 | 2022-12-26 | 2023-01-06 | 70
0 | GDVOF1290 | PIPELINE ANTI-CORROSION FIELD JOINT COATING PROCEDURE - FINAL | 10 | 2022-09-19 | 2022-09-30 | 2023-02-23 | 2023-03-08 | 111
0 | GDVOF1600 | CABLE TRANSPOOLIING PROCEDURE - IFA | 10 | 2022-09-21 | 2022-10-04 | 2023-06-16 | 2023-07-04 | 188
0 | GDVOF1060 | BARGE POSITING AND INSTALLATION SURVEY PROCEDURE - FINAL | 5 | 2022-10-05 | 2022-10-11 | 2023-03-02 | 2023-03-08 | 104
0 | GDVOF1380 | RISER (STALK-IN) INSTALLATION PROCEDURE - FINAL | 5 | 2022-10-07 | 2022-10-13 | 2023-03-02 | 2023-03-08 | 102
0 | GDVOF1395 | MID LINE SURFCAE TIE IN(s) INSTALLATION PROCEDURE - FINAL | 5 | 2022-10-07 | 2022-10-13 | 2023-03-02 | 2023-03-08 | 102
0 | GDVOF1225 | ANCHOR HANDLING AND MOORING PROCEDURE FOR JACK UP BARGES - FINAL | 5 | 2022-10-07 | 2022-10-13 | 2023-03-02 | 2023-03-08 | 102
0 | GDVOF1335 | FIBER OPTIC CABLES INSTALLATION PROCEDURE - FINAL | 5 | 2022-10-07 | 2022-10-13 | 2023-03-02 | 2023-03-08 | 102
0 | GDVOF1210 | ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES- FINAL | 10 | 2022-10-03 | 2022-10-14 | 2023-02-23 | 2023-03-08 | 101
0 | GDVOF1305 | PIPELINES INSTALLATION MANUAL - FINAL | 4 | 2022-10-12 | 2022-10-17 | 2023-03-03 | 2023-03-08 | 100
0 | GDVOF1320 | UMBILICALS INSTALLATION PROCEURE - FINAL | 5 | 2022-10-12 | 2022-10-18 | 2023-03-02 | 2023-03-08 | 99
0 | GDVOF1575 | PIPELINES INTLIGANT PIGGING PROCEDURE - FINAL | 5 | 2022-10-12 | 2022-10-18 | 2023-03-02 | 2023-03-08 | 99
0 | GDVOF1590 | PIPELINES DEWATERING, DRYING AND NITROGEN PURGING PROCEDURE - FINAL | 5 | 2022-10-12 | 2022-10-18 | 2023-03-02 | 2023-03-08 | 99
0 | GDVOF1530 | METHOD STATEMENT FOR CIVIL WORKS FOR SHOREPULL - FINAL | 10 | 2022-10-06 | 2022-10-19 | 2023-02-23 | 2023-03-08 | 98
0 | GDVOF1545 | OFFSHORE HOOK-UP PROCEDURE - FINAL | 10 | 2022-10-06 | 2022-10-19 | 2023-02-23 | 2023-03-08 | 98
0 | GDVOF1560 | PIPELINES CALIPER PIGGING PROCEDURE - FINAL | 10 | 2022-10-07 | 2022-10-20 | 2023-02-23 | 2023-03-08 | 97
0 | GDVOF1615 | UMBILICAL TRANSPOOLIING PROCEDURE - IFA | 10 | 2022-10-12 | 2022-10-25 | 2023-03-07 | 2023-03-20 | 102
0 | GDVOF1605 | CABLE TRANSPOOLIING PROCEDURE - FINAL | 10 | 2022-10-19 | 2022-11-01 | 2023-07-20 | 2023-08-02 | 188
0 | GDVOF1350 | ARZANAH ISLAND PIPELINES SHORE PULL PROCEDURE- FINAL | 10 | 2022-10-26 | 2022-11-08 | 2023-04-11 | 2023-04-26 | 117
0 | GDVOF1620 | UMBILICAL TRANSPOOLIING PROCEDURE - FINAL | 10 | 2022-11-09 | 2022-11-22 | 2023-04-04 | 2023-04-17 | 102
0 | GDVOF1095 | PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY REPORT - IFI | 10 | 2022-12-05 | 2022-12-16 | 2023-03-15 | 2023-03-28 | 72
0 | GDVOF1120 | PIPELINE BASELINE SURVEY REPORT - ICR | 20 | 2024-01-04 | 2024-01-31 | 2024-03-22 | 2024-04-23 | 55
0 | GDVOF1125 | PIPELINE BASELINE SURVEY REPORT - IFA | 10 | 2024-02-16 | 2024-02-29 | 2024-05-08 | 2024-05-21 | 55
0 | GDVOF1130 | PIPELINE BASELINE SURVEY REPORT - FINAL | 10 | 2024-03-15 | 2024-03-28 | 2024-06-05 | 2024-06-21 | 55
0 | GDVOF1135 | PIPELINE/CABLE/UMBILICAL AS-BUILT SURVEY REPORT - IFI | 20 | 2024-03-29 | 2024-04-30 | 2024-06-24 | 2024-07-19 | 55
0 | GDVOF1115 | PIPELINE/CABLE/UMBILICAL AS LAID SURVEY REPORT - IFI | 15 | 2024-04-05 | 2024-04-30 | 2024-07-01 | 2024-07-19 | 55
PRE-COMM. / COMMISSIONING |  |  | 225 | 2022-05-18 | 2023-04-05 | 2022-10-11 | 2023-11-16 | 155
0 | GDVCG1000 | COMMISSIONING DELIVERABLE REGISTER- ICR | 20 | 2022-05-18 | 2022-06-15 | 2022-10-11 | 2022-11-07 | 101
0 | GDVCG1015 | PRECOMMISSIONING AND COMMISSIONING PROCEDURE- ICR | 20 | 2022-05-25 | 2022-06-22 | 2022-10-18 | 2022-11-14 | 101
0 | GDVCG1030 | SYSTEM / SUBSYSTEM LIST ICR | 20 | 2022-06-08 | 2022-07-06 | 2022-11-01 | 2022-11-28 | 101
0 | GDVCG1120 | CO-CONSOLE PROCEDURE- ICR | 20 | 2022-06-15 | 2022-07-18 | 2022-11-08 | 2022-12-07 | 101
0 | GDVCG1045 | PERMIT TO WORK (PTW) PROCEDURE- ICR | 20 | 2022-06-22 | 2022-07-25 | 2022-11-15 | 2022-12-14 | 101
0 | GDVCG1075 | LIST OF OPERATIONAL TEST PROCEDURES- ICR | 20 | 2022-06-22 | 2022-07-25 | 2022-11-15 | 2022-12-14 | 101
0 | GDVCG1090 | PUNCH LIST PROCEDURE- ICR | 20 | 2022-06-22 | 2022-07-25 | 2022-11-15 | 2022-12-14 | 101
0 | GDVCG1200 | METHOD STATEMENT FOR INSTRUMENT LOOP CHECKS & FUNCTION TESTS RELATED TO DCS, ESD AND F&G SYSTEMS - ICR | 20 | 2022-06-22 | 2022-07-25 | 2022-11-23 | 2022-12-22 | 107
0 | GDVCG1155 | COMMISSIONING EXECUTION PLAN - ICR | 20 | 2022-06-22 | 2022-07-25 | 2022-11-15 | 2022-12-14 | 101
0 | GDVCG1060 | COMMISSIONING PERMIT TO WORK (PTW) PROCEDURE- ICR | 20 | 2022-06-22 | 2022-07-25 | 2022-11-15 | 2022-12-14 | 101
0 | GDVCG1170 | N2-HE LEAK TEST PROCEDURE - ICR | 20 | 2022-06-22 | 2022-07-25 | 2022-11-15 | 2022-12-14 | 101
0 | GDVCG1105 | PRE-COMMISSIONING / COMMISSIONING TEST RECORDS AND RESPONSIBILITY MATRIX- ICR | 20 | 2022-06-22 | 2022-07-25 | 2022-11-15 | 2022-12-14 | 101
0 | GDVCG1135 | FIRST FILL INVENTORY, CONSUMPTION AND TOP UP SCHEDULE (INCLUDING CHEMICALS, HYDRAULIC OIL) - ICR | 20 | 2022-06-22 | 2022-07-25 | 2022-11-15 | 2022-12-14 | 101
0 | GDVCG1005 | COMMISSIONING DELIVERABLE REGISTER- IFA | 20 | 2022-06-29 | 2022-08-01 | 2022-12-29 | 2023-01-25 | 126
0 | GDVCG1020 | PRECOMMISSIONING AND COMMISSIONING PROCEDURE - IFA | 20 | 2022-07-06 | 2022-08-08 | 2022-12-29 | 2023-01-25 | 121
0 | GDVCG1035 | SYSTEM / SUBSYSTEM LIST- IFA | 20 | 2022-07-25 | 2022-08-22 | 2023-03-08 | 2023-04-04 | 160
0 | GDVCG1125 | CO-CONSOLE PROCEDURE- IFA | 20 | 2022-08-01 | 2022-08-29 | 2022-12-29 | 2023-01-25 | 106
0 | GDVCG1205 | METHOD STATEMENT FOR INSTRUMENT LOOP CHECKS & FUNCTION TESTS RELATED TO DCS, ESD AND F&G SYSTEMS - IFA | 20 | 2022-08-03 | 2022-08-31 | 2023-01-03 | 2023-01-30 | 107
0 | GDVCG1050 | PERMIT TO WORK (PTW) PROCEDURE- IFA | 20 | 2022-08-08 | 2022-09-05 | 2022-12-29 | 2023-01-25 | 101
0 | GDVCG1080 | LIST OF OPERATIONAL TEST PROCEDURES- IFA | 20 | 2022-08-08 | 2022-09-05 | 2022-12-29 | 2023-01-25 | 101
0 | GDVCG1095 | PUNCH LIST PROCEDURE- IFA | 20 | 2022-08-08 | 2022-09-05 | 2023-03-22 | 2023-04-18 | 160
0 | GDVCG1065 | COMMISSIONING PERMIT TO WORK (PTW) PROCEDURE- IFA | 20 | 2022-08-08 | 2022-09-05 | 2022-12-29 | 2023-01-25 | 101
0 | GDVCG1160 | COMMISSIONING EXECUTION PLAN - IFA | 20 | 2022-08-08 | 2022-09-05 | 2022-12-29 | 2023-01-25 | 101
0 | GDVCG1110 | PRE-COMMISSIONING / COMMISSIONING TEST RECORDS AND RESPONSIBILITY MATRIX - IFA | 20 | 2022-08-08 | 2022-09-05 | 2022-12-29 | 2023-01-25 | 101
0 | GDVCG1175 | N2-HE LEAK TEST PROCEDURE - IFA | 20 | 2022-08-08 | 2022-09-05 | 2022-12-29 | 2023-01-25 | 101
0 | GDVCG1140 | FIRST FILL INVENTORY, CONSUMPTION AND TOP UP SCHEDULE (INCLUDING CHEMICALS, HYDRAULIC OIL) - IFA | 20 | 2022-08-08 | 2022-09-05 | 2023-01-03 | 2023-01-30 | 104
0 | GDVCG1150 | VENDOR MOBILIZATION PLAN - IFI | 30 | 2022-07-25 | 2022-09-05 | 2023-01-26 | 2023-03-08 | 131
0 | GDVCG1010 | COMMISSIONING DELIVERABLE REGISTER- FINAL | 20 | 2022-08-15 | 2022-09-12 | 2023-02-09 | 2023-03-08 | 126
0 | GDVCG1025 | PRECOMMISSIONING AND COMMISSIONING PROCEDURE - FINAL | 20 | 2022-08-22 | 2022-09-19 | 2023-02-09 | 2023-03-08 | 121
0 | GDVCG1040 | SYSTEM / SUBSYSTEM LIST- FINAL | 20 | 2022-09-05 | 2022-10-03 | 2023-04-19 | 2023-05-18 | 160
0 | GDVCG1100 | PUNCH LIST PROCEDURE- FINAL | 20 | 2022-09-05 | 2022-10-03 | 2023-04-19 | 2023-05-18 | 160
0 | GDVCG1130 | CO-CONSOLE PROCEDURE- FINAL | 20 | 2022-09-12 | 2022-10-10 | 2023-02-09 | 2023-03-08 | 106
0 | GDVCG1145 | FIRST FILL INVENTORY, CONSUMPTION AND TOP UP SCHEDULE (INCLUDING CHEMICALS, HYDRAULIC OIL) - FINAL | 20 | 2022-09-14 | 2022-10-12 | 2023-02-09 | 2023-03-08 | 104
0 | GDVCG1055 | PERMIT TO WORK (PTW) PROCEDURE - FINAL | 20 | 2022-09-19 | 2022-10-17 | 2023-02-09 | 2023-03-08 | 101
0 | GDVCG1085 | LIST OF OPERATIONAL TEST PROCEDURES - FINAL | 20 | 2022-09-19 | 2022-10-17 | 2023-02-09 | 2023-03-08 | 101
0 | GDVCG1210 | METHOD STATEMENT FOR INSTRUMENT LOOP CHECKS & FUNCTION TESTS RELATED TO DCS, ESD AND F&G SYSTEMS - FINAL | 20 | 2022-09-19 | 2022-10-17 | 2023-02-09 | 2023-03-08 | 101
0 | GDVCG1165 | COMMISSIONING EXECUTION PLAN - FINAL | 20 | 2022-09-19 | 2022-10-17 | 2023-02-09 | 2023-03-08 | 101
0 | GDVCG1070 | COMMISSIONING PERMIT TO WORK (PTW) PROCEDURE- FINAL | 20 | 2022-09-19 | 2022-10-17 | 2023-02-09 | 2023-03-08 | 101
0 | GDVCG1180 | N2-HE LEAK TEST PROCEDURE - FINAL | 20 | 2022-09-19 | 2022-10-17 | 2023-02-09 | 2023-03-08 | 101
0 | GDVCG1235 | LIST OF SPECIAL TOOLS AND CONSUMABLES- ICR | 20 | 2022-09-19 | 2022-10-17 | 2023-02-13 | 2023-03-10 | 103
0 | GDVCG1115 | PRE-COMMISSIONING / COMMISSIONING TEST RECORDS AND RESPONSIBILITY MATRIX - FINAL | 20 | 2022-09-19 | 2022-10-17 | 2023-02-09 | 2023-03-08 | 101
0 | GDVCG1250 | LIST OF COMMISSIONING SPARE PARTS - ICR | 20 | 2022-10-17 | 2022-11-14 | 2023-05-26 | 2023-06-22 | 155
0 | GDVCG1215 | SYSTEM OPERATION TEST PROCEDURES - ICR | 20 | 2022-10-17 | 2022-11-14 | 2023-06-09 | 2023-07-11 | 165
0 | GDVCG1220 | PROJECT PRESERVATION PROCEDURE - IFI | 20 | 2022-10-17 | 2022-11-14 | 2023-04-10 | 2023-05-09 | 123
0 | GDVCG1240 | LIST OF SPECIAL TOOLS AND CONSUMABLES- IFA | 20 | 2022-10-31 | 2022-11-28 | 2023-03-27 | 2023-04-25 | 103
0 | GDVCG1185 | HANDOVER PROCEDURE - ICR | 20 | 2022-10-31 | 2022-11-28 | 2023-06-23 | 2023-07-26 | 165
0 | GDVCG1265 | PERFORMANCE TEST - ICR | 20 | 2022-11-14 | 2022-12-14 | 2023-06-23 | 2023-07-26 | 155
0 | GDVCG1255 | LIST OF COMMISSIONING SPARE PARTS - IFA | 20 | 2022-11-28 | 2022-12-28 | 2023-08-10 | 2023-09-06 | 175
0 | GDVCG1225 | SYSTEM OPERATION TEST PROCEDURES - IFA | 20 | 2022-11-28 | 2022-12-28 | 2023-08-10 | 2023-09-06 | 175
0 | GDVCG1190 | HANDOVER PROCEDURE - IFA | 20 | 2022-12-14 | 2023-01-11 | 2023-08-10 | 2023-09-06 | 165
0 | GDVCG1280 | START-UP PROCEDURE- ICR | 20 | 2022-12-14 | 2023-01-11 | 2023-07-27 | 2023-08-23 | 155
0 | GDVCG1245 | LIST OF SPECIAL TOOLS AND CONSUMABLES- FINAL | 20 | 2022-12-14 | 2023-01-11 | 2023-05-10 | 2023-06-06 | 103
0 | GDVCG1270 | PERFORMANCE TEST - IFA | 20 | 2022-12-28 | 2023-01-25 | 2023-09-07 | 2023-10-05 | 175
0 | GDVCG1230 | SYSTEM OPERATION TEST PROCEDURES - FINAL | 20 | 2023-01-11 | 2023-02-08 | 2023-09-21 | 2023-10-19 | 175
0 | GDVCG1285 | START-UP PROCEDURE- IFA | 20 | 2023-01-25 | 2023-02-22 | 2023-09-07 | 2023-10-05 | 155
0 | GDVCG1260 | LIST OF COMMISSIONING SPARE PARTS FINAL | 20 | 2023-01-25 | 2023-02-22 | 2023-09-21 | 2023-10-19 | 165
0 | GDVCG1195 | HANDOVER PROCEDURE- FINAL | 20 | 2023-01-25 | 2023-02-22 | 2023-09-21 | 2023-10-19 | 165
0 | GDVCG1275 | PERFORMANCE TEST - FINAL | 20 | 2023-02-08 | 2023-03-08 | 2023-10-20 | 2023-11-16 | 175
0 | GDVCG1290 | START-UP PROCEDURE FINAL | 20 | 2023-03-08 | 2023-04-05 | 2023-10-20 | 2023-11-16 | 155
ASSISTANCE TO COMPANY PMT |  |  | 572 | 2021-12-19 | 2024-03-21 | 2022-06-21 | 2024-05-20 | 39
PROVISION FOR COMPANY |  |  | 572 | 2021-12-19 | 2024-03-21 | 2022-06-21 | 2024-05-20 | 39
0 | GDVCG1320 | CONTRACTOR PROVISION OF ASSISSTANCE TO COMPANY AT CONTRACTOR'S HOME OFFICES. | 430 | 2021-12-19 | 2023-08-31 | 2022-06-21 | 2024-03-04 | 129
0 | GDVCG1330 | CONTRACTOR PROVISION OF ASSISSTANCE TO COMPANY AT OFFSHORE/MARINE SPREADS | 270 | 2023-02-24 | 2024-03-21 | 2023-04-20 | 2024-05-20 | 39
ENGINEERING |  |  | 696 | 2021-12-19 | 2023-11-14 | 2021-12-19 | 2024-03-04 | 111
OFFSHORE |  |  | 696 | 2021-12-19 | 2023-11-14 | 2021-12-19 | 2024-03-04 | 111
DETAILED ENGINEERING |  |  | 696 | 2021-12-19 | 2023-11-14 | 2021-12-19 | 2024-02-02 | 80
COMMON |  |  | 483 | 2021-12-19 | 2023-11-14 | 2021-12-19 | 2024-02-02 | 56
GENERAL |  |  | 398 | 2021-12-19 | 2023-07-14 | 2021-12-19 | 2023-10-04 | 56
DOCUMENTS |  |  | 89 | 2021-12-19 | 2022-04-20 | 2021-12-19 | 2022-07-28 | 65
0 | EDCDGE1000 | ENGINEERING DELIVERABLE REGISTER - ICR | 25 | 2021-12-19 | 2022-01-21 | 2021-12-19 | 2022-01-21 | 0
0 | EDCDGE1065 | PROJECT PROCEDURE FOR TAG NUMBERING PACKAGE-A - ICR | 20 | 2022-01-04 | 2022-02-01 | 2022-04-08 | 2022-05-10 | 68
0 | EDCDGE1010 | ENGINEERING EXECUTION PLAN - ICR | 30 | 2021-12-23 | 2022-02-04 | 2022-03-30 | 2022-05-13 | 68
0 | EDCDGE1125 | VALUE ENGINEERING TERMS OF REFERENCE (TOR) - ICR | 3 | 2022-02-04 | 2022-02-08 | 2022-05-11 | 2022-05-13 | 65
0 | EDCDGE1005 | ENGINEERING DELIVERABLE REGISTER - IFA | 5 | 2022-02-04 | 2022-02-11 | 2022-02-04 | 2022-02-11 | 0
0 | EDCDGE1007 | ENGINEERING DELIVERABLE REGISTER - IFC | 6 | 2022-02-25 | 2022-03-07 | 2022-02-25 | 2022-03-07 | 0
0 | EDCDGE1135 | VALUE ENGINEERING TERMS OF REFERENCE (TOR) - IFA | 10 | 2022-02-23 | 2022-03-08 | 2022-06-08 | 2022-06-21 | 72
0 | EDCDGE1155 | VALUE ENGINEERING REGISTER - IFI | 20 | 2022-02-10 | 2022-03-09 | 2022-05-17 | 2022-06-13 | 65
0 | EDCDGE1015 | ENGINEERING EXECUTION PLAN - IFA | 17 | 2022-02-18 | 2022-03-15 | 2022-06-03 | 2022-06-27 | 72
0 | EDCDGE1075 | PROJECT PROCEDURE FOR TAG NUMBERING PACKAGE-A - IFA | 20 | 2022-02-15 | 2022-03-15 | 2022-05-25 | 2022-06-21 | 68
0 | EDCDGE1025 | ENGINEERING EXECUTION PLAN - IFC | 4 | 2022-03-29 | 2022-04-04 | 2022-07-15 | 2022-07-20 | 72
0 | EDCDGE1085 | PROJECT PROCEDURE FOR TAG NUMBERING PACKAGE-A - IFC | 4 | 2022-03-29 | 2022-04-04 | 2022-07-06 | 2022-07-14 | 68
0 | EDCDGE1145 | VALUE ENGINEERING TERMS OF REFERENCE (TOR) - IFC | 10 | 2022-03-29 | 2022-04-12 | 2022-07-06 | 2022-07-22 | 68
0 | EDCDGE1165 | VALUE ENGINEERING REGISTER - IFC | 20 | 2022-03-24 | 2022-04-20 | 2022-06-28 | 2022-07-28 | 65
WORKSHOP |  |  | 360 | 2022-02-09 | 2023-07-14 | 2022-05-16 | 2023-10-04 | 56
0 | GDVWS1015 | VALUE ENGINEERING WORKSHOP | 1 | 2022-02-09 | 2022-02-09 | 2022-05-16 | 2022-05-16 | 65
0 | EDCWGE1045 | P&ID REVIEW WORKSHOP | 6 | 2022-03-28 | 2022-04-05 | 2022-06-17 | 2022-06-24 | 56
0 | EDCWGE1005 | HAZID/ENVID/OHID WORKSHOP | 3 | 2022-04-26 | 2022-04-29 | 2022-08-08 | 2022-08-10 | 68
0 | EDCWGE1000 | CRAS WORKSHOP | 2 | 2022-06-08 | 2022-06-09 | 2022-09-23 | 2022-09-26 | 74
0 | EDCWGE1050 | HAZOP WORKSHOP | 7 | 2022-06-15 | 2022-06-24 | 2022-08-29 | 2022-09-06 | 50
0 | EDCWGE1025 | BOW-TIE WORKSHOP | 3 | 2022-06-28 | 2022-07-01 | 2022-10-21 | 2022-10-25 | 80
0 | EDCWGE1055 | EHAZOP WORKSHOP | 2 | 2022-07-14 | 2022-07-15 | 2022-10-18 | 2022-10-19 | 68
0 | EDCWGE1060 | SIL WORKSHOP | 4 | 2022-07-13 | 2022-07-19 | 2022-10-14 | 2022-10-19 | 67
0 | EDCWGE1020 | ALARP WORKSHOP | 3 | 2022-08-22 | 2022-08-25 | 2023-02-10 | 2023-02-14 | 122
0 | EDCWGE1070 | HAZOP WORKSHOP (BIOCIDE PKG) | 2 | 2022-10-27 | 2022-10-28 | 2023-01-17 | 2023-01-18 | 57
0 | EDCWGE1030 | PHSER-3 WORKSHOP | 3 | 2022-12-14 | 2022-12-16 | 2023-03-29 | 2023-04-03 | 76
0 | EDCWGE1035 | PHSER-4 WORKSHOP | 2 | 2023-01-04 | 2023-01-06 | 2023-05-30 | 2023-05-31 | 102
0 | GDVWS1055 | E-HAZOP 90% REVIEW WORKSHOP | 1 | 2023-01-09 | 2023-01-09 | 2023-04-25 | 2023-04-25 | 74
0 | EDCWGE1040 | PHSER-5 WORKSHOP | 3 | 2023-03-14 | 2023-03-17 | 2023-06-20 | 2023-06-22 | 68
0 | EDCWGE1010 | RBI WORKSHOP - TOPSIDES | 2 | 2023-06-05 | 2023-06-07 | 2023-09-19 | 2023-09-20 | 72
0 | EDCWGE1015 | RBI WORKSHOP - PIPELINES | 2 | 2023-07-13 | 2023-07-14 | 2023-10-03 | 2023-10-04 | 56
PROCESS |  |  | 370 | 2021-12-20 | 2023-06-06 | 2022-02-18 | 2023-11-16 | 113
DOCUMENTS |  |  | 370 | 2021-12-20 | 2023-06-06 | 2022-02-18 | 2023-11-16 | 113
DESIGN BASIS |  |  | 83 | 2021-12-20 | 2022-04-15 | 2022-02-23 | 2022-07-22 | 64
0 | EDCDPR1015 | SIMULATION BASIS - ICR | 15 | 2021-12-20 | 2022-01-11 | 2022-02-23 | 2022-03-16 | 46
0 | EDCDPR1000 | PROCESS DESIGN BASIS - ICR | 14 | 2021-12-26 | 2022-01-14 | 2022-02-23 | 2022-03-15 | 42
0 | EDCDPR1020 | SIMULATION BASIS - IFA | 10 | 2022-01-25 | 2022-02-08 | 2022-05-20 | 2022-06-02 | 79
0 | EDCDPR1005 | PROCESS DESIGN BASIS - IFA | 10 | 2022-01-28 | 2022-02-11 | 2022-05-11 | 2022-05-24 | 69
0 | EDCDPR1030 | BASIS OF DESIGN - PROCESS DESIGN CRITERIA - ICR | 15 | 2022-01-28 | 2022-02-18 | 2022-04-29 | 2022-05-24 | 64
0 | EDCDPR1025 | SIMULATION BASIS - IFC | 16 | 2022-02-22 | 2022-03-16 | 2022-06-17 | 2022-07-13 | 79
0 | EDCDPR1035 | BASIS OF DESIGN - PROCESS DESIGN CRITERIA - IFA | 10 | 2022-03-04 | 2022-03-18 | 2022-06-08 | 2022-06-21 | 64
0 | EDCDPR1010 | PROCESS DESIGN BASIS - IFC | 20 | 2022-02-25 | 2022-03-25 | 2022-06-08 | 2022-07-05 | 69
0 | EDCDPR1040 | BASIS OF DESIGN - PROCESS DESIGN CRITERIA - IFC | 10 | 2022-04-01 | 2022-04-15 | 2022-07-06 | 2022-07-22 | 64
SCOPE OF WORK |  |  | 250 | 2021-12-23 | 2022-12-21 | 2022-02-18 | 2023-04-27 | 90
0 | EDCDPR1045 | SCOPE OF WORK FOR PIPELINE TRANSIENT HYDRAULICS STUDY - ICR | 4 | 2021-12-30 | 2022-01-06 | 2022-03-01 | 2022-03-04 | 42
0 | EDCDPR1055 | SCOPE OF WORK FOR DEPRESSURIZATION, MMDT AND HYDRATE STUDY - ICR | 10 | 2021-12-23 | 2022-01-07 | 2022-02-18 | 2022-03-03 | 40
0 | EDCDPR1050 | SCOPE OF WORK FOR PIPELINE TRANSIENT HYDRAULICS STUDY - IFA | 9 | 2022-01-20 | 2022-02-02 | 2022-04-22 | 2022-05-09 | 66
0 | EDCDPR1060 | SCOPE OF WORK FOR DEPRESSURIZATION, MMDT AND HYDRATE STUDY - IFA | 10 | 2022-01-21 | 2022-02-04 | 2022-04-19 | 2022-05-05 | 62
0 | EDCDPR1052 | SCOPE OF WORK FOR PIPELINE TRANSIENT HYDRAULICS STUDY - IFC | 11 | 2022-02-16 | 2022-03-03 | 2022-05-31 | 2022-06-14 | 71
0 | EDCDPR1062 | SCOPE OF WORK FOR DEPRESSURIZATION, MMDT AND HYDRATE STUDY - IFC | 11 | 2022-02-18 | 2022-03-07 | 2022-05-20 | 2022-06-03 | 62
0 | EDCDPR1065 | SCOPE OF WORK FOR FLOW AND ACOUSTIC INDUCED VIBRATION STUDY (AIV / FIV) - ICR | 14 | 2022-03-15 | 2022-04-04 | 2022-06-02 | 2022-06-21 | 54
0 | EDCDPR1070 | SCOPE OF WORK FOR FLOW AND ACOUSTIC INDUCED VIBRATION STUDY (AIV / FIV) - IFA | 14 | 2022-04-18 | 2022-05-11 | 2022-08-03 | 2022-08-22 | 71
0 | EDCDPR1072 | SCOPE OF WORK FOR FLOW AND ACOUSTIC INDUCED VIBRATION STUDY (AIV / FIV) - IFC | 11 | 2022-05-25 | 2022-06-09 | 2022-09-21 | 2022-10-05 | 82
0 | EDCDPR1075 | SCOPE OF WORK FOR PREPARATION OF OPERATING MANUAL AND PROCEDURES - ICR | 14 | 2022-07-26 | 2022-08-15 | 2022-11-29 | 2022-12-20 | 90
0 | EDCDPR1080 | SCOPE OF WORK FOR PREPARATION OF OPERATING MANUAL AND PROCEDURES - IFA | 14 | 2022-08-29 | 2022-09-16 | 2023-03-03 | 2023-03-22 | 132
0 | EDCDPR1082 | SCOPE OF WORK FOR PREPARATION OF OPERATING MANUAL AND PROCEDURES - IFC | 14 | 2022-11-29 | 2022-12-21 | 2023-04-06 | 2023-04-27 | 90
TBE |  |  | 211 | 2022-01-28 | 2022-11-29 | 2022-03-29 | 2023-04-05 | 90
DEPRESSURIZATION, MMDT & HYDRATE STUDY |  |  | 42 | 2022-02-21 | 2022-04-20 | 2022-04-19 | 2022-06-24 | 45
0 | EDCDPR2000 | ISSUE TBE : DEPRESSURIZATION, MMDT & HYDRATE STUDY - ICR | 10 | 2022-02-21 | 2022-03-07 | 2022-04-19 | 2022-05-05 | 41
0 | EDCDPR2005 | ISSUE TBE : DEPRESSURIZATION, MMDT & HYDRATE STUDY - IFA | 5 | 2022-03-21 | 2022-03-28 | 2022-05-20 | 2022-05-26 | 41
0 | EDCDPR2010 | ISSUE TBE : DEPRESSURIZATION, MMDT & HYDRATE STUDY - IFC | 7 | 2022-04-11 | 2022-04-20 | 2022-06-16 | 2022-06-24 | 45
PIPELINE TRANSIENT HYDRAULICS STUDY |  |  | 44 | 2022-01-28 | 2022-03-31 | 2022-03-29 | 2022-06-07 | 46
0 | EDCDPR2015 | ISSUE TBE : PIPELINE TRANSIENT HYDRAULIC STUDY - ICR | 18 | 2022-01-28 | 2022-02-23 | 2022-03-29 | 2022-04-21 | 42
0 | EDCDPR2020 | ISSUE TBE : PIPELINE TRANSIENT HYDRAULIC STUDY - IFA | 3 | 2022-03-09 | 2022-03-14 | 2022-05-13 | 2022-05-17 | 44
0 | EDCDPR2025 | ISSUE TBE : PIPELINE TRANSIENT HYDRAULIC STUDY - IFC | 3 | 2022-03-28 | 2022-03-31 | 2022-06-03 | 2022-06-07 | 46
FLOW AND ACOUSTIC INDUCED VIBRATION STUDY (AIV / FIV) |  |  | 45 | 2022-04-26 | 2022-07-01 | 2022-07-19 | 2022-09-19 | 54
0 | EDCDPR2030 | ISSUE TBE : FIV STUDY / AIV STUDY - ICR | 15 | 2022-04-26 | 2022-05-20 | 2022-07-19 | 2022-08-08 | 54
0 | EDCDPR2035 | ISSUE TBE : FIV STUDY / AIV STUDY - IFA | 5 | 2022-06-03 | 2022-06-10 | 2022-08-23 | 2022-08-29 | 54
0 | EDCDPR2040 | ISSUE TBE : FIV STUDY / AIV STUDY - IFC | 5 | 2022-06-24 | 2022-07-01 | 2022-09-13 | 2022-09-19 | 54
OPERATING MANUAL AND PROCEDURES |  |  | 55 | 2022-09-13 | 2022-11-29 | 2023-01-19 | 2023-04-05 | 90
0 | EDCDPR2045 | ISSUE TBE : OPERATING MANUALS - ICR | 20 | 2022-09-13 | 2022-10-11 | 2023-01-19 | 2023-02-15 | 90
0 | EDCDPR2050 | ISSUE TBE : OPERATING MANUALS - IFA | 10 | 2022-10-25 | 2022-11-08 | 2023-03-02 | 2023-03-15 | 90
0 | EDCDPR2055 | ISSUE TBE : OPERATING MANUALS - IFC | 5 | 2022-11-22 | 2022-11-29 | 2023-03-30 | 2023-04-05 | 90
PROCESS PHILOSOPHIES |  |  | 125 | 2022-01-14 | 2022-07-18 | 2022-03-16 | 2022-11-21 | 91
0 | EDCDPR1085 | ISOLATION PHILOSOPHY - ICR | 15 | 2022-01-14 | 2022-02-04 | 2022-03-16 | 2022-04-05 | 42
0 | EDCDPR1130 | VENT AND DRAIN PHILOSOPHY - ICR | 15 | 2022-01-18 | 2022-02-08 | 2022-03-18 | 2022-04-07 | 42
0 | EDCDPR1145 | SPARING PHILOSOPHY - ICR | 15 | 2022-01-20 | 2022-02-10 | 2022-03-22 | 2022-04-11 | 42
0 | EDCDPR1100 | P&ID DEVELOPMENT PHILOSOPHY - ICR | 20 | 2022-01-28 | 2022-02-25 | 2022-04-15 | 2022-05-17 | 54
0 | EDCDPR1160 | PROCESS SAFEGUARDING AND ESD PHILOSOPHY - ICR | 17 | 2022-02-10 | 2022-03-07 | 2022-04-12 | 2022-05-09 | 42
0 | EDCDPR1115 | FLARE RELIEF AND BLOWDOWN PHILOSOPHY - ICR | 21 | 2022-02-11 | 2022-03-14 | 2022-04-29 | 2022-06-01 | 54
0 | EDCDPR1175 | OVERPRESSURE PROTECTION PHILOSOPHY - ICR | 26 | 2022-02-10 | 2022-03-18 | 2022-04-22 | 2022-06-01 | 50
0 | EDCDPR1090 | ISOLATION PHILOSOPHY - IFA | 25 | 2022-02-18 | 2022-03-25 | 2022-05-20 | 2022-06-23 | 61
0 | EDCDPR1105 | P&ID DEVELOPMENT PHILOSOPHY - IFA | 10 | 2022-03-11 | 2022-03-25 | 2022-06-10 | 2022-06-23 | 61
0 | EDCDPR1135 | VENT AND DRAIN PHILOSOPHY - IFA | 25 | 2022-02-22 | 2022-03-29 | 2022-05-20 | 2022-06-23 | 59
0 | EDCDPR1150 | SPARING PHILOSOPHY - IFA | 25 | 2022-02-24 | 2022-03-31 | 2022-05-20 | 2022-06-23 | 57
0 | EDCDPR1165 | PROCESS SAFEGUARDING AND ESD PHILOSOPHY - IFA | 10 | 2022-03-21 | 2022-04-04 | 2022-06-10 | 2022-06-23 | 55
0 | EDCDPR1190 | PLANT OPERATION AND CONTROL PHILOSOPHY FOR OFFSHORE PLATFORMS - ICR | 15 | 2022-03-15 | 2022-04-05 | 2022-05-27 | 2022-06-16 | 50
0 | EDCDPR1205 | START-UP AND SHUTDOWN PHILOSOPHY - ICR | 15 | 2022-03-17 | 2022-04-07 | 2022-06-29 | 2022-07-22 | 71
0 | EDCDPR1235 | PIGGING PHILOSOPHY - ICR | 15 | 2022-03-21 | 2022-04-11 | 2022-08-09 | 2022-08-29 | 95
0 | EDCDPR1220 | TIE-IN PHILOSOPHY - ICR | 15 | 2022-03-25 | 2022-04-15 | 2022-07-07 | 2022-08-01 | 71
0 | EDCDPR1120 | FLARE RELIEF AND BLOWDOWN PHILOSOPHY - IFA | 15 | 2022-03-28 | 2022-04-18 | 2022-06-16 | 2022-07-06 | 54
0 | EDCDPR1180 | OVERPRESSURE PROTECTION PHILOSOPHY - IFA | 15 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 2022-07-06 | 50
0 | EDCDPR1195 | PLANT OPERATION AND CONTROL PHILOSOPHY FOR OFFSHORE PLATFORMS - IFA | 10 | 2022-04-19 | 2022-05-06 | 2022-07-01 | 2022-07-19 | 50
0 | EDCDPR1110 | P&ID DEVELOPMENT PHILOSOPHY - IFC | 20 | 2022-04-08 | 2022-05-11 | 2022-08-01 | 2022-08-26 | 74
0 | EDCDPR1210 | START-UP AND SHUTDOWN PHILOSOPHY - IFA | 15 | 2022-04-21 | 2022-05-17 | 2022-09-13 | 2022-10-03 | 97
0 | EDCDPR1095 | ISOLATION PHILOSOPHY - IFC | 25 | 2022-04-08 | 2022-05-18 | 2022-07-26 | 2022-08-29 | 70
0 | EDCDPR1240 | PIGGING PHILOSOPHY - IFA | 15 | 2022-04-25 | 2022-05-19 | 2022-09-13 | 2022-10-03 | 95
0 | EDCDPR1140 | VENT AND DRAIN PHILOSOPHY - IFC | 25 | 2022-04-12 | 2022-05-20 | 2022-07-26 | 2022-08-29 | 68
0 | EDCDPR1155 | SPARING PHILOSOPHY - IFC | 25 | 2022-04-14 | 2022-05-24 | 2022-07-25 | 2022-08-26 | 65
0 | EDCDPR1225 | TIE-IN PHILOSOPHY - IFA | 15 | 2022-04-29 | 2022-05-25 | 2022-08-16 | 2022-09-05 | 71
0 | EDCDPR1170 | PROCESS SAFEGUARDING AND ESD PHILOSOPHY - IFC | 25 | 2022-04-18 | 2022-05-26 | 2022-07-26 | 2022-08-29 | 64
0 | EDCDPR1125 | FLARE RELIEF AND BLOWDOWN PHILOSOPHY - IFC | 25 | 2022-05-05 | 2022-06-09 | 2022-07-26 | 2022-08-29 | 54
0 | EDCDPR1185 | OVERPRESSURE PROTECTION PHILOSOPHY - IFC | 25 | 2022-05-11 | 2022-06-15 | 2022-07-26 | 2022-08-29 | 50
0 | EDCDPR1200 | PLANT OPERATION AND CONTROL PHILOSOPHY FOR OFFSHORE PLATFORMS - IFC | 25 | 2022-05-20 | 2022-06-24 | 2022-08-03 | 2022-09-06 | 50
0 | EDCDPR1215 | START-UP AND SHUTDOWN PHILOSOPHY - IFC | 25 | 2022-05-31 | 2022-07-05 | 2022-10-18 | 2022-11-21 | 97
0 | EDCDPR1245 | PIGGING PHILOSOPHY - IFC | 25 | 2022-06-02 | 2022-07-07 | 2022-10-18 | 2022-11-21 | 95
0 | EDCDPR1230 | TIE-IN PHILOSOPHY - IFC | 25 | 2022-06-08 | 2022-07-18 | 2022-09-20 | 2022-10-24 | 71
PROCESS DATA SHEETS / REGISTERS |  |  | 195 | 2022-03-08 | 2022-12-16 | 2022-05-12 | 2023-04-27 | 93
0 | EDCDPR1250 | PROCESS DATASHEET PORTABLE BIOCIDE INJECTION SKID - ICR | 5 | 2022-03-08 | 2022-03-15 | 2022-05-12 | 2022-05-18 | 44
0 | EDCDPR1255 | PROCESS DATASHEET PORTABLE BIOCIDE INJECTION SKID - IFA | 9 | 2022-03-29 | 2022-04-11 | 2022-07-06 | 2022-07-21 | 68
0 | EDCDPR1260 | PROCESS DATASHEET PORTABLE BIOCIDE INJECTION SKID - IFC | 19 | 2022-04-25 | 2022-05-25 | 2022-08-08 | 2022-09-01 | 69
0 | EDCDPR1265 | REGISTER OF SAFETY RELATED DEVICES - IFI | 9 | 2022-10-21 | 2022-11-03 | 2023-03-03 | 2023-03-15 | 93
0 | EDCDPR1275 | REGISTER OF SAFETY RELATED DEVICES - IFC | 19 | 2022-11-17 | 2022-12-16 | 2023-03-30 | 2023-04-27 | 93
PROCESS LIST |  |  | 70 | 2022-02-03 | 2022-05-17 | 2022-05-16 | 2022-09-08 | 80
0 | EDCDPR1280 | FLUID LIST - ICR | 15 | 2022-02-03 | 2022-02-24 | 2022-05-16 | 2022-06-03 | 69
0 | EDCDPR1285 | FLUID LIST - IFA | 10 | 2022-03-10 | 2022-03-24 | 2022-06-29 | 2022-07-15 | 76
0 | EDCDPR1290 | FLUID LIST - IFC | 25 | 2022-04-07 | 2022-05-17 | 2022-08-05 | 2022-09-08 | 80
REPORTS & CALCULATIONS |  |  | 202 | 2022-01-03 | 2022-10-20 | 2022-03-03 | 2023-01-18 | 63
0 | EDCDPR1295 | PROCESS SIMULATION REPORT - ICR | 10 | 2022-01-03 | 2022-01-17 | 2022-03-03 | 2022-03-16 | 43
0 | EDCDPR1300 | PROCESS SIMULATION REPORT - IFA | 10 | 2022-01-31 | 2022-02-14 | 2022-05-24 | 2022-06-06 | 78
0 | EDCDPR1355 | PROCESS CALCULATION REPORT - ICR | 10 | 2022-03-14 | 2022-03-28 | 2022-06-03 | 2022-06-16 | 56
0 | EDCDPR1340 | OFFSHORE PLATFORM PROCESS AND UTILITY SYSTEM DESCRIPTION - ICR | 10 | 2022-03-15 | 2022-03-29 | 2022-07-19 | 2022-08-01 | 84
0 | EDCDPR1310 | PIPELINE STEADY STATE HYDRAULICS STUDY REPORT - ICR | 10 | 2022-03-17 | 2022-03-31 | 2022-05-19 | 2022-06-01 | 42
0 | EDCDPR1305 | PROCESS SIMULATION REPORT - IFC | 24 | 2022-02-28 | 2022-04-01 | 2022-06-21 | 2022-07-27 | 78
0 | EDCDPR1325 | HP/LP INTERFACE STUDY REPORT - ICR | 15 | 2022-03-15 | 2022-04-05 | 2022-06-03 | 2022-06-23 | 55
0 | EDCDPR1430 | CHEMICAL CONSUMPTION SUMMARY REPORT - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-07-28 | 2022-08-10 | 82
0 | EDCDPR1415 | UTILITY BALANCE / CONSUMPTION SUMMARY - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-07-28 | 2022-08-10 | 82
0 | EDCDPR1315 | PIPELINE STEADY STATE HYDRAULICS STUDY REPORT - IFA | 4 | 2022-04-14 | 2022-04-20 | 2022-06-16 | 2022-06-21 | 42
0 | EDCDPR1345 | OFFSHORE PLATFORM PROCESS AND UTILITY SYSTEM DESCRIPTION - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-08-16 | 2022-08-29 | 84
0 | EDCDPR1385 | P&ID DESIGN REVIEW AND CLOSEOUT REPORT - ICR | 15 | 2022-04-05 | 2022-04-26 | 2022-07-04 | 2022-07-27 | 61
0 | EDCDPR1330 | HP/LP INTERFACE STUDY REPORT - IFA | 9 | 2022-04-19 | 2022-05-05 | 2022-07-13 | 2022-07-25 | 55
0 | EDCDPR1435 | CHEMICAL CONSUMPTION SUMMARY REPORT - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-08-25 | 2022-09-07 | 82
0 | EDCDPR1420 | UTILITY BALANCE / CONSUMPTION SUMMARY - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-08-25 | 2022-09-07 | 82
0 | EDCDPR1475 | DEPRESSURIZATION, MMDT AND HYDRATE STUDY REPORT - ICR | 25 | 2022-04-06 | 2022-05-16 | 2022-06-06 | 2022-07-13 | 40
0 | EDCDPR1490 | PIPELINE TRANSIENT HYDRAULICS STUDY REPORT - ICR | 30 | 2022-03-31 | 2022-05-17 | 2022-06-15 | 2022-07-29 | 51
0 | EDCDPR1445 | HAZOP TERMS OF REFERENCE - ICR | 28 | 2022-04-05 | 2022-05-18 | 2022-06-17 | 2022-07-29 | 50
0 | EDCDPR1370 | HIPPS STUDY REPORT - ICR | 30 | 2022-04-04 | 2022-05-19 | 2022-06-29 | 2022-08-12 | 59
0 | EDCDPR1360 | PROCESS CALCULATION REPORT - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-08-18 | 2022-08-31 | 68
0 | EDCDPR1390 | P&ID DESIGN REVIEW AND CLOSEOUT REPORT - IFA | 12 | 2022-05-13 | 2022-05-31 | 2022-08-11 | 2022-08-26 | 61
0 | EDCDPR1320 | PIPELINE STEADY STATE HYDRAULICS STUDY REPORT - IFC | 19 | 2022-05-09 | 2022-06-03 | 2022-09-26 | 2022-10-20 | 97
0 | EDCDPR1335 | HP/LP INTERFACE STUDY REPORT - IFC | 15 | 2022-05-19 | 2022-06-09 | 2022-08-09 | 2022-08-29 | 55
0 | EDCDPR1480 | DEPRESSURIZATION, MMDT AND HYDRATE STUDY REPORT - IFA | 10 | 2022-05-30 | 2022-06-13 | 2022-07-28 | 2022-08-10 | 40
0 | EDCDPR1495 | PIPELINE TRANSIENT HYDRAULICS STUDY REPORT - IFA | 10 | 2022-05-31 | 2022-06-14 | 2022-08-15 | 2022-08-26 | 51
0 | EDCDPR1450 | HAZOP TERMS OF REFERENCE - IFA | 10 | 2022-06-01 | 2022-06-15 | 2022-08-15 | 2022-08-26 | 50
0 | EDCDPR1375 | HIPPS STUDY REPORT - IFA | 10 | 2022-06-02 | 2022-06-16 | 2022-09-16 | 2022-09-29 | 73
0 | EDCDPR1350 | OFFSHORE PLATFORM PROCESS AND UTILITY SYSTEM DESCRIPTION - IFC | 27 | 2022-05-13 | 2022-06-21 | 2022-09-13 | 2022-10-19 | 84
0 | EDCDPR1440 | CHEMICAL CONSUMPTION SUMMARY REPORT - IFC | 20 | 2022-05-26 | 2022-06-23 | 2022-09-22 | 2022-10-19 | 82
0 | EDCDPR1425 | UTILITY BALANCE / CONSUMPTION SUMMARY - IFC | 20 | 2022-05-26 | 2022-06-23 | 2022-09-22 | 2022-10-19 | 82
0 | EDCDPR1400 | OFFSHORE PLATFORMS RELIEF AND BLOWDOWN STUDY REPORT - ICR | 30 | 2022-05-16 | 2022-06-27 | 2022-08-02 | 2022-09-12 | 53
0 | EDCDPR1395 | P&ID DESIGN REVIEW AND CLOSEOUT REPORT - IFC | 15 | 2022-06-14 | 2022-07-05 | 2022-09-13 | 2022-10-03 | 62
0 | EDCDPR1460 | HAZOP STUDY REPORT - ICR | 10 | 2022-06-24 | 2022-07-13 | 2022-09-14 | 2022-09-27 | 55
0 | EDCDPR1365 | PROCESS CALCULATION REPORT- IFC | 25 | 2022-06-08 | 2022-07-18 | 2022-09-15 | 2022-10-19 | 68
0 | EDCDPR1500 | PIPELINE TRANSIENT HYDRAULICS STUDY REPORT - IFC | 16 | 2022-06-28 | 2022-07-25 | 2022-09-12 | 2022-10-03 | 51
0 | EDCDPR1455 | HAZOP TERMS OF REFERENCE - IFC | 16 | 2022-06-29 | 2022-07-26 | 2022-09-12 | 2022-10-03 | 50
0 | EDCDPR1380 | HIPPS STUDY REPORT - IFC | 16 | 2022-06-30 | 2022-07-27 | 2022-10-14 | 2022-11-04 | 73
0 | EDCDPR1485 | DEPRESSURIZATION, MMDT AND HYDRATE STUDY REPORT - IFC | 20 | 2022-06-27 | 2022-07-28 | 2022-10-11 | 2022-11-07 | 73
0 | EDCDPR1405 | OFFSHORE PLATFORMS RELIEF AND BLOWDOWN STUDY REPORT - IFA | 10 | 2022-07-14 | 2022-07-28 | 2022-09-27 | 2022-10-10 | 53
0 | EDCDPR1520 | AIV / FIV STUDY REPORT - ICR | 10 | 2022-07-21 | 2022-08-04 | 2022-10-06 | 2022-10-19 | 55
0 | EDCDPR1465 | HAZOP STUDY REPORT - IFA | 6 | 2022-07-27 | 2022-08-04 | 2022-10-12 | 2022-10-19 | 55
0 | EDCDPR1470 | HAZOP STUDY REPORT - IFC | 4 | 2022-08-18 | 2022-08-24 | 2022-12-16 | 2022-12-21 | 84
0 | EDCDPR1505 | HAZOP CLOSE OUT REPORT - ICR | 15 | 2022-08-04 | 2022-08-25 | 2022-11-01 | 2022-11-21 | 63
0 | EDCDPR1525 | AIV / FIV STUDY REPORT - IFA | 10 | 2022-08-18 | 2022-09-01 | 2022-11-28 | 2022-12-13 | 72
0 | EDCDPR1410 | OFFSHORE PLATFORMS RELIEF AND BLOWDOWN STUDY REPORT - IFC | 20 | 2022-08-11 | 2022-09-08 | 2022-10-25 | 2022-11-21 | 53
0 | EDCDPR1510 | HAZOP CLOSE OUT REPORT - IFA | 10 | 2022-09-08 | 2022-09-22 | 2022-12-08 | 2022-12-21 | 63
0 | EDCDPR1530 | AIV / FIV STUDY REPORT - IFC | 16 | 2022-09-15 | 2022-10-07 | 2022-12-28 | 2023-01-18 | 72
0 | EDCDPR1515 | HAZOP CLOSE OUT REPORT - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-01-05 | 2023-01-18 | 63
PROCESS MANUAL |  |  | 91 | 2023-01-26 | 2023-06-06 | 2023-07-11 | 2023-11-16 | 113
0 | EDCDPR1535 | OPERATING MANUAL AND PROCEDURES - ICR | 40 | 2023-01-26 | 2023-03-23 | 2023-07-11 | 2023-09-05 | 113
0 | EDCDPR1540 | OPERATING MANUAL AND PROCEDURES - IFA | 15 | 2023-04-04 | 2023-04-27 | 2023-09-18 | 2023-10-09 | 113
0 | EDCDPR1545 | OPERATING MANUAL AND PROCEDURES - IFC | 20 | 2023-05-09 | 2023-06-06 | 2023-10-20 | 2023-11-16 | 113
DRAWINGS |  |  | 195 | 2022-01-12 | 2022-10-20 | 2022-03-14 | 2022-12-28 | 48
P&ID / PSFS / DPDT |  |  | 195 | 2022-01-12 | 2022-10-20 | 2022-03-14 | 2022-12-28 | 48
0 | EDCGPR1010 | HEAT AND MATERIAL BALANCE DRAWING INDEX (H&MB) - IFI | 10 | 2022-01-17 | 2022-01-31 | 2022-04-04 | 2022-04-15 | 55
0 | EDCGPR1000 | PROCESS FLOW AND UTILITY FLOW DIAGRAM INDEX - ICR | 18 | 2022-01-12 | 2022-02-07 | 2022-03-14 | 2022-04-06 | 43
0 | EDCGPR1020 | DPDT DIAGRAM INDEX - ICR | 10 | 2022-02-07 | 2022-02-21 | 2022-04-19 | 2022-05-05 | 51
0 | EDCGPR1030 | PROCESS SAFEGUARDING FLOW SCHEMES DIAGRAM INDEX - ICR | 10 | 2022-02-09 | 2022-02-23 | 2022-04-19 | 2022-05-05 | 49
0 | EDCGPR1170 | P&ID - EQUIPMENT SYMBOLS TANKS & FLARES - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1200 | P&ID - INSTRUMENT DETAILS ESD TRIPS - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1230 | P&ID - LEVEL INSTRUMENTATION ISOLATION - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1215 | P&ID - MOTOR CONTROL DETAILS - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1140 | P&ID - EQUIPMENT SYMBOLS LEGEND - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1155 | P&ID - EQUIPMENT SYMBOLS MACHINERY & MISCELLANEOUS - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1095 | P&ID - INSTRUMENT & LOGIC FUNCTION IDENTIFICATION - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1125 | P&ID - INSTRUMENT DETAILS FOR HYDRAULIC ACTUATED VALVES - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1110 | P&ID - INSTRUMENT DETAILS FOR MOV XV ESDV & BDV VALVES - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1080 | P&ID - INSTRUMENT SYMBOLS - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1065 | P&ID - LINE NUMBERING & MISCELLANEOUS PIPING SYMBOLS - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1050 | P&ID - PIPING SYMBOLS LEGEND & MANUAL VALVE CODES - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1185 | P&ID - SAMPLE SYSTEM DETAILS - ICR | 9 | 2022-03-01 | 2022-03-14 | 2022-04-29 | 2022-05-16 | 43
0 | EDCGPR1040 | P&ID INDEX LEGEND P&IDS - ICR | 15 | 2022-02-21 | 2022-03-14 | 2022-04-21 | 2022-05-16 | 43
0 | EDCGPR1003 | PROCESS FLOW AND UTILITY FLOW DIAGRAM INDEX - IFA | 15 | 2022-02-21 | 2022-03-14 | 2022-06-29 | 2022-07-22 | 89
0 | EDCGPR1022 | DPDT DIAGRAM INDEX - IFA | 10 | 2022-03-08 | 2022-03-22 | 2022-08-25 | 2022-09-07 | 116
0 | EDCGPR1033 | PROCESS SAFEGUARDING FLOW SCHEMES DIAGRAM INDEX - IFA | 15 | 2022-03-09 | 2022-03-30 | 2022-08-25 | 2022-09-14 | 115
0 | EDCGPR1015 | HEAT AND MATERIAL BALANCE DRAWING INDEX (H&MB) - IFC | 24 | 2022-03-10 | 2022-04-13 | 2022-07-05 | 2022-08-10 | 80
0 | EDCGPR1005 | PROCESS FLOW AND UTILITY FLOW DIAGRAM INDEX - IFC | 15 | 2022-03-28 | 2022-04-18 | 2022-08-08 | 2022-08-26 | 89
0 | EDCGPR1025 | DPDT DIAGRAM INDEX - IFC | 20 | 2022-04-05 | 2022-05-06 | 2022-09-22 | 2022-10-19 | 116
0 | EDCGPR1035 | PROCESS SAFEGUARDING FLOW SCHEMES DIAGRAM INDEX - IFC | 15 | 2022-04-13 | 2022-05-09 | 2022-09-29 | 2022-10-19 | 115
0 | EDCGPR1145 | P&ID - EQUIPMENT SYMBOLS LEGEND - IFA | 9 | 2022-06-29 | 2022-07-15 | 2022-09-21 | 2022-10-03 | 57
0 | EDCGPR1055 | P&ID - PIPING SYMBOLS LEGEND & MANUAL VALVE CODES - IFA | 9 | 2022-07-01 | 2022-07-19 | 2022-09-21 | 2022-10-03 | 55
0 | EDCGPR1070 | P&ID - LINE NUMBERING & MISCELLANEOUS PIPING SYMBOLS - IFA | 9 | 2022-07-01 | 2022-07-19 | 2022-09-21 | 2022-10-03 | 55
0 | EDCGPR1085 | P&ID - INSTRUMENT SYMBOLS - IFA | 9 | 2022-07-01 | 2022-07-19 | 2022-09-21 | 2022-10-03 | 55
0 | EDCGPR1100 | P&ID - INSTRUMENT & LOGIC FUNCTION IDENTIFICATION - IFA | 9 | 2022-07-01 | 2022-07-19 | 2022-09-21 | 2022-10-03 | 55
0 | EDCGPR1130 | P&ID - INSTRUMENT DETAILS FOR HYDRAULIC ACTUATED VALVES - IFA | 9 | 2022-07-01 | 2022-07-19 | 2022-09-21 | 2022-10-03 | 55
0 | EDCGPR1175 | P&ID - EQUIPMENT SYMBOLS TANKS & FLARES - IFA | 9 | 2022-07-01 | 2022-07-19 | 2022-09-21 | 2022-10-03 | 55
0 | EDCGPR1190 | P&ID - SAMPLE SYSTEM DETAILS - IFA | 9 | 2022-07-01 | 2022-07-19 | 2022-09-21 | 2022-10-03 | 55
0 | EDCGPR1205 | P&ID - INSTRUMENT DETAILS ESD TRIPS - IFA | 9 | 2022-07-01 | 2022-07-19 | 2022-09-21 | 2022-10-03 | 55
0 | EDCGPR1220 | P&ID - MOTOR CONTROL DETAILS - IFA | 9 | 2022-07-01 | 2022-07-19 | 2022-09-21 | 2022-10-03 | 55
0 | EDCGPR1235 | P&ID - LEVEL INSTRUMENTATION ISOLATION - IFA | 9 | 2022-07-01 | 2022-07-19 | 2022-09-21 | 2022-10-03 | 55
0 | EDCGPR1115 | P&ID - INSTRUMENT DETAILS FOR MOV XV ESDV & BDV VALVES - IFA | 10 | 2022-07-01 | 2022-07-20 | 2022-09-20 | 2022-10-03 | 54
0 | EDCGPR1160 | P&ID - EQUIPMENT SYMBOLS MACHINERY & MISCELLANEOUS - IFA | 10 | 2022-07-01 | 2022-07-20 | 2022-09-20 | 2022-10-03 | 54
0 | EDCGPR1043 | P&ID INDEX LEGEND P&IDS - IFA | 15 | 2022-06-30 | 2022-07-26 | 2022-10-18 | 2022-11-07 | 75
0 | EDCGPR1180 | P&ID - EQUIPMENT SYMBOLS TANKS & FLARES - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1210 | P&ID - INSTRUMENT DETAILS ESD TRIPS - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1240 | P&ID - LEVEL INSTRUMENTATION ISOLATION - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1225 | P&ID - MOTOR CONTROL DETAILS - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1150 | P&ID - EQUIPMENT SYMBOLS LEGEND - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1165 | P&ID - EQUIPMENT SYMBOLS MACHINERY & MISCELLANEOUS - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1105 | P&ID - INSTRUMENT & LOGIC FUNCTION IDENTIFICATION - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1135 | P&ID - INSTRUMENT DETAILS FOR HYDRAULIC ACTUATED VALVES - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1120 | P&ID - INSTRUMENT DETAILS FOR MOV XV ESDV & BDV VALVES - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1090 | P&ID - INSTRUMENT SYMBOLS - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1075 | P&ID - LINE NUMBERING & MISCELLANEOUS PIPING SYMBOLS - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1060 | P&ID - PIPING SYMBOLS LEGEND & MANUAL VALVE CODES - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1195 | P&ID - SAMPLE SYSTEM DETAILS - IFC | 25 | 2022-09-09 | 2022-10-14 | 2022-11-22 | 2022-12-28 | 52
0 | EDCGPR1045 | P&ID INDEX LEGEND P&IDS - IFC | 25 | 2022-09-15 | 2022-10-20 | 2022-11-22 | 2022-12-28 | 48
MATERIAL & CORROSION |  |  | 473 | 2021-12-30 | 2023-11-14 | 2022-04-14 | 2024-02-02 | 56
DOCUMENTS |  |  | 473 | 2021-12-30 | 2023-11-14 | 2022-04-14 | 2024-02-02 | 56
SCOPE OF WORKS |  |  | 255 | 2021-12-30 | 2023-01-04 | 2022-04-14 | 2023-05-09 | 88
0 | EDCDMA1000 | SCOPE OF WORK FOR CORROSION RISK ASSESSMENT STUDY & CORROSION CONTROL MANUAL - ICR | 15 | 2021-12-30 | 2022-01-21 | 2022-04-14 | 2022-05-10 | 74
0 | EDCDMA1005 | SCOPE OF WORK FOR CORROSION RISK ASSESSMENT STUDY & CORROSION CONTROL MANUAL - IFA | 15 | 2022-02-04 | 2022-02-25 | 2022-06-15 | 2022-07-06 | 90
0 | EDCDMA1010 | SCOPE OF WORK FOR CORROSION RISK ASSESSMENT STUDY & CORROSION CONTROL MANUAL - IFC | 5 | 2022-03-11 | 2022-03-18 | 2022-07-25 | 2022-08-01 | 90
0 | EDCDMA1015 | SCOPE OF WORK FOR RISK BASED INSPECTION (RBI) STUDY - ICR | 10 | 2022-10-21 | 2022-11-04 | 2023-02-02 | 2023-02-15 | 72
0 | EDCDMA1020 | SCOPE OF WORK FOR RISK BASED INSPECTION (RBI) STUDY - IFA | 10 | 2022-11-18 | 2022-12-06 | 2023-03-24 | 2023-04-06 | 88
0 | EDCDMA1025 | SCOPE OF WORK FOR RISK BASED INSPECTION (RBI) STUDY - IFC | 13 | 2022-12-16 | 2023-01-04 | 2023-04-19 | 2023-05-09 | 88
TBE |  |  | 244 | 2022-02-28 | 2023-02-15 | 2022-06-20 | 2023-06-13 | 83
CORROSION RISK ASSESSMENT STUDY & CORROSION CONTROL MANUAL |  |  | 37 | 2022-02-28 | 2022-04-20 | 2022-06-20 | 2022-08-19 | 81
0 | EDCDMA2000 | ISSUE TBE : MATERIAL AND CORROSSION CONTROL STUDY (CRAS & CCM) - ICR | 11 | 2022-02-28 | 2022-03-15 | 2022-06-20 | 2022-07-05 | 77
0 | EDCDMA2005 | ISSUE TBE : MATERIAL AND CORROSSION CONTROL STUDY (CRAS & CCM) - IFA | 5 | 2022-03-29 | 2022-04-05 | 2022-07-22 | 2022-07-29 | 77
0 | EDCDMA2010 | ISSUE TBE : MATERIAL AND CORROSSION CONTROL STUDY (CRAS & CCM) - IFC | 1 | 2022-04-19 | 2022-04-20 | 2022-08-18 | 2022-08-19 | 81
RISK BASED INSPECTION (RBI) STUDY |  |  | 55 | 2022-11-28 | 2023-02-15 | 2023-03-10 | 2023-06-13 | 83
0 | EDCDMA2015 | ISSUE TBE : RBI STUDY - ICR | 20 | 2022-11-28 | 2022-12-28 | 2023-03-10 | 2023-04-06 | 72
0 | EDCDMA2020 | ISSUE TBE : RBI STUDY - IFA | 10 | 2023-01-11 | 2023-01-25 | 2023-04-25 | 2023-05-08 | 72
0 | EDCDMA2025 | ISSUE TBE : RBI STUDY - IFC | 5 | 2023-02-08 | 2023-02-15 | 2023-06-07 | 2023-06-13 | 83
SPECIFICATION |  |  | 327 | 2022-02-03 | 2023-05-22 | 2022-05-23 | 2023-10-02 | 91
0 | EDCDMA1045 | CORROSION INHIBITION TREATMENT SPECIFICATION - ICR | 21 | 2022-02-03 | 2022-03-04 | 2022-05-23 | 2022-06-20 | 74
0 | EDCDMA1030 | COATING AND PAINTING SPECIFICATION - ICR | 21 | 2022-02-11 | 2022-03-14 | 2022-08-25 | 2022-09-22 | 132
0 | EDCDMA1060 | CORROSION MONITORING SPECIFICATION - ICR | 16 | 2022-02-23 | 2022-03-17 | 2022-06-13 | 2022-07-04 | 75
0 | EDCDMA1050 | CORROSION INHIBITION TREATMENT SPECIFICATION - IFA | 15 | 2022-03-18 | 2022-04-08 | 2022-07-05 | 2022-07-28 | 74
0 | EDCDMA1035 | COATING AND PAINTING SPECIFICATION - IFA | 10 | 2022-03-28 | 2022-04-11 | 2022-10-07 | 2022-10-20 | 132
0 | EDCDMA1065 | CORROSION MONITORING SPECIFICATION - IFA | 15 | 2022-03-31 | 2022-04-21 | 2022-07-22 | 2022-08-11 | 75
0 | EDCDMA1070 | CORROSION MONITORING SPECIFICATION - IFC | 10 | 2022-05-10 | 2022-05-24 | 2022-08-26 | 2022-09-08 | 75
0 | EDCDMA1055 | CORROSION INHIBITION TREATMENT SPECIFICATION - IFC | 20 | 2022-04-22 | 2022-05-25 | 2022-08-12 | 2022-09-08 | 74
0 | EDCDMA1040 | COATING AND PAINTING SPECIFICATION - IFC | 25 | 2022-04-25 | 2022-06-02 | 2022-11-04 | 2022-12-12 | 132
0 | EDCDMA1075 | RBI METHODOLOGY/SPECIFICATION - ICR | 15 | 2023-02-09 | 2023-03-02 | 2023-05-24 | 2023-06-13 | 72
0 | EDCDMA1080 | RBI METHODOLOGY/SPECIFICATION - IFA | 15 | 2023-03-16 | 2023-04-06 | 2023-07-03 | 2023-07-24 | 72
0 | EDCDMA1085 | RBI METHODOLOGY/SPECIFICATION - IFC | 20 | 2023-04-20 | 2023-05-22 | 2023-09-04 | 2023-10-02 | 91
REPORTS / PHILOSOPHIES / STUDIES |  |  | 452 | 2022-01-28 | 2023-11-14 | 2022-05-27 | 2024-02-02 | 56
0 | EDCDMA1090 | CORROSION CONTROL AND MANAGEMENT PHILOSOPHY - ICR | 10 | 2022-01-28 | 2022-02-11 | 2022-06-15 | 2022-06-28 | 94
0 | EDCDMA1135 | MATERIAL SELECTION REPORT - ICR | 10 | 2022-02-23 | 2022-03-09 | 2022-05-27 | 2022-06-09 | 64
0 | EDCDMA1095 | CORROSION CONTROL AND MANAGEMENT PHILOSOPHY - IFA | 11 | 2022-02-25 | 2022-03-14 | 2022-07-18 | 2022-08-01 | 94
0 | EDCDMA2035 | CHEMICAL INJECTION STUDY REPORT - ICR | 10 | 2022-03-14 | 2022-03-28 | 2022-09-06 | 2022-09-19 | 119
0 | EDCDMA1140 | MATERIAL SELECTION REPORT - IFA | 9 | 2022-03-23 | 2022-04-05 | 2022-07-07 | 2022-07-22 | 73
0 | EDCDMA1105 | CRAS METHODOLOGY - ICR | 4 | 2022-04-11 | 2022-04-15 | 2022-08-01 | 2022-08-05 | 74
0 | EDCDMA2045 | CHEMICAL INJECTION STUDY REPORT - IFA | 10 | 2022-04-11 | 2022-04-25 | 2022-10-04 | 2022-10-17 | 119
0 | EDCDMA1110 | CRAS METHODOLOGY - IFA | 5 | 2022-04-29 | 2022-05-11 | 2022-08-19 | 2022-08-26 | 74
0 | EDCDMA1100 | CORROSION CONTROL AND MANAGEMENT PHILOSOPHY - IFC | 30 | 2022-03-28 | 2022-05-12 | 2022-08-16 | 2022-09-26 | 94
0 | EDCDMA1145 | MATERIAL SELECTION REPORT - IFC | 15 | 2022-04-19 | 2022-05-13 | 2022-08-09 | 2022-08-29 | 74
0 | EDCDMA2055 | CHEMICAL INJECTION STUDY REPORT - IFC | 15 | 2022-05-12 | 2022-06-02 | 2022-11-01 | 2022-11-21 | 119
0 | EDCDMA1115 | CRAS METHODOLOGY - IFC | 10 | 2022-05-25 | 2022-06-08 | 2022-09-09 | 2022-09-23 | 74
0 | EDCDMA1120 | CORROSION RISK ASSESSMENT STUDY REPORT - ICR | 10 | 2022-06-10 | 2022-06-23 | 2022-09-27 | 2022-10-10 | 74
0 | EDCDMA1125 | CORROSION RISK ASSESSMENT STUDY REPORT - IFA | 10 | 2022-07-13 | 2022-07-26 | 2022-10-25 | 2022-11-07 | 74
0 | EDCDMA1130 | CORROSION RISK ASSESSMENT STUDY REPORT - IFC | 25 | 2022-08-10 | 2022-09-13 | 2022-11-22 | 2022-12-28 | 74
0 | EDCDMA1165 | RBI STUDY REPORT FOR TOPSIDE & WHT - ICR | 30 | 2023-06-07 | 2023-07-25 | 2023-09-21 | 2023-11-02 | 72
0 | EDCDMA1170 | RBI STUDY REPORT FOR TOPSIDE & WHT - IFA | 10 | 2023-08-08 | 2023-08-22 | 2023-11-17 | 2023-11-30 | 72
0 | EDCDMA1180 | RBI STUDY REPORT FOR PIPELINES - ICR | 30 | 2023-07-17 | 2023-08-28 | 2023-10-05 | 2023-11-15 | 56
0 | EDCDMA1175 | RBI STUDY REPORT FOR TOPSIDE & WHT - IFC | 10 | 2023-09-05 | 2023-09-19 | 2023-12-18 | 2023-12-29 | 72
0 | EDCDMA1185 | RBI STUDY REPORT FOR PIPELINES - IFA | 15 | 2023-09-12 | 2023-10-03 | 2023-11-30 | 2023-12-21 | 56
0 | EDCDMA1190 | RBI STUDY REPORT FOR PIPELINES - IFC | 20 | 2023-10-18 | 2023-11-14 | 2024-01-08 | 2024-02-02 | 56
MANUAL |  |  | 95 | 2023-01-26 | 2023-06-12 | 2023-05-16 | 2023-10-02 | 76
0 | EDCDMA1195 | CORROSION CONTROL MANUAL - ICR | 45 | 2023-01-26 | 2023-03-30 | 2023-05-16 | 2023-07-21 | 76
0 | EDCDMA1200 | CORROSION CONTROL MANUAL - IFA | 15 | 2023-04-13 | 2023-05-08 | 2023-08-07 | 2023-08-25 | 76
0 | EDCDMA1205 | CORROSION CONTROL MANUAL - IFC | 15 | 2023-05-22 | 2023-06-12 | 2023-09-11 | 2023-10-02 | 76
SAFETY |  |  | 414 | 2021-12-21 | 2023-08-14 | 2022-03-14 | 2023-11-16 | 68
DOCUMENTS |  |  | 414 | 2021-12-21 | 2023-08-14 | 2022-03-14 | 2023-11-16 | 68
BASIS OF DESIGN |  |  | 100 | 2021-12-21 | 2022-05-16 | 2022-04-07 | 2022-09-02 | 76
0 | EDCDSA1000 | ENGINEERING HSE PLAN - ICR | 10 | 2021-12-21 | 2022-01-05 | 2022-04-07 | 2022-04-21 | 76
0 | EDCDSA1005 | ENGINEERING HSE PLAN - IFA | 15 | 2022-01-19 | 2022-02-09 | 2022-05-11 | 2022-05-31 | 76
0 | EDCDSA1015 | ENVIRONMENTAL BASIS OF DESIGN - ICR | 10 | 2022-02-09 | 2022-02-23 | 2022-06-01 | 2022-06-14 | 76
0 | EDCDSA1010 | ENGINEERING HSE PLAN - IFC | 16 | 2022-02-23 | 2022-03-17 | 2022-07-15 | 2022-08-05 | 95
0 | EDCDSA1020 | ENVIRONMENTAL BASIS OF DESIGN - IFA | 15 | 2022-03-09 | 2022-03-30 | 2022-06-29 | 2022-07-22 | 76
0 | EDCDSA1025 | ENVIRONMENTAL BASIS OF DESIGN - IFC | 20 | 2022-04-13 | 2022-05-16 | 2022-08-08 | 2022-09-02 | 76
SCOPE OF WORK |  |  | 73 | 2021-12-28 | 2022-04-11 | 2022-03-14 | 2022-09-15 | 108
0 | EDCDSA1030 | SCOPE OF WORK FOR HSE STUDIES - ICR | 10 | 2021-12-28 | 2022-01-12 | 2022-03-14 | 2022-03-25 | 53
0 | EDCDSA1045 | SOW FOR IVB HSECES - ICR | 20 | 2022-01-12 | 2022-02-09 | 2022-06-06 | 2022-07-01 | 100
0 | EDCDSA1035 | SCOPE OF WORK FOR HSE STUDIES - IFA | 10 | 2022-01-26 | 2022-02-09 | 2022-04-28 | 2022-05-16 | 66
0 | EDCDSA1040 | SCOPE OF WORK FOR HSE STUDIES - IFC | 11 | 2022-02-23 | 2022-03-10 | 2022-05-31 | 2022-06-14 | 66
0 | EDCDSA1050 | SOW FOR IVB HSECES - IFA | 14 | 2022-02-23 | 2022-03-15 | 2022-08-02 | 2022-08-19 | 108
0 | EDCDSA1055 | SOW FOR IVB HSECES - IFC | 9 | 2022-03-29 | 2022-04-11 | 2022-09-05 | 2022-09-15 | 108
TBE |  |  | 61 | 2022-02-10 | 2022-05-11 | 2022-04-27 | 2022-10-03 | 101
HSE STUDIES |  |  | 45 | 2022-02-10 | 2022-04-14 | 2022-04-27 | 2022-08-19 | 86
0 | EDCDSA2000 | ISSUE TBE : HSE STUDIES - ICR | 15 | 2022-02-10 | 2022-03-03 | 2022-04-27 | 2022-05-20 | 54
0 | EDCDSA2005 | ISSUE TBE : HSE STUDIES - IFA | 5 | 2022-03-17 | 2022-03-24 | 2022-06-08 | 2022-06-14 | 56
0 | EDCDSA2010 | ISSUE TBE : HSE STUDIES - IFC | 5 | 2022-04-07 | 2022-04-14 | 2022-08-15 | 2022-08-19 | 86
IVB HSECES |  |  | 41 | 2022-03-10 | 2022-05-11 | 2022-08-08 | 2022-10-03 | 101
0 | EDCDSA2015 | ISSUE TBE : IVB HSECES STUDIES - ICR | 11 | 2022-03-10 | 2022-03-25 | 2022-08-08 | 2022-08-22 | 101
0 | EDCDSA2020 | ISSUE TBE : IVB HSECES STUDIES - IFA | 5 | 2022-04-08 | 2022-04-15 | 2022-09-06 | 2022-09-12 | 101
0 | EDCDSA2025 | ISSUE TBE : IVB HSECES STUDIES - IFC | 5 | 2022-04-29 | 2022-05-11 | 2022-09-27 | 2022-10-03 | 101
SPECIFICATIONS |  |  | 75 | 2022-05-30 | 2022-09-15 | 2022-09-06 | 2023-03-22 | 133
0 | EDCDSA1060 | FIREFIGHTING SAFETY AND LIFE SAVING EQUIPMENT LIST - ICR | 10 | 2022-05-30 | 2022-06-13 | 2022-09-13 | 2022-09-26 | 73
0 | EDCDSA1075 | FIRE FIGHTING, LIFE SAVING & SAFETY EQUIPMENT SPECIFICATION - ICR | 15 | 2022-05-30 | 2022-06-20 | 2022-09-06 | 2022-09-26 | 68
0 | EDCDSA1090 | SAFETY SIGN SPECIFICATION - ICR | 10 | 2022-06-20 | 2022-07-04 | 2022-09-27 | 2022-10-10 | 68
0 | EDCDSA1065 | FIREFIGHTING SAFETY AND LIFE SAVING EQUIPMENT LIST - IFA | 10 | 2022-06-27 | 2022-07-14 | 2022-10-25 | 2022-11-07 | 83
0 | EDCDSA1080 | FIRE FIGHTING, LIFE SAVING & SAFETY EQUIPMENT SPECIFICATION - IFA | 15 | 2022-07-04 | 2022-07-28 | 2023-01-19 | 2023-02-08 | 138
0 | EDCDSA1095 | SAFETY SIGN SPECIFICATION - IFA | 10 | 2022-07-21 | 2022-08-04 | 2022-10-25 | 2022-11-07 | 68
0 | EDCDSA1070 | FIREFIGHTING SAFETY AND LIFE SAVING EQUIPMENT LIST - IFC | 15 | 2022-07-28 | 2022-08-18 | 2022-12-29 | 2023-01-18 | 108
0 | EDCDSA1085 | FIRE FIGHTING, LIFE SAVING & SAFETY EQUIPMENT SPECIFICATION - IFC | 20 | 2022-08-11 | 2022-09-08 | 2023-02-23 | 2023-03-22 | 138
0 | EDCDSA1100 | SAFETY SIGN SPECIFICATION - IFC | 20 | 2022-08-18 | 2022-09-15 | 2023-01-13 | 2023-02-09 | 104
STUDIES / REPORTS / ANALYSIS |  |  | 333 | 2022-04-14 | 2023-08-14 | 2022-07-07 | 2023-11-16 | 68
0 | EDCDSA1135 | EIA SCOPING REPORT - ICR | 15 | 2022-04-14 | 2022-05-10 | 2022-09-27 | 2022-10-17 | 112
0 | EDCDSA1510 | CFD STUDY - METHODOLOGY & ASSUMPTIONS REGISTER - ICR | 15 | 2022-04-14 | 2022-05-10 | 2022-08-26 | 2022-09-15 | 90
0 | EDCDSA1210 | HAZID/ENVID/OHID REPORT - ICR | 8 | 2022-04-29 | 2022-05-16 | 2022-08-11 | 2022-08-22 | 68
0 | EDCDSA1105 | EERA, QRA & FERA STUDY - METHODOLOGY & ASSUMPTIONS REGISTER- ICR | 15 | 2022-04-20 | 2022-05-16 | 2022-07-07 | 2022-08-01 | 53
0 | EDCDSA1525 | NOISE STUDY METHODOLOGY AND ASSUMPTION REGISTER - ICR | 15 | 2022-04-26 | 2022-05-20 | 2022-09-16 | 2022-10-06 | 97
0 | EDCDSA1150 | EIA REPORT - ICR | 10 | 2022-05-10 | 2022-05-24 | 2022-10-18 | 2022-10-31 | 112
0 | EDCDSA1180 | FIRE AND EXPLOSION RISK ASSESSMENT (FERA) STUDY REPORT - ICR | 10 | 2022-05-19 | 2022-06-02 | 2022-08-19 | 2022-09-01 | 63
0 | EDCDSA1240 | HAZID/ENVID/OHID CLOSEOUT REPORT - ICR | 15 | 2022-05-16 | 2022-06-06 | 2022-12-08 | 2022-12-28 | 143
0 | EDCDSA1140 | EIA SCOPING REPORT - IFA | 10 | 2022-05-24 | 2022-06-07 | 2022-11-08 | 2022-11-21 | 117
0 | EDCDSA1360 | VENT RADIATION AND DISPERSION STUDY REPORT - ICR | 15 | 2022-05-24 | 2022-06-14 | 2022-10-18 | 2022-11-07 | 102
0 | EDCDSA1515 | CFD STUDY - METHODOLOGY & ASSUMPTIONS REGISTER - IFA | 15 | 2022-05-24 | 2022-06-14 | 2022-10-31 | 2022-11-18 | 111
0 | EDCDSA1315 | FIRE AND GAS MAPPING STUDY REPORT - ICR | 15 | 2022-05-27 | 2022-06-17 | 2022-08-23 | 2022-09-12 | 59
0 | EDCDSA1110 | EERA, QRA & FERA STUDY - METHODOLOGY & ASSUMPTIONS REGISTER- IFA | 15 | 2022-05-30 | 2022-06-20 | 2022-08-22 | 2022-09-09 | 57
0 | EDCDSA1155 | EIA REPORT - IFA | 10 | 2022-06-07 | 2022-06-21 | 2022-11-15 | 2022-11-28 | 112
0 | EDCDSA1530 | NOISE STUDY METHODOLOGY AND ASSUMPTION REGISTER - IFA | 15 | 2022-06-03 | 2022-06-24 | 2022-10-21 | 2022-11-10 | 97
0 | EDCDSA1215 | HAZID/ENVID/OHID REPORT - IFA | 20 | 2022-05-30 | 2022-06-27 | 2022-10-11 | 2022-11-07 | 93
0 | EDCDSA1185 | FIRE AND EXPLOSION RISK ASSESSMENT (FERA) STUDY REPORT - IFA | 10 | 2022-06-16 | 2022-06-30 | 2022-10-11 | 2022-10-24 | 80
0 | EDCDSA1195 | HAZARDOUS AREA CLASSIFICATION REPORT & SCHEDULE (PHA) - ICR | 10 | 2022-06-17 | 2022-07-01 | 2022-11-11 | 2022-11-24 | 102
0 | EDCDSA1285 | CFD FLAMMABLE AND TOXIC GAS DISPERSION AND EXPLOSION STUDY REPORT - ICR | 10 | 2022-06-22 | 2022-07-06 | 2022-09-16 | 2022-09-29 | 59
0 | EDCDSA1345 | QUANTITATIVE RISK ASSESSMENT (QRA) STUDY REPORT - ICR | 10 | 2022-06-22 | 2022-07-06 | 2022-09-16 | 2022-09-29 | 59
0 | EDCDSA1255 | FIREWATER DEMAND CALCULATION REPORT - IFI | 15 | 2022-06-17 | 2022-07-13 | 2022-10-14 | 2022-11-03 | 82
0 | EDCDSA1270 | FIREWATER HYDRAULIC CALCULATION REPORT - IFI | 15 | 2022-06-17 | 2022-07-13 | 2022-10-14 | 2022-11-03 | 82
0 | EDCDSA1245 | HAZID/ENVID/OHID CLOSEOUT REPORT - IFA | 15 | 2022-06-20 | 2022-07-14 | 2023-01-12 | 2023-02-01 | 143
0 | EDCDSA1375 | COMAH REPORT - ICR | 10 | 2022-06-29 | 2022-07-18 | 2022-10-21 | 2022-11-03 | 79
0 | EDCDSA1330 | OHRA REPORT - ICR | 10 | 2022-06-29 | 2022-07-18 | 2022-10-18 | 2022-10-31 | 76
0 | EDCDSA1225 | BOW-TIE REPORT AND HSECES REGISTER - ICR | 10 | 2022-07-01 | 2022-07-20 | 2022-10-26 | 2022-11-08 | 80
0 | EDCDSA1390 | H2S DISPERSION AND ZONING STUDY REPORT - ICR | 10 | 2022-07-01 | 2022-07-20 | 2022-11-07 | 2022-11-18 | 88
0 | EDCDSA1405 | ESCAPE EVACUATION AND RESCUE ASSESSMENT (EERA) STUDY REPORT - ICR | 10 | 2022-07-01 | 2022-07-20 | 2022-09-27 | 2022-10-10 | 59
0 | EDCDSA1755 | HSEIA SCREENING REPORT – OPERATION PHASE- ICR | 10 | 2022-07-01 | 2022-07-20 | 2022-10-28 | 2022-11-10 | 82
0 | EDCDSA1300 | HSECES & PERFORMANCE STANDARDS REPORT - ICR | 10 | 2022-07-04 | 2022-07-21 | 2022-10-28 | 2022-11-10 | 81
0 | EDCDSA1120 | HSE CRITICAL INTEGRITY VERIFICATION SCHEME (HSECIVS) - IVB SERVICES - ICR | 15 | 2022-06-27 | 2022-07-21 | 2022-10-21 | 2022-11-10 | 81
0 | EDCDSA1435 | EPC PHASE HSEIA REPORT AND DOSSIER- ICR | 10 | 2022-07-04 | 2022-07-21 | 2022-10-26 | 2022-11-08 | 79
0 | EDCDSA1145 | EIA SCOPING REPORT - IFC | 20 | 2022-06-21 | 2022-07-22 | 2022-12-08 | 2023-01-04 | 117
0 | EDCDSA1365 | VENT RADIATION AND DISPERSION STUDY REPORT - IFA | 15 | 2022-06-28 | 2022-07-22 | 2022-11-22 | 2022-12-14 | 102
0 | EDCDSA1520 | CFD STUDY - METHODOLOGY & ASSUMPTIONS REGISTER - IFC | 15 | 2022-06-28 | 2022-07-22 | 2022-12-07 | 2022-12-27 | 111
0 | EDCDSA1570 | DROPPED OBJECT PROTECTION STUDY - ICR | 10 | 2022-07-06 | 2022-07-25 | 2022-11-02 | 2022-11-15 | 82
0 | EDCDSA1320 | FIRE AND GAS MAPPING STUDY REPORT - IFA | 15 | 2022-07-01 | 2022-07-27 | 2022-09-27 | 2022-10-17 | 59
0 | EDCDSA1420 | EMERGENCY SYSTEM SURVIVABILITY ANALYSIS (ESSA) REPORT - ICR | 15 | 2022-07-01 | 2022-07-27 | 2022-09-27 | 2022-10-17 | 59
0 | EDCDSA1160 | EIA REPORT - IFC | 15 | 2022-07-05 | 2022-07-29 | 2022-12-15 | 2023-01-04 | 112
0 | EDCDSA1165 | NOISE STUDY REPORT - ICR | 10 | 2022-07-15 | 2022-07-29 | 2022-10-14 | 2022-10-27 | 65
0 | EDCDSA1200 | HAZARDOUS AREA CLASSIFICATION REPORT & SCHEDULE (PHA) - IFA | 10 | 2022-07-20 | 2022-08-03 | 2023-01-03 | 2023-01-16 | 117
0 | EDCDSA1535 | NOISE STUDY METHODOLOGY AND ASSUMPTION REGISTER - IFC | 15 | 2022-07-13 | 2022-08-03 | 2022-12-20 | 2023-01-09 | 112
0 | EDCDSA1350 | QUANTITATIVE RISK ASSESSMENT (QRA) STUDY REPORT - IFA | 10 | 2022-07-25 | 2022-08-08 | 2022-11-22 | 2022-12-07 | 86
0 | EDCDSA1220 | HAZID/ENVID/OHID REPORT - IFC | 20 | 2022-07-14 | 2022-08-11 | 2022-11-22 | 2022-12-21 | 93
0 | EDCDSA1115 | EERA, QRA & FERA STUDY - METHODOLOGY & ASSUMPTIONS REGISTER- IFC | 25 | 2022-07-04 | 2022-08-11 | 2022-09-26 | 2022-10-28 | 57
0 | EDCDSA1190 | FIRE AND EXPLOSION RISK ASSESSMENT (FERA) STUDY REPORT - IFC | 15 | 2022-07-21 | 2022-08-11 | 2022-11-08 | 2022-11-28 | 78
0 | EDCDSA1380 | COMAH REPORT - IFA | 10 | 2022-08-01 | 2022-08-15 | 2023-01-12 | 2023-01-25 | 116
0 | EDCDSA1335 | OHRA REPORT - IFA | 10 | 2022-08-01 | 2022-08-15 | 2022-11-15 | 2022-11-28 | 76
0 | EDCDSA1410 | ESCAPE EVACUATION AND RESCUE ASSESSMENT (EERA) STUDY REPORT - IFA | 10 | 2022-08-03 | 2022-08-17 | 2022-11-15 | 2022-11-28 | 74
0 | EDCDSA1440 | EPC PHASE HSEIA REPORT AND DOSSIER- IFA | 9 | 2022-08-04 | 2022-08-17 | 2022-11-23 | 2022-12-07 | 79
0 | EDCDSA1395 | H2S DISPERSION AND ZONING STUDY REPORT - IFA | 10 | 2022-08-03 | 2022-08-17 | 2022-12-07 | 2022-12-20 | 88
0 | EDCDSA1230 | BOW-TIE REPORT AND HSECES REGISTER - IFA | 10 | 2022-08-03 | 2022-08-17 | 2022-11-23 | 2022-12-08 | 80
0 | EDCDSA1765 | HSEIA SCREENING REPORT – OPERATION PHASE- IFA | 10 | 2022-08-03 | 2022-08-17 | 2022-11-25 | 2022-12-12 | 82
0 | EDCDSA1125 | HSE CRITICAL INTEGRITY VERIFICATION SCHEME (HSECIVS) - IVB SERVICES - IFA | 10 | 2022-08-04 | 2022-08-18 | 2022-11-25 | 2022-12-12 | 81
0 | EDCDSA1305 | HSECES & PERFORMANCE STANDARDS REPORT - IFA | 10 | 2022-08-04 | 2022-08-18 | 2022-11-25 | 2022-12-12 | 81
0 | EDCDSA1575 | DROPPED OBJECT PROTECTION STUDY - IFA | 9 | 2022-08-08 | 2022-08-19 | 2022-11-30 | 2022-12-14 | 82
0 | EDCDSA1290 | CFD FLAMMABLE AND TOXIC GAS DISPERSION AND EXPLOSION STUDY REPORT - IFA | 10 | 2022-08-08 | 2022-08-22 | 2022-11-28 | 2022-12-13 | 80
0 | EDCDSA1250 | HAZID/ENVID/OHID CLOSEOUT REPORT - IFC | 19 | 2022-07-28 | 2022-08-24 | 2023-02-16 | 2023-03-14 | 143
0 | EDCDSA1265 | FIREWATER DEMAND CALCULATION REPORT - IFC | 20 | 2022-07-27 | 2022-08-24 | 2022-11-18 | 2022-12-19 | 82
0 | EDCDSA1280 | FIREWATER HYDRAULIC CALCULATION REPORT- IFC | 20 | 2022-07-27 | 2022-08-24 | 2022-11-18 | 2022-12-19 | 82
0 | EDCDSA1450 | ALARP DEMONSTRATION REPORT - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-02-01 | 2023-02-14 | 122
0 | EDCDSA1370 | VENT RADIATION AND DISPERSION STUDY REPORT - IFC | 15 | 2022-08-05 | 2022-08-26 | 2022-12-29 | 2023-01-18 | 102
0 | EDCDSA1170 | NOISE STUDY REPORT - IFA | 10 | 2022-08-12 | 2022-08-26 | 2022-11-11 | 2022-11-24 | 65
0 | EDCDSA2100 | SHIPPING INTERACTION STUDY REPORT - ICR | 15 | 2022-08-08 | 2022-08-29 | 2022-10-13 | 2022-11-02 | 48
0 | EDCDSA1205 | HAZARDOUS AREA CLASSIFICATION REPORT & SCHEDULE (PHA) - IFC | 10 | 2022-08-17 | 2022-08-31 | 2023-01-31 | 2023-02-13 | 117
0 | EDCDSA1425 | EMERGENCY SYSTEM SURVIVABILITY ANALYSIS (ESSA) REPORT - IFA | 15 | 2022-08-10 | 2022-08-31 | 2022-11-01 | 2022-11-21 | 59
0 | EDCDSA1325 | FIRE AND GAS MAPPING STUDY REPORT - IFC | 20 | 2022-08-10 | 2022-09-07 | 2022-11-01 | 2022-11-28 | 59
0 | EDCDSA1235 | BOW-TIE REPORT AND HSECES REGISTER - IFC | 7 | 2022-08-31 | 2022-09-09 | 2022-12-23 | 2023-01-02 | 80
0 | EDCDSA1580 | DROPPED OBJECT PROTECTION STUDY - IFC | 5 | 2022-09-02 | 2022-09-09 | 2022-12-29 | 2023-01-04 | 82
0 | EDCDSA2160 | HUMAN FACTOR ENGINEERING STUDY REPORT - ICR | 10 | 2022-08-26 | 2022-09-09 | 2022-11-08 | 2022-11-21 | 52
0 | EDCDSA1130 | HSE CRITICAL INTEGRITY VERIFICATION SCHEME (HSECIVS) - IVB SERVICES - IFC | 7 | 2022-09-01 | 2022-09-12 | 2022-12-27 | 2023-01-04 | 81
0 | EDCDSA1385 | COMAH REPORT - IFC | 10 | 2022-08-29 | 2022-09-12 | 2023-02-09 | 2023-02-22 | 116
0 | EDCDSA1340 | OHRA REPORT - IFC | 10 | 2022-08-29 | 2022-09-12 | 2022-12-15 | 2022-12-28 | 76
0 | EDCDSA1295 | CFD FLAMMABLE AND TOXIC GAS DISPERSION AND EXPLOSION STUDY REPORT - IFC | 5 | 2022-09-05 | 2022-09-12 | 2022-12-28 | 2023-01-03 | 80
0 | EDCDSA1310 | HSECES & PERFORMANCE STANDARDS REPORT - IFC | 7 | 2022-09-01 | 2022-09-12 | 2022-12-27 | 2023-01-04 | 81
0 | EDCDSA1775 | HSEIA SCREENING REPORT – OPERATION PHASE- IFC | 7 | 2022-09-01 | 2022-09-12 | 2022-12-27 | 2023-01-04 | 81
0 | EDCDSA1355 | QUANTITATIVE RISK ASSESSMENT ASSUMPTION REPORT - IFC | 10 | 2022-08-30 | 2022-09-13 | 2022-12-22 | 2023-01-04 | 80
0 | EDCDSA1445 | EPC PHASE HSEIA REPORT AND DOSSIER- IFC | 10 | 2022-09-05 | 2022-09-19 | 2022-12-22 | 2023-01-04 | 76
0 | EDCDSA1415 | ESCAPE EVACUATION AND RESCUE ASSESSMENT (EERA) STUDY REPORT - IFC | 15 | 2022-08-31 | 2022-09-21 | 2022-12-15 | 2023-01-04 | 74
0 | EDCDSA1400 | H2S DISPERSION AND ZONING STUDY REPORT - IFC | 15 | 2022-08-31 | 2022-09-21 | 2023-01-04 | 2023-01-24 | 88
0 | EDCDSA1585 | HSE ACTION TRACKING REGISTER - ICR | 50 | 2022-07-13 | 2022-09-21 | 2022-10-24 | 2023-01-03 | 73
0 | EDCDSA1455 | ALARP DEMONSTRATION REPORT - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-01 | 2023-03-14 | 122
0 | EDCDSA2105 | SHIPPING INTERACTION STUDY REPORT - IFA | 15 | 2022-09-12 | 2022-10-03 | 2022-11-17 | 2022-12-09 | 48
0 | EDCDSA1175 | NOISE STUDY REPORT - IFC | 20 | 2022-09-09 | 2022-10-07 | 2022-12-13 | 2023-01-09 | 65
0 | EDCDSA2165 | HUMAN FACTOR ENGINEERING STUDY REPORT - IFA | 10 | 2022-09-23 | 2022-10-07 | 2022-12-08 | 2022-12-21 | 52
0 | EDCDSA1430 | EMERGENCY SYSTEM SURVIVABILITY ANALYSIS (ESSA) REPORT - IFC | 20 | 2022-09-14 | 2022-10-12 | 2022-12-08 | 2023-01-04 | 59
0 | EDCDSA1600 | SIMOPS PROCEDURE - DRILLING AND OPERATION/MAINTENANCE- ICR | 20 | 2022-10-03 | 2022-10-31 | 2023-01-18 | 2023-02-14 | 75
0 | EDCDSA2110 | SHIPPING INTERACTION STUDY REPORT - IFC | 10 | 2022-10-17 | 2022-10-31 | 2022-12-26 | 2023-01-06 | 48
0 | EDCDSA1460 | ALARP DEMONSTRATION REPORT - IFC | 20 | 2022-10-06 | 2022-11-03 | 2023-03-29 | 2023-04-27 | 122
0 | EDCDSA2170 | HUMAN FACTOR ENGINEERING STUDY REPORT - IFC | 10 | 2022-10-21 | 2022-11-04 | 2023-01-05 | 2023-01-18 | 52
0 | EDCDSA1590 | HSE ACTION TRACKING REGISTER - IFA | 30 | 2022-10-05 | 2022-11-16 | 2023-01-18 | 2023-02-28 | 73
0 | EDCDSA1605 | SIMOPS PROCEDURE - DRILLING AND OPERATION/MAINTENANCE - IFA | 15 | 2022-11-14 | 2022-12-07 | 2023-03-01 | 2023-03-21 | 75
0 | EDCDSA1480 | PHSER STAGE 3 REPORT - ICR | 14 | 2022-12-19 | 2023-01-05 | 2023-05-17 | 2023-06-05 | 105
0 | EDCDSA1465 | OPERATION PHASE HSEIA REPORT AND DOSSIER - ICR | 15 | 2022-12-19 | 2023-01-06 | 2023-06-23 | 2023-07-18 | 132
0 | EDCDSA1610 | SIMOPS PROCEDURE - DRILLING AND OPERATION/MAINTENANCE- IFC | 15 | 2022-12-21 | 2023-01-11 | 2023-04-05 | 2023-04-27 | 75
0 | EDCDSA1595 | HSE ACTION TRACKING REGISTER - IFC | 30 | 2022-11-30 | 2023-01-13 | 2023-03-15 | 2023-04-27 | 73
0 | EDCDSA2120 | EMERGENCY RESPONSE PLAN – OPERATIONS - ICR | 15 | 2023-01-02 | 2023-01-20 | 2023-06-23 | 2023-07-18 | 122
0 | EDCDSA1495 | PHSER STAGE 3 CLOSEOUT REPORT - ICR | 14 | 2023-01-06 | 2023-01-25 | 2023-06-06 | 2023-06-23 | 105
0 | EDCDSA2140 | ENVIRONMENTAL MANAGEMENT PLAN – OPERATIONS - ICR | 15 | 2023-01-09 | 2023-01-27 | 2023-06-23 | 2023-07-18 | 117
0 | EDCDSA1485 | PHSER STAGE 3 REPORT - IFA | 14 | 2023-01-20 | 2023-02-08 | 2023-07-13 | 2023-08-02 | 119
0 | EDCDSA1470 | OPERATION PHASE HSEIA REPORT AND DOSSIER - IFA | 15 | 2023-01-23 | 2023-02-10 | 2023-08-03 | 2023-08-23 | 132
0 | EDCDSA1540 | PHSER STAGE IV REPORT - ICR | 30 | 2023-01-09 | 2023-02-20 | 2023-06-02 | 2023-07-18 | 102
0 | EDCDSA2125 | EMERGENCY RESPONSE PLAN – OPERATIONS- IFA | 15 | 2023-02-06 | 2023-02-24 | 2023-08-03 | 2023-08-23 | 122
0 | EDCDSA1500 | PHSER STAGE 3 CLOSEOUT REPORT - IFA | 14 | 2023-02-09 | 2023-02-28 | 2023-07-13 | 2023-08-02 | 105
0 | EDCDSA2145 | ENVIRONMENTAL MANAGEMENT PLAN – OPERATIONS- IFA | 15 | 2023-02-13 | 2023-03-03 | 2023-08-03 | 2023-08-23 | 117
0 | EDCDSA1490 | PHSER STAGE 3 REPORT - IFC | 15 | 2023-02-23 | 2023-03-15 | 2023-08-17 | 2023-09-06 | 119
0 | EDCDSA1475 | OPERATION PHASE HSEIA REPORT AND DOSSIER - IFC | 15 | 2023-02-27 | 2023-03-17 | 2023-09-07 | 2023-09-28 | 132
0 | EDCDSA1545 | PHSER STAGE IV REPORT - IFA | 15 | 2023-03-06 | 2023-03-27 | 2023-08-03 | 2023-08-23 | 102
0 | EDCDSA2130 | EMERGENCY RESPONSE PLAN – OPERATIONS - IFC | 15 | 2023-03-13 | 2023-03-31 | 2023-09-07 | 2023-09-28 | 122
0 | EDCDSA1505 | PHSER STAGE 3 CLOSEOUT REPORT - IFC | 15 | 2023-03-15 | 2023-04-04 | 2023-08-17 | 2023-09-06 | 105
0 | EDCDSA2150 | ENVIRONMENTAL MANAGEMENT PLAN – OPERATIONS - IFC | 15 | 2023-03-20 | 2023-04-07 | 2023-09-07 | 2023-09-28 | 117
0 | EDCDSA2035 | PHSER STAGE IV CLOSEOUT REPORT - ICR | 10 | 2023-03-27 | 2023-04-10 | 2023-09-01 | 2023-09-14 | 108
0 | EDCDSA1555 | PHSER STAGE V REPORT - ICR | 30 | 2023-03-17 | 2023-05-02 | 2023-06-23 | 2023-08-09 | 68
0 | EDCDSA1550 | PHSER STAGE IV REPORT - IFC | 15 | 2023-04-10 | 2023-05-03 | 2023-09-07 | 2023-09-28 | 102
0 | EDCDSA2045 | PHSER STAGE IV CLOSEOUT REPORT - IFA | 10 | 2023-04-26 | 2023-05-10 | 2023-10-02 | 2023-10-13 | 108
0 | EDCDSA1560 | PHSER STAGE V REPORT - IFA | 15 | 2023-05-16 | 2023-06-06 | 2023-08-24 | 2023-09-13 | 68
0 | EDCDSA2055 | PHSER STAGE IV CLOSEOUT REPORT - IFC | 10 | 2023-05-24 | 2023-06-07 | 2023-10-30 | 2023-11-10 | 108
0 | EDCDSA2065 | PHSER STAGE V CLOSEOUT REPORT - ICR | 10 | 2023-05-30 | 2023-06-13 | 2023-09-07 | 2023-09-20 | 68
0 | EDCDSA1565 | PHSER STAGE V REPORT - IFC | 15 | 2023-06-20 | 2023-07-14 | 2023-10-23 | 2023-11-10 | 84
0 | EDCDSA2075 | PHSER STAGE V CLOSEOUT REPORT - IFA | 10 | 2023-06-30 | 2023-07-14 | 2023-10-06 | 2023-10-19 | 68
0 | EDCDSA2085 | PHSER STAGE V CLOSEOUT REPORT - IFC | 10 | 2023-07-31 | 2023-08-14 | 2023-11-03 | 2023-11-16 | 68
PHILOSOPHIES |  |  | 159 | 2022-01-05 | 2022-08-24 | 2022-04-27 | 2022-12-05 | 72
0 | EDCDSA1615 | HSE DESIGN PHILOSOPHY - ICR | 20 | 2022-01-05 | 2022-02-02 | 2022-04-27 | 2022-05-27 | 79
0 | EDCDSA1620 | HSE DESIGN PHILOSOPHY - IFA | 11 | 2022-02-14 | 2022-03-01 | 2022-06-09 | 2022-06-23 | 79
0 | EDCDSA1630 | LOSS PREVENTION PHILOSOPHY - ICR | 10 | 2022-02-24 | 2022-03-10 | 2022-06-21 | 2022-07-04 | 79
0 | EDCDSA1645 | ESCAPE EVACUATION AND RESCUE PHILOSOPHY - ICR | 16 | 2022-03-02 | 2022-03-24 | 2022-07-05 | 2022-07-29 | 85
0 | EDCDSA1635 | LOSS PREVENTION PHILOSOPHY - IFA | 10 | 2022-03-22 | 2022-04-05 | 2022-07-20 | 2022-08-02 | 79
0 | EDCDSA1625 | HSE DESIGN PHILOSOPHY - IFC | 25 | 2022-03-15 | 2022-04-19 | 2022-07-25 | 2022-08-26 | 88
0 | EDCDSA1650 | ESCAPE EVACUATION AND RESCUE PHILOSOPHY - IFA | 10 | 2022-04-07 | 2022-04-21 | 2022-08-15 | 2022-08-26 | 85
0 | EDCDSA1640 | LOSS PREVENTION PHILOSOPHY - IFC | 8 | 2022-04-19 | 2022-04-29 | 2022-08-17 | 2022-08-26 | 79
0 | EDCDSA1655 | ESCAPE EVACUATION AND RESCUE PHILOSOPHY - IFC | 20 | 2022-05-10 | 2022-06-07 | 2022-11-04 | 2022-12-05 | 124
0 | EDCDSA1660 | PASSIVE FIRE PROTECTION SCHEDULE - ICR | 10 | 2022-06-02 | 2022-06-16 | 2022-09-02 | 2022-09-15 | 63
0 | EDCDSA1665 | PASSIVE FIRE PROTECTION SCHEDULE - IFA | 10 | 2022-06-28 | 2022-07-15 | 2022-09-28 | 2022-10-11 | 63
0 | EDCDSA1670 | PASSIVE FIRE PROTECTION SCHEDULE - IFC | 20 | 2022-07-27 | 2022-08-24 | 2022-10-24 | 2022-11-18 | 63
PROCEDURE |  |  | 243 | 2022-03-29 | 2023-03-15 | 2022-07-06 | 2023-06-20 | 68
0 | EDCDSA1675 | PHA (HAZID/ENVID/OHID) PROCEDURE - ICR | 3 | 2022-03-29 | 2022-04-01 | 2022-07-06 | 2022-07-13 | 68
0 | EDCDSA1735 | BOW-TIE TOR - ICR | 9 | 2022-04-01 | 2022-04-14 | 2022-08-01 | 2022-08-11 | 80
0 | EDCDSA1680 | PHA (HAZID/ENVID/OHID) PROCEDURE - IFA | 7 | 2022-04-15 | 2022-04-26 | 2022-07-28 | 2022-08-05 | 68
0 | EDCDSA1740 | BOW-TIE TOR - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-08-26 | 2022-09-08 | 80
0 | EDCDSA1685 | PHA (HAZID/ENVID/OHID) PROCEDURE - IFC | 7 | 2022-05-13 | 2022-05-24 | 2022-11-11 | 2022-11-21 | 127
0 | EDCDSA1745 | BOW-TIE TOR - IFC | 10 | 2022-05-31 | 2022-06-14 | 2022-09-23 | 2022-10-06 | 80
0 | EDCDSA1690 | PHSER 3 TOR - ICR | 9 | 2022-10-07 | 2022-10-20 | 2023-01-13 | 2023-01-25 | 68
0 | EDCDSA1705 | PHSER IV TOR - ICR | 10 | 2022-10-27 | 2022-11-10 | 2023-02-02 | 2023-02-15 | 68
0 | EDCDSA1695 | PHSER 3 TOR - IFA | 10 | 2022-11-03 | 2022-11-17 | 2023-02-21 | 2023-03-06 | 76
0 | EDCDSA1710 | PHSER IV TOR - IFA | 10 | 2022-11-24 | 2022-12-12 | 2023-03-02 | 2023-03-15 | 68
0 | EDCDSA1700 | PHSER 3 TOR - IFC | 8 | 2022-12-05 | 2022-12-15 | 2023-03-21 | 2023-03-30 | 76
0 | EDCDSA1715 | PHSER IV TOR - IFC | 7 | 2022-12-26 | 2023-01-04 | 2023-03-30 | 2023-04-07 | 68
0 | EDCDSA1720 | PHSER V TOR - ICR | 10 | 2023-01-04 | 2023-01-18 | 2023-04-10 | 2023-04-25 | 68
0 | EDCDSA1725 | PHSER V TOR - IFA | 10 | 2023-02-01 | 2023-02-15 | 2023-05-10 | 2023-05-23 | 68
0 | EDCDSA1730 | PHSER V TOR - IFC | 10 | 2023-03-01 | 2023-03-15 | 2023-06-07 | 2023-06-20 | 68
REQUISITIONS |  |  | 67 | 2022-08-04 | 2022-11-07 | 2022-11-08 | 2023-04-06 | 107
MR 62881 FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT |  |  | 62 | 2022-08-04 | 2022-10-31 | 2022-11-08 | 2023-04-06 | 112
REQUISITIONS |  |  | 35 | 2022-08-04 | 2022-09-22 | 2022-11-08 | 2023-04-06 | 139
0 | EDCMSA1000 | FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT - ISSUE MR - ICR | 5 | 2022-08-04 | 2022-08-11 | 2022-11-08 | 2022-11-14 | 68
0 | EDCMSA1005 | FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT - ISSUE MR - IFA | 5 | 2022-08-25 | 2022-09-01 | 2023-03-01 | 2023-03-07 | 132
0 | EDCMSA1010 | FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT - ISSUE MR - IFC | 5 | 2022-09-15 | 2022-09-22 | 2023-03-31 | 2023-04-06 | 139
TBE |  |  | 37 | 2022-09-08 | 2022-10-31 | 2023-02-15 | 2023-04-06 | 112
0 | EDCMSA2010 | COMPLETE EVALUATION AND SUBMIT TBE - FIREFIGHTING, LIFE SAVING & SAFETY EQUIMENT - ICR | 15 | 2022-09-08 | 2022-09-29 | 2023-02-15 | 2023-03-07 | 112
0 | EDCMSA2015 | RECEIVE COMMENTS & ISSUE TBE - FIREFIGHTING, LIFE SAVING & SAFETY EQUIMENT - IFA | 10 | 2022-09-29 | 2022-10-13 | 2023-03-08 | 2023-03-21 | 112
0 | EDCMSA2020 | ISSUE TBE - FIREFIGHTING, LIFE SAVING & SAFETY EQUIMENT - IFC | 11 | 2022-10-14 | 2022-10-31 | 2023-03-23 | 2023-04-06 | 112
MR 62882 SAFETY SIGNS |  |  | 62 | 2022-08-11 | 2022-11-07 | 2022-12-08 | 2023-03-03 | 83
REQUISITIONS |  |  | 35 | 2022-08-11 | 2022-09-29 | 2022-12-08 | 2023-02-16 | 99
0 | EDCMSA1015 | SAFETY SIGNS - ISSUE MR - ICR | 5 | 2022-08-11 | 2022-08-18 | 2022-12-08 | 2022-12-14 | 83
0 | EDCMSA1020 | SAFETY SIGNS - ISSUE MR - IFA | 5 | 2022-09-01 | 2022-09-08 | 2023-01-05 | 2023-01-11 | 88
0 | EDCMSA1025 | SAFETY SIGNS - ISSUE MR - IFC | 5 | 2022-09-22 | 2022-09-29 | 2023-02-10 | 2023-02-16 | 99
TBE |  |  | 37 | 2022-09-15 | 2022-11-07 | 2023-01-12 | 2023-03-03 | 83
0 | EDCMSA2030 | COMPLETE EVALUATION AND SUBMIT TBE - SAFETY SIGNS - ICR | 15 | 2022-09-15 | 2022-10-06 | 2023-01-12 | 2023-02-01 | 83
0 | EDCMSA2035 | RECEIVE TBE COMPANY APPROVAL - SAFETY SIGNS | 10 | 2022-10-06 | 2022-10-20 | 2023-02-02 | 2023-02-15 | 83
0 | EDCMSA2040 | ISSUE TBE - SAFETY SIGNS - IFC | 11 | 2022-10-21 | 2022-11-07 | 2023-02-17 | 2023-03-03 | 83
PIPING |  |  | 225 | 2021-12-30 | 2022-11-21 | 2022-03-09 | 2023-01-24 | 45
DOCUMENTS |  |  | 167 | 2021-12-30 | 2022-08-31 | 2022-03-09 | 2023-01-06 | 91
DESING BASIS |  |  | 75 | 2022-01-05 | 2022-04-20 | 2022-03-14 | 2022-07-22 | 62
0 | EDCDPI1000 | PIPING BASIS OF DESIGN - ICR | 15 | 2022-01-05 | 2022-01-26 | 2022-03-14 | 2022-04-01 | 48
0 | EDCDPI1005 | PIPING BASIS OF DESIGN - IFA | 16 | 2022-02-09 | 2022-03-03 | 2022-05-11 | 2022-06-01 | 62
0 | EDCDPI1010 | PIPING BASIS OF DESIGN - IFC | 24 | 2022-03-17 | 2022-04-20 | 2022-06-16 | 2022-07-22 | 62
SCOPE OF WORK |  |  | 65 | 2021-12-30 | 2022-04-01 | 2022-03-09 | 2022-06-13 | 48
0 | EDCDPI1015 | SOW FOR 3D LASER SCAN SURVEY - ICR | 20 | 2021-12-30 | 2022-01-28 | 2022-03-09 | 2022-04-06 | 48
0 | EDCDPI1017 | SOW FOR 3D LASER SCAN SURVEY - IFA | 20 | 2022-02-11 | 2022-03-11 | 2022-04-21 | 2022-05-23 | 48
0 | EDCDPI1020 | SOW FOR 3D LASER SCAN SURVEY - IFC | 5 | 2022-03-25 | 2022-04-01 | 2022-06-07 | 2022-06-13 | 48
TBE |  |  | 41 | 2022-02-14 | 2022-04-12 | 2022-04-27 | 2022-07-05 | 57
0 | EDCDPI2000 | ISSUE TBE : 3D LASER SCAN SURVEY - ICR | 11 | 2022-02-14 | 2022-03-01 | 2022-04-27 | 2022-05-16 | 51
0 | EDCDPI2005 | ISSUE TBE : 3D LASER SCAN SURVEY - IFA | 10 | 2022-03-01 | 2022-03-15 | 2022-05-25 | 2022-06-07 | 57
0 | EDCDPI2010 | ISSUE TBE : 3D LASER SCAN SURVEY - IFC | 10 | 2022-03-29 | 2022-04-12 | 2022-06-22 | 2022-07-05 | 57
SPECIFICATION |  |  | 106 | 2022-02-21 | 2022-07-27 | 2022-05-25 | 2022-11-18 | 83
0 | EDCDPI1025 | PIPING MATERIAL SPECIFICATION - ICR | 15 | 2022-02-21 | 2022-03-14 | 2022-05-25 | 2022-06-14 | 64
0 | EDCDPI1040 | SPECIFICATION FOR PIPING STRESS ANALYSIS - ICR | 15 | 2022-02-21 | 2022-03-14 | 2022-07-14 | 2022-08-03 | 97
0 | EDCDPI1130 | SPECIFICATION FOR PIPES - ICR | 10 | 2022-03-03 | 2022-03-17 | 2022-06-22 | 2022-07-05 | 76
0 | EDCDPI1220 | SPECIFICATION FOR CLADDED PIPING COMPONENTS - ICR | 5 | 2022-03-10 | 2022-03-17 | 2022-07-20 | 2022-07-26 | 88
0 | EDCDPI1145 | SPECIFICATIONS FOR FITTINGS (AMENDMENTS/SUPPLEMENTS TO STD-108) - ICR | 10 | 2022-03-03 | 2022-03-17 | 2022-06-22 | 2022-07-05 | 76
0 | EDCDPI1160 | SPECIFICATIONS FOR FLANGES (AMENDMENTS/SUPPLEMENTS TO STD-108) - ICR | 10 | 2022-03-04 | 2022-03-18 | 2022-06-23 | 2022-07-06 | 76
0 | EDCDPI1175 | SPECIFICATION FOR GRE PIPING ( (AMENDMENTS/SUPPLEMENTS TO SP-1160) - ICR | 10 | 2022-03-07 | 2022-03-21 | 2022-06-24 | 2022-07-07 | 76
0 | EDCDPI1510 | SPECIFICATION FOR PIPING SPECIAL ITEMS - ICR | 10 | 2022-03-07 | 2022-03-21 | 2022-07-01 | 2022-07-19 | 81
0 | EDCDPI1190 | SPECIFICATIONS FOR GASKETS (AMENDMENTS/SUPPLEMENTS TO STD-127) - ICR | 10 | 2022-03-08 | 2022-03-22 | 2022-06-27 | 2022-07-13 | 76
0 | EDCDPI1205 | SPECIFICATION FOR BOLTING (AMENDMENTS/SUPPLEMENTS TO STD-126) - ICR | 10 | 2022-03-09 | 2022-03-23 | 2022-07-19 | 2022-08-01 | 88
0 | EDCDPI1070 | SPECIFICATIONS FOR CHECK VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-3) - ICR | 10 | 2022-03-09 | 2022-03-23 | 2022-06-16 | 2022-06-29 | 68
0 | EDCDPI1055 | SPECIFICATIONS FOR BALL VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-2) -ICR | 15 | 2022-03-07 | 2022-03-28 | 2022-06-14 | 2022-07-04 | 68
0 | EDCDPI1235 | SPECIFICATION FOR BOLT TORQUE - ICR | 10 | 2022-03-15 | 2022-03-29 | 2022-07-04 | 2022-07-20 | 76
0 | EDCDPI1085 | SPECIFICATIONS FOR GATE VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-1) - ICR | 15 | 2022-03-11 | 2022-04-01 | 2022-06-20 | 2022-07-13 | 68
0 | EDCDPI1115 | SPECIFICATIONS FOR BUTTERFLY VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-4) -ICR | 10 | 2022-03-18 | 2022-04-01 | 2022-06-27 | 2022-07-13 | 68
0 | EDCDPI1100 | SPECIFICATIONS FOR GLOBE VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-5) - ICR | 15 | 2022-03-16 | 2022-04-06 | 2022-06-23 | 2022-07-18 | 68
0 | EDCDPI1225 | SPECIFICATION FOR CLADDED PIPING COMPONENTS - IFA | 5 | 2022-03-31 | 2022-04-07 | 2022-08-11 | 2022-08-17 | 89
0 | EDCDPI1045 | SPECIFICATION FOR PIPING STRESS ANALYSIS - IFA | 10 | 2022-03-28 | 2022-04-11 | 2022-08-18 | 2022-08-31 | 97
0 | EDCDPI1540 | SPECIFICATION FOR SPRINGS AND RIGID STRUTS - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-07-21 | 2022-08-03 | 76
0 | EDCDPI1600 | SPECIFICATION FOR PIPE SUPPORT - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-07-21 | 2022-08-03 | 76
0 | EDCDPI1150 | SPECIFICATIONS FOR FITTINGS (AMENDMENTS/SUPPLEMENTS TO STD-108) - IFA | 10 | 2022-03-31 | 2022-04-14 | 2022-08-08 | 2022-08-19 | 86
0 | EDCDPI1135 | SPECIFICATION FOR PIPES - IFA | 10 | 2022-03-31 | 2022-04-14 | 2022-07-28 | 2022-08-10 | 79
0 | EDCDPI1165 | SPECIFICATIONS FOR FLANGES (AMENDMENTS/SUPPLEMENTS TO STD-108) - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-08-11 | 2022-08-24 | 88
0 | EDCDPI1030 | PIPING MATERIAL SPECIFICATION - IFA | 15 | 2022-03-28 | 2022-04-18 | 2022-06-29 | 2022-07-22 | 64
0 | EDCDPI1180 | SPECIFICATION FOR GRE PIPING ( (AMENDMENTS/SUPPLEMENTS TO SP-1160) - IFA | 10 | 2022-04-04 | 2022-04-18 | 2022-08-15 | 2022-08-26 | 89
0 | EDCDPI1520 | SPECIFICATION FOR PIPING SPECIAL ITEMS - IFA | 10 | 2022-04-04 | 2022-04-18 | 2022-08-23 | 2022-09-05 | 95
0 | EDCDPI1630 | SPECIFICATION FOR PIPING FABRICATION, ERECTION & TESTING - ICR | 10 | 2022-04-04 | 2022-04-18 | 2022-07-27 | 2022-08-09 | 76
0 | EDCDPI1195 | SPECIFICATIONS FOR GASKETS (AMENDMENTS/SUPPLEMENTS TO STD-127) - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-09-02 | 2022-09-15 | 102
0 | EDCDPI1660 | SPECIFICATION FOR INSULATION - ICR | 10 | 2022-04-05 | 2022-04-19 | 2022-07-28 | 2022-08-10 | 76
0 | EDCDPI1210 | SPECIFICATION FOR BOLTING (AMENDMENTS/SUPPLEMENTS TO STD-126) - IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-09-02 | 2022-09-15 | 101
0 | EDCDPI1075 | SPECIFICATIONS FOR CHECK VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-3) - IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-08-02 | 2022-08-15 | 78
0 | EDCDPI1690 | SPECIFICATION FOR PRESSURE TESTING OF PIPING - ICR | 10 | 2022-04-06 | 2022-04-20 | 2022-09-12 | 2022-09-23 | 107
0 | EDCDPI1060 | SPECIFICATIONS FOR BALL VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-2) -IFA | 10 | 2022-04-11 | 2022-04-25 | 2022-08-05 | 2022-08-18 | 78
0 | EDCDPI1240 | SPECIFICATION FOR BOLT TORQUE - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-09-02 | 2022-09-15 | 97
0 | EDCDPI1120 | SPECIFICATIONS FOR BUTTERFLY VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-4) -IFA | 10 | 2022-04-15 | 2022-04-29 | 2022-07-28 | 2022-08-10 | 68
0 | EDCDPI1090 | SPECIFICATIONS FOR GATE VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-1) - IFA | 10 | 2022-04-15 | 2022-04-29 | 2022-08-04 | 2022-08-17 | 73
0 | EDCDPI1105 | SPECIFICATIONS FOR GLOBE VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-5) - IFA | 10 | 2022-04-20 | 2022-05-09 | 2022-08-04 | 2022-08-17 | 70
0 | EDCDPI1550 | SPECIFICATION FOR SPRINGS AND RIGID STRUTS - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-09-06 | 2022-09-19 | 89
0 | EDCDPI1610 | SPECIFICATION FOR PIPE SUPPORT - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-09-20 | 2022-10-03 | 99
0 | EDCDPI2020 | SPECIFICATION FOR HUMAN FACTOR ENGINEERING - ICR | 30 | 2022-03-29 | 2022-05-13 | 2022-06-27 | 2022-08-10 | 61
0 | EDCDPI1230 | SPECIFICATION FOR CLADDED PIPING COMPONENTS - IFC | 15 | 2022-04-21 | 2022-05-17 | 2022-09-05 | 2022-09-23 | 91
0 | EDCDPI1155 | SPECIFICATIONS FOR FITTINGS (AMENDMENTS/SUPPLEMENTS TO STD-108) - IFC | 10 | 2022-04-28 | 2022-05-17 | 2022-09-05 | 2022-09-16 | 86
0 | EDCDPI1170 | SPECIFICATIONS FOR FLANGES (AMENDMENTS/SUPPLEMENTS TO STD-108) - IFC | 10 | 2022-04-29 | 2022-05-18 | 2022-09-12 | 2022-09-23 | 90
0 | EDCDPI1185 | SPECIFICATION FOR GRE PIPING ( (AMENDMENTS/SUPPLEMENTS TO SP-1160) - IFC | 10 | 2022-05-05 | 2022-05-19 | 2022-09-12 | 2022-09-23 | 89
0 | EDCDPI1530 | SPECIFICATION FOR PIPING SPECIAL ITEMS - IFC | 10 | 2022-05-05 | 2022-05-19 | 2022-09-27 | 2022-10-10 | 100
0 | EDCDPI1640 | SPECIFICATION FOR PIPING FABRICATION, ERECTION & TESTING - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-10-10 | 2022-10-21 | 109
0 | EDCDPI1670 | SPECIFICATION FOR INSULATION - IFA | 10 | 2022-05-06 | 2022-05-20 | 2022-08-25 | 2022-09-07 | 76
0 | EDCDPI1700 | SPECIFICATION FOR PRESSURE TESTING OF PIPING - IFA | 10 | 2022-05-09 | 2022-05-23 | 2022-10-10 | 2022-10-21 | 107
0 | EDCDPI1035 | PIPING MATERIAL SPECIFICATION - IFC | 14 | 2022-05-05 | 2022-05-25 | 2022-08-22 | 2022-09-08 | 74
0 | EDCDPI1140 | SPECIFICATION FOR PIPES - IFC | 20 | 2022-04-28 | 2022-05-31 | 2022-09-22 | 2022-10-19 | 99
0 | EDCDPI1050 | SPECIFICATION FOR PIPING STRESS ANALYSIS - IFC | 25 | 2022-04-25 | 2022-06-02 | 2022-09-15 | 2022-10-19 | 97
0 | EDCDPI1065 | SPECIFICATIONS FOR BALL VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-2) -IFC | 15 | 2022-05-12 | 2022-06-02 | 2022-09-13 | 2022-10-03 | 85
0 | EDCDPI1200 | SPECIFICATIONS FOR GASKETS (AMENDMENTS/SUPPLEMENTS TO STD-127) - IFC | 20 | 2022-05-06 | 2022-06-03 | 2022-09-30 | 2022-10-27 | 102
0 | EDCDPI1215 | SPECIFICATION FOR BOLTING (AMENDMENTS/SUPPLEMENTS TO STD-126) - IFC | 20 | 2022-05-09 | 2022-06-06 | 2022-09-30 | 2022-10-27 | 101
0 | EDCDPI1080 | SPECIFICATIONS FOR CHECK VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-3) - IFC | 20 | 2022-05-09 | 2022-06-06 | 2022-08-30 | 2022-09-26 | 78
0 | EDCDPI1245 | SPECIFICATION FOR BOLT TORQUE - IFC | 20 | 2022-05-13 | 2022-06-10 | 2022-09-30 | 2022-10-27 | 97
0 | EDCDPI1560 | SPECIFICATION FOR SPRINGS AND RIGID STRUTS - IFC | 10 | 2022-05-27 | 2022-06-10 | 2022-10-18 | 2022-10-31 | 99
0 | EDCDPI1620 | SPECIFICATION FOR PIPE SUPPORT - IFC | 10 | 2022-05-27 | 2022-06-10 | 2022-10-18 | 2022-10-31 | 99
0 | EDCDPI1710 | SPECIFICATION FOR PRESSURE TESTING OF PIPING - IFC | 5 | 2022-06-06 | 2022-06-13 | 2022-11-07 | 2022-11-11 | 107
0 | EDCDPI1095 | SPECIFICATIONS FOR GATE VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-1) - IFC | 20 | 2022-05-18 | 2022-06-15 | 2022-09-01 | 2022-09-28 | 73
0 | EDCDPI1125 | SPECIFICATIONS FOR BUTTERFLY VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-4) -IFC | 20 | 2022-05-18 | 2022-06-15 | 2022-08-25 | 2022-09-21 | 68
0 | EDCDPI1650 | SPECIFICATION FOR PIPING FABRICATION, ERECTION & TESTING - IFC | 10 | 2022-06-02 | 2022-06-16 | 2022-11-07 | 2022-11-18 | 109
0 | EDCDPI1680 | SPECIFICATION FOR INSULATION - IFC | 10 | 2022-06-03 | 2022-06-17 | 2022-09-22 | 2022-10-05 | 76
0 | EDCDPI2025 | SPECIFICATION FOR HUMAN FACTOR ENGINEERING - IFA | 15 | 2022-05-27 | 2022-06-17 | 2022-08-25 | 2022-09-14 | 61
0 | EDCDPI1110 | SPECIFICATIONS FOR GLOBE VALVES (AMENDMENTS/SUPPLEMENTS TO SP-1151 PART-5) - IFC | 20 | 2022-05-23 | 2022-06-20 | 2022-09-01 | 2022-09-28 | 70
0 | EDCDPI2030 | SPECIFICATION FOR HUMAN FACTOR ENGINEERING - IFC | 15 | 2022-07-01 | 2022-07-27 | 2022-09-29 | 2022-10-19 | 61
MTO |  |  | 105 | 2022-03-29 | 2022-08-31 | 2022-07-04 | 2023-01-06 | 91
0 | EDCDPI1250 | 1ST MTO - PIPING BULK MATERIALS | 20 | 2022-03-29 | 2022-04-26 | 2022-07-04 | 2022-08-03 | 66
0 | EDCDPI1255 | FINAL MTO - PIPING BULK MATERIALS | 10 | 2022-08-17 | 2022-08-31 | 2022-12-26 | 2023-01-06 | 91
DATA SHEET |  |  | 72 | 2022-03-23 | 2022-07-06 | 2022-06-30 | 2022-10-31 | 81
0 | EDCDPI1290 | DATA SHEETS FOR CHECK VALVES - ICR | 5 | 2022-03-23 | 2022-03-30 | 2022-06-30 | 2022-07-06 | 68
0 | EDCDPI1260 | DATA SHEETS FOR BALL VALVES - ICR | 5 | 2022-03-28 | 2022-04-04 | 2022-07-13 | 2022-07-19 | 71
0 | EDCDPI1305 | DATA SHEETS FOR GATE, GLOBE & PISTON LIFT CHECK VALVES - ICR | 4 | 2022-04-01 | 2022-04-07 | 2022-07-14 | 2022-07-19 | 68
0 | EDCDPI1320 | DATA SHEETS FOR IDBB VALVES - ICR | 5 | 2022-04-01 | 2022-04-08 | 2022-07-14 | 2022-07-20 | 68
0 | EDCDPI1275 | DATA SHEETS FOR BUTTEFLY VALVES - ICR | 5 | 2022-04-01 | 2022-04-08 | 2022-07-19 | 2022-07-25 | 71
0 | EDCDPI1335 | DATA SHEETS PIPING SPECIALTY ITEMS - ICR | 15 | 2022-04-01 | 2022-04-22 | 2022-07-20 | 2022-08-09 | 72
0 | EDCDPI1570 | DATA SHEETS ITEMIZED PIPE SUPPORTS (SPRINGS/ SLIDING PLATES) - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-08-08 | 2022-08-19 | 78
0 | EDCDPI1265 | DATA SHEETS FOR BALL VALVES - IFA | 10 | 2022-04-19 | 2022-05-06 | 2022-08-05 | 2022-08-18 | 72
0 | EDCDPI1295 | DATA SHEETS FOR CHECK VALVES - IFA | 15 | 2022-04-13 | 2022-05-09 | 2022-07-26 | 2022-08-15 | 68
0 | EDCDPI1280 | DATA SHEETS FOR BUTTEFLY VALVES - IFA | 10 | 2022-04-22 | 2022-05-11 | 2022-08-09 | 2022-08-22 | 71
0 | EDCDPI1310 | DATA SHEETS FOR GATE, GLOBE & PISTON LIFT CHECK VALVES - IFA | 14 | 2022-04-21 | 2022-05-16 | 2022-08-08 | 2022-08-25 | 71
0 | EDCDPI1325 | DATA SHEETS FOR IDBB VALVES - IFA | 15 | 2022-04-22 | 2022-05-18 | 2022-08-09 | 2022-08-29 | 71
0 | EDCDPI1580 | DATA SHEETS ITEMIZED PIPE SUPPORTS (SPRINGS/ SLIDING PLATES) - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-09-20 | 2022-10-03 | 89
0 | EDCDPI1340 | DATA SHEETS PIPING SPECIALTY ITEMS - IFA | 15 | 2022-05-11 | 2022-06-01 | 2022-08-25 | 2022-09-14 | 73
0 | EDCDPI1270 | DATA SHEETS FOR BALL VALVES - IFC | 20 | 2022-05-20 | 2022-06-17 | 2022-09-06 | 2022-10-03 | 74
0 | EDCDPI1300 | DATA SHEETS FOR CHECK VALVES - IFC | 20 | 2022-05-23 | 2022-06-20 | 2022-08-30 | 2022-09-26 | 68
0 | EDCDPI1590 | DATA SHEETS ITEMIZED PIPE SUPPORTS (SPRINGS/ SLIDING PLATES) - IFC | 10 | 2022-06-10 | 2022-06-24 | 2022-10-18 | 2022-10-31 | 89
0 | EDCDPI1315 | DATA SHEETS FOR GATE, GLOBE & PISTON LIFT CHECK VALVES - IFC | 19 | 2022-05-31 | 2022-06-27 | 2022-09-09 | 2022-10-05 | 70
0 | EDCDPI1330 | DATA SHEETS FOR IDBB VALVES - IFC | 20 | 2022-06-01 | 2022-06-29 | 2022-09-22 | 2022-10-19 | 78
0 | EDCDPI1345 | DATA SHEETS PIPING SPECIALTY ITEMS- IFC | 15 | 2022-06-15 | 2022-07-06 | 2022-09-29 | 2022-10-19 | 73
0 | EDCDPI1285 | DATA SHEETS FOR BUTTEFLY VALVES - IFC | 15 | 2022-06-15 | 2022-07-06 | 2022-09-22 | 2022-10-12 | 68
REPORTS & CALCULATIONS / STANDARDS |  |  | 111 | 2022-01-26 | 2022-07-05 | 2022-04-04 | 2022-11-02 | 84
0 | EDCDPI1350 | LAYOUT PHILOSOPHY AND DESIGN CRITERIA - ICR | 10 | 2022-01-26 | 2022-02-09 | 2022-04-04 | 2022-04-15 | 48
0 | EDCDPI1380 | MECHANICAL HANDLING PHILOSOPHY - ICR | 10 | 2022-02-02 | 2022-02-16 | 2022-04-27 | 2022-05-13 | 60
0 | EDCDPI1355 | LAYOUT PHILOSOPHY AND DESIGN CRITERIA - IFA | 11 | 2022-02-23 | 2022-03-10 | 2022-05-05 | 2022-05-19 | 48
0 | EDCDPI1385 | MECHANICAL HANDLING PHILOSOPHY - IFA | 10 | 2022-03-02 | 2022-03-16 | 2022-05-30 | 2022-06-10 | 60
0 | EDCDPI1365 | PIPE WALL THICKNESS CALCULATION - ICR | 10 | 2022-03-03 | 2022-03-17 | 2022-06-27 | 2022-07-13 | 79
0 | EDCDPI1750 | VALVE LIST - IFI | 10 | 2022-03-15 | 2022-03-29 | 2022-06-20 | 2022-07-01 | 66
0 | EDCDPI1395 | PIPE SUPPORT STANDARD - ICR | 19 | 2022-03-17 | 2022-04-13 | 2022-06-20 | 2022-07-19 | 64
0 | EDCDPI1360 | LAYOUT PHILOSOPHY AND DESIGN CRITERIA - IFC | 15 | 2022-03-24 | 2022-04-14 | 2022-06-03 | 2022-06-23 | 48
0 | EDCDPI1370 | PIPE WALL THICKNESS CALCULATION - IFA | 10 | 2022-03-31 | 2022-04-14 | 2022-07-28 | 2022-08-10 | 79
0 | EDCDPI1720 | ACCESSIBILITY REPORT TO INSPECTION & CORROSION MONITORING LOCATION - ICR | 10 | 2022-04-04 | 2022-04-18 | 2022-08-11 | 2022-08-24 | 87
0 | EDCDPI1390 | MECHANICAL HANDLING PHILOSOPHY - IFC | 17 | 2022-03-30 | 2022-04-22 | 2022-06-27 | 2022-07-22 | 60
0 | EDCDPI1410 | PIPING CONSTRUCTION STANDARD - ICR | 20 | 2022-03-25 | 2022-04-22 | 2022-06-28 | 2022-07-28 | 64
0 | EDCDPI1755 | VALVE LIST - IFC | 10 | 2022-04-12 | 2022-04-26 | 2022-07-21 | 2022-08-03 | 66
0 | EDCDPI1400 | PIPE SUPPORT STANDARD - IFA | 10 | 2022-04-27 | 2022-05-16 | 2022-08-25 | 2022-09-07 | 80
0 | EDCDPI1730 | ACCESSIBILITY REPORT TO INSPECTION & CORROSION MONITORING LOCATION - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-09-08 | 2022-09-21 | 87
0 | EDCDPI1415 | PIPING CONSTRUCTION STANDARD - IFA | 9 | 2022-05-11 | 2022-05-24 | 2022-08-31 | 2022-09-12 | 77
0 | EDCDPI1375 | PIPE WALL THICKNESS CALCULATION - IFC | 16 | 2022-04-28 | 2022-05-25 | 2022-10-12 | 2022-11-02 | 113
0 | EDCDPI1740 | ACCESSIBILITY REPORT TO INSPECTION & CORROSION MONITORING LOCATION - IFC | 10 | 2022-06-02 | 2022-06-16 | 2022-10-06 | 2022-10-19 | 87
0 | EDCDPI1405 | PIPE SUPPORT STANDARD - IFC | 20 | 2022-05-30 | 2022-06-27 | 2022-09-22 | 2022-10-19 | 80
0 | EDCDPI1420 | PIPING CONSTRUCTION STANDARD - IFC | 20 | 2022-06-07 | 2022-07-05 | 2022-09-27 | 2022-10-24 | 77
3D MODELING |  |  | 133 | 2022-05-13 | 2022-11-21 | 2022-07-25 | 2023-01-24 | 45
30% MODEL REVIEW/REPORT |  |  | 4 | 2022-05-13 | 2022-05-19 | 2022-07-25 | 2022-07-28 | 48
0 | EDCDPI1445 | 30% MODEL REVIEW | 4 | 2022-05-13 | 2022-05-19 | 2022-07-25 | 2022-07-28 | 48
60% MODEL REVIEW/REPORT |  |  | 3 | 2022-08-17 | 2022-08-22 | 2022-10-20 | 2022-10-24 | 46
0 | EDCDPI1465 | 60% MODEL REVIEW | 3 | 2022-08-17 | 2022-08-22 | 2022-10-20 | 2022-10-24 | 46
90% MODEL REVIEW/REPORT |  |  | 4 | 2022-11-15 | 2022-11-21 | 2023-01-19 | 2023-01-24 | 45
0 | EDCDPI1485 | 90% MODEL REVIEW | 4 | 2022-11-15 | 2022-11-21 | 2023-01-19 | 2023-01-24 | 45
REQUISITIONS |  |  | 148 | 2022-03-10 | 2022-10-12 | 2022-07-01 | 2023-01-24 | 73
BALL VALVES (CS/LTCS/CRA) |  |  | 86 | 2022-03-22 | 2022-07-28 | 2022-07-04 | 2022-11-23 | 85
REQUISITIONS |  |  | 53 | 2022-03-22 | 2022-06-08 | 2022-07-04 | 2022-09-22 | 74
0 | EDCMPI1000 | BALL VALVES (CS/LTCS/CRA/CS-CLADDED) - ISSUE MR - ICR | 10 | 2022-03-22 | 2022-04-05 | 2022-07-04 | 2022-07-20 | 71
0 | EDCMPI1005 | BALL VALVES (CS/LTCS/CRA/CS-CLADDED) - ISSUE MR - IFA | 10 | 2022-04-19 | 2022-05-06 | 2022-08-12 | 2022-08-25 | 77
0 | EDCMPI1010 | BALL VALVES (CS/LTCS/CRA/CS-CLADDED) - ISSUE MR - IFC | 10 | 2022-05-25 | 2022-06-08 | 2022-09-09 | 2022-09-22 | 74
TBE |  |  | 56 | 2022-05-06 | 2022-07-28 | 2022-08-19 | 2022-11-23 | 85
0 | EDCMPI2010 | COMPLETE EVALUATION AND SUBMIT TBE - BALL VALVES (CS/LTCS/ CLADDED) - ICR | 15 | 2022-05-06 | 2022-05-27 | 2022-08-19 | 2022-09-08 | 72
0 | EDCMPI2015 | RECEIVE TBE COMPANY APPROVAL - BALL VALVES (CS/LTCS/ CLADDED) | 10 | 2022-06-10 | 2022-06-24 | 2022-09-27 | 2022-10-10 | 74
0 | EDCMPI2020 | ISSUE TBE - BALL VALVES (CS/LTCS/ CLADDED) - IFC | 11 | 2022-07-13 | 2022-07-28 | 2022-11-09 | 2022-11-23 | 85
BALL VALVES (API 6A) |  |  | 92 | 2022-03-21 | 2022-08-04 | 2022-07-01 | 2022-11-28 | 83
REQUISITIONS |  |  | 51 | 2022-03-21 | 2022-06-03 | 2022-07-01 | 2022-09-22 | 77
0 | EDCMPI1015 | API 6A BALL VALVES - ISSUE MR - ICR | 10 | 2022-03-21 | 2022-04-04 | 2022-07-01 | 2022-07-19 | 71
0 | EDCMPI1020 | API 6A BALL VALVES - ISSUE MR - IFA | 10 | 2022-04-18 | 2022-05-05 | 2022-08-17 | 2022-08-30 | 81
0 | EDCMPI1025 | API 6A BALL VALVES - ISSUE MR - IFC | 7 | 2022-05-25 | 2022-06-03 | 2022-09-14 | 2022-09-22 | 77
TBE |  |  | 56 | 2022-05-13 | 2022-08-04 | 2022-09-02 | 2022-11-28 | 83
0 | EDCMPI2030 | COMPLETE EVALUATION AND SUBMIT TBE - BALL VALVES (API 6A) - ICR | 15 | 2022-05-13 | 2022-06-03 | 2022-09-02 | 2022-09-22 | 77
0 | EDCMPI2035 | RECEIVE TBE COMPANY APPROVAL - BALL VALVES (API 6A) | 10 | 2022-06-17 | 2022-07-01 | 2022-10-11 | 2022-10-24 | 79
0 | EDCMPI2040 | ISSUE TBE - BALL VALVES (API 6A) - IFC | 11 | 2022-07-20 | 2022-08-04 | 2022-11-14 | 2022-11-28 | 83
GATE VALVES (CS/LTCS/CRA) |  |  | 84 | 2022-03-31 | 2022-08-04 | 2022-07-13 | 2022-11-16 | 75
REQUISITIONS |  |  | 50 | 2022-03-31 | 2022-06-14 | 2022-07-13 | 2022-09-28 | 74
0 | EDCMPI1030 | GATE VALVES (CS/LTCS/CRA) - ISSUE MR - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-07-13 | 2022-07-26 | 68
0 | EDCMPI1035 | GATE VALVES (CS/LTCS/CRA) - ISSUE MR - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-08-18 | 2022-08-31 | 74
0 | EDCMPI1040 | GATE VALVES (CS/LTCS/CRA) - ISSUE MR - IFC | 10 | 2022-05-31 | 2022-06-14 | 2022-09-15 | 2022-09-28 | 74
TBE |  |  | 56 | 2022-05-13 | 2022-08-04 | 2022-08-25 | 2022-11-16 | 75
0 | EDCMPI2045 | COMPLETE EVALUATION AND SUBMIT TBE - GATE VALVES (CS/LTCS/CRA) - ICR | 15 | 2022-05-13 | 2022-06-03 | 2022-08-25 | 2022-09-14 | 71
0 | EDCMPI2050 | RECEIVE TBE COMPANY APPROVAL - GATE VALVES (CS/LTCS/CRA) | 10 | 2022-06-17 | 2022-07-01 | 2022-09-29 | 2022-10-12 | 71
0 | EDCMPI2055 | ISSUE TBE - GATE VALVES (CS/LTCS/CRA) - IFC | 11 | 2022-07-20 | 2022-08-04 | 2022-11-02 | 2022-11-16 | 75
GATE VALVES (API) |  |  | 84 | 2022-03-31 | 2022-08-04 | 2022-07-13 | 2022-11-11 | 72
REQUISITIONS |  |  | 50 | 2022-03-31 | 2022-06-14 | 2022-07-13 | 2022-09-23 | 71
0 | EDCMPI1045 | GATE VALVES (API) - ISSUE MR - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-07-13 | 2022-07-26 | 68
0 | EDCMPI1050 | GATE VALVES (API) - ISSUE MR - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-08-15 | 2022-08-26 | 71
0 | EDCMPI1055 | GATE VALVES (API) - ISSUE MR - IFC | 10 | 2022-05-31 | 2022-06-14 | 2022-09-12 | 2022-09-23 | 71
TBE |  |  | 56 | 2022-05-13 | 2022-08-04 | 2022-08-22 | 2022-11-11 | 72
0 | EDCMPI2060 | COMPLETE EVALUATION AND SUBMIT TBE - GATE VALVES (API) - ICR | 15 | 2022-05-13 | 2022-06-03 | 2022-08-22 | 2022-09-09 | 68
0 | EDCMPI2065 | RECEIVE TBE COMPANY APPROVAL - GATE VALVES (API) | 10 | 2022-06-17 | 2022-07-01 | 2022-09-28 | 2022-10-11 | 70
0 | EDCMPI2070 | ISSUE TBE - GATE VALVES (API) - IFC | 11 | 2022-07-20 | 2022-08-04 | 2022-10-28 | 2022-11-11 | 72
GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) |  |  | 86 | 2022-04-05 | 2022-08-11 | 2022-07-18 | 2022-11-23 | 75
REQUISITIONS |  |  | 50 | 2022-04-05 | 2022-06-17 | 2022-07-18 | 2022-10-06 | 77
0 | EDCMPI1060 | GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) - ISSUE MR - ICR | 10 | 2022-04-05 | 2022-04-19 | 2022-07-18 | 2022-07-29 | 68
0 | EDCMPI1065 | GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) - ISSUE MR - IFA | 10 | 2022-05-06 | 2022-05-20 | 2022-08-26 | 2022-09-08 | 77
0 | EDCMPI1070 | GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) - ISSUE MR - IFC | 10 | 2022-06-03 | 2022-06-17 | 2022-09-23 | 2022-10-06 | 77
TBE |  |  | 56 | 2022-05-20 | 2022-08-11 | 2022-09-01 | 2022-11-23 | 75
0 | EDCMPI2075 | COMPLETE EVALUATION AND SUBMIT TBE GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) - ICR | 15 | 2022-05-20 | 2022-06-10 | 2022-09-01 | 2022-09-21 | 71
0 | EDCMPI2080 | RECEIVE TBE COMPANY APPROVAL - GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) | 10 | 2022-06-24 | 2022-07-13 | 2022-10-10 | 2022-10-21 | 73
0 | EDCMPI2085 | ISSUE TBE - GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) - IFC | 11 | 2022-07-27 | 2022-08-11 | 2022-11-09 | 2022-11-23 | 75
GLOBE, PISTON LIFT CHECK VALVES (API) |  |  | 84 | 2022-04-05 | 2022-08-09 | 2022-07-22 | 2022-11-23 | 77
REQUISITIONS |  |  | 50 | 2022-04-05 | 2022-06-17 | 2022-07-22 | 2022-10-05 | 76
0 | EDCMPI1075 | GLOBE, PISTON LIFT CHECK VALVES (API) - ISSUE MR - ICR | 10 | 2022-04-05 | 2022-04-19 | 2022-07-22 | 2022-08-04 | 72
0 | EDCMPI1080 | GLOBE, PISTON LIFT CHECK VALVES (API) - ISSUE MR - IFA | 10 | 2022-05-06 | 2022-05-20 | 2022-08-25 | 2022-09-07 | 76
0 | EDCMPI1085 | GLOBE, PISTON LIFT CHECK VALVES (API) - ISSUE MR - IFC | 10 | 2022-06-03 | 2022-06-17 | 2022-09-22 | 2022-10-05 | 76
TBE |  |  | 56 | 2022-05-18 | 2022-08-09 | 2022-08-31 | 2022-11-23 | 77
0 | EDCMPI2090 | COMPLETE EVALUATION AND SUBMIT TBE GLOBE, PISTON LIFT CHECK VALVES (API) - ICR | 15 | 2022-05-18 | 2022-06-08 | 2022-08-31 | 2022-09-20 | 72
0 | EDCMPI2095 | RECEIVE TBE COMPANY APPROVAL - GLOBE, PISTON LIFT CHECK VALVES (API) | 10 | 2022-06-22 | 2022-07-06 | 2022-10-07 | 2022-10-20 | 74
0 | EDCMPI2098 | ISSUE TBE - GLOBE, PISTON LIFT CHECK VALVES (API) - IFC | 11 | 2022-07-25 | 2022-08-09 | 2022-11-09 | 2022-11-23 | 77
IDBB VALVES (CS/LTCS/CRA) |  |  | 89 | 2022-03-29 | 2022-08-09 | 2022-07-06 | 2022-11-21 | 75
REQUISITIONS |  |  | 50 | 2022-03-29 | 2022-06-10 | 2022-07-06 | 2022-09-22 | 72
0 | EDCMPI1090 | IDBB VALVES (CS/LTCS/CRA/CRA) - ISSUE MR - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-07-06 | 2022-07-22 | 68
0 | EDCMPI1095 | IDBB VALVES (CS/LTCS/CRA/CRA) - ISSUE MR - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-08-12 | 2022-08-25 | 72
0 | EDCMPI1100 | IDBB VALVES (CS/LTCS/CRA/CRA) - ISSUE MR - IFC | 10 | 2022-05-27 | 2022-06-10 | 2022-09-09 | 2022-09-22 | 72
TBE |  |  | 56 | 2022-05-18 | 2022-08-09 | 2022-08-30 | 2022-11-21 | 75
0 | EDCMPI2003 | COMPLETE EVALUATION AND SUBMIT TBE - IDBB VALVES (CS/LTCS/CRA) - ICR | 15 | 2022-05-18 | 2022-06-08 | 2022-08-30 | 2022-09-19 | 71
0 | EDCMPI2008 | RECEIVE TBE COMPANY APPROVAL - IDBB VALVES (CS/LTCS/CRA) | 10 | 2022-06-22 | 2022-07-06 | 2022-10-06 | 2022-10-19 | 73
0 | EDCMPI2012 | ISSUE TBE - IDBB VALVES (CS/LTCS/CRA) - IFC | 11 | 2022-07-25 | 2022-08-09 | 2022-11-07 | 2022-11-21 | 75
IDBB VALVES (API 6A) |  |  | 81 | 2022-03-28 | 2022-07-27 | 2022-07-05 | 2022-11-09 | 76
REQUISITIONS |  |  | 47 | 2022-03-28 | 2022-06-06 | 2022-07-05 | 2022-09-19 | 73
0 | EDCMPI1105 | IDBB VALVES - ISSUE MR - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-07-05 | 2022-07-21 | 68
0 | EDCMPI1110 | IDBB VALVES - ISSUE MR - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-08-12 | 2022-08-25 | 73
0 | EDCMPI1115 | IDBB VALVES - ISSUE MR - IFC | 7 | 2022-05-26 | 2022-06-06 | 2022-09-09 | 2022-09-19 | 73
TBE |  |  | 51 | 2022-05-12 | 2022-07-27 | 2022-08-25 | 2022-11-09 | 76
0 | EDCMPI2100 | COMPLETE EVALUATION AND SUBMIT TBE - IDBB VALVES (API 6A) - ICR | 10 | 2022-05-12 | 2022-05-26 | 2022-08-25 | 2022-09-07 | 72
0 | EDCMPI2105 | RECEIVE TBE COMPANY APPROVAL - IDBB VALVES (API 6A) | 10 | 2022-06-09 | 2022-06-23 | 2022-09-26 | 2022-10-07 | 74
0 | EDCMPI2110 | ISSUE TBE - IDBB VALVES (API 6A) - IFC | 11 | 2022-07-07 | 2022-07-27 | 2022-10-26 | 2022-11-09 | 76
BUTTEFLY VALVES |  |  | 76 | 2022-04-08 | 2022-08-02 | 2022-07-26 | 2022-11-14 | 75
REQUISITIONS |  |  | 45 | 2022-04-08 | 2022-06-15 | 2022-07-26 | 2022-09-27 | 72
0 | EDCMPI1120 | BUTTEFLY VALVES - ISSUE MR - ICR | 5 | 2022-04-08 | 2022-04-15 | 2022-07-26 | 2022-08-01 | 71
0 | EDCMPI1125 | BUTTEFLY VALVES - ISSUE MR - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-08-17 | 2022-08-30 | 72
0 | EDCMPI1130 | BUTTEFLY VALVES - ISSUE MR - IFC | 10 | 2022-06-01 | 2022-06-15 | 2022-09-14 | 2022-09-27 | 72
TBE |  |  | 56 | 2022-05-11 | 2022-08-02 | 2022-08-23 | 2022-11-14 | 75
0 | EDCMPI2115 | COMPLETE EVALUATION AND SUBMIT TBE - BUTTERFLY VALVES - ICR | 15 | 2022-05-11 | 2022-06-01 | 2022-08-23 | 2022-09-12 | 71
0 | EDCMPI2120 | RECEIVE TBE COMPANY APPROVAL - BUTTERFLY VALVES | 10 | 2022-06-15 | 2022-06-29 | 2022-09-29 | 2022-10-12 | 73
0 | EDCMPI2125 | ISSUE TBE - BUTTERFLY VALVES - IFC | 11 | 2022-07-18 | 2022-08-02 | 2022-10-31 | 2022-11-14 | 75
SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) |  |  | 81 | 2022-04-06 | 2022-08-05 | 2022-07-19 | 2022-11-14 | 72
REQUISITIONS |  |  | 50 | 2022-04-06 | 2022-06-20 | 2022-07-19 | 2022-09-27 | 69
0 | EDCMPI1135 | SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) - ISSUE MR - ICR | 10 | 2022-04-06 | 2022-04-20 | 2022-07-19 | 2022-08-01 | 68
0 | EDCMPI1140 | SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) - ISSUE MR - IFA | 10 | 2022-05-09 | 2022-05-23 | 2022-08-17 | 2022-08-30 | 69
0 | EDCMPI1145 | SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) - ISSUE MR - IFC | 10 | 2022-06-06 | 2022-06-20 | 2022-09-14 | 2022-09-27 | 69
TBE |  |  | 56 | 2022-05-16 | 2022-08-05 | 2022-08-23 | 2022-11-14 | 72
0 | EDCMPI2130 | COMPLETE EVALUATION AND SUBMIT TBE - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) - ICR | 15 | 2022-05-16 | 2022-06-06 | 2022-08-23 | 2022-09-12 | 68
0 | EDCMPI2135 | RECEIVE TBE COMPANY APPROVAL - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 10 | 2022-06-20 | 2022-07-04 | 2022-09-29 | 2022-10-12 | 70
0 | EDCMPI2140 | ISSUE TBE - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) - IFC | 11 | 2022-07-21 | 2022-08-05 | 2022-10-31 | 2022-11-14 | 72
SWING CHECK VALVES (API) |  |  | 86 | 2022-04-01 | 2022-08-09 | 2022-07-14 | 2022-11-21 | 75
REQUISITIONS |  |  | 50 | 2022-04-01 | 2022-06-15 | 2022-07-14 | 2022-10-03 | 76
0 | EDCMPI1150 | SWING CHECK VALVES (API) - ISSUE MR - ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-07-14 | 2022-07-27 | 68
0 | EDCMPI1155 | SWING CHECK VALVES (API) - ISSUE MR - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-08-23 | 2022-09-05 | 76
0 | EDCMPI1160 | SWING CHECK VALVES (API) - ISSUE MR - IFC | 10 | 2022-06-01 | 2022-06-15 | 2022-09-20 | 2022-10-03 | 76
TBE |  |  | 56 | 2022-05-18 | 2022-08-09 | 2022-08-29 | 2022-11-21 | 75
0 | EDCMPI2145 | COMPLETE EVALUATION AND SUBMIT TBE - SWING CHECK VALVES (API) - ICR | 15 | 2022-05-18 | 2022-06-08 | 2022-08-29 | 2022-09-16 | 70
0 | EDCMPI2150 | RECEIVE TBE COMPANY APPROVAL - SWING CHECK VALVES (API) | 10 | 2022-06-22 | 2022-07-06 | 2022-10-05 | 2022-10-18 | 72
0 | EDCMPI2160 | ISSUE TBE - SWING CHECK VALVES (API) - IFC | 11 | 2022-07-25 | 2022-08-09 | 2022-11-07 | 2022-11-21 | 75
DUAL PLATE CHECK VALVES (CS/LTCS/CRA/CLADDED) |  |  | 81 | 2022-04-05 | 2022-08-04 | 2022-07-18 | 2022-11-11 | 72
REQUISITIONS |  |  | 50 | 2022-04-05 | 2022-06-17 | 2022-07-18 | 2022-09-26 | 69
0 | EDCMPI1435 | DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) - ISSUE MR - ICR | 10 | 2022-04-05 | 2022-04-19 | 2022-07-18 | 2022-07-29 | 68
0 | EDCMPI1440 | DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) - ISSUE MR - IFA | 10 | 2022-05-06 | 2022-05-20 | 2022-08-16 | 2022-08-29 | 69
0 | EDCMPI1445 | DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) - ISSUE MR - IFC | 10 | 2022-06-03 | 2022-06-17 | 2022-09-13 | 2022-09-26 | 69
TBE |  |  | 56 | 2022-05-13 | 2022-08-04 | 2022-08-22 | 2022-11-11 | 72
0 | EDCMPI2165 | COMPLETE EVALUATION AND SUBMIT TBE - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) - ICR | 15 | 2022-05-13 | 2022-06-03 | 2022-08-22 | 2022-09-09 | 68
0 | EDCMPI2170 | RECEIVE TBE COMPANY APPROVAL - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 10 | 2022-06-17 | 2022-07-01 | 2022-09-28 | 2022-10-11 | 70
0 | EDCMPI2175 | ISSUE TBE - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) - IFC | 11 | 2022-07-20 | 2022-08-04 | 2022-10-28 | 2022-11-11 | 72
DUAL PLATE CHECK VALVES (API) |  |  | 80 | 2022-04-06 | 2022-08-04 | 2022-07-19 | 2022-11-16 | 75
REQUISITIONS |  |  | 50 | 2022-04-06 | 2022-06-20 | 2022-07-19 | 2022-09-26 | 68
0 | EDCMPI1450 | DUAL PLATE CHECK VALVES (API) - ISSUE MR - ICR | 10 | 2022-04-06 | 2022-04-20 | 2022-07-19 | 2022-08-01 | 68
0 | EDCMPI1455 | DUAL PLATE CHECK VALVES (API) - ISSUE MR - IFA | 10 | 2022-05-09 | 2022-05-23 | 2022-08-16 | 2022-08-29 | 68
0 | EDCMPI1460 | DUAL PLATE CHECK VALVES (API) - ISSUE MR - IFC | 10 | 2022-06-06 | 2022-06-20 | 2022-09-13 | 2022-09-26 | 68
TBE |  |  | 55 | 2022-05-16 | 2022-08-04 | 2022-08-25 | 2022-11-16 | 75
0 | EDCMPI2180 | COMPLETE EVALUATION AND SUBMIT TBE - DUAL PLATE CHECK VALVES (API) - ICR | 15 | 2022-05-16 | 2022-06-06 | 2022-08-25 | 2022-09-14 | 70
0 | EDCMPI2185 | RECEIVE TBE COMPANY APPROVAL - DUAL PLATE CHECK VALVES (API) | 10 | 2022-06-20 | 2022-07-04 | 2022-10-03 | 2022-10-14 | 72
0 | EDCMPI2190 | ISSUE TBE - DUAL PLATE CHECK VALVES (API) - IFC | 10 | 2022-07-21 | 2022-08-04 | 2022-11-03 | 2022-11-16 | 75
PIPES CS & LTCS/CRA |  |  | 64 | 2022-03-11 | 2022-06-14 | 2022-07-13 | 2022-11-02 | 99
REQUISITIONS |  |  | 50 | 2022-03-11 | 2022-05-25 | 2022-07-13 | 2022-10-19 | 103
0 | EDCMPI1285 | PIPES CS & LTCS/CRA - ISSUE MR - ICR | 5 | 2022-03-11 | 2022-03-18 | 2022-07-13 | 2022-07-19 | 82
0 | EDCMPI1290 | PIPES CS & LTCS/CRA - ISSUE MR - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-09-15 | 2022-09-28 | 113
0 | EDCMPI1295 | PIPES CS & LTCS/CRA - ISSUE MR - IFC | 5 | 2022-05-18 | 2022-05-25 | 2022-10-13 | 2022-10-19 | 103
TBE |  |  | 50 | 2022-03-31 | 2022-06-14 | 2022-07-28 | 2022-11-02 | 99
0 | EDCMPI2195 | COMPLETE EVALUATION AND SUBMIT TBE - PIPES CS & LTCS/CRA - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-07-28 | 2022-08-10 | 79
0 | EDCMPI2200 | RECEIVE TBE COMPANY APPROVAL - PIPES CS & LTCS/CRA | 10 | 2022-04-28 | 2022-05-17 | 2022-08-25 | 2022-09-07 | 79
0 | EDCMPI2205 | ISSUE TBE - PIPES CS & LTCS/CRA - IFC | 10 | 2022-05-31 | 2022-06-14 | 2022-10-20 | 2022-11-02 | 99
PIPE & FITTINGS CLADDED SERVICE |  |  | 66 | 2022-03-11 | 2022-06-16 | 2022-07-21 | 2022-10-28 | 94
REQUISITIONS |  |  | 55 | 2022-03-11 | 2022-06-01 | 2022-07-21 | 2022-10-13 | 94
0 | EDCMPI1315 | PIPES & FITINGS CLADDED SERVICE - ISSUE MR - ICR | 5 | 2022-03-11 | 2022-03-18 | 2022-07-21 | 2022-07-27 | 88
0 | EDCMPI1320 | PIPES & FITINGS CLADDED SERVICE - ISSUE MR - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-08-11 | 2022-08-24 | 88
0 | EDCMPI1325 | PIPES & FITINGS CLADDED SERVICE - ISSUE MR - IFC | 5 | 2022-05-25 | 2022-06-01 | 2022-10-07 | 2022-10-13 | 94
TBE |  |  | 51 | 2022-04-01 | 2022-06-16 | 2022-08-11 | 2022-10-28 | 94
0 | EDCMPI2210 | COMPLETE EVALUATION AND SUBMIT TBE - PIPES & FITINGS CLADDED SERVICED - ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-08-11 | 2022-08-24 | 88
0 | EDCMPI2215 | RECEIVE TBE COMPANY APPROVAL - PIPES & FITINGS CLADDED SERVICE | 10 | 2022-04-29 | 2022-05-18 | 2022-09-12 | 2022-09-23 | 90
0 | EDCMPI2220 | ISSUE TBE - PIPES & FITINGS CLADDED SERVICE - IFC | 11 | 2022-06-01 | 2022-06-16 | 2022-10-14 | 2022-10-28 | 94
FLANGES CS/ LTCS/CRA & CLADDED |  |  | 66 | 2022-03-11 | 2022-06-16 | 2022-07-21 | 2022-10-28 | 94
REQUISITIONS |  |  | 55 | 2022-03-11 | 2022-06-01 | 2022-07-21 | 2022-10-13 | 94
0 | EDCMPI1345 | FLANGES CS, LTCS/CRA & CS-CLADDED - ISSUE MR - ICR | 5 | 2022-03-11 | 2022-03-18 | 2022-07-21 | 2022-07-27 | 88
0 | EDCMPI1350 | FLANGES CS, LTCS/CRA & CS-CLADDED - ISSUE MR - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-08-11 | 2022-08-24 | 88
0 | EDCMPI1355 | FLANGES CS, LTCS/CRA & CS-CLADDED - ISSUE MR - IFC | 5 | 2022-05-25 | 2022-06-01 | 2022-10-07 | 2022-10-13 | 94
TBE |  |  | 46 | 2022-04-08 | 2022-06-16 | 2022-08-18 | 2022-10-28 | 94
0 | EDCMPI2225 | COMPLETE EVALUATION AND SUBMIT TBE - FLANGES CS, LTCS /CRA & CS CLADDED - ICR | 5 | 2022-04-08 | 2022-04-15 | 2022-08-18 | 2022-08-24 | 88
0 | EDCMPI2230 | RECEIVE TBE COMPANY APPROVAL - FLANGES CS, LTCS /CRA & CS CLADDED | 10 | 2022-04-29 | 2022-05-18 | 2022-09-12 | 2022-09-23 | 90
0 | EDCMPI2235 | ISSUE TBE - FLANGES CS, LTCS /CRA & CS CLADDED - IFC | 11 | 2022-06-01 | 2022-06-16 | 2022-10-14 | 2022-10-28 | 94
FORGED FITTINGS CS, LTCS/CRA |  |  | 67 | 2022-03-10 | 2022-06-16 | 2022-07-21 | 2022-10-28 | 94
REQUISITIONS |  |  | 56 | 2022-03-10 | 2022-06-01 | 2022-07-21 | 2022-10-13 | 94
0 | EDCMPI1330 | FORGED FITTINGS CS, LTCS/CRA - ISSUE MR - ICR | 5 | 2022-03-10 | 2022-03-17 | 2022-07-21 | 2022-07-27 | 89
0 | EDCMPI1335 | FORGED FITTINGS CS, LTCS/CRA - ISSUE MR - IFA | 10 | 2022-03-31 | 2022-04-14 | 2022-08-11 | 2022-08-24 | 89
0 | EDCMPI1340 | FORGED FITTINGS CS, LTCS/CRA - ISSUE MR - IFC | 5 | 2022-05-25 | 2022-06-01 | 2022-10-07 | 2022-10-13 | 94
TBE |  |  | 47 | 2022-04-07 | 2022-06-16 | 2022-08-18 | 2022-10-28 | 94
0 | EDCMPI2240 | COMPLETE EVALUATION AND SUBMIT TBE - FORGED FITTINGS CS, LTCS/CRA - ICR | 5 | 2022-04-07 | 2022-04-14 | 2022-08-18 | 2022-08-24 | 89
0 | EDCMPI2245 | RECEIVE TBE COMPANY APPROVAL - FORGED FITTINGS CS, LTCS/CRA | 10 | 2022-04-28 | 2022-05-17 | 2022-09-12 | 2022-09-23 | 91
0 | EDCMPI2250 | ISSUE TBE - FORGED FITTINGS CS, LTCS/CRA - IFC | 11 | 2022-06-01 | 2022-06-16 | 2022-10-14 | 2022-10-28 | 94
BUTT WELD FITTINGS CS, LTCS/CRA |  |  | 66 | 2022-03-10 | 2022-06-15 | 2022-07-14 | 2022-10-21 | 90
REQUISITIONS |  |  | 40 | 2022-03-10 | 2022-05-10 | 2022-07-14 | 2022-10-06 | 105
0 | EDCMPI1465 | BUTT WELD FITTINGS CS, LTCS/CRA - ISSUE MR - ICR | 5 | 2022-03-10 | 2022-03-17 | 2022-07-14 | 2022-07-20 | 84
0 | EDCMPI1470 | BUTT WELD FITTINGS CS, LTCS/CRA - ISSUE MR - IFA | 10 | 2022-03-31 | 2022-04-14 | 2022-08-04 | 2022-08-17 | 84
0 | EDCMPI1475 | BUTT WELD FITTINGS CS, LTCS/CRA - ISSUE MR - IFC | 5 | 2022-04-28 | 2022-05-10 | 2022-09-30 | 2022-10-06 | 105
TBE |  |  | 46 | 2022-04-07 | 2022-06-15 | 2022-08-11 | 2022-10-21 | 90
0 | EDCMPI2255 | COMPLETE EVALUATION AND SUBMIT TBE - BUTT WELD FITTINGS CS, LTCS/CRA - ICR | 5 | 2022-04-07 | 2022-04-14 | 2022-08-11 | 2022-08-17 | 84
0 | EDCMPI2260 | RECEIVE TBE COMPANY APPROVAL - BUTT WELD FITTINGS CS, LTCS/CRA | 10 | 2022-04-28 | 2022-05-17 | 2022-09-05 | 2022-09-16 | 86
0 | EDCMPI2265 | ISSUE TBE - BUTT WELD FITTINGS CS, LTCS/CRA - IFC | 11 | 2022-05-31 | 2022-06-15 | 2022-10-07 | 2022-10-21 | 90
CU-NI PIPE FITTINGS AND FLANGES |  |  | 71 | 2022-03-18 | 2022-06-30 | 2022-07-21 | 2022-10-28 | 84
REQUISITIONS |  |  | 45 | 2022-03-18 | 2022-05-25 | 2022-07-21 | 2022-09-30 | 90
0 | EDCMPI1405 | CU-NI PIPE FITTINGS AND FLANGES - ISSUE MR -ICR | 5 | 2022-03-18 | 2022-03-25 | 2022-07-21 | 2022-07-27 | 83
0 | EDCMPI1410 | CU-NI PIPE FITTINGS AND FLANGES - ISSUE MR -IFA | 10 | 2022-04-08 | 2022-04-22 | 2022-08-18 | 2022-08-31 | 88
0 | EDCMPI1415 | CU-NI PIPE FITTINGS AND FLANGES - ISSUE MR -IFC | 10 | 2022-05-11 | 2022-05-25 | 2022-09-19 | 2022-09-30 | 90
TBE |  |  | 51 | 2022-04-15 | 2022-06-30 | 2022-08-18 | 2022-10-28 | 84
0 | EDCMPI2270 | COMPLETE EVALUATION AND SUBMIT TBE - CU-NI PIPES FITTINGS AND FLANGES - ICR | 10 | 2022-04-15 | 2022-04-29 | 2022-08-18 | 2022-08-31 | 83
0 | EDCMPI2275 | RECEIVE TBE COMPANY APPROVAL - CU-NI PIPES FITTINGS AND FLANGES | 10 | 2022-05-18 | 2022-06-01 | 2022-09-16 | 2022-09-29 | 84
0 | EDCMPI2280 | ISSUE TBE - CU-NI PIPES FITTINGS AND FLANGES - IFC | 11 | 2022-06-15 | 2022-06-30 | 2022-10-14 | 2022-10-28 | 84
PIPE SUPPORT MATERIAL |  |  | 80 | 2022-04-26 | 2022-08-24 | 2022-08-22 | 2022-12-13 | 78
REQUISITIONS |  |  | 42 | 2022-04-26 | 2022-06-28 | 2022-08-22 | 2022-10-31 | 87
0 | EDCMPI1390 | PIPE SUPPORT MATERIAL - ISSUE MR - ICR | 4 | 2022-04-26 | 2022-05-05 | 2022-08-22 | 2022-08-25 | 78
0 | EDCMPI1395 | PIPE SUPPORT MATERIAL - ISSUE MR - IFA | 9 | 2022-05-19 | 2022-06-01 | 2022-09-22 | 2022-10-04 | 87
0 | EDCMPI1400 | PIPE SUPPORT MATERIAL - ISSUE MR - IFC | 9 | 2022-06-15 | 2022-06-28 | 2022-10-19 | 2022-10-31 | 87
TBE |  |  | 56 | 2022-06-02 | 2022-08-24 | 2022-09-23 | 2022-12-13 | 78
0 | EDCMPI2285 | COMPLETE EVALUATION AND SUBMIT TBE - PIPE SUPPORT MATERIALS - ICR | 15 | 2022-06-02 | 2022-06-23 | 2022-09-23 | 2022-10-13 | 78
0 | EDCMPI2290 | RECEIVE TBE COMPANY APPROVAL - PIPE SUPPORT MATERIALS | 10 | 2022-07-07 | 2022-07-26 | 2022-10-28 | 2022-11-10 | 78
0 | EDCMPI2295 | ISSUE TBE - PIPE SUPPORT MATERIALS - IFC | 11 | 2022-08-09 | 2022-08-24 | 2022-11-25 | 2022-12-13 | 78
ACCESS FITTINGS AND CORROSION COUPON |  |  | 86 | 2022-04-22 | 2022-08-30 | 2022-08-10 | 2022-12-12 | 73
REQUISITIONS |  |  | 50 | 2022-04-22 | 2022-07-06 | 2022-08-10 | 2022-10-28 | 80
0 | EDCMPI1165 | ACCESS FITTINGS AND CORROSION COUPON - ISSUE MR - ICR | 10 | 2022-04-22 | 2022-05-11 | 2022-08-10 | 2022-08-23 | 72
0 | EDCMPI1170 | ACCESS FITTINGS AND CORROSION COUPON - ISSUE MR - IFA | 10 | 2022-05-25 | 2022-06-08 | 2022-09-19 | 2022-09-30 | 80
0 | EDCMPI1175 | ACCESS FITTINGS AND CORROSION COUPON - ISSUE MR - IFC | 10 | 2022-06-22 | 2022-07-06 | 2022-10-17 | 2022-10-28 | 80
TBE |  |  | 56 | 2022-06-08 | 2022-08-30 | 2022-09-22 | 2022-12-12 | 73
0 | EDCMPI2300 | COMPLETE EVALUATION AND SUBMIT TBE - ACCESS FITTINGS AND CORROSION COUPON - ICR | 15 | 2022-06-08 | 2022-06-29 | 2022-09-22 | 2022-10-12 | 73
0 | EDCMPI2310 | RECEIVE TBE COMPANY APPROVAL - ACCESS FITTINGS AND CORROSION COUPEN | 10 | 2022-07-18 | 2022-08-01 | 2022-10-27 | 2022-11-09 | 73
0 | EDCMPI2320 | ISSUE TBE - ACCESS FITTINGS AND CORROSION COUPEN - IFC | 11 | 2022-08-15 | 2022-08-30 | 2022-11-24 | 2022-12-12 | 73
INSULATING GASKET |  |  | 80 | 2022-04-26 | 2022-08-24 | 2022-08-12 | 2022-12-12 | 77
REQUISITIONS |  |  | 47 | 2022-04-26 | 2022-07-05 | 2022-08-12 | 2022-12-12 | 110
0 | EDCMPI1180 | INSULATING GASKET - ISSUE MR - ICR | 9 | 2022-04-26 | 2022-05-12 | 2022-08-12 | 2022-08-24 | 72
0 | EDCMPI1185 | INSULATING GASKET - ISSUE MR - IFA | 9 | 2022-05-26 | 2022-06-08 | 2022-11-01 | 2022-11-11 | 110
0 | EDCMPI1190 | INSULATING GASKET - ISSUE MR - IFC | 9 | 2022-06-22 | 2022-07-05 | 2022-11-28 | 2022-12-12 | 110
TBE |  |  | 56 | 2022-06-02 | 2022-08-24 | 2022-09-22 | 2022-12-12 | 77
0 | EDCMPI2330 | COMPLETE EVALUATION AND SUBMIT TBE - INSULATING GASKET - ICR | 15 | 2022-06-02 | 2022-06-23 | 2022-09-22 | 2022-10-12 | 77
0 | EDCMPI2335 | RECEIVE TBE COMPANY APPROVAL - INSULATING GASKET | 10 | 2022-07-07 | 2022-07-26 | 2022-10-27 | 2022-11-09 | 77
0 | EDCMPI2340 | ISSUE TBE - INSULATING GASKET - IFC | 11 | 2022-08-09 | 2022-08-24 | 2022-11-24 | 2022-12-12 | 77
STRAINER |  |  | 86 | 2022-04-27 | 2022-09-02 | 2022-08-15 | 2022-12-15 | 73
REQUISITIONS |  |  | 50 | 2022-04-27 | 2022-07-14 | 2022-08-15 | 2022-10-31 | 78
0 | EDCMPI1195 | STRAINER - ISSUE MR - ICR | 10 | 2022-04-27 | 2022-05-16 | 2022-08-15 | 2022-08-26 | 72
0 | EDCMPI1200 | STRAINER - ISSUE MR - IFA | 10 | 2022-05-30 | 2022-06-13 | 2022-09-20 | 2022-10-03 | 78
0 | EDCMPI1205 | STRAINER - ISSUE MR - IFC | 10 | 2022-06-27 | 2022-07-14 | 2022-10-18 | 2022-10-31 | 78
TBE |  |  | 56 | 2022-06-13 | 2022-09-02 | 2022-09-26 | 2022-12-15 | 73
0 | EDCMPI2345 | COMPLETE EVALUATION AND SUBMIT TBE - STRAINER - ICR | 15 | 2022-06-13 | 2022-07-04 | 2022-09-26 | 2022-10-14 | 72
0 | EDCMPI2350 | RECEIVE TBE COMPANY APPROVAL - STRAINER | 10 | 2022-07-21 | 2022-08-04 | 2022-11-01 | 2022-11-14 | 73
0 | EDCMPI2355 | ISSUE TBE - STRAINER - IFC | 11 | 2022-08-18 | 2022-09-02 | 2022-11-29 | 2022-12-15 | 73
BIRD SCREEN |  |  | 86 | 2022-04-29 | 2022-09-06 | 2022-08-18 | 2022-12-23 | 77
REQUISITIONS |  |  | 50 | 2022-04-29 | 2022-07-18 | 2022-08-18 | 2022-11-10 | 84
0 | EDCMPI1210 | BIRD SCREEN - ISSUE MR - ICR | 10 | 2022-04-29 | 2022-05-18 | 2022-08-18 | 2022-08-31 | 73
0 | EDCMPI1215 | BIRD SCREEN - ISSUE MR - IFA | 10 | 2022-06-01 | 2022-06-15 | 2022-09-30 | 2022-10-13 | 84
0 | EDCMPI1220 | BIRD SCREEN - ISSUE MR - IFC | 10 | 2022-06-29 | 2022-07-18 | 2022-10-28 | 2022-11-10 | 84
TBE |  |  | 56 | 2022-06-15 | 2022-09-06 | 2022-10-05 | 2022-12-23 | 77
0 | EDCMPI2360 | COMPLETE EVALUATION AND SUBMIT TBE - BIRD SCREEN - ICR | 15 | 2022-06-15 | 2022-07-06 | 2022-10-05 | 2022-10-25 | 77
0 | EDCMPI2365 | RECEIVE TBE COMPANY APPROVAL - BIRD SCREEN | 10 | 2022-07-25 | 2022-08-08 | 2022-11-09 | 2022-11-22 | 77
0 | EDCMPI2370 | ISSUE TBE - BIRD SCREEN | 11 | 2022-08-22 | 2022-09-06 | 2022-12-09 | 2022-12-23 | 77
VALVE INTERLOCK |  |  | 84 | 2022-05-06 | 2022-09-06 | 2022-08-22 | 2022-12-19 | 73
REQUISITIONS |  |  | 50 | 2022-05-06 | 2022-07-20 | 2022-08-22 | 2022-11-04 | 78
0 | EDCMPI1225 | VALVE INTERLOCK - ISSUE MR - ICR | 10 | 2022-05-06 | 2022-05-20 | 2022-08-22 | 2022-09-02 | 73
0 | EDCMPI1230 | VALVE INTERLOCK - ISSUE MR - IFA | 10 | 2022-06-03 | 2022-06-17 | 2022-09-26 | 2022-10-07 | 78
0 | EDCMPI1235 | VALVE INTERLOCK - ISSUE MR - IFC | 10 | 2022-07-01 | 2022-07-20 | 2022-10-24 | 2022-11-04 | 78
TBE |  |  | 56 | 2022-06-15 | 2022-09-06 | 2022-09-29 | 2022-12-19 | 73
0 | EDCMPI2375 | COMPLETE EVALUATION AND SUBMIT TBE - VALVE INTERLOCK - ICR | 15 | 2022-06-15 | 2022-07-06 | 2022-09-29 | 2022-10-19 | 73
0 | EDCMPI2380 | RECEIVE TBE COMPANY APPROVAL - VALVE INTERLOCK | 10 | 2022-07-25 | 2022-08-08 | 2022-11-03 | 2022-11-16 | 73
0 | EDCMPI2385 | ISSUE TBE - VALVE INTERLOCK | 11 | 2022-08-22 | 2022-09-06 | 2022-12-05 | 2022-12-19 | 73
FIRE WATER SPRAY NOZZLE |  |  | 57 | 2022-05-10 | 2022-08-02 | 2022-09-02 | 2022-11-21 | 80
REQUISITIONS |  |  | 50 | 2022-05-10 | 2022-07-22 | 2022-09-02 | 2022-11-21 | 87
0 | EDCMPI1240 | FIRE WATER SPRAY NOZZLE - ISSUE MR - ICR | 10 | 2022-05-10 | 2022-05-24 | 2022-09-02 | 2022-09-15 | 80
0 | EDCMPI1245 | FIRE WATER SPRAY NOZZLE - ISSUE MR - IFA | 10 | 2022-06-07 | 2022-06-21 | 2022-10-07 | 2022-10-20 | 85
0 | EDCMPI1250 | FIRE WATER SPRAY NOZZLE - ISSUE MR - IFC | 10 | 2022-07-05 | 2022-07-22 | 2022-11-08 | 2022-11-21 | 87
TBE |  |  | 32 | 2022-06-14 | 2022-08-02 | 2022-10-07 | 2022-11-21 | 80
0 | EDCMPI2390 | COMPLETE EVALUATION AND SUBMIT TBE - FIRE WATER SPRAY NOZZLE - ICR | 10 | 2022-06-14 | 2022-06-28 | 2022-10-07 | 2022-10-20 | 80
0 | EDCMPI2395 | RECEIVE TBE COMPANY APPROVAL - FIRE WATER SPRAY NOZZLE | 10 | 2022-06-28 | 2022-07-15 | 2022-10-24 | 2022-11-04 | 81
0 | EDCMPI2400 | ISSUE TBE - FIRE WATER SPRAY NOZZLE | 11 | 2022-07-18 | 2022-08-02 | 2022-11-07 | 2022-11-21 | 80
FLEXIBLE HOSE AND COUPLING |  |  | 69 | 2022-07-04 | 2022-10-12 | 2022-10-13 | 2023-01-24 | 73
REQUISITIONS |  |  | 40 | 2022-07-04 | 2022-09-01 | 2022-10-13 | 2022-12-12 | 71
0 | EDCMPI1255 | FLEXIBLE HOSE AND COUPLING - ISSUE MR - ICR | 5 | 2022-07-04 | 2022-07-14 | 2022-10-13 | 2022-10-19 | 70
0 | EDCMPI1260 | FLEXIBLE HOSE AND COUPLING - ISSUE MR - IFA | 10 | 2022-07-28 | 2022-08-11 | 2022-11-04 | 2022-11-17 | 71
0 | EDCMPI1265 | FLEXIBLE HOSE AND COUPLING - ISSUE MR - IFC | 5 | 2022-08-25 | 2022-09-01 | 2022-12-06 | 2022-12-12 | 71
TBE |  |  | 51 | 2022-08-02 | 2022-10-12 | 2022-11-10 | 2023-01-24 | 73
0 | EDCMPI2405 | COMPLETE EVALUATION AND SUBMIT TBE - FLEXIBLE HOSE AND COUPLING - ICR | 10 | 2022-08-02 | 2022-08-16 | 2022-11-10 | 2022-11-23 | 72
0 | EDCMPI2410 | RECEIVE TBE COMPANY APPROVAL - FLEXIBLE HOSE AND COUPLING | 10 | 2022-08-30 | 2022-09-13 | 2022-12-13 | 2022-12-26 | 73
0 | EDCMPI2415 | ISSUE TBE - FLEXIBLE HOSE AND COUPLING | 11 | 2022-09-27 | 2022-10-12 | 2023-01-10 | 2023-01-24 | 73
SIGHT GLASS |  |  | 68 | 2022-07-05 | 2022-10-12 | 2022-10-14 | 2023-01-20 | 71
REQUISITIONS |  |  | 40 | 2022-07-05 | 2022-09-02 | 2022-10-14 | 2022-12-23 | 79
0 | EDCMPI1270 | SIGHT GLASS - ISSUE MR - ICR | 5 | 2022-07-05 | 2022-07-15 | 2022-10-14 | 2022-10-20 | 70
0 | EDCMPI1275 | SIGHT GLASS - ISSUE MR - IFA | 10 | 2022-07-29 | 2022-08-12 | 2022-11-08 | 2022-11-21 | 72
0 | EDCMPI1280 | SIGHT GLASS - ISSUE MR - IFC | 5 | 2022-08-26 | 2022-09-02 | 2022-12-19 | 2022-12-23 | 79
TBE |  |  | 51 | 2022-08-02 | 2022-10-12 | 2022-11-08 | 2023-01-20 | 71
0 | EDCMPI2420 | COMPLETE EVALUATION AND SUBMIT TBE - SIGHT GLASS - ICR | 10 | 2022-08-02 | 2022-08-16 | 2022-11-08 | 2022-11-21 | 70
0 | EDCMPI2425 | RECEIVE TBE COMPANY APPROVAL - SIGHT GLASS | 10 | 2022-08-30 | 2022-09-13 | 2022-12-09 | 2022-12-22 | 71
0 | EDCMPI2430 | ISSUE TBE - SIGHT GLASS | 11 | 2022-09-27 | 2022-10-12 | 2023-01-06 | 2023-01-20 | 71
GASKETS |  |  | 84 | 2022-03-29 | 2022-08-02 | 2022-08-17 | 2022-11-30 | 87
REQUISITIONS |  |  | 50 | 2022-03-29 | 2022-06-10 | 2022-08-17 | 2022-10-27 | 97
0 | EDCMPI1360 | GASKETS - ISSUE MR - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-08-17 | 2022-08-30 | 95
0 | EDCMPI1365 | GASKETS - ISSUE MR - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-09-21 | 2022-10-04 | 100
0 | EDCMPI1370 | GASKETS - ISSUE MR - IFC | 5 | 2022-06-03 | 2022-06-10 | 2022-10-21 | 2022-10-27 | 97
TBE |  |  | 51 | 2022-05-18 | 2022-08-02 | 2022-09-21 | 2022-11-30 | 87
0 | EDCMPI2450 | COMPLETE EVALUATION AND SUBMIT TBE - GASKETS - ICR | 10 | 2022-05-18 | 2022-06-01 | 2022-09-21 | 2022-10-04 | 87
0 | EDCMPI2455 | RECEIVE TBE COMPANY APPROVAL - GASKETS | 10 | 2022-06-15 | 2022-06-29 | 2022-10-19 | 2022-11-01 | 87
0 | EDCMPI2460 | ISSUE TBE - GASKETS | 11 | 2022-07-18 | 2022-08-02 | 2022-11-16 | 2022-11-30 | 87
BOLTING |  |  | 76 | 2022-03-31 | 2022-07-25 | 2022-08-25 | 2022-12-12 | 99
REQUISITIONS |  |  | 45 | 2022-03-31 | 2022-06-07 | 2022-08-25 | 2022-10-27 | 100
0 | EDCMPI1375 | BOLTING - ISSUE MR - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-08-25 | 2022-09-07 | 99
0 | EDCMPI1380 | BOLTING - ISSUE MR - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-09-23 | 2022-10-06 | 100
0 | EDCMPI1385 | BOLTING - ISSUE MR - IFC | 5 | 2022-05-31 | 2022-06-07 | 2022-10-21 | 2022-10-27 | 100
TBE |  |  | 51 | 2022-05-10 | 2022-07-25 | 2022-09-29 | 2022-12-12 | 99
0 | EDCMPI2465 | COMPLETE EVALUATION AND SUBMIT TBE - BOLTING - ICR | 10 | 2022-05-10 | 2022-05-24 | 2022-09-29 | 2022-10-12 | 99
0 | EDCMPI2470 | RECEIVE TBE COMPANY APPROVAL - BOLTING | 10 | 2022-06-07 | 2022-06-21 | 2022-10-27 | 2022-11-09 | 99
0 | EDCMPI2475 | ISSUE TBE - BOLTING | 11 | 2022-07-05 | 2022-07-25 | 2022-11-24 | 2022-12-12 | 99
MECHANICAL (STATIC / ROTATING / PACKAGE EQUIPMENT) |  |  | 262 | 2022-01-06 | 2023-01-19 | 2022-03-25 | 2023-04-12 | 60
STATIC |  |  | 261 | 2022-01-07 | 2023-01-19 | 2022-03-25 | 2023-04-12 | 60
DOCUMENTS |  |  | 92 | 2022-01-07 | 2022-05-20 | 2022-03-25 | 2022-08-05 | 53
DESIGN BASIS |  |  | 68 | 2022-01-07 | 2022-04-13 | 2022-03-25 | 2022-07-22 | 67
0 | EDCDME1000 | DESIGN BASIS-STATIC EQUIPMENT - ICR | 15 | 2022-01-07 | 2022-01-28 | 2022-03-25 | 2022-04-14 | 55
0 | EDCDME1005 | DESIGN BASIS-STATIC EQUIPMENT - IFA | 15 | 2022-02-09 | 2022-03-02 | 2022-05-18 | 2022-06-07 | 67
0 | EDCDME1010 | DESIGN BASIS-STATIC EQUIPMENT - IFC | 20 | 2022-03-16 | 2022-04-13 | 2022-06-22 | 2022-07-22 | 67
SPECIFICATION |  |  | 67 | 2022-02-07 | 2022-05-16 | 2022-04-15 | 2022-08-05 | 57
0 | EDCDME1030 | SPECIFICATION FOR PIG LAUNCHER AND RECEIVER - ICR | 10 | 2022-02-16 | 2022-03-02 | 2022-04-26 | 2022-05-12 | 49
0 | EDCDME1015 | SPECIFICATION FOR DESIGN AND FABRICATION OF PRESSURE VESSELS - ICR | 20 | 2022-02-07 | 2022-03-07 | 2022-04-15 | 2022-05-17 | 49
0 | EDCDME1035 | SPECIFICATION FOR PIG LAUNCHER AND RECEIVER - IFA | 10 | 2022-03-14 | 2022-03-28 | 2022-05-30 | 2022-06-10 | 52
0 | EDCDME1020 | SPECIFICATION FOR DESIGN AND FABRICATION OF PRESSURE VESSELS - IFA | 9 | 2022-03-17 | 2022-03-30 | 2022-06-09 | 2022-06-21 | 57
0 | EDCDME1040 | SPECIFICATION FOR PIG LAUNCHER AND RECEIVER - IFC | 20 | 2022-04-11 | 2022-05-12 | 2022-06-27 | 2022-07-27 | 52
0 | EDCDME1025 | SPECIFICATION FOR DESIGN AND FABRICATION OF PRESSURE VESSELS - IFC | 20 | 2022-04-13 | 2022-05-16 | 2022-07-06 | 2022-08-05 | 57
REPORTS |  |  | 50 | 2022-03-08 | 2022-05-20 | 2022-05-13 | 2022-07-27 | 46
0 | EDCDME1045 | REPORT ON PIG LAUNCHER RECEIVER LENGTH - ICR | 7 | 2022-03-09 | 2022-03-18 | 2022-05-16 | 2022-05-24 | 45
0 | EDCDME1155 | CRITICALITY RATING PROCEDURE & REPORT FOR LLI MAJOR EQUIPMENT & ITEMS - ICR | 8 | 2022-03-08 | 2022-03-18 | 2022-05-13 | 2022-05-24 | 45
0 | EDCDME1050 | REPORT ON PIG LAUNCHER RECEIVER LENGTH - IFA | 10 | 2022-03-30 | 2022-04-13 | 2022-06-07 | 2022-06-20 | 46
0 | EDCDME1160 | CRITICALITY RATING PROCEDURE & REPORT FOR LLI MAJOR EQUIPMENT & ITEMS - IFA | 10 | 2022-03-30 | 2022-04-13 | 2022-06-07 | 2022-06-20 | 46
0 | EDCDME1055 | REPORT ON PIG LAUNCHER RECEIVER LENGTH - IFC | 17 | 2022-04-22 | 2022-05-20 | 2022-06-30 | 2022-07-27 | 46
0 | EDCDME1165 | CRITICALITY RATING PROCEDURE & REPORT FOR LLI MAJOR EQUIPMENT & ITEMS - IFC | 17 | 2022-04-22 | 2022-05-20 | 2022-06-30 | 2022-07-27 | 46
REQUISITIONS |  |  | 219 | 2022-03-08 | 2023-01-19 | 2022-05-13 | 2023-04-12 | 60
PIG LAUNCHERS & RECEIVERS |  |  | 69 | 2022-03-08 | 2022-06-16 | 2022-05-13 | 2022-08-31 | 52
REQUISITION |  |  | 49 | 2022-03-08 | 2022-05-19 | 2022-05-13 | 2022-07-27 | 47
0 | EDCMME1000 | PIG LAUNCHERS AND RECEIVERS - ISSUE MR - ICR | 8 | 2022-03-08 | 2022-03-18 | 2022-05-13 | 2022-05-24 | 45
0 | EDCMME1005 | PIG LAUNCHERS AND RECEIVERS - ISSUE MR - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-06-22 | 2022-07-05 | 55
0 | EDCMME1010 | PIG LAUNCHERS AND RECEIVERS - ISSUE MR - IFC | 3 | 2022-05-16 | 2022-05-19 | 2022-07-25 | 2022-07-27 | 47
TBE |  |  | 51 | 2022-04-01 | 2022-06-16 | 2022-06-09 | 2022-08-31 | 52
0 | EDCMME3000 | COMPLETE EVALUATION AND SUBMIT TBE - PIG LAUNCHER AND RECEIVER - ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-06-09 | 2022-06-22 | 46
0 | EDCMME3005 | RECEIVE COMMENTS & ISSUE TBE - PIG LAUNCHER AND RECEIVER - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-07-14 | 2022-07-27 | 48
0 | EDCMME3010 | ISSUE TBE - PIG LAUNCHER AND RECEIVER - IFC | 11 | 2022-06-01 | 2022-06-16 | 2022-08-17 | 2022-08-31 | 52
INCONEL & SS PLATES - VESSEL |  |  | 69 | 2022-03-22 | 2022-06-30 | 2022-05-25 | 2022-09-02 | 44
REQUISITION |  |  | 43 | 2022-03-22 | 2022-05-25 | 2022-05-25 | 2022-08-05 | 50
0 | EDCMME3040 | INCONEL & SS PLATES - VESSEL - ISSUE MR - ICR | 8 | 2022-03-22 | 2022-04-01 | 2022-05-25 | 2022-06-03 | 43
0 | EDCMME3030 | INCONEL & SS PLATES - VESSEL - ISSUE MR - IFA | 10 | 2022-04-15 | 2022-04-29 | 2022-07-01 | 2022-07-19 | 52
0 | EDCMME3020 | INCONEL & SS PLATES - VESSEL - ISSUE MR - IFC | 3 | 2022-05-20 | 2022-05-25 | 2022-08-03 | 2022-08-05 | 50
TBE |  |  | 51 | 2022-04-15 | 2022-06-30 | 2022-06-21 | 2022-09-02 | 44
0 | EDCMME3050 | COMPLETE EVALUATION AND SUBMIT TBE - INCONEL & SS PLATES - VESSEL - ICR | 10 | 2022-04-15 | 2022-04-29 | 2022-06-21 | 2022-07-04 | 44
0 | EDCMME3060 | RECEIVE COMMENTS & ISSUE TBE - INCONEL & SS PLATES - VESSEL - IFA | 10 | 2022-05-18 | 2022-06-01 | 2022-07-22 | 2022-08-04 | 44
0 | EDCMME3070 | ISSUE TBE - INCONEL & SS PLATES - VESSEL - IFC | 11 | 2022-06-15 | 2022-06-30 | 2022-08-19 | 2022-09-02 | 44
DISHED HEAD - VESSEL |  |  | 68 | 2022-03-29 | 2022-07-06 | 2022-06-29 | 2022-10-07 | 65
REQUISITION |  |  | 43 | 2022-03-29 | 2022-06-01 | 2022-06-29 | 2022-09-09 | 70
0 | EDCMME3100 | DISHED HEAD - VESSEL- ISSUE MR - ICR | 8 | 2022-03-29 | 2022-04-08 | 2022-06-29 | 2022-07-13 | 63
0 | EDCMME3090 | DISHED HEAD - VESSEL - ISSUE MR - IFA | 10 | 2022-04-22 | 2022-05-11 | 2022-08-10 | 2022-08-23 | 72
0 | EDCMME3080 | DISHED HEAD - VESSEL - ISSUE MR - IFC | 3 | 2022-05-27 | 2022-06-01 | 2022-09-07 | 2022-09-09 | 70
TBE |  |  | 50 | 2022-04-22 | 2022-07-06 | 2022-07-28 | 2022-10-07 | 65
0 | EDCMME3110 | COMPLETE EVALUATION AND SUBMIT TBE - DISHED HEAD - VESSEL - ICR | 10 | 2022-04-22 | 2022-05-11 | 2022-07-28 | 2022-08-10 | 63
0 | EDCMME3120 | RECEIVE COMMENTS & ISSUE TBE - DISHED HEAD - VESSEL - IFA | 10 | 2022-05-25 | 2022-06-08 | 2022-08-29 | 2022-09-09 | 65
0 | EDCMME3130 | ISSUE TBE - DISHED HEAD - VESSEL - IFC | 10 | 2022-06-22 | 2022-07-06 | 2022-09-26 | 2022-10-07 | 65
NAME PLATE - VESSEL |  |  | 83 | 2022-09-22 | 2023-01-19 | 2023-01-11 | 2023-04-12 | 60
REQUISITION |  |  | 83 | 2022-09-22 | 2023-01-19 | 2023-01-11 | 2023-04-12 | 60
0 | EDCMME3160 | NAME PLATE - VESSEL - ISSUE MR - ICR | 5 | 2022-09-22 | 2022-09-29 | 2023-01-11 | 2023-01-17 | 77
0 | EDCMME3150 | NAME PLATE - VESSEL - ISSUE MR - IFA | 5 | 2022-10-13 | 2022-10-20 | 2023-03-20 | 2023-03-24 | 110
0 | EDCMME3140 | NAME PLATE - VESSEL - ISSUE MR - IFC | 3 | 2023-01-16 | 2023-01-19 | 2023-04-10 | 2023-04-12 | 60
TBE |  |  | 68 | 2022-10-13 | 2023-01-19 | 2023-02-01 | 2023-04-12 | 60
0 | EDCMME3170 | COMPLETE EVALUATION AND SUBMIT TBE - NAME PLATE - VESSEL - ICR | 10 | 2022-10-13 | 2022-10-27 | 2023-02-01 | 2023-02-14 | 77
0 | EDCMME3180 | RECEIVE COMMENTS & ISSUE TBE - NAME PLATE - VESSEL- IFA | 10 | 2022-11-10 | 2022-11-24 | 2023-03-01 | 2023-03-14 | 77
0 | EDCMME3190 | ISSUE TBE - NAME PLATE - VESSEL - IFC | 11 | 2023-01-04 | 2023-01-19 | 2023-03-29 | 2023-04-12 | 60
ROTATING |  |  | 111 | 2022-01-06 | 2022-06-15 | 2022-03-29 | 2022-08-26 | 50
DOCUMENTS |  |  | 93 | 2022-01-06 | 2022-05-20 | 2022-03-29 | 2022-07-22 | 43
DESIGN BASIS |  |  | 66 | 2022-01-06 | 2022-04-08 | 2022-03-29 | 2022-07-22 | 70
0 | EDCDME1060 | MACHINERY & PACKAGE EQUIPMENT DESIGN BASIS - ICR | 15 | 2022-01-06 | 2022-01-27 | 2022-03-29 | 2022-04-18 | 58
0 | EDCDME1065 | MACHINERY & PACKAGE EQUIPMENT DESIGN BASIS - IFA | 16 | 2022-02-10 | 2022-03-04 | 2022-05-24 | 2022-06-14 | 70
0 | EDCDME1070 | MACHINERY & PACKAGE EQUIPMENT DESIGN BASIS - IFC | 15 | 2022-03-18 | 2022-04-08 | 2022-06-29 | 2022-07-22 | 70
SPECIFICATIONS |  |  | 50 | 2022-03-04 | 2022-05-18 | 2022-05-06 | 2022-07-21 | 44
0 | EDCDME1075 | SPECIFICATION FOR POSITIVE DISPLACEMENT PUMP ( DRAIN PUMP) - ICR | 10 | 2022-03-04 | 2022-03-18 | 2022-05-06 | 2022-05-19 | 42
0 | EDCDME1080 | SPECIFICATION FOR POSITIVE DISPLACEMENT PUMP ( DRAIN PUMP) - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-06-03 | 2022-06-16 | 42
0 | EDCDME1085 | SPECIFICATION FOR POSITIVE DISPLACEMENT PUMP ( DRAIN PUMP) - IFC | 10 | 2022-04-29 | 2022-05-18 | 2022-07-05 | 2022-07-21 | 44
DATA SHEETS |  |  | 47 | 2022-03-11 | 2022-05-20 | 2022-05-13 | 2022-07-21 | 42
0 | EDCDME1090 | DATA SHEET FOR DRAIN PUMP - ICR | 5 | 2022-03-11 | 2022-03-18 | 2022-05-13 | 2022-05-19 | 42
0 | EDCDME1095 | DATA SHEET FOR DRAIN PUMP - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-06-03 | 2022-06-16 | 42
0 | EDCDME1100 | DATA SHEET FOR DRAIN PUMP - IFC | 10 | 2022-05-06 | 2022-05-20 | 2022-07-05 | 2022-07-21 | 42
REQUISITIONS |  |  | 70 | 2022-03-04 | 2022-06-15 | 2022-05-06 | 2022-08-26 | 50
POSITIVE DISPLACEMENT PUMP ( DRAIN PUMP) |  |  | 70 | 2022-03-04 | 2022-06-15 | 2022-05-06 | 2022-08-26 | 50
REQUISITION |  |  | 52 | 2022-03-04 | 2022-05-20 | 2022-05-06 | 2022-07-21 | 42
0 | EDCMME1075 | POSITIVE DISPLACEMENT PUMP ( DRAIN PUMP) - ISSUE MR - ICR | 10 | 2022-03-04 | 2022-03-18 | 2022-05-06 | 2022-05-19 | 42
0 | EDCMME1080 | POSITIVE DISPLACEMENT PUMP ( DRAIN PUMP) - ISSUE MR - IFA | 5 | 2022-04-08 | 2022-04-15 | 2022-06-10 | 2022-06-16 | 42
0 | EDCMME1085 | POSITIVE DISPLACEMENT PUMP ( DRAIN PUMP) - ISSUE MR - IFC | 5 | 2022-05-13 | 2022-05-20 | 2022-07-15 | 2022-07-21 | 42
TBE |  |  | 50 | 2022-04-01 | 2022-06-15 | 2022-06-03 | 2022-08-26 | 50
0 | EDCMME2000 | COMPLETE EVALUATION AND SUBMIT TBE - POSITIVE DISPLACEMENT PUMPS - ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-06-03 | 2022-06-16 | 42
0 | EDCMME2005 | RECEIVE COMMENTS & ISSUE TBE - POSITIVE DISPLACEMENT PUMPS - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-07-05 | 2022-07-21 | 44
0 | EDCMME2010 | ISSUE TBE - POSITIVE DISPLACEMENT PUMPS - IFC | 10 | 2022-06-01 | 2022-06-15 | 2022-08-15 | 2022-08-26 | 50
PACKAGE EQUIPMENT |  |  | 186 | 2022-03-15 | 2022-12-12 | 2022-05-19 | 2023-03-15 | 68
DOCUMENTS |  |  | 60 | 2022-03-15 | 2022-06-10 | 2022-05-19 | 2022-09-07 | 61
SPECIFICATION |  |  | 58 | 2022-03-15 | 2022-06-08 | 2022-05-19 | 2022-09-07 | 63
0 | EDCDME1105 | SPECIFICATION FOR PORTABLE BIOCIDE INJECTION PACKAGE - ICR | 7 | 2022-03-15 | 2022-03-24 | 2022-05-19 | 2022-05-27 | 44
0 | EDCDME1120 | SPECIFICATION FOR MATERIAL HANDLING EQUIPMENT - ICR | 6 | 2022-03-21 | 2022-03-29 | 2022-06-15 | 2022-06-22 | 59
0 | EDCDME1110 | SPECIFICATION FOR PORTABLE BIOCIDE INJECTION PACKAGE - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-07-05 | 2022-07-21 | 62
0 | EDCDME1125 | SPECIFICATION FOR MATERIAL HANDLING EQUIPMENT - IFA | 10 | 2022-04-08 | 2022-04-22 | 2022-07-14 | 2022-07-27 | 63
0 | EDCDME1115 | SPECIFICATION FOR PORTABLE BIOCIDE INJECTION PACKAGE - IFC | 20 | 2022-05-06 | 2022-06-03 | 2022-08-05 | 2022-09-01 | 62
0 | EDCDME1130 | SPECIFICATION FOR MATERIAL HANDLING EQUIPMENT - IFC | 20 | 2022-05-11 | 2022-06-08 | 2022-08-11 | 2022-09-07 | 63
DATASHEETS |  |  | 55 | 2022-03-22 | 2022-06-10 | 2022-05-26 | 2022-09-07 | 61
0 | EDCDME1135 | DATA SHEET FOR PORTABLE BIOCIDE INJECTION PACKAGE - ICR | 5 | 2022-03-22 | 2022-03-29 | 2022-05-26 | 2022-06-01 | 44
0 | EDCDME1140 | DATA SHEET FOR PORTABLE BIOCIDE INJECTION PACKAGE - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-07-14 | 2022-07-27 | 61
0 | EDCDME1145 | DATA SHEET FOR PORTABLE BIOCIDE INJECTION PACKAGE - IFC | 20 | 2022-05-13 | 2022-06-10 | 2022-08-11 | 2022-09-07 | 61
REQUISITIONS |  |  | 176 | 2022-03-29 | 2022-12-12 | 2022-06-02 | 2023-03-15 | 68
MATERIAL HANDLING EQUIPMENT |  |  | 135 | 2022-04-06 | 2022-10-20 | 2022-07-01 | 2023-03-15 | 103
REQUISITION |  |  | 46 | 2022-04-06 | 2022-06-14 | 2022-07-01 | 2022-09-07 | 59
0 | EDCMME1090 | MATERIAL HANDLING EQUIPMENT - ISSUE MR - ICR | 8 | 2022-04-06 | 2022-04-18 | 2022-07-01 | 2022-07-15 | 59
0 | EDCMME1095 | MATERIAL HANDLING EQUIPMENT - ISSUE MR - IFA | 9 | 2022-05-05 | 2022-05-18 | 2022-08-01 | 2022-08-11 | 59
0 | EDCMME1100 | MATERIAL HANDLING EQUIPMENT - ISSUE MR - IFC | 9 | 2022-06-01 | 2022-06-14 | 2022-08-26 | 2022-09-07 | 59
TBE |  |  | 107 | 2022-05-19 | 2022-10-20 | 2022-09-15 | 2023-03-15 | 103
0 | EDCMME2105 | COMPLETE EVALUATION AND SUBMIT TBE - MATERIAL HANDLING EQUIPMENT - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-09-15 | 2022-10-12 | 82
0 | EDCMME2110 | RECEIVE COMMENTS & ISSUE TBE- MATERIAL HANDLING EQUIPMENT - IFA | 10 | 2022-06-30 | 2022-07-19 | 2022-10-27 | 2022-11-09 | 82
0 | EDCMME2115 | ISSUE TBE - MATERIAL HANDLING EQUIPMENT - IFC | 11 | 2022-10-05 | 2022-10-20 | 2023-03-01 | 2023-03-15 | 103
PORTABLE BIOCIDE INJECTION PACKAGE |  |  | 80 | 2022-03-29 | 2022-07-27 | 2022-06-02 | 2022-09-28 | 46
REQUISITION |  |  | 52 | 2022-03-29 | 2022-06-14 | 2022-06-02 | 2022-09-07 | 59
0 | EDCMME1105 | PORTABLE BIOCIDE INJECTION PACKAGE - ISSUE MR - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-06-02 | 2022-06-15 | 44
0 | EDCMME1110 | PORTABLE BIOCIDE INJECTION PACKAGE - ISSUE MR - IFA | 12 | 2022-04-26 | 2022-05-17 | 2022-07-26 | 2022-08-10 | 59
0 | EDCMME1115 | PORTABLE BIOCIDE INJECTION PACKAGE - ISSUE MR - IFC | 10 | 2022-05-31 | 2022-06-14 | 2022-08-25 | 2022-09-07 | 59
TBE |  |  | 50 | 2022-05-13 | 2022-07-27 | 2022-07-19 | 2022-09-28 | 46
0 | EDCMME2130 | COMPLETE EVALUATION AND SUBMIT TBE - PORTABLE BIOCIDE INJECTION PACKAGE - ICR | 15 | 2022-05-13 | 2022-06-03 | 2022-07-19 | 2022-08-08 | 44
0 | EDCMME2135 | RECEIVE COMMENTS & ISSUE TBE - PORTABLE BIOCIDE INJECTION PACKAGE - IFA | 10 | 2022-06-17 | 2022-07-01 | 2022-08-23 | 2022-09-05 | 44
0 | EDCMME2140 | ISSUE TBE - PORTABLE BIOCIDE INJECTION PACKAGE - IFC | 5 | 2022-07-20 | 2022-07-27 | 2022-09-22 | 2022-09-28 | 46
LIFE RAFT |  |  | 85 | 2022-08-11 | 2022-12-12 | 2022-11-15 | 2023-03-15 | 68
REQUISITION |  |  | 50 | 2022-08-11 | 2022-10-20 | 2022-11-15 | 2023-03-03 | 95
0 | EDCMME1120 | LIFE RAFT - ISSUE MR - ICR | 10 | 2022-08-11 | 2022-08-25 | 2022-11-15 | 2022-11-28 | 68
0 | EDCMME1125 | LIFE RAFT - ISSUE MR - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-01-19 | 2023-02-01 | 93
0 | EDCMME1130 | LIFE RAFT - ISSUE MR - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-02-20 | 2023-03-03 | 95
TBE |  |  | 50 | 2022-09-29 | 2022-12-12 | 2023-01-05 | 2023-03-15 | 68
0 | EDCMME2150 | COMPLETE EVALUATION AND SUBMIT TBE - LIFE RAFT - ICR | 20 | 2022-09-29 | 2022-10-27 | 2023-01-05 | 2023-02-01 | 68
0 | EDCMME2155 | RECEIVE COMMENTS & ISSUE TBE - LIFE RAFT - IFA | 10 | 2022-11-10 | 2022-11-24 | 2023-02-16 | 2023-03-01 | 68
0 | EDCMME2160 | ISSUE TBE - LIFE RAFT - IFC | 10 | 2022-11-24 | 2022-12-12 | 2023-03-02 | 2023-03-15 | 68
ELECTRICAL |  |  | 275 | 2021-12-19 | 2023-01-18 | 2022-02-11 | 2023-05-16 | 83
DOCUMENTS |  |  | 275 | 2021-12-19 | 2023-01-18 | 2022-02-11 | 2023-04-27 | 70
DESIGN BASIS |  |  | 88 | 2021-12-19 | 2022-04-20 | 2022-02-11 | 2022-07-22 | 62
0 | EDCDEL1000 | ELECTRICAL DESIGN BASIS - ICR | 20 | 2021-12-19 | 2022-01-14 | 2022-02-11 | 2022-03-10 | 40
0 | EDCDEL1005 | ELECTRICAL DESIGN BASIS - IFA | 10 | 2022-03-10 | 2022-03-24 | 2022-06-09 | 2022-06-22 | 62
0 | EDCDEL1010 | ELECTRICAL DESIGN BASIS - IFC | 9 | 2022-04-07 | 2022-04-20 | 2022-07-07 | 2022-07-22 | 62
SPECIFICATIONS |  |  | 131 | 2021-12-30 | 2022-07-07 | 2022-02-24 | 2023-02-02 | 146
0 | EDCDEL1015 | SPECIFICATION FOR COMPOSITE SUBSEA CABLE - ICR | 15 | 2021-12-30 | 2022-01-21 | 2022-02-24 | 2022-03-17 | 40
0 | EDCDEL1030 | SPECIFICATION FOR 6.6kV RING MAIN UNIT - ICR | 15 | 2022-01-14 | 2022-02-04 | 2022-04-27 | 2022-05-20 | 73
0 | EDCDEL1045 | SPECIFICATION FOR ELECTRICAL REQUIREMENT FOR PACKAGE EQUIPMENT - ICR | 15 | 2022-01-21 | 2022-02-11 | 2022-03-24 | 2022-04-13 | 44
0 | EDCDEL1020 | SPECIFICATION FOR COMPOSITE SUBSEA CABLE - IFA | 10 | 2022-02-04 | 2022-02-18 | 2022-07-04 | 2022-07-20 | 103
0 | EDCDEL1105 | SPECIFICATION FOR LV MOTORS - ICR | 15 | 2022-02-04 | 2022-02-25 | 2022-06-15 | 2022-07-05 | 90
0 | EDCDEL1035 | SPECIFICATION FOR 6.6kV RING MAIN UNIT - IFA | 11 | 2022-02-18 | 2022-03-07 | 2022-07-28 | 2022-08-11 | 108
0 | EDCDEL1120 | SPECIFICATION FOR HIGH VOLTAGE CABLES - ICR | 16 | 2022-02-11 | 2022-03-07 | 2022-06-09 | 2022-06-30 | 81
0 | EDCDEL1090 | SPECIFICATION FOR 24V DC UPS - ICR | 16 | 2022-02-11 | 2022-03-07 | 2022-04-14 | 2022-05-10 | 44
0 | EDCDEL1075 | SPECIFICATION FOR DISTRIBUTION TRANSFORMERS - ICR | 16 | 2022-02-11 | 2022-03-07 | 2022-04-14 | 2022-05-10 | 44
0 | EDCDEL1060 | SPECIFICATION FOR 415V SWITCHBOARD AND LV DISTRIBUTION BOARDS ICR | 11 | 2022-02-24 | 2022-03-11 | 2022-04-27 | 2022-05-16 | 44
0 | EDCDEL1050 | SPECIFICATION FOR ELECTRICAL REQUIREMENT FOR PACKAGE EQUIPMENT - IFA | 10 | 2022-02-25 | 2022-03-11 | 2022-07-28 | 2022-08-10 | 103
0 | EDCDEL1135 | SPECIFICATION FOR LOW VOLTAGE CABLES - ICR | 16 | 2022-02-18 | 2022-03-14 | 2022-06-16 | 2022-07-07 | 81
0 | EDCDEL1025 | SPECIFICATION FOR COMPOSITE SUBSEA CABLE - IFC | 10 | 2022-03-04 | 2022-03-18 | 2022-08-04 | 2022-08-17 | 103
0 | EDCDEL1165 | SPECIFICATION FOR NAVIGATIONAL AIDS - ICR | 16 | 2022-02-25 | 2022-03-21 | 2022-06-23 | 2022-07-19 | 81
0 | EDCDEL1110 | SPECIFICATION FOR LV MOTORS - IFA | 10 | 2022-03-11 | 2022-03-25 | 2022-07-28 | 2022-08-10 | 93
0 | EDCDEL1040 | SPECIFICATION FOR 6.6kV RING MAIN UNIT - IFC | 9 | 2022-03-21 | 2022-04-01 | 2022-08-26 | 2022-09-07 | 108
0 | EDCDEL1080 | SPECIFICATION FOR DISTRIBUTION TRANSFORMERS - IFA | 9 | 2022-03-21 | 2022-04-01 | 2022-07-29 | 2022-08-10 | 88
0 | EDCDEL1095 | SPECIFICATION FOR 24V DC UPS - IFA | 9 | 2022-03-21 | 2022-04-01 | 2022-05-25 | 2022-06-06 | 44
0 | EDCDEL1125 | SPECIFICATION FOR HIGH VOLTAGE CABLES - IFA | 10 | 2022-03-21 | 2022-04-04 | 2022-12-16 | 2022-12-29 | 186
0 | EDCDEL1055 | SPECIFICATION FOR ELECTRICAL REQUIREMENT FOR PACKAGE EQUIPMENT - IFC | 10 | 2022-03-25 | 2022-04-08 | 2022-08-25 | 2022-09-07 | 103
0 | EDCDEL1065 | SPECIFICATION FOR 415V SWITCHBOARD AND LV DISTRIBUTION BOARDS - IFA | 10 | 2022-03-25 | 2022-04-08 | 2022-06-20 | 2022-07-01 | 58
0 | EDCDEL1195 | SPECIFICATION FOR ELECTRICAL BULK MATERIALS - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-11-16 | 2022-11-29 | 161
0 | EDCDEL1210 | SPECIFICATION FOR ELECTRICAL INSTALLATION - ICR | 15 | 2022-03-21 | 2022-04-11 | 2022-11-11 | 2022-12-05 | 163
0 | EDCDEL1180 | SPECIFICATION FOR BIRD DETERRENT SYSTEM - ICR | 15 | 2022-03-21 | 2022-04-11 | 2022-08-09 | 2022-08-29 | 95
0 | EDCDEL1140 | SPECIFICATION FOR LOW VOLTAGE CABLES ) - IFA | 10 | 2022-03-28 | 2022-04-11 | 2022-10-11 | 2022-10-24 | 135
0 | EDCDEL1170 | SPECIFICATION FOR NAVIGATIONAL AIDS - IFA | 10 | 2022-04-04 | 2022-04-18 | 2022-10-03 | 2022-10-14 | 124
0 | EDCDEL1115 | SPECIFICATION FOR LV MOTORS - IFC | 10 | 2022-04-08 | 2022-04-22 | 2022-08-25 | 2022-09-07 | 93
0 | EDCDEL1085 | SPECIFICATION FOR DISTRIBUTION TRANSFORMERS - IFC | 10 | 2022-04-15 | 2022-04-29 | 2022-08-25 | 2022-09-07 | 88
0 | EDCDEL1130 | SPECIFICATION FOR HIGH VOLTAGE CABLES - IFC | 10 | 2022-04-18 | 2022-05-05 | 2023-01-13 | 2023-01-26 | 186
0 | EDCDEL1150 | SPECIFICATION FOR GRP CABLE TRAYS & LADDERS - ICR | 15 | 2022-04-11 | 2022-05-05 | 2022-10-25 | 2022-11-14 | 135
0 | EDCDEL1100 | SPECIFICATION FOR 24V DC UPS - IFC | 15 | 2022-04-15 | 2022-05-11 | 2022-08-18 | 2022-09-07 | 83
0 | EDCDEL1070 | SPECIFICATION FOR 415V SWITCHBOARD AND LV DISTRIBUTION BOARDS - IFC | 10 | 2022-04-22 | 2022-05-11 | 2022-08-25 | 2022-09-07 | 83
0 | EDCDEL1145 | SPECIFICATION FOR LOW VOLTAGE CABLES - IFC | 10 | 2022-04-25 | 2022-05-12 | 2022-12-07 | 2022-12-20 | 154
0 | EDCDEL1185 | SPECIFICATION FOR BIRD DETERRENT SYSTEM - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-10-20 | 2022-11-02 | 122
0 | EDCDEL1215 | SPECIFICATION FOR ELECTRICAL INSTALLATION - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-12-20 | 2023-01-02 | 163
0 | EDCDEL1175 | SPECIFICATION FOR NAVIGATIONAL AIDS - IFC | 10 | 2022-05-05 | 2022-05-19 | 2022-10-31 | 2022-11-11 | 124
0 | EDCDEL1200 | SPECIFICATION FOR ELECTRICAL BULK MATERIALS - IFA | 15 | 2022-04-25 | 2022-05-19 | 2022-12-16 | 2023-01-05 | 161
0 | EDCDEL1155 | SPECIFICATION FOR GRP CABLE TRAYS & LADDERS - IFA | 10 | 2022-05-19 | 2022-06-02 | 2022-12-16 | 2022-12-29 | 146
0 | EDCDEL1220 | SPECIFICATION FOR ELECTRICAL INSTALLATION - IFC | 10 | 2022-05-26 | 2022-06-09 | 2023-01-17 | 2023-01-30 | 163
0 | EDCDEL1205 | SPECIFICATION FOR ELECTRICAL BULK MATERIALS - IFC | 10 | 2022-06-02 | 2022-06-16 | 2023-01-20 | 2023-02-02 | 161
0 | EDCDEL1190 | SPECIFICATION FOR BIRD DETERRENT SYSTEM - IFC | 15 | 2022-05-26 | 2022-06-16 | 2022-11-17 | 2022-12-09 | 122
0 | EDCDEL1160 | SPECIFICATION FOR GRP CABLE TRAYS & LADDERS - IFC | 15 | 2022-06-16 | 2022-07-07 | 2023-01-13 | 2023-02-02 | 146
DATASHEETS |  |  | 124 | 2022-01-07 | 2022-07-05 | 2022-03-04 | 2023-02-17 | 159
0 | EDCDEL1225 | DATASHEET FOR COMPOSITE SUBSEA CABLE - ICR | 15 | 2022-01-07 | 2022-01-28 | 2022-03-04 | 2022-03-24 | 40
0 | EDCDEL1240 | DATASHEET FOR 6.6kV RING MAIN UNIT (RMU) - ICR | 15 | 2022-01-21 | 2022-02-11 | 2022-05-09 | 2022-05-27 | 73
0 | EDCDEL1230 | DATASHEET FOR COMPOSITE SUBSEA CABLE - IFA | 10 | 2022-02-11 | 2022-02-25 | 2022-04-08 | 2022-04-21 | 40
0 | EDCDEL1300 | DATASHEET FOR LV MOTORS - ICR | 16 | 2022-02-10 | 2022-03-04 | 2022-06-21 | 2022-07-15 | 90
0 | EDCDEL1245 | DATASHEET FOR 6.6kV RING MAIN UNIT (RMU) - IFA | 11 | 2022-02-25 | 2022-03-14 | 2022-07-27 | 2022-08-10 | 102
0 | EDCDEL1270 | DATASHEET FOR 6.6kV/0.433kV TRANSFORMERS - ICR | 16 | 2022-02-18 | 2022-03-14 | 2022-04-21 | 2022-05-17 | 44
0 | EDCDEL1285 | DATASHEET FOR 24V DC UPS - ICR | 16 | 2022-02-18 | 2022-03-14 | 2022-05-13 | 2022-06-03 | 57
0 | EDCDEL1255 | DATASHEET FOR 415V SWITCHBOARD - ICR | 16 | 2022-02-24 | 2022-03-18 | 2022-04-27 | 2022-05-23 | 44
0 | EDCDEL1235 | DATASHEET FOR COMPOSITE SUBSEA CABLE - IFC | 10 | 2022-03-11 | 2022-03-25 | 2022-08-04 | 2022-08-17 | 98
0 | EDCDEL1500 | DATASHEET FOR LV DISTRIBUTION BOARDS - ICR | 15 | 2022-03-04 | 2022-03-25 | 2022-06-20 | 2022-07-13 | 73
0 | EDCDEL1305 | DATASHEET FOR LV MOTORS - IFA | 10 | 2022-03-16 | 2022-03-30 | 2022-07-28 | 2022-08-10 | 90
0 | EDCDEL1315 | DATASHEET FOR HV CABLES - ICR | 20 | 2022-03-07 | 2022-04-04 | 2022-10-10 | 2022-11-04 | 149
0 | EDCDEL1345 | DATASHEET FOR NAVIGATIONAL AIDS AND BIRD DETERRENT SYSTEM - ICR | 15 | 2022-03-14 | 2022-04-04 | 2022-07-13 | 2022-08-02 | 81
0 | EDCDEL1275 | DATASHEET FOR 6.6kV/0.433kV TRANSFORMERS - IFA | 8 | 2022-03-28 | 2022-04-07 | 2022-06-01 | 2022-06-10 | 44
0 | EDCDEL1250 | DATASHEET FOR 6.6kV RING MAIN UNIT (RMU) - IFC | 10 | 2022-03-28 | 2022-04-11 | 2022-08-25 | 2022-09-07 | 102
0 | EDCDEL1290 | DATASHEET FOR 24V DC UPS - IFA | 10 | 2022-03-28 | 2022-04-11 | 2022-07-28 | 2022-08-10 | 82
0 | EDCDEL1260 | DATASHEET FOR 415V SWITCHBOARD - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-07-28 | 2022-08-10 | 78
0 | EDCDEL1330 | DATASHEET FOR LV CABLES - ICR | 15 | 2022-03-28 | 2022-04-18 | 2022-10-24 | 2022-11-11 | 144
0 | EDCDEL1510 | DATASHEET FOR LV DISTRIBUTION BOARDS - IFA | 10 | 2022-04-08 | 2022-04-22 | 2022-07-28 | 2022-08-10 | 73
0 | EDCDEL1310 | DATASHEET FOR LV MOTORS - IFC | 10 | 2022-04-13 | 2022-04-27 | 2022-08-25 | 2022-09-07 | 90
0 | EDCDEL1350 | DATASHEET FOR NAVIGATIONAL AIDS AND BIRD DETERRENT SYSTEM - IFA | 9 | 2022-04-18 | 2022-04-29 | 2022-10-31 | 2022-11-10 | 134
0 | EDCDEL1320 | DATASHEET FOR HV CABLES - IFA | 10 | 2022-04-18 | 2022-05-05 | 2022-12-23 | 2023-01-05 | 171
0 | EDCDEL1280 | DATASHEET FOR 6.6kV/0.433kV TRANSFORMERS - IFC | 10 | 2022-04-21 | 2022-05-10 | 2022-08-25 | 2022-09-07 | 84
0 | EDCDEL1295 | DATASHEET FOR 24V DC UPS - IFC | 10 | 2022-04-25 | 2022-05-12 | 2022-08-25 | 2022-09-07 | 82
0 | EDCDEL1360 | DATASHEET FOR CABLE TRAYS & LADDERS - ICR | 15 | 2022-04-18 | 2022-05-12 | 2022-11-01 | 2022-11-21 | 135
0 | EDCDEL1265 | DATASHEET FOR 415V SWITCHBOARD - IFC | 10 | 2022-04-29 | 2022-05-18 | 2022-08-25 | 2022-09-07 | 78
0 | EDCDEL1335 | DATASHEET FOR LV CABLES - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-12-15 | 2022-12-28 | 155
0 | EDCDEL1520 | DATASHEET FOR LV DISTRIBUTION BOARDS - IFC | 10 | 2022-05-11 | 2022-05-25 | 2022-08-25 | 2022-09-07 | 73
0 | EDCDEL1355 | DATASHEET FOR NAVIGATIONAL AIDS AND BIRD DETERRENT SYSTEM - IFC | 9 | 2022-05-18 | 2022-05-31 | 2022-11-25 | 2022-12-09 | 134
0 | EDCDEL1325 | DATASHEET FOR HV CABLES - IFC | 10 | 2022-05-19 | 2022-06-02 | 2023-01-20 | 2023-02-02 | 171
0 | EDCDEL1365 | DATASHEET FOR CABLE TRAYS & LADDERS - IFA | 9 | 2022-05-26 | 2022-06-08 | 2023-01-11 | 2023-01-23 | 159
0 | EDCDEL1340 | DATASHEET FOR LV CABLES - IFC | 10 | 2022-06-02 | 2022-06-16 | 2023-01-12 | 2023-01-25 | 155
0 | EDCDEL1370 | DATASHEET FOR CABLE TRAYS & LADDERS - IFC | 9 | 2022-06-22 | 2022-07-05 | 2023-02-07 | 2023-02-17 | 159
STUDIES & REPORTS / SCHEDULES |  |  | 265 | 2021-12-30 | 2023-01-18 | 2022-04-13 | 2023-04-27 | 70
0 | EDCDEL1375 | IMPLEMENTATION PROCEDURE FOR SMARTPLANT ELECTRICAL (SPEL) - ICR | 15 | 2021-12-30 | 2022-01-21 | 2022-04-13 | 2022-05-06 | 73
0 | EDCDEL1380 | IMPLEMENTATION PROCEDURE FOR SMARTPLANT ELECTRICAL (SPEL) - IFA | 16 | 2022-02-04 | 2022-02-28 | 2022-05-23 | 2022-06-13 | 73
0 | EDCDEL1385 | IMPLEMENTATION PROCEDURE FOR SMARTPLANT ELECTRICAL (SPEL) - IFC | 10 | 2022-03-14 | 2022-03-28 | 2022-06-28 | 2022-07-14 | 73
0 | EDCDEL1435 | ELECTRICAL PROTECTION, CONTROL & METERING PHILOSOPHY - ICR | 15 | 2022-03-10 | 2022-03-31 | 2022-10-17 | 2022-11-04 | 151
0 | EDCDEL1465 | ELECTRICAL SITE VISIT REPORT - ICR | 15 | 2022-03-28 | 2022-04-18 | 2022-07-15 | 2022-08-04 | 73
0 | EDCDEL1440 | ELECTRICAL PROTECTION, CONTROL & METERING PHILOSOPHY - IFA | 15 | 2022-04-14 | 2022-05-10 | 2022-11-21 | 2022-12-13 | 151
0 | EDCDEL1470 | ELECTRICAL SITE VISIT REPORT - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-10-25 | 2022-11-07 | 120
0 | EDCDEL1420 | ELECTRICAL I/O SCHEDULE - ICR | 15 | 2022-05-26 | 2022-06-16 | 2022-08-11 | 2022-08-31 | 52
0 | EDCDEL1445 | ELECTRICAL PROTECTION, CONTROL & METERING PHILOSOPHY - IFC | 20 | 2022-05-24 | 2022-06-21 | 2022-12-28 | 2023-01-24 | 151
0 | EDCDEL1450 | ELECTRICAL PROTECTION COORDINATION STUDY REPORT - ICR | 20 | 2022-05-24 | 2022-06-21 | 2022-12-28 | 2023-01-24 | 151
0 | EDCDEL1475 | ELECTRICAL SITE VISIT REPORT - IFC | 15 | 2022-06-02 | 2022-06-23 | 2022-11-22 | 2022-12-14 | 120
0 | EDCDEL1455 | ELECTRICAL PROTECTION COORDINATION STUDY REPORT - IFA | 10 | 2022-07-05 | 2022-07-22 | 2023-02-08 | 2023-02-21 | 151
0 | EDCDEL1425 | ELECTRICAL I/O SCHEDULE - IFA | 15 | 2022-06-30 | 2022-07-26 | 2022-09-15 | 2022-10-05 | 52
0 | EDCDEL1460 | ELECTRICAL PROTECTION COORDINATION STUDY REPORT - IFC | 20 | 2022-08-05 | 2022-09-02 | 2023-03-08 | 2023-04-04 | 151
0 | EDCDEL1430 | ELECTRICAL I/O SCHEDULE - IFC | 20 | 2022-08-09 | 2022-09-06 | 2022-10-20 | 2022-11-16 | 52
0 | EDCDEL1530 | ELECTRICAL DRUM SCHEDULE - IRC | 15 | 2022-10-31 | 2022-11-21 | 2023-02-08 | 2023-02-28 | 70
0 | EDCDEL1540 | ELECTRICAL DRUM SCHEDULE - IFA | 10 | 2022-12-07 | 2022-12-21 | 2023-03-15 | 2023-03-28 | 70
0 | EDCDEL1550 | ELECTRICAL DRUM SCHEDULE - IFC | 10 | 2023-01-04 | 2023-01-18 | 2023-04-12 | 2023-04-27 | 70
E- HAZOP |  |  | 81 | 2022-03-10 | 2022-07-06 | 2022-06-24 | 2022-10-19 | 73
SCOPE OF WORK |  |  | 50 | 2022-03-10 | 2022-05-24 | 2022-06-24 | 2022-09-14 | 79
0 | EDCDEL1480 | SCOPE OF WORK FOR E-HAZOP STUDY - ICR | 10 | 2022-03-10 | 2022-03-24 | 2022-06-24 | 2022-07-07 | 73
0 | EDCDEL1485 | SCOPE OF WORK FOR E-HAZOP STUDY - IFA | 10 | 2022-04-07 | 2022-04-21 | 2022-08-04 | 2022-08-17 | 79
0 | EDCDEL1490 | SCOPE OF WORK FOR E-HAZOP STUDY - IFC | 10 | 2022-05-10 | 2022-05-24 | 2022-09-01 | 2022-09-14 | 79
TBE |  |  | 55 | 2022-04-15 | 2022-07-06 | 2022-08-04 | 2022-10-19 | 73
0 | EDCDEL1495 | EHAZOP STUDY - TBE - ICR | 20 | 2022-04-15 | 2022-05-18 | 2022-08-04 | 2022-08-31 | 73
0 | EDCDEL1505 | EHAZOP STUDY - TBE - - IFA | 10 | 2022-06-01 | 2022-06-15 | 2022-09-15 | 2022-09-28 | 73
0 | EDCDEL1515 | EHAZOP STUDY - TBE - : IFC | 5 | 2022-06-29 | 2022-07-06 | 2022-10-13 | 2022-10-19 | 73
DRAWINGS |  |  | 146 | 2022-01-14 | 2022-08-16 | 2022-06-07 | 2023-01-30 | 118
0 | EDCGEL1000 | ELECTRICAL KEY SINGLE LINE DIAGRAM FOR OFFSHORE FACILITIES - ICR | 14 | 2022-01-14 | 2022-02-03 | 2022-06-07 | 2022-06-24 | 99
0 | EDCGEL1005 | ELECTRICAL KEY SINGLE LINE DIAGRAM FOR OFFSHORE FACILITIES - IFA | 14 | 2022-02-17 | 2022-03-09 | 2022-07-14 | 2022-08-02 | 99
0 | EDCGEL1015 | ELECTRICAL SYMBOLS & LEGENDS - ICR | 14 | 2022-03-10 | 2022-03-30 | 2022-10-26 | 2022-11-14 | 158
0 | EDCGEL1010 | ELECTRICAL KEY SINGLE LINE DIAGRAM FOR OFFSHORE FACILITIES - IFC | 19 | 2022-03-23 | 2022-04-19 | 2022-10-03 | 2022-10-27 | 132
0 | EDCGEL1030 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - POWER - ICR | 20 | 2022-03-24 | 2022-04-21 | 2022-09-14 | 2022-10-11 | 118
0 | EDCGEL1020 | ELECTRICAL SYMBOLS & LEGENDS - IFA | 14 | 2022-04-13 | 2022-05-06 | 2022-11-29 | 2022-12-20 | 158
0 | EDCGEL1045 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - LIGHTING - ICR | 14 | 2022-04-21 | 2022-05-16 | 2022-10-12 | 2022-10-31 | 118
0 | EDCGEL1060 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - EARTHING - ICR | 14 | 2022-05-10 | 2022-05-30 | 2022-10-26 | 2022-11-14 | 118
0 | EDCGEL1035 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - POWER - IFA | 14 | 2022-05-10 | 2022-05-30 | 2022-11-29 | 2022-12-20 | 142
0 | EDCGEL1025 | ELECTRICAL SYMBOLS & LEGENDS - IFC | 14 | 2022-05-20 | 2022-06-09 | 2023-01-04 | 2023-01-23 | 158
0 | EDCGEL1050 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - LIGHTING - IFA | 14 | 2022-05-30 | 2022-06-17 | 2022-11-22 | 2022-12-13 | 123
0 | EDCGEL1065 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - EARTHING - IFA | 14 | 2022-06-13 | 2022-07-01 | 2022-11-29 | 2022-12-20 | 118
0 | EDCGEL1040 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - POWER - IFC | 19 | 2022-06-13 | 2022-07-13 | 2023-01-04 | 2023-01-30 | 142
0 | EDCGEL1055 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - LIGHTING - IFC | 19 | 2022-07-01 | 2022-08-02 | 2022-12-28 | 2023-01-23 | 123
0 | EDCGEL1070 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - EARTHING - IFC | 19 | 2022-07-20 | 2022-08-16 | 2023-01-04 | 2023-01-30 | 118
CALCULATION |  |  | 147 | 2022-02-10 | 2022-09-13 | 2022-06-07 | 2023-02-27 | 118
0 | EDCGEL1240 | HV/LV CABLE SIZING CALCULATIONS - ICR | 16 | 2022-02-10 | 2022-03-04 | 2022-10-25 | 2022-11-15 | 177
0 | EDCGEL1245 | HV/LV CABLE SIZING CALCULATIONS - IFA | 15 | 2022-03-18 | 2022-04-08 | 2022-11-30 | 2022-12-22 | 177
0 | EDCGEL1180 | TRANSFORMER AND SWITCHGEAR SIZING CALCULATIONS - ICR | 15 | 2022-03-25 | 2022-04-15 | 2022-06-20 | 2022-07-13 | 58
0 | EDCGEL1195 | 24V DC UPS SIZING CALCULATIONS - ICR | 15 | 2022-04-01 | 2022-04-22 | 2022-06-07 | 2022-06-27 | 44
0 | EDCGEL1210 | LIGHTING CALCULATIONS - ICR | 15 | 2022-04-22 | 2022-05-18 | 2022-11-18 | 2022-12-12 | 144
0 | EDCGEL1225 | LIGHTNING PROTECTION CALCULATIONS - ICR | 15 | 2022-04-22 | 2022-05-18 | 2022-11-18 | 2022-12-12 | 144
0 | EDCGEL1185 | TRANSFORMER AND SWITCHGEAR SIZING CALCULATIONS - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-07-28 | 2022-08-10 | 58
0 | EDCGEL1200 | 24V DC UPS SIZING CALCULATIONS - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-07-15 | 2022-07-28 | 44
0 | EDCGEL1250 | HV/LV CABLE SIZING CALCULATIONS - IFC | 20 | 2022-04-27 | 2022-05-30 | 2023-01-06 | 2023-02-02 | 174
0 | EDCGEL1190 | TRANSFORMER AND SWITCHGEAR SIZING CALCULATIONS - IFC | 10 | 2022-06-01 | 2022-06-15 | 2022-08-25 | 2022-09-07 | 58
0 | EDCGEL1205 | 24V DC UPS SIZING CALCULATIONS - IFC | 10 | 2022-06-08 | 2022-06-22 | 2022-08-12 | 2022-08-25 | 44
0 | EDCGEL1215 | LIGHTING CALCULATIONS - IFA | 15 | 2022-06-01 | 2022-06-22 | 2022-12-27 | 2023-01-16 | 144
0 | EDCGEL1230 | LIGHTNING PROTECTION CALCULATIONS - IFA | 15 | 2022-06-01 | 2022-06-22 | 2022-12-27 | 2023-01-16 | 144
0 | EDCGEL1220 | LIGHTING CALCULATIONS - IFC | 20 | 2022-07-06 | 2022-08-08 | 2023-01-31 | 2023-02-27 | 144
0 | EDCGEL1235 | LIGHTNING PROTECTION CALCULATIONS - IFC | 20 | 2022-08-16 | 2022-09-13 | 2023-01-31 | 2023-02-27 | 118
REQUISITIONS & TBE |  |  | 188 | 2022-03-02 | 2022-11-29 | 2022-04-27 | 2023-05-16 | 117
6.6kV COMPOSITE SUBSEA CABLE |  |  | 94 | 2022-03-02 | 2022-07-20 | 2022-04-27 | 2022-09-28 | 51
REQUISITION |  |  | 50 | 2022-03-02 | 2022-05-16 | 2022-04-27 | 2022-08-17 | 65
0 | EDCMEL1000 | 6.6kV COMPOSITE SUBSEA CABLE - ISSUE MR -IRC | 10 | 2022-03-02 | 2022-03-16 | 2022-04-27 | 2022-05-13 | 40
0 | EDCMEL1005 | 6.6kV COMPOSITE SUBSEA CABLE - ISSUE MR -IIFA | 10 | 2022-03-30 | 2022-04-13 | 2022-07-04 | 2022-07-20 | 65
0 | EDCMEL1010 | 6.6kV COMPOSITE SUBSEA CABLE - ISSUE MR -IFC | 10 | 2022-04-27 | 2022-05-16 | 2022-08-04 | 2022-08-17 | 65
TBE |  |  | 61 | 2022-04-18 | 2022-07-20 | 2022-06-16 | 2022-09-28 | 51
0 | EDCMEL2010 | COMPLETE EVALUATION AND SUBMIT TBE - 6.6KV COMPOSITE SUBSEA CABLE - ICR | 20 | 2022-04-18 | 2022-05-19 | 2022-06-16 | 2022-07-18 | 40
0 | EDCMEL2015 | RECEIVE COMMENTS & ISSUE TBE - 6.6KV COMPOSITE SUBSEA CABLE - IFA | 10 | 2022-06-02 | 2022-06-16 | 2022-08-02 | 2022-08-15 | 40
0 | EDCMEL2020 | ISSUE TBE - 6.6KV COMPOSITE SUBSEA CABLE - IFC | 11 | 2022-06-30 | 2022-07-20 | 2022-09-14 | 2022-09-28 | 51
6.6kV RING MAIN UNIT (RMU) |  |  | 79 | 2022-03-24 | 2022-07-21 | 2022-05-30 | 2022-10-05 | 55
REQUISITION |  |  | 50 | 2022-03-24 | 2022-06-07 | 2022-05-30 | 2022-09-07 | 64
0 | EDCMEL1015 | 6.6kV RING MAIN UNIT (RMU) - ISSUE MR ICR | 10 | 2022-03-24 | 2022-04-07 | 2022-05-30 | 2022-06-10 | 44
0 | EDCMEL1020 | 6.6kV RING MAIN UNIT (RMU) - ISSUE MR IFA | 10 | 2022-04-21 | 2022-05-10 | 2022-07-28 | 2022-08-10 | 64
0 | EDCMEL1025 | 6.6kV RING MAIN UNIT (RMU) - ISSUE MR IFC | 10 | 2022-05-24 | 2022-06-07 | 2022-08-25 | 2022-09-07 | 64
TBE |  |  | 51 | 2022-05-06 | 2022-07-21 | 2022-07-07 | 2022-10-05 | 55
0 | EDCMEL2025 | COMPLETE EVALUATION AND SUBMIT TBE - 6.6KV RING MAIN UNIT(RMU) - ICR | 20 | 2022-05-06 | 2022-06-03 | 2022-07-07 | 2022-08-08 | 44
0 | EDCMEL2030 | RECEIVE COMMENTS & ISSUE TBE - 6.6KV RING MAIN UNIT(RMU) - IFA | 10 | 2022-06-17 | 2022-07-01 | 2022-08-24 | 2022-09-06 | 45
0 | EDCMEL2035 | ISSUE TBE - 6.6KV RING MAIN UNIT(RMU) - IFC | 11 | 2022-07-01 | 2022-07-21 | 2022-09-21 | 2022-10-05 | 55
6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS |  |  | 85 | 2022-03-25 | 2022-08-01 | 2022-06-01 | 2022-10-26 | 63
REQUISITION |  |  | 56 | 2022-03-25 | 2022-06-16 | 2022-06-01 | 2022-09-07 | 57
0 | EDCMEL1030 | 6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS - ISSUE MR - ICR | 10 | 2022-03-25 | 2022-04-08 | 2022-06-01 | 2022-06-14 | 45
0 | EDCMEL1035 | 6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS - ISSUE MR - IFA | 11 | 2022-04-22 | 2022-05-12 | 2022-07-20 | 2022-08-03 | 57
0 | EDCMEL1040 | 6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS - ISSUE MR - IFC | 15 | 2022-05-26 | 2022-06-16 | 2022-08-18 | 2022-09-07 | 57
TBE |  |  | 56 | 2022-05-10 | 2022-08-01 | 2022-07-19 | 2022-10-26 | 63
0 | EDCMEL2040 | COMPLETE EVALUATION AND SUBMIT TBE 6.6/ 0.433 KV DISTRIBUTION TRANSF'R - ICR | 15 | 2022-05-10 | 2022-05-31 | 2022-07-19 | 2022-08-08 | 47
0 | EDCMEL2045 | RECEIVE COMMENTS & ISSUE TBE - 6.6/ 0.433 KV DISTRIBUTION TRANSFORMERS - IFA | 10 | 2022-06-14 | 2022-06-28 | 2022-08-23 | 2022-09-05 | 47
0 | EDCMEL2050 | ISSUE TBE - 6.6/ 0.433 KV DISTRIBUTION TRANSFORMERS - IFC | 11 | 2022-07-15 | 2022-08-01 | 2022-10-12 | 2022-10-26 | 63
LV DISTRIBUTION BOARDS |  |  | 85 | 2022-03-28 | 2022-08-02 | 2022-06-02 | 2022-10-05 | 47
REQUISITION |  |  | 50 | 2022-03-28 | 2022-06-09 | 2022-06-02 | 2022-09-07 | 62
0 | EDCMEL1045 | LV DISTRIBUTION BOARDS - ISSUE MR - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-06-02 | 2022-06-15 | 45
0 | EDCMEL1050 | LV DISTRIBUTION BOARDS - ISSUE MR - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-07-28 | 2022-08-10 | 62
0 | EDCMEL1055 | LV DISTRIBUTION BOARDS - ISSUE MR - IFC | 10 | 2022-05-26 | 2022-06-09 | 2022-08-25 | 2022-09-07 | 62
TBE |  |  | 55 | 2022-05-12 | 2022-08-02 | 2022-07-19 | 2022-10-05 | 47
0 | EDCMEL2055 | COMPLETE EVALUATION AND SUBMIT TBE - LV DISTRIBUTION BOARDS - ICR | 15 | 2022-05-12 | 2022-06-02 | 2022-07-19 | 2022-08-08 | 45
0 | EDCMEL2060 | RECEIVE COMMENTS & ISSUE TBE - LV DISTRIBUTION BOARDS - IFA | 10 | 2022-06-16 | 2022-06-30 | 2022-08-23 | 2022-09-05 | 45
0 | EDCMEL2065 | ISSUE TBE - LV DISTRIBUTION BOARDS - IFC | 10 | 2022-07-19 | 2022-08-02 | 2022-09-22 | 2022-10-05 | 47
HV CABLE TERMINATION KITS |  |  | 85 | 2022-08-01 | 2022-11-28 | 2022-11-07 | 2023-03-27 | 84
REQUISITION |  |  | 35 | 2022-08-01 | 2022-09-19 | 2022-11-07 | 2023-02-02 | 97
0 | EDCMEL1275 | HV CABLES TERMINATION KITS - ISSUE MR - ICR | 5 | 2022-08-01 | 2022-08-08 | 2022-11-07 | 2022-11-11 | 70
0 | EDCMEL1280 | HV CABLES TERMINATION KITS - ISSUE MR - IFA | 5 | 2022-08-22 | 2022-08-29 | 2023-01-06 | 2023-01-12 | 97
0 | EDCMEL1285 | HV CABLES TERMINATION KITS - ISSUE MR - IFC | 5 | 2022-09-12 | 2022-09-19 | 2023-01-27 | 2023-02-02 | 97
TBE |  |  | 60 | 2022-09-05 | 2022-11-28 | 2022-12-23 | 2023-03-27 | 84
0 | EDCMEL2070 | COMPLETE EVALUATION AND SUBMIT TBE - HV CABLES TERMINATION KITS - ICR | 20 | 2022-09-05 | 2022-10-03 | 2022-12-23 | 2023-01-19 | 77
0 | EDCMEL2075 | RECEIVE COMMENTS & ISSUE TBE - HV CABLES TERMINATION KITS - IFA | 10 | 2022-10-17 | 2022-10-31 | 2023-02-03 | 2023-02-16 | 77
0 | EDCMEL2080 | ISSUE TBE - HV CABLES TERMINATION KITS - IFC | 10 | 2022-11-14 | 2022-11-28 | 2023-03-14 | 2023-03-27 | 84
24V DC UPS |  |  | 83 | 2022-03-30 | 2022-08-02 | 2022-06-06 | 2022-10-19 | 57
REQUISITION |  |  | 47 | 2022-03-30 | 2022-06-08 | 2022-06-06 | 2022-09-07 | 63
0 | EDCMEL1060 | 24V DC UPS - ISSUE MR - ICR | 10 | 2022-03-30 | 2022-04-13 | 2022-06-06 | 2022-06-17 | 45
0 | EDCMEL1065 | 24V DC UPS - ISSUE MR - IFA | 7 | 2022-04-27 | 2022-05-11 | 2022-08-02 | 2022-08-10 | 63
0 | EDCMEL1070 | 24V DC UPS - ISSUE MR - IFC | 10 | 2022-05-25 | 2022-06-08 | 2022-08-25 | 2022-09-07 | 63
TBE |  |  | 55 | 2022-05-12 | 2022-08-02 | 2022-07-19 | 2022-10-19 | 57
0 | EDCMEL2085 | COMPLETE EVALUATION AND SUBMIT TBE - 24V DC UPS - ICR | 15 | 2022-05-12 | 2022-06-02 | 2022-07-19 | 2022-08-08 | 45
0 | EDCMEL2090 | RECEIVE COMMENTS & ISSUE TBE - 24V DC UPS - IFA | 10 | 2022-06-16 | 2022-06-30 | 2022-08-23 | 2022-09-05 | 45
0 | EDCMEL3100 | ISSUE TBE - 24V DC UPS - IFC | 10 | 2022-07-19 | 2022-08-02 | 2022-10-06 | 2022-10-19 | 57
415V SWITCHBOARDS |  |  | 85 | 2022-03-29 | 2022-08-03 | 2022-06-02 | 2022-10-26 | 61
REQUISITION |  |  | 40 | 2022-03-29 | 2022-05-27 | 2022-06-02 | 2022-09-07 | 71
0 | EDCMEL1075 | 415V SWITCHBOARDS - ISSUE MR - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-06-02 | 2022-06-15 | 44
0 | EDCMEL1080 | 415V SWITCHBOARDS - ISSUE MR - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-07-28 | 2022-08-10 | 71
0 | EDCMEL1085 | 415V SWITCHBOARDS - ISSUE MR - IFC | 10 | 2022-05-13 | 2022-05-27 | 2022-08-25 | 2022-09-07 | 71
TBE |  |  | 55 | 2022-05-13 | 2022-08-03 | 2022-07-19 | 2022-10-26 | 61
0 | EDCMEL3105 | COMPLETE EVALUATION AND SUBMIT TBE - 415V SWITCHBOARDS - ICR | 15 | 2022-05-13 | 2022-06-03 | 2022-07-19 | 2022-08-08 | 44
0 | EDCMEL3110 | RECEIVE COMMENTS & ISSUE TBE - 415V SWITCHBOARDS - IFA | 10 | 2022-06-17 | 2022-07-01 | 2022-08-25 | 2022-09-07 | 46
0 | EDCMEL3115 | ISSUE TBE - 415V SWITCHBOARDS - IFC | 10 | 2022-07-20 | 2022-08-03 | 2022-10-13 | 2022-10-26 | 61
BIRD DETERENT SYSTEM |  |  | 91 | 2022-05-16 | 2022-09-23 | 2022-08-30 | 2023-01-06 | 74
REQUISITION |  |  | 50 | 2022-05-16 | 2022-07-28 | 2022-08-30 | 2022-12-09 | 95
0 | EDCMEL1090 | BIRD DETERRENT SYSTEM - ISSUE MR - ICR | 10 | 2022-05-16 | 2022-05-30 | 2022-08-30 | 2022-09-12 | 73
0 | EDCMEL1095 | BIRD DETERRENT SYSTEM - ISSUE MR - IFA | 10 | 2022-06-13 | 2022-06-27 | 2022-10-27 | 2022-11-09 | 95
0 | EDCMEL1100 | BIRD DETERRENT SYSTEM - ISSUE MR - IFC | 10 | 2022-07-14 | 2022-07-28 | 2022-11-24 | 2022-12-09 | 95
TBE |  |  | 61 | 2022-06-27 | 2022-09-23 | 2022-10-11 | 2023-01-06 | 74
0 | EDCMEL3120 | COMPLETE EVALUATION AND SUBMIT TBE - BIRD DETERRENT SYSTEM - ICR | 20 | 2022-06-27 | 2022-07-28 | 2022-10-11 | 2022-11-07 | 73
0 | EDCMEL3125 | RECEIVE COMMENTS & ISSUE TBE - BIRD DETERRENT SYSTEM - IFA | 10 | 2022-08-11 | 2022-08-25 | 2022-11-23 | 2022-12-08 | 74
0 | EDCMEL3130 | ISSUE TBE - BIRD DETERRENT SYSTEM - IFC | 11 | 2022-09-08 | 2022-09-23 | 2022-12-23 | 2023-01-06 | 74
NAVIGATIONAL AID SYSTEM |  |  | 91 | 2022-04-27 | 2022-09-09 | 2022-08-03 | 2022-12-09 | 64
REQUISITION |  |  | 50 | 2022-04-27 | 2022-07-14 | 2022-08-03 | 2022-11-11 | 87
0 | EDCMEL1105 | NAVIGATIONAL AIDS SYSTEM - ISSUE MR - ICR | 10 | 2022-04-27 | 2022-05-16 | 2022-08-03 | 2022-08-16 | 64
0 | EDCMEL1110 | NAVIGATIONAL AIDS SYSTEM - ISSUE MR - IFA | 10 | 2022-05-30 | 2022-06-13 | 2022-10-03 | 2022-10-14 | 87
0 | EDCMEL1115 | NAVIGATIONAL AIDS SYSTEM - ISSUE MR - IFC | 10 | 2022-06-27 | 2022-07-14 | 2022-10-31 | 2022-11-11 | 87
TBE |  |  | 61 | 2022-06-13 | 2022-09-09 | 2022-09-14 | 2022-12-09 | 64
0 | EDCMEL3135 | COMPLETE EVALUATION AND SUBMIT TBE - NAVIGATIONAL AIDS SYSTEM - ICR | 20 | 2022-06-13 | 2022-07-14 | 2022-09-14 | 2022-10-11 | 64
0 | EDCMEL3140 | RECEIVE COMMENTS & ISSUE TBE - NAVIGATIONAL AIDS SYSTEM - IFA | 10 | 2022-07-28 | 2022-08-11 | 2022-10-26 | 2022-11-08 | 64
0 | EDCMEL3145 | ISSUE TBE - NAVIGATIONAL AIDS SYSTEM - IFC | 11 | 2022-08-25 | 2022-09-09 | 2022-11-23 | 2022-12-09 | 64
HIGH VOLTAGE CABLES |  |  | 86 | 2022-07-25 | 2022-11-22 | 2022-11-07 | 2023-03-02 | 71
REQUISITION |  |  | 39 | 2022-07-25 | 2022-09-16 | 2022-11-07 | 2023-02-02 | 98
0 | EDCMEL1120 | HIGH VOLTAGE CABLES - ISSUE MR - ICR | 5 | 2022-07-25 | 2022-08-01 | 2022-11-07 | 2022-11-11 | 75
0 | EDCMEL1125 | HIGH VOLTAGE CABLES - ISSUE MR - IFA | 10 | 2022-08-15 | 2022-08-29 | 2023-01-02 | 2023-01-13 | 98
0 | EDCMEL1130 | HIGH VOLTAGE CABLES - ISSUE MR - IFC | 4 | 2022-09-12 | 2022-09-16 | 2023-01-30 | 2023-02-02 | 98
TBE |  |  | 56 | 2022-09-05 | 2022-11-22 | 2022-12-14 | 2023-03-02 | 71
0 | EDCMEL3150 | COMPLETE EVALUATION AND SUBMIT TBE - HIGH VOLTAGE CABLES - ICR | 15 | 2022-09-05 | 2022-09-26 | 2022-12-14 | 2023-01-03 | 70
0 | EDCMEL3155 | RECEIVE COMMENTS & ISSUE TBE - HIGH VOLTAGE CABLES - IFA | 10 | 2022-10-10 | 2022-10-24 | 2023-01-19 | 2023-02-01 | 71
0 | EDCMEL3160 | ISSUE TBE - HIGH VOLTAGE CABLES - IFC | 11 | 2022-11-07 | 2022-11-22 | 2023-02-16 | 2023-03-02 | 71
LOW VOLTAGE CABLES |  |  | 81 | 2022-08-01 | 2022-11-22 | 2022-11-14 | 2023-03-16 | 81
REQUISITION |  |  | 35 | 2022-08-01 | 2022-09-19 | 2022-11-14 | 2023-02-02 | 97
0 | EDCMEL1135 | LOW VOLTAGE CABLES - ISSUE MR - ICR | 5 | 2022-08-01 | 2022-08-08 | 2022-11-14 | 2022-11-18 | 75
0 | EDCMEL1140 | LOW VOLTAGE CABLES - ISSUE MR - IFA | 5 | 2022-08-22 | 2022-08-29 | 2023-01-06 | 2023-01-12 | 97
0 | EDCMEL1145 | LOW VOLTAGE CABLES - ISSUE MR - IFC | 5 | 2022-09-12 | 2022-09-19 | 2023-01-27 | 2023-02-02 | 97
TBE |  |  | 56 | 2022-09-05 | 2022-11-22 | 2022-12-21 | 2023-03-16 | 81
0 | EDCMEL3165 | COMPLETE EVALUATION AND SUBMIT TBE - LOW VOLTAGE CABLES - ICR | 15 | 2022-09-05 | 2022-09-26 | 2022-12-21 | 2023-01-10 | 75
0 | EDCMEL3170 | RECEIVE COMMENTS & ISSUE TBE - LOW VOLTAGE CABLES - IFA | 10 | 2022-10-10 | 2022-10-24 | 2023-01-27 | 2023-02-09 | 77
0 | EDCMEL3175 | ISSUE TBE - LOW VOLTAGE CABLES - IFC | 11 | 2022-11-07 | 2022-11-22 | 2023-03-02 | 2023-03-16 | 81
CABLE TRAYS & LADDERS |  |  | 80 | 2022-08-01 | 2022-11-21 | 2022-11-22 | 2023-03-17 | 83
REQUISITION |  |  | 35 | 2022-08-01 | 2022-09-19 | 2022-11-22 | 2023-02-02 | 97
0 | EDCMEL1150 | CABLE TRAYS & LADDERS - ISSUE MR - ICR | 5 | 2022-08-01 | 2022-08-08 | 2022-11-22 | 2022-11-28 | 81
0 | EDCMEL1155 | CABLE TRAYS & LADDERS - ISSUE MR - IFA | 5 | 2022-08-22 | 2022-08-29 | 2023-01-06 | 2023-01-12 | 97
0 | EDCMEL1160 | CABLE TRAYS & LADDERS - ISSUE MR - IFC | 5 | 2022-09-12 | 2022-09-19 | 2023-01-27 | 2023-02-02 | 97
TBE |  |  | 55 | 2022-09-05 | 2022-11-21 | 2022-12-29 | 2023-03-17 | 83
0 | EDCMEL3180 | COMPLETE EVALUATION AND SUBMIT TBE - CABLE TRAYS & LADDERS - ICR | 15 | 2022-09-05 | 2022-09-26 | 2022-12-29 | 2023-01-18 | 81
0 | EDCMEL3185 | RECEIVE COMMENTS & ISSUE TBE - CABLE TRAYS & LADDERS - IFA | 10 | 2022-10-10 | 2022-10-24 | 2023-02-06 | 2023-02-17 | 83
0 | EDCMEL3190 | ISSUE TBE - CABLE TRAYS & LADDERS - IFC | 10 | 2022-11-07 | 2022-11-21 | 2023-03-06 | 2023-03-17 | 83
LIGHTING FIXTURES & ACCESSORIES |  |  | 78 | 2022-08-02 | 2022-11-18 | 2022-11-29 | 2023-03-23 | 88
REQUISITION |  |  | 34 | 2022-08-02 | 2022-09-19 | 2022-11-29 | 2023-02-02 | 97
0 | EDCMEL1165 | LIGHTING FIXTURES & ACCESSORIES - ISSUE MR - ICR | 5 | 2022-08-02 | 2022-08-09 | 2022-11-29 | 2022-12-07 | 85
0 | EDCMEL1170 | LIGHTING FIXTURES & ACCESSORIES - ISSUE MR - IFA | 5 | 2022-08-23 | 2022-08-30 | 2023-01-09 | 2023-01-13 | 97
0 | EDCMEL1175 | LIGHTING FIXTURES & ACCESSORIES - ISSUE MR - IFC | 4 | 2022-09-13 | 2022-09-19 | 2023-01-30 | 2023-02-02 | 97
TBE |  |  | 55 | 2022-09-02 | 2022-11-18 | 2023-01-06 | 2023-03-23 | 88
0 | EDCMEL3195 | COMPLETE EVALUATION AND SUBMIT TBE - LIGHTING FIXTURE & ACCESSORIES - ICR | 15 | 2022-09-02 | 2022-09-23 | 2023-01-06 | 2023-01-26 | 88
0 | EDCMEL3200 | RECEIVE COMMENTS & ISSUE TBE - LIGHTING FIXTURE & ACCESSORIES - IFA | 10 | 2022-10-07 | 2022-10-21 | 2023-02-10 | 2023-02-23 | 88
0 | EDCMEL3205 | ISSUE TBE - LIGHTING FIXTURE & ACCESSORIES - IFC | 10 | 2022-11-04 | 2022-11-18 | 2023-03-10 | 2023-03-23 | 88
SOCKETS & ISOLATING SWITCHES |  |  | 80 | 2022-08-03 | 2022-11-23 | 2022-11-30 | 2023-04-14 | 101
REQUISITION |  |  | 33 | 2022-08-03 | 2022-09-19 | 2022-11-30 | 2023-02-02 | 97
0 | EDCMEL1185 | SOCKETS & ISOLATING SWITCHES - ISSUE MR - ICR | 5 | 2022-08-03 | 2022-08-10 | 2022-11-30 | 2022-12-08 | 85
0 | EDCMEL1190 | SOCKETS & ISOLATING SWITCHES - ISSUE MR - IFA | 4 | 2022-08-24 | 2022-08-30 | 2023-01-10 | 2023-01-13 | 97
0 | EDCMEL1195 | SOCKETS & ISOLATING SWITCHES - ISSUE MR - IFC | 4 | 2022-09-13 | 2022-09-19 | 2023-01-30 | 2023-02-02 | 97
TBE |  |  | 55 | 2022-09-07 | 2022-11-23 | 2023-01-30 | 2023-04-14 | 101
0 | EDCMEL3210 | COMPLETE EVALUATION AND SUBMIT TBE - SOCKETS & ISOLATING SWITCHES - ICR | 15 | 2022-09-07 | 2022-09-28 | 2023-01-30 | 2023-02-17 | 101
0 | EDCMEL3215 | RECEIVE COMMENTS & ISSUE TBE - SOCKETS & ISOLATING SWITCHES - IFA | 10 | 2022-10-12 | 2022-10-26 | 2023-03-06 | 2023-03-17 | 101
0 | EDCMEL3220 | ISSUE TBE - SOCKETS & ISOLATING SWITCHES - IFC | 10 | 2022-11-09 | 2022-11-23 | 2023-04-03 | 2023-04-14 | 101
ELECTRICAL JUNCTION BOXES |  |  | 81 | 2022-08-04 | 2022-11-25 | 2022-12-05 | 2023-04-26 | 105
REQUISITION |  |  | 32 | 2022-08-04 | 2022-09-19 | 2022-12-05 | 2023-02-02 | 97
0 | EDCMEL1200 | ELECTRICAL JUNCTION BOXES - ISSUE MR - ICR | 5 | 2022-08-04 | 2022-08-11 | 2022-12-05 | 2022-12-09 | 85
0 | EDCMEL1205 | ELECTRICAL JUNCTION BOXES - ISSUE MR - IFA | 4 | 2022-08-25 | 2022-08-31 | 2023-01-11 | 2023-01-16 | 97
0 | EDCMEL1210 | ELECTRICAL JUNCTION BOXES - ISSUE MR - IFC | 3 | 2022-09-14 | 2022-09-19 | 2023-01-31 | 2023-02-02 | 97
TBE |  |  | 56 | 2022-09-08 | 2022-11-25 | 2023-01-24 | 2023-04-26 | 105
0 | EDCMEL3225 | COMPLETE EVALUATION AND SUBMIT TBE - ELECTRICAL JUNCTION BOXES - ICR | 15 | 2022-09-08 | 2022-09-29 | 2023-01-24 | 2023-02-13 | 96
0 | EDCMEL3230 | RECEIVE COMMENTS & ISSUE TBE - ELECTRICAL JUNCTION BOXES - IFA | 10 | 2022-10-13 | 2022-10-27 | 2023-03-02 | 2023-03-15 | 98
0 | EDCMEL3235 | ISSUE TBE - ELECTRICAL JUNCTION BOXES - IFC | 11 | 2022-11-10 | 2022-11-25 | 2023-04-10 | 2023-04-26 | 105
EARTHING MATERIAL & ACCESSORIES |  |  | 81 | 2022-08-04 | 2022-11-25 | 2022-12-06 | 2023-05-16 | 119
REQUISITION |  |  | 32 | 2022-08-04 | 2022-09-19 | 2022-12-06 | 2023-02-02 | 97
0 | EDCMEL1215 | EARTHING MATERIAL & ACCESSORIES - ISSUE MR - ICR | 5 | 2022-08-04 | 2022-08-11 | 2022-12-06 | 2022-12-12 | 86
0 | EDCMEL1220 | EARTHING MATERIAL & ACCESSORIES - ISSUE MR - IFA | 4 | 2022-08-25 | 2022-08-31 | 2023-01-11 | 2023-01-16 | 97
0 | EDCMEL1225 | EARTHING MATERIAL & ACCESSORIES - ISSUE MR - IFC | 3 | 2022-09-14 | 2022-09-19 | 2023-01-31 | 2023-02-02 | 97
TBE |  |  | 56 | 2022-09-08 | 2022-11-25 | 2023-02-13 | 2023-05-16 | 119
0 | EDCMEL3240 | COMPLETE EVALUATION AND SUBMIT TBE- EARTHING MATERIALS & ACCESSOTIES - ICR | 15 | 2022-09-08 | 2022-09-29 | 2023-02-13 | 2023-03-03 | 110
0 | EDCMEL3245 | RECEIVE COMMENTS & ISSUE TBE- EARTHING MATERIALS & ACCESSOTIES - IFA | 10 | 2022-10-13 | 2022-10-27 | 2023-03-22 | 2023-04-04 | 112
0 | EDCMEL3250 | ISSUE TBE - EARTHING MATERIALS & ACCESSOTIES - IFC | 11 | 2022-11-10 | 2022-11-25 | 2023-05-02 | 2023-05-16 | 119
ELECTRICAL CABLE GLANDS |  |  | 81 | 2022-08-04 | 2022-11-25 | 2022-12-05 | 2023-04-11 | 96
REQUISITION |  |  | 32 | 2022-08-04 | 2022-09-19 | 2022-12-05 | 2023-02-02 | 97
0 | EDCMEL1230 | ELECTRICAL CABLE GLANDS - ISSUE MR - ICR | 5 | 2022-08-04 | 2022-08-11 | 2022-12-05 | 2022-12-09 | 85
0 | EDCMEL1235 | ELECTRICAL CABLE GLANDS - ISSUE MR - IFA | 4 | 2022-08-25 | 2022-08-31 | 2023-01-11 | 2023-01-16 | 97
0 | EDCMEL1240 | ELECTRICAL CABLE GLANDS - ISSUE MR - IFC | 3 | 2022-09-14 | 2022-09-19 | 2023-01-31 | 2023-02-02 | 97
TBE |  |  | 56 | 2022-09-08 | 2022-11-25 | 2023-01-09 | 2023-04-11 | 96
0 | EDCMEL3255 | COMPLETE EVALUATION AND SUBMIT TBE - ELECTRICAL CABLE GLANDS - ICR | 15 | 2022-09-08 | 2022-09-29 | 2023-01-09 | 2023-01-27 | 85
0 | EDCMEL3260 | RECEIVE COMMENTS & ISSUE TBE - ELECTRICAL CABLE GLANDS - IFA | 10 | 2022-10-13 | 2022-10-27 | 2023-02-15 | 2023-02-28 | 87
0 | EDCMEL3265 | ISSUE TBE - ELECTRICAL CABLE GLANDS - IFC | 11 | 2022-11-10 | 2022-11-25 | 2023-03-28 | 2023-04-11 | 96
ELECTRICAL BOLTS & NUTS |  |  | 81 | 2022-08-08 | 2022-11-29 | 2022-12-08 | 2023-04-07 | 92
REQUISITION |  |  | 45 | 2022-08-08 | 2022-10-10 | 2022-12-08 | 2023-03-03 | 103
0 | EDCMEL1245 | ELECTRICAL BOLTS & NUTS - ISSUE MR - ICR | 5 | 2022-08-08 | 2022-08-15 | 2022-12-08 | 2022-12-14 | 86
0 | EDCMEL1250 | ELECTRICAL BOLTS & NUTS - ISSUE MR - IFA | 10 | 2022-08-29 | 2022-09-12 | 2023-01-23 | 2023-02-03 | 103
0 | EDCMEL1255 | ELECTRICAL BOLTS & NUTS - ISSUE MR - IFC | 10 | 2022-09-26 | 2022-10-10 | 2023-02-20 | 2023-03-03 | 103
TBE |  |  | 56 | 2022-09-12 | 2022-11-29 | 2023-01-12 | 2023-04-07 | 92
0 | EDCMEL3270 | COMPLETE EVALUATION AND SUBMIT TBE - ELECTRICAL BOLTS & NUTS - ICR | 15 | 2022-09-12 | 2022-10-03 | 2023-01-12 | 2023-02-01 | 86
0 | EDCMEL3275 | RECEIVE COMMENTS & ISSUE TBE - ELECTRICAL BOLTS & NUTS - IFA | 10 | 2022-10-17 | 2022-10-31 | 2023-02-20 | 2023-03-03 | 88
0 | EDCMEL3280 | ISSUE TBE - ELECTRICAL BOLTS & NUTS - IFC | 11 | 2022-11-14 | 2022-11-29 | 2023-03-24 | 2023-04-07 | 92
INSTRUMENTATION & CONTROL |  |  | 260 | 2021-12-30 | 2023-01-11 | 2022-03-02 | 2023-04-27 | 75
DOCUMENTS |  |  | 260 | 2021-12-30 | 2023-01-11 | 2022-03-02 | 2023-04-27 | 75
DESIGN BASIS |  |  | 60 | 2021-12-30 | 2022-03-25 | 2022-03-02 | 2022-07-22 | 80
0 | EDCDIN1000 | INSTRUMENTATION AND CONTROL DESIGN BASIS - ICR | 20 | 2021-12-30 | 2022-01-28 | 2022-03-02 | 2022-03-29 | 43
0 | EDCDIN1005 | INSTRUMENTATION AND CONTROL DESIGN BASIS - IFA | 10 | 2022-02-11 | 2022-02-25 | 2022-04-13 | 2022-04-26 | 43
0 | EDCDIN1010 | INSTRUMENTATION AND CONTROL DESIGN BASIS - IFC | 10 | 2022-03-11 | 2022-03-25 | 2022-07-06 | 2022-07-22 | 80
NARRATIVES |  |  | 56 | 2022-10-21 | 2023-01-11 | 2023-02-07 | 2023-04-27 | 75
0 | EDCDIN1015 | CONTROL & LOGIC NARRATIVES - ICR | 10 | 2022-10-21 | 2022-11-04 | 2023-02-07 | 2023-02-20 | 75
0 | EDCDIN1020 | CONTROL & LOGIC NARRATIVES - IFA | 10 | 2022-11-16 | 2022-11-30 | 2023-03-03 | 2023-03-16 | 75
0 | EDCDIN1025 | CONTROL & LOGIC NARRATIVES - IFC | 20 | 2022-12-14 | 2023-01-11 | 2023-03-29 | 2023-04-27 | 75
PHILOSOPHIES / REPORTS / SCHEDULE |  |  | 189 | 2022-02-10 | 2022-11-10 | 2022-06-21 | 2023-04-19 | 113
0 | EDCDIN1120 | INSTRUMENT CONTROL & SAFEGUARDING PHILOSOPHY - ICR | 16 | 2022-02-10 | 2022-03-04 | 2022-07-27 | 2022-08-17 | 113
0 | EDCDIN1030 | PROCESS (ESD & HIPPS) SIL DETERMINATION PROCEDURE - ICR | 15 | 2022-03-15 | 2022-04-05 | 2022-06-21 | 2022-07-14 | 67
0 | EDCDIN1125 | INSTRUMENT CONTROL & SAFEGUARDING PHILOSOPHY - IFA | 15 | 2022-03-16 | 2022-04-06 | 2022-08-30 | 2022-09-19 | 113
0 | EDCDIN1035 | PROCESS (ESD & HIPPS) SIL DETERMINATION PROCEDURE - IFA | 15 | 2022-04-19 | 2022-05-13 | 2022-09-01 | 2022-09-21 | 91
0 | EDCDIN1130 | INSTRUMENT CONTROL & SAFEGUARDING PHILOSOPHY - IFC | 20 | 2022-04-18 | 2022-05-19 | 2022-09-30 | 2022-10-27 | 113
0 | EDCDIN1105 | ALARM PHILOSOPHY - ICR | 10 | 2022-05-19 | 2022-06-02 | 2023-01-26 | 2023-02-08 | 175
0 | EDCDIN1075 | POWER CONSUMPTION & HEAT DISSIPATION CALCULATIONS - ICR | 10 | 2022-05-24 | 2022-06-07 | 2022-12-29 | 2023-01-11 | 152
0 | EDCDIN1060 | CALCULATION NOTE FOR WELLHEAD HYDRAULIC SUPPLY CONSUMPTION - ICR | 25 | 2022-05-05 | 2022-06-09 | 2022-09-26 | 2022-10-28 | 99
0 | EDCDIN1040 | PROCESS (ESD & HIPPS) SIL DETERMINATION PROCEDURE - IFC | 20 | 2022-05-27 | 2022-06-24 | 2022-10-06 | 2022-11-02 | 91
0 | EDCDIN1110 | ALARM PHILOSOPHY - IFA | 10 | 2022-06-16 | 2022-06-30 | 2023-02-23 | 2023-03-08 | 175
0 | EDCDIN1045 | PROCEDURE FOR SIL ASSESSMENT AND EVALUATION OF F&G SYSTEM EFFECTIVENESS - ICR | 10 | 2022-06-17 | 2022-07-01 | 2022-09-30 | 2022-10-13 | 72
0 | EDCDIN1080 | POWER CONSUMPTION & HEAT DISSIPATION CALCULATIONS - IFA | 10 | 2022-06-21 | 2022-07-05 | 2023-01-26 | 2023-02-08 | 152
0 | EDCDIN1135 | SAFETY LIFE CYCLE ACTIVITY REPORT (ESD & HIPPS) - ICR | 10 | 2022-07-19 | 2022-08-02 | 2022-10-20 | 2022-11-02 | 67
0 | EDCDIN1065 | CALCULATION NOTE FOR WELLHEAD HYDRAULIC SUPPLY CONSUMPTION - IFA | 25 | 2022-06-23 | 2022-08-02 | 2022-11-14 | 2022-12-20 | 99
0 | EDCDIN1050 | PROCEDURE FOR SIL ASSESSMENT AND EVALUATION OF F&G SYSTEM EFFECTIVENESS - IFA | 10 | 2022-07-20 | 2022-08-03 | 2022-10-31 | 2022-11-11 | 73
0 | EDCDIN1085 | POWER CONSUMPTION & HEAT DISSIPATION CALCULATIONS - IFC | 10 | 2022-07-22 | 2022-08-05 | 2023-02-23 | 2023-03-08 | 152
0 | EDCDIN1150 | F&G SYSTEM EFFECTIVENESS STUDY AND SAFETY LIFE CYCLE ACTIVITY REPORT (F&G SYSTEM) - ICR | 9 | 2022-07-28 | 2022-08-10 | 2022-10-31 | 2022-11-10 | 67
0 | EDCDIN1115 | ALARM PHILOSOPHY - IFC | 20 | 2022-07-19 | 2022-08-16 | 2023-03-23 | 2023-04-19 | 175
0 | EDCDIN1140 | SAFETY LIFE CYCLE ACTIVITY REPORT (ESD & HIPPS) - IFA | 10 | 2022-08-16 | 2022-08-30 | 2022-11-21 | 2022-12-06 | 69
0 | EDCDIN1155 | F&G SYSTEM EFFECTIVENESS STUDY AND SAFETY LIFE CYCLE ACTIVITY REPORT (F&G SYSTEM) - IFA | 10 | 2022-08-22 | 2022-09-05 | 2022-11-23 | 2022-12-08 | 67
0 | EDCDIN1055 | PROCEDURE FOR SIL ASSESSMENT AND EVALUATION OF F&G SYSTEM EFFECTIVENESS - IFC | 15 | 2022-08-17 | 2022-09-07 | 2022-11-28 | 2022-12-20 | 73
0 | EDCDIN1090 | INSTRUMENT CABLE DRUM SCHEDULE - ICR | 10 | 2022-09-01 | 2022-09-15 | 2023-01-05 | 2023-01-18 | 88
0 | EDCDIN1145 | SAFETY LIFE CYCLE ACTIVITY REPORT (ESD & HIPPS) - IFC | 10 | 2022-09-13 | 2022-09-27 | 2022-12-21 | 2023-01-03 | 69
0 | EDCDIN1160 | F&G SYSTEM EFFECTIVENESS STUDY AND SAFETY LIFE CYCLE ACTIVITY REPORT (F&G SYSTEM) - IFC | 20 | 2022-09-15 | 2022-10-13 | 2022-12-21 | 2023-01-17 | 67
0 | EDCDIN1095 | INSTRUMENT CABLE DRUM SCHEDULE - IFA | 10 | 2022-09-29 | 2022-10-13 | 2023-02-02 | 2023-02-15 | 88
0 | EDCDIN1070 | CALCULATION NOTE FOR WELLHEAD HYDRAULIC SUPPLY CONSUMPTION - IFC | 25 | 2022-09-15 | 2022-10-20 | 2022-12-21 | 2023-01-24 | 67
0 | EDCDIN1100 | INSTRUMENT CABLE DRUM SCHEDULE - IFC | 10 | 2022-10-27 | 2022-11-10 | 2023-03-02 | 2023-03-15 | 88
SCOPE OF WORK |  |  | 55 | 2022-04-05 | 2022-06-24 | 2022-07-15 | 2022-10-06 | 72
0 | EDCDIN1165 | SOW FOR FOR SIL CLASSIFICATION ASSESSMENT OF PROCESS (ESD/HIPPS) & F&G SAFETY INSTRUMENTED FUNCTIONS - ICR | 15 | 2022-04-05 | 2022-04-26 | 2022-07-15 | 2022-08-04 | 67
0 | EDCDIN1170 | SOW FOR FOR SIL CLASSIFICATION ASSESSMENT OF PROCESS (ESD/HIPPS) & F&G SAFETY INSTRUMENTED FUNCTIONS - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-08-26 | 2022-09-08 | 72
0 | EDCDIN1175 | SOW FOR FOR SIL CLASSIFICATION ASSESSMENT OF PROCESS (ESD/HIPPS) & F&G SAFETY INSTRUMENTED FUNCTIONS - IFC | 10 | 2022-06-10 | 2022-06-24 | 2022-09-23 | 2022-10-06 | 72
TBE |  |  | 36 | 2022-05-25 | 2022-07-19 | 2022-08-31 | 2022-10-19 | 67
SIL CLASSIFICATION ASSESSMENT OF PROCESS (ESD/HIPPS) & F&G SAFETY INSTRUMENTED FUNCTIONS |  |  | 36 | 2022-05-25 | 2022-07-19 | 2022-08-31 | 2022-10-19 | 67
0 | EDCDIN2000 | ISSUE TBE : SIL STUDY - ICR | 10 | 2022-05-25 | 2022-06-08 | 2022-08-31 | 2022-09-13 | 67
0 | EDCDIN2005 | ISSUE TBE : SIL STUDY - IFA | 5 | 2022-06-22 | 2022-06-29 | 2022-09-28 | 2022-10-04 | 67
0 | EDCDIN2010 | ISSUE TBE : SIL STUDY - IFC | 1 | 2022-07-18 | 2022-07-19 | 2022-10-19 | 2022-10-19 | 67
SPECIFICATIONS |  |  | 84 | 2022-02-25 | 2022-06-28 | 2022-04-27 | 2023-01-10 | 136
0 | EDCDIN1195 | SPECIFICATION FOR HIPPS - ICR | 10 | 2022-02-25 | 2022-03-11 | 2022-04-27 | 2022-05-13 | 43
0 | EDCDIN1210 | SPECIFICATION FOR WELLHEAD CONTROL PANELS - ICR | 10 | 2022-02-25 | 2022-03-11 | 2022-04-27 | 2022-05-13 | 43
0 | EDCDIN1180 | SPECIFICATION FOR INTEGRATED CONTROL AND SAFETY SYSTEM (ICSS) - ICR | 10 | 2022-03-04 | 2022-03-18 | 2022-05-24 | 2022-06-06 | 54
0 | EDCDIN1225 | INSTRUMENT SPECIFICATION FOR PACKAGED EQUIPMENT - ICR | 11 | 2022-03-08 | 2022-03-23 | 2022-05-11 | 2022-05-25 | 43
0 | EDCDIN1300 | SPECIFICATION FOR PRESSURE RELIEF VALVES - ICR | 11 | 2022-03-08 | 2022-03-23 | 2022-05-12 | 2022-05-26 | 44
0 | EDCDIN1240 | SPECIFICATION FOR WET GAS FLOW METER (WGFM) I.E, MULTI-PHASE FLOW METER (MPFM) - ICR | 11 | 2022-03-08 | 2022-03-23 | 2022-05-11 | 2022-05-25 | 43
0 | EDCDIN1285 | SPECIFICATION FOR MOTOR OPERATED VALVE (MOV)- ICR | 11 | 2022-03-08 | 2022-03-23 | 2022-05-11 | 2022-05-25 | 43
0 | EDCDIN1255 | SPECIFICATION FOR ACTUATED ON-OFF VALVES - ICR | 11 | 2022-03-08 | 2022-03-23 | 2022-05-11 | 2022-05-25 | 43
0 | EDCDIN1400 | SPECIFICATION FOR INJECTION RATE CONTROL DEVICE (IRCD) SKID - ICR | 10 | 2022-03-11 | 2022-03-25 | 2022-05-31 | 2022-06-13 | 54
0 | EDCDIN1270 | SPECIFICATION FOR CHOKE VALVES - ICR | 14 | 2022-03-08 | 2022-03-28 | 2022-05-11 | 2022-05-30 | 43
0 | EDCDIN1330 | SPECIFICATION FOR FIRE & GAS DETECTORS/DEVICES - ICR | 10 | 2022-03-17 | 2022-03-31 | 2022-05-31 | 2022-06-13 | 50
0 | EDCDIN1315 | SPECIFICATION FOR FIELD INSTRUMENTS - ICR | 10 | 2022-03-17 | 2022-03-31 | 2022-05-23 | 2022-06-03 | 44
0 | EDCDIN1200 | SPECIFICATION FOR HIPPS - IFA | 10 | 2022-03-25 | 2022-04-08 | 2022-07-14 | 2022-07-27 | 73
0 | EDCDIN1215 | SPECIFICATION FOR WELLHEAD CONTROL PANELS - IFA | 10 | 2022-03-25 | 2022-04-08 | 2022-07-13 | 2022-07-26 | 72
0 | EDCDIN1345 | SPECIFICATION FOR INSTRUMENT & CONTROL CABLE - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-06-14 | 2022-06-27 | 50
0 | EDCDIN1375 | SPECIFICATION FOR INSTRUMENT INSTALLATION - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-10-17 | 2022-10-28 | 136
0 | EDCDIN1360 | SPECIFICATION FOR INSTRUMENT BULK MATERIAL - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-06-14 | 2022-06-27 | 50
0 | EDCDIN1185 | SPECIFICATION FOR INTEGRATED CONTROL AND SAFETY SYSTEM (ICSS) - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-07-14 | 2022-07-27 | 68
0 | EDCDIN1230 | INSTRUMENT SPECIFICATION FOR PACKAGED EQUIPMENT - IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-06-27 | 2022-07-13 | 55
0 | EDCDIN1260 | SPECIFICATION FOR ACTUATED ON-OFF VALVES - IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-07-14 | 2022-07-27 | 65
0 | EDCDIN1290 | SPECIFICATION FOR MOTOR OPERATED VALVE (MOV)- IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-07-14 | 2022-07-27 | 65
0 | EDCDIN1305 | SPECIFICATION FOR PRESSURE RELIEF VALVES - IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-10-05 | 2022-10-18 | 124
0 | EDCDIN1245 | SPECIFICATION FOR WET GAS FLOW METER (WGFM) I.E, MULTI-PHASE FLOW METER (MPFM) - IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-07-14 | 2022-07-27 | 65
0 | EDCDIN1405 | SPECIFICATION FOR INJECTION RATE CONTROL DEVICE (IRCD) SKID - IFA | 10 | 2022-04-08 | 2022-04-22 | 2022-08-25 | 2022-09-07 | 93
0 | EDCDIN1275 | SPECIFICATION FOR CHOKE VALVES - IFA | 10 | 2022-04-11 | 2022-04-25 | 2022-06-14 | 2022-06-27 | 43
0 | EDCDIN1320 | SPECIFICATION FOR FIELD INSTRUMENTS - IFA | 10 | 2022-04-14 | 2022-04-28 | 2022-08-03 | 2022-08-16 | 73
0 | EDCDIN1335 | SPECIFICATION FOR FIRE & GAS DETECTORS/DEVICES - IFA | 10 | 2022-04-14 | 2022-04-28 | 2022-10-13 | 2022-10-26 | 124
0 | EDCDIN1350 | SPECIFICATION FOR INSTRUMENT & CONTROL CABLE - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-09-09 | 2022-09-22 | 90
0 | EDCDIN1365 | SPECIFICATION FOR INSTRUMENT BULK MATERIAL - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-10-25 | 2022-11-07 | 122
0 | EDCDIN1380 | SPECIFICATION FOR INSTRUMENT INSTALLATION - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-11-14 | 2022-11-25 | 136
0 | EDCDIN1205 | SPECIFICATION FOR HIPPS - IFC | 15 | 2022-04-22 | 2022-05-18 | 2022-12-08 | 2022-12-28 | 156
0 | EDCDIN1190 | SPECIFICATION FOR INTEGRATED CONTROL AND SAFETY SYSTEM (ICSS) - IFC | 15 | 2022-04-29 | 2022-05-25 | 2022-12-08 | 2022-12-28 | 151
0 | EDCDIN1220 | SPECIFICATION FOR WELLHEAD CONTROL PANELS - IFC | 20 | 2022-04-22 | 2022-05-25 | 2022-08-10 | 2022-09-06 | 72
0 | EDCDIN1280 | SPECIFICATION FOR CHOKE VALVES - IFC | 10 | 2022-05-12 | 2022-05-26 | 2022-08-11 | 2022-08-24 | 62
0 | EDCDIN1410 | SPECIFICATION FOR INJECTION RATE CONTROL DEVICE (IRCD) SKID - IFC | 15 | 2022-05-11 | 2022-06-01 | 2022-10-20 | 2022-11-09 | 113
0 | EDCDIN1235 | INSTRUMENT SPECIFICATION FOR PACKAGED EQUIPMENT - IFC | 20 | 2022-05-09 | 2022-06-06 | 2022-07-28 | 2022-08-24 | 55
0 | EDCDIN1310 | SPECIFICATION FOR PRESSURE RELIEF VALVES - IFC | 20 | 2022-05-09 | 2022-06-06 | 2022-11-02 | 2022-11-29 | 124
0 | EDCDIN1250 | SPECIFICATION FOR WET GAS FLOW METER (WGFM) I.E, MULTI-PHASE FLOW METER (MPFM) - IFC | 20 | 2022-05-09 | 2022-06-06 | 2022-08-11 | 2022-09-07 | 65
0 | EDCDIN1295 | SPECIFICATION FOR MOTOR OPERATED VALVE (MOV)- IFC | 20 | 2022-05-09 | 2022-06-06 | 2022-08-11 | 2022-09-07 | 65
0 | EDCDIN1265 | SPECIFICATION FOR ACTUATED ON-OFF VALVES - IFC | 20 | 2022-05-09 | 2022-06-06 | 2022-08-11 | 2022-09-07 | 65
0 | EDCDIN1340 | SPECIFICATION FOR FIRE & GAS DETECTORS/DEVICES - IFC | 20 | 2022-05-17 | 2022-06-14 | 2022-11-10 | 2022-12-09 | 124
0 | EDCDIN1325 | SPECIFICATION FOR FIELD INSTRUMENTS - IFC | 20 | 2022-05-17 | 2022-06-14 | 2022-08-31 | 2022-09-27 | 73
0 | EDCDIN1355 | SPECIFICATION FOR INSTRUMENT & CONTROL CABLE - IFC | 15 | 2022-05-31 | 2022-06-21 | 2022-10-07 | 2022-10-27 | 90
0 | EDCDIN1385 | SPECIFICATION FOR INSTRUMENT INSTALLATION - IFC | 20 | 2022-05-31 | 2022-06-28 | 2022-12-14 | 2023-01-10 | 136
0 | EDCDIN1370 | SPECIFICATION FOR INSTRUMENT BULK MATERIAL - IFC | 20 | 2022-05-31 | 2022-06-28 | 2022-11-22 | 2022-12-21 | 122
DRAWINGS |  |  | 144 | 2022-05-19 | 2022-12-14 | 2022-08-15 | 2023-04-04 | 80
0 | EDCGIN1000 | CONTROL SYSTEM BLOCK DIAGRAM / CONTROL SYSTEM ARCHITECTURE DRAWINGS - ICR | 10 | 2022-05-19 | 2022-06-02 | 2022-08-15 | 2022-08-26 | 59
0 | EDCGIN1005 | CONTROL SYSTEM BLOCK DIAGRAM / CONTROL SYSTEM ARCHITECTURE DRAWINGS - IFA | 15 | 2022-06-16 | 2022-07-07 | 2022-12-07 | 2022-12-27 | 119
0 | EDCGIN1010 | CONTROL SYSTEM BLOCK DIAGRAM / CONTROL SYSTEM ARCHITECTURE DRAWINGS - IFC | 30 | 2022-07-26 | 2022-09-06 | 2023-01-11 | 2023-02-21 | 119
0 | EDCGIN1015 | TYPICAL INSTRUMENT INSTALLATION DRAWINGS / TYPICAL DETAILED INSTALLATION DRAWINGS - ICR | 15 | 2022-08-22 | 2022-09-12 | 2022-12-14 | 2023-01-03 | 80
0 | EDCGIN1035 | TYPICAL INSTRUMENT GROUNDING STANDARD DRAWINGS - ICR | 15 | 2022-08-29 | 2022-09-19 | 2022-12-28 | 2023-01-17 | 85
0 | EDCGIN1020 | TYPICAL INSTRUMENT INSTALLATION DRAWINGS / TYPICAL DETAILED INSTALLATION DRAWINGS - IFA | 15 | 2022-09-26 | 2022-10-17 | 2023-01-18 | 2023-02-07 | 80
0 | EDCGIN1040 | TYPICAL INSTRUMENT GROUNDING STANDARD DRAWINGS - IFA | 15 | 2022-10-03 | 2022-10-24 | 2023-02-01 | 2023-02-21 | 85
0 | EDCGIN1045 | TYPICAL INSTRUMENT GROUNDING STANDARD DRAWINGS - IFC | 20 | 2022-11-07 | 2022-12-07 | 2023-03-08 | 2023-04-04 | 85
0 | EDCGIN1025 | TYPICAL INSTRUMENT INSTALLATION DRAWINGS / TYPICAL DETAILED INSTALLATION DRAWINGS - IFC | 30 | 2022-10-31 | 2022-12-14 | 2023-02-22 | 2023-04-04 | 80
REQUISITIONS & TBE |  |  | 146 | 2022-03-16 | 2022-10-14 | 2022-05-27 | 2023-03-17 | 109
IRCD SKID |  |  | 78 | 2022-04-08 | 2022-08-04 | 2022-06-14 | 2022-11-09 | 70
REQUISITION |  |  | 56 | 2022-04-08 | 2022-06-30 | 2022-06-14 | 2022-09-07 | 47
0 | EDCMIN1015 | IRCD SKID - ISSUE MR - ICR | 5 | 2022-04-08 | 2022-04-15 | 2022-06-14 | 2022-06-20 | 44
0 | EDCMIN1020 | IRCD SKID - ISSUE MR - IFA | 10 | 2022-05-12 | 2022-05-26 | 2022-07-26 | 2022-08-08 | 50
0 | EDCMIN1025 | IRCD SKID - ISSUE MR - IFC | 10 | 2022-06-16 | 2022-06-30 | 2022-08-25 | 2022-09-07 | 47
TBE |  |  | 56 | 2022-05-13 | 2022-08-04 | 2022-07-19 | 2022-11-09 | 70
0 | EDCMIN2000 | COMPLETE EVALUATION AND SUBMIT TBE - IRCD SKID - ICR | 15 | 2022-05-13 | 2022-06-03 | 2022-07-19 | 2022-08-08 | 44
0 | EDCMIN2005 | RECEIVE COMMENTS & ISSUE TBE- IRCD SKID - IFA | 10 | 2022-06-17 | 2022-07-01 | 2022-08-25 | 2022-09-07 | 46
0 | EDCMIN2010 | ISSUE TBE- IRCD SKID - IFC | 11 | 2022-07-20 | 2022-08-04 | 2022-10-26 | 2022-11-09 | 70
INTEGRATED CONTROL AND SAFETY SYSTEM (ICSS) |  |  | 41 | 2022-04-06 | 2022-06-07 | 2022-06-14 | 2022-12-28 | 142
REQUISITION |  |  | 34 | 2022-04-06 | 2022-05-27 | 2022-06-14 | 2022-12-28 | 149
0 | EDCMIN1330 | ICSS - ISSUE MR - ICR | 2 | 2022-04-06 | 2022-04-08 | 2022-06-14 | 2022-06-15 | 46
0 | EDCMIN1335 | ICSS - ISSUE MR - IFA | 5 | 2022-04-22 | 2022-04-29 | 2022-07-21 | 2022-07-27 | 58
0 | EDCMIN1340 | ICSS - ISSUE MR - IFC | 7 | 2022-05-18 | 2022-05-27 | 2022-12-20 | 2022-12-28 | 149
TBE |  |  | 37 | 2022-04-12 | 2022-06-07 | 2022-06-20 | 2022-11-28 | 122
0 | EDCMIN2015 | COMPLETE EVALUATION AND SUBMIT TBE - ICSS - ICR | 3 | 2022-04-12 | 2022-04-15 | 2022-06-20 | 2022-06-22 | 46
0 | EDCMIN2020 | RECEIVE COMMENTS & ISSUE TBE - ICSS - IFA | 3 | 2022-05-05 | 2022-05-10 | 2022-07-25 | 2022-07-27 | 54
0 | EDCMIN2025 | ISSUE TBE - ICSS - IFC | 10 | 2022-05-24 | 2022-06-07 | 2022-11-15 | 2022-11-28 | 122
HIPPS |  |  | 81 | 2022-03-18 | 2022-07-19 | 2022-05-27 | 2022-10-07 | 59
REQUISITION |  |  | 45 | 2022-03-18 | 2022-05-25 | 2022-05-27 | 2022-08-26 | 65
0 | EDCMIN1350 | HIPPS - ISSUE MR - ICR | 5 | 2022-03-18 | 2022-03-25 | 2022-05-27 | 2022-06-02 | 47
0 | EDCMIN1355 | HIPPS - ISSUE MR - IFA | 10 | 2022-04-08 | 2022-04-22 | 2022-07-14 | 2022-07-27 | 63
0 | EDCMIN1360 | HIPPS - ISSUE MR - IFC | 10 | 2022-05-11 | 2022-05-25 | 2022-08-15 | 2022-08-26 | 65
TBE |  |  | 58 | 2022-04-20 | 2022-07-19 | 2022-06-29 | 2022-10-07 | 59
0 | EDCMIN2030 | COMPLETE EVALUATION AND SUBMIT TBE - HIPPS - ICR | 18 | 2022-04-20 | 2022-05-19 | 2022-06-29 | 2022-07-27 | 47
0 | EDCMIN2035 | RECEIVE COMMENTS & ISSUE TBE - HIPPS - IFA | 10 | 2022-06-02 | 2022-06-16 | 2022-08-15 | 2022-08-26 | 49
0 | EDCMIN2040 | ISSUE TBE - HIPPS - IFC | 10 | 2022-06-30 | 2022-07-19 | 2022-09-26 | 2022-10-07 | 59
WELLHEAD CONTROL PANELS |  |  | 84 | 2022-03-16 | 2022-07-20 | 2022-06-03 | 2022-10-18 | 65
REQUISITION |  |  | 47 | 2022-03-16 | 2022-05-25 | 2022-06-03 | 2022-09-06 | 72
0 | EDCMIN1365 | WELLHEAD CONTROL PANELS - ISSUE MR - ICR | 5 | 2022-03-16 | 2022-03-23 | 2022-06-03 | 2022-06-09 | 54
0 | EDCMIN1370 | WELLHEAD CONTROL PANELS - ISSUE MR - IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-07-25 | 2022-08-05 | 72
0 | EDCMIN1375 | WELLHEAD CONTROL PANELS - ISSUE MR - IFC | 10 | 2022-05-11 | 2022-05-25 | 2022-08-24 | 2022-09-06 | 72
TBE |  |  | 61 | 2022-04-18 | 2022-07-20 | 2022-07-06 | 2022-10-18 | 65
0 | EDCMIN2045 | COMPLETE EVALUATION AND SUBMIT TBE - WELLHEAD CONTROL PANEL - ICR | 20 | 2022-04-18 | 2022-05-19 | 2022-07-06 | 2022-08-05 | 54
0 | EDCMIN2050 | RECEIVE COMMENTS & ISSUE TBE - WELLHEAD CONTROL PANEL - IFA | 10 | 2022-06-02 | 2022-06-16 | 2022-08-24 | 2022-09-06 | 56
0 | EDCMIN2055 | ISSUE TBE - WELLHEAD CONTROL PANEL - IFC | 11 | 2022-06-30 | 2022-07-20 | 2022-10-04 | 2022-10-18 | 65
ACTUATED ON/OFF VALVES |  |  | 80 | 2022-04-06 | 2022-08-04 | 2022-06-09 | 2022-10-26 | 60
REQUISITION |  |  | 46 | 2022-04-06 | 2022-06-14 | 2022-06-09 | 2022-09-07 | 59
0 | EDCMIN1380 | ACTUATED ON/OFF VALVES - ISSUE MR - ICR | 5 | 2022-04-06 | 2022-04-13 | 2022-06-09 | 2022-06-15 | 43
0 | EDCMIN1385 | ACTUATED ON/OFF VALVES - ISSUE MR - IFA | 10 | 2022-04-27 | 2022-05-16 | 2022-07-26 | 2022-08-08 | 58
0 | EDCMIN1390 | ACTUATED ON/OFF VALVES - ISSUE MR - IFC | 10 | 2022-05-31 | 2022-06-14 | 2022-08-25 | 2022-09-07 | 59
TBE |  |  | 55 | 2022-05-16 | 2022-08-04 | 2022-07-19 | 2022-10-26 | 60
0 | EDCMIN2060 | COMPLETE EVALUATION AND SUBMIT TBE - ACTUATED ON/OFF VALVES - ICR | 15 | 2022-05-16 | 2022-06-06 | 2022-07-19 | 2022-08-08 | 43
0 | EDCMIN2065 | RECEIVE COMMENTS & ISSUE TBE - ACTUATED ON/OFF VALVES - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-08-25 | 2022-09-07 | 45
0 | EDCMIN2070 | ISSUE TBE - ACTUATED ON/OFF VALVES - IFC | 10 | 2022-07-21 | 2022-08-04 | 2022-10-13 | 2022-10-26 | 60
MOTORISED CHOKE VALVES |  |  | 77 | 2022-04-11 | 2022-08-04 | 2022-06-14 | 2022-10-12 | 50
REQUISITION |  |  | 56 | 2022-04-11 | 2022-07-01 | 2022-06-14 | 2022-09-07 | 46
0 | EDCMIN1395 | MOTORISED CHOKE VALVES - ISSUE MR - ICR | 5 | 2022-04-11 | 2022-04-18 | 2022-06-14 | 2022-06-20 | 43
0 | EDCMIN1400 | MOTORISED CHOKE VALVES - ISSUE MR - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-07-26 | 2022-08-08 | 55
0 | EDCMIN1405 | MOTORISED CHOKE VALVES - ISSUE MR - IFC | 10 | 2022-06-17 | 2022-07-01 | 2022-08-25 | 2022-09-07 | 46
TBE |  |  | 53 | 2022-05-18 | 2022-08-04 | 2022-07-21 | 2022-10-12 | 50
0 | EDCMIN2075 | COMPLETE EVALUATION AND SUBMIT TBE - MOTORISED CHOKE VALVES - ICR | 13 | 2022-05-18 | 2022-06-06 | 2022-07-21 | 2022-08-08 | 43
0 | EDCMIN2080 | RECEIVE COMMENTS & ISSUE TBE - MOTORISED CHOKE VALVES - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-08-25 | 2022-09-07 | 45
0 | EDCMIN2085 | ISSUE TBE - MOTORISED CHOKE VALVES - IFC | 10 | 2022-07-21 | 2022-08-04 | 2022-09-29 | 2022-10-12 | 50
ULTRASONIC FLOW METER |  |  | 68 | 2022-04-07 | 2022-07-20 | 2022-06-27 | 2022-11-09 | 81
REQUISITION |  |  | 45 | 2022-04-07 | 2022-06-14 | 2022-06-27 | 2022-09-06 | 58
0 | EDCMIN1315 | ULTRASONIC FLOW METER - ISSUE MR - ICR | 5 | 2022-04-07 | 2022-04-14 | 2022-06-27 | 2022-07-01 | 54
0 | EDCMIN1320 | ULTRASONIC FLOW METER - ISSUE MR - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-07-25 | 2022-08-05 | 56
0 | EDCMIN1325 | ULTRASONIC FLOW METER - ISSUE MR - IFC | 10 | 2022-05-31 | 2022-06-14 | 2022-08-24 | 2022-09-06 | 58
TBE |  |  | 51 | 2022-05-05 | 2022-07-20 | 2022-07-25 | 2022-11-09 | 81
0 | EDCMIN2090 | COMPLETE EVALUATION AND SUBMIT TBE - ULTRASONIC FLOW METER - ICR | 10 | 2022-05-05 | 2022-05-19 | 2022-07-25 | 2022-08-05 | 54
0 | EDCMIN2095 | RECEIVE COMMENTS & ISSUE TBE - ULTRASONIC FLOW METER - IFA | 10 | 2022-06-02 | 2022-06-16 | 2022-08-24 | 2022-09-06 | 56
0 | EDCMIN2100 | ISSUE TBE - ULTRASONIC FLOW METER - IFC | 11 | 2022-06-30 | 2022-07-20 | 2022-10-26 | 2022-11-09 | 81
MOTOR OPERATED VALVES (BALL TYPE) |  |  | 81 | 2022-04-06 | 2022-08-05 | 2022-06-09 | 2022-10-13 | 50
REQUISITION |  |  | 45 | 2022-04-06 | 2022-06-13 | 2022-06-09 | 2022-09-07 | 60
0 | EDCMIN1180 | MOTOR OPERATED VALVES (BALL TYPE) - ISSUE MR - ICR | 5 | 2022-04-06 | 2022-04-13 | 2022-06-09 | 2022-06-15 | 43
0 | EDCMIN1185 | MOTOR OPERATED VALVES (BALL TYPE) - ISSUE MR - IFA | 10 | 2022-04-27 | 2022-05-16 | 2022-07-26 | 2022-08-08 | 58
0 | EDCMIN1190 | MOTOR OPERATED VALVES (BALL TYPE) - ISSUE MR - IFC | 10 | 2022-05-30 | 2022-06-13 | 2022-08-25 | 2022-09-07 | 60
TBE |  |  | 56 | 2022-05-16 | 2022-08-05 | 2022-07-19 | 2022-10-13 | 50
0 | EDCMIN2105 | COMPLETE EVALUATION AND SUBMIT TBE - MOTOR OPERATED VALVES (BALL TYPE) - ICR | 15 | 2022-05-16 | 2022-06-06 | 2022-07-19 | 2022-08-08 | 43
0 | EDCMIN2110 | RECEIVE COMMENTS & ISSUE TBE - MOTOR OPERATED VALVES (BALL TYPE) - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-08-25 | 2022-09-07 | 45
0 | EDCMIN2115 | ISSUE TBE - MOTOR OPERATED VALVES (BALL TYPE) - IFC | 11 | 2022-07-21 | 2022-08-05 | 2022-09-29 | 2022-10-13 | 50
MOTOR OPERATED VALVES (IDBB TYPE) |  |  | 81 | 2022-04-06 | 2022-08-05 | 2022-06-09 | 2022-10-19 | 54
REQUISITION |  |  | 45 | 2022-04-06 | 2022-06-13 | 2022-06-09 | 2022-09-07 | 60
0 | EDCMIN1195 | MOTOR OPERATED VALVES (IDBB TYPE) - ISSUE MR - ICR | 5 | 2022-04-06 | 2022-04-13 | 2022-06-09 | 2022-06-15 | 43
0 | EDCMIN1200 | MOTOR OPERATED VALVES (IDBB TYPE) - ISSUE MR - IFA | 10 | 2022-04-27 | 2022-05-16 | 2022-07-26 | 2022-08-08 | 58
0 | EDCMIN1205 | MOTOR OPERATED VALVES (IDBB TYPE) - ISSUE MR - IFC | 10 | 2022-05-30 | 2022-06-13 | 2022-08-25 | 2022-09-07 | 60
TBE |  |  | 56 | 2022-05-16 | 2022-08-05 | 2022-07-19 | 2022-10-19 | 54
0 | EDCMIN2120 | COMPLETE EVALUATION AND SUBMIT TBE - MOTOR OPERATED VALVES (IDBB TYPE) - ICR | 15 | 2022-05-16 | 2022-06-06 | 2022-07-19 | 2022-08-08 | 43
0 | EDCMIN2125 | RECEIVE COMMENTS & ISSUE TBE - MOTOR OPERATED VALVES (IDBB TYPE) - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-08-25 | 2022-09-07 | 45
0 | EDCMIN2130 | ISSUE TBE - MOTOR OPERATED VALVES (IDBB TYPE) - IFC | 11 | 2022-07-21 | 2022-08-05 | 2022-10-05 | 2022-10-19 | 54
CORROSION MONITORING DEVICES |  |  | 74 | 2022-05-17 | 2022-09-01 | 2022-10-12 | 2023-02-03 | 110
REQUISITION |  |  | 49 | 2022-05-17 | 2022-07-28 | 2022-10-12 | 2022-12-29 | 109
0 | EDCMIN1030 | CORROSION MONITORING DEVICES - ISSUE MR - ICR | 5 | 2022-05-17 | 2022-05-24 | 2022-10-12 | 2022-10-18 | 103
0 | EDCMIN1035 | CORROSION MONITORING DEVICES - ISSUE MR - IFA | 10 | 2022-06-07 | 2022-06-21 | 2022-11-14 | 2022-11-25 | 111
0 | EDCMIN1040 | CORROSION MONITORING DEVICES - ISSUE MR - IFC | 10 | 2022-07-14 | 2022-07-28 | 2022-12-16 | 2022-12-29 | 109
TBE |  |  | 51 | 2022-06-17 | 2022-09-01 | 2022-11-14 | 2023-02-03 | 110
0 | EDCMIN2135 | COMPLETE EVALUATION AND SUBMIT TBE - CORROSION MONITORING DEVICES - ICR | 10 | 2022-06-17 | 2022-07-01 | 2022-11-14 | 2022-11-25 | 103
0 | EDCMIN2140 | RECEIVE COMMENTS & ISSUE TBE - CORROSION MONITORING DEVICES - IFA | 10 | 2022-07-20 | 2022-08-03 | 2022-12-16 | 2022-12-29 | 105
0 | EDCMIN2145 | ISSUE TBE - CORROSION MONITORING DEVICES - IFC | 11 | 2022-08-17 | 2022-09-01 | 2023-01-20 | 2023-02-03 | 110
FIRE & GAS DETECTORS / DEVICES |  |  | 81 | 2022-05-13 | 2022-09-08 | 2022-11-07 | 2023-03-07 | 127
REQUISITION |  |  | 45 | 2022-05-13 | 2022-07-20 | 2022-11-07 | 2023-01-17 | 128
0 | EDCMIN1045 | FIRE & GAS DETECTORS / DEVICES - ISSUE MR - ICR | 5 | 2022-05-13 | 2022-05-20 | 2022-11-07 | 2022-11-11 | 123
0 | EDCMIN1050 | FIRE & GAS DETECTORS / DEVICES - ISSUE MR - IFA | 10 | 2022-06-03 | 2022-06-17 | 2022-12-05 | 2022-12-16 | 126
0 | EDCMIN1055 | FIRE & GAS DETECTORS / DEVICES - ISSUE MR - IFC | 5 | 2022-07-13 | 2022-07-20 | 2023-01-11 | 2023-01-17 | 128
TBE |  |  | 51 | 2022-06-24 | 2022-09-08 | 2022-12-05 | 2023-03-07 | 127
0 | EDCMIN2150 | COMPLETE EVALUATION AND SUBMIT TBE - FIRE & GAS DETECTORS/ DEVICES - ICR | 10 | 2022-06-24 | 2022-07-13 | 2022-12-05 | 2022-12-16 | 111
0 | EDCMIN2155 | RECEIVE COMMENTS & ISSUE TBE - FIRE & GAS DETECTORS/ DEVICES - IFA | 10 | 2022-07-27 | 2022-08-10 | 2023-01-04 | 2023-01-17 | 113
0 | EDCMIN2160 | ISSUE TBE - FIRE & GAS DETECTORS/ DEVICES - IFC | 11 | 2022-08-24 | 2022-09-08 | 2023-02-21 | 2023-03-07 | 127
FLOW RESTRICTION ORIFICE |  |  | 75 | 2022-04-22 | 2022-08-15 | 2022-09-13 | 2022-12-28 | 96
REQUISITION |  |  | 55 | 2022-04-22 | 2022-07-18 | 2022-09-13 | 2022-11-23 | 93
0 | EDCMIN1075 | FLOW RESTRICTION ORIFICE - ISSUE MR - ICR | 5 | 2022-04-22 | 2022-04-29 | 2022-09-13 | 2022-09-19 | 96
0 | EDCMIN1080 | FLOW RESTRICTION ORIFICE - ISSUE MR - IFA | 10 | 2022-05-24 | 2022-06-07 | 2022-10-11 | 2022-10-24 | 97
0 | EDCMIN1085 | FLOW RESTRICTION ORIFICE - ISSUE MR - IFC | 10 | 2022-06-29 | 2022-07-18 | 2022-11-10 | 2022-11-23 | 93
TBE |  |  | 50 | 2022-06-01 | 2022-08-15 | 2022-10-11 | 2022-12-28 | 96
0 | EDCMIN2165 | COMPLETE EVALUATION AND SUBMIT TBE - FLOW RESTRICTION ORIFICE - ICR | 10 | 2022-06-01 | 2022-06-15 | 2022-10-11 | 2022-10-24 | 91
0 | EDCMIN2170 | RECEIVE COMMENTS & ISSUE TBE - FLOW RESTRICTION ORIFICE - IFA | 10 | 2022-06-29 | 2022-07-18 | 2022-11-10 | 2022-11-23 | 93
0 | EDCMIN2175 | ISSUE TBE - FLOW RESTRICTION ORIFICE - IFC | 10 | 2022-08-01 | 2022-08-15 | 2022-12-15 | 2022-12-28 | 96
GWR & RADAR TYPE LEVEL TRANSMITTER |  |  | 70 | 2022-04-27 | 2022-08-11 | 2022-09-19 | 2023-01-25 | 118
REQUISITION |  |  | 45 | 2022-04-27 | 2022-07-04 | 2022-09-19 | 2022-11-29 | 104
0 | EDCMIN1090 | GWR & RADAR TYPE LEVEL TRANSMITTER - ISSUE MR - ICR | 5 | 2022-04-27 | 2022-05-09 | 2022-09-19 | 2022-09-23 | 97
0 | EDCMIN1095 | GWR & RADAR TYPE LEVEL TRANSMITTER - ISSUE MR - IFA | 5 | 2022-05-23 | 2022-05-30 | 2022-10-24 | 2022-10-28 | 107
0 | EDCMIN1100 | GWR & RADAR TYPE LEVEL TRANSMITTER - ISSUE MR - IFC | 5 | 2022-06-27 | 2022-07-04 | 2022-11-23 | 2022-11-29 | 104
TBE |  |  | 50 | 2022-05-30 | 2022-08-11 | 2022-10-17 | 2023-01-25 | 118
0 | EDCMIN2180 | COMPLETE EVALUATION AND SUBMIT TBE - GWR & RADAR TYPE LEVEL TRANSMITTER - ICR | 10 | 2022-05-30 | 2022-06-13 | 2022-10-17 | 2022-10-28 | 97
0 | EDCMIN2185 | RECEIVE COMMENTS & ISSUE TBE - GWR & RADAR TYPE LEVEL TRANSMITTER - IFA | 10 | 2022-06-27 | 2022-07-14 | 2022-11-16 | 2022-11-29 | 99
0 | EDCMIN2190 | ISSUE TBE - GWR & RADAR TYPE LEVEL TRANSMITTER - IFC | 10 | 2022-07-28 | 2022-08-11 | 2023-01-12 | 2023-01-25 | 118
INSTRUMENT & CONTROL AND TELECOMMUNICATION CABLES |  |  | 68 | 2022-07-04 | 2022-10-11 | 2022-10-25 | 2023-02-15 | 90
REQUISITION |  |  | 39 | 2022-07-04 | 2022-08-31 | 2022-10-25 | 2023-01-04 | 89
0 | EDCMIN1105 | INSTRUMENT & CONTROL & TELECOMMUNICATION CABLES - ISSUE MR - ICR | 5 | 2022-07-04 | 2022-07-14 | 2022-10-25 | 2022-10-31 | 78
0 | EDCMIN1110 | INSTRUMENT & CONTROL & TELECOMMUNICATION CABLES - ISSUE MR - IFA | 10 | 2022-07-28 | 2022-08-11 | 2022-11-18 | 2022-12-05 | 81
0 | EDCMIN1115 | INSTRUMENT & CONTROL & TELECOMMUNICATION CABLES - ISSUE MR - IFC | 4 | 2022-08-25 | 2022-08-31 | 2022-12-30 | 2023-01-04 | 89
TBE |  |  | 50 | 2022-08-02 | 2022-10-11 | 2022-11-18 | 2023-02-15 | 90
0 | EDCMIN2195 | COMPLETE EVALUATION AND SUBMIT TBE - INST'NT/ CONTROL & FO AN COMMUNICATION CABLES - ICR | 10 | 2022-08-02 | 2022-08-16 | 2022-11-18 | 2022-12-05 | 78
0 | EDCMIN2200 | RECEIVE COMMENTS & ISSUE TBE - INST'NT/ CONTROL& FO ANDCOMMUNICATION CABLES - IFA | 10 | 2022-08-30 | 2022-09-13 | 2022-12-22 | 2023-01-04 | 80
0 | EDCMIN2205 | ISSUE TBE - INST'NT/ CONTROL & COMMUNICATION CABLES - IFC | 10 | 2022-09-27 | 2022-10-11 | 2023-02-02 | 2023-02-15 | 90
INSTRUMENT CABLE GLANDS |  |  | 68 | 2022-07-07 | 2022-10-14 | 2022-11-16 | 2023-03-17 | 109
REQUISITION |  |  | 33 | 2022-07-07 | 2022-08-26 | 2022-11-16 | 2023-01-25 | 107
0 | EDCMIN1000 | INSTRUMENT CABLE GLANDS - ISSUE MR - ICR | 5 | 2022-07-07 | 2022-07-19 | 2022-11-16 | 2022-11-22 | 91
0 | EDCMIN1005 | INSTRUMENT CABLE GLANDS - ISSUE MR - IFA | 5 | 2022-08-02 | 2022-08-09 | 2022-12-20 | 2022-12-26 | 98
0 | EDCMIN1010 | INSTRUMENT CABLE GLANDS - ISSUE MR - IFC | 3 | 2022-08-23 | 2022-08-26 | 2023-01-23 | 2023-01-25 | 107
TBE |  |  | 51 | 2022-08-04 | 2022-10-14 | 2022-12-13 | 2023-03-17 | 109
0 | EDCMIN2210 | COMPLETE EVALUATION AND SUBMIT TBE - INSTRUMENT CABLE GLANDS - ICR | 10 | 2022-08-04 | 2022-08-18 | 2022-12-13 | 2022-12-26 | 91
0 | EDCMIN2215 | RECEIVE COMMENTS & ISSUE TBE - INSTRUMENT CABLE GLANDS - IFA | 10 | 2022-09-01 | 2022-09-15 | 2023-01-12 | 2023-01-25 | 93
0 | EDCMIN2220 | ISSUE TBE - INSTRUMENT CABLE GLANDS - IFC | 11 | 2022-09-29 | 2022-10-14 | 2023-03-03 | 2023-03-17 | 109
INSTRUMENT BULK MATERIAL |  |  | 68 | 2022-06-08 | 2022-09-15 | 2022-10-12 | 2023-01-25 | 93
REQUISITION |  |  | 45 | 2022-06-08 | 2022-08-15 | 2022-10-12 | 2023-01-04 | 101
0 | EDCMIN1120 | INSTRUMENT BULK MATERIAL - MR - ICR | 5 | 2022-06-08 | 2022-06-15 | 2022-10-12 | 2022-10-18 | 87
0 | EDCMIN1125 | INSTRUMENT BULK MATERIAL - MR - IFA | 10 | 2022-06-29 | 2022-07-18 | 2022-11-18 | 2022-12-05 | 99
0 | EDCMIN1130 | INSTRUMENT BULK MATERIAL - MR - IFC | 10 | 2022-08-01 | 2022-08-15 | 2022-12-22 | 2023-01-04 | 101
TBE |  |  | 50 | 2022-07-04 | 2022-09-15 | 2022-11-11 | 2023-01-25 | 93
0 | EDCMIN2225 | COMPLETE EVALUATION AND SUBMIT TBE - INSTRUMENT BULK MATERIALS - ICR | 15 | 2022-07-04 | 2022-07-28 | 2022-11-11 | 2022-12-05 | 91
0 | EDCMIN2230 | RECEIVE COMMENTS & ISSUE TBE - INSTRUMENT BULK MATERIALS - IFA | 10 | 2022-08-11 | 2022-08-25 | 2022-12-22 | 2023-01-04 | 93
0 | EDCMIN2235 | ISSUE TBE - INSTRUMENT BULK MATERIALS - IFC | 5 | 2022-09-08 | 2022-09-15 | 2023-01-19 | 2023-01-25 | 93
INSTRUMENT SUN SHADES |  |  | 65 | 2022-06-13 | 2022-09-15 | 2022-10-17 | 2023-01-25 | 93
REQUISITION |  |  | 45 | 2022-06-13 | 2022-08-18 | 2022-10-17 | 2023-01-05 | 99
0 | EDCMIN1135 | INSTRUMENT SUN SHADES - ISSUE MR - ICR | 5 | 2022-06-13 | 2022-06-20 | 2022-10-17 | 2022-10-21 | 87
0 | EDCMIN1140 | INSTRUMENT SUN SHADES - ISSUE MR - IFA | 10 | 2022-07-04 | 2022-07-21 | 2022-11-21 | 2022-12-06 | 97
0 | EDCMIN1145 | INSTRUMENT SUN SHADES - ISSUE MR - IFC | 10 | 2022-08-04 | 2022-08-18 | 2022-12-23 | 2023-01-05 | 99
TBE |  |  | 40 | 2022-07-21 | 2022-09-15 | 2022-11-21 | 2023-01-25 | 93
0 | EDCMIN2240 | COMPLETE EVALUATION AND SUBMIT TBE - INSTRUMENT SUN SHADES - ICR | 10 | 2022-07-21 | 2022-08-04 | 2022-11-21 | 2022-12-06 | 87
0 | EDCMIN2245 | RECEIVE COMMENTS & ISSUE TBE - INSTRUMENT SUN SHADES - IFA | 5 | 2022-08-18 | 2022-08-25 | 2022-12-29 | 2023-01-04 | 93
0 | EDCMIN2250 | ISSUE TBE - INSTRUMENT SUN SHADES - IFC | 5 | 2022-09-08 | 2022-09-15 | 2023-01-19 | 2023-01-25 | 93
JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM |  |  | 81 | 2022-05-11 | 2022-09-06 | 2022-08-30 | 2022-12-22 | 76
REQUISITION |  |  | 45 | 2022-05-11 | 2022-07-18 | 2022-08-30 | 2022-12-22 | 112
0 | EDCMIN1150 | JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM - ISSUE MR - ICR | 5 | 2022-05-11 | 2022-05-18 | 2022-08-30 | 2022-09-05 | 76
0 | EDCMIN1155 | JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM - ISSUE MR - IFA | 10 | 2022-06-01 | 2022-06-15 | 2022-10-11 | 2022-10-24 | 91
0 | EDCMIN1160 | JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM - ISSUE MR - IFC | 10 | 2022-06-29 | 2022-07-18 | 2022-12-09 | 2022-12-22 | 112
TBE |  |  | 56 | 2022-06-15 | 2022-09-06 | 2022-10-04 | 2022-12-22 | 76
0 | EDCMIN2255 | COMPLETE EVALUATION AND SUBMIT TBE - JUNCTION /MARSHAKKING BOXES INSTRUMENT & TELECOM - ICR | 15 | 2022-06-15 | 2022-07-06 | 2022-10-04 | 2022-10-24 | 76
0 | EDCMIN2260 | RECEIVE COMMENTS & ISSUE TBE - JUNCTION /MARSHAKKING BOXES INSTRUMENT & TELECOM - IFA | 10 | 2022-07-25 | 2022-08-08 | 2022-11-08 | 2022-11-21 | 76
0 | EDCMIN2265 | ISSUE TBE - JUNCTION /MARSHAKKING BOXES INSTRUMENT & TELECOM - IFC | 11 | 2022-08-22 | 2022-09-06 | 2022-12-08 | 2022-12-22 | 76
MAGNETIC LEVEL GAUGES |  |  | 65 | 2022-04-26 | 2022-08-03 | 2022-09-19 | 2023-02-08 | 134
REQUISITION |  |  | 51 | 2022-04-26 | 2022-07-14 | 2022-09-19 | 2022-11-29 | 99
0 | EDCMIN1165 | MAGNETIC LEVEL GAUGES- ISSUE MR - ICR | 5 | 2022-04-26 | 2022-05-06 | 2022-09-19 | 2022-09-23 | 98
0 | EDCMIN1170 | MAGNETIC LEVEL GAUGES- ISSUE MR - IFA | 10 | 2022-05-20 | 2022-06-03 | 2022-10-17 | 2022-10-28 | 103
0 | EDCMIN1175 | MAGNETIC LEVEL GAUGES- ISSUE MR - IFC | 10 | 2022-06-27 | 2022-07-14 | 2022-11-16 | 2022-11-29 | 99
TBE |  |  | 45 | 2022-05-27 | 2022-08-03 | 2022-10-17 | 2023-02-08 | 134
0 | EDCMIN2270 | COMPLETE EVALUATION AND SUBMIT TBE - MAGNETIC LEVEL GAUGE - ICR | 10 | 2022-05-27 | 2022-06-10 | 2022-10-17 | 2022-10-28 | 98
0 | EDCMIN2275 | RECEIVE COMMENTS & ISSUE TBE - MAGNETIC LEVEL GAUGE - IFA | 10 | 2022-06-24 | 2022-07-13 | 2022-11-16 | 2022-11-29 | 100
0 | EDCMIN2280 | ISSUE TBE - MAGNETIC LEVEL GAUGE - IFC | 5 | 2022-07-27 | 2022-08-03 | 2023-02-02 | 2023-02-08 | 134
PIG SIGNALLER |  |  | 80 | 2022-06-07 | 2022-09-30 | 2022-10-17 | 2023-03-16 | 118
REQUISITION |  |  | 45 | 2022-06-07 | 2022-08-12 | 2022-10-17 | 2023-01-12 | 108
0 | EDCMIN1210 | PIG SIGNALLER - ISSUE MR - ICR | 5 | 2022-06-07 | 2022-06-14 | 2022-10-17 | 2022-10-21 | 91
0 | EDCMIN1215 | PIG SIGNALLER - ISSUE MR - IFA | 10 | 2022-06-28 | 2022-07-15 | 2022-11-28 | 2022-12-13 | 106
0 | EDCMIN1220 | PIG SIGNALLER - ISSUE MR - IFC | 10 | 2022-07-29 | 2022-08-12 | 2022-12-30 | 2023-01-12 | 108
TBE |  |  | 55 | 2022-07-15 | 2022-09-30 | 2022-11-21 | 2023-03-16 | 118
0 | EDCMIN2285 | COMPLETE EVALUATION AND SUBMIT TBE - PIG SIGNALLER - ICR | 15 | 2022-07-15 | 2022-08-05 | 2022-11-21 | 2022-12-13 | 91
0 | EDCMIN2290 | RECEIVE COMMENTS & ISSUE TBE - PIG SIGNALLER - IFA | 10 | 2022-08-19 | 2022-09-02 | 2022-12-30 | 2023-01-12 | 93
0 | EDCMIN2295 | ISSUE TBE - PIG SIGNALLER - IFC | 10 | 2022-09-16 | 2022-09-30 | 2023-03-03 | 2023-03-16 | 118
PRESSURE GAUGES |  |  | 80 | 2022-04-20 | 2022-08-18 | 2022-09-09 | 2023-01-30 | 116
REQUISITION |  |  | 47 | 2022-04-20 | 2022-06-29 | 2022-09-09 | 2022-12-07 | 111
0 | EDCMIN1225 | PRESSURE GAUGES - ISSUE MR - ICR | 5 | 2022-04-20 | 2022-04-27 | 2022-09-09 | 2022-09-15 | 96
0 | EDCMIN1230 | PRESSURE GAUGES - ISSUE MR - IFA | 10 | 2022-05-16 | 2022-05-30 | 2022-10-21 | 2022-11-03 | 111
0 | EDCMIN1235 | PRESSURE GAUGES - ISSUE MR - IFC | 10 | 2022-06-15 | 2022-06-29 | 2022-11-22 | 2022-12-07 | 111
TBE |  |  | 55 | 2022-05-30 | 2022-08-18 | 2022-10-14 | 2023-01-30 | 116
0 | EDCMIN2300 | COMPLETE EVALUATION AND SUBMIT TBE - PRESSURE GAUGES - ICR | 15 | 2022-05-30 | 2022-06-20 | 2022-10-14 | 2022-11-03 | 96
0 | EDCMIN2305 | RECEIVE COMMENTS & ISSUE TBE - PRESSURE GAUGES - IFA | 10 | 2022-07-04 | 2022-07-21 | 2022-11-22 | 2022-12-07 | 98
0 | EDCMIN2310 | ISSUE TBE - PRESSURE GAUGES - IFC | 10 | 2022-08-04 | 2022-08-18 | 2023-01-17 | 2023-01-30 | 116
PRESSURE RELIEF VALVES |  |  | 85 | 2022-04-11 | 2022-08-16 | 2022-08-30 | 2023-01-20 | 112
REQUISITION |  |  | 49 | 2022-04-11 | 2022-06-22 | 2022-08-30 | 2022-11-29 | 112
0 | EDCMIN1240 | PRESSURE RELIEF VALVES - ISSUE MR - ICR | 5 | 2022-04-11 | 2022-04-18 | 2022-08-30 | 2022-09-05 | 95
0 | EDCMIN1245 | PRESSURE RELIEF VALVES - ISSUE MR - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-10-17 | 2022-10-28 | 114
0 | EDCMIN1250 | PRESSURE RELIEF VALVES - ISSUE MR - IFC | 10 | 2022-06-08 | 2022-06-22 | 2022-11-16 | 2022-11-29 | 112
TBE |  |  | 62 | 2022-05-17 | 2022-08-16 | 2022-09-30 | 2023-01-20 | 112
0 | EDCMIN2315 | COMPLETE EVALUATION AND SUBMIT TBE - PRESSURE RELIFE VALVES - ICR | 21 | 2022-05-17 | 2022-06-15 | 2022-09-30 | 2022-10-28 | 95
0 | EDCMIN2320 | RECEIVE COMMENTS & ISSUE TBE - PRESSURE RELIFE VALVES - IFA | 10 | 2022-06-29 | 2022-07-18 | 2022-11-16 | 2022-11-29 | 97
0 | EDCMIN2325 | ISSUE TBE - PRESSURE RELIFE VALVES - IFC | 11 | 2022-08-01 | 2022-08-16 | 2023-01-06 | 2023-01-20 | 112
TEMPERATURE GAUGES |  |  | 71 | 2022-06-07 | 2022-09-19 | 2022-09-21 | 2023-01-13 | 83
REQUISITION |  |  | 45 | 2022-06-07 | 2022-08-12 | 2022-09-21 | 2022-12-05 | 80
0 | EDCMIN1270 | TEMPERATURE GAUGES - ISSUE MR - ICR | 5 | 2022-06-07 | 2022-06-14 | 2022-09-21 | 2022-09-27 | 73
0 | EDCMIN1275 | TEMPERATURE GAUGES - ISSUE MR - IFA | 10 | 2022-06-28 | 2022-07-15 | 2022-10-19 | 2022-11-01 | 78
0 | EDCMIN1280 | TEMPERATURE GAUGES - ISSUE MR - IFC | 10 | 2022-07-29 | 2022-08-12 | 2022-11-18 | 2022-12-05 | 80
TBE |  |  | 51 | 2022-07-05 | 2022-09-19 | 2022-10-19 | 2023-01-13 | 83
0 | EDCMIN2330 | COMPLETE EVALUATION AND SUBMIT TBE - TEMPERATURE GAUGES - ICR | 10 | 2022-07-05 | 2022-07-22 | 2022-10-19 | 2022-11-01 | 73
0 | EDCMIN2335 | RECEIVE COMMENTS & ISSUE TBE - TEMPERATURE GAUGES - IFA | 10 | 2022-08-05 | 2022-08-19 | 2022-11-18 | 2022-12-05 | 75
0 | EDCMIN2340 | ISSUE TBE - TEMPERATURE GAUGES - IFC | 11 | 2022-09-02 | 2022-09-19 | 2022-12-30 | 2023-01-13 | 83
THERMAL FLOW SWITCH |  |  | 79 | 2022-06-09 | 2022-10-03 | 2022-11-01 | 2023-03-15 | 116
REQUISITION |  |  | 45 | 2022-06-09 | 2022-08-16 | 2022-11-01 | 2023-01-25 | 115
0 | EDCMIN1285 | THERMAL FLOW SWITCH - ISSUE MR - ICR | 5 | 2022-06-09 | 2022-06-16 | 2022-11-01 | 2022-11-07 | 100
0 | EDCMIN1290 | THERMAL FLOW SWITCH - ISSUE MR - IFA | 10 | 2022-06-30 | 2022-07-19 | 2022-12-13 | 2022-12-26 | 113
0 | EDCMIN1295 | THERMAL FLOW SWITCH - ISSUE MR - IFC | 10 | 2022-08-02 | 2022-08-16 | 2023-01-12 | 2023-01-25 | 115
TBE |  |  | 56 | 2022-07-15 | 2022-10-03 | 2022-12-06 | 2023-03-15 | 116
0 | EDCMIN2345 | COMPLETE EVALUATION AND SUBMIT TBE - THERMAL FLOW SWITCH - ICR | 15 | 2022-07-15 | 2022-08-05 | 2022-12-06 | 2022-12-26 | 100
0 | EDCMIN2350 | RECEIVE COMMENTS & ISSUE TBE - THERMAL FLOW SWITCH - IFA | 10 | 2022-08-19 | 2022-09-02 | 2023-01-12 | 2023-01-25 | 102
0 | EDCMIN2355 | ISSUE TBE - THERMAL FLOW SWITCH - IFC | 11 | 2022-09-16 | 2022-10-03 | 2023-03-01 | 2023-03-15 | 116
ELECTRONIC TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) |  |  | 79 | 2022-04-18 | 2022-08-15 | 2022-09-08 | 2023-01-23 | 114
REQUISITION |  |  | 52 | 2022-04-18 | 2022-07-04 | 2022-09-08 | 2022-11-30 | 105
0 | EDCMIN1300 | TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) - ISSUE MR - ICR | 5 | 2022-04-18 | 2022-04-25 | 2022-09-08 | 2022-09-14 | 97
0 | EDCMIN1305 | TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) - ISSUE MR - IFA | 10 | 2022-05-16 | 2022-05-30 | 2022-10-18 | 2022-10-31 | 108
0 | EDCMIN1310 | TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) - ISSUE MR - IFC | 10 | 2022-06-20 | 2022-07-04 | 2022-11-17 | 2022-11-30 | 105
TBE |  |  | 56 | 2022-05-24 | 2022-08-15 | 2022-10-11 | 2023-01-23 | 114
0 | EDCMIN2360 | COMPLETE EVALUATION AND SUBMIT TBE - TRANSMITTERS (PT, PDT, TT, FT, DP TYPE) - ICR | 15 | 2022-05-24 | 2022-06-14 | 2022-10-11 | 2022-10-31 | 97
0 | EDCMIN2365 | RECEIVE COMMENTS & ISSUE TBE - TRANSMITTERS (PT, PDT, TT, FT, DP TYPE) - IFA | 10 | 2022-06-28 | 2022-07-15 | 2022-11-17 | 2022-11-30 | 99
0 | EDCMIN2370 | ISSUE TBE - TRANSMITTERS (PT, PDT, TT, FT, DP TYPE) - IFC | 11 | 2022-07-29 | 2022-08-15 | 2023-01-09 | 2023-01-23 | 114
WET GAS FLOW METER (WGFM) |  |  | 79 | 2022-04-08 | 2022-08-05 | 2022-06-13 | 2022-10-12 | 49
REQUISITION |  |  | 50 | 2022-04-08 | 2022-06-22 | 2022-06-13 | 2022-09-07 | 53
0 | EDCMIN1410 | WET GAS FLOW METER (WGFM) - ISSUE MR - ICR | 5 | 2022-04-08 | 2022-04-15 | 2022-06-13 | 2022-06-17 | 43
0 | EDCMIN1415 | WET GAS FLOW METER (WGFM) - ISSUE MR - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-07-26 | 2022-08-08 | 56
0 | EDCMIN1420 | WET GAS FLOW METER (WGFM) - ISSUE MR - IFC | 10 | 2022-06-08 | 2022-06-22 | 2022-08-25 | 2022-09-07 | 53
TBE |  |  | 56 | 2022-05-16 | 2022-08-05 | 2022-07-19 | 2022-10-12 | 49
0 | EDCMIN2375 | COMPLETE EVALUATION AND SUBMIT TBE - WET GAS FLOW METER - ICR | 15 | 2022-05-16 | 2022-06-06 | 2022-07-19 | 2022-08-08 | 43
0 | EDCMIN2380 | RECEIVE COMMENTS & ISSUE TBE - WET GAS FLOW METER - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-08-25 | 2022-09-07 | 45
0 | EDCMIN2385 | ISSUE TBE - WET GAS FLOW METER - IFC | 11 | 2022-07-21 | 2022-08-05 | 2022-09-28 | 2022-10-12 | 49
E&I STRUCTURAL STEEL |  |  | 80 | 2022-06-02 | 2022-09-27 | 2022-10-11 | 2023-02-03 | 92
REQUISITION |  |  | 45 | 2022-06-02 | 2022-08-09 | 2022-10-11 | 2023-01-06 | 107
0 | EDCMIN1425 | E&I STRUCTURAL STEEL - ISSUE MR - ICR | 5 | 2022-06-02 | 2022-06-09 | 2022-10-11 | 2022-10-17 | 90
0 | EDCMIN1430 | E&I STRUCTURAL STEEL - ISSUE MR - IFA | 10 | 2022-06-23 | 2022-07-07 | 2022-11-22 | 2022-12-07 | 105
0 | EDCMIN1435 | E&I STRUCTURAL STEEL - ISSUE MR - IFC | 10 | 2022-07-26 | 2022-08-09 | 2022-12-26 | 2023-01-06 | 107
TBE |  |  | 55 | 2022-07-07 | 2022-09-27 | 2022-11-15 | 2023-02-03 | 92
0 | EDCMIN2390 | COMPLETE EVALUATION AND SUBMIT TBE - E&I STRUCTURAL STEEL - ICR | 15 | 2022-07-07 | 2022-08-02 | 2022-11-15 | 2022-12-07 | 90
0 | EDCMIN2395 | RECEIVE COMMENTS & ISSUE TBE - E&I STRUCTURAL STEEL - IFA | 10 | 2022-08-16 | 2022-08-30 | 2022-12-26 | 2023-01-06 | 92
0 | EDCMIN2400 | ISSUE TBE - E&I STRUCTURAL STEEL - IFC | 10 | 2022-09-13 | 2022-09-27 | 2023-01-23 | 2023-02-03 | 92
TELECOM |  |  | 135 | 2022-02-07 | 2022-08-23 | 2022-04-08 | 2023-01-24 | 109
DOCUMENTS |  |  | 96 | 2022-02-07 | 2022-06-24 | 2022-04-08 | 2023-01-04 | 134
DESIGN BASIS |  |  | 51 | 2022-02-07 | 2022-04-19 | 2022-04-08 | 2022-07-22 | 63
0 | EDCDTE1050 | TELECOMMUNICATION DESIGN BASIS - ICR | 16 | 2022-02-07 | 2022-03-01 | 2022-04-08 | 2022-04-29 | 44
0 | EDCDTE1055 | TELECOMMUNICATION DESIGN BASIS - IFA | 10 | 2022-03-15 | 2022-03-29 | 2022-06-15 | 2022-06-28 | 63
0 | EDCDTE1060 | TELECOMMUNICATION DESIGN BASIS - IFC | 5 | 2022-04-12 | 2022-04-19 | 2022-07-18 | 2022-07-22 | 63
SPECIFICATION |  |  | 86 | 2022-02-21 | 2022-06-24 | 2022-04-22 | 2023-01-04 | 134
0 | EDCDTE1000 | SPECIFICATIONS FOR SUBSEA FO CABLE - ICR | 16 | 2022-02-21 | 2022-03-15 | 2022-04-22 | 2022-05-18 | 44
0 | EDCDTE1015 | SPECIFICATIONS FOR FO CABLE - ICR | 15 | 2022-03-07 | 2022-03-28 | 2022-09-27 | 2022-10-17 | 140
0 | EDCDTE1070 | SPECIFICATION FOR TELECOMMUNICATION SYSTEM - ICR | 15 | 2022-03-15 | 2022-04-05 | 2022-08-16 | 2022-09-05 | 104
0 | EDCDTE1005 | SPECIFICATIONS FOR SUBSEA FO CABLE - IFA | 15 | 2022-03-29 | 2022-04-19 | 2022-06-29 | 2022-07-22 | 63
0 | EDCDTE1020 | SPECIFICATIONS FOR FO CABLE - IFA | 15 | 2022-04-11 | 2022-05-05 | 2022-11-01 | 2022-11-21 | 140
0 | EDCDTE1075 | SPECIFICATION FOR TELECOMMUNICATION SYSTEM - IFA | 15 | 2022-04-19 | 2022-05-13 | 2022-09-20 | 2022-10-10 | 104
0 | EDCDTE1010 | SPECIFICATIONS FOR SUBSEA FO CABLE - IFC | 15 | 2022-05-06 | 2022-05-27 | 2022-08-23 | 2022-09-12 | 74
0 | EDCDTE1025 | SPECIFICATIONS FOR FO CABLE - IFC | 20 | 2022-05-19 | 2022-06-16 | 2022-12-08 | 2023-01-04 | 140
0 | EDCDTE1080 | SPECIFICATION FOR TELECOMMUNICATION SYSTEM - IFC | 20 | 2022-05-27 | 2022-06-24 | 2022-10-25 | 2022-11-21 | 104
DATA SHEET |  |  | 65 | 2022-03-03 | 2022-06-07 | 2022-05-19 | 2022-09-21 | 74
0 | EDCDTE1030 | DATA SHEET FOR SUBSEA FO CABLE - ICR | 15 | 2022-03-03 | 2022-03-24 | 2022-05-19 | 2022-06-08 | 52
0 | EDCDTE1035 | DATA SHEET FOR SUBSEA FO CABLE - IFA | 15 | 2022-04-07 | 2022-04-28 | 2022-07-13 | 2022-08-02 | 63
0 | EDCDTE1040 | DATA SHEET FOR SUBSEA FO CABLE - IFC | 15 | 2022-05-17 | 2022-06-07 | 2022-09-01 | 2022-09-21 | 74
DRAWINGS |  |  | 84 | 2022-04-19 | 2022-08-23 | 2022-09-20 | 2023-01-24 | 109
0 | EDCGTE1000 | TELECOMMUNICATION SYSTEM BLOCK DIAGRAM - ICR | 15 | 2022-04-19 | 2022-05-13 | 2022-09-20 | 2022-10-10 | 104
0 | EDCGTE1050 | FIBER OPTIC NETWORK BLOCK DIAGRAM - ICR | 15 | 2022-04-25 | 2022-05-19 | 2022-10-07 | 2022-10-27 | 113
0 | EDCGTE1030 | SUBSEA FOC ROUTING LAYOUTS - ZIRKU ISLAND - ICR | 15 | 2022-05-13 | 2022-06-03 | 2022-10-24 | 2022-11-11 | 113
0 | EDCGTE1015 | SUBSEA FOC ROUTING LAYOUTS - ARZANAH ISLAND - ICR | 15 | 2022-05-13 | 2022-06-03 | 2022-10-18 | 2022-11-07 | 109
0 | EDCGTE1080 | TELECOMMUNICATION EQUIPMENT INSTALLATION DRAWINGS - ICR | 15 | 2022-05-19 | 2022-06-09 | 2022-10-18 | 2022-11-07 | 105
0 | EDCGTE1005 | TELECOMMUNICATION SYSTEM BLOCK DIAGRAM - IFA | 15 | 2022-05-27 | 2022-06-17 | 2022-11-01 | 2022-11-21 | 109
0 | EDCGTE1060 | FIBER OPTIC NETWORK BLOCK DIAGRAM - IFA | 15 | 2022-06-02 | 2022-06-23 | 2022-11-11 | 2022-12-05 | 113
0 | EDCGTE1020 | SUBSEA FOC ROUTING LAYOUTS - ARZANAH ISLAND - IFA | 15 | 2022-06-17 | 2022-07-13 | 2022-11-22 | 2022-12-14 | 109
0 | EDCGTE1035 | SUBSEA FOC ROUTING LAYOUTS - ZIRKU ISLAND - IFA | 15 | 2022-06-17 | 2022-07-13 | 2022-11-28 | 2022-12-20 | 113
0 | EDCGTE1090 | TELECOMMUNICATION EQUIPMENT INSTALLATION DRAWINGS - IFA | 15 | 2022-06-23 | 2022-07-19 | 2022-11-22 | 2022-12-14 | 105
0 | EDCGTE1010 | TELECOMMUNICATION SYSTEM BLOCK DIAGRAM - IFC | 15 | 2022-07-01 | 2022-07-27 | 2022-12-08 | 2022-12-28 | 109
0 | EDCGTE1070 | FIBER OPTIC NETWORK BLOCK DIAGRAM - IFC | 15 | 2022-07-13 | 2022-08-03 | 2022-12-20 | 2023-01-09 | 112
0 | EDCGTE1040 | SUBSEA FOC ROUTING LAYOUTS - ZIRKU ISLAND - IFC | 15 | 2022-07-27 | 2022-08-17 | 2023-01-04 | 2023-01-24 | 113
0 | EDCGTE1025 | SUBSEA FOC ROUTING LAYOUTS - ARZANAH ISLAND - IFC | 15 | 2022-07-27 | 2022-08-17 | 2022-12-29 | 2023-01-18 | 109
0 | EDCGTE1100 | TELECOMMUNICATION EQUIPMENT INSTALLATION DRAWINGS - IFC | 15 | 2022-08-02 | 2022-08-23 | 2022-12-29 | 2023-01-18 | 105
REQUISITIONS |  |  | 63 | 2022-04-05 | 2022-07-06 | 2022-06-09 | 2022-09-21 | 53
REQUISITION |  |  | 63 | 2022-04-05 | 2022-07-06 | 2022-06-09 | 2022-09-21 | 53
0 | EDCMTE1000 | SUBSEA FIBRE OPTIC CABLE - ISSUE MR - ICR | 10 | 2022-04-05 | 2022-04-19 | 2022-06-09 | 2022-06-22 | 44
0 | EDCMTE1005 | SUBSEA FIBRE OPTIC CABLE - ISSUE MR - IFA | 14 | 2022-05-06 | 2022-05-26 | 2022-07-25 | 2022-08-11 | 53
0 | EDCMTE1010 | SUBSEA FIBRE OPTIC CABLE - ISSUE MR - IFC | 19 | 2022-06-09 | 2022-07-06 | 2022-08-26 | 2022-09-21 | 53
TBE |  |  | 41 | 2022-05-20 | 2022-07-21 | 2022-07-26 | 2022-11-02 | 75
0 | EDCMTE2000 | COMPLETE EVALUATION AND SUBMIT TBE - SUBSEA FO CABLE - ICR | 20 | 2022-05-20 | 2022-06-17 | 2022-07-26 | 2022-08-22 | 44
0 | EDCMTE2005 | RECEIVE TBE COMPANY APPROVAL - SUBSEA FO CABLE | 10 | 2022-06-17 | 2022-07-01 | 2022-09-08 | 2022-09-21 | 56
0 | EDCMTE2010 | ISSUE TBE - SUBSEA FO CABLE - IFC | 10 | 2022-07-04 | 2022-07-21 | 2022-10-20 | 2022-11-02 | 75
CIVIL |  |  | 81 | 2022-05-26 | 2022-09-20 | 2022-07-21 | 2023-04-27 | 153
DOCUMENT |  |  | 80 | 2022-05-26 | 2022-09-19 | 2022-07-21 | 2022-11-16 | 42
SPECIFICATION |  |  | 80 | 2022-05-26 | 2022-09-19 | 2022-07-21 | 2022-11-16 | 42
0 | EDCDCI1000 | CONCRETE SLEEPER DESIGN REPORT - ICR | 10 | 2022-05-26 | 2022-06-08 | 2022-07-21 | 2022-08-03 | 37
0 | EDCDCI1015 | SPECIFICATION FOR CONCRETE SLEEPERS - ICR | 10 | 2022-06-02 | 2022-06-15 | 2022-07-28 | 2022-08-10 | 37
0 | EDCDCI1005 | CONCRETE SLEEPER DESIGN REPORT - IFA | 10 | 2022-06-21 | 2022-07-04 | 2022-09-26 | 2022-10-07 | 66
0 | EDCDCI1020 | SPECIFICATION FOR CONCRETE SLEEPERS - IFA | 10 | 2022-06-30 | 2022-07-18 | 2022-08-25 | 2022-09-07 | 37
0 | EDCDCI1030 | SOW FOR FABRICATION AND SUPPLY OF OFFSHORE CONCRETE SLEEPERS - ICR | 10 | 2022-07-19 | 2022-08-01 | 2022-09-08 | 2022-09-21 | 37
0 | EDCDCI1010 | CONCRETE SLEEPER DESIGN REPORT - IFC | 20 | 2022-08-02 | 2022-08-29 | 2022-10-20 | 2022-11-16 | 57
0 | EDCDCI1025 | SPECIFICATION FOR CONCRETE SLEEPERS - IFC | 20 | 2022-08-02 | 2022-08-29 | 2022-10-20 | 2022-11-16 | 57
0 | EDCDCI1035 | SOW FOR FABRICATION AND SUPPLY OF OFFSHORE CONCRETE SLEEPERS - IFA | 10 | 2022-08-16 | 2022-08-29 | 2022-10-13 | 2022-10-26 | 42
0 | EDCDCI1040 | SOW FOR FABRICATION AND SUPPLY OF OFFSHORE CONCRETE SLEEPERS - IFC | 5 | 2022-09-13 | 2022-09-19 | 2022-11-10 | 2022-11-16 | 42
DRAWINGS |  |  | 66 | 2022-06-16 | 2022-09-20 | 2023-01-24 | 2023-04-27 | 153
0 | EDCGCI1000 | DETAIL DRAWINGS FOR OFFSHORE CONCRETE SLEEPERS - ICR | 15 | 2022-06-16 | 2022-07-06 | 2023-01-24 | 2023-02-13 | 153
0 | EDCGCI1005 | DETAIL DRAWINGS FOR OFFSHORE CONCRETE SLEEPERS - IFA | 15 | 2022-07-22 | 2022-08-11 | 2023-02-24 | 2023-03-16 | 153
0 | EDCGCI1010 | DETAIL DRAWINGS FOR OFFSHORE CONCRETE SLEEPERS - IFC | 20 | 2022-08-24 | 2022-09-20 | 2023-03-29 | 2023-04-27 | 153
STRUCTURAL |  |  | 200 | 2021-12-19 | 2022-10-03 | 2022-03-16 | 2023-04-27 | 145
DOCUMENTS |  |  | 200 | 2021-12-19 | 2022-10-03 | 2022-03-16 | 2023-04-27 | 145
DESIGN BASIS |  |  | 75 | 2021-12-19 | 2022-04-01 | 2022-03-16 | 2022-07-22 | 75
0 | EDCDSR1000 | STRUCTURAL DESIGN BASIS AND DESIGN DATA - ICR | 20 | 2021-12-19 | 2022-01-14 | 2022-03-16 | 2022-04-12 | 63
0 | EDCDSR1005 | STRUCTURAL DESIGN BASIS AND DESIGN DATA - IFA | 20 | 2022-01-28 | 2022-02-25 | 2022-04-28 | 2022-05-30 | 64
0 | EDCDSR1010 | STRUCTURAL DESIGN BASIS AND DESIGN DATA - IFC | 15 | 2022-03-11 | 2022-04-01 | 2022-06-29 | 2022-07-22 | 75
SCOPE OF WORK |  |  | 161 | 2022-02-10 | 2022-10-03 | 2022-07-13 | 2023-04-27 | 145
3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL AND CERTIFICATION |  |  | 87 | 2022-02-10 | 2022-06-16 | 2022-07-13 | 2022-11-30 | 117
SCOPE OF WORK |  |  | 71 | 2022-02-10 | 2022-05-25 | 2022-07-13 | 2022-11-03 | 114
0 | EDCDSR1015 | SCOPE OF WORK FOR 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL AND CERTIFICATION - ICR | 21 | 2022-02-10 | 2022-03-11 | 2022-07-13 | 2022-08-10 | 103
0 | EDCDSR1020 | SCOPE OF WORK FOR 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL AND CERTIFICATION - IFA | 15 | 2022-03-25 | 2022-04-15 | 2022-09-09 | 2022-09-29 | 114
0 | EDCDSR1025 | SCOPE OF WORK FOR 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL AND CERTIFICATION - IFC | 15 | 2022-04-29 | 2022-05-25 | 2022-10-14 | 2022-11-03 | 114
TBE |  |  | 45 | 2022-04-11 | 2022-06-16 | 2022-09-16 | 2022-11-30 | 117
0 | EDCDSR2000 | ISSUE TBE : 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL & CERTIFICATION - ICR | 15 | 2022-04-11 | 2022-05-05 | 2022-09-16 | 2022-10-06 | 108
0 | EDCDSR2005 | ISSUE TBE : 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL & CERTIFICATION - IFA | 5 | 2022-05-19 | 2022-05-26 | 2022-10-21 | 2022-10-27 | 108
0 | EDCDSR2015 | ISSUE TBE : 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL & CERTIFICATION - IFC | 5 | 2022-06-09 | 2022-06-16 | 2022-11-24 | 2022-11-30 | 117
SCOPE OF WORK FOR COLD BENDING OF J TUBES |  |  | 90 | 2022-05-25 | 2022-10-03 | 2022-12-21 | 2023-04-27 | 145
SCOPE OF WORK |  |  | 80 | 2022-05-25 | 2022-09-19 | 2022-12-21 | 2023-04-18 | 150
0 | EDCDSR2025 | SCOPE OF WORK FOR COLD BENDING OF J TUBES - ICR | 20 | 2022-05-25 | 2022-06-22 | 2022-12-21 | 2023-01-17 | 145
0 | EDCDSR2035 | SCOPE OF WORK FOR COLD BENDING OF J TUBES - IFA | 20 | 2022-07-06 | 2022-08-08 | 2023-02-08 | 2023-03-07 | 150
0 | EDCDSR2045 | SCOPE OF WORK FOR COLD BENDING OF J TUBES - IFC | 20 | 2022-08-22 | 2022-09-19 | 2023-03-22 | 2023-04-18 | 150
TBE |  |  | 45 | 2022-08-01 | 2022-10-03 | 2023-02-22 | 2023-04-27 | 145
0 | EDCDSR2055 | ISSUE TBE : COLD BENDING OF J TUBES WORKS - ICR | 15 | 2022-08-01 | 2022-08-22 | 2023-02-22 | 2023-03-14 | 145
0 | EDCDSR2065 | ISSUE TBE : COLD BENDING OF J TUBES WORKS - IFA | 5 | 2022-09-05 | 2022-09-12 | 2023-03-29 | 2023-04-04 | 145
0 | EDCDSR2075 | ISSUE TBE : COLD BENDING OF J TUBES WORKS - IFC | 5 | 2022-09-26 | 2022-10-03 | 2023-04-19 | 2023-04-27 | 145
SPECIFICATIONS |  |  | 155 | 2021-12-23 | 2022-08-08 | 2022-03-25 | 2023-03-02 | 147
0 | EDCDSR1045 | SPECIFICATION FOR OFFSHORE STRUCTURAL STEEL MATERIAL - ICR | 22 | 2021-12-23 | 2022-01-25 | 2022-03-25 | 2022-04-25 | 65
0 | EDCDSR1060 | SPECIFICATION FOR BOLTS NUTS AND WASHERS FOR OFFSHORE STRUCTURES - ICR | 14 | 2022-01-12 | 2022-02-01 | 2022-04-12 | 2022-05-05 | 65
0 | EDCDSR1075 | SPECIFICATION FOR EQUIPMENT SKIDS - ICR | 19 | 2022-01-14 | 2022-02-10 | 2022-04-13 | 2022-05-12 | 63
0 | EDCDSR1050 | SPECIFICATION FOR OFFSHORE STRUCTURAL STEEL MATERIAL - IFA | 16 | 2022-02-08 | 2022-03-02 | 2022-06-10 | 2022-07-01 | 85
0 | EDCDSR1065 | SPECIFICATION FOR BOLTS NUTS AND WASHERS FOR OFFSHORE STRUCTURES - IFA | 15 | 2022-02-15 | 2022-03-08 | 2022-06-10 | 2022-06-30 | 80
0 | EDCDSR1090 | SPECIFICATION FOR GRATINGS STAIR TREADS AND HANDRAILS OF OFFSHORE STRUCTURES - ICR | 20 | 2022-02-10 | 2022-03-10 | 2022-05-13 | 2022-06-09 | 63
0 | EDCDSR1080 | SPECIFICATION FOR EQUIPMENT SKIDS - IFA | 16 | 2022-02-24 | 2022-03-18 | 2022-08-10 | 2022-08-31 | 113
0 | EDCDSR1055 | SPECIFICATION FOR OFFSHORE STRUCTURAL STEEL MATERIAL - IFC | 9 | 2022-03-16 | 2022-03-29 | 2022-07-21 | 2022-08-02 | 85
0 | EDCDSR1070 | SPECIFICATION FOR BOLTS NUTS AND WASHERS FOR OFFSHORE STRUCTURES - IFC | 14 | 2022-03-22 | 2022-04-11 | 2022-07-20 | 2022-08-08 | 80
0 | EDCDSR1095 | SPECIFICATION FOR GRATINGS STAIR TREADS AND HANDRAILS OF OFFSHORE STRUCTURES - IFA | 15 | 2022-03-24 | 2022-04-14 | 2022-10-14 | 2022-11-03 | 140
0 | EDCDSR1120 | SPECIFICATION FOR HELIDECK SAFETY NET - ICR | 21 | 2022-03-17 | 2022-04-15 | 2022-06-17 | 2022-07-20 | 63
0 | EDCDSR1105 | SPECIFICATION FOR FABRICATION OF OFFSHORE STRUCTURES - ICR | 21 | 2022-03-17 | 2022-04-15 | 2022-06-17 | 2022-07-20 | 63
0 | EDCDSR1085 | SPECIFICATION FOR EQUIPMENT SKIDS - IFC | 15 | 2022-04-01 | 2022-04-22 | 2022-09-15 | 2022-10-05 | 113
0 | EDCDSR1135 | SPECIFICATION FOR MISCELLANEOUS ITEMS OF OFFSHORE STRUCTURES - ICR | 21 | 2022-03-24 | 2022-04-22 | 2022-06-24 | 2022-07-27 | 63
0 | EDCDSR1150 | SPECIFICATION OF ANODES FOR CATHODIC PROTECTION - ICR | 21 | 2022-04-07 | 2022-05-11 | 2022-07-13 | 2022-08-10 | 63
0 | EDCDSR1165 | SPECIFICATION FOR PASSIVE FIRE PROTECTION - ICR | 20 | 2022-04-15 | 2022-05-18 | 2022-08-18 | 2022-09-14 | 83
0 | EDCDSR1180 | SPECIFICATION FOR LOADOUT TRANSPORTATION AND INSTALLATION OF OFFSHORE STRUCTURES - ICR | 20 | 2022-04-22 | 2022-05-25 | 2022-08-25 | 2022-09-21 | 83
0 | EDCDSR1110 | SPECIFICATION FOR FABRICATION OF OFFSHORE STRUCTURES - IFA | 15 | 2022-04-29 | 2022-05-25 | 2022-10-14 | 2022-11-03 | 114
0 | EDCDSR1125 | SPECIFICATION FOR HELIDECK SAFETY NET - IFA | 15 | 2022-04-29 | 2022-05-25 | 2022-09-14 | 2022-10-04 | 92
0 | EDCDSR1140 | SPECIFICATION FOR MISCELLANEOUS ITEMS OF OFFSHORE STRUCTURES - IFA | 15 | 2022-05-11 | 2022-06-01 | 2022-10-14 | 2022-11-03 | 109
0 | EDCDSR1155 | SPECIFICATION OF ANODES FOR CATHODIC PROTECTION - IFA | 15 | 2022-05-25 | 2022-06-15 | 2022-08-25 | 2022-09-14 | 63
0 | EDCDSR1170 | SPECIFICATION FOR PASSIVE FIRE PROTECTION - IFA | 15 | 2022-06-01 | 2022-06-22 | 2022-11-22 | 2022-12-14 | 121
0 | EDCDSR1130 | SPECIFICATION FOR HELIDECK SAFETY NET - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-10-19 | 2022-11-08 | 92
0 | EDCDSR1115 | SPECIFICATION FOR FABRICATION OF OFFSHORE STRUCTURES - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-11-18 | 2022-12-12 | 114
0 | EDCDSR1100 | SPECIFICATION FOR GRATINGS STAIR TREADS AND HANDRAILS OF OFFSHORE STRUCTURES - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-11-18 | 2022-12-12 | 114
0 | EDCDSR1185 | SPECIFICATION FOR LOADOUT TRANSPORTATION AND INSTALLATION OF OFFSHORE STRUCTURES - IFA | 15 | 2022-06-08 | 2022-06-29 | 2023-01-06 | 2023-01-26 | 147
0 | EDCDSR1145 | SPECIFICATION FOR MISCELLANEOUS ITEMS OF OFFSHORE STRUCTURES - IFC | 15 | 2022-06-15 | 2022-07-06 | 2022-11-18 | 2022-12-12 | 109
0 | EDCDSR1160 | SPECIFICATION OF ANODES FOR CATHODIC PROTECTION - IFC | 15 | 2022-06-29 | 2022-07-25 | 2022-09-29 | 2022-10-19 | 63
0 | EDCDSR1175 | SPECIFICATION FOR PASSIVE FIRE PROTECTION - IFC | 15 | 2022-07-06 | 2022-08-01 | 2022-12-29 | 2023-01-18 | 121
0 | EDCDSR1190 | SPECIFICATION FOR LOADOUT TRANSPORTATION AND INSTALLATION OF OFFSHORE STRUCTURES - IFC | 15 | 2022-07-18 | 2022-08-08 | 2023-02-10 | 2023-03-02 | 147
DRAWINGS |  |  | 95 | 2022-01-28 | 2022-06-15 | 2022-04-28 | 2023-03-02 | 182
0 | EDCGSR1000 | GENERAL NOTES AND ABBREVIATIONS - ICR | 15 | 2022-01-28 | 2022-02-18 | 2022-04-28 | 2022-05-23 | 64
0 | EDCGSR1015 | STANDARD CONNECTION DETAILS - IRC | 15 | 2022-02-04 | 2022-02-25 | 2022-06-02 | 2022-06-22 | 81
0 | EDCGSR1045 | STANDARD DECK DRAIN & MISCELLANEOUS DETAILS - IRC | 15 | 2022-02-11 | 2022-03-04 | 2022-06-09 | 2022-06-29 | 81
0 | EDCGSR1030 | STANDARD WELDING DETAILS - IRC | 15 | 2022-02-11 | 2022-03-04 | 2022-06-09 | 2022-06-29 | 81
0 | EDCGSR1060 | STANDARD FIXED HANDRAIL DETAILS - IRC | 15 | 2022-02-18 | 2022-03-11 | 2022-06-16 | 2022-07-06 | 81
0 | EDCGSR1075 | STANDARD LADDER DETAILS - IRC | 15 | 2022-02-18 | 2022-03-11 | 2022-06-16 | 2022-07-06 | 81
0 | EDCGSR1090 | STANDARD PENETRATION DETAILS - IRC | 15 | 2022-02-25 | 2022-03-18 | 2022-06-23 | 2022-07-18 | 81
0 | EDCGSR1105 | STANDARD PLATING & GRATING DETAILS - ICR | 15 | 2022-02-25 | 2022-03-18 | 2022-06-23 | 2022-07-18 | 81
0 | EDCGSR1005 | GENERAL NOTES AND ABBREVIATIONS - IFA | 10 | 2022-03-04 | 2022-03-18 | 2022-08-29 | 2022-09-09 | 120
0 | EDCGSR1120 | STANDARD REMOVABLE HANDRAIL DETAILS - ICR | 15 | 2022-03-04 | 2022-03-25 | 2022-06-30 | 2022-07-25 | 81
0 | EDCGSR1135 | STANDARD STAIR DETAILS - IRC | 15 | 2022-03-04 | 2022-03-25 | 2022-06-30 | 2022-07-25 | 81
0 | EDCGSR1170 | STANDARD CONNECTION DETAILS - IFA | 10 | 2022-03-11 | 2022-03-25 | 2022-09-05 | 2022-09-16 | 120
0 | EDCGSR1150 | STANDARD BUILT UP SECTION DETAILS - ICR | 15 | 2022-03-11 | 2022-04-01 | 2022-07-07 | 2022-08-01 | 81
0 | EDCGSR1180 | STANDARD WELDING DETAILS - IFA | 15 | 2022-03-18 | 2022-04-08 | 2022-09-05 | 2022-09-23 | 115
0 | EDCGSR1190 | STANDARD DECK DRAIN & MISCELLANEOUS DETAILS - IFA | 15 | 2022-03-18 | 2022-04-08 | 2022-12-09 | 2022-12-29 | 182
0 | EDCGSR1210 | STANDARD LADDER DETAILS - IFA | 10 | 2022-03-25 | 2022-04-08 | 2023-01-13 | 2023-01-26 | 202
0 | EDCGSR1230 | STANDARD PLATING & GRATING DETAILS - IFA | 15 | 2022-03-18 | 2022-04-08 | 2022-11-04 | 2022-11-24 | 159
0 | EDCGSR1200 | STANDARD FIXED HANDRAIL DETAILS - IFA | 15 | 2022-03-25 | 2022-04-15 | 2022-12-30 | 2023-01-19 | 192
0 | EDCGSR1240 | STANDARD REMOVABLE HANDRAIL DETAILS - IFA | 15 | 2022-03-25 | 2022-04-15 | 2022-11-04 | 2022-11-24 | 154
0 | EDCGSR1250 | STANDARD STAIR DETAILS - IFA | 15 | 2022-03-25 | 2022-04-15 | 2022-11-07 | 2022-11-25 | 155
0 | EDCGSR1010 | GENERAL NOTES AND ABBREVIATIONS - IFC | 15 | 2022-04-01 | 2022-04-22 | 2022-09-26 | 2022-10-14 | 120
0 | EDCGSR1115 | STANDARD PLATING & GRATING DETAILS - IFC | 10 | 2022-04-08 | 2022-04-22 | 2022-11-25 | 2022-12-12 | 159
0 | EDCGSR1220 | STANDARD PENETRATION DETAILS - IFA | 15 | 2022-04-01 | 2022-04-22 | 2022-11-10 | 2022-11-30 | 153
0 | EDCGSR1025 | STANDARD CONNECTION DETAILS - IFC | 15 | 2022-04-08 | 2022-04-29 | 2022-10-03 | 2022-10-21 | 120
0 | EDCGSR1130 | STANDARD REMOVABLE HANDRAIL DETAILS - IFC | 10 | 2022-04-15 | 2022-04-29 | 2022-11-25 | 2022-12-12 | 154
0 | EDCGSR1145 | STANDARD STAIR DETAILS - IFC | 10 | 2022-04-15 | 2022-04-29 | 2022-11-28 | 2022-12-13 | 155
0 | EDCGSR1260 | STANDARD BUILT UP SECTION DETAILS - IFA | 15 | 2022-04-15 | 2022-05-11 | 2022-09-12 | 2022-09-30 | 100
0 | EDCGSR1055 | STANDARD DECK DRAIN & MISCELLANEOUS DETAILS - IFC | 15 | 2022-04-22 | 2022-05-18 | 2023-01-13 | 2023-02-02 | 182
0 | EDCGSR1040 | STANDARD WELDING DETAILS - IFC | 15 | 2022-04-22 | 2022-05-18 | 2022-10-10 | 2022-10-28 | 115
0 | EDCGSR1100 | STANDARD PENETRATION DETAILS - IFC | 20 | 2022-04-22 | 2022-05-25 | 2022-12-05 | 2022-12-30 | 153
0 | EDCGSR1070 | STANDARD FIXED HANDRAIL DETAILS - IFC | 10 | 2022-05-18 | 2022-06-01 | 2023-02-03 | 2023-02-16 | 182
0 | EDCGSR1160 | STANDARD BUILT UP SECTION DETAILS - IFC | 10 | 2022-05-25 | 2022-06-08 | 2022-10-17 | 2022-10-28 | 100
0 | EDCGSR1085 | STANDARD LADDER DETAILS - IFC | 15 | 2022-05-25 | 2022-06-15 | 2023-02-10 | 2023-03-02 | 182
REQUISITIONS |  |  | 163 | 2022-01-18 | 2022-09-12 | 2022-04-25 | 2023-04-07 | 148
CS PLATES |  |  | 67 | 2022-01-18 | 2022-04-21 | 2022-04-25 | 2022-09-05 | 92
REQUISITION |  |  | 52 | 2022-01-18 | 2022-03-31 | 2022-04-25 | 2022-07-13 | 69
0 | EDCMSR1000 | CS PLATES - ISSUE MR - ICR | 5 | 2022-01-18 | 2022-01-25 | 2022-04-25 | 2022-04-29 | 69
0 | EDCMSR1005 | CS PLATES - ISSUE MR - IFA | 15 | 2022-02-08 | 2022-03-01 | 2022-05-19 | 2022-06-08 | 69
0 | EDCMSR1010 | CS PLATES - ISSUE MR - IFC | 15 | 2022-03-10 | 2022-03-31 | 2022-06-20 | 2022-07-13 | 69
TBE |  |  | 49 | 2022-02-11 | 2022-04-21 | 2022-06-09 | 2022-09-05 | 92
0 | EDCMSR2000 | COMPLETE EVALUATION AND SUBMIT TBE - CS PLATES - ICR | 14 | 2022-02-11 | 2022-03-03 | 2022-06-09 | 2022-06-28 | 81
0 | EDCMSR2005 | RECEIVE COMMENTS & ISSUE TBE - CS PLATES - IFA | 10 | 2022-03-17 | 2022-03-31 | 2022-07-20 | 2022-08-02 | 83
0 | EDCMSR2010 | ISSUE TBE - CS PLATES - IFC | 5 | 2022-04-14 | 2022-04-21 | 2022-08-30 | 2022-09-05 | 92
SAW TUBULAR |  |  | 65 | 2022-01-20 | 2022-04-21 | 2022-05-09 | 2022-09-02 | 91
REQUISITION |  |  | 42 | 2022-01-20 | 2022-03-21 | 2022-05-09 | 2022-07-22 | 84
0 | EDCMSR1015 | SAW TUBULAR - ISSUE MR - ICR | 5 | 2022-01-20 | 2022-01-27 | 2022-05-09 | 2022-05-13 | 74
0 | EDCMSR1020 | SAW TUBULAR - ISSUE MR - IFA | 10 | 2022-02-10 | 2022-02-24 | 2022-06-13 | 2022-06-24 | 84
0 | EDCMSR1025 | SAW TUBULAR - ISSUE MR - IFC | 10 | 2022-03-07 | 2022-03-21 | 2022-07-06 | 2022-07-22 | 84
TBE |  |  | 47 | 2022-02-15 | 2022-04-21 | 2022-06-02 | 2022-09-02 | 91
0 | EDCMSR2015 | COMPLETE EVALUATION AND SUBMIT TBE - SAW TUBULAR - ICR | 12 | 2022-02-15 | 2022-03-03 | 2022-06-02 | 2022-06-17 | 74
0 | EDCMSR2020 | RECEIVE COMMENTS & ISSUE TBE - SAW TUBULAR - IFA | 10 | 2022-03-17 | 2022-03-31 | 2022-07-06 | 2022-07-22 | 76
0 | EDCMSR2025 | ISSUE TBE - SAW TUBULAR - IFC | 5 | 2022-04-14 | 2022-04-21 | 2022-08-29 | 2022-09-02 | 91
SEAMLESS TUBULAR |  |  | 71 | 2022-01-20 | 2022-04-29 | 2022-05-09 | 2022-09-02 | 85
REQUISITION |  |  | 42 | 2022-01-20 | 2022-03-21 | 2022-05-09 | 2022-07-22 | 84
0 | EDCMSR1030 | SEAMLESS TUBULAR - ISSUE MR - ICR | 5 | 2022-01-20 | 2022-01-27 | 2022-05-09 | 2022-05-13 | 74
0 | EDCMSR1035 | SEAMLESS TUBULAR - ISSUE MR - IFA | 10 | 2022-02-10 | 2022-02-24 | 2022-06-13 | 2022-06-24 | 84
0 | EDCMSR1040 | SEAMLESS TUBULAR - ISSUE MR - IFC | 10 | 2022-03-07 | 2022-03-21 | 2022-07-06 | 2022-07-22 | 84
TBE |  |  | 53 | 2022-02-15 | 2022-04-29 | 2022-06-02 | 2022-09-02 | 85
0 | EDCMSR2030 | COMPLETE EVALUATION AND SUBMIT TBE - SEAMLESS TUBULAR - ICR | 12 | 2022-02-15 | 2022-03-03 | 2022-06-02 | 2022-06-17 | 74
0 | EDCMSR2035 | RECEIVE COMMENTS & ISSUE TBE - SEAMLESS TUBULAR - IFA | 10 | 2022-03-17 | 2022-03-31 | 2022-07-06 | 2022-07-22 | 76
0 | EDCMSR2040 | ISSUE TBE - SEAMLESS TUBULAR - IFC | 11 | 2022-04-14 | 2022-04-29 | 2022-08-19 | 2022-09-02 | 85
ROLLED SECTIONS |  |  | 70 | 2022-01-21 | 2022-04-29 | 2022-05-19 | 2022-09-22 | 99
REQUISITION |  |  | 42 | 2022-01-21 | 2022-03-22 | 2022-05-19 | 2022-08-02 | 90
0 | EDCMSR1045 | ROLLED SECTIONS - ISSUE MR - ICR | 5 | 2022-01-21 | 2022-01-28 | 2022-05-19 | 2022-05-25 | 81
0 | EDCMSR1050 | ROLLED SECTIONS - ISSUE MR - IFA | 10 | 2022-02-11 | 2022-02-25 | 2022-06-22 | 2022-07-05 | 90
0 | EDCMSR1055 | ROLLED SECTIONS - ISSUE MR - IFC | 10 | 2022-03-08 | 2022-03-22 | 2022-07-20 | 2022-08-02 | 90
TBE |  |  | 52 | 2022-02-16 | 2022-04-29 | 2022-06-14 | 2022-09-22 | 99
0 | EDCMSR2045 | COMPLETE EVALUATION AND SUBMIT TBE- ROLLED SECTIONS - ICR | 11 | 2022-02-16 | 2022-03-03 | 2022-06-14 | 2022-06-28 | 81
0 | EDCMSR2050 | RECEIVE COMMENTS & ISSUE TBE - ROLLED SECTIONS - IFA | 10 | 2022-03-17 | 2022-03-31 | 2022-07-20 | 2022-08-02 | 83
0 | EDCMSR2055 | ISSUE TBE - ROLLED SECTIONS - IFC | 11 | 2022-04-14 | 2022-04-29 | 2022-09-08 | 2022-09-22 | 99
C.S GRATING & STAIR TREADS |  |  | 85 | 2022-03-31 | 2022-08-05 | 2022-07-14 | 2022-11-25 | 81
REQUISITION |  |  | 42 | 2022-03-31 | 2022-06-02 | 2022-07-14 | 2022-10-14 | 94
0 | EDCMSR1060 | C.S. GRATINGS & STAIR TREADS - ISSUE MR - ICR | 5 | 2022-03-31 | 2022-04-07 | 2022-07-14 | 2022-07-20 | 69
0 | EDCMSR1065 | C.S. GRATINGS & STAIR TREADS - ISSUE MR - IFA | 10 | 2022-04-21 | 2022-05-10 | 2022-09-08 | 2022-09-21 | 94
0 | EDCMSR1070 | C.S. GRATINGS & STAIR TREADS - ISSUE MR - IFC | 10 | 2022-05-19 | 2022-06-02 | 2022-10-03 | 2022-10-14 | 94
TBE |  |  | 60 | 2022-05-10 | 2022-08-05 | 2022-08-18 | 2022-11-25 | 81
0 | EDCMSR2060 | COMPLETE EVALUATION AND SUBMIT TBE - CS GRATINGS & STAIR TREADS - ICR | 20 | 2022-05-10 | 2022-06-07 | 2022-08-18 | 2022-09-14 | 69
0 | EDCMSR2065 | RECEIVE COMMENTS & ISSUE TBE - CS GRATINGS & STAIR TREADS - IFA | 10 | 2022-06-21 | 2022-07-05 | 2022-10-03 | 2022-10-14 | 71
0 | EDCMSR2070 | ISSUE TBE - CS GRATINGS & STAIR TREADS - IFC | 10 | 2022-07-22 | 2022-08-05 | 2022-11-14 | 2022-11-25 | 81
CATHODIC PROTECTION [SACRIFICIAL ANODES] |  |  | 85 | 2022-04-07 | 2022-08-12 | 2022-07-26 | 2022-12-09 | 84
REQUISITION |  |  | 42 | 2022-04-07 | 2022-06-09 | 2022-07-26 | 2022-10-28 | 99
0 | EDCMSR1075 | CATHODIC PROTECTION [SACRIFICIAL ANODES] - ISSUE MR - ICR | 5 | 2022-04-07 | 2022-04-14 | 2022-07-26 | 2022-08-01 | 72
0 | EDCMSR1080 | CATHODIC PROTECTION [SACRIFICIAL ANODES] - ISSUE MR - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-09-22 | 2022-10-05 | 99
0 | EDCMSR1085 | CATHODIC PROTECTION [SACRIFICIAL ANODES] - ISSUE MR - IFC | 10 | 2022-05-26 | 2022-06-09 | 2022-10-17 | 2022-10-28 | 99
TBE |  |  | 60 | 2022-05-17 | 2022-08-12 | 2022-09-01 | 2022-12-09 | 84
0 | EDCMSR2075 | COMPLETE EVALUATION AND SUBMIT TBE - (SACRIFICIAL ANODES) - ICR | 20 | 2022-05-17 | 2022-06-14 | 2022-09-01 | 2022-09-28 | 74
0 | EDCMSR2080 | RECEIVE COMMENTS & ISSUE TBE - (SACRIFICIAL ANODES) - IFA | 10 | 2022-06-28 | 2022-07-15 | 2022-10-17 | 2022-10-28 | 76
0 | EDCMSR2085 | ISSUE TBE - (SACRIFICIAL ANODES) - IFC | 10 | 2022-07-29 | 2022-08-12 | 2022-11-24 | 2022-12-09 | 84
BOLTS, NUTS & WASHERS |  |  | 85 | 2022-04-14 | 2022-08-19 | 2022-08-02 | 2022-12-15 | 83
REQUISITION |  |  | 42 | 2022-04-14 | 2022-06-16 | 2022-08-02 | 2022-11-03 | 98
0 | EDCMSR1090 | BOLTS, NUTS & WASHERS - ISSUE MR - ICR | 5 | 2022-04-14 | 2022-04-21 | 2022-08-02 | 2022-08-08 | 72
0 | EDCMSR1095 | BOLTS, NUTS & WASHERS - ISSUE MR - IFA | 10 | 2022-05-10 | 2022-05-24 | 2022-09-28 | 2022-10-11 | 98
0 | EDCMSR1100 | BOLTS, NUTS & WASHERS - ISSUE MR - IFC | 10 | 2022-06-02 | 2022-06-16 | 2022-10-21 | 2022-11-03 | 98
TBE |  |  | 60 | 2022-05-24 | 2022-08-19 | 2022-09-07 | 2022-12-15 | 83
0 | EDCMSR2090 | COMPLETE EVALUATION AND SUBMIT TBE - BOLTS, NUTS & WASHERS - ICR | 20 | 2022-05-24 | 2022-06-21 | 2022-09-07 | 2022-10-04 | 73
0 | EDCMSR2095 | RECEIVE COMMENTS & ISSUE TBE - BOLTS, NUTS & WASHERS - IFA | 10 | 2022-07-05 | 2022-07-22 | 2022-10-21 | 2022-11-03 | 75
0 | EDCMSR2100 | ISSUE TBE - BOLTS, NUTS & WASHERS - IFC | 10 | 2022-08-05 | 2022-08-19 | 2022-11-30 | 2022-12-15 | 83
HELI DECK SAFETY NET |  |  | 86 | 2022-04-21 | 2022-08-29 | 2022-08-09 | 2023-01-04 | 91
REQUISITION |  |  | 42 | 2022-04-21 | 2022-06-23 | 2022-08-09 | 2022-11-23 | 107
0 | EDCMSR1105 | HELI DECK SAFETY NET - ISSUE MR - ICR | 5 | 2022-04-21 | 2022-04-28 | 2022-08-09 | 2022-08-15 | 72
0 | EDCMSR1110 | HELI DECK SAFETY NET - ISSUE MR - IFA | 10 | 2022-05-17 | 2022-05-31 | 2022-10-18 | 2022-10-31 | 107
0 | EDCMSR1115 | HELI DECK SAFETY NET - ISSUE MR - IFC | 10 | 2022-06-09 | 2022-06-23 | 2022-11-10 | 2022-11-23 | 107
TBE |  |  | 61 | 2022-05-31 | 2022-08-29 | 2022-09-27 | 2023-01-04 | 91
0 | EDCMSR2105 | COMPLETE EVALUATION AND SUBMIT TBE - HELIDECK SAFETY NET - ICR | 20 | 2022-05-31 | 2022-06-28 | 2022-09-27 | 2022-10-24 | 82
0 | EDCMSR2110 | RECEIVE COMMENTS & ISSUE TBE - HELIDECK SAFETY NET - IFA | 10 | 2022-07-15 | 2022-07-29 | 2022-11-10 | 2022-11-23 | 84
0 | EDCMSR2115 | ISSUE TBE - HELIDECK SAFETY NET - IFC | 11 | 2022-08-12 | 2022-08-29 | 2022-12-21 | 2023-01-04 | 91
MISC.STRUCTURAL ITEMS |  |  | 86 | 2022-04-28 | 2022-09-05 | 2022-08-16 | 2023-01-27 | 103
REQUISITION |  |  | 25 | 2022-04-28 | 2022-06-07 | 2022-08-16 | 2022-11-23 | 119
0 | EDCMSR1120 | MISC STRUCTURAL ITEMS - ISSUE MR - ICR | 5 | 2022-04-28 | 2022-05-10 | 2022-08-16 | 2022-08-22 | 72
0 | EDCMSR1125 | MISC STRUCTURAL ITEMS - ISSUE MR - IFA | 10 | 2022-05-10 | 2022-05-24 | 2022-10-27 | 2022-11-09 | 119
0 | EDCMSR1130 | MISC STRUCTURAL ITEMS - ISSUE MR - IFC | 10 | 2022-05-24 | 2022-06-07 | 2022-11-10 | 2022-11-23 | 119
TBE |  |  | 61 | 2022-06-07 | 2022-09-05 | 2022-10-18 | 2023-01-27 | 103
0 | EDCMSR2120 | COMPLETE EVALUATION AND SUBMIT TBE - MISCELLANEOUS STRUCTURAL ITEMS - ICR | 20 | 2022-06-07 | 2022-07-05 | 2022-10-18 | 2022-11-14 | 92
0 | EDCMSR2125 | RECEIVE COMMENTS & ISSUE TBE - MISCELLANEOUS STRUCTURAL ITEMS - IFA | 10 | 2022-07-22 | 2022-08-05 | 2022-12-05 | 2022-12-16 | 94
0 | EDCMSR2130 | ISSUE TBE - MISCELLANEOUS STRUCTURAL ITEMS - IFC | 11 | 2022-08-19 | 2022-09-05 | 2023-01-13 | 2023-01-27 | 103
GROUTING MATERIAL |  |  | 86 | 2022-05-10 | 2022-09-12 | 2022-08-23 | 2023-01-04 | 81
REQUISITION |  |  | 42 | 2022-05-10 | 2022-07-07 | 2022-08-23 | 2022-11-23 | 97
0 | EDCMSR1135 | GROUTING MATERIAL - ISSUE MR - ICR | 5 | 2022-05-10 | 2022-05-17 | 2022-08-23 | 2022-08-29 | 72
0 | EDCMSR1140 | GROUTING MATERIAL - ISSUE MR - IFA | 10 | 2022-05-31 | 2022-06-14 | 2022-10-18 | 2022-10-31 | 97
0 | EDCMSR1145 | GROUTING MATERIAL - ISSUE MR - IFC | 10 | 2022-06-23 | 2022-07-07 | 2022-11-10 | 2022-11-23 | 97
TBE |  |  | 61 | 2022-06-14 | 2022-09-12 | 2022-09-27 | 2023-01-04 | 81
0 | EDCMSR2135 | COMPLETE EVALUATION AND SUBMIT TBE- GROUTING MATERIAL - ICR | 20 | 2022-06-14 | 2022-07-15 | 2022-09-27 | 2022-10-24 | 72
0 | EDCMSR2140 | RECEIVE COMMENTS & ISSUE TBE- GROUTING MATERIAL - IFA | 10 | 2022-07-29 | 2022-08-12 | 2022-11-10 | 2022-11-23 | 74
0 | EDCMSR2145 | ISSUE TBE- GROUTING MATERIAL - IFC | 11 | 2022-08-26 | 2022-09-12 | 2022-12-21 | 2023-01-04 | 81
SWING ROPE ASSEMBLY |  |  | 81 | 2022-05-17 | 2022-09-12 | 2022-09-27 | 2023-04-07 | 148
REQUISITION |  |  | 42 | 2022-05-17 | 2022-07-19 | 2022-09-27 | 2022-11-23 | 92
0 | EDCMSR1150 | SWING ROPE ASSEMBLY - ISSUE MR - ICR | 5 | 2022-05-17 | 2022-05-24 | 2022-09-27 | 2022-10-03 | 92
0 | EDCMSR1155 | SWING ROPE ASSEMBLY - ISSUE MR - IFA | 10 | 2022-06-07 | 2022-06-21 | 2022-10-18 | 2022-10-31 | 92
0 | EDCMSR1160 | SWING ROPE ASSEMBLY - ISSUE MR - IFC | 10 | 2022-06-30 | 2022-07-19 | 2022-11-10 | 2022-11-23 | 92
TBE |  |  | 56 | 2022-06-21 | 2022-09-12 | 2022-11-11 | 2023-04-07 | 148
0 | EDCMSR2150 | COMPLETE EVALUATION AND SUBMIT TBE - SWING ROPE ASSEMBLY - ICR | 15 | 2022-06-21 | 2022-07-15 | 2022-11-11 | 2022-12-05 | 100
0 | EDCMSR2155 | RECEIVE COMMENTS & ISSUE TBE - SWING ROPE ASSEMBLY - IFA | 10 | 2022-07-29 | 2022-08-12 | 2022-12-22 | 2023-01-04 | 102
0 | EDCMSR2160 | ISSUE TBE - SWING ROPE ASSEMBLY - IFC | 11 | 2022-08-26 | 2022-09-12 | 2023-03-24 | 2023-04-07 | 148
NAVAL & ARCHITECTURE |  |  | 60 | 2022-02-18 | 2022-05-18 | 2022-05-24 | 2022-09-08 | 79
0 | EDCMNA2230 | WEIGHT CONTROL PROCEDURE- IRC | 15 | 2022-02-18 | 2022-03-11 | 2022-05-24 | 2022-06-13 | 64
0 | EDCMNA2260 | SUPPLIER WEIGHT CONTROL PROCEDURE IRC | 10 | 2022-03-04 | 2022-03-18 | 2022-06-28 | 2022-07-14 | 79
0 | EDCMNA2240 | WEIGHT CONTROL PROCEDURE - IFA | 10 | 2022-03-25 | 2022-04-08 | 2022-06-28 | 2022-07-14 | 64
0 | EDCMNA2270 | SUPPLIER WEIGHT CONTROL PROCEDURE - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-07-29 | 2022-08-11 | 79
0 | EDCMNA2250 | WEIGHT CONTROL PROCEDURE - IFC | 10 | 2022-04-22 | 2022-05-11 | 2022-07-29 | 2022-08-11 | 64
0 | EDCMNA2280 | SUPPLIER WEIGHT CONTROL PROCEDURE - IFC | 10 | 2022-04-29 | 2022-05-18 | 2022-08-26 | 2022-09-08 | 79
BU HASEER WHP BH-03 TOPSIDES |  |  | 367 | 2022-01-17 | 2023-01-19 | 2022-03-24 | 2023-06-16 | 149
PROCESS |  |  | 253 | 2022-01-17 | 2023-01-17 | 2022-03-24 | 2023-04-27 | 71
DOCUMENTS |  |  | 85 | 2022-03-08 | 2022-07-13 | 2022-05-12 | 2023-01-23 | 137
PROCESS SIMULATIONS & REPORTS |  |  | 61 | 2022-03-15 | 2022-06-13 | 2022-06-20 | 2022-11-08 | 104
0 | EDBDPR1000 | ALARM AND TRIP SCHEDULE (BU HASEER BH-03 WHP) - ICR | 11 | 2022-03-15 | 2022-03-30 | 2022-06-20 | 2022-07-04 | 66
0 | EDBDPR1005 | ALARM AND TRIP SCHEDULE (BU HASEER BH-03 WHP) - IFA | 15 | 2022-04-13 | 2022-05-09 | 2022-08-08 | 2022-08-26 | 77
0 | EDBDPR1010 | ALARM AND TRIP SCHEDULE (BU HASEER BH-03 WHP) - IFC | 15 | 2022-05-23 | 2022-06-13 | 2022-10-19 | 2022-11-08 | 104
PROCESS LISTS |  |  | 65 | 2022-03-08 | 2022-06-10 | 2022-06-02 | 2022-11-21 | 114
0 | EDBDPR1015 | EQUIPMENT LIST (BU HASEER BH-03 WHP) - ICR | 10 | 2022-03-08 | 2022-03-22 | 2022-06-02 | 2022-06-15 | 59
0 | EDBDPR1030 | LINE LIST (BU HASEER BH-03 WHP) - ICR | 10 | 2022-03-15 | 2022-03-29 | 2022-06-27 | 2022-07-13 | 71
0 | EDBDPR1020 | EQUIPMENT LIST (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-06-30 | 2022-07-18 | 59
0 | EDBDPR1035 | LINE LIST (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-08-25 | 2022-09-07 | 91
0 | EDBDPR1025 | EQUIPMENT LIST (BU HASEER BH-03 WHP) - IFC | 19 | 2022-05-06 | 2022-06-02 | 2022-10-26 | 2022-11-21 | 120
0 | EDBDPR1040 | LINE LIST (BU HASEER BH-03 WHP) - IFC | 20 | 2022-05-13 | 2022-06-10 | 2022-09-22 | 2022-10-19 | 91
PREPARATION OF DATASHEETS |  |  | 85 | 2022-03-08 | 2022-07-13 | 2022-05-12 | 2023-01-23 | 137
0 | EDBDPR1270 | PROCESS DATA SHEET PIG LAUNCHER (BU HASEER BH-03 WHP) - ICR | 5 | 2022-03-08 | 2022-03-15 | 2022-05-13 | 2022-05-19 | 45
0 | EDBDPR1240 | PROCESS DATA SHEET DRAIN DRUM PUMP (BU HASEER BH-03 WHP) - ICR | 6 | 2022-03-10 | 2022-03-18 | 2022-05-12 | 2022-05-19 | 42
0 | EDBDPR1045 | PROCESS DATA SHEET CHOKE VALVES (BU HASEER BH-03 WHP) - ICR | 5 | 2022-03-15 | 2022-03-22 | 2022-05-18 | 2022-05-24 | 43
0 | EDBDPR1075 | PROCESS DATA SHEET MOTOR OPERATED VALVES (BU HASEER BH-03 WHP) - ICR | 5 | 2022-03-15 | 2022-03-22 | 2022-05-19 | 2022-05-25 | 44
0 | EDBDPR1255 | PROCESS DATA SHEET VENT / DRAIN DRUM (BU HASEER BH-03 WHP) - ICR | 5 | 2022-03-16 | 2022-03-23 | 2022-06-07 | 2022-06-13 | 56
0 | EDBDPR1090 | PROCESS DATASHEET SHUTDOWN VALVES (BU HASEER BH-03 WHP) - ICR | 5 | 2022-03-17 | 2022-03-24 | 2022-05-23 | 2022-05-27 | 44
0 | EDBDPR1120 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (BU HASEER BH-03 WHP) - ICR | 5 | 2022-03-21 | 2022-03-28 | 2022-06-10 | 2022-06-16 | 56
0 | EDBDPR1105 | PROCESS DATASHEET IRCD (BU HASEER BH-03 WHP) - ICR | 5 | 2022-03-21 | 2022-03-28 | 2022-05-26 | 2022-06-01 | 45
0 | EDBDPR1135 | PROCESS DATASHEET PRESSURE GAUGES (BU HASEER BH-03 WHP) - ICR | 5 | 2022-03-23 | 2022-03-30 | 2022-07-01 | 2022-07-07 | 69
0 | EDBDPR1060 | PROCESS DATA SHEET WET GAS METER (BU HASEER BH-03 WHP) - MULTI PHASE FLOW METER - ICR | 5 | 2022-03-25 | 2022-04-01 | 2022-05-30 | 2022-06-03 | 43
0 | EDBDPR1150 | PROCESS DATASHEET PRESSURE INSTRUMENT (BU HASEER BH-03 WHP) - ICR | 5 | 2022-03-28 | 2022-04-04 | 2022-07-01 | 2022-07-07 | 66
0 | EDBDPR1180 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (BU HASEER BH-03 WHP) - ICR | 7 | 2022-03-30 | 2022-04-08 | 2022-07-05 | 2022-07-18 | 66
0 | EDBDPR1165 | PROCESS DATASHEET TEMPERATURE GAUGE (BU HASEER BH-03 WHP) - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-07-01 | 2022-07-19 | 66
0 | EDBDPR1195 | PROCESS DATASHEET LEVEL GAUGE (BU HASEER BH-03 WHP) - ICR | 7 | 2022-04-01 | 2022-04-12 | 2022-07-07 | 2022-07-20 | 66
0 | EDBDPR1275 | PROCESS DATA SHEET PIG LAUNCHER (BU HASEER BH-03 WHP) - IFA | 10 | 2022-03-29 | 2022-04-12 | 2022-07-21 | 2022-08-03 | 76
0 | EDBDPR1210 | PROCESS DATASHEET LEVEL INSTRUMENT (BU HASEER BH-03 WHP) - ICR | 7 | 2022-04-05 | 2022-04-14 | 2022-07-14 | 2022-07-22 | 66
0 | EDBDPR1245 | PROCESS DATA SHEET DRAIN DRUM PUMP (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-06-07 | 2022-06-20 | 44
0 | EDBDPR1050 | PROCESS DATA SHEET CHOKE VALVES (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-06-22 | 2022-07-05 | 53
0 | EDBDPR1080 | PROCESS DATA SHEET MOTOR OPERATED VALVES (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-07-07 | 2022-07-25 | 64
0 | EDBDPR1260 | PROCESS DATA SHEET VENT / DRAIN DRUM (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-08-15 | 2022-08-26 | 87
0 | EDBDPR1225 | PROCESS DATASHEET FLOW SWITCH (BU HASEER BH-03 WHP) - ICR | 10 | 2022-04-07 | 2022-04-21 | 2022-07-18 | 2022-07-29 | 66
0 | EDBDPR1095 | PROCESS DATASHEET SHUTDOWN VALVES (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-07 | 2022-04-21 | 2022-07-06 | 2022-07-22 | 61
0 | EDBDPR1125 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-11 | 2022-04-25 | 2022-08-15 | 2022-08-26 | 84
0 | EDBDPR1110 | PROCESS DATASHEET IRCD (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-11 | 2022-04-25 | 2022-06-27 | 2022-07-13 | 52
0 | EDBDPR1285 | PROCESS DATA SHEET RESTRICTION ORIFICES (BU HASEER BH-03 WHP) - ICR | 11 | 2022-04-11 | 2022-04-26 | 2022-07-15 | 2022-07-29 | 63
0 | EDBDPR1140 | PROCESS DATASHEET PRESSURE GAUGES (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-13 | 2022-04-27 | 2022-08-15 | 2022-08-26 | 82
0 | EDBDPR1065 | PROCESS DATA SHEET WET GAS METER (BU HASEER BH-03 WHP) - MULTI PHASE FLOW METER - IFA | 10 | 2022-04-15 | 2022-04-29 | 2022-07-06 | 2022-07-22 | 55
0 | EDBDPR1155 | PROCESS DATASHEET PRESSURE INSTRUMENT (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-18 | 2022-05-05 | 2022-08-15 | 2022-08-26 | 79
0 | EDBDPR1185 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-22 | 2022-05-11 | 2022-08-15 | 2022-08-26 | 75
0 | EDBDPR1170 | PROCESS DATASHEET TEMPERATURE GAUGE (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-08-15 | 2022-08-26 | 74
0 | EDBDPR1200 | PROCESS DATASHEET LEVEL GAUGE (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-08-15 | 2022-08-26 | 73
0 | EDBDPR1215 | PROCESS DATASHEET LEVEL INSTRUMENT (BU HASEER BH-03 WHP) - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-08-15 | 2022-08-26 | 71
0 | EDBDPR1250 | PROCESS DATA SHEET DRAIN DRUM PUMP (BU HASEER BH-03 WHP) - IFC | 10 | 2022-04-29 | 2022-05-18 | 2022-07-05 | 2022-07-21 | 44
0 | EDBDPR1265 | PROCESS DATA SHEET VENT / DRAIN DRUM (BU HASEER BH-03 WHP) - IFC | 10 | 2022-05-09 | 2022-05-23 | 2022-11-03 | 2022-11-16 | 125
0 | EDBDPR1230 | PROCESS DATASHEET FLOW SWITCH (BU HASEER BH-03 WHP) - IFA | 10 | 2022-05-10 | 2022-05-24 | 2022-08-15 | 2022-08-26 | 66
0 | EDBDPR1085 | PROCESS DATA SHEET MOTOR OPERATED VALVES (BU HASEER BH-03 WHP) - IFC | 15 | 2022-05-06 | 2022-05-27 | 2022-08-09 | 2022-08-29 | 64
0 | EDBDPR1280 | PROCESS DATA SHEET PIG LAUNCHER (BU HASEER BH-03 WHP) - IFC | 20 | 2022-04-26 | 2022-05-27 | 2022-08-18 | 2022-09-14 | 76
0 | EDBDPR1290 | PROCESS DATA SHEET RESTRICTION ORIFICES (BU HASEER BH-03 WHP) - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-08-15 | 2022-08-26 | 63
0 | EDBDPR1055 | PROCESS DATA SHEET CHOKE VALVES (BU HASEER BH-03 WHP) - IFC | 20 | 2022-05-06 | 2022-06-03 | 2022-07-25 | 2022-08-19 | 53
0 | EDBDPR1100 | PROCESS DATASHEET SHUTDOWN VALVES (BU HASEER BH-03 WHP) - IFC | 20 | 2022-05-10 | 2022-06-07 | 2022-08-08 | 2022-09-02 | 61
0 | EDBDPR1130 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (BU HASEER BH-03 WHP) - IFC | 20 | 2022-05-12 | 2022-06-09 | 2022-10-27 | 2022-11-23 | 117
0 | EDBDPR1115 | PROCESS DATASHEET IRCD (BU HASEER BH-03 WHP) - IFC | 20 | 2022-05-12 | 2022-06-09 | 2022-07-28 | 2022-08-24 | 52
0 | EDBDPR1070 | PROCESS DATA SHEET WET GAS METER (BU HASEER BH-03 WHP) - MULTI PHASE FLOW METER - IFC | 20 | 2022-05-18 | 2022-06-15 | 2022-08-08 | 2022-09-02 | 55
0 | EDBDPR1160 | PROCESS DATASHEET PRESSURE INSTRUMENT (BU HASEER BH-03 WHP) - IFC | 20 | 2022-05-19 | 2022-06-16 | 2022-10-31 | 2022-11-25 | 114
0 | EDBDPR1145 | PROCESS DATASHEET PRESSURE GAUGES (BU HASEER BH-03 WHP) - IFC | 20 | 2022-05-19 | 2022-06-16 | 2022-11-02 | 2022-11-29 | 116
0 | EDBDPR1190 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (BU HASEER BH-03 WHP) - IFC | 20 | 2022-05-25 | 2022-06-22 | 2022-11-01 | 2022-11-28 | 111
0 | EDBDPR1175 | PROCESS DATASHEET TEMPERATURE GAUGE (BU HASEER BH-03 WHP) - IFC | 19 | 2022-05-26 | 2022-06-22 | 2022-10-31 | 2022-11-24 | 109
0 | EDBDPR1205 | PROCESS DATASHEET LEVEL GAUGE (BU HASEER BH-03 WHP) - IFC | 19 | 2022-05-27 | 2022-06-23 | 2022-10-18 | 2022-11-11 | 99
0 | EDBDPR1220 | PROCESS DATASHEET LEVEL INSTRUMENT (BU HASEER BH-03 WHP) - IFC | 20 | 2022-05-31 | 2022-06-28 | 2022-12-15 | 2023-01-11 | 137
0 | EDBDPR1235 | PROCESS DATASHEET FLOW SWITCH (BU HASEER BH-03 WHP) - IFC | 20 | 2022-06-07 | 2022-07-05 | 2022-12-27 | 2023-01-23 | 140
0 | EDBDPR1295 | PROCESS DATA SHEET RESTRICTION ORIFICES (BU HASEER BH-03 WHP) - IFC | 20 | 2022-06-10 | 2022-07-13 | 2022-10-24 | 2022-11-18 | 93
DRAWINGS |  |  | 193 | 2022-01-17 | 2022-10-21 | 2022-03-24 | 2022-12-28 | 47
PFD / UFD / DPDT / PSFS & HMB |  |  | 77 | 2022-01-17 | 2022-05-09 | 2022-03-24 | 2022-10-19 | 115
0 | EDBGPR1030 | HEAT AND MATERIAL BALANCE - BU HASEER BH-03 WHP - ICR | 13 | 2022-01-17 | 2022-02-03 | 2022-04-04 | 2022-04-20 | 55
0 | EDBGPR1015 | UFD's - BU HASEER BH-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - ICR | 13 | 2022-01-17 | 2022-02-03 | 2022-07-25 | 2022-08-10 | 129
0 | EDBGPR1000 | PFD's - BU HASEER BH-03 WHP TEST AND PRODUCTION MANIFOLD - ICR | 10 | 2022-01-24 | 2022-02-07 | 2022-03-24 | 2022-04-06 | 43
0 | EDBGPR1045 | DPDT DIAGRAMS - BU HASEER BH-03 WHP - TEST AND PRODUCTION MANIFOLD - ICR | 15 | 2022-01-31 | 2022-02-21 | 2022-04-12 | 2022-05-05 | 51
0 | EDBGPR1060 | DPDT DIAGRAMS - BU HASEER BH-03 WHP VENT AND DRAIN UTILITIES SUPPLY - ICR | 20 | 2022-01-26 | 2022-02-23 | 2022-07-15 | 2022-08-11 | 116
0 | EDBGPR1075 | PSFS's - BU HASEER BH-03 WHP - TEST AND PRODUCTION MANIFOLD - ICR | 10 | 2022-02-09 | 2022-02-23 | 2022-04-21 | 2022-05-09 | 51
0 | EDBGPR1090 | PSFS's - BU HASEER BH-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - ICR | 20 | 2022-01-26 | 2022-02-23 | 2022-04-07 | 2022-05-09 | 51
0 | EDBGPR1035 | HEAT AND MATERIAL BALANCE - BU HASEER BH-03 WHP - IFA | 14 | 2022-02-17 | 2022-03-09 | 2022-06-15 | 2022-07-04 | 81
0 | EDBGPR1005 | PFD's - BU HASEER BH-03 WHP TEST AND PRODUCTION MANIFOLD - IFA | 14 | 2022-02-21 | 2022-03-11 | 2022-06-23 | 2022-07-15 | 85
0 | EDBGPR1020 | UFD's - BU HASEER BH-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFA | 20 | 2022-02-17 | 2022-03-17 | 2022-08-25 | 2022-09-21 | 129
0 | EDBGPR1050 | DPDT DIAGRAMS - BU HASEER BH-03 WHP - TEST AND PRODUCTION MANIFOLD - IFA | 9 | 2022-03-07 | 2022-03-18 | 2022-08-26 | 2022-09-07 | 118
0 | EDBGPR1065 | DPDT DIAGRAMS - BU HASEER BH-03 WHP VENT AND DRAIN UTILITIES SUPPLY - IFA | 9 | 2022-03-09 | 2022-03-22 | 2022-08-26 | 2022-09-07 | 116
0 | EDBGPR1080 | PSFS's - BU HASEER BH-03 WHP - TEST AND PRODUCTION MANIFOLD - IFA | 9 | 2022-03-09 | 2022-03-22 | 2022-08-26 | 2022-09-07 | 116
0 | EDBGPR1095 | PSFS's - BU HASEER BH-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFA | 9 | 2022-03-09 | 2022-03-22 | 2022-08-26 | 2022-09-07 | 116
0 | EDBGPR1025 | UFD's - BU HASEER BH-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFC | 10 | 2022-03-31 | 2022-04-14 | 2022-10-06 | 2022-10-19 | 129
0 | EDBGPR1040 | HEAT AND MATERIAL BALANCE - BU HASEER BH-03 WHP - IFC | 20 | 2022-03-23 | 2022-04-20 | 2022-08-01 | 2022-08-26 | 87
0 | EDBGPR1010 | PFD's - BU HASEER BH-03 WHP TEST AND PRODUCTION MANIFOLD - IFC | 20 | 2022-03-25 | 2022-04-22 | 2022-08-01 | 2022-08-26 | 85
0 | EDBGPR1055 | DPDT DIAGRAMS - BU HASEER BH-03 WHP - TEST AND PRODUCTION MANIFOLD - IFC | 20 | 2022-04-05 | 2022-05-06 | 2022-09-22 | 2022-10-19 | 116
0 | EDBGPR1070 | DPDT DIAGRAMS - BU HASEER BH-03 WHP VENT AND DRAIN UTILITIES SUPPLY - IFC | 20 | 2022-04-05 | 2022-05-06 | 2022-09-22 | 2022-10-19 | 116
0 | EDBGPR1085 | PSFS's - BU HASEER BH-03 WHP - TEST AND PRODUCTION MANIFOLD - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-09-22 | 2022-10-19 | 115
0 | EDBGPR1100 | PSFS's - BU HASEER BH-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-09-22 | 2022-10-19 | 115
PIPING & INSTRUMENTATION DIAGRAMS |  |  | 176 | 2022-02-09 | 2022-10-21 | 2022-04-21 | 2022-12-28 | 47
0 | EDBGPR1105 | P&ID - DRAWING INDEX BU HASEER BH-03 WHP - ICR | 15 | 2022-02-09 | 2022-03-02 | 2022-04-21 | 2022-05-16 | 51
0 | EDBGPR1120 | P&IDs - BU HASEER BH-03 WHP - ICR | 15 | 2022-02-22 | 2022-03-15 | 2022-04-21 | 2022-05-16 | 42
0 | EDBGPR1125 | P&IDs - BU HASEER BH-03 WHP - ISSUED FOR HAZOP | 28 | 2022-04-04 | 2022-05-17 | 2022-06-24 | 2022-08-05 | 55
0 | EDBGPR1130 | P&IDs - BU HASEER BH-03 WHP - IFA | 25 | 2022-06-16 | 2022-07-26 | 2022-09-02 | 2022-10-06 | 53
0 | EDBGPR1110 | P&ID - DRAWING INDEX BU HASEER BH-03 WHP - IFA | 25 | 2022-06-16 | 2022-07-26 | 2022-09-27 | 2022-10-31 | 70
0 | EDBGPR1135 | P&IDs - BU HASEER BH-03 WHP - IFC | 25 | 2022-09-16 | 2022-10-21 | 2022-11-22 | 2022-12-28 | 47
0 | EDBGPR1115 | P&ID - DRAWING INDEX BU HASEER BH-03 WHP - IFC | 30 | 2022-09-09 | 2022-10-21 | 2022-11-15 | 2022-12-28 | 47
CAUSE & EFFECT & SAFE CHARTS |  |  | 83 | 2022-03-15 | 2022-07-18 | 2022-06-29 | 2022-12-19 | 109
0 | EDBGPR1140 | CAUSE & EFFECT CHARTS - BU HASEER BH-03 WHP - ICR | 20 | 2022-03-15 | 2022-04-12 | 2022-06-29 | 2022-07-29 | 73
0 | EDBGPR1155 | SAFE CHART - BU HASEER BH-03 WHP - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-08-29 | 2022-09-09 | 93
0 | EDBGPR1145 | CAUSE & EFFECT CHARTS - BU HASEER BH-03 WHP - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-08-15 | 2022-08-26 | 73
0 | EDBGPR1160 | SAFE CHART - BU HASEER BH-03 WHP - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-09-22 | 2022-10-05 | 93
0 | EDBGPR1165 | SAFE CHART - BU HASEER BH-03 WHP - IFC | 25 | 2022-06-06 | 2022-07-14 | 2022-10-18 | 2022-11-21 | 93
0 | EDBGPR1150 | CAUSE & EFFECT CHARTS - BU HASEER BH-03 WHP - IFC | 35 | 2022-05-25 | 2022-07-18 | 2022-10-28 | 2022-12-19 | 109
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-23 | 2023-01-17 | 2023-01-04 | 2023-04-27 | 71
0 | EDBGPR2000 | BH-03 PROCESS MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-23 | 2022-10-21 | 2023-01-04 | 2023-01-31 | 71
0 | EDBGPR2005 | BH-03 PROCESS MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-04 | 2022-12-06 | 2023-02-15 | 2023-03-14 | 71
0 | EDBGPR2010 | BH-03 PROCESS MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-20 | 2023-01-17 | 2023-03-29 | 2023-04-27 | 71
MATERIAL & CORROSION |  |  | 238 | 2022-02-07 | 2023-01-17 | 2022-04-21 | 2023-04-27 | 71
DOCUMENTS |  |  | 68 | 2022-08-22 | 2022-11-24 | 2022-11-09 | 2023-02-14 | 57
0 | EDBDMA1000 | BH-03 DEAD-LEG REGISTER - ICR | 15 | 2022-08-22 | 2022-09-12 | 2022-11-09 | 2022-11-29 | 57
0 | EDBDMA1010 | BH-03 DEAD-LEG REGISTER - IFA | 15 | 2022-09-26 | 2022-10-17 | 2022-12-16 | 2023-01-05 | 57
0 | EDBDMA1020 | BH-03 DEAD-LEG REGISTER - IFC | 20 | 2022-10-27 | 2022-11-24 | 2023-01-18 | 2023-02-14 | 57
DRAWINGS |  |  | 72 | 2022-02-07 | 2022-05-23 | 2022-04-21 | 2022-09-08 | 76
0 | EDBGMA1000 | MATERIAL SELECTION DIAGRAMS - BU HASEER BH-03 WHP - ICR | 12 | 2022-02-07 | 2022-02-23 | 2022-04-21 | 2022-05-11 | 53
0 | EDBGMA1005 | MATERIAL SELECTION DIAGRAMS - BU HASEER BH-03 WHP - IFA | 15 | 2022-03-09 | 2022-03-30 | 2022-06-28 | 2022-07-21 | 76
0 | EDBGMA1010 | MATERIAL SELECTION DIAGRAMS - BU HASEER BH-03 WHP - IFC | 25 | 2022-04-13 | 2022-05-23 | 2022-08-05 | 2022-09-08 | 76
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-23 | 2023-01-17 | 2023-01-04 | 2023-04-27 | 71
0 | EDBGMA2000 | BH-03 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-23 | 2022-10-21 | 2023-01-04 | 2023-01-31 | 71
0 | EDBGMA2005 | BH-03 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-04 | 2022-12-06 | 2023-02-15 | 2023-03-14 | 71
0 | EDBGMA2010 | BH-03 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-20 | 2023-01-17 | 2023-03-29 | 2023-04-27 | 71
SAFETY |  |  | 329 | 2022-02-22 | 2023-01-17 | 2022-06-08 | 2023-04-27 | 101
DRAWINGS |  |  | 240 | 2022-02-22 | 2022-10-20 | 2022-06-08 | 2023-04-18 | 181
0 | EDBGSA1000 | P&ID FIREWATER DRY SYSTEM - BU HASEER BH-03 - ICR | 15 | 2022-02-22 | 2022-03-15 | 2022-06-08 | 2022-06-28 | 73
0 | EDBGSA1005 | P&ID FIREWATER DRY SYSTEM - BU HASEER BH-03 - ISSUED FOR HAZOP | 15 | 2022-04-17 | 2022-05-08 | 2022-07-18 | 2022-08-07 | 66
0 | EDBGSA1015 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - BU HASEER BH - 03 - ICR | 10 | 2022-05-16 | 2022-05-30 | 2022-08-23 | 2022-09-05 | 68
0 | EDBGSA1030 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - BU HASEER WHP 3 - ICR | 10 | 2022-06-10 | 2022-06-24 | 2022-09-27 | 2022-10-10 | 74
0 | EDBGSA1007 | P&ID FIREWATER DRY SYSTEM - BU HASEER BH-03 - IFA | 15 | 2022-06-09 | 2022-06-30 | 2022-08-25 | 2022-09-14 | 55
0 | EDBGSA1060 | FIRE AND GAS CAUSE & EFFECT CHART – BU HASEER - WHP 03 - ICR | 15 | 2022-06-10 | 2022-07-01 | 2022-09-27 | 2022-10-17 | 74
0 | EDBGSA1020 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - BU HASEER BH - 03 - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-10-25 | 2022-11-07 | 91
0 | EDBGSA1035 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - BU HASEER WHP 3 - IFA | 10 | 2022-07-13 | 2022-07-27 | 2022-12-14 | 2022-12-27 | 110
0 | EDBGSA1065 | FIRE AND GAS CAUSE & EFFECT CHART – BU HASEER - WHP 03 - IFA | 10 | 2022-07-20 | 2022-08-03 | 2022-11-01 | 2022-11-14 | 74
0 | EDBGSA1010 | P&ID FIREWATER DRY SYSTEM - BU HASEER BH-03 - IFC | 15 | 2022-07-14 | 2022-08-04 | 2022-09-29 | 2022-10-19 | 55
0 | EDBGSA1045 | H2S ZONE LAYOUT - BU HASEER BH-03 - ICR | 15 | 2022-07-20 | 2022-08-10 | 2023-02-01 | 2023-02-21 | 138
0 | EDBGSA1075 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - BU HASEER BH-03 - ICR | 15 | 2022-07-20 | 2022-08-10 | 2022-12-27 | 2023-01-16 | 112
0 | EDBGSA1025 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - BU HASEER BH - 03 - IFC | 15 | 2022-08-11 | 2022-09-01 | 2023-01-04 | 2023-01-24 | 102
0 | EDBGSA1040 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - BU HASEER WHP 3 - IFC | 10 | 2022-08-24 | 2022-09-07 | 2023-01-11 | 2023-01-24 | 98
0 | EDBGSA1050 | H2S ZONE LAYOUT - BU HASEER BH-03 - IFA | 10 | 2022-08-24 | 2022-09-07 | 2023-03-08 | 2023-03-21 | 140
0 | EDBGSA1080 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - BU HASEER BH-03 - IFA | 15 | 2022-08-24 | 2022-09-14 | 2023-01-31 | 2023-02-20 | 114
0 | EDBGSA1070 | FIRE AND GAS CAUSE & EFFECT CHART – BU HASEER - WHP 03 - IFC | 10 | 2022-09-07 | 2022-09-21 | 2022-11-29 | 2022-12-14 | 59
0 | EDBGSA1055 | H2S ZONE LAYOUT - BU HASEER BH-03 - IFC | 10 | 2022-09-21 | 2022-10-05 | 2023-04-05 | 2023-04-18 | 138
0 | EDBGSA1085 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - BU HASEER BH-03 - IFC | 16 | 2022-09-28 | 2022-10-20 | 2023-03-07 | 2023-03-28 | 112
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-23 | 2023-01-17 | 2023-01-04 | 2023-04-27 | 71
0 | EDBGSA2000 | BH-03 SAFETY MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-23 | 2022-10-21 | 2023-01-04 | 2023-01-31 | 71
0 | EDBGSA2005 | BH-03 SAFETY MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-04 | 2022-12-06 | 2023-02-15 | 2023-03-14 | 71
0 | EDBGSA2010 | BH-03 SAFETY MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-20 | 2023-01-17 | 2023-03-29 | 2023-04-27 | 71
PIPING |  |  | 216 | 2022-03-11 | 2023-01-19 | 2022-05-25 | 2023-06-16 | 105
3D MODEL DEVELOPMENT |  |  | 200 | 2022-04-04 | 2023-01-19 | 2022-06-27 | 2023-04-07 | 57
0 | EDBDPI3000 | BH-03 3D MODEL DEVELOPMENT - PIPING | 200 | 2022-04-04 | 2023-01-19 | 2022-06-27 | 2023-04-07 | 57
3D MODELING |  |  | 166 | 2022-05-25 | 2023-01-19 | 2022-08-11 | 2023-04-07 | 57
30% MODEL REVIEW/REPORT |  |  | 50 | 2022-05-25 | 2022-08-08 | 2022-08-11 | 2022-10-28 | 60
0 | EDBDPI3100 | BH-03 30% 3D MODEL REVIEW REPORT - ICR | 10 | 2022-05-25 | 2022-06-08 | 2022-08-11 | 2022-08-24 | 53
0 | EDBDPI3105 | BH-03 30% 3D MODEL REVIEW REPORT - IFA | 10 | 2022-06-22 | 2022-07-06 | 2022-09-08 | 2022-09-21 | 53
0 | EDBDPI3110 | BH-03 30% 3D MODEL REVIEW REPORT - IFC | 10 | 2022-07-25 | 2022-08-08 | 2022-10-17 | 2022-10-28 | 60
60% MODEL REVIEW/REPORT |  |  | 60 | 2022-08-26 | 2022-11-18 | 2022-10-31 | 2023-01-24 | 46
0 | EDBDPI3120 | BH-03 60% 3D MODEL REVIEW REPORT - ICR | 10 | 2022-08-26 | 2022-09-09 | 2022-10-31 | 2022-11-11 | 46
0 | EDBDPI3125 | BH-03 60% 3D MODEL REVIEW REPORT - IFA | 10 | 2022-09-23 | 2022-10-07 | 2022-11-28 | 2022-12-13 | 46
0 | EDBDPI3130 | BH-03 60% 3D MODEL REVIEW REPORT - IFC | 20 | 2022-10-21 | 2022-11-18 | 2022-12-28 | 2023-01-24 | 46
90% MODEL REVIEW/REPORT |  |  | 41 | 2022-11-21 | 2023-01-19 | 2023-02-16 | 2023-04-07 | 57
0 | EDBDPI3140 | BH-03 90% 3D MODEL REVIEW REPORT - ICR | 7 | 2022-11-21 | 2022-11-30 | 2023-02-16 | 2023-02-24 | 61
0 | EDBDPI3145 | BH-03 90% 3D MODEL REVIEW REPORT - IFA | 7 | 2022-12-21 | 2022-12-30 | 2023-03-13 | 2023-03-21 | 58
0 | EDBDPI3150 | BH-03 90% 3D MODEL REVIEW REPORT - IFC | 3 | 2023-01-16 | 2023-01-19 | 2023-04-05 | 2023-04-07 | 57
DOCUMENTS |  |  | 203 | 2022-03-29 | 2023-01-18 | 2022-07-14 | 2023-06-16 | 106
REPORTS & CALCULATIONS |  |  | 203 | 2022-03-29 | 2023-01-18 | 2022-07-14 | 2023-06-16 | 106
0 | EDBDPI1000 | BH-03 PIPE STRESS CRITICAL LINE LIST - ICR | 15 | 2022-03-29 | 2022-04-19 | 2022-07-14 | 2022-08-03 | 71
0 | EDBDPI1005 | BH-03 PIPE STRESS CRITICAL LINE LIST - IFA | 15 | 2022-05-06 | 2022-05-27 | 2022-08-18 | 2022-09-07 | 71
0 | EDBDPI1015 | BH-03 PIPING STRESS ANALYSIS REPORT - ICR | 15 | 2022-05-19 | 2022-06-09 | 2022-12-20 | 2023-01-09 | 148
0 | EDBDPI1010 | BH-03 PIPE STRESS CRITICAL LINE LIST - IFC | 20 | 2022-06-10 | 2022-07-13 | 2022-09-22 | 2022-10-19 | 71
0 | EDBDPI1030 | BH-03 MECHANICAL HANDLING STUDY REPORT - ICR | 10 | 2022-07-06 | 2022-07-25 | 2022-09-22 | 2022-10-05 | 53
0 | EDBDPI1035 | BH-03 MECHANICAL HANDLING STUDY REPORT - IFA | 10 | 2022-08-26 | 2022-09-09 | 2023-01-25 | 2023-02-07 | 106
0 | EDBDPI1020 | BH-03 PIPING STRESS ANALYSIS REPORT - IFA | 15 | 2022-08-22 | 2022-09-12 | 2023-01-10 | 2023-01-30 | 99
0 | EDBDPI1040 | BH-03 MECHANICAL HANDLING STUDY REPORT - IFC | 10 | 2022-11-21 | 2022-12-07 | 2023-03-01 | 2023-03-14 | 70
0 | EDBDPI1025 | BH-03 PIPING STRESS ANALYSIS REPORT - IFC | 20 | 2022-11-21 | 2022-12-21 | 2023-02-10 | 2023-03-09 | 57
0 | EDBDPI1050 | BH-03 PIPE SUPPORT SCHEDULE - IFI | 10 | 2022-12-07 | 2022-12-21 | 2023-05-08 | 2023-05-19 | 106
0 | EDBDPI1060 | BH-03 PIPE SUPPORT SCHEDULE - IFC | 10 | 2023-01-04 | 2023-01-18 | 2023-06-05 | 2023-06-16 | 106
DRAWINGS |  |  | 216 | 2022-03-11 | 2023-01-19 | 2022-05-25 | 2023-04-27 | 69
0 | EDBGPI1000 | BU HASEER WELLHEAD PLATFORM BH-03 PLOT PLAN DRAWINGS - ICR | 30 | 2022-03-11 | 2022-04-22 | 2022-05-25 | 2022-07-05 | 50
0 | EDBGPI1005 | BU HASEER WELLHEAD PLATFORM BH-03 PLOT PLAN DRAWINGS - IFA | 19 | 2022-05-11 | 2022-06-07 | 2022-08-02 | 2022-08-26 | 56
0 | EDBGPI1035 | BH-03 SPECIAL SUPPORT DRAWINGS - ICR | 10 | 2022-11-21 | 2022-12-07 | 2023-02-15 | 2023-02-28 | 60
0 | EDBGPI1010 | BU HASEER WELLHEAD PLATFORM BH-03 PLOT PLAN DRAWINGS - IFC | 15 | 2022-11-21 | 2022-12-14 | 2023-03-29 | 2023-04-18 | 90
0 | EDBGPI1015 | BU HASEER WELLHEAD PLATFORM BH-03 ENGINEERING ISOMETRICS | 18 | 2022-11-21 | 2022-12-19 | 2023-02-23 | 2023-03-20 | 66
0 | EDBGPI1020 | BU HASEER WELLHEAD PLATFORM BH-03 PIPING GA DRAWING - IFI | 10 | 2022-12-14 | 2022-12-28 | 2023-03-22 | 2023-04-04 | 70
0 | EDBGPI1040 | BH-03 SPECIAL SUPPORT DRAWINGS - IFA | 7 | 2022-12-21 | 2022-12-30 | 2023-03-15 | 2023-03-23 | 60
0 | EDBGPI1025 | BU HASEER WELLHEAD PLATFORM BH-03 PIPING GA DRAWING - IFC | 5 | 2023-01-11 | 2023-01-18 | 2023-04-19 | 2023-04-27 | 70
0 | EDBGPI1045 | BH-03 SPECIAL SUPPORT DRAWINGS - IFC | 4 | 2023-01-13 | 2023-01-19 | 2023-04-07 | 2023-04-12 | 60
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-23 | 2023-01-17 | 2023-01-04 | 2023-04-27 | 71
0 | EDBGPI2000 | BH-03 PIPING MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-23 | 2022-10-21 | 2023-01-04 | 2023-01-31 | 71
0 | EDBGPI2005 | BH-03 PIPING MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-04 | 2022-12-06 | 2023-02-15 | 2023-03-14 | 71
0 | EDBGPI2010 | BH-03 PIPING MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-20 | 2023-01-17 | 2023-03-29 | 2023-04-27 | 71
MECHANICAL (STATIC / ROTATING) |  |  | 219 | 2022-03-04 | 2023-01-17 | 2022-05-11 | 2023-04-27 | 71
STATIC |  |  | 219 | 2022-03-04 | 2023-01-17 | 2022-05-11 | 2023-04-27 | 71
DOCUMENTS |  |  | 112 | 2022-03-04 | 2022-08-17 | 2022-05-11 | 2022-12-21 | 89
CALCULATION |  |  | 70 | 2022-05-06 | 2022-08-17 | 2022-07-20 | 2022-12-21 | 89
0 | EDBDME1000 | BH-03 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (BH203-V-001) - ICR | 20 | 2022-05-06 | 2022-06-03 | 2022-07-20 | 2022-08-16 | 50
0 | EDBDME1005 | BH-03 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (BH203-V-001) - IFA | 20 | 2022-06-17 | 2022-07-20 | 2022-10-25 | 2022-11-21 | 89
0 | EDBDME1010 | BH-03 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (BH203-V-001) - IFC | 10 | 2022-08-03 | 2022-08-17 | 2022-12-08 | 2022-12-21 | 89
DATA SHEET |  |  | 68 | 2022-03-04 | 2022-06-13 | 2022-05-11 | 2022-11-23 | 115
0 | EDBDME1015 | BH-03 MECHANICAL DATA SHEET FOR PIG LAUNCHER (BH203-PL-001) - ICR | 10 | 2022-03-04 | 2022-03-18 | 2022-05-11 | 2022-05-24 | 45
0 | EDBDME1020 | BH-03 MECHANICAL DATA SHEET FOR PIG LAUNCHER (BH203-PL-001) - IFA | 10 | 2022-03-18 | 2022-04-01 | 2022-05-30 | 2022-06-10 | 48
0 | EDBDME1030 | BH-03 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (BH203-V-001) - ICR | 10 | 2022-03-30 | 2022-04-13 | 2022-06-21 | 2022-07-04 | 56
0 | EDBDME1035 | BH-03 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (BH203-V-001) - IFA | 10 | 2022-04-27 | 2022-05-16 | 2022-10-13 | 2022-10-26 | 115
0 | EDBDME1025 | BH-03 MECHANICAL DATA SHEET FOR PIG LAUNCHER (BH203-PL-001) - IFC | 20 | 2022-04-15 | 2022-05-18 | 2022-06-27 | 2022-07-27 | 48
0 | EDBDME1040 | BH-03 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (BH203-V-001) - IFC | 10 | 2022-05-30 | 2022-06-13 | 2022-11-10 | 2022-11-23 | 115
DRAWINGS |  |  | 97 | 2022-05-27 | 2022-10-14 | 2022-08-10 | 2023-01-31 | 76
0 | EDBGME1000 | BH-03 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.BH203-V-001) - ICR | 10 | 2022-05-27 | 2022-06-10 | 2022-08-10 | 2022-08-23 | 50
0 | EDBGME1005 | BH-03 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.BH203-V-001) - IFA | 10 | 2022-06-24 | 2022-07-13 | 2022-09-07 | 2022-09-20 | 50
0 | EDBGME1015 | BH-03 DETAIL DRAWING FOR VENT DRAIN DRUM (BH203-V-001) - IFI | 10 | 2022-07-28 | 2022-08-11 | 2022-10-06 | 2022-10-19 | 50
0 | EDBGME1045 | BH-03 NOZZLE DETAIL (TAG NO. HD203-V-001) - IFI | 10 | 2022-08-03 | 2022-08-17 | 2022-10-28 | 2022-11-10 | 62
0 | EDBGME1030 | BH-03 WELDING DETAIL & WELD MAP (TAG NO. HD203-V-001) - IFI | 10 | 2022-08-09 | 2022-08-23 | 2022-11-03 | 2022-11-16 | 62
0 | EDBGME1010 | BH-03 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.BH203-V-001) - IFC | 20 | 2022-07-29 | 2022-08-26 | 2022-12-05 | 2022-12-30 | 89
0 | EDBGME1060 | BH-03 MANWAY DAVIT DETAIL (TAG NO. HD203-V-001) - IFI | 10 | 2022-08-15 | 2022-08-29 | 2022-11-29 | 2022-12-14 | 76
0 | EDBGME1075 | BH-03 INTERNAL / EXTERNAL ATTACHMENTS (TAG NO. HD203-V-001) - IFI | 10 | 2022-08-15 | 2022-08-29 | 2022-11-29 | 2022-12-14 | 76
0 | EDBGME1090 | BH-03 NAME PLATE DETAIL (TAG NO. HD203-V-001) - IFI | 10 | 2022-08-19 | 2022-09-02 | 2022-12-07 | 2022-12-20 | 76
0 | EDBGME1025 | BH-03 DETAIL DRAWING FOR VENT DRAIN DRUM (BH203-V-001) - IFC | 15 | 2022-08-25 | 2022-09-15 | 2022-11-24 | 2022-12-16 | 65
0 | EDBGME1055 | BH-03 NOZZLE DETAIL (TAG NO. HD203-V-001) - IFC | 20 | 2022-08-31 | 2022-09-28 | 2022-12-05 | 2022-12-30 | 66
0 | EDBGME1040 | BH-03 WELDING DETAIL & WELD MAP (TAG NO. HD203-V-001) - IFC | 20 | 2022-09-06 | 2022-10-04 | 2022-12-05 | 2022-12-30 | 62
0 | EDBGME1070 | BH-03 MANWAY DAVIT DETAIL (TAG NO. HD203-V-001) - IFC | 20 | 2022-09-12 | 2022-10-10 | 2023-01-02 | 2023-01-27 | 78
0 | EDBGME1085 | BH-03 INTERNAL / EXTERNAL ATTACHMENTS (TAG NO. HD203-V-001) - IFC | 20 | 2022-09-12 | 2022-10-10 | 2023-01-02 | 2023-01-27 | 78
0 | EDBGME1100 | BH-03 NAME PLATE DETAIL (TAG NO. HD203-V-001) - IFC | 20 | 2022-09-16 | 2022-10-14 | 2023-01-04 | 2023-01-31 | 76
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-23 | 2023-01-17 | 2023-01-04 | 2023-04-27 | 71
0 | EDBGME2000 | BH-03 MECHANICAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-23 | 2022-10-21 | 2023-01-04 | 2023-01-31 | 71
0 | EDBGME2005 | BH-03 MECHANICAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-04 | 2022-12-06 | 2023-02-15 | 2023-03-14 | 71
0 | EDBGME2010 | BH-03 MECHANICAL MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-20 | 2023-01-17 | 2023-03-29 | 2023-04-27 | 71
PACKAGE EQUIPMENT |  |  | 47 | 2022-03-23 | 2022-06-01 | 2022-06-20 | 2022-09-07 | 68
DOCUMENTS |  |  | 47 | 2022-03-23 | 2022-06-01 | 2022-06-20 | 2022-09-07 | 68
DATASHEETS |  |  | 47 | 2022-03-23 | 2022-06-01 | 2022-06-20 | 2022-09-07 | 68
0 | EDBDME1045 | BH-03 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - ICR | 9 | 2022-03-23 | 2022-04-05 | 2022-06-20 | 2022-06-30 | 60
0 | EDBDME1050 | BH-03 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - IFA | 9 | 2022-04-19 | 2022-05-05 | 2022-08-01 | 2022-08-11 | 68
0 | EDBDME1055 | BH-03 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - IFC | 9 | 2022-05-19 | 2022-06-01 | 2022-08-26 | 2022-09-07 | 68
ELECTRICAL |  |  | 198 | 2022-04-06 | 2023-01-19 | 2022-07-07 | 2023-04-27 | 69
3D MODEL DEVELOPMENT |  |  | 186 | 2022-04-22 | 2023-01-19 | 2022-07-20 | 2023-04-07 | 57
0 | EDBDEL3000 | BH-03 3D MODEL DEVELOPMENT - ELECTRICAL | 186 | 2022-04-22 | 2023-01-19 | 2022-07-20 | 2023-04-07 | 57
DRAWINGS |  |  | 197 | 2022-04-06 | 2023-01-18 | 2022-07-07 | 2023-04-27 | 70
DIAGRAM |  |  | 150 | 2022-04-06 | 2022-11-10 | 2022-07-07 | 2023-04-27 | 117
0 | EDBGEL1000 | BH-03 SINGLE LINE DIAGRAM – 6.6KV RMU - ICR | 15 | 2022-04-06 | 2022-04-27 | 2022-08-17 | 2022-09-06 | 89
0 | EDBGEL1015 | BH-03 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - ICR | 15 | 2022-04-20 | 2022-05-16 | 2022-08-24 | 2022-09-13 | 84
0 | EDBGEL1002 | BH-03 ELECTRICAL EQUIPMENT LIST - ICR | 15 | 2022-04-25 | 2022-05-19 | 2022-07-07 | 2022-08-01 | 50
0 | EDBGEL1030 | BH-03 SINGLE LINE DIAGRAM – 24V DC UPS - ICR | 15 | 2022-04-27 | 2022-05-23 | 2022-08-31 | 2022-09-20 | 84
0 | EDBGEL1003 | BH-03 ELECTRICAL LOAD LIST - ICR | 15 | 2022-05-05 | 2022-05-26 | 2022-07-19 | 2022-08-08 | 50
0 | EDBGEL1045 | BH-03 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - ICR | 15 | 2022-05-09 | 2022-05-30 | 2022-09-07 | 2022-09-27 | 84
0 | EDBGEL1005 | BH-03 SINGLE LINE DIAGRAM – 6.6KV RMU - IFA | 10 | 2022-05-16 | 2022-05-30 | 2022-10-12 | 2022-10-25 | 104
0 | EDBGEL1060 | BH-03 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - ICR | 15 | 2022-05-16 | 2022-06-06 | 2022-09-14 | 2022-10-04 | 84
0 | EDBGEL1075 | BH-03 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - ICR | 15 | 2022-05-23 | 2022-06-13 | 2022-09-28 | 2022-10-18 | 89
0 | EDBGEL1020 | BH-03 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - IFA | 10 | 2022-05-30 | 2022-06-13 | 2022-10-12 | 2022-10-25 | 94
0 | EDBGEL1035 | BH-03 SINGLE LINE DIAGRAM – 24V DC UPS - IFA | 10 | 2022-06-06 | 2022-06-20 | 2022-10-19 | 2022-11-01 | 94
0 | EDBGEL1006 | BH-03 ELECTRICAL EQUIPMENT LIST - IFA | 15 | 2022-06-02 | 2022-06-23 | 2022-09-01 | 2022-09-21 | 62
0 | EDBGEL1050 | BH-03 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - IFA | 10 | 2022-06-13 | 2022-06-27 | 2022-10-19 | 2022-11-01 | 89
0 | EDBGEL1009 | BH-03 ELECTRICAL LOAD LIST - IFA | 15 | 2022-06-09 | 2022-06-30 | 2022-09-08 | 2022-09-28 | 62
0 | EDBGEL1010 | BH-03 SINGLE LINE DIAGRAM – 6.6KV RMU - IFC | 15 | 2022-06-13 | 2022-07-04 | 2022-11-09 | 2022-11-29 | 104
0 | EDBGEL1065 | BH-03 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-10-19 | 2022-11-01 | 84
0 | EDBGEL1080 | BH-03 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - IFA | 10 | 2022-06-27 | 2022-07-14 | 2022-11-02 | 2022-11-15 | 89
0 | EDBGEL1025 | BH-03 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - IFC | 15 | 2022-06-27 | 2022-07-21 | 2022-11-09 | 2022-11-29 | 94
0 | EDBGEL1040 | BH-03 SINGLE LINE DIAGRAM – 24V DC UPS - IFC | 10 | 2022-07-04 | 2022-07-21 | 2022-11-16 | 2022-11-29 | 94
0 | EDBGEL1055 | BH-03 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - IFC | 10 | 2022-07-14 | 2022-07-28 | 2022-11-16 | 2022-11-29 | 89
0 | EDBGEL1070 | BH-03 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - IFC | 10 | 2022-07-21 | 2022-08-04 | 2022-11-16 | 2022-11-29 | 84
0 | EDBGEL1004 | BH-03 ELECTRICAL EQUIPMENT LIST - IFC | 20 | 2022-07-07 | 2022-08-09 | 2022-10-06 | 2022-11-02 | 62
0 | EDBGEL1085 | BH-03 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - IFC | 10 | 2022-07-28 | 2022-08-11 | 2022-11-30 | 2022-12-15 | 89
0 | EDBGEL1007 | BH-03 ELECTRICAL LOAD LIST - IFC | 20 | 2022-07-19 | 2022-08-16 | 2022-10-13 | 2022-11-09 | 62
0 | EDBGEL1090 | BH-03 ELECTRICAL CABLE SCHEDULE - ICR | 15 | 2022-08-01 | 2022-08-22 | 2023-01-18 | 2023-02-07 | 120
0 | EDBGEL1105 | BH-03 ELECTRICAL INTERCONNECTION DIAGRAM - ICR | 15 | 2022-08-25 | 2022-09-15 | 2023-02-08 | 2023-02-28 | 117
0 | EDBGEL1095 | BH-03 ELECTRICAL CABLE SCHEDULE - IFA | 10 | 2022-09-05 | 2022-09-19 | 2023-03-08 | 2023-03-21 | 130
0 | EDBGEL2020 | BH-03 ELECTRICAL INTERCONNECTION DIAGRAM - IFA | 10 | 2022-09-29 | 2022-10-13 | 2023-03-15 | 2023-03-28 | 117
0 | EDBGEL1100 | BH-03 ELECTRICAL CABLE SCHEDULE - IFC | 15 | 2022-10-03 | 2022-10-24 | 2023-04-05 | 2023-04-27 | 130
0 | EDBGEL1110 | BH-03 ELECTRICAL INTERCONNECTION DIAGRAM - IFC | 10 | 2022-10-27 | 2022-11-10 | 2023-04-12 | 2023-04-27 | 117
BOOKLET |  |  | 50 | 2022-11-07 | 2023-01-18 | 2023-02-15 | 2023-04-27 | 70
0 | EDBGEL1200 | BH-03 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - ICR | 10 | 2022-11-07 | 2022-11-21 | 2023-02-15 | 2023-02-28 | 70
0 | EDBGEL2030 | BH-03 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - IFA | 10 | 2022-12-07 | 2022-12-21 | 2023-03-15 | 2023-03-28 | 70
0 | EDBGEL1205 | BH-03 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - IFC | 10 | 2023-01-04 | 2023-01-18 | 2023-04-12 | 2023-04-27 | 70
LAYOUT |  |  | 137 | 2022-05-05 | 2022-11-17 | 2022-10-25 | 2023-03-23 | 89
0 | EDBGEL1300 | BH-03 ELECTRICAL EQUIPMENT LAYOUT - ICR | 15 | 2022-05-05 | 2022-05-26 | 2022-10-25 | 2022-11-14 | 120
0 | EDBGEL1305 | BH-03 ELECTRICAL EQUIPMENT LAYOUT - IFA | 10 | 2022-06-09 | 2022-06-23 | 2022-11-29 | 2022-12-14 | 120
0 | EDBGEL1375 | BH-03 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - ICR | 10 | 2022-08-12 | 2022-08-26 | 2022-12-09 | 2022-12-22 | 83
0 | EDBGEL1390 | BH-03 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - ICR | 10 | 2022-08-12 | 2022-08-26 | 2023-01-02 | 2023-01-13 | 99
0 | EDBGEL1315 | BH-03 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - ICR | 15 | 2022-08-08 | 2022-08-29 | 2022-11-30 | 2022-12-22 | 82
0 | EDBGEL1330 | BH-03 ELECTRICAL CABLE ROUTING LAYOUT - ICR | 15 | 2022-08-15 | 2022-09-05 | 2022-12-09 | 2022-12-29 | 82
0 | EDBGEL1360 | BH-03 EARTHING & LIGHTNING PROTECTION LAYOUT - ICR | 15 | 2022-08-22 | 2022-09-12 | 2022-12-16 | 2023-01-05 | 82
0 | EDBGEL1345 | BH-03 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - ICR | 15 | 2022-08-22 | 2022-09-12 | 2022-12-16 | 2023-01-05 | 82
0 | EDBGEL1310 | BH-03 ELECTRICAL EQUIPMENT LAYOUT - IFC | 15 | 2022-08-22 | 2022-09-12 | 2022-12-29 | 2023-01-18 | 91
0 | EDBGEL1395 | BH-03 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - IFA | 10 | 2022-09-09 | 2022-09-23 | 2023-01-30 | 2023-02-10 | 99
0 | EDBGEL1380 | BH-03 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - IFA | 10 | 2022-09-09 | 2022-09-23 | 2023-01-16 | 2023-01-27 | 89
0 | EDBGEL2040 | BH-03 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IFA | 10 | 2022-09-12 | 2022-09-26 | 2023-01-20 | 2023-02-02 | 92
0 | EDBGEL2050 | BH-03 ELECTRICAL CABLE ROUTING LAYOUT - IFA | 15 | 2022-09-19 | 2022-10-10 | 2023-01-25 | 2023-02-14 | 90
0 | EDBGEL2060 | BH-03 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IFA | 10 | 2022-09-26 | 2022-10-10 | 2023-02-01 | 2023-02-14 | 90
0 | EDBGEL2070 | BH-03 EARTHING & LIGHTNING PROTECTION LAYOUT - IFA | 15 | 2022-09-26 | 2022-10-17 | 2023-01-20 | 2023-02-09 | 82
0 | EDBGEL1385 | BH-03 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - IFC | 9 | 2022-10-07 | 2022-10-20 | 2023-02-13 | 2023-02-23 | 89
0 | EDBGEL1400 | BH-03 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - IFC | 9 | 2022-10-07 | 2022-10-20 | 2023-02-27 | 2023-03-09 | 99
0 | EDBGEL1325 | BH-03 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IFC | 15 | 2022-10-21 | 2022-11-11 | 2023-02-17 | 2023-03-09 | 83
0 | EDBGEL1355 | BH-03 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IFC | 15 | 2022-10-24 | 2022-11-14 | 2023-03-01 | 2023-03-21 | 90
0 | EDBGEL1370 | BH-03 EARTHING & LIGHTNING PROTECTION LAYOUT - IFC | 10 | 2022-10-31 | 2022-11-14 | 2023-02-24 | 2023-03-09 | 82
0 | EDBGEL1340 | BH-03 ELECTRICAL CABLE ROUTING LAYOUT - IFC | 15 | 2022-10-27 | 2022-11-17 | 2023-03-03 | 2023-03-23 | 89
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-23 | 2023-01-17 | 2023-01-04 | 2023-04-27 | 71
0 | EDBGEL2000 | BH-03 ELECTRICAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-23 | 2022-10-21 | 2023-01-04 | 2023-01-31 | 71
0 | EDBGEL2005 | BH-03 ELECTRICAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-04 | 2022-12-06 | 2023-02-15 | 2023-03-14 | 71
0 | EDBGEL2010 | BH-03 ELECTRICAL MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-20 | 2023-01-17 | 2023-03-29 | 2023-04-27 | 71
INSTRUMENTATION & CONTROL |  |  | 222 | 2022-03-03 | 2023-01-19 | 2022-05-12 | 2023-04-27 | 69
3D MODEL DEVELOPMENT |  |  | 181 | 2022-04-29 | 2023-01-19 | 2022-07-27 | 2023-04-07 | 57
0 | EDBDIN3000 | BH-03 3D MODEL DEVELOPMENT - INSTRUMENTATION | 181 | 2022-04-29 | 2023-01-19 | 2022-07-27 | 2023-04-07 | 57
DOCUMENTS |  |  | 211 | 2022-03-03 | 2023-01-04 | 2022-05-12 | 2023-04-27 | 80
CALCULATIONS |  |  | 73 | 2022-03-22 | 2022-07-06 | 2022-05-25 | 2023-02-27 | 164
0 | EDBDIN1000 | BH-03 CALCULATION NOTE FOR CHOKE VALVES - ICR | 11 | 2022-03-22 | 2022-04-06 | 2022-05-25 | 2022-06-08 | 43
0 | EDBDIN1030 | BH-03 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - ICR | 15 | 2022-03-28 | 2022-04-18 | 2022-08-16 | 2022-09-05 | 95
0 | EDBDIN1045 | BH-03 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - ICR | 15 | 2022-04-08 | 2022-04-29 | 2022-12-06 | 2022-12-26 | 164
0 | EDBDIN1015 | BH-03 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - ICR | 8 | 2022-04-19 | 2022-04-29 | 2022-09-08 | 2022-09-19 | 96
0 | EDBDIN1005 | BH-03 CALCULATION NOTE FOR CHOKE VALVES - IFA | 10 | 2022-04-20 | 2022-05-09 | 2022-06-23 | 2022-07-06 | 43
0 | EDBDIN1035 | BH-03 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - IFA | 15 | 2022-05-05 | 2022-05-26 | 2022-10-26 | 2022-11-15 | 121
0 | EDBDIN1020 | BH-03 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - IFA | 10 | 2022-05-18 | 2022-06-01 | 2022-10-13 | 2022-10-26 | 103
0 | EDBDIN1010 | BH-03 CALCULATION NOTE FOR CHOKE VALVES - IFC | 10 | 2022-05-23 | 2022-06-06 | 2022-07-26 | 2022-08-08 | 43
0 | EDBDIN1050 | BH-03 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - IFA | 15 | 2022-05-18 | 2022-06-08 | 2023-01-10 | 2023-01-30 | 164
0 | EDBDIN1040 | BH-03 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - IFC | 10 | 2022-05-26 | 2022-06-09 | 2022-11-16 | 2022-11-29 | 121
0 | EDBDIN1025 | BH-03 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - IFC | 10 | 2022-06-15 | 2022-06-29 | 2022-11-10 | 2022-11-23 | 103
0 | EDBDIN1055 | BH-03 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - IFC | 10 | 2022-06-22 | 2022-07-06 | 2023-02-14 | 2023-02-27 | 164
INDEX / NARRATIVE |  |  | 50 | 2022-08-15 | 2022-10-24 | 2022-11-08 | 2023-04-27 | 130
0 | EDBDIN1060 | BH-03 INSTRUMENT INDEX - ICR | 10 | 2022-08-15 | 2022-08-29 | 2022-11-08 | 2022-11-21 | 61
0 | EDBDIN1075 | BH-03 FIRE & GAS INDEX - ICR | 10 | 2022-08-15 | 2022-08-29 | 2022-11-08 | 2022-11-21 | 61
0 | EDBDIN1065 | BH-03 INSTRUMENT INDEX - IFA | 10 | 2022-09-12 | 2022-09-26 | 2023-03-22 | 2023-04-04 | 135
0 | EDBDIN1080 | BH-03 FIRE & GAS INDEX - IFA | 10 | 2022-09-12 | 2022-09-26 | 2022-12-08 | 2022-12-21 | 61
0 | EDBDIN1070 | BH-03 INSTRUMENT INDEX - IFC | 5 | 2022-10-10 | 2022-10-17 | 2023-04-19 | 2023-04-27 | 135
0 | EDBDIN1085 | BH-03 FIRE & GAS INDEX - IFC | 10 | 2022-10-10 | 2022-10-24 | 2023-01-05 | 2023-01-18 | 61
DATA SHEET |  |  | 93 | 2022-03-03 | 2022-07-20 | 2022-05-12 | 2023-01-25 | 134
0 | EDBDIN1090 | BH-03 DATASHEETS FOR HIPPS VALVES - ICR | 11 | 2022-03-03 | 2022-03-18 | 2022-05-12 | 2022-05-26 | 47
0 | EDBDIN1135 | BH-03 DATASHEETS FOR ACTUATED ON/OFF VALVES - ICR | 8 | 2022-03-24 | 2022-04-05 | 2022-05-30 | 2022-06-08 | 44
0 | EDBDIN1150 | BH-03 DATASHEETS FOR MOV - ICR | 10 | 2022-03-23 | 2022-04-06 | 2022-05-26 | 2022-06-08 | 43
0 | EDBDIN1120 | BH-03 DATASHEETS FOR CHOKE VALVES - ICR | 8 | 2022-03-28 | 2022-04-07 | 2022-06-02 | 2022-06-13 | 45
0 | EDBDIN1180 | BH-03 DATASHEETS FOR FLOW CHOKE VALVE - ICR | 8 | 2022-03-28 | 2022-04-07 | 2022-06-02 | 2022-06-13 | 45
0 | EDBDIN1195 | BH-03 DATASHEETS FOR SOLENOID OPERATED VALVES - ICR | 8 | 2022-03-28 | 2022-04-07 | 2022-06-02 | 2022-06-13 | 45
0 | EDBDIN1165 | BH-03 DATASHEETS FOR PRESSURE RELIEF VALVES - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-08-16 | 2022-08-29 | 95
0 | EDBDIN1240 | BH-03 DATASHEETS FOR PRESSURE GAUGES - ICR | 10 | 2022-03-30 | 2022-04-13 | 2022-08-26 | 2022-09-08 | 101
0 | EDBDIN1390 | BH-03 DATASHEETS FOR ELECTRONIC SOUNDER - ICR | 9 | 2022-03-31 | 2022-04-13 | 2022-10-13 | 2022-10-25 | 134
0 | EDBDIN1210 | BH-03 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - ICR | 8 | 2022-04-04 | 2022-04-14 | 2022-06-08 | 2022-06-17 | 44
0 | EDBDIN1105 | BH-03 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-06-06 | 2022-06-17 | 43
0 | EDBDIN1405 | BH-03 DATASHEETS FOR EMERGENCY S/D PB - ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-10-14 | 2022-10-27 | 134
0 | EDBDIN1095 | BH-03 DATASHEETS FOR HIPPS VALVES - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-07-14 | 2022-07-27 | 68
0 | EDBDIN1270 | BH-03 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - ICR | 10 | 2022-04-04 | 2022-04-18 | 2022-09-15 | 2022-09-28 | 112
0 | EDBDIN1420 | BH-03 DATASHEETS FOR FLAMMABLE GAS DETECTOR - ICR | 10 | 2022-04-04 | 2022-04-18 | 2022-10-17 | 2022-10-28 | 134
0 | EDBDIN1435 | BH-03 DATASHEETS FOR FIRE GAS DETECTOR - ICR | 10 | 2022-04-05 | 2022-04-19 | 2022-10-18 | 2022-10-31 | 134
0 | EDBDIN1300 | BH-03 DATASHEETS FOR TEMPERATURE TRANSMITTERS - ICR | 8 | 2022-04-08 | 2022-04-20 | 2022-08-31 | 2022-09-09 | 97
0 | EDBDIN1345 | BH-03 DATASHEETS FOR LEVEL TRANSMITTERS - ICR | 10 | 2022-04-07 | 2022-04-21 | 2022-09-05 | 2022-09-16 | 101
0 | EDBDIN1450 | BH-03 DATASHEETS FOR FLASHING BEACON - ICR | 10 | 2022-04-07 | 2022-04-21 | 2022-10-20 | 2022-11-02 | 134
0 | EDBDIN1285 | BH-03 DATASHEETS FOR TEMPERATURE GAUGES - ICR | 8 | 2022-04-11 | 2022-04-21 | 2022-09-09 | 2022-09-20 | 103
0 | EDBDIN1480 | BH-03 DATASHEETS FOR MAN ON BOARD PB - ICR | 9 | 2022-04-11 | 2022-04-22 | 2022-10-24 | 2022-11-03 | 134
0 | EDBDIN1465 | BH-03 DATASHEETS FOR HEAT DETECTOR - ICR | 10 | 2022-04-11 | 2022-04-25 | 2022-10-24 | 2022-11-04 | 134
0 | EDBDIN1495 | BH-03 DATASHEETS FOR TOXIC GAS DETECTOR - ICR | 10 | 2022-04-11 | 2022-04-25 | 2022-10-24 | 2022-11-04 | 134
0 | EDBDIN1330 | BH-03 DATASHEETS FOR LEVEL GAUGES - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-09-05 | 2022-09-16 | 98
0 | EDBDIN1510 | BH-03 DATASHEETS FOR MANUAL ALARM CALL POINT - ICR | 10 | 2022-04-13 | 2022-04-27 | 2022-10-31 | 2022-11-11 | 137
0 | EDBDIN1225 | BH-03 DATASHEETS FOR FLOW RESTRICTION ORIFICE - ICR | 10 | 2022-04-14 | 2022-04-28 | 2022-09-08 | 2022-09-21 | 99
0 | EDBDIN1140 | BH-03 DATASHEETS FOR ACTUATED ON/OFF VALVES - IFA | 10 | 2022-04-19 | 2022-05-06 | 2022-07-21 | 2022-08-03 | 61
0 | EDBDIN1315 | BH-03 DATASHEETS FOR PIG SIGNALLER - ICR | 10 | 2022-04-20 | 2022-05-09 | 2022-10-03 | 2022-10-14 | 112
0 | EDBDIN1155 | BH-03 DATASHEETS FOR MOV - IFA | 10 | 2022-04-20 | 2022-05-09 | 2022-07-21 | 2022-08-03 | 60
0 | EDBDIN1360 | BH-03 DATASHEETS FOR FLOW SWITCHES - ICR | 10 | 2022-04-21 | 2022-05-10 | 2022-10-19 | 2022-11-01 | 123
0 | EDBDIN1125 | BH-03 DATASHEETS FOR CHOKE VALVES - IFA | 10 | 2022-04-21 | 2022-05-10 | 2022-07-04 | 2022-07-20 | 49
0 | EDBDIN1185 | BH-03 DATASHEETS FOR FLOW CHOKE VALVE - IFA | 10 | 2022-04-21 | 2022-05-10 | 2022-07-21 | 2022-08-03 | 59
0 | EDBDIN1200 | BH-03 DATASHEETS FOR SOLENOID OPERATED VALVES - IFA | 10 | 2022-04-21 | 2022-05-10 | 2022-07-21 | 2022-08-03 | 59
0 | EDBDIN1100 | BH-03 DATASHEETS FOR HIPPS VALVES - IFC | 15 | 2022-04-15 | 2022-05-11 | 2022-08-08 | 2022-08-26 | 75
0 | EDBDIN1255 | BH-03 DATASHEETS FOR CORROSION MONITOR - ICR | 10 | 2022-04-22 | 2022-05-11 | 2022-09-28 | 2022-10-11 | 107
0 | EDBDIN1170 | BH-03 DATASHEETS FOR PRESSURE RELIEF VALVES - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-10-12 | 2022-10-25 | 116
0 | EDBDIN1375 | BH-03 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - ICR | 10 | 2022-04-26 | 2022-05-13 | 2022-10-24 | 2022-11-04 | 123
0 | EDBDIN1395 | BH-03 DATASHEETS FOR ELECTRONIC SOUNDER - IFA | 9 | 2022-04-27 | 2022-05-13 | 2022-11-30 | 2022-12-14 | 149
0 | EDBDIN1245 | BH-03 DATASHEETS FOR PRESSURE GAUGES - IFA | 10 | 2022-04-27 | 2022-05-16 | 2022-10-18 | 2022-10-31 | 118
0 | EDBDIN1215 | BH-03 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-07-21 | 2022-08-03 | 54
0 | EDBDIN1110 | BH-03 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-07-21 | 2022-08-03 | 53
0 | EDBDIN1410 | BH-03 DATASHEETS FOR EMERGENCY S/D PB - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-11-28 | 2022-12-13 | 145
0 | EDBDIN1425 | BH-03 DATASHEETS FOR FLAMMABLE GAS DETECTOR - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-11-28 | 2022-12-13 | 144
0 | EDBDIN1275 | BH-03 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-10-13 | 2022-10-26 | 112
0 | EDBDIN1440 | BH-03 DATASHEETS FOR FIRE GAS DETECTOR - IFA | 10 | 2022-05-06 | 2022-05-20 | 2022-11-28 | 2022-12-13 | 143
0 | EDBDIN1305 | BH-03 DATASHEETS FOR TEMPERATURE TRANSMITTERS - IFA | 10 | 2022-05-09 | 2022-05-23 | 2022-10-13 | 2022-10-26 | 110
0 | EDBDIN1455 | BH-03 DATASHEETS FOR FLASHING BEACON - IFA | 10 | 2022-05-10 | 2022-05-24 | 2022-11-28 | 2022-12-13 | 141
0 | EDBDIN1485 | BH-03 DATASHEETS FOR MAN ON BOARD PB - IFA | 9 | 2022-05-11 | 2022-05-24 | 2022-11-30 | 2022-12-14 | 142
0 | EDBDIN1290 | BH-03 DATASHEETS FOR TEMPERATURE GAUGES - IFA | 10 | 2022-05-10 | 2022-05-24 | 2022-10-14 | 2022-10-27 | 110
0 | EDBDIN1350 | BH-03 DATASHEETS FOR LEVEL TRANSMITTERS - IFA | 10 | 2022-05-10 | 2022-05-24 | 2022-10-17 | 2022-10-28 | 111
0 | EDBDIN1470 | BH-03 DATASHEETS FOR HEAT DETECTOR - IFA | 10 | 2022-05-12 | 2022-05-26 | 2022-11-28 | 2022-12-13 | 139
0 | EDBDIN1500 | BH-03 DATASHEETS FOR TOXIC GAS DETECTOR - IFA | 10 | 2022-05-12 | 2022-05-26 | 2022-11-28 | 2022-12-13 | 139
0 | EDBDIN1335 | BH-03 DATASHEETS FOR LEVEL GAUGES - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-10-05 | 2022-10-18 | 100
0 | EDBDIN1515 | BH-03 DATASHEETS FOR MANUAL ALARM CALL POINT - IFA | 10 | 2022-05-16 | 2022-05-30 | 2022-11-28 | 2022-12-13 | 137
0 | EDBDIN1320 | BH-03 DATASHEETS FOR PIG SIGNALLER - IFA | 10 | 2022-05-23 | 2022-06-06 | 2022-11-23 | 2022-12-08 | 129
0 | EDBDIN1230 | BH-03 DATASHEETS FOR FLOW RESTRICTION ORIFICE - IFA | 10 | 2022-05-24 | 2022-06-07 | 2022-10-06 | 2022-10-19 | 94
0 | EDBDIN1365 | BH-03 DATASHEETS FOR FLOW SWITCHES - IFA | 10 | 2022-05-24 | 2022-06-07 | 2022-12-08 | 2022-12-21 | 137
0 | EDBDIN1260 | BH-03 DATASHEETS FOR CORROSION MONITOR - IFA | 10 | 2022-05-25 | 2022-06-08 | 2022-11-09 | 2022-11-22 | 117
0 | EDBDIN1145 | BH-03 DATASHEETS FOR ACTUATED ON/OFF VALVES - IFC | 15 | 2022-05-20 | 2022-06-10 | 2022-08-18 | 2022-09-07 | 61
0 | EDBDIN1380 | BH-03 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - IFA | 10 | 2022-05-27 | 2022-06-10 | 2022-11-28 | 2022-12-13 | 128
0 | EDBDIN1160 | BH-03 DATASHEETS FOR MOV - IFC | 15 | 2022-05-23 | 2022-06-13 | 2022-08-18 | 2022-09-07 | 60
0 | EDBDIN1130 | BH-03 DATASHEETS FOR CHOKE VALVES - IFC | 15 | 2022-05-24 | 2022-06-14 | 2022-08-04 | 2022-08-24 | 49
0 | EDBDIN1190 | BH-03 DATASHEETS FOR FLOW CHOKE VALVE - IFC | 15 | 2022-05-24 | 2022-06-14 | 2022-08-18 | 2022-09-07 | 59
0 | EDBDIN1205 | BH-03 DATASHEETS FOR SOLENOID OPERATED VALVES - IFC | 15 | 2022-05-24 | 2022-06-14 | 2022-08-18 | 2022-09-07 | 59
0 | EDBDIN1175 | BH-03 DATASHEETS FOR PRESSURE RELIEF VALVES - IFC | 15 | 2022-05-26 | 2022-06-16 | 2022-11-09 | 2022-11-29 | 116
0 | EDBDIN1400 | BH-03 DATASHEETS FOR ELECTRONIC SOUNDER - IFC | 14 | 2022-05-27 | 2022-06-16 | 2022-12-29 | 2023-01-17 | 149
0 | EDBDIN1355 | BH-03 DATASHEETS FOR LEVEL TRANSMITTERS - IFC | 10 | 2022-06-07 | 2022-06-21 | 2022-11-16 | 2022-11-29 | 113
0 | EDBDIN1220 | BH-03 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - IFC | 15 | 2022-05-31 | 2022-06-21 | 2022-08-18 | 2022-09-07 | 54
0 | EDBDIN1250 | BH-03 DATASHEETS FOR PRESSURE GAUGES - IFC | 15 | 2022-06-01 | 2022-06-22 | 2022-11-15 | 2022-12-07 | 116
0 | EDBDIN1115 | BH-03 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - IFC | 15 | 2022-06-01 | 2022-06-22 | 2022-08-18 | 2022-09-07 | 53
0 | EDBDIN1415 | BH-03 DATASHEETS FOR EMERGENCY S/D PB - IFC | 15 | 2022-06-01 | 2022-06-22 | 2022-12-28 | 2023-01-17 | 145
0 | EDBDIN1280 | BH-03 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - IFC | 15 | 2022-06-02 | 2022-06-23 | 2022-11-10 | 2022-11-30 | 112
0 | EDBDIN1430 | BH-03 DATASHEETS FOR FLAMMABLE GAS DETECTOR - IFC | 15 | 2022-06-02 | 2022-06-23 | 2022-12-28 | 2023-01-17 | 144
0 | EDBDIN1445 | BH-03 DATASHEETS FOR FIRE GAS DETECTOR - IFC | 15 | 2022-06-03 | 2022-06-24 | 2022-12-28 | 2023-01-17 | 143
0 | EDBDIN1490 | BH-03 DATASHEETS FOR MAN ON BOARD PB - IFC | 14 | 2022-06-07 | 2022-06-27 | 2022-12-29 | 2023-01-17 | 142
0 | EDBDIN1310 | BH-03 DATASHEETS FOR TEMPERATURE TRANSMITTERS - IFC | 15 | 2022-06-06 | 2022-06-27 | 2022-11-10 | 2022-11-30 | 110
0 | EDBDIN1460 | BH-03 DATASHEETS FOR FLASHING BEACON - IFC | 15 | 2022-06-07 | 2022-06-28 | 2022-12-28 | 2023-01-17 | 141
0 | EDBDIN1295 | BH-03 DATASHEETS FOR TEMPERATURE GAUGES - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-11-11 | 2022-12-05 | 109
0 | EDBDIN1475 | BH-03 DATASHEETS FOR HEAT DETECTOR - IFC | 15 | 2022-06-09 | 2022-06-30 | 2022-12-28 | 2023-01-17 | 139
0 | EDBDIN1505 | BH-03 DATASHEETS FOR TOXIC GAS DETECTOR - IFC | 15 | 2022-06-09 | 2022-06-30 | 2022-12-28 | 2023-01-17 | 139
0 | EDBDIN1340 | BH-03 DATASHEETS FOR LEVEL GAUGES - IFC | 15 | 2022-06-13 | 2022-07-04 | 2022-11-02 | 2022-11-22 | 99
0 | EDBDIN1520 | BH-03 DATASHEETS FOR MANUAL ALARM CALL POINT- IFC | 15 | 2022-06-13 | 2022-07-04 | 2022-12-28 | 2023-01-17 | 137
0 | EDBDIN1325 | BH-03 DATASHEETS FOR PIG SIGNALLER - IFC | 15 | 2022-06-20 | 2022-07-14 | 2022-12-23 | 2023-01-12 | 129
0 | EDBDIN1370 | BH-03 DATASHEETS FOR FLOW SWITCHES - IFC | 15 | 2022-06-21 | 2022-07-15 | 2023-01-05 | 2023-01-25 | 137
0 | EDBDIN1235 | BH-03 DATASHEETS FOR FLOW RESTRICTION ORIFICE - IFC | 15 | 2022-06-22 | 2022-07-18 | 2022-11-03 | 2022-11-23 | 93
0 | EDBDIN1265 | BH-03 DATASHEETS FOR CORROSION MONITOR - IFC | 15 | 2022-06-22 | 2022-07-18 | 2022-12-09 | 2022-12-29 | 117
0 | EDBDIN1385 | BH-03 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - IFC | 15 | 2022-06-24 | 2022-07-20 | 2022-12-28 | 2023-01-17 | 128
SCHEDULE / MTO |  |  | 99 | 2022-06-02 | 2022-10-24 | 2022-10-20 | 2023-04-27 | 130
0 | EDBDIN1525 | BH-03 INSTRUMENT 1ST MTO | 10 | 2022-06-02 | 2022-06-16 | 2022-12-23 | 2023-01-05 | 141
0 | EDBDIN1535 | BH-03 INSTRUMENT CABLE SCHEDULE - ICR | 10 | 2022-06-29 | 2022-07-18 | 2022-10-20 | 2022-11-02 | 78
0 | EDBDIN1550 | BH-03 JUNCTION BOX SCHEDULE - ICR | 10 | 2022-06-29 | 2022-07-18 | 2022-11-08 | 2022-11-21 | 91
0 | EDBDIN1540 | BH-03 INSTRUMENT CABLE SCHEDULE - IFA | 10 | 2022-08-01 | 2022-08-15 | 2022-12-08 | 2022-12-21 | 91
0 | EDBDIN1555 | BH-03 JUNCTION BOX SCHEDULE - IFA | 10 | 2022-08-01 | 2022-08-15 | 2022-12-08 | 2022-12-21 | 91
0 | EDBDIN1565 | BH-03 TUBE SCHEDULE - ICR | 10 | 2022-08-15 | 2022-08-29 | 2023-02-15 | 2023-02-28 | 130
0 | EDBDIN1545 | BH-03 INSTRUMENT CABLE SCHEDULE - IFC | 10 | 2022-08-29 | 2022-09-12 | 2023-01-05 | 2023-01-18 | 91
0 | EDBDIN1560 | BH-03 JUNCTION BOX SCHEDULE - IFC | 10 | 2022-08-29 | 2022-09-12 | 2023-01-05 | 2023-01-18 | 91
0 | EDBDIN1530 | BH-03 INSTRUMENT FINAL MTO | 10 | 2022-09-05 | 2022-09-19 | 2023-01-20 | 2023-02-02 | 97
0 | EDBDIN1570 | BH-03 TUBE SCHEDULE - IFA | 10 | 2022-09-12 | 2022-09-26 | 2023-03-15 | 2023-03-28 | 130
0 | EDBDIN1575 | BH-03 TUBE SCHEDULE - IFC | 10 | 2022-10-10 | 2022-10-24 | 2023-04-12 | 2023-04-27 | 130
LIST |  |  | 95 | 2022-08-22 | 2023-01-04 | 2022-12-14 | 2023-04-27 | 80
0 | EDBDIN1580 | BH-03 I/O LIST FOR DCS - ICR | 20 | 2022-08-22 | 2022-09-19 | 2022-12-14 | 2023-01-10 | 80
0 | EDBDIN1595 | BH-03 I/O LIST FOR ESD SYSTEM - ICR | 20 | 2022-08-29 | 2022-09-26 | 2022-12-21 | 2023-01-17 | 80
0 | EDBDIN1610 | BH-03 I/O LIST FOR F&G SYSTEM - ICR | 20 | 2022-09-05 | 2022-10-03 | 2022-12-28 | 2023-01-24 | 80
0 | EDBDIN1625 | BH-03 I/O LIST FOR HIPPS - ICR | 20 | 2022-09-12 | 2022-10-10 | 2023-01-04 | 2023-01-31 | 80
0 | EDBDIN1585 | BH-03 I/O LIST FOR DCS - IFA | 20 | 2022-10-03 | 2022-10-31 | 2023-02-15 | 2023-03-14 | 95
0 | EDBDIN1600 | BH-03 I/O LIST FOR ESD SYSTEM - IFA | 20 | 2022-10-10 | 2022-11-07 | 2023-02-15 | 2023-03-14 | 90
0 | EDBDIN1615 | BH-03 I/O LIST FOR F&G SYSTEM - IFA | 20 | 2022-10-17 | 2022-11-14 | 2023-02-15 | 2023-03-14 | 85
0 | EDBDIN1630 | BH-03 I/O LIST FOR HIPPS - IFA | 20 | 2022-10-24 | 2022-11-21 | 2023-02-15 | 2023-03-14 | 80
0 | EDBDIN1590 | BH-03 I/O LIST FOR DCS - IFC | 20 | 2022-11-14 | 2022-12-14 | 2023-03-29 | 2023-04-27 | 95
0 | EDBDIN1605 | BH-03 I/O LIST FOR ESD SYSTEM - IFC | 20 | 2022-11-21 | 2022-12-21 | 2023-03-29 | 2023-04-27 | 90
0 | EDBDIN1620 | BH-03 I/O LIST FOR F&G SYSTEM - IFC | 20 | 2022-11-28 | 2022-12-28 | 2023-03-29 | 2023-04-27 | 85
0 | EDBDIN1635 | BH-03 I/O LIST FOR HIPPS - IFC | 20 | 2022-12-07 | 2023-01-04 | 2023-03-29 | 2023-04-27 | 80
DRAWINGS |  |  | 200 | 2022-03-30 | 2023-01-16 | 2022-08-08 | 2023-04-27 | 72
DIAGRAM |  |  | 200 | 2022-03-30 | 2023-01-16 | 2022-08-08 | 2023-04-27 | 72
0 | EDBGIN1000 | BH-03 LEVEL SKETCH- ICR | 12 | 2022-03-30 | 2022-04-15 | 2022-08-08 | 2022-08-23 | 87
0 | EDBGIN1015 | BH-03 INSTRUMENT CABLE BLOCK DIAGRAM - ICR | 15 | 2022-03-31 | 2022-04-21 | 2022-08-30 | 2022-09-19 | 102
0 | EDBGIN1030 | BH-03 TUBING BLOCK DIAGRAM - ICR | 15 | 2022-04-21 | 2022-05-17 | 2022-10-11 | 2022-10-31 | 117
0 | EDBGIN1005 | BH-03 LEVEL SKETCH- IFA | 12 | 2022-04-29 | 2022-05-20 | 2022-09-07 | 2022-09-22 | 87
0 | EDBGIN1020 | BH-03 INSTRUMENT CABLE BLOCK DIAGRAM - IFA | 15 | 2022-05-10 | 2022-05-31 | 2022-11-15 | 2022-12-07 | 132
0 | EDBGIN1075 | BH-03 PROCESS & HYDRAULIC HOOK-UPS DRAWING - ICR | 15 | 2022-05-20 | 2022-06-10 | 2022-09-23 | 2022-10-13 | 87
0 | EDBGIN1010 | BH-03 LEVEL SKETCH- IFC | 12 | 2022-06-03 | 2022-06-21 | 2022-12-09 | 2022-12-26 | 130
0 | EDBGIN1035 | BH-03 TUBING BLOCK DIAGRAM - IFA | 15 | 2022-05-31 | 2022-06-21 | 2022-11-15 | 2022-12-07 | 117
0 | EDBGIN1025 | BH-03 INSTRUMENT CABLE BLOCK DIAGRAM - IFC | 20 | 2022-06-14 | 2022-07-15 | 2022-12-22 | 2023-01-18 | 132
0 | EDBGIN1080 | BH-03 PROCESS & HYDRAULIC HOOK-UPS DRAWING - IFA | 15 | 2022-06-24 | 2022-07-20 | 2022-11-08 | 2022-11-28 | 94
0 | EDBGIN1040 | BH-03 TUBING BLOCK DIAGRAM - IFC | 20 | 2022-07-05 | 2022-08-05 | 2022-12-22 | 2023-01-18 | 117
0 | EDBGIN1085 | BH-03 PROCESS & HYDRAULIC HOOK-UPS DRAWING - IFC | 15 | 2022-08-03 | 2022-08-24 | 2022-12-15 | 2023-01-04 | 94
0 | EDBGIN1090 | BH-03 INSTRUMENT LOOP DIAGRAMS - DCS - ICR | 10 | 2022-10-07 | 2022-10-21 | 2023-01-27 | 2023-02-09 | 78
0 | EDBGIN1045 | BH-03 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - ICR | 15 | 2022-09-30 | 2022-10-21 | 2023-01-12 | 2023-02-01 | 72
0 | EDBGIN1105 | BH-03 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - ICR | 10 | 2022-10-11 | 2022-10-25 | 2023-01-31 | 2023-02-13 | 78
0 | EDBGIN1060 | BH-03 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - ICR | 15 | 2022-10-06 | 2022-10-27 | 2023-01-18 | 2023-02-07 | 72
0 | EDBGIN1120 | BH-03 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - ICR | 10 | 2022-10-13 | 2022-10-27 | 2023-02-02 | 2023-02-15 | 78
0 | EDBGIN1135 | BH-03 INSTRUMENT LOOP DIAGRAMS - HIPPS - ICR | 10 | 2022-10-21 | 2022-11-04 | 2023-02-08 | 2023-02-21 | 76
0 | EDBGIN1095 | BH-03 INSTRUMENT LOOP DIAGRAMS - DCS - IFA | 10 | 2022-11-04 | 2022-11-18 | 2023-03-08 | 2023-03-21 | 86
0 | EDBGIN1110 | BH-03 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - IFA | 10 | 2022-11-08 | 2022-11-22 | 2023-03-08 | 2023-03-21 | 84
0 | EDBGIN1125 | BH-03 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - IFA | 10 | 2022-11-10 | 2022-11-24 | 2023-03-08 | 2023-03-21 | 82
0 | EDBGIN1050 | BH-03 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - IFA | 15 | 2022-11-04 | 2022-11-25 | 2023-03-01 | 2023-03-21 | 81
0 | EDBGIN1065 | BH-03 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - IFA | 15 | 2022-11-10 | 2022-12-05 | 2023-02-22 | 2023-03-14 | 72
0 | EDBGIN1140 | BH-03 INSTRUMENT LOOP DIAGRAMS - HIPPS - IFA | 10 | 2022-11-18 | 2022-12-06 | 2023-03-08 | 2023-03-21 | 76
0 | EDBGIN1100 | BH-03 INSTRUMENT LOOP DIAGRAMS - DCS - IFC | 15 | 2022-12-06 | 2022-12-27 | 2023-04-05 | 2023-04-27 | 86
0 | EDBGIN1115 | BH-03 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - IFC | 15 | 2022-12-08 | 2022-12-29 | 2023-04-05 | 2023-04-27 | 84
0 | EDBGIN1130 | BH-03 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - IFC | 15 | 2022-12-12 | 2023-01-02 | 2023-04-05 | 2023-04-27 | 82
0 | EDBGIN1055 | BH-03 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - IFC | 15 | 2022-12-14 | 2023-01-04 | 2023-04-05 | 2023-04-27 | 80
0 | EDBGIN1145 | BH-03 INSTRUMENT LOOP DIAGRAMS - HIPPS - IFC | 15 | 2022-12-20 | 2023-01-10 | 2023-04-05 | 2023-04-27 | 76
0 | EDBGIN1070 | BH-03 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
LAYOUT |  |  | 87 | 2022-06-30 | 2022-11-03 | 2022-10-07 | 2023-04-27 | 122
0 | EDBGIN1215 | BH-03 INSTRUMENT CABLE ROUTING LAYOUT - ICR | 15 | 2022-06-30 | 2022-07-26 | 2022-10-19 | 2022-11-08 | 76
0 | EDBGIN1230 | BH-03 INSTRUMENT LOCATION LAYOUTS - ICR | 15 | 2022-07-07 | 2022-08-02 | 2023-01-12 | 2023-02-01 | 130
0 | EDBGIN1245 | BH-03 TUBE ROUTING LAYOUT - ICR | 15 | 2022-07-18 | 2022-08-08 | 2023-01-18 | 2023-02-07 | 130
0 | EDBGIN1200 | BH-03 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - ICR | 15 | 2022-07-26 | 2022-08-16 | 2022-10-07 | 2022-10-27 | 53
0 | EDBGIN1220 | BH-03 INSTRUMENT CABLE ROUTING LAYOUT - IFA | 10 | 2022-08-09 | 2022-08-23 | 2022-11-23 | 2022-12-08 | 76
0 | EDBGIN1265 | BH-03 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - ICR | 15 | 2022-08-04 | 2022-08-25 | 2022-10-18 | 2022-11-07 | 53
0 | EDBGIN1235 | BH-03 INSTRUMENT LOCATION LAYOUTS - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-02-22 | 2023-03-14 | 134
0 | EDBGIN1250 | BH-03 TUBE ROUTING LAYOUT - IFA | 15 | 2022-08-22 | 2022-09-12 | 2023-02-22 | 2023-03-14 | 130
0 | EDBGIN1205 | BH-03 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - IFA | 15 | 2022-08-30 | 2022-09-20 | 2022-11-28 | 2022-12-20 | 64
0 | EDBGIN1275 | BH-03 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - IFA | 15 | 2022-09-08 | 2022-09-29 | 2022-11-22 | 2022-12-14 | 53
0 | EDBGIN1225 | BH-03 INSTRUMENT CABLE ROUTING LAYOUT - IFC | 20 | 2022-09-06 | 2022-10-04 | 2022-12-23 | 2023-01-19 | 76
0 | EDBGIN1240 | BH-03 INSTRUMENT LOCATION LAYOUTS - IFC | 20 | 2022-09-20 | 2022-10-18 | 2023-03-29 | 2023-04-27 | 134
0 | EDBGIN1255 | BH-03 TUBE ROUTING LAYOUT - IFC | 20 | 2022-09-26 | 2022-10-24 | 2023-03-29 | 2023-04-27 | 130
0 | EDBGIN1210 | BH-03 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - IFC | 15 | 2022-10-04 | 2022-10-25 | 2023-01-04 | 2023-01-24 | 64
0 | EDBGIN1285 | BH-03 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - IFC | 15 | 2022-10-13 | 2022-11-03 | 2022-12-29 | 2023-01-18 | 53
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-23 | 2023-01-17 | 2023-01-04 | 2023-04-27 | 71
0 | EDBGIN2000 | BH-03 INSTRUMENT MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-23 | 2022-10-21 | 2023-01-04 | 2023-01-31 | 71
0 | EDBGIN2005 | BH-03 INSTRUMENT MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-04 | 2022-12-06 | 2023-02-15 | 2023-03-14 | 71
0 | EDBGIN2010 | BH-03 INSTRUMENT MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-20 | 2023-01-17 | 2023-03-29 | 2023-04-27 | 71
TELECOM |  |  | 157 | 2022-06-03 | 2023-01-17 | 2022-09-27 | 2023-04-27 | 71
DOCUMENTS |  |  | 96 | 2022-06-03 | 2022-10-20 | 2022-09-27 | 2023-04-27 | 132
LIST/SCHEDULE |  |  | 96 | 2022-06-03 | 2022-10-20 | 2022-09-27 | 2023-04-27 | 132
0 | EDBDTE1000 | BH-03 TELECOMMUNICATION - 1ST MTO | 10 | 2022-06-03 | 2022-06-17 | 2022-09-27 | 2022-10-10 | 79
0 | EDBDTE1010 | BH-03 TELECOM EQUIPMENT LIST - ICR | 10 | 2022-06-17 | 2022-07-01 | 2022-10-11 | 2022-10-24 | 79
0 | EDBDTE1015 | BH-03 TELECOM EQUIPMENT LIST - IFA | 10 | 2022-07-20 | 2022-08-03 | 2022-11-22 | 2022-12-07 | 89
0 | EDBDTE1025 | BH-03 TELECOM CABLE SCHEDULE - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-02-01 | 2023-02-14 | 122
0 | EDBDTE1020 | BH-03 TELECOM EQUIPMENT LIST - IFC | 20 | 2022-08-17 | 2022-09-14 | 2022-12-22 | 2023-01-18 | 89
0 | EDBDTE1005 | BH-03 TELECOMMUNICATION - FINAL MTO | 9 | 2022-09-06 | 2022-09-19 | 2023-01-23 | 2023-02-02 | 97
0 | EDBDTE1030 | BH-03 TELECOM CABLE SCHEDULE - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-15 | 2023-03-28 | 132
0 | EDBDTE1035 | BH-03 TELECOM CABLE SCHEDULE - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-04-12 | 2023-04-27 | 132
DRAWINGS |  |  | 86 | 2022-07-20 | 2022-11-17 | 2022-11-08 | 2023-04-27 | 112
LAYOUT |  |  | 86 | 2022-07-20 | 2022-11-17 | 2022-11-08 | 2023-04-27 | 112
0 | EDBGTE1015 | BH-03 TELECOM EQUIPMENT LOCATION LAYOUTS - ICR | 10 | 2022-07-20 | 2022-08-03 | 2022-11-08 | 2022-11-21 | 79
0 | EDBGTE1000 | BH-03 TELECOM CABLE ROUTING LAYOUT - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-01-18 | 2023-01-31 | 112
0 | EDBGTE1020 | BH-03 TELECOM EQUIPMENT LOCATION LAYOUTS - IFA | 10 | 2022-08-17 | 2022-08-31 | 2022-12-08 | 2022-12-21 | 79
0 | EDBGTE1045 | BH-03 TELECOM DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - ICR | 10 | 2022-08-25 | 2022-09-08 | 2023-02-01 | 2023-02-14 | 112
0 | EDBGTE1030 | BH-03 FIBER OPTIC ALLOCATION DRAWING - ICR | 10 | 2022-08-25 | 2022-09-08 | 2023-02-15 | 2023-02-28 | 122
0 | EDBGTE1005 | BH-03 TELECOM CABLE ROUTING LAYOUT - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-15 | 2023-03-28 | 132
0 | EDBGTE1025 | BH-03 TELECOM EQUIPMENT LOCATION LAYOUTS - IFC | 10 | 2022-09-14 | 2022-09-28 | 2023-01-05 | 2023-01-18 | 79
0 | EDBGTE1035 | BH-03 FIBER OPTIC ALLOCATION DRAWING - IFA | 10 | 2022-09-22 | 2022-10-06 | 2023-03-15 | 2023-03-28 | 122
0 | EDBGTE1050 | BH-03 TELECOM DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - IFA | 10 | 2022-09-22 | 2022-10-06 | 2023-03-01 | 2023-03-14 | 112
0 | EDBGTE1010 | BH-03 TELECOM CABLE ROUTING LAYOUT - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-04-12 | 2023-04-27 | 132
0 | EDBGTE1040 | BH-03 FIBER OPTIC ALLOCATION DRAWING - IFC | 10 | 2022-10-20 | 2022-11-03 | 2023-04-12 | 2023-04-27 | 122
0 | EDBGTE1055 | BH-03 TELECOM DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - IFC | 20 | 2022-10-20 | 2022-11-17 | 2023-03-29 | 2023-04-27 | 112
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-23 | 2023-01-17 | 2023-01-04 | 2023-04-27 | 71
0 | EDBGTE2000 | BH-03 TELECOM MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-23 | 2022-10-21 | 2023-01-04 | 2023-01-31 | 71
0 | EDBGTE2005 | BH-03 TELECOM MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-04 | 2022-12-06 | 2023-02-15 | 2023-03-14 | 71
0 | EDBGTE2010 | BH-03 TELECOM MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-20 | 2023-01-17 | 2023-03-29 | 2023-04-27 | 71
STRUCTURAL |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-06-06 | 2023-06-05 | 96
3D MODEL DEVELOPMENT |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-06-06 | 2023-04-07 | 57
0 | EDBDSR3000 | BH-03 3D MODEL DEVELOPMENT - STRUCTURAL | 215 | 2022-03-14 | 2023-01-19 | 2022-06-06 | 2023-04-07 | 57
DOCUMENTS |  |  | 145 | 2022-05-05 | 2022-11-29 | 2022-08-05 | 2023-04-19 | 100
REPORTS |  |  | 145 | 2022-05-05 | 2022-11-29 | 2022-08-05 | 2023-04-19 | 100
0 | EDBDSR1000 | BH-03 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - ICR | 20 | 2022-05-05 | 2022-06-02 | 2022-08-05 | 2022-09-01 | 63
0 | EDBDSR1135 | BH-03 TOPSIDES LIFT ANALYSES REPORT - ICR | 20 | 2022-05-12 | 2022-06-09 | 2022-09-01 | 2022-09-28 | 77
0 | EDBDSR1195 | BH-03 TOPSIDES LINEAR BLAST ANALYSIS REPORT - ICR | 20 | 2022-05-12 | 2022-06-09 | 2022-08-12 | 2022-09-08 | 63
0 | EDBDSR1090 | BH-03 HELIDECK DESIGN REPORT - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-09-23 | 2022-10-20 | 88
0 | EDBDSR1150 | BH-03 TOPSIDES LOADOUT ANALYSIS REPORT - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-11-15 | 2022-12-14 | 125
0 | EDBDSR1075 | BH-03 TOPSIDE JOINT DESIGN REPORT - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-08-19 | 2022-09-15 | 63
0 | EDBDSR1165 | BH-03 TOPSIDES TRANSPORTATION ANALYSES REPORT - ICR | 20 | 2022-05-26 | 2022-06-23 | 2022-11-22 | 2022-12-21 | 125
0 | EDBDSR1005 | BH-03 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - IFA | 10 | 2022-06-16 | 2022-06-30 | 2022-09-30 | 2022-10-13 | 73
0 | EDBDSR1105 | BH-03 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - ICR | 20 | 2022-06-09 | 2022-07-07 | 2022-09-22 | 2022-10-19 | 72
0 | EDBDSR1140 | BH-03 TOPSIDES LIFT ANALYSES REPORT - IFA | 15 | 2022-06-23 | 2022-07-19 | 2023-01-11 | 2023-01-31 | 139
0 | EDBDSR1200 | BH-03 TOPSIDES LINEAR BLAST ANALYSIS REPORT - IFA | 15 | 2022-06-23 | 2022-07-19 | 2022-12-22 | 2023-01-11 | 125
0 | EDBDSR1180 | BH-03 TOPSIDE MISCELLANEOUS DESIGN REPORT - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-12-22 | 2023-01-18 | 125
0 | EDBDSR1015 | BH-03 JACKET INPLACE ANALYSIS REPORT - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-11-15 | 2022-12-14 | 100
0 | EDBDSR1095 | BH-03 HELIDECK DESIGN REPORT - IFA | 15 | 2022-06-30 | 2022-07-26 | 2022-11-11 | 2022-12-05 | 93
0 | EDBDSR1155 | BH-03 TOPSIDES LOADOUT ANALYSIS REPORT - IFA | 15 | 2022-06-30 | 2022-07-26 | 2023-02-01 | 2023-02-21 | 149
0 | EDBDSR1080 | BH-03 TOPSIDE JOINT DESIGN REPORT - IFA | 15 | 2022-06-30 | 2022-07-26 | 2022-09-30 | 2022-10-20 | 63
0 | EDBDSR1170 | BH-03 TOPSIDES TRANSPORTATION ANALYSES REPORT - IFA | 15 | 2022-07-07 | 2022-08-02 | 2023-02-01 | 2023-02-21 | 144
0 | EDBDSR1030 | BH-03 JACKET PUSHOVER ANALYSIS REPORT - ICR | 20 | 2022-07-07 | 2022-08-09 | 2022-11-29 | 2022-12-28 | 100
0 | EDBDSR1010 | BH-03 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - IFC | 10 | 2022-08-01 | 2022-08-15 | 2022-10-28 | 2022-11-10 | 64
0 | EDBDSR1110 | BH-03 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - IFA | 15 | 2022-07-26 | 2022-08-16 | 2022-12-29 | 2023-01-18 | 110
0 | EDBDSR1205 | BH-03 TOPSIDES LINEAR BLAST ANALYSIS REPORT - IFC | 15 | 2022-08-02 | 2022-08-23 | 2023-01-26 | 2023-02-15 | 125
0 | EDBDSR1045 | BH-03 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - ICR | 20 | 2022-07-26 | 2022-08-23 | 2022-12-15 | 2023-01-11 | 100
0 | EDBDSR1100 | BH-03 HELIDECK DESIGN REPORT - IFC | 15 | 2022-08-09 | 2022-08-30 | 2022-12-20 | 2023-01-09 | 93
0 | EDBDSR1160 | BH-03 TOPSIDES LOADOUT ANALYSIS REPORT - IFC | 15 | 2022-08-09 | 2022-08-30 | 2023-03-08 | 2023-03-28 | 149
0 | EDBDSR1020 | BH-03 JACKET INPLACE ANALYSIS REPORT - IFA | 15 | 2022-08-09 | 2022-08-30 | 2023-01-30 | 2023-02-17 | 122
0 | EDBDSR1185 | BH-03 TOPSIDE MISCELLANEOUS DESIGN REPORT - IFA | 15 | 2022-08-09 | 2022-08-30 | 2023-02-02 | 2023-02-22 | 125
0 | EDBDSR1085 | BH-03 TOPSIDE JOINT DESIGN REPORT - IFC | 15 | 2022-08-09 | 2022-08-30 | 2022-11-04 | 2022-11-24 | 63
0 | EDBDSR1145 | BH-03 TOPSIDES LIFT ANALYSES REPORT - IFC | 15 | 2022-08-15 | 2022-09-05 | 2023-02-15 | 2023-03-07 | 130
0 | EDBDSR1175 | BH-03 TOPSIDES TRANSPORTATION ANALYSES REPORT - IFC | 15 | 2022-08-16 | 2022-09-06 | 2023-03-08 | 2023-03-28 | 144
0 | EDBDSR1060 | BH-03 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - ICR | 20 | 2022-08-09 | 2022-09-06 | 2022-12-29 | 2023-01-25 | 100
0 | EDBDSR1035 | BH-03 JACKET PUSHOVER ANALYSIS REPORT- IFA | 15 | 2022-08-23 | 2022-09-13 | 2023-02-09 | 2023-03-01 | 120
0 | EDBDSR1120 | BH-03 JACKET MISCELLANEOUS DESIGN REPORT - ICR | 20 | 2022-08-23 | 2022-09-20 | 2023-01-12 | 2023-02-08 | 100
0 | EDBDSR1115 | BH-03 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - IFC | 15 | 2022-08-30 | 2022-09-20 | 2023-02-02 | 2023-02-22 | 110
0 | EDBDSR1050 | BH-03 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - IFA | 15 | 2022-09-06 | 2022-09-27 | 2023-02-16 | 2023-03-08 | 115
0 | EDBDSR1190 | BH-03 TOPSIDE MISCELLANEOUS DESIGN REPORT - IFC | 15 | 2022-09-13 | 2022-10-04 | 2023-03-09 | 2023-03-29 | 125
0 | EDBDSR1025 | BH-03 JACKET INPLACE ANALYSIS REPORT - IFC | 15 | 2022-09-13 | 2022-10-04 | 2023-03-08 | 2023-03-28 | 124
0 | EDBDSR1065 | BH-03 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - IFA | 15 | 2022-09-20 | 2022-10-11 | 2023-02-23 | 2023-03-15 | 110
0 | EDBDSR1040 | BH-03 JACKET PUSHOVER ANALYSIS REPORT - IFC | 15 | 2022-09-27 | 2022-10-18 | 2023-03-16 | 2023-04-05 | 120
0 | EDBDSR1125 | BH-03 JACKET MISCELLANEOUS DESIGN REPORT - IFA | 15 | 2022-10-04 | 2022-10-25 | 2023-02-23 | 2023-03-15 | 100
0 | EDBDSR1055 | BH-03 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - IFC | 15 | 2022-10-11 | 2022-11-01 | 2023-03-23 | 2023-04-12 | 115
0 | EDBDSR1070 | BH-03 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - IFC | 15 | 2022-10-25 | 2022-11-15 | 2023-03-30 | 2023-04-19 | 110
0 | EDBDSR1130 | BH-03 JACKET MISCELLANEOUS DESIGN REPORT - IFC | 15 | 2022-11-08 | 2022-11-29 | 2023-03-30 | 2023-04-19 | 100
DRAWINGS |  |  | 186 | 2022-04-22 | 2023-01-19 | 2022-08-19 | 2023-06-05 | 96
GENERAL |  |  | 165 | 2022-04-22 | 2022-12-21 | 2022-11-22 | 2023-04-27 | 90
0 | EDBGSR1000 | BH-03 DRAWING INDEX - ICR | 15 | 2022-04-22 | 2022-05-18 | 2022-11-22 | 2022-12-14 | 146
0 | EDBGSR1002 | BH-03 DRAWING INDEX - IFA | 15 | 2022-06-07 | 2022-06-28 | 2022-12-29 | 2023-01-18 | 142
0 | EDBGSR1005 | BH-03 DRAWING INDEX - IFC | 15 | 2022-11-28 | 2022-12-21 | 2023-04-05 | 2023-04-27 | 90
PRIMARY |  |  | 114 | 2022-05-19 | 2022-10-31 | 2022-08-19 | 2023-04-10 | 114
0 | EDBGSR1025 | BH-03 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-08-22 | 2022-09-16 | 64
0 | EDBGSR1010 | BH-03 MAIN DECK PRIMARY FRAMING PLAN EL(+) 15.000 - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-08-19 | 2022-09-15 | 63
0 | EDBGSR1040 | BH-03 DECK ELEVATION ROW-1 & 2 - ICR | 20 | 2022-05-26 | 2022-06-23 | 2022-08-29 | 2022-09-23 | 64
0 | EDBGSR1055 | BH-03 DECK ELEVATION ROW-A & B - ICR | 20 | 2022-05-26 | 2022-06-23 | 2022-08-29 | 2022-09-23 | 64
0 | EDBGSR1085 | BH-03 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 9.000- ICR | 20 | 2022-05-30 | 2022-06-27 | 2022-08-31 | 2022-09-27 | 64
0 | EDBGSR1100 | BH-03 ACCESS PLATFORM FRAMING PLAN EL(+) 18.000 - ICR | 20 | 2022-05-30 | 2022-06-27 | 2022-09-02 | 2022-09-29 | 66
0 | EDBGSR1070 | BH-03 DECK SECTIONS - ICR | 20 | 2022-05-30 | 2022-06-27 | 2022-08-31 | 2022-09-27 | 64
0 | EDBGSR1115 | BH-03 MEZZANINE DECK FRAMING PLAN EL(+) 21.000 - ICR | 20 | 2022-06-06 | 2022-07-04 | 2022-09-09 | 2022-10-06 | 66
0 | EDBGSR1130 | BH-03 WEATHER DECK FRAMING PLAN EL(+) 25.500 - ICR | 20 | 2022-06-13 | 2022-07-14 | 2022-09-16 | 2022-10-13 | 66
0 | EDBGSR1145 | BH-03 - HELIDECK FRAMING PLAN AT EL. (+) 32.300 - ICR | 20 | 2022-06-20 | 2022-07-21 | 2022-10-21 | 2022-11-17 | 86
0 | EDBGSR1160 | BH-03 DECK LEG STABBING GUIDE DETAILS - ICR | 20 | 2022-06-23 | 2022-07-26 | 2023-01-03 | 2023-01-30 | 133
0 | EDBGSR1030 | BH-03 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - IFA | 15 | 2022-06-30 | 2022-07-26 | 2022-10-07 | 2022-10-27 | 68
0 | EDBGSR1015 | BH-03 MAIN DECK PRIMARY FRAMING PLAN EL(+) 15.000- IFA. | 15 | 2022-06-30 | 2022-07-26 | 2022-09-30 | 2022-10-20 | 63
0 | EDBGSR1045 | BH-03 DECK ELEVATION ROW-1 & 2 - IFA | 15 | 2022-07-07 | 2022-08-02 | 2022-10-14 | 2022-11-03 | 68
0 | EDBGSR1060 | BH-03 DECK ELEVATION ROW-A & B - IFA | 15 | 2022-07-07 | 2022-08-02 | 2022-10-28 | 2022-11-17 | 78
0 | EDBGSR1090 | BH-03 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 9.000 - IFA | 15 | 2022-07-14 | 2022-08-04 | 2022-10-12 | 2022-11-01 | 64
0 | EDBGSR1105 | BH-03 ACCESS PLATFORM FRAMING PLAN EL(+) 18.000 - IFA | 15 | 2022-07-14 | 2022-08-04 | 2022-10-28 | 2022-11-17 | 76
0 | EDBGSR1075 | BH-03 DECK SECTIONS - IFA | 15 | 2022-07-14 | 2022-08-04 | 2022-10-28 | 2022-11-17 | 76
0 | EDBGSR1120 | BH-03 MEZZANINE DECK FRAMING PLAN EL(+) 21.000 - IFA | 15 | 2022-07-21 | 2022-08-11 | 2022-10-21 | 2022-11-10 | 66
0 | EDBGSR1135 | BH-03 WEATHER DECK FRAMING PLAN EL(+) 25.500 - IFA | 15 | 2022-07-28 | 2022-08-18 | 2022-10-28 | 2022-11-17 | 66
0 | EDBGSR1150 | BH-03 - HELIDECK FRAMING PLAN AT EL. (+) 32.300 - IFA | 15 | 2022-08-04 | 2022-08-25 | 2022-12-06 | 2022-12-26 | 86
0 | EDBGSR1165 | BH-03 DECK LEG STABBING GUIDE DETAILS - IFA | 15 | 2022-08-09 | 2022-08-30 | 2023-02-14 | 2023-03-06 | 133
0 | EDBGSR1020 | BH-03 MAIN DECK PRIMARY FRAMING PLAN EL(+) 15.000 - IFC | 15 | 2022-08-11 | 2022-09-01 | 2022-11-04 | 2022-11-24 | 61
0 | EDBGSR1050 | BH-03 DECK ELEVATION ROW-1 & 2 - IFC | 15 | 2022-08-16 | 2022-09-06 | 2022-11-18 | 2022-12-12 | 68
0 | EDBGSR1065 | BH-03 DECK ELEVATION ROW-A & B - IFC | 15 | 2022-08-16 | 2022-09-06 | 2022-12-06 | 2022-12-26 | 78
0 | EDBGSR1035 | BH-03 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - IFC | 15 | 2022-08-18 | 2022-09-08 | 2022-11-11 | 2022-12-05 | 61
0 | EDBGSR1095 | BH-03 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 9.000 - IFC | 15 | 2022-08-18 | 2022-09-08 | 2022-11-16 | 2022-12-08 | 64
0 | EDBGSR1110 | BH-03 ACCESS PLATFORM FRAMING PLAN EL(+) 18.000 - IFC | 15 | 2022-08-18 | 2022-09-08 | 2022-12-06 | 2022-12-26 | 76
0 | EDBGSR1080 | BH-03 DECK SECTIONS - IFC | 15 | 2022-08-18 | 2022-09-08 | 2022-12-06 | 2022-12-26 | 76
0 | EDBGSR1125 | BH-03 MEZZANINE DECK FRAMING PLAN EL(+) 21.000 - IFC | 15 | 2022-08-25 | 2022-09-15 | 2022-11-25 | 2022-12-19 | 66
0 | EDBGSR1140 | BH-03 WEATHER DECK FRAMING PLAN EL(+) 25.500 - IFC | 15 | 2022-09-01 | 2022-09-22 | 2022-12-06 | 2022-12-26 | 66
0 | EDBGSR1170 | BH-03 DECK LEG STABBING GUIDE DETAILS - IFC | 15 | 2022-09-13 | 2022-10-04 | 2023-03-21 | 2023-04-10 | 133
0 | EDBGSR1155 | BH-03 - HELIDECK FRAMING PLAN AT EL. (+) 32.300 - IFC | 15 | 2022-10-10 | 2022-10-31 | 2023-01-10 | 2023-01-30 | 64
SECONDARY |  |  | 119 | 2022-06-02 | 2022-11-21 | 2022-09-07 | 2023-04-03 | 94
0 | EDBGSR1175 | BH-03 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - ICR | 20 | 2022-06-02 | 2022-06-30 | 2022-09-07 | 2022-10-04 | 66
0 | EDBGSR1235 | BH-03 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - ICR | 20 | 2022-06-09 | 2022-07-07 | 2022-09-14 | 2022-10-11 | 66
0 | EDBGSR1190 | BH-03 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - ICR | 20 | 2022-06-09 | 2022-07-07 | 2022-09-14 | 2022-10-11 | 66
0 | EDBGSR1265 | BH-03 ACCESSPLATFORM PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 18.000 - ICR | 20 | 2022-06-16 | 2022-07-19 | 2022-09-21 | 2022-10-18 | 66
0 | EDBGSR1250 | BH-03 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - ICR | 20 | 2022-06-16 | 2022-07-19 | 2022-09-21 | 2022-10-18 | 66
0 | EDBGSR1205 | BH-03 MEZZANINE DECK SECONDARY FRAMING PLAN EL(+) 21.000 - ICR | 20 | 2022-06-16 | 2022-07-19 | 2022-09-21 | 2022-10-18 | 66
0 | EDBGSR1280 | BH-03 MEZZANINE DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-09-28 | 2022-10-25 | 66
0 | EDBGSR2020 | BH-03 CELLAR DECK INFILL BEAM FRAMING PLAN AT EL(+) 9.000 T.O.S. - ICR | 15 | 2022-06-30 | 2022-07-26 | 2022-10-07 | 2022-10-27 | 68
0 | EDBGSR2050 | BH-03 MAIN DECK INFILL BEAM FRAMING PLAN AT EL(+) 15.000 T.O.S. - ICR | 15 | 2022-06-30 | 2022-07-26 | 2022-10-07 | 2022-10-27 | 68
0 | EDBGSR1220 | BH-03 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - ICR | 20 | 2022-06-27 | 2022-07-28 | 2022-10-21 | 2022-11-17 | 81
0 | EDBGSR2080 | BH-03 MEZZANINE DECK INFILL BEAM FRAMING PLAN AT EL(+) 21.000 T.O.S. - ICR | 15 | 2022-07-07 | 2022-08-02 | 2022-10-21 | 2022-11-10 | 73
0 | EDBGSR1295 | BH-03 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - ICR | 20 | 2022-07-04 | 2022-08-04 | 2022-10-28 | 2022-11-24 | 81
0 | EDBGSR1180 | BH-03 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - IFA | 15 | 2022-07-19 | 2022-08-09 | 2022-10-28 | 2022-11-17 | 73
0 | EDBGSR1310 | BH-03 HELIDECK PLATING DETAILS - ICR | 20 | 2022-07-14 | 2022-08-11 | 2022-11-11 | 2022-12-12 | 86
0 | EDBGSR2110 | BH-03 WEATHER DECK INFILL BEAM FRAMING PLAN AT EL(+) 25.500 T.O.S. - ICR | 15 | 2022-07-21 | 2022-08-11 | 2022-11-22 | 2022-12-14 | 88
0 | EDBGSR1240 | BH-03 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - IFA | 15 | 2022-07-26 | 2022-08-16 | 2022-11-04 | 2022-11-24 | 73
0 | EDBGSR1195 | BH-03 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - IFA | 15 | 2022-07-26 | 2022-08-16 | 2022-11-04 | 2022-11-24 | 73
0 | EDBGSR1325 | BH-03 HELIDECK SAFETY NET LAYOUT & DETAILS - ICR | 20 | 2022-07-21 | 2022-08-18 | 2022-11-18 | 2022-12-19 | 86
0 | EDBGSR1255 | BH-03 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - IFA | 15 | 2022-08-02 | 2022-08-23 | 2022-11-18 | 2022-12-12 | 78
0 | EDBGSR1270 | BH-03 ACCESSPLATFORM PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 18.000 - IFA | 15 | 2022-08-02 | 2022-08-23 | 2022-11-18 | 2022-12-12 | 78
0 | EDBGSR1210 | BH-03 MEZZANINE DECK SECONDARY FRAMING PLAN EL(+) 21.000 - IFA | 15 | 2022-08-02 | 2022-08-23 | 2022-11-09 | 2022-11-29 | 71
0 | EDBGSR1285 | BH-03 MEZZANINE DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - IFA | 15 | 2022-08-09 | 2022-08-30 | 2022-11-09 | 2022-11-29 | 66
0 | EDBGSR2030 | BH-03 CELLAR DECK INFILL BEAM FRAMING PLAN AT EL(+) 9.000 T.O.S. - IFA | 15 | 2022-08-09 | 2022-08-30 | 2022-11-18 | 2022-12-12 | 73
0 | EDBGSR2060 | BH-03 MAIN DECK INFILL BEAM FRAMING PLAN AT EL(+) 15.000 T.O.S. - IFA | 15 | 2022-08-09 | 2022-08-30 | 2022-11-11 | 2022-12-05 | 68
0 | EDBGSR1225 | BH-03 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - IFA | 15 | 2022-08-11 | 2022-09-01 | 2022-12-08 | 2022-12-28 | 83
0 | EDBGSR2090 | BH-03 MEZZANINE DECK INFILL BEAM FRAMING PLAN AT EL(+) 21.000 T.O.S. - IFA | 15 | 2022-08-16 | 2022-09-06 | 2022-11-25 | 2022-12-19 | 73
0 | EDBGSR1300 | BH-03 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - IFA | 15 | 2022-08-18 | 2022-09-08 | 2022-12-13 | 2023-01-02 | 81
0 | EDBGSR1185 | BH-03 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - IFC | 10 | 2022-08-25 | 2022-09-08 | 2022-12-06 | 2022-12-19 | 71
0 | EDBGSR1200 | BH-03 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - IFC | 10 | 2022-08-30 | 2022-09-13 | 2022-12-13 | 2022-12-26 | 73
0 | EDBGSR1315 | BH-03 HELIDECK PLATING DETAILS - IFA | 15 | 2022-08-25 | 2022-09-15 | 2023-02-07 | 2023-02-27 | 116
0 | EDBGSR2120 | BH-03 WEATHER DECK INFILL BEAM FRAMING PLAN AT EL(+) 25.500 T.O.S. - IFA | 15 | 2022-08-25 | 2022-09-15 | 2022-12-29 | 2023-01-18 | 88
0 | EDBGSR1330 | BH-03 HELIDECK SAFETY NET LAYOUT & DETAILS - IFA | 15 | 2022-09-01 | 2022-09-22 | 2023-01-03 | 2023-01-23 | 86
0 | EDBGSR1215 | BH-03 MEZZANINE DECK SECONDARY FRAMING PLAN EL(+) 21.000 - IFC | 15 | 2022-09-06 | 2022-09-27 | 2022-12-16 | 2023-01-05 | 71
0 | EDBGSR2040 | BH-03 CELLAR DECK INFILL BEAM FRAMING PLAN AT EL(+) 9.000 T.O.S. - IFC | 10 | 2022-09-13 | 2022-09-27 | 2022-12-27 | 2023-01-09 | 73
0 | EDBGSR2070 | BH-03 MAIN DECK INFILL BEAM FRAMING PLAN AT EL(+) 15.000 T.O.S. - IFC | 10 | 2022-09-13 | 2022-09-27 | 2022-12-20 | 2023-01-02 | 68
0 | EDBGSR1260 | BH-03 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - IFC | 15 | 2022-09-08 | 2022-09-29 | 2022-12-27 | 2023-01-16 | 76
0 | EDBGSR1245 | BH-03 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - IFC | 15 | 2022-09-08 | 2022-09-29 | 2022-12-13 | 2023-01-02 | 66
0 | EDBGSR1275 | BH-03 ACCESSPLATFORM PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 18.000 - IFC | 15 | 2022-09-08 | 2022-09-29 | 2022-12-27 | 2023-01-16 | 76
0 | EDBGSR1290 | BH-03 MEZZANINE DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - IFC | 15 | 2022-09-13 | 2022-10-04 | 2022-12-16 | 2023-01-05 | 66
0 | EDBGSR2100 | BH-03 MEZZANINE DECK INFILL BEAM FRAMING PLAN AT EL(+) 21.000 T.O.S. - IFC | 10 | 2022-09-20 | 2022-10-04 | 2023-01-03 | 2023-01-16 | 73
0 | EDBGSR1230 | BH-03 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - IFC | 15 | 2022-09-15 | 2022-10-06 | 2023-01-12 | 2023-02-01 | 83
0 | EDBGSR1305 | BH-03 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - IFC | 15 | 2022-09-22 | 2022-10-13 | 2023-01-17 | 2023-02-06 | 81
0 | EDBGSR1320 | BH-03 HELIDECK PLATING DETAILS - IFC | 15 | 2022-09-29 | 2022-10-20 | 2023-03-14 | 2023-04-03 | 116
0 | EDBGSR2130 | BH-03 WEATHER DECK INFILL BEAM FRAMING PLAN AT EL(+) 25.500 T.O.S. - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-02-02 | 2023-02-15 | 83
0 | EDBGSR1335 | BH-03 HELIDECK SAFETY NET LAYOUT & DETAILS - IFC | 15 | 2022-10-31 | 2022-11-21 | 2023-02-07 | 2023-02-27 | 69
TERTAIRY |  |  | 140 | 2022-06-30 | 2023-01-19 | 2022-09-29 | 2023-06-05 | 96
0 | EDBGSR2135 | BH-03 CELLAR DECK LOADING DIAGRAM - ICR | 15 | 2022-06-30 | 2022-07-26 | 2022-11-07 | 2022-11-25 | 89
0 | EDBGSR2160 | BH-03 MAIN DECK LOADING DIAGRAM - ICR | 15 | 2022-07-07 | 2022-08-02 | 2022-11-14 | 2022-12-06 | 89
0 | EDBGSR1400 | BH-03 - DECK LIFTING PADEYE DETAILS - ICR | 20 | 2022-07-01 | 2022-08-03 | 2022-09-29 | 2022-10-26 | 61
0 | EDBGSR2190 | BH-03 MEZZANINE DECK LOADING DIAGRAM - ICR | 15 | 2022-07-19 | 2022-08-09 | 2022-11-21 | 2022-12-13 | 89
0 | EDBGSR1415 | BH-03 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - ICR | 20 | 2022-07-13 | 2022-08-10 | 2022-10-06 | 2022-11-02 | 61
0 | EDBGSR2220 | BH-03 WEATHER DECK LOADING DIAGRAM - ICR | 15 | 2022-07-26 | 2022-08-16 | 2022-11-28 | 2022-12-20 | 89
0 | EDBGSR1430 | BH-03 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS- ICR | 20 | 2022-07-20 | 2022-08-17 | 2022-10-13 | 2022-11-09 | 61
0 | EDBGSR2250 | BH-03 HELIDECK LOADING DIAGRAM - ICR | 15 | 2022-08-02 | 2022-08-23 | 2022-12-07 | 2022-12-27 | 89
0 | EDBGSR2310 | BH-03 PIPE SUPPORT DETAILS - ICR | 15 | 2022-08-02 | 2022-08-23 | 2022-12-28 | 2023-01-17 | 104
0 | EDBGSR1445 | BH-03 MEZZANINE DECK EQUIPMENT SUPPORT GA AND DETAILS - ICR | 20 | 2022-07-27 | 2022-08-24 | 2022-10-20 | 2022-11-16 | 61
0 | EDBGSR1460 | BH-03 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - ICR | 20 | 2022-07-27 | 2022-08-24 | 2022-10-20 | 2022-11-16 | 61
0 | EDBGSR2140 | BH-03 CELLAR DECK LOADING DIAGRAM - IFA | 15 | 2022-08-09 | 2022-08-30 | 2023-02-01 | 2023-02-21 | 124
0 | EDBGSR2170 | BH-03 MAIN DECK LOADING DIAGRAM - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-02-01 | 2023-02-21 | 119
0 | EDBGSR1475 | BH-03 REMOVABLE HATCH DETAILS- ICR | 20 | 2022-08-10 | 2022-09-07 | 2022-11-03 | 2022-11-30 | 61
0 | EDBGSR1490 | BH-03 DECK PENETRATION AND DETAILS- ICR | 20 | 2022-08-10 | 2022-09-07 | 2022-11-03 | 2022-11-30 | 61
0 | EDBGSR2200 | BH-03 MEZZANINE DECK LOADING DIAGRAM - IFA | 15 | 2022-08-23 | 2022-09-13 | 2023-02-01 | 2023-02-21 | 114
0 | EDBGSR2280 | BH-03 PULLING POST & MATERIAL HANDLING PADEYES - ICR | 15 | 2022-08-23 | 2022-09-13 | 2022-12-28 | 2023-01-17 | 89
0 | EDBGSR1420 | BH-03 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-24 | 2022-09-14 | 2023-01-19 | 2023-02-08 | 104
0 | EDBGSR2230 | BH-03 WEATHER DECK LOADING DIAGRAM - IFA | 15 | 2022-08-30 | 2022-09-20 | 2023-02-01 | 2023-02-21 | 109
0 | EDBGSR1535 | BH-03 WEST STAIR TOWER ELEVATIONS- ICR | 20 | 2022-08-24 | 2022-09-21 | 2022-11-17 | 2022-12-16 | 61
0 | EDBGSR1435 | BH-03 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-31 | 2022-09-21 | 2023-01-19 | 2023-02-08 | 99
0 | EDBGSR1405 | BH-03 - DECK LIFTING PADEYE DETAILS - IFA | 15 | 2022-09-02 | 2022-09-23 | 2023-02-01 | 2023-02-21 | 106
0 | EDBGSR2260 | BH-03 HELIDECK LOADING DIAGRAM - IFA | 15 | 2022-09-06 | 2022-09-27 | 2023-02-01 | 2023-02-21 | 104
0 | EDBGSR2320 | BH-03 PIPE SUPPORT DETAILS - IFA | 15 | 2022-09-06 | 2022-09-27 | 2023-02-01 | 2023-02-21 | 104
0 | EDBGSR1550 | BH-03 WEST STAIR TOWER LAYOUT PLAN- ICR | 20 | 2022-08-31 | 2022-09-28 | 2022-11-24 | 2022-12-23 | 61
0 | EDBGSR1450 | BH-03 MEZZANINE DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-09-07 | 2022-09-28 | 2023-01-26 | 2023-02-15 | 99
0 | EDBGSR1465 | BH-03 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-09-07 | 2022-09-28 | 2023-02-02 | 2023-02-22 | 104
0 | EDBGSR2150 | BH-03 CELLAR DECK LOADING DIAGRAM - IFC | 15 | 2022-09-13 | 2022-10-04 | 2023-03-08 | 2023-03-28 | 124
0 | EDBGSR2180 | BH-03 MAIN DECK LOADING DIAGRAM - IFC | 15 | 2022-09-20 | 2022-10-11 | 2023-03-08 | 2023-03-28 | 119
0 | EDBGSR1505 | BH-03 - VENT BOOM GA AND DETAILS - ICR | 20 | 2022-09-14 | 2022-10-12 | 2022-12-26 | 2023-01-20 | 71
0 | EDBGSR1480 | BH-03 REMOVABLE HATCH DETAILS - IFA | 15 | 2022-09-21 | 2022-10-12 | 2023-03-14 | 2023-04-03 | 122
0 | EDBGSR1495 | BH-03 DECK PENETRATION AND DETAIL - IFA | 15 | 2022-09-21 | 2022-10-12 | 2023-01-04 | 2023-01-24 | 73
0 | EDBGSR1855 | BH-03 - WEST/ EAST SIDE STAIR DETAILS - ICR | 20 | 2022-09-14 | 2022-10-12 | 2022-12-12 | 2023-01-06 | 61
0 | EDBGSR2210 | BH-03 MEZZANINE DECK LOADING DIAGRAM - IFC | 15 | 2022-09-27 | 2022-10-18 | 2023-03-08 | 2023-03-28 | 114
0 | EDBGSR2290 | BH-03 PULLING POST & MATERIAL HANDLING PADEYES - IFA | 15 | 2022-09-27 | 2022-10-18 | 2023-02-01 | 2023-02-21 | 89
0 | EDBGSR1520 | BH-03 - MAIN DECK / CELLAR DECK MONORAIL AND DETAILS- ICR | 20 | 2022-09-21 | 2022-10-19 | 2023-01-27 | 2023-02-23 | 90
0 | EDBGSR2240 | BH-03 WEATHER DECK LOADING DIAGRAM - IFC | 15 | 2022-10-04 | 2022-10-25 | 2023-03-08 | 2023-03-28 | 109
0 | EDBGSR1595 | BH-03 STAIR FROM WEATHER DECK TO HELIDECK - ICR | 20 | 2022-09-28 | 2022-10-26 | 2022-12-26 | 2023-01-20 | 61
0 | EDBGSR1640 | BH-03 HELIDECK DRAIN GUTTER GA AND DETAILS - ICR | 10 | 2022-10-12 | 2022-10-26 | 2023-01-09 | 2023-01-20 | 61
0 | EDBGSR2350 | BH-03 WEST STAIR TOWER LAYOUT PLAN- IFA | 10 | 2022-10-12 | 2022-10-26 | 2023-03-17 | 2023-03-30 | 110
0 | EDBGSR2270 | BH-03 HELIDECK LOADING DIAGRAM - IFC | 15 | 2022-10-11 | 2022-11-01 | 2023-03-08 | 2023-03-28 | 104
0 | EDBGSR2330 | BH-03 PIPE SUPPORT DETAILS - IFC | 15 | 2022-10-11 | 2022-11-01 | 2023-03-08 | 2023-03-28 | 104
0 | EDBGSR1700 | BH-03 - HELIDECK MARKING PLAN - ICR | 20 | 2022-10-05 | 2022-11-02 | 2023-01-18 | 2023-02-14 | 73
0 | EDBGSR1715 | BH-03 IDENTIFICATION BOARD DRAWING- ICR | 20 | 2022-10-05 | 2022-11-02 | 2023-01-18 | 2023-02-14 | 73
0 | EDBGSR1485 | BH-03 REMOVABLE HATCH DETAILS - IFC | 15 | 2022-10-12 | 2022-11-02 | 2023-04-04 | 2023-04-26 | 122
0 | EDBGSR1500 | BH-03 DECK PENETRATION AND DETAIL - IFC | 15 | 2022-10-12 | 2022-11-02 | 2023-01-25 | 2023-02-14 | 73
0 | EDBGSR1655 | BH-03 DECK DAVIT GA AND DETAILS - ICR | 10 | 2022-10-19 | 2022-11-02 | 2023-01-16 | 2023-01-27 | 61
0 | EDBGSR1730 | BH-03 OFFSHORE INSTALLED FRAMING AND GRATING - ICR | 10 | 2022-10-19 | 2022-11-02 | 2023-02-08 | 2023-02-21 | 78
0 | EDBGSR1760 | BH-03 HELICOPTER TIE DOWN DETAILS - ICR | 10 | 2022-10-19 | 2022-11-02 | 2023-02-01 | 2023-02-14 | 73
0 | EDBGSR1775 | BH-03 SWING ROPE DETAILS DRAWING - ICR | 10 | 2022-10-19 | 2022-11-02 | 2023-02-01 | 2023-02-14 | 73
0 | EDBGSR2340 | BH-03 WEST STAIR TOWER ELEVATIONS- IFA | 20 | 2022-10-05 | 2022-11-02 | 2023-02-24 | 2023-03-23 | 100
0 | EDBGSR2400 | BH-03 - WEST/ EAST SIDE STAIR DETAILS - IFA | 15 | 2022-10-12 | 2022-11-02 | 2023-03-15 | 2023-04-04 | 108
0 | EDBGSR1805 | BH-03 WEATHER DECK INSTRUMENTAION CABINET SUNSHADE AND DETAILS - ICR | 10 | 2022-10-24 | 2022-11-07 | 2023-01-19 | 2023-02-01 | 61
0 | EDBGSR1610 | BH-03 ACCESS PLATFORM - ICR | 20 | 2022-10-12 | 2022-11-09 | 2023-01-09 | 2023-02-03 | 61
0 | EDBGSR1625 | BH-03 LADDER - IRC | 20 | 2022-10-12 | 2022-11-09 | 2023-01-09 | 2023-02-03 | 61
0 | EDBGSR1670 | BH-03 - STRUCTURAL MISCELLANEOUS DETAIL - ICR | 20 | 2022-10-12 | 2022-11-09 | 2023-01-09 | 2023-02-03 | 61
0 | EDBGSR1745 | BH-03 STAIR FROM JACKET WALKWAY TO CELLAR DECK - ICR | 10 | 2022-10-26 | 2022-11-09 | 2023-02-15 | 2023-02-28 | 78
0 | EDBGSR1510 | BH-03 - VENT BOOM GA AND DETAILS - IFA | 15 | 2022-10-26 | 2022-11-16 | 2023-03-31 | 2023-04-20 | 110
0 | EDBGSR2300 | BH-03 PULLING POST & MATERIAL HANDLING PADEYES - IFC | 15 | 2022-11-01 | 2022-11-22 | 2023-03-08 | 2023-03-28 | 89
0 | EDBGSR1525 | BH-03 - MAIN DECK / CELLAR DECK MONORAIL AND DETAILS - IFA | 15 | 2022-11-02 | 2022-11-23 | 2023-03-10 | 2023-03-30 | 90
0 | EDBGSR1875 | BH-03 - WEST/ EAST SIDE STAIR DETAILS - IFC | 15 | 2022-11-02 | 2022-11-23 | 2023-04-05 | 2023-04-27 | 108
0 | EDBGSR1645 | BH-03 HELIDECK DRAIN GUTTER GA AND DETAILS - IFA | 15 | 2022-11-09 | 2022-11-30 | 2023-03-01 | 2023-03-21 | 78
0 | EDBGSR2360 | BH-03 STAIR FROM WEATHER DECK TO HELIDECK - IFA | 15 | 2022-11-09 | 2022-11-30 | 2023-03-10 | 2023-03-30 | 85
0 | EDBGSR1705 | BH-03 - HELIDECK MARKING PLAN - IFA | 15 | 2022-11-16 | 2022-12-09 | 2023-03-01 | 2023-03-21 | 73
0 | EDBGSR1720 | BH-03 IDENTIFICATION BOARD DRAWING - IFA | 15 | 2022-11-16 | 2022-12-09 | 2023-03-01 | 2023-03-21 | 73
0 | EDBGSR1660 | BH-03 DECK DAVIT GA AND DETAILS - IFA | 15 | 2022-11-16 | 2022-12-09 | 2023-02-28 | 2023-03-20 | 72
0 | EDBGSR1735 | BH-03 OFFSHORE INSTALLED FRAMING AND GRATING - IFA | 15 | 2022-11-16 | 2022-12-09 | 2023-03-08 | 2023-03-28 | 78
0 | EDBGSR1765 | BH-03 HELICOPTER TIE DOWN DETAILS - IFA | 15 | 2022-11-16 | 2022-12-09 | 2023-03-01 | 2023-03-21 | 73
0 | EDBGSR1780 | BH-03 SWING ROPE DETAILS DRAWING - IFA | 15 | 2022-11-16 | 2022-12-09 | 2023-03-01 | 2023-03-21 | 73
0 | EDBGSR2390 | BH-03 STAIR FROM JACKET WALKWAY TO CELLAR DECK - IFA | 10 | 2022-11-23 | 2022-12-09 | 2023-03-15 | 2023-03-28 | 78
0 | EDBGSR1440 | BH-03 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-21 | 2022-12-14 | 2023-02-23 | 2023-03-15 | 66
0 | EDBGSR1425 | BH-03 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-21 | 2022-12-14 | 2023-02-23 | 2023-03-15 | 66
0 | EDBGSR1810 | BH-03 WEATHER DECK INSTRUMENTAION CABINET SUNSHADE AND DETAILS - IFA | 15 | 2022-11-21 | 2022-12-14 | 2023-02-16 | 2023-03-08 | 61
0 | EDBGSR1560 | BH-03 WEST STAIR TOWER LAYOUT PLAN- IFC | 15 | 2022-11-23 | 2022-12-16 | 2023-04-14 | 2023-05-08 | 100
0 | EDBGSR1545 | BH-03 WEST STAIR TOWER ELEVATIONS- IFC | 20 | 2022-11-16 | 2022-12-16 | 2023-04-07 | 2023-05-08 | 100
0 | EDBGSR1675 | BH-03 - STRUCTURAL MISCELLANEOUS DETAIL - IFA | 15 | 2022-11-23 | 2022-12-16 | 2023-03-03 | 2023-03-23 | 70
0 | EDBGSR2370 | BH-03 ACCESS PLATFORM - IFA | 15 | 2022-11-23 | 2022-12-16 | 2023-04-10 | 2023-05-02 | 96
0 | EDBGSR2380 | BH-03 LADDER - IFA | 15 | 2022-11-23 | 2022-12-16 | 2023-04-10 | 2023-05-02 | 96
0 | EDBGSR1410 | BH-03 - DECK LIFTING PADEYE DETAILS - IFC | 15 | 2022-11-28 | 2022-12-21 | 2023-03-08 | 2023-03-28 | 70
0 | EDBGSR1455 | BH-03 MEZZANINE DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-28 | 2022-12-21 | 2023-03-02 | 2023-03-22 | 66
0 | EDBGSR1515 | BH-03 - VENT BOOM GA AND DETAILS - IFC | 15 | 2022-11-30 | 2022-12-23 | 2023-05-09 | 2023-05-29 | 110
0 | EDBGSR1530 | BH-03 - MAIN DECK / CELLAR DECK MONORAIL AND DETAILS - IFC | 10 | 2022-12-09 | 2022-12-23 | 2023-04-14 | 2023-05-01 | 90
0 | EDBGSR1470 | BH-03 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-12-07 | 2022-12-28 | 2023-03-09 | 2023-03-29 | 66
0 | EDBGSR1605 | BH-03 STAIR FROM WEATHER DECK TO HELIDECK - IFC | 15 | 2022-12-16 | 2023-01-06 | 2023-04-14 | 2023-05-08 | 85
0 | EDBGSR1650 | BH-03 HELIDECK DRAIN GUTTER GA AND DETAILS - IFC | 15 | 2022-12-16 | 2023-01-06 | 2023-04-05 | 2023-04-27 | 78
0 | EDBGSR1740 | BH-03 OFFSHORE INSTALLED FRAMING AND GRATING - IFC | 10 | 2022-12-23 | 2023-01-06 | 2023-04-12 | 2023-04-27 | 78
0 | EDBGSR1755 | BH-03 STAIR FROM JACKET WALKWAY TO CELLAR DECK - IFC | 10 | 2022-12-23 | 2023-01-06 | 2023-04-12 | 2023-04-27 | 78
0 | EDBGSR1710 | BH-03 - HELIDECK MARKING PLAN - IFC | 15 | 2022-12-23 | 2023-01-13 | 2023-04-05 | 2023-04-27 | 73
0 | EDBGSR1725 | BH-03 IDENTIFICATION BOARD DRAWING - IFC | 15 | 2022-12-23 | 2023-01-13 | 2023-04-05 | 2023-04-27 | 73
0 | EDBGSR1665 | BH-03 DECK DAVIT GA AND DETAILS - IFC | 15 | 2022-12-23 | 2023-01-13 | 2023-04-04 | 2023-04-26 | 72
0 | EDBGSR1770 | BH-03 HELICOPTER TIE DOWN DETAILS - IFC | 15 | 2022-12-23 | 2023-01-13 | 2023-04-05 | 2023-04-27 | 73
0 | EDBGSR1785 | BH-03 SWING ROPE DETAILS DRAWING - IFC | 15 | 2022-12-23 | 2023-01-13 | 2023-04-05 | 2023-04-27 | 73
0 | EDBGSR1815 | BH-03 WEATHER DECK INSTRUMENTAION CABINET SUNSHADE AND DETAILS - IFC | 15 | 2022-12-28 | 2023-01-18 | 2023-03-23 | 2023-04-12 | 61
0 | EDBGSR1620 | BH-03 ACCESS PLATFORM - IFC | 14 | 2022-12-30 | 2023-01-19 | 2023-05-17 | 2023-06-05 | 96
0 | EDBGSR1635 | BH-03 LADDER - IFC | 14 | 2022-12-30 | 2023-01-19 | 2023-05-17 | 2023-06-05 | 96
0 | EDBGSR1680 | BH-03 - STRUCTURAL MISCELLANEOUS DETAIL - IFC | 14 | 2022-12-30 | 2023-01-19 | 2023-04-07 | 2023-04-28 | 70
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-23 | 2023-01-17 | 2023-01-04 | 2023-04-27 | 71
0 | EDBGSR2000 | BH-03 STRUCTURAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-23 | 2022-10-21 | 2023-01-04 | 2023-01-31 | 71
0 | EDBGSR2005 | BH-03 STRUCTURAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-04 | 2022-12-06 | 2023-02-15 | 2023-03-14 | 71
0 | EDBGSR2010 | BH-03 STRUCTURAL MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-20 | 2023-01-17 | 2023-03-29 | 2023-04-27 | 71
NAVAL & ARCHITECTURE |  |  | 133 | 2022-04-22 | 2022-11-03 | 2022-07-29 | 2023-04-27 | 122
DOCUMENTS |  |  | 133 | 2022-04-22 | 2022-11-03 | 2022-07-29 | 2023-04-27 | 122
0 | EDBDNA1000 | BH-03 TOPSIDE -WEIGHT & COG CALCULATION - ICR | 20 | 2022-04-22 | 2022-05-25 | 2022-07-29 | 2022-08-25 | 64
0 | EDBDNA1020 | BH-3 JACKET-WEIGHT & COG CALCULATION- ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-10-18 | 2022-11-14 | 105
0 | EDBDNA1005 | BH-03 TOPSIDE -WEIGHT & COG CALCULATION - IFA | 10 | 2022-06-08 | 2022-06-22 | 2022-09-09 | 2022-09-22 | 64
0 | EDBDNA1010 | BH-03 TOPSIDE -WEIGHT & COG CALCULATION - IFC | 20 | 2022-07-06 | 2022-08-08 | 2022-10-07 | 2022-11-03 | 64
0 | EDBDNA1030 | BH-3 JACKET-WEIGHT & COG CALCULATION- IFA | 20 | 2022-08-30 | 2022-09-27 | 2023-02-20 | 2023-03-17 | 122
0 | EDBDNA1040 | BH-3 JACKET-WEIGHT & COG CALCULATION - IFC | 20 | 2022-10-06 | 2022-11-03 | 2023-03-29 | 2023-04-27 | 122
SATAH WHP 10 TOPSIDES |  |  | 367 | 2022-01-17 | 2023-01-19 | 2022-03-17 | 2023-08-17 | 211
PROCESS |  |  | 252 | 2022-01-17 | 2023-01-16 | 2022-03-17 | 2023-04-27 | 72
DOCUMENTS |  |  | 85 | 2022-03-08 | 2022-07-13 | 2022-05-10 | 2023-01-23 | 137
PROCESS SIMULATIONS & REPORTS |  |  | 62 | 2022-03-15 | 2022-06-14 | 2022-06-22 | 2022-11-08 | 103
0 | EDSDPR1000 | ALARM AND TRIP SCHEDULE (SATAH WHP-10) - ICR | 16 | 2022-03-15 | 2022-04-06 | 2022-06-22 | 2022-07-18 | 68
0 | EDSDPR1005 | ALARM AND TRIP SCHEDULE (SATAH WHP-10) - IFA | 10 | 2022-04-20 | 2022-05-09 | 2022-09-20 | 2022-10-03 | 103
0 | EDSDPR1010 | ALARM AND TRIP SCHEDULE (SATAH WHP-10) - IFC | 16 | 2022-05-23 | 2022-06-14 | 2022-10-18 | 2022-11-08 | 103
PROCESS LISTS |  |  | 65 | 2022-03-08 | 2022-06-10 | 2022-06-08 | 2022-11-21 | 114
0 | EDSDPR1015 | EQUIPMENT LIST (SATAH WHP-10) - ICR | 10 | 2022-03-08 | 2022-03-22 | 2022-06-08 | 2022-06-21 | 63
0 | EDSDPR1030 | LINE LIST (SATAH WHP-10) - ICR | 10 | 2022-03-15 | 2022-03-29 | 2022-07-06 | 2022-07-22 | 78
0 | EDSDPR1020 | EQUIPMENT LIST (SATAH WHP-10) - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-07-06 | 2022-07-22 | 63
0 | EDSDPR1035 | LINE LIST (SATAH WHP-10) - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-08-25 | 2022-09-07 | 91
0 | EDSDPR1025 | EQUIPMENT LIST (SATAH WHP-10) - IFC | 15 | 2022-05-06 | 2022-05-27 | 2022-11-01 | 2022-11-21 | 124
0 | EDSDPR1040 | LINE LIST (SATAH WHP-10) - IFC | 20 | 2022-05-13 | 2022-06-10 | 2022-09-22 | 2022-10-19 | 91
PREPARATION OF DATASHEETS |  |  | 85 | 2022-03-08 | 2022-07-13 | 2022-05-10 | 2023-01-23 | 137
0 | EDSDPR1240 | PROCESS DATA SHEET DRAIN DRUM PUMP (SATAH WHP-10) - ICR | 5 | 2022-03-08 | 2022-03-15 | 2022-05-10 | 2022-05-16 | 42
0 | EDSDPR1270 | PROCESS DATA SHEET PIG LAUNCHER (SATAH WHP-10) - ICR | 4 | 2022-03-09 | 2022-03-15 | 2022-05-19 | 2022-05-24 | 48
0 | EDSDPR1045 | PROCESS DATA SHEET CHOKE VALVES (SATAH WHP-10) - ICR | 5 | 2022-03-15 | 2022-03-22 | 2022-05-18 | 2022-05-24 | 43
0 | EDSDPR1255 | PROCESS DATA SHEET VENT / DRAIN DRUM (SATAH WHP-10) - ICR | 5 | 2022-03-15 | 2022-03-22 | 2022-05-18 | 2022-05-24 | 43
0 | EDSDPR1075 | PROCESS DATA SHEET MOTOR OPERATED VALVES (SATAH WHP-10) - ICR | 5 | 2022-03-15 | 2022-03-22 | 2022-05-18 | 2022-05-24 | 43
0 | EDSDPR1090 | PROCESS DATASHEET SHUTDOWN VALVES (SATAH WHP-10) - ICR | 5 | 2022-03-17 | 2022-03-24 | 2022-05-20 | 2022-05-26 | 43
0 | EDSDPR1120 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (SATAH WHP-10) - ICR | 5 | 2022-03-21 | 2022-03-28 | 2022-06-10 | 2022-06-16 | 56
0 | EDSDPR1105 | PROCESS DATASHEET IRCD (SATAH WHP-10) - ICR | 5 | 2022-03-21 | 2022-03-28 | 2022-05-26 | 2022-06-01 | 45
0 | EDSDPR1060 | PROCESS DATA SHEET WET GAS METER (SATAH WHP-10) - MULTI PHASE FLOW METER - ICR | 5 | 2022-03-29 | 2022-04-05 | 2022-06-06 | 2022-06-10 | 46
0 | EDSDPR1135 | PROCESS DATASHEET PRESSURE GAUGES (SATAH WHP-10) - ICR | 5 | 2022-03-30 | 2022-04-06 | 2022-07-07 | 2022-07-18 | 68
0 | EDSDPR1150 | PROCESS DATASHEET PRESSURE INSTRUMENT (SATAH WHP-10) - ICR | 8 | 2022-03-30 | 2022-04-11 | 2022-07-07 | 2022-07-21 | 68
0 | EDSDPR1275 | PROCESS DATA SHEET PIG LAUNCHER (SATAH WHP-10) - IFA | 9 | 2022-03-29 | 2022-04-11 | 2022-11-14 | 2022-11-24 | 158
0 | EDSDPR1165 | PROCESS DATASHEET TEMPERATURE GAUGE (SATAH WHP-10) - ICR | 9 | 2022-03-30 | 2022-04-12 | 2022-07-07 | 2022-07-22 | 68
0 | EDSDPR1245 | PROCESS DATA SHEET DRAIN DRUM PUMP (SATAH WHP-10) - IFA | 10 | 2022-03-29 | 2022-04-12 | 2022-05-31 | 2022-06-13 | 42
0 | EDSDPR1180 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (SATAH WHP-10) - ICR | 8 | 2022-04-01 | 2022-04-13 | 2022-07-14 | 2022-07-25 | 68
0 | EDSDPR1195 | PROCESS DATASHEET LEVEL GAUGE (SATAH WHP-10) - ICR | 8 | 2022-04-05 | 2022-04-15 | 2022-07-18 | 2022-07-27 | 68
0 | EDSDPR1210 | PROCESS DATASHEET LEVEL INSTRUMENT (SATAH WHP-10) - ICR | 7 | 2022-04-07 | 2022-04-18 | 2022-07-20 | 2022-07-28 | 68
0 | EDSDPR1050 | PROCESS DATA SHEET CHOKE VALVES (SATAH WHP-10) - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-06-22 | 2022-07-05 | 53
0 | EDSDPR1080 | PROCESS DATA SHEET MOTOR OPERATED VALVES (SATAH WHP-10) - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-07-07 | 2022-07-25 | 64
0 | EDSDPR1260 | PROCESS DATA SHEET VENT / DRAIN DRUM (SATAH WHP-10) - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-06-17 | 2022-06-30 | 50
0 | EDSDPR1225 | PROCESS DATASHEET FLOW SWITCH (SATAH WHP-10) - ICR | 7 | 2022-04-11 | 2022-04-20 | 2022-10-10 | 2022-10-18 | 124
0 | EDSDPR1095 | PROCESS DATASHEET SHUTDOWN VALVES (SATAH WHP-10) - IFA | 10 | 2022-04-07 | 2022-04-21 | 2022-07-06 | 2022-07-22 | 61
0 | EDSDPR1125 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (SATAH WHP-10) - IFA | 10 | 2022-04-11 | 2022-04-25 | 2022-09-29 | 2022-10-12 | 117
0 | EDSDPR1110 | PROCESS DATASHEET IRCD (SATAH WHP-10) - IFA | 10 | 2022-04-11 | 2022-04-25 | 2022-06-27 | 2022-07-13 | 52
0 | EDSDPR1285 | PROCESS DATA SHEET RESTRICTION ORIFICES (SATAH WHP-10) - ICR | 14 | 2022-04-06 | 2022-04-26 | 2022-08-23 | 2022-09-09 | 93
0 | EDSDPR1065 | PROCESS DATA SHEET WET GAS METER (SATAH WHP-10) - MULTI PHASE FLOW METER - IFA | 10 | 2022-04-19 | 2022-05-06 | 2022-07-06 | 2022-07-22 | 53
0 | EDSDPR1140 | PROCESS DATASHEET PRESSURE GAUGES (SATAH WHP-10) - IFA | 9 | 2022-04-20 | 2022-05-06 | 2022-10-07 | 2022-10-19 | 116
0 | EDSDPR1155 | PROCESS DATASHEET PRESSURE INSTRUMENT (SATAH WHP-10) - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-10-03 | 2022-10-14 | 109
0 | EDSDPR1170 | PROCESS DATASHEET TEMPERATURE GAUGE (SATAH WHP-10) - IFA | 9 | 2022-04-26 | 2022-05-12 | 2022-10-04 | 2022-10-14 | 109
0 | EDSDPR1250 | PROCESS DATA SHEET DRAIN DRUM PUMP (SATAH WHP-10) - IFC | 10 | 2022-04-26 | 2022-05-13 | 2022-06-28 | 2022-07-14 | 42
0 | EDSDPR1185 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (SATAH WHP-10) - IFA | 10 | 2022-04-27 | 2022-05-16 | 2022-10-04 | 2022-10-17 | 108
0 | EDSDPR1200 | PROCESS DATASHEET LEVEL GAUGE (SATAH WHP-10) - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-09-26 | 2022-10-07 | 100
0 | EDSDPR1215 | PROCESS DATASHEET LEVEL INSTRUMENT (SATAH WHP-10) - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-08-12 | 2022-08-25 | 68
0 | EDSDPR1265 | PROCESS DATA SHEET VENT / DRAIN DRUM (SATAH WHP-10) - IFC | 10 | 2022-05-06 | 2022-05-20 | 2022-07-20 | 2022-08-02 | 50
0 | EDSDPR1230 | PROCESS DATASHEET FLOW SWITCH (SATAH WHP-10) - IFA | 10 | 2022-05-09 | 2022-05-23 | 2022-11-25 | 2022-12-12 | 141
0 | EDSDPR1280 | PROCESS DATA SHEET PIG LAUNCHER (SATAH WHP-10) - IFC | 19 | 2022-04-25 | 2022-05-25 | 2022-12-13 | 2023-01-06 | 158
0 | EDSDPR1085 | PROCESS DATA SHEET MOTOR OPERATED VALVES (SATAH WHP-10) - IFC | 15 | 2022-05-06 | 2022-05-27 | 2022-08-09 | 2022-08-29 | 64
0 | EDSDPR1290 | PROCESS DATA SHEET RESTRICTION ORIFICES (SATAH WHP-10) - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-09-26 | 2022-10-07 | 93
0 | EDSDPR1055 | PROCESS DATA SHEET CHOKE VALVES (SATAH WHP-10) - IFC | 20 | 2022-05-06 | 2022-06-03 | 2022-07-25 | 2022-08-19 | 53
0 | EDSDPR1100 | PROCESS DATASHEET SHUTDOWN VALVES (SATAH WHP-10) - IFC | 20 | 2022-05-10 | 2022-06-07 | 2022-08-08 | 2022-09-02 | 61
0 | EDSDPR1130 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (SATAH WHP-10) - IFC | 20 | 2022-05-12 | 2022-06-09 | 2022-10-27 | 2022-11-23 | 117
0 | EDSDPR1115 | PROCESS DATASHEET IRCD (SATAH WHP-10) - IFC | 20 | 2022-05-12 | 2022-06-09 | 2022-07-28 | 2022-08-24 | 52
0 | EDSDPR1070 | PROCESS DATA SHEET WET GAS METER (SATAH WHP-10) - MULTI PHASE FLOW METER - IFC | 20 | 2022-05-20 | 2022-06-17 | 2022-08-08 | 2022-09-02 | 53
0 | EDSDPR1145 | PROCESS DATASHEET PRESSURE GAUGES (SATAH WHP-10) - IFC | 19 | 2022-05-23 | 2022-06-17 | 2022-11-03 | 2022-11-29 | 115
0 | EDSDPR1205 | PROCESS DATASHEET LEVEL GAUGE (SATAH WHP-10) - IFC | 15 | 2022-06-01 | 2022-06-22 | 2022-10-24 | 2022-11-11 | 100
0 | EDSDPR1175 | PROCESS DATASHEET TEMPERATURE GAUGE (SATAH WHP-10) - IFC | 19 | 2022-05-26 | 2022-06-22 | 2022-10-31 | 2022-11-24 | 109
0 | EDSDPR1160 | PROCESS DATASHEET PRESSURE INSTRUMENT (SATAH WHP-10) - IFC | 20 | 2022-05-26 | 2022-06-23 | 2022-10-31 | 2022-11-25 | 109
0 | EDSDPR1190 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (SATAH WHP-10) - IFC | 20 | 2022-05-30 | 2022-06-27 | 2022-11-01 | 2022-11-28 | 108
0 | EDSDPR1220 | PROCESS DATASHEET LEVEL INSTRUMENT (SATAH WHP-10) - IFC | 20 | 2022-06-02 | 2022-06-30 | 2022-12-15 | 2023-01-11 | 135
0 | EDSDPR1235 | PROCESS DATASHEET FLOW SWITCH (SATAH WHP-10) - IFC | 20 | 2022-06-06 | 2022-07-04 | 2022-12-27 | 2023-01-23 | 141
0 | EDSDPR1295 | PROCESS DATA SHEET RESTRICTION ORIFICES (SATAH WHP-10) - IFC | 20 | 2022-06-10 | 2022-07-13 | 2022-10-24 | 2022-11-18 | 93
DRAWINGS |  |  | 192 | 2022-01-17 | 2022-10-20 | 2022-03-17 | 2023-01-24 | 67
PFD / UFD / DPDT / PSFS & HMB |  |  | 77 | 2022-01-17 | 2022-05-09 | 2022-03-17 | 2022-12-14 | 153
0 | EDSGPR1030 | HEAT AND MATERIAL BALANCE - SATAH WHP-10 WHP - ICR | 13 | 2022-01-17 | 2022-02-03 | 2022-04-01 | 2022-04-19 | 54
0 | EDSGPR1015 | UFD's - SATAH WHP-10 WHP - VENT AND DRAIN - UTILITIES SUPPLY - ICR | 13 | 2022-01-17 | 2022-02-03 | 2022-07-25 | 2022-08-10 | 129
0 | EDSGPR1000 | PFD's - SATAH WHP-10 WHP TEST AND PRODUCTION MANIFOLD - ICR | 15 | 2022-01-17 | 2022-02-07 | 2022-03-17 | 2022-04-06 | 43
0 | EDSGPR1060 | DPDT DIAGRAMS - SATAH WHP-10 WHP VENT AND DRAIN UTILITIES SUPPLY - ICR | 20 | 2022-01-19 | 2022-02-16 | 2022-07-14 | 2022-08-10 | 120
0 | EDSGPR1045 | DPDT DIAGRAMS - SATAH WHP-10 WHP - TEST AND PRODUCTION MANIFOLD - ICR | 20 | 2022-01-24 | 2022-02-21 | 2022-04-05 | 2022-05-05 | 51
0 | EDSGPR1075 | PSFS's - SATAH WHP-10 WHP - TEST AND PRODUCTION MANIFOLD - ICR | 20 | 2022-01-26 | 2022-02-23 | 2022-04-05 | 2022-05-05 | 49
0 | EDSGPR1090 | PSFS's - SATAH WHP-10 WHP - VENT AND DRAIN - UTILITIES SUPPLY - ICR | 20 | 2022-01-26 | 2022-02-23 | 2022-04-07 | 2022-05-09 | 51
0 | EDSGPR1020 | UFD's - SATAH WHP-10 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFA | 10 | 2022-02-17 | 2022-03-03 | 2022-08-25 | 2022-09-07 | 129
0 | EDSGPR1035 | HEAT AND MATERIAL BALANCE - SATAH WHP-10 WHP - IFA | 15 | 2022-02-17 | 2022-03-10 | 2022-06-14 | 2022-07-04 | 80
0 | EDSGPR1005 | PFD's - SATAH WHP-10 WHP TEST AND PRODUCTION MANIFOLD - IFA | 15 | 2022-02-21 | 2022-03-14 | 2022-07-18 | 2022-08-05 | 99
0 | EDSGPR1065 | DPDT DIAGRAMS - SATAH WHP-10 WHP VENT AND DRAIN UTILITIES SUPPLY - IFA | 10 | 2022-03-02 | 2022-03-16 | 2022-08-25 | 2022-09-07 | 120
0 | EDSGPR1050 | DPDT DIAGRAMS - SATAH WHP-10 WHP - TEST AND PRODUCTION MANIFOLD - IFA | 10 | 2022-03-07 | 2022-03-21 | 2022-08-25 | 2022-09-07 | 117
0 | EDSGPR1080 | PSFS's - SATAH WHP-10 WHP - TEST AND PRODUCTION MANIFOLD - IFA | 10 | 2022-03-09 | 2022-03-23 | 2022-09-01 | 2022-09-14 | 120
0 | EDSGPR1095 | PSFS's - SATAH WHP-10 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFA | 10 | 2022-03-09 | 2022-03-23 | 2022-09-01 | 2022-09-14 | 120
0 | EDSGPR1025 | UFD's - SATAH WHP-10 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFC | 20 | 2022-03-17 | 2022-04-14 | 2022-09-22 | 2022-10-19 | 129
0 | EDSGPR1040 | HEAT AND MATERIAL BALANCE - SATAH WHP-10 WHP - IFC | 20 | 2022-03-24 | 2022-04-21 | 2022-10-25 | 2022-11-21 | 147
0 | EDSGPR1010 | PFD's - SATAH WHP-10 WHP TEST AND PRODUCTION MANIFOLD - IFC | 20 | 2022-03-28 | 2022-04-25 | 2022-10-31 | 2022-11-25 | 149
0 | EDSGPR1070 | DPDT DIAGRAMS - SATAH WHP-10 WHP VENT AND DRAIN UTILITIES SUPPLY - IFC | 20 | 2022-03-30 | 2022-04-27 | 2022-11-15 | 2022-12-14 | 158
0 | EDSGPR1055 | DPDT DIAGRAMS - SATAH WHP-10 WHP - TEST AND PRODUCTION MANIFOLD - IFC | 20 | 2022-04-05 | 2022-05-06 | 2022-10-25 | 2022-11-21 | 139
0 | EDSGPR1085 | PSFS's - SATAH WHP-10 WHP - TEST AND PRODUCTION MANIFOLD - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-10-25 | 2022-11-21 | 138
0 | EDSGPR1100 | PSFS's - SATAH WHP-10 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-10-25 | 2022-11-21 | 138
PIPING & INSTRUMENTATION DIAGRAMS |  |  | 176 | 2022-02-08 | 2022-10-20 | 2022-04-11 | 2023-01-24 | 67
0 | EDSGPR1105 | P&ID - DRAWING INDEX SATAH WHP-10 WHP - ICR | 16 | 2022-02-08 | 2022-03-02 | 2022-04-20 | 2022-05-16 | 51
0 | EDSGPR1120 | P&IDs - SATAH WHP-10 WHP - ICR | 23 | 2022-02-10 | 2022-03-15 | 2022-04-11 | 2022-05-16 | 42
0 | EDSGPR1125 | P&IDs - SATAH WHP-10 WHP - ISSUED FOR HAZOP | 26 | 2022-04-04 | 2022-05-13 | 2022-06-28 | 2022-08-05 | 57
0 | EDSGPR1130 | P&IDs - SATAH WHP-10 WHP - IFA | 21 | 2022-06-22 | 2022-07-26 | 2022-09-12 | 2022-10-10 | 55
0 | EDSGPR1110 | P&ID - DRAWING INDEX SATAH WHP-10 WHP - IFA | 21 | 2022-06-22 | 2022-07-26 | 2022-11-04 | 2022-12-06 | 94
0 | EDSGPR1135 | P&IDs - SATAH WHP-10 WHP - IFC | 25 | 2022-09-15 | 2022-10-20 | 2022-11-22 | 2022-12-28 | 48
0 | EDSGPR1115 | P&ID - DRAWING INDEX SATAH WHP-10 WHP - IFC | 25 | 2022-09-15 | 2022-10-20 | 2022-12-21 | 2023-01-24 | 67
CAUSE & EFFECT & SAFE CHARTS |  |  | 80 | 2022-03-22 | 2022-07-20 | 2022-07-06 | 2022-12-19 | 107
0 | EDSGPR1140 | CAUSE & EFFECT CHARTS - SATAH WHP-10 WHP - ICR | 15 | 2022-03-22 | 2022-04-12 | 2022-07-06 | 2022-07-29 | 73
0 | EDSGPR1155 | SAFE CHART - SATAH WHP-10 WHP - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-08-23 | 2022-09-05 | 89
0 | EDSGPR1145 | CAUSE & EFFECT CHARTS - SATAH WHP-10 WHP - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-08-15 | 2022-08-26 | 73
0 | EDSGPR1160 | SAFE CHART - SATAH WHP-10 WHP - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-09-20 | 2022-10-03 | 89
0 | EDSGPR1165 | SAFE CHART - SATAH WHP-10 WHP - IFC | 25 | 2022-06-10 | 2022-07-20 | 2022-10-18 | 2022-11-21 | 89
0 | EDSGPR1150 | CAUSE & EFFECT CHARTS - SATAH WHP-10 WHP - IFC | 35 | 2022-05-27 | 2022-07-20 | 2022-10-28 | 2022-12-19 | 107
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDSGPR2000 | WHP-10 PROCESS MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDSGPR2005 | WHP-10 PROCESS MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDSGPR2010 | WHP-10 PROCESS MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
MATERIAL & CORROSION |  |  | 239 | 2022-02-03 | 2023-01-16 | 2022-04-20 | 2023-04-27 | 72
DOCUMENTS |  |  | 68 | 2022-08-22 | 2022-11-24 | 2022-11-09 | 2023-02-14 | 57
0 | EDSDMA1000 | WHP-10 DEAD-LEG REGISTER - ICR | 15 | 2022-08-22 | 2022-09-12 | 2022-11-09 | 2022-11-29 | 57
0 | EDSDMA1010 | WHP-10 DEAD-LEG REGISTER - IFA | 15 | 2022-09-26 | 2022-10-17 | 2022-12-16 | 2023-01-05 | 57
0 | EDSDMA1020 | WHP-10 DEAD-LEG REGISTER - IFC | 20 | 2022-10-27 | 2022-11-24 | 2023-01-18 | 2023-02-14 | 57
DRAWINGS |  |  | 72 | 2022-02-03 | 2022-05-19 | 2022-04-20 | 2022-11-21 | 130
0 | EDSGMA1000 | MATERIAL SELECTION DIAGRAMS - SATAH WHP-10 WHP - ICR | 12 | 2022-02-03 | 2022-02-21 | 2022-04-20 | 2022-05-10 | 54
0 | EDSGMA1005 | MATERIAL SELECTION DIAGRAMS - SATAH WHP-10 WHP - IFA | 15 | 2022-03-07 | 2022-03-28 | 2022-08-08 | 2022-08-26 | 104
0 | EDSGMA1010 | MATERIAL SELECTION DIAGRAMS - SATAH WHP-10 WHP - IFC | 25 | 2022-04-11 | 2022-05-19 | 2022-10-18 | 2022-11-21 | 130
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDSGMA2000 | WHP-10 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDSGMA2005 | WHP-10 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDSGMA2010 | WHP-10 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
SAFETY |  |  | 328 | 2022-02-22 | 2023-01-16 | 2022-06-08 | 2023-04-27 | 102
DRAWINGS |  |  | 246 | 2022-02-22 | 2022-10-26 | 2022-06-08 | 2023-03-31 | 157
0 | EDSGSA1000 | P&ID FIREWATER DRY SYSTEM - SATAH WHP-10 - ICR | 15 | 2022-02-22 | 2022-03-15 | 2022-06-08 | 2022-06-28 | 73
0 | EDSGSA1005 | P&ID FIREWATER DRY SYSTEM - SATAH WHP-10 - ISSUED FOR HAZOP | 15 | 2022-04-17 | 2022-05-08 | 2022-07-18 | 2022-08-07 | 66
0 | EDSGSA1015 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - SATAH WHP-10 - ICR | 10 | 2022-05-16 | 2022-05-30 | 2022-08-23 | 2022-09-05 | 68
0 | EDSGSA1030 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - SATAH WHP-10 - ICR | 9 | 2022-06-17 | 2022-06-30 | 2022-10-03 | 2022-10-13 | 73
0 | EDSGSA1007 | P&ID FIREWATER DRY SYSTEM - SATAH WHP-10 - IFA | 15 | 2022-06-09 | 2022-06-30 | 2022-08-25 | 2022-09-14 | 55
0 | EDSGSA1020 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - SATAH WHP-10 - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-10-05 | 2022-10-18 | 77
0 | EDSGSA1060 | FIRE AND GAS CAUSE & EFFECT CHART – SATAH WHP-10 - ICR | 13 | 2022-06-30 | 2022-07-22 | 2022-10-28 | 2022-11-15 | 83
0 | EDSGSA1010 | P&ID FIREWATER DRY SYSTEM - SATAH WHP-10 - IFC | 15 | 2022-07-14 | 2022-08-04 | 2022-09-29 | 2022-10-19 | 55
0 | EDSGSA1045 | H2S ZONE LAYOUT - SATAH WHP-10 - ICR | 15 | 2022-07-20 | 2022-08-10 | 2023-01-16 | 2023-02-03 | 126
0 | EDSGSA1035 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - SATAH WHP-10 - IFA | 10 | 2022-07-27 | 2022-08-10 | 2022-12-01 | 2022-12-14 | 91
0 | EDSGSA1075 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - SATAH WHP-10 - ICR | 11 | 2022-07-27 | 2022-08-11 | 2022-11-02 | 2022-11-16 | 70
0 | EDSGSA1065 | FIRE AND GAS CAUSE & EFFECT CHART – SATAH WHP-10 - IFA | 10 | 2022-08-07 | 2022-08-18 | 2022-11-30 | 2022-12-13 | 83
0 | EDSGSA1025 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - SATAH WHP-10 - IFC | 15 | 2022-08-11 | 2022-09-01 | 2022-12-29 | 2023-01-18 | 98
0 | EDSGSA1050 | H2S ZONE LAYOUT - SATAH WHP-10 - IFA | 10 | 2022-08-24 | 2022-09-07 | 2023-02-20 | 2023-03-05 | 128
0 | EDSGSA1080 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - SATAH WHP-10 - IFA | 15 | 2022-08-31 | 2022-09-21 | 2022-12-01 | 2022-12-21 | 66
0 | EDSGSA1040 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - SATAH WHP-10 - IFC | 15 | 2022-09-07 | 2022-09-28 | 2022-12-29 | 2023-01-18 | 79
0 | EDSGSA1070 | FIRE AND GAS CAUSE & EFFECT CHART – SATAH WHP-10 - IFC | 16 | 2022-09-07 | 2022-09-29 | 2022-12-28 | 2023-01-18 | 78
0 | EDSGSA1055 | H2S ZONE LAYOUT - SATAH WHP-10 - IFC | 10 | 2022-09-21 | 2022-10-05 | 2023-03-20 | 2023-03-31 | 126
0 | EDSGSA1085 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - SATAH WHP-10 - IFC | 10 | 2022-10-12 | 2022-10-26 | 2023-01-05 | 2023-01-18 | 59
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDSGSA2000 | WHP-10 SAFETY MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDSGSA2005 | WHP-10 SAFETY MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDSGSA2010 | WHP-10 SAFETY MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
PIPING |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-05-24 | 2023-04-27 | 69
3D MODELING |  |  | 166 | 2022-05-25 | 2023-01-19 | 2022-08-09 | 2023-03-28 | 49
30% MODEL REVIEW/REPORT |  |  | 50 | 2022-05-25 | 2022-08-08 | 2022-08-09 | 2022-10-31 | 61
0 | EDSDPI3100 | ST-10 30% 3D MODEL REVIEW REPORT - ICR | 10 | 2022-05-25 | 2022-06-08 | 2022-08-09 | 2022-08-22 | 51
0 | EDSDPI3105 | ST-10 30% 3D MODEL REVIEW REPORT - IFA | 10 | 2022-06-22 | 2022-07-06 | 2022-09-20 | 2022-10-03 | 61
0 | EDSDPI3110 | ST-10 30% 3D MODEL REVIEW REPORT - IFC | 10 | 2022-07-25 | 2022-08-08 | 2022-10-18 | 2022-10-31 | 61
60% MODEL REVIEW/REPORT |  |  | 60 | 2022-08-26 | 2022-11-18 | 2022-11-01 | 2023-02-02 | 53
0 | EDSDPI3120 | ST-10 60% 3D MODEL REVIEW REPORT - ICR | 10 | 2022-08-26 | 2022-09-09 | 2022-11-01 | 2022-11-14 | 47
0 | EDSDPI3125 | ST-10 60% 3D MODEL REVIEW REPORT - IFA | 10 | 2022-09-23 | 2022-10-07 | 2022-12-09 | 2022-12-22 | 53
0 | EDSDPI3130 | ST-10 60% 3D MODEL REVIEW REPORT - IFC | 20 | 2022-10-21 | 2022-11-18 | 2023-01-06 | 2023-02-02 | 53
90% MODEL REVIEW/REPORT |  |  | 41 | 2022-11-21 | 2023-01-19 | 2023-02-03 | 2023-03-28 | 49
0 | EDSDPI3140 | ST-10 90% 3D MODEL REVIEW REPORT - ICR | 8 | 2022-11-21 | 2022-12-05 | 2023-02-03 | 2023-02-14 | 52
0 | EDSDPI3145 | ST-10 90% 3D MODEL REVIEW REPORT - IFA | 7 | 2022-12-21 | 2022-12-30 | 2023-03-01 | 2023-03-09 | 50
0 | EDSDPI3150 | ST-10 90% 3D MODEL REVIEW REPORT - IFC | 3 | 2023-01-16 | 2023-01-19 | 2023-03-24 | 2023-03-28 | 49
3D MODEL DEVELOPMENT |  |  | 200 | 2022-04-04 | 2023-01-19 | 2022-06-15 | 2023-03-28 | 49
0 | EDSDPI3000 | WHP-10 3D MODEL DEVELOPMENT - PIPING | 200 | 2022-04-04 | 2023-01-19 | 2022-06-15 | 2023-03-28 | 49
DOCUMENTS |  |  | 203 | 2022-03-29 | 2023-01-18 | 2022-09-22 | 2023-04-14 | 63
REPORTS & CALCULATIONS |  |  | 203 | 2022-03-29 | 2023-01-18 | 2022-09-22 | 2023-04-14 | 63
0 | EDSDPI1000 | SATAH WHP-10 PLATFORM PIPE STRESS CRITICAL LINE LIST - ICR | 15 | 2022-03-29 | 2022-04-19 | 2022-10-11 | 2022-10-31 | 134
0 | EDSDPI1005 | SATAH WHP-10 PLATFROM PIPE STRESS CRITICAL LINE LIST - IFA | 15 | 2022-05-06 | 2022-05-27 | 2022-11-15 | 2022-12-07 | 134
0 | EDSDPI1015 | SATAH WHP-10 PLATFROM PIPING STRESS ANALYSIS REPORT - ICR | 15 | 2022-05-19 | 2022-06-09 | 2022-12-20 | 2023-01-09 | 148
0 | EDSDPI1030 | WHP-10 MECHANICAL HANDLING STUDY REPORT - ICR | 10 | 2022-06-22 | 2022-07-06 | 2022-09-22 | 2022-10-05 | 63
0 | EDSDPI1010 | SATAH WHP-10 PLATFROM PIPE STRESS CRITICAL LINE LIST - IFC | 20 | 2022-06-10 | 2022-07-13 | 2022-12-22 | 2023-01-18 | 134
0 | EDSDPI1035 | WHP-10 MECHANICAL HANDLING STUDY REPORT - IFA | 10 | 2022-08-26 | 2022-09-09 | 2023-01-20 | 2023-02-02 | 103
0 | EDSDPI1020 | SATAH WHP-10 PLATFROM PIPING STRESS ANALYSIS REPORT - IFA | 15 | 2022-08-22 | 2022-09-12 | 2023-01-10 | 2023-01-30 | 99
0 | EDSDPI1040 | WHP-10 MECHANICAL HANDLING STUDY REPORT - IFC | 10 | 2022-11-21 | 2022-12-07 | 2023-02-23 | 2023-03-08 | 66
0 | EDSDPI1025 | SATAH WHP-10 PLATFROM PIPING STRESS ANALYSIS REPORT - IFC | 20 | 2022-11-21 | 2022-12-21 | 2023-02-10 | 2023-03-09 | 57
0 | EDSDPI1050 | WHP-10 PIPE SUPPORT SCHEDULE - IFI | 10 | 2022-12-07 | 2022-12-21 | 2023-03-06 | 2023-03-17 | 63
0 | EDSDPI1060 | WHP-10 PIPE SUPPORT SCHEDULE - IFC | 10 | 2023-01-04 | 2023-01-18 | 2023-04-03 | 2023-04-14 | 63
DRAWINGS |  |  | 214 | 2022-03-14 | 2023-01-18 | 2022-05-24 | 2023-04-27 | 70
0 | EDSGPI1000 | SATAH WHP-10 PLATFROM PLOT PLAN DRAWINGS - ICR | 30 | 2022-03-14 | 2022-04-25 | 2022-05-24 | 2022-07-04 | 48
0 | EDSGPI1005 | SATAH WHP-10 PLATFROM PLOT PLAN DRAWINGS - IFA | 22 | 2022-05-12 | 2022-06-13 | 2022-07-26 | 2022-08-24 | 50
0 | EDSGPI1035 | WHP-10 SPECIAL SUPPORT DRAWINGS - ICR | 10 | 2022-11-21 | 2022-12-07 | 2023-02-20 | 2023-03-03 | 63
0 | EDSGPI1010 | SATAH WHP-10 PLATFROM PLOT PLAN DRAWINGS - IFC | 17 | 2022-11-21 | 2022-12-16 | 2023-04-03 | 2023-04-27 | 93
0 | EDSGPI1015 | SATAH WHP-10 PLATFROM ENGINEERING ISOMETRICS | 18 | 2022-11-21 | 2022-12-19 | 2023-01-25 | 2023-02-17 | 45
0 | EDSGPI1020 | SATAH WHP-10 PLATFROM PIPING GA DRAWING - IFI | 10 | 2022-12-14 | 2022-12-28 | 2023-03-22 | 2023-04-04 | 70
0 | EDSGPI1040 | WHP-10 SPECIAL SUPPORT DRAWINGS - IFA | 7 | 2022-12-21 | 2022-12-30 | 2023-03-20 | 2023-03-28 | 63
0 | EDSGPI1025 | SATAH WHP-10 PLATFROM PIPING GA DRAWING - IFC | 5 | 2023-01-11 | 2023-01-18 | 2023-04-19 | 2023-04-27 | 70
0 | EDSGPI1045 | WHP-10 SPECIAL SUPPORT DRAWINGS - IFC | 3 | 2023-01-13 | 2023-01-18 | 2023-04-12 | 2023-04-14 | 63
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDSGPI2000 | WHP-10 PIPING MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDSGPI2005 | WHP-10 PIPING MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDSGPI2010 | WHP-10 PIPING MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
MECHANICAL (STATIC / ROTATING) |  |  | 222 | 2022-02-28 | 2023-01-16 | 2022-05-10 | 2023-04-07 | 60
STATIC |  |  | 222 | 2022-02-28 | 2023-01-16 | 2022-05-10 | 2023-04-07 | 60
DOCUMENTS |  |  | 120 | 2022-02-28 | 2022-08-23 | 2022-05-10 | 2022-12-07 | 75
CALCULATION |  |  | 65 | 2022-05-19 | 2022-08-23 | 2022-07-28 | 2022-12-07 | 75
0 | EDSDME1000 | WHP-10 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (ST110-V-001) - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-07-28 | 2022-08-24 | 47
0 | EDSDME1005 | WHP-10 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (ST110-V-001) - IFA | 15 | 2022-06-30 | 2022-07-26 | 2022-10-18 | 2022-11-07 | 75
0 | EDSDME1010 | WHP-10 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (ST110-V-001) - IFC | 10 | 2022-08-09 | 2022-08-23 | 2022-11-22 | 2022-12-07 | 75
DATA SHEET |  |  | 61 | 2022-02-28 | 2022-05-27 | 2022-05-10 | 2022-09-06 | 70
0 | EDSDME1015 | WHP-10 MECHANICAL DATA SHEET FOR PIG LAUNCHER (ST110-PL-001) - ICR | 11 | 2022-02-28 | 2022-03-15 | 2022-05-10 | 2022-05-24 | 48
0 | EDSDME1030 | WHP-10 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (ST110-V-001) - ICR | 5 | 2022-03-18 | 2022-03-25 | 2022-06-22 | 2022-06-28 | 65
0 | EDSDME1020 | WHP-10 MECHANICAL DATA SHEET FOR PIG LAUNCHER (ST110-PL-001) - IFA | 10 | 2022-03-29 | 2022-04-12 | 2022-06-08 | 2022-06-21 | 48
0 | EDSDME1035 | WHP-10 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (ST110-V-001) - IFA | 10 | 2022-04-08 | 2022-04-22 | 2022-07-27 | 2022-08-09 | 72
0 | EDSDME1025 | WHP-10 MECHANICAL DATA SHEET FOR PIG LAUNCHER (ST110-PL-001) - IFC | 13 | 2022-04-26 | 2022-05-18 | 2022-07-06 | 2022-07-27 | 48
0 | EDSDME1040 | WHP-10 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (ST110-V-001) - IFC | 10 | 2022-05-13 | 2022-05-27 | 2022-08-24 | 2022-09-06 | 70
DRAWINGS |  |  | 79 | 2022-06-23 | 2022-10-17 | 2022-09-01 | 2023-01-10 | 60
0 | EDSGME1000 | WHP-10 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.(ST110-V-001) - ICR | 10 | 2022-06-23 | 2022-07-07 | 2022-09-01 | 2022-09-14 | 47
0 | EDSGME1015 | WHP-10 DETAIL DRAWING FOR VENT DRAIN DRUM ((ST110-V-001) - IFI | 10 | 2022-07-22 | 2022-08-05 | 2022-09-27 | 2022-10-10 | 47
0 | EDSGME1005 | WHP-10 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.(ST110-V-001) - IFA | 10 | 2022-07-26 | 2022-08-09 | 2022-10-06 | 2022-10-19 | 52
0 | EDSGME1045 | WHP-10 NOZZLE DETAIL (TAG NO. (ST110-V-001) - IFI | 10 | 2022-07-29 | 2022-08-12 | 2022-10-04 | 2022-10-17 | 47
0 | EDSGME1030 | WHP-10 WELDING DETAIL & WELD MAP (TAG NO. (ST110-V-001) - IFI | 10 | 2022-08-04 | 2022-08-18 | 2022-10-10 | 2022-10-21 | 47
0 | EDSGME1060 | WHP-10 MANWAY DAVIT DETAIL (TAG NO. (ST110-V-001) - IFI | 10 | 2022-08-10 | 2022-08-24 | 2022-10-14 | 2022-10-27 | 47
0 | EDSGME1075 | WHP-10 INTERNAL / EXTERNAL ATTACHMENTS (TAG NO. (ST110-V-001) - IFI | 10 | 2022-08-16 | 2022-08-30 | 2022-10-20 | 2022-11-02 | 47
0 | EDSGME1090 | WHP-10 NAME PLATE DETAIL (TAG NO. (ST110-V-001) - IFI | 10 | 2022-08-22 | 2022-09-05 | 2022-11-14 | 2022-11-25 | 60
0 | EDSGME1025 | WHP-10 DETAIL DRAWING FOR VENT DRAIN DRUM ((ST110-V-001) - IFC | 15 | 2022-08-19 | 2022-09-09 | 2022-11-08 | 2022-11-28 | 57
0 | EDSGME1010 | WHP-10 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.(ST110-V-001) - IFC | 20 | 2022-08-23 | 2022-09-20 | 2022-11-17 | 2022-12-16 | 62
0 | EDSGME1055 | WHP-10 NOZZLE DETAIL (TAG NO. (ST110-V-001) - IFC | 20 | 2022-08-26 | 2022-09-23 | 2022-11-03 | 2022-11-30 | 49
0 | EDSGME1040 | WHP-10 WELDING DETAIL & WELD MAP (TAG NO. (ST110-V-001) - IFC | 20 | 2022-09-01 | 2022-09-29 | 2022-11-17 | 2022-12-16 | 55
0 | EDSGME1070 | WHP-10 MANWAY DAVIT DETAIL (TAG NO. (ST110-V-001) - IFC | 19 | 2022-09-07 | 2022-10-04 | 2022-11-18 | 2022-12-16 | 52
0 | EDSGME1085 | WHP-10 INTERNAL / EXTERNAL ATTACHMENTS (TAG NO. (ST110-V-001) - IFC | 20 | 2022-09-13 | 2022-10-11 | 2022-11-17 | 2022-12-16 | 47
0 | EDSGME1100 | WHP-10 NAME PLATE DETAIL (TAG NO. (ST110-V-001) - IFC | 20 | 2022-09-19 | 2022-10-17 | 2022-12-14 | 2023-01-10 | 60
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2022-12-19 | 2023-04-07 | 60
0 | EDSGME2000 | WHP-10 MECHANICAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2022-12-19 | 2023-01-13 | 60
0 | EDSGME2005 | WHP-10 MECHANICAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-01-30 | 2023-02-24 | 60
0 | EDSGME2010 | WHP-10 MECHANICAL MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-13 | 2023-04-07 | 60
PACKAGE EQUIPMENT |  |  | 47 | 2022-03-23 | 2022-06-01 | 2022-06-20 | 2022-09-07 | 68
DOCUMENTS |  |  | 47 | 2022-03-23 | 2022-06-01 | 2022-06-20 | 2022-09-07 | 68
DATASHEETS |  |  | 47 | 2022-03-23 | 2022-06-01 | 2022-06-20 | 2022-09-07 | 68
0 | EDSDME1045 | WHP-10 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - ICR | 9 | 2022-03-23 | 2022-04-05 | 2022-06-20 | 2022-06-30 | 60
0 | EDSDME1050 | WHP-10 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - IFA | 9 | 2022-04-19 | 2022-05-05 | 2022-08-01 | 2022-08-11 | 68
0 | EDSDME1055 | WHP-10 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - IFC | 9 | 2022-05-19 | 2022-06-01 | 2022-08-26 | 2022-09-07 | 68
ELECTRICAL |  |  | 198 | 2022-04-06 | 2023-01-19 | 2022-07-05 | 2023-04-27 | 69
3D MODEL DEVELOPMENT |  |  | 186 | 2022-04-22 | 2023-01-19 | 2022-07-05 | 2023-03-28 | 49
0 | EDSDEL3000 | WHP-10 3D MODEL DEVELOPMENT - ELECTRICAL | 186 | 2022-04-22 | 2023-01-19 | 2022-07-05 | 2023-03-28 | 49
DRAWINGS |  |  | 197 | 2022-04-06 | 2023-01-18 | 2022-07-07 | 2023-04-27 | 70
DIAGRAM |  |  | 162 | 2022-04-06 | 2022-11-28 | 2022-07-07 | 2023-04-27 | 105
0 | EDSGEL1000 | WHP-10 SINGLE LINE DIAGRAM – 6.6KV RMU - ICR | 15 | 2022-04-06 | 2022-04-27 | 2022-08-03 | 2022-08-23 | 79
0 | EDSGEL1015 | WHP-10 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - ICR | 15 | 2022-04-20 | 2022-05-16 | 2022-08-10 | 2022-08-30 | 74
0 | EDSGEL1002 | WHP-10 ELECTRICAL EQUIPMENT LIST - ICR | 15 | 2022-04-25 | 2022-05-19 | 2022-07-07 | 2022-08-01 | 50
0 | EDSGEL1030 | WHP-10 SINGLE LINE DIAGRAM – 24V DC UPS - ICR | 15 | 2022-04-26 | 2022-05-20 | 2022-08-16 | 2022-09-05 | 74
0 | EDSGEL1045 | WHP-10 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - ICR | 15 | 2022-05-05 | 2022-05-26 | 2022-08-22 | 2022-09-09 | 74
0 | EDSGEL1003 | WHP-10 ELECTRICAL LOAD LIST - ICR | 15 | 2022-05-05 | 2022-05-26 | 2022-07-21 | 2022-08-10 | 52
0 | EDSGEL1005 | WHP-10 SINGLE LINE DIAGRAM – 6.6KV RMU - IFA | 10 | 2022-05-16 | 2022-05-30 | 2022-09-30 | 2022-10-13 | 96
0 | EDSGEL1060 | WHP-10 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - ICR | 15 | 2022-05-11 | 2022-06-01 | 2022-08-26 | 2022-09-15 | 74
0 | EDSGEL1075 | WHP-10 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - ICR | 15 | 2022-05-18 | 2022-06-08 | 2022-09-09 | 2022-09-29 | 79
0 | EDSGEL1020 | WHP-10 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - IFA | 10 | 2022-05-30 | 2022-06-13 | 2022-09-30 | 2022-10-13 | 86
0 | EDSGEL1035 | WHP-10 SINGLE LINE DIAGRAM – 24V DC UPS - IFA | 10 | 2022-06-03 | 2022-06-17 | 2022-09-30 | 2022-10-13 | 82
0 | EDSGEL1050 | WHP-10 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - IFA | 10 | 2022-06-09 | 2022-06-23 | 2022-09-30 | 2022-10-13 | 78
0 | EDSGEL1006 | WHP-10 ELECTRICAL EQUIPMENT LIST - IFA | 15 | 2022-06-02 | 2022-06-23 | 2022-09-01 | 2022-09-21 | 62
0 | EDSGEL1065 | WHP-10 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - IFA | 10 | 2022-06-15 | 2022-06-29 | 2022-09-30 | 2022-10-13 | 74
0 | EDSGEL1009 | WHP-10 ELECTRICAL LOAD LIST - IFA | 15 | 2022-06-09 | 2022-06-30 | 2022-09-08 | 2022-09-28 | 62
0 | EDSGEL1010 | WHP-10 SINGLE LINE DIAGRAM – 6.6KV RMU - IFC | 15 | 2022-06-13 | 2022-07-04 | 2022-10-28 | 2022-11-17 | 96
0 | EDSGEL1080 | WHP-10 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - IFA | 10 | 2022-06-22 | 2022-07-06 | 2022-10-14 | 2022-10-27 | 79
0 | EDSGEL1025 | WHP-10 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - IFC | 15 | 2022-06-27 | 2022-07-21 | 2022-10-28 | 2022-11-17 | 86
0 | EDSGEL1040 | WHP-10 SINGLE LINE DIAGRAM – 24V DC UPS - IFC | 15 | 2022-07-01 | 2022-07-27 | 2022-10-28 | 2022-11-17 | 82
0 | EDSGEL1055 | WHP-10 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - IFC | 15 | 2022-07-07 | 2022-08-02 | 2022-10-28 | 2022-11-17 | 78
0 | EDSGEL1070 | WHP-10 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - IFC | 15 | 2022-07-18 | 2022-08-08 | 2022-10-28 | 2022-11-17 | 74
0 | EDSGEL1004 | WHP-10 ELECTRICAL EQUIPMENT LIST - IFC | 20 | 2022-07-07 | 2022-08-09 | 2022-10-06 | 2022-11-02 | 62
0 | EDSGEL1085 | WHP-10 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - IFC | 15 | 2022-07-25 | 2022-08-15 | 2022-11-11 | 2022-12-05 | 79
0 | EDSGEL1007 | WHP-10 ELECTRICAL LOAD LIST - IFC | 20 | 2022-07-19 | 2022-08-16 | 2022-10-13 | 2022-11-09 | 62
0 | EDSGEL1090 | WHP-10 ELECTRICAL CABLE SCHEDULE - ICR | 15 | 2022-08-01 | 2022-08-22 | 2023-01-04 | 2023-01-24 | 110
0 | EDSGEL1105 | WHP-10 ELECTRICAL INTERCONNECTION DIAGRAM - ICR | 15 | 2022-08-29 | 2022-09-19 | 2023-01-25 | 2023-02-14 | 105
0 | EDSGEL1095 | WHP-10 ELECTRICAL CABLE SCHEDULE - IFA | 10 | 2022-09-05 | 2022-09-19 | 2023-03-08 | 2023-03-21 | 130
0 | EDSGEL1100 | WHP-10 ELECTRICAL CABLE SCHEDULE - IFC | 15 | 2022-10-03 | 2022-10-24 | 2023-04-05 | 2023-04-27 | 130
0 | EDSGEL2020 | WHP-10 ELECTRICAL INTERCONNECTION DIAGRAM - IFA | 15 | 2022-10-03 | 2022-10-24 | 2023-03-01 | 2023-03-21 | 105
0 | EDSGEL1110 | WHP-10 ELECTRICAL INTERCONNECTION DIAGRAM - IFC | 15 | 2022-11-07 | 2022-11-28 | 2023-04-05 | 2023-04-27 | 105
BOOKLET |  |  | 50 | 2022-11-07 | 2023-01-18 | 2023-02-15 | 2023-04-27 | 70
0 | EDSGEL1200 | WHP-10 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - ICR | 10 | 2022-11-07 | 2022-11-21 | 2023-02-15 | 2023-02-28 | 70
0 | EDSGEL2030 | WHP-10 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - IFA | 10 | 2022-12-07 | 2022-12-21 | 2023-03-15 | 2023-03-28 | 70
0 | EDSGEL1205 | WHP-10 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - IFC | 10 | 2023-01-04 | 2023-01-18 | 2023-04-12 | 2023-04-27 | 70
LAYOUT |  |  | 134 | 2022-05-05 | 2022-11-14 | 2022-11-18 | 2023-03-21 | 90
0 | EDSGEL1300 | WHP-10 ELECTRICAL EQUIPMENT LAYOUT - ICR | 15 | 2022-05-05 | 2022-05-26 | 2022-12-06 | 2022-12-26 | 148
0 | EDSGEL1305 | WHP-10 ELECTRICAL EQUIPMENT LAYOUT - IFA | 10 | 2022-06-09 | 2022-06-23 | 2023-01-10 | 2023-01-23 | 148
0 | EDSGEL1375 | WHP-10 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - ICR | 10 | 2022-08-10 | 2022-08-24 | 2022-11-25 | 2022-12-12 | 77
0 | EDSGEL1390 | WHP-10 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - ICR | 10 | 2022-08-11 | 2022-08-25 | 2022-12-20 | 2023-01-02 | 91
0 | EDSGEL1315 | WHP-10 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IRC | 15 | 2022-08-08 | 2022-08-29 | 2022-11-18 | 2022-12-12 | 74
0 | EDSGEL1330 | WHP-10 ELECTRICAL CABLE ROUTING LAYOUT - IRC | 15 | 2022-08-15 | 2022-09-05 | 2022-11-25 | 2022-12-19 | 74
0 | EDSGEL1360 | WHP-10 EARTHING & LIGHTNING PROTECTION LAYOUT - IRC | 15 | 2022-08-22 | 2022-09-12 | 2022-12-06 | 2022-12-26 | 74
0 | EDSGEL1345 | WHP-10 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IRC | 15 | 2022-08-22 | 2022-09-12 | 2022-12-06 | 2022-12-26 | 74
0 | EDSGEL1310 | WHP-10 ELECTRICAL EQUIPMENT LAYOUT - IFC | 15 | 2022-08-22 | 2022-09-12 | 2023-02-07 | 2023-02-27 | 119
0 | EDSGEL1380 | WHP-10 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - IFA | 10 | 2022-09-07 | 2022-09-21 | 2023-01-03 | 2023-01-16 | 82
0 | EDSGEL1395 | WHP-10 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-01-17 | 2023-01-30 | 91
0 | EDSGEL2040 | WHP-10 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IFA | 15 | 2022-09-12 | 2022-10-03 | 2023-01-10 | 2023-01-30 | 84
0 | EDSGEL2050 | WHP-10 ELECTRICAL CABLE ROUTING LAYOUT - IFA | 15 | 2022-09-19 | 2022-10-10 | 2023-01-17 | 2023-02-06 | 84
0 | EDSGEL2060 | WHP-10 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IFA | 10 | 2022-09-26 | 2022-10-10 | 2023-02-01 | 2023-02-14 | 90
0 | EDSGEL2070 | WHP-10 EARTHING & LIGHTNING PROTECTION LAYOUT - IFA | 15 | 2022-09-26 | 2022-10-17 | 2023-01-10 | 2023-01-30 | 74
0 | EDSGEL1385 | WHP-10 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - IFC | 10 | 2022-10-05 | 2022-10-19 | 2023-01-31 | 2023-02-13 | 82
0 | EDSGEL1400 | WHP-10 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-02-14 | 2023-02-27 | 91
0 | EDSGEL1325 | WHP-10 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IFC | 10 | 2022-10-21 | 2022-11-04 | 2023-02-14 | 2023-02-27 | 80
0 | EDSGEL1355 | WHP-10 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IFC | 15 | 2022-10-24 | 2022-11-14 | 2023-03-01 | 2023-03-21 | 90
0 | EDSGEL1340 | WHP-10 ELECTRICAL CABLE ROUTING LAYOUT - IFC | 15 | 2022-10-24 | 2022-11-14 | 2023-02-21 | 2023-03-13 | 84
0 | EDSGEL1370 | WHP-10 EARTHING & LIGHTNING PROTECTION LAYOUT - IFC | 10 | 2022-10-31 | 2022-11-14 | 2023-02-14 | 2023-02-27 | 74
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDSGEL2000 | WHP-10 ELECTRICAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDSGEL2005 | WHP-10 ELECTRICAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDSGEL2010 | WHP-10 ELECTRICAL MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
INSTRUMENTATION & CONTROL |  |  | 221 | 2022-03-03 | 2023-01-18 | 2022-05-12 | 2023-08-17 | 146
3D MODEL DEVELOPMENT |  |  | 180 | 2022-04-29 | 2023-01-18 | 2022-07-18 | 2023-03-28 | 50
0 | EDSDIN3000 | WHP-10 3D MODEL DEVELOPMENT - INSTRUMENTATION | 180 | 2022-04-29 | 2023-01-18 | 2022-07-18 | 2023-03-28 | 50
DOCUMENTS |  |  | 211 | 2022-03-03 | 2023-01-04 | 2022-05-12 | 2023-04-27 | 80
CALCULATIONS |  |  | 81 | 2022-03-22 | 2022-07-21 | 2022-05-26 | 2022-12-26 | 111
0 | EDSDIN1000 | WHP-10 CALCULATION NOTE FOR CHOKE VALVES - ICR | 10 | 2022-03-22 | 2022-04-05 | 2022-05-26 | 2022-06-08 | 44
0 | EDSDIN1030 | WHP-10 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - ICR | 15 | 2022-03-28 | 2022-04-18 | 2022-08-16 | 2022-09-05 | 95
0 | EDSDIN1015 | WHP-10 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - ICR | 10 | 2022-04-15 | 2022-04-29 | 2022-09-06 | 2022-09-19 | 96
0 | EDSDIN1005 | WHP-10 CALCULATION NOTE FOR CHOKE VALVES - IFA | 10 | 2022-04-19 | 2022-05-06 | 2022-06-23 | 2022-07-06 | 44
0 | EDSDIN1045 | WHP-10 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - ICR | 15 | 2022-04-13 | 2022-05-09 | 2022-09-23 | 2022-10-13 | 111
0 | EDSDIN1035 | WHP-10 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - IFA | 15 | 2022-05-05 | 2022-05-26 | 2022-09-27 | 2022-10-17 | 100
0 | EDSDIN1020 | WHP-10 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - IFA | 10 | 2022-05-18 | 2022-06-01 | 2022-10-13 | 2022-10-26 | 103
0 | EDSDIN1010 | WHP-10 CALCULATION NOTE FOR CHOKE VALVES - IFC | 10 | 2022-05-20 | 2022-06-03 | 2022-07-26 | 2022-08-08 | 44
0 | EDSDIN1050 | WHP-10 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - IFA | 15 | 2022-05-23 | 2022-06-13 | 2022-10-28 | 2022-11-17 | 111
0 | EDSDIN1025 | WHP-10 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - IFC | 10 | 2022-06-15 | 2022-06-29 | 2022-11-10 | 2022-11-23 | 103
0 | EDSDIN1040 | WHP-10 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - IFC | 15 | 2022-06-09 | 2022-06-30 | 2022-11-01 | 2022-11-21 | 100
0 | EDSDIN1055 | WHP-10 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - IFC | 15 | 2022-06-27 | 2022-07-21 | 2022-12-06 | 2022-12-26 | 111
INDEX / NARRATIVE |  |  | 50 | 2022-08-22 | 2022-10-31 | 2022-11-08 | 2023-01-24 | 60
0 | EDSDIN1060 | WHP-10 INSTRUMENT INDEX - ICR | 10 | 2022-08-22 | 2022-09-05 | 2022-11-08 | 2022-11-21 | 56
0 | EDSDIN1075 | WHP-10 FIRE & GAS INDEX -ICR | 10 | 2022-08-22 | 2022-09-05 | 2022-11-08 | 2022-11-21 | 56
0 | EDSDIN1080 | WHP-10 FIRE & GAS INDEX -IFA | 10 | 2022-09-19 | 2022-10-03 | 2022-12-08 | 2022-12-21 | 56
0 | EDSDIN1065 | WHP-10 INSTRUMENT INDEX - IFA | 10 | 2022-09-19 | 2022-10-03 | 2022-12-14 | 2022-12-27 | 60
0 | EDSDIN1070 | WHP-10 INSTRUMENT INDEX - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-01-11 | 2023-01-24 | 60
0 | EDSDIN1085 | WHP-10 FIRE & GAS INDEX - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-01-05 | 2023-01-18 | 56
DATA SHEET |  |  | 92 | 2022-03-03 | 2022-07-19 | 2022-05-12 | 2023-01-25 | 135
0 | EDSDIN1100 | WHP-10 DATASHEETS FOR HIPPS VALVES - ICR | 11 | 2022-03-03 | 2022-03-18 | 2022-05-12 | 2022-05-26 | 47
0 | EDSDIN1160 | WHP-10 DATASHEETS FOR MOV - ICR | 10 | 2022-03-23 | 2022-04-06 | 2022-05-26 | 2022-06-08 | 43
0 | EDSDIN1145 | WHP-10 DATASHEETS FOR ACTUATED ON/OFF VALVES - ICR | 10 | 2022-03-24 | 2022-04-07 | 2022-05-27 | 2022-06-09 | 43
0 | EDSDIN1190 | WHP-10 DATASHEETS FOR FLOW CHOKE VALVE - ICR | 8 | 2022-03-28 | 2022-04-07 | 2022-06-02 | 2022-06-13 | 45
0 | EDSDIN1205 | WHP-10 DATASHEETS FOR SOLENOID OPERATED VALVES - ICR | 8 | 2022-03-28 | 2022-04-07 | 2022-06-02 | 2022-06-13 | 45
0 | EDSDIN1175 | WHP-10 DATASHEETS FOR PRESSURE RELIEF VALVES - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-08-16 | 2022-08-29 | 95
0 | EDSDIN1130 | WHP-10 DATASHEETS FOR CHOKE VALVES - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-06-01 | 2022-06-14 | 44
0 | EDSDIN1115 | WHP-10 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-06-06 | 2022-06-17 | 46
0 | EDSDIN1220 | WHP-10 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - ICR | 8 | 2022-03-31 | 2022-04-12 | 2022-06-06 | 2022-06-15 | 44
0 | EDSDIN1400 | WHP-10 DATASHEETS FOR ELECTRONIC SOUNDER - ICR | 9 | 2022-03-31 | 2022-04-13 | 2022-10-17 | 2022-10-27 | 136
0 | EDSDIN1105 | WHP-10 DATASHEETS FOR HIPPS VALVES - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-07-14 | 2022-07-27 | 68
0 | EDSDIN1415 | WHP-10 DATASHEETS FOR EMERGENCY S/D PB - ICR | 10 | 2022-04-04 | 2022-04-18 | 2022-10-19 | 2022-11-01 | 136
0 | EDSDIN1310 | WHP-10 DATASHEETS FOR TEMPERATURE TRANSMITTERS - ICR | 8 | 2022-04-07 | 2022-04-19 | 2022-08-31 | 2022-09-09 | 98
0 | EDSDIN1250 | WHP-10 DATASHEETS FOR PRESSURE GAUGES - ICR | 10 | 2022-04-06 | 2022-04-20 | 2022-08-26 | 2022-09-08 | 96
0 | EDSDIN1430 | WHP-10 DATASHEETS FOR FLAMMABLE GAS DETECTOR - ICR | 10 | 2022-04-06 | 2022-04-20 | 2022-10-21 | 2022-11-03 | 136
0 | EDSDIN1460 | WHP-10 DATASHEETS FOR FLASHING BEACON - ICR | 9 | 2022-04-11 | 2022-04-22 | 2022-10-26 | 2022-11-07 | 136
0 | EDSDIN1445 | WHP-10 DATASHEETS FOR FIRE GAS DETECTOR - ICR | 10 | 2022-04-08 | 2022-04-22 | 2022-10-25 | 2022-11-07 | 136
0 | EDSDIN1280 | WHP-10 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - ICR | 10 | 2022-04-11 | 2022-04-25 | 2022-09-15 | 2022-09-28 | 107
0 | EDSDIN1475 | WHP-10 DATASHEETS FOR HEAT DETECTOR - ICR | 9 | 2022-04-12 | 2022-04-25 | 2022-10-27 | 2022-11-08 | 136
0 | EDSDIN1490 | WHP-10 DATASHEETS FOR MAN ON BOARD PB - ICR | 9 | 2022-04-12 | 2022-04-25 | 2022-10-27 | 2022-11-08 | 136
0 | EDSDIN1235 | WHP-10 DATASHEETS FOR FLOW RESTRICTION ORIFICE - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-09-13 | 2022-09-26 | 104
0 | EDSDIN1340 | WHP-10 DATASHEETS FOR LEVEL GAUGES - ICR | 7 | 2022-04-15 | 2022-04-26 | 2022-09-08 | 2022-09-16 | 98
0 | EDSDIN1295 | WHP-10 DATASHEETS FOR TEMPERATURE GAUGES - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-09-07 | 2022-09-20 | 100
0 | EDSDIN1505 | WHP-10 DATASHEETS FOR TOXIC GAS DETECTOR - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-10-27 | 2022-11-09 | 136
0 | EDSDIN1355 | WHP-10 DATASHEETS FOR LEVEL TRANSMITTERS - ICR | 7 | 2022-04-18 | 2022-04-27 | 2022-09-08 | 2022-09-16 | 97
0 | EDSDIN1520 | WHP-10 DATASHEETS FOR MANUAL ALARM CALL POINT - ICR | 10 | 2022-04-14 | 2022-04-28 | 2022-10-31 | 2022-11-11 | 136
0 | EDSDIN1325 | WHP-10 DATASHEETS FOR PIG SIGNALLER - ICR | 10 | 2022-04-19 | 2022-05-06 | 2022-10-03 | 2022-10-14 | 113
0 | EDSDIN1370 | WHP-10 DATASHEETS FOR FLOW SWITCHES - ICR | 10 | 2022-04-20 | 2022-05-09 | 2022-10-19 | 2022-11-01 | 124
0 | EDSDIN1165 | WHP-10 DATASHEETS FOR MOV - IFA | 10 | 2022-04-20 | 2022-05-09 | 2022-07-21 | 2022-08-03 | 60
0 | EDSDIN1150 | WHP-10 DATASHEETS FOR ACTUATED ON/OFF VALVES - IFA | 10 | 2022-04-21 | 2022-05-10 | 2022-07-21 | 2022-08-03 | 59
0 | EDSDIN1195 | WHP-10 DATASHEETS FOR FLOW CHOKE VALVE - IFA | 10 | 2022-04-21 | 2022-05-10 | 2022-07-21 | 2022-08-03 | 59
0 | EDSDIN1210 | WHP-10 DATASHEETS FOR SOLENOID OPERATED VALVES - IFA | 10 | 2022-04-21 | 2022-05-10 | 2022-07-21 | 2022-08-03 | 59
0 | EDSDIN1110 | WHP-10 DATASHEETS FOR HIPPS VALVES - IFC | 15 | 2022-04-15 | 2022-05-11 | 2022-08-08 | 2022-08-26 | 75
0 | EDSDIN1265 | WHP-10 DATASHEETS FOR CORROSION MONITOR - ICR | 10 | 2022-04-22 | 2022-05-11 | 2022-09-28 | 2022-10-11 | 107
0 | EDSDIN1385 | WHP-10 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - ICR | 10 | 2022-04-25 | 2022-05-12 | 2022-10-24 | 2022-11-04 | 124
0 | EDSDIN1135 | WHP-10 DATASHEETS FOR CHOKE VALVES - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-07-04 | 2022-07-20 | 47
0 | EDSDIN1180 | WHP-10 DATASHEETS FOR PRESSURE RELIEF VALVES - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-10-12 | 2022-10-25 | 116
0 | EDSDIN1405 | WHP-10 DATASHEETS FOR ELECTRONIC SOUNDER - IFA | 9 | 2022-04-27 | 2022-05-13 | 2022-11-30 | 2022-12-14 | 149
0 | EDSDIN1225 | WHP-10 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-07-21 | 2022-08-03 | 56
0 | EDSDIN1120 | WHP-10 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-07-21 | 2022-08-03 | 54
0 | EDSDIN1420 | WHP-10 DATASHEETS FOR EMERGENCY S/D PB - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-11-28 | 2022-12-13 | 144
0 | EDSDIN1315 | WHP-10 DATASHEETS FOR TEMPERATURE TRANSMITTERS - IFA | 10 | 2022-05-06 | 2022-05-20 | 2022-10-13 | 2022-10-26 | 111
0 | EDSDIN1435 | WHP-10 DATASHEETS FOR FLAMMABLE GAS DETECTOR - IFA | 10 | 2022-05-09 | 2022-05-23 | 2022-11-28 | 2022-12-13 | 142
0 | EDSDIN1255 | WHP-10 DATASHEETS FOR PRESSURE GAUGES - IFA | 10 | 2022-05-09 | 2022-05-23 | 2022-10-18 | 2022-10-31 | 113
0 | EDSDIN1450 | WHP-10 DATASHEETS FOR FIRE GAS DETECTOR - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-11-28 | 2022-12-13 | 140
0 | EDSDIN1465 | WHP-10 DATASHEETS FOR FLASHING BEACON - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-11-28 | 2022-12-13 | 140
0 | EDSDIN1495 | WHP-10 DATASHEETS FOR MAN ON BOARD PB - IFA | 9 | 2022-05-12 | 2022-05-25 | 2022-11-30 | 2022-12-14 | 141
0 | EDSDIN1480 | WHP-10 DATASHEETS FOR HEAT DETECTOR - IFA | 10 | 2022-05-12 | 2022-05-26 | 2022-11-28 | 2022-12-13 | 139
0 | EDSDIN1285 | WHP-10 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - IFA | 10 | 2022-05-12 | 2022-05-26 | 2022-10-13 | 2022-10-26 | 107
0 | EDSDIN1300 | WHP-10 DATASHEETS FOR TEMPERATURE GAUGES - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-10-14 | 2022-10-27 | 107
0 | EDSDIN1510 | WHP-10 DATASHEETS FOR TOXIC GAS DETECTOR - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-11-28 | 2022-12-13 | 138
0 | EDSDIN1345 | WHP-10 DATASHEETS FOR LEVEL GAUGES - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-10-05 | 2022-10-18 | 100
0 | EDSDIN1360 | WHP-10 DATASHEETS FOR LEVEL TRANSMITTERS - IFA | 10 | 2022-05-16 | 2022-05-30 | 2022-10-12 | 2022-10-25 | 104
0 | EDSDIN1525 | WHP-10 DATASHEETS FOR MANUAL ALARM CALL POINT - IFA | 10 | 2022-05-17 | 2022-05-31 | 2022-11-28 | 2022-12-13 | 136
0 | EDSDIN1330 | WHP-10 DATASHEETS FOR PIG SIGNALLER - IFA | 10 | 2022-05-20 | 2022-06-03 | 2022-11-23 | 2022-12-08 | 130
0 | EDSDIN1375 | WHP-10 DATASHEETS FOR FLOW SWITCHES - IFA | 10 | 2022-05-23 | 2022-06-06 | 2022-12-08 | 2022-12-21 | 138
0 | EDSDIN1240 | WHP-10 DATASHEETS FOR FLOW RESTRICTION ORIFICE - IFA | 10 | 2022-05-24 | 2022-06-07 | 2022-10-11 | 2022-10-24 | 97
0 | EDSDIN1270 | WHP-10 DATASHEETS FOR CORROSION MONITOR - IFA | 10 | 2022-05-25 | 2022-06-08 | 2022-11-09 | 2022-11-22 | 117
0 | EDSDIN1390 | WHP-10 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - IFA | 10 | 2022-05-26 | 2022-06-09 | 2022-11-28 | 2022-12-13 | 129
0 | EDSDIN1170 | WHP-10 DATASHEETS FOR MOV - IFC | 15 | 2022-05-23 | 2022-06-13 | 2022-08-18 | 2022-09-07 | 60
0 | EDSDIN1155 | WHP-10 DATASHEETS FOR ACTUATED ON/OFF VALVES - IFC | 15 | 2022-05-24 | 2022-06-14 | 2022-08-18 | 2022-09-07 | 59
0 | EDSDIN1200 | WHP-10 DATASHEETS FOR FLOW CHOKE VALVE - IFC | 15 | 2022-05-24 | 2022-06-14 | 2022-08-18 | 2022-09-07 | 59
0 | EDSDIN1215 | WHP-10 DATASHEETS FOR SOLENOID OPERATED VALVES - IFC | 15 | 2022-05-24 | 2022-06-14 | 2022-08-18 | 2022-09-07 | 59
0 | EDSDIN1185 | WHP-10 DATASHEETS FOR PRESSURE RELIEF VALVES - IFC | 15 | 2022-05-26 | 2022-06-16 | 2022-11-09 | 2022-11-29 | 116
0 | EDSDIN1410 | WHP-10 DATASHEETS FOR ELECTRONIC SOUNDER - IFC | 14 | 2022-05-27 | 2022-06-16 | 2022-12-29 | 2023-01-17 | 149
0 | EDSDIN1140 | WHP-10 DATASHEETS FOR CHOKE VALVES - IFC | 15 | 2022-05-26 | 2022-06-16 | 2022-08-04 | 2022-08-24 | 47
0 | EDSDIN1230 | WHP-10 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - IFC | 15 | 2022-05-27 | 2022-06-17 | 2022-08-18 | 2022-09-07 | 56
0 | EDSDIN1125 | WHP-10 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - IFC | 15 | 2022-06-01 | 2022-06-22 | 2022-08-18 | 2022-09-07 | 53
0 | EDSDIN1425 | WHP-10 DATASHEETS FOR EMERGENCY S/D PB - IFC | 15 | 2022-06-02 | 2022-06-23 | 2022-12-28 | 2023-01-17 | 144
0 | EDSDIN1260 | WHP-10 DATASHEETS FOR PRESSURE GAUGES - IFC | 15 | 2022-06-06 | 2022-06-27 | 2022-11-15 | 2022-12-07 | 113
0 | EDSDIN1440 | WHP-10 DATASHEETS FOR FLAMMABLE GAS DETECTOR - IFC | 15 | 2022-06-06 | 2022-06-27 | 2022-12-28 | 2023-01-17 | 142
0 | EDSDIN1500 | WHP-10 DATASHEETS FOR MAN ON BOARD PB - IFC | 14 | 2022-06-08 | 2022-06-28 | 2022-12-29 | 2023-01-17 | 141
0 | EDSDIN1470 | WHP-10 DATASHEETS FOR FLASHING BEACON - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-12-28 | 2023-01-17 | 140
0 | EDSDIN1455 | WHP-10 DATASHEETS FOR FIRE GAS DETECTOR - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-12-28 | 2023-01-17 | 140
0 | EDSDIN1320 | WHP-10 DATASHEETS FOR TEMPERATURE TRANSMITTERS - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-11-10 | 2022-11-30 | 108
0 | EDSDIN1290 | WHP-10 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - IFC | 15 | 2022-06-09 | 2022-06-30 | 2022-11-10 | 2022-11-30 | 107
0 | EDSDIN1485 | WHP-10 DATASHEETS FOR HEAT DETECTOR - IFC | 15 | 2022-06-09 | 2022-06-30 | 2022-12-28 | 2023-01-17 | 139
0 | EDSDIN1350 | WHP-10 DATASHEETS FOR LEVEL GAUGES - IFC | 15 | 2022-06-10 | 2022-07-01 | 2022-11-02 | 2022-11-22 | 100
0 | EDSDIN1305 | WHP-10 DATASHEETS FOR TEMPERATURE GAUGES - IFC | 15 | 2022-06-10 | 2022-07-01 | 2022-11-11 | 2022-12-05 | 107
0 | EDSDIN1515 | WHP-10 DATASHEETS FOR TOXIC GAS DETECTOR - IFC | 15 | 2022-06-10 | 2022-07-01 | 2022-12-28 | 2023-01-17 | 138
0 | EDSDIN1365 | WHP-10 DATASHEETS FOR LEVEL TRANSMITTERS - IFC | 15 | 2022-06-13 | 2022-07-04 | 2022-11-09 | 2022-11-29 | 104
0 | EDSDIN1530 | WHP-10 DATASHEETS FOR MANUAL ALARM CALL POINT- IFC | 15 | 2022-06-14 | 2022-07-05 | 2022-12-28 | 2023-01-17 | 136
0 | EDSDIN1335 | WHP-10 DATASHEETS FOR PIG SIGNALLER - IFC | 15 | 2022-06-17 | 2022-07-13 | 2022-12-23 | 2023-01-12 | 130
0 | EDSDIN1380 | WHP-10 DATASHEETS FOR FLOW SWITCHES - IFC | 15 | 2022-06-20 | 2022-07-14 | 2023-01-05 | 2023-01-25 | 138
0 | EDSDIN1245 | WHP-10 DATASHEETS FOR FLOW RESTRICTION ORIFICE - IFC | 10 | 2022-06-29 | 2022-07-18 | 2022-11-10 | 2022-11-23 | 93
0 | EDSDIN1275 | WHP-10 DATASHEETS FOR CORROSION MONITOR - IFC | 15 | 2022-06-22 | 2022-07-18 | 2022-12-09 | 2022-12-29 | 117
0 | EDSDIN1395 | WHP-10 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - IFC | 15 | 2022-06-23 | 2022-07-19 | 2022-12-28 | 2023-01-17 | 129
SCHEDULE / MTO |  |  | 98 | 2022-06-03 | 2022-10-24 | 2022-12-27 | 2023-04-27 | 130
0 | EDSDIN1600 | WHP-10 INSTRUMENT 1ST MTO | 10 | 2022-06-03 | 2022-06-17 | 2022-12-27 | 2023-01-09 | 142
0 | EDSDIN1610 | WHP-10 INSTRUMENT CABLE SCHEDULE - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-02-15 | 2023-02-28 | 132
0 | EDSDIN1625 | WHP-10 JUNCTION BOX SCHEDULE - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-02-15 | 2023-02-28 | 132
0 | EDSDIN1640 | WHP-10 TUBE SCHEDULE - ICR | 10 | 2022-08-15 | 2022-08-29 | 2023-02-15 | 2023-02-28 | 130
0 | EDSDIN1605 | WHP-10 INSTRUMENT FINAL MTO | 10 | 2022-09-05 | 2022-09-19 | 2023-01-20 | 2023-02-02 | 97
0 | EDSDIN1615 | WHP-10 INSTRUMENT CABLE SCHEDULE - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-15 | 2023-03-28 | 132
0 | EDSDIN1630 | WHP-10 JUNCTION BOX SCHEDULE - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-15 | 2023-03-28 | 132
0 | EDSDIN1645 | WHP-10 TUBE SCHEDULE - IFA | 10 | 2022-09-12 | 2022-09-26 | 2023-03-15 | 2023-03-28 | 130
0 | EDSDIN1620 | WHP-10 INSTRUMENT CABLE SCHEDULE - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-04-12 | 2023-04-27 | 132
0 | EDSDIN1635 | WHP-10 JUNCTION BOX SCHEDULE - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-04-12 | 2023-04-27 | 132
0 | EDSDIN1650 | WHP-10 TUBE SCHEDULE - IFC | 10 | 2022-10-10 | 2022-10-24 | 2023-04-12 | 2023-04-27 | 130
LIST |  |  | 95 | 2022-08-22 | 2023-01-04 | 2022-12-14 | 2023-04-27 | 80
0 | EDSDIN1700 | WHP-10 I/O LIST FOR DCS - ICR | 20 | 2022-08-22 | 2022-09-19 | 2022-12-14 | 2023-01-10 | 80
0 | EDSDIN1715 | WHP-10 I/O LIST FOR ESD SYSTEM - ICR | 20 | 2022-08-29 | 2022-09-26 | 2022-12-21 | 2023-01-17 | 80
0 | EDSDIN1730 | WHP-10 I/O LIST FOR F&G SYSTEM - ICR | 20 | 2022-09-05 | 2022-10-03 | 2022-12-28 | 2023-01-24 | 80
0 | EDSDIN1745 | WHP-10 I/O LIST FOR HIPPS - ICR | 20 | 2022-09-12 | 2022-10-10 | 2023-01-04 | 2023-01-31 | 80
0 | EDSDIN1705 | WHP-10 I/O LIST FOR DCS - IFA | 20 | 2022-10-03 | 2022-10-31 | 2023-02-15 | 2023-03-14 | 95
0 | EDSDIN1720 | WHP-10 I/O LIST FOR ESD SYSTEM - IFA | 20 | 2022-10-10 | 2022-11-07 | 2023-02-15 | 2023-03-14 | 90
0 | EDSDIN1735 | WHP-10 I/O LIST FOR F&G SYSTEM - IFA | 20 | 2022-10-17 | 2022-11-14 | 2023-02-15 | 2023-03-14 | 85
0 | EDSDIN1750 | WHP-10 I/O LIST FOR HIPPS - IFA | 20 | 2022-10-24 | 2022-11-21 | 2023-02-15 | 2023-03-14 | 80
0 | EDSDIN1710 | WHP-10 I/O LIST FOR DCS - IFC | 20 | 2022-11-14 | 2022-12-14 | 2023-03-29 | 2023-04-27 | 95
0 | EDSDIN1725 | WHP-10 I/O LIST FOR ESD SYSTEM - IFC | 20 | 2022-11-21 | 2022-12-21 | 2023-03-29 | 2023-04-27 | 90
0 | EDSDIN1740 | WHP-10 I/O LIST FOR F&G SYSTEM - IFC | 20 | 2022-11-28 | 2022-12-28 | 2023-03-29 | 2023-04-27 | 85
0 | EDSDIN1755 | WHP-10 I/O LIST FOR HIPPS - IFC | 20 | 2022-12-07 | 2023-01-04 | 2023-03-29 | 2023-04-27 | 80
DRAWINGS |  |  | 194 | 2022-04-01 | 2023-01-10 | 2022-08-30 | 2023-08-17 | 152
DIAGRAM |  |  | 194 | 2022-04-01 | 2023-01-10 | 2022-08-30 | 2023-08-17 | 152
0 | EDSGIN1015 | WHP-10 INSTRUMENT CABLE BLOCK DIAGRAM - ICR | 15 | 2022-04-01 | 2022-04-22 | 2022-08-30 | 2022-09-19 | 101
0 | EDSGIN1000 | WHP-10 LEVEL SKETCH- ICR | 12 | 2022-04-06 | 2022-04-22 | 2022-10-17 | 2022-11-01 | 132
0 | EDSGIN1030 | WHP-10 TUBING BLOCK DIAGRAM - ICR | 15 | 2022-04-22 | 2022-05-18 | 2022-09-27 | 2022-10-17 | 106
0 | EDSGIN1005 | WHP-10 LEVEL SKETCH- IFA | 12 | 2022-05-11 | 2022-05-27 | 2022-11-16 | 2022-12-05 | 132
0 | EDSGIN1020 | WHP-10 INSTRUMENT CABLE BLOCK DIAGRAM - IFA | 15 | 2022-05-11 | 2022-06-01 | 2022-11-01 | 2022-11-21 | 121
0 | EDSGIN1035 | WHP-10 TUBING BLOCK DIAGRAM - IFA | 15 | 2022-06-01 | 2022-06-22 | 2022-11-01 | 2022-11-21 | 106
0 | EDSGIN1010 | WHP-10 LEVEL SKETCH- IFC | 12 | 2022-06-10 | 2022-06-28 | 2022-12-20 | 2023-01-04 | 132
0 | EDSGIN1025 | WHP-10 INSTRUMENT CABLE BLOCK DIAGRAM - IFC | 20 | 2022-06-15 | 2022-07-18 | 2022-12-08 | 2023-01-04 | 121
0 | EDSGIN1040 | WHP-10 TUBING BLOCK DIAGRAM - IFC | 20 | 2022-07-06 | 2022-08-08 | 2022-12-08 | 2023-01-04 | 106
0 | EDSGIN1045 | WHP-10 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - ICR | 15 | 2022-08-08 | 2022-08-29 | 2023-01-05 | 2023-01-25 | 106
0 | EDSGIN1060 | WHP-10 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - ICR | 15 | 2022-08-12 | 2022-09-02 | 2023-01-11 | 2023-01-31 | 106
0 | EDSGIN1075 | WHP-10 PROCESS & HYDRAULIC HOOK-UPS DRAWING - ICR | 15 | 2022-08-19 | 2022-09-09 | 2023-01-18 | 2023-02-07 | 106
0 | EDSGIN1050 | WHP-10 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - IFA | 15 | 2022-09-12 | 2022-10-03 | 2023-04-14 | 2023-05-08 | 152
0 | EDSGIN1065 | WHP-10 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - IFA | 15 | 2022-09-16 | 2022-10-07 | 2023-05-09 | 2023-05-29 | 163
0 | EDSGIN1080 | WHP-10 PROCESS & HYDRAULIC HOOK-UPS DRAWING - IFA | 15 | 2022-09-23 | 2022-10-14 | 2023-02-22 | 2023-03-14 | 106
0 | EDSGIN1090 | WHP-10 INSTRUMENT LOOP DIAGRAMS - DCS - ICR | 10 | 2022-10-07 | 2022-10-21 | 2023-01-27 | 2023-02-09 | 78
0 | EDSGIN1105 | WHP-10 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - ICR | 10 | 2022-10-11 | 2022-10-25 | 2023-01-31 | 2023-02-13 | 78
0 | EDSGIN1120 | WHP-10 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - ICR | 10 | 2022-10-13 | 2022-10-27 | 2023-02-02 | 2023-02-15 | 78
0 | EDSGIN1135 | WHP-10 INSTRUMENT LOOP DIAGRAMS - HIPPS - ICR | 10 | 2022-10-21 | 2022-11-04 | 2023-02-08 | 2023-02-21 | 76
0 | EDSGIN1055 | WHP-10 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - IFC | 20 | 2022-10-17 | 2022-11-14 | 2023-05-23 | 2023-06-19 | 152
0 | EDSGIN1070 | WHP-10 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - IFC | 20 | 2022-10-21 | 2022-11-18 | 2023-06-13 | 2023-07-13 | 163
0 | EDSGIN1095 | WHP-10 INSTRUMENT LOOP DIAGRAMS - DCS - IFA | 10 | 2022-11-04 | 2022-11-18 | 2023-03-08 | 2023-03-21 | 86
0 | EDSGIN1110 | WHP-10 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - IFA | 10 | 2022-11-08 | 2022-11-22 | 2023-03-08 | 2023-03-21 | 84
0 | EDSGIN1125 | WHP-10 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - IFA | 10 | 2022-11-10 | 2022-11-24 | 2023-06-26 | 2023-07-12 | 158
0 | EDSGIN1085 | WHP-10 PROCESS & HYDRAULIC HOOK-UPS DRAWING - IFC | 20 | 2022-10-28 | 2022-11-25 | 2023-03-29 | 2023-04-27 | 106
0 | EDSGIN1140 | WHP-10 INSTRUMENT LOOP DIAGRAMS - HIPPS - IFA | 10 | 2022-11-18 | 2022-12-06 | 2023-03-08 | 2023-03-21 | 76
0 | EDSGIN1100 | WHP-10 INSTRUMENT LOOP DIAGRAMS - DCS - IFC | 15 | 2022-12-06 | 2022-12-27 | 2023-04-05 | 2023-04-27 | 86
0 | EDSGIN1115 | WHP-10 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - IFC | 15 | 2022-12-08 | 2022-12-29 | 2023-04-05 | 2023-04-27 | 84
0 | EDSGIN1130 | WHP-10 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - IFC | 15 | 2022-12-12 | 2023-01-02 | 2023-07-28 | 2023-08-17 | 158
0 | EDSGIN1145 | WHP-10 INSTRUMENT LOOP DIAGRAMS - HIPPS - IFC | 15 | 2022-12-20 | 2023-01-10 | 2023-04-05 | 2023-04-27 | 76
LAYOUT |  |  | 85 | 2022-06-30 | 2022-11-01 | 2022-10-11 | 2023-04-27 | 124
0 | EDSGIN1215 | WHP-10 INSTRUMENT CABLE ROUTING LAYOUT - ICR | 15 | 2022-06-30 | 2022-07-26 | 2022-10-14 | 2022-11-03 | 73
0 | EDSGIN1230 | WHP-10 INSTRUMENT LOCATION LAYOUTS - ICR | 15 | 2022-07-07 | 2022-08-02 | 2023-01-12 | 2023-02-01 | 130
0 | EDSGIN1245 | WHP-10 TUBE ROUTING LAYOUT - ICR | 15 | 2022-07-18 | 2022-08-08 | 2023-01-18 | 2023-02-07 | 130
0 | EDSGIN1200 | WHP-10 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - ICR | 15 | 2022-07-26 | 2022-08-16 | 2022-10-11 | 2022-10-31 | 55
0 | EDSGIN1265 | WHP-10 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - ICR | 15 | 2022-07-26 | 2022-08-16 | 2022-10-11 | 2022-10-31 | 55
0 | EDSGIN1220 | WHP-10 INSTRUMENT CABLE ROUTING LAYOUT - IFA | 10 | 2022-08-09 | 2022-08-23 | 2022-11-18 | 2022-12-05 | 73
0 | EDSGIN1235 | WHP-10 INSTRUMENT LOCATION LAYOUTS - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-02-22 | 2023-03-14 | 134
0 | EDSGIN1250 | WHP-10 TUBE ROUTING LAYOUT - IFA | 15 | 2022-08-22 | 2022-09-12 | 2023-02-22 | 2023-03-14 | 130
0 | EDSGIN1205 | WHP-10 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - IFA | 15 | 2022-08-30 | 2022-09-20 | 2022-11-21 | 2022-12-13 | 59
0 | EDSGIN1275 | WHP-10 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - IFA | 15 | 2022-08-30 | 2022-09-20 | 2022-11-15 | 2022-12-07 | 55
0 | EDSGIN1225 | WHP-10 INSTRUMENT CABLE ROUTING LAYOUT - IFC | 20 | 2022-09-06 | 2022-10-04 | 2022-12-20 | 2023-01-16 | 73
0 | EDSGIN1240 | WHP-10 INSTRUMENT LOCATION LAYOUTS - IFC | 20 | 2022-09-20 | 2022-10-18 | 2023-03-29 | 2023-04-27 | 134
0 | EDSGIN1255 | WHP-10 TUBE ROUTING LAYOUT - IFC | 20 | 2022-09-26 | 2022-10-24 | 2023-03-29 | 2023-04-27 | 130
0 | EDSGIN1210 | WHP-10 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - IFC | 20 | 2022-10-04 | 2022-11-01 | 2022-12-28 | 2023-01-24 | 59
0 | EDSGIN1285 | WHP-10 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - IFC | 20 | 2022-10-04 | 2022-11-01 | 2022-12-22 | 2023-01-18 | 55
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDSGIN2000 | WHP-10 INSTRUMENT MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDSGIN2005 | WHP-10 INSTRUMENT MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDSGIN2010 | WHP-10 INSTRUMENT MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
TELECOM |  |  | 156 | 2022-06-03 | 2023-01-16 | 2022-09-27 | 2023-04-27 | 72
DOCUMENTS |  |  | 96 | 2022-06-03 | 2022-10-20 | 2022-09-27 | 2023-04-27 | 132
LIST/SCHEDULE |  |  | 96 | 2022-06-03 | 2022-10-20 | 2022-09-27 | 2023-04-27 | 132
0 | EDSDTE1000 | WHP-10 TELECOMMUNICATION - 1ST MTO | 10 | 2022-06-03 | 2022-06-17 | 2022-09-27 | 2022-10-10 | 79
0 | EDSDTE1010 | WHP-10 TELECOM EQUIPMENT LIST - ICR | 10 | 2022-06-17 | 2022-07-01 | 2022-10-11 | 2022-10-24 | 79
0 | EDSDTE1015 | WHP-10 TELECOM EQUIPMENT LIST - IFA | 10 | 2022-07-20 | 2022-08-03 | 2023-03-01 | 2023-03-14 | 158
0 | EDSDTE1025 | WHP-10 TELECOM CABLE SCHEDULE - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-02-01 | 2023-02-14 | 122
0 | EDSDTE1020 | WHP-10 TELECOM EQUIPMENT LIST - IFC | 20 | 2022-08-17 | 2022-09-14 | 2023-03-29 | 2023-04-27 | 158
0 | EDSDTE1005 | WHP-10 TELECOMMUNICATION - FINAL MTO | 9 | 2022-09-06 | 2022-09-19 | 2023-01-23 | 2023-02-02 | 97
0 | EDSDTE1030 | WHP-10 TELECOM CABLE SCHEDULE - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-15 | 2023-03-28 | 132
0 | EDSDTE1035 | WHP-10 TELECOM CABLE SCHEDULE - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-04-12 | 2023-04-27 | 132
DRAWINGS |  |  | 86 | 2022-07-20 | 2022-11-17 | 2022-11-08 | 2023-04-27 | 112
LAYOUT |  |  | 86 | 2022-07-20 | 2022-11-17 | 2022-11-08 | 2023-04-27 | 112
0 | EDSGTE1015 | WHP-10 TELECOM EQUIPMENT LOCATION LAYOUTS - ICR | 10 | 2022-07-20 | 2022-08-03 | 2022-11-08 | 2022-11-21 | 79
0 | EDSGTE1000 | WHP-10 TELECOM CABLE ROUTING LAYOUT - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-01-18 | 2023-01-31 | 112
0 | EDSGTE1020 | WHP-10 TELECOM EQUIPMENT LOCATION LAYOUTS - IFA | 10 | 2022-08-17 | 2022-08-31 | 2022-12-08 | 2022-12-21 | 79
0 | EDSGTE1045 | WHP-10 DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - ICR | 10 | 2022-08-25 | 2022-09-08 | 2023-02-01 | 2023-02-14 | 112
0 | EDSGTE1030 | WHP-10 FIBER OPTIC ALLOCATION DRAWING - ICR | 10 | 2022-08-25 | 2022-09-08 | 2023-02-15 | 2023-02-28 | 122
0 | EDSGTE1005 | WHP-10 TELECOM CABLE ROUTING LAYOUT - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-15 | 2023-03-28 | 132
0 | EDSGTE1025 | WHP-10 TELECOM EQUIPMENT LOCATION LAYOUTS - IFC | 10 | 2022-09-14 | 2022-09-28 | 2023-01-05 | 2023-01-18 | 79
0 | EDSGTE1035 | WHP-10 FIBER OPTIC ALLOCATION DRAWING - IFA | 10 | 2022-09-22 | 2022-10-06 | 2023-03-15 | 2023-03-28 | 122
0 | EDSGTE1050 | WHP-10 DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - IFA | 10 | 2022-09-22 | 2022-10-06 | 2023-03-01 | 2023-03-14 | 112
0 | EDSGTE1010 | WHP-10 TELECOM CABLE ROUTING LAYOUT - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-04-12 | 2023-04-27 | 132
0 | EDSGTE1040 | WHP-10 FIBER OPTIC ALLOCATION DRAWING - IFC | 10 | 2022-10-20 | 2022-11-03 | 2023-04-12 | 2023-04-27 | 122
0 | EDSGTE1055 | WHP-10 DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - IFC | 20 | 2022-10-20 | 2022-11-17 | 2023-03-29 | 2023-04-27 | 112
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDSGTE2000 | WHP-10 TELECOM MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDSGTE2005 | WHP-10 TELECOM MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDSGTE2010 | WHP-10 TELECOM MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
STRUCTURAL |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-05-25 | 2023-06-21 | 108
3D MODEL DEVELOPMENT |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-05-25 | 2023-03-28 | 49
0 | EDSDSR3000 | WHP-10 3D MODEL DEVELOPMENT - STRUCTURAL | 215 | 2022-03-14 | 2023-01-19 | 2022-05-25 | 2023-03-28 | 49
DOCUMENTS |  |  | 142 | 2022-05-09 | 2022-11-28 | 2022-07-19 | 2023-04-28 | 106
REPORTS |  |  | 142 | 2022-05-09 | 2022-11-28 | 2022-07-19 | 2023-04-28 | 106
0 | EDSDSR1000 | WHP-10 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - ICR | 20 | 2022-05-09 | 2022-06-06 | 2022-07-19 | 2022-08-15 | 48
0 | EDSDSR1135 | WHP-10 TOPSIDES LIFT ANALYSES REPORT - ICR | 20 | 2022-05-16 | 2022-06-13 | 2022-08-25 | 2022-09-21 | 70
0 | EDSDSR1195 | WHP-10 TOPSIDES LINEAR BLAST ANALYSIS REPORT - ICR | 20 | 2022-05-16 | 2022-06-13 | 2022-07-26 | 2022-08-22 | 48
0 | EDSDSR1090 | WHP-10 HELIDECK DESIGN REPORT - ICR | 20 | 2022-05-23 | 2022-06-20 | 2022-09-08 | 2022-10-05 | 75
0 | EDSDSR1150 | WHP-10 TOPSIDES LOADOUT ANALYSIS REPORT - ICR | 20 | 2022-05-23 | 2022-06-20 | 2022-12-14 | 2023-01-10 | 142
0 | EDSDSR1075 | WHP-10 TOPSIDE JOINT DESIGN REPORT - ICR | 20 | 2022-05-23 | 2022-06-20 | 2022-08-02 | 2022-08-29 | 48
0 | EDSDSR1165 | WHP-10 TOPSIDES TRANSPORTATION ANALYSES REPORT - ICR | 20 | 2022-05-30 | 2022-06-27 | 2022-12-21 | 2023-01-17 | 142
0 | EDSDSR1005 | WHP-10 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - IFA | 12 | 2022-06-20 | 2022-07-06 | 2022-09-22 | 2022-10-07 | 65
0 | EDSDSR1105 | WHP-10 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - ICR | 20 | 2022-06-13 | 2022-07-14 | 2022-09-22 | 2022-10-19 | 70
0 | EDSDSR1140 | WHP-10 TOPSIDES LIFT ANALYSES REPORT - IFA | 15 | 2022-06-27 | 2022-07-21 | 2023-01-06 | 2023-01-26 | 134
0 | EDSDSR1200 | WHP-10 TOPSIDES LINEAR BLAST ANALYSIS REPORT - IFA | 15 | 2022-06-27 | 2022-07-21 | 2023-03-01 | 2023-03-21 | 172
0 | EDSDSR1015 | WHP-10 JACKET INPLACE ANALYSIS REPORT - ICR | 20 | 2022-06-22 | 2022-07-25 | 2022-11-21 | 2022-12-20 | 105
0 | EDSDSR1180 | WHP-10 TOPSIDE MISCELLANEOUS DESIGN REPORT - ICR | 20 | 2022-06-27 | 2022-07-28 | 2023-01-18 | 2023-02-14 | 142
0 | EDSDSR1095 | WHP-10 HELIDECK DESIGN REPORT - IFA | 15 | 2022-07-04 | 2022-07-28 | 2022-10-27 | 2022-11-16 | 80
0 | EDSDSR1155 | WHP-10 TOPSIDES LOADOUT ANALYSIS REPORT - IFA | 15 | 2022-07-04 | 2022-07-28 | 2023-03-02 | 2023-03-22 | 168
0 | EDSDSR1080 | WHP-10 TOPSIDE JOINT DESIGN REPORT - IFA | 15 | 2022-07-04 | 2022-07-28 | 2022-09-19 | 2022-10-07 | 52
0 | EDSDSR1170 | WHP-10 TOPSIDES TRANSPORTATION ANALYSES REPORT - IFA | 15 | 2022-07-14 | 2022-08-04 | 2023-03-01 | 2023-03-21 | 162
0 | EDSDSR1010 | WHP-10 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - IFC | 10 | 2022-07-25 | 2022-08-08 | 2022-10-24 | 2022-11-04 | 65
0 | EDSDSR1030 | WHP-10 JACKET PUSHOVER ANALYSIS REPORT - ICR | 20 | 2022-07-06 | 2022-08-08 | 2022-12-07 | 2023-01-03 | 105
0 | EDSDSR1110 | WHP-10 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - IFA | 15 | 2022-07-28 | 2022-08-18 | 2023-01-06 | 2023-01-26 | 114
0 | EDSDSR1045 | WHP-10 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - ICR | 20 | 2022-07-25 | 2022-08-22 | 2022-12-21 | 2023-01-17 | 105
0 | EDSDSR1205 | WHP-10 TOPSIDES LINEAR BLAST ANALYSIS REPORT - IFC | 15 | 2022-08-04 | 2022-08-25 | 2023-04-05 | 2023-04-27 | 172
0 | EDSDSR1145 | WHP-10 TOPSIDES LIFT ANALYSES REPORT - IFC | 15 | 2022-08-08 | 2022-08-29 | 2023-02-10 | 2023-03-02 | 132
0 | EDSDSR1020 | WHP-10 JACKET INPLACE ANALYSIS REPORT - IFA | 15 | 2022-08-08 | 2022-08-29 | 2023-01-25 | 2023-02-14 | 120
0 | EDSDSR1100 | WHP-10 HELIDECK DESIGN REPORT - IFC | 15 | 2022-08-11 | 2022-09-01 | 2022-12-05 | 2022-12-23 | 80
0 | EDSDSR1160 | WHP-10 TOPSIDES LOADOUT ANALYSIS REPORT - IFC | 15 | 2022-08-11 | 2022-09-01 | 2023-04-06 | 2023-04-28 | 168
0 | EDSDSR1185 | WHP-10 TOPSIDE MISCELLANEOUS DESIGN REPORT - IFA | 15 | 2022-08-11 | 2022-09-01 | 2023-03-01 | 2023-03-21 | 142
0 | EDSDSR1085 | WHP-10 TOPSIDE JOINT DESIGN REPORT - IFC | 15 | 2022-08-11 | 2022-09-01 | 2022-10-24 | 2022-11-11 | 52
0 | EDSDSR1060 | WHP-10 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - ICR | 20 | 2022-08-08 | 2022-09-05 | 2023-01-04 | 2023-01-31 | 105
0 | EDSDSR1175 | WHP-10 TOPSIDES TRANSPORTATION ANALYSES REPORT - IFC | 15 | 2022-08-18 | 2022-09-08 | 2023-04-05 | 2023-04-27 | 162
0 | EDSDSR1035 | WHP-10 JACKET PUSHOVER ANALYSIS REPORT - IFA | 15 | 2022-08-22 | 2022-09-12 | 2023-02-15 | 2023-03-07 | 125
0 | EDSDSR1120 | WHP-10 JACKET MISCELLANEOUS DESIGN REPORT - ICR | 20 | 2022-08-22 | 2022-09-19 | 2023-01-18 | 2023-02-14 | 105
0 | EDSDSR1115 | WHP-10 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - IFC | 15 | 2022-09-01 | 2022-09-22 | 2023-02-10 | 2023-03-02 | 114
0 | EDSDSR1050 | WHP-10 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - IFA | 15 | 2022-09-05 | 2022-09-26 | 2023-02-22 | 2023-03-14 | 120
0 | EDSDSR1025 | WHP-10 JACKET INPLACE ANALYSIS REPORT - IFC | 15 | 2022-09-12 | 2022-10-03 | 2023-03-08 | 2023-03-28 | 125
0 | EDSDSR1190 | WHP-10 TOPSIDE MISCELLANEOUS DESIGN REPORT - IFC | 15 | 2022-09-15 | 2022-10-06 | 2023-04-05 | 2023-04-27 | 142
0 | EDSDSR1065 | WHP-10 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - IFA | 15 | 2022-09-19 | 2022-10-10 | 2023-03-01 | 2023-03-21 | 115
0 | EDSDSR1040 | WHP-10 JACKET PUSHOVER ANALYSIS REPORT - IFC | 15 | 2022-09-26 | 2022-10-17 | 2023-03-22 | 2023-04-11 | 125
0 | EDSDSR1125 | WHP-10 JACKET MISCELLANEOUS DESIGN REPORT - IFA | 15 | 2022-10-03 | 2022-10-24 | 2023-03-01 | 2023-03-21 | 105
0 | EDSDSR1055 | WHP-10 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - IFC | 15 | 2022-10-10 | 2022-10-31 | 2023-03-29 | 2023-04-18 | 120
0 | EDSDSR1070 | WHP-10 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - IFC | 15 | 2022-10-24 | 2022-11-14 | 2023-04-05 | 2023-04-27 | 115
0 | EDSDSR1130 | WHP-10 JACKET MISCELLANEOUS DESIGN REPORT - IFC | 15 | 2022-11-07 | 2022-11-28 | 2023-04-05 | 2023-04-27 | 105
DRAWINGS |  |  | 172 | 2022-04-25 | 2023-01-02 | 2022-08-02 | 2023-06-21 | 121
GENERAL |  |  | 72 | 2022-04-25 | 2022-08-11 | 2022-08-16 | 2022-11-14 | 68
0 | EDSGSR1000 | WHP-10 DRAWING INDEX - ICR | 15 | 2022-04-25 | 2022-05-19 | 2022-08-16 | 2022-09-05 | 75
0 | EDSGSR1002 | WHP-10 DRAWING INDEX - IFA | 15 | 2022-06-13 | 2022-07-04 | 2022-09-20 | 2022-10-10 | 68
0 | EDSGSR1005 | WHP-10 DRAWING INDEX - IFC | 15 | 2022-07-21 | 2022-08-11 | 2022-10-25 | 2022-11-14 | 68
PRIMARY |  |  | 117 | 2022-05-23 | 2022-11-07 | 2022-08-02 | 2023-03-21 | 95
0 | EDSGSR1025 | WHP-10 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - ICR | 20 | 2022-05-23 | 2022-06-20 | 2022-08-02 | 2022-08-29 | 48
0 | EDSGSR1010 | WHP-10 MAIN DECK PRIMARY FRAMING PLAN EL(+) 15.000 - ICR | 20 | 2022-05-23 | 2022-06-20 | 2022-08-02 | 2022-08-29 | 48
0 | EDSGSR1040 | WHP-10 DECK ELEVATION ROW-1 & 2 - ICR | 20 | 2022-05-30 | 2022-06-27 | 2022-08-09 | 2022-09-05 | 48
0 | EDSGSR1055 | WHP-10 DECK ELEVATION ROW-A & B - ICR | 20 | 2022-05-30 | 2022-06-27 | 2022-08-09 | 2022-09-05 | 48
0 | EDSGSR1085 | WHP-10 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 9.000- ICR | 20 | 2022-06-06 | 2022-07-04 | 2022-08-16 | 2022-09-12 | 48
0 | EDSGSR1100 | WHP-10 ACCESS PLATFORM FRAMING PLAN EL(+) 18.000 - ICR | 20 | 2022-06-06 | 2022-07-04 | 2022-08-17 | 2022-09-13 | 49
0 | EDSGSR1070 | WHP-10 DECK SECTIONS - ICR | 20 | 2022-06-06 | 2022-07-04 | 2022-08-16 | 2022-09-12 | 48
0 | EDSGSR1115 | WHP-10 MEZZANINE DECK FRAMING PLAN EL(+) 21.000 - ICR | 20 | 2022-06-09 | 2022-07-07 | 2022-08-22 | 2022-09-16 | 49
0 | EDSGSR1130 | WHP-10 WEATHER DECK FRAMING PLAN EL(+) 25.500 - ICR | 20 | 2022-06-16 | 2022-07-19 | 2022-08-29 | 2022-09-23 | 49
0 | EDSGSR1145 | WHP-10 - HELIDECK FRAMING PLAN AT EL. (+) 32.300 - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-10-06 | 2022-11-02 | 72
0 | EDSGSR1160 | WHP-10 DECK LEG STABBING GUIDE DETAILS - ICR | 20 | 2022-06-27 | 2022-07-28 | 2022-12-14 | 2023-01-10 | 117
0 | EDSGSR1030 | WHP-10 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - IFA | 15 | 2022-07-04 | 2022-07-28 | 2022-09-26 | 2022-10-14 | 57
0 | EDSGSR1015 | WHP-10 MAIN DECK PRIMARY FRAMING PLAN EL(+) 15.000- IFA. | 15 | 2022-07-04 | 2022-07-28 | 2022-09-26 | 2022-10-14 | 57
0 | EDSGSR1045 | WHP-10 DECK ELEVATION ROW-1 & 2 - IFA | 15 | 2022-07-14 | 2022-08-04 | 2022-10-14 | 2022-11-03 | 66
0 | EDSGSR1060 | WHP-10 DECK ELEVATION ROW-A & B - IFA | 15 | 2022-07-14 | 2022-08-04 | 2022-10-17 | 2022-11-04 | 67
0 | EDSGSR1090 | WHP-10 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 9.000 - IFA | 15 | 2022-07-21 | 2022-08-11 | 2022-10-04 | 2022-10-24 | 53
0 | EDSGSR1105 | WHP-10 ACCESS PLATFORM FRAMING PLAN EL(+) 18.000 - IFA | 15 | 2022-07-21 | 2022-08-11 | 2022-10-20 | 2022-11-09 | 65
0 | EDSGSR1075 | WHP-10 DECK SECTIONS - IFA | 15 | 2022-07-21 | 2022-08-11 | 2022-10-17 | 2022-11-04 | 62
0 | EDSGSR1120 | WHP-10 MEZZANINE DECK FRAMING PLAN EL(+) 21.000 - IFA | 15 | 2022-07-26 | 2022-08-16 | 2022-10-06 | 2022-10-26 | 52
0 | EDSGSR1135 | WHP-10 WEATHER DECK FRAMING PLAN EL(+) 25.500 - IFA | 15 | 2022-08-02 | 2022-08-23 | 2022-10-10 | 2022-10-28 | 49
0 | EDSGSR1150 | WHP-10 - HELIDECK FRAMING PLAN AT EL. (+) 32.300 - IFA | 15 | 2022-08-09 | 2022-08-30 | 2022-11-17 | 2022-12-09 | 72
0 | EDSGSR1165 | WHP-10 DECK LEG STABBING GUIDE DETAILS - IFA | 15 | 2022-08-11 | 2022-09-01 | 2023-01-25 | 2023-02-14 | 117
0 | EDSGSR1020 | WHP-10 MAIN DECK PRIMARY FRAMING PLAN EL(+) 15.000 - IFC | 15 | 2022-08-15 | 2022-09-05 | 2022-10-31 | 2022-11-18 | 55
0 | EDSGSR1035 | WHP-10 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - IFC | 15 | 2022-08-18 | 2022-09-08 | 2022-10-31 | 2022-11-18 | 52
0 | EDSGSR1050 | WHP-10 DECK ELEVATION ROW-1 & 2 - IFC | 15 | 2022-08-18 | 2022-09-08 | 2022-11-18 | 2022-12-12 | 66
0 | EDSGSR1065 | WHP-10 DECK ELEVATION ROW-A & B - IFC | 15 | 2022-08-18 | 2022-09-08 | 2022-11-21 | 2022-12-13 | 67
0 | EDSGSR1095 | WHP-10 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 9.000 - IFC | 12 | 2022-08-25 | 2022-09-12 | 2022-11-08 | 2022-11-23 | 53
0 | EDSGSR1110 | WHP-10 ACCESS PLATFORM FRAMING PLAN EL(+) 18.000 - IFC | 15 | 2022-08-25 | 2022-09-15 | 2022-11-24 | 2022-12-16 | 65
0 | EDSGSR1080 | WHP-10 DECK SECTIONS - IFC | 15 | 2022-08-25 | 2022-09-15 | 2022-11-21 | 2022-12-13 | 62
0 | EDSGSR1125 | WHP-10 MEZZANINE DECK FRAMING PLAN EL(+) 21.000 - IFC | 15 | 2022-08-30 | 2022-09-20 | 2022-11-10 | 2022-11-30 | 52
0 | EDSGSR1140 | WHP-10 WEATHER DECK FRAMING PLAN EL(+) 25.500 - IFC | 15 | 2022-09-06 | 2022-09-27 | 2022-11-14 | 2022-12-06 | 49
0 | EDSGSR1170 | WHP-10 DECK LEG STABBING GUIDE DETAILS - IFC | 15 | 2022-09-15 | 2022-10-06 | 2023-03-01 | 2023-03-21 | 117
0 | EDSGSR1155 | WHP-10 - HELIDECK FRAMING PLAN AT EL. (+) 32.300 - IFC | 15 | 2022-10-17 | 2022-11-07 | 2022-12-26 | 2023-01-13 | 48
SECONDARY |  |  | 122 | 2022-06-06 | 2022-11-28 | 2022-08-23 | 2023-03-24 | 83
0 | EDSGSR1175 | WHP-10 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - ICR | 20 | 2022-06-06 | 2022-07-04 | 2022-08-23 | 2022-09-19 | 53
0 | EDSGSR1235 | WHP-10 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - ICR | 20 | 2022-06-13 | 2022-07-14 | 2022-08-30 | 2022-09-26 | 53
0 | EDSGSR1190 | WHP-10 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - ICR | 20 | 2022-06-20 | 2022-07-21 | 2022-08-30 | 2022-09-26 | 48
0 | EDSGSR1250 | WHP-10 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - ICR | 20 | 2022-06-27 | 2022-07-28 | 2022-09-06 | 2022-10-03 | 48
0 | EDSGSR1205 | WHP-10 MEZZANINE DECK SECONDARY FRAMING PLAN EL(+) 21.000 - ICR | 20 | 2022-06-27 | 2022-07-28 | 2022-09-08 | 2022-10-05 | 50
0 | EDSGSR2110 | WHP-10 - CELLAR DECK INFILL BEAM FRAMING PLAN AT EL (+) 9.000 T.O.S - ICR | 15 | 2022-07-04 | 2022-07-28 | 2022-09-29 | 2022-10-19 | 60
0 | EDSGSR1265 | WHP-10 ACCESSPLATFORM PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 18.000 - ICR | 20 | 2022-06-29 | 2022-08-01 | 2022-09-08 | 2022-10-05 | 48
0 | EDSGSR1220 | WHP-10 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - ICR | 20 | 2022-07-04 | 2022-08-04 | 2022-10-06 | 2022-11-02 | 65
0 | EDSGSR2020 | WHP-10 - MAIN DECK INFILL BEAM FRAMING PLAN AT EL (+) 15.000 T.O.S - ICR | 15 | 2022-07-14 | 2022-08-04 | 2022-10-06 | 2022-10-26 | 60
0 | EDSGSR1280 | WHP-10 MEZZANINE DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - ICR | 20 | 2022-07-06 | 2022-08-08 | 2022-09-15 | 2022-10-12 | 48
0 | EDSGSR1180 | WHP-10 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - IFA | 15 | 2022-07-21 | 2022-08-11 | 2022-10-28 | 2022-11-17 | 71
0 | EDSGSR2050 | WHP-10 - MEZZANINE DECK INFILL BEAM FRAMING PLAN (+) 21.000 T.O.S - ICR | 15 | 2022-07-21 | 2022-08-11 | 2022-10-13 | 2022-11-02 | 60
0 | EDSGSR1295 | WHP-10 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - ICR | 20 | 2022-07-18 | 2022-08-15 | 2022-10-13 | 2022-11-09 | 63
0 | EDSGSR1240 | WHP-10 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - IFA | 15 | 2022-07-28 | 2022-08-18 | 2022-11-04 | 2022-11-24 | 71
0 | EDSGSR2080 | WHP-10 - WEATHER DECK INFILL BEAM FRAMING PLAN EL (+) 25.000 T.O.S - ICR | 15 | 2022-07-28 | 2022-08-18 | 2022-11-10 | 2022-11-30 | 75
0 | EDSGSR1310 | WHP-10 HELIDECK PLATING DETAILS - ICR | 20 | 2022-07-25 | 2022-08-22 | 2022-11-16 | 2022-12-15 | 82
0 | EDSGSR1195 | WHP-10 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - IFA | 15 | 2022-08-04 | 2022-08-25 | 2022-10-27 | 2022-11-16 | 60
0 | EDSGSR1325 | WHP-10 HELIDECK SAFETY NET LAYOUT & DETAILS - ICR | 20 | 2022-08-01 | 2022-08-29 | 2022-11-23 | 2022-12-22 | 82
0 | EDSGSR1255 | WHP-10 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - IFA | 15 | 2022-08-11 | 2022-09-01 | 2022-11-15 | 2022-12-07 | 68
0 | EDSGSR1210 | WHP-10 MEZZANINE DECK SECONDARY FRAMING PLAN EL(+) 21.000 - IFA | 15 | 2022-08-11 | 2022-09-01 | 2022-10-27 | 2022-11-16 | 55
0 | EDSGSR2120 | WHP-10 - CELLAR DECK INFILL BEAM FRAMING PLAN AT EL (+) 9.000 T.O.S - IFA | 15 | 2022-08-11 | 2022-09-01 | 2022-11-10 | 2022-11-30 | 65
0 | EDSGSR1270 | WHP-10 ACCESSPLATFORM PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 18.000 - IFA | 15 | 2022-08-15 | 2022-09-05 | 2022-11-10 | 2022-11-30 | 63
0 | EDSGSR1225 | WHP-10 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - IFA | 15 | 2022-08-18 | 2022-09-08 | 2022-11-24 | 2022-12-16 | 70
0 | EDSGSR2030 | WHP-10 - MAIN DECK INFILL BEAM FRAMING PLAN AT EL (+) 15.000 T.O.S - IFA | 15 | 2022-08-18 | 2022-09-08 | 2022-11-11 | 2022-12-05 | 61
0 | EDSGSR1285 | WHP-10 MEZZANINE DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - IFA | 15 | 2022-08-22 | 2022-09-12 | 2022-10-27 | 2022-11-16 | 48
0 | EDSGSR1185 | WHP-10 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - IFC | 10 | 2022-08-29 | 2022-09-12 | 2022-12-06 | 2022-12-19 | 69
0 | EDSGSR2060 | WHP-10 - MEZZANINE DECK INFILL BEAM FRAMING PLAN (+) 21.000 T.O.S - IFA | 15 | 2022-08-25 | 2022-09-15 | 2022-11-17 | 2022-12-09 | 60
0 | EDSGSR1300 | WHP-10 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - IFA | 15 | 2022-08-29 | 2022-09-19 | 2022-11-24 | 2022-12-16 | 63
0 | EDSGSR1200 | WHP-10 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - IFC | 10 | 2022-09-08 | 2022-09-22 | 2022-12-05 | 2022-12-16 | 60
0 | EDSGSR2090 | WHP-10 - WEATHER DECK INFILL BEAM FRAMING PLAN EL (+) 25.000 T.O.S - IFA | 15 | 2022-09-01 | 2022-09-22 | 2022-12-19 | 2023-01-06 | 75
0 | EDSGSR1315 | WHP-10 HELIDECK PLATING DETAILS - IFA | 15 | 2022-09-05 | 2022-09-26 | 2023-01-30 | 2023-02-17 | 103
0 | EDSGSR1245 | WHP-10 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - IFC | 15 | 2022-09-08 | 2022-09-29 | 2022-12-13 | 2023-01-02 | 66
0 | EDSGSR1260 | WHP-10 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - IFC | 12 | 2022-09-15 | 2022-10-03 | 2022-12-22 | 2023-01-06 | 68
0 | EDSGSR1330 | WHP-10 HELIDECK SAFETY NET LAYOUT & DETAILS- IFA | 15 | 2022-09-12 | 2022-10-03 | 2023-01-06 | 2023-01-26 | 82
0 | EDSGSR1215 | WHP-10 MEZZANINE DECK SECONDARY FRAMING PLAN EL(+) 21.000 - IFC | 15 | 2022-09-15 | 2022-10-06 | 2022-12-05 | 2022-12-23 | 55
0 | EDSGSR2040 | WHP-10 - MAIN DECK INFILL BEAM FRAMING PLAN AT EL (+) 15.000 T.O.S - IFC | 10 | 2022-09-22 | 2022-10-06 | 2022-12-20 | 2023-01-02 | 61
0 | EDSGSR2130 | WHP-10 - CELLAR DECK INFILL BEAM FRAMING PLAN AT EL (+) 9.000 T.O.S - IFC | 10 | 2022-09-22 | 2022-10-06 | 2022-12-19 | 2022-12-30 | 60
0 | EDSGSR1275 | WHP-10 ACCESSPLATFORM PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 18.000 - IFC | 15 | 2022-09-19 | 2022-10-10 | 2022-12-19 | 2023-01-06 | 63
0 | EDSGSR1230 | WHP-10 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - IFC | 15 | 2022-09-22 | 2022-10-13 | 2023-01-02 | 2023-01-20 | 70
0 | EDSGSR1290 | WHP-10 MEZZANINE DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - IFC | 15 | 2022-09-26 | 2022-10-17 | 2022-12-05 | 2022-12-23 | 48
0 | EDSGSR2070 | WHP-10 - MEZZANINE DECK INFILL BEAM FRAMING PLAN (+) 21.000 T.O.S - IFC | 10 | 2022-10-06 | 2022-10-20 | 2022-12-26 | 2023-01-06 | 55
0 | EDSGSR1305 | WHP-10 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - IFC | 15 | 2022-10-03 | 2022-10-24 | 2023-01-02 | 2023-01-20 | 63
0 | EDSGSR2100 | WHP-10 - WEATHER DECK INFILL BEAM FRAMING PLAN EL (+) 25.000 T.O.S - IFC | 10 | 2022-10-13 | 2022-10-27 | 2023-01-23 | 2023-02-03 | 70
0 | EDSGSR1320 | WHP-10 HELIDECK PLATING DETAILS - IFC | 15 | 2022-10-10 | 2022-10-31 | 2023-03-06 | 2023-03-24 | 103
0 | EDSGSR1335 | WHP-10 HELIDECK SAFETY NET LAYOUT & DETAILS- IFC | 15 | 2022-11-07 | 2022-11-28 | 2023-02-10 | 2023-03-02 | 67
TERTAIRY |  |  | 135 | 2022-06-20 | 2023-01-02 | 2022-09-22 | 2023-06-21 | 121
0 | EDSGSR1400 | WHP-10 - DECK LIFTING PADEYE DETAILS - ICR | 20 | 2022-06-20 | 2022-07-21 | 2022-09-22 | 2022-10-19 | 65
0 | EDSGSR1415 | WHP-10 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - ICR | 20 | 2022-06-27 | 2022-07-28 | 2022-09-29 | 2022-10-26 | 65
0 | EDSGSR1430 | WHP-10 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS- ICR | 20 | 2022-07-04 | 2022-08-04 | 2022-10-06 | 2022-11-02 | 65
0 | EDSGSR2140 | WHP-10 CELLAR DECK LOADING DIAGRAM - ICR | 20 | 2022-07-06 | 2022-08-08 | 2022-10-27 | 2022-11-23 | 78
0 | EDSGSR1445 | WHP-10 MEZZANINE DECK EQUIPMENT SUPPORT GA AND DETAILS - ICR | 20 | 2022-07-14 | 2022-08-11 | 2022-10-13 | 2022-11-09 | 65
0 | EDSGSR1460 | WHP-10 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - ICR | 20 | 2022-07-14 | 2022-08-11 | 2022-10-13 | 2022-11-09 | 65
0 | EDSGSR2170 | WHP-10 MAIN DECK LOADING DIAGRAM - ICR | 15 | 2022-07-25 | 2022-08-15 | 2022-11-10 | 2022-11-30 | 78
0 | EDSGSR2200 | WHP-10 MEZZANINE DECK LOADING DIAGRAM- ICR | 15 | 2022-08-01 | 2022-08-22 | 2022-11-17 | 2022-12-09 | 78
0 | EDSGSR1475 | WHP-10 REMOVABLE HATCH DETAILS- ICR | 20 | 2022-07-28 | 2022-08-25 | 2022-10-27 | 2022-11-23 | 65
0 | EDSGSR2230 | WHP-10 WEATHER DECK LOADING DIAGRAM - ICR | 15 | 2022-08-08 | 2022-08-29 | 2022-11-24 | 2022-12-16 | 78
0 | EDSGSR1420 | WHP-10 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-15 | 2022-09-05 | 2023-01-27 | 2023-02-16 | 117
0 | EDSGSR1490 | WHP-10 DECK PENETRATION AND DETAILS- ICR | 20 | 2022-08-08 | 2022-09-05 | 2022-10-27 | 2022-11-23 | 58
0 | EDSGSR2150 | WHP-10 CELLAR DECK LOADING DIAGRAM - IFA | 10 | 2022-08-22 | 2022-09-05 | 2023-02-09 | 2023-02-22 | 121
0 | EDSGSR2260 | WHP-10 HELIDECK LOADING DIAGRAM - ICR | 15 | 2022-08-15 | 2022-09-05 | 2022-12-05 | 2022-12-23 | 78
0 | EDSGSR1535 | WHP-10 WEST STAIR TOWER ELEVATIONS- ICR | 20 | 2022-08-11 | 2022-09-08 | 2022-11-28 | 2022-12-27 | 77
0 | EDSGSR1435 | WHP-10 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-18 | 2022-09-08 | 2023-01-27 | 2023-02-16 | 114
0 | EDSGSR2180 | WHP-10 MAIN DECK LOADING DIAGRAM - IFA | 10 | 2022-08-29 | 2022-09-12 | 2023-02-09 | 2023-02-22 | 116
0 | EDSGSR1550 | WHP-10 WEST STAIR TOWER LAYOUT PLAN- ICR | 20 | 2022-08-18 | 2022-09-15 | 2022-12-07 | 2023-01-03 | 77
0 | EDSGSR1685 | WHP-10 JACKET RISER GA AND SUPPORT DETAILS - ICR | 10 | 2022-09-01 | 2022-09-15 | 2023-01-09 | 2023-01-20 | 90
0 | EDSGSR1450 | WHP-10 MEZZANINE DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-25 | 2022-09-15 | 2023-02-03 | 2023-02-23 | 114
0 | EDSGSR1465 | WHP-10 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-25 | 2022-09-15 | 2023-02-10 | 2023-03-02 | 119
0 | EDSGSR2210 | WHP-10 MEZZANINE DECK LOADING DIAGRAM - IFA | 10 | 2022-09-05 | 2022-09-19 | 2023-02-09 | 2023-02-22 | 111
0 | EDSGSR2320 | WHP-10 PIPE SUPPORT DETAILS - ICR | 10 | 2022-09-05 | 2022-09-19 | 2022-12-26 | 2023-01-06 | 78
0 | EDSGSR1595 | WHP-10 STAIR FROM WEATHER DECK TO HELIDECK - ICR | 20 | 2022-08-25 | 2022-09-22 | 2023-01-02 | 2023-01-27 | 90
0 | EDSGSR1640 | WHP-10 HELIDECK DRAIN GUTTER GA AND DETAILS - ICR | 10 | 2022-09-08 | 2022-09-22 | 2022-12-28 | 2023-01-10 | 77
0 | EDSGSR1730 | WHP-10 OFFSHORE INSTALLED FRAMING AND GRATING - ICR | 10 | 2022-09-08 | 2022-09-22 | 2023-02-01 | 2023-02-14 | 102
0 | EDSGSR1405 | WHP-10 - DECK LIFTING PADEYE DETAILS - IFA | 15 | 2022-09-02 | 2022-09-23 | 2023-01-27 | 2023-02-16 | 103
0 | EDSGSR2240 | WHP-10 WEATHER DECK LOADING DIAGRAM - IFA | 10 | 2022-09-12 | 2022-09-26 | 2023-02-09 | 2023-02-22 | 106
0 | EDSGSR1700 | WHP-10 - HELIDECK MARKING PLAN - ICR | 20 | 2022-09-01 | 2022-09-29 | 2023-01-09 | 2023-02-03 | 90
0 | EDSGSR1715 | WHP-10 IDENTIFICATION BOARD DRAWING- ICR | 20 | 2022-09-01 | 2022-09-29 | 2023-01-18 | 2023-02-14 | 97
0 | EDSGSR1480 | WHP-10 REMOVABLE HATCH DETAILS - IFA | 15 | 2022-09-08 | 2022-09-29 | 2023-02-15 | 2023-03-07 | 112
0 | EDSGSR1610 | WHP-10 ACCESS PLATFORM - ICR | 20 | 2022-09-01 | 2022-09-29 | 2022-12-21 | 2023-01-17 | 77
0 | EDSGSR1625 | WHP-10 LADDER - ICR | 20 | 2022-09-01 | 2022-09-29 | 2022-12-21 | 2023-01-17 | 77
0 | EDSGSR1670 | WHP-10 - STRUCTURAL MISCELLANEOUS DETAIL - ICR | 20 | 2022-09-01 | 2022-09-29 | 2022-12-21 | 2023-01-17 | 77
0 | EDSGSR1655 | WHP-10 DECK DAVIT GA AND DETAILS - ICR | 10 | 2022-09-15 | 2022-09-29 | 2023-01-04 | 2023-01-17 | 77
0 | EDSGSR1760 | WHP-10 HELICOPTER TIE DOWN DETAILS - ICR | 10 | 2022-09-15 | 2022-09-29 | 2023-01-23 | 2023-02-03 | 90
0 | EDSGSR1775 | WHP-10 SWING ROPE DETAILS DRAWING - ICR | 10 | 2022-09-15 | 2022-09-29 | 2023-02-01 | 2023-02-14 | 97
0 | EDSGSR1855 | WHP-10 - WEST/ EAST SIDE STAIR TOWER DETAILS - IRC | 20 | 2022-09-01 | 2022-09-29 | 2022-12-21 | 2023-01-17 | 77
0 | EDSGSR2160 | WHP-10 CELLAR DECK LOADING DIAGRAM - IFC | 10 | 2022-09-19 | 2022-10-03 | 2023-03-09 | 2023-03-22 | 121
0 | EDSGSR2270 | WHP-10 HELIDECK LOADING DIAGRAM - IFA | 10 | 2022-09-19 | 2022-10-03 | 2023-02-09 | 2023-02-22 | 101
0 | EDSGSR2290 | WHP-10 PULLING POST & MATERIAL HANDLING PADEYES- ICR | 10 | 2022-09-19 | 2022-10-03 | 2023-04-12 | 2023-04-27 | 145
0 | EDSGSR2330 | WHP-10 PIPE SUPPORT DETAILS- IFA | 10 | 2022-09-19 | 2022-10-03 | 2023-01-09 | 2023-01-20 | 78
0 | EDSGSR1745 | WHP-10 STAIR FROM JACKET WALKWAY TO CELLAR DECK - IRC | 10 | 2022-09-22 | 2022-10-06 | 2023-02-01 | 2023-02-14 | 92
0 | EDSGSR1805 | WHP-10 WEATHER DECK INSTRUMENTAION CABINET SUNSHADE AND DETAILS - ICR | 10 | 2022-09-22 | 2022-10-06 | 2023-02-01 | 2023-02-14 | 92
0 | EDSGSR1505 | WHP-10 - VENT BOOM GA AND DETAILS - ICR | 20 | 2022-09-12 | 2022-10-10 | 2023-01-16 | 2023-02-10 | 88
0 | EDSGSR1495 | WHP-10 DECK PENETRATION AND DETAIL - IFA | 15 | 2022-09-19 | 2022-10-10 | 2022-12-12 | 2022-12-30 | 58
0 | EDSGSR2190 | WHP-10 MAIN DECK LOADING DIAGRAM - IFC | 10 | 2022-09-26 | 2022-10-10 | 2023-03-09 | 2023-03-22 | 116
0 | EDSGSR1690 | WHP-10 JACKET RISER GA AND SUPPORT DETAILS - IFA | 10 | 2022-09-29 | 2022-10-13 | 2023-03-15 | 2023-03-28 | 117
0 | EDSGSR1520 | WHP-10 - MAIN / CELLAR DECK MONORAIL AND DETAILS- ICR | 20 | 2022-09-19 | 2022-10-17 | 2023-01-23 | 2023-02-17 | 88
0 | EDSGSR2220 | WHP-10 MEZZANINE DECK LOADING DIAGRAM - IFC | 10 | 2022-10-03 | 2022-10-17 | 2023-03-09 | 2023-03-22 | 111
0 | EDSGSR2300 | WHP-10 PULLING POST & MATERIAL HANDLING PADEYES- IFA | 10 | 2022-10-03 | 2022-10-17 | 2023-04-28 | 2023-05-11 | 145
0 | EDSGSR2340 | WHP-10 PIPE SUPPORT DETAILS - IFC | 10 | 2022-10-03 | 2022-10-17 | 2023-01-23 | 2023-02-03 | 78
0 | EDSGSR1485 | WHP-10 REMOVABLE HATCH DETAILS - IFC | 15 | 2022-09-29 | 2022-10-20 | 2023-03-08 | 2023-03-28 | 112
0 | EDSGSR2350 | WHP-10 WEST STAIR TOWER ELEVATIONS- IFA | 20 | 2022-09-22 | 2022-10-20 | 2023-03-08 | 2023-04-04 | 117
0 | EDSGSR2360 | WHP-10 WEST STAIR TOWER LAYOUT PLAN- IFA | 15 | 2022-09-29 | 2022-10-20 | 2023-03-22 | 2023-04-11 | 122
0 | EDSGSR2370 | WHP-10 STAIR FROM WEATHER DECK TO HELIDECK - IFA | 20 | 2022-09-22 | 2022-10-20 | 2023-03-22 | 2023-04-18 | 127
0 | EDSGSR2250 | WHP-10 WEATHER DECK LOADING DIAGRAM - IFC | 10 | 2022-10-10 | 2022-10-24 | 2023-03-09 | 2023-03-22 | 106
0 | EDSGSR1645 | WHP-10 HELIDECK DRAIN GUTTER GA AND DETAILS - IFA | 15 | 2022-10-06 | 2022-10-27 | 2023-02-20 | 2023-03-10 | 95
0 | EDSGSR1735 | WHP-10 OFFSHORE INSTALLED FRAMING AND GRATING - IFA | 15 | 2022-10-06 | 2022-10-27 | 2023-03-01 | 2023-03-21 | 102
0 | EDSGSR1500 | WHP-10 DECK PENETRATION AND DETAIL - IFC | 15 | 2022-10-10 | 2022-10-31 | 2023-01-02 | 2023-01-20 | 58
0 | EDSGSR2280 | WHP-10 HELIDECK LOADING DIAGRAM - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-03-09 | 2023-03-22 | 101
0 | EDSGSR2310 | WHP-10 PULLING POST & MATERIAL HANDLING PADEYES- IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-05-12 | 2023-05-25 | 145
0 | EDSGSR1705 | WHP-10 - HELIDECK MARKING PLAN - IFA | 15 | 2022-10-13 | 2022-11-03 | 2023-02-20 | 2023-03-10 | 90
0 | EDSGSR1720 | WHP-10 IDENTIFICATION BOARD DRAWING - IFA | 15 | 2022-10-13 | 2022-11-03 | 2023-03-01 | 2023-03-21 | 97
0 | EDSGSR1675 | WHP-10 - STRUCTURAL MISCELLANEOUS DETAIL - IFA | 15 | 2022-10-13 | 2022-11-03 | 2023-03-31 | 2023-04-20 | 119
0 | EDSGSR1660 | WHP-10 DECK DAVIT GA AND DETAILS - IFA | 15 | 2022-10-13 | 2022-11-03 | 2023-02-01 | 2023-02-21 | 77
0 | EDSGSR1765 | WHP-10 HELICOPTER TIE DOWN DETAILS - IFA | 15 | 2022-10-13 | 2022-11-03 | 2023-02-20 | 2023-03-10 | 90
0 | EDSGSR1780 | WHP-10 SWING ROPE DETAILS DRAWING - IFA | 15 | 2022-10-13 | 2022-11-03 | 2023-03-01 | 2023-03-21 | 97
0 | EDSGSR2390 | WHP-10 LADDER - IFA | 15 | 2022-10-13 | 2022-11-03 | 2023-02-23 | 2023-03-15 | 93
0 | EDSGSR2400 | WHP-10 STAIR FROM JACKET WALKWAY TO CELLAR DECK - IFA | 10 | 2022-10-20 | 2022-11-03 | 2023-03-01 | 2023-03-14 | 92
0 | EDSGSR2410 | WHP-10 - WEST/ EAST SIDE STAIR TOWER DETAILS - IFA | 15 | 2022-10-13 | 2022-11-03 | 2023-03-29 | 2023-04-18 | 117
0 | EDSGSR1695 | WHP-10 JACKET RISER GA AND SUPPORT DETAILS - IFC | 10 | 2022-10-27 | 2022-11-10 | 2023-04-12 | 2023-04-27 | 117
0 | EDSGSR1810 | WHP-10 WEATHER DECK INSTRUMENTAION CABINET SUNSHADE AND DETAILS - IFA | 15 | 2022-10-20 | 2022-11-10 | 2023-03-01 | 2023-03-21 | 92
0 | EDSGSR2380 | WHP-10 ACCESS PLATFORM - IFA | 20 | 2022-10-13 | 2022-11-10 | 2023-02-08 | 2023-03-07 | 82
0 | EDSGSR1510 | WHP-10 - VENT BOOM GA AND DETAILS - IFA | 15 | 2022-10-24 | 2022-11-14 | 2023-04-27 | 2023-05-17 | 129
0 | EDSGSR1525 | WHP-10 - MAIN / CELLAR DECK MONORAIL AND DETAILS - IFA | 15 | 2022-10-31 | 2022-11-21 | 2023-03-06 | 2023-03-24 | 88
0 | EDSGSR1605 | WHP-10 STAIR FROM WEATHER DECK TO HELIDECK - IFC | 25 | 2022-10-20 | 2022-11-24 | 2023-04-19 | 2023-05-25 | 127
0 | EDSGSR1560 | WHP-10 WEST STAIR TOWER LAYOUT PLAN- IFC | 20 | 2022-11-03 | 2022-12-05 | 2023-04-28 | 2023-05-25 | 122
0 | EDSGSR1650 | WHP-10 HELIDECK DRAIN GUTTER GA AND DETAILS - IFC | 15 | 2022-11-10 | 2022-12-05 | 2023-03-27 | 2023-04-14 | 95
0 | EDSGSR1740 | WHP-10 OFFSHORE INSTALLED FRAMING AND GRATING - IFC | 15 | 2022-11-10 | 2022-12-05 | 2023-04-05 | 2023-04-27 | 102
0 | EDSGSR1545 | WHP-10 WEST STAIR TOWER ELEVATIONS- IFC | 25 | 2022-11-03 | 2022-12-12 | 2023-04-19 | 2023-05-25 | 117
0 | EDSGSR1725 | WHP-10 IDENTIFICATION BOARD DRAWING - IFC | 15 | 2022-11-17 | 2022-12-12 | 2023-04-05 | 2023-04-27 | 97
0 | EDSGSR1665 | WHP-10 DECK DAVIT GA AND DETAILS - IFC | 15 | 2022-11-17 | 2022-12-12 | 2023-03-08 | 2023-03-28 | 77
0 | EDSGSR1770 | WHP-10 HELICOPTER TIE DOWN DETAILS - IFC | 15 | 2022-11-17 | 2022-12-12 | 2023-03-27 | 2023-04-14 | 90
0 | EDSGSR1785 | WHP-10 SWING ROPE DETAILS DRAWING - IFC | 15 | 2022-11-17 | 2022-12-12 | 2023-04-05 | 2023-04-27 | 97
0 | EDSGSR1875 | WHP-10 - WEST/ EAST SIDE STAIR TOWER DETAILS - IFC | 15 | 2022-11-17 | 2022-12-12 | 2023-05-05 | 2023-05-25 | 117
0 | EDSGSR1440 | WHP-10 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-21 | 2022-12-14 | 2023-03-03 | 2023-03-23 | 72
0 | EDSGSR1425 | WHP-10 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-21 | 2022-12-14 | 2023-03-03 | 2023-03-23 | 72
0 | EDSGSR1530 | WHP-10 - MAIN / CELLAR DECK MONORAIL AND DETAILS - IFC | 15 | 2022-11-21 | 2022-12-14 | 2023-03-27 | 2023-04-14 | 88
0 | EDSGSR1635 | WHP-10 LADDER - IFC | 20 | 2022-11-17 | 2022-12-19 | 2023-03-30 | 2023-04-28 | 93
0 | EDSGSR1755 | WHP-10 STAIR FROM JACKET WALKWAY TO CELLAR DECK - IFC | 20 | 2022-11-17 | 2022-12-19 | 2023-03-29 | 2023-04-27 | 92
0 | EDSGSR1815 | WHP-10 WEATHER DECK INSTRUMENTAION CABINET SUNSHADE AND DETAILS - IFC | 15 | 2022-11-24 | 2022-12-19 | 2023-04-05 | 2023-04-27 | 92
0 | EDSGSR1410 | WHP-10 - DECK LIFTING PADEYE DETAILS - IFC | 14 | 2022-11-29 | 2022-12-21 | 2023-03-03 | 2023-03-22 | 66
0 | EDSGSR1710 | WHP-10 - HELIDECK MARKING PLAN - IFC | 15 | 2022-11-28 | 2022-12-21 | 2023-03-27 | 2023-04-14 | 83
0 | EDSGSR1515 | WHP-10 - VENT BOOM GA AND DETAILS - IFC | 15 | 2022-11-28 | 2022-12-21 | 2023-06-01 | 2023-06-21 | 129
0 | EDSGSR1455 | WHP-10 MEZZANINE DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-28 | 2022-12-21 | 2023-03-10 | 2023-03-30 | 72
0 | EDSGSR1680 | WHP-10 - STRUCTURAL MISCELLANEOUS DETAIL - IFC | 15 | 2022-11-28 | 2022-12-21 | 2023-05-09 | 2023-05-29 | 112
0 | EDSGSR1470 | WHP-10 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-12-07 | 2022-12-28 | 2023-03-17 | 2023-04-06 | 72
0 | EDSGSR1620 | WHP-10 ACCESS PLATFORM - IFC | 25 | 2022-11-24 | 2023-01-02 | 2023-03-22 | 2023-04-27 | 82
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDSGSR2000 | WHP-10 STRUCTURAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDSGSR2005 | WHP-10 STRUCTURAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDSGSR2010 | WHP-10 STRUCTURAL MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
NAVAL & ARCHITECTURE |  |  | 150 | 2022-04-01 | 2022-11-07 | 2022-07-07 | 2023-04-27 | 120
DOCUMENTS |  |  | 150 | 2022-04-01 | 2022-11-07 | 2022-07-07 | 2023-04-27 | 120
0 | EDSDNA1000 | WHP-10 TOPSIDE -WEIGHT & COG CALCULATION - ICR | 20 | 2022-04-01 | 2022-04-29 | 2022-07-07 | 2022-08-08 | 66
0 | EDSDNA1020 | WHP-10 JACKET -WEIGHT & COG CALCULATION - ICR | 20 | 2022-05-09 | 2022-06-06 | 2022-10-24 | 2022-11-18 | 117
0 | EDSDNA1005 | WHP-10 TOPSIDE -WEIGHT & COG CALCULATION - IFA | 15 | 2022-05-18 | 2022-06-08 | 2022-08-29 | 2022-09-16 | 70
0 | EDSDNA1010 | WHP-10 TOPSIDE -WEIGHT & COG CALCULATION - IFC | 20 | 2022-06-22 | 2022-07-25 | 2022-10-03 | 2022-10-28 | 70
0 | EDSDNA1030 | WHP-10 JACKET -WEIGHT & COG CALCULATION - IFA | 20 | 2022-08-29 | 2022-09-26 | 2023-02-15 | 2023-03-14 | 120
0 | EDSDNA1040 | WHP-10 JACKET -WEIGHT & COG CALCULATION - IFC | 20 | 2022-10-10 | 2022-11-07 | 2023-03-29 | 2023-04-27 | 120
HAIR DALMA WHP HD-T4 TOPSIDES |  |  | 363 | 2022-01-21 | 2023-01-19 | 2022-04-04 | 2023-08-14 | 208
PROCESS |  |  | 243 | 2022-01-21 | 2023-01-09 | 2022-04-04 | 2023-04-27 | 77
DOCUMENTS |  |  | 90 | 2022-03-08 | 2022-07-20 | 2022-05-16 | 2023-01-23 | 132
PROCESS SIMULATIONS & REPORTS |  |  | 62 | 2022-03-15 | 2022-06-14 | 2022-08-05 | 2022-11-08 | 103
0 | EDTDPR1000 | ALARM AND TRIP SCHEDULE HAIR DALMA T4 WHP - ICR | 15 | 2022-03-15 | 2022-04-05 | 2022-08-05 | 2022-08-25 | 97
0 | EDTDPR1005 | ALARM AND TRIP SCHEDULE HAIR DALMA T4 WHP - IFA | 12 | 2022-04-19 | 2022-05-10 | 2022-09-19 | 2022-10-04 | 103
0 | EDTDPR1010 | ALARM AND TRIP SCHEDULE HAIR DALMA T4 WHP - IFC | 15 | 2022-05-24 | 2022-06-14 | 2022-10-19 | 2022-11-08 | 103
PROCESS LISTS |  |  | 65 | 2022-03-08 | 2022-06-10 | 2022-06-08 | 2022-11-21 | 114
0 | EDTDPR1015 | EQUIPMENT LIST HAIR DALMA T4 WHP - ICR | 10 | 2022-03-08 | 2022-03-22 | 2022-06-08 | 2022-06-21 | 63
0 | EDTDPR1030 | LINE LIST HAIR DALMA T4 WHP - ICR | 10 | 2022-03-15 | 2022-03-29 | 2022-07-06 | 2022-07-22 | 78
0 | EDTDPR1020 | EQUIPMENT LIST HAIR DALMA T4 WHP - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-07-06 | 2022-07-22 | 63
0 | EDTDPR1035 | LINE LIST HAIR DALMA T4 WHP - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-08-25 | 2022-09-07 | 91
0 | EDTDPR1025 | EQUIPMENT LIST HAIR DALMA T4 WHP - IFC | 20 | 2022-05-06 | 2022-06-03 | 2022-10-25 | 2022-11-21 | 119
0 | EDTDPR1040 | LINE LIST HAIR DALMA T4 WHP - IFC | 20 | 2022-05-13 | 2022-06-10 | 2022-09-22 | 2022-10-19 | 91
PREPARATION OF DATASHEETS |  |  | 90 | 2022-03-08 | 2022-07-20 | 2022-05-16 | 2023-01-23 | 132
0 | EDTDPR1270 | PROCESS DATA SHEET PIG LAUNCHER HAIR DALMA T4 WHP - ICR | 4 | 2022-03-15 | 2022-03-21 | 2022-05-24 | 2022-05-27 | 47
0 | EDTDPR1045 | PROCESS DATA SHEET CHOKE VALVES HAIR DALMA T4 WHP - ICR | 10 | 2022-03-08 | 2022-03-22 | 2022-05-16 | 2022-05-27 | 46
0 | EDTDPR1240 | PROCESS DATA SHEET DRAIN DRUM PUMP HAIR DALMA T4 WHP - ICR | 5 | 2022-03-15 | 2022-03-22 | 2022-06-15 | 2022-06-21 | 63
0 | EDTDPR1075 | PROCESS DATA SHEET MOTOR OPERATED VALVES HAIR DALMA T4 WHP - ICR | 10 | 2022-03-08 | 2022-03-22 | 2022-05-19 | 2022-06-01 | 49
0 | EDTDPR1285 | PROCESS DATA SHEET PIG RECEIVER HAIR DALMA T4 WHP - ICR | 5 | 2022-03-16 | 2022-03-23 | 2022-05-25 | 2022-05-31 | 47
0 | EDTDPR1090 | PROCESS DATASHEET SHUTDOWN VALVES HAIR DALMA T4 WHP - ICR | 10 | 2022-03-10 | 2022-03-24 | 2022-05-23 | 2022-06-03 | 49
0 | EDTDPR1120 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES HAIR DALMA T4 WHP - ICR | 10 | 2022-03-14 | 2022-03-28 | 2022-07-18 | 2022-07-29 | 84
0 | EDTDPR1105 | PROCESS DATASHEET IRCD HAIR DALMA T4 WHP - ICR | 10 | 2022-03-14 | 2022-03-28 | 2022-05-26 | 2022-06-08 | 50
0 | EDTDPR1255 | PROCESS DATA SHEET VENT / DRAIN DRUM HAIR DALMA T4 WHP - ICR | 5 | 2022-03-22 | 2022-03-29 | 2022-06-22 | 2022-06-28 | 63
0 | EDTDPR1060 | PROCESS DATA SHEET WET GAS METER HAIR DALMA T4 WHP - MULTI PHASE FLOW METER - ICR | 10 | 2022-03-22 | 2022-04-05 | 2022-05-30 | 2022-06-10 | 46
0 | EDTDPR1135 | PROCESS DATASHEET PRESSURE GAUGES HAIR DALMA T4 WHP - ICR | 9 | 2022-03-28 | 2022-04-08 | 2022-08-18 | 2022-08-30 | 97
0 | EDTDPR1165 | PROCESS DATASHEET TEMPERATURE GAUGE HAIR DALMA T4 WHP - ICR | 9 | 2022-03-28 | 2022-04-08 | 2022-08-19 | 2022-08-31 | 98
0 | EDTDPR1150 | PROCESS DATASHEET PRESSURE INSTRUMENT HAIR DALMA T4 WHP - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-08-18 | 2022-08-31 | 97
0 | EDTDPR1180 | PROCESS DATASHEET TEMPERATURE INSTRUMENT HAIR DALMA T4 WHP - ICR | 10 | 2022-03-30 | 2022-04-13 | 2022-08-23 | 2022-09-05 | 98
0 | EDTDPR1195 | PROCESS DATASHEET LEVEL GAUGE HAIR DALMA T4 WHP - ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-08-29 | 2022-09-09 | 100
0 | EDTDPR1275 | PROCESS DATA SHEET PIG LAUNCHER HAIR DALMA T4 WHP - IFA | 9 | 2022-04-04 | 2022-04-15 | 2022-08-16 | 2022-08-26 | 90
0 | EDTDPR1210 | PROCESS DATASHEET LEVEL INSTRUMENT HAIR DALMA T4 WHP - ICR | 10 | 2022-04-05 | 2022-04-19 | 2022-08-31 | 2022-09-13 | 100
0 | EDTDPR1050 | PROCESS DATA SHEET CHOKE VALVES HAIR DALMA T4 WHP - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-06-22 | 2022-07-05 | 53
0 | EDTDPR1245 | PROCESS DATA SHEET DRAIN DRUM PUMP HAIR DALMA T4 WHP - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-08-15 | 2022-08-26 | 88
0 | EDTDPR1080 | PROCESS DATA SHEET MOTOR OPERATED VALVES HAIR DALMA T4 WHP - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-06-23 | 2022-07-06 | 54
0 | EDTDPR1290 | PROCESS DATA SHEET PIG RECEIVER HAIR DALMA T4 WHP - IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-06-15 | 2022-06-28 | 47
0 | EDTDPR1225 | PROCESS DATASHEET FLOW SWITCH HAIR DALMA T4 WHP - ICR | 10 | 2022-04-07 | 2022-04-21 | 2022-09-12 | 2022-09-23 | 106
0 | EDTDPR1095 | PROCESS DATASHEET SHUTDOWN VALVES HAIR DALMA T4 WHP - IFA | 10 | 2022-04-07 | 2022-04-21 | 2022-06-22 | 2022-07-05 | 51
0 | EDTDPR1125 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES HAIR DALMA T4 WHP - IFA | 10 | 2022-04-11 | 2022-04-25 | 2022-08-15 | 2022-08-26 | 84
0 | EDTDPR1110 | PROCESS DATASHEET IRCD HAIR DALMA T4 WHP - IFA | 10 | 2022-04-11 | 2022-04-25 | 2022-06-27 | 2022-07-13 | 52
0 | EDTDPR1260 | PROCESS DATA SHEET VENT / DRAIN DRUM HAIR DALMA T4 WHP - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-08-15 | 2022-08-26 | 83
0 | EDTDPR1300 | PROCESS DATA SHEET RESTRICTION ORIFICES HAIR DALMA T4 WHP - ICR | 15 | 2022-04-12 | 2022-05-06 | 2022-08-22 | 2022-09-09 | 88
0 | EDTDPR1065 | PROCESS DATA SHEET WET GAS METER HAIR DALMA T4 WHP - MULTI PHASE FLOW METER - IFA | 10 | 2022-04-19 | 2022-05-06 | 2022-06-29 | 2022-07-15 | 48
0 | EDTDPR1140 | PROCESS DATASHEET PRESSURE GAUGES HAIR DALMA T4 WHP - IFA | 9 | 2022-04-22 | 2022-05-10 | 2022-10-07 | 2022-10-19 | 114
0 | EDTDPR1170 | PROCESS DATASHEET TEMPERATURE GAUGE HAIR DALMA T4 WHP - IFA | 9 | 2022-04-22 | 2022-05-10 | 2022-10-04 | 2022-10-14 | 111
0 | EDTDPR1155 | PROCESS DATASHEET PRESSURE INSTRUMENT HAIR DALMA T4 WHP - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-09-19 | 2022-09-30 | 99
0 | EDTDPR1185 | PROCESS DATASHEET TEMPERATURE INSTRUMENT HAIR DALMA T4 WHP - IFA | 10 | 2022-04-27 | 2022-05-16 | 2022-09-23 | 2022-10-06 | 101
0 | EDTDPR1200 | PROCESS DATASHEET LEVEL GAUGE HAIR DALMA T4 WHP - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-09-27 | 2022-10-10 | 101
0 | EDTDPR1295 | PROCESS DATA SHEET PIG RECEIVER HAIR DALMA T4 WHP - IFC | 8 | 2022-05-09 | 2022-05-19 | 2022-07-18 | 2022-07-27 | 47
0 | EDTDPR1215 | PROCESS DATASHEET LEVEL INSTRUMENT HAIR DALMA T4 WHP - IFA | 10 | 2022-05-06 | 2022-05-20 | 2022-11-15 | 2022-11-28 | 134
0 | EDTDPR1230 | PROCESS DATASHEET FLOW SWITCH HAIR DALMA T4 WHP - IFA | 10 | 2022-05-10 | 2022-05-24 | 2022-11-25 | 2022-12-12 | 140
0 | EDTDPR1085 | PROCESS DATA SHEET MOTOR OPERATED VALVES HAIR DALMA T4 WHP - IFC | 15 | 2022-05-06 | 2022-05-27 | 2022-07-26 | 2022-08-15 | 54
0 | EDTDPR1280 | PROCESS DATA SHEET PIG LAUNCHER HAIR DALMA T4 WHP - IFC | 19 | 2022-04-29 | 2022-05-31 | 2022-12-13 | 2023-01-06 | 154
0 | EDTDPR1055 | PROCESS DATA SHEET CHOKE VALVES HAIR DALMA T4 WHP - IFC | 20 | 2022-05-06 | 2022-06-03 | 2022-07-25 | 2022-08-19 | 53
0 | EDTDPR1250 | PROCESS DATA SHEET DRAIN DRUM PUMP HAIR DALMA T4 WHP - IFC | 20 | 2022-05-06 | 2022-06-03 | 2022-11-02 | 2022-11-29 | 125
0 | EDTDPR1305 | PROCESS DATA SHEET RESTRICTION ORIFICES HAIR DALMA T4 WHP - IFA | 10 | 2022-05-20 | 2022-06-03 | 2022-09-26 | 2022-10-07 | 88
0 | EDTDPR1100 | PROCESS DATASHEET SHUTDOWN VALVES HAIR DALMA T4 WHP - IFC | 20 | 2022-05-10 | 2022-06-07 | 2022-07-25 | 2022-08-19 | 51
0 | EDTDPR1130 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES HAIR DALMA T4 WHP - IFC | 20 | 2022-05-12 | 2022-06-09 | 2022-10-27 | 2022-11-23 | 117
0 | EDTDPR1115 | PROCESS DATASHEET IRCD HAIR DALMA T4 WHP - IFC | 20 | 2022-05-12 | 2022-06-09 | 2022-07-28 | 2022-08-24 | 52
0 | EDTDPR1265 | PROCESS DATA SHEET VENT / DRAIN DRUM HAIR DALMA T4 WHP - IFC | 20 | 2022-05-13 | 2022-06-10 | 2022-10-05 | 2022-11-01 | 100
0 | EDTDPR1070 | PROCESS DATA SHEET WET GAS METER HAIR DALMA T4 WHP - MULTI PHASE FLOW METER - IFC | 20 | 2022-05-20 | 2022-06-17 | 2022-08-01 | 2022-08-26 | 48
0 | EDTDPR1145 | PROCESS DATASHEET PRESSURE GAUGES HAIR DALMA T4 WHP - IFC | 19 | 2022-05-24 | 2022-06-20 | 2022-11-03 | 2022-11-29 | 114
0 | EDTDPR1175 | PROCESS DATASHEET TEMPERATURE GAUGE HAIR DALMA T4 WHP - IFC | 19 | 2022-05-24 | 2022-06-20 | 2022-10-31 | 2022-11-24 | 111
0 | EDTDPR1160 | PROCESS DATASHEET PRESSURE INSTRUMENT HAIR DALMA T4 WHP - IFC | 20 | 2022-05-26 | 2022-06-23 | 2022-10-17 | 2022-11-11 | 99
0 | EDTDPR1190 | PROCESS DATASHEET TEMPERATURE INSTRUMENT HAIR DALMA T4 WHP - IFC | 20 | 2022-05-30 | 2022-06-27 | 2022-10-21 | 2022-11-17 | 101
0 | EDTDPR1205 | PROCESS DATASHEET LEVEL GAUGE HAIR DALMA T4 WHP - IFC | 19 | 2022-06-01 | 2022-06-28 | 2022-10-25 | 2022-11-18 | 101
0 | EDTDPR1220 | PROCESS DATASHEET LEVEL INSTRUMENT HAIR DALMA T4 WHP - IFC | 20 | 2022-06-03 | 2022-07-01 | 2022-12-15 | 2023-01-11 | 134
0 | EDTDPR1235 | PROCESS DATASHEET FLOW SWITCH HAIR DALMA T4 WHP - IFC | 20 | 2022-06-07 | 2022-07-05 | 2022-12-27 | 2023-01-23 | 140
0 | EDTDPR1310 | PROCESS DATA SHEET RESTRICTION ORIFICES HAIR DALMA T4 WHP - IFC | 20 | 2022-06-17 | 2022-07-20 | 2022-10-24 | 2022-11-18 | 88
DRAWINGS |  |  | 188 | 2022-01-21 | 2022-10-20 | 2022-04-04 | 2023-01-24 | 67
PFD / UFD / DPDT / PSFS & HMB |  |  | 73 | 2022-01-21 | 2022-05-09 | 2022-04-04 | 2022-12-14 | 153
0 | EDTGPR1030 | HEAT AND MATERIAL BALANCE - HAIR DALMA T4 WHP - ICR | 15 | 2022-01-21 | 2022-02-11 | 2022-04-04 | 2022-04-22 | 51
0 | EDTGPR1000 | PFD's - HAIR DALMA T4 WHP TEST AND PRODUCTION MANIFOLD - ICR | 15 | 2022-01-24 | 2022-02-14 | 2022-04-07 | 2022-04-27 | 53
0 | EDTGPR1015 | UFD's - HAIR DALMA T4 WHP - VENT AND DRAIN - UTILITIES SUPPLY - ICR | 15 | 2022-01-24 | 2022-02-14 | 2022-08-29 | 2022-09-16 | 149
0 | EDTGPR1045 | DPDT DIAGRAMS - HAIR DALMA T4 WHP - TEST AND PRODUCTION MANIFOLD - ICR | 20 | 2022-01-26 | 2022-02-23 | 2022-04-11 | 2022-05-11 | 53
0 | EDTGPR1060 | DPDT DIAGRAMS - HAIR DALMA T4 WHP VENT AND DRAIN UTILITIES SUPPLY - ICR | 20 | 2022-01-26 | 2022-02-23 | 2022-09-06 | 2022-10-03 | 153
0 | EDTGPR1075 | PSFS's - HAIR DALMA T4 WHP - TEST AND PRODUCTION MANIFOLD - ICR | 20 | 2022-01-26 | 2022-02-23 | 2022-04-11 | 2022-05-11 | 53
0 | EDTGPR1090 | PSFS's - HAIR DALMA T4 WHP - VENT AND DRAIN - UTILITIES SUPPLY - ICR | 20 | 2022-01-26 | 2022-02-23 | 2022-04-13 | 2022-05-13 | 55
0 | EDTGPR1020 | UFD's - HAIR DALMA T4 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFA | 10 | 2022-02-28 | 2022-03-14 | 2022-10-03 | 2022-10-14 | 149
0 | EDTGPR1035 | HEAT AND MATERIAL BALANCE - HAIR DALMA T4 WHP - IFA | 15 | 2022-02-25 | 2022-03-18 | 2022-10-18 | 2022-11-07 | 161
0 | EDTGPR1005 | PFD's - HAIR DALMA T4 WHP TEST AND PRODUCTION MANIFOLD - IFA | 15 | 2022-02-28 | 2022-03-21 | 2022-06-29 | 2022-07-22 | 84
0 | EDTGPR1050 | DPDT DIAGRAMS - HAIR DALMA T4 WHP - TEST AND PRODUCTION MANIFOLD - IFA | 10 | 2022-03-09 | 2022-03-23 | 2022-10-18 | 2022-10-31 | 153
0 | EDTGPR1065 | DPDT DIAGRAMS - HAIR DALMA T4 WHP VENT AND DRAIN UTILITIES SUPPLY - IFA | 10 | 2022-03-09 | 2022-03-23 | 2022-10-18 | 2022-10-31 | 153
0 | EDTGPR1080 | PSFS's - HAIR DALMA T4 WHP - TEST AND PRODUCTION MANIFOLD - IFA | 10 | 2022-03-09 | 2022-03-23 | 2022-10-18 | 2022-10-31 | 153
0 | EDTGPR1095 | PSFS's - HAIR DALMA T4 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFA | 10 | 2022-03-09 | 2022-03-23 | 2022-10-18 | 2022-10-31 | 153
0 | EDTGPR1040 | HEAT AND MATERIAL BALANCE - HAIR DALMA T4 WHP - IFC | 15 | 2022-04-01 | 2022-04-22 | 2022-11-22 | 2022-12-14 | 161
0 | EDTGPR1010 | PFD's - HAIR DALMA T4 WHP TEST AND PRODUCTION MANIFOLD - IFC | 15 | 2022-04-04 | 2022-04-25 | 2022-08-08 | 2022-08-26 | 84
0 | EDTGPR1025 | UFD's - HAIR DALMA T4 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFC | 20 | 2022-03-28 | 2022-04-25 | 2022-10-31 | 2022-11-25 | 149
0 | EDTGPR1055 | DPDT DIAGRAMS - HAIR DALMA T4 WHP - TEST AND PRODUCTION MANIFOLD - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-11-15 | 2022-12-14 | 153
0 | EDTGPR1070 | DPDT DIAGRAMS - HAIR DALMA T4 WHP VENT AND DRAIN UTILITIES SUPPLY - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-11-15 | 2022-12-14 | 153
0 | EDTGPR1085 | PSFS's - HAIR DALMA T4 WHP - TEST AND PRODUCTION MANIFOLD - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-11-15 | 2022-12-14 | 153
0 | EDTGPR1100 | PSFS's - HAIR DALMA T4 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-11-15 | 2022-12-14 | 153
PIPING & INSTRUMENTATION DIAGRAMS |  |  | 180 | 2022-02-02 | 2022-10-20 | 2022-04-14 | 2023-01-24 | 67
0 | EDTGPR1105 | P&ID - DRAWING INDEX HAIR DALMA T4 WHP - ICR | 20 | 2022-02-02 | 2022-03-02 | 2022-04-20 | 2022-05-20 | 55
0 | EDTGPR1120 | P&IDs - HAIR DALMA T4 WHP - ICR | 24 | 2022-02-09 | 2022-03-15 | 2022-04-14 | 2022-05-20 | 46
0 | EDTGPR1125 | P&IDs - HAIR DALMA T4 WHP - ISSUED FOR HAZOP | 25 | 2022-04-12 | 2022-05-20 | 2022-07-06 | 2022-08-12 | 58
0 | EDTGPR1130 | P&IDs - HAIR DALMA T4 WHP - IFA | 30 | 2022-06-24 | 2022-08-10 | 2022-09-08 | 2022-10-19 | 51
0 | EDTGPR1110 | P&ID - DRAWING INDEX HAIR DALMA T4 WHP - IFA | 30 | 2022-06-24 | 2022-08-10 | 2022-10-24 | 2022-12-06 | 83
0 | EDTGPR1135 | P&IDs - HAIR DALMA T4 WHP - IFC | 25 | 2022-09-15 | 2022-10-20 | 2022-11-22 | 2022-12-28 | 48
0 | EDTGPR1115 | P&ID - DRAWING INDEX HAIR DALMA T4 WHP - IFC | 25 | 2022-09-15 | 2022-10-20 | 2022-12-21 | 2023-01-24 | 67
CAUSE & EFFECT & SAFE CHARTS |  |  | 73 | 2022-03-29 | 2022-07-18 | 2022-07-18 | 2022-12-19 | 109
0 | EDTGPR1140 | CAUSE & EFFECT CHARTS - HAIR DALMA T4 WHP - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-07-18 | 2022-07-29 | 73
0 | EDTGPR1155 | SAFE CHART - HAIR DALMA T4 WHP - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-08-29 | 2022-09-09 | 93
0 | EDTGPR1145 | CAUSE & EFFECT CHARTS - HAIR DALMA T4 WHP - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-08-15 | 2022-08-26 | 73
0 | EDTGPR1160 | SAFE CHART - HAIR DALMA T4 WHP - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-09-22 | 2022-10-05 | 93
0 | EDTGPR1165 | SAFE CHART - HAIR DALMA T4 WHP - IFC | 25 | 2022-06-06 | 2022-07-14 | 2022-10-18 | 2022-11-21 | 93
0 | EDTGPR1150 | CAUSE & EFFECT CHARTS - HAIR DALMA T4 WHP - IFC | 35 | 2022-05-25 | 2022-07-18 | 2022-10-28 | 2022-12-19 | 109
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDTGPR2000 | HD-T4 PROCESS MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDTGPR2005 | HD-T4 PROCESS MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDTGPR2010 | HD-T4 PROCESS MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
MATERIAL & CORROSION |  |  | 228 | 2022-02-11 | 2023-01-09 | 2022-04-25 | 2023-04-27 | 77
DOCUMENTS |  |  | 66 | 2022-08-31 | 2022-12-05 | 2022-11-11 | 2023-02-14 | 52
0 | EDTDMA1000 | HD-T4 DEAD-LEG REGISTER - ICR | 15 | 2022-08-31 | 2022-09-21 | 2022-11-11 | 2022-12-05 | 52
0 | EDTDMA1010 | HD-T4 DEAD-LEG REGISTER - IFA | 15 | 2022-10-05 | 2022-10-26 | 2022-12-20 | 2023-01-09 | 52
0 | EDTDMA1020 | HD-T4 DEAD-LEG REGISTER - IFC | 18 | 2022-11-07 | 2022-12-05 | 2023-01-20 | 2023-02-14 | 52
DRAWINGS |  |  | 75 | 2022-02-11 | 2022-06-01 | 2022-04-25 | 2022-11-21 | 121
0 | EDTGMA1000 | MATERIAL SELECTION DIAGRAMS - HAIR DALMA T4 WHP - ICR | 15 | 2022-02-11 | 2022-03-04 | 2022-04-25 | 2022-05-18 | 51
0 | EDTGMA1005 | MATERIAL SELECTION DIAGRAMS - HAIR DALMA T4 WHP - IFA | 15 | 2022-03-18 | 2022-04-08 | 2022-08-08 | 2022-08-26 | 95
0 | EDTGMA1010 | MATERIAL SELECTION DIAGRAMS - HAIR DALMA T4 WHP - IFC | 25 | 2022-04-22 | 2022-06-01 | 2022-10-18 | 2022-11-21 | 121
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDTGMA2000 | HD-T4 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDTGMA2005 | HD-T4 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDTGMA2010 | HD-T4 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
SAFETY |  |  | 321 | 2022-02-22 | 2023-01-09 | 2022-06-08 | 2023-04-27 | 109
DRAWINGS |  |  | 246 | 2022-02-22 | 2022-10-26 | 2022-06-08 | 2023-01-24 | 91
0 | EDTGSA1000 | P&ID FIREWATER DRY SYSTEM - HAIR DALMA T4 WHP - ICR | 15 | 2022-02-22 | 2022-03-15 | 2022-06-08 | 2022-06-28 | 73
0 | EDTGSA1005 | P&ID FIREWATER DRY SYSTEM - HAIR DALMA T4 WHP - ISSUED FOR HAZOP | 15 | 2022-03-29 | 2022-04-19 | 2022-07-18 | 2022-08-07 | 79
0 | EDTGSA1015 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - HAIR DALMA T4 WHP - ICR | 10 | 2022-05-16 | 2022-05-30 | 2022-08-23 | 2022-09-05 | 68
0 | EDTGSA1030 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - HAIR DALMA T4 WHP - ICR | 10 | 2022-06-17 | 2022-07-01 | 2022-09-30 | 2022-10-13 | 72
0 | EDTGSA1007 | P&ID FIREWATER DRY SYSTEM - HAIR DALMA T4 WHP - IFA | 15 | 2022-06-12 | 2022-07-03 | 2022-08-30 | 2022-09-19 | 57
0 | EDTGSA1020 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - HAIR DALMA T4 WHP - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-09-29 | 2022-10-12 | 73
0 | EDTGSA1060 | FIRE AND GAS CAUSE & EFFECT CHART – HAIR DALMA T4 WHP - ICR | 15 | 2022-07-01 | 2022-07-27 | 2022-11-01 | 2022-11-21 | 84
0 | EDTGSA1010 | P&ID FIREWATER DRY SYSTEM - HAIR DALMA T4 WHP - IFC | 15 | 2022-07-14 | 2022-08-04 | 2022-10-04 | 2022-10-24 | 57
0 | EDTGSA1035 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - HAIR DALMA T4 WHP - IFA | 10 | 2022-07-27 | 2022-08-10 | 2022-12-07 | 2022-12-20 | 95
0 | EDTGSA1075 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - HAIR DALMA T4 WHP - ICR | 15 | 2022-07-27 | 2022-08-17 | 2022-10-27 | 2022-11-16 | 66
0 | EDTGSA1065 | FIRE AND GAS CAUSE & EFFECT CHART – HAIR DALMA T4 WHP - IFA | 10 | 2022-08-10 | 2022-08-24 | 2022-12-08 | 2022-12-21 | 86
0 | EDTGSA1025 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - HAIR DALMA T4 WHP - IFC | 15 | 2022-08-11 | 2022-09-01 | 2023-01-04 | 2023-01-24 | 102
0 | EDTGSA1070 | FIRE AND GAS CAUSE & EFFECT CHART – HAIR DALMA T4 WHP - IFC | 10 | 2022-09-07 | 2022-09-21 | 2023-01-05 | 2023-01-18 | 84
0 | EDTGSA1080 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - HAIR DALMA T4 WHP - IFA | 15 | 2022-08-31 | 2022-09-21 | 2022-12-01 | 2022-12-21 | 66
0 | EDTGSA1040 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - HAIR DALMA T4 WHP - IFC | 15 | 2022-09-07 | 2022-09-28 | 2023-01-04 | 2023-01-24 | 83
0 | EDTGSA1085 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - HAIR DALMA T4 WHP - IFC | 10 | 2022-10-12 | 2022-10-26 | 2023-01-05 | 2023-01-18 | 59
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDTGSA2000 | HD-T4 SAFETY MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDTGSA2005 | HD-T4 SAFETY MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDTGSA2010 | HD-T4 SAFETY MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
PIPING |  |  | 214 | 2022-03-15 | 2023-01-19 | 2022-05-31 | 2023-07-21 | 126
3D MODELING |  |  | 166 | 2022-05-25 | 2023-01-19 | 2022-08-17 | 2023-04-27 | 69
30% MODEL REVIEW/REPORT |  |  | 50 | 2022-05-25 | 2022-08-08 | 2022-08-17 | 2022-11-01 | 62
0 | EDTDPI3100 | HD-T4 30% 3D MODEL REVIEW REPORT - ICR | 10 | 2022-05-25 | 2022-06-08 | 2022-08-17 | 2022-08-30 | 57
0 | EDTDPI3105 | HD-T4 30% 3D MODEL REVIEW REPORT - IFA | 10 | 2022-06-22 | 2022-07-06 | 2022-09-15 | 2022-09-28 | 58
0 | EDTDPI3110 | HD-T4 30% 3D MODEL REVIEW REPORT - IFC | 10 | 2022-07-25 | 2022-08-08 | 2022-10-19 | 2022-11-01 | 62
60% MODEL REVIEW/REPORT |  |  | 60 | 2022-08-26 | 2022-11-18 | 2022-11-02 | 2023-03-02 | 73
0 | EDTDPI3120 | HD-T4 60% 3D MODEL REVIEW REPORT - ICR | 10 | 2022-08-26 | 2022-09-09 | 2022-11-02 | 2022-11-15 | 48
0 | EDTDPI3125 | HD-T4 60% 3D MODEL REVIEW REPORT - IFA | 10 | 2022-09-23 | 2022-10-07 | 2022-12-30 | 2023-01-12 | 68
0 | EDTDPI3130 | HD-T4 60% 3D MODEL REVIEW REPORT - IFC | 20 | 2022-10-21 | 2022-11-18 | 2023-02-03 | 2023-03-02 | 73
90% MODEL REVIEW/REPORT |  |  | 41 | 2022-11-21 | 2023-01-19 | 2023-03-03 | 2023-04-27 | 69
0 | EDTDPI3140 | HD-T4 90% 3D MODEL REVIEW REPORT - ICR | 8 | 2022-11-21 | 2022-12-05 | 2023-03-03 | 2023-03-14 | 72
0 | EDTDPI3145 | HD-T4 90% 3D MODEL REVIEW REPORT - IFA | 7 | 2022-12-21 | 2022-12-30 | 2023-03-29 | 2023-04-06 | 70
0 | EDTDPI3150 | HD-T4 90% 3D MODEL REVIEW REPORT - IFC | 3 | 2023-01-16 | 2023-01-19 | 2023-04-25 | 2023-04-27 | 69
3D MODEL DEVELOPMENT |  |  | 200 | 2022-04-04 | 2023-01-19 | 2022-07-18 | 2023-04-27 | 69
0 | EDTDPI3000 | HD-T4 3D MODEL DEVELOPMENT - PIPING | 200 | 2022-04-04 | 2023-01-19 | 2022-07-18 | 2023-04-27 | 69
DOCUMENTS |  |  | 203 | 2022-03-29 | 2023-01-18 | 2022-09-22 | 2023-07-21 | 127
REPORTS & CALCULATIONS |  |  | 203 | 2022-03-29 | 2023-01-18 | 2022-09-22 | 2023-07-21 | 127
0 | EDTDPI1000 | HAIR DALMA T4 WELLHEAD PLATFORM PIPE STRESS CRITICAL LINE LIST - ICR | 15 | 2022-03-29 | 2022-04-19 | 2022-11-02 | 2022-11-22 | 150
0 | EDTDPI1005 | HAIR DALMA T4 WELLHEAD PLATFORMBH PIPE STRESS CRITICAL LINE LIST - IFA | 15 | 2022-05-06 | 2022-05-27 | 2022-12-09 | 2022-12-29 | 150
0 | EDTDPI1015 | HAIR DALMA T4 WELLHEAD PLATFORMBH PIPING STRESS ANALYSIS REPORT - ICR | 15 | 2022-05-30 | 2022-06-20 | 2022-12-20 | 2023-01-09 | 141
0 | EDTDPI1010 | HAIR DALMA T4 WELLHEAD PLATFORMBH PIPE STRESS CRITICAL LINE LIST - IFC | 20 | 2022-06-10 | 2022-07-13 | 2023-01-13 | 2023-02-09 | 150
0 | EDTDPI1030 | HD-T4 MECHANICAL HANDLING STUDY REPORT - ICR | 10 | 2022-06-29 | 2022-07-18 | 2022-09-22 | 2022-10-05 | 58
0 | EDTDPI1035 | HD-T4 MECHANICAL HANDLING STUDY REPORT - IFA | 10 | 2022-08-26 | 2022-09-09 | 2023-03-14 | 2023-03-27 | 140
0 | EDTDPI1020 | HAIR DALMA T4 WELLHEAD PLATFORMBH PIPING STRESS ANALYSIS REPORT - IFA | 15 | 2022-08-31 | 2022-09-21 | 2023-01-10 | 2023-01-30 | 92
0 | EDTDPI1040 | HD-T4 MECHANICAL HANDLING STUDY REPORT - IFC | 10 | 2022-11-21 | 2022-12-07 | 2023-04-12 | 2023-04-27 | 100
0 | EDTDPI1050 | HD-T4 PIPE SUPPORT SCHEDULE - IFI | 10 | 2022-12-07 | 2022-12-21 | 2023-06-06 | 2023-06-19 | 127
0 | EDTDPI1025 | HAIR DALMA T4 WELLHEAD PLATFORMBH PIPING STRESS ANALYSIS REPORT - IFC | 20 | 2022-11-30 | 2022-12-30 | 2023-02-10 | 2023-03-09 | 50
0 | EDTDPI1060 | HD-T4 PIPE SUPPORT SCHEDULE - IFC | 10 | 2023-01-04 | 2023-01-18 | 2023-07-07 | 2023-07-21 | 127
DRAWINGS |  |  | 214 | 2022-03-15 | 2023-01-19 | 2022-05-31 | 2023-07-21 | 126
0 | EDTGPI1000 | HAIR DALMA T4 WELLHEAD PLATFORMBH PLOT PLAN DRAWINGS - ICR | 30 | 2022-03-15 | 2022-04-26 | 2022-05-31 | 2022-07-14 | 52
0 | EDTGPI1005 | HAIR DALMA T4 WELLHEAD PLATFORMBH PLOT PLAN DRAWINGS - IFA | 22 | 2022-05-13 | 2022-06-14 | 2022-08-23 | 2022-09-21 | 68
0 | EDTGPI1035 | HD- T4 SPECIAL SUPPORT DRAWINGS - ICR | 10 | 2022-11-21 | 2022-12-07 | 2023-05-22 | 2023-06-02 | 126
0 | EDTGPI1010 | HAIR DALMA T4 WELLHEAD PLATFORMBH PLOT PLAN DRAWINGS - IFC | 17 | 2022-11-21 | 2022-12-16 | 2023-03-27 | 2023-04-18 | 88
0 | EDTGPI1015 | HAIR DALMA T4 WELLHEAD PLATFORMBH ENGINEERING ISOMETRICS | 18 | 2022-11-21 | 2022-12-19 | 2023-03-02 | 2023-03-27 | 71
0 | EDTGPI1020 | HAIR DALMA T4 WELLHEAD PLATFORMBH PIPING GA DRAWING - IFI | 10 | 2022-12-12 | 2022-12-26 | 2023-03-21 | 2023-04-03 | 71
0 | EDTGPI1040 | HD- T4 SPECIAL SUPPORT DRAWINGS - IFA | 7 | 2022-12-21 | 2022-12-30 | 2023-06-19 | 2023-06-30 | 126
0 | EDTGPI1025 | HAIR DALMA T4 WELLHEAD PLATFORMBH PIPING GA DRAWING - IFC | 6 | 2023-01-09 | 2023-01-17 | 2023-04-18 | 2023-04-27 | 71
0 | EDTGPI1045 | HD- T4 SPECIAL SUPPORT DRAWINGS - IFC | 4 | 2023-01-13 | 2023-01-19 | 2023-07-17 | 2023-07-21 | 126
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDTGPI2000 | HD-T4 PIPING MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDTGPI2005 | HD-T4 PIPING MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDTGPI2010 | HD-T4 PIPING MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
MECHANICAL (STATIC / ROTATING) |  |  | 210 | 2022-03-09 | 2023-01-09 | 2022-05-18 | 2023-04-27 | 77
STATIC |  |  | 210 | 2022-03-09 | 2023-01-09 | 2022-05-18 | 2023-04-27 | 77
DOCUMENTS |  |  | 123 | 2022-03-09 | 2022-09-06 | 2022-05-18 | 2022-12-29 | 81
CALCULATION |  |  | 65 | 2022-06-02 | 2022-09-06 | 2022-08-11 | 2022-12-29 | 81
0 | EDTDME1000 | HD-T4 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (HD304-V-001) - ICR | 20 | 2022-06-02 | 2022-06-30 | 2022-08-11 | 2022-09-07 | 47
0 | EDTDME1005 | HD-T4 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (HD304-V-001) - IFA | 15 | 2022-07-19 | 2022-08-09 | 2022-11-09 | 2022-11-29 | 81
0 | EDTDME1010 | HD-T4 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (HD304-V-001) - IFC | 10 | 2022-08-23 | 2022-09-06 | 2022-12-16 | 2022-12-29 | 81
DATA SHEET |  |  | 94 | 2022-03-09 | 2022-07-27 | 2022-05-18 | 2022-11-29 | 90
0 | EDTDME1015 | HD-T4 MECHANICAL DATA SHEET FOR PIG LAUNCHER (HD304-PL-001) - ICR | 10 | 2022-03-09 | 2022-03-23 | 2022-05-18 | 2022-05-31 | 47
0 | EDTDME1030 | HD-T4 MECHANICAL DATA SHEET FOR PIG RECEIVER (HD304-RC-001) - ICR | 10 | 2022-03-09 | 2022-03-23 | 2022-05-18 | 2022-05-31 | 47
0 | EDTDME1020 | HD-T4 MECHANICAL DATA SHEET FOR PIG LAUNCHER (HD304-PL-001) - IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-06-15 | 2022-06-28 | 47
0 | EDTDME1035 | HD-T4 MECHANICAL DATA SHEET FOR PIG RECEIVER (HD304-RC-001) - IFA | 10 | 2022-04-06 | 2022-04-20 | 2022-06-15 | 2022-06-28 | 47
0 | EDTDME1045 | HD-T4 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (HD304-V-001) - ICR | 14 | 2022-04-20 | 2022-05-13 | 2022-06-29 | 2022-07-21 | 47
0 | EDTDME1025 | HD-T4 MECHANICAL DATA SHEET FOR PIG LAUNCHER (HD304-PL-001) - IFC | 8 | 2022-05-09 | 2022-05-19 | 2022-07-18 | 2022-07-27 | 47
0 | EDTDME1040 | HD-T4 MECHANICAL DATA SHEET FOR PIG RECEIVER (HD304-RC-001) - IFC | 8 | 2022-05-09 | 2022-05-19 | 2022-07-18 | 2022-07-27 | 47
0 | EDTDME1050 | HD-T4 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (HD304-V-001) - IFA | 10 | 2022-05-27 | 2022-06-10 | 2022-10-05 | 2022-10-18 | 90
0 | EDTDME1055 | HD-T4 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (HD304-V-001) - IFC | 20 | 2022-06-24 | 2022-07-27 | 2022-11-02 | 2022-11-29 | 90
DRAWINGS |  |  | 71 | 2022-06-30 | 2022-10-12 | 2022-09-08 | 2023-02-01 | 79
0 | EDTGME1000 | HD-T4 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.HD304-V-001) - ICR | 10 | 2022-06-30 | 2022-07-19 | 2022-09-08 | 2022-09-21 | 47
0 | EDTGME1015 | HD-T4 DETAIL DRAWING FOR VENT DRAIN DRUM (HD304-V-001) - IFI | 10 | 2022-07-20 | 2022-08-03 | 2022-10-06 | 2022-10-19 | 56
0 | EDTGME1045 | HD-T4 NOZZLE DETAIL (TAG NO. HD304-V-001) - IFI | 10 | 2022-07-26 | 2022-08-09 | 2022-10-26 | 2022-11-08 | 66
0 | EDTGME1030 | HD-T4 WELDING DETAIL & WELD MAP (TAG NO. HD304-V-001) - IFI | 10 | 2022-08-01 | 2022-08-15 | 2022-11-01 | 2022-11-14 | 66
0 | EDTGME1005 | HD-T4 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.HD304-V-001) - IFA | 10 | 2022-08-02 | 2022-08-16 | 2022-10-06 | 2022-10-19 | 47
0 | EDTGME1060 | HD-T4 MANWAY DAVIT DETAIL (TAG NO. HD304-V-001) - IFI | 9 | 2022-08-05 | 2022-08-18 | 2022-11-07 | 2022-11-17 | 66
0 | EDTGME1075 | HD-T4 INTERNAL / EXTERNAL ATTACHMENTS (TAG NO. HD304-V-001) - IFI | 10 | 2022-08-11 | 2022-08-25 | 2022-11-11 | 2022-11-24 | 66
0 | EDTGME1090 | HD-T4 NAME PLATE DETAIL (TAG NO. HD304-V-001) - IFI | 10 | 2022-08-17 | 2022-08-31 | 2022-12-08 | 2022-12-21 | 79
0 | EDTGME1025 | HD-T4 DETAIL DRAWING FOR VENT DRAIN DRUM (HD304-V-001) - IFC | 15 | 2022-08-17 | 2022-09-07 | 2022-11-30 | 2022-12-22 | 75
0 | EDTGME1055 | HD-T4 NOZZLE DETAIL (TAG NO. HD304-V-001) - IFC | 20 | 2022-08-23 | 2022-09-20 | 2022-12-13 | 2023-01-09 | 78
0 | EDTGME1040 | HD-T4 WELDING DETAIL & WELD MAP (TAG NO. HD304-V-001) - IFC | 20 | 2022-08-29 | 2022-09-26 | 2022-12-13 | 2023-01-09 | 74
0 | EDTGME1010 | HD-T4 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.HD304-V-001) - IFC | 20 | 2022-08-30 | 2022-09-27 | 2022-12-13 | 2023-01-09 | 73
0 | EDTGME1070 | HD-T4 MANWAY DAVIT DETAIL (TAG NO. HD304-V-001) - IFC | 19 | 2022-09-01 | 2022-09-28 | 2022-12-14 | 2023-01-09 | 72
0 | EDTGME1085 | HD-T4 INTERNAL / EXTERNAL ATTACHMENTS (TAG NO. HD304-V-001) - IFC | 20 | 2022-09-08 | 2022-10-06 | 2022-12-13 | 2023-01-09 | 66
0 | EDTGME1100 | HD-T4 NAME PLATE DETAIL (TAG NO. HD304-V-001) - IFC | 20 | 2022-09-14 | 2022-10-12 | 2023-01-05 | 2023-02-01 | 79
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDTGME2000 | HD-T4 MECHANICAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDTGME2005 | HD-T4 MECHANICAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDTGME2010 | HD-T4 MECHANICAL MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
PACKAGE EQUIPMENT |  |  | 47 | 2022-03-24 | 2022-06-02 | 2022-06-20 | 2022-09-07 | 67
DOCUMENTS |  |  | 47 | 2022-03-24 | 2022-06-02 | 2022-06-20 | 2022-09-07 | 67
DATASHEETS |  |  | 47 | 2022-03-24 | 2022-06-02 | 2022-06-20 | 2022-09-07 | 67
0 | EDTDME1060 | HD-T4 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - ICR | 9 | 2022-03-24 | 2022-04-06 | 2022-06-20 | 2022-06-30 | 59
0 | EDTDME1065 | HD-T4 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - IFA | 9 | 2022-04-20 | 2022-05-06 | 2022-08-01 | 2022-08-11 | 67
0 | EDTDME1070 | HD-T4 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - IFC | 9 | 2022-05-20 | 2022-06-02 | 2022-08-26 | 2022-09-07 | 67
ELECTRICAL |  |  | 191 | 2022-04-15 | 2023-01-19 | 2022-07-07 | 2023-04-27 | 69
3D MODEL DEVELOPMENT |  |  | 185 | 2022-04-25 | 2023-01-19 | 2022-08-08 | 2023-04-27 | 69
0 | EDTDEL3000 | HD-T4 3D MODEL DEVELOPMENT - ELECTRICAL | 185 | 2022-04-25 | 2023-01-19 | 2022-08-08 | 2023-04-27 | 69
DRAWINGS |  |  | 190 | 2022-04-15 | 2023-01-18 | 2022-07-07 | 2023-04-27 | 70
DIAGRAM |  |  | 160 | 2022-04-15 | 2022-12-07 | 2022-07-07 | 2023-04-27 | 100
0 | EDTGEL1000 | HD-T4 SINGLE LINE DIAGRAM – 6.6KV RMU - ICR | 15 | 2022-04-15 | 2022-05-11 | 2022-08-24 | 2022-09-13 | 87
0 | EDTGEL1002 | HD-T4 ELECTRICAL EQUIPMENT LIST - ICR | 15 | 2022-04-25 | 2022-05-19 | 2022-07-07 | 2022-08-01 | 50
0 | EDTGEL1015 | HD-T4 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - ICR | 15 | 2022-04-29 | 2022-05-25 | 2022-09-07 | 2022-09-27 | 87
0 | EDTGEL1003 | HD-T4 ELECTRICAL LOAD LIST - ICR | 15 | 2022-05-05 | 2022-05-26 | 2022-07-21 | 2022-08-10 | 52
0 | EDTGEL1030 | HD-T4 SINGLE LINE DIAGRAM – 24V DC UPS - ICR | 15 | 2022-05-11 | 2022-06-01 | 2022-09-14 | 2022-10-04 | 87
0 | EDTGEL1045 | HD-T4 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - ICR | 15 | 2022-05-18 | 2022-06-08 | 2022-09-21 | 2022-10-11 | 87
0 | EDTGEL1005 | HD-T4 SINGLE LINE DIAGRAM – 6.6KV RMU - IFA | 10 | 2022-05-25 | 2022-06-08 | 2022-10-24 | 2022-11-04 | 105
0 | EDTGEL1060 | HD-T4 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - ICR | 15 | 2022-05-25 | 2022-06-15 | 2022-09-28 | 2022-10-18 | 87
0 | EDTGEL1075 | HD-T4 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - ICR | 15 | 2022-06-01 | 2022-06-22 | 2022-10-10 | 2022-10-28 | 90
0 | EDTGEL1020 | HD-T4 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - IFA | 10 | 2022-06-08 | 2022-06-22 | 2022-10-24 | 2022-11-04 | 95
0 | EDTGEL1006 | HD-T4 ELECTRICAL EQUIPMENT LIST - IFA | 15 | 2022-06-02 | 2022-06-23 | 2022-09-01 | 2022-09-21 | 62
0 | EDTGEL1035 | HD-T4 SINGLE LINE DIAGRAM – 24V DC UPS - IFA | 10 | 2022-06-15 | 2022-06-29 | 2022-10-24 | 2022-11-04 | 90
0 | EDTGEL1009 | HD-T4 ELECTRICAL LOAD LIST - IFA | 15 | 2022-06-09 | 2022-06-30 | 2022-09-08 | 2022-09-28 | 62
0 | EDTGEL1050 | HD-T4 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - IFA | 10 | 2022-06-22 | 2022-07-06 | 2022-10-31 | 2022-11-11 | 90
0 | EDTGEL1010 | HD-T4 SINGLE LINE DIAGRAM – 6.6KV RMU - IFC | 15 | 2022-06-22 | 2022-07-18 | 2022-11-21 | 2022-12-13 | 105
0 | EDTGEL1065 | HD-T4 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - IFA | 10 | 2022-06-29 | 2022-07-18 | 2022-11-02 | 2022-11-15 | 87
0 | EDTGEL1080 | HD-T4 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - IFA | 10 | 2022-07-06 | 2022-07-25 | 2022-11-14 | 2022-11-25 | 90
0 | EDTGEL1025 | HD-T4 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - IFC | 15 | 2022-07-06 | 2022-08-01 | 2022-11-21 | 2022-12-13 | 95
0 | EDTGEL1040 | HD-T4 SINGLE LINE DIAGRAM – 24V DC UPS - IFC | 15 | 2022-07-18 | 2022-08-08 | 2022-11-21 | 2022-12-13 | 90
0 | EDTGEL1055 | HD-T4 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - IFC | 10 | 2022-07-25 | 2022-08-08 | 2022-11-28 | 2022-12-13 | 90
0 | EDTGEL1004 | HD-T4 ELECTRICAL EQUIPMENT LIST - IFC | 20 | 2022-07-07 | 2022-08-09 | 2022-10-06 | 2022-11-02 | 62
0 | EDTGEL1007 | HD-T4 ELECTRICAL LOAD LIST - IFC | 20 | 2022-07-19 | 2022-08-16 | 2022-10-13 | 2022-11-09 | 62
0 | EDTGEL1070 | HD-T4 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - IFC | 13 | 2022-08-01 | 2022-08-18 | 2022-11-30 | 2022-12-20 | 87
0 | EDTGEL1085 | HD-T4 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - IFC | 10 | 2022-08-08 | 2022-08-22 | 2022-12-14 | 2022-12-27 | 90
0 | EDTGEL1090 | HD-T4 ELECTRICAL CABLE SCHEDULE - ICR | 15 | 2022-08-10 | 2022-08-31 | 2023-01-04 | 2023-01-24 | 103
0 | EDTGEL1105 | HD-T4 ELECTRICAL INTERCONNECTION DIAGRAM - ICR | 15 | 2022-09-05 | 2022-09-26 | 2023-01-25 | 2023-02-14 | 100
0 | EDTGEL1095 | HD-T4 ELECTRICAL CABLE SCHEDULE - IFA | 10 | 2022-09-14 | 2022-09-28 | 2023-03-08 | 2023-03-21 | 123
0 | EDTGEL2020 | HD-T4 ELECTRICAL INTERCONNECTION DIAGRAM - IFA | 15 | 2022-10-10 | 2022-10-31 | 2023-03-01 | 2023-03-21 | 100
0 | EDTGEL1100 | HD-T4 ELECTRICAL CABLE SCHEDULE - IFC | 15 | 2022-10-12 | 2022-11-02 | 2023-04-05 | 2023-04-27 | 123
0 | EDTGEL1110 | HD-T4 ELECTRICAL INTERCONNECTION DIAGRAM - IFC | 15 | 2022-11-14 | 2022-12-07 | 2023-04-05 | 2023-04-27 | 100
BOOKLET |  |  | 50 | 2022-11-07 | 2023-01-18 | 2023-02-15 | 2023-04-27 | 70
0 | EDTGEL1200 | HD-T4 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - ICR | 10 | 2022-11-07 | 2022-11-21 | 2023-02-15 | 2023-02-28 | 70
0 | EDTGEL2030 | HD-T4 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - IFA | 10 | 2022-12-07 | 2022-12-21 | 2023-03-15 | 2023-03-28 | 70
0 | EDTGEL1205 | HD-T4 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - IFC | 10 | 2023-01-04 | 2023-01-18 | 2023-04-12 | 2023-04-27 | 70
LAYOUT |  |  | 137 | 2022-05-05 | 2022-11-17 | 2022-12-14 | 2023-04-27 | 112
0 | EDTGEL1300 | HD-T4 ELECTRICAL EQUIPMENT LAYOUT - ICR | 15 | 2022-05-05 | 2022-05-26 | 2023-01-18 | 2023-02-07 | 179
0 | EDTGEL1305 | HD-T4 ELECTRICAL EQUIPMENT LAYOUT - IFA | 10 | 2022-06-09 | 2022-06-23 | 2023-02-22 | 2023-03-07 | 179
0 | EDTGEL1315 | HD-T4 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - ICR | 10 | 2022-08-11 | 2022-08-25 | 2022-12-14 | 2022-12-27 | 87
0 | EDTGEL1375 | HD-T4 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-01-13 | 2023-01-26 | 109
0 | EDTGEL1390 | HD-T4 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - ICR | 10 | 2022-08-12 | 2022-08-26 | 2023-02-13 | 2023-02-24 | 129
0 | EDTGEL1330 | HD-T4 ELECTRICAL CABLE ROUTING LAYOUT - ICR | 15 | 2022-08-11 | 2022-09-01 | 2022-12-14 | 2023-01-03 | 87
0 | EDTGEL1360 | HD-T4 EARTHING & LIGHTNING PROTECTION LAYOUT - ICR | 15 | 2022-08-18 | 2022-09-08 | 2023-01-20 | 2023-02-09 | 109
0 | EDTGEL1345 | HD-T4 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - ICR | 15 | 2022-08-18 | 2022-09-08 | 2022-12-21 | 2023-01-10 | 87
0 | EDTGEL1310 | HD-T4 ELECTRICAL EQUIPMENT LAYOUT - IFC | 15 | 2022-08-22 | 2022-09-12 | 2023-03-22 | 2023-04-11 | 150
0 | EDTGEL1380 | HD-T4 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-02-24 | 2023-03-09 | 119
0 | EDTGEL2040 | HD-T4 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-10 | 2023-03-23 | 129
0 | EDTGEL1395 | HD-T4 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - IFA | 10 | 2022-09-09 | 2022-09-23 | 2023-03-13 | 2023-03-24 | 129
0 | EDTGEL2050 | HD-T4 ELECTRICAL CABLE ROUTING LAYOUT - IFA | 15 | 2022-09-15 | 2022-10-06 | 2023-03-01 | 2023-03-21 | 117
0 | EDTGEL2060 | HD-T4 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IFA | 15 | 2022-09-22 | 2022-10-13 | 2023-01-25 | 2023-02-14 | 87
0 | EDTGEL2070 | HD-T4 EARTHING & LIGHTNING PROTECTION LAYOUT - IFA | 15 | 2022-09-22 | 2022-10-13 | 2023-02-24 | 2023-03-16 | 109
0 | EDTGEL1385 | HD-T4 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-03-24 | 2023-04-06 | 119
0 | EDTGEL1400 | HD-T4 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - IFC | 9 | 2022-10-07 | 2022-10-20 | 2023-04-10 | 2023-04-20 | 129
0 | EDTGEL1325 | HD-T4 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IFC | 10 | 2022-10-21 | 2022-11-04 | 2023-04-07 | 2023-04-20 | 118
0 | EDTGEL1340 | HD-T4 ELECTRICAL CABLE ROUTING LAYOUT - IFC | 15 | 2022-10-20 | 2022-11-10 | 2023-04-05 | 2023-04-27 | 117
0 | EDTGEL1355 | HD-T4 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IFC | 15 | 2022-10-27 | 2022-11-17 | 2023-03-01 | 2023-03-21 | 87
0 | EDTGEL1370 | HD-T4 EARTHING & LIGHTNING PROTECTION LAYOUT - IFC | 15 | 2022-10-27 | 2022-11-17 | 2023-03-31 | 2023-04-20 | 109
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDTGEL2000 | HD-T4 ELECTRICAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDTGEL2005 | HD-T4 ELECTRICAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDTGEL2010 | HD-T4 ELECTRICAL MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
INSTRUMENTATION & CONTROL |  |  | 216 | 2022-03-11 | 2023-01-19 | 2022-06-02 | 2023-04-27 | 69
3D MIODEL DEVELOPMENT |  |  | 180 | 2022-05-05 | 2023-01-19 | 2022-08-15 | 2023-04-27 | 69
0 | EDTDIN3000 | HD-T4 3D MODEL DEVELOPMENT - INSTRUMENTATION | 180 | 2022-05-05 | 2023-01-19 | 2022-08-15 | 2023-04-27 | 69
DOCUMENTS |  |  | 212 | 2022-03-11 | 2023-01-13 | 2022-06-02 | 2023-04-27 | 73
CALCULATIONS |  |  | 80 | 2022-03-22 | 2022-07-20 | 2022-06-09 | 2022-12-26 | 112
0 | EDTDIN1000 | HD-T4 CALCULATION NOTE FOR CHOKE VALVES - ICR | 15 | 2022-03-22 | 2022-04-12 | 2022-06-09 | 2022-06-29 | 54
0 | EDTDIN1030 | HD-T4 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - ICR | 15 | 2022-03-28 | 2022-04-18 | 2022-09-07 | 2022-09-27 | 111
0 | EDTDIN1045 | HD-T4 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - ICR | 15 | 2022-04-13 | 2022-05-09 | 2022-10-07 | 2022-10-27 | 121
0 | EDTDIN1005 | HD-T4 CALCULATION NOTE FOR CHOKE VALVES - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-07-19 | 2022-08-01 | 54
0 | EDTDIN1035 | HD-T4 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-10-12 | 2022-10-25 | 111
0 | EDTDIN1015 | HD-T4 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - ICR | 10 | 2022-05-06 | 2022-05-20 | 2022-09-15 | 2022-09-28 | 91
0 | EDTDIN1050 | HD-T4 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - IFA | 10 | 2022-05-23 | 2022-06-06 | 2022-11-11 | 2022-11-24 | 121
0 | EDTDIN1010 | HD-T4 CALCULATION NOTE FOR CHOKE VALVES - IFC | 10 | 2022-05-27 | 2022-06-10 | 2022-08-16 | 2022-08-29 | 54
0 | EDTDIN1040 | HD-T4 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - IFC | 10 | 2022-06-02 | 2022-06-16 | 2022-11-09 | 2022-11-22 | 111
0 | EDTDIN1020 | HD-T4 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - IFA | 10 | 2022-06-03 | 2022-06-17 | 2022-10-13 | 2022-10-26 | 91
0 | EDTDIN1055 | HD-T4 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - IFC | 10 | 2022-06-20 | 2022-07-04 | 2022-12-13 | 2022-12-26 | 121
0 | EDTDIN1025 | HD-T4 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - IFC | 10 | 2022-07-01 | 2022-07-20 | 2022-11-10 | 2022-11-23 | 91
INDEX / NARRATIVE |  |  | 45 | 2022-09-01 | 2022-11-03 | 2022-11-21 | 2023-01-24 | 57
0 | EDTDIN1060 | HD-T4 INSTRUMENT INDEX - ICR | 10 | 2022-09-01 | 2022-09-15 | 2022-11-21 | 2022-12-06 | 57
0 | EDTDIN1075 | HD-T4 FIRE & GAS INDEX - ICR | 10 | 2022-09-01 | 2022-09-15 | 2022-11-21 | 2022-12-06 | 57
0 | EDTDIN1065 | HD-T4 INSTRUMENT INDEX - IFA | 10 | 2022-09-29 | 2022-10-13 | 2022-12-21 | 2023-01-03 | 57
0 | EDTDIN1080 | HD-T4 FIRE & GAS INDEX - IFA | 10 | 2022-09-29 | 2022-10-13 | 2022-12-21 | 2023-01-03 | 57
0 | EDTDIN1070 | HD-T4 INSTRUMENT INDEX - IFC | 5 | 2022-10-27 | 2022-11-03 | 2023-01-18 | 2023-01-24 | 57
0 | EDTDIN1085 | HD-T4 FIRE & GAS INDEX - IFC | 5 | 2022-10-27 | 2022-11-03 | 2023-01-18 | 2023-01-24 | 57
DATA SHEET |  |  | 93 | 2022-03-11 | 2022-07-28 | 2022-06-02 | 2023-01-25 | 128
0 | EDTDIN1100 | HD-T4 DATASHEETS FOR HIPPS VALVES - ICR | 10 | 2022-03-11 | 2022-03-25 | 2022-06-13 | 2022-06-24 | 63
0 | EDTDIN1175 | HD-T4 DATASHEETS FOR PRESSURE RELIEF VALVES - ICR | 10 | 2022-03-23 | 2022-04-06 | 2022-09-14 | 2022-09-27 | 119
0 | EDTDIN1160 | HD-T4 DATASHEETS FOR MOV - ICR | 10 | 2022-03-23 | 2022-04-06 | 2022-06-06 | 2022-06-17 | 50
0 | EDTDIN1145 | HD-T4 DATASHEETS FOR ACTUATED ON/OFF VALVES - ICR | 10 | 2022-03-24 | 2022-04-07 | 2022-06-06 | 2022-06-17 | 49
0 | EDTDIN1130 | HD-T4 DATASHEETS FOR CHOKE VALVES - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-06-06 | 2022-06-17 | 47
0 | EDTDIN1190 | HD-T4 DATASHEETS FOR FLOW CHOKE VALVE - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-06-02 | 2022-06-15 | 45
0 | EDTDIN1205 | HD-T4 DATASHEETS FOR SOLENOID OPERATED VALVES - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-06-02 | 2022-06-15 | 45
0 | EDTDIN1400 | HD-T4 DATASHEETS FOR ELECTRONIC SOUNDER - ICR | 9 | 2022-03-31 | 2022-04-13 | 2022-10-07 | 2022-10-19 | 130
0 | EDTDIN1220 | HD-T4 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-06-06 | 2022-06-17 | 44
0 | EDTDIN1415 | HD-T4 DATASHEETS FOR EMERGENCY S/D PB - ICR | 10 | 2022-04-04 | 2022-04-18 | 2022-10-11 | 2022-10-24 | 130
0 | EDTDIN1115 | HD-T4 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - ICR | 10 | 2022-04-05 | 2022-04-19 | 2022-06-13 | 2022-06-24 | 46
0 | EDTDIN1430 | HD-T4 DATASHEETS FOR FLAMMABLE GAS DETECTOR - ICR | 10 | 2022-04-06 | 2022-04-20 | 2022-10-13 | 2022-10-26 | 130
0 | EDTDIN1250 | HD-T4 DATASHEETS FOR PRESSURE GAUGES - ICR | 10 | 2022-04-08 | 2022-04-22 | 2022-09-20 | 2022-10-03 | 111
0 | EDTDIN1295 | HD-T4 DATASHEETS FOR TEMPERATURE GAUGES - ICR | 10 | 2022-04-08 | 2022-04-22 | 2022-09-16 | 2022-09-29 | 109
0 | EDTDIN1445 | HD-T4 DATASHEETS FOR FIRE GAS DETECTOR - ICR | 10 | 2022-04-08 | 2022-04-22 | 2022-10-17 | 2022-10-28 | 130
0 | EDTDIN1105 | HD-T4 DATASHEETS FOR HIPPS VALVES - IFA | 10 | 2022-04-08 | 2022-04-22 | 2022-07-14 | 2022-07-27 | 63
0 | EDTDIN1280 | HD-T4 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - ICR | 10 | 2022-04-11 | 2022-04-25 | 2022-09-01 | 2022-09-14 | 97
0 | EDTDIN1460 | HD-T4 DATASHEETS FOR FLASHING BEACON - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-10-24 | 2022-11-04 | 133
0 | EDTDIN1490 | HD-T4 DATASHEETS FOR MAN ON BOARD PB - ICR | 9 | 2022-04-14 | 2022-04-27 | 2022-10-26 | 2022-11-07 | 133
0 | EDTDIN1310 | HD-T4 DATASHEETS FOR TEMPERATURE TRANSMITTERS - ICR | 10 | 2022-04-13 | 2022-04-27 | 2022-09-06 | 2022-09-19 | 98
0 | EDTDIN1475 | HD-T4 DATASHEETS FOR HEAT DETECTOR - ICR | 10 | 2022-04-14 | 2022-04-28 | 2022-10-26 | 2022-11-08 | 133
0 | EDTDIN1340 | HD-T4 DATASHEETS FOR LEVEL GAUGES - ICR | 10 | 2022-04-15 | 2022-04-29 | 2022-09-14 | 2022-09-27 | 102
0 | EDTDIN1355 | HD-T4 DATASHEETS FOR LEVEL TRANSMITTERS - ICR | 10 | 2022-04-19 | 2022-05-06 | 2022-09-14 | 2022-09-27 | 100
0 | EDTDIN1520 | HD-T4 DATASHEETS FOR MANUAL ALARM CALL POINT - ICR | 10 | 2022-04-19 | 2022-05-06 | 2022-10-31 | 2022-11-11 | 133
0 | EDTDIN1165 | HD-T4 DATASHEETS FOR MOV - IFA | 10 | 2022-04-20 | 2022-05-09 | 2022-07-04 | 2022-07-20 | 50
0 | EDTDIN1180 | HD-T4 DATASHEETS FOR PRESSURE RELIEF VALVES - IFA | 10 | 2022-04-20 | 2022-05-09 | 2022-10-12 | 2022-10-25 | 119
0 | EDTDIN1370 | HD-T4 DATASHEETS FOR FLOW SWITCHES - ICR | 10 | 2022-04-21 | 2022-05-10 | 2022-09-26 | 2022-10-07 | 106
0 | EDTDIN1150 | HD-T4 DATASHEETS FOR ACTUATED ON/OFF VALVES - IFA | 10 | 2022-04-21 | 2022-05-10 | 2022-07-04 | 2022-07-20 | 49
0 | EDTDIN1135 | HD-T4 DATASHEETS FOR CHOKE VALVES - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-07-04 | 2022-07-20 | 47
0 | EDTDIN1195 | HD-T4 DATASHEETS FOR FLOW CHOKE VALVE - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-07-21 | 2022-08-03 | 57
0 | EDTDIN1210 | HD-T4 DATASHEETS FOR SOLENOID OPERATED VALVES - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-07-21 | 2022-08-03 | 57
0 | EDTDIN1385 | HD-T4 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - ICR | 10 | 2022-04-26 | 2022-05-13 | 2022-09-29 | 2022-10-12 | 106
0 | EDTDIN1405 | HD-T4 DATASHEETS FOR ELECTRONIC SOUNDER - IFA | 9 | 2022-04-27 | 2022-05-13 | 2022-11-04 | 2022-11-16 | 131
0 | EDTDIN1325 | HD-T4 DATASHEETS FOR PIG SIGNALLER - ICR | 10 | 2022-04-27 | 2022-05-16 | 2022-10-26 | 2022-11-08 | 124
0 | EDTDIN1225 | HD-T4 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-07-21 | 2022-08-03 | 54
0 | EDTDIN1110 | HD-T4 DATASHEETS FOR HIPPS VALVES - IFC | 15 | 2022-04-22 | 2022-05-18 | 2022-08-08 | 2022-08-26 | 70
0 | EDTDIN1420 | HD-T4 DATASHEETS FOR EMERGENCY S/D PB - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-11-14 | 2022-11-25 | 134
0 | EDTDIN1235 | HD-T4 DATASHEETS FOR FLOW RESTRICTION ORIFICE - ICR | 10 | 2022-05-06 | 2022-05-20 | 2022-09-15 | 2022-09-28 | 91
0 | EDTDIN1120 | HD-T4 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - IFA | 10 | 2022-05-06 | 2022-05-20 | 2022-07-14 | 2022-07-27 | 46
0 | EDTDIN1265 | HD-T4 DATASHEETS FOR CORROSION MONITOR - ICR | 10 | 2022-05-09 | 2022-05-23 | 2022-10-04 | 2022-10-17 | 103
0 | EDTDIN1435 | HD-T4 DATASHEETS FOR FLAMMABLE GAS DETECTOR - IFA | 10 | 2022-05-09 | 2022-05-23 | 2022-11-14 | 2022-11-25 | 132
0 | EDTDIN1450 | HD-T4 DATASHEETS FOR FIRE GAS DETECTOR - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-11-14 | 2022-11-25 | 130
0 | EDTDIN1255 | HD-T4 DATASHEETS FOR PRESSURE GAUGES - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-10-18 | 2022-10-31 | 111
0 | EDTDIN1300 | HD-T4 DATASHEETS FOR TEMPERATURE GAUGES - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-10-14 | 2022-10-27 | 109
0 | EDTDIN1285 | HD-T4 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - IFA | 10 | 2022-05-12 | 2022-05-26 | 2022-09-29 | 2022-10-12 | 97
0 | EDTDIN1465 | HD-T4 DATASHEETS FOR FLASHING BEACON - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-11-28 | 2022-12-13 | 138
0 | EDTDIN1495 | HD-T4 DATASHEETS FOR MAN ON BOARD PB - IFA | 9 | 2022-05-16 | 2022-05-27 | 2022-11-30 | 2022-12-14 | 139
0 | EDTDIN1315 | HD-T4 DATASHEETS FOR TEMPERATURE TRANSMITTERS - IFA | 10 | 2022-05-16 | 2022-05-30 | 2022-10-04 | 2022-10-17 | 98
0 | EDTDIN1480 | HD-T4 DATASHEETS FOR HEAT DETECTOR - IFA | 10 | 2022-05-17 | 2022-05-31 | 2022-11-28 | 2022-12-13 | 136
0 | EDTDIN1345 | HD-T4 DATASHEETS FOR LEVEL GAUGES - IFA | 10 | 2022-05-18 | 2022-06-01 | 2022-10-12 | 2022-10-25 | 102
0 | EDTDIN1525 | HD-T4 DATASHEETS FOR MANUAL ALARM CALL POINT - IFA | 10 | 2022-05-20 | 2022-06-03 | 2022-11-28 | 2022-12-13 | 133
0 | EDTDIN1360 | HD-T4 DATASHEETS FOR LEVEL TRANSMITTERS - IFA | 10 | 2022-05-20 | 2022-06-03 | 2022-10-12 | 2022-10-25 | 100
0 | EDTDIN1375 | HD-T4 DATASHEETS FOR FLOW SWITCHES - IFA | 10 | 2022-05-24 | 2022-06-07 | 2022-12-08 | 2022-12-21 | 137
0 | EDTDIN1410 | HD-T4 DATASHEETS FOR ELECTRONIC SOUNDER - IFC | 10 | 2022-05-27 | 2022-06-10 | 2022-12-05 | 2022-12-16 | 131
0 | EDTDIN1390 | HD-T4 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - IFA | 10 | 2022-05-27 | 2022-06-10 | 2022-10-27 | 2022-11-09 | 106
0 | EDTDIN1170 | HD-T4 DATASHEETS FOR MOV - IFC | 15 | 2022-05-23 | 2022-06-13 | 2022-08-04 | 2022-08-24 | 50
0 | EDTDIN1330 | HD-T4 DATASHEETS FOR PIG SIGNALLER - IFA | 10 | 2022-05-30 | 2022-06-13 | 2022-11-23 | 2022-12-08 | 124
0 | EDTDIN1155 | HD-T4 DATASHEETS FOR ACTUATED ON/OFF VALVES - IFC | 15 | 2022-05-24 | 2022-06-14 | 2022-08-04 | 2022-08-24 | 49
0 | EDTDIN1185 | HD-T4 DATASHEETS FOR PRESSURE RELIEF VALVES - IFC | 15 | 2022-05-25 | 2022-06-15 | 2022-11-09 | 2022-11-29 | 117
0 | EDTDIN1140 | HD-T4 DATASHEETS FOR CHOKE VALVES - IFC | 15 | 2022-05-26 | 2022-06-16 | 2022-08-04 | 2022-08-24 | 47
0 | EDTDIN1200 | HD-T4 DATASHEETS FOR FLOW CHOKE VALVE - IFC | 15 | 2022-05-26 | 2022-06-16 | 2022-08-18 | 2022-09-07 | 57
0 | EDTDIN1215 | HD-T4 DATASHEETS FOR SOLENOID OPERATED VALVES - IFC | 15 | 2022-05-26 | 2022-06-16 | 2022-08-18 | 2022-09-07 | 57
0 | EDTDIN1240 | HD-T4 DATASHEETS FOR FLOW RESTRICTION ORIFICE - IFA | 10 | 2022-06-03 | 2022-06-17 | 2022-10-13 | 2022-10-26 | 91
0 | EDTDIN1270 | HD-T4 DATASHEETS FOR CORROSION MONITOR - IFA | 10 | 2022-06-06 | 2022-06-20 | 2022-11-09 | 2022-11-22 | 109
0 | EDTDIN1230 | HD-T4 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - IFC | 15 | 2022-05-31 | 2022-06-21 | 2022-08-18 | 2022-09-07 | 54
0 | EDTDIN1425 | HD-T4 DATASHEETS FOR EMERGENCY S/D PB - IFC | 15 | 2022-06-02 | 2022-06-23 | 2022-12-14 | 2023-01-03 | 134
0 | EDTDIN1125 | HD-T4 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - IFC | 15 | 2022-06-03 | 2022-06-24 | 2022-08-11 | 2022-08-31 | 46
0 | EDTDIN1440 | HD-T4 DATASHEETS FOR FLAMMABLE GAS DETECTOR - IFC | 15 | 2022-06-06 | 2022-06-27 | 2022-12-14 | 2023-01-03 | 132
0 | EDTDIN1260 | HD-T4 DATASHEETS FOR PRESSURE GAUGES - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-11-15 | 2022-12-07 | 111
0 | EDTDIN1305 | HD-T4 DATASHEETS FOR TEMPERATURE GAUGES - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-11-11 | 2022-12-05 | 109
0 | EDTDIN1455 | HD-T4 DATASHEETS FOR FIRE GAS DETECTOR - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-12-14 | 2023-01-03 | 130
0 | EDTDIN1290 | HD-T4 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - IFC | 15 | 2022-06-09 | 2022-06-30 | 2022-10-27 | 2022-11-16 | 97
0 | EDTDIN1500 | HD-T4 DATASHEETS FOR MAN ON BOARD PB - IFC | 14 | 2022-06-10 | 2022-06-30 | 2022-12-29 | 2023-01-17 | 139
0 | EDTDIN1470 | HD-T4 DATASHEETS FOR FLASHING BEACON - IFC | 15 | 2022-06-10 | 2022-07-01 | 2022-12-28 | 2023-01-17 | 138
0 | EDTDIN1320 | HD-T4 DATASHEETS FOR TEMPERATURE TRANSMITTERS - IFC | 15 | 2022-06-13 | 2022-07-04 | 2022-11-01 | 2022-11-21 | 98
0 | EDTDIN1485 | HD-T4 DATASHEETS FOR HEAT DETECTOR - IFC | 15 | 2022-06-14 | 2022-07-05 | 2022-12-28 | 2023-01-17 | 136
0 | EDTDIN1350 | HD-T4 DATASHEETS FOR LEVEL GAUGES - IFC | 15 | 2022-06-16 | 2022-07-07 | 2022-11-09 | 2022-11-29 | 101
0 | EDTDIN1365 | HD-T4 DATASHEETS FOR LEVEL TRANSMITTERS - IFC | 15 | 2022-06-17 | 2022-07-13 | 2022-11-09 | 2022-11-29 | 100
0 | EDTDIN1530 | HD-T4 DATASHEETS FOR MANUAL ALARM CALL POINT- IFC | 15 | 2022-06-17 | 2022-07-13 | 2022-12-28 | 2023-01-17 | 133
0 | EDTDIN1395 | HD-T4 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - IFC | 10 | 2022-06-24 | 2022-07-13 | 2022-11-24 | 2022-12-09 | 106
0 | EDTDIN1380 | HD-T4 DATASHEETS FOR FLOW SWITCHES - IFC | 15 | 2022-06-21 | 2022-07-15 | 2023-01-05 | 2023-01-25 | 137
0 | EDTDIN1335 | HD-T4 DATASHEETS FOR PIG SIGNALLER - IFC | 15 | 2022-06-27 | 2022-07-21 | 2022-12-23 | 2023-01-12 | 124
0 | EDTDIN1245 | HD-T4 DATASHEETS FOR FLOW RESTRICTION ORIFICE - IFC | 10 | 2022-07-06 | 2022-07-25 | 2022-11-10 | 2022-11-23 | 88
0 | EDTDIN1275 | HD-T4 DATASHEETS FOR CORROSION MONITOR - IFC | 15 | 2022-07-04 | 2022-07-28 | 2022-12-09 | 2022-12-29 | 109
SCHEDULE / MTO |  |  | 120 | 2022-05-19 | 2022-11-08 | 2022-10-11 | 2023-04-27 | 119
0 | EDTDIN1600 | HD-T4 INSTRUMENT 1ST MTO | 10 | 2022-05-19 | 2022-06-02 | 2022-10-11 | 2022-10-24 | 100
0 | EDTDIN1610 | HD-T4 INSTRUMENT CABLE SCHEDULE - ICR | 10 | 2022-08-22 | 2022-09-05 | 2023-02-15 | 2023-02-28 | 125
0 | EDTDIN1625 | HD-T4 JUNCTION BOX SCHEDULE - ICR | 10 | 2022-08-22 | 2022-09-05 | 2023-02-15 | 2023-02-28 | 125
0 | EDTDIN1640 | HD-T4 TUBE SCHEDULE - ICR | 10 | 2022-08-30 | 2022-09-13 | 2023-02-15 | 2023-02-28 | 119
0 | EDTDIN1605 | HD-T4 INSTRUMENT FINAL MTO | 10 | 2022-09-05 | 2022-09-19 | 2023-01-20 | 2023-02-02 | 97
0 | EDTDIN1615 | HD-T4 INSTRUMENT CABLE SCHEDULE - IFA | 10 | 2022-09-19 | 2022-10-03 | 2023-03-15 | 2023-03-28 | 125
0 | EDTDIN1630 | HD-T4 JUNCTION BOX SCHEDULE - IFA | 10 | 2022-09-19 | 2022-10-03 | 2023-03-15 | 2023-03-28 | 125
0 | EDTDIN1645 | HD-T4 TUBE SCHEDULE - IFA | 10 | 2022-09-27 | 2022-10-11 | 2023-03-15 | 2023-03-28 | 119
0 | EDTDIN1620 | HD-T4 INSTRUMENT CABLE SCHEDULE - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-04-12 | 2023-04-27 | 125
0 | EDTDIN1635 | HD-T4 JUNCTION BOX SCHEDULE - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-04-12 | 2023-04-27 | 125
0 | EDTDIN1650 | HD-T4 TUBE SCHEDULE - IFC | 10 | 2022-10-25 | 2022-11-08 | 2023-04-12 | 2023-04-27 | 119
LIST |  |  | 95 | 2022-08-31 | 2023-01-13 | 2022-12-14 | 2023-04-27 | 73
0 | EDTDIN1700 | HD-T4 I/O LIST FOR DCS - ICR | 20 | 2022-08-31 | 2022-09-28 | 2022-12-14 | 2023-01-10 | 73
0 | EDTDIN1715 | HD-T4 I/O LIST FOR ESD SYSTEM - ICR | 20 | 2022-09-07 | 2022-10-05 | 2022-12-21 | 2023-01-17 | 73
0 | EDTDIN1730 | HD-T4 I/O LIST FOR F&G SYSTEM - ICR | 20 | 2022-09-14 | 2022-10-12 | 2022-12-28 | 2023-01-24 | 73
0 | EDTDIN1745 | HD-T4 I/O LIST FOR HIPPS - ICR | 20 | 2022-09-21 | 2022-10-19 | 2023-01-04 | 2023-01-31 | 73
0 | EDTDIN1705 | HD-T4 I/O LIST FOR DCS - IFA | 20 | 2022-10-12 | 2022-11-09 | 2023-02-15 | 2023-03-14 | 88
0 | EDTDIN1720 | HD-T4 I/O LIST FOR ESD SYSTEM - IFA | 20 | 2022-10-19 | 2022-11-16 | 2023-02-15 | 2023-03-14 | 83
0 | EDTDIN1735 | HD-T4 I/O LIST FOR F&G SYSTEM - IFA | 20 | 2022-10-26 | 2022-11-23 | 2023-02-15 | 2023-03-14 | 78
0 | EDTDIN1750 | HD-T4 I/O LIST FOR HIPPS - IFA | 20 | 2022-11-02 | 2022-11-30 | 2023-02-15 | 2023-03-14 | 73
0 | EDTDIN1710 | HD-T4 I/O LIST FOR DCS - IFC | 20 | 2022-11-23 | 2022-12-23 | 2023-03-29 | 2023-04-27 | 88
0 | EDTDIN1725 | HD-T4 I/O LIST FOR ESD SYSTEM - IFC | 20 | 2022-11-30 | 2022-12-30 | 2023-03-29 | 2023-04-27 | 83
0 | EDTDIN1740 | HD-T4 I/O LIST FOR F&G SYSTEM - IFC | 20 | 2022-12-09 | 2023-01-06 | 2023-03-29 | 2023-04-27 | 78
0 | EDTDIN1755 | HD-T4 I/O LIST FOR HIPPS - IFC | 20 | 2022-12-16 | 2023-01-13 | 2023-03-29 | 2023-04-27 | 73
DRAWINGS |  |  | 197 | 2022-04-04 | 2023-01-16 | 2022-08-30 | 2023-04-27 | 72
DIAGRAM |  |  | 197 | 2022-04-04 | 2023-01-16 | 2022-08-30 | 2023-04-27 | 72
0 | EDTGIN1000 | HD-T4 LEVEL SKETCH- ICR | 12 | 2022-04-05 | 2022-04-21 | 2022-10-28 | 2022-11-14 | 142
0 | EDTGIN1015 | HD-T4 INSTRUMENT CABLE BLOCK DIAGRAM - ICR | 15 | 2022-04-04 | 2022-04-25 | 2022-08-30 | 2022-09-19 | 100
0 | EDTGIN1030 | HD-T4 TUBING BLOCK DIAGRAM - ICR | 15 | 2022-04-25 | 2022-05-19 | 2022-09-27 | 2022-10-17 | 105
0 | EDTGIN1005 | HD-T4 LEVEL SKETCH- IFA | 12 | 2022-05-10 | 2022-05-26 | 2022-11-29 | 2022-12-16 | 142
0 | EDTGIN1020 | HD-T4 INSTRUMENT CABLE BLOCK DIAGRAM - IFA | 15 | 2022-05-12 | 2022-06-02 | 2022-11-01 | 2022-11-21 | 120
0 | EDTGIN1035 | HD-T4 TUBING BLOCK DIAGRAM - IFA | 15 | 2022-06-02 | 2022-06-23 | 2022-11-01 | 2022-11-21 | 105
0 | EDTGIN1010 | HD-T4 LEVEL SKETCH- IFC | 12 | 2022-06-09 | 2022-06-27 | 2023-01-02 | 2023-01-17 | 142
0 | EDTGIN1025 | HD-T4 INSTRUMENT CABLE BLOCK DIAGRAM - IFC | 20 | 2022-06-16 | 2022-07-19 | 2022-12-08 | 2023-01-04 | 120
0 | EDTGIN1040 | HD-T4 TUBING BLOCK DIAGRAM - IFC | 20 | 2022-07-07 | 2022-08-09 | 2022-12-08 | 2023-01-04 | 105
0 | EDTGIN1045 | HD-T4 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - ICR | 15 | 2022-08-09 | 2022-08-30 | 2023-01-05 | 2023-01-25 | 105
0 | EDTGIN1060 | HD-T4 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - ICR | 15 | 2022-08-15 | 2022-09-05 | 2023-01-11 | 2023-01-31 | 105
0 | EDTGIN1075 | HD-T4 PROCESS & HYDRAULIC HOOK-UPS DRAWING - ICR | 15 | 2022-08-22 | 2022-09-12 | 2023-01-18 | 2023-02-07 | 105
0 | EDTGIN1050 | HD-T4 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - IFA | 15 | 2022-09-13 | 2022-10-04 | 2023-02-22 | 2023-03-14 | 114
0 | EDTGIN1065 | HD-T4 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - IFA | 15 | 2022-09-19 | 2022-10-10 | 2023-02-22 | 2023-03-14 | 110
0 | EDTGIN1080 | HD-T4 PROCESS & HYDRAULIC HOOK-UPS DRAWING - IFA | 15 | 2022-09-26 | 2022-10-17 | 2023-02-22 | 2023-03-14 | 105
0 | EDTGIN1090 | HD-T4 INSTRUMENT LOOP DIAGRAMS - DCS - ICR | 10 | 2022-10-07 | 2022-10-21 | 2023-01-27 | 2023-02-09 | 78
0 | EDTGIN1105 | HD-T4 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - ICR | 10 | 2022-10-11 | 2022-10-25 | 2023-01-31 | 2023-02-13 | 78
0 | EDTGIN1120 | HD-T4 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - ICR | 10 | 2022-10-21 | 2022-11-04 | 2023-02-02 | 2023-02-15 | 72
0 | EDTGIN1135 | HD-T4 INSTRUMENT LOOP DIAGRAMS - HIPPS - ICR | 10 | 2022-10-27 | 2022-11-10 | 2023-02-08 | 2023-02-21 | 72
0 | EDTGIN1055 | HD-T4 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - IFC | 20 | 2022-10-18 | 2022-11-15 | 2023-03-29 | 2023-04-27 | 114
0 | EDTGIN1095 | HD-T4 INSTRUMENT LOOP DIAGRAMS - DCS - IFA | 10 | 2022-11-04 | 2022-11-18 | 2023-03-08 | 2023-03-21 | 86
0 | EDTGIN1070 | HD-T4 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - IFC | 20 | 2022-10-24 | 2022-11-21 | 2023-03-29 | 2023-04-27 | 110
0 | EDTGIN1110 | HD-T4 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - IFA | 10 | 2022-11-08 | 2022-11-22 | 2023-03-08 | 2023-03-21 | 84
0 | EDTGIN1085 | HD-T4 PROCESS & HYDRAULIC HOOK-UPS DRAWING - IFC | 20 | 2022-10-31 | 2022-11-28 | 2023-03-29 | 2023-04-27 | 105
0 | EDTGIN1125 | HD-T4 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - IFA | 10 | 2022-11-18 | 2022-12-06 | 2023-03-08 | 2023-03-21 | 76
0 | EDTGIN1140 | HD-T4 INSTRUMENT LOOP DIAGRAMS - HIPPS - IFA | 10 | 2022-11-24 | 2022-12-12 | 2023-03-08 | 2023-03-21 | 72
0 | EDTGIN1100 | HD-T4 INSTRUMENT LOOP DIAGRAMS - DCS - IFC | 15 | 2022-12-06 | 2022-12-27 | 2023-04-05 | 2023-04-27 | 86
0 | EDTGIN1115 | HD-T4 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - IFC | 15 | 2022-12-08 | 2022-12-29 | 2023-04-05 | 2023-04-27 | 84
0 | EDTGIN1130 | HD-T4 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - IFC | 15 | 2022-12-20 | 2023-01-10 | 2023-04-05 | 2023-04-27 | 76
0 | EDTGIN1145 | HD-T4 INSTRUMENT LOOP DIAGRAMS - HIPPS - IFC | 15 | 2022-12-26 | 2023-01-16 | 2023-04-05 | 2023-04-27 | 72
LAYOUT |  |  | 93 | 2022-06-30 | 2022-11-11 | 2022-10-20 | 2023-04-27 | 116
0 | EDTGIN1215 | HD-T4 INSTRUMENT CABLE ROUTING LAYOUT - ICR | 15 | 2022-06-30 | 2022-07-26 | 2023-01-05 | 2023-01-25 | 130
0 | EDTGIN1230 | HD-T4 INSTRUMENT LOCATION LAYOUTS - ICR | 15 | 2022-07-07 | 2022-08-02 | 2023-01-12 | 2023-02-01 | 130
0 | EDTGIN1245 | HD-T4 TUBE ROUTING LAYOUT - ICR | 15 | 2022-07-18 | 2022-08-08 | 2023-01-18 | 2023-02-07 | 130
0 | EDTGIN1220 | HD-T4 INSTRUMENT CABLE ROUTING LAYOUT - IFA | 10 | 2022-08-09 | 2022-08-23 | 2023-02-24 | 2023-03-09 | 141
0 | EDTGIN1200 | HD-T4 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - ICR | 15 | 2022-08-10 | 2022-08-31 | 2022-10-20 | 2022-11-09 | 51
0 | EDTGIN1235 | HD-T4 INSTRUMENT LOCATION LAYOUTS - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-02-22 | 2023-03-14 | 134
0 | EDTGIN1265 | HD-T4 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - ICR | 15 | 2022-08-19 | 2022-09-09 | 2022-10-31 | 2022-11-18 | 51
0 | EDTGIN1250 | HD-T4 TUBE ROUTING LAYOUT - IFA | 15 | 2022-08-22 | 2022-09-12 | 2023-02-22 | 2023-03-14 | 130
0 | EDTGIN1225 | HD-T4 INSTRUMENT CABLE ROUTING LAYOUT - IFC | 20 | 2022-09-06 | 2022-10-04 | 2023-03-24 | 2023-04-20 | 141
0 | EDTGIN1205 | HD-T4 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - IFA | 15 | 2022-09-14 | 2022-10-05 | 2022-11-28 | 2022-12-20 | 53
0 | EDTGIN1275 | HD-T4 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - IFA | 15 | 2022-09-23 | 2022-10-14 | 2022-12-07 | 2022-12-27 | 51
0 | EDTGIN1240 | HD-T4 INSTRUMENT LOCATION LAYOUTS - IFC | 20 | 2022-09-20 | 2022-10-18 | 2023-03-29 | 2023-04-27 | 134
0 | EDTGIN1255 | HD-T4 TUBE ROUTING LAYOUT - IFC | 20 | 2022-09-26 | 2022-10-24 | 2023-03-29 | 2023-04-27 | 130
0 | EDTGIN1210 | HD-T4 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - IFC | 15 | 2022-10-19 | 2022-11-09 | 2023-01-04 | 2023-01-24 | 53
0 | EDTGIN1285 | HD-T4 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - IFC | 10 | 2022-10-28 | 2022-11-11 | 2023-01-11 | 2023-01-24 | 51
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-29 | 2023-01-16 | 2023-01-11 | 2023-04-27 | 72
0 | EDTGIN2000 | HD-T4 INSTRUMENT MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-29 | 2022-10-27 | 2023-01-11 | 2023-02-07 | 72
0 | EDTGIN2005 | HD-T4 INSTRUMENT MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-10 | 2022-12-12 | 2023-02-22 | 2023-03-21 | 72
0 | EDTGIN2010 | HD-T4 INSTRUMENT MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-26 | 2023-01-16 | 2023-04-05 | 2023-04-27 | 72
TELECOM |  |  | 152 | 2022-06-02 | 2023-01-09 | 2022-09-27 | 2023-04-27 | 77
DOCUMENTS |  |  | 104 | 2022-06-02 | 2022-10-31 | 2022-09-27 | 2023-04-27 | 125
LIST/SCHEDULE |  |  | 104 | 2022-06-02 | 2022-10-31 | 2022-09-27 | 2023-04-27 | 125
0 | EDTDTE1000 | HD-T4 TELECOMMUNICATION - 1ST MTO | 10 | 2022-06-02 | 2022-06-16 | 2022-09-27 | 2022-10-10 | 80
0 | EDTDTE1010 | HD-T4 TELECOM EQUIPMENT LIST - ICR | 10 | 2022-06-16 | 2022-06-30 | 2022-10-11 | 2022-10-24 | 80
0 | EDTDTE1015 | HD-T4 TELECOM EQUIPMENT LIST - IFA | 10 | 2022-07-19 | 2022-08-02 | 2023-02-15 | 2023-02-28 | 149
0 | EDTDTE1025 | HD-T4 TELECOM CABLE SCHEDULE - ICR | 10 | 2022-08-22 | 2022-09-05 | 2023-02-01 | 2023-02-14 | 115
0 | EDTDTE1020 | HD-T4 TELECOM EQUIPMENT LIST - IFC | 20 | 2022-08-16 | 2022-09-13 | 2023-03-15 | 2023-04-11 | 149
0 | EDTDTE1005 | HD-T4 TELECOMMUNICATION - FINAL MTO | 10 | 2022-09-05 | 2022-09-19 | 2023-01-20 | 2023-02-02 | 97
0 | EDTDTE1030 | HD-T4 TELECOM CABLE SCHEDULE - IFA | 10 | 2022-09-19 | 2022-10-03 | 2023-03-15 | 2023-03-28 | 125
0 | EDTDTE1035 | HD-T4 TELECOM CABLE SCHEDULE - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-04-12 | 2023-04-27 | 125
DRAWINGS |  |  | 94 | 2022-07-19 | 2022-11-28 | 2022-11-08 | 2023-04-27 | 105
LAYOUT |  |  | 94 | 2022-07-19 | 2022-11-28 | 2022-11-08 | 2023-04-27 | 105
0 | EDTGTE1015 | HD-T4 TELECOM EQUIPMENT LOCATION LAYOUTS - ICR | 10 | 2022-07-19 | 2022-08-02 | 2022-11-08 | 2022-11-21 | 80
0 | EDTGTE1020 | HD-T4 TELECOM EQUIPMENT LOCATION LAYOUTS - IFA | 10 | 2022-08-16 | 2022-08-30 | 2022-12-08 | 2022-12-21 | 80
0 | EDTGTE1000 | HD-T4 TELECOM CABLE ROUTING LAYOUT - ICR | 10 | 2022-08-22 | 2022-09-05 | 2023-01-18 | 2023-01-31 | 105
0 | EDTGTE1045 | HD-T4 DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - ICR | 10 | 2022-09-05 | 2022-09-19 | 2023-02-01 | 2023-02-14 | 105
0 | EDTGTE1030 | HD-T4 FIBER OPTIC ALLOCATION DRAWING - ICR | 10 | 2022-09-05 | 2022-09-19 | 2023-02-15 | 2023-02-28 | 115
0 | EDTGTE1025 | HD-T4 TELECOM EQUIPMENT LOCATION LAYOUTS - IFC | 10 | 2022-09-13 | 2022-09-27 | 2023-01-05 | 2023-01-18 | 80
0 | EDTGTE1005 | HD-T4 TELECOM CABLE ROUTING LAYOUT - IFA | 10 | 2022-09-19 | 2022-10-03 | 2023-03-15 | 2023-03-28 | 125
0 | EDTGTE1035 | HD-T4 FIBER OPTIC ALLOCATION DRAWING - IFA | 10 | 2022-10-03 | 2022-10-17 | 2023-03-15 | 2023-03-28 | 115
0 | EDTGTE1050 | HD-T4 DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - IFA | 10 | 2022-10-03 | 2022-10-17 | 2023-03-01 | 2023-03-14 | 105
0 | EDTGTE1010 | HD-T4 TELECOM CABLE ROUTING LAYOUT - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-04-12 | 2023-04-27 | 125
0 | EDTGTE1040 | HD-T4 FIBER OPTIC ALLOCATION DRAWING - IFC | 10 | 2022-10-31 | 2022-11-14 | 2023-04-12 | 2023-04-27 | 115
0 | EDTGTE1055 | HD-T4 DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - IFC | 20 | 2022-10-31 | 2022-11-28 | 2023-03-29 | 2023-04-27 | 105
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDTGTE2000 | HD-T4 TELECOM MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDTGTE2005 | HD-T4 TELECOM MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDTGTE2010 | HD-T4 TELECOM MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
STRUCTURAL |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-06-22 | 2023-08-14 | 142
3D MODEL DEVELOPMENT |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-06-22 | 2023-04-27 | 69
0 | EDTDSR3000 | HD-T4 3D MODEL DEVELOPMENT - STRUCTURAL | 215 | 2022-03-14 | 2023-01-19 | 2022-06-22 | 2023-04-27 | 69
DOCUMENTS |  |  | 150 | 2022-05-12 | 2022-12-15 | 2022-09-12 | 2023-08-04 | 161
REPORTS |  |  | 150 | 2022-05-12 | 2022-12-15 | 2022-09-12 | 2023-08-04 | 161
0 | EDTDSR1000 | HD-T4 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - ICR | 20 | 2022-05-12 | 2022-06-09 | 2022-09-12 | 2022-10-07 | 84
0 | EDTDSR1195 | HD-T4 TOPSIDES LINEAR BLAST ANALYSIS REPORT - ICR | 20 | 2022-05-12 | 2022-06-09 | 2022-09-12 | 2022-10-07 | 84
0 | EDTDSR1135 | HD-T4 TOPSIDES LIFT ANALYSES REPORT - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-09-26 | 2022-10-21 | 89
0 | EDTDSR1075 | HD-T4 TOPSIDE JOINT DESIGN REPORT - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-09-19 | 2022-10-14 | 84
0 | EDTDSR1090 | HD-T4 HELIDECK DESIGN REPORT - ICR | 20 | 2022-05-26 | 2022-06-23 | 2022-11-07 | 2022-12-06 | 114
0 | EDTDSR1150 | HD-T4 TOPSIDES LOADOUT ANALYSIS REPORT - ICR | 20 | 2022-05-26 | 2022-06-23 | 2022-12-14 | 2023-01-10 | 139
0 | EDTDSR1165 | HD-T4 TOPSIDES TRANSPORTATION ANALYSES REPORT - ICR | 20 | 2022-06-02 | 2022-06-30 | 2022-12-21 | 2023-01-17 | 139
0 | EDTDSR1105 | HD-T4 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - ICR | 20 | 2022-06-09 | 2022-07-07 | 2022-10-24 | 2022-11-18 | 94
0 | EDTDSR1005 | HD-T4 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - IFA | 15 | 2022-06-23 | 2022-07-19 | 2022-11-07 | 2022-11-25 | 94
0 | EDTDSR1200 | HD-T4 TOPSIDES LINEAR BLAST ANALYSIS REPORT - IFA | 15 | 2022-06-23 | 2022-07-19 | 2023-03-01 | 2023-03-21 | 174
0 | EDTDSR1140 | HD-T4 TOPSIDES LIFT ANALYSES REPORT - IFA | 15 | 2022-06-30 | 2022-07-26 | 2023-02-28 | 2023-03-20 | 168
0 | EDTDSR1080 | HD-T4 TOPSIDE JOINT DESIGN REPORT - IFA | 15 | 2022-06-30 | 2022-07-26 | 2022-12-19 | 2023-01-06 | 117
0 | EDTDSR1180 | HD-T4 TOPSIDE MISCELLANEOUS DESIGN REPORT - ICR | 20 | 2022-06-30 | 2022-08-02 | 2023-01-18 | 2023-02-14 | 139
0 | EDTDSR1095 | HD-T4 HELIDECK DESIGN REPORT - IFA | 15 | 2022-07-07 | 2022-08-02 | 2022-12-28 | 2023-01-17 | 119
0 | EDTDSR1155 | HD-T4 TOPSIDES LOADOUT ANALYSIS REPORT - IFA | 15 | 2022-07-07 | 2022-08-02 | 2023-06-06 | 2023-06-26 | 231
0 | EDTDSR1015 | HD-T4 JACKET INPLACE ANALYSIS REPORT - ICR | 20 | 2022-07-07 | 2022-08-09 | 2022-11-21 | 2022-12-20 | 94
0 | EDTDSR1170 | HD-T4 TOPSIDES TRANSPORTATION ANALYSES REPORT - IFA | 15 | 2022-07-19 | 2022-08-09 | 2023-03-01 | 2023-03-21 | 159
0 | EDTDSR1110 | HD-T4 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - IFA | 15 | 2022-07-26 | 2022-08-16 | 2023-03-01 | 2023-03-21 | 154
0 | EDTDSR1010 | HD-T4 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - IFC | 15 | 2022-08-02 | 2022-08-23 | 2023-01-02 | 2023-01-20 | 107
0 | EDTDSR1205 | HD-T4 TOPSIDES LINEAR BLAST ANALYSIS REPORT - IFC | 15 | 2022-08-02 | 2022-08-23 | 2023-04-05 | 2023-04-27 | 174
0 | EDTDSR1030 | HD-T4 JACKET PUSHOVER ANALYSIS REPORT - ICR | 20 | 2022-07-26 | 2022-08-23 | 2022-12-07 | 2023-01-03 | 94
0 | EDTDSR1085 | HD-T4 TOPSIDE JOINT DESIGN REPORT - IFC | 15 | 2022-08-09 | 2022-08-30 | 2023-01-23 | 2023-02-10 | 117
0 | EDTDSR1145 | HD-T4 TOPSIDES LIFT ANALYSES REPORT - IFC | 15 | 2022-08-16 | 2022-09-06 | 2023-04-04 | 2023-04-26 | 163
0 | EDTDSR1100 | HD-T4 HELIDECK DESIGN REPORT - IFC | 15 | 2022-08-16 | 2022-09-06 | 2023-02-01 | 2023-02-21 | 119
0 | EDTDSR1160 | HD-T4 TOPSIDES LOADOUT ANALYSIS REPORT - IFC | 15 | 2022-08-16 | 2022-09-06 | 2023-07-14 | 2023-08-04 | 231
0 | EDTDSR1045 | HD-T4 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - ICR | 20 | 2022-08-09 | 2022-09-06 | 2022-12-21 | 2023-01-17 | 94
0 | EDTDSR1185 | HD-T4 TOPSIDE MISCELLANEOUS DESIGN REPORT - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-03-01 | 2023-03-21 | 139
0 | EDTDSR1175 | HD-T4 TOPSIDES TRANSPORTATION ANALYSES REPORT - IFC | 15 | 2022-08-23 | 2022-09-13 | 2023-04-05 | 2023-04-27 | 159
0 | EDTDSR1020 | HD-T4 JACKET INPLACE ANALYSIS REPORT - IFA | 15 | 2022-08-23 | 2022-09-13 | 2023-01-25 | 2023-02-14 | 109
0 | EDTDSR1060 | HD-T4 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - ICR | 20 | 2022-08-23 | 2022-09-20 | 2023-01-04 | 2023-01-31 | 94
0 | EDTDSR1115 | HD-T4 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - IFC | 15 | 2022-08-30 | 2022-09-20 | 2023-04-05 | 2023-04-27 | 154
0 | EDTDSR1035 | HD-T4 JACKET PUSHOVER ANALYSIS REPORT - IFA | 15 | 2022-09-06 | 2022-09-27 | 2023-02-15 | 2023-03-07 | 114
0 | EDTDSR1120 | HD-T4 JACKET MISCELLANEOUS DESIGN REPORT - ICR | 20 | 2022-09-06 | 2022-10-04 | 2023-01-18 | 2023-02-14 | 94
0 | EDTDSR1190 | HD-T4 TOPSIDE MISCELLANEOUS DESIGN REPORT - IFC | 15 | 2022-09-20 | 2022-10-11 | 2023-04-05 | 2023-04-27 | 139
0 | EDTDSR1050 | HD-T4 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - IFA | 15 | 2022-09-20 | 2022-10-11 | 2023-02-22 | 2023-03-14 | 109
0 | EDTDSR1025 | HD-T4 JACKET INPLACE ANALYSIS REPORT - IFC | 15 | 2022-09-27 | 2022-10-18 | 2023-03-08 | 2023-03-28 | 114
0 | EDTDSR1065 | HD-T4 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - IFA | 15 | 2022-10-04 | 2022-10-25 | 2023-03-01 | 2023-03-21 | 104
0 | EDTDSR1040 | HD-T4 JACKET PUSHOVER ANALYSIS REPORT - IFC | 15 | 2022-10-11 | 2022-11-01 | 2023-03-22 | 2023-04-11 | 114
0 | EDTDSR1125 | HD-T4 JACKET MISCELLANEOUS DESIGN REPORT - IFA | 15 | 2022-10-18 | 2022-11-08 | 2023-03-01 | 2023-03-21 | 94
0 | EDTDSR1055 | HD-T4 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - IFC | 15 | 2022-10-25 | 2022-11-15 | 2023-03-29 | 2023-04-18 | 109
0 | EDTDSR1070 | HD-T4 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - IFC | 15 | 2022-11-08 | 2022-11-29 | 2023-04-05 | 2023-04-27 | 104
0 | EDTDSR1130 | HD-T4 JACKET MISCELLANEOUS DESIGN REPORT - IFC | 15 | 2022-11-22 | 2022-12-15 | 2023-04-05 | 2023-04-27 | 94
DRAWINGS |  |  | 174 | 2022-04-26 | 2023-01-05 | 2022-08-25 | 2023-08-14 | 152
GENERAL |  |  | 165 | 2022-04-26 | 2022-12-23 | 2022-08-25 | 2023-04-27 | 88
0 | EDTGSR1000 | HD-T4 DRAWING INDEX - ICR | 15 | 2022-04-26 | 2022-05-20 | 2022-08-25 | 2022-09-14 | 81
0 | EDTGSR1002 | HD-T4 DRAWING INDEX - IFA | 15 | 2022-06-14 | 2022-07-05 | 2022-09-29 | 2022-10-19 | 73
0 | EDTGSR1005 | HD-T4 DRAWING INDEX - IFC | 15 | 2022-11-30 | 2022-12-23 | 2023-04-05 | 2023-04-27 | 88
PRIMARY |  |  | 126 | 2022-05-19 | 2022-11-16 | 2022-09-19 | 2023-04-27 | 113
0 | EDTGSR1025 | HD-T4 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-09-19 | 2022-10-14 | 84
0 | EDTGSR1010 | HD-T4 MAIN DECK PRIMARY FRAMING PLAN EL(+) 15.000 - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-09-19 | 2022-10-14 | 84
0 | EDTGSR1040 | HD-T4 DECK ELEVATION ROW-1 & 2 - ICR | 20 | 2022-05-26 | 2022-06-23 | 2022-09-26 | 2022-10-21 | 84
0 | EDTGSR1055 | HD-T4 DECK ELEVATION ROW-A & B - ICR | 20 | 2022-05-26 | 2022-06-23 | 2022-10-24 | 2022-11-18 | 104
0 | EDTGSR1085 | HD-T4 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 9.000- ICR | 20 | 2022-06-02 | 2022-06-30 | 2022-10-31 | 2022-11-25 | 104
0 | EDTGSR1100 | HD-T4 ACCESS PLATFORM FRAMING PLAN EL(+) 18.000 - ICR | 20 | 2022-06-02 | 2022-06-30 | 2022-11-07 | 2022-12-06 | 109
0 | EDTGSR1070 | HD-T4 DECK SECTIONS - ICR | 20 | 2022-06-02 | 2022-06-30 | 2022-10-31 | 2022-11-25 | 104
0 | EDTGSR1115 | HD-T4 MEZZANINE DECK FRAMING PLAN EL(+) 21.000 - ICR | 20 | 2022-06-09 | 2022-07-07 | 2022-11-14 | 2022-12-13 | 109
0 | EDTGSR1130 | HD-T4 WEATHER DECK FRAMING PLAN EL(+) 25.500 - ICR | 20 | 2022-06-16 | 2022-07-19 | 2022-11-21 | 2022-12-20 | 109
0 | EDTGSR1145 | HD-T4 - HELIDECK FRAMING PLAN AT EL. (+) 32.300 - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-12-07 | 2023-01-03 | 114
0 | EDTGSR1160 | HD-T4 DECK LEG STABBING GUIDE DETAILS - ICR | 20 | 2022-06-23 | 2022-07-26 | 2023-01-18 | 2023-02-14 | 144
0 | EDTGSR1030 | HD-T4 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - IFA | 15 | 2022-06-30 | 2022-07-26 | 2022-12-26 | 2023-01-13 | 122
0 | EDTGSR1015 | HD-T4 MAIN DECK PRIMARY FRAMING PLAN EL(+) 15.000- IFA. | 15 | 2022-06-30 | 2022-07-26 | 2022-12-08 | 2022-12-28 | 110
0 | EDTGSR1045 | HD-T4 DECK ELEVATION ROW-1 & 2 - IFA | 15 | 2022-07-07 | 2022-08-02 | 2023-01-12 | 2023-02-01 | 130
0 | EDTGSR1060 | HD-T4 DECK ELEVATION ROW-A & B - IFA | 15 | 2022-07-07 | 2022-08-02 | 2023-01-12 | 2023-02-01 | 130
0 | EDTGSR1090 | HD-T4 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 9.000 - IFA | 15 | 2022-07-19 | 2022-08-09 | 2022-12-23 | 2023-01-12 | 111
0 | EDTGSR1105 | HD-T4 ACCESS PLATFORM FRAMING PLAN EL(+) 18.000 - IFA | 15 | 2022-07-19 | 2022-08-09 | 2023-01-26 | 2023-02-15 | 135
0 | EDTGSR1075 | HD-T4 DECK SECTIONS - IFA | 15 | 2022-07-19 | 2022-08-09 | 2023-01-12 | 2023-02-01 | 125
0 | EDTGSR1120 | HD-T4 MEZZANINE DECK FRAMING PLAN EL(+) 21.000 - IFA | 15 | 2022-07-26 | 2022-08-16 | 2022-12-30 | 2023-01-19 | 111
0 | EDTGSR1135 | HD-T4 WEATHER DECK FRAMING PLAN EL(+) 25.500 - IFA | 15 | 2022-08-02 | 2022-08-23 | 2023-01-09 | 2023-01-27 | 112
0 | EDTGSR1150 | HD-T4 - HELIDECK FRAMING PLAN AT EL. (+) 32.300 - IFA | 15 | 2022-08-09 | 2022-08-30 | 2023-01-18 | 2023-02-07 | 114
0 | EDTGSR1165 | HD-T4 DECK LEG STABBING GUIDE DETAILS - IFA | 15 | 2022-08-09 | 2022-08-30 | 2023-03-01 | 2023-03-21 | 144
0 | EDTGSR1035 | HD-T4 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - IFC | 15 | 2022-08-16 | 2022-09-06 | 2023-01-30 | 2023-02-17 | 117
0 | EDTGSR1050 | HD-T4 DECK ELEVATION ROW-1 & 2 - IFC | 15 | 2022-08-16 | 2022-09-06 | 2023-02-16 | 2023-03-08 | 130
0 | EDTGSR1065 | HD-T4 DECK ELEVATION ROW-A & B - IFC | 15 | 2022-08-16 | 2022-09-06 | 2023-02-16 | 2023-03-08 | 130
0 | EDTGSR1095 | HD-T4 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 9.000 - IFC | 15 | 2022-08-23 | 2022-09-13 | 2023-01-27 | 2023-02-16 | 111
0 | EDTGSR1110 | HD-T4 ACCESS PLATFORM FRAMING PLAN EL(+) 18.000 - IFC | 15 | 2022-08-23 | 2022-09-13 | 2023-03-02 | 2023-03-22 | 135
0 | EDTGSR1080 | HD-T4 DECK SECTIONS - IFC | 15 | 2022-08-23 | 2022-09-13 | 2023-02-16 | 2023-03-08 | 125
0 | EDTGSR1020 | HD-T4 MAIN DECK PRIMARY FRAMING PLAN EL(+) 15.000 - IFC | 15 | 2022-08-23 | 2022-09-13 | 2023-01-23 | 2023-02-10 | 107
0 | EDTGSR1125 | HD-T4 MEZZANINE DECK FRAMING PLAN EL(+) 21.000 - IFC | 15 | 2022-08-30 | 2022-09-20 | 2023-02-03 | 2023-02-23 | 111
0 | EDTGSR1140 | HD-T4 WEATHER DECK FRAMING PLAN EL(+) 25.500 - IFC | 15 | 2022-09-06 | 2022-09-27 | 2023-02-13 | 2023-03-03 | 112
0 | EDTGSR1170 | HD-T4 DECK LEG STABBING GUIDE DETAILS - IFC | 15 | 2022-09-13 | 2022-10-04 | 2023-04-05 | 2023-04-27 | 144
0 | EDTGSR1155 | HD-T4 - HELIDECK FRAMING PLAN AT EL. (+) 32.300 - IFC | 15 | 2022-10-26 | 2022-11-16 | 2023-02-22 | 2023-03-14 | 83
SECONDARY |  |  | 131 | 2022-06-02 | 2022-12-09 | 2022-10-03 | 2023-05-11 | 108
0 | EDTGSR1175 | HD-T4 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - ICR | 20 | 2022-06-02 | 2022-06-30 | 2022-10-03 | 2022-10-28 | 84
0 | EDTGSR1235 | HD-T4 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - ICR | 20 | 2022-06-09 | 2022-07-07 | 2022-10-10 | 2022-11-04 | 84
0 | EDTGSR1190 | HD-T4 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - ICR | 20 | 2022-06-16 | 2022-07-19 | 2022-11-14 | 2022-12-13 | 104
0 | EDTGSR1250 | HD-T4 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-11-21 | 2022-12-20 | 104
0 | EDTGSR1205 | HD-T4 MEZZANINE DECK SECONDARY FRAMING PLAN EL(+) 21.000 - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-11-28 | 2022-12-27 | 109
0 | EDTGSR1265 | HD-T4 ACCESSPLATFORM PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 18.000 - ICR | 20 | 2022-06-30 | 2022-08-02 | 2022-11-28 | 2022-12-27 | 104
0 | EDTGSR1220 | HD-T4 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - ICR | 20 | 2022-06-30 | 2022-08-02 | 2022-12-07 | 2023-01-03 | 109
0 | EDTGSR2020 | HD-T4 CELLAR DECK INFILL BEAM FRAMING PLAN AT EL (+) 9.000 T.O.S - ICR | 10 | 2022-07-19 | 2022-08-02 | 2023-01-16 | 2023-01-27 | 127
0 | EDTGSR1280 | HD-T4 MEZZANINE DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - ICR | 20 | 2022-07-07 | 2022-08-09 | 2022-12-07 | 2023-01-03 | 104
0 | EDTGSR1180 | HD-T4 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - IFA | 15 | 2022-07-19 | 2022-08-09 | 2023-02-02 | 2023-02-22 | 140
0 | EDTGSR2050 | HD-T4 MAIN DECK INFILL BEAM FRAMING PLAN AT EL (+) 15.000 T.O.S - ICR | 10 | 2022-07-26 | 2022-08-09 | 2023-01-23 | 2023-02-03 | 127
0 | EDTGSR1295 | HD-T4 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - ICR | 20 | 2022-07-19 | 2022-08-16 | 2022-12-14 | 2023-01-10 | 104
0 | EDTGSR1240 | HD-T4 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - IFA | 15 | 2022-07-26 | 2022-08-16 | 2023-02-09 | 2023-03-01 | 140
0 | EDTGSR2080 | HD-T4 MEZZANINE DECK INFILL BEAM FRAMING PLAN (+) 21.000 T.O.S - ICR | 10 | 2022-08-02 | 2022-08-16 | 2023-02-03 | 2023-02-16 | 131
0 | EDTGSR1310 | HD-T4 HELIDECK PLATING DETAILS - ICR | 20 | 2022-07-26 | 2022-08-23 | 2022-12-21 | 2023-01-17 | 104
0 | EDTGSR1195 | HD-T4 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - IFA | 15 | 2022-08-02 | 2022-08-23 | 2023-02-06 | 2023-02-24 | 132
0 | EDTGSR2110 | HD-T4 WEATHER DECK INFILL BEAM FRAMING PLAN EL (+) 25.000 T.O.S - ICR | 10 | 2022-08-09 | 2022-08-23 | 2023-03-01 | 2023-03-14 | 144
0 | EDTGSR1255 | HD-T4 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - IFA | 15 | 2022-08-09 | 2022-08-30 | 2023-02-20 | 2023-03-10 | 137
0 | EDTGSR1325 | HD-T4 HELIDECK SAFETY NET LAYOUT & DETAILS - ICR | 20 | 2022-08-02 | 2022-08-30 | 2022-12-28 | 2023-01-24 | 104
0 | EDTGSR1210 | HD-T4 MEZZANINE DECK SECONDARY FRAMING PLAN EL(+) 21.000 - IFA | 15 | 2022-08-09 | 2022-08-30 | 2023-02-08 | 2023-02-28 | 129
0 | EDTGSR2030 | HD-T4 CELLAR DECK INFILL BEAM FRAMING PLAN AT EL (+) 9.000 T.O.S - IFA | 10 | 2022-08-16 | 2022-08-30 | 2023-02-27 | 2023-03-10 | 137
0 | EDTGSR1270 | HD-T4 ACCESSPLATFORM PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 18.000 - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-02-16 | 2023-03-08 | 130
0 | EDTGSR1225 | HD-T4 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-03-01 | 2023-03-21 | 139
0 | EDTGSR2060 | HD-T4 MAIN DECK INFILL BEAM FRAMING PLAN AT EL (+) 15.000 T.O.S - IFA | 10 | 2022-08-23 | 2022-09-06 | 2023-02-20 | 2023-03-03 | 127
0 | EDTGSR1285 | HD-T4 MEZZANINE DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - IFA | 15 | 2022-08-23 | 2022-09-13 | 2023-02-08 | 2023-02-28 | 119
0 | EDTGSR2090 | HD-T4 MEZZANINE DECK INFILL BEAM FRAMING PLAN (+) 21.000 T.O.S - IFA | 10 | 2022-08-30 | 2022-09-13 | 2023-03-03 | 2023-03-16 | 131
0 | EDTGSR1300 | HD-T4 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - IFA | 15 | 2022-08-30 | 2022-09-20 | 2023-03-01 | 2023-03-21 | 129
0 | EDTGSR1200 | HD-T4 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - IFC | 10 | 2022-09-06 | 2022-09-20 | 2023-03-13 | 2023-03-24 | 132
0 | EDTGSR2120 | HD-T4 WEATHER DECK INFILL BEAM FRAMING PLAN EL (+) 25.000 T.O.S - IFA | 10 | 2022-09-06 | 2022-09-20 | 2023-03-29 | 2023-04-11 | 144
0 | EDTGSR1315 | HD-T4 HELIDECK PLATING DETAILS - IFA | 15 | 2022-09-06 | 2022-09-27 | 2023-03-01 | 2023-03-21 | 124
0 | EDTGSR1185 | HD-T4 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - IFC | 10 | 2022-09-13 | 2022-09-27 | 2023-03-09 | 2023-03-22 | 125
0 | EDTGSR2040 | HD-T4 CELLAR DECK INFILL BEAM FRAMING PLAN AT EL (+) 9.000 T.O.S - IFC | 10 | 2022-09-13 | 2022-09-27 | 2023-03-27 | 2023-04-07 | 137
0 | EDTGSR1260 | HD-T4 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - IFC | 15 | 2022-09-13 | 2022-10-04 | 2023-03-27 | 2023-04-14 | 137
0 | EDTGSR1245 | HD-T4 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - IFC | 15 | 2022-09-13 | 2022-10-04 | 2023-03-16 | 2023-04-05 | 130
0 | EDTGSR1330 | HD-T4 HELIDECK SAFETY NET LAYOUT & DETAILS - IFA | 15 | 2022-09-13 | 2022-10-04 | 2023-02-08 | 2023-02-28 | 104
0 | EDTGSR1215 | HD-T4 MEZZANINE DECK SECONDARY FRAMING PLAN EL(+) 21.000 - IFC | 15 | 2022-09-13 | 2022-10-04 | 2023-03-15 | 2023-04-04 | 129
0 | EDTGSR2070 | HD-T4 MAIN DECK INFILL BEAM FRAMING PLAN AT EL (+) 15.000 T.O.S - IFC | 10 | 2022-09-20 | 2022-10-04 | 2023-03-20 | 2023-03-31 | 127
0 | EDTGSR1275 | HD-T4 ACCESSPLATFORM PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 18.000 - IFC | 15 | 2022-09-20 | 2022-10-11 | 2023-03-23 | 2023-04-12 | 130
0 | EDTGSR1230 | HD-T4 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - IFC | 15 | 2022-09-20 | 2022-10-11 | 2023-04-05 | 2023-04-27 | 139
0 | EDTGSR2100 | HD-T4 MEZZANINE DECK INFILL BEAM FRAMING PLAN (+) 21.000 T.O.S - IFC | 10 | 2022-09-27 | 2022-10-11 | 2023-03-31 | 2023-04-13 | 131
0 | EDTGSR1290 | HD-T4 MEZZANINE DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - IFC | 15 | 2022-09-27 | 2022-10-18 | 2023-03-15 | 2023-04-04 | 119
0 | EDTGSR2130 | HD-T4 WEATHER DECK INFILL BEAM FRAMING PLAN EL (+) 25.000 T.O.S - IFC | 10 | 2022-10-04 | 2022-10-18 | 2023-04-28 | 2023-05-11 | 144
0 | EDTGSR1305 | HD-T4 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - IFC | 15 | 2022-10-04 | 2022-10-25 | 2023-04-05 | 2023-04-27 | 129
0 | EDTGSR1320 | HD-T4 HELIDECK PLATING DETAILS - IFC | 15 | 2022-10-11 | 2022-11-01 | 2023-04-05 | 2023-04-27 | 124
0 | EDTGSR1335 | HD-T4 HELIDECK SAFETY NET LAYOUT & DETAILS - IFC | 15 | 2022-11-16 | 2022-12-09 | 2023-03-15 | 2023-04-04 | 83
TERTAIRY |  |  | 135 | 2022-06-23 | 2023-01-05 | 2022-10-24 | 2023-08-14 | 152
0 | EDTGSR1400 | HD-T4 - DECK LIFTING PADEYE DETAILS - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-10-24 | 2022-11-18 | 84
0 | EDTGSR1415 | HD-T4 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - ICR | 20 | 2022-06-30 | 2022-08-02 | 2022-10-31 | 2022-11-25 | 84
0 | EDTGSR1430 | HD-T4 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS- ICR | 20 | 2022-07-07 | 2022-08-09 | 2022-11-07 | 2022-12-06 | 84
0 | EDTGSR2140 | HD-T4 CELLAR DECK LOADING DIAGRAM - IRC | 15 | 2022-07-19 | 2022-08-09 | 2023-01-04 | 2023-01-24 | 119
0 | EDTGSR1445 | HD-T4 MEZZANINE DECK EQUIPMENT SUPPORT GA AND DETAILS - ICR | 20 | 2022-07-19 | 2022-08-16 | 2022-11-14 | 2022-12-13 | 84
0 | EDTGSR1460 | HD-T4 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - ICR | 20 | 2022-07-19 | 2022-08-16 | 2022-11-14 | 2022-12-13 | 84
0 | EDTGSR2170 | HD-T4 MAIN DECK LOADING DIAGRAM - IRC | 15 | 2022-07-26 | 2022-08-16 | 2023-01-11 | 2023-01-31 | 119
0 | EDTGSR2200 | HD-T4 MEZZANINE DECK LOADING DIAGRAM - IRC | 15 | 2022-08-02 | 2022-08-23 | 2023-01-18 | 2023-02-07 | 119
0 | EDTGSR1475 | HD-T4 REMOVABLE HATCH DETAILS- ICR | 20 | 2022-08-02 | 2022-08-30 | 2022-11-28 | 2022-12-27 | 84
0 | EDTGSR2230 | HD-T4 WEATHER DECK LOADING DIAGRAM - IRC | 15 | 2022-08-09 | 2022-08-30 | 2023-01-25 | 2023-02-14 | 119
0 | EDTGSR1420 | HD-T4 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-05-02 | 2023-05-22 | 181
0 | EDTGSR2260 | HD-T4 HELIDECK LOADING DIAGRAM- IRC | 15 | 2022-08-16 | 2022-09-06 | 2023-02-01 | 2023-02-21 | 119
0 | EDTGSR1435 | HD-T4 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-23 | 2022-09-13 | 2023-05-02 | 2023-05-22 | 176
0 | EDTGSR2150 | HD-T4 CELLAR DECK LOADING DIAGRAM - IFA | 15 | 2022-08-23 | 2022-09-13 | 2023-03-21 | 2023-04-10 | 148
0 | EDTGSR2290 | HD-T4 PULLING POST & MATERIAL HANDLING PADEYES - IRC | 15 | 2022-08-23 | 2022-09-13 | 2023-02-14 | 2023-03-06 | 123
0 | EDTGSR1490 | HD-T4 DECK PENETRATION AND DETAILS- ICR | 20 | 2022-08-17 | 2022-09-14 | 2023-01-12 | 2023-02-08 | 104
0 | EDTGSR1450 | HD-T4 MEZZANINE DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-30 | 2022-09-20 | 2023-05-09 | 2023-05-29 | 176
0 | EDTGSR1465 | HD-T4 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-30 | 2022-09-20 | 2023-05-16 | 2023-06-05 | 181
0 | EDTGSR2180 | HD-T4 MAIN DECK LOADING DIAGRAM- IFA | 15 | 2022-08-30 | 2022-09-20 | 2023-03-21 | 2023-04-10 | 143
0 | EDTGSR2320 | HD-T4 PIPE SUPPORT DETAILS- IRC | 15 | 2022-08-30 | 2022-09-20 | 2023-02-15 | 2023-03-07 | 119
0 | EDTGSR1405 | HD-T4 - DECK LIFTING PADEYE DETAILS - IFA | 15 | 2022-09-02 | 2022-09-23 | 2023-03-21 | 2023-04-10 | 140
0 | EDTGSR1550 | HD-T4 WEST STAIR TOWER LAYOUT PLAN- ICR | 20 | 2022-08-30 | 2022-09-27 | 2023-03-01 | 2023-03-28 | 129
0 | EDTGSR1535 | HD-T4 WEST STAIR TOWER ELEVATIONS- ICR | 20 | 2022-08-30 | 2022-09-27 | 2022-12-28 | 2023-01-24 | 84
0 | EDTGSR2210 | HD-T4 MEZZANINE DECK LOADING DIAGRAM - IFA | 15 | 2022-09-06 | 2022-09-27 | 2023-03-21 | 2023-04-10 | 138
0 | EDTGSR1700 | HD-T4 - HELIDECK MARKING PLAN - ICR | 15 | 2022-09-13 | 2022-10-04 | 2023-01-25 | 2023-02-14 | 94
0 | EDTGSR1685 | HD-T4 JACKET RISER GA AND SUPPORT DETAILS - ICR | 15 | 2022-09-13 | 2022-10-04 | 2023-01-25 | 2023-02-14 | 94
0 | EDTGSR1595 | HD-T4 STAIR FROM WEATHER DECK TO HELIDECK - IRC | 15 | 2022-09-13 | 2022-10-04 | 2023-01-25 | 2023-02-14 | 94
0 | EDTGSR1715 | HD-T4 IDENTIFICATION BOARD DRAWING- ICR | 20 | 2022-09-06 | 2022-10-04 | 2023-01-18 | 2023-02-14 | 94
0 | EDTGSR1480 | HD-T4 REMOVABLE HATCH DETAILS - IFA | 15 | 2022-09-13 | 2022-10-04 | 2023-04-19 | 2023-05-11 | 154
0 | EDTGSR1610 | HD-T4 ACCESS PLATFORM - ICR | 20 | 2022-09-06 | 2022-10-04 | 2023-01-04 | 2023-01-31 | 84
0 | EDTGSR1625 | HD-T4 LADDER - ICR | 15 | 2022-09-13 | 2022-10-04 | 2023-01-11 | 2023-01-31 | 84
0 | EDTGSR1855 | HD-T4 WEST/ EAST SIDE STAIR DETAILS - IRC | 20 | 2022-09-06 | 2022-10-04 | 2023-01-04 | 2023-01-31 | 84
0 | EDTGSR2240 | HD-T4 WEATHER DECK LOADING DIAGRAM - IFA | 15 | 2022-09-13 | 2022-10-04 | 2023-03-21 | 2023-04-10 | 133
0 | EDTGSR1670 | HD-T4 - STRUCTURAL MISCELLANEOUS DETAIL - ICR | 20 | 2022-09-13 | 2022-10-11 | 2023-01-11 | 2023-02-07 | 84
0 | EDTGSR1640 | HD-T4 HELIDECK DRAIN GUTTER GA AND DETAILS - ICR | 10 | 2022-09-27 | 2022-10-11 | 2023-01-25 | 2023-02-07 | 84
0 | EDTGSR2270 | HD-T4 HELIDECK LOADING DIAGRAM - IFA | 15 | 2022-09-20 | 2022-10-11 | 2023-03-21 | 2023-04-10 | 128
0 | EDTGSR1505 | HD-T4 - VENT BOOM GA AND DETAILS - ICR | 20 | 2022-09-14 | 2022-10-12 | 2023-04-12 | 2023-05-11 | 148
0 | EDTGSR1655 | HD-T4 DECK DAVIT GA AND DETAILS - ICR | 10 | 2022-10-04 | 2022-10-18 | 2023-02-01 | 2023-02-14 | 84
0 | EDTGSR1730 | HD-T4 OFFSHORE INSTALLED FRAMING AND GRATING - ICR | 10 | 2022-10-04 | 2022-10-18 | 2023-02-01 | 2023-02-14 | 84
0 | EDTGSR1760 | HD-T4 HELICOPTER TIE DOWN DETAILS - ICR | 10 | 2022-10-04 | 2022-10-18 | 2023-02-01 | 2023-02-14 | 84
0 | EDTGSR1745 | HD-T4 STAIR FROM JACKET WALKWAY TO CELLAR DECK - ICR | 10 | 2022-10-04 | 2022-10-18 | 2023-02-01 | 2023-02-14 | 84
0 | EDTGSR1775 | HD-T4 SWING ROPE DETAILS DRAWING - ICR | 10 | 2022-10-04 | 2022-10-18 | 2023-02-01 | 2023-02-14 | 84
0 | EDTGSR2160 | HD-T4 CELLAR DECK LOADING DIAGRAM - IFC | 15 | 2022-09-27 | 2022-10-18 | 2023-04-27 | 2023-05-17 | 148
0 | EDTGSR2300 | HD-T4 PULLING POST & MATERIAL HANDLING PADEYES - IFA | 15 | 2022-09-27 | 2022-10-18 | 2023-03-21 | 2023-04-10 | 123
0 | EDTGSR2330 | HD-T4 PIPE SUPPORT DETAILS - IFA | 10 | 2022-10-04 | 2022-10-18 | 2023-03-22 | 2023-04-04 | 119
0 | EDTGSR1520 | HD-T4 - MAIN / CELLAR DECK MONORAIL AND DETAILS- ICR | 20 | 2022-09-21 | 2022-10-19 | 2023-05-17 | 2023-06-13 | 166
0 | EDTGSR1495 | HD-T4 DECK PENETRATION AND DETAIL - IFA | 15 | 2022-09-28 | 2022-10-19 | 2023-02-23 | 2023-03-15 | 104
0 | EDTGSR1485 | HD-T4 REMOVABLE HATCH DETAILS - IFC | 15 | 2022-10-04 | 2022-10-25 | 2023-05-12 | 2023-06-01 | 154
0 | EDTGSR1805 | HD-T4 WEATHER DECK INSTRUMENTAION CABINET SUNSHADE AND DETAILS - ICR | 10 | 2022-10-11 | 2022-10-25 | 2023-02-08 | 2023-02-21 | 84
0 | EDTGSR2190 | HD-T4 MAIN DECK LOADING DIAGRAM - IFC | 15 | 2022-10-04 | 2022-10-25 | 2023-04-27 | 2023-05-17 | 143
0 | EDTGSR2220 | HD-T4 MEZZANINE DECK LOADING DIAGRAM - IFC | 15 | 2022-10-11 | 2022-11-01 | 2023-04-27 | 2023-05-17 | 138
0 | EDTGSR1705 | HD-T4 - HELIDECK MARKING PLAN - IFA | 15 | 2022-10-18 | 2022-11-08 | 2023-03-01 | 2023-03-21 | 94
0 | EDTGSR1690 | HD-T4 JACKET RISER GA AND SUPPORT DETAILS - IFA | 15 | 2022-10-18 | 2022-11-08 | 2023-05-09 | 2023-05-29 | 141
0 | EDTGSR1720 | HD-T4 IDENTIFICATION BOARD DRAWING - IFA | 15 | 2022-10-18 | 2022-11-08 | 2023-03-01 | 2023-03-21 | 94
0 | EDTGSR2250 | HD-T4 WEATHER DECK LOADING DIAGRAM - IFC | 15 | 2022-10-18 | 2022-11-08 | 2023-04-27 | 2023-05-17 | 133
0 | EDTGSR2350 | HD-T4 WEST STAIR TOWER ELEVATIONS- IFA | 20 | 2022-10-11 | 2022-11-08 | 2023-04-12 | 2023-05-11 | 129
0 | EDTGSR2360 | HD-T4 WEST STAIR TOWER LAYOUT PLAN- IFA | 20 | 2022-10-11 | 2022-11-08 | 2023-04-12 | 2023-05-11 | 129
0 | EDTGSR2370 | HD-T4 STAIR FROM WEATHER DECK TO HELIDECK - IFA | 15 | 2022-10-18 | 2022-11-08 | 2023-04-19 | 2023-05-11 | 129
0 | EDTGSR2380 | HD-T4 ACCESS PLATFORM - IFA | 15 | 2022-10-18 | 2022-11-08 | 2023-05-30 | 2023-06-19 | 156
0 | EDTGSR2390 | HD-T4 LADDER - IFA | 15 | 2022-10-18 | 2022-11-08 | 2023-05-30 | 2023-06-19 | 156
0 | EDTGSR1500 | HD-T4 DECK PENETRATION AND DETAIL - IFC | 15 | 2022-10-19 | 2022-11-09 | 2023-03-16 | 2023-04-05 | 104
0 | EDTGSR1675 | HD-T4 - STRUCTURAL MISCELLANEOUS DETAIL - IFA | 15 | 2022-10-25 | 2022-11-15 | 2023-05-26 | 2023-06-15 | 149
0 | EDTGSR1645 | HD-T4 HELIDECK DRAIN GUTTER GA AND DETAILS - IFA | 15 | 2022-10-25 | 2022-11-15 | 2023-03-01 | 2023-03-21 | 89
0 | EDTGSR2280 | HD-T4 HELIDECK LOADING DIAGRAM - IFC | 15 | 2022-10-25 | 2022-11-15 | 2023-04-27 | 2023-05-17 | 128
0 | EDTGSR2340 | HD-T4 PIPE SUPPORT DETAILS - IFC | 10 | 2022-11-01 | 2022-11-15 | 2023-04-19 | 2023-05-04 | 119
0 | EDTGSR2400 | HD-T4 STAIR FROM JACKET WALKWAY TO CELLAR DECK - IFA | 10 | 2022-11-01 | 2022-11-15 | 2023-03-01 | 2023-03-14 | 84
0 | EDTGSR2410 | HD-T4 WEST/ EAST SIDE STAIR DETAILS - IFA | 20 | 2022-10-18 | 2022-11-15 | 2023-02-15 | 2023-03-14 | 84
0 | EDTGSR1510 | HD-T4 - VENT BOOM GA AND DETAILS - IFA | 15 | 2022-10-26 | 2022-11-16 | 2023-05-26 | 2023-06-15 | 148
0 | EDTGSR1660 | HD-T4 DECK DAVIT GA AND DETAILS - IFA | 15 | 2022-11-01 | 2022-11-22 | 2023-03-01 | 2023-03-21 | 84
0 | EDTGSR1735 | HD-T4 OFFSHORE INSTALLED FRAMING AND GRATING - IFA | 15 | 2022-11-01 | 2022-11-22 | 2023-03-01 | 2023-03-21 | 84
0 | EDTGSR1765 | HD-T4 HELICOPTER TIE DOWN DETAILS - IFA | 15 | 2022-11-01 | 2022-11-22 | 2023-03-01 | 2023-03-21 | 84
0 | EDTGSR1780 | HD-T4 SWING ROPE DETAILS DRAWING - IFA | 15 | 2022-11-01 | 2022-11-22 | 2023-03-01 | 2023-03-21 | 84
0 | EDTGSR2310 | HD-T4 PULLING POST & MATERIAL HANDLING PADEYES - IFC | 15 | 2022-11-01 | 2022-11-22 | 2023-04-27 | 2023-05-17 | 123
0 | EDTGSR1525 | HD-T4 - MAIN / CELLAR DECK MONORAIL AND DETAILS - IFA | 15 | 2022-11-02 | 2022-11-23 | 2023-07-03 | 2023-07-24 | 166
0 | EDTGSR1810 | HD-T4 WEATHER DECK INSTRUMENTAION CABINET SUNSHADE AND DETAILS - IFA | 15 | 2022-11-08 | 2022-11-29 | 2023-03-08 | 2023-03-28 | 84
0 | EDTGSR1440 | HD-T4 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-21 | 2022-12-14 | 2023-06-06 | 2023-06-26 | 137
0 | EDTGSR1425 | HD-T4 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-21 | 2022-12-14 | 2023-06-06 | 2023-06-26 | 137
0 | EDTGSR1695 | HD-T4 JACKET RISER GA AND SUPPORT DETAILS - IFC | 15 | 2022-11-22 | 2022-12-15 | 2023-06-13 | 2023-07-06 | 141
0 | EDTGSR1725 | HD-T4 IDENTIFICATION BOARD DRAWING - IFC | 15 | 2022-11-22 | 2022-12-15 | 2023-04-05 | 2023-04-27 | 94
0 | EDTGSR1530 | HD-T4 - MAIN / CELLAR DECK MONORAIL AND DETAILS - IFC | 15 | 2022-11-23 | 2022-12-16 | 2023-07-25 | 2023-08-14 | 166
0 | EDTGSR1410 | HD-T4 - DECK LIFTING PADEYE DETAILS - IFC | 15 | 2022-11-28 | 2022-12-21 | 2023-04-27 | 2023-05-17 | 104
0 | EDTGSR1455 | HD-T4 MEZZANINE DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-28 | 2022-12-21 | 2023-06-13 | 2023-07-06 | 137
0 | EDTGSR1560 | HD-T4 WEST STAIR TOWER LAYOUT PLAN- IFC | 20 | 2022-11-22 | 2022-12-22 | 2023-05-26 | 2023-06-22 | 129
0 | EDTGSR1545 | HD-T4 WEST STAIR TOWER ELEVATIONS- IFC | 20 | 2022-11-22 | 2022-12-22 | 2023-05-26 | 2023-06-22 | 129
0 | EDTGSR1605 | HD-T4 STAIR FROM WEATHER DECK TO HELIDECK - IFC | 20 | 2022-11-22 | 2022-12-22 | 2023-05-26 | 2023-06-22 | 129
0 | EDTGSR1620 | HD-T4 ACCESS PLATFORM - IFC | 20 | 2022-11-22 | 2022-12-22 | 2023-07-07 | 2023-08-04 | 156
0 | EDTGSR1635 | HD-T4 LADDER - IFC | 20 | 2022-11-22 | 2022-12-22 | 2023-07-07 | 2023-08-04 | 156
0 | EDTGSR1650 | HD-T4 HELIDECK DRAIN GUTTER GA AND DETAILS - IFC | 15 | 2022-11-29 | 2022-12-22 | 2023-04-05 | 2023-04-27 | 89
0 | EDTGSR1515 | HD-T4 - VENT BOOM GA AND DETAILS - IFC | 15 | 2022-11-30 | 2022-12-23 | 2023-07-05 | 2023-07-26 | 148
0 | EDTGSR1470 | HD-T4 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-12-07 | 2022-12-28 | 2023-06-20 | 2023-07-13 | 137
0 | EDTGSR1665 | HD-T4 DECK DAVIT GA AND DETAILS - IFC | 15 | 2022-12-08 | 2022-12-29 | 2023-04-05 | 2023-04-27 | 84
0 | EDTGSR1740 | HD-T4 OFFSHORE INSTALLED FRAMING AND GRATING - IFC | 15 | 2022-12-08 | 2022-12-29 | 2023-04-05 | 2023-04-27 | 84
0 | EDTGSR1770 | HD-T4 HELICOPTER TIE DOWN DETAILS - IFC | 15 | 2022-12-08 | 2022-12-29 | 2023-04-05 | 2023-04-27 | 84
0 | EDTGSR1755 | HD-T4 STAIR FROM JACKET WALKWAY TO CELLAR DECK - IFC | 20 | 2022-11-29 | 2022-12-29 | 2023-03-29 | 2023-04-27 | 84
0 | EDTGSR1785 | HD-T4 SWING ROPE DETAILS DRAWING - IFC | 15 | 2022-12-08 | 2022-12-29 | 2023-04-05 | 2023-04-27 | 84
0 | EDTGSR1815 | HD-T4 WEATHER DECK INSTRUMENTAION CABINET SUNSHADE AND DETAILS - IFC | 10 | 2022-12-15 | 2022-12-29 | 2023-04-12 | 2023-04-27 | 84
0 | EDTGSR1875 | HD-T4 WEST/ EAST SIDE STAIR DETAILS - IFC | 20 | 2022-11-29 | 2022-12-29 | 2023-03-29 | 2023-04-27 | 84
0 | EDTGSR1710 | HD-T4 - HELIDECK MARKING PLAN - IFC | 15 | 2022-12-09 | 2022-12-30 | 2023-04-05 | 2023-04-27 | 83
0 | EDTGSR1680 | HD-T4 - STRUCTURAL MISCELLANEOUS DETAIL - IFC | 15 | 2022-12-15 | 2023-01-05 | 2023-07-05 | 2023-07-26 | 139
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDTGSR2000 | HD-T4 STRUCTURAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDTGSR2005 | HD-T4 STRUCTURAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDTGSR2010 | HD-T4 STRUCTURAL MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
PIPELINE |  |  | 76 | 2022-08-11 | 2022-11-24 | 2023-01-10 | 2023-04-27 | 106
DRAWINGS |  |  | 76 | 2022-08-11 | 2022-11-24 | 2023-01-10 | 2023-04-27 | 106
0 | DEP1PL4790 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA WHP HD-T4 - ICR | 16 | 2022-08-11 | 2022-09-01 | 2023-01-10 | 2023-01-31 | 106
0 | DEP1PL4830 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA WHP HD-T4 - IFA | 16 | 2022-09-16 | 2022-10-07 | 2023-02-15 | 2023-03-08 | 106
0 | DEP1PL4780 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA WHP HD-T4 - IFC | 24 | 2022-10-24 | 2022-11-24 | 2023-03-23 | 2023-04-27 | 106
NAVAL & ARCHITECTURE |  |  | 159 | 2022-04-05 | 2022-11-22 | 2022-09-05 | 2023-04-27 | 109
DOCUMENTS |  |  | 159 | 2022-04-05 | 2022-11-22 | 2022-09-05 | 2023-04-27 | 109
0 | EDTDNA1000 | HD-T4 TOPSIDE -WEIGHT & COG CALCULATION - ICR | 20 | 2022-04-05 | 2022-05-06 | 2022-09-05 | 2022-09-30 | 103
0 | EDTDNA1020 | HD-T4 JACKET -WEIGHT & COG CALCULATION - ICR | 20 | 2022-05-12 | 2022-06-09 | 2022-11-07 | 2022-12-06 | 124
0 | EDTDNA1005 | HD-T4 TOPSIDE -WEIGHT & COG CALCULATION - IFA | 15 | 2022-05-20 | 2022-06-10 | 2022-10-31 | 2022-11-18 | 113
0 | EDTDNA1010 | HD-T4 TOPSIDE -WEIGHT & COG CALCULATION - IFC | 20 | 2022-06-24 | 2022-07-27 | 2022-12-19 | 2023-01-13 | 121
0 | EDTDNA1030 | HD-T4 JACKET -WEIGHT & COG CALCULATION - IFA | 20 | 2022-09-13 | 2022-10-11 | 2023-02-15 | 2023-03-14 | 109
0 | EDTDNA1040 | HD-T4 JACKET -WEIGHT & COG CALCULATION - IFC | 20 | 2022-10-25 | 2022-11-22 | 2023-03-29 | 2023-04-27 | 109
HAIR DALMA WHP HD-03 TOPSIDES |  |  | 363 | 2022-01-21 | 2023-01-19 | 2022-03-25 | 2023-08-29 | 223
PROCESS |  |  | 243 | 2022-01-21 | 2023-01-09 | 2022-03-25 | 2023-04-27 | 77
DOCUMENTS |  |  | 92 | 2022-03-08 | 2022-07-22 | 2022-05-19 | 2023-01-23 | 130
PROCESS SIMULATIONS & REPORTS |  |  | 62 | 2022-03-15 | 2022-06-14 | 2022-08-05 | 2022-11-04 | 101
0 | EDHDPR1000 | ALARM AND TRIP SCHEDULE (HAIR DALMA HD-03 WHP) - ICR | 15 | 2022-03-15 | 2022-04-05 | 2022-08-05 | 2022-08-25 | 97
0 | EDHDPR1005 | ALARM AND TRIP SCHEDULE (HAIR DALMA HD-03 WHP) - IFA | 12 | 2022-04-19 | 2022-05-10 | 2022-09-15 | 2022-09-30 | 101
0 | EDHDPR1010 | ALARM AND TRIP SCHEDULE (HAIR DALMA HD-03 WHP) - IFC | 15 | 2022-05-24 | 2022-06-14 | 2022-10-17 | 2022-11-04 | 101
PROCESS LISTS |  |  | 65 | 2022-03-08 | 2022-06-10 | 2022-06-08 | 2022-11-28 | 119
0 | EDHDPR1015 | EQUIPMENT LIST (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-03-08 | 2022-03-22 | 2022-06-08 | 2022-06-21 | 63
0 | EDHDPR1030 | LINE LIST (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-03-15 | 2022-03-29 | 2022-07-06 | 2022-07-22 | 78
0 | EDHDPR1020 | EQUIPMENT LIST (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-07-06 | 2022-07-22 | 63
0 | EDHDPR1035 | LINE LIST (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-08-25 | 2022-09-07 | 91
0 | EDHDPR1025 | EQUIPMENT LIST (HAIR DALMA HD-03 WHP) - IFC | 19 | 2022-05-06 | 2022-06-02 | 2022-11-02 | 2022-11-28 | 125
0 | EDHDPR1040 | LINE LIST (HAIR DALMA HD-03 WHP) - IFC | 20 | 2022-05-13 | 2022-06-10 | 2022-09-22 | 2022-10-19 | 91
PREPARATION OF DATASHEETS |  |  | 87 | 2022-03-15 | 2022-07-22 | 2022-05-19 | 2023-01-23 | 130
0 | EDHDPR1255 | PROCESS DATA SHEET PIG LAUNCHER (HAIR DALMA HD-03 WHP) - ICR | 4 | 2022-03-15 | 2022-03-21 | 2022-05-24 | 2022-05-27 | 47
0 | EDHDPR1045 | PROCESS DATA SHEET CHOKE VALVES (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-03-15 | 2022-03-29 | 2022-05-19 | 2022-06-01 | 44
0 | EDHDPR1240 | PROCESS DATA SHEET VENT / DRAIN DRUM (HAIR DALMA HD-03 WHP) - ICR | 5 | 2022-03-22 | 2022-03-29 | 2022-06-14 | 2022-06-20 | 57
0 | EDHDPR1075 | PROCESS DATA SHEET MOTOR OPERATED VALVES (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-03-15 | 2022-03-29 | 2022-05-19 | 2022-06-01 | 44
0 | EDHDPR1090 | PROCESS DATASHEET SHUTDOWN VALVES (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-03-17 | 2022-03-31 | 2022-05-23 | 2022-06-03 | 44
0 | EDHDPR1120 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-03-21 | 2022-04-04 | 2022-08-12 | 2022-08-25 | 98
0 | EDHDPR1105 | PROCESS DATASHEET IRCD (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-03-21 | 2022-04-04 | 2022-05-30 | 2022-06-10 | 47
0 | EDHDPR1135 | PROCESS DATASHEET PRESSURE GAUGES (HAIR DALMA HD-03 WHP) - ICR | 9 | 2022-03-28 | 2022-04-08 | 2022-08-18 | 2022-08-30 | 97
0 | EDHDPR1165 | PROCESS DATASHEET TEMPERATURE GAUGE (HAIR DALMA HD-03 WHP) - ICR | 9 | 2022-03-28 | 2022-04-08 | 2022-08-19 | 2022-08-31 | 98
0 | EDHDPR1150 | PROCESS DATASHEET PRESSURE INSTRUMENT (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-08-18 | 2022-08-31 | 97
0 | EDHDPR1060 | PROCESS DATA SHEET WET GAS METER (HAIR DALMA HD-03 WHP) - MULTI PHASE FLOW METER - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-06-06 | 2022-06-17 | 46
0 | EDHDPR1245 | PROCESS DATA SHEET VENT / DRAIN DRUM (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-03-29 | 2022-04-12 | 2022-09-02 | 2022-09-15 | 107
0 | EDHDPR1180 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-03-30 | 2022-04-13 | 2022-08-23 | 2022-09-05 | 98
0 | EDHDPR1195 | PROCESS DATASHEET LEVEL GAUGE (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-08-31 | 2022-09-13 | 102
0 | EDHDPR1260 | PROCESS DATA SHEET PIG LAUNCHER (HAIR DALMA HD-03 WHP) - IFA | 9 | 2022-04-04 | 2022-04-15 | 2022-11-14 | 2022-11-24 | 154
0 | EDHDPR1210 | PROCESS DATASHEET LEVEL INSTRUMENT (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-04-05 | 2022-04-19 | 2022-09-08 | 2022-09-21 | 106
0 | EDHDPR1225 | PROCESS DATASHEET FLOW SWITCH (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-04-07 | 2022-04-21 | 2022-09-28 | 2022-10-11 | 118
0 | EDHDPR1050 | PROCESS DATA SHEET CHOKE VALVES (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-06-22 | 2022-07-05 | 48
0 | EDHDPR1080 | PROCESS DATA SHEET MOTOR OPERATED VALVES (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-06-23 | 2022-07-06 | 49
0 | EDHDPR1095 | PROCESS DATASHEET SHUTDOWN VALVES (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-04-14 | 2022-04-28 | 2022-06-22 | 2022-07-05 | 46
0 | EDHDPR1125 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-04-18 | 2022-05-05 | 2022-09-29 | 2022-10-12 | 112
0 | EDHDPR1110 | PROCESS DATASHEET IRCD (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-04-18 | 2022-05-05 | 2022-06-27 | 2022-07-13 | 47
0 | EDHDPR1270 | PROCESS DATA SHEET RESTRICTION ORIFICES (HAIR DALMA HD-03 WHP) - ICR | 10 | 2022-04-21 | 2022-05-10 | 2022-08-29 | 2022-09-09 | 86
0 | EDHDPR1140 | PROCESS DATASHEET PRESSURE GAUGES (HAIR DALMA HD-03 WHP) - IFA | 9 | 2022-04-22 | 2022-05-10 | 2022-10-07 | 2022-10-19 | 114
0 | EDHDPR1170 | PROCESS DATASHEET TEMPERATURE GAUGE (HAIR DALMA HD-03 WHP) - IFA | 9 | 2022-04-22 | 2022-05-10 | 2022-10-04 | 2022-10-14 | 111
0 | EDHDPR1155 | PROCESS DATASHEET PRESSURE INSTRUMENT (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-09-15 | 2022-09-28 | 97
0 | EDHDPR1250 | PROCESS DATA SHEET VENT / DRAIN DRUM (HAIR DALMA HD-03 WHP) - IFC | 20 | 2022-04-12 | 2022-05-13 | 2022-09-16 | 2022-10-13 | 107
0 | EDHDPR1065 | PROCESS DATA SHEET WET GAS METER (HAIR DALMA HD-03 WHP) - MULTI PHASE FLOW METER - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-07-06 | 2022-07-22 | 48
0 | EDHDPR1200 | PROCESS DATASHEET LEVEL GAUGE (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-04-27 | 2022-05-16 | 2022-09-29 | 2022-10-12 | 105
0 | EDHDPR1185 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-04-27 | 2022-05-16 | 2022-09-20 | 2022-10-03 | 98
0 | EDHDPR1215 | PROCESS DATASHEET LEVEL INSTRUMENT (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-05-06 | 2022-05-20 | 2022-11-15 | 2022-11-28 | 134
0 | EDHDPR1230 | PROCESS DATASHEET FLOW SWITCH (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-05-10 | 2022-05-24 | 2022-11-25 | 2022-12-12 | 140
0 | EDHDPR1265 | PROCESS DATA SHEET PIG LAUNCHER (HAIR DALMA HD-03 WHP) - IFC | 19 | 2022-04-29 | 2022-05-31 | 2022-12-13 | 2023-01-06 | 154
0 | EDHDPR1085 | PROCESS DATA SHEET MOTOR OPERATED VALVES (HAIR DALMA HD-03 WHP) - IFC | 15 | 2022-05-13 | 2022-06-03 | 2022-07-26 | 2022-08-15 | 49
0 | EDHDPR1275 | PROCESS DATA SHEET RESTRICTION ORIFICES (HAIR DALMA HD-03 WHP) - IFA | 10 | 2022-05-24 | 2022-06-07 | 2022-09-26 | 2022-10-07 | 86
0 | EDHDPR1055 | PROCESS DATA SHEET CHOKE VALVES (HAIR DALMA HD-03 WHP) - IFC | 20 | 2022-05-13 | 2022-06-10 | 2022-07-25 | 2022-08-19 | 48
0 | EDHDPR1100 | PROCESS DATASHEET SHUTDOWN VALVES (HAIR DALMA HD-03 WHP) - IFC | 20 | 2022-05-17 | 2022-06-14 | 2022-07-25 | 2022-08-19 | 46
0 | EDHDPR1130 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (HAIR DALMA HD-03 WHP) - IFC | 20 | 2022-05-19 | 2022-06-16 | 2022-10-27 | 2022-11-23 | 112
0 | EDHDPR1115 | PROCESS DATASHEET IRCD (HAIR DALMA HD-03 WHP) - IFC | 20 | 2022-05-19 | 2022-06-16 | 2022-07-28 | 2022-08-24 | 47
0 | EDHDPR1145 | PROCESS DATASHEET PRESSURE GAUGES (HAIR DALMA HD-03 WHP) - IFC | 19 | 2022-05-24 | 2022-06-20 | 2022-11-03 | 2022-11-29 | 114
0 | EDHDPR1175 | PROCESS DATASHEET TEMPERATURE GAUGE (HAIR DALMA HD-03 WHP) - IFC | 19 | 2022-05-24 | 2022-06-20 | 2022-10-31 | 2022-11-24 | 111
0 | EDHDPR1205 | PROCESS DATASHEET LEVEL GAUGE (HAIR DALMA HD-03 WHP) - IFC | 19 | 2022-05-26 | 2022-06-22 | 2022-10-25 | 2022-11-18 | 105
0 | EDHDPR1160 | PROCESS DATASHEET PRESSURE INSTRUMENT (HAIR DALMA HD-03 WHP) - IFC | 20 | 2022-05-26 | 2022-06-23 | 2022-10-13 | 2022-11-09 | 97
0 | EDHDPR1070 | PROCESS DATA SHEET WET GAS METER (HAIR DALMA HD-03 WHP) - MULTI PHASE FLOW METER - IFC | 20 | 2022-05-27 | 2022-06-24 | 2022-08-08 | 2022-09-02 | 48
0 | EDHDPR1190 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (HAIR DALMA HD-03 WHP) - IFC | 20 | 2022-05-30 | 2022-06-27 | 2022-10-18 | 2022-11-14 | 98
0 | EDHDPR1220 | PROCESS DATASHEET LEVEL INSTRUMENT (HAIR DALMA HD-03 WHP) - IFC | 20 | 2022-06-03 | 2022-07-01 | 2022-12-15 | 2023-01-11 | 134
0 | EDHDPR1235 | PROCESS DATASHEET FLOW SWITCH (HAIR DALMA HD-03 WHP) - IFC | 20 | 2022-06-07 | 2022-07-05 | 2022-12-27 | 2023-01-23 | 140
0 | EDHDPR1280 | PROCESS DATA SHEET RESTRICTION ORIFICES (HAIR DALMA HD-03 WHP) - IFC | 20 | 2022-06-21 | 2022-07-22 | 2022-10-24 | 2022-11-18 | 86
DRAWINGS |  |  | 188 | 2022-01-21 | 2022-10-20 | 2022-03-25 | 2023-01-24 | 67
PFD / UFD / DPDT / PSFS & HMB |  |  | 73 | 2022-01-21 | 2022-05-09 | 2022-03-25 | 2022-12-28 | 163
0 | EDHGPR1030 | HEAT AND MATERIAL BALANCE - HAIR DALMA HD-03 WHP - ICR | 15 | 2022-01-21 | 2022-02-11 | 2022-03-29 | 2022-04-18 | 47
0 | EDHGPR1000 | PFD's - HAIR DALMA HD-03 WHP TEST AND PRODUCTION MANIFOLD - ICR | 15 | 2022-01-21 | 2022-02-11 | 2022-03-25 | 2022-04-14 | 45
0 | EDHGPR1015 | UFD's - HAIR DALMA HD-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - ICR | 15 | 2022-01-21 | 2022-02-11 | 2022-08-29 | 2022-09-16 | 150
0 | EDHGPR1045 | DPDT DIAGRAMS - HAIR DALMA HD-03 WHP - TEST AND PRODUCTION MANIFOLD - ICR | 20 | 2022-01-25 | 2022-02-22 | 2022-04-07 | 2022-05-09 | 52
0 | EDHGPR1060 | DPDT DIAGRAMS - HAIR DALMA HD-03 WHP VENT AND DRAIN UTILITIES SUPPLY - ICR | 20 | 2022-01-25 | 2022-02-22 | 2022-09-06 | 2022-10-03 | 154
0 | EDHGPR1075 | PSFS's - HAIR DALMA HD-03 WHP - TEST AND PRODUCTION MANIFOLD - ICR | 20 | 2022-01-26 | 2022-02-23 | 2022-04-07 | 2022-05-09 | 51
0 | EDHGPR1090 | PSFS's - HAIR DALMA HD-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - ICR | 20 | 2022-01-26 | 2022-02-23 | 2022-04-11 | 2022-05-11 | 53
0 | EDHGPR1020 | UFD's - HAIR DALMA HD-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFA | 10 | 2022-02-25 | 2022-03-11 | 2022-10-03 | 2022-10-14 | 150
0 | EDHGPR1005 | PFD's - HAIR DALMA HD-03 WHP TEST AND PRODUCTION MANIFOLD - IFA | 15 | 2022-02-25 | 2022-03-18 | 2022-08-08 | 2022-08-26 | 110
0 | EDHGPR1035 | HEAT AND MATERIAL BALANCE - HAIR DALMA HD-03 WHP - IFA | 15 | 2022-02-25 | 2022-03-18 | 2022-11-01 | 2022-11-21 | 171
0 | EDHGPR1080 | PSFS's - HAIR DALMA HD-03 WHP - TEST AND PRODUCTION MANIFOLD - IFA | 10 | 2022-03-07 | 2022-03-21 | 2022-10-20 | 2022-11-02 | 157
0 | EDHGPR1095 | PSFS's - HAIR DALMA HD-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFA | 10 | 2022-03-07 | 2022-03-21 | 2022-10-20 | 2022-11-02 | 157
0 | EDHGPR1050 | DPDT DIAGRAMS - HAIR DALMA HD-03 WHP - TEST AND PRODUCTION MANIFOLD - IFA | 10 | 2022-03-08 | 2022-03-22 | 2022-10-18 | 2022-10-31 | 154
0 | EDHGPR1065 | DPDT DIAGRAMS - HAIR DALMA HD-03 WHP VENT AND DRAIN UTILITIES SUPPLY - IFA | 10 | 2022-03-08 | 2022-03-22 | 2022-10-18 | 2022-10-31 | 154
0 | EDHGPR1040 | HEAT AND MATERIAL BALANCE - HAIR DALMA HD-03 WHP - IFC | 15 | 2022-04-01 | 2022-04-22 | 2022-12-08 | 2022-12-28 | 171
0 | EDHGPR1025 | UFD's - HAIR DALMA HD-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFC | 20 | 2022-03-25 | 2022-04-22 | 2022-10-31 | 2022-11-25 | 150
0 | EDHGPR1010 | PFD's - HAIR DALMA HD-03 WHP TEST AND PRODUCTION MANIFOLD - IFC | 16 | 2022-04-01 | 2022-04-25 | 2022-11-04 | 2022-11-25 | 149
0 | EDHGPR1055 | DPDT DIAGRAMS - HAIR DALMA HD-03 WHP - TEST AND PRODUCTION MANIFOLD - IFC | 20 | 2022-04-05 | 2022-05-06 | 2022-11-15 | 2022-12-14 | 154
0 | EDHGPR1070 | DPDT DIAGRAMS - HAIR DALMA HD-03 WHP VENT AND DRAIN UTILITIES SUPPLY - IFC | 20 | 2022-04-05 | 2022-05-06 | 2022-11-15 | 2022-12-14 | 154
0 | EDHGPR1085 | PSFS's - HAIR DALMA HD-03 WHP - TEST AND PRODUCTION MANIFOLD - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-11-15 | 2022-12-14 | 153
0 | EDHGPR1100 | PSFS's - HAIR DALMA HD-03 WHP - VENT AND DRAIN - UTILITIES SUPPLY - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-11-15 | 2022-12-14 | 153
PIPING & INSTRUMENTATION DIAGRAMS |  |  | 172 | 2022-02-14 | 2022-10-20 | 2022-04-15 | 2023-01-24 | 67
0 | EDHGPR1105 | P&ID - DRAWING INDEX HAIR DALMA HD-03 WHP - ICR | 18 | 2022-02-16 | 2022-03-14 | 2022-04-20 | 2022-05-18 | 45
0 | EDHGPR1120 | P&IDs - HAIR DALMA HD-03 WHP - ICR | 21 | 2022-02-14 | 2022-03-15 | 2022-04-15 | 2022-05-18 | 44
0 | EDHGPR1125 | P&IDs - HAIR DALMA HD-03 WHP - ISSUED FOR HAZOP | 24 | 2022-04-14 | 2022-05-23 | 2022-07-14 | 2022-08-16 | 59
0 | EDHGPR1130 | P&IDs - HAIR DALMA HD-03 WHP - IFA | 20 | 2022-07-13 | 2022-08-10 | 2022-09-21 | 2022-10-18 | 50
0 | EDHGPR1110 | P&ID - DRAWING INDEX HAIR DALMA HD-03 WHP - IFA | 20 | 2022-07-13 | 2022-08-10 | 2022-11-01 | 2022-11-28 | 79
0 | EDHGPR1135 | P&IDs - HAIR DALMA HD-03 WHP - IFC | 20 | 2022-09-22 | 2022-10-20 | 2022-11-29 | 2022-12-28 | 48
0 | EDHGPR1115 | P&ID - DRAWING INDEX HAIR DALMA HD-03 WHP - IFC | 20 | 2022-09-22 | 2022-10-20 | 2022-12-28 | 2023-01-24 | 67
CAUSE & EFFECT & SAFE CHARTS |  |  | 73 | 2022-03-29 | 2022-07-18 | 2022-07-18 | 2022-12-19 | 109
0 | EDHGPR1140 | CAUSE & EFFECT CHARTS - HAIR DALMA HD-03 WHP - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-07-18 | 2022-07-29 | 73
0 | EDHGPR1155 | SAFE CHART - HAIR DALMA HD-03 WHP - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-09-05 | 2022-09-16 | 98
0 | EDHGPR1145 | CAUSE & EFFECT CHARTS - HAIR DALMA HD-03 WHP - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-08-15 | 2022-08-26 | 73
0 | EDHGPR1160 | SAFE CHART - HAIR DALMA HD-03 WHP - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-09-29 | 2022-10-12 | 98
0 | EDHGPR1165 | SAFE CHART - HAIR DALMA HD-03 WHP - IFC | 25 | 2022-06-06 | 2022-07-14 | 2022-10-25 | 2022-11-28 | 98
0 | EDHGPR1150 | CAUSE & EFFECT CHARTS - HAIR DALMA HD-03 WHP - IFC | 35 | 2022-05-25 | 2022-07-18 | 2022-10-28 | 2022-12-19 | 109
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDHGPR2000 | HD-03 PROCESS MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDHGPR2005 | HD-03 PROCESS MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDHGPR2010 | HD-03 PROCESS MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
MATERIAL & CORROSION |  |  | 226 | 2022-02-11 | 2023-01-05 | 2022-04-19 | 2023-04-27 | 79
DOCUMENTS |  |  | 70 | 2022-09-09 | 2022-12-20 | 2022-11-30 | 2023-03-09 | 58
0 | EDHDMA1000 | HD-03 DEAD-LEG REGISTER - ICR | 15 | 2022-09-09 | 2022-09-30 | 2022-11-30 | 2022-12-22 | 58
0 | EDHDMA1010 | HD-03 DEAD-LEG REGISTER - IFA | 15 | 2022-10-14 | 2022-11-04 | 2023-01-06 | 2023-01-26 | 58
0 | EDHDMA1020 | HD-03 DEAD-LEG REGISTER - IFC | 20 | 2022-11-18 | 2022-12-20 | 2023-02-10 | 2023-03-09 | 58
DRAWINGS |  |  | 71 | 2022-02-11 | 2022-05-26 | 2022-04-19 | 2022-11-28 | 130
0 | EDHGMA1000 | MATERIAL SELECTION DIAGRAMS - HAIR DALMA HD-03 WHP - ICR | 14 | 2022-02-11 | 2022-03-03 | 2022-04-19 | 2022-05-11 | 47
0 | EDHGMA1005 | MATERIAL SELECTION DIAGRAMS - HAIR DALMA HD-03 WHP - IFA | 15 | 2022-03-17 | 2022-04-07 | 2022-08-08 | 2022-08-26 | 96
0 | EDHGMA1010 | MATERIAL SELECTION DIAGRAMS - HAIR DALMA HD-03 WHP - IFC | 22 | 2022-04-21 | 2022-05-26 | 2022-10-28 | 2022-11-28 | 130
MISCELLANEOUS DELIVERABLES |  |  | 73 | 2022-09-22 | 2023-01-05 | 2023-01-13 | 2023-04-27 | 79
0 | EDHGMA2000 | HD-03 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-13 | 2023-02-09 | 79
0 | EDHGMA2005 | HD-03 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - IFA | 18 | 2022-11-03 | 2022-11-29 | 2023-02-24 | 2023-03-21 | 79
0 | EDHGMA2010 | HD-03 MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-15 | 2023-01-05 | 2023-04-05 | 2023-04-27 | 79
SAFETY |  |  | 321 | 2022-02-22 | 2023-01-09 | 2022-06-13 | 2023-04-27 | 109
DRAWINGS |  |  | 246 | 2022-02-22 | 2022-10-26 | 2022-06-13 | 2023-01-24 | 91
0 | EDHGSA1000 | P&ID FIREWATER DRY SYSTEM - HAIR DALMA HD-03 WHP - ICR | 15 | 2022-02-22 | 2022-03-15 | 2022-06-13 | 2022-07-01 | 76
0 | EDHGSA1005 | P&ID FIREWATER DRY SYSTEM - HAIR DALMA HD-03 WHP - ISSUED FOR HAZOP | 15 | 2022-03-29 | 2022-04-19 | 2022-07-21 | 2022-08-10 | 82
0 | EDHGSA1015 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - HAIR DALMA HD-03 WHP - ICR | 10 | 2022-05-16 | 2022-05-30 | 2022-08-23 | 2022-09-05 | 68
0 | EDHGSA1030 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - HAIR DALMA HD-03 WHP - ICR | 10 | 2022-06-17 | 2022-07-01 | 2022-09-30 | 2022-10-13 | 72
0 | EDHGSA1007 | P&ID FIREWATER DRY SYSTEM - HAIR DALMA HD-03 WHP - IFA | 15 | 2022-06-12 | 2022-07-03 | 2022-08-25 | 2022-09-14 | 54
0 | EDHGSA1020 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - HAIR DALMA HD-03 WHP - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-09-29 | 2022-10-12 | 73
0 | EDHGSA1060 | FIRE AND GAS CAUSE & EFFECT CHART – HAIR DALMA HD-03 WHP - ICR | 15 | 2022-07-01 | 2022-07-27 | 2022-11-01 | 2022-11-21 | 84
0 | EDHGSA1010 | P&ID FIREWATER DRY SYSTEM - HAIR DALMA HD-03 WHP - IFC | 15 | 2022-07-14 | 2022-08-04 | 2022-09-29 | 2022-10-19 | 54
0 | EDHGSA1035 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - HAIR DALMA HD-03 WHP - IFA | 10 | 2022-07-27 | 2022-08-10 | 2022-12-07 | 2022-12-20 | 95
0 | EDHGSA1075 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - HAIR DALMA HD-03 WHP - ICR | 15 | 2022-07-27 | 2022-08-17 | 2022-10-27 | 2022-11-16 | 66
0 | EDHGSA1065 | FIRE AND GAS CAUSE & EFFECT CHART – HAIR DALMA HD-03 WHP - IFA | 10 | 2022-08-10 | 2022-08-24 | 2022-12-08 | 2022-12-21 | 86
0 | EDHGSA1025 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - HAIR DALMA HD-03 WHP - IFC | 15 | 2022-08-11 | 2022-09-01 | 2023-01-04 | 2023-01-24 | 102
0 | EDHGSA1070 | FIRE AND GAS CAUSE & EFFECT CHART – HAIR DALMA HD-03 WHP - IFC | 10 | 2022-09-07 | 2022-09-21 | 2023-01-05 | 2023-01-18 | 84
0 | EDHGSA1080 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - HAIR DALMA HD-03 WHP - IFA | 15 | 2022-08-31 | 2022-09-21 | 2022-12-01 | 2022-12-21 | 66
0 | EDHGSA1040 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - HAIR DALMA HD-03 WHP - IFC | 15 | 2022-09-07 | 2022-09-28 | 2023-01-04 | 2023-01-24 | 83
0 | EDHGSA1085 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT - HAIR DALMA HD-03 WHP - IFC | 10 | 2022-10-12 | 2022-10-26 | 2023-01-05 | 2023-01-18 | 59
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDHGSA2000 | HD-03 SAFETY MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDHGSA2005 | HD-03 SAFETY MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDHGSA2010 | HD-03 SAFETY MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
PIPING |  |  | 216 | 2022-03-11 | 2023-01-19 | 2022-05-25 | 2023-04-27 | 69
3D MODELING |  |  | 166 | 2022-05-25 | 2023-01-19 | 2022-08-04 | 2023-03-29 | 50
30% MODEL REVIEW/REPORT |  |  | 50 | 2022-05-25 | 2022-08-08 | 2022-08-04 | 2022-10-12 | 48
0 | EDHDPI3100 | HD-03 30% 3D MODEL REVIEW REPORT - ICR | 10 | 2022-05-25 | 2022-06-08 | 2022-08-04 | 2022-08-17 | 48
0 | EDHDPI3105 | HD-03 30% 3D MODEL REVIEW REPORT - IFA | 10 | 2022-06-22 | 2022-07-06 | 2022-09-01 | 2022-09-14 | 48
0 | EDHDPI3110 | HD-03 30% 3D MODEL REVIEW REPORT - IFC | 10 | 2022-07-25 | 2022-08-08 | 2022-09-29 | 2022-10-12 | 48
60% MODEL REVIEW/REPORT |  |  | 60 | 2022-08-26 | 2022-11-18 | 2022-11-02 | 2023-02-01 | 52
0 | EDHDPI3120 | HD-03 60% 3D MODEL REVIEW REPORT - ICR | 10 | 2022-08-26 | 2022-09-09 | 2022-11-02 | 2022-11-15 | 48
0 | EDHDPI3125 | HD-03 60% 3D MODEL REVIEW REPORT - IFA | 10 | 2022-09-23 | 2022-10-07 | 2022-12-08 | 2022-12-21 | 52
0 | EDHDPI3130 | HD-03 60% 3D MODEL REVIEW REPORT - IFC | 20 | 2022-10-21 | 2022-11-18 | 2023-01-05 | 2023-02-01 | 52
90% MODEL REVIEW/REPORT |  |  | 41 | 2022-11-21 | 2023-01-19 | 2023-02-02 | 2023-03-29 | 50
0 | EDHDPI3140 | HD-03 90% 3D MODEL REVIEW REPORT - ICR | 8 | 2022-11-21 | 2022-12-05 | 2023-02-02 | 2023-02-13 | 51
0 | EDHDPI3145 | HD-03 90% 3D MODEL REVIEW REPORT - IFA | 9 | 2022-12-19 | 2022-12-30 | 2023-02-28 | 2023-03-10 | 51
0 | EDHDPI3150 | HD-03 90% 3D MODEL REVIEW REPORT - IFC | 3 | 2023-01-16 | 2023-01-19 | 2023-03-27 | 2023-03-29 | 50
3D MODEL DEVELOPMENT |  |  | 200 | 2022-04-04 | 2023-01-19 | 2022-06-16 | 2023-03-29 | 50
0 | EDHDPI3000 | HD-03 3D MODEL DEVELOPMENT - PIPING | 200 | 2022-04-04 | 2023-01-19 | 2022-06-16 | 2023-03-29 | 50
DOCUMENTS |  |  | 201 | 2022-03-29 | 2023-01-16 | 2022-10-13 | 2023-04-14 | 65
REPORTS & CALCULATIONS |  |  | 201 | 2022-03-29 | 2023-01-16 | 2022-10-13 | 2023-04-14 | 65
0 | EDHDPI1000 | HAIR DALMA HD-03 WELLHEAD PLATFORM PIPE STRESS CRITICAL LINE LIST - ICR | 15 | 2022-03-29 | 2022-04-19 | 2022-11-02 | 2022-11-22 | 150
0 | EDHDPI1005 | HAIR DALMA HD-03 WELLHEAD PLATFORM PIPE STRESS CRITICAL LINE LIST - IFA | 15 | 2022-05-06 | 2022-05-27 | 2022-12-09 | 2022-12-29 | 150
0 | EDHDPI1015 | HAIR DALMA HD-03 WELLHEAD PLATFORM PIPING STRESS ANALYSIS REPORT - ICR | 15 | 2022-05-30 | 2022-06-20 | 2022-12-20 | 2023-01-09 | 141
0 | EDHDPI1010 | HAIR DALMA HD-03 WELLHEAD PLATFORM PIPE STRESS CRITICAL LINE LIST - IFC | 20 | 2022-06-10 | 2022-07-13 | 2023-01-13 | 2023-02-09 | 150
0 | EDHDPI1030 | HD-03 MECHANICAL HANDLING STUDY REPORT - ICR | 10 | 2022-08-08 | 2022-08-22 | 2022-10-13 | 2022-10-26 | 48
0 | EDHDPI1035 | HD-03 MECHANICAL HANDLING STUDY REPORT - IFA | 10 | 2022-09-05 | 2022-09-19 | 2023-02-07 | 2023-02-20 | 109
0 | EDHDPI1020 | HAIR DALMA HD-03 WELLHEAD PLATFORM PIPING STRESS ANALYSIS REPORT - IFA | 15 | 2022-08-31 | 2022-09-21 | 2023-01-10 | 2023-01-30 | 92
0 | EDHDPI1040 | HD-03 MECHANICAL HANDLING STUDY REPORT - IFC | 8 | 2022-11-21 | 2022-12-05 | 2023-03-20 | 2023-03-29 | 83
0 | EDHDPI1050 | HD-03 PIPE SUPPORT SCHEDULE - IFI | 10 | 2022-12-07 | 2022-12-21 | 2023-03-08 | 2023-03-21 | 65
0 | EDHDPI1025 | HAIR DALMA HD-03 WELLHEAD PLATFORM PIPING STRESS ANALYSIS REPORT - IFC | 20 | 2022-11-30 | 2022-12-30 | 2023-02-10 | 2023-03-09 | 50
0 | EDHDPI1060 | HD-03 PIPE SUPPORT SCHEDULE - IFC | 8 | 2023-01-04 | 2023-01-16 | 2023-04-05 | 2023-04-14 | 65
DRAWINGS |  |  | 216 | 2022-03-11 | 2023-01-19 | 2022-05-25 | 2023-04-27 | 69
0 | EDHGPI1000 | HAIR DALMA HD-03 WELLHEAD PLATFORM PLOT PLAN DRAWINGS - ICR | 30 | 2022-03-11 | 2022-04-22 | 2022-05-25 | 2022-07-05 | 50
0 | EDHGPI1005 | HAIR DALMA HD-03 WELLHEAD PLATFORM PLOT PLAN DRAWINGS - IFA | 22 | 2022-05-16 | 2022-06-15 | 2022-08-23 | 2022-09-21 | 68
0 | EDHGPI1035 | HD-03 SPECIAL SUPPORT DRAWINGS - ICR | 10 | 2022-11-21 | 2022-12-07 | 2023-02-17 | 2023-03-02 | 62
0 | EDHGPI1010 | HAIR DALMA HD-03 WELLHEAD PLATFORM PLOT PLAN DRAWINGS - IFC | 17 | 2022-11-21 | 2022-12-16 | 2023-03-27 | 2023-04-18 | 88
0 | EDHGPI1015 | HAIR DALMA HD-03 WELLHEAD PLATFORM ENGINEERING ISOMETRICS | 17 | 2022-11-22 | 2022-12-19 | 2023-02-08 | 2023-03-02 | 54
0 | EDHGPI1020 | HAIR DALMA HD-03 WELLHEAD PLATFORM PIPING GA DRAWING - IFI | 10 | 2022-12-08 | 2022-12-22 | 2023-03-22 | 2023-04-04 | 74
0 | EDHGPI1040 | HD-03 SPECIAL SUPPORT DRAWINGS - IFA | 7 | 2022-12-21 | 2022-12-30 | 2023-03-17 | 2023-03-27 | 62
0 | EDHGPI1025 | HAIR DALMA HD-03 WELLHEAD PLATFORM PIPING GA DRAWING - IFC | 5 | 2023-01-05 | 2023-01-12 | 2023-04-19 | 2023-04-27 | 74
0 | EDHGPI1045 | HD-03 SPECIAL SUPPORT DRAWINGS - IFC | 4 | 2023-01-13 | 2023-01-19 | 2023-04-11 | 2023-04-14 | 62
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDHGPI2000 | HD-03 PIPING MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDHGPI2005 | HD-03 PIPING MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDHGPI2010 | HD-03 PIPING MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
MECHANICAL (STATIC / ROTATING) |  |  | 209 | 2022-03-10 | 2023-01-09 | 2022-05-19 | 2023-04-27 | 77
STATIC |  |  | 209 | 2022-03-10 | 2023-01-09 | 2022-05-19 | 2023-04-27 | 77
DOCUMENTS |  |  | 117 | 2022-03-10 | 2022-08-30 | 2022-05-19 | 2022-12-12 | 73
CALCULATION |  |  | 70 | 2022-05-19 | 2022-08-30 | 2022-08-04 | 2022-12-12 | 73
0 | EDHDME1000 | HD-03 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (HD303-V-001) - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-08-04 | 2022-08-31 | 52
0 | EDHDME1005 | HD-03 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (HD303-V-001) - IFA | 20 | 2022-06-30 | 2022-08-02 | 2022-10-14 | 2022-11-10 | 73
0 | EDHDME1010 | HD-03 MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (HD303-V-001) - IFC | 10 | 2022-08-16 | 2022-08-30 | 2022-11-25 | 2022-12-12 | 73
DATA SHEET |  |  | 78 | 2022-03-10 | 2022-07-01 | 2022-05-19 | 2022-11-10 | 92
0 | EDHDME1015 | HD-03 MECHANICAL DATA SHEET FOR PIG LAUNCHER (HD303-PL-001) - ICR | 10 | 2022-03-10 | 2022-03-24 | 2022-05-19 | 2022-06-01 | 47
0 | EDHDME1030 | HD-03 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (HD303-V-001) - ICR | 15 | 2022-03-29 | 2022-04-19 | 2022-06-21 | 2022-07-14 | 57
0 | EDHDME1020 | HD-03 MECHANICAL DATA SHEET FOR PIG LAUNCHER (HD303-PL-001) - IFA | 10 | 2022-04-07 | 2022-04-21 | 2022-06-16 | 2022-06-29 | 47
0 | EDHDME1025 | HD-03 MECHANICAL DATA SHEET FOR PIG LAUNCHER (HD303-PL-001) - IFC | 7 | 2022-05-10 | 2022-05-19 | 2022-07-19 | 2022-07-27 | 47
0 | EDHDME1035 | HD-03 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (HD303-V-001) - IFA | 10 | 2022-05-06 | 2022-05-20 | 2022-09-16 | 2022-09-29 | 92
0 | EDHDME1040 | HD-03 MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (HD303-V-001) - IFC | 20 | 2022-06-03 | 2022-07-01 | 2022-10-14 | 2022-11-10 | 92
DRAWINGS |  |  | 80 | 2022-06-23 | 2022-10-18 | 2022-09-08 | 2023-01-27 | 72
0 | EDHGME1000 | HD-03 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.HD303-V-001) - ICR | 10 | 2022-06-23 | 2022-07-07 | 2022-09-08 | 2022-09-21 | 52
0 | EDHGME1015 | HD-03 DETAIL DRAWING VENT DRAIN DRUM (HD303-V-001) - IFI | 10 | 2022-07-26 | 2022-08-09 | 2022-10-06 | 2022-10-19 | 52
0 | EDHGME1005 | HD-03 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.HD303-V-001) - IFA | 10 | 2022-07-26 | 2022-08-09 | 2022-10-06 | 2022-10-19 | 52
0 | EDHGME1045 | HD-03 NOZZLE DETAIL (TAG NO. HD303-V-001) - IFI | 10 | 2022-08-01 | 2022-08-15 | 2022-10-19 | 2022-11-01 | 57
0 | EDHGME1030 | HD-03 WELDING DETAIL & WELD MAP (TAG NO. HD303-V-001) - IFI | 10 | 2022-08-05 | 2022-08-19 | 2022-10-25 | 2022-11-07 | 57
0 | EDHGME1060 | HD-03 MANWAY DAVIT DETAIL (TAG NO. HD303-V-001) - IFI | 9 | 2022-08-11 | 2022-08-24 | 2022-10-31 | 2022-11-10 | 57
0 | EDHGME1075 | HD-03 INTERNAL / EXTERNAL ATTACHMENTS (TAG NO. HD303-V-001) - IFI | 10 | 2022-08-17 | 2022-08-31 | 2022-11-04 | 2022-11-17 | 57
0 | EDHGME1090 | HD-03 NAME PLATE DETAIL (TAG NO. HD303-V-001) - IFI | 10 | 2022-08-23 | 2022-09-06 | 2022-12-05 | 2022-12-16 | 72
0 | EDHGME1025 | HD-03 DETAIL DRAWING FOR VENT DRAIN DRUM (HD303-V-001) - IFC | 15 | 2022-08-23 | 2022-09-13 | 2022-12-06 | 2022-12-26 | 73
0 | EDHGME1010 | HD-03 G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.HD303-V-001) - IFC | 20 | 2022-08-23 | 2022-09-20 | 2022-11-22 | 2022-12-21 | 65
0 | EDHGME1055 | HD-03 NOZZLE DETAIL (TAG NO. HD303-V-001) - IFC | 20 | 2022-08-29 | 2022-09-26 | 2022-12-15 | 2023-01-11 | 76
0 | EDHGME1040 | HD-03 WELDING DETAIL & WELD MAP (TAG NO. HD303-V-001) - IFC | 20 | 2022-09-02 | 2022-09-30 | 2022-12-15 | 2023-01-11 | 72
0 | EDHGME1070 | HD-03 MANWAY DAVIT DETAIL (TAG NO. HD303-V-001) - IFC | 19 | 2022-09-07 | 2022-10-04 | 2022-12-16 | 2023-01-11 | 70
0 | EDHGME1085 | HD-03 INTERNAL / EXTERNAL ATTACHMENTS (TAG NO. HD303-V-001) - IFC | 20 | 2022-09-14 | 2022-10-12 | 2022-12-06 | 2023-01-02 | 57
0 | EDHGME1100 | HD-03 NAME PLATE DETAIL (TAG NO. HD303-V-001) - IFC | 20 | 2022-09-20 | 2022-10-18 | 2023-01-02 | 2023-01-27 | 72
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDHGME2000 | HD-03 MECHANICAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDHGME2005 | HD-03 MECHANICAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDHGME2010 | HD-03 MECHANICAL MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
PACKAGE EQUIPMENT |  |  | 47 | 2022-03-24 | 2022-06-02 | 2022-06-30 | 2022-09-07 | 67
DOCUMENTS |  |  | 47 | 2022-03-24 | 2022-06-02 | 2022-06-30 | 2022-09-07 | 67
DATASHEETS |  |  | 47 | 2022-03-24 | 2022-06-02 | 2022-06-30 | 2022-09-07 | 67
0 | EDHDME1045 | HD-03 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - ICR | 9 | 2022-03-24 | 2022-04-06 | 2022-06-30 | 2022-07-15 | 67
0 | EDHDME1050 | HD-03 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - IFA | 9 | 2022-04-20 | 2022-05-06 | 2022-08-01 | 2022-08-11 | 67
0 | EDHDME1055 | HD-03 MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - IFC | 9 | 2022-05-20 | 2022-06-02 | 2022-08-26 | 2022-09-07 | 67
ELECTRICAL |  |  | 191 | 2022-04-15 | 2023-01-19 | 2022-07-06 | 2023-04-27 | 69
3D MODEL DEVELOPMENT |  |  | 186 | 2022-04-22 | 2023-01-19 | 2022-07-06 | 2023-03-29 | 50
0 | EDHDEL3000 | HD-03 3D MODEL DEVELOPMENT - ELECTRICAL | 186 | 2022-04-22 | 2023-01-19 | 2022-07-06 | 2023-03-29 | 50
DRAWINGS |  |  | 190 | 2022-04-15 | 2023-01-18 | 2022-07-07 | 2023-04-27 | 70
DIAGRAM |  |  | 159 | 2022-04-15 | 2022-12-06 | 2022-07-07 | 2023-04-27 | 101
0 | EDHGEL1000 | HD-03 SINGLE LINE DIAGRAM – 6.6KV RMU - ICR | 15 | 2022-04-15 | 2022-05-11 | 2022-08-08 | 2022-08-26 | 75
0 | EDHGEL1002 | HD-03 ELECTRICAL EQUIPMENT LIST - ICR | 15 | 2022-04-25 | 2022-05-19 | 2022-07-07 | 2022-08-01 | 50
0 | EDHGEL1015 | HD-03 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - ICR | 15 | 2022-05-05 | 2022-05-26 | 2022-08-23 | 2022-09-12 | 75
0 | EDHGEL1003 | HD-03 ELECTRICAL LOAD LIST - ICR | 15 | 2022-05-05 | 2022-05-26 | 2022-07-21 | 2022-08-10 | 52
0 | EDHGEL1030 | HD-03 SINGLE LINE DIAGRAM – 24V DC UPS - ICR | 12 | 2022-05-13 | 2022-05-31 | 2022-08-31 | 2022-09-15 | 75
0 | EDHGEL1045 | HD-03 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - ICR | 15 | 2022-05-17 | 2022-06-07 | 2022-09-02 | 2022-09-22 | 75
0 | EDHGEL1005 | HD-03 SINGLE LINE DIAGRAM – 6.6KV RMU - IFA | 10 | 2022-05-25 | 2022-06-08 | 2022-10-03 | 2022-10-14 | 90
0 | EDHGEL1060 | HD-03 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - ICR | 15 | 2022-05-24 | 2022-06-14 | 2022-09-09 | 2022-09-29 | 75
0 | EDHGEL1075 | HD-03 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - ICR | 15 | 2022-05-31 | 2022-06-21 | 2022-09-19 | 2022-10-07 | 76
0 | EDHGEL1020 | HD-03 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - IFA | 10 | 2022-06-09 | 2022-06-23 | 2022-10-03 | 2022-10-14 | 79
0 | EDHGEL1006 | HD-03 ELECTRICAL EQUIPMENT LIST - IFA | 15 | 2022-06-02 | 2022-06-23 | 2022-09-01 | 2022-09-21 | 62
0 | EDHGEL1035 | HD-03 SINGLE LINE DIAGRAM – 24V DC UPS - IFA | 10 | 2022-06-14 | 2022-06-28 | 2022-10-03 | 2022-10-14 | 76
0 | EDHGEL1009 | HD-T4 ELECTRICAL LOAD LIST - IFA | 15 | 2022-06-09 | 2022-06-30 | 2022-09-08 | 2022-09-28 | 62
0 | EDHGEL1050 | HD-03 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - IFA | 10 | 2022-06-21 | 2022-07-05 | 2022-10-10 | 2022-10-21 | 76
0 | EDHGEL1065 | HD-03 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - IFA | 10 | 2022-06-28 | 2022-07-15 | 2022-10-14 | 2022-10-27 | 75
0 | EDHGEL1010 | HD-03 SINGLE LINE DIAGRAM – 6.6KV RMU - IFC | 15 | 2022-06-22 | 2022-07-18 | 2022-10-31 | 2022-11-18 | 90
0 | EDHGEL1080 | HD-03 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - IFA | 10 | 2022-07-05 | 2022-07-22 | 2022-10-24 | 2022-11-04 | 76
0 | EDHGEL1025 | HD-03 SINGLE LINE DIAGRAM – 415V SWITCHBOARD - IFC | 15 | 2022-07-07 | 2022-08-02 | 2022-10-31 | 2022-11-18 | 79
0 | EDHGEL1040 | HD-03 SINGLE LINE DIAGRAM – 24V DC UPS - IFC | 15 | 2022-07-15 | 2022-08-05 | 2022-10-31 | 2022-11-18 | 76
0 | EDHGEL1055 | HD-03 SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - IFC | 10 | 2022-07-22 | 2022-08-05 | 2022-11-07 | 2022-11-18 | 76
0 | EDHGEL1004 | HD-03 ELECTRICAL EQUIPMENT LIST - IFC | 20 | 2022-07-07 | 2022-08-09 | 2022-10-06 | 2022-11-02 | 62
0 | EDHGEL1070 | HD-03 SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - IFC | 11 | 2022-07-29 | 2022-08-15 | 2022-11-11 | 2022-11-25 | 75
0 | EDHGEL1007 | HD-03 ELECTRICAL LOAD LIST - IFC | 20 | 2022-07-19 | 2022-08-16 | 2022-10-13 | 2022-11-09 | 62
0 | EDHGEL1085 | HD-03 SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - IFC | 10 | 2022-08-05 | 2022-08-19 | 2022-11-21 | 2022-12-06 | 76
0 | EDHGEL1090 | HD-03 ELECTRICAL CABLE SCHEDULE - ICR | 15 | 2022-08-11 | 2022-09-01 | 2023-01-04 | 2023-01-24 | 102
0 | EDHGEL1105 | HD-03 ELECTRICAL INTERCONNECTION DIAGRAM - ICR | 15 | 2022-09-02 | 2022-09-23 | 2023-01-25 | 2023-02-14 | 101
0 | EDHGEL1095 | HD-03 ELECTRICAL CABLE SCHEDULE - IFA | 10 | 2022-09-15 | 2022-09-29 | 2023-03-08 | 2023-03-21 | 122
0 | EDHGEL2020 | HD-03 ELECTRICAL INTERCONNECTION DIAGRAM - IFA | 15 | 2022-10-07 | 2022-10-28 | 2023-03-01 | 2023-03-21 | 101
0 | EDHGEL1100 | HD-03 ELECTRICAL CABLE SCHEDULE - IFC | 15 | 2022-10-13 | 2022-11-03 | 2023-04-05 | 2023-04-27 | 122
0 | EDHGEL1110 | HD-03 ELECTRICAL INTERCONNECTION DIAGRAM - IFC | 15 | 2022-11-11 | 2022-12-06 | 2023-04-05 | 2023-04-27 | 101
BOOKLET |  |  | 50 | 2022-11-07 | 2023-01-18 | 2023-02-15 | 2023-04-27 | 70
0 | EDHGEL1200 | HD-03 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - ICR | 10 | 2022-11-07 | 2022-11-21 | 2023-02-15 | 2023-02-28 | 70
0 | EDHGEL2030 | HD-03 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - IFA | 10 | 2022-12-07 | 2022-12-21 | 2023-03-15 | 2023-03-28 | 70
0 | EDHGEL1205 | HD-03 LIGHTING AND SMALL POWER CIRCUIT BOOKLET - IFC | 10 | 2023-01-04 | 2023-01-18 | 2023-04-12 | 2023-04-27 | 70
LAYOUT |  |  | 135 | 2022-05-05 | 2022-11-15 | 2022-11-21 | 2023-04-27 | 114
0 | EDHGEL1300 | HD-03 ELECTRICAL EQUIPMENT LAYOUT - ICR | 15 | 2022-05-05 | 2022-05-26 | 2023-01-18 | 2023-02-07 | 179
0 | EDHGEL1305 | HD-03 ELECTRICAL EQUIPMENT LAYOUT - IFA | 10 | 2022-06-09 | 2022-06-23 | 2023-02-22 | 2023-03-07 | 179
0 | EDHGEL1315 | HD-03 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IRC | 10 | 2022-08-08 | 2022-08-22 | 2022-11-21 | 2022-12-06 | 75
0 | EDHGEL1375 | HD-03 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - ICR | 10 | 2022-08-09 | 2022-08-23 | 2023-01-06 | 2023-01-19 | 106
0 | EDHGEL1390 | HD-03 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - ICR | 10 | 2022-08-09 | 2022-08-23 | 2023-02-03 | 2023-02-16 | 126
0 | EDHGEL1330 | HD-03 ELECTRICAL CABLE ROUTING LAYOUT - IRC | 15 | 2022-08-08 | 2022-08-29 | 2022-11-21 | 2022-12-13 | 75
0 | EDHGEL1345 | HD-03 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IRC | 15 | 2022-08-15 | 2022-09-05 | 2022-11-28 | 2022-12-20 | 75
0 | EDHGEL1360 | HD-03 EARTHING & LIGHTNING PROTECTION LAYOUT - IRC | 15 | 2022-08-16 | 2022-09-06 | 2023-01-13 | 2023-02-02 | 106
0 | EDHGEL1310 | HD-03 ELECTRICAL EQUIPMENT LAYOUT - IFC | 15 | 2022-08-22 | 2022-09-12 | 2023-03-22 | 2023-04-11 | 150
0 | EDHGEL2040 | HD-03 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IFA | 10 | 2022-09-05 | 2022-09-19 | 2023-03-03 | 2023-03-16 | 127
0 | EDHGEL1395 | HD-03 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - IFA | 10 | 2022-09-06 | 2022-09-20 | 2023-03-03 | 2023-03-16 | 126
0 | EDHGEL1380 | HD-03 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - IFA | 10 | 2022-09-06 | 2022-09-20 | 2023-02-17 | 2023-03-02 | 116
0 | EDHGEL2050 | HD-03 ELECTRICAL CABLE ROUTING LAYOUT - IFA | 15 | 2022-09-12 | 2022-10-03 | 2023-03-01 | 2023-03-21 | 120
0 | EDHGEL2060 | HD-03 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IFA | 10 | 2022-09-19 | 2022-10-03 | 2023-01-04 | 2023-01-17 | 75
0 | EDHGEL2070 | HD-03 EARTHING & LIGHTNING PROTECTION LAYOUT - IFA | 15 | 2022-09-20 | 2022-10-11 | 2023-02-17 | 2023-03-09 | 106
0 | EDHGEL1385 | HD-03 HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - IFC | 10 | 2022-10-04 | 2022-10-18 | 2023-03-17 | 2023-03-30 | 116
0 | EDHGEL1400 | HD-03 HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - IFC | 10 | 2022-10-04 | 2022-10-18 | 2023-03-31 | 2023-04-13 | 126
0 | EDHGEL1325 | HD-03 ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IFC | 10 | 2022-10-21 | 2022-11-04 | 2023-03-31 | 2023-04-13 | 113
0 | EDHGEL1355 | HD-03 LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IFC | 15 | 2022-10-17 | 2022-11-07 | 2023-02-01 | 2023-02-21 | 75
0 | EDHGEL1340 | HD-03 ELECTRICAL CABLE ROUTING LAYOUT - IFC | 15 | 2022-10-18 | 2022-11-08 | 2023-04-05 | 2023-04-27 | 119
0 | EDHGEL1370 | HD-03 EARTHING & LIGHTNING PROTECTION LAYOUT - IFC | 15 | 2022-10-25 | 2022-11-15 | 2023-03-24 | 2023-04-13 | 106
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDHGEL2000 | HD-03 ELECTRICAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDHGEL2005 | HD-03 ELECTRICAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDHGEL2010 | HD-03 ELECTRICAL MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
INSTRUMENTATION & CONTROL |  |  | 221 | 2022-03-03 | 2023-01-18 | 2022-06-02 | 2023-05-29 | 92
3D MODEL DEVELOPMENT |  |  | 180 | 2022-04-29 | 2023-01-18 | 2022-07-19 | 2023-03-29 | 51
0 | EDHDIN3000 | HD-03 3D MODEL DEVELOPMENT - INSTRUMENTATION | 180 | 2022-04-29 | 2023-01-18 | 2022-07-19 | 2023-03-29 | 51
DOCUMENTS |  |  | 218 | 2022-03-03 | 2023-01-13 | 2022-06-02 | 2023-04-27 | 73
CALCULATIONS |  |  | 76 | 2022-03-29 | 2022-07-21 | 2022-06-06 | 2023-02-27 | 156
0 | EDHDIN1000 | HD-03 CALCULATION NOTE FOR CHOKE VALVES - ICR | 15 | 2022-03-29 | 2022-04-19 | 2022-06-06 | 2022-06-24 | 46
0 | EDHDIN1030 | HD-03 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - ICR | 15 | 2022-04-04 | 2022-04-25 | 2022-08-26 | 2022-09-15 | 98
0 | EDHDIN1045 | HD-03 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - ICR | 15 | 2022-04-13 | 2022-05-09 | 2022-11-25 | 2022-12-19 | 156
0 | EDHDIN1015 | HD-03 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - ICR | 15 | 2022-04-21 | 2022-05-17 | 2022-09-08 | 2022-09-28 | 94
0 | EDHDIN1005 | HD-03 CALCULATION NOTE FOR CHOKE VALVES - IFA | 15 | 2022-05-06 | 2022-05-27 | 2022-07-14 | 2022-08-03 | 46
0 | EDHDIN1035 | HD-03 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - IFA | 15 | 2022-05-12 | 2022-06-02 | 2022-09-30 | 2022-10-20 | 98
0 | EDHDIN1050 | HD-03 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - IFA | 15 | 2022-05-23 | 2022-06-13 | 2023-01-03 | 2023-01-23 | 156
0 | EDHDIN1020 | HD-03 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - IFA | 10 | 2022-05-31 | 2022-06-14 | 2022-10-13 | 2022-10-26 | 94
0 | EDHDIN1010 | HD-03 CALCULATION NOTE FOR CHOKE VALVES - IFC | 15 | 2022-06-10 | 2022-07-01 | 2022-08-18 | 2022-09-07 | 46
0 | EDHDIN1040 | HD-03 CALCULATION NOTE FOR PRESSURE RELIEF VALVES - IFC | 15 | 2022-06-16 | 2022-07-07 | 2022-11-04 | 2022-11-24 | 98
0 | EDHDIN1025 | HD-03 CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - IFC | 10 | 2022-06-28 | 2022-07-15 | 2022-11-10 | 2022-11-23 | 94
0 | EDHDIN1055 | HD-03 THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - IFC | 15 | 2022-06-27 | 2022-07-21 | 2023-02-07 | 2023-02-27 | 156
INDEX / NARRATIVE |  |  | 50 | 2022-08-31 | 2022-11-09 | 2022-11-11 | 2023-01-24 | 53
0 | EDHDIN1060 | HD-03 INSTRUMENT INDEX - ICR | 10 | 2022-08-31 | 2022-09-14 | 2022-11-11 | 2022-11-24 | 52
0 | EDHDIN1075 | HD-03 FIRE & GAS INDEX - ICR | 10 | 2022-08-31 | 2022-09-14 | 2022-11-11 | 2022-11-24 | 52
0 | EDHDIN1065 | HD-03 INSTRUMENT INDEX - IFA | 10 | 2022-09-28 | 2022-10-12 | 2022-12-14 | 2022-12-27 | 53
0 | EDHDIN1080 | HD-03 FIRE & GAS INDEX - IFA | 10 | 2022-09-28 | 2022-10-12 | 2022-12-13 | 2022-12-26 | 52
0 | EDHDIN1070 | HD-03 INSTRUMENT INDEX - IFC | 10 | 2022-10-26 | 2022-11-09 | 2023-01-11 | 2023-01-24 | 53
0 | EDHDIN1085 | HD-03 FIRE & GAS INDEX - IFC | 10 | 2022-10-26 | 2022-11-09 | 2023-01-10 | 2023-01-23 | 52
DATA SHEET |  |  | 98 | 2022-03-03 | 2022-07-27 | 2022-06-02 | 2023-01-25 | 129
0 | EDHDIN1100 | HD-03 DATASHEETS FOR HIPPS VALVES - ICR | 11 | 2022-03-03 | 2022-03-18 | 2022-06-10 | 2022-06-24 | 68
0 | EDHDIN1175 | HD-03 DATASHEETS FOR PRESSURE RELIEF VALVES - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-09-14 | 2022-09-27 | 116
0 | EDHDIN1190 | HD-03 DATASHEETS FOR FLOW CHOKE VALVE - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-06-02 | 2022-06-15 | 45
0 | EDHDIN1205 | HD-03 DATASHEETS FOR SOLENOID OPERATED VALVES - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-06-02 | 2022-06-15 | 45
0 | EDHDIN1130 | HD-03 DATASHEETS FOR CHOKE VALVES - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-06-06 | 2022-06-17 | 46
0 | EDHDIN1160 | HD-03 DATASHEETS FOR MOV - ICR | 10 | 2022-03-29 | 2022-04-12 | 2022-06-06 | 2022-06-17 | 46
0 | EDHDIN1400 | HD-03 DATASHEETS FOR ELECTRONIC SOUNDER - ICR | 9 | 2022-03-31 | 2022-04-13 | 2022-10-17 | 2022-10-27 | 136
0 | EDHDIN1220 | HD-03 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-06-07 | 2022-06-20 | 45
0 | EDHDIN1145 | HD-03 DATASHEETS FOR ACTUATED ON/OFF VALVES - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-06-06 | 2022-06-17 | 44
0 | EDHDIN1105 | HD-03 DATASHEETS FOR HIPPS VALVES - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-07-14 | 2022-07-27 | 68
0 | EDHDIN1415 | HD-03 DATASHEETS FOR EMERGENCY S/D PB - ICR | 10 | 2022-04-04 | 2022-04-18 | 2022-10-19 | 2022-11-01 | 136
0 | EDHDIN1430 | HD-03 DATASHEETS FOR FLAMMABLE GAS DETECTOR - ICR | 10 | 2022-04-06 | 2022-04-20 | 2022-10-21 | 2022-11-03 | 136
0 | EDHDIN1250 | HD-03 DATASHEETS FOR PRESSURE GAUGES - ICR | 10 | 2022-04-08 | 2022-04-22 | 2022-09-20 | 2022-10-03 | 111
0 | EDHDIN1295 | HD-03 DATASHEETS FOR TEMPERATURE GAUGES - ICR | 10 | 2022-04-08 | 2022-04-22 | 2022-09-16 | 2022-09-29 | 109
0 | EDHDIN1445 | HD-03 DATASHEETS FOR FIRE GAS DETECTOR - ICR | 10 | 2022-04-08 | 2022-04-22 | 2022-10-25 | 2022-11-07 | 136
0 | EDHDIN1280 | HD-03 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - ICR | 10 | 2022-04-11 | 2022-04-25 | 2022-09-01 | 2022-09-14 | 97
0 | EDHDIN1355 | HD-03 DATASHEETS FOR LEVEL TRANSMITTERS - ICR | 7 | 2022-04-15 | 2022-04-26 | 2022-09-20 | 2022-09-28 | 106
0 | EDHDIN1115 | HD-03 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-06-20 | 2022-07-01 | 46
0 | EDHDIN1460 | HD-03 DATASHEETS FOR FLASHING BEACON - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-10-27 | 2022-11-09 | 136
0 | EDHDIN1490 | HD-03 DATASHEETS FOR MAN ON BOARD PB - ICR | 9 | 2022-04-14 | 2022-04-27 | 2022-11-02 | 2022-11-14 | 138
0 | EDHDIN1310 | HD-03 DATASHEETS FOR TEMPERATURE TRANSMITTERS - ICR | 10 | 2022-04-13 | 2022-04-27 | 2022-09-08 | 2022-09-21 | 100
0 | EDHDIN1475 | HD-03 DATASHEETS FOR HEAT DETECTOR - ICR | 10 | 2022-04-14 | 2022-04-28 | 2022-10-31 | 2022-11-11 | 136
0 | EDHDIN1340 | HD-03 DATASHEETS FOR LEVEL GAUGES - ICR | 10 | 2022-04-15 | 2022-04-29 | 2022-09-14 | 2022-09-27 | 102
0 | EDHDIN1520 | HD-03 DATASHEETS FOR MANUAL ALARM CALL POINT - ICR | 10 | 2022-04-19 | 2022-05-06 | 2022-11-07 | 2022-11-18 | 138
0 | EDHDIN1370 | HD-03 DATASHEETS FOR FLOW SWITCHES - ICR | 10 | 2022-04-21 | 2022-05-10 | 2022-10-12 | 2022-10-25 | 118
0 | EDHDIN1110 | HD-03 DATASHEETS FOR HIPPS VALVES - IFC | 15 | 2022-04-15 | 2022-05-11 | 2022-08-08 | 2022-08-26 | 75
0 | EDHDIN1195 | HD-03 DATASHEETS FOR FLOW CHOKE VALVE - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-07-04 | 2022-07-20 | 47
0 | EDHDIN1180 | HD-03 DATASHEETS FOR PRESSURE RELIEF VALVES - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-10-12 | 2022-10-25 | 116
0 | EDHDIN1210 | HD-03 DATASHEETS FOR SOLENOID OPERATED VALVES - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-07-21 | 2022-08-03 | 57
0 | EDHDIN1385 | HD-03 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - ICR | 10 | 2022-04-26 | 2022-05-13 | 2022-10-17 | 2022-10-28 | 118
0 | EDHDIN1135 | HD-03 DATASHEETS FOR CHOKE VALVES - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-07-04 | 2022-07-20 | 46
0 | EDHDIN1405 | HD-03 DATASHEETS FOR ELECTRONIC SOUNDER - IFA | 9 | 2022-04-27 | 2022-05-13 | 2022-11-16 | 2022-11-28 | 139
0 | EDHDIN1165 | HD-03 DATASHEETS FOR MOV - IFA | 10 | 2022-04-26 | 2022-05-13 | 2022-07-04 | 2022-07-20 | 46
0 | EDHDIN1325 | HD-03 DATASHEETS FOR PIG SIGNALLER - ICR | 10 | 2022-04-27 | 2022-05-16 | 2022-10-26 | 2022-11-08 | 124
0 | EDHDIN1150 | HD-03 DATASHEETS FOR ACTUATED ON/OFF VALVES - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-07-04 | 2022-07-20 | 44
0 | EDHDIN1225 | HD-03 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-07-21 | 2022-08-03 | 54
0 | EDHDIN1420 | HD-03 DATASHEETS FOR EMERGENCY S/D PB - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-11-28 | 2022-12-13 | 144
0 | EDHDIN1265 | HD-03 DATASHEETS FOR CORROSION MONITOR - ICR | 10 | 2022-05-06 | 2022-05-20 | 2022-10-04 | 2022-10-17 | 104
0 | EDHDIN1435 | HD-03 DATASHEETS FOR FLAMMABLE GAS DETECTOR - IFA | 10 | 2022-05-09 | 2022-05-23 | 2022-11-28 | 2022-12-13 | 142
0 | EDHDIN1235 | HD-03 DATASHEETS FOR FLOW RESTRICTION ORIFICE - ICR | 10 | 2022-05-10 | 2022-05-24 | 2022-09-15 | 2022-09-28 | 89
0 | EDHDIN1360 | HD-03 DATASHEETS FOR LEVEL TRANSMITTERS - IFA | 7 | 2022-05-13 | 2022-05-24 | 2022-10-13 | 2022-10-21 | 106
0 | EDHDIN1450 | HD-03 DATASHEETS FOR FIRE GAS DETECTOR - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-11-28 | 2022-12-13 | 140
0 | EDHDIN1255 | HD-03 DATASHEETS FOR PRESSURE GAUGES - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-10-18 | 2022-10-31 | 111
0 | EDHDIN1300 | HD-03 DATASHEETS FOR TEMPERATURE GAUGES - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-10-14 | 2022-10-27 | 109
0 | EDHDIN1285 | HD-03 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - IFA | 10 | 2022-05-12 | 2022-05-26 | 2022-09-29 | 2022-10-12 | 97
0 | EDHDIN1120 | HD-03 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-07-21 | 2022-08-03 | 46
0 | EDHDIN1465 | HD-03 DATASHEETS FOR FLASHING BEACON - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-11-28 | 2022-12-13 | 138
0 | EDHDIN1495 | HD-03 DATASHEETS FOR MAN ON BOARD PB - IFA | 9 | 2022-05-16 | 2022-05-27 | 2022-11-30 | 2022-12-14 | 139
0 | EDHDIN1315 | HD-03 DATASHEETS FOR TEMPERATURE TRANSMITTERS - IFA | 10 | 2022-05-16 | 2022-05-30 | 2022-10-06 | 2022-10-19 | 100
0 | EDHDIN1480 | HD-03 DATASHEETS FOR HEAT DETECTOR - IFA | 10 | 2022-05-17 | 2022-05-31 | 2022-11-28 | 2022-12-13 | 136
0 | EDHDIN1345 | HD-03 DATASHEETS FOR LEVEL GAUGES - IFA | 10 | 2022-05-18 | 2022-06-01 | 2022-10-12 | 2022-10-25 | 102
0 | EDHDIN1525 | HD-03 DATASHEETS FOR MANUAL ALARM CALL POINT - IFA | 10 | 2022-05-20 | 2022-06-03 | 2022-12-07 | 2022-12-20 | 138
0 | EDHDIN1375 | HD-03 DATASHEETS FOR FLOW SWITCHES - IFA | 10 | 2022-05-24 | 2022-06-07 | 2022-12-08 | 2022-12-21 | 137
0 | EDHDIN1390 | HD-03 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - IFA | 10 | 2022-05-27 | 2022-06-10 | 2022-11-14 | 2022-11-25 | 118
0 | EDHDIN1330 | HD-03 DATASHEETS FOR PIG SIGNALLER - IFA | 10 | 2022-05-30 | 2022-06-13 | 2022-11-23 | 2022-12-08 | 124
0 | EDHDIN1365 | HD-03 DATASHEETS FOR LEVEL TRANSMITTERS - IFC | 7 | 2022-06-07 | 2022-06-16 | 2022-11-07 | 2022-11-15 | 106
0 | EDHDIN1410 | HD-03 DATASHEETS FOR ELECTRONIC SOUNDER - IFC | 14 | 2022-05-27 | 2022-06-16 | 2022-12-15 | 2023-01-03 | 139
0 | EDHDIN1200 | HD-03 DATASHEETS FOR FLOW CHOKE VALVE - IFC | 15 | 2022-05-26 | 2022-06-16 | 2022-08-04 | 2022-08-24 | 47
0 | EDHDIN1215 | HD-03 DATASHEETS FOR SOLENOID OPERATED VALVES - IFC | 15 | 2022-05-26 | 2022-06-16 | 2022-08-18 | 2022-09-07 | 57
0 | EDHDIN1140 | HD-03 DATASHEETS FOR CHOKE VALVES - IFC | 15 | 2022-05-27 | 2022-06-17 | 2022-08-04 | 2022-08-24 | 46
0 | EDHDIN1170 | HD-03 DATASHEETS FOR MOV - IFC | 15 | 2022-05-27 | 2022-06-17 | 2022-08-04 | 2022-08-24 | 46
0 | EDHDIN1270 | HD-03 DATASHEETS FOR CORROSION MONITOR - IFA | 10 | 2022-06-03 | 2022-06-17 | 2022-11-09 | 2022-11-22 | 110
0 | EDHDIN1230 | HD-03 DATASHEETS FOR FLOW METER - CORIOLIS TYPE - IFC | 15 | 2022-05-31 | 2022-06-21 | 2022-08-18 | 2022-09-07 | 54
0 | EDHDIN1155 | HD-03 DATASHEETS FOR ACTUATED ON/OFF VALVES - IFC | 15 | 2022-05-31 | 2022-06-21 | 2022-08-04 | 2022-08-24 | 44
0 | EDHDIN1240 | HD-03 DATASHEETS FOR FLOW RESTRICTION ORIFICE - IFA | 10 | 2022-06-07 | 2022-06-21 | 2022-10-13 | 2022-10-26 | 89
0 | EDHDIN1185 | HD-03 DATASHEETS FOR PRESSURE RELIEF VALVES - IFC | 15 | 2022-06-01 | 2022-06-22 | 2022-11-09 | 2022-11-29 | 112
0 | EDHDIN1425 | HD-03 DATASHEETS FOR EMERGENCY S/D PB - IFC | 15 | 2022-06-02 | 2022-06-23 | 2022-12-28 | 2023-01-17 | 144
0 | EDHDIN1440 | HD-03 DATASHEETS FOR FLAMMABLE GAS DETECTOR - IFC | 15 | 2022-06-06 | 2022-06-27 | 2022-12-28 | 2023-01-17 | 142
0 | EDHDIN1260 | HD-03 DATASHEETS FOR PRESSURE GAUGES - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-11-15 | 2022-12-07 | 111
0 | EDHDIN1305 | HD-03 DATASHEETS FOR TEMPERATURE GAUGES - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-11-11 | 2022-12-05 | 109
0 | EDHDIN1455 | HD-03 DATASHEETS FOR FIRE GAS DETECTOR - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-12-28 | 2023-01-17 | 140
0 | EDHDIN1320 | HD-03 DATASHEETS FOR TEMPERATURE TRANSMITTERS - IFC | 10 | 2022-06-15 | 2022-06-29 | 2022-11-03 | 2022-11-16 | 98
0 | EDHDIN1290 | HD-03 DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - IFC | 15 | 2022-06-09 | 2022-06-30 | 2022-10-27 | 2022-11-16 | 97
0 | EDHDIN1500 | HD-03 DATASHEETS FOR MAN ON BOARD PB - IFC | 14 | 2022-06-10 | 2022-06-30 | 2022-12-29 | 2023-01-17 | 139
0 | EDHDIN1125 | HD-03 DATASHEETS FOR WET GAS FLOW METERS (MPFM) - IFC | 15 | 2022-06-10 | 2022-07-01 | 2022-08-18 | 2022-09-07 | 46
0 | EDHDIN1530 | HD-03 DATASHEETS FOR MANUAL ALARM CALL POINT- IFC | 10 | 2022-06-17 | 2022-07-01 | 2023-01-04 | 2023-01-17 | 138
0 | EDHDIN1470 | HD-03 DATASHEETS FOR FLASHING BEACON - IFC | 15 | 2022-06-10 | 2022-07-01 | 2022-12-28 | 2023-01-17 | 138
0 | EDHDIN1485 | HD-03 DATASHEETS FOR HEAT DETECTOR - IFC | 15 | 2022-06-14 | 2022-07-05 | 2022-12-28 | 2023-01-17 | 136
0 | EDHDIN1350 | HD-03 DATASHEETS FOR LEVEL GAUGES - IFC | 15 | 2022-06-15 | 2022-07-06 | 2022-11-09 | 2022-11-29 | 102
0 | EDHDIN1380 | HD-03 DATASHEETS FOR FLOW SWITCHES - IFC | 15 | 2022-06-21 | 2022-07-15 | 2023-01-05 | 2023-01-25 | 137
0 | EDHDIN1395 | HD-03 DATASHEETS FOR ELECTRICAL RESISTANCE PROBE - IFC | 15 | 2022-06-24 | 2022-07-20 | 2022-12-14 | 2023-01-03 | 118
0 | EDHDIN1335 | HD-03 DATASHEETS FOR PIG SIGNALLER - IFC | 15 | 2022-06-27 | 2022-07-21 | 2022-12-23 | 2023-01-12 | 124
0 | EDHDIN1245 | HD-03 DATASHEETS FOR FLOW RESTRICTION ORIFICE - IFC | 10 | 2022-07-13 | 2022-07-27 | 2022-11-10 | 2022-11-23 | 86
0 | EDHDIN1275 | HD-03 DATASHEETS FOR CORROSION MONITOR - IFC | 15 | 2022-07-01 | 2022-07-27 | 2022-12-09 | 2022-12-29 | 110
SCHEDULE / MTO |  |  | 110 | 2022-06-02 | 2022-11-08 | 2022-12-22 | 2023-04-27 | 119
0 | EDHDIN1600 | HD-03 INSTRUMENT 1ST MTO | 10 | 2022-06-02 | 2022-06-16 | 2022-12-22 | 2023-01-04 | 140
0 | EDHDIN1610 | HD-03 INSTRUMENT CABLE SCHEDULE - ICR | 10 | 2022-08-22 | 2022-09-05 | 2023-01-05 | 2023-01-18 | 96
0 | EDHDIN1625 | HD-03 JUNCTION BOX SCHEDULE - ICR | 10 | 2022-08-22 | 2022-09-05 | 2023-02-15 | 2023-02-28 | 125
0 | EDHDIN1640 | HD-03 TUBE SCHEDULE - ICR | 10 | 2022-08-30 | 2022-09-13 | 2023-02-15 | 2023-02-28 | 119
0 | EDHDIN1605 | HD-03 INSTRUMENT FINAL MTO | 10 | 2022-09-05 | 2022-09-19 | 2023-01-20 | 2023-02-02 | 97
0 | EDHDIN1615 | HD-03 INSTRUMENT CABLE SCHEDULE - IFA | 10 | 2022-09-19 | 2022-10-03 | 2023-03-15 | 2023-03-28 | 125
0 | EDHDIN1630 | HD-03 JUNCTION BOX SCHEDULE - IFA | 10 | 2022-09-19 | 2022-10-03 | 2023-03-15 | 2023-03-28 | 125
0 | EDHDIN1645 | HD-03 TUBE SCHEDULE - IFA | 10 | 2022-09-27 | 2022-10-11 | 2023-03-15 | 2023-03-28 | 119
0 | EDHDIN1620 | HD-03 INSTRUMENT CABLE SCHEDULE - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-04-12 | 2023-04-27 | 125
0 | EDHDIN1635 | HD-03 JUNCTION BOX SCHEDULE - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-04-12 | 2023-04-27 | 125
0 | EDHDIN1650 | HD-03 TUBE SCHEDULE - IFC | 10 | 2022-10-25 | 2022-11-08 | 2023-04-12 | 2023-04-27 | 119
LIST |  |  | 95 | 2022-08-31 | 2023-01-13 | 2022-12-14 | 2023-04-27 | 73
0 | EDHDIN1700 | HD-03 I/O LIST FOR DCS - ICR | 20 | 2022-08-31 | 2022-09-28 | 2022-12-14 | 2023-01-10 | 73
0 | EDHDIN1715 | HD-03 I/O LIST FOR ESD SYSTEM - ICR | 20 | 2022-09-07 | 2022-10-05 | 2022-12-21 | 2023-01-17 | 73
0 | EDHDIN1730 | HD-03 I/O LIST FOR F&G SYSTEM - ICR | 20 | 2022-09-14 | 2022-10-12 | 2022-12-28 | 2023-01-24 | 73
0 | EDHDIN1745 | HD-03 I/O LIST FOR HIPPS - ICR | 20 | 2022-09-21 | 2022-10-19 | 2023-01-04 | 2023-01-31 | 73
0 | EDHDIN1705 | HD-03 I/O LIST FOR DCS - IFA | 20 | 2022-10-12 | 2022-11-09 | 2023-02-15 | 2023-03-14 | 88
0 | EDHDIN1720 | HD-03 I/O LIST FOR ESD SYSTEM - IFA | 20 | 2022-10-19 | 2022-11-16 | 2023-02-15 | 2023-03-14 | 83
0 | EDHDIN1735 | HD-03 I/O LIST FOR F&G SYSTEM - IFA | 20 | 2022-10-26 | 2022-11-23 | 2023-02-15 | 2023-03-14 | 78
0 | EDHDIN1750 | HD-03 I/O LIST FOR HIPPS - IFA | 20 | 2022-11-02 | 2022-11-30 | 2023-02-15 | 2023-03-14 | 73
0 | EDHDIN1710 | HD-03 I/O LIST FOR DCS - IFC | 20 | 2022-11-23 | 2022-12-23 | 2023-03-29 | 2023-04-27 | 88
0 | EDHDIN1725 | HD-03 I/O LIST FOR ESD SYSTEM - IFC | 20 | 2022-11-30 | 2022-12-30 | 2023-03-29 | 2023-04-27 | 83
0 | EDHDIN1740 | HD-03 I/O LIST FOR F&G SYSTEM - IFC | 20 | 2022-12-09 | 2023-01-06 | 2023-03-29 | 2023-04-27 | 78
0 | EDHDIN1755 | HD-03 I/O LIST FOR HIPPS - IFC | 20 | 2022-12-16 | 2023-01-13 | 2023-03-29 | 2023-04-27 | 73
DRAWINGS |  |  | 195 | 2022-03-31 | 2023-01-10 | 2022-08-30 | 2023-05-29 | 98
DIAGRAM |  |  | 195 | 2022-03-31 | 2023-01-10 | 2022-08-30 | 2023-05-29 | 98
0 | EDHGIN1015 | HD-03 INSTRUMENT CABLE BLOCK DIAGRAM - ICR | 15 | 2022-03-31 | 2022-04-21 | 2022-08-30 | 2022-09-19 | 102
0 | EDHGIN1000 | HD-03 LEVEL SKETCH- ICR | 12 | 2022-04-05 | 2022-04-21 | 2023-01-10 | 2023-01-25 | 192
0 | EDHGIN1030 | HD-03 TUBING BLOCK DIAGRAM - ICR | 15 | 2022-04-21 | 2022-05-17 | 2022-12-30 | 2023-01-19 | 173
0 | EDHGIN1005 | HD-03 LEVEL SKETCH- IFA | 12 | 2022-05-10 | 2022-05-26 | 2023-02-09 | 2023-02-24 | 192
0 | EDHGIN1020 | HD-03 INSTRUMENT CABLE BLOCK DIAGRAM - IFA | 15 | 2022-05-10 | 2022-05-31 | 2023-03-24 | 2023-04-13 | 223
0 | EDHGIN1035 | HD-03 TUBING BLOCK DIAGRAM - IFA | 15 | 2022-05-31 | 2022-06-21 | 2023-03-24 | 2023-04-13 | 208
0 | EDHGIN1010 | HD-03 LEVEL SKETCH- IFC | 12 | 2022-06-09 | 2022-06-27 | 2023-03-13 | 2023-03-28 | 192
0 | EDHGIN1025 | HD-03 INSTRUMENT CABLE BLOCK DIAGRAM - IFC | 20 | 2022-06-14 | 2022-07-15 | 2023-05-02 | 2023-05-29 | 223
0 | EDHGIN1040 | HD-03 TUBING BLOCK DIAGRAM - IFC | 20 | 2022-07-05 | 2022-08-05 | 2023-05-02 | 2023-05-29 | 208
0 | EDHGIN1045 | HD-03 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - ICR | 15 | 2022-08-22 | 2022-09-12 | 2023-01-05 | 2023-01-25 | 96
0 | EDHGIN1060 | HD-03 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - ICR | 15 | 2022-08-26 | 2022-09-16 | 2023-01-11 | 2023-01-31 | 96
0 | EDHGIN1075 | HD-03 PROCESS & HYDRAULIC HOOK-UPS DRAWING - ICR | 15 | 2022-09-02 | 2022-09-23 | 2023-01-18 | 2023-02-07 | 96
0 | EDHGIN1090 | HD-03 INSTRUMENT LOOP DIAGRAMS - DCS - ICR | 9 | 2022-09-23 | 2022-10-06 | 2023-01-27 | 2023-02-08 | 88
0 | EDHGIN1105 | HD-03 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - ICR | 10 | 2022-09-27 | 2022-10-11 | 2023-01-31 | 2023-02-13 | 88
0 | EDHGIN1050 | HD-03 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - IFA | 15 | 2022-09-26 | 2022-10-17 | 2023-02-22 | 2023-03-14 | 105
0 | EDHGIN1120 | HD-03 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - ICR | 10 | 2022-10-07 | 2022-10-21 | 2023-02-02 | 2023-02-15 | 82
0 | EDHGIN1065 | HD-03 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - IFA | 15 | 2022-09-30 | 2022-10-21 | 2023-02-22 | 2023-03-14 | 101
0 | EDHGIN1080 | HD-03 PROCESS & HYDRAULIC HOOK-UPS DRAWING - IFA | 15 | 2022-10-07 | 2022-10-28 | 2023-02-22 | 2023-03-14 | 96
0 | EDHGIN1095 | HD-03 INSTRUMENT LOOP DIAGRAMS - DCS - IFA | 10 | 2022-10-20 | 2022-11-03 | 2023-03-08 | 2023-03-21 | 97
0 | EDHGIN1135 | HD-03 INSTRUMENT LOOP DIAGRAMS - HIPPS - ICR | 10 | 2022-10-21 | 2022-11-04 | 2023-02-08 | 2023-02-21 | 76
0 | EDHGIN1110 | HD-03 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - IFA | 10 | 2022-10-25 | 2022-11-08 | 2023-03-08 | 2023-03-21 | 94
0 | EDHGIN1125 | HD-03 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - IFA | 10 | 2022-11-04 | 2022-11-18 | 2023-03-08 | 2023-03-21 | 86
0 | EDHGIN1055 | HD-03 INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - IFC | 20 | 2022-10-31 | 2022-11-28 | 2023-03-29 | 2023-04-27 | 105
0 | EDHGIN1070 | HD-03 INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - IFC | 20 | 2022-11-04 | 2022-12-06 | 2023-03-29 | 2023-04-27 | 101
0 | EDHGIN1140 | HD-03 INSTRUMENT LOOP DIAGRAMS - HIPPS - IFA | 10 | 2022-11-18 | 2022-12-06 | 2023-03-08 | 2023-03-21 | 76
0 | EDHGIN1100 | HD-03 INSTRUMENT LOOP DIAGRAMS - DCS - IFC | 15 | 2022-11-17 | 2022-12-12 | 2023-04-05 | 2023-04-27 | 97
0 | EDHGIN1085 | HD-03 PROCESS & HYDRAULIC HOOK-UPS DRAWING - IFC | 20 | 2022-11-11 | 2022-12-13 | 2023-03-29 | 2023-04-27 | 96
0 | EDHGIN1115 | HD-03 INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - IFC | 15 | 2022-11-22 | 2022-12-15 | 2023-04-05 | 2023-04-27 | 94
0 | EDHGIN1130 | HD-03 INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - IFC | 15 | 2022-12-06 | 2022-12-27 | 2023-04-05 | 2023-04-27 | 86
0 | EDHGIN1145 | HD-03 INSTRUMENT LOOP DIAGRAMS - HIPPS - IFC | 15 | 2022-12-20 | 2023-01-10 | 2023-04-05 | 2023-04-27 | 76
LAYOUT |  |  | 85 | 2022-07-15 | 2022-11-11 | 2022-10-19 | 2023-04-27 | 116
0 | EDHGIN1215 | HD-03 INSTRUMENT CABLE ROUTING LAYOUT - ICR | 15 | 2022-07-15 | 2022-08-05 | 2022-12-30 | 2023-01-19 | 118
0 | EDHGIN1230 | HD-03 INSTRUMENT LOCATION LAYOUTS - ICR | 15 | 2022-07-22 | 2022-08-12 | 2023-01-12 | 2023-02-01 | 122
0 | EDHGIN1245 | HD-03 TUBE ROUTING LAYOUT - ICR | 15 | 2022-07-28 | 2022-08-18 | 2023-01-18 | 2023-02-07 | 122
0 | EDHGIN1200 | HD-03 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - ICR | 15 | 2022-08-10 | 2022-08-31 | 2022-10-19 | 2022-11-08 | 50
0 | EDHGIN1220 | HD-03 INSTRUMENT CABLE ROUTING LAYOUT - IFA | 10 | 2022-08-19 | 2022-09-02 | 2023-02-03 | 2023-02-16 | 118
0 | EDHGIN1265 | HD-03 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - ICR | 15 | 2022-08-19 | 2022-09-09 | 2022-10-28 | 2022-11-17 | 50
0 | EDHGIN1235 | HD-03 INSTRUMENT LOCATION LAYOUTS - IFA | 15 | 2022-08-26 | 2022-09-16 | 2023-02-22 | 2023-03-14 | 126
0 | EDHGIN1250 | HD-03 TUBE ROUTING LAYOUT - IFA | 15 | 2022-09-01 | 2022-09-22 | 2023-02-22 | 2023-03-14 | 122
0 | EDHGIN1205 | HD-03 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - IFA | 15 | 2022-09-14 | 2022-10-05 | 2022-11-28 | 2022-12-20 | 53
0 | EDHGIN1225 | HD-03 INSTRUMENT CABLE ROUTING LAYOUT - IFC | 20 | 2022-09-16 | 2022-10-14 | 2023-03-03 | 2023-03-30 | 118
0 | EDHGIN1275 | HD-03 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - IFA | 15 | 2022-09-23 | 2022-10-14 | 2022-12-06 | 2022-12-26 | 50
0 | EDHGIN1240 | HD-03 INSTRUMENT LOCATION LAYOUTS - IFC | 20 | 2022-09-30 | 2022-10-28 | 2023-03-29 | 2023-04-27 | 126
0 | EDHGIN1255 | HD-03 TUBE ROUTING LAYOUT - IFC | 20 | 2022-10-06 | 2022-11-03 | 2023-03-29 | 2023-04-27 | 122
0 | EDHGIN1210 | HD-03 INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - IFC | 15 | 2022-10-19 | 2022-11-09 | 2023-01-04 | 2023-01-24 | 53
0 | EDHGIN1285 | HD-03 FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - IFC | 10 | 2022-10-28 | 2022-11-11 | 2023-01-10 | 2023-01-23 | 50
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-29 | 2023-01-16 | 2023-01-11 | 2023-04-27 | 72
0 | EDHGIN2000 | HD-03 INSTRUMENT MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-29 | 2022-10-27 | 2023-01-11 | 2023-02-07 | 72
0 | EDHGIN2005 | HD-03 INSTRUMENT MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-10 | 2022-12-12 | 2023-02-22 | 2023-03-21 | 72
0 | EDHGIN2010 | HD-03 INSTRUMENT MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-26 | 2023-01-16 | 2023-04-05 | 2023-04-27 | 72
TELECOM |  |  | 152 | 2022-06-02 | 2023-01-09 | 2022-09-27 | 2023-04-27 | 77
DOCUMENTS |  |  | 104 | 2022-06-02 | 2022-10-31 | 2022-09-27 | 2023-04-27 | 125
LIST/SCHEDULE |  |  | 104 | 2022-06-02 | 2022-10-31 | 2022-09-27 | 2023-04-27 | 125
0 | EDHDTE1000 | HD-03 TELECOMMUNICATION - 1ST MTO | 10 | 2022-06-02 | 2022-06-16 | 2022-09-27 | 2022-10-10 | 80
0 | EDHDTE1010 | HD-03 TELECOM EQUIPMENT LIST - ICR | 10 | 2022-06-16 | 2022-06-30 | 2022-10-11 | 2022-10-24 | 80
0 | EDHDTE1015 | HD-03 TELECOM EQUIPMENT LIST - IFA | 10 | 2022-07-19 | 2022-08-02 | 2023-03-01 | 2023-03-14 | 159
0 | EDHDTE1025 | HD-03 TELECOM CABLE SCHEDULE - ICR | 10 | 2022-08-22 | 2022-09-05 | 2023-02-01 | 2023-02-14 | 115
0 | EDHDTE1020 | HD-03 TELECOM EQUIPMENT LIST - IFC | 20 | 2022-08-16 | 2022-09-13 | 2023-03-29 | 2023-04-27 | 159
0 | EDHDTE1005 | HD-03 TELECOMMUNICATION - FINAL MTO | 10 | 2022-09-05 | 2022-09-19 | 2023-01-20 | 2023-02-02 | 97
0 | EDHDTE1030 | HD-03 TELECOM CABLE SCHEDULE - IFA | 10 | 2022-09-19 | 2022-10-03 | 2023-03-15 | 2023-03-28 | 125
0 | EDHDTE1035 | HD-03 TELECOM CABLE SCHEDULE - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-04-12 | 2023-04-27 | 125
DRAWINGS |  |  | 87 | 2022-07-19 | 2022-11-17 | 2022-11-08 | 2023-04-27 | 112
LAYOUT |  |  | 87 | 2022-07-19 | 2022-11-17 | 2022-11-08 | 2023-04-27 | 112
0 | EDHGTE1015 | HD-03 TELECOM EQUIPMENT LOCATION LAYOUTS - ICR | 10 | 2022-07-19 | 2022-08-02 | 2022-11-08 | 2022-11-21 | 80
0 | EDHGTE1000 | HD-03 TELECOM CABLE ROUTING LAYOUT - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-01-18 | 2023-01-31 | 112
0 | EDHGTE1020 | HD-03 TELECOM EQUIPMENT LOCATION LAYOUTS - IFA | 10 | 2022-08-16 | 2022-08-30 | 2022-12-08 | 2022-12-21 | 80
0 | EDHGTE1045 | HD-03 DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - ICR | 10 | 2022-08-25 | 2022-09-08 | 2023-02-01 | 2023-02-14 | 112
0 | EDHGTE1030 | HD-03 FIBER OPTIC ALLOCATION DRAWING - ICR | 10 | 2022-09-05 | 2022-09-19 | 2023-02-15 | 2023-02-28 | 115
0 | EDHGTE1005 | HD-03 TELECOM CABLE ROUTING LAYOUT - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-15 | 2023-03-28 | 132
0 | EDHGTE1025 | HD-03 TELECOM EQUIPMENT LOCATION LAYOUTS - IFC | 10 | 2022-09-13 | 2022-09-27 | 2023-01-05 | 2023-01-18 | 80
0 | EDHGTE1050 | HD-03 DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - IFA | 10 | 2022-09-22 | 2022-10-06 | 2023-03-01 | 2023-03-14 | 112
0 | EDHGTE1035 | HD-03 FIBER OPTIC ALLOCATION DRAWING - IFA | 10 | 2022-10-03 | 2022-10-17 | 2023-03-15 | 2023-03-28 | 115
0 | EDHGTE1010 | HD-03 TELECOM CABLE ROUTING LAYOUT - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-04-12 | 2023-04-27 | 132
0 | EDHGTE1040 | HD-03 FIBER OPTIC ALLOCATION DRAWING - IFC | 10 | 2022-10-31 | 2022-11-14 | 2023-04-12 | 2023-04-27 | 115
0 | EDHGTE1055 | HD-03 DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - IFC | 20 | 2022-10-20 | 2022-11-17 | 2023-03-29 | 2023-04-27 | 112
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDHGTE2000 | HD-03 TELECOM MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDHGTE2005 | HD-03 TELECOM MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDHGTE2010 | HD-03 TELECOM MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
STRUCTURAL |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-05-26 | 2023-08-29 | 153
3D MODEL DEVELOPMENT |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-05-26 | 2023-03-29 | 50
0 | EDHDSR3000 | HD-03 3D MODEL DEVELOPMENT - STRUCTURAL | 215 | 2022-03-14 | 2023-01-19 | 2022-05-26 | 2023-03-29 | 50
DOCUMENTS |  |  | 165 | 2022-05-12 | 2023-01-05 | 2022-08-11 | 2023-07-26 | 139
REPORTS |  |  | 165 | 2022-05-12 | 2023-01-05 | 2022-08-11 | 2023-07-26 | 139
0 | EDHDSR1000 | HD-03 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - ICR | 20 | 2022-05-12 | 2022-06-09 | 2022-08-11 | 2022-09-07 | 62
0 | EDHDSR1120 | HD-03 TOPSIDES LIFT ANALYSES REPORT - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-09-19 | 2022-10-14 | 84
0 | EDHDSR1180 | HD-03 TOPSIDES LINEAR BLAST ANALYSIS REPORT - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-08-19 | 2022-09-15 | 63
0 | EDHDSR1135 | HD-03 TOPSIDES LOADOUT ANALYSIS REPORT - ICR | 20 | 2022-05-26 | 2022-06-23 | 2022-12-14 | 2023-01-10 | 139
0 | EDHDSR1075 | HD-03 TOPSIDE JOINT DESIGN REPORT - ICR | 20 | 2022-05-26 | 2022-06-23 | 2022-08-26 | 2022-09-22 | 63
0 | EDHDSR1150 | HD-03 TOPSIDES TRANSPORTATION ANALYSES REPORT - ICR | 20 | 2022-06-02 | 2022-06-30 | 2022-12-21 | 2023-01-17 | 139
0 | EDHDSR1005 | HD-03 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - IFA | 15 | 2022-06-23 | 2022-07-19 | 2022-10-06 | 2022-10-26 | 72
0 | EDHDSR1090 | HD-03 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - ICR | 20 | 2022-06-16 | 2022-07-19 | 2022-10-17 | 2022-11-11 | 84
0 | EDHDSR1125 | HD-03 TOPSIDES LIFT ANALYSES REPORT - IFA | 15 | 2022-06-30 | 2022-07-26 | 2023-01-24 | 2023-02-13 | 143
0 | EDHDSR1185 | HD-03 TOPSIDES LINEAR BLAST ANALYSIS REPORT - IFA | 15 | 2022-06-30 | 2022-07-26 | 2023-03-01 | 2023-03-21 | 169
0 | EDHDSR1165 | HD-03 TOPSIDE MISCELLANEOUS DESIGN REPORT - ICR | 20 | 2022-06-30 | 2022-08-02 | 2023-01-18 | 2023-02-14 | 139
0 | EDHDSR1140 | HD-03 TOPSIDES LOADOUT ANALYSIS REPORT - IFA | 15 | 2022-07-07 | 2022-08-02 | 2023-05-26 | 2023-06-15 | 224
0 | EDHDSR1080 | HD-03 TOPSIDE JOINT DESIGN REPORT - IFA | 15 | 2022-07-07 | 2022-08-02 | 2022-10-13 | 2022-11-02 | 67
0 | EDHDSR1015 | HD-03 JACKET INPLACE ANALYSIS REPORT - ICR | 20 | 2022-07-07 | 2022-08-09 | 2022-10-31 | 2022-11-25 | 79
0 | EDHDSR1155 | HD-03 TOPSIDES TRANSPORTATION ANALYSES REPORT - IFA | 15 | 2022-07-19 | 2022-08-09 | 2023-03-01 | 2023-03-21 | 159
0 | EDHDSR1030 | HD-03 JACKET PUSHOVER ANALYSIS REPORT - ICR | 20 | 2022-07-26 | 2022-08-23 | 2022-11-14 | 2022-12-13 | 79
0 | EDHDSR1095 | HD-03 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - IFA | 15 | 2022-08-02 | 2022-08-23 | 2022-12-23 | 2023-01-12 | 101
0 | EDHDSR1010 | HD-03 GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - IFC | 15 | 2022-08-03 | 2022-08-24 | 2022-11-10 | 2022-11-30 | 71
0 | EDHDSR1190 | HD-03 TOPSIDES LINEAR BLAST ANALYSIS REPORT - IFC | 15 | 2022-08-09 | 2022-08-30 | 2023-04-05 | 2023-04-27 | 169
0 | EDHDSR1145 | HD-03 TOPSIDES LOADOUT ANALYSIS REPORT - IFC | 15 | 2022-08-16 | 2022-09-06 | 2023-07-05 | 2023-07-26 | 224
0 | EDHDSR1045 | HD-03 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - ICR | 20 | 2022-08-09 | 2022-09-06 | 2022-11-28 | 2022-12-27 | 79
0 | EDHDSR1170 | HD-03 TOPSIDE MISCELLANEOUS DESIGN REPORT - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-03-01 | 2023-03-21 | 139
0 | EDHDSR1085 | HD-03 TOPSIDE JOINT DESIGN REPORT - IFC | 15 | 2022-08-16 | 2022-09-06 | 2022-11-17 | 2022-12-09 | 67
0 | EDHDSR1130 | HD-03 TOPSIDES LIFT ANALYSES REPORT - IFC | 15 | 2022-08-17 | 2022-09-07 | 2023-02-28 | 2023-03-20 | 137
0 | EDHDSR1160 | HD-03 TOPSIDES TRANSPORTATION ANALYSES REPORT - IFC | 15 | 2022-08-23 | 2022-09-13 | 2023-04-05 | 2023-04-27 | 159
0 | EDHDSR1020 | HD-03 JACKET INPLACE ANALYSIS REPORT - IFA | 15 | 2022-08-23 | 2022-09-13 | 2022-12-28 | 2023-01-17 | 89
0 | EDHDSR1060 | HD-03 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - ICR | 20 | 2022-08-23 | 2022-09-20 | 2022-12-28 | 2023-01-24 | 89
0 | EDHDSR1035 | HD-03 JACKET PUSHOVER ANALYSIS REPORT - IFA | 15 | 2022-09-06 | 2022-09-27 | 2023-01-04 | 2023-01-24 | 84
0 | EDHDSR1100 | HD-03 TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - IFC | 15 | 2022-09-06 | 2022-09-27 | 2023-01-27 | 2023-02-16 | 101
0 | EDHDSR1200 | HD-3 SLEEVE PILE DRIVABILITY REPORT - ICR | 15 | 2022-09-06 | 2022-09-27 | 2023-01-04 | 2023-01-24 | 84
0 | EDHDSR1105 | HD-03 JACKET MISCELLANEOUS DESIGN REPORT - ICR | 20 | 2022-09-06 | 2022-10-04 | 2023-01-18 | 2023-02-14 | 94
0 | EDHDSR1230 | HD-3 NEW JACKET LEG WITH BRACES ON BOTTOM STABILITY ANALYSIS - ICR | 15 | 2022-09-13 | 2022-10-04 | 2023-01-18 | 2023-02-07 | 89
0 | EDHDSR1175 | HD-03 TOPSIDE MISCELLANEOUS DESIGN REPORT - IFC | 15 | 2022-09-20 | 2022-10-11 | 2023-04-05 | 2023-04-27 | 139
0 | EDHDSR1050 | HD-03 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - IFA | 15 | 2022-09-20 | 2022-10-11 | 2023-01-11 | 2023-01-31 | 79
0 | EDHDSR1260 | HD-3 EXISTING (DEMOLITION) TOPSIDE LIFT ANALYSIS REPORT - ICR | 15 | 2022-09-20 | 2022-10-11 | 2023-01-25 | 2023-02-14 | 89
0 | EDHDSR1025 | HD-03 JACKET INPLACE ANALYSIS REPORT - IFC | 15 | 2022-09-27 | 2022-10-18 | 2023-02-01 | 2023-02-21 | 89
0 | EDHDSR1290 | HD-3 EXISTING (DEMOLITION) TOPSIDE TRANSPORTATION ANALYSIS REPORT - ICR | 10 | 2022-10-04 | 2022-10-18 | 2023-02-15 | 2023-02-28 | 94
0 | EDHDSR1065 | HD-03 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - IFA | 15 | 2022-10-04 | 2022-10-25 | 2023-03-01 | 2023-03-21 | 104
0 | EDHDSR1210 | HD-3 SLEEVE PILE DRIVABILITY REPORT - IFA | 10 | 2022-10-11 | 2022-10-25 | 2023-02-08 | 2023-02-21 | 84
0 | EDHDSR1040 | HD-03 JACKET PUSHOVER ANALYSIS REPORT - IFC | 15 | 2022-10-11 | 2022-11-01 | 2023-02-08 | 2023-02-28 | 84
0 | EDHDSR1240 | HD-3 NEW JACKET LEG WITH BRACES ON BOTTOM STABILITY ANALYSIS - IFA | 10 | 2022-10-18 | 2022-11-01 | 2023-02-22 | 2023-03-07 | 89
0 | EDHDSR1110 | HD-03 JACKET MISCELLANEOUS DESIGN REPORT - IFA | 15 | 2022-10-18 | 2022-11-08 | 2023-03-01 | 2023-03-21 | 94
0 | EDHDSR1055 | HD-03 JACKET SPECTRAL FATIGUE ANALYSIS REPORT - IFC | 15 | 2022-10-25 | 2022-11-15 | 2023-02-15 | 2023-03-07 | 79
0 | EDHDSR1270 | HD-3 EXISTING (DEMOLITION) TOPSIDE LIFT ANALYSIS REPORT - IFA | 15 | 2022-10-25 | 2022-11-15 | 2023-03-01 | 2023-03-21 | 89
0 | EDHDSR1300 | HD-3 EXISTING (DEMOLITION) TOPSIDE TRANSPORTATION ANALYSIS REPORT - IFA | 10 | 2022-11-01 | 2022-11-15 | 2023-03-15 | 2023-03-28 | 94
0 | EDHDSR1070 | HD-03 JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - IFC | 15 | 2022-11-08 | 2022-11-29 | 2023-04-05 | 2023-04-27 | 104
0 | EDHDSR1220 | HD-3 SLEEVE PILE DRIVABILITY REPORT - IFC | 10 | 2022-11-15 | 2022-11-29 | 2023-03-08 | 2023-03-21 | 79
0 | EDHDSR1115 | HD-03 JACKET MISCELLANEOUS DESIGN REPORT - IFC | 15 | 2022-11-22 | 2022-12-15 | 2023-04-05 | 2023-04-27 | 94
0 | EDHDSR1250 | HD-3 NEW JACKET LEG WITH BRACES ON BOTTOM STABILITY ANALYSIS - IFC | 10 | 2022-11-29 | 2022-12-15 | 2023-03-22 | 2023-04-04 | 79
0 | EDHDSR1280 | HD-3 EXISTING (DEMOLITION) TOPSIDE LIFT ANALYSIS REPORT - IFC | 15 | 2022-12-15 | 2023-01-05 | 2023-04-05 | 2023-04-27 | 79
0 | EDHDSR1310 | HD-3 EXISTING (DEMOLITION) TOPSIDE TRANSPORTATION ANALYSIS REPORT - IFC | 10 | 2022-12-22 | 2023-01-05 | 2023-04-12 | 2023-04-27 | 79
DRAWINGS |  |  | 176 | 2022-04-22 | 2023-01-05 | 2022-08-25 | 2023-08-29 | 163
GENERAL |  |  | 167 | 2022-04-22 | 2022-12-23 | 2022-09-01 | 2023-04-27 | 88
0 | EDHGSR1000 | HD-03 DRAWING INDEX - ICR | 15 | 2022-04-22 | 2022-05-18 | 2022-09-01 | 2022-09-21 | 88
0 | EDHGSR1002 | HD-03 DRAWING INDEX - IFA | 15 | 2022-06-15 | 2022-07-06 | 2022-10-06 | 2022-10-26 | 78
0 | EDHGSR1005 | HD-03 DRAWING INDEX - IFC | 15 | 2022-11-30 | 2022-12-23 | 2023-04-05 | 2023-04-27 | 88
PRIMARY |  |  | 95 | 2022-05-26 | 2022-10-11 | 2022-08-25 | 2023-04-17 | 133
0 | EDHGSR1030 | HD-03 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - ICR | 20 | 2022-05-26 | 2022-06-23 | 2022-08-26 | 2022-09-22 | 63
0 | EDHGSR1015 | HD-03 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 15.000 - ICR | 20 | 2022-05-26 | 2022-06-23 | 2022-08-25 | 2022-09-21 | 62
0 | EDHGSR1045 | HD-03 DECK ELEVATION ROW-1 & 2 - ICR | 20 | 2022-06-02 | 2022-06-30 | 2022-09-02 | 2022-09-29 | 63
0 | EDHGSR1060 | HD-03 DECK ELEVATION ROW-A & B - ICR | 20 | 2022-06-02 | 2022-06-30 | 2022-09-02 | 2022-09-29 | 63
0 | EDHGSR1075 | HD-03 DECK SECTIONS - ICR | 20 | 2022-06-09 | 2022-07-07 | 2022-09-09 | 2022-10-06 | 63
0 | EDHGSR1105 | HD-03 MAIN DECK FRAMING PLAN EL(+) 18.000 - ICR | 20 | 2022-06-27 | 2022-07-28 | 2022-09-27 | 2022-10-24 | 63
0 | EDHGSR1120 | HD-03 UPPER DECK FRAMING PLAN EL(+) 21.000 - ICR | 20 | 2022-06-27 | 2022-07-28 | 2022-09-27 | 2022-10-24 | 63
0 | EDHGSR1135 | HD-03 WEATHER DECK FRAMING PLAN EL(+) 25.500 - ICR | 20 | 2022-06-30 | 2022-08-02 | 2022-11-24 | 2022-12-23 | 102
0 | EDHGSR1150 | HD-03 DECK LEG STABBING GUIDE DETAILS - ICR | 20 | 2022-06-30 | 2022-08-02 | 2023-01-10 | 2023-02-06 | 133
0 | EDHGSR1020 | HD-03 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 15.000- IFA. | 15 | 2022-07-07 | 2022-08-02 | 2022-10-06 | 2022-10-26 | 62
0 | EDHGSR1035 | HD-03 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - IFA | 20 | 2022-07-07 | 2022-08-09 | 2022-10-13 | 2022-11-09 | 67
0 | EDHGSR1050 | HD-03 DECK ELEVATION ROW-1 & 2 - IFA | 15 | 2022-07-19 | 2022-08-09 | 2022-11-24 | 2022-12-16 | 92
0 | EDHGSR1065 | HD-03 DECK ELEVATION ROW-A & B - IFA | 15 | 2022-07-19 | 2022-08-09 | 2022-12-08 | 2022-12-28 | 100
0 | EDHGSR1080 | HD-03 DECK SECTIONS - IFA | 15 | 2022-07-26 | 2022-08-16 | 2022-12-08 | 2022-12-28 | 95
0 | EDHGSR1110 | HD-03 MAIN DECK FRAMING PLAN EL(+) 18.000 - IFA | 15 | 2022-08-11 | 2022-09-01 | 2022-11-22 | 2022-12-14 | 73
0 | EDHGSR1125 | HD-03 UPPER DECK FRAMING PLAN EL(+) 21.000 - IFA | 15 | 2022-08-11 | 2022-09-01 | 2022-11-08 | 2022-11-28 | 63
0 | EDHGSR1140 | HD-03 WEATHER DECK FRAMING PLAN EL(+) 25.500 - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-01-09 | 2023-01-27 | 102
0 | EDHGSR1155 | HD-03 DECK LEG STABBING GUIDE DETAILS - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-02-21 | 2023-03-13 | 133
0 | EDHGSR1025 | HD-03 CELLAR DECK PRIMARY FRAMING PLAN EL(+) 15.000 - IFC | 15 | 2022-08-16 | 2022-09-06 | 2022-11-10 | 2022-11-30 | 62
0 | EDHGSR1055 | HD-03 DECK ELEVATION ROW-1 & 2 - IFC | 15 | 2022-08-23 | 2022-09-13 | 2023-01-02 | 2023-01-20 | 92
0 | EDHGSR1070 | HD-03 DECK ELEVATION ROW-A & B - IFC | 15 | 2022-08-23 | 2022-09-13 | 2023-01-12 | 2023-02-01 | 100
0 | EDHGSR1085 | HD-03 DECK SECTIONS - IFC | 15 | 2022-08-30 | 2022-09-20 | 2023-01-12 | 2023-02-01 | 95
0 | EDHGSR1040 | HD-03 DECK PRIMARY JOINT & TYPICAL JOINT DETAILS - IFC | 20 | 2022-08-30 | 2022-09-27 | 2022-11-24 | 2022-12-23 | 62
0 | EDHGSR1115 | HD-03 MAIN DECK FRAMING PLAN EL(+) 18.000 - IFC | 15 | 2022-09-15 | 2022-10-06 | 2022-12-29 | 2023-01-18 | 73
0 | EDHGSR1130 | HD-03 UPPER DECK FRAMING PLAN EL(+) 21.000 - IFC | 15 | 2022-09-15 | 2022-10-06 | 2022-12-15 | 2023-01-04 | 63
0 | EDHGSR1145 | HD-03 WEATHER DECK FRAMING PLAN EL(+) 25.500 - IFC | 15 | 2022-09-20 | 2022-10-11 | 2023-02-13 | 2023-03-03 | 102
0 | EDHGSR1160 | HD-03 DECK LEG STABBING GUIDE DETAILS - IFC | 15 | 2022-09-20 | 2022-10-11 | 2023-03-28 | 2023-04-17 | 133
SECONDARY |  |  | 102 | 2022-06-09 | 2022-11-03 | 2022-10-03 | 2023-05-02 | 125
0 | EDHGSR1165 | HD-03 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - ICR | 20 | 2022-06-09 | 2022-07-07 | 2022-10-03 | 2022-10-28 | 79
0 | EDHGSR1225 | HD-03 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - ICR | 20 | 2022-06-16 | 2022-07-19 | 2022-10-10 | 2022-11-04 | 79
0 | EDHGSR1180 | HD-03 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-10-27 | 2022-11-23 | 87
0 | EDHGSR1240 | HD-03 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - ICR | 20 | 2022-06-30 | 2022-08-02 | 2022-11-03 | 2022-11-30 | 87
0 | EDHGSR2145 | HD-3 CELLAR DECK INFILL BEAM FRAMING PLAN EL (+) 10.700 T.O.S. - ICR | 15 | 2022-07-07 | 2022-08-02 | 2022-11-17 | 2022-12-09 | 92
0 | EDHGSR1255 | HD-3 ESDV / DRAIN DRUM PLATFORM PLATING / GRATING & HANDRAIL LAYOUT AT EL. (+) 7.300 T.O.S. - ICR | 20 | 2022-07-07 | 2022-08-09 | 2022-11-10 | 2022-12-09 | 87
0 | EDHGSR2175 | HD-3 MAIN DECK INFILL BEAM FRAMING PLAN EL (+) 14.100 T.O.S. - ICR | 15 | 2022-07-19 | 2022-08-09 | 2022-12-05 | 2022-12-23 | 97
0 | EDHGSR1195 | HD-03 UPPER DECK SECONDARY FRAMING PLAN EL(+) 21.000 - ICR | 20 | 2022-07-14 | 2022-08-11 | 2022-11-10 | 2022-12-09 | 85
0 | EDHGSR1170 | HD-03 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - IFA | 15 | 2022-07-26 | 2022-08-16 | 2022-12-12 | 2022-12-30 | 97
0 | EDHGSR1270 | HD-03 UPPER DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - ICR | 20 | 2022-07-21 | 2022-08-18 | 2022-11-17 | 2022-12-16 | 85
0 | EDHGSR1210 | HD-03 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - ICR | 20 | 2022-07-21 | 2022-08-18 | 2022-12-13 | 2023-01-09 | 101
0 | EDHGSR2205 | HD-3 UPPER DECK INFILL BEAM FRAMING PLAN EL (+) 18.800 T.O.S. - ICR | 15 | 2022-07-28 | 2022-08-18 | 2022-12-12 | 2022-12-30 | 95
0 | EDHGSR1230 | HD-03 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - IFA | 15 | 2022-08-02 | 2022-08-23 | 2022-12-19 | 2023-01-06 | 97
0 | EDHGSR1285 | HD-03 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - ICR | 20 | 2022-07-28 | 2022-08-25 | 2022-12-20 | 2023-01-16 | 101
0 | EDHGSR2235 | HD-3 WEATHER DECK INFILL BEAM FRAMING PLAN EL (+) 23.000 T.O.S. - ICR | 15 | 2022-08-04 | 2022-08-25 | 2023-01-30 | 2023-02-17 | 125
0 | EDHGSR1185 | HD-03 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - IFA | 15 | 2022-08-09 | 2022-08-30 | 2022-12-19 | 2023-01-06 | 92
0 | EDHGSR1245 | HD-03 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-01-02 | 2023-01-20 | 97
0 | EDHGSR2155 | HD-3 CELLAR DECK INFILL BEAM FRAMING PLAN EL (+) 10.700 T.O.S. - IFA | 15 | 2022-08-16 | 2022-09-06 | 2022-12-26 | 2023-01-13 | 92
0 | EDHGSR1260 | HD-3 ESDV / DRAIN DRUM PLATFORM PLATING / GRATING & HANDRAIL LAYOUT AT EL. (+) 7.300 T.O.S.- IFA | 15 | 2022-08-23 | 2022-09-13 | 2023-01-16 | 2023-02-03 | 102
0 | EDHGSR1175 | HD-03 MAIN DECK SECONDARY FRAMING PLAN EL(+) 15.000 - IFC | 10 | 2022-08-30 | 2022-09-13 | 2023-01-16 | 2023-01-27 | 97
0 | EDHGSR2185 | HD-3 MAIN DECK INFILL BEAM FRAMING PLAN EL (+) 14.100 T.O.S. - IFA | 15 | 2022-08-23 | 2022-09-13 | 2023-01-30 | 2023-02-17 | 112
0 | EDHGSR1200 | HD-03 UPPER DECK SECONDARY FRAMING PLAN EL(+) 21.000 - IFA | 15 | 2022-08-25 | 2022-09-15 | 2023-01-02 | 2023-01-20 | 90
0 | EDHGSR1275 | HD-03 UPPER DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - IFA | 15 | 2022-09-01 | 2022-09-22 | 2023-01-02 | 2023-01-20 | 85
0 | EDHGSR1215 | HD-03 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - IFA | 15 | 2022-09-01 | 2022-09-22 | 2023-02-23 | 2023-03-15 | 123
0 | EDHGSR2215 | HD-3 UPPER DECK INFILL BEAM FRAMING PLAN EL (+) 18.800 T.O.S. - IFA | 15 | 2022-09-01 | 2022-09-22 | 2023-01-16 | 2023-02-03 | 95
0 | EDHGSR1190 | HD-03 CELLAR DECK SECONDARY FRAMING PLAN EL(+) 9.000 - IFC | 10 | 2022-09-13 | 2022-09-27 | 2023-01-23 | 2023-02-03 | 92
0 | EDHGSR1290 | HD-03 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - IFA | 15 | 2022-09-08 | 2022-09-29 | 2023-01-31 | 2023-02-20 | 101
0 | EDHGSR2245 | HD-3 WEATHER DECK INFILL BEAM FRAMING PLAN EL (+) 23.000 T.O.S. - IFA | 15 | 2022-09-08 | 2022-09-29 | 2023-03-06 | 2023-03-24 | 125
0 | EDHGSR1250 | HD-03 CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 9.000 - IFC | 15 | 2022-09-20 | 2022-10-11 | 2023-02-06 | 2023-02-24 | 97
0 | EDHGSR2165 | HD-3 CELLAR DECK INFILL BEAM FRAMING PLAN EL (+) 10.700 T.O.S. - IFC | 15 | 2022-09-20 | 2022-10-11 | 2023-01-30 | 2023-02-17 | 92
0 | EDHGSR1235 | HD-03 MAIN DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 15.000 - IFC | 15 | 2022-09-27 | 2022-10-18 | 2023-01-23 | 2023-02-10 | 82
0 | EDHGSR2195 | HD-3 MAIN DECK INFILL BEAM FRAMING PLAN EL (+) 14.100 T.O.S. - IFC | 15 | 2022-09-27 | 2022-10-18 | 2023-03-06 | 2023-03-24 | 112
0 | EDHGSR1205 | HD-03 UPPER DECK SECONDARY FRAMING PLAN EL(+) 21.000 - IFC | 15 | 2022-09-29 | 2022-10-20 | 2023-02-06 | 2023-02-24 | 90
0 | EDHGSR1265 | HD-3 ESDV / DRAIN DRUM PLATFORM PLATING / GRATING & HANDRAIL LAYOUT AT EL. (+) 7.300 T.O.S. - IFC | 15 | 2022-10-06 | 2022-10-27 | 2023-02-20 | 2023-03-10 | 95
0 | EDHGSR1280 | HD-03 UPPER DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL(+) 21.000 - IFC | 15 | 2022-10-06 | 2022-10-27 | 2023-02-06 | 2023-02-24 | 85
0 | EDHGSR1220 | HD-03 WEATHER DECK SECONDARY FRAMING PLAN EL(+) 25.500 - IFC | 15 | 2022-10-06 | 2022-10-27 | 2023-03-30 | 2023-04-19 | 123
0 | EDHGSR2225 | HD-3 UPPER DECK INFILL BEAM FRAMING PLAN EL (+) 18.800 T.O.S.- IFC | 15 | 2022-10-06 | 2022-10-27 | 2023-02-20 | 2023-03-10 | 95
0 | EDHGSR1295 | HD-03 WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 25 500 - IFC | 15 | 2022-10-13 | 2022-11-03 | 2023-03-07 | 2023-03-27 | 101
0 | EDHGSR2255 | HD-3 WEATHER DECK INFILL BEAM FRAMING PLAN EL (+) 23.000 T.O.S. - IFC | 15 | 2022-10-13 | 2022-11-03 | 2023-04-10 | 2023-05-02 | 125
TERTAIRY |  |  | 135 | 2022-06-23 | 2023-01-05 | 2022-10-17 | 2023-08-29 | 163
0 | EDHGSR1400 | HD-03 - DECK LIFTING PADEYE DETAILS - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-10-17 | 2022-11-11 | 79
0 | EDHGSR1415 | HD-03 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - ICR | 20 | 2022-06-30 | 2022-08-02 | 2022-10-24 | 2022-11-18 | 79
0 | EDHGSR1430 | HD-03 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS- ICR | 17 | 2022-07-15 | 2022-08-09 | 2022-11-03 | 2022-11-25 | 79
0 | EDHGSR1885 | HD-3 ESDV/DRAIN DRUM PLATFORM EQUIPMENT SUPPORT DETAILS - ICR | 15 | 2022-07-19 | 2022-08-09 | 2023-01-20 | 2023-02-09 | 131
0 | EDHGSR1445 | HD-03 UPPER DECK EQUIPMENT SUPPORTGA AND DETAILS - ICR | 20 | 2022-07-19 | 2022-08-16 | 2022-11-07 | 2022-12-06 | 79
0 | EDHGSR1460 | HD-03 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - ICR | 20 | 2022-07-19 | 2022-08-16 | 2022-11-07 | 2022-12-06 | 79
0 | EDHGSR2265 | HD-3 CELLAR DECK LOADING DIAGRAM - IRC | 15 | 2022-08-02 | 2022-08-23 | 2022-12-12 | 2022-12-30 | 92
0 | EDHGSR2295 | HD-3 MAIN DECK LOADING DIAGRAM - IRC | 15 | 2022-08-09 | 2022-08-30 | 2022-12-19 | 2023-01-06 | 92
0 | EDHGSR2325 | HD-3 UPPER DECK LOADING DIAGRAM - IRC | 15 | 2022-08-16 | 2022-09-06 | 2022-12-26 | 2023-01-13 | 92
0 | EDHGSR1505 | HD-03 - VENT BOOM GA AND DETAILS - ICR | 20 | 2022-08-16 | 2022-09-13 | 2022-12-07 | 2023-01-03 | 79
0 | EDHGSR1435 | HD-03 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-23 | 2022-09-13 | 2023-01-27 | 2023-02-16 | 111
0 | EDHGSR1420 | HD-03 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-23 | 2022-09-13 | 2023-01-13 | 2023-02-02 | 101
0 | EDHGSR1895 | HD-3 ESDV/DRAIN DRUM PLATFORM EQUIPMENT SUPPORT DETAILS - IFA | 15 | 2022-08-23 | 2022-09-13 | 2023-02-24 | 2023-03-16 | 131
0 | EDHGSR1915 | HD-3 WEATHER DECK JIB CRANE AND DETAILS - ICR | 15 | 2022-08-23 | 2022-09-13 | 2023-03-22 | 2023-04-11 | 149
0 | EDHGSR2355 | HD-3 WEATHER DECK LOADING DIAGRAM - IRC | 15 | 2022-08-23 | 2022-09-13 | 2023-01-02 | 2023-01-20 | 92
0 | EDHGSR1550 | HD-03 NORTH SIDE STAIR TOWER LAYOUT PLAN- ICR | 20 | 2022-08-23 | 2022-09-20 | 2022-12-14 | 2023-01-10 | 79
0 | EDHGSR1535 | HAIR DALMA HD-3 SOUTH SIDE STAIRCASE GA AND DETAILS- ICR | 20 | 2022-08-23 | 2022-09-20 | 2022-12-14 | 2023-01-10 | 79
0 | EDHGSR1450 | HD-03 UPPER DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-30 | 2022-09-20 | 2023-02-03 | 2023-02-23 | 111
0 | EDHGSR1465 | HD-03 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - IFA | 15 | 2022-08-30 | 2022-09-20 | 2023-02-10 | 2023-03-02 | 116
0 | EDHGSR1520 | HD-03 - MONORAIL AND DETAILS- ICR | 20 | 2022-08-23 | 2022-09-20 | 2022-12-14 | 2023-01-10 | 79
0 | EDHGSR2275 | HD-3 CELLAR DECK LOADING DIAGRAM - IFA | 15 | 2022-09-06 | 2022-09-27 | 2023-02-13 | 2023-03-03 | 112
0 | EDHGSR1405 | HD-03 - DECK LIFTING PADEYE DETAILS - IFA | 15 | 2022-09-12 | 2022-10-03 | 2023-02-14 | 2023-03-06 | 109
0 | EDHGSR1945 | HD-3 NORTH SIDE STAIR TOWER ELEVATIONS/ DETAILS- ICR | 15 | 2022-09-13 | 2022-10-04 | 2023-01-04 | 2023-01-24 | 79
0 | EDHGSR2055 | HD-3 JACKET NEW ANODE DETAILS - ICR | 10 | 2022-09-20 | 2022-10-04 | 2023-03-01 | 2023-03-14 | 114
0 | EDHGSR2305 | HD-3 MAIN DECK LOADING DIAGRAM - IFA | 15 | 2022-09-13 | 2022-10-04 | 2023-02-13 | 2023-03-03 | 107
0 | EDHGSR2385 | HD-3 PULLING POST & MATERIAL HANDLING PADEYES - IRC | 15 | 2022-09-13 | 2022-10-04 | 2023-01-23 | 2023-02-10 | 92
0 | EDHGSR2415 | HD-3 PIPE SUPPORT DETAILS - IRC | 15 | 2022-09-13 | 2022-10-04 | 2023-01-23 | 2023-02-10 | 92
0 | EDHGSR1625 | HD-03 LADDER - ICR | 15 | 2022-09-20 | 2022-10-11 | 2023-01-17 | 2023-02-06 | 83
0 | EDHGSR1670 | HD-03 - STRUCTURAL MISCELLANEOUS DETAIL - ICR | 20 | 2022-09-13 | 2022-10-11 | 2023-01-11 | 2023-02-07 | 84
0 | EDHGSR1655 | HD-03 DECK DAVIT GA AND DETAILS - ICR | 10 | 2022-09-27 | 2022-10-11 | 2023-01-24 | 2023-02-06 | 83
0 | EDHGSR1775 | HD-03 SWING ROPE DETAILS DRAWING - ICR | 10 | 2022-09-27 | 2022-10-11 | 2023-02-01 | 2023-02-14 | 89
0 | EDHGSR1855 | HD-03 JACKET EXTENSION PLAN/ ELEVATION & DETAILS - ICR | 20 | 2022-09-13 | 2022-10-11 | 2023-01-18 | 2023-02-14 | 89
0 | EDHGSR2335 | HD-3 UPPER DECK LOADING DIAGRAM - IFA | 15 | 2022-09-20 | 2022-10-11 | 2023-02-13 | 2023-03-03 | 102
0 | EDHGSR1685 | HD-03 JACKET RISER GA AND SUPPORT DETAILS - ICR | 20 | 2022-09-20 | 2022-10-18 | 2023-01-18 | 2023-02-14 | 84
0 | EDHGSR1510 | HD-03 - VENT BOOM GA AND DETAILS - IFA | 15 | 2022-09-27 | 2022-10-18 | 2023-04-19 | 2023-05-11 | 144
0 | EDHGSR1525 | HD-03 - MONORAIL AND DETAILS - IFA | 15 | 2022-09-27 | 2022-10-18 | 2023-06-07 | 2023-06-30 | 177
0 | EDHGSR1715 | HD-03 IDENTIFICATION BOARD DRAWING- ICR | 17 | 2022-09-23 | 2022-10-18 | 2023-01-23 | 2023-02-14 | 84
0 | EDHGSR1610 | HD-3 MAIN DECK ACCESS PLATFORM GA AND DETAILS - ICR | 20 | 2022-09-20 | 2022-10-18 | 2023-01-11 | 2023-02-07 | 79
0 | EDHGSR1905 | HD-3 ESDV/DRAIN DRUM PLATFORM EQUIPMENT SUPPORT DETAILS - IFC | 15 | 2022-09-27 | 2022-10-18 | 2023-03-31 | 2023-04-20 | 131
0 | EDHGSR1925 | HD-3 WEATHER DECK JIB CRANE AND DETAILS - IFA | 15 | 2022-09-27 | 2022-10-18 | 2023-04-28 | 2023-05-18 | 149
0 | EDHGSR1975 | HD-3 NORTH SIDE STAIR JACKET WALKWAY TO CELLAR DECK - ICR | 15 | 2022-09-27 | 2022-10-18 | 2023-01-18 | 2023-02-07 | 79
0 | EDHGSR1995 | HD-3 ESDV/DRAIN DRUM PLATFORM PLAN - ICR | 15 | 2022-09-27 | 2022-10-18 | 2023-04-19 | 2023-05-11 | 144
0 | EDHGSR2025 | HD-3 JACKET J-TUBE GENERAL ARRANGEMENT / SUPPORT DETAILS - IRC | 15 | 2022-09-27 | 2022-10-18 | 2023-03-08 | 2023-03-28 | 114
0 | EDHGSR2085 | HD-3 JACKET LEG PROTECTOR DETAILS- ICR | 10 | 2022-10-04 | 2022-10-18 | 2023-03-15 | 2023-03-28 | 114
0 | EDHGSR2115 | HD-03 JACKET EXTENSION MISC. DWGS/ DETAILS - ICR | 15 | 2022-09-27 | 2022-10-18 | 2023-03-15 | 2023-04-04 | 119
0 | EDHGSR2365 | HD-3 WEATHER DECK LOADING DIAGRAM - IFA | 15 | 2022-09-27 | 2022-10-18 | 2023-02-13 | 2023-03-03 | 97
0 | EDHGSR2455 | HD-03 NORTH SIDE STAIR TOWER LAYOUT PLAN- IFA | 15 | 2022-10-04 | 2022-10-25 | 2023-04-05 | 2023-04-27 | 129
0 | EDHGSR2065 | HD-3 JACKET NEW ANODE DETAILS - IFA | 10 | 2022-10-18 | 2022-11-01 | 2023-04-05 | 2023-04-18 | 119
0 | EDHGSR2285 | HD-3 CELLAR DECK LOADING DIAGRAM - IFC | 15 | 2022-10-11 | 2022-11-01 | 2023-03-20 | 2023-04-07 | 112
0 | EDHGSR2445 | HAIR DALMA HD-3 SOUTH SIDE STAIRCASE GA AND DETAILS- IFA | 20 | 2022-10-04 | 2022-11-01 | 2023-04-28 | 2023-05-25 | 144
0 | EDHGSR2485 | HD-3 NORTH SIDE STAIR TOWER ELEVATIONS/ DETAILS- IFA | 10 | 2022-10-18 | 2022-11-01 | 2023-04-19 | 2023-05-04 | 129
0 | EDHGSR2315 | HD-3 MAIN DECK LOADING DIAGRAM - IFC | 15 | 2022-10-18 | 2022-11-08 | 2023-03-20 | 2023-04-07 | 107
0 | EDHGSR2395 | HD-3 PULLING POST & MATERIAL HANDLING PADEYES - IFA | 15 | 2022-10-18 | 2022-11-08 | 2023-02-27 | 2023-03-17 | 92
0 | EDHGSR2425 | HD-3 PIPE SUPPORT DETAILS - IFA | 15 | 2022-10-18 | 2022-11-08 | 2023-02-27 | 2023-03-17 | 92
0 | EDHGSR1675 | HD-03 - STRUCTURAL MISCELLANEOUS DETAIL - IFA | 15 | 2022-10-25 | 2022-11-15 | 2023-07-04 | 2023-07-25 | 173
0 | EDHGSR1660 | HD-03 DECK DAVIT GA AND DETAILS - IFA | 15 | 2022-10-25 | 2022-11-15 | 2023-02-21 | 2023-03-13 | 83
0 | EDHGSR1780 | HD-03 SWING ROPE DETAILS DRAWING - IFA | 15 | 2022-10-25 | 2022-11-15 | 2023-03-01 | 2023-03-21 | 89
0 | EDHGSR1865 | HD-03 JACKET EXTENSION PLAN/ ELEVATION & DETAILS - IFA | 15 | 2022-10-25 | 2022-11-15 | 2023-03-01 | 2023-03-21 | 89
0 | EDHGSR2035 | HD-3 JACKET J-TUBE GENERAL ARRANGEMENT / SUPPORT DETAILS - IFA | 10 | 2022-11-01 | 2022-11-15 | 2023-04-12 | 2023-04-27 | 114
0 | EDHGSR2095 | HD-3 JACKET LEG PROTECTOR DETAILS- IFA | 10 | 2022-11-01 | 2022-11-15 | 2023-04-12 | 2023-04-27 | 114
0 | EDHGSR2345 | HD-3 UPPER DECK LOADING DIAGRAM - IFC | 15 | 2022-10-25 | 2022-11-15 | 2023-03-20 | 2023-04-07 | 102
0 | EDHGSR2475 | HD-03 LADDER - IFA | 15 | 2022-10-25 | 2022-11-15 | 2023-05-26 | 2023-06-15 | 149
0 | EDHGSR1515 | HD-03 - VENT BOOM GA AND DETAILS - IFC | 15 | 2022-11-01 | 2022-11-22 | 2023-05-26 | 2023-06-15 | 144
0 | EDHGSR1690 | HD-03 JACKET RISER GA AND SUPPORT DETAILS - IFA | 15 | 2022-11-01 | 2022-11-22 | 2023-03-08 | 2023-03-28 | 89
0 | EDHGSR1720 | HD-03 IDENTIFICATION BOARD DRAWING - IFA | 15 | 2022-11-01 | 2022-11-22 | 2023-03-01 | 2023-03-21 | 84
0 | EDHGSR1530 | HD-03 - MONORAIL AND DETAILS - IFC | 15 | 2022-11-01 | 2022-11-22 | 2023-07-17 | 2023-08-07 | 177
0 | EDHGSR1935 | HD-3 WEATHER DECK JIB CRANE AND DETAILS - IFC | 15 | 2022-11-01 | 2022-11-22 | 2023-06-02 | 2023-06-22 | 149
0 | EDHGSR2005 | HD-3 ESDV/DRAIN DRUM PLATFORM PLAN - IFA | 15 | 2022-11-01 | 2022-11-22 | 2023-05-26 | 2023-06-15 | 144
0 | EDHGSR2125 | HD-03 JACKET EXTENSION MISC. DWGS/ DETAILS - IFA | 15 | 2022-11-01 | 2022-11-22 | 2023-04-19 | 2023-05-11 | 119
0 | EDHGSR2375 | HD-3 WEATHER DECK LOADING DIAGRAM - IFC | 15 | 2022-11-01 | 2022-11-22 | 2023-03-20 | 2023-04-07 | 97
0 | EDHGSR2495 | HD-3 NORTH SIDE STAIR JACKET WALKWAY TO CELLAR DECK - IFA | 15 | 2022-11-01 | 2022-11-22 | 2023-05-05 | 2023-05-25 | 129
0 | EDHGSR1560 | HD-03 NORTH SIDE STAIR TOWER LAYOUT PLAN- IFC | 15 | 2022-11-08 | 2022-11-29 | 2023-05-12 | 2023-06-01 | 129
0 | EDHGSR2075 | HD-3 JACKET NEW ANODE DETAILS- IFC | 10 | 2022-11-15 | 2022-11-29 | 2023-05-05 | 2023-05-18 | 119
0 | EDHGSR2465 | HD-3 MAIN DECK ACCESS PLATFORM GA AND DETAILS - IFA | 20 | 2022-11-01 | 2022-11-29 | 2023-02-22 | 2023-03-21 | 79
0 | EDHGSR1545 | HAIR DALMA HD-3 SOUTH SIDE STAIRCASE GA AND DETAILS- IFC | 15 | 2022-11-15 | 2022-12-08 | 2023-06-09 | 2023-07-04 | 144
0 | EDHGSR1440 | HD-03 CELLAR DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-15 | 2022-12-08 | 2023-03-03 | 2023-03-23 | 76
0 | EDHGSR1425 | HD-03 MAIN DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-15 | 2022-12-08 | 2023-02-17 | 2023-03-09 | 66
0 | EDHGSR1965 | HD-3 NORTH SIDE STAIR TOWER ELEVATIONS/ DETAILS- IFC | 15 | 2022-11-15 | 2022-12-08 | 2023-05-19 | 2023-06-08 | 129
0 | EDHGSR1410 | HD-03 - DECK LIFTING PADEYE DETAILS - IFC | 14 | 2022-11-22 | 2022-12-14 | 2023-03-21 | 2023-04-07 | 83
0 | EDHGSR1455 | HD-03 UPPER DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-22 | 2022-12-15 | 2023-03-10 | 2023-03-30 | 76
0 | EDHGSR2045 | HD-3 JACKET J-TUBE GENERAL ARRANGEMENT / SUPPORT DETAILS - IFC | 10 | 2022-11-29 | 2022-12-15 | 2023-05-12 | 2023-05-25 | 114
0 | EDHGSR2105 | HD-3 JACKET LEG PROTECTOR DETAILS- IFC | 10 | 2022-11-29 | 2022-12-15 | 2023-05-12 | 2023-05-25 | 114
0 | EDHGSR2405 | HD-3 PULLING POST & MATERIAL HANDLING PADEYES - IFC | 15 | 2022-11-22 | 2022-12-15 | 2023-04-03 | 2023-04-25 | 92
0 | EDHGSR2435 | HD-3 PIPE SUPPORT DETAILS - IFC | 15 | 2022-11-22 | 2022-12-15 | 2023-04-03 | 2023-04-25 | 92
0 | EDHGSR1695 | HD-03 JACKET RISER GA AND SUPPORT DETAILS - IFC | 10 | 2022-12-08 | 2022-12-22 | 2023-04-12 | 2023-04-27 | 89
0 | EDHGSR1470 | HD-03 WEATHER DECK EQUIPMENT SUPPORT GA AND DETAILS - IFC | 15 | 2022-11-29 | 2022-12-22 | 2023-03-17 | 2023-04-06 | 76
0 | EDHGSR1635 | HD-03 LADDER - IFC | 15 | 2022-11-29 | 2022-12-22 | 2023-07-05 | 2023-07-26 | 149
0 | EDHGSR1665 | HD-03 DECK DAVIT GA AND DETAILS - IFC | 15 | 2022-11-29 | 2022-12-22 | 2023-03-28 | 2023-04-17 | 83
0 | EDHGSR1785 | HD-03 SWING ROPE DETAILS DRAWING - IFC | 15 | 2022-11-29 | 2022-12-22 | 2023-04-05 | 2023-04-27 | 89
0 | EDHGSR1875 | HD-03 JACKET EXTENSION PLAN/ ELEVATION & DETAILS - IFC | 15 | 2022-11-29 | 2022-12-22 | 2023-04-05 | 2023-04-27 | 89
0 | EDHGSR1725 | HD-03 IDENTIFICATION BOARD DRAWING - IFC | 15 | 2022-12-08 | 2022-12-29 | 2023-04-05 | 2023-04-27 | 84
0 | EDHGSR1985 | HD-3 NORTH SIDE STAIR JACKET WALKWAY TO CELLAR DECK - IFC | 15 | 2022-12-08 | 2022-12-29 | 2023-06-09 | 2023-07-04 | 129
0 | EDHGSR2015 | HD-3 ESDV/DRAIN DRUM PLATFORM PLAN - IFC | 15 | 2022-12-08 | 2022-12-29 | 2023-07-05 | 2023-07-26 | 144
0 | EDHGSR2135 | HD-03 JACKET EXTENSION MISC. DWGS/ DETAILS - IFC | 15 | 2022-12-08 | 2022-12-29 | 2023-05-26 | 2023-06-15 | 119
0 | EDHGSR1620 | HD-3 MAIN DECK ACCESS PLATFORM GA AND DETAILS - IFC | 15 | 2022-12-15 | 2023-01-05 | 2023-04-05 | 2023-04-27 | 79
0 | EDHGSR1680 | HD-03 - STRUCTURAL MISCELLANEOUS DETAIL - IFC | 15 | 2022-12-15 | 2023-01-05 | 2023-08-09 | 2023-08-29 | 163
MISCELLANEOUS DELIVERABLES |  |  | 75 | 2022-09-22 | 2023-01-09 | 2023-01-11 | 2023-04-27 | 77
0 | EDHGSR2000 | HD-03 STRUCTURAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-11 | 2023-02-07 | 77
0 | EDHGSR2006 | HD-03 STRUCTURAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-22 | 2023-03-21 | 77
0 | EDHGSR2010 | HD-03 STRUCTURAL MISCELLANEOUS DELIVERABLES - IFC | 15 | 2022-12-19 | 2023-01-09 | 2023-04-05 | 2023-04-27 | 77
PIPELINE |  |  | 76 | 2022-08-09 | 2022-11-22 | 2023-01-10 | 2023-04-27 | 108
DRAWINGS |  |  | 76 | 2022-08-09 | 2022-11-22 | 2023-01-10 | 2023-04-27 | 108
0 | DEP1PL4880 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA WHP HD-T3 - ICR | 16 | 2022-08-09 | 2022-08-30 | 2023-01-10 | 2023-01-31 | 108
0 | DEP1PL4920 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA WHP HD-T3 - IFA | 16 | 2022-09-14 | 2022-10-05 | 2023-02-15 | 2023-03-08 | 108
0 | DEP1PL4870 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA WHP HD-T3 - IFC | 24 | 2022-10-20 | 2022-11-22 | 2023-03-23 | 2023-04-27 | 108
NAVAL & ARCHITECTURE |  |  | 154 | 2022-04-12 | 2022-11-22 | 2022-07-28 | 2023-04-27 | 109
DOCUMENTS |  |  | 154 | 2022-04-12 | 2022-11-22 | 2022-07-28 | 2023-04-27 | 109
0 | EDHDNA1000 | HD-03 TOPSIDE -WEIGHT & COG CALCULATION - ICR | 20 | 2022-04-12 | 2022-05-13 | 2022-07-28 | 2022-08-24 | 71
0 | EDHDNA1005 | HD-03 TOPSIDE -WEIGHT & COG CALCULATION - IFA | 20 | 2022-05-27 | 2022-06-24 | 2022-09-08 | 2022-10-05 | 71
0 | EDHDNA1020 | HD-3 JACKET -WEIGHT & COG CALCULATION - ICR | 20 | 2022-06-09 | 2022-07-07 | 2023-01-04 | 2023-01-31 | 144
0 | EDHDNA1010 | HD-03 TOPSIDE -WEIGHT & COG CALCULATION - IFC | 25 | 2022-07-13 | 2022-08-17 | 2022-10-20 | 2022-11-23 | 71
0 | EDHDNA1030 | HD-3 JACKET -WEIGHT & COG CALCULATION - IFA | 20 | 2022-09-13 | 2022-10-11 | 2023-02-15 | 2023-03-14 | 109
0 | EDHDNA1040 | HD-3 JACKET -WEIGHT & COG CALCULATION - IFC | 20 | 2022-10-25 | 2022-11-22 | 2023-03-29 | 2023-04-27 | 109
IGD-E TOWER (EXISTING) |  |  | 367 | 2022-01-17 | 2023-01-19 | 2022-03-30 | 2023-06-30 | 163
PROCESS |  |  | 252 | 2022-01-17 | 2023-01-16 | 2022-03-30 | 2023-04-27 | 72
DOCUMENTS |  |  | 82 | 2022-03-08 | 2022-07-05 | 2022-05-19 | 2023-01-11 | 132
PROCESS SIMULATIONS & REPORTS |  |  | 62 | 2022-03-15 | 2022-06-14 | 2022-08-05 | 2022-11-08 | 103
0 | EDIDPR1000 | ALARM AND TRIP SCHEDULE (IGD-E (KP038) TOWER) - ICR | 15 | 2022-03-15 | 2022-04-05 | 2022-08-05 | 2022-08-25 | 97
0 | EDIDPR1005 | ALARM AND TRIP SCHEDULE (IGD-E (KP038) TOWER) - IFA | 12 | 2022-04-19 | 2022-05-10 | 2022-09-19 | 2022-10-04 | 103
0 | EDIDPR1010 | ALARM AND TRIP SCHEDULE (IGD-E (KP038) TOWER) - IFC | 15 | 2022-05-24 | 2022-06-14 | 2022-10-19 | 2022-11-08 | 103
PROCESS LISTS |  |  | 69 | 2022-03-08 | 2022-06-16 | 2022-06-08 | 2022-11-28 | 115
0 | EDIDPR1015 | EQUIPMENT LIST (IGD-E (KP038) TOWER) - ICR | 10 | 2022-03-08 | 2022-03-22 | 2022-06-08 | 2022-06-21 | 63
0 | EDIDPR1030 | LINE LIST (IGD-E (KP038) TOWER) - ICR | 10 | 2022-03-15 | 2022-03-29 | 2022-07-06 | 2022-07-22 | 78
0 | EDIDPR1045 | TIE-IN LIST (IGD-E (KP038) TOWER) - ICR | 10 | 2022-03-21 | 2022-04-04 | 2022-08-02 | 2022-08-16 | 90
0 | EDIDPR1020 | EQUIPMENT LIST (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-05 | 2022-04-19 | 2022-07-06 | 2022-07-22 | 63
0 | EDIDPR1035 | LINE LIST (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-12 | 2022-04-26 | 2022-08-25 | 2022-09-07 | 91
0 | EDIDPR1050 | TIE-IN LIST (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-18 | 2022-05-05 | 2022-08-30 | 2022-09-13 | 90
0 | EDIDPR1025 | EQUIPMENT LIST (IGD-E (KP038) TOWER) - IFC | 15 | 2022-05-06 | 2022-05-27 | 2022-11-08 | 2022-11-28 | 129
0 | EDIDPR1040 | LINE LIST (IGD-E (KP038) TOWER) - IFC | 20 | 2022-05-13 | 2022-06-10 | 2022-09-22 | 2022-10-19 | 91
0 | EDIDPR1055 | TIE-IN LIST (IGD-E (KP038) TOWER) - IFC | 20 | 2022-05-19 | 2022-06-16 | 2022-09-27 | 2022-10-25 | 90
PREPARATION OF DATASHEETS |  |  | 77 | 2022-03-15 | 2022-07-05 | 2022-05-19 | 2023-01-11 | 132
0 | EDIDPR1225 | PROCESS DATA SHEET EXPORT GAS PIG RECEIVER (IGD-E (KP038) TOWER) - ICR | 4 | 2022-03-15 | 2022-03-21 | 2022-05-24 | 2022-05-27 | 47
0 | EDIDPR1060 | PROCESS DATA SHEET MOTOR OPERATED VALVES (IGD-E (KP038) TOWER) - ICR | 7 | 2022-03-15 | 2022-03-24 | 2022-05-19 | 2022-05-27 | 44
0 | EDIDPR1210 | PROCESS DATA SHEET VENT / DRAIN DRUM (IGD-E (KP038) TOWER) - ICR | 5 | 2022-03-18 | 2022-03-25 | 2022-06-29 | 2022-07-05 | 70
0 | EDIDPR1090 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (IGD-E (KP038) TOWER) - ICR | 7 | 2022-03-22 | 2022-03-31 | 2022-08-12 | 2022-08-22 | 97
0 | EDIDPR1075 | PROCESS DATASHEET SHUTDOWN VALVES (IGD-E (KP038) TOWER) - ICR | 10 | 2022-03-17 | 2022-03-31 | 2022-05-23 | 2022-06-03 | 44
0 | EDIDPR1105 | PROCESS DATASHEET PRESSURE GAUGES (IGD-E (KP038) TOWER) - ICR | 9 | 2022-03-28 | 2022-04-08 | 2022-08-18 | 2022-08-30 | 97
0 | EDIDPR1135 | PROCESS DATASHEET TEMPERATURE GAUGE (IGD-E (KP038) TOWER) - ICR | 9 | 2022-03-28 | 2022-04-08 | 2022-08-19 | 2022-08-31 | 98
0 | EDIDPR1120 | PROCESS DATASHEET PRESSURE INSTRUMENT (IGD-E (KP038) TOWER) - ICR | 10 | 2022-03-28 | 2022-04-11 | 2022-08-18 | 2022-08-31 | 97
0 | EDIDPR1150 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (IGD-E (KP038) TOWER) - ICR | 10 | 2022-03-30 | 2022-04-13 | 2022-08-23 | 2022-09-05 | 98
0 | EDIDPR1180 | PROCESS DATASHEET LEVEL INSTRUMENT (IGD-E (KP038) TOWER) - ICR | 7 | 2022-04-05 | 2022-04-14 | 2022-09-20 | 2022-09-28 | 114
0 | EDIDPR1165 | PROCESS DATASHEET LEVEL GAUGE (IGD-E (KP038) TOWER) - ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-08-30 | 2022-09-12 | 101
0 | EDIDPR1230 | PROCESS DATA SHEET EXPORT GAS PIG RECEIVER (IGD-E (KP038) TOWER) - IFA | 9 | 2022-04-04 | 2022-04-15 | 2022-06-22 | 2022-07-04 | 54
0 | EDIDPR1240 | PROCESS DATA SHEET RESTRICTION ORIFICES (IGD-E (KP038) TOWER) - ICR | 10 | 2022-04-06 | 2022-04-20 | 2022-06-24 | 2022-07-07 | 54
0 | EDIDPR1195 | PROCESS DATASHEET FLOW SWITCH (IGD-E (KP038) TOWER) - ICR | 10 | 2022-04-07 | 2022-04-21 | 2022-10-11 | 2022-10-24 | 127
0 | EDIDPR1065 | PROCESS DATA SHEET MOTOR OPERATED VALVES (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-07 | 2022-04-21 | 2022-06-23 | 2022-07-06 | 52
0 | EDIDPR1215 | PROCESS DATA SHEET VENT / DRAIN DRUM (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-08 | 2022-04-22 | 2022-10-17 | 2022-10-28 | 130
0 | EDIDPR1255 | PROCESS DATA SHEET ULTRASONIC FLOWMETER (IGD-E (KP038) TOWER) - ICR | 8 | 2022-04-12 | 2022-04-22 | 2022-06-30 | 2022-07-14 | 54
0 | EDIDPR1095 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-14 | 2022-04-28 | 2022-09-29 | 2022-10-12 | 114
0 | EDIDPR1080 | PROCESS DATASHEET SHUTDOWN VALVES (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-14 | 2022-04-28 | 2022-06-22 | 2022-07-05 | 46
0 | EDIDPR1110 | PROCESS DATASHEET PRESSURE GAUGES (IGD-E (KP038) TOWER) - IFA | 9 | 2022-04-22 | 2022-05-10 | 2022-10-07 | 2022-10-19 | 114
0 | EDIDPR1140 | PROCESS DATASHEET TEMPERATURE GAUGE (IGD-E (KP038) TOWER) - IFA | 9 | 2022-04-22 | 2022-05-10 | 2022-10-04 | 2022-10-14 | 111
0 | EDIDPR1125 | PROCESS DATASHEET PRESSURE INSTRUMENT (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-25 | 2022-05-12 | 2022-09-19 | 2022-09-30 | 99
0 | EDIDPR1155 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-27 | 2022-05-16 | 2022-09-20 | 2022-10-03 | 98
0 | EDIDPR1185 | PROCESS DATASHEET LEVEL INSTRUMENT (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-11-15 | 2022-11-28 | 137
0 | EDIDPR1170 | PROCESS DATASHEET LEVEL GAUGE (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-09-27 | 2022-10-10 | 101
0 | EDIDPR1245 | PROCESS DATA SHEET RESTRICTION ORIFICES (IGD-E (KP038) TOWER) - IFA | 10 | 2022-05-09 | 2022-05-23 | 2022-09-09 | 2022-09-22 | 86
0 | EDIDPR1260 | PROCESS DATA SHEET ULTRASONIC FLOWMETER (IGD-E (KP038) TOWER) - IFA | 8 | 2022-05-11 | 2022-05-23 | 2022-07-29 | 2022-08-09 | 54
0 | EDIDPR1070 | PROCESS DATA SHEET MOTOR OPERATED VALVES (IGD-E (KP038) TOWER) - IFC | 10 | 2022-05-10 | 2022-05-24 | 2022-07-26 | 2022-08-08 | 52
0 | EDIDPR1200 | PROCESS DATASHEET FLOW SWITCH (IGD-E (KP038) TOWER) - IFA | 10 | 2022-05-10 | 2022-05-24 | 2022-11-11 | 2022-11-24 | 130
0 | EDIDPR1235 | PROCESS DATA SHEET EXPORT GAS PIG RECEIVER (IGD-E (KP038) TOWER) - IFC | 19 | 2022-04-29 | 2022-05-31 | 2022-12-13 | 2023-01-06 | 154
0 | EDIDPR1220 | PROCESS DATA SHEET VENT / DRAIN DRUM (IGD-E (KP038) TOWER) - IFC | 20 | 2022-05-11 | 2022-06-08 | 2022-11-14 | 2022-12-13 | 130
0 | EDIDPR1100 | PROCESS DATA SHEET PRESSURE SAFETY RELIEF VALVES (IGD-E (KP038) TOWER) - IFC | 20 | 2022-05-17 | 2022-06-14 | 2022-10-27 | 2022-11-23 | 114
0 | EDIDPR1085 | PROCESS DATASHEET SHUTDOWN VALVES (IGD-E (KP038) TOWER) - IFC | 20 | 2022-05-17 | 2022-06-14 | 2022-07-25 | 2022-08-19 | 46
0 | EDIDPR1115 | PROCESS DATASHEET PRESSURE GAUGES (IGD-E (KP038) TOWER) - IFC | 19 | 2022-05-24 | 2022-06-20 | 2022-11-03 | 2022-11-29 | 114
0 | EDIDPR1145 | PROCESS DATASHEET TEMPERATURE GAUGE (IGD-E (KP038) TOWER) - IFC | 19 | 2022-05-24 | 2022-06-20 | 2022-10-31 | 2022-11-24 | 111
0 | EDIDPR1265 | PROCESS DATA SHEET ULTRASONIC FLOWMETER (IGD-E (KP038) TOWER) - IFC | 10 | 2022-06-06 | 2022-06-20 | 2022-08-24 | 2022-09-06 | 54
0 | EDIDPR1130 | PROCESS DATASHEET PRESSURE INSTRUMENT (IGD-E (KP038) TOWER) - IFC | 20 | 2022-05-26 | 2022-06-23 | 2022-10-17 | 2022-11-11 | 99
0 | EDIDPR1160 | PROCESS DATASHEET TEMPERATURE INSTRUMENT (IGD-E (KP038) TOWER) - IFC | 20 | 2022-05-30 | 2022-06-27 | 2022-10-18 | 2022-11-14 | 98
0 | EDIDPR1190 | PROCESS DATASHEET LEVEL INSTRUMENT (IGD-E (KP038) TOWER) - IFC | 20 | 2022-05-31 | 2022-06-28 | 2022-12-15 | 2023-01-11 | 137
0 | EDIDPR1175 | PROCESS DATASHEET LEVEL GAUGE (IGD-E (KP038) TOWER) - IFC | 19 | 2022-06-01 | 2022-06-28 | 2022-10-25 | 2022-11-18 | 101
0 | EDIDPR1250 | PROCESS DATA SHEET RESTRICTION ORIFICES (IGD-E (KP038) TOWER) - IFC | 20 | 2022-06-06 | 2022-07-04 | 2022-10-07 | 2022-11-03 | 86
0 | EDIDPR1205 | PROCESS DATASHEET FLOW SWITCH (IGD-E (KP038) TOWER) - IFC | 20 | 2022-06-07 | 2022-07-05 | 2022-12-13 | 2023-01-09 | 130
DRAWINGS |  |  | 192 | 2022-01-17 | 2022-10-20 | 2022-03-30 | 2023-01-24 | 67
PFD / UFD / DPDT / PSFS & HMB |  |  | 77 | 2022-01-17 | 2022-05-09 | 2022-03-30 | 2022-12-21 | 158
0 | EDIGPR1015 | HEAT AND MATERIAL BALANCE - (IGD-E (KP038) TOWER) - ICR | 13 | 2022-01-17 | 2022-02-03 | 2022-03-30 | 2022-04-15 | 52
0 | EDIGPR1000 | PFD's - (IGD-E (KP038) TOWER) TOWER GAS EXPORT TIE-IN - ICR | 15 | 2022-01-17 | 2022-02-07 | 2022-03-31 | 2022-04-20 | 53
0 | EDIGPR1030 | DPDT DIAGRAMS - (IGD-E (KP038) TOWER) - TOWER GAS EXPORT TIE-IN - ICR | 20 | 2022-01-24 | 2022-02-21 | 2022-04-07 | 2022-05-09 | 53
0 | EDIGPR1045 | PSFS's - (IGD-E (KP038) TOWER) - TOWER GAS EXPORT TIE-IN - ICR | 20 | 2022-01-26 | 2022-02-23 | 2022-04-07 | 2022-05-09 | 51
0 | EDIGPR1020 | HEAT AND MATERIAL BALANCE - (IGD-E (KP038) TOWER) - IFA | 14 | 2022-02-17 | 2022-03-09 | 2022-06-07 | 2022-06-24 | 75
0 | EDIGPR1005 | PFD's - (IGD-E (KP038) TOWER) TOWER GAS EXPORT TIE-IN - IFA | 15 | 2022-02-21 | 2022-03-14 | 2022-08-08 | 2022-08-26 | 114
0 | EDIGPR1035 | DPDT DIAGRAMS - (IGD-E (KP038) TOWER) - TOWER GAS EXPORT TIE-IN - IFA | 9 | 2022-03-07 | 2022-03-18 | 2022-10-26 | 2022-11-07 | 161
0 | EDIGPR1050 | PSFS's - (IGD-E (KP038) TOWER) - TOWER GAS EXPORT TIE-IN - IFA | 9 | 2022-03-07 | 2022-03-18 | 2022-10-28 | 2022-11-09 | 163
0 | EDIGPR1025 | HEAT AND MATERIAL BALANCE - (IGD-E (KP038) TOWER) - IFC | 20 | 2022-03-23 | 2022-04-20 | 2022-07-14 | 2022-08-10 | 75
0 | EDIGPR1010 | PFD's - (IGD-E (KP038) TOWER) TOWER GAS EXPORT TIE-IN - IFC | 20 | 2022-03-28 | 2022-04-25 | 2022-11-07 | 2022-12-06 | 154
0 | EDIGPR1040 | DPDT DIAGRAMS - (IGD-E (KP038) TOWER) - TOWER GAS EXPORT TIE-IN - IFC | 20 | 2022-04-05 | 2022-05-06 | 2022-11-22 | 2022-12-21 | 159
0 | EDIGPR1055 | PSFS's - (IGD-E (KP038) TOWER) - TOWER GAS EXPORT TIE-IN - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-11-22 | 2022-12-21 | 158
PIPING & INSTRUMENTATION DIAGRAMS |  |  | 177 | 2022-02-07 | 2022-10-20 | 2022-04-14 | 2023-01-24 | 67
0 | EDIGPR1060 | P&ID - DRAWING INDEX (IGD-E (KP038) TOWER) - ICR | 17 | 2022-02-07 | 2022-03-02 | 2022-04-21 | 2022-05-18 | 53
0 | EDIGPR1075 | P&IDs - (IGD-E (KP038) TOWER) - ICR | 22 | 2022-02-11 | 2022-03-15 | 2022-04-14 | 2022-05-18 | 44
0 | EDIGPR1080 | P&IDs - (IGD-E (KP038) TOWER) - ISSUED FOR HAZOP | 25 | 2022-04-05 | 2022-05-13 | 2022-07-07 | 2022-08-15 | 64
0 | EDIGPR1085 | P&IDs - (IGD-E (KP038) TOWER) - IFA | 25 | 2022-06-16 | 2022-07-26 | 2022-08-30 | 2022-10-03 | 50
0 | EDIGPR1065 | P&ID - DRAWING INDEX (IGD-E (KP038) TOWER) - IFA | 25 | 2022-06-16 | 2022-07-26 | 2022-10-31 | 2022-12-06 | 94
0 | EDIGPR1090 | P&IDs - (IGD-E (KP038) TOWER) - IFC | 25 | 2022-09-15 | 2022-10-20 | 2022-11-29 | 2023-01-04 | 53
0 | EDIGPR1070 | P&ID - DRAWING INDEX (IGD-E (KP038) TOWER) - IFC | 25 | 2022-09-15 | 2022-10-20 | 2022-12-21 | 2023-01-24 | 67
CAUSE & EFFECT & SAFE CHARTS |  |  | 75 | 2022-03-25 | 2022-07-18 | 2022-07-18 | 2022-12-26 | 114
0 | EDIGPR1095 | CAUSE & EFFECT CHARTS - (IGD-E (KP038) TOWER) - ICR | 10 | 2022-03-25 | 2022-04-08 | 2022-07-18 | 2022-07-29 | 75
0 | EDIGPR1110 | SAFE CHART - (IGD-E (KP038) TOWER) - ICR | 10 | 2022-04-08 | 2022-04-22 | 2022-08-30 | 2022-09-12 | 96
0 | EDIGPR1100 | CAUSE & EFFECT CHARTS - (IGD-E (KP038) TOWER) - IFA | 10 | 2022-04-22 | 2022-05-11 | 2022-08-15 | 2022-08-26 | 75
0 | EDIGPR1115 | SAFE CHART - (IGD-E (KP038) TOWER) - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-09-27 | 2022-10-10 | 96
0 | EDIGPR1120 | SAFE CHART - (IGD-E (KP038) TOWER) - IFC | 25 | 2022-06-08 | 2022-07-18 | 2022-10-25 | 2022-11-28 | 96
0 | EDIGPR1105 | CAUSE & EFFECT CHARTS - (IGD-E (KP038) TOWER) - IFC | 35 | 2022-05-25 | 2022-07-18 | 2022-11-04 | 2022-12-26 | 114
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDIGPR2000 | IGD-E PROCESS MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDIGPR2005 | IGD-E PROCESS MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDIGPR2010 | IGD-E PROCESS MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
MATERIAL & CORROSION |  |  | 239 | 2022-02-03 | 2023-01-16 | 2022-04-18 | 2023-04-27 | 72
DOCUMENTS |  |  | 60 | 2022-08-22 | 2022-11-14 | 2022-10-31 | 2023-01-24 | 50
0 | EDIDMA1000 | DEADLEG REGISTER--KP - IGD-E TIE-IN PLATFORM KP38 TOWER - ICR | 15 | 2022-08-22 | 2022-09-12 | 2022-10-31 | 2022-11-18 | 50
0 | EDIDMA1005 | DEADLEG REGISTER--KP - IGD-E TIE-IN PLATFORM KP38 TOWER - IFA | 15 | 2022-09-26 | 2022-10-17 | 2022-12-07 | 2022-12-27 | 50
0 | EDIDMA1010 | DEADLEG REGISTER--KP - IGD-E TIE-IN PLATFORM KP38 TOWER - IFC | 10 | 2022-10-31 | 2022-11-14 | 2023-01-11 | 2023-01-24 | 50
DRAWINGS |  |  | 75 | 2022-02-03 | 2022-05-24 | 2022-04-18 | 2022-11-28 | 132
0 | EDIGMA1000 | MATERIAL SELECTION DIAGRAMS - IGD-E (KP038) TOWER - ICR | 15 | 2022-02-03 | 2022-02-24 | 2022-04-18 | 2022-05-11 | 52
0 | EDIGMA1005 | MATERIAL SELECTION DIAGRAMS - IGD-E (KP038) TOWER - IFA | 15 | 2022-03-10 | 2022-03-31 | 2022-08-09 | 2022-08-29 | 102
0 | EDIGMA1010 | MATERIAL SELECTION DIAGRAMS - IGD-E (KP038) TOWER - IFC | 25 | 2022-04-14 | 2022-05-24 | 2022-10-25 | 2022-11-28 | 132
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDIGMA2000 | IGD-E MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDIGMA2005 | IGD-E MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDIGMA2010 | IGD-E MATERIAL & CORROSION MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
SAFETY |  |  | 245 | 2022-05-16 | 2023-01-16 | 2022-08-23 | 2023-04-27 | 102
DRAWINGS |  |  | 142 | 2022-05-16 | 2022-10-05 | 2022-08-23 | 2023-04-18 | 196
0 | EDIGSA1000 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - (IGD-E (KP038) TOWER) - ICR | 10 | 2022-05-16 | 2022-05-30 | 2022-08-23 | 2022-09-05 | 68
0 | EDIGSA1015 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - (IGD-E (KP038) TOWER) - ICR | 10 | 2022-06-17 | 2022-07-01 | 2022-09-30 | 2022-10-13 | 72
0 | EDIGSA1005 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - (IGD-E (KP038) TOWER) - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-10-25 | 2022-11-07 | 91
0 | EDIGSA1045 | FIRE AND GAS CAUSE & EFFECT CHART – (IGD-E (KP038) TOWER) - ICR | 15 | 2022-07-01 | 2022-07-27 | 2022-10-26 | 2022-11-15 | 80
0 | EDIGSA1030 | H2S ZONE LAYOUT - (IGD-E (KP038) TOWER) - ICR | 15 | 2022-07-20 | 2022-08-10 | 2023-02-01 | 2023-02-21 | 138
0 | EDIGSA1020 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - (IGD-E (KP038) TOWER) - IFA | 10 | 2022-07-27 | 2022-08-10 | 2022-12-01 | 2022-12-14 | 91
0 | EDIGSA1050 | FIRE AND GAS CAUSE & EFFECT CHART – (IGD-E (KP038) TOWER) - IFA | 10 | 2022-08-10 | 2022-08-24 | 2022-11-30 | 2022-12-13 | 80
0 | EDIGSA1010 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUT - (IGD-E (KP038) TOWER) - IFC | 15 | 2022-08-11 | 2022-09-01 | 2022-12-29 | 2023-01-18 | 98
0 | EDIGSA1035 | H2S ZONE LAYOUT - (IGD-E (KP038) TOWER) - IFA | 10 | 2022-08-24 | 2022-09-07 | 2023-03-08 | 2023-03-21 | 140
0 | EDIGSA1025 | FIRE ZONE AND FIRE & GAS DETECTION LAYOUT - (IGD-E (KP038) TOWER) - IFC | 15 | 2022-09-07 | 2022-09-28 | 2022-12-29 | 2023-01-18 | 79
0 | EDIGSA1055 | FIRE AND GAS CAUSE & EFFECT CHART – (IGD-E (KP038) TOWER) - IFC | 16 | 2022-09-07 | 2022-09-29 | 2022-12-28 | 2023-01-18 | 78
0 | EDIGSA1040 | H2S ZONE LAYOUT - (IGD-E (KP038) TOWER) - IFC | 10 | 2022-09-21 | 2022-10-05 | 2023-04-05 | 2023-04-18 | 138
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDIGSA2000 | IGD-E SAFETY MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDIGSA2005 | IGD-E SAFETY MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDIGSA2010 | IGD-E SAFETY MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
PIPING |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-05-25 | 2023-06-06 | 97
3D MODELING |  |  | 166 | 2022-05-25 | 2023-01-19 | 2022-08-11 | 2023-04-27 | 69
30% MODEL REVIEW/REPORT |  |  | 50 | 2022-05-25 | 2022-08-08 | 2022-08-11 | 2022-11-01 | 62
0 | EDIDPI3100 | IGD-E 30% 3D MODEL REVIEW REPORT - ICR | 10 | 2022-05-25 | 2022-06-08 | 2022-08-11 | 2022-08-24 | 53
0 | EDIDPI3105 | IGD-E 30% 3D MODEL REVIEW REPORT - IFA | 10 | 2022-06-22 | 2022-07-06 | 2022-09-21 | 2022-10-04 | 62
0 | EDIDPI3110 | IGD-E 30% 3D MODEL REVIEW REPORT - IFC | 10 | 2022-07-25 | 2022-08-08 | 2022-10-19 | 2022-11-01 | 62
60% MODEL REVIEW/REPORT |  |  | 60 | 2022-08-26 | 2022-11-18 | 2022-11-02 | 2023-04-20 | 108
0 | EDIDPI3120 | IGD-E 60% 3D MODEL REVIEW REPORT - ICR | 10 | 2022-08-26 | 2022-09-09 | 2022-11-02 | 2022-11-15 | 48
0 | EDIDPI3125 | IGD-E 60% 3D MODEL REVIEW REPORT - IFA | 10 | 2022-09-23 | 2022-10-07 | 2022-12-30 | 2023-01-12 | 68
0 | EDIDPI3130 | IGD-E 60% 3D MODEL REVIEW REPORT - IFC | 20 | 2022-10-21 | 2022-11-18 | 2023-03-24 | 2023-04-20 | 108
90% MODEL REVIEW/REPORT |  |  | 41 | 2022-11-21 | 2023-01-19 | 2023-03-01 | 2023-04-27 | 69
0 | EDIDPI3140 | IGD-E 90% 3D MODEL REVIEW REPORT - ICR | 8 | 2022-11-21 | 2022-12-05 | 2023-03-01 | 2023-03-10 | 70
0 | EDIDPI3145 | IGD-E 90% 3D MODEL REVIEW REPORT - IFA | 9 | 2022-12-19 | 2022-12-30 | 2023-03-27 | 2023-04-06 | 70
0 | EDIDPI3150 | IGD-E 90% 3D MODEL REVIEW REPORT - IFC | 3 | 2023-01-16 | 2023-01-19 | 2023-04-25 | 2023-04-27 | 69
3D MODEL DEVELOPMENT |  |  | 200 | 2022-04-04 | 2023-01-19 | 2022-07-18 | 2023-04-27 | 69
0 | EDIDPI3000 | IGD-E 3D MODEL DEVELOPMENT - PIPING | 200 | 2022-04-04 | 2023-01-19 | 2022-07-18 | 2023-04-27 | 69
DOCUMENTS |  |  | 203 | 2022-03-29 | 2023-01-18 | 2022-07-14 | 2023-06-06 | 98
REPORTS & CALCULATIONS |  |  | 203 | 2022-03-29 | 2023-01-18 | 2022-07-14 | 2023-06-06 | 98
0 | EDIDPI1000 | IGD-E (KP038) TOWER PIPE STRESS CRITICAL LINE LIST - ICR | 15 | 2022-03-29 | 2022-04-19 | 2022-11-02 | 2022-11-22 | 150
0 | EDIDPI1045 | IGD-E (KP038) TOWER SURVEY REPORT - ICR | 15 | 2022-04-11 | 2022-05-05 | 2022-07-14 | 2022-08-03 | 62
0 | EDIDPI1005 | IGD-E (KP038) TOWER PIPE STRESS CRITICAL LINE LIST - IFA | 15 | 2022-05-06 | 2022-05-27 | 2022-12-09 | 2022-12-29 | 150
0 | EDIDPI1015 | IGD-E (KP038) TOWER PIPING STRESS ANALYSIS REPORT - ICR | 15 | 2022-05-19 | 2022-06-09 | 2022-11-30 | 2022-12-22 | 136
0 | EDIDPI1050 | IGD-E (KP038) TOWER SURVEY REPORT - IFA | 15 | 2022-05-19 | 2022-06-09 | 2022-08-18 | 2022-09-07 | 62
0 | EDIDPI1065 | IGD-E (KP038) MECHANICAL HANDLING STUDY REPORT - ICR | 10 | 2022-06-08 | 2022-06-22 | 2022-11-14 | 2022-11-25 | 110
0 | EDIDPI1010 | IGD-E (KP038) TOWER PIPE STRESS CRITICAL LINE LIST - IFC | 20 | 2022-06-10 | 2022-07-13 | 2023-01-13 | 2023-02-09 | 150
0 | EDIDPI1075 | IGD-E (KP038) MECHANICAL HANDLING STUDY REPORT - IFA | 10 | 2022-07-06 | 2022-07-25 | 2022-12-14 | 2022-12-27 | 110
0 | EDIDPI1030 | IGD-E (KP038) TOWER TIE-IN LIST INCL. SKETCHES & SCHEDULE - ICR | 10 | 2022-07-07 | 2022-07-26 | 2022-10-25 | 2022-11-08 | 75
0 | EDIDPI1055 | IGD-E (KP038) TOWER SURVEY REPORT - IFC | 20 | 2022-06-23 | 2022-07-26 | 2022-09-22 | 2022-10-19 | 62
0 | EDIDPI1085 | IGD-E (KP038) MECHANICAL HANDLING STUDY REPORT - IFC | 10 | 2022-08-08 | 2022-08-22 | 2023-01-11 | 2023-01-24 | 110
0 | EDIDPI1035 | IGD-E (KP038) TOWER TIE-IN LIST INCL. SKETCHES & SCHEDULE - IFA | 10 | 2022-08-09 | 2022-08-23 | 2022-11-22 | 2022-12-08 | 75
0 | EDIDPI1020 | IGD-E (KP038) TOWER PIPING STRESS ANALYSIS REPORT - IFA | 15 | 2022-08-22 | 2022-09-12 | 2023-01-06 | 2023-01-26 | 97
0 | EDIDPI1040 | IGD-E (KP038) TOWER TIE-IN LIST INCL. SKETCHES & SCHEDULE - IFC | 9 | 2022-09-06 | 2022-09-19 | 2022-12-22 | 2023-01-04 | 75
0 | EDIDPI1025 | IGD-E (KP038) TOWER PIPING STRESS ANALYSIS REPORT - IFC | 20 | 2022-11-21 | 2022-12-21 | 2023-02-10 | 2023-03-09 | 57
0 | EDIDPI1095 | IGD-E (KP038) PIPE SUPPORT SCHEDULE - IFI | 10 | 2022-12-07 | 2022-12-21 | 2023-04-26 | 2023-05-09 | 98
0 | EDIDPI1105 | IGD-E (KP038) PIPE SUPPORT SCHEDULE - IFC | 10 | 2023-01-04 | 2023-01-18 | 2023-05-24 | 2023-06-06 | 98
DRAWINGS |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-05-25 | 2023-06-06 | 97
0 | EDIGPI1000 | IGD-E (KP038) TOWER PLOT PLAN DRAWINGS - ICR | 30 | 2022-03-14 | 2022-04-25 | 2022-05-25 | 2022-07-05 | 48
0 | EDIGPI1015 | IGD-E (KP038) TOWER DEMOLITION PLOT PLAN DRAWINGS - ICR | 30 | 2022-03-18 | 2022-04-29 | 2022-06-14 | 2022-07-28 | 58
0 | EDIGPI1005 | IGD-E (KP038) TOWER PLOT PLAN DRAWINGS - IFA | 25 | 2022-05-13 | 2022-06-17 | 2022-08-23 | 2022-09-26 | 69
0 | EDIGPI1020 | IGD-E (KP038) TOWER DEMOLITION PLOT PLAN DRAWINGS - IFA | 25 | 2022-05-18 | 2022-06-22 | 2022-08-26 | 2022-09-29 | 68
0 | EDIGPI1025 | IGD-E (KP038) TOWER DEMOLITION PLOT PLAN DRAWINGS - IFC | 35 | 2022-07-06 | 2022-08-29 | 2022-11-15 | 2023-01-04 | 90
0 | EDIGPI1065 | IGD-E (KP038) SPECIAL SUPPORT DRAWINGS - ICR | 10 | 2022-11-21 | 2022-12-07 | 2023-04-07 | 2023-04-20 | 97
0 | EDIGPI1030 | IGD-E (KP038) TOWER ENGINEERING ISOMETRICS | 12 | 2022-11-21 | 2022-12-09 | 2023-02-28 | 2023-03-15 | 69
0 | EDIGPI1010 | IGD-E (KP038) TOWER PLOT PLAN DRAWINGS - IFC | 17 | 2022-11-21 | 2022-12-16 | 2023-03-27 | 2023-04-18 | 88
0 | EDIGPI1040 | IGD-E (KP038) TOWER PIPING GA DRAWING - IFI | 10 | 2022-11-30 | 2022-12-16 | 2023-03-22 | 2023-04-04 | 78
0 | EDIGPI1035 | IGD-E (KP038) TOWER ENGINEERING DEMOLITION ISOMETRICS | 20 | 2022-11-21 | 2022-12-21 | 2023-02-28 | 2023-03-27 | 69
0 | EDIGPI1050 | IGD-E (KP038) TOWER DEMOLITION PIPING GA DRAWING - IFI | 10 | 2022-12-15 | 2022-12-29 | 2023-03-22 | 2023-04-04 | 69
0 | EDIGPI1070 | IGD-E (KP038) SPECIAL SUPPORT DRAWINGS - IFA | 7 | 2022-12-21 | 2022-12-30 | 2023-05-09 | 2023-05-17 | 97
0 | EDIGPI1045 | IGD-E (KP038) TOWER PIPING GA DRAWING - IFC | 5 | 2022-12-30 | 2023-01-06 | 2023-04-19 | 2023-04-27 | 78
0 | EDIGPI1055 | IGD-E (KP038) TOWER DEMOTION PIPING GA DRAWING - IFC | 5 | 2023-01-12 | 2023-01-19 | 2023-04-19 | 2023-04-27 | 69
0 | EDIGPI1075 | IGD-E (KP038) SPECIAL SUPPORT DRAWINGS - IFC | 4 | 2023-01-13 | 2023-01-19 | 2023-06-01 | 2023-06-06 | 97
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDIGPI2000 | IGD-E PIPING MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDIGPI2005 | IGD-E PIPING MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDIGPI2010 | IGD-E PIPING MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
MECHANICAL (STATIC / ROTATING) |  |  | 207 | 2022-03-21 | 2023-01-16 | 2022-05-30 | 2023-04-27 | 72
STATIC |  |  | 207 | 2022-03-21 | 2023-01-16 | 2022-05-30 | 2023-04-27 | 72
DOCUMENTS |  |  | 127 | 2022-03-21 | 2022-09-22 | 2022-05-30 | 2023-01-10 | 77
CALCULATION |  |  | 65 | 2022-06-20 | 2022-09-22 | 2022-08-18 | 2022-12-30 | 70
0 | EDIDME1000 | IGD-E MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (KP-038-V-001) - ICR | 20 | 2022-06-20 | 2022-07-21 | 2022-08-18 | 2022-09-14 | 40
0 | EDIDME1005 | IGD-E MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (KP-038-V-001) - IFA | 15 | 2022-08-04 | 2022-08-25 | 2022-11-10 | 2022-11-30 | 70
0 | EDIDME1010 | MECHANICAL DESIGN CALCULATION FOR VENT DRAIN DRUM (KP-038-V-001) - IFC | 10 | 2022-09-08 | 2022-09-22 | 2022-12-19 | 2022-12-30 | 70
DATA SHEET |  |  | 74 | 2022-03-21 | 2022-07-06 | 2022-05-30 | 2023-01-10 | 130
0 | EDIDME1015 | IGD-E MECHANICAL DATA SHEET FOR GAS EXPORT PIG RECEIVER (KP038-RC-001) - ICR | 10 | 2022-03-21 | 2022-04-04 | 2022-05-30 | 2022-06-10 | 47
0 | EDIDME1030 | IGD-E MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (KP-038-V-001) - ICR | 10 | 2022-03-25 | 2022-04-08 | 2022-07-06 | 2022-07-22 | 70
0 | EDIDME1020 | IGD-E MECHANICAL DATA SHEET FOR GAS EXPORT PIG RECEIVER (KP038-RC-001) - IFA | 7 | 2022-04-18 | 2022-04-27 | 2022-06-27 | 2022-07-05 | 47
0 | EDIDME1035 | IGD-E MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (KP-038-V-001) - IFA | 10 | 2022-04-22 | 2022-05-11 | 2022-11-14 | 2022-11-25 | 140
0 | EDIDME1025 | IGD-E MECHANICAL DATA SHEET FOR GAS EXPORT PIG RECEIVER (KP038-RC-001) - IFC | 3 | 2022-05-16 | 2022-05-19 | 2022-07-25 | 2022-07-27 | 47
0 | EDIDME1040 | IGD-E MECHANICAL DATA SHEET FOR VENT DRAIN DRUM (KP-038-V-001) - IFC | 20 | 2022-06-08 | 2022-07-06 | 2022-12-14 | 2023-01-10 | 130
DRAWINGS |  |  | 81 | 2022-07-28 | 2022-11-18 | 2022-09-22 | 2023-01-19 | 43
0 | EDIGME1000 | IGD-E G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.KP-038-V-001) - ICR | 10 | 2022-07-28 | 2022-08-11 | 2022-09-22 | 2022-10-05 | 40
0 | EDIGME1005 | IGD-E G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.KP-038-V-001) - IFA | 10 | 2022-08-25 | 2022-09-08 | 2022-11-14 | 2022-11-25 | 57
0 | EDIGME1015 | IGD-E DETAIL DRAWING FOR VENT DRAIN DRUM (KP-038-V-001) - IFI | 10 | 2022-08-26 | 2022-09-09 | 2022-10-21 | 2022-11-03 | 40
0 | EDIGME1045 | IGD-E NOZZLE DETAIL (TAG NO. KP-038-V-001) - IFI | 10 | 2022-09-01 | 2022-09-15 | 2022-10-27 | 2022-11-09 | 40
0 | EDIGME1030 | IGD-E WELDING DETAIL & WELD MAP (TAG NO. KP-038-V-001) - IFI | 10 | 2022-09-07 | 2022-09-21 | 2022-11-02 | 2022-11-15 | 40
0 | EDIGME1060 | IGD-E MANWAY DAVIT DETAIL (TAG NO. KP-038-V-001) - IFI | 9 | 2022-09-13 | 2022-09-26 | 2022-11-08 | 2022-11-18 | 40
0 | EDIGME1075 | IGD-E INTERNAL / EXTERNAL ATTACHMENTS (TAG NO. KP-038-V-001) - IFI | 10 | 2022-09-19 | 2022-10-03 | 2022-11-14 | 2022-11-25 | 40
0 | EDIGME1090 | IGD-E NAME PLATE DETAIL (TAG NO. KP-038-V-001) - IFI | 10 | 2022-09-23 | 2022-10-07 | 2022-11-23 | 2022-12-08 | 43
0 | EDIGME1025 | IGD-E DETAIL DRAWING FOR VENT DRAIN DRUM (KP-038-V-001) - IFC | 15 | 2022-09-23 | 2022-10-14 | 2022-12-05 | 2022-12-23 | 49
0 | EDIGME1010 | IGD-E G.A DRAWING FOR VENT DRAIN DRUM (TAG NO.KP-038-V-001) - IFC | 20 | 2022-09-22 | 2022-10-20 | 2022-12-14 | 2023-01-10 | 57
0 | EDIGME1055 | IGD-E NOZZLE DETAIL (TAG NO. KP-038-V-001) - IFC | 20 | 2022-09-29 | 2022-10-27 | 2022-12-14 | 2023-01-10 | 52
0 | EDIGME1040 | IGD-E WELDING DETAIL & WELD MAP (TAG NO. KP-038-V-001) - IFC | 20 | 2022-10-05 | 2022-11-02 | 2022-12-14 | 2023-01-10 | 48
0 | EDIGME1070 | IGD-E MANWAY DAVIT DETAIL (TAG NO. KP-038-V-001) - IFC | 19 | 2022-10-10 | 2022-11-04 | 2022-12-15 | 2023-01-10 | 46
0 | EDIGME1085 | IGD-E INTERNAL / EXTERNAL ATTACHMENTS (TAG NO. KP-038-V-001) - IFC | 20 | 2022-10-17 | 2022-11-14 | 2022-12-14 | 2023-01-10 | 40
0 | EDIGME1100 | IGD-E NAME PLATE DETAIL (TAG NO. KP-038-V-001) - IFC | 20 | 2022-10-21 | 2022-11-18 | 2022-12-23 | 2023-01-19 | 43
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDIGME2000 | IGD-E MECHANICAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDIGME2005 | IGD-E MECHANICAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDIGME2010 | IGD-E MECHANICAL MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
PACKAGE EQUIPMENT |  |  | 47 | 2022-03-24 | 2022-06-02 | 2022-06-20 | 2022-09-07 | 67
DOCUMENTS |  |  | 47 | 2022-03-24 | 2022-06-02 | 2022-06-20 | 2022-09-07 | 67
DATASHEETS |  |  | 47 | 2022-03-24 | 2022-06-02 | 2022-06-20 | 2022-09-07 | 67
0 | EDIDME1045 | IGD-E MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - ICR | 9 | 2022-03-24 | 2022-04-06 | 2022-06-20 | 2022-06-30 | 59
0 | EDIDME1050 | IGD-E MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - IFA | 9 | 2022-04-20 | 2022-05-06 | 2022-08-01 | 2022-08-11 | 67
0 | EDIDME1055 | IGD-E MECHANICAL DATA SHEET FOR MATERIAL HANDLING EQUIPMENT - IFC | 9 | 2022-05-20 | 2022-06-02 | 2022-08-26 | 2022-09-07 | 67
ELECTRICAL |  |  | 198 | 2022-04-06 | 2023-01-19 | 2022-07-14 | 2023-04-27 | 69
3D MODEL DEVELOPMENT |  |  | 185 | 2022-04-25 | 2023-01-19 | 2022-08-08 | 2023-04-27 | 69
0 | EDIDEL3000 | IGD-E 3D MODEL DEVELOPMENT - ELECTRICAL | 185 | 2022-04-25 | 2023-01-19 | 2022-08-08 | 2023-04-27 | 69
DOCUMENTS |  |  | 90 | 2022-04-25 | 2022-09-06 | 2022-07-14 | 2023-04-04 | 149
LIST |  |  | 90 | 2022-04-25 | 2022-09-06 | 2022-07-14 | 2023-04-04 | 149
0 | EDIDEL1000 | IGD-E ELECTRICAL EQUIPMENT LIST - ICR | 15 | 2022-04-25 | 2022-05-19 | 2022-07-14 | 2022-08-03 | 52
0 | EDIDEL1015 | IGD-E ELECTRICAL LOAD LIST - ICR | 15 | 2022-05-05 | 2022-05-26 | 2022-07-21 | 2022-08-10 | 52
0 | EDIDEL1030 | ELECTRICAL POWER CHANGEOVER PHILOSOPHY IGD-E (KP038) WHP - ICR | 15 | 2022-05-26 | 2022-06-16 | 2022-11-28 | 2022-12-20 | 129
0 | EDIDEL1005 | IGD-E ELECTRICAL EQUIPMENT LIST - IFA | 15 | 2022-06-02 | 2022-06-23 | 2022-09-01 | 2022-09-21 | 62
0 | EDIDEL1020 | IGD-E ELECTRICAL LOAD LIST - IFA | 15 | 2022-06-09 | 2022-06-30 | 2022-09-08 | 2022-09-28 | 62
0 | EDIDEL1035 | ELECTRICAL POWER CHANGEOVER PHILOSOPHY IGD-E (KP038) WHP - IFA | 15 | 2022-06-30 | 2022-07-26 | 2023-01-04 | 2023-01-24 | 129
0 | EDIDEL1010 | IGD-E ELECTRICAL EQUIPMENT LIST - IFC | 20 | 2022-07-07 | 2022-08-09 | 2022-10-06 | 2022-11-02 | 62
0 | EDIDEL1025 | IGD-E ELECTRICAL LOAD LIST - IFC | 20 | 2022-07-19 | 2022-08-16 | 2022-10-13 | 2022-11-09 | 62
0 | EDIDEL1040 | ELECTRICAL POWER CHANGEOVER PHILOSOPHY IGD-E (KP038) WHP - IFC | 20 | 2022-08-09 | 2022-09-06 | 2023-03-08 | 2023-04-04 | 149
DRAWINGS |  |  | 197 | 2022-04-06 | 2023-01-18 | 2022-08-24 | 2023-04-27 | 70
DIAGRAM |  |  | 165 | 2022-04-06 | 2022-12-05 | 2022-08-24 | 2023-04-27 | 102
0 | EDIGEL1000 | IGD-E SINGLE LINE DIAGRAM – 6.6KV RMU - ICR | 15 | 2022-04-06 | 2022-04-27 | 2022-08-24 | 2022-09-13 | 94
0 | EDIGEL1015 | IGD-E SINGLE LINE DIAGRAM – 415V SWITCHBOARD - ICR | 15 | 2022-04-20 | 2022-05-16 | 2022-08-31 | 2022-09-20 | 89
0 | EDIGEL1030 | IGD-E SINGLE LINE DIAGRAM – 24V DC UPS - ICR | 15 | 2022-04-27 | 2022-05-23 | 2022-09-07 | 2022-09-27 | 89
0 | EDIGEL1045 | IGD-E SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - ICR | 15 | 2022-05-09 | 2022-05-30 | 2022-09-14 | 2022-10-04 | 89
0 | EDIGEL1005 | IGD-E SINGLE LINE DIAGRAM – 6.6KV RMU - IFA | 10 | 2022-05-16 | 2022-05-30 | 2022-10-24 | 2022-11-04 | 112
0 | EDIGEL1060 | IGD-E SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - ICR | 15 | 2022-05-16 | 2022-06-06 | 2022-09-21 | 2022-10-11 | 89
0 | EDIGEL1075 | IGD-E SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - ICR | 15 | 2022-05-23 | 2022-06-13 | 2022-10-03 | 2022-10-21 | 92
0 | EDIGEL1020 | IGD-E SINGLE LINE DIAGRAM – 415V SWITCHBOARD - IFA | 10 | 2022-05-30 | 2022-06-13 | 2022-10-24 | 2022-11-04 | 102
0 | EDIGEL1035 | IGD-E SINGLE LINE DIAGRAM – 24V DC UPS - IFA | 10 | 2022-06-06 | 2022-06-20 | 2022-10-24 | 2022-11-04 | 97
0 | EDIGEL1050 | IGD-E SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - IFA | 10 | 2022-06-13 | 2022-06-27 | 2022-10-24 | 2022-11-04 | 92
0 | EDIGEL1010 | IGD-E SINGLE LINE DIAGRAM – 6.6KV RMU - IFC | 15 | 2022-06-13 | 2022-07-04 | 2022-11-21 | 2022-12-13 | 112
0 | EDIGEL1065 | IGD-E SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - IFA | 10 | 2022-06-20 | 2022-07-04 | 2022-10-26 | 2022-11-08 | 89
0 | EDIGEL1080 | IGD-E SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - IFA | 10 | 2022-06-27 | 2022-07-14 | 2022-11-07 | 2022-11-18 | 92
0 | EDIGEL1025 | IGD-E SINGLE LINE DIAGRAM – 415V SWITCHBOARD - IFC | 15 | 2022-06-27 | 2022-07-21 | 2022-11-21 | 2022-12-13 | 102
0 | EDIGEL1040 | IGD-E SINGLE LINE DIAGRAM – 24V DC UPS - IFC | 15 | 2022-07-04 | 2022-07-28 | 2022-11-21 | 2022-12-13 | 97
0 | EDIGEL1055 | IGD-E SINGLE LINE DIAGRAM – EMERGENCY LIGHTING DISTRIBUTION BOARD - IFC | 15 | 2022-07-14 | 2022-08-04 | 2022-11-21 | 2022-12-13 | 92
0 | EDIGEL1070 | IGD-E SINGLE LINE DIAGRAM – AUXILIARY POWER DISTRIBUTION BOARD - IFC | 13 | 2022-07-21 | 2022-08-09 | 2022-11-23 | 2022-12-13 | 89
0 | EDIGEL1085 | IGD-E SINGLE LINE DIAGRAM – MOV DISTRIBUTION BOARD - IFC | 15 | 2022-07-28 | 2022-08-18 | 2022-12-07 | 2022-12-27 | 92
0 | EDIGEL1090 | IGD-E ELECTRICAL CABLE SCHEDULE - ICR | 15 | 2022-08-01 | 2022-08-22 | 2023-01-04 | 2023-01-24 | 110
0 | EDIGEL1095 | IGD-E ELECTRICAL CABLE SCHEDULE - IFA | 10 | 2022-09-05 | 2022-09-19 | 2023-03-08 | 2023-03-21 | 130
0 | EDIGEL1105 | IGD-E ELECTRICAL INTERCONNECTION DIAGRAM - ICR | 15 | 2022-09-01 | 2022-09-22 | 2023-01-25 | 2023-02-14 | 102
0 | EDIGEL1100 | IGD-E ELECTRICAL CABLE SCHEDULE - IFC | 15 | 2022-10-03 | 2022-10-24 | 2023-04-05 | 2023-04-27 | 130
0 | EDIGEL2020 | IGD-E ELECTRICAL INTERCONNECTION DIAGRAM - IFA | 15 | 2022-10-06 | 2022-10-27 | 2023-03-01 | 2023-03-21 | 102
0 | EDIGEL1110 | IGD-E ELECTRICAL INTERCONNECTION DIAGRAM - IFC | 15 | 2022-11-10 | 2022-12-05 | 2023-04-05 | 2023-04-27 | 102
BOOKLET |  |  | 50 | 2022-11-07 | 2023-01-18 | 2023-02-15 | 2023-04-27 | 70
0 | EDIGEL1200 | IGD-E LIGHTING AND SMALL POWER CIRCUIT BOOKLET - IRC | 10 | 2022-11-07 | 2022-11-21 | 2023-02-15 | 2023-02-28 | 70
0 | EDIGEL2030 | IGD-E LIGHTING AND SMALL POWER CIRCUIT BOOKLET - IFA | 10 | 2022-12-07 | 2022-12-21 | 2023-03-15 | 2023-03-28 | 70
0 | EDIGEL1205 | IGD-E LIGHTING AND SMALL POWER CIRCUIT BOOKLET - IFC | 10 | 2023-01-04 | 2023-01-18 | 2023-04-12 | 2023-04-27 | 70
LAYOUT |  |  | 135 | 2022-05-05 | 2022-11-15 | 2022-10-25 | 2023-04-27 | 114
0 | EDIGEL1300 | IGD-E ELECTRICAL EQUIPMENT LAYOUT - ICR | 15 | 2022-05-05 | 2022-05-26 | 2022-10-25 | 2022-11-14 | 120
0 | EDIGEL1305 | IGD-E ELECTRICAL EQUIPMENT LAYOUT - IFA | 10 | 2022-06-09 | 2022-06-23 | 2022-11-29 | 2022-12-14 | 120
0 | EDIGEL1375 | IGD-E HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - ICR | 10 | 2022-08-09 | 2022-08-23 | 2023-01-25 | 2023-02-07 | 119
0 | EDIGEL1390 | IGD-E HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - ICR | 10 | 2022-08-10 | 2022-08-24 | 2023-02-15 | 2023-02-28 | 133
0 | EDIGEL1315 | IGD-E ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IRC | 15 | 2022-08-09 | 2022-08-30 | 2022-12-14 | 2023-01-03 | 89
0 | EDIGEL1330 | IGD-E ELECTRICAL CABLE ROUTING LAYOUT - IRC | 15 | 2022-08-16 | 2022-09-06 | 2022-12-21 | 2023-01-10 | 89
0 | EDIGEL1310 | IGD-E ELECTRICAL EQUIPMENT LAYOUT - IFC | 15 | 2022-08-22 | 2022-09-12 | 2022-12-29 | 2023-01-18 | 91
0 | EDIGEL1360 | IGD-E EARTHING & LIGHTNING PROTECTION LAYOUT - IRC | 15 | 2022-08-23 | 2022-09-13 | 2023-02-01 | 2023-02-21 | 114
0 | EDIGEL1345 | IGD-E LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IRC | 15 | 2022-08-23 | 2022-09-13 | 2022-12-28 | 2023-01-17 | 89
0 | EDIGEL1380 | IGD-E HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - IFA | 10 | 2022-09-06 | 2022-09-20 | 2023-03-01 | 2023-03-14 | 124
0 | EDIGEL1395 | IGD-E HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - IFA | 10 | 2022-09-07 | 2022-09-21 | 2023-03-15 | 2023-03-28 | 133
0 | EDIGEL2040 | IGD-E ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IFA | 15 | 2022-09-13 | 2022-10-04 | 2023-03-06 | 2023-03-24 | 122
0 | EDIGEL2050 | IGD-E ELECTRICAL CABLE ROUTING LAYOUT - IFA | 15 | 2022-09-20 | 2022-10-11 | 2023-03-01 | 2023-03-21 | 114
0 | EDIGEL2060 | IGD-E LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IFA | 10 | 2022-09-27 | 2022-10-11 | 2023-02-01 | 2023-02-14 | 89
0 | EDIGEL2070 | IGD-E EARTHING & LIGHTNING PROTECTION LAYOUT - IFA | 10 | 2022-09-27 | 2022-10-11 | 2023-03-08 | 2023-03-21 | 114
0 | EDIGEL1385 | IGD-E HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATION) - IFC | 10 | 2022-10-04 | 2022-10-18 | 2023-03-29 | 2023-04-11 | 124
0 | EDIGEL1400 | IGD-E HAZARDOUS AREA CLASSIFICATION DRAWING (WORK OVER / WIRELINE OPERATIONS) - IFC | 10 | 2022-10-05 | 2022-10-19 | 2023-04-12 | 2023-04-27 | 133
0 | EDIGEL1325 | IGD-E ELECTRICAL & INSTRUMENTATION CABLE TRAY LAYOUT - IFC | 10 | 2022-10-21 | 2022-11-04 | 2023-04-10 | 2023-04-25 | 119
0 | EDIGEL1355 | IGD-E LIGHTING/SMALL POWER AND NAVIGATIONAL SYSTEM LAYOUT - IFC | 15 | 2022-10-25 | 2022-11-15 | 2023-03-01 | 2023-03-21 | 89
0 | EDIGEL1340 | IGD-E ELECTRICAL CABLE ROUTING LAYOUT - IFC | 15 | 2022-10-25 | 2022-11-15 | 2023-04-05 | 2023-04-27 | 114
0 | EDIGEL1370 | IGD-E EARTHING & LIGHTNING PROTECTION LAYOUT - IFC | 15 | 2022-10-25 | 2022-11-15 | 2023-04-05 | 2023-04-27 | 114
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDIGEL2000 | IGD-E ELECTRICAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDIGEL2005 | IGD-E ELECTRICAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDIGEL2010 | IGD-E ELECTRICAL MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
INSTRUMENTATION & CONTROL |  |  | 207 | 2022-03-24 | 2023-01-19 | 2022-06-06 | 2023-04-27 | 69
3D MODEL DEVELOPMENT |  |  | 180 | 2022-05-05 | 2023-01-19 | 2022-08-15 | 2023-04-27 | 69
0 | EDIDIN3000 | IGD-E 3D MODEL DEVELOPMENT - INSTRUMENTATION | 180 | 2022-05-05 | 2023-01-19 | 2022-08-15 | 2023-04-27 | 69
DOCUMENTS |  |  | 191 | 2022-03-24 | 2022-12-28 | 2022-06-06 | 2023-04-27 | 85
CALCULATIONS |  |  | 74 | 2022-03-31 | 2022-07-21 | 2022-08-23 | 2022-12-26 | 111
0 | EDIDIN1015 | IGD-E CALCULATION NOTE FOR PRESSURE RELIEF VALVES - ICR | 15 | 2022-03-31 | 2022-04-21 | 2022-08-23 | 2022-09-12 | 97
0 | EDIDIN1030 | IGD-E THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - ICR | 15 | 2022-04-13 | 2022-05-09 | 2022-09-23 | 2022-10-13 | 111
0 | EDIDIN1000 | IGD-E CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - ICR | 14 | 2022-04-20 | 2022-05-13 | 2022-09-05 | 2022-09-22 | 92
0 | EDIDIN1020 | IGD-E CALCULATION NOTE FOR PRESSURE RELIEF VALVES - IFA | 15 | 2022-05-10 | 2022-05-31 | 2022-09-27 | 2022-10-17 | 97
0 | EDIDIN1035 | IGD-E THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - IFA | 15 | 2022-05-23 | 2022-06-13 | 2022-10-28 | 2022-11-17 | 111
0 | EDIDIN1005 | IGD-E CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - IFA | 14 | 2022-05-27 | 2022-06-16 | 2022-10-07 | 2022-10-26 | 92
0 | EDIDIN1025 | IGD-E CALCULATION NOTE FOR PRESSURE RELIEF VALVES - IFC | 15 | 2022-06-14 | 2022-07-05 | 2022-11-01 | 2022-11-21 | 97
0 | EDIDIN1010 | IGD-E CALCULATION NOTE FOR RESTRICTION ORIFICE PLATES - IFC | 10 | 2022-06-30 | 2022-07-19 | 2022-11-10 | 2022-11-23 | 92
0 | EDIDIN1040 | IGD-E THERMOWELL VIBRATION ANALYSIS / CALCULATIONS - IFC | 15 | 2022-06-27 | 2022-07-21 | 2022-12-06 | 2022-12-26 | 111
INDEX / NARRATIVE |  |  | 50 | 2022-08-22 | 2022-10-31 | 2022-11-14 | 2023-01-24 | 60
0 | EDIDIN1060 | IGD-E INSTRUMENT INDEX - ICR | 10 | 2022-08-22 | 2022-09-05 | 2022-11-14 | 2022-11-25 | 60
0 | EDIDIN1075 | IGD-E FIRE & GAS INDEX - ICR | 10 | 2022-08-22 | 2022-09-05 | 2022-11-14 | 2022-11-25 | 60
0 | EDIDIN1065 | IGD-E INSTRUMENT INDEX - IFA | 10 | 2022-09-19 | 2022-10-03 | 2022-12-21 | 2023-01-03 | 65
0 | EDIDIN1080 | IGD-E FIRE & GAS INDEX - IFA | 10 | 2022-09-19 | 2022-10-03 | 2022-12-14 | 2022-12-27 | 60
0 | EDIDIN1070 | IGD-E INSTRUMENT INDEX - IFC | 5 | 2022-10-17 | 2022-10-24 | 2023-01-18 | 2023-01-24 | 65
0 | EDIDIN1085 | IGD-E FIRE & GAS INDEX - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-01-11 | 2023-01-24 | 60
DATA SHEET |  |  | 79 | 2022-03-24 | 2022-07-21 | 2022-06-06 | 2023-01-17 | 127
0 | EDIDIN1115 | IGD-E DATASHEETS FOR MOV - ICR | 10 | 2022-03-24 | 2022-04-07 | 2022-06-06 | 2022-06-17 | 49
0 | EDIDIN1310 | IGD-E DATASHEETS FOR ELECTRONIC SOUNDER - ICR | 9 | 2022-03-31 | 2022-04-13 | 2022-10-27 | 2022-11-08 | 144
0 | EDIDIN1130 | IGD-E DATASHEETS FOR PRESSURE RELIEF VALVES - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-09-14 | 2022-09-27 | 113
0 | EDIDIN1100 | IGD-E DATASHEETS FOR ACTUATED ON/OFF VALVES - ICR | 10 | 2022-03-31 | 2022-04-14 | 2022-06-06 | 2022-06-17 | 44
0 | EDIDIN1325 | IGD-E DATASHEETS FOR EMERGENCY S/D PB - ICR | 10 | 2022-04-04 | 2022-04-18 | 2022-10-31 | 2022-11-11 | 144
0 | EDIDIN1340 | IGD-E DATASHEETS FOR FLAMMABLE GAS DETECTOR - ICR | 10 | 2022-04-06 | 2022-04-20 | 2022-11-02 | 2022-11-15 | 144
0 | EDIDIN1280 | IGD-E DATASHEETS FOR LEVEL TRANSMITTERS - ICR | 7 | 2022-04-12 | 2022-04-21 | 2022-09-27 | 2022-10-05 | 114
0 | EDIDIN1175 | IGD-E DATASHEETS FOR PRESSURE GAUGES - ICR | 10 | 2022-04-08 | 2022-04-22 | 2022-09-20 | 2022-10-03 | 111
0 | EDIDIN1220 | IGD-E DATASHEETS FOR TEMPERATURE GAUGES - ICR | 10 | 2022-04-08 | 2022-04-22 | 2022-09-16 | 2022-09-29 | 109
0 | EDIDIN1355 | IGD-E DATASHEETS FOR FIRE GAS DETECTOR - ICR | 10 | 2022-04-08 | 2022-04-22 | 2022-11-04 | 2022-11-17 | 144
0 | EDIDIN1205 | IGD-E DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - ICR | 10 | 2022-04-11 | 2022-04-25 | 2022-09-01 | 2022-09-14 | 97
0 | EDIDIN1160 | IGD-E DATASHEETS FOR FLOW RESTRICTION ORIFICE - ICR | 10 | 2022-04-11 | 2022-04-25 | 2022-08-24 | 2022-09-06 | 91
0 | EDIDIN1145 | IGD-E DATASHEETS FOR FLOW METER - ULTRASONIC - ICR | 10 | 2022-04-11 | 2022-04-25 | 2022-06-20 | 2022-07-01 | 47
0 | EDIDIN1370 | IGD-E DATASHEETS FOR FLASHING BEACON - ICR | 10 | 2022-04-12 | 2022-04-26 | 2022-11-08 | 2022-11-21 | 144
0 | EDIDIN1400 | IGD-E DATASHEETS FOR MAN ON BOARD PB - ICR | 9 | 2022-04-14 | 2022-04-27 | 2022-11-10 | 2022-11-22 | 144
0 | EDIDIN1235 | IGD-E DATASHEETS FOR TEMPERATURE TRANSMITTERS - ICR | 10 | 2022-04-13 | 2022-04-27 | 2022-09-08 | 2022-09-21 | 100
0 | EDIDIN1385 | IGD-E DATASHEETS FOR HEAT DETECTOR - ICR | 10 | 2022-04-14 | 2022-04-28 | 2022-11-10 | 2022-11-23 | 144
0 | EDIDIN1415 | IGD-E DATASHEETS FOR TOXIC GAS DETECTOR - ICR | 10 | 2022-04-14 | 2022-04-28 | 2022-11-10 | 2022-11-23 | 144
0 | EDIDIN1265 | IGD-E DATASHEETS FOR LEVEL GAUGES - ICR | 10 | 2022-04-15 | 2022-04-29 | 2022-09-14 | 2022-09-27 | 102
0 | EDIDIN1430 | IGD-E DATASHEETS FOR MANUAL ALARM CALL POINT - ICR | 10 | 2022-04-18 | 2022-05-05 | 2022-11-14 | 2022-11-25 | 144
0 | EDIDIN1295 | IGD-E DATASHEETS FOR FLOW SWITCHES - ICR | 10 | 2022-04-21 | 2022-05-10 | 2022-10-25 | 2022-11-07 | 127
0 | EDIDIN1120 | IGD-E DATASHEETS FOR MOV - IFA | 10 | 2022-04-21 | 2022-05-10 | 2022-07-04 | 2022-07-20 | 49
0 | EDIDIN1190 | IGD-E DATASHEETS FOR CORROSION MONITOR - ICR | 10 | 2022-04-22 | 2022-05-11 | 2022-09-28 | 2022-10-11 | 107
0 | EDIDIN1315 | IGD-E DATASHEETS FOR ELECTRONIC SOUNDER - IFA | 9 | 2022-04-27 | 2022-05-13 | 2022-11-30 | 2022-12-14 | 149
0 | EDIDIN1250 | IGD-E DATASHEETS FOR PIG SIGNALLER - ICR | 10 | 2022-04-27 | 2022-05-16 | 2022-10-26 | 2022-11-08 | 124
0 | EDIDIN1105 | IGD-E DATASHEETS FOR ACTUATED ON/OFF VALVES - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-07-04 | 2022-07-20 | 44
0 | EDIDIN1135 | IGD-E DATASHEETS FOR PRESSURE RELIEF VALVES - IFA | 10 | 2022-04-28 | 2022-05-17 | 2022-10-12 | 2022-10-25 | 113
0 | EDIDIN1330 | IGD-E DATASHEETS FOR EMERGENCY S/D PB - IFA | 10 | 2022-05-05 | 2022-05-19 | 2022-11-28 | 2022-12-13 | 144
0 | EDIDIN1285 | IGD-E DATASHEETS FOR LEVEL TRANSMITTERS - IFA | 7 | 2022-05-10 | 2022-05-19 | 2022-10-20 | 2022-10-28 | 114
0 | EDIDIN1345 | IGD-E DATASHEETS FOR FLAMMABLE GAS DETECTOR - IFA | 10 | 2022-05-09 | 2022-05-23 | 2022-12-07 | 2022-12-20 | 147
0 | EDIDIN1360 | IGD-E DATASHEETS FOR FIRE GAS DETECTOR - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-12-07 | 2022-12-20 | 145
0 | EDIDIN1180 | IGD-E DATASHEETS FOR PRESSURE GAUGES - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-10-18 | 2022-10-31 | 111
0 | EDIDIN1225 | IGD-E DATASHEETS FOR TEMPERATURE GAUGES - IFA | 10 | 2022-05-11 | 2022-05-25 | 2022-10-14 | 2022-10-27 | 109
0 | EDIDIN1150 | IGD-E DATASHEETS FOR FLOW METER - ULTRASONIC - IFA | 10 | 2022-05-12 | 2022-05-26 | 2022-07-21 | 2022-08-03 | 47
0 | EDIDIN1210 | IGD-E DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - IFA | 10 | 2022-05-12 | 2022-05-26 | 2022-09-29 | 2022-10-12 | 97
0 | EDIDIN1375 | IGD-E DATASHEETS FOR FLASHING BEACON - IFA | 10 | 2022-05-13 | 2022-05-27 | 2022-12-12 | 2022-12-23 | 146
0 | EDIDIN1405 | IGD-E DATASHEETS FOR MAN ON BOARD PB - IFA | 9 | 2022-05-16 | 2022-05-27 | 2022-12-12 | 2022-12-22 | 145
0 | EDIDIN1240 | IGD-E DATASHEETS FOR TEMPERATURE TRANSMITTERS - IFA | 10 | 2022-05-16 | 2022-05-30 | 2022-10-06 | 2022-10-19 | 100
0 | EDIDIN1390 | IGD-E DATASHEETS FOR HEAT DETECTOR - IFA | 10 | 2022-05-17 | 2022-05-31 | 2022-12-14 | 2022-12-27 | 146
0 | EDIDIN1420 | IGD-E DATASHEETS FOR TOXIC GAS DETECTOR - IFA | 10 | 2022-05-17 | 2022-05-31 | 2022-12-14 | 2022-12-27 | 146
0 | EDIDIN1165 | IGD-E DATASHEETS FOR FLOW RESTRICTION ORIFICE - IFA | 10 | 2022-05-18 | 2022-06-01 | 2022-09-21 | 2022-10-04 | 87
0 | EDIDIN1270 | IGD-E DATASHEETS FOR LEVEL GAUGES - IFA | 10 | 2022-05-18 | 2022-06-01 | 2022-10-12 | 2022-10-25 | 102
0 | EDIDIN1435 | IGD-E DATASHEETS FOR MANUAL ALARM CALL POINT - IFA | 10 | 2022-05-19 | 2022-06-02 | 2022-12-14 | 2022-12-27 | 144
0 | EDIDIN1125 | IGD-E DATASHEETS FOR MOV - IFC | 10 | 2022-05-24 | 2022-06-07 | 2022-08-04 | 2022-08-17 | 49
0 | EDIDIN1300 | IGD-E DATASHEETS FOR FLOW SWITCHES - IFA | 10 | 2022-05-24 | 2022-06-07 | 2022-11-22 | 2022-12-07 | 127
0 | EDIDIN1195 | IGD-E DATASHEETS FOR CORROSION MONITOR - IFA | 10 | 2022-05-25 | 2022-06-08 | 2022-11-09 | 2022-11-22 | 117
0 | EDIDIN1290 | IGD-E DATASHEETS FOR LEVEL TRANSMITTERS - IFC | 7 | 2022-06-02 | 2022-06-13 | 2022-11-14 | 2022-11-22 | 114
0 | EDIDIN1255 | IGD-E DATASHEETS FOR PIG SIGNALLER - IFA | 10 | 2022-05-30 | 2022-06-13 | 2022-11-23 | 2022-12-08 | 124
0 | EDIDIN1320 | IGD-E DATASHEETS FOR ELECTRONIC SOUNDER - IFC | 14 | 2022-05-27 | 2022-06-16 | 2022-12-29 | 2023-01-17 | 149
0 | EDIDIN1350 | IGD-E DATASHEETS FOR FLAMMABLE GAS DETECTOR - IFC | 10 | 2022-06-06 | 2022-06-20 | 2023-01-04 | 2023-01-17 | 147
0 | EDIDIN1140 | IGD-E DATASHEETS FOR PRESSURE RELIEF VALVES - IFC | 15 | 2022-05-31 | 2022-06-21 | 2022-11-09 | 2022-11-29 | 113
0 | EDIDIN1395 | IGD-E DATASHEETS FOR HEAT DETECTOR - IFC | 5 | 2022-06-14 | 2022-06-21 | 2023-01-11 | 2023-01-17 | 146
0 | EDIDIN1380 | IGD-E DATASHEETS FOR FLASHING BEACON - IFC | 7 | 2022-06-10 | 2022-06-21 | 2023-01-09 | 2023-01-17 | 146
0 | EDIDIN1110 | IGD-E DATASHEETS FOR ACTUATED ON/OFF VALVES - IFC | 15 | 2022-05-31 | 2022-06-21 | 2022-08-04 | 2022-08-24 | 44
0 | EDIDIN1425 | IGD-E DATASHEETS FOR TOXIC GAS DETECTOR - IFC | 5 | 2022-06-14 | 2022-06-21 | 2023-01-11 | 2023-01-17 | 146
0 | EDIDIN1410 | IGD-E DATASHEETS FOR MAN ON BOARD PB - IFC | 8 | 2022-06-10 | 2022-06-22 | 2023-01-06 | 2023-01-17 | 145
0 | EDIDIN1365 | IGD-E DATASHEETS FOR FIRE GAS DETECTOR - IFC | 10 | 2022-06-08 | 2022-06-22 | 2023-01-04 | 2023-01-17 | 145
0 | EDIDIN1440 | IGD-E DATASHEETS FOR MANUAL ALARM CALL POINT- IFC | 5 | 2022-06-16 | 2022-06-23 | 2023-01-11 | 2023-01-17 | 144
0 | EDIDIN1335 | IGD-E DATASHEETS FOR EMERGENCY S/D PB - IFC | 15 | 2022-06-02 | 2022-06-23 | 2022-12-28 | 2023-01-17 | 144
0 | EDIDIN1185 | IGD-E DATASHEETS FOR PRESSURE GAUGES - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-11-15 | 2022-12-07 | 111
0 | EDIDIN1230 | IGD-E DATASHEETS FOR TEMPERATURE GAUGES - IFC | 15 | 2022-06-08 | 2022-06-29 | 2022-11-11 | 2022-12-05 | 109
0 | EDIDIN1245 | IGD-E DATASHEETS FOR TEMPERATURE TRANSMITTERS - IFC | 10 | 2022-06-15 | 2022-06-29 | 2022-11-03 | 2022-11-16 | 98
0 | EDIDIN1215 | IGD-E DATASHEETS FOR PRESSURE, DIFF PRESS TRANSMITTERS - IFC | 15 | 2022-06-09 | 2022-06-30 | 2022-10-27 | 2022-11-16 | 97
0 | EDIDIN1155 | IGD-E DATASHEETS FOR FLOW METER - ULTRASONIC - IFC | 15 | 2022-06-09 | 2022-06-30 | 2022-08-18 | 2022-09-07 | 47
0 | EDIDIN1170 | IGD-E DATASHEETS FOR FLOW RESTRICTION ORIFICE - IFC | 15 | 2022-06-16 | 2022-07-07 | 2022-10-19 | 2022-11-08 | 86
0 | EDIDIN1275 | IGD-E DATASHEETS FOR LEVEL GAUGES - IFC | 15 | 2022-06-16 | 2022-07-07 | 2022-11-09 | 2022-11-29 | 101
0 | EDIDIN1305 | IGD-E DATASHEETS FOR FLOW SWITCHES - IFC | 15 | 2022-06-21 | 2022-07-15 | 2022-12-22 | 2023-01-11 | 127
0 | EDIDIN1200 | IGD-E DATASHEETS FOR CORROSION MONITOR - IFC | 15 | 2022-06-22 | 2022-07-18 | 2022-12-09 | 2022-12-29 | 117
0 | EDIDIN1260 | IGD-E DATASHEETS FOR PIG SIGNALLER - IFC | 15 | 2022-06-27 | 2022-07-21 | 2022-12-23 | 2023-01-12 | 124
SCHEDULE / MTO |  |  | 98 | 2022-06-03 | 2022-10-24 | 2022-12-27 | 2023-04-27 | 130
0 | EDIDIN1600 | IGD-E INSTRUMENT 1ST MTO | 10 | 2022-06-03 | 2022-06-17 | 2022-12-27 | 2023-01-09 | 142
0 | EDIDIN1610 | IGD-E INSTRUMENT CABLE SCHEDULE - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-02-15 | 2023-02-28 | 132
0 | EDIDIN1625 | IGD-E JUNCTION BOX SCHEDULE - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-02-15 | 2023-02-28 | 132
0 | EDIDIN1640 | IGD-E TUBE SCHEDULE - ICR | 10 | 2022-08-15 | 2022-08-29 | 2023-02-15 | 2023-02-28 | 130
0 | EDIDIN1605 | IGD-E INSTRUMENT FINAL MTO | 10 | 2022-09-05 | 2022-09-19 | 2023-01-20 | 2023-02-02 | 97
0 | EDIDIN1615 | IGD-E INSTRUMENT CABLE SCHEDULE - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-15 | 2023-03-28 | 132
0 | EDIDIN1630 | IGD-E JUNCTION BOX SCHEDULE - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-15 | 2023-03-28 | 132
0 | EDIDIN1645 | IGD-E TUBE SCHEDULE - IFA | 10 | 2022-09-12 | 2022-09-26 | 2023-03-15 | 2023-03-28 | 130
0 | EDIDIN1620 | IGD-E INSTRUMENT CABLE SCHEDULE - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-04-12 | 2023-04-27 | 132
0 | EDIDIN1635 | IGD-E JUNCTION BOX SCHEDULE - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-04-12 | 2023-04-27 | 132
0 | EDIDIN1650 | IGD-E TUBE SCHEDULE - IFC | 10 | 2022-10-10 | 2022-10-24 | 2023-04-12 | 2023-04-27 | 130
LIST |  |  | 90 | 2022-08-22 | 2022-12-28 | 2022-12-21 | 2023-04-27 | 85
0 | EDIDIN1700 | IGD-E I/O LIST FOR DCS - ICR | 20 | 2022-08-22 | 2022-09-19 | 2022-12-21 | 2023-01-17 | 85
0 | EDIDIN1715 | IGD-E I/O LIST FOR ESD SYSTEM - ICR | 20 | 2022-08-29 | 2022-09-26 | 2022-12-28 | 2023-01-24 | 85
0 | EDIDIN1730 | IGD-E I/O LIST FOR F&G SYSTEM - ICR | 20 | 2022-09-05 | 2022-10-03 | 2023-01-04 | 2023-01-31 | 85
0 | EDIDIN1705 | IGD-E I/O LIST FOR DCS - IFA | 20 | 2022-10-03 | 2022-10-31 | 2023-02-15 | 2023-03-14 | 95
0 | EDIDIN1720 | IGD-E I/O LIST FOR ESD SYSTEM - IFA | 20 | 2022-10-10 | 2022-11-07 | 2023-02-15 | 2023-03-14 | 90
0 | EDIDIN1735 | IGD-E I/O LIST FOR F&G SYSTEM - IFA | 20 | 2022-10-17 | 2022-11-14 | 2023-02-15 | 2023-03-14 | 85
0 | EDIDIN1710 | IGD-E I/O LIST FOR DCS - IFC | 20 | 2022-11-14 | 2022-12-14 | 2023-03-29 | 2023-04-27 | 95
0 | EDIDIN1725 | IGD-E I/O LIST FOR ESD SYSTEM - IFC | 20 | 2022-11-21 | 2022-12-21 | 2023-03-29 | 2023-04-27 | 90
0 | EDIDIN1740 | IGD-E I/O LIST FOR F&G SYSTEM - IFC | 20 | 2022-11-28 | 2022-12-28 | 2023-03-29 | 2023-04-27 | 85
DRAWINGS |  |  | 182 | 2022-04-05 | 2022-12-27 | 2022-08-30 | 2023-04-27 | 86
DIAGRAM |  |  | 182 | 2022-04-05 | 2022-12-27 | 2022-08-30 | 2023-04-27 | 86
0 | EDIGIN1000 | IGD-E LEVEL SKETCH- ICR | 12 | 2022-04-05 | 2022-04-21 | 2022-11-04 | 2022-11-21 | 147
0 | EDIGIN1015 | IGD-E INSTRUMENT CABLE BLOCK DIAGRAM - ICR | 15 | 2022-04-18 | 2022-05-12 | 2022-08-30 | 2022-09-19 | 89
0 | EDIGIN1005 | IGD-E LEVEL SKETCH- IFA | 12 | 2022-05-10 | 2022-05-26 | 2022-12-08 | 2022-12-23 | 147
0 | EDIGIN1030 | IGD-E TUBING BLOCK DIAGRAM - ICR | 15 | 2022-05-12 | 2022-06-02 | 2022-10-28 | 2022-11-17 | 117
0 | EDIGIN1020 | IGD-E INSTRUMENT CABLE BLOCK DIAGRAM - IFA | 15 | 2022-05-26 | 2022-06-16 | 2022-11-04 | 2022-11-24 | 112
0 | EDIGIN1010 | IGD-E LEVEL SKETCH- IFC | 12 | 2022-06-09 | 2022-06-27 | 2023-01-09 | 2023-01-24 | 147
0 | EDIGIN1035 | IGD-E TUBING BLOCK DIAGRAM - IFA | 15 | 2022-06-16 | 2022-07-07 | 2022-12-06 | 2022-12-26 | 117
0 | EDIGIN1025 | IGD-E INSTRUMENT CABLE BLOCK DIAGRAM - IFC | 20 | 2022-06-30 | 2022-08-02 | 2022-12-13 | 2023-01-09 | 112
0 | EDIGIN1045 | IGD-E INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - ICR | 15 | 2022-07-26 | 2022-08-16 | 2023-01-05 | 2023-01-25 | 114
0 | EDIGIN1060 | IGD-E INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - ICR | 15 | 2022-08-01 | 2022-08-22 | 2023-01-11 | 2023-01-31 | 114
0 | EDIGIN1075 | IGD-E PROCESS & HYDRAULIC HOOK-UPS DRAWING - ICR | 15 | 2022-08-08 | 2022-08-29 | 2023-01-18 | 2023-02-07 | 114
0 | EDIGIN1040 | IGD-E TUBING BLOCK DIAGRAM - IFC | 20 | 2022-08-02 | 2022-08-30 | 2023-01-10 | 2023-02-06 | 112
0 | EDIGIN1050 | IGD-E INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - IFA | 15 | 2022-08-30 | 2022-09-20 | 2023-02-22 | 2023-03-14 | 123
0 | EDIGIN1090 | IGD-E INSTRUMENT LOOP DIAGRAMS - DCS - ICR | 10 | 2022-09-12 | 2022-09-26 | 2023-02-02 | 2023-02-15 | 101
0 | EDIGIN1065 | IGD-E INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - IFA | 15 | 2022-09-05 | 2022-09-26 | 2023-02-22 | 2023-03-14 | 119
0 | EDIGIN1105 | IGD-E INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - ICR | 10 | 2022-09-14 | 2022-09-28 | 2023-02-06 | 2023-02-17 | 101
0 | EDIGIN1080 | IGD-E PROCESS & HYDRAULIC HOOK-UPS DRAWING - IFA | 15 | 2022-09-12 | 2022-10-03 | 2023-02-22 | 2023-03-14 | 114
0 | EDIGIN1120 | IGD-E INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - ICR | 10 | 2022-10-07 | 2022-10-21 | 2023-02-08 | 2023-02-21 | 86
0 | EDIGIN1095 | IGD-E INSTRUMENT LOOP DIAGRAMS - DCS - IFA | 10 | 2022-10-10 | 2022-10-24 | 2023-03-08 | 2023-03-21 | 105
0 | EDIGIN1110 | IGD-E INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - IFA | 10 | 2022-10-12 | 2022-10-26 | 2023-03-08 | 2023-03-21 | 103
0 | EDIGIN1055 | IGD-E INSTRUMENT DETAILED INTERFACE-INTERCONNECTION DRAWING WITH TIE-IN DETAILS - IFC | 20 | 2022-10-04 | 2022-11-01 | 2023-03-29 | 2023-04-27 | 123
0 | EDIGIN1070 | IGD-E INSTRUMENT WIRING/INTERCONNECTION DIAGRAMS - IFC | 20 | 2022-10-10 | 2022-11-07 | 2023-03-29 | 2023-04-27 | 119
0 | EDIGIN1085 | IGD-E PROCESS & HYDRAULIC HOOK-UPS DRAWING - IFC | 20 | 2022-10-17 | 2022-11-14 | 2023-03-29 | 2023-04-27 | 114
0 | EDIGIN1125 | IGD-E INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - IFA | 10 | 2022-11-04 | 2022-11-18 | 2023-03-08 | 2023-03-21 | 86
0 | EDIGIN1100 | IGD-E INSTRUMENT LOOP DIAGRAMS - DCS - IFC | 15 | 2022-11-07 | 2022-11-28 | 2023-04-05 | 2023-04-27 | 105
0 | EDIGIN1115 | IGD-E INSTRUMENT LOOP DIAGRAMS - ESD SYSTEM - IFC | 15 | 2022-11-09 | 2022-11-30 | 2023-04-05 | 2023-04-27 | 103
0 | EDIGIN1130 | IGD-E INSTRUMENT LOOP DIAGRAMS - F&G SYSTEM - IFC | 15 | 2022-12-06 | 2022-12-27 | 2023-04-05 | 2023-04-27 | 86
LAYOUT |  |  | 94 | 2022-06-30 | 2022-11-14 | 2022-10-04 | 2023-04-27 | 115
0 | EDIGIN1215 | IGD-E INSTRUMENT CABLE ROUTING LAYOUT - ICR | 15 | 2022-06-30 | 2022-07-26 | 2023-01-05 | 2023-01-25 | 130
0 | EDIGIN1230 | IGD-E INSTRUMENT CABLE ROUTING LAYOUT DEMOLITION - ICR | 15 | 2022-06-30 | 2022-07-26 | 2023-01-05 | 2023-01-25 | 130
0 | EDIGIN1245 | IGD-E INSTRUMENT LOCATION LAYOUTS - ICR | 15 | 2022-07-07 | 2022-08-02 | 2023-01-12 | 2023-02-01 | 130
0 | EDIGIN1260 | IGD-E TUBE ROUTING LAYOUT - ICR | 15 | 2022-07-18 | 2022-08-08 | 2023-01-18 | 2023-02-07 | 130
0 | EDIGIN1200 | IGD-E INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - ICR | 15 | 2022-07-26 | 2022-08-16 | 2022-10-04 | 2022-10-24 | 50
0 | EDIGIN1220 | IGD-E INSTRUMENT CABLE ROUTING LAYOUT - IFA | 10 | 2022-08-09 | 2022-08-23 | 2023-03-01 | 2023-03-14 | 144
0 | EDIGIN1235 | IGD-E INSTRUMENT CABLE ROUTING LAYOUT DEMOLITION - IFA | 10 | 2022-08-09 | 2022-08-23 | 2023-03-01 | 2023-03-14 | 144
0 | EDIGIN1280 | IGD-E FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - ICR | 15 | 2022-08-04 | 2022-08-25 | 2022-10-13 | 2022-11-02 | 50
0 | EDIGIN1310 | IGD-E FIRE & GAS LOCATION LAYOUTS- DEMOLITION – OFFSHORE PLATFORM - ICR | 15 | 2022-08-15 | 2022-09-05 | 2022-10-24 | 2022-11-11 | 50
0 | EDIGIN1250 | IGD-E INSTRUMENT LOCATION LAYOUTS - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-02-22 | 2023-03-14 | 134
0 | EDIGIN1265 | IGD-E TUBE ROUTING LAYOUT - IFA | 15 | 2022-08-22 | 2022-09-12 | 2023-02-22 | 2023-03-14 | 130
0 | EDIGIN1205 | IGD-E INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - IFA | 15 | 2022-08-30 | 2022-09-20 | 2022-11-28 | 2022-12-20 | 64
0 | EDIGIN1290 | IGD-E FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - IFA | 15 | 2022-09-08 | 2022-09-29 | 2022-11-28 | 2022-12-20 | 57
0 | EDIGIN1225 | IGD-E INSTRUMENT CABLE ROUTING LAYOUT - IFC | 20 | 2022-09-06 | 2022-10-04 | 2023-03-29 | 2023-04-27 | 144
0 | EDIGIN1240 | IGD-E INSTRUMENT CABLE ROUTING LAYOUT DEMOLITION - IFC | 20 | 2022-09-06 | 2022-10-04 | 2023-03-29 | 2023-04-27 | 144
0 | EDIGIN1320 | IGD-E FIRE & GAS LOCATION LAYOUTS – DEMOLITION - OFFSHORE PLATFORM - IFA | 15 | 2022-09-19 | 2022-10-10 | 2022-11-28 | 2022-12-20 | 50
0 | EDIGIN1255 | IGD-E INSTRUMENT LOCATION LAYOUTS - IFC | 20 | 2022-09-20 | 2022-10-18 | 2023-03-29 | 2023-04-27 | 134
0 | EDIGIN1270 | IGD-E TUBE ROUTING LAYOUT - IFC | 20 | 2022-09-26 | 2022-10-24 | 2023-03-29 | 2023-04-27 | 130
0 | EDIGIN1210 | IGD-E INSTRUMENT EQUIPMENT LOCATION LAYOUTS – OFFSHORE PLATFORM - IFC | 15 | 2022-10-04 | 2022-10-25 | 2023-01-04 | 2023-01-24 | 64
0 | EDIGIN1300 | IGD-E FIRE & GAS LOCATION LAYOUTS – OFFSHORE PLATFORM - IFC | 15 | 2022-10-13 | 2022-11-03 | 2023-01-04 | 2023-01-24 | 57
0 | EDIGIN1330 | IGD-E FIRE & GAS LOCATION LAYOUTS – DEMOLITION - OFFSHORE PLATFORM - IFC | 15 | 2022-10-24 | 2022-11-14 | 2023-01-04 | 2023-01-24 | 50
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDIGIN2000 | IGD-E INSTRUMENT MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDIGIN2005 | IGD-E INSTRUMENT MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDIGIN2010 | IGD-E INSTRUMENT MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
TELECOM |  |  | 156 | 2022-06-03 | 2023-01-16 | 2022-09-27 | 2023-04-27 | 72
DOCUMENTS |  |  | 96 | 2022-06-03 | 2022-10-20 | 2022-09-27 | 2023-04-27 | 132
LIST/SCHEDULE |  |  | 96 | 2022-06-03 | 2022-10-20 | 2022-09-27 | 2023-04-27 | 132
0 | EDIDTE1000 | IGD-E TELECOMMUNICATION - 1ST MTO | 10 | 2022-06-03 | 2022-06-17 | 2022-09-27 | 2022-10-10 | 79
0 | EDIDTE1010 | IGD-E TELECOM EQUIPMENT LIST - ICR | 10 | 2022-06-17 | 2022-07-01 | 2022-10-11 | 2022-10-24 | 79
0 | EDIDTE1015 | IGD-E TELECOM EQUIPMENT LIST - IFA | 10 | 2022-07-20 | 2022-08-03 | 2023-03-01 | 2023-03-14 | 158
0 | EDIDTE1025 | IGD-E TELECOM CABLE SCHEDULE - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-02-01 | 2023-02-14 | 122
0 | EDIDTE1020 | IGD-E TELECOM EQUIPMENT LIST - IFC | 20 | 2022-08-17 | 2022-09-14 | 2023-03-29 | 2023-04-27 | 158
0 | EDIDTE1005 | IGD-E TELECOMMUNICATION - FINAL MTO | 9 | 2022-09-06 | 2022-09-19 | 2023-01-23 | 2023-02-02 | 97
0 | EDIDTE1030 | IGD-E TELECOM CABLE SCHEDULE - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-15 | 2023-03-28 | 132
0 | EDIDTE1035 | IGD-E TELECOM CABLE SCHEDULE - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-04-12 | 2023-04-27 | 132
DRAWINGS |  |  | 86 | 2022-07-20 | 2022-11-17 | 2022-11-08 | 2023-04-27 | 112
LAYOUT |  |  | 86 | 2022-07-20 | 2022-11-17 | 2022-11-08 | 2023-04-27 | 112
0 | EDIGTE1015 | IGD-E TELECOM EQUIPMENT LOCATION LAYOUTS - ICR | 10 | 2022-07-20 | 2022-08-03 | 2022-11-08 | 2022-11-21 | 79
0 | EDIGTE1000 | IGD-E TELECOM CABLE ROUTING LAYOUT - ICR | 10 | 2022-08-11 | 2022-08-25 | 2023-01-18 | 2023-01-31 | 112
0 | EDIGTE1020 | IGD-E TELECOM EQUIPMENT LOCATION LAYOUTS - IFA | 10 | 2022-08-17 | 2022-08-31 | 2022-12-08 | 2022-12-21 | 79
0 | EDIGTE1045 | IGD-E DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - ICR | 10 | 2022-08-25 | 2022-09-08 | 2023-02-01 | 2023-02-14 | 112
0 | EDIGTE1030 | IGD-E FIBER OPTIC ALLOCATION DRAWING - ICR | 10 | 2022-08-25 | 2022-09-08 | 2023-02-15 | 2023-02-28 | 122
0 | EDIGTE1005 | IGD-E TELECOM CABLE ROUTING LAYOUT - IFA | 10 | 2022-09-08 | 2022-09-22 | 2023-03-15 | 2023-03-28 | 132
0 | EDIGTE1025 | IGD-E TELECOM EQUIPMENT LOCATION LAYOUTS - IFC | 10 | 2022-09-14 | 2022-09-28 | 2023-01-05 | 2023-01-18 | 79
0 | EDIGTE1035 | IGD-E FIBER OPTIC ALLOCATION DRAWING - IFA | 10 | 2022-09-22 | 2022-10-06 | 2023-03-15 | 2023-03-28 | 122
0 | EDIGTE1050 | IGD-E DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - IFA | 10 | 2022-09-22 | 2022-10-06 | 2023-03-01 | 2023-03-14 | 112
0 | EDIGTE1010 | IGD-E TELECOM CABLE ROUTING LAYOUT - IFC | 10 | 2022-10-06 | 2022-10-20 | 2023-04-12 | 2023-04-27 | 132
0 | EDIGTE1040 | IGD-E FIBER OPTIC ALLOCATION DRAWING - IFC | 10 | 2022-10-20 | 2022-11-03 | 2023-04-12 | 2023-04-27 | 122
0 | EDIGTE1055 | IGD-E TELECOM DETAILED INTERFACE / INTERCONNECTION DRAWINGS WITH TIE-IN DETAILS - IFC | 20 | 2022-10-20 | 2022-11-17 | 2023-03-29 | 2023-04-27 | 112
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDIGTE2000 | IGD-E TELECOM MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDIGTE2005 | IGD-E TELECOM MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDIGTE2010 | IGD-E TELECOM MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
STRUCTURAL |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-06-22 | 2023-06-30 | 112
3D MODEL DEVELOPMENT |  |  | 215 | 2022-03-14 | 2023-01-19 | 2022-06-22 | 2023-04-27 | 69
0 | EDIDSR3000 | IGD-E 3D MODEL DEVELOPMENT - STRUCTURAL | 215 | 2022-03-14 | 2023-01-19 | 2022-06-22 | 2023-04-27 | 69
DOCUMENTS |  |  | 139 | 2022-05-19 | 2022-12-07 | 2022-10-10 | 2023-04-27 | 100
REPORTS |  |  | 139 | 2022-05-19 | 2022-12-07 | 2022-10-10 | 2023-04-27 | 100
0 | EDIDSR1000 | IGD-E GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-10-10 | 2022-11-04 | 99
0 | EDIDSR1005 | IGD-E GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - IFA | 15 | 2022-06-30 | 2022-07-26 | 2022-11-21 | 2022-12-13 | 99
0 | EDIDSR1105 | IGD-E TOPSIDE MISCELLANEOUS DESIGN REPORT - ICR | 20 | 2022-07-26 | 2022-08-23 | 2023-01-18 | 2023-02-14 | 124
0 | EDIDSR1015 | IGD-E JACKET INPLACE ANALYSIS REPORT - ICR | 20 | 2022-07-26 | 2022-08-23 | 2022-12-14 | 2023-01-10 | 99
0 | EDIDSR1075 | IGD-E TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - ICR | 20 | 2022-07-26 | 2022-08-23 | 2023-01-18 | 2023-02-14 | 124
0 | EDIDSR1010 | IGD-E GLOBAL TOPSIDES INPLACE ANALYSIS REPORT - IFC | 15 | 2022-08-09 | 2022-08-30 | 2023-03-27 | 2023-04-14 | 162
0 | EDIDSR1030 | IGD-E JACKET PUSHOVER ANALYSIS REPORT - ICR | 20 | 2022-08-02 | 2022-08-30 | 2023-01-04 | 2023-01-31 | 109
0 | EDIDSR1045 | IGD-E JACKET SPECTRAL FATIGUE ANALYSIS REPORT - ICR | 20 | 2022-08-09 | 2022-09-06 | 2023-01-11 | 2023-02-07 | 109
0 | EDIDSR1060 | IGD-E JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - ICR | 20 | 2022-08-16 | 2022-09-13 | 2023-01-18 | 2023-02-14 | 109
0 | EDIDSR1090 | IGD-E JACKET MISCELLANEOUS DESIGN REPORT - ICR | 20 | 2022-08-16 | 2022-09-13 | 2023-01-18 | 2023-02-14 | 109
0 | EDIDSR1020 | IGD-E JACKET INPLACE ANALYSIS REPORT - IFA | 15 | 2022-09-06 | 2022-09-27 | 2023-01-25 | 2023-02-14 | 99
0 | EDIDSR1110 | IGD-E TOPSIDE MISCELLANEOUS DESIGN REPORT - IFA | 15 | 2022-09-06 | 2022-09-27 | 2023-03-01 | 2023-03-21 | 124
0 | EDIDSR1080 | IGD-E TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - IFA | 15 | 2022-09-06 | 2022-09-27 | 2023-03-01 | 2023-03-21 | 124
0 | EDIDSR1035 | IGD-E JACKET PUSHOVER ANALYSIS REPORT - IFA | 15 | 2022-09-13 | 2022-10-04 | 2023-02-15 | 2023-03-07 | 109
0 | EDIDSR1050 | IGD-E JACKET SPECTRAL FATIGUE ANALYSIS REPORT - IFA | 15 | 2022-09-20 | 2022-10-11 | 2023-02-22 | 2023-03-14 | 109
0 | EDIDSR1065 | IGD-E JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - IFA | 15 | 2022-09-27 | 2022-10-18 | 2023-03-01 | 2023-03-21 | 109
0 | EDIDSR1095 | IGD-E JACKET MISCELLANEOUS DESIGN REPORT - IFA | 15 | 2022-09-27 | 2022-10-18 | 2023-03-01 | 2023-03-21 | 109
0 | EDIDSR1115 | IGD-E TOPSIDE MISCELLANEOUS DESIGN REPORT - IFC | 15 | 2022-10-11 | 2022-11-01 | 2023-04-05 | 2023-04-27 | 124
0 | EDIDSR1025 | IGD-E JACKET INPLACE ANALYSIS REPORT - IFC | 15 | 2022-10-11 | 2022-11-01 | 2023-03-08 | 2023-03-28 | 104
0 | EDIDSR1040 | IGD-E JACKET PUSHOVER ANALYSIS REPORT - IFC | 15 | 2022-10-18 | 2022-11-08 | 2023-03-22 | 2023-04-11 | 109
0 | EDIDSR1055 | IGD-E JACKET SPECTRAL FATIGUE ANALYSIS REPORT - IFC | 15 | 2022-10-25 | 2022-11-15 | 2023-03-29 | 2023-04-18 | 109
0 | EDIDSR1070 | IGD-E JACKET CP ADEQUACY CHECK AND MISCELLANEOUS ITEMS DESIGN REPORT - IFC | 15 | 2022-11-01 | 2022-11-22 | 2023-04-05 | 2023-04-27 | 109
0 | EDIDSR1100 | IGD-E JACKET MISCELLANEOUS DESIGN REPORT - IFC | 15 | 2022-11-01 | 2022-11-22 | 2023-04-05 | 2023-04-27 | 109
0 | EDIDSR1085 | IGD-E TOPSIDE EQUIPMENT SUPPORT DESIGN REPORT - IFC | 15 | 2022-11-14 | 2022-12-07 | 2023-04-05 | 2023-04-27 | 100
DRAWINGS |  |  | 151 | 2022-05-19 | 2022-12-23 | 2022-10-24 | 2023-06-30 | 131
GENERAL |  |  | 151 | 2022-05-19 | 2022-12-23 | 2022-10-24 | 2023-04-27 | 88
0 | EDIGSR1000 | IGD-E DRAWING INDEX - ICR | 15 | 2022-05-19 | 2022-06-09 | 2022-10-24 | 2022-11-11 | 109
0 | EDIGSR1002 | IGD-E DRAWING INDEX - IFA | 15 | 2022-06-23 | 2022-07-19 | 2023-03-01 | 2023-03-21 | 174
0 | EDIGSR1005 | IGD-E DRAWING INDEX - IFC | 15 | 2022-11-30 | 2022-12-23 | 2023-04-05 | 2023-04-27 | 88
SECONDARY |  |  | 80 | 2022-06-16 | 2022-10-11 | 2022-11-07 | 2023-05-02 | 142
0 | EDIGSR1015 | IGD-E CELLAR DECK SECONDARY FRAMING PLAN EL(+) 12.000 - ICR | 20 | 2022-06-16 | 2022-07-19 | 2022-11-07 | 2022-12-06 | 99
0 | EDIGSR1045 | IGD-E CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 12.000 - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-11-14 | 2022-12-13 | 99
0 | EDIGSR1030 | IGD-E WEATHER DECK SECONDARY FRAMING PLAN EL(+) 22.000 - ICR | 20 | 2022-06-23 | 2022-07-26 | 2022-11-14 | 2022-12-13 | 99
0 | EDIGSR1060 | IGD-E WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 22 000 - ICR | 20 | 2022-06-30 | 2022-08-02 | 2022-11-21 | 2022-12-20 | 99
0 | EDIGSR1020 | IGD-E CELLAR DECK SECONDARY FRAMING PLAN EL(+) 12.000 - IFA | 15 | 2022-08-02 | 2022-08-23 | 2023-03-13 | 2023-03-31 | 157
0 | EDIGSR1050 | IGD-E CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 12.000 - IFA | 15 | 2022-08-09 | 2022-08-30 | 2023-03-06 | 2023-03-24 | 147
0 | EDIGSR1035 | IGD-E WEATHER DECK SECONDARY FRAMING PLAN EL(+) 22.000 - IFA | 15 | 2022-08-09 | 2022-08-30 | 2023-03-01 | 2023-03-21 | 144
0 | EDIGSR1065 | IGD-E WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 22 000 - IFA | 15 | 2022-08-16 | 2022-09-06 | 2023-03-01 | 2023-03-21 | 139
0 | EDIGSR1025 | IGD-E CELLAR DECK SECONDARY FRAMING PLAN EL(+) 12.000 - IFC | 10 | 2022-09-06 | 2022-09-20 | 2023-04-17 | 2023-05-02 | 157
0 | EDIGSR1055 | IGD-E CELLAR DECK PLATING/GRATING & HANDRAIL LAYOUT AT EL (+) 12.000 - IFC | 15 | 2022-09-13 | 2022-10-04 | 2023-04-10 | 2023-05-02 | 147
0 | EDIGSR1040 | IGD-E WEATHER DECK SECONDARY FRAMING PLAN EL(+) 22.000 - IFC | 15 | 2022-09-13 | 2022-10-04 | 2023-04-05 | 2023-04-27 | 144
0 | EDIGSR1070 | IGD-E WEATHER DECK PLATING/GRATING AND HANDRAIL LAYOUT AT EL(+) 22 000 - IFC | 15 | 2022-09-20 | 2022-10-11 | 2023-04-05 | 2023-04-27 | 139
TERTAIRY |  |  | 90 | 2022-08-02 | 2022-12-08 | 2022-12-21 | 2023-06-30 | 142
0 | EDIGSR1430 | IGD-E VENT /DRAIN DRUM GRATING AND HANDRAIL LAYOUT AT EL + 7.800 TOS- ICR | 20 | 2022-08-02 | 2022-08-30 | 2022-12-21 | 2023-01-17 | 99
0 | EDIGSR1400 | IGD-E - VENT BOOM GA AND DETAILS - ICR | 20 | 2022-08-02 | 2022-08-30 | 2022-12-21 | 2023-01-17 | 99
0 | EDIGSR1445 | IGD-E BELOW WEATHER DECK LIFTING BEAM DETAILS - ICR | 20 | 2022-08-09 | 2022-09-06 | 2022-12-28 | 2023-01-24 | 99
0 | EDIGSR1415 | IGD-E - VENT DRAIN DRUM FRAMING PLAN AT EL. (+) 7.800 TO.S.& SECTIONS- ICR | 20 | 2022-08-09 | 2022-09-06 | 2023-02-01 | 2023-02-28 | 124
0 | EDIGSR1460 | IGD-E - CELLAR DECK AT EL (+) 12.000 TO.S. - DEMOLITION SCOPE - ICR | 20 | 2022-08-16 | 2022-09-13 | 2023-01-04 | 2023-01-31 | 99
0 | EDIGSR1475 | IGD-E JACKET NEW ANODE GA AND DETAILS - ICR | 20 | 2022-08-23 | 2022-09-20 | 2023-01-11 | 2023-02-07 | 99
0 | EDIGSR1535 | IGD-E JACKET RISER GA AND SUPPORT DETAILS - ICR | 20 | 2022-08-23 | 2022-09-20 | 2023-01-11 | 2023-02-07 | 99
0 | EDIGSR1505 | IGD-E JACKET J-TUBE SUPPORT DETAILS - ICR | 20 | 2022-08-23 | 2022-09-20 | 2023-01-18 | 2023-02-14 | 104
0 | EDIGSR1520 | IGD-E JACKET RISER GENRAL ARRANGEMENT - ICR | 20 | 2022-08-23 | 2022-09-20 | 2023-01-18 | 2023-02-14 | 104
0 | EDIGSR1490 | IGD-E JACKET J-TUBE GENERAL ARRANGEMENT - ICR | 20 | 2022-08-30 | 2022-09-27 | 2023-01-18 | 2023-02-14 | 99
0 | EDIGSR1435 | IGD-E VENT /DRAIN DRUM GRATING AND HANDRAIL LAYOUT AT EL + 7.800 TOS- IFA | 15 | 2022-09-13 | 2022-10-04 | 2023-05-03 | 2023-05-23 | 162
0 | EDIGSR1405 | IGD-E - VENT BOOM GA AND DETAILS - IFA | 15 | 2022-09-13 | 2022-10-04 | 2023-03-01 | 2023-03-21 | 119
0 | EDIGSR1450 | IGD-E BELOW WEATHER DECK LIFTING BEAM DETAILS - IFA | 15 | 2022-09-20 | 2022-10-11 | 2023-03-27 | 2023-04-14 | 132
0 | EDIGSR1420 | IGD-E - VENT DRAIN DRUM FRAMING PLAN AT EL. (+) 7.800 TO.S.& SECTIONS - IFA | 15 | 2022-09-20 | 2022-10-11 | 2023-03-15 | 2023-04-04 | 124
0 | EDIGSR1465 | IGD-E - CELLAR DECK AT EL (+) 12.000 TO.S. - DEMOLITION SCOPE - IFA | 15 | 2022-09-27 | 2022-10-18 | 2023-03-01 | 2023-03-21 | 109
0 | EDIGSR1480 | IGD-E JACKET NEW ANODE GA AND DETAILS - IFA | 15 | 2022-10-04 | 2022-10-25 | 2023-03-27 | 2023-04-14 | 122
0 | EDIGSR1540 | IGD-E JACKET RISER GA AND SUPPORT DETAILS - IFA | 15 | 2022-10-04 | 2022-10-25 | 2023-03-06 | 2023-03-24 | 107
0 | EDIGSR1510 | IGD-E JACKET J-TUBE SUPPORT DETAILS - IFA | 15 | 2022-10-04 | 2022-10-25 | 2023-03-01 | 2023-03-21 | 104
0 | EDIGSR1525 | IGD-E JACKET RISER GENRAL ARRANGEMENT - IFA | 15 | 2022-10-04 | 2022-10-25 | 2023-03-01 | 2023-03-21 | 104
0 | EDIGSR1495 | IGD-E JACKET J-TUBE GENERAL ARRANGEMENT - IFA | 15 | 2022-10-11 | 2022-11-01 | 2023-03-01 | 2023-03-21 | 99
0 | EDIGSR1425 | IGD-E - VENT DRAIN DRUM FRAMING PLAN AT EL. (+) 7.800 TO.S.& SECTIONS - IFC | 15 | 2022-10-11 | 2022-11-01 | 2023-04-05 | 2023-04-27 | 124
0 | EDIGSR1440 | IGD-E VENT /DRAIN DRUM GRATING AND HANDRAIL LAYOUT AT EL + 7.800 TOS- IFC | 15 | 2022-10-18 | 2022-11-08 | 2023-06-07 | 2023-06-30 | 162
0 | EDIGSR1410 | IGD-E - VENT BOOM GA AND DETAILS - IFC | 15 | 2022-10-18 | 2022-11-08 | 2023-04-05 | 2023-04-27 | 119
0 | EDIGSR1455 | IGD-E BELOW WEATHER DECK LIFTING BEAM DETAILS - IFC | 15 | 2022-10-25 | 2022-11-15 | 2023-05-03 | 2023-05-23 | 132
0 | EDIGSR1470 | IGD-E - CELLAR DECK AT EL (+) 12.000 TO.S. - DEMOLITION SCOPE - IFC | 15 | 2022-11-01 | 2022-11-22 | 2023-04-05 | 2023-04-27 | 109
0 | EDIGSR1485 | IGD-E JACKET NEW ANODE GA AND DETAILS - IFC | 15 | 2022-11-08 | 2022-11-29 | 2023-05-03 | 2023-05-23 | 122
0 | EDIGSR1545 | IGD-E JACKET RISER GA AND SUPPORT DETAILS - IFC | 15 | 2022-11-08 | 2022-11-29 | 2023-04-10 | 2023-05-02 | 107
0 | EDIGSR1515 | IGD-E JACKET J-TUBE SUPPORT DETAILS - IFC | 15 | 2022-11-08 | 2022-11-29 | 2023-04-05 | 2023-04-27 | 104
0 | EDIGSR1530 | IGD-E JACKET RISER GENRAL ARRANGEMENT - IFC | 15 | 2022-11-08 | 2022-11-29 | 2023-04-05 | 2023-04-27 | 104
0 | EDIGSR1500 | IGD-E JACKET J-TUBE GENERAL ARRANGEMENT - IFC | 15 | 2022-11-15 | 2022-12-08 | 2023-04-05 | 2023-04-27 | 99
MISCELLANEOUS DELIVERABLES |  |  | 80 | 2022-09-22 | 2023-01-16 | 2023-01-04 | 2023-04-27 | 72
0 | EDIGSR2000 | IGD-E STRUCTURAL MISCELLANEOUS DELIVERABLES - ICR | 20 | 2022-09-22 | 2022-10-20 | 2023-01-04 | 2023-01-31 | 72
0 | EDIGSR2005 | IGD-E STRUCTURAL MISCELLANEOUS DELIVERABLES - IFA | 20 | 2022-11-03 | 2022-12-05 | 2023-02-15 | 2023-03-14 | 72
0 | EDIGSR2010 | IGD-E STRUCTURAL MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-19 | 2023-01-16 | 2023-03-29 | 2023-04-27 | 72
PIPELINE |  |  | 76 | 2022-08-15 | 2022-11-28 | 2023-01-10 | 2023-04-27 | 104
DRAWINGS |  |  | 76 | 2022-08-15 | 2022-11-28 | 2023-01-10 | 2023-04-27 | 104
0 | DEP1PL4970 | PIPELINE / UMBILICAL APPROACH DRAWING AT IGD-E TOWER - ICR | 16 | 2022-08-15 | 2022-09-05 | 2023-01-10 | 2023-01-31 | 104
0 | DEP1PL5010 | PIPELINE / UMBILICAL APPROACH DRAWING AT IGD-E TOWER - IFA | 16 | 2022-09-20 | 2022-10-11 | 2023-02-15 | 2023-03-08 | 104
0 | DEP1PL4960 | PIPELINE / UMBILICAL APPROACH DRAWING AT IGD-E TOWER - IFC | 24 | 2022-10-26 | 2022-11-28 | 2023-03-23 | 2023-04-27 | 104
NAVAL & ARCHITECTURE |  |  | 159 | 2022-04-19 | 2022-12-08 | 2022-09-26 | 2023-04-27 | 99
DOCUMENTS |  |  | 159 | 2022-04-19 | 2022-12-08 | 2022-09-26 | 2023-04-27 | 99
0 | EDIDNA1000 | IGD-E TOPSIDE -WEIGHT & COG CALCULATION - ICR | 20 | 2022-04-19 | 2022-05-20 | 2022-09-26 | 2022-10-21 | 108
0 | EDIDNA1015 | IGD-E TOPSIDE -WEIGHT & COG CALCULATION DEMOLITION - ICR | 20 | 2022-05-19 | 2022-06-16 | 2023-01-04 | 2023-01-31 | 159
0 | EDIDNA1035 | IGD-E JACKET-WEIGHT & COG CALCULATION - ICR | 20 | 2022-05-19 | 2022-06-16 | 2022-11-28 | 2022-12-27 | 134
0 | EDIDNA1005 | IGD-E TOPSIDE -WEIGHT & COG CALCULATION - IFA | 20 | 2022-06-03 | 2022-07-01 | 2022-11-07 | 2022-12-06 | 108
0 | EDIDNA1020 | IGD-E TOPSIDE -WEIGHT & COG CALCULATION DEMOLITION - IFA | 20 | 2022-06-30 | 2022-08-02 | 2023-02-15 | 2023-03-14 | 159
0 | EDIDNA1010 | IGD-E TOPSIDE -WEIGHT & COG CALCULATION - IFC | 20 | 2022-07-20 | 2022-08-17 | 2023-03-13 | 2023-04-07 | 166
0 | EDIDNA1025 | IGD-E TOPSIDE -WEIGHT & COG CALCULATION DEMOLITION - IFC | 20 | 2022-08-16 | 2022-09-13 | 2023-03-29 | 2023-04-27 | 159
0 | EDIDNA1045 | IGD-E JACKET-WEIGHT & COG CALCULATION - IFA | 20 | 2022-09-27 | 2022-10-25 | 2023-02-15 | 2023-03-14 | 99
0 | EDIDNA1055 | IGD-E JACKET-WEIGHT & COG CALCULATION - IFC | 20 | 2022-11-08 | 2022-12-08 | 2023-03-29 | 2023-04-27 | 99
PIPELINE |  |  | 265 | 2021-12-19 | 2023-01-04 | 2022-02-14 | 2023-06-20 | 117
DOCUMENTS |  |  | 235 | 2021-12-19 | 2022-11-21 | 2022-02-14 | 2023-04-11 | 100
DESIGN BASIS |  |  | 138 | 2021-12-19 | 2022-07-04 | 2022-02-14 | 2022-12-09 | 110
0 | EDCDPL1000 | SUBSEA PIPELINE - RISER AND CABLE DESIGN BASIS - ICR | 25 | 2021-12-19 | 2022-01-21 | 2022-02-14 | 2022-03-18 | 41
0 | EDCDPL1005 | SUBSEA PIPELINE - RISER AND CABLE DESIGN BASIS - IFA | 16 | 2022-01-21 | 2022-02-14 | 2022-06-06 | 2022-06-27 | 93
0 | EDCDPL1015 | BUCKLING & WALKING DESIGN BASIS - ICR | 20 | 2022-03-23 | 2022-04-20 | 2022-08-05 | 2022-09-01 | 91
0 | EDCDPL1010 | SUBSEA PIPELINE - RISER AND CABLE DESIGN BASIS - IFC | 6 | 2022-04-12 | 2022-04-20 | 2022-07-15 | 2022-07-22 | 62
0 | EDCDPL1020 | BUCKLING & WALKING DESIGN BASIS - IFA | 15 | 2022-05-09 | 2022-05-30 | 2022-10-13 | 2022-11-02 | 110
0 | EDCDPL1025 | BUCKLING & WALKING DESIGN BASIS - IFC | 15 | 2022-06-13 | 2022-07-04 | 2022-11-17 | 2022-12-09 | 110
SCOPE OF WORK |  |  | 50 | 2021-12-19 | 2022-02-25 | 2022-02-21 | 2022-04-29 | 46
0 | EDCDPL1030 | SOW FOR GEOTECHNICAL INVESTIGATION FOR SUBSEA PIPELINES, CABLES AND UMBILICALS - ICR | 20 | 2021-12-19 | 2022-01-14 | 2022-02-21 | 2022-03-18 | 46
0 | EDCDPL1045 | SOW FOR GEOPHYSICAL AND ROV INVESTIGATION FOR OFFSHORE PLATFORMS, SUBSEA PIPELINES, CABLES AND UMBILICALS - ICR | 20 | 2021-12-19 | 2022-01-14 | 2022-02-21 | 2022-03-18 | 46
0 | EDCDPL1035 | SOW FOR GEOTECHNICAL INVESTIGATION FOR SUBSEA PIPELINES, CABLES AND UMBILICALS - IFA | 8 | 2022-01-28 | 2022-02-09 | 2022-04-04 | 2022-04-13 | 46
0 | EDCDPL1050 | SOW FOR GEOPHYSICAL AND ROV INVESTIGATION FOR OFFSHORE PLATFORMS, SUBSEA PIPELINES, CABLES AND UMBILICALS - IFA | 8 | 2022-01-28 | 2022-02-09 | 2022-04-04 | 2022-04-13 | 46
0 | EDCDPL1040 | SOW FOR GEOTECHNICAL INVESTIGATION FOR SUBSEA PIPELINES, CABLES AND UMBILICALS - IFC | 2 | 2022-02-23 | 2022-02-25 | 2022-04-28 | 2022-04-29 | 46
0 | EDCDPL1055 | SOW FOR GEOPHYSICAL & ROV INVESTIGATION FOR OFFSHORE PLATFORMS, SUBSEA PIPELINES, CABLES & UMBILICALS - IFC | 2 | 2022-02-23 | 2022-02-25 | 2022-04-28 | 2022-04-29 | 46
TBE |  |  | 87 | 2022-04-01 | 2022-08-10 | 2022-06-08 | 2022-11-25 | 78
THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) |  |  | 66 | 2022-05-05 | 2022-08-10 | 2022-08-04 | 2022-11-03 | 62
SCOPE OF WORK |  |  | 50 | 2022-05-05 | 2022-07-19 | 2022-08-04 | 2022-11-03 | 78
0 | EDCDPL1060 | SOW FOR THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) - ICR | 10 | 2022-05-05 | 2022-05-19 | 2022-08-04 | 2022-08-17 | 62
0 | EDCDPL1065 | SOW FOR THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES )- IFA | 10 | 2022-06-02 | 2022-06-16 | 2022-09-23 | 2022-10-06 | 78
0 | EDCDPL1070 | SOW FOR THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) - IFC | 10 | 2022-06-30 | 2022-07-19 | 2022-10-21 | 2022-11-03 | 78
TBE |  |  | 45 | 2022-06-03 | 2022-08-10 | 2022-09-02 | 2022-11-03 | 62
0 | EDCDPL2100 | ISSUE TBE : THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) - ICR | 10 | 2022-06-03 | 2022-06-17 | 2022-09-02 | 2022-09-15 | 62
0 | EDCDPL2105 | ISSUE TBE : THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) - IFA | 10 | 2022-07-01 | 2022-07-20 | 2022-09-30 | 2022-10-13 | 62
0 | EDCDPL2108 | ISSUE TBE : THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) - IFC | 5 | 2022-08-03 | 2022-08-10 | 2022-10-28 | 2022-11-03 | 62
DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL PIPELINE |  |  | 60 | 2022-04-22 | 2022-07-25 | 2022-08-11 | 2022-11-25 | 90
SCOPE OF WORK |  |  | 50 | 2022-04-22 | 2022-07-06 | 2022-08-11 | 2022-11-25 | 100
0 | EDCDPL2920 | SOW FOR DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE - ICR | 10 | 2022-04-22 | 2022-05-11 | 2022-08-11 | 2022-08-24 | 73
0 | EDCDPL2930 | SOW FOR DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE - IFA | 10 | 2022-05-25 | 2022-06-08 | 2022-10-03 | 2022-10-14 | 90
0 | EDCDPL2940 | SOW FOR DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE - IFC | 10 | 2022-06-22 | 2022-07-06 | 2022-11-14 | 2022-11-25 | 100
TBE |  |  | 50 | 2022-05-11 | 2022-07-25 | 2022-09-19 | 2022-11-25 | 90
0 | EDCDPL2950 | ISSUE TBE : DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE - ICR | 10 | 2022-05-11 | 2022-05-25 | 2022-09-19 | 2022-09-30 | 90
0 | EDCDPL2960 | ISSUE TBE : DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE - IFA | 10 | 2022-06-08 | 2022-06-22 | 2022-10-17 | 2022-10-28 | 90
0 | EDCDPL2970 | ISSUE TBE : DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE - IFC | 10 | 2022-07-06 | 2022-07-25 | 2022-11-14 | 2022-11-25 | 90
GLOBAL BUCKLING AND WALKING ANALYSIS |  |  | 58 | 2022-04-01 | 2022-06-27 | 2022-06-08 | 2022-10-19 | 80
SCOPE OF WORK |  |  | 38 | 2022-04-01 | 2022-05-30 | 2022-06-08 | 2022-08-04 | 46
0 | EDCDPL2980 | SOW FOR GLOBAL BUCKLING AND WALKING ANALYSIS - ICR | 5 | 2022-04-01 | 2022-04-08 | 2022-06-08 | 2022-06-14 | 45
0 | EDCDPL2990 | SOW FOR GLOBAL BUCKLING AND WALKING ANALYSIS - IFA | 3 | 2022-04-22 | 2022-04-27 | 2022-06-29 | 2022-07-01 | 45
0 | EDCDPL3000 | SOW FOR GLOBAL BUCKLING AND WALKING ANALYSIS - IFC | 10 | 2022-05-16 | 2022-05-30 | 2022-07-22 | 2022-08-04 | 46
TBE |  |  | 45 | 2022-04-20 | 2022-06-27 | 2022-06-27 | 2022-10-19 | 80
0 | EDCDPL3010 | ISSUE TBE : GLOBAL BUCKLING AND WALKING ANALYSIS - ICR | 5 | 2022-04-20 | 2022-04-27 | 2022-06-27 | 2022-07-01 | 45
0 | EDCDPL3020 | ISSUE TBE : GLOBAL BUCKLING AND WALKING ANALYSIS - IFA | 10 | 2022-05-16 | 2022-05-30 | 2022-07-22 | 2022-08-04 | 46
0 | EDCDPL3030 | ISSUE TBE : GLOBAL BUCKLING AND WALKING ANALYSIS - IFC | 10 | 2022-06-13 | 2022-06-27 | 2022-10-06 | 2022-10-19 | 80
SPECIFICATION |  |  | 137 | 2021-12-21 | 2022-07-06 | 2022-02-18 | 2023-02-16 | 157
0 | EDCDPL1120 | SPECIFICATION FOR PIPELINE WELDING - ICR | 14 | 2021-12-21 | 2022-01-11 | 2022-02-24 | 2022-03-16 | 46
0 | EDCDPL1090 | SPECIFICATION FOR LINE PIPE (SMLS) - ICR | 20 | 2021-12-21 | 2022-01-19 | 2022-02-18 | 2022-03-17 | 42
0 | EDCDPL1195 | SPECIFICATION FOR BARRED TEE - ICR | 15 | 2021-12-30 | 2022-01-21 | 2022-04-18 | 2022-05-11 | 76
0 | EDCDPL1465 | SPECIFICATION FOR RISER HANGER FLANGES - ICR | 10 | 2022-01-07 | 2022-01-21 | 2022-06-16 | 2022-06-29 | 111
0 | EDCDPL1165 | SPECIFICATION FOR ANTI-CORROSION COATING (3LPE) - ICR | 15 | 2022-01-04 | 2022-01-25 | 2022-08-17 | 2022-09-06 | 155
0 | EDCDPL1135 | SPECIFICATION FOR PIPELINE INDUCTION BENDS - ICR | 9 | 2022-01-12 | 2022-01-25 | 2022-04-29 | 2022-05-17 | 77
0 | EDCDPL1270 | SPECIFICATION FOR FIELD JOINT COATING - ICR | 10 | 2022-01-21 | 2022-02-04 | 2022-10-12 | 2022-10-25 | 182
0 | EDCDPL1075 | SPECIFICATION FOR LINE PIPE (SAW) - ICR | 21 | 2022-01-07 | 2022-02-07 | 2022-03-07 | 2022-04-04 | 41
0 | EDCDPL1180 | SPECIFICATION FOR ANTI-CORROSION COATING (3LPP) - ICR | 15 | 2022-01-21 | 2022-02-11 | 2022-09-22 | 2022-10-12 | 168
0 | EDCDPL1240 | SPECIFICATION FOR CONCRETE WEIGHT COATING & ANODE INSTALLATION - ICR | 15 | 2022-01-21 | 2022-02-11 | 2022-09-02 | 2022-09-22 | 154
0 | EDCDPL1150 | SPECIFICATION FOR ADDITIONAL STABILIZATION - ICR | 15 | 2022-01-25 | 2022-02-15 | 2022-09-05 | 2022-09-23 | 152
0 | EDCDPL1125 | SPECIFICATION FOR PIPELINE WELDING - IFA | 15 | 2022-01-25 | 2022-02-15 | 2022-03-31 | 2022-04-20 | 46
0 | EDCDPL1095 | SPECIFICATION FOR LINE PIPE (SMLS) - IFA | 10 | 2022-02-02 | 2022-02-16 | 2022-04-12 | 2022-04-25 | 49
0 | EDCDPL1435 | SPECIFICATION FOR POLYETHYLENE FIELD JOINT COATING - ICR | 15 | 2022-01-28 | 2022-02-18 | 2022-09-29 | 2022-10-19 | 168
0 | EDCDPL1470 | SPECIFICATION FOR RISER HANGER FLANGES - IFA | 10 | 2022-02-04 | 2022-02-18 | 2022-07-19 | 2022-08-01 | 111
0 | EDCDPL1140 | SPECIFICATION FOR PIPELINE INDUCTION BENDS - IFA | 10 | 2022-02-08 | 2022-02-22 | 2022-07-28 | 2022-08-11 | 116
0 | EDCDPL1315 | SPECIFICATION FOR NEOPRENE COATING - ICR | 25 | 2022-01-21 | 2022-02-25 | 2022-03-25 | 2022-04-28 | 45
0 | EDCDPL1255 | SPECIFICATION FOR DROPPED OBJECTION PROTECTION COVERS - ICR | 25 | 2022-01-21 | 2022-02-25 | 2022-09-06 | 2022-10-10 | 156
0 | EDCDPL1200 | SPECIFICATION FOR BARRED TEE - IFA | 15 | 2022-02-04 | 2022-02-25 | 2022-06-27 | 2022-07-20 | 98
0 | EDCDPL1170 | SPECIFICATION FOR ANTI-CORROSION COATING (3LPE) - IFA | 16 | 2022-02-08 | 2022-03-02 | 2022-09-21 | 2022-10-12 | 155
0 | EDCDPL1330 | SPECIFICATION FOR OFFSHORE PIPELINE - RISER AND CABLE INSTALLATION - ICR | 11 | 2022-02-17 | 2022-03-04 | 2022-04-21 | 2022-05-10 | 45
0 | EDCDPL1285 | SPECIFICATION FOR FLEXIBLE MATTRESS DESIGN & INSTALLATION - ICR | 11 | 2022-02-17 | 2022-03-04 | 2022-10-05 | 2022-10-19 | 158
0 | EDCDPL1275 | SPECIFICATION FOR FIELD JOINT COATING - IFA | 11 | 2022-02-18 | 2022-03-07 | 2022-11-09 | 2022-11-23 | 182
0 | EDCDPL1105 | SPECIFICATION FOR PIPELINE FLANGES AND FITTINGS- ICR | 16 | 2022-02-16 | 2022-03-10 | 2022-06-07 | 2022-06-29 | 76
0 | EDCDPL1480 | SPECIFICATION FOR SHORE APPROACH - ICR | 25 | 2022-02-04 | 2022-03-11 | 2022-08-19 | 2022-09-22 | 134
0 | EDCDPL1080 | SPECIFICATION FOR LINE PIPE (SAW) - IFA | 15 | 2022-02-21 | 2022-03-14 | 2022-04-21 | 2022-05-16 | 43
0 | EDCDPL1405 | SPECIFICATION FOR PIPELINE PRESERVATION & MOTHBALLING - ICR | 11 | 2022-03-03 | 2022-03-18 | 2022-10-14 | 2022-10-28 | 155
0 | EDCDPL1300 | SPECIFICATION FOR HYDROSTATIC TESTING OF PIPELINE - ICR | 10 | 2022-03-04 | 2022-03-18 | 2022-10-20 | 2022-11-02 | 158
0 | EDCDPL1345 | SPECIFICATION FOR OFFSHORE TRENCHING AND BACKFILLING - ICR | 10 | 2022-03-07 | 2022-03-21 | 2022-10-17 | 2022-10-28 | 154
0 | EDCDPL1185 | SPECIFICATION FOR ANTI-CORROSION COATING (3LPP) - IFA | 16 | 2022-02-25 | 2022-03-21 | 2022-11-02 | 2022-11-23 | 172
0 | EDCDPL1245 | SPECIFICATION FOR CONCRETE WEIGHT COATING & ANODE INSTALLATION - IFA | 16 | 2022-02-25 | 2022-03-21 | 2022-10-07 | 2022-10-28 | 154
0 | EDCDPL1100 | SPECIFICATION FOR LINE PIPE (SMLS) - IFC | 15 | 2022-03-02 | 2022-03-23 | 2022-05-13 | 2022-06-02 | 49
0 | EDCDPL1155 | SPECIFICATION FOR ADDITIONAL STABILIZATION - IFA | 16 | 2022-03-01 | 2022-03-23 | 2022-10-10 | 2022-10-31 | 152
0 | EDCDPL1210 | SPECIFICATION FOR CATHODIC PROTECTION AND PIPELINE SACRIFICIAL ANODES - ICR | 10 | 2022-03-11 | 2022-03-25 | 2022-08-04 | 2022-08-17 | 98
0 | EDCDPL1475 | SPECIFICATION FOR RISER HANGER FLANGES - IFC | 15 | 2022-03-04 | 2022-03-25 | 2022-08-16 | 2022-09-05 | 111
0 | EDCDPL1390 | SPECIFICATION FOR PIPELINE FREE SPAN CORRECTION - ICR | 10 | 2022-03-11 | 2022-03-25 | 2022-09-23 | 2022-10-06 | 134
0 | EDCDPL1320 | SPECIFICATION FOR NEOPRENE COATING - IFA | 10 | 2022-03-11 | 2022-03-25 | 2022-10-20 | 2022-11-02 | 153
0 | EDCDPL1440 | SPECIFICATION FOR POLYETHYLENE FIELD JOINT COATING - IFA | 15 | 2022-03-04 | 2022-03-25 | 2022-11-03 | 2022-11-23 | 168
0 | EDCDPL1130 | SPECIFICATION FOR PIPELINE WELDING - IFC | 20 | 2022-03-01 | 2022-03-29 | 2022-05-10 | 2022-06-06 | 46
0 | EDCDPL1205 | SPECIFICATION FOR BARRED TEE - IFC | 15 | 2022-03-11 | 2022-04-01 | 2022-08-04 | 2022-08-24 | 98
0 | EDCDPL1260 | SPECIFICATION FOR DROPPED OBJECTION PROTECTION COVERS - IFA | 15 | 2022-03-11 | 2022-04-01 | 2022-10-25 | 2022-11-14 | 156
0 | EDCDPL1290 | SPECIFICATION FOR FLEXIBLE MATTRESS DESIGN & INSTALLATION - IFA | 10 | 2022-03-18 | 2022-04-01 | 2022-11-10 | 2022-11-23 | 163
0 | EDCDPL1335 | SPECIFICATION FOR OFFSHORE PIPELINE - RISER AND CABLE INSTALLATION - IFA | 10 | 2022-03-18 | 2022-04-01 | 2022-05-25 | 2022-06-07 | 45
0 | EDCDPL2550 | SPECIFICATION FOR CATHODIC PROTECTION OF PIPELINES - ICR | 10 | 2022-03-18 | 2022-04-01 | 2022-08-11 | 2022-08-24 | 98
0 | EDCDPL1085 | SPECIFICATION FOR LINE PIPE (SAW) - IFC | 5 | 2022-03-28 | 2022-04-04 | 2022-05-31 | 2022-06-06 | 43
0 | EDCDPL1145 | SPECIFICATION FOR PIPELINE INDUCTION BENDS - IFC | 21 | 2022-03-08 | 2022-04-06 | 2022-08-25 | 2022-09-23 | 116
0 | EDUDUC1000 | SPECIFICATION FOR PIGGYBACK SADDLES AND STRAPPING ARRANGEMENT - ICR | 14 | 2022-03-21 | 2022-04-08 | 2022-05-26 | 2022-06-14 | 45
0 | EDCDPL1175 | SPECIFICATION FOR ANTI-CORROSION COATING (3LPE) - IFC | 20 | 2022-03-16 | 2022-04-13 | 2022-10-27 | 2022-11-23 | 155
0 | EDCDPL1110 | SPECIFICATION FOR PIPELINE FLANGES AND FITTINGS - IFA | 15 | 2022-03-24 | 2022-04-14 | 2022-07-18 | 2022-08-08 | 76
0 | EDCDPL1375 | SPECIFICATION FOR PIPELINE CLEANING - FLUSHING AND FLOODING.- ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-09-23 | 2022-10-06 | 119
0 | EDCDPL1305 | SPECIFICATION FOR HYDROSTATIC TESTING OF PIPELINE - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-11-17 | 2022-11-30 | 158
0 | EDCDPL1410 | SPECIFICATION FOR PIPELINE PRESERVATION & MOTHBALLING - IFA | 10 | 2022-04-01 | 2022-04-15 | 2022-11-14 | 2022-11-25 | 155
0 | EDCDPL1485 | SPECIFICATION FOR SHORE APPROACH - IFA | 15 | 2022-03-25 | 2022-04-15 | 2022-10-10 | 2022-10-28 | 135
0 | EDCDPL1350 | SPECIFICATION FOR OFFSHORE TRENCHING AND BACKFILLING - IFA | 10 | 2022-04-04 | 2022-04-18 | 2022-11-14 | 2022-11-25 | 154
0 | EDCDPL1450 | SPECIFICATION FOR PRE-CONSTRUCTION AS-LAID AND AS-BUILT SURVEY - ICR | 10 | 2022-04-07 | 2022-04-21 | 2022-11-23 | 2022-12-08 | 158
0 | EDCDPL1325 | SPECIFICATION FOR NEOPRENE COATING - IFC | 10 | 2022-04-08 | 2022-04-22 | 2022-11-17 | 2022-11-30 | 153
0 | EDCDPL1215 | SPECIFICATION FOR CATHODIC PROTECTION AND PIPELINE SACRIFICIAL ANODES - IFA | 10 | 2022-04-08 | 2022-04-22 | 2022-09-08 | 2022-09-21 | 103
0 | EDCDPL1395 | SPECIFICATION FOR PIPELINE FREE SPAN CORRECTION - IFA | 10 | 2022-04-08 | 2022-04-22 | 2022-10-21 | 2022-11-03 | 134
0 | EDCDPL1190 | SPECIFICATION FOR ANTI-CORROSION COATING (3LPP) - IFC | 15 | 2022-04-04 | 2022-04-25 | 2022-12-12 | 2022-12-30 | 172
0 | EDCDPL1250 | SPECIFICATION FOR CONCRETE WEIGHT COATING & ANODE INSTALLATION - IFC | 15 | 2022-04-04 | 2022-04-25 | 2022-11-22 | 2022-12-14 | 160
0 | EDCDPL1445 | SPECIFICATION FOR POLYETHYLENE FIELD JOINT COATING - IFC | 15 | 2022-04-08 | 2022-04-29 | 2022-12-12 | 2022-12-30 | 168
0 | EDCDPL1420 | SPECIFICATION FOR PIPELINE/FLEXIBLE CROSSING - ICR | 10 | 2022-04-15 | 2022-04-29 | 2022-10-17 | 2022-10-28 | 125
0 | EDCDPL1265 | SPECIFICATION FOR DROPPED OBJECTION PROTECTION COVERS - IFC | 10 | 2022-04-15 | 2022-04-29 | 2022-11-29 | 2022-12-14 | 156
0 | EDCDPL2560 | SPECIFICATION FOR CATHODIC PROTECTION OF PIPELINES - IFA | 10 | 2022-04-15 | 2022-04-29 | 2022-09-08 | 2022-09-21 | 98
0 | EDCDPL1280 | SPECIFICATION FOR FIELD JOINT COATING - IFC | 15 | 2022-04-13 | 2022-05-09 | 2022-12-12 | 2022-12-30 | 165
0 | EDCDPL1160 | SPECIFICATION FOR ADDITIONAL STABILIZATION - IFC | 20 | 2022-04-06 | 2022-05-09 | 2022-11-15 | 2022-12-14 | 152
0 | EDCDPL1340 | SPECIFICATION FOR OFFSHORE PIPELINE - RISER AND CABLE INSTALLATION - IFC | 15 | 2022-04-15 | 2022-05-11 | 2022-12-22 | 2023-01-11 | 171
0 | EDCDPL1295 | SPECIFICATION FOR FLEXIBLE MATTRESS DESIGN & INSTALLATION - IFC | 15 | 2022-04-15 | 2022-05-11 | 2022-12-12 | 2022-12-30 | 163
0 | EDUDUC1005 | SPECIFICATION FOR PIGGYBACK SADDLES AND STRAPPING ARRANGEMENT - IFA | 14 | 2022-04-22 | 2022-05-17 | 2022-06-29 | 2022-07-21 | 45
0 | EDCDPL1310 | SPECIFICATION FOR HYDROSTATIC TESTING OF PIPELINE - IFC | 10 | 2022-04-29 | 2022-05-18 | 2022-12-19 | 2022-12-30 | 158
0 | EDCDPL1380 | SPECIFICATION FOR PIPELINE CLEANING - FLUSHING AND FLOODING.- IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-10-21 | 2022-11-03 | 119
0 | EDCDPL1455 | SPECIFICATION FOR PRE-CONSTRUCTION AS-LAID AND AS-BUILT SURVEY - IFA | 10 | 2022-05-10 | 2022-05-24 | 2022-12-23 | 2023-01-05 | 158
0 | EDCDPL1415 | SPECIFICATION FOR PIPELINE PRESERVATION & MOTHBALLING - IFC | 15 | 2022-04-29 | 2022-05-25 | 2022-12-14 | 2023-01-03 | 155
0 | EDCDPL1220 | SPECIFICATION FOR CATHODIC PROTECTION AND PIPELINE SACRIFICIAL ANODES - IFC | 10 | 2022-05-11 | 2022-05-25 | 2022-10-06 | 2022-10-19 | 103
0 | EDCDPL1490 | SPECIFICATION FOR SHORE APPROACH - IFC | 15 | 2022-04-29 | 2022-05-25 | 2022-11-14 | 2022-12-06 | 135
0 | EDCDPL1355 | SPECIFICATION FOR OFFSHORE TRENCHING AND BACKFILLING - IFC | 15 | 2022-05-05 | 2022-05-26 | 2022-12-14 | 2023-01-03 | 154
0 | EDCDPL1115 | SPECIFICATION FOR PIPELINE FLANGES AND FITTINGS - IFC | 20 | 2022-04-28 | 2022-05-31 | 2022-08-22 | 2022-09-19 | 76
0 | EDCDPL1400 | SPECIFICATION FOR PIPELINE FREE SPAN CORRECTION - IFC | 15 | 2022-05-11 | 2022-06-01 | 2022-11-18 | 2022-12-12 | 134
0 | EDCDPL1425 | SPECIFICATION FOR PIPELINE/FLEXIBLE CROSSING - IFA | 10 | 2022-05-18 | 2022-06-01 | 2022-11-14 | 2022-11-25 | 125
0 | EDCDPL2570 | SPECIFICATION FOR CATHODIC PROTECTION OF PIPELINES - IFC | 10 | 2022-05-18 | 2022-06-01 | 2022-10-06 | 2022-10-19 | 98
0 | EDCDPL1385 | SPECIFICATION FOR PIPELINE CLEANING - FLUSHING AND FLOODING.- IFC | 15 | 2022-06-01 | 2022-06-22 | 2022-11-18 | 2022-12-12 | 119
0 | EDUDUC1010 | SPECIFICATION FOR PIGGYBACK SADDLES AND STRAPPING ARRANGEMENT - IFC | 19 | 2022-05-31 | 2022-06-27 | 2022-09-06 | 2022-09-30 | 67
0 | EDCDPL1460 | SPECIFICATION FOR PRE-CONSTRUCTION AS-LAID AND AS-BUILT SURVEY - IFC | 20 | 2022-06-07 | 2022-07-05 | 2023-01-20 | 2023-02-16 | 158
0 | EDCDPL1430 | SPECIFICATION FOR PIPELINE/FLEXIBLE CROSSING - IFC | 15 | 2022-06-15 | 2022-07-06 | 2022-12-14 | 2023-01-03 | 125
DATA SHEETS |  |  | 157 | 2022-01-11 | 2022-08-26 | 2022-03-10 | 2022-11-03 | 50
0 | EDCDPL1525 | DATASHEET FOR LINE PIPE (SMLS) - ICR | 8 | 2022-01-11 | 2022-01-21 | 2022-03-10 | 2022-03-21 | 42
0 | EDCDPL1540 | DATASHEET FOR HOT INDUCTION BEND - ICR | 9 | 2022-01-14 | 2022-01-27 | 2022-06-17 | 2022-06-29 | 106
0 | EDCDPL1510 | DATASHEET FOR LINE PIPE (SAW) - ICR | 20 | 2022-01-12 | 2022-02-09 | 2022-03-10 | 2022-04-06 | 41
0 | EDCDPL1530 | DATASHEET FOR LINE PIPE (SMLS) - IFA | 9 | 2022-02-04 | 2022-02-17 | 2022-04-05 | 2022-04-15 | 42
0 | EDCDPL1545 | DATASHEET FOR HOT INDUCTION BEND - IFA | 10 | 2022-02-10 | 2022-02-24 | 2022-07-19 | 2022-08-01 | 106
0 | EDCDPL1515 | DATASHEET FOR LINE PIPE (SAW) - IFA | 15 | 2022-02-23 | 2022-03-16 | 2022-04-21 | 2022-05-16 | 41
0 | EDCDPL1535 | DATASHEET FOR LINE PIPE (SMLS) - IFC | 14 | 2022-03-03 | 2022-03-23 | 2022-05-05 | 2022-05-24 | 42
0 | EDCDPL1555 | DATASHEET FOR BARRED TEE - ICR | 10 | 2022-03-16 | 2022-03-30 | 2022-07-01 | 2022-07-19 | 74
0 | EDCDPL1550 | DATASHEET FOR HOT INDUCTION BEND - IFC | 15 | 2022-03-10 | 2022-03-31 | 2022-08-16 | 2022-09-05 | 106
0 | EDCDPL1570 | DATASHEET FOR FLANGES AND FITTINGS - ICR | 10 | 2022-03-21 | 2022-04-04 | 2022-07-06 | 2022-07-22 | 74
0 | EDCDPL1520 | DATASHEET FOR LINE PIPE (SAW) - IFC | 3 | 2022-03-30 | 2022-04-04 | 2022-05-31 | 2022-06-02 | 41
0 | EDCDPL1585 | DATASHEET FOR RISER HANGER FLANGES - ICR | 10 | 2022-03-22 | 2022-04-05 | 2022-07-07 | 2022-07-25 | 74
0 | EDCDPL1560 | DATASHEET FOR BARRED TEE - IFA | 5 | 2022-04-13 | 2022-04-20 | 2022-08-09 | 2022-08-15 | 78
0 | EDCDPL1575 | DATASHEET FOR FLANGES AND FITTINGS - IFA | 5 | 2022-04-18 | 2022-04-25 | 2022-08-09 | 2022-08-15 | 75
0 | EDCDPL1590 | DATASHEET FOR RISER HANGER FLANGES - IFA | 5 | 2022-04-19 | 2022-04-26 | 2022-08-09 | 2022-08-15 | 74
0 | EDCDPL1565 | DATASHEET FOR BARRED TEE - IFC | 5 | 2022-05-09 | 2022-05-16 | 2022-08-30 | 2022-09-05 | 78
0 | EDCDPL1580 | DATASHEET FOR FLANGES AND FITTINGS - IFC | 4 | 2022-05-12 | 2022-05-18 | 2022-08-30 | 2022-09-02 | 75
0 | EDCDPL1595 | DATASHEET FOR RISER HANGER FLANGES - IFC | 5 | 2022-05-13 | 2022-05-20 | 2022-08-30 | 2022-09-05 | 74
0 | EDCDPL1600 | DATASHEET FOR SACRIFICIAL ANODES - ICR | 10 | 2022-06-07 | 2022-06-21 | 2022-08-12 | 2022-08-25 | 45
0 | EDCDPL1605 | DATASHEET FOR SACRIFICIAL ANODES - IFA | 15 | 2022-07-05 | 2022-07-29 | 2022-09-16 | 2022-10-06 | 50
0 | EDCDPL1610 | DATASHEET FOR SACRIFICIAL ANODES - IFC | 10 | 2022-08-12 | 2022-08-26 | 2022-10-21 | 2022-11-03 | 50
REPORTS & CALCULATIONS |  |  | 219 | 2022-01-10 | 2022-11-21 | 2022-03-08 | 2023-04-11 | 100
0 | EDCDPL1615 | PIPELINE WALL THICKNESS DESIGN REPORT - ICR | 25 | 2022-01-10 | 2022-02-14 | 2022-03-08 | 2022-04-11 | 41
0 | EDCDPL1630 | PIPELINE PIGGING SYSTEM ASSURANCE STUDY REPORT - ICR | 19 | 2022-02-14 | 2022-03-11 | 2022-04-18 | 2022-05-17 | 45
0 | EDCDPL1620 | PIPELINE WALL THICKNESS DESIGN REPORT - IFA | 12 | 2022-02-28 | 2022-03-16 | 2022-08-25 | 2022-09-09 | 122
0 | EDCDPL1635 | PIPELINE PIGGING SYSTEM ASSURANCE STUDY REPORT - IFA | 10 | 2022-03-25 | 2022-04-08 | 2022-06-01 | 2022-06-14 | 45
0 | EDCDPL1625 | PIPELINE WALL THICKNESS DESIGN REPORT - IFC | 10 | 2022-04-20 | 2022-05-09 | 2022-09-12 | 2022-09-23 | 97
0 | EDCDPL1640 | PIPELINE PIGGING SYSTEM ASSURANCE STUDY REPORT - IFC | 10 | 2022-04-22 | 2022-05-11 | 2022-07-26 | 2022-08-08 | 61
0 | EDCDPL1720 | SHORE APPROACH DESIGN REPORT AT SOUTH ARZANA - ICR | 10 | 2022-04-28 | 2022-05-16 | 2022-06-30 | 2022-07-18 | 42
0 | EDCDPL1705 | SHORE APPROACH DESIGN REPORT AT EAST ARZANA - ICR | 15 | 2022-04-28 | 2022-05-23 | 2022-06-23 | 2022-07-18 | 37
0 | EDCDPL1645 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL1,PL2&PL3 - ICR | 15 | 2022-04-28 | 2022-05-23 | 2022-06-23 | 2022-07-18 | 37
0 | EDCDPL1735 | SHORE APPROACH DESIGN REPORT AT ZIRKU - ICR | 10 | 2022-05-17 | 2022-05-30 | 2022-07-07 | 2022-07-25 | 37
0 | EDCDPL1660 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL4 - ICR | 15 | 2022-05-10 | 2022-05-30 | 2022-08-26 | 2022-09-15 | 75
0 | EDCDPL1750 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL4 - ICR | 15 | 2022-05-17 | 2022-06-06 | 2022-09-02 | 2022-09-22 | 75
0 | EDCDPL1960 | PIPELINE EXPANSION DESIGN REPORT FOR PL1,PL2&PL3 - ICR | 15 | 2022-05-17 | 2022-06-06 | 2022-07-07 | 2022-08-01 | 37
0 | EDCDPL1675 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL5 - ICR | 15 | 2022-05-17 | 2022-06-06 | 2022-11-18 | 2022-12-12 | 130
0 | EDCDPL1765 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL1,PL2&PL3 - ICR | 15 | 2022-05-17 | 2022-06-06 | 2022-11-10 | 2022-11-30 | 124
0 | EDCDPL2110 | CROSSING DESIGN REPORT FOR PL1,PL2&PL3 - ICR | 17 | 2022-05-17 | 2022-06-08 | 2022-07-07 | 2022-08-03 | 37
0 | EDCDPL1690 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL6 - ICR | 15 | 2022-05-24 | 2022-06-13 | 2022-12-06 | 2022-12-26 | 135
0 | EDCDPL1780 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL5 - ICR | 15 | 2022-05-24 | 2022-06-13 | 2022-11-17 | 2022-12-09 | 124
0 | EDCDPL2320 | RISER SA REPORT (BU HASEER TO ARZANAH) - ICR | 20 | 2022-05-19 | 2022-06-15 | 2022-10-07 | 2022-11-03 | 98
0 | EDCDPL2125 | CROSSING DESIGN REPORT FOR PL4 - ICR | 20 | 2022-05-19 | 2022-06-15 | 2022-09-26 | 2022-10-21 | 89
0 | EDCDPL1795 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL6 - ICR | 15 | 2022-05-31 | 2022-06-20 | 2022-11-24 | 2022-12-16 | 124
0 | EDCDPL2170 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL1,PL2&PL3- ICR | 20 | 2022-05-26 | 2022-06-22 | 2022-08-05 | 2022-09-01 | 48
0 | EDCDPL2140 | CROSSING DESIGN REPORT FOR PL5 - ICR | 20 | 2022-05-26 | 2022-06-22 | 2022-10-03 | 2022-10-28 | 89
0 | EDCDPL2335 | RISER SA REPORT @ HD-3 AND @ WHP T-4 - ICR | 20 | 2022-05-26 | 2022-06-22 | 2022-11-15 | 2022-12-14 | 120
0 | EDCDPL2155 | CROSSING DESIGN REPORT FOR PL6 - ICR | 20 | 2022-06-02 | 2022-06-29 | 2022-10-10 | 2022-11-04 | 89
0 | EDCDPL2185 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL4 - ICR | 20 | 2022-06-02 | 2022-06-29 | 2022-09-26 | 2022-10-21 | 79
0 | EDCDPL2350 | RISER SA REPORT (SATAH WHP-10 TO ARZANAH) - ICR | 20 | 2022-06-02 | 2022-06-29 | 2022-11-22 | 2022-12-21 | 120
0 | EDCDPL2515 | PIPELINE PLASTIC BENDING MOMENT CAPACITY - FEA STUDY REPORT- ICR | 20 | 2022-06-07 | 2022-07-04 | 2022-10-20 | 2022-11-16 | 94
0 | EDCDPL2200 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL5 - ICR | 20 | 2022-06-09 | 2022-07-06 | 2022-10-03 | 2022-10-28 | 79
0 | EDCDPL2365 | RISER SA REPOR (IGD-E AT KP-38 TO ARZANAH) - ICR | 20 | 2022-06-09 | 2022-07-06 | 2022-11-29 | 2022-12-28 | 120
0 | EDCDPL2395 | PL2&PL3 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT- ICR | 30 | 2022-05-31 | 2022-07-15 | 2022-08-05 | 2022-09-15 | 45
0 | EDCDPL2410 | PL4 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT- ICR | 30 | 2022-05-31 | 2022-07-15 | 2022-08-12 | 2022-09-22 | 50
0 | EDCDPL2455 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL1,PL2&PL3 - ICR | 15 | 2022-06-23 | 2022-07-18 | 2022-09-08 | 2022-09-28 | 52
0 | EDCDPL2215 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL6- ICR | 20 | 2022-06-16 | 2022-07-18 | 2022-10-10 | 2022-11-04 | 79
0 | EDCDPL2880 | RISER SA REPORT (BU HASEER TO ARZANAH) - IFA | 10 | 2022-06-30 | 2022-07-18 | 2022-11-18 | 2022-12-05 | 98
0 | EDCDPL2380 | PL1 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT - ICR | 30 | 2022-06-07 | 2022-07-22 | 2022-08-12 | 2022-09-22 | 45
0 | EDCDPL2470 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL4 - ICR | 15 | 2022-06-30 | 2022-07-25 | 2022-10-31 | 2022-11-18 | 84
0 | EDCDPL1755 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL4 - IFA | 10 | 2022-07-15 | 2022-07-29 | 2022-10-07 | 2022-10-20 | 60
0 | EDCDPL1665 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL4 - IFA | 10 | 2022-07-15 | 2022-07-29 | 2023-01-03 | 2023-01-16 | 120
0 | EDCDPL2485 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL5 - ICR | 15 | 2022-07-07 | 2022-08-01 | 2022-11-07 | 2022-11-25 | 84
0 | EDCDPL2520 | PIPELINE PLASTIC BENDING MOMENT CAPACITY - FEA STUDY REPORT -- IFA | 10 | 2022-07-22 | 2022-08-04 | 2023-02-15 | 2023-02-28 | 146
0 | EDCDPL1650 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL1,PL2&PL3 - IFA | 10 | 2022-07-22 | 2022-08-05 | 2022-12-20 | 2023-01-02 | 105
0 | EDCDPL1965 | PIPELINE EXPANSION DESIGN REPORT FOR PL1,PL2&PL3 - IFA | 10 | 2022-07-22 | 2022-08-05 | 2022-10-07 | 2022-10-20 | 55
0 | EDCDPL1725 | SHORE APPROACH DESIGN REPORT AT SOUTH ARZANA - IFA | 15 | 2022-07-15 | 2022-08-05 | 2022-12-13 | 2023-01-02 | 105
0 | EDCDPL1770 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL1,PL2&PL3 - IFA | 10 | 2022-07-22 | 2022-08-05 | 2023-01-17 | 2023-01-30 | 125
0 | EDCDPL2130 | CROSSING DESIGN REPORT FOR PL4 - IFA | 15 | 2022-07-15 | 2022-08-05 | 2022-11-07 | 2022-11-25 | 81
0 | EDCDPL2500 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL6 - ICR | 15 | 2022-07-19 | 2022-08-08 | 2022-11-14 | 2022-12-06 | 84
0 | EDCDPL2890 | RISER SA REPORT @ HD-3 AND @ WHP T-4 - IFA | 20 | 2022-07-07 | 2022-08-08 | 2023-01-06 | 2023-02-02 | 126
0 | EDCDPL2020 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL1,PL2&PL3 - ICR | 15 | 2022-07-22 | 2022-08-12 | 2022-10-07 | 2022-10-27 | 55
0 | EDCDPL2400 | PL2&PL3 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT-- IFA | 10 | 2022-07-29 | 2022-08-12 | 2022-11-24 | 2022-12-09 | 84
0 | EDCDPL2415 | PL4 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT-- IFA | 10 | 2022-07-29 | 2022-08-12 | 2022-12-05 | 2022-12-16 | 89
0 | EDCDPL2330 | RISER SA REPORT (BU HASEER TO ARZANAH) - IFC | 10 | 2022-08-02 | 2022-08-15 | 2022-12-20 | 2023-01-02 | 98
0 | EDCDPL2460 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL1,PL2&PL3 - IFA | 10 | 2022-08-02 | 2022-08-15 | 2022-10-27 | 2022-11-09 | 62
0 | EDCDPL2900 | RISER SA REPORT (SATAH WHP-10 TO ARZANAH) - IFA | 20 | 2022-07-19 | 2022-08-15 | 2023-01-13 | 2023-02-09 | 126
0 | EDCDPL2385 | PL1 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT -- IFA | 10 | 2022-08-05 | 2022-08-19 | 2022-10-20 | 2022-11-02 | 54
0 | EDCDPL2425 | PL5 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT - ICR | 30 | 2022-07-05 | 2022-08-19 | 2022-09-16 | 2022-10-27 | 50
0 | EDCDPL2475 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL4 - IFA | 10 | 2022-08-09 | 2022-08-22 | 2023-01-02 | 2023-01-13 | 102
0 | EDCDPL2910 | RISER SA REPOR (IGD-E AT KP-38 TO ARZANAH) - IFA | 20 | 2022-07-26 | 2022-08-22 | 2023-01-12 | 2023-02-08 | 120
0 | EDCDPL2440 | PL6 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT- ICR | 30 | 2022-07-18 | 2022-08-29 | 2022-09-26 | 2022-11-04 | 50
0 | EDCDPL2490 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL5 - IFA | 10 | 2022-08-16 | 2022-08-29 | 2023-03-01 | 2023-03-14 | 139
0 | EDCDPL2115 | CROSSING DESIGN REPORT FOR PL1,PL2&PL3 - IFA | 10 | 2022-08-17 | 2022-08-31 | 2022-11-28 | 2022-12-13 | 73
0 | EDCDPL2190 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL4 - IFA | 10 | 2022-08-17 | 2022-08-31 | 2022-11-28 | 2022-12-13 | 73
0 | EDCDPL2525 | PIPELINE PLASTIC BENDING MOMENT CAPACITY - FEA STUDY REPORT - - IFC | 10 | 2022-08-19 | 2022-09-01 | 2023-03-15 | 2023-03-28 | 146
0 | EDCDPL1655 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL1,PL2&PL3 - IFC | 10 | 2022-08-19 | 2022-09-02 | 2023-01-17 | 2023-01-30 | 105
0 | EDCDPL1810 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL1,PL2&PL3 - ICR | 15 | 2022-08-12 | 2022-09-02 | 2022-12-12 | 2022-12-30 | 84
0 | EDCDPL1970 | PIPELINE EXPANSION DESIGN REPORT FOR PL1,PL2&PL3 - IFC | 10 | 2022-08-19 | 2022-09-02 | 2023-02-21 | 2023-03-06 | 130
0 | EDCDPL2530 | CONCRETE COATING SELECTION REPORT- ICR | 20 | 2022-08-05 | 2022-09-02 | 2022-10-20 | 2022-11-16 | 54
0 | EDCDPL1680 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL5 - IFA | 10 | 2022-08-19 | 2022-09-02 | 2022-12-27 | 2023-01-09 | 90
0 | EDCDPL1775 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL1,PL2&PL3 - IFC | 10 | 2022-08-19 | 2022-09-02 | 2023-02-14 | 2023-02-27 | 125
0 | EDCDPL1785 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL5 - IFA | 10 | 2022-08-19 | 2022-09-02 | 2023-01-17 | 2023-01-30 | 105
0 | EDCDPL2135 | CROSSING DESIGN REPORT FOR PL4 - IFC | 10 | 2022-08-19 | 2022-09-02 | 2022-12-28 | 2023-01-10 | 91
0 | EDCDPL2145 | CROSSING DESIGN REPORT FOR PL5 - IFA | 10 | 2022-08-19 | 2022-09-02 | 2022-11-29 | 2022-12-14 | 72
0 | EDCDPL2505 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL6 - IFA | 10 | 2022-08-23 | 2022-09-05 | 2023-01-24 | 2023-02-06 | 108
0 | EDCDPL2175 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL1,PL2&PL3 - IFA | 10 | 2022-08-24 | 2022-09-07 | 2022-12-07 | 2022-12-20 | 73
0 | EDCDPL2025 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL1,PL2&PL3 - IFA | 10 | 2022-08-26 | 2022-09-09 | 2022-11-11 | 2022-11-24 | 55
0 | EDCDPL1730 | SHORE APPROACH DESIGN REPORT AT SOUTH ARZANA - IFC | 15 | 2022-08-19 | 2022-09-09 | 2023-01-17 | 2023-02-06 | 105
0 | EDCDPL1825 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL4 - ICR | 15 | 2022-08-19 | 2022-09-09 | 2022-12-19 | 2023-01-06 | 84
0 | EDCDPL2205 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL5 - IFA | 10 | 2022-08-26 | 2022-09-09 | 2022-12-08 | 2022-12-21 | 72
0 | EDCDPL2405 | PL2&PL3 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT - IFC | 15 | 2022-08-19 | 2022-09-09 | 2022-12-26 | 2023-01-13 | 89
0 | EDCDPL2420 | PL4 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT - IFC | 15 | 2022-08-19 | 2022-09-09 | 2023-01-23 | 2023-02-10 | 109
0 | EDCDPL1710 | SHORE APPROACH DESIGN REPORT AT EAST ARZANA - IFA | 10 | 2022-08-29 | 2022-09-12 | 2022-11-07 | 2022-11-18 | 50
0 | EDCDPL1740 | SHORE APPROACH DESIGN REPORT AT ZIRKU - IFA | 10 | 2022-08-29 | 2022-09-12 | 2022-12-27 | 2023-01-09 | 84
0 | EDCDPL1695 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL6 - IFA | 10 | 2022-08-29 | 2022-09-12 | 2023-01-10 | 2023-01-23 | 94
0 | EDCDPL1800 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL6 - IFA | 10 | 2022-08-29 | 2022-09-12 | 2023-01-24 | 2023-02-06 | 104
0 | EDCDPL2160 | CROSSING DESIGN REPORT FOR PL6 - IFA | 10 | 2022-08-29 | 2022-09-12 | 2022-12-14 | 2022-12-27 | 75
0 | EDCDPL2220 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL6 - IFA | 10 | 2022-08-29 | 2022-09-12 | 2022-12-14 | 2022-12-27 | 75
0 | EDCDPL2465 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL1,PL2&PL3 - IFC | 10 | 2022-08-30 | 2022-09-12 | 2022-11-24 | 2022-12-09 | 62
0 | EDCDPL1975 | PIPELINE EXPANSION DESIGN REPORT FOR PL4 - ICR | 15 | 2022-08-26 | 2022-09-16 | 2022-12-26 | 2023-01-13 | 84
0 | EDCDPL2430 | PL5 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT - IFA | 10 | 2022-09-02 | 2022-09-16 | 2023-01-02 | 2023-01-13 | 84
0 | EDCDPL2345 | RISER SA REPORT @ HD-3 AND @ WHP T-4 - IFC | 20 | 2022-08-23 | 2022-09-19 | 2023-02-17 | 2023-03-16 | 126
0 | EDCDPL2480 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL4 - IFC | 10 | 2022-09-06 | 2022-09-19 | 2023-01-30 | 2023-02-10 | 102
0 | EDCDPL1840 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL5 - ICR | 15 | 2022-09-02 | 2022-09-23 | 2023-01-02 | 2023-01-20 | 84
0 | EDCDPL1990 | PIPELINE EXPANSION DESIGN REPORT FOR PL5 - ICR | 15 | 2022-09-02 | 2022-09-23 | 2023-01-02 | 2023-01-20 | 84
0 | EDCDPL2035 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL4 - ICR | 15 | 2022-09-02 | 2022-09-23 | 2023-01-02 | 2023-01-20 | 84
0 | EDCDPL1855 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL6 - ICR | 15 | 2022-09-05 | 2022-09-26 | 2023-01-03 | 2023-01-23 | 84
0 | EDCDPL2005 | PIPELINE EXPANSION DESIGN REPORT FOR PL6 - ICR | 10 | 2022-09-12 | 2022-09-26 | 2023-01-10 | 2023-01-23 | 84
0 | EDCDPL2050 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL5 - ICR | 15 | 2022-09-05 | 2022-09-26 | 2023-01-03 | 2023-01-23 | 84
0 | EDCDPL2445 | PL6 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT- IFA | 10 | 2022-09-12 | 2022-09-26 | 2023-01-10 | 2023-01-23 | 84
0 | EDCDPL2360 | RISER SA REPORT (SATAH WHP-10 TO ARZANAH) - IFC | 20 | 2022-08-30 | 2022-09-26 | 2023-02-24 | 2023-03-23 | 126
0 | EDCDPL2495 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL5 - IFC | 10 | 2022-09-13 | 2022-09-26 | 2023-03-29 | 2023-04-11 | 139
0 | EDCDPL2120 | CROSSING DESIGN REPORT FOR PL1,PL2&PL3 - IFC | 10 | 2022-09-14 | 2022-09-28 | 2022-12-28 | 2023-01-10 | 73
0 | EDCDPL2195 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL4 - IFC | 10 | 2022-09-14 | 2022-09-28 | 2022-12-28 | 2023-01-10 | 73
0 | EDCDPL1815 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL1,PL2&PL3 - IFA | 10 | 2022-09-16 | 2022-09-30 | 2023-01-31 | 2023-02-13 | 95
0 | EDCDPL2535 | CONCRETE COATING SELECTION REPORT -- IFA | 10 | 2022-09-16 | 2022-09-30 | 2022-12-05 | 2022-12-16 | 54
0 | EDCDPL1670 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL4 - IFC | 10 | 2022-09-16 | 2022-09-30 | 2023-01-24 | 2023-02-06 | 90
0 | EDCDPL2150 | CROSSING DESIGN REPORT FOR PL5 - IFC | 10 | 2022-09-16 | 2022-09-30 | 2022-12-29 | 2023-01-11 | 72
0 | EDCDPL2065 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL6 - ICR | 15 | 2022-09-12 | 2022-10-03 | 2023-01-17 | 2023-02-06 | 89
0 | EDCDPL2510 | CATHODIC PROTECTION SYSTEM DESIGN REPORT FOR PL6 - IFC | 10 | 2022-09-20 | 2022-10-03 | 2023-02-21 | 2023-03-06 | 108
0 | EDCDPL2375 | RISER SA REPOR (IGD-E AT KP-38 TO ARZANAH) - IFC | 20 | 2022-09-06 | 2022-10-03 | 2023-02-23 | 2023-03-22 | 120
0 | EDCDPL2180 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL1,PL2&PL3 - IFC | 10 | 2022-09-21 | 2022-10-05 | 2023-01-04 | 2023-01-17 | 73
0 | EDCDPL2030 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL1,PL2&PL3 - IFC | 10 | 2022-09-23 | 2022-10-07 | 2022-12-13 | 2022-12-26 | 55
0 | EDCDPL1685 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL5 - IFC | 10 | 2022-09-23 | 2022-10-07 | 2023-01-31 | 2023-02-13 | 90
0 | EDCDPL1830 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL4 - IFA | 10 | 2022-09-23 | 2022-10-07 | 2023-02-07 | 2023-02-20 | 95
0 | EDCDPL2210 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL5 - IFC | 10 | 2022-09-23 | 2022-10-07 | 2023-01-05 | 2023-01-18 | 72
0 | EDCDPL2165 | CROSSING DESIGN REPORT FOR PL6 - IFC | 10 | 2022-09-26 | 2022-10-10 | 2023-01-11 | 2023-01-24 | 75
0 | EDCDPL2225 | CROSSING DESIGN REPORT - DYNAMIC ANALYSIS FOR PL6 - IFC | 10 | 2022-09-26 | 2022-10-10 | 2023-01-11 | 2023-01-24 | 75
0 | EDCDPL2390 | PL1 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT - IFC | 15 | 2022-09-22 | 2022-10-13 | 2022-12-12 | 2022-12-30 | 55
0 | EDCDPL1700 | PIPELINE PIPELINES ROUTE SELECTION REPORT FOR PL6 - IFC | 10 | 2022-09-30 | 2022-10-14 | 2023-02-07 | 2023-02-20 | 90
0 | EDCDPL1980 | PIPELINE EXPANSION DESIGN REPORT FOR PL4 - IFA | 10 | 2022-09-30 | 2022-10-14 | 2023-01-31 | 2023-02-13 | 85
0 | EDCDPL1715 | SHORE APPROACH DESIGN REPORT AT EAST ARZANA - IFC | 15 | 2022-09-26 | 2022-10-17 | 2022-12-07 | 2022-12-27 | 50
0 | EDCDPL1745 | SHORE APPROACH DESIGN REPORT AT ZIRKU - IFC | 15 | 2022-09-26 | 2022-10-17 | 2023-01-24 | 2023-02-13 | 84
0 | EDCDPL1790 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL5 - IFC | 10 | 2022-10-07 | 2022-10-21 | 2023-02-14 | 2023-02-27 | 90
0 | EDCDPL1845 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL5 - IFA | 10 | 2022-10-07 | 2022-10-21 | 2023-02-06 | 2023-02-17 | 84
0 | EDCDPL1995 | PIPELINE EXPANSION DESIGN REPORT FOR PL4,PL5&PL6 - IFA | 10 | 2022-10-07 | 2022-10-21 | 2023-02-07 | 2023-02-20 | 85
0 | EDCDPL2040 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL4 - IFA | 10 | 2022-10-07 | 2022-10-21 | 2023-02-07 | 2023-02-20 | 85
0 | EDCDPL2435 | PL5 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT - IFC | 15 | 2022-09-30 | 2022-10-21 | 2023-03-22 | 2023-04-11 | 121
0 | EDCDPL1860 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL6 - IFA | 10 | 2022-10-10 | 2022-10-24 | 2023-02-07 | 2023-02-20 | 84
0 | EDCDPL2010 | PIPELINE EXPANSION DESIGN REPORT FOR PL6 - IFA | 10 | 2022-10-10 | 2022-10-24 | 2023-02-07 | 2023-02-20 | 84
0 | EDCDPL2055 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL5 - IFA | 10 | 2022-10-10 | 2022-10-24 | 2023-02-07 | 2023-02-20 | 84
0 | EDCDPL1805 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL6 - IFC | 10 | 2022-10-14 | 2022-10-28 | 2023-02-21 | 2023-03-06 | 90
0 | EDCDPL1760 | PIPELINE ON-BOTTOM STABILITY REPORT FOR PL4 - IFC | 10 | 2022-10-17 | 2022-10-31 | 2023-02-14 | 2023-02-27 | 84
0 | EDCDPL2070 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL6 - IFA | 10 | 2022-10-17 | 2022-10-31 | 2023-02-21 | 2023-03-06 | 89
0 | EDCDPL2540 | CONCRETE COATING SELECTION REPORT - - IFC | 10 | 2022-10-18 | 2022-10-31 | 2023-01-02 | 2023-01-13 | 52
0 | EDCDPL1985 | PIPELINE EXPANSION DESIGN REPORT FOR PL4 - IFC | 10 | 2022-10-28 | 2022-11-11 | 2023-02-28 | 2023-03-13 | 85
0 | EDCDPL1820 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL1,PL2&PL3 - IFC | 10 | 2022-10-31 | 2022-11-14 | 2023-02-28 | 2023-03-13 | 84
0 | EDCDPL1850 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL5 - IFC | 10 | 2022-11-04 | 2022-11-18 | 2023-03-06 | 2023-03-17 | 84
0 | EDCDPL2000 | PIPELINE EXPANSION DESIGN REPORT FOR PL4,PL5&PL6 - IFC | 10 | 2022-11-04 | 2022-11-18 | 2023-03-07 | 2023-03-20 | 85
0 | EDCDPL1835 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL4 - IFC | 10 | 2022-11-07 | 2022-11-21 | 2023-03-07 | 2023-03-20 | 84
0 | EDCDPL1865 | PIPELINE ON BOTTOM ROUGHNESS REPORT FOR PL6 - IFC | 10 | 2022-11-07 | 2022-11-21 | 2023-03-07 | 2023-03-20 | 84
0 | EDCDPL2015 | PIPELINE EXPANSION DESIGN REPORT FOR PL6 - IFC | 10 | 2022-11-07 | 2022-11-21 | 2023-03-07 | 2023-03-20 | 84
0 | EDCDPL2045 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL4 - IFC | 10 | 2022-11-07 | 2022-11-21 | 2023-03-07 | 2023-03-20 | 84
0 | EDCDPL2060 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL5 - IFC | 10 | 2022-11-07 | 2022-11-21 | 2023-03-07 | 2023-03-20 | 84
0 | EDCDPL2075 | PIPELINE FREE SPAN ANALYSIS REPORT FOR PL6 - IFC | 10 | 2022-11-07 | 2022-11-21 | 2023-03-07 | 2023-03-20 | 84
0 | EDCDPL2450 | PL6 –PIPELINE DETAILED GLOBAL BUCKLING AND WALKING ANALYSIS DESIGN REPORT - IFC | 10 | 2022-11-07 | 2022-11-21 | 2023-03-07 | 2023-03-20 | 84
DRAWINGS |  |  | 165 | 2022-04-22 | 2022-12-20 | 2022-07-26 | 2023-06-20 | 128
0 | EDCGPL1000 | OVERALL FIELD LAYOUT - ICR | 10 | 2022-04-22 | 2022-05-11 | 2022-07-26 | 2022-08-08 | 61
0 | EDCGPL1005 | OVERALL FIELD LAYOUT - IFA | 5 | 2022-05-25 | 2022-06-01 | 2022-08-23 | 2022-08-29 | 61
0 | EDCGPL1010 | OVERALL FIELD LAYOUT - IFC | 3 | 2022-06-15 | 2022-06-20 | 2022-09-13 | 2022-09-15 | 61
0 | EDCGPL1285 | RISER AND SPOOL GENERAL ARRAGNEMENT DRAWING FOR (PL-4) 16” GAS CONDENSATE PIPELINE AT BU HASEER WHP BH-3- ICR | 10 | 2022-07-22 | 2022-08-05 | 2023-01-04 | 2023-01-17 | 116
0 | EDCGPL1225 | TYPICAL ANODE DETAIL DRAWING - ICR | 15 | 2022-07-19 | 2022-08-08 | 2022-09-29 | 2022-10-19 | 52
0 | EDCGPL1315 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-2) 12” GAS CONDENSATE PIPELINE AT HD-3- ICR | 15 | 2022-07-22 | 2022-08-12 | 2023-01-04 | 2023-01-24 | 116
0 | EDCGPL1240 | TYPICAL FIELD JOINT COATING DETAIL DRAWING - ICR | 15 | 2022-07-26 | 2022-08-15 | 2022-10-06 | 2022-10-26 | 52
0 | EDUGUC1045 | TYPICAL PIGGYBACK SIDDLES & STRAPPING ARRANGEMENT DRAWING - ICR | 15 | 2022-07-26 | 2022-08-15 | 2023-03-24 | 2023-04-14 | 172
0 | EDCGPL1030 | PIPELINE CROSSING DETAILS (PL-1) 14"GAS CONDENSATE PIPELINE- ICR | 15 | 2022-07-26 | 2022-08-15 | 2022-10-31 | 2022-11-18 | 69
0 | EDCGPL1045 | SUBSEA PIPELINE CROSSING DETAILS (PL3 - 16" GAS-CONDENSATE PIPELINE) - ICR | 15 | 2022-07-26 | 2022-08-15 | 2022-10-31 | 2022-11-18 | 69
0 | EDCGPL1060 | PIPELINE CROSSING DETAILS (PX-1) (PL-5) 24" GAS CONDENSATE PIPELINE - ICR | 15 | 2022-07-28 | 2022-08-17 | 2022-11-02 | 2022-11-22 | 69
0 | EDCGPL1345 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-2) 12” GAS CONDENSATE PIPELINE AT WHP-T4- ICR | 15 | 2022-07-29 | 2022-08-19 | 2023-01-11 | 2023-01-31 | 116
0 | EDCGPL1435 | PIPELINE ALIGNMENT DRAWING (PL-1) 14" GAS PIPELINE - ICR | 15 | 2022-07-29 | 2022-08-19 | 2022-11-17 | 2022-12-09 | 79
0 | EDUGUC1030 | CROSSING DETAILS SUBSEA UMBILICAL CROSSING DETAILS (TYPE-1 – TYPE-2 AND TYPE-3) - ICR | 15 | 2022-08-01 | 2022-08-19 | 2022-10-03 | 2022-10-21 | 45
0 | EDCGPL1075 | PIPELINE CROSSING DETAILS (PX-1 PX-2 AND CX-1) (PL-6) 6" EXPORT CONDENSATE PIPELINE - ICR | 15 | 2022-08-02 | 2022-08-22 | 2022-11-07 | 2022-11-25 | 69
0 | EDCGPL1450 | PIPELINE ALIGNMENT DRAWING (PL-2) 12" GAS - CONDENSATE PIPELINE - ICR | 15 | 2022-08-03 | 2022-08-24 | 2022-11-22 | 2022-12-14 | 79
0 | EDCGPL1360 | RISER AND SPOOL GENERAL ARRANGMENT DRAWING FOR (PL-3) 16” GAS CONDENSATE PIPELINE AT WHP-T4- ICR | 15 | 2022-08-05 | 2022-08-26 | 2023-01-18 | 2023-02-07 | 116
0 | EDCGPL1495 | PIPELINE ALIGNMENT DRAWING (PL-5) 24” EXPORT GAS PIPELINE - ICR | 10 | 2022-08-12 | 2022-08-26 | 2022-11-30 | 2022-12-15 | 78
0 | EDCGPL1135 | PIPELINE SHORE APPROACH DRAWING AT ARZANAH ISLAND (EAST APPROACH) - ICR | 15 | 2022-08-08 | 2022-08-26 | 2022-10-10 | 2022-10-28 | 45
0 | EDCGPL1270 | PIPELINE / UMBILICAL APPROACH DRAWING AT BU HASEER WHP BH-3- ICR | 15 | 2022-08-08 | 2022-08-26 | 2022-12-26 | 2023-01-13 | 98
0 | EDCGPL1465 | PIPELINE ALIGNMENT DRAWING: (PL3) 16 GAS CONDENSATE PIPELINE - ICR | 15 | 2022-08-08 | 2022-08-29 | 2022-11-25 | 2022-12-19 | 79
0 | EDCGPL1300 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA HD-3- ICR | 15 | 2022-08-10 | 2022-08-30 | 2022-12-28 | 2023-01-17 | 98
0 | EDCGPL1480 | PIPELINE ALIGNMENT DRAWING (PL-4) 16" GAS -CONDENSATE PIPELINE - ICR | 15 | 2022-08-11 | 2022-09-01 | 2022-11-30 | 2022-12-22 | 79
0 | EDCGPL1330 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA WHP-T4- ICR | 15 | 2022-08-12 | 2022-09-01 | 2023-01-09 | 2023-01-27 | 104
0 | EDCGPL1375 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-1) 14" GAS CONDENSATE PIPELINE AT SATAH WHP-10- ICR | 15 | 2022-08-12 | 2022-09-02 | 2023-01-25 | 2023-02-14 | 116
0 | EDCGPL1510 | PIPELINE ALIGNMENT DRAWING (PL-6) 6 “ EXPORT CONDENSATE PIPELINE (FOC PIGGYBACKED) - ICR | 15 | 2022-08-15 | 2022-09-05 | 2022-12-07 | 2022-12-27 | 80
0 | EDCGPL1230 | TYPICAL ANODE DETAIL DRAWING - IFA | 10 | 2022-08-23 | 2022-09-05 | 2022-11-10 | 2022-11-23 | 57
0 | EDCGPL1390 | PIPELINE / UMBILICAL APPROACH DRAWING AT IGD-E (AT KP-38)- ICR | 15 | 2022-08-16 | 2022-09-05 | 2023-01-11 | 2023-01-31 | 104
0 | EDCGPL1420 | PIPELINE / UMBILICAL APPROACH DRAWING AT SATAH WHP-10- ICR | 15 | 2022-08-18 | 2022-09-07 | 2023-01-20 | 2023-02-09 | 109
0 | EDCGPL1320 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-2) 12” GAS CONDENSATE PIPELINE AT HD-3 - IFA | 10 | 2022-08-26 | 2022-09-09 | 2023-02-08 | 2023-02-21 | 116
0 | EDCGPL1405 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-5) 24” EXPORT GAS PIPELINE AT IGD - E (AT KP-38)- ICR | 15 | 2022-08-19 | 2022-09-09 | 2023-02-01 | 2023-02-21 | 116
0 | EDCGPL1150 | PIPELINE SHORE APPROACH DRAWING AT ARZANAH ISLAND (SOUTH APPROACH) - ICR | 15 | 2022-08-22 | 2022-09-09 | 2022-10-24 | 2022-11-11 | 45
0 | EDUGUC1050 | TYPICAL PIGGYBACK SIDDLES & STRAPPING ARRANGEMENT DRAWING - IFA | 10 | 2022-08-30 | 2022-09-12 | 2023-05-02 | 2023-05-16 | 172
0 | EDCGPL1245 | TYPICAL FIELD JOINT COATING DETAIL DRAWING - IFA | 10 | 2022-08-30 | 2022-09-12 | 2022-11-10 | 2022-11-23 | 52
0 | EDCGPL1035 | PIPELINE CROSSING DETAILS (PL-1) 14"GAS CONDENSATE PIPELINE- IFA | 10 | 2022-08-30 | 2022-09-12 | 2022-12-14 | 2022-12-27 | 74
0 | EDCGPL1050 | SUBSEA PIPELINE CROSSING DETAILS (PL3 - 16" GAS-CONDENSATE PIPELINE) - IFA | 10 | 2022-08-30 | 2022-09-12 | 2023-03-08 | 2023-03-21 | 134
0 | EDCGPL1065 | PIPELINE CROSSING DETAILS (PX-1) (PL-5) 24" GAS CONDENSATE PIPELINE - IFA | 10 | 2022-09-01 | 2022-09-14 | 2022-12-14 | 2022-12-27 | 72
0 | EDCGPL1350 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-2) 12” GAS CONDENSATE PIPELINE AT WHP-T4- IFA | 10 | 2022-09-02 | 2022-09-16 | 2023-02-15 | 2023-02-28 | 116
0 | EDCGPL1440 | PIPELINE ALIGNMENT DRAWING (PL-1) 14" GAS PIPELINE - IFA | 10 | 2022-09-02 | 2022-09-16 | 2023-03-01 | 2023-03-14 | 126
0 | EDCGPL1165 | PIPELINE SHORE APPROACH DRAWING AT ZIRKU ISLAND - ICR | 15 | 2022-08-29 | 2022-09-16 | 2023-01-04 | 2023-01-24 | 90
0 | EDUGUC1035 | CROSSING DETAILS SUBSEA UMBILICAL CROSSING DETAILS (TYPE-1 – TYPE-2 AND TYPE-3) - IFA | 10 | 2022-09-05 | 2022-09-16 | 2022-12-16 | 2022-12-29 | 72
0 | EDCGPL1080 | PIPELINE CROSSING DETAILS (PX-1 PX-2 AND CX-1) (PL-6) 6" EXPORT CONDENSATE PIPELINE - IFA | 10 | 2022-09-06 | 2022-09-19 | 2022-12-14 | 2022-12-27 | 69
0 | EDCGPL1455 | PIPELINE ALIGNMENT DRAWING (PL-2) 12" GAS - CONDENSATE PIPELINE - IFA | 10 | 2022-09-07 | 2022-09-21 | 2023-03-03 | 2023-03-16 | 125
0 | EDCGPL1365 | RISER AND SPOOL GENERAL ARRANGMENT DRAWING FOR (PL-3) 16” GAS CONDENSATE PIPELINE AT WHP-T4- IFA | 10 | 2022-09-09 | 2022-09-23 | 2023-02-22 | 2023-03-07 | 116
0 | EDCGPL1500 | PIPELINE ALIGNMENT DRAWING (PL-5) 24” EXPORT GAS PIPELINE - IFA | 10 | 2022-09-09 | 2022-09-23 | 2023-03-15 | 2023-03-28 | 131
0 | EDCGPL1180 | PL-1 PIPELINE CONTROLLED BUCKLING MITIGATION SCHEME DRAWING - ICR | 15 | 2022-09-05 | 2022-09-23 | 2023-01-11 | 2023-01-31 | 90
0 | EDCGPL1140 | PIPELINE SHORE APPROACH DRAWING AT ARZANAH ISLAND (EAST APPROACH) - IFA | 10 | 2022-09-12 | 2022-09-23 | 2022-12-07 | 2022-12-20 | 60
0 | EDCGPL1275 | PIPELINE / UMBILICAL APPROACH DRAWING AT BU HASEER WHP BH-3 - IFA | 10 | 2022-09-12 | 2022-09-23 | 2023-02-16 | 2023-03-01 | 111
0 | EDCGPL1470 | PIPELINE ALIGNMENT DRAWING: (PL3) 16 GAS CONDENSATE PIPELINE - IFA | 10 | 2022-09-12 | 2022-09-26 | 2023-03-08 | 2023-03-21 | 125
0 | EDCGPL1305 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA HD-3 - IFA | 10 | 2022-09-14 | 2022-09-27 | 2023-02-17 | 2023-03-02 | 110
0 | EDCGPL1290 | RISER AND SPOOL GENERAL ARRAGNEMENT DRAWING FOR (PL-4) 16” GAS CONDENSATE PIPELINE AT BU HASEER WHP BH-3 - IFA | 10 | 2022-09-14 | 2022-09-27 | 2023-02-01 | 2023-02-14 | 98
0 | EDCGPL1485 | PIPELINE ALIGNMENT DRAWING (PL-4) 16" GAS -CONDENSATE PIPELINE - IFA | 10 | 2022-09-15 | 2022-09-29 | 2023-03-09 | 2023-03-22 | 123
0 | EDCGPL1335 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA WHP-T4 - IFA | 10 | 2022-09-16 | 2022-09-29 | 2023-03-08 | 2023-03-21 | 121
0 | EDCGPL1380 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-1) 14" GAS CONDENSATE PIPELINE AT SATAH WHP-10- IFA | 10 | 2022-09-16 | 2022-09-30 | 2023-03-01 | 2023-03-14 | 116
0 | EDCGPL1195 | PL-3 PIPELINE CONTROLLED BUCKLING MITIGATION SCHEME DRAWING - ICR | 15 | 2022-09-12 | 2022-09-30 | 2023-01-18 | 2023-02-07 | 90
0 | EDCGPL1515 | PIPELINE ALIGNMENT DRAWING (PL-6) 6 “ EXPORT CONDENSATE PIPELINE (FOC PIGGYBACKED) - IFA | 10 | 2022-09-19 | 2022-10-03 | 2023-01-11 | 2023-01-24 | 80
0 | EDCGPL1395 | PIPELINE / UMBILICAL APPROACH DRAWING AT IGD-E (AT KP-38)- IFA | 10 | 2022-09-20 | 2022-10-03 | 2023-02-23 | 2023-03-08 | 110
0 | EDCGPL1425 | PIPELINE / UMBILICAL APPROACH DRAWING AT SATAH WHP-10- IFA | 10 | 2022-09-22 | 2022-10-05 | 2023-02-24 | 2023-03-09 | 109
0 | EDCGPL1410 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-5) 24” EXPORT GAS PIPELINE AT IGD - E (AT KP-38)- IFA | 10 | 2022-09-23 | 2022-10-07 | 2023-03-08 | 2023-03-21 | 116
0 | EDCGPL1155 | PIPELINE SHORE APPROACH DRAWING AT ARZANAH ISLAND (SOUTH APPROACH) - IFA | 10 | 2022-09-26 | 2022-10-07 | 2022-11-28 | 2022-12-13 | 45
0 | EDCGPL1235 | TYPICAL ANODE DETAIL DRAWING - IFC | 15 | 2022-09-20 | 2022-10-10 | 2022-12-12 | 2022-12-30 | 57
0 | EDCGPL1040 | PIPELINE CROSSING DETAILS (PL-1) 14"GAS CONDENSATE PIPELINE - IFC | 10 | 2022-09-28 | 2022-10-12 | 2023-01-11 | 2023-01-24 | 73
0 | EDUGUC1040 | CROSSING DETAILS SUBSEA UMBILICAL CROSSING DETAILS (TYPE-1 – TYPE-2 AND TYPE-3) - IFC | 8 | 2022-10-03 | 2022-10-12 | 2023-01-13 | 2023-01-24 | 72
0 | EDCGPL1070 | PIPELINE CROSSING DETAILS (PX-1) (PL-5) 24" GAS CONDENSATE PIPELINE - IFC | 10 | 2022-09-29 | 2022-10-13 | 2023-01-11 | 2023-01-24 | 72
0 | EDCGPL1210 | PL-4 PIPELINE CONTROLLED BUCKING MITIGATION SCHEME DRAWING - ICR | 15 | 2022-09-26 | 2022-10-14 | 2023-02-01 | 2023-02-21 | 90
0 | EDCGPL1170 | PIPELINE SHORE APPROACH DRAWING AT ZIRKU ISLAND - IFA | 10 | 2022-10-03 | 2022-10-14 | 2023-03-08 | 2023-03-21 | 110
0 | EDUGUC1055 | TYPICAL PIGGYBACK SIDDLES & STRAPPING ARRANGEMENT DRAWING - IFC | 15 | 2022-09-27 | 2022-10-17 | 2023-05-30 | 2023-06-20 | 172
0 | EDCGPL1250 | TYPICAL FIELD JOINT COATING DETAIL DRAWING - IFC | 15 | 2022-09-27 | 2022-10-17 | 2022-12-12 | 2022-12-30 | 52
0 | EDCGPL1055 | SUBSEA PIPELINE CROSSING DETAILS (PL3 - 16" GAS-CONDENSATE PIPELINE) - IFC | 15 | 2022-09-27 | 2022-10-17 | 2023-04-05 | 2023-04-27 | 134
0 | EDCGPL1085 | PIPELINE CROSSING DETAILS (PX-1 PX-2 AND CX-1) (PL-6) 6" EXPORT CONDENSATE PIPELINE - IFC | 10 | 2022-10-04 | 2022-10-17 | 2023-01-11 | 2023-01-24 | 69
0 | EDCGPL1185 | PL-1 PIPELINE CONTROLLED BUCKLING MITIGATION SCHEME DRAWING - IFA | 10 | 2022-10-10 | 2022-10-21 | 2023-03-08 | 2023-03-21 | 105
0 | EDCGPL1200 | PL-3 PIPELINE CONTROLLED BUCKLING MITIGATION SCHEME DRAWING - IFA | 10 | 2022-10-17 | 2022-10-28 | 2023-03-08 | 2023-03-21 | 100
0 | EDCGPL1280 | PIPELINE / UMBILICAL APPROACH DRAWING AT BU HASEER WHP BH-3 - IFC | 15 | 2022-10-10 | 2022-10-28 | 2023-03-16 | 2023-04-05 | 111
0 | EDCGPL1310 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA HD-3 - IFC | 15 | 2022-10-12 | 2022-11-01 | 2023-03-17 | 2023-04-06 | 110
0 | EDCGPL1295 | RISER AND SPOOL GENERAL ARRAGNEMENT DRAWING FOR (PL-4) 16” GAS CONDENSATE PIPELINE AT BU HASEER WHP BH-3 - IFC | 15 | 2022-10-12 | 2022-11-01 | 2023-03-01 | 2023-03-21 | 98
0 | EDCGPL1340 | PIPELINE / UMBILICAL APPROACH DRAWING AT HAIR DALMA WHP-T4 - IFC | 15 | 2022-10-14 | 2022-11-03 | 2023-04-05 | 2023-04-27 | 121
0 | EDCGPL1145 | PIPELINE SHORE APPROACH DRAWING AT ARZANAH ISLAND (EAST APPROACH) - IFC | 15 | 2022-10-17 | 2022-11-07 | 2023-01-04 | 2023-01-24 | 55
0 | EDCGPL1400 | PIPELINE / UMBILICAL APPROACH DRAWING AT IGD-E (AT KP-38) - IFC | 15 | 2022-10-18 | 2022-11-07 | 2023-03-23 | 2023-04-12 | 110
0 | EDCGPL1325 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-2) 12” GAS CONDENSATE PIPELINE AT HD-3 - IFC | 15 | 2022-10-19 | 2022-11-08 | 2023-03-08 | 2023-03-28 | 98
0 | EDCGPL1430 | PIPELINE / UMBILICAL APPROACH DRAWING AT SATAH WHP-10 - IFC | 15 | 2022-10-20 | 2022-11-09 | 2023-03-24 | 2023-04-13 | 109
0 | EDCGPL1160 | PIPELINE SHORE APPROACH DRAWING AT ARZANAH ISLAND (SOUTH APPROACH) - IFC | 15 | 2022-10-24 | 2022-11-11 | 2022-12-28 | 2023-01-17 | 45
0 | EDCGPL1215 | PL-4 PIPELINE CONTROLLED BUCKING MITIGATION SCHEME DRAWING - IFA | 10 | 2022-10-31 | 2022-11-11 | 2023-03-08 | 2023-03-21 | 90
0 | EDCGPL1445 | PIPELINE ALIGNMENT DRAWING (PL-1) 14" GAS PIPELINE - IFC | 15 | 2022-10-25 | 2022-11-14 | 2023-03-29 | 2023-04-18 | 109
0 | EDCGPL1355 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-2) 12” GAS CONDENSATE PIPELINE AT WHP-T4 - IFC | 15 | 2022-10-26 | 2022-11-15 | 2023-03-15 | 2023-04-04 | 98
0 | EDCGPL1460 | PIPELINE ALIGNMENT DRAWING (PL-2) 12" GAS - CONDENSATE PIPELINE - IFC | 15 | 2022-10-27 | 2022-11-16 | 2023-03-31 | 2023-04-20 | 109
0 | EDCGPL1175 | PIPELINE SHORE APPROACH DRAWING AT ZIRKU ISLAND - IFC | 15 | 2022-10-31 | 2022-11-18 | 2023-04-05 | 2023-04-27 | 110
0 | EDCGPL1520 | PIPELINE ALIGNMENT DRAWING (PL-6) 6 “ EXPORT CONDENSATE PIPELINE (FOC PIGGYBACKED) - IFC | 10 | 2022-11-07 | 2022-11-21 | 2023-03-07 | 2023-03-20 | 84
0 | EDCGPL1490 | PIPELINE ALIGNMENT DRAWING (PL-4) 16" GAS -CONDENSATE PIPELINE - IFC | 14 | 2022-11-02 | 2022-11-21 | 2023-04-06 | 2023-04-27 | 109
0 | EDCGPL1505 | PIPELINE ALIGNMENT DRAWING (PL-5) 24” EXPORT GAS PIPELINE - IFC | 10 | 2022-11-08 | 2022-11-21 | 2023-04-12 | 2023-04-27 | 109
0 | EDCGPL1475 | PIPELINE ALIGNMENT DRAWING: (PL3) 16 GAS CONDENSATE PIPELINE - IFC | 15 | 2022-11-01 | 2022-11-21 | 2023-04-05 | 2023-04-27 | 109
0 | EDCGPL1370 | RISER AND SPOOL GENERAL ARRANGMENT DRAWING FOR (PL-3) 16” GAS CONDENSATE PIPELINE AT WHP-T4 - IFC | 15 | 2022-11-02 | 2022-11-22 | 2023-03-22 | 2023-04-11 | 98
0 | EDCGPL1190 | PL-1 PIPELINE CONTROLLED BUCKLING MITIGATION SCHEME DRAWING - IFC | 15 | 2022-11-07 | 2022-11-25 | 2023-04-05 | 2023-04-27 | 105
0 | EDCGPL1385 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-1) 14" GAS CONDENSATE PIPELINE AT SATAH WHP-10 - IFC | 15 | 2022-11-09 | 2022-11-29 | 2023-03-29 | 2023-04-18 | 98
0 | EDCGPL1205 | PL-3 PIPELINE CONTROLLED BUCKLING MITIGATION SCHEME DRAWING - IFC | 15 | 2022-11-14 | 2022-12-06 | 2023-04-05 | 2023-04-27 | 100
0 | EDCGPL1415 | RISER AND SPOOL GENERAL ARRANGEMENT DRAWING FOR (PL-5) 24” EXPORT GAS PIPELINE AT IGD - E (AT KP-38) - IFC | 15 | 2022-11-16 | 2022-12-08 | 2023-04-05 | 2023-04-27 | 98
0 | EDCGPL1220 | PL-4 PIPELINE CONTROLLED BUCKING MITIGATION SCHEME DRAWING - IFC | 15 | 2022-11-28 | 2022-12-20 | 2023-04-05 | 2023-04-27 | 90
REQUISITIONS |  |  | 197 | 2022-01-27 | 2022-11-08 | 2022-03-25 | 2023-03-28 | 98
LINEPIPE - SAW |  |  | 69 | 2022-01-27 | 2022-05-09 | 2022-03-25 | 2022-07-05 | 42
REQUISITION |  |  | 47 | 2022-01-27 | 2022-04-04 | 2022-03-25 | 2022-06-02 | 41
0 | EDCMPL1000 | SAW LINEPIPES - ISSUE MR - ICR | 15 | 2022-01-27 | 2022-02-17 | 2022-03-25 | 2022-04-14 | 41
0 | EDCMPL1005 | SAW LINEPIPES - ISSUE MR - IFA | 10 | 2022-03-03 | 2022-03-17 | 2022-04-29 | 2022-05-17 | 41
0 | EDCMPL1010 | SAW LINEPIPES - ISSUE MR - IFC | 5 | 2022-03-28 | 2022-04-04 | 2022-05-27 | 2022-06-02 | 41
TBE |  |  | 50 | 2022-02-23 | 2022-05-09 | 2022-04-25 | 2022-07-05 | 42
0 | EDCMPL2005 | COMPLETE EVALUATION AND SUBMIT TBE - LINE PIPES (SAW) - ICR | 7 | 2022-02-23 | 2022-03-04 | 2022-04-25 | 2022-05-06 | 43
0 | EDCMPL2010 | RECEIVE COMMENTS & ISSUE TBE - LINE PIPES (SAW) - IFA | 10 | 2022-03-18 | 2022-04-01 | 2022-05-24 | 2022-06-06 | 44
0 | EDCMPL2015 | ISSUE TBE - LINE PIPES (SAW) - IFC | 11 | 2022-04-19 | 2022-05-09 | 2022-06-21 | 2022-07-05 | 42
LINEPIPE - SEAMLESS |  |  | 64 | 2022-02-01 | 2022-05-05 | 2022-03-30 | 2022-07-14 | 48
REQUISITION |  |  | 44 | 2022-02-01 | 2022-04-04 | 2022-03-30 | 2022-06-02 | 41
0 | EDCMPL1015 | SEAMLESS LINEPIPES - ISSUE MR - ICR | 9 | 2022-02-01 | 2022-02-14 | 2022-03-30 | 2022-04-11 | 41
0 | EDCMPL1020 | SEAMLESS LINEPIPES - ISSUE MR - IFA | 11 | 2022-02-28 | 2022-03-15 | 2022-04-26 | 2022-05-13 | 41
0 | EDCMPL1025 | SEAMLESS LINEPIPES - ISSUE MR - IFC | 4 | 2022-03-29 | 2022-04-04 | 2022-05-30 | 2022-06-02 | 41
TBE |  |  | 51 | 2022-02-18 | 2022-05-05 | 2022-04-18 | 2022-07-14 | 48
0 | EDCMPL2020 | COMPLETE EVALUATION AND SUBMIT TBE- LINE PIPES (SML S) - ICR | 10 | 2022-02-18 | 2022-03-04 | 2022-04-18 | 2022-04-29 | 41
0 | EDCMPL2025 | RECEIVE COMMENTS & ISSUE TBE- LINE PIPES (SML S) - IFA | 10 | 2022-03-18 | 2022-04-01 | 2022-05-20 | 2022-06-02 | 42
0 | EDCMPL2030 | ISSUE TBE - LINE PIPES (SML S) - IFC | 11 | 2022-04-15 | 2022-05-05 | 2022-06-27 | 2022-07-14 | 48
PIPELINE INDUCTION BENDS |  |  | 69 | 2022-03-08 | 2022-06-16 | 2022-05-18 | 2022-10-26 | 92
REQUISITION |  |  | 33 | 2022-03-08 | 2022-04-22 | 2022-05-18 | 2022-09-05 | 91
0 | EDCMPL1030 | PIPELINE INDUCTION BENDS - ISSUE MR - ICR | 5 | 2022-03-08 | 2022-03-15 | 2022-05-18 | 2022-05-24 | 48
0 | EDCMPL1035 | PIPELINE INDUCTION BENDS - ISSUE MR - IFA | 5 | 2022-03-29 | 2022-04-05 | 2022-08-11 | 2022-08-17 | 91
0 | EDCMPL1040 | PIPELINE INDUCTION BENDS - ISSUE MR - IFC | 3 | 2022-04-19 | 2022-04-22 | 2022-09-01 | 2022-09-05 | 91
TBE |  |  | 51 | 2022-04-01 | 2022-06-16 | 2022-08-10 | 2022-10-26 | 92
0 | EDCMPL2035 | COMPLETE EVALUATION AND SUBMIT TBE - PIPELINE INDUCTION BENDS - ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-08-10 | 2022-08-24 | 87
0 | EDCMPL2040 | RECEIVE COMMENTS & ISSUE TBE - PIPELINE INDUCTION BENDS - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-09-09 | 2022-09-23 | 89
0 | EDCMPL2045 | ISSUE TBE - PIPELINE INDUCTION BENDS - IFC | 11 | 2022-06-01 | 2022-06-16 | 2022-10-12 | 2022-10-26 | 92
PIPELINE BARRED TEE |  |  | 86 | 2022-03-02 | 2022-07-05 | 2022-05-12 | 2022-11-02 | 84
REQUISITION |  |  | 50 | 2022-03-02 | 2022-05-16 | 2022-05-12 | 2022-09-05 | 78
0 | EDCMPL1045 | PIPELINE BARRED TEE - ISSUE MR - ICR | 10 | 2022-03-02 | 2022-03-16 | 2022-05-12 | 2022-05-25 | 48
0 | EDCMPL1050 | PIPELINE BARRED TEE - ISSUE MR - IFA | 5 | 2022-03-30 | 2022-04-06 | 2022-08-11 | 2022-08-17 | 90
0 | EDCMPL1055 | PIPELINE BARRED TEE - ISSUE MR - IFC | 3 | 2022-05-11 | 2022-05-16 | 2022-09-01 | 2022-09-05 | 78
TBE |  |  | 56 | 2022-04-13 | 2022-07-05 | 2022-08-03 | 2022-11-02 | 84
0 | EDCMPL2050 | COMPLETE EVALUATION AND SUBMIT TBE - PIPELINE BARRED TEES - ICR | 15 | 2022-04-13 | 2022-05-09 | 2022-08-03 | 2022-08-23 | 74
0 | EDCMPL2055 | RECEIVE COMMENTS & ISSUE TBE - PIPELINE BARRED TEES - IFA | 10 | 2022-05-23 | 2022-06-06 | 2022-09-09 | 2022-09-22 | 76
0 | EDCMPL2060 | ISSUE TBE - PIPELINE BARRED TEES - IFC | 11 | 2022-06-20 | 2022-07-05 | 2022-10-19 | 2022-11-02 | 84
RISER HANGER FLANGES |  |  | 87 | 2022-03-08 | 2022-07-15 | 2022-05-18 | 2022-12-12 | 105
REQUISITION |  |  | 50 | 2022-03-08 | 2022-05-20 | 2022-05-18 | 2022-09-05 | 74
0 | EDCMPL1060 | RISER HANGER FLANGES - ISSUE MR - ICR | 11 | 2022-03-08 | 2022-03-23 | 2022-05-18 | 2022-06-01 | 48
0 | EDCMPL1065 | RISER HANGER FLANGES - ISSUE MR - IFA | 5 | 2022-04-06 | 2022-04-13 | 2022-08-16 | 2022-08-22 | 88
0 | EDCMPL1070 | RISER HANGER FLANGES - ISSUE MR - IFC | 3 | 2022-05-17 | 2022-05-20 | 2022-09-01 | 2022-09-05 | 74
TBE |  |  | 56 | 2022-04-20 | 2022-07-15 | 2022-08-17 | 2022-12-12 | 105
0 | EDCMPL2065 | COMPLETE EVALUATION AND SUBMIT TBE- RISER HANGER FLANGES - ICR | 15 | 2022-04-20 | 2022-05-16 | 2022-08-17 | 2022-09-07 | 79
0 | EDCMPL2070 | RECEIVE COMMENTS & ISSUE TBE- RISER HANGER FLANGES - IFA | 10 | 2022-05-30 | 2022-06-13 | 2022-09-23 | 2022-10-07 | 81
0 | EDCMPL2075 | ISSUE TBE - RISER HANGER FLANGES - IFC | 11 | 2022-06-27 | 2022-07-15 | 2022-11-24 | 2022-12-12 | 105
PIPELINE FLANGES |  |  | 84 | 2022-03-16 | 2022-07-20 | 2022-05-26 | 2022-11-16 | 85
REQUISITION |  |  | 42 | 2022-03-16 | 2022-05-18 | 2022-05-26 | 2022-09-05 | 76
0 | EDCMPL1075 | PIPELINE FLANGES - ISSUE MR - ICR | 10 | 2022-03-16 | 2022-03-30 | 2022-05-26 | 2022-06-08 | 48
0 | EDCMPL1080 | PIPELINE FLANGES - ISSUE MR - IFA | 5 | 2022-04-18 | 2022-04-25 | 2022-08-11 | 2022-08-17 | 77
0 | EDCMPL1085 | PIPELINE FLANGES - ISSUE MR - IFC | 3 | 2022-05-13 | 2022-05-18 | 2022-09-01 | 2022-09-05 | 76
TBE |  |  | 56 | 2022-04-25 | 2022-07-20 | 2022-08-12 | 2022-11-16 | 85
0 | EDCMPL2080 | COMPLETE EVALUATION AND SUBMIT TBE - PIPELINE FLANGES - ICR | 15 | 2022-04-25 | 2022-05-19 | 2022-08-12 | 2022-09-02 | 73
0 | EDCMPL2085 | RECEIVE COMMENTS & ISSUE TBE - PIPELINE FLANGES - IFA | 10 | 2022-06-02 | 2022-06-16 | 2022-09-20 | 2022-10-04 | 75
0 | EDCMPL2090 | ISSUE TBE - PIPELINE FLANGES - IFC | 11 | 2022-06-30 | 2022-07-20 | 2022-11-01 | 2022-11-16 | 85
PIPELINE FITTINGS |  |  | 86 | 2022-03-21 | 2022-07-27 | 2022-05-31 | 2022-10-17 | 58
REQUISITION |  |  | 40 | 2022-03-21 | 2022-05-19 | 2022-05-31 | 2022-09-05 | 75
0 | EDCMPL1090 | PIPELINE FITTINGS - ISSUE MR - ICR | 10 | 2022-03-21 | 2022-04-04 | 2022-05-31 | 2022-06-13 | 48
0 | EDCMPL1095 | PIPELINE FITTINGS - ISSUE MR - IFA | 3 | 2022-04-18 | 2022-04-21 | 2022-08-15 | 2022-08-17 | 79
0 | EDCMPL1100 | PIPELINE FITTINGS - ISSUE MR - IFC | 3 | 2022-05-16 | 2022-05-19 | 2022-09-01 | 2022-09-05 | 75
TBE |  |  | 56 | 2022-05-05 | 2022-07-27 | 2022-07-29 | 2022-10-17 | 58
0 | EDCMPL2095 | COMPLETE EVALUATION AND SUBMIT TBE - PIPELINE FITTINGS - ICR | 15 | 2022-05-05 | 2022-05-26 | 2022-07-29 | 2022-08-19 | 58
0 | EDCMPL2100 | RECEIVE COMMENTS & ISSUE TBE - PIPELINE FITTINGS - IFA | 10 | 2022-06-09 | 2022-06-23 | 2022-09-02 | 2022-09-16 | 58
0 | EDCMPL2105 | ISSUE TBE - PIPELINE FITTINGS - IFC | 11 | 2022-07-07 | 2022-07-27 | 2022-09-30 | 2022-10-17 | 58
HDPE PIPES |  |  | 87 | 2022-04-04 | 2022-08-11 | 2022-06-14 | 2022-10-27 | 56
REQUISITION |  |  | 51 | 2022-04-04 | 2022-06-17 | 2022-06-14 | 2022-09-20 | 65
0 | EDCMPL1105 | HDPE PIPES - ISSUE MR - ICR | 11 | 2022-04-04 | 2022-04-19 | 2022-06-14 | 2022-06-28 | 48
0 | EDCMPL1110 | HDPE PIPES - ISSUE MR - IFA | 10 | 2022-05-06 | 2022-05-20 | 2022-08-10 | 2022-08-23 | 65
0 | EDCMPL1115 | HDPE PIPES - ISSUE MR - IFC | 10 | 2022-06-03 | 2022-06-17 | 2022-09-07 | 2022-09-20 | 65
TBE |  |  | 56 | 2022-05-20 | 2022-08-11 | 2022-08-01 | 2022-10-27 | 56
0 | EDCMPL2110 | COMPLETE EVALUATION AND SUBMIT TBE- HDPE PIPES - ICR | 15 | 2022-05-20 | 2022-06-10 | 2022-08-01 | 2022-08-19 | 48
0 | EDCMPL2115 | RECEIVE COMMENTS & ISSUE TBE- HDPE PIPES - IFA | 10 | 2022-06-24 | 2022-07-13 | 2022-09-07 | 2022-09-20 | 50
0 | EDCMPL2120 | ISSUE TBE - HDPE PIPES - IFC | 11 | 2022-07-27 | 2022-08-11 | 2022-10-13 | 2022-10-27 | 56
PIPELINE ANODES |  |  | 67 | 2022-06-15 | 2022-09-21 | 2022-08-22 | 2022-11-25 | 48
REQUISITION |  |  | 50 | 2022-06-15 | 2022-08-29 | 2022-08-22 | 2022-11-03 | 49
0 | EDCMPL1120 | PIPELINE ANODES - ISSUE MR - ICR | 10 | 2022-06-15 | 2022-06-29 | 2022-08-22 | 2022-09-02 | 45
0 | EDCMPL1125 | PIPELINE ANODES - ISSUE MR - IFA | 10 | 2022-07-18 | 2022-08-01 | 2022-09-23 | 2022-10-06 | 49
0 | EDCMPL1130 | PIPELINE ANODES - ISSUE MR - IFC | 10 | 2022-08-15 | 2022-08-29 | 2022-10-21 | 2022-11-03 | 49
TBE |  |  | 45 | 2022-07-20 | 2022-09-21 | 2022-09-21 | 2022-11-25 | 48
0 | EDCMPL2125 | COMPLETE EVALUATION AND SUBMIT TBE - PIPELINE ANODES - ICR | 10 | 2022-07-20 | 2022-08-03 | 2022-09-21 | 2022-10-04 | 45
0 | EDCMPL2130 | RECEIVE COMMENTS & ISSUE TBE- PIPELINE ANODES - IFA | 10 | 2022-08-17 | 2022-08-31 | 2022-10-21 | 2022-11-03 | 47
0 | EDCMPL2135 | ISSUE TBE - PIPELINE ANODES - IFC | 5 | 2022-09-14 | 2022-09-21 | 2022-11-21 | 2022-11-25 | 48
EXTERNAL COATING FOR INDUCTION BENDS |  |  | 86 | 2022-06-22 | 2022-10-25 | 2022-09-14 | 2023-02-03 | 71
REQUISITION |  |  | 50 | 2022-06-22 | 2022-09-05 | 2022-09-14 | 2022-12-20 | 74
0 | EDCMPL1135 | EXTERNAL COATING FOR INDUCTION BENDS - ISSUE MR - ICR | 10 | 2022-06-22 | 2022-07-06 | 2022-09-14 | 2022-09-28 | 57
0 | EDCMPL1140 | EXTERNAL COATING FOR INDUCTION BENDS - ISSUE MR - IFA | 10 | 2022-07-25 | 2022-08-08 | 2022-11-04 | 2022-11-18 | 74
0 | EDCMPL1145 | EXTERNAL COATING FOR INDUCTION BENDS - ISSUE MR - IFC | 10 | 2022-08-22 | 2022-09-05 | 2022-12-06 | 2022-12-20 | 74
TBE |  |  | 56 | 2022-08-08 | 2022-10-25 | 2022-10-26 | 2023-02-03 | 71
0 | EDCMPL2140 | COMPLETE EVALUATION AND SUBMIT TBE- EXTERNAL COATING FOR INDUCTION BENDS - ICR | 15 | 2022-08-08 | 2022-08-29 | 2022-10-26 | 2022-11-16 | 57
0 | EDCMPL2145 | RECEIVE COMMENTS & ISSUE TBE- EXTERNAL COATING FOR INDUCTION BENDS - IFA | 10 | 2022-09-12 | 2022-09-26 | 2022-12-06 | 2022-12-20 | 59
0 | EDCMPL2150 | ISSUE TBE - EXTERNAL COATING FOR INDUCTION BENDS - IFC | 11 | 2022-10-10 | 2022-10-25 | 2023-01-19 | 2023-02-03 | 71
CABLE PROTECTOR & BALLAST MODULE |  |  | 86 | 2022-06-27 | 2022-10-28 | 2022-10-26 | 2023-03-10 | 94
REQUISITION |  |  | 50 | 2022-06-27 | 2022-09-08 | 2022-10-26 | 2023-01-31 | 102
0 | EDCMPL1150 | CABLE PROTECTOR & BALLAST MODULE - ISSUE MR - ICR | 10 | 2022-06-27 | 2022-07-14 | 2022-10-26 | 2022-11-08 | 84
0 | EDCMPL1155 | CABLE PROTECTOR & BALLAST MODULE - ISSUE MR - IFA | 10 | 2022-07-28 | 2022-08-11 | 2022-12-21 | 2023-01-03 | 102
0 | EDCMPL1160 | CABLE PROTECTOR & BALLAST MODULE - ISSUE MR - IFC | 10 | 2022-08-25 | 2022-09-08 | 2023-01-18 | 2023-01-31 | 102
TBE |  |  | 56 | 2022-08-11 | 2022-10-28 | 2022-12-12 | 2023-03-10 | 94
0 | EDCMPL2155 | COMPLETE EVALUATION AND SUBMIT TBE - CABLE PROTECTION & BALAST MODULE - ICR | 15 | 2022-08-11 | 2022-09-01 | 2022-12-12 | 2022-12-30 | 85
0 | EDCMPL2160 | RECEIVE TBE COMPANY APPROVAL - CABLE PROTECTION & BALAST MODULE | 10 | 2022-09-15 | 2022-09-29 | 2023-01-18 | 2023-01-31 | 87
0 | EDCMPL2165 | ISSUE TBE - CABLE PROTECTION & BALAST MODULE - IFC | 11 | 2022-10-13 | 2022-10-28 | 2023-02-24 | 2023-03-10 | 94
PIPELINE BOLTS & NUTS |  |  | 86 | 2022-07-04 | 2022-11-04 | 2022-11-02 | 2023-03-09 | 87
REQUISITION |  |  | 50 | 2022-07-04 | 2022-09-15 | 2022-11-02 | 2023-02-06 | 101
0 | EDCMPL1165 | PIPELINE BOLTS & NUTS - ISSUE MR - ICR | 10 | 2022-07-04 | 2022-07-21 | 2022-11-02 | 2022-11-15 | 84
0 | EDCMPL1170 | PIPELINE BOLTS & NUTS - ISSUE MR - IFA | 10 | 2022-08-04 | 2022-08-18 | 2022-12-27 | 2023-01-09 | 101
0 | EDCMPL1175 | PIPELINE BOLTS & NUTS - ISSUE MR - IFC | 10 | 2022-09-01 | 2022-09-15 | 2023-01-24 | 2023-02-06 | 101
TBE |  |  | 56 | 2022-08-18 | 2022-11-04 | 2022-12-16 | 2023-03-09 | 87
0 | EDCMPL2170 | COMPLETE EVALUATION AND SUBMIT TBE - PIPELINE BOLTS &NUT - ICR | 15 | 2022-08-18 | 2022-09-08 | 2022-12-16 | 2023-01-05 | 84
0 | EDCMPL2175 | RECEIVE COMMENTS & ISSUE TBE - PIPELINE BOLTS &NUT - IFA | 10 | 2022-09-22 | 2022-10-06 | 2023-01-24 | 2023-02-06 | 86
0 | EDCMPL2180 | ISSUE TBE - PIPELINE BOLTS &NUT - IFC | 11 | 2022-10-20 | 2022-11-04 | 2023-02-22 | 2023-03-09 | 87
PIPELINE GASKETS |  |  | 85 | 2022-07-07 | 2022-11-08 | 2022-11-09 | 2023-03-28 | 98
REQUISITION |  |  | 50 | 2022-07-07 | 2022-09-20 | 2022-11-09 | 2023-02-13 | 103
0 | EDCMPL1180 | PIPELINE GASKETS - ISSUE MR - ICR | 10 | 2022-07-07 | 2022-07-26 | 2022-11-09 | 2022-11-22 | 86
0 | EDCMPL1185 | PIPELINE GASKETS - ISSUE MR - IFA | 10 | 2022-08-09 | 2022-08-23 | 2023-01-03 | 2023-01-16 | 103
0 | EDCMPL1190 | PIPELINE GASKETS - ISSUE MR - IFC | 10 | 2022-09-06 | 2022-09-20 | 2023-01-31 | 2023-02-13 | 103
TBE |  |  | 55 | 2022-08-23 | 2022-11-08 | 2022-12-23 | 2023-03-28 | 98
0 | EDCMPL2185 | COMPLETE EVALUATION AND SUBMIT TBE - PIPELINE GASKETS - ICR | 15 | 2022-08-23 | 2022-09-13 | 2022-12-23 | 2023-01-12 | 86
0 | EDCMPL2190 | RECEIVE COMMENTS & ISSUE TBE - PIPELINE GASKETS - IFA | 10 | 2022-09-27 | 2022-10-11 | 2023-01-31 | 2023-02-13 | 88
0 | EDCMPL2195 | ISSUE TBE - PIPELINE GASKETS - IFC | 10 | 2022-10-25 | 2022-11-08 | 2023-03-14 | 2023-03-28 | 98
PIGGYBACK SADDLES |  |  | 83 | 2022-05-11 | 2022-09-08 | 2022-07-18 | 2022-11-16 | 50
REQUISITION |  |  | 50 | 2022-05-11 | 2022-07-25 | 2022-07-18 | 2022-10-14 | 60
0 | EDCMPL1195 | PIGGYBACK SADDLES - ISSUE MR - ICR | 10 | 2022-05-11 | 2022-05-25 | 2022-07-18 | 2022-07-29 | 45
0 | EDCMPL1200 | PIGGYBACK SADDLES - ISSUE MR - IFA | 10 | 2022-06-08 | 2022-06-22 | 2022-09-05 | 2022-09-16 | 60
0 | EDCMPL1205 | PIGGYBACK SADDLES - ISSUE MR - IFC | 10 | 2022-07-06 | 2022-07-25 | 2022-10-03 | 2022-10-14 | 60
TBE |  |  | 55 | 2022-06-20 | 2022-09-08 | 2022-08-25 | 2022-11-16 | 50
0 | EDCMPL2200 | COMPLETE EVALUATION AND SUBMIT TBE - PIGGYBACK SADDLES - ICR | 15 | 2022-06-20 | 2022-07-14 | 2022-08-25 | 2022-09-14 | 45
0 | EDCMPL2205 | RECEIVE COMMENTS & ISSUE TBE - PIGGYBACK SADDLES - IFA | 10 | 2022-07-28 | 2022-08-11 | 2022-10-03 | 2022-10-14 | 47
0 | EDCMPL2210 | ISSUE TBE - PIGGYBACK SADDLES - IFC | 10 | 2022-08-25 | 2022-09-08 | 2022-11-03 | 2022-11-16 | 50
MISCELLANEOUS DELIVERABLES |  |  | 65 | 2022-10-03 | 2023-01-04 | 2023-01-25 | 2023-04-27 | 80
0 | EDCGPL2000 | PIPELINE MISCELLANEOUS DELIVERABLES - ICR | 15 | 2022-10-03 | 2022-10-24 | 2023-01-25 | 2023-02-14 | 80
0 | EDCGPL2005 | PIPELINE MISCELLANEOUS DELIVERABLES - IFA | 15 | 2022-11-07 | 2022-11-28 | 2023-03-01 | 2023-03-21 | 80
0 | EDCGPL2010 | PIPELINE MISCELLANEOUS DELIVERABLES - IFA | 15 | 2022-12-14 | 2023-01-04 | 2023-04-05 | 2023-04-27 | 80
UMBILICAL, COMPOSITE CABLE & FOC |  |  | 192 | 2022-04-01 | 2023-01-06 | 2022-07-07 | 2023-04-27 | 78
DOCUMENTS |  |  | 159 | 2022-04-01 | 2022-11-18 | 2022-07-07 | 2023-04-26 | 110
SPECIFICATION |  |  | 50 | 2022-04-01 | 2022-06-15 | 2022-10-11 | 2022-12-21 | 131
0 | EDCDPL2610 | SPECIFICATION FOR SUBSEA UMBILICAL - ICR | 10 | 2022-04-01 | 2022-04-15 | 2022-10-11 | 2022-10-24 | 131
0 | EDCDPL2620 | SPECIFICATION FOR SUBSEA UMBILICAL - IFA | 10 | 2022-04-29 | 2022-05-18 | 2022-11-08 | 2022-11-21 | 131
0 | EDCDPL2630 | SPECIFICATION FOR SUBSEA UMBILICAL - IFC | 10 | 2022-06-01 | 2022-06-15 | 2022-12-08 | 2022-12-21 | 131
REPORTS & CALCULATIONS |  |  | 131 | 2022-05-17 | 2022-11-18 | 2022-07-07 | 2023-04-26 | 110
0 | EDUDUC1050 | UMBILICALS ON-BOTTOM STABILITY REPORT - ICR | 20 | 2022-05-17 | 2022-06-13 | 2022-07-07 | 2022-08-08 | 37
0 | EDUDUC1230 | UMBILICALS ROUTE SELECTION REPORT - ICR | 20 | 2022-05-17 | 2022-06-13 | 2022-08-22 | 2022-09-16 | 66
0 | EDUDUC1080 | COMPOSITE CABLE ON-BOTTOM STABILITY REPORT - ICR | 20 | 2022-05-24 | 2022-06-20 | 2022-07-29 | 2022-08-25 | 45
0 | EDUDUC1245 | COMPOSITE CABLE ROUTE SELECTION REPORT- ICR | 20 | 2022-05-24 | 2022-06-20 | 2022-08-29 | 2022-09-23 | 66
0 | EDUDUC1065 | UMBILICALS ON-BOTTOM STABILITY REPORT -DYNAMIC ANALYSIS - ICR | 20 | 2022-06-14 | 2022-07-14 | 2022-08-19 | 2022-09-15 | 45
0 | EDUDUC1055 | UMBILICALS ON-BOTTOM STABILITY REPORT - IFA | 10 | 2022-06-28 | 2022-07-14 | 2022-11-08 | 2022-11-21 | 92
0 | EDUDUC1095 | COMPOSITE CABLE ON-BOTTOM STABILITY REPORT -DYNAMIC ANALYSIS - ICR | 20 | 2022-06-14 | 2022-07-14 | 2022-08-19 | 2022-09-15 | 45
0 | EDUDUC1235 | UMBILICALS ROUTE SELECTION REPORT - IFA | 10 | 2022-06-28 | 2022-07-14 | 2023-02-02 | 2023-02-15 | 152
0 | EDUDUC1085 | COMPOSITE CABLE ON-BOTTOM STABILITY REPORT - IFA | 10 | 2022-07-05 | 2022-07-21 | 2022-11-15 | 2022-11-28 | 92
0 | EDUDUC1250 | COMPOSITE CABLE ROUTE SELECTION REPORT - IFA | 10 | 2022-07-05 | 2022-07-21 | 2023-02-16 | 2023-03-01 | 157
0 | EDUDUC1140 | UMBILICALS FREE SPAN ANALYSIS REPORT - ICR | 15 | 2022-07-05 | 2022-07-28 | 2022-09-09 | 2022-09-29 | 45
0 | EDUDUC1170 | UMBILICALS CROSSING DESIGN REPORT - ICR | 20 | 2022-07-05 | 2022-08-04 | 2022-09-09 | 2022-10-06 | 45
0 | EDUDUC1185 | COMPOSITE CABLE CROSSING DESIGN REPORT - ICR | 20 | 2022-07-13 | 2022-08-09 | 2022-09-14 | 2022-10-11 | 45
0 | EDUDUC1070 | UMBILICALS ON-BOTTOM STABILITY REPORT -DYNAMIC ANALYSIS - IFA | 10 | 2022-07-29 | 2022-08-11 | 2022-11-08 | 2022-11-21 | 72
0 | EDUDUC1060 | UMBILICALS ON-BOTTOM STABILITY REPORT - IFC | 10 | 2022-07-29 | 2022-08-11 | 2022-12-08 | 2022-12-21 | 92
0 | EDUDUC1100 | COMPOSITE CABLE ON-BOTTOM STABILITY REPORT -DYNAMIC ANALYSIS - IFA | 10 | 2022-07-29 | 2022-08-11 | 2022-11-15 | 2022-11-28 | 77
0 | EDUDUC1125 | COMPOSITE CABLE ON BOTTOM ROUGHNES ANALYSIS REPORT - ICR | 20 | 2022-07-15 | 2022-08-11 | 2022-10-18 | 2022-11-14 | 67
0 | EDUDUC1240 | UMBILICALS ROUTE SELECTION REPORT - IFC | 10 | 2022-07-29 | 2022-08-11 | 2023-03-02 | 2023-03-15 | 152
0 | EDUDUC1200 | UMBILICALS CROSSING DESIGN REPORT - DYNAMIC ANALYSIS- ICR | 20 | 2022-07-18 | 2022-08-12 | 2022-09-19 | 2022-10-14 | 45
0 | EDUDUC1215 | COMPOSITE CABLE CROSSING DESIGN REPORT - DYNAMIC ANALYSIS- ICR | 20 | 2022-07-20 | 2022-08-16 | 2022-10-26 | 2022-11-22 | 70
0 | EDUDUC1090 | COMPOSITE CABLE ON-BOTTOM STABILITY REPORT - IFC | 10 | 2022-08-05 | 2022-08-18 | 2022-12-15 | 2022-12-28 | 92
0 | EDUDUC1155 | COMPOSITE CABLE FREE SPAN ANALYSIS REPORT - ICR | 15 | 2022-07-29 | 2022-08-18 | 2022-11-01 | 2022-11-21 | 67
0 | EDUDUC1255 | COMPOSITE CABLE ROUTE SELECTION REPORT - IFC | 10 | 2022-08-05 | 2022-08-18 | 2023-03-16 | 2023-03-29 | 157
0 | EDUDUC1145 | UMBILICALS FREE SPAN ANALYSIS REPORT - IFA | 10 | 2022-08-12 | 2022-08-25 | 2022-11-29 | 2022-12-14 | 77
0 | EDUDUC1175 | UMBILICALS CROSSING DESIGN REPORT - IFA | 10 | 2022-08-19 | 2022-09-01 | 2022-11-29 | 2022-12-14 | 72
0 | EDUDUC1190 | COMPOSITE CABLE CROSSING DESIGN REPORT - IFA | 10 | 2022-08-24 | 2022-09-06 | 2023-02-22 | 2023-03-07 | 128
0 | EDUDUC1075 | UMBILICALS ON-BOTTOM STABILITY REPORT -DYNAMIC ANALYSIS - IFC | 10 | 2022-08-26 | 2022-09-08 | 2022-12-08 | 2022-12-21 | 72
0 | EDUDUC1130 | COMPOSITE CABLE ON BOTTOM ROUGHNES ANALYSIS REPORT - IFA | 10 | 2022-08-26 | 2022-09-08 | 2022-11-29 | 2022-12-14 | 67
0 | EDUDUC1205 | UMBILICALS CROSSING DESIGN REPORT - DYNAMIC ANALYSIS - IFA | 10 | 2022-08-29 | 2022-09-09 | 2022-12-07 | 2022-12-20 | 70
0 | EDUDUC1220 | COMPOSITE CABLE CROSSING DESIGN REPORT - DYNAMIC ANALYSIS - IFA | 10 | 2022-08-31 | 2022-09-13 | 2022-12-09 | 2022-12-22 | 70
0 | EDUDUC1105 | COMPOSITE CABLE ON-BOTTOM STABILITY REPORT -DYNAMIC ANALYSIS - IFC | 10 | 2022-09-02 | 2022-09-15 | 2022-12-15 | 2022-12-28 | 72
0 | EDUDUC1160 | COMPOSITE CABLE FREE SPAN ANALYSIS REPORT - IFA | 10 | 2022-09-02 | 2022-09-15 | 2022-12-08 | 2022-12-21 | 67
0 | EDUDUC1150 | UMBILICALS FREE SPAN ANALYSIS REPORT - IFC | 10 | 2022-09-09 | 2022-09-22 | 2022-12-29 | 2023-01-11 | 77
0 | EDCDPL2820 | UMBILICALS ON BOTTOM ROUGHNES ANALYSIS REPORT - ICR | 10 | 2022-09-09 | 2022-09-23 | 2023-02-14 | 2023-02-27 | 110
0 | EDUDUC1180 | UMBILICALS CROSSING DESIGN REPORT - IFC | 10 | 2022-09-16 | 2022-09-29 | 2022-12-29 | 2023-01-11 | 72
0 | EDUDUC1195 | COMPOSITE CABLE CROSSING DESIGN REPORT - IFC | 10 | 2022-09-21 | 2022-10-04 | 2023-03-22 | 2023-04-04 | 128
0 | EDUDUC1135 | COMPOSITE CABLE ON BOTTOM ROUGHNES ANALYSIS REPORT - IFC | 10 | 2022-09-23 | 2022-10-06 | 2022-12-29 | 2023-01-11 | 67
0 | EDUDUC1210 | UMBILICALS CROSSING DESIGN REPORT - DYNAMIC ANALYSIS - IFC | 10 | 2022-09-26 | 2022-10-07 | 2023-01-04 | 2023-01-17 | 70
0 | EDUDUC1225 | COMPOSITE CABLE CROSSING DESIGN REPORT - DYNAMIC ANALYSIS - IFC | 10 | 2022-09-28 | 2022-10-11 | 2023-01-06 | 2023-01-19 | 70
0 | EDUDUC1165 | COMPOSITE CABLE FREE SPAN ANALYSIS REPORT - IFC | 10 | 2022-09-30 | 2022-10-13 | 2023-01-05 | 2023-01-18 | 67
0 | EDCDPL2830 | UMBILICALS ON BOTTOM ROUGHNES ANALYSIS REPORT - IFA | 10 | 2022-10-07 | 2022-10-21 | 2023-03-14 | 2023-03-27 | 110
0 | EDCDPL2840 | UMBILICALS ON BOTTOM ROUGHNES ANALYSIS REPORT - IFC | 10 | 2022-11-04 | 2022-11-18 | 2023-04-11 | 2023-04-26 | 110
DRAWINGS |  |  | 88 | 2022-07-21 | 2022-11-21 | 2022-09-26 | 2023-04-27 | 110
0 | EDCGPL1015 | CABLE CROSSING DETAILS (CX-1 AND CX-2) (PL-2) 14" GAS CONDENSATE PIPELINE FROM HD-3 TO HD WHP-T4 - ICR | 15 | 2022-07-21 | 2022-08-10 | 2022-09-26 | 2022-10-14 | 47
0 | EDUGUC1000 | CROSSING DETAILS FOR SUBSEA UMBILICAL CROSSING DETAILS (TYPE-4 AND TYPE-5) - ICR | 15 | 2022-07-22 | 2022-08-11 | 2022-09-26 | 2022-10-14 | 46
0 | EDUGUC1015 | CROSSING DETAILS FOR COMPOSITE CABLE CROSSING DETAILS (TYPE-4 AND TYPE-5) - ICR | 15 | 2022-08-01 | 2022-08-19 | 2022-11-07 | 2022-11-25 | 70
0 | EDCGPL1530 | CABLE CROSSING DETAILS (CX-1 AND CX-2) (PL-1) 14" GAS PIPELINE FROM WHP-10 TO ARZANAH ISLAND- ICR | 15 | 2022-08-02 | 2022-08-22 | 2023-02-01 | 2023-02-21 | 129
0 | EDUGUC1120 | COMPOSITE CABLE ALIGNMENT DRAWING (CC1 - COMPOSITE CABLE FROM ARZANAH TO IGD-E) - ICR | 10 | 2022-08-12 | 2022-08-26 | 2022-11-30 | 2022-12-15 | 78
0 | EDUGUC1060 | UMBILICAL ALIGNMENT DRAWING (UC1 - UMBILICAL FROM ARZANAH TO SATAH WHP-10) - ICR | 10 | 2022-08-19 | 2022-09-02 | 2023-01-25 | 2023-02-07 | 111
0 | EDCGPL1020 | CABLE CROSSING DETAILS (CX-1 AND CX-2) (PL-2) 14" GAS CONDENSATE PIPELINE FROM HD-3 TO HD WHP-T4 - IFA | 10 | 2022-08-25 | 2022-09-07 | 2023-03-02 | 2023-03-15 | 133
0 | EDUGUC1005 | CROSSING DETAILS FOR SUBSEA UMBILICAL CROSSING DETAILS (TYPE-4 AND TYPE-5)- IFA | 10 | 2022-08-26 | 2022-09-08 | 2022-12-08 | 2022-12-21 | 72
0 | EDUGUC1075 | UMBILICAL ALIGNMENT DRAWINGS (UC-2) UMBILICAL FROM HD WHP-T4 TO HD-3 - ICR | 15 | 2022-08-19 | 2022-09-09 | 2023-01-25 | 2023-02-14 | 111
0 | EDUGUC1090 | UMBILICAL ALIGNMENT DRAWING (UC-3 - UMBILICAL FROM ARZANAH TO HD WHP T4) - ICR | 15 | 2022-08-26 | 2022-09-16 | 2023-02-01 | 2023-02-21 | 111
0 | EDUGUC1020 | CROSSING DETAILS FOR COMPOSITE CABLE CROSSING DETAILS (TYPE-4 AND TYPE-5)- IFA | 10 | 2022-09-05 | 2022-09-16 | 2022-12-14 | 2022-12-27 | 70
0 | EDCGPL1540 | CABLE CROSSING DETAILS (CX-1 AND CX-2) (PL-1) 14" GAS PIPELINE FROM WHP-10 TO ARZANAH ISLAND- IFA | 10 | 2022-09-06 | 2022-09-19 | 2023-03-08 | 2023-03-21 | 129
0 | EDUGUC1125 | COMPOSITE CABLE ALIGNMENT DRAWING (CC1 - COMPOSITE CABLE FROM ARZANAH TO IGD-E) - IFA | 10 | 2022-09-09 | 2022-09-23 | 2022-12-30 | 2023-01-12 | 78
0 | EDUGUC1105 | UMBILICAL ALIGNMENT DRAWING (UC-4 - UMBILICAL FROM ARZANAH TO WHP BH3) - ICR | 15 | 2022-09-02 | 2022-09-23 | 2023-02-08 | 2023-02-28 | 111
0 | EDUGUC1065 | UMBILICAL ALIGNMENT DRAWING (UC1 - UMBILICAL FROM ARZANAH TO SATAH WHP-10) - IFA | 10 | 2022-09-16 | 2022-09-30 | 2023-03-08 | 2023-03-21 | 121
0 | EDUGUC1080 | UMBILICAL ALIGNMENT DRAWINGS (UC-2) UMBILICAL FROM HD WHP-T4 TO HD-3 - IFA | 10 | 2022-09-23 | 2022-10-07 | 2023-03-08 | 2023-03-21 | 116
0 | EDUGUC1010 | CROSSING DETAILS FOR SUBSEA UMBILICAL CROSSING DETAILS (TYPE-4 AND TYPE-5) - IFC | 14 | 2022-09-23 | 2022-10-12 | 2023-01-05 | 2023-01-24 | 72
0 | EDCGPL1025 | CABLE CROSSING DETAILS (CX-1 AND CX-2) (PL-2) 14" GAS CONDENSATE PIPELINE FROM HD-3 TO HD WHP-T4 - IFC | 15 | 2022-09-23 | 2022-10-13 | 2023-03-30 | 2023-04-19 | 132
0 | EDUGUC1095 | UMBILICAL ALIGNMENT DRAWING (UC-3 - UMBILICAL FROM ARZANAH TO HD WHP T4) - IFA | 10 | 2022-09-30 | 2022-10-14 | 2023-03-08 | 2023-03-21 | 111
0 | EDUGUC1130 | COMPOSITE CABLE ALIGNMENT DRAWING (CC1 - COMPOSITE CABLE FROM ARZANAH TO IGD-E) - IFC | 4 | 2022-10-14 | 2022-10-19 | 2023-04-20 | 2023-04-27 | 132
0 | EDUGUC1025 | CROSSING DETAILS FOR COMPOSITE CABLE CROSSING DETAILS (TYPE-4 AND TYPE-5) - IFC | 10 | 2022-10-06 | 2022-10-19 | 2023-01-11 | 2023-01-24 | 67
0 | EDUGUC1110 | UMBILICAL ALIGNMENT DRAWING (UC-4 - UMBILICAL FROM ARZANAH TO WHP BH3) - IFA | 10 | 2022-10-07 | 2022-10-21 | 2023-03-15 | 2023-03-28 | 111
0 | EDCGPL1550 | CABLE CROSSING DETAILS (CX-1 AND CX-2) (PL-1) 14" GAS PIPELINE FROM WHP-10 TO ARZANAH ISLAND- IFC | 15 | 2022-10-05 | 2022-10-25 | 2023-04-05 | 2023-04-27 | 128
0 | EDUGUC1085 | UMBILICAL ALIGNMENT DRAWINGS (UC-2) UMBILICAL FROM HD WHP-T4 TO HD-3 - IFC | 15 | 2022-10-21 | 2022-11-11 | 2023-04-05 | 2023-04-27 | 116
0 | EDUGUC1100 | UMBILICAL ALIGNMENT DRAWING (UC-3 - UMBILICAL FROM ARZANAH TO HD WHP T4) - IFC | 15 | 2022-10-28 | 2022-11-18 | 2023-04-05 | 2023-04-27 | 111
0 | EDUGUC1115 | UMBILICAL ALIGNMENT DRAWING (UC-4 - UMBILICAL FROM ARZANAH TO WHP BH3) - IFC | 10 | 2022-11-04 | 2022-11-18 | 2023-04-12 | 2023-04-27 | 111
0 | EDUGUC1070 | UMBILICAL ALIGNMENT DRAWING (UC1 - UMBILICAL FROM ARZANAH TO SATAH WHP-10) - IFC | 15 | 2022-10-31 | 2022-11-21 | 2023-04-05 | 2023-04-27 | 110
MISCELLANEOUS DELIVERABLES |  |  | 73 | 2022-09-23 | 2023-01-06 | 2023-01-13 | 2023-04-27 | 78
0 | EDUGUC2000 | CABLE MISCELLANEOUS DELIVERABLES - ICR | 15 | 2022-09-23 | 2022-10-14 | 2023-01-13 | 2023-02-02 | 78
0 | EDUGUC2005 | CABLE MISCELLANEOUS DELIVERABLES - IFA | 18 | 2022-10-28 | 2022-11-23 | 2023-02-17 | 2023-03-14 | 78
0 | EDUGUC2010 | CABLE MISCELLANEOUS DELIVERABLES - IFC | 20 | 2022-12-09 | 2023-01-06 | 2023-03-29 | 2023-04-27 | 78
CONSTRUCTION ENGINEERING |  |  | 280 | 2022-09-01 | 2023-10-11 | 2022-11-21 | 2024-03-04 | 101
BU HASEER WHP BH-03 TOPSIDES |  |  | 241 | 2022-09-01 | 2023-08-15 | 2022-11-28 | 2023-11-03 | 57
STRUCTURAL |  |  | 152 | 2022-09-01 | 2023-04-05 | 2022-11-28 | 2023-07-21 | 72
0 | ECBGSR1000 | BH-03 SHOP DWGS - DECK FRAMING PLANS (MAIN DECK) | 9 | 2022-09-01 | 2022-09-14 | 2022-11-28 | 2022-12-12 | 62
0 | ECBGSR1020 | BH-03 SHOP DWGS - DECK FRAMING PLANS (CELLAR DECK) | 12 | 2022-09-08 | 2022-09-26 | 2022-12-09 | 2022-12-26 | 64
0 | ECBGSR1005 | BH-03 SHOP DWGS - DECK NODE DETAILS (MAIN DECK) | 15 | 2022-09-08 | 2022-09-29 | 2022-12-06 | 2022-12-26 | 61
0 | ECBGSR1075 | BH-03 SHOP DWGS - DECK FRAMING PLANS (ACCESSPLATFORM) | 15 | 2022-09-08 | 2022-09-29 | 2023-01-17 | 2023-02-06 | 91
0 | ECBGSR1060 | BH-03 SHOP DWGS - DECK TRUSS ROWS / ELEVATIONS | 15 | 2022-09-08 | 2022-09-29 | 2022-12-27 | 2023-01-16 | 76
0 | ECBGSR1025 | BH-03 SHOP DWGS - DECK NODE DETAILS (CELLAR DECK) | 15 | 2022-09-12 | 2022-10-03 | 2022-12-20 | 2023-01-09 | 69
0 | ECBGSR1040 | BH-03 SHOP DWGS - DECK FRAMING PLANS (MEZZANINE DECK) | 12 | 2022-09-15 | 2022-10-03 | 2022-12-20 | 2023-01-04 | 66
0 | ECBGSR1010 | BH-03 SHOP DWGS - DECK SECONDARY STEEL (MAIN DECK) | 15 | 2022-09-15 | 2022-10-06 | 2022-12-20 | 2023-01-09 | 66
0 | ECBGSR1045 | BH-03 SHOP DWGS - DECK NODE DETAILS (MEZZANINE DECK) | 15 | 2022-09-19 | 2022-10-10 | 2022-12-27 | 2023-01-16 | 69
0 | ECBGSR1030 | BH-03 SHOP DWGS - DECK SECONDARY STEEL (CELLAR DECK) | 15 | 2022-09-19 | 2022-10-10 | 2022-12-27 | 2023-01-16 | 69
0 | ECBGSR1090 | BH-03 SHOP DWGS - DECK FRAMING PLANS (WEATHER DECK) | 12 | 2022-09-22 | 2022-10-10 | 2022-12-27 | 2023-01-11 | 66
0 | ECBGSR1095 | BH-03 SHOP DWGS - DECK NODE DETAILS (WEATHER DECK) | 15 | 2022-09-26 | 2022-10-17 | 2023-01-04 | 2023-01-24 | 70
0 | ECBGSR1050 | BH-03 SHOP DWGS - DECK SECONDARY STEEL (MEZZANINE DECK) | 12 | 2022-10-04 | 2022-10-20 | 2023-01-06 | 2023-01-23 | 66
0 | ECBGSR1080 | BH-03 SHOP DWGS - DECK SECONDARY STEEL (ACCESSPLATFORM) | 15 | 2022-09-29 | 2022-10-20 | 2023-01-17 | 2023-02-06 | 76
0 | ECBGSR1035 | BH-03 SHOP DWGS - DECK PLATING DETAILS (CELLAR DECK) | 15 | 2022-10-10 | 2022-10-31 | 2023-03-10 | 2023-03-30 | 107
0 | ECBGSR1015 | BH-03 SHOP DWGS - DECK PLATING DETAILS (MAIN DECK) | 15 | 2022-10-17 | 2022-11-07 | 2023-01-25 | 2023-02-14 | 70
0 | ECBGSR1100 | BH-03 SHOP DWGS - DECK SECONDARY STEEL (WEATHER DECK) | 12 | 2022-10-28 | 2022-11-15 | 2023-02-07 | 2023-02-22 | 70
0 | ECBGSR1110 | BH-03 SHOP DWGS - DECK FRAMING PLANS (HELIDECK) | 12 | 2022-10-31 | 2022-11-16 | 2023-01-31 | 2023-02-15 | 64
0 | ECBGSR1140 | BH-03 SHOP DWGS - DECK PENETRATION AND DETAILS | 10 | 2022-11-02 | 2022-11-16 | 2023-02-15 | 2023-02-28 | 73
0 | ECBGSR1135 | BH-03 SHOP DWGS - DECK STABING GUIDES | 20 | 2022-10-20 | 2022-11-17 | 2023-04-11 | 2023-05-10 | 121
0 | ECBGSR1115 | BH-03 SHOP DWGS - DECK NODE DETAILS (HELIDECK) | 15 | 2022-11-09 | 2022-11-30 | 2023-02-16 | 2023-03-08 | 69
0 | ECBGSR1145 | BH-03 SHOP DWGS - DECK GRATINGS & HANDRAILS LAYOUT | 20 | 2022-11-07 | 2022-12-07 | 2023-02-14 | 2023-03-13 | 69
0 | ECBGSR1055 | BH-03 SHOP DWGS - DECK PLATING DETAILS (MEZZANINE DECK) | 15 | 2022-11-15 | 2022-12-08 | 2023-03-10 | 2023-03-30 | 81
0 | ECBGSR1120 | BH-03 SHOP DWGS - DECK SECONDARY STEEL (HELIDECK) | 12 | 2022-11-21 | 2022-12-09 | 2023-03-02 | 2023-03-17 | 71
0 | ECBGSR1105 | BH-03 SHOP DWGS - DECK PLATING DETAILS (WEATHER DECK) | 20 | 2022-11-15 | 2022-12-15 | 2023-04-17 | 2023-05-16 | 107
0 | ECBGSR1085 | BH-03 SHOP DWGS - DECK PLATING DETAILS (ACCESSPLATFORM) | 15 | 2022-12-08 | 2022-12-29 | 2023-03-31 | 2023-04-20 | 81
0 | ECBGSR1125 | BH-03 SHOP DWGS - DECK PLATING DETAILS (HELIDECK) | 15 | 2022-12-09 | 2022-12-30 | 2023-04-04 | 2023-04-26 | 82
0 | ECBGSR1070 | BH-03 SHOP DWGS- DECK PAD EYES | 10 | 2022-12-21 | 2023-01-04 | 2023-03-29 | 2023-04-11 | 70
0 | ECBGSR1065 | BH-03 SHOP DWGS - EQUIPMENT SUPPORT & PLAN DETAILS | 30 | 2022-11-28 | 2023-01-11 | 2023-03-02 | 2023-04-12 | 66
0 | ECBGSR1150 | BH-03 SHOP DWGS - DECK MONORAILS GA & DETAILS | 15 | 2022-12-23 | 2023-01-13 | 2023-05-02 | 2023-05-22 | 90
0 | ECBGSR1165 | BH-03 SHOP DWGS - CONDUCTOR GUIDE / HATCH | 10 | 2023-01-13 | 2023-01-27 | 2023-04-27 | 2023-05-10 | 72
0 | ECBGSR1130 | BH-03 SHOP DWGS - HELI DECK MISC DETAILS | 15 | 2023-01-13 | 2023-02-03 | 2023-05-11 | 2023-05-31 | 82
0 | ECBGSR1190 | BH-03 SHOP DWGS - DECK STAIR TOWER | 15 | 2023-01-13 | 2023-02-03 | 2023-05-09 | 2023-05-29 | 80
0 | ECBGSR1195 | BH-03 SHOP DRAWINGS - ACCESS PLATFORMS/ LADDERS | 15 | 2023-01-19 | 2023-02-09 | 2023-06-06 | 2023-06-26 | 96
0 | ECBGSR1175 | BH-03 SHOP DRAWINGS - STRUCTURAL MISCELLANEOUS DETAIL | 15 | 2023-02-01 | 2023-02-22 | 2023-05-01 | 2023-05-19 | 61
0 | ECBGSR1180 | BH-03 BH-03 SHOP DRAWINGS - OFFSHORE INSTALL FRAME & GRATING | 15 | 2023-02-03 | 2023-02-24 | 2023-06-12 | 2023-07-05 | 89
0 | ECBGSR1155 | BH-03 SHOP DWGS - VENT BOOM | 20 | 2023-02-03 | 2023-03-03 | 2023-05-30 | 2023-06-26 | 80
0 | ECBGSR1185 | BH-03 SHOP DRAWINGS - SWING ROPES | 15 | 2023-02-22 | 2023-03-15 | 2023-05-22 | 2023-06-09 | 61
0 | ECBGSR1170 | BH-03 SHOP DWGS - DECK IDENTIFICATION PANELS DETAILS | 15 | 2023-03-03 | 2023-03-24 | 2023-06-30 | 2023-07-21 | 80
0 | ECBGSR1200 | BH-03 SHOP DRAWINGS - SEAFASTENING DETAILS | 20 | 2023-03-08 | 2023-04-05 | 2023-06-05 | 2023-07-05 | 61
PIPING |  |  | 120 | 2022-11-17 | 2023-05-10 | 2023-02-24 | 2023-08-18 | 69
0 | ECBGPI1000 | BH-03 SHOP DWGS - PIPING SUPPORTS - CELLAR DECK | 20 | 2022-11-17 | 2022-12-19 | 2023-02-24 | 2023-03-23 | 69
0 | ECBGPI1005 | BH-03 SHOP DWGS - PIPING SUPPORTS - MAIN DECK | 20 | 2022-11-17 | 2022-12-19 | 2023-02-24 | 2023-03-23 | 69
0 | ECBGPI1010 | BH-03 SHOP DWGS - PIPING SUPPORTS - MEZZANINE DECK | 20 | 2022-11-24 | 2022-12-26 | 2023-03-03 | 2023-03-30 | 69
0 | ECBGPI1015 | BH-03 SHOP DWGS - PIPING SUPPORTS - WEATHER DECK | 20 | 2022-12-05 | 2023-01-02 | 2023-03-10 | 2023-04-06 | 69
0 | ECBGPI1020 | BH-03 SHOP DWGS - PIPING ISOMETRICS - (CS/LTCS/ CLADDED) | 15 | 2023-01-16 | 2023-02-06 | 2023-04-05 | 2023-04-27 | 57
0 | ECBGPI1025 | BH-03 SHOP DWGS - PIPING ISOMETRICS - (CU-NI) | 15 | 2023-01-30 | 2023-02-20 | 2023-04-25 | 2023-05-15 | 59
0 | ECBGPI1030 | BH-03 SHOP DWGS - PIPING ISOMETRICS - (INCONEL) | 15 | 2023-02-13 | 2023-03-06 | 2023-05-09 | 2023-05-29 | 59
0 | ECBGPI1035 | BH-03 SHOP DWGS - PIPING ISOMETRICS (SS/DUPLEX) | 15 | 2023-02-27 | 2023-03-20 | 2023-05-23 | 2023-06-12 | 59
0 | ECBGPI1040 | BH-03 PIPING HYDROTEST PACKS | 25 | 2023-04-03 | 2023-05-10 | 2023-07-14 | 2023-08-18 | 69
ELECTRICAL |  |  | 45 | 2022-11-14 | 2023-01-18 | 2023-03-10 | 2023-05-15 | 82
0 | ECBGEL1000 | BH-03 ELECTRICAL SHOP DWGS (CABLE TRAY SUPPORTS) | 35 | 2022-11-14 | 2023-01-04 | 2023-03-10 | 2023-05-01 | 82
0 | ECBGEL1010 | BH-03 ELECTRICAL - SHOP DWGS (OTHER SUPPORTS) | 35 | 2022-11-28 | 2023-01-18 | 2023-03-24 | 2023-05-15 | 82
INSTRUMENTATION / TELECOM |  |  | 80 | 2022-10-04 | 2023-01-26 | 2023-01-20 | 2023-05-15 | 76
0 | ECBGIN1000 | BH-03 INSTRUMENTATION SHOP DWGS (CABLE TRAY SUPPORTS) | 40 | 2022-10-04 | 2022-11-29 | 2023-01-20 | 2023-03-16 | 76
0 | ECBGIN1010 | BH-03 INSTRUMENTATION - SHOP DWGS (OTHER SUPPORTS) | 40 | 2022-11-29 | 2023-01-26 | 2023-03-17 | 2023-05-15 | 76
MECHANICAL |  |  | 30 | 2022-10-04 | 2022-11-15 | 2023-01-02 | 2023-02-10 | 62
0 | ECBGME1000 | BH-03 SHOP DRAWINGS - VENT DRAIN DRUM | 30 | 2022-10-04 | 2022-11-15 | 2023-01-02 | 2023-02-10 | 62
NAVAL ARCHITECTURE / INSTALLATION |  |  | 31 | 2023-07-03 | 2023-08-15 | 2023-09-21 | 2023-11-03 | 57
DOCUMENTS |  |  | 24 | 2023-07-10 | 2023-08-11 | 2023-10-05 | 2023-11-03 | 59
0 | ECBDNA1010 | BH-3 TOPSIDE -LOADOUT MOORING FORCE CALCULATION - ICR/IFA | 7 | 2023-07-10 | 2023-07-18 | 2023-10-05 | 2023-10-13 | 61
0 | ECBDNA1000 | BH-3 TOPSIDE -BARGE BALLASTING CALCULATIONS DURING LOADOUT - ICR/IFA | 7 | 2023-07-12 | 2023-07-21 | 2023-10-05 | 2023-10-13 | 59
0 | ECBDNA1030 | BH-3 TOPSIDE -BOLLARD PULL CALCULATION - ICR/IFA | 7 | 2023-07-12 | 2023-07-21 | 2023-10-05 | 2023-10-13 | 59
0 | ECBDNA1020 | BH-3 TOPSIDE -STABILITY ANALYSIS DURING TRANSPORTATION - ICR/IFA | 7 | 2023-07-12 | 2023-07-21 | 2023-10-05 | 2023-10-13 | 59
0 | ECBDNA1015 | BH-3 TOPSIDE -LOADOUT MOORING FORCE CALCULATION - IFC | 5 | 2023-08-03 | 2023-08-09 | 2023-10-30 | 2023-11-03 | 61
0 | ECBDNA1005 | BH-3 TOPSIDE -BARGE BALLASTING CALCULATIONS DURING LOADOUT - IFC | 5 | 2023-08-07 | 2023-08-11 | 2023-10-30 | 2023-11-03 | 59
0 | ECBDNA1035 | BH-3 TOPSIDE -BOLLARD PULL CALCULATION - IFC | 5 | 2023-08-07 | 2023-08-11 | 2023-10-30 | 2023-11-03 | 59
0 | ECBDNA1025 | BH-3 TOPSIDE -STABILITY ANALYSIS DURING TRANSPORTATION - IFC | 5 | 2023-08-07 | 2023-08-11 | 2023-10-30 | 2023-11-03 | 59
DRAWINGS |  |  | 31 | 2023-07-03 | 2023-08-15 | 2023-09-21 | 2023-11-03 | 57
0 | ECBGNA1000 | BH-3 TOPSIDE -LOADOUT ARRANGEMENT - ICR/IFA | 7 | 2023-07-03 | 2023-07-11 | 2023-09-21 | 2023-10-02 | 57
0 | ECBGNA1010 | BH-3 TOPSIDE -LOADOUT MOORING ARRANGEMENT - ICR/IFA | 7 | 2023-07-10 | 2023-07-18 | 2023-09-29 | 2023-10-09 | 57
0 | ECBGNA1030 | BH-3 TOPSIDE -CARGO BARGE ARRANGEMENT & SEAFASTENING DETAILS - ICR/IFA | 7 | 2023-07-12 | 2023-07-21 | 2023-10-03 | 2023-10-11 | 57
0 | ECBGNA1020 | BH-3 TOPSIDE -INSTALLATION STUDIES DRAWING - ICR/IFA | 7 | 2023-07-12 | 2023-07-21 | 2023-10-03 | 2023-10-11 | 57
0 | ECBGNA1040 | BH-3 TOPSIDE -SLING LAYING ARRANGEMENT - ICR/IFA | 7 | 2023-07-14 | 2023-07-25 | 2023-10-05 | 2023-10-13 | 57
0 | ECBGNA1005 | BH-3 TOPSIDE -LOADOUT ARRANGEMENT - IFC | 5 | 2023-07-27 | 2023-08-02 | 2023-10-30 | 2023-11-03 | 66
0 | ECBGNA1015 | BH-3 TOPSIDE -LOADOUT MOORING ARRANGEMENT - IFC | 5 | 2023-08-03 | 2023-08-09 | 2023-10-30 | 2023-11-03 | 61
0 | ECBGNA1035 | BH-3 TOPSIDE -CARGO BARGE ARRANGEMENT & SEAFASTENING DETAILS - IFC | 5 | 2023-08-07 | 2023-08-11 | 2023-10-30 | 2023-11-03 | 59
0 | ECBGNA1025 | BH-3 TOPSIDE -INSTALLATION STUDIES DRAWING - IFC | 5 | 2023-08-07 | 2023-08-11 | 2023-10-30 | 2023-11-03 | 59
0 | ECBGNA1045 | BH-3 TOPSIDE -SLING LAYING ARRANGEMENT - IFC | 5 | 2023-08-09 | 2023-08-15 | 2023-10-30 | 2023-11-03 | 57
SATAH WHP 10 TOPSIDES |  |  | 247 | 2022-09-08 | 2023-08-31 | 2022-11-21 | 2023-11-16 | 55
STRUCTURAL |  |  | 119 | 2022-09-08 | 2023-02-24 | 2022-11-21 | 2023-07-28 | 105
0 | ECSGSR1000 | WHP-10 SHOP DWGS - DECK FRAMING PLANS (MAIN DECK) | 10 | 2022-09-08 | 2022-09-22 | 2022-11-21 | 2022-12-06 | 52
0 | ECSGSR1020 | WHP-10 SHOP DWGS - DECK FRAMING PLANS (CELLAR DECK) | 12 | 2022-09-12 | 2022-09-28 | 2022-11-24 | 2022-12-13 | 53
0 | ECSGSR1005 | WHP-10 SHOP DWGS - DECK NODE DETAILS (MAIN DECK) | 15 | 2022-09-08 | 2022-09-29 | 2022-12-09 | 2022-12-29 | 64
0 | ECSGSR1040 | WHP-10 SHOP DWGS - DECK FRAMING PLANS (MEZZANINE DECK) | 12 | 2022-09-20 | 2022-10-06 | 2022-12-05 | 2022-12-20 | 52
0 | ECSGSR1075 | WHP-10 SHOP DWGS - DECK FRAMING PLANS (ACCESSPLATFORM) | 15 | 2022-09-15 | 2022-10-06 | 2023-01-09 | 2023-01-27 | 80
0 | ECSGSR1060 | WHP-10 SHOP DWGS - DECK TRUSS ROWS / ELEVATIONS | 15 | 2022-09-15 | 2022-10-06 | 2022-12-14 | 2023-01-03 | 62
0 | ECSGSR1025 | WHP-10 SHOP DWGS - DECK NODE DETAILS (CELLAR DECK) | 15 | 2022-09-21 | 2022-10-12 | 2022-12-12 | 2022-12-30 | 56
0 | ECSGSR1045 | WHP-10 SHOP DWGS - DECK NODE DETAILS (MEZZANINE DECK) | 15 | 2022-09-22 | 2022-10-13 | 2022-12-19 | 2023-01-06 | 60
0 | ECSGSR1010 | WHP-10 SHOP DWGS - DECK SECONDARY STEEL (MAIN DECK) | 15 | 2022-09-22 | 2022-10-13 | 2022-12-20 | 2023-01-09 | 61
0 | ECSGSR1090 | WHP-10 SHOP DWGS - DECK FRAMING PLANS (WEATHER DECK) | 15 | 2022-09-27 | 2022-10-18 | 2022-12-07 | 2022-12-27 | 49
0 | ECSGSR1030 | WHP-10 SHOP DWGS - DECK SECONDARY STEEL (CELLAR DECK) | 15 | 2022-09-28 | 2022-10-19 | 2022-12-19 | 2023-01-06 | 56
0 | ECSGSR1095 | WHP-10 SHOP DWGS - DECK NODE DETAILS (WEATHER DECK) | 15 | 2022-10-04 | 2022-10-25 | 2023-01-11 | 2023-01-31 | 69
0 | ECSGSR1015 | WHP-10 SHOP DWGS - DECK PLATING DETAILS (MAIN DECK) | 20 | 2022-09-29 | 2022-10-27 | 2023-02-14 | 2023-03-13 | 96
0 | ECSGSR1080 | WHP-10 SHOP DWGS - DECK SECONDARY STEEL (ACCESSPLATFORM) | 15 | 2022-10-10 | 2022-10-31 | 2023-01-09 | 2023-01-27 | 63
0 | ECSGSR1135 | WHP-10 SHOP DWGS - DECK STABING GUIDES | 20 | 2022-10-06 | 2022-11-03 | 2023-03-22 | 2023-04-18 | 117
0 | ECSGSR1050 | WHP-10 SHOP DWGS - DECK SECONDARY STEEL (MEZZANINE DECK) | 15 | 2022-10-17 | 2022-11-07 | 2022-12-26 | 2023-01-13 | 48
0 | ECSGSR1035 | WHP-10 SHOP DWGS - DECK PLATING DETAILS (CELLAR DECK) | 15 | 2022-10-19 | 2022-11-09 | 2023-03-02 | 2023-03-22 | 94
0 | ECSGSR1100 | WHP-10 SHOP DWGS - DECK SECONDARY STEEL (WEATHER DECK) | 15 | 2022-10-24 | 2022-11-14 | 2023-01-23 | 2023-02-10 | 63
0 | ECSGSR1085 | WHP-10 SHOP DWGS - DECK PLATING DETAILS (ACCESSPLATFORM) | 15 | 2022-10-31 | 2022-11-21 | 2023-03-23 | 2023-04-12 | 101
0 | ECSGSR1140 | WHP-10 SHOP DWGS - DECK PENETRATION AND DETAILS | 15 | 2022-10-31 | 2022-11-21 | 2023-01-23 | 2023-02-10 | 58
0 | ECSGSR1110 | WHP-10 SHOP DWGS - DECK FRAMING PLANS (HELIDECK) | 12 | 2022-11-07 | 2022-11-23 | 2023-01-16 | 2023-01-31 | 48
0 | ECSGSR1055 | WHP-10 SHOP DWGS - DECK PLATING DETAILS (MEZZANINE DECK) | 15 | 2022-11-07 | 2022-11-28 | 2023-03-23 | 2023-04-12 | 96
0 | ECSGSR1115 | WHP-10 SHOP DWGS - DECK NODE DETAILS (HELIDECK) | 15 | 2022-11-09 | 2022-11-30 | 2023-02-01 | 2023-02-21 | 58
0 | ECSGSR1105 | WHP-10 SHOP DWGS - DECK PLATING DETAILS (WEATHER DECK) | 15 | 2022-11-14 | 2022-12-07 | 2023-04-06 | 2023-04-28 | 101
0 | ECSGSR1120 | WHP-10 SHOP DWGS - DECK SECONDARY STEEL (HELIDECK) | 15 | 2022-11-16 | 2022-12-09 | 2023-02-15 | 2023-03-07 | 63
0 | ECSGSR1145 | WHP-10 SHOP DWGS - DECK GRATINGS & HANDRAILS LAYOUT | 20 | 2022-11-14 | 2022-12-14 | 2023-02-17 | 2023-03-16 | 67
0 | ECSGSR1125 | WHP-10 SHOP DWGS - DECK PLATING DETAILS (HELIDECK) | 15 | 2022-12-09 | 2022-12-30 | 2023-03-27 | 2023-04-14 | 76
0 | ECSGSR1165 | WHP-10 SHOP DWGS - CONDUCTOR GUIDE / HATCH | 15 | 2022-12-12 | 2023-01-02 | 2023-03-29 | 2023-04-18 | 77
0 | ECSGSR1180 | WHP-10 SHOP DRAWINGS - OFFSHORE INSTALL FRAME & GRATING | 20 | 2022-12-05 | 2023-01-02 | 2023-05-30 | 2023-06-26 | 124
0 | ECSGSR1185 | WHP-10 SHOP DRAWINGS - SWING ROPES | 15 | 2022-12-12 | 2023-01-02 | 2023-06-06 | 2023-06-26 | 124
0 | ECSGSR1150 | WHP-10 SHOP DWGS - DECK MONORAILS GA & DETAILS | 15 | 2022-12-14 | 2023-01-04 | 2023-04-17 | 2023-05-09 | 88
0 | ECSGSR1190 | WHP-10 SHOP DWGS - DECK STAIR TOWER | 15 | 2022-12-19 | 2023-01-09 | 2023-05-26 | 2023-06-15 | 112
0 | ECSGSR1155 | WHP-10 SHOP DWGS - VENT BOOM | 15 | 2022-12-21 | 2023-01-11 | 2023-06-22 | 2023-07-17 | 129
0 | ECSGSR1070 | WHP-10 SHOP DWGS- DECK PAD EYES | 15 | 2022-12-21 | 2023-01-11 | 2023-03-23 | 2023-04-12 | 66
0 | ECSGSR1065 | WHP-10 SHOP DWGS - EQUIPMENT SUPPORT & PLAN DETAILS | 30 | 2022-11-28 | 2023-01-11 | 2023-03-10 | 2023-04-20 | 72
0 | ECSGSR1175 | WHP-10 SHOP DRAWINGS - STRUCTURAL MISCELLANEOUS DETAIL | 20 | 2022-12-21 | 2023-01-18 | 2023-05-30 | 2023-06-26 | 112
0 | ECSGSR1160 | WHP-10 SHOP DWGS - BH-03 JACKET RISER GA AND SUPPORT DETAILS | 24 | 2022-12-19 | 2023-01-20 | 2023-06-02 | 2023-07-10 | 117
0 | ECSGSR1195 | WHP-10 SHOP DRAWINGS - ACCESS PLATFORMS/ LADDERS | 15 | 2023-01-02 | 2023-01-23 | 2023-05-01 | 2023-05-19 | 83
0 | ECSGSR1130 | WHP-10 SHOP DWGS - HELI DECK MISC DETAILS | 20 | 2022-12-30 | 2023-01-27 | 2023-04-17 | 2023-05-16 | 76
0 | ECSGSR1170 | WHP-10 SHOP DWGS - DECK IDENTIFICATION PANELS DETAILS | 15 | 2023-01-27 | 2023-02-17 | 2023-07-07 | 2023-07-28 | 110
0 | ECSGSR1200 | WHP-10 SHOP DRAWINGS - SEAFASTENING DETAILS | 20 | 2023-01-27 | 2023-02-24 | 2023-05-30 | 2023-06-26 | 85
PIPING |  |  | 100 | 2022-12-19 | 2023-05-10 | 2023-02-20 | 2023-07-31 | 55
0 | ECSGPI1000 | WHP-10 SHOP DWGS - PIPING SUPPORTS - CELLAR DECK | 20 | 2022-12-19 | 2023-01-16 | 2023-02-20 | 2023-03-17 | 45
0 | ECSGPI1005 | WHP-10 SHOP DWGS - PIPING SUPPORTS - MAIN DECK | 20 | 2022-12-26 | 2023-01-23 | 2023-02-27 | 2023-03-24 | 45
0 | ECSGPI1020 | WHP-10 SHOP DWGS - PIPING ISOMETRICS - (CS/LTCS/ CLADDED) | 15 | 2023-01-16 | 2023-02-06 | 2023-03-24 | 2023-04-13 | 49
0 | ECSGPI1010 | WHP-10 SHOP DWGS - PIPING SUPPORTS - MEZZANINE DECK | 20 | 2023-01-09 | 2023-02-06 | 2023-03-13 | 2023-04-07 | 45
0 | ECSGPI1015 | WHP-10 SHOP DWGS - PIPING SUPPORTS - WEATHER DECK | 15 | 2023-01-23 | 2023-02-13 | 2023-03-27 | 2023-04-14 | 45
0 | ECSGPI1025 | WHP-10 SHOP DWGS - PIPING ISOMETRICS - (CU-NI) | 15 | 2023-01-30 | 2023-02-20 | 2023-04-07 | 2023-05-01 | 49
0 | ECSGPI1030 | WHP-10 SHOP DWGS - PIPING ISOMETRICS - (INCONEL) | 15 | 2023-02-13 | 2023-03-06 | 2023-04-25 | 2023-05-15 | 49
0 | ECSGPI1035 | WHP-10 SHOP DWGS - PIPING ISOMETRICS (SS/DUPLEX) | 15 | 2023-02-27 | 2023-03-20 | 2023-05-09 | 2023-05-29 | 49
0 | ECSGPI1040 | WHP-10 PIPING HYDROTEST PACKS | 25 | 2023-04-03 | 2023-05-10 | 2023-06-21 | 2023-07-31 | 55
ELECTRICAL |  |  | 50 | 2022-11-14 | 2023-01-25 | 2023-02-28 | 2023-05-10 | 74
0 | ECSGEL1000 | WHP-10 ELECTRICAL SHOP DWGS (CABLE TRAY SUPPORTS) | 40 | 2022-11-14 | 2023-01-11 | 2023-02-28 | 2023-04-26 | 74
0 | ECSGEL1010 | WHP-10 ELECTRICAL - SHOP DWGS (OTHER SUPPORTS) | 40 | 2022-11-28 | 2023-01-25 | 2023-03-14 | 2023-05-10 | 74
INSTRUMENTATION / TELECOM |  |  | 80 | 2022-10-04 | 2023-01-26 | 2023-01-17 | 2023-05-10 | 73
0 | ECSGIN1000 | WHP-10 INSTRUMENTATION SHOP DWGS (CABLE TRAY SUPPORTS) | 40 | 2022-10-04 | 2022-11-29 | 2023-01-17 | 2023-03-13 | 73
0 | ECSGIN1010 | WHP-10 INSTRUMENTATION - SHOP DWGS (OTHER SUPPORTS) | 40 | 2022-11-29 | 2023-01-26 | 2023-03-14 | 2023-05-10 | 73
MECHANICAL |  |  | 25 | 2022-10-11 | 2022-11-15 | 2022-12-19 | 2023-01-20 | 47
0 | ECSGME1000 | WHP-10 SHOP DRAWINGS - VENT DRAIN DRUM | 25 | 2022-10-11 | 2022-11-15 | 2022-12-19 | 2023-01-20 | 47
NAVAL ARCHITECTURE / INSTALLATION |  |  | 37 | 2023-07-10 | 2023-08-31 | 2023-09-13 | 2023-11-16 | 55
DOCUMENTS |  |  | 29 | 2023-07-17 | 2023-08-28 | 2023-10-05 | 2023-11-16 | 58
0 | ECSDNA1010 | WHP-10 TOPSIDE -LOADOUT MOORING FORCE CALCULATION - ICR/IFA | 7 | 2023-07-17 | 2023-07-27 | 2023-10-05 | 2023-10-13 | 56
0 | ECSDNA1000 | WHP-10 TOPSIDE -BARGE BALLASTING CALCULATIONS DURING LOADOUT - ICR/IFA | 7 | 2023-07-20 | 2023-07-31 | 2023-10-18 | 2023-10-26 | 63
0 | ECSDNA1030 | WHP-10 TOPSIDE -BOLLARD PULL CALCULATION - ICR/IFA | 7 | 2023-07-27 | 2023-08-07 | 2023-10-05 | 2023-10-13 | 49
0 | ECSDNA1020 | WHP-10 TOPSIDE -STABILITY ANALYSIS DURING TRANSPORTATION - ICR/IFA | 7 | 2023-07-27 | 2023-08-07 | 2023-10-05 | 2023-10-13 | 49
0 | ECSDNA1015 | WHP-10 TOPSIDE -LOADOUT MOORING FORCE CALCULATION - IFC | 5 | 2023-08-10 | 2023-08-17 | 2023-10-30 | 2023-11-03 | 56
0 | ECSDNA1005 | WHP-10 TOPSIDE -BARGE BALLASTING CALCULATIONS DURING LOADOUT - IFC | 5 | 2023-08-14 | 2023-08-21 | 2023-11-10 | 2023-11-16 | 63
0 | ECSDNA1035 | WHP-10 TOPSIDE -BOLLARD PULL CALCULATION - IFC | 5 | 2023-08-21 | 2023-08-28 | 2023-10-30 | 2023-11-03 | 49
0 | ECSDNA1025 | WHP-10 TOPSIDE -STABILITY ANALYSIS DURING TRANSPORTATION - IFC | 5 | 2023-08-21 | 2023-08-28 | 2023-10-30 | 2023-11-03 | 49
DRAWINGS |  |  | 37 | 2023-07-10 | 2023-08-31 | 2023-09-13 | 2023-11-16 | 55
0 | ECSGNA1000 | WHP-10 TOPSIDE -LOADOUT ARRANGEMENT - ICR/IFA | 7 | 2023-07-10 | 2023-07-20 | 2023-09-13 | 2023-09-21 | 46
0 | ECSGNA1010 | WHP-10 TOPSIDE -LOADOUT MOORING ARRANGEMENT - ICR/IFA | 7 | 2023-07-17 | 2023-07-27 | 2023-09-20 | 2023-09-29 | 46
0 | ECSGNA1020 | WHP-10 TOPSIDE -INSTALLATION STUDIES DRAWING - ICR/IFA | 7 | 2023-07-20 | 2023-07-31 | 2023-09-22 | 2023-10-03 | 46
0 | ECSGNA1030 | WHP-10 TOPSIDE -CARGO BARGE ARRANGEMENT & SEAFASTENING DETAILS - ICR/IFA | 7 | 2023-07-27 | 2023-08-07 | 2023-10-02 | 2023-10-10 | 46
0 | ECSGNA1005 | WHP-10 TOPSIDE -LOADOUT ARRANGEMENT - IFC | 5 | 2023-08-03 | 2023-08-10 | 2023-10-30 | 2023-11-03 | 61
0 | ECSGNA1040 | WHP-10 TOPSIDE -SLING LAYING ARRANGEMENT - ICR/IFA | 7 | 2023-08-01 | 2023-08-10 | 2023-10-05 | 2023-10-13 | 46
0 | ECSGNA1015 | WHP-10 TOPSIDE -LOADOUT MOORING ARRANGEMENT - IFC | 5 | 2023-08-10 | 2023-08-17 | 2023-11-10 | 2023-11-16 | 65
0 | ECSGNA1025 | WHP-10 TOPSIDE -INSTALLATION STUDIES DRAWING - IFC | 5 | 2023-08-14 | 2023-08-21 | 2023-10-30 | 2023-11-03 | 54
0 | ECSGNA1035 | WHP-10 TOPSIDE -CARGO BARGE ARRANGEMENT & SEAFASTENING DETAILS - IFC | 5 | 2023-08-21 | 2023-08-28 | 2023-10-30 | 2023-11-03 | 49
0 | ECSGNA1045 | WHP-10 TOPSIDE -SLING LAYING ARRANGEMENT - IFC | 5 | 2023-08-24 | 2023-08-31 | 2023-10-30 | 2023-11-03 | 46
HAIR DALMA WHP HD-T4 TOPSIDES |  |  | 272 | 2022-09-13 | 2023-10-11 | 2023-01-10 | 2024-03-04 | 101
STRUCTURAL |  |  | 154 | 2022-09-13 | 2023-04-19 | 2023-02-13 | 2023-09-26 | 109
0 | ECTGSR1000 | HD-T4 SHOP DWGS - DECK FRAMING PLANS (MAIN DECK) | 10 | 2022-09-13 | 2022-09-27 | 2023-02-13 | 2023-02-24 | 107
0 | ECTGSR1020 | HD-T4 SHOP DWGS - DECK FRAMING PLANS (CELLAR DECK) | 12 | 2022-09-13 | 2022-09-29 | 2023-02-17 | 2023-03-06 | 111
0 | ECTGSR1075 | HD-T4 SHOP DWGS - DECK FRAMING PLANS (ACCESSPLATFORM) | 13 | 2022-09-13 | 2022-09-30 | 2023-04-17 | 2023-05-05 | 152
0 | ECTGSR1005 | HD-T4 SHOP DWGS - DECK NODE DETAILS (MAIN DECK) | 15 | 2022-09-13 | 2022-10-04 | 2023-03-23 | 2023-04-12 | 135
0 | ECTGSR1040 | HD-T4 SHOP DWGS - DECK FRAMING PLANS (MEZZANINE DECK) | 15 | 2022-09-20 | 2022-10-11 | 2023-02-24 | 2023-03-16 | 111
0 | ECTGSR1060 | HD-T4 SHOP DWGS - DECK TRUSS ROWS / ELEVATIONS | 20 | 2022-09-13 | 2022-10-11 | 2023-03-09 | 2023-04-05 | 125
0 | ECTGSR1025 | HD-T4 SHOP DWGS - DECK NODE DETAILS (CELLAR DECK) | 15 | 2022-09-22 | 2022-10-13 | 2023-03-20 | 2023-04-07 | 125
0 | ECTGSR1010 | HD-T4 SHOP DWGS - DECK SECONDARY STEEL (MAIN DECK) | 12 | 2022-09-27 | 2022-10-13 | 2023-03-23 | 2023-04-07 | 125
0 | ECTGSR1090 | HD-T4 SHOP DWGS - DECK FRAMING PLANS (WEATHER DECK) | 15 | 2022-09-27 | 2022-10-18 | 2023-03-06 | 2023-03-24 | 112
0 | ECTGSR1030 | HD-T4 SHOP DWGS - DECK SECONDARY STEEL (CELLAR DECK) | 15 | 2022-09-29 | 2022-10-20 | 2023-03-27 | 2023-04-14 | 125
0 | ECTGSR1045 | HD-T4 SHOP DWGS - DECK NODE DETAILS (MEZZANINE DECK) | 15 | 2022-10-04 | 2022-10-25 | 2023-03-10 | 2023-03-30 | 111
0 | ECTGSR1015 | HD-T4 SHOP DWGS - DECK PLATING DETAILS (MAIN DECK) | 15 | 2022-10-04 | 2022-10-25 | 2023-06-12 | 2023-07-05 | 175
0 | ECTGSR1135 | HD-T4 SHOP DWGS - DECK STABING GUIDES | 15 | 2022-10-04 | 2022-10-25 | 2023-07-12 | 2023-08-02 | 194
0 | ECTGSR1080 | HD-T4 SHOP DWGS - DECK SECONDARY STEEL (ACCESSPLATFORM) | 15 | 2022-10-11 | 2022-11-01 | 2023-04-13 | 2023-05-05 | 130
0 | ECTGSR1050 | HD-T4 SHOP DWGS - DECK SECONDARY STEEL (MEZZANINE DECK) | 12 | 2022-10-18 | 2022-11-03 | 2023-04-05 | 2023-04-20 | 119
0 | ECTGSR1095 | HD-T4 SHOP DWGS - DECK NODE DETAILS (WEATHER DECK) | 15 | 2022-10-18 | 2022-11-08 | 2023-03-28 | 2023-04-17 | 113
0 | ECTGSR1085 | HD-T4 SHOP DWGS - DECK PLATING DETAILS (ACCESSPLATFORM) | 15 | 2022-11-01 | 2022-11-22 | 2023-06-23 | 2023-07-18 | 164
0 | ECTGSR1145 | HD-T4 SHOP DWGS - DECK PENETRATION AND DETAILS | 10 | 2022-11-09 | 2022-11-23 | 2023-04-06 | 2023-04-19 | 104
0 | ECTGSR1055 | HD-T4 SHOP DWGS - DECK PLATING DETAILS (MEZZANINE DECK) | 15 | 2022-11-03 | 2022-11-24 | 2023-06-23 | 2023-07-18 | 162
0 | ECTGSR1035 | HD-T4 SHOP DWGS - DECK PLATING DETAILS (CELLAR DECK) | 15 | 2022-11-03 | 2022-11-24 | 2023-06-06 | 2023-06-26 | 149
0 | ECTGSR1100 | HD-T4 SHOP DWGS - DECK SECONDARY STEEL (WEATHER DECK) | 15 | 2022-11-08 | 2022-11-29 | 2023-04-28 | 2023-05-18 | 119
0 | ECTGSR1110 | HD-T4 SHOP DWGS - DECK FRAMING PLANS (HELIDECK) | 15 | 2022-11-16 | 2022-12-09 | 2023-04-11 | 2023-05-03 | 102
0 | ECTGSR1115 | HD-T4 SHOP DWGS - DECK NODE DETAILS (HELIDECK) | 15 | 2022-11-25 | 2022-12-20 | 2023-05-04 | 2023-05-24 | 110
0 | ECTGSR1105 | HD-T4 SHOP DWGS - DECK PLATING DETAILS (WEATHER DECK) | 15 | 2022-11-29 | 2022-12-22 | 2023-06-13 | 2023-07-06 | 136
0 | ECTGSR1120 | HD-T4 SHOP DWGS - DECK SECONDARY STEEL (HELIDECK) | 15 | 2022-12-06 | 2022-12-27 | 2023-05-18 | 2023-06-07 | 115
0 | ECTGSR1160 | HD-T4 SHOP DWGS - BH-03 JACKET RISER GA AND SUPPORT DETAILS | 10 | 2022-12-15 | 2022-12-29 | 2023-07-07 | 2023-07-21 | 141
0 | ECTGSR1070 | HD-T4 SHOP DWGS- DECK PAD EYES | 10 | 2022-12-21 | 2023-01-04 | 2023-05-18 | 2023-05-31 | 104
0 | ECTGSR1150 | HD-T4 SHOP DWGS - DECK MONORAILS GA & DETAILS | 15 | 2022-12-16 | 2023-01-06 | 2023-08-15 | 2023-09-04 | 166
0 | ECTGSR1140 | HD-T4 SHOP DWGS - DECK GRATINGS & HANDRAILS LAYOUT | 20 | 2022-12-09 | 2023-01-06 | 2023-05-31 | 2023-06-30 | 121
0 | ECTGSR1065 | HD-T4 SHOP DWGS - EQUIPMENT SUPPORT & PLAN DETAILS | 30 | 2022-11-28 | 2023-01-11 | 2023-06-13 | 2023-07-28 | 137
0 | ECTGSR1195 | HD-T4 SHOP DRAWINGS - ACCESS PLATFORMS/ LADDERS | 15 | 2022-12-22 | 2023-01-12 | 2023-08-07 | 2023-08-25 | 156
0 | ECTGSR1125 | HD-T4 SHOP DWGS - DECK PLATING DETAILS (HELIDECK) | 15 | 2022-12-27 | 2023-01-17 | 2023-07-05 | 2023-07-26 | 131
0 | ECTGSR1165 | HD-T4 SHOP DWGS - CONDUCTOR GUIDE / HATCH | 15 | 2022-12-29 | 2023-01-19 | 2023-06-02 | 2023-06-22 | 109
0 | ECTGSR1190 | HD-T4 SHOP DWGS - DECK STAIR TOWER | 15 | 2023-01-19 | 2023-02-09 | 2023-06-23 | 2023-07-18 | 109
0 | ECTGSR1185 | HD-T4 SHOP DRAWINGS - SWING ROPES | 15 | 2023-02-02 | 2023-02-23 | 2023-07-12 | 2023-08-02 | 109
0 | ECTGSR1130 | HD-T4 SHOP DWGS - HELI DECK MISC DETAILS | 15 | 2023-02-09 | 2023-03-02 | 2023-07-20 | 2023-08-09 | 109
0 | ECTGSR1155 | HD-T4 SHOP DWGS - VENT BOOM | 15 | 2023-02-16 | 2023-03-09 | 2023-07-27 | 2023-08-16 | 109
0 | ECTGSR1170 | HD-T4 SHOP DWGS - DECK IDENTIFICATION PANELS DETAILS | 15 | 2023-02-23 | 2023-03-16 | 2023-08-03 | 2023-08-23 | 109
0 | ECTGSR1175 | HD-T4 SHOP DRAWINGS - STRUCTURAL MISCELLANEOUS DETAIL | 15 | 2023-03-02 | 2023-03-23 | 2023-08-10 | 2023-08-30 | 109
0 | ECTGSR1180 | HD-T4 SHOP DRAWINGS - OFFSHORE INSTALL FRAME & GRATING | 15 | 2023-03-15 | 2023-04-05 | 2023-08-23 | 2023-09-12 | 109
0 | ECTGSR1200 | HD-T4 SHOP DRAWINGS - SEAFASTENING DETAILS | 15 | 2023-03-29 | 2023-04-19 | 2023-09-06 | 2023-09-26 | 109
PIPING |  |  | 100 | 2022-12-19 | 2023-05-10 | 2023-05-16 | 2023-11-17 | 133
0 | ECTGPI1000 | WHP HD-T4 SHOP DWGS - PIPING SUPPORTS - CELLAR DECK | 20 | 2022-12-19 | 2023-01-16 | 2023-05-16 | 2023-06-12 | 104
0 | ECTGPI1005 | WHP HD-T4 SHOP DWGS - PIPING SUPPORTS - MAIN DECK | 20 | 2022-12-26 | 2023-01-23 | 2023-05-23 | 2023-06-19 | 104
0 | ECTGPI1020 | WHP HD-T4 SHOP DWGS - PIPING ISOMETRICS - (CS/LTCS/ CLADDED) | 15 | 2023-01-16 | 2023-02-06 | 2023-07-17 | 2023-08-07 | 125
0 | ECTGPI1010 | WHP HD-T4 SHOP DWGS - PIPING SUPPORTS - MEZZANINE DECK | 20 | 2023-01-09 | 2023-02-06 | 2023-06-06 | 2023-07-06 | 104
0 | ECTGPI1025 | WHP HD-T4 SHOP DWGS - PIPING ISOMETRICS - (CU-NI) | 15 | 2023-01-30 | 2023-02-20 | 2023-08-02 | 2023-08-22 | 126
0 | ECTGPI1015 | WHP HD-T4 SHOP DWGS - PIPING SUPPORTS - WEATHER DECK | 20 | 2023-01-23 | 2023-02-20 | 2023-06-20 | 2023-07-21 | 104
0 | ECTGPI1030 | WHP HD-T4 SHOP DWGS - PIPING ISOMETRICS - (INCONEL) | 15 | 2023-02-13 | 2023-03-06 | 2023-08-16 | 2023-09-05 | 126
0 | ECTGPI1035 | WHP HD-T4 SHOP DWGS - PIPING ISOMETRICS (SS/DUPLEX) | 15 | 2023-02-27 | 2023-03-20 | 2023-08-30 | 2023-09-19 | 126
0 | ECTGPI1040 | WHP HD-T4 PIPING HYDROTEST PACKS | 25 | 2023-04-03 | 2023-05-10 | 2023-10-16 | 2023-11-17 | 133
ELECTRICAL |  |  | 80 | 2022-11-17 | 2023-03-13 | 2023-04-25 | 2023-08-18 | 109
0 | ECTGEL1000 | HD-T4 ELECTRICAL SHOP DWGS (CABLE TRAY SUPPORTS) | 40 | 2022-11-17 | 2023-01-16 | 2023-04-25 | 2023-06-19 | 109
0 | ECTGEL1010 | HD-T4 ELECTRICAL - SHOP DWGS (OTHER SUPPORTS) | 40 | 2023-01-16 | 2023-03-13 | 2023-06-20 | 2023-08-18 | 109
INSTRUMENTATION / TELECOM |  |  | 80 | 2022-10-04 | 2023-01-26 | 2023-04-25 | 2023-08-18 | 141
0 | ECTGIN1000 | HD-T4 INSTRUMENTATION SHOP DWGS (CABLE TRAY SUPPORTS) | 40 | 2022-10-04 | 2022-11-29 | 2023-04-25 | 2023-06-19 | 141
0 | ECTGIN1010 | HD-T4 INSTRUMENTATION - SHOP DWGS (OTHER SUPPORTS) | 40 | 2022-11-29 | 2023-01-26 | 2023-06-20 | 2023-08-18 | 141
MECHANICAL |  |  | 25 | 2022-10-06 | 2022-11-10 | 2023-01-10 | 2023-02-13 | 66
0 | ECTGME1000 | HD-T4 SHOP DRAWINGS - VENT DRAIN DRUM | 25 | 2022-10-06 | 2022-11-10 | 2023-01-10 | 2023-02-13 | 66
NAVAL ARCHITECTURE / INSTALLATION |  |  | 29 | 2023-08-30 | 2023-10-11 | 2024-01-23 | 2024-03-04 | 101
DOCUMENTS |  |  | 24 | 2023-09-04 | 2023-10-09 | 2024-02-01 | 2024-03-04 | 103
0 | ECTDNA1000 | HD-T4 TOPSIDE -BARGE BALLASTING CALCULATIONS DURING LOADOUT - ICR/IFA | 7 | 2023-09-04 | 2023-09-13 | 2024-02-01 | 2024-02-12 | 105
0 | ECTDNA1030 | HD-T4 TOPSIDE -BOLLARD PULL CALCULATION - ICR/IFA | 7 | 2023-09-06 | 2023-09-15 | 2024-02-01 | 2024-02-12 | 103
0 | ECTDNA1010 | HD-T4 TOPSIDE -LOADOUT MOORING FORCE CALCULATION - ICR/IFA | 7 | 2023-09-06 | 2023-09-15 | 2024-02-01 | 2024-02-12 | 103
0 | ECTDNA1020 | HD-T4 TOPSIDE -STABILITY ANALYSIS DURING TRANSPORTATION - ICR/IFA | 7 | 2023-09-06 | 2023-09-15 | 2024-02-01 | 2024-02-12 | 103
0 | ECTDNA1005 | HD-T4 TOPSIDE -BARGE BALLASTING CALCULATIONS DURING LOADOUT - IFC | 5 | 2023-09-28 | 2023-10-05 | 2024-02-27 | 2024-03-04 | 105
0 | ECTDNA1035 | HD-T4 TOPSIDE -BOLLARD PULL CALCULATION - IFC | 5 | 2023-10-02 | 2023-10-09 | 2024-02-27 | 2024-03-04 | 103
0 | ECTDNA1015 | HD-T4 TOPSIDE -LOADOUT MOORING FORCE CALCULATION - IFC | 5 | 2023-10-02 | 2023-10-09 | 2024-02-27 | 2024-03-04 | 103
0 | ECTDNA1025 | HD-T4 TOPSIDE -STABILITY ANALYSIS DURING TRANSPORTATION - IFC | 5 | 2023-10-02 | 2023-10-09 | 2024-02-27 | 2024-03-04 | 103
DRAWINGS |  |  | 29 | 2023-08-30 | 2023-10-11 | 2024-01-23 | 2024-03-04 | 101
0 | ECTGNA1000 | HD-T4 TOPSIDE -LOADOUT ARRANGEMENT - ICR/IFA | 5 | 2023-08-30 | 2023-09-06 | 2024-01-23 | 2024-01-29 | 101
0 | ECTGNA1020 | HD-T4 TOPSIDE -INSTALLATION STUDIES DRAWING - ICR/IFA | 6 | 2023-09-06 | 2023-09-14 | 2024-01-30 | 2024-02-06 | 101
0 | ECTGNA1030 | HD-T4 TOPSIDE -CARGO BARGE ARRANGEMENT & SEAFASTENING DETAILS - ICR/IFA | 7 | 2023-09-06 | 2023-09-15 | 2024-01-30 | 2024-02-08 | 101
0 | ECTGNA1010 | HD-T4 TOPSIDE -LOADOUT MOORING ARRANGEMENT - ICR/IFA | 7 | 2023-09-06 | 2023-09-15 | 2024-01-30 | 2024-02-08 | 101
0 | ECTGNA1040 | HD-T4 TOPSIDE -SLING LAYING ARRANGEMENT - ICR/IFA | 7 | 2023-09-08 | 2023-09-19 | 2024-02-01 | 2024-02-12 | 101
0 | ECTGNA1005 | HD-T4 TOPSIDE -LOADOUT ARRANGEMENT - IFC | 5 | 2023-09-20 | 2023-09-28 | 2024-02-27 | 2024-03-04 | 110
0 | ECTGNA1025 | HD-T4 TOPSIDE -INSTALLATION STUDIES DRAWING - IFC | 5 | 2023-09-29 | 2023-10-06 | 2024-02-27 | 2024-03-04 | 104
0 | ECTGNA1035 | HD-T4 TOPSIDE -CARGO BARGE ARRANGEMENT & SEAFASTENING DETAILS - IFC | 5 | 2023-10-02 | 2023-10-09 | 2024-02-27 | 2024-03-04 | 103
0 | ECTGNA1015 | HD-T4 TOPSIDE -LOADOUT MOORING ARRANGEMENT - IFC | 5 | 2023-10-02 | 2023-10-09 | 2024-02-27 | 2024-03-04 | 103
0 | ECTGNA1045 | HD-T4 TOPSIDE -SLING LAYING ARRANGEMENT - IFC | 5 | 2023-10-04 | 2023-10-11 | 2024-02-27 | 2024-03-04 | 101
HAIR DALMA WHP HD-03 TOPSIDES |  |  | 251 | 2022-09-27 | 2023-09-25 | 2022-12-26 | 2023-11-17 | 39
STRUCTURAL |  |  | 145 | 2022-09-27 | 2023-04-20 | 2022-12-26 | 2023-10-11 | 118
0 | ECHGSR1000 | HD-03 SHOP DWGS - DECK FRAMING PLANS CELLAR DECK | 10 | 2022-09-27 | 2022-10-11 | 2022-12-26 | 2023-01-06 | 62
0 | ECHGSR1025 | HD-03 SHOP DWGS - DECK NODE DETAILS (CELLAR DECK) | 15 | 2022-09-27 | 2022-10-18 | 2023-01-23 | 2023-02-10 | 82
0 | ECHGSR1040 | HD-03 SHOP DWGS - DECK FRAMING PLANS (UPPER DECK) | 12 | 2022-10-06 | 2022-10-24 | 2023-01-05 | 2023-01-20 | 63
0 | ECHGSR1010 | HD-03 SHOP DWGS - DECK SECONDARY STEEL (MAIN DECK) | 15 | 2022-10-04 | 2022-10-25 | 2023-01-30 | 2023-02-17 | 82
0 | ECHGSR1060 | HD-03 SHOP DWGS - DECK TRUSS ROWS / ELEVATIONS | 15 | 2022-10-04 | 2022-10-25 | 2023-02-02 | 2023-02-22 | 85
0 | ECHGSR1075 | HD-03 SHOP DWGS - DECK FRAMING PLANS MAIN DECK | 15 | 2022-10-06 | 2022-10-27 | 2023-01-19 | 2023-02-08 | 73
0 | ECHGSR1005 | HD-03 SHOP DWGS - DECK NODE DETAILS (MAIN DECK) | 15 | 2022-10-11 | 2022-11-01 | 2023-01-19 | 2023-02-08 | 70
0 | ECHGSR1110 | HD-03 SHOP DWGS - DECK STABING GUIDES | 15 | 2022-10-11 | 2022-11-01 | 2023-04-18 | 2023-05-10 | 133
0 | ECHGSR1030 | HD-03 SHOP DWGS - DECK SECONDARY STEEL (CELLAR DECK) | 15 | 2022-10-11 | 2022-11-01 | 2023-02-06 | 2023-02-24 | 82
0 | ECHGSR1090 | HD-03 SHOP DWGS - DECK FRAMING PLANS (WEATHER DECK) | 15 | 2022-10-11 | 2022-11-01 | 2023-03-06 | 2023-03-24 | 102
0 | ECHGSR1095 | HD-03 SHOP DWGS - DECK NODE DETAILS (WEATHER DECK) | 15 | 2022-10-18 | 2022-11-08 | 2023-03-27 | 2023-04-14 | 112
0 | ECHGSR1015 | HD-03 SHOP DWGS - DECK PLATING DETAILS (MAIN DECK) | 15 | 2022-10-18 | 2022-11-08 | 2023-04-06 | 2023-04-28 | 120
0 | ECHGSR1035 | HD-03 SHOP DWGS - DECK PLATING DETAILS (CELLAR DECK) | 15 | 2022-10-18 | 2022-11-08 | 2023-03-31 | 2023-04-20 | 116
0 | ECHGSR1045 | HD-03 SHOP DWGS - DECK NODE DETAILS (UPPER DECK) | 15 | 2022-10-24 | 2022-11-14 | 2023-02-20 | 2023-03-10 | 83
0 | ECHGSR1080 | HD-03 SHOP DWGS - DECK SECONDARY STEEL MAIN DECK | 15 | 2022-10-27 | 2022-11-17 | 2023-03-13 | 2023-03-31 | 95
0 | ECHGSR1050 | HD-03 SHOP DWGS - DECK SECONDARY STEEL (UPPER DECK) | 15 | 2022-10-31 | 2022-11-21 | 2023-02-27 | 2023-03-17 | 83
0 | ECHGSR1100 | HD-03 SHOP DWGS - DECK SECONDARY STEEL (WEATHER DECK) | 12 | 2022-11-08 | 2022-11-24 | 2023-04-20 | 2023-05-09 | 115
0 | ECHGSR1115 | HD-03 SHOP DWGS - DECK GRATINGS & HANDRAILS LAYOUT | 20 | 2022-11-03 | 2022-12-05 | 2023-03-28 | 2023-04-26 | 101
0 | ECHGSR1125 | HD-03 SHOP DWGS - DECK MONORAILS GA & DETAILS | 15 | 2022-11-15 | 2022-12-08 | 2023-08-01 | 2023-08-21 | 177
0 | ECHGSR1085 | HD-03 SHOP DWGS - DECK PLATING DETAILS MAIN DECK | 15 | 2022-11-17 | 2022-12-12 | 2023-05-24 | 2023-06-13 | 130
0 | ECHGSR1055 | HD-03 SHOP DWGS - DECK PLATING DETAILS (UPPER DECK) | 15 | 2022-11-21 | 2022-12-14 | 2023-05-24 | 2023-06-13 | 128
0 | ECHGSR1070 | HD-03 SHOP DWGS- DECK PAD EYES | 15 | 2022-12-14 | 2023-01-04 | 2023-04-10 | 2023-05-02 | 83
0 | ECHGSR1105 | HD-03 SHOP DWGS - DECK PLATING DETAILS (WEATHER DECK) | 15 | 2022-12-15 | 2023-01-05 | 2023-06-09 | 2023-07-04 | 124
0 | ECHGSR1135 | HD-03 SHOP DWGS - BH-03 JACKET RISER GA AND SUPPORT DETAILS | 10 | 2022-12-22 | 2023-01-05 | 2023-05-19 | 2023-06-01 | 104
0 | ECHGSR1140 | HD-03 SHOP DWGS - CONDUCTOR GUIDE / HATCH | 15 | 2022-12-22 | 2023-01-12 | 2023-04-18 | 2023-05-10 | 83
0 | ECHGSR1065 | HD-03 SHOP DWGS - EQUIPMENT SUPPORT & PLAN DETAILS | 30 | 2022-12-08 | 2023-01-19 | 2023-03-10 | 2023-04-20 | 66
0 | ECHGSR1160 | HD-03 SHOP DRAWINGS - SWING ROPES | 15 | 2023-01-05 | 2023-01-26 | 2023-06-02 | 2023-06-22 | 104
0 | ECHGSR1130 | HD-03 SHOP DWGS - VENT BOOM | 15 | 2023-01-19 | 2023-02-09 | 2023-06-16 | 2023-07-11 | 104
0 | ECHGSR1165 | HD-03 SHOP DWGS - DECK STAIR TOWER | 15 | 2023-02-02 | 2023-02-23 | 2023-07-05 | 2023-07-26 | 104
0 | ECHGSR1145 | HD-03 SHOP DWGS - DECK IDENTIFICATION PANELS DETAILS | 15 | 2023-02-09 | 2023-03-02 | 2023-07-12 | 2023-08-02 | 104
0 | ECHGSR1185 | HD-03 SHOP DWGS JECKET EXTENSION PLAN/ ELEVATION & DETAILS | 15 | 2023-02-16 | 2023-03-09 | 2023-07-20 | 2023-08-09 | 104
0 | ECHGSR1170 | HD-03 SHOP DRAWINGS - ACCESS PLATFORMS/ LADDERS | 15 | 2023-02-23 | 2023-03-16 | 2023-07-27 | 2023-08-16 | 104
0 | ECHGSR1150 | HD-03 SHOP DRAWINGS - STRUCTURAL MISCELLANEOUS DETAIL | 15 | 2023-03-09 | 2023-03-30 | 2023-08-30 | 2023-09-19 | 118
0 | ECHGSR1175 | HD-03 SHOP DRAWINGS - SEAFASTENING DETAILS | 15 | 2023-03-30 | 2023-04-20 | 2023-09-20 | 2023-10-11 | 118
PIPING |  |  | 102 | 2022-12-15 | 2023-05-10 | 2023-03-01 | 2023-08-25 | 74
0 | ECHGPI1000 | WHP HD-03 SHOP DWGS - PIPING SUPPORTS - CELLAR DECK | 20 | 2022-12-15 | 2023-01-12 | 2023-03-01 | 2023-03-28 | 54
0 | ECHGPI1005 | WHP HD-03 SHOP DWGS - PIPING SUPPORTS - MAIN DECK | 20 | 2022-12-22 | 2023-01-19 | 2023-03-08 | 2023-04-04 | 54
0 | ECHGPI1010 | WHP HD-03 SHOP DWGS - PIPING SUPPORTS - UPPER DECK | 20 | 2022-12-29 | 2023-01-26 | 2023-03-15 | 2023-04-11 | 54
0 | ECHGPI1015 | WHP HD-03 SHOP DWGS - PIPING SUPPORTS - WEATHER DECK | 18 | 2023-01-05 | 2023-01-31 | 2023-03-22 | 2023-04-14 | 54
0 | ECHGPI1020 | WHP HD-03 SHOP DWGS - PIPING ISOMETRICS - (CS/LTCS/ CLADDED) | 15 | 2023-01-16 | 2023-02-06 | 2023-03-27 | 2023-04-14 | 50
0 | ECHGPI1025 | WHP HD-03 SHOP DWGS - PIPING ISOMETRICS - (CU-NI) | 15 | 2023-01-30 | 2023-02-20 | 2023-04-28 | 2023-05-18 | 62
0 | ECHGPI1030 | WHP HD-03 SHOP DWGS - PIPING ISOMETRICS - (INCONEL) | 15 | 2023-02-13 | 2023-03-06 | 2023-05-12 | 2023-06-01 | 62
0 | ECHGPI1035 | WHP HD-03 SHOP DWGS - PIPING ISOMETRICS (SS/DUPLEX) | 15 | 2023-02-27 | 2023-03-20 | 2023-05-26 | 2023-06-15 | 62
0 | ECHGPI1040 | WHP HD-03 PIPING HYDROTEST PACKS | 25 | 2023-04-03 | 2023-05-10 | 2023-07-24 | 2023-08-25 | 74
ELECTRICAL |  |  | 70 | 2022-11-15 | 2023-02-23 | 2023-04-14 | 2023-07-28 | 106
0 | ECHGEL1000 | HD-03 ELECTRICAL SHOP DWGS (CABLE TRAY SUPPORTS) | 35 | 2022-11-15 | 2023-01-05 | 2023-04-14 | 2023-06-05 | 106
0 | ECHGEL1010 | HD-03 ELECTRICAL - SHOP DWGS (OTHER SUPPORTS) | 35 | 2023-01-05 | 2023-02-23 | 2023-06-06 | 2023-07-28 | 106
INSTRUMENTATION / TELECOM |  |  | 80 | 2022-10-14 | 2023-02-07 | 2023-03-31 | 2023-07-28 | 118
0 | ECHGIN1000 | HD-03 INSTRUMENTATION SHOP DWGS (CABLE TRAY SUPPORTS) | 40 | 2022-10-14 | 2022-12-13 | 2023-03-31 | 2023-05-29 | 118
0 | ECHGIN1010 | HD-03 INSTRUMENTATION - SHOP DWGS (OTHER SUPPORTS) | 40 | 2022-12-13 | 2023-02-07 | 2023-05-30 | 2023-07-28 | 118
MECHANICAL |  |  | 20 | 2022-10-21 | 2022-11-18 | 2023-01-12 | 2023-02-08 | 57
0 | ECHGME1000 | HD-03 SHOP DRAWINGS - VENT DRAIN DRUM | 20 | 2022-10-21 | 2022-11-18 | 2023-01-12 | 2023-02-08 | 57
NAVAL ARCHITECTURE / INSTALLATION |  |  | 27 | 2023-08-17 | 2023-09-25 | 2023-10-12 | 2023-11-17 | 39
DOCUMENTS |  |  | 27 | 2023-08-17 | 2023-09-25 | 2023-10-16 | 2023-11-17 | 39
0 | ECHDNA1000 | HD-03 TOPSIDE -BARGE BALLASTING CALCULATIONS DURING LOADOUT - ICR/IFA | 7 | 2023-08-17 | 2023-08-28 | 2023-10-19 | 2023-10-27 | 44
0 | ECHDNA1010 | HD-03 TOPSIDE -LOADOUT MOORING FORCE CALCULATION - ICR/IFA | 8 | 2023-08-17 | 2023-08-29 | 2023-10-18 | 2023-10-27 | 43
0 | ECHDNA1020 | HD-03 TOPSIDE -STABILITY ANALYSIS DURING TRANSPORTATION - ICR/IFA | 7 | 2023-08-21 | 2023-08-30 | 2023-10-16 | 2023-10-24 | 39
0 | ECHDNA1030 | HD-03 TOPSIDE -BOLLARD PULL CALCULATION - ICR/IFA | 7 | 2023-08-24 | 2023-09-04 | 2023-10-19 | 2023-10-27 | 39
0 | ECHDNA1005 | HD-03 TOPSIDE -BARGE BALLASTING CALCULATIONS DURING LOADOUT - IFC | 5 | 2023-09-11 | 2023-09-18 | 2023-11-13 | 2023-11-17 | 44
0 | ECHDNA1015 | HD-03 TOPSIDE -LOADOUT MOORING FORCE CALCULATION - IFC | 5 | 2023-09-12 | 2023-09-19 | 2023-11-13 | 2023-11-17 | 43
0 | ECHDNA1025 | HD-03 TOPSIDE -STABILITY ANALYSIS DURING TRANSPORTATION - IFC | 5 | 2023-09-13 | 2023-09-20 | 2023-11-13 | 2023-11-17 | 42
0 | ECHDNA1035 | HD-03 TOPSIDE -BOLLARD PULL CALCULATION - IFC | 5 | 2023-09-18 | 2023-09-25 | 2023-11-13 | 2023-11-17 | 39
DRAWINGS |  |  | 24 | 2023-08-17 | 2023-09-20 | 2023-10-12 | 2023-11-17 | 42
0 | ECHGNA1000 | HD-03 TOPSIDE -LOADOUT ARRANGEMENT - ICR/IFA | 7 | 2023-08-17 | 2023-08-28 | 2023-10-12 | 2023-10-20 | 39
0 | ECHGNA1010 | HD-03 TOPSIDE -LOADOUT MOORING ARRANGEMENT - ICR/IFA | 7 | 2023-08-17 | 2023-08-28 | 2023-10-12 | 2023-10-20 | 39
0 | ECHGNA1030 | HD-03 TOPSIDE -CARGO BARGE ARRANGEMENT & SEAFASTENING DETAILS - ICR/IFA | 7 | 2023-08-21 | 2023-08-30 | 2023-10-16 | 2023-10-24 | 39
0 | ECHGNA1020 | HD-03 TOPSIDE -INSTALLATION STUDIES DRAWING - ICR/IFA | 7 | 2023-08-21 | 2023-08-30 | 2023-10-16 | 2023-10-24 | 39
0 | ECHGNA1040 | HD-03 TOPSIDE -SLING LAYING ARRANGEMENT - ICR/IFA | 7 | 2023-08-23 | 2023-09-01 | 2023-11-02 | 2023-11-10 | 50
0 | ECHGNA1045 | HD-03 TOPSIDE -SLING LAYING ARRANGEMENT - IFC | 5 | 2023-09-01 | 2023-09-08 | 2023-11-13 | 2023-11-17 | 50
0 | ECHGNA1005 | HD-03 TOPSIDE -LOADOUT ARRANGEMENT - IFC | 5 | 2023-09-11 | 2023-09-18 | 2023-11-13 | 2023-11-17 | 44
0 | ECHGNA1015 | HD-03 TOPSIDE -LOADOUT MOORING ARRANGEMENT - IFC | 5 | 2023-09-11 | 2023-09-18 | 2023-11-13 | 2023-11-17 | 44
0 | ECHGNA1035 | HD-03 TOPSIDE -CARGO BARGE ARRANGEMENT & SEAFASTENING DETAILS - IFC | 5 | 2023-09-13 | 2023-09-20 | 2023-11-13 | 2023-11-17 | 42
0 | ECHGNA1025 | HD-03 TOPSIDE -INSTALLATION STUDIES DRAWING - IFC | 5 | 2023-09-13 | 2023-09-20 | 2023-11-13 | 2023-11-17 | 42
IGD-E TOWER (EXISTING) |  |  | 242 | 2022-10-04 | 2023-09-19 | 2023-01-11 | 2023-12-29 | 72
STRUCTURAL |  |  | 94 | 2022-10-04 | 2023-02-15 | 2023-05-03 | 2023-08-04 | 117
0 | ECIGSR1000 | IGD-E SHOP DWGS - DECK SECONDARY STEEL (CELLAR DECK) | 15 | 2022-10-04 | 2022-10-25 | 2023-05-03 | 2023-05-23 | 147
0 | ECIGSR1010 | IGD-E SHOP DWGS - DECK SECONDARY STEEL (WEATHER DECK) | 15 | 2022-10-11 | 2022-11-01 | 2023-05-03 | 2023-05-23 | 142
0 | ECIGSR1005 | IGD-E SHOP DWGS - DECK PLATING DETAILS (CELLAR DECK) | 15 | 2022-10-25 | 2022-11-15 | 2023-05-24 | 2023-06-13 | 147
0 | ECIGSR1025 | IGD-E SHOP DWGS - VENT DRAIN FRAMING PLAN | 15 | 2022-11-01 | 2022-11-22 | 2023-05-24 | 2023-06-13 | 142
0 | ECIGSR1020 | IGD-E SHOP DWGS - DECK GRATINGS & HANDRAILS LAYOUT | 20 | 2022-10-25 | 2022-11-22 | 2023-06-22 | 2023-07-25 | 168
0 | ECIGSR1015 | IGD-E SHOP DWGS - DECK PLATING DETAILS (WEATHER DECK) | 15 | 2022-11-01 | 2022-11-22 | 2023-05-24 | 2023-06-13 | 142
0 | ECIGSR1030 | IGD-E SHOP DWGS - VENT BOOM | 15 | 2022-11-08 | 2022-11-29 | 2023-05-24 | 2023-06-13 | 137
0 | ECIGSR1035 | IGD-E SHOP DWGS - WEATHER DECK LIFTING BEAMS | 15 | 2022-11-15 | 2022-12-08 | 2023-05-24 | 2023-06-13 | 132
0 | ECIGSR1040 | IGD-E SHOP DWGS - BH-03 JACKET RISER GA AND SUPPORT DETAILS | 15 | 2022-11-29 | 2022-12-22 | 2023-05-03 | 2023-05-23 | 107
0 | ECIGSR1045 | IGD-E SHOP DWGS - JACKET NEW ANODE GA & DETAILS | 15 | 2022-12-22 | 2023-01-12 | 2023-05-24 | 2023-06-13 | 107
0 | ECIGSR1050 | IGD-E SHOP DWGS - VENT DRAIN DRUM GRATING & HANDRAILS | 15 | 2023-01-12 | 2023-02-02 | 2023-07-03 | 2023-07-24 | 117
0 | ECIGSR1055 | IGD-E SHOP DRAWINGS - J-TUBE SUPPORTS | 15 | 2023-01-25 | 2023-02-15 | 2023-07-14 | 2023-08-04 | 117
PIPING |  |  | 114 | 2022-12-09 | 2023-05-22 | 2023-03-20 | 2023-12-08 | 139
0 | ECIGPI1000 | IGD-E TOWER SHOP DWGS - PIPING SUPPORTS - CELLAR DECK | 20 | 2022-12-09 | 2023-01-06 | 2023-03-20 | 2023-04-14 | 71
0 | ECIGPI1005 | IGD-E TOWER SHOP DWGS - PIPING SUPPORTS - MAIN DECK | 20 | 2022-12-16 | 2023-01-13 | 2023-03-27 | 2023-04-25 | 71
0 | ECIGPI1010 | IGD-E TOWER SHOP DWGS - PIPING SUPPORTS - MEZZANINE DECK | 20 | 2022-12-30 | 2023-01-27 | 2023-04-10 | 2023-05-09 | 71
0 | ECIGPI1020 | IGD-E TOWER SHOP DWGS - PIPING ISOMETRICS - (CS/LTCS/ CLADDED) | 15 | 2023-01-19 | 2023-02-09 | 2023-07-26 | 2023-08-15 | 128
0 | ECIGPI1015 | IGD-E TOWER SHOP DWGS - PIPING SUPPORTS - WEATHER DECK | 20 | 2023-01-13 | 2023-02-10 | 2023-04-26 | 2023-05-23 | 71
0 | ECIGPI1025 | IGD-E TOWER SHOP DWGS - PIPING ISOMETRICS - (CU-NI) | 15 | 2023-02-09 | 2023-03-02 | 2023-08-16 | 2023-09-05 | 128
0 | ECIGPI1030 | IGD-E TOWER SHOP DWGS - PIPING ISOMETRICS - (INCONEL) | 15 | 2023-02-23 | 2023-03-16 | 2023-08-30 | 2023-09-19 | 128
0 | ECIGPI1035 | IGD-E TOWER SHOP DWGS - PIPING ISOMETRICS (SS/DUPLEX) | 15 | 2023-03-09 | 2023-03-30 | 2023-09-13 | 2023-10-04 | 128
0 | ECIGPI1040 | IGD-E TOWER PIPING HYDROTEST PACKS | 25 | 2023-04-13 | 2023-05-22 | 2023-11-03 | 2023-12-08 | 139
ELECTRICAL |  |  | 70 | 2022-11-15 | 2023-02-23 | 2023-06-09 | 2023-09-20 | 144
0 | ECIGEL1000 | IGD-E ELECTRICAL SHOP DWGS (CABLE TRAY SUPPORTS) | 35 | 2022-11-15 | 2023-01-05 | 2023-06-09 | 2023-08-02 | 144
0 | ECIGEL1010 | IGD-E ELECTRICAL - SHOP DWGS (OTHER SUPPORTS) | 35 | 2023-01-05 | 2023-02-23 | 2023-08-03 | 2023-09-20 | 144
INSTRUMENTATION / TELECOM |  |  | 72 | 2022-12-27 | 2023-04-06 | 2023-06-07 | 2023-09-20 | 114
0 | ECIGIN1000 | IGD-E INSTRUMENTATION SHOP DWGS (CABLE TRAY SUPPORTS) | 40 | 2022-12-27 | 2023-02-21 | 2023-06-07 | 2023-08-07 | 114
0 | ECIGIN1010 | IGD-E INSTRUMENTATION - SHOP DWGS (OTHER SUPPORTS) | 32 | 2023-02-21 | 2023-04-06 | 2023-08-08 | 2023-09-20 | 114
MECHANICAL |  |  | 15 | 2022-11-14 | 2022-12-07 | 2023-01-11 | 2023-01-31 | 40
0 | ECIGME1000 | IGD-E SHOP DRAWINGS - VENT DRAIN DRUM | 15 | 2022-11-14 | 2022-12-07 | 2023-01-11 | 2023-01-31 | 40
NAVAL ARCHITECTURE / INSTALLATION |  |  | 44 | 2023-07-18 | 2023-09-19 | 2023-10-30 | 2023-12-29 | 72
DOCUMENTS |  |  | 40 | 2023-07-25 | 2023-09-19 | 2023-11-03 | 2023-12-29 | 72
0 | ECIDNA1010 | IGD-E TOPSIDE -BOLLARD PULL CALCULATION - ICR/IFA | 10 | 2023-07-25 | 2023-08-08 | 2023-11-03 | 2023-11-16 | 72
0 | ECIDNA1000 | IGD-E TOPSIDE -STABILITY ANALYSIS DURING TRANSPORTATION - ICR/IFA | 10 | 2023-07-25 | 2023-08-08 | 2023-11-03 | 2023-11-16 | 72
0 | ECIDNA1015 | IGD-E TOPSIDE -BOLLARD PULL CALCULATION - IFC | 10 | 2023-08-22 | 2023-09-05 | 2023-12-04 | 2023-12-15 | 72
0 | ECIDNA1005 | IGD-E TOPSIDE -STABILITY ANALYSIS DURING TRANSPORTATION - IFC | 10 | 2023-09-05 | 2023-09-19 | 2023-12-18 | 2023-12-29 | 72
DRAWINGS |  |  | 31 | 2023-07-18 | 2023-08-31 | 2023-10-30 | 2023-12-29 | 85
0 | ECIGNA1000 | IGD-E TOPSIDE -LOADOUT ARRANGEMENT - ICR/IFA | 7 | 2023-07-18 | 2023-07-28 | 2023-10-30 | 2023-11-07 | 72
0 | ECIGNA1010 | IGD-E TOPSIDE -INSTALLATION STUDIES DRAWING - ICR/IFA | 7 | 2023-07-26 | 2023-08-04 | 2023-11-06 | 2023-11-14 | 72
0 | ECIGNA1020 | IGD-E TOPSIDE -DEMOLITION STUDIES DRAWING - ICR/IFA | 7 | 2023-07-27 | 2023-08-07 | 2023-11-07 | 2023-11-15 | 72
0 | ECIGNA1030 | IGD-E TOPSIDE -CARGO BARGE ARRANGEMENT & SEAFASTENING DETAILS - ICR/IFA | 7 | 2023-07-28 | 2023-08-08 | 2023-11-08 | 2023-11-16 | 72
0 | ECIGNA1040 | IGD-E TOPSIDE -SLING LAYING ARRANGEMENT - ICR/IFA | 7 | 2023-08-01 | 2023-08-10 | 2023-11-29 | 2023-12-08 | 85
0 | ECIGNA1005 | IGD-E TOPSIDE -LOADOUT ARRANGEMENT - IFC | 5 | 2023-08-11 | 2023-08-18 | 2023-12-25 | 2023-12-29 | 94
0 | ECIGNA1015 | IGD-E TOPSIDE -INSTALLATION STUDIES DRAWING - IFC | 5 | 2023-08-15 | 2023-08-22 | 2023-12-25 | 2023-12-29 | 92
0 | ECIGNA1025 | IGD-E TOPSIDE -DEMOLITION STUDIES DRAWING - IFC | 5 | 2023-08-21 | 2023-08-28 | 2023-12-25 | 2023-12-29 | 88
0 | ECIGNA1035 | IGD-E TOPSIDE -CARGO BARGE ARRANGEMENT & SEAFASTENING DETAILS - IFC | 5 | 2023-08-22 | 2023-08-29 | 2023-12-25 | 2023-12-29 | 87
0 | ECIGNA1045 | IGD-E TOPSIDE -SLING LAYING ARRANGEMENT - IFC | 5 | 2023-08-24 | 2023-08-31 | 2023-12-25 | 2023-12-29 | 85
PIPELINES & RISERS |  |  | 59 | 2022-10-24 | 2023-01-17 | 2023-02-21 | 2023-09-29 | 177
PIPELINES |  |  | 59 | 2022-10-24 | 2023-01-17 | 2023-02-21 | 2023-09-29 | 177
0 | CEP1PL1000 | PIPELINE INSTALLATION ANALYSIS | 20 | 2022-10-24 | 2022-11-21 | 2023-02-21 | 2023-03-20 | 84
0 | CEP1PL1010 | PIPELINE STACKING ANALYSIS | 20 | 2022-10-31 | 2022-11-28 | 2023-03-07 | 2023-04-03 | 89
0 | CEP1PL1060 | PIPELINE PULL HEAD DESIGN | 15 | 2022-11-14 | 2022-12-07 | 2023-03-21 | 2023-04-10 | 89
0 | CEP1PL1050 | PIPELINE STARTUP / LAYDOWN HEAD DESIGN | 15 | 2022-11-14 | 2022-12-07 | 2023-03-21 | 2023-04-10 | 89
0 | CEP1PL1020 | PIPELINES SEA FASTENING DESIGN REPORT/DRAWINGS | 12 | 2022-11-21 | 2022-12-09 | 2023-03-21 | 2023-04-05 | 84
0 | CEP1PL1090 | PIPELINE - LOADING ARRANGEMENT & SEA FASTENING | 12 | 2022-11-28 | 2022-12-16 | 2023-03-28 | 2023-04-12 | 84
0 | CEP1PL1070 | SHOP DRAWINGS FOR CONSTRUCTION AIDS | 20 | 2022-11-21 | 2022-12-21 | 2023-03-28 | 2023-04-26 | 89
0 | CEP1PL1030 | RISER / SPOOL SHOP DRAWINGS | 10 | 2022-12-09 | 2022-12-22 | 2023-06-20 | 2023-07-07 | 136
0 | CEP1PL1100 | PIPELINE - TRANSPORTATION STABILITY ANALYSIS | 12 | 2022-12-07 | 2022-12-23 | 2023-04-04 | 2023-04-19 | 84
0 | CEP1PL1110 | PIPELINE - MOORING ANALYSIS | 12 | 2022-12-14 | 2022-12-30 | 2023-04-11 | 2023-04-28 | 84
0 | CEP1PL1040 | DAVIT LIFT ANALYSIS FOR RISER INSTALLATION | 16 | 2022-12-19 | 2023-01-09 | 2023-08-18 | 2023-09-08 | 168
0 | CEP1PL1080 | PIPELINES HYDRO TESTING DRAWING | 12 | 2022-12-30 | 2023-01-17 | 2023-09-13 | 2023-09-29 | 177
RISERS |  |  | 20 | 2022-12-19 | 2023-01-13 | 2023-08-18 | 2023-09-14 | 168
0 | CEP1PL1150 | RISER - INSTALLATION MOORING ANALYSIS | 20 | 2022-12-19 | 2023-01-13 | 2023-08-18 | 2023-09-14 | 168
0 | CEP1PL1140 | RISER/SPOOL - LIFTING & INSTALLATION DRAWINGS | 20 | 2022-12-19 | 2023-01-13 | 2023-08-18 | 2023-09-14 | 168
0 | CEP1PL1130 | RISERS - TRANSPORTATION STABILITY ANALYSIS | 20 | 2022-12-19 | 2023-01-13 | 2023-08-18 | 2023-09-14 | 168
0 | CEP1PL1120 | RISERS - LOADING ARRANGEMENT & SEA FASTENING | 20 | 2022-12-19 | 2023-01-13 | 2023-08-18 | 2023-09-14 | 168
PROCUREMENT SERVICES |  |  | 580 | 2022-01-25 | 2023-08-28 | 2022-04-12 | 2024-03-04 | 190
EQUIPMENT / TAGGED ITEMS |  |  | 502 | 2022-03-18 | 2023-08-02 | 2022-05-20 | 2024-01-22 | 174
EQUIPMENT - ROTATING / PACKAGES |  |  | 502 | 2022-03-18 | 2023-08-02 | 2022-05-20 | 2024-01-20 | 172
POSITIVE DISPLACEMENT PUMPS |  |  | 444 | 2022-03-18 | 2023-06-05 | 2022-05-20 | 2023-11-02 | 151
0 | PPEQME1000 | PREPARE RFQ & FLOAT ENQUIRY - POSITIVE DISPLACEMENT PUMPS | 3 | 2022-03-18 | 2022-03-23 | 2022-05-20 | 2022-05-24 | 42
0 | PPEQME1005 | RECEIVE OFFERS - POSITIVE DISPLACEMENT PUMPS | 7 | 2022-03-23 | 2022-04-01 | 2022-05-25 | 2022-06-02 | 42
0 | PPEQME1010 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - POSITIVE DISPLACEMENT PUMPS | 10 | 2022-04-01 | 2022-04-15 | 2022-06-03 | 2022-06-16 | 42
0 | PPEQME1015 | RECEIVE TBE COMPANY APPROVAL ON TBE - POSITIVE DISPLACEMENT PUMPS | 10 | 2022-04-15 | 2022-04-29 | 2022-06-17 | 2022-06-30 | 42
0 | PPEQME1020 | COMPLETE CBE / ISSUE ROA - POSITIVE DISPLACEMENT PUMPS | 1 | 2022-04-29 | 2022-05-05 | 2022-07-01 | 2022-07-01 | 42
0 | PPEQME1025 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - POSITIVE DISPLACEMENT PUMPS | 11 | 2022-05-05 | 2022-05-20 | 2022-07-04 | 2022-07-21 | 42
0 | PPEQME1027 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - POSITIVE DISPLACEMENT PUMPS | 259 | 2022-05-20 | 2023-05-29 | 2022-07-22 | 2023-07-31 | 42
0 | PMEQME2060 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE)- POSITIVE DISPLACEMENT PUMP | 7 | 2023-05-29 | 2023-06-05 | 2023-10-26 | 2023-11-02 | 150
PORTABLE BIOCIDE INJECTION PACKAGE |  |  | 370 | 2022-04-12 | 2023-04-17 | 2022-06-16 | 2023-08-01 | 106
0 | PPEQME1030 | PREPARE RFQ & FLOAT ENQUIRY - PORTABLE BIOCIDE INJECTION PACKAGE | 5 | 2022-04-12 | 2022-04-19 | 2022-06-16 | 2022-06-22 | 44
0 | PPEQME1035 | RECEIVE OFFERS - PORTABLE BIOCIDE INJECTION PACKAGE | 15 | 2022-04-19 | 2022-05-13 | 2022-06-23 | 2022-07-18 | 44
0 | PPEQME1040 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PORTABLE BIOCIDE INJECTION PACKAGE | 15 | 2022-05-13 | 2022-06-03 | 2022-07-19 | 2022-08-08 | 44
0 | PPEQME1045 | RECEIVE TBE COMPANY APPROVAL - PORTABLE BIOCIDE INJECTION PACKAGE | 10 | 2022-06-03 | 2022-06-17 | 2022-08-09 | 2022-08-22 | 44
0 | PPEQME1050 | COMPLETE CBE / ISSUE ROA - PORTABLE BIOCIDE INJECTION PACKAGE | 1 | 2022-06-17 | 2022-06-20 | 2022-08-23 | 2022-08-23 | 44
0 | PPEQME1055 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PORTABLE BIOCIDE INJECTION PACKAGE | 11 | 2022-06-20 | 2022-07-05 | 2022-08-24 | 2022-09-07 | 44
0 | PPEQME1057 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PORTABLE BIOCIDE INJECTION PACKAGE | 194 | 2022-07-05 | 2023-04-10 | 2022-10-14 | 2023-07-24 | 70
0 | PMEQME2098 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PORTABLE BIOCIDE INJECTION PACKAGE | 7 | 2023-04-10 | 2023-04-17 | 2023-07-25 | 2023-08-01 | 106
MATERIAL HANDLING EQUIPMENT |  |  | 350 | 2022-04-18 | 2023-04-03 | 2022-08-18 | 2023-08-03 | 122
0 | PPEQME1060 | PREPARE RFQ & FLOAT ENQUIRY - MATERIAL HANDLING EQUIPMENT | 5 | 2022-04-18 | 2022-04-25 | 2022-08-18 | 2022-08-24 | 82
0 | PPEQME1065 | RECEIVE OFFERS - MATERIAL HANDLING EQUIPMENT | 15 | 2022-04-25 | 2022-05-19 | 2022-08-25 | 2022-09-14 | 82
0 | PPEQME1070 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - MATERIAL HANDLING EQUIPMENT | 20 | 2022-05-19 | 2022-06-16 | 2022-09-15 | 2022-10-12 | 82
0 | PPEQME1075 | RECEIVE TBE COMPANY APPROVAL - MATERIAL HANDLING EQUIPMENT | 10 | 2022-06-16 | 2022-06-30 | 2022-10-13 | 2022-10-26 | 82
0 | PPEQME1080 | COMPLETE CBE / ISSUE ROA - MATERIAL HANDLING EQUIPMENT | 1 | 2022-06-30 | 2022-07-01 | 2022-10-27 | 2022-10-27 | 82
0 | PPEQME1085 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - MATERIAL HANDLING EQUIPMENT | 11 | 2022-07-01 | 2022-07-21 | 2022-10-28 | 2022-11-11 | 82
0 | PPEQME1087 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - MATERIAL HANDLING EQUIPMENT | 170 | 2022-07-21 | 2023-03-20 | 2022-11-14 | 2023-07-18 | 82
0 | PMEQME2132 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - MATERIAL HANDLING EQUIPMENT | 14 | 2023-03-20 | 2023-04-03 | 2023-07-20 | 2023-08-03 | 122
LIFE RAFT |  |  | 342 | 2022-08-25 | 2023-08-02 | 2022-11-29 | 2024-01-20 | 172
0 | PPEQME1090 | PREPARE RFQ & FLOAT ENQUIRY - LIFE RAFT | 5 | 2022-08-25 | 2022-09-01 | 2022-11-29 | 2022-12-07 | 68
0 | PPEQME1095 | RECEIVE OFFERS - LIFE RAFT | 20 | 2022-09-01 | 2022-09-29 | 2022-12-08 | 2023-01-04 | 68
0 | PPEQME1100 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - LIFE RAFT | 20 | 2022-09-29 | 2022-10-27 | 2023-01-05 | 2023-02-01 | 68
0 | PPEQME1105 | RECEIVE TBE COMPANY APPROVAL - LIFE RAFT | 10 | 2022-10-27 | 2022-11-10 | 2023-02-02 | 2023-02-15 | 68
0 | PPEQME1110 | COMPLETE CBE / ISSUE ROA - LIFE RAFT | 1 | 2022-11-10 | 2022-11-11 | 2023-02-16 | 2023-02-16 | 68
0 | PPEQME1115 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - LIFE RAFT | 11 | 2022-11-11 | 2022-11-28 | 2023-02-17 | 2023-03-03 | 68
0 | PPEQME1117 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - LIFE RAFT | 163 | 2022-11-28 | 2023-07-25 | 2023-05-22 | 2024-01-12 | 121
0 | PMEQME2167 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE)- LIFE RAFT | 7 | 2023-07-26 | 2023-08-02 | 2024-01-13 | 2024-01-20 | 171
EQUIPMENT - STATIC |  |  | 446 | 2022-03-18 | 2023-06-07 | 2022-05-26 | 2023-09-07 | 93
PIG LAUNCHERS AND RECEIVERS |  |  | 417 | 2022-03-18 | 2023-05-09 | 2022-05-26 | 2023-08-17 | 101
0 | PPEQME1120 | PREPARE RFQ & FLOAT ENQUIRY - PIG LAUNCHER AND RECEIVER | 3 | 2022-03-18 | 2022-03-23 | 2022-05-26 | 2022-05-30 | 46
0 | PPEQME1125 | RECEIVE OFFERS - PIG LAUNCHER AND RECEIVER | 7 | 2022-03-23 | 2022-04-01 | 2022-05-31 | 2022-06-08 | 46
0 | PPEQME1130 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIG LAUNCHER AND RECEIVER | 10 | 2022-04-01 | 2022-04-15 | 2022-06-09 | 2022-06-22 | 46
0 | PPEQME1135 | RECEIVE TBE COMPANY APPROVAL - PIG LAUNCHER AND RECEIVER | 10 | 2022-04-15 | 2022-04-29 | 2022-06-23 | 2022-07-06 | 46
0 | PPEQME1140 | COMPLETE CBE/ SUBMIT ROA TO COMPANY - PIG LAUNCHER AND RECEIVER | 1 | 2022-04-29 | 2022-05-05 | 2022-07-07 | 2022-07-07 | 46
0 | PPEQME1145 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIG LAUNCHER AND RECEIVER | 11 | 2022-05-05 | 2022-05-20 | 2022-07-13 | 2022-07-27 | 46
0 | PPEQME1147 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIG LAUNCHER AND RECEIVER | 241 | 2022-05-20 | 2023-05-03 | 2022-08-22 | 2023-08-03 | 63
0 | PMEQME2210 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - PIG LAUNCHERS AND RECEIVERS | 6 | 2023-05-03 | 2023-05-09 | 2023-08-11 | 2023-08-17 | 100
CLOSE DRAIN DRUM MATERIAL |  |  | 432 | 2022-04-01 | 2023-06-07 | 2022-06-06 | 2023-09-07 | 93
INCONEL & SS PLATES - VESSEL |  |  | 256 | 2022-04-01 | 2022-12-13 | 2022-06-06 | 2023-04-28 | 136
0 | PPEQME1157 | PREPARE RFQ & FLOAT ENQUIRY - INCONEL & SS PLATES - VESSEL | 3 | 2022-04-01 | 2022-04-06 | 2022-06-06 | 2022-06-08 | 43
0 | PPEQME1167 | RECEIVE OFFERS - INCONEL & SS PLATES - VESSEL | 7 | 2022-04-06 | 2022-04-15 | 2022-06-09 | 2022-06-17 | 43
0 | PPEQME1177 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - INCONEL & SS PLATES - VESSEL | 10 | 2022-04-15 | 2022-04-29 | 2022-06-20 | 2022-07-01 | 43
0 | PPEQME1187 | RECEIVE TBE COMPANY APPROVAL - INCONEL & SS PLATES - VESSEL | 10 | 2022-04-29 | 2022-05-18 | 2022-07-04 | 2022-07-20 | 43
0 | PPEQME1207 | COMPLETE CBE/ SUBMIT ROA TO COMPANY - INCONEL & SS PLATES - VESSEL | 1 | 2022-05-18 | 2022-05-19 | 2022-07-21 | 2022-07-21 | 43
0 | PPEQME1197 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - INCONEL & SS PLATES - VESSEL | 11 | 2022-05-19 | 2022-06-03 | 2022-07-22 | 2022-08-05 | 43
0 | PPEQME1217 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - INCONEL & SS PLATES - VESSEL | 125 | 2022-06-03 | 2022-11-30 | 2022-10-26 | 2023-04-20 | 100
0 | PMEQME2220 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - INCONEL & SS PLATES - VESSEL | 6 | 2022-12-07 | 2022-12-13 | 2023-04-22 | 2023-04-28 | 136
DISHED HEAD - VESSEL |  |  | 251 | 2022-04-08 | 2022-12-15 | 2022-07-14 | 2023-04-28 | 134
0 | PPEQME1227 | PREPARE RFQ & FLOAT ENQUIRY - DISHED HEAD - VESSEL | 3 | 2022-04-08 | 2022-04-13 | 2022-07-14 | 2022-07-18 | 63
0 | PPEQME1237 | RECEIVE OFFERS - DISHED HEAD - VESSEL | 7 | 2022-04-13 | 2022-04-22 | 2022-07-19 | 2022-07-27 | 63
0 | PPEQME1247 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - DISHED HEAD - VESSEL | 10 | 2022-04-22 | 2022-05-11 | 2022-07-28 | 2022-08-10 | 63
0 | PPEQME1257 | RECEIVE TBE COMPANY APPROVAL - DISHED HEAD - VESSEL | 10 | 2022-05-11 | 2022-05-25 | 2022-08-11 | 2022-08-24 | 63
0 | PPEQME1277 | COMPLETE CBE/ SUBMIT ROA TO COMPANY - DISHED HEAD - VESSEL | 1 | 2022-05-25 | 2022-05-26 | 2022-08-25 | 2022-08-25 | 63
0 | PPEQME1267 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - DISHED HEAD - VESSEL | 11 | 2022-05-26 | 2022-06-10 | 2022-08-26 | 2022-09-09 | 63
0 | PPEQME1287 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - DISHED HEAD - VESSEL | 120 | 2022-06-10 | 2022-11-30 | 2022-11-02 | 2023-04-20 | 100
0 | PMEQME2230 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - DISHED HEAD - VESSEL | 6 | 2022-12-09 | 2022-12-15 | 2023-04-22 | 2023-04-28 | 134
NAME PLATE - VESSEL |  |  | 251 | 2022-09-29 | 2023-06-07 | 2023-01-18 | 2023-09-07 | 93
0 | PPEQME1297 | PREPARE RFQ & FLOAT ENQUIRY - NAME PLATE - VESSEL | 3 | 2022-09-29 | 2022-10-04 | 2023-01-18 | 2023-01-20 | 77
0 | PPEQME1307 | RECEIVE OFFERS - NAME PLATE - VESSEL | 7 | 2022-10-04 | 2022-10-13 | 2023-01-23 | 2023-01-31 | 77
0 | PPEQME1317 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - NAME PLATE - VESSEL | 10 | 2022-10-13 | 2022-10-27 | 2023-03-15 | 2023-03-28 | 107
0 | PPEQME1327 | RECEIVE TBE COMPANY APPROVAL - NAME PLATE - VESSEL | 10 | 2022-10-27 | 2022-11-10 | 2023-03-29 | 2023-04-11 | 107
0 | PPEQME1347 | COMPLETE CBE/ SUBMIT ROA TO COMPANY - NAME PLATE - VESSEL | 1 | 2022-11-10 | 2022-11-11 | 2023-04-12 | 2023-04-12 | 107
0 | PPEQME1337 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - NAME PLATE - VESSEL | 10 | 2023-01-19 | 2023-02-02 | 2023-04-13 | 2023-04-28 | 60
0 | PPEQME1357 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - NAME PLATE - VESSEL | 80 | 2023-02-02 | 2023-05-29 | 2023-05-09 | 2023-09-01 | 66
0 | PMEQME2240 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - NAME PLATE - VESSEL | 6 | 2023-06-01 | 2023-06-07 | 2023-09-01 | 2023-09-07 | 92
INSTRUMENTATION |  |  | 491 | 2022-03-23 | 2023-07-27 | 2022-06-03 | 2024-01-22 | 180
ICSS |  |  | 475 | 2022-04-08 | 2023-07-27 | 2022-06-16 | 2023-12-26 | 152
0 | PPEQIN1000 | PREPARE RFQ & FLOAT ENQUIRY - ICSS | 1 | 2022-04-08 | 2022-04-11 | 2022-06-16 | 2022-06-16 | 46
0 | PPEQIN1005 | RECEIVE OFFERS - ICSS | 1 | 2022-04-11 | 2022-04-12 | 2022-06-17 | 2022-06-17 | 46
0 | PPEQIN1010 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - ICSS | 3 | 2022-04-12 | 2022-04-15 | 2022-06-20 | 2022-06-22 | 46
0 | PPEQIN1015 | RECEIVE TBE COMPANY APPROVAL - ICSS | 10 | 2022-04-15 | 2022-04-29 | 2022-06-23 | 2022-07-06 | 46
0 | PPEQIN1020 | COMPLETE CBE / ISSUE ROA - ICSS | 1 | 2022-04-29 | 2022-05-05 | 2022-07-07 | 2022-07-07 | 46
0 | PPEQIN1025 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - ICSS | 11 | 2022-05-05 | 2022-05-20 | 2022-07-13 | 2022-07-27 | 46
0 | PPEQIN1027 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - ICSS | 284 | 2022-05-20 | 2023-07-06 | 2022-10-27 | 2023-12-12 | 111
0 | PMEQIN2420 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - ICSS | 7 | 2023-07-20 | 2023-07-27 | 2023-12-19 | 2023-12-26 | 152
IRCD SKID |  |  | 406 | 2022-04-15 | 2023-05-26 | 2022-06-21 | 2023-09-21 | 118
0 | PPBKIN1330 | PREPARE RFQ & FLOAT ENQUIRY - IRCD SKID | 2 | 2022-04-15 | 2022-04-19 | 2022-06-21 | 2022-06-22 | 44
0 | PPBKIN1335 | RECEIVE OFFERS - IRCD SKID | 15 | 2022-04-19 | 2022-05-13 | 2022-06-23 | 2022-07-18 | 44
0 | PPBKIN1340 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - IRCD SKID | 15 | 2022-05-13 | 2022-06-03 | 2022-07-19 | 2022-08-08 | 44
0 | PPBKIN1345 | RECEIVE TBE COMPANY APPROVAL- IRCD SKID | 10 | 2022-06-03 | 2022-06-17 | 2022-08-09 | 2022-08-22 | 44
0 | PPBKIN1350 | COMPLETE CBE / ISSUE ROA - IRCD SKID | 1 | 2022-06-17 | 2022-06-20 | 2022-08-23 | 2022-08-23 | 44
0 | PPBKIN1355 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER- IRCD SKID | 11 | 2022-06-20 | 2022-07-05 | 2022-08-24 | 2022-09-07 | 44
0 | PPBKIN1357 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY- IRCD SKID | 221 | 2022-07-05 | 2023-05-19 | 2022-09-21 | 2023-08-07 | 53
0 | PMBKIN2930 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - IRCD SKID | 7 | 2023-05-19 | 2023-05-26 | 2023-09-14 | 2023-09-21 | 118
HIPPS |  |  | 460 | 2022-03-25 | 2023-06-28 | 2022-06-03 | 2023-11-27 | 152
0 | PPEQIN1030 | PREPARE RFQ & FLOAT ENQUIRY - HIPPS | 3 | 2022-03-25 | 2022-03-30 | 2022-06-03 | 2022-06-07 | 47
0 | PPEQIN1035 | RECEIVE OFFERS - HIPPS | 15 | 2022-03-30 | 2022-04-20 | 2022-06-08 | 2022-06-28 | 47
0 | PPEQIN1040 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - HIPPS | 18 | 2022-04-20 | 2022-05-19 | 2022-06-29 | 2022-07-27 | 47
0 | PPEQIN1045 | RECEIVE TBE COMPANY APPROVAL - HIPPS | 10 | 2022-05-19 | 2022-06-02 | 2022-07-28 | 2022-08-10 | 47
0 | PPEQIN1050 | COMPLETE CBE / ISSUE ROA - HIPPS | 1 | 2022-06-02 | 2022-06-03 | 2022-08-11 | 2022-08-11 | 47
0 | PPEQIN1055 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - HIPPS | 11 | 2022-06-03 | 2022-06-20 | 2022-08-12 | 2022-08-26 | 47
0 | PPEQIN1057 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - HIPPS | 255 | 2022-06-20 | 2023-06-21 | 2022-11-08 | 2023-11-10 | 98
0 | PMEQIN2410 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - HIPPS | 7 | 2023-06-21 | 2023-06-28 | 2023-11-20 | 2023-11-27 | 152
WELLHEAD CONTROL PANEL |  |  | 461 | 2022-03-23 | 2023-06-27 | 2022-06-10 | 2023-12-09 | 166
0 | PPEQIN1060 | PREPARE RFQ & FLOAT ENQUIRY - WELLHEAD CONTROL PANEL | 3 | 2022-03-23 | 2022-03-28 | 2022-06-10 | 2022-06-14 | 54
0 | PPEQIN1065 | RECEIVE OFFERS - WELLHEAD CONTROL PANEL | 15 | 2022-03-28 | 2022-04-18 | 2022-06-15 | 2022-07-05 | 54
0 | PPEQIN1070 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - WELLHEAD CONTROL PANEL | 20 | 2022-04-18 | 2022-05-19 | 2022-07-06 | 2022-08-05 | 54
0 | PPEQIN1075 | RECEIVE TBE COMPANY APPROVAL - WELLHEAD CONTROL PANEL | 10 | 2022-05-19 | 2022-06-02 | 2022-08-08 | 2022-08-19 | 54
0 | PPEQIN1080 | COMPLETE CBE / ISSUE ROA - WELLHEAD CONTROL PANEL | 1 | 2022-06-02 | 2022-06-03 | 2022-08-22 | 2022-08-22 | 54
0 | PPEQIN1085 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - WELLHEAD CONTROL PANEL | 11 | 2022-06-03 | 2022-06-20 | 2022-08-23 | 2022-09-06 | 54
0 | PPEQIN1087 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - WELLHEAD CONTROL PANEL | 254 | 2022-06-20 | 2023-06-20 | 2022-09-20 | 2023-09-20 | 63
0 | PMEQIN2400 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - WELLHEAD CONTROL PANEL | 7 | 2023-06-20 | 2023-06-27 | 2023-12-02 | 2023-12-09 | 165
ACTUATED ON/OFF VALVES |  |  | 428 | 2022-04-13 | 2023-06-15 | 2022-06-16 | 2024-01-22 | 222
0 | PPEQIN1090 | PREPARE RFQ & FLOAT ENQUIRY - ACTUATED ON/OFF VALVES | 5 | 2022-04-13 | 2022-04-20 | 2022-06-16 | 2022-06-22 | 43
0 | PPEQIN1095 | RECEIVE OFFERS - ACTUATED ON/OFF VALVES | 15 | 2022-04-20 | 2022-05-16 | 2022-06-23 | 2022-07-18 | 43
0 | PPEQIN1100 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - ACTUATED ON/OFF VALVES | 15 | 2022-05-16 | 2022-06-06 | 2022-07-19 | 2022-08-08 | 43
0 | PPEQIN1105 | RECEIVE TBE COMPANY APPROVAL - ACTUATED ON/OFF VALVES | 10 | 2022-06-06 | 2022-06-20 | 2022-08-09 | 2022-08-22 | 43
0 | PPEQIN1110 | COMPLETE CBE / ISSUE ROA - ACTUATED ON/OFF VALVES | 1 | 2022-06-20 | 2022-06-21 | 2022-08-23 | 2022-08-23 | 43
0 | PPEQIN1115 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - ACTUATED ON/OFF VALVES | 11 | 2022-06-21 | 2022-07-06 | 2022-08-24 | 2022-09-07 | 43
0 | PPEQIN1117 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - ACTUATED ON/OFF VALVES | 234 | 2022-07-06 | 2023-06-08 | 2022-09-29 | 2023-09-01 | 58
0 | PMEQIN2390 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE)- ACTUATED ON/OFF VALVES | 7 | 2023-06-08 | 2023-06-15 | 2024-01-15 | 2024-01-22 | 221
MOTOR OPERATED VALVES (BALL TYPE) |  |  | 453 | 2022-04-13 | 2023-07-10 | 2022-06-16 | 2024-01-22 | 197
0 | PPEQIN1120 | PREPARE RFQ & FLOAT ENQUIRY - MOTOR OPERATED VALVES (BALL TYPE) | 5 | 2022-04-13 | 2022-04-20 | 2022-06-16 | 2022-06-22 | 43
0 | PPEQIN1125 | RECEIVE OFFERS - MOTOR OPERATED VALVES (BALL TYPE) | 15 | 2022-04-20 | 2022-05-16 | 2022-06-23 | 2022-07-18 | 43
0 | PPEQIN1130 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - MOTOR OPERATED VALVES (BALL TYPE) | 15 | 2022-05-16 | 2022-06-06 | 2022-07-19 | 2022-08-08 | 43
0 | PPEQIN1135 | RECEIVE TBE COMPANY APPROVAL - MOTOR OPERATED VALVES (BALL TYPE) | 10 | 2022-06-06 | 2022-06-20 | 2022-08-09 | 2022-08-22 | 43
0 | PPEQIN1140 | COMPLETE CBE / ISSUE ROA - MOTOR OPERATED VALVES (BALL TYPE) | 1 | 2022-06-20 | 2022-06-21 | 2022-08-23 | 2022-08-23 | 43
0 | PPEQIN1145 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - MOTOR OPERATED VALVES (BALL TYPE) | 11 | 2022-06-21 | 2022-07-06 | 2022-08-24 | 2022-09-07 | 43
0 | PPEQIN1147 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - MOTOR OPERATED VALVES (BALL TYPE) | 248 | 2022-07-06 | 2023-07-03 | 2022-09-09 | 2023-09-01 | 44
0 | PMEQIN2440 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - MOTOR OPERATED VALVES (BALL TYPE) | 7 | 2023-07-03 | 2023-07-10 | 2024-01-15 | 2024-01-22 | 196
MOTOR OPERATED VALVES (IDBB TYPE) |  |  | 446 | 2022-04-13 | 2023-07-03 | 2022-06-16 | 2024-01-22 | 204
0 | PPEQIN1150 | PREPARE RFQ & FLOAT ENQUIRY - MOTOR OPERATED VALVES (IDBB TYPE) | 5 | 2022-04-13 | 2022-04-20 | 2022-06-16 | 2022-06-22 | 43
0 | PPEQIN1155 | RECEIVE OFFERS - MOTOR OPERATED VALVES (IDBB TYPE) | 15 | 2022-04-20 | 2022-05-16 | 2022-06-23 | 2022-07-18 | 43
0 | PPEQIN1160 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - MOTOR OPERATED VALVES (IDBB TYPE) | 15 | 2022-05-16 | 2022-06-06 | 2022-07-19 | 2022-08-08 | 43
0 | PPEQIN1165 | RECEIVE TBE COMPANY APPROVAL - MOTOR OPERATED VALVES (IDBB TYPE) | 10 | 2022-06-06 | 2022-06-20 | 2022-08-09 | 2022-08-22 | 43
0 | PPEQIN1170 | COMPLETE CBE / ISSUE ROA - MOTOR OPERATED VALVES (IDBB TYPE) | 1 | 2022-06-20 | 2022-06-21 | 2022-08-23 | 2022-08-23 | 43
0 | PPEQIN1175 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - MOTOR OPERATED VALVES (IDBB TYPE) | 11 | 2022-06-21 | 2022-07-06 | 2022-08-24 | 2022-09-07 | 43
0 | PPEQIN1178 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - MOTOR OPERATED VALVES (IDBB TYPE) | 246 | 2022-07-06 | 2023-06-26 | 2022-09-13 | 2023-09-01 | 46
0 | PMEQIN2430 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - MOTOR OPERATED VALVES (IDBB TYPE) | 7 | 2023-06-26 | 2023-07-03 | 2024-01-15 | 2024-01-22 | 203
MOTORISED CHOKE VALVES |  |  | 387 | 2022-04-18 | 2023-05-10 | 2022-06-21 | 2023-11-11 | 185
0 | PPEQIN1180 | PREPARE RFQ & FLOAT ENQUIRY - MOTORISED CHOKE VALVES | 2 | 2022-04-18 | 2022-04-20 | 2022-06-21 | 2022-06-22 | 43
0 | PPEQIN1185 | RECEIVE OFFERS - MOTORISED CHOKE VALVES | 15 | 2022-04-20 | 2022-05-16 | 2022-06-23 | 2022-07-18 | 43
0 | PPEQIN1190 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - MOTORISED CHOKE VALVES | 15 | 2022-05-16 | 2022-06-06 | 2022-07-19 | 2022-08-08 | 43
0 | PPEQIN1195 | RECEIVE TBE COMPANY APPROVAL - MOTORISED CHOKE VALVES | 10 | 2022-06-06 | 2022-06-20 | 2022-08-09 | 2022-08-22 | 43
0 | PPEQIN1200 | COMPLETE CBE / ISSUE ROA - MOTORISED CHOKE VALVES | 1 | 2022-06-20 | 2022-06-21 | 2022-08-23 | 2022-08-23 | 43
0 | PPEQIN1205 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - MOTORISED CHOKE VALVES | 11 | 2022-06-21 | 2022-07-06 | 2022-08-24 | 2022-09-07 | 43
0 | PPEQIN1207 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - MOTORISED CHOKE VALVES | 208 | 2022-07-06 | 2023-05-03 | 2022-11-04 | 2023-09-01 | 84
0 | PMEQIN2380 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE)- MOTORISED CHOKE VALVES | 7 | 2023-05-03 | 2023-05-10 | 2023-11-04 | 2023-11-11 | 185
WET GAS FLOW METER |  |  | 367 | 2022-04-15 | 2023-04-17 | 2022-06-20 | 2023-08-07 | 112
0 | PPEQIN1210 | PREPARE RFQ & FLOAT ENQUIRY - WET GAS FLOW METER | 3 | 2022-04-15 | 2022-04-20 | 2022-06-20 | 2022-06-22 | 43
0 | PPEQIN1215 | RECEIVE OFFERS - WET GAS FLOW METER | 15 | 2022-04-20 | 2022-05-16 | 2022-06-23 | 2022-07-18 | 43
0 | PPEQIN1220 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - WET GAS FLOW METER | 15 | 2022-05-16 | 2022-06-06 | 2022-07-19 | 2022-08-08 | 43
0 | PPEQIN1225 | RECEIVE TBE COMPANY APPROVAL - WET GAS FLOW METER | 10 | 2022-06-06 | 2022-06-20 | 2022-08-09 | 2022-08-22 | 43
0 | PPEQIN1230 | COMPLETE CBE / ISSUE ROA - WET GAS FLOW METER | 1 | 2022-06-20 | 2022-06-21 | 2022-08-23 | 2022-08-23 | 43
0 | PPEQIN1235 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - WET GAS FLOW METER | 11 | 2022-06-21 | 2022-07-06 | 2022-08-24 | 2022-09-07 | 43
0 | PPEQIN1237 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - WET GAS FLOW METER | 193 | 2022-07-06 | 2023-04-10 | 2022-10-21 | 2023-07-28 | 74
0 | PMEQIN2370 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE- WET GAS FLOW METER | 7 | 2023-04-10 | 2023-04-17 | 2023-07-31 | 2023-08-07 | 112
SUBSEA FO CABLE |  |  | 356 | 2022-04-19 | 2023-04-10 | 2022-06-23 | 2023-06-16 | 68
0 | PPEQIN1245 | PREPARE RFQ & FLOAT ENQUIRY - SUBSEA FO CABLE | 5 | 2022-04-19 | 2022-04-26 | 2022-06-23 | 2022-06-29 | 44
0 | PPEQIN1250 | RECEIVE OFFERS - SUBSEA FO CABLE | 15 | 2022-04-26 | 2022-05-20 | 2022-06-30 | 2022-07-25 | 44
0 | PPEQIN1255 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - SUBSEA FO CABLE | 20 | 2022-05-20 | 2022-06-17 | 2022-07-26 | 2022-08-22 | 44
0 | PPEQIN1260 | RECEIVE TBE COMPANY APPROVAL - SUBSEA FO CABLE | 10 | 2022-06-17 | 2022-07-01 | 2022-08-23 | 2022-09-05 | 44
0 | PPEQIN1240 | COMPLETE CBE / ISSUE ROA - SUBSEA FO CABLE | 1 | 2022-07-01 | 2022-07-04 | 2022-09-06 | 2022-09-06 | 44
0 | PPEQIN1265 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - SUBSEA FO CABLE | 11 | 2022-07-04 | 2022-07-22 | 2022-09-07 | 2022-09-21 | 44
0 | PPEQIN1275 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - SUBSEA FO CABLE | 179 | 2022-07-22 | 2023-04-03 | 2022-09-22 | 2023-06-05 | 44
0 | PMEQIN2360 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - SUBSEA FO CABLE | 7 | 2023-04-03 | 2023-04-10 | 2023-06-09 | 2023-06-16 | 67
ELECTRICAL |  |  | 431 | 2022-04-07 | 2023-06-12 | 2022-06-13 | 2023-12-08 | 179
6.6kV RING MAIN UNIT (RMU) |  |  | 431 | 2022-04-07 | 2023-06-12 | 2022-06-13 | 2023-11-25 | 166
0 | PPEQEL1030 | PREPARE RFQ & FLOAT ENQUIRY - 6.6KV RING MAIN UNIT(RMU) | 3 | 2022-04-07 | 2022-04-12 | 2022-06-13 | 2022-06-15 | 44
0 | PPEQEL1035 | RECEIVE OFFERS - 6.6KV RING MAIN UNIT(RMU) | 15 | 2022-04-12 | 2022-05-06 | 2022-06-16 | 2022-07-06 | 44
0 | PPEQEL1040 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - 6.6KV RING MAIN UNIT(RMU) | 20 | 2022-05-06 | 2022-06-03 | 2022-07-07 | 2022-08-08 | 44
0 | PPEQEL1045 | RECEIVE TBE COMPANY APPROVAL - 6.6KV RING MAIN UNIT(RMU) | 10 | 2022-06-03 | 2022-06-17 | 2022-08-09 | 2022-08-22 | 44
0 | PPEQEL1050 | COMPLETE CBE / ISSUE ROA - 6.6KV RING MAIN UNIT(RMU) | 1 | 2022-06-17 | 2022-06-20 | 2022-08-23 | 2022-08-23 | 44
0 | PPEQEL1055 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - 6.6KV RING MAIN UNIT(RMU) | 11 | 2022-06-20 | 2022-07-05 | 2022-08-24 | 2022-09-07 | 44
0 | PPEQEL1057 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - 6.6KV RING MAIN UNIT(RMU) | 232 | 2022-07-05 | 2023-06-05 | 2022-10-24 | 2023-09-22 | 76
0 | PMEQEL2390 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - 6.6kV RING MAIN UNIT (RMU) | 7 | 2023-06-05 | 2023-06-12 | 2023-11-18 | 2023-11-25 | 166
415V SWITCHBOARDS |  |  | 357 | 2022-04-12 | 2023-04-04 | 2022-06-16 | 2023-11-22 | 232
0 | PPEQEL1060 | PREPARE RFQ & FLOAT ENQUIRY - 415V SWITCHBOARDS | 5 | 2022-04-12 | 2022-04-19 | 2022-06-16 | 2022-06-22 | 44
0 | PPEQEL1065 | RECEIVE OFFERS - 415V SWITCHBOARDS | 15 | 2022-04-19 | 2022-05-13 | 2022-06-23 | 2022-07-18 | 44
0 | PPEQEL1070 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - 415V SWITCHBOARDS | 15 | 2022-05-13 | 2022-06-03 | 2022-07-19 | 2022-08-08 | 44
0 | PPEQEL1075 | RECEIVE TBE COMPANY APPROVAL - 415V SWITCHBOARDS | 10 | 2022-06-03 | 2022-06-17 | 2022-08-09 | 2022-08-22 | 44
0 | PPEQEL1080 | COMPLETE CBE / ISSUE ROA - 415V SWITCHBOARDS | 1 | 2022-06-17 | 2022-06-20 | 2022-08-23 | 2022-08-23 | 44
0 | PPEQEL1085 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - 415V SWITCHBOARDS | 11 | 2022-06-20 | 2022-07-05 | 2022-08-24 | 2022-09-07 | 44
0 | PPEQEL1087 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - 415V SWITCHBOARDS | 174 | 2022-07-05 | 2023-03-13 | 2023-01-03 | 2023-09-11 | 125
0 | PMEQEL2380 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - 415V SWITCHBOARDS | 7 | 2023-03-28 | 2023-04-04 | 2023-11-15 | 2023-11-22 | 232
6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS |  |  | 396 | 2022-04-08 | 2023-05-09 | 2022-06-17 | 2023-12-08 | 213
0 | PPEQEL1090 | PREPARE RFQ & FLOAT ENQUIRY - 6.6/ 0.433 KV DISTRIBUTION TRANSFORMERS | 4 | 2022-04-08 | 2022-04-14 | 2022-06-17 | 2022-06-22 | 47
0 | PPEQEL1095 | RECEIVE OFFERS - 6.6/ 0.433 KV DISTRIBUTION TRANSFORMERS | 15 | 2022-04-14 | 2022-05-10 | 2022-06-23 | 2022-07-18 | 47
0 | PPEQEL1100 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL 6.6/ 0.433 KV DISTRIBUTION TRANSF'R | 15 | 2022-05-10 | 2022-05-31 | 2022-07-19 | 2022-08-08 | 47
0 | PPEQEL1105 | RECEIVE TBE COMPANY APPROVAL - 6.6/ 0.433 KV DISTRIBUTION TRANSFORMERS | 10 | 2022-05-31 | 2022-06-14 | 2022-08-09 | 2022-08-22 | 47
0 | PPEQEL1110 | COMPLETE CBE / ISSUE ROA - 6.6/ 0.433 KV DISTRIBUTION TRANSFORMERS | 1 | 2022-06-14 | 2022-06-15 | 2022-08-23 | 2022-08-23 | 47
0 | PPEQEL1115 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - 6.6/ 0.433 KV DISTRIBUTION TRANSFORMERS | 11 | 2022-06-15 | 2022-06-30 | 2022-08-24 | 2022-09-07 | 47
0 | PPEQEL1117 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - 6.6/ 0.433 KV DISTRIBUTION TRANSFORMERS | 199 | 2022-06-30 | 2023-04-12 | 2022-12-12 | 2023-09-22 | 112
0 | PMEQEL2370 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - 6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS | 7 | 2023-05-02 | 2023-05-09 | 2023-12-01 | 2023-12-08 | 213
24V DC UPS |  |  | 415 | 2022-04-13 | 2023-06-02 | 2022-06-20 | 2023-11-17 | 168
0 | PPEQEL1120 | PREPARE RFQ & FLOAT ENQUIRY - 24V DC UPS | 3 | 2022-04-13 | 2022-04-18 | 2022-06-20 | 2022-06-22 | 45
0 | PPEQEL1125 | RECEIVE OFFERS - 24V DC UPS | 15 | 2022-04-18 | 2022-05-12 | 2022-06-23 | 2022-07-18 | 45
0 | PPEQEL1130 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - 24V DC UPS | 15 | 2022-05-12 | 2022-06-02 | 2022-07-19 | 2022-08-08 | 45
0 | PPEQEL1135 | RECEIVE TBE COMPANY APPROVAL - 24V DC UPS | 10 | 2022-06-02 | 2022-06-16 | 2022-08-09 | 2022-08-22 | 45
0 | PPEQEL1140 | COMPLETE CBE / ISSUE ROA - 24V DC UPS | 1 | 2022-06-16 | 2022-06-17 | 2022-08-23 | 2022-08-23 | 45
0 | PPEQEL1145 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - 24V DC UPS | 11 | 2022-06-20 | 2022-07-05 | 2022-08-24 | 2022-09-07 | 44
0 | PPEQEL1147 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - 24V DC UPS | 226 | 2022-07-05 | 2023-05-26 | 2022-11-01 | 2023-09-22 | 82
0 | PMEQEL2360 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - 24V DC UPS | 7 | 2023-05-26 | 2023-06-02 | 2023-11-10 | 2023-11-17 | 168
NAVIGATIONAL AIDS SYSTEM |  |  | 367 | 2022-05-16 | 2023-05-18 | 2022-08-17 | 2023-11-04 | 170
0 | PPEQEL1150 | PREPARE RFQ & FLOAT ENQUIRY - NAVIGATIONAL AIDS SYSTEM | 5 | 2022-05-16 | 2022-05-23 | 2022-08-17 | 2022-08-23 | 64
0 | PPEQEL1155 | RECEIVE OFFERS - NAVIGATIONAL AIDS SYSTEM | 15 | 2022-05-23 | 2022-06-13 | 2022-08-24 | 2022-09-13 | 64
0 | PPEQEL1160 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - NAVIGATIONAL AIDS SYSTEM | 20 | 2022-06-13 | 2022-07-14 | 2022-09-15 | 2022-10-12 | 65
0 | PPEQEL1165 | RECEIVE TBE COMPANY APPROVAL - NAVIGATIONAL AIDS SYSTEM | 10 | 2022-07-14 | 2022-07-28 | 2022-10-13 | 2022-10-26 | 65
0 | PPEQEL1170 | COMPLETE CBE / ISSUE ROA - NAVIGATIONAL AIDS SYSTEM | 1 | 2022-07-28 | 2022-07-29 | 2022-10-27 | 2022-10-27 | 65
0 | PPEQEL1175 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - NAVIGATIONAL AIDS SYSTEM | 11 | 2022-07-29 | 2022-08-15 | 2022-10-28 | 2022-11-11 | 65
0 | PPEQEL1335 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - NAVIGATIONAL AIDS SYSTEM | 170 | 2022-08-15 | 2023-04-12 | 2023-01-20 | 2023-09-22 | 112
0 | PMEQEL2350 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - NAVIGATIONAL AIDS SYSTEM | 7 | 2023-05-11 | 2023-05-18 | 2023-10-28 | 2023-11-04 | 170
BIRD DETERRENT SYSTEM |  |  | 355 | 2022-05-30 | 2023-05-20 | 2022-09-13 | 2023-11-20 | 184
0 | PPEQEL1180 | PREPARE RFQ & FLOAT ENQUIRY - BIRD DETERRENT SYSTEM | 5 | 2022-05-30 | 2022-06-06 | 2022-09-13 | 2022-09-19 | 73
0 | PPEQEL1185 | RECEIVE OFFERS - BIRD DETERRENT SYSTEM | 15 | 2022-06-06 | 2022-06-27 | 2022-09-20 | 2022-10-10 | 73
0 | PPEQEL1190 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - BIRD DETERRENT SYSTEM | 20 | 2022-06-27 | 2022-07-28 | 2022-10-11 | 2022-11-07 | 73
0 | PPEQEL1195 | RECEIVE TBE COMPANY APPROVAL - BIRD DETERRENT SYSTEM | 10 | 2022-07-28 | 2022-08-11 | 2022-11-08 | 2022-11-21 | 73
0 | PPEQEL1200 | COMPLETE CBE / ISSUE ROA - BIRD DETERRENT SYSTEM | 1 | 2022-08-11 | 2022-08-12 | 2022-11-22 | 2022-11-22 | 73
0 | PPEQEL1205 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - BIRD DETERRENT SYSTEM | 11 | 2022-08-12 | 2022-08-29 | 2022-11-23 | 2022-12-09 | 73
0 | PPEQEL1207 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - BIRD DETERRENT SYSTEM | 165 | 2022-08-29 | 2023-04-19 | 2023-01-27 | 2023-09-22 | 107
0 | PMEQEL2340 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE)- BIRD DETERRENT SYSTEM | 7 | 2023-05-13 | 2023-05-20 | 2023-11-13 | 2023-11-20 | 184
LV DISTRIBUTION BOARDS |  |  | 408 | 2022-04-11 | 2023-05-24 | 2022-06-16 | 2023-11-21 | 182
0 | PPEQEL1210 | PREPARE RFQ & FLOAT ENQUIRY - LV DISTRIBUTION BOARDS | 5 | 2022-04-11 | 2022-04-18 | 2022-06-16 | 2022-06-22 | 45
0 | PPEQEL1215 | RECEIVE OFFERS - LV DISTRIBUTION BOARDS | 15 | 2022-04-18 | 2022-05-12 | 2022-06-23 | 2022-07-18 | 45
0 | PPEQEL1220 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - LV DISTRIBUTION BOARDS | 15 | 2022-05-12 | 2022-06-02 | 2022-07-19 | 2022-08-08 | 45
0 | PPEQEL1225 | RECEIVE TBE COMPANY APPROVAL - LV DISTRIBUTION BOARDS | 10 | 2022-06-02 | 2022-06-16 | 2022-08-09 | 2022-08-22 | 45
0 | PPEQEL1230 | COMPLETE CBE / ISSUE ROA - LV DISTRIBUTION BOARDS | 1 | 2022-06-16 | 2022-06-17 | 2022-08-23 | 2022-08-23 | 45
0 | PPEQEL1235 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - LV DISTRIBUTION BOARDS | 11 | 2022-06-17 | 2022-07-04 | 2022-08-24 | 2022-09-07 | 45
0 | PPEQEL1237 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - LV DISTRIBUTION BOARDS | 171 | 2022-07-04 | 2023-03-07 | 2023-01-17 | 2023-09-20 | 136
0 | PMEQEL2330 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - LV DISTRIBUTION BOARDS | 42 | 2023-04-12 | 2023-05-24 | 2023-10-10 | 2023-11-21 | 181
BULK MATERIAL |  |  | 477 | 2022-01-25 | 2023-05-17 | 2022-05-16 | 2024-01-06 | 234
STRUCTURAL |  |  | 408 | 2022-01-25 | 2023-03-09 | 2022-05-16 | 2023-11-03 | 239
CS PLATES |  |  | 220 | 2022-01-25 | 2022-09-02 | 2022-05-23 | 2023-02-09 | 160
0 | PPBKSR1000 | PREPARE RFQ & FLOAT ENQUIRY - CS PLATES | 3 | 2022-01-25 | 2022-01-28 | 2022-05-23 | 2022-05-25 | 81
0 | PPBKSR1005 | RECEIVE OFFERS - CS PLATES | 10 | 2022-01-28 | 2022-02-11 | 2022-05-26 | 2022-06-08 | 81
0 | PPBKSR1010 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - CS PLATES | 14 | 2022-02-11 | 2022-03-03 | 2022-06-09 | 2022-06-28 | 81
0 | PPBKSR1015 | RECEIVE TBE COMPANY APPROVAL - CS PLATES | 10 | 2022-03-03 | 2022-03-17 | 2022-06-29 | 2022-07-15 | 81
0 | PPBKSR1020 | COMPLETE CBE / ISSUE ROA - CS PLATES | 1 | 2022-03-17 | 2022-03-18 | 2022-07-18 | 2022-07-18 | 81
0 | PPBKSR1025 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - CS PLATES | 11 | 2022-03-18 | 2022-04-04 | 2022-07-19 | 2022-08-02 | 81
0 | PPBKSR1027 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - CS PLATES | 96 | 2022-04-04 | 2022-08-24 | 2022-08-24 | 2023-01-06 | 96
0 | PMBKSR2480 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - CS PLATES | 7 | 2022-08-26 | 2022-09-02 | 2023-02-02 | 2023-02-09 | 160
ROLLED SECTIONS |  |  | 249 | 2022-01-28 | 2022-10-04 | 2022-05-26 | 2023-02-20 | 139
0 | PPBKSR1030 | PREPARE RFQ & FLOAT ENQUIRY - ROLLED SECTIONS | 3 | 2022-01-28 | 2022-02-02 | 2022-05-26 | 2022-05-30 | 81
0 | PPBKSR1035 | RECEIVE OFFERS - ROLLED SECTIONS | 10 | 2022-02-02 | 2022-02-16 | 2022-05-31 | 2022-06-13 | 81
0 | PPBKSR1040 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL- ROLLED SECTIONS | 10 | 2022-02-17 | 2022-03-03 | 2022-06-15 | 2022-06-28 | 81
0 | PPBKSR1045 | RECEIVE TBE COMPANY APPROVAL - ROLLED SECTIONS | 10 | 2022-03-03 | 2022-03-17 | 2022-06-29 | 2022-07-15 | 81
0 | PPBKSR1050 | COMPLETE CBE / ISSUE ROA - ROLLED SECTIONS | 1 | 2022-03-17 | 2022-03-18 | 2022-07-18 | 2022-07-18 | 81
0 | PPBKSR1055 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - ROLLED SECTIONS | 11 | 2022-03-18 | 2022-04-04 | 2022-07-19 | 2022-08-02 | 81
0 | PPBKSR1057 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - ROLLED SECTIONS | 120 | 2022-04-04 | 2022-09-27 | 2022-08-25 | 2023-02-10 | 97
0 | PMBKSR2450 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE- ROLLED SECTIONS | 7 | 2022-09-27 | 2022-10-04 | 2023-02-13 | 2023-02-20 | 139
SAW TUBULAR |  |  | 257 | 2022-01-27 | 2022-10-11 | 2022-05-16 | 2023-06-23 | 255
0 | PPBKSR1060 | PREPARE RFQ & FLOAT ENQUIRY - SAW TUBULAR | 3 | 2022-01-27 | 2022-02-01 | 2022-05-16 | 2022-05-18 | 74
0 | PPBKSR1065 | RECEIVE OFFERS - SAW TUBULAR | 10 | 2022-02-01 | 2022-02-15 | 2022-05-19 | 2022-06-01 | 74
0 | PPBKSR1070 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - SAW TUBULAR | 11 | 2022-02-16 | 2022-03-03 | 2022-06-03 | 2022-06-17 | 74
0 | PPBKSR1075 | RECEIVE TBE COMPANY APPROVAL - SAW TUBULAR | 10 | 2022-03-03 | 2022-03-17 | 2022-06-20 | 2022-07-01 | 74
0 | PPBKSR1080 | COMPLETE CBE / ISSUE ROA - SAW TUBULAR | 1 | 2022-03-17 | 2022-03-18 | 2022-07-04 | 2022-07-04 | 74
0 | PPBKSR1085 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - SAW TUBULAR | 11 | 2022-03-18 | 2022-04-04 | 2022-07-05 | 2022-07-22 | 74
0 | PPBKSR1087 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - SAW TUBULAR | 125 | 2022-04-04 | 2022-10-04 | 2022-08-02 | 2023-01-25 | 80
0 | PMBKSR2470 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - SAW TUBULAR | 7 | 2022-10-04 | 2022-10-11 | 2023-06-16 | 2023-06-23 | 255
SEAMLESS TUBULAR |  |  | 256 | 2022-01-27 | 2022-10-10 | 2022-05-16 | 2023-06-23 | 256
0 | PPBKSR1090 | PREPARE RFQ & FLOAT ENQUIRY - SEAMLESS TUBULAR | 3 | 2022-01-27 | 2022-02-01 | 2022-05-16 | 2022-05-18 | 74
0 | PPBKSR1095 | RECEIVE OFFERS - SEAMLESS TUBULAR | 10 | 2022-02-01 | 2022-02-15 | 2022-05-19 | 2022-06-01 | 74
0 | PPBKSR1100 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - SEAMLESS TUBULAR | 11 | 2022-02-16 | 2022-03-03 | 2022-06-03 | 2022-06-17 | 74
0 | PPBKSR1105 | RECEIVE TBE COMPANY APPROVAL - SEAMLESS TUBULAR | 10 | 2022-03-03 | 2022-03-17 | 2022-06-20 | 2022-07-01 | 74
0 | PPBKSR1110 | COMPLETE CBE / ISSUE ROA - SEAMLESS TUBULAR | 1 | 2022-03-17 | 2022-03-18 | 2022-07-04 | 2022-07-04 | 74
0 | PPBKSR1115 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - SEAMLESS TUBULAR | 11 | 2022-03-18 | 2022-04-04 | 2022-07-05 | 2022-07-22 | 74
0 | PPBKSR1117 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - SEAMLESS TUBULAR | 124 | 2022-04-04 | 2022-10-03 | 2022-08-31 | 2023-02-22 | 101
0 | PMBKSR2460 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - SEAMLESS TUBULAR | 7 | 2022-10-03 | 2022-10-10 | 2023-06-16 | 2023-06-23 | 256
CS GRATINGS & STAIR TREADS |  |  | 307 | 2022-04-07 | 2023-02-08 | 2022-07-21 | 2023-09-20 | 224
0 | PPBKSR1120 | PREPARE RFQ & FLOAT ENQUIRY - CS GRATINGS & STAIR TREADS | 5 | 2022-04-07 | 2022-04-14 | 2022-07-21 | 2022-07-27 | 69
0 | PPBKSR1125 | RECEIVE OFFERS - CS GRATINGS & STAIR TREADS | 15 | 2022-04-14 | 2022-05-10 | 2022-07-28 | 2022-08-17 | 69
0 | PPBKSR1130 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - CS GRATINGS & STAIR TREADS | 20 | 2022-05-10 | 2022-06-07 | 2022-08-18 | 2022-09-14 | 69
0 | PPBKSR1135 | RECEIVE TBE COMPANY APPROVAL - CS GRATINGS & STAIR TREADS | 10 | 2022-06-07 | 2022-06-21 | 2022-09-15 | 2022-09-28 | 69
0 | PPBKSR1140 | COMPLETE CBE / ISSUE ROA - CS GRATINGS & STAIR TREADS | 1 | 2022-06-21 | 2022-06-22 | 2022-09-29 | 2022-09-29 | 69
0 | PPBKSR1145 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - CS GRATINGS & STAIR TREADS | 11 | 2022-06-22 | 2022-07-07 | 2022-09-30 | 2022-10-14 | 69
0 | PPBKSR1147 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - CS GRATINGS & STAIR TREADS | 144 | 2022-07-07 | 2023-02-01 | 2022-12-28 | 2023-07-25 | 119
0 | PMBKSR2440 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - CS GRATINGS & STAIR TREADS | 7 | 2023-02-01 | 2023-02-08 | 2023-09-13 | 2023-09-20 | 224
MISCELLANEOUS STRUCTURAL ITEMS |  |  | 277 | 2022-05-10 | 2023-02-11 | 2022-09-20 | 2023-06-22 | 131
0 | PPBKSR1150 | PREPARE RFQ & FLOAT ENQUIRY - MISCELLANEOUS STRUCTURAL ITEMS | 5 | 2022-05-10 | 2022-05-17 | 2022-09-20 | 2022-09-26 | 92
0 | PPBKSR1155 | RECEIVE OFFERS - MISCELLANEOUS STRUCTURAL ITEMS | 15 | 2022-05-17 | 2022-06-07 | 2022-09-27 | 2022-10-17 | 92
0 | PPBKSR1160 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - MISCELLANEOUS STRUCTURAL ITEMS | 20 | 2022-06-07 | 2022-07-05 | 2022-10-18 | 2022-11-14 | 92
0 | PPBKSR1165 | RECEIVE TBE COMPANY APPROVAL - MISCELLANEOUS STRUCTURAL ITEMS | 10 | 2022-07-05 | 2022-07-22 | 2022-11-15 | 2022-11-28 | 92
0 | PPBKSR1170 | COMPLETE CBE / ISSUE ROA - MISCELLANEOUS STRUCTURAL ITEMS | 1 | 2022-07-22 | 2022-07-25 | 2022-11-29 | 2022-11-29 | 92
0 | PPBKSR1175 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - MISCELLANEOUS STRUCTURAL ITEMS | 11 | 2022-07-25 | 2022-08-09 | 2022-11-30 | 2022-12-16 | 92
0 | PPBKSR1177 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - MISCELLANEOUS STRUCTURAL ITEMS | 125 | 2022-08-09 | 2023-02-02 | 2022-12-20 | 2023-06-14 | 93
0 | PMBKSR2490 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - MISCELLANEOUS STRUCTURAL ITEM | 7 | 2023-02-04 | 2023-02-11 | 2023-06-15 | 2023-06-22 | 131
GROUTING MATERIAL |  |  | 266 | 2022-05-17 | 2023-02-07 | 2022-08-30 | 2023-08-02 | 176
0 | PPBKSR1180 | PREPARE RFQ & FLOAT ENQUIRY - GROUTING MATERIAL | 5 | 2022-05-17 | 2022-05-24 | 2022-08-30 | 2022-09-05 | 72
0 | PPBKSR1185 | RECEIVE OFFERS- GROUTING MATERIAL | 15 | 2022-05-24 | 2022-06-14 | 2022-09-06 | 2022-09-26 | 72
0 | PPBKSR1190 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL- GROUTING MATERIAL | 20 | 2022-06-14 | 2022-07-15 | 2022-09-27 | 2022-10-24 | 72
0 | PPBKSR1195 | RECEIVE TBE COMPANY APPROVAL- GROUTING MATERIAL | 10 | 2022-07-15 | 2022-07-29 | 2022-10-25 | 2022-11-07 | 72
0 | PPBKSR1200 | COMPLETE CBE / ISSUE ROA - GROUTING MATERIAL | 1 | 2022-07-29 | 2022-08-01 | 2022-11-08 | 2022-11-08 | 72
0 | PPBKSR1205 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER- GROUTING MATERIAL | 11 | 2022-08-01 | 2022-08-16 | 2022-11-09 | 2022-11-23 | 72
0 | PPBKSR1207 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY- GROUTING MATERIAL | 118 | 2022-08-16 | 2023-01-31 | 2023-02-02 | 2023-07-25 | 120
0 | PMBKSR2400 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - GROUTING MATERIAL | 7 | 2023-01-31 | 2023-02-07 | 2023-07-26 | 2023-08-02 | 176
BOLTS, NUTS & WASHERS |  |  | 287 | 2022-04-21 | 2023-02-02 | 2022-08-10 | 2023-06-19 | 137
0 | PPBKSR1210 | PREPARE RFQ & FLOAT ENQUIRY - BOLTS, NUTS & WASHERS | 5 | 2022-04-21 | 2022-04-28 | 2022-08-10 | 2022-08-16 | 73
0 | PPBKSR1215 | RECEIVE OFFERS - BOLTS, NUTS & WASHERS | 15 | 2022-04-28 | 2022-05-24 | 2022-08-17 | 2022-09-06 | 73
0 | PPBKSR1220 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - BOLTS, NUTS & WASHERS | 20 | 2022-05-24 | 2022-06-21 | 2022-09-07 | 2022-10-04 | 73
0 | PPBKSR1225 | RECEIVE TBE COMPANY APPROVAL - BOLTS, NUTS & WASHERS | 10 | 2022-06-21 | 2022-07-05 | 2022-10-05 | 2022-10-18 | 73
0 | PPBKSR1230 | COMPLETE CBE / ISSUE ROA - BOLTS, NUTS & WASHERS | 1 | 2022-07-05 | 2022-07-06 | 2022-10-19 | 2022-10-19 | 73
0 | PPBKSR1235 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - BOLTS, NUTS & WASHERS | 11 | 2022-07-06 | 2022-07-26 | 2022-10-20 | 2022-11-03 | 73
0 | PPBKSR1237 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - BOLTS, NUTS & WASHERS | 130 | 2022-07-26 | 2023-01-26 | 2022-12-08 | 2023-06-09 | 95
0 | PMBKSR2420 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - BOLTS, NUTS & WASHERS | 7 | 2023-01-26 | 2023-02-02 | 2023-06-12 | 2023-06-19 | 137
CATHODIC PROTECTION [SACRIFICIAL ANODES] |  |  | 299 | 2022-04-14 | 2023-02-07 | 2022-08-04 | 2023-09-19 | 224
0 | PPBKSR1240 | PREPARE RFQ & FLOAT ENQUIRY - CATHODIC PROTECTION - (SACRIFICIAL ANODES) | 5 | 2022-04-14 | 2022-04-21 | 2022-08-04 | 2022-08-10 | 74
0 | PPBKSR1245 | RECEIVE OFFERS - (SACRIFICIAL ANODES) | 15 | 2022-04-21 | 2022-05-17 | 2022-08-11 | 2022-08-31 | 74
0 | PPBKSR1250 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - (SACRIFICIAL ANODES) | 20 | 2022-05-17 | 2022-06-14 | 2022-09-01 | 2022-09-28 | 74
0 | PPBKSR1255 | RECEIVE TBE COMPANY APPROVAL - (SACRIFICIAL ANODES) | 10 | 2022-06-14 | 2022-06-28 | 2022-09-29 | 2022-10-12 | 74
0 | PPBKSR1260 | COMPLETE CBE / ISSUE ROA - (SACRIFICIAL ANODES) | 1 | 2022-06-28 | 2022-06-29 | 2022-10-13 | 2022-10-13 | 74
0 | PPBKSR1265 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - (SACRIFICIAL ANODES) | 11 | 2022-06-29 | 2022-07-19 | 2022-10-14 | 2022-10-28 | 74
0 | PPBKSR1267 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - (SACRIFICIAL ANODES) | 138 | 2022-07-19 | 2023-01-31 | 2023-02-22 | 2023-09-11 | 154
0 | PMBKSR2430 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - CATHODIC PROTECTION [SACRIFICIAL ANODES] | 7 | 2023-01-31 | 2023-02-07 | 2023-09-12 | 2023-09-19 | 224
HELI DECK SAFETY NET |  |  | 315 | 2022-04-28 | 2023-03-09 | 2022-08-30 | 2023-08-31 | 175
0 | PPBKSR1270 | PREPARE RFQ & FLOAT ENQUIRY - HELIDECK SAFETY NET | 5 | 2022-04-28 | 2022-05-10 | 2022-08-30 | 2022-09-05 | 82
0 | PPBKSR1275 | RECEIVE OFFERS - HELIDECK SAFETY NET | 15 | 2022-05-10 | 2022-05-31 | 2022-09-06 | 2022-09-26 | 82
0 | PPBKSR1280 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - HELIDECK SAFETY NET | 20 | 2022-05-31 | 2022-06-28 | 2022-09-27 | 2022-10-24 | 82
0 | PPBKSR1285 | RECEIVE TBE COMPANY APPROVAL - HELIDECK SAFETY NET | 10 | 2022-06-28 | 2022-07-15 | 2022-10-25 | 2022-11-07 | 82
0 | PPBKSR1290 | COMPLETE CBE / ISSUE ROA - HELIDECK SAFETY NET | 1 | 2022-07-15 | 2022-07-18 | 2022-11-08 | 2022-11-08 | 82
0 | PPBKSR1295 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - HELIDECK SAFETY NET | 11 | 2022-07-18 | 2022-08-02 | 2022-11-09 | 2022-11-23 | 82
0 | PPBKSR1297 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - HELIDECK SAFETY NET | 148 | 2022-08-02 | 2023-02-28 | 2023-01-20 | 2023-08-23 | 121
0 | PMBKSR2410 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - HELI DECK SAFETY NET | 7 | 2023-03-02 | 2023-03-09 | 2023-08-24 | 2023-08-31 | 175
SWING ROPE ASSEMBLY |  |  | 263 | 2022-05-24 | 2023-02-11 | 2022-10-14 | 2023-11-03 | 265
0 | PPBKSR1300 | PREPARE RFQ & FLOAT ENQUIRY - SWING ROPE ASSEMBLY | 5 | 2022-05-24 | 2022-05-31 | 2022-10-14 | 2022-10-20 | 100
0 | PPBKSR1305 | RECEIVE OFFERS - SWING ROPE ASSEMBLY | 15 | 2022-05-31 | 2022-06-21 | 2022-10-21 | 2022-11-10 | 100
0 | PPBKSR1310 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - SWING ROPE ASSEMBLY | 15 | 2022-06-21 | 2022-07-15 | 2022-11-11 | 2022-12-05 | 100
0 | PPBKSR1315 | RECEIVE TBE COMPANY APPROVAL - SWING ROPE ASSEMBLY | 10 | 2022-07-15 | 2022-07-29 | 2022-12-06 | 2022-12-19 | 100
0 | PPBKSR1320 | COMPLETE CBE / ISSUE ROA - SWING ROPE ASSEMBLY | 1 | 2022-07-29 | 2022-08-01 | 2022-12-20 | 2022-12-20 | 100
0 | PPBKSR1325 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - SWING ROPE ASSEMBLY | 11 | 2022-08-01 | 2022-08-16 | 2022-12-21 | 2023-01-04 | 100
0 | PPBKSR1327 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - SWING ROPE ASSEMBLY | 120 | 2022-08-16 | 2023-02-02 | 2023-05-05 | 2023-10-26 | 184
0 | PMBKSR2390 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - SWING ROPE ASSEMBLY | 7 | 2023-02-04 | 2023-02-11 | 2023-10-27 | 2023-11-03 | 265
PIPING |  |  | 315 | 2022-03-17 | 2023-01-26 | 2022-07-20 | 2023-07-05 | 160
BALL VALVES (CS/LTCS/CLADDED) |  |  | 290 | 2022-04-05 | 2023-01-20 | 2022-07-26 | 2023-07-05 | 166
0 | PPBKPI1000 | PREPARE RFQ & FLOAT ENQUIRY - BALL VALVES (CS/LTCS/ CLADDED) | 3 | 2022-04-05 | 2022-04-08 | 2022-07-26 | 2022-07-28 | 74
0 | PPBKPI1005 | RECEIVE OFFERS - BALL VALVES (CS/LTCS/ CLADDED) | 15 | 2022-04-08 | 2022-04-29 | 2022-07-29 | 2022-08-18 | 74
0 | PPBKPI1010 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - BALL VALVES (CS/LTCS/ CLADDED) | 15 | 2022-05-06 | 2022-05-27 | 2022-08-19 | 2022-09-08 | 72
0 | PPBKPI1015 | RECEIVE TBE COMPANY APPROVAL - BALL VALVES (CS/LTCS/ CLADDED) | 10 | 2022-05-27 | 2022-06-10 | 2022-09-09 | 2022-09-22 | 72
0 | PPBKPI1020 | COMPLETE CBE / ISSUE ROA - BALL VALVES (CS/LTCS/ CLADDED) | 1 | 2022-06-10 | 2022-06-13 | 2022-09-23 | 2022-09-23 | 72
0 | PPBKPI1025 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - BALL VALVES (CS/LTCS/ CLADDED) | 11 | 2022-06-13 | 2022-06-28 | 2022-09-26 | 2022-10-10 | 72
0 | PPBKPI1027 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - BALL VALVES (CS/LTCS/ CLADDED) | 138 | 2022-06-28 | 2023-01-13 | 2022-10-12 | 2023-04-27 | 73
0 | PMBKPI3535 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - BALL VALVES (CS/LTCS/CLADDED) | 7 | 2023-01-13 | 2023-01-20 | 2023-06-28 | 2023-07-05 | 166
BALL VALVES (API 6A) |  |  | 287 | 2022-04-04 | 2023-01-16 | 2022-08-05 | 2023-07-05 | 170
0 | PPBKPI1030 | PREPARE RFQ & FLOAT ENQUIRY - BALL VALVES (API 6A) | 5 | 2022-04-04 | 2022-04-11 | 2022-08-05 | 2022-08-11 | 83
0 | PPBKPI1035 | RECEIVE OFFERS - BALL VALVES (API 6A) | 15 | 2022-04-11 | 2022-05-05 | 2022-08-12 | 2022-09-01 | 83
0 | PPBKPI1040 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - BALL VALVES (API 6A) | 15 | 2022-05-13 | 2022-06-03 | 2022-09-02 | 2022-09-22 | 77
0 | PPBKPI1045 | RECEIVE TBE COMPANY APPROVAL - BALL VALVES (API 6A) | 10 | 2022-06-03 | 2022-06-17 | 2022-09-23 | 2022-10-06 | 77
0 | PPBKPI1050 | COMPLETE CBE / ISSUE ROA - BALL VALVES (API 6A) | 1 | 2022-06-17 | 2022-06-20 | 2022-10-07 | 2022-10-07 | 77
0 | PPBKPI1055 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - BALL VALVES (API 6A) | 11 | 2022-06-20 | 2022-07-05 | 2022-10-10 | 2022-10-24 | 77
0 | PPBKPI1057 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - BALL VALVES (API 6A) | 129 | 2022-07-05 | 2023-01-09 | 2022-10-25 | 2023-04-27 | 77
0 | PMBKPI3525 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE- BALL VALVES (API 6A) | 7 | 2023-01-09 | 2023-01-16 | 2023-06-28 | 2023-07-05 | 170
GATE VALVES (CS/LTCS/CRA) |  |  | 284 | 2022-04-14 | 2023-01-23 | 2022-08-01 | 2023-07-05 | 163
0 | PPBKPI1060 | PREPARE RFQ & FLOAT ENQUIRY - GATE VALVES (CS/LTCS/CRA) | 3 | 2022-04-14 | 2022-04-19 | 2022-08-01 | 2022-08-03 | 71
0 | PPBKPI1065 | RECEIVE OFFERS - GATE VALVES (CS/LTCS/CRA) | 15 | 2022-04-19 | 2022-05-13 | 2022-08-04 | 2022-08-24 | 71
0 | PPBKPI1070 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - GATE VALVES (CS/LTCS/CRA) | 15 | 2022-05-13 | 2022-06-03 | 2022-08-25 | 2022-09-14 | 71
0 | PPBKPI1075 | RECEIVE TBE COMPANY APPROVAL - GATE VALVES (CS/LTCS/CRA) | 10 | 2022-06-03 | 2022-06-17 | 2022-09-15 | 2022-09-28 | 71
0 | PPBKPI1080 | COMPLETE CBE / ISSUE ROA - GATE VALVES (CS/LTCS/CRA) | 1 | 2022-06-17 | 2022-06-20 | 2022-09-29 | 2022-09-29 | 71
0 | PPBKPI1085 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - GATE VALVES (CS/LTCS/CRA) | 11 | 2022-06-20 | 2022-07-05 | 2022-09-30 | 2022-10-14 | 71
0 | PPBKPI1087 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - GATE VALVES (CS/LTCS/CRA) | 134 | 2022-07-05 | 2023-01-16 | 2022-10-18 | 2023-04-27 | 72
0 | PMBKPI3515 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - GATE VALVES (CS/LTCS/CRA) | 7 | 2023-01-16 | 2023-01-23 | 2023-06-28 | 2023-07-05 | 163
GATE VALVES (API) |  |  | 287 | 2022-04-14 | 2023-01-26 | 2022-07-27 | 2023-07-05 | 160
0 | PPBKPI1090 | PREPARE RFQ & FLOAT ENQUIRY - GATE VALVES (API) | 3 | 2022-04-14 | 2022-04-19 | 2022-07-27 | 2022-07-29 | 68
0 | PPBKPI1095 | RECEIVE OFFERS - GATE VALVES (API) | 15 | 2022-04-19 | 2022-05-13 | 2022-08-01 | 2022-08-19 | 68
0 | PPBKPI1100 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - GATE VALVES (API) | 15 | 2022-05-13 | 2022-06-03 | 2022-08-22 | 2022-09-09 | 68
0 | PPBKPI1105 | RECEIVE TBE COMPANY APPROVAL - GATE VALVES (API) | 10 | 2022-06-03 | 2022-06-17 | 2022-09-12 | 2022-09-23 | 68
0 | PPBKPI1110 | COMPLETE CBE / ISSUE ROA - GATE VALVES (API) | 1 | 2022-06-17 | 2022-06-20 | 2022-09-26 | 2022-09-26 | 68
0 | PPBKPI1115 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - GATE VALVES (API) | 11 | 2022-06-20 | 2022-07-05 | 2022-09-27 | 2022-10-11 | 68
0 | PPBKPI1117 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - GATE VALVES (API) | 135 | 2022-07-05 | 2023-01-17 | 2022-10-17 | 2023-04-27 | 71
0 | PMBKPI3505 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - GATE VALVES (API) | 7 | 2023-01-19 | 2023-01-26 | 2023-06-28 | 2023-07-05 | 160
GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) |  |  | 280 | 2022-04-19 | 2023-01-24 | 2022-08-04 | 2023-07-05 | 162
0 | PPBKPI1120 | PREPARE RFQ & FLOAT ENQUIRY - GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) | 5 | 2022-04-19 | 2022-04-26 | 2022-08-04 | 2022-08-10 | 71
0 | PPBKPI1125 | RECEIVE OFFERS - GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) | 15 | 2022-04-26 | 2022-05-20 | 2022-08-11 | 2022-08-31 | 71
0 | PPBKPI1130 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) | 15 | 2022-05-20 | 2022-06-10 | 2022-09-01 | 2022-09-21 | 71
0 | PPBKPI1135 | RECEIVE TBE COMPANY APPROVAL - GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) | 10 | 2022-06-10 | 2022-06-24 | 2022-09-22 | 2022-10-05 | 71
0 | PPBKPI1140 | COMPLETE CBE / ISSUE ROA - GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) | 1 | 2022-06-24 | 2022-06-27 | 2022-10-06 | 2022-10-06 | 71
0 | PPBKPI1145 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) | 11 | 2022-06-27 | 2022-07-15 | 2022-10-07 | 2022-10-21 | 71
0 | PPBKPI1147 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) | 130 | 2022-07-15 | 2023-01-17 | 2022-10-24 | 2023-04-27 | 71
0 | PMBKPI3495 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - GATE, GLOBE, PISTON LIFT CHECK & NEEDLE VALVES | 7 | 2023-01-17 | 2023-01-24 | 2023-06-28 | 2023-07-05 | 162
GLOBE, PISTON LIFT CHECK VALVES (API) |  |  | 281 | 2022-04-19 | 2023-01-25 | 2022-08-05 | 2023-07-05 | 161
0 | PPBKPI1150 | PREPARE RFQ & FLOAT ENQUIRY - GLOBE, PISTON LIFT CHECK VALVES (API) | 3 | 2022-04-19 | 2022-04-22 | 2022-08-05 | 2022-08-09 | 72
0 | PPBKPI1155 | RECEIVE OFFERS - GLOBE, PISTON LIFT CHECK VALVES (API) | 15 | 2022-04-22 | 2022-05-18 | 2022-08-10 | 2022-08-30 | 72
0 | PPBKPI1160 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL GLOBE, PISTON LIFT CHECK VALVES (API) | 15 | 2022-05-18 | 2022-06-08 | 2022-08-31 | 2022-09-20 | 72
0 | PPBKPI1165 | RECEIVE TBE COMPANY APPROVAL - GLOBE, PISTON LIFT CHECK VALVES (API) | 10 | 2022-06-08 | 2022-06-22 | 2022-09-21 | 2022-10-04 | 72
0 | PPBKPI1170 | COMPLETE CBE / ISSUE ROA - GLOBE, PISTON LIFT CHECK VALVES (API) | 1 | 2022-06-22 | 2022-06-23 | 2022-10-05 | 2022-10-05 | 72
0 | PPBKPI1175 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - GLOBE, PISTON LIFT CHECK VALVES (API) | 11 | 2022-06-27 | 2022-07-15 | 2022-10-06 | 2022-10-20 | 70
0 | PPBKPI1177 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - GLOBE, PISTON LIFT CHECK VALVES (API) | 131 | 2022-07-15 | 2023-01-18 | 2022-10-21 | 2023-04-27 | 70
0 | PMBKPI3485 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - GLOBE, PISTON LIFT CHECK VALVES (API) | 7 | 2023-01-18 | 2023-01-25 | 2023-06-28 | 2023-07-05 | 161
IDBB VALVES (CS/LTCS/CRA) |  |  | 289 | 2022-04-12 | 2023-01-26 | 2022-08-04 | 2023-07-05 | 160
0 | PPBKPI1180 | PREPARE RFQ & FLOAT ENQUIRY - IDBB VALVES (CS/LTCS/CRA) | 3 | 2022-04-12 | 2022-04-15 | 2022-08-04 | 2022-08-08 | 76
0 | PPBKPI1185 | RECEIVE OFFERS - IDBB VALVES (CS/LTCS/CRA) | 15 | 2022-04-15 | 2022-05-11 | 2022-08-09 | 2022-08-29 | 76
0 | PPBKPI1190 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - IDBB VALVES (CS/LTCS/CRA) | 15 | 2022-05-18 | 2022-06-08 | 2022-08-30 | 2022-09-19 | 71
0 | PPBKPI1195 | RECEIVE TBE COMPANY APPROVAL - IDBB VALVES (CS/LTCS/CRA) | 10 | 2022-06-08 | 2022-06-22 | 2022-09-20 | 2022-10-03 | 71
0 | PPBKPI1200 | COMPLETE CBE / ISSUE ROA - IDBB VALVES (CS/LTCS/CRA) | 1 | 2022-06-22 | 2022-06-23 | 2022-10-04 | 2022-10-04 | 71
0 | PPBKPI1205 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - IDBB VALVES (CS/LTCS/CRA) | 11 | 2022-06-23 | 2022-07-13 | 2022-10-05 | 2022-10-19 | 71
0 | PPBKPI1207 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - IDBB VALVES (CS/LTCS/CRA) | 130 | 2022-07-13 | 2023-01-13 | 2022-10-24 | 2023-04-27 | 73
0 | PMBKPI3475 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - IDBB VALVES (CS/LTCS/CRA) | 7 | 2023-01-19 | 2023-01-26 | 2023-06-28 | 2023-07-05 | 160
IDBB VALVES (API 6A) |  |  | 286 | 2022-04-11 | 2023-01-22 | 2022-07-28 | 2023-07-05 | 164
0 | PPBKPI1210 | PREPARE RFQ & FLOAT ENQUIRY - IDBB VALVES (API 6A) | 5 | 2022-04-11 | 2022-04-18 | 2022-07-28 | 2022-08-03 | 72
0 | PPBKPI1215 | RECEIVE OFFERS - IDBB VALVES (API 6A) | 15 | 2022-04-18 | 2022-05-12 | 2022-08-04 | 2022-08-24 | 72
0 | PPBKPI1220 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - IDBB VALVES (API 6A) | 10 | 2022-05-12 | 2022-05-26 | 2022-08-25 | 2022-09-07 | 72
0 | PPBKPI1225 | RECEIVE TBE COMPANY APPROVAL - IDBB VALVES (API 6A) | 10 | 2022-05-26 | 2022-06-09 | 2022-09-08 | 2022-09-21 | 72
0 | PPBKPI1230 | COMPLETE CBE / ISSUE ROA - IDBB VALVES (API 6A) | 1 | 2022-06-09 | 2022-06-10 | 2022-09-22 | 2022-09-22 | 72
0 | PPBKPI1235 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - IDBB VALVES (API 6A) | 11 | 2022-06-10 | 2022-06-27 | 2022-09-23 | 2022-10-07 | 72
0 | PPBKPI1237 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - IDBB VALVES (API 6A) | 138 | 2022-06-27 | 2023-01-12 | 2022-10-12 | 2023-04-27 | 74
0 | PMBKPI3465 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE- IDBB VALVES (API 6A) | 7 | 2023-01-15 | 2023-01-22 | 2023-06-28 | 2023-07-05 | 164
BUTTERFLY VALVES |  |  | 286 | 2022-04-15 | 2023-01-26 | 2022-08-02 | 2023-07-05 | 160
0 | PPBKPI1240 | PREPARE RFQ & FLOAT ENQUIRY - BUTTERFLY VALVES | 5 | 2022-04-15 | 2022-04-22 | 2022-08-02 | 2022-08-08 | 71
0 | PPBKPI1245 | RECEIVE OFFERS - BUTTERFLY VALVES | 10 | 2022-04-22 | 2022-05-11 | 2022-08-09 | 2022-08-22 | 71
0 | PPBKPI1250 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - BUTTERFLY VALVES | 15 | 2022-05-11 | 2022-06-01 | 2022-08-23 | 2022-09-12 | 71
0 | PPBKPI1255 | RECEIVE TBE COMPANY APPROVAL - BUTTERFLY VALVES | 10 | 2022-06-01 | 2022-06-15 | 2022-09-13 | 2022-09-26 | 71
0 | PPBKPI1260 | COMPLETE CBE / ISSUE ROA - BUTTERFLY VALVES | 1 | 2022-06-15 | 2022-06-16 | 2022-09-27 | 2022-09-27 | 71
0 | PPBKPI1265 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - BUTTERFLY VALVES | 11 | 2022-06-21 | 2022-07-06 | 2022-09-28 | 2022-10-12 | 68
0 | PPBKPI1267 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - BUTTERFLY VALVES | 135 | 2022-07-06 | 2023-01-18 | 2022-10-17 | 2023-04-27 | 70
0 | PMBKPI3455 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - BUTTERFLY VALVES | 7 | 2023-01-19 | 2023-01-26 | 2023-06-28 | 2023-07-05 | 160
SWING CHECK VALVES (CS/LTCS/CLADDED) |  |  | 281 | 2022-04-20 | 2023-01-26 | 2022-08-02 | 2023-07-05 | 160
0 | PPBKPI1270 | PREPARE RFQ & FLOAT ENQUIRY - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 5 | 2022-04-20 | 2022-04-27 | 2022-08-02 | 2022-08-08 | 68
0 | PPBKPI1275 | RECEIVE OFFERS - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 10 | 2022-04-27 | 2022-05-16 | 2022-08-09 | 2022-08-22 | 68
0 | PPBKPI1280 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 15 | 2022-05-16 | 2022-06-06 | 2022-08-23 | 2022-09-12 | 68
0 | PPBKPI1285 | RECEIVE TBE COMPANY APPROVAL - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 10 | 2022-06-06 | 2022-06-20 | 2022-09-13 | 2022-09-26 | 68
0 | PPBKPI1290 | COMPLETE CBE / ISSUE ROA - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 1 | 2022-06-20 | 2022-06-21 | 2022-09-27 | 2022-09-27 | 68
0 | PPBKPI1295 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 11 | 2022-06-21 | 2022-07-06 | 2022-09-28 | 2022-10-12 | 68
0 | PPBKPI1297 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 135 | 2022-07-06 | 2023-01-18 | 2022-10-17 | 2023-04-27 | 70
0 | PMBKPI3275 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 7 | 2023-01-19 | 2023-01-26 | 2023-06-28 | 2023-07-05 | 160
SWING CHECK VALVES (API) |  |  | 286 | 2022-04-15 | 2023-01-26 | 2022-08-01 | 2023-07-05 | 160
0 | PPBKPI1300 | PREPARE RFQ & FLOAT ENQUIRY - SWING CHECK VALVES (API) | 5 | 2022-04-15 | 2022-04-22 | 2022-08-01 | 2022-08-05 | 70
0 | PPBKPI1305 | RECEIVE OFFERS - SWING CHECK VALVES (API) | 15 | 2022-04-22 | 2022-05-18 | 2022-08-08 | 2022-08-26 | 70
0 | PPBKPI1310 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - SWING CHECK VALVES (API) | 15 | 2022-05-18 | 2022-06-08 | 2022-08-29 | 2022-09-16 | 70
0 | PPBKPI1315 | RECEIVE TBE COMPANY APPROVAL - SWING CHECK VALVES (API) | 10 | 2022-06-08 | 2022-06-22 | 2022-09-19 | 2022-09-30 | 70
0 | PPBKPI1320 | COMPLETE CBE / ISSUE ROA - SWING CHECK VALVES (API) | 1 | 2022-06-22 | 2022-06-23 | 2022-10-03 | 2022-10-03 | 70
0 | PPBKPI1325 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - SWING CHECK VALVES (API) | 11 | 2022-06-23 | 2022-07-13 | 2022-10-04 | 2022-10-18 | 70
0 | PPBKPI1327 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - SWING CHECK VALVES (API) | 133 | 2022-07-13 | 2023-01-18 | 2022-10-19 | 2023-04-27 | 70
0 | PMBKPI3265 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE- SWING CHECK VALVES (API) | 7 | 2023-01-19 | 2023-01-26 | 2023-06-28 | 2023-07-05 | 160
DUAL PLATE CHECK VALVES (API) |  |  | 278 | 2022-04-20 | 2023-01-23 | 2022-08-04 | 2023-07-05 | 163
0 | PPBKPI1330 | PREPARE RFQ & FLOAT ENQUIRY - DUAL PLATE CHECK VALVES (API) | 5 | 2022-04-20 | 2022-04-27 | 2022-08-04 | 2022-08-10 | 70
0 | PPBKPI1335 | RECEIVE OFFERS - DUAL PLATE CHECK VALVES (API) | 10 | 2022-04-27 | 2022-05-16 | 2022-08-11 | 2022-08-24 | 70
0 | PPBKPI1340 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - DUAL PLATE CHECK VALVES (API) | 15 | 2022-05-16 | 2022-06-06 | 2022-08-25 | 2022-09-14 | 70
0 | PPBKPI1345 | RECEIVE TBE COMPANY APPROVAL - DUAL PLATE CHECK VALVES (API) | 10 | 2022-06-06 | 2022-06-20 | 2022-09-15 | 2022-09-28 | 70
0 | PPBKPI1350 | COMPLETE CBE / ISSUE ROA - DUAL PLATE CHECK VALVES (API) | 1 | 2022-06-20 | 2022-06-21 | 2022-09-29 | 2022-09-29 | 70
0 | PPBKPI1355 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - DUAL PLATE CHECK VALVES (API) | 11 | 2022-06-21 | 2022-07-06 | 2022-09-30 | 2022-10-14 | 70
0 | PPBKPI1357 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - DUAL PLATE CHECK VALVES (API) | 133 | 2022-07-06 | 2023-01-16 | 2022-10-19 | 2023-04-27 | 72
0 | PMBKPI3245 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - DUAL PLATE CHECK VALVES (API) | 7 | 2023-01-16 | 2023-01-23 | 2023-06-28 | 2023-07-05 | 163
DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) |  |  | 282 | 2022-04-19 | 2023-01-26 | 2022-08-01 | 2023-07-05 | 160
0 | PPBKPI1360 | PREPARE RFQ & FLOAT ENQUIRY - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 5 | 2022-04-19 | 2022-04-26 | 2022-08-01 | 2022-08-05 | 68
0 | PPBKPI1365 | RECEIVE OFFERS - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 10 | 2022-04-26 | 2022-05-13 | 2022-08-08 | 2022-08-19 | 68
0 | PPBKPI1370 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 15 | 2022-05-13 | 2022-06-03 | 2022-08-22 | 2022-09-09 | 68
0 | PPBKPI1375 | RECEIVE TBE COMPANY APPROVAL - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 10 | 2022-06-03 | 2022-06-17 | 2022-09-12 | 2022-09-23 | 68
0 | PPBKPI1380 | COMPLETE CBE / ISSUE ROA - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 1 | 2022-06-17 | 2022-06-20 | 2022-09-26 | 2022-09-26 | 68
0 | PPBKPI1385 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 11 | 2022-06-20 | 2022-07-05 | 2022-09-27 | 2022-10-11 | 68
0 | PPBKPI1387 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 137 | 2022-07-05 | 2023-01-19 | 2022-10-13 | 2023-04-27 | 69
0 | PMBKPI3255 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 7 | 2023-01-19 | 2023-01-26 | 2023-06-28 | 2023-07-05 | 160
PIPES CS & LTCS/CRA |  |  | 297 | 2022-03-18 | 2023-01-09 | 2022-07-20 | 2023-04-28 | 109
0 | PPBKPI1390 | PREPARE RFQ & FLOAT ENQUIRY - PIPES CS & LTCS/CRA | 1 | 2022-03-18 | 2022-03-21 | 2022-07-20 | 2022-07-20 | 82
0 | PPBKPI1395 | RECEIVE OFFERS - PIPES CS & LTCS/CRA | 5 | 2022-03-21 | 2022-03-28 | 2022-07-21 | 2022-07-27 | 82
0 | PPBKPI1400 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIPES CS & LTCS/CRA | 10 | 2022-03-31 | 2022-04-14 | 2022-07-28 | 2022-08-10 | 79
0 | PPBKPI1405 | RECEIVE TBE COMPANY APPROVAL - PIPES CS & LTCS/CRA | 10 | 2022-04-14 | 2022-04-28 | 2022-08-11 | 2022-08-24 | 79
0 | PPBKPI1410 | COMPLETE CBE / ISSUE ROA - PIPES CS & LTCS/CRA | 1 | 2022-04-28 | 2022-04-29 | 2022-08-25 | 2022-08-25 | 79
0 | PPBKPI1415 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIPES CS & LTCS/CRA | 11 | 2022-04-29 | 2022-05-19 | 2022-08-26 | 2022-09-09 | 79
0 | PPBKPI1417 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIPES CS & LTCS/CRA | 157 | 2022-05-19 | 2023-01-02 | 2022-09-12 | 2023-04-20 | 79
0 | PMBKPI3345 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PIPES CS & LTCS/CRA | 7 | 2023-01-02 | 2023-01-09 | 2023-04-21 | 2023-04-28 | 109
FORGED FITTINGS CS, LTCS/CRA |  |  | 298 | 2022-03-17 | 2023-01-09 | 2022-08-08 | 2023-04-28 | 109
0 | PPBKPI1420 | PREPARE RFQ & FLOAT ENQUIRY - FORGED FITTINGS CS, LTCS/CRA | 3 | 2022-03-17 | 2022-03-22 | 2022-08-08 | 2022-08-10 | 96
0 | PPBKPI1425 | RECEIVE OFFERS - FORGED FITTINGS CS, LTCS/CRA | 5 | 2022-03-22 | 2022-03-29 | 2022-08-11 | 2022-08-17 | 96
0 | PPBKPI1430 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - FORGED FITTINGS CS, LTCS/CRA | 5 | 2022-04-07 | 2022-04-14 | 2022-08-18 | 2022-08-24 | 89
0 | PPBKPI1435 | RECEIVE TBE COMPANY APPROVAL - FORGED FITTINGS CS, LTCS/CRA | 10 | 2022-04-14 | 2022-04-28 | 2022-08-25 | 2022-09-07 | 89
0 | PPBKPI1440 | COMPLETE CBE / ISSUE ROA - FORGED FITTINGS CS, LTCS/CRA | 1 | 2022-04-28 | 2022-04-29 | 2022-09-08 | 2022-09-08 | 89
0 | PPBKPI1445 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - FORGED FITTINGS CS, LTCS/CRA | 11 | 2022-04-29 | 2022-05-19 | 2022-09-09 | 2022-09-23 | 89
0 | PPBKPI1447 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - FORGED FITTINGS CS, LTCS/CRA | 147 | 2022-05-19 | 2022-12-19 | 2022-09-26 | 2023-04-20 | 89
0 | PMBKPI3315 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - FORGED FITTINGS CS, LTCS/CRA | 7 | 2023-01-02 | 2023-01-09 | 2023-04-21 | 2023-04-28 | 109
BUTT WELD FITTINGS CS, LTCS/CRA |  |  | 284 | 2022-03-17 | 2022-12-26 | 2022-08-03 | 2023-04-28 | 123
0 | PPBKPI1450 | PREPARE RFQ & FLOAT ENQUIRY - BUTT WELD FITTINGS CS, LTCS/CRA | 1 | 2022-03-17 | 2022-03-18 | 2022-08-03 | 2022-08-03 | 93
0 | PPBKPI1455 | RECEIVE OFFERS - BUTT WELD FITTINGS CS, LTCS/CRA | 5 | 2022-03-18 | 2022-03-25 | 2022-08-04 | 2022-08-10 | 93
0 | PPBKPI1460 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - BUTT WELD FITTINGS CS, LTCS/CRA | 5 | 2022-04-07 | 2022-04-14 | 2022-08-11 | 2022-08-17 | 84
0 | PPBKPI1465 | RECEIVE TBE COMPANY APPROVAL - BUTT WELD FITTINGS CS, LTCS/CRA | 10 | 2022-04-14 | 2022-04-28 | 2022-08-18 | 2022-08-31 | 84
0 | PPBKPI1470 | COMPLETE CBE / ISSUE ROA - BUTT WELD FITTINGS CS, LTCS/CRA | 1 | 2022-04-28 | 2022-04-29 | 2022-09-01 | 2022-09-01 | 84
0 | PPBKPI1475 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - BUTT WELD FITTINGS CS, LTCS/CRA | 11 | 2022-04-29 | 2022-05-19 | 2022-09-02 | 2022-09-16 | 84
0 | PPBKPI1477 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - BUTT WELD FITTINGS CS, LTCS/CRA | 147 | 2022-05-19 | 2022-12-19 | 2022-09-26 | 2023-04-20 | 89
0 | PMBKPI3325 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - BUTT WELD FITTINGS CS, LTCS/CRA | 7 | 2022-12-19 | 2022-12-26 | 2023-04-21 | 2023-04-28 | 123
FLANGES CS/ LTCS/CRA & CLADDED |  |  | 283 | 2022-03-18 | 2022-12-26 | 2022-08-10 | 2023-04-28 | 123
0 | PPBKPI1480 | PREPARE RFQ & FLOAT ENQUIRY - FLANGES CS, LTCS /CRA & CS CLADDED | 1 | 2022-03-18 | 2022-03-21 | 2022-08-10 | 2022-08-10 | 97
0 | PPBKPI1485 | RECEIVE OFFERS - FLANGES CS, LTCS /CRA & CS CLADDED | 5 | 2022-03-21 | 2022-03-28 | 2022-08-11 | 2022-08-17 | 97
0 | PPBKPI1490 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - FLANGES CS, LTCS /CRA & CS CLADDED | 5 | 2022-04-08 | 2022-04-15 | 2022-08-18 | 2022-08-24 | 88
0 | PPBKPI1495 | RECEIVE TBE COMPANY APPROVAL - FLANGES CS, LTCS /CRA & CS CLADDED | 10 | 2022-04-15 | 2022-04-29 | 2022-08-25 | 2022-09-07 | 88
0 | PPBKPI1500 | COMPLETE CBE / ISSUE ROA - FLANGES CS, LTCS /CRA & CS CLADDED | 1 | 2022-04-29 | 2022-05-05 | 2022-09-08 | 2022-09-08 | 88
0 | PPBKPI1505 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - FLANGES CS, LTCS /CRA & CS CLADDED | 11 | 2022-05-05 | 2022-05-20 | 2022-09-09 | 2022-09-23 | 88
0 | PPBKPI1507 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - FLANGES CS, LTCS /CRA & CS CLADDED | 146 | 2022-05-20 | 2022-12-19 | 2022-09-27 | 2023-04-20 | 89
0 | PMBKPI3305 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - FLANGES CS/ LTCS/CRA & CLADDED | 7 | 2022-12-19 | 2022-12-26 | 2023-04-21 | 2023-04-28 | 123
PIPES & FITINGS CLADDED SERVICE |  |  | 284 | 2022-03-18 | 2022-12-27 | 2022-08-03 | 2023-04-28 | 122
0 | PPBKPI1510 | PREPARE RFQ & FLOAT ENQUIRY - PIPES & FITINGS CLADDED SERVICE | 1 | 2022-03-18 | 2022-03-21 | 2022-08-03 | 2022-08-03 | 92
0 | PPBKPI1515 | RECEIVE OFFERS - PIPES & FITINGS CLADDED SERVICE | 5 | 2022-03-21 | 2022-03-28 | 2022-08-04 | 2022-08-10 | 92
0 | PPBKPI1520 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIPES & FITINGS CLADDED SERVICED | 5 | 2022-04-08 | 2022-04-15 | 2022-08-18 | 2022-08-24 | 88
0 | PPBKPI1525 | RECEIVE TBE COMPANY APPROVAL - PIPES & FITINGS CLADDED SERVICE | 10 | 2022-04-15 | 2022-04-29 | 2022-08-25 | 2022-09-07 | 88
0 | PPBKPI1530 | COMPLETE CBE / ISSUE ROA - PIPES & FITINGS CLADDED SERVICE | 1 | 2022-04-29 | 2022-05-05 | 2022-09-08 | 2022-09-08 | 88
0 | PPBKPI1535 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIPES & FITINGS CLADDED SERVICE | 11 | 2022-05-05 | 2022-05-20 | 2022-09-09 | 2022-09-23 | 88
0 | PPBKPI1537 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIPES & FITINGS CLADDED SERVICE | 147 | 2022-05-20 | 2022-12-20 | 2022-09-26 | 2023-04-20 | 88
0 | PMBKPI3335 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PIPES & FITINGS CLADDED SERVICE | 7 | 2022-12-20 | 2022-12-27 | 2023-04-21 | 2023-04-28 | 122
CU-NI PIPE FITTINGS AND FLANGES |  |  | 288 | 2022-03-25 | 2023-01-07 | 2022-07-28 | 2023-05-23 | 136
0 | PPBKPI1565 | PREPARE RFQ & FLOAT ENQUIRY - CU-NI PIPES FITTINGS AND FLANGES | 5 | 2022-03-25 | 2022-04-01 | 2022-07-28 | 2022-08-03 | 83
0 | PPBKPI1570 | RECEIVE OFFERS - CU-NI PIPES FITTINGS AND FLANGES | 10 | 2022-04-01 | 2022-04-15 | 2022-08-04 | 2022-08-17 | 83
0 | PPBKPI1575 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - CU-NI PIPES FITTINGS AND FLANGES | 10 | 2022-04-15 | 2022-04-29 | 2022-08-18 | 2022-08-31 | 83
0 | PPBKPI1580 | RECEIVE TBE COMPANY APPROVAL - CU-NI PIPES FITTINGS AND FLANGES | 10 | 2022-04-29 | 2022-05-18 | 2022-09-01 | 2022-09-14 | 83
0 | PPBKPI1585 | COMPLETE CBE / ISSUE ROA - CU-NI PIPES FITTINGS AND FLANGES | 1 | 2022-05-18 | 2022-05-19 | 2022-09-15 | 2022-09-15 | 83
0 | PPBKPI1590 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - CU-NI PIPES FITTINGS AND FLANGES | 11 | 2022-05-19 | 2022-06-03 | 2022-09-16 | 2022-09-30 | 83
0 | PPBKPI1592 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - CU-NI PIPES FITTINGS AND FLANGES | 145 | 2022-06-03 | 2022-12-30 | 2022-10-03 | 2023-04-27 | 83
0 | PMBKPI3285 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - CU-NI PIPE FITTINGS AND FLANGES | 7 | 2022-12-31 | 2023-01-07 | 2023-05-16 | 2023-05-23 | 136
GASKETS |  |  | 277 | 2022-04-12 | 2023-01-14 | 2022-08-31 | 2023-07-03 | 170
0 | PPBKPI1595 | PREPARE RFQ & FLOAT ENQUIRY - GASKETS | 5 | 2022-04-12 | 2022-04-19 | 2022-08-31 | 2022-09-06 | 95
0 | PPBKPI1600 | RECEIVE OFFERS - GASKETS | 10 | 2022-04-19 | 2022-05-06 | 2022-09-07 | 2022-09-20 | 95
0 | PPBKPI1605 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - GASKETS | 10 | 2022-05-18 | 2022-06-01 | 2022-09-29 | 2022-10-12 | 93
0 | PPBKPI1610 | RECEIVE TBE COMPANY APPROVAL - GASKETS | 10 | 2022-06-01 | 2022-06-15 | 2022-10-13 | 2022-10-26 | 93
0 | PPBKPI1615 | COMPLETE CBE / ISSUE ROA - GASKETS | 1 | 2022-06-15 | 2022-06-16 | 2022-10-27 | 2022-10-27 | 93
0 | PPBKPI1620 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - GASKETS | 11 | 2022-07-06 | 2022-07-26 | 2022-10-28 | 2022-11-11 | 79
0 | PPBKPI1622 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - GASKETS | 115 | 2022-07-26 | 2023-01-05 | 2022-11-14 | 2023-04-27 | 79
0 | PMBKPI3365 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - GASKETS | 7 | 2023-01-07 | 2023-01-14 | 2023-06-26 | 2023-07-03 | 170
BOLTING |  |  | 245 | 2022-04-14 | 2022-12-15 | 2022-09-08 | 2023-07-03 | 200
0 | PPBKPI1625 | PREPARE RFQ & FLOAT ENQUIRY - BOLTING | 5 | 2022-04-14 | 2022-04-21 | 2022-09-08 | 2022-09-14 | 99
0 | PPBKPI1630 | RECEIVE OFFERS - BOLTING | 10 | 2022-04-21 | 2022-05-10 | 2022-09-15 | 2022-09-28 | 99
0 | PPBKPI1635 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - BOLTING | 10 | 2022-05-10 | 2022-05-24 | 2022-09-29 | 2022-10-12 | 99
0 | PPBKPI1640 | RECEIVE TBE COMPANY APPROVAL - BOLTING | 10 | 2022-05-24 | 2022-06-07 | 2022-10-13 | 2022-10-26 | 99
0 | PPBKPI1645 | COMPLETE CBE / ISSUE ROA - BOLTING | 1 | 2022-06-07 | 2022-06-08 | 2022-10-27 | 2022-10-27 | 99
0 | PPBKPI1650 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - BOLTING | 11 | 2022-06-08 | 2022-06-23 | 2022-10-28 | 2022-11-11 | 99
0 | PPBKPI1652 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - BOLTING | 115 | 2022-06-23 | 2022-12-08 | 2022-11-14 | 2023-04-27 | 99
0 | PMBKPI3355 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - BOLTING | 7 | 2022-12-08 | 2022-12-15 | 2023-06-26 | 2023-07-03 | 200
ACCESS FITTINGS AND CORROSION COUPON |  |  | 255 | 2022-05-11 | 2023-01-21 | 2022-08-25 | 2023-07-03 | 163
0 | PPBKPI1655 | PREPARE RFQ & FLOAT ENQUIRY - ACCESS FITTINGS AND CORROSION COUPEN | 5 | 2022-05-11 | 2022-05-18 | 2022-08-25 | 2022-08-31 | 73
0 | PPBKPI1660 | RECEIVE OFFERS - ACCESS FITTINGS AND CORROSION COUPEN | 15 | 2022-05-18 | 2022-06-08 | 2022-09-01 | 2022-09-21 | 73
0 | PPBKPI1665 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - ACCESS FITTINGS AND CORROSION COUPEN | 15 | 2022-06-08 | 2022-06-29 | 2022-09-23 | 2022-10-13 | 74
0 | PPBKPI1670 | RECEIVE TBE COMPANY APPROVAL - ACCESS FITTINGS AND CORROSION COUPEN | 10 | 2022-06-29 | 2022-07-18 | 2022-10-14 | 2022-10-27 | 74
0 | PPBKPI1675 | COMPLETE CBE / ISSUE ROA - ACCESS FITTINGS AND CORROSION COUPEN | 1 | 2022-07-18 | 2022-07-19 | 2022-10-28 | 2022-10-28 | 74
0 | PPBKPI1680 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - ACCESS FITTINGS AND CORROSION COUPEN | 11 | 2022-07-19 | 2022-08-03 | 2022-10-31 | 2022-11-14 | 74
0 | PPBKPI1682 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - ACCESS FITTINGS AND CORROSION COUPEN | 114 | 2022-08-03 | 2023-01-12 | 2022-11-15 | 2023-04-27 | 74
0 | PMBKPI3445 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - ACCESS FITTINGS AND CORROSION COUPON | 7 | 2023-01-14 | 2023-01-21 | 2023-06-26 | 2023-07-03 | 163
BIRD SCREEN |  |  | 242 | 2022-05-18 | 2023-01-15 | 2022-09-07 | 2023-07-03 | 169
0 | PPBKPI1685 | PREPARE RFQ & FLOAT ENQUIRY - BIRD SCREEN | 5 | 2022-05-18 | 2022-05-25 | 2022-09-07 | 2022-09-13 | 77
0 | PPBKPI1690 | RECEIVE OFFERS - BIRD SCREEN | 15 | 2022-05-25 | 2022-06-15 | 2022-09-14 | 2022-10-04 | 77
0 | PPBKPI1695 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - BIRD SCREEN | 15 | 2022-06-15 | 2022-07-06 | 2022-10-06 | 2022-10-26 | 78
0 | PPBKPI1700 | RECEIVE TBE COMPANY APPROVAL - BIRD SCREEN | 10 | 2022-07-06 | 2022-07-25 | 2022-10-27 | 2022-11-09 | 78
0 | PPBKPI1705 | COMPLETE CBE / ISSUE ROA - BIRD SCREEN | 1 | 2022-07-25 | 2022-07-26 | 2022-11-10 | 2022-11-10 | 78
0 | PPBKPI1710 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - BIRD SCREEN | 11 | 2022-07-26 | 2022-08-10 | 2022-11-11 | 2022-11-25 | 78
0 | PPBKPI1712 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - BIRD SCREEN | 104 | 2022-08-10 | 2023-01-05 | 2022-11-29 | 2023-04-27 | 79
0 | PMBKPI3415 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - BIRD SCREEN | 7 | 2023-01-08 | 2023-01-15 | 2023-06-26 | 2023-07-03 | 169
FLEXIBLE HOSE AND COUPLING |  |  | 192 | 2022-07-14 | 2023-01-22 | 2022-10-24 | 2023-07-03 | 162
0 | PPBKPI1715 | PREPARE RFQ & FLOAT ENQUIRY - FLEXIBLE HOSE AND COUPLING | 3 | 2022-07-14 | 2022-07-19 | 2022-10-24 | 2022-10-26 | 72
0 | PPBKPI1720 | RECEIVE OFFERS - FLEXIBLE HOSE AND COUPLING | 10 | 2022-07-19 | 2022-08-02 | 2022-10-27 | 2022-11-09 | 72
0 | PPBKPI1725 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - FLEXIBLE HOSE AND COUPLING | 10 | 2022-08-02 | 2022-08-16 | 2022-11-10 | 2022-11-23 | 72
0 | PPBKPI1730 | RECEIVE TBE COMPANY APPROVAL - FLEXIBLE HOSE AND COUPLING | 10 | 2022-08-16 | 2022-08-30 | 2022-11-24 | 2022-12-09 | 72
0 | PPBKPI1735 | COMPLETE CBE / ISSUE ROA - FLEXIBLE HOSE AND COUPLING | 1 | 2022-08-30 | 2022-08-31 | 2022-12-12 | 2022-12-12 | 72
0 | PPBKPI1740 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - FLEXIBLE HOSE AND COUPLING | 11 | 2022-09-01 | 2022-09-16 | 2022-12-13 | 2022-12-27 | 71
0 | PPBKPI1742 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - FLEXIBLE HOSE AND COUPLING | 83 | 2022-09-16 | 2023-01-13 | 2022-12-30 | 2023-04-27 | 73
0 | PMBKPI3385 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - FLEXIBLE HOSE AND COUPLING | 7 | 2023-01-15 | 2023-01-22 | 2023-06-26 | 2023-07-03 | 162
FIRE WATER SPRAY NOZZLE |  |  | 234 | 2022-05-24 | 2023-01-13 | 2022-09-16 | 2023-05-26 | 133
0 | PPBKPI1745 | PREPARE RFQ & FLOAT ENQUIRY - FIRE WATER SPRAY NOZZLE | 5 | 2022-05-24 | 2022-05-31 | 2022-09-16 | 2022-09-22 | 80
0 | PPBKPI1750 | RECEIVE OFFERS - FIRE WATER SPRAY NOZZLE | 10 | 2022-05-31 | 2022-06-14 | 2022-09-23 | 2022-10-06 | 80
0 | PPBKPI1755 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - FIRE WATER SPRAY NOZZLE | 10 | 2022-06-14 | 2022-06-28 | 2022-10-07 | 2022-10-20 | 80
0 | PPBKPI1760 | RECEIVE TBE COMPANY APPROVAL - FIRE WATER SPRAY NOZZLE | 10 | 2022-06-28 | 2022-07-15 | 2022-10-21 | 2022-11-03 | 80
0 | PPBKPI1765 | COMPLETE CBE / ISSUE ROA - FIRE WATER SPRAY NOZZLE | 1 | 2022-07-15 | 2022-07-18 | 2022-11-04 | 2022-11-04 | 80
0 | PPBKPI1770 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - FIRE WATER SPRAY NOZZLE | 11 | 2022-07-18 | 2022-08-02 | 2022-11-07 | 2022-11-21 | 80
0 | PPBKPI1772 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - FIRE WATER SPRAY NOZZLE | 109 | 2022-08-02 | 2023-01-04 | 2022-11-22 | 2023-04-27 | 80
0 | PMBKPI3395 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - FIRE WATER SPRAY NOZZLE | 7 | 2023-01-06 | 2023-01-13 | 2023-05-19 | 2023-05-26 | 133
INSULATING GASKET |  |  | 249 | 2022-05-12 | 2023-01-16 | 2022-09-01 | 2023-07-03 | 168
0 | PPBKPI1775 | PREPARE RFQ & FLOAT ENQUIRY - INSULATING GASKET | 3 | 2022-05-12 | 2022-05-17 | 2022-09-01 | 2022-09-05 | 77
0 | PPBKPI1780 | RECEIVE OFFERS - INSULATING GASKET | 12 | 2022-05-17 | 2022-06-02 | 2022-09-06 | 2022-09-21 | 77
0 | PPBKPI1785 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - INSULATING GASKET | 15 | 2022-06-02 | 2022-06-23 | 2022-09-22 | 2022-10-12 | 77
0 | PPBKPI1790 | RECEIVE TBE COMPANY APPROVAL - INSULATING GASKET | 10 | 2022-06-23 | 2022-07-07 | 2022-10-13 | 2022-10-26 | 77
0 | PPBKPI1795 | COMPLETE CBE / ISSUE ROA - INSULATING GASKET | 1 | 2022-07-07 | 2022-07-13 | 2022-10-27 | 2022-10-27 | 77
0 | PPBKPI1800 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - INSULATING GASKET | 11 | 2022-07-13 | 2022-07-28 | 2022-10-28 | 2022-11-11 | 77
0 | PPBKPI1802 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - INSULATING GASKET | 115 | 2022-07-28 | 2023-01-09 | 2022-11-14 | 2023-04-27 | 77
0 | PMBKPI3435 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - INSULATING GASKET | 7 | 2023-01-09 | 2023-01-16 | 2023-06-26 | 2023-07-03 | 168
SIGHT GLASS |  |  | 193 | 2022-07-15 | 2023-01-24 | 2022-10-21 | 2023-07-03 | 160
0 | PPBKPI1805 | PREPARE RFQ & FLOAT ENQUIRY - SIGHT GLASS | 2 | 2022-07-15 | 2022-07-19 | 2022-10-21 | 2022-10-24 | 70
0 | PPBKPI1810 | RECEIVE OFFERS - SIGHT GLASS | 10 | 2022-07-19 | 2022-08-02 | 2022-10-25 | 2022-11-07 | 70
0 | PPBKPI1815 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - SIGHT GLASS | 10 | 2022-08-02 | 2022-08-16 | 2022-11-08 | 2022-11-21 | 70
0 | PPBKPI1820 | RECEIVE TBE COMPANY APPROVAL - SIGHT GLASS | 10 | 2022-08-16 | 2022-08-30 | 2022-11-22 | 2022-12-07 | 70
0 | PPBKPI1825 | COMPLETE CBE / ISSUE ROA - SIGHT GLASS | 1 | 2022-08-30 | 2022-08-31 | 2022-12-08 | 2022-12-08 | 70
0 | PPBKPI1830 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - SIGHT GLASS | 11 | 2022-08-31 | 2022-09-15 | 2022-12-09 | 2022-12-23 | 70
0 | PPBKPI1832 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - SIGHT GLASS | 85 | 2022-09-15 | 2023-01-16 | 2022-12-28 | 2023-04-27 | 72
0 | PMBKPI3375 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - SIGHT GLASS | 7 | 2023-01-17 | 2023-01-24 | 2023-06-26 | 2023-07-03 | 160
STRAINER |  |  | 252 | 2022-05-16 | 2023-01-23 | 2022-08-29 | 2023-07-03 | 161
0 | PPBKPI1835 | PREPARE RFQ & FLOAT ENQUIRY - STRAINER | 5 | 2022-05-16 | 2022-05-23 | 2022-08-29 | 2022-09-02 | 72
0 | PPBKPI1840 | RECEIVE OFFERS - STRAINER | 15 | 2022-05-23 | 2022-06-13 | 2022-09-05 | 2022-09-23 | 72
0 | PPBKPI1845 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - STRAINER | 15 | 2022-06-13 | 2022-07-04 | 2022-09-26 | 2022-10-14 | 72
0 | PPBKPI1850 | RECEIVE TBE COMPANY APPROVAL - STRAINER | 10 | 2022-07-04 | 2022-07-21 | 2022-10-17 | 2022-10-28 | 72
0 | PPBKPI1855 | COMPLETE CBE / ISSUE ROA - STRAINER | 1 | 2022-07-21 | 2022-07-22 | 2022-10-31 | 2022-10-31 | 72
0 | PPBKPI1860 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - STRAINER | 11 | 2022-07-22 | 2022-08-08 | 2022-11-01 | 2022-11-15 | 72
0 | PPBKPI1862 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - STRAINER | 113 | 2022-08-08 | 2023-01-16 | 2022-11-16 | 2023-04-27 | 72
0 | PMBKPI3425 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - STRAINER | 7 | 2023-01-16 | 2023-01-23 | 2023-06-26 | 2023-07-03 | 161
VALVE INTERLOCK |  |  | 246 | 2022-05-20 | 2023-01-21 | 2022-09-05 | 2023-07-03 | 163
0 | PPBKPI1865 | PREPARE RFQ & FLOAT ENQUIRY - VALVE INTERLOCK | 3 | 2022-05-20 | 2022-05-25 | 2022-09-05 | 2022-09-07 | 73
0 | PPBKPI1870 | RECEIVE OFFERS - VALVE INTERLOCK | 15 | 2022-05-25 | 2022-06-15 | 2022-09-08 | 2022-09-28 | 73
0 | PPBKPI1875 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - VALVE INTERLOCK | 15 | 2022-06-15 | 2022-07-06 | 2022-09-30 | 2022-10-20 | 74
0 | PPBKPI1880 | RECEIVE TBE COMPANY APPROVAL - VALVE INTERLOCK | 10 | 2022-07-06 | 2022-07-25 | 2022-10-21 | 2022-11-03 | 74
0 | PPBKPI1885 | COMPLETE CBE / ISSUE ROA - VALVE INTERLOCK | 1 | 2022-07-25 | 2022-07-26 | 2022-11-04 | 2022-11-04 | 74
0 | PPBKPI1890 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - VALVE INTERLOCK | 11 | 2022-07-26 | 2022-08-10 | 2022-11-07 | 2022-11-21 | 74
0 | PPBKPI1892 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - VALVE INTERLOCK | 109 | 2022-08-10 | 2023-01-12 | 2022-11-22 | 2023-04-27 | 74
0 | PMBKPI3405 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE- VALVE INTERLOCK | 7 | 2023-01-14 | 2023-01-21 | 2023-06-26 | 2023-07-03 | 163
PIPE SUPPORT MATERIAL |  |  | 232 | 2022-05-05 | 2022-12-23 | 2022-08-26 | 2023-04-13 | 111
0 | PPBKPI1895 | PREPARE RFQ & FLOAT ENQUIRY - PIPE SUPPORT MATERIALS | 5 | 2022-05-05 | 2022-05-12 | 2022-08-26 | 2022-09-01 | 78
0 | PPBKPI1900 | RECEIVE OFFERS - PIPE SUPPORT MATERIALS | 15 | 2022-05-12 | 2022-06-02 | 2022-09-02 | 2022-09-22 | 78
0 | PPBKPI1905 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIPE SUPPORT MATERIALS | 15 | 2022-06-02 | 2022-06-23 | 2022-09-26 | 2022-10-14 | 79
0 | PPBKPI1910 | RECEIVE TBE COMPANY APPROVAL - PIPE SUPPORT MATERIALS | 10 | 2022-06-23 | 2022-07-07 | 2022-10-17 | 2022-10-28 | 79
0 | PPBKPI1915 | COMPLETE CBE / ISSUE ROA - PIPE SUPPORT MATERIALS | 1 | 2022-07-07 | 2022-07-13 | 2022-10-31 | 2022-10-31 | 79
0 | PPBKPI1920 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIPE SUPPORT MATERIALS | 11 | 2022-07-13 | 2022-07-28 | 2022-11-01 | 2022-11-15 | 79
0 | PPBKPI1922 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIPE SUPPORT MATERIALS | 99 | 2022-07-28 | 2022-12-16 | 2022-11-16 | 2023-04-05 | 79
0 | PMBKPI3295 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PIPE SUPPORT MATERIALS | 7 | 2022-12-16 | 2022-12-23 | 2023-04-06 | 2023-04-13 | 111
INSTRUMENTATION |  |  | 398 | 2022-04-14 | 2023-05-17 | 2022-07-04 | 2023-12-09 | 207
PRESSURE GAUGES |  |  | 350 | 2022-04-27 | 2023-04-12 | 2022-09-16 | 2023-08-31 | 142
0 | PPBKIN1000 | PREPARE RFQ & FLOAT ENQUIRY - PRESSURE GAUGES | 5 | 2022-04-27 | 2022-05-09 | 2022-09-16 | 2022-09-22 | 96
0 | PPBKIN1005 | RECEIVE OFFERS - PRESSURE GAUGES | 15 | 2022-05-09 | 2022-05-30 | 2022-09-23 | 2022-10-13 | 96
0 | PPBKIN1010 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PRESSURE GAUGES | 15 | 2022-05-30 | 2022-06-20 | 2022-10-14 | 2022-11-03 | 96
0 | PPBKIN1015 | RECEIVE TBE COMPANY APPROVAL - PRESSURE GAUGES | 10 | 2022-06-20 | 2022-07-04 | 2022-11-04 | 2022-11-17 | 96
0 | PPBKIN1020 | COMPLETE CBE / ISSUE ROA - PRESSURE GAUGES | 1 | 2022-07-04 | 2022-07-05 | 2022-11-18 | 2022-11-18 | 96
0 | PPBKIN1025 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PRESSURE GAUGES | 11 | 2022-07-05 | 2022-07-25 | 2022-11-21 | 2022-12-07 | 96
0 | PPBKIN1027 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PRESSURE GAUGES | 180 | 2022-07-25 | 2023-04-05 | 2022-12-08 | 2023-08-24 | 96
0 | PMBKIN2810 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - PRESSURE GAUGES | 7 | 2023-04-05 | 2023-04-12 | 2023-08-24 | 2023-08-31 | 141
TEMPERATURE GAUGES |  |  | 331 | 2022-06-14 | 2023-05-11 | 2022-09-28 | 2023-08-28 | 109
0 | PPBKIN1030 | PREPARE RFQ & FLOAT ENQUIRY - TEMPERATURE GAUGES | 5 | 2022-06-14 | 2022-06-21 | 2022-09-28 | 2022-10-04 | 73
0 | PPBKIN1035 | RECEIVE OFFERS - TEMPERATURE GAUGES | 10 | 2022-06-21 | 2022-07-05 | 2022-10-05 | 2022-10-18 | 73
0 | PPBKIN1040 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - TEMPERATURE GAUGES | 10 | 2022-07-05 | 2022-07-22 | 2022-10-19 | 2022-11-01 | 73
0 | PPBKIN1045 | RECEIVE TBE COMPANY APPROVAL - TEMPERATURE GAUGES | 10 | 2022-07-22 | 2022-08-05 | 2022-11-02 | 2022-11-15 | 73
0 | PPBKIN1050 | COMPLETE CBE / ISSUE ROA - TEMPERATURE GAUGES | 1 | 2022-08-05 | 2022-08-08 | 2022-11-16 | 2022-11-16 | 73
0 | PPBKIN1055 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - TEMPERATURE GAUGES | 11 | 2022-08-08 | 2022-08-23 | 2022-11-17 | 2022-12-05 | 73
0 | PPBKIN1057 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - TEMPERATURE GAUGES | 178 | 2022-08-23 | 2023-05-04 | 2022-12-06 | 2023-08-18 | 73
0 | PMBKIN2780 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - TEMPERATURE GAUGES | 7 | 2023-05-04 | 2023-05-11 | 2023-08-21 | 2023-08-28 | 109
TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) |  |  | 345 | 2022-04-25 | 2023-04-05 | 2022-09-15 | 2023-08-28 | 145
0 | PPBKIN1060 | PREPARE RFQ & FLOAT ENQUIRY - TANSMITTERS (PT, PDT, TT, FT, DP TYPE) | 3 | 2022-04-25 | 2022-04-28 | 2022-09-15 | 2022-09-19 | 97
0 | PPBKIN1065 | RECEIVE OFFERS - TANSMITTERS (PT, PDT, TT, FT, DP TYPE) | 15 | 2022-04-28 | 2022-05-24 | 2022-09-20 | 2022-10-10 | 97
0 | PPBKIN1070 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - TANSMITTERS (PT, PDT, TT, FT, DP TYPE) | 15 | 2022-05-24 | 2022-06-14 | 2022-10-11 | 2022-10-31 | 97
0 | PPBKIN1075 | RECEIVE TBE COMPANY APPROVAL - TANSMITTERS (PT, PDT, TT, FT, DP TYPE) | 10 | 2022-06-14 | 2022-06-28 | 2022-11-01 | 2022-11-14 | 97
0 | PPBKIN1080 | COMPLETE CBE / ISSUE ROA - TANSMITTERS (PT, PDT, TT, FT, DP TYPE) | 1 | 2022-06-28 | 2022-06-29 | 2022-11-15 | 2022-11-15 | 97
0 | PPBKIN1085 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - TANSMITTERS (PT, PDT, TT, FT, DP TYPE) | 11 | 2022-06-29 | 2022-07-19 | 2022-11-16 | 2022-11-30 | 97
0 | PPBKIN1087 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - TANSMITTERS (PT, PDT, TT, FT, DP TYPE) | 179 | 2022-07-19 | 2023-03-29 | 2022-12-05 | 2023-08-18 | 97
0 | PMBKIN2760 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) | 7 | 2023-03-29 | 2023-04-05 | 2023-08-21 | 2023-08-28 | 145
PIG SIGNALLER |  |  | 303 | 2022-06-14 | 2023-04-13 | 2022-10-24 | 2023-08-28 | 137
0 | PPBKIN1090 | PREPARE RFQ & FLOAT ENQUIRY - PIG SIGNALLER | 5 | 2022-06-14 | 2022-06-21 | 2022-10-24 | 2022-10-28 | 91
0 | PPBKIN1095 | RECEIVE OFFERS - PIG SIGNALLER | 15 | 2022-06-21 | 2022-07-15 | 2022-10-31 | 2022-11-18 | 91
0 | PPBKIN1100 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIG SIGNALLER | 15 | 2022-07-15 | 2022-08-05 | 2022-11-21 | 2022-12-13 | 91
0 | PPBKIN1105 | RECEIVE TBE COMPANY APPROVAL - PIG SIGNALLER | 10 | 2022-08-05 | 2022-08-19 | 2022-12-14 | 2022-12-27 | 91
0 | PPBKIN1110 | COMPLETE CBE / ISSUE ROA - PIG SIGNALLER | 1 | 2022-08-19 | 2022-08-22 | 2022-12-28 | 2022-12-28 | 91
0 | PPBKIN1115 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIG SIGNALLER | 11 | 2022-08-22 | 2022-09-06 | 2022-12-29 | 2023-01-12 | 91
0 | PPBKIN1117 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIG SIGNALLER | 150 | 2022-09-06 | 2023-04-06 | 2023-01-13 | 2023-08-18 | 91
0 | PMBKIN2820 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - PIG SIGNALLER | 7 | 2023-04-06 | 2023-04-13 | 2023-08-21 | 2023-08-28 | 137
THERMAL FLOW SWITCH |  |  | 287 | 2022-06-16 | 2023-03-30 | 2022-11-08 | 2023-08-28 | 151
0 | PPBKIN1120 | PREPARE RFQ & FLOAT ENQUIRY - THERMAL FLOW SWITCH | 3 | 2022-06-16 | 2022-06-21 | 2022-11-08 | 2022-11-10 | 100
0 | PPBKIN1125 | RECEIVE OFFERS - THERMAL FLOW SWITCH | 15 | 2022-06-21 | 2022-07-15 | 2022-11-11 | 2022-12-05 | 100
0 | PPBKIN1130 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - THERMAL FLOW SWITCH | 15 | 2022-07-15 | 2022-08-05 | 2022-12-06 | 2022-12-26 | 100
0 | PPBKIN1135 | RECEIVE TBE COMPANY APPROVAL - THERMAL FLOW SWITCH | 10 | 2022-08-05 | 2022-08-19 | 2022-12-27 | 2023-01-09 | 100
0 | PPBKIN1140 | COMPLETE CBE / ISSUE ROA - THERMAL FLOW SWITCH | 1 | 2022-08-19 | 2022-08-22 | 2023-01-10 | 2023-01-10 | 100
0 | PPBKIN1145 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - THERMAL FLOW SWITCH | 11 | 2022-08-22 | 2022-09-06 | 2023-01-11 | 2023-01-25 | 100
0 | PPBKIN1147 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - THERMAL FLOW SWITCH | 140 | 2022-09-06 | 2023-03-23 | 2023-01-27 | 2023-08-18 | 101
0 | PMBKIN2770 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - THERMAL FLOW SWITCH | 7 | 2023-03-23 | 2023-03-30 | 2023-08-21 | 2023-08-28 | 151
GWR & RADAR TYPE LEVEL TRANSMITTER |  |  | 331 | 2022-05-09 | 2023-04-05 | 2022-09-26 | 2023-08-28 | 145
0 | PPBKIN1150 | PREPARE RFQ & FLOAT ENQUIRY - GWR & RADAR TYPE LEVEL TRANSMITTER | 5 | 2022-05-09 | 2022-05-16 | 2022-09-26 | 2022-09-30 | 97
0 | PPBKIN1155 | RECEIVE OFFERS - GWR & RADAR TYPE LEVEL TRANSMITTER | 10 | 2022-05-16 | 2022-05-30 | 2022-10-03 | 2022-10-14 | 97
0 | PPBKIN1160 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - GWR & RADAR TYPE LEVEL TRANSMITTER | 10 | 2022-05-30 | 2022-06-13 | 2022-10-17 | 2022-10-28 | 97
0 | PPBKIN1165 | RECEIVE TBE COMPANY APPROVAL - GWR & RADAR TYPE LEVEL TRANSMITTER | 10 | 2022-06-13 | 2022-06-27 | 2022-10-31 | 2022-11-11 | 97
0 | PPBKIN1170 | COMPLETE CBE / ISSUE ROA - GWR & RADAR TYPE LEVEL TRANSMITTER | 1 | 2022-06-27 | 2022-06-28 | 2022-11-14 | 2022-11-14 | 97
0 | PPBKIN1175 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - GWR & RADAR TYPE LEVEL TRANSMITTER | 11 | 2022-06-28 | 2022-07-18 | 2022-11-15 | 2022-11-29 | 97
0 | PPBKIN1177 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - GWR & RADAR TYPE LEVEL TRANSMITTER | 180 | 2022-07-18 | 2023-03-29 | 2022-11-30 | 2023-08-18 | 97
0 | PMBKIN2880 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE)- GWR & RADAR TYPE LEVEL TRANSMITTER | 7 | 2023-03-29 | 2023-04-05 | 2023-08-21 | 2023-08-28 | 145
MAGNETIC LEVEL GAUGE |  |  | 333 | 2022-05-06 | 2023-04-04 | 2022-09-26 | 2023-08-28 | 146
0 | PPBKIN1180 | PREPARE RFQ & FLOAT ENQUIRY - MAGNETIC LEVEL GAUGE | 5 | 2022-05-06 | 2022-05-13 | 2022-09-26 | 2022-09-30 | 98
0 | PPBKIN1185 | RECEIVE OFFERS - MAGNETIC LEVEL GAUGE | 10 | 2022-05-13 | 2022-05-27 | 2022-10-03 | 2022-10-14 | 98
0 | PPBKIN1190 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - MAGNETIC LEVEL GAUGE | 10 | 2022-05-27 | 2022-06-10 | 2022-10-17 | 2022-10-28 | 98
0 | PPBKIN1195 | RECEIVE TBE COMPANY APPROVAL - MAGNETIC LEVEL GAUGE | 10 | 2022-06-10 | 2022-06-24 | 2022-10-31 | 2022-11-11 | 98
0 | PPBKIN1200 | COMPLETE CBE / ISSUE ROA - MAGNETIC LEVEL GAUGE | 1 | 2022-06-24 | 2022-06-27 | 2022-11-14 | 2022-11-14 | 98
0 | PPBKIN1205 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - MAGNETIC LEVEL GAUGE | 11 | 2022-06-27 | 2022-07-15 | 2022-11-15 | 2022-11-29 | 98
0 | PPBKIN1207 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - MAGNETIC LEVEL GAUGE | 180 | 2022-07-15 | 2023-03-28 | 2022-11-30 | 2023-08-18 | 98
0 | PMBKIN2830 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - MAGNETIC LEVEL GAUGE | 7 | 2023-03-28 | 2023-04-04 | 2023-08-21 | 2023-08-28 | 146
FLOW RESTRICTION ORIFICE |  |  | 321 | 2022-04-29 | 2023-03-16 | 2022-09-20 | 2023-08-28 | 165
0 | PPBKIN1210 | PREPARE RFQ & FLOAT ENQUIRY - FLOW RESTRICTION ORIFICE | 5 | 2022-04-29 | 2022-05-11 | 2022-09-20 | 2022-09-26 | 96
0 | PPBKIN1215 | RECEIVE OFFERS - FLOW RESTRICTION ORIFICE | 10 | 2022-05-11 | 2022-05-25 | 2022-09-27 | 2022-10-10 | 96
0 | PPBKIN1220 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - FLOW RESTRICTION ORIFICE | 10 | 2022-06-01 | 2022-06-15 | 2022-10-11 | 2022-10-24 | 91
0 | PPBKIN1225 | RECEIVE TBE COMPANY APPROVAL - FLOW RESTRICTION ORIFICE | 10 | 2022-06-15 | 2022-06-29 | 2022-10-25 | 2022-11-07 | 91
0 | PPBKIN1230 | COMPLETE CBE / ISSUE ROA - FLOW RESTRICTION ORIFICE | 1 | 2022-07-06 | 2022-07-07 | 2022-11-08 | 2022-11-08 | 86
0 | PPBKIN1235 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - FLOW RESTRICTION ORIFICE | 11 | 2022-07-07 | 2022-07-27 | 2022-11-09 | 2022-11-23 | 86
0 | PPBKIN1237 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - FLOW RESTRICTION ORIFICE | 159 | 2022-07-27 | 2023-03-09 | 2023-01-02 | 2023-08-18 | 111
0 | PMBKIN2890 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - FLOW RESTRICTION ORIFICE | 7 | 2023-03-09 | 2023-03-16 | 2023-08-21 | 2023-08-28 | 165
ULTRASONIC FLOW METER |  |  | 349 | 2022-04-14 | 2023-03-29 | 2022-07-04 | 2023-08-28 | 152
0 | PPBKIN1240 | PREPARE RFQ & FLOAT ENQUIRY - ULTRASONIC FLOW METER | 2 | 2022-04-14 | 2022-04-18 | 2022-07-04 | 2022-07-05 | 54
0 | PPBKIN1245 | RECEIVE OFFERS - ULTRASONIC FLOW METER | 10 | 2022-04-18 | 2022-05-05 | 2022-07-06 | 2022-07-22 | 54
0 | PPBKIN1250 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - ULTRASONIC FLOW METER | 10 | 2022-05-05 | 2022-05-19 | 2022-07-25 | 2022-08-05 | 54
0 | PPBKIN1255 | RECEIVE TBE COMPANY APPROVAL - ULTRASONIC FLOW METER | 10 | 2022-05-19 | 2022-06-02 | 2022-08-08 | 2022-08-19 | 54
0 | PPBKIN1260 | COMPLETE CBE / ISSUE ROA - ULTRASONIC FLOW METER | 1 | 2022-06-02 | 2022-06-03 | 2022-08-22 | 2022-08-22 | 54
0 | PPBKIN1265 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - ULTRASONIC FLOW METER | 11 | 2022-06-03 | 2022-06-20 | 2022-08-23 | 2022-09-06 | 54
0 | PPBKIN1267 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - ULTRASONIC FLOW METER | 192 | 2022-06-20 | 2023-03-22 | 2022-11-14 | 2023-08-18 | 102
0 | PMBKIN2750 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - ULTRASONIC FLOW METER | 7 | 2023-03-22 | 2023-03-29 | 2023-08-21 | 2023-08-28 | 152
FIRE & GAS DETECTORS / DEVICES |  |  | 305 | 2022-05-20 | 2023-03-21 | 2022-11-14 | 2023-08-28 | 160
0 | PPBKIN1270 | PREPARE RFQ & FLOAT ENQUIRY - FIRE & GAS DETECTORS/ DEVICES | 3 | 2022-05-20 | 2022-05-25 | 2022-11-14 | 2022-11-16 | 123
0 | PPBKIN1275 | RECEIVE OFFERS - FIRE & GAS DETECTORS/ DEVICES | 10 | 2022-05-25 | 2022-06-08 | 2022-11-17 | 2022-11-30 | 123
0 | PPBKIN1280 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - FIRE & GAS DETECTORS/ DEVICES | 10 | 2022-07-01 | 2022-07-20 | 2022-12-05 | 2022-12-16 | 106
0 | PPBKIN1285 | RECEIVE TBE COMPANY APPROVAL - FIRE & GAS DETECTORS/ DEVICES | 10 | 2022-07-20 | 2022-08-03 | 2022-12-19 | 2022-12-30 | 106
0 | PPBKIN1290 | COMPLETE CBE / ISSUE ROA - FIRE & GAS DETECTORS/ DEVICES | 1 | 2022-08-03 | 2022-08-04 | 2023-01-02 | 2023-01-02 | 106
0 | PPBKIN1295 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - FIRE & GAS DETECTORS/ DEVICES | 11 | 2022-08-04 | 2022-08-19 | 2023-01-03 | 2023-01-17 | 106
0 | PPBKIN1297 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - FIRE & GAS DETECTORS/ DEVICES | 145 | 2022-08-19 | 2023-03-14 | 2023-01-20 | 2023-08-18 | 108
0 | PMBKIN2910 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - FIRE & GAS DETECTORS / DEVICES | 7 | 2023-03-14 | 2023-03-21 | 2023-08-21 | 2023-08-28 | 160
PRESSURE RELIEF VALVES |  |  | 354 | 2022-04-18 | 2023-04-07 | 2022-09-06 | 2023-08-28 | 143
0 | PPBKIN1300 | PREPARE RFQ & FLOAT ENQUIRY - PRESSURE RELIFE VALVES | 3 | 2022-04-18 | 2022-04-21 | 2022-09-06 | 2022-09-08 | 95
0 | PPBKIN1305 | RECEIVE OFFERS - PRESSURE RELIFE VALVES | 15 | 2022-04-21 | 2022-05-17 | 2022-09-09 | 2022-09-29 | 95
0 | PPBKIN1310 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PRESSURE RELIFE VALVES | 15 | 2022-05-25 | 2022-06-15 | 2022-10-10 | 2022-10-28 | 95
0 | PPBKIN1315 | RECEIVE TBE COMPANY APPROVAL - PRESSURE RELIFE VALVES | 10 | 2022-06-15 | 2022-06-29 | 2022-10-31 | 2022-11-11 | 95
0 | PPBKIN1320 | COMPLETE CBE / ISSUE ROA - PRESSURE RELIFE VALVES | 1 | 2022-06-29 | 2022-06-30 | 2022-11-14 | 2022-11-14 | 95
0 | PPBKIN1325 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PRESSURE RELIFE VALVES | 11 | 2022-06-30 | 2022-07-20 | 2022-11-15 | 2022-11-29 | 95
0 | PPBKIN1327 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PRESSURE RELIFE VALVES | 180 | 2022-07-20 | 2023-03-31 | 2022-11-30 | 2023-08-18 | 95
0 | PMBKIN2800 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE)- PRESSURE RELIEF VALVES | 7 | 2023-03-31 | 2023-04-07 | 2023-08-21 | 2023-08-28 | 143
CORROSION MONITORING DEVICES |  |  | 313 | 2022-05-24 | 2023-04-02 | 2022-10-19 | 2023-08-28 | 148
0 | PPBKIN1360 | PREPARE RFQ & FLOAT ENQUIRY - CORROSION MONITORING DEVICES | 3 | 2022-05-24 | 2022-05-27 | 2022-10-19 | 2022-10-21 | 103
0 | PPBKIN1365 | RECEIVE OFFERS - CORROSION MONITORING DEVICES | 15 | 2022-05-27 | 2022-06-17 | 2022-10-24 | 2022-11-11 | 103
0 | PPBKIN1370 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - CORROSION MONITORING DEVICES | 10 | 2022-06-17 | 2022-07-01 | 2022-11-14 | 2022-11-25 | 103
0 | PPBKIN1375 | RECEIVE TBE COMPANY APPROVAL - CORROSION MONITORING DEVICES | 10 | 2022-07-01 | 2022-07-20 | 2022-11-28 | 2022-12-13 | 103
0 | PPBKIN1380 | COMPLETE CBE / ISSUE ROA - CORROSION MONITORING DEVICES | 1 | 2022-07-20 | 2022-07-21 | 2022-12-14 | 2022-12-14 | 103
0 | PPBKIN1385 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - CORROSION MONITORING DEVICES | 11 | 2022-07-21 | 2022-08-05 | 2022-12-15 | 2022-12-29 | 103
0 | PPBKIN1387 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - CORROSION MONITORING DEVICES | 160 | 2022-08-05 | 2023-03-21 | 2022-12-30 | 2023-08-18 | 103
0 | PMBKIN2920 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - CORROSION MONITORING DEVICES | 7 | 2023-03-26 | 2023-04-02 | 2023-08-21 | 2023-08-28 | 148
INSTRUMENT CABLE GLANDS |  |  | 262 | 2022-07-19 | 2023-04-07 | 2022-11-23 | 2023-08-31 | 146
0 | PPBKIN1390 | PREPARE RFQ & FLOAT ENQUIRY - INSTRUMENT CABLE GLANDS | 2 | 2022-07-19 | 2022-07-21 | 2022-11-23 | 2022-11-24 | 91
0 | PPBKIN1395 | RECEIVE OFFERS - INSTRUMENT CABLE GLANDS | 10 | 2022-07-21 | 2022-08-04 | 2022-11-25 | 2022-12-12 | 91
0 | PPBKIN1400 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - INSTRUMENT CABLE GLANDS | 10 | 2022-08-04 | 2022-08-18 | 2022-12-13 | 2022-12-26 | 91
0 | PPBKIN1405 | RECEIVE TBE COMPANY APPROVAL - INSTRUMENT CABLE GLANDS | 10 | 2022-08-18 | 2022-09-01 | 2022-12-27 | 2023-01-09 | 91
0 | PPBKIN1410 | COMPLETE CBE / ISSUE ROA - INSTRUMENT CABLE GLANDS | 1 | 2022-09-01 | 2022-09-02 | 2023-01-10 | 2023-01-10 | 91
0 | PPBKIN1415 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - INSTRUMENT CABLE GLANDS | 11 | 2022-09-02 | 2022-09-19 | 2023-01-11 | 2023-01-25 | 91
0 | PPBKIN1417 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - INSTRUMENT CABLE GLANDS | 136 | 2022-09-19 | 2023-03-30 | 2023-02-07 | 2023-08-23 | 99
0 | PMBKIN2940 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - INSTRUMENT CABLE GLANDS | 7 | 2023-03-31 | 2023-04-07 | 2023-08-24 | 2023-08-31 | 146
INSTRUMENT & CONTROL, FO AND TELECOMMUNICATION CABLES |  |  | 284 | 2022-07-14 | 2023-04-24 | 2022-11-01 | 2023-08-14 | 112
0 | PPBKIN1420 | PREPARE RFQ & FLOAT ENQUIRY - INST'NT/ CONTROL & FO AND COMMUNICATION CABLES | 3 | 2022-07-14 | 2022-07-19 | 2022-11-01 | 2022-11-03 | 78
0 | PPBKIN1425 | RECEIVE OFFERS - INST'NT/ CONTROL & FO AND COMMUNICATION CABLES | 10 | 2022-07-19 | 2022-08-02 | 2022-11-04 | 2022-11-17 | 78
0 | PPBKIN1430 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL RECEIVE APPROVAL - INST'NT/ CONTROL & FO AN COMMUNICATION CABLES | 10 | 2022-08-02 | 2022-08-16 | 2022-11-18 | 2022-12-05 | 78
0 | PPBKIN1435 | RECEIVE TBE COMPANY APPROVAL - INST'NT/ CONTROL& FO ANDCOMMUNICATION CABLES | 10 | 2022-08-16 | 2022-08-30 | 2022-12-06 | 2022-12-19 | 78
0 | PPBKIN1440 | COMPLETE CBE / ISSUE ROA - INST'NT/ CONTROL & FO AND COMMUNICATION CABLES | 1 | 2022-08-30 | 2022-08-31 | 2022-12-20 | 2022-12-20 | 78
0 | PPBKIN1445 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - INST'NT/ CONTROL & COMMUNICATION CABLES | 11 | 2022-08-31 | 2022-09-15 | 2022-12-21 | 2023-01-04 | 78
0 | PPBKIN1447 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - INST'NT/ CONTROL & COMMUNICATION CABLES | 130 | 2022-09-15 | 2023-03-20 | 2023-01-27 | 2023-08-04 | 94
0 | PMBKIN2870 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - INSTRUMENT & FO AND CONTROL AND TELECOMMUNICATION CABLES | 7 | 2023-04-17 | 2023-04-24 | 2023-08-07 | 2023-08-14 | 112
INSTRUMENT BULK MATERIAL |  |  | 296 | 2022-06-15 | 2023-04-07 | 2022-10-25 | 2023-08-14 | 129
0 | PPBKIN1480 | PREPARE RFQ & FLOAT ENQUIRY - INSTRUMENT BULK MATERIALS | 3 | 2022-06-15 | 2022-06-20 | 2022-10-25 | 2022-10-27 | 91
0 | PPBKIN1485 | RECEIVE OFFERS - INSTRUMENT BULK MATERIALS | 10 | 2022-06-20 | 2022-07-04 | 2022-10-28 | 2022-11-10 | 91
0 | PPBKIN1490 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - INSTRUMENT BULK MATERIALS | 15 | 2022-07-04 | 2022-07-28 | 2022-11-11 | 2022-12-05 | 91
0 | PPBKIN1495 | RECEIVE TBE COMPANY APPROVAL - INSTRUMENT BULK MATERIALS | 10 | 2022-07-28 | 2022-08-11 | 2022-12-06 | 2022-12-19 | 91
0 | PPBKIN1500 | COMPLETE CBE / ISSUE ROA - INSTRUMENT BULK MATERIALS | 1 | 2022-08-11 | 2022-08-12 | 2022-12-20 | 2022-12-20 | 91
0 | PPBKIN1505 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - INSTRUMENT BULK MATERIALS | 11 | 2022-08-12 | 2022-08-29 | 2022-12-21 | 2023-01-04 | 91
0 | PPBKIN1507 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - INSTRUMENT BULK MATERIALS | 140 | 2022-08-29 | 2023-03-15 | 2023-01-13 | 2023-08-04 | 97
0 | PMBKIN2860 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - INSTRUMENT BULK MATERIAL | 7 | 2023-03-31 | 2023-04-07 | 2023-08-07 | 2023-08-14 | 129
INSTRUMENT SUN SHADES |  |  | 303 | 2022-06-20 | 2023-04-19 | 2022-10-24 | 2023-08-28 | 131
0 | PPBKIN1510 | PREPARE RFQ & FLOAT ENQUIRY - INSTRUMENT SUN SHADES | 5 | 2022-06-20 | 2022-06-27 | 2022-10-24 | 2022-10-28 | 87
0 | PPBKIN1515 | RECEIVE OFFERS - INSTRUMENT SUN SHADES | 15 | 2022-06-27 | 2022-07-21 | 2022-10-31 | 2022-11-18 | 87
0 | PPBKIN1520 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - INSTRUMENT SUN SHADES | 10 | 2022-07-21 | 2022-08-04 | 2022-11-21 | 2022-12-06 | 87
0 | PPBKIN1525 | RECEIVE TBE COMPANY APPROVAL - INSTRUMENT SUN SHADES | 10 | 2022-08-04 | 2022-08-18 | 2022-12-07 | 2022-12-20 | 87
0 | PPBKIN1530 | COMPLETE CBE / ISSUE ROA - INSTRUMENT SUN SHADES | 1 | 2022-08-18 | 2022-08-19 | 2022-12-21 | 2022-12-21 | 87
0 | PPBKIN1535 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - INSTRUMENT SUN SHADES | 11 | 2022-08-19 | 2022-09-05 | 2022-12-22 | 2023-01-05 | 87
0 | PPBKIN1537 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - INSTRUMENT SUN SHADES | 155 | 2022-09-05 | 2023-04-12 | 2023-01-06 | 2023-08-18 | 87
0 | PMBKIN2850 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - INSTRUMENT SUN SHADES | 7 | 2023-04-12 | 2023-04-19 | 2023-08-21 | 2023-08-28 | 131
JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM |  |  | 364 | 2022-05-18 | 2023-05-17 | 2022-09-06 | 2023-12-09 | 207
0 | PPBKIN1570 | PREPARE RFQ & FLOAT ENQUIRY - JUNCTION /MARSHAKKING BOXES INSTRUMENT & TELECOM | 5 | 2022-05-18 | 2022-05-25 | 2022-09-06 | 2022-09-12 | 76
0 | PPBKIN1575 | RECEIVE OFFERS - JUNCTION /MARSHAKKING BOXES INSTRUMENT & TELECOM | 15 | 2022-05-25 | 2022-06-15 | 2022-09-13 | 2022-10-03 | 76
0 | PPBKIN1580 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - JUNCTION /MARSHAKKING BOXES INSTRUMENT & TELECOM | 15 | 2022-06-15 | 2022-07-06 | 2022-10-31 | 2022-11-18 | 95
0 | PPBKIN1585 | RECEIVE TBE COMPANY APPROVAL - JUNCTION /MARSHAKKING BOXES INSTRUMENT & TELECOM | 10 | 2022-07-06 | 2022-07-25 | 2022-11-21 | 2022-12-06 | 95
0 | PPBKIN1590 | COMPLETE CBE / ISSUE ROA - JUNCTION /MARSHAKKING BOXES INSTRUMENT & TELECOM | 1 | 2022-07-25 | 2022-07-26 | 2022-12-07 | 2022-12-07 | 95
0 | PPBKIN1595 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - JUNCTION /MARSHAKKING BOXES INSTRUMENT & TELECOM | 11 | 2022-07-26 | 2022-08-10 | 2022-12-08 | 2022-12-22 | 95
0 | PPBKIN1597 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - JUNCTION /MARSHAKKING BOXES INSTRUMENT & TELECOM | 190 | 2022-08-10 | 2023-05-09 | 2022-12-23 | 2023-09-22 | 95
0 | PMBKIN2840 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM | 7 | 2023-05-10 | 2023-05-17 | 2023-12-02 | 2023-12-09 | 206
E&I STRUCTURAL STEEL |  |  | 235 | 2022-06-09 | 2023-01-30 | 2022-10-18 | 2023-10-04 | 247
0 | PPBKIN1600 | PREPARE RFQ & FLOAT ENQUIRY - E&I STRUCTURAL STEEL | 5 | 2022-06-09 | 2022-06-16 | 2022-10-18 | 2022-10-24 | 90
0 | PPBKIN1605 | RECEIVE OFFERS - E&I STRUCTURAL STEEL | 15 | 2022-06-16 | 2022-07-07 | 2022-10-25 | 2022-11-14 | 90
0 | PPBKIN1610 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - E&I STRUCTURAL STEEL | 15 | 2022-07-07 | 2022-08-02 | 2022-11-15 | 2022-12-07 | 90
0 | PPBKIN1615 | RECEIVE TBE COMPANY APPROVAL - E&I STRUCTURAL STEEL | 10 | 2022-08-02 | 2022-08-16 | 2022-12-08 | 2022-12-21 | 90
0 | PPBKIN1620 | COMPLETE CBE / ISSUE ROA - E&I STRUCTURAL STEEL | 1 | 2022-08-16 | 2022-08-17 | 2022-12-22 | 2022-12-22 | 90
0 | PPBKIN1625 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - E&I STRUCTURAL STEEL | 11 | 2022-08-17 | 2022-09-01 | 2022-12-23 | 2023-01-06 | 90
0 | PPBKIN1627 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - E&I STRUCTURAL STEEL | 100 | 2022-09-01 | 2023-01-23 | 2023-05-01 | 2023-09-21 | 168
0 | PMBKIN2740 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - E&I STRUCTURAL STEEL | 7 | 2023-01-23 | 2023-01-30 | 2023-09-27 | 2023-10-04 | 247
ELECTRICAL |  |  | 278 | 2022-08-08 | 2023-05-13 | 2022-11-14 | 2023-11-08 | 179
HIGH VOLTAGE CABLES |  |  | 278 | 2022-08-08 | 2023-05-13 | 2022-11-14 | 2023-11-01 | 172
0 | PPBKEL1000 | PREPARE RFQ & FLOAT ENQUIRY - HIGH VOLTAGE CABLES | 5 | 2022-08-08 | 2022-08-15 | 2022-11-14 | 2022-11-18 | 70
0 | PPBKEL1005 | RECEIVE OFFERS - HIGH VOLTAGE CABLES | 15 | 2022-08-15 | 2022-09-05 | 2022-11-21 | 2022-12-13 | 70
0 | PPBKEL1010 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - HIGH VOLTAGE CABLES | 15 | 2022-09-05 | 2022-09-26 | 2022-12-14 | 2023-01-03 | 70
0 | PPBKEL1015 | RECEIVE TBE COMPANY APPROVAL - HIGH VOLTAGE CABLES | 10 | 2022-09-26 | 2022-10-10 | 2023-01-04 | 2023-01-17 | 70
0 | PPBKEL1020 | COMPLETE CBE / ISSUE ROA - HIGH VOLTAGE CABLES | 1 | 2022-10-10 | 2022-10-11 | 2023-01-18 | 2023-01-18 | 70
0 | PPBKEL1025 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - HIGH VOLTAGE CABLES | 11 | 2022-10-11 | 2022-10-26 | 2023-01-19 | 2023-02-02 | 70
0 | PPBKEL1027 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - HIGH VOLTAGE CABLES | 133 | 2022-10-26 | 2023-05-05 | 2023-04-12 | 2023-10-24 | 118
0 | PMBKEL2435 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE)- HIGH VOLTAGE CABLES | 7 | 2023-05-06 | 2023-05-13 | 2023-10-25 | 2023-11-01 | 172
LOW VOLTAGE CABLES |  |  | 270 | 2022-08-08 | 2023-05-05 | 2022-11-21 | 2023-11-01 | 180
0 | PPBKEL1030 | PREPARE RFQ & FLOAT ENQUIRY - LOW VOLTAGE CABLES | 5 | 2022-08-08 | 2022-08-15 | 2022-11-21 | 2022-11-25 | 75
0 | PPBKEL1035 | RECEIVE OFFERS - LOW VOLTAGE CABLES | 15 | 2022-08-15 | 2022-09-05 | 2022-11-28 | 2022-12-20 | 75
0 | PPBKEL1040 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - LOW VOLTAGE CABLES | 15 | 2022-09-05 | 2022-09-26 | 2022-12-21 | 2023-01-10 | 75
0 | PPBKEL1045 | RECEIVE TBE COMPANY APPROVAL - LOW VOLTAGE CABLES | 10 | 2022-09-26 | 2022-10-10 | 2023-01-11 | 2023-01-24 | 75
0 | PPBKEL1050 | COMPLETE CBE / ISSUE ROA - LOW VOLTAGE CABLES | 1 | 2022-10-10 | 2022-10-11 | 2023-01-25 | 2023-01-25 | 75
0 | PPBKEL1055 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - LOW VOLTAGE CABLES | 11 | 2022-10-11 | 2022-10-26 | 2023-01-26 | 2023-02-09 | 75
0 | PPBKEL1057 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - LOW VOLTAGE CABLES | 128 | 2022-10-26 | 2023-04-28 | 2023-04-19 | 2023-10-24 | 123
0 | PMBKEL2425 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE)- LOW VOLTAGE CABLES | 7 | 2023-04-28 | 2023-05-05 | 2023-10-25 | 2023-11-01 | 180
CABLE TRAYS & LADDERS |  |  | 244 | 2022-08-08 | 2023-04-09 | 2022-11-29 | 2023-10-18 | 192
0 | PPBKEL1060 | PREPARE RFQ & FLOAT ENQUIRY - CABLE TRAYS & LADDERS | 5 | 2022-08-08 | 2022-08-15 | 2022-11-29 | 2022-12-07 | 81
0 | PPBKEL1065 | RECEIVE OFFERS - CABLE TRAYS & LADDERS | 15 | 2022-08-15 | 2022-09-05 | 2022-12-08 | 2022-12-28 | 81
0 | PPBKEL1070 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - CABLE TRAYS & LADDERS | 15 | 2022-09-05 | 2022-09-26 | 2022-12-29 | 2023-01-18 | 81
0 | PPBKEL1075 | RECEIVE TBE COMPANY APPROVAL - CABLE TRAYS & LADDERS | 10 | 2022-09-26 | 2022-10-10 | 2023-01-19 | 2023-02-01 | 81
0 | PPBKEL1080 | COMPLETE CBE / ISSUE ROA - CABLE TRAYS & LADDERS | 1 | 2022-10-10 | 2022-10-11 | 2023-02-02 | 2023-02-02 | 81
0 | PPBKEL1085 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - CABLE TRAYS & LADDERS | 11 | 2022-10-11 | 2022-10-26 | 2023-02-03 | 2023-02-17 | 81
0 | PPBKEL1087 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - CABLE TRAYS & LADDERS | 110 | 2022-10-26 | 2023-03-31 | 2023-04-27 | 2023-10-04 | 127
0 | PMBKEL2415 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - CABLE TRAYS & LADDERS | 7 | 2023-04-02 | 2023-04-09 | 2023-10-11 | 2023-10-18 | 192
LIGHTING FIXTURES & ACCESSORIES |  |  | 256 | 2022-08-09 | 2023-04-22 | 2022-12-13 | 2023-10-25 | 186
0 | PPBKEL1090 | PREPARE RFQ & FLOAT ENQUIRY - LIGHTING FIXTURE & ACCESSORIES | 3 | 2022-08-09 | 2022-08-12 | 2022-12-13 | 2022-12-15 | 88
0 | PPBKEL1095 | RECEIVE OFFERS - LIGHTING FIXTURE & ACCESSORIES | 15 | 2022-08-12 | 2022-09-02 | 2022-12-16 | 2023-01-05 | 88
0 | PPBKEL1100 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - LIGHTING FIXTURE & ACCESSORIES | 15 | 2022-09-02 | 2022-09-23 | 2023-01-06 | 2023-01-26 | 88
0 | PPBKEL1105 | RECEIVE TBE COMPANY APPROVAL - LIGHTING FIXTURE & ACCESSORIES | 10 | 2022-09-23 | 2022-10-07 | 2023-01-27 | 2023-02-09 | 88
0 | PPBKEL1110 | COMPLETE CBE / ISSUE ROA - LIGHTING FIXTURE & ACCESSORIES | 1 | 2022-10-07 | 2022-10-10 | 2023-02-10 | 2023-02-10 | 88
0 | PPBKEL1115 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - LIGHTING FIXTURE & ACCESSORIES | 11 | 2022-10-10 | 2022-10-25 | 2023-02-13 | 2023-02-27 | 88
0 | PPBKEL1117 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - LIGHTING FIXTURE & ACCESSORIES | 121 | 2022-10-25 | 2023-04-14 | 2023-04-25 | 2023-10-17 | 126
0 | PMBKEL2405 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - LIGHTING FIXTURES & ACCESSORIES | 7 | 2023-04-15 | 2023-04-22 | 2023-10-18 | 2023-10-25 | 186
CABLE GLANDS |  |  | 267 | 2022-08-11 | 2023-05-05 | 2022-12-12 | 2023-11-08 | 187
0 | PPBKEL1120 | PREPARE RFQ & FLOAT ENQUIRY - ELECTRICAL CABLE GLANDS | 5 | 2022-08-11 | 2022-08-18 | 2022-12-12 | 2022-12-16 | 85
0 | PPBKEL1125 | RECEIVE OFFERS - ELECTRICAL CABLE GLANDS | 15 | 2022-08-18 | 2022-09-08 | 2022-12-19 | 2023-01-06 | 85
0 | PPBKEL1130 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - ELECTRICAL CABLE GLANDS | 15 | 2022-09-08 | 2022-09-29 | 2023-01-09 | 2023-01-27 | 85
0 | PPBKEL1135 | RECEIVE TBE COMPANY APPROVAL - ELECTRICAL CABLE GLANDS | 10 | 2022-09-29 | 2022-10-13 | 2023-01-30 | 2023-02-10 | 85
0 | PPBKEL1140 | COMPLETE CBE / ISSUE ROA - ELECTRICAL CABLE GLANDS | 1 | 2022-10-13 | 2022-10-14 | 2023-02-13 | 2023-02-13 | 85
0 | PPBKEL1145 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - ELECTRICAL CABLE GLANDS | 11 | 2022-10-14 | 2022-10-31 | 2023-02-14 | 2023-02-28 | 85
0 | PPBKEL1147 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - ELECTRICAL CABLE GLANDS | 124 | 2022-10-31 | 2023-04-27 | 2023-05-04 | 2023-10-31 | 129
0 | PMBKEL2365 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - ELECTRICAL CABLE GLANDS | 7 | 2023-04-28 | 2023-05-05 | 2023-11-01 | 2023-11-08 | 187
JUNCTION BOXES |  |  | 260 | 2022-08-11 | 2023-04-28 | 2022-12-27 | 2023-11-08 | 194
0 | PPBKEL1150 | PREPARE RFQ & FLOAT ENQUIRY - ELECTRICAL JUNCTION BOXES | 5 | 2022-08-11 | 2022-08-18 | 2022-12-27 | 2023-01-02 | 96
0 | PPBKEL1155 | RECEIVE OFFERS - ELECTRICAL JUNCTION BOXES | 15 | 2022-08-18 | 2022-09-08 | 2023-01-03 | 2023-01-23 | 96
0 | PPBKEL1160 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - ELECTRICAL JUNCTION BOXES | 15 | 2022-09-08 | 2022-09-29 | 2023-01-24 | 2023-02-13 | 96
0 | PPBKEL1165 | RECEIVE TBE COMPANY APPROVAL - ELECTRICAL JUNCTION BOXES | 10 | 2022-09-29 | 2022-10-13 | 2023-02-14 | 2023-02-27 | 96
0 | PPBKEL1170 | COMPLETE CBE / ISSUE ROA - ELECTRICAL JUNCTION BOXES | 1 | 2022-10-13 | 2022-10-14 | 2023-02-28 | 2023-02-28 | 96
0 | PPBKEL1175 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - ELECTRICAL JUNCTION BOXES | 11 | 2022-10-14 | 2022-10-31 | 2023-03-01 | 2023-03-15 | 96
0 | PPBKEL1177 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - ELECTRICAL JUNCTION BOXES | 121 | 2022-10-31 | 2023-04-20 | 2023-04-28 | 2023-10-20 | 125
0 | PMBKEL2385 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - ELECTRICAL JUNCTION BOXES | 7 | 2023-04-21 | 2023-04-28 | 2023-11-01 | 2023-11-08 | 194
EARTHING MATERIAL & ACCESSORIES |  |  | 260 | 2022-08-11 | 2023-04-28 | 2023-01-16 | 2023-10-21 | 176
0 | PPBKEL1180 | PREPARE RFQ & FLOAT ENQUIRY - EARTHING MATERIALS & ACCESSOTIES | 5 | 2022-08-11 | 2022-08-18 | 2023-01-16 | 2023-01-20 | 110
0 | PPBKEL1185 | RECEIVE OFFERS- EARTHING MATERIALS & ACCESSOTIES | 15 | 2022-08-18 | 2022-09-08 | 2023-01-23 | 2023-02-10 | 110
0 | PPBKEL1190 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL- EARTHING MATERIALS & ACCESSOTIES | 15 | 2022-09-08 | 2022-09-29 | 2023-02-13 | 2023-03-03 | 110
0 | PPBKEL1195 | RECEIVE TBE COMPANY APPROVAL- EARTHING MATERIALS & ACCESSOTIES | 10 | 2022-09-29 | 2022-10-13 | 2023-03-06 | 2023-03-17 | 110
0 | PPBKEL1200 | COMPLETE CBE / ISSUE ROA - EARTHING MATERIALS & ACCESSOTIES | 1 | 2022-10-13 | 2022-10-14 | 2023-03-20 | 2023-03-20 | 110
0 | PPBKEL1205 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER- EARTHING MATERIALS & ACCESSOTIES | 11 | 2022-10-14 | 2022-10-31 | 2023-03-21 | 2023-04-04 | 110
0 | PPBKEL1207 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - EARTHING MATERIALS & ACCESSOTIES | 121 | 2022-10-31 | 2023-04-20 | 2023-04-19 | 2023-10-13 | 120
0 | PMBKEL2375 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - EARTHING MATERIAL & ACCESSORIES | 7 | 2023-04-21 | 2023-04-28 | 2023-10-14 | 2023-10-21 | 176
ELECTRICAL BOLTS & NUTS |  |  | 248 | 2022-08-15 | 2023-04-20 | 2022-12-15 | 2023-10-25 | 188
0 | PPBKEL1210 | PREPARE RFQ & FLOAT ENQUIRY - ELECTRICAL BOLTS & NUTS | 5 | 2022-08-15 | 2022-08-22 | 2022-12-15 | 2022-12-21 | 86
0 | PPBKEL1215 | RECEIVE OFFERS - ELECTRICAL BOLTS & NUTS | 15 | 2022-08-22 | 2022-09-12 | 2022-12-22 | 2023-01-11 | 86
0 | PPBKEL1220 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - ELECTRICAL BOLTS & NUTS | 15 | 2022-09-12 | 2022-10-03 | 2023-01-12 | 2023-02-01 | 86
0 | PPBKEL1225 | RECEIVE TBE COMPANY APPROVAL - ELECTRICAL BOLTS & NUTS | 10 | 2022-10-03 | 2022-10-17 | 2023-02-02 | 2023-02-15 | 86
0 | PPBKEL1230 | COMPLETE CBE / ISSUE ROA - ELECTRICAL BOLTS & NUTS | 1 | 2022-10-17 | 2022-10-18 | 2023-02-16 | 2023-02-16 | 86
0 | PPBKEL1235 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - ELECTRICAL BOLTS & NUTS | 11 | 2022-10-18 | 2022-11-02 | 2023-02-17 | 2023-03-03 | 86
0 | PPBKEL1237 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - ELECTRICAL BOLTS & NUTS | 114 | 2022-11-02 | 2023-04-13 | 2023-05-04 | 2023-10-17 | 127
0 | PMBKEL2355 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - ELECTRICAL BOLTS & NUTS | 7 | 2023-04-13 | 2023-04-20 | 2023-10-18 | 2023-10-25 | 188
HV CABLE TERMINATION KITS |  |  | 272 | 2022-08-08 | 2023-05-07 | 2022-11-23 | 2023-11-01 | 178
0 | PPEQEL1240 | PREPARE RFQ & FLOAT ENQUIRY - HV CABLES TERMINATION KITS | 5 | 2022-08-08 | 2022-08-15 | 2022-11-23 | 2022-11-29 | 77
0 | PPEQEL1245 | RECEIVE OFFERS - HV CABLES TERMINATION KITS | 15 | 2022-08-15 | 2022-09-05 | 2022-11-30 | 2022-12-22 | 77
0 | PPEQEL1250 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - HV CABLES TERMINATION KITS | 20 | 2022-09-05 | 2022-10-03 | 2022-12-23 | 2023-01-19 | 77
0 | PPEQEL1255 | RECEIVE TBE COMPANY APPROVAL - HV CABLES TERMINATION KITS | 10 | 2022-10-03 | 2022-10-17 | 2023-01-20 | 2023-02-02 | 77
0 | PPEQEL1260 | COMPLETE CBE / ISSUE ROA - HV CABLES TERMINATION KITS | 1 | 2022-10-17 | 2022-10-18 | 2023-02-03 | 2023-02-03 | 77
0 | PPEQEL1265 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - HV CABLES TERMINATION KITS | 11 | 2022-10-18 | 2022-11-02 | 2023-02-06 | 2023-02-20 | 77
0 | PPEQEL1267 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - HV CABLES TERMINATION KITS | 123 | 2022-11-02 | 2023-04-28 | 2023-04-28 | 2023-10-24 | 123
0 | PMEQEL2320 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - HV CABLES TERMINATION KITS | 7 | 2023-04-30 | 2023-05-07 | 2023-10-25 | 2023-11-01 | 178
SOCKETS & ISOLATING SWITCHES |  |  | 258 | 2022-08-10 | 2023-04-25 | 2023-01-02 | 2023-10-25 | 183
0 | PPBKEL1265 | PREPARE RFQ & FLOAT ENQUIRY - SOCKETS & ISOLATING SWITCHES | 5 | 2022-08-10 | 2022-08-17 | 2023-01-02 | 2023-01-06 | 101
0 | PPBKEL1270 | RECEIVE OFFERS - SOCKETS & ISOLATING SWITCHES | 15 | 2022-08-17 | 2022-09-07 | 2023-01-09 | 2023-01-27 | 101
0 | PPBKEL1275 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - SOCKETS & ISOLATING SWITCHES | 15 | 2022-09-07 | 2022-09-28 | 2023-01-30 | 2023-02-17 | 101
0 | PPBKEL1280 | RECEIVE TBE COMPANY APPROVAL - SOCKETS & ISOLATING SWITCHES | 10 | 2022-09-28 | 2022-10-12 | 2023-02-20 | 2023-03-03 | 101
0 | PPBKEL1285 | COMPLETE CBE / ISSUE ROA - SOCKETS & ISOLATING SWITCHES | 1 | 2022-10-12 | 2022-10-13 | 2023-03-06 | 2023-03-06 | 101
0 | PPBKEL1290 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - SOCKETS & ISOLATING SWITCHES | 11 | 2022-10-13 | 2022-10-28 | 2023-03-07 | 2023-03-21 | 101
0 | PPBKEL1297 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - SOCKETS & ISOLATING SWITCHES | 120 | 2022-10-28 | 2023-04-18 | 2023-04-26 | 2023-10-17 | 124
0 | PMBKEL2395 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - SOCKET & ISOLATION SWITCHES | 7 | 2023-04-18 | 2023-04-25 | 2023-10-18 | 2023-10-25 | 183
SAFETY |  |  | 274 | 2022-08-11 | 2023-05-12 | 2022-12-15 | 2024-01-06 | 239
FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT |  |  | 274 | 2022-08-11 | 2023-05-12 | 2023-01-18 | 2024-01-06 | 239
0 | PPBKSA1000 | PREPARE RFQ & FLOAT ENQUIRY - FIREFIGHTING, LIFE SAVING & SAFETY EQUIMENT | 5 | 2022-08-11 | 2022-08-18 | 2023-01-18 | 2023-01-24 | 112
0 | PPBKSA1005 | RECEIVE OFFERS - FIREFIGHTING, LIFE SAVING & SAFETY EQUIMENT | 15 | 2022-08-18 | 2022-09-08 | 2023-01-25 | 2023-02-14 | 112
0 | PPBKSA1010 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVALRECEIVE APPROVAL - FIREFIGHTING, LIFE SAVING & SAFETY EQUIMENT | 15 | 2022-09-08 | 2022-09-29 | 2023-02-15 | 2023-03-07 | 112
0 | PPBKSA1015 | RECEIVE TBE COMPANY APPROVAL - FIREFIGHTING, LIFE SAVING & SAFETY EQUIMENT | 10 | 2022-09-29 | 2022-10-13 | 2023-03-08 | 2023-03-21 | 112
0 | PPBKSA1020 | COMPLETE CBE / ISSUE ROA - FIREFIGHTING, LIFE SAVING & SAFETY EQUIMENT | 1 | 2022-10-13 | 2022-10-14 | 2023-03-22 | 2023-03-22 | 112
0 | PPBKSA1025 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - FIREFIGHTING, LIFE SAVING & SAFETY EQUIMENT | 11 | 2022-10-14 | 2022-10-31 | 2023-03-23 | 2023-04-06 | 112
0 | PPBKSA1027 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - FIREFIGHTING, LIFE SAVING & SAFETY EQUIMENT | 128 | 2022-10-31 | 2023-05-03 | 2023-05-08 | 2023-11-08 | 131
0 | PMBKSA2085 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT | 7 | 2023-05-05 | 2023-05-12 | 2023-12-30 | 2024-01-06 | 239
SAFETY SIGNS |  |  | 260 | 2022-08-18 | 2023-05-05 | 2022-12-15 | 2023-12-07 | 216
0 | PPBKSA1030 | PREPARE RFQ & FLOAT ENQUIRY - SAFETY SIGNS | 5 | 2022-08-18 | 2022-08-25 | 2022-12-15 | 2022-12-21 | 83
0 | PPBKSA1035 | RECEIVE OFFERS - SAFETY SIGNS | 15 | 2022-08-25 | 2022-09-15 | 2022-12-22 | 2023-01-11 | 83
0 | PPBKSA1040 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - SAFETY SIGNS | 15 | 2022-09-15 | 2022-10-06 | 2023-01-12 | 2023-02-01 | 83
0 | PPBKSA1045 | RECEIVE TBE COMPANY APPROVAL - SAFETY SIGNS | 10 | 2022-10-06 | 2022-10-20 | 2023-02-02 | 2023-02-15 | 83
0 | PPBKSA1050 | COMPLETE CBE / ISSUE ROA - SAFETY SIGNS | 1 | 2022-10-20 | 2022-10-21 | 2023-02-16 | 2023-02-16 | 83
0 | PPBKSA1055 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - SAFETY SIGNS | 11 | 2022-10-21 | 2022-11-07 | 2023-02-17 | 2023-03-03 | 83
0 | PPBKSA1057 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - SAFETY SIGNS | 118 | 2022-11-07 | 2023-04-26 | 2023-05-22 | 2023-11-08 | 136
0 | PMBKSA2075 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - SAFETY SIGNS | 7 | 2023-04-28 | 2023-05-05 | 2023-11-30 | 2023-12-07 | 216
PIPELINE & OTHER PIPELINE MATERIALS |  |  | 504 | 2022-02-14 | 2023-07-03 | 2022-04-12 | 2023-11-05 | 126
LINE PIPE (SAW) |  |  | 400 | 2022-02-17 | 2023-03-24 | 2022-04-19 | 2023-06-03 | 72
0 | PPBKPL1000 | PREPARE RFQ & FLOAT ENQUIRYL - LINE PIPES (SAW) | 1 | 2022-02-17 | 2022-02-18 | 2022-04-19 | 2022-04-19 | 43
0 | PPBKPL1005 | RECEIVE OFFERS - LINE PIPES (SAW) | 3 | 2022-02-18 | 2022-02-23 | 2022-04-20 | 2022-04-22 | 43
0 | PPBKPL1010 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - LINE PIPES (SAW) | 7 | 2022-02-23 | 2022-03-04 | 2022-04-25 | 2022-05-06 | 43
0 | PPBKPL1015 | RECEIVE TBE COMPANY APPROVAL - LINE PIPES (SAW) | 10 | 2022-03-04 | 2022-03-18 | 2022-05-09 | 2022-05-20 | 43
0 | PPBKPL1020 | COMPLETE CBE / ISSUE ROA - LINE PIPES (SAW) | 1 | 2022-03-18 | 2022-03-21 | 2022-05-23 | 2022-05-23 | 43
0 | PPBKPL1025 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - LINE PIPES (SAW) | 10 | 2022-03-21 | 2022-04-04 | 2022-05-24 | 2022-06-06 | 43
0 | PPBKPL1027 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - LINE PIPES (SAW) | 241 | 2022-04-04 | 2023-03-17 | 2022-06-07 | 2023-05-18 | 43
0 | PMBKPL2585 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - LINE PIPE (SAW) | 7 | 2023-03-17 | 2023-03-24 | 2023-05-27 | 2023-06-03 | 71
LINE PIPE (SMLS) |  |  | 307 | 2022-02-14 | 2022-12-18 | 2022-04-12 | 2023-03-21 | 93
0 | PPBKPL1030 | PREPARE RFQ & FLOAT ENQUIRY - LINE PIPES (SML S) | 1 | 2022-02-14 | 2022-02-15 | 2022-04-12 | 2022-04-12 | 41
0 | PPBKPL1035 | RECEIVE OFFERS- LINE PIPES (SML S) | 3 | 2022-02-15 | 2022-02-18 | 2022-04-13 | 2022-04-15 | 41
0 | PPBKPL1040 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL- LINE PIPES (SML S) | 10 | 2022-02-18 | 2022-03-04 | 2022-04-18 | 2022-04-29 | 41
0 | PPBKPL1045 | RECEIVE TBE COMPANY APPROVAL- LINE PIPES (SML S) | 10 | 2022-03-04 | 2022-03-18 | 2022-05-05 | 2022-05-18 | 41
0 | PPBKPL1050 | COMPLETE CBE / ISSUE ROA - LINE PIPES (SML S) | 1 | 2022-03-18 | 2022-03-21 | 2022-05-19 | 2022-05-19 | 41
0 | PPBKPL1055 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER L- LINE PIPES (SML S) | 10 | 2022-03-21 | 2022-04-04 | 2022-05-20 | 2022-06-02 | 41
0 | PPBKPL1057 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - LINE PIPES (SML S) | 171 | 2022-04-04 | 2022-12-09 | 2022-07-13 | 2023-03-10 | 66
0 | PMBKPL2575 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - LINE PIPE (SMLS) | 7 | 2022-12-11 | 2022-12-18 | 2023-03-14 | 2023-03-21 | 93
PIPELINE INDUCTION BENDS |  |  | 356 | 2022-03-15 | 2023-03-06 | 2022-07-22 | 2023-08-10 | 157
0 | PPBKPL1060 | PREPARE RFQ & FLOAT ENQUIRY - PIPELINE INDUCTION BENDS | 3 | 2022-03-15 | 2022-03-18 | 2022-07-22 | 2022-07-27 | 87
0 | PPBKPL1065 | RECEIVE OFFERS - PIPELINE INDUCTION BENDS | 10 | 2022-03-18 | 2022-04-01 | 2022-07-27 | 2022-08-10 | 87
0 | PPBKPL1070 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIPELINE INDUCTION BENDS | 10 | 2022-04-01 | 2022-04-15 | 2022-08-10 | 2022-08-24 | 87
0 | PPBKPL1075 | RECEIVE TBE COMPANY APPROVAL - PIPELINE INDUCTION BENDS | 10 | 2022-04-15 | 2022-04-29 | 2022-08-24 | 2022-09-07 | 87
0 | PPBKPL1080 | COMPLETE CBE / ISSUE ROA - PIPELINE INDUCTION BENDS | 1 | 2022-04-29 | 2022-05-05 | 2022-09-07 | 2022-09-08 | 87
0 | PPBKPL1085 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIPELINE INDUCTION BENDS | 11 | 2022-05-05 | 2022-05-20 | 2022-09-08 | 2022-09-23 | 87
0 | PPBKPL1087 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIPELINE INDUCTION BENDS | 196 | 2022-05-20 | 2023-02-27 | 2022-09-23 | 2023-07-05 | 87
0 | PMBKPL2565 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE- PIPELINE INDUCTION BENDS | 7 | 2023-02-27 | 2023-03-06 | 2023-08-03 | 2023-08-10 | 157
RISER HANGER FLANGES |  |  | 366 | 2022-03-23 | 2023-03-24 | 2022-07-20 | 2023-08-10 | 139
0 | PPBKPL1090 | PREPARE RFQ & FLOAT ENQUIRY - RISER HANGER FLANGES | 5 | 2022-03-23 | 2022-03-30 | 2022-07-20 | 2022-07-27 | 79
0 | PPBKPL1095 | RECEIVE OFFERS- RISER HANGER FLANGES | 15 | 2022-03-30 | 2022-04-20 | 2022-07-27 | 2022-08-17 | 79
0 | PPBKPL1100 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL- RISER HANGER FLANGES | 15 | 2022-04-20 | 2022-05-16 | 2022-08-17 | 2022-09-07 | 79
0 | PPBKPL1105 | RECEIVE TBE COMPANY APPROVAL- RISER HANGER FLANGES | 10 | 2022-05-16 | 2022-05-30 | 2022-09-07 | 2022-09-21 | 79
0 | PPBKPL1110 | COMPLETE CBE / ISSUE ROA - RISER HANGER FLANGES | 1 | 2022-05-30 | 2022-05-31 | 2022-09-21 | 2022-09-22 | 79
0 | PPBKPL1115 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER- RISER HANGER FLANGES | 11 | 2022-05-31 | 2022-06-15 | 2022-09-22 | 2022-10-07 | 79
0 | PPBKPL1117 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - RISER HANGER FLANGES | 192 | 2022-06-15 | 2023-03-17 | 2022-10-27 | 2023-08-02 | 93
0 | PMBKPL2555 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - RISER HANGER FLANGES | 7 | 2023-03-17 | 2023-03-24 | 2023-08-03 | 2023-08-10 | 139
PIPELINE ANODES |  |  | 148 | 2022-06-29 | 2022-11-24 | 2022-09-05 | 2023-01-27 | 65
0 | PPBKPL1120 | PREPARE RFQ & FLOAT ENQUIRY- PIPELINE ANODES | 2 | 2022-06-29 | 2022-07-01 | 2022-09-05 | 2022-09-06 | 45
0 | PPBKPL1125 | RECEIVE OFFERS- PIPELINE ANODES | 10 | 2022-07-01 | 2022-07-20 | 2022-09-07 | 2022-09-20 | 45
0 | PPBKPL1130 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIPELINE ANODES | 10 | 2022-07-20 | 2022-08-03 | 2022-09-21 | 2022-10-04 | 45
0 | PPBKPL1135 | RECEIVE TBE COMPANY APPROVAL- PIPELINE ANODES | 10 | 2022-08-03 | 2022-08-17 | 2022-10-05 | 2022-10-18 | 45
0 | PPBKPL1140 | COMPLETE CBE / ISSUE ROA - PIPELINE ANODES | 1 | 2022-08-17 | 2022-08-18 | 2022-10-19 | 2022-10-19 | 45
0 | PPBKPL1145 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER- PIPELINE ANODES | 11 | 2022-08-18 | 2022-09-02 | 2022-10-20 | 2022-11-03 | 45
0 | PPBKPL1427 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIPELINE ANODES | 54 | 2022-09-02 | 2022-11-17 | 2022-11-04 | 2023-01-20 | 45
0 | PMBKPL2545 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PIPELINE ANODES | 7 | 2022-11-17 | 2022-11-24 | 2023-01-20 | 2023-01-27 | 64
PIPELINE FLANGES |  |  | 359 | 2022-03-30 | 2023-03-24 | 2022-07-19 | 2023-07-11 | 109
0 | PPBKPL1150 | PREPARE RFQ & FLOAT ENQUIRY - PIPELINE ANODES FLANGES | 3 | 2022-03-30 | 2022-04-04 | 2022-07-19 | 2022-07-22 | 73
0 | PPBKPL1155 | RECEIVE OFFERS - PIPELINE ANODES FLANGES | 15 | 2022-04-04 | 2022-04-25 | 2022-07-22 | 2022-08-12 | 73
0 | PPBKPL1160 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIPELINE FLANGES | 15 | 2022-04-25 | 2022-05-19 | 2022-08-12 | 2022-09-02 | 73
0 | PPBKPL1165 | RECEIVE TBE COMPANY APPROVAL - PIPELINE FLANGES | 10 | 2022-05-19 | 2022-06-02 | 2022-09-02 | 2022-09-16 | 73
0 | PPBKPL1170 | COMPLETE CBE / ISSUE ROA - PIPELINE FLANGES | 1 | 2022-06-02 | 2022-06-03 | 2022-09-16 | 2022-09-19 | 73
0 | PPBKPL1175 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIPELINE FLANGES | 11 | 2022-06-03 | 2022-06-20 | 2022-09-19 | 2022-10-04 | 73
0 | PPBKPL1177 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIPELINE FLANGES | 188 | 2022-06-20 | 2023-03-16 | 2022-10-04 | 2023-07-04 | 73
0 | PMBKPL2535 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PIPELINE FLANGES | 7 | 2023-03-17 | 2023-03-24 | 2023-07-04 | 2023-07-11 | 109
PIPELINE BARRED TEES |  |  | 366 | 2022-03-16 | 2023-03-17 | 2022-07-01 | 2023-07-03 | 108
0 | PPBKPL1180 | PREPARE RFQ & FLOAT ENQUIRY - PIPELINE BARRED TEES | 5 | 2022-03-16 | 2022-03-23 | 2022-07-01 | 2022-07-07 | 74
0 | PPBKPL1185 | RECEIVE OFFERS - PIPELINE BARRED TEES | 15 | 2022-03-23 | 2022-04-13 | 2022-07-13 | 2022-08-02 | 74
0 | PPBKPL1190 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIPELINE BARRED TEES | 15 | 2022-04-13 | 2022-05-09 | 2022-08-03 | 2022-08-23 | 74
0 | PPBKPL1195 | RECEIVE TBE COMPANY APPROVAL - PIPELINE BARRED TEES | 10 | 2022-05-09 | 2022-05-23 | 2022-08-24 | 2022-09-06 | 74
0 | PPBKPL1200 | COMPLETE CBE / ISSUE ROA - PIPELINE BARRED TEES | 1 | 2022-05-23 | 2022-05-24 | 2022-09-07 | 2022-09-07 | 74
0 | PPBKPL1205 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIPELINE BARRED TEES | 11 | 2022-05-24 | 2022-06-08 | 2022-09-08 | 2022-09-22 | 74
0 | PPBKPL1207 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIPELINE BARRED TEES | 192 | 2022-06-08 | 2023-03-10 | 2022-09-23 | 2023-06-23 | 74
0 | PMBKPL2525 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PIPELINE BARRED TEE | 7 | 2023-03-10 | 2023-03-17 | 2023-06-26 | 2023-07-03 | 108
PIPELINE FITTINGS |  |  | 388 | 2022-04-04 | 2023-04-27 | 2022-06-28 | 2023-09-09 | 135
0 | PPBKPL1210 | PREPARE RFQ & FLOAT ENQUIRY - PIPELINE FITTINGS | 5 | 2022-04-04 | 2022-04-11 | 2022-06-28 | 2022-07-05 | 58
0 | PPBKPL1215 | RECEIVE OFFERS - PIPELINE FITTINGS | 15 | 2022-04-11 | 2022-05-05 | 2022-07-05 | 2022-07-29 | 58
0 | PPBKPL1220 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIPELINE FITTINGS | 15 | 2022-05-05 | 2022-05-26 | 2022-08-25 | 2022-09-15 | 77
0 | PPBKPL1225 | RECEIVE TBE COMPANY APPROVAL - PIPELINE FITTINGS | 10 | 2022-05-26 | 2022-06-09 | 2022-09-15 | 2022-09-29 | 77
0 | PPBKPL1230 | COMPLETE CBE / ISSUE ROA - PIPELINE FITTINGS | 1 | 2022-06-09 | 2022-06-10 | 2022-09-29 | 2022-09-30 | 77
0 | PPBKPL1235 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIPELINE FITTINGS | 11 | 2022-06-10 | 2022-06-27 | 2022-09-30 | 2022-10-17 | 77
0 | PPBKPL1237 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIPELINE FITTINGS | 105 | 2022-06-27 | 2022-11-24 | 2023-01-24 | 2023-06-22 | 146
0 | PMBKPL2515 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PIPELINE FITTING | 7 | 2023-04-20 | 2023-04-27 | 2023-09-02 | 2023-09-09 | 135
CABLE PROTECTOR & BALLAST MODULE |  |  | 354 | 2022-07-14 | 2023-07-03 | 2022-11-10 | 2023-11-05 | 126
0 | PPBKPL1240 | PREPARE RFQ & FLOAT ENQUIRY - CABLE PROTECTION & BALAST MODULE | 5 | 2022-07-14 | 2022-07-21 | 2022-11-10 | 2022-11-16 | 85
0 | PPBKPL1245 | RECEIVE OFFERS - CABLE PROTECTION & BALAST MODULE | 15 | 2022-07-21 | 2022-08-11 | 2022-11-17 | 2022-12-09 | 85
0 | PPBKPL1250 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - CABLE PROTECTION & BALAST MODULE | 15 | 2022-08-11 | 2022-09-01 | 2022-12-12 | 2022-12-30 | 85
0 | PPBKPL1255 | RECEIVE TBE COMPANY APPROVAL - CABLE PROTECTION & BALAST MODULE | 10 | 2022-09-01 | 2022-09-15 | 2023-01-02 | 2023-01-13 | 85
0 | PPBKPL1260 | COMPLETE CBE / ISSUE ROA - CABLE PROTECTION & BALAST MODULE | 1 | 2022-09-15 | 2022-09-16 | 2023-01-16 | 2023-01-16 | 85
0 | PPBKPL1265 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - CABLE PROTECTION & BALAST MODULE | 11 | 2022-09-16 | 2022-10-03 | 2023-01-17 | 2023-01-31 | 85
0 | PPBKPL1267 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - CABLE PROTECTION & BALAST MODULE | 186 | 2022-10-03 | 2023-06-26 | 2023-02-01 | 2023-10-27 | 85
0 | PMBKPL2505 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PIPELINE CABLE PROTECTOR & BALLAST MODULE | 7 | 2023-06-26 | 2023-07-03 | 2023-10-29 | 2023-11-05 | 125
PIGGYBACK SADDLES |  |  | 325 | 2022-05-25 | 2023-04-15 | 2022-08-01 | 2023-06-22 | 69
0 | PPBKPL1270 | PREPARE RFQ & FLOAT ENQUIRY - PIGGYBACK SADDLES | 3 | 2022-05-25 | 2022-05-30 | 2022-08-01 | 2022-08-03 | 45
0 | PPBKPL1275 | RECEIVE OFFERS - PIGGYBACK SADDLES | 15 | 2022-05-30 | 2022-06-20 | 2022-08-04 | 2022-08-24 | 45
0 | PPBKPL1280 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIGGYBACK SADDLES | 15 | 2022-06-20 | 2022-07-14 | 2022-08-25 | 2022-09-14 | 45
0 | PPBKPL1285 | RECEIVE TBE COMPANY APPROVAL - PIGGYBACK SADDLES | 10 | 2022-07-14 | 2022-07-28 | 2022-09-15 | 2022-09-28 | 45
0 | PPBKPL1290 | COMPLETE CBE / ISSUE ROA - PIGGYBACK SADDLES | 1 | 2022-07-28 | 2022-07-29 | 2022-09-29 | 2022-09-29 | 45
0 | PPBKPL1295 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIGGYBACK SADDLES | 11 | 2022-07-29 | 2022-08-15 | 2022-09-30 | 2022-10-14 | 45
0 | PPBKPL1297 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIGGYBACK SADDLES | 166 | 2022-08-15 | 2023-04-06 | 2022-10-17 | 2023-06-09 | 45
0 | PMBKPL2495 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PIGGYBACK SADDLES | 7 | 2023-04-08 | 2023-04-15 | 2023-06-15 | 2023-06-22 | 68
PIPELINE GASKETS |  |  | 286 | 2022-07-26 | 2023-05-08 | 2022-11-23 | 2023-09-09 | 124
0 | PPBKPL1300 | PREPARE RFQ & FLOAT ENQUIRY - PIPELINE GASKETS | 5 | 2022-07-26 | 2022-08-02 | 2022-11-23 | 2022-11-29 | 86
0 | PPBKPL1305 | RECEIVE OFFERS - PIPELINE GASKETS | 15 | 2022-08-02 | 2022-08-23 | 2022-11-30 | 2022-12-22 | 86
0 | PPBKPL1310 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIPELINE GASKETS | 15 | 2022-08-23 | 2022-09-13 | 2022-12-23 | 2023-01-12 | 86
0 | PPBKPL1315 | RECEIVE TBE COMPANY APPROVAL - PIPELINE GASKETS | 10 | 2022-09-13 | 2022-09-27 | 2023-01-13 | 2023-01-26 | 86
0 | PPBKPL1320 | COMPLETE CBE / ISSUE ROA - PIPELINE GASKETS | 1 | 2022-09-27 | 2022-09-28 | 2023-01-27 | 2023-01-27 | 86
0 | PPBKPL1325 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIPELINE GASKETS | 11 | 2022-09-28 | 2022-10-13 | 2023-01-30 | 2023-02-13 | 86
0 | PPBKPL1327 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIPELINE GASKETS | 138 | 2022-10-13 | 2023-05-01 | 2023-02-14 | 2023-09-01 | 86
0 | PMBKPL2605 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PIPELINE GASKET | 7 | 2023-05-01 | 2023-05-08 | 2023-09-02 | 2023-09-09 | 124
PIPELINE BOLTS & NUTS |  |  | 293 | 2022-07-21 | 2023-05-10 | 2022-11-16 | 2023-09-09 | 122
0 | PPBKPL1330 | PREPARE RFQ & FLOAT ENQUIRY - PIPELINE BOLTS &NUT | 5 | 2022-07-21 | 2022-07-28 | 2022-11-16 | 2022-11-22 | 84
0 | PPBKPL1335 | RECEIVE OFFERS - PIPELINE BOLTS &NUT | 15 | 2022-07-28 | 2022-08-18 | 2022-11-23 | 2022-12-15 | 84
0 | PPBKPL1340 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - PIPELINE BOLTS &NUT | 15 | 2022-08-18 | 2022-09-08 | 2022-12-16 | 2023-01-05 | 84
0 | PPBKPL1345 | RECEIVE TBE COMPANY APPROVAL - PIPELINE BOLTS &NUT | 10 | 2022-09-08 | 2022-09-22 | 2023-01-06 | 2023-01-19 | 84
0 | PPBKPL1350 | COMPLETE CBE / ISSUE ROA - PIPELINE BOLTS &NUT | 1 | 2022-09-22 | 2022-09-23 | 2023-01-20 | 2023-01-20 | 84
0 | PPBKPL1355 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - PIPELINE BOLTS &NUT | 11 | 2022-09-23 | 2022-10-10 | 2023-01-23 | 2023-02-06 | 84
0 | PPBKPL1357 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - PIPELINE BOLTS &NUT | 143 | 2022-10-10 | 2023-05-03 | 2023-02-07 | 2023-09-01 | 84
0 | PMBKPL2625 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - PIPELINE BOLTS & NUTS | 7 | 2023-05-03 | 2023-05-10 | 2023-09-02 | 2023-09-09 | 122
EXTERNAL COATING FOR INDUCTION BENDS |  |  | 284 | 2022-07-06 | 2023-04-16 | 2022-09-28 | 2023-07-11 | 86
0 | PPBKPL1360 | PREPARE RFQ & FLOAT ENQUIRY - EXTERNAL COATING FOR INDUCTION BENDS | 5 | 2022-07-06 | 2022-07-18 | 2022-09-28 | 2022-10-05 | 57
0 | PPBKPL1365 | RECEIVE OFFERS- EXTERNAL COATING FOR INDUCTION BENDS | 15 | 2022-07-18 | 2022-08-08 | 2022-10-05 | 2022-10-26 | 57
0 | PPBKPL1370 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL- EXTERNAL COATING FOR INDUCTION BENDS | 15 | 2022-08-08 | 2022-08-29 | 2022-10-26 | 2022-11-16 | 57
0 | PPBKPL1375 | RECEIVE TBE COMPANY APPROVAL- EXTERNAL COATING FOR INDUCTION BENDS | 10 | 2022-08-29 | 2022-09-12 | 2022-11-16 | 2022-11-30 | 57
0 | PPBKPL1380 | COMPLETE CBE / ISSUE ROA - EXTERNAL COATING FOR INDUCTION BENDS | 1 | 2022-09-12 | 2022-09-13 | 2022-11-30 | 2022-12-05 | 57
0 | PPBKPL1385 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER- EXTERNAL COATING FOR INDUCTION BENDS | 11 | 2022-09-13 | 2022-09-28 | 2022-12-05 | 2022-12-20 | 57
0 | PPBKPL1387 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - EXTERNAL COATING FOR INDUCTION BENDS | 135 | 2022-09-28 | 2023-04-07 | 2022-12-20 | 2023-07-04 | 57
0 | PMBKPL2615 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - EXTERNAL COATING FOR INDUCTION BENDS | 7 | 2023-04-09 | 2023-04-16 | 2023-07-04 | 2023-07-11 | 86
HDPE PIPES |  |  | 328 | 2022-04-19 | 2023-03-13 | 2022-06-29 | 2023-05-22 | 70
0 | PPBKPL1390 | PREPARE RFQ & FLOAT ENQUIRY- HDPE PIPES | 5 | 2022-04-19 | 2022-04-26 | 2022-06-29 | 2022-07-05 | 48
0 | PPBKPL1395 | RECEIVE OFFERS- HDPE PIPES | 15 | 2022-04-26 | 2022-05-20 | 2022-07-06 | 2022-07-29 | 48
0 | PPBKPL1400 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL- HDPE PIPES | 15 | 2022-05-20 | 2022-06-10 | 2022-08-01 | 2022-08-19 | 48
0 | PPBKPL1405 | RECEIVE TBE COMPANY APPROVAL- HDPE PIPES | 10 | 2022-06-10 | 2022-06-24 | 2022-08-22 | 2022-09-02 | 48
0 | PPBKPL1410 | COMPLETE CBE / ISSUE ROA - HDPE PIPES | 1 | 2022-06-24 | 2022-06-27 | 2022-09-05 | 2022-09-05 | 48
0 | PPBKPL1415 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - HDPE PIPES | 11 | 2022-06-27 | 2022-07-15 | 2022-09-06 | 2022-09-20 | 48
0 | PPBKPL1417 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - HDPE PIPES | 164 | 2022-07-15 | 2023-03-06 | 2022-09-21 | 2023-05-12 | 48
0 | PMBKPL2595 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - HDPE PIPES | 7 | 2023-03-06 | 2023-03-13 | 2023-05-15 | 2023-05-22 | 70
UMBILICALS & COMPOSITE CABLE |  |  | 530 | 2022-03-16 | 2023-08-28 | 2022-05-16 | 2024-03-04 | 190
6.6kV COMPOSITE SUBSEA CABLE |  |  | 530 | 2022-03-16 | 2023-08-28 | 2022-05-16 | 2024-03-04 | 190
0 | PPEQEL1000 | PREPARE RFQ & FLOAT ENQUIRY - 6.6KV COMPOSITE SUBSEA CABLE | 3 | 2022-03-16 | 2022-03-21 | 2022-05-16 | 2022-05-18 | 40
0 | PPEQEL1005 | RECEIVE OFFERS - 6.6KV COMPOSITE SUBSEA CABLE | 20 | 2022-03-21 | 2022-04-18 | 2022-05-19 | 2022-06-15 | 40
0 | PPEQEL1010 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - 6.6KV COMPOSITE SUBSEA CABLE | 20 | 2022-04-18 | 2022-05-19 | 2022-06-16 | 2022-07-18 | 40
0 | PPEQEL1015 | RECEIVE TBE COMPANY APPROVAL - 6.6KV COMPOSITE SUBSEA CABLE | 10 | 2022-05-19 | 2022-06-02 | 2022-07-19 | 2022-08-01 | 40
0 | PPEQEL1020 | COMPLETE CBE / ISSUE ROA - 6.6KV COMPOSITE SUBSEA CABLE | 1 | 2022-06-02 | 2022-06-03 | 2022-08-02 | 2022-08-02 | 40
0 | PPEQEL1025 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - 6.6KV COMPOSITE SUBSEA CABLE | 11 | 2022-06-03 | 2022-06-20 | 2022-08-03 | 2022-08-17 | 40
0 | PPEQEL1027 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - 6.6KV COMPOSITE SUBSEA CABLE | 294 | 2022-06-20 | 2023-08-21 | 2022-08-22 | 2023-10-18 | 42
0 | PMEQEL2400 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE) - 6.6kV COMPOSITE SUBSEA CABLE | 7 | 2023-08-21 | 2023-08-28 | 2024-02-26 | 2024-03-04 | 189
MISC. MATERIAL ( CONTINGENCY) |  |  | 313 | 2022-08-17 | 2023-06-26 | 2023-01-12 | 2024-01-02 | 190
0 | PPEQEL1275 | PREPARE RFQ & FLOAT ENQUIRY - MISC. MATERIAL ( CONTINGENCY) | 5 | 2022-08-17 | 2022-08-24 | 2023-01-12 | 2023-01-18 | 104
0 | PPEQEL1285 | RECEIVE OFFERS - MISC. MATERIAL ( CONTINGENCY) | 20 | 2022-08-24 | 2022-09-21 | 2023-01-19 | 2023-02-15 | 104
0 | PPEQEL1295 | COMPLETE EVALUATION AND SUBMIT TBE FOR COMPANY APPROVAL - MISC. MATERIAL ( CONTINGENCY) | 24 | 2022-09-21 | 2022-10-25 | 2023-02-16 | 2023-03-21 | 104
0 | PPEQEL1305 | RECEIVE TBE COMPANY APPROVAL - MISC. MATERIAL ( CONTINGENCY) | 10 | 2022-10-25 | 2022-11-08 | 2023-03-22 | 2023-04-04 | 104
0 | PPEQEL1325 | COMPLETE CBE / ISSUE ROA - MISC. MATERIAL ( CONTINGENCY) | 1 | 2022-11-08 | 2022-11-09 | 2023-04-05 | 2023-04-05 | 104
0 | PPEQEL1315 | APPROVAL OF ROA/ ISSUE PURCHASE ORDER - MISC. MATERIAL ( CONTINGENCY) | 11 | 2022-11-09 | 2022-11-24 | 2023-04-06 | 2023-04-20 | 104
0 | PPEQEL1327 | RECEIVE VENDOR DOCUMENTS TO MATERIAL DELIVERY - MISC. MATERIAL ( CONTINGENCY) | 143 | 2022-11-24 | 2023-06-19 | 2023-04-25 | 2023-11-16 | 104
0 | PMBKSA2165 | PREPARE MATERIAL RECEIPT VOUCHER (MRV) (COMPLETE - MISC. MATERIAL ( CONTINGENCY) | 7 | 2023-06-19 | 2023-06-26 | 2023-12-26 | 2024-01-02 | 190
SUB-CONTRACT SERVICES |  |  | 405 | 2022-01-06 | 2023-08-15 | 2022-03-04 | 2023-11-24 | 72
ENGINEERING S/C |  |  | 267 | 2022-01-06 | 2023-01-26 | 2022-03-04 | 2023-05-09 | 72
HSE STUDIES |  |  | 54 | 2022-01-12 | 2022-03-29 | 2022-03-28 | 2022-06-14 | 53
0 | SEEN1000 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : HSE STUDIES | 10 | 2022-01-12 | 2022-01-26 | 2022-03-28 | 2022-04-08 | 53
0 | SEEN1005 | PREPARE AND ISSUE RFQ : HSE STUDIES | 1 | 2022-01-26 | 2022-01-27 | 2022-04-11 | 2022-04-11 | 53
0 | SEEN1010 | RECEIVED TECHNICAL BIDS : HSE STUDIES | 10 | 2022-01-27 | 2022-02-10 | 2022-04-12 | 2022-04-25 | 53
0 | SEEN1015 | ISSUE TBE : HSE STUDIES | 16 | 2022-02-10 | 2022-03-04 | 2022-04-26 | 2022-05-20 | 53
0 | SEEN1020 | TBE APPROVAL BY COMPANY : HSE STUDIES | 11 | 2022-03-04 | 2022-03-21 | 2022-05-23 | 2022-06-06 | 53
0 | SEEN1025 | SUBMIT & APPROVAL CBE/ WARD OF RECOMENDATION BY COMPANY : HSE STUDIES | 5 | 2022-03-21 | 2022-03-28 | 2022-06-07 | 2022-06-13 | 53
0 | SEEN1030 | SO AWARD : HSE STUDIES | 1 | 2022-03-28 | 2022-03-29 | 2022-06-14 | 2022-06-14 | 53
IVB HSECES STUDY |  |  | 51 | 2022-02-09 | 2022-04-21 | 2022-07-04 | 2022-09-15 | 100
0 | SEEN1040 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : IVB HSECES STUDIES | 10 | 2022-02-09 | 2022-02-23 | 2022-07-04 | 2022-07-20 | 100
0 | SEEN1045 | PREPARE AND ISSUE RFQ : IVB HSECES STUDIES | 1 | 2022-02-23 | 2022-02-24 | 2022-07-21 | 2022-07-21 | 100
0 | SEEN1050 | RECEIVED TECHNICAL BIDS : IVB HSECES STUDIES | 10 | 2022-02-24 | 2022-03-10 | 2022-07-22 | 2022-08-04 | 100
0 | SEEN1055 | ISSUE TBE : IVB HSECES STUDIES | 14 | 2022-03-10 | 2022-03-30 | 2022-08-05 | 2022-08-24 | 100
0 | SEEN1060 | TBE APPROVAL BY COMPANY : IVB HSECES STUDIES | 10 | 2022-03-30 | 2022-04-13 | 2022-08-25 | 2022-09-07 | 100
0 | SEEN1065 | SUBMIT & APPROVAL CBE/ WARD OF RECOMENDATION BY COMPANY : IVB HSECES STUDIES | 5 | 2022-04-13 | 2022-04-20 | 2022-09-08 | 2022-09-14 | 100
0 | SEEN1070 | SO AWARD : IVB HSECES STUDIES | 1 | 2022-04-20 | 2022-04-21 | 2022-09-15 | 2022-09-15 | 100
FIV STUDY / AIV STUDY |  |  | 47 | 2022-04-04 | 2022-06-13 | 2022-06-22 | 2022-08-31 | 55
0 | SEEN1080 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : FIV STUDY / AIV STUDY | 5 | 2022-04-04 | 2022-04-11 | 2022-06-22 | 2022-06-28 | 54
0 | SEEN1085 | PREPARE AND ISSUE RFQ : FIV STUDY / AIV STUDY | 1 | 2022-04-11 | 2022-04-12 | 2022-06-29 | 2022-06-29 | 54
0 | SEEN1090 | RECEIVED TECHNICAL BIDS : FIV STUDY / AIV STUDY | 10 | 2022-04-12 | 2022-04-26 | 2022-06-30 | 2022-07-18 | 54
0 | SEEN1095 | ISSUE TBE : FIV STUDY / AIV STUDY | 15 | 2022-04-26 | 2022-05-20 | 2022-07-20 | 2022-08-09 | 55
0 | SEEN1100 | TBE APPROVAL BY COMPANY : FIV STUDY / AIV STUDY | 10 | 2022-05-20 | 2022-06-03 | 2022-08-10 | 2022-08-23 | 55
0 | SEEN1105 | SUBMIT & APPROVAL AWARD OF RECOMENDATION BY COMPANY : FIV STUDY / AIV STUDY | 5 | 2022-06-03 | 2022-06-10 | 2022-08-24 | 2022-08-30 | 55
0 | SEEN1110 | SO AWARD : FIV STUDY / AIV STUDY | 1 | 2022-06-10 | 2022-06-13 | 2022-08-31 | 2022-08-31 | 55
SIL CLASSIFICATION ASSESSMENT OF PROCESS (ESD/HIPPS) AND F&G SAFETY INSTRUMENTED FUNCTIONS |  |  | 44 | 2022-04-26 | 2022-06-30 | 2022-08-05 | 2022-10-06 | 68
0 | SEEN1120 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : SIL STUDY | 7 | 2022-04-26 | 2022-05-10 | 2022-08-05 | 2022-08-15 | 67
0 | SEEN1125 | PREPARE AND ISSUE RFQ : SIL STUDY | 1 | 2022-05-10 | 2022-05-11 | 2022-08-16 | 2022-08-16 | 67
0 | SEEN1130 | RECEIVED TECHNICAL BIDS : SIL STUDY | 10 | 2022-05-11 | 2022-05-25 | 2022-08-17 | 2022-08-30 | 67
0 | SEEN1135 | ISSUE TBE : SIL STUDY | 10 | 2022-05-25 | 2022-06-08 | 2022-09-01 | 2022-09-14 | 68
0 | SEEN1140 | TBE APPROVAL BY COMPANY : SIL STUDY | 10 | 2022-06-08 | 2022-06-22 | 2022-09-15 | 2022-09-28 | 68
0 | SEEN1145 | SUBMIT & APPROVAL AWARD OF RECOMENDATION BY COMPANY : SIL STUDY | 5 | 2022-06-22 | 2022-06-29 | 2022-09-29 | 2022-10-05 | 68
0 | SEEN1150 | SO AWARD : SIL STUDY | 1 | 2022-06-29 | 2022-06-30 | 2022-10-06 | 2022-10-06 | 68
MATERIAL AND CORROSSION CONTROL STUDY (CRAS & CCM) |  |  | 56 | 2022-01-21 | 2022-04-11 | 2022-05-10 | 2022-08-01 | 74
0 | SEEN1160 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : MATERIAL AND CORROSSION CONTROL STUDY (CRAS & CCM) | 5 | 2022-01-21 | 2022-01-28 | 2022-05-10 | 2022-05-17 | 74
0 | SEEN1165 | PREPARE AND ISSUE RFQ : MATERIAL AND CORROSSION CONTROL STUDY (CRAS & CCM) | 1 | 2022-01-28 | 2022-01-31 | 2022-05-17 | 2022-05-18 | 74
0 | SEEN1170 | RECEIVED TECHNICAL BIDS : MATERIAL AND CORROSSION CONTROL STUDY ( (CRAS & CCM) | 20 | 2022-01-31 | 2022-02-28 | 2022-05-18 | 2022-06-15 | 74
0 | SEEN1175 | ISSUE TBE : MATERIAL AND CORROSSION CONTROL STUDY (CRAS & CCM) | 14 | 2022-02-28 | 2022-03-18 | 2022-06-15 | 2022-07-05 | 74
0 | SEEN1180 | TBE APPROVAL BY COMPANY : MATERIAL AND CORROSSION CONTROL STUDY (CRAS & CCM) | 10 | 2022-03-18 | 2022-04-01 | 2022-07-05 | 2022-07-22 | 74
0 | SEEN1185 | SUBMIT & APPROVAL CBE/ WARD OF RECOMENDATION BY COMPANY : MATERIAL AND CORROSSION CONTROL STUDY (CRAS & CCM) | 5 | 2022-04-01 | 2022-04-08 | 2022-07-22 | 2022-07-29 | 74
0 | SEEN1190 | SO AWARD : MATERIAL AND CORROSSION CONTROL STUDY (CRAS & CCM) | 1 | 2022-04-08 | 2022-04-11 | 2022-07-29 | 2022-08-01 | 74
OPERATING MANUALS |  |  | 76 | 2022-08-15 | 2022-11-29 | 2022-12-21 | 2023-04-05 | 90
0 | SEEN1200 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : OPERATING MANUALS | 10 | 2022-08-15 | 2022-08-29 | 2022-12-21 | 2023-01-03 | 90
0 | SEEN1205 | PREPARE AND ISSUE RFQ : OPERATING MANUALS | 1 | 2022-08-29 | 2022-08-30 | 2023-01-04 | 2023-01-04 | 90
0 | SEEN1210 | RECEIVED TECHNICAL BIDS : OPERATING MANUALS | 10 | 2022-08-30 | 2022-09-13 | 2023-01-05 | 2023-01-18 | 90
0 | SEEN1215 | ISSUE TBE : OPERATING MANUALS | 20 | 2022-09-13 | 2022-10-11 | 2023-01-26 | 2023-02-22 | 95
0 | SEEN1220 | TBE APPROVAL BY COMPANY : OPERATING MANUALS | 10 | 2022-10-11 | 2022-10-25 | 2023-02-23 | 2023-03-08 | 95
0 | SEEN1225 | SUBMIT & APPROVAL AWARD OF RECOMENDATION BY COMPANY : OPERATING MANUALS | 10 | 2022-10-25 | 2022-11-08 | 2023-03-09 | 2023-03-22 | 95
0 | SEEN1230 | SO AWARD : OPERATING MANUALS | 10 | 2022-11-15 | 2022-11-29 | 2023-03-23 | 2023-04-05 | 90
EHAZOP STUDY |  |  | 57 | 2022-03-24 | 2022-06-16 | 2022-07-13 | 2022-10-18 | 85
0 | SEEN1560 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : EHAZOP STUDY | 5 | 2022-03-24 | 2022-03-31 | 2022-07-13 | 2022-07-19 | 73
0 | SEEN1580 | PREPARE AND ISSUE RFQ : EHAZOP STUDY | 1 | 2022-03-31 | 2022-04-01 | 2022-07-20 | 2022-07-20 | 73
0 | SEEN1590 | RECEIVED TECHNICAL BIDS : EHAZOP STUDY | 10 | 2022-04-01 | 2022-04-15 | 2022-07-21 | 2022-08-03 | 73
0 | SEEN1570 | ISSUE TBE : EHAZOP STUDY | 20 | 2022-04-15 | 2022-05-18 | 2022-08-04 | 2022-08-31 | 73
0 | SEEN1620 | TBE APPROVAL BY COMPANY : EHAZOP STUDY | 10 | 2022-05-18 | 2022-06-01 | 2022-09-19 | 2022-10-03 | 85
0 | SEEN1610 | SUBMIT & APPROVAL AWARD OF RECOMENDATION BY COMPANY : EHAZOP STUDY | 10 | 2022-06-01 | 2022-06-15 | 2022-10-03 | 2022-10-17 | 85
0 | SEEN1600 | SO AWARD : EHAZOP STUDY | 1 | 2022-06-15 | 2022-06-16 | 2022-10-17 | 2022-10-18 | 85
RBI STUDY |  |  | 57 | 2022-11-04 | 2023-01-26 | 2023-02-16 | 2023-05-09 | 72
0 | SEEN1280 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : RBI STUDY | 5 | 2022-11-04 | 2022-11-11 | 2023-02-16 | 2023-02-22 | 72
0 | SEEN1285 | PREPARE AND ISSUE RFQ : RBI STUDY | 1 | 2022-11-11 | 2022-11-14 | 2023-02-23 | 2023-02-23 | 72
0 | SEEN1290 | RECEIVED TECHNICAL BIDS : RBI STUDY | 10 | 2022-11-14 | 2022-11-28 | 2023-02-24 | 2023-03-09 | 72
0 | SEEN1295 | ISSUE TBE : RBI STUDY | 20 | 2022-11-28 | 2022-12-28 | 2023-03-10 | 2023-04-06 | 72
0 | SEEN1300 | TBE APPROVAL BY COMPANY : RBI STUDY | 10 | 2022-12-28 | 2023-01-11 | 2023-04-07 | 2023-04-20 | 72
0 | SEEN1305 | SUBMIT & APPROVAL AWARD OF RECOMENDATION BY COMPANY : RBI STUDY | 10 | 2023-01-11 | 2023-01-25 | 2023-04-25 | 2023-05-08 | 72
0 | SEEN1310 | SO AWARD : RBI STUDY | 1 | 2023-01-25 | 2023-01-26 | 2023-05-09 | 2023-05-09 | 72
DEPRESSURIZATION, MMDT & HYDRATE STUDY |  |  | 58 | 2022-01-07 | 2022-03-30 | 2022-03-04 | 2022-05-27 | 40
0 | SEEN1320 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : DEPRESSURIZATION, MMDT & HYDRATE STUDY | 5 | 2022-01-07 | 2022-01-14 | 2022-03-04 | 2022-03-10 | 40
0 | SEEN1325 | PREPARE AND ISSUE RFQ : DEPRESSURIZATION, MMDT & HYDRATE STUDY | 1 | 2022-01-14 | 2022-01-17 | 2022-03-11 | 2022-03-11 | 40
0 | SEEN1330 | RECEIVED TECHNICAL BIDS : DEPRESSURIZATION, MMDT & HYDRATE STUDY | 20 | 2022-01-17 | 2022-02-14 | 2022-03-14 | 2022-04-08 | 40
0 | SEEN1335 | ISSUE TBE : DEPRESSURIZATION, MMDT & HYDRATE STUDY | 15 | 2022-02-14 | 2022-03-07 | 2022-04-11 | 2022-04-29 | 40
0 | SEEN1340 | TBE APPROVAL BY COMPANY : DEPRESSURIZATION, MMDT & HYDRATE STUDY | 11 | 2022-03-07 | 2022-03-22 | 2022-05-05 | 2022-05-19 | 40
0 | SEEN1345 | SUBMIT & APPROVAL CBE/ WARD OF RECOMENDATION BY COMPANY : DEPRESSURIZATION, MMDT & HYDRATE STUDY | 5 | 2022-03-22 | 2022-03-29 | 2022-05-20 | 2022-05-26 | 40
0 | SEEN1350 | SO AWARD : DEPRESSURIZATION, MMDT & HYDRATE STUDY | 1 | 2022-03-29 | 2022-03-30 | 2022-05-27 | 2022-05-27 | 40
THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) |  |  | 46 | 2022-05-19 | 2022-07-27 | 2022-08-18 | 2022-11-03 | 72
0 | SEEN1360 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) | 5 | 2022-05-19 | 2022-05-26 | 2022-08-18 | 2022-08-24 | 62
0 | SEEN1365 | PREPARE AND ISSUE RFQ : THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) | 1 | 2022-05-26 | 2022-05-27 | 2022-08-25 | 2022-08-25 | 62
0 | SEEN1370 | RECEIVED TECHNICAL BIDS : THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) | 5 | 2022-05-27 | 2022-06-03 | 2022-08-26 | 2022-09-01 | 62
0 | SEEN1375 | ISSUE TBE : THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) | 10 | 2022-06-03 | 2022-06-17 | 2022-09-02 | 2022-09-15 | 62
0 | SEEN1380 | TBE APPROVAL BY COMPANY : THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) | 10 | 2022-06-17 | 2022-07-01 | 2022-09-30 | 2022-10-13 | 72
0 | SEEN1385 | SUBMIT & APPROVAL AWARD OF RECOMENDATION BY COMPANY : THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) | 10 | 2022-07-01 | 2022-07-20 | 2022-10-14 | 2022-10-27 | 72
0 | SEEN1390 | SO AWARD : THIRD PARTY CERTIFICATION (PIPELINES & STRUCTURES ) | 5 | 2022-07-20 | 2022-07-27 | 2022-10-28 | 2022-11-03 | 72
PIPELINE TRANSIENT HYDRAULIC STUDY |  |  | 50 | 2022-01-06 | 2022-03-17 | 2022-03-07 | 2022-05-18 | 42
0 | SEEN1400 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : PIPELINE TRANSIENT HYDRAULIC STUDY | 5 | 2022-01-06 | 2022-01-13 | 2022-03-07 | 2022-03-11 | 42
0 | SEEN1405 | PREPARE AND ISSUE RFQ : PIPELINE TRANSIENT HYDRAULIC STUDY | 1 | 2022-01-13 | 2022-01-14 | 2022-03-14 | 2022-03-14 | 42
0 | SEEN1410 | RECEIVED TECHNICAL BIDS : PIPELINE TRANSIENT HYDRAULIC STUDY | 10 | 2022-01-14 | 2022-01-28 | 2022-03-15 | 2022-03-28 | 42
0 | SEEN1415 | ISSUE TBE : PIPELINE TRANSIENT HYDRAULIC STUDY | 18 | 2022-01-28 | 2022-02-23 | 2022-03-29 | 2022-04-21 | 42
0 | SEEN1420 | TBE APPROVAL BY COMPANY: PIPELINE TRANSIENT HYDRAULIC STUDY | 10 | 2022-02-23 | 2022-03-09 | 2022-04-22 | 2022-05-10 | 42
0 | SEEN1425 | SUBMIT & APPROVAL CBE/ WARD OF RECOMENDATION BY COMPANY : PIPELINE TRANSIENT HYDRAULIC STUDY | 5 | 2022-03-09 | 2022-03-16 | 2022-05-11 | 2022-05-17 | 42
0 | SEEN1430 | SO AWARD : PIPELINE TRANSIENT HYDRAULIC STUDY | 1 | 2022-03-16 | 2022-03-17 | 2022-05-18 | 2022-05-18 | 42
3D LASER SCAN SURVEY |  |  | 46 | 2022-01-28 | 2022-04-04 | 2022-04-12 | 2022-06-14 | 48
0 | SEEN1440 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : 3D LASER SCAN SURVEY | 5 | 2022-01-28 | 2022-02-04 | 2022-04-12 | 2022-04-18 | 51
0 | SEEN1445 | PREPARE AND ISSUE RFQ : 3D LASER SCAN SURVEY | 1 | 2022-02-04 | 2022-02-07 | 2022-04-19 | 2022-04-19 | 51
0 | SEEN1450 | RECEIVED TECHNICAL BIDS : 3D LASER SCAN SURVEY | 5 | 2022-02-07 | 2022-02-14 | 2022-04-20 | 2022-04-26 | 51
0 | SEEN1455 | ISSUE TBE : 3D LASER SCAN SURVEY | 11 | 2022-02-14 | 2022-03-01 | 2022-04-27 | 2022-05-16 | 51
0 | SEEN1460 | TBE APPROVAL BY COMPANY: 3D LASER SCAN SURVEY | 10 | 2022-03-01 | 2022-03-15 | 2022-05-17 | 2022-05-30 | 51
0 | SEEN1465 | SUBMIT & APPROVAL CBE/ WARD OF RECOMENDATION BY COMPANY : 3D LASER SCAN SURVEY | 10 | 2022-03-15 | 2022-03-29 | 2022-05-31 | 2022-06-13 | 51
0 | SEEN1470 | SO AWARD : 3D LASER SCAN SURVEY | 1 | 2022-04-01 | 2022-04-04 | 2022-06-14 | 2022-06-14 | 48
HELIDECK DESIGN VARIFICATION AND CERTIFICATION |  |  | 61 | 2022-03-11 | 2022-06-09 | 2022-08-11 | 2022-11-03 | 103
0 | SEEN1480 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL AND CERTIFICATION | 10 | 2022-03-11 | 2022-03-25 | 2022-08-11 | 2022-08-24 | 103
0 | SEEN1485 | PREPARE AND ISSUE RFQ : 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL AND CERTIFICATION | 1 | 2022-03-25 | 2022-03-28 | 2022-08-25 | 2022-08-25 | 103
0 | SEEN1490 | RECEIVED TECHNICAL BIDS : 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL AND CERTIFICATION | 10 | 2022-03-28 | 2022-04-11 | 2022-08-26 | 2022-09-08 | 103
0 | SEEN1495 | ISSUE TBE : 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL AND CERTIFICATION | 15 | 2022-04-11 | 2022-05-05 | 2022-09-09 | 2022-09-29 | 103
0 | SEEN1500 | TBE APPROVAL BY COMPANY: 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL AND CERTIFICATION | 10 | 2022-05-05 | 2022-05-19 | 2022-09-30 | 2022-10-13 | 103
0 | SEEN1505 | SUBMIT & APPROVAL CBE/AWARD OF RECOMEND'N BY COMPANY : 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL & CERTIFICATION | 10 | 2022-05-19 | 2022-06-02 | 2022-10-14 | 2022-10-27 | 103
0 | SEEN1510 | SO AWARD : 3rd PARTY SERVICES FOR HELIDECK DESIGN APPROVAL AND CERTIFICATION | 5 | 2022-06-02 | 2022-06-09 | 2022-10-28 | 2022-11-03 | 103
DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE |  |  | 57 | 2022-05-11 | 2022-08-03 | 2022-08-25 | 2022-11-11 | 73
0 | SEEN1640 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE & PL | 10 | 2022-05-11 | 2022-05-25 | 2022-08-25 | 2022-09-07 | 73
0 | SEEN1650 | PREPARE AND ISSUE RFQ : DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE | 1 | 2022-05-25 | 2022-05-26 | 2022-09-08 | 2022-09-08 | 73
0 | SEEN1660 | RECEIVED TECHNICAL BIDS : DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE | 10 | 2022-05-26 | 2022-06-09 | 2022-09-09 | 2022-09-22 | 73
0 | SEEN1670 | ISSUE TBE : DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE | 15 | 2022-06-09 | 2022-06-30 | 2022-09-23 | 2022-10-13 | 73
0 | SEEN1680 | TBE APPROVAL BY COMPANY: DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE | 10 | 2022-06-30 | 2022-07-19 | 2022-10-14 | 2022-10-27 | 73
0 | SEEN1690 | SUBMIT & APPROVAL CBE/AWARD OF RECOMEND'N BY COMPANY : DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE & PL | 10 | 2022-07-19 | 2022-08-02 | 2022-10-28 | 2022-11-10 | 73
0 | SEEN1630 | SO AWARD : DYNAMIC ON-BOTTOM STABILITY ANALYSIS FOR SUBSEA CABLE , UMBILICAL AND PIPELINE | 1 | 2022-08-02 | 2022-08-03 | 2022-11-11 | 2022-11-11 | 73
GLOBAL BUCKLING AND WALKING ANALYSIS |  |  | 34 | 2022-04-08 | 2022-05-31 | 2022-06-15 | 2022-08-04 | 45
0 | SEEN1710 | FINALIZE BIDER LIST & OBTAINED COMPANY APPROVAL : GLOBAL BUCKLING AND WALKING ANALYSIS | 2 | 2022-04-08 | 2022-04-12 | 2022-06-15 | 2022-06-16 | 45
0 | SEEN1720 | PREPARE AND ISSUE RFQ : GLOBAL BUCKLING AND WALKING ANALYSIS | 1 | 2022-04-12 | 2022-04-13 | 2022-06-17 | 2022-06-17 | 45
0 | SEEN1730 | RECEIVED TECHNICAL BIDS : GLOBAL BUCKLING AND WALKING ANALYSIS | 5 | 2022-04-13 | 2022-04-20 | 2022-06-20 | 2022-06-24 | 45
0 | SEEN1740 | ISSUE TBE : GLOBAL BUCKLING AND WALKING ANALYSIS | 5 | 2022-04-20 | 2022-04-27 | 2022-06-27 | 2022-07-01 | 45
0 | SEEN1750 | TBE APPROVAL BY COMPANY: GLOBAL BUCKLING AND WALKING ANALYSIS | 10 | 2022-04-27 | 2022-05-16 | 2022-07-04 | 2022-07-20 | 45
0 | SEEN1760 | SUBMIT & APPROVAL CBE/AWARD OF RECOMEND'N BY COMPANY : GLOBAL BUCKLING AND WALKING ANALYSIS | 10 | 2022-05-16 | 2022-05-30 | 2022-07-21 | 2022-08-03 | 45
0 | SEEN1700 | SO AWARD : GLOBAL BUCKLING AND WALKING ANALYSIS | 1 | 2022-05-30 | 2022-05-31 | 2022-08-04 | 2022-08-04 | 45
CONSTRUCTION S/C |  |  | 251 | 2022-03-16 | 2023-03-13 | 2022-09-05 | 2023-06-23 | 72
PIPING INSULATION WORKS |  |  | 65 | 2022-08-08 | 2022-11-07 | 2023-03-13 | 2023-06-13 | 153
0 | SCCN1370 | FINALIZE BIDDER LIST/ APPROVAL: PIPING INSULATION WORKS | 5 | 2022-08-08 | 2022-08-15 | 2023-03-13 | 2023-03-17 | 153
0 | SCCN1380 | PREPARE AND ISSUE RFQ : PIPING INSULATION WORKS | 5 | 2022-08-15 | 2022-08-22 | 2023-03-20 | 2023-03-24 | 153
0 | SCCN1390 | RECEIVED TECHNICAL BIDS : PIPING INSULATION WORKS | 15 | 2022-08-22 | 2022-09-12 | 2023-03-27 | 2023-04-14 | 153
0 | SCCN1400 | ISSUE TBE : PIPING INSULATION WORKS | 15 | 2022-09-12 | 2022-10-03 | 2023-04-17 | 2023-05-09 | 153
0 | SCCN1410 | TBE APPROVAL BY COMPANY : PIPING INSULATION WORKS | 10 | 2022-10-03 | 2022-10-17 | 2023-05-10 | 2023-05-23 | 153
0 | SCCN1420 | SUBMIT & APPROVAL CBE/AWARD OF RECO : PIPING INSULATION WORKS | 10 | 2022-10-17 | 2022-10-31 | 2023-05-24 | 2023-06-06 | 153
0 | SCCN1360 | SO AWARD : PIPING INSULATION WORKS | 5 | 2022-10-31 | 2022-11-07 | 2023-06-07 | 2023-06-13 | 153
COLD BENDING OF J TUBES WORKS |  |  | 70 | 2022-06-22 | 2022-10-03 | 2023-01-18 | 2023-04-27 | 145
0 | SCCN1580 | FINALIZE BIDDER LIST/ APPROVAL: COLD BENDING OF J TUBES WORKS | 5 | 2022-06-22 | 2022-06-29 | 2023-01-18 | 2023-01-24 | 145
0 | SCCN1590 | PREPARE AND ISSUE RFQ : COLD BENDING OF J TUBES WORKS | 5 | 2022-06-29 | 2022-07-06 | 2023-01-25 | 2023-01-31 | 145
0 | SCCN1600 | RECEIVED TECHNICAL BIDS : COLD BENDING OF J TUBES WORKS | 15 | 2022-07-06 | 2022-08-01 | 2023-02-01 | 2023-02-21 | 145
0 | SCCN1610 | ISSUE TBE : COLD BENDING OF J TUBES WORKS | 15 | 2022-08-01 | 2022-08-22 | 2023-03-01 | 2023-03-21 | 150
0 | SCCN1620 | TBE APPROVAL BY COMPANY : COLD BENDING OF J TUBES WORKS | 10 | 2022-08-22 | 2022-09-05 | 2023-03-22 | 2023-04-04 | 150
0 | SCCN1630 | SUBMIT & APPROVAL CBE/AWARD OF RECO : COLD BENDING OF J TUBES WORKS | 10 | 2022-09-05 | 2022-09-19 | 2023-04-05 | 2023-04-18 | 150
0 | SCCN1570 | SO AWARD : COLD BENDING OF J TUBES WORKS | 5 | 2022-09-26 | 2022-10-03 | 2023-04-19 | 2023-04-27 | 145
FABRICATION OF GRATING AND GALVANIZATION |  |  | 56 | 2022-07-14 | 2022-09-30 | 2023-03-03 | 2023-05-23 | 164
0 | SCCN1440 | FINALIZE BIDDER LIST/ APPROVAL: FABRICATION OF GRATING AND GALVANIZATION | 5 | 2022-07-14 | 2022-07-21 | 2023-03-03 | 2023-03-09 | 164
0 | SCCN1450 | PREPARE AND ISSUE RFQ : FABRICATION OF GRATING AND GALVANIZATION | 1 | 2022-07-21 | 2022-07-22 | 2023-03-10 | 2023-03-10 | 164
0 | SCCN1460 | RECEIVED TECHNICAL BIDS : FABRICATION OF GRATING AND GALVANIZATION | 10 | 2022-07-22 | 2022-08-05 | 2023-03-13 | 2023-03-24 | 164
0 | SCCN1470 | ISSUE TBE : FABRICATION OF GRATING AND GALVANIZATION | 15 | 2022-08-05 | 2022-08-26 | 2023-03-27 | 2023-04-14 | 164
0 | SCCN1480 | TBE APPROVAL BY COMPANY : FABRICATION OF GRATING AND GALVANIZATION | 10 | 2022-08-26 | 2022-09-09 | 2023-04-17 | 2023-05-02 | 164
0 | SCCN1490 | SUBMIT & APPROVAL CBE/AWARD OF RECO : FABRICATION OF GRATING AND GALVANIZATION | 10 | 2022-09-09 | 2022-09-23 | 2023-05-03 | 2023-05-16 | 164
0 | SCCN1430 | SO AWARD : FABRICATION OF GRATING AND GALVANIZATION | 5 | 2022-09-23 | 2022-09-30 | 2023-05-17 | 2023-05-23 | 164
TERTIARY STEEL WORKS |  |  | 61 | 2022-06-27 | 2022-09-23 | 2023-01-05 | 2023-03-30 | 133
0 | SCCN1510 | FINALIZE BIDDER LIST/ APPROVAL: TERTIARY STEEL WORKS | 5 | 2022-06-27 | 2022-07-04 | 2023-01-05 | 2023-01-11 | 133
0 | SCCN1520 | PREPARE AND ISSUE RFQ : TERTIARY STEEL WORKS | 1 | 2022-07-04 | 2022-07-05 | 2023-01-12 | 2023-01-12 | 133
0 | SCCN1530 | RECEIVED TECHNICAL BIDS : TERTIARY STEEL WORKS | 15 | 2022-07-05 | 2022-07-29 | 2023-01-13 | 2023-02-02 | 133
0 | SCCN1540 | ISSUE TBE : TERTIARY STEEL WORKS | 15 | 2022-07-29 | 2022-08-19 | 2023-02-03 | 2023-02-23 | 133
0 | SCCN1550 | TBE APPROVAL BY COMPANY : TERTIARY STEEL WORKS | 10 | 2022-08-19 | 2022-09-02 | 2023-02-24 | 2023-03-09 | 133
0 | SCCN1560 | SUBMIT & APPROVAL CBE/AWARD OF RECO : TERTIARY STEEL WORKS | 10 | 2022-09-02 | 2022-09-16 | 2023-03-10 | 2023-03-23 | 133
0 | SCCN1500 | SO AWARD : TERTIARY STEEL WORKS | 5 | 2022-09-16 | 2022-09-23 | 2023-03-24 | 2023-03-30 | 133
CALIPER PIGGING AND INTELLIGENT PIGGING |  |  | 61 | 2022-12-19 | 2023-03-13 | 2023-03-29 | 2023-06-23 | 72
0 | SCCN1080 | FINALIZE BIDDER LIST/ APPROVAL : CALIPER PIGGING AND INTELLIGENT PIGGING | 5 | 2022-12-19 | 2022-12-23 | 2023-03-29 | 2023-04-04 | 72
0 | SCCN1085 | PREPARE AND ISSUE RFQ : CALIPER PIGGING AND INTELLIGENT PIGGING | 1 | 2022-12-26 | 2022-12-26 | 2023-04-05 | 2023-04-05 | 72
0 | SCCN1090 | RECEIVED TECHNICAL BIDS : CALIPER PIGGING AND INTELLIGENT PIGGING | 15 | 2022-12-27 | 2023-01-16 | 2023-04-06 | 2023-04-28 | 72
0 | SCCN1095 | ISSUE TBE : CALIPER PIGGING AND INTELLIGENT PIGGING | 15 | 2023-01-17 | 2023-02-06 | 2023-05-01 | 2023-05-19 | 72
0 | SCCN1100 | TBE APPROVAL BY COMPANY: CALIPER PIGGING AND INTELLIGENT PIGGING | 10 | 2023-02-07 | 2023-02-20 | 2023-05-22 | 2023-06-02 | 72
0 | SCCN1105 | SUBMIT & APPROVAL WARD OF RECOMED'N : CALIPER PIGGING AND INTELLIGENT PIGGING | 10 | 2023-02-21 | 2023-03-06 | 2023-06-05 | 2023-06-16 | 72
0 | SCCN1110 | SO AWARD : CALIPER PIGGING AND INTELLIGENT PIGGING | 5 | 2023-03-07 | 2023-03-13 | 2023-06-19 | 2023-06-23 | 72
TRENCHING AND BACKFILLING WORKS |  |  | 48 | 2022-06-24 | 2022-09-02 | 2022-09-05 | 2022-11-09 | 48
0 | SCCN1200 | FINALIZE BIDDER LIST/ APPROVAL : TRENCHING AND BACKFILLING WORKS | 3 | 2022-06-24 | 2022-06-28 | 2022-09-05 | 2022-09-07 | 48
0 | SCCN1205 | PREPARE AND ISSUE RFQ : TRENCHING AND BACKFILLING WORKS | 1 | 2022-06-29 | 2022-06-29 | 2022-09-08 | 2022-09-08 | 48
0 | SCCN1210 | RECEIVED TECHNICAL BIDS : TRENCHING AND BACKFILLING WORKS | 10 | 2022-06-30 | 2022-07-18 | 2022-09-09 | 2022-09-22 | 48
0 | SCCN1215 | ISSUE TBE : TRENCHING AND BACKFILLING WORKS | 13 | 2022-07-19 | 2022-08-04 | 2022-09-23 | 2022-10-11 | 48
0 | SCCN1220 | TBE APPROVAL BY COMPANY : TRENCHING AND BACKFILLING WORKS | 10 | 2022-08-05 | 2022-08-18 | 2022-10-12 | 2022-10-25 | 48
0 | SCCN1225 | SUBMIT & APPROVAL WARD OF RECOMED'N : TRENCHING AND BACKFILLING WORKS | 10 | 2022-08-19 | 2022-09-01 | 2022-10-26 | 2022-11-08 | 48
0 | SCCN1230 | SO AWARD : TRENCHING AND BACKFILLING WORKS | 1 | 2022-09-02 | 2022-09-02 | 2022-11-09 | 2022-11-09 | 48
PIPELINE SLEEPERS |  |  | 55 | 2022-08-02 | 2022-10-17 | 2022-09-22 | 2022-12-09 | 37
0 | SCCN1240 | FINALIZE BIDDER LIST/ APPROVAL : PIPELINE SLEEPERS | 3 | 2022-08-02 | 2022-08-04 | 2022-09-22 | 2022-09-26 | 37
0 | SCCN1245 | PREPARE AND ISSUE RFQ : PIPELINE SLEEPERS | 2 | 2022-08-05 | 2022-08-08 | 2022-09-27 | 2022-09-28 | 37
0 | SCCN1250 | RECEIVED TECHNICAL BIDS : PIPELINE SLEEPERS | 10 | 2022-08-09 | 2022-08-22 | 2022-09-29 | 2022-10-12 | 37
0 | SCCN1255 | ISSUE TBE : PIPELINE SLEEPERS | 15 | 2022-08-23 | 2022-09-12 | 2022-10-13 | 2022-11-02 | 37
0 | SCCN1260 | TBE APPROVAL BY COMPANY : PIPELINE SLEEPERS | 10 | 2022-09-13 | 2022-09-26 | 2022-11-03 | 2022-11-16 | 37
0 | SCCN1265 | SUBMIT & APPROVAL WARD OF RECOMED'N : PIPELINE SLEEPERS | 10 | 2022-09-27 | 2022-10-10 | 2022-11-17 | 2022-11-30 | 37
0 | SCCN1270 | SO AWARD : PIPELINE SLEEPERS | 5 | 2022-10-11 | 2022-10-17 | 2022-12-05 | 2022-12-09 | 37
ONSHORE WORKS AND ASSISTANCE TO MISCELLANEOUS WORKS (SHORE PULL) |  |  | 141 | 2022-07-20 | 2023-02-03 | 2022-09-21 | 2023-04-07 | 45
0 | SCCN1280 | FINALIZE BIDDER LIST/ APPROVAL : ONSHORE WORKS & ASSISTANCE (SHORE PULL) | 10 | 2022-07-20 | 2022-08-02 | 2022-09-21 | 2022-10-04 | 45
0 | SCCN1285 | PREPARE AND ISSUE RFQ : ONSHORE WORKS & ASSISTANCE (SHORE PULL) | 1 | 2022-08-03 | 2022-08-03 | 2022-10-05 | 2022-10-05 | 45
0 | SCCN1290 | RECEIVED TECHNICAL BIDS : ONSHORE WORKS & ASSISTANCE (SHORE PULL) | 15 | 2022-08-04 | 2022-08-24 | 2022-10-06 | 2022-10-26 | 45
0 | SCCN1295 | ISSUE TBE : ONSHORE WORKS & ASSISTANCE (SHORE PULL) | 15 | 2022-08-25 | 2022-09-14 | 2022-10-27 | 2022-11-16 | 45
0 | SCCN1300 | TBE APPROVAL BY COMPANY : ONSHORE WORKS & ASSISTANCE (SHORE PULL) | 10 | 2022-09-15 | 2022-09-28 | 2022-11-17 | 2022-11-30 | 45
0 | SCCN1305 | SUBMIT & APPROVAL WARD OF RECOMED'N : ONSHORE WORKS & ASSISTANCE (SHORE PULL) | 10 | 2022-09-29 | 2022-10-12 | 2022-12-05 | 2022-12-16 | 45
0 | SCCN1310 | SO AWARD : ONSHORE WORKS & ASSISTANCE (SHORE PULL) | 5 | 2022-10-13 | 2022-10-19 | 2022-12-19 | 2022-12-23 | 45
0 | SCCN1640 | CIVIL SPECIFICATION ISSUANCE (SHORE PULL S/C) | 75 | 2022-10-20 | 2023-02-03 | 2022-12-26 | 2023-04-07 | 45
TRANSPORTATION OF UMBILICALS FROM VENDOR |  |  | 41 | 2022-03-16 | 2022-05-17 | 2023-01-13 | 2023-03-10 | 209
0 | SCCN1320 | FINALIZE BIDDER LIST/ APPROVAL : TRANSPORTATION OF UMBILICALS FROM VENDOR | 2 | 2022-03-16 | 2022-03-18 | 2023-01-13 | 2023-01-16 | 209
0 | SCCN1325 | PREPARE AND ISSUE RFQ : TRANSPORTATION OF UMBILICALS FROM VENDOR | 1 | 2022-03-18 | 2022-03-21 | 2023-01-17 | 2023-01-17 | 209
0 | SCCN1330 | RECEIVED TECHNICAL BIDS : TRANSPORTATION OF UMBILICALS FROM VENDOR | 10 | 2022-03-21 | 2022-04-04 | 2023-01-18 | 2023-01-31 | 209
0 | SCCN1335 | ISSUE TBE : TRANSPORTATION OF UMBILICALS FROM VENDOR | 5 | 2022-04-04 | 2022-04-11 | 2023-02-01 | 2023-02-07 | 209
0 | SCCN1340 | TBE APPROVAL BY COMPANY : TRANSPORTATION OF UMBILICALS FROM VENDOR | 10 | 2022-04-11 | 2022-04-25 | 2023-02-08 | 2023-02-21 | 209
0 | SCCN1345 | SUBMIT & APPROVAL WARD OF RECOMED'N : TRANSPORTATION OF UMBILICALS FROM VENDOR | 10 | 2022-04-25 | 2022-05-12 | 2023-02-22 | 2023-03-07 | 209
0 | SCCN1350 | SO AWARD : TRANSPORTATION OF UMBILICALS FROM VENDOR | 3 | 2022-05-12 | 2022-05-17 | 2023-03-08 | 2023-03-10 | 209
MISC. SUBCONTRACTING (CONTINGENCY) |  |  | 105 | 2023-03-14 | 2023-08-15 | 2023-06-26 | 2023-11-24 | 72
MISC. SUBCONTRACTING (CONTINGENCY) |  |  | 105 | 2023-03-14 | 2023-08-15 | 2023-06-26 | 2023-11-24 | 72
0 | SCMS1000 | FINALIZE BIDDER LIST/ APPROVAL : MISC SUBCONTRACTING (CONTINGENCY) | 15 | 2023-03-14 | 2023-04-03 | 2023-06-26 | 2023-07-20 | 72
0 | SCMS1005 | PREPARE AND ISSUE RFQ : MISC SUBCONTRACTING (CONTINGENCY) | 10 | 2023-04-04 | 2023-04-17 | 2023-07-21 | 2023-08-03 | 72
0 | SCMS1010 | RECEIVED TECHNICAL BIDS : MISC SUBCONTRACTING (CONTINGENCY) | 20 | 2023-04-18 | 2023-05-17 | 2023-08-04 | 2023-08-31 | 72
0 | SCMS1015 | ISSUE TBE : MISC SUBCONTRACTING (CONTINGENCY) | 20 | 2023-05-18 | 2023-06-14 | 2023-09-01 | 2023-09-29 | 72
0 | SCMS1020 | TBE APPROVAL BY COMPANY: MISC SUBCONTRACTING (CONTINGENCY) | 10 | 2023-06-15 | 2023-07-03 | 2023-10-02 | 2023-10-13 | 72
0 | SCMS1025 | SUBMIT & APPROVAL WARD OF RECOMED'N : MISC SUBCONTRACTING (CONTINGENCY) | 15 | 2023-07-04 | 2023-07-25 | 2023-10-16 | 2023-11-03 | 72
0 | SCMS1030 | SO AWARD : MISC SUBCONTRACTING (CONTINGENCY) | 15 | 2023-07-26 | 2023-08-15 | 2023-11-06 | 2023-11-24 | 72
MANUFACTURING & DELIVERY |  |  | 610 | 2021-12-19 | 2023-08-21 | 2022-06-03 | 2024-01-13 | 145
EQUIPMENT / TAGGED ITEMS |  |  | 432 | 2022-05-20 | 2023-07-26 | 2022-07-23 | 2024-01-13 | 171
EQUIPMENT - ROTATING / PACKAGES |  |  | 432 | 2022-05-20 | 2023-07-26 | 2022-07-23 | 2024-01-13 | 171
POSITIVE DISPLACEMENT PUMPS |  |  | 374 | 2022-05-20 | 2023-05-29 | 2022-07-23 | 2023-08-01 | 64
0 | PMEQME2000 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - POSITIVE DISPLACEMENT PUMPS | 56 | 2022-05-20 | 2022-07-15 | 2022-07-23 | 2022-09-17 | 64
0 | PMEQME2005 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - POSITIVE DISPLACEMENT PUMPS | 56 | 2022-07-15 | 2022-09-09 | 2022-09-17 | 2022-11-12 | 64
0 | PMEQME2020 | COMPLETE MANUFACTURING AND READY FOR FINAL INSPECTION - POSITIVE DISPLACEMENT PUMPS | 235 | 2022-07-15 | 2023-03-07 | 2022-09-17 | 2023-05-10 | 64
0 | PMEQME2035 | COMPLETE FINAL INSPECTION / FAT - POSITIVE DISPLACEMENT PUMPS | 7 | 2023-03-07 | 2023-03-14 | 2023-05-10 | 2023-05-17 | 64
0 | PMEQME2045 | COMPLETE MATERIAL DISPATCH / FOB - POSITIVE DISPLACEMENT PUMPS | 14 | 2023-03-14 | 2023-03-28 | 2023-05-17 | 2023-05-31 | 64
0 | PMEQME2050 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - POSITIVE DISPLACEMENT PUMPS | 42 | 2023-03-28 | 2023-05-09 | 2023-05-31 | 2023-07-12 | 64
0 | PMEQME2055 | TRANSPORTATION & DELIVERY AT SITE 2ND/LAST LOT - POSITIVE DISPLACEMENT PUMPS | 42 | 2023-04-17 | 2023-05-29 | 2023-06-20 | 2023-08-01 | 64
PORTABLE BIOCIDE INJECTION PACKAGE |  |  | 278 | 2022-07-06 | 2023-04-10 | 2022-09-08 | 2023-07-25 | 106
0 | PMEQME2062 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PORTABLE BIOCIDE INJECTION PACKAGE | 56 | 2022-07-06 | 2022-08-31 | 2022-09-08 | 2022-11-03 | 64
0 | PMEQME2065 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PORTABLE BIOCIDE INJECTION PACKAGE | 56 | 2022-08-31 | 2022-10-26 | 2022-11-21 | 2023-01-16 | 82
0 | PMEQME2075 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PORTABLE BIOCIDE INJECTION PACKAGE | 127 | 2022-08-31 | 2023-01-05 | 2022-12-17 | 2023-04-23 | 108
0 | PMEQME2080 | FINAL ACCEPTANCE TEST (FAT) - PORTABLE BIOCIDE INJECTION PACKAGE | 7 | 2023-01-05 | 2023-01-12 | 2023-04-23 | 2023-04-30 | 108
0 | PMEQME2085 | FOB DELIVERY - PORTABLE BIOCIDE INJECTION PACKAGE | 14 | 2023-01-12 | 2023-01-26 | 2023-04-30 | 2023-05-14 | 108
0 | PMEQME2090 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PORTABLE BIOCIDE INJECTION PACKAGE | 42 | 2023-01-26 | 2023-03-09 | 2023-05-14 | 2023-06-25 | 108
0 | PMEQME2095 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PORTABLE BIOCIDE INJECTION PACKAGE | 42 | 2023-02-27 | 2023-04-10 | 2023-06-13 | 2023-07-25 | 106
MATERIAL HANDLING EQUIPMENT |  |  | 242 | 2022-07-21 | 2023-03-20 | 2022-11-15 | 2023-07-20 | 122
0 | PMEQME2100 | RECEIVE VENDOR DOCUMENTS (CRITICAL - MATERIAL HANDLING EQUIPMENT | 56 | 2022-07-21 | 2022-09-15 | 2022-11-15 | 2023-01-10 | 117
0 | PMEQME2105 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - MATERIAL HANDLING EQUIPMENT | 56 | 2022-09-15 | 2022-11-10 | 2023-02-08 | 2023-04-05 | 146
0 | PMEQME2110 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - MATERIAL HANDLING EQUIPMENT | 120 | 2022-09-15 | 2023-01-13 | 2023-01-10 | 2023-05-10 | 117
0 | PMEQME2115 | COMPLETE FINAL ACCEPTANCE TEST (FAT) - MATERIAL HANDLING EQUIPMENT | 7 | 2023-01-13 | 2023-01-20 | 2023-05-10 | 2023-05-17 | 117
0 | PMEQME2120 | COMPLETE MATERIAL DISPATCH / FOB - MATERIAL HANDLING EQUIPMENT | 14 | 2023-01-20 | 2023-02-03 | 2023-05-17 | 2023-05-31 | 117
0 | PMEQME2125 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - MATERIAL HANDLING EQUIPMENT | 42 | 2023-02-03 | 2023-03-17 | 2023-05-31 | 2023-07-12 | 117
0 | PMEQME2130 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - MATERIAL HANDLING EQUIPMENT | 42 | 2023-02-06 | 2023-03-20 | 2023-06-08 | 2023-07-20 | 122
LIFE RAFT |  |  | 240 | 2022-11-28 | 2023-07-26 | 2023-03-04 | 2024-01-13 | 171
0 | PMEQME2135 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - LIFE RAFT | 56 | 2022-11-28 | 2023-01-23 | 2023-03-04 | 2023-04-29 | 96
0 | PMEQME2142 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - LIFE RAFT | 56 | 2023-01-23 | 2023-03-20 | 2023-04-29 | 2023-06-24 | 96
0 | PMEQME2145 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - LIFE RAFT | 91 | 2023-01-23 | 2023-04-24 | 2023-04-29 | 2023-07-29 | 96
0 | PMEQME2150 | FINAL ACCEPTANCE TEST (FAT) - LIFE RAFT | 7 | 2023-04-24 | 2023-05-01 | 2023-07-29 | 2023-08-05 | 96
0 | PMEQME2155 | COMPLETE MATERIAL DISPATCH / FOB - LIFE RAFT | 14 | 2023-05-01 | 2023-05-15 | 2023-08-05 | 2023-08-19 | 96
0 | PMEQME2160 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - LIFE RAFT | 42 | 2023-05-15 | 2023-06-26 | 2023-08-19 | 2023-09-30 | 96
0 | PMEQME2165 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - LIFE RAFT | 42 | 2023-06-14 | 2023-07-26 | 2023-12-02 | 2024-01-13 | 171
EQUIPMENT - STATIC |  |  | 377 | 2022-05-20 | 2023-06-01 | 2022-07-28 | 2023-09-01 | 92
PIG LAUNCHERS AND RECEIVERS |  |  | 348 | 2022-05-20 | 2023-05-03 | 2022-07-28 | 2023-08-04 | 93
0 | PMEQME2170 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIG LAUNCHERS AND RECEIVERS | 63 | 2022-05-20 | 2022-07-22 | 2022-07-28 | 2022-09-29 | 69
0 | PMEQME2175 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIG LAUNCHERS AND RECEIVERS | 63 | 2022-07-22 | 2022-09-23 | 2022-09-29 | 2022-12-01 | 69
0 | PMEQME2185 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIG LAUNCHERS AND RECEIVERS | 180 | 2022-07-22 | 2023-01-18 | 2022-09-29 | 2023-03-28 | 69
0 | PMEQME2190 | COMPLETE FINAL ACCEPTANCE TEST (FAT) - PIG LAUNCHERS AND RECEIVERS | 7 | 2023-01-18 | 2023-01-25 | 2023-03-28 | 2023-04-04 | 69
0 | PMEQME2195 | COMPLETE MATERIAL DISPATCH / FOB - PIG LAUNCHERS AND RECEIVERS | 14 | 2023-01-25 | 2023-02-08 | 2023-04-04 | 2023-04-18 | 69
0 | PMEQME2200 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIG LAUNCHERS AND RECEIVERS | 42 | 2023-02-08 | 2023-03-22 | 2023-04-18 | 2023-05-30 | 69
0 | PMEQME2205 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIG LAUNCHERS AND RECEIVERS | 42 | 2023-03-22 | 2023-05-03 | 2023-06-23 | 2023-08-04 | 93
CLOSE DRAIN DRUM |  |  | 363 | 2022-06-03 | 2023-06-01 | 2022-08-07 | 2023-09-01 | 92
INCONEL & SS PLATES - VESSEL |  |  | 187 | 2022-06-03 | 2022-12-07 | 2022-08-07 | 2023-04-22 | 136
0 | PMEQME2310 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - INCONEL & SS PLATES - VESSEL | 28 | 2022-06-03 | 2022-07-01 | 2022-08-07 | 2022-09-04 | 65
0 | PMEQME2250 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - INCONEL & SS PLATES - VESSEL | 28 | 2022-07-01 | 2022-07-29 | 2022-09-04 | 2022-10-02 | 65
0 | PMEQME2260 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - INCONEL & SS PLATES - VESSEL | 95 | 2022-07-01 | 2022-10-04 | 2022-09-04 | 2022-12-08 | 65
0 | PMEQME2270 | COMPLETE FINAL ACCEPTANCE TEST (FAT) - INCONEL & SS PLATES - VESSEL | 7 | 2022-10-04 | 2022-10-11 | 2022-12-08 | 2022-12-15 | 65
0 | PMEQME2280 | COMPLETE MATERIAL DISPATCH / FOB - INCONEL & SS PLATES - VESSEL | 7 | 2022-10-11 | 2022-10-18 | 2022-12-15 | 2022-12-22 | 65
0 | PMEQME2290 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - INCONEL & SS PLATES - VESSEL | 30 | 2022-10-18 | 2022-11-17 | 2022-12-22 | 2023-01-21 | 65
0 | PMEQME2300 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - INCONEL & SS PLATES - VESSEL | 30 | 2022-11-07 | 2022-12-07 | 2023-03-23 | 2023-04-22 | 136
DISHED HEAD - VESSEL |  |  | 182 | 2022-06-10 | 2022-12-09 | 2022-09-11 | 2023-04-22 | 134
0 | PMEQME2380 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - DISHED HEAD - VESSEL | 28 | 2022-06-10 | 2022-07-08 | 2022-09-11 | 2022-10-09 | 93
0 | PMEQME2320 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - DISHED HEAD - VESSEL | 28 | 2022-07-08 | 2022-08-05 | 2022-10-09 | 2022-11-06 | 93
0 | PMEQME2330 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - DISHED HEAD - VESSEL | 90 | 2022-07-08 | 2022-10-06 | 2022-10-09 | 2023-01-07 | 93
0 | PMEQME2340 | COMPLETE FINAL ACCEPTANCE TEST (FAT) - DISHED HEAD - VESSEL | 7 | 2022-10-06 | 2022-10-13 | 2023-01-07 | 2023-01-14 | 93
0 | PMEQME2350 | COMPLETE MATERIAL DISPATCH / FOB - DISHED HEAD - VESSEL | 7 | 2022-10-13 | 2022-10-20 | 2023-01-14 | 2023-01-21 | 93
0 | PMEQME2360 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - DISHED HEAD - VESSEL | 30 | 2022-10-20 | 2022-11-19 | 2023-01-21 | 2023-02-20 | 93
0 | PMEQME2370 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - DISHED HEAD - VESSEL | 30 | 2022-11-09 | 2022-12-09 | 2023-03-23 | 2023-04-22 | 134
NAME PLATE - VESSEL |  |  | 119 | 2023-02-02 | 2023-06-01 | 2023-04-28 | 2023-09-01 | 92
0 | PMEQME2450 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - NAME PLATE - VESSEL | 35 | 2023-02-02 | 2023-03-09 | 2023-04-28 | 2023-06-02 | 85
0 | PMEQME2390 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - NAME PLATE - VESSEL | 18 | 2023-03-09 | 2023-03-27 | 2023-06-02 | 2023-06-20 | 85
0 | PMEQME2400 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - NAME PLATE - VESSEL | 20 | 2023-03-09 | 2023-03-29 | 2023-06-02 | 2023-06-22 | 85
0 | PMEQME2410 | COMPLETE FINAL ACCEPTANCE TEST (FAT) - NAME PLATE - VESSEL | 7 | 2023-03-29 | 2023-04-05 | 2023-06-22 | 2023-06-29 | 85
0 | PMEQME2420 | COMPLETE MATERIAL DISPATCH / FOB - NAME PLATE - VESSEL | 7 | 2023-04-05 | 2023-04-12 | 2023-06-29 | 2023-07-06 | 85
0 | PMEQME2430 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - NAME PLATE - VESSEL | 30 | 2023-04-12 | 2023-05-12 | 2023-07-06 | 2023-08-05 | 85
0 | PMEQME2440 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - NAME PLATE - VESSEL | 30 | 2023-05-02 | 2023-06-01 | 2023-08-02 | 2023-09-01 | 92
INSTRUMENTATION |  |  | 426 | 2022-05-20 | 2023-07-20 | 2022-07-27 | 2023-12-12 | 145
ICSS |  |  | 426 | 2022-05-20 | 2023-07-20 | 2022-07-27 | 2023-12-12 | 145
0 | PMEQIN2002 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - ICSS | 154 | 2022-05-20 | 2022-10-21 | 2022-07-27 | 2022-12-28 | 68
0 | PMEQIN2000 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - ICSS | 70 | 2022-10-21 | 2022-12-30 | 2022-12-29 | 2023-03-09 | 69
0 | PMEQIN2025 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - ICSS | 28 | 2023-04-23 | 2023-05-21 | 2023-07-01 | 2023-07-29 | 69
0 | PMEQIN2010 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - ICSS | 216 | 2022-10-21 | 2023-05-25 | 2022-12-29 | 2023-08-02 | 69
0 | PMEQIN2015 | FINAL ACCEPTANCE TEST (FAT) - ICSS | 63 | 2023-03-30 | 2023-06-01 | 2023-06-07 | 2023-08-09 | 69
0 | PMEQIN2020 | FOB DELIVERY - ICSS | 60 | 2023-04-09 | 2023-06-08 | 2023-06-17 | 2023-08-16 | 69
0 | PMEQIN2030 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - ICSS | 42 | 2023-06-08 | 2023-07-20 | 2023-10-31 | 2023-12-12 | 145
IRCD SKID |  |  | 318 | 2022-07-05 | 2023-05-19 | 2022-09-08 | 2023-08-08 | 81
0 | PMBKIN2387 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - IRCD SKID | 63 | 2022-07-05 | 2022-09-06 | 2022-09-08 | 2022-11-10 | 65
0 | PMBKIN2385 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - IRCD SKID | 63 | 2022-09-06 | 2022-11-08 | 2022-12-08 | 2023-02-09 | 93
0 | PMBKIN2395 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - IRCD SKID | 150 | 2022-09-06 | 2023-02-03 | 2022-12-08 | 2023-05-07 | 93
0 | PMBKIN2400 | FINAL ACCEPTANCE TEST (FAT) - IRCD SKID | 7 | 2023-02-03 | 2023-02-10 | 2023-05-07 | 2023-05-14 | 93
0 | PMBKIN2405 | FOB DELIVERY - IRCD SKID | 14 | 2023-02-10 | 2023-02-24 | 2023-05-14 | 2023-05-28 | 93
0 | PMBKIN2410 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - IRCD SKID | 30 | 2023-02-24 | 2023-03-26 | 2023-05-28 | 2023-06-27 | 93
0 | PMBKIN2415 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - IRCD SKID | 42 | 2023-04-07 | 2023-05-19 | 2023-06-27 | 2023-08-08 | 81
HIPPS |  |  | 366 | 2022-06-20 | 2023-06-21 | 2022-08-27 | 2023-11-12 | 144
0 | PMEQIN2037 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - HIPPS | 70 | 2022-06-20 | 2022-08-29 | 2022-08-27 | 2022-11-05 | 68
0 | PMEQIN2035 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - HIPPS | 70 | 2022-08-29 | 2022-11-07 | 2022-11-05 | 2023-01-14 | 68
0 | PMEQIN2045 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - HIPPS | 203 | 2022-08-29 | 2023-03-20 | 2022-11-05 | 2023-05-27 | 68
0 | PMEQIN2050 | FINAL ACCEPTANCE TEST (FAT) - HIPPS | 7 | 2023-03-20 | 2023-03-27 | 2023-05-27 | 2023-06-03 | 68
0 | PMEQIN2055 | FOB DELIVERY - HIPPS | 14 | 2023-03-27 | 2023-04-10 | 2023-06-03 | 2023-06-17 | 68
0 | PMEQIN2060 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - HIPPS | 42 | 2023-04-10 | 2023-05-22 | 2023-06-17 | 2023-07-29 | 68
0 | PMEQIN2065 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - HIPPS | 42 | 2023-05-10 | 2023-06-21 | 2023-10-01 | 2023-11-12 | 144
WELLHEAD CONTROL PANEL |  |  | 365 | 2022-06-20 | 2023-06-20 | 2022-09-06 | 2023-09-20 | 92
0 | PMEQIN2072 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - WELLHEAD CONTROL PANEL | 70 | 2022-06-20 | 2022-08-29 | 2022-09-06 | 2022-11-15 | 78
0 | PMEQIN2070 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - WELLHEAD CONTROL PANEL | 70 | 2022-08-29 | 2022-11-07 | 2022-11-15 | 2023-01-24 | 78
0 | PMEQIN2080 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - WELLHEAD CONTROL PANEL | 190 | 2022-08-29 | 2023-03-07 | 2022-11-18 | 2023-05-27 | 81
0 | PMEQIN2085 | FINAL ACCEPTANCE TEST (FAT) - WELLHEAD CONTROL PANEL | 7 | 2023-03-07 | 2023-03-14 | 2023-05-27 | 2023-06-03 | 81
0 | PMEQIN2090 | FOB DELIVERY - WELLHEAD CONTROL PANEL | 14 | 2023-03-14 | 2023-03-28 | 2023-06-03 | 2023-06-17 | 81
0 | PMEQIN2095 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - WELLHEAD CONTROL PANEL | 42 | 2023-03-28 | 2023-05-09 | 2023-06-17 | 2023-07-29 | 81
0 | PMEQIN2100 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - WELLHEAD CONTROL PANEL | 42 | 2023-05-09 | 2023-06-20 | 2023-08-09 | 2023-09-20 | 92
ACTUATED ON/OFF VALVES |  |  | 337 | 2022-07-06 | 2023-06-08 | 2022-09-08 | 2023-09-01 | 85
0 | PMEQIN2107 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - ACTUATED ON/OFF VALVES | 63 | 2022-07-06 | 2022-09-07 | 2022-09-08 | 2022-11-10 | 64
0 | PMEQIN2105 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - ACTUATED ON/OFF VALVES | 63 | 2022-09-07 | 2022-11-09 | 2022-11-22 | 2023-01-24 | 76
0 | PMEQIN2115 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - ACTUATED ON/OFF VALVES | 190 | 2022-09-07 | 2023-03-16 | 2022-12-01 | 2023-06-09 | 85
0 | PMEQIN2120 | FINAL ACCEPTANCE TEST (FAT) - ACTUATED ON/OFF VALVES | 7 | 2023-03-16 | 2023-03-23 | 2023-06-09 | 2023-06-16 | 85
0 | PMEQIN2125 | FOB DELIVERY - ACTUATED ON/OFF VALVES | 14 | 2023-03-23 | 2023-04-06 | 2023-06-16 | 2023-06-30 | 85
0 | PMEQIN2130 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - ACTUATED ON/OFF VALVES | 42 | 2023-04-06 | 2023-05-18 | 2023-06-30 | 2023-08-11 | 85
0 | PMEQIN2135 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - ACTUATED ON/OFF VALVES | 42 | 2023-04-27 | 2023-06-08 | 2023-07-21 | 2023-09-01 | 85
MOTOR OPERATED VALVES (BALL TYPE) |  |  | 362 | 2022-07-06 | 2023-07-03 | 2022-09-08 | 2023-09-01 | 60
0 | PMEQIN2142 | RECEIVE VENDOR DOCUMENTS (CRITICAL)- MOTOR OPERATED VALVES (BALL TYPE) | 70 | 2022-07-06 | 2022-09-14 | 2022-09-08 | 2022-11-17 | 64
0 | PMEQIN2140 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - MOTOR OPERATED VALVES (BALL TYPE) | 70 | 2022-09-14 | 2022-11-23 | 2022-11-22 | 2023-01-31 | 69
0 | PMEQIN2150 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - MOTOR OPERATED VALVES (BALL TYPE) | 190 | 2022-09-14 | 2023-03-23 | 2022-11-22 | 2023-05-31 | 69
0 | PMEQIN2155 | FINAL ACCEPTANCE TEST (FAT) - MOTOR OPERATED VALVES (BALL TYPE) | 7 | 2023-03-23 | 2023-03-30 | 2023-05-31 | 2023-06-07 | 69
0 | PMEQIN2160 | FOB DELIVERY - MOTOR OPERATED VALVES (BALL TYPE) | 14 | 2023-03-30 | 2023-04-13 | 2023-06-07 | 2023-06-21 | 69
0 | PMEQIN2165 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - MOTOR OPERATED VALVES (BALL TYPE) | 42 | 2023-04-13 | 2023-05-25 | 2023-06-21 | 2023-08-02 | 69
0 | PMEQIN2170 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - MOTOR OPERATED VALVES (BALL TYPE) | 42 | 2023-05-22 | 2023-07-03 | 2023-07-21 | 2023-09-01 | 60
MOTOR OPERATED VALVES (IDBB TYPE) |  |  | 355 | 2022-07-06 | 2023-06-26 | 2022-09-08 | 2023-09-01 | 67
0 | PMEQIN2177 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - MOTOR OPERATED VALVES (IDBB TYPE) | 70 | 2022-07-06 | 2022-09-14 | 2022-09-08 | 2022-11-17 | 64
0 | PMEQIN2175 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - MOTOR OPERATED VALVES (IDBB TYPE) | 70 | 2022-09-14 | 2022-11-23 | 2022-11-22 | 2023-01-31 | 69
0 | PMEQIN2185 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - MOTOR OPERATED VALVES (IDBB TYPE) | 190 | 2022-09-14 | 2023-03-23 | 2022-11-22 | 2023-05-31 | 69
0 | PMEQIN2190 | FINAL ACCEPTANCE TEST (FAT) - MOTOR OPERATED VALVES (IDBB TYPE) | 7 | 2023-03-23 | 2023-03-30 | 2023-05-31 | 2023-06-07 | 69
0 | PMEQIN2195 | FOB DELIVERY - MOTOR OPERATED VALVES (IDBB TYPE) | 14 | 2023-03-30 | 2023-04-13 | 2023-06-07 | 2023-06-21 | 69
0 | PMEQIN2200 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - MOTOR OPERATED VALVES (IDBB TYPE) | 42 | 2023-04-13 | 2023-05-25 | 2023-06-21 | 2023-08-02 | 69
0 | PMEQIN2205 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - MOTOR OPERATED VALVES (IDBB TYPE) | 42 | 2023-05-15 | 2023-06-26 | 2023-07-21 | 2023-09-01 | 67
MOTORISED CHOKE VALVES |  |  | 301 | 2022-07-06 | 2023-05-03 | 2022-09-08 | 2023-09-01 | 121
0 | PMEQIN2212 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - MOTORISED CHOKE VALVES | 63 | 2022-07-06 | 2022-09-07 | 2022-09-08 | 2022-11-10 | 64
0 | PMEQIN2210 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - MOTORISED CHOKE VALVES | 63 | 2022-09-07 | 2022-11-09 | 2023-01-06 | 2023-03-10 | 121
0 | PMEQIN2220 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - MOTORISED CHOKE VALVES | 145 | 2022-09-07 | 2023-01-30 | 2023-01-06 | 2023-05-31 | 121
0 | PMEQIN2225 | FINAL ACCEPTANCE TEST (FAT) - MOTORISED CHOKE VALVES | 7 | 2023-01-30 | 2023-02-06 | 2023-05-31 | 2023-06-07 | 121
0 | PMEQIN2230 | FOB DELIVERY - MOTORISED CHOKE VALVES | 14 | 2023-02-06 | 2023-02-20 | 2023-06-07 | 2023-06-21 | 121
0 | PMEQIN2235 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - MOTORISED CHOKE VALVES | 42 | 2023-02-20 | 2023-04-03 | 2023-06-21 | 2023-08-02 | 121
0 | PMEQIN2240 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - MOTORISED CHOKE VALVES | 42 | 2023-03-22 | 2023-05-03 | 2023-07-21 | 2023-09-01 | 121
WET GAS FLOW METER |  |  | 278 | 2022-07-06 | 2023-04-10 | 2022-09-08 | 2023-07-31 | 112
0 | PMEQIN2247 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - WET GAS FLOW METER | 63 | 2022-07-06 | 2022-09-07 | 2022-09-08 | 2022-11-10 | 64
0 | PMEQIN2245 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - WET GAS FLOW METER | 63 | 2022-09-07 | 2022-11-09 | 2022-12-30 | 2023-03-03 | 114
0 | PMEQIN2255 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - WET GAS FLOW METER | 120 | 2022-09-07 | 2023-01-05 | 2022-12-30 | 2023-04-29 | 114
0 | PMEQIN2260 | FINAL ACCEPTANCE TEST (FAT) - WET GAS FLOW METER | 7 | 2023-01-05 | 2023-01-12 | 2023-04-29 | 2023-05-06 | 114
0 | PMEQIN2265 | FOB DELIVERY - WET GAS FLOW METER | 14 | 2023-01-12 | 2023-01-26 | 2023-05-06 | 2023-05-20 | 114
0 | PMEQIN2270 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - WET GAS FLOW METER | 42 | 2023-01-26 | 2023-03-09 | 2023-05-20 | 2023-07-01 | 114
0 | PMEQIN2275 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - WET GAS FLOW METER | 42 | 2023-02-27 | 2023-04-10 | 2023-06-19 | 2023-07-31 | 112
SUBSEA FO CABLE |  |  | 255 | 2022-07-22 | 2023-04-03 | 2022-09-25 | 2023-06-05 | 63
0 | PMEQIN2282 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - SUBSEA FO CABLE | 70 | 2022-07-22 | 2022-09-30 | 2022-09-25 | 2022-12-04 | 65
0 | PMEQIN2280 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - SUBSEA FO CABLE | 70 | 2022-09-30 | 2022-12-09 | 2022-12-12 | 2023-02-20 | 73
0 | PMEQIN2290 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - SUBSEA FO CABLE | 120 | 2022-09-30 | 2023-01-28 | 2022-12-04 | 2023-04-03 | 65
0 | PMEQIN2295 | FINAL ACCEPTANCE TEST (FAT) - SUBSEA FO CABLE | 7 | 2023-01-28 | 2023-02-04 | 2023-04-03 | 2023-04-10 | 65
0 | PMEQIN2300 | FOB DELIVERY - SUBSEA FO CABLE | 14 | 2023-02-04 | 2023-02-18 | 2023-04-10 | 2023-04-24 | 65
0 | PMEQIN2305 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - SUBSEA FO CABLE | 42 | 2023-02-18 | 2023-04-01 | 2023-04-24 | 2023-06-05 | 65
0 | PMEQIN2310 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - SUBSEA FO CABLE | 42 | 2023-02-20 | 2023-04-03 | 2023-04-24 | 2023-06-05 | 63
ELECTRICAL |  |  | 340 | 2022-06-30 | 2023-06-05 | 2022-09-08 | 2023-09-23 | 110
6.6kV RING MAIN UNIT (RMU) |  |  | 335 | 2022-07-05 | 2023-06-05 | 2022-09-08 | 2023-09-23 | 110
0 | PMEQEL2033 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - 6.6kV RING MAIN UNIT (RMU) | 70 | 2022-07-05 | 2022-09-13 | 2022-09-08 | 2022-11-17 | 65
0 | PMEQEL2035 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - 6.6kV RING MAIN UNIT (RMU) | 63 | 2022-09-13 | 2022-11-15 | 2022-11-17 | 2023-01-19 | 65
0 | PMEQEL2045 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - 6.6kV RING MAIN UNIT (RMU) | 172 | 2022-09-13 | 2023-03-04 | 2022-12-02 | 2023-05-23 | 80
0 | PMEQEL2050 | FINAL ACCEPTANCE TEST (FAT) - 6.6kV RING MAIN UNIT (RMU) | 7 | 2023-03-04 | 2023-03-11 | 2023-05-23 | 2023-05-30 | 80
0 | PMEQEL2055 | FOB DELIVERY - 6.6kV RING MAIN UNIT (RMU) | 14 | 2023-03-11 | 2023-03-25 | 2023-05-30 | 2023-06-13 | 80
0 | PMEQEL2060 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - 6.6kV RING MAIN UNIT (RMU) | 42 | 2023-03-25 | 2023-05-06 | 2023-06-13 | 2023-07-25 | 80
0 | PMEQEL2065 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - 6.6kV RING MAIN UNIT (RMU) | 42 | 2023-04-24 | 2023-06-05 | 2023-08-12 | 2023-09-23 | 110
415V SWITCHBOARDS |  |  | 266 | 2022-07-05 | 2023-03-28 | 2022-09-08 | 2023-09-12 | 168
0 | PMEQEL2072 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - 415V SWITCHBOARDS | 63 | 2022-07-05 | 2022-09-06 | 2022-09-08 | 2022-11-10 | 65
0 | PMEQEL2070 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - 415V SWITCHBOARDS | 63 | 2022-09-06 | 2022-11-08 | 2022-11-17 | 2023-01-19 | 72
0 | PMEQEL2080 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - 415V SWITCHBOARDS | 120 | 2022-09-06 | 2023-01-04 | 2023-01-06 | 2023-05-06 | 122
0 | PMEQEL2085 | FINAL ACCEPTANCE TEST (FAT) - 415V SWITCHBOARDS | 7 | 2023-01-04 | 2023-01-11 | 2023-05-06 | 2023-05-13 | 122
0 | PMEQEL2090 | FOB DELIVERY - 415V SWITCHBOARDS | 14 | 2023-01-11 | 2023-01-25 | 2023-05-13 | 2023-05-27 | 122
0 | PMEQEL2095 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - 415V SWITCHBOARDS | 42 | 2023-01-25 | 2023-03-08 | 2023-05-27 | 2023-07-08 | 122
0 | PMEQEL2100 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - 415V SWITCHBOARDS | 42 | 2023-02-14 | 2023-03-28 | 2023-08-01 | 2023-09-12 | 168
6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS |  |  | 306 | 2022-06-30 | 2023-05-02 | 2022-09-08 | 2023-09-23 | 144
0 | PMEQEL2102 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - 6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS | 63 | 2022-06-30 | 2022-09-01 | 2022-09-08 | 2022-11-10 | 70
0 | PMEQEL2105 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - 6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS | 63 | 2022-09-01 | 2022-11-03 | 2023-01-14 | 2023-03-18 | 135
0 | PMEQEL2115 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - 6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS | 150 | 2022-09-01 | 2023-01-29 | 2023-01-14 | 2023-06-13 | 135
0 | PMEQEL2120 | FINAL ACCEPTANCE TEST (FAT) - 6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS | 7 | 2023-01-29 | 2023-02-05 | 2023-06-13 | 2023-06-20 | 135
0 | PMEQEL2125 | FOB DELIVERY - 6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS | 14 | 2023-02-05 | 2023-02-19 | 2023-06-20 | 2023-07-04 | 135
0 | PMEQEL2130 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - 6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS | 42 | 2023-02-19 | 2023-04-02 | 2023-07-04 | 2023-08-15 | 135
0 | PMEQEL2135 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - 6.6 / 0.433 kV DISTRIBUTION TRANSFORMERS | 42 | 2023-03-21 | 2023-05-02 | 2023-08-12 | 2023-09-23 | 144
24V DC UPS |  |  | 325 | 2022-07-05 | 2023-05-26 | 2022-09-08 | 2023-09-23 | 120
0 | PMEQEL2142 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - 24V DC UPS | 70 | 2022-07-05 | 2022-09-13 | 2022-09-08 | 2022-11-17 | 65
0 | PMEQEL2140 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - 24V DC UPS | 63 | 2022-09-13 | 2022-11-15 | 2022-11-17 | 2023-01-19 | 65
0 | PMEQEL2150 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - 24V DC UPS | 150 | 2022-09-13 | 2023-02-10 | 2022-12-24 | 2023-05-23 | 102
0 | PMEQEL2155 | FINAL ACCEPTANCE TEST (FAT) - 24V DC UPS | 7 | 2023-02-10 | 2023-02-17 | 2023-05-23 | 2023-05-30 | 102
0 | PMEQEL2160 | FOB DELIVERY - 24V DC UPS | 14 | 2023-02-17 | 2023-03-03 | 2023-05-30 | 2023-06-13 | 102
0 | PMEQEL2165 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - 24V DC UPS | 42 | 2023-03-03 | 2023-04-14 | 2023-06-13 | 2023-07-25 | 102
0 | PMEQEL2170 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - 24V DC UPS | 42 | 2023-04-14 | 2023-05-26 | 2023-08-12 | 2023-09-23 | 120
NAVIGATIONAL AIDS SYSTEM |  |  | 269 | 2022-08-15 | 2023-05-11 | 2022-11-14 | 2023-09-23 | 135
0 | PMEQEL2172 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - NAVIGATIONAL AIDS SYSTEM | 56 | 2022-08-15 | 2022-10-10 | 2022-11-14 | 2023-01-09 | 91
0 | PMEQEL2175 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - NAVIGATIONAL AIDS SYSTEM | 56 | 2022-10-10 | 2022-12-05 | 2023-02-07 | 2023-04-04 | 120
0 | PMEQEL2185 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - NAVIGATIONAL AIDS SYSTEM | 120 | 2022-10-10 | 2023-02-07 | 2023-01-09 | 2023-05-09 | 91
0 | PMEQEL2190 | FINAL ACCEPTANCE TEST (FAT) - NAVIGATIONAL AIDS SYSTEM | 7 | 2023-02-07 | 2023-02-14 | 2023-05-09 | 2023-05-16 | 91
0 | PMEQEL2195 | FOB DELIVERY - NAVIGATIONAL AIDS SYSTEM | 14 | 2023-02-14 | 2023-02-28 | 2023-05-16 | 2023-05-30 | 91
0 | PMEQEL2200 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - NAVIGATIONAL AIDS SYSTEM | 42 | 2023-02-28 | 2023-04-11 | 2023-05-30 | 2023-07-11 | 91
0 | PMEQEL2205 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - NAVIGATIONAL AIDS SYSTEM | 42 | 2023-03-30 | 2023-05-11 | 2023-08-12 | 2023-09-23 | 135
BIRD DETERRENT SYSTEM |  |  | 257 | 2022-08-29 | 2023-05-13 | 2022-12-10 | 2023-09-23 | 133
0 | PMEQEL2212 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - BIRD DETERRENT SYSTEM | 56 | 2022-08-29 | 2022-10-24 | 2022-12-10 | 2023-02-04 | 103
0 | PMEQEL2210 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - BIRD DETERRENT SYSTEM | 56 | 2022-10-24 | 2022-12-19 | 2023-03-12 | 2023-05-07 | 139
0 | PMEQEL2220 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - BIRD DETERRENT SYSTEM | 120 | 2022-10-24 | 2023-02-21 | 2023-02-04 | 2023-06-04 | 103
0 | PMEQEL2225 | FINAL ACCEPTANCE TEST (FAT) - BIRD DETERRENT SYSTEM | 7 | 2023-02-21 | 2023-02-28 | 2023-06-04 | 2023-06-11 | 103
0 | PMEQEL2230 | FOB DELIVERY - BIRD DETERRENT SYSTEM | 14 | 2023-02-28 | 2023-03-14 | 2023-06-11 | 2023-06-25 | 103
0 | PMEQEL2235 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - BIRD DETERRENT SYSTEM | 30 | 2023-03-14 | 2023-04-13 | 2023-06-25 | 2023-07-25 | 103
0 | PMEQEL2240 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - BIRD DETERRENT SYSTEM | 30 | 2023-04-13 | 2023-05-13 | 2023-08-24 | 2023-09-23 | 133
LV DISTRIBUTION BOARDS |  |  | 281 | 2022-07-05 | 2023-04-12 | 2022-09-08 | 2023-09-21 | 162
0 | PMEQEL2247 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - LV DISTRIBUTION BOARDS | 56 | 2022-07-05 | 2022-08-30 | 2022-09-08 | 2022-11-03 | 65
0 | PMEQEL2245 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - LV DISTRIBUTION BOARDS | 56 | 2022-08-30 | 2022-10-25 | 2022-11-24 | 2023-01-19 | 86
0 | PMEQEL2255 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - LV DISTRIBUTION BOARDS | 120 | 2022-08-30 | 2022-12-28 | 2022-12-16 | 2023-04-15 | 108
0 | PMEQEL2260 | FINAL ACCEPTANCE TEST (FAT) - LV DISTRIBUTION BOARDS | 7 | 2022-12-28 | 2023-01-04 | 2023-04-15 | 2023-04-22 | 108
0 | PMEQEL2265 | FOB DELIVERY - LV DISTRIBUTION BOARDS | 14 | 2023-01-04 | 2023-01-18 | 2023-04-22 | 2023-05-06 | 108
0 | PMEQEL2270 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - LV DISTRIBUTION BOARDS | 42 | 2023-01-18 | 2023-03-01 | 2023-05-06 | 2023-06-17 | 108
0 | PMEQEL2275 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - LV DISTRIBUTION BOARDS | 42 | 2023-03-01 | 2023-04-12 | 2023-08-10 | 2023-09-21 | 162
BULK MATERIAL |  |  | 401 | 2022-04-04 | 2023-05-10 | 2022-07-24 | 2023-11-09 | 183
STRUCTURAL |  |  | 332 | 2022-04-04 | 2023-03-02 | 2022-07-24 | 2023-10-27 | 239
CS PLATES |  |  | 144 | 2022-04-04 | 2022-08-26 | 2022-08-09 | 2023-01-09 | 136
0 | PMBKSR2002 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - CS PLATES | 14 | 2022-04-04 | 2022-04-18 | 2022-08-09 | 2022-08-23 | 127
0 | PMBKSR2000 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - CS PLATES | 14 | 2022-04-18 | 2022-05-02 | 2022-08-23 | 2022-09-06 | 127
0 | PMBKSR2010 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - CS PLATES | 56 | 2022-04-18 | 2022-06-13 | 2022-08-23 | 2022-10-18 | 127
0 | PMBKSR2015 | FINAL ACCEPTANCE TEST (FAT) - CS PLATES | 7 | 2022-06-13 | 2022-06-20 | 2022-10-18 | 2022-10-25 | 127
0 | PMBKSR2020 | FOB DELIVERY - CS PLATES | 7 | 2022-06-20 | 2022-06-27 | 2022-10-25 | 2022-11-01 | 127
0 | PMBKSR2025 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - CS PLATES | 30 | 2022-06-27 | 2022-07-27 | 2022-11-01 | 2022-12-01 | 127
0 | PMBKSR2030 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - CS PLATES | 30 | 2022-07-27 | 2022-08-26 | 2022-12-10 | 2023-01-09 | 136
ROLLED SECTIONS |  |  | 176 | 2022-04-04 | 2022-09-27 | 2022-08-03 | 2023-02-13 | 139
0 | PMBKSR2037 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - ROLLED SECTIONS | 42 | 2022-04-04 | 2022-05-16 | 2022-08-03 | 2022-09-14 | 121
0 | PMBKSR2035 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - ROLLED SECTIONS | 21 | 2022-05-16 | 2022-06-06 | 2022-09-23 | 2022-10-14 | 130
0 | PMBKSR2045 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - ROLLED SECTIONS | 60 | 2022-05-16 | 2022-07-15 | 2022-09-14 | 2022-11-13 | 121
0 | PMBKSR2050 | FINAL ACCEPTANCE TEST (FAT) - ROLLED SECTIONS | 7 | 2022-07-15 | 2022-07-22 | 2022-11-13 | 2022-11-20 | 121
0 | PMBKSR2055 | FOB DELIVERY - ROLLED SECTIONS | 7 | 2022-07-22 | 2022-07-29 | 2022-11-20 | 2022-11-27 | 121
0 | PMBKSR2060 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - ROLLED SECTIONS | 30 | 2022-07-29 | 2022-08-28 | 2022-11-27 | 2022-12-27 | 121
0 | PMBKSR2065 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - ROLLED SECTIONS | 30 | 2022-08-28 | 2022-09-27 | 2023-01-14 | 2023-02-13 | 139
SAW TUBULAR |  |  | 183 | 2022-04-04 | 2022-10-04 | 2022-07-24 | 2023-01-25 | 113
0 | PMBKSR2072 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - SAW TUBULAR | 42 | 2022-04-04 | 2022-05-16 | 2022-07-24 | 2022-09-04 | 111
0 | PMBKSR2070 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - SAW TUBULAR | 21 | 2022-05-16 | 2022-06-06 | 2022-09-04 | 2022-09-25 | 111
0 | PMBKSR2080 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - SAW TUBULAR | 67 | 2022-05-16 | 2022-07-22 | 2022-09-04 | 2022-11-10 | 111
0 | PMBKSR2085 | FINAL ACCEPTANCE TEST (FAT) - SAW TUBULAR | 7 | 2022-07-22 | 2022-07-29 | 2022-11-10 | 2022-11-17 | 111
0 | PMBKSR2090 | FOB DELIVERY - SAW TUBULAR | 7 | 2022-07-29 | 2022-08-05 | 2022-11-17 | 2022-11-24 | 111
0 | PMBKSR2095 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - SAW TUBULAR | 30 | 2022-08-05 | 2022-09-04 | 2022-11-24 | 2022-12-24 | 111
0 | PMBKSR2100 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - SAW TUBULAR | 30 | 2022-09-04 | 2022-10-04 | 2022-12-26 | 2023-01-25 | 113
SEAMLESS TUBULAR |  |  | 182 | 2022-04-04 | 2022-10-03 | 2022-07-25 | 2023-02-23 | 143
0 | PMBKSR2102 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - SEAMLESS TUBULAR | 42 | 2022-04-04 | 2022-05-16 | 2022-07-25 | 2022-09-05 | 112
0 | PMBKSR2105 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - SEAMLESS TUBULAR | 21 | 2022-05-16 | 2022-06-06 | 2022-09-05 | 2022-09-26 | 112
0 | PMBKSR2115 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - SEAMLESS TUBULAR | 60 | 2022-05-22 | 2022-07-21 | 2022-09-11 | 2022-11-10 | 112
0 | PMBKSR2120 | FINAL ACCEPTANCE TEST (FAT) - SEAMLESS TUBULAR | 7 | 2022-07-21 | 2022-07-28 | 2022-11-10 | 2022-11-17 | 112
0 | PMBKSR2125 | FOB DELIVERY - SEAMLESS TUBULAR | 7 | 2022-07-28 | 2022-08-04 | 2022-11-17 | 2022-11-24 | 112
0 | PMBKSR2130 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - SEAMLESS TUBULAR | 30 | 2022-08-04 | 2022-09-03 | 2022-11-24 | 2022-12-24 | 112
0 | PMBKSR2135 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - SEAMLESS TUBULAR | 30 | 2022-09-03 | 2022-10-03 | 2023-01-24 | 2023-02-23 | 143
CS GRATINGS & STAIR TREADS |  |  | 209 | 2022-07-07 | 2023-02-01 | 2022-10-15 | 2023-07-26 | 175
0 | PMBKSR2142 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - CS GRATINGS & STAIR TREADS | 42 | 2022-07-07 | 2022-08-18 | 2022-10-15 | 2022-11-26 | 100
0 | PMBKSR2140 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - CS GRATINGS & STAIR TREADS | 42 | 2022-08-18 | 2022-09-29 | 2022-11-29 | 2023-01-10 | 103
0 | PMBKSR2150 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - CS GRATINGS & STAIR TREADS | 80 | 2022-08-18 | 2022-11-06 | 2022-11-26 | 2023-02-14 | 100
0 | PMBKSR2155 | FINAL ACCEPTANCE TEST (FAT) - CS GRATINGS & STAIR TREADS | 7 | 2022-11-06 | 2022-11-13 | 2023-02-14 | 2023-02-21 | 100
0 | PMBKSR2160 | FOB DELIVERY - CS GRATINGS & STAIR TREADS | 7 | 2022-11-13 | 2022-11-20 | 2023-02-21 | 2023-02-28 | 100
0 | PMBKSR2165 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - CS GRATINGS & STAIR TREADS | 30 | 2022-11-20 | 2022-12-20 | 2023-02-28 | 2023-03-30 | 100
0 | PMBKSR2170 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - CS GRATINGS & STAIR TREADS | 30 | 2023-01-02 | 2023-02-01 | 2023-06-26 | 2023-07-26 | 175
MISCELLANEOUS STRUCTURAL ITEMS |  |  | 179 | 2022-08-09 | 2023-02-04 | 2022-12-18 | 2023-06-15 | 131
0 | PMBKSR2173 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - MISCELLANEOUS STRUCTURAL ITEM | 42 | 2022-08-09 | 2022-09-20 | 2022-12-18 | 2023-01-29 | 131
0 | PMBKSR2175 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - MISCELLANEOUS STRUCTURAL ITEM | 24 | 2022-09-20 | 2022-10-14 | 2023-02-09 | 2023-03-05 | 142
0 | PMBKSR2185 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - MISCELLANEOUS STRUCTURAL ITEM | 63 | 2022-09-20 | 2022-11-22 | 2023-01-29 | 2023-04-02 | 131
0 | PMBKSR2190 | FINAL ACCEPTANCE TEST (FAT) - MISCELLANEOUS STRUCTURAL ITEM | 7 | 2022-11-22 | 2022-11-29 | 2023-04-02 | 2023-04-09 | 131
0 | PMBKSR2195 | FOB DELIVERY - MISCELLANEOUS STRUCTURAL ITEM | 7 | 2022-11-29 | 2022-12-06 | 2023-04-09 | 2023-04-16 | 131
0 | PMBKSR2200 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - MISCELLANEOUS STRUCTURAL ITEM | 30 | 2022-12-06 | 2023-01-05 | 2023-04-16 | 2023-05-16 | 131
0 | PMBKSR2205 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - MISCELLANEOUS STRUCTURAL ITEM | 30 | 2023-01-05 | 2023-02-04 | 2023-05-16 | 2023-06-15 | 131
GROUTING MATERIAL |  |  | 168 | 2022-08-16 | 2023-01-31 | 2022-11-24 | 2023-07-26 | 176
0 | PMBKSR2212 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - GROUTING MATERIAL | 42 | 2022-08-16 | 2022-09-27 | 2022-11-24 | 2023-01-05 | 100
0 | PMBKSR2210 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - GROUTING MATERIAL | 28 | 2022-09-27 | 2022-10-25 | 2023-01-10 | 2023-02-07 | 105
0 | PMBKSR2220 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - GROUTING MATERIAL | 40 | 2022-09-27 | 2022-11-06 | 2023-01-05 | 2023-02-14 | 100
0 | PMBKSR2225 | FINAL ACCEPTANCE TEST (FAT) - GROUTING MATERIAL | 7 | 2022-11-06 | 2022-11-13 | 2023-02-14 | 2023-02-21 | 100
0 | PMBKSR2230 | FOB DELIVERY - GROUTING MATERIAL | 7 | 2022-11-13 | 2022-11-20 | 2023-02-21 | 2023-02-28 | 100
0 | PMBKSR2235 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - GROUTING MATERIAL | 30 | 2022-11-20 | 2022-12-20 | 2023-02-28 | 2023-03-30 | 100
0 | PMBKSR2240 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - GROUTING MATERIAL | 30 | 2023-01-01 | 2023-01-31 | 2023-06-26 | 2023-07-26 | 176
BOLTS, NUTS & WASHERS |  |  | 184 | 2022-07-26 | 2023-01-26 | 2022-11-04 | 2023-06-12 | 137
0 | PMBKSR2243 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - BOLTS, NUTS & WASHERS | 42 | 2022-07-26 | 2022-09-06 | 2022-11-04 | 2022-12-16 | 101
0 | PMBKSR2245 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - BOLTS, NUTS & WASHERS | 28 | 2022-09-06 | 2022-10-04 | 2023-01-17 | 2023-02-14 | 133
0 | PMBKSR2255 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - BOLTS, NUTS & WASHERS | 60 | 2022-09-06 | 2022-11-05 | 2022-12-16 | 2023-02-14 | 101
0 | PMBKSR2260 | FINAL ACCEPTANCE TEST (FAT) - BOLTS, NUTS & WASHERS | 7 | 2022-11-05 | 2022-11-12 | 2023-02-14 | 2023-02-21 | 101
0 | PMBKSR2265 | FOB DELIVERY - BOLTS, NUTS & WASHERS | 7 | 2022-11-12 | 2022-11-19 | 2023-02-21 | 2023-02-28 | 101
0 | PMBKSR2270 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - BOLTS, NUTS & WASHERS | 30 | 2022-11-19 | 2022-12-19 | 2023-02-28 | 2023-03-30 | 101
0 | PMBKSR2275 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - BOLTS, NUTS & WASHERS | 30 | 2022-12-27 | 2023-01-26 | 2023-05-13 | 2023-06-12 | 137
CATHODIC PROTECTION [SACRIFICIAL ANODES] |  |  | 196 | 2022-07-19 | 2023-01-31 | 2022-10-30 | 2023-09-12 | 224
0 | PMBKSR2282 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - CATHODIC PROTECTION [SACRIFICIAL ANODES] | 42 | 2022-07-19 | 2022-08-30 | 2022-10-30 | 2022-12-11 | 103
0 | PMBKSR2280 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - CATHODIC PROTECTION [SACRIFICIAL ANODES] | 42 | 2022-08-30 | 2022-10-11 | 2022-12-20 | 2023-01-31 | 112
0 | PMBKSR2290 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - CATHODIC PROTECTION [SACRIFICIAL ANODES] | 65 | 2022-08-30 | 2022-11-03 | 2022-12-11 | 2023-02-14 | 103
0 | PMBKSR2295 | FINAL ACCEPTANCE TEST (FAT) - CATHODIC PROTECTION [SACRIFICIAL ANODES] | 7 | 2022-11-03 | 2022-11-10 | 2023-02-14 | 2023-02-21 | 103
0 | PMBKSR2300 | FOB DELIVERY - CATHODIC PROTECTION [SACRIFICIAL ANODES] | 7 | 2022-11-10 | 2022-11-17 | 2023-02-21 | 2023-02-28 | 103
0 | PMBKSR2305 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - CATHODIC PROTECTION [SACRIFICIAL ANODES] | 30 | 2022-11-17 | 2022-12-17 | 2023-02-28 | 2023-03-30 | 103
0 | PMBKSR2310 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - CATHODIC PROTECTION [SACRIFICIAL ANODES] | 30 | 2023-01-01 | 2023-01-31 | 2023-08-13 | 2023-09-12 | 224
HELI DECK SAFETY NET |  |  | 212 | 2022-08-02 | 2023-03-02 | 2022-11-24 | 2023-08-24 | 175
0 | PMBKSR2313 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - HELI DECK SAFETY NET | 42 | 2022-08-02 | 2022-09-13 | 2022-11-24 | 2023-01-05 | 114
0 | PMBKSR2315 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - HELI DECK SAFETY NET | 42 | 2022-09-13 | 2022-10-25 | 2023-02-28 | 2023-04-11 | 168
0 | PMBKSR2325 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - HELI DECK SAFETY NET | 96 | 2022-09-13 | 2022-12-18 | 2023-01-05 | 2023-04-11 | 114
0 | PMBKSR2330 | FINAL ACCEPTANCE TEST (FAT) - HELI DECK SAFETY NET | 7 | 2022-12-18 | 2022-12-25 | 2023-04-11 | 2023-04-18 | 114
0 | PMBKSR2335 | FOB DELIVERY - HELI DECK SAFETY NET | 7 | 2022-12-25 | 2023-01-01 | 2023-04-18 | 2023-04-25 | 114
0 | PMBKSR2340 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - HELI DECK SAFETY NET | 30 | 2023-01-01 | 2023-01-31 | 2023-04-25 | 2023-05-25 | 114
0 | PMBKSR2345 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - HELI DECK SAFETY NET | 30 | 2023-01-31 | 2023-03-02 | 2023-07-25 | 2023-08-24 | 175
SWING ROPE ASSEMBLY |  |  | 172 | 2022-08-16 | 2023-02-04 | 2023-02-26 | 2023-10-27 | 265
0 | PMBKSR2352 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - SWING ROPE ASSEMBLY | 42 | 2022-08-16 | 2022-09-27 | 2023-02-26 | 2023-04-09 | 194
0 | PMBKSR2350 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - SWING ROPE ASSEMBLY | 24 | 2022-09-27 | 2022-10-21 | 2023-04-13 | 2023-05-07 | 198
0 | PMBKSR2360 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - SWING ROPE ASSEMBLY | 56 | 2022-09-27 | 2022-11-22 | 2023-04-09 | 2023-06-04 | 194
0 | PMBKSR2365 | FINAL ACCEPTANCE TEST (FAT) - SWING ROPE ASSEMBLY | 7 | 2022-11-22 | 2022-11-29 | 2023-06-04 | 2023-06-11 | 194
0 | PMBKSR2370 | FOB DELIVERY - SWING ROPE ASSEMBLY | 7 | 2022-11-29 | 2022-12-06 | 2023-06-11 | 2023-06-18 | 194
0 | PMBKSR2375 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - SWING ROPE ASSEMBLY | 30 | 2022-12-06 | 2023-01-05 | 2023-06-18 | 2023-07-18 | 194
0 | PMBKSR2380 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - SWING ROPE ASSEMBLY | 30 | 2023-01-05 | 2023-02-04 | 2023-09-27 | 2023-10-27 | 265
PIPING |  |  | 245 | 2022-05-19 | 2023-01-19 | 2022-09-19 | 2023-04-28 | 99
BALL VALVES (CS/LTCS/CLADDED) |  |  | 199 | 2022-06-28 | 2023-01-13 | 2022-10-11 | 2023-04-28 | 105
0 | PMBKPI2002 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - BALL VALVES (CS/LTCS/CLADDED) | 63 | 2022-06-28 | 2022-08-30 | 2022-10-11 | 2022-12-13 | 105
0 | PMBKPI2000 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - BALL VALVES (CS/LTCS/CLADDED) | 49 | 2022-08-30 | 2022-10-18 | 2022-12-13 | 2023-01-31 | 105
0 | PMBKPI2010 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - BALL VALVES (CS/LTCS/CLADDED) | 55 | 2022-08-30 | 2022-10-24 | 2022-12-13 | 2023-02-06 | 105
0 | PMBKPI2015 | FINAL ACCEPTANCE TEST (FAT) - BALL VALVES (CS/LTCS/CLADDED) | 7 | 2022-10-24 | 2022-10-31 | 2023-02-06 | 2023-02-13 | 105
0 | PMBKPI2020 | FOB DELIVERY - BALL VALVES (CS/LTCS/CLADDED) | 14 | 2022-10-31 | 2022-11-14 | 2023-02-13 | 2023-02-27 | 105
0 | PMBKPI2025 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - BALL VALVES (CS/LTCS/CLADDED) | 30 | 2022-11-14 | 2022-12-14 | 2023-02-27 | 2023-03-29 | 105
0 | PMBKPI2030 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - BALL VALVES (CS/LTCS/CLADDED) | 30 | 2022-12-14 | 2023-01-13 | 2023-03-29 | 2023-04-28 | 105
BALL VALVES (API 6A) |  |  | 188 | 2022-07-05 | 2023-01-09 | 2022-10-27 | 2023-04-28 | 109
0 | PMBKPI2042 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - BALL VALVES (API 6A) | 63 | 2022-07-05 | 2022-09-06 | 2022-10-27 | 2022-12-29 | 114
0 | PMBKPI2040 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - BALL VALVES (API 6A) | 42 | 2022-09-06 | 2022-10-18 | 2022-12-29 | 2023-02-09 | 114
0 | PMBKPI2050 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - BALL VALVES (API 6A) | 49 | 2022-09-06 | 2022-10-25 | 2022-12-29 | 2023-02-16 | 114
0 | PMBKPI2055 | FINAL ACCEPTANCE TEST (FAT) - BALL VALVES (API 6A) | 7 | 2022-10-25 | 2022-11-01 | 2023-02-16 | 2023-02-23 | 114
0 | PMBKPI2060 | FOB DELIVERY - BALL VALVES (API 6A) | 14 | 2022-11-01 | 2022-11-15 | 2023-02-23 | 2023-03-09 | 114
0 | PMBKPI2065 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - BALL VALVES (API 6A) | 30 | 2022-11-15 | 2022-12-15 | 2023-03-09 | 2023-04-08 | 114
0 | PMBKPI2070 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - BALL VALVES (API 6A) | 30 | 2022-12-10 | 2023-01-09 | 2023-03-29 | 2023-04-28 | 109
GATE VALVES (CS/LTCS/CRA) |  |  | 195 | 2022-07-05 | 2023-01-16 | 2022-10-16 | 2023-04-28 | 102
0 | PMBKPI2077 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - GATE VALVES (CS/LTCS/CRA) | 63 | 2022-07-05 | 2022-09-06 | 2022-10-16 | 2022-12-18 | 103
0 | PMBKPI2075 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - GATE VALVES (CS/LTCS/CRA) | 63 | 2022-09-06 | 2022-11-08 | 2022-12-18 | 2023-02-19 | 103
0 | PMBKPI2085 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - GATE VALVES (CS/LTCS/CRA) | 65 | 2022-09-06 | 2022-11-10 | 2022-12-18 | 2023-02-21 | 103
0 | PMBKPI2090 | FINAL ACCEPTANCE TEST (FAT) - GATE VALVES (CS/LTCS/CRA) | 7 | 2022-11-10 | 2022-11-17 | 2023-02-21 | 2023-02-28 | 103
0 | PMBKPI2095 | FOB DELIVERY - GATE VALVES (CS/LTCS/CRA) | 14 | 2022-11-17 | 2022-12-01 | 2023-02-28 | 2023-03-14 | 103
0 | PMBKPI2100 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - GATE VALVES (CS/LTCS/CRA) | 30 | 2022-12-01 | 2022-12-31 | 2023-03-14 | 2023-04-13 | 103
0 | PMBKPI2105 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - GATE VALVES (CS/LTCS/CRA) | 30 | 2022-12-17 | 2023-01-16 | 2023-03-29 | 2023-04-28 | 102
GATE VALVES (API) |  |  | 198 | 2022-07-05 | 2023-01-19 | 2022-10-12 | 2023-04-28 | 99
0 | PMBKPI2112 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - GATE VALVES (API) | 63 | 2022-07-05 | 2022-09-06 | 2022-10-12 | 2022-12-14 | 99
0 | PMBKPI2110 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - GATE VALVES (API) | 63 | 2022-09-06 | 2022-11-08 | 2022-12-14 | 2023-02-15 | 99
0 | PMBKPI2120 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - GATE VALVES (API) | 69 | 2022-09-06 | 2022-11-14 | 2022-12-14 | 2023-02-21 | 99
0 | PMBKPI2125 | FINAL ACCEPTANCE TEST (FAT) - GATE VALVES (API) | 7 | 2022-11-14 | 2022-11-21 | 2023-02-21 | 2023-02-28 | 99
0 | PMBKPI2130 | FOB DELIVERY - GATE VALVES (API) | 14 | 2022-11-21 | 2022-12-05 | 2023-02-28 | 2023-03-14 | 99
0 | PMBKPI2135 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - GATE VALVES (API) | 30 | 2022-12-05 | 2023-01-04 | 2023-03-14 | 2023-04-13 | 99
0 | PMBKPI2140 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - GATE VALVES (API) | 30 | 2022-12-20 | 2023-01-19 | 2023-03-29 | 2023-04-28 | 99
GLOBE, PISTON LIFT CHECK VALVES (CS/LTCS/CRA) |  |  | 186 | 2022-07-15 | 2023-01-17 | 2022-10-24 | 2023-04-28 | 101
0 | PMBKPI2147 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - GATE, GLOBE, PISTON LIFT CHECK & NEEDLE VALVES | 63 | 2022-07-15 | 2022-09-16 | 2022-10-24 | 2022-12-26 | 101
0 | PMBKPI2145 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - GATE, GLOBE, PISTON LIFT CHECK & NEEDLE VALVES | 49 | 2022-09-16 | 2022-11-04 | 2022-12-26 | 2023-02-13 | 101
0 | PMBKPI2155 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - GATE, GLOBE, PISTON LIFT CHECK & NEEDLE VALVES | 52 | 2022-09-16 | 2022-11-07 | 2022-12-26 | 2023-02-16 | 101
0 | PMBKPI2160 | FINAL ACCEPTANCE TEST (FAT) - GATE, GLOBE, PISTON LIFT CHECK & NEEDLE VALVES | 7 | 2022-11-07 | 2022-11-14 | 2023-02-16 | 2023-02-23 | 101
0 | PMBKPI2165 | FOB DELIVERY - GATE, GLOBE, PISTON LIFT CHECK & NEEDLE VALVES | 14 | 2022-11-14 | 2022-11-28 | 2023-02-23 | 2023-03-09 | 101
0 | PMBKPI2170 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - GATE, GLOBE, PISTON LIFT CHECK & NEEDLE VALVES | 30 | 2022-11-28 | 2022-12-28 | 2023-03-09 | 2023-04-08 | 101
0 | PMBKPI2175 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - GATE, GLOBE, PISTON LIFT CHECK & NEEDLE VALVES | 30 | 2022-12-18 | 2023-01-17 | 2023-03-29 | 2023-04-28 | 101
GLOBE, PISTON LIFT CHECK VALVES (API) |  |  | 187 | 2022-07-15 | 2023-01-18 | 2022-10-23 | 2023-04-28 | 100
0 | PMBKPI2182 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - GLOBE, PISTON LIFT CHECK VALVES (API) | 63 | 2022-07-15 | 2022-09-16 | 2022-10-23 | 2022-12-25 | 100
0 | PMBKPI2180 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - GLOBE, PISTON LIFT CHECK VALVES (API) | 56 | 2022-09-16 | 2022-11-11 | 2022-12-25 | 2023-02-19 | 100
0 | PMBKPI2190 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - GLOBE, PISTON LIFT CHECK VALVES (API) | 58 | 2022-09-16 | 2022-11-13 | 2022-12-25 | 2023-02-21 | 100
0 | PMBKPI2195 | FINAL ACCEPTANCE TEST (FAT) - GLOBE, PISTON LIFT CHECK VALVES (API) | 7 | 2022-11-13 | 2022-11-20 | 2023-02-21 | 2023-02-28 | 100
0 | PMBKPI2200 | FOB DELIVERY - GLOBE, PISTON LIFT CHECK VALVES (API) | 14 | 2022-11-20 | 2022-12-04 | 2023-02-28 | 2023-03-14 | 100
0 | PMBKPI2205 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - GLOBE, PISTON LIFT CHECK VALVES (API) | 30 | 2022-12-04 | 2023-01-03 | 2023-03-14 | 2023-04-13 | 100
0 | PMBKPI2210 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - GLOBE, PISTON LIFT CHECK VALVES (API) | 30 | 2022-12-19 | 2023-01-18 | 2023-03-29 | 2023-04-28 | 100
IDBB VALVES (CS/LTCS/CRA) |  |  | 190 | 2022-07-13 | 2023-01-19 | 2022-10-20 | 2023-04-28 | 99
0 | PMBKPI2217 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - IDBB VALVES (CS/LTCS/CRA) | 63 | 2022-07-13 | 2022-09-14 | 2022-10-20 | 2022-12-22 | 99
0 | PMBKPI2215 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - IDBB VALVES (CS/LTCS/CRA) | 49 | 2022-09-14 | 2022-11-02 | 2022-12-22 | 2023-02-09 | 99
0 | PMBKPI2225 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - IDBB VALVES (CS/LTCS/CRA) | 56 | 2022-09-14 | 2022-11-09 | 2022-12-22 | 2023-02-16 | 99
0 | PMBKPI2230 | FINAL ACCEPTANCE TEST (FAT) - IDBB VALVES (CS/LTCS/CRA) | 7 | 2022-11-09 | 2022-11-16 | 2023-02-16 | 2023-02-23 | 99
0 | PMBKPI2235 | FOB DELIVERY - IDBB VALVES (CS/LTCS/CRA) | 14 | 2022-11-16 | 2022-11-30 | 2023-02-23 | 2023-03-09 | 99
0 | PMBKPI2240 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - IDBB VALVES (CS/LTCS/CRA) | 30 | 2022-11-30 | 2022-12-30 | 2023-03-09 | 2023-04-08 | 99
0 | PMBKPI2245 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - IDBB VALVES (CS/LTCS/CRA) | 30 | 2022-12-20 | 2023-01-19 | 2023-03-29 | 2023-04-28 | 99
IDBB VALVES (API 6A) |  |  | 202 | 2022-06-27 | 2023-01-15 | 2022-10-08 | 2023-04-28 | 103
0 | PMBKPI2252 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - IDBB VALVES (API 6A) | 63 | 2022-06-27 | 2022-08-29 | 2022-10-08 | 2022-12-10 | 103
0 | PMBKPI2250 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - IDBB VALVES (API 6A) | 63 | 2022-08-29 | 2022-10-31 | 2022-12-10 | 2023-02-11 | 103
0 | PMBKPI2260 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - IDBB VALVES (API 6A) | 68 | 2022-08-29 | 2022-11-05 | 2022-12-10 | 2023-02-16 | 103
0 | PMBKPI2265 | FINAL ACCEPTANCE TEST (FAT) - IDBB VALVES (API 6A) | 7 | 2022-11-05 | 2022-11-12 | 2023-02-16 | 2023-02-23 | 103
0 | PMBKPI2270 | FOB DELIVERY - IDBB VALVES (API 6A) | 14 | 2022-11-12 | 2022-11-26 | 2023-02-23 | 2023-03-09 | 103
0 | PMBKPI2275 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - IDBB VALVES (API 6A) | 30 | 2022-11-26 | 2022-12-26 | 2023-03-09 | 2023-04-08 | 103
0 | PMBKPI2280 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - IDBB VALVES (API 6A) | 30 | 2022-12-16 | 2023-01-15 | 2023-03-29 | 2023-04-28 | 103
BUTTERFLY VALVES |  |  | 197 | 2022-07-06 | 2023-01-19 | 2022-10-13 | 2023-04-28 | 99
0 | PMBKPI2283 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - BUTTERFLY VALVES | 63 | 2022-07-06 | 2022-09-07 | 2022-10-13 | 2022-12-15 | 99
0 | PMBKPI2285 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - BUTTERFLY VALVES | 56 | 2022-09-07 | 2022-11-02 | 2022-12-15 | 2023-02-09 | 99
0 | PMBKPI2295 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - BUTTERFLY VALVES | 68 | 2022-09-07 | 2022-11-14 | 2022-12-15 | 2023-02-21 | 99
0 | PMBKPI2300 | FINAL ACCEPTANCE TEST (FAT) - BUTTERFLY VALVES | 7 | 2022-11-14 | 2022-11-21 | 2023-02-21 | 2023-02-28 | 99
0 | PMBKPI2305 | FOB DELIVERY - BUTTERFLY VALVES | 14 | 2022-11-21 | 2022-12-05 | 2023-02-28 | 2023-03-14 | 99
0 | PMBKPI2310 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - BUTTERFLY VALVES | 30 | 2022-12-05 | 2023-01-04 | 2023-03-14 | 2023-04-13 | 99
0 | PMBKPI2315 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - BUTTERFLY VALVES | 30 | 2022-12-20 | 2023-01-19 | 2023-03-29 | 2023-04-28 | 99
SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) |  |  | 197 | 2022-07-06 | 2023-01-19 | 2022-10-13 | 2023-04-28 | 99
0 | PMBKPI3205 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 63 | 2022-07-06 | 2022-09-07 | 2022-10-13 | 2022-12-15 | 99
0 | PMBKPI2320 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 56 | 2022-09-07 | 2022-11-02 | 2022-12-15 | 2023-02-09 | 99
0 | PMBKPI2330 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 63 | 2022-09-07 | 2022-11-09 | 2022-12-15 | 2023-02-16 | 99
0 | PMBKPI2335 | FINAL ACCEPTANCE TEST (FAT) - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 7 | 2022-11-09 | 2022-11-16 | 2023-02-16 | 2023-02-23 | 99
0 | PMBKPI2340 | FOB DELIVERY - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 14 | 2022-11-16 | 2022-11-30 | 2023-02-23 | 2023-03-09 | 99
0 | PMBKPI2345 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 30 | 2022-11-30 | 2022-12-30 | 2023-03-09 | 2023-04-08 | 99
0 | PMBKPI2350 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - SWING CHECK VALVES (CS/LTCS/CRA/CLADDED) | 30 | 2022-12-20 | 2023-01-19 | 2023-03-29 | 2023-04-28 | 99
SWING CHECK VALVES (API) |  |  | 190 | 2022-07-13 | 2023-01-19 | 2022-10-20 | 2023-04-28 | 99
0 | PMBKPI3215 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - SWING CHECK VALVES (API) | 63 | 2022-07-13 | 2022-09-14 | 2022-10-20 | 2022-12-22 | 99
0 | PMBKPI2355 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - SWING CHECK VALVES (API) | 56 | 2022-09-14 | 2022-11-09 | 2022-12-22 | 2023-02-16 | 99
0 | PMBKPI2365 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - SWING CHECK VALVES (API) | 56 | 2022-09-14 | 2022-11-09 | 2022-12-22 | 2023-02-16 | 99
0 | PMBKPI2370 | FINAL ACCEPTANCE TEST (FAT) - SWING CHECK VALVES (API) | 7 | 2022-11-09 | 2022-11-16 | 2023-02-16 | 2023-02-23 | 99
0 | PMBKPI2375 | FOB DELIVERY - SWING CHECK VALVES (API) | 14 | 2022-11-16 | 2022-11-30 | 2023-02-23 | 2023-03-09 | 99
0 | PMBKPI2380 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - SWING CHECK VALVES (API) | 30 | 2022-11-30 | 2022-12-30 | 2023-03-09 | 2023-04-08 | 99
0 | PMBKPI2385 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - SWING CHECK VALVES (API) | 30 | 2022-12-20 | 2023-01-19 | 2023-03-29 | 2023-04-28 | 99
DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) |  |  | 198 | 2022-07-05 | 2023-01-19 | 2022-10-12 | 2023-04-28 | 99
0 | PMBKPI3225 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 63 | 2022-07-05 | 2022-09-06 | 2022-10-12 | 2022-12-14 | 99
0 | PMBKPI2390 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 56 | 2022-09-06 | 2022-11-01 | 2022-12-14 | 2023-02-08 | 99
0 | PMBKPI2400 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 64 | 2022-09-06 | 2022-11-09 | 2022-12-14 | 2023-02-16 | 99
0 | PMBKPI2405 | FINAL ACCEPTANCE TEST (FAT) - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 7 | 2022-11-09 | 2022-11-16 | 2023-02-16 | 2023-02-23 | 99
0 | PMBKPI2410 | FOB DELIVERY - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 14 | 2022-11-16 | 2022-11-30 | 2023-02-23 | 2023-03-09 | 99
0 | PMBKPI2415 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 30 | 2022-11-30 | 2022-12-30 | 2023-03-09 | 2023-04-08 | 99
0 | PMBKPI2420 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - DUAL PLATE CHECK VALVES (CS/LTCS/CRA/ CLADDED) | 30 | 2022-12-20 | 2023-01-19 | 2023-03-29 | 2023-04-28 | 99
DUAL PLATE CHECK VALVES (API) |  |  | 194 | 2022-07-06 | 2023-01-16 | 2022-10-16 | 2023-04-28 | 102
0 | PMBKPI3235 | RECEIVE VENDOR DOCUMENTS (CRITICAL)- DUAL PLATE CHECK VALVES (API) | 63 | 2022-07-06 | 2022-09-07 | 2022-10-16 | 2022-12-18 | 102
0 | PMBKPI2425 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - DUAL PLATE CHECK VALVES (API) | 63 | 2022-09-07 | 2022-11-09 | 2022-12-18 | 2023-02-19 | 102
0 | PMBKPI2435 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - DUAL PLATE CHECK VALVES (API) | 65 | 2022-09-07 | 2022-11-11 | 2022-12-18 | 2023-02-21 | 102
0 | PMBKPI2440 | FINAL ACCEPTANCE TEST (FAT) - DUAL PLATE CHECK VALVES (API) | 7 | 2022-11-11 | 2022-11-18 | 2023-02-21 | 2023-02-28 | 102
0 | PMBKPI2445 | FOB DELIVERY - DUAL PLATE CHECK VALVES (API) | 14 | 2022-11-18 | 2022-12-02 | 2023-02-28 | 2023-03-14 | 102
0 | PMBKPI2450 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - DUAL PLATE CHECK VALVES (API) | 30 | 2022-12-02 | 2023-01-01 | 2023-03-14 | 2023-04-13 | 102
0 | PMBKPI2455 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - DUAL PLATE CHECK VALVES (API) | 30 | 2022-12-17 | 2023-01-16 | 2023-03-29 | 2023-04-28 | 102
PIPES CS & LTCS/CRA |  |  | 228 | 2022-05-19 | 2023-01-02 | 2022-10-03 | 2023-04-21 | 109
0 | PMBKPI3135 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIPES CS & LTCS/CRA | 63 | 2022-05-19 | 2022-07-21 | 2022-10-03 | 2022-12-05 | 137
0 | PMBKPI2460 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIPES CS & LTCS/CRA | 42 | 2022-07-21 | 2022-09-01 | 2022-12-12 | 2023-01-23 | 144
0 | PMBKPI2470 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIPES CS & LTCS/CRA | 56 | 2022-07-21 | 2022-09-15 | 2022-12-05 | 2023-01-30 | 137
0 | PMBKPI2475 | FINAL ACCEPTANCE TEST (FAT) - PIPES CS & LTCS/CRA | 7 | 2022-09-15 | 2022-09-22 | 2023-01-30 | 2023-02-06 | 137
0 | PMBKPI2480 | FOB DELIVERY - PIPES CS & LTCS/CRA | 14 | 2022-09-22 | 2022-10-06 | 2023-02-06 | 2023-02-20 | 137
0 | PMBKPI2485 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIPES CS & LTCS/CRA | 30 | 2022-10-06 | 2022-11-05 | 2023-02-20 | 2023-03-22 | 137
0 | PMBKPI2490 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIPES CS & LTCS/CRA | 35 | 2022-11-28 | 2023-01-02 | 2023-03-17 | 2023-04-21 | 109
FORGED FITTINGS CS, LTCS/CRA |  |  | 214 | 2022-05-19 | 2022-12-19 | 2022-09-26 | 2023-04-21 | 123
0 | PMBKPI3165 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - FORGED FITTINGS CS, LTCS/CRA | 63 | 2022-05-19 | 2022-07-21 | 2022-09-26 | 2022-11-28 | 130
0 | PMBKPI2495 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - FORGED FITTINGS CS, LTCS/CRA | 35 | 2022-07-21 | 2022-08-25 | 2022-12-21 | 2023-01-25 | 153
0 | PMBKPI2505 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - FORGED FITTINGS CS, LTCS/CRA | 63 | 2022-07-21 | 2022-09-22 | 2022-11-28 | 2023-01-30 | 130
0 | PMBKPI2510 | FINAL ACCEPTANCE TEST (FAT) - FORGED FITTINGS CS, LTCS/CRA | 7 | 2022-09-22 | 2022-09-29 | 2023-01-30 | 2023-02-06 | 130
0 | PMBKPI2515 | FOB DELIVERY - FORGED FITTINGS CS, LTCS/CRA | 14 | 2022-09-29 | 2022-10-13 | 2023-02-06 | 2023-02-20 | 130
0 | PMBKPI2520 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - FORGED FITTINGS CS, LTCS/CRA | 30 | 2022-10-13 | 2022-11-12 | 2023-02-20 | 2023-03-22 | 130
0 | PMBKPI2525 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - FORGED FITTINGS CS, LTCS/CRA | 42 | 2022-11-07 | 2022-12-19 | 2023-03-10 | 2023-04-21 | 123
BUTT WELD FITTINGS CS, LTCS/CRA |  |  | 214 | 2022-05-19 | 2022-12-19 | 2022-09-19 | 2023-04-21 | 123
0 | PMBKPI3155 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - BUTT WELD FITTINGS CS, LTCS/CRA | 63 | 2022-05-19 | 2022-07-21 | 2022-09-19 | 2022-11-21 | 123
0 | PMBKPI2530 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - BUTT WELD FITTINGS CS, LTCS/CRA | 35 | 2022-07-21 | 2022-08-25 | 2022-12-19 | 2023-01-23 | 151
0 | PMBKPI2540 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - BUTT WELD FITTINGS CS, LTCS/CRA | 70 | 2022-07-21 | 2022-09-29 | 2022-11-21 | 2023-01-30 | 123
0 | PMBKPI2545 | FINAL ACCEPTANCE TEST (FAT) - BUTT WELD FITTINGS CS, LTCS/CRA | 7 | 2022-09-29 | 2022-10-06 | 2023-01-30 | 2023-02-06 | 123
0 | PMBKPI2550 | FOB DELIVERY - BUTT WELD FITTINGS CS, LTCS/CRA | 14 | 2022-10-06 | 2022-10-20 | 2023-02-06 | 2023-02-20 | 123
0 | PMBKPI2555 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - BUTT WELD FITTINGS CS, LTCS/CRA | 30 | 2022-10-20 | 2022-11-19 | 2023-02-20 | 2023-03-22 | 123
0 | PMBKPI2560 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - BUTT WELD FITTINGS CS, LTCS/CRA | 30 | 2022-11-19 | 2022-12-19 | 2023-03-22 | 2023-04-21 | 123
FLANGES CS/ LTCS/CRA & CLADDED |  |  | 213 | 2022-05-20 | 2022-12-19 | 2022-09-26 | 2023-04-21 | 123
0 | PMBKPI3175 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - FLANGES CS/ LTCS/CRA & CLADDED | 63 | 2022-05-20 | 2022-07-22 | 2022-09-26 | 2022-11-28 | 129
0 | PMBKPI2565 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - FLANGES CS/ LTCS/CRA & CLADDED | 35 | 2022-07-22 | 2022-08-26 | 2022-12-19 | 2023-01-23 | 150
0 | PMBKPI2575 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - FLANGES CS/ LTCS/CRA & CLADDED | 63 | 2022-07-22 | 2022-09-23 | 2022-11-28 | 2023-01-30 | 129
0 | PMBKPI2580 | FINAL ACCEPTANCE TEST (FAT) - FLANGES CS/ LTCS/CRA & CLADDED | 7 | 2022-09-23 | 2022-09-30 | 2023-01-30 | 2023-02-06 | 129
0 | PMBKPI2585 | FOB DELIVERY - FLANGES CS/ LTCS/CRA & CLADDED | 14 | 2022-09-30 | 2022-10-14 | 2023-02-06 | 2023-02-20 | 129
0 | PMBKPI2590 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - FLANGES CS/ LTCS/CRA & CLADDED | 30 | 2022-10-14 | 2022-11-13 | 2023-02-20 | 2023-03-22 | 129
0 | PMBKPI2595 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - FLANGES CS/ LTCS/CRA & CLADDED | 30 | 2022-11-19 | 2022-12-19 | 2023-03-22 | 2023-04-21 | 123
PIPES & FITINGS CLADDED SERVICE |  |  | 210 | 2022-05-24 | 2022-12-20 | 2022-10-03 | 2023-04-21 | 122
0 | PMBKPI3145 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIPES & FITINGS CLADDED SERVICE | 56 | 2022-05-24 | 2022-07-19 | 2022-10-03 | 2022-11-28 | 132
0 | PMBKPI2600 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIPES & FITINGS CLADDED SERVICE | 35 | 2022-07-19 | 2022-08-23 | 2022-12-19 | 2023-01-23 | 153
0 | PMBKPI2610 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIPES & FITINGS CLADDED SERVICE | 63 | 2022-07-19 | 2022-09-20 | 2022-11-28 | 2023-01-30 | 132
0 | PMBKPI2615 | FINAL ACCEPTANCE TEST (FAT) - PIPES & FITINGS CLADDED SERVICE | 7 | 2022-09-20 | 2022-09-27 | 2023-01-30 | 2023-02-06 | 132
0 | PMBKPI2620 | FOB DELIVERY - PIPES & FITINGS CLADDED SERVICE | 14 | 2022-09-27 | 2022-10-11 | 2023-02-06 | 2023-02-20 | 132
0 | PMBKPI2625 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIPES & FITINGS CLADDED SERVICE | 30 | 2022-10-11 | 2022-11-10 | 2023-02-20 | 2023-03-22 | 132
0 | PMBKPI2630 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIPES & FITINGS CLADDED SERVICE | 42 | 2022-11-08 | 2022-12-20 | 2023-03-10 | 2023-04-21 | 122
CU-NI PIPE FITTINGS AND FLANGES |  |  | 207 | 2022-06-07 | 2022-12-31 | 2022-10-03 | 2023-04-28 | 118
0 | PMBKPI3195 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - CU-NI PIPE FITTINGS AND FLANGES | 56 | 2022-06-07 | 2022-08-02 | 2022-10-03 | 2022-11-28 | 118
0 | PMBKPI2635 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - CU-NI PIPE FITTINGS AND FLANGES | 42 | 2022-08-02 | 2022-09-13 | 2022-11-28 | 2023-01-09 | 118
0 | PMBKPI2645 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - CU-NI PIPE FITTINGS AND FLANGES | 70 | 2022-08-02 | 2022-10-11 | 2022-11-28 | 2023-02-06 | 118
0 | PMBKPI2650 | FINAL ACCEPTANCE TEST (FAT) - CU-NI PIPE FITTINGS AND FLANGES | 7 | 2022-10-11 | 2022-10-18 | 2023-02-06 | 2023-02-13 | 118
0 | PMBKPI2655 | FOB DELIVERY - CU-NI PIPE FITTINGS AND FLANGES | 14 | 2022-10-18 | 2022-11-01 | 2023-02-13 | 2023-02-27 | 118
0 | PMBKPI2660 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - CU-NI PIPE FITTINGS AND FLANGES | 30 | 2022-11-01 | 2022-12-01 | 2023-02-27 | 2023-03-29 | 118
0 | PMBKPI2665 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - CU-NI PIPE FITTINGS AND FLANGES | 30 | 2022-12-01 | 2022-12-31 | 2023-03-29 | 2023-04-28 | 118
GASKETS |  |  | 165 | 2022-07-26 | 2023-01-07 | 2022-11-14 | 2023-04-28 | 111
0 | PMBKPI3115 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - GASKETS | 35 | 2022-07-26 | 2022-08-30 | 2022-11-14 | 2022-12-19 | 111
0 | PMBKPI2670 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - GASKETS | 21 | 2022-08-30 | 2022-09-20 | 2022-12-19 | 2023-01-09 | 111
0 | PMBKPI2680 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - GASKETS | 56 | 2022-08-30 | 2022-10-25 | 2022-12-19 | 2023-02-13 | 111
0 | PMBKPI2685 | FINAL ACCEPTANCE TEST (FAT) - GASKETS | 7 | 2022-10-25 | 2022-11-01 | 2023-02-13 | 2023-02-20 | 111
0 | PMBKPI2690 | FOB DELIVERY - GASKETS | 7 | 2022-11-01 | 2022-11-08 | 2023-02-20 | 2023-02-27 | 111
0 | PMBKPI2695 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - GASKETS | 30 | 2022-11-08 | 2022-12-08 | 2023-02-27 | 2023-03-29 | 111
0 | PMBKPI2700 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - GASKETS | 30 | 2022-12-08 | 2023-01-07 | 2023-03-29 | 2023-04-28 | 111
BOLTING |  |  | 150 | 2022-07-11 | 2022-12-08 | 2022-11-29 | 2023-04-28 | 141
0 | PMBKPI3125 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - BOLTING | 28 | 2022-07-11 | 2022-08-08 | 2022-11-29 | 2022-12-27 | 141
0 | PMBKPI2705 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - BOLTING | 21 | 2022-08-08 | 2022-08-29 | 2022-12-27 | 2023-01-17 | 141
0 | PMBKPI2715 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - BOLTING | 56 | 2022-08-15 | 2022-10-10 | 2023-01-03 | 2023-02-28 | 141
0 | PMBKPI2720 | FINAL ACCEPTANCE TEST (FAT) - BOLTING | 7 | 2022-10-10 | 2022-10-17 | 2023-02-28 | 2023-03-07 | 141
0 | PMBKPI2725 | FOB DELIVERY - BOLTING | 7 | 2022-10-17 | 2022-10-24 | 2023-03-07 | 2023-03-14 | 141
0 | PMBKPI2730 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - BOLTING | 30 | 2022-10-24 | 2022-11-23 | 2023-03-14 | 2023-04-13 | 141
0 | PMBKPI2735 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - BOLTING | 30 | 2022-11-08 | 2022-12-08 | 2023-03-29 | 2023-04-28 | 141
ACCESS FITTINGS AND CORROSION COUPON |  |  | 164 | 2022-08-03 | 2023-01-14 | 2022-11-15 | 2023-04-28 | 104
0 | PMBKPI2742 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - ACCESS FITTINGS AND CORROSION COUPON | 56 | 2022-08-03 | 2022-09-28 | 2022-11-15 | 2023-01-10 | 104
0 | PMBKPI2740 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - ACCESS FITTINGS AND CORROSION COUPON | 35 | 2022-09-28 | 2022-11-02 | 2023-01-10 | 2023-02-14 | 104
0 | PMBKPI2750 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - ACCESS FITTINGS AND CORROSION COUPON | 49 | 2022-09-28 | 2022-11-16 | 2023-01-10 | 2023-02-28 | 104
0 | PMBKPI2755 | FINAL ACCEPTANCE TEST (FAT) - ACCESS FITTINGS AND CORROSION COUPON | 7 | 2022-11-16 | 2022-11-23 | 2023-02-28 | 2023-03-07 | 104
0 | PMBKPI2760 | FOB DELIVERY - ACCESS FITTINGS AND CORROSION COUPON | 7 | 2022-11-23 | 2022-11-30 | 2023-03-07 | 2023-03-14 | 104
0 | PMBKPI2765 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - ACCESS FITTINGS AND CORROSION COUPON | 30 | 2022-11-30 | 2022-12-30 | 2023-03-14 | 2023-04-13 | 104
0 | PMBKPI2770 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - ACCESS FITTINGS AND CORROSION COUPON | 30 | 2022-12-15 | 2023-01-14 | 2023-03-29 | 2023-04-28 | 104
BIRD SCREEN |  |  | 151 | 2022-08-10 | 2023-01-08 | 2022-11-28 | 2023-04-28 | 110
0 | PMBKPI2777 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - BIRD SCREEN | 42 | 2022-08-10 | 2022-09-21 | 2022-11-28 | 2023-01-09 | 110
0 | PMBKPI2775 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - BIRD SCREEN | 28 | 2022-09-21 | 2022-10-19 | 2023-01-09 | 2023-02-06 | 110
0 | PMBKPI2785 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - BIRD SCREEN | 35 | 2022-09-21 | 2022-10-26 | 2023-01-09 | 2023-02-13 | 110
0 | PMBKPI2790 | FINAL ACCEPTANCE TEST (FAT) - BIRD SCREEN | 7 | 2022-10-26 | 2022-11-02 | 2023-02-13 | 2023-02-20 | 110
0 | PMBKPI2795 | FOB DELIVERY - BIRD SCREEN | 7 | 2022-11-02 | 2022-11-09 | 2023-02-20 | 2023-02-27 | 110
0 | PMBKPI2800 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - BIRD SCREEN | 30 | 2022-11-09 | 2022-12-09 | 2023-02-27 | 2023-03-29 | 110
0 | PMBKPI2805 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - BIRD SCREEN | 30 | 2022-12-09 | 2023-01-08 | 2023-03-29 | 2023-04-28 | 110
FLEXIBLE HOSE AND COUPLING |  |  | 121 | 2022-09-16 | 2023-01-15 | 2022-12-28 | 2023-04-28 | 103
0 | PMBKPI3095 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - FLEXIBLE HOSE AND COUPLING | 42 | 2022-09-16 | 2022-10-28 | 2022-12-28 | 2023-02-08 | 103
0 | PMBKPI2810 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - FLEXIBLE HOSE AND COUPLING | 28 | 2022-10-28 | 2022-11-25 | 2023-02-08 | 2023-03-08 | 103
0 | PMBKPI2820 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - FLEXIBLE HOSE AND COUPLING | 35 | 2022-10-28 | 2022-12-02 | 2023-02-08 | 2023-03-15 | 103
0 | PMBKPI2825 | FINAL ACCEPTANCE TEST (FAT) - FLEXIBLE HOSE AND COUPLING | 7 | 2022-12-02 | 2022-12-09 | 2023-03-15 | 2023-03-22 | 103
0 | PMBKPI2830 | FOB DELIVERY - FLEXIBLE HOSE AND COUPLING | 7 | 2022-12-09 | 2022-12-16 | 2023-03-22 | 2023-03-29 | 103
0 | PMBKPI2835 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - FLEXIBLE HOSE AND COUPLING | 30 | 2022-12-16 | 2023-01-15 | 2023-03-29 | 2023-04-28 | 103
0 | PMBKPI2840 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - FLEXIBLE HOSE AND COUPLING | 30 | 2022-12-16 | 2023-01-15 | 2023-03-29 | 2023-04-28 | 103
FIRE WATER SPRAY NOZZLE |  |  | 157 | 2022-08-02 | 2023-01-06 | 2022-11-22 | 2023-04-28 | 112
0 | PMBKPI2843 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - FIRE WATER SPRAY NOZZLE | 56 | 2022-08-02 | 2022-09-27 | 2022-11-22 | 2023-01-17 | 112
0 | PMBKPI2845 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - FIRE WATER SPRAY NOZZLE | 35 | 2022-09-27 | 2022-11-01 | 2023-01-17 | 2023-02-21 | 112
0 | PMBKPI2855 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - FIRE WATER SPRAY NOZZLE | 42 | 2022-09-27 | 2022-11-08 | 2023-01-17 | 2023-02-28 | 112
0 | PMBKPI2860 | FINAL ACCEPTANCE TEST (FAT) - FIRE WATER SPRAY NOZZLE | 7 | 2022-11-08 | 2022-11-15 | 2023-02-28 | 2023-03-07 | 112
0 | PMBKPI2865 | FOB DELIVERY - FIRE WATER SPRAY NOZZLE | 7 | 2022-11-15 | 2022-11-22 | 2023-03-07 | 2023-03-14 | 112
0 | PMBKPI2870 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - FIRE WATER SPRAY NOZZLE | 30 | 2022-11-22 | 2022-12-22 | 2023-03-14 | 2023-04-13 | 112
0 | PMBKPI2875 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - FIRE WATER SPRAY NOZZLE | 30 | 2022-12-07 | 2023-01-06 | 2023-03-29 | 2023-04-28 | 112
INSULATING GASKET |  |  | 165 | 2022-07-28 | 2023-01-09 | 2022-11-15 | 2023-04-28 | 109
0 | PMBKPI2882 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - INSULATING GASKET | 56 | 2022-07-28 | 2022-09-22 | 2022-11-15 | 2023-01-10 | 110
0 | PMBKPI2880 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - INSULATING GASKET | 35 | 2022-09-22 | 2022-10-27 | 2023-01-24 | 2023-02-28 | 124
0 | PMBKPI2890 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - INSULATING GASKET | 49 | 2022-09-22 | 2022-11-10 | 2023-01-10 | 2023-02-28 | 110
0 | PMBKPI2895 | FINAL ACCEPTANCE TEST (FAT) - INSULATING GASKET | 7 | 2022-11-10 | 2022-11-17 | 2023-02-28 | 2023-03-07 | 110
0 | PMBKPI2900 | FOB DELIVERY - INSULATING GASKET | 7 | 2022-11-17 | 2022-11-24 | 2023-03-07 | 2023-03-14 | 110
0 | PMBKPI2905 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - INSULATING GASKET | 30 | 2022-11-24 | 2022-12-24 | 2023-03-14 | 2023-04-13 | 110
0 | PMBKPI2910 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - INSULATING GASKET | 30 | 2022-12-10 | 2023-01-09 | 2023-03-29 | 2023-04-28 | 109
SIGHT GLASS |  |  | 124 | 2022-09-15 | 2023-01-17 | 2022-12-25 | 2023-04-28 | 101
0 | PMBKPI3105 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - SIGHT GLASS | 42 | 2022-09-15 | 2022-10-27 | 2022-12-25 | 2023-02-05 | 101
0 | PMBKPI2915 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - SIGHT GLASS | 21 | 2022-10-27 | 2022-11-17 | 2023-02-05 | 2023-02-26 | 101
0 | PMBKPI2925 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - SIGHT GLASS | 28 | 2022-10-27 | 2022-11-24 | 2023-02-05 | 2023-03-05 | 101
0 | PMBKPI2930 | FINAL ACCEPTANCE TEST (FAT) - SIGHT GLASS | 7 | 2022-11-24 | 2022-12-01 | 2023-03-05 | 2023-03-12 | 101
0 | PMBKPI2935 | FOB DELIVERY - SIGHT GLASS | 7 | 2022-12-01 | 2022-12-08 | 2023-03-12 | 2023-03-19 | 101
0 | PMBKPI2940 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - SIGHT GLASS | 30 | 2022-12-08 | 2023-01-07 | 2023-03-19 | 2023-04-18 | 101
0 | PMBKPI2945 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - SIGHT GLASS | 30 | 2022-12-18 | 2023-01-17 | 2023-03-29 | 2023-04-28 | 101
STRAINER |  |  | 161 | 2022-08-08 | 2023-01-16 | 2022-11-18 | 2023-04-28 | 102
0 | PMBKPI2952 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - STRAINER | 56 | 2022-08-08 | 2022-10-03 | 2022-11-18 | 2023-01-13 | 102
0 | PMBKPI2950 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - STRAINER | 28 | 2022-10-03 | 2022-10-31 | 2023-01-13 | 2023-02-10 | 102
0 | PMBKPI2960 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - STRAINER | 34 | 2022-10-03 | 2022-11-06 | 2023-01-13 | 2023-02-16 | 102
0 | PMBKPI2965 | FINAL ACCEPTANCE TEST (FAT) - STRAINER | 7 | 2022-11-06 | 2022-11-13 | 2023-02-16 | 2023-02-23 | 102
0 | PMBKPI2970 | FOB DELIVERY - STRAINER | 14 | 2022-11-13 | 2022-11-27 | 2023-02-23 | 2023-03-09 | 102
0 | PMBKPI2975 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - STRAINER | 30 | 2022-11-27 | 2022-12-27 | 2023-03-09 | 2023-04-08 | 102
0 | PMBKPI2980 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - STRAINER | 30 | 2022-12-17 | 2023-01-16 | 2023-03-29 | 2023-04-28 | 102
VALVE INTERLOCK |  |  | 157 | 2022-08-10 | 2023-01-14 | 2022-11-22 | 2023-04-28 | 104
0 | PMBKPI2987 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - VALVE INTERLOCK | 56 | 2022-08-10 | 2022-10-05 | 2022-11-22 | 2023-01-17 | 104
0 | PMBKPI2985 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - VALVE INTERLOCK | 28 | 2022-10-05 | 2022-11-02 | 2023-01-17 | 2023-02-14 | 104
0 | PMBKPI2995 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - VALVE INTERLOCK | 35 | 2022-10-05 | 2022-11-09 | 2023-01-17 | 2023-02-21 | 104
0 | PMBKPI3000 | FINAL ACCEPTANCE TEST (FAT) - VALVE INTERLOCK | 7 | 2022-11-09 | 2022-11-16 | 2023-02-21 | 2023-02-28 | 104
0 | PMBKPI3005 | FOB DELIVERY - VALVE INTERLOCK | 14 | 2022-11-16 | 2022-11-30 | 2023-02-28 | 2023-03-14 | 104
0 | PMBKPI3010 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - VALVE INTERLOCK | 30 | 2022-11-30 | 2022-12-30 | 2023-03-14 | 2023-04-13 | 104
0 | PMBKPI3015 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - VALVE INTERLOCK | 30 | 2022-12-15 | 2023-01-14 | 2023-03-29 | 2023-04-28 | 104
PIPE SUPPORT MATERIAL |  |  | 141 | 2022-07-28 | 2022-12-16 | 2022-11-16 | 2023-04-06 | 111
0 | PMBKPI3185 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIPE SUPPORT MATERIALS | 35 | 2022-07-28 | 2022-09-01 | 2022-11-16 | 2022-12-21 | 111
0 | PMBKPI3020 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIPE SUPPORT MATERIALS | 14 | 2022-09-01 | 2022-09-15 | 2022-12-28 | 2023-01-11 | 118
0 | PMBKPI3030 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIPE SUPPORT MATERIALS | 42 | 2022-09-01 | 2022-10-13 | 2022-12-21 | 2023-02-01 | 111
0 | PMBKPI3035 | FINAL ACCEPTANCE TEST (FAT) - PIPE SUPPORT MATERIALS | 7 | 2022-10-13 | 2022-10-20 | 2023-02-01 | 2023-02-08 | 111
0 | PMBKPI3040 | FOB DELIVERY - PIPE SUPPORT MATERIALS | 7 | 2022-10-20 | 2022-10-27 | 2023-02-08 | 2023-02-15 | 111
0 | PMBKPI3045 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIPE SUPPORT MATERIALS | 30 | 2022-10-27 | 2022-11-26 | 2023-02-15 | 2023-03-17 | 111
0 | PMBKPI3050 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIPE SUPPORT MATERIALS | 30 | 2022-11-16 | 2022-12-16 | 2023-03-07 | 2023-04-06 | 111
INSTRUMENTATION |  |  | 324 | 2022-06-20 | 2023-05-10 | 2022-10-09 | 2023-09-23 | 136
PRESSURE GAUGES |  |  | 254 | 2022-07-25 | 2023-04-05 | 2022-12-27 | 2023-08-24 | 141
0 | PMBKIN2001 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PRESSURE GAUGES | 63 | 2022-07-25 | 2022-09-26 | 2022-12-27 | 2023-02-28 | 155
0 | PMBKIN2000 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PRESSURE GAUGES | 63 | 2022-09-26 | 2022-11-28 | 2023-02-28 | 2023-05-02 | 155
0 | PMBKIN2010 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PRESSURE GAUGES | 85 | 2022-10-02 | 2022-12-26 | 2023-03-06 | 2023-05-30 | 155
0 | PMBKIN2015 | FINAL ACCEPTANCE TEST (FAT) - PRESSURE GAUGES | 7 | 2022-12-26 | 2023-01-02 | 2023-05-30 | 2023-06-06 | 155
0 | PMBKIN2020 | FOB DELIVERY - PRESSURE GAUGES | 14 | 2023-01-02 | 2023-01-16 | 2023-06-06 | 2023-06-20 | 155
0 | PMBKIN2025 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PRESSURE GAUGES | 30 | 2023-01-16 | 2023-02-15 | 2023-06-20 | 2023-07-20 | 155
0 | PMBKIN2030 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PRESSURE GAUGES | 30 | 2023-03-06 | 2023-04-05 | 2023-07-25 | 2023-08-24 | 141
TEMPERATURE GAUGES |  |  | 254 | 2022-08-23 | 2023-05-04 | 2022-12-10 | 2023-08-21 | 109
0 | PMBKIN2037 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - TEMPERATURE GAUGES | 63 | 2022-08-23 | 2022-10-25 | 2022-12-10 | 2023-02-11 | 109
0 | PMBKIN2035 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - TEMPERATURE GAUGES | 56 | 2022-10-25 | 2022-12-20 | 2023-02-11 | 2023-04-08 | 109
0 | PMBKIN2045 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - TEMPERATURE GAUGES | 65 | 2022-10-25 | 2022-12-29 | 2023-02-11 | 2023-04-17 | 109
0 | PMBKIN2050 | FINAL ACCEPTANCE TEST (FAT) - TEMPERATURE GAUGES | 7 | 2022-12-29 | 2023-01-05 | 2023-04-17 | 2023-04-24 | 109
0 | PMBKIN2055 | FOB DELIVERY - TEMPERATURE GAUGES | 14 | 2023-01-05 | 2023-01-19 | 2023-04-24 | 2023-05-08 | 109
0 | PMBKIN2060 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - TEMPERATURE GAUGES | 30 | 2023-01-19 | 2023-02-18 | 2023-05-08 | 2023-06-07 | 109
0 | PMBKIN2065 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - TEMPERATURE GAUGES | 42 | 2023-03-23 | 2023-05-04 | 2023-07-10 | 2023-08-21 | 109
TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) |  |  | 253 | 2022-07-19 | 2023-03-29 | 2022-12-20 | 2023-08-21 | 145
0 | PMBKIN2072 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) | 63 | 2022-07-19 | 2022-09-20 | 2022-12-20 | 2023-02-21 | 154
0 | PMBKIN2070 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) | 63 | 2022-09-20 | 2022-11-22 | 2023-02-21 | 2023-04-25 | 154
0 | PMBKIN2080 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) | 90 | 2022-09-28 | 2022-12-27 | 2023-03-01 | 2023-05-30 | 154
0 | PMBKIN2085 | FINAL ACCEPTANCE TEST (FAT) - TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) | 7 | 2022-12-27 | 2023-01-03 | 2023-05-30 | 2023-06-06 | 154
0 | PMBKIN2090 | FOB DELIVERY - TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) | 14 | 2023-01-03 | 2023-01-17 | 2023-06-06 | 2023-06-20 | 154
0 | PMBKIN2095 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) | 30 | 2023-01-17 | 2023-02-16 | 2023-06-20 | 2023-07-20 | 154
0 | PMBKIN2100 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - TRANSMITTERS (PT, PDT, TT, FT-DP TYPE) | 42 | 2023-02-15 | 2023-03-29 | 2023-07-10 | 2023-08-21 | 145
PIG SIGNALLER |  |  | 212 | 2022-09-06 | 2023-04-06 | 2023-01-27 | 2023-08-21 | 137
0 | PMBKIN2106 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIG SIGNALLER | 63 | 2022-09-06 | 2022-11-08 | 2023-01-27 | 2023-03-31 | 143
0 | PMBKIN2105 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIG SIGNALLER | 42 | 2022-11-08 | 2022-12-20 | 2023-03-31 | 2023-05-12 | 143
0 | PMBKIN2115 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIG SIGNALLER | 50 | 2022-11-08 | 2022-12-28 | 2023-03-31 | 2023-05-20 | 143
0 | PMBKIN2120 | FINAL ACCEPTANCE TEST (FAT) - PIG SIGNALLER | 7 | 2022-12-28 | 2023-01-04 | 2023-05-20 | 2023-05-27 | 143
0 | PMBKIN2125 | FOB DELIVERY - PIG SIGNALLER | 14 | 2023-01-04 | 2023-01-18 | 2023-05-27 | 2023-06-10 | 143
0 | PMBKIN2130 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIG SIGNALLER | 30 | 2023-01-18 | 2023-02-17 | 2023-06-10 | 2023-07-10 | 143
0 | PMBKIN2135 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIG SIGNALLER | 42 | 2023-02-23 | 2023-04-06 | 2023-07-10 | 2023-08-21 | 137
THERMAL FLOW SWITCH |  |  | 198 | 2022-09-06 | 2023-03-23 | 2023-02-09 | 2023-08-21 | 151
0 | PMBKIN2142 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - THERMAL FLOW SWITCH | 63 | 2022-09-06 | 2022-11-08 | 2023-02-09 | 2023-04-13 | 156
0 | PMBKIN2140 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - THERMAL FLOW SWITCH | 49 | 2022-11-08 | 2022-12-27 | 2023-04-13 | 2023-06-01 | 156
0 | PMBKIN2150 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - THERMAL FLOW SWITCH | 42 | 2022-11-15 | 2022-12-27 | 2023-04-20 | 2023-06-01 | 156
0 | PMBKIN2155 | FINAL ACCEPTANCE TEST (FAT) - THERMAL FLOW SWITCH | 7 | 2022-12-27 | 2023-01-03 | 2023-06-01 | 2023-06-08 | 156
0 | PMBKIN2160 | FOB DELIVERY - THERMAL FLOW SWITCH | 14 | 2023-01-03 | 2023-01-17 | 2023-06-08 | 2023-06-22 | 156
0 | PMBKIN2165 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - THERMAL FLOW SWITCH | 30 | 2023-01-17 | 2023-02-16 | 2023-06-22 | 2023-07-22 | 156
0 | PMBKIN2170 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - THERMAL FLOW SWITCH | 30 | 2023-02-21 | 2023-03-23 | 2023-07-22 | 2023-08-21 | 151
GWR & RADAR TYPE LEVEL TRANSMITTER |  |  | 254 | 2022-07-18 | 2023-03-29 | 2022-12-22 | 2023-08-21 | 145
0 | PMBKIN2177 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - GWR & RADAR TYPE LEVEL TRANSMITTER | 63 | 2022-07-18 | 2022-09-19 | 2022-12-22 | 2023-02-23 | 157
0 | PMBKIN2175 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - GWR & RADAR TYPE LEVEL TRANSMITTER | 63 | 2022-09-19 | 2022-11-21 | 2023-02-23 | 2023-04-27 | 157
0 | PMBKIN2185 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - GWR & RADAR TYPE LEVEL TRANSMITTER | 98 | 2022-09-19 | 2022-12-26 | 2023-02-23 | 2023-06-01 | 157
0 | PMBKIN2190 | FINAL ACCEPTANCE TEST (FAT) - GWR & RADAR TYPE LEVEL TRANSMITTER | 7 | 2022-12-26 | 2023-01-02 | 2023-06-01 | 2023-06-08 | 157
0 | PMBKIN2195 | FOB DELIVERY - GWR & RADAR TYPE LEVEL TRANSMITTER | 14 | 2023-01-02 | 2023-01-16 | 2023-06-08 | 2023-06-22 | 157
0 | PMBKIN2200 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - GWR & RADAR TYPE LEVEL TRANSMITTER | 30 | 2023-01-16 | 2023-02-15 | 2023-06-22 | 2023-07-22 | 157
0 | PMBKIN2205 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - GWR & RADAR TYPE LEVEL TRANSMITTER | 42 | 2023-02-15 | 2023-03-29 | 2023-07-10 | 2023-08-21 | 145
MAGNETIC LEVEL GAUGE |  |  | 256 | 2022-07-15 | 2023-03-28 | 2022-12-22 | 2023-08-21 | 146
0 | PMBKIN2217 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - MAGNETIC LEVEL GAUGE | 63 | 2022-07-15 | 2022-09-16 | 2022-12-22 | 2023-02-23 | 160
0 | PMBKIN2210 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - MAGNETIC LEVEL GAUGE | 63 | 2022-09-16 | 2022-11-18 | 2023-02-23 | 2023-04-27 | 160
0 | PMBKIN2220 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - MAGNETIC LEVEL GAUGE | 98 | 2022-09-16 | 2022-12-23 | 2023-02-23 | 2023-06-01 | 160
0 | PMBKIN2225 | FINAL ACCEPTANCE TEST (FAT) - MAGNETIC LEVEL GAUGE | 7 | 2022-12-23 | 2022-12-30 | 2023-06-01 | 2023-06-08 | 160
0 | PMBKIN2230 | FOB DELIVERY - MAGNETIC LEVEL GAUGE | 14 | 2022-12-30 | 2023-01-13 | 2023-06-08 | 2023-06-22 | 160
0 | PMBKIN2235 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - MAGNETIC LEVEL GAUGE | 30 | 2023-01-13 | 2023-02-12 | 2023-06-22 | 2023-07-22 | 160
0 | PMBKIN2240 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - MAGNETIC LEVEL GAUGE | 42 | 2023-02-14 | 2023-03-28 | 2023-07-10 | 2023-08-21 | 146
FLOW RESTRICTION ORIFICE |  |  | 225 | 2022-07-27 | 2023-03-09 | 2022-11-24 | 2023-08-21 | 165
0 | PMBKIN2247 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - FLOW RESTRICTION ORIFICE | 63 | 2022-07-27 | 2022-09-28 | 2022-11-24 | 2023-01-26 | 120
0 | PMBKIN2245 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - FLOW RESTRICTION ORIFICE | 63 | 2022-09-28 | 2022-11-30 | 2023-01-26 | 2023-03-30 | 120
0 | PMBKIN2255 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - FLOW RESTRICTION ORIFICE | 80 | 2022-09-29 | 2022-12-18 | 2023-01-27 | 2023-04-17 | 120
0 | PMBKIN2260 | FINAL ACCEPTANCE TEST (FAT) - FLOW RESTRICTION ORIFICE | 7 | 2022-12-18 | 2022-12-25 | 2023-04-17 | 2023-04-24 | 120
0 | PMBKIN2265 | FOB DELIVERY - FLOW RESTRICTION ORIFICE | 14 | 2022-12-25 | 2023-01-08 | 2023-04-24 | 2023-05-08 | 120
0 | PMBKIN2270 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - FLOW RESTRICTION ORIFICE | 30 | 2023-01-08 | 2023-02-07 | 2023-05-08 | 2023-06-07 | 120
0 | PMBKIN2275 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - FLOW RESTRICTION ORIFICE | 30 | 2023-02-07 | 2023-03-09 | 2023-07-22 | 2023-08-21 | 165
ULTRASONIC FLOW METER |  |  | 275 | 2022-06-20 | 2023-03-22 | 2022-10-09 | 2023-08-21 | 152
0 | PMBKIN2281 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - ULTRASONIC FLOW METER | 63 | 2022-06-20 | 2022-08-22 | 2022-10-09 | 2022-12-11 | 111
0 | PMBKIN2280 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - ULTRASONIC FLOW METER | 63 | 2022-08-22 | 2022-10-24 | 2022-12-28 | 2023-03-01 | 128
0 | PMBKIN2290 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - ULTRASONIC FLOW METER | 115 | 2022-08-22 | 2022-12-15 | 2022-12-11 | 2023-04-05 | 111
0 | PMBKIN2295 | FINAL ACCEPTANCE TEST (FAT) - ULTRASONIC FLOW METER | 7 | 2022-12-15 | 2022-12-22 | 2023-04-05 | 2023-04-12 | 111
0 | PMBKIN2300 | FOB DELIVERY - ULTRASONIC FLOW METER | 14 | 2022-12-22 | 2023-01-05 | 2023-04-12 | 2023-04-26 | 111
0 | PMBKIN2305 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - ULTRASONIC FLOW METER | 42 | 2023-01-05 | 2023-02-16 | 2023-04-26 | 2023-06-07 | 111
0 | PMBKIN2310 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - ULTRASONIC FLOW METER | 42 | 2023-02-08 | 2023-03-22 | 2023-07-10 | 2023-08-21 | 152
FIRE & GAS DETECTORS / DEVICES |  |  | 207 | 2022-08-19 | 2023-03-14 | 2023-01-18 | 2023-08-21 | 160
0 | PMBKIN2318 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - FIRE & GAS DETECTORS / DEVICES | 63 | 2022-08-19 | 2022-10-21 | 2023-01-18 | 2023-03-22 | 152
0 | PMBKIN2315 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - FIRE & GAS DETECTORS / DEVICES | 56 | 2022-10-21 | 2022-12-16 | 2023-03-22 | 2023-05-17 | 152
0 | PMBKIN2325 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - FIRE & GAS DETECTORS / DEVICES | 63 | 2022-10-21 | 2022-12-23 | 2023-03-22 | 2023-05-24 | 152
0 | PMBKIN2330 | FINAL ACCEPTANCE TEST (FAT) - FIRE & GAS DETECTORS / DEVICES | 7 | 2022-12-23 | 2022-12-30 | 2023-05-24 | 2023-05-31 | 152
0 | PMBKIN2335 | FOB DELIVERY - FIRE & GAS DETECTORS / DEVICES | 14 | 2022-12-30 | 2023-01-13 | 2023-05-31 | 2023-06-14 | 152
0 | PMBKIN2340 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - FIRE & GAS DETECTORS / DEVICES | 30 | 2023-01-13 | 2023-02-12 | 2023-06-14 | 2023-07-14 | 152
0 | PMBKIN2345 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - FIRE & GAS DETECTORS / DEVICES | 42 | 2023-01-31 | 2023-03-14 | 2023-07-10 | 2023-08-21 | 160
PRESSURE RELIEF VALVES |  |  | 254 | 2022-07-20 | 2023-03-31 | 2022-12-18 | 2023-08-21 | 143
0 | PMBKIN2352 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PRESSURE RELIEF VALVES | 63 | 2022-07-20 | 2022-09-21 | 2022-12-18 | 2023-02-19 | 151
0 | PMBKIN2350 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PRESSURE RELIEF VALVES | 63 | 2022-09-21 | 2022-11-23 | 2023-02-19 | 2023-04-23 | 151
0 | PMBKIN2360 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PRESSURE RELIEF VALVES | 90 | 2022-09-21 | 2022-12-20 | 2023-02-19 | 2023-05-20 | 151
0 | PMBKIN2365 | FINAL ACCEPTANCE TEST (FAT) - PRESSURE RELIEF VALVES | 7 | 2022-12-20 | 2022-12-27 | 2023-05-20 | 2023-05-27 | 151
0 | PMBKIN2370 | FOB DELIVERY - PRESSURE RELIEF VALVES | 14 | 2022-12-27 | 2023-01-10 | 2023-05-27 | 2023-06-10 | 151
0 | PMBKIN2375 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PRESSURE RELIEF VALVES | 40 | 2023-01-10 | 2023-02-19 | 2023-06-10 | 2023-07-20 | 151
0 | PMBKIN2380 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PRESSURE RELIEF VALVES | 42 | 2023-02-17 | 2023-03-31 | 2023-07-10 | 2023-08-21 | 143
CORROSION MONITORING DEVICES |  |  | 233 | 2022-08-05 | 2023-03-26 | 2022-12-31 | 2023-08-21 | 148
0 | PMBKIN2422 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - CORROSION MONITORING DEVICES | 63 | 2022-08-05 | 2022-10-07 | 2022-12-31 | 2023-03-04 | 148
0 | PMBKIN2420 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - CORROSION MONITORING DEVICES | 42 | 2022-10-07 | 2022-11-18 | 2023-03-04 | 2023-04-15 | 148
0 | PMBKIN2430 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - CORROSION MONITORING DEVICES | 84 | 2022-10-07 | 2022-12-30 | 2023-03-04 | 2023-05-27 | 148
0 | PMBKIN2435 | FINAL ACCEPTANCE TEST (FAT) - CORROSION MONITORING DEVICES | 7 | 2022-12-30 | 2023-01-06 | 2023-05-27 | 2023-06-03 | 148
0 | PMBKIN2440 | FOB DELIVERY - CORROSION MONITORING DEVICES | 7 | 2023-01-06 | 2023-01-13 | 2023-06-03 | 2023-06-10 | 148
0 | PMBKIN2445 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - CORROSION MONITORING DEVICES | 42 | 2023-01-13 | 2023-02-24 | 2023-06-10 | 2023-07-22 | 148
0 | PMBKIN2450 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - CORROSION MONITORING DEVICES | 42 | 2023-02-12 | 2023-03-26 | 2023-07-10 | 2023-08-21 | 148
INSTRUMENT CABLE GLANDS |  |  | 193 | 2022-09-19 | 2023-03-31 | 2023-02-12 | 2023-08-24 | 146
0 | PMBKIN2457 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - INSTRUMENT CABLE GLANDS | 42 | 2022-09-19 | 2022-10-31 | 2023-02-12 | 2023-03-26 | 146
0 | PMBKIN2455 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - INSTRUMENT CABLE GLANDS | 35 | 2022-10-31 | 2022-12-05 | 2023-03-26 | 2023-04-30 | 146
0 | PMBKIN2465 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - INSTRUMENT CABLE GLANDS | 70 | 2022-10-31 | 2023-01-09 | 2023-03-26 | 2023-06-04 | 146
0 | PMBKIN2470 | FINAL ACCEPTANCE TEST (FAT) - INSTRUMENT CABLE GLANDS | 7 | 2023-01-09 | 2023-01-16 | 2023-06-04 | 2023-06-11 | 146
0 | PMBKIN2475 | FOB DELIVERY - INSTRUMENT CABLE GLANDS | 14 | 2023-01-16 | 2023-01-30 | 2023-06-11 | 2023-06-25 | 146
0 | PMBKIN2480 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - INSTRUMENT CABLE GLANDS | 30 | 2023-01-30 | 2023-03-01 | 2023-06-25 | 2023-07-25 | 146
0 | PMBKIN2485 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - INSTRUMENT CABLE GLANDS | 30 | 2023-03-01 | 2023-03-31 | 2023-07-25 | 2023-08-24 | 146
INSTRUMENT & FO AND CONTROL AND TELECOMMUNICATION CABLES |  |  | 214 | 2022-09-15 | 2023-04-17 | 2023-01-05 | 2023-08-07 | 112
0 | PMBKIN2492 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - INSTRUMENT & FO AND CONTROL AND TELECOMMUNICATION CABLES | 56 | 2022-09-15 | 2022-11-10 | 2023-01-05 | 2023-03-02 | 112
0 | PMBKIN2490 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - INSTRUMENT & FO AND CONTROL AND TELECOMMUNICATION CABLES | 35 | 2022-11-10 | 2022-12-15 | 2023-04-02 | 2023-05-07 | 143
0 | PMBKIN2500 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - INSTRUMENT & FO AND CONTROL AND TELECOMMUNICATION CABLES | 84 | 2022-11-10 | 2023-02-02 | 2023-03-02 | 2023-05-25 | 112
0 | PMBKIN2505 | FINAL ACCEPTANCE TEST (FAT) - INSTRUMENT & FO AND CONTROL AND TELECOMMUNICATION CABLES | 7 | 2023-02-02 | 2023-02-09 | 2023-05-25 | 2023-06-01 | 112
0 | PMBKIN2510 | FOB DELIVERY - INSTRUMENT & FO AND CONTROL AND TELECOMMUNICATION CABLES | 7 | 2023-02-09 | 2023-02-16 | 2023-06-01 | 2023-06-08 | 112
0 | PMBKIN2515 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - INSTRUMENT & FO AND CONTROL AND TELECOMMUNICATION CABLES | 30 | 2023-02-16 | 2023-03-18 | 2023-06-08 | 2023-07-08 | 112
0 | PMBKIN2520 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - INSTRUMENT & FO AND CONTROL AND TELECOMMUNICATION CABLES | 30 | 2023-03-18 | 2023-04-17 | 2023-07-08 | 2023-08-07 | 112
INSTRUMENT BULK MATERIAL |  |  | 214 | 2022-08-29 | 2023-03-31 | 2023-01-05 | 2023-08-07 | 129
0 | PMBKIN2561 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - INSTRUMENT BULK MATERIAL | 63 | 2022-08-29 | 2022-10-31 | 2023-01-05 | 2023-03-09 | 129
0 | PMBKIN2560 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - INSTRUMENT BULK MATERIAL | 42 | 2022-10-31 | 2022-12-12 | 2023-03-09 | 2023-04-20 | 129
0 | PMBKIN2570 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - INSTRUMENT BULK MATERIAL | 70 | 2022-10-31 | 2023-01-09 | 2023-03-09 | 2023-05-18 | 129
0 | PMBKIN2575 | FINAL ACCEPTANCE TEST (FAT) - INSTRUMENT BULK MATERIAL | 7 | 2023-01-09 | 2023-01-16 | 2023-05-18 | 2023-05-25 | 129
0 | PMBKIN2580 | FOB DELIVERY - INSTRUMENT BULK MATERIAL | 14 | 2023-01-16 | 2023-01-30 | 2023-05-25 | 2023-06-08 | 129
0 | PMBKIN2585 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - INSTRUMENT BULK MATERIAL | 30 | 2023-01-30 | 2023-03-01 | 2023-06-08 | 2023-07-08 | 129
0 | PMBKIN2590 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - INSTRUMENT BULK MATERIAL | 30 | 2023-03-01 | 2023-03-31 | 2023-07-08 | 2023-08-07 | 129
INSTRUMENT SUN SHADES |  |  | 219 | 2022-09-05 | 2023-04-12 | 2023-02-09 | 2023-08-21 | 131
0 | PMBKIN2597 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - INSTRUMENT SUN SHADES | 56 | 2022-09-05 | 2022-10-31 | 2023-02-09 | 2023-04-06 | 157
0 | PMBKIN2595 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - INSTRUMENT SUN SHADES | 42 | 2022-10-31 | 2022-12-12 | 2023-04-06 | 2023-05-18 | 157
0 | PMBKIN2605 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - INSTRUMENT SUN SHADES | 56 | 2022-10-31 | 2022-12-26 | 2023-04-06 | 2023-06-01 | 157
0 | PMBKIN2610 | FINAL ACCEPTANCE TEST (FAT) - INSTRUMENT SUN SHADES | 7 | 2022-12-26 | 2023-01-02 | 2023-06-01 | 2023-06-08 | 157
0 | PMBKIN2615 | FOB DELIVERY - INSTRUMENT SUN SHADES | 14 | 2023-01-02 | 2023-01-16 | 2023-06-08 | 2023-06-22 | 157
0 | PMBKIN2620 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - INSTRUMENT SUN SHADES | 30 | 2023-01-16 | 2023-02-15 | 2023-06-22 | 2023-07-22 | 157
0 | PMBKIN2625 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - INSTRUMENT SUN SHADES | 42 | 2023-03-01 | 2023-04-12 | 2023-07-10 | 2023-08-21 | 131
JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM |  |  | 246 | 2022-09-06 | 2023-05-10 | 2022-12-23 | 2023-09-23 | 136
0 | PMBKIN2667 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM | 63 | 2022-09-06 | 2022-11-08 | 2022-12-23 | 2023-02-24 | 108
0 | PMBKIN2665 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM | 56 | 2022-11-08 | 2023-01-03 | 2023-03-02 | 2023-04-27 | 114
0 | PMBKIN2675 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM | 90 | 2022-11-08 | 2023-02-06 | 2023-02-24 | 2023-05-25 | 108
0 | PMBKIN2680 | FINAL ACCEPTANCE TEST (FAT) - JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM | 7 | 2023-02-06 | 2023-02-13 | 2023-05-25 | 2023-06-01 | 108
0 | PMBKIN2685 | FOB DELIVERY - JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM | 14 | 2023-02-13 | 2023-02-27 | 2023-06-01 | 2023-06-15 | 108
0 | PMBKIN2690 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM | 42 | 2023-02-27 | 2023-04-10 | 2023-06-15 | 2023-07-27 | 108
0 | PMBKIN2695 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - JUNCTION / MARSALLING BOXES INSTRUMENT & TELECOM | 42 | 2023-03-29 | 2023-05-10 | 2023-08-12 | 2023-09-23 | 136
E&I STRUCTURAL STEEL |  |  | 144 | 2022-09-01 | 2023-01-23 | 2023-01-08 | 2023-09-22 | 242
0 | PMBKIN2702 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - E&I STRUCTURAL STEEL | 28 | 2022-09-01 | 2022-09-29 | 2023-01-08 | 2023-02-05 | 129
0 | PMBKIN2700 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - E&I STRUCTURAL STEEL | 14 | 2022-09-29 | 2022-10-13 | 2023-02-05 | 2023-02-19 | 129
0 | PMBKIN2710 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - E&I STRUCTURAL STEEL | 42 | 2022-09-29 | 2022-11-10 | 2023-02-05 | 2023-03-19 | 129
0 | PMBKIN2715 | FINAL ACCEPTANCE TEST (FAT) - E&I STRUCTURAL STEEL | 7 | 2022-11-10 | 2022-11-17 | 2023-03-19 | 2023-03-26 | 129
0 | PMBKIN2720 | FOB DELIVERY - E&I STRUCTURAL STEEL | 7 | 2022-11-17 | 2022-11-24 | 2023-03-26 | 2023-04-02 | 129
0 | PMBKIN2725 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - E&I STRUCTURAL STEEL | 30 | 2022-11-24 | 2022-12-24 | 2023-04-02 | 2023-05-02 | 129
0 | PMBKIN2730 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - E&I STRUCTURAL STEEL | 30 | 2022-12-24 | 2023-01-23 | 2023-08-23 | 2023-09-22 | 242
ELECTRICAL |  |  | 193 | 2022-10-25 | 2023-05-06 | 2023-02-03 | 2023-11-01 | 179
HIGH VOLTAGE CABLES |  |  | 191 | 2022-10-27 | 2023-05-06 | 2023-02-03 | 2023-10-25 | 172
0 | PMBKEL2003 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - HIGH VOLTAGE CABLES | 42 | 2022-10-27 | 2022-12-08 | 2023-02-03 | 2023-03-17 | 99
0 | PMBKEL2000 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - HIGH VOLTAGE CABLES | 28 | 2022-12-08 | 2023-01-05 | 2023-03-17 | 2023-04-14 | 99
0 | PMBKEL2010 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - HIGH VOLTAGE CABLES | 63 | 2022-12-08 | 2023-02-09 | 2023-03-17 | 2023-05-19 | 99
0 | PMBKEL2015 | FINAL ACCEPTANCE TEST (FAT) - HIGH VOLTAGE CABLES | 7 | 2023-02-09 | 2023-02-16 | 2023-05-19 | 2023-05-26 | 99
0 | PMBKEL2020 | COMPLETE MATERIAL DISPATCH / FOB - HIGH VOLTAGE CABLES | 7 | 2023-02-16 | 2023-02-23 | 2023-05-26 | 2023-06-02 | 99
0 | PMBKEL2025 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - HIGH VOLTAGE CABLES | 42 | 2023-02-23 | 2023-04-06 | 2023-06-02 | 2023-07-14 | 99
0 | PMBKEL2030 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - HIGH VOLTAGE CABLES | 42 | 2023-03-25 | 2023-05-06 | 2023-09-13 | 2023-10-25 | 172
LOW VOLTAGE CABLES |  |  | 184 | 2022-10-26 | 2023-04-28 | 2023-02-10 | 2023-10-25 | 180
0 | PMBKEL2033 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - LOW VOLTAGE CABLES | 35 | 2022-10-26 | 2022-11-30 | 2023-02-10 | 2023-03-17 | 107
0 | PMBKEL2035 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - LOW VOLTAGE CABLES | 28 | 2022-11-30 | 2022-12-28 | 2023-03-17 | 2023-04-14 | 107
0 | PMBKEL2045 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - LOW VOLTAGE CABLES | 63 | 2022-11-30 | 2023-02-01 | 2023-03-17 | 2023-05-19 | 107
0 | PMBKEL2050 | FINAL ACCEPTANCE TEST (FAT) - LOW VOLTAGE CABLES | 7 | 2023-02-01 | 2023-02-08 | 2023-05-19 | 2023-05-26 | 107
0 | PMBKEL2055 | COMPLETE MATERIAL DISPATCH / FOB - LOW VOLTAGE CABLES | 7 | 2023-02-08 | 2023-02-15 | 2023-05-26 | 2023-06-02 | 107
0 | PMBKEL2060 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - LOW VOLTAGE CABLES | 42 | 2023-02-15 | 2023-03-29 | 2023-06-02 | 2023-07-14 | 107
0 | PMBKEL2065 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - LOW VOLTAGE CABLES | 42 | 2023-03-17 | 2023-04-28 | 2023-09-13 | 2023-10-25 | 180
CABLE TRAYS & LADDERS |  |  | 158 | 2022-10-26 | 2023-04-02 | 2023-02-19 | 2023-10-05 | 186
0 | PMBKEL2072 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - CABLE TRAYS & LADDERS | 28 | 2022-10-26 | 2022-11-23 | 2023-02-19 | 2023-03-19 | 116
0 | PMBKEL2070 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - CABLE TRAYS & LADDERS | 21 | 2022-11-23 | 2022-12-14 | 2023-03-26 | 2023-04-16 | 123
0 | PMBKEL2080 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - CABLE TRAYS & LADDERS | 56 | 2022-11-23 | 2023-01-18 | 2023-03-19 | 2023-05-14 | 116
0 | PMBKEL2085 | FINAL ACCEPTANCE TEST (FAT) - CABLE TRAYS & LADDERS | 7 | 2023-01-18 | 2023-01-25 | 2023-05-14 | 2023-05-21 | 116
0 | PMBKEL2090 | FOB DELIVERY - CABLE TRAYS & LADDERS | 7 | 2023-01-25 | 2023-02-01 | 2023-05-21 | 2023-05-28 | 116
0 | PMBKEL2095 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - CABLE TRAYS & LADDERS | 30 | 2023-02-01 | 2023-03-03 | 2023-05-28 | 2023-06-27 | 116
0 | PMBKEL2100 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - CABLE TRAYS & LADDERS | 30 | 2023-03-03 | 2023-04-02 | 2023-09-05 | 2023-10-05 | 186
LIGHTING FIXTURES & ACCESSORIES |  |  | 172 | 2022-10-25 | 2023-04-15 | 2023-02-28 | 2023-10-18 | 186
0 | PMBKEL2103 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - LIGHTING FIXTURES & ACCESSORIES | 56 | 2022-10-25 | 2022-12-20 | 2023-02-28 | 2023-04-25 | 126
0 | PMBKEL2105 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - LIGHTING FIXTURES & ACCESSORIES | 21 | 2022-12-20 | 2023-01-10 | 2023-04-25 | 2023-05-16 | 126
0 | PMBKEL2115 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - LIGHTING FIXTURES & ACCESSORIES | 42 | 2022-12-20 | 2023-01-31 | 2023-04-25 | 2023-06-06 | 126
0 | PMBKEL2120 | FINAL ACCEPTANCE TEST (FAT) - LIGHTING FIXTURES & ACCESSORIES | 7 | 2023-01-31 | 2023-02-07 | 2023-06-06 | 2023-06-13 | 126
0 | PMBKEL2125 | COMPLETE MATERIAL DISPATCH / FOB - LIGHTING FIXTURES & ACCESSORIES | 7 | 2023-02-07 | 2023-02-14 | 2023-06-13 | 2023-06-20 | 126
0 | PMBKEL2130 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - LIGHTING FIXTURES & ACCESSORIES | 30 | 2023-02-14 | 2023-03-16 | 2023-06-20 | 2023-07-20 | 126
0 | PMBKEL2135 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - LIGHTING FIXTURES & ACCESSORIES | 30 | 2023-03-16 | 2023-04-15 | 2023-09-18 | 2023-10-18 | 186
CABLE GLANDS |  |  | 179 | 2022-10-31 | 2023-04-28 | 2023-03-01 | 2023-11-01 | 187
0 | PMBKEL2142 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - ELECTRICAL CABLE GLANDS | 42 | 2022-10-31 | 2022-12-12 | 2023-03-01 | 2023-04-12 | 121
0 | PMBKEL2140 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - ELECTRICAL CABLE GLANDS | 35 | 2022-12-12 | 2023-01-16 | 2023-04-12 | 2023-05-17 | 121
0 | PMBKEL2150 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - ELECTRICAL CABLE GLANDS | 63 | 2022-12-12 | 2023-02-13 | 2023-04-12 | 2023-06-14 | 121
0 | PMBKEL2155 | FINAL ACCEPTANCE TEST (FAT) - ELECTRICAL CABLE GLANDS | 7 | 2023-02-13 | 2023-02-20 | 2023-06-14 | 2023-06-21 | 121
0 | PMBKEL2160 | FOB DELIVERY - ELECTRICAL CABLE GLANDS | 7 | 2023-02-20 | 2023-02-27 | 2023-06-21 | 2023-06-28 | 121
0 | PMBKEL2165 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - ELECTRICAL CABLE GLANDS | 30 | 2023-02-27 | 2023-03-29 | 2023-06-28 | 2023-07-28 | 121
0 | PMBKEL2170 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - ELECTRICAL CABLE GLANDS | 30 | 2023-03-29 | 2023-04-28 | 2023-10-02 | 2023-11-01 | 187
JUNCTION BOXES |  |  | 172 | 2022-10-31 | 2023-04-21 | 2023-03-16 | 2023-10-21 | 183
0 | PMBKEL2172 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - ELECTRICAL JUNCTION BOXES | 42 | 2022-10-31 | 2022-12-12 | 2023-03-16 | 2023-04-27 | 136
0 | PMBKEL2175 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - ELECTRICAL JUNCTION BOXES | 21 | 2022-12-12 | 2023-01-02 | 2023-04-27 | 2023-05-18 | 136
0 | PMBKEL2185 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - ELECTRICAL JUNCTION BOXES | 56 | 2022-12-12 | 2023-02-06 | 2023-04-27 | 2023-06-22 | 136
0 | PMBKEL2190 | FINAL ACCEPTANCE TEST (FAT) - ELECTRICAL JUNCTION BOXES | 7 | 2023-02-06 | 2023-02-13 | 2023-06-22 | 2023-06-29 | 136
0 | PMBKEL2195 | FOB DELIVERY - ELECTRICAL JUNCTION BOXES | 7 | 2023-02-13 | 2023-02-20 | 2023-06-29 | 2023-07-06 | 136
0 | PMBKEL2200 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - ELECTRICAL JUNCTION BOXES | 30 | 2023-02-20 | 2023-03-22 | 2023-07-06 | 2023-08-05 | 136
0 | PMBKEL2205 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - ELECTRICAL JUNCTION BOXES | 30 | 2023-03-22 | 2023-04-21 | 2023-09-21 | 2023-10-21 | 183
EARTHING MATERIAL & ACCESSORIES |  |  | 172 | 2022-10-31 | 2023-04-21 | 2023-04-04 | 2023-10-14 | 176
0 | PMBKEL2208 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - EARTHING MATERIAL & ACCESSORIES | 42 | 2022-10-31 | 2022-12-12 | 2023-04-04 | 2023-05-16 | 155
0 | PMBKEL2210 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - EARTHING MATERIAL & ACCESSORIES | 28 | 2022-12-12 | 2023-01-09 | 2023-05-16 | 2023-06-13 | 155
0 | PMBKEL2220 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - EARTHING MATERIAL & ACCESSORIES | 56 | 2022-12-12 | 2023-02-06 | 2023-05-16 | 2023-07-11 | 155
0 | PMBKEL2225 | FINAL ACCEPTANCE TEST (FAT) - EARTHING MATERIAL & ACCESSORIES | 7 | 2023-02-06 | 2023-02-13 | 2023-07-11 | 2023-07-18 | 155
0 | PMBKEL2230 | FOB DELIVERY - EARTHING MATERIAL & ACCESSORIES | 7 | 2023-02-13 | 2023-02-20 | 2023-07-18 | 2023-07-25 | 155
0 | PMBKEL2235 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - EARTHING MATERIAL & ACCESSORIES | 30 | 2023-02-20 | 2023-03-22 | 2023-07-25 | 2023-08-24 | 155
0 | PMBKEL2240 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - EARTHING MATERIAL & ACCESSORIES | 30 | 2023-03-22 | 2023-04-21 | 2023-09-14 | 2023-10-14 | 176
ELECTRICAL BOLTS & NUTS |  |  | 162 | 2022-11-02 | 2023-04-13 | 2023-03-06 | 2023-10-18 | 188
0 | PMBKEL2243 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - ELECTRICAL BOLTS & NUTS | 35 | 2022-11-02 | 2022-12-07 | 2023-03-06 | 2023-04-10 | 124
0 | PMBKEL2245 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - ELECTRICAL BOLTS & NUTS | 35 | 2022-12-07 | 2023-01-11 | 2023-04-10 | 2023-05-15 | 124
0 | PMBKEL2255 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - ELECTRICAL BOLTS & NUTS | 56 | 2022-12-14 | 2023-02-08 | 2023-04-17 | 2023-06-12 | 124
0 | PMBKEL2260 | FINAL ACCEPTANCE TEST (FAT) - ELECTRICAL BOLTS & NUTS | 7 | 2023-02-08 | 2023-02-15 | 2023-06-12 | 2023-06-19 | 124
0 | PMBKEL2265 | FOB DELIVERY - ELECTRICAL BOLTS & NUTS | 7 | 2023-02-15 | 2023-02-22 | 2023-06-19 | 2023-06-26 | 124
0 | PMBKEL2270 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - ELECTRICAL BOLTS & NUTS | 30 | 2023-02-22 | 2023-03-24 | 2023-06-26 | 2023-07-26 | 124
0 | PMBKEL2275 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - ELECTRICAL BOLTS & NUTS | 30 | 2023-03-14 | 2023-04-13 | 2023-09-18 | 2023-10-18 | 188
HV CABLE TERMINATION KITS |  |  | 179 | 2022-11-02 | 2023-04-30 | 2023-02-21 | 2023-10-25 | 178
0 | PMEQEL2282 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - HV CABLES TERMINATION KITS | 42 | 2022-11-02 | 2022-12-14 | 2023-02-21 | 2023-04-04 | 111
0 | PMEQEL2280 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - HV CABLES TERMINATION KITS | 35 | 2022-12-14 | 2023-01-18 | 2023-04-08 | 2023-05-13 | 115
0 | PMEQEL2290 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - HV CABLES TERMINATION KITS | 63 | 2022-12-14 | 2023-02-15 | 2023-04-04 | 2023-06-06 | 111
0 | PMEQEL2295 | FINAL ACCEPTANCE TEST (FAT) - HV CABLES TERMINATION KITS | 7 | 2023-02-15 | 2023-02-22 | 2023-06-06 | 2023-06-13 | 111
0 | PMEQEL2300 | FOB DELIVERY - HV CABLES TERMINATION KITS | 7 | 2023-02-22 | 2023-03-01 | 2023-06-13 | 2023-06-20 | 111
0 | PMEQEL2305 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - HV CABLES TERMINATION KITS | 30 | 2023-03-01 | 2023-03-31 | 2023-06-20 | 2023-07-20 | 111
0 | PMEQEL2310 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - HV CABLES TERMINATION KITS | 30 | 2023-03-31 | 2023-04-30 | 2023-09-25 | 2023-10-25 | 178
SOCKETS & ISOLATING SWITCHES |  |  | 172 | 2022-10-28 | 2023-04-18 | 2023-03-22 | 2023-10-18 | 183
0 | PMBKEL2313 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - SOCKET & ISOLATION SWITCHES | 42 | 2022-10-28 | 2022-12-09 | 2023-03-22 | 2023-05-03 | 145
0 | PMBKEL2315 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - SOCKET & ISOLATION SWITCHES | 35 | 2022-12-09 | 2023-01-13 | 2023-05-03 | 2023-06-07 | 145
0 | PMBKEL2325 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - SOCKET & ISOLATION SWITCHES | 56 | 2022-12-09 | 2023-02-03 | 2023-05-03 | 2023-06-28 | 145
0 | PMBKEL2330 | FINAL ACCEPTANCE TEST (FAT) - SOCKET & ISOLATION SWITCHES | 7 | 2023-02-03 | 2023-02-10 | 2023-06-28 | 2023-07-05 | 145
0 | PMBKEL2335 | COMPLETE MATERIAL DISPATCH / FOB - SOCKET & ISOLATION SWITCHES | 7 | 2023-02-10 | 2023-02-17 | 2023-07-05 | 2023-07-12 | 145
0 | PMBKEL2340 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - SOCKET & ISOLATION SWITCHES | 30 | 2023-02-17 | 2023-03-19 | 2023-07-12 | 2023-08-11 | 145
0 | PMBKEL2345 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - SOCKET & ISOLATION SWITCHES | 30 | 2023-03-19 | 2023-04-18 | 2023-09-18 | 2023-10-18 | 183
SAFETY |  |  | 186 | 2022-10-31 | 2023-05-05 | 2023-03-04 | 2023-11-09 | 188
FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT |  |  | 186 | 2022-10-31 | 2023-05-05 | 2023-04-07 | 2023-11-09 | 188
0 | PMBKSA2002 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT | 56 | 2022-10-31 | 2022-12-26 | 2023-04-07 | 2023-06-02 | 158
0 | PMBKSA2000 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT | 28 | 2022-12-26 | 2023-01-23 | 2023-06-02 | 2023-06-30 | 158
0 | PMBKSA2010 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT | 56 | 2022-12-26 | 2023-02-20 | 2023-06-02 | 2023-07-28 | 158
0 | PMBKSA2015 | FINAL ACCEPTANCE TEST (FAT) - FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT | 7 | 2023-02-20 | 2023-02-27 | 2023-07-28 | 2023-08-04 | 158
0 | PMBKSA2020 | FOB DELIVERY - FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT | 7 | 2023-02-27 | 2023-03-06 | 2023-08-04 | 2023-08-11 | 158
0 | PMBKSA2025 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT | 30 | 2023-03-06 | 2023-04-05 | 2023-08-11 | 2023-09-10 | 158
0 | PMBKSA2030 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - FIREFIGHTING, LIFE-SAVING & SAFETY EQUIPMENT | 30 | 2023-04-05 | 2023-05-05 | 2023-10-10 | 2023-11-09 | 188
SAFETY SIGNS |  |  | 172 | 2022-11-07 | 2023-04-28 | 2023-03-04 | 2023-11-09 | 195
0 | PMBKSA2037 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - SAFETY SIGNS | 42 | 2022-11-07 | 2022-12-19 | 2023-03-04 | 2023-04-15 | 117
0 | PMBKSA2035 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - SAFETY SIGNS | 28 | 2022-12-19 | 2023-01-16 | 2023-04-15 | 2023-05-13 | 117
0 | PMBKSA2045 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - SAFETY SIGNS | 56 | 2022-12-19 | 2023-02-13 | 2023-04-15 | 2023-06-10 | 117
0 | PMBKSA2050 | FINAL ACCEPTANCE TEST (FAT) - SAFETY SIGNS | 7 | 2023-02-13 | 2023-02-20 | 2023-06-10 | 2023-06-17 | 117
0 | PMBKSA2055 | FOB DELIVERY - SAFETY SIGNS | 7 | 2023-02-20 | 2023-02-27 | 2023-06-17 | 2023-06-24 | 117
0 | PMBKSA2060 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - SAFETY SIGNS | 30 | 2023-02-27 | 2023-03-29 | 2023-06-24 | 2023-07-24 | 117
0 | PMBKSA2065 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - SAFETY SIGNS | 30 | 2023-03-29 | 2023-04-28 | 2023-10-10 | 2023-11-09 | 195
PIPELINES & OTHER PIPELINE MATERIALS |  |  | 448 | 2022-04-04 | 2023-06-26 | 2022-06-03 | 2023-10-29 | 125
LINE PIPE (SAW) |  |  | 333 | 2022-04-18 | 2023-03-17 | 2022-06-19 | 2023-05-18 | 62
0 | PMBKPL2002 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - LINE PIPE (SAW) | 63 | 2022-04-18 | 2022-06-20 | 2022-06-19 | 2022-08-21 | 62
0 | PMBKPL2000 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - LINE PIPE (SAW) | 63 | 2022-06-20 | 2022-08-22 | 2022-08-21 | 2022-10-23 | 62
0 | PMBKPL2635 | RECEIVE PLATE AT PIPE SHOP - LINE PIPE (SAW) | 70 | 2022-06-20 | 2022-08-29 | 2022-08-21 | 2022-10-30 | 62
0 | PMBKPL2010 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - LINE PIPE (SAW) | 107 | 2022-08-29 | 2022-12-14 | 2022-10-30 | 2023-02-14 | 62
0 | PMBKPL2020 | FINAL ACCEPTANCE TEST (FAT) - LINE PIPE (SAW) | 7 | 2022-12-14 | 2022-12-21 | 2023-02-14 | 2023-02-21 | 62
0 | PMBKPL2025 | FOB DELIVERY - LINE PIPE (SAW) | 14 | 2022-12-21 | 2023-01-04 | 2023-02-21 | 2023-03-07 | 62
0 | PMBKPL2015 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - LINE PIPE (SAW) | 42 | 2023-01-04 | 2023-02-15 | 2023-03-07 | 2023-04-18 | 62
0 | PMBKPL2030 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - LINE PIPE (SAW) | 42 | 2023-02-03 | 2023-03-17 | 2023-04-06 | 2023-05-18 | 62
LINE PIPE (SMLS) |  |  | 251 | 2022-04-04 | 2022-12-11 | 2022-06-03 | 2023-03-11 | 90
0 | PMBKPL2033 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - LINE PIPE (SMLS) | 70 | 2022-04-04 | 2022-06-13 | 2022-06-03 | 2022-08-12 | 60
0 | PMBKPL2645 | RECEIVE PLATE AT PIPE SHOP - LINE PIPE (SMLS) | 42 | 2022-06-13 | 2022-07-25 | 2022-08-12 | 2022-09-23 | 60
0 | PMBKPL2035 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - LINE PIPE (SMLS) | 70 | 2022-06-13 | 2022-08-22 | 2022-08-12 | 2022-10-21 | 60
0 | PMBKPL2045 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - LINE PIPE (SMLS) | 58 | 2022-07-25 | 2022-09-21 | 2022-09-23 | 2022-11-20 | 60
0 | PMBKPL2050 | FINAL ACCEPTANCE TEST (FAT) - LINE PIPE (SMLS) | 7 | 2022-09-21 | 2022-09-28 | 2022-11-20 | 2022-11-27 | 60
0 | PMBKPL2055 | FOB DELIVERY - LINE PIPE (SMLS) | 14 | 2022-09-28 | 2022-10-12 | 2022-11-27 | 2022-12-11 | 60
0 | PMBKPL2060 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - LINE PIPE (SMLS) | 30 | 2022-10-12 | 2022-11-11 | 2022-12-11 | 2023-01-10 | 60
0 | PMBKPL2065 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - LINE PIPE (SMLS) | 30 | 2022-11-11 | 2022-12-11 | 2023-02-09 | 2023-03-11 | 90
PIPELINE INDUCTION BENDS |  |  | 283 | 2022-05-20 | 2023-02-27 | 2022-09-25 | 2023-07-05 | 128
0 | PMBKPL2072 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIPELINE INDUCTION BENDS | 70 | 2022-05-20 | 2022-07-29 | 2022-09-25 | 2022-12-04 | 128
0 | PMBKPL2070 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIPELINE INDUCTION BENDS | 56 | 2022-07-29 | 2022-09-23 | 2022-12-12 | 2023-02-06 | 136
0 | PMBKPL2080 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIPELINE INDUCTION BENDS | 120 | 2022-07-29 | 2022-11-26 | 2022-12-04 | 2023-04-03 | 128
0 | PMBKPL2085 | FINAL ACCEPTANCE TEST (FAT) - PIPELINE INDUCTION BENDS | 7 | 2022-11-26 | 2022-12-03 | 2023-04-03 | 2023-04-10 | 128
0 | PMBKPL2095 | FOB DELIVERY - PIPELINE INDUCTION BENDS | 14 | 2022-12-03 | 2022-12-17 | 2023-04-10 | 2023-04-24 | 128
0 | PMBKPL2090 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIPELINE INDUCTION BENDS | 42 | 2022-12-17 | 2023-01-28 | 2023-04-24 | 2023-06-05 | 128
0 | PMBKPL2100 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIPELINE INDUCTION BENDS | 42 | 2023-01-16 | 2023-02-27 | 2023-05-24 | 2023-07-05 | 128
RISER HANGER FLANGES |  |  | 275 | 2022-06-15 | 2023-03-17 | 2022-11-01 | 2023-08-03 | 139
0 | PMBKPL2103 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - RISER HANGER FLANGES | 70 | 2022-06-15 | 2022-08-24 | 2022-11-01 | 2023-01-10 | 139
0 | PMBKPL2105 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - RISER HANGER FLANGES | 56 | 2022-08-24 | 2022-10-19 | 2023-01-10 | 2023-03-07 | 139
0 | PMBKPL2115 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - RISER HANGER FLANGES | 110 | 2022-08-26 | 2022-12-14 | 2023-01-12 | 2023-05-02 | 139
0 | PMBKPL2120 | FINAL ACCEPTANCE TEST (FAT) - RISER HANGER FLANGES | 7 | 2022-12-14 | 2022-12-21 | 2023-05-02 | 2023-05-09 | 139
0 | PMBKPL2130 | FOB DELIVERY - RISER HANGER FLANGES | 14 | 2022-12-21 | 2023-01-04 | 2023-05-09 | 2023-05-23 | 139
0 | PMBKPL2125 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - RISER HANGER FLANGES | 42 | 2023-01-04 | 2023-02-15 | 2023-05-23 | 2023-07-04 | 139
0 | PMBKPL2135 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - RISER HANGER FLANGES | 42 | 2023-02-03 | 2023-03-17 | 2023-06-22 | 2023-08-03 | 139
PIPELINE ANODES |  |  | 76 | 2022-09-02 | 2022-11-17 | 2022-11-05 | 2023-01-20 | 64
0 | PMBKPL2142 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIPELINE ANODES | 21 | 2022-09-02 | 2022-09-23 | 2022-11-05 | 2022-11-26 | 64
0 | PMBKPL2140 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIPELINE ANODES | 14 | 2022-09-23 | 2022-10-07 | 2022-11-26 | 2022-12-10 | 64
0 | PMBKPL2150 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIPELINE ANODES | 35 | 2022-09-23 | 2022-10-28 | 2022-11-26 | 2022-12-31 | 64
0 | PMBKPL2155 | FINAL ACCEPTANCE TEST (FAT) - PIPELINE ANODES | 3 | 2022-10-28 | 2022-10-31 | 2022-12-31 | 2023-01-03 | 64
0 | PMBKPL2160 | FOB DELIVERY - PIPELINE ANODES | 3 | 2022-10-31 | 2022-11-03 | 2023-01-03 | 2023-01-06 | 64
0 | PMBKPL2165 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIPELINE ANODES | 7 | 2022-11-03 | 2022-11-10 | 2023-01-06 | 2023-01-13 | 64
0 | PMBKPL2170 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIPELINE ANODES | 7 | 2022-11-10 | 2022-11-17 | 2023-01-13 | 2023-01-20 | 64
PIPELINE FLANGES |  |  | 270 | 2022-06-20 | 2023-03-17 | 2022-10-07 | 2023-07-04 | 109
0 | PMBKPL2177 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIPELINE FLANGES | 70 | 2022-06-20 | 2022-08-29 | 2022-10-07 | 2022-12-16 | 109
0 | PMBKPL2175 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIPELINE FLANGES | 56 | 2022-08-29 | 2022-10-24 | 2022-12-22 | 2023-02-16 | 115
0 | PMBKPL2185 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIPELINE FLANGES | 107 | 2022-08-29 | 2022-12-14 | 2022-12-16 | 2023-04-02 | 109
0 | PMBKPL2190 | FINAL ACCEPTANCE TEST (FAT) - PIPELINE FLANGES | 7 | 2022-12-14 | 2022-12-21 | 2023-04-02 | 2023-04-09 | 109
0 | PMBKPL2200 | FOB DELIVERY - PIPELINE FLANGES | 14 | 2022-12-21 | 2023-01-04 | 2023-04-09 | 2023-04-23 | 109
0 | PMBKPL2195 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIPELINE FLANGES | 42 | 2023-01-04 | 2023-02-15 | 2023-04-23 | 2023-06-04 | 109
0 | PMBKPL2205 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIPELINE FLANGES | 42 | 2023-02-03 | 2023-03-17 | 2023-05-23 | 2023-07-04 | 109
PIPELINE BARRED TEE |  |  | 275 | 2022-06-08 | 2023-03-10 | 2022-09-24 | 2023-06-26 | 108
0 | PMBKPL2218 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIPELINE BARRED TEE | 70 | 2022-06-08 | 2022-08-17 | 2022-09-24 | 2022-12-03 | 108
0 | PMBKPL2210 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIPELINE BARRED TEE | 56 | 2022-08-17 | 2022-10-12 | 2022-12-03 | 2023-01-28 | 108
0 | PMBKPL2220 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIPELINE BARRED TEE | 110 | 2022-08-19 | 2022-12-07 | 2022-12-05 | 2023-03-25 | 108
0 | PMBKPL2225 | FINAL ACCEPTANCE TEST (FAT) - PIPELINE BARRED TEE | 7 | 2022-12-07 | 2022-12-14 | 2023-03-25 | 2023-04-01 | 108
0 | PMBKPL2235 | FOB DELIVERY - PIPELINE BARRED TEE | 14 | 2022-12-14 | 2022-12-28 | 2023-04-01 | 2023-04-15 | 108
0 | PMBKPL2230 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIPELINE BARRED TEE | 42 | 2022-12-28 | 2023-02-08 | 2023-04-15 | 2023-05-27 | 108
0 | PMBKPL2240 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIPELINE BARRED TEE | 42 | 2023-01-27 | 2023-03-10 | 2023-05-15 | 2023-06-26 | 108
PIPELINE FITTINGS |  |  | 267 | 2022-07-27 | 2023-04-20 | 2022-10-17 | 2023-07-11 | 82
0 | PMBKPL2243 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIPELINE FITTING | 70 | 2022-07-27 | 2022-10-05 | 2022-10-17 | 2022-12-26 | 82
0 | PMBKPL2245 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIPELINE FITTING | 56 | 2022-10-05 | 2022-11-30 | 2022-12-30 | 2023-02-24 | 86
0 | PMBKPL2255 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIPELINE FITTING | 105 | 2022-10-05 | 2023-01-18 | 2022-12-26 | 2023-04-10 | 82
0 | PMBKPL2260 | FINAL ACCEPTANCE TEST (FAT) - PIPELINE FITTING | 7 | 2023-01-18 | 2023-01-25 | 2023-04-10 | 2023-04-17 | 82
0 | PMBKPL2270 | FOB DELIVERY - PIPELINE FITTING | 14 | 2023-01-25 | 2023-02-08 | 2023-04-17 | 2023-05-01 | 82
0 | PMBKPL2265 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIPELINE FITTING | 42 | 2023-02-08 | 2023-03-22 | 2023-05-01 | 2023-06-12 | 82
0 | PMBKPL2275 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIPELINE FITTING | 42 | 2023-03-09 | 2023-04-20 | 2023-05-30 | 2023-07-11 | 82
PIPELINE CABLE PROTECTOR & BALLAST MODULE |  |  | 266 | 2022-10-03 | 2023-06-26 | 2023-02-05 | 2023-10-29 | 125
0 | PMBKPL2282 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIPELINE CABLE PROTECTOR & BALLAST MODULE | 63 | 2022-10-03 | 2022-12-05 | 2023-02-05 | 2023-04-09 | 125
0 | PMBKPL2280 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIPELINE CABLE PROTECTOR & BALLAST MODULE | 56 | 2022-12-05 | 2023-01-30 | 2023-04-14 | 2023-06-09 | 130
0 | PMBKPL2290 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIPELINE CABLE PROTECTOR & BALLAST MODULE | 110 | 2022-12-05 | 2023-03-25 | 2023-04-09 | 2023-07-28 | 125
0 | PMBKPL2295 | FINAL ACCEPTANCE TEST (FAT) - PIPELINE CABLE PROTECTOR & BALLAST MODULE | 7 | 2023-03-25 | 2023-04-01 | 2023-07-28 | 2023-08-04 | 125
0 | PMBKPL2305 | FOB DELIVERY - PIPELINE CABLE PROTECTOR & BALLAST MODULE | 14 | 2023-04-01 | 2023-04-15 | 2023-08-04 | 2023-08-18 | 125
0 | PMBKPL2300 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIPELINE CABLE PROTECTOR & BALLAST MODULE | 42 | 2023-04-15 | 2023-05-27 | 2023-08-18 | 2023-09-29 | 125
0 | PMBKPL2310 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIPELINE CABLE PROTECTOR & BALLAST MODULE | 42 | 2023-05-15 | 2023-06-26 | 2023-09-17 | 2023-10-29 | 125
PIGGYBACK SADDLES |  |  | 236 | 2022-08-15 | 2023-04-08 | 2022-10-16 | 2023-06-09 | 62
0 | PMBKPL2313 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIGGYBACK SADDLES | 63 | 2022-08-15 | 2022-10-17 | 2022-10-16 | 2022-12-18 | 62
0 | PMBKPL2315 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIGGYBACK SADDLES | 56 | 2022-10-17 | 2022-12-12 | 2023-02-10 | 2023-04-07 | 116
0 | PMBKPL2325 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIGGYBACK SADDLES | 110 | 2022-10-17 | 2023-02-04 | 2022-12-18 | 2023-04-07 | 62
0 | PMBKPL2330 | FINAL ACCEPTANCE TEST (FAT) - PIGGYBACK SADDLES | 7 | 2023-02-04 | 2023-02-11 | 2023-04-07 | 2023-04-14 | 62
0 | PMBKPL2340 | FOB DELIVERY - PIGGYBACK SADDLES | 14 | 2023-02-11 | 2023-02-25 | 2023-04-14 | 2023-04-28 | 62
0 | PMBKPL2335 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIGGYBACK SADDLES | 42 | 2023-02-25 | 2023-04-08 | 2023-04-28 | 2023-06-09 | 62
0 | PMBKPL2345 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIGGYBACK SADDLES | 42 | 2023-02-25 | 2023-04-08 | 2023-04-28 | 2023-06-09 | 62
PIPELINE GASKETS |  |  | 200 | 2022-10-13 | 2023-05-01 | 2023-02-14 | 2023-09-02 | 124
0 | PMBKPL2352 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIPELINE GASKET | 56 | 2022-10-13 | 2022-12-08 | 2023-02-14 | 2023-04-11 | 124
0 | PMBKPL2350 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIPELINE GASKET | 35 | 2022-12-08 | 2023-01-12 | 2023-04-11 | 2023-05-16 | 124
0 | PMBKPL2360 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIPELINE GASKET | 63 | 2022-12-08 | 2023-02-09 | 2023-04-11 | 2023-06-13 | 124
0 | PMBKPL2365 | FINAL ACCEPTANCE TEST (FAT) - PIPELINE GASKET | 7 | 2023-02-09 | 2023-02-16 | 2023-06-13 | 2023-06-20 | 124
0 | PMBKPL2375 | FOB DELIVERY - PIPELINE GASKET | 14 | 2023-02-16 | 2023-03-02 | 2023-06-20 | 2023-07-04 | 124
0 | PMBKPL2370 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIPELINE GASKET | 30 | 2023-03-02 | 2023-04-01 | 2023-07-04 | 2023-08-03 | 124
0 | PMBKPL2380 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIPELINE GASKET | 30 | 2023-04-01 | 2023-05-01 | 2023-08-03 | 2023-09-02 | 124
PIPELINE BOLTS & NUTS |  |  | 205 | 2022-10-10 | 2023-05-03 | 2023-02-09 | 2023-09-02 | 122
0 | PMBKPL2387 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - PIPELINE BOLTS & NUTS | 42 | 2022-10-10 | 2022-11-21 | 2023-02-09 | 2023-03-23 | 122
0 | PMBKPL2390 | COMMENCE MANUFACTURING - PIPELINE BOLTS & NUTS | 7 | 2022-11-21 | 2022-11-28 | 2023-03-23 | 2023-03-30 | 122
0 | PMBKPL2385 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - PIPELINE BOLTS & NUTS | 28 | 2022-11-21 | 2022-12-19 | 2023-03-23 | 2023-04-20 | 122
0 | PMBKPL2395 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - PIPELINE BOLTS & NUTS | 63 | 2022-11-28 | 2023-01-30 | 2023-03-30 | 2023-06-01 | 122
0 | PMBKPL2400 | FINAL ACCEPTANCE TEST (FAT) - PIPELINE BOLTS & NUTS | 7 | 2023-01-30 | 2023-02-06 | 2023-06-01 | 2023-06-08 | 122
0 | PMBKPL2410 | FOB DELIVERY - PIPELINE BOLTS & NUTS | 14 | 2023-02-06 | 2023-02-20 | 2023-06-08 | 2023-06-22 | 122
0 | PMBKPL2405 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - PIPELINE BOLTS & NUTS | 42 | 2023-02-20 | 2023-04-03 | 2023-06-22 | 2023-08-03 | 122
0 | PMBKPL2415 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - PIPELINE BOLTS & NUTS | 42 | 2023-03-22 | 2023-05-03 | 2023-07-22 | 2023-09-02 | 122
EXTERNAL COATING FOR INDUCTION BENDS |  |  | 193 | 2022-09-28 | 2023-04-09 | 2022-12-23 | 2023-07-04 | 86
0 | PMBKPL2422 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - EXTERNAL COATING FOR INDUCTION BENDS | 56 | 2022-09-28 | 2022-11-23 | 2022-12-23 | 2023-02-17 | 86
0 | PMBKPL2420 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - EXTERNAL COATING FOR INDUCTION BENDS | 35 | 2022-11-23 | 2022-12-28 | 2023-02-19 | 2023-03-26 | 88
0 | PMBKPL2430 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - EXTERNAL COATING FOR INDUCTION BENDS | 65 | 2022-11-23 | 2023-01-27 | 2023-02-17 | 2023-04-23 | 86
0 | PMBKPL2435 | FINAL ACCEPTANCE TEST (FAT) - EXTERNAL COATING FOR INDUCTION BENDS | 7 | 2023-01-27 | 2023-02-03 | 2023-04-23 | 2023-04-30 | 86
0 | PMBKPL2440 | FOB DELIVERY - EXTERNAL COATING FOR INDUCTION BENDS | 14 | 2023-02-03 | 2023-02-17 | 2023-04-30 | 2023-05-14 | 86
0 | PMBKPL2445 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - EXTERNAL COATING FOR INDUCTION BENDS | 30 | 2023-02-08 | 2023-03-10 | 2023-05-05 | 2023-06-04 | 86
0 | PMBKPL2450 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - EXTERNAL COATING FOR INDUCTION BENDS | 30 | 2023-03-10 | 2023-04-09 | 2023-06-04 | 2023-07-04 | 86
HDPE PIPES |  |  | 234 | 2022-07-15 | 2023-03-06 | 2022-09-23 | 2023-05-15 | 70
0 | PMBKPL2457 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - HDPE PIPES | 63 | 2022-07-15 | 2022-09-16 | 2022-09-23 | 2022-11-25 | 70
0 | PMBKPL2455 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - HDPE PIPES | 42 | 2022-09-16 | 2022-10-28 | 2022-11-28 | 2023-01-09 | 73
0 | PMBKPL2465 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - HDPE PIPES | 90 | 2022-09-16 | 2022-12-15 | 2022-11-25 | 2023-02-23 | 70
0 | PMBKPL2470 | FINAL ACCEPTANCE TEST (FAT) - HDPE PIPES | 7 | 2022-12-15 | 2022-12-22 | 2023-02-23 | 2023-03-02 | 70
0 | PMBKPL2480 | FOB DELIVERY - HDPE PIPES | 14 | 2022-12-22 | 2023-01-05 | 2023-03-02 | 2023-03-16 | 70
0 | PMBKPL2475 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - HDPE PIPES | 30 | 2023-01-05 | 2023-02-04 | 2023-03-16 | 2023-04-15 | 70
0 | PMBKPL2485 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - HDPE PIPES | 30 | 2023-02-04 | 2023-03-06 | 2023-04-15 | 2023-05-15 | 70
UMBILICALS & COMPOSITE CABLE |  |  | 610 | 2021-12-19 | 2023-08-21 | 2022-08-18 | 2023-10-19 | 59
6.6kV COMPOSITE SUBSEA CABLE |  |  | 427 | 2022-06-20 | 2023-08-21 | 2022-08-18 | 2023-10-19 | 59
0 | PMEQEL2002 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - 6.6kV COMPOSITE SUBSEA CABLE | 84 | 2022-06-20 | 2022-09-12 | 2022-08-18 | 2022-11-10 | 59
0 | PMEQEL2000 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - 6.6kV COMPOSITE SUBSEA CABLE | 84 | 2022-09-12 | 2022-12-05 | 2022-11-10 | 2023-02-02 | 59
0 | PMEQEL2010 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - 6.6kV COMPOSITE SUBSEA CABLE | 280 | 2022-09-12 | 2023-06-19 | 2022-11-10 | 2023-08-17 | 59
0 | PMEQEL2015 | FINAL ACCEPTANCE TEST (FAT) - 6.6kV COMPOSITE SUBSEA CABLE | 7 | 2023-06-19 | 2023-06-26 | 2023-08-17 | 2023-08-24 | 59
0 | PMEQEL2020 | FOB DELIVERY - 6.6kV COMPOSITE SUBSEA CABLE | 14 | 2023-06-26 | 2023-07-10 | 2023-08-24 | 2023-09-07 | 59
0 | PMEQEL2025 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - 6.6kV COMPOSITE SUBSEA CABLE | 42 | 2023-07-10 | 2023-08-21 | 2023-09-07 | 2023-10-19 | 59
0 | PMEQEL2030 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - 6.6kV COMPOSITE SUBSEA CABLE | 42 | 2023-07-10 | 2023-08-21 | 2023-09-07 | 2023-10-19 | 59
UMBILICAL |  |  | 244 | 2021-12-19 | 2022-08-20 | 2022-10-09 | 2023-06-10 | 294
0 | PMEQIN2315 | DRAFT TRIPARTITE NOVATION AGREEMENT RELATED TO PROCUREMENT OF THE UMBILICAL IS TO BE PROVIDED BY COMPANY - UMBILICAL | 18 | 2021-12-19 | 2022-01-06 | 2022-10-09 | 2022-10-27 | 294
0 | PMEQIN2320 | REVIEW BY CONTRACTOR (DRAFT TRIPARTITE NOVATION AGREEMENT RELATED TO PROCUREMENT OF THE UMBILICAL) - UMBILICAL | 45 | 2022-01-06 | 2022-02-20 | 2022-10-27 | 2022-12-11 | 294
0 | PMEQIN2325 | DISCUSS WITH COMPANY AND VENDOR AND ULTIMATELY SIGNED TRIPARTITE NOVATION AGREEMENT OF UMBILICAL PROC FOR EXECUTION | 30 | 2022-02-20 | 2022-03-22 | 2022-12-11 | 2023-01-10 | 294
0 | PMEQIN2330 | VENDOR DOCUMENTS REVIEW & APPROVAL - UMBILICAL | 10 | 2022-03-22 | 2022-04-01 | 2023-01-10 | 2023-01-20 | 294
0 | PMEQIN2335 | COMPLETE MANUFACTURING AND READY FOR INSPECTION - UMBILICAL | 127 | 2022-04-01 | 2022-08-06 | 2023-01-20 | 2023-05-27 | 294
0 | PMEQIN2340 | FINAL ACCEPTANCE TEST (FAT) - UMBILICAL | 7 | 2022-08-06 | 2022-08-13 | 2023-05-27 | 2023-06-03 | 294
0 | PMEQIN2345 | FOB DELIVERY - - UMBILICAL | 7 | 2022-08-13 | 2022-08-20 | 2023-06-03 | 2023-06-10 | 294
MISC. MATERIAL ( CONTINGENCY) |  |  | 207 | 2022-11-24 | 2023-06-19 | 2023-04-23 | 2023-11-16 | 150
0 | PMBKSA2155 | RECEIVE VENDOR DOCUMENTS (CRITICAL) - MISC. MATERIAL ( CONTINGENCY) | 56 | 2022-11-24 | 2023-01-19 | 2023-04-23 | 2023-06-18 | 150
0 | PMBKSA2095 | APPROVE VENDOR DOCUMENTS FOR MANUFACTURING (COMPLETE) - MISC. MATERIAL ( CONTINGENCY) | 63 | 2023-01-19 | 2023-03-23 | 2023-06-18 | 2023-08-20 | 150
0 | PMBKSA2105 | COMPLETE MANUFACTURING AND READY FOR INSPECTION -MISC. MATERIAL ( CONTINGENCY) | 70 | 2023-01-19 | 2023-03-30 | 2023-06-18 | 2023-08-27 | 150
0 | PMBKSA2115 | FINAL ACCEPTANCE TEST (FAT) - MISC. MATERIAL ( CONTINGENCY) | 7 | 2023-03-30 | 2023-04-06 | 2023-08-27 | 2023-09-03 | 150
0 | PMBKSA2125 | FOB DELIVERY - MISC. MATERIAL ( CONTINGENCY) | 14 | 2023-04-06 | 2023-04-20 | 2023-09-03 | 2023-09-17 | 150
0 | PMBKSA2135 | TRANSPORTATION & DELIVERY AT SITE 1ST LOT - MISC. MATERIAL ( CONTINGENCY) | 30 | 2023-04-20 | 2023-05-20 | 2023-09-17 | 2023-10-17 | 150
0 | PMBKSA2145 | TRANSPORTATION & DELIVERY AT SITE 2ND LOT - MISC. MATERIAL ( CONTINGENCY) | 30 | 2023-05-20 | 2023-06-19 | 2023-10-17 | 2023-11-16 | 150
CONSTRUCTION, PRE-COMM, COMMISSIONING |  |  | 924 | 2022-02-11 | 2024-08-23 | 2022-04-09 | 2024-09-20 | 28
ONSHORE FABRICATION (INCL. TESTING & ONSHORE PRE-COMM) |  |  | 393 | 2022-09-14 | 2023-10-12 | 2022-12-07 | 2024-03-13 | 153
OFFSHORE |  |  | 393 | 2022-09-14 | 2023-10-12 | 2022-12-07 | 2024-03-13 | 153
FABRICATION OF BU HASEER WHP BH-03 TOPSIDES |  |  | 292 | 2022-09-14 | 2023-08-21 | 2022-12-13 | 2023-11-17 | 77
STRUCTURAL |  |  | 270 | 2022-09-14 | 2023-07-26 | 2022-12-13 | 2023-11-16 | 98
STRUCTURAL PRE-FABRICATION |  |  | 230 | 2022-09-14 | 2023-06-09 | 2022-12-13 | 2023-11-16 | 138
PRE-FAB PLATES |  |  | 102 | 2022-09-14 | 2023-01-11 | 2022-12-13 | 2023-05-10 | 103
0 | FBST1010 | BH-03 - CUT & PROFILE - PLATES (MAIN DECK) | 15 | 2022-09-14 | 2022-10-01 | 2022-12-13 | 2022-12-29 | 77
0 | FBST1000 | BH-03 - CUT & PROFILE - PLATES CELLAR DECK | 15 | 2022-09-26 | 2022-10-13 | 2022-12-27 | 2023-01-12 | 79
0 | FBST1020 | BH-03 - CUT & PROFILE - PLATES (MEZZANINE DECK) | 15 | 2022-10-03 | 2022-10-20 | 2023-01-05 | 2023-01-21 | 81
0 | FBST1030 | BH-03 - CUT & PROFILE - PLATES (WEATHER DECK) | 15 | 2022-10-10 | 2022-10-27 | 2023-01-12 | 2023-01-28 | 81
0 | FBST1040 | BH-03 - CUT & PROFILE - PLATES (ACCESSPLATFORM) | 15 | 2022-10-20 | 2022-11-07 | 2023-02-10 | 2023-02-27 | 97
0 | FBST1050 | BH-03 - CUT & PROFILE - PLATES (HELIDECK, OTHER MISC.) | 48 | 2022-11-16 | 2023-01-11 | 2023-03-16 | 2023-05-10 | 103
PRE-FAB GIRDERS |  |  | 66 | 2022-09-21 | 2022-12-07 | 2022-12-20 | 2023-03-08 | 79
0 | FBST1060 | BH-03 - SUB ASSEMBLE - GIRDERS (MAIN DECK) | 18 | 2022-09-21 | 2022-10-12 | 2022-12-20 | 2023-01-09 | 77
0 | FBST1070 | BH-03 - SUB ASSEMBLE - GIRDERS CELLAR DECK | 18 | 2022-10-03 | 2022-10-24 | 2023-01-13 | 2023-02-02 | 88
0 | FBST1080 | BH-03 - SUB ASSEMBLE - GIRDERS (MEZZANINE DECK) | 18 | 2022-10-10 | 2022-10-31 | 2023-01-26 | 2023-02-15 | 93
0 | FBST1090 | BH-03 - SUB ASSEMBLE - GIRDERS (WEATHER DECK) | 18 | 2022-10-24 | 2022-11-14 | 2023-01-26 | 2023-02-15 | 81
0 | FBST1100 | BH-03 - SUB ASSEMBLE - GIRDERS (HELIDECK) | 18 | 2022-11-16 | 2022-12-07 | 2023-02-16 | 2023-03-08 | 79
WORKSHOP SUB-ASSEMBLE - DECK NODES |  |  | 77 | 2022-09-29 | 2022-12-28 | 2022-12-27 | 2023-03-29 | 79
0 | FBST1110 | BH-03 - SUB ASSEMBLE - NODES (MAIN DECK) | 18 | 2022-09-29 | 2022-10-20 | 2022-12-27 | 2023-01-16 | 76
0 | FBST1120 | BH-03 - SUB ASSEMBLE - NODES CELLAR DECK | 18 | 2022-10-10 | 2022-10-31 | 2023-01-20 | 2023-02-09 | 88
0 | FBST1130 | BH-03 - SUB ASSEMBLE - NODES (MEZZANINE DECK) | 18 | 2022-10-17 | 2022-11-07 | 2023-02-02 | 2023-02-22 | 93
0 | FBST4030 | BH-03 - SUB ASSEMBLE - NODES (ACCESS PLATFORM) | 18 | 2022-10-17 | 2022-11-07 | 2023-02-07 | 2023-02-27 | 97
0 | FBST1140 | BH-03 - SUB ASSEMBLE - NODES (WEATHER DECK) | 18 | 2022-10-31 | 2022-11-21 | 2023-02-16 | 2023-03-08 | 93
0 | FBST1150 | BH-03 - SUB ASSEMBLE - NODES (HELIDECK | 18 | 2022-12-07 | 2022-12-28 | 2023-03-09 | 2023-03-29 | 79
PRE-FAB SECTIONS |  |  | 124 | 2022-10-06 | 2023-02-28 | 2023-01-10 | 2023-06-07 | 86
0 | FBST1160 | BH-03 - CUT & PROFILE - SECTIONS (MAIN DECK) | 21 | 2022-10-06 | 2022-10-31 | 2023-01-10 | 2023-02-02 | 82
0 | FBST1170 | BH-03 - CUT & PROFILE - SECTIONS CELLAR DECK | 21 | 2022-10-13 | 2022-11-07 | 2023-01-17 | 2023-02-09 | 82
0 | FBST1180 | BH-03 - CUT & PROFILE - SECTIONS (MEZZANINE DECK) | 21 | 2022-10-20 | 2022-11-14 | 2023-01-24 | 2023-02-16 | 82
0 | FBST1200 | BH-03 - CUT & PROFILE - SECTIONS (ACCESS PALTFORM) | 18 | 2022-11-03 | 2022-11-24 | 2023-02-07 | 2023-02-27 | 82
0 | FBST1190 | BH-03 - CUT & PROFILE - SECTIONS (WEATHER DECK) | 21 | 2022-11-15 | 2022-12-09 | 2023-02-23 | 2023-03-18 | 86
0 | FBST1210 | BH-03 - CUT & PROFILE - SECTIONS (HDK) | 21 | 2022-12-09 | 2023-01-03 | 2023-03-20 | 2023-04-12 | 86
0 | FBST1220 | BH-03 - CUT & PROFILE - SECTIONS (OTHER MISC.) | 60 | 2022-12-20 | 2023-02-28 | 2023-03-30 | 2023-06-07 | 86
PRE-FAB TUBULARS |  |  | 145 | 2022-09-14 | 2023-03-02 | 2022-12-30 | 2023-07-10 | 112
0 | FBST4040 | BH-03 - CUT & PROFILE - TUBULARS CELLAR/ MAIN & MEZZ DECK FRAMING | 24 | 2022-09-14 | 2022-10-12 | 2022-12-30 | 2023-01-26 | 92
0 | FBST1230 | BH-03 - CUT & PROFILE - TUBULARS (B/W CELLAR DECK & MAIN DECK | 24 | 2022-10-10 | 2022-11-07 | 2023-01-17 | 2023-02-13 | 85
0 | FBST1240 | BH-03 - CUT & PROFILE - TUBULARS (B/W (MAIN DECK) & (MEZZANINE DECK) | 24 | 2022-10-17 | 2022-11-14 | 2023-01-24 | 2023-02-20 | 85
0 | FBST1250 | BH-03 - CUT & PROFILE - TUBULARS (B/W MEZZANINE DECK & WEATHER DECK) | 24 | 2022-10-24 | 2022-11-21 | 2023-02-02 | 2023-03-01 | 87
0 | FBST1260 | BH-03 - CUT & PROFILE - TUBULARS (B/W ACCESS PLATFORM & MEZZANINE DECK) | 24 | 2022-10-24 | 2022-11-21 | 2023-03-24 | 2023-04-20 | 130
0 | FBST1270 | BH-03 - CUT & PROFILE - TUBULARS (HELIDECK) | 24 | 2022-11-21 | 2022-12-19 | 2023-03-02 | 2023-03-29 | 87
0 | FBST1280 | BH-03 - CUT & PROFILE - TUBULARS (OTHER MISC.) | 75 | 2022-12-05 | 2023-03-02 | 2023-04-14 | 2023-07-10 | 112
WORKSHOP SUB-ASSEMBLE - HANDRAILS & LADDERS |  |  | 105 | 2022-12-05 | 2023-04-06 | 2023-04-14 | 2023-08-22 | 119
0 | FBST1290 | BH-03 - SUB ASSEMBLE - HANDRAILS CELLAR DECK | 36 | 2022-12-05 | 2023-01-16 | 2023-04-14 | 2023-05-25 | 112
0 | FBST1300 | BH-03 - SUB ASSEMBLE - HANDRAILS (MAIN DECK) | 36 | 2022-12-16 | 2023-01-27 | 2023-04-28 | 2023-06-08 | 114
0 | FBST4050 | BH-03 - SUB ASSEMBLE - HANDRAILS (ACCESSPLATFORM) | 30 | 2022-12-30 | 2023-02-03 | 2023-06-10 | 2023-07-14 | 139
0 | FBST1310 | BH-03 - SUB ASSEMBLE - HANDRAILS (MEZZANINE DECK) | 36 | 2022-12-30 | 2023-02-10 | 2023-06-03 | 2023-07-14 | 133
0 | FBST1320 | BH-03 - SUB ASSEMBLE - HANDRAILS (WEATHER DECK)) | 36 | 2023-01-13 | 2023-02-24 | 2023-06-21 | 2023-08-01 | 136
0 | FBST1330 | BH-03 - SUB ASSEMBLE - LADDERS & CAGES | 48 | 2023-02-09 | 2023-04-06 | 2023-06-28 | 2023-08-22 | 119
WORKSHOP SUB ASSEMBLE - STAIRWAYS / STAIR TOWER / MAIN LADDER |  |  | 78 | 2023-02-28 | 2023-05-30 | 2023-06-08 | 2023-09-06 | 86
EAST SIDE |  |  | 42 | 2023-02-28 | 2023-04-18 | 2023-06-08 | 2023-08-23 | 110
0 | FBST1340 | BH-03 - SUB ASSEMBLE - CELLAR DECK TO JACKET WALKWAY (EAST SIDE) | 24 | 2023-02-28 | 2023-03-28 | 2023-06-08 | 2023-07-05 | 86
0 | FBST1350 | BH-03 - SUB ASSEMBLE - (MAIN DECK) TO CELLAR DECK (EAST SIDE) | 24 | 2023-03-07 | 2023-04-04 | 2023-07-13 | 2023-08-09 | 110
0 | FBST1360 | BH-03 - SUB ASSEMBLE - MEZZANINE DECK TO (MAIN DECK) (EAST SIDE) | 24 | 2023-03-14 | 2023-04-11 | 2023-07-20 | 2023-08-16 | 110
0 | FBST1370 | BH-03 - SUB ASSEMBLE - WEATHER DECK TO MEZZANINE DECK (EAST SIDE) | 24 | 2023-03-21 | 2023-04-18 | 2023-07-27 | 2023-08-23 | 110
WEST SIDE |  |  | 42 | 2023-03-14 | 2023-05-02 | 2023-06-22 | 2023-08-16 | 92
0 | FBST1380 | BH-03 - SUB ASSEMBLE - MAIN LADDER FROM MAIN. DECK TO CELLAR DECKK (WEST SIDE) | 21 | 2023-03-14 | 2023-04-07 | 2023-06-22 | 2023-07-15 | 86
0 | FBST1390 | BH-03 - SUB ASSEMBLE - MAIN LADDER FROM MEZZANINE DECK TO (MAIN DECK) (WEST SIDE) | 21 | 2023-03-28 | 2023-04-21 | 2023-07-13 | 2023-08-05 | 92
0 | FBST1400 | BH-03 - SUB ASSEMBLE - MAIN LADDER FROM WEATHER DECK TO MEZZANINE DECK (WEST SIDE) | 21 | 2023-04-07 | 2023-05-02 | 2023-07-24 | 2023-08-16 | 92
OTHER MISCELLANEOUS |  |  | 60 | 2023-03-21 | 2023-05-30 | 2023-06-29 | 2023-09-06 | 86
0 | FBST1410 | BH-03 - SUB ASSEMBLE - STAIRWAYS (OTHER MISC.) | 60 | 2023-03-21 | 2023-05-30 | 2023-06-29 | 2023-09-06 | 86
FLOOR DRAINS |  |  | 48 | 2022-10-13 | 2022-12-08 | 2023-02-07 | 2023-05-16 | 137
0 | FBST1420 | BH-03 - SUB ASSEMBLE - FLOOR DRAINS (CELLAR DK) | 21 | 2022-10-13 | 2022-11-07 | 2023-02-07 | 2023-03-02 | 100
0 | FBST1430 | BH-03 - SUB ASSEMBLE - FLOOR DRAINS (MAIN DECK) | 30 | 2022-10-20 | 2022-11-24 | 2023-02-14 | 2023-03-20 | 100
0 | FBST1440 | BH-03 - SUB ASSEMBLE - FLOOR DRAINS (MEZZANINE DECK) | 30 | 2022-10-27 | 2022-12-01 | 2023-03-24 | 2023-04-27 | 127
0 | FBST1450 | BH-03 - SUB ASSEMBLE - FLOOR DRAINS (WEATHER DK) | 30 | 2022-11-03 | 2022-12-08 | 2023-04-12 | 2023-05-16 | 137
WORKSHOP SUB-ASSEMBLE - OTHER STRUCTURES |  |  | 176 | 2022-11-16 | 2023-06-09 | 2023-03-01 | 2023-11-16 | 138
0 | FBST1460 | BH-03 - SUB ASSEMBLE - DECK PENETRATIONS | 36 | 2022-11-16 | 2022-12-28 | 2023-03-01 | 2023-04-11 | 90
0 | FBST1500 | BH-03 - SUB ASSEMBLE - STABBING GUIDES | 24 | 2023-01-27 | 2023-02-24 | 2023-05-11 | 2023-06-07 | 89
0 | FBST1480 | BH-03 - SUB ASSEMBLE DECK PADEYES | 45 | 2023-01-04 | 2023-02-25 | 2023-04-12 | 2023-06-02 | 84
0 | FBST1490 | BH-03 - SUB ASSEMBLE - MONORAIL FRAMES | 56 | 2023-01-14 | 2023-03-21 | 2023-05-23 | 2023-07-26 | 110
0 | FBST1530 | BH-03 - SUB ASSEMBLE SAFETY NET | 24 | 2023-03-08 | 2023-04-05 | 2023-06-08 | 2023-07-05 | 79
0 | FBST1550 | BH-03 - SUB ASSEMBLE - FLARE BOOM | 30 | 2023-03-04 | 2023-04-08 | 2023-07-10 | 2023-08-12 | 109
0 | FBST1520 | BH-03 - SUB ASSEMBLE - DECK HATCHES | 42 | 2023-02-25 | 2023-04-15 | 2023-06-03 | 2023-07-21 | 84
0 | FBST1540 | BH-03 - FABRICATE MISCELLANEOUS ITEMS | 60 | 2023-03-04 | 2023-05-13 | 2023-07-10 | 2023-09-16 | 109
0 | FBST1570 | BH-03 - FABRICATE HELIDECK DRAIN/GUTTER | 60 | 2023-03-04 | 2023-05-13 | 2023-09-08 | 2023-11-16 | 161
0 | FBST1580 | BH-03 - SUB ASSEMBLE - PLATFORM IDENTIFICATION PANELS | 42 | 2023-04-15 | 2023-06-03 | 2023-07-22 | 2023-09-08 | 84
0 | FBST1510 | BH-03 - SUB ASSEMBLE OTHER MISCL STRUCTURES | 56 | 2023-04-05 | 2023-06-09 | 2023-07-06 | 2023-09-08 | 79
PRE-FAB - PIPE SUPPORTS |  |  | 65 | 2022-12-27 | 2023-03-13 | 2023-04-06 | 2023-06-27 | 92
0 | FBST1600 | BH-03 - PRE-FAB -PIPE SUPPORTS (CELLAR DK) (Welded attachments to frame) | 12 | 2022-12-27 | 2023-01-10 | 2023-04-06 | 2023-04-19 | 86
0 | FBST1590 | BH-03 - PRE-FAB - PIPE SUPPORTS (MAIN DECK) (Welded attachments to frame) | 18 | 2022-12-28 | 2023-01-18 | 2023-04-06 | 2023-04-26 | 85
0 | FBST1620 | BH-03 - PRE-FAB - PIPE SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-01-04 | 2023-01-25 | 2023-05-27 | 2023-06-16 | 123
0 | FBST1630 | BH-03 - PRE-FAB - PIPE SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 18 | 2023-01-19 | 2023-02-09 | 2023-04-13 | 2023-05-03 | 72
0 | FBST1610 | BH-03 - PRE-FAB - BALANCE PIPE SUPPORTS (Other than Welded attachments to frame) | 60 | 2023-01-02 | 2023-03-13 | 2023-04-19 | 2023-06-27 | 92
PRE-FAB - EQUIPMENT SUPPORTS |  |  | 67 | 2023-01-11 | 2023-03-30 | 2023-04-13 | 2023-06-22 | 73
0 | FBST1640 | BH-03 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (MAIN DECK) (Welded attachments to frame) | 18 | 2023-01-11 | 2023-02-01 | 2023-04-13 | 2023-05-03 | 79
0 | FBST1660 | BH-03 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (CELLARN DK) (Welded attachments to frame) | 18 | 2023-01-18 | 2023-02-08 | 2023-04-25 | 2023-05-15 | 83
0 | FBST1650 | BH-03 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 18 | 2023-01-26 | 2023-02-16 | 2023-04-20 | 2023-05-10 | 72
0 | FBST1680 | BH-03 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-02-09 | 2023-03-02 | 2023-05-04 | 2023-05-24 | 72
0 | FBST1670 | BH-03 - PRE-FAB - VENT SUPPORT STRUCTURE | 36 | 2023-02-09 | 2023-03-23 | 2023-05-04 | 2023-06-14 | 72
0 | FBST1690 | BH-03 - PRE-FAB - BALANCE EQUIPMENT SUPPORTS (Other than Welded attachments to frame) | 24 | 2023-03-02 | 2023-03-30 | 2023-05-26 | 2023-06-22 | 73
PRE-FAB - E & I CABLE TRAY SUPPORTS |  |  | 74 | 2023-01-25 | 2023-04-21 | 2023-05-02 | 2023-07-27 | 84
0 | FBST1700 | BH-03 - PRE-FAB - CABLE TRAY SUPPORTS (CELLAR DK) (Welded attachments to frame) | 15 | 2023-01-25 | 2023-02-11 | 2023-05-02 | 2023-05-18 | 83
0 | FBST1710 | BH-03 - PRE-FAB - CABLE TRAY SUPPORTS (MAIN DECK) (Welded attachments to frame) | 15 | 2023-02-01 | 2023-02-18 | 2023-05-09 | 2023-05-25 | 83
0 | FBST1720 | BH-03 - PRE-FAB - CABLE TRAY SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 15 | 2023-02-08 | 2023-02-25 | 2023-05-30 | 2023-06-15 | 95
0 | FBST1730 | BH-03 - PRE-FAB - CABLE TRAY SUPPORTS (WEATHER DK) (Welded attachments to frame) | 15 | 2023-02-23 | 2023-03-13 | 2023-06-06 | 2023-06-22 | 88
0 | FBST1750 | BH-03 - PRE-FAB - SECONDARY CABLE TRAY SUPPORTS | 42 | 2023-02-22 | 2023-04-12 | 2023-06-09 | 2023-07-27 | 92
0 | FBST1740 | BH-03 - PRE-FAB - BALANCE CABLE TRAY SUPPORTS (Other than Welded attachments to frame) | 56 | 2023-02-15 | 2023-04-21 | 2023-05-24 | 2023-07-27 | 84
PRE-FAB - OTHER E&I SUPPORTS |  |  | 72 | 2023-02-08 | 2023-05-03 | 2023-05-16 | 2023-08-07 | 83
0 | FBST1760 | BH-03 - PRE-FAB - OTHER E&I SUPPORTS (MAIN DECK) | 30 | 2023-02-08 | 2023-03-15 | 2023-05-16 | 2023-06-19 | 83
0 | FBST1770 | BH-03 - PRE-FAB - OTHER E&I SUPPORTS (CELLAR DK) | 30 | 2023-02-15 | 2023-03-22 | 2023-05-23 | 2023-06-26 | 83
0 | FBST1780 | BH-03 - PRE-FAB - OTHER E&I SUPPORTS (MEZZANINE DECK) | 30 | 2023-02-22 | 2023-03-29 | 2023-05-30 | 2023-07-03 | 83
0 | FBST1800 | BH-03 - PRE-FAB - OTHER E&I SUPPORTS (WEATHER DK) | 30 | 2023-03-01 | 2023-04-05 | 2023-06-06 | 2023-07-10 | 83
0 | FBST1790 | BH-03 - PRE-FAB - BALANCE OTHER E&I SUPPORTS (Other than Welded attachments to frame) | 56 | 2023-02-27 | 2023-05-03 | 2023-06-03 | 2023-08-07 | 83
GENERAL |  |  | 180 | 2022-09-28 | 2023-04-26 | 2023-01-05 | 2023-08-02 | 85
0 | FBST4060 | BH-03 - JOB PREPRATION FOR ASSEMLY & LEVEL LIFTING | 180 | 2022-09-28 | 2023-04-26 | 2023-01-05 | 2023-08-02 | 85
STRUCTURAL ASSEMBLY & ERECTION |  |  | 245 | 2022-10-13 | 2023-07-26 | 2023-01-10 | 2023-10-25 | 79
ASSEMBLY & WELD MAIN DECK |  |  | 93 | 2022-10-13 | 2023-01-30 | 2023-01-10 | 2023-04-27 | 76
0 | FBST2000 | BH-03 - FIT-UP & TACK WELD - MAIN DECK MAIN FRAME - GIRDERS | 21 | 2022-10-13 | 2022-11-07 | 2023-01-10 | 2023-02-02 | 76
0 | FBST2010 | BH-03 - FIT-UP & TACK WELD - MAIN DECK MAIN FRAME - NODES | 21 | 2022-10-13 | 2022-11-07 | 2023-01-10 | 2023-02-02 | 76
0 | FBST2020 | BH-03 - FIT-UP & TACK WELD - MAIN DECK SECONDARY STEEL | 21 | 2022-10-31 | 2022-11-24 | 2023-01-27 | 2023-02-20 | 76
0 | FBST2030 | BH-03 - COMPLETE WELDING - MAIN DECK | 24 | 2022-11-14 | 2022-12-12 | 2023-02-10 | 2023-03-09 | 76
0 | FBST2040 | BH-03 - ERECT & WELD - MAIN DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2022-12-12 | 2023-01-02 | 2023-03-10 | 2023-03-30 | 76
0 | FBST2050 | BH-03 - ERECT & WELD - DECK LEGS AND BRACES (MAIN DECK) | 18 | 2022-12-12 | 2023-01-02 | 2023-03-10 | 2023-03-30 | 76
0 | FBST2060 | BH-03 - PREPARATION - MAIN DECK ERECTION / LIFT | 3 | 2023-01-26 | 2023-01-30 | 2023-04-25 | 2023-04-27 | 76
ASSEMBLY & WELD CELLAR DECK |  |  | 84 | 2022-10-27 | 2023-02-02 | 2023-02-07 | 2023-05-18 | 91
0 | FBST2070 | BH-03 - FIT-UP & TACK WELD - CELLAR DECK MAIN FRAME - GIRDERS | 18 | 2022-10-27 | 2022-11-17 | 2023-02-07 | 2023-02-27 | 88
0 | FBST2080 | BH-03 - FIT-UP & TACK WELD - CELLAR DECK MAIN FRAME - NODES | 18 | 2022-10-27 | 2022-11-17 | 2023-02-10 | 2023-03-02 | 91
0 | FBST2090 | BH-03 - FIT-UP & TACK WELD - CELLAR DECK SECONDARY FRAME | 18 | 2022-11-10 | 2022-12-01 | 2023-02-24 | 2023-03-16 | 91
0 | FBST2100 | BH-03 - COMPLETE WELDING - CELLAR DECK | 15 | 2022-12-01 | 2022-12-19 | 2023-03-17 | 2023-04-03 | 91
0 | FBST2110 | BH-03 - ERECT & WELD - CELLAR DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2022-12-15 | 2023-01-05 | 2023-03-31 | 2023-04-20 | 91
0 | FBST2120 | BH-03 - PREPARATION - CELLAR DECK ERECTION / LIFT | 3 | 2023-01-30 | 2023-02-02 | 2023-05-16 | 2023-05-18 | 91
ASSEMBLY & WELD MEZZANINE DECK |  |  | 93 | 2022-11-03 | 2023-02-20 | 2023-02-20 | 2023-06-08 | 94
0 | FBST2130 | BH-03 - FIT-UP & TACK WELD - MEZZANINE DECK MAIN FRAME - GIRDERS | 21 | 2022-11-03 | 2022-11-28 | 2023-02-20 | 2023-03-15 | 93
0 | FBST2140 | BH-03 - FIT-UP & TACK WELD - MEZZANINE DECK MAIN FRAME - NODES | 21 | 2022-11-03 | 2022-11-28 | 2023-02-21 | 2023-03-16 | 94
0 | FBST2150 | BH-03 - FIT-UP & TACK WELD - MEZZANINE DECK SECONDARY FRAME | 21 | 2022-11-21 | 2022-12-15 | 2023-03-10 | 2023-04-03 | 94
0 | FBST2160 | BH-03 - COMPLETE WELDING - MEZZANINE DECK | 24 | 2022-12-05 | 2023-01-02 | 2023-03-24 | 2023-04-20 | 94
0 | FBST2170 | BH-03 - ERECT & WELD - MEZZANINE DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-01-02 | 2023-01-23 | 2023-04-21 | 2023-05-11 | 94
0 | FBST2180 | BH-03 - ERECT & WELD - DECK LEGS AND BRACES (MEZZANINE DECK - MAIND DECK) | 18 | 2023-01-02 | 2023-01-23 | 2023-04-21 | 2023-05-11 | 94
0 | FBST2190 | BH-03 - PREPARATION - MEZZANINE DECK ERECTION / LIFT | 3 | 2023-02-16 | 2023-02-20 | 2023-06-06 | 2023-06-08 | 94
ASSEMBLY & WELD ACCESS PLATFORM |  |  | 60 | 2022-11-24 | 2023-02-02 | 2023-02-28 | 2023-05-08 | 82
0 | FBST2200 | BH-03 - FIT-UP & TACK WELD - ACCESS PLATFORMS MAIN FRAME | 18 | 2022-11-24 | 2022-12-15 | 2023-02-28 | 2023-03-20 | 82
0 | FBST2210 | BH-03 - FIT-UP & TACK WELD - ACCESS PLATFORMS SECONDARY FRAME | 15 | 2022-12-08 | 2022-12-26 | 2023-03-14 | 2023-03-30 | 82
0 | FBST2220 | BH-03 - COMPLETE WELDING - ACCESS PLATFORMS | 18 | 2022-12-26 | 2023-01-16 | 2023-03-31 | 2023-04-20 | 82
0 | FBST2230 | BH-03 - ERECT & WELD - ACCESS PLATFORMS FLOOR PLATING | 15 | 2023-01-16 | 2023-02-02 | 2023-04-21 | 2023-05-08 | 82
0 | FBST2240 | BH-03 - ERECT & WELD - DECK LEGS AND BRACES (ACCESS PLATFORM & MEZZANINE DECK) | 15 | 2023-01-16 | 2023-02-02 | 2023-04-21 | 2023-05-08 | 82
ASSEMBLY & WELD WEATHER DECK |  |  | 101 | 2022-11-24 | 2023-03-22 | 2023-03-13 | 2023-07-06 | 92
0 | FBST2250 | BH-03 - FIT-UP & TACK WELD - WEATHER DECK MAIN FRAME | 21 | 2022-11-24 | 2022-12-19 | 2023-03-13 | 2023-04-05 | 93
0 | FBST2260 | BH-03 - FIT-UP & TACK WELD - WEATHER DECK FRAME - NODES | 21 | 2022-11-24 | 2022-12-19 | 2023-03-18 | 2023-04-11 | 98
0 | FBST2270 | BH-03 - FIT-UP & TACK WELD - WEATHER DECK SECONDARY FRAME | 21 | 2022-12-12 | 2023-01-05 | 2023-04-05 | 2023-04-28 | 98
0 | FBST2280 | BH-03 - COMPLETE WELDING - WEATHER DECK | 18 | 2023-01-02 | 2023-01-23 | 2023-04-26 | 2023-05-16 | 98
0 | FBST2290 | BH-03 - ERECT & WELD - WEATHER DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-02-01 | 2023-02-22 | 2023-05-17 | 2023-06-06 | 90
0 | FBST2300 | BH-03 - PREPARATION - WEATHER DECK ERECTION / LIFT | 3 | 2023-03-18 | 2023-03-22 | 2023-07-04 | 2023-07-06 | 92
ASSEMBLY & WELD HELI DECK |  |  | 102 | 2022-12-28 | 2023-04-26 | 2023-03-30 | 2023-07-26 | 79
0 | FBST2310 | BH-03 - FIT-UP & TACK WELD - HELI DECK MAIN FRAME | 24 | 2022-12-28 | 2023-01-25 | 2023-03-30 | 2023-04-26 | 79
0 | FBST2320 | BH-03 - FIT-UP & TACK WELD - HELI DECK MAIN FRAME - NODES | 24 | 2022-12-28 | 2023-01-25 | 2023-04-17 | 2023-05-13 | 94
0 | FBST2330 | BH-03 - FIT-UP & TACK WELD - HELI DECK SECONDARY FRAME | 24 | 2023-01-14 | 2023-02-11 | 2023-04-17 | 2023-05-13 | 79
0 | FBST2340 | BH-03 - COMPLETE WELDING - HELI DECK | 15 | 2023-02-11 | 2023-03-01 | 2023-05-15 | 2023-05-31 | 79
0 | FBST2350 | BH-03 - ERECT & WELD - HDK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-03-01 | 2023-03-22 | 2023-06-01 | 2023-06-21 | 79
0 | FBST2360 | BH-03 - INSTALL - SAFETY NET | 6 | 2023-04-15 | 2023-04-22 | 2023-07-17 | 2023-07-22 | 79
0 | FBST2370 | BH-03 - PREPARATION - HELI DECK ERECTION / LIFT | 3 | 2023-04-22 | 2023-04-26 | 2023-07-24 | 2023-07-26 | 79
ERECT - CELLAR DECK |  |  | 30 | 2023-02-02 | 2023-03-09 | 2023-05-19 | 2023-09-06 | 156
0 | FBST2380 | BH-03 - LIFT,INSTALL & WELD - CELLAR DECK | 6 | 2023-02-02 | 2023-02-09 | 2023-05-19 | 2023-05-25 | 91
0 | FBST2390 | BH-03 - ERECT & WELD - REMAINING DECK ELEVATIONS / BRACES (B/W CELLAR DK & MAIN DECK) | 24 | 2023-02-09 | 2023-03-09 | 2023-08-10 | 2023-09-06 | 156
ERECT - MAIN DECK |  |  | 6 | 2023-02-09 | 2023-02-16 | 2023-05-26 | 2023-06-01 | 91
0 | FBST2400 | BH-03 - LIFT,INSTALL & WELD - MAIN DECK | 6 | 2023-02-09 | 2023-02-16 | 2023-05-26 | 2023-06-01 | 91
ACCESS PLATFORM |  |  | 6 | 2023-02-27 | 2023-03-06 | 2023-06-02 | 2023-06-08 | 82
0 | FBST2410 | BH-03 - INSTALL & WELD - ACCESS PLATFORMS | 6 | 2023-02-27 | 2023-03-06 | 2023-06-02 | 2023-06-08 | 82
ERECT - MEZZANINE DECK |  |  | 15 | 2023-03-06 | 2023-03-23 | 2023-06-09 | 2023-09-06 | 144
0 | FBST2420 | BH-03 - LIFT,INSTALL & WELD - MEZZANINE DECK | 6 | 2023-03-06 | 2023-03-13 | 2023-06-09 | 2023-06-15 | 82
0 | FBST2430 | BH-03 - ERECT & WELD - VERTICAL LEGS (B/W MEZZANINE DECK & MAIN DK) | 12 | 2023-03-09 | 2023-03-23 | 2023-08-24 | 2023-09-06 | 144
ERECT WEATHER DECK |  |  | 91 | 2023-03-28 | 2023-07-12 | 2023-07-07 | 2023-10-11 | 79
0 | FBST2440 | BH-03 - LIFT,INSTALL & WELD - WEATHER DECK | 6 | 2023-03-28 | 2023-04-04 | 2023-07-07 | 2023-07-13 | 87
0 | FBST2450 | BH-03 - ERECT BALANCE BRACES AND COMPLETE BOX UP | 60 | 2023-05-03 | 2023-07-12 | 2023-08-03 | 2023-10-11 | 79
ERECT- HELI DECK |  |  | 6 | 2023-04-26 | 2023-05-03 | 2023-07-27 | 2023-08-02 | 79
0 | FBST2460 | BH-03 - LIFT,INSTALL & WELD - HELI DECK | 6 | 2023-04-26 | 2023-05-03 | 2023-07-27 | 2023-08-02 | 79
ERECT- HANDRAILS, LADDERS |  |  | 165 | 2022-12-07 | 2023-06-17 | 2023-03-14 | 2023-10-25 | 112
0 | FBST2480 | BH-03 - WELD - MAIN DECK HANDRAIL SOCKETS | 15 | 2022-12-07 | 2022-12-24 | 2023-03-14 | 2023-03-30 | 83
0 | FBST2470 | BH-03 - WELD - CELLAR DECK HANDRAIL SOCKETS | 15 | 2022-12-07 | 2022-12-24 | 2023-04-04 | 2023-04-20 | 101
0 | FBST2490 | BH-03 - WELD - MEZZANINE DECK HANDRAIL SOCKETS | 15 | 2022-12-15 | 2023-01-02 | 2023-04-25 | 2023-05-11 | 112
0 | FBST2500 | BH-03 - WELD - WEATHER HANDRAILS SOCKETS | 15 | 2023-01-05 | 2023-01-23 | 2023-05-20 | 2023-06-06 | 116
0 | FBST2510 | BH-03 - ERECT - CELLAR DECK HANDRAILS | 30 | 2023-02-27 | 2023-04-03 | 2023-07-25 | 2023-08-28 | 127
0 | FBST2520 | BH-03 - ERECT - MAIN DECK HANDRAILS | 30 | 2023-03-13 | 2023-04-17 | 2023-07-21 | 2023-08-24 | 112
0 | FBST2530 | BH-03 - ERECT - MEZZANINE DECK HANDRAILS | 30 | 2023-03-30 | 2023-05-04 | 2023-08-26 | 2023-09-29 | 128
0 | FBST2540 | BH-03 - ERECT - WEATHER DECK HANDRAILS | 30 | 2023-04-17 | 2023-05-22 | 2023-09-21 | 2023-10-25 | 135
0 | FBST2550 | BH-03 - ERECT & WELD - LADDERS & CAGES | 54 | 2023-04-15 | 2023-06-17 | 2023-08-12 | 2023-10-13 | 102
ERECT- GRATINGS |  |  | 120 | 2023-02-22 | 2023-07-12 | 2023-06-07 | 2023-10-25 | 91
0 | FBST2560 | BH-03 - TAILORING OF GRATINGS - CELLAR DECK | 21 | 2023-02-22 | 2023-03-18 | 2023-06-07 | 2023-06-30 | 90
0 | FBST2570 | BH-03 - TAILORING OF GRATINGS - MAIN DECK | 21 | 2023-03-08 | 2023-04-01 | 2023-06-21 | 2023-07-14 | 90
0 | FBST2580 | BH-03 - TAILORING OF GRATINGS - MEZZANINE DECK | 21 | 2023-03-15 | 2023-04-08 | 2023-06-28 | 2023-07-21 | 90
0 | FBST2590 | BH-03 - TAILORING OF GRATINGS - WEATHER DECK | 21 | 2023-03-22 | 2023-04-15 | 2023-07-05 | 2023-07-28 | 90
0 | FBST4020 | BH-03 - TAILORING OF GRATINGS - (ACCESS PLATFORM) | 21 | 2023-04-01 | 2023-04-26 | 2023-07-17 | 2023-08-09 | 91
0 | FBST2600 | BH-03 - INSTALL - GRATINGS (CELLAR DK) | 21 | 2023-05-17 | 2023-06-10 | 2023-10-02 | 2023-10-25 | 118
0 | FBST2630 | BH-03 - INSTALL - GRATINGS (MAIN DECK) | 30 | 2023-05-10 | 2023-06-14 | 2023-09-21 | 2023-10-25 | 115
0 | FBST2610 | BH-03 - INSTALL - GRATINGS MEZZANINE DECK | 30 | 2023-05-24 | 2023-06-28 | 2023-09-21 | 2023-10-25 | 103
0 | FBST4010 | BH-03 - INSTALL - GRATINGS (ACCESS PLATFORM) | 21 | 2023-06-14 | 2023-07-08 | 2023-10-02 | 2023-10-25 | 94
0 | FBST2620 | BH-03 - INSTALL - GRATINGS WEATHER DECK | 30 | 2023-06-07 | 2023-07-12 | 2023-09-21 | 2023-10-25 | 91
ERECT STAIRWAYS/STAIR TOWER |  |  | 60 | 2023-04-25 | 2023-07-04 | 2023-08-03 | 2023-10-18 | 92
0 | FBST2660 | BH-03 - ERECT & WELD - STAIRWAYS/STAIR TOWER (EAST SIDE) | 30 | 2023-05-09 | 2023-06-13 | 2023-09-14 | 2023-10-18 | 110
0 | FBST2650 | BH-03 - ERECT & WELD - STAIRWAYS/STAIR TOWER (NORTH SIDE) | 30 | 2023-05-23 | 2023-06-27 | 2023-09-07 | 2023-10-11 | 92
0 | FBST2640 | BH-03 - ERECT & WELD - OTHER BALANCE STAIRWAYS | 60 | 2023-04-25 | 2023-07-04 | 2023-08-03 | 2023-10-11 | 86
ERECT PIPE SUPPORTS |  |  | 107 | 2022-12-31 | 2023-05-05 | 2023-05-22 | 2023-08-21 | 93
0 | FBST2670 | BH-03 - INSTALL & WELD - PIPE SUPPORTS CELLAR DECK (Welded attachments to frame) | 18 | 2023-01-10 | 2023-01-31 | 2023-06-12 | 2023-07-01 | 131
0 | FBST2700 | BH-03 - INSTALL & WELD - PIPE SUPPORTS (WEATHER DECK) (Welded attachments to frame) | 24 | 2023-01-14 | 2023-02-11 | 2023-07-24 | 2023-08-19 | 163
0 | FBST2680 | BH-03 - INSTALL & WELD - PIPE SUPPORTS (MAIN DECK) (Welded attachments to frame) | 36 | 2022-12-31 | 2023-02-11 | 2023-05-22 | 2023-07-01 | 121
0 | FBST2690 | BH-03 - INSTALL & WELD - PIPE SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 24 | 2023-01-26 | 2023-02-23 | 2023-07-25 | 2023-08-21 | 154
0 | FBST2710 | BH-03 - NSTALL & WELD - BALANCE PIPE SUPPORTS (Other than Welded attachments to frame) | 70 | 2023-02-13 | 2023-05-05 | 2023-05-31 | 2023-08-19 | 92
ERECT EQPT SUOPPORTS |  |  | 100 | 2023-01-18 | 2023-05-15 | 2023-06-16 | 2023-08-26 | 90
0 | FBST2720 | BH-03 - INSTALL & WELD - EQUIPMENT SUPPORTS (MAIN DECK) (Welded attachments to frame) | 18 | 2023-01-18 | 2023-02-08 | 2023-06-16 | 2023-07-06 | 128
0 | FBST2740 | BH-03 - INSTALL & WELD - EQUIPMENT SUPPORTS (CELLAR DK) (Welded attachments to frame) | 18 | 2023-02-01 | 2023-02-22 | 2023-08-07 | 2023-08-26 | 160
0 | FBST2730 | BH-03 - INSTALL & WELD - EQUIPMENT SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 18 | 2023-02-09 | 2023-03-02 | 2023-06-16 | 2023-07-06 | 109
0 | FBST2750 | BH-03 - INSTALL & WELD - EQUIPMENT SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-02-23 | 2023-03-16 | 2023-07-28 | 2023-08-17 | 133
0 | FBST2770 | BH-03 - INSTALL & WELD - VENT SUPPORT STRUCTURE | 21 | 2023-04-20 | 2023-05-15 | 2023-07-13 | 2023-08-05 | 72
0 | FBST2760 | BH-03 - INSTALL & WELD - BALANCE EQUIPMENT SUPPORTS (Other than Welded attachments to frame) | 42 | 2023-03-27 | 2023-05-15 | 2023-06-19 | 2023-08-05 | 72
ERECT CABLE TRAYS SUPPORTS |  |  | 98 | 2023-02-01 | 2023-05-26 | 2023-06-23 | 2023-08-31 | 84
0 | FBST2780 | BH-03 - INSTALL & WELD - CABLE TRAY SUPPORTS (CELLAR DK) (Welded attachments to frame) | 15 | 2023-02-01 | 2023-02-18 | 2023-07-07 | 2023-07-24 | 134
0 | FBST2790 | BH-03 - INSTALL & WELD - CABLE TRAY SUPPORTS (MAIN DECK) (Welded attachments to frame) | 15 | 2023-02-08 | 2023-02-25 | 2023-08-01 | 2023-08-17 | 149
0 | FBST2800 | BH-03 - INSTALL & WELD - CABLE TRAY SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 21 | 2023-02-15 | 2023-03-11 | 2023-07-25 | 2023-08-17 | 137
0 | FBST2810 | BH-03 - INSTALL & WELD - CABLE TRAY SUPPORTS (WEATHER DK) (Welded attachments to frame) | 15 | 2023-03-09 | 2023-03-27 | 2023-08-01 | 2023-08-17 | 124
0 | FBST2820 | BH-03 - INSTALL & WELD - SECONDARY CABLE TRAY SUPPORTS | 60 | 2023-03-08 | 2023-05-17 | 2023-06-23 | 2023-08-31 | 92
0 | FBST2830 | BH-03 - INSTALL & WELD - BALANCE CABLE TRAY SUPPORTS (Other than Welded attachments to frame) | 60 | 2023-03-17 | 2023-05-26 | 2023-06-23 | 2023-08-31 | 84
ERECT OTHER E&I SUPPORTS |  |  | 51 | 2023-03-29 | 2023-05-27 | 2023-07-13 | 2023-08-31 | 83
0 | FBST2840 | BH-03 - INSTALL & WELD - OTHER E&I SUPPORTS (MAIN DECK) | 15 | 2023-03-29 | 2023-04-15 | 2023-07-24 | 2023-08-09 | 100
0 | FBST2860 | BH-03 - INSTALL & WELD - OTHER E&I SUPPORTS (CELLAR DK) | 15 | 2023-04-05 | 2023-04-22 | 2023-07-17 | 2023-08-02 | 88
0 | FBST2850 | BH-03 - INSTALL & WELD - OTHER E&I SUPPORTS (WEATHER DK) | 24 | 2023-04-05 | 2023-05-03 | 2023-07-13 | 2023-08-09 | 85
0 | FBST2880 | BH-03 - INSTALL & WELD - OTHER E&I SUPPORTS (MEZZANINE DECK) | 21 | 2023-04-12 | 2023-05-06 | 2023-07-21 | 2023-08-14 | 86
0 | FBST2870 | BH-03 - INSTALL & WELD - BALANCE E&I SUPPORTS (Other than Welded attachments to frame) | 42 | 2023-04-08 | 2023-05-27 | 2023-07-14 | 2023-08-31 | 83
FLOOR DRAINS |  |  | 51 | 2022-10-31 | 2022-12-29 | 2023-03-10 | 2023-06-06 | 137
0 | FBST2890 | BH-03 - INSTALL & WELD - FLOOR DRAINS (CELLAR DK) | 18 | 2022-10-31 | 2022-11-21 | 2023-03-31 | 2023-04-20 | 130
0 | FBST2900 | BH-03 - INSTALL & WELD - FLOOR DRAINS (MAIN DECK) | 18 | 2022-11-14 | 2022-12-05 | 2023-03-10 | 2023-03-30 | 100
0 | FBST2910 | BH-03 - INSTALL & WELD - FLOOR DRAINS (MEZZANINE DECK) | 18 | 2022-11-24 | 2022-12-15 | 2023-04-21 | 2023-05-11 | 127
0 | FBST2920 | BH-03 - INSTALL & WELD - FLOOR DRAINS (WEATHER DK) | 18 | 2022-12-08 | 2022-12-29 | 2023-05-17 | 2023-06-06 | 137
ERECT OTHER STRUCTURES |  |  | 198 | 2022-11-30 | 2023-07-19 | 2023-03-15 | 2023-10-20 | 81
0 | FBST2930 | BH-03 - INSTALL & WELD - AVAILABLE DECK PENETRATIONS | 60 | 2022-11-30 | 2023-02-08 | 2023-03-15 | 2023-05-23 | 90
0 | FBST2940 | BH-03 - INSTALL & WELD - STABBING GUIDES | 9 | 2023-03-10 | 2023-03-21 | 2023-06-22 | 2023-07-01 | 89
0 | FBST2960 | BH-03 - INSTALL & WELD - BALANCE DECK PENETRATIONS | 42 | 2023-02-09 | 2023-03-30 | 2023-06-12 | 2023-07-29 | 105
0 | FBST2950 | BH-03 - INSTALL & WELD - DECK PAD EYES | 28 | 2023-03-31 | 2023-05-03 | 2023-07-27 | 2023-08-28 | 101
0 | FBST2990 | BH-03 - INSTALL & WELD - FLARE BOOM | 21 | 2023-05-22 | 2023-06-15 | 2023-09-04 | 2023-09-27 | 90
0 | FBST2980 | BH-03 - INSTALL & WELD - HELIDECK DRAIN/GUTTER | 25 | 2023-05-17 | 2023-06-15 | 2023-08-30 | 2023-09-27 | 90
0 | FBST3010 | BH-03 - INSTALL & WELD - MONORAIL FRAMES | 60 | 2023-04-07 | 2023-06-16 | 2023-07-18 | 2023-09-25 | 87
0 | FBST3020 | BH-03 - INSTALL & WELD - DECK HATCHES | 60 | 2023-04-15 | 2023-06-24 | 2023-07-29 | 2023-10-06 | 90
0 | FBST3000 | BH-03 - INSTALL & WELD - PLATFORM IDENTIFICATION PANELS | 30 | 2023-06-10 | 2023-07-15 | 2023-09-16 | 2023-10-20 | 84
0 | FBST2970 | BH-03 - INSTALL & WELD - MISC STRUCTURAL ITEMS | 60 | 2023-05-10 | 2023-07-19 | 2023-08-10 | 2023-10-18 | 79
PUNCH LIST CLEARANCE- STRUCTURAL |  |  | 15 | 2023-07-08 | 2023-07-26 | 2023-10-09 | 2023-10-25 | 79
0 | FBST3030 | BH-03 - STRUCTURAL PUNCHLIST CLEARANCE | 15 | 2023-07-08 | 2023-07-26 | 2023-10-09 | 2023-10-25 | 79
PRESSURE VESSEL (FABRICATION & PAINTING) |  |  | 168 | 2022-11-18 | 2023-06-02 | 2023-02-13 | 2023-08-26 | 74
0 | FBPV1000 | BH-03 - FABRICATE - VENT/DRAIN DRUM | 150 | 2022-11-18 | 2023-05-12 | 2023-02-13 | 2023-08-05 | 74
0 | FBPV1010 | BH-03 - PAINT - VENT/DRAIN DRUM | 18 | 2023-05-12 | 2023-06-02 | 2023-08-07 | 2023-08-26 | 74
PIPING WORKS |  |  | 150 | 2023-02-06 | 2023-07-31 | 2023-04-28 | 2023-11-02 | 82
PIPING PRE-FABRICATION |  |  | 75 | 2023-02-06 | 2023-05-04 | 2023-04-28 | 2023-08-15 | 89
0 | FBPI1010 | BH-03 - FABRICATE - CU-NI PIPING SPOOLS | 30 | 2023-02-20 | 2023-03-27 | 2023-05-23 | 2023-06-26 | 79
0 | FBPI1000 | BH-03 - FABRICATE - CS/ LTCS/ CLADDED PIPING SPOOLS | 56 | 2023-02-06 | 2023-04-12 | 2023-04-28 | 2023-07-01 | 70
0 | FBPI1020 | BH-03 - FABRICATE - SS/DUPLEX PIPING SPOOLS | 30 | 2023-03-20 | 2023-04-24 | 2023-06-13 | 2023-07-17 | 73
0 | FBPI1030 | BH-03 - FABRICATE - INCONEL PIPING SPOOLS | 42 | 2023-03-16 | 2023-05-04 | 2023-06-28 | 2023-08-15 | 89
VALVE LEAK TESTING |  |  | 36 | 2023-03-15 | 2023-04-26 | 2023-07-05 | 2023-08-15 | 96
0 | FBPI1040 | BH-03 - VALVE LEAK TESTING | 36 | 2023-03-15 | 2023-04-26 | 2023-07-05 | 2023-08-15 | 96
PIPING ERECTION/HYDROTESTING/INSULATION |  |  | 94 | 2023-04-12 | 2023-07-31 | 2023-07-03 | 2023-11-02 | 82
PIPING ERECTION |  |  | 63 | 2023-04-12 | 2023-06-24 | 2023-07-03 | 2023-09-20 | 76
0 | FBPI2000 | BH-03 - ERECT - CS/ LTCS/ CLADDED SPOOLS | 54 | 2023-04-12 | 2023-06-14 | 2023-07-03 | 2023-09-02 | 70
0 | FBPI2010 | BH-03 - ERECT - INCONEL SPOOLS | 49 | 2023-04-28 | 2023-06-24 | 2023-07-19 | 2023-09-13 | 70
0 | FBPI2020 | BH-03 - ERECT - CU-NI SPOOLS | 35 | 2023-05-15 | 2023-06-24 | 2023-08-11 | 2023-09-20 | 76
0 | FBPI2030 | BH-03 - ERECT - SS/DUPLEX SPOOLS | 35 | 2023-05-15 | 2023-06-24 | 2023-08-04 | 2023-09-13 | 70
HYDROTESTING & REINSTATEMENT |  |  | 48 | 2023-05-24 | 2023-07-19 | 2023-08-21 | 2023-10-30 | 89
HYDROTESTING |  |  | 36 | 2023-05-24 | 2023-07-05 | 2023-08-21 | 2023-10-13 | 87
0 | FBPI2040 | BH-03 - HYDROTESTING AND RE-INSTATEMENT - OIL PRODUCTION SYSTEM | 18 | 2023-05-24 | 2023-06-14 | 2023-08-21 | 2023-09-09 | 76
0 | FBPI2050 | BH-03 - HYDROTESTING AND RE-INSTATEMENT - WATER INJECTION SYSTEM | 18 | 2023-06-07 | 2023-06-28 | 2023-08-28 | 2023-09-16 | 70
0 | FBPI2060 | BH-03 - HYDROTESTING AND RE-INSTATEMENT - CLOSED DRAIN SYSTEM | 18 | 2023-06-10 | 2023-07-01 | 2023-08-31 | 2023-09-20 | 70
0 | FBPI2070 | BH-03 - HYDROTESTING AND RE-INSTATEMENT - OPEN DRAIN SYSTEM | 18 | 2023-06-10 | 2023-07-01 | 2023-09-07 | 2023-09-27 | 76
0 | FBPI2090 | BH-03 - HYDROTESTING AND RE-INSTATEMENT - VENT SYSTEM | 12 | 2023-06-21 | 2023-07-05 | 2023-09-18 | 2023-09-30 | 76
0 | FBPI2080 | BH-03 - HYDROTESTING AND RE-INSTATEMENT - CORROSION INHABITOR INJECTION SYSTEM | 18 | 2023-06-14 | 2023-07-05 | 2023-09-23 | 2023-10-13 | 87
INSULATION |  |  | 45 | 2023-05-27 | 2023-07-19 | 2023-09-08 | 2023-10-30 | 89
0 | FBPI2100 | BH-03 - PIPING INSULATION WORK | 45 | 2023-05-27 | 2023-07-19 | 2023-09-08 | 2023-10-30 | 89
PIPING SYSTEMS MECHANICAL COMPLETION |  |  | 25 | 2023-07-01 | 2023-07-31 | 2023-10-04 | 2023-10-27 | 77
0 | FBPI2140 | BH-03 - MECHANICAL COMPLETION - CLOSED/OPEN DRAIN SYSTEM | 10 | 2023-07-01 | 2023-07-13 | 2023-10-14 | 2023-10-25 | 90
0 | FBPI2120 | BH-03 - MECHANICAL COMPLETION - CHEMICAL INJECTION SYSTEM | 10 | 2023-07-05 | 2023-07-17 | 2023-10-17 | 2023-10-27 | 89
0 | FBPI2150 | BH-03 - MECHANICAL COMPLETION - VENT SYSTEM | 10 | 2023-07-07 | 2023-07-19 | 2023-10-04 | 2023-10-14 | 76
0 | FBPI2110 | BH-03 - MECHANICAL COMPLETION - PRODUCTION SYSTEM | 10 | 2023-07-19 | 2023-07-31 | 2023-10-16 | 2023-10-26 | 76
0 | FBPI2130 | BH-03 - MECHANICAL COMPLETION - WATER INJECTION SYSTEM | 10 | 2023-07-19 | 2023-07-31 | 2023-10-16 | 2023-10-26 | 76
PUNCHLIST CLEARANCE - PIPING |  |  | 40 | 2023-05-26 | 2023-07-12 | 2023-09-18 | 2023-11-02 | 98
0 | FBPI2160 | BH-03 - PUNCHLIST CLEARANCE - PIPING | 40 | 2023-05-26 | 2023-07-12 | 2023-09-18 | 2023-11-02 | 98
PIPING PWHT |  |  | 110 | 2023-02-13 | 2023-06-21 | 2023-05-25 | 2023-09-20 | 79
0 | FBPI2170 | BH-03 - PWHT - FABRICATED SPOOLS | 72 | 2023-02-13 | 2023-05-08 | 2023-05-25 | 2023-08-16 | 87
0 | FBPI2180 | BH-03 - PWHT - ERECTED SPOOLS | 72 | 2023-03-29 | 2023-06-21 | 2023-06-29 | 2023-09-20 | 79
MECHANICAL EQUIPMENT |  |  | 83 | 2023-03-28 | 2023-07-03 | 2023-07-07 | 2023-10-23 | 97
CELLAR DECK |  |  | 22 | 2023-05-15 | 2023-06-09 | 2023-08-21 | 2023-09-02 | 74
0 | FBME2010 | BH-03 - INSTALL - DRAIN SUMP PUMP | 6 | 2023-05-15 | 2023-05-22 | 2023-08-21 | 2023-08-26 | 84
0 | FBME2000 | BH-03 - INSTALL - VENT DRAIN TANK | 6 | 2023-06-02 | 2023-06-09 | 2023-08-28 | 2023-09-02 | 74
MAIN DECK |  |  | 83 | 2023-03-28 | 2023-07-03 | 2023-07-07 | 2023-10-23 | 97
0 | FBME2030 | BH-03 - INSTALL - PIG LAUNCHER/ RECEIVER (730-L-001) | 12 | 2023-03-28 | 2023-04-11 | 2023-07-07 | 2023-07-20 | 87
0 | FBME2050 | BH-03 - INSTALL - MONORAIL/HOIST | 70 | 2023-04-12 | 2023-07-03 | 2023-08-03 | 2023-10-23 | 97
WEATHER DECK |  |  | 70 | 2023-04-12 | 2023-07-03 | 2023-08-03 | 2023-10-23 | 97
0 | FBME2060 | BH-03 - INSTALL - MONORAIL/HOIST | 70 | 2023-04-12 | 2023-07-03 | 2023-08-03 | 2023-10-23 | 97
ELECTRICAL |  |  | 140 | 2023-02-18 | 2023-08-01 | 2023-06-07 | 2023-11-16 | 93
GENERAL |  |  | 140 | 2023-02-18 | 2023-08-01 | 2023-06-07 | 2023-11-16 | 93
0 | FBEL1052 | BH-03 - MATERIAL INSPECTION & PRESERVATION | 140 | 2023-02-18 | 2023-08-01 | 2023-06-07 | 2023-11-16 | 93
CABLE TRAYS |  |  | 48 | 2023-04-14 | 2023-06-09 | 2023-07-21 | 2023-09-14 | 84
0 | FBEL1050 | BH-03 - INSTALL - ELECTRICAL MAIN CABLE TRAYS | 42 | 2023-04-14 | 2023-06-02 | 2023-07-21 | 2023-09-07 | 84
0 | FBEL1040 | BH-03 - INSTALL - SECONDARY CABLE TRAYS | 42 | 2023-04-21 | 2023-06-09 | 2023-07-28 | 2023-09-14 | 84
CABLE PULLING, G&T & TESTING |  |  | 57 | 2023-05-01 | 2023-07-06 | 2023-08-04 | 2023-10-09 | 82
0 | FBEL1060 | BH-03 - PULL - ELECTRICAL CABLES | 42 | 2023-05-01 | 2023-06-19 | 2023-08-04 | 2023-09-21 | 82
0 | FBEL1070 | BH-03 - GLAND & TERMINATE - ELECTRICAL CABLES | 42 | 2023-05-15 | 2023-07-03 | 2023-08-18 | 2023-10-05 | 82
0 | FBEL1080 | BH-03 - IR & CONTINUITY CHECK - ELECTRICAL CABLES | 36 | 2023-05-25 | 2023-07-06 | 2023-08-29 | 2023-10-09 | 82
FITTINGS/JB's & SOCKETS |  |  | 18 | 2023-05-03 | 2023-05-24 | 2023-08-11 | 2023-09-14 | 98
0 | FBEL1100 | BH-03 - INSTALL - INSTALL EARTHING | 12 | 2023-05-03 | 2023-05-17 | 2023-08-11 | 2023-08-24 | 86
0 | FBEL1090 | BH-03 - INSTALL LIGHT FITTINGS/JBs/SOCKETS | 12 | 2023-05-03 | 2023-05-17 | 2023-08-11 | 2023-08-24 | 86
0 | FBEL1110 | BH-03 - INSTALL - SMALL POWER / LIGHTING DB'S | 12 | 2023-05-10 | 2023-05-24 | 2023-09-01 | 2023-09-14 | 98
ELECTRICAL EQUIPMENTS |  |  | 62 | 2023-03-20 | 2023-05-31 | 2023-06-23 | 2023-09-11 | 89
0 | FBEL1130 | BH-03 - INSTALL - LV DISTRIBUTION BOARD INSTALLATION - MEZZ DECK | 18 | 2023-03-20 | 2023-04-10 | 2023-06-23 | 2023-07-13 | 82
0 | FBEL1170 | BH-03 - INSTALL - TUTU BOX- CELLAR DECK | 12 | 2023-03-31 | 2023-04-14 | 2023-08-17 | 2023-08-30 | 119
0 | FBEL1160 | BH-03 - INSTALL - TRANSFRMER INSTALLLATION - WEATHER DECK | 6 | 2023-04-08 | 2023-04-15 | 2023-09-05 | 2023-09-11 | 128
0 | FBEL1180 | BH-03 - INSTALL - 415V SWITCHBOARD - MEZZ DECK | 18 | 2023-04-10 | 2023-05-01 | 2023-07-14 | 2023-08-03 | 82
0 | FBEL1120 | BH-03 - INSTALL - BIRD DETTERENT SYSTEM - MEZZ DECK | 12 | 2023-04-19 | 2023-05-03 | 2023-08-15 | 2023-08-28 | 101
0 | FBEL1150 | BH-03 - INSTALL - AC UPS SYSTEM - MEZZ DECK | 18 | 2023-04-19 | 2023-05-10 | 2023-08-21 | 2023-09-09 | 106
0 | FBEL1140 | BH-03 - INSTALL - NAVIGATION AID SYSTEM - WEATHER/ CELLAR/ MEZZ DECK | 24 | 2023-04-17 | 2023-05-15 | 2023-08-01 | 2023-08-28 | 91
0 | FBEL1190 | BH-03 - INSTALL - 6.6 Kv RMU INSTALLATION - WEATHER DECK | 18 | 2023-05-10 | 2023-05-31 | 2023-08-22 | 2023-09-11 | 89
ELECTRICAL SYSTEMS MECHANICAL COMPLETION |  |  | 21 | 2023-06-19 | 2023-07-13 | 2023-09-22 | 2023-10-30 | 94
0 | FBEL1200 | BH-03 - MECHANICAL COMPLETION - POWER SYSTEM | 18 | 2023-06-19 | 2023-07-10 | 2023-09-22 | 2023-10-12 | 82
0 | FBEL1210 | BH-03 - MECHANICAL COMPLETION - LIGHTING SYSTEM | 18 | 2023-06-22 | 2023-07-13 | 2023-10-10 | 2023-10-30 | 94
PUNCHLIST CLEARANCE - ELECTRICAL |  |  | 24 | 2023-06-19 | 2023-07-17 | 2023-10-06 | 2023-11-02 | 94
0 | FBEL1220 | BH-03 - PUNCHLIST CLEARANCE - ELECTRICAL | 24 | 2023-06-19 | 2023-07-17 | 2023-10-06 | 2023-11-02 | 94
INSTRUMENTATION/TELECOM |  |  | 92 | 2023-04-11 | 2023-07-27 | 2023-08-07 | 2023-11-02 | 85
CABLE TRAYS & CABLE PULLING |  |  | 66 | 2023-05-08 | 2023-07-24 | 2023-08-14 | 2023-10-21 | 78
0 | FBIN1010 | BH-03 - PULL - INSTRUMENT CABLES | 42 | 2023-05-08 | 2023-06-26 | 2023-08-14 | 2023-09-30 | 84
0 | FBIN1020 | BH-03 - GLAND/TERMINATE - INSTRUMENT CABLES | 42 | 2023-06-01 | 2023-07-20 | 2023-08-31 | 2023-10-18 | 78
0 | FBIN1030 | BH-03 - IR & CONTINUITY CHECK - INSTRUMENT CABLES | 36 | 2023-06-12 | 2023-07-24 | 2023-09-11 | 2023-10-21 | 78
INSTRUMENTS INSTALLATION |  |  | 76 | 2023-04-11 | 2023-07-08 | 2023-08-07 | 2023-10-14 | 85
0 | FBIN1040 | BH-03 - INSTALL - F&G DETECTORS | 24 | 2023-04-11 | 2023-05-09 | 2023-08-24 | 2023-09-20 | 116
0 | FBIN1180 | BH-03 - INTRUMENT CALIBIRATION | 42 | 2023-04-17 | 2023-06-05 | 2023-08-07 | 2023-09-23 | 96
0 | FBIN1050 | BH-03 - INSTALL - FIELD INSTRUMENTS | 42 | 2023-05-20 | 2023-07-08 | 2023-08-28 | 2023-10-14 | 85
PANELS & JB's |  |  | 42 | 2023-05-03 | 2023-06-21 | 2023-08-10 | 2023-09-27 | 85
0 | FBIN1060 | BH-03 - INSTALL - JUNCTION BOXES/ MARSHALING BOXES / SPLITTER BOXES | 42 | 2023-05-03 | 2023-06-21 | 2023-08-10 | 2023-09-27 | 85
INSTRUMENT EQUIPMENTS |  |  | 73 | 2023-04-18 | 2023-07-12 | 2023-08-10 | 2023-10-18 | 85
0 | FBIN1170 | BH-03 - INSTALL TELECOM EQUIPMENT - MAIN / MEZZ DECK | 18 | 2023-04-18 | 2023-05-09 | 2023-08-10 | 2023-08-30 | 98
0 | FBIN1200 | BH-03 - INSTALL IRCD SKID | 9 | 2023-05-09 | 2023-05-19 | 2023-08-21 | 2023-08-30 | 89
0 | FBIN1110 | BH-03 - INSTALL ICSS SYSTEM - MEZZ DECK | 9 | 2023-05-24 | 2023-06-03 | 2023-08-23 | 2023-09-01 | 78
0 | FBIN1080 | BH-03 - INSTALL HIPPS SYSTEM - MAIN DECK | 12 | 2023-05-29 | 2023-06-10 | 2023-09-02 | 2023-09-15 | 83
0 | FBIN1070 | BH-03 - INSTALL WELLHEAD CONTROL PANEL - MEZZ DECK | 12 | 2023-06-06 | 2023-06-20 | 2023-09-07 | 2023-09-20 | 80
0 | FBIN1100 | BH-03 - INSTALL FLOW METERS - MAIN / MEZZ DECK | 24 | 2023-06-10 | 2023-07-08 | 2023-09-21 | 2023-10-18 | 88
0 | FBIN1090 | BH-03 - INSTALL INSTRUMENT VALVES - MAIN/ MEZZ/ CELLAR DECK | 24 | 2023-06-14 | 2023-07-12 | 2023-09-16 | 2023-10-13 | 81
INSTRUMENT TUBING & INCONEL PIPING |  |  | 45 | 2023-05-31 | 2023-07-22 | 2023-09-08 | 2023-10-30 | 86
0 | FBIN1190 | BH-03 - INSTALL - INSTRUMENT PIPING | 36 | 2023-05-31 | 2023-07-12 | 2023-09-12 | 2023-10-23 | 89
0 | FBIN1120 | BH-03 - INSTALL - INSTRUMENT TUBING | 42 | 2023-05-31 | 2023-07-19 | 2023-09-08 | 2023-10-26 | 86
0 | FBIN1130 | BH-03 - PRESSURE TEST - INSTRUMENT TUBING | 24 | 2023-06-24 | 2023-07-22 | 2023-10-03 | 2023-10-30 | 86
INSTRUMENT/TELECOM SYSTEMS MECHANICAL COMPLETION |  |  | 24 | 2023-06-29 | 2023-07-27 | 2023-10-05 | 2023-10-25 | 78
0 | FBIN1150 | BH-03 - MECHANICAL COMPLETION - TELECOM SYSTEM | 12 | 2023-06-29 | 2023-07-13 | 2023-10-05 | 2023-10-18 | 84
0 | FBIN1140 | BH-03 - MECHANICAL COMPLETION - CONTROL SYSTEM | 18 | 2023-07-06 | 2023-07-27 | 2023-10-05 | 2023-10-25 | 78
PUNCHLIST CLEARANCE - INSTRUMENT |  |  | 20 | 2023-07-04 | 2023-07-27 | 2023-10-11 | 2023-11-02 | 85
0 | FBIN1160 | BH-03 - PUNCHLIST CLEARANCE - INSTRUMENTATION | 20 | 2023-07-04 | 2023-07-27 | 2023-10-11 | 2023-11-02 | 85
SAFETY |  |  | 20 | 2023-06-28 | 2023-07-21 | 2023-10-07 | 2023-10-30 | 87
0 | FBSA1010 | BH-03 - INSTALLATION OF SAFETY SIGN | 15 | 2023-07-04 | 2023-07-21 | 2023-10-13 | 2023-10-30 | 87
0 | FBSA1000 | BH-03 - INSTALLATION OF SAFETY EQUIPMENT | 20 | 2023-06-28 | 2023-07-21 | 2023-10-07 | 2023-10-30 | 87
PAINTING |  |  | 252 | 2022-10-17 | 2023-08-07 | 2023-02-10 | 2023-11-06 | 79
BLAST/PAINT- MAIN STRUCTURE |  |  | 155 | 2022-10-17 | 2023-04-15 | 2023-02-10 | 2023-07-15 | 79
BLAST/PAINT- CELLAR DECK |  |  | 90 | 2022-10-17 | 2023-01-30 | 2023-03-03 | 2023-05-15 | 91
0 | FBSTPN1000 | BH-03 - BLAST/PAINT - DECK BRACES (BTWN CELLAR & MAIN DECK) | 24 | 2022-10-17 | 2022-11-14 | 2023-03-03 | 2023-03-30 | 118
0 | FBSTPN1010 | BH-03 - BLAST/PAINT - DECK LEGS (BTWN CELLAR, & MAIN DECK) | 15 | 2022-11-21 | 2022-12-08 | 2023-03-14 | 2023-03-30 | 97
0 | FBSTPN1020 | BH-03 - BLAST/PAINT - CELLAR DECK | 21 | 2023-01-05 | 2023-01-30 | 2023-04-21 | 2023-05-15 | 91
BLAST/PAINT- MAIN DECK |  |  | 72 | 2022-11-03 | 2023-01-26 | 2023-02-10 | 2023-04-24 | 76
0 | FBSTPN1030 | BH-03 - BLAST/PAINT - DECK BRACES (BTWN MAIN DECK & MEZZANINE DECK) | 24 | 2022-11-03 | 2022-12-01 | 2023-02-10 | 2023-03-09 | 85
0 | FBSTPN1040 | BH-03 - BLAST/PAINT - DECK LEGS (BTWN MAIN DECK & MEZZANINE DECK) | 15 | 2022-11-14 | 2022-12-01 | 2023-02-21 | 2023-03-09 | 85
0 | FBSTPN1050 | BH-03 - BLAST/PAINT - MAIN DECK | 21 | 2023-01-02 | 2023-01-26 | 2023-03-31 | 2023-04-24 | 76
BLAST/PAINT- MEZZANINE DECK |  |  | 78 | 2022-11-17 | 2023-02-16 | 2023-03-24 | 2023-06-05 | 94
0 | FBSTPN1070 | BH-03 - BLAST/PAINT - DECK LEGS (BTWN MEZZANINE DECK & WEATHER DK) | 15 | 2022-11-21 | 2022-12-08 | 2023-04-04 | 2023-04-20 | 115
0 | FBSTPN1060 | BH-03 - BLAST/PAINT - DECK BRACES (BTWN MEZZANINE DECK & WEATHER DK) | 24 | 2022-11-17 | 2022-12-15 | 2023-03-24 | 2023-04-20 | 109
0 | FBSTPN1080 | BH-03 - BLAST/PAINT - MEZZANINE DECK | 21 | 2023-01-23 | 2023-02-16 | 2023-05-12 | 2023-06-05 | 94
BLAST/PAINT- ACCESS PLATFORM |  |  | 21 | 2023-02-02 | 2023-02-27 | 2023-05-09 | 2023-06-01 | 82
0 | FBSTPN1090 | BH-03 - BLAST/PAINT - ACCESS PLATFORMS | 21 | 2023-02-02 | 2023-02-27 | 2023-05-09 | 2023-06-01 | 82
BLAST/PAINT-WEATHE DECK |  |  | 21 | 2023-02-22 | 2023-03-18 | 2023-06-09 | 2023-07-03 | 92
0 | FBSTPN1100 | BH-03 - BLAST/PAINT - WEATHER DECK | 21 | 2023-02-22 | 2023-03-18 | 2023-06-09 | 2023-07-03 | 92
BLAST/PAINT- HELI DECK |  |  | 21 | 2023-03-22 | 2023-04-15 | 2023-06-22 | 2023-07-15 | 79
0 | FBSTPN1110 | BH-03 - BLAST/PAINT - HELI DECK | 21 | 2023-03-22 | 2023-04-15 | 2023-06-22 | 2023-07-15 | 79
BLAST/PAINT- OTHER STRUCT/ACCESSORIES |  |  | 174 | 2023-01-16 | 2023-08-07 | 2023-05-10 | 2023-11-06 | 79
GALVANIZE/PAINT - HANDRAILS/LADDERS |  |  | 96 | 2023-01-16 | 2023-05-08 | 2023-05-26 | 2023-09-22 | 119
0 | FBSTPN1120 | BH-03 - GALVANIZE - HANDRAILS CELLAR DECK | 18 | 2023-01-16 | 2023-02-06 | 2023-05-26 | 2023-06-15 | 112
0 | FBSTPN1130 | BH-03 - GALVANIZE - HANDRAILS MAIN DECK | 18 | 2023-01-30 | 2023-02-20 | 2023-06-09 | 2023-06-29 | 112
0 | FBSTPN1140 | BH-03 - PAINT - HANDRAILS CELLAR DECK | 18 | 2023-02-06 | 2023-02-27 | 2023-07-04 | 2023-07-24 | 127
0 | FBSTPN1160 | BH-03 - GALVANIZE - HANDRAILS (MEZZANINE DECK) | 18 | 2023-02-10 | 2023-03-03 | 2023-07-15 | 2023-08-04 | 133
0 | FBSTPN1170 | BH-03 - PAINT - HANDRAILS MAIN DECK | 18 | 2023-02-20 | 2023-03-13 | 2023-06-30 | 2023-07-20 | 112
0 | FBSTPN1180 | BH-03 - GALVANIZE - HANDRAILS (WEATHER DECK) | 22 | 2023-02-24 | 2023-03-22 | 2023-08-05 | 2023-08-30 | 139
0 | FBSTPN1190 | BH-03 - PAINT - HANDRAILS (MEZZANINE DECK) | 18 | 2023-03-03 | 2023-03-24 | 2023-08-05 | 2023-08-25 | 133
0 | FBSTPN1200 | BH-03 - PAINT - HANDRAILS (WEATHER DECK) | 18 | 2023-03-22 | 2023-04-12 | 2023-08-31 | 2023-09-20 | 139
0 | FBSTPN1150 | BH-03 - BLAST/PAINT - LADDERS & CAGES | 60 | 2023-02-27 | 2023-05-08 | 2023-07-15 | 2023-09-22 | 119
BLAST/PAINT - STAIRWAYS |  |  | 72 | 2023-03-28 | 2023-06-20 | 2023-08-10 | 2023-09-27 | 86
EAST SIDE |  |  | 36 | 2023-03-28 | 2023-05-09 | 2023-08-24 | 2023-09-13 | 110
0 | FBSTPN1210 | BH-03 - BLAST/PAINT - CELLAR DECK TO JACKET WALKWAY (EAST SIDE) | 18 | 2023-03-28 | 2023-04-18 | 2023-08-24 | 2023-09-13 | 128
0 | FBSTPN1220 | BH-03 - BLAST/PAINT - MAIN DECK TO CELLAR DECK (EAST SIDE) | 18 | 2023-04-04 | 2023-04-25 | 2023-08-24 | 2023-09-13 | 122
0 | FBSTPN1230 | BH-03 - BLAST/PAINT - MEZZANINE DECK TO MAIN DECK (EAST SIDE) | 18 | 2023-04-11 | 2023-05-02 | 2023-08-24 | 2023-09-13 | 116
0 | FBSTPN1240 | BH-03 - BLAST/PAINT - MAIN DECK TO MEZZANINE DECK (EAST SIDE) | 18 | 2023-04-18 | 2023-05-09 | 2023-08-24 | 2023-09-13 | 110
NORTH SIDE |  |  | 39 | 2023-04-07 | 2023-05-23 | 2023-08-17 | 2023-09-06 | 92
0 | FBSTPN1250 | BH-03 - BLAST/PAINT - MONKEY LADDER FROM MAIN. DECK TO CELLAR DECK (NORTH SIDE) | 18 | 2023-04-07 | 2023-04-28 | 2023-08-17 | 2023-09-06 | 113
0 | FBSTPN1260 | BH-03 - BLAST/PAINT - MONKEY LADDER FROM MEZZANINE DECK TO MAIN DECK (NORTH SIDE) | 18 | 2023-04-21 | 2023-05-12 | 2023-08-17 | 2023-09-06 | 101
0 | FBSTPN1270 | BH-03 - BLAST/PAINT - MONKEY LADDER FROM MAIN DECK TO MEZZANINE DECK (NORTH SIDE) | 18 | 2023-05-02 | 2023-05-23 | 2023-08-17 | 2023-09-06 | 92
OTHER MISCELLENEOUS |  |  | 42 | 2023-05-02 | 2023-06-20 | 2023-08-10 | 2023-09-27 | 86
0 | FBSTPN1280 | BH-03 - BLAST/PAINT - STAIRWAYS (OTHER MISC.) | 42 | 2023-05-02 | 2023-06-20 | 2023-08-10 | 2023-09-27 | 86
BLAST/PAINT - PIPE SUPPORTS |  |  | 60 | 2023-01-23 | 2023-04-03 | 2023-05-10 | 2023-07-18 | 92
0 | FBSTPN2000 | BH-03 - BLAST/PAINT - BALANCE PIPE SUPPORTS | 60 | 2023-01-23 | 2023-04-03 | 2023-05-10 | 2023-07-18 | 92
BLAST/PAINTING - PIPING |  |  | 63 | 2023-02-27 | 2023-05-11 | 2023-06-19 | 2023-08-22 | 89
0 | FBPIPN1010 | BH-03 - BLAST/PAINT - CU-NI/ INCONEL PIPING SPOOLS | 42 | 2023-03-06 | 2023-04-24 | 2023-06-29 | 2023-08-16 | 99
0 | FBPIPN1020 | BH-03 - BLAST/PAINT - CS/LTCS / CLADDED PIPING SPOOLS | 56 | 2023-02-27 | 2023-05-03 | 2023-06-19 | 2023-08-22 | 96
0 | FBPIPN1030 | BH-03 - BLAST/PAINT - SS PIPING SPOOLS | 30 | 2023-04-06 | 2023-05-11 | 2023-06-30 | 2023-08-03 | 73
BLAST/PAINT - EQUIPMENT SUPPORTS |  |  | 42 | 2023-03-20 | 2023-05-08 | 2023-06-13 | 2023-07-31 | 73
0 | FBSTPN2020 | BH-03 - BLAST/PAINT - VENT SUPPORT STRUCTURE | 24 | 2023-03-23 | 2023-04-20 | 2023-06-15 | 2023-07-12 | 72
0 | FBSTPN2010 | BH-03 - BLAST/PAINT - BALANCE EQUIPMENT SUPPORTS | 42 | 2023-03-20 | 2023-05-08 | 2023-06-13 | 2023-07-31 | 73
BLAST/PAINT - E&I SUPPORTS |  |  | 56 | 2023-03-01 | 2023-05-05 | 2023-06-07 | 2023-08-10 | 84
0 | FBSTPN2040 | BH-03 - BLAST/PAINT - SECONDARY CABLE TRAY SUPPORTS | 42 | 2023-03-01 | 2023-04-19 | 2023-06-16 | 2023-08-03 | 92
0 | FBSTPN2030 | BH-03 - BLAST/PAINT - BALANCE MAIN CABLE TRAY SUPPORTS | 56 | 2023-03-01 | 2023-05-05 | 2023-06-07 | 2023-08-10 | 84
BLAST/PAINT - OTHER SUPPORTS |  |  | 75 | 2023-02-22 | 2023-05-20 | 2023-06-12 | 2023-08-24 | 83
0 | FBSTPN2050 | BH-03 - BLAST/PAINT - OTHER E&I SUPPORTS MAIN DECK | 30 | 2023-02-22 | 2023-03-29 | 2023-06-19 | 2023-07-22 | 100
0 | FBSTPN2060 | BH-03 - BLAST/PAINT - OTHER E&I SUPPORTS (CELLAR DDK) | 30 | 2023-03-01 | 2023-04-05 | 2023-06-12 | 2023-07-15 | 88
0 | FBSTPN2070 | BH-03 - BLAST/PAINT - OTHER E&I SUPPORTS (MEZZANINE DK) | 30 | 2023-03-08 | 2023-04-12 | 2023-06-16 | 2023-07-20 | 86
0 | FBSTPN2080 | BH-03 - BLAST/PAINT - OTHER E&I SUPPORTS (WEATHER MDK) | 30 | 2023-03-15 | 2023-04-19 | 2023-06-22 | 2023-07-26 | 85
0 | FBSTPN2090 | BH-03 - BLAST/PAINT - BALANCE OTHER E&I SUPPORTS | 56 | 2023-03-16 | 2023-05-20 | 2023-06-21 | 2023-08-24 | 83
BLAST/PAINT - OTHER STRUCTURES |  |  | 117 | 2023-02-11 | 2023-06-28 | 2023-06-08 | 2023-09-27 | 79
0 | FBSTPN2120 | BH-03 - BLAST/PAINT - STABBING GUIDES | 12 | 2023-02-24 | 2023-03-10 | 2023-06-08 | 2023-06-21 | 89
0 | FBSTPN2110 | BH-03 - BLAST/PAINT - DECK PAD EYES | 24 | 2023-02-15 | 2023-03-15 | 2023-06-15 | 2023-07-12 | 103
0 | FBSTPN2100 | BH-03 - BLAST/PAINT - MONORAILS FRAME | 60 | 2023-02-11 | 2023-04-22 | 2023-06-20 | 2023-08-28 | 110
0 | FBSTPN2150 | BH-03 - BLAST/PAINT - FLARE BOOM | 18 | 2023-04-08 | 2023-04-29 | 2023-08-14 | 2023-09-02 | 109
0 | FBSTPN2130 | BH-03 - BLAST/PAINT - DECK HATCHES | 30 | 2023-03-29 | 2023-05-03 | 2023-08-12 | 2023-09-15 | 117
0 | FBSTPN2160 | BH-03 - BLAST/PAINT - PLATFORM IDENTIFICATION PANELS | 18 | 2023-05-20 | 2023-06-10 | 2023-08-26 | 2023-09-15 | 84
0 | FBSTPN2170 | BH-03 - BLAST/PAINT - GRATINGS | 42 | 2023-04-26 | 2023-06-14 | 2023-08-10 | 2023-09-27 | 91
0 | FBSTPN2140 | BH-03 - BLAST/PAINT - MISCELLANEOUS STRUCTRUAL ITEMS | 60 | 2023-04-19 | 2023-06-28 | 2023-07-20 | 2023-09-27 | 79
FINAL TOUCH-UP PAINTING |  |  | 74 | 2023-05-12 | 2023-08-07 | 2023-08-22 | 2023-11-06 | 79
0 | FBSTPN2180 | BH-03 - FIRE PROOFING ON DECK STRUCTURE | 60 | 2023-05-12 | 2023-07-21 | 2023-08-22 | 2023-10-30 | 87
0 | FBSTPN2190 | BH-03 - FINAL PAINT & TOUCH-UP PAINTING | 60 | 2023-05-29 | 2023-08-07 | 2023-08-29 | 2023-11-06 | 79
MISCELLANEOUS WORKS |  |  | 42 | 2023-05-15 | 2023-07-03 | 2023-09-05 | 2023-10-23 | 97
0 | FBST4000 | BH-03 - MISCELLANEOUS WORKS | 42 | 2023-05-15 | 2023-07-03 | 2023-09-05 | 2023-10-23 | 97
COMMISIONING |  |  | 48 | 2023-06-26 | 2023-08-21 | 2023-09-29 | 2023-11-16 | 76
0 | FBCG1150 | BH-03 - 415V AUXILIARY DB | 3 | 2023-06-28 | 2023-07-01 | 2023-10-03 | 2023-10-05 | 83
0 | FBCG1160 | BH-03 - 24V DC UPS BATTERY CHARGER & BATTERY | 6 | 2023-06-29 | 2023-07-06 | 2023-10-04 | 2023-10-10 | 83
0 | FBCG1140 | BH-03 - 415 V SWITCHGEAR (2 I/C +15 FDRS.+ 3 SPR.) | 15 | 2023-06-26 | 2023-07-13 | 2023-09-29 | 2023-10-16 | 82
0 | FBCG1210 | BH-03 - MOV POWER DB | 2 | 2023-07-15 | 2023-07-18 | 2023-10-21 | 2023-10-23 | 84
0 | FBCG1400 | BH-03 - FIRE FIGHTING & SAFETY EQUIPMENT | 3 | 2023-07-14 | 2023-07-18 | 2023-11-11 | 2023-11-14 | 103
0 | FBCG1200 | BH-03 - TELECOM & LAN SYSTEM - 3 NOS | 5 | 2023-07-13 | 2023-07-19 | 2023-10-19 | 2023-10-24 | 84
0 | FBCG1170 | BH-03 - ECMS SYSTEM | 14 | 2023-07-05 | 2023-07-21 | 2023-10-10 | 2023-10-25 | 83
0 | FBCG1220 | BH-03 - NAVIGATIONAL AID SYSTEM | 3 | 2023-07-18 | 2023-07-21 | 2023-10-24 | 2023-10-26 | 84
0 | FBCG1230 | BH-03 - CCTV SYSTEM - 3 NOS | 3 | 2023-07-18 | 2023-07-21 | 2023-10-24 | 2023-10-26 | 84
0 | FBCG1250 | BH-03 - BIRD DETERRENT SYSTEM- | 2 | 2023-07-21 | 2023-07-24 | 2023-10-27 | 2023-10-28 | 84
0 | FBCG1260 | BH-03 - UHF RADIO - 3 NOS | 2 | 2023-07-21 | 2023-07-24 | 2023-10-27 | 2023-10-28 | 84
0 | FBCG1040 | BH-03 - RTU SYSTEM (OTP & LOOP CHECKING) | 14 | 2023-07-11 | 2023-07-27 | 2023-10-10 | 2023-10-25 | 78
0 | FBCG1270 | BH-03 - 6.6 KV RMU SYSTEM | 6 | 2023-07-20 | 2023-07-27 | 2023-10-26 | 2023-11-01 | 84
0 | FBCG1190 | BH-03 - ESD SYSTEM (OTP & LOOP CHECKING) | 14 | 2023-07-13 | 2023-07-29 | 2023-10-14 | 2023-10-30 | 80
0 | FBCG1310 | BH-03 - CLOSED DRAIN | 3 | 2023-07-27 | 2023-07-31 | 2023-10-26 | 2023-10-28 | 78
0 | FBCG1290 | BH-03 - HIPPS (OTP & LOOP CHECKING | 5 | 2023-07-27 | 2023-08-02 | 2023-10-28 | 2023-11-02 | 80
0 | FBCG1300 | BH-03 - 6.6KV / 433V POWER TRANSFORMER | 4 | 2023-07-28 | 2023-08-02 | 2023-10-30 | 2023-11-02 | 80
0 | FBCG1320 | BH-03 - COMM -CHEMICAL INJECTION | 4 | 2023-07-29 | 2023-08-03 | 2023-10-28 | 2023-11-01 | 78
0 | FBCG1240 | BH-03 - WELL HEAD CONTROL PANEL (OTP & LOOP CHECKING) | 6 | 2023-07-29 | 2023-08-05 | 2023-10-26 | 2023-11-01 | 76
0 | FBCG1330 | BH-03 - LIGHTING SYSTEM | 5 | 2023-08-02 | 2023-08-08 | 2023-11-03 | 2023-11-08 | 80
0 | FBCG1340 | BH-03 - WELL SLOT-1 (WELL#626) | 6 | 2023-08-01 | 2023-08-08 | 2023-10-31 | 2023-11-06 | 78
0 | FBCG1280 | BH-03 - FIRE &GAS SYSTEM (OTP & LOOP CHECKING) | 11 | 2023-07-27 | 2023-08-09 | 2023-10-28 | 2023-11-09 | 80
0 | FBCG1360 | BH-03 - MPFM - COMMUNICATION ESTABLISHMENT | 3 | 2023-08-05 | 2023-08-09 | 2023-11-02 | 2023-11-04 | 76
0 | FBCG1370 | BH-03 - PRODUCTION MANIFOLD | 3 | 2023-08-07 | 2023-08-10 | 2023-11-06 | 2023-11-08 | 78
0 | FBCG1380 | BH-03 - COMM -PIG LAUNCHER/RECEIVER | 3 | 2023-08-10 | 2023-08-14 | 2023-11-09 | 2023-11-11 | 78
0 | FBCG1390 | BH-03 - VENT & DRAIN SYSTEM OTP | 4 | 2023-08-11 | 2023-08-16 | 2023-11-10 | 2023-11-14 | 78
0 | FBCG1350 | BH-03 - LEAK TEST | 14 | 2023-08-04 | 2023-08-21 | 2023-11-01 | 2023-11-16 | 76
READY FOR LOADOUT |  |  | 18 | 2023-07-31 | 2023-08-21 | 2023-10-31 | 2023-11-17 | 77
0 | FBLO1010 | BH-03 - FINAL DECK WEIGHING | 6 | 2023-07-31 | 2023-08-07 | 2023-10-31 | 2023-11-06 | 79
0 | FBLO2010 | BH-03 - COMPANY WALK THROUGH AND PUNCH LIST CLEARANCE | 12 | 2023-08-03 | 2023-08-17 | 2023-11-03 | 2023-11-16 | 79
0 | FBLO1000 | BH-03 - READY FOR LOADOUT - WHP BH-03 TOPSIDE | 0 |  | 2023-08-21 |  | 2023-11-16 | 76
0 | FBLO2020 | BH-03 - STAND BY AFTER READY FOR LOAD OUT - WHP BH-03 TOPSIDE | 0 | 2023-08-21 | 2023-08-21 | 2023-11-17 | 2023-11-17 | 77
FABRICATION SATAH WHP 10 TOPSIDE |  |  | 307 | 2022-09-22 | 2023-09-15 | 2022-12-07 | 2023-11-16 | 54
STRUCTURAL |  |  | 288 | 2022-09-22 | 2023-08-24 | 2022-12-07 | 2023-11-04 | 63
STRUCTURAL PRE-FABRICATION |  |  | 249 | 2022-09-22 | 2023-07-10 | 2022-12-07 | 2023-09-16 | 60
PRE-FAB PLATES |  |  | 101 | 2022-09-22 | 2023-01-18 | 2022-12-07 | 2023-04-18 | 78
0 | FSST1000 | WHP 10 - CUT & PROFILE - PLATES (MAIN DECK) | 15 | 2022-09-22 | 2022-10-10 | 2022-12-07 | 2022-12-23 | 65
0 | FSST1010 | WHP 10 - CUT & PROFILE - PLATES CELLAR DECK | 15 | 2022-09-29 | 2022-10-17 | 2022-12-14 | 2022-12-30 | 65
0 | FSST1020 | WHP 10 - CUT & PROFILE - PLATES (MEZZANINE DECK) | 15 | 2022-10-06 | 2022-10-24 | 2022-12-21 | 2023-01-06 | 65
0 | FSST1030 | WHP 10 - CUT & PROFILE - PLATES (WEATHER DECK) | 15 | 2022-10-18 | 2022-11-04 | 2022-12-28 | 2023-01-13 | 61
0 | FSST1040 | WHP 10 - CUT & PROFILE - PLATES (ACCESSPLATFORM) | 15 | 2022-10-24 | 2022-11-10 | 2023-02-02 | 2023-02-18 | 87
0 | FSST1050 | WHP 10 - CUT & PROFILE - PLATES (HELIDECK, OTHER MISC.) | 48 | 2022-11-23 | 2023-01-18 | 2023-02-22 | 2023-04-18 | 78
PRE-FAB GIRDERS |  |  | 65 | 2022-09-29 | 2022-12-14 | 2022-12-23 | 2023-02-21 | 60
0 | FSST1060 | WHP 10 - SUB ASSEMBLE - GIRDERS (MAIN DECK) | 18 | 2022-09-29 | 2022-10-20 | 2022-12-23 | 2023-01-12 | 73
0 | FSST1070 | WHP 10 - SUB ASSEMBLE - GIRDERS CELLAR DECK | 18 | 2022-10-06 | 2022-10-27 | 2023-01-05 | 2023-01-25 | 78
0 | FSST1080 | WHP 10 - SUB ASSEMBLE - GIRDERS (MEZZANINE DECK) | 18 | 2022-10-13 | 2022-11-03 | 2023-01-11 | 2023-01-31 | 77
0 | FSST1090 | WHP 10 - SUB ASSEMBLE - GIRDERS (WEATHER DECK) | 18 | 2022-11-01 | 2022-11-22 | 2023-01-11 | 2023-01-31 | 61
0 | FSST1100 | WHP 10 - SUB ASSEMBLE - GIRDERS (HELIDECK) | 18 | 2022-11-23 | 2022-12-14 | 2023-02-01 | 2023-02-21 | 60
WORKSHOP SUB-ASSEMBLE - DECK NODES |  |  | 77 | 2022-10-06 | 2023-01-04 | 2022-12-30 | 2023-03-14 | 60
0 | FSST1120 | WHP 10 - SUB ASSEMBLE - NODES (MAIN DECK) | 18 | 2022-10-06 | 2022-10-27 | 2022-12-30 | 2023-01-19 | 73
0 | FSST1130 | WHP 10 - SUB ASSEMBLE - NODES CELLAR DECK | 18 | 2022-10-13 | 2022-11-03 | 2023-01-12 | 2023-02-01 | 78
0 | FSST5030 | WHP 10 - SUB ASSEMBLE - NODES (ACCESS PLATFORM) | 18 | 2022-10-13 | 2022-11-03 | 2023-01-30 | 2023-02-18 | 93
0 | FSST1140 | WHP 10 - SUB ASSEMBLE - NODES (MEZZANINE DECK) | 18 | 2022-10-20 | 2022-11-10 | 2023-01-18 | 2023-02-07 | 77
0 | FSST1150 | WHP 10 - SUB ASSEMBLE - NODES (WEATHER DECK) | 18 | 2022-11-08 | 2022-11-29 | 2023-02-01 | 2023-02-21 | 73
0 | FSST1160 | WHP 10 - SUB ASSEMBLE - NODES (HELIDECK | 18 | 2022-12-14 | 2023-01-04 | 2023-02-22 | 2023-03-14 | 60
PRE-FAB SECTIONS |  |  | 123 | 2022-10-06 | 2023-02-27 | 2023-01-02 | 2023-06-15 | 94
0 | FSST1170 | WHP 10 - CUT & PROFILE - SECTIONS (MAIN DECK) | 21 | 2022-10-06 | 2022-10-31 | 2023-01-02 | 2023-01-25 | 75
0 | FSST1180 | WHP 10 - CUT & PROFILE - SECTIONS CELLAR DECK | 21 | 2022-10-19 | 2022-11-12 | 2023-01-09 | 2023-02-01 | 70
0 | FSST1190 | WHP 10 - CUT & PROFILE - SECTIONS (MEZZANINE DECK) | 21 | 2022-11-07 | 2022-12-01 | 2023-01-16 | 2023-02-08 | 60
0 | FSST1200 | WHP 10 - CUT & PROFILE - SECTIONS (WEATHER DECK) | 21 | 2022-11-14 | 2022-12-08 | 2023-02-11 | 2023-03-07 | 77
0 | FSST1210 | WHP 10 - CUT & PROFILE - SECTIONS (ACCESS PALTFORM) | 18 | 2022-11-21 | 2022-12-12 | 2023-01-30 | 2023-02-18 | 60
0 | FSST1220 | WHP 10 - CUT & PROFILE - SECTIONS (HDK) | 21 | 2022-12-09 | 2023-01-03 | 2023-03-08 | 2023-03-31 | 76
0 | FSST1230 | WHP 10 - CUT & PROFILE - SECTIONS (OTHER MISC.) | 60 | 2022-12-19 | 2023-02-27 | 2023-04-07 | 2023-06-15 | 94
PRE-FAB TUBULARS |  |  | 129 | 2022-10-06 | 2023-03-06 | 2023-01-04 | 2023-08-16 | 141
0 | FSST5040 | WHP 10 - CUT & PROFILE - TUBULARS CELLAR/ MAIN & MEZZ DECK | 24 | 2022-10-06 | 2022-11-03 | 2023-01-10 | 2023-02-06 | 82
0 | FSST1240 | WHP 10 - CUT & PROFILE - TUBULARS (B/W CELLAR DECK & MAIN DECK | 24 | 2022-10-13 | 2022-11-10 | 2023-01-04 | 2023-01-31 | 71
0 | FSST1250 | WHP 10 - CUT & PROFILE - TUBULARS (B/W (MAIN DECK) & (MEZZANINE DECK) | 24 | 2022-10-20 | 2022-11-17 | 2023-01-11 | 2023-02-07 | 71
0 | FSST1260 | WHP 10 - CUT & PROFILE - TUBULARS (B/W MEZZANINE DECK & WEATHER DECK) | 24 | 2022-10-27 | 2022-11-24 | 2023-01-18 | 2023-02-14 | 71
0 | FSST1270 | WHP 10 - CUT & PROFILE - TUBULARS (B/W ACCESS PLATFORM & MEZZANINE DECK) | 24 | 2022-10-27 | 2022-11-24 | 2023-03-16 | 2023-04-12 | 120
0 | FSST1280 | WHP 10 - CUT & PROFILE - TUBULARS (HELIDECK) | 24 | 2022-11-24 | 2022-12-22 | 2023-02-15 | 2023-03-14 | 71
0 | FSST1290 | WHP 10 - CUT & PROFILE - TUBULARS (OTHER MISC.) | 75 | 2022-12-08 | 2023-03-06 | 2023-05-22 | 2023-08-16 | 141
WORKSHOP SUB-ASSEMBLE - HANDRAILS & LADDERS |  |  | 90 | 2022-12-05 | 2023-03-20 | 2023-03-27 | 2023-07-14 | 101
0 | FSST1300 | WHP 10 - SUB ASSEMBLE - HANDRAILS CELLAR DECK | 36 | 2022-12-05 | 2023-01-16 | 2023-03-27 | 2023-05-06 | 96
0 | FSST1310 | WHP 10 - SUB ASSEMBLE - HANDRAILS (MAIN DECK) | 36 | 2022-12-19 | 2023-01-30 | 2023-04-12 | 2023-05-23 | 98
0 | FSST5050 | WHP 10 - SUB ASSEMBLE - HANDRAILS (ACCESSPLATFORM) | 36 | 2022-12-26 | 2023-02-06 | 2023-04-19 | 2023-05-30 | 98
0 | FSST1320 | WHP 10 - SUB ASSEMBLE - HANDRAILS (MEZZANINE DECK) | 36 | 2023-01-02 | 2023-02-13 | 2023-04-29 | 2023-06-09 | 101
0 | FSST1330 | WHP 10 - SUB ASSEMBLE - HANDRAILS (WEATHER DECK)) | 36 | 2023-01-16 | 2023-02-27 | 2023-05-13 | 2023-06-23 | 101
0 | FSST1340 | WHP 10 - SUB ASSEMBLE - LADDERS & CAGES | 48 | 2023-01-23 | 2023-03-20 | 2023-05-20 | 2023-07-14 | 101
WORKSHOP SUB ASSEMBLE - STAIRWAYS / STAIR TOWER / MAIN LADDER |  |  | 78 | 2023-02-27 | 2023-05-29 | 2023-06-16 | 2023-09-14 | 94
EAST SIDE |  |  | 42 | 2023-02-27 | 2023-04-17 | 2023-06-16 | 2023-09-02 | 120
0 | FSST1350 | WHP 10 - SUB ASSEMBLE - CELLAR DECK TO JACKET WALKWAY (EAST SIDE) | 24 | 2023-02-27 | 2023-03-27 | 2023-06-16 | 2023-07-13 | 94
0 | FSST1360 | WHP 10 - SUB ASSEMBLE - (MAIN DECK) TO CELLAR DECK (EAST SIDE) | 24 | 2023-03-06 | 2023-04-03 | 2023-07-24 | 2023-08-19 | 120
0 | FSST1370 | WHP 10 - SUB ASSEMBLE - MEZZANINE DECK TO (MAIN DECK) (EAST SIDE) | 24 | 2023-03-13 | 2023-04-10 | 2023-07-31 | 2023-08-26 | 120
0 | FSST1380 | WHP 10 - SUB ASSEMBLE - WEATHER DECK TO MEZZANINE DECK (EAST SIDE) | 24 | 2023-03-20 | 2023-04-17 | 2023-08-07 | 2023-09-02 | 120
WEST SIDE |  |  | 42 | 2023-03-13 | 2023-05-01 | 2023-06-30 | 2023-08-24 | 100
0 | FSST1390 | WHP 10 - SUB ASSEMBLE - MAIN LADDER FROM MAIN. DECK TO CELLAR DECKK (WEST SIDE) | 21 | 2023-03-13 | 2023-04-06 | 2023-06-30 | 2023-07-24 | 94
0 | FSST1400 | WHP 10 - SUB ASSEMBLE - MAIN LADDER FROM MEZZANINE DECK TO (MAIN DECK) (WEST SIDE) | 21 | 2023-03-27 | 2023-04-20 | 2023-07-21 | 2023-08-14 | 100
0 | FSST1410 | WHP 10 - SUB ASSEMBLE - MAIN LADDER FROM WEATHER DECK TO MEZZANINE DECK (WEST SIDE) | 21 | 2023-04-06 | 2023-05-01 | 2023-08-01 | 2023-08-24 | 100
OTHER MISCELLANEOUS |  |  | 60 | 2023-03-20 | 2023-05-29 | 2023-07-07 | 2023-09-14 | 94
0 | FSST1420 | WHP 10 - SUB ASSEMBLE - STAIRWAYS (OTHER MISC.) | 60 | 2023-03-20 | 2023-05-29 | 2023-07-07 | 2023-09-14 | 94
FLOOR DRAINS |  |  | 48 | 2022-10-17 | 2022-12-12 | 2023-02-10 | 2023-04-29 | 120
0 | FSST1430 | WHP 10 - SUB ASSEMBLE - FLOOR DRAINS (CELLAR DK) | 21 | 2022-10-17 | 2022-11-10 | 2023-02-10 | 2023-03-06 | 100
0 | FSST1440 | WHP 10 - SUB ASSEMBLE - FLOOR DRAINS (MAIN DECK) | 30 | 2022-10-24 | 2022-11-28 | 2023-02-17 | 2023-03-23 | 100
0 | FSST1450 | WHP 10 - SUB ASSEMBLE - FLOOR DRAINS (MEZZANINE DECK) | 30 | 2022-10-31 | 2022-12-05 | 2023-03-16 | 2023-04-19 | 117
0 | FSST1460 | WHP 10 - SUB ASSEMBLE - FLOOR DRAINS (WEATHER DK) | 30 | 2022-11-07 | 2022-12-12 | 2023-03-27 | 2023-04-29 | 120
WORKSHOP SUB-ASSEMBLE - OTHER STRUCTURES |  |  | 198 | 2022-11-21 | 2023-07-10 | 2023-02-13 | 2023-09-16 | 60
0 | FSST1470 | WHP 10 - SUB ASSEMBLE - DECK PENETRATIONS | 36 | 2022-11-21 | 2023-01-02 | 2023-02-13 | 2023-03-25 | 72
0 | FSST1510 | WHP 10 - SUB ASSEMBLE - STABBING GUIDES | 24 | 2023-01-18 | 2023-02-15 | 2023-04-19 | 2023-05-16 | 78
0 | FSST1490 | WHP 10 - SUB ASSEMBLE DECK PADEYES | 45 | 2023-01-11 | 2023-03-04 | 2023-04-13 | 2023-06-03 | 79
0 | FSST1500 | WHP 10 - SUB ASSEMBLE - MONORAIL FRAMES | 56 | 2023-01-13 | 2023-03-20 | 2023-05-10 | 2023-07-13 | 100
0 | FSST1560 | WHP 10 - SUB ASSEMBLE - FLARE BOOM | 30 | 2023-03-11 | 2023-04-15 | 2023-07-18 | 2023-08-21 | 110
0 | FSST1540 | WHP 10 - SUB ASSEMBLE SAFETY NET | 24 | 2023-03-22 | 2023-04-19 | 2023-05-31 | 2023-06-27 | 60
0 | FSST1530 | WHP 10 - SUB ASSEMBLE - DECK HATCHES | 42 | 2023-03-04 | 2023-04-22 | 2023-06-05 | 2023-07-22 | 79
0 | FSST1550 | WHP 10 - FABRICATE MISCELLANEOUS ITEMS | 60 | 2023-03-11 | 2023-05-20 | 2023-06-12 | 2023-08-19 | 79
0 | FSST1580 | WHP 10 - FABRICATE HELIDECK DRAIN/GUTTER | 60 | 2023-03-11 | 2023-05-20 | 2023-06-12 | 2023-08-19 | 79
0 | FSST1590 | WHP 10 - SUB ASSEMBLE - PLATFORM IDENTIFICATION PANELS | 42 | 2023-04-22 | 2023-06-10 | 2023-07-31 | 2023-09-16 | 85
0 | FSST1520 | WHP 10 - SUB ASSEMBLE OTHER MISCL STRUCTURES | 70 | 2023-04-19 | 2023-07-10 | 2023-06-28 | 2023-09-16 | 60
PRE-FAB - PIPE SUPPORTS |  |  | 60 | 2023-02-13 | 2023-04-24 | 2023-04-17 | 2023-06-30 | 59
0 | FSST1610 | WHP 10 - PRE-FAB -PIPE SUPPORTS (CELLAR DK) (Welded attachments to frame) | 12 | 2023-02-13 | 2023-02-27 | 2023-04-17 | 2023-04-29 | 54
0 | FSST1600 | WHP 10 - PRE-FAB - PIPE SUPPORTS (MAIN DECK) (Welded attachments to frame) | 18 | 2023-02-13 | 2023-03-06 | 2023-04-17 | 2023-05-06 | 54
0 | FSST1630 | WHP 10 - PRE-FAB - PIPE SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-02-20 | 2023-03-13 | 2023-05-31 | 2023-06-20 | 86
0 | FSST1640 | WHP 10 - PRE-FAB - PIPE SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 18 | 2023-02-20 | 2023-03-13 | 2023-04-24 | 2023-05-13 | 54
0 | FSST1620 | WHP 10 - PRE-FAB - BALANCE PIPE SUPPORTS (Other than Welded attachments to frame) | 60 | 2023-02-13 | 2023-04-24 | 2023-04-22 | 2023-06-30 | 59
PRE-FAB - EQUIPMENT SUPPORTS |  |  | 86 | 2023-02-17 | 2023-05-29 | 2023-04-22 | 2023-08-21 | 73
0 | FSST1650 | WHP 10 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (MAIN DECK) (Welded attachments to frame) | 18 | 2023-02-17 | 2023-03-10 | 2023-04-22 | 2023-05-12 | 55
0 | FSST1670 | WHP 10 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (CELLARN DK) (Welded attachments to frame) | 18 | 2023-02-22 | 2023-03-15 | 2023-04-27 | 2023-05-17 | 55
0 | FSST1660 | WHP 10 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 18 | 2023-02-27 | 2023-03-20 | 2023-05-01 | 2023-05-20 | 54
0 | FSST1690 | WHP 10 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-03-13 | 2023-04-03 | 2023-05-15 | 2023-06-03 | 54
0 | FSST1680 | WHP 10 - PRE-FAB - VENT SUPPORT STRUCTURE | 42 | 2023-03-13 | 2023-05-01 | 2023-06-28 | 2023-08-15 | 92
0 | FSST1700 | WHP 10 - PRE-FAB - BALANCE EQUIPMENT SUPPORTS (Other than Welded attachments to frame) | 48 | 2023-04-03 | 2023-05-29 | 2023-06-27 | 2023-08-21 | 73
PRE-FAB - E & I CABLE TRAY SUPPORTS |  |  | 69 | 2023-02-27 | 2023-05-18 | 2023-05-02 | 2023-07-22 | 57
0 | FSST1710 | WHP 10 - PRE-FAB - CABLE TRAY SUPPORTS (CELLAR DK) (Welded attachments to frame) | 15 | 2023-02-27 | 2023-03-16 | 2023-05-02 | 2023-05-18 | 55
0 | FSST1720 | WHP 10 - PRE-FAB - CABLE TRAY SUPPORTS (MAIN DECK) (Welded attachments to frame) | 15 | 2023-03-03 | 2023-03-21 | 2023-05-06 | 2023-05-23 | 55
0 | FSST1730 | WHP 10 - PRE-FAB - CABLE TRAY SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 15 | 2023-03-10 | 2023-03-28 | 2023-05-22 | 2023-06-07 | 62
0 | FSST1740 | WHP 10 - PRE-FAB - CABLE TRAY SUPPORTS (WEATHER DK) (Welded attachments to frame) | 15 | 2023-03-27 | 2023-04-13 | 2023-05-29 | 2023-06-14 | 54
0 | FSST1760 | WHP 10 - PRE-FAB - SECONDARY CABLE TRAY SUPPORTS | 42 | 2023-03-21 | 2023-05-09 | 2023-06-05 | 2023-07-22 | 65
0 | FSST1750 | WHP 10 - PRE-FAB - BALANCE CABLE TRAY SUPPORTS (Other than Welded attachments to frame) | 56 | 2023-03-14 | 2023-05-18 | 2023-05-16 | 2023-07-19 | 54
PRE-FAB - OTHER E&I SUPPORTS |  |  | 68 | 2023-03-08 | 2023-05-26 | 2023-05-11 | 2023-08-01 | 58
0 | FSST1770 | WHP 10 - PRE-FAB - OTHER E&I SUPPORTS (MAIN DECK) | 30 | 2023-03-08 | 2023-04-12 | 2023-05-11 | 2023-06-14 | 55
0 | FSST1780 | WHP 10 - PRE-FAB - OTHER E&I SUPPORTS (CELLAR DK) | 30 | 2023-03-13 | 2023-04-17 | 2023-05-16 | 2023-06-19 | 55
0 | FSST1790 | WHP 10 - PRE-FAB - OTHER E&I SUPPORTS (MEZZANINE DECK) | 30 | 2023-03-17 | 2023-04-21 | 2023-05-23 | 2023-06-26 | 57
0 | FSST1810 | WHP 10 - PRE-FAB - OTHER E&I SUPPORTS (WEATHER DK) | 30 | 2023-03-24 | 2023-04-28 | 2023-05-31 | 2023-07-04 | 58
0 | FSST1800 | WHP 10 - PRE-FAB - BALANCE OTHER E&I SUPPORTS (Other than Welded attachments to frame) | 56 | 2023-03-22 | 2023-05-26 | 2023-05-29 | 2023-08-01 | 58
GENERAL |  |  | 180 | 2022-09-29 | 2023-04-27 | 2023-02-17 | 2023-09-14 | 121
0 | FSST5060 | WHP 10 - JOB PREPRATION FOR ASSEMBLY & LEVEL- LIFTING | 180 | 2022-09-29 | 2023-04-27 | 2023-02-17 | 2023-09-14 | 121
STRUCTURAL ASSEMBLY & ERECTION |  |  | 264 | 2022-10-20 | 2023-08-24 | 2023-01-13 | 2023-11-04 | 63
ASSEMBLY & WELD MAIN DECK |  |  | 93 | 2022-10-20 | 2023-02-06 | 2023-01-13 | 2023-05-01 | 73
0 | FSST2000 | WHP 10 - FIT-UP & TACK WELD - MAIN DECK MAIN FRAME - GIRDERS | 21 | 2022-10-20 | 2022-11-14 | 2023-01-13 | 2023-02-06 | 73
0 | FSST2010 | WHP 10 - FIT-UP & TACK WELD - MAIN DECK MAIN FRAME - NODES | 21 | 2022-10-20 | 2022-11-14 | 2023-01-13 | 2023-02-06 | 73
0 | FSST2020 | WHP 10 - FIT-UP & TACK WELD - MAIN DECK SECONDARY STEEL | 21 | 2022-11-07 | 2022-12-01 | 2023-01-31 | 2023-02-23 | 73
0 | FSST2030 | WHP 10 - COMPLETE WELDING - MAIN DECK | 24 | 2022-11-21 | 2022-12-19 | 2023-02-14 | 2023-03-13 | 73
0 | FSST2040 | WHP 10 - ERECT & WELD - MAIN DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2022-12-19 | 2023-01-09 | 2023-03-14 | 2023-04-03 | 73
0 | FSST2050 | WHP 10 - ERECT & WELD - DECK LEGS AND BRACES (MAIN DECK) | 18 | 2022-12-19 | 2023-01-09 | 2023-03-14 | 2023-04-03 | 73
0 | FSST2060 | WHP 10 - PREPARATION - MAIN DECK ERECTION / LIFT | 3 | 2023-02-02 | 2023-02-06 | 2023-04-28 | 2023-05-01 | 73
ASSEMBLY & WELD CELLAR DECK |  |  | 84 | 2022-10-31 | 2023-02-06 | 2023-01-30 | 2023-05-10 | 81
0 | FSST2070 | WHP 10 - FIT-UP & TACK WELD - CELLAR DECK MAIN FRAME - GIRDERS | 18 | 2022-10-31 | 2022-11-21 | 2023-01-30 | 2023-02-18 | 78
0 | FSST2080 | WHP 10 - FIT-UP & TACK WELD - CELLAR DECK MAIN FRAME - NODES | 18 | 2022-10-31 | 2022-11-21 | 2023-02-02 | 2023-02-22 | 81
0 | FSST2090 | WHP 10 - FIT-UP & TACK WELD - CELLAR DECK SECONDARY FRAME | 18 | 2022-11-14 | 2022-12-05 | 2023-02-16 | 2023-03-08 | 81
0 | FSST2100 | WHP 10 - COMPLETE WELDING - CELLAR DECK | 15 | 2022-12-05 | 2022-12-22 | 2023-03-09 | 2023-03-25 | 81
0 | FSST2110 | WHP 10 - ERECT & WELD - CELLAR DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2022-12-19 | 2023-01-09 | 2023-03-23 | 2023-04-12 | 81
0 | FSST2120 | WHP 10 - PREPARATION - CELLAR DECK ERECTION / LIFT | 3 | 2023-02-02 | 2023-02-06 | 2023-05-08 | 2023-05-10 | 81
ASSEMBLY & WELD MEZZANINE DECK |  |  | 93 | 2022-11-07 | 2023-02-23 | 2023-02-04 | 2023-05-31 | 84
0 | FSST2130 | WHP 10 - FIT-UP & TACK WELD - MEZZANINE DECK MAIN FRAME - GIRDERS | 21 | 2022-11-07 | 2022-12-01 | 2023-02-04 | 2023-02-28 | 77
0 | FSST2140 | WHP 10 - FIT-UP & TACK WELD - MEZZANINE DECK MAIN FRAME - NODES | 21 | 2022-11-07 | 2022-12-01 | 2023-02-13 | 2023-03-08 | 84
0 | FSST2150 | WHP 10 - FIT-UP & TACK WELD - MEZZANINE DECK SECONDARY FRAME | 21 | 2022-11-24 | 2022-12-19 | 2023-03-02 | 2023-03-25 | 84
0 | FSST2160 | WHP 10 - COMPLETE WELDING - MEZZANINE DECK | 24 | 2022-12-08 | 2023-01-05 | 2023-03-16 | 2023-04-12 | 84
0 | FSST2170 | WHP 10 - ERECT & WELD - MEZZANINE DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-01-05 | 2023-01-26 | 2023-04-13 | 2023-05-03 | 84
0 | FSST2180 | WHP 10 - ERECT & WELD - DECK LEGS AND BRACES (MEZZANINE DECK - MAIND DECK) | 18 | 2023-01-05 | 2023-01-26 | 2023-04-13 | 2023-05-03 | 84
0 | FSST2190 | WHP 10 - PREPARATION - MEZZANINE DECK ERECTION / LIFT | 3 | 2023-02-20 | 2023-02-23 | 2023-05-29 | 2023-05-31 | 84
ASSEMBLY & WELD ACCESS PLATFORM |  |  | 60 | 2022-12-12 | 2023-02-20 | 2023-02-20 | 2023-04-29 | 60
0 | FSST2200 | WHP 10 - FIT-UP & TACK WELD - ACCESS PLATFORMS MAIN FRAME | 18 | 2022-12-12 | 2023-01-02 | 2023-02-20 | 2023-03-11 | 60
0 | FSST2210 | WHP 10 - FIT-UP & TACK WELD - ACCESS PLATFORMS SECONDARY FRAME | 15 | 2022-12-26 | 2023-01-12 | 2023-03-06 | 2023-03-22 | 60
0 | FSST2220 | WHP 10 - COMPLETE WELDING - ACCESS PLATFORMS | 18 | 2023-01-12 | 2023-02-02 | 2023-03-23 | 2023-04-12 | 60
0 | FSST2230 | WHP 10 - ERECT & WELD - ACCESS PLATFORMS FLOOR PLATING | 15 | 2023-02-02 | 2023-02-20 | 2023-04-13 | 2023-04-29 | 60
0 | FSST2240 | WHP 10 - ERECT & WELD - DECK LEGS AND BRACES (ACCESS PLATFORM & MEZZANINE DECK) | 15 | 2023-02-02 | 2023-02-20 | 2023-04-13 | 2023-04-29 | 60
ASSEMBLY & WELD WEATHER DECK |  |  | 101 | 2022-11-29 | 2023-03-27 | 2023-02-25 | 2023-06-17 | 72
0 | FSST2250 | WHP 10 - FIT-UP & TACK WELD - WEATHER DECK MAIN FRAME | 21 | 2022-11-29 | 2022-12-23 | 2023-02-25 | 2023-03-21 | 76
0 | FSST2260 | WHP 10 - FIT-UP & TACK WELD - WEATHER DECK FRAME - NODES | 21 | 2022-11-29 | 2022-12-23 | 2023-03-02 | 2023-03-25 | 80
0 | FSST2270 | WHP 10 - FIT-UP & TACK WELD - WEATHER DECK SECONDARY FRAME | 21 | 2022-12-16 | 2023-01-10 | 2023-03-20 | 2023-04-12 | 80
0 | FSST2280 | WHP 10 - COMPLETE WELDING - WEATHER DECK | 18 | 2023-01-06 | 2023-01-27 | 2023-04-10 | 2023-04-29 | 80
0 | FSST2290 | WHP 10 - ERECT & WELD - WEATHER DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-02-06 | 2023-02-27 | 2023-05-01 | 2023-05-20 | 72
0 | FSST2300 | WHP 10 - PREPARATION - WEATHER DECK ERECTION / LIFT | 3 | 2023-03-23 | 2023-03-27 | 2023-06-15 | 2023-06-17 | 72
ASSEMBLY & WELD HELI DECK |  |  | 102 | 2023-01-04 | 2023-05-03 | 2023-03-15 | 2023-09-07 | 110
0 | FSST2310 | WHP 10 - FIT-UP & TACK WELD - HELI DECK MAIN FRAME | 24 | 2023-01-04 | 2023-02-01 | 2023-03-15 | 2023-04-11 | 60
0 | FSST2320 | WHP 10 - FIT-UP & TACK WELD - HELI DECK MAIN FRAME - NODES | 24 | 2023-01-04 | 2023-02-01 | 2023-04-01 | 2023-04-28 | 75
0 | FSST2330 | WHP 10 - FIT-UP & TACK WELD - HELI DECK SECONDARY FRAME | 24 | 2023-01-21 | 2023-02-18 | 2023-04-01 | 2023-04-28 | 60
0 | FSST2340 | WHP 10 - COMPLETE WELDING - HELI DECK | 15 | 2023-02-18 | 2023-03-08 | 2023-04-29 | 2023-05-16 | 60
0 | FSST2350 | WHP 10 - ERECT & WELD - HDK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-03-08 | 2023-03-29 | 2023-05-17 | 2023-06-06 | 60
0 | FSST2360 | WHP 10 - INSTALL - SAFETY NET | 6 | 2023-04-22 | 2023-04-29 | 2023-08-29 | 2023-09-04 | 110
0 | FSST2370 | WHP 10 - PREPARATION - HELI DECK ERECTION / LIFT | 3 | 2023-04-29 | 2023-05-03 | 2023-09-05 | 2023-09-07 | 110
ERECT - CELLAR DECK |  |  | 30 | 2023-02-06 | 2023-03-13 | 2023-05-11 | 2023-06-17 | 84
0 | FSST2380 | WHP 10 - LIFT,INSTALL & WELD - CELLAR DECK | 6 | 2023-02-06 | 2023-02-13 | 2023-05-11 | 2023-05-17 | 81
0 | FSST2390 | WHP 10 - ERECT & WELD - REMAINING DECK ELEVATIONS / BRACES (B/W CELLAR DK & MAIN DECK) | 24 | 2023-02-13 | 2023-03-13 | 2023-05-22 | 2023-06-17 | 84
ERECT - MAIN DECK |  |  | 6 | 2023-02-13 | 2023-02-20 | 2023-05-18 | 2023-05-24 | 81
0 | FSST2400 | WHP 10 - LIFT,INSTALL & WELD - MAIN DECK | 6 | 2023-02-13 | 2023-02-20 | 2023-05-18 | 2023-05-24 | 81
ACCESS PLATFORM |  |  | 6 | 2023-03-16 | 2023-03-23 | 2023-05-25 | 2023-05-31 | 60
0 | FSST2410 | WHP 10 - INSTALL & WELD - ACCESS PLATFORMS | 6 | 2023-03-16 | 2023-03-23 | 2023-05-25 | 2023-05-31 | 60
ERECT - MEZZANINE DECK |  |  | 15 | 2023-03-23 | 2023-04-10 | 2023-06-01 | 2023-07-19 | 87
0 | FSST2420 | WHP 10 - LIFT,INSTALL & WELD - MEZZANINE DECK | 6 | 2023-03-23 | 2023-03-30 | 2023-06-01 | 2023-06-07 | 60
0 | FSST2430 | WHP 10 - ERECT & WELD - VERTICAL LEGS (B/W MEZZANINE DECK & MAIN DK) | 12 | 2023-03-27 | 2023-04-10 | 2023-07-06 | 2023-07-19 | 87
ERECT WEATHER DECK |  |  | 66 | 2023-04-17 | 2023-07-03 | 2023-06-19 | 2023-09-27 | 75
0 | FSST2440 | WHP 10 - LIFT,INSTALL & WELD - WEATHER DECK | 6 | 2023-04-17 | 2023-04-24 | 2023-06-19 | 2023-06-24 | 54
0 | FSST2450 | WHP 10 - ERECT BALANCE BRACES AND COMPLETE BOX UP | 60 | 2023-04-24 | 2023-07-03 | 2023-07-20 | 2023-09-27 | 75
ERECT- HELI DECK |  |  | 6 | 2023-05-04 | 2023-05-11 | 2023-09-08 | 2023-09-14 | 109
0 | FSST2460 | WHP 10 - LIFT,INSTALL & WELD - HELI DECK | 6 | 2023-05-04 | 2023-05-11 | 2023-09-08 | 2023-09-14 | 109
ERECT- HANDRAILS, LADDERS |  |  | 181 | 2022-12-14 | 2023-07-13 | 2023-03-17 | 2023-11-04 | 99
0 | FSST2480 | WHP 10 - WELD - MAIN DECK HANDRAIL SOCKETS | 15 | 2022-12-14 | 2022-12-31 | 2023-03-17 | 2023-04-03 | 80
0 | FSST2470 | WHP 10 - WELD - CELLAR DECK HANDRAIL SOCKETS | 15 | 2022-12-14 | 2022-12-31 | 2023-03-27 | 2023-04-12 | 88
0 | FSST2490 | WHP 10 - WELD - MEZZANINE DECK HANDRAIL SOCKETS | 15 | 2022-12-19 | 2023-01-05 | 2023-04-17 | 2023-05-03 | 102
0 | FSST2500 | WHP 10 - WELD - WEATHER HANDRAILS SOCKETS | 15 | 2023-01-10 | 2023-01-27 | 2023-05-04 | 2023-05-20 | 98
0 | FSST2520 | WHP 10 - ERECT - MAIN DECK HANDRAILS | 30 | 2023-03-13 | 2023-04-17 | 2023-07-05 | 2023-08-08 | 98
0 | FSST2510 | WHP 10 - ERECT - CELLAR DECK HANDRAILS | 30 | 2023-03-13 | 2023-04-17 | 2023-06-19 | 2023-07-22 | 84
0 | FSST2530 | WHP 10 - ERECT - MEZZANINE DECK HANDRAILS | 30 | 2023-04-17 | 2023-05-22 | 2023-08-30 | 2023-10-03 | 116
0 | FSST2540 | WHP 10 - ERECT - WEATHER DECK HANDRAILS | 30 | 2023-05-11 | 2023-06-15 | 2023-10-02 | 2023-11-04 | 123
0 | FSST2550 | WHP 10 - ERECT & WELD - LADDERS & CAGES | 54 | 2023-05-11 | 2023-07-13 | 2023-08-16 | 2023-10-17 | 83
ERECT- GRATINGS |  |  | 102 | 2023-02-27 | 2023-06-26 | 2023-07-01 | 2023-11-02 | 112
0 | FSST2560 | WHP 10 - TAILORING OF GRATINGS - CELLAR DECK | 21 | 2023-02-27 | 2023-03-23 | 2023-07-01 | 2023-07-25 | 107
0 | FSST2570 | WHP 10 - TAILORING OF GRATINGS - MAIN DECK | 21 | 2023-03-13 | 2023-04-06 | 2023-07-15 | 2023-08-08 | 107
0 | FSST5010 | WHP 10 - TAILORING OF GRATINGS - ACCESS PLATFORM | 21 | 2023-03-13 | 2023-04-06 | 2023-07-15 | 2023-08-08 | 107
0 | FSST2580 | WHP 10 - TAILORING OF GRATINGS - MEZZANINE DECK | 21 | 2023-03-20 | 2023-04-13 | 2023-08-09 | 2023-09-01 | 122
0 | FSST2590 | WHP 10 - TAILORING OF GRATINGS - WEATHER DECK | 21 | 2023-03-27 | 2023-04-20 | 2023-08-16 | 2023-09-08 | 122
0 | FSST5020 | WHP 10 - INSTALL - GRATINGS (ACCESS PLATFORM) | 21 | 2023-04-06 | 2023-05-01 | 2023-08-09 | 2023-09-01 | 107
0 | FSST2600 | WHP 10 - INSTALL - GRATINGS (CELLAR DK) | 21 | 2023-05-01 | 2023-05-25 | 2023-09-02 | 2023-09-26 | 107
0 | FSST2630 | WHP 10 - INSTALL - GRATINGS (MAIN DECK) | 30 | 2023-05-04 | 2023-06-08 | 2023-09-06 | 2023-10-10 | 107
0 | FSST2610 | WHP 10 - INSTALL - GRATINGS MEZZANINE DECK | 30 | 2023-05-08 | 2023-06-12 | 2023-09-29 | 2023-11-02 | 124
0 | FSST2620 | WHP 10 - INSTALL - GRATINGS WEATHER DECK | 30 | 2023-05-22 | 2023-06-26 | 2023-09-29 | 2023-11-02 | 112
ERECT STAIRWAYS/STAIR TOWER |  |  | 60 | 2023-04-24 | 2023-07-03 | 2023-08-11 | 2023-10-28 | 102
0 | FSST2660 | WHP 10 - ERECT & WELD - STAIRWAYS/STAIR TOWER (EAST SIDE) | 30 | 2023-05-08 | 2023-06-12 | 2023-09-25 | 2023-10-28 | 120
0 | FSST2650 | WHP 10 - ERECT & WELD - STAIRWAYS/STAIR TOWER (NORTH SIDE) | 30 | 2023-05-22 | 2023-06-26 | 2023-09-15 | 2023-10-19 | 100
0 | FSST2640 | WHP 10 - ERECT & WELD - OTHER BALANCE STAIRWAYS | 60 | 2023-04-24 | 2023-07-03 | 2023-08-11 | 2023-10-19 | 94
ERECT PIPE SUPPORTS |  |  | 89 | 2023-02-16 | 2023-05-31 | 2023-05-18 | 2023-08-09 | 61
0 | FSST2670 | WHP 10 - INSTALL & WELD - PIPE SUPPORTS CELLAR DECK (Welded attachments to frame) | 12 | 2023-02-16 | 2023-03-02 | 2023-07-25 | 2023-08-07 | 136
0 | FSST2680 | WHP 10 - INSTALL & WELD - PIPE SUPPORTS (MAIN DECK) (Welded attachments to frame) | 15 | 2023-02-20 | 2023-03-09 | 2023-07-21 | 2023-08-07 | 130
0 | FSST2690 | WHP 10 - INSTALL & WELD - PIPE SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 24 | 2023-02-27 | 2023-03-27 | 2023-07-13 | 2023-08-09 | 117
0 | FSST2700 | WHP 10 - INSTALL & WELD - PIPE SUPPORTS (WEATHER DECK) (Welded attachments to frame) | 24 | 2023-03-02 | 2023-03-30 | 2023-07-11 | 2023-08-07 | 112
0 | FSST2710 | WHP 10 - INSTALL & WELD - BALANCE PIPE SUPPORTS (Other than Welded attachments to frame) | 70 | 2023-03-10 | 2023-05-31 | 2023-05-18 | 2023-08-07 | 59
ERECT EQPT SUOPPORTS |  |  | 120 | 2023-02-24 | 2023-07-14 | 2023-05-15 | 2023-10-06 | 73
0 | FSST2720 | WHP 10 - INSTALL & WELD - EQUIPMENT SUPPORTS (MAIN DECK) (Welded attachments to frame) | 18 | 2023-02-24 | 2023-03-17 | 2023-05-15 | 2023-06-03 | 68
0 | FSST2740 | WHP 10 - INSTALL & WELD - EQUIPMENT SUPPORTS (CELLAR DK) (Welded attachments to frame) | 18 | 2023-03-08 | 2023-03-29 | 2023-07-19 | 2023-08-08 | 114
0 | FSST2730 | WHP 10 - INSTALL & WELD - EQUIPMENT SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 18 | 2023-03-13 | 2023-04-03 | 2023-05-15 | 2023-06-03 | 54
0 | FSST2750 | WHP 10 - STALL & WELD - EQUIPMENT SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-03-27 | 2023-04-17 | 2023-07-06 | 2023-07-26 | 87
0 | FSST2770 | WHP 10 - INSTALL & WELD - VENT SUPPORT STRUCTURE | 21 | 2023-05-29 | 2023-06-22 | 2023-09-13 | 2023-10-06 | 92
0 | FSST2760 | WHP 10 - INSTALL & WELD - BALANCE EQUIPMENT SUPPORTS (Other than Welded attachments to frame) | 60 | 2023-05-05 | 2023-07-14 | 2023-07-29 | 2023-10-06 | 73
ERECT CABLE TRAYS SUPPORTS |  |  | 83 | 2023-03-06 | 2023-06-10 | 2023-06-19 | 2023-08-12 | 55
0 | FSST2780 | WHP 10 - INSTALL & WELD - CABLE TRAY SUPPORTS (CELLAR DK) (Welded attachments to frame) | 15 | 2023-03-06 | 2023-03-23 | 2023-06-19 | 2023-07-05 | 90
0 | FSST2790 | WHP 10 - INSTALL & WELD - CABLE TRAY SUPPORTS (MAIN DECK) (Welded attachments to frame) | 15 | 2023-03-10 | 2023-03-28 | 2023-07-17 | 2023-08-02 | 110
0 | FSST2800 | WHP 10 - INSTALL & WELD - CABLE TRAY SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 21 | 2023-03-17 | 2023-04-11 | 2023-07-10 | 2023-08-02 | 98
0 | FSST2810 | WHP 10 - INSTALL & WELD - CABLE TRAY SUPPORTS (WEATHER DK) (Welded attachments to frame) | 15 | 2023-04-10 | 2023-04-27 | 2023-07-17 | 2023-08-02 | 84
0 | FSST2820 | WHP 10 - INSTALL & WELD - SECONDARY CABLE TRAY SUPPORTS | 48 | 2023-04-04 | 2023-05-30 | 2023-06-19 | 2023-08-12 | 65
0 | FSST2830 | WHP 10 - INSTALL & WELD - BALANCE CABLE TRAY SUPPORTS (Other than Welded attachments to frame) | 42 | 2023-04-22 | 2023-06-10 | 2023-06-24 | 2023-08-11 | 54
ERECT OTHER E&I SUPPORTS |  |  | 47 | 2023-04-26 | 2023-06-20 | 2023-07-01 | 2023-08-25 | 58
0 | FSST2840 | WHP 10 - INSTALL & WELD - OTHER E&I SUPPORTS (MAIN DECK) | 15 | 2023-04-26 | 2023-05-13 | 2023-07-01 | 2023-07-18 | 57
0 | FSST2860 | WHP 10 - INSTALL & WELD - OTHER E&I SUPPORTS (CELLAR DK) | 15 | 2023-04-28 | 2023-05-16 | 2023-07-04 | 2023-07-20 | 57
0 | FSST2850 | WHP 10 - INSTALL & WELD - OTHER E&I SUPPORTS (WEATHER DK) | 24 | 2023-04-28 | 2023-05-26 | 2023-07-05 | 2023-08-01 | 58
0 | FSST2880 | WHP 10 - INSTALL & WELD - OTHER E&I SUPPORTS (MEZZANINE DECK) | 21 | 2023-05-03 | 2023-05-27 | 2023-07-08 | 2023-08-01 | 57
0 | FSST2870 | WHP 10 - INSTALL & WELD - BALANCE E&I SUPPORTS (Other than Welded attachments to frame) | 42 | 2023-05-02 | 2023-06-20 | 2023-07-08 | 2023-08-25 | 58
FLOOR DRAINS |  |  | 51 | 2022-11-03 | 2023-01-02 | 2023-03-14 | 2023-05-20 | 120
0 | FSST2890 | WHP 10 - INSTALL & WELD - FLOOR DRAINS (CELLAR DK) | 18 | 2022-11-03 | 2022-11-24 | 2023-03-23 | 2023-04-12 | 120
0 | FSST2900 | WHP 10 - INSTALL & WELD - FLOOR DRAINS (MAIN DECK) | 18 | 2022-11-17 | 2022-12-08 | 2023-03-14 | 2023-04-03 | 100
0 | FSST2910 | WHP 10 - INSTALL & WELD - FLOOR DRAINS (MEZZANINE DECK) | 18 | 2022-11-28 | 2022-12-19 | 2023-04-13 | 2023-05-03 | 117
0 | FSST2920 | WHP 10 - INSTALL & WELD - FLOOR DRAINS (WEATHER DK) | 18 | 2022-12-12 | 2023-01-02 | 2023-05-01 | 2023-05-20 | 120
ERECT OTHER STRUCTURES |  |  | 222 | 2022-12-05 | 2023-08-21 | 2023-02-27 | 2023-10-28 | 60
0 | FSST2930 | WHP 10 - INSTALL & WELD - AVAILABLE DECK PENETRATIONS | 60 | 2022-12-05 | 2023-02-13 | 2023-02-27 | 2023-05-06 | 72
0 | FSST2940 | WHP 10 - INSTALL & WELD - STABBING GUIDES | 9 | 2023-03-01 | 2023-03-11 | 2023-05-31 | 2023-06-09 | 78
0 | FSST2960 | WHP 10 - INSTALL & WELD - BALANCE DECK PENETRATIONS | 42 | 2023-02-13 | 2023-04-03 | 2023-05-27 | 2023-07-14 | 89
0 | FSST2950 | WHP 10 - INSTALL & WELD - DECK PAD EYES | 21 | 2023-03-11 | 2023-04-05 | 2023-06-29 | 2023-07-22 | 94
0 | FSST3010 | WHP 10 - INSTALL & WELD - MONORAIL FRAMES | 60 | 2023-05-01 | 2023-07-10 | 2023-07-05 | 2023-09-12 | 56
0 | FSST2990 | WHP 10 - INSTALL & WELD - FLARE BOOM | 21 | 2023-06-16 | 2023-07-11 | 2023-09-12 | 2023-10-05 | 75
0 | FSST2980 | WHP 10 - INSTALL & WELD - HELIDECK DRAIN/GUTTER | 25 | 2023-06-12 | 2023-07-11 | 2023-09-07 | 2023-10-05 | 75
0 | FSST3000 | WHP 10 - INSTALL & WELD - PLATFORM IDENTIFICATION PANELS | 30 | 2023-06-17 | 2023-07-22 | 2023-09-25 | 2023-10-28 | 85
0 | FSST3020 | WHP 10 - INSTALL & WELD - DECK HATCHES | 60 | 2023-05-15 | 2023-07-24 | 2023-07-17 | 2023-09-23 | 54
0 | FSST2970 | WHP 10 - INSTALL & WELD - MISC STRUCTURAL ITEMS | 60 | 2023-06-12 | 2023-08-21 | 2023-08-21 | 2023-10-28 | 60
PUNCH LIST CLEARANCE- STRUCTURAL |  |  | 20 | 2023-08-01 | 2023-08-24 | 2023-10-11 | 2023-11-02 | 61
0 | FSST4000 | WHP 10 - STRUCTURAL PUNCHLIST CLEARANCE | 20 | 2023-08-01 | 2023-08-24 | 2023-10-11 | 2023-11-02 | 61
PRESSURE VESSEL (FABRICATION & PAINTING) |  |  | 168 | 2022-11-17 | 2023-06-01 | 2023-01-21 | 2023-08-04 | 56
0 | FSPV1000 | WHP 10 - FABRICATE - VENT/DRAIN DRUM | 150 | 2022-11-17 | 2023-05-11 | 2023-01-21 | 2023-07-14 | 56
0 | FSPV1010 | WHP 10 - PAINT - VENT/DRAIN DRUM | 18 | 2023-05-11 | 2023-06-01 | 2023-07-15 | 2023-08-04 | 56
PIPING WORKS |  |  | 168 | 2023-02-06 | 2023-08-21 | 2023-05-02 | 2023-10-31 | 62
PIPING PRE-FABRICATION |  |  | 75 | 2023-02-06 | 2023-05-04 | 2023-05-02 | 2023-08-02 | 78
0 | FSPI1010 | WHP 10 - FABRICATE - CU-NI PIPING SPOOLS | 30 | 2023-02-20 | 2023-03-27 | 2023-05-09 | 2023-06-12 | 67
0 | FSPI1000 | WHP 10 - FABRICATE - CS/ LTCS/ CLADDED PIPING SPOOLS | 56 | 2023-02-06 | 2023-04-12 | 2023-05-02 | 2023-07-05 | 73
0 | FSPI1020 | WHP 10 - FABRICATE - SS/DUPLEX PIPING SPOOLS | 30 | 2023-03-20 | 2023-04-24 | 2023-05-30 | 2023-07-03 | 61
0 | FSPI1030 | WHP 10 - FABRICATE - INCONEL PIPING SPOOLS | 42 | 2023-03-16 | 2023-05-04 | 2023-06-15 | 2023-08-02 | 78
VALVE LEAK TESTING |  |  | 36 | 2023-03-15 | 2023-04-26 | 2023-06-22 | 2023-08-02 | 85
0 | FSPI1040 | WHP 10 - VALVE LEAK TESTING | 36 | 2023-03-15 | 2023-04-26 | 2023-06-22 | 2023-08-02 | 85
PIPING ERECTION/HYDROTESTING/INSULATION |  |  | 117 | 2023-04-06 | 2023-08-21 | 2023-06-10 | 2023-10-31 | 62
PIPING ERECTION |  |  | 67 | 2023-04-06 | 2023-06-23 | 2023-06-10 | 2023-08-31 | 60
0 | FSPI2000 | WHP 10 - ERECT - CS/ LTCS/ CLADDED SPOOLS | 60 | 2023-04-06 | 2023-06-15 | 2023-06-10 | 2023-08-18 | 56
0 | FSPI2010 | WHP 10 - ERECT - INCONEL SPOOLS | 49 | 2023-04-27 | 2023-06-23 | 2023-07-06 | 2023-08-31 | 60
0 | FSPI2020 | WHP 10 - ERECT - CU-NI SPOOLS | 35 | 2023-05-13 | 2023-06-23 | 2023-07-22 | 2023-08-31 | 60
0 | FSPI2030 | WHP 10 - ERECT - SS/DUPLEX SPOOLS | 35 | 2023-05-13 | 2023-06-23 | 2023-07-21 | 2023-08-30 | 59
HYDROTESTING & REINSTATEMENT |  |  | 61 | 2023-05-27 | 2023-08-07 | 2023-08-01 | 2023-10-31 | 74
HYDROTESTING |  |  | 47 | 2023-05-27 | 2023-07-21 | 2023-08-01 | 2023-09-27 | 59
0 | FSPI2040 | WHP 10 - HYDROTESTING AND RE-INSTATEMENT - OIL PRODUCTION SYSTEM | 21 | 2023-05-27 | 2023-06-21 | 2023-08-01 | 2023-08-24 | 56
0 | FSPI2050 | WHP 10 - HYDROTESTING AND RE-INSTATEMENT - WATER INJECTION SYSTEM | 21 | 2023-06-08 | 2023-07-03 | 2023-08-12 | 2023-09-05 | 56
0 | FSPI2060 | WHP 10 - HYDROTESTING AND RE-INSTATEMENT - CLOSED DRAIN SYSTEM | 21 | 2023-06-14 | 2023-07-08 | 2023-08-18 | 2023-09-11 | 56
0 | FSPI2070 | WHP 10 - HYDROTESTING AND RE-INSTATEMENT - OPEN DRAIN SYSTEM | 21 | 2023-06-20 | 2023-07-14 | 2023-08-24 | 2023-09-16 | 56
0 | FSPI2090 | WHP 10 - HYDROTESTING AND RE-INSTATEMENT - VENT SYSTEM | 12 | 2023-07-05 | 2023-07-19 | 2023-09-08 | 2023-09-21 | 56
0 | FSPI2080 | WHP 10 - HYDROTESTING AND RE-INSTATEMENT - CORROSION INHABITOR INJECTION SYSTEM | 21 | 2023-06-27 | 2023-07-21 | 2023-09-04 | 2023-09-27 | 59
INSULATION |  |  | 40 | 2023-06-21 | 2023-08-07 | 2023-09-15 | 2023-10-31 | 74
0 | FSPI2100 | WHP 10 - PIPING INSULATION WORK | 40 | 2023-06-21 | 2023-08-07 | 2023-09-15 | 2023-10-31 | 74
PIPING SYSTEMS MECHANICAL COMPLETION |  |  | 26 | 2023-07-21 | 2023-08-21 | 2023-10-02 | 2023-10-24 | 56
0 | FSPI3010 | WHP 10 - MECHANICAL COMPLETION - CHEMICAL INJECTION SYSTEM | 10 | 2023-07-21 | 2023-08-02 | 2023-10-02 | 2023-10-12 | 62
0 | FSPI3000 | WHP 10 - MECHANICAL COMPLETION - PRODUCTION SYSTEM | 10 | 2023-07-26 | 2023-08-07 | 2023-10-06 | 2023-10-17 | 62
0 | FSPI3020 | WHP 10 - MECHANICAL COMPLETION - WATER INJECTION SYSTEM | 10 | 2023-07-31 | 2023-08-11 | 2023-10-11 | 2023-10-21 | 62
0 | FSPI3030 | WHP 10 - MECHANICAL COMPLETION - CLOSED/OPEN DRAIN SYSTEM | 10 | 2023-08-02 | 2023-08-14 | 2023-10-13 | 2023-10-24 | 62
0 | FSPI3040 | WHP 10 - MECHANICAL COMPLETION - VENT SYSTEM | 10 | 2023-08-09 | 2023-08-21 | 2023-10-13 | 2023-10-24 | 56
PUNCHLIST CLEARANCE - PIPING |  |  | 60 | 2023-05-19 | 2023-07-28 | 2023-08-16 | 2023-10-24 | 76
0 | FSPI4000 | WHP 10 - PUNCHLIST CLEARANCE - PIPING | 60 | 2023-05-19 | 2023-07-28 | 2023-08-16 | 2023-10-24 | 76
PIPING PWHT |  |  | 115 | 2023-02-08 | 2023-06-22 | 2023-05-16 | 2023-09-11 | 70
0 | FSPI5000 | WHP 10 - PWHT - FABRICATED SPOOLS | 72 | 2023-02-08 | 2023-05-03 | 2023-05-16 | 2023-08-07 | 83
0 | FSPI5010 | WHP 10 - PWHT - ERECTED SPOOLS | 72 | 2023-03-30 | 2023-06-22 | 2023-06-20 | 2023-09-11 | 70
MECHANICAL EQUIPMENT |  |  | 96 | 2023-04-03 | 2023-07-24 | 2023-06-05 | 2023-10-06 | 65
CELLAR DECK |  |  | 21 | 2023-05-15 | 2023-06-08 | 2023-08-02 | 2023-08-11 | 56
0 | FSME1010 | WHP 10 - INSTALL - DRAIN SUMP PUMP | 6 | 2023-05-15 | 2023-05-22 | 2023-08-02 | 2023-08-08 | 68
0 | FSME1000 | WHP 10 - INSTALL - VENT DRAIN TANK | 6 | 2023-06-01 | 2023-06-08 | 2023-08-05 | 2023-08-11 | 56
MAIN DECK |  |  | 96 | 2023-04-03 | 2023-07-24 | 2023-06-05 | 2023-10-06 | 65
0 | FSME1020 | WHP 10 - INSTALL - PIG LAUNCHER/ RECEIVER (730-L-001) | 12 | 2023-04-03 | 2023-04-17 | 2023-06-05 | 2023-06-17 | 54
0 | FSME1030 | WHP 10 - INSTALL - PORTABLE BIOCIDE INJECTION PACKAGE | 6 | 2023-04-17 | 2023-04-24 | 2023-08-01 | 2023-08-07 | 91
0 | FSME1040 | WHP 10 - INSTALL - MONORAIL/HOIST | 70 | 2023-05-03 | 2023-07-24 | 2023-07-18 | 2023-10-06 | 65
WEATHER DECK |  |  | 70 | 2023-04-24 | 2023-07-14 | 2023-07-18 | 2023-10-06 | 73
0 | FSME1050 | WHP 10 - INSTALL - MONORAIL/HOIST | 70 | 2023-04-24 | 2023-07-14 | 2023-07-18 | 2023-10-06 | 73
ELECTRICAL |  |  | 126 | 2023-04-04 | 2023-08-29 | 2023-06-23 | 2023-11-16 | 69
GENERAL |  |  | 126 | 2023-04-04 | 2023-08-29 | 2023-06-23 | 2023-11-16 | 69
0 | FSEL1042 | WHP 10 - MATERIAL INSPECTION & PRESERVATION | 126 | 2023-04-04 | 2023-08-29 | 2023-06-23 | 2023-11-16 | 69
CABLE TRAYS |  |  | 47 | 2023-04-25 | 2023-06-19 | 2023-07-03 | 2023-08-26 | 60
0 | FSEL1040 | WHP 10 - INSTALL - SECONDARY CABLE TRAYS | 42 | 2023-04-25 | 2023-06-13 | 2023-07-10 | 2023-08-26 | 65
0 | FSEL1050 | WHP 10 - INSTALL - ELECTRICAL MAIN CABLE TRAYS | 42 | 2023-05-01 | 2023-06-19 | 2023-07-03 | 2023-08-19 | 54
CABLE PULLING, G&T & TESTING |  |  | 60 | 2023-05-18 | 2023-07-27 | 2023-07-20 | 2023-09-27 | 54
0 | FSEL1060 | WHP 10 - PULL - ELECTRICAL CABLES | 42 | 2023-05-18 | 2023-07-06 | 2023-07-20 | 2023-09-06 | 54
0 | FSEL1070 | WHP 10 - GLAND & TERMINATE - ELECTRICAL CABLES | 42 | 2023-06-01 | 2023-07-20 | 2023-08-03 | 2023-09-20 | 54
0 | FSEL1080 | WHP 10 - IR & CONTINUITY CHECK - ELECTRICAL CABLES | 36 | 2023-06-15 | 2023-07-27 | 2023-08-17 | 2023-09-27 | 54
FITTINGS/JB's & SOCKETS |  |  | 24 | 2023-05-20 | 2023-06-17 | 2023-07-26 | 2023-09-04 | 68
0 | FSEL1090 | WHP 10 - INSTALL LIGHT FITTINGS/JBs/SOCKETS | 12 | 2023-05-20 | 2023-06-03 | 2023-07-26 | 2023-08-08 | 57
0 | FSEL1100 | WHP 10 - INSTALL - INSTALL EARTHING | 12 | 2023-05-27 | 2023-06-10 | 2023-08-14 | 2023-08-26 | 67
0 | FSEL1110 | WHP 10 - INSTALL - SMALL POWER / LIGHTING DB'S | 12 | 2023-06-03 | 2023-06-17 | 2023-08-22 | 2023-09-04 | 68
ELECTRICAL EQUIPMENTS |  |  | 49 | 2023-04-06 | 2023-06-02 | 2023-07-17 | 2023-09-06 | 83
0 | FSEL1130 | WHP 10 - INSTALL - LV DISTRIBUTION BOARD INSTALLATION - MEZZ DECK | 18 | 2023-04-06 | 2023-04-27 | 2023-07-27 | 2023-08-16 | 96
0 | FSEL1160 | WHP 10 - INSTALL - TRANSFRMER INSTALLLATION - WEATHER DECK | 6 | 2023-04-24 | 2023-05-01 | 2023-08-21 | 2023-08-26 | 102
0 | FSEL1120 | WHP 10 - INSTALL - BIRD DETTERENT SYSTEM - MEZZ DECK | 12 | 2023-04-19 | 2023-05-03 | 2023-07-31 | 2023-08-12 | 88
0 | FSEL1170 | WHP 10 - INSTALL - TUTU BOX- CELLAR DECK | 12 | 2023-04-24 | 2023-05-08 | 2023-08-04 | 2023-08-17 | 88
0 | FSEL1140 | WHP 10 - INSTALL - NAVIGATION AID SYSTEM - WEATHER/ CELLAR/ MEZZ DECK | 24 | 2023-04-17 | 2023-05-15 | 2023-07-17 | 2023-08-12 | 78
0 | FSEL1150 | WHP 10 - INSTALL - AC UPS SYSTEM - MEZZ DECK | 24 | 2023-04-18 | 2023-05-16 | 2023-07-29 | 2023-08-25 | 88
0 | FSEL1180 | WHP 10 - INSTALL - 415V SWITCHBOARD - MEZZ DECK | 18 | 2023-04-27 | 2023-05-18 | 2023-08-17 | 2023-09-06 | 96
0 | FSEL1190 | WHP 10 - INSTALL - 6.6 Kv RMU INSTALLATION - WEATHER DECK | 18 | 2023-05-12 | 2023-06-02 | 2023-08-07 | 2023-08-26 | 74
ELECTRICAL SYSTEMS MECHANICAL COMPLETION |  |  | 18 | 2023-07-13 | 2023-08-03 | 2023-09-14 | 2023-10-06 | 56
0 | FSEL2000 | WHP 10 - MECHANICAL COMPLETION - POWER SYSTEM | 10 | 2023-07-13 | 2023-07-25 | 2023-09-14 | 2023-09-25 | 54
0 | FSEL2010 | WHP 10 - MECHANICAL COMPLETION - LIGHTING SYSTEM | 12 | 2023-07-20 | 2023-08-03 | 2023-09-23 | 2023-10-06 | 56
PUNCHLIST CLEARANCE - ELECTRICAL |  |  | 20 | 2023-07-17 | 2023-08-09 | 2023-09-20 | 2023-10-12 | 56
0 | FSEL4000 | WHP 10 - PUNCHLIST CLEARANCE - ELECTRICAL | 20 | 2023-07-17 | 2023-08-09 | 2023-09-20 | 2023-10-12 | 56
INSTRUMENTATION/TELECOM |  |  | 110 | 2023-04-12 | 2023-08-18 | 2023-07-14 | 2023-10-24 | 58
CABLE TRAYS & CABLE PULLING |  |  | 67 | 2023-05-25 | 2023-08-11 | 2023-07-28 | 2023-10-12 | 54
0 | FSIN1020 | WHP 10 - PULL - INSTRUMENT CABLES | 42 | 2023-05-25 | 2023-07-13 | 2023-07-28 | 2023-09-14 | 55
0 | FSIN1010 | WHP 10 - GLAND/TERMINATE - INSTRUMENT CABLES | 42 | 2023-06-16 | 2023-08-04 | 2023-08-18 | 2023-10-05 | 54
0 | FSIN1000 | WHP 10 - IR & CONTINUITY CHECK - INSTRUMENT CABLES | 36 | 2023-06-30 | 2023-08-11 | 2023-09-01 | 2023-10-12 | 54
INSTRUMENTS INSTALLATION |  |  | 87 | 2023-04-12 | 2023-07-22 | 2023-07-14 | 2023-09-27 | 58
0 | FSIN1180 | WHP 10 - INSTRUMENT CALIBIRATION | 42 | 2023-04-12 | 2023-05-31 | 2023-07-20 | 2023-09-06 | 85
0 | FSIN1040 | WHP 10 - INSTALL - F&G DETECTORS | 30 | 2023-05-01 | 2023-06-05 | 2023-07-14 | 2023-08-17 | 64
0 | FSIN1050 | WHP 10 - INSTALL - FIELD INSTRUMENTS | 42 | 2023-06-03 | 2023-07-22 | 2023-08-10 | 2023-09-27 | 58
PANELS & JB's |  |  | 42 | 2023-05-27 | 2023-07-15 | 2023-08-02 | 2023-09-19 | 57
0 | FSIN1060 | WHP 10 - INSTALL - JUNCTION BOXES/ MARSHALING BOXES / SPLITTER BOXES | 42 | 2023-05-27 | 2023-07-15 | 2023-08-02 | 2023-09-19 | 57
INSTRUMENT EQUIPMENTS |  |  | 60 | 2023-05-12 | 2023-07-21 | 2023-07-14 | 2023-10-05 | 66
0 | FSIN1200 | WHP 10 - INSTALL IRCD SKID | 9 | 2023-05-19 | 2023-05-30 | 2023-08-08 | 2023-08-17 | 69
0 | FSIN1170 | WHP 10 - INSTALL TELECOM EQUIPMENTS - MAIN DECK/MEZZ DECK | 18 | 2023-05-12 | 2023-06-02 | 2023-07-14 | 2023-08-03 | 54
0 | FSIN1100 | WHP 10 - INSTALL ICSS SYSTEM - MEZZ DECK | 12 | 2023-05-27 | 2023-06-10 | 2023-08-04 | 2023-08-17 | 59
0 | FSIN1090 | WHP 10 - INSTALL HIPPS SYSTEM - MAIN DECK | 12 | 2023-05-29 | 2023-06-10 | 2023-08-04 | 2023-08-17 | 58
0 | FSIN1080 | WHP 10 - INSTALL WELLHEAD CONTROL PANEL - MEZZ DECK | 12 | 2023-06-02 | 2023-06-16 | 2023-08-04 | 2023-08-17 | 54
0 | FSIN1070 | WHP 10 - INSTALL INSTRUMENT VALVES - MAIN/ MEZZ/ CELLAR DECK | 24 | 2023-06-23 | 2023-07-21 | 2023-08-31 | 2023-09-27 | 59
0 | FSIN1110 | WHP 10 - INSTALL FLOW METERS - MAIN / MEZZ DECK | 24 | 2023-06-23 | 2023-07-21 | 2023-09-08 | 2023-10-05 | 66
INSTRUMENT TUBING & INCONEL PIPING |  |  | 46 | 2023-06-17 | 2023-08-10 | 2023-08-28 | 2023-10-16 | 58
0 | FSIN1190 | WHP 10 - INSTALL - INSTRUMENT PIPING | 36 | 2023-06-17 | 2023-07-29 | 2023-08-29 | 2023-10-09 | 62
0 | FSIN1130 | WHP 10 - INSTALL - INSTRUMENT TUBING | 36 | 2023-06-21 | 2023-08-02 | 2023-08-28 | 2023-10-07 | 58
0 | FSIN1120 | WHP 10 - PRESSURE TEST - INSTRUMENT TUBING | 21 | 2023-07-17 | 2023-08-10 | 2023-09-22 | 2023-10-16 | 58
INSTRUMENT/TELECOM SYSTEMS MECHANICAL COMPLETION |  |  | 40 | 2023-06-30 | 2023-08-16 | 2023-10-05 | 2023-10-24 | 60
0 | FSIN1150 | WHP 10 - MECHANICAL COMPLETION - TELECOM SYSTEM | 12 | 2023-06-30 | 2023-07-14 | 2023-10-05 | 2023-10-18 | 83
0 | FSIN1140 | WHP 10 - MECHANICAL COMPLETION - CONTROL SYSTEM | 12 | 2023-08-02 | 2023-08-16 | 2023-10-11 | 2023-10-24 | 60
PUNCHLIST CLEARANCE - INSTRUMENT |  |  | 21 | 2023-07-25 | 2023-08-18 | 2023-09-30 | 2023-10-24 | 58
0 | FSIN1160 | WHP 10 - PUNCHLIST CLEARANCE - INSTRUMENTATION | 21 | 2023-07-25 | 2023-08-18 | 2023-09-30 | 2023-10-24 | 58
SAFETY |  |  | 47 | 2023-07-01 | 2023-08-25 | 2023-09-16 | 2023-10-26 | 54
0 | FSSA1010 | WHP 10 - INSTALLATION OF SAFETY EQUIPMENT | 20 | 2023-07-01 | 2023-07-25 | 2023-09-16 | 2023-10-09 | 66
0 | FSSA1000 | WHP 10 - INSTALLATION OF SAFETY SIGN | 15 | 2023-08-08 | 2023-08-25 | 2023-10-10 | 2023-10-26 | 54
PAINTING |  |  | 276 | 2022-10-20 | 2023-09-07 | 2023-02-14 | 2023-11-16 | 61
BLAST/PAINT- MAIN STRUCTURE |  |  | 158 | 2022-10-20 | 2023-04-22 | 2023-02-14 | 2023-08-28 | 110
BLAST/PAINT- CELLAR DECK |  |  | 90 | 2022-10-20 | 2023-02-02 | 2023-02-23 | 2023-05-06 | 81
0 | FSSTPN1000 | WHP 10 - BLAST/PAINT - DECK BRACES (BTWN CELLAR & MAIN DECK) | 24 | 2022-10-20 | 2022-11-17 | 2023-02-23 | 2023-03-22 | 108
0 | FSSTPN1010 | WHP 10 - BLAST/PAINT - DECK LEGS (BTWN CELLAR, & MAIN DECK) | 15 | 2022-11-24 | 2022-12-12 | 2023-03-06 | 2023-03-22 | 87
0 | FSSTPN1020 | WHP 10 - BLAST/PAINT - CELLAR DECK | 21 | 2023-01-09 | 2023-02-02 | 2023-04-13 | 2023-05-06 | 81
BLAST/PAINT- MAIN DECK |  |  | 75 | 2022-11-07 | 2023-02-02 | 2023-02-14 | 2023-04-27 | 73
0 | FSSTPN1030 | WHP 10 - BLAST/PAINT - DECK BRACES (BTWN MAIN DECK & MEZZANINE DECK) | 24 | 2022-11-07 | 2022-12-05 | 2023-02-14 | 2023-03-13 | 85
0 | FSSTPN1040 | WHP 10 - BLAST/PAINT - DECK LEGS (BTWN MAIN DECK & MEZZANINE DECK) | 15 | 2022-11-17 | 2022-12-05 | 2023-02-24 | 2023-03-13 | 85
0 | FSSTPN1050 | WHP 10 - BLAST/PAINT - MAIN DECK | 21 | 2023-01-09 | 2023-02-02 | 2023-04-04 | 2023-04-27 | 73
BLAST/PAINT- MEZZANINE DECK |  |  | 78 | 2022-11-21 | 2023-02-20 | 2023-03-16 | 2023-05-27 | 84
0 | FSSTPN1070 | WHP 10 - BLAST/PAINT - DECK LEGS (BTWN MEZZANINE DECK & WEATHER DK) | 15 | 2022-11-24 | 2022-12-12 | 2023-03-27 | 2023-04-12 | 105
0 | FSSTPN1060 | WHP 10 - BLAST/PAINT - DECK BRACES (BTWN MEZZANINE DECK & WEATHER DK) | 24 | 2022-11-21 | 2022-12-19 | 2023-03-16 | 2023-04-12 | 99
0 | FSSTPN1080 | WHP 10 - BLAST/PAINT - MEZZANINE DECK | 21 | 2023-01-26 | 2023-02-20 | 2023-05-04 | 2023-05-27 | 84
BLAST/PAINT- ACCESS PLATFORM |  |  | 21 | 2023-02-20 | 2023-03-16 | 2023-05-01 | 2023-05-24 | 60
0 | FSSTPN1090 | WHP 10 - BLAST/PAINT - ACCESS PLATFORMS | 21 | 2023-02-20 | 2023-03-16 | 2023-05-01 | 2023-05-24 | 60
BLAST/PAINT-WEATHE DECK |  |  | 21 | 2023-02-27 | 2023-03-23 | 2023-05-22 | 2023-06-14 | 72
0 | FSSTPN1100 | WHP 10 - BLAST/PAINT - WEATHER DECK | 21 | 2023-02-27 | 2023-03-23 | 2023-05-22 | 2023-06-14 | 72
BLAST/PAINT- HELI DECK |  |  | 21 | 2023-03-29 | 2023-04-22 | 2023-08-04 | 2023-08-28 | 110
0 | FSSTPN1110 | WHP 10 - BLAST/PAINT - HELI DECK | 21 | 2023-03-29 | 2023-04-22 | 2023-08-04 | 2023-08-28 | 110
BLAST/PAINT- OTHER STRUCT/ACCESSORIES |  |  | 201 | 2023-01-16 | 2023-09-07 | 2023-05-06 | 2023-11-16 | 61
GALVANIZE/PAINT - HANDRAILS/LADDERS |  |  | 81 | 2023-01-16 | 2023-04-20 | 2023-05-08 | 2023-09-30 | 141
0 | FSSTPN1200 | WHP 10 - GALVANIZE - HANDRAILS CELLAR DECK | 18 | 2023-01-16 | 2023-02-06 | 2023-05-08 | 2023-05-27 | 96
0 | FSSTPN1190 | WHP 10 - GALVANIZE - HANDRAILS MAIN DECK | 18 | 2023-01-30 | 2023-02-20 | 2023-05-24 | 2023-06-13 | 98
0 | FSSTPN1160 | WHP 10 - PAINT - HANDRAILS CELLAR DECK | 18 | 2023-02-06 | 2023-02-27 | 2023-05-29 | 2023-06-17 | 96
0 | FSSTPN1180 | WHP 10 - GALVANIZE - HANDRAILS (MEZZANINE DECK) | 18 | 2023-02-13 | 2023-03-06 | 2023-07-19 | 2023-08-08 | 134
0 | FSSTPN1150 | WHP 10 - PAINT - HANDRAILS MAIN DECK | 18 | 2023-02-20 | 2023-03-13 | 2023-06-14 | 2023-07-04 | 98
0 | FSSTPN1170 | WHP 10 - GALVANIZE - HANDRAILS (WEATHER DECK) | 22 | 2023-02-27 | 2023-03-24 | 2023-08-16 | 2023-09-09 | 146
0 | FSSTPN1140 | WHP 10 - PAINT - HANDRAILS (MEZZANINE DECK) | 18 | 2023-03-06 | 2023-03-27 | 2023-08-09 | 2023-08-29 | 134
0 | FSSTPN1130 | WHP 10 - PAINT - HANDRAILS (WEATHER DECK) | 18 | 2023-03-24 | 2023-04-14 | 2023-09-11 | 2023-09-30 | 146
0 | FSSTPN1120 | WHP 10 - BLAST/PAINT - LADDERS & CAGES | 60 | 2023-02-09 | 2023-04-20 | 2023-06-07 | 2023-08-15 | 101
BLAST/PAINT - STAIRWAYS |  |  | 72 | 2023-03-27 | 2023-06-19 | 2023-08-18 | 2023-10-05 | 94
EAST SIDE |  |  | 36 | 2023-03-27 | 2023-05-08 | 2023-09-04 | 2023-09-23 | 120
0 | FSSTPN1210 | WHP 10 - BLAST/PAINT - CELLAR DECK TO JACKET WALKWAY (EAST SIDE) | 18 | 2023-03-27 | 2023-04-17 | 2023-09-04 | 2023-09-23 | 138
0 | FSSTPN1220 | WHP 10 - BLAST/PAINT - MAIN DECK TO CELLAR DECK (EAST SIDE) | 18 | 2023-04-03 | 2023-04-24 | 2023-09-04 | 2023-09-23 | 132
0 | FSSTPN1230 | WHP 10 - BLAST/PAINT - MEZZANINE DECK TO MAIN DECK (EAST SIDE) | 18 | 2023-04-10 | 2023-05-01 | 2023-09-04 | 2023-09-23 | 126
0 | FSSTPN1240 | WHP 10 - BLAST/PAINT - MAIN DECK TO MEZZANINE DECK (EAST SIDE) | 18 | 2023-04-17 | 2023-05-08 | 2023-09-04 | 2023-09-23 | 120
NORTH SIDE |  |  | 39 | 2023-04-06 | 2023-05-22 | 2023-08-25 | 2023-09-14 | 100
0 | FSSTPN1250 | WHP 10 - BLAST/PAINT - MONKEY LADDER FROM MAIN. DECK TO CELLAR DECK (NORTH SIDE) | 18 | 2023-04-06 | 2023-04-27 | 2023-08-25 | 2023-09-14 | 121
0 | FSSTPN1260 | WHP 10 - BLAST/PAINT - MONKEY LADDER FROM MEZZANINE DECK TO MAIN DECK (NORTH SIDE) | 18 | 2023-04-20 | 2023-05-11 | 2023-08-25 | 2023-09-14 | 109
0 | FSSTPN1270 | WHP 10 - BLAST/PAINT - MONKEY LADDER FROM MAIN DECK TO MEZZANINE DECK (NORTH SIDE) | 18 | 2023-05-01 | 2023-05-22 | 2023-08-25 | 2023-09-14 | 100
OTHER MISCELLENEOUS |  |  | 42 | 2023-05-01 | 2023-06-19 | 2023-08-18 | 2023-10-05 | 94
0 | FSSTPN1280 | WHP 10 - BLAST/PAINT - STAIRWAYS (OTHER MISC.) | 42 | 2023-05-01 | 2023-06-19 | 2023-08-18 | 2023-10-05 | 94
BLAST/PAINT - PIPE SUPPORTS |  |  | 60 | 2023-02-27 | 2023-05-08 | 2023-05-06 | 2023-07-14 | 59
0 | FSSTPN1290 | WHP 10 - BLAST/PAINT - BALANCE PIPE SUPPORTS | 60 | 2023-02-27 | 2023-05-08 | 2023-05-06 | 2023-07-14 | 59
BLAST/PAINTING - PIPING |  |  | 63 | 2023-02-27 | 2023-05-11 | 2023-05-30 | 2023-08-02 | 72
0 | FSPIPN1000 | WHP 10 - BLAST/PAINT - CU-NI/ INCONEL PIPING SPOOLS | 42 | 2023-03-06 | 2023-04-24 | 2023-06-09 | 2023-07-27 | 82
0 | FSPIPN1020 | WHP 10 - BLAST/PAINT - CS/LTCS / CLADDED PIPING SPOOLS | 56 | 2023-02-27 | 2023-05-03 | 2023-05-30 | 2023-08-02 | 79
0 | FSPIPN1010 | WHP 10 - BLAST/PAINT - SS PIPING SPOOLS | 30 | 2023-04-06 | 2023-05-11 | 2023-06-16 | 2023-07-20 | 61
BLAST/PAINT - EQUIPMENT SUPPORTS |  |  | 42 | 2023-04-24 | 2023-06-12 | 2023-07-18 | 2023-09-12 | 80
0 | FSSTPN1300 | WHP 10 - BLAST/PAINT - VENT SUPPORT STRUCTURE | 24 | 2023-05-01 | 2023-05-29 | 2023-08-16 | 2023-09-12 | 92
0 | FSSTPN1310 | WHP 10 - BLAST/PAINT - BALANCE EQUIPMENT SUPPORTS | 42 | 2023-04-24 | 2023-06-12 | 2023-07-18 | 2023-09-04 | 73
BLAST/PAINT - E&I SUPPORTS |  |  | 56 | 2023-03-25 | 2023-05-30 | 2023-05-27 | 2023-07-31 | 54
0 | FSSTPN1330 | WHP 10 - BLAST/PAINT - SECONDARY CABLE TRAY SUPPORTS | 42 | 2023-03-28 | 2023-05-16 | 2023-06-12 | 2023-07-29 | 65
0 | FSSTPN1320 | WHP 10 - BLAST/PAINT - BALANCE MAIN CABLE TRAY SUPPORTS | 56 | 2023-03-25 | 2023-05-30 | 2023-05-27 | 2023-07-31 | 54
BLAST/PAINT - OTHER SUPPORTS |  |  | 71 | 2023-03-22 | 2023-06-13 | 2023-05-27 | 2023-08-18 | 58
0 | FSSTPN1360 | WHP 10 - BLAST/PAINT - OTHER E&I SUPPORTS MAIN DECK | 30 | 2023-03-22 | 2023-04-26 | 2023-05-27 | 2023-06-30 | 57
0 | FSSTPN1370 | WHP 10 - BLAST/PAINT - OTHER E&I SUPPORTS (CELLAR DDK) | 30 | 2023-03-24 | 2023-04-28 | 2023-05-30 | 2023-07-03 | 57
0 | FSSTPN1350 | WHP 10 - BLAST/PAINT - OTHER E&I SUPPORTS (MEZZANINE DK) | 30 | 2023-03-29 | 2023-05-03 | 2023-06-03 | 2023-07-07 | 57
0 | FSSTPN1340 | WHP 10 - BLAST/PAINT - OTHER E&I SUPPORTS (WEATHER MDK) | 30 | 2023-04-07 | 2023-05-12 | 2023-06-14 | 2023-07-18 | 58
0 | FSSTPN1380 | WHP 10 - BLAST/PAINT - BALANCE OTHER E&I SUPPORTS | 56 | 2023-04-08 | 2023-06-13 | 2023-06-15 | 2023-08-18 | 58
BLAST/PAINT - OTHER STRUCTURES |  |  | 146 | 2023-02-10 | 2023-07-31 | 2023-05-17 | 2023-10-07 | 60
0 | FSSTPN1440 | WHP 10 - BLAST/PAINT - STABBING GUIDES | 12 | 2023-02-15 | 2023-03-01 | 2023-05-17 | 2023-05-30 | 78
0 | FSSTPN1390 | WHP 10 - BLAST/PAINT - DECK PAD EYES | 24 | 2023-02-22 | 2023-03-22 | 2023-06-12 | 2023-07-08 | 94
0 | FSSTPN1430 | WHP 10 - BLAST/PAINT - MONORAILS FRAME | 60 | 2023-02-10 | 2023-04-21 | 2023-06-07 | 2023-08-15 | 100
0 | FSSTPN1450 | WHP 10 - BLAST/PAINT - FLARE BOOM | 18 | 2023-04-15 | 2023-05-06 | 2023-08-22 | 2023-09-11 | 110
0 | FSSTPN1420 | WHP 10 - BLAST/PAINT - DECK HATCHES | 30 | 2023-04-05 | 2023-05-10 | 2023-07-31 | 2023-09-02 | 100
0 | FSSTPN1400 | WHP 10 - BLAST/PAINT - GRATINGS | 42 | 2023-04-10 | 2023-05-29 | 2023-08-12 | 2023-09-29 | 107
0 | FSSTPN1410 | WHP 10 - BLAST/PAINT - PLATFORM IDENTIFICATION PANELS | 18 | 2023-05-27 | 2023-06-17 | 2023-09-04 | 2023-09-23 | 85
0 | FSSTPN1460 | WHP 10 - BLAST/PAINT - MISCELLANEOUS STRUCTRUAL ITEMS | 60 | 2023-05-22 | 2023-07-31 | 2023-07-31 | 2023-10-07 | 60
FINAL TOUCH-UP PAINTING |  |  | 100 | 2023-05-13 | 2023-09-07 | 2023-07-24 | 2023-11-16 | 61
0 | FSSTPN1470 | WHP 10 - FIRE PROOFING ON DECK STRUCTURE | 60 | 2023-06-08 | 2023-08-17 | 2023-08-10 | 2023-10-18 | 54
0 | FSSTPN1480 | WHP 10 - FINAL PAINT & TOUCH-UP PAINTING | 100 | 2023-05-13 | 2023-09-07 | 2023-07-24 | 2023-11-16 | 61
MISCELLANEOUS WORKS |  |  | 42 | 2023-05-11 | 2023-06-29 | 2023-09-15 | 2023-11-02 | 109
0 | FSST5000 | WHP 10 - MISCELLANEOUS WORKS | 42 | 2023-05-11 | 2023-06-29 | 2023-09-15 | 2023-11-02 | 109
COMMISIONING |  |  | 45 | 2023-07-25 | 2023-09-15 | 2023-09-26 | 2023-11-16 | 54
0 | FSCG1030 | WHP 10 - 415V AUXILIARY DB | 3 | 2023-07-27 | 2023-07-31 | 2023-10-02 | 2023-10-04 | 57
0 | FSCG1040 | WHP 10 - 24V DC UPS BATTERY CHARGER & BATTERY | 6 | 2023-07-28 | 2023-08-04 | 2023-10-03 | 2023-10-09 | 57
0 | FSCG1020 | WHP 10 - 415 V SWITCHGEAR (2 I/C +15 FDRS.+ 3 SPR.) | 15 | 2023-07-25 | 2023-08-11 | 2023-09-26 | 2023-10-12 | 54
0 | FSCG1090 | WHP 10 - MOV POWER DB | 2 | 2023-08-11 | 2023-08-14 | 2023-10-21 | 2023-10-23 | 61
0 | FSCG1080 | WHP 10 - TELECOM & LAN SYSTEM - 3 NOS | 5 | 2023-08-11 | 2023-08-17 | 2023-10-19 | 2023-10-24 | 59
0 | FSCG1100 | WHP 10 - NAVIGATIONAL AID SYSTEM | 3 | 2023-08-14 | 2023-08-17 | 2023-10-24 | 2023-10-26 | 61
0 | FSCG1050 | WHP 10 - ECMS SYSTEM | 14 | 2023-08-03 | 2023-08-19 | 2023-10-09 | 2023-10-24 | 57
0 | FSCG1110 | WHP 10 - CCTV SYSTEM - 3 NOS | 3 | 2023-08-16 | 2023-08-19 | 2023-10-24 | 2023-10-26 | 59
0 | FSCG1130 | WHP 10 - BIRD DETERRENT SYSTEM- | 2 | 2023-08-19 | 2023-08-22 | 2023-10-27 | 2023-10-28 | 59
0 | FSCG1140 | WHP 10 - UHF RADIO - 3 NOS | 2 | 2023-08-19 | 2023-08-22 | 2023-10-27 | 2023-10-28 | 59
0 | FSCG1060 | WHP 10 - RTU SYSTEM (OTP & LOOP CHECKING) | 14 | 2023-08-07 | 2023-08-23 | 2023-10-09 | 2023-10-24 | 54
0 | FSCG1120 | WHP 10 - WELL HEAD CONTROL PANEL (OTP & LOOP CHECKING) | 6 | 2023-08-17 | 2023-08-24 | 2023-10-26 | 2023-11-01 | 60
0 | FSCG1150 | WHP 10 - 6.6 KV RMU SYSTEM | 6 | 2023-08-18 | 2023-08-25 | 2023-10-26 | 2023-11-01 | 59
0 | FSCG1190 | WHP 10 - CLOSED DRAIN | 3 | 2023-08-23 | 2023-08-26 | 2023-10-25 | 2023-10-27 | 54
0 | FSCG1070 | WHP 10 - ESD SYSTEM (OTP & LOOP CHECKING) | 14 | 2023-08-11 | 2023-08-28 | 2023-10-14 | 2023-10-30 | 55
0 | FSCG1170 | WHP 10 - HIPPS (OTP & LOOP CHECKING | 5 | 2023-08-25 | 2023-08-31 | 2023-10-28 | 2023-11-02 | 55
0 | FSCG1180 | WHP 10 - 6.6KV / 433V POWER TRANSFORMER | 4 | 2023-08-26 | 2023-08-31 | 2023-10-30 | 2023-11-02 | 55
0 | FSCG1200 | WHP 10 - COMM -CHEMICAL INJECTION | 4 | 2023-08-26 | 2023-08-31 | 2023-10-28 | 2023-11-01 | 54
0 | FSCG1240 | WHP 10 - MPFM - COMMUNICATION ESTABLISHMENT | 3 | 2023-08-31 | 2023-09-04 | 2023-11-02 | 2023-11-04 | 54
0 | FSCG1220 | WHP 10 - WELL SLOT-1 (WELL#626) | 6 | 2023-08-29 | 2023-09-05 | 2023-10-31 | 2023-11-06 | 54
0 | FSCG1210 | WHP 10 - LIGHTING SYSTEM | 5 | 2023-08-31 | 2023-09-06 | 2023-11-03 | 2023-11-08 | 55
0 | FSCG1160 | WHP 10 - FIRE &GAS SYSTEM (OTP & LOOP CHECKING) | 11 | 2023-08-25 | 2023-09-07 | 2023-10-28 | 2023-11-09 | 55
0 | FSCG1250 | WHP 10 - PRODUCTION MANIFOLD | 3 | 2023-09-04 | 2023-09-07 | 2023-11-06 | 2023-11-08 | 54
0 | FSCG1260 | WHP 10 - COMM -PIG LAUNCHER/RECEIVER | 3 | 2023-09-07 | 2023-09-11 | 2023-11-09 | 2023-11-11 | 54
0 | FSCG1270 | WHP 10 - VENT & DRAIN SYSTEM OTP | 4 | 2023-09-08 | 2023-09-13 | 2023-11-10 | 2023-11-14 | 54
0 | FSCG1280 | WHP 10 - FIRE FIGHTING & SAFETY EQUIPMENT | 3 | 2023-09-09 | 2023-09-13 | 2023-11-11 | 2023-11-14 | 54
0 | FSCG1230 | WHP 10 - LEAK TEST | 14 | 2023-08-30 | 2023-09-15 | 2023-11-01 | 2023-11-16 | 54
READY FOR LOADOUT |  |  | 18 | 2023-08-25 | 2023-09-15 | 2023-10-27 | 2023-11-16 | 54
0 | FSLO1010 | WHP 10 - FINAL DECK WEIGHING | 6 | 2023-08-25 | 2023-09-01 | 2023-10-27 | 2023-11-02 | 54
0 | FSLO1000 | WHP 10 - READY FOR LOADOUT - WHP-10 TOPSIDE | 0 |  | 2023-09-15 |  | 2023-11-16 | 54
0 | FSLO2010 | WHP 10 - COMPANY WALK THROUGH AND PUNCH LIST CLEARANCE | 12 | 2023-09-01 | 2023-09-15 | 2023-11-03 | 2023-11-16 | 54
FABRICATION HAIR DALMA WHP HD-T4 TOPSIDE |  |  | 378 | 2022-09-29 | 2023-10-12 | 2023-02-14 | 2024-03-13 | 153
STRUCTURAL |  |  | 307 | 2022-09-29 | 2023-09-22 | 2023-03-01 | 2024-03-04 | 141
STRUCTURAL PRE-FABRICATION |  |  | 257 | 2022-09-29 | 2023-07-26 | 2023-03-01 | 2024-03-04 | 191
PRE-FAB PLATES |  |  | 109 | 2022-09-29 | 2023-02-03 | 2023-03-01 | 2023-08-02 | 155
0 | FTST1010 | HD-T4 - CUT & PROFILE - PLATES (MAIN DECK) | 15 | 2022-09-29 | 2022-10-17 | 2023-03-01 | 2023-03-17 | 131
0 | FTST1000 | HD-T4 - CUT & PROFILE - PLATES CELLAR DECK | 15 | 2022-10-07 | 2022-10-25 | 2023-03-09 | 2023-03-25 | 131
0 | FTST1020 | HD-T4 - CUT & PROFILE - PLATES (MEZZANINE DECK) | 15 | 2022-10-15 | 2022-11-02 | 2023-03-17 | 2023-04-03 | 131
0 | FTST1030 | HD-T4 - CUT & PROFILE - PLATES (WEATHER DECK) | 15 | 2022-10-24 | 2022-11-10 | 2023-03-25 | 2023-04-11 | 131
0 | FTST1050 | HD-T4 - CUT & PROFILE - PLATES (ACCESSPLATFORM) | 15 | 2022-11-02 | 2022-11-19 | 2023-05-11 | 2023-05-27 | 163
0 | FTST1040 | HD-T4 - CUT & PROFILE - PLATES (HELIDECK, OTHER MISC.) | 48 | 2022-12-09 | 2023-02-03 | 2023-06-08 | 2023-08-02 | 155
PRE-FAB GIRDERS |  |  | 73 | 2022-10-06 | 2022-12-30 | 2023-03-24 | 2023-05-24 | 125
0 | FTST1070 | HD-T4 - SUB ASSEMBLE - GIRDERS (MAIN DECK) | 18 | 2022-10-06 | 2022-10-27 | 2023-04-06 | 2023-04-26 | 156
0 | FTST1060 | HD-T4 - SUB ASSEMBLE - GIRDERS CELLAR DECK | 18 | 2022-10-14 | 2022-11-04 | 2023-04-13 | 2023-05-03 | 155
0 | FTST1080 | HD-T4 - SUB ASSEMBLE - GIRDERS (MEZZANINE DECK) | 18 | 2022-10-22 | 2022-11-12 | 2023-03-24 | 2023-04-13 | 131
0 | FTST1090 | HD-T4 - SUB ASSEMBLE - GIRDERS (WEATHER DECK) | 18 | 2022-11-09 | 2022-11-30 | 2023-04-11 | 2023-05-01 | 131
0 | FTST1100 | HD-T4 - SUB ASSEMBLE - GIRDERS (HELIDECK) | 18 | 2022-12-09 | 2022-12-30 | 2023-05-04 | 2023-05-24 | 125
WORKSHOP SUB-ASSEMBLE - DECK NODES |  |  | 85 | 2022-10-13 | 2023-01-20 | 2023-03-31 | 2023-06-14 | 125
0 | FTST1140 | HD-T4 - SUB ASSEMBLE - NODES (MAIN DECK) | 18 | 2022-10-13 | 2022-11-03 | 2023-04-13 | 2023-05-03 | 156
0 | FTST1110 | HD-T4 - SUB ASSEMBLE - NODES CELLAR DECK | 18 | 2022-10-21 | 2022-11-11 | 2023-04-20 | 2023-05-10 | 155
0 | FTST1130 | HD-T4 - SUB ASSEMBLE - NODES (MEZZANINE DECK) | 18 | 2022-10-29 | 2022-11-19 | 2023-03-31 | 2023-04-20 | 131
0 | FTST5010 | HD-T4 - SUB ASSEMBLE - NODES (ACCESS PLATFORM) | 18 | 2022-11-03 | 2022-11-24 | 2023-05-08 | 2023-05-27 | 159
0 | FTST1120 | HD-T4 - SUB ASSEMBLE - NODES (WEATHER DECK) | 18 | 2022-11-16 | 2022-12-07 | 2023-04-18 | 2023-05-08 | 131
0 | FTST1150 | HD-T4 - SUB ASSEMBLE - NODES (HELIDECK | 18 | 2022-12-30 | 2023-01-20 | 2023-05-25 | 2023-06-14 | 125
PRE-FAB SECTIONS |  |  | 117 | 2022-10-13 | 2023-02-27 | 2023-04-10 | 2023-09-27 | 183
0 | FTST1210 | HD-T4 - CUT & PROFILE - SECTIONS (MAIN DECK) | 21 | 2022-10-13 | 2022-11-07 | 2023-04-10 | 2023-05-03 | 153
0 | FTST1180 | HD-T4 - CUT & PROFILE - SECTIONS CELLAR DECK | 21 | 2022-10-20 | 2022-11-14 | 2023-04-17 | 2023-05-10 | 153
0 | FTST1200 | HD-T4 - CUT & PROFILE - SECTIONS (MEZZANINE DECK) | 21 | 2022-11-03 | 2022-11-28 | 2023-04-24 | 2023-05-17 | 147
0 | FTST1220 | HD-T4 - CUT & PROFILE - SECTIONS (ACCESS PALTFORM) | 18 | 2022-11-17 | 2022-12-08 | 2023-05-08 | 2023-05-27 | 147
0 | FTST1190 | HD-T4 - CUT & PROFILE - SECTIONS (WEATHER DECK) | 21 | 2022-11-24 | 2022-12-19 | 2023-05-12 | 2023-06-05 | 145
0 | FTST1160 | HD-T4 - CUT & PROFILE - SECTIONS (HDK) | 21 | 2022-12-27 | 2023-01-20 | 2023-06-08 | 2023-07-01 | 140
0 | FTST1170 | HD-T4 - CUT & PROFILE - SECTIONS (OTHER MISC.) | 60 | 2022-12-19 | 2023-02-27 | 2023-07-20 | 2023-09-27 | 183
PRE-FAB TUBULARS |  |  | 134 | 2022-10-11 | 2023-03-16 | 2023-03-21 | 2023-09-28 | 169
0 | FTST5020 | HD-T4 - CUT & PROFILE - TUBULARS CELLAR/ MAIN/ MEZZ DECK | 18 | 2022-10-11 | 2022-11-01 | 2023-03-21 | 2023-04-10 | 138
0 | FTST1270 | HD-T4 - CUT & PROFILE - TUBULARS (B/W CELLAR DECK & MAIN DECK | 24 | 2022-10-21 | 2022-11-18 | 2023-04-06 | 2023-05-03 | 143
0 | FTST1260 | HD-T4 - CUT & PROFILE - TUBULARS (B/W (MAIN DECK) & (MEZZANINE DECK) | 24 | 2022-10-28 | 2022-11-25 | 2023-04-13 | 2023-05-10 | 143
0 | FTST1250 | HD-T4 - CUT & PROFILE - TUBULARS (B/W MEZZANINE DECK & WEATHER DECK) | 24 | 2022-11-04 | 2022-12-02 | 2023-04-20 | 2023-05-17 | 143
0 | FTST1280 | HD-T4 - CUT & PROFILE - TUBULARS (B/W ACCESS PLATFORM & MEZZANINE DECK) | 24 | 2022-11-04 | 2022-12-02 | 2023-06-22 | 2023-07-19 | 197
0 | FTST1230 | HD-T4 - CUT & PROFILE - TUBULARS (HELIDECK) | 24 | 2022-12-02 | 2022-12-30 | 2023-05-18 | 2023-06-14 | 143
0 | FTST1240 | HD-T4 - CUT & PROFILE - TUBULARS (OTHER MISC.) | 75 | 2022-12-19 | 2023-03-16 | 2023-07-04 | 2023-09-28 | 169
WORKSHOP SUB-ASSEMBLE - HANDRAILS & LADDERS |  |  | 95 | 2022-12-19 | 2023-04-08 | 2023-07-04 | 2023-10-21 | 169
0 | FTST1330 | HD-T4 - SUB ASSEMBLE - HANDRAILS CELLAR DECK | 36 | 2022-12-19 | 2023-01-30 | 2023-07-04 | 2023-08-14 | 169
0 | FTST5030 | HD-T4 - SUB ASSEMBLE - SUB ASSEMBLE - HANDRAILS (ACCESSPLATFORM) | 18 | 2023-01-16 | 2023-02-06 | 2023-08-17 | 2023-09-06 | 183
0 | FTST1320 | HD-T4 - SUB ASSEMBLE - HANDRAILS (MAIN DECK) | 36 | 2023-01-02 | 2023-02-13 | 2023-07-18 | 2023-08-28 | 169
0 | FTST1310 | HD-T4 - SUB ASSEMBLE - HANDRAILS (MEZZANINE DECK) | 36 | 2023-01-16 | 2023-02-27 | 2023-08-01 | 2023-09-11 | 169
0 | FTST1300 | HD-T4 - SUB ASSEMBLE - HANDRAILS (WEATHER DECK)) | 36 | 2023-02-01 | 2023-03-15 | 2023-08-17 | 2023-09-27 | 169
0 | FTST1290 | HD-T4 - SUB ASSEMBLE - LADDERS & CAGES | 48 | 2023-02-11 | 2023-04-08 | 2023-08-28 | 2023-10-21 | 169
WORKSHOP SUB ASSEMBLE - STAIRWAYS / STAIR TOWER / MAIN LADDER |  |  | 78 | 2023-02-27 | 2023-05-29 | 2023-09-28 | 2023-12-27 | 183
EAST SIDE |  |  | 42 | 2023-02-27 | 2023-04-17 | 2023-09-28 | 2023-11-27 | 193
0 | FTST1340 | HD-T4 - SUB ASSEMBLE - CELLAR DECK TO JACKET WALKWAY (EAST SIDE) | 24 | 2023-02-27 | 2023-03-27 | 2023-09-28 | 2023-10-25 | 183
0 | FTST1350 | HD-T4 - SUB ASSEMBLE - (MAIN DECK) TO CELLAR DECK (EAST SIDE) | 24 | 2023-03-06 | 2023-04-03 | 2023-10-17 | 2023-11-13 | 193
0 | FTST1360 | HD-T4 - SUB ASSEMBLE - MEZZANINE DECK TO (MAIN DECK) (EAST SIDE) | 24 | 2023-03-13 | 2023-04-10 | 2023-10-24 | 2023-11-20 | 193
0 | FTST1370 | HD-T4 - SUB ASSEMBLE - WEATHER DECK TO MEZZANINE DECK (EAST SIDE) | 24 | 2023-03-20 | 2023-04-17 | 2023-10-31 | 2023-11-27 | 193
WEST SIDE |  |  | 42 | 2023-03-13 | 2023-05-01 | 2023-10-12 | 2023-12-06 | 189
0 | FTST1380 | HD-T4 - SUB ASSEMBLE - MAIN LADDER FROM MAIN. DECK TO CELLAR DECKK (WEST SIDE) | 21 | 2023-03-13 | 2023-04-06 | 2023-10-12 | 2023-11-04 | 183
0 | FTST1390 | HD-T4 - SUB ASSEMBLE - MAIN LADDER FROM MEZZANINE DECK TO (MAIN DECK) (WEST SIDE) | 21 | 2023-03-27 | 2023-04-20 | 2023-11-02 | 2023-11-25 | 189
0 | FTST1400 | HD-T4 - SUB ASSEMBLE - MAIN LADDER FROM WEATHER DECK TO MEZZANINE DECK (WEST SIDE) | 21 | 2023-04-06 | 2023-05-01 | 2023-11-13 | 2023-12-06 | 189
OTHER MISCELLANEOUS |  |  | 60 | 2023-03-20 | 2023-05-29 | 2023-10-19 | 2023-12-27 | 183
0 | FTST1410 | HD-T4 - SUB ASSEMBLE - STAIRWAYS (OTHER MISC.) | 60 | 2023-03-20 | 2023-05-29 | 2023-10-19 | 2023-12-27 | 183
FLOOR DRAINS |  |  | 48 | 2022-10-25 | 2022-12-20 | 2023-05-12 | 2023-07-06 | 171
0 | FTST1420 | HD-T4 - SUB ASSEMBLE - FLOOR DRAINS (CELLAR DK) | 21 | 2022-10-25 | 2022-11-18 | 2023-05-12 | 2023-06-05 | 171
0 | FTST1450 | HD-T4 - SUB ASSEMBLE - FLOOR DRAINS (MAIN DECK) | 30 | 2022-11-01 | 2022-12-06 | 2023-05-19 | 2023-06-22 | 171
0 | FTST1440 | HD-T4 - SUB ASSEMBLE - FLOOR DRAINS (MEZZANINE DECK) | 30 | 2022-11-08 | 2022-12-13 | 2023-05-26 | 2023-06-29 | 171
0 | FTST1430 | HD-T4 - SUB ASSEMBLE - FLOOR DRAINS (WEATHER DK) | 30 | 2022-11-15 | 2022-12-20 | 2023-06-02 | 2023-07-06 | 171
WORKSHOP SUB-ASSEMBLE - OTHER STRUCTURES |  |  | 210 | 2022-11-23 | 2023-07-26 | 2023-04-20 | 2024-03-04 | 191
0 | FTST1500 | HD-T4 - SUB ASSEMBLE - DECK PENETRATIONS | 36 | 2022-11-23 | 2023-01-04 | 2023-04-20 | 2023-05-31 | 127
0 | FTST1470 | HD-T4 - SUB ASSEMBLE DECK PADEYES | 45 | 2023-01-04 | 2023-02-25 | 2023-06-01 | 2023-07-22 | 127
0 | FTST1520 | HD-T4 - SUB ASSEMBLE - STABBING GUIDES | 24 | 2023-02-03 | 2023-03-03 | 2023-08-03 | 2023-08-30 | 155
0 | FTST1540 | HD-T4 - SUB ASSEMBLE - MONORAIL FRAMES | 56 | 2023-01-13 | 2023-03-20 | 2023-09-05 | 2023-11-08 | 201
0 | FTST1530 | HD-T4 - SUB ASSEMBLE - DECK HATCHES | 42 | 2023-02-25 | 2023-04-15 | 2023-09-15 | 2023-11-02 | 173
0 | FTST1560 | HD-T4 - SUB ASSEMBLE - FLARE BOOM | 30 | 2023-03-17 | 2023-04-21 | 2023-11-06 | 2023-12-09 | 200
0 | FTST1480 | HD-T4 - SUB ASSEMBLE SAFETY NET | 24 | 2023-04-07 | 2023-05-05 | 2023-08-31 | 2023-09-27 | 125
0 | FTST1550 | HD-T4 - FABRICATE MISCELLANEOUS ITEMS | 60 | 2023-03-17 | 2023-05-26 | 2023-11-06 | 2024-01-13 | 200
0 | FTST1580 | HD-T4 - FABRICATE HELIDECK DRAIN/GUTTER | 60 | 2023-03-17 | 2023-05-26 | 2023-12-26 | 2024-03-04 | 243
0 | FTST1510 | HD-T4 - SUB ASSEMBLE - PLATFORM IDENTIFICATION PANELS | 42 | 2023-04-24 | 2023-06-12 | 2023-11-11 | 2023-12-29 | 173
0 | FTST1490 | HD-T4 - SUB ASSEMBLE OTHER MISCL STRUCTURES | 70 | 2023-05-05 | 2023-07-26 | 2023-09-28 | 2023-12-18 | 125
PRE-FAB - PIPE SUPPORTS |  |  | 60 | 2023-02-20 | 2023-05-01 | 2023-07-24 | 2023-10-07 | 138
0 | FTST1620 | HD-T4 - PRE-FAB -PIPE SUPPORTS (CELLAR DK) (Welded attachments to frame) | 12 | 2023-02-20 | 2023-03-06 | 2023-07-24 | 2023-08-05 | 132
0 | FTST1610 | HD-T4 - PRE-FAB - PIPE SUPPORTS (MAIN DECK) (Welded attachments to frame) | 18 | 2023-02-20 | 2023-03-13 | 2023-07-24 | 2023-08-12 | 132
0 | FTST1600 | HD-T4 - PRE-FAB - PIPE SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 18 | 2023-02-27 | 2023-03-20 | 2023-07-31 | 2023-08-19 | 132
0 | FTST1590 | HD-T4 - PRE-FAB - PIPE SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-03-03 | 2023-03-24 | 2023-09-07 | 2023-09-27 | 161
0 | FTST1630 | HD-T4 - PRE-FAB - BALANCE PIPE SUPPORTS (Other than Welded attachments to frame) | 60 | 2023-02-20 | 2023-05-01 | 2023-07-31 | 2023-10-07 | 138
PRE-FAB - EQUIPMENT SUPPORTS |  |  | 62 | 2023-02-24 | 2023-05-08 | 2023-07-31 | 2023-11-24 | 173
0 | FTST1670 | HD-T4 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (MAIN DECK) (Welded attachments to frame) | 18 | 2023-02-24 | 2023-03-17 | 2023-07-31 | 2023-08-19 | 134
0 | FTST1680 | HD-T4 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (CELLARN DK) (Welded attachments to frame) | 18 | 2023-03-01 | 2023-03-22 | 2023-08-05 | 2023-08-25 | 135
0 | FTST1660 | HD-T4 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 18 | 2023-03-06 | 2023-03-27 | 2023-08-07 | 2023-08-26 | 132
0 | FTST1650 | HD-T4 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-03-20 | 2023-04-10 | 2023-08-21 | 2023-09-09 | 132
0 | FTST1690 | HD-T4 - PRE-FAB - BALANCE EQUIPMENT SUPPORTS (Other than Welded attachments to frame) | 24 | 2023-03-31 | 2023-04-28 | 2023-10-10 | 2023-11-06 | 165
0 | FTST1640 | HD-T4 - PRE-FAB - VENT SUPPORT STRUCTURE | 42 | 2023-03-20 | 2023-05-08 | 2023-10-07 | 2023-11-24 | 173
PRE-FAB - E & I CABLE TRAY SUPPORTS |  |  | 63 | 2023-03-06 | 2023-05-18 | 2023-08-10 | 2023-10-26 | 139
0 | FTST1730 | HD-T4 - PRE-FAB - CABLE TRAY SUPPORTS (CELLAR DK) (Welded attachments to frame) | 15 | 2023-03-06 | 2023-03-23 | 2023-08-10 | 2023-08-26 | 135
0 | FTST1720 | HD-T4 - PRE-FAB - CABLE TRAY SUPPORTS (MAIN DECK) (Welded attachments to frame) | 15 | 2023-03-10 | 2023-03-28 | 2023-08-15 | 2023-08-31 | 135
0 | FTST1710 | HD-T4 - PRE-FAB - CABLE TRAY SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 15 | 2023-03-17 | 2023-04-04 | 2023-08-28 | 2023-09-13 | 140
0 | FTST1700 | HD-T4 - PRE-FAB - CABLE TRAY SUPPORTS (WEATHER DK) (Welded attachments to frame) | 15 | 2023-04-03 | 2023-04-20 | 2023-09-04 | 2023-09-20 | 132
0 | FTST1740 | HD-T4 - PRE-FAB - BALANCE CABLE TRAY SUPPORTS (Other than Welded attachments to frame) | 48 | 2023-03-23 | 2023-05-18 | 2023-08-24 | 2023-10-18 | 132
0 | FTST1750 | HD-T4 - PRE-FAB - SECONDARY CABLE TRAY SUPPORTS | 42 | 2023-03-30 | 2023-05-18 | 2023-09-08 | 2023-10-26 | 139
PRE-FAB - OTHER E&I SUPPORTS |  |  | 60 | 2023-03-15 | 2023-05-24 | 2023-08-19 | 2023-11-11 | 148
0 | FTST1780 | HD-T4 - PRE-FAB - OTHER E&I SUPPORTS (MAIN DECK) | 28 | 2023-03-15 | 2023-04-17 | 2023-08-19 | 2023-09-20 | 135
0 | FTST1790 | HD-T4 - PRE-FAB - OTHER E&I SUPPORTS (CELLAR DK) | 28 | 2023-03-20 | 2023-04-21 | 2023-08-24 | 2023-09-25 | 135
0 | FTST1770 | HD-T4 - PRE-FAB - OTHER E&I SUPPORTS (MEZZANINE DECK) | 28 | 2023-03-27 | 2023-04-28 | 2023-09-02 | 2023-10-04 | 137
0 | FTST1760 | HD-T4 - PRE-FAB - OTHER E&I SUPPORTS (WEATHER DK) | 30 | 2023-04-03 | 2023-05-08 | 2023-09-15 | 2023-10-19 | 142
0 | FTST1800 | HD-T4 - PRE-FAB - BALANCE OTHER E&I SUPPORTS (Other than Welded attachments to frame) | 56 | 2023-03-20 | 2023-05-24 | 2023-09-08 | 2023-11-11 | 148
GENERAL |  |  | 180 | 2022-10-13 | 2023-05-11 | 2023-06-06 | 2024-01-01 | 202
0 | FTST5060 | HD-T4 - JOB PREPRATION FOR ASSEMBLY & LEVEL- LIFTING | 180 | 2022-10-13 | 2023-05-11 | 2023-06-06 | 2024-01-01 | 202
STRUCTURAL ASSEMBLY & ERECTION |  |  | 283 | 2022-10-27 | 2023-09-22 | 2023-04-18 | 2024-02-21 | 131
ASSEMBLY & WELD MAIN DECK |  |  | 100 | 2022-10-27 | 2023-02-21 | 2023-05-08 | 2023-08-23 | 158
0 | FTST2040 | HD-T4 - FIT-UP & TACK WELD - MAIN DECK MAIN FRAME - GIRDERS | 21 | 2022-10-27 | 2022-11-21 | 2023-05-08 | 2023-05-31 | 165
0 | FTST2060 | HD-T4 - FIT-UP & TACK WELD - MAIN DECK MAIN FRAME - NODES | 21 | 2022-10-27 | 2022-11-21 | 2023-05-08 | 2023-05-31 | 165
0 | FTST2030 | HD-T4 - FIT-UP & TACK WELD - MAIN DECK SECONDARY STEEL | 21 | 2022-11-14 | 2022-12-08 | 2023-05-25 | 2023-06-17 | 165
0 | FTST2020 | HD-T4 - COMPLETE WELDING - MAIN DECK | 24 | 2022-11-28 | 2022-12-26 | 2023-06-08 | 2023-07-05 | 165
0 | FTST2010 | HD-T4 - ERECT & WELD - MAIN DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-01-03 | 2023-01-24 | 2023-07-06 | 2023-07-26 | 158
0 | FTST2050 | HD-T4 - ERECT & WELD - DECK LEGS AND BRACES (MAIN DECK) | 18 | 2023-01-03 | 2023-01-24 | 2023-07-06 | 2023-07-26 | 158
0 | FTST2000 | HD-T4 - PREPARATION - MAIN DECK ERECTION / LIFT | 3 | 2023-02-17 | 2023-02-21 | 2023-08-21 | 2023-08-23 | 158
ASSEMBLY & WELD CELLAR DECK |  |  | 90 | 2022-11-08 | 2023-02-21 | 2023-05-08 | 2023-08-16 | 152
0 | FTST2110 | HD-T4 - FIT-UP & TACK WELD - CELLAR DECK MAIN FRAME - GIRDERS | 18 | 2022-11-08 | 2022-11-29 | 2023-05-08 | 2023-05-27 | 155
0 | FTST2120 | HD-T4 - FIT-UP & TACK WELD - CELLAR DECK MAIN FRAME - NODES | 18 | 2022-11-08 | 2022-11-29 | 2023-05-11 | 2023-05-31 | 158
0 | FTST2100 | HD-T4 - FIT-UP & TACK WELD - CELLAR DECK SECONDARY FRAME | 18 | 2022-11-22 | 2022-12-13 | 2023-05-25 | 2023-06-14 | 158
0 | FTST2090 | HD-T4 - COMPLETE WELDING - CELLAR DECK | 15 | 2022-12-13 | 2022-12-30 | 2023-06-15 | 2023-07-01 | 158
0 | FTST2080 | HD-T4 - ERECT & WELD - CELLAR DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-01-03 | 2023-01-24 | 2023-06-29 | 2023-07-19 | 152
0 | FTST2070 | HD-T4 - PREPARATION - CELLAR DECK ERECTION / LIFT | 3 | 2023-02-17 | 2023-02-21 | 2023-08-14 | 2023-08-16 | 152
ASSEMBLY & WELD MEZZANINE DECK |  |  | 93 | 2022-11-16 | 2023-03-04 | 2023-04-18 | 2023-09-06 | 160
0 | FTST2170 | HD-T4 - FIT-UP & TACK WELD - MEZZANINE DECK MAIN FRAME - GIRDERS | 21 | 2022-11-16 | 2022-12-10 | 2023-04-18 | 2023-05-11 | 131
0 | FTST2190 | HD-T4 - FIT-UP & TACK WELD - MEZZANINE DECK MAIN FRAME - NODES | 21 | 2022-11-16 | 2022-12-10 | 2023-05-22 | 2023-06-14 | 160
0 | FTST2160 | HD-T4 - FIT-UP & TACK WELD - MEZZANINE DECK SECONDARY FRAME | 21 | 2022-12-03 | 2022-12-28 | 2023-06-08 | 2023-07-01 | 160
0 | FTST2150 | HD-T4 - COMPLETE WELDING - MEZZANINE DECK | 24 | 2022-12-17 | 2023-01-14 | 2023-06-22 | 2023-07-19 | 160
0 | FTST2140 | HD-T4 - ERECT & WELD - MEZZANINE DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-01-14 | 2023-02-04 | 2023-07-20 | 2023-08-09 | 160
0 | FTST2180 | HD-T4 - ERECT & WELD - DECK LEGS AND BRACES (MEZZANINE DECK - MAIND DECK) | 18 | 2023-01-14 | 2023-02-04 | 2023-07-20 | 2023-08-09 | 160
0 | FTST2130 | HD-T4 - PREPARATION - MEZZANINE DECK ERECTION / LIFT | 3 | 2023-03-01 | 2023-03-04 | 2023-09-04 | 2023-09-06 | 160
ASSEMBLY & WELD ACCESS PLATFORM |  |  | 60 | 2022-12-08 | 2023-02-16 | 2023-05-29 | 2023-08-05 | 147
0 | FTST2200 | HD-T4 - FIT-UP & TACK WELD - ACCESS PLATFORMS MAIN FRAME | 18 | 2022-12-08 | 2022-12-29 | 2023-05-29 | 2023-06-17 | 147
0 | FTST2210 | HD-T4 - FIT-UP & TACK WELD - ACCESS PLATFORMS SECONDARY FRAME | 15 | 2022-12-22 | 2023-01-09 | 2023-06-12 | 2023-06-28 | 147
0 | FTST2220 | HD-T4 - COMPLETE WELDING - ACCESS PLATFORMS | 18 | 2023-01-09 | 2023-01-30 | 2023-06-29 | 2023-07-19 | 147
0 | FTST2230 | HD-T4 - ERECT & WELD - ACCESS PLATFORMS FLOOR PLATING | 15 | 2023-01-30 | 2023-02-16 | 2023-07-20 | 2023-08-05 | 147
0 | FTST2240 | HD-T4 - ERECT & WELD - DECK LEGS AND BRACES (ACCESS PLATFORM & MEZZANINE DECK) | 15 | 2023-01-30 | 2023-02-16 | 2023-07-20 | 2023-08-05 | 147
ASSEMBLY & WELD WEATHER DECK |  |  | 96 | 2022-12-07 | 2023-03-29 | 2023-05-09 | 2023-10-10 | 168
0 | FTST2290 | HD-T4 - FIT-UP & TACK WELD - WEATHER DECK MAIN FRAME | 21 | 2022-12-07 | 2022-12-31 | 2023-05-09 | 2023-06-01 | 131
0 | FTST2300 | HD-T4 - FIT-UP & TACK WELD - WEATHER DECK FRAME - NODES | 21 | 2022-12-07 | 2022-12-31 | 2023-05-09 | 2023-06-01 | 131
0 | FTST2280 | HD-T4 - FIT-UP & TACK WELD - WEATHER DECK SECONDARY FRAME | 21 | 2022-12-24 | 2023-01-18 | 2023-05-26 | 2023-06-19 | 131
0 | FTST2270 | HD-T4 - COMPLETE WELDING - WEATHER DECK | 18 | 2023-01-14 | 2023-02-04 | 2023-06-16 | 2023-07-06 | 131
0 | FTST2260 | HD-T4 - ERECT & WELD - WEATHER DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-02-08 | 2023-03-01 | 2023-07-07 | 2023-07-27 | 128
0 | FTST2250 | HD-T4 - PREPARATION - WEATHER DECK ERECTION / LIFT | 3 | 2023-03-25 | 2023-03-29 | 2023-10-07 | 2023-10-10 | 168
ASSEMBLY & WELD HELI DECK |  |  | 102 | 2023-01-20 | 2023-05-19 | 2023-06-15 | 2023-12-25 | 189
0 | FTST2360 | HD-T4 - FIT-UP & TACK WELD - HELI DECK MAIN FRAME | 24 | 2023-01-20 | 2023-02-17 | 2023-06-15 | 2023-07-12 | 125
0 | FTST2370 | HD-T4 - FIT-UP & TACK WELD - HELI DECK MAIN FRAME - NODES | 24 | 2023-01-20 | 2023-02-17 | 2023-07-03 | 2023-07-29 | 140
0 | FTST2350 | HD-T4 - FIT-UP & TACK WELD - HELI DECK SECONDARY FRAME | 24 | 2023-02-07 | 2023-03-07 | 2023-07-03 | 2023-07-29 | 125
0 | FTST2340 | HD-T4 - COMPLETE WELDING - HELI DECK | 15 | 2023-03-07 | 2023-03-24 | 2023-07-31 | 2023-08-16 | 125
0 | FTST2330 | HD-T4 - ERECT & WELD - HDK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-03-24 | 2023-04-14 | 2023-08-17 | 2023-09-06 | 125
0 | FTST2310 | HD-T4 - INSTALL - SAFETY NET | 6 | 2023-05-09 | 2023-05-16 | 2023-12-15 | 2023-12-21 | 189
0 | FTST2320 | HD-T4 - PREPARATION - HELI DECK ERECTION / LIFT | 3 | 2023-05-16 | 2023-05-19 | 2023-12-22 | 2023-12-25 | 189
ERECT - CELLAR DECK |  |  | 30 | 2023-02-21 | 2023-03-28 | 2023-08-17 | 2023-12-09 | 221
0 | FTST2390 | HD-T4 - LIFT,INSTALL & WELD - CELLAR DECK | 6 | 2023-02-21 | 2023-02-28 | 2023-08-17 | 2023-08-23 | 152
0 | FTST2380 | HD-T4 - ERECT & WELD - REMAINING DECK ELEVATIONS / BRACES (B/W CELLAR DK & MAIN DECK) | 24 | 2023-02-28 | 2023-03-28 | 2023-11-13 | 2023-12-09 | 221
ERECT - MAIN DECK |  |  | 6 | 2023-03-29 | 2023-04-05 | 2023-08-24 | 2023-08-30 | 127
0 | FTST2400 | HD-T4 - LIFT,INSTALL & WELD - MAIN DECK | 6 | 2023-03-29 | 2023-04-05 | 2023-08-24 | 2023-08-30 | 127
ACCESS PLATFORM |  |  | 6 | 2023-04-05 | 2023-04-12 | 2023-08-31 | 2023-09-06 | 127
0 | FTST2410 | HD-T4 - INSTALL & WELD - ACCESS PLATFORMS | 6 | 2023-04-05 | 2023-04-12 | 2023-08-31 | 2023-09-06 | 127
ERECT - MEZZANINE DECK |  |  | 15 | 2023-04-12 | 2023-04-29 | 2023-09-07 | 2023-12-09 | 193
0 | FTST2430 | HD-T4 - LIFT,INSTALL & WELD - MEZZANINE DECK | 6 | 2023-04-12 | 2023-04-19 | 2023-09-07 | 2023-09-13 | 127
0 | FTST2420 | HD-T4 - ERECT & WELD - VERTICAL LEGS (B/W MEZZANINE DECK & MAIN DK) | 12 | 2023-04-15 | 2023-04-29 | 2023-11-27 | 2023-12-09 | 193
ERECT WEATHER DECK |  |  | 66 | 2023-05-16 | 2023-08-01 | 2023-10-11 | 2024-01-13 | 143
0 | FTST2450 | HD-T4 - LIFT,INSTALL & WELD - WEATHER DECK | 6 | 2023-05-16 | 2023-05-23 | 2023-10-11 | 2023-10-17 | 127
0 | FTST2440 | HD-T4 - ERECT BALANCE BRACES AND COMPLETE BOX UP | 60 | 2023-05-23 | 2023-08-01 | 2023-11-06 | 2024-01-13 | 143
ERECT- HELI DECK |  |  | 6 | 2023-06-02 | 2023-06-09 | 2023-12-26 | 2024-01-01 | 177
0 | FTST2460 | HD-T4 - LIFT,INSTALL & WELD - HELI DECK | 6 | 2023-06-02 | 2023-06-09 | 2023-12-26 | 2024-01-01 | 177
ERECT- HANDRAILS, LADDERS |  |  | 186 | 2023-01-06 | 2023-08-11 | 2023-07-03 | 2024-02-21 | 167
0 | FTST2530 | HD-T4 - WELD - MEZZANINE DECK HANDRAIL SOCKETS | 15 | 2023-01-06 | 2023-01-24 | 2023-07-24 | 2023-08-09 | 170
0 | FTST2540 | HD-T4 - WELD - MAIN DECK HANDRAIL SOCKETS | 15 | 2023-01-06 | 2023-01-24 | 2023-07-10 | 2023-07-26 | 158
0 | FTST2550 | HD-T4 - WELD - CELLAR DECK HANDRAIL SOCKETS | 15 | 2023-01-06 | 2023-01-24 | 2023-07-03 | 2023-07-19 | 152
0 | FTST2520 | HD-T4 - WELD - WEATHER HANDRAILS SOCKETS | 15 | 2023-01-18 | 2023-02-04 | 2023-07-11 | 2023-07-27 | 149
0 | FTST2500 | HD-T4 - ERECT - CELLAR DECK HANDRAILS | 30 | 2023-03-17 | 2023-04-21 | 2023-10-05 | 2023-11-08 | 173
0 | FTST2490 | HD-T4 - ERECT - MAIN DECK HANDRAILS | 30 | 2023-04-22 | 2023-05-27 | 2023-10-19 | 2023-11-22 | 154
0 | FTST2480 | HD-T4 - ERECT - MEZZANINE DECK HANDRAILS | 30 | 2023-05-06 | 2023-06-10 | 2023-12-07 | 2024-01-10 | 184
0 | FTST2470 | HD-T4 - ERECT - WEATHER DECK HANDRAILS | 30 | 2023-06-09 | 2023-07-14 | 2024-01-18 | 2024-02-21 | 191
0 | FTST2510 | HD-T4 - ERECT & WELD - LADDERS & CAGES | 54 | 2023-06-09 | 2023-08-11 | 2023-11-23 | 2024-01-24 | 143
ERECT- GRATINGS |  |  | 101 | 2023-03-01 | 2023-06-27 | 2023-07-28 | 2024-02-02 | 190
0 | FTST2620 | HD-T4 - TAILORING OF GRATINGS - CELLAR DECK | 21 | 2023-03-01 | 2023-03-25 | 2023-07-28 | 2023-08-21 | 128
0 | FTST2580 | HD-T4 - TAILORING OF GRATINGS - MAIN DECK | 21 | 2023-03-15 | 2023-04-08 | 2023-08-11 | 2023-09-04 | 128
0 | FTST2600 | HD-T4 - TAILORING OF GRATINGS - MEZZANINE DECK | 21 | 2023-03-22 | 2023-04-15 | 2023-08-18 | 2023-09-11 | 128
0 | FTST5040 | HD-T4 - TAILORING OF GRATINGS - ACCESSPLATFORM | 21 | 2023-03-22 | 2023-04-15 | 2023-09-08 | 2023-10-02 | 146
0 | FTST2560 | HD-T4 - TAILORING OF GRATINGS - WEATHER DECK | 21 | 2023-03-29 | 2023-04-22 | 2023-08-25 | 2023-09-18 | 128
0 | FTST2630 | HD-T4 - INSTALL - GRATINGS (CELLAR DK) | 21 | 2023-04-15 | 2023-05-10 | 2023-12-29 | 2024-01-22 | 221
0 | FTST2610 | HD-T4 - INSTALL - GRATINGS MEZZANINE DECK | 30 | 2023-04-22 | 2023-05-27 | 2023-09-19 | 2023-10-23 | 128
0 | FTST5050 | HD-T4 - INSTALL - GRATINGS -ACCESS PLATFORM | 21 | 2023-05-13 | 2023-06-07 | 2023-12-29 | 2024-01-22 | 197
0 | FTST2590 | HD-T4 - INSTALL - GRATINGS (MAIN DECK) | 30 | 2023-05-06 | 2023-06-10 | 2023-10-03 | 2023-11-06 | 128
0 | FTST2570 | HD-T4 - INSTALL - GRATINGS WEATHER DECK | 30 | 2023-05-23 | 2023-06-27 | 2023-12-30 | 2024-02-02 | 190
ERECT STAIRWAYS/STAIR TOWER |  |  | 60 | 2023-04-24 | 2023-07-03 | 2023-11-23 | 2024-01-31 | 183
0 | FTST2660 | HD-T4 - ERECT & WELD - STAIRWAYS/STAIR TOWER (NORTH SIDE) | 30 | 2023-05-22 | 2023-06-26 | 2023-12-28 | 2024-01-31 | 189
0 | FTST2650 | HD-T4 - ERECT & WELD - STAIRWAYS/STAIR TOWER (EAST SIDE) | 30 | 2023-05-23 | 2023-06-27 | 2023-12-19 | 2024-01-22 | 180
0 | FTST2640 | HD-T4 - ERECT & WELD - OTHER BALANCE STAIRWAYS | 60 | 2023-04-24 | 2023-07-03 | 2023-11-23 | 2024-01-31 | 183
ERECT PIPE SUPPORTS |  |  | 91 | 2023-02-23 | 2023-06-09 | 2023-08-28 | 2023-12-05 | 154
0 | FTST2700 | HD-T4 - INSTALL & WELD - PIPE SUPPORTS CELLAR DECK (Welded attachments to frame) | 12 | 2023-02-23 | 2023-03-09 | 2023-10-28 | 2023-11-10 | 212
0 | FTST2690 | HD-T4 - INSTALL & WELD - PIPE SUPPORTS (MAIN DECK) (Welded attachments to frame) | 15 | 2023-02-27 | 2023-03-16 | 2023-10-25 | 2023-11-10 | 206
0 | FTST2680 | HD-T4 - INSTALL & WELD - PIPE SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 24 | 2023-03-06 | 2023-04-03 | 2023-11-08 | 2023-12-05 | 212
0 | FTST2670 | HD-T4 - INSTALL & WELD - PIPE SUPPORTS (WEATHER DECK) (Welded attachments to frame) | 24 | 2023-03-14 | 2023-04-11 | 2023-10-20 | 2023-11-16 | 189
0 | FTST2710 | HD-T4 - INSTALL & WELD - BALANCE PIPE SUPPORTS (Other than Welded attachments to frame) | 70 | 2023-03-20 | 2023-06-09 | 2023-08-28 | 2023-11-16 | 138
ERECT EQPT SUOPPORTS |  |  | 109 | 2023-03-03 | 2023-07-08 | 2023-09-13 | 2024-01-16 | 165
0 | FTST2750 | HD-T4 - INSTALL & WELD - EQUIPMENT SUPPORTS (MAIN DECK) (Welded attachments to frame) | 18 | 2023-03-03 | 2023-03-24 | 2023-09-13 | 2023-10-03 | 166
0 | FTST2760 | HD-T4 - INSTALL & WELD - EQUIPMENT SUPPORTS (CELLAR DK) (Welded attachments to frame) | 18 | 2023-03-15 | 2023-04-05 | 2023-10-18 | 2023-11-07 | 186
0 | FTST2740 | HD-T4 - INSTALL & WELD - EQUIPMENT SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 18 | 2023-03-20 | 2023-04-10 | 2023-09-13 | 2023-10-03 | 152
0 | FTST2730 | HD-T4 - INSTALL & WELD - EQUIPMENT SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-04-03 | 2023-04-24 | 2023-10-27 | 2023-11-16 | 178
0 | FTST2720 | HD-T4 - INSTALL & WELD - VENT SUPPORT STRUCTURE | 21 | 2023-06-05 | 2023-06-29 | 2023-12-23 | 2024-01-16 | 173
0 | FTST2770 | HD-T4 - INSTALL & WELD - BALANCE EQUIPMENT SUPPORTS (Other than Welded attachments to frame) | 60 | 2023-04-29 | 2023-07-08 | 2023-11-08 | 2024-01-16 | 165
ERECT CABLE TRAYS SUPPORTS |  |  | 89 | 2023-03-13 | 2023-06-24 | 2023-09-22 | 2023-11-30 | 137
0 | FTST2810 | HD-T4 - INSTALL & WELD - CABLE TRAY SUPPORTS (CELLAR DK) (Welded attachments to frame) | 15 | 2023-03-13 | 2023-03-30 | 2023-10-04 | 2023-10-20 | 176
0 | FTST2800 | HD-T4 - INSTALL & WELD - CABLE TRAY SUPPORTS (MAIN DECK) (Welded attachments to frame) | 15 | 2023-03-17 | 2023-04-04 | 2023-11-04 | 2023-11-21 | 199
0 | FTST2780 | HD-T4 - INSTALL & WELD - CABLE TRAY SUPPORTS (MEZZANINE DECK) (Welded attachments to frame) | 21 | 2023-03-24 | 2023-04-18 | 2023-10-30 | 2023-11-22 | 188
0 | FTST2790 | HD-T4 - INSTALL & WELD - CABLE TRAY SUPPORTS (WEATHER DK) (Welded attachments to frame) | 15 | 2023-04-17 | 2023-05-04 | 2023-11-06 | 2023-11-22 | 174
0 | FTST2830 | HD-T4 - INSTALL & WELD - SECONDARY CABLE TRAY SUPPORTS | 60 | 2023-04-13 | 2023-06-22 | 2023-09-22 | 2023-11-30 | 139
0 | FTST2820 | HD-T4 - INSTALL & WELD - BALANCE CABLE TRAY SUPPORTS (Other than Welded attachments to frame) | 50 | 2023-04-27 | 2023-06-24 | 2023-09-28 | 2023-11-24 | 132
ERECT OTHER E&I SUPPORTS |  |  | 42 | 2023-04-29 | 2023-06-17 | 2023-10-16 | 2023-12-06 | 148
0 | FTST2850 | HD-T4 - INSTALL & WELD - OTHER E&I SUPPORTS (MAIN DECK) | 15 | 2023-05-03 | 2023-05-20 | 2023-10-31 | 2023-11-16 | 155
0 | FTST2870 | HD-T4 - INSTALL & WELD - OTHER E&I SUPPORTS (CELLAR DK) | 15 | 2023-05-08 | 2023-05-25 | 2023-10-16 | 2023-11-01 | 138
0 | FTST2840 | HD-T4 - INSTALL & WELD - OTHER E&I SUPPORTS (WEATHER DK) | 24 | 2023-05-08 | 2023-06-05 | 2023-10-20 | 2023-11-16 | 142
0 | FTST2860 | HD-T4 - INSTALL & WELD - OTHER E&I SUPPORTS (MEZZANINE DECK) | 21 | 2023-05-12 | 2023-06-06 | 2023-10-19 | 2023-11-11 | 137
0 | FTST2880 | HD-T4 - INSTALL & WELD - BALANCE E&I SUPPORTS (Other than Welded attachments to frame) | 42 | 2023-04-29 | 2023-06-17 | 2023-10-19 | 2023-12-06 | 148
FLOOR DRAINS |  |  | 51 | 2022-11-11 | 2023-01-10 | 2023-06-29 | 2023-08-09 | 182
0 | FTST2890 | HD-T4 - INSTALL & WELD - FLOOR DRAINS (CELLAR DK) | 18 | 2022-11-11 | 2022-12-02 | 2023-06-29 | 2023-07-19 | 197
0 | FTST2920 | HD-T4 - INSTALL & WELD - FLOOR DRAINS (MAIN DECK) | 18 | 2022-11-25 | 2022-12-16 | 2023-07-06 | 2023-07-26 | 191
0 | FTST2910 | HD-T4 - INSTALL & WELD - FLOOR DRAINS (MEZZANINE DECK) | 18 | 2022-12-06 | 2022-12-27 | 2023-07-20 | 2023-08-09 | 194
0 | FTST2900 | HD-T4 - INSTALL & WELD - FLOOR DRAINS (WEATHER DK) | 18 | 2022-12-20 | 2023-01-10 | 2023-07-07 | 2023-07-27 | 171
ERECT OTHER STRUCTURES |  |  | 228 | 2022-12-07 | 2023-08-30 | 2023-05-05 | 2024-02-09 | 141
0 | FTST3010 | HD-T4 - INSTALL & WELD - AVAILABLE DECK PENETRATIONS | 60 | 2022-12-07 | 2023-02-15 | 2023-05-05 | 2023-07-13 | 128
0 | FTST2980 | HD-T4 - INSTALL & WELD - STABBING GUIDES | 9 | 2023-03-17 | 2023-03-28 | 2023-09-14 | 2023-09-23 | 155
0 | FTST2930 | HD-T4 - INSTALL & WELD - DECK PAD EYES | 21 | 2023-03-04 | 2023-03-29 | 2023-07-31 | 2023-08-23 | 127
0 | FTST2950 | HD-T4 - INSTALL & WELD - BALANCE DECK PENETRATIONS | 42 | 2023-02-28 | 2023-04-18 | 2023-09-06 | 2023-10-24 | 163
0 | FTST2940 | HD-T4 - INSTALL & WELD - PLATFORM IDENTIFICATION PANELS | 30 | 2023-06-19 | 2023-07-24 | 2024-01-06 | 2024-02-09 | 173
0 | FTST2970 | HD-T4 - INSTALL & WELD - MONORAIL FRAMES | 60 | 2023-05-31 | 2023-08-09 | 2023-10-31 | 2024-01-08 | 131
0 | FTST2960 | HD-T4 - INSTALL & WELD - DECK HATCHES | 60 | 2023-06-10 | 2023-08-19 | 2023-11-07 | 2024-01-15 | 128
0 | FTST2990 | HD-T4 - INSTALL & WELD - FLARE BOOM | 21 | 2023-08-05 | 2023-08-30 | 2024-01-01 | 2024-01-24 | 127
0 | FTST3000 | HD-T4 - INSTALL & WELD - MISC STRUCTURAL ITEMS | 60 | 2023-06-21 | 2023-08-30 | 2023-11-14 | 2024-01-22 | 125
0 | FTST3020 | HD-T4 - INSTALL & WELD - HELIDECK DRAIN/GUTTER | 25 | 2023-08-01 | 2023-08-30 | 2023-12-25 | 2024-01-22 | 125
PUNCH LIST CLEARANCE- STRUCTURAL |  |  | 20 | 2023-08-30 | 2023-09-22 | 2024-01-23 | 2024-02-14 | 125
0 | FTST4000 | HD-T4 - STRUCTURAL PUNCHLIST CLEARANCE | 20 | 2023-08-30 | 2023-09-22 | 2024-01-23 | 2024-02-14 | 125
PRESSURE VESSEL (FABRICATION & PAINTING) |  |  | 177 | 2022-11-28 | 2023-06-21 | 2023-02-14 | 2023-09-07 | 67
0 | FTPV1000 | HD-T4 - FABRICATE - VENT/DRAIN DRUM | 160 | 2022-11-28 | 2023-06-01 | 2023-02-14 | 2023-08-18 | 67
0 | FTPV1010 | HD-T4 - PAINT - VENT/DRAIN DRUM | 17 | 2023-06-02 | 2023-06-21 | 2023-08-19 | 2023-09-07 | 67
PIPING WORKS |  |  | 181 | 2023-02-15 | 2023-09-13 | 2023-08-17 | 2024-02-26 | 142
PIPING PRE-FABRICATION |  |  | 69 | 2023-02-15 | 2023-05-06 | 2023-08-17 | 2023-11-21 | 171
0 | FTPI1010 | HD-T4 - FABRICATE - CU-NI PIPING SPOOLS | 30 | 2023-02-22 | 2023-03-29 | 2023-08-30 | 2023-10-03 | 162
0 | FTPI1030 | HD-T4 - FABRICATE - CS/ LTCS/ CLADDED PIPING SPOOLS | 56 | 2023-02-15 | 2023-04-21 | 2023-08-17 | 2023-10-20 | 157
0 | FTPI1020 | HD-T4 - FABRICATE - SS/DUPLEX PIPING SPOOLS | 30 | 2023-03-20 | 2023-04-24 | 2023-09-20 | 2023-10-24 | 158
0 | FTPI1000 | HD-T4 - FABRICATE - INCONEL PIPING SPOOLS | 42 | 2023-03-18 | 2023-05-06 | 2023-10-04 | 2023-11-21 | 171
VALVE LEAK TESTING |  |  | 36 | 2023-03-24 | 2023-05-05 | 2023-10-11 | 2023-11-21 | 172
0 | FTPI1040 | HD-T4 - VALVE LEAK TESTING | 36 | 2023-03-24 | 2023-05-05 | 2023-10-11 | 2023-11-21 | 172
PIPING ERECTION/HYDROTESTING/INSULATION |  |  | 119 | 2023-04-28 | 2023-09-13 | 2023-09-25 | 2024-02-26 | 142
PIPING ERECTION |  |  | 68 | 2023-04-28 | 2023-07-15 | 2023-09-25 | 2023-12-12 | 128
0 | FTPI1080 | HD-T4 - ERECT - CS/ LTCS/ CLADDED SPOOLS | 56 | 2023-04-28 | 2023-07-01 | 2023-09-25 | 2023-11-28 | 128
0 | FTPI1050 | HD-T4 - ERECT - INCONEL SPOOLS | 42 | 2023-05-29 | 2023-07-15 | 2023-10-25 | 2023-12-12 | 128
0 | FTPI1060 | HD-T4 - ERECT - CU-NI SPOOLS | 30 | 2023-06-12 | 2023-07-15 | 2023-11-08 | 2023-12-12 | 128
0 | FTPI1070 | HD-T4 - ERECT - SS/DUPLEX SPOOLS | 30 | 2023-06-12 | 2023-07-15 | 2023-11-08 | 2023-12-12 | 128
HYDROTESTING & REINSTATEMENT |  |  | 63 | 2023-06-22 | 2023-09-02 | 2023-11-20 | 2024-02-26 | 151
HYDROTESTING |  |  | 44 | 2023-06-22 | 2023-08-11 | 2023-11-20 | 2024-01-13 | 133
0 | FTPI1110 | HD-T4 - HYDROTESTING AND RE-INSTATEMENT - OIL PRODUCTION SYSTEM | 18 | 2023-06-22 | 2023-07-12 | 2023-11-20 | 2023-12-09 | 129
0 | FTPI1120 | HD-T4 - HYDROTESTING AND RE-INSTATEMENT - WATER INJECTION SYSTEM | 18 | 2023-07-04 | 2023-07-24 | 2023-12-01 | 2023-12-21 | 129
0 | FTPI1090 | HD-T4 - HYDROTESTING AND RE-INSTATEMENT - CLOSED DRAIN SYSTEM | 18 | 2023-07-10 | 2023-07-29 | 2023-12-07 | 2023-12-27 | 129
0 | FTPI1100 | HD-T4 - HYDROTESTING AND RE-INSTATEMENT - OPEN DRAIN SYSTEM | 18 | 2023-07-17 | 2023-08-05 | 2023-12-13 | 2024-01-02 | 128
0 | FTPI1130 | HD-T4 - HYDROTESTING AND RE-INSTATEMENT - VENT SYSTEM | 12 | 2023-07-29 | 2023-08-11 | 2023-12-27 | 2024-01-09 | 129
0 | FTPI1140 | HD-T4 - HYDROTESTING AND RE-INSTATEMENT - CORROSION INHABITOR INJECTION SYSTEM | 18 | 2023-07-22 | 2023-08-11 | 2023-12-25 | 2024-01-13 | 133
INSULATION |  |  | 45 | 2023-07-13 | 2023-09-02 | 2024-01-05 | 2024-02-26 | 151
0 | FTPI1150 | HD-T4 - PIPING INSULATION WORK | 45 | 2023-07-13 | 2023-09-02 | 2024-01-05 | 2024-02-26 | 151
PIPING SYSTEMS MECHANICAL COMPLETION |  |  | 28 | 2023-08-12 | 2023-09-13 | 2024-01-29 | 2024-02-21 | 138
0 | FTPI1180 | HD-T4 - MECHANICAL COMPLETION - CHEMICAL INJECTION SYSTEM | 10 | 2023-08-12 | 2023-08-23 | 2024-02-02 | 2024-02-13 | 149
0 | FTPI1190 | HD-T4 - MECHANICAL COMPLETION - PRODUCTION SYSTEM | 10 | 2023-08-17 | 2023-08-28 | 2024-02-10 | 2024-02-21 | 152
0 | FTPI1200 | HD-T4 - MECHANICAL COMPLETION - WATER INJECTION SYSTEM | 10 | 2023-08-22 | 2023-09-01 | 2024-01-29 | 2024-02-08 | 137
0 | FTPI1170 | HD-T4 - MECHANICAL COMPLETION - CLOSED/OPEN DRAIN SYSTEM | 10 | 2023-08-24 | 2023-09-04 | 2024-01-31 | 2024-02-10 | 137
0 | FTPI1160 | HD-T4 - MECHANICAL COMPLETION - VENT SYSTEM | 10 | 2023-09-02 | 2023-09-13 | 2024-01-31 | 2024-02-10 | 129
PUNCHLIST CLEARANCE - PIPING |  |  | 40 | 2023-07-05 | 2023-08-19 | 2023-12-27 | 2024-02-10 | 150
0 | FTPI4000 | HD-T4 - PUNCHLIST CLEARANCE - PIPING | 40 | 2023-07-05 | 2023-08-19 | 2023-12-27 | 2024-02-10 | 150
PIPING PWHT |  |  | 120 | 2023-02-20 | 2023-07-08 | 2023-08-22 | 2023-12-27 | 147
0 | FTPI5010 | HD-T4 - PWHT - FABRICATED SPOOLS | 70 | 2023-02-20 | 2023-05-12 | 2023-08-22 | 2023-11-10 | 157
0 | FTPI5000 | HD-T4 - PWHT - ERECTED SPOOLS | 60 | 2023-05-01 | 2023-07-08 | 2023-10-19 | 2023-12-27 | 147
MECHANICAL EQUIPMENT |  |  | 91 | 2023-05-09 | 2023-08-23 | 2023-10-04 | 2024-01-22 | 131
CELLAR DECK |  |  | 21 | 2023-06-05 | 2023-06-28 | 2023-11-01 | 2023-11-28 | 131
0 | FTME1010 | HD-T4 - INSTALL - DRAIN SUMP PUMP | 6 | 2023-06-05 | 2023-06-10 | 2023-11-01 | 2023-11-07 | 128
0 | FTME1000 | HD-T4 - INSTALL - VENT DRAIN TANK | 6 | 2023-06-22 | 2023-06-28 | 2023-11-22 | 2023-11-28 | 131
MAIN DECK |  |  | 91 | 2023-05-09 | 2023-08-23 | 2023-10-04 | 2024-01-22 | 131
0 | FTME1030 | HD-T4 - INSTALL - PIG LAUNCHER/ RECEIVER (730-L-001) | 12 | 2023-05-09 | 2023-05-23 | 2023-10-04 | 2023-10-17 | 127
0 | FTME1020 | HD-T4 - INSTALL - MONORAIL/HOIST | 70 | 2023-06-02 | 2023-08-23 | 2023-11-02 | 2024-01-22 | 131
WEATHER DECK |  |  | 70 | 2023-05-23 | 2023-08-12 | 2023-11-02 | 2024-01-22 | 140
0 | FTME1050 | HD-T4 - INSTALL - MONORAIL/HOIST | 70 | 2023-05-23 | 2023-08-12 | 2023-11-02 | 2024-01-22 | 140
ELECTRICAL |  |  | 150 | 2023-03-28 | 2023-09-19 | 2023-09-12 | 2024-03-04 | 144
GENERAL |  |  | 150 | 2023-03-28 | 2023-09-19 | 2023-09-12 | 2024-03-04 | 144
0 | FTEL1002 | HD-T4 - MATERIAL INSPECTION & PRESERVATION | 150 | 2023-03-28 | 2023-09-19 | 2023-09-12 | 2024-03-04 | 144
CABLE TRAYS |  |  | 52 | 2023-05-23 | 2023-07-22 | 2023-10-18 | 2023-12-16 | 127
0 | FTEL1000 | HD-T4 - INSTALL - ELECTRICAL MAIN CABLE TRAYS | 42 | 2023-05-23 | 2023-07-11 | 2023-10-18 | 2023-12-05 | 127
0 | FTEL1050 | HD-T4 - INSTALL - SECONDARY CABLE TRAYS | 42 | 2023-06-03 | 2023-07-22 | 2023-10-30 | 2023-12-16 | 127
CABLE PULLING, G&T & TESTING |  |  | 64 | 2023-06-07 | 2023-08-21 | 2023-11-02 | 2024-01-15 | 127
0 | FTEL1080 | HD-T4 - PULL - ELECTRICAL CABLES | 48 | 2023-06-07 | 2023-08-02 | 2023-11-02 | 2023-12-27 | 127
0 | FTEL1070 | HD-T4 - GLAND & TERMINATE - ELECTRICAL CABLES | 42 | 2023-06-26 | 2023-08-14 | 2023-11-21 | 2024-01-08 | 127
0 | FTEL1060 | HD-T4 - IR & CONTINUITY CHECK - ELECTRICAL CABLES | 36 | 2023-07-10 | 2023-08-21 | 2023-12-05 | 2024-01-15 | 127
FITTINGS/JB's & SOCKETS |  |  | 24 | 2023-06-02 | 2023-06-30 | 2023-11-09 | 2023-12-13 | 143
0 | FTEL1110 | HD-T4 - INSTALL LIGHT FITTINGS/JBs/SOCKETS | 12 | 2023-06-02 | 2023-06-16 | 2023-11-09 | 2023-11-22 | 137
0 | FTEL1100 | HD-T4 - INSTALL - INSTALL EARTHING | 12 | 2023-06-09 | 2023-06-23 | 2023-11-23 | 2023-12-06 | 143
0 | FTEL1090 | HD-T4 - INSTALL - SMALL POWER / LIGHTING DB'S | 12 | 2023-06-16 | 2023-06-30 | 2023-11-30 | 2023-12-13 | 143
ELECTRICAL EQUIPMENTS |  |  | 57 | 2023-04-20 | 2023-06-26 | 2023-09-21 | 2023-12-16 | 150
0 | FTEL1150 | HD-T4 - INSTALL - LV DISTRIBUTION BOARD INSTALLATION - MEZZ DECK | 18 | 2023-04-26 | 2023-05-17 | 2023-09-21 | 2023-10-11 | 127
0 | FTEL1140 | HD-T4 - INSTALL - AC UPS SYSTEM - MEZZ DECK | 24 | 2023-04-20 | 2023-05-18 | 2023-11-18 | 2023-12-15 | 182
0 | FTEL1170 | HD-T4 - INSTALL - TRANSFRMER INSTALLLATION - WEATHER DECK | 6 | 2023-05-23 | 2023-05-30 | 2023-12-08 | 2023-12-14 | 171
0 | FTEL1190 | HD-T4 - INSTALL - TUTU BOX- CELLAR DECK | 12 | 2023-05-23 | 2023-06-06 | 2023-11-18 | 2023-12-01 | 154
0 | FTEL1120 | HD-T4 - INSTALL - BIRD DETTERENT SYSTEM - MEZZ DECK | 12 | 2023-05-24 | 2023-06-07 | 2023-11-20 | 2023-12-02 | 154
0 | FTEL1180 | HD-T4 - INSTALL - 415V SWITCHBOARD - MEZZ DECK | 18 | 2023-05-17 | 2023-06-07 | 2023-10-12 | 2023-11-01 | 127
0 | FTEL1130 | HD-T4 - INSTALL - NAVIGATION AID SYSTEM - WEATHER/ CELLAR/ MEZZ DECK | 24 | 2023-05-16 | 2023-06-13 | 2023-11-06 | 2023-12-02 | 149
0 | FTEL1160 | HD-T4 - INSTALL - 6.6 Kv RMU INSTALLATION - WEATHER DECK | 18 | 2023-06-05 | 2023-06-26 | 2023-11-27 | 2023-12-16 | 150
ELECTRICAL SYSTEMS MECHANICAL COMPLETION |  |  | 19 | 2023-08-02 | 2023-08-24 | 2023-12-28 | 2024-01-22 | 130
0 | FTEL1200 | HD-T4 - MECHANICAL COMPLETION - POWER SYSTEM | 12 | 2023-08-02 | 2023-08-16 | 2023-12-28 | 2024-01-10 | 127
0 | FTEL1210 | HD-T4 - MECHANICAL COMPLETION - LIGHTING SYSTEM | 12 | 2023-08-10 | 2023-08-24 | 2024-01-09 | 2024-01-22 | 130
PUNCHLIST CLEARANCE - ELECTRICAL |  |  | 36 | 2023-07-19 | 2023-08-30 | 2023-12-18 | 2024-01-27 | 130
0 | FTEL1220 | HD-T4 - PUNCHLIST CLEARANCE - ELECTRICAL | 36 | 2023-07-19 | 2023-08-30 | 2023-12-18 | 2024-01-27 | 130
INSTRUMENTATION/TELECOM |  |  | 98 | 2023-05-22 | 2023-09-13 | 2023-11-04 | 2024-02-07 | 127
CABLE TRAYS & CABLE PULLING |  |  | 71 | 2023-06-14 | 2023-09-05 | 2023-11-16 | 2024-01-26 | 124
0 | FTIN1020 | HD-T4 - PULL - INSTRUMENT CABLES | 42 | 2023-06-14 | 2023-08-02 | 2023-11-16 | 2024-01-03 | 133
0 | FTIN1010 | HD-T4 - GLAND/TERMINATE - INSTRUMENT CABLES | 42 | 2023-07-11 | 2023-08-29 | 2023-12-02 | 2024-01-19 | 124
0 | FTIN1000 | HD-T4 - IR & CONTINUITY CHECK - INSTRUMENT CABLES | 36 | 2023-07-25 | 2023-09-05 | 2023-12-16 | 2024-01-26 | 124
INSTRUMENTS INSTALLATION |  |  | 74 | 2023-05-22 | 2023-08-15 | 2023-11-04 | 2024-01-12 | 129
0 | FTIN1040 | HD-T4 - INSTALL - F&G DETECTORS | 24 | 2023-05-30 | 2023-06-27 | 2023-11-04 | 2023-12-01 | 136
0 | FTIN1180 | HD-T4 - INSTRUMENT CALIBIRATION | 42 | 2023-05-22 | 2023-07-10 | 2023-11-04 | 2023-12-22 | 143
0 | FTIN1050 | HD-T4 - INSTALL - FIELD INSTRUMENTS | 42 | 2023-06-28 | 2023-08-15 | 2023-11-25 | 2024-01-12 | 129
PANELS & JB's |  |  | 42 | 2023-06-05 | 2023-07-24 | 2023-11-17 | 2024-01-04 | 142
0 | FTIN1060 | HD-T4 - INSTALL - JUNCTION BOXES/ MARSHALING BOXES / SPLITTER BOXES | 42 | 2023-06-05 | 2023-07-24 | 2023-11-17 | 2024-01-04 | 142
INSTRUMENT EQUIPMENTS |  |  | 60 | 2023-06-03 | 2023-08-11 | 2023-11-18 | 2024-01-19 | 138
0 | FTIN1100 | HD-T4 - INSTALL ICSS SYSTEM - MEZZ DECK | 9 | 2023-06-05 | 2023-06-15 | 2023-11-27 | 2023-12-06 | 150
0 | FTIN1170 | HD-T4 - INSTALL TELECOM SYSTEM - MAIN / MEZZ DECK | 18 | 2023-06-03 | 2023-06-24 | 2023-12-14 | 2024-01-03 | 166
0 | FTIN1080 | HD-T4 - INSTALL WELLHEAD CONTROL PANEL - MEZZ DECK | 12 | 2023-06-20 | 2023-07-04 | 2023-11-18 | 2023-12-01 | 130
0 | FTIN1090 | HD-T4 - INSTALL HIPPS SYSTEM - MAIN DECK | 12 | 2023-06-27 | 2023-07-11 | 2023-11-18 | 2023-12-01 | 124
0 | FTIN1200 | HD-T4 - INSTALL IRCD SKID | 9 | 2023-07-10 | 2023-07-20 | 2023-12-02 | 2023-12-12 | 125
0 | FTIN1070 | HD-T4 - INSTALL INSTRUMENT VALVES - MAIN/ MEZZ/ CELLAR DECK | 24 | 2023-07-15 | 2023-08-11 | 2023-12-18 | 2024-01-13 | 133
0 | FTIN1110 | HD-T4 - INSTALL FLOW METERS - MAIN / MEZZ DECK | 24 | 2023-07-15 | 2023-08-11 | 2023-12-23 | 2024-01-19 | 138
INSTRUMENT TUBING & INCONEL PIPING |  |  | 46 | 2023-07-12 | 2023-09-02 | 2023-12-14 | 2024-01-31 | 129
0 | FTIN1190 | HD-T4 - INSTALL - INCONEL PIPING | 36 | 2023-07-12 | 2023-08-22 | 2023-12-14 | 2024-01-24 | 133
0 | FTIN1130 | HD-T4 - INSTALL - INSTRUMENT TUBING | 36 | 2023-07-17 | 2023-08-26 | 2023-12-14 | 2024-01-24 | 129
0 | FTIN1120 | HD-T4 - PRESSURE TEST - INSTRUMENT TUBING | 24 | 2023-08-07 | 2023-09-02 | 2024-01-04 | 2024-01-31 | 129
INSTRUMENT/TELECOM SYSTEMS MECHANICAL COMPLETION |  |  | 32 | 2023-08-02 | 2023-09-08 | 2024-01-13 | 2024-02-03 | 128
0 | FTIN1150 | HD-T4 - MECHANICAL COMPLETION - TELECOM SYSTEM | 12 | 2023-08-02 | 2023-08-16 | 2024-01-22 | 2024-02-03 | 148
0 | FTIN1140 | HD-T4 - MECHANICAL COMPLETION - CONTROL SYSTEM | 15 | 2023-08-22 | 2023-09-08 | 2024-01-13 | 2024-01-30 | 124
PUNCHLIST CLEARANCE - INSTRUMENT |  |  | 20 | 2023-08-21 | 2023-09-13 | 2024-01-16 | 2024-02-07 | 127
0 | FTIN1160 | HD-T4 - PUNCHLIST CLEARANCE - INSTRUMENTATION | 20 | 2023-08-21 | 2023-09-13 | 2024-01-16 | 2024-02-07 | 127
SAFETY |  |  | 45 | 2023-08-02 | 2023-09-23 | 2024-01-10 | 2024-02-19 | 128
0 | FTSA1010 | HD-T4 - INSTALLATION OF SAFETY EQUIPMENT | 20 | 2023-08-02 | 2023-08-25 | 2024-01-10 | 2024-02-01 | 138
0 | FTSA1000 | HD-T4 - INSTALLATION OF SAFETY SIGN | 15 | 2023-09-06 | 2023-09-23 | 2024-02-02 | 2024-02-19 | 128
PAINTING |  |  | 294 | 2022-10-28 | 2023-10-06 | 2023-06-01 | 2024-03-04 | 129
BLAST/PAINT- MAIN STRUCTURE |  |  | 165 | 2022-10-28 | 2023-05-09 | 2023-06-01 | 2023-12-14 | 189
BLAST/PAINT- CELLAR DECK |  |  | 96 | 2022-10-28 | 2023-02-17 | 2023-06-01 | 2023-08-12 | 152
0 | FTSTPN1000 | HD-T4 - BLAST/PAINT - DECK BRACES (BTWN CELLAR & MAIN DECK) | 24 | 2022-10-28 | 2022-11-25 | 2023-06-01 | 2023-06-28 | 185
0 | FTSTPN1010 | HD-T4 - BLAST/PAINT - DECK LEGS (BTWN CELLAR, & MAIN DECK) | 15 | 2022-12-02 | 2022-12-20 | 2023-06-12 | 2023-06-28 | 164
0 | FTSTPN1020 | HD-T4 - BLAST/PAINT - CELLAR DECK | 21 | 2023-01-24 | 2023-02-17 | 2023-07-20 | 2023-08-12 | 152
BLAST/PAINT- MAIN DECK |  |  | 81 | 2022-11-15 | 2023-02-17 | 2023-06-08 | 2023-08-19 | 158
0 | FTSTPN1030 | HD-T4 - BLAST/PAINT - DECK BRACES (BTWN MAIN DECK & MEZZANINE DECK) | 24 | 2022-11-15 | 2022-12-13 | 2023-06-08 | 2023-07-05 | 176
0 | FTSTPN1040 | HD-T4 - BLAST/PAINT - DECK LEGS (BTWN MAIN DECK & MEZZANINE DECK) | 15 | 2022-11-25 | 2022-12-13 | 2023-06-19 | 2023-07-05 | 176
0 | FTSTPN1050 | HD-T4 - BLAST/PAINT - MAIN DECK | 21 | 2023-01-24 | 2023-02-17 | 2023-07-27 | 2023-08-19 | 158
BLAST/PAINT- MEZZANINE DECK |  |  | 79 | 2022-11-29 | 2023-03-01 | 2023-06-09 | 2023-09-02 | 160
0 | FTSTPN1070 | HD-T4 - BLAST/PAINT - DECK LEGS (BTWN MEZZANINE DECK & WEATHER DK) | 15 | 2022-12-02 | 2022-12-20 | 2023-06-20 | 2023-07-06 | 171
0 | FTSTPN1060 | HD-T4 - BLAST/PAINT - DECK BRACES (BTWN MEZZANINE DECK & WEATHER DK) | 24 | 2022-11-29 | 2022-12-27 | 2023-06-09 | 2023-07-06 | 165
0 | FTSTPN1080 | HD-T4 - BLAST/PAINT - MEZZANINE DECK | 21 | 2023-02-04 | 2023-03-01 | 2023-08-10 | 2023-09-02 | 160
BLAST/PAINT- ACCESS PLATFORM |  |  | 21 | 2023-02-16 | 2023-03-13 | 2023-08-07 | 2023-08-30 | 147
0 | FTSTPN1090 | HD-T4 - BLAST/PAINT - ACCESS PLATFORMS | 21 | 2023-02-16 | 2023-03-13 | 2023-08-07 | 2023-08-30 | 147
BLAST/PAINT-WEATHE DECK |  |  | 21 | 2023-03-01 | 2023-03-25 | 2023-09-13 | 2023-10-06 | 168
0 | FTSTPN1100 | HD-T4 - BLAST/PAINT - WEATHER DECK | 21 | 2023-03-01 | 2023-03-25 | 2023-09-13 | 2023-10-06 | 168
BLAST/PAINT- HELI DECK |  |  | 21 | 2023-04-14 | 2023-05-09 | 2023-11-21 | 2023-12-14 | 189
0 | FTSTPN1110 | HD-T4 - BLAST/PAINT - HELI DECK | 21 | 2023-04-14 | 2023-05-09 | 2023-11-21 | 2023-12-14 | 189
BLAST/PAINT- OTHER STRUCT/ACCESSORIES |  |  | 214 | 2023-01-30 | 2023-10-06 | 2023-07-13 | 2024-03-04 | 129
GALVANIZE/PAINT - HANDRAILS/LADDERS |  |  | 86 | 2023-01-30 | 2023-05-10 | 2023-08-24 | 2024-01-17 | 217
0 | FTSTPN1200 | HD-T4 - GALVANIZE - HANDRAILS CELLAR DECK | 18 | 2023-01-30 | 2023-02-20 | 2023-08-24 | 2023-09-13 | 177
0 | FTSTPN1190 | HD-T4 - GALVANIZE - HANDRAILS MAIN DECK | 18 | 2023-02-13 | 2023-03-06 | 2023-09-07 | 2023-09-27 | 177
0 | FTSTPN1160 | HD-T4 - PAINT - HANDRAILS CELLAR DECK | 18 | 2023-02-20 | 2023-03-13 | 2023-09-14 | 2023-10-04 | 177
0 | FTSTPN1180 | HD-T4 - GALVANIZE - HANDRAILS (MEZZANINE DECK) | 18 | 2023-02-27 | 2023-03-20 | 2023-10-26 | 2023-11-15 | 207
0 | FTSTPN1150 | HD-T4 - PAINT - HANDRAILS MAIN DECK | 18 | 2023-03-06 | 2023-03-27 | 2023-09-28 | 2023-10-18 | 177
0 | FTSTPN1140 | HD-T4 - PAINT - HANDRAILS (MEZZANINE DECK) | 18 | 2023-03-20 | 2023-04-10 | 2023-11-16 | 2023-12-06 | 207
0 | FTSTPN1170 | HD-T4 - GALVANIZE - HANDRAILS (WEATHER DECK) | 22 | 2023-03-15 | 2023-04-10 | 2023-12-02 | 2023-12-27 | 225
0 | FTSTPN1130 | HD-T4 - PAINT - HANDRAILS (WEATHER DECK) | 18 | 2023-04-10 | 2023-05-01 | 2023-12-28 | 2024-01-17 | 225
0 | FTSTPN1120 | HD-T4 - BLAST/PAINT - LADDERS & CAGES | 60 | 2023-03-01 | 2023-05-10 | 2023-09-14 | 2023-11-22 | 169
BLAST/PAINT - STAIRWAYS |  |  | 72 | 2023-03-27 | 2023-06-19 | 2023-11-28 | 2024-01-17 | 183
EAST SIDE |  |  | 36 | 2023-03-27 | 2023-05-08 | 2023-11-28 | 2023-12-18 | 193
0 | FTSTPN1210 | HD-T4 - BLAST/PAINT - CELLAR DECK TO JACKET WALKWAY (EAST SIDE) | 18 | 2023-03-27 | 2023-04-17 | 2023-11-28 | 2023-12-18 | 211
0 | FTSTPN1220 | HD-T4 - BLAST/PAINT - MAIN DECK TO CELLAR DECK (EAST SIDE) | 18 | 2023-04-03 | 2023-04-24 | 2023-11-28 | 2023-12-18 | 205
0 | FTSTPN1230 | HD-T4 - BLAST/PAINT - MEZZANINE DECK TO MAIN DECK (EAST SIDE) | 18 | 2023-04-10 | 2023-05-01 | 2023-11-28 | 2023-12-18 | 199
0 | FTSTPN1240 | HD-T4 - BLAST/PAINT - MAIN DECK TO MEZZANINE DECK (EAST SIDE) | 18 | 2023-04-17 | 2023-05-08 | 2023-11-28 | 2023-12-18 | 193
NORTH SIDE |  |  | 39 | 2023-04-06 | 2023-05-22 | 2023-12-07 | 2023-12-27 | 189
0 | FTSTPN1250 | HD-T4 - BLAST/PAINT - MONKEY LADDER FROM MAIN. DECK TO CELLAR DECK (NORTH SIDE) | 18 | 2023-04-06 | 2023-04-27 | 2023-12-07 | 2023-12-27 | 210
0 | FTSTPN1260 | HD-T4 - BLAST/PAINT - MONKEY LADDER FROM MEZZANINE DECK TO MAIN DECK (NORTH SIDE) | 18 | 2023-04-20 | 2023-05-11 | 2023-12-07 | 2023-12-27 | 198
0 | FTSTPN1270 | HD-T4 - BLAST/PAINT - MONKEY LADDER FROM MAIN DECK TO MEZZANINE DECK (NORTH SIDE) | 18 | 2023-05-01 | 2023-05-22 | 2023-12-07 | 2023-12-27 | 189
OTHER MISCELLENEOUS |  |  | 42 | 2023-05-01 | 2023-06-19 | 2023-11-30 | 2024-01-17 | 183
0 | FTSTPN1280 | HD-T4 - BLAST/PAINT - STAIRWAYS (OTHER MISC.) | 42 | 2023-05-01 | 2023-06-19 | 2023-11-30 | 2024-01-17 | 183
BLAST/PAINT - PIPE SUPPORTS |  |  | 60 | 2023-03-06 | 2023-05-15 | 2023-08-14 | 2023-10-21 | 138
0 | FTSTPN1290 | HD-T4 - BLAST/PAINT - BALANCE PIPE SUPPORTS | 60 | 2023-03-06 | 2023-05-15 | 2023-08-14 | 2023-10-21 | 138
BLAST/PAINTING - PIPING |  |  | 56 | 2023-03-08 | 2023-05-12 | 2023-09-11 | 2023-11-14 | 160
0 | FTPIPN1000 | HD-T4 - BLAST/PAINT - CU-NI/ INCONEL PIPING SPOOLS | 42 | 2023-03-08 | 2023-04-26 | 2023-09-20 | 2023-11-07 | 168
0 | FTPIPN1010 | HD-T4 - BLAST/PAINT - SS PIPING SPOOLS | 30 | 2023-04-03 | 2023-05-08 | 2023-10-04 | 2023-11-07 | 158
0 | FTPIPN1020 | HD-T4 - BLAST/PAINT - CS/LTCS / CLADDED PIPING SPOOLS | 56 | 2023-03-08 | 2023-05-12 | 2023-09-11 | 2023-11-14 | 160
BLAST/PAINT - EQUIPMENT SUPPORTS |  |  | 42 | 2023-04-18 | 2023-06-06 | 2023-10-27 | 2023-12-22 | 172
0 | FTSTPN1300 | HD-T4 - BLAST/PAINT - VENT SUPPORT STRUCTURE | 24 | 2023-05-08 | 2023-06-05 | 2023-11-25 | 2023-12-22 | 173
0 | FTSTPN1310 | HD-T4 - BLAST/PAINT - BALANCE EQUIPMENT SUPPORTS | 42 | 2023-04-18 | 2023-06-06 | 2023-10-27 | 2023-12-14 | 165
BLAST/PAINT - E&I SUPPORTS |  |  | 56 | 2023-04-06 | 2023-06-10 | 2023-09-07 | 2023-11-10 | 132
0 | FTSTPN1330 | HD-T4 - BLAST/PAINT - SECONDARY CABLE TRAY SUPPORTS | 42 | 2023-04-06 | 2023-05-25 | 2023-09-15 | 2023-11-02 | 139
0 | FTSTPN1320 | HD-T4 - BLAST/PAINT - BALANCE MAIN CABLE TRAY SUPPORTS | 56 | 2023-04-06 | 2023-06-10 | 2023-09-07 | 2023-11-10 | 132
BLAST/PAINT - OTHER SUPPORTS |  |  | 63 | 2023-03-29 | 2023-06-10 | 2023-09-11 | 2023-11-29 | 148
0 | FTSTPN1360 | HD-T4 - BLAST/PAINT - OTHER E&I SUPPORTS MAIN DECK | 30 | 2023-03-29 | 2023-05-03 | 2023-09-26 | 2023-10-30 | 155
0 | FTSTPN1370 | HD-T4 - BLAST/PAINT - OTHER E&I SUPPORTS (CELLAR DDK) | 30 | 2023-04-03 | 2023-05-08 | 2023-09-11 | 2023-10-14 | 138
0 | FTSTPN1350 | HD-T4 - BLAST/PAINT - OTHER E&I SUPPORTS (MEZZANINE DK) | 30 | 2023-04-07 | 2023-05-12 | 2023-09-14 | 2023-10-18 | 137
0 | FTSTPN1340 | HD-T4 - BLAST/PAINT - OTHER E&I SUPPORTS (WEATHER MDK) | 30 | 2023-04-17 | 2023-05-22 | 2023-09-29 | 2023-11-02 | 142
0 | FTSTPN1380 | HD-T4 - BLAST/PAINT - BALANCE OTHER E&I SUPPORTS | 56 | 2023-04-06 | 2023-06-10 | 2023-09-26 | 2023-11-29 | 148
BLAST/PAINT - OTHER STRUCTURES |  |  | 160 | 2023-02-10 | 2023-08-16 | 2023-07-13 | 2024-01-08 | 125
0 | FTSTPN1390 | HD-T4 - BLAST/PAINT - DECK PAD EYES | 24 | 2023-02-15 | 2023-03-15 | 2023-07-13 | 2023-08-09 | 127
0 | FTSTPN1440 | HD-T4 - BLAST/PAINT - STABBING GUIDES | 12 | 2023-03-03 | 2023-03-17 | 2023-08-31 | 2023-09-13 | 155
0 | FTSTPN1430 | HD-T4 - BLAST/PAINT - MONORAILS FRAME | 60 | 2023-02-10 | 2023-04-21 | 2023-10-03 | 2023-12-11 | 201
0 | FTSTPN1420 | HD-T4 - BLAST/PAINT - DECK HATCHES | 30 | 2023-03-29 | 2023-05-03 | 2023-11-21 | 2023-12-25 | 203
0 | FTSTPN1450 | HD-T4 - BLAST/PAINT - FLARE BOOM | 18 | 2023-04-21 | 2023-05-12 | 2023-12-11 | 2023-12-30 | 200
0 | FTSTPN1400 | HD-T4 - BLAST/PAINT - GRATINGS | 42 | 2023-03-25 | 2023-05-13 | 2023-08-22 | 2023-10-09 | 128
0 | FTSTPN1410 | HD-T4 - BLAST/PAINT - PLATFORM IDENTIFICATION PANELS | 18 | 2023-05-29 | 2023-06-19 | 2023-12-16 | 2024-01-05 | 173
0 | FTSTPN1460 | HD-T4 - BLAST/PAINT - MISCELLANEOUS STRUCTRUAL ITEMS | 60 | 2023-06-07 | 2023-08-16 | 2023-10-31 | 2024-01-08 | 125
FINAL TOUCH-UP PAINTING |  |  | 100 | 2023-06-12 | 2023-10-06 | 2023-11-09 | 2024-03-04 | 129
0 | FTSTPN1470 | HD-T4 - FIRE PROOFING ON DECK STRUCTURE | 60 | 2023-07-10 | 2023-09-18 | 2023-12-06 | 2024-02-13 | 128
0 | FTSTPN1480 | HD-T4 - FINAL PAINT & TOUCH-UP PAINTING | 100 | 2023-06-12 | 2023-10-06 | 2023-11-09 | 2024-03-04 | 129
MISCELLANEOUS WORKS |  |  | 42 | 2023-06-09 | 2023-07-28 | 2024-01-02 | 2024-02-19 | 177
0 | FTST5000 | HD-T4 - MISCELLANEOUS WORKS | 42 | 2023-06-09 | 2023-07-28 | 2024-01-02 | 2024-02-19 | 177
COMMISIONING |  |  | 49 | 2023-08-16 | 2023-10-12 | 2024-01-11 | 2024-03-04 | 124
0 | FTCG1030 | HD-T4 - 415V AUXILIARY DB | 3 | 2023-08-18 | 2023-08-22 | 2024-01-19 | 2024-01-22 | 132
0 | FTCG1040 | HD-T4 - 24V DC UPS BATTERY CHARGER & BATTERY | 6 | 2023-08-19 | 2023-08-26 | 2024-01-20 | 2024-01-26 | 132
0 | FTCG1020 | HD-T4 - 415 V SWITCHGEAR (2 I/C +15 FDRS.+ 3 SPR.) | 15 | 2023-08-16 | 2023-09-02 | 2024-01-11 | 2024-01-27 | 127
0 | FTCG1050 | HD-T4 - ECMS SYSTEM | 14 | 2023-08-25 | 2023-09-11 | 2024-01-26 | 2024-02-10 | 132
0 | FTCG1090 | HD-T4 - MOV POWER DB | 2 | 2023-09-08 | 2023-09-11 | 2024-02-07 | 2024-02-08 | 130
0 | FTCG1080 | HD-T4 - TELECOM & LAN SYSTEM - 3 NOS | 5 | 2023-09-08 | 2023-09-14 | 2024-02-05 | 2024-02-09 | 128
0 | FTCG1100 | HD-T4 - NAVIGATIONAL AID SYSTEM | 3 | 2023-09-11 | 2023-09-14 | 2024-02-09 | 2024-02-12 | 130
0 | FTCG1110 | HD-T4 - CCTV SYSTEM - 3 NOS | 3 | 2023-09-13 | 2023-09-16 | 2024-02-09 | 2024-02-12 | 128
0 | FTCG1130 | HD-T4 - BIRD DETERRENT SYSTEM- | 2 | 2023-09-16 | 2023-09-19 | 2024-02-13 | 2024-02-14 | 128
0 | FTCG1140 | HD-T4 - UHF RADIO - 3 NOS | 2 | 2023-09-16 | 2023-09-19 | 2024-02-13 | 2024-02-14 | 128
0 | FTCG1060 | HD-T4 - RTU SYSTEM (OTP & LOOP CHECKING) | 14 | 2023-09-04 | 2023-09-20 | 2024-01-26 | 2024-02-10 | 124
0 | FTCG1150 | HD-T4 - 6.6 KV RMU SYSTEM | 6 | 2023-09-13 | 2023-09-20 | 2024-02-12 | 2024-02-17 | 130
0 | FTCG1120 | HD-T4 - WELL HEAD CONTROL PANEL (OTP & LOOP CHECKING) | 6 | 2023-09-14 | 2023-09-21 | 2024-02-09 | 2024-02-15 | 127
0 | FTCG1190 | HD-T4 - CLOSED DRAIN | 3 | 2023-09-20 | 2023-09-23 | 2024-02-12 | 2024-02-14 | 124
0 | FTCG1070 | HD-T4 - ESD SYSTEM (OTP & LOOP CHECKING) | 14 | 2023-09-08 | 2023-09-25 | 2024-01-31 | 2024-02-15 | 124
0 | FTCG1200 | HD-T4 - COMM -CHEMICAL INJECTION | 4 | 2023-09-22 | 2023-09-27 | 2024-02-14 | 2024-02-17 | 124
0 | FTCG1170 | HD-T4 - HIPPS (OTP & LOOP CHECKING | 5 | 2023-09-22 | 2023-09-28 | 2024-02-14 | 2024-02-19 | 124
0 | FTCG1180 | HD-T4 - 6.6KV / 433V POWER TRANSFORMER | 4 | 2023-09-23 | 2023-09-28 | 2024-02-15 | 2024-02-19 | 124
0 | FTCG1240 | HD-T4 - MPFM - COMMUNICATION ESTABLISHMENT | 3 | 2023-09-27 | 2023-09-30 | 2024-02-19 | 2024-02-21 | 124
0 | FTCG1220 | HD-T4 - WELL SLOT-1 (WELL#626) | 6 | 2023-09-25 | 2023-10-02 | 2024-02-16 | 2024-02-22 | 124
0 | FTCG1210 | HD-T4 - LIGHTING SYSTEM | 5 | 2023-09-28 | 2023-10-04 | 2024-02-20 | 2024-02-24 | 124
0 | FTCG1250 | HD-T4 - PRODUCTION MANIFOLD | 3 | 2023-09-30 | 2023-10-04 | 2024-02-22 | 2024-02-24 | 124
0 | FTCG1160 | HD-T4 - FIRE &GAS SYSTEM (OTP & LOOP CHECKING) | 11 | 2023-09-22 | 2023-10-05 | 2024-02-14 | 2024-02-26 | 124
0 | FTCG1260 | HD-T4 - COMM -PIG LAUNCHER/RECEIVER | 3 | 2023-10-04 | 2023-10-07 | 2024-02-26 | 2024-02-28 | 124
0 | FTCG1270 | HD-T4 - VENT & DRAIN SYSTEM OTP | 4 | 2023-10-05 | 2023-10-10 | 2024-02-27 | 2024-03-01 | 124
0 | FTCG1280 | HD-T4 - FIRE FIGHTING & SAFETY EQUIPMENT | 3 | 2023-10-06 | 2023-10-10 | 2024-02-28 | 2024-03-01 | 124
0 | FTCG1230 | HD-T4 - LEAK TEST | 14 | 2023-09-26 | 2023-10-12 | 2024-02-17 | 2024-03-04 | 124
READY FOR LOADOUT |  |  | 26 | 2023-09-16 | 2023-10-12 | 2024-02-13 | 2024-03-13 | 153
0 | FTLO1010 | HD-T4 - FINAL DECK WEIGHING | 6 | 2023-09-16 | 2023-09-23 | 2024-02-13 | 2024-02-19 | 128
0 | FTLO2010 | HD-T4 - COMPANY WALK THROUGH AND PUNCH LIST CLEARANCE | 12 | 2023-09-23 | 2023-10-07 | 2024-02-20 | 2024-03-04 | 128
0 | FTLO1000 | HD-T4 - READY FOR LOADOUT - WHP HD-T4 TOPSIDE | 0 |  | 2023-10-12 |  | 2024-03-04 | 124
0 | FTLO2020 | HD-T4 - STAND BY FOR LOADOUT - WHP HD-T4 TOPSIDE | 0 | 2023-10-12 | 2023-10-12 | 2024-03-13 | 2024-03-13 | 153
FABRICATION HAIR DALMA WHP HD-03 TOPSIDE |  |  | 313 | 2022-10-11 | 2023-10-11 | 2023-01-09 | 2024-03-04 | 125
STRUCTURAL |  |  | 291 | 2022-10-11 | 2023-09-15 | 2023-01-09 | 2024-02-21 | 137
STRUCTURAL PRE-FABRICATION |  |  | 252 | 2022-10-11 | 2023-08-01 | 2023-01-09 | 2024-01-11 | 141
PRE-FAB PLATES |  |  | 42 | 2022-10-11 | 2022-11-29 | 2023-01-09 | 2023-04-11 | 115
0 | FHST1010 | HD-03 - CUT & PROFILE - PLATES (CELLAR DECK) | 15 | 2022-10-11 | 2022-10-28 | 2023-01-09 | 2023-01-25 | 77
0 | FHST1000 | HD-03 - CUT & PROFILE - PLATES ESDV DECK | 15 | 2022-10-18 | 2022-11-04 | 2023-01-16 | 2023-02-01 | 77
0 | FHST1020 | HD-03 - CUT & PROFILE - PLATES (UPPER DECK) | 15 | 2022-10-25 | 2022-11-11 | 2023-01-23 | 2023-02-08 | 77
0 | FHST1030 | HD-03 - CUT & PROFILE - PLATES (WEATHER DECK) | 15 | 2022-11-01 | 2022-11-18 | 2023-03-25 | 2023-04-11 | 124
0 | FHST1040 | HD-03 - CUT & PROFILE - PLATES (MAIN DECK) | 15 | 2022-11-11 | 2022-11-29 | 2023-02-09 | 2023-02-25 | 77
PRE-FAB GIRDERS |  |  | 42 | 2022-10-18 | 2022-12-06 | 2023-02-02 | 2023-04-28 | 124
0 | FHST1060 | HD-03 - SUB ASSEMBLE - GIRDERS (CELLAR DECK) | 18 | 2022-10-18 | 2022-11-08 | 2023-02-02 | 2023-02-22 | 92
0 | FHST1050 | HD-03 - SUB ASSEMBLE - GIRDERS ESDV DECK | 18 | 2022-10-25 | 2022-11-15 | 2023-02-09 | 2023-03-01 | 92
0 | FHST1090 | HD-03 - SUB ASSEMBLE - GIRDERS (MAIN DECK) | 18 | 2022-10-27 | 2022-11-17 | 2023-04-08 | 2023-04-28 | 140
0 | FHST1070 | HD-03 - SUB ASSEMBLE - GIRDERS (UPPER DECK) | 18 | 2022-11-01 | 2022-11-22 | 2023-03-22 | 2023-04-11 | 121
0 | FHST1080 | HD-03 - SUB ASSEMBLE - GIRDERS (WEATHER DECK) | 18 | 2022-11-15 | 2022-12-06 | 2023-04-08 | 2023-04-28 | 124
WORKSHOP SUB-ASSEMBLE - DECK NODES |  |  | 27 | 2022-11-11 | 2022-12-13 | 2023-02-09 | 2023-05-05 | 124
0 | FHST1130 | HD-03 - SUB ASSEMBLE - NODES (CELLAR DECK) | 18 | 2022-11-11 | 2022-12-02 | 2023-02-09 | 2023-03-01 | 77
0 | FHST1120 | HD-03 - SUB ASSEMBLE - NODES (UPPER DECK) | 18 | 2022-11-14 | 2022-12-05 | 2023-03-29 | 2023-04-18 | 116
0 | FHST1100 | HD-03 - SUB ASSEMBLE - NODES ESDV DECK | 18 | 2022-11-18 | 2022-12-09 | 2023-02-16 | 2023-03-08 | 77
0 | FHST1140 | HD-03 - SUB ASSEMBLE - NODES (MAIN DECK) | 18 | 2022-11-18 | 2022-12-09 | 2023-04-08 | 2023-04-28 | 121
0 | FHST1110 | HD-03 - SUB ASSEMBLE - NODES (WEATHER DECK) | 18 | 2022-11-22 | 2022-12-13 | 2023-04-15 | 2023-05-05 | 124
PRE-FAB SECTIONS |  |  | 110 | 2022-10-25 | 2023-03-02 | 2023-02-20 | 2023-08-14 | 142
0 | FHST1190 | HD-03 - CUT & PROFILE - SECTIONS (CELLAR DECK) | 21 | 2022-10-25 | 2022-11-18 | 2023-02-20 | 2023-03-15 | 101
0 | FHST1160 | HD-03 - CUT & PROFILE - SECTIONS ESDV DECK | 21 | 2022-11-01 | 2022-11-25 | 2023-02-27 | 2023-03-22 | 101
0 | FHST1180 | HD-03 - CUT & PROFILE - SECTIONS (UPPER DECK) | 21 | 2022-11-21 | 2022-12-15 | 2023-03-18 | 2023-04-11 | 101
0 | FHST1170 | HD-03 - CUT & PROFILE - SECTIONS (WEATHER DECK) | 21 | 2022-11-28 | 2022-12-22 | 2023-05-10 | 2023-06-02 | 140
0 | FHST1200 | HD-03 - CUT & PROFILE - SECTIONS (MAIN DECK) | 18 | 2022-12-05 | 2022-12-26 | 2023-04-01 | 2023-04-21 | 101
0 | FHST1150 | HD-03 - CUT & PROFILE - SECTIONS (OTHER MISC.) | 60 | 2022-12-22 | 2023-03-02 | 2023-06-06 | 2023-08-14 | 142
PRE-FAB TUBULARS |  |  | 111 | 2022-11-01 | 2023-03-10 | 2023-02-23 | 2023-09-18 | 165
0 | FHST1240 | HD-03 - CUT & PROFILE - TUBULARS (B/W ESDV DECK & (CELLAR DECK) | 24 | 2022-11-01 | 2022-11-29 | 2023-02-23 | 2023-03-22 | 98
0 | FHST1230 | HD-03 - CUT & PROFILE - TUBULARS (B/W (CELLAR DECK) & (UPPER DECK) | 24 | 2022-11-08 | 2022-12-06 | 2023-03-16 | 2023-04-12 | 110
0 | FHST1220 | HD-03 - CUT & PROFILE - TUBULARS (B/W (UPPER DECK) & WEATHER DECK) | 24 | 2022-11-15 | 2022-12-13 | 2023-04-22 | 2023-05-19 | 136
0 | FHST1250 | HD-03 - CUT & PROFILE - TUBULARS (B/W (MAIN DECK) & (UPPER DECK) | 24 | 2022-11-15 | 2022-12-13 | 2023-05-17 | 2023-06-13 | 157
0 | FHST1210 | HD-03 - CUT & PROFILE - TUBULARS (OTHER MISC.) | 75 | 2022-12-13 | 2023-03-10 | 2023-06-23 | 2023-09-18 | 165
WORKSHOP SUB-ASSEMBLE - HANDRAILS & LADDERS |  |  | 117 | 2022-12-26 | 2023-05-11 | 2023-06-29 | 2023-10-11 | 132
0 | FHST1300 | HD-03 - SUB ASSEMBLE - HANDRAILS ESDV DECK | 36 | 2022-12-26 | 2023-02-06 | 2023-06-29 | 2023-08-09 | 159
0 | FHST1290 | HD-03 - SUB ASSEMBLE - HANDRAILS (CELLAR DECK) | 36 | 2023-01-09 | 2023-02-20 | 2023-07-13 | 2023-08-23 | 159
0 | FHST1280 | HD-03 - SUB ASSEMBLE - HANDRAILS (UPPER DECK) | 36 | 2023-01-23 | 2023-03-06 | 2023-07-27 | 2023-09-06 | 159
0 | FHST1270 | HD-03 - SUB ASSEMBLE - HANDRAILS (WEATHER DECK)) | 36 | 2023-02-06 | 2023-03-20 | 2023-08-10 | 2023-09-20 | 159
0 | FHST1260 | HD-03 - SUB ASSEMBLE - LADDERS & CAGES | 48 | 2023-03-16 | 2023-05-11 | 2023-08-17 | 2023-10-11 | 132
WORKSHOP SUB ASSEMBLE - STAIRWAYS / STAIR TOWER / MAIN LADDER |  |  | 78 | 2023-03-02 | 2023-06-01 | 2023-08-15 | 2024-01-01 | 184
NORTH SIDE |  |  | 42 | 2023-03-02 | 2023-04-20 | 2023-08-15 | 2023-10-02 | 142
0 | FHST1310 | HD-03 - SUB ASSEMBLE - ESDV DECK TO JACKET WALKWAY (NORTH SIDE) STAIR WAYS | 24 | 2023-03-02 | 2023-03-30 | 2023-08-15 | 2023-09-11 | 142
0 | FHST1320 | HD-03 - SUB ASSEMBLE - NORTH SIDE NORTH SIDE | 24 | 2023-03-09 | 2023-04-06 | 2023-08-22 | 2023-09-18 | 142
0 | FHST1330 | HD-03 - SUB ASSEMBLE - MEZZANINE DECK TO (CELLAR DECK) (NORTH SIDE) | 24 | 2023-03-16 | 2023-04-13 | 2023-08-29 | 2023-09-25 | 142
0 | FHST1340 | HD-03 - SUB ASSEMBLE - WEATHER DECK TO (UPPER DECK) (NORTH SIDE) | 24 | 2023-03-23 | 2023-04-20 | 2023-09-05 | 2023-10-02 | 142
SOUTH SIDE |  |  | 42 | 2023-03-16 | 2023-05-04 | 2023-10-17 | 2023-12-11 | 190
0 | FHST1350 | HD-03 - SUB ASSEMBLE - SOUTH SIDE STAIR WAYS | 21 | 2023-03-16 | 2023-04-10 | 2023-10-17 | 2023-11-09 | 184
0 | FHST1360 | HD-03 - SUB ASSEMBLE - MAIN LADDER FROM (UPPER DECK) TO (CELLAR DECK) (SOUTH SIDE) | 21 | 2023-03-30 | 2023-04-24 | 2023-11-07 | 2023-11-30 | 190
0 | FHST1370 | HD-03 - SUB ASSEMBLE - MAIN LADDER FROM WEATHER DECK TO (UPPER DECK) (SOUTH SIDE) | 21 | 2023-04-10 | 2023-05-04 | 2023-11-17 | 2023-12-11 | 190
OTHER MISCELLANEOUS |  |  | 60 | 2023-03-23 | 2023-06-01 | 2023-10-24 | 2024-01-01 | 184
0 | FHST1380 | HD-03 - SUB ASSEMBLE - STAIRWAYS (OTHER MISC.) | 60 | 2023-03-23 | 2023-06-01 | 2023-10-24 | 2024-01-01 | 184
FLOOR DRAINS |  |  | 48 | 2022-11-04 | 2022-12-30 | 2023-03-30 | 2023-07-04 | 160
0 | FHST1390 | HD-03 - SUB ASSEMBLE - FLOOR DRAINS (CELLAR DK) | 21 | 2022-11-04 | 2022-11-29 | 2023-03-30 | 2023-04-22 | 125
0 | FHST1420 | HD-03 - SUB ASSEMBLE - FLOOR DRAINS (CELLAR DECK) | 30 | 2022-11-11 | 2022-12-16 | 2023-04-06 | 2023-05-10 | 125
0 | FHST1410 | HD-03 - SUB ASSEMBLE - FLOOR DRAINS (UPPER DECK) | 30 | 2022-11-18 | 2022-12-23 | 2023-05-17 | 2023-06-20 | 154
0 | FHST1400 | HD-03 - SUB ASSEMBLE - FLOOR DRAINS (WEATHER DK) | 30 | 2022-11-25 | 2022-12-30 | 2023-05-31 | 2023-07-04 | 160
WORKSHOP SUB-ASSEMBLE - OTHER STRUCTURES |  |  | 231 | 2022-11-04 | 2023-08-01 | 2023-03-22 | 2024-01-11 | 141
0 | FHST1460 | HD-03 - SUB ASSEMBLE - DECK PENETRATIONS | 36 | 2022-11-04 | 2022-12-16 | 2023-03-22 | 2023-05-02 | 118
0 | FHST1480 | HD-03 - SUB ASSEMBLE - STABBING GUIDES | 24 | 2023-01-12 | 2023-02-09 | 2023-05-11 | 2023-06-07 | 102
0 | FHST1440 | HD-03 - SUB ASSEMBLE DECK PADEYES | 45 | 2023-01-04 | 2023-02-25 | 2023-05-03 | 2023-06-23 | 102
0 | FHST1500 | HD-03 - SUB ASSEMBLE - MONORAIL FRAMES | 56 | 2023-01-17 | 2023-03-23 | 2023-08-22 | 2023-10-25 | 186
0 | FHST1490 | HD-03 - SUB ASSEMBLE - DECK HATCHES | 42 | 2023-02-25 | 2023-04-15 | 2023-09-28 | 2023-11-15 | 184
0 | FHST1520 | HD-03 - SUB ASSEMBLE - FLARE BOOM | 30 | 2023-03-17 | 2023-04-21 | 2023-11-03 | 2023-12-07 | 198
0 | FHST1510 | HD-03 - FABRICATE MISCELLANEOUS ITEMS | 60 | 2023-03-17 | 2023-05-26 | 2023-11-03 | 2024-01-11 | 198
0 | FHST1470 | HD-03 - SUB ASSEMBLE - PLATFORM IDENTIFICATION PANELS | 42 | 2023-04-15 | 2023-06-03 | 2023-11-16 | 2024-01-03 | 184
0 | FHST1450 | HD-03 - SUB ASSEMBLE OTHER MISCL STRUCTURES | 70 | 2023-05-11 | 2023-08-01 | 2023-10-12 | 2024-01-01 | 132
PRE-FAB - PIPE SUPPORTS |  |  | 60 | 2023-01-31 | 2023-04-11 | 2023-04-17 | 2023-07-18 | 85
0 | FHST1570 | HD-03 - PRE-FAB -PIPE SUPPORTS (ESDV DECK) (Welded attachments to frame) | 12 | 2023-01-31 | 2023-02-14 | 2023-04-17 | 2023-04-29 | 65
0 | FHST1560 | HD-03 - PRE-FAB - PIPE SUPPORTS (CELLAR DECK) (Welded attachments to frame) | 18 | 2023-01-31 | 2023-02-21 | 2023-04-17 | 2023-05-06 | 65
0 | FHST1540 | HD-03 - PRE-FAB - PIPE SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-02-07 | 2023-02-28 | 2023-06-17 | 2023-07-07 | 112
0 | FHST1550 | HD-03 - PRE-FAB - PIPE SUPPORTS (UPPER DECK) (Welded attachments to frame) | 18 | 2023-02-07 | 2023-02-28 | 2023-04-24 | 2023-05-13 | 65
0 | FHST1580 | HD-03 - PRE-FAB - BALANCE PIPE SUPPORTS (Other than Welded attachments to frame) | 60 | 2023-01-31 | 2023-04-11 | 2023-05-10 | 2023-07-18 | 85
PRE-FAB - EQUIPMENT SUPPORTS |  |  | 78 | 2023-02-07 | 2023-05-09 | 2023-04-24 | 2023-07-29 | 71
0 | FHST1620 | HD-03 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (CELLAR DECK) (Welded attachments to frame) | 18 | 2023-02-07 | 2023-02-28 | 2023-04-24 | 2023-05-13 | 65
0 | FHST1610 | HD-03 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (UPPER DECK) (Welded attachments to frame) | 18 | 2023-02-14 | 2023-03-07 | 2023-05-01 | 2023-05-20 | 65
0 | FHST1630 | HD-03 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (ESDV DECK) (Welded attachments to frame) | 18 | 2023-02-14 | 2023-03-07 | 2023-07-10 | 2023-07-29 | 125
0 | FHST1600 | HD-03 - PRE-FAB - MAIN EQUIPMENT SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-02-21 | 2023-03-14 | 2023-05-08 | 2023-05-27 | 65
0 | FHST1590 | HD-03 - PRE-FAB - VENT SUPPORT STRUCTURE | 42 | 2023-02-21 | 2023-04-11 | 2023-05-30 | 2023-07-17 | 84
0 | FHST1640 | HD-03 - PRE-FAB - BALANCE EQUIPMENT SUPPORTS (Other than Welded attachments to frame) | 48 | 2023-03-14 | 2023-05-09 | 2023-05-29 | 2023-07-22 | 65
PRE-FAB - E & I CABLE TRAY SUPPORTS |  |  | 74 | 2023-02-21 | 2023-05-18 | 2023-07-17 | 2023-10-27 | 140
0 | FHST1680 | HD-03 - PRE-FAB - CABLE TRAY SUPPORTS (ESDV DECK) (Welded attachments to frame) | 15 | 2023-02-21 | 2023-03-10 | 2023-07-17 | 2023-08-02 | 125
0 | FHST1670 | HD-03 - PRE-FAB - CABLE TRAY SUPPORTS (CELLAR DECK) (Welded attachments to frame) | 15 | 2023-02-28 | 2023-03-17 | 2023-07-24 | 2023-08-09 | 125
0 | FHST1660 | HD-03 - PRE-FAB - CABLE TRAY SUPPORTS (UPPER DECK) (Welded attachments to frame) | 15 | 2023-03-07 | 2023-03-24 | 2023-08-30 | 2023-09-15 | 151
0 | FHST1650 | HD-03 - PRE-FAB - CABLE TRAY SUPPORTS (WEATHER DK) (Welded attachments to frame) | 15 | 2023-03-14 | 2023-03-31 | 2023-09-06 | 2023-09-22 | 151
0 | FHST1700 | HD-03 - PRE-FAB - SECONDARY CABLE TRAY SUPPORTS | 42 | 2023-03-21 | 2023-05-09 | 2023-09-09 | 2023-10-27 | 148
0 | FHST1690 | HD-03 - PRE-FAB - BALANCE CABLE TRAY SUPPORTS (Other than Welded attachments to frame) | 56 | 2023-03-14 | 2023-05-18 | 2023-08-24 | 2023-10-27 | 140
PRE-FAB - OTHER E&I SUPPORTS |  |  | 72 | 2023-03-07 | 2023-05-30 | 2023-07-31 | 2023-11-10 | 142
0 | FHST1730 | HD-03 - PRE-FAB - OTHER E&I SUPPORTS (CELLAR DECK) | 30 | 2023-03-07 | 2023-04-11 | 2023-07-31 | 2023-09-02 | 125
0 | FHST1740 | HD-03 - PRE-FAB - OTHER E&I SUPPORTS (ESDV DECK) | 30 | 2023-03-14 | 2023-04-18 | 2023-08-07 | 2023-09-09 | 125
0 | FHST1720 | HD-03 - PRE-FAB - OTHER E&I SUPPORTS (UPPER DECK) | 30 | 2023-03-21 | 2023-04-25 | 2023-08-14 | 2023-09-16 | 125
0 | FHST1710 | HD-03 - PRE-FAB - OTHER E&I SUPPORTS (WEATHER DK) | 30 | 2023-03-28 | 2023-05-02 | 2023-08-21 | 2023-09-23 | 125
0 | FHST1750 | HD-03 - PRE-FAB - BALANCE OTHER E&I SUPPORTS (Other than Welded attachments to frame) | 56 | 2023-03-25 | 2023-05-30 | 2023-09-07 | 2023-11-10 | 142
GENERAL |  |  | 180 | 2022-10-28 | 2023-05-26 | 2023-06-16 | 2024-01-11 | 198
0 | FHST1430 | HD-03 - JOB PREPRATION FOR ASSEMBLY & LEVEL- LIFTING | 180 | 2022-10-28 | 2023-05-26 | 2023-06-16 | 2024-01-11 | 198
STRUCTURAL ASSEMBLY & ERECTION |  |  | 258 | 2022-11-18 | 2023-09-15 | 2023-03-02 | 2024-02-21 | 137
ASSEMBLY & WELD CELLAR DECK |  |  | 93 | 2022-11-25 | 2023-03-14 | 2023-03-02 | 2023-06-17 | 83
0 | FHST2040 | HD-03 - FIT-UP & TACK WELD - (CELLAR DECK) MAIN FRAME - GIRDERS | 21 | 2022-11-25 | 2022-12-20 | 2023-03-02 | 2023-03-25 | 83
0 | FHST2060 | HD-03 - FIT-UP & TACK WELD - (CELLAR DECK) MAIN FRAME - NODES | 21 | 2022-11-25 | 2022-12-20 | 2023-03-02 | 2023-03-25 | 83
0 | FHST2030 | HD-03 - FIT-UP & TACK WELD - (CELLAR DECK) SECONDARY STEEL | 21 | 2022-12-13 | 2023-01-06 | 2023-03-20 | 2023-04-12 | 83
0 | FHST2020 | HD-03 - COMPLETE WELDING - (CELLAR DECK) | 24 | 2022-12-27 | 2023-01-24 | 2023-04-03 | 2023-04-29 | 83
0 | FHST2010 | HD-03 - ERECT & WELD - (CELLAR DECK) FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-01-24 | 2023-02-14 | 2023-05-01 | 2023-05-20 | 83
0 | FHST2050 | HD-03 - ERECT & WELD - DECK LEGS AND BRACES (CELLAR DECK) | 18 | 2023-01-24 | 2023-02-14 | 2023-05-01 | 2023-05-20 | 83
0 | FHST2000 | HD-03 - PREPARATION - (CELLAR DECK) ERECTION / LIFT | 3 | 2023-03-10 | 2023-03-14 | 2023-06-15 | 2023-06-17 | 83
ASSEMBLY & WELD ESDV DECK |  |  | 84 | 2022-12-06 | 2023-03-14 | 2023-03-06 | 2023-06-10 | 77
0 | FHST2110 | HD-03 - FIT-UP & TACK WELD - (ESDV DECK) MAIN FRAME - GIRDERS | 18 | 2022-12-06 | 2022-12-27 | 2023-03-06 | 2023-03-25 | 77
0 | FHST2120 | HD-03 - FIT-UP & TACK WELD - (ESDV DECK) MAIN FRAME - NODES | 18 | 2022-12-06 | 2022-12-27 | 2023-03-06 | 2023-03-25 | 77
0 | FHST2100 | HD-03 - FIT-UP & TACK WELD - (ESDV DECK) SECONDARY FRAME | 18 | 2022-12-20 | 2023-01-10 | 2023-03-20 | 2023-04-08 | 77
0 | FHST2090 | HD-03 - COMPLETE WELDING - (ESDV DECK) | 15 | 2023-01-10 | 2023-01-27 | 2023-04-10 | 2023-04-26 | 77
0 | FHST2080 | HD-03 - ERECT & WELD - (ESDV DECK) FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-01-24 | 2023-02-14 | 2023-04-24 | 2023-05-13 | 77
0 | FHST2070 | HD-03 - PREPARATION - (ESDV DECK) ERECTION / LIFT | 3 | 2023-03-10 | 2023-03-14 | 2023-06-08 | 2023-06-10 | 77
ASSEMBLY & WELD UPPER DECK DECK |  |  | 93 | 2022-12-01 | 2023-03-20 | 2023-04-15 | 2023-08-01 | 116
0 | FHST2170 | HD-03 - FIT-UP & TACK WELD - (UPPER DECK) MAIN FRAME - GIRDERS | 21 | 2022-12-01 | 2022-12-26 | 2023-04-15 | 2023-05-09 | 116
0 | FHST2190 | HD-03 - FIT-UP & TACK WELD - (UPPER DECK) MAIN FRAME - NODES | 21 | 2022-12-01 | 2022-12-26 | 2023-04-15 | 2023-05-09 | 116
0 | FHST2160 | HD-03 - FIT-UP & TACK WELD - (UPPER DECK) SECONDARY FRAME | 21 | 2022-12-19 | 2023-01-12 | 2023-05-03 | 2023-05-26 | 116
0 | FHST2150 | HD-03 - COMPLETE WELDING - (UPPER DECK) | 24 | 2023-01-02 | 2023-01-30 | 2023-05-17 | 2023-06-13 | 116
0 | FHST2140 | HD-03 - ERECT & WELD - (UPPER DECK) FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-01-30 | 2023-02-20 | 2023-06-14 | 2023-07-04 | 116
0 | FHST2180 | HD-03 - ERECT & WELD - DECK LEGS AND BRACES (UPPER DECK) - (CELLAR DECK)) | 18 | 2023-01-30 | 2023-02-20 | 2023-06-14 | 2023-07-04 | 116
0 | FHST2130 | HD-03 - PREPARATION - (UPPER DECK) ERECTION / LIFT | 3 | 2023-03-16 | 2023-03-20 | 2023-07-29 | 2023-08-01 | 116
ASSEMBLY & WELD MAIN DECK |  |  | 60 | 2022-12-27 | 2023-03-07 | 2023-04-22 | 2023-06-30 | 100
0 | FHST2200 | HD-03 - FIT-UP & TACK WELD - (MAIN DECK) MAIN FRAME | 18 | 2022-12-27 | 2023-01-17 | 2023-04-22 | 2023-05-12 | 100
0 | FHST2210 | HD-03 - FIT-UP & TACK WELD - (MAIN DECK) SECONDARY FRAME | 15 | 2023-01-10 | 2023-01-27 | 2023-05-06 | 2023-05-23 | 100
0 | FHST2220 | HD-03 - COMPLETE WELDING - (MAIN DECK) | 18 | 2023-01-27 | 2023-02-17 | 2023-05-24 | 2023-06-13 | 100
0 | FHST2230 | HD-03 - ERECT & WELD - (MAIN DECK) FLOOR PLATING | 15 | 2023-02-17 | 2023-03-07 | 2023-06-14 | 2023-06-30 | 100
0 | FHST2240 | HD-03 - ERECT & WELD - DECK LEGS AND BRACES ( (MAIN DECK) & (UPPER DECK) | 15 | 2023-02-17 | 2023-03-07 | 2023-06-14 | 2023-06-30 | 100
ASSEMBLY & WELD WEATHER DECK |  |  | 106 | 2022-12-22 | 2023-04-25 | 2023-05-06 | 2023-08-22 | 103
0 | FHST2290 | HD-03 - FIT-UP & TACK WELD - WEATHER DECK MAIN FRAME | 21 | 2022-12-22 | 2023-01-16 | 2023-05-06 | 2023-05-30 | 116
0 | FHST2300 | HD-03 - FIT-UP & TACK WELD - WEATHER DECK FRAME - NODES | 21 | 2022-12-22 | 2023-01-16 | 2023-05-06 | 2023-05-30 | 116
0 | FHST2280 | HD-03 - FIT-UP & TACK WELD - WEATHER DECK SECONDARY FRAME | 21 | 2023-01-09 | 2023-02-02 | 2023-05-24 | 2023-06-16 | 116
0 | FHST2270 | HD-03 - COMPLETE WELDING - WEATHER DECK | 18 | 2023-01-30 | 2023-02-20 | 2023-06-14 | 2023-07-04 | 116
0 | FHST2260 | HD-03 - ERECT & WELD - WEATHER DECK FLOOR PLATING & MAIN SUPPORTS | 18 | 2023-03-07 | 2023-03-28 | 2023-07-05 | 2023-07-25 | 103
0 | FHST2250 | HD-03 - PREPARATION - WEATHER DECK ERECTION / LIFT | 3 | 2023-04-21 | 2023-04-25 | 2023-08-19 | 2023-08-22 | 103
ERECT - ESDV DECK |  |  | 30 | 2023-03-14 | 2023-04-18 | 2023-06-12 | 2023-10-23 | 162
0 | FHST2320 | HD-03 - LIFT,INSTALL & WELD - (ESDV DECK) | 6 | 2023-03-14 | 2023-03-21 | 2023-06-12 | 2023-06-17 | 77
0 | FHST2310 | HD-03 - ERECT & WELD - REMAINING DECK ELEVATIONS / BRACES (B/W (ESDV DECK) & (CELLAR DECK)) | 24 | 2023-03-21 | 2023-04-18 | 2023-09-26 | 2023-10-23 | 162
ERECT - CELLAR DECK |  |  | 6 | 2023-03-21 | 2023-03-28 | 2023-06-19 | 2023-06-24 | 77
0 | FHST2330 | HD-03 - LIFT,INSTALL & WELD - (CELLAR DECK) | 6 | 2023-03-21 | 2023-03-28 | 2023-06-19 | 2023-06-24 | 77
ERECT - MAIN DECK |  |  | 6 | 2023-03-31 | 2023-04-07 | 2023-07-26 | 2023-08-01 | 100
0 | FHST2340 | HD-03 - LIFT INSTALL & WELD - (MAIN DECK) | 6 | 2023-03-31 | 2023-04-07 | 2023-07-26 | 2023-08-01 | 100
ERECT - UPPER DECK |  |  | 15 | 2023-04-07 | 2023-04-25 | 2023-08-02 | 2023-10-23 | 156
0 | FHST2360 | HD-03 - LIFT,INSTALL & WELD - (UPPER DECK) | 6 | 2023-04-07 | 2023-04-14 | 2023-08-02 | 2023-08-08 | 100
0 | FHST2350 | HD-03 - ERECT & WELD - VERTICAL LEGS (B/W (UPPER DECK) & (CELLAR DECK)) | 12 | 2023-04-11 | 2023-04-25 | 2023-10-10 | 2023-10-23 | 156
ERECT WEATHER DECK |  |  | 60 | 2023-03-21 | 2023-05-30 | 2023-08-23 | 2023-11-27 | 156
0 | FHST2380 | HD-03 - LIFT,INSTALL & WELD - WEATHER DECK | 6 | 2023-04-28 | 2023-05-05 | 2023-08-23 | 2023-08-29 | 100
0 | FHST2370 | HD-03 - ERECT BALANCE BRACES AND COMPLETE BOX UP | 60 | 2023-03-21 | 2023-05-30 | 2023-09-19 | 2023-11-27 | 156
ERECT- HANDRAILS, LADDERS |  |  | 169 | 2023-01-03 | 2023-07-19 | 2023-04-27 | 2024-02-21 | 187
0 | FHST2470 | HD-03 - WELD - (ESDV DECK) HANDRAIL SOCKETS | 15 | 2023-01-03 | 2023-01-20 | 2023-04-27 | 2023-05-13 | 98
0 | FHST2460 | HD-03 - WELD - (CELLAR DECK) HANDRAIL SOCKETS | 15 | 2023-01-06 | 2023-01-24 | 2023-05-04 | 2023-05-20 | 101
0 | FHST2450 | HD-03 - WELD - (UPPER DECK) HANDRAIL SOCKETS | 15 | 2023-01-12 | 2023-01-30 | 2023-06-17 | 2023-07-04 | 134
0 | FHST2440 | HD-03 - WELD - WEATHER HANDRAILS SOCKETS | 15 | 2023-02-02 | 2023-02-20 | 2023-07-08 | 2023-07-25 | 134
0 | FHST2420 | HD-03 - ERECT - (ESDV DECK) HANDRAILS | 30 | 2023-04-07 | 2023-05-12 | 2023-10-05 | 2023-11-08 | 155
0 | FHST2410 | HD-03 - ERECT - (CELLAR DECK) HANDRAILS | 30 | 2023-04-14 | 2023-05-19 | 2023-10-25 | 2023-11-28 | 166
0 | FHST2400 | HD-03 - ERECT - (UPPER DECK) HANDRAILS | 30 | 2023-05-02 | 2023-06-06 | 2023-12-21 | 2024-01-24 | 200
0 | FHST2390 | HD-03 - ERECT - WEATHER DECK HANDRAILS | 30 | 2023-05-06 | 2023-06-10 | 2024-01-18 | 2024-02-21 | 220
0 | FHST2430 | HD-03 - ERECT & WELD - LADDERS & CAGES | 54 | 2023-05-17 | 2023-07-19 | 2023-12-07 | 2024-02-07 | 175
ERECT- GRATINGS |  |  | 87 | 2023-03-28 | 2023-07-07 | 2023-08-23 | 2023-12-11 | 135
0 | FHST2540 | HD-03 - TAILORING OF GRATINGS - (ESDV DECK) | 21 | 2023-03-28 | 2023-04-21 | 2023-08-23 | 2023-09-15 | 127
0 | FHST2500 | HD-03 - TAILORING OF GRATINGS - (CELLAR DECK) | 21 | 2023-04-11 | 2023-05-05 | 2023-09-06 | 2023-09-29 | 127
0 | FHST2520 | HD-03 - TAILORING OF GRATINGS - (UPPER DECK) | 21 | 2023-04-18 | 2023-05-12 | 2023-09-13 | 2023-10-06 | 127
0 | FHST2480 | HD-03 - TAILORING OF GRATINGS - WEATHER DECK | 21 | 2023-04-25 | 2023-05-19 | 2023-09-20 | 2023-10-13 | 127
0 | FHST2550 | HD-03 - INSTALL - GRATINGS (ESDV DECK) | 21 | 2023-05-12 | 2023-06-06 | 2023-10-17 | 2023-11-09 | 135
0 | FHST2530 | HD-03 - INSTALL - GRATINGS (UPPER DECK) | 30 | 2023-05-19 | 2023-06-23 | 2023-11-07 | 2023-12-11 | 147
0 | FHST2490 | HD-03 - INSTALL - GRATINGS WEATHER DECK | 30 | 2023-06-02 | 2023-07-07 | 2023-10-28 | 2023-12-01 | 127
0 | FHST2510 | HD-03 - INSTALL - GRATINGS (CELLAR DECK) | 27 | 2023-06-06 | 2023-07-07 | 2023-11-10 | 2023-12-11 | 135
ERECT STAIRWAYS/STAIR TOWER |  |  | 60 | 2023-04-27 | 2023-07-06 | 2023-10-24 | 2024-02-05 | 184
0 | FHST2570 | HD-03 - ERECT & WELD - STAIRWAYS/STAIR TOWER (NOTH SIDE) | 30 | 2023-05-11 | 2023-06-15 | 2023-10-24 | 2023-11-27 | 142
0 | FHST2580 | HD-03 - ERECT & WELD - STAIRWAYS/STAIR TOWER (SOUTH SIDE) | 30 | 2023-05-25 | 2023-06-29 | 2024-01-02 | 2024-02-05 | 190
0 | FHST2560 | HD-03 - ERECT & WELD - OTHER BALANCE STAIRWAYS | 60 | 2023-04-27 | 2023-07-06 | 2023-11-28 | 2024-02-05 | 184
ERECT PIPE SUPPORTS |  |  | 91 | 2023-02-03 | 2023-05-20 | 2023-06-07 | 2023-11-20 | 158
0 | FHST2620 | HD-03 - INSTALL & WELD - PIPE SUPPORTS (ESDV DECK) (Welded attachments to frame) | 12 | 2023-02-03 | 2023-02-17 | 2023-08-10 | 2023-08-23 | 161
0 | FHST2610 | HD-03 - INSTALL & WELD - PIPE SUPPORTS (CELLAR DECK) (Welded attachments to frame) | 15 | 2023-02-07 | 2023-02-24 | 2023-08-07 | 2023-08-23 | 155
0 | FHST2600 | HD-03 - INSTALL & WELD - PIPE SUPPORTS (UPPER DECK) (Welded attachments to frame) | 24 | 2023-02-14 | 2023-03-14 | 2023-10-24 | 2023-11-20 | 216
0 | FHST2590 | HD-03 - INSTALL & WELD - PIPE SUPPORTS (WEATHER DECK) (Welded attachments to frame) | 24 | 2023-02-17 | 2023-03-17 | 2023-07-31 | 2023-08-26 | 140
0 | FHST2630 | HD-03 - INSTALL & WELD - BALANCE PIPE SUPPORTS (Other than Welded attachments to frame) | 70 | 2023-02-28 | 2023-05-20 | 2023-06-07 | 2023-08-26 | 85
ERECT EQPT SUOPPORTS |  |  | 112 | 2023-02-14 | 2023-06-24 | 2023-06-30 | 2023-09-07 | 65
0 | FHST2670 | HD-03 - INSTALL & WELD - EQUIPMENT SUPPORTS (CELLAR DECK) (Welded attachments to frame) | 18 | 2023-02-14 | 2023-03-07 | 2023-07-14 | 2023-08-03 | 129
0 | FHST2660 | HD-03 - INSTALL & WELD - EQUIPMENT SUPPORTS (UPPER DECK) (Welded attachments to frame) | 18 | 2023-02-28 | 2023-03-21 | 2023-07-14 | 2023-08-03 | 117
0 | FHST2680 | HD-03 - INSTALL & WELD - EQUIPMENT SUPPORTS (ESDV DECK) (Welded attachments to frame) | 18 | 2023-02-28 | 2023-03-21 | 2023-07-24 | 2023-08-12 | 125
0 | FHST2650 | IHD-03 - NSTALL & WELD - EQUIPMENT SUPPORTS (WEATHER DK) (Welded attachments to frame) | 18 | 2023-03-07 | 2023-03-28 | 2023-07-05 | 2023-07-25 | 103
0 | FHST2640 | HD-03 - INSTALL & WELD - VENT SUPPORT STRUCTURE | 21 | 2023-05-09 | 2023-06-02 | 2023-08-15 | 2023-09-07 | 84
0 | FHST2690 | HD-03 - INSTALL & WELD - BALANCE EQUIPMENT SUPPORTS (Other than Welded attachments to frame) | 60 | 2023-04-15 | 2023-06-24 | 2023-06-30 | 2023-09-07 | 65
ERECT CABLE TRAYS SUPPORTS |  |  | 98 | 2023-02-28 | 2023-06-22 | 2023-09-23 | 2023-12-01 | 140
0 | FHST2730 | HD-03 - INSTALL & WELD - CABLE TRAY SUPPORTS (ESDV DECK) (Welded attachments to frame) | 15 | 2023-02-28 | 2023-03-17 | 2023-10-04 | 2023-10-20 | 187
0 | FHST2720 | HD-03 - INSTALL & WELD - CABLE TRAY SUPPORTS (CELLAR DECK) (Welded attachments to frame) | 15 | 2023-03-07 | 2023-03-24 | 2023-11-04 | 2023-11-21 | 208
0 | FHST2700 | HD-03 - INSTALL & WELD - CABLE TRAY SUPPORTS (UPPER DECK) (Welded attachments to frame) | 21 | 2023-03-14 | 2023-04-07 | 2023-10-28 | 2023-11-21 | 196
0 | FHST2710 | HD-03 - INSTALL & WELD - CABLE TRAY SUPPORTS (WEATHER DK) (Welded attachments to frame) | 15 | 2023-03-28 | 2023-04-14 | 2023-11-04 | 2023-11-21 | 190
0 | FHST2750 | HD-03 - INSTALL & WELD - SECONDARY CABLE TRAY SUPPORTS | 60 | 2023-04-04 | 2023-06-13 | 2023-09-23 | 2023-12-01 | 148
0 | FHST2740 | HD-03 - INSTALL & WELD - BALANCE CABLE TRAY SUPPORTS (Other than Welded attachments to frame) | 60 | 2023-04-13 | 2023-06-22 | 2023-09-23 | 2023-12-01 | 140
ERECT OTHER E&I SUPPORTS |  |  | 51 | 2023-04-25 | 2023-06-23 | 2023-09-25 | 2023-12-05 | 142
0 | FHST2770 | HD-03 - INSTALL & WELD - OTHER E&I SUPPORTS (CELLAR DECK) | 15 | 2023-04-25 | 2023-05-12 | 2023-10-05 | 2023-10-21 | 140
0 | FHST2790 | HD-03 - INSTALL & WELD - OTHER E&I SUPPORTS (ESDV DECK) | 15 | 2023-05-02 | 2023-05-19 | 2023-10-04 | 2023-10-20 | 133
0 | FHST2760 | HD-03 - INSTALL & WELD - OTHER E&I SUPPORTS (WEATHER DK) | 24 | 2023-05-02 | 2023-05-30 | 2023-09-25 | 2023-10-21 | 125
0 | FHST2780 | HD-03 - INSTALL & WELD - OTHER E&I SUPPORTS (UPPER DECK) | 21 | 2023-05-09 | 2023-06-02 | 2023-10-18 | 2023-11-10 | 139
0 | FHST2800 | HD-03 - INSTALL & WELD - BALANCE E&I SUPPORTS (Other than Welded attachments to frame) | 42 | 2023-05-05 | 2023-06-23 | 2023-10-18 | 2023-12-05 | 142
FLOOR DRAINS |  |  | 51 | 2022-11-22 | 2023-01-20 | 2023-04-24 | 2023-07-25 | 160
0 | FHST2810 | HD-03 - INSTALL & WELD - FLOOR DRAINS (ESDV DECK) | 18 | 2022-11-22 | 2022-12-13 | 2023-04-24 | 2023-05-13 | 131
0 | FHST2840 | HD-03 - INSTALL & WELD - FLOOR DRAINS (CELLAR DECK) | 18 | 2022-12-06 | 2022-12-27 | 2023-05-01 | 2023-05-20 | 125
0 | FHST2830 | HD-03 - INSTALL & WELD - FLOOR DRAINS (UPPER DECK) | 18 | 2022-12-16 | 2023-01-06 | 2023-06-14 | 2023-07-04 | 154
0 | FHST2820 | HD-03 - INSTALL & WELD - FLOOR DRAINS (WEATHER DK) | 18 | 2022-12-30 | 2023-01-20 | 2023-07-05 | 2023-07-25 | 160
ERECT OTHER STRUCTURES |  |  | 249 | 2022-11-18 | 2023-09-05 | 2023-04-17 | 2024-02-14 | 140
0 | FHST2930 | HD-03 - INSTALL & WELD - AVAILABLE DECK PENETRATIONS | 60 | 2022-11-18 | 2023-01-27 | 2023-04-17 | 2023-06-24 | 128
0 | FHST2900 | HD-03 - INSTALL & WELD - STABBING GUIDES | 9 | 2023-02-23 | 2023-03-06 | 2023-06-22 | 2023-07-01 | 102
0 | FHST2850 | HD-03 - INSTALL & WELD - DECK PAD EYES | 21 | 2023-03-04 | 2023-03-29 | 2023-07-01 | 2023-07-25 | 102
0 | FHST2870 | HD-03 - INSTALL & WELD - BALANCE DECK PENETRATIONS | 42 | 2023-03-21 | 2023-05-09 | 2023-06-19 | 2023-08-05 | 77
0 | FHST2910 | HD-03 - INSTALL & WELD - FLARE BOOM | 21 | 2023-05-12 | 2023-06-06 | 2023-12-29 | 2024-01-22 | 198
0 | FHST2890 | HD-03 - INSTALL & WELD - MONORAIL FRAMES | 60 | 2023-05-05 | 2023-07-14 | 2023-10-17 | 2023-12-25 | 141
0 | FHST2860 | HD-03 - INSTALL & WELD - PLATFORM IDENTIFICATION PANELS | 30 | 2023-06-10 | 2023-07-15 | 2024-01-11 | 2024-02-14 | 184
0 | FHST2880 | HD-03 - INSTALL & WELD - DECK HATCHES | 60 | 2023-06-02 | 2023-08-11 | 2023-10-28 | 2024-01-05 | 127
0 | FHST2920 | HD-03 - INSTALL & WELD - MISC STRUCTURAL ITEMS | 60 | 2023-06-27 | 2023-09-05 | 2023-11-28 | 2024-02-05 | 132
PUNCH LIST CLEARANCE- STRUCTURAL |  |  | 60 | 2023-07-07 | 2023-09-15 | 2023-12-12 | 2024-02-19 | 135
0 | FHST4000 | HD-03 - STRUCTURAL PUNCHLIST CLEARANCE | 60 | 2023-07-07 | 2023-09-15 | 2023-12-12 | 2024-02-19 | 135
PRESSURE VESSEL (FABRICATION & PAINTING) |  |  | 172 | 2022-11-18 | 2023-06-07 | 2023-02-09 | 2023-09-07 | 80
0 | FHPV1000 | HD-03 - FABRICATE - VENT/DRAIN DRUM | 150 | 2022-11-18 | 2023-05-12 | 2023-02-09 | 2023-08-02 | 71
0 | FHPV1030 | HD-03 - PAINT - VENT/DRAIN DRUM | 15 | 2023-05-20 | 2023-06-07 | 2023-08-22 | 2023-09-07 | 80
JECKET EXTENSION |  |  | 120 | 2023-03-09 | 2023-07-27 | 2023-10-17 | 2024-03-04 | 190
0 | FHPV1010 | HD-03 - FABRICATE JECKET PILES & MISC ITEMS | 90 | 2023-03-09 | 2023-06-22 | 2023-10-17 | 2024-01-29 | 190
0 | FHPV1020 | HD-03 - PAINTING OF JECKET EXTENSION | 30 | 2023-06-22 | 2023-07-27 | 2024-01-30 | 2024-03-04 | 190
PIPING WORKS |  |  | 185 | 2023-02-15 | 2023-09-19 | 2023-04-28 | 2024-02-26 | 138
PIPING PRE-FABRICATION |  |  | 69 | 2023-02-15 | 2023-05-06 | 2023-04-28 | 2023-08-15 | 87
0 | FHPI1010 | HD-03 - FABRICATE - CU-NI PIPING SPOOLS | 30 | 2023-02-22 | 2023-03-29 | 2023-05-26 | 2023-06-29 | 80
0 | FHPI1030 | HD-03 - FABRICATE - CS/ LTCS/ CLADDED PIPING SPOOLS | 56 | 2023-02-15 | 2023-04-21 | 2023-04-28 | 2023-07-01 | 62
0 | FHPI1020 | HD-03 - FABRICATE - SS/DUPLEX PIPING SPOOLS | 30 | 2023-03-29 | 2023-05-03 | 2023-06-16 | 2023-07-20 | 68
0 | FHPI1000 | HD-03 - FABRICATE - INCONEL PIPING SPOOLS | 42 | 2023-03-18 | 2023-05-06 | 2023-06-28 | 2023-08-15 | 87
VALVE LEAK TESTING |  |  | 36 | 2023-03-24 | 2023-05-05 | 2023-07-07 | 2023-08-17 | 90
0 | FHPI1040 | HD-03 - VALVE LEAK TESTING | 36 | 2023-03-24 | 2023-05-05 | 2023-07-07 | 2023-08-17 | 90
PIPING ERECTION/HYDROTESTING/INSULATION |  |  | 120 | 2023-05-02 | 2023-09-19 | 2023-07-03 | 2024-02-26 | 138
PIPING ERECTION |  |  | 75 | 2023-05-02 | 2023-07-28 | 2023-07-03 | 2023-09-23 | 50
0 | FHPI1080 | HD-03 - ERECT - CS/ LTCS/ CLADDED SPOOLS | 60 | 2023-05-02 | 2023-07-11 | 2023-07-03 | 2023-09-09 | 53
0 | FHPI1070 | HD-03 - ERECT - SS/DUPLEX SPOOLS | 35 | 2023-06-07 | 2023-07-18 | 2023-08-08 | 2023-09-16 | 53
0 | FHPI1050 | HD-03 - ERECT - INCONEL SPOOLS | 56 | 2023-05-24 | 2023-07-28 | 2023-07-19 | 2023-09-21 | 48
0 | FHPI1060 | HD-03 - ERECT - CU-NI SPOOLS | 35 | 2023-06-17 | 2023-07-28 | 2023-08-15 | 2023-09-23 | 50
HYDROTESTING & REINSTATEMENT |  |  | 81 | 2023-06-16 | 2023-09-19 | 2023-08-28 | 2024-02-26 | 138
HYDROTESTING |  |  | 48 | 2023-06-16 | 2023-08-11 | 2023-08-28 | 2023-10-05 | 48
0 | FHPI1110 | HD-03 - HYDROTESTING AND RE-INSTATEMENT - OIL PRODUCTION SYSTEM | 21 | 2023-06-16 | 2023-07-11 | 2023-08-28 | 2023-09-20 | 62
0 | FHPI1120 | HD-03 - HYDROTESTING AND RE-INSTATEMENT - WATER INJECTION SYSTEM | 21 | 2023-06-27 | 2023-07-21 | 2023-09-01 | 2023-09-25 | 57
0 | FHPI1090 | HD-03 - HYDROTESTING AND RE-INSTATEMENT - CLOSED DRAIN SYSTEM | 21 | 2023-07-11 | 2023-08-04 | 2023-09-05 | 2023-09-28 | 48
0 | FHPI1100 | HD-03 - HYDROTESTING AND RE-INSTATEMENT - OPEN DRAIN SYSTEM | 21 | 2023-07-14 | 2023-08-08 | 2023-09-08 | 2023-10-02 | 48
0 | FHPI1130 | HD-03 - HYDROTESTING AND RE-INSTATEMENT - VENT SYSTEM | 12 | 2023-07-28 | 2023-08-11 | 2023-09-22 | 2023-10-05 | 48
0 | FHPI1140 | HD-03 - HYDROTESTING AND RE-INSTATEMENT - CORROSION INHABITOR INJECTION SYSTEM | 21 | 2023-07-18 | 2023-08-11 | 2023-09-12 | 2023-10-05 | 48
INSULATION |  |  | 60 | 2023-07-11 | 2023-09-19 | 2023-12-19 | 2024-02-26 | 138
0 | FHPI1150 | HD-03 - PIPING INSULATION WORK | 60 | 2023-07-11 | 2023-09-19 | 2023-12-19 | 2024-02-26 | 138
PIPING SYSTEMS MECHANICAL COMPLETION |  |  | 26 | 2023-08-11 | 2023-09-11 | 2024-01-31 | 2024-02-16 | 137
0 | FHPI1180 | HD-03 - MECHANICAL COMPLETION - CHEMICAL INJECTION SYSTEM | 10 | 2023-08-11 | 2023-08-23 | 2024-02-02 | 2024-02-13 | 150
0 | FHPI1200 | HD-03 - MECHANICAL COMPLETION - WATER INJECTION SYSTEM | 10 | 2023-08-11 | 2023-08-23 | 2024-02-02 | 2024-02-13 | 150
0 | FHPI1190 | HD-03 - MECHANICAL COMPLETION - PRODUCTION SYSTEM | 10 | 2023-08-15 | 2023-08-26 | 2024-02-06 | 2024-02-16 | 150
0 | FHPI1170 | HD-03 - MECHANICAL COMPLETION - CLOSED/OPEN DRAIN SYSTEM | 10 | 2023-08-16 | 2023-08-28 | 2024-01-31 | 2024-02-10 | 144
0 | FHPI1160 | HD-03 - MECHANICAL COMPLETION - VENT SYSTEM | 10 | 2023-08-30 | 2023-09-11 | 2024-01-31 | 2024-02-10 | 132
PUNCHLIST CLEARANCE - PIPING |  |  | 60 | 2023-06-08 | 2023-08-17 | 2023-08-03 | 2023-10-11 | 48
0 | FHPI4000 | HD-03 - PUNCHLIST CLEARANCE - PIPING | 60 | 2023-06-08 | 2023-08-17 | 2023-08-03 | 2023-10-11 | 48
PIPING PWHT |  |  | 127 | 2023-02-20 | 2023-07-18 | 2023-06-03 | 2023-09-28 | 63
0 | FHPI5010 | HD-03 - PWHT - FABRICATED SPOOLS | 70 | 2023-02-20 | 2023-05-12 | 2023-06-03 | 2023-08-23 | 89
0 | FHPI5000 | HD-03 - PWHT - ERECTED SPOOLS | 60 | 2023-05-09 | 2023-07-18 | 2023-07-21 | 2023-09-28 | 63
MECHANICAL EQUIPMENT |  |  | 78 | 2023-05-03 | 2023-08-02 | 2023-08-04 | 2024-01-20 | 148
CELLAR DECK |  |  | 40 | 2023-06-05 | 2023-07-21 | 2023-08-07 | 2023-09-14 | 48
0 | FHME1010 | HD-03 - INSTALL - DRAIN SUMP PUMP | 6 | 2023-06-05 | 2023-06-10 | 2023-08-07 | 2023-08-12 | 54
0 | FHME1000 | HD-03 - INSTALL - VENT DRAIN TANK | 6 | 2023-07-14 | 2023-07-21 | 2023-09-08 | 2023-09-14 | 48
MAIN DECK |  |  | 78 | 2023-05-03 | 2023-08-02 | 2023-08-04 | 2024-01-20 | 148
0 | FHME1030 | HD-03 - INSTALL - PIG LAUNCHER/ RECEIVER (730-L-001) | 12 | 2023-05-03 | 2023-05-17 | 2023-08-04 | 2023-08-17 | 80
0 | FHME1020 | HD-03 - INSTALL - MONORAIL/HOIST | 70 | 2023-05-12 | 2023-08-02 | 2023-11-01 | 2024-01-20 | 148
WEATHER DECK |  |  | 70 | 2023-05-05 | 2023-07-26 | 2023-11-01 | 2024-01-20 | 154
0 | FHME1050 | HD-03 - INSTALL - MONORAIL/HOIST | 70 | 2023-05-05 | 2023-07-26 | 2023-11-01 | 2024-01-20 | 154
ELECTRICAL |  |  | 140 | 2023-04-03 | 2023-09-13 | 2023-10-05 | 2024-03-04 | 149
GENERAL |  |  | 130 | 2023-04-14 | 2023-09-13 | 2023-10-05 | 2024-03-04 | 149
0 | FHEL4010 | HD-03 - MATERIAL INSPECTION & PRESERVATION | 130 | 2023-04-14 | 2023-09-13 | 2023-10-05 | 2024-03-04 | 149
CABLE TRAYS |  |  | 79 | 2023-04-03 | 2023-07-04 | 2023-10-05 | 2023-12-15 | 142
0 | FHEL1010 | HD-03 - INSTALL MAIN CABLE TRAYS - (ESDV DECK) - (Max on ground on Deck) | 6 | 2023-04-03 | 2023-04-08 | 2023-10-05 | 2023-10-11 | 159
0 | FHEL1020 | HD-03 - INSTALL MAIN CABLE TRAYS - (CELLAR DECK) - (Max on ground on Deck) | 9 | 2023-04-03 | 2023-04-12 | 2023-10-21 | 2023-10-31 | 173
0 | FHEL1030 | HD-03 - INSTALL MAIN CABLE TRAYS - (UPPER DECK) - (Max on ground on Deck) | 12 | 2023-04-03 | 2023-04-15 | 2023-10-18 | 2023-10-31 | 170
0 | FHEL1040 | HD-03 - INSTALL MAIN CABLE TRAYS - WEATHER DECK - (Max on ground on Deck) | 15 | 2023-04-21 | 2023-05-09 | 2023-10-11 | 2023-10-27 | 148
0 | FHEL1050 | HD-03 - INSTALL - SECONDARY CABLE TRAYS | 48 | 2023-05-02 | 2023-06-27 | 2023-10-21 | 2023-12-15 | 148
0 | FHEL1000 | HD-03 - INSTALL - BALANCE MAIN CABLE TRAYS | 48 | 2023-05-09 | 2023-07-04 | 2023-10-18 | 2023-12-12 | 139
CABLE PULLING, G&T & TESTING |  |  | 69 | 2023-05-30 | 2023-08-18 | 2023-11-01 | 2024-01-19 | 133
0 | FHEL1080 | HD-03 - PULL - ELECTRICAL CABLES | 48 | 2023-05-30 | 2023-07-25 | 2023-11-01 | 2023-12-26 | 133
0 | FHEL1070 | HD-03 - GLAND & TERMINATE - ELECTRICAL CABLES | 60 | 2023-06-06 | 2023-08-15 | 2023-11-08 | 2024-01-16 | 133
0 | FHEL1060 | HD-03 - IR & CONTINUITY CHECK - ELECTRICAL CABLES | 60 | 2023-06-09 | 2023-08-18 | 2023-11-11 | 2024-01-19 | 133
FITTINGS/JB's & SOCKETS |  |  | 48 | 2023-05-09 | 2023-07-04 | 2023-10-18 | 2023-12-05 | 133
0 | FHEL1110 | HD-03 - INSTALL LIGHT FITTINGS/JBs/SOCKETS | 36 | 2023-05-09 | 2023-06-20 | 2023-10-18 | 2023-11-28 | 139
0 | FHEL1100 | HD-03 - INSTALL - INSTALL EARTHING | 36 | 2023-05-19 | 2023-06-30 | 2023-10-21 | 2023-12-01 | 133
0 | FHEL1090 | HD-03 - INSTALL - SMALL POWER / LIGHTING DB'S | 36 | 2023-05-23 | 2023-07-04 | 2023-10-25 | 2023-12-05 | 133
ELECTRICAL EQUIPMENTS |  |  | 52 | 2023-05-03 | 2023-07-03 | 2023-11-01 | 2023-12-15 | 143
0 | FHEL1170 | HD-03 - INSTALL - TRANSFRMER INSTALLLATION - WEATHER DECK | 6 | 2023-05-09 | 2023-05-16 | 2023-12-09 | 2023-12-15 | 184
0 | FHEL1190 | HD-03 - INSTALL - TUTU BOX- (ESDV DECK) | 12 | 2023-05-05 | 2023-05-19 | 2023-11-27 | 2023-12-09 | 176
0 | FHEL1150 | HD-03 - INSTALL - LV DISTRIBUTION BOARD INSTALLATION - (UPPER DECK) | 18 | 2023-05-03 | 2023-05-24 | 2023-11-01 | 2023-11-21 | 156
0 | FHEL1180 | HD-03 - INSTALL - 415V SWITCHBOARD - (UPPER DECK) | 18 | 2023-05-24 | 2023-06-14 | 2023-11-22 | 2023-12-12 | 156
0 | FHEL1130 | HD-03 - INSTALL - NAVIGATION AID SYSTEM - WEATHER/ (ESDV DECK)/ (UPPER DECK) | 24 | 2023-05-18 | 2023-06-15 | 2023-11-04 | 2023-12-01 | 146
0 | FHEL1140 | HD-03 - INSTALL - AC UPS SYSTEM - (UPPER DECK) | 24 | 2023-06-02 | 2023-06-30 | 2023-11-17 | 2023-12-14 | 144
0 | FHEL1160 | HD-03 - INSTALL - 6.6 Kv RMU INSTALLATION - WEATHER DECK | 18 | 2023-06-12 | 2023-07-03 | 2023-11-25 | 2023-12-15 | 143
ELECTRICAL SYSTEMS MECHANICAL COMPLETION |  |  | 33 | 2023-07-14 | 2023-08-22 | 2023-12-30 | 2024-01-23 | 133
0 | FHEL1200 | HD-03 - MECHANICAL COMPLETION - POWER SYSTEM | 12 | 2023-07-14 | 2023-07-28 | 2023-12-30 | 2024-01-12 | 145
0 | FHEL1210 | HD-03 - MECHANICAL COMPLETION - LIGHTING SYSTEM | 12 | 2023-08-08 | 2023-08-22 | 2024-01-10 | 2024-01-23 | 133
PUNCHLIST CLEARANCE - ELECTRICAL |  |  | 36 | 2023-07-14 | 2023-08-25 | 2023-12-16 | 2024-01-26 | 133
0 | FHEL4000 | HD-03 - PUNCHLIST CLEARANCE - ELECTRICAL | 36 | 2023-07-14 | 2023-08-25 | 2023-12-16 | 2024-01-26 | 133
INSTRUMENTATION/TELECOM |  |  | 135 | 2023-04-14 | 2023-09-19 | 2023-10-23 | 2024-02-12 | 126
CABLE TRAYS & CABLE PULLING |  |  | 84 | 2023-06-09 | 2023-09-15 | 2023-11-29 | 2024-02-07 | 125
0 | FHIN1020 | HD-03 - PULL - INSTRUMENT CABLES | 45 | 2023-06-09 | 2023-08-01 | 2023-11-29 | 2024-01-19 | 148
0 | FHIN1010 | HD-03 - GLAND/TERMINATE - INSTRUMENT CABLES | 48 | 2023-07-18 | 2023-09-12 | 2023-12-11 | 2024-02-03 | 125
0 | FHIN1000 | HD-03 - IR & CONTINUITY CHECK - INSTRUMENT CABLES | 48 | 2023-07-21 | 2023-09-15 | 2023-12-14 | 2024-02-07 | 125
INSTRUMENTS INSTALLATION |  |  | 81 | 2023-05-12 | 2023-08-15 | 2023-11-06 | 2024-01-19 | 136
0 | FHIN1040 | HD-03 - INSTALL - F&G DETECTORS | 30 | 2023-05-12 | 2023-06-16 | 2023-11-06 | 2023-12-09 | 152
0 | FHIN4020 | HD-03 - INSTRUMENT CALIBRATION | 42 | 2023-05-27 | 2023-07-15 | 2023-11-11 | 2023-12-29 | 144
0 | FHIN1050 | HD-03 - INSTALL - FIELD INSTRUMENTS | 42 | 2023-06-27 | 2023-08-15 | 2023-12-02 | 2024-01-19 | 136
PANELS & JB's |  |  | 42 | 2023-05-30 | 2023-07-18 | 2023-10-23 | 2023-12-09 | 125
0 | FHIN1060 | HD-03 - INSTALL - JUNCTION BOXES/ MARSHALING BOXES / SPLITTER BOXES | 42 | 2023-05-30 | 2023-07-18 | 2023-10-23 | 2023-12-09 | 125
INSTRUMENT EQUIPMENTS |  |  | 116 | 2023-04-14 | 2023-08-28 | 2023-11-13 | 2024-02-03 | 138
0 | FHIN4010 | HD-03 - INSTALL TELECOM SYSTEM - (MAIN DECK) | 12 | 2023-04-14 | 2023-04-28 | 2023-11-13 | 2023-11-25 | 182
0 | FHIN4040 | HD-03 - INSTALL IRCD SKID | 6 | 2023-05-19 | 2023-05-26 | 2023-12-04 | 2023-12-09 | 170
0 | FHIN1080 | HD-03 - INSTALL WELLHEAD CONTROL PANEL - (UPPER DECK) | 12 | 2023-06-20 | 2023-07-04 | 2023-11-27 | 2023-12-09 | 137
0 | FHIN1090 | HD-03 - INSTALL HIPPS SYSTEM - (CELLAR DECK) | 12 | 2023-06-28 | 2023-07-12 | 2023-11-27 | 2023-12-09 | 130
0 | FHIN1100 | HD-03 - INSTALL ICSS SYSTEM - (UPPER DECK) | 6 | 2023-07-27 | 2023-08-03 | 2023-12-26 | 2024-01-01 | 130
0 | FHIN1110 | HD-03 - INSTALL FLOW METERS -CELLAR DECK / (UPPER DECK) | 30 | 2023-07-07 | 2023-08-11 | 2024-01-01 | 2024-02-03 | 152
0 | FHIN1070 | HD-03 - INSTALL INSTRUMENT VALVES - CELLAR / (UPPER DECK)/ (ESDV DECK) | 48 | 2023-07-03 | 2023-08-28 | 2023-11-28 | 2024-01-22 | 127
INSTRUMENT TUBING & INCONEL PIPING |  |  | 77 | 2023-06-13 | 2023-09-11 | 2023-11-21 | 2024-02-05 | 127
0 | FHIN4030 | HD-03 - INSTALL - INSTALL INCONEL PIPING | 60 | 2023-06-13 | 2023-08-22 | 2023-11-21 | 2024-01-29 | 138
0 | FHIN1130 | HD-03 - INSTALL - INSTRUMENT TUBING | 60 | 2023-06-26 | 2023-09-04 | 2023-11-21 | 2024-01-29 | 127
0 | FHIN1120 | HD-03 - PRESSURE TEST - INSTRUMENT TUBING | 35 | 2023-08-01 | 2023-09-11 | 2023-12-27 | 2024-02-05 | 127
INSTRUMENT/TELECOM SYSTEMS MECHANICAL COMPLETION |  |  | 33 | 2023-07-21 | 2023-08-29 | 2024-01-13 | 2024-02-03 | 137
0 | FHIN1150 | HD-03 - MECHANICAL COMPLETION - TELECOM SYSTEM | 12 | 2023-07-21 | 2023-08-04 | 2024-01-22 | 2024-02-03 | 158
0 | FHIN1140 | HD-03 - MECHANICAL COMPLETION - CONTROL SYSTEM | 12 | 2023-08-15 | 2023-08-29 | 2024-01-13 | 2024-01-26 | 130
PUNCHLIST CLEARANCE - INSTRUMENT |  |  | 20 | 2023-08-26 | 2023-09-19 | 2024-01-20 | 2024-02-12 | 126
0 | FHIN4000 | HD-03 - PUNCHLIST CLEARANCE - INSTRUMENTATION | 20 | 2023-08-26 | 2023-09-19 | 2024-01-20 | 2024-02-12 | 126
SAFETY |  |  | 52 | 2023-07-19 | 2023-09-18 | 2024-01-06 | 2024-02-12 | 127
0 | FHSA1010 | HD-03 - INSTALLATION OF SAFETY EQUIPMENT | 20 | 2023-07-19 | 2023-08-11 | 2024-01-06 | 2024-01-29 | 147
0 | FHSA1000 | HD-03 - INSTALLATION OF SAFETY SIGN | 12 | 2023-09-04 | 2023-09-18 | 2024-01-30 | 2024-02-12 | 127
PAINTING |  |  | 282 | 2022-11-08 | 2023-10-03 | 2023-03-27 | 2024-03-04 | 132
BLAST/PAINT- MAIN STRUCTURE |  |  | 141 | 2022-11-08 | 2023-04-21 | 2023-03-27 | 2023-08-18 | 103
BLAST/PAINT- CELLAR DECK |  |  | 105 | 2022-11-08 | 2023-03-10 | 2023-03-27 | 2023-06-07 | 77
0 | FHSTPN1000 | HD-03 - BLAST/PAINT - DECK BRACES (BTWN (ESDV DECK) & (CELLAR DECK) | 24 | 2022-11-08 | 2022-12-06 | 2023-03-27 | 2023-04-22 | 119
0 | FHSTPN1010 | HD-03 - BLAST/PAINT - DECK LEGS (BTWN (ESDV DECK), & (CELLAR DECK) | 15 | 2022-12-13 | 2022-12-30 | 2023-04-06 | 2023-04-22 | 98
0 | FHSTPN1020 | HD-03 - BLAST/PAINT - (ESDV DECK) | 21 | 2023-02-14 | 2023-03-10 | 2023-05-15 | 2023-06-07 | 77
BLAST/PAINT- MAIN DECK |  |  | 90 | 2022-11-25 | 2023-03-10 | 2023-04-03 | 2023-06-14 | 83
0 | FHSTPN1030 | HD-03 - BLAST/PAINT - DECK BRACES (BTWN (CELLAR DECK) & (UPPER DECK) | 24 | 2022-11-25 | 2022-12-23 | 2023-04-03 | 2023-04-29 | 110
0 | FHSTPN1040 | HD-03 - BLAST/PAINT - DECK LEGS (BTWN (CELLAR DECK) & (UPPER DECK) | 15 | 2022-12-06 | 2022-12-23 | 2023-04-13 | 2023-04-29 | 110
0 | FHSTPN1050 | HD-03 - BLAST/PAINT - MAIN DECK | 21 | 2023-02-14 | 2023-03-10 | 2023-05-22 | 2023-06-14 | 83
BLAST/PAINT- MEZZANINE DECK |  |  | 83 | 2022-12-09 | 2023-03-16 | 2023-05-17 | 2023-07-28 | 116
0 | FHSTPN1070 | HD-03 - BLAST/PAINT - DECK LEGS (BTWN (UPPER DECK) & WEATHER DK) | 15 | 2022-12-13 | 2022-12-30 | 2023-05-27 | 2023-06-13 | 142
0 | FHSTPN1060 | HD-03 - BLAST/PAINT - DECK BRACES (BTWN (UPPER DECK) & WEATHER DK) | 24 | 2022-12-09 | 2023-01-06 | 2023-05-17 | 2023-06-13 | 136
0 | FHSTPN1080 | HD-03 - BLAST/PAINT - (UPPER DECK) | 21 | 2023-02-20 | 2023-03-16 | 2023-07-05 | 2023-07-28 | 116
BLAST/PAINT- ACCESS PLATFORM |  |  | 21 | 2023-03-07 | 2023-03-31 | 2023-07-01 | 2023-07-25 | 100
0 | FHSTPN1090 | HD-03 - BLAST/PAINT - (MAIN DECK) | 21 | 2023-03-07 | 2023-03-31 | 2023-07-01 | 2023-07-25 | 100
BLAST/PAINT-WEATHE DECK |  |  | 21 | 2023-03-28 | 2023-04-21 | 2023-07-26 | 2023-08-18 | 103
0 | FHSTPN1100 | HD-03 - BLAST/PAINT - WEATHER DECK | 21 | 2023-03-28 | 2023-04-21 | 2023-07-26 | 2023-08-18 | 103
BLAST/PAINT- OTHER STRUCT/ACCESSORIES |  |  | 205 | 2023-02-06 | 2023-10-03 | 2023-05-24 | 2024-03-04 | 132
GALVANIZE/PAINT - HANDRAILS/LADDERS |  |  | 108 | 2023-02-06 | 2023-06-12 | 2023-08-24 | 2024-01-17 | 189
0 | FHSTPN1190 | HD-03 - GALVANIZE - HANDRAILS (ESDV DECK) | 18 | 2023-02-06 | 2023-02-27 | 2023-08-24 | 2023-09-13 | 171
0 | FHSTPN1180 | HD-03 - GALVANIZE - HANDRAILS (CELLAR DECK) | 18 | 2023-02-20 | 2023-03-13 | 2023-09-13 | 2023-10-03 | 176
0 | FHSTPN1150 | HD-03 - PAINT - HANDRAILS (ESDV DECK) | 18 | 2023-02-27 | 2023-03-20 | 2023-09-14 | 2023-10-04 | 171
0 | FHSTPN1170 | HD-03 - GALVANIZE - HANDRAILS (UPPER DECK) | 18 | 2023-03-06 | 2023-03-27 | 2023-11-09 | 2023-11-29 | 213
0 | FHSTPN1140 | HD-03 - PAINT - HANDRAILS (CELLAR DECK) | 18 | 2023-03-13 | 2023-04-03 | 2023-10-04 | 2023-10-24 | 176
0 | FHSTPN1160 | HD-03 - GALVANIZE - HANDRAILS (WEATHER DECK) | 23 | 2023-03-20 | 2023-04-15 | 2023-12-01 | 2023-12-27 | 220
0 | FHSTPN1130 | HD-03 - PAINT - HANDRAILS (UPPER DECK) | 18 | 2023-03-27 | 2023-04-17 | 2023-11-30 | 2023-12-20 | 213
0 | FHSTPN1120 | HD-03 - PAINT - HANDRAILS (WEATHER DECK) | 18 | 2023-04-15 | 2023-05-06 | 2023-12-28 | 2024-01-17 | 220
0 | FHSTPN1110 | HD-03 - BLAST/PAINT - LADDERS & CAGES | 60 | 2023-04-03 | 2023-06-12 | 2023-10-17 | 2023-12-25 | 169
BLAST/PAINT - STAIRWAYS |  |  | 72 | 2023-03-30 | 2023-06-22 | 2023-10-03 | 2024-01-22 | 184
NORTH SIDE |  |  | 36 | 2023-03-30 | 2023-05-11 | 2023-10-03 | 2023-10-23 | 142
0 | FHSTPN1200 | HD-03 - BLAST/PAINT - (ESDV DECK) TO JACKET WALKWAY (NORTH SIDE ) STAIR WAYS | 18 | 2023-03-30 | 2023-04-20 | 2023-10-03 | 2023-10-23 | 160
0 | FHSTPN1210 | HD-03 - BLAST/PAINT - NORTH SIDE STAIR WAYS | 18 | 2023-04-06 | 2023-04-27 | 2023-10-03 | 2023-10-23 | 154
0 | FHSTPN1220 | HD-03 - BLAST/PAINT - (UPPER DECK) TO MAIN DECK (NORTH SIDE) | 18 | 2023-04-13 | 2023-05-04 | 2023-10-03 | 2023-10-23 | 148
0 | FHSTPN1230 | HD-03 - BLAST/PAINT - MAIN DECK TO (UPPER DECK) (NORTH SIDE) | 18 | 2023-04-20 | 2023-05-11 | 2023-10-03 | 2023-10-23 | 142
SOUTH SIDE |  |  | 39 | 2023-04-10 | 2023-05-25 | 2023-12-12 | 2024-01-01 | 190
0 | FHSTPN1240 | HD-03 - BLAST/PAINT - SOUTH SDIE STAIR WAYS | 18 | 2023-04-10 | 2023-05-01 | 2023-12-12 | 2024-01-01 | 211
0 | FHSTPN1250 | HD-03 - BLAST/PAINT - MONKEY LADDER FROM MEZZANINE DECK TO MAIN DECK (SOUTH SIDE) | 18 | 2023-04-24 | 2023-05-15 | 2023-12-12 | 2024-01-01 | 199
0 | FHSTPN1260 | HD-03 - BLAST/PAINT - MONKEY LADDER FROM MAIN DECK TO MEZZANINE DECK (SOUTH SIDE) | 18 | 2023-05-04 | 2023-05-25 | 2023-12-12 | 2024-01-01 | 190
OTHER MISCELLENEOUS |  |  | 42 | 2023-05-04 | 2023-06-22 | 2023-12-05 | 2024-01-22 | 184
0 | FHSTPN1270 | HD-03 - BLAST/PAINT - STAIRWAYS (OTHER MISC.) | 42 | 2023-05-04 | 2023-06-22 | 2023-12-05 | 2024-01-22 | 184
BLAST/PAINT - PIPE SUPPORTS |  |  | 60 | 2023-02-14 | 2023-04-25 | 2023-05-24 | 2023-08-01 | 85
0 | FHSTPN1280 | HD-03 - BLAST/PAINT - BALANCE PIPE SUPPORTS | 60 | 2023-02-14 | 2023-04-25 | 2023-05-24 | 2023-08-01 | 85
BLAST/PAINTING - PIPING |  |  | 63 | 2023-03-08 | 2023-05-20 | 2023-06-19 | 2023-08-22 | 81
0 | FHPIPN1000 | HD-03 - BLAST/PAINT - CU-NI/ INCONEL PIPING SPOOLS | 42 | 2023-03-08 | 2023-04-26 | 2023-07-03 | 2023-08-19 | 100
0 | FHPIPN1020 | HD-03 - BLAST/PAINT - CS/LTCS / CLADDED PIPING SPOOLS | 56 | 2023-03-08 | 2023-05-12 | 2023-06-19 | 2023-08-22 | 88
0 | FHPIPN1010 | HD-03 - BLAST/PAINT - SS PIPING SPOOLS | 30 | 2023-04-15 | 2023-05-20 | 2023-07-04 | 2023-08-07 | 68
BLAST/PAINT - EQUIPMENT SUPPORTS |  |  | 42 | 2023-04-04 | 2023-05-23 | 2023-06-19 | 2023-08-14 | 72
0 | FHSTPN1300 | HD-03 - BLAST/PAINT - VENT SUPPORT STRUCTURE | 24 | 2023-04-11 | 2023-05-09 | 2023-07-18 | 2023-08-14 | 84
0 | FHSTPN1310 | HD-03 - BLAST/PAINT - BALANCE EQUIPMENT SUPPORTS | 42 | 2023-04-04 | 2023-05-23 | 2023-06-19 | 2023-08-05 | 65
BLAST/PAINT - E&I SUPPORTS |  |  | 56 | 2023-03-28 | 2023-06-01 | 2023-09-07 | 2023-11-10 | 140
0 | FHSTPN1330 | HD-03 - BLAST/PAINT - SECONDARY CABLE TRAY SUPPORTS | 42 | 2023-03-28 | 2023-05-16 | 2023-09-16 | 2023-11-03 | 148
0 | FHSTPN1320 | HD-03 - BLAST/PAINT - BALANCE MAIN CABLE TRAY SUPPORTS | 56 | 2023-03-28 | 2023-06-01 | 2023-09-07 | 2023-11-10 | 140
BLAST/PAINT - OTHER SUPPORTS |  |  | 75 | 2023-03-21 | 2023-06-16 | 2023-08-30 | 2023-11-28 | 142
0 | FHSTPN1360 | HD-03 - BLAST/PAINT - OTHER E&I SUPPORTS (CELLAR DECK) | 30 | 2023-03-21 | 2023-04-25 | 2023-08-31 | 2023-10-04 | 140
0 | FHSTPN1370 | HD-03 - BLAST/PAINT - OTHER E&I SUPPORTS ((ESDV DECK) | 30 | 2023-03-28 | 2023-05-02 | 2023-08-30 | 2023-10-03 | 133
0 | FHSTPN1350 | HD-03 - BLAST/PAINT - OTHER E&I SUPPORTS (UPPER DECK) | 30 | 2023-04-04 | 2023-05-09 | 2023-09-13 | 2023-10-17 | 139
0 | FHSTPN1340 | HD-03 - BLAST/PAINT - OTHER E&I SUPPORTS (WEATHER MDK) | 30 | 2023-04-11 | 2023-05-16 | 2023-09-04 | 2023-10-07 | 125
0 | FHSTPN1380 | HD-03 - BLAST/PAINT - BALANCE OTHER E&I SUPPORTS | 56 | 2023-04-12 | 2023-06-16 | 2023-09-25 | 2023-11-28 | 142
BLAST/PAINT - OTHER STRUCTURES |  |  | 166 | 2023-02-09 | 2023-08-22 | 2023-06-08 | 2024-01-22 | 132
0 | FHSTPN1440 | HD-03 - BLAST/PAINT - STABBING GUIDES | 12 | 2023-02-09 | 2023-02-23 | 2023-06-08 | 2023-06-21 | 102
0 | FHSTPN1390 | HD-03 - BLAST/PAINT - DECK PAD EYES | 24 | 2023-02-15 | 2023-03-15 | 2023-06-14 | 2023-07-11 | 102
0 | FHSTPN1430 | HD-03 - BLAST/PAINT - MONORAILS FRAME | 60 | 2023-02-14 | 2023-04-25 | 2023-09-19 | 2023-11-27 | 186
0 | FHSTPN1420 | HD-03 - BLAST/PAINT - DECK HATCHES | 30 | 2023-03-29 | 2023-05-03 | 2023-11-11 | 2023-12-15 | 195
0 | FHSTPN1450 | HD-03 - BLAST/PAINT - FLARE BOOM | 18 | 2023-04-21 | 2023-05-12 | 2023-12-08 | 2023-12-28 | 198
0 | FHSTPN1400 | HD-03 - BLAST/PAINT - GRATINGS | 42 | 2023-04-21 | 2023-06-09 | 2023-09-16 | 2023-11-03 | 127
0 | FHSTPN1410 | HD-03 - BLAST/PAINT - PLATFORM IDENTIFICATION PANELS | 18 | 2023-05-20 | 2023-06-10 | 2023-12-21 | 2024-01-10 | 184
0 | FHSTPN1460 | HD-03 - BLAST/PAINT - MISCELLANEOUS STRUCTRUAL ITEMS | 60 | 2023-06-13 | 2023-08-22 | 2023-11-14 | 2024-01-22 | 132
FINAL TOUCH-UP PAINTING |  |  | 100 | 2023-06-08 | 2023-10-03 | 2023-11-09 | 2024-03-04 | 132
0 | FHSTPN1470 | HD-03 - FIRE PROOFING ON DECK STRUCTURE | 60 | 2023-06-26 | 2023-09-04 | 2023-11-21 | 2024-01-29 | 127
0 | FHSTPN1480 | HD-03 - FINAL PAINT & TOUCH-UP PAINTING | 100 | 2023-06-08 | 2023-10-03 | 2023-11-09 | 2024-03-04 | 132
MISCELLANEOUS WORKS |  |  | 42 | 2023-08-01 | 2023-09-19 | 2024-01-02 | 2024-02-19 | 132
0 | FHST5000 | HD-03 - MISCELLANEOUS WORKS | 42 | 2023-08-01 | 2023-09-19 | 2024-01-02 | 2024-02-19 | 132
COMMISIONING |  |  | 55 | 2023-08-08 | 2023-10-11 | 2024-01-10 | 2024-03-04 | 125
0 | FHCG1005 | HD-03 - 415V AUXILIARY DB | 3 | 2023-08-10 | 2023-08-14 | 2024-01-20 | 2024-01-23 | 140
0 | FHCG1020 | HD-03 - 24V DC UPS BATTERY CHARGER & BATTERY | 6 | 2023-08-11 | 2023-08-18 | 2024-01-22 | 2024-01-27 | 140
0 | FHCG1000 | HD-03 - 415 V SWITCHGEAR (2 I/C +15 FDRS.+ 3 SPR.) | 15 | 2023-08-08 | 2023-08-25 | 2024-01-10 | 2024-01-26 | 133
0 | FHCG1030 | HD-03 - ECMS SYSTEM | 14 | 2023-08-17 | 2023-09-02 | 2024-01-27 | 2024-02-12 | 140
0 | FHCG1070 | HD-03 - MOV POWER DB | 2 | 2023-09-09 | 2023-09-12 | 2024-02-08 | 2024-02-09 | 130
0 | FHCG1060 | HD-03 - TELECOM & LAN SYSTEM - 3 NOS | 5 | 2023-09-08 | 2023-09-14 | 2024-02-05 | 2024-02-09 | 128
0 | FHCG1080 | HD-03 - NAVIGATIONAL AID SYSTEM | 3 | 2023-09-12 | 2023-09-15 | 2024-02-10 | 2024-02-13 | 130
0 | FHCG1090 | HD-03 - CCTV SYSTEM - 3 NOS | 3 | 2023-09-14 | 2023-09-18 | 2024-02-10 | 2024-02-13 | 128
0 | FHCG1040 | HD-03 - RTU SYSTEM (OTP & LOOP CHECKING) | 14 | 2023-09-04 | 2023-09-20 | 2024-01-27 | 2024-02-12 | 125
0 | FHCG1110 | HD-03 - BIRD DETERRENT SYSTEM- | 2 | 2023-09-18 | 2023-09-20 | 2024-02-14 | 2024-02-15 | 128
0 | FHCG1120 | HD-03 - UHF RADIO - 3 NOS | 2 | 2023-09-18 | 2023-09-20 | 2024-02-14 | 2024-02-15 | 128
0 | FHCG1170 | HD-03 - CLOSED DRAIN | 3 | 2023-09-16 | 2023-09-20 | 2024-02-12 | 2024-02-14 | 127
0 | FHCG1100 | HD-03 - WELL HEAD CONTROL PANEL (OTP & LOOP CHECKING) | 6 | 2023-09-14 | 2023-09-21 | 2024-02-09 | 2024-02-15 | 127
0 | FHCG1130 | HD-03 - 6.6 KV RMU SYSTEM | 6 | 2023-09-14 | 2023-09-21 | 2024-02-12 | 2024-02-17 | 129
0 | FHCG1180 | HD-03 - COMM -CHEMICAL INJECTION | 4 | 2023-09-19 | 2023-09-23 | 2024-02-14 | 2024-02-17 | 127
0 | FHCG1050 | HD-03 - ESD SYSTEM (OTP & LOOP CHECKING) | 14 | 2023-09-08 | 2023-09-25 | 2024-02-01 | 2024-02-16 | 125
0 | FHCG1150 | HD-03 - HIPPS (OTP & LOOP CHECKING | 5 | 2023-09-22 | 2023-09-28 | 2024-02-15 | 2024-02-20 | 125
0 | FHCG1160 | HD-03 - 6.6KV / 433V POWER TRANSFORMER | 4 | 2023-09-23 | 2023-09-28 | 2024-02-16 | 2024-02-20 | 125
0 | FHCG1200 | HD-03 - WELL SLOT | 6 | 2023-09-21 | 2023-09-28 | 2024-02-16 | 2024-02-22 | 127
0 | FHCG1220 | HD-03 - MPFM - COMMUNICATION ESTABLISHMENT | 3 | 2023-09-25 | 2023-09-28 | 2024-02-19 | 2024-02-21 | 126
0 | FHCG1230 | HD-03 - PRODUCTION MANIFOLD | 3 | 2023-09-27 | 2023-09-30 | 2024-02-22 | 2024-02-24 | 127
0 | FHCG1190 | HD-03 - LIGHTING SYSTEM | 5 | 2023-09-28 | 2023-10-04 | 2024-02-21 | 2024-02-26 | 125
0 | FHCG1240 | HD-03 - COMM -PIG LAUNCHER/RECEIVER | 3 | 2023-09-30 | 2023-10-04 | 2024-02-26 | 2024-02-28 | 127
0 | FHCG1140 | HD-03 - FIRE &GAS SYSTEM (OTP & LOOP CHECKING) | 11 | 2023-09-22 | 2023-10-05 | 2024-02-15 | 2024-02-27 | 125
0 | FHCG1250 | HD-03 - VENT & DRAIN SYSTEM OTP | 4 | 2023-10-02 | 2023-10-06 | 2024-02-27 | 2024-03-01 | 127
0 | FHCG1260 | HD-03 - FIRE FIGHTING & SAFETY EQUIPMENT | 3 | 2023-10-05 | 2023-10-09 | 2024-02-28 | 2024-03-01 | 125
0 | FHCG1210 | HD-03 - LEAK TEST | 14 | 2023-09-25 | 2023-10-11 | 2024-02-17 | 2024-03-04 | 125
READY FOR LOADOUT |  |  | 20 | 2023-09-18 | 2023-10-11 | 2024-02-13 | 2024-03-04 | 125
0 | FHLO1010 | HD-03 - FINAL DECK WEIGHING | 6 | 2023-09-18 | 2023-09-25 | 2024-02-13 | 2024-02-19 | 127
0 | FHLO1000 | HD-03 - READY FOR LOADOUT - WHP HD-03 TOPSIDE | 0 |  | 2023-10-11 |  | 2024-03-04 | 125
0 | FHLO2010 | HD-03 COMPANY WALK THROUGH AND PUNCH LIST CLEARANCE | 12 | 2023-09-27 | 2023-10-11 | 2024-02-20 | 2024-03-04 | 125
FABRICATION FOR MODIFICATION IGD-E TOWER (EXISTING) |  |  | 233 | 2022-12-21 | 2023-09-19 | 2023-02-15 | 2023-12-29 | 88
STRUCTURAL |  |  | 214 | 2023-01-12 | 2023-09-19 | 2023-06-06 | 2023-12-29 | 88
STRUCTURAL PRE-FABRICATION |  |  | 214 | 2023-01-12 | 2023-09-19 | 2023-06-06 | 2023-12-29 | 88
PRE-FAB PLATES |  |  | 15 | 2023-01-12 | 2023-01-30 | 2023-06-14 | 2023-06-30 | 131
0 | FIST1000 | IGD-E - CUT & PROFILE - PLATES | 15 | 2023-01-12 | 2023-01-30 | 2023-06-14 | 2023-06-30 | 131
PRE-FAB SECTIONS |  |  | 21 | 2023-01-30 | 2023-02-23 | 2023-07-01 | 2023-07-25 | 131
0 | FIST1010 | IGD-E - CUT & PROFILE - SECTIONS | 21 | 2023-01-30 | 2023-02-23 | 2023-07-01 | 2023-07-25 | 131
WORKSHOP SUB-ASSEMBLE - HANDRAILS & LADDERS |  |  | 135 | 2023-04-14 | 2023-09-19 | 2023-07-26 | 2023-12-29 | 88
0 | FIST1030 | IGD-E - SUB ASSEMBLE - HANDRAILS | 36 | 2023-04-14 | 2023-05-26 | 2023-07-26 | 2023-09-05 | 88
0 | FIST5010 | IGD-E - FABRICATE ACCESS PLATFORM | 36 | 2023-05-26 | 2023-07-07 | 2023-09-06 | 2023-10-17 | 88
0 | FIST5020 | IGD-E - FABRICATE MONORAILS | 70 | 2023-05-26 | 2023-08-16 | 2023-09-07 | 2023-11-27 | 89
0 | FIST5030 | IGD-E - FABRICATE GRATING | 24 | 2023-08-09 | 2023-09-06 | 2023-11-21 | 2023-12-18 | 89
0 | FIST5040 | IGD-E - FABRICATE FLARE BOOM | 63 | 2023-07-07 | 2023-09-19 | 2023-10-18 | 2023-12-29 | 88
PRE-FAB - PIPE SUPPORTS |  |  | 42 | 2023-02-24 | 2023-04-14 | 2023-06-06 | 2023-07-25 | 88
0 | FIST1040 | IGD-E - PRE FABRICATE PIPE SUPPORTS | 42 | 2023-02-24 | 2023-04-14 | 2023-06-06 | 2023-07-25 | 88
PRE-FAB - EQUIPMENT SUPPORTS |  |  | 24 | 2023-03-17 | 2023-04-14 | 2023-06-28 | 2023-07-25 | 88
0 | FIST1050 | IGD-E - PRE FABRICATE EQUIPMENT SUPPORTS | 24 | 2023-03-17 | 2023-04-14 | 2023-06-28 | 2023-07-25 | 88
PRE-FAB - E & I CABLE TRAY SUPPORTS |  |  | 56 | 2023-04-06 | 2023-06-10 | 2023-09-21 | 2023-11-24 | 144
0 | FIST1060 | IGD-E - PRE FABRICATE CABLE TRAY SUPPORTS | 56 | 2023-04-06 | 2023-06-10 | 2023-09-21 | 2023-11-24 | 144
PRE-FAB - OTHER E&I SUPPORTS |  |  | 60 | 2023-04-06 | 2023-06-15 | 2023-10-07 | 2023-12-15 | 158
0 | FIST1070 | IGD-E - PRE-FAB - OTHER E&I SUPPORTS | 60 | 2023-04-06 | 2023-06-15 | 2023-10-07 | 2023-12-15 | 158
PRESSURE VESSEL (FABRICATION & PAINTING) |  |  | 182 | 2022-12-21 | 2023-07-21 | 2023-02-15 | 2023-09-14 | 48
0 | FIPV1000 | IGD-E - FABRICATE - VENT/DRAIN DRUM | 165 | 2022-12-21 | 2023-07-01 | 2023-02-15 | 2023-08-25 | 48
0 | FIPV1010 | IGD-E - PAINT - VENT/DRAIN DRUM | 17 | 2023-07-01 | 2023-07-21 | 2023-08-26 | 2023-09-14 | 48
PIPING WORKS |  |  | 56 | 2023-03-30 | 2023-06-03 | 2023-10-05 | 2023-12-08 | 162
PIPING PRE-FABRICATION |  |  | 56 | 2023-03-30 | 2023-06-03 | 2023-10-05 | 2023-12-08 | 162
0 | FIPI1000 | IGD-E - FABRICATE - PIPING SPOOLS | 56 | 2023-03-30 | 2023-06-03 | 2023-10-05 | 2023-12-08 | 162
PAINTING |  |  | 116 | 2023-04-14 | 2023-08-28 | 2023-07-25 | 2023-12-29 | 107
BLAST/PAINT- MAIN STRUCTURE |  |  | 66 | 2023-05-26 | 2023-08-11 | 2023-11-18 | 2023-12-29 | 121
BLAST/PAINT- CELLAR DECK |  |  | 66 | 2023-05-26 | 2023-08-11 | 2023-11-18 | 2023-12-29 | 121
0 | FISTPN1010 | IGD-E - GALVANIZE - HANDRAILS | 18 | 2023-05-26 | 2023-06-16 | 2023-11-18 | 2023-12-08 | 151
0 | FISTPN1000 | IGD-E - PAINT - HANDRAILS | 18 | 2023-06-16 | 2023-07-07 | 2023-12-09 | 2023-12-29 | 151
0 | FISTPN1020 | IGD-E - BLAST/PAINT - FABRICATED STRUCTURAL ITEMS | 24 | 2023-07-14 | 2023-08-11 | 2023-12-02 | 2023-12-29 | 121
BLAST/PAINT- OTHER STRUCT/ACCESSORIES |  |  | 116 | 2023-04-14 | 2023-08-28 | 2023-07-25 | 2023-12-29 | 107
BLAST/PAINT - PIPE SUPPORTS |  |  | 60 | 2023-04-14 | 2023-06-23 | 2023-07-25 | 2023-10-03 | 88
0 | FISTPN1030 | IGD-E - BLAST/PAINT - BALANCE PIPE SUPPORTS | 60 | 2023-04-14 | 2023-06-23 | 2023-07-25 | 2023-10-03 | 88
BLAST/PAINTING - PIPING |  |  | 56 | 2023-06-23 | 2023-08-28 | 2023-10-26 | 2023-12-29 | 107
0 | FIPIPN1030 | IGD-E - BLAST/PAINT - CS/LTCS / CLADDED PIPING SPOOLS | 56 | 2023-06-23 | 2023-08-28 | 2023-10-26 | 2023-12-29 | 107
BLAST/PAINT - OTHER SUPPORTS |  |  | 30 | 2023-06-23 | 2023-07-28 | 2023-11-25 | 2023-12-29 | 133
0 | FISTPN1040 | IGD-E - BLAST/PAINT - OTHER E&I SUPPORTS MAIN DECK | 30 | 2023-06-23 | 2023-07-28 | 2023-11-25 | 2023-12-29 | 133
MISCELLANEOUS WORKS |  |  | 56 | 2023-05-24 | 2023-07-28 | 2023-09-02 | 2023-11-07 | 88
0 | FIST5000 | IGD-E - MISCELLANEOUS WORKS | 56 | 2023-05-24 | 2023-07-28 | 2023-09-02 | 2023-11-07 | 88
READY FOR LOADOUT |  |  | 0 | 2023-09-19 | 2023-09-19 | 2023-12-29 | 2023-12-29 | 88
0 | FILO1000 | IGD-E - READY FOR LOADOUT - IGD-E MODIFICATION | 0 |  | 2023-09-19 |  | 2023-12-29 | 88
PIPELINE SLEPEER & SUPPORTS FABRICATION |  |  | 60 | 2022-11-30 | 2023-02-08 | 2023-01-25 | 2023-04-04 | 47
0 | FPSL1000 | SLEEPER FABRICATION | 60 | 2022-11-30 | 2023-02-08 | 2023-01-25 | 2023-04-04 | 47
FABRICATION OF PIPELINE RISERS & TIE-INS SPOOLS |  |  | 125 | 2023-02-03 | 2023-06-29 | 2023-07-11 | 2023-10-18 | 96
RISER & RISER CLAMP AND J TUBE & J TUBE CLAMP FABRICATION |  |  | 118 | 2023-02-03 | 2023-06-21 | 2023-07-22 | 2023-10-18 | 103
RISER CLAMP AND J TUBE CLAMP FABRICATION |  |  | 58 | 2023-02-03 | 2023-04-12 | 2023-07-26 | 2023-09-30 | 148
0 | FCRI1020 | FABRICATE - RISER CLAMPS AND J TUBE CLAMPS PL-1, 2, 3, 4 & 6) | 42 | 2023-02-03 | 2023-03-24 | 2023-07-26 | 2023-09-12 | 148
0 | FCRI1030 | FABRICATE - RISER CLAMPS AND J TUBE CLAMPS (PL-5) | 42 | 2023-02-15 | 2023-04-05 | 2023-08-07 | 2023-09-23 | 148
0 | FCRI2010 | PAINTING OF CLAMPS | 24 | 2023-03-15 | 2023-04-12 | 2023-09-04 | 2023-09-30 | 148
RISER AND J TUBE FABRICATION |  |  | 108 | 2023-02-15 | 2023-06-21 | 2023-07-22 | 2023-10-18 | 103
0 | FCRI1040 | FABRICATE - RISERS AND J TUBE PL-1, 2, 3, 4 & 6 | 60 | 2023-02-15 | 2023-04-26 | 2023-07-22 | 2023-09-29 | 135
0 | FCRI1050 | FABRICATE - RISERS AND J TUBE (PL-5) | 60 | 2023-04-12 | 2023-06-21 | 2023-08-10 | 2023-10-18 | 103
TIE-IN SPOOLS FABRICATION |  |  | 85 | 2023-03-22 | 2023-06-29 | 2023-07-11 | 2023-09-25 | 75
0 | FCRI1000 | FABRICATE - PIPELINE SUBSEA & TIE-IN SPOOLS (PL-1, 2, 3, 4 & 6) | 60 | 2023-03-22 | 2023-05-31 | 2023-07-17 | 2023-09-25 | 100
0 | FCRI1010 | FABRICATE - PIPELINE SUBSEA & TIE-IN SPOOLS (PL-5) | 60 | 2023-04-20 | 2023-06-29 | 2023-07-11 | 2023-09-19 | 70
MISC. FABRICATION ITEMS (CONTINGENCY) |  |  | 70 | 2023-07-18 | 2023-10-07 | 2023-12-14 | 2024-03-04 | 128
0 | FCRI2020 | MISC. STRUCTURAL ITEMS (CONTINGENCY) | 40 | 2023-07-18 | 2023-09-02 | 2023-12-14 | 2024-01-29 | 128
0 | FCRI2030 | MISC. E & I ITEMS (CONTINGENCY) | 40 | 2023-08-15 | 2023-09-30 | 2024-01-18 | 2024-03-04 | 134
0 | FCRI2040 | MISC. PAINTING ITEMS (CONTINGENCY) | 60 | 2023-07-25 | 2023-10-03 | 2023-12-26 | 2024-03-04 | 132
0 | FCRI2050 | MISC. COMMISSIONING ITEMS (CONTINGENCY) | 30 | 2023-09-02 | 2023-10-07 | 2024-01-30 | 2024-03-04 | 128
PIPE & CONCRETE COATING |  |  | 129 | 2022-11-15 | 2023-04-14 | 2023-01-14 | 2023-09-23 | 140
0 | FCRI2000 | FABRICATE PIPELINE CONSTRUCTION AIDS | 30 | 2023-03-01 | 2023-04-05 | 2023-08-21 | 2023-09-23 | 148
3 LPE / 3LPP COATING |  |  | 127 | 2022-11-15 | 2023-04-12 | 2023-01-14 | 2023-06-13 | 54
0 | FCLC1000 | 3 LPP PIPE COATING - PL-2 HAIR DALMA HD-3 TO HD-T4 (12" - 1.2 KM) - | 2 | 2022-11-15 | 2022-11-17 | 2023-01-14 | 2023-01-16 | 52
0 | FCLC1010 | 3 LPP PIPE COATING - PL3- HAIR DALMA HD-T4 TO ARZANAH (16" - 36 KM) - | 16 | 2022-11-17 | 2022-12-06 | 2023-01-17 | 2023-02-03 | 52
0 | FCLC1020 | 3 LPP PIPE COATING - PL 4 WHP BH-03 TO ARZANAH (16" - 49.1KM) - | 24 | 2022-12-06 | 2023-01-03 | 2023-02-13 | 2023-03-11 | 59
0 | FCLC1030 | 3 LPP PIPE COATING - PL-1 SATAH WHP-10 TO ARZANAH (14" - 17.5 KM) - | 8 | 2023-01-03 | 2023-01-12 | 2023-03-17 | 2023-03-25 | 63
0 | FCLC1050 | 3 LPE PIPE COATING - PL-6 SATAH TO ARZANAH (6" - 52.6 KM) - | 21 | 2023-01-12 | 2023-02-06 | 2023-03-31 | 2023-04-24 | 67
0 | FCLC1040 | 3 LPE PIPE COATING - PL-5 IGD-E TO ARZANAH (24" - 33.2 KM) - | 26 | 2023-03-13 | 2023-04-12 | 2023-05-15 | 2023-06-13 | 54
CONCRETE COATING |  |  | 128 | 2022-11-16 | 2023-04-14 | 2023-01-17 | 2023-06-15 | 54
0 | FCLC1060 | CONCRETE COATING - PL-2 HAIR DALMA HD-3 TO HD-T4 (12" - 1.2 KM) - | 2 | 2022-11-16 | 2022-11-18 | 2023-01-17 | 2023-01-18 | 53
0 | FCLC1070 | CONCRETE COATING - PL3- HAIR DALMA HD-T4 TO ARZANAH (16" - 36 KM) - | 16 | 2022-11-19 | 2022-12-08 | 2023-01-19 | 2023-02-06 | 52
0 | FCLC1080 | CONCRETE COATING - PL 4 WHP BH-03 TO ARZANAH (16" - 49.1KM) - | 31 | 2022-12-08 | 2023-01-13 | 2023-02-07 | 2023-03-14 | 52
0 | FCLC1090 | CONCRETE COATING - PL-1 SATAH WHP-10 TO ARZANAH (14" - 17.5 KM) - | 12 | 2023-01-13 | 2023-01-27 | 2023-03-15 | 2023-03-28 | 52
0 | FCLC1110 | CONCRETE COATING - PL-6 SATAH TO ARZANAH (6" - 52.6 KM) - | 25 | 2023-01-27 | 2023-02-25 | 2023-03-29 | 2023-04-26 | 52
0 | FCLC1100 | CONCRETE COATING - PL-5 IGD-E TO ARZANAH (24" - 33.2 KM) - | 26 | 2023-03-15 | 2023-04-14 | 2023-05-17 | 2023-06-15 | 54
LOADOUT & SEAFASTENING |  |  | 336 | 2023-02-06 | 2024-03-04 | 2023-04-03 | 2024-03-25 | 18
OFFSHORE |  |  | 336 | 2023-02-06 | 2024-03-04 | 2023-04-03 | 2024-03-25 | 18
LOADOUT & SEAFASTENING - BU HASEER WHP BH-03 TOPSIDES |  |  | 5 | 2023-10-19 | 2023-10-24 | 2023-11-18 | 2023-11-23 | 26
0 | FBLO2000 | LOADOUT SEAFASTENING OF WHP BH-03 TOPSIDES | 5 | 2023-10-19 | 2023-10-24 | 2023-11-18 | 2023-11-23 | 26
LOADOUT & SEAFASTENING - SATAH WHP 10 TOPSIDES |  |  | 5 | 2023-10-24 | 2023-10-28 | 2023-11-23 | 2023-11-28 | 26
0 | FSLO2000 | LOADOUT SEAFASTENING OF WHP 10 TOPSIDES | 5 | 2023-10-24 | 2023-10-28 | 2023-11-23 | 2023-11-28 | 26
LOADOUT & SEAFASTENING - HAIR DALMA WHP HD-03 TOPSIDES |  |  | 5 | 2024-02-28 | 2024-03-04 | 2024-03-20 | 2024-03-25 | 18
0 | FHLO2000 | LOADOUT SEAFASTENING OF WHP HD-03 TOPSIDES | 5 | 2024-02-28 | 2024-03-04 | 2024-03-20 | 2024-03-25 | 18
LOADOUT & SEAFASTENING - HAIR DALMA WHP HD-T4 TOPSIDES |  |  | 5 | 2024-02-22 | 2024-02-27 | 2024-03-13 | 2024-03-18 | 17
0 | FTLO2000 | LOADOUT SEAFASTENING OF WHP HD-T4 TOPSIDES | 5 | 2024-02-22 | 2024-02-27 | 2024-03-13 | 2024-03-18 | 17
LOADOUT & SEAFASTENING - MODIFICATION IGD-E TOWER (EXISTING) |  |  | 5 | 2023-09-19 | 2023-09-25 | 2023-12-30 | 2024-01-04 | 88
0 | FILO2000 | LOADOUT SEAFASTENING OF IGD-E MODIFICATION MATERIAL | 5 | 2023-09-19 | 2023-09-25 | 2023-12-30 | 2024-01-04 | 88
LOADOUT & SEAFASTENING - PIPELINE SLEPEER & SUPPORTS |  |  | 7 | 2023-02-06 | 2023-02-14 | 2023-04-03 | 2023-04-10 | 47
0 | FCLOPL1050 | LOADOUT & SEAFASTENING OF SLEEPER | 7 | 2023-02-06 | 2023-02-14 | 2023-04-03 | 2023-04-10 | 47
LOADOUT & SEAFASTENING - PIPELINE RISERS & TIE-INS SPOOLS |  |  | 98 | 2023-03-18 | 2023-07-11 | 2023-09-15 | 2023-10-30 | 96
0 | FCLOPL1000 | LOADOUT & SEAFASTENING OF RISER CLAMPS AND J TUBE CLAMPS PL-1, 2, 3, 4 & 6) | 10 | 2023-03-18 | 2023-03-30 | 2023-09-15 | 2023-09-26 | 155
0 | FCLOPL1080 | LOADOUT & SEAFASTENING OF RISER CLAMPS AND J TUBE CLAMPS PL5 | 5 | 2023-04-12 | 2023-04-18 | 2023-10-02 | 2023-10-06 | 148
0 | FCLOPL1070 | LOADOUT & SEAFASTENING OF RISER AND J TUBE PL-1, 2, 3, 4 & 6) | 10 | 2023-04-26 | 2023-05-08 | 2023-09-30 | 2023-10-11 | 135
0 | FCLOPL1060 | LOADOUT & SEAFASTENING OF RISERS AND J TUBE PL5 | 10 | 2023-06-21 | 2023-07-03 | 2023-10-19 | 2023-10-30 | 103
0 | FCLOPL1040 | LOADOUT & SEAFASTENING OF PIPELINE SUBSEA & TIE-IN SPOOLS | 10 | 2023-06-29 | 2023-07-11 | 2023-09-19 | 2023-09-30 | 70
LOADOUT & SEAFASTENING - PIPE & CONCRETE COATING |  |  | 59 | 2023-02-25 | 2023-05-05 | 2023-04-27 | 2023-07-06 | 54
0 | FCLOPL1010 | LOADOUT SEAFASTENING OF LINE PIPES PL-2 & PL-3 | 9 | 2023-02-25 | 2023-03-08 | 2023-04-27 | 2023-05-06 | 52
0 | FCLOPL1020 | LOADOUT SEAFASTENING OF LINE PIPES PL-4 PL-1 & PL-6 | 9 | 2023-03-11 | 2023-03-22 | 2023-05-11 | 2023-05-20 | 52
0 | FCLOPL1030 | LOADOUT SEAFASTENING OF LINE PIPES PL-5 SHORE PULL) | 4 | 2023-04-14 | 2023-04-19 | 2023-06-22 | 2023-06-26 | 59
0 | FCLOPL1090 | LOADOUT SEAFASTENING OF LINE PIPES PL-5 (BALANCE) | 4 | 2023-05-01 | 2023-05-05 | 2023-07-03 | 2023-07-06 | 54
TRANSPORTATION |  |  | 655 | 2022-05-22 | 2024-03-06 | 2023-03-12 | 2024-03-27 | 21
OFFSHORE |  |  | 655 | 2022-05-22 | 2024-03-06 | 2023-03-12 | 2024-03-27 | 21
TRANSPORTATION - BU HASEER WHP BH-03 TOPSIDES |  |  | 2 | 2023-10-25 | 2023-10-26 | 2023-11-24 | 2023-11-25 | 26
0 | TBTO2000 | TRANSPORT WHP-BH-03 TOPSIDES | 2 | 2023-10-25 | 2023-10-26 | 2023-11-24 | 2023-11-25 | 26
TRANSPORTATION - SATAH WHP 10 TOPSIDES |  |  | 2 | 2023-10-30 | 2023-10-31 | 2023-11-29 | 2023-11-30 | 26
0 | TSTO2000 | TRANSPORT WHP-10 TOPSIDES | 2 | 2023-10-30 | 2023-10-31 | 2023-11-29 | 2023-11-30 | 26
TRANSPORTATION - HAIR DALMA WHP HD-03 TOPSIDES |  |  | 4 | 2024-03-02 | 2024-03-06 | 2024-03-23 | 2024-03-27 | 18
0 | THTO2010 | TRANSPORT WHP HD-03 DEMOLISHED TOPSIDES FROM SITE TO NPCC | 2 | 2024-03-02 | 2024-03-04 | 2024-03-23 | 2024-03-25 | 18
0 | THTO2000 | TRANSPORT WHP HD-03 TOPSIDES | 2 | 2024-03-05 | 2024-03-06 | 2024-03-26 | 2024-03-27 | 18
TRANSPORTATION - HAIR DALMA WHP HD-T4 TOPSIDES |  |  | 2 | 2024-02-28 | 2024-02-29 | 2024-03-19 | 2024-03-20 | 17
0 | TTTO2000 | TRANSPORT WHP HD-T4 TOPSIDES | 2 | 2024-02-28 | 2024-02-29 | 2024-03-19 | 2024-03-20 | 17
TRANSPORTATION - MODIFICATION IGD-E TOWER (EXISTING) |  |  | 2 | 2023-09-25 | 2023-09-27 | 2024-01-05 | 2024-01-06 | 88
0 | TITO2000 | TRANSPORT IGD-E MODIFICATION | 2 | 2023-09-25 | 2023-09-27 | 2024-01-05 | 2024-01-06 | 88
TRANSPORTATION - PIPELINE SLEPEER & SUPPORTS |  |  | 2 | 2023-02-14 | 2023-02-16 | 2023-04-11 | 2023-04-12 | 47
0 | TCPL1100 | TRANSPORTATION OF SLEEPER | 2 | 2023-02-14 | 2023-02-16 | 2023-04-11 | 2023-04-12 | 47
TRANSPORTATION - PIPELINE RISERS & TIE-INS SPOOLS |  |  | 98 | 2023-03-30 | 2023-07-22 | 2023-09-27 | 2023-11-02 | 89
0 | TCPL1070 | TRANSPORTATION OF RISER CLAMPS AND J TUBE CLAMPS PL-1, 2, 3, 4 & 6) | 2 | 2023-03-30 | 2023-04-01 | 2023-09-27 | 2023-09-28 | 155
0 | TCPL1080 | TRANSPORTATION OF RISER CLAMPS AND J TUBE CLAMPS PL5) | 3 | 2023-04-18 | 2023-04-21 | 2023-10-07 | 2023-10-10 | 148
0 | TCPL1050 | TRANSPORTATION OF RISERS AND J TUBE PL-1, 2, 3, 4 & 6) | 3 | 2023-05-08 | 2023-05-11 | 2023-10-12 | 2023-10-14 | 135
0 | TCPL1060 | TRANSPORTATION OF RISERS AND J TUBE PL5) | 3 | 2023-07-03 | 2023-07-06 | 2023-10-31 | 2023-11-02 | 103
0 | TCPL1090 | TRANSPORTATION OF PIPELINE SUBSEA & TIE-IN SPOOLS | 10 | 2023-07-11 | 2023-07-22 | 2023-09-30 | 2023-10-12 | 70
TRANSPORTATION - PIPE & CONCRETE COATING |  |  | 52 | 2023-03-08 | 2023-05-08 | 2023-05-08 | 2023-07-08 | 54
0 | TCPL1000 | TRANSPORTATION OF LINE PIPES PL-2 & PL-3 | 2 | 2023-03-08 | 2023-03-10 | 2023-05-08 | 2023-05-09 | 52
0 | TCPL1010 | TRANSPORTATION OF LINE PIPES PL-4 PL-1 & PL-6 | 2 | 2023-03-22 | 2023-03-24 | 2023-05-22 | 2023-05-23 | 52
0 | TCPL1020 | TRANSPORTATION OF LINE PIPES PL-5 (SHORE PULL) | 2 | 2023-04-19 | 2023-04-21 | 2023-06-27 | 2023-06-28 | 59
0 | TCPL1110 | TRANSPORTATION OF LINE PIPES PL-5 (BALANCE) | 2 | 2023-05-05 | 2023-05-08 | 2023-07-07 | 2023-07-08 | 54
POWER CABLE |  |  | 10 | 2023-08-28 | 2023-09-07 | 2023-10-25 | 2023-11-04 | 50
0 | TCPL1030 | TRANSPORTATION OF SUB SEA CABLES | 10 | 2023-08-28 | 2023-09-07 | 2023-10-25 | 2023-11-04 | 50
UMBILICAL STORAGE |  |  | 507 | 2022-05-22 | 2023-10-11 | 2023-03-12 | 2023-11-10 | 30
0 | TCPL1105 | SUBCONTRACTOR PREPRATION FOR THE CARUSEL + MOBILIZATION - UMBILICAL | 90 | 2022-05-22 | 2022-08-20 | 2023-03-12 | 2023-06-10 | 294
0 | TCPL1108 | TRANSPOOLING OF ALL UMBILICAL TO DLB-1000 & POSTLOADING TEST - UMBILICAL | 45 | 2022-08-20 | 2022-10-04 | 2023-06-10 | 2023-07-25 | 294
0 | TCPL1115 | SHIPPING & TRANSPORTATION TO NPCC BY S/C - UMBILICAL | 102 | 2022-10-04 | 2023-01-14 | 2023-07-25 | 2023-11-04 | 294
0 | TCPL1130 | ARRIVAL @ NPCC - UMBILICAL | 0 | 2023-01-14 |  | 2023-11-04 |  | 294
0 | TCPL1120 | STORAGE & PRESERVATION AND TRANSPORTATION OF UMBILICAL | 270 | 2023-01-14 | 2023-10-11 | 2023-11-04 | 2023-11-10 | 30
OFFSHORE CONSTRUCTION / INSTALLATION |  |  | 924 | 2022-02-11 | 2024-08-23 | 2022-04-09 | 2024-09-20 | 28
OFFSHORE SURVEY |  |  | 809 | 2022-02-11 | 2024-04-30 | 2022-04-09 | 2024-07-21 | 82
PRE-ENGINEERING SURVEY |  |  | 77 | 2022-02-11 | 2022-04-29 | 2022-04-09 | 2022-07-25 | 87
PRE-ENGINEERING GEOPYSICAL SURVEY ( SURVEY VESSEL) |  |  | 55 | 2022-02-11 | 2022-04-07 | 2022-04-09 | 2022-06-04 | 58
MOBILIZATION |  |  | 26 | 2022-02-11 | 2022-03-09 | 2022-04-09 | 2022-05-06 | 58
0 | OFCON5610 | Nomination Of Vessel / Loa/ Security Pass/ Optima & Inspection/ Audit | 20 | 2022-02-11 | 2022-03-03 | 2022-04-09 | 2022-04-29 | 57
0 | OFCON1020 | Mobilization at Base | 4 | 2022-03-03 | 2022-03-07 | 2022-04-29 | 2022-05-03 | 57
0 | OFCON1040 | Sail to Site | 2 | 2022-03-07 | 2022-03-09 | 2022-05-04 | 2022-05-06 | 58
PRE-ENGINEERING GEOPHYSICAL SURVEY |  |  | 25 | 2022-03-09 | 2022-04-03 | 2022-05-06 | 2022-05-31 | 58
0 | OFCON1050 | Pre-Engineering Survey of PL-1 & Umbilical UC-1 from Satah WHP-10 to Arzanah | 4 | 2022-03-09 | 2022-03-13 | 2022-05-06 | 2022-05-10 | 58
0 | OFCON1080 | Pre-Engineering Survey of PL-2 & 1No. Umbilical UC-2 from HD-3 to HD WHP-T4 platform | 5 | 2022-03-13 | 2022-03-18 | 2022-05-10 | 2022-05-15 | 58
0 | OFCON1100 | Pre-Engineering Survey of PL-3 & 1No. Umbilical UC-3 from HD WHP-T4 to Arzanah | 4 | 2022-03-18 | 2022-03-22 | 2022-05-15 | 2022-05-19 | 58
0 | OFCON1130 | Pre-Engineering Survey of PL-4 & 1No. Umbilical UC-4 from BH WHP-3 to Arzanah | 4 | 2022-03-22 | 2022-03-26 | 2022-05-19 | 2022-05-23 | 58
0 | OFCON6010 | Pre-Engineering Survey of PL-5, PL-6 P/L & Umbilical CC-1 together (11.7 Km) | 2 | 2022-03-26 | 2022-03-28 | 2022-05-23 | 2022-05-25 | 58
0 | OFCON6020 | Pre-Engineering Survey of PL-5 & 1 No. Composite Cable CC-1 from Arzanah to Existing IGD-E Platform (17.3 Km.) | 2 | 2022-03-28 | 2022-03-30 | 2022-05-25 | 2022-05-27 | 58
0 | OFCON1170 | Pre-Engineering Survey of PL-6 from Arzanah to Zirku Island (35.10 Km) | 4 | 2022-03-30 | 2022-04-03 | 2022-05-27 | 2022-05-31 | 58
DEMOBILIZATION |  |  | 4 | 2022-04-03 | 2022-04-07 | 2022-05-31 | 2022-06-04 | 58
0 | OFCON1190 | Sail to Base | 2 | 2022-04-03 | 2022-04-05 | 2022-05-31 | 2022-06-02 | 58
0 | OFCON1220 | Demob at Base | 2 | 2022-04-05 | 2022-04-07 | 2022-06-02 | 2022-06-04 | 58
PRE-ENGINEERING GEOTECHNICAL SURVEY( SURVEY VESSEL) |  |  | 49 | 2022-02-15 | 2022-04-05 | 2022-04-13 | 2022-06-01 | 57
MOBILIZATION |  |  | 25 | 2022-02-15 | 2022-03-12 | 2022-04-13 | 2022-05-08 | 57
0 | OFCON5620 | Nomination Of Vessel / Loa/ Security Pass/ Optima & Inspection/ Audit | 20 | 2022-02-15 | 2022-03-07 | 2022-04-13 | 2022-05-03 | 57
0 | OFCON1030 | Mobilization at Base | 3 | 2022-03-07 | 2022-03-10 | 2022-05-03 | 2022-05-06 | 57
0 | OFCON1070 | Sail to Site | 2 | 2022-03-10 | 2022-03-12 | 2022-05-06 | 2022-05-08 | 57
PRE-ENGINEERING GEOTECHNICAL SURVEY |  |  | 21 | 2022-03-12 | 2022-04-02 | 2022-05-08 | 2022-05-29 | 57
0 | OFCON1090 | Pre-Engineering Survey of PL-1 & Umbilical UC-1 from Satah WHP-10 to Arzanah | 2 | 2022-03-12 | 2022-03-14 | 2022-05-08 | 2022-05-10 | 57
0 | OFCON1120 | Pre-Engineering Survey of PL-2 & 1No. Umbilical UC-2 from HD-3 to HD WHP-T4 platform | 2 | 2022-03-14 | 2022-03-16 | 2022-05-10 | 2022-05-12 | 57
0 | OFCON1150 | Pre-Engineering Survey of PL-3 & 1No. Umbilical UC-3 from HD WHP-T4 to Arzanah | 3 | 2022-03-16 | 2022-03-19 | 2022-05-12 | 2022-05-15 | 57
0 | OFCON1200 | Pre-Engineering Survey of PL-4 & 1No. Umbilical UC-4 from BH WHP-3 to Arzanah | 3 | 2022-03-19 | 2022-03-22 | 2022-05-15 | 2022-05-18 | 57
0 | OFCON1250 | Pre-Engineering Survey of PL-5, PL-6 P/L & Umbilical CC-1 together (11.7 Km) | 2 | 2022-03-22 | 2022-03-24 | 2022-05-18 | 2022-05-20 | 57
0 | OFCON1280 | Pre-Engineering Survey of PL-5 & 1 No. Composite Cable CC-1 from Arzanah to Existing IGD-E Platform (17.3 Km.) | 2 | 2022-03-24 | 2022-03-26 | 2022-05-20 | 2022-05-22 | 57
0 | OFCON1310 | Pre-Engineering Survey of PL-6 from Arzanah to Zirku Island (35.10 Km) | 3 | 2022-03-26 | 2022-03-29 | 2022-05-22 | 2022-05-25 | 57
0 | OFCON1330 | Soil coring at 35 crossing locations | 4 | 2022-03-29 | 2022-04-02 | 2022-05-25 | 2022-05-29 | 57
DEMOBILIZATION |  |  | 3 | 2022-04-02 | 2022-04-05 | 2022-05-29 | 2022-06-01 | 57
0 | OFCON1380 | Sail to Base | 1 | 2022-04-02 | 2022-04-03 | 2022-05-29 | 2022-05-30 | 57
0 | OFCON1390 | Demob at Base | 2 | 2022-04-03 | 2022-04-05 | 2022-05-30 | 2022-06-01 | 57
PRE-ENGINEERING ROV & CP SURVEY FOR PIPELINES, CABLES & UMBILICALS CROSSINGS DP-2 VESSEL |  |  | 55 | 2022-03-05 | 2022-04-29 | 2022-05-02 | 2022-07-25 | 87
MOBILIZATION |  |  | 36 | 2022-03-05 | 2022-04-10 | 2022-05-02 | 2022-06-06 | 57
0 | OFCON5630 | Nomination Of Vessel / Loa/ Security Pass/ Optima & Inspection/ Audit | 30 | 2022-03-05 | 2022-04-04 | 2022-05-02 | 2022-06-01 | 58
0 | OFCON1060 | Mobilization at Base | 3 | 2022-04-05 | 2022-04-08 | 2022-06-01 | 2022-06-04 | 57
0 | OFCON1110 | Sail to Site | 2 | 2022-04-08 | 2022-04-10 | 2022-06-04 | 2022-06-06 | 57
PRE-ENGINEERING ROV & CP SURVEY FOR PIPELINES, CABLES & UMBILICALS CROSSINGS(INCLUDING JACKET FACE |  |  | 16 | 2022-04-10 | 2022-04-26 | 2022-06-06 | 2022-06-22 | 57
0 | OFCON1140 | ROV Survey - HD-03 (West face) for 1 No. 14" Riser & 1 No.24" J-Tbue incl. Anodes Repalcement Location. | 1 | 2022-04-10 | 2022-04-11 | 2022-06-06 | 2022-06-07 | 57
0 | OFCON1160 | ROV Survey - 13 Nos. Pipeline Crossings for PL-6, 6" P/L, Arzanah Island to Zirku Island | 1 | 2022-04-11 | 2022-04-12 | 2022-06-07 | 2022-06-08 | 57
0 | OFCON1180 | ROV Survey - 6 Nos. Pipeline Crossings for PL-3, 16" P/L, HD WHP T4 to Arzanah Island | 2 | 2022-04-12 | 2022-04-14 | 2022-06-08 | 2022-06-10 | 57
0 | OFCON1210 | ROV Survey - 2 Nos. Pipeline Crossings for PL-2, 12" P/L, HD 3 to HD WHP T4 | 1 | 2022-04-14 | 2022-04-15 | 2022-06-10 | 2022-06-11 | 57
0 | OFCON1230 | ROV Survey - 1 No.Pipeline Crossings for PL-5 24" P/L, Arzanah Island to IGD-E (KP-38) | 1 | 2022-04-15 | 2022-04-16 | 2022-06-11 | 2022-06-12 | 57
0 | OFCON1240 | ROV Survey - 9 No. Pipeline Crossings for PL-4, 16" P/L, BH WHP-3 to Arzanah Island | 1 | 2022-04-16 | 2022-04-17 | 2022-06-12 | 2022-06-13 | 57
0 | OFCON1260 | ROV Survey - 1 No. Pipeline Crossings for PL-1, 14" P/L, Satah WHP-10 to Arzanah Island | 1 | 2022-04-17 | 2022-04-18 | 2022-06-13 | 2022-06-14 | 57
0 | OFCON1270 | ROV Survey - 2 No. Umbilical Crossings for UC-1, Arzanah Island to Satah WHP-10 | 1 | 2022-04-18 | 2022-04-19 | 2022-06-14 | 2022-06-15 | 57
0 | OFCON1290 | ROV Survey - 6 No.Umbilical Crossings for UC-2 , HD WHP T4 to HD-3 | 1 | 2022-04-19 | 2022-04-20 | 2022-06-15 | 2022-06-16 | 57
0 | OFCON1300 | ROV Survey - 6 No. Umbilical Crossings for UC-3, Arzanah Island to HD WHP T4 | 2 | 2022-04-20 | 2022-04-22 | 2022-06-16 | 2022-06-18 | 57
0 | OFCON1320 | ROV Survey - Umbilical Crossings 10 No. for UC-4, Arzanah Island to BH WHP-3 | 3 | 2022-04-22 | 2022-04-25 | 2022-06-18 | 2022-06-21 | 57
0 | OFCON1340 | ROV Survey - Composite Cable Crossings 1 No. for CC-1, Arzanah Island to IGD-E | 1 | 2022-04-25 | 2022-04-26 | 2022-06-21 | 2022-06-22 | 57
0 | OFCON1360 | ROV Survey - Survey in the Al Qarnain Island Marine Protected Area | 0 | 2022-04-26 | 2022-04-26 | 2022-06-22 | 2022-06-22 | 57
DEMOBILIZATION |  |  | 3 | 2022-04-26 | 2022-04-29 | 2022-07-22 | 2022-07-25 | 87
0 | OFCON1350 | Sail to Base | 1 | 2022-04-26 | 2022-04-27 | 2022-07-22 | 2022-07-23 | 87
0 | OFCON1370 | Demob at Base | 2 | 2022-04-27 | 2022-04-29 | 2022-07-23 | 2022-07-25 | 87
PRE-CONSTRUCTION SURVEY |  |  | 81 | 2022-09-19 | 2022-12-09 | 2022-12-29 | 2023-04-13 | 125
PRE-CONSTRUCTION TOPSIDE SURVEY AT EXISTING JACKETS ( SURVEY VESSEL) |  |  | 10 | 2022-09-19 | 2022-09-29 | 2022-12-29 | 2023-01-12 | 105
MOBILIZATION |  |  | 3 | 2022-09-19 | 2022-09-22 | 2022-12-29 | 2023-01-01 | 101
0 | OFCON1620 | Mobilization at Base | 2 | 2022-09-19 | 2022-09-21 | 2022-12-29 | 2022-12-31 | 101
0 | OFCON1630 | Sail to Site | 1 | 2022-09-21 | 2022-09-22 | 2022-12-31 | 2023-01-01 | 101
PRE-CONSTRUCTION TOPSIDE SURVEY AT EXISTING JACKETS |  |  | 5 | 2022-09-22 | 2022-09-27 | 2023-01-01 | 2023-01-06 | 101
0 | OFCON1650 | Pre-Construction Topside Survey at IGD-E (KP-38) | 1 | 2022-09-22 | 2022-09-23 | 2023-01-01 | 2023-01-02 | 101
0 | OFCON1660 | Pre-Construction Topside Survey at Satah WHP-10 Jacket | 1 | 2022-09-23 | 2022-09-24 | 2023-01-02 | 2023-01-03 | 101
0 | OFCON1680 | Pre-Construction Topside Survey at BH WHP-3 Jacket | 1 | 2022-09-24 | 2022-09-25 | 2023-01-03 | 2023-01-04 | 101
0 | OFCON1690 | Pre-Construction Topside Survey at HD-3 Jacket | 1 | 2022-09-25 | 2022-09-26 | 2023-01-04 | 2023-01-05 | 101
0 | OFCON1700 | Pre-Construction Topside Survey at HD WHP T4 Jacket | 1 | 2022-09-26 | 2022-09-27 | 2023-01-05 | 2023-01-06 | 101
DEMOBILIZATION |  |  | 2 | 2022-09-27 | 2022-09-29 | 2023-01-06 | 2023-01-12 | 105
0 | OFCON1710 | Sail to Base | 1 | 2022-09-27 | 2022-09-28 | 2023-01-06 | 2023-01-07 | 101
0 | OFCON1720 | Demob at Base | 1 | 2022-09-28 | 2022-09-29 | 2023-01-11 | 2023-01-12 | 105
PRE- CONSTRUCTION ANCHOR CLEARANCE SURVEY ( SURVEY VESSEL) |  |  | 72 | 2022-09-28 | 2022-12-09 | 2023-01-07 | 2023-04-13 | 125
MOBILIZATION |  |  | 5 | 2022-09-28 | 2022-10-03 | 2023-01-07 | 2023-01-12 | 101
0 | OFCON1580 | Mobilization at Base | 3 | 2022-09-28 | 2022-10-01 | 2023-01-07 | 2023-01-10 | 101
0 | OFCON1600 | Sail to Site | 2 | 2022-10-01 | 2022-10-03 | 2023-01-10 | 2023-01-12 | 101
PRE- CONSTRUCTION ANCHOR CLEARANCE SURVEY |  |  | 62 | 2022-10-03 | 2022-12-04 | 2023-01-12 | 2023-03-15 | 101
0 | OFCON1610 | Pre-Construction anchor clearance survey of PL-1 & Umbilical UC-1 from Satah WHP-10 to Arzanah | 5 | 2022-10-03 | 2022-10-08 | 2023-01-12 | 2023-01-17 | 101
0 | OFCON1640 | Pre-Construction anchor clearance survey of PL-2 & 1No. Umbilical UC-2 from HD-3 to HD WHP-T4 platform | 2 | 2022-10-08 | 2022-10-10 | 2023-01-17 | 2023-01-19 | 101
0 | OFCON1670 | Pre-Construction anchor clearance survey of PL-3 & 1No. Umbilical UC-3 from HD WHP-T4 to Arzanah | 14 | 2022-10-10 | 2022-10-24 | 2023-01-19 | 2023-02-02 | 101
0 | OFCON1730 | Pre-Construction anchor clearance survey of PL-4 & 1No. Umbilical UC-4 from BH WHP-3 to Arzanah | 16 | 2022-10-24 | 2022-11-09 | 2023-02-02 | 2023-02-18 | 101
0 | OFCON1740 | Pre-Construction anchor clearance survey of PL-5, PL-6 P/L, CC-1 together (11.7 Km length) | 5 | 2022-11-09 | 2022-11-14 | 2023-02-18 | 2023-02-23 | 101
0 | OFCON1760 | Pre-Const'n anchor clearance survey of PL-5 & 1 # Composite Cable CC-1 from Arzanah to Existing IGD-E Platform 17.3 Km | 7 | 2022-11-14 | 2022-11-21 | 2023-02-23 | 2023-03-02 | 101
0 | OFCON1840 | Pre-Construction anchor clearance survey of PL-6 from Arzanah to Zirku Island (35.1Km length) | 13 | 2022-11-21 | 2022-12-04 | 2023-03-02 | 2023-03-15 | 101
DEMOBILIZATION |  |  | 5 | 2022-12-04 | 2022-12-09 | 2023-04-08 | 2023-04-13 | 125
0 | OFCON1890 | Sail to Base | 2 | 2022-12-04 | 2022-12-06 | 2023-04-08 | 2023-04-10 | 125
0 | OFCON1920 | Demob at Base | 3 | 2022-12-06 | 2022-12-09 | 2023-04-10 | 2023-04-13 | 125
AS LAID ROV SURVEY OF PIPELINE (CCC MARITIME-2) |  |  | 54 | 2023-09-30 | 2023-11-23 | 2023-12-14 | 2024-05-21 | 180
MOBILIZATION |  |  | 5 | 2023-09-30 | 2023-10-05 | 2023-12-14 | 2023-12-19 | 75
0 | OFCON2920 | Mobilization at Base | 3 | 2023-09-30 | 2023-10-03 | 2023-12-14 | 2023-12-17 | 75
0 | OFCON2950 | Sail to Site | 2 | 2023-10-03 | 2023-10-05 | 2023-12-17 | 2023-12-19 | 75
AS LAID ROV SURVEY OF PIPELINE |  |  | 46 | 2023-10-05 | 2023-11-20 | 2023-12-19 | 2024-02-03 | 75
0 | OFCON3140 | As Laid ROV Survey - PL-2, 12" P/L, HD-3 to HD WHP T4, 1.179 kms. | 1 | 2023-10-05 | 2023-10-06 | 2023-12-19 | 2023-12-20 | 75
0 | OFCON3430 | As Laid ROV Survey - PL-3, 16" P/L, HD WHP T4 to Arzanah Island, 34.864 kms. | 8 | 2023-10-06 | 2023-10-14 | 2023-12-20 | 2023-12-28 | 75
0 | OFCON3750 | As Laid ROV Survey - PL-5, 24" P/L, Arzanah Island to IGD-E, 33.503 kms. | 8 | 2023-10-14 | 2023-10-22 | 2023-12-28 | 2024-01-05 | 75
0 | OFCON3230 | As Laid ROV Survey - PL-4, 16" P/L, BH WHP-3 to Arzanah Island, 48.824 kms. | 12 | 2023-10-22 | 2023-11-03 | 2024-01-05 | 2024-01-17 | 75
0 | OFCON3160 | As Laid ROV Survey - PL-1, 14" P/L, Satah WHP-10 to Arzanah Island, 17.449 kms. | 5 | 2023-11-03 | 2023-11-08 | 2024-01-17 | 2024-01-22 | 75
0 | OFCON2970 | As Laid ROV Survey - PL-6, 6" P/L, Arzanah Island to Zirku Island, 52.406 kms. | 12 | 2023-11-08 | 2023-11-20 | 2024-01-22 | 2024-02-03 | 75
DEMOBILIZATION |  |  | 3 | 2023-11-20 | 2023-11-23 | 2024-05-18 | 2024-05-21 | 180
0 | OFCON3880 | Sail to Base | 1 | 2023-11-20 | 2023-11-21 | 2024-05-18 | 2024-05-19 | 180
0 | OFCON3930 | Demob at Base | 2 | 2023-11-21 | 2023-11-23 | 2024-05-19 | 2024-05-21 | 180
AS-LAID ROV SURVEY OF UMBILICALS & CABLE (4 NO. UMBILICALS & 1 NO. CABLE) (DP-II CCC MARITIME) |  |  | 117 | 2023-12-10 | 2024-04-05 | 2024-03-02 | 2024-05-21 | 46
MOBILIZATION |  |  | 5 | 2023-12-10 | 2023-12-15 | 2024-03-02 | 2024-03-07 | 83
0 | OFCON4540 | Mobilization at Base | 3 | 2023-12-10 | 2023-12-13 | 2024-03-02 | 2024-03-05 | 83
0 | OFCON4580 | Sail to Site | 2 | 2023-12-13 | 2023-12-15 | 2024-03-05 | 2024-03-07 | 83
AS-LAID ROV SURVEY OF UMBILICALS & CABLE (4 NO. UMBILICALS & 1 NO. CABLE) |  |  | 109 | 2023-12-15 | 2024-04-02 | 2024-03-07 | 2024-05-18 | 46
0 | OFCON5090 | As Laid ROV Survey Arzanah Island to IGD-E, 1st CC-1 Composite Cable (33.534 Kms. Length) | 8 | 2023-12-15 | 2023-12-23 | 2024-03-07 | 2024-03-15 | 83
0 | OFCON4670 | As Laid ROV Survey Arzanah Island to Satah WHP-10 UC-1 Umbilical (17.529 Kms. Length) | 4 | 2023-12-24 | 2023-12-28 | 2024-03-15 | 2024-03-19 | 82
0 | OFCON4960 | As Laid ROV Survey Arzanah Island to BH WHP-3 UC-4 Umbilical (48.816 Kms. Length) | 11 | 2024-01-04 | 2024-01-15 | 2024-03-19 | 2024-03-30 | 75
0 | OFCON4640 | As Laid ROV HD WHP T4 to HD-3 UC-2 Umbilical (1.244 Kms. Length) | 1 | 2024-03-22 | 2024-03-23 | 2024-04-19 | 2024-04-20 | 28
0 | OFCON4750 | As Laid ROV Survey Arzanah Island to HD WHP T4 UC-3 Umbilical (34.92 Kms. Length) | 8 | 2024-03-25 | 2024-04-02 | 2024-05-10 | 2024-05-18 | 46
DEMOBILIZATION |  |  | 3 | 2024-04-02 | 2024-04-05 | 2024-05-18 | 2024-05-21 | 46
0 | OFCON5280 | Sail to Base | 1 | 2024-04-02 | 2024-04-03 | 2024-05-18 | 2024-05-19 | 46
0 | OFCON5290 | Demob at Base | 2 | 2024-04-03 | 2024-04-05 | 2024-05-19 | 2024-05-21 | 46
POST- CONSTRUCTION ANCHOR CLEARANCE SURVEY |  |  | 109 | 2024-01-12 | 2024-04-30 | 2024-06-08 | 2024-07-21 | 82
POST- CONSTRUCTION ANCHOR CLEARANCE SURVEY (SURVEY VESSEL) |  |  | 109 | 2024-01-12 | 2024-04-30 | 2024-06-08 | 2024-07-21 | 82
MOBILIZATION |  |  | 5 | 2024-01-13 | 2024-01-18 | 2024-06-19 | 2024-06-24 | 158
0 | OFCON5690 | Mobilization at Base | 3 | 2024-01-13 | 2024-01-16 | 2024-06-19 | 2024-06-22 | 158
0 | OFCON5700 | Sail to Site | 2 | 2024-01-16 | 2024-01-18 | 2024-06-22 | 2024-06-24 | 158
POST- CONSTRUCTION ANCHOR CLEARANCE SURVEY |  |  | 109 | 2024-01-12 | 2024-04-30 | 2024-06-08 | 2024-07-21 | 82
0 | OFCON5790 | Post-Construction anchor clearance survey of PL-5 & 1 No. Composite Cable from Arzanah to Existing IGD-E Platform | 7 | 2024-01-12 | 2024-01-19 | 2024-06-08 | 2024-06-15 | 148
0 | OFCON5710 | Post-Construction anchor clearance survey of PL-1 & Umbilical from Satah WHP-10 to Arzanah | 6 | 2024-01-18 | 2024-01-24 | 2024-06-24 | 2024-06-30 | 158
0 | OFCON5740 | Post-Construction anchor clearance survey of PL-4 & 1No. Umbilical from BH WHP-3 to Arzanah | 15 | 2024-01-19 | 2024-02-03 | 2024-06-15 | 2024-06-30 | 148
0 | OFCON5720 | Post-Construction anchor clearance survey of PL-2 & 1No. Umbilical from HD-3 to HD WHP-T4 platform | 1 | 2024-03-24 | 2024-03-25 | 2024-07-07 | 2024-07-08 | 105
0 | OFCON5780 | Post-Construction anchor clearance survey of PL-5, PL-6 P/L together for 11.7 Km length | 5 | 2024-03-30 | 2024-04-04 | 2024-06-30 | 2024-07-05 | 92
0 | OFCON5750 | Post-Construction anchor clearance survey of PL-6 from Arzanah to Zirku Island for 35.1Km length | 13 | 2024-04-04 | 2024-04-17 | 2024-07-05 | 2024-07-18 | 92
0 | OFCON5730 | Post-Construction anchor clearance survey of PL-3 & 1No. Umbilical from HD WHP-T4 to Arzanah | 13 | 2024-04-17 | 2024-04-30 | 2024-07-08 | 2024-07-21 | 82
DEMOBILIZATION |  |  | 3 | 2024-04-17 | 2024-04-20 | 2024-07-18 | 2024-07-21 | 92
0 | OFCON5760 | Sail to Base | 1 | 2024-04-17 | 2024-04-18 | 2024-07-18 | 2024-07-19 | 92
0 | OFCON5770 | Demob at Base | 2 | 2024-04-18 | 2024-04-20 | 2024-07-19 | 2024-07-21 | 92
AS-BUILT ROV AND CP SURVEY OF PIPELINES, UMBILICALS & CABLES (DP-II ZAKHER PELICAN/EQ) |  |  | 110 | 2023-12-29 | 2024-04-17 | 2024-03-30 | 2024-07-08 | 82
MOBILIZATION |  |  | 5 | 2024-01-04 | 2024-01-09 | 2024-04-07 | 2024-04-12 | 94
0 | OFCON4650 | Mobilization at Base | 3 | 2024-01-04 | 2024-01-07 | 2024-04-07 | 2024-04-10 | 94
0 | OFCON4720 | Sail to Site | 2 | 2024-01-07 | 2024-01-09 | 2024-04-10 | 2024-04-12 | 94
AS-BUILT ROV AND CP SURVEY OF PIPELINES, UMBILICALS & CABLES |  |  | 110 | 2023-12-29 | 2024-04-17 | 2024-03-30 | 2024-07-08 | 82
0 | OFCON5350 | As-built Survey of PL-5 & 2 No. Composite Cable CC-1 from Arzanah to Existing IGD-E Platform | 14 | 2023-12-29 | 2024-01-12 | 2024-04-22 | 2024-05-06 | 115
0 | OFCON4730 | As-built Survey of PL-1 & Umbilical UC-1 from Satah WHP-10 to Arzanah | 9 | 2024-01-09 | 2024-01-18 | 2024-04-12 | 2024-04-21 | 94
0 | OFCON5130 | As-built Survey of PL-4 & Umbilical UC-4 from BH WHP-3 to Arzanah | 22 | 2024-01-15 | 2024-02-06 | 2024-03-30 | 2024-04-21 | 75
0 | OFCON4890 | As-built Survey of PL-2 & Umbilical UC-2 from HD-3 to HD WHP-T4 Platform | 1 | 2024-03-23 | 2024-03-24 | 2024-04-20 | 2024-04-21 | 28
0 | OFCON5420 | As-built Survey of PL-6 from Arzanah to Zirku Island | 12 | 2024-03-18 | 2024-03-30 | 2024-05-06 | 2024-05-18 | 49
0 | OFCON4920 | As-built Survey of PL-3 & Umbilical UC-3 from HD WHP-T4 to Arzanah | 15 | 2024-04-02 | 2024-04-17 | 2024-06-23 | 2024-07-08 | 82
DEMOBILIZATION |  |  | 3 | 2024-03-30 | 2024-04-02 | 2024-05-18 | 2024-05-21 | 49
0 | OFCON5500 | Sail to Base | 1 | 2024-03-30 | 2024-03-31 | 2024-05-18 | 2024-05-19 | 49
0 | OFCON5540 | Demob at Base | 2 | 2024-03-31 | 2024-04-02 | 2024-05-19 | 2024-05-21 | 49
PIPELINE INSTALLATION |  |  | 410 | 2023-02-11 | 2024-03-28 | 2023-04-08 | 2024-05-21 | 54
INSTALLATION OF PRELAY SUPPORTS, SLEEPERS ETC FOR PIPELINE, UMBILICAL, CABLE CROSSINGS (CCC PIONEER/ |  |  | 98 | 2023-02-11 | 2023-05-20 | 2023-04-08 | 2023-11-20 | 184
MOBILIZATION |  |  | 5 | 2023-02-11 | 2023-02-16 | 2023-04-08 | 2023-04-13 | 56
0 | OFCON1800 | Mobilization at Base | 3 | 2023-02-11 | 2023-02-14 | 2023-04-08 | 2023-04-11 | 56
0 | OFCON1820 | Sail to Site | 2 | 2023-02-14 | 2023-02-16 | 2023-04-11 | 2023-04-13 | 56
SLEEPERS INSTALLATION FOR PIPELINES CROSSINGS |  |  | 45 | 2023-02-16 | 2023-04-02 | 2023-04-13 | 2023-06-15 | 74
0 | OFCON2030 | Install 4 Nos. Sleeper for PL-2, 12" P/L crossings HD 3 to HD WHP T4 | 1 | 2023-02-16 | 2023-02-17 | 2023-04-13 | 2023-04-14 | 56
0 | OFCON2040 | Pre lay Correction of PL-2, 12" P/L with 26 Nos. Mattresses | 3 | 2023-02-17 | 2023-02-20 | 2023-04-14 | 2023-04-17 | 56
0 | OFCON1960 | Install 16 Nos. Sleeper for PL-3, 16" P/L crossings HD WHP T4 to Arzanah Island | 3 | 2023-02-20 | 2023-02-23 | 2023-04-17 | 2023-04-20 | 56
0 | OFCON1970 | Install 6 No. RCC Sleepers & 6 No. Log Mattresses for Buckling trigger of PL-3 P/L | 2 | 2023-02-23 | 2023-02-25 | 2023-05-01 | 2023-05-03 | 67
0 | OFCON1990 | Pre lay Span Correction of PL-3, 16" P/L with 10 No. Grout bags | 7 | 2023-02-25 | 2023-03-04 | 2023-05-03 | 2023-05-10 | 67
0 | OFCON2050 | Install 8 Nos. Sleeper for PL-5 24" P/L crossings Arzanah Island to IGD-E (KP-38) | 1 | 2023-03-04 | 2023-03-05 | 2023-05-10 | 2023-05-11 | 67
0 | OFCON2090 | Install 6 No. RCC Sleepers & 6 No. Log Mattresses for Buckling trigger of PL-5, 16" P/L | 2 | 2023-03-05 | 2023-03-07 | 2023-05-11 | 2023-05-13 | 67
0 | OFCON2070 | Install 62 Nos. Sleeper for PL-4, 16" P/L crossings BH WHP-3 to Arzanah Island | 7 | 2023-03-07 | 2023-03-14 | 2023-05-13 | 2023-05-20 | 67
0 | OFCON2100 | Pre lay correction of PL-4, 16" P/L with 4 Nos. Grout Bags | 3 | 2023-03-14 | 2023-03-17 | 2023-05-20 | 2023-05-23 | 67
0 | OFCON2110 | Install 8 Nos. Sleeper for PL-1, 14" P/L crossings Satah WHP-10 to Arzanah Island | 2 | 2023-03-17 | 2023-03-19 | 2023-05-26 | 2023-05-28 | 70
0 | OFCON2140 | Install 6 No. RCC Sleepers & 6 No. Log Mattresses for Buckling trigger of PL-1, 14" P/L | 2 | 2023-03-19 | 2023-03-21 | 2023-05-28 | 2023-05-30 | 70
0 | OFCON2150 | Pre lay correction of 14" P/L with 4 Nos. Grout Bargs Supports | 3 | 2023-03-21 | 2023-03-24 | 2023-05-30 | 2023-06-02 | 70
0 | OFCON1880 | Install 58 Nos. Sleeper for PL-6, 6" P/L crossings Arzanah Island to Zirku Island | 8 | 2023-03-24 | 2023-04-01 | 2023-06-06 | 2023-06-14 | 74
0 | OFCON1950 | Pre lay Correction of PL-6, 6" P/L with 1 No. Grout Bag Supports | 1 | 2023-04-01 | 2023-04-02 | 2023-06-14 | 2023-06-15 | 74
INSTALLATION OF CLAMPS FOR RISERS & J-TUBES AND INSTALLATION OF J-TUBES |  |  | 30 | 2023-04-02 | 2023-05-02 | 2023-09-28 | 2023-10-21 | 172
0 | OFCON2160 | At HD WHP T4, Install 3No. Riser Clamps for 16" Riser (West Face) | 3 | 2023-04-02 | 2023-04-05 | 2023-09-28 | 2023-10-01 | 179
0 | OFCON2170 | At HD WHP T4, Install 3No. Riser Clamps for 12" Riser (East Face) | 3 | 2023-04-05 | 2023-04-08 | 2023-10-01 | 2023-10-04 | 179
0 | OFCON2180 | At HD-3, Install 3No. Riser Clamps for 12" Riser (West Face) | 3 | 2023-04-08 | 2023-04-11 | 2023-10-04 | 2023-10-07 | 179
0 | OFCON2190 | At HD-3, Install 3No. J-Tube Clamps | 3 | 2023-04-11 | 2023-04-14 | 2023-10-07 | 2023-10-10 | 179
0 | OFCON2200 | At IGD-E, Install 2No. Riser Clamps for 24" Riser (South Face) | 2 | 2023-04-21 | 2023-04-23 | 2023-10-10 | 2023-10-12 | 172
0 | OFCON2210 | At IGD-E, Install 6No. J-Tube Clamps & 2 No. Clamps for Bell Mouth | 5 | 2023-04-23 | 2023-04-28 | 2023-10-12 | 2023-10-17 | 172
0 | OFCON2220 | At BH WHP-3, Install 3No. Riser Clamps for 16" Riser (West Face) | 2 | 2023-04-28 | 2023-04-30 | 2023-10-17 | 2023-10-19 | 172
0 | OFCON2240 | At Satah WHP-10, Install 2No. Riser Clamps for 14" Riser (East Face) | 2 | 2023-04-30 | 2023-05-02 | 2023-10-19 | 2023-10-21 | 172
SLEEPERS INSTALLATION FOR CABLE CROSSINGS (HDPE PIPES) |  |  | 15 | 2023-05-02 | 2023-05-17 | 2023-10-21 | 2023-11-05 | 172
0 | OFCON2250 | Install 6 Nos. HDPE pipes for UC-1 Umbilical Crossing, Arzanah Island to Satah WHP-10 | 2 | 2023-05-02 | 2023-05-04 | 2023-10-21 | 2023-10-23 | 172
0 | OFCON2260 | Install 6 Nos. HDPE pipes for UC-2 Umbilical Crossings, HD WHP T4 to HD-3 | 2 | 2023-05-04 | 2023-05-06 | 2023-10-23 | 2023-10-25 | 172
0 | OFCON2270 | Install 17 Nos. HDPE pipes for UC-3 Umbilical Crossing, Arzanah Island to HD WHP T4 | 4 | 2023-05-06 | 2023-05-10 | 2023-10-25 | 2023-10-29 | 172
0 | OFCON2300 | Install 36 Nos. HDPE pipes for UC-4 Umbilical Crossing, Arzanah Island to BH WHP-3 | 5 | 2023-05-10 | 2023-05-15 | 2023-10-29 | 2023-11-03 | 172
0 | OFCON2350 | Install 10Nos. HDPE pipes for CC-1 Composite Cable Crossing, Arzanah Island to IGD-E | 2 | 2023-05-15 | 2023-05-17 | 2023-11-03 | 2023-11-05 | 172
DEMOBILIZATION |  |  | 3 | 2023-05-17 | 2023-05-20 | 2023-11-17 | 2023-11-20 | 184
0 | OFCON2370 | Sail to Base | 1 | 2023-05-17 | 2023-05-18 | 2023-11-17 | 2023-11-18 | 184
0 | OFCON2390 | Demob at Base | 2 | 2023-05-18 | 2023-05-20 | 2023-11-18 | 2023-11-20 | 184
6 NO. SHOREPULL & LAY 6NO. PIPELINES AND COMPOSITE CABLES (DLB-750 OR EQ.) |  |  | 186 | 2023-03-04 | 2023-09-06 | 2023-05-03 | 2023-11-05 | 60
MOBILIZATION |  |  | 6 | 2023-03-04 | 2023-03-10 | 2023-05-03 | 2023-05-09 | 60
0 | OFCON2280 | Mobilization at Base | 4 | 2023-03-04 | 2023-03-08 | 2023-05-03 | 2023-05-07 | 60
0 | OFCON2320 | Sail to Site | 2 | 2023-03-08 | 2023-03-10 | 2023-05-07 | 2023-05-09 | 60
PL 2 - 12" GAS PRODUCER FROM HAIR DALMA HD-03 TO HAIRE DALMA WHP HD-T4 |  |  | 4 | 2023-03-10 | 2023-03-14 | 2023-05-09 | 2023-05-13 | 60
0 | OFCON2870 | Move & Set up at HD WHP T4 platform East face, Install PL-2, 14", HD WHP T4 to HD-3 P/L & Recover anchor | 4 | 2023-03-10 | 2023-03-14 | 2023-05-09 | 2023-05-13 | 60
PL 3 - 16" GAS PRODUCER FROM HAIR DALMA WHP HD-T4 TO ARZANAH ISLAND |  |  | 25 | 2023-06-01 | 2023-06-26 | 2023-07-31 | 2023-08-25 | 60
BALANCE PIPELINE - PL 3 16" GAS |  |  | 25 | 2023-06-01 | 2023-06-26 | 2023-07-31 | 2023-08-25 | 60
0 | OFCON3020 | Lay bal 33.85 Km PL-3, 18" P/L upto HD WHP T4, Laydown & Recover anchor | 25 | 2023-06-01 | 2023-06-26 | 2023-07-31 | 2023-08-25 | 60
PL 4 - 16" GAS PRODUCER BU HASEER WHP BH-03 TO ARZANAH ISLANE |  |  | 32 | 2023-06-26 | 2023-07-28 | 2023-08-25 | 2023-09-26 | 60
BALANCE PIPELINE - PL 4 16" GAS |  |  | 32 | 2023-06-26 | 2023-07-28 | 2023-08-25 | 2023-09-26 | 60
0 | OFCON2890 | Move to Arzanah East, Set-up at 1.2 Km from LFP, Lay Bal 47.7 Km PL-4, 16" Arzanah to BH WHP-3 P/L & Recover Anchors. | 32 | 2023-06-26 | 2023-07-28 | 2023-08-25 | 2023-09-26 | 60
PL1 - 14" GAS PRODUCER SATAH WHP-10 TO ARZANAH ISLAND |  |  | 12 | 2023-07-28 | 2023-08-09 | 2023-09-26 | 2023-10-08 | 60
BALANCE PIPELINE PL1 14" GAS |  |  | 12 | 2023-07-28 | 2023-08-09 | 2023-09-26 | 2023-10-08 | 60
0 | OFCON2880 | Move to Arzanah East, Set-up at 1.20 Km from LFP (KP16.249), Lay Bal 16.3Km PL-1, 14" Arzanah to Satah WHP 10 P/L | 12 | 2023-07-28 | 2023-08-09 | 2023-09-26 | 2023-10-08 | 60
PL 6 - 6" CONDENSATE EXPORT ARZANAH ISLAND TO ZIRKU ISLAND |  |  | 28 | 2023-08-09 | 2023-09-06 | 2023-10-08 | 2023-11-05 | 60
BALANCE PIPELINE PL 6 - 6" CONDENSATE |  |  | 28 | 2023-08-09 | 2023-09-06 | 2023-10-08 | 2023-11-05 | 60
0 | OFCON2670 | Shore pull of 6" PL-6 P/L with 2 No. FO Cable & Continue laying upto KP 51.0, Laydown & Recover Anchor | 28 | 2023-08-09 | 2023-09-06 | 2023-10-08 | 2023-11-05 | 60
PL 5 - 24" GAS EXPORT ARZANAH ISLAND TO IGD E TOWER |  |  | 23 | 2023-05-09 | 2023-06-01 | 2023-07-08 | 2023-07-31 | 60
BALANCE PIPELINE PL 5 - 24" GAS EXPORT |  |  | 23 | 2023-05-09 | 2023-06-01 | 2023-07-08 | 2023-07-31 | 60
0 | OFCON3420 | Move to Arzanah (East), Set-up at KP 1.2, Lay Bal 32.3 Km PL-5, 16" Arzanah to IGD-E (KP-38) P/L, Laydown | 23 | 2023-05-09 | 2023-06-01 | 2023-07-08 | 2023-07-31 | 60
RISERS & J-TUBE INSTALLATION (BARGE EQV. TO DLB-1000) |  |  | 54 | 2023-08-10 | 2023-10-03 | 2023-10-10 | 2023-12-27 | 85
MOBILIZATION |  |  | 4 | 2023-08-10 | 2023-08-14 | 2023-10-10 | 2023-10-14 | 61
0 | OFCON3250 | Mobilization at Base | 3 | 2023-08-10 | 2023-08-13 | 2023-10-10 | 2023-10-13 | 61
0 | OFCON3310 | Sail to Site | 1 | 2023-08-13 | 2023-08-14 | 2023-10-13 | 2023-10-14 | 61
RISERS & J-TUBE INSTALLATION |  |  | 47 | 2023-08-14 | 2023-09-30 | 2023-10-14 | 2023-12-14 | 75
0 | OFCON4070 | Move & setup at HD-3 west face, Install 1No. 12" Riser & 1 No 24" J Tube | 7 | 2023-08-14 | 2023-08-21 | 2023-10-14 | 2023-10-21 | 61
0 | OFCON4380 | Readjust Anchor to HD WHP T4 east face, Install 1No. 12" Riser | 6 | 2023-08-21 | 2023-08-27 | 2023-10-21 | 2023-10-27 | 61
0 | OFCON4200 | Move & setup at HD WHP T4 west face, Install 1No.16" Riser | 6 | 2023-08-27 | 2023-09-02 | 2023-10-27 | 2023-11-02 | 61
0 | OFCON3730 | Move & setup at IGD-E, South face, Install 1No. 24" riser & 2 Nos 16" J Tube | 8 | 2023-09-02 | 2023-09-10 | 2023-11-02 | 2023-11-10 | 61
0 | OFCON3840 | Move setup BH03, West face, Install 1No. 16" Riser | 6 | 2023-09-10 | 2023-09-16 | 2023-11-24 | 2023-11-30 | 75
0 | OFCON4000 | Move & setup at Satah WHP-10 east face, Install 1No. 14" Riser | 6 | 2023-09-16 | 2023-09-22 | 2023-11-30 | 2023-12-06 | 75
0 | OFCON3320 | Move to KP51.0 for PL-6 location, midline tie-in for 6"P/L & FOC cable | 8 | 2023-09-22 | 2023-09-30 | 2023-12-06 | 2023-12-14 | 75
DEMOBILIZATION |  |  | 3 | 2023-09-30 | 2023-10-03 | 2023-12-24 | 2023-12-27 | 85
0 | OFCON4470 | Sail to Base | 1 | 2023-09-30 | 2023-10-01 | 2023-12-24 | 2023-12-25 | 85
0 | OFCON4480 | Demob at Base | 2 | 2023-10-01 | 2023-10-03 | 2023-12-25 | 2023-12-27 | 85
POST LAY CORRECTION FOR PIPELINES, UMBILICAL AND CABLES |  |  | 167 | 2023-10-13 | 2024-03-28 | 2023-12-27 | 2024-05-21 | 54
MOBILIZATION |  |  | 5 | 2023-10-13 | 2023-10-18 | 2023-12-27 | 2024-01-01 | 75
0 | OFCON3390 | Mobilization at Base | 3 | 2023-10-13 | 2023-10-16 | 2023-12-27 | 2023-12-30 | 75
0 | OFCON3440 | Sail to Site | 2 | 2023-10-16 | 2023-10-18 | 2023-12-30 | 2024-01-01 | 75
GROUT BAG/ FREE SPAN CORRECTION INSTALLATION FOR PIPELINE |  |  | 39 | 2023-10-18 | 2023-11-26 | 2024-01-01 | 2024-02-09 | 75
12" PL-2 Pipeline, HD-3 to HD WHP T4 |  |  | 4 | 2023-10-18 | 2023-10-22 | 2024-01-01 | 2024-01-05 | 75
0 | OFCON3710 | Grout bags installation for PL-2 '12" P/L Crossings (4 No.) | 2 | 2023-10-18 | 2023-10-20 | 2024-01-01 | 2024-01-03 | 75
0 | OFCON3720 | Support Installation for Span Correction (5 Nos.) | 2 | 2023-10-20 | 2023-10-22 | 2024-01-03 | 2024-01-05 | 75
14" PL-3 Pipeline, HD WHP T4 to Arzanah Island |  |  | 11 | 2023-10-22 | 2023-11-02 | 2024-01-05 | 2024-01-16 | 75
0 | OFCON3560 | Grout bags installation for PL-3 16" P/L Crossings (8 No.) | 4 | 2023-10-22 | 2023-10-26 | 2024-01-05 | 2024-01-09 | 75
0 | OFCON3600 | Support Installation for Span Correction (12 Nos.) | 6 | 2023-10-26 | 2023-11-01 | 2024-01-09 | 2024-01-15 | 75
0 | OFCON3680 | Mattresses Installation for Buckle Mitigation (12 Nos.) | 1 | 2023-11-01 | 2023-11-02 | 2024-01-15 | 2024-01-16 | 75
24" PL-5 Pipeline, Arzanah Island to IGD-E. |  |  | 2 | 2023-11-02 | 2023-11-04 | 2024-01-16 | 2024-01-18 | 75
0 | OFCON3900 | Grout bags installation for PL-5 '24" P/L Crossings (2 No.) | 1 | 2023-11-02 | 2023-11-03 | 2024-01-16 | 2024-01-17 | 75
0 | OFCON3940 | Support Installation for Span Correction (1 No.) | 1 | 2023-11-03 | 2023-11-04 | 2024-01-17 | 2024-01-18 | 75
16" PL-4 Pipeline, BH WHP-3 to Arzanah Island |  |  | 10 | 2023-11-04 | 2023-11-14 | 2024-01-18 | 2024-01-28 | 75
0 | OFCON3970 | Grout bags installation for PL-4 '16" P/L Crossings (6 No.) | 3 | 2023-11-04 | 2023-11-07 | 2024-01-18 | 2024-01-21 | 75
0 | OFCON4020 | Grout bags installation for Free Span Correction (12 Nos.) | 6 | 2023-11-07 | 2023-11-13 | 2024-01-21 | 2024-01-27 | 75
0 | OFCON4100 | Mattresses Installation for Buckle Mitigation (12 Nos.) | 1 | 2023-11-13 | 2023-11-14 | 2024-01-27 | 2024-01-28 | 75
14" PL-1 Pipeline, Satah WHP-10 to Arzanah Island |  |  | 6 | 2023-11-14 | 2023-11-20 | 2024-01-28 | 2024-02-03 | 75
0 | OFCON4120 | Grout bags installation for PL-1 '14" P/L Crossings (8 No.) | 4 | 2023-11-14 | 2023-11-18 | 2024-01-28 | 2024-02-01 | 75
0 | OFCON4210 | Grout bags installation for Free Span Correction (2 Nos.) | 1 | 2023-11-18 | 2023-11-19 | 2024-02-01 | 2024-02-02 | 75
0 | OFCON4250 | Mattresses Installation for Buckle Mitigation (12 Nos.) | 1 | 2023-11-19 | 2023-11-20 | 2024-02-02 | 2024-02-03 | 75
6" PL-6 Pipeline, Arzanah Island to Zirku Island. |  |  | 6 | 2023-11-20 | 2023-11-26 | 2024-02-03 | 2024-02-09 | 75
0 | OFCON3460 | Grout bags installation for PL-6 ' 6" P/L Crossings (10 No.) | 4 | 2023-11-20 | 2023-11-24 | 2024-02-03 | 2024-02-07 | 75
0 | OFCON3510 | Support Installation for Span Correction (4 Nos.) | 2 | 2023-11-24 | 2023-11-26 | 2024-02-07 | 2024-02-09 | 75
POST LAY CORRECTION FOR UMBILICAL |  |  | 1 | 2024-03-18 | 2024-03-19 | 2024-04-15 | 2024-04-16 | 28
0 | OFCON4280 | corrections of UC-2, Umbilical from HD WHP T4 to HD-3 (1.244 Kms.) | 1 | 2024-03-18 | 2024-03-19 | 2024-04-15 | 2024-04-16 | 28
FREE SPAN CORRECTION FOR UMBILICAL & CABLES |  |  | 119 | 2023-11-26 | 2024-03-24 | 2024-02-09 | 2024-04-21 | 28
0 | OFCON4490 | Free span correction (3 Nos. for each Cable, 6 Nos.) of CC-1, Composite cable (2 No.)from Arzanah to IGD-E (33.534 Kms.) | 3 | 2023-11-26 | 2023-11-29 | 2024-02-09 | 2024-02-12 | 75
0 | OFCON4340 | Free span correction (3 Nos.) of UC-1, Umbilical from Arzanah Island to Satah WHP-10 (17.529 Kms.) | 2 | 2023-11-29 | 2023-12-01 | 2024-02-12 | 2024-02-14 | 75
0 | OFCON4420 | Free span correction (7 Nos.) of UC-4, Umbilical from Arzanah Island to BH WHP-3 (48.816 Kms.) | 3 | 2023-12-01 | 2023-12-04 | 2024-02-14 | 2024-02-17 | 75
0 | OFCON4350 | Free span correction (3 Nos.) of UC-2, Umbilical from HD WHP T4 to HD-3 (1.244 Kms.) | 2 | 2024-03-19 | 2024-03-21 | 2024-04-16 | 2024-04-18 | 28
0 | OFCON4390 | Free span correction (5 Nos.) of UC-3, Umbilical from Arzanah Island to HD WHP T4 (34.92 Kms.) | 3 | 2024-03-21 | 2024-03-24 | 2024-04-18 | 2024-04-21 | 28
STABILIZATION OF UMBILICALS (USING CONCRETE BLOCKS) |  |  | 112 | 2023-12-04 | 2024-03-25 | 2024-02-17 | 2024-05-10 | 46
0 | OFCON4950 | Install 130 No. Conc. Blocks for Stabilization of CC-1 Composite Cable from Arzanah Island to IGD-E (33.534 Kms.) | 11 | 2023-12-04 | 2023-12-15 | 2024-02-17 | 2024-02-28 | 75
0 | OFCON5080 | 'Grout bags below J-Tubes / Risers (4Nos.) | 5 | 2023-12-15 | 2023-12-20 | 2024-02-28 | 2024-03-04 | 75
0 | OFCON4530 | Install 44 # Conc Blocks for Stabiliz'n /4 # Conc Block for 2# Cable Crossing of UC-1 Umbilical Arzanah to WHP-10-17.5 K | 4 | 2023-12-20 | 2023-12-24 | 2024-03-04 | 2024-03-08 | 75
0 | OFCON4740 | Inst'l 124# Conc Block for Stabiliz'n,8# Conc Block for 4# Cable Crossing of UC-4 Umbilical Arzanah to BH WHP-3-48.8K | 11 | 2023-12-24 | 2024-01-04 | 2024-03-08 | 2024-03-19 | 75
0 | OFCON4600 | Install 4Nos. Concrete blocks for 2 No. Cable Crossings of UC-2 Umbilical HD WHP T4 to HD-3 | 1 | 2024-03-18 | 2024-03-19 | 2024-04-18 | 2024-04-19 | 31
0 | OFCON4630 | Install 52 # Conc Block for Stabiliz'n,10#Conc. Block for 5#Cable Crossing of UC-3 Umbilical Arzanah to HD WHP T4 -34.9K | 6 | 2024-03-19 | 2024-03-25 | 2024-05-04 | 2024-05-10 | 46
DEMOBILIZATION |  |  | 3 | 2024-03-25 | 2024-03-28 | 2024-05-18 | 2024-05-21 | 54
0 | OFCON5150 | Sail to Base | 1 | 2024-03-25 | 2024-03-26 | 2024-05-18 | 2024-05-19 | 54
0 | OFCON5160 | Demob at Base | 2 | 2024-03-26 | 2024-03-28 | 2024-05-19 | 2024-05-21 | 54
SHORE PULL WORKS |  |  | 317 | 2022-10-28 | 2023-09-10 | 2023-01-06 | 2023-11-24 | 75
TRENCHING & BACKFILLING |  |  | 317 | 2022-10-28 | 2023-09-10 | 2023-01-06 | 2023-11-24 | 75
ARZANAH SOUTH |  |  | 225 | 2022-10-28 | 2023-06-10 | 2023-01-06 | 2023-08-24 | 75
MOBILIZATION |  |  | 9 | 2022-10-28 | 2022-11-06 | 2023-01-06 | 2023-01-15 | 70
0 | OFCON1430 | Mobilization at Base | 4 | 2022-10-28 | 2022-11-01 | 2023-01-06 | 2023-01-10 | 70
0 | OFCON1450 | Sail to Site | 5 | 2022-11-01 | 2022-11-06 | 2023-01-10 | 2023-01-15 | 70
ARZANAH SOUTH TRENCHING WORKS |  |  | 34 | 2022-11-06 | 2022-12-10 | 2023-01-15 | 2023-02-18 | 70
0 | OFCON1780 | Move to Arzanah (South) site & Set-Up (PL-3) | 4 | 2022-11-06 | 2022-11-10 | 2023-01-15 | 2023-01-19 | 70
0 | OFCON1830 | Onshore Trenching(4.5m wide ) (PL-3) | 30 | 2022-11-10 | 2022-12-10 | 2023-01-19 | 2023-02-18 | 70
ARZANAH SOUTH BACKFILLING WORKS |  |  | 32 | 2023-05-09 | 2023-06-10 | 2023-07-23 | 2023-08-24 | 75
0 | OFCON2540 | Move to Arzanah (South) site & Set-Up (PL-3) | 4 | 2023-05-09 | 2023-05-13 | 2023-07-23 | 2023-07-27 | 75
0 | OFCON2580 | Backfilling of Arzanah south Trench (PL-3) | 28 | 2023-05-13 | 2023-06-10 | 2023-07-27 | 2023-08-24 | 75
ARZANAH EAST |  |  | 274 | 2022-12-10 | 2023-09-10 | 2023-02-18 | 2023-11-24 | 75
ARZANAH EAST TRENCHING WORKS |  |  | 86 | 2022-12-10 | 2023-03-06 | 2023-02-18 | 2023-05-15 | 70
0 | OFCON1460 | Move to Arzanah (East) site & Set-Up (PL-1,PL-4, PL-5 & PL-6) | 6 | 2022-12-10 | 2022-12-16 | 2023-02-18 | 2023-02-24 | 70
0 | OFCON1470 | Onshore Trenching(17m wide ) (PL-1,PL-4, PL-5 & PL-6) | 80 | 2022-12-16 | 2023-03-06 | 2023-02-24 | 2023-05-15 | 70
ARZANAH EAST BACKFILLING WORKS |  |  | 84 | 2023-06-10 | 2023-09-02 | 2023-08-24 | 2023-11-16 | 75
0 | OFCON1980 | Move to Arzanah (East) site & Set-Up (PL-1,PL-4, PL-5 & PL-6) | 4 | 2023-06-10 | 2023-06-14 | 2023-08-24 | 2023-08-28 | 75
0 | OFCON2010 | Backfilling of Trench after completion of shorepull (PL-1,PL-4, PL-5 & PL-6) | 80 | 2023-06-14 | 2023-09-02 | 2023-08-28 | 2023-11-16 | 75
DEMOBILIZATION |  |  | 8 | 2023-09-02 | 2023-09-10 | 2023-11-16 | 2023-11-24 | 75
0 | OFCON2700 | Sail to Base | 4 | 2023-09-02 | 2023-09-06 | 2023-11-16 | 2023-11-20 | 75
0 | OFCON2710 | Demob at Base | 4 | 2023-09-06 | 2023-09-10 | 2023-11-20 | 2023-11-24 | 75
ZIRKU ISLAND |  |  | 184 | 2022-12-16 | 2023-06-18 | 2023-04-04 | 2023-11-24 | 159
MOBILIZATION |  |  | 7 | 2022-12-16 | 2022-12-23 | 2023-04-04 | 2023-04-11 | 109
0 | OFCON2360 | Mobilization at Base | 4 | 2022-12-16 | 2022-12-20 | 2023-04-04 | 2023-04-08 | 109
0 | OFCON2400 | Sail to Site | 3 | 2022-12-20 | 2022-12-23 | 2023-04-08 | 2023-04-11 | 109
ZIRKU ISLAND TRENCHING WORKS |  |  | 65 | 2022-12-23 | 2023-02-26 | 2023-04-11 | 2023-06-15 | 109
0 | OFCON2440 | Move to Zirku Island & Set-Up (PL-6) | 5 | 2022-12-23 | 2022-12-28 | 2023-04-11 | 2023-04-16 | 109
0 | OFCON2500 | Onshore Trenching works (2.0m wide ) (PL-6) | 60 | 2022-12-28 | 2023-02-26 | 2023-04-16 | 2023-06-15 | 109
ZIRKU ISLAND BACKFILLING WORKS |  |  | 44 | 2023-04-29 | 2023-06-12 | 2023-10-05 | 2023-11-18 | 159
0 | OFCON2810 | Backfilling of Trench (PL-6) | 39 | 2023-04-29 | 2023-06-07 | 2023-10-05 | 2023-11-13 | 159
0 | OFCON2900 | Demob of Equipments except Crane & Trailers (To be used for Hydrotest Spread) | 5 | 2023-06-07 | 2023-06-12 | 2023-11-13 | 2023-11-18 | 159
DEMOBILIZATION |  |  | 6 | 2023-06-12 | 2023-06-18 | 2023-11-18 | 2023-11-24 | 159
0 | OFCON2910 | Sail to Base | 3 | 2023-06-12 | 2023-06-15 | 2023-11-18 | 2023-11-21 | 159
0 | OFCON2940 | Demob at Base | 3 | 2023-06-15 | 2023-06-18 | 2023-11-21 | 2023-11-24 | 159
6 NO. SHOREPULL & LAY 6NO. PIPELINES AND COMPOSITE CABLES (DLB-750 ) |  |  | 56 | 2023-03-14 | 2023-05-09 | 2023-05-13 | 2023-07-08 | 60
SHORE PULL - PL 3 16" GAS |  |  | 10 | 2023-03-14 | 2023-03-24 | 2023-05-13 | 2023-05-23 | 60
0 | OFCON2770 | Move to Arzanah Island South shore approch and set up at KP 0.350 | 1 | 2023-03-14 | 2023-03-15 | 2023-05-13 | 2023-05-14 | 60
0 | OFCON2780 | Trench clearance, connect stinger and run messenger wire | 1 | 2023-03-15 | 2023-03-16 | 2023-05-14 | 2023-05-15 | 60
0 | OFCON2800 | Shore pull of 24" Conduit P/L (UC-3) & Continue laying upto 0.350 Km, Laydown | 3 | 2023-03-16 | 2023-03-19 | 2023-05-15 | 2023-05-18 | 60
0 | OFCON2820 | Readjust Anchor at Arzanah Island South shore approch | 1 | 2023-03-19 | 2023-03-20 | 2023-05-18 | 2023-05-19 | 60
0 | OFCON2850 | Shorepull of PL-3, 16" P/L lay upto 0.5 Km., Laydown & Recover Anchor | 4 | 2023-03-20 | 2023-03-24 | 2023-05-19 | 2023-05-23 | 60
SHORE PULL - PL 4 16" GAS |  |  | 10 | 2023-03-24 | 2023-04-03 | 2023-05-23 | 2023-06-02 | 60
0 | OFCON2460 | Move to Arzanah Island East shore approch and set up at 0.65 Km from LFP (KP 48.174) | 1 | 2023-03-24 | 2023-03-25 | 2023-05-23 | 2023-05-24 | 60
0 | OFCON2480 | Run messenger wire | 1 | 2023-03-25 | 2023-03-26 | 2023-05-24 | 2023-05-25 | 60
0 | OFCON2490 | Shore pull of PL-4, 16" P/L & Continue laying upto 1.2 Km , Laydown | 3 | 2023-03-26 | 2023-03-29 | 2023-05-25 | 2023-05-28 | 60
0 | OFCON2530 | Shore pull of 24" Conduit P/L (UC-4) & Continue laying upto 0.85 Km & Laydown | 5 | 2023-03-29 | 2023-04-03 | 2023-05-28 | 2023-06-02 | 60
SHORE PULL PL1 14" GAS |  |  | 13 | 2023-04-03 | 2023-04-16 | 2023-06-02 | 2023-06-15 | 60
0 | OFCON2330 | Move to Arzanah Island East shore approch and set up at 0.650 Km from LFP (KP 16.799) | 1 | 2023-04-03 | 2023-04-04 | 2023-06-02 | 2023-06-03 | 60
0 | OFCON2340 | Trench clearance, connect stinger and run messenger wire | 3 | 2023-04-04 | 2023-04-07 | 2023-06-03 | 2023-06-06 | 60
0 | OFCON2380 | Shore pull of PL-1, 14" P/l & Continue laying upto 1.2 Km, Laydown | 4 | 2023-04-07 | 2023-04-11 | 2023-06-06 | 2023-06-10 | 60
0 | OFCON2430 | Shore pull of 24" Conduit P/L (UC-1) & Continue laying upto 0.85 Km, Laydown | 5 | 2023-04-11 | 2023-04-16 | 2023-06-10 | 2023-06-15 | 60
SHORE PULL PL 6 - 6" CONDENSATE |  |  | 13 | 2023-04-16 | 2023-04-29 | 2023-06-15 | 2023-06-28 | 60
0 | OFCON2640 | Move to Arzanah Island East shore approch & set up at 0.65 Km from LFP | 1 | 2023-04-16 | 2023-04-17 | 2023-06-15 | 2023-06-16 | 60
0 | OFCON5800 | Shore pull of 6" PL-6 P/L with 2 No. FO Cable | 4 | 2023-04-17 | 2023-04-21 | 2023-06-16 | 2023-06-20 | 60
0 | OFCON2730 | Move to Zirku Island shore approch and set up at 0.850 Km from LFP | 1 | 2023-04-21 | 2023-04-22 | 2023-06-20 | 2023-06-21 | 60
0 | OFCON2740 | Trench clearance, connect stinger and run messenger wire | 2 | 2023-04-22 | 2023-04-24 | 2023-06-21 | 2023-06-23 | 60
0 | OFCON2750 | Shore pull of PL-6, 6" continue laying upto KP51.0, P/L length 1.4Km & Laydown | 5 | 2023-04-24 | 2023-04-29 | 2023-06-23 | 2023-06-28 | 60
SHORE PULL PL 5 - 24" GAS EXPORT |  |  | 10 | 2023-04-29 | 2023-05-09 | 2023-06-28 | 2023-07-08 | 60
0 | OFCON2560 | Move to Arzanah Island East shore approch & set up at 0.65 Km from LFP | 1 | 2023-04-29 | 2023-04-30 | 2023-06-28 | 2023-06-29 | 60
0 | OFCON2590 | Shore pull of PL-5, 24" P/L & Continue laying upto 1.2 Km, Laydown | 4 | 2023-04-30 | 2023-05-04 | 2023-06-29 | 2023-07-03 | 60
0 | OFCON2610 | Move to Arzanah Island East shore approch & set up at 0.65 Km from LFP | 1 | 2023-05-04 | 2023-05-05 | 2023-07-03 | 2023-07-04 | 60
0 | OFCON2630 | Shore pull of 12" Conduit P/L (CC-1) & Continue laying upto 0.85 Km & Laydown | 4 | 2023-05-05 | 2023-05-09 | 2023-07-04 | 2023-07-08 | 60
UMBILICALS & COMPOSITE CABLE |  |  | 196 | 2023-09-07 | 2024-03-22 | 2023-11-04 | 2024-05-21 | 60
UMBILICAL INSTALLATION INCLUDING SHORE PULL (BARGE EQV. TO DLB-1000) |  |  | 169 | 2023-10-05 | 2024-03-22 | 2023-11-04 | 2024-05-21 | 60
MOBILIZATION |  |  | 23 | 2023-10-05 | 2023-10-28 | 2023-11-04 | 2023-11-27 | 30
0 | OFCON3000 | Mobilization at Base | 6 | 2023-10-05 | 2023-10-11 | 2023-11-04 | 2023-11-10 | 30
0 | OFCON3080 | Preparation for Umbilicals transfer, transfer of 4 No. Umbilicals, Spares, Aids etc & Testing | 16 | 2023-10-11 | 2023-10-27 | 2023-11-10 | 2023-11-26 | 30
0 | OFCON3330 | Sail to Site | 1 | 2023-10-27 | 2023-10-28 | 2023-11-26 | 2023-11-27 | 30
UC-1 UMBILICAL INSTALLATION ARZANAH TO SATAH WHP-10 |  |  | 12 | 2023-10-28 | 2023-11-09 | 2023-11-27 | 2023-12-09 | 30
0 | OFCON3480 | Move & Set-up at Arzanah Island at KP 0.9, Connect Messenger wire for inst'n of UC-1 Umbilical (Arzanah to Satah WHP-10) | 1 | 2023-10-28 | 2023-10-29 | 2023-11-27 | 2023-11-28 | 30
0 | OFCON3490 | Shorepull Umbilical through Conduit pipe (Trench) | 4 | 2023-10-29 | 2023-11-02 | 2023-11-28 | 2023-12-02 | 30
0 | OFCON3550 | Lay UC-1 Umbilical (17.529 Kms) inclu'n inst'n of Ballast before/ after Crossings, J-Tube entry and Uraduct on Crossing | 4 | 2023-11-02 | 2023-11-06 | 2023-12-02 | 2023-12-06 | 30
0 | OFCON3590 | Lay down Umbilicals at Satah WHP-10 | 1 | 2023-11-06 | 2023-11-07 | 2023-12-06 | 2023-12-07 | 30
0 | OFCON3610 | Pull Umbilical through J-Tube, fix Umbilical on top & Testing | 2 | 2023-11-07 | 2023-11-09 | 2023-12-07 | 2023-12-09 | 30
UC-4 UMBILICAL INSTALLATION ARZANAH TO BH WHP-3 |  |  | 18 | 2023-11-09 | 2023-11-27 | 2023-12-09 | 2023-12-27 | 30
0 | OFCON3860 | Move & Set-up at Arzanah Island at KP 0.85 Connect Messenger wire for UC-4 Umbilical Inst'nn Arzanah Island to BH WHP-3 | 1 | 2023-11-09 | 2023-11-10 | 2023-12-09 | 2023-12-10 | 30
0 | OFCON3890 | Shorepull Umbilical through Conduit pipe (Trench) | 4 | 2023-11-10 | 2023-11-14 | 2023-12-10 | 2023-12-14 | 30
0 | OFCON4010 | Lay UC-4 Umbilical (48.816 Kms) including Ballast before & after Crossing & @J-Tube entry and Uraduct on Crossings | 10 | 2023-11-14 | 2023-11-24 | 2023-12-14 | 2023-12-24 | 30
0 | OFCON4170 | Lay down Umbilical at BH WHP-3 | 1 | 2023-11-24 | 2023-11-25 | 2023-12-24 | 2023-12-25 | 30
0 | OFCON4180 | Pull Umbilical through J-Tube, fix Umbilical on top & Testing | 2 | 2023-11-25 | 2023-11-27 | 2023-12-25 | 2023-12-27 | 30
UC-3 UMBILICAL INSTALLATION ARZANAH TO HAIR DALMA WHP HD-T4 |  |  | 15 | 2024-02-25 | 2024-03-11 | 2024-03-24 | 2024-04-08 | 28
0 | OFCON3630 | Move & Set-up at Arzanah @ KP 0.5, Connect Messenger wire for UC-3 Umbilical Inst'n Arzanah Island to HD WHP T4 | 1 | 2024-02-25 | 2024-02-26 | 2024-03-24 | 2024-03-25 | 28
0 | OFCON3650 | Shorepull Umbilical through Conduit pipe (Trench) | 3 | 2024-02-26 | 2024-02-29 | 2024-03-25 | 2024-03-28 | 28
0 | OFCON3700 | Lay UC-3 Umbilical (34.92 Kms) include'g Ballast before & after Crossing, @ J-Tube entry and Uraduct on Crossings | 8 | 2024-02-29 | 2024-03-08 | 2024-03-28 | 2024-04-05 | 28
0 | OFCON3780 | Lay down Umbilical at HD WHP T4 | 1 | 2024-03-08 | 2024-03-09 | 2024-04-05 | 2024-04-06 | 28
0 | OFCON3820 | Pull Umbilical through J-Tube, fix Umbilical on top & Testing | 2 | 2024-03-09 | 2024-03-11 | 2024-04-06 | 2024-04-08 | 28
UC-2 UMBILICAL INSTALLATION WHP T4 TO HAIR DALMA HD-03 |  |  | 7 | 2024-03-11 | 2024-03-18 | 2024-04-08 | 2024-04-15 | 28
0 | OFCON3350 | Move & Set-up at HD WHP T4, Prepration for UC-2 Umbilical Installation WHP T4 to HD-3 | 1 | 2024-03-11 | 2024-03-12 | 2024-04-08 | 2024-04-09 | 28
0 | OFCON3370 | Pull Umbilical through J-Tube & fix Umbilical on top | 2 | 2024-03-12 | 2024-03-14 | 2024-04-09 | 2024-04-11 | 28
0 | OFCON3400 | Lay UC-2 Umbilical (1.244 Kms) including Ballast before & after Crossing & at J-Tube entry and Uraduct on Crossings | 1 | 2024-03-14 | 2024-03-15 | 2024-04-11 | 2024-04-12 | 28
0 | OFCON3410 | Lay down Umbilical at HD-3 | 1 | 2024-03-15 | 2024-03-16 | 2024-04-12 | 2024-04-13 | 28
0 | OFCON3450 | Pull Umbilical through J-Tube, fix Umbilical on top & Testing | 2 | 2024-03-16 | 2024-03-18 | 2024-04-13 | 2024-04-15 | 28
DEMOBILIZATION |  |  | 4 | 2024-03-18 | 2024-03-22 | 2024-05-17 | 2024-05-21 | 60
0 | OFCON4240 | Sail to Base | 1 | 2024-03-18 | 2024-03-19 | 2024-05-17 | 2024-05-18 | 60
0 | OFCON4270 | Demob at Base | 3 | 2024-03-19 | 2024-03-22 | 2024-05-18 | 2024-05-21 | 60
COMPOSITE CABLE INSTALLATION (DLB-750 ) |  |  | 21 | 2023-09-07 | 2023-09-28 | 2023-11-05 | 2023-11-26 | 59
0 | OFCON3740 | Move to NPCC, MFY Transfer 1 no. Composite cable to DLB-750, Prepr'n for composite cable inst'n, & back to Arzanah | 5 | 2023-09-07 | 2023-09-12 | 2023-11-05 | 2023-11-10 | 59
0 | OFCON3830 | Move/Set-up at Arzanah @ KP 0.85 Connect Messenger wire for Composite Cable shore-pull through conduit | 1 | 2023-09-12 | 2023-09-13 | 2023-11-10 | 2023-11-11 | 59
0 | OFCON3850 | Shorepull Cable through Conduit pipe (Trench) | 3 | 2023-09-13 | 2023-09-16 | 2023-11-11 | 2023-11-14 | 59
0 | OFCON3920 | Lay Composite Cable CC-1 (33.534Kms)including Ballast before/after Crossing & @ J-Tube entry&Uraduct on Crossings | 6 | 2023-09-16 | 2023-09-22 | 2023-11-14 | 2023-11-20 | 59
0 | OFCON4060 | Pull 1st Composite Cable through J-Tube & Testing | 3 | 2023-09-22 | 2023-09-25 | 2023-11-20 | 2023-11-23 | 59
DEMOBILIZATION |  |  | 3 | 2023-09-25 | 2023-09-28 | 2023-11-23 | 2023-11-26 | 59
0 | OFCON4080 | Sail to Base | 1 | 2023-09-25 | 2023-09-26 | 2023-11-23 | 2023-11-24 | 59
0 | OFCON4090 | Demob at Base | 2 | 2023-09-26 | 2023-09-28 | 2023-11-24 | 2023-11-26 | 59
DECK INSTALLATION (DLS-4200 ) |  |  | 144 | 2023-10-23 | 2024-03-15 | 2023-11-21 | 2024-05-19 | 65
MOBILIZATION |  |  | 4 | 2023-10-23 | 2023-10-27 | 2023-11-21 | 2023-11-25 | 30
0 | OFCON3010 | Mobilization at Base | 3 | 2023-10-23 | 2023-10-26 | 2023-11-21 | 2023-11-24 | 30
0 | OFCON3040 | Sail to Site | 1 | 2023-10-26 | 2023-10-27 | 2023-11-24 | 2023-11-25 | 30
INSTALLATION OF BU HASEER WHP BH-03 |  |  | 5 | 2023-10-27 | 2023-11-01 | 2023-11-25 | 2023-12-01 | 30
0 | OFCON3050 | Move and Set-up at BH WHP-3 | 1 | 2023-10-27 | 2023-10-28 | 2023-11-25 | 2023-11-26 | 30
0 | OFCON3070 | Lift & Install Deck - BH WHP-3 | 3 | 2023-10-28 | 2023-10-31 | 2023-11-26 | 2023-11-29 | 30
0 | OFCON3120 | Move away - BH WHP-3 | 1 | 2023-10-31 | 2023-11-01 | 2023-11-30 | 2023-12-01 | 30
INSTALLATION OFSATAH WHP-10 |  |  | 5 | 2023-11-01 | 2023-11-06 | 2023-12-01 | 2023-12-06 | 30
0 | OFCON3130 | Move and Set-up at Satah WHP-10 | 1 | 2023-11-01 | 2023-11-02 | 2023-12-01 | 2023-12-02 | 30
0 | OFCON3170 | Lift & Install Deck -WHP-10 | 3 | 2023-11-02 | 2023-11-05 | 2023-12-02 | 2023-12-05 | 30
0 | OFCON3200 | Move away, Recover anchor - WHP-10 | 1 | 2023-11-05 | 2023-11-06 | 2023-12-05 | 2023-12-06 | 30
INSTALLATION OFHAIR DALMA WHP HD-T4 |  |  | 6 | 2024-03-01 | 2024-03-07 | 2024-03-21 | 2024-03-27 | 20
0 | OFCON3270 | Move and Set-up at HD WHP T4 | 1 | 2024-03-01 | 2024-03-02 | 2024-03-21 | 2024-03-22 | 20
0 | OFCON3290 | Lift & Install Deck - HD WHP T4 | 4 | 2024-03-02 | 2024-03-06 | 2024-03-22 | 2024-03-26 | 20
0 | OFCON3340 | Move away & Demob - HD WHP T4 | 1 | 2024-03-06 | 2024-03-07 | 2024-03-26 | 2024-03-27 | 20
INSTALLATION OFHAIR DALMA HD-03 |  |  | 5 | 2024-03-07 | 2024-03-12 | 2024-03-28 | 2024-04-02 | 21
0 | OFCON3220 | Move and Set-up at HD-3 | 1 | 2024-03-07 | 2024-03-08 | 2024-03-28 | 2024-03-29 | 21
0 | OFCON3240 | Lift & Install Deck - HD-3 | 3 | 2024-03-08 | 2024-03-11 | 2024-03-29 | 2024-04-01 | 21
0 | OFCON3260 | Move away - HD-3 | 1 | 2024-03-11 | 2024-03-12 | 2024-04-01 | 2024-04-02 | 21
DEMOBILIZATION |  |  | 3 | 2024-03-12 | 2024-03-15 | 2024-05-16 | 2024-05-19 | 65
0 | OFCON3360 | Sail to Base | 1 | 2024-03-12 | 2024-03-13 | 2024-05-16 | 2024-05-17 | 65
0 | OFCON3380 | Demob at Base | 2 | 2024-03-13 | 2024-03-15 | 2024-05-17 | 2024-05-19 | 65
PRE-DRILLING HOOK-UP WORKS |  |  | 331 | 2023-09-04 | 2024-07-31 | 2023-10-20 | 2024-07-31 | 0
HOOK-UP WORKS |  |  | 209 | 2023-09-04 | 2024-03-31 | 2023-10-20 | 2024-04-21 | 21
MODIFICATION, HOOK-UP WORKS AT HAIR DALAM HD-03 & IGD -E TOWER (SEP-450) |  |  | 209 | 2023-09-04 | 2024-03-31 | 2023-10-20 | 2024-04-21 | 21
MOBILIZATION |  |  | 5 | 2023-09-04 | 2023-09-09 | 2023-10-20 | 2023-10-25 | 46
0 | OFCON2930 | Mobilization at Base | 3 | 2023-09-04 | 2023-09-07 | 2023-10-20 | 2023-10-23 | 46
0 | OFCON2960 | Sail to Site | 2 | 2023-09-07 | 2023-09-09 | 2023-10-23 | 2023-10-25 | 46
HAIR DALMA HD-03 (EXISTING)- DEMOLITION |  |  | 18 | 2023-09-09 | 2023-09-27 | 2023-10-25 | 2024-01-07 | 102
0 | OFCON2980 | Move and Set-up at HD-3 | 1 | 2023-09-09 | 2023-09-10 | 2023-10-25 | 2023-10-26 | 46
0 | OFCON2990 | Demolition of Existing Deck, Erect Stabbing guide HD-3, Including Lifting of demolish deck | 4 | 2023-09-10 | 2023-09-14 | 2023-10-26 | 2023-10-30 | 46
0 | OFCON3030 | Install Template, Drill & Grout 2 No. Skirt Piles (Provisional Sum) HD-3 | 6 | 2023-09-14 | 2023-09-20 | 2023-10-30 | 2023-11-05 | 46
0 | OFCON3100 | Inst'n of Walkway/ Conductor framing (EL+4.820), Drain drum platform (EL+7.30), Conductor access platform(EL+9.490) HD-3 | 6 | 2023-09-20 | 2023-09-26 | 2023-12-31 | 2024-01-06 | 102
0 | OFCON3210 | Jack-down and Move out HD-3 | 1 | 2023-09-26 | 2023-09-27 | 2024-01-06 | 2024-01-07 | 102
IGD - E TOWER (EXISTING) |  |  | 40 | 2023-09-27 | 2023-11-06 | 2024-01-07 | 2024-02-16 | 102
0 | OFCON3670 | Move and Set-up at IGD-E (KP-38) | 2 | 2023-09-27 | 2023-09-29 | 2024-01-07 | 2024-01-09 | 102
0 | OFCON3690 | Structural strenthening, Pipeline tie-in, E&I, Modification & Pre-commissioining works -IGD-E | 38 | 2023-09-29 | 2023-11-06 | 2024-01-09 | 2024-02-16 | 102
HAIR DALMA HD-03 (EXISTING) - HOOK-UP WORKS |  |  | 16 | 2024-03-15 | 2024-03-31 | 2024-04-05 | 2024-04-21 | 21
0 | OFCON3280 | Move and Set-up at HD-3 | 1 | 2024-03-15 | 2024-03-16 | 2024-04-05 | 2024-04-06 | 21
0 | OFCON3300 | Hook-up Works HD-3 | 15 | 2024-03-16 | 2024-03-31 | 2024-04-06 | 2024-04-21 | 21
MODIFICATION, HOOK-UP WORKS @ BH-03, WHP-10 & WHP HD T-04 (SEP-750) |  |  | 144 | 2023-10-31 | 2024-03-23 | 2023-12-02 | 2024-04-12 | 20
MOBILIZATION |  |  | 4 | 2023-10-31 | 2023-11-04 | 2023-12-02 | 2023-12-06 | 32
0 | OFCON3060 | Mobilization at Base | 3 | 2023-10-31 | 2023-11-03 | 2023-12-02 | 2023-12-05 | 32
0 | OFCON3110 | Sail to Site | 1 | 2023-11-03 | 2023-11-04 | 2023-12-05 | 2023-12-06 | 32
BU HASEER BH-03 |  |  | 16 | 2023-11-04 | 2023-11-20 | 2023-12-06 | 2023-12-22 | 32
0 | OFCON3150 | Move and Set-up at BH-03 | 1 | 2023-11-04 | 2023-11-05 | 2023-12-06 | 2023-12-07 | 32
0 | OFCON3180 | Hook-up Works BH-03 | 15 | 2023-11-05 | 2023-11-20 | 2023-12-07 | 2023-12-22 | 32
SATAH WHP-10 |  |  | 16 | 2023-11-29 | 2023-12-15 | 2023-12-31 | 2024-01-16 | 32
0 | OFCON3530 | Move and Set-up at Satah WHP-10 | 1 | 2023-11-29 | 2023-11-30 | 2023-12-31 | 2024-01-01 | 32
0 | OFCON3570 | Hook-up Works WHP-10 | 15 | 2023-11-30 | 2023-12-15 | 2024-01-01 | 2024-01-16 | 32
HAIR DALMA WHP HD-T4 |  |  | 16 | 2024-03-07 | 2024-03-23 | 2024-03-27 | 2024-04-12 | 20
0 | OFCON3960 | Move and Set-up at HD WHP T-04 | 1 | 2024-03-07 | 2024-03-08 | 2024-03-27 | 2024-03-28 | 20
0 | OFCON3990 | Hook-up Works WHP T-04 | 15 | 2024-03-08 | 2024-03-23 | 2024-03-28 | 2024-04-12 | 20
PRE-COMMISSIOINING |  |  | 161 | 2023-11-01 | 2024-04-10 | 2023-12-18 | 2024-06-25 | 76
PRE-COMMISSIONING WORKS AT HAIR DALAM HD-03 & IGD -E TOWER (SEP-450) |  |  | 161 | 2023-11-01 | 2024-04-10 | 2024-03-09 | 2024-05-21 | 41
IGD - E TOWER (EXISTING) |  |  | 20 | 2023-11-01 | 2023-11-21 | 2024-03-09 | 2024-03-29 | 129
0 | OFCON5870 | Pre-commissioining works -IGD-E | 20 | 2023-11-01 | 2023-11-21 | 2024-03-09 | 2024-03-29 | 129
0 | OFCON6080 | Pre-commissioining Subsea Cable -IGD-E | 7 | 2023-11-14 | 2023-11-21 | 2024-03-22 | 2024-03-29 | 129
HAIR DALMA HD-03 |  |  | 13 | 2024-03-25 | 2024-04-07 | 2024-04-18 | 2024-05-01 | 24
0 | OFCON5880 | Pre-Commissioning works HD-3 | 12 | 2024-03-25 | 2024-04-06 | 2024-04-18 | 2024-04-30 | 24
0 | OFCON6070 | Pre-commissioining of Umbilical UC-2 | 5 | 2024-04-01 | 2024-04-06 | 2024-04-25 | 2024-04-30 | 24
0 | OFCON3640 | Jack-down and Move out HD-3 | 1 | 2024-04-06 | 2024-04-07 | 2024-04-30 | 2024-05-01 | 24
DEMOBILIZATION |  |  | 3 | 2024-04-07 | 2024-04-10 | 2024-05-18 | 2024-05-21 | 41
0 | OFCON4680 | Sail to Base | 1 | 2024-04-07 | 2024-04-08 | 2024-05-18 | 2024-05-19 | 41
0 | OFCON4710 | Demob at Base | 2 | 2024-04-08 | 2024-04-10 | 2024-05-19 | 2024-05-21 | 41
PRE-COMMISSIONING WORKS @ BH-03, WHP-10 & WHP HD T-04 (SEP-750) |  |  | 140 | 2023-11-16 | 2024-04-04 | 2023-12-18 | 2024-04-26 | 22
BU HASEER BH-03 |  |  | 16 | 2023-11-16 | 2023-12-02 | 2023-12-18 | 2024-01-01 | 30
0 | OFCON5890 | Pre-commissioining Works BH-03 | 12 | 2023-11-16 | 2023-11-28 | 2023-12-18 | 2023-12-30 | 32
0 | OFCON3520 | Jack-down and Move out BH-03 | 1 | 2023-11-28 | 2023-11-29 | 2023-12-30 | 2023-12-31 | 32
0 | OFCON6040 | Pre-commissioining of Umbilical UC-4 (by Work Boat) | 5 | 2023-11-27 | 2023-12-02 | 2023-12-27 | 2024-01-01 | 30
SATAH WHP-10 |  |  | 13 | 2023-12-11 | 2023-12-24 | 2024-01-12 | 2024-02-01 | 39
0 | OFCON5900 | Pre-commissioining Works WHP-10 | 12 | 2023-12-11 | 2023-12-23 | 2024-01-12 | 2024-01-24 | 32
0 | OFCON6050 | Pre-commissioining of Umbilical UC-1 | 5 | 2023-12-18 | 2023-12-23 | 2024-01-26 | 2024-01-31 | 39
0 | OFCON3910 | Jack-down and Move out WHP-10 | 1 | 2023-12-23 | 2023-12-24 | 2024-01-31 | 2024-02-01 | 39
HAIR DALMA WHP HD-T4 |  |  | 13 | 2024-03-19 | 2024-04-01 | 2024-04-08 | 2024-04-21 | 20
0 | OFCON5910 | Pre-Commissioining Works WHP T-04 | 12 | 2024-03-19 | 2024-03-31 | 2024-04-08 | 2024-04-20 | 20
0 | OFCON6060 | Pre-commissioining of Umbilical UC-3 | 5 | 2024-03-26 | 2024-03-31 | 2024-04-15 | 2024-04-20 | 20
0 | OFCON4410 | Jack-down and Move out WHP T-04 | 1 | 2024-03-31 | 2024-04-01 | 2024-04-20 | 2024-04-21 | 20
DEMOBILIZATION-1 |  |  | 3 | 2024-04-01 | 2024-04-04 | 2024-04-23 | 2024-04-26 | 22
0 | OFCON4430 | Sail to Base | 1 | 2024-04-01 | 2024-04-02 | 2024-04-23 | 2024-04-24 | 22
0 | OFCON4450 | Demob at Base | 2 | 2024-04-02 | 2024-04-04 | 2024-04-24 | 2024-04-26 | 22
FLOODING, CLEANING, GAUGING & HYDRO TESTING OF 5 NO. PIPELINES |  |  | 124 | 2023-11-24 | 2024-03-27 | 2024-01-27 | 2024-06-25 | 90
FLOODING, CLEANING, GAUGING & HYDRO TESTING OF 5 NO. PIPELINES (HYDRO TEST VESSEL) |  |  | 118 | 2023-11-26 | 2024-03-23 | 2024-02-01 | 2024-05-21 | 59
MOBILIZATION |  |  | 5 | 2023-12-18 | 2023-12-23 | 2024-03-03 | 2024-03-08 | 76
0 | OFCON4140 | Mobilization at Base | 3 | 2023-12-18 | 2023-12-21 | 2024-03-03 | 2024-03-06 | 76
0 | OFCON4220 | Sail to Site | 2 | 2023-12-21 | 2023-12-23 | 2024-03-06 | 2024-03-08 | 76
FLOODING, CLEANING, GAUGING & HYDRO TESTING OF 5 NO. PIPELINES |  |  | 118 | 2023-11-26 | 2024-03-23 | 2024-02-01 | 2024-04-21 | 29
0 | OFCON4820 | Move and Set-up at BH WHP-3 & Preparatory works PL-4 | 3 | 2023-11-26 | 2023-11-29 | 2024-02-01 | 2024-02-04 | 67
0 | OFCON4880 | Receive Flooding, Cleaning, Gauging, Pigs & Monitor Hydrotest of PL4, 16" BH WHP-3 to Arzanah Island P/L, 48.824 kms. | 11 | 2023-11-29 | 2023-12-10 | 2024-02-05 | 2024-02-16 | 68
0 | OFCON5030 | Move and Set-up at IGD-E platform & Preparatory works PL-5 | 3 | 2023-12-10 | 2023-12-13 | 2024-02-16 | 2024-02-19 | 68
0 | OFCON5100 | Receive Flooding, Cleaning, Gauging, Pigs & Monitor Hydrotest of PL5, 24" Arzanah Island to IGD-E P/L, 33.503 kms | 10 | 2023-12-13 | 2023-12-23 | 2024-02-21 | 2024-03-02 | 70
0 | OFCON4290 | Move and Set-up at Satah WHP - 10 & Preparatory works PL-1 | 3 | 2023-12-23 | 2023-12-26 | 2024-03-08 | 2024-03-11 | 76
0 | OFCON4360 | Receive Flooding, Cleaning, Gauging, Pigs & Monitor Hydrotest of PL1, 14" Satah WHP-10 to Arzanah P/L, 17.5 kms | 8 | 2023-12-26 | 2024-01-03 | 2024-03-31 | 2024-04-08 | 96
0 | OFCON4610 | Move and Set-up at HD WHP T4 & Preparatory works PL-3 | 3 | 2024-03-08 | 2024-03-11 | 2024-04-08 | 2024-04-11 | 31
0 | OFCON4500 | Move and Set-up at HD-3 & Preparatory works PL-2 | 3 | 2024-03-16 | 2024-03-19 | 2024-04-13 | 2024-04-16 | 28
0 | OFCON4690 | Receive Flooding, Cleaning, Gauging, Pigs & Monitor Hydrotest of PL3, 16" HD WHP T4 to Arzanah P/L, 34.864 kms | 9 | 2024-03-11 | 2024-03-20 | 2024-04-12 | 2024-04-21 | 32
0 | OFCON4550 | Flood, Clean, Gauge & Hydrotest PL-2, 12" HD-3 to HD WHP T4 P/L, 1.179 kms. | 4 | 2024-03-19 | 2024-03-23 | 2024-04-16 | 2024-04-20 | 28
DEMOBILIZATION |  |  | 3 | 2024-03-20 | 2024-03-23 | 2024-05-18 | 2024-05-21 | 59
0 | OFCON5220 | Sail to Base | 1 | 2024-03-20 | 2024-03-21 | 2024-05-18 | 2024-05-19 | 59
0 | OFCON5260 | Demob at Base | 2 | 2024-03-21 | 2024-03-23 | 2024-05-19 | 2024-05-21 | 59
FLOODING, CLEANING, GAUGING & HYDRO TESTING OF 5 NO. PIPELINES (HYDRO TEST VESSEL)-1 |  |  | 124 | 2023-11-24 | 2024-03-27 | 2024-01-27 | 2024-05-21 | 55
MOBILIZATION |  |  | 5 | 2023-11-24 | 2023-11-29 | 2024-01-27 | 2024-02-01 | 64
0 | OFCON3790 | Mobilization at Base | 3 | 2023-11-24 | 2023-11-27 | 2024-01-27 | 2024-01-30 | 64
0 | OFCON3870 | Sail to Site | 2 | 2023-11-27 | 2023-11-29 | 2024-01-30 | 2024-02-01 | 64
FLOODING, CLEANING, GAUGING & HYDRO TESTING OF 5 NO. PIPELINES |  |  | 116 | 2023-11-29 | 2024-03-24 | 2024-02-01 | 2024-04-21 | 28
0 | OFCON4760 | Preparatory works for PL4, 16" P/L | 3 | 2023-11-29 | 2023-12-02 | 2024-02-01 | 2024-02-04 | 64
0 | OFCON4830 | Flood, Clean, Gauge & Hydrotest of PL4, 16" BH WHP-3 to Arzanah Island P/L , 48.824 kms. | 12 | 2023-12-02 | 2023-12-14 | 2024-02-04 | 2024-02-16 | 64
0 | OFCON5020 | Preparatory works for PL5, 24" P/L | 3 | 2023-12-14 | 2023-12-17 | 2024-02-16 | 2024-02-19 | 64
0 | OFCON5050 | Flood, Clean, Gauge & Hydrotest of PL5, 24" Arzanah Island to IGD-E P/L , 33.503 kms. | 12 | 2023-12-17 | 2023-12-29 | 2024-02-19 | 2024-03-02 | 64
0 | OFCON4300 | Preparatory works for PL1, 14" P/L | 3 | 2023-12-29 | 2024-01-01 | 2024-03-08 | 2024-03-11 | 70
0 | OFCON4370 | Flood, Clean, Gauge & Hydrotest PL1, 16" Satah WHP-10 to Arzanah Island P/L , 17.449 kms. | 8 | 2024-01-01 | 2024-01-09 | 2024-03-11 | 2024-03-19 | 70
0 | OFCON3950 | Move and Set-up at Arzanah Island East & Preparatory works for PL6, 6" P/L | 6 | 2024-01-09 | 2024-01-15 | 2024-03-19 | 2024-03-25 | 70
0 | OFCON4040 | Flood, Clean, Gauge & Hydrotest of PL6, 6" Arzanah Island to Zirku Island P/L, 52.406 kms. | 11 | 2024-02-06 | 2024-02-17 | 2024-03-25 | 2024-04-05 | 48
0 | OFCON4510 | Preparatory works for PL3, 16" P/L | 6 | 2024-03-08 | 2024-03-14 | 2024-04-05 | 2024-04-11 | 28
0 | OFCON4590 | Flood, Clean, Gauge & Hydrotest of PL3, 16" HD WHP T4 to Arzanah Island P/L , 34.864 kms. | 10 | 2024-03-14 | 2024-03-24 | 2024-04-11 | 2024-04-21 | 28
DEMOBILIZATION |  |  | 3 | 2024-03-24 | 2024-03-27 | 2024-05-18 | 2024-05-21 | 55
0 | OFCON5200 | Sail to Base | 1 | 2024-03-24 | 2024-03-25 | 2024-05-18 | 2024-05-19 | 55
0 | OFCON5230 | Demob at Base | 2 | 2024-03-25 | 2024-03-27 | 2024-05-19 | 2024-05-21 | 55
FLOODING, CLEANING, GAUGING & HYDRO TESTING OF PL6, 6" PIPELINE (ONSHORE SPREAD) |  |  | 28 | 2024-01-05 | 2024-02-02 | 2024-03-27 | 2024-06-25 | 144
MOBILIZATION |  |  | 4 | 2024-01-05 | 2024-01-09 | 2024-03-27 | 2024-03-31 | 82
0 | OFCON3760 | Mobilization at Base | 2 | 2024-01-05 | 2024-01-07 | 2024-03-27 | 2024-03-29 | 82
0 | OFCON3770 | Sail to Site | 2 | 2024-01-07 | 2024-01-09 | 2024-03-29 | 2024-03-31 | 82
FLOODING, CLEANING, GAUGING & HYDRO TESTING OF PL6, 6" PIPELINE |  |  | 21 | 2024-01-09 | 2024-01-30 | 2024-03-31 | 2024-04-21 | 82
0 | OFCON3800 | Move and Set-up at Zirku Island & Preparatory works | 6 | 2024-01-09 | 2024-01-15 | 2024-03-31 | 2024-04-06 | 82
0 | OFCON3980 | Flood, Clean, Gauge & Hydrotest PL6, 6" Arzanah Island to Zirku Island P/L, 52.406 kms. | 15 | 2024-01-15 | 2024-01-30 | 2024-04-06 | 2024-04-21 | 82
DEMOBILIZATION |  |  | 3 | 2024-01-30 | 2024-02-02 | 2024-06-22 | 2024-06-25 | 144
0 | OFCON4260 | Sail to Base | 1 | 2024-01-30 | 2024-01-31 | 2024-06-22 | 2024-06-23 | 144
0 | OFCON4310 | Demob at Base | 2 | 2024-01-31 | 2024-02-02 | 2024-06-23 | 2024-06-25 | 144
MISC. OFFSHORE WORKS ( CONTIGENCY) |  |  | 60 | 2023-09-29 | 2023-11-28 | 2023-11-02 | 2024-01-01 | 34
0 | OFCON6030 | MISC. OFFSHORE WORKS (CONTIGENCY) | 60 | 2023-09-29 | 2023-11-28 | 2023-11-02 | 2024-01-01 | 34
COMPANY DRILLING SCHEDULE |  |  | 212 | 2024-01-01 | 2024-07-31 | 2024-01-01 | 2024-07-31 | 0
0 | OFCON5570 | BU HASSER BH-03 DRILLING WORKS | 120 | 2024-01-01 | 2024-04-30 | 2024-01-01 | 2024-04-30 | 0
0 | OFCON5580 | SATAH WHP-10 DRILLING WORKS | 89 | 2024-02-01 | 2024-04-30 | 2024-02-01 | 2024-04-30 | 0
0 | OFCON5600 | HAIR DALMA HD-03 DRILLING WORKS | 60 | 2024-05-01 | 2024-06-30 | 2024-05-01 | 2024-06-30 | 0
0 | OFCON5590 | HAIR DALMA HD-T4 DRILLING WORKS | 91 | 2024-05-01 | 2024-07-31 | 2024-05-01 | 2024-07-31 | 0
POST DRILLING HOOK-WORKS |  |  | 280 | 2023-11-17 | 2024-08-23 | 2024-02-26 | 2024-09-20 | 28
COMMISSIONING & RFSU |  |  | 280 | 2023-11-17 | 2024-08-23 | 2024-02-26 | 2024-09-20 | 28
COMMISSIOINING @ IGD -E TOWER (SEP-450) |  |  | 11 | 2023-11-17 | 2023-11-28 | 2024-03-25 | 2024-04-05 | 129
0 | OFCON6130 | Commissioining works -IGD-E | 10 | 2023-11-17 | 2023-11-27 | 2024-03-25 | 2024-04-04 | 129
0 | OFCON4660 | Jack-down and Move out IGD-E | 1 | 2023-11-27 | 2023-11-28 | 2024-04-04 | 2024-04-05 | 129
COMMISSIONING & RFSU WORKS @ BH WHP-03 (SEP-750) |  |  | 29 | 2024-04-26 | 2024-05-25 | 2024-04-26 | 2024-07-21 | 57
MOBILIZATION |  |  | 5 | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2024-05-01 | 0
0 | OFCON5000 | Mobilization at Base | 3 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-04-29 | 0
0 | OFCON5040 | Sail to Site | 2 | 2024-04-29 | 2024-05-01 | 2024-04-29 | 2024-05-01 | 0
BU HASEER WHP BH-03 |  |  | 21 | 2024-05-01 | 2024-05-22 | 2024-05-01 | 2024-07-18 | 57
0 | OFCON5060 | Move and Set-up at BH WHP-03 | 1 | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2024-05-02 | 0
0 | OFCON5110 | Hook-up & Commissioning upto RFSU status BH WHP-03 | 19 | 2024-05-02 | 2024-05-21 | 2024-05-02 | 2024-05-21 | 0
0 | OFCON5650 | Complete Commission'g & Achievem't of RFSU for Bu Haseer(BH-03) WHT with pipeline, umbilical's & associated facilities | 0 |  | 2024-05-21 |  | 2024-05-21 | 0
0 | OFCON6090 | Commissioning Umbilical UC-4 | 7 | 2024-05-14 | 2024-05-21 | 2024-05-14 | 2024-05-21 | 0
0 | OFCON5320 | Jack-down and Move out BH WHP-03 | 1 | 2024-05-21 | 2024-05-22 | 2024-07-17 | 2024-07-18 | 57
DEMOBILIZATION |  |  | 3 | 2024-05-22 | 2024-05-25 | 2024-07-18 | 2024-07-21 | 57
0 | OFCON5450 | Sail to Base | 1 | 2024-05-22 | 2024-05-23 | 2024-07-18 | 2024-07-19 | 57
0 | OFCON5460 | Demob at Base | 2 | 2024-05-23 | 2024-05-25 | 2024-07-19 | 2024-07-21 | 57
COMMISSIONING & RFSU WORKS @ SATAH WHP-10 ( SEP-350) |  |  | 29 | 2024-04-26 | 2024-05-25 | 2024-04-26 | 2024-09-18 | 116
MOBILIZATION |  |  | 5 | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2024-05-01 | 0
0 | OFCON5820 | Mobilization at Base | 3 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-04-29 | 0
0 | OFCON5830 | Sail to Site | 2 | 2024-04-29 | 2024-05-01 | 2024-04-29 | 2024-05-01 | 0
SATAH WHP-10 |  |  | 21 | 2024-05-01 | 2024-05-22 | 2024-05-01 | 2024-07-18 | 57
0 | OFCON5860 | Move and Set-up at Satah WHP-10 | 1 | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2024-05-02 | 0
0 | OFCON5340 | Hook-up & Commissioning upto RFSU status Satah WHP-10 | 19 | 2024-05-02 | 2024-05-21 | 2024-05-02 | 2024-05-21 | 0
0 | OFCON5640 | Complete Commission'g & Achievement of RFSU for Satah(ST-10) WHT with new pipeline, umbilical's & associated facilities | 0 |  | 2024-05-21 |  | 2024-05-21 | 0
0 | OFCON6100 | Commissioning of Umbilical UC-1 | 7 | 2024-05-14 | 2024-05-21 | 2024-05-14 | 2024-05-21 | 0
0 | OFCON5440 | Jack-down and Move out Satah WHP-10 | 1 | 2024-05-21 | 2024-05-22 | 2024-07-17 | 2024-07-18 | 57
DEMOBILIZATION |  |  | 3 | 2024-05-22 | 2024-05-25 | 2024-09-15 | 2024-09-18 | 116
0 | OFCON5840 | Sail to Base | 1 | 2024-05-22 | 2024-05-23 | 2024-09-15 | 2024-09-16 | 116
0 | OFCON5850 | Demob at Base | 2 | 2024-05-23 | 2024-05-25 | 2024-09-16 | 2024-09-18 | 116
COMMISSIONING & RFSU WORKS @ HD-03 (EXISTING ) & HD-T4 ( SEP-350) |  |  | 59 | 2024-06-25 | 2024-08-23 | 2024-06-25 | 2024-09-20 | 28
MOBILIZATION |  |  | 5 | 2024-06-25 | 2024-06-30 | 2024-06-25 | 2024-06-30 | 0
0 | OFCON3470 | Mobilization at Base | 3 | 2024-06-25 | 2024-06-28 | 2024-06-25 | 2024-06-28 | 0
0 | OFCON3500 | Sail to Site | 2 | 2024-06-28 | 2024-06-30 | 2024-06-28 | 2024-06-30 | 0
HAIR DALMA HD-03 ( EXISTING) |  |  | 21 | 2024-06-30 | 2024-07-21 | 2024-06-30 | 2024-07-21 | 0
0 | OFCON3540 | Move and Set-up at HD-3 | 1 | 2024-06-30 | 2024-07-01 | 2024-06-30 | 2024-07-01 | 0
0 | OFCON3580 | Hook-up & Commissioning Works HD-3 | 19 | 2024-07-01 | 2024-07-20 | 2024-07-01 | 2024-07-20 | 0
0 | OFCON6110 | Commissioning of Umbilical UC-2 | 7 | 2024-07-13 | 2024-07-20 | 2024-07-13 | 2024-07-20 | 0
0 | OFCON3810 | Jack-down and Move out HD-3 | 1 | 2024-07-20 | 2024-07-21 | 2024-07-20 | 2024-07-21 | 0
0 | OFCON5660 | Complete Commission'g & Achievem't of RFSU for Hair Dalma (HD-03) WHT with pipeline, umbilical's & associated facilities | 0 |  | 2024-07-21 |  | 2024-07-21 | 0
HAIR DALMA WHP HD-T4 |  |  | 20 | 2024-07-31 | 2024-08-20 | 2024-08-28 | 2024-09-20 | 31
0 | OFCON4440 | Move and Set-up at HD WHP T4 | 1 | 2024-07-31 | 2024-08-01 | 2024-08-28 | 2024-08-29 | 28
0 | OFCON4460 | Hook-up & Commissioning WHP T4 | 18 | 2024-08-01 | 2024-08-19 | 2024-08-29 | 2024-09-16 | 28
0 | OFCON6120 | Commissioning of Umbilical UC-3 | 7 | 2024-08-12 | 2024-08-19 | 2024-09-09 | 2024-09-16 | 28
0 | OFCON4770 | Jack-down and Move out WHP T4 | 1 | 2024-08-19 | 2024-08-20 | 2024-09-16 | 2024-09-17 | 28
0 | OFCON5670 | Complete Commission'g & Achievem't of RFSU for Hair Dalma (HD-T4) WHT with pipeline, umbilical's & associated facilities | 0 |  | 2024-08-20 |  | 2024-09-20 | 31
DEMOBILIZATION |  |  | 3 | 2024-08-20 | 2024-08-23 | 2024-09-17 | 2024-09-20 | 28
0 | OFCON4780 | Sail to Base | 1 | 2024-08-20 | 2024-08-21 | 2024-09-17 | 2024-09-18 | 28
0 | OFCON4800 | Demob at Base | 2 | 2024-08-21 | 2024-08-23 | 2024-09-18 | 2024-09-20 | 28
PIGGING, BASELINE SURVEY, DEWATERING AND NITROGEN PACKING OF 5 NO. PIPELINES |  |  | 122 | 2023-12-17 | 2024-04-17 | 2024-02-26 | 2024-09-20 | 156
PIGGING, BASELINE SURVEY, DEWATERING AND NITROGEN PACKING - ARZANAH ISLAND (HYDRO TEST VESSEL) |  |  | 122 | 2023-12-17 | 2024-04-17 | 2024-03-04 | 2024-09-20 | 156
MOBILIZATION |  |  | 5 | 2024-03-18 | 2024-03-23 | 2024-06-12 | 2024-06-17 | 86
0 | OFCON4520 | Mobilization at Base | 3 | 2024-03-18 | 2024-03-21 | 2024-06-12 | 2024-06-15 | 86
0 | OFCON4560 | Sail to Site | 2 | 2024-03-21 | 2024-03-23 | 2024-06-15 | 2024-06-17 | 86
PIGGING, BASELINE SURVEY, DEWATERING AND NITROGEN PACKING - ARZANAH ISLAND |  |  | 122 | 2023-12-17 | 2024-04-17 | 2024-03-04 | 2024-09-20 | 156
0 | OFCON5120 | Move and Set-up at Arzanah Island & Preparatory works PL5 | 3 | 2023-12-17 | 2023-12-20 | 2024-03-04 | 2024-03-07 | 78
0 | OFCON5140 | Pigging,Caliper pigging,Baseline survey,Dewatering & Nitrogen Packing of PL5, 24" P/L Arzanah Island to IGD-E, 33.5 kms | 15 | 2023-12-20 | 2024-01-04 | 2024-03-07 | 2024-03-22 | 78
0 | OFCON5300 | Move and Set-up at BH WHP-3 & Preparatory works PL4 | 3 | 2024-01-04 | 2024-01-07 | 2024-04-17 | 2024-04-20 | 104
0 | OFCON5310 | Pigging,Caliper Pigging,Baseline survey,Dewatering & Nitrogen Packing of PL4, 16" P/L BH WHP-3 to Arzanah, 48.8 kms | 15 | 2024-01-07 | 2024-01-22 | 2024-04-20 | 2024-05-05 | 104
0 | OFCON5410 | Move and Set-up at Satah WHP - 10 & Preparatory works PL1 | 3 | 2024-01-22 | 2024-01-25 | 2024-05-05 | 2024-05-08 | 104
0 | OFCON5430 | Pigging,Caliper Pigging,Baseline survey,Dewatering & Nitrogen Packing of PL1, 14" P/L Satah WHP-10 to Arzanah,17.5 kms | 10 | 2024-01-25 | 2024-02-04 | 2024-05-08 | 2024-05-18 | 104
0 | OFCON4620 | Move and Set-up at HD-3 & Preparatory works PL2 | 3 | 2024-03-23 | 2024-03-26 | 2024-06-17 | 2024-06-20 | 86
0 | OFCON4700 | Pigging, Caliper Pigging, Baseline survey, Dewatering and Nitrogen Packing of PL2, 12" P/L HD-3 to HD WHP T4, 1.2 kms | 6 | 2024-03-26 | 2024-04-01 | 2024-06-20 | 2024-06-26 | 86
0 | OFCON4840 | Move and Set-up at HD WHP T4 & Preparatory works PL3 | 3 | 2024-04-01 | 2024-04-04 | 2024-06-26 | 2024-06-29 | 86
0 | OFCON4910 | Pigging,Caliper Pigging,Baseline survey,Dewatering & Nitrogen Packing of PL3, 16" P/L HD WHP T4 to Arzanah, 34.9 kms | 13 | 2024-04-04 | 2024-04-17 | 2024-09-07 | 2024-09-20 | 156
DEMOBILIZATION |  |  | 3 | 2024-02-04 | 2024-02-07 | 2024-05-18 | 2024-05-21 | 104
0 | OFCON5490 | Sail to Base | 1 | 2024-02-04 | 2024-02-05 | 2024-05-18 | 2024-05-19 | 104
0 | OFCON5520 | Demob at Base | 2 | 2024-02-05 | 2024-02-07 | 2024-05-19 | 2024-05-21 | 104
PIGGING, BASELINE SURVEY, DEWATERING AND NITROGEN PACKING - ARZANAH ISLAND (SOUTH & EAST) |  |  | 115 | 2023-12-24 | 2024-04-17 | 2024-02-26 | 2024-07-12 | 86
MOBILIZATION |  |  | 5 | 2023-12-24 | 2023-12-29 | 2024-02-26 | 2024-03-02 | 64
0 | OFCON4150 | Mobilization at Base | 3 | 2023-12-24 | 2023-12-27 | 2024-02-26 | 2024-02-29 | 64
0 | OFCON4230 | Sail to Site | 2 | 2023-12-27 | 2023-12-29 | 2024-02-29 | 2024-03-02 | 64
PIGGING, BASELINE SURVEY, DEWATERING AND NITROGEN PACKING - ARZANAH ISLAND |  |  | 110 | 2023-12-29 | 2024-04-17 | 2024-03-02 | 2024-07-12 | 86
0 | OFCON5250 | Preparatory works PL-5 | 3 | 2023-12-29 | 2024-01-01 | 2024-03-02 | 2024-03-05 | 64
0 | OFCON5270 | Pigging, Baseline survey, Dewatering and Nitrogen Packing of 24" P/L Arzanah Island to IGD-E, 33.503 kms.PL-5 | 15 | 2024-01-01 | 2024-01-16 | 2024-03-05 | 2024-03-20 | 64
0 | OFCON5380 | Preparatory works PL-4 | 3 | 2024-01-16 | 2024-01-19 | 2024-03-20 | 2024-03-23 | 64
0 | OFCON5390 | Pigging, Baseline survey, Dewatering and Nitrogen Packing of 16" P/L BH WHP-3 to Arzanah Island, 48.824 kms. PL-4 | 16 | 2024-01-19 | 2024-02-04 | 2024-03-23 | 2024-04-08 | 64
0 | OFCON5470 | Preparatory works PL-1 | 3 | 2024-02-04 | 2024-02-07 | 2024-04-08 | 2024-04-11 | 64
0 | OFCON5530 | Pigging, Baseline survey, Dewatering and Nitrogen Packing of 14" P/L Satah WHP-10 to Arzanah Island, 17.449 kms. PL-1 | 10 | 2024-02-07 | 2024-02-17 | 2024-04-11 | 2024-04-21 | 64
0 | OFCON4320 | Move and Set-up at Arzanah Island east & preparatory works PL6 | 7 | 2024-02-17 | 2024-02-24 | 2024-04-21 | 2024-04-28 | 64
0 | OFCON4570 | Pigging, Baseline survey, Dewatering and Nitrogen Packing of 6" P/L Arzanah Island to Zirku Island, 52.406 kms. PL-6 | 14 | 2024-02-24 | 2024-03-09 | 2024-05-04 | 2024-05-18 | 70
0 | OFCON4850 | Move and Set-up at Arzanah South PL3 | 6 | 2024-03-29 | 2024-04-04 | 2024-06-23 | 2024-06-29 | 86
0 | OFCON4970 | Pigging, Baseline survey, Dewatering and Nitrogen Packing of 16" P/L HD WHP T4 to Arzanah Island, 34.864 kms. PL3 | 13 | 2024-04-04 | 2024-04-17 | 2024-06-29 | 2024-07-12 | 86
DEMOBILIZATION |  |  | 3 | 2024-03-09 | 2024-03-12 | 2024-05-18 | 2024-05-21 | 70
0 | OFCON5550 | Sail to Base | 1 | 2024-03-09 | 2024-03-10 | 2024-05-18 | 2024-05-19 | 70
0 | OFCON5560 | Demob at Base | 2 | 2024-03-10 | 2024-03-12 | 2024-05-19 | 2024-05-21 | 70
PIGGING, BASELINE SURVEY, DEWATERING AND NITROGEN PACKING (ONSHORE TEST SPREAD) |  |  | 39 | 2024-02-12 | 2024-03-22 | 2024-04-16 | 2024-07-21 | 121
MOBILIZATION |  |  | 5 | 2024-02-12 | 2024-02-17 | 2024-04-16 | 2024-04-21 | 64
0 | OFCON4160 | Mobilization at Base | 2 | 2024-02-12 | 2024-02-14 | 2024-04-16 | 2024-04-18 | 64
0 | OFCON4190 | Sail to Site | 3 | 2024-02-14 | 2024-02-17 | 2024-04-18 | 2024-04-21 | 64
PIGGING, BASELINE SURVEY, DEWATERING AND NITROGEN PACKING |  |  | 30 | 2024-02-17 | 2024-03-18 | 2024-04-21 | 2024-05-21 | 64
0 | OFCON4330 | Move and Set-up at Arzanah Island & Preparatory works | 5 | 2024-02-17 | 2024-02-22 | 2024-04-21 | 2024-04-26 | 64
0 | OFCON4400 | Pigging, Bseline survey, Dewatering and Nitrogen Packing of 6" P/L Arzanah Island to Zirku Island, 52.406 kms. PL-6 | 25 | 2024-02-22 | 2024-03-18 | 2024-04-26 | 2024-05-21 | 64
DEMOBILIZATION |  |  | 4 | 2024-03-18 | 2024-03-22 | 2024-07-17 | 2024-07-21 | 121
0 | OFCON1000 | Sail to Base | 2 | 2024-03-18 | 2024-03-20 | 2024-07-17 | 2024-07-19 | 121
0 | OFCON1010 | Demob at Base | 2 | 2024-03-20 | 2024-03-22 | 2024-07-19 | 2024-07-21 | 121
PROVISIONAL ACCEPTANCE CERTIFICATE (PAC) |  |  | 181 | 2024-08-23 | 2025-02-20 | 2024-09-22 | 2025-03-22 | 31
0 | OFCON5680 | Complete Test Run and Achieve Provisional Acceptance Certificate (PAC) for all WHT's,Pipelines & Umbilicals | 181 | 2024-08-23 | 2025-02-20 | 2024-09-22 | 2025-03-22 | 31
AS BUILT & FINAL DOCUMENTATION |  |  | 164 | 2023-12-25 | 2024-08-20 | 2024-01-24 | 2024-09-19 | 21
0 | OFCON5930 | Instrumentation & Control - As-Built Documents | 150 | 2023-12-25 | 2024-07-31 | 2024-01-24 | 2024-08-29 | 21
0 | OFCON5940 | Electrical - As-Built Documents | 150 | 2023-12-25 | 2024-07-31 | 2024-01-24 | 2024-08-29 | 21
0 | OFCON5950 | Civil / Structural - As-Built Documents | 150 | 2023-12-25 | 2024-07-31 | 2024-01-24 | 2024-08-29 | 21
0 | OFCON5960 | Piping - As-Built Documents | 150 | 2023-12-25 | 2024-07-31 | 2024-01-24 | 2024-08-29 | 21
0 | OFCON5970 | Mechanical - As-Built Documents | 150 | 2023-12-25 | 2024-07-31 | 2024-01-24 | 2024-08-29 | 21
0 | OFCON5980 | Process - As-Built Documents | 150 | 2023-12-25 | 2024-07-31 | 2024-01-24 | 2024-08-29 | 21
0 | OFCON6000 | Pipeline / Umbilical & Composite Cable - As-Built Documents | 150 | 2023-12-25 | 2024-07-31 | 2024-01-24 | 2024-08-29 | 21
0 | OFCON5920 | Final Project Dossier Handover | 150 | 2024-01-15 | 2024-08-20 | 2024-02-14 | 2024-09-19 | 21

## Data_List_Final_03 (hidden)
EPC FOR DALMA GAS DEVELOPMENT PROJECT PACKAGE-A (OFFSHORE FACILITIES)
PROJECT DELIVERABLES REGISTER
COMPANY Project No. |  |  |  |  | COMPANY DOC. No. CA0000-59-REG-0001 |  |  | REV
P4331432
CONTRACTOR Project No. |  |  |  |  | CONTRACTOR DOC. No. 8405-PP-GE-001 |  |  | 03
8405
SECTION | COMPANY DOCUMENT No. | ID2 | ID4 | ID5 | CONTRACTOR DOCUMENT No. | TITLE / DESCRIPTION | DOCUMENT CLASS | PLANNED ISSUANCE DATE | DOCUMENT CLASS
A | PROJECT MANAGEMENT | [11 empty] | -56 | 0 | 0
A.1 | PROJECT GENERAL | [11 empty] | 48 | 0 | 0
A.1.1 | CA0000-59-REG-0001 | GDVPJ1000 | GDVPJ1005 | GDVPJ1010 | 8405-PP-GE-001 | PROJECT DELIVERABLES REGISTER | 1 | 2021-12-30 | 1 | 2021-12-30 | 2022-03-04 | 2022-03-25 | 0 | 0 | 0
A.1.2 | CA0000-59-PLN-0001 | GDVPJ1015 | GDVPJ1020 | GDVPJ1025 | 8405-PP-GE-002 | PROJECT EXECUTION PLAN | 1 | 2022-01-12 | 1 | 2022-01-12 | 2022-02-09 | 2022-03-23 | 0 | 0 | 0
A.1.3 | CA0000-59-PRO-0001 | GDVPJ1030 | GDVPJ1035 | GDVPJ1040 | 8405-PP-GE-003 | PROJECT COORDINATION & COMMUNICATION PROCEDURE | 1 | 2022-02-09 | 1 | 2022-02-09 | 2022-03-09 | 2022-04-04 | 0 | 0 | 0
A.1.4 | CA0000-59-PRO-0002 | GDVPJ1045 | GDVPJ1050 | GDVPJ1055 | 8405-PP-GE-004 | PROJECT DOCUMENT CONTROL PROCEDURE | 1 | 2022-01-21 | 1 | 2022-01-21 | 2022-02-25 | 2022-03-22 | 0 | 0 | 0
A.1.5 | CA0000-59-PLN-0002 | GDVPJ1060 | GDVPJ1065 | GDVPJ1070 | 8405-PP-GE-005 | PROJECT INTERFACE MANAGEMENT PLAN | 2 | 2022-02-11 | 2 | 2022-02-11 | 2022-03-04 | 2022-03-22 | 0 | 0 | 0
A.1.6 | CA0000-59-REG-0002 | GDVPJ1090 | GDVPJ1095 | GDVPJ1100 | 8405-PP-GE-006 | PROJECT RISK REGISTER | 2 | 2022-02-23 | 2 | 2022-03-11 | 2022-03-29 | 2022-04-11 | 16 | 0 | 0
A.1.7 | CA0000-59-PRO-0011 | GDVPT1065 | GDVPT1075 | GDVPT1085 | 8405-PP-GE-007 | VENDOR DOCUMENT MANAGEMENT PROCEDURE | 1 | 2022-05-11 | 1 | 2022-05-18 | 2022-06-15 | 2022-07-18 | 7 | 0 | 0
A.1.8 | CA0000-59-PRO-0004 | GDVPJ1075 | GDVPJ1080 | GDVPJ1085 | 8405-PP-GE-008 | PROJECT RISK MANAGEMENT PROCEDURE | 1 | 2022-01-28 | 1 | 2022-01-28 | 2022-02-22 | 2022-03-15 | 0 | 0 | 0
A.1.9 | CA0000-50-REP-0002 | GDVPJ1240 | GDVPJ1245 | GDVPJ1310 | 8405-PP-GE-029 | PROJECT RISK CLOSE-OUT REPORT | 1 | 2024-08-28 | 1 | 2024-08-28 | 2024-09-26 | 2025-02-20 | 0 | 0 | 0
A.1.10 | CA0000-50-PRO-0008 |  |  |  | 8405-PP-GE-037 | TOR / PROCEDURE FOR PROJECT RISK ASSESSMENT WORKSHOP | 1 | 2022-02-17 | 1 |  |  |  | 0 | 0 | 0
A.1.11 | CA0000-59-PLN-0003 | GDVPJ1105 | GDVPJ1110 | GDVPJ1115 | 8405-PP-GE-009 | PROJECT SUBCONTRACT PLAN | 1 | 2022-01-14 | 1 | 2022-01-17 | 2022-02-28 | 2022-03-28 | 3 | 0 | 0
A.1.12 | CA0000-59-PLN-0004 | GDVPJ1120 | GDVPJ1125 | GDVPJ1130 | 8405-PP-GE-010 | ASSET INTEGRITY MANAGEMENT PLAN | 1 | 2022-03-11 | 1 | 2022-03-18 | 2022-04-22 | 2022-05-25 | 7 | 0 | 0
A.1.13 | CA0000-59-PRO-0005 | GDVPJ1290 | GDVPJ1300 | GDVPJ1250 | 8405-PP-GE-011 | FINAL DOCUMENTATION HANDOVER PROCEDURE | 1 | 2023-09-18 | 1 | 2023-09-18 | 2023-10-17 | 2023-11-14 | 0 | 0 | 0
A.1.14 | CA0000-59-PRO-0006 | GDVPJ1135 | GDVPJ1140 | GDVPJ1145 | 8405-PP-GE-012 | CONSTRUCTABILITY WORKSHOP PROCEDURE | 1 | 2022-06-20 | 1 | 2022-06-15 | 2022-07-18 | 2022-08-18 | -5 | 0 | 0
A.1.15 | CA0000-59-REP-0002 |  |  |  | 8405-PP-GE-035 | CONSTRUCTABILITY WORKSHOP REPORT | 1 | 2022-06-27 | 1 |  |  |  | 0 | 0 | 0
A.1.17 | CA0000-59-PRO-0007 | GDVPJ1150 | GDVPJ1155 | GDVPJ1160 | 8405-PP-GE-013 | PROJECT MATERIAL MANAGEMENT PROCEDURE | 1 | 2022-02-09 | 1 | 2022-02-09 | 2022-03-23 | 2022-04-20 | 0 | 0 | 0
A.1.18 | CA0000-59-REG-0003 | GDVPJ1165 | GDVPJ1170 | GDVPJ1175 | 8405-PP-GE-014 | PROJECT INTERFACE REGISTER | 2 | 2022-01-28 | 2 | 2022-01-28 | 2022-02-25 | 2022-03-29 | 0 | 0 | 0
A.1.19 | CA0000-59-PRO-0008 | GDVPJ1180 | GDVPJ1185 | GDVPJ1190 | 8405-PP-GE-015 | DESIGN DEVIATION / CONCESSION REQUEST AUTHORIZATION (DCA) PROCEDURE | 1 | 2022-02-16 | 1 | 2022-02-16 | 2022-03-11 | 2022-04-01 | 0 | 0 | 0
A.1.20 | CA0000-59-GDD-0001 | GDVPJ1195 | GDVPJ1200 | GDVPJ1205 | 8405-PP-GE-016 | PROJECT PROCEDURE FOR NOTIFICATION TO SITE OF CHANGE (NSC) | 1 | 2022-02-16 | 1 | 2022-02-16 | 2022-03-09 | 2022-03-30 | 0 | 0 | 0
A.1.21 | CA0000-89-REP-0001 |  |  |  | 8405-PP-GE-017 | PROJECT CLOSE OUT REPORT | 2 | 2024-08-20 | 2 |  |  |  | 0 | 0 | 0
A.1.22 | CA0000-59-COD-0001 |  |  |  | 8405-PP-GE-038 | PROJECT COMPLETION DOSSIER | 1 | 2024-08-20 | 1 |  |  |  | 0 | 0 | 0
A.1.23 | CA0000-59-PRO-0009 |  |  |  | 8405-PP-GE-039 | AS-BUILT DOCUMENTATION PROCEDURE | 1 | 2024-02-25 | 1 |  |  |  | 0 | 0 | 0
A.1.24 | CA0000-59-PLN-0005 | GDVPJ1260 | GDVPJ1270 | GDVPJ1280 | 8405-PP-GE-018 | LOGISTICS MANAGEMENT PLAN | 3 | 2022-06-27 | 3 | 2022-06-22 | 2022-07-25 | 2022-08-15 | -5 | 0 | 0
A.1.25 | CA0000-50-PRO-0009 |  |  |  | 8405-PP-GE-033 | LESSON LEARNT PROCEDURE | 1 | 2022-02-01 | 1 |  |  |  | 0 | 0 | 0
A.1.27 | CA0000-89-REP-0002 | GDVPJ1225 | GDVPJ1230 | GDVPJ1235 | 8405-PP-GE-020 | LESSON LEARNT WORKSHOP REPORT | 2 | 2022-04-20 | 2 | 2022-04-15 | 2022-05-18 | 2022-06-15 | -5 | 0 | 0
A.1.28 | CA0000-54-MAN-001 |  |  |  | 8405-PP-CM-033 | OPERATING MANUALS (VARIOUS DOCUMENTS) | 2 | 2024-08-20 | 2 |  |  |  | 0 | 0 | 0
A.1.29 | CA0000-54-MAN-002 |  |  |  | 8405-PP-CM-034 | INSTALLATION AND MAINTENANCE MANUALS (VARIOUS DOCUMENTS) | 2 | 2024-08-20 | 2 |  |  |  | 0 | 0 | 0
A.1.30 | CA0000-59-MAN-001 |  |  |  | 8405-PP-GE-040 | CERTIFICATION MANUAL (THIS DOCUMENT ALREADY SEND THRU LETTER NO. 8405-NPCC-A-L-0059 DATED 22-02-22 | 3 | 2022-02-22 | 3 |  |  |  | 0 | 0 | 0
A.1.31 | CA0000-59-MAN-002 |  |  |  | 8405-PP-GE-041 | INDEXES FOR FINAL DOCUMENTATION MANUALS | 3 | 2024-06-15 | 3 |  |  |  | 0 | 0 | 0
A.1.32 | CA0000-52-PLN-0008 |  |  |  | 8405-PP-HS-023 | TRAINING PLAN | 3 | 2024-05-21 | 3 |  |  |  | 0 | 0 | 0
A.1.33 | CA0000-58-GDD-0001 |  |  |  | 8405-PP-PR-012 | CONTRACT ORGANIZATION AND MANNING, ORGANIZATION CHARTS | 1 | 2022-01-17 | 1
A.1.2 | PROJECT CONTROL | [11 empty] | 0 | 0 | 0
A.1.2.1 | CA0000-50-PRO-0001 | GDVPC1005 | GDVPC1010 | GDVPC1015 | 8405-PP-GE-021 | PLANNING & SCHEDULING PROCEDURE | 1 | 2022-01-13 | 1 | 2022-01-13 | 2022-02-10 | 2022-03-03 | 0 | 0 | 0
A.1.2.2 | CA0000-50-PRO-0002 | GDVPC1020 | GDVPC1025 | GDVPC1030 | 8405-PP-GE-022 | PROGRESS MEASUREMENT PROCEDURE | 1 | 2022-01-11 | 1 | 2022-01-11 | 2022-02-08 | 2022-03-03 | 0 | 0 | 0
A.1.2.3 | CA0000-50-GDD-0001 | GDVPC1050 | GDVPC1055 | GDVPC1060 | 8405-PP-GE-023 | PROJECT PLANNING PACKAGE | 1 | 2022-02-04 | 1 | 2022-02-04 | 2022-02-28 | 2022-03-09 | 0 | 0 | 0
A.1.2.4 | CA0000-50-REP-0001 | GDVPC1085 | GDVPC1090 | GDVPC1095 | 8405-PP-GE-024 | QUARTERLY SCHEDULE RISK ANALYSIS REPORT | 1 | 2022-04-29 | 1 | 2022-04-29 | 2022-06-01 | 2022-06-29 | 0 | 0 | 0
A.1.2.5 | CA0000-50-PRO-0003 | GDVPC1115 | GDVPC1120 | GDVPC1125 | 8405-PP-GE-025 | MANAGEMENT OF CHANGE PROCEDURE | 1 | 2022-02-10 | 1 | 2022-02-25 | 2022-04-01 | 2022-05-25 | 15 | 0 | 0
A.1.2.6 | CA0000-50-SCH-0001 | GDVPC1000 | GDVPC1000 | GDVPC1000 | 8405-PP-GE-030 | 30/90 DAYS FRONT END SCHEDULES | 3 | 2021-12-21 | 3 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 6 | 0 | 0
A.1.2.7 | CA0000-50-PRO-0004 |  |  |  | 8405-PP-GE-027 | PROJECT CONTRACT TRENDING PROCEDURE | 1 | 2022-01-14 | 1 |  |  |  | 0 | 0 | 0
A.1.2.8 | CA0000-50-PRO-0005 | GDVPC1065 | GDVPC1070 | GDVPC1075 | 8405-PP-GE-028 | INVOICING PROCEDURE | 2 | 2022-01-28 | 2 | 2022-01-28 | 2022-02-25 | 2022-03-25 | 0 | 0 | 0
A.1.2.9 | CA0000-50-PRO-0006 | GDVPC1035 | GDVPC1040 | GDVPC1045 | 8405-PP-GE-031 | PROGRESS REPORTING & PROGRESS REVIEW/CERTIFICATION PROCEDURE | 1 | 2022-01-07 | 1 | 2022-01-07 | 2022-02-04 | 2022-03-04 | 0 | 0 | 0
A.1.2.10 | CA0000-50-PRO-0007 | GDVPC1080 | GDVPC1080 | GDVPC1080 | 8405-PP-GE-032 | SCHEDULE RISK ANALYSIS PROCEDURE | 1 | 2022-02-04 | 1 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 48 | 0 | 0
A.1.2.11 | CA0000-54-SCH-0001 |  |  |  | 8405-PP-CM-035 | DETAILED PRE-COMMISSIONING / COMMISSIONING & START UP SCHEDULES | 1 | 2023-05-15 | 1 |  |  |  | 0 | 0 | 0
A.1.2.12 | CA0000-58-SCH-0001 |  |  |  | 8405-PP-PR-013 | DETAILED CONSTRUCTION / MECHANICAL COMPLETION SCHEDULE | 2 | 2022-08-22 | 2 |  |  |  | 0 | 0 | 0
A.1.2.13 | CA0000-50-REP-00XX |  |  |  | 8405-WPR-0XX | WEEKLY PROGRESS REPORTS | 3 |  | 3 |  |  |  | 0 | 0 | 0
A.1.2.14 | CA0000-50-REP-3-00XX |  |  |  | 8405-MPR-0XX | MONTHLY PROGRESS REPORTS | 3 |  | 3 |  |  |  | 0 | 0 | 0
A.1.2.15 | CA0000-58-PLN-0002 |  |  |  | 8405-PP-PR-014 | RECOVERY PLANS | 2 |  | 2 |  |  |  | 0 | 0 | 0
A.1.2.16 | CA0000-59-PRO-0010 |  |  |  | 8405-PP-GE-042 | ASSET REGISTER PROCEDURE | 1 | 2022-04-22 | 1 |  |  |  | 0 | 0 | 0
A.1.2.17 | CA0000-59-REG-0005 |  |  |  | 8405-PP-GE-043 | ASSET REGISTER | 2 | 2022-05-20 | 2 |  |  |  | 0 | 0 | 0
| CONTRACTS | [11 empty] | 0 | 0 | 0
A.1.2.18 | CA0000-58-GDD-0003 |  |  |  | 8405-PP-PR-015 | PERFORMANCE BANK GUARANTEE | 1 |  | 1 |  |  |  | 0 | 0 | 0
A.1.2.19 | CA0000-58-GDD-0004 |  |  |  | 8405-PP-PR-016 | ADVANCE PAYMENT BOND | 1 |  | 1 |  |  |  | 0 | 0 | 0
A.1.2.20 | CA0000-58-GDD-0005 |  |  |  | 8405-PP-PR-017 | INSURANCE POLICIES/CERTIFICATES (CONTRACTOR AND SUBCONTRACTOR) | 1 |  | 1 |  |  |  | 0 | 0 | 0
A.1.2.22 | CA0000-59-REP-0004 |  |  |  | 8405-PP-GE-044 | SUBCONTRACTOR’S PERFORMANCE FEEDBACK REPORT | 3 |  | 3 |  |  |  | 0 | 0 | 0
A.1.2.23 | CA0000-59-GDD-0006 |  |  |  | 8405-PP-GE-045 | UNPRICED COPY SUBCONTRACT AGREEMENTS (WILL BE DEVELOPED SEPARATELY FOR ALL S/C) | 3 |  | 3 |  |  |  | 0 | 0 | 0
A.1.3 | PROCUREMENT | [11 empty] | 0 | 0 | 0
A.1.3.1 | CA0000-58-PLN-0001 | GDVPT1000 | GDVPT1005 | GDVPT1010 | 8405-PP-PR-001 | PROJECT PROCUREMENT PLAN | 2 | 2022-02-04 | 2 | 2022-02-04 | 2022-03-11 | 2022-04-01 | 0 | 0 | 0
A.1.3.2 | CA0000-58-PVL-0001 | GDVPT1015 | GDVPT1020 | GDVPT1025 | 8405-PP-PR-002 | PROJECT VENDOR LIST (PVL) | 1 | 2022-02-11 | 1 | 2022-02-11 | 2022-03-11 | 2022-04-04 | 0 | 0 | 0
A.1.3.3 | CA0000-58-LST-0001 | GDVPT1030 | GDVPT1035 | GDVPT1040 | 8405-PP-PR-003 | LIST OF LONG LEAD ITEM (LLIS) | 2 | 2022-03-11 | 2 | 2022-03-18 | 2022-04-15 | 2022-05-18 | 7 | 0 | 0
A.1.3.4 | CA0000-58-PRO-0001 | GDVPT1045 | GDVPT1050 | GDVPT1055 | 8405-PP-PR-004 | VENDOR INSPECTION COORDINATION PROCEDURE | 3 | 2022-04-08 | 3 | 2022-04-15 | 2022-05-18 | 2022-06-09 | 7 | 0 | 0
A.1.3.5 | CA0000-58-LST-0002 |  |  |  | 8405-PP-PR-005 | PROJECT SUBCONTRACTORS LIST (PSL) | 2 | 2022-01-10 | 2 |  |  |  | 0 | 0 | 0
A.1.3.6 | CA0000-58-PRO-0002 |  |  |  | 8405-PP-PR-006 | VENDOR PREQUALIFICATION PROCEDURE (Agreed with COMPANY and withdrawn) |  | 2022-01-15 | 2
A.1.3.7 | CA0000-58-GDD-0002 |  |  |  | 8405-PP-PR-008 | AWARD RECOMMENDATIONS | 1 |  | 1 |  |  |  | 0 | 0 | 0
A.1.3.8 | CA0000-58-PAR-0001 |  |  |  | 8405-PP-PR-009 | UNPRICED PURCHASE ORDERS | 3 |  | 3 |  |  |  | 0 | 0 | 0
A.1.3.9 | CA0000-58-TBE-0001 |  |  |  | 8405-PP-PR-010 | TECHNICAL BID EVALUATION REPORTS (MULTIPLE DOCUMENTS) | 2 |  | 2 |  |  |  | 0 | 0 | 0
A.1.3.10 | CA0000-58-REP-0001 |  |  |  | 8405-PP-PR-011 | EXPEDITING REPORTS (MULTIPLE DOCUMENTS) | 2 |  | 2 |  |  |  | 0 | 0 | 0
A.1.3.11 | CA0000-58-PRO-0006 |  |  |  | 8405-PP-PR-018 | EXPEDITING PROCEDURE | 2 | 2022-04-15 | 2 |  |  |  | 0 | 0 | 0
A.1.4 | HSE | [11 empty] | 0 | 0 | 0
A.1.4.1 | CA0000-52-MAN-0001 | GDVHS1000 | GDVHS1000 | GDVHS1000 | 8405-PP-HS-001 | HSE MANUAL SAF-002 - CORPORATE DOCUMENT | 3 | 2022-01-06 | 3 | 2022-01-28 | 2022-01-28 | 2022-01-28 | 22 | 0 | 0
A.1.4.2 | CA0000-52-MAN-0002 | GDVHS1010 | GDVHS1010 | GDVHS1010 | 8405-PP-HS-002 | NPCC ENVIRONMENT MANAGEMENT SYSTEM MANUAL | 3 | 2022-02-04 | 3 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 35 | 0 | 0
A.1.4.3 | CA0000-52-PLN-0001 |  |  |  | 8405-PP-HS-004 | RISK ASSESSMENT FOR PRE-ENGINEERING GEOPHYSICAL SURVEY- IFI | 2 | 2022-02-21 | 2 |  |  |  | 0 | 0 | 0
A.1.4.4 | CA0000-52-PLN-0002 | GDVHS1045 | GDVHS1050 | GDVHS1055 | 8405-PP-HS-005 | CONSTRUCTION HSE PLAN - OFFSHORE | 1 | 2022-05-19 | 1 | 2022-05-19 | 2022-06-16 | 2022-07-19 | 0 | 0 | 0
A.1.4.5 | CA0000-52-PLN-0003 |  |  |  | 8405-PP-HS-006 | EMERGENCY RESPONSE PLAN | 1 | 2022-05-10 | 1 |  |  |  | 0 | 0 | 0
A.1.4.6 | CA0000-52-PLN-0006 | GDVHS1075 | GDVHS1080 | GDVHS1085 | 8405-PP-HS-009 | WASTE MANAGEMENT PLAN | 1 | 2022-08-17 | 1 | 2022-07-01 | 2022-08-03 | 2022-08-31 | -47 | 0 | 0
A.1.4.7 | CA0000-52-PRO-0003 | GDVHS1060 | GDVHS1065 | GDVHS1070 | 8405-PP-HS-012 | CONSTRUCTION ENVIRONMENT MANAGEMENT PLAN - OFFSHORE (By Sub-Contractor) | 1 | 2022-08-05 | 1 | 2022-06-10 | 2022-07-13 | 2022-08-02 | -56 | 0 | 0
A.1.4.8 | CA0000-52-PLN-0007 | GDVHS1005 | GDVHS1015 | GDVHS1020 | 8405-PP-HS-013 | PROJECT HSE PLAN | 1 | 2022-02-04 | 1 | 2022-02-04 | 2022-03-04 | 2022-04-01 | 0 | 0 | 0
A.1.4.9 | CA0000-52-GDD-0002 |  |  |  | 8405-PP-HS-014 | COVID-19 & BUSINESS CONTINUATY BRIDGING | 1 | 2022-03-28 | 3 |  |  |  | 0 | 0 | 0
A.1.4.10 | CA0000-52-PLN-0009 |  |  |  | 8405-PP-HS-017 | OPERATIONAL ENVIRONMENTAL MANAGEMENT PLAN (CONSTRUCTION & OPERATIONS) (By Sub-Contractor) | 1 | 2022-08-05 | 1 |  |  |  | 0 | 0 | 0
A.1.4.11 | CA0000-52-PRO-0004 |  |  |  | 8405-PP-HS-018 | WORK PERMIT PROCEDURE | 2 | 2022-07-07 | 2 |  |  |  | 0 | 0 | 0
A.1.4.12 | CA0000-52-PLN-0010 |  |  |  | 8405-PP-HS-019 | WELFARE MANAGEMENT PLAN | 1 (Offshore Barges) | 2022-08-17 | 1 |  |  |  | 0 | 0 | 0
A.1.4.13 | CA0000-52-REP-0001 |  |  |  | 8405-PP-HS-020 | CONSTRUCTION ONSHORE RISK ASSESSMENT | 2 | 2022-06-30 | 2 |  |  |  | 0 | 0 | 0
A.1.4.14 | CA0000-52-REP-0003 |  |  |  | 8405-PP-HS-026 | CONSTRUCTION OFFSHORE RISK ASSESSMENT |  | 2022-12-26 | 2
A.1.4.15 | CA0000-52-PLN-0011 |  |  |  | 8405-PP-HS-022 | ERP BRIDGING DOCUMENT (By Sub-Contractor) | 1 | 2022-07-15 | 1 |  |  |  | 0 | 0 | 0
A.1.4.16 | CA0000-52-PLN-0012 |  |  |  | 8405-PP-HS-025 | CONSTRUCTION HSE PLAN ONSHORE |  | 2022-07-01 | 1
A.1.5 | QA&QC | [11 empty] | 0 | 0 | 0
A.1.5.1 | CA0000-63-PLN-0001 | GDVQA1000 | GDVQA1005 | GDVQA1010 | 8405-PP-QA-001 | PROJECT QUALITY PLAN | 1 | 2022-01-28 | 1 | 2022-01-28 | 2022-03-04 | 2022-04-01 | 0 | 0 | 0
A.1.5.2 | CA0000-63-SCH-0001 | GDVQA1015 | GDVQA1020 | GDVQA1025 | 8405-PP-QA-002 | PROJECT QUALITY AUDIT SCHEDULE | 1 | 2022-02-04 | 1 | 2022-02-04 | 2022-03-18 | 2022-04-15 | 0 | 0 | 0
A.1.5.3 | CA0000-63-PRO-0025 | GDVQA1030 | GDVQA1035 | GDVQA1040 | 8405-PP-QA-003 | NON-CONFORMANCE REPORTING SYSTEM PROCEDURE | 1 | 2022-04-15 | 1 | 2022-04-15 | 2022-06-15 | 2022-08-22 | 0 | 0 | 0
A.1.5.4 | CA0000-63-PRO-0002 | GDVQA1045 | GDVQA1050 | GDVQA1055 | 8405-PP-QA-004 | PROJECT MATERIAL CONTROL INSPECTION IDENTIFICATION AND TRACEABILITY PROCEDURE | 1 | 2022-04-22 | 1 | 2022-04-22 | 2022-06-15 | 2022-09-08 | 0 | 0 | 0
A.1.5.5 | CA0000-63-PRO-0003 | GDVQA1060 | GDVQA1065 | GDVQA1070 | 8405-PP-QA-005 | DIMENSIONAL CONTROL PROCEDURE | 1 | 2022-05-25 | 1 | 2022-05-25 | 2022-07-06 | 2022-09-08 | 0 | 0 | 0
A.1.5.6 | CA0000-63-PRO-0004 | GDVQA1075 | GDVQA1080 | GDVQA1085 | 8405-PP-QA-006 | POSITIVE MATERIAL IDENTIFICATION (PMI) PROCEDURE | 1 | 2022-05-30 | 1 | 2022-05-30 | 2022-07-14 | 2022-09-01 | 0 | 0 | 0
A.1.5.7 | CA0000-63-PRO-0005 | GDVQA1090 | GDVQA1095 | GDVQA1100 | 8405-PP-QA-007 | WELDING CONSUMABLE CONTROL PROCEDURE | 2 | 2022-06-02 | 2 | 2022-06-02 | 2022-07-19 | 2022-08-30 | 0 | 0 | 0
A.1.5.8 | CA0000-63-PRO-0006 | GDVQA1105 | GDVQA1110 | GDVQA1115 | 8405-PP-QA-008 | WELDING PROCEDURES - STRUCTURAL | 1 | 2022-06-09 | 1 | 2022-06-09 | 2022-07-26 | 2022-09-06 | 0 | 0 | 0
A.1.5.9 | CA0000-63-PRO-0007 | GDVQA1120 | GDVQA1125 | GDVQA1130 | 8405-PP-QA-009 | WELDING PROCEDURES - PIPING | 1 | 2022-07-07 | 1 | 2022-07-07 | 2022-08-23 | 2022-10-25 | 0 | 0 | 0
A.1.5.10 | CA0000-63-PRO-0008 | GDVQA1135 | GDVQA1140 | GDVQA1145 | 8405-PP-QA-010 | WELDING PROCEDURES - PIPELINE SPOOLS | 1 | 2022-08-23 | 1 | 2022-08-23 | 2022-10-04 | 2022-12-08 | 0 | 0 | 0
A.1.5.11 | CA0000-63-PLN-0002 | GDVQA1150 | GDVQA1155 | GDVQA1160 | 8405-PP-QA-011 | INSPECTION AND TEST PLAN FOR E & I WORKS (ONSHORE) | 1 | 2022-08-09 | 1 | 2022-08-09 | 2022-09-20 | 2022-11-22 | 0 | 0 | 0
A.1.5.12 | CA0000-63-PLN-0003 | GDVQA1180 | GDVQA1185 | GDVQA1190 | 8405-PP-QA-013 | INSPECTION AND TEST PLAN FOR PIPELAYING WORK | 1 | 2022-09-27 | 1 | 2022-09-27 | 2022-11-08 | 2023-01-12 | 0 | 0 | 0
A.1.5.13 | CA0000-63-PLN-0004 | GDVQA1195 | GDVQA1200 | GDVQA1205 | 8405-PP-QA-014 | INSPECTION & TEST PLAN FOR SUBSEA UMBILICAL AND FIBRE OPTIC & CABLE INSTALLATION | 1 | 2022-08-08 | 1 | 2022-08-08 | 2022-09-19 | 2022-10-31 | 0 | 0 | 0
A.1.5.14 | CA0000-63-LST-0011 | GDVQA1210 | GDVQA1215 | GDVQA1220 | 8405-PP-QA-015 | QC PERSONNEL LIST (ONSHORE) | 2 | 2022-04-29 | 2 | 2022-04-29 | 2022-06-15 | 2022-08-01 | 0 | 0 | 0
A.1.5.15 | CA0000-63-LST-0002 | GDVQA1225 | GDVQA1230 | GDVQA1235 | 8405-PP-QA-016 | QC PERSONNEL LIST (OFFSHORE) | 2 | 2022-07-18 | 2 | 2022-07-18 | 2022-08-29 | 2022-10-10 | 0 | 0 | 0
A.1.5.16 | CA0000-63-LST-0003 | GDVQA1240 | GDVQA1240 | GDVQA1240 | 8405-PP-QA-017 | MUSSAFAH WELDERS LIST (STRUCTURAL) | 1 | 2022-04-01 | 1 | 2022-05-18 | 2022-05-18 | 2022-05-18 | 47 | 0 | 0
A.1.5.17 | CA0000-63-LST-0004 | GDVQA1245 | GDVQA1245 | GDVQA1245 | 8405-PP-QA-018 | MUSSAFAH WELDERS LIST (PIPING) | 1 | 2022-06-16 | 1 | 2022-07-26 | 2022-07-26 | 2022-07-26 | 40 | 0 | 0
A.1.5.18 | CA0000-63-LST-0005 | GDVQA1250 | GDVQA1250 | GDVQA1250 | 8405-PP-QA-019 | OFFSHORE WELDERS LIST (STRUCTURAL) | 1 | 2022-10-17 | 1 | 2022-11-21 | 2022-11-21 | 2022-11-21 | 35 | 0 | 0
A.1.5.19 | CA0000-63-LST-0006 | GDVQA1270 | GDVQA1270 | GDVQA1270 | 8405-PP-QA-020 | OFFSHORE WELDERS LIST (PIPING) | 1 | 2022-11-28 | 1 | 2023-01-04 | 2023-01-04 | 2023-01-04 | 37 | 0 | 0
A.1.5.20 | CA0000-63-LST-0007 | GDVQA1255 | GDVQA1255 | GDVQA1255 | 8405-PP-QA-021 | OFFSHORE WELDERS LIST (RISERS & TIE-IN) | 1 | 2022-07-25 | 1 | 2022-08-29 | 2022-08-29 | 2022-08-29 | 35 | 0 | 0
A.1.5.21 | CA0000-63-LST-0008 | GDVQA1260 | GDVQA1260 | GDVQA1260 | 8405-PP-QA-022 | OFFSHORE WELDERS LIST (PIPELINE) - AUTOMATIC & REPAIR | 1 | 2022-08-08 | 1 | 2022-09-12 | 2022-09-12 | 2022-09-12 | 35 | 0 | 0
A.1.5.22 | CA0000-63-LST-0009 | GDVQA1265 | GDVQA1265 | GDVQA1265 | 8405-PP-QA-023 | OFFSHORE WELDERS LIST (PIPELINE) - MANUAL & REPAIR | 1 | 2022-08-22 | 1 | 2022-09-26 | 2022-09-26 | 2022-09-26 | 35 | 0 | 0
A.1.5.23 | CA0000-63-PRO-0009 | GDVQA1275 | GDVQA1280 | GDVQA1285 | 8405-PP-QA-024 | RADIOGRAPHIC TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS | 1 | 2022-05-18 | 1 | 2022-05-18 | 2022-06-15 | 2022-07-18 | 0 | 0 | 0
A.1.5.24 | CA0000-63-PRO-0010 | GDVQA1290 | GDVQA1295 | GDVQA1300 | 8405-PP-QA-025 | ULTRASONIC TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS | 1 | 2022-05-18 | 1 | 2022-05-18 | 2022-06-29 | 2022-08-15 | 0 | 0 | 0
A.1.5.25 | CA0000-63-PRO-0011 | GDVQA1640 | GDVQA1650 | GDVQA1660 | 8405-PP-QA-026 | LIQUID PENETRANT PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS | 1 | 2022-07-06 | 1 | 2022-07-06 | 2022-08-08 | 2022-09-05 | 0 | 0 | 0
A.1.5.26 | CA0000-63-PRO-0012 | GDVQA1305 | GDVQA1310 | GDVQA1315 | 8405-PP-QA-027 | MAGNETIC PARTICLE TESTING PROCEDURE FOR ONSHORE AND OFFSHORE CONSTRUCTION WORKS | 1 | 2022-05-18 | 1 | 2022-05-18 | 2022-06-29 | 2022-09-05 | 0 | 0 | 0
A.1.5.27 | CA0000-63-PRO-0013 | GDVQA1320 | GDVQA1325 | GDVQA1330 | 8405-PP-QA-028 | NDT PROCEDURES (PIPELINES) | 1 | 2022-06-20 | 1 | 2022-06-20 | 2022-08-04 | 2022-09-08 | 0 | 0 | 0
A.1.5.28 | CA0000-63-LST-0010 | GDVQA1335 | GDVQA1340 | GDVQA1345 | 8405-PP-QA-029 | NDT OPERATORS LIST (ONSHORE / OFFSHORE) | 2 | 2022-06-20 | 2 | 2022-06-20 | 2022-08-04 | 2022-10-06 | 0 | 0 | 0
A.1.5.29 | CA0000-63-PRO-0014 | GDVQA1350 | GDVQA1355 | GDVQA1360 | 8405-PP-QA-030 | PIPING WELDS PHASED ARRAY ULTRASONIC TESTING PROCEDURE | 1 | 2022-06-20 | 1 | 2022-06-20 | 2022-08-04 | 2022-09-22 | 0 | 0 | 0
A.1.5.30 | CA0000-63-PRO-0015 | GDVQA1365 | GDVQA1370 | GDVQA1375 | 8405-PP-QA-031 | AUTOMATED ULTRASONIC TESTING PROCEDURE FOR PIPELINE WELDS | 1 | 2022-06-20 | 1 | 2022-06-20 | 2022-08-04 | 2022-10-06 | 0 | 0 | 0
A.1.5.31 | CA0000-63-RPT-0001 | GDVQA1380 | GDVQA1385 | GDVQA1390 | 8405-PP-QA-032 | ENGINEERING CRITICALITY ASSESSMENT REPORT FOR PIPELINE WELDS | 1 | 2022-06-20 | 1 | 2022-06-20 | 2022-08-04 | 2022-10-06 | 0 | 0 | 0
A.1.5.32 | CA0000-63-PRO-0016 | GDVQA1395 | GDVQA1400 | GDVQA1405 | 8405-PP-QA-033 | BASELINE SURVEY PROCEDURE | 1 | 2022-07-21 | 1 | 2022-07-21 | 2022-08-18 | 2022-09-15 | 0 | 0 | 0
A.1.5.33 | CA0000-63-GDD-0001 | GDVQA1410 | GDVQA1415 | GDVQA1420 | 8405-PP-QA-034 | AUT / NDT PERSONNEL QUALIFICATIONS SUMMARY | 2 | 2022-07-21 | 2 | 2022-07-21 | 2022-09-01 | 2022-10-13 | 0 | 0 | 0
A.1.5.34 | CA0000-63-PRO-0017 | GDVQA1520 | GDVQA1530 | GDVQA1540 | 8405-PP-QA-035 | INSTALLATION PROCEDURE FOR E&I WORKS (Moved to Onshore Construction) | 1 | 2022-08-01 | 1 | 2022-08-01 | 2022-08-29 | 2022-09-26 | 0 | 0 | 0
A.1.5.35 | CA0000-63-PLN-0005 | GDVQA1425 | GDVQA1430 | GDVQA1435 | 8405-PP-QA-036 | INSPECTION & TEST PLAN FOR ONSHORE CONSTRUCTION WORKS | 1 | 2022-05-18 | 1 | 2022-05-18 | 2022-06-29 | 2022-08-15 | 0 | 0 | 0
A.1.5.36 | CA0000-63-PLN-0006 | GDVQA1440 | GDVQA1445 | GDVQA1450 | 8405-PP-QA-037 | INSPECTION & TEST PLAN FOR OFFSHORE CONSTRUCTION WORKS | 1 | 2022-08-18 | 1 | 2022-08-18 | 2022-09-29 | 2022-11-10 | 0 | 0 | 0
A.1.5.37 | CA0000-63-PLN-0007 | GDVQA1550 | GDVQA1560 | GDVQA1570 | 8405-PP-QA-038 | INSPECTION AND TEST PLAN (MATERIAL RECEIVING INSPECTION) | 1 | 2022-07-18 | 1 | 2022-07-18 | 2022-08-15 | 2022-09-12 | 0 | 0 | 0
A.1.5.38 | CA0000-63-PLN-0008 | GDVQA1455 | GDVQA1460 | GDVQA1465 | 8405-PP-QA-039 | STRUCTURAL NDT PLAN | 2 | 2022-05-25 | 2 | 2022-05-25 | 2022-07-06 | 2022-08-15 | 0 | 0 | 0
A.1.5.39 | CA0000-63-GDD-0002 | GDVQA1470 | GDVQA1475 | GDVQA1480 | 8405-PP-QA-040 | PROCEDURE FOR DIGITIZATION OF RADIOGRAPHS (NPCC YARD & OFFSHORE WORKS) | 2 | 2022-06-08 | 2 | 2022-06-08 | 2022-07-25 | 2022-09-05 | 0 | 0 | 0
A.1.5.40 | CA0000-63-PRO-0018 | GDVQA1485 | GDVQA1490 | GDVQA1495 | 8405-PP-QA-041 | HARDNESS TEST PROCEDURE | 2 | 2022-06-08 | 2 | 2022-06-08 | 2022-07-25 | 2022-09-05 | 0 | 0 | 0
A.1.5.41 | CA0000-63-PRO-0019 | GDVQA1500 | GDVQA1505 | GDVQA1510 | 8405-PP-QA-042 | PIPELINE CAD (THERMIT) WELDING PROCEDURE | 1 | 2022-04-29 | 1 | 2022-05-18 | 2022-06-15 | 2022-07-18 | 19 | 0 | 0
A.1.5.42 | CA0000-63-GDD-0003 | GDVQA1580 | GDVQA1590 | GDVQA1600 | 8405-PP-QA-043 | QC DOSSIER INDEX | 1 | 2022-08-15 | 1 | 2022-08-15 | 2022-09-05 | 2022-09-26 | 0 | 0 | 0
A.1.5.43 | CA0000-63-PRO-0020 |  |  |  | 8405-PP-QA-044 | PROJECT QUALITY AUDIT PROCEDURE | 1 | 2022-04-25 | 1 |  |  |  | 0 | 0 | 0
A.1.5.44 | CA0000-63-SPE-0002 |  |  |  | 8405-PP-QA-045 | PROJECT WELDING SPECIFICATION | 1 | 2022-04-25 | 1 |  |  |  | 0 | 0 | 0
A.1.5.45 | CA0000-63-SPE-0001 |  |  |  | 8405-PP-QA-046 | POSITIVE MATERIAL IDENTIFICATION (PMI) SPECIFICATION | 1 | 2022-04-22 | 1 |  |  |  | 0 | 0 | 0
A.1.5.46 | CA0000-63-PRO-0021 |  |  |  | 8405-PP-QA-047 | CA/PA PROCEDURE (Duplicate) | 1 |  | 1
A.1.5.47 | CA0000-63-LST-0001 |  |  |  | 8405-PP-QA-048 | LIST OF QUALITY OBJECTIVES AND KPIS | 2 | 2022-05-10 | 2 |  |  |  | 0 | 0 | 0
A.1.5.48 | CA0000-63-PRO-0022 |  |  |  | 8405-PP-QA-049 | INSPECTION MANAGEMENT PROCEDURE | 1 | 2022-05-15 | 1 |  |  |  | 0 | 0 | 0
A.1.5.49 | CA0000-63-GDD-0004 |  |  |  | 8405-PP-QA-050 | PROJECT QUALITY ORGANIZATION CHART | 2 | 2022-04-15 | 2 |  |  |  | 0 | 0 | 0
A.1.5.50 | CA0000-63-PRO-0023 |  |  |  | 8405-PP-QA-051 | WELD NUMBERING PROCEDURES | 2 | 2022-06-10 | 2 |  |  |  | 0 | 0 | 0
A.1.5.51 | CA0000-63-REP-0001 |  |  |  | 8405-PP-QA-052 | WELD MAP/S (REPORT) | 2 |  | 2 |  |  |  | 0 | 0 | 0
A.1.5.52 | CA0000-63-REP-0002 |  |  |  | 8405-PP-QA-053 | PAINTING / COATING APPLICATOR QUALIFICATION RECORDS (REPORT) | 2 |  | 2 |  |  |  | 0 | 0 | 0
A.1.5.53 | CA0000-63-PRO-0024 |  |  |  | 8405-PP-QA-054 | CORRECTIVE & PREVENTIVE ACTION PROCEDURE | 2 | 2022-05-25 | 2 |  |  |  | 0 | 0 | 0
A.1.5.54 | CA0000-63-PLN-0009 |  |  |  | 8405-PP-QA-055 | INSPECTION & TEST PLAN FOR PIPING CONSTRUCTION WORKS (ONSHORE |  | 2022-06-25 | 1
A.1.5.55 | CA0000-63-PLN-0010 |  |  |  | 8405-PP-QA-056 | INSPECTION & TEST PLAN FOR EQUIPMENT INSTALLATION ON DECKS |  | 2022-06-25 | 1
A.1.5.56 | CA0000-63-PLN-0011 |  |  |  | 8405-PP-QA-057 | INSPECTION & TEST PLAN FOR INSTRUMENTATION CONSTRUCTION WORKS (ONSHORE) |  | 2022-06-25 | 1
A.1.5.57 | CA0000-63-PLN-0012 |  |  |  | 8405-PP-QA-058 | INSPECTION & TEST PLAN FOR TELECOM CONSTRUCTION WORKS (ONSHORE) |  | 2022-06-25 | 1
A.1.5.58 | CA0000-63-PLN-0013 |  |  |  | 8405-PP-QA-059 | INSPECTION & TEST PLAN FOR PIPELINE AND RISER FABRICATION |  | 2022-07-25 | 1
A.1.5.59 | CA0000-63-PLN-0014 | 8405-PP-QA-060 | Concrete Weight Coating and Anode Installation Inspection and Test Plan |  | 8405-PP-QA-060 | CONCERETE WEIGHT COATING AND ANODE INSTALLATION INSPECTION AND TEST PLAN |  | 2022-06-30 | 1
| CA0000-63-PLN-0009 |  |  |  | 8405-PP-QA-056 | Three Layer Polypropylene (3LPP) Coating Inspection and Test Plan |  | 2022-06-30 | 1
| New No. reqd. |  |  |  | New No. reqd. | Three Layer Polyethylene (3LPE) Coating Procedure Inspection and Test Plan |  | 2022-06-30 | 1
A.1.6 | ONSHORE CONSTRUCTION | [11 empty] | 0 | 0 | 0
A.1.6.1 | CA0000-51-PRO-0001 |  |  |  | 8405-PP-ON-001 | HOT TAPPING PROCEDURE | 1 | 2023-08-10 | 1 |  |  |  | 0 | 0 | 0
A.1.6.2 | CA0000-51-PRO-0002 | GDVYF1090 | GDVYF1095 | GDVYF1100 | 8405-PP-ON-002 | EQUIPMENT INSULATION PROCEDURE - HOT & COLD | 1 | 2022-06-15 | 1 | 2022-06-15 | 2022-07-18 | 2022-08-19 | 0 | 0 | 0
A.1.6.3 | CA0000-51-PRO-0003 | GDVYF1105 | GDVYF1110 | GDVYF1115 | 8405-PP-ON-003 | HOT DIP GALVANIZING PROCEDURE | 1 | 2022-06-15 | 1 | 2022-06-15 | 2022-07-18 | 2022-08-15 | 0 | 0 | 0
A.1.6.4 | CA0000-51-PRO-0004 | GDVYF1045 | GDVYF1050 | GDVYF1055 | 8405-PP-ON-004 | SURFACE PREPARATION AND PAINTING PROCEDURE | 1 | 2022-05-11 | 1 | 2022-05-11 | 2022-06-08 | 2022-07-06 | 0 | 0 | 0
A.1.6.5 | CA0000-51-PRO-0005 | GDVYF1060 | GDVYF1065 | GDVYF1070 | 8405-PP-ON-005 | POST WELD HEAT TREATMENT (PWHT) PROCEDURE (PIPING) | 1 | 2022-05-18 | 1 | 2022-05-18 | 2022-06-15 | 2022-07-18 | 0 | 0 | 0
A.1.6.6 | CA0000-51-PRO-0006 | GDVYF1120 | GDVYF1125 | GDVYF1130 | 8405-PP-ON-006 | PIPING FLUSHING, TESTING AND DRYING PROCEDURE | 1 | 2022-06-15 | 1 | 2022-06-15 | 2022-07-18 | 2022-08-15 | 0 | 0 | 0
A.1.6.7 | CA0000-51-PRO-0007 | GDVYF1135 | GDVYF1140 | GDVYF1145 | 8405-PP-ON-007 | PASSIVE FIRE PROOFING PROCEDURE | 1 | 2022-06-15 | 1 | 2022-06-15 | 2022-07-18 | 2022-08-15 | 0 | 0 | 0
A.1.6.8 | CA0000-51-GDD-0001 | GDVYF1150 | GDVYF1150 | GDVYF1150 | 8405-PP-ON-008 | COLOR CODING SYSTEM FOR PIPES | 2 | 2022-06-22 | 2 | 2022-07-18 | 2022-07-18 | 2022-07-18 | 26 | 0 | 0
A.1.6.9 | CA0000-51-PRO-0008 | GDVYF1155 | GDVYF1155 | GDVYF1155 | 8405-PP-ON-009 | PIPING FLANGE MANAGEMENT PROCEDURE | 1 | 2022-06-29 | 1 | 2022-07-25 | 2022-07-25 | 2022-07-25 | 26 | 0 | 0
A.1.6.10 | CA0000-51-MES-0001 | GDVYF1160 | GDVYF1160 | GDVYF1160 | 8405-PP-ON-010 | METHOD STATEMENT FOR RETESTING OF VALVES (VALVE SEAT / LEAK TESTING) | 1 | 2022-08-01 | 1 | 2022-08-22 | 2022-08-22 | 2022-08-22 | 21 | 0 | 0
A.1.6.11 | CA0000-51-MES-0002 | GDVYF1165 | GDVYF1165 | GDVYF1165 | 8405-PP-ON-011 | METHOD STATEMENT FOR PIPE INSULATION AT ONSHORE AND OFFSHORE | 1 | 2022-08-15 | 1 | 2022-09-05 | 2022-09-05 | 2022-09-05 | 21 | 0 | 0
A.1.6.12 | CA0000-51-PRO-0009 | GDVYF1000 | GDVYF1005 | GDVYF1010 | 8405-PP-ON-012 | STRUCTURAL FABRICATION AND ERECTION PROCEDURE | 1 | 2022-04-15 | 1 | 2022-04-15 | 2022-05-18 | 2022-06-15 | 0 | 0 | 0
A.1.6.13 | CA0000-51-PRO-0010 | GDVYF1015 | GDVYF1020 | GDVYF1025 | 8405-PP-ON-013 | PIPING FABRICATION AND ERECTION PROCEDURE | 1 | 2022-04-22 | 1 | 2022-04-22 | 2022-05-25 | 2022-07-18 | 0 | 0 | 0
A.1.6.14 | CA0000-51-PRO-0011 | GDVYF1215 | GDVYF1220 | GDVYF1225 | 8405-PP-ON-014 | WEIGHING PROCEDURE FOR JACKETS AND DECKS | 1 | 2022-06-15 | 1 | 2022-06-15 | 2022-07-18 | 2022-08-15 | 0 | 0 | 0
A.1.6.15 | CA0000-51-PRO-0012 | GDVYF1230 | GDVYF1235 | GDVYF1240 | 8405-PP-ON-015 | LOAD OUT PROCEDURE FOR THE DECKS | 1 | 2022-08-29 | 1 | 2022-08-29 | 2022-09-26 | 2022-10-24 | 0 | 0 | 0
A.1.6.16 | CA0000-51-PRO-0013 | GDVYF1030 | GDVYF1035 | GDVYF1040 | 8405-PP-ON-016 | DISTORTION (FREESPAN) CORRECTION PROCEDURE | 1 | 2022-04-29 | 1 | 2022-04-29 | 2022-06-01 | 2022-06-29 | 0 | 0 | 0
A.1.6.17 | CA0000-51-PRO-0014 | GDVYF1200 | GDVYF1205 | GDVYF1210 | 8405-PP-ON-017 | FABRICATION PROCEDURE FOR PRESSURE VESSELS (Procurement Scope) | 1 | 2022-06-15 | 1 | 2022-06-15 | 2022-07-13 | 2022-08-05 | 0 | 0 | 0
A.1.6.18 | CA0000-51-MES-0003 | GDVYF1185 | GDVYF1190 | GDVYF1195 | 8405-PP-ON-018 | METHOD STATEMENT FOR COLD BENDING OF J-TUBE BENDS (Sub-Con Scope) | 1 | 2022-06-15 | 1 | 2022-06-15 | 2022-07-18 | 2022-08-01 | 0 | 0 | 0
A.1.6.19 | CA0000-51-PRO-0015 | GDVYF1170 | GDVYF1175 | GDVYF1180 | 8405-PP-ON-019 | PROCEDURE FOR PWHT OF STRUCTURAL WORKS AT SITE (FIELD JOINTS) | 1 | 2022-04-29 | 1 | 2022-04-29 | 2022-06-01 | 2022-08-10 | 0 | 0 | 0
A.1.6.20 | CA0000-51-PRO-0016 | GDVYF1245 | GDVYF1250 | GDVYF1255 | 8405-PP-ON-020 | GROSS AIR LEAK TEST PROCEDURE (Moved to Commissioning) | 1 | 2022-06-15 | 1 | 2022-06-15 | 2022-07-18 | 2022-08-15 | 0 | 0 | 0
A.1.6.21 | CA0000-59-GDD-0002 |  |  |  | 8405-PP-GE-046 | TEMPORARY SITE FACILITIES LAYOUT WITH RELATED TEMPORARY SERVICES DETAILS (TO INCLUDE OFFICES, WORKSHOPS, WAREHOUSES, ETC. | 2 | 2022-06-13 | 2
A.1.5.34 | CA0000-63-PRO-0017 | GDVQA1520 | GDVQA1530 | GDVQA1540 | 8405-PP-QA-035 | INSTALLATION PROCEDURE FOR E&I WORKS | 1 | 2022-08-01 | 1
| CA0000-63-PRO-0025 |  |  |  | 8405-PP-QA-055 | Three Layer Polypropylene Coating Procedure |  | 2022-06-30 | 1
| CA0000-63-PRO-0026 |  |  |  | 8405-PP-QA-057 | Three Layer Polyethylene Coating Procedure |  | 2022-06-30 | 1
| CA0000-63-PRO-0027 |  |  |  | 8405-PP-QA-059 | Concrete Weight Coating and Anode Installation Procedure |  | 2022-06-30 | 1 |  |  |  | 0 | 0 | 0
A.1.7 | OFFSHORE CONSTRUCTION | [11 empty] | 0 | 0 | 0
A.1.7.1 | CA0000-51-PRO-0017 | GDVOF1000 | GDVOF1005 | GDVOF1010 | 8405-PP-OF-001 | PRE-ENGINEERING GEOPHYSICAL SURVEY PROCEDURE | 1 | 2022-01-19 | 1 | 2022-01-19 | 2022-02-23 | 2022-03-07 | 0 | 0 | 0
A.1.7.2 | CA0000-51-PRO-0018 | GDVOF1015 | GDVOF1020 | GDVOF1025 | 8405-PP-OF-002 | PRE-ENGINEERING GEOTECHNICAL SURVEY PROCEDURE | 1 | 2022-01-19 | 1 | 2022-01-19 | 2022-02-14 | 2022-02-24 | 0 | 0 | 0
A.1.7.3 | CA0000-51-RPT-0001 | GDVOF1030 | GDVOF1030 | GDVOF1030 | 8405-PP-OF-003 | GEOTECHNICAL FACTUAL REPORT | 3 | 2022-04-06 | 3 | 2022-04-27 | 2022-04-27 | 2022-04-27 | 21 | 0 | 0
A.1.7.4 | CA0000-51-PRO-0019 | GDVOF1035 | GDVOF1040 | GDVOF1045 | 8405-PP-OF-004 | PRE-ENGINEERING JACKET FACE DIVING SURVEY PROCEDURE | 1 | 2022-02-02 | 1 | 2022-02-02 | 2022-03-02 | 2022-03-23 | 0 | 0 | 0
A.1.7.5 | CA0000-51-PRO-0020 | GDVOF1065 | GDVOF1070 | GDVOF1075 | 8405-PP-OF-005 | PRE-ENGINEERING ROV SURVEY PROCEDURE (JACKET FACE SURVEY, PLATFORM APPROACH & CROSSING) | 1 | 2022-02-16 | 1 | 2022-02-16 | 2022-03-03 | 2022-03-17 | 0 | 0 | 0
A.1.7.6 | CA0000-51-PRO-0021 | GDVOF1645 | GDVOF1655 | GDVOF1665 | 8405-PP-OF-006 | PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY PROCEDURE | 1 | 2022-06-13 | 1 | 2022-06-14 | 2022-07-15 | 2022-08-12 | 1 | 0 | 0
A.1.7.7 | CA0000-51-PRO-0022 | GDVOF1050 | GDVOF1055 | GDVOF1060 | 8405-PP-OF-007 | POSITIONING AND INSTALLATION SURVEY PROCEDURE | 1 | 2022-08-30 | 1 | 2022-08-30 | 2022-09-20 | 2022-10-11 | 0 | 0 | 0
A.1.7.8 | CA0000-51-PRO-0023 | GDVOF1100 | GDVOF1105 | GDVOF1110 | 8405-PP-OF-008 | PIPELINE BASELINE SURVEY PROCEDURE | 1 | 2022-05-23 | 1 | 2022-05-23 | 2022-06-20 | 2022-07-21 | 0 | 0 | 0
A.1.7.9 | CA0000-51-RPT-0002 | GDVOF1120 | GDVOF1125 | GDVOF1130 | 8405-PP-OF-009 | PIPELINE BASELINE SURVEY REPORT | 1 | 2024-01-31 | 1 | 2024-01-31 | 2024-02-29 | 2024-03-28 | 0 | 0 | 0
A.1.7.10 | CA0000-51-RPT-0003 | GDVOF1085 | GDVOF1085 | GDVOF1085 | 8405-PP-OF-010 | PRE-ENGINEERING GEOPHYSICAL SURVEY REPORT | 1 | 2022-04-06 | 1 | 2022-04-26 | 2022-04-26 | 2022-04-26 | 20 | 0 | 0
A.1.7.11 | CA0000-51-RPT-0004 |  |  |  | 8405-PP-OF-011 | PRE-ENGINEERING GEOTECHNICAL SURVEY REPORT | 1 | 2022-04-10 | 1 |  |  |  | 0 | 0 | 0
A.1.7.12 | CA0000-51-RPT-0005 | GDVOF1095 | GDVOF1095 | GDVOF1095 | 8405-PP-OF-012 | PRE-CONSTRUCTION ANCHOR CLEARANCE SURVEY REPORT | 2 | 2022-12-08 | 2 | 2022-12-16 | 2022-12-16 | 2022-12-16 | 8 | 0 | 0
A.1.7.13 | CA0000-51-RPT-0006 | GDVOF1090 | GDVOF1090 | GDVOF1090 | 8405-PP-OF-013 | PRE-ENGINEERING ROV/CROSSING SURVEY REPORT | 2 | 2022-04-29 | 2 | 2022-05-26 | 2022-05-26 | 2022-05-26 | 27 | 0 | 0
A.1.7.14 | CA0000-51-PRO-0024 | GDVOF1140 | GDVOF1145 | GDVOF1150 | 8405-PP-OF-014 | PIPELINE/CABLE/UMBILICAL AS-BUILT SURVEY PROCEDURE | 1 | 2022-07-21 | 1 | 2022-07-21 | 2022-08-18 | 2022-09-12 | 0 | 0 | 0
A.1.7.15 | CA0000-51-PRO-0025 | GDVOF1155 | GDVOF1160 | GDVOF1165 | 8405-PP-OF-015 | PIPELINE/CABLE/UMBILICAL AS LAID SURVEY PROCEDURE | 1 | 2022-07-21 | 1 | 2022-07-21 | 2022-08-18 | 2022-09-12 | 0 | 0 | 0
A.1.7.16 | CA0000-51-RPT-0007 | GDVOF1135 | GDVOF1135 | GDVOF1135 | 8405-PP-OF-016 | PIPELINE/CABLE/UMBILICAL AS-BUILT SURVEY REPORT | 2 | 2024-04-05 | 2 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 25 | 0 | 0
A.1.7.17 | CA0000-51-RPT-0008 | GDVOF1115 | GDVOF1115 | GDVOF1115 | 8405-PP-OF-017 | PIPELINE/CABLE/UMBILICAL AS LAID SURVEY REPORT | 2 | 2024-04-08 | 2 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 22 | 0 | 0
A.1.7.18 | CA0000-51-PRO-0026 | GDVOF1170 | GDVOF1175 | GDVOF1180 | 8405-PP-OF-018 | ANCHOR HANDLING PROCEDURE FOR GRAVITY ANCHORS BY HAMMER HEAD CRANE VESSEL | 1 | 2022-07-21 | 1 | 2022-07-21 | 2022-08-18 | 2022-09-12 | 0 | 0 | 0
A.1.7.19 | CA0000-51-PRO-0027 | GDVOF1185 | GDVOF1190 | GDVOF1195 | 8405-PP-OF-019 | ANCHOR HANDLING AND MOORING PROCEDURE FOR WORK BOATS | 1 | 2022-07-21 | 1 | 2022-07-21 | 2022-08-18 | 2022-09-15 | 0 | 0 | 0
A.1.7.20 | CA0000-51-PRO-0028 | GDVOF1200 | GDVOF1205 | GDVOF1210 | 8405-PP-OF-020 | ANCHOR HANDLING AND MOORING PROCEDURE FOR FLOATING BARGES | 1 | 2022-08-24 | 1 | 2022-08-24 | 2022-09-21 | 2022-10-14 | 0 | 0 | 0
A.1.7.21 | CA0000-51-PRO-0029 | GDVOF1215 | GDVOF1220 | GDVOF1225 | 8405-PP-OF-021 | ANCHOR HANDLING AND MOORING PROCEDURE FOR JACK UP BARGES | 1 | 2022-08-30 | 1 | 2022-08-30 | 2022-09-27 | 2022-10-13 | 0 | 0 | 0
A.1.7.22 | CA0000-51-PRO-0030 | GDVOF1230 | GDVOF1235 | GDVOF1240 | 8405-PP-OF-022 | FREE SPANS CORRECTION PROCEURE | 1 | 2022-07-27 | 1 | 2022-07-27 | 2022-08-24 | 2022-09-21 | 0 | 0 | 0
A.1.7.23 | CA0000-51-PRO-0031 | GDVOF1265 | GDVOF1270 | GDVOF1275 | 8405-PP-OF-023 | SLEEPERS/MATTRESS/GROUT BAG INSTALLATION PROCEDURES | 1 | 2022-07-27 | 1 | 2022-07-27 | 2022-08-17 | 2022-09-28 | 0 | 0 | 0
A.1.7.24 | CA0000-51-PRO-0032 | GDVOF1245 | GDVOF1250 | GDVOF1255 | 8405-PP-OF-024 | PIPELINE INFILL MATERIAL FIELD JOINT COATING PROCEDURE | 1 | 2022-07-27 | 1 | 2022-07-27 | 2022-08-24 | 2022-09-21 | 0 | 0 | 0
A.1.7.25 | CA0000-51-PRO-0033 | GDVOF1280 | GDVOF1285 | GDVOF1290 | 8405-PP-OF-025 | PIPELINE ANTI-CORROSION FIELD JOINT COATING PROCEDURE | 1 | 2022-08-24 | 1 | 2022-08-24 | 2022-09-14 | 2022-09-30 | 0 | 0 | 0
A.1.7.26 | CA0000-51-MAN-0001 | GDVOF1295 | GDVOF1300 | GDVOF1305 | 8405-PP-OF-026 | PIPELINES INSTALLATION MANUAL | 2 | 2022-08-30 | 2 | 2022-08-30 | 2022-09-27 | 2022-10-17 | 0 | 0 | 0
A.1.7.27 | CA0000-51-PRO-0034 |  |  |  | 8405-PP-OF-027 | UMBILICALS INSTALLATION MANUAL | 1 | 2023-08-12 | 1 |  |  |  | 0 | 0 | 0
A.1.7.28 | CA0000-51-PRO-0036 | GDVOF1340 | GDVOF1345 | GDVOF1350 | 8405-PP-OF-029 | CABLE INSTALLATION MANUAL | 1 | 2022-08-30 | 1 | 2022-08-30 | 2022-09-27 | 2022-11-08 | 0 | 0 | 0
A.1.7.29 | CA0000-51-PRO-0037 | GDVOF1355 | GDVOF1360 | GDVOF1365 | 8405-PP-OF-030 | ZIRKU ISLAND PIPELINES SHORE PULL PROCEDURE | 1 | 2022-08-30 | 1 | 2022-08-30 | 2022-09-13 | 2022-09-27 | 0 | 0 | 0
A.1.7.30 | CA0000-51-PRO-0055 |  |  |  | 8405-PP-ON-021 | ARZANAH ISLAND (AT EAST SIDE) PIPELINES SHORE PULL PROCEDURE | 1 | 2023-01-06 | 1 |  |  |  | 0 | 0 | 0
A.1.7.31 | CA0000-51-PRO-0056 |  |  |  | 8405-PP-ON-022 | ARZANAH ISLAND (AT SOUTH SIDE) PIPELINES SHORE PULL PROCEDURE | 1 | 2023-01-06 | 1 |  |  |  | 0 | 0 | 0
A.1.7.32 | CA0000-51-PRO-0038 | GDVOF1370 | GDVOF1375 | GDVOF1380 | 8405-PP-OF-031 | RISER (STALK-IN) INSTALLATION PROCEDURE | 1 | 2022-08-30 | 1 | 2022-08-30 | 2022-09-27 | 2022-10-13 | 0 | 0 | 0
A.1.7.33 | CA0000-51-PRO-0039 | GDVOF1385 | GDVOF1390 | GDVOF1395 | 8405-PP-OF-032 | MID LINE SURFCAE TIE IN(s) INSTALLATION PROCEDURE | 1 | 2022-08-30 | 1 | 2022-08-30 | 2022-09-27 | 2022-10-13 | 0 | 0 | 0
A.1.7.34 | CA0000-51-PRO-0040 | GDVOF1400 | GDVOF1405 | GDVOF1410 | 8405-PP-OF-033 | J-TUBE AND ASSOCIATED CLAMPS INSTALLATION PROCEDURE | 1 | 2022-05-30 | 1 | 2022-05-30 | 2022-06-27 | 2022-07-28 | 0 | 0 | 0
A.1.7.35 | CA0000-51-PRO-0041 | GDVOF1415 | GDVOF1420 | GDVOF1425 | 8405-PP-OF-034 | NEW WHP-10 DECK INSTALLATION PROCEDURE | 1 | 2022-05-30 | 1 | 2022-05-30 | 2022-06-27 | 2022-07-28 | 0 | 0 | 0
A.1.7.36 | CA0000-51-PRO-0043 | GDVOF1445 | GDVOF1450 | GDVOF1455 | 8405-PP-OF-036 | DEMOLITION OF EXISTING DECK AND NEW DECK INSTALLATION PROCEDURE FOR HD-3 | 1 | 2022-05-30 | 1 | 2022-05-30 | 2022-06-27 | 2022-07-28 | 0 | 0 | 0
A.1.7.37 | CA0000-51-PRO-0045 | GDVOF1475 | GDVOF1480 | GDVOF1485 | 8405-PP-OF-038 | PIPELINES FLOODING, GAUGING, CLEANING AND HYDROTESTING PROCEDURE | 1 | 2022-06-06 | 1 | 2022-06-06 | 2022-07-04 | 2022-08-04 | 0 | 0 | 0
A.1.7.38 | CA0000-51-MES-0004 | GDVOF1520 | GDVOF1525 | GDVOF1530 | 8405-PP-OF-041 | METHOD STATEMENT FOR CIVIL WORKS FOR SHOREPULL | 1 | 2022-08-24 | 1 | 2022-08-24 | 2022-09-21 | 2022-10-19 | 0 | 0 | 0
A.1.7.39 | CA0000-51-PRO-0048 | GDVOF1535 | GDVOF1540 | GDVOF1545 | 8405-PP-OF-042 | OFFSHORE HOOK-UP PROCEDURE | 1 | 2022-08-24 | 1 | 2022-08-24 | 2022-09-21 | 2022-10-19 | 0 | 0 | 0
A.1.7.40 | CA0000-51-PRO-0049 | GDVOF1550 | GDVOF1555 | GDVOF1560 | 8405-PP-OF-043 | PIPELINES CALIPER PIGGING PROCEDURE | 1 | 2022-08-25 | 1 | 2022-08-25 | 2022-09-22 | 2022-10-20 | 0 | 0 | 0
A.1.7.41 | CA0000-51-PRO-0050 | GDVOF1565 | GDVOF1570 | GDVOF1575 | 8405-PP-OF-044 | PIPELINES Intelligent PIGGING PROCEDURE | 1 | 2022-08-30 | 1 | 2022-08-30 | 2022-09-27 | 2022-10-18 | 0 | 0 | 0
A.1.7.42 | CA0000-51-PRO-0051 | GDVOF1580 | GDVOF1585 | GDVOF1590 | 8405-PP-OF-045 | PIPELINES DEWATERING, DRYING AND NITROGEN PURGING PROCEDURE | 1 | 2022-08-30 | 1 | 2022-08-30 | 2022-09-27 | 2022-10-18 | 0 | 0 | 0
A.1.7.43 | CA0000-51-PRO-0052 | GDVOF1595 | GDVOF1600 | GDVOF1605 | 8405-PP-OF-046 | CABLE TRANSPOOLIING PROCEDURE | 2 | 2022-09-06 | 2 | 2022-09-06 | 2022-10-04 | 2022-11-01 | 0 | 0 | 0
A.1.7.44 | CA0000-51-PRO-0053 | GDVOF1610 | GDVOF1615 | GDVOF1620 | 8405-PP-OF-047 | UMBILICAL TRANSPOOLIING PROCEDURE | 1 | 2022-09-27 | 1 | 2022-09-27 | 2022-10-25 | 2022-11-22 | 0 | 0 | 0
A.1.7.45 | CA0000-51-PRO-0054 | GDVOF1625 | GDVOF1630 | GDVOF1635 | 8405-PP-OF-048 | TRENCHING & BACKFILLING PROCEDURE | 1 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-31 | 2022-09-28 | 0 | 0 | 0
A.1.7.46 | CA0000-51-PRO-0057 |  |  |  | 8405-PP-OF-049 | 3D LASER SCAN SURVEY PROCEDURE | 2 | 2022-03-30 | 2 |  |  |  | 0 | 0 | 0
A.1.7.47 | CA0000-51-PRO-0058 |  |  |  | 8405-PP-OF-050 | ROV AS-BUILT SURVEY PROCEDURE | 1 | 2022-03-02 | 1 |  |  |  | 0 | 0 | 0
A.1.7.48 | CA0000-51-PRO-0059 |  |  |  | 8405-PP-OF-051 | UMBILICAL PROTECTION, PACKAGING, STORAGE AND TRANSPORTATION GUIDELINES / PROCEDURES. | 1 | 2022-05-02 | 1 |  |  |  | 0 | 0 | 0
A.1.7.49 | CA0000-51-PRO-0060 |  |  |  | 8405-PP-OF-052 | UMBILICAL HANDLING, PULL-IN & HOOK-UP PROCEDURES / GUIDELINES. | 1 | 2023-08-12 | 1 |  |  |  | 0 | 0 | 0
A.1.7.50 | CA0000-51-PRO-0061 |  |  |  | 8405-PP-OF-053 | PIPELINE PRESERVATION PROCEDURE | 1 | 2023-04-10 | 1 |  |  |  | 0 | 0 | 0
A.1.7.51 | CA0000-51-SOW-0001 |  |  |  | 8405-PP-OF-054 | SCOPE OF WORK FOR TRANSPORTATIONOF UMBILICALS FROM VENDOR |  | 2022-04-07 | 2
A.1.7.52 | CA0000-52-REP-0002 |  |  |  | 8405-PP-HS-024 | CONSTRUCTION BARGE QRA/SAFETY CASE (REPORT) | 1 (Old Barges approval) |  | 1
A.1.7.53 | CA0000-51-PLN-0001 |  |  |  | 8405-PP-OF-055 | TRANSPORTATION MANAGEMENT PLAN |  | 2022-12-20 | 1 |  |  |  | 0 | 0 | 0
A.1.7.54 | CA0000-51-RPT-0009 |  |  |  | 8405-PP-OF-056 | PRE - ENGINEERING GEOTECHANICAL SURVEY AND PIPE SOIL INTERACTION REPORT SURVEY REPORT |  |  | 2
A.1.7.55 | CA0000-51-PRO-0063 |  |  |  | 8405-PP-OF-057 | UMBILICALS INSTALLATION PROCEURE |  | 2023-03-25 | 2
A.1.7.56 | CA0000-51-PRO-0064 |  |  |  | 8405-PP-OF-058 | NEW HD-T4 DECK INSTALLATION PROCEDURE |  | 2022-12-20 | 2
A.1.7.57 | CA0000-51-SOW-0002 |  |  |  | 8405-PP-OF-059 | SCOPE OF WORK FOR TRENCHING AND BACKFILLING |  | 2022-06-09 | 2
A.1.7.58 | CA0000-51-SOW-0003 |  |  |  | 8405-PP-OF-060 | SCOPE OF WORK FOR ONSHORE WORKS & ASSISTANCE |  | 2022-06-17 | 2
A.1.7.59 | CA0000-51-SOW-0004 |  |  |  | 8405-PP-OF-061 | SCOPE OF WORK FOR LAYING OF SUBSEA UMBILICAL CABLES |  | 2022-07-15 | 2
A.1.8 | COMMISSIONING | [11 empty] | 0 | 0 | 0
A.1.8.1 | CA0000-54-REG-0001 | GDVCG1000 | GDVCG1005 | GDVCG1010 | 8405-PP-CM-001 | COMMISSIONING DELIVERABLE REGISTER | 2 | 2022-06-15 | 2 | 2022-06-15 | 2022-08-01 | 2022-09-12 | 0 | 0 | 0
A.1.8.2 | CA0000-54-PRO-0001 | GDVCG1015 | GDVCG1020 | GDVCG1025 | 8405-PP-CM-002 | PRECOMMISSIONING AND COMMISSIONING PROCEDURE | 1 | 2022-06-22 | 1 | 2022-06-22 | 2022-08-08 | 2022-09-19 | 0 | 0 | 0
A.1.8.3 | CA0000-54-LST-0001 | GDVCG1030 | GDVCG1035 | GDVCG1040 | 8405-PP-CM-003 | SYSTEM / SUBSYSTEM LIST | 1 | 2022-07-06 | 1 | 2022-07-06 | 2022-08-22 | 2022-10-03 | 0 | 0 | 0
A.1.8.4 | CA0000-54-PRO-0002 | GDVCG1045 | GDVCG1050 | GDVCG1055 | 8405-PP-CM-004 | PERMIT TO WORK (PTW) PROCEDURE | 1 | 2022-07-25 | 1 | 2022-07-25 | 2022-09-05 | 2022-10-17 | 0 | 0 | 0
A.1.8.5 | CA0000-54-PLN-0002 | GDVCG1150 | GDVCG1150 | GDVCG1150 | 8405-PP-CM-005 | VENDOR MOBILIZATION PLAN | 3 | 2022-08-01 | 3 | 2022-09-05 | 2022-09-05 | 2022-09-05 | 35 | 0 | 0
A.1.8.6 | CA0000-54-PRO-0003 | GDVCG1075 | GDVCG1080 | GDVCG1085 | 8405-PP-CM-006 | LIST OF OPERATIONAL TEST PROCEDURES | 1 | 2022-07-25 | 1 | 2022-07-25 | 2022-09-05 | 2022-10-17 | 0 | 0 | 0
A.1.8.7 | CA0000-54-PRO-0004 | GDVCG1090 | GDVCG1095 | GDVCG1100 | 8405-PP-CM-007 | PUNCH LIST PROCEDURE | 1 | 2022-07-25 | 1 | 2022-07-25 | 2022-09-05 | 2022-10-03 | 0 | 0 | 0
A.1.8.8 | CA0000-54-PRO-0005 | GDVCG1105 | GDVCG1110 | GDVCG1115 | 8405-PP-CM-008 | PRE-COMMISSIONING / COMMISSIONING TEST RECORDS AND RESPONSIBILITY MATRIX | 2 | 2022-07-25 | 2 | 2022-07-25 | 2022-09-05 | 2022-10-17 | 0 | 0 | 0
A.1.8.9 | CA0000-54-PRO-0006 | GDVCG1120 | GDVCG1125 | GDVCG1130 | 8405-PP-CM-009 | CO-CONSOLE PROCEDURE | 2 | 2022-07-18 | 2 | 2022-07-18 | 2022-08-29 | 2022-10-10 | 0 | 0 | 0
A.1.8.10 | CA0000-54-GDD-0001 | GDVCG1135 | GDVCG1140 | GDVCG1145 | 8405-PP-CM-010 | FIRST FILL INVENTORY, CONSUMPTION AND TOP UP SCHEDULE (INCLUDING CHEMICALS, HYDRAULIC OIL) | 1 | 2022-07-25 | 1 | 2022-07-25 | 2022-09-05 | 2022-10-12 | 0 | 0 | 0
A.1.8.11 | CA0000-54-PLN-0001 | GDVCG1155 | GDVCG1160 | GDVCG1165 | 8405-PP-CM-011 | COMMISSIONING EXECUTION PLAN | 1 | 2022-07-25 | 1 | 2022-07-25 | 2022-09-05 | 2022-10-17 | 0 | 0 | 0
A.1.8.12 | CA0000-54-PRO-0007 | GDVCG1170 | GDVCG1175 | GDVCG1180 | 8405-PP-CM-012 | N2-HE LEAK TEST & Inserting PROCEDURE | 1 | 2022-07-25 | 1 | 2022-07-25 | 2022-09-05 | 2022-10-17 | 0 | 0 | 0
A.1.8.13 | CA0000-54-PRO-0008 | GDVCG1185 | GDVCG1190 | GDVCG1195 | 8405-PP-CM-013 | HANDOVER PROCEDURE | 1 | 2022-11-28 | 1 | 2022-11-28 | 2023-01-11 | 2023-02-22 | 0 | 0 | 0
A.1.8.14 | CA0000-54-MES-0001 | GDVCG1200 | GDVCG1205 | GDVCG1210 | 8405-PP-CM-014 | METHOD STATEMENT FOR INSTRUMENT LOOP CHECKS & FUNCTION TESTS RELATED TO DCS, ESD AND F&G SYSTEMS | 1 | 2022-07-25 | 1 | 2022-07-25 | 2022-08-31 | 2022-10-17 | 0 | 0 | 0
A.1.8.15 | CA0000-54-PRO-0009 | GDVCG1220 | GDVCG1220 | GDVCG1220 | 8405-PP-CM-015 | PROJECT PRESERVATION PROCEDURE | 1 | 2022-10-24 | 1 | 2022-11-14 | 2022-11-14 | 2022-11-14 | 21 | 0 | 0
A.1.8.16 | CA0000-54-PRO-0010 | GDVCG1215 | GDVCG1225 | GDVCG1230 | 8405-PP-CM-016 | SYSTEM OPERATION TEST PROCEDURES | 1 | 2022-11-14 | 1 | 2022-11-14 | 2022-12-28 | 2023-02-08 | 0 | 0 | 0
A.1.8.17 | CA0000-54-LST-0002 | GDVCG1235 | GDVCG1240 | GDVCG1245 | 8405-PP-CM-017 | LIST OF SPECIAL TOOLS AND CONSUMABLES | 2 | 2022-10-17 | 2 | 2022-10-17 | 2022-11-28 | 2023-01-11 | 0 | 0 | 0
A.1.8.18 | CA0000-54-LST-0003 | GDVCG1250 | GDVCG1255 | GDVCG1260 | 8405-PP-CM-018 | LIST OF COMMISSIONING SPARE PARTS | 1 | 2022-11-14 | 1 | 2022-11-14 | 2022-12-28 | 2023-02-22 | 0 | 0 | 0
A.1.8.19 | CA0000-54-GDD-0002 | GDVCG1265 | GDVCG1270 | GDVCG1275 | 8405-PP-CM-019 | PERFORMANCE TEST | 1 | 2022-12-14 | 1 | 2022-12-14 | 2023-01-25 | 2023-03-08 | 0 | 0 | 0
A.1.8.20 | CA0000-54-PRO-0011 | GDVCG1280 | GDVCG1285 | GDVCG1290 | 8405-PP-CM-020 | START-UP PROCEDURE | 1 | 2023-01-11 | 1 | 2023-01-11 | 2023-02-22 | 2023-04-05 | 0 | 0 | 0
A.1.8.21 | CA0000-54-PRO-0012 | GDVCG1060 | GDVCG1065 | GDVCG1070 | 8405-PP-CM-021 | COMMISSIONING PERMIT TO WORK (PTW) PROCEDURE | 1 | 2022-07-25 | 1 | 2022-07-25 | 2022-09-05 | 2022-10-17 | 0 | 0 | 0
A.1.8.22 | CA0000-54-PRO-0013 |  |  |  | 8405-PP-CM-022 | PRE-START-UP ACTIVITIES PROCEDURE | 1 | 2024-07-21 | 1 |  |  |  | 0 | 0 | 0
A.1.8.23 | CA0000-54-PRO-0014 |  |  |  | 8405-PP-CM-023 | AS COMMISSIONED DOCUMENTATION PROCEDURE | 1 | 2022-11-22 | 1 |  |  |  | 0 | 0 | 0
A.1.8.24 | CA0000-54-PRO-0015 |  |  |  | 8405-PP-CM-024 | MODIFICATIONS PROCEDURE | 1 | 2022-11-20 | 1 |  |  |  | 0 | 0 | 0
A.1.8.25 | CA0000-54-COD-0001 |  |  |  | 8405-PP-CM-025 | RFC/RFSU & HAND OVER DOSSIER | 1 | 2024-09-20 | 1 |  |  |  | 0 | 0 | 0
A.1.8.26 | CA0000-54-PHL-0001 |  |  |  | 8405-PP-CM-026 | MANNING PHILOSOPHY | 1 | 2024-05-21 | 1 |  |  |  | 0 | 0 | 0
A.1.8.27 | CA0000-54-PRO-0016 |  |  |  | 8405-PP-CM-027 | SAT (SITE ACCEPTANCE TEST) PROCEDURE AND REPORT. | 1 | 2023-06-10 | 1 |  |  |  | 0 | 0 | 0
A.1.8.28 | CA0000-54-PRO-0017 |  |  |  | 8405-PP-CM-028 | ISOLATION PLAN/PROCEDURES | 1 | 2023-05-14 | 1 |  |  |  | 0 | 0 | 0
A.1.8.29 | CA0000-54-REP-0001 |  |  |  | 8405-PP-CM-029 | CMMS INCLUDING DATA ENTRY TO SAP SYSTEM | 1 | 2023-12-23 | 1 |  |  |  | 0 | 0 | 0
A.1.8.30 | CA0000-54-PRO-0018 |  |  |  | 8405-PP-CM-030 | LOCK-OUT / TAG-OUT PROCEDURE | 1 | 2023-04-10 | 1 |  |  |  | 0 | 0 | 0
A.1.8.31 | CA0000-54-PRO-0019 |  |  |  | 8405-PP-CM-031 | CONSTRUCTION & COMMISSIONING PTW BRIDGING DOCUMENT | 1 | 2022-11-17 | 1 |  |  |  | 0 | 0 | 0
A.1.8.32 | CA0000-54-DWG-0001 |  |  |  | 8405-PP-CM-032 | MARKED-UP CRITICAL DRAWINGS AND DOCUMENTS | 1 | 2023-02-07 | 1
| CA0000-51-PRO-0016 | GDVYF1245 | GDVYF1250 | GDVYF1255 | 8405-PP-ON-020 | GROSS AIR LEAK TEST PROCEDURE | 1 | 2022-06-15 | 1 | 2022-06-15 | 2022-07-18 | 2022-08-15 | 0 | 0 | 0